## Issues Log
ID | Date raised | Reporter Name | Issue | Description | Potential Impact/Priority | Outcome | Dependencies | MHHS Products impacted | REC / BSC Products impacted | Classification | Status
Drafting-01 | sprint 1 end | Sarah Jones Matt McKeon | Terminology | MHHS design artefects use terminology from the TOM which needs to be reflected in the codes. Where possible, a joint REC / BSC approach should be agreed to avoid future confusion | High | Joint list of defined terms agreed - ongoing |  | Various | Various | Public | Open
Drafting-02 |  | Sarah Jones Matt McKeon | Reflection of DIP interfaces within REC Schedules and BSCPs | The design artefacts show messages sent to and from the DIP. Proposed approach reflected in prototyping that the DIP is treated as a transfer mechanism so messages are defined as being sent by the original sender to the final recipient(s) | High | Proposed approach reflected in prototyping output and agreed with CDWG |  | Various | Various | Public | Closed
Drafting-03 |  | Sarah Jones Matt McKeon | Hosting DIP interface definitions | As the Energy Market Data Spec it is assumed that the EMAR will be used to host the new data item and message definitions introduced by MHHS, noting that the metadata will be owned and governed by the relevant code | High | CCAG confirmation that interfaces will be hosted in the EMDS |  | DIP Interface Specification (DES138) | Energy Market Data Specification (not REC itself) | Public | Closed
Drafting-04 |  | Sarah Jones Matt McKeon | SLAs for sending DIP synch responses | The MHHS design artefact defines non funtional requirements for the sending of DIP responses and associated error messages. Should there be a Settlement Data Management BSCP (similar to REC Switching Data Management Schedule) to cover this. The BSCP could include the definition of DIP message types and synch validation / SLA and potentially also ISD. | High | MHHS Programme and Elexon to agree roles and responsibilities for drafting this text and where it sits in the plan |  | Open | End to end non functional requirements E2E002 | Public | Open
Drafting-05 |  | Sarah Jones Matt McKeon | MEM and Data Service section headings | The REC Metering Operations Schedule already breaks down the provisions into different processes (aligned to the gas provisions). These processes differ from the defined processes in the MHHS design artefacted. Discussion required to agree how processes are documented in the various codes. | Med | Conclusion that drafting should focus on the ease of understanding for users rather than reflecting the design artefact structure. Drafters to determine the best approach and discuss specific issues with parties as required. In addition, for REC it was suggested that gas and electricity sections are separated. |  | Various | REC Metering Operations Schedule. New Data Service BSCP | Public | Closed
Drafting-06 |  | Sarah Jones Matt McKeon | Location of DNO obligations | Current duplication of obligations between DCUSA, REC and BSC to be resolved. Proposing the end to end metering processes are captured in the REC Metering Operation Schedule (including any DNO obligations). BSCP515 to just retain settlement specific processes | High | Ongoing discussions to support traceability work. Proposed approach applied to drafting for Disconnection process whereby the physical works are defined in DCUSA and not duplicated in the BSC. |  | Open | Various | Public | Open
Drafting-07 |  | Sarah Jones Matt McKeon | Scope of end to end processes | BSCPs typically only show the interactions involving the role that they apply to, so miss out any interim steps. To consider how Supplier to SMRS upstream steps should be reflected. REC drafting captures the full end to end as there is no separate tables for ERDS processes. | Med | Ongoing discussion on approach to BSC drafting |  | Open | Various | Public | Open
Drafting-08 |  | Sarah Jones Matt McKeon | Approach to managing branches within business processes | Where there is optionality that depends on meter type, e.g. Smart vs Trad, the approach needs to be agreed on whether to have one overarching process that only branches in individual steps where it says “For a Smart Meter, do [x]“ and “For a Traditional Meter, do [y]“, or have a section that is Smart only and another that is Trad only. The latter creates a bit of duplication but it means for Smart only SDSs they can just follow the Smart only process. As those become the prevailing type of meter, fewer actors will have to deal with Trad MTDs. | Med | Conclusion that drafting should focus on the ease of understanding for users rather than reflecting the design artefact structure. Drafters to determine the best approach and discuss specific issues with parties as required. |  | Various | REC Metering Operations Schedule. New Data Service BSCP | Public | Closed
Drafting-09 |  | Sarah Jones Matt McKeon | Whether MEMs and Data Services are treated as Supplier Agents | BSC Section j defines the approach to governing supplier agents. Clarity is required on whether the MEMs and Data Services will be deemed to be Supplier Agents of whether these provisions need amending | High | Programme position previously shared is that there will be no change to the supplier hub principle |  | N/A | BSC Section J Various other BSC and REC references | Public | Closed
Drafting-10 |  | Sarah Jones Matt McKeon | MHHS Interface Names | Can we rename all the MHHS interfaces to reflect code terminology e.g. IF031 refers to Service Provider Appointment whereas we refer to agents elsewhere in the codes | Med | Ongoing | Workoff plan closing - will seek advice from CDWG | Open | Interface Catalogue | Public | Open
Drafting-11 |  | Sarah Jones Matt McKeon | Numbering and cross references | Approach to drafting will leave cross references and numbering placeholders with a final review in the consistency check at the end | Med | Reviewers to focus on content and not numbering / cross references |  | Various | Various | Public | Closed
Drafting 12 |  | Sarah Jones Matt McKeon | Interface validation rules | Validation rules associated with the new MHHS interfaces are included in the interface catalogue. Should these be captured within the Energy Market Data Spec or within the relevant BSCPs / REC Schedules | Med | To be discussed with CDWG |  | Open | Interface Catalogue | Public | Open
Drafting 13 |  | Sarah Jones Matt McKeon | Definition of data items used within ECS reports | Linked to Drafting Principle 03, the expectation is that the DIP interfaces will be defined in the Energy Market Data Spec. However, ECS reports will be treated slightly differently, with the reports included in the SVA Data Catalogue as well for a period of time. Due to conventions for defining decimal numbers differing between codes, these will be different, with each location applying their own convention. | Med | To be discussed with CDWG | Linked to the workoff plan closing | Open | ECS Reporting Catalogue | Public | Open
Drafting 14 |  | Becca to confirm | Service Data Rentention Periods | BSCP11 puts an obligation for Parties and Agents to store settlement data for 40 months. The reduction in the Settlement Timetable post transition will be 24 months for Settlement Data. Will this issue be resolved in the code drafting? |  | Drafting will be reflected in BSCP11 and will be implemented with the new settlement timetable and all will align to 24 months for settlement dates after the cut-over |  |  |  | Public | Open

## Sheet1 (hidden)
Open
Closed
Internal
External