## Tier 2 Milestones
Wave | Tier | Milestone ID | Task Name | Task Description | Old Date | New Date | Description of Change
1 | T2 | T2-QU-0150 | Qualification Wave 1 Participants Qualification approved by BSC PAB and REC Manager | BSC PAB and REC Manager approval of Qualification for Wave 1 Participants who have met all requirements | 2025-09-01 | 29/08/2025 | Wording of title amended to make it clearer that this approval of MHHS Qualification rather than Qualification Testing which is just one aspect of Qualification. The date has been aligned to the QA&P.
2 | T2 | T2-QU-0200 | Qualification Wave 2 Participants Qualification approved by BSC PAB and REC Manager | BSC PAB and REC Manager approval of Qualification for Wave 2 Participants who have met all requirements | 29/9/2025 | 31/10/2025 | Wording of title amended to make it clearer that this approval of MHHS Qualification rather than Qualification Testing which is just one aspect of Qualification. The date has been aligned to the QA&P.
3 | T2 | T2-QU-0250 | Qualification Wave 3 Participants Qualification approved by BSC PAB and REC Manager | BSC PAB and REC Manager approval of Qualification for Wave 3 Participants who have met all requirements | 27/10/2025 | 19/12/2025 | Wording of title amended to make it clearer that this approval of MHHS Qualification rather than Qualification Testing which is just one aspect of Qualification. The date has been aligned to the QA&P.
4 | T2 | T2-QU-0300 | Qualification Wave 4 Participants Qualification approved by BSC PAB and REC Manager | BSC PAB and REC Manager approval of Qualification for Wave 4 Participants who have met all requirements | 24/11/2025 | 27/02/2026 | Wording of title amended to make it clearer that this approval of MHHS Qualification rather than Qualification Testing which is just one aspect of Qualification. The date has been aligned to the QA&P.
REMOVE | T2 | T2-QU-0350 | BSC PAB & REC Manager approval of Qualification Testing Tranche 5 Completion | The end of Qualification Tranche 5 test execution is approved by PAB | 22/12/2025 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T2 | T2-QU-0400 | BSC PAB & REC Manager approval of Qualification Testing Tranche 6 Completion | The end of Qualification Tranche 6 test execution is approved by PAB | 19/1/2026 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T2 | T2-QU-0450 | BSC PAB & REC Manager approval of Qualification Testing Tranche 7 Completion | The end of Qualification Tranche 7 test execution is approved by PAB | 16/2/2026 | REMOVE | Removing due to reduction in number of Qualification Waves

## Tier 3 Milestones
Wave | Tier | Milestone ID | Task Name | Task Description | Old Date | New Date | Description of Change
Overall | T3 | T3-QU-0063 | Functional Testing elements of Qualification Approach & Plan v2 approved by REC Manager & BSC PAB | The approval by REC PAB and BSC PAB of the Functional Testing Approach & Plan for Qualification. | 2023-10-31 | 2024-03-28 | Updated milestone dates aligned to QA&P
Overall | T3 | T3-QU-0064 | Migration Testing elements of Qualification Approach & Plan v2 approved by REC PAB & BSC PAB | The approval by REC PAB and BSC PAB of the Migration Testing Approach & Plan for Qualification. | 2024-03-06 | 2024-03-28 | Updated milestone dates aligned to QA&P
Overall | T3 | T3-QU-0066 | Qualification Assessment Document v1 approved by REC PAB and BSC PAB | The approval by BSC PAB and REC PAB of the Qualification Assessment Document v1 | 2024-04-16 | 2024-03-28 | Updated milestone dates aligned to QA&P
Overall | T3 | T3-QU-0065 | Non-Functional Testing elements of Qualification Approach & Plan v3 approved by REC PAB & BSC PAB | The approval by REC PAB and BSC PAB of the Non Functional Testing Approach & Plan for Qualification. | 2024-05-30 | 2024-06-27 | Updated milestone dates aligned to QA&P
Overall | T3 | T3-QU-0012 | Confirmation of participant Qualification Wave allocation | The date by which the Code Bodies confirm to the programme the wave allocation for all participants taking part in Qualification Testing | 2024-06-08 | 2024-06-28 | Wording and date change to reflect the change to the allocation approach
Overall | T3 | T3-QU-0062 | Final Qualification Approach & Plan v4 approved by REC PAB & BSC PAB | The approval by REC PAB and BSC PAB of the Final Approach & Plan for Qualification. | 2024-08-14 | 2024-08-29 | Updated milestone dates aligned to QA&P
Overall | T3 | T3-QU-0067 | Qualification Assessment Document v2 approved by REC PAB and BSC PAB | The approval by BSC PAB and REC PAB of the Qualification Assessment Document v2 | 2024-10-25 | 2024-08-29 | Updated milestone dates aligned to QA&P
Overall | T3 | T3-QU-0068 | Operational Testing elements of Qualification Approach & Plan v4 approved by REC PAB & BSC PAB | The approval by BSC PAB and REC PAB of the Non Functional Testing Approach & Plan for Qualification. | 2024-08-14 | 2024-08-29 | Updated milestone dates aligned to QA&P
Overall | T3 | New | Qualification Testing Wave Readiness Confirmed | QAG approves that all preparation activities required to commence Qualification Testing Waves have been completed and assured. | New | 2025-01-23 | New Milestone to represent the overall entry to the Qualification Waves Phase
Overall | T3​ | New​ | Pre-Qualification Submission and PIT Test Plan Deadline for Submission ​ | The date by when participants who intend to qualify via wave a are expecting to submit their Pre-Qualification Submission and PIT Test Plan to Code Bodies. ​ | New​ | 26/04/2024​ | Wording and date change to reflect the change to the allocation approach​
1 | T3 | T3-QU-0017 | Qualification Wave 1 Participants' have started DIP Onboarding | The final date by which Wave 1 Qualification Test participants are expected to declare that their UIT environments have been stood up and that DIP Onboarding is underway. | 2024-11-04 | 2024-11-01 | Wording and date change to reflect the change to Waves
1 | T3​ | New​ | Qualification Wave 1 Participants to provide status of PIT completion and submit QT Test Plan | The final date by which Wave 1 Qualification Test participants are expected to have submitted their QT Test Plan and a status report for their PIT completion. | New​ | 29/11/2024​ | New milestone added to support participant planning​
1 | T3​ | New​ | Qualification Wave 1 Participants have submitted their Initial QAD​ | The final date of the submission window by which Wave 1 Qualification Test participants are expected to submit their initial QAD.​ | New​ | 20/12/2024​ | New milestone added to support participant planning​
1 | T3 | New | Qualification Wave 1 Participants have submitted PIT Test Completion Report and evidence for QT Entry | The final date by which Wave 1 Qualification Test participants are expected to submit their PIT Test Completion Report and evidence | New | 2024-12-20 | New milestone added to support participant planning​
1 | T3 | T3-QU-0016 | Qualification Test Plans for Wave 1 Participants approved | The date by which all Wave 1 participant QT Test Plans need to be approved by the Test Manager (MHHS Programme and Code Bodies informed) | 2024-11-04 | 2024-12-20 | Wording and date change to reflect the change to Waves
1 | T3 | T3-QU-0027 | Qualification Wave 1 Participant Test Readiness confirmed | Test Manager approves that all preparation activities required by participants to commence Qualification Testing Wave 1 have been completed and assured (MHHS Programme and Code Bodies informed) | 2025-01-13 | 2025-01-31 | Wording and date change to reflect the change to Waves
1 | T3 | T3-QU-0028 | Qualification Wave 1 QT Execution Start | The start of Qualification Wave 1 QT Execution is approved by the Test Manager (MHHS Programme and Code Bodies informed) | 2025-01-20 | 2025-02-03 | Wording and date change to reflect the change to Waves
1 | T3 | T3-QU-0054 | Qualfication Wave 1 QT Projected Execution End | The end of Qualification Wave 1 QT Execution is confirmed by the Test Manager (MHHS Programme and Code Bodies informed) | 2025-08-04 | 2025-06-13 | Wording and date change to reflect the change to Waves
1 | T3 | New | Qualification Wave 1 Participants have submitted their final QAD | The final date of the submission window by which Wave 1 Qualification Test participants are expected to submit their final QAD.​ | New | 2025-06-20 | New milestone added to support participant planning​
2 | T3 | T3-QU-0021 | Qualification Wave 2 Participants' have started DIP Onboarding | The final date by which Wave 2 Qualification Test participants are expected to declare that their UIT environments have been stood up and that DIP Onboarding is underway. | 2024-12-02 | 2025-01-06 | Wording and date change to reflect the change to Waves
2 | T3​ | New​ | Qualification Wave 2 Participants to provide status of PIT completion and submit QT Test Plan | The final date by which Wave 2 Qualification Test participants are expected to have submitted their QT Test Plan and a status report for their PIT completion. | New​ | 31/01/2025​ | New milestone added to support participant planning​
2 | T3 | T3-QU-0020 | Qualification Test Plans for Wave 2 Participants approved | The date by which all Wave 2 participant QT Test Plans need to be approved by the Test Manager (MHHS Programme and Code Bodies informed) | 2024-12-02 | 2025-02-21 | Wording and date change to reflect the change to Waves
2 | T3​ | New​ | Qualification Wave 2 Participants have submitted their Initial QAD​ | The final date of the submission window by which Wave 2 Qualification Test participants are expected to submit their initial QAD.​ | New​ | 21/02/2025​ | New milestone added to support participant planning​
2 | T3 | New | Qualification Wave 2 Participants have submitted PIT Test Completion Report and evidence for QT Entry | The final date by which Wave 2 Qualification Test participants are expected to submit their PIT Test Completion Report and evidence | New | 2025-02-21 | New milestone added to support participant planning​
2 | T3 | T3-QU-0033 | Qualification Wave 2 Participant Test Readiness confirmed | Test Manager approves that all preparation activities required by participants to commence Qualification Testing Wave 2 have been completed and assured (MHHS Programme and Code Bodies informed) | 2025-02-10 | 2025-03-31 | Wording and date change to reflect the change to Waves
2 | T3 | T3-QU-0034 | Qualification Wave 2 QT Execution Start | The start of Qualification Wave 2 Qualification Testing Execution is approved by the Test Manager (MHHS Programme and Code Bodies informed) | 2025-02-17 | 2025-04-01 | Wording and date change to reflect the change to Waves
2 | T3 | T3-QU-0055 | Qualfication Wave 2 QT Execution End | The end of Qualification Wave 2 QT Execution is confirmed by the Test Manager (MHHS Programme and Code Bodies informed) | 2025-09-01 | 2025-08-08 | Wording and date change to reflect the change to Waves
2 | T3 | New | Qualification Wave 2 Participants have submitted their final QAD | The final date of the submission window by which Wave 2 Qualification Test participants are expected to submit their final QAD.​ | New | 2025-08-15 | New milestone added to support participant planning​
3 | T3 | T3-QU-0025 | Qualification Wave 3 Participants' have started DIP Onboarding | The final date by which Wave 3 Qualification Test participants are expected to declare that their UIT environments have been stood up and that DIP Onboarding is underway. | 2024-12-30 | 2025-03-03 | Wording and date change to reflect the change to Waves
3 | T3​ | New​ | Qualification Wave 3 Participants to provide status of PIT completion and submit QT Test Plan | The final date by which Wave 3 Qualification Test participants are expected to have submitted their QT Test Plan and a status report for their PIT completion. | New​ | 2025-03-31 | New milestone added to support participant planning​
3 | T3​ | New​ | Qualification Wave 3 Participants have submitted PIT Test Completion Report and evidence for QT Entry​ | The final date by which Wave 3 Qualification Test participants are expected to submit their PIT Test Completion Report and evidence​ | New​ | 2025-04-18 | New milestone added to support participant planning​
3 | T3​ | New​ | Qualification Wave 3 Participants have submitted their Initial QAD​ | The final date of the submission window by which Wave 3 Qualification Test participants are expected to submit their initial QAD.​ | New​ | 18/04/2025​ | New milestone added to support participant planning​
3 | T3 | T3-QU-0024 | Qualification Test Plans for Wave 3 Participants approved | The date by which all Wave 3 participant QT Test Plans need to be approved by the Test Manager (MHHS Programme and Code Bodies informed) | 2024-12-30 | 2025-04-18 | Wording and date change to reflect the change to Waves
3 | T3 | T3-QU-0038 | Qualification Wave 3 Participant Test Readiness confirmed | Test Manager approves that all preparation activities required by participants to commence Qualification Testing Wave 3 have been completed and assured (MHHS Programme and Code Bodies informed) | 2025-03-10 | 2025-05-30 | Wording and date change to reflect the change to Waves
3 | T3 | T3-QU-0039 | Qualification Wave 3 QT Execution Start | The start of Qualification Wave 3 QT Execution is approved by the Test Manager (MHHS Programme and Code Bodies informed) | 2025-03-17 | 2025-06-02 | Wording and date change to reflect the change to Waves
3 | T3 | T3-QU-0056 | Qualfication Wave 3 QT Execution End | The end of Qualification Wave 3 QT Execution is confirmed by the Test Manager (MHHS Programme and Code Bodies informed) | 2025-09-29 | 2025-10-10 | Wording and date change to reflect the change to Waves
3 | T3 | New | Qualification Wave 3 Participants have submitted their final QAD | The final date of the submission window by which Wave 3 Qualification Test participants are expected to submit their final QAD.​ | New | 2025-10-17 | New milestone added to support participant planning​
4 | T3 | T3-QU-0031 | Qualification Wave 4 Participants' have started DIP Onboarding | The final date by which Wave 4 Qualification Test participants are expected to declare that their UIT environments have been stood up and that DIP Onboarding is underway. | 2025-01-27 | 2025-05-01 | Wording and date change to reflect the change to Waves
4 | T3​ | New​ | Qualification Wave 3 Participants to provide status of PIT completion and submit QT Test Plan | The final date by which Wave 3 Qualification Test participants are expected to have submitted their QT Test Plan and a status report for their PIT completion. | New​ | 2025-05-30 | New milestone added to support participant planning​
4 | T3​ | New​ | Qualification Wave 4 Participants have submitted PIT Test Completion Report and evidence for QT Entry​ | The final date by which Wave 4 Qualification Test participants are expected to submit their PIT Test Completion Report and evidence​ | New​ | 2025-06-20 | New milestone added to support participant planning​
4 | T3​ | New​ | Qualification Wave 4 Participants have submitted their Initial QAD​ | The final date of the submission window by which Wave 4 Qualification Test participants are expected to submit their initial QAD.​ | New​ | 2025-06-20 | New milestone added to support participant planning​
4 | T3 | T3-QU-0030 | Qualification Test Plans for Qualification Wave 4 Participants approved | The date by which all Wave 4 participant QT Test Plans need to be approved by the Test Manager (MHHS Programme and Code Bodies informed) | 2025-01-27 | 2025-06-20 | Wording and date change to reflect the change to Waves
4 | T3 | T3-QU-0043 | Qualification Wave 4 Participant Test Readiness confirmed | Test Manager approves that all preparation activities required by participants to commence Qualification Testing Wave 4 have been completed and assured (MHHS Programme and Code Bodies informed) | 2025-04-07 | 2025-07-31 | Wording and date change to reflect the change to Waves
4 | T3 | T3-QU-0044 | Qualification Wave 4 QT Execution Start | The start of Qualification Wave 4 QT Execution is approved by the Test Manager (MHHS Programme and Code Bodies informed) | 2025-04-14 | 2025-08-01 | Wording and date change to reflect the change to Waves
4 | T3 | T3-QU-0057 | Qualfication Wave 4 QT Execution End | The end of Qualification Wave 4 QT Execution is confirmed by the Test Manager (MHHS Programme and Code Bodies informed) | 2025-10-27 | 2025-12-13 | Wording and date change to reflect the change to Waves
4 | T3 | New | Qualification Wave 4 Participants have submitted their final QAD | The final date of the submission window by which Wave 4 Qualification Test participants are expected to submit their final QAD.​ | New | 2025-12-19 | New milestone added to support participant planning​
REMOVE | T3 | T3-QU-0013 | Confirm Qualification Testing Tranche 2 Participants | The date by which the Code Bodies confirm programme all the participants that will be included in Tranche 2 Qualification Testing. | 2024-09-03 | REMOVE | Removing due to change in Qualification Wave assignment
REMOVE | T3 | T3-QU-0014 | Confirm Qualification Testing Tranche 3 Participants | The date by which the Code Bodies confirm programme all the participants that will be included in Tranche 3 Qualification Testing. | 2024-10-01 | REMOVE | Removing due to change in Qualification Wave assignment
REMOVE | T3 | T3-QU-0015 | Confirm Qualification Testing Tranche 4 Participants | The date by which the Code Bodies confirm programme all the particIpants that will be included in Tranche 4 Qualification Testing. | 2024-10-29 | REMOVE | Removing due to change in Qualification Wave assignment
REMOVE | T3 | T3-QU-0018 | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 1 Participants) | MHHS SI confirms the MPAN range that has been allocated to the Code Bodies for Qualification Tranche 1. | 2024-11-04 | REMOVE | Removing due to change in Test Data approach
REMOVE | T3 | T3-QU-0019 | Confirm Qualification Testing Tranche 5 Participants | The date by which the Code Bodies confirm programme all the participants that will be included in Tranche 5 Qualification Testing. | 2024-11-26 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0022 | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 2 Participants) | MHHS SI confirms the MPAN range that has been allocated to the Code Bodies for Qualification Tranche 2. | 2024-12-02 | REMOVE | Removing due to change in Test Data approach
REMOVE | T3 | T3-QU-0023 | Confirm Qualification Testing Tranche 6 Participants | The date by which the Code Bodies confirm programme all the particpants that will be included in Tranche 6 Qualification Testing. | 2024-12-24 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0026 | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 3 Participants) | MHHS SI confirms the MPAN range that has been allocated to the Code Bodies for Qualification Tranche 3. | 2024-12-30 | REMOVE | Removing due to change in Test Data approach
REMOVE | T3 | T3-QU-0029 | Confirm Qualification Testing Tranche 7 Participants | The date by which the Code Bodies confirm programme all the participants that will be included in Tranche 7 Qualification Testing. | 2025-01-21 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0032 | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 4 Participants) | MHHS SI confirms the MPAN range that has been allocated to the Code Bodies for Qualification Tranche 4. | 2025-01-27 | REMOVE | Removing due to change in Test Data approach
REMOVE | T3 | T3-QU-0035 | Qualification Testing Tranche 5 Test execution schedule approved | The approval by TMAG of the Test Execution Schedule for the Tranche 5 Qualification Test stage | 2025-02-24 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0036 | Qualification Testing Tranche 5 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | The final date by which Tranche 5 Qualification Test participants are expected to declare that their UIT environments have been stood up, security certificates applied and security compliance achieved, and they are ready to commence connectivity proving. | 2025-02-24 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0037 | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 5 Participants) | MHHS SI confirms the MPAN range that has been allocated to the Code Bodies for Qualification Tranche 5. | 2025-02-24 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0040 | Qualification Testing Tranche 6 Test execution schedule approved | The approval by TMAG of the Test Execution Schedule for the Tranche 6 Qualification Test stage | 2025-03-24 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0041 | Qualification Testing Tranche 6 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | The final date by which Tranche 6 Qualification Test participants are expected to declare that their UIT environments have been stood up, security certificates applied and security compliance achieved, and they are ready to commence connectivity proving. | 2025-03-24 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0042 | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 6 Participants) | MHHS SI confirms the MPAN range that has been allocated to the Code Bodies for Qualification Tranche 6. | 2025-03-24 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0045 | Qualification Testing Tranche 7 Test execution schedule approved | The approval by TMAG of the Test Execution Schedule for the Tranche 7 Qualification Test stage | 2025-04-21 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0046 | Qualification Testing Tranche 7 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | The final date by which Tranche 7 Qualification Test participants are expected to declare that their UIT environments have been stood up, security certificates applied and security compliance achieved, and they are ready to commence connectivity proving. | 2025-04-21 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0047 | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 7 Participants) | MHHS SI confirms the MPAN range that has been allocated to the Code Bodies for Qualification Tranche 7. | 2025-04-21 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0048 | Qualification Testing Tranche 5 Test Readiness confirmed | TMAG approves that all preparation activities required to commence Qualification Testing Tranche 5 have been completed and assured. | 2025-05-05 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0049 | Qualification Testing Tranche 5 Start | The start of Qualification Tranche 5 execution is approved by the PAB (MHHS Programme Informed). | 2025-05-12 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0050 | Qualification Testing Tranche 6 Test Readiness confirmed | TMAG approves that all preparation activities required to commence Qualification Testing Tranche 6 have been completed and assured. | 2025-06-02 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0051 | Qualification Testing Tranche 6 Start | The start of Qualification Tranche 6 test execution is approved by PAB (MHHS Programme Informed). | 2025-06-09 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0052 | Qualification Testing Tranche 7 Test Readiness confirmed | TMAG approves that all preparation activities required to commence Qualification Testing Tranche 7 have been completed and assured. | 2025-06-30 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0053 | Qualification Testing Tranche 7 Start | The start of Qualification Tranche 7 test execution is approved by PAB (MHHS Programme Informed). | 2025-07-07 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0058 | Qualification Testing Tranche 5 End | The end of Qualification Tranche 5 test execution. | 2025-11-24 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0059 | Qualification Testing Tranche 6 End | The end of Qualification Tranche 6 test execution. | 2025-12-22 | REMOVE | Removing due to reduction in number of Qualification Waves
REMOVE | T3 | T3-QU-0060 | Qualification Testing Tranche 7 End | The end of Qualification Tranche 7 test execution. | 2026-01-19 | REMOVE | Removing due to reduction in number of Qualification Waves