## Tranche 1 TD Comments
Comment ID | *Artefact Reference & Name | *Document Section/ Requirement | *Comment | *Suggested Change | *Impact of not making the Change | *Comment Owner | Organisation | Date Returned | Triage Category | Transition Design Team Response
To be populated by MHHS Transition Design Team | Select the Artefact Reference from the Drop Down List | Indicate the specific section of the document or the requirement that the comment relates to | Succinctly state the problem identified with the design and the basis for the concern | Provide detail of the change or action required to resolve the comment | Provide a rationale for the change detailing the impact or materiality as a result of not making the recommended change
TD-001 | MHHS-DES241 - Transitional Scaling Weights | NewCCC_Weights | Only the Principles and Structure for these need to be finalised to baseline the design. There is no requirement for the values themselves to be finalised at this stage. At present these values have essentially been made up by Elexon in accordance with the principles but without any empirical analysis from Elexon or industry parties. The MHHS implementation date is too far in the future for these values to be approved as final. There are too many unknowns that may become clearer nearer the time. As a point of comparison, the equivalent in the Gas industry of GSPGCF scaling weights is AUGE weightings for Unidentified Gas. Proposed changes to these weightings occur annually and are accompanied by an evidence based paper and are implemented following a consultation. https://www.gasgovernance.co.uk/AUGStatement2324 | It should be explicitly stated that these values are provisional and not final. The programme/Elexon should publish a timetable for refining these values both closer to go live and again during transition when there will be more information to validate them. This should include supplier (and other party) engagement, and preferably a more scientific approach by Elexon. | At this stage it is very difficult for suppliers to provide meaningful input on whether the values will result in fair allocation of energy. This is because the allocation calculation is so complicated and sensitive to a number of factors that are currently unknown (e.g overall level of GSPGCF, mix of estimation types, impact of metered export). However, once all suppliers have further developed their demand forecasting models for MHHS they may be able to provide much more informed views on the impact of these weightings. Small movements in these values have a material impact on Supplier profitability. | Dom Bradbury | OVO Energy | 2023-04-26 | Accepted | Document updated to say these are provisional pending further input from Suppliers.
TD-002 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | Reference - MHHTR-16 | The requirement is not well specified and open to interpretation. It doesn't reference which flows are in scope of the requirement (the belief is that it should be NHH consumptions only, i.e. D0030, D0242, D0314, D0315, MHHS-REP-002, MHHS-REP-002A and "MHHS-REP-242" from CR019) | Ideally the TransitionTranch 1 document should follow the same structure as the MHHS design and migration requirement documents split by tabs referencing requirements specific to each party only as well as a clear reference to the dataflows the requirement is referencing and the correct step in relevant process or processes. | DUoS billing/validation software developers confusion who use baselined requirement documents and do not expect to reference these documents with any working groups meetings slide packs | Aga Medley | UKPN | 2023-04-27 | Accepted | The requirement has been updated to reference the data interfaces.
TD-003 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | Entire | Missing requirements about keeping the timetables for the new arrangement and old arrangements in sync. For example, SF run date for the common settlement day needs to be common to both arrangements | Add additional requirements | Potentially missing requirements | Clare Hannah | IMServ | 2023-04-28 | Acknowledge | These requirements are in the material for discussion in Tranche 2.
TD-004 | MHHS-DES241 - Transitional Scaling Weights | Entire | Unclear on logic of proposed scaling weights and their selection. Is there another document that describes the assumptions made to reach these proposals? Are current arrangement scaling weights left at current levels? If so, does this mean that current world and new world have different treatments for GSPG correction? | More clarity needed | Unclear. Difficult to review document. | Clare Hannah | IMServ | 2023-04-28 | Accepted | The document has been updated with the tables from the Tranche 1 slides.
TD-005 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-01 to MHHTR-05 | As a general rule, please don't refer to the 'end of migration' as this could be ambigous. Please use the defined milestones. | Change 'end of migration' to M15. | Possible ambiguity. | Stacey Watson | Siemens | 2023-04-28 | Accepted | Updated as stated.
TD-006 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-03 | Please confirm. From one settlement day prior to milestone M16, legacy settlement data will continue to be provided until RF 14 months later. | Clarification. | Clarification. | Stacey Watson | Siemens | 2023-04-28 | Acknowledge | This is subject to discussion. It has been suggested that at M16 there will only be reconcilliation until R2. This is to be discussed in Tranche 2. The word 'scheduled' has been added to cover this off.
TD-007 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-23 | Suggest this data is currently required for HHDAs and not HHDCs | LLF data for HHDAs - there is also a typo in column D where it should be HHDAs irrespective of this comment being accepted or not. | Minor - it is simply an accuracy comment | Stacey Watson | Siemens | 2023-04-28 | Accepted | Notionally the HHDA does this calculation but in practice some HHDCs make the calculation a MPAN level and the HHDA aggregates them. The wording has been amended to cover off both scenarios.
TD-008 | MHHS-DES241 - Transitional Scaling Weights | NewCCC_Weights | A lot of tacit knowledge is required to understand this material | It would assist the interpretation of the document to include a key for each of the fields, without the need to refer to other artefacts. e.g. definitions of each of the estimate types | Simplicity and transparency | Rhys Kealley | Centrica | 2023-04-28 | Accepted | Further detail has been added to the document on how the calulation is undertaken. A key to the new CCC ids has been added to explain which values are deemed to be actuals and which are estimates.
TD-009 | MHHS-DES241 - Transitional Scaling Weights | Worked_Example_Allocation | A lot of tacit knowledge is required to understand this material | A short written decsption of the maths would be useful | Simplicity and transparency | Rhys Kealley | Centrica | 2023-04-28 | Accepted | Detail added on calculation in principles tab.
TD-010 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-01 | The existing Daily Profile Production run must continue until the end of Migration. - please include the milestone for clarity - in this and all other requirements | The existing Daily Profile Production run must continue until the end of Migration (M15) | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Updated as stated.
TD-011 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-02 | The daily Profile Coefficients must continue to be provided to the NHHDCs | The daily Profile Coefficients must continue to be provided to the NHHDCs until end of Migration (M15) (???)) | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Updated as stated.
TD-012 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-03 | NHHDAs and HHDAs must continue to provide SPM data to BSC Central Systems for both forward and backward looking dates until the final reconciliation Settlement Date for the Settlement Date prior to the end of Migration. | is this until M15? | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Updated as stated.
TD-013 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-04 | Please define COCCID - is this Consumption Class ID? Do you mean CCCIDs? | Include in programme glossary or correct | Do not understand the requirement | Neil Strange | Centrica | 2023-04-28 | Accepted | Updated as stated.
TD-014 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-04 | When does MDS stop doing this | Include milestone reference | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Clarification | MDS does not stop doing this but document has been updated to reflect when it commences.
TD-015 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-05 | Is this until M15? | Include milestone reference | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Updated as stated.
TD-016 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-06 | When does this start & stop? M11 to M16? | Include milestone references | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Updated from M11 to M15. as M15 is the end of migration.
TD-017 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-08 | Is go live date M11 | Include milestone reference | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Go-live is M10 - added to requirement.
TD-018 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-09 | Does this start &stop? M11 to M16? | Include milestone references | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Added from M10 to M15.
TD-019 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-10 | Does this start at M11 & stop at M16? I'm assuming that we'd still be settling on the last MPANs until M16 | Include milestone references | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Added from M11 to M15.
TD-020 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-11 | Does this start &stop? M11 to M16? | Include milestone references | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Added from M10 to M15.
TD-021 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-15 | Is there a milestone when you stop doing this - - M16? | State until M16 or intended milestone | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Added from M10 to M15.
TD-022 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-16 | Does this start &stop? M11 to M16? | Include milestone references | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Added from M11 to M15.
TD-023 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-17 | When does this start - M11? | State when this starts | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Added from M11 to M15.
TD-024 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-19 | When does this stop M16? | Include milestone references | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Added from M10 to M15.
TD-025 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-20 | When does this stop M16? | Include milestone references | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Added until M15.
TD-026 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-21 | Include milestone references - | Think this is M11 to M15 or M16 | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Updated to reflect ISD will only generate LLF data against LLF Id prior to the start of the migration at M10 and will continue post migration at M15.
TD-027 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-22 | From M11? | Include milestone references | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Updated prior to M10 and continue post M15.
TD-028 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-23 | Until M15? | Include milestone references | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Updated to until M15.
TD-029 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-24 | Between M11 and M15 or M16 | Include milestone references | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Updated to from M10 until M15.
TD-030 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-26 | Does this stop at M16? | Include milestone references | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Updated to until M15.
TD-031 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-27 | Does this start at M11 | Include milestone references | Lack of precision | Neil Strange | Centrica | 2023-04-28 | Accepted | Added from M10.
TD-032 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-04 | What reports does this requirement relate to, are these ELEX-REP-090 and MHHS-REP-006? | Clarify |  | Mike Ceney | Elexon | 2023-04-28 | Accepted | Updated as suggested.
TD-033 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | General | How will the Trading Dispute process work during Transition? Will MDS only correct the data for the migrated period and old DA to process for pre-migrated period? VAS will need to ingest 2 sets of data and carry out different calculations? Also if the DF Settlement run is 28 months, MDS will not hold data for all of that period, MDS would only be responsible for correction of data effective from the Migration date | Clarify |  | Mike Ceney | Elexon | 2023-04-28 | Acknowledge | This needs to be discussed.as part of Tranche 2
TD-034 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | General | In what Tranche is Annual Consumption being looked at? The Method Statement states that calculations may change due to Transition design, is this the case? | Clarify |  | Mike Ceney | Elexon | 2023-04-28 | Acknowledge | No plan to discuss this. Transition Design team do not believe there is anything that impacts the calculation or provision of the AC data. As discussed in MTDSG-05 a DIN will be raised to amend the Method Statement accordingly
TD-035 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | General | Requirements are silent on any potential Demand Disconnection Events. Should DDE be referenced to provided clarity. | Clarity |  | Derek Weaving | Elexon | 2023-04-28 | Accepted | New Requirement MHHS-TR-28 added.
TD-036 | MHHS-DES242-Transitional BMU Aggreated Data | MHHTR-17 | This looks to be the same format as MHHS-REP-003 in the enduring state. Is a separate transitional document required? | Clarify |  | Derek Weaving | Elexon | 2023-04-28 | Acknowledge | Acknowlege but the report is revised to accomodate combined legacy and new CCC ids.
TD-037 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-15 | Reference is made to GSPGCF for Import. As only one GSPGCF will be provided as per current requirements, is the term " import" required? | Clarify |  | Derek Weaving | Elexon | 2023-04-28 | Clarification | Import is required as there wil be two GCFs from M10. Only the import one will be reported on legacy flows.
TD-038 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-23 | Minor comment Typo in Requirement Descriptionas reference made to HHDC's and HHDC. | Suggest changing to HHDCs/HHDAs as per requirement column |  | Derek Weaving | Elexon | 2023-04-28 | Accepted | Updated to remove typo.
TD-039 | MHHS-DES241 - Transitional Scaling Weights | MHHTR-14 | Interface catalogue is missing some of the scaling weights mentioned in the MHHS-DES241 doc | suggest to align all design artefacts |  | Rashmi Radhakrishnan | Elexon | 2023-04-28 | Clarification | No change. Transition Design team think this is refering to missing estimation flags rather than scaling weights. Scaling weights only appear in the ISD and MDD tables.
TD-040 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-20 | publishing of D265 report LLFC level will stop post transition | clarify |  | Rashmi Radhakrishnan | Elexon | 2023-04-28 | Accepted | Added until M15.
TD-041 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-25 | Clarify the validation requirement for UMS charge codes | clarify |  | Rashmi Radhakrishnan | Elexon | 2023-04-28 | Accepted | Added: The ISD record will be the master record. The UMS data will be validated to agree with the formats specified in the Operational Information Document (OID) in ISD before being updated in Legacy MDD Spreadsheets.
TD-042 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-22 and 27 | Terminology used Elexon website/portal etc. | Assuming Helix can identify appropriate location to publish the report |  | Rashmi Radhakrishnan | Elexon | 2023-04-28 | Accepted | Added ELEXON Portal
TD-043 |  | MHHS-DES238 ISD population | Redlined changes to the document will impact ISD and require changes to ISD entity. | Clarify- Requesting to change releavant design artefacts (ISD Entity Specification) and publish |  | Rashmi Radhakrishnan | Elexon | 2023-04-28 | Acknowledge | Noted DIN265 has been raised and will require the ISD Entity to be updated.
TD-044 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-03 | Define the "final reconciliation settlement date" and the "settlement date prior to the end of Migration" and how they are identified | Clarify |  | Nigel Rees / James Lee | Elexon | 2023-04-28 | Accepted | Added 'scheduled' as cut-off has not yet been defined. Also added M15 as this would be the end of Migration.
TD-045 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-07 | Which milestone is indicated by the "Go-Live Date"? | Clarify |  | Nigel Rees / James Lee | Elexon | 2023-04-28 | Accepted | Changed Go-live to M10.
TD-046 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-08 | Which milestone is indicated by the "Go-Live Date"? | Clarify |  | Nigel Rees / James Lee | Elexon | 2023-04-28 | Accepted | Changed Go-live to M10.
TD-047 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-08 | Unlcear if "Go-Live Date" in this requirement aligns with "settlement date prior to the end of Migration" in previous requirements MHHTR-03 / 05 | Clarify |  | Nigel Rees / James Lee | Elexon | 2023-04-28 | Accepted | Added from M11 to M15.
TD-048 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-09 | MDD does not have "Scaling Weights" - should this be "GSP Group Correction Scaling Factor" ? | Clarify |  | Nigel Rees / James Lee | Elexon | 2023-04-28 | Accepted | Added clarification.
TD-049 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-12 | MDD does not have "Scaling Weights" - should this be "GSP Group Correction Scaling Factor" ? | Clarify |  | Nigel Rees / James Lee | Elexon | 2023-04-28 | Accepted | Added clarification.
TD-050 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-13 | MDD does not have "Scaling Weights" - should this be "GSP Group Correction Scaling Factor" ? | Clarify |  | Nigel Rees / James Lee | Elexon | 2023-04-28 | Accepted | Added clarification.
TD-051 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-14 | Will the review of "Scaling Weights" include "Scaling Factors" in MDD? These are understood to be frozen from the start of Transition? | Clarify |  | Nigel Rees / James Lee | Elexon | 2023-04-28 | Acknowledge | Good point - this will need to be discussed.
TD-052 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-24 | UMS changes are caputred in an separate process, not MDD | Reword |  | Nigel Rees / James Lee | Elexon | 2023-04-28 | Clarification | No change to artefact. UMS data is part of MDD and goes through the same process and timetable.
TD-053 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-25 | "Legacy MDD Spreadsheets" should be "Legacy UMS Spreadsheets." | Reword |  | Nigel Rees / James Lee | Elexon | 2023-04-28 | Clarification | UMS added. The spreadsheets are part of MDD and follow the MDD change processes and timetable.
TD-054 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-04 | Typo - "Coccid" should be "MHHS CCC Id" | Reword |  | James Lee | Elexon | 2023-04-28 | Accepted | Updated as stated.
TD-055 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-05 | This requirement suggests that legacy SVAA and VAS will run for the same settlement dates and reconciliation runs, and that output from legacy SVAA will feed into VAS? Suggest this is explicitly stated either in a requirement or elsewhere | Clarify |  | James Lee | Elexon | 2023-04-28 | Accepted | new Requirement MHHS-TR-29 added.
TD-056 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-09 | Typo - "Legacy Coccid" should be "Legacy CCC Id" | Reword |  | James Lee | Elexon | 2023-04-28 | Accepted | Updated as stated.
TD-057 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-10 | This requirement suggests that VAS is correcting the legacy consumption volumes for legacy CCC ids from legacy SVAA (non-migrated MPANs). Suggest this is explicitly stated either in a requirement or elsewhere | Clarify |  | James Lee | Elexon | 2023-04-28 | Accepted | new Requirement MHHS-TR-29 added.
TD-058 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-11 | By BSCCo, does this mean specifically VAS? | Clarify |  | James Lee | Elexon | 2023-04-28 | Accepted | Amended to 'VAS'. There is already a requirement for BSCCo to publish the GCFs on the portal.
TD-059 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-14 | We assume this review will be carried out in accordance with the published ISD change timetable | Clarify |  | James Lee | Elexon | 2023-04-28 | Clarification | Yes, any ISD changes would follow the ISD change timetable.
TD-060 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-23 | Clarification requested that this only for for pre-migrated MPANs. Also, clarify if this is only for transition period. | Clarify |  | James Lee | Elexon | 2023-04-28 | Accepted | Clarification added to state this is for non-migrated MPANs
TD-061 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-22 | At a location on the BSC website' this vaguity needs to be clarified for testing/BAU. Parties who need to access this information also require notification that there is a publication for which they are required to act | Clarify BSC website location & design the notification which will be received when a publication as been made | Clarity from this point will allow Business to design their own internal processes to allow for testing/success at go-live | Rachael Prosser | NGED | 2023-05-03 | Clarification | The Transtion Design team understand that Helix intend to publish this data on the ELEXON Portal. The DIP flow Notification of the Publication of a Downloadable Asset IF-047 / PUB-047 will identify the exact location so it can be collected.
TD-062 | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments | MHHTR-27 | At a location on the BSC website' this vaguity needs to be clarified for testing/BAU. Parties who need to access this information also require notification that there is a publication for which they are required to act | Clarify BSC website location & design the notification which will be received when a publication as been made | Clarity from this point will allow Business to design their own internal processes to allow for testing/success at go-live | Rachael Prosser | NGED | 2023-05-03 | Clarification | The Transition Design team understand that Helix intend to publish this data on the ELEXON Portal. The DIP flow Notification of the Publication of a Downloadable Asset IF-047 / PUB-047 will identify the exact location so it can be collected.
Transition Design Artefacts Tranche 1 Consolidated Comments Log

## Triage Categorisation
Triage status Definitions:
Accepted - Comment has been accepted and change has been made to the Tranche 1 Design Artefacts
Acknowledge - Comment acknowledged but no change to artefact required and/or is an issue that will need to be discussed as part of Tranche 2 or in other workstreams
Clarification -Clarification provided in the comment response

## Control (hidden)
Constituency | Artefacts
Central Party | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments
Large Supplier | MHHS-DES242-Transitional BMU Aggreated Data
Medium Supplier | MHHS-DES241 - Transitional Scaling Weights
Small Supplier
I&C Supplier
Supplier Agent
Independent Supplier Agent
DNO
IDNO
Software Provider
Other- MHHS Participant

## Design Artefacts (hidden)
Published Documents |  | Lists
Design Artefact | Version Number | Version Number | Status
METH001 - ADV Validation and Estimation | 1 | v1.1 | Accepted
Rejected
Requires Further Clarification
Action
Submitted