## D-Flows
Comment ID (to be assigned by MHHS Programme) | Design Artefact Name | Document Section | Comments | Related Design Artefact | Related Design Artefact Section/Step | Suggested Change e.g. proposed wording | Comment Owner | Organisation | Constituency | Submitted | Triage Status
ECSR-001 | MM00ddd- Ddddd-001 - Supplier BM Unit Report (MHHS) v0.5 | All | • SSR Run bm unit id mentioned in data items but not in flow • Daily DA HH MSID count not mentioned on flow but in list of data items • Group correction scaling weight - should this not have a J item associated in data items? • Default BM unit reason code in data items but not in flow structure • Settlement period id, settlement period label, uncorrected BM units period level consumption, daily uncorrected bm units period level consumption, daily uncorrected bm units period consumption losses, daily corrected component, daily corrected component losses on flow structure but not in list of data items. |  |  |  | Helen Banks | E.ON (EEM) | In-House Supplier Agent | 2023-08-24 | Accepted ​
ECSR-002 | MM00ccc-Dcccc-001-GSP Group Consumption Totals Report (MHHS) v0.5 |  | • valid settlement period quality indicator set not in list of data items • should the below data items in the amended flow not map to current DTN references J1565, J1566, J1567, J1568, J1705 ? Total CCC Aggregated Supplier Consumption Total CCC Aggregated Supplier Line Loss Total CCC Corrected Supplier Consumption Total CCC Corrected Supplier Line Loss MSID Count |  |  |  | Helen Banks | E.ON (EEM) | In-House Supplier Agent | 2023-08-24 | Accepted ​
ECSR-003 | MM00bbb-Dbbbb-001-Supplier Settlement Header Report (MHHS) v0.5 |  | • Should D50138 be DI50138 for GSP Group Name • BSC Trading Party Id originally had DI-389 associated with it, has this changed to DI50127 or does this need re-aligning? • SSR Run Type ID - name doesn’t match DTN name • Why has run type code been omitted? |  |  |  | Helen Banks | E.ON (EEM) | In-House Supplier Agent | 2023-08-24 | Accepted ​
ECSR-004 | MM00aaa-Daaaa-001-Supplier Half Hourly Demand Report (MHHS) v0.5 |  | • GSP Group J1104 is on list of data items but not in the flow structure • Should DI-083 read Settlement Period Quality Indicator Set in the list of Data Items? |  |  |  | Helen Banks | E.ON (EEM) | In-House Supplier Agent | 2023-08-24 | Accepted ​
ECSR-005 | MHHS Impacts to BSC Owned Data Flows v0.5 | general for all | Due to the inconsistencies in the data items and flow structures it’s very hard to comment. It isn’t 100% clear what the proposals are as a result of these inconsistencies. |  |  |  | Helen Banks | E.ON (EEM) | In-House Supplier Agent | 2023-08-24 | Acknowledge​
ECSR-006 | MHHS Impacts to BSC Owned Data Flows v0.5 | 3. Solution statement 3.1 Approach outline | Ref : . References to Market Domain Data (MDD) within DTN flows will be amended to Industry Standing Data (ISD) where that Data Item will continue to be in ISD in the MHHS design. The D0269 and D0270 will be retained for distributing ‘old world’ MDD only, with new ISD published via subscription. |  |  | The ESO manually extracts its MDD data from the Elexon portal and does not use the D0269 / D0270. Will this facility exist after the implementation of MHHS or will the ESO have to setup a subscription to automatically receive the ISD data? | Andrew Dudkowsky | ESO | Central Party | 2023-08-25 | Acknowledge​
ECSR-007 | MHHS-DESxxx-MHHS Impacts to BSC Owned Data Flows v0.5 | Data Flow D0275 | SV ADS>DNO missing | Add SV ADS>DNO | Jacqui Barton | Add SV ADS>DNO | Jacqui Barton | National Grid Electricity Distribution | DNO | 2023-08-25 | Acknowledge​
ECSR-008 | MHHS Impacts to BSC Owned Data Flows v0.5 | 3.2 | D0004 flow - 'Bullet Point " Data Retriever to Smart Data Service", I wasn't aware that the role of Data Retriever existed? Is this role replacing NHHDR? | Clarify please | IH | Clarify please | IH | IMServ | Independant Supplier Agent | 2023-08-29 | Acknowledge​
ECSR-009 | MHHS Impacts to BSC Owned Data Flows v0.5 | 3.2 | D0001 flow - Data Retriever to NHHDC currently exists but isn't being carried forward while the D0004 is being carried forward, is this consist/correct? | Clarify please | IH | Clarify please | IH | IMServ | Independant Supplier Agent | 2023-08-29 | Acknowledge​
ECSR-010 | MHHS Impacts to BSC Owned Data Flows v0.5 | 3.2 | D0002 flow - should there be a "Electricity Smart Meter Equipment Manager to Electricity Smart Meter Equipment Manager" row added? | Clarify please | IH | Clarify please | IH | IMServ | Independant Supplier Agent | 2023-08-29 | Acknowledge​
ECSR-011 | MHHS Impacts to BSC Owned Data Flows v0.5 | 3.2 | D0010 flow is missing ADS to ADS? Also SDS to SDS? | Clarify please | IH | Clarify please | IH | IMServ | Independant Supplier Agent | 2023-08-29 | Acknowledge​
ECSR-012 | MHHS Impacts to BSC Owned Data Flows v0.5 | 3.2 | D0010 flow is missing Electricity Advanced Meter Equipment Manager to Electricity Advanced Meter Equipment Manager? Same for Smart? | Clarify please | IH | Clarify please | IH | IMServ | Independant Supplier Agent | 2023-08-29 | Acknowledge​
ECSR-013 | MHHS Impacts to BSC Owned Data Flows v0.5 | 3.2 | D0010, no Data Retriever to SDS relationship? no Supplier to DNO or Supplier to Supplier? | Clarify please | IH | Clarify please | IH | IMServ | Independant Supplier Agent | 2023-08-29 | Acknowledge​
ECSR-014 | MHHS Impacts to BSC Owned Data Flows v0.5 | 3.2 | Have the following flows omitted as they are RECCo owned flows? - D0135/136/139/149/150/164/268, a number of others? Is it intended that RECCo produce a similar list? | Clarify please | IH | Clarify please | IH | IMServ | Independant Supplier Agent | 2023-08-29 | Acknowledge​
ECSR-015 | MHHS Impacts to BSC Owned Data Flows v0.5 | 3.2 | Both D0001 & D0005 are stated as being for advanced and Traditional meters - under the new TOM what mechanism is expected to be used for instructing Electricity Smart Meter Equipment Manager to investigate a metering fault/issue? | Clarify please | MM | Clarify please | MM | IMServ | Independant Supplier Agent | 2023-08-29 | Acknowledge​
ECSR-016 | MHHS Impacts to BSC Owned Data Flows v0.5 | 3.2 | For the D0355, this will also need to be routed to EMR. This is notification to EMR that the Mpan has been added or removed from the register | Add a new SV from MDS to EMR | Mike Ceney | Add a new SV from MDS to EMR | Mike Ceney | Elexon | Central Party | 2023-08-29 | Acknowledge​
ECSR-017 | MM00aaa-Daaaa-001-Supplier Half Hourly Demand Report (MHHS) v0.5 | Various | WP4 integration work carried out using D0081/D0266/D0276 and D0296 standard header. New files (MM00aaa/bbb/ccc/ddd) will need rework, already planned in for when the final format is available. Just for awareness of impact. |  | Ilinca Pirvulescu |  | Ilinca Pirvulescu | Elexon | Central Party | 2023-08-29 | Accepted ​
ECSR-018 | MM00ddd- Ddddd-001 - Supplier BM Unit Report (MHHS) v0.5 |  | Two files with a different code (D0XXX and MMhhxxx) with be coming in at the same time, with the same title. Impact needs to be assessed. |  | Ilinca Pirvulescu |  | Ilinca Pirvulescu | Elexon | Central Party | 2023-08-29 | Accepted ​
ECSR-019 | MM00ccc-Dcccc-001-GSP Group Consumption Totals Report (MHHS) v0.5 | HDR | Existing HDR group contains Settlement Date, Code, Description, SSR Run Date, Run Number, Run Type, Supplier ID and Supplier Name. HDR in Dcccc and Ddddd do not contain this full list. In previous discussions it was agreed a new group would be created to reflect the change in attributes | Propose to create new group as previously discussed. | Ilinca Pirvulescu / Soniya Jakhu | Propose to create new group as previously discussed. | Ilinca Pirvulescu / Soniya Jakhu | Elexon | Central Party | 2023-08-29 | Accepted ​
ECSR-020 | MM00ccc-Dcccc-001-GSP Group Consumption Totals Report (MHHS) v0.5 | CCC | CCC group in Dcccc and Ddddd requires a new group name as this refers to the MHHS CCC. | XXX is used in Daaaa, suggest to use the same. | Ilinca Pirvulescu / Soniya Jakhu | XXX is used in Daaaa, suggest to use the same. | Ilinca Pirvulescu / Soniya Jakhu | Elexon | Central Party | 2023-08-29 | Accepted ​
ECSR-021 | MM00bbb-Dbbbb-001-Supplier Settlement Header Report (MHHS) v0.5 | ZPD | there is no GSP ID, name or Run Type info. Is this required? |  | Ilinca Pirvulescu |  | Ilinca Pirvulescu | Elexon | Central Party | 2023-08-29 | Accepted ​
ECSR-022 | MM00aaa-Daaaa-001-Supplier Half Hourly Demand Report (MHHS) v0.5 | HRD | Daaaa has supplier information in the SUP group, whereas in Dcccc and Ddddd, they are in the SUX group. | They could either be added back to the HDR group (existing group) so it can be reused or a consistent group name is used for supplier info | Ilinca Pirvulescu / Soniya Jakhu | They could either be added back to the HDR group (existing group) so it can be reused or a consistent group name is used for supplier info | Ilinca Pirvulescu / Soniya Jakhu | Elexon | Central Party | 2023-08-29 | Accepted ​
ECSR-023 | MM00bbb-Dbbbb-001-Supplier Settlement Header Report (MHHS) v0.5 | GSP | GSP section called bbb in this file only. | For consistency , revert bbb to GSP for GSP info section. | Ilinca Pirvulescu | For consistency , revert bbb to GSP for GSP info section. | Ilinca Pirvulescu | Elexon | Central Party | 2023-08-29 | Accepted ​
ECSR-024 | MM00bbb-Dbbbb-001-Supplier Settlement Header Report (MHHS) v0.5 | ZPD | bbb in used as a placeholder for both GP1 and and ZPD. This creates confusion. | when replacing the placeholder with a true reference, ensure they are not the same for different section. | Ilinca Pirvulescu | when replacing the placeholder with a true reference, ensure they are not the same for different section. | Ilinca Pirvulescu | Elexon | Central Party | 2023-08-29 | Accepted ​
ECSR-025 | MHHS Impacts to BSC Owned Data Flows v0.5 | 3 Solution Statement 3.1 Approach Outline | Section where it states that `ISD published via subscription` we do not agree. It has been previously agreed that published ISD Data will not require Subscription. OR Is this referring to the subscritpion that participant needed for the DIP in order to receive the notification of the new catalogue, which they download from the Data Store | In ISD, Market Participants will be informed via DIP when a new ISD catalogue is published with a URL which they can use to access the data. There is no subscription mechanism (unless DIP allows them to opt in/out of the PUB-047 messages) Alignment required with MHHS otherwise creates confusion. | Sedef Kiris | In ISD, Market Participants will be informed via DIP when a new ISD catalogue is published with a URL which they can use to access the data. There is no subscription mechanism (unless DIP allows them to opt in/out of the PUB-047 messages) Alignment required with MHHS otherwise creates confusion. | Sedef Kiris | Elexon | Central Party | 2023-08-29 | Acknowledge​
ECSR-026 | MHHS Impacts to BSC Owned Data Flows v0.5 | 3 Solution Statement 3.1 Approach Outline | Section states that `LLF data will be reported at LLF Id level using REP-005 in ISD and an equivalent to the D0265 at LLF Id level published on the Elexon Portal.` Creates confusion by referring to 2 different file. | Just to clarify For LLFS we will be publishing the REP-005 which is the equivalent of the legacy D0265. Clarification required to agree on the fact that REP-005 and D0265 are the same file. | Sedef Kiris | Just to clarify For LLFS we will be publishing the REP-005 which is the equivalent of the legacy D0265. Clarification required to agree on the fact that REP-005 and D0265 are the same file. | Sedef Kiris | Elexon | Central Party | 2023-08-29 | Acknowledge​
ECSR-027 | Data Catalogue v5.2.1 | Row 10, Data Item Details | In the data catalogue its been referred to DI-300 MHHS Consumption Component Class ID, however in the 4 new data flows its been referred to just “Consumption Component Class” | Inconsistency to be aligned by MHHS | Alan Griffiths / Sedef Kiris | Inconsistency to be aligned by MHHS | Alan Griffiths / Sedef Kiris | Elexon | Central Party | 2023-08-29 | Accepted ​
ECSR-028 | MM00aaa-Daaaa-001-Supplier Half Hourly Demand Report (MHHS) v0.5 | Data Items Section | In the MM00aaa – Daaa document the list of data items refers to Daily Supplier MSID count as “DI-xxx” whereas in the data catalogue it is “DI-218” | Inconsistency to be aligned by MHHS | Alan Griffiths / Sedef Kiris | Inconsistency to be aligned by MHHS | Alan Griffiths / Sedef Kiris | Elexon | Central Party | 2023-08-29 | Accepted ​
ECSR-029 | MM00bbb-Dbbbb-001-Supplier Settlement Header Report (MHHS) v0.5 | Data Items Section | In the MM00bbbb – Dbbb document similarly MDS Run Date and MDS Run Number as “DI-xxx” rather than “DI-219” and “DI-220” in the data catalogue | Inconsistency to be aligned by MHHS | Alan Griffiths / Sedef Kiris | Inconsistency to be aligned by MHHS | Alan Griffiths / Sedef Kiris | Elexon | Central Party | 2023-08-29 | Accepted ​
ECSR-030 | MM00ddd- Ddddd-001 - Supplier BM Unit Report (MHHS) v0.5 | Data Items Section & Flow Structure (CCC) | In MM00ddd-Dddd document there are inconstancies between use of MHHS Consumption Component Class ID and CCC ID | Inconsistency to be aligned by MHHS | Alan Griffiths / Sedef Kiris | Inconsistency to be aligned by MHHS | Alan Griffiths / Sedef Kiris | Elexon | Central Party | 2023-08-29 | Accepted ​
ECSR-031 | MM00aaa-Daaaa-001-Supplier Half Hourly Demand Report (MHHS) v0.5 | Flow Structure | This applies to all reports. It was clarified on a previous call that the ZHD header is also required. Is it possible to include in the specs? | Suggest to include in the Flow Structure | Soniya Jakhu | Suggest to include in the Flow Structure | Soniya Jakhu | Elexon | Central Party | 2023-08-29 | Acknowledge​
ECSR-032 | MM00aaa-Daaaa-001-Supplier Half Hourly Demand Report (MHHS) v0.5 | RDT | The existing RDT group contains username and report parameters. RDT in Daaaa and Dbbbb does not contain both. . In previous discussions it was agreed a new group would be created to reflect the change in attributes. | Propose to create new group as previously discussed. | Soniya Jakhu | Propose to create new group as previously discussed. | Soniya Jakhu | Elexon | Central Party | 2023-08-29 | Accepted ​
ECSR-033 | MM00ddd- Ddddd-001 - Supplier BM Unit Report (MHHS) v0.5 | BM2 / TL2 | Is there a reason these groups end with 2 and do not appear as BM1 and TL1? |  | Soniya Jakhu |  | Soniya Jakhu | Elexon | Central Party | 2023-08-29 | Accepted ​
ECSR-034 | MM00ccc-Dcccc-001-GSP Group Consumption Totals Report (MHHS) v0.5 | Flow Structure | Has a separator been agreed for the Valid Settlement Period Quality Indicator Set in the new MHHS CCCs? Pipe was agreed for ISD but it won’t work in these files as they already pipe delimited. This applies to Daaaa, Dbbbb and Ddddd. |  | Soniya Jakhu |  | Soniya Jakhu | Elexon | Central Party | 2023-08-29 | Accepted ​
ECSR-035 | MM00bbb-Dbbbb-001-Supplier Settlement Header Report (MHHS) v0.5 | IDD | The existing IDD group contains MPID, Profile Production Run Number, Run Date and Run Time . IDD in Dbbbb does not contain all. In previous discussions it was agreed a new group would be created to reflect the change in attributes. | Propose to create new group as previously discussed. | Soniya Jakhu | Propose to create new group as previously discussed. | Soniya Jakhu | Elexon | Central Party | 2023-08-29 | Accepted ​
ECSR-036 | MHHS Impacts to BSC Owned Data Flows v0.5 | 3.2 | Some of the DTC messages have the following bullet point "Used under MHHS: Yes for Advanced and Traditional Meters" - they do not refer to smart meters. Can clarity be given as to whether this means these apply to Advanced Segment and Traditional Meters only and exclude Smart Meters and the smart segment, are smart meters included within the definition of advanced, meters with the definition of 'advanced' matching the supplier license conditions (i.e. an advanced meter being any meter capable of remote connectivity and reads such as smart, AMR and HH meters)? |  |  | Clarity on advanced meters as per SLC or Advanced segment with exclusion of smart meters from smart segment but inclusion of traditional meters from smart segment - and if smart meters are excluded, why that is. | Keith Barlow | EDF | Large Supplier | 2023-08-30 | Acknowledge​
ECSR-037 | MHHS Impacts to BSC Owned Data Flows v0.5 | D0003 - Half Hourly Advances | Currently as an HHDC we only use this flow for responding to proving tests from the meter operator. We've never received any from a Supplier. Also not aware of any other use setout in the draft ADS BSCP. |  |  | Only include this route for MHHS "Advanced Data Service to Electricity Advanced Meter Equipment Manager" | Keith Donaldson | TMA Data Management Ltd | Supplier Agent | 2023-08-30 | Acknowledge​
ECSR-038 | MHHS Impacts to BSC Owned Data Flows v0.5 | D0005 - Instruction on Action | "Used under MHHS" for this flow lists Traditional Meters but there are no scenario varients added for SDS |  |  | Either remove the use for Traditional Meters or add in SDS Scenario Variants | Keith Donaldson | TMA Data Management Ltd | Supplier Agent | 2023-08-30 | Acknowledge​
ECSR-039 | MHHS Impacts to BSC Owned Data Flows v0.5 | D0275 - Validation Half Hourly Advances | IF/PUB-021 is not currently sent from Supplier to Data service and not aware of a use in the BSCP of the D0275 being sent to the data service |  |  | Remove to Data Service scenario variants | Keith Donaldson | TMA Data Management Ltd | Supplier Agent | 2023-08-30 | Acknowledge​
|  |  | Note: SPEN replied to say they have no comments at this time | [6 empty] | 2023-08-29 | Accepted ​
MHHS Impacts to BSC Owned Data Flows Review Consolidated Comments Log v1.0

## Sheet1
Triage status | Description​
​
Accepted ​ | Comment has been accepted and change has been made
Rejected​ | Comment reject - No change will be made
Acknowledge​ | Comment is not related to the reports but may be picked up in other workstreams, or further clarification will be provided to the comment raiser.​​
Requires further clarification with PP​ | Comment is not fully understood by the reviewer and requires clarification with the comment raiser.​​
Clarification Provided​ | No change made - clarification is provided to respond to reviewers comment​

## Control Sheet (hidden)
Aretfact Name
Data Catalogue v5.2.1
MM00ddd- Ddddd-001 - Supplier BM Unit Report (MHHS) v0.5
MM00ccc-Dcccc-001-GSP Group Consumption Totals Report (MHHS) v0.5
MM00bbb-Dbbbb-001-Supplier Settlement Header Report (MHHS) v0.5
MM00aaa-Daaaa-001-Supplier Half Hourly Demand Report (MHHS) v0.5
MHHS Impacts to BSC Owned Data Flows v0.5