DIN-495 | P497 |  | Data interface correction | Entered Value Added.
DIN-495 | Q497 |  | Supporting Docs | Entered Value Added.
DIN-495 | R497 |  | Interface Catalogue | Entered Value Added.
DIN-495 | S497 |  | DES138-InterfaceCatalogue | Entered Value Added.
DIN-496 | D498 |  | 13/07/2023 (13/07/2023 00:00:00) | Entered Value Added.
DIN-496 | E498 |  | CGI | Entered Value Added.
DIN-496 | F498 |  | 2549 | Entered Value Added.
DIN-496 | G498 |  | Dave Webster | Entered Value Added.
DIN-496 | H498 |  | Software Provider | Entered Value Added.
DIN-496 | I498 |  | Correction to METH001 | Entered Value Added.
DIN-496 | J498 |  | MHHSP-METH001_SDS_Validation_Estimation 5.1 section 2.7 States "SDS shall inform the Supplier using the Meter Reading Reason Code on the IF-041/PUB-41" . There is no Meter Reading Reason Code on the IF-041 in DES138 v5.1.2. Therefore, either Meter Reading Reason Code should be included in DES138, or this requirement should be removed. | Entered Value Added.
DIN-496 | K498 |  | Open - awaiting assessment | Entered Value Added.
DIN-496 | M498 |  | Interim Release 6 | Entered Value Added.
DIN-496 | N498 |  | 20/10/2023 (20/10/2023 00:00:00) | Entered Value Added.
DIN-496 | O498 |  | Remove the following from METH001: 'Where consumption data has been deemed invalid the SDS shall inform the Supplier using the Meter Reading Reason Code on the IF-041/PUB-41.' | Entered Value Added.
DIN-497 | D499 |  | 13/07/2023 (13/07/2023 00:00:00) | Entered Value Added.
DIN-497 | E499 |  | CGI | Entered Value Added.
DIN-497 | F499 |  | 2549 | Entered Value Added.
DIN-497 | G499 |  | Dave Webster | Entered Value Added.
DIN-497 | H499 |  | Software Provider | Entered Value Added.
DIN-497 | I499 |  | Correction to METH001 | Entered Value Added.
DIN-497 | J499 |  | MHHSP-METH001_SDS_Validation_Estimation 5.1 Section 5.4 Where DA records are < 90 days from UTC date this is inconsistent with Method 4, which states "DA is available [either in the past or future] and less than [3] months different from the UTC Date requiring a daily Meter advance". | Entered Value Added.
DIN-497 | K499 |  | Open - awaiting assessment | Entered Value Added.
DIN-497 | M499 |  | Interim Release 6 | Entered Value Added.
DIN-497 | N499 |  | 20/10/2023 (20/10/2023 00:00:00) | Entered Value Added.
DIN-497 | O499 |  | Be consistent - use either 90 days or trhee months within the document | Entered Value Added.
DIN-498 | D500 |  | 13/07/2023 (13/07/2023 00:00:00) | Entered Value Added.
DIN-498 | E500 |  | CGI | Entered Value Added.
DIN-498 | F500 |  | 2549 | Entered Value Added.
DIN-498 | G500 |  | Dave Webster | Entered Value Added.
DIN-498 | H500 |  | Software Provider | Entered Value Added.
DIN-498 | I500 |  | Correction to METH001 Method 13 | Entered Value Added.
DIN-498 | J500 |  | MHHSP-METH001_SDS_Validation_Estimation 5.1 Method 13 This describes the outcomes for Smart and Advanced meters. Does this imply that traditional meters should have zero consumption submitted to settlements, or should Method 13 text be adjusted to include trad meters? ALSO If actual data is recovered, or an Advance Meter Reading is received, and this indicates zero consumption, should this be submitted to settlements? The first part of the sentence implies it should be submitted, and the brackets imply it shouldn't. | Entered Value Added.
DIN-498 | K500 |  | Open - awaiting assessment | Entered Value Added.
DIN-498 | M500 |  | Interim Release 6 | Entered Value Added.
DIN-498 | N500 |  | 20/10/2023 (20/10/2023 00:00:00) | Entered Value Added.
DIN-498 | O500 |  | Alter wording of Method 13 to reflect we shouldn't be sending estimates for Deenergised trad meters as well as Smart and Advanced, AND 'there is no need to submit zero consumption for de-energised MPAN's' needs changing to refer to 'zero ESTIMATED consumption' | Entered Value Added.
DIN-499 | D501 |  | 13/07/2023 (13/07/2023 00:00:00) | Entered Value Added.
DIN-499 | E501 |  | CGI | Entered Value Added.
DIN-499 | F501 |  | 2549 | Entered Value Added.
DIN-499 | G501 |  | Dave Webster | Entered Value Added.
DIN-499 | H501 |  | Software Provider | Entered Value Added.
DIN-499 | I501 |  | Alignemtn of Estimation Reason Codes | Entered Value Added.
DIN-499 | J501 |  | METH001 refers to Estimation Reason Code 'Adjustment'. DES138 refers to 'Consumption Amendment' Assume these are the same thing and need to be aligned between both sets of documentation | Entered Value Added.
DIN-499 | K501 |  | Open - awaiting assessment | Entered Value Added.
DIN-499 | M501 |  | Interim Release 6 | Entered Value Added.
DIN-499 | N501 |  | 20/10/2023 (20/10/2023 00:00:00) | Entered Value Added.
DIN-499 | O501 |  | Align Method Statements to match the Estimation Reason Codes within DES138 | Entered Value Added.
DIN-500 | D502 |  | 13/07/2023 (13/07/2023 00:00:00) | Entered Value Added.
DIN-500 | E502 |  | CGI | Entered Value Added.
DIN-500 | F502 |  | 2549 | Entered Value Added.
DIN-500 | G502 |  | Dave Webster | Entered Value Added.
DIN-500 | H502 |  | Software Provider | Entered Value Added.
DIN-500 | I502 |  | ISD Entity M17 Example Correction | Entered Value Added.
DIN-500 | J502 |  | MHHSP_EDI021_ISD_Entities 5.1 Entity id M17 Industry Standing Data: MHHS Entities/Data Items v5.1 ISD Entity Id M17 - Valid Consent Granularity Combinations, includes combination I¦F¦S¦D. According to Decision 2 in "https://www.ofgem.gov.uk/sites/default/files/docs/2019/06/access_to_data_consultation_ofgem_response_0.pdf" a non-domestic customer is unable to opt out. The OFGEM document states "There will be no opt out possible for microbusinesses in relation to data for settlement purposes". Therefore, I ¦ F ¦ S ¦ D is not a valid combination. | Entered Value Added.
DIN-500 | K502 |  | Open - awaiting assessment | Entered Value Added.
DIN-500 | M502 |  | Interim Release 6 | Entered Value Added.
DIN-500 | N502 |  | 20/10/2023 (20/10/2023 00:00:00) | Entered Value Added.
DIN-500 | O502 |  | Remove I ¦ F ¦ S ¦ D from the example list | Entered Value Added.
DIN-501 | A503 |  | MHHS-DIN-501 | Entered Value Added.
DIN-501 | D503 |  | 13/07/2023 (13/07/2023 00:00:00) | Entered Value Added.
DIN-501 | E503 |  | CGI | Entered Value Added.
DIN-501 | F503 |  | 2549 | Entered Value Added.
DIN-501 | G503 |  | Dave Webster | Entered Value Added.
DIN-501 | H503 |  | Software Provider | Entered Value Added.
DIN-501 | I503 |  | Addition of Method 13 to METH002 | Entered Value Added.
DIN-501 | J503 |  | MHHSP-METH002_ADS_Validation_Estimation 5.1 Section 3.16 States "The below estimation methods are based on those used in the Smart Data Service (SDS) Method Statement. For that reason, methods 0, 1, 6, 11 and 13 have been omitted as they are only applicable to Smart meters." However, method 13 is "Estimation for a Site where Supply is de-energised" and this is included in METH002 in section 2.29. The statement is wrong as some of the methods have been renumbered in METH001 since this was written. | Entered Value Added.
DIN-501 | K503 |  | Open - awaiting assessment | Entered Value Added.
DIN-501 | M503 |  | Interim Release 6 | Entered Value Added.
DIN-501 | N503 |  | 20/10/2023 (20/10/2023 00:00:00) | Entered Value Added.
DIN-501 | O503 |  | Update METH002 to add MEthod 13 back in | Entered Value Added.
DIN-502 | A504 |  | MHHS-DIN-502 | Entered Value Added.
DIN-502 | D504 |  | 13/07/2023 (13/07/2023 00:00:00) | Entered Value Added.
DIN-502 | E504 |  | CGI | Entered Value Added.
DIN-502 | F504 |  | 2549 | Entered Value Added.
DIN-502 | G504 |  | Dave Webster | Entered Value Added.
DIN-502 | H504 |  | Software Provider | Entered Value Added.
DIN-502 | I504 |  | SP Quality Indicator Clarification | Entered Value Added.
DIN-502 | J504 |  | MHHSP-METH001_SDS_Validation_Estimation 5.1 It is our assumption that if NO estimation is required, the Settlement Period Quality Indicator should be set to "A". This is however, never explicitly mentioned. The only mention of using value "A" is for method 1. | Entered Value Added.
DIN-502 | K504 |  | Open - awaiting assessment | Entered Value Added.
DIN-502 | M504 |  | Interim Release 6 | Entered Value Added.
DIN-502 | N504 |  | 20/10/2023 (20/10/2023 00:00:00) | Entered Value Added.
DIN-502 | O504 |  | Update artefacts to clarify when to use A as the SEttlement Period Quality Indicator value | Entered Value Added.
DIN-503 | A505 |  | MHHS-DIN-503 | Entered Value Added.
DIN-503 | D505 |  | 13/07/2023 (13/07/2023 00:00:00) | Entered Value Added.
DIN-503 | E505 |  | SIMS | Entered Value Added.
DIN-503 | F505 |  | 2439 | Entered Value Added.
DIN-503 | G505 |  | Martin Freeman | Entered Value Added.
DIN-503 | H505 |  | Central Body | Entered Value Added.
DIN-503 | I505 |  | S1.senderUniqueReference interface component is too small to identify the message interface | Entered Value Added.
DIN-503 | J505 |  | DES138 and the E2E001 the S1.senderUniqueReference property has a 3 digit component that contains the interfaceID of the message. However since the reporting interfaces reuse the same interface numbers as the standard interfaces, and some reporting interfaces have 4 character interface identifiers, this means this component is not sufficiently large to unambiguously identify which interface a given senderUniqueReference was generated for. This also applies for TransactionID. | Entered Value Added.
DIN-503 | K505 |  | Initial Assessment/Updating | Entered Value Added.
DIN-503 | M505 |  | Interim Release 4 | Entered Value Added.
DIN-503 | N505 |  | 8/16/2023 (16/08/2023 00:00:00) | Entered Value Added.
DIN-503 | O505 |  | Update any Data Items that utilise InterfaceID to align with the enumeration of values defined for DI-000 to that this is unique across all interface / report types. This includes data types like SenderUniqueReference (DI-995) and TransactionID (DI-990). This change will require updates in DES-138, E2E001 and Swagger 1.4. | Entered Value Added.
DIN-503 | P505 |  | Design Ambiguous | Entered Value Added.
DIN-503 | Q505 |  | Supporting Docs | Entered Value Added.
DIN-503 | R505 |  | DES-138, E2E001 and Swagger 1.4 | Entered Value Added.
DIN-503 | S505 |  | DES-138, E2E001 and Swagger 1.4 | Entered Value Added.
DIN-504 | A506 |  | MHHS-DIN-504 | Entered Value Added.
DIN-504 | D506 |  | 13/07/2023 (13/07/2023 00:00:00) | Entered Value Added.
DIN-504 | E506 |  | CGI | Entered Value Added.
DIN-504 | F506 |  | 2549 | Entered Value Added.
DIN-504 | G506 |  | Dave Webster | Entered Value Added.
DIN-504 | H506 |  | Software Provider | Entered Value Added.
DIN-504 | I506 |  | Clarification of link between IF22/IF23 | Entered Value Added.
DIN-504 | J506 |  | DES138 IF-022/023 IF an IF-022 or IF-023 is re-issued, can you confirm that they will be reissued as a pair so that the totals align? The issue is if an updated IF-022 is issued with new values, should the SDS/ADS await an updated IF-023, or not? How can the SDS/ADS pair the IF-022 and IF-023 without doing their own summations? | Entered Value Added.
DIN-504 | K506 |  | Open - awaiting assessment | Entered Value Added.
DIN-504 | M506 |  | Interim Release 6 | Entered Value Added.
DIN-504 | N506 |  | 20/10/2023 (20/10/2023 00:00:00) | Entered Value Added.
DIN-504 | O506 |  | Update BRS007 to show that a re-run of IF-022 will result in a rerun of IF-023 | Entered Value Added.
DIN-505 | A507 |  | MHHS-DIN-505 | Entered Value Added.
DIN-505 | D507 |  | 13/07/2023 (13/07/2023 00:00:00) | Entered Value Added.
DIN-505 | E507 |  | SCS | Entered Value Added.
DIN-505 | G507 |  | Sean Cooper | Entered Value Added.
DIN-505 | H507 |  | SRO Design | Entered Value Added.
DIN-505 | I507 |  | DUoS Tariff ID to hold values from 1-3 in length | Entered Value Added.
DIN-505 | J507 |  | The DUoS Tariff ID needs to be updated in Swagger and the Interface Catalogue so that it can hold values from 1 to 3 in length in order to align with ISD. | Entered Value Added.
DIN-505 | K507 |  | Ready for Internal Review | Entered Value Added.
DIN-505 | M507 |  | Interim Release 4 | Entered Value Added.
DIN-505 | N507 |  | 8/16/2023 (16/08/2023 00:00:00) | Entered Value Added.
DIN-505 | O507 |  | Update DUoS Tariff ID to hold values from 1 to 3 in length in Swagger and Interface Catalogue | Entered Value Added.
DIN-505 | P507 |  | Data interface correction | Entered Value Added.
DIN-505 | Q507 |  | Supporting Docs | Entered Value Added.
DIN-505 | R507 |  | Interface Catalogue and Swagger 1.4 | Entered Value Added.
DIN-505 | S507 |  | DES138-InterfaceCatalogue Swagger 1.4 | Entered Value Added.
DIN-506 | A508 |  | MHHS-DIN-506 | Entered Value Added.
DIN-506 | D508 |  | 13/07/2023 (13/07/2023 00:00:00) | Entered Value Added.
DIN-506 | E508 |  | Design Team | Entered Value Added.
DIN-506 | G508 |  | Sean Cooper | Entered Value Added.
DIN-506 | H508 |  | SRO Design | Entered Value Added.
DIN-506 | I508 |  | Renaming of IF-014 | Entered Value Added.
DIN-506 | J508 |  | Rename IF-014 to clarify the purpose | Entered Value Added.
DIN-506 | K508 |  | Ready for Internal Review | Entered Value Added.
DIN-506 | M508 |  | Interim Release 4 | Entered Value Added.
DIN-506 | N508 |  | 8/16/2023 (16/08/2023 00:00:00) | Entered Value Added.
DIN-506 | O508 |  | Changed to "UTC Settlement Period Consumption Data (Warnings & Rejections)" | Entered Value Added.
DIN-506 | P508 |  | Data interface correction | Entered Value Added.
DIN-506 | Q508 |  | Supporting Docs | Entered Value Added.
DIN-506 | R508 |  | Interface Catalogue | Entered Value Added.
DIN-506 | S508 |  | DES138-InterfaceCatalogue | Entered Value Added.
DIN-507 | A509 |  | MHHS-DIN-507 | Entered Value Added.
DIN-507 | D509 |  | 14/07/2023 (14/07/2023 00:00:00) | Entered Value Added.
DIN-507 | E509 |  | Design Team | Entered Value Added.
DIN-507 | G509 |  | Sean COoper | Entered Value Added.
DIN-507 | H509 |  | SRO Design | Entered Value Added.
DIN-507 | I509 |  | Clarification of IF-036 Routing Requirements | Entered Value Added.
DIN-507 | J509 |  | Update IF-036 to clarify / provide additional info on the routing destinations of IF-036 | Entered Value Added.
DIN-507 | K509 |  | Ready for Internal Review | Entered Value Added.
DIN-507 | M509 |  | Interim Release 4 | Entered Value Added.
DIN-507 | N509 |  | 8/16/2023 (16/08/2023 00:00:00) | Entered Value Added.
DIN-507 | O509 |  | Added following Text: Primary Routing Participants for IF-036 MSAppActive • Supplier (i.e. the supplier who initiated the appointment, either current in the case of Change Of / Update to SP’s, or incoming in the case of a COS) • Metering Service (i.e. the Metering Service being appointed) • [Partner] Data Service (i.e. the Data Service in effect on the App Start Date of the MS Appointment – this could be either an ‘existing’ Data Service in the case of an MS Only appointment OR the ‘incoming’ Data Service with a coincident App Start Date to that of the [incoming] Metering Service • Linked Supplier(s) – (ie the Supplier(s) with responsibility for the Linked [Import/export] MPANs on the App Start Date of the Metering Service Appointment) DSAppActive • Supplier (i.e. the supplier who initiated the appointment, either current in the case of Change Of / Update to SP’s, or incoming in the case of a COS) • Data Service (i.e. the Data Service being appointed) • [Partner] Metering Service (i.e. the Metering | Entered Value Added.
DIN-507 | P509 |  | Data interface correction | Entered Value Added.
DIN-507 | Q509 |  | Supporting Docs | Entered Value Added.
DIN-507 | R509 |  | Interface Catalogue | Entered Value Added.
DIN-507 | S509 |  | DES138-InterfaceCatalogue | Entered Value Added.
DIN-508 | A510 |  | MHHS-DIN-508 | Entered Value Added.
DIN-508 | D510 |  | 17/07/2023 (17/07/2023 00:00:00) | Entered Value Added.
DIN-508 | E510 |  | Design Team | Entered Value Added.
DIN-508 | G510 |  | Sean Cooper | Entered Value Added.
DIN-508 | H510 |  | SRO Design | Entered Value Added.
DIN-508 | I510 |  | Addition of MP Status and RMP Status Effective From Dates to IF-050 | Entered Value Added.
DIN-508 | J510 |  | Addition of MP Status and RMP Status Effective From Dates to IF-050 | Entered Value Added.
DIN-508 | K510 |  | Initial Assessment/Updating | Entered Value Added.
DIN-508 | M510 |  | Interim Release 4 | Entered Value Added.
DIN-508 | N510 |  | 8/16/2023 (16/08/2023 00:00:00) | Entered Value Added.
DIN-508 | O510 |  | New Data Items Created DI : DI-167 RMP Status (Registration) DI-168 MP Status | Entered Value Added.
DIN-508 | P510 |  | Data interface correction | Entered Value Added.
DIN-508 | Q510 |  | Supporting Docs | Entered Value Added.
DIN-508 | R510 |  | Interface Catalogue | Entered Value Added.
DIN-508 | S510 |  | DES138-InterfaceCatalogue | Entered Value Added.
DIN-509 | A511 |  | MHHS-DIN-509 | Entered Value Added.
DIN-51 | M53 | Interim Release 4 | Interim Release 6 | Entered Value Changed.
DIN-51 | N53 | 09/08/2023 (09/08/2023 00:00:00) | 10/20/2023 (20/10/2023 00:00:00) | Entered Value Changed.
DIN-51 | O53 | Refresh Functionality was rejected by the Working Groups so not in current design. Scenarios required. | Refresh Functionality was rejected by the Working Groups so not in current design. Internal Design Discussion Required on if Programme position has changed on this given CSS Issue / EES Fed via DIP ?? | Entered Value Changed.
DIN-510 | A512 |  | MHHS-DIN-510 | Entered Value Added.
DIN-52 | M54 |  | Interim Release 1 | Entered Value Added.
DIN-56 | M58 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
DIN-56 | N58 | 09/08/2023 (09/08/2023 00:00:00) | 20/09/2023 (20/09/2023 00:00:00) | Entered Value Changed.
DIN-56 | O58 | Original response was: This has been raised as potential consequential change utilising SDEP Nothing in design, would want updates via a flow to maintain sychronisation. Requires a change to implement, request specific data items requested - needs to be related to settlement, needs to be updated via appropriate flow. | Internal review required | Entered Value Changed.
DIN-58 | N60 | 13/09/2023 (13/09/2023 00:00:00) | 20/09/2023 (20/09/2023 00:00:00) | Entered Value Changed.
DIN-70 | K72 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
DIN-70 | O72 | Design Agreement is to utilise M16 for this purpose. Propose to update ISD document with details and examples to this effect. | Design Agreement is to utilise M16 for this purpose. ISD document updated with details and examples to this effect. | Entered Value Changed.
DIN-70 | S72 | MHHSP-DES138-Interface Catalogue - probable updates to relevant BP/BPD/BRS | MHHS-EDI-021-ISD_Entities | Entered Value Changed.
DIN-81 | K83 | Updates Ready to Release | Implemented | Entered Value Changed.
DIN-82 | K84 | Updates Ready to Release | Implemented | Entered Value Changed.
DIN-83 | K85 | Updates Ready to Release | Implemented | Entered Value Changed.
DIN-84 | K86 | Updates Ready to Release | Implemented | Entered Value Changed.
DIN-87 | K89 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
DIN-87 | O89 | New Purple Boxes to be added in BP009 and BP008 to make it clear that Remove/DeEn could still be requested and carried out but MS would need to send two interfaces. Also that DeEn did not need to be notified if meter works completed within same day (ie same rules as today) | New Purple Boxes added in BP009 and BP008 to make it clear that Remove/DeEn could still be requested and carried out but MS would need to send two interfaces. Also that DeEn did not need to be notified if meter works completed within same day (ie same rules as today) | Entered Value Changed.
DIN-87 | S89 | MHHSP-BP009, MHHSP-BPD009 | MHHSP-BP009 | Entered Value Changed.
DIN-88 | F90 | 2587 |  | Entered Value Deleted.
DIN-88 | O90 | Part of ongoing discussions with Code Drafting team why would the incumbant share the MTD via the IF-035 as early sight. IF-37 is the deappoint they code need to reflect . The Metering Service is appointed until they get de-appointed using a PUB-037. They are only receiving the PUB-035 as notification of who to send MTDs to, it is not intended as a notification of de-appointment. SC= Incumbent Metering Service is a term used to refer to the MS appointed at the point another new SP Appointment is accepted (MS or DS), it shall be the Incumbent Metering Service's responsibility to share MTDs (ADV/Trad) to the incoming party. No change recommend CLOSE | Part of ongoing discussions with Code Drafting team. It is not expected that the incumbant share the MTD via the IF-035 as early sight. IF-37 is the deappoint code they need to reflect . The Metering Service is appointed until they get de-appointed using a PUB-037. They are only receiving the PUB-035 as notification of who to send MTDs to, it is not intended as a notification of de-appointment. Incumbent Metering Service is a term used to refer to the MS appointed at the point another new SP Appointment is accepted (MS or DS), it shall be the Incumbent Metering Service's responsibility to share MTDs (ADV/Trad) to the incoming party. No change recommend CLOSE | Entered Value Changed.
DIN-89 | K91 | Initial Assessment/Updating | Closed | Entered Value Changed.
DIN-89 | M91 | Interim Release 4 |  | Entered Value Deleted.
DIN-89 | N91 | 09/08/2023 (09/08/2023 00:00:00) |  | Entered Value Deleted.
DIN-89 | O91 | Part of ongoing discussions with Code Drafting team | Programme has called out the need for data management wrt GDPR. It is for each participant to determine the action required based on their own GDPR Guidelines and policies. | Entered Value Changed.
DIN-90 | K92 | Initial Assessment/Updating | Closed | Entered Value Changed.
DIN-90 | M92 | Interim Release 4 |  | Entered Value Deleted.
DIN-90 | N92 | 09/08/2023 (09/08/2023 00:00:00) |  | Entered Value Deleted.
DIN-90 | O92 | Part of ongoing discussions with Code Drafting team to have a look at the process that Mpans are in the correct group The daily process monitoring (BP011C) would pick up any linked Export MPANs and ensure that the same Metering Service is appointed as the Import MPAN. If the Export MPAN is not linked, then the BAU appointment process can be followed. | Part of ongoing discussions with Code Drafting team - this is not a Design Issue. Design will operate as described below: The daily process monitoring (BP011C) would pick up any [new] Linked Export MPANs and ensure that the same Metering Service is appointed as the Import MPAN. If the Export MPAN is not linked, then the BAU appointment process can be followed. | Entered Value Changed.
DIN-93 | K95 | Updates Ready to Release | Implemented | Entered Value Changed.
DIN-97 | K99 | Updates Ready to Release | Implemented | Entered Value Changed.
DIN-98 | K100 | Updates Ready to Release | Implemented | Entered Value Changed.
DIN-99 | K101 | Updates Ready to Release | Implemented | Entered Value Changed.

## DIN Compare 010823 (hidden)
Compare of DIN log from 17/7/23 to 010823
Differences
Sheet | DIN | Range | Old Value | New Value | Description
DIN Log | DIN-107 | J109 | Definition of DI-301 in the ESC Reporting Data Catalogue needs to be updated as follows 'The Unique Identifier of a set of Line Loss Factors' | Definition of DI-301 in the ECS Reporting Data Catalogue needs to be updated as follows 'The Unique Identifier of a set of Line Loss Factors' | Entered Value Changed.
DIN Log | DIN-107 | K109 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-107 | P109 | Update to be made in the ESC Reporting Data Catalogue against DI-301 LLF ID it should read as 'The Unique Identifier of a set of Line Loss Factors' | Update to be made in the ECS Internal & External Reports - Data Catalogue tab against DI-301 LLF ID it should read as 'The Unique Identifier of a set of Line Loss Factors' | Entered Value Changed.
DIN Log | DIN-107 | T109 | ESC Reporting Catalogue | MHHSP - ERI011A - ECS Reports - Internal v5.2 MHHSP - ERI011B - ECS Reports - Enternal | Entered Value Changed.
DIN Log | DIN-149 | P151 | SRO Team do not belive that a change is required. | SRO Team do not believe that a change is required. Linked to DIN-554 | Entered Value Changed.
DIN Log | DIN-154 | K156 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-154 | P156 | Agreed with SCS that, changes would be made to support Rules 1 and 4. Validation Rules updated accordingly with new Error codes (REG1067/1068) created to support. | Agreed with SCS that changes to IF-19 tab would be made to support Rules 1 and 4. Validation Rules updated accordingly with new Error codes (REG1067/1068) created to support. | Entered Value Changed.
DIN Log | DIN-158 | I160 |  | Use of CCCs to categorise the data for future charges | Entered Value Added.
DIN Log | DIN-158 | M160 | Interim Release 5 | Interim Release 4 | Entered Value Changed.
DIN Log | DIN-158 | P160 | Recommending a change to this ISD Data Item: Settlement Period Quality Indicator to be set as per Appendix 1 of MHHSP_METH007 MDS_Method_Statement v5.0 This data item need to be changes to something like ‘Valid Settlement Period Quality Indicator Set’ and the field size needs to be increased. The data catalugue will need the revised data item and the field length will need increasing from 20 to at least 50. This Item also appears in some interfaces that will need t be updated This is because it represents a set of SPQIs. The initial intention is to populate as per the table and check if any new SPQIs have been introduced in the baseline design Method Statement that are not covered. If new CCCs are introduced the appropriate flags for each new CCC would need to be agreed. However, it is likely that another dimension to the table below would need to be introduced to facilitate new CCCs. | Recommending a change to this ISD Data Item: Settlement Period Quality Indicator to be set as per Appendix 1 of MHHSP_METH007 MDS_Method_Statement v5.0 This data item need to be changes to something like ‘Valid Settlement Period Quality Indicator Set’ and the field size needs to be increased. The data catalugue will need the revised data item and the field length will need increasing from 20 to at least 50. This Item also appears in some interfaces that will need t be updated This is because it represents a set of SPQIs. The initial intention is to populate as per the table and check if any new SPQIs have been introduced in the baseline design Method Statement that are not covered. If new CCCs are introduced the appropriate flags for each new CCC would need to be agreed. However, it is likely that another dimension to the table below would need to be introduced to facilitate new CCCs. Word 'Illustrative' to be removed and will be updated to say Valid Settlement Quality Indicator Set. Change to be | Entered Value Changed.
DIN Log | DIN-158 | Q160 |  | Missing/incorrect validation rule | Entered Value Added.
DIN Log | DIN-17 | K19 | Initial Assessment/Updating | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-17 | P19 | Solution agreed at DRG on what MAP updates are required. Various document updates required to align with DRG decision to only maintain latest MAP | Solution agreed at DRG on what MAP updates are required. Various document updates required to align with DRG decision to only maintain latest MAP. Removed section 13 from IF005 user guide plus other corrections to doc. Updated DES138 IF005 validation rules. | Entered Value Changed.
DIN Log | DIN-17 | T19 | MHHSP-DES138-Interface Catalogue | IF-005 Use Case guide MHHSP-DES138-Interface Catalogue | Entered Value Changed.
DIN Log | DIN-191 | M193 | Interim Release 4 | Interim Release 6 | Entered Value Changed.
DIN Log | DIN-191 | P193 | Internal review to take place as to whether DUOS Tariff ID updates should be retrospective. LINKED TO DIN-056 above | Internal review has taken place as to whether DUOS Tariff ID updates should be retrospective. SC to create PPT Review Internally & with ScS then agree DRG discussion date. LINKED TO DIN-056 above | Entered Value Changed.
DIN Log | DIN-198 | L200 |  | 8/31/2023 (31/08/2023 00:00:00) | Entered Value Added.
DIN Log | DIN-200 | K202 | Initial Assessment/Updating | Closed | Entered Value Changed.
DIN Log | DIN-200 | M202 | Interim Release 3 |  | Entered Value Deleted.
DIN Log | DIN-200 | N202 | 12/07/2023 (12/07/2023 00:00:00) |  | Entered Value Deleted.
DIN Log | DIN-208 | K210 | Initial Assessment/Updating | Closed | Entered Value Changed.
DIN Log | DIN-208 | M210 | Interim Release 4 |  | Entered Value Deleted.
DIN Log | DIN-208 | P210 | LINKED to DIN-056 and DIN-191 Above | Closed following internal review with Design, Migration and Code Team. Agreed that current design will stand in that all legacy messages will be rejected following the point the IF-031 is issued. Reaffirm existing guidance that migration should be timed to avoid any planned work. Unplanned work/change occuring during migration should be communicated using an MHHS IF Message once migration has been completed. | Entered Value Changed.
DIN Log | DIN-241 | I243 |  | Routing rules via the PUB-018 | Entered Value Added.
DIN Log | DIN-241 | Q243 |  | Data interface correction | Entered Value Added.
DIN Log | DIN-243 | K245 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-243 | P245 | Changes as agreed at DRG and slides circulated. Updated Method 2 and Method 7 within the SDS method statement (METH001) | Changes as agreed at DRG and slides circulated. Updated Method 2 and Method 7 within the SDS method statement (METH001). BR-DS-168 & BR-DS-169 added to BRS001. BR-SU-163, BR-SU-164 & BR-SU165 added to BRS004. BP004 text box amended. Creation of x2 New Data Catalogue Items​ OPD Day​ & OPD Proportion​. Changes to IF-024​ Addition of new Event Code [SN-OffPeakDec]​ & Addition of new B-Block BXXX Off-Peak Declaration​ | Entered Value Changed.
DIN Log | DIN-264 | I266 |  | Update to CCC Method Statement | Entered Value Added.
DIN Log | DIN-264 | M266 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
DIN Log | DIN-265 | I267 |  | Validity of Settlement Period quality indicator data set | Entered Value Added.
DIN Log | DIN-265 | M267 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
DIN Log | DIN-266 | F268 | 3899 | 3899/ 925 | Entered Value Changed.
DIN Log | DIN-266 | K268 | Initial Assessment/Updating | Closed | Entered Value Changed.
DIN Log | DIN-266 | M268 | Interim Release 4 |  | Entered Value Deleted.
DIN Log | DIN-266 | P268 | Check with Elexon/Code Drafting that latest version of DES196 contains the D0300 | Email comms sent to Patricia confirming the D0300 is a Supplier to Supplier flow. Therefore should there be a need to send readings to the DS, this would be done via a D0010/IF-041 with the correct data flags set in both. Based on this there is no requirement to send D0300 to the DS. Matt M confirmed when finalising DES196 he confirmed this in his comment response to ESG. The MSAG Consequential Change - Switch Meter Read Exceptions v1.0 22.06.23 provides a more comprehensive explanation of the MSAG conclusions. No change required to DES196 | Entered Value Changed.
DIN Log | DIN-278 | K280 | Initial Assessment/Updating | Requires Industry Work Group review | Entered Value Changed.
DIN Log | DIN-278 | M280 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
DIN Log | DIN-298 | K300 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
DIN Log | DIN-298 | P300 | Table provided by PDA has been updated and will be shown within section 10, Publish and Data Flags within the UMSDS Method Statement. UMS method statement updated with text to address query. Updated text below: If a D0388 has been received with load associated data and the MPAN is de-energised the load should be calculated, submitted as ‘A’ Flagged but with an Estimation Reason Code of De-energised. | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Entered Value Changed.
DIN Log | DIN-300 | K302 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
DIN Log | DIN-300 | P302 | Table provided by PDA has been updated and will be shown within section 10, Publish and Data Flags within the UMSDS Method Statement. | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Entered Value Changed.
DIN Log | DIN-301 | K303 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
DIN Log | DIN-301 | P303 | Table provided by PDA has been updated and will be shown within section 10, Publish and Data Flags within the UMSDS Method Statement. | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Entered Value Changed.
DIN Log | DIN-302 | K304 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
DIN Log | DIN-302 | P304 | Table provided by PDA has been updated and will be shown within section 10, Publish and Data Flags within the UMSDS Method Statement. | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Entered Value Changed.
DIN Log | DIN-302 | T304 | UMSDS Method Statement DES138 | UMSDS Method Statement | Entered Value Changed.
DIN Log | DIN-318 | K320 | Initial Assessment/Updating | Closed | Entered Value Changed.
DIN Log | DIN-318 | M320 | Interim Release 4 |  | Entered Value Deleted.
DIN Log | DIN-318 | P320 | Waiting on SCS Feedback | REF DIN-508 | Entered Value Changed.
DIN Log | DIN-318 | Q320 |  | No Change | Entered Value Added.
DIN Log | DIN-321 | K323 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-324 | I326 |  | NHHSP-BPM00C- Transfer of Reads on Change of Data Service process steps and messages clarification | Entered Value Added.
DIN Log | DIN-329 | K331 | Initial Assessment/Updating | Closed | Entered Value Changed.
DIN Log | DIN-329 | M331 | Interim Release 4 |  | Entered Value Deleted.
DIN Log | DIN-329 | P331 | Further details of the solution are under discussion/review. | ERDS Interfaces are ouf of scope of MHHS. If a change to ERDS interface is required or efficiencies in its existing operation are possible to align with MHHS Design - this would be a consquential change. | Entered Value Changed.
DIN Log | DIN-329 | Q331 |  | No Change | Entered Value Added.
DIN Log | DIN-335 | J337 | IF/PUB-004 – DIP Common Blocks referencing MHHSP-DES138-Interface Catalogue v5.1.1 As a minimum this needs to be referenced in the supplier requirements MHHSP-BRS004-Supplier Overview and MHHSP-BRS002-Metering Service requirements, but to ensure parties get sight of this we would suggest it needs to be included in a business process map and have associated requirements. For IF-004 to be useful to participants DI-999 – Event Code needs to be elaborated e.g. 1- Installation 2- Removal; 3- Exchange; 4 - Found (Where installed by Gas supplier and Elec Supplier takes ownership) C/M/O rules for DI-192, DI-193 and DI-194 need to be explained in the notes – presumably driven by event code Available is spelled incorrectly (available) for DI-192 and DI-194 there are a couple of angles here – 1) ensuring wider awareness and 2) it seems there is a question mark on the governance here as it is odd a flow has been added but industry does not appear to have been sighted on it especially with no associated referencing in ar | IF/PUB-004 – DIP Common Blocks referencing MHHSP-DES138-Interface Catalogue v5.1.1 As a minimum this needs to be referenced in the supplier requirements MHHSP-BRS004-Supplier Overview and MHHSP-BRS002-Metering Service requirements, but to ensure parties get sight of this we would suggest it needs to be included in a business process map and have associated requirements. For IF-004 to be useful to participants DI-999 – Event Code needs to be elaborated e.g. 1- Installation 2- Removal; 3- Exchange; 4 - Found (Where installed by Gas supplier and Elec Supplier takes ownership) C/M/O rules for DI-192, DI-193 and DI-194 need to be explained in the notes – presumably driven by event code Available is spelled incorrectly (available) for DI-192 and DI-194 there are a couple of angles here – 1) ensuring wider awareness and 2) it seems there is a question mark on the governance here as it is odd a flow has been added but industry does not appear to have been sighted on it especially with no associated referencing in | Entered Value Changed.
DIN Log | DIN-335 | K337 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
DIN Log | DIN-335 | P337 | Update BPM to include sending of Optional Flow at correct point in process | Updated BP009 Change of Metering to include the "optional" sending of IF-004 from MS via DIP to Supplier, if changes to Comms Hub need to be notified. Included same updated to BPD009 to reflect new BP steps. Other comments have been addressed previously and are reflected in DES138 IF-004 | Entered Value Changed.
DIN Log | DIN-335 | Q337 | Data interface correction | Process Model correction | Entered Value Changed.
DIN Log | DIN-335 | R337 | Supporting Docs | Meter to Bank | Entered Value Changed.
DIN Log | DIN-335 | T337 | MHHSP-DES138-Interface Catalogue | BP009 Change oF Metering BPD009 Change of Metering | Entered Value Changed.
DIN Log | DIN-336 | I338 |  | Requirements clean up in iServer | Entered Value Added.
DIN Log | DIN-336 | Q338 |  | Doc Ref correction | Entered Value Added.
DIN Log | DIN-338 | I340 |  | BP003 to be updated to clearly show IF-036 going to both Import & Export supplier | Entered Value Added.
DIN Log | DIN-338 | Q340 |  | Process Model correction | Entered Value Added.
DIN Log | DIN-339 | I341 |  | IF-001 to be updated to be additionally sent to the Export supplier rather than just the import | Entered Value Added.
DIN Log | DIN-339 | Q341 |  | Process Model correction | Entered Value Added.
DIN Log | DIN-340 | I342 |  | ELEX-REP-02/02A report | Entered Value Added.
DIN Log | DIN-342 | I344 |  | ELEX-REP-02/02A Consumption data clarification | Entered Value Added.
DIN Log | DIN-353 | K355 | Initial Assessment/Updating | Closed | Entered Value Changed.
DIN Log | DIN-353 | M355 | Interim Release 4 |  | Entered Value Deleted.
DIN Log | DIN-353 | P355 | Further details of the solution are under discussion/review. | Solution options discussed with SCS. Closed as covered under DIN 560 | Entered Value Changed.
DIN Log | DIN-354 | C356 |  | DI-179 | Entered Value Added.
DIN Log | DIN-358 | K360 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
DIN Log | DIN-358 | P360 | Further details of the solution are under discussion/review. | Annual Consumption Method Statement updated with following text in red: 1.1 The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN within 30 calendar days following notification of the set-up of that MPAN in MHHS-IF-036 Registration Service Notification of Service Appointment & Supporting information. . | Entered Value Changed.
DIN Log | DIN-358 | Q360 |  | Method statement correction | Entered Value Added.
DIN Log | DIN-358 | R360 |  | Supporting Docs | Entered Value Added.
DIN Log | DIN-358 | S360 |  | Method Statement | Entered Value Added.
DIN Log | DIN-358 | T360 |  | Annual Consumption Meth 10 | Entered Value Added.
DIN Log | DIN-359 | K361 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
DIN Log | DIN-359 | P361 | Further details of the solution are under discussion/review. | Annual Consumption Method Statement updated with following text in red: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: | Entered Value Changed.
DIN Log | DIN-359 | Q361 |  | Method statement correction | Entered Value Added.
DIN Log | DIN-359 | R361 |  | Supporting Docs | Entered Value Added.
DIN Log | DIN-359 | S361 |  | Method Statement | Entered Value Added.
DIN Log | DIN-359 | T361 |  | Annual Consumption Meth 10 | Entered Value Added.
DIN Log | DIN-360 | I362 |  | Greater than or equal to change for UTC Period Consumption Data | Entered Value Added.
DIN Log | DIN-360 | K362 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
DIN Log | DIN-360 | P362 | Further details of the solution are under discussion/review. | Annual Consumption Method Statement updated with following text in red: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. | Entered Value Changed.
DIN Log | DIN-360 | Q362 |  | Method statement correction | Entered Value Added.
DIN Log | DIN-360 | R362 |  | Supporting Docs | Entered Value Added.
DIN Log | DIN-360 | S362 |  | Method Statement | Entered Value Added.
DIN Log | DIN-360 | T362 |  | Annual Consumption Meth 10 | Entered Value Added.
DIN Log | DIN-361 | I363 |  | Section Name change | Entered Value Added.
DIN Log | DIN-361 | J363 | Section 5 incorrectly named Section 6 needs to be removed: 6. Transition and Next steps | Section 5 incorrectly named Section 6 needs to be updated: 6. Transition and Next steps | Entered Value Changed.
DIN Log | DIN-361 | K363 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
DIN Log | DIN-361 | P363 | Further details of the solution are under discussion/review. | Section 6 has been updated to Section 5 within AC Method Statement and old section 5.1The initial Annual Consumption calculation, as set out in section 3.7 above may change, depending on the consideration of the working groups during the MHHS Transition requirements work- has been removed | Entered Value Changed.
DIN Log | DIN-361 | Q363 |  | Method statement correction | Entered Value Added.
DIN Log | DIN-361 | R363 |  | Supporting Docs | Entered Value Added.
DIN Log | DIN-361 | S363 |  | Method Statement | Entered Value Added.
DIN Log | DIN-361 | T363 |  | Annual Consumption Meth 10 | Entered Value Added.
DIN Log | DIN-362 | I364 |  | Load Shaping Service calculations | Entered Value Added.
DIN Log | DIN-362 | J364 | We may also need to document how the is calculated by the Load Shaping Service in the first year. I believe Helix have developed a calculation and this would need to go in the Load Shaping Method Statement and be referenced in the AC Method Statement. | We may also need to document how this is calculated by the Load Shaping Service in the first year. I believe Helix have developed a calculation and this would need to go in the Load Shaping Method Statement and be referenced in the AC Method Statement. | Entered Value Changed.
DIN Log | DIN-362 | M364 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
DIN Log | DIN-362 | P364 | Further details of the solution are under discussion/review. | Kevin Spencer to arrange a session with Mike Ceney to discuss solution further. | Entered Value Changed.
DIN Log | DIN-362 | Q364 |  | Method statement correction | Entered Value Added.
DIN Log | DIN-362 | R364 |  | Supporting Docs | Entered Value Added.
DIN Log | DIN-362 | S364 |  | Method Statement | Entered Value Added.
DIN Log | DIN-362 | T364 |  | Annual Consumption Meth 10 | Entered Value Added.
DIN Log | DIN-371 | K373 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-371 | P373 | This would seem to best fit within ISD. Specifically Entity #21. Proposed solution is to add DIP Role ID into ISD Entity #21 We would also add validation into Entity M16 to ensure it always references the valid mappings in #21 when a new MPID to DIPID mapping is created | New entity M18 created to show the DIP market roles. Minor corrections to M16 to clarify DIP ID field length. | Entered Value Changed.
DIN Log | DIN-371 | Q373 |  | Other | Entered Value Added.
DIN Log | DIN-371 | R373 |  | Supporting Docs | Entered Value Added.
DIN Log | DIN-371 | S373 |  | ISD Entities | Entered Value Added.
DIN Log | DIN-371 | T373 |  | MHHS-EDI-021-ISD_Entities | Entered Value Added.
DIN Log | DIN-383 | K385 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-383 | T385 | BP011 - Change of Segment DES138-Interface Doc BRS002- Metering Service Requirements BRS001 - Registration Service Requirements BRS005 - LDSO Overview OPS001 - Operational Choreography MHHSP-DES229-IF005_UseCaseguide | BP011 - Change of Segment DES138-Interface Doc BRS002- Metering Service Requirements BRS003 - Registration Service Requirements BRS005 - LDSO Overview OPC001 - Operational Choreography MHHSP-DES229-IF005_UseCaseguide | Entered Value Changed.
DIN Log | DIN-384 | K386 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-384 | P386 | Block data items aligned. New validation rule add to ensure that Sender ID matches MS/DS CDC ID. New Error code REG1076 added to support validation rule. | Block data items were aligned in release 2. New validation rule on IF-38 add to ensure that Sender ID matches MS/DS CDC ID. New Error code REG1076 added to support validation rule. | Entered Value Changed.
DIN Log | DIN-388 | K390 | Initial Assessment/Updating | Closed | Entered Value Changed.
DIN Log | DIN-388 | M390 | Interim Release 4 |  | Entered Value Deleted.
DIN Log | DIN-388 | P390 | To engage with SCS | Ref DIN-507 | Entered Value Changed.
DIN Log | DIN-389 | K391 | Initial Assessment/Updating | Closed | Entered Value Changed.
DIN Log | DIN-389 | M391 | Interim Release 4 |  | Entered Value Deleted.
DIN Log | DIN-389 | P391 | To engage with SCS | CLOSED - DUPLICATE OF DIN-207 ABOVE | Entered Value Changed.
DIN Log | DIN-390 | M392 | Interim Release 3 | Interim Release 4 | Entered Value Changed.
DIN Log | DIN-391 | K393 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-391 | P393 | Created x2 new rules to prevent duplicate MPANS within repeating B90 groups within a single message. Error Code REG1079 created to support validation checks | Created x2 new rules to prevent duplicate MPANS within repeating B90 groups within a single message. Error Code REG1059 created to support validation checks | Entered Value Changed.
DIN Log | DIN-395 | K397 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-396 | K398 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-398 | J400 | Can we have an ISD entity ID for LLF data. This would be required for the API used to retrive the data from ISD data store. Are you happy for us to create and put it in the Guidance note. | Can we have an ISD entity ID for LLF data. This would be required for the API used to retrive the data from ISD data store. Are you happy for us to create and put it in the Guidance note. What is the ask? | Entered Value Changed.
DIN Log | DIN-399 | J401 | Requirement should be reworded to be "ISD must make available the data sets required by LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. | Requirement should be reworded to be "ISD must make available the data sets required by LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. ISD must make available the entire current data set to LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. | Entered Value Changed.
DIN Log | DIN-399 | P401 |  | Agreed in a session with Elexon 26/07 that the requirements document will not be changed as the requirement has already been fufilled by Elexon in line with the current requirement. | Entered Value Added.
DIN Log | DIN-409 | J411 | EDI012 ISD entities document shows that the settlement period quality indicator in entity M5 is a comma separated list of possible values. This will be difficult to use in systems that need to refer to this data. Could this instead show Actual or Estimate? Alternatively could this be split into parent and child entities to avoid a comma separated list? | EDI012 ISD entities document shows that the settlement period quality indicator in entity M5 is a comma separated list of possible values. This will be difficult to use in systems that need to refer to this data. Could this instead show Actual or Estimate? Alternatively could this be split into parent and child entities to avoid a comma separated list? Metering Service ID MPID is incorrect and must be changed to {MS Id} also in ISD Entity M8 | Entered Value Changed.
DIN Log | DIN-409 | K411 | Open - awaiting assessment | Ready for Internal Review | Entered Value Changed.
DIN Log | DIN-409 | M411 | Interim Release 5 | Interim Release 4 | Entered Value Changed.
DIN Log | DIN-409 | P411 |  | Amendments relating to “Valid Settlement Period Quality Indicator Set” wording and field length in section M5 of EDI012 ISD entities document. Change also made from Metering Service ID MPID to Metering Service {MS Id} in Entitiy M8 | Entered Value Added.
DIN Log | DIN-409 | Q411 |  | Method statement correction | Entered Value Added.
DIN Log | DIN-409 | R411 |  | Supporting Docs | Entered Value Added.
DIN Log | DIN-409 | S411 |  | Method Statement | Entered Value Added.
DIN Log | DIN-409 | T411 |  | Annual Consumption Meth 10 | Entered Value Added.
DIN Log | DIN-412 | P414 | Agreed at meeting on 27/06/23 - MMcK will draft and raise a CP to cover these changes. |  | Entered Value Deleted.
DIN Log | DIN-413 | P415 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes. | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes. Replaces DIN-442 | Entered Value Changed.
DIN Log | DIN-416 | K418 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-416 | P418 | New valued added to DI-800 Swagger 1.3 updated to reflect new value | IF -031 New valued added to DI-800 data catalogue and Swagger 1.3 updated to reflect new value | Entered Value Changed.
DIN Log | DIN-417 | K419 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-418 | K420 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-418 | P420 | New valued added to DI-800 Swagger 1.3 updated to reflect new value | IF-031 New valued added to DI-800 data catalogue and Swagger 1.3 updated to reflect new value | Entered Value Changed.
DIN Log | DIN-419 | K421 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-420 | K422 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-421 | K423 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-422 | K424 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-423 | J425 | New REGS Requirment - Only action the auto-realign functionality on MPANs where both Linked MPANs are in a Migrated state. | New REGS Requirement - Only action the auto-realign functionality on MPANs where both Linked MPANs are in a Migrated state. | Entered Value Changed.
DIN Log | DIN-423 | K425 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-424 | K426 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-424 | P426 | Note explaining that it will not be possible to Link IF-019/IF020 messages together using Correlation ID , in the case of Linked MPANs. | IF20/IF19 Note amended explaining that it will not be possible to Link IF-019/IF020 messages together using Correlation ID , in the case of Linked MPANs. | Entered Value Changed.
DIN Log | DIN-430 | K432 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-433 | K435 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-434 | K436 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-434 | P436 | Add IF-003 to DES138-Interface Cat. Created new Data items: DI-500 MHHS Regime End Date, DI-501 Rev Migration Incoming MOP MPID, DI-502, Rev Migration Incoming MOP Eff From Date, DI-503, Rev Migration Incoming DC MPID DI-504 Rev Migration Incoming DC Eff From Date. Swagger v1.3 updated to reflect new IF-003, Blocks (B096/B095/B094) & Data Items (as above). | Add data items DES138-Interface data Cat and to IF-003. Created new Data items: DI-500 MHHS Regime End Date, DI-501 Rev Migration Incoming MOP MPID, DI-502, Rev Migration Incoming MOP Eff From Date, DI-503, Rev Migration Incoming DC MPID DI-504 Rev Migration Incoming DC Eff From Date. Swagger v1.3 updated to reflect new IF-003, Blocks (B096/B095/B094) & Data Items (as above). | Entered Value Changed.
DIN Log | DIN-437 | K439 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-438 | K440 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-439 | K441 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-440 | K442 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-441 | K443 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
DIN Log | DIN-441 | P443 | Design Team Discussion with SCS required. Design Team minded that this is an invalid requirement. Helix will produce AC provided the site has not completed Reverse Migration, these updated should be accepted, design does not allow for rejection of an AC update. | Annual Consumption Method Statement section 5 has been updated with the text below in red: Where an MPAN is no longer active under MHHS during the transition phase the Market-wide Data Service shall not calculate or submit an annual consumption on the IF/PUB-040. | Entered Value Changed.
DIN Log | DIN-441 | Q443 |  | Method statement correction | Entered Value Added.
DIN Log | DIN-441 | R443 |  | Supporting Docs | Entered Value Added.
DIN Log | DIN-441 | S443 |  | Method Statement | Entered Value Added.
DIN Log | DIN-441 | T443 |  | Annual Consumption Meth 10 | Entered Value Added.
DIN Log | DIN-442 | K444 | Industry CP Required | Closed | Entered Value Changed.
DIN Log | DIN-442 | M444 | Interim Release 5 |  | Entered Value Deleted.
DIN Log | DIN-442 | P444 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes. | Original migration design. Superceded by DIN-413. | Entered Value Changed.
DIN Log | DIN-444 | K446 | Initial Assessment/Updating | Closed | Entered Value Changed.
DIN Log | DIN-444 | M446 | Interim Release 4 |  | Entered Value Deleted.
DIN Log | DIN-444 | P446 | Confirmation required from SCS | Discussed with SCS and they have confirmed that where co-incidnet COS occurs they would look to populate the [new/incoming] Linked Supplier ID.... No change to documentation required. | Entered Value Changed.
DIN Log | DIN-445 | K447 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-447 | K449 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-447 | P449 | In Swagger 1.3, updated IF-041-CustomBlock: The field B065List and B064List will be either / or as they are defined as conditionally mandatory in DES-138. This uses oneOf notation in Swagger. | In Swagger 1.3, updated IF-041-CustomBlock: The field B065List and B064List will be either / or as they are defined as conditionally mandatory in DES-138. This uses AnyOf notation in Swagger. | Entered Value Changed.
DIN Log | DIN-448 | K450 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-449 | K451 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-450 | K452 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-451 | C453 |  | CR-018 | Entered Value Added.
DIN Log | DIN-451 | E453 |  | Design Team | Entered Value Added.
DIN Log | DIN-451 | K453 | Ready for Internal Review | Initial Assessment/Updating | Entered Value Changed.
DIN Log | DIN-451 | M453 | Interim Release 3 | Interim Release 4 | Entered Value Changed.
DIN Log | DIN-451 | P453 | CR Contents incorporated into a new Section 7 of Ops Choreography Document | CR Contents incorporated into a new Section 7 of Ops Choreography Document. The redlining of the Ops Choreography document is still under review subject to approval. | Entered Value Changed.
DIN Log | DIN-452 | K454 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-452 | P454 | IF-031 alidation rules updated per the DIN Details. Consent checking rules added so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing. | IF-031 validation rules updated per the DIN Details. Consent checking rules added so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing. | Entered Value Changed.
DIN Log | DIN-453 | C455 |  | DI-124 | Entered Value Added.
DIN Log | DIN-453 | K455 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-454 | K456 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-454 | P456 | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service. added rule to support REG0011 logic in IF-031. | Entered Value Changed.
DIN Log | DIN-454 | T456 | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP-EDI021-ISD Entities | Entered Value Changed.
DIN Log | DIN-455 | K457 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-455 | P457 | IF-014 Deadline split into two. First [ActivePowerRejected] remains UNCHANGED. Deadline for [ConsumptionOnDeEnergisedMPAN] is also UNCHANGED but moved from IF-013 row into IF-014 Row, to mirror the change delivered by (DIN-255) | IF-014 Deadline split into two. First [ActivePowerRejected] remains UNCHANGED. Deadline for [ConsumptionOnDeEnergisedMPAN] is also UNCHANGED but moved from IF-013 row into IF-014 Row, to mirror the change delivered by (DIN-255). OPC_580 ID details updated in OPC001 Operational Choreography document. | Entered Value Changed.
DIN Log | DIN-455 | T457 | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP_OPC001_Operational_Choreography | Entered Value Changed.
DIN Log | DIN-456 | K458 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-457 | P459 |  | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes. | Entered Value Added.
DIN Log | DIN-458 | J460 | New Validation Rule required for IF-019 to ensure that only Import MPANs can be realted. Add to Create and Add Related - this is per REC Shedulle 28 | New Validation Rule required for IF-019 to ensure that only Import MPANs can be related. Add to Create and Add Related - this is per REC Shedulle 28 | Entered Value Changed.
DIN Log | DIN-458 | K460 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-460 | K462 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-460 | P462 | Spelling mistake corrected in Data Catallouge, IF-019, IF-020. Note YAML name also corrected for DI-073. | Spelling mistake corrected in Data Catalogue, IF-019, IF-020. Note YAML name also corrected for DI-073. | Entered Value Changed.
DIN Log | DIN-460 | T462 | Swagger 1.3 | MHHSP-DES138-Interface Catalogue Swagger 1.3 | Entered Value Changed.
DIN Log | DIN-461 | K463 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-462 | K464 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-463 | K465 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-464 | K466 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-465 | K467 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-465 | P467 | BP010 Related MPANs Process updated to show specific Rejection Route. | BP010B Related MPANs Process updated to show specific Rejection Route. | Entered Value Changed.
DIN Log | DIN-466 | K468 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-466 | T468 | DES138-InterfaceCatalouge | MHHSP-DES138-Interface Catalogue | Entered Value Changed.
DIN Log | DIN-467 | K469 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
DIN Log | DIN-467 | P469 | Further details of the solution are under discussion/review. | Various updates to obfuscation on IF-036 to align with IF-035. DI-019/DI-800/DI-809/DI-207 obfuscated for Data Service DI-020/Di-800/DI-126/DI-842/DI-209/Di-844/DI-811/DI-208 /DI-018 obfuscated for Metering Service | Entered Value Changed.
DIN Log | DIN-467 | Q469 |  | Data interface correction | Entered Value Added.
DIN Log | DIN-467 | R469 |  | Supporting Docs | Entered Value Added.
DIN Log | DIN-467 | S469 |  | Interface Catalogue | Entered Value Added.
DIN Log | DIN-467 | T469 |  | MHHS-DES138-Interfaces | Entered Value Added.
DIN Log | DIN-468 | K470 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-469 | K471 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-469 | P471 | Remove Z0 & Z1 data items from all MHHS reports in ECS external reporting artefact | Removed Z0 & Z1 data items from all MHHS reports in ECS external reporting artefact | Entered Value Changed.
DIN Log | DIN-470 | K472 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-471 | K473 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-471 | P473 | Update R019 parent to R017 for REP-003 in ERI011B - ECS Reports External. Swagger v1.3 updated to align with changes within ECS reports artefact. | Updated R019 parent to R017 for REP-003 in ERI011B - ECS Reports External. Swagger v1.3 updated to align with changes within ECS reports artefact. | Entered Value Changed.
DIN Log | DIN-471 | T473 | Swagger 1.3 | ERI021 -ECS Reports External Swagger 1.3 | Entered Value Changed.
DIN Log | DIN-473 | K475 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-474 | P476 | Addition of DI-503, DI-504, DI-505 data items across ECS reports artefact. MHHSP - ERI011B - ECS Reports - External v5.2 and MHHSP - ERI011A - ECS Reports - Internal v5.2 | Addition of data items DI-503-DI-513 to data catalogue and across ECS reports artefact. MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Entered Value Changed.
DIN Log | DIN-475 | P477 | Update to block names, DTN references, data items and descriptions in MHHSP - ERI011B - ECS Reports - External v5.2 | Update to block names, DTN references, data items, descriptions and reordering of data item blocks to exisiting reports in MHHSP - ERI011B - ECS Reports - External | Entered Value Changed.
DIN Log | DIN-476 | K478 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-476 | P478 | To align with Open API spec clarification at https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md, we have updated all Data Types that are nullable and have an enum to align as follows: Following discussion, have decided to align with OpenAPI 3.1 DI-076-Estimation-Reason-Code: description : Used inconjunction with Settlement Period Quality Indicator to explain why data has been estimated type : string nullable: true maxLength : 2 example : '1' enum: - '1' # OptOut - '2' # Missing .. - '8' # Disconnected - '9' # Consumption Amendment - '10' # NonSmart - null The Data Types affected / updated as as follows: --- DI-039-Load-Shape-GSP-Group-ID --- DI-076-Estimation-Reason-Code --- DI-096-Site-Visit-Check-Code --- DI-126-Traditional-Fall-Back-Read-Frequency --- DI-137-IHD-Install-Status --- DI-150-Annual-Consumption-Quality-Indicato | To align with Open API spec clarification at https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md, we have updated all Data Types that are nullable and have an enum to align as follows: Following discussion, have decided to align with OpenAPI 3.1 DI-076-Estimation-Reason-Code: description : Used inconjunction with Settlement Period Quality Indicator to explain why data has been estimated type : string nullable: true maxLength : 2 example : '1' enum: - '1' # OptOut - '2' # Missing .. - '8' # Disconnected - '9' # Consumption Amendment - '10' # NonSmart - null The Data Types affected / updated as follows: --- DI-039-Load-Shape-GSP-Group-ID --- DI-076-Estimation-Reason-Code --- DI-096-Site-Visit-Check-Code --- DI-126-Traditional-Fall-Back-Read-Frequency --- DI-137-IHD-Install-Status --- DI-150-Annual-Consumption-Quality-Indicator | Entered Value Changed.
DIN Log | DIN-477 | M479 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
DIN Log | DIN-478 | J480 | In the Release 2 version of DES138 a limit was introduced that asked Participants not to submit more than 150 Settlement Days’ worth of data in a single message. The value of 150 was proposed as this meant a single message would realistically be ~600KB in size. We’ve had some queries regarding this value, and given ECS should reject consumption data if it over 194 days old, the proposal is to increase sizing from 150 to 194 day message and the size increases from 600KB to ~780KB for IF-021 message. ECS will need to validate the message contents. However, rather than letting a ‘large’ IF-021 message traversing though the DIP, the proposal is to limit the IF-021 on ingress to the DIP and a single request will have a limit of 1MB – this will done at the API level. | In the Release 2 version of DES138 a limit was introduced that asked Participants not to submit more than 150 Settlement Days’ worth of data in a single message. The value of 150 was proposed as this meant a single message would realistically be ~600KB in size. We’ve had some queries regarding this value, the proposal is to increase sizing from 150 to 194 day message and the size increases from 600KB to ~780KB for IF-021 message. ECS will need to validate the message contents. However, rather than letting a ‘large’ IF-021 message traversing though the DIP, the proposal is to limit the IF-021 on ingress to the DIP and a single request will have a limit of 1MB – this will done at the API level. | Entered Value Changed.
DIN Log | DIN-478 | K480 | Requires Industry Work Group review | Initial Assessment/Updating | Entered Value Changed.
DIN Log | DIN-478 | L480 | 7/17/2023 (17/07/2023 00:00:00) |  | Entered Value Deleted.
DIN Log | DIN-478 | P480 | DIN DETAILS TO BE UPDATED FOLLOWING DRG 17/07/2023 | Update DES138 so that it is clear that the minimum number of settlement days in a message is increasing from 150 to 194. | Entered Value Changed.
DIN Log | DIN-478 | Q480 |  | Data interface correction | Entered Value Added.
DIN Log | DIN-478 | R480 |  | Minor | Entered Value Added.
DIN Log | DIN-478 | S480 |  | DES138 and Swagger | Entered Value Added.
DIN Log | DIN-478 | T480 |  | DES-138 and Swagger 1.4 | Entered Value Added.
DIN Log | DIN-479 | K481 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-480 | K482 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-480 | P482 | SCS have confirmed that it is possible currently and should continue to be possible to manage MPAN Linkages whilst MPAN(s) are at Created Status. Therefore we have reversed the change implemented at part of DIN105 and now allow processing of IF-019 if mpan status = "Created" | SCS have confirmed that it is possible currently and should continue to be possible to manage MPAN Linkages whilst MPAN(s) are at Created Status. Therefore we have reversed the change implemented as part of DIN105 and now allow processing of IF-019 if mpan status = "Created" | Entered Value Changed.
DIN Log | DIN-481 | K483 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
DIN Log | DIN-481 | P483 | Further details of the solution are under discussion/review. | Two new data type references have been created DT-024 and DT-024N. For NUM(16,6) data type within ECS reports/ECS data catalogue replace DT-023/DT-023N with DT-024/DT-024N. | Entered Value Changed.
DIN Log | DIN-481 | Q483 |  | Reporting correction | Entered Value Added.
DIN Log | DIN-481 | R483 |  | Minor | Entered Value Added.
DIN Log | DIN-481 | S483 |  | ECS Reports | Entered Value Added.
DIN Log | DIN-481 | T483 |  | "MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2" | Entered Value Added.
DIN Log | DIN-484 | M486 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
DIN Log | DIN-484 | P486 | Update section 4.6.1 in the E2E001 Design document to provide better clarity on how SenderID and RecipientID are populated in the StandardResponseBodyType. Provided worked examples for L1-L6 to illustrate this as examples. | Update section 4.6.1 in the E2E001 Design document to provide better clarity on how SenderID and RecipientID are populated in the StandardResponseBodyType. Provided worked examples for L1-L6 to illustrate this as examples. Updated Swagger 1.4 to align with the above. | Entered Value Changed.
DIN Log | DIN-485 | F487 |  | 2380 | Entered Value Added.
DIN Log | DIN-485 | I487 | Unable to identify Recipient / Role on DELETE | Unable to identify Recipient on DELETE and some POST methods | Entered Value Changed.
DIN Log | DIN-485 | J487 | For the DELETE methods in Swagger for StatusMessage and PublicationConfig, need to update the method so you can identify the correct recipientID and roleID to be used for the method call. | For the DELETE methods in Swagger for StatusMessage and PublicationConfig, need to update the method so you can identify the correct recipientID to be used for the method call. Some frameworks will ignore a body on a DELETE method as being incompatible with the semantics of the DELETE method, and the correct RESTful implementation would be something more along the lines of "DELETE dip-channel/{id}/{role}/pubconfig". Which of course raises the question of whether the POST message should be refactored for consistency. The issue is more widespread han just the DELETE methods, it also affects some of the POST methods where a recieipent ID is required | Entered Value Changed.
DIN Log | DIN-485 | P487 | Further details of the solution are under discussion/review. | Design changes required to Swagger 1.4 to support updates to API endpoints for DELETE API verbs to ensure we are able to remove the correct StatusMessage or PublicationConfig for the appropriate recipient combination. The isue also affects some of the POST methods where a recipient ID is required, e.g webhook config. A standard pattern is proposed where a recipeint id is specified in the path. Updates will also be made to E2E001 design document to ensure the document provides any clarity required. | Entered Value Changed.
DIN Log | DIN-486 | J488 | Please can you raise a DIN to cover the following request from Participant to clarify the From and To Parties at the top of each sheet to align with the role codes the programme is using and defined in the E2E Solution Architecture document. And if these ‘pure’ roles code could be included in the introduction sheet that would certainly help. More detail can be seen in the Ticket | Please can you raise a DIN to cover the following request from Participant to clarify the From and To Parties at the top of each sheet to align with the role codes the programme is using and defined in the E2E Solution Architecture document. And if these ‘pure’ roles code could be included in the introduction sheet that would certainly help. More detail can be seen in the Ticket | Entered Value Changed.
DIN Log | DIN-486 | K488 | Closed | Initial Assessment/Updating | Entered Value Changed.
DIN Log | DIN-486 | M488 |  | Interim Release 4 | Entered Value Added.
DIN Log | DIN-486 | P488 |  | Update the role codes in DES-138 for the From / To Parties for each of the Interfaces to align with other documents including E2E001. Update information in the Introductory section in DES-138 to aid understanding / clarity. | Entered Value Added.
DIN Log | DIN-486 | Q488 |  | Design Ambiguous | Entered Value Added.
DIN Log | DIN-486 | R488 |  | Supporting Docs | Entered Value Added.
DIN Log | DIN-486 | S488 |  | DES-138, E2E001 | Entered Value Added.
DIN Log | DIN-486 | T488 |  | DES-138, E2E001 | Entered Value Added.
DIN Log | DIN-487 | P489 | Further details of the solution are under discussion/review. | Updates required to E2E001 design section 4.4.4 to ensure we improve clarity on schema vs data validation errors, with updates to worked examples and JSON examples. | Entered Value Changed.
DIN Log | DIN-487 | T489 |  | E2E001 E2E Architecture Document Swagger 1.4 | Entered Value Added.
DIN Log | DIN-488 | F490 |  | 1506 | Entered Value Added.
DIN Log | DIN-488 | G490 | ME | Steve Weston | Entered Value Changed.
DIN Log | DIN-490 | P492 | This should be consistent across all interfaces in that a schema validation failure for any message should fail the entire request. In the E2E001 design, sections 4.4.3 and 4.6 are to be updated to reflect this / provide the appropriate level of clarity. | This should be consistent across all interfaces in that a schema validation failure for any message should fail the entire request. In the E2E001 design, sections 4.4.3 and 4.6 are to be updated to reflect this / provide the appropriate level of clarity. This issue affects both the http delete operations. Easy to fix, same fix as the post need to include the webconfigas a parameter | Entered Value Changed.
DIN Log | DIN-494 | E496 |  | Callisto | Entered Value Added.
DIN Log | DIN-494 | K496 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
DIN Log | DIN-495 | E497 |  | Design Team | Entered Value Added.
DIN Log | DIN-495 | K497 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-495 | M497 | Interim Release 4 | Interim Release 3 | Entered Value Changed.
DIN Log | DIN-495 | P497 | IF-035 for Trad/Advanced meters was previously shown as being direct interaction between REGS and MS. Changed to show message as flowing via the DIP | IF-035 for Trad/Advanced meters was previously shown as a flow being direct interaction between REGS and MS. Changed to show message as flowing via the DIP (at step 90). Also change applied to Forward migration process for consistency. | Entered Value Changed.
DIN Log | DIN-495 | Q497 | Data interface correction | Process Model correction | Entered Value Changed.
DIN Log | DIN-495 | R497 | Supporting Docs | MPAN Ownership | Entered Value Changed.
DIN Log | DIN-495 | S497 | Interface Catalogue | BP003 | Entered Value Changed.
DIN Log | DIN-495 | T497 | DES138-InterfaceCatalogue | MHHSP-BP003-Change of Service - Data Service MHHS-DEL964 BPM-003 - Change of Servie - Data Service - Forward Migration | Entered Value Changed.
DIN Log | DIN-497 | P499 | Be consistent - use either 90 days or trhee months within the document | Be consistent - use either 90 days or three months within the document | Entered Value Changed.
DIN Log | DIN-503 | P505 | Update any Data Items that utilise InterfaceID to align with the enumeration of values defined for DI-000 to that this is unique across all interface / report types. This includes data types like SenderUniqueReference (DI-995) and TransactionID (DI-990). This change will require updates in DES-138, E2E001 and Swagger 1.4. | Update any Data Items that utilise InterfaceID to align with the enumeration of values defined for DI-000 so that this is unique across all interface / report types. This includes data types like SenderUniqueReference (DI-995) and TransactionID (DI-990). This change will require updates in DES-138, E2E001 and Swagger 1.4. | Entered Value Changed.
DIN Log | DIN-506 | P508 | Changed to "UTC Settlement Period Consumption Data (Warnings & Rejections)" | Changed to "UTC Settlement Period Consumption Data (Warnings & Rejections)". Interface description and notes updated to reflect that IF-014 could also contain warnings for Consumption on De-enegised sites. | Entered Value Changed.
DIN Log | DIN-507 | C509 |  | DI-194 | Entered Value Added.
DIN Log | DIN-507 | G509 | Sean COoper | Sean Cooper | Entered Value Changed.
DIN Log | DIN-508 | J510 | Addition of MP Status and RMP Status Effective From Dates to IF-050 | Addition of MP Status and RMP Status Effective From Dates to IF-050 ( Linked to DIN 318 ) | Entered Value Changed.
DIN Log | DIN-508 | K510 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
DIN Log | DIN-508 | P510 | New Data Items Created DI : DI-167 RMP Status (Registration) DI-168 MP Status | New Data Items Created and added to IF-050 in block B079: DI-167 RMP Status Effective From Date DI-168 MP Status Effective from Date (DIN 318 Closed as duplicate) | Entered Value Changed.
DIN Log | DIN-509 | B511 |  | SW | Entered Value Added.
DIN Log | DIN-509 | D511 |  | 18/07/2023 (18/07/2023 00:00:00) | Entered Value Added.
DIN Log | DIN-509 | E511 |  | MHHS | Entered Value Added.
DIN Log | DIN-509 | G511 |  | Steve Weston | Entered Value Added.
DIN Log | DIN-509 | H511 |  | Central Body | Entered Value Added.
DIN Log | DIN-509 | I511 |  | Missing Archival NFR Information | Entered Value Added.
DIN Log | DIN-509 | J511 |  | There is no detailed non-functional requirements in relation to data archiving, retrieval, archival tiers, recovery from archival so we need to update the NFR's to ensure these are included. | Entered Value Added.
DIN Log | DIN-509 | K511 |  | Open - awaiting assessment | Entered Value Added.
DIN Log | DIN-509 | M511 |  | Interim Release 5 | Entered Value Added.
DIN Log | DIN-509 | P511 |  | Further details of the solution are under discussion/review. | Entered Value Added.
DIN Log | DIN-510 | B512 |  | SW | Entered Value Added.
DIN Log | DIN-510 | D512 |  | 18/07/2023 (18/07/2023 00:00:00) | Entered Value Added.
DIN Log | DIN-510 | E512 |  | MHHS | Entered Value Added.
DIN Log | DIN-510 | F512 |  | 2675 | Entered Value Added.
DIN Log | DIN-510 | G512 |  | Steve Weston | Entered Value Added.
DIN Log | DIN-510 | H512 |  | Central Body | Entered Value Added.
DIN Log | DIN-510 | I512 |  | Properties on block B047 | Entered Value Added.
DIN Log | DIN-510 | J512 |  | The Swagger definition has the properties ‘sp’,’v’,’q’,’e’ and ‘arc’ which matches the items in red. However the data catalogue has different YAML names. YAML Swagger names have to be updated in DES-138 to match the above characters. | Entered Value Added.
DIN Log | DIN-510 | K512 |  | Ready for Internal Review | Entered Value Added.
DIN Log | DIN-510 | M512 |  | Interim Release 4 | Entered Value Added.
DIN Log | DIN-510 | P512 |  | This was done to reduce IF-021 content size, but the DES-138 5.4.1 YAML needs to be updated to align with Swagger 1.4 - the YAML names should be as follows DI-082 ‘sp’ - B052 (IF-022), B047 (IF-021) DI-147 ’v’ - B047(IF-021, 4, 16) DI-083 ’q’ - B047 (IF-021, 14, 16) DI-076 ’e’ - B047 (IF-021, 14, 16) DI-166 ‘arc’ - B073 (IF-027 / 28) Swagger 1.4 has been updated to align for the approrpiate blocks above to ensure consistency across the data catalogue. | Entered Value Added.
DIN Log | DIN-510 | Q512 |  | Data Interface correction | Entered Value Added.
DIN Log | DIN-510 | R512 |  | Supporting Docs | Entered Value Added.
DIN Log | DIN-510 | S512 |  | Interface Catalogue | Entered Value Added.
DIN Log | DIN-510 | T512 |  | DES138-InterfaceCatalogue | Entered Value Added.
DIN Log | DIN-511 | B513 |  | BK | Entered Value Added.
DIN Log | DIN-511 | C513 |  | CR027 | Entered Value Added.
DIN Log | DIN-511 | D513 |  | 18/07/2023 (18/07/2023 00:00:00) | Entered Value Added.
DIN Log | DIN-511 | E513 |  | Eastern Power Networks | Entered Value Added.
DIN Log | DIN-511 | G513 |  | Peter Waymont | Entered Value Added.
DIN Log | DIN-511 | H513 |  | Network Operator | Entered Value Added.
DIN Log | DIN-511 | I513 |  | DUoS E-Billing DIP Message for MHHS | Entered Value Added.
DIN Log | DIN-511 | J513 |  | A new flow needs to be introduced for e-billing of site-specific DUoS in the post Market-Wide Half-Hourly Settlement (MHHS) environment because the existing flow uses the DTN and all other DUoS data will be DIP based. The change is required in order to continue to operate the site specific DUoS billing process in the MHHS environment. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the HH data sent by Data Services to the LDSO for use in DUoS billing, using IF-021/IF-013/IF-014. At present DUoS billing systems can send the D2021 data flow as a form of e-billing for site-specific DUoS, using the DTN. As DUoS billing systems will need to interact with the DIP for migrated site-specific billed customers, it is preferable that the outputs are also DIP messages, to enable the parties to move forward completely in the new environment. A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors | Entered Value Added.
DIN Log | DIN-511 | K513 |  | Open - awaiting assessment | Entered Value Added.
DIN Log | DIN-511 | M513 |  | Interim Release 5 | Entered Value Added.
DIN Log | DIN-52 | M54 | Interim Release 1 |  | Entered Value Deleted.
DIN Log | DIN-70 | K72 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-87 | K89 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-87 | T89 | MHHSP-BP009 | MHHSP-BP009 MHHSP-BP008 | Entered Value Changed.
DIN Log | DIN-88 | K90 | Initial Assessment/Updating | Closed | Entered Value Changed.
DIN Log | DIN-88 | M90 | Interim Release 3 |  | Entered Value Deleted.
DIN Log | DIN-88 | N90 | 12/07/2023 (12/07/2023 00:00:00) |  | Entered Value Deleted.
DIN Log | DIN-88 | Q90 | Process Model correction |  | Entered Value Deleted.
DIN Log | DIN-88 | R90 | MPAN Ownership |  | Entered Value Deleted.
DIN Log | DIN-88 | S90 | Change of Service |  | Entered Value Deleted.
DIN Log | DIN-88 | T90 | MHHSP-BP002-Change of Metering Service MHHSP-BPD002 |  | Entered Value Deleted.
DIN Log | DIN-94 | K96 | Ready for Internal Review | Updates Ready to Release | Entered Value Changed.
DIN Log | DIN-94 | P96 | Question 1. Supplier will receive both events as outlined in BP007 (See DIN 294) Question 2. BPD009 step 145 updated to show that Supplier cannot choose to receive rejections. A decision was made at the DRG on 29th June to leave the messaging in BPD009 step 145 and instead update the business process model in BPD009 to give Supplier's the option to subscribe to rejections. | Question 1. Supplier will receive both events as outlined in BP007 (See DIN 294) Question 2. A decision was made at the DRG on 29th June to leave the messaging in BPD009 step 145 and instead update the business process model in BPD009 to give Supplier's the option to subscribe to rejections. | Entered Value Changed.
DIN Log | DIN-94 | S96 | Disconnection / Change of Metering | Change of Metering | Entered Value Changed.
DIN Log | DIN-94 | T96 | MHHSP-BP007-Disconnection MHHSP-BP009 – Change of Metering (Install / Remove / Exchange) MHHSP-DES138-Interface Catalogue | MHHSP-BP009 – Change of Metering (Install / Remove / Exchange) , MHHSP-BPD009 MHHSP-DES138-Interface Catalogue | Entered Value Changed.

## DIN Compare 310823 (hidden)
DIN Log Compare between 17/08/23 and 31/08/23
Differences
Sheet | DIN Reference | Range | Old Value | New Value | Description
Log | DIN-621 | B623 |  | SC | Entered Value Added.
Log | DIN-622 | B624 |  | SC | Entered Value Added.
Log | DIN-623 | B625 |  | SC | Entered Value Added.
Log | DIN-624 | B626 |  | ME | Entered Value Added.
Log | DIN-625 | B627 |  | SC | Entered Value Added.
Log | DIN-626 | B628 |  | SC | Entered Value Added.
Log | DIN-627 | B629 |  | SC | Entered Value Added.
Log | DIN-628 | B630 |  | SC | Entered Value Added.
Log | DIN-629 | B631 |  | MF | Entered Value Added.
Log | DIN-630 | B632 |  | MF | Entered Value Added.
Log | DIN-631 | B633 |  | SC | Entered Value Added.
Log | DIN-632 | B634 |  | SC | Entered Value Added.
Log | DIN-633 | B635 |  | SC | Entered Value Added.
Log | DIN-622 | C624 |  | SCS | Entered Value Added.
Log | DIN-623 | C625 |  | SCS | Entered Value Added.
Log | DIN-625 | C627 |  | SCS | Entered Value Added.
Log | DIN-626 | C628 |  | ESG | Entered Value Added.
Log | DIN-627 | C629 |  | ESG | Entered Value Added.
Log | DIN-621 | D623 |  | 17/08/2023 (17/08/2023 00:00:00) | Entered Value Added.
Log | DIN-622 | D624 |  | 17/08/2023 (17/08/2023 00:00:00) | Entered Value Added.
Log | DIN-623 | D625 |  | 17/08/2023 (17/08/2023 00:00:00) | Entered Value Added.
Log | DIN-624 | D626 |  | 18/08/2023 (18/08/2023 00:00:00) | Entered Value Added.
Log | DIN-625 | D627 |  | 18/08/2023 (18/08/2023 00:00:00) | Entered Value Added.
Log | DIN-626 | D628 |  | 22/08/2023 (22/08/2023 00:00:00) | Entered Value Added.
Log | DIN-627 | D629 |  | 22/08/2023 (22/08/2023 00:00:00) | Entered Value Added.
Log | DIN-628 | D630 |  | 23/08/2023 (23/08/2023 00:00:00) | Entered Value Added.
Log | DIN-629 | D631 |  | 25/08/2023 (25/08/2023 00:00:00) | Entered Value Added.
Log | DIN-630 | D632 |  | 25/08/2023 (25/08/2023 00:00:00) | Entered Value Added.
Log | DIN-631 | D633 |  | 29/08/2023 (29/08/2023 00:00:00) | Entered Value Added.
Log | DIN-632 | D634 |  | 31/08/2023 (31/08/2023 00:00:00) | Entered Value Added.
Log | DIN-633 | D635 |  | 31/08/2023 (31/08/2023 00:00:00) | Entered Value Added.
Log | DIN-621 | E623 |  | MHHS | Entered Value Added.
Log | DIN-622 | E624 |  | SCS | Entered Value Added.
Log | DIN-623 | E625 |  | SCS | Entered Value Added.
Log | DIN-624 | E626 |  | MHHS | Entered Value Added.
Log | DIN-625 | E627 |  | SCS | Entered Value Added.
Log | DIN-626 | E628 |  | ESG | Entered Value Added.
Log | DIN-627 | E629 |  | ESC | Entered Value Added.
Log | DIN-632 | E634 |  | Helix | Entered Value Added.
Log | DIN-633 | E635 |  | Helix | Entered Value Added.
Log | DIN-563 | F565 |  | 2705 | Entered Value Added.
Log | DIN-630 | F632 |  | N/A | Entered Value Added.
Log | DIN-631 | F633 |  | N/A | Entered Value Added.
Log | DIN-632 | F634 |  | N/A | Entered Value Added.
Log | DIN-633 | F635 |  | N/A | Entered Value Added.
Log | DIN-621 | G623 |  | Sean Cooper | Entered Value Added.
Log | DIN-622 | G624 |  | Sean Cooper | Entered Value Added.
Log | DIN-623 | G625 |  | Sean Cooper | Entered Value Added.
Log | DIN-624 | G626 |  | Miriam Ellis | Entered Value Added.
Log | DIN-625 | G627 |  | Sean Cooper | Entered Value Added.
Log | DIN-626 | G628 |  | Sean Cooper | Entered Value Added.
Log | DIN-627 | G629 |  | Sean Cooper | Entered Value Added.
Log | DIN-628 | G630 |  | Sean Cooper | Entered Value Added.
Log | DIN-629 | G631 |  | Mike Fensome | Entered Value Added.
Log | DIN-630 | G632 |  | Mike Fensome | Entered Value Added.
Log | DIN-631 | G633 |  | Sean Cooper | Entered Value Added.
Log | DIN-632 | G634 |  | Sean Cooper | Entered Value Added.
Log | DIN-633 | G635 |  | Sean Cooper | Entered Value Added.
Log | DIN-621 | H623 |  | SRO Design | Entered Value Added.
Log | DIN-622 | H624 |  | SRO Design | Entered Value Added.
Log | DIN-623 | H625 |  | SRO Design | Entered Value Added.
Log | DIN-624 | H626 |  | SRO Design | Entered Value Added.
Log | DIN-625 | H627 |  | SRO Design | Entered Value Added.
Log | DIN-626 | H628 |  | SRO Design | Entered Value Added.
Log | DIN-627 | H629 |  | SRO Design | Entered Value Added.
Log | DIN-628 | H630 |  | SRO Design | Entered Value Added.
Log | DIN-629 | H631 |  | SRO Design | Entered Value Added.
Log | DIN-630 | H632 |  | SRO Design | Entered Value Added.
Log | DIN-631 | H633 |  | SRO Design | Entered Value Added.
Log | DIN-632 | H634 |  | SRO Design | Entered Value Added.
Log | DIN-633 | H635 |  | SRO Design | Entered Value Added.
Log | DIN-572 | I574 | Clearification of IF-013 Issuance | Clarification of IF-013 Issuance | Entered Value Changed.
Log | DIN-584 | I586 | DI-511 Change of Data Type from String to Number | DI-511 Change of Data Type from String to Number in IF-024 | Entered Value Changed.
Log | DIN-597 | I599 | IF-026 B069 Presence | IF-026 B068 Presence | Entered Value Changed.
Log | DIN-606 | I608 | Update Ops C to include clearification on issuing of IF-035 | Update Ops C to include clarification on issuing of IF-035 | Entered Value Changed.
Log | DIN-615 | I617 | Number of Registers Validation | Number of Registers Validation | Entered Value Changed.
Log | DIN-621 | I623 |  | Changes to D303 DTN Flow | Entered Value Added.
Log | DIN-622 | I624 |  | DIP Validation of Sender Correlation ID | Entered Value Added.
Log | DIN-623 | I625 |  | Change IF-001 Routing | Entered Value Added.
Log | DIN-624 | I626 |  | BP013 DDE Updates | Entered Value Added.
Log | DIN-625 | I627 |  | B092 should also be array to allow MPRS to populate multiple rejections | Entered Value Added.
Log | DIN-626 | I628 |  | Update Routing of IF-003 | Entered Value Added.
Log | DIN-627 | I629 |  | Update Interface Doc "Correlation ID Required" to "Correlation ID Created" | Entered Value Added.
Log | DIN-628 | I630 |  | Add in Missing IF-021 Validation | Entered Value Added.
Log | DIN-629 | I631 |  | Routing for SUPC on IF-037 | Entered Value Added.
Log | DIN-630 | I632 |  | Remove incorrect arrow on BP002 | Entered Value Added.
Log | DIN-631 | I633 |  | Swagger Alignment - Block B051 | Entered Value Added.
Log | DIN-632 | I634 |  | Header & Footer Requirements for ISD Entity Files | Entered Value Added.
Log | DIN-633 | I635 |  | Update to ISD E45 | Entered Value Added.
Log | DIN-414 | J416 | Ref Previous DIN-244. In the "DES196 D-Flow Document" the D0275 is showing as redundent. This is misleading it should be marked as by agreement between contracting Supplier-DS. Document should be updated to reflect this. | Ref Previous DIN-244. In the "DES196 D-Flow Document" the D0275 is showing as redundant. This is misleading it should be marked as by agreement between contracting Supplier-DS. Document should be updated to reflect this. | Entered Value Changed.
Log | DIN-545 | J547 | Update swagger to show DI-496 as INT (3) | Update swagger to show DI-496 as INT (2) | Entered Value Changed.
Log | DIN-574 | J576 | Smets 1 Number of digits can be 0 - 9 Replaces previous logic. | Smets 1 Number of digits can be 0 - 9 Replaces previous logic. | Entered Value Changed.
Log | DIN-597 | J599 | IF-026 / B069 - SCS requested removal of wording "must be required for smart meter removed" as this is inherant as part of the Event Type. | IF-026 / B068 - SCS requested removal of wording "must be required for smart meter removed" as this is inherent as part of the Event Type. | Entered Value Changed.
Log | DIN-613 | J615 | In line with DAG Decision on 4th Aug - it was agreed that ALL Serive Provider Appointments should commence at Midnight UTC. Text against DI-086 and Di-121 has been removed. A new section addressing the treatment of Time has been added to the Additional Information tab of DES-138 | In line with DRG Decision on 4th Aug - it was agreed that ALL Service Provider Appointments should commence at Midnight UTC. Text against DI-086 and DI-121 has been removed. A new section addressing the treatment of Time has been added to the Additional Information tab of DES-138 | Entered Value Changed.
Log | DIN-615 | J617 | Clarification following on from DIN-574. Text against Number of Register Digits field ammended to say "per the manufacturer specification" . Note text for SCS validation will remain unchanged. | Clarification following on from DIN-574. Text against Number of Register Digits fields amended to say "per the manufacturer specification" . Note text for SCS validation will remain unchanged. Swagger validation of this field updated to match SCS logical test ie value can be 0-9 | Entered Value Changed.
Log | DIN-617 | J619 |  | Missing interface notes on Discretionary Use of IF-023/IF-040 by Data Service | Entered Value Added.
Log | DIN-621 | J623 |  | Need to make "Manufacture and Type" non mandatory in the D303 flow. Follow migration to MHHS it is possible that this data item is not held in REGS and therefore not shared with all MHHS Participants incl. MS who currently would need to provided it on the D303. Discussions were held in Data Working group around back population of this data item but that proposal was REJECTED - therefore only other option is to make this field optional in D303 | Entered Value Added.
Log | DIN-622 | J624 |  | Implement DIP validation to check for incorrect population of Sender Correlation ID. | Entered Value Added.
Log | DIN-623 | J625 |  | Add SUPL (Linked Supplier) as an additional Primary Receipient of Inital Registration Event | Entered Value Added.
Log | DIN-624 | J626 |  | MHHS test team have identified discrepancies within the ECS BPM's that require updates to align with the ECS reports. Updates are required to BPM13 DDE | Entered Value Added.
Log | DIN-625 | J627 |  | B092 should also be array to allow MPRS to populate multiple rejections | Entered Value Added.
Log | DIN-626 | J628 |  | Routing of this flow should match that of the IF-037 - in that a copy should also be sent to the Supplier. IF-003 Routing table updated to show Supplier as being a receipient of the iF-003 | Entered Value Added.
Log | DIN-627 | J629 |  | Inconsistancy indentified in the column headings across different IFs. All should read "Correlation ID Created" as this column denotes if the DIP IF should create/copy a DIP Correlation ID value or not. | Entered Value Added.
Log | DIN-628 | J630 |  | Add NEW validation to ensure that "UTC Settlement Date" has time of Midnight UTC. Added clarification to existing validation rule that time element of "Settlement period end date time" should align with Settlement period duration | Entered Value Added.
Log | DIN-629 | J631 |  | To ensure that the outgoing Supplier are correctly notified of de-appointment of their Service Providers, routing rules for SUPC updated to Primary routing for IF-037 | Entered Value Added.
Log | DIN-630 | J632 |  | Arrow incorrectly added into BPOO2 between steps 225 and steps 245 | Entered Value Added.
Log | DIN-631 | J633 |  | Required Data Items field names do not match those specfied in the defintion. | Entered Value Added.
Log | DIN-632 | J634 |  | ISD Specification should be updated to include specification/definition of a standard Header and Footer to be applied to each ISD Entity CSV file. | Entered Value Added.
Log | DIN-633 | J635 |  | Update Entity 45 - Market Role code needs to allow Blanks in order to align with other tables in ISD and to provide for [new] Market Participants who dont have a legacy market particpant role code | Entered Value Added.
Log | DIN-207 | K209 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
Log | DIN-241 | K243 | Initial Assessment/Updating | Closed | Entered Value Changed.
Log | DIN-246 | K248 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
Log | DIN-298 | K300 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-300 | K302 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-301 | K303 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-302 | K304 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-335 | K337 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-336 | K338 | Open - awaiting assessment | Initial Assessment/Updating | Entered Value Changed.
Log | DIN-338 | K340 | Open - awaiting assessment | Initial Assessment/Updating | Entered Value Changed.
Log | DIN-339 | K341 | Open - awaiting assessment | Initial Assessment/Updating | Entered Value Changed.
Log | DIN-340 | K342 | Open - awaiting assessment | Initial Assessment/Updating | Entered Value Changed.
Log | DIN-342 | K344 | Open - awaiting assessment | Initial Assessment/Updating | Entered Value Changed.
Log | DIN-358 | K360 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-359 | K361 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-360 | K362 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-361 | K363 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-390 | K392 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-414 | K416 | Open - awaiting assessment | Closed | Entered Value Changed.
Log | DIN-441 | K443 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-451 | K453 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-467 | K469 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-474 | K476 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-475 | K477 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-478 | K480 | Initial Assessment/Updating | Implemented | Entered Value Changed.
Log | DIN-485 | K487 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-486 | K488 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-487 | K489 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-488 | K490 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-489 | K491 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-493 | K495 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-494 | K496 | Initial Assessment/Updating | Closed | Entered Value Changed.
Log | DIN-503 | K505 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-505 | K507 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-506 | K508 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-507 | K509 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-508 | K510 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-510 | K512 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-512 | K514 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-513 | K515 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-514 | K516 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-515 | K517 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-516 | K518 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-517 | K519 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-518 | K520 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-519 | K521 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-520 | K522 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-521 | K523 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-522 | K524 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-523 | K525 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-524 | K526 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-525 | K527 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-526 | K528 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-527 | K529 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-528 | K530 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-529 | K531 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-530 | K532 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-532 | K534 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-533 | K535 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-534 | K536 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-535 | K537 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-536 | K538 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-537 | K539 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-538 | K540 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-539 | K541 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-540 | K542 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-541 | K543 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-542 | K544 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-543 | K545 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-545 | K547 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-546 | K548 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-547 | K549 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-551 | K553 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-552 | K554 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-554 | K556 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
Log | DIN-555 | K557 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-556 | K558 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-558 | K560 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-559 | K561 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-560 | K562 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-562 | K564 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-567 | K569 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-568 | K570 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-569 | K571 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-570 | K572 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-571 | K573 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-573 | K575 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-574 | K576 | Ready for Internal Review | Closed | Entered Value Changed.
Log | DIN-575 | K577 | Open - awaiting assessment | Requires Industry Work Group review | Entered Value Changed.
Log | DIN-577 | K579 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-578 | K580 | Open - awaiting assessment | Closed | Entered Value Changed.
Log | DIN-579 | K581 | Open - awaiting assessment | Initial Assessment/Updating | Entered Value Changed.
Log | DIN-581 | K583 | Open - awaiting assessment | Ready for Internal Review | Entered Value Changed.
Log | DIN-582 | K584 | Open - awaiting assessment | Ready for Internal Review | Entered Value Changed.
Log | DIN-584 | K586 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-585 | K587 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-586 | K588 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-589 | K591 | Open - awaiting assessment | Initial Assessment/Updating | Entered Value Changed.
Log | DIN-597 | K599 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-601 | K603 | Open - awaiting assessment | Closed | Entered Value Changed.
Log | DIN-613 | K615 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-615 | K617 | Ready for Internal Review | Implemented | Entered Value Changed.
Log | DIN-617 | K619 | Open - awaiting assessment | Ready for Internal Review | Entered Value Changed.
Log | DIN-621 | K623 |  | Industry CP Required | Entered Value Added.
Log | DIN-622 | K624 |  | Initial Assessment/Updating | Entered Value Added.
Log | DIN-623 | K625 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-624 | K626 |  | Initial Assessment/Updating | Entered Value Added.
Log | DIN-625 | K627 |  | Initial Assessment/Updating | Entered Value Added.
Log | DIN-626 | K628 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-627 | K629 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-628 | K630 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-629 | K631 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-630 | K632 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-631 | K633 |  | Implemented | Entered Value Added.
Log | DIN-632 | K634 |  | Requires Industry Work Group review | Entered Value Added.
Log | DIN-633 | K635 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-207 | L209 | 8/4/2023 (04/08/2023 00:00:00) |  | Entered Value Deleted.
Log | DIN-253 | L255 |  | 9/13/2023 (13/09/2023 00:00:00) | Entered Value Added.
Log | DIN-610 | L612 | 8/31/2023 (31/08/2023 00:00:00) | 9/13/2023 (13/09/2023 00:00:00) | Entered Value Changed.
Log | DIN-56 | M58 | Interim Release 5 | Interim Release 6 | Entered Value Changed.
Log | DIN-278 | M280 | Interim Release 5 | Interim Release 6 | Entered Value Changed.
Log | DIN-310 | M312 | Interim Release 5 | Interim Release 6 | Entered Value Changed.
Log | DIN-317 | M319 | Interim Release 5 | Interim Release 7 | Entered Value Changed.
Log | DIN-446 | M448 | Interim Release 5 | Interim Release 6 | Entered Value Changed.
Log | DIN-494 | M496 | Interim Release 5 |  | Entered Value Deleted.
Log | DIN-557 | M559 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
Log | DIN-574 | M576 | Interim Release 4 |  | Entered Value Deleted.
Log | DIN-575 | M577 | Interim Release 5 | Interim Release 6 | Entered Value Changed.
Log | DIN-588 | M590 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
Log | DIN-619 | M621 | Interim Release 5 | Interim Release 6 | Entered Value Changed.
Log | DIN-621 | M623 |  | Interim Release 5 | Entered Value Added.
Log | DIN-622 | M624 |  | Interim Release 5 | Entered Value Added.
Log | DIN-623 | M625 |  | Interim Release 5 | Entered Value Added.
Log | DIN-624 | M626 |  | Interim Release 5 | Entered Value Added.
Log | DIN-625 | M627 |  | Interim Release 5 | Entered Value Added.
Log | DIN-626 | M628 |  | Interim Release 5 | Entered Value Added.
Log | DIN-627 | M629 |  | Interim Release 5 | Entered Value Added.
Log | DIN-628 | M630 |  | Interim Release 5 | Entered Value Added.
Log | DIN-629 | M631 |  | Interim Release 5 | Entered Value Added.
Log | DIN-630 | M632 |  | Interim Release 5 | Entered Value Added.
Log | DIN-631 | M633 |  | Interim Release 4 | Entered Value Added.
Log | DIN-632 | M634 |  | Interim Release 6 | Entered Value Added.
Log | DIN-633 | M635 |  | Interim Release 5 | Entered Value Added.
Log | DIN-158 | O160 | This DIN has been moved to Interim Release 5 as it is related to DIN-409 which has an objection raised that is pending a discussion to clarify the solution. Recommending a change to this ISD Data Item: Settlement Period Quality Indicator to be set as per Appendix 1 of MHHSP_METH007 MDS_Method_Statement v5.0 This data item need to be changed to something like ‘Valid Settlement Period Quality Indicator Set’ and the field size needs to be increased. The data catalugue will need the revised data item and the field length will need increasing from 20 to at least 100. This Item also appears in some interfaces that will need to be updated. This is because it represents a set of SPQIs. The initial intention is to populate as per the table and check if any new SPQIs have been introduced in the baseline design Method Statement that are not covered. If new CCCs are introduced the appropriate flags for each new CCC would need to be agreed. However, it is likely that another dimension to the table below would ne | This DIN has been moved to Interim Release 5 as it is related to DIN-409 which has an objection raised that is pending a discussion to clarify the solution. Name change and field length have been actioned. Reviewing whether any changes to Settlement reports are required Recommending a change to this ISD Data Item: Settlement Period Quality Indicator to be set as per Appendix 1 of MHHSP_METH007 MDS_Method_Statement v5.0 This data item need to be changed to something like ‘Valid Settlement Period Quality Indicator Set’ and the field size needs to be increased. The data catalugue will need the revised data item and the field length will need increasing from 20 to at least 100. This Item also appears in some interfaces that will need to be updated. This is because it represents a set of SPQIs. The initial intention is to populate as per the table and check if any new SPQIs have been introduced in the baseline design Method Statement that are not covered. If new CCCs are introduced the appropriate flags fo | Entered Value Changed.
Log | DIN-207 | O209 | At the DRG held on 4th August it was agreed that Appointments need to become active in UTC. DIN- was raised to update the relevant artefacts to reflect this decision. Old solution: Appointments become active at midnight local time. Participants raised objections against the old solution therefore this DIN went to a DRG on 4th Aug for discussion. | At the DRG held on 4th August it was agreed that Appointments need to become active in UTC. References to local time removed Old solution: Appointments become active at midnight local time. Participants raised objections against the old solution therefore this DIN went to a DRG on 4th Aug for discussion. | Entered Value Changed.
Log | DIN-246 | O248 | A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors) and receivers (suppliers) of the flows has identified the desired flow content and now wish to bring this back to the program to ensure that it can be delivered in readiness for migration. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the supercustomer data from settlement (REP-002/002A). There will be removal of certain data items used in the current process and addition of new data items, making population of the D0242 ‘Supercustomer DUoS Daily Statement’/D0315 ‘Embedded Network Supercustomer DUoS Daily Statement’ impossible in their current format for migrated customers. The “MHHS Design: Reporting and Transition Sub Group” identified the need for a new DIP flow to replace the D0242/D0315 last summer but noted that these flows are under DCUSA ownership and so passed the development of the flow content to DCUSA. More information | A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors) and receivers (suppliers) of the flows has identified the desired flow content and now wish to bring this back to the program to ensure that it can be delivered in readiness for migration. REP-900 and REP-901 added to reporting catalogue. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the supercustomer data from settlement (REP-002/002A). There will be removal of certain data items used in the current process and addition of new data items, making population of the D0242 ‘Supercustomer DUoS Daily Statement’/D0315 ‘Embedded Network Supercustomer DUoS Daily Statement’ impossible in their current format for migrated customers. The “MHHS Design: Reporting and Transition Sub Group” identified the need for a new DIP flow to replace the D0242/D0315 last summer but noted that these flows are under DCUSA ownership and so passed the developme | Entered Value Changed.
Log | DIN-264 | O266 | Further details of the solution are under discussion/review. | Method Statement will be updated for "W" to be replaced by "U". Please note: ISD entity M5 file has already been updates to reflect the fact that unmetered supplies have a connection type of "U". | Entered Value Changed.
Log | DIN-265 | O267 | The Freshdesk ticket details redlined changes have been made to the DES240 document. Further details of the solution are under discussion/review. | Interface document will be updated with the full list of settlement period qulity indicators. | Entered Value Changed.
Log | DIN-300 | O302 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. See DIN 506 which has updated DES138 to show that IF-014 also contains warnings for MPANs with consumption on de-energised sites. | Entered Value Changed.
Log | DIN-301 | O303 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. See DIN 506 which has updated DES138 to show that IF-014 also contains warnings for MPANs on de-energised sites. | Entered Value Changed.
Log | DIN-328 | O330 | ALL Updates between RS and CSS/DSP are existing interactions, covered by existig SLA's document in RECCO documentation. OPSC document was updated per Recco comment to highlight existing RECCO SLA in this area and to ensure primacy of the RECCO documented timings | RECCo confirmed closure of DIN following review of amendments to the Operational Choreography for CR018. ALL Updates between RS and CSS/DSP are existing interactions, covered by existig SLA's document in RECCO documentation. OPSC document was updated per Recco comment to highlight existing RECCO SLA in this area and to ensure primacy of the RECCO documented timings. | Entered Value Changed.
Log | DIN-336 | O338 |  | Requirements have been found in BRS001, BRS004, BRS005, BRS014. Models have the correct steps identified. Unable to identify whats missing, checking with the originator. | Entered Value Added.
Log | DIN-338 | O340 |  | BP003 from Step 255 relable "PUB-36" flow to Step 260 for the Supplier (prospective/incumbent) to state "PUB-036 for Import & Export Supplier" | Entered Value Added.
Log | DIN-339 | O341 | See 338 as well | See 338 as well, Assuming referring to IF031 not IF001, BP003 from step from step 030 new flow to Supplier (prospectice/incumbent) for PUB-031 for import & Export Supplier to new step ¦Receive Initial Appointment request | Entered Value Changed.
Log | DIN-340 | O342 |  | Updated the below test to Section D within MDS Method statement: 17.4 The I/F021 ‘UTC Settlement Period Consumption Data’ can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/F014 Rejected Consumption Data Submission and I/F ‘Notification of Defaulted UTC Settlement Period Consumption Data’ to any I/F021 data to ensure LDSO’s are not using rejected data or are missing I/F 021 data in respect of an MPAN. | Entered Value Added.
Log | DIN-342 | O344 |  | Updated full list of actuals with the MDS Method Statement. The amended list added to the Method statement: A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6. | Entered Value Added.
Log | DIN-412 | O414 |  | As the Migration documentation was approved via DAG and following discusion with RecCo and BSC the updates are being documented inThis is being picked up in an update to DES196 Dflow interface | Entered Value Added.
Log | DIN-414 | O416 | Update to DES196 required | Centrica have been notified on closure of DIN. Update was delivered in the published V1.0 of DES-196 as part of July DAG and the updated version is available on the Collaboration Base. | Entered Value Changed.
Log | DIN-451 | O453 | CR Contents incorporated into a new Section 7 of Ops Choreography Document. The redlining of the Ops Choreography document is still under review subject to approval. | Following feedback provided on the redlined version of the Operational Choreography, and following discussion on CR018 at PSG, the SRO maintained the DAG Chair’s decision to approve the implementation of CR018. CR Contents incorporated into a new Section 7 of Ops Choreography Document. Updates to clarify low level processing details in Section 7 Out-Of-Hours Processes table. Following feedback from DNO Review - Additional updates to replace the term ‘SLA’ with the phrase “target response time(s)”. Changes to Column headings to ‘When’ across the Operational Choreography document to align with Code Drafting convention. Addition of Intro text and removal of text “or Performance Regime” in Section 5. | Entered Value Changed.
Log | DIN-481 | O483 | Two new data type references have been created DT-024 and DT-024N. For NUM(16,6) data type within ECS reports/ECS data catalogue replace DT-023/DT-023N with DT-024/DT-024N. DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. | Two new data type references have been created DT-024 and DT-024N. For NUM(16,6) data type within ECS reports/ECS data catalogue replace DT-023/DT-023N with DT-024/DT-024N. DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. 31/08: A reconciliation exercise is being carried out internally of the ECS data catalogue to assess data types. Further work may be required to swagger following the reconciliation. | Entered Value Changed.
Log | DIN-485 | O487 | Design changes required to Swagger 1.4 to support updates to API endpoints for DELETE API verbs to ensure we are able to remove the correct StatusMessage or PublicationConfig for the appropriate recipient combination. The issue also affects some of the POST methods where a recipient ID is required, e.g webhook config. A standard pattern is proposed where a recipeint id is specified in the path. Updates will also be made to E2E001 design document to ensure the document provides any clarity required. | Design changes required to Swagger 1.4 to support updates to API endpoints for DELETE API verbs to ensure we are able to remove the correct StatusMessage or PublicationConfig for the appropriate recipient combination. The issue also affects some of the POST methods where a recipient ID is required, e.g webhook config. A standard pattern is proposed where a recipeint id is specified in the path. Updates to section 4.5.1 and 4.7 also made to E2E001 design document to ensure the document provides any clarity required. | Entered Value Changed.
Log | DIN-486 | O488 | Update the role codes in DES-138 for the From / To Parties for each of the Interfaces to align with other documents including E2E001. Update information in the Introductory section in DES-138 to aid understanding / clarity. | Update the role codes in DES-138 for the From / To Parties for each of the Interfaces to align with other documents including E2E001. No change to information in the Introductory section in DES-138 required. | Entered Value Changed.
Log | DIN-494 | O496 | Swagger 1.4 to be updated for DI-091 minimum is 5 and maximum is 6. Currently this is 1 and 1 respectively which is incorrect. DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. | This DIN is now superseded by DIN-615 following on from DIN-574. Text against Number of Register Digits field amended to say "per the manufacturer specification". Swagger validation of this field updated to match SCS logical test ie value can be 0-9. This DIN was to ensure there was consistency in Swagger 1.4 to align with DES-138 so that min and max was 5 and 6 respectievly. This objection is related to the values in DES-138, to update from 5 and 6 to 0 and 9, and then align Swagger to the values in DES-138. | Entered Value Changed.
Log | DIN-508 | O510 | New Data Items Created and added to IF-050 in block B079: DI-167 RMP Status Effective From Date DI-168 MP Status Effective from Date (DIN 318 Closed as duplicate) | New Data Items Created and added to IF-050 in block B079 and the data catalogue tab: DI-167 RMP Status Effective From Date DI-168 MP Status Effective from Date (DIN 318 Closed as duplicate) | Entered Value Changed.
Log | DIN-533 | O535 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-368. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-339. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Entered Value Changed.
Log | DIN-548 | O550 | Internal discussion required between Elexon, KS and MH to reword the requirements to reflect the baselined BAU requirements more closely. Session to be arranged once Transition requirements have been handed over to Elexon. | Internal discussion required between Elexon, KS and MH to reword the requirements to reflect the baselined BAU requirements more closely. Session to be arranged once Transition requirements have been handed over to Elexon. 31/08: A session has been arranged with Elexon/MH/ME on Tuesday 5/09 to discuss this DIN and the rewording for the the requirements. | Entered Value Changed.
Log | DIN-551 | O553 | DI-082 Minimum and Maximum column updated with 1 and 5 respectively in MHHS ECS data catalouge Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | DI-083 Minimum and Maximum column updated with 1 and 5 respectively in MHHS ECS data catalouge Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Entered Value Changed.
Log | DIN-554 | O556 | DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. Agreed changes with SCS, awaiting feedback from RECCO Linked to DIN-149. | DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. Process map emailed to particpants - added to BP010E and validation rules for IF-038 updated accordingly Agreed changes with SCS, awaiting feedback from RECCO | Entered Value Changed.
Log | DIN-556 | O558 | ADS Method Statement has been updated with "Reconciliation for smart Meter Advance Reconciliation" section. | ADS Method Statement has been updated with "Reconciliation for smart Meter Advance Reconciliation" section 2.21 - 2.25. | Entered Value Changed.
Log | DIN-559 | O561 | Added clarification to IF-036 to confirm that the Appointment Scenario Code used for Secondary MPANs will mirror that applied to the Primary MPAN (eg COS/CSP/Etc). In cases of Auto-Alignment of MPANs the Appointment Scenatio of (ALG - Auto Alignment of MPAN Service Providers) will be applied. ALG added as allowable value in DI-800 ( Data Catalogue and Swagger ) | Added clarification to IF-036 to confirm that the (DI-800) Appointment Scenario Code used for Secondary MPANs will mirror that applied to the Primary MPAN (eg COS/CSP/Etc). In cases of Auto-Alignment of MPANs the Appointment Scenatio of (ALG - Auto Alignment of MPAN Service Providers) will be applied. ALG added as allowable value in DI-800 ( Data Catalogue and Swagger ) | Entered Value Changed.
Log | DIN-563 | O565 |  | A response was provided to Ayo on 24/07 by design team. Follow up email has been sent for Ayo to confirm whether issue is resolved, thus closing the DIN or whether a call is required with Design team for further resolution.. | Entered Value Added.
Log | DIN-570 | O572 | Added validation to align with MDS/LSS method statements where estimated data is provided on a de-energised site (ECS1008 - SP End Date/Time [DI-082] contains non-actual consumption for ECS De-Energised MPAN) | IF-021 Added validation to align with MDS/LSS method statements where estimated data is provided on a de-energised site (ECS1008 - SP End Date/Time [DI-082] contains non-actual consumption for ECS De-Energised MPAN) | Entered Value Changed.
Log | DIN-572 | O574 |  | Further details of the solution are under discussion/review. | Entered Value Added.
Log | DIN-574 | O576 | Text updated as follows: "Where the Meter Type is S1 the Number of Displayed Register Digits value must be between 0 - 9" | DIN CLOSED as agreed with St Clements and RECCo. DIN-615 supercedes this DIN. The text has been updated as suggested below from RECCo, ‘Where the Meter Type is S1, the value should be populated as per the manufacturer specification.’ However, the logical test for SMETS1 in the DES-138 Interface Catalogue will remain unchanged. DIN-615 also includes updating the Swagger validation of this field to match SCS logical test i.e. value can be 0-9. | Entered Value Changed.
Log | DIN-575 | O577 |  | SCS to raise at DRG for initial feedback, ahead of raising formal CR | Entered Value Added.
Log | DIN-578 | O580 |  | THe Effective From date is not currently shared on the D0386 which was the basis for the IF-019/PUB-020. If EES requires an EFD suggest that the transaction date from the header is used. These updates can only be made by the current Supplier. | Entered Value Added.
Log | DIN-579 | O581 |  | BP011B from Step 542 new flow for PUB-043 to LDSO new step Manage Change of Connection type Notification | Entered Value Added.
Log | DIN-581 | O583 |  | Updated population notes for DI-090 to refer to Data Catalogue | Entered Value Added.
Log | DIN-582 | O584 |  | Updated SU-163, SU-164 and SU-165 to refer "for switched load tariff (eg. Economy 7/Economy 10) sites" rather than Economy 7/Economy 10 sites | Entered Value Added.
Log | DIN-584 | O586 | DI-511 Off Peak Declaration Proportion has been changed from String to Number so as to allow for improved Swagger validation of this data item. The new Number value will have a Minimum value = 0 and a Maximum Value = 100. | DI-511 Off Peak Declaration Proportion has been changed from String to Number so as to allow for improved Swagger validation of this data item. The new Number value will have a Minimum value = 0 and a Maximum Value = 100. (IF-024). Data Catalogue updated accordingly. | Entered Value Changed.
Log | DIN-586 | O588 | Updated DES138 D0 Common block so that YAML names in DES-138 now align with Swagger initialCorrelationID (DI-987), transactionTimestamp (DI-989), transactionID (DI-990) | Updated DES138 Data Catalogue D0 Common block data items so that YAML names in DES-138 now align with Swagger initialCorrelationID (DI-987), transactionTimestamp (DI-989), transactionID (DI-990) | Entered Value Changed.
Log | DIN-589 | O591 | Align the ADS method statement with the SDS method statement to resolve the discrepancy | We will align the ADS method statement with the SDS method statement to keep it uniform. | Entered Value Changed.
Log | DIN-590 | O592 |  | Update all the role codes referenced in DES-138 to ensure they are included in E2E001 and that there is a full explanation of what these are. | Entered Value Added.
Log | DIN-591 | O593 |  | Update MDS Method Statement Section 2.1 to read If SP End Date/Time [DI-082] > MDS Run Date (RF) as specified for the SP End Date/Time [DI-082] in the Master Settlement Table in ISD | Entered Value Added.
Log | DIN-592 | O594 |  | Align inconsistencies between StatusMessage / Standard Response body definitions for what is contained with E2E001 and Swagger. Provide clariry on how TransactionID is populated in Status Message for Level 2 validation and Level 4 validation | Entered Value Added.
Log | DIN-596 | O598 |  | Added validation rule to IF-031 to ensure appointments are made at midnight UTC. Added clarification on Regs Notes tab. | Entered Value Added.
Log | DIN-597 | O599 | IF-026 / B069 - SCS requested removal of wording "must be required for smart meter removed" as this is inherant as part of the Event Type. | IF-026 / B068 - SCS requested removal of wording "must be required for smart meter removed" as this is inherant as part of the Event Type. | Entered Value Changed.
Log | DIN-601 | O603 | This is deliberate. Sean has the details | M1 is used in IF-019 and IF-20. M0 is used in all other IFs where required. Swagger version 1.4 has been reviewed and correctly reflects this position. | Entered Value Changed.
Log | DIN-603 | O605 |  | Update Section 4.2.1 of E2E001 so that this shows A0 not being removed | Entered Value Added.
Log | DIN-604 | O606 |  | Update B066 block in IF-035 to conditional mandatory in DES-138 and Swagger 1.5 | Entered Value Added.
Log | DIN-606 | O608 | Waiting for OPS C document to be copied to R5 folder | Update OPS Choreography document to clarify processing of IF-035 | Entered Value Changed.
Log | DIN-611 | O613 |  | We will update section 9.3 to state that the report will be provided using IF-014. | Entered Value Added.
Log | DIN-612 | O614 | Added x2 new validtion rules to prevent the creation / addition of Related MPANs with a Connection Type of "U - Unmetered". No validation applied to remove so as to allow for the resolution of any historically erroneous links | Added x2 new validation rules to prevent the creation / addition of Related MPANs with a Connection Type of "U - Unmetered". No validation applied to remove so as to allow for the resolution of any historically erroneous links | Entered Value Changed.
Log | DIN-613 | O615 | In line with DAG Decision on 4th Aug - it was agreed that ALL Serive Provider Appointments should commence at Midnight UTC. Text against DI-086 and Di-121 has been removed. A new section addressing the treatment of Time will be added to the Additional Information tab of DES-138 as part of R5 (DIN-614) | In line with DRG Decision on 4th Aug - it was agreed that ALL Serive Provider Appointments should commence at Midnight UTC. Text against DI-086 and DI-121 has been removed. A new section addressing the treatment of Time will be added to the Additional Information tab of DES-138 as part of Interim Release 5 (DIN-614) | Entered Value Changed.
Log | DIN-614 | O616 |  | Added validation rule to IF-031 to ensure appointments are made at midnight UTC. Added clarification on Regs Notes tab. | Entered Value Added.
Log | DIN-615 | O617 | Clarification following on from DIN-574. Text against Number of Register Digits field ammended to say "per the manufacturer specification" . Note text for SCS validation will remain unchanged. | Clarification following on from DIN-574. Text against Number of Register Digits field amended in IF-002, IF-005, IF-006, IF-033, to say "per the manufacturer specification". Note text for SCS validation will remain unchanged. Swagger validation of this field updated to match SCS logical test ie value can be 0-9. | Entered Value Changed.
Log | DIN-616 | O618 |  | BP003C may need updating follow impact assessment | Entered Value Added.
Log | DIN-617 | O619 |  | Added interface notes to clarify Annual Consumption usage in IF-040 and Load Shape Totals in IF-023 | Entered Value Added.
Log | DIN-619 | O621 |  | Pending feedback from PDA on UMS process | Entered Value Added.
Log | DIN-621 | O623 |  | Passed to Matt McC to add to existing industry CP changes. | Entered Value Added.
Log | DIN-622 | O624 |  | Email sent to SCS. Design Team to share requirements with internal DIP Team | Entered Value Added.
Log | DIN-623 | O625 |  | Add SUPL (Linked Supplier) as an additional Primary Receipient of Inital Registration Event | Entered Value Added.
Log | DIN-624 | O626 |  | Updates to BPM013: 1. Removal of MHHS-REP-001 reference 2. Update reference of REP-005 to ELEX-REP-005 3. Reference of MHHS-REP-002A included with BP header 4. Reference of REP-002 changed to ELEX-REP-001 | Entered Value Added.
Log | DIN-625 | O627 |  | Consider breaking out DI-980 into an array in B092 block of IF-035. | Entered Value Added.
Log | DIN-626 | O628 |  | Routing of this flow should match that of the IF-037 - in that a copy should also be sent to the Supplier. IF-003 Routing table updated to show Supplier as being a receipient of the iF-003 | Entered Value Added.
Log | DIN-627 | O629 |  | Update Interface Doc "Correlation ID Required" to "Correlation ID Created" | Entered Value Added.
Log | DIN-628 | O630 |  | Add NEW validation to ensure that "UTC Settlement Date" has time of Midnight UTC. Added clarification to existing validation rule that time element of "Settlement period end date time" should align with Settlement period duration | Entered Value Added.
Log | DIN-629 | O631 |  | SUPC routing moved from Secondary to Primary for IF-037 for all events | Entered Value Added.
Log | DIN-630 | O632 |  | Arrow between steps 225 and steps 245 on BP002 removed. Previously added in error. | Entered Value Added.
Log | DIN-631 | O633 |  | loadShapeGSPGroup and loadShapeDomesticPremiseIndicator added to Required fields section to align with block definition. | Entered Value Added.
Log | DIN-632 | O634 |  | DRG to decide on exact content/structure of Header ... Is a footer required? If so what should it include (eg number of Entity entries) | Entered Value Added.
Log | DIN-633 | O635 |  | Update Entity 45 - Market Role code needs to allow Blanks in order to align with other tables in ISD and to provide for [new MHHS] Market Participants who dont have a legacy market participant role code | Entered Value Added.
Log | DIN-207 | P209 | Process Model correction | Data interface correction | Entered Value Changed.
Log | DIN-241 | P243 | Data interface correction |  | Entered Value Deleted.
Log | DIN-253 | P255 |  | Design Ambiguous | Entered Value Added.
Log | DIN-340 | P342 |  | Design Ambiguous | Entered Value Added.
Log | DIN-342 | P344 |  | Method statement correction | Entered Value Added.
Log | DIN-413 | P415 |  | Design Ambiguous | Entered Value Added.
Log | DIN-425 | P427 |  | Design Ambiguous | Entered Value Added.
Log | DIN-426 | P428 |  | Design Ambiguous | Entered Value Added.
Log | DIN-429 | P431 |  | Design Ambiguous | Entered Value Added.
Log | DIN-431 | P433 |  | Design Ambiguous | Entered Value Added.
Log | DIN-435 | P437 |  | Design Ambiguous | Entered Value Added.
Log | DIN-436 | P438 |  | Design Ambiguous | Entered Value Added.
Log | DIN-443 | P445 |  | Design Ambiguous | Entered Value Added.
Log | DIN-457 | P459 |  | Design Ambiguous | Entered Value Added.
Log | DIN-477 | P479 |  | Design Ambiguous | Entered Value Added.
Log | DIN-494 | P496 | Design Ambiguous | No Change | Entered Value Changed.
Log | DIN-509 | P511 |  | Clarification | Entered Value Added.
Log | DIN-548 | P550 |  | Design Ambiguous | Entered Value Added.
Log | DIN-572 | P574 |  | Clarification | Entered Value Added.
Log | DIN-574 | P576 | Design Ambiguous | No Change | Entered Value Changed.
Log | DIN-579 | P581 |  | Process Model correction | Entered Value Added.
Log | DIN-581 | P583 |  | Clarification | Entered Value Added.
Log | DIN-582 | P584 |  | Clarification | Entered Value Added.
Log | DIN-589 | P591 |  | Method statement correction | Entered Value Added.
Log | DIN-590 | P592 |  | Data interface correction | Entered Value Added.
Log | DIN-591 | P593 |  | Data interface correction | Entered Value Added.
Log | DIN-592 | P594 |  | Data interface correction | Entered Value Added.
Log | DIN-594 | P596 |  | Process Model correction | Entered Value Added.
Log | DIN-595 | P597 |  | Clarification | Entered Value Added.
Log | DIN-600 | P602 |  | Data interface correction | Entered Value Added.
Log | DIN-603 | P605 |  | Design Ambiguous | Entered Value Added.
Log | DIN-604 | P606 |  | Data interface correction | Entered Value Added.
Log | DIN-606 | P608 |  | Clarification | Entered Value Added.
Log | DIN-607 | P609 |  | Clarification | Entered Value Added.
Log | DIN-608 | P610 |  | Clarification | Entered Value Added.
Log | DIN-609 | P611 |  | Clarification | Entered Value Added.
Log | DIN-610 | P612 |  | Clarification | Entered Value Added.
Log | DIN-611 | P613 |  | Method statement correction | Entered Value Added.
Log | DIN-612 | P614 |  | Data interface correction | Entered Value Added.
Log | DIN-613 | P615 |  | Design Clarification | Entered Value Added.
Log | DIN-614 | P616 |  | Data interface correction | Entered Value Added.
Log | DIN-615 | P617 |  | Design Clarification | Entered Value Added.
Log | DIN-616 | P618 |  | Clarification | Entered Value Added.
Log | DIN-617 | P619 |  | Data interface correction | Entered Value Added.
Log | DIN-618 | P620 |  | Data interface correction | Entered Value Added.
Log | DIN-620 | P622 |  | Data interface correction | Entered Value Added.
Log | DIN-622 | P624 |  | Clarification | Entered Value Added.
Log | DIN-623 | P625 |  | Data interface correction | Entered Value Added.
Log | DIN-624 | P626 |  | Clarification | Entered Value Added.
Log | DIN-625 | P627 |  | Data interface correction | Entered Value Added.
Log | DIN-626 | P628 |  | Data interface correction | Entered Value Added.
Log | DIN-627 | P629 |  | Data interface correction | Entered Value Added.
Log | DIN-628 | P630 |  | Data interface correction | Entered Value Added.
Log | DIN-629 | P631 |  | Data interface correction | Entered Value Added.
Log | DIN-630 | P632 |  | Process Model correction | Entered Value Added.
Log | DIN-631 | P633 |  | Correction | Entered Value Added.
Log | DIN-633 | P635 |  | Clarification | Entered Value Added.
Log | DIN-207 | Q209 | Migration | Supporting Docs | Entered Value Changed.
Log | DIN-253 | Q255 |  | Supporting Docs | Entered Value Added.
Log | DIN-265 | Q267 |  | Supporting Docs | Entered Value Added.
Log | DIN-336 | Q338 |  | Supporting Docs | Entered Value Added.
Log | DIN-338 | Q340 |  | MPAN Ownership | Entered Value Added.
Log | DIN-339 | Q341 |  | MPAN Ownership | Entered Value Added.
Log | DIN-340 | Q342 |  | Supporting Docs | Entered Value Added.
Log | DIN-342 | Q344 |  | Supporting Docs | Entered Value Added.
Log | DIN-413 | Q415 |  | Supporting Docs | Entered Value Added.
Log | DIN-425 | Q427 |  | Supporting Docs | Entered Value Added.
Log | DIN-426 | Q428 |  | Supporting Docs | Entered Value Added.
Log | DIN-429 | Q431 |  | Supporting Docs | Entered Value Added.
Log | DIN-431 | Q433 |  | Supporting Docs | Entered Value Added.
Log | DIN-435 | Q437 |  | Supporting Docs | Entered Value Added.
Log | DIN-436 | Q438 |  | Supporting Docs | Entered Value Added.
Log | DIN-443 | Q445 |  | Supporting Docs | Entered Value Added.
Log | DIN-457 | Q459 |  | Supporting Docs | Entered Value Added.
Log | DIN-477 | Q479 |  | Supporting Docs | Entered Value Added.
Log | DIN-494 | Q496 | Supporting Docs |  | Entered Value Deleted.
Log | DIN-548 | Q550 |  | Supporting Docs | Entered Value Added.
Log | DIN-554 | Q556 |  | Supporting Docs | Entered Value Added.
Log | DIN-574 | Q576 | Supporting Docs |  | Entered Value Deleted.
Log | DIN-579 | Q581 |  | MPAN Ownership | Entered Value Added.
Log | DIN-581 | Q583 |  | Supporting Docs | Entered Value Added.
Log | DIN-582 | Q584 |  | Supporting Docs | Entered Value Added.
Log | DIN-589 | Q591 |  | Supporting Docs | Entered Value Added.
Log | DIN-590 | Q592 |  | Supporting Docs | Entered Value Added.
Log | DIN-591 | Q593 |  | Supporting Docs | Entered Value Added.
Log | DIN-592 | Q594 |  | Supporting Docs | Entered Value Added.
Log | DIN-594 | Q596 |  | MPAN Ownership | Entered Value Added.
Log | DIN-595 | Q597 |  | Supporting Docs | Entered Value Added.
Log | DIN-600 | Q602 | Minor | Supporting Docs | Entered Value Changed.
Log | DIN-603 | Q605 |  | Supporting Docs | Entered Value Added.
Log | DIN-604 | Q606 |  | Supporting Docs | Entered Value Added.
Log | DIN-606 | Q608 |  | Supporting Docs | Entered Value Added.
Log | DIN-608 | Q610 |  | Minor | Entered Value Added.
Log | DIN-611 | Q613 |  | Supporting Docs | Entered Value Added.
Log | DIN-612 | Q614 |  | Supporting Docs | Entered Value Added.
Log | DIN-613 | Q615 |  | Minor | Entered Value Added.
Log | DIN-614 | Q616 |  | Supporting Docs | Entered Value Added.
Log | DIN-615 | Q617 |  | Minor | Entered Value Added.
Log | DIN-617 | Q619 |  | Supporting Docs | Entered Value Added.
Log | DIN-618 | Q620 |  | Supporting Docs | Entered Value Added.
Log | DIN-620 | Q622 |  | Supporting Docs | Entered Value Added.
Log | DIN-623 | Q625 |  | Supporting Docs | Entered Value Added.
Log | DIN-624 | Q626 |  | Supporting Docs | Entered Value Added.
Log | DIN-625 | Q627 |  | Supporting Docs | Entered Value Added.
Log | DIN-626 | Q628 |  | Supporting Docs | Entered Value Added.
Log | DIN-627 | Q629 |  | Supporting Docs | Entered Value Added.
Log | DIN-628 | Q630 |  | Supporting Docs | Entered Value Added.
Log | DIN-629 | Q631 |  | Supporting Docs | Entered Value Added.
Log | DIN-630 | Q632 |  | Minor | Entered Value Added.
Log | DIN-631 | Q633 |  | Minor | Entered Value Added.
Log | DIN-633 | Q635 |  | Supporting Docs | Entered Value Added.
Log | DIN-207 | R209 | Migration | Interface Catalogue | Entered Value Changed.
Log | DIN-253 | R255 |  | E2E Architecture Document | Entered Value Added.
Log | DIN-265 | R267 |  | Interface Catalogue | Entered Value Added.
Log | DIN-336 | R338 |  | Supporting Docs | Entered Value Added.
Log | DIN-338 | R340 |  | Process Models | Entered Value Added.
Log | DIN-339 | R341 |  | Process Models | Entered Value Added.
Log | DIN-340 | R342 |  | Method Statement | Entered Value Added.
Log | DIN-342 | R344 |  | Method Statement | Entered Value Added.
Log | DIN-413 | R415 |  | Interfaces | Entered Value Added.
Log | DIN-425 | R427 |  | Interfaces | Entered Value Added.
Log | DIN-426 | R428 |  | Interfaces | Entered Value Added.
Log | DIN-429 | R431 |  | Interfaces | Entered Value Added.
Log | DIN-431 | R433 |  | Interfaces | Entered Value Added.
Log | DIN-435 | R437 |  | Interfaces | Entered Value Added.
Log | DIN-436 | R438 |  | Interfaces | Entered Value Added.
Log | DIN-443 | R445 |  | Interfaces | Entered Value Added.
Log | DIN-451 | R453 | Operation Choreography | Operational Choreography | Entered Value Changed.
Log | DIN-457 | R459 |  | Interfaces | Entered Value Added.
Log | DIN-477 | R479 |  | Interfaces | Entered Value Added.
Log | DIN-482 | R484 |  | Interface Catalogue | Entered Value Added.
Log | DIN-486 | R488 | DES-138, E2E001 | Interface Catalogue | Entered Value Changed.
Log | DIN-494 | R496 | Swagger |  | Entered Value Deleted.
Log | DIN-548 | R550 |  | ISD Document | Entered Value Added.
Log | DIN-554 | R556 |  | Supporting Docs | Entered Value Added.
Log | DIN-574 | R576 | Interface Catalogue |  | Entered Value Deleted.
Log | DIN-579 | R581 |  | Supporting Document | Entered Value Added.
Log | DIN-581 | R583 |  | Interfaces | Entered Value Added.
Log | DIN-582 | R584 |  | Interfaces | Entered Value Added.
Log | DIN-587 | R589 |  | Interfaces | Entered Value Added.
Log | DIN-589 | R591 |  | Method Statement | Entered Value Added.
Log | DIN-590 | R592 |  | Interface Catalogue | Entered Value Added.
Log | DIN-591 | R593 |  | Supporting Docs | Entered Value Added.
Log | DIN-592 | R594 |  | Interface Catalogue | Entered Value Added.
Log | DIN-594 | R596 |  | Supporting Document | Entered Value Added.
Log | DIN-595 | R597 |  | Interfaces | Entered Value Added.
Log | DIN-597 | R599 | Interfaces | Interface Catalogue | Entered Value Changed.
Log | DIN-600 | R602 | Interfaces | Interface Catalogue | Entered Value Changed.
Log | DIN-603 | R605 |  | E2E Architecture Document Swagger 1.4 | Entered Value Added.
Log | DIN-604 | R606 |  | Interfaces | Entered Value Added.
Log | DIN-606 | R608 |  | Supporting Document | Entered Value Added.
Log | DIN-608 | R610 |  | Interfaces | Entered Value Added.
Log | DIN-611 | R613 |  | Method Statement | Entered Value Added.
Log | DIN-612 | R614 |  | Interface Catalogue | Entered Value Added.
Log | DIN-613 | R615 |  | Interface Catalogue | Entered Value Added.
Log | DIN-614 | R616 |  | Interface Catalogue | Entered Value Added.
Log | DIN-615 | R617 |  | Interface Catalogue | Entered Value Added.
Log | DIN-617 | R619 |  | Interface Catalogue | Entered Value Added.
Log | DIN-618 | R620 |  | Interface Catalogue | Entered Value Added.
Log | DIN-620 | R622 |  | Interface Catalogue | Entered Value Added.
Log | DIN-623 | R625 |  | Interface Catalogue | Entered Value Added.
Log | DIN-624 | R626 |  | Reporting Catalogue | Entered Value Added.
Log | DIN-625 | R627 |  | Interface Catalogue | Entered Value Added.
Log | DIN-626 | R628 |  | Interface Catalogue | Entered Value Added.
Log | DIN-627 | R629 |  | Interface Catalogue | Entered Value Added.
Log | DIN-628 | R630 |  | Interface Catalogue | Entered Value Added.
Log | DIN-629 | R631 |  | Interface Catalogue | Entered Value Added.
Log | DIN-630 | R632 |  | Interfaces | Entered Value Added.
Log | DIN-633 | R635 |  | Supporting Document | Entered Value Added.
Log | DIN-207 | S209 | BP001 & BPD001 BP002 & BPD002 BP003 & BPD003 Migration Design | MHHSP-DES138-Interface Catalogue | Entered Value Changed.
Log | DIN-253 | S255 |  | E2E001 E2E Architecture Document | Entered Value Added.
Log | DIN-265 | S267 |  | MHHSP-DES138-Interface Catalogue | Entered Value Added.
Log | DIN-298 | S300 | UMSDS Method Statement | METH004_UMSDS Method Statement | Entered Value Changed.
Log | DIN-300 | S302 | UMSDS Method Statement DES138 | METH004_UMSDS Method Statement | Entered Value Changed.
Log | DIN-301 | S303 | UMSDS Method Statement DES138 | METH004_UMSDS Method Statement | Entered Value Changed.
Log | DIN-302 | S304 | UMSDS Method Statement | METH004_UMSDS Method Statement | Entered Value Changed.
Log | DIN-336 | S338 |  | BRS001, BRS004, BRS005, BRS014 | Entered Value Added.
Log | DIN-338 | S340 |  | BP003 | Entered Value Added.
Log | DIN-339 | S341 |  | BP003 | Entered Value Added.
Log | DIN-340 | S342 |  | MDS Method Statement | Entered Value Added.
Log | DIN-342 | S344 |  | MDS Method Statement | Entered Value Added.
Log | DIN-358 | S360 | Annual Consumption Meth 10 | METH010_Annual_Consumption | Entered Value Changed.
Log | DIN-359 | S361 | Annual Consumption Meth 10 | METH010_Annual_Consumption | Entered Value Changed.
Log | DIN-360 | S362 | Annual Consumption Meth 10 | METH010_Annual_Consumption | Entered Value Changed.
Log | DIN-361 | S363 | Annual Consumption Meth 10 | METH010_Annual_Consumption | Entered Value Changed.
Log | DIN-413 | S415 |  | DES196 D-Flow and interface mapping | Entered Value Added.
Log | DIN-425 | S427 |  | DES196 D-Flow and interface mapping | Entered Value Added.
Log | DIN-426 | S428 |  | DES196 D-Flow and interface mapping | Entered Value Added.
Log | DIN-429 | S431 |  | DES196 D-Flow and interface mapping | Entered Value Added.
Log | DIN-431 | S433 |  | DES196 D-Flow and interface mapping | Entered Value Added.
Log | DIN-435 | S437 |  | DES196 D-Flow and interface mapping | Entered Value Added.
Log | DIN-436 | S438 |  | DES196 D-Flow and interface mapping | Entered Value Added.
Log | DIN-441 | S443 | Annual Consumption Meth 10 | METH010_Annual_Consumption | Entered Value Changed.
Log | DIN-443 | S445 |  | DES196 D-Flow and interface mapping | Entered Value Added.
Log | DIN-457 | S459 |  | DES196 D-Flow and interface mapping | Entered Value Added.
Log | DIN-477 | S479 |  | Swagger 1.5 | Entered Value Added.
Log | DIN-486 | S488 | DES-138, E2E001 | DES138-InterfaceCatalogue | Entered Value Changed.
Log | DIN-494 | S496 | Swagger 1.4 |  | Entered Value Deleted.
Log | DIN-503 | S505 | DES-138, E2E001 and Swagger 1.4 | DES-138-interface catalogue, E2E001 E2E Architecture document and Swagger 1.4 | Entered Value Changed.
Log | DIN-548 | S550 |  | ISD Document EDI-021 | Entered Value Added.
Log | DIN-554 | S556 |  | BP10 Registration Updates DES138 - Interface Catalogue | Entered Value Added.
Log | DIN-556 | S558 | ADS Validation METH002 | METH002 ADS Validation Estimation | Entered Value Changed.
Log | DIN-560 | S562 | DES138-InterfaceCatalogue BRS-002 Metering Service Requirements | BRS-002 Metering Service Requirements | Entered Value Changed.
Log | DIN-571 | S573 | Interface Catalogue Swagger 1.4 | Swagger 1.4 | Entered Value Changed.
Log | DIN-574 | S576 | DES138-InterfaceCatalogue |  | Entered Value Deleted.
Log | DIN-579 | S581 |  | BP011B | Entered Value Added.
Log | DIN-581 | S583 |  | DES-138 Interface Spec | Entered Value Added.
Log | DIN-582 | S584 |  | DES-138 Interface Spec | Entered Value Added.
Log | DIN-584 | S586 | DES-138 Interface Catalouge | DES-138 Interface Catalogue | Entered Value Changed.
Log | DIN-585 | S587 | DES-138 Interface Catalouge | DES-138 Interface Catalogue | Entered Value Changed.
Log | DIN-586 | S588 | DES-138 Interface Catalouge | DES-138 Interface Catalogue | Entered Value Changed.
Log | DIN-589 | S591 |  | ADS Method Statement SDS Method Statement | Entered Value Added.
Log | DIN-590 | S592 | E2E001 MHHSP_EDI021_ISD_Entities | MHHSP-DES138-Interface Catalogue | Entered Value Changed.
Log | DIN-592 | S594 |  | E2E001 MHHSP-DES138-Interface Catalogue | Entered Value Added.
Log | DIN-600 | S602 | DES-138 Interface Doc | MHHSP-DES138-Interface Catalogue | Entered Value Changed.
Log | DIN-603 | S605 |  | E2E001 E2E Architecture Document Swagger 1.4 | Entered Value Added.
Log | DIN-604 | S606 |  | Swagger 1.5 MHHSP-DES138-Interface Catalogue | Entered Value Added.
Log | DIN-606 | S608 |  | OPS Choreography | Entered Value Added.
Log | DIN-608 | S610 |  | BP003 | Entered Value Added.
Log | DIN-611 | S613 |  | MDS Method Statement | Entered Value Added.
Log | DIN-612 | S614 |  | MHHSP-DES138-Interface Catalogue | Entered Value Added.
Log | DIN-613 | S615 |  | DES-138 Interface Catalogue | Entered Value Added.
Log | DIN-614 | S616 |  | MHHSP-DES138-Interface Catalogue | Entered Value Added.
Log | DIN-615 | S617 |  | DES-138 Interface Catalogue | Entered Value Added.
Log | DIN-617 | S619 |  | MHHSP-DES138-Interface Catalogue | Entered Value Added.
Log | DIN-618 | S620 |  | MHHSP-DES138-Interface Catalogue | Entered Value Added.
Log | DIN-620 | S622 |  | MHHSP-DES138-Interface Catalogue | Entered Value Added.
Log | DIN-623 | S625 |  | MHHSP-DES138-Interface Catalogue | Entered Value Added.
Log | DIN-624 | S626 |  | BPM013 | Entered Value Added.
Log | DIN-625 | S627 |  | MHHSP-DES138-Interface Catalogue | Entered Value Added.
Log | DIN-626 | S628 |  | MHHSP-DES138-Interface Catalogue | Entered Value Added.
Log | DIN-627 | S629 |  | MHHSP-DES138-Interface Catalogue | Entered Value Added.
Log | DIN-628 | S630 |  | MHHSP-DES138-Interface Catalogue | Entered Value Added.
Log | DIN-629 | S631 |  | MHHSP-DES138-Interface Catalogue | Entered Value Added.
Log | DIN-630 | S632 |  | BP002 | Entered Value Added.
Log | DIN-631 | S633 |  | DES-138 Interface Cat | Entered Value Added.
Log | DIN-633 | S635 |  | ISD Entity | Entered Value Added.

## Backup 150923 (hidden)
DIN ITEM DETAILS | [10 empty] | Scheduling |  |  | DIN IMPACT ASSESSMENT |  |  |  |  | DIN OUTCOME
Reference | Created BY | other Reference(s) | Date Raised | Organisation | Freshdesk Ticket # | Contact Name | Constituency | Title | Design Issue Notification Details (as notified by participant) | Current Status | Target working Group Date (If Required) | Target Release | Objection Cut-off Date | Design Issue Proposed solution | Justification/Type of Change | Design Area | Design Area - L2 | Artefact(s) Impacted | DAG Review Date | DAG Outcome | Reason for Rejection/Accept caveats | Design Change Reference Number | Internal Freeze Date
MHHS-DIN-1 |  | T4-COM-1744 | 2023-01-30 | St Clements | 2655 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1744 on 15th Sept 2022 MPRS does not currently restrict IHD Installs to Smart Meters, there maybe cases where there is an IHD present but the Meter is Trad (Not compatible with DCC and Customer Switched) Either Allow IHD on all Market Segments OR Cleansing to ensure IHDs are only present on S2 and S1 Meters SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses, as this is still not resolved | Implemented |  | Interim Release 1 |  | Discussed with SCS and agreed to add new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) Added requirements into BRS003. SCS to raise a potential data cleanse. | Requirement correction | MPAN Ownership | SCS Validation | MHHSP-BRS003-Registration Requirements | 2023-03-23
MHHS-DIN-2 |  | T4-COM-1745 | 2023-01-30 | St Clements | 2657 | Madison Layton | Software Provider |  | Orginally raised as T4-COM-1745 on 15th Sept 2022 DB002 is not the interface on which MPRS will be informed of a change to import/export relationship, it is DB05. The wrong diagram was updated, the EDI was updated to DB05 not import/export. SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses and artefact updates, to inform the wrong data item diagram was updated. However the diagram for EDI updates is still incorrectly reading DB005 update instead of DB02 | Closed |  |  |  | This appears to have been missed in v4.6 - the arrow on BP-010B from step435 to Step 440 shows DB005 (not DB05, assume that’s a minor typo in the comment) - and this is the Energy Direction Information (EDI) which is wrong. It has cbeen onfirmed that this was updated in v4.7 to go into v5.0 baseline. | No Change |  |  | None
MHHS-DIN-3 |  | T4-COM-1752 | 2023-01-30 | St Clements | 2661 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1752 on 15th Sept 2022: MHHS-BR-RS-020: "Retro" (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier ) In the D0205 the Supplier can cancel out the current Agent Appointment by setting the EFD to equal the currently stored Appointment EFD. Is this no longer allowed? All Services must be appointed for at least one day valid or not? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: removing the ability for Suppliers to Correct Invalid Service Appointments may not be understood by suppliers. We want to avoid a later Design CR to add this functionality in. SCS has not had a response, feel this is important discuss with Suppliers to avoid later CRs | Closed |  |  |  | The appointment can be resubmitted if it hasn’t been accepted yet. Once accepted, there is a need to maintain contiguous appointment periods. The scenario mentioned is the CoA not linked to a switch, so the acceptance of a new appointment from a particular EFD will ‘lock in’ that date and the previous MS/DS will be de-appointed at midnight on the previous day. This is to ensure that there are no periods left without MS and/or DS in place, which can happen today with D0155/D0151 sequencing issues. As an overall comment, there is not a concept of cancellation of appointments. The only way to alter the appointment is to get a new IF-031 issued. The only way to do this for the scenario presented, would be to issue an IF-031 for the old MS for the original date and an IF-031 for the new MS for the revised date. Requirement MHHS-BR-RS-021 ensures that Registration Service will action the latest received appointment where there are duplicate appointments for the same day. St Clements had requested that we build in a rule saying that you cannot submit a Change of Service Provider (CSP) request for the same Service Provider. It is a bit of a work-around, but we believe sending it as SEG should work, or alternatively a CR would be required to re-look at the interface validation. Closing, as this doesn't require further action - point noted. We have already spoken to a number of suppliers, and will continue to engage to ensure the functionality of the baselined design is understood and any issues picked up as early as possible. Documentation for LDSOs to point at. Pick up in Code Drafting as well. | No Change |  |  | None
MHHS-DIN-4 |  | T4-COM-1755 | 2023-01-30 | St Clements | 2666 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1755 on 15th Sept 2022: MHHS-BR-RS-071.2 REC CP R062 has been raised to remove the restriction on the number of EDI changes. Will this cause any downstream MHHS issues? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Needs to be aligned with REC Change No responses | Closed |  |  |  | As per original SRO response, the impacts of the REC change need to be dealt with through the REC change process and impact assessment. | No Change |  |  | None
MHHS-DIN-5 |  | T4-COM-1760 | 2023-01-30 | St Clements | 2667 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1760 on 15th Sept 2022: There are no Registration Service Reports defined in MHHSP-ERI011A. Will there be a requirement for MPRS to produce any Industry Reports for MHHS? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Design for the complete solution must be defined by M5. This is a DBT Design Start Blocker No responses This could significantly increase DBT time as development of reports can be costly and time consuming | Closed |  |  |  | Who is raising these requirements? What happens today? Possibly CC issues Agreed with SCS that reporting requirements will be introduced via the CR process. Reporting requirements are to be added to the programme RAID log | No Change |  |  | None
MHHS-DIN-6 |  | T4-COM-1761 DI-7 | 2023-01-30 | St Clements | 2668 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1761 on 15th Sept 2022: IF-005, REG1014 First MAP Block, MAP Eff From Date [DI-054] in message, must = MPAN Install date OR >= Eff Form date of all existing MAP Effective From Dates held in Registration prior to first [DI-054] in message I understand that the First MAP must equal the Install Date, I am unsure what the second condition is trying to say? You can not have a Meter Without a MAP. (ignoring customer owned meters where CUST is used) SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: response is incorrect. The Second Rule "Each subsequent MAP Effective From Date [DI-054] must be > MAP Eff From Date in previous block" covers the subsequent overlapping MAPs. The second half of this First Block Rule must be removed. The First Block can only ever equal the install date No responses, the rule has not been amended | Implemented |  | Interim Release 1 |  | This appears valid - the first MAP block can only start at the creation date (assuming the MAP blocks are in chronological order, which they must be if each subsequent map block has an EFD > the last) Currently the design allows 2 ways to amend the MAP History as outlined in Sections 13 and 14 of the IF005 Use Case Guide. Either the Metering Service can provide the full MAP history from the installation date or they can add a new MAP to the existing history, provided it is the next MAP in chronological order. So for example if you have MAPs 1,2 and 3, then you can extend to MAPs 1,2, 3 and 4 using the approach set out in section 14 to extend the MAP history. However if you wanted to set MAP 4 between 2 and 3, you would need to send the whole MAP history from the install date and provide 1,2,4 and 3 as set out in Section 13 to replace MAP history. The second validation rule is required if you are using the extend the MAP history functionality. Added note to REG Notes that where a MAP history is provided it must be in chronological order Added new REG1014 Validation Rule to MeterInstall and MeterExchange events to ensure only 1 MAP block is provided | Data interface correction | MPAN Ownership | SCS Validation | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-7 |  | DI-8, DI-11, DI-12, DI-14 | 2023-01-30 | St Clements | 2669 | Madison Layton | Software Provider |  | MPRS will reject any PUB-031 inlcuding those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8) | Implemented |  | Interim Release 1 |  | See Comments Revised CSS Registration Request ID validation on IF-031, 034 and 025 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | IF General | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-8 |  | N/A | 2023-02-01 | Elexon | 2642 | Sedef Kiris | Central Body |  | We have had the following comment ........... Also just found out that “Metering Service Id” have “MPID” in brackets afterwards, and not “MSID”. We believe it should be MSID | Closed |  |  |  | MPID is the correct term here, it is the metering service MPID. MHHSP_EDI012_ISD_Entities v4.6 Section M8 | No Change |  |  | None
MHHS-DIN-9 |  | N/A | 2023-01-30 | St Clements | 2672 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: [UpdateSiteTechnicalInfoMS] is not included in the interface catalogue and is not utilised by MPRS. Assume this is related to Issue 99 and needs removing? (raised as DI ID 9) | Implemented |  | Interim Release 1 |  | Removed from IF-005 Guide Section 4.1 | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-10 |  | N/A | 2023-01-30 | St Clements | 2799/2670 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: Is the currently appointed Meter Service informed of Prospective MS changes? Changes to MTDs can be made by prospective MS (e.g. change meter type to complete SEG market change before the MS can be appointed). As the MS is only prospective at this point the MS may still be lapsed and not take effect. However any MTD updates made would remain within the MPRS system and not be backed out. The current MS would therefore need to be aware of what changes have been made by the prospective MS. (raised as DI ID 10) | Closed |  |  |  | BP009 only talks about the Metering Service, not the current or prospective Metering Service, and it appears only the registration service receive metering service MTD details, not the current MS. Refer to SRO - what is the assumption here, as the alternative route is for registration to update the current MS The design is based on PUB-006, with the Updated Meter details, being sent to the current Metering Service ( BP011A step 280 ) as well as the Prospective Metering Service (Step 275). It is built into the routing rules in PUB-006. | No Change |  |  | None
MHHS-DIN-11 |  | N/A | 2023-01-30 | St Clements | 2675 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install / Remove Date(s) takes place within the Metering Services period of ownership (or proposed period of ownership for in the case of a prospective SEG appointment) " Sent on 11th Jan: Does not match business rules, as future dated installs are not allowed: "REG1020 - Meter Install Date [DI-057] cannot take place in the future. The proposed MS on a seg will have a future dated EFD, so they only have the +2 day lapse extension period for meter installs (raised as DI ID 11) | Implemented |  | Interim Release 1 |  | Added change of segment scenario's to IF005 USE CASE Guide. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 |  | Refer back to SCS as additional comentary needed on the issue and bring to next meeting
MHHS-DIN-12 |  | N/A | 2023-01-30 | St Clements | 2679 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install /Remove Date(s), cannot have taken place in the future" Sent on 11th Jan: It would be useful to have the Change of Segment process covered in this guide. We are not sure how the Prospective MS can exchange meters when their appointment period is in the future (raised as DI ID 12) | Implemented |  | Interim Release 1 |  | Nomenclature issue - requires a reword of this statement to conform to the business rules. Recommend the following update to section 3.2 of the IF005 Use Case Guide to confirm who can make Metering updates Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed BAU metering updates ( For the avoidance of doubt not meter update/meter history updates), it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. The one exception, is during a change of segment, when the incoming Metering Service is able to provide a BAU metering update, where it’s prospective “SEG” appointment is due to become active on the same day. SEG scenario's added to IF005 Use case guide Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-13 |  | N/A | 2023-01-30 | St Clements | 2683 | Madison Layton | Software Provider |  | Comment on Section 5.1 "validation allows for meter removal at a point following Disconnection if required)" Sent on 11th Jan: This rule prevents this REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational (raised as DI ID 13) | Implemented |  | Interim Release 1 |  | This statement doesn't appear to be a convention. There is no mention of this in E2E001 End to End Solution Architecture. Believe this statement needs to be amended or removed. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. IF-005 validation Rule changed to include meter removal at status Disconnected | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES138-Interface Catalogue, E2E001 End to End Solution Architecture
MHHS-DIN-14 |  | N/A | 2023-01-30 | St Clements | 2684 | Madison Layton | Software Provider |  | Comment on Section 3.2 "Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed metering updates, it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. " Statement is misleading- the 10 day period is only permitted for install, remove and exchange events, it is not listed for meterUpdate/meterHistoryUpdate in interface catalogue Also the prospective MS should be able to make changes for SEG to enable a market segment change to complete (raised as DI ID 14) | Implemented |  | Interim Release 1 |  | Validation rule(s) updated to constrain 10 day window to non-update events. Test in 3.2 reworded to remove ambiguity. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Refer back to SCS for additional clarity on the requirement and include RecCo and bring to next meeting
MHHS-DIN-15 |  | N/A | 2023-01-30 | St Clements | 2685 | Madison Layton | Software Provider |  | Comment raised in guide, sent on 11th Jan, that the JSON examples use MPID when it should use DIP ID e.g."distributorID": "SWAL" (raised as DI ID 15) | Implemented |  | Interim Release 1 |  | Corrected to use Dist DIP ID | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-16 |  | N/A | 2023-01-30 | St Clements | 2686 | Madison Layton | Software Provider |  | Comment on Section 9 " Albeit that these transactions can be ‘clubbed together’ and send as a group in single overarching message/API transaction. " Sent on 11th Jan: As DIP does not protect the sequencing of events (FIFO), is there a risk that the ordering of these updates might arrive out of sequence resulting in the wrong end state? If MS space out their updates it would reduce this risk (raised as DI ID 16) | Implemented |  | Interim Release 1 |  | Clairifcation added to Sec 9.2 to reference Time-Stamps rather than 'clubbing' | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-17 |  | DI-017 | 2023-01-30 | St Clements | 2690 | Madison Layton | Software Provider | MAP History availability to Metering Service | Section 9 says "a supporting MAP history commencing in line with the revised Installation Date must also be provided" Will the MS know the full MAP history? Risk they could destroy the data. Potential MAP billing issues? | Implemented |  | Interim Release 3 | 2023-07-12 | Solution agreed at DRG on what MAP updates are required. Various document updates required to align with DRG decision to only maintain latest MAP. Removed section 13 from IF005 user guide plus other corrections to doc. Updated DES138 IF005 validation rules. | Missing/incorrect validation rule | Supporting Docs | Various Documents | IF-005 Use Case guide MHHSP-DES138-Interface Catalogue |  |  |  |  | 14//7
MHHS-DIN-18 |  | N/A | 2023-01-30 | St Clements | 2691 | Madison Layton | Software Provider |  | Comment on Section 9 "• When maintaining the MAP History in cases where there is no change in Meter Installation Date then the MAP history provided should commence either with a MAP Effective From Date matching the existing install date of the meter OR be greater than the most recent, already existing, MAP Effective From Date" Sent on 11th Jan: So it's possible to update ALL MAP history back to installation, or add a new MAP, but it's not possible to amend MAP history only part way back (have to go back to installation date instead every time to do this) (raised as DI ID 18) | Closed |  |  |  | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • To update BRS003, requirement MHHS-BR-RS-027 to add “Registration Service must lapse any appointments that fail this validation” • Remove Rejected from Step 225 of BP002/BPD002 • Remove Rejected from label on line after step 215 of BP003. | No Change |  |  | None
MHHS-DIN-19 |  | N/A | 2023-01-30 | St Clements | 2692 | Madison Layton | Software Provider |  | Comment on Section 10 "E2E Architecture convention states that all data items are provided in each message even where these data items are not changing or are null" Sent on 11th Jan: Some of the items are optional not mandatory which conflicts with this statement. Not all data items need to be provided (raised as DI ID 19) | Implemented |  | Interim Release 1 |  | Update of E2E Doc to allow for Nullable values. | Data interface correction | Meter to Bank |  | MHHSP-E2E001 End-to-End Solution Architecture | 2023-02-23 |  | Defer as a E2E clarification may be needed
MHHS-DIN-20 |  | N/A | 2023-01-30 | St Clements | 2693 | Madison Layton | Software Provider |  | Comment on Section 13, sent on 11th Jan: What should MPRS do if it holds a MAP not included in the MAPHistory block? (raised as DI ID 20) | Implemented |  | Interim Release 1 |  | Update "all existing history will be replaced by that contained within the message" | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-21 |  | N/A | 2023-01-30 | St Clements | 2699 | Madison Layton | Software Provider |  | Comment on Section 15.2 "It is understood that currently there a numerous instances of duplicated Meter ID’s, some of which may have overlapping installation dates. " Sent on Jan 11th: Meter id is only unique at mpan. Should not be any instances of conflicted MSNs at MPAN. Can you verify with ECOES? Or we can do a RFI to DNOs but will take time (raised as DI ID 21) | Implemented |  | Interim Release 1 |  | All references to duplicated MSN IDs has been removed from the document | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-22 |  | N/A | 2023-01-30 | St Clements | 2700 | Madison Layton | Software Provider |  | Comment on Seciton 15.3 "add some kind of suffix (X1, X2) to the existing Meter ID." Sent on Jan 11th: This can take the meter ID over the allowable string length (string 10), in this example it would take it to string(12) and so would be rejected (raised as DI ID 22) | Implemented |  | Interim Release 1 |  | As above, Section 15.3 removed from IF-005 User Guide. | Data interface correction | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-23 |  | N/A | 2023-01-30 | St Clements | 2701 | Madison Layton | Software Provider |  | Comment on Section 16.3 Sent on Jan 11th: Cancelled Flag Set. Only a logical deletion. Still held in MPRS but not visible to EES/MEM The section implies the record would be fully deleted from MPRS, however this is not correct, MPRS would set a cancellation flag that would indicate the record has effectively been cancelled/logically deleted. It would however remain in the systems database (raised as DI ID 23) | Implemented |  | Interim Release 1 |  | Added a statement at the end of the table in 16.3 to say "NB the registration service will only logically delete the MAP entry with a flag, it will not be deleted from the database." | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Accepted
MHHS-DIN-24 |  | N/A | 2023-01-30 | St Clements | 2702 | Madison Layton | Software Provider |  | Comment on Section 17.2 "situations where multiple existing meters are identified, the selection process should be extended to include Meter Removal date (if provided) else;" Sent on Jan 11th: Shouldn’t be possible, can run an EES or MPRS RFI to confirm. Noting that MSN is only unique at an MPAN level not a databse level Related to DI-21 (raised as DI ID 24) | Implemented |  | Interim Release 1 |  | Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. The wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-25 |  | N/A | 2023-01-30 | St Clements | 2706 | Madison Layton | Software Provider |  | Comment on Section 17.2 "where multiple meters still exist even after matching on all three data items should be rejected and require manual intervention (i.e. request to LDSO to intervene) ." Sent on Jan 11th: There's no super user functionality for this so how could the LDSO intervene? The LDSO is not able to manually intervene in regards to MTDs, they can for some other data items such as registration data but not MTDs. (raised as DI ID 25) | Implemented |  | Interim Release 1 |  | Reference to LDSO User Removed - agreed with SCS that scenario should not arise provided existing SCS data rules are met | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-26 |  | N/A | 2023-01-30 | St Clements | 2707 | Madison Layton | Software Provider |  | Comment on Section 17.2 "If the MAP segment is not provided, the existing MAP history should be maintained to greatest degree possible, with ‘trimming’ to align to any revised Install / Remove Dates provided" Sent on Jan 11th: Risk that changing of the Meter Lifespan could result in MAPs being logically deleted. The MS would need to re-apply the MAP history to fit into the new meter Lifespan MS would need to understand this process/constraint (raised as DI ID 26) | Implemented |  | Interim Release 1 |  | Section 17.2 of the guidance document updated. Also added new validation rule REG1014 for MeterHistoryUpdate in IF-005 to ensure MAP is provided when creating a new meter picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-27 |  | N/A | 2023-01-30 | St Clements | 2708 | Madison Layton | Software Provider |  | Comment on Section 19.2 "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the permanent deletion of data, mirroring the existing functionality associated with the use of the D0312." Sent on Jan 11th: Only logically deleted, still visible in the MPRS History. Just not visible to MEM or EES Existing functionality on D0312 utilises cancellation flags not permanent deletion (raised as DI ID 27) | Implemented |  | Interim Release 1 |  | Reword to reflect the logical deletion. See MHHS-DIN-23 Reword this paragraph to: "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the removal of a MAP from a meters MAP history using a logical flag, mirroring the existing functionality associated with the use of the D0312." NB Main section header is incorrect - should be updated to section 19, rather than a duplicate of section 18. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Accepted but note there is another DIN already raised
MHHS-DIN-28 |  | N/A | 2023-01-30 | St Clements | 2709 | Madison Layton | Software Provider |  | Comment on Section 19.4 "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories. However, this would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." Sent on Jan 11th: This functionality already exists with the MPAN History Report showing who changed what when for all MPRS data items. Will be extended to include DIP transactional information (raised as DI ID 28) | Implemented |  | Interim Release 1 |  | Proposed Change Reword this paragraph to: "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories, noting that this is also available via the MPAN history report which will be updated with DIP transactional information and could also be used. Any use of EES would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-29 |  | N/A | 2023-01-30 | St Clements | 2710 | Madison Layton | Software Provider |  | There should be an additional rule for USP, if DI-830/DI-833 is populated, the MS/DS Proposed Effective From Date must equal the currently held EFD for the MS/DS appointment in MPRS (raised as DI 29) | Implemented | 2023-04-27 | Interim Release 1 |  | Added rule for USP scenario in IF-031 to check SP Effective from date. Proposing SCS have flexibility on error codes - requires industry Working Group. Picked up as part of Change of Service Provider review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-30 |  | N/A | 2023-01-30 | St Clements | 2711 | Madison Layton | Software Provider |  | The IF-035 does not provide the opportunity for MPRS to populate a lapsed reason. Will need to be able to provide a reason for a lapsed appointment, otherwise there'll be a higher volume of unecessary supplier enquries to DNOs which will require more resource and cost. (raised as DI 30) | Implemented |  | Interim Release 1 |  | Additional Data Item on IF-035 for a reason comment - what reasons would these be other than gone beyond the date? Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-31 |  | N/A | 2023-01-30 | St Clements | 2712 | Madison Layton | Software Provider |  | MHHS-BR-RS-027 "Registration Service must re-run validation, in line with the validation rules set out in the appropriate interface specification, for all Metering Service appointments that have been confirmed to re-process from the Prospective Appointment Queue, to ensure that the appointment is still valid" It is not clear if MPRS would send MSAppRejected or MSAppLapsed if the appointment fails validation after it's been queued? If this is not made clear in the deisgn then there is a risk that we build to use the wrong event code, or if the code should be MSAppRejected then risk that suppliers build a design where they can't process a MSAppRejected after receiving already an MSAppAccepted from MPRS (raised as DI 31) | Implemented |  | Interim Release 1 |  | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • Updated BRS003, requirement MHHS-BR-RS-032 and 66 to show that appointments will be lapsed (not rejected) • Remove Rejected from Step 225 of BP002/BPD002 Also on BP003 leading from step 215 should have the rejected removed. Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Corrections also to BPM002 & BPM003 Forward Migration and BPD002 Froward Migration | Data interface correction | MPAN Ownership |  | MHHSP-BP002-Change of Service - Metering service, BPD002,MHHSP-BRS003-Registration Service requirements MHHSP-DES138-Interface Catalogue, MHHSP-BP003, MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration), MHHS-DEL969-BPD002 (forward migration) | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-32 |  | N/A | 2023-01-30 | St Clements | 2713 | Madison Layton | Software Provider |  | The interface catalogue lists setting a removal date as an action that can be used with event code meterUpdate on IF-005, however in the interface catalogue, the block B039 does not list meterUpdate as a event code that can utilise this block. Need greater clarity on whether meterUpdate and meterHistoryUpdate should apply meter installations and meter removals or not. (raised as DI 33) | Implemented |  | Interim Release 1 |  | The definition of a [MeterUpdate] event code is: Allows currently appointed Metering Service to amend the details associated with a currently installed meter. Therefore the appointed Metering Service must be able to remove the meter as part of an update, this is an omission from the design and a small update to IF-005 The design principle that IF-005 works on is that: • BAU transactions (Install/Exchange/Remove) that are in the Metering Services Period of ownership are covered by the Install/Exchange/Remove events • Changes to currently installed metering can be made by the Appointed Metering Service using the Meter Update event. Note this therefore includes, where required, removing the currently installed meter where it is prior to the current period of ownership. • Changes to metering history ( ie not the currently installed meter ) can be made by the Appointed Metering Service using the Meter History Update Proposed changes: Added MeterUpdate as Optional to B039 block in IF-005 and added validation rule to ensure MeterUpdate is not used to remove meters in current period of ownership picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP-DELS229-IF-005 Use Case Guide | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-33 |  | T4-COM-1759 | 2023-01-30 | St Clements | 2719 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1759 on 15th Sept 2022: IF-005, REG1011 Install date must be > Creation date, should this REG1011 rule apply also to meter Exchange not just meter install SCS raised as a design blocker on 7th October 2022 Still no resolution, should this rule apply to meterHistoryUpdate at least as this allows for meter installations (raised as DI 34) | Implemented |  | Interim Release 1 |  | An exchange will not be a creation date, and the validation already in place ensures that future installation dates will all follow each other, which means this rule isn't required. ​This shouldn't be needed for exchanges, as its covered by REG1008 (install date >= remove date), as an exchange would replace an existing meter, which at first install would be validated against creation date. Moved REG1011 to cover all scenarios in IF005 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-34 |  | T4-COM-1774 | 2023-01-30 | St Clements | 2720 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1774 on 15th Sept 2022: IF-005, REG1011 "REG1009 - MAP ID [DI_055] is not valid for MAP Effective Date [DI-054] REG1011 - Install Date [DI-057] for MeterID [DI-056] is prior to MPAN Creation Date There are many meters in MPRS that pre-date the existence of the MAP and also MPRS install dates of 1980 etc. these will break a number of rules. should these be cleansed before MHHS start? If they are valid, then the rules need adjusting"l SCS raised as a design blocker on 7th October 2022 Still no resolution (raised as DI 35) | Closed |  |  |  | This could be a data cleanse requirement which is a consequential change/transition requirement, but for REG1009 - the MAP effective date should be the point at which the MAP took over the meter, and the exchange date should be after this (ie it should be after the date MHHS goes live). For Reg 1011 currently this is only valid on installs (and installs won't occur on legacy meters). If Reg 1011 is valid on exchanges, then the exchange date should also be after the MPAN creation date - if it isn't then the data should be cleansed. Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-35 |  | N/A | 2023-01-30 | St Clements | 2721 | Madison Layton | Software Provider |  | On the IF-005, should REG1028 (Install date cannot be null or blank) apply to meterinstall, meter exchange and meterupdate too? (raised as DI 36) | Implemented |  | Interim Release 1 |  | Requires amendment to interface validation - look at alternative validation Agree the rule should also apply for those events. Note we believe validation would fail for another reason. Eg REG1019 Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-36 |  | DI-37 | 2023-01-30 | St Clements | 2722 | Madison Layton | Software Provider | Re-alignment of rejection reasons to main block | In the summary of error codes box at the bottom of IF-005 tab the rejection reasons need re-aligning to the main block, e.g. REG1001 should read RMP stats must be Created or Operational, not just Operational As a general note across all interfaces, the rejection codes are referenced in numerous places and the respective descriptions are in many places not consistent for the same rejection code (raised as DI 37) | Closed |  |  |  | Will be revisited once SCS provide definative Error Code Texts | No Change |  |  |  | 2023-02-23 | 23/2/23 - Not discussed at meeting carry to next meeting
MHHS-DIN-37 |  | N/A | 2023-01-30 | St Clements | 2723 | Madison Layton | Software Provider |  | REG1015 (cannot be removed meter) is listed for meterHistoryUpdate in interface catalogue for IF-005. This should actually apply to meterUpdate not meterHistoryUpdate, REG1018 (cannot be installed meter) applies to metering history update (raised as DI 38) | Implemented |  | Interim Release 1 |  | Change accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-38 |  | N/A | 2023-01-30 | St Clements | 2724 | Madison Layton | Software Provider |  | In the interface catalogue, the IHD block B030 for IF-005 should also be optional for meterUpdate according to the IF-005 guide Section 16 Development Notes "The IHD segment, if provided as part of [MeterUpdate], relating to any currently installed meter should replace/update the IHD details currently held at the MPAN to which that Meter is associated." (raised as DI 39) | Implemented |  | Interim Release 1 |  | Small change to schema operation IHD information may be updated as part of the [MeterUpdate] event. The change is to add [MeterUpdate] event to block B030, so it now reads "B030 - MPAN IHD Information (Optional & may only be used with [MeterInstall],[MeterExchange],[MeterUpdate]) NB this also standardises the use of commas between event codes, rather than using the & symbol. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-39 |  | N/A | 2023-01-30 | St Clements | 2725 | Madison Layton | Software Provider |  | In interface catalogue for IF-005, there needs to be a rule that if event code MeterInstall is used, then modified meter ID cannot be populated (raised as DI 40) | Implemented |  | Interim Release 1 |  | Update agreed | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-40 |  |  | 2023-02-01 | SI Design |  |  |  |  | Not used - raised as duplicate in error | Closed
MHHS-DIN-41 |  | N/A | 2023-01-30 | St Clements | 2730 | Madison Layton | Software Provider |  | In interface catalogue IF-005: The REG1003 reads Metering Service [S0.SenderID] holds valid previous appointment then Meter Install Date [DI-57] should be < [REG.App End Date] + 10 The way it's curently written suggests MPRS should accept an IF-005 from the previous appoint, even if their ETD was greater than 10 days ago, provided the install date was less than their ETD + 10. E.g the previous MS could send IF-005 two years later with Install date of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then REG1002/REG1019 should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? (Raised as DI 41) | Implemented |  | Interim Release 1 |  | Having looked through IF-005 Dates should be within the appointment date, and current deign does give the ability to go outside this Change the validation rule for REG1003 on events [MeterExchange], [MeterInstall] and [MeterRemoval] to "If Metering Service [S0.SenderID] holds valid previous appointment then [system date] < [REG.App End Date] + 10" Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. Rule amended after review by SCS, to remove second "if" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-42 |  | N/A | 2023-01-30 | St Clements | 2784 | Madison Layton | Software Provider |  | In interface catalogue IF-005: Meter Update should apply validation REG1027 (current MS or prospective MS) not REG1012 (current MS only) to allow the prospective queued MS to update the Meter Type on a SEG change and therfore complete the market segment change and appointment. MHHS-BR-RS-132 . If the SEG prospective appointment was not allowed to update on meterUpdate event code then they would not be able to update the meter type to completed change of market segment, and would not meet the conditions needed to then be appointed in MPRS, their appointment would then lapse and market segment would remain invalid. (Raised as DI 42) | Closed |  |  |  | We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error... | No Change |  |  | None
MHHS-DIN-43 |  | N/A | 2023-01-30 | St Clements | 2732 | Madison Layton | Software Provider |  | In Interface Catalogue, on If-005, REG1002 and REG1019 are duplicates (install/removal dates should be within MS period of ownership). We can only use one of the rejection codes and descriptions, programme should choose which one to keep and remove the other. (Raised as DI 43) | Closed |  |  |  | These are testing slightly different things. The first test (REG1002) is checking that the Metering Service is an eligible party to send the request ie currently appointed OR was at the time of the install (to cover for previous Metering Services updating in the 10 day window). The second (REG1019) is checking that the Install Date is in the Metering Services period of ownership. So you could have that the Metering Service is currently appointed, but that they weren't at the install date. Eg Today is 2nd Feb, Meter installed on 27th Jan, Sending MS was appointed on 1st Feb REG1002 would pass as they are eligible as the currently appointed MS REG1019 would fail as they are not appointed at the time of the install Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-44 |  | N/A | 2023-01-30 | St Clements | 2733 | Madison Layton | Software Provider |  | Should the new rule for meter update in IF-005 also apply to meter history update? If no MAP entries provided, and revised Meter Install / Remove Dates result in no valid MAM History then reject with REGE1014 – MAP Eff From Sequence Error (Raised as DI 44) | Implemented |  | Interim Release 1 |  | Added REG1014 ( MAP History ) to IF-005 MeterHistoryUpdate event | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-45 |  | N/A | 2023-01-30 | St Clements | 2736 | Madison Layton | Software Provider |  | New rule for IF-005 Meter Update REG1017 could be misinterpreted as it currently reads incorrectly - need brackets to correct to how the AND and AND/OR conditions are to be applied If [DI-60] is not null AND Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null) Should read If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null)) (Raised as DI 45) | Implemented |  | Interim Release 1 |  | Clarification of existing design rule Change the validation rule for REG1017 to: "If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null))" picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-46 |  | N/A | 2023-01-30 | St Clements | 2737 | Madison Layton | Software Provider |  | on IF-005 for Meter Exchange and meter install the rule for REG1027 has been changed, but I'm not sure the wording implements the rule intended exactly? Currently it reads as The MS must be the currently appoint MS AND the install date must be > MS EFD AND the MS must not have proposed MS app with SEG scenario in the queue. If not then reject with REG1027 - Metering Service is not currently appointed and does not hold a Prospective SEG Appointment SHould the rule actually read The MS must be the current MS OR the MS must have a proposed MS App in the queue with SEG scenario And then the other part of the rule about install date > MS should be a separate rule (with REG1019 error code). (Raised as DI 46) | Implemented |  | Interim Release 1 |  | Sent to Mike F for validation - SI believe wording in current documentation is correct. Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. I would suggest the wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. DIN-46 – On review we agree, the date test should always be true if REG1019 is satisfied ( with minor clarification update ), so validation rules should be updated as below: Proposed changes: REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 |  | Not discussed at meeting carry to next meeting
MHHS-DIN-47 |  | N/A | 2023-01-30 | St Clements | 2738 | Madison Layton | Software Provider |  | REG1001 on IF-005 does not allow for meters to be removed after a disconnection. Instead should restrict for allow other event codes but allow Status Terminated for MeterRemoval. DES204 CCR-0556 Linked to DI-13 | Implemented |  | Interim Release 1 |  | Rule update required picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-48 |  | DI-048 | 2023-01-30 | St Clements | 2739 | Madison Layton | Software Provider | CSS failure to apply CoS to related secondary MPANs | Unhappy path scenario:- What happens if, for whatever reason, CSS fails to apply CoS to all the related secondary MPANs MPRS receives IF-031 on primary RMP to change agent, MPRS applies this to all seocndary MPANs too But if the CoS was not received from CSS for secondary MPANs that the secondary MPANs would still currently be held for the wrong supplier Would this cause any issues downstream? (Raised as DI 48) | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | CSS Defects issue. Agreed that Risk would be raised and all CSS related issued assessed at a later date | Other | MPAN Ownership | Related MPANs | [5 empty] | 2023-07-14
MHHS-DIN-49 |  | N/A | 2023-01-30 | St Clements | 2740 | Madison Layton | Software Provider |  | Unhappy path scenario:- If MPRS sends a IF-033 but never receives back a IF-034 then the rest of the process will not continue. The Supplier will never receive the IF-035 they are waiting for and the SP would never get appointed by MPRS. Is there a process in place to detect/resolve this scenario? (Raised as DI 49) | Closed |  |  |  | There is a requirement for the Supplier to monitor for any delayed responses and request an update if not received in expected timescales. Reviewed with SCS and agreed ticket can be closed | No Change |  |  | None
MHHS-DIN-50 |  | N/A | 2023-01-30 | St Clements | 2741 | Madison Layton | Software Provider |  | We need clear rules to define what a valid Consent granularity looks like. Current rules don’t mention any validation around EDI. (Raised as DI 50) | Implemented |  | Interim Release 1 |  | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-51 |  | DI-51 | 2023-01-30 | St Clements | 2747 | Madison Layton | Software Provider | St Clements Design Query - DI 51 | We have had some feedback from DNOs asking about how systems will recover from System Misalignment because of data errors or significant downtime? We have the D0204 (Supplier) and D0209 (Data Aggregator) Refresh functions today which are not being replaced with a DIP message equivalent. I am aware of the DIP Replay function, but this wouldn’t be of any help if there were data errors, as the DIP would just be replaying the incorrect data. The Source system would need to re-send the corrected data in an agreed format. I know there is a design principle to move away from bulk loads and refreshes of data, Faster Switching took a similar approach. However today, CSS leans heavily on the MPRS Refresh function to get itself back inline and there are REC CP’s being raised to add a Refresh function to CSS for all parties (first CP being R0067). DNO’s are keen to understand the MHHS Programme’s position on and if Refresh functionality should be built into MPRS for MHHS. | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | Refresh Functionality was rejected by the Working Groups so not in current design. Internal Design Discussion Required on if Programme position has changed on this given CSS Issue / EES Fed via DIP ?? | Other | Supporting Docs | Refresh Process? | [5 empty] | 2023-07-14
MHHS-DIN-52 |  | DI-52 | 2023-01-30 | St Clements | 2748 | Madison Layton | Software Provider |  | For IF-005, REG-1006 and REG1013, would it make sense to include the installation date of the MPAN already in the system in the rejection description too to help MS with triage? | Closed |  |  |  | DIN closed as instructed by St Clements. Old comments: Discussed with SCS potential for them to have flexibility on error messages. Industry agreement required. Participant Discussion Required | No Change |  |  |  | 2023-02-23 |  | Not discussed at meeting carry to next meeting
MHHS-DIN-53 |  | N/A | 2023-01-30 | St Clements | 2749 | Madison Layton | Software Provider |  | Requirement on LDSO requirements spreadsheet: MHHS-BR-LD-035 LDSO Maintain DUoS Tariff ID LDSO must set Duos Tariff ID on MPAN creation and maintain DUoS Tariff ID's in line with their Charging Method Statement. This should include updating the Duos Tariff ID, as required, following any updates to Domestic Premise Indicator, Connection Type and Energy Direction Note for MHHS, LLFC ID is being renamed as DUoS Tariff ID to make it clearer what this data item is used for. "BP010B Change of registration data" 250 However missing the respective requirement for Registration Services in the Registration Services Requirements spreadsheet | Closed |  |  |  | Looked through the Registration Services Requirements spreadsheet v4.6 and it looks like DUoS Tariff ID is there - MHHS-BR-RS-091.1, MHHS-BR-RS-121 and MHHS-BR-RS-122 | No Change |  |  | None
MHHS-DIN-54 |  | N/A | 2023-01-30 | St Clements | 2750 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1699 on 15th Sept 2022: On the IF-031 and IF-035 there are a number of "Proposed" Data items. Should MPRS load these and updated the stored data items. Or are these data items only for passing through to Supplier and Service? SCS raised as a design blocker on 7th October 2022 We have some clarity verbally on this but nothing has been formally documented in the design artefacts. This needs to be reflected somewhere in the requirements. | Implemented |  | Interim Release 1 |  | Added "Appoinments - Data" section in REG Notes to highlight what data becomes effective with the appointment. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-55 |  | T4-COM-1738 | 2023-01-30 | St Clements | 2751 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1738 on 15th Sept 2022: the DB02 flow updates multiple data items on the IF-018 in one event. Can multiple EventCode be included in one IF-018 or will MPRS need to generate an individual IF-018 for each EventCode? SCS received a blank response and raised as a design blocker on 7th October 2022 | Closed |  |  |  | Original response was that clarification was to be provided on 24th Oct - is this available? Which document? One at a time | No Change |  |  | None
MHHS-DIN-56 |  | T4-COM-1742 | 2023-01-30 | St Clements | 2752 | Madison Layton | Software Provider | Manual Correction to MHHS data items | Originally raised as T4-COM-1742 on 15th Sept 2022: BSCP604 currently allows LDSO and Suppliers to request manual corrections to Data Items held in MPRS. Will this type of Manual Correction be allowed in MHHS, if yes then this should be added to the business process to capture manual amendments and how these changes are reflected back to DIP users (IF-018 & IF-026, or a new Refresh Message?) SCS received a blank response and raised as a design blocker on 7th October 2022 Another exaple of this: If the MS/DS history is incorrect and cannot be amended via BAU, would the DNO be able to correct this via an exceptional error handling process? | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | Internal review required | Requirement correction | MPAN Ownership | CSS Defects | MHHS-BPD005 Data Processing, MHHS-BRS005 LDSO overview |  |  |  |  | 2023-07-14
MHHS-DIN-57 |  | T4-COM-1748 | 2023-01-30 | St Clements | 2756 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1748 on 15th Sept 2022: "Additional information field DI-120 is String200, where the existing DB03 allows a free text field of 2000 characters" SCS raised as a design blocker on 7th October 2022 This was corrected but then in v4.5 artefacts released there was a change back for DI-120 addition infromation field from string 2000 to string 200 in the interface catalogue data catalogue tab reintroducing the issue. For disconnection additional notes MPRS database holds 2000 characters so this field will need to be string 2000 in the IF interfaces (Raised as DI 57) | Closed |  |  |  | Change to the data catalogue included in the 4.7 baseline | No Change |  |  | None
MHHS-DIN-58 |  | T4-COM-1789 | 2023-01-30 | St Clements | 2757 | Madison Layton | Software Provider | Valid combinations of ISD data for MPRS validation development | Originally raised as T4-COM-1789 on 15th Sept 2022: "Valid combinations of data in ISD are critical to the MPRS validation development, we must have these defined and agreed before we can start development" SCS raised as a design blocker on 7th October 2022 | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Elexon is defining the valid combinations of data in the ISD. Parties need to define their own data. | Requirement correction | Supporting Docs | ISD | MHHSP-EM021 ISD Entity Map |  |  |  |  | 2023-07-14
MHHS-DIN-59 |  | T4-COM-1707 | 2023-01-30 | St Clements | 2758 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1707 on 15th Sept 2022: "The Smart DS for Export and Secondary MPANs can be different to the Import/Primary DS as the Customer can choose their own DS for Export and Primary (Smart only)" The IF-031 validation rules have been amended but they are still not corrrectly reflecting the rule. The heading above both rules REG1038 and REG1039 reads: "If event type = [MSApp] OR event type [DSApp] & MPAN Segment is not 'Smart'" This heading should ONLY apply to REG1038 for linked MPANs and should not apply to REG1039 concerning related MPANs It should also have brackets to clarify the logic otherwise it could be misinterpreted e.g. "If event type = [MSApp] OR (event type [DSApp] & MPAN Segment is not 'Smart')" | Implemented |  | Interim Release 1 |  | This seems a valid issue. REG 1039 on linked meters should be allowed for trad meters (eg economy 7) Proposed Change: The logic issue here is that REG1039 caters for related meters, which are applicable to trad as well as smart meters. Remove REG1039 from this validation Change the validation to: "If (event type = [MSApp] OR event type [DSApp]) & MPAN Segment is not 'Smart'" Updated heading above REG1038 and added heading above REG1039 to clarify the validation rule in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-60 |  | T4-COM-1708 | 2023-01-30 | St Clements | 2759 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1708 on 15th Sept 2022: "The Service Appointment Date must be equal to the SSD or there will be a period with no Service" And T4-COM-1776 also on 15th September 2022 "REG1032 - Metering Service Eff From Date [DI-830] is not contiguous - Appointment must be from [Max[Reg.MPAN_SSD] ,[Reg.ExistingMSAppFrmDate]] for a COS, it can only equal the SSD otherwise there will be a gap" This has been applied incorrectly. In IF031 rules REG1032 now reads that the MS/DS prop EFD must be = Max(SSD, existing MS/DS EFD + 1) This would restrict the MS/DS to setting the new EFD to either SSD or the day after the last MS/DS appointment, and all other dates would be rejected. It should read >= not just =. All four refrences to REG1032 in the validation rules for IF-031 references the +1 day after EFD, but the rejection description in the right hand columns for 'scneario not SEG or CoS' section does not reference this + 1. This should be corrected to be consistent with the other rules. (Raised as DI 60) | Implemented |  | Interim Release 1 |  | Original response to 1708: New rules added to cover all scenarios Original response to 1776: Change to be incorporated into design artefact Updated REG 1032 validation in IF-031, original single rule, split into 2 separate rules picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-61 |  | T4-COM-1445 | 2023-01-30 | St Clements | 2760 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1445 on 15th Sept 2022: "There is no mechanism to update the Profile Class. We would assume that this would be updated by the Supplier (with business rules restricting when this should be set) and confirmed on the IF-026. Please can you confirm if this is the intention or if it will be updated through another route. If so, the EES would need to know which PUB would confirm the data item had been updated. " Whilst this is now included in the design the validation rules from D0205 have not been carried over, e.g. PC/SSC need to be a valid combination. ISD will need to contain the valid PC/SSC Combinations (previously MDD Entity 11) and the validation rules in the interface catalogue will need to reference this validation against the ISD valid combinations. (Raised as DI 61) | Implemented |  | Interim Release 1 |  | See also DIN-58, need to find out who is defining ISD validation Updated Interface notes in IF-025 to confirm that there is no Profile Class/ SSC combination checks | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-62 |  | DI-062 | 2023-01-30 | St Clements | 2761 | Madison Layton | Software Provider |  | In the business process diagram for Registration Updates MHHSP-BP010-Change of Registation Data - v4.5, the MPL update section, the C0300 has been changed to C0400 which is incorrect, C0400 is for MAP updates. Address updates are actually sent in the C0600. (Raised as DI 62) Change raised 30 March:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly. | Implemented |  | Interim Release 1 |  | Also in the BPD. MHHS-BR-RS-114 also confirms this should be C0300, this appears to be a straightforward typo. Amend label between Step 20 and Step 30 on BP010A to CSS0300, and update the corresponding BPD description on step 30 Update required:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly in BP010A, BPD010 and in MHHS-BR-RS-114. | Process model correction | Metering Changes | MPAN Updates | MHHSP-BP010-Change of Registration Data MHHSP-BPD010 MHHSP-BRS003
MHHS-DIN-63 |  | DI-063 | 2023-01-30 | St Clements | 2792 | Madison Layton | Software Provider |  | In the business process diag for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 (Raised as DI 63) | Closed |  |  |  | SCS have now confirmed that C0700 is the correct reference - no need to change documentation - agreed to close | No Change | MPAN Ownership | Disconnection | MHHSP-BP007-Disconnection MHHSP-BPD007
MHHS-DIN-64 |  | N/A | 2023-01-30 | St Clements | 2793 | Madison Layton | Software Provider |  | In business process diag for change of data service MHHSP-BP003-Change of Service- Data Service-v4.5 and MHHSP-BP002-Change of Service- Metering Service v3.5, this still makes reference to D0386 in the purple note boxes. This should now have changed to IF-019 (Raised as DI 64) | Implemented |  | Interim Release 1 |  | Update notes on BP002 and BP003 from D0386 to IF-019, and for BPM002 & BPM003 (forward migration) | Process model correction | MPAN Ownership | Change of DS | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-65 |  | N/A | 2023-01-30 | St Clements | 2794 | Madison Layton | Software Provider |  | The business process diagram for change to connection type/market segment has been amended to name only DB01, connection type is set on DB01 but it can then be changed on DB02 (Raised as DI 65) | Implemented |  | Interim Release 1 |  | Update label between step 220 and 225 from "DB-001" to "DB02" | Process model correction | Metering Changes | Market Segement | MHHSP-BP011-Change of Connection Type or Mkt Segment
MHHS-DIN-66 |  | N/A | 2023-01-30 | St Clements | 2795 | Madison Layton | Software Provider |  | In interface catalogue, on IF-031, shouldn't rule REG1036 (MDR app EFD must be after DS app EFD), be applicable to all scenarios including SEG? Currently under section for if not SEG (Raised as DI 66) | Implemented |  | Interim Release 1 |  | Updated validation rule for REG1036 and made applicable to all scenario's in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-67 |  | N/A | 2023-01-30 | St Clements | 2796 | Madison Layton | Software Provider |  | Currently no rule on IF-031 that the SP appointment has to be within the prospective suppliers registration period - just that it can't be past dated. This rule will need to be added. (Raised as DI 67) | Closed |  |  |  | Reviewed with SCS and agreed that this validation is covered by existing rules. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-68 |  | N/A | 2023-01-30 | St Clements | 2797 | Madison Layton | Software Provider |  | If-031 business rule missing If the Scenario is USP, the consent granularity must be the same as the existing consent granularity held within MPRS (Updates should be through IF-025 not through IF-031) (Raised as DI 68) | Implemented |  | Interim Release 1 |  | picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Updated Interface notes in IF-031 to clarify that Registration Service will ignore any differences in Domestic Premise Indicator/ Consent Granularity sent on IF-031 (USP scenario) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-69 |  | N/A | 2023-02-02 | ESG Global | 2653 | Luke Speakes | Software Provider |  | PUB-033 - Block 029 is conditionally mandatory for DCC Commissioned Meters, but includes DI-025 DCC Service Flag with valid values of A-Active, I-Installed Not Commissioned, N - Non Active. The title of the block, which should define whether it is mandatory or not, is not appropriate if a DCC meter has been installed and not commissioned, or is inactive. Propose following SI and SRO design discussion that title of block 029 is revised to conditionally mandatory for 'DCC Smart Meters' | Implemented |  | Interim Release 1 |  | Concludes this can be resolved by a minor wording change to the block title | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 |  | Not discussed at meeting carry to next meeting
MHHS-DIN-70 |  | N/A | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory | Addition of MDR validation rule | Elexon is required to maintain a valid list of Meter Data Retrievers in Industry Standing Data, to allow RegService to validate they're suitably qualified (DCC and SEC) MDRs are being appointed. | Implemented |  | Interim Release 3 | 2023-07-12 | Design Agreement is to utilise M16 for this purpose. ISD document updated with details and examples to this effect. | Other | Supporting Docs | ISD | MHHS-EDI-021-ISD_Entities | 2023-02-23 |  | Not discussed at meeting carry to next meeting |  | 2023-07-14
MHHS-DIN-71 |  | N/A | 2023-01-30 | St Clements | 2839 | Madison Layton | Software Provider |  | When would event code [MSDeAppUpdate] and [DSDeAppUpdate] be used for on an IF-037? (Raised as DI 69) | Closed |  |  |  | Reviewed with SCS and it is used to notify the incoming Service Providers when de-appointing and not origanally known. In case of Linked/Related MPANs individual MPANs move through the process. RS need to apply the logic for sending the updated IF-037 to all MPANs. Agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-72 |  | N/A | 2023-01-30 | St Clements | 2840 | Madison Layton | Software Provider |  | Block B018 on IF-034 and IF-035 should not be mandatory - it will only be provided for smart meters. This needs to be set to mandatory for SDS-MDRUpdate only, optional for DSAppSPResponse (Raised as DI 70) | Implemented |  | Interim Release 1 |  | Updated B018 block to be optional for non Smart on IF-034 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-73 |  | N/A | 2023-01-30 | St Clements | 2841 | Madison Layton | Software Provider |  | IF-026/IF-025, added new event code [SSCandProfileClass], but still kept in original [SSC] and [ProfileClass] event codes, should the original two have been removed? Particularly as the B032 group says it's madatory where event code is [SSCandProfileClass] and does not refer to [SSC] or [ProfileClass] individual event codes (Raised as DI 71) | Implemented |  | Interim Release 1 |  | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-74 |  | N/A | 2023-01-30 | St Clements | 2842 | Madison Layton | Software Provider |  | A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a new MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60 (Raised as DI 72) | Implemented |  | Interim Release 1 |  | This appears to be the reciprical change to MHHS-DIN-60 for the response interface Update description to "Check if MDR Eff Date = SSD OR on or after existing MDR Eff From + 1" Update rule to "If [DI-841] <>SSD OR <MDR Eff Date + 1" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-75 |  | N/A | 2023-01-30 | St Clements | 2843 | Madison Layton | Software Provider |  | On IF-035, overidden the description for Data Item 836 incorrectly with the description for Data Item 838 (Raised as DI 73) | Implemented |  | Interim Release 1 |  | Update the definition field based on the description in the data catalogue for DI-836 on IF-035 (Date From which Supplier would like Nominated MDR to take effect) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-76 |  | N/A | 2023-01-30 | St Clements | 2844 | Madison Layton | Software Provider |  | Data catalogue - changed the estimation reason code authoritative source to Registration Service, this data item is not received by, sent by or held by registration services and so the authoritative sourse cannot be Registration Service (Raised as DI 74) | Implemented |  | Interim Release 1 |  | The authoriative source has changed between v4.0 (from Data Service) to 4.7 (Registration Service) - have asked why the change was made, and what the authoritative source should actually be. Source updated to SDS/MDS | Data interface correction | Meter to Bank | Estimation | MHHSP-DES138-Interface Catalogue
MHHS-DIN-77 |  | N/A | 2023-01-30 | St Clements | 2845 | Madison Layton | Software Provider |  | Data catalogue - Added issue 99 items (CT Ratio, Phases etc) DI-170 - DI-180. Was agreed in work off meeting these items are not within the scope of MHHS, to introduce these would require a CR (Raised as DI 75) | Implemented |  | Interim Release 1 |  | these data items don't appear to be used in any interfaces so this could be a relatively simple change to remove 11 items from the data catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-78 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E0404 requirement is blank - row needs to be deleted | Closed |  |  |  | This update was already incorporated into version 5.0 closing it here | No Change | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-79 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E21114 typo - should be VAS Output Retention | Implemented |  | Interim Release 1 |  | change as per description | Technical corrrection | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-80 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHSP-DES138-Interface Catalogue v4.6 - DI-846 Issuing Data Service EZ Name should be scored through in IF/ PUB21 definition | Closed |  |  |  | Completed in V5.0, part can review change as part of Interim Release 2 | No Change | Meter to Bank | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-81 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier | Correction of step in BP020 | MHHSP - BP020 - Volume Allocation Service (ECS) v4.6 - Step 75 to Step 80 references report “REP-00” - needs correcting | Implemented |  | Interim Release 2 | 2023-06-23 | BP020 step 75 to step 80 process flow REP list correction BPD020 step 75 & step 80 detail list of REP's correction | Process Model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions |  |  |  |  | 2023-06-16
MHHS-DIN-82 |  | N/A | 2023-02-09 | SI Design | 2716 | Rob Short | SI Design | Missing listed number of reports in BPD002 | Related to DIN-81 - BPD002 lists number of reports at step 75, BP002 does not reflect this list, missing PO275, PO214 and PO213 | Implemented |  | Interim Release 2 | 2023-06-23 | This relates to BP020 (not BP002), similar to DIN81, reconcile REP list correction on BP020 at step 75 and 80 and reconcile with BPD020 list of REPs | Process model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions |  |  |  |  | 2023-06-16
MHHS-DIN-83 |  | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | BP011 missing PUB-044 flow | A discrepancy with the Interface Catalogue - IF_LIST states MHHSP-IF-044 is sent to Central Settlements, DS, MS, Supplier, LDSO. IF-044 tab states it is sent to Supplier, MDS, LDSO In BP011 the PUB-044 is not sent to DS only Supplier, Settlements and EES | Implemented |  | Interim Release 2 | 2023-06-23 | Add Manage change of segment in LDSO lane on business process BP011C with a PUB-044 flow from step 570 Add new step to BPD011 Interface catalogue is already updated | Process Model correction | Metering Changes | Interface Catalogue | MHHSP-BP011 Change of ConType andor Mkt Segment MHHSP-BPD011 MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-84 |  | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | DES-138 IF List Tab Consistency | IF_LIST states MHHSP-IF-020 is sent to Supplier onlyIF-020 states it is sent to Supplier, Data Service, Metering Service, LDSOIn BP010, the PUB-020 is sent to Central Settlements, CSS, EES, Supplier, Data Service, Metering Service, LDSO.This one looks like its just the Interface Catalogue that needs updating. IF-020 Updated to refect new agreed Routing | Implemented |  | Interim Release 2 | 2023-06-23 | Updated parties receiving PUB-020 in the IF_LIST, updated PUB-020 routing to include MDS for Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-85 |  |  | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory |  | Elexon see DIP qualification for new users being part of market entry post-programme, but want to understand how MHHSP will operate qualification during the programme. This is likely to cover the majority of participants. Discussions with SRO colleagues indicate they are assuming this is a process for the Enduring Service Operator to define. Challenge applies to non-BSC DIP participants (e.g. adaptor providers), and considerations under Issue Group 101. SI design has spoken to at least 4 participants who are operating in this space and seeking to understand how they can engage with SIT and other programme activities as a DIP connection provider (E2E Architecture - 3.3.2) | Closed |  |  |  | To be handled as part of the Placing Reliance document | No Change | Qualification | Qualification | New Process - DIP Qualification for New Users
MHHS-DIN-86 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Invalid Market Segment BP011C requires SMRS to notify the Supplier of an invalid market segment. RegService requirement RS0124 states that SMRS must derive a value for Market Segment based on Connection Type and Meter Type following a Change of Metering, Change of Connection Type (Change of Unmetered Indicator) or Change of Related MPAN relationships. Given that SMRS determines segment as above, when would an invalid market segment occur, giving rise to the processes from step 560 in BP011C? Further, upon receipt of a PUB-045 Market Segment Invalid Advisory Notification, what are the next steps for a Supplier to address the issue? There are no provisions in the IF-025 for Suppliers to update Market Segment. | Closed |  |  |  | Part of ongoing discussions with Code Drafting team 20/4//23 Code Drafting believe an update needs to be made to the design to update Market Segment via IF-25. This could occur when a Supplier is trying to arrange a change of segment but one of the activities has not completed on time eg the new metering has not been notified. When Registration Service tries to evaluate the segment it may not be compatible. Notification would then go to Supplier to prompt them to chase the required update, in this example chasing the Metering Service to provide the new metering details. Another example is if the LDSO has not notified a change of connection type. The Supplier may also need to send a further SEG appointment if the original has lapsed. | No Change | Metering Changes | Change of Connection Type and/or Market Segment | MHHSP-BP011, MHHSP-BPD011
MHHS-DIN-87 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory | Process clarification for meter removal and de-energisation on same job | Energisation Process Clarification BP009 states that change of energisation status at the same time as meter works means that BP008 will be followed - what is the process when a meter removal and de-energisation are carried out in the same job? Are both D0139 (de-energise) and D0142 (remove meter) and relevant DIP interfaces required. At the moment MEMs only have to send flows relating to meter removal | Implemented |  | Interim Release 3 | 2023-07-12 | New Purple Boxes added in BP009 and BP008 to make it clear that Remove/DeEn could still be requested and carried out but MS would need to send two interfaces. Also that DeEn did not need to be notified if meter works completed within same day (ie same rules as today) | Process model correction | Metering Changes | Change of Metering | MHHSP-BP009 MHHSP-BP008 |  |  |  |  | 2023-07-14
MHHS-DIN-88 |  |  | 2023-02-09 | RECCo |  | Sarah Jones | Regulatory | Update to Incumbent MS provider for Lapsed Appointments | Update to Incumbent MS provider for Lapsed Appointments Currently BP002 only addresses the positive confirmation of de-appointment from RegService (PUB-037 - step 140/231), but if there is no secured active, there is no subsequent notification to the incumbent. The prospective MS receives a PUB-035 at step 225. How should the incumbent MS determine when the de-appointment has lapsed? | Closed |  |  |  | Part of ongoing discussions with Code Drafting team. It is not expected that the incumbant share the MTD via the IF-035 as early sight. IF-37 is the deappoint code they need to reflect . The Metering Service is appointed until they get de-appointed using a PUB-037. They are only receiving the PUB-035 as notification of who to send MTDs to, it is not intended as a notification of de-appointment. Incumbent Metering Service is a term used to refer to the MS appointed at the point another new SP Appointment is accepted (MS or DS), it shall be the Incumbent Metering Service's responsibility to share MTDs (ADV/Trad) to the incoming party. No change recommend CLOSE | [8 empty] | 2023-07-14
MHHS-DIN-89 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Customer Details on De-Appointment The MHHS design currently allows for customer data to be deleted or obfuscated by MS on de-appointment. Has obfuscation been confirmed as acceptable under GDPR? | Closed |  |  |  | Programme has called out the need for data management wrt GDPR. It is for each participant to determine the action required based on their own GDPR Guidelines and policies. |  | All Areas | [6 empty] | 2023-07-14
MHHS-DIN-90 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | MS Appointment for Associated Export Metering Points How will an initial MEM be appointed for a new export MPAN, created post MHHS go live? | Closed |  |  |  | Part of ongoing discussions with Code Drafting team - this is not a Design Issue. Design will operate as described below: The daily process monitoring (BP011C) would pick up any [new] Linked Export MPANs and ensure that the same Metering Service is appointed as the Import MPAN. If the Export MPAN is not linked, then the BAU appointment process can be followed. |  | Metering Changes | Change of Connection Type / Market Segment | MHHSP-BP011, MHHSP-BPD011 |  |  |  |  | 2023-07-14
MHHS-DIN-91 |  | N/A | 2023-02-10 | AWS | 2858 | Duncan Parsons | Software Provider |  | Document MHHS-E2E001 section 3.6 Actor Workflows Summary - Typo in the MSA Outbound. States IF-04, this should be IF-041 | Implemented |  | Interim Release 1 |  | Reference Corrected | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-92 |  |  | 2023-02-14 | RECCo | 2903, 2805, 2911 | Sarah Jones | Regulatory |  | Customer Direct Contract Flag (D053) Multiple tickets - RECCo, ESG and National Grid - all highlighting the same problem. The 4.7 artefacts do not consistently reflect the agreed position that the Customer Direct Contract flag can only be set by the incumbent Metering Service provider. The validation rules on the IF-038 should be updated The requirements for MS (013) and DS (34) in the respective BRS artefacts should be aligned | Implemented |  | Interim Release 1 |  | Added validation rule REG1075 to IF-038 in the interface catalogue Updated requirements in MS-013 and DS-034 in BRS to reflect the agreed position for D053 1/3 - ticket #3035 - SCS supportive of this change, need more detail. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue, BRS001, BRS002 | 2023-02-23 |  | Accepted but split these into two DINs one of the updates to the BRS and deal with as a minor chnge, the other as a major for the Interface Specification change
MHHS-DIN-93 |  | N/A | 2023-02-14 | Power Data Associates |  | Tom | Data Service Provider | Work off Plan D-034D updates for exceptions to Unmetered Supplies | Work off Plan D-034D updates for exceptions to Unmetered Supplies | Implemented |  | Interim Release 2 | 2023-06-23 | 1. Section 2.3 of MHHSP-METH004-UMSDS- EM Functions will be updated to make explicit that the following data items are not required by the UMSDS and as such will be ignored. • Consent Granularity (T4-COM-1857) • Domestic/Non-domestic Indicator (T4-COM-1830/1850) • Distributer Id (T4-COM-1826/1842/1845/1858/1859/1864/1865/1871/1875) • DUoS (T4-COM-1856) • LLF Data (T4-COM-1856) • Domestic Premise Indicator (T4-COM-1830/1850) • Metered Indicator- (D-045) 2. MHHSP-METH001- SDS Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 3. MHHSP-METH002- ADS- Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 4. MHHSP-METH009- UMSO Method Statement should be updated to make explicit that the following data items are not required by the UMSO and should be ignored (list to be reviewed and validated). • Consent Granularity • Domestic/Non-domestic Indicator • Distributor Id • DUoS • LLF Data • Domestic Premise Indicator • Metered Indicator | Method statement correction | Supporting Docs |  | MHHSP-METH004-UMSDS MHHSP-METH001- SDS MHHSP-METH002- ADS MHHSP-METH009 - UMSO | 2023-02-23 | 23/2/23 - Accepted |  |  | 2023-06-16
MHHS-DIN-94 |  |  | 2023-02-16 | ESG | 2777 | Patricia | Software Provider | IF-005 rejections | The IF_009 has 2 event codes: [MPANDisconnection] & [CSSDeRegistration]. [CSSDeRegistration] is listed as having Supplier as Secondary routing however on BP007 there is only reference to the supplier receiving the [MPANDisconnection] flavour of the flow. Please can you clarify which artefact is accurate. MHHSP – BPD009 step 145 states Where the Registration Service has rejected the metering update the DIP will publish the rejection to metering services. Supplier have the option to subscribe to this also. Your response was:- Our reading of this is that regservice will reject the PUB-006 back to sender if the IF-005 fails those rules. So just back to sender, not always meter service or supplier Therefore, does the BPD009 step 145 need to be updated to reflect that as the IF005 can only be generated by Metering Service Smart (MSS) & Metering Service Advanced (MSA) not the Supplier | Implemented |  | Interim Release 3 | 2023-07-12 | Question 1. Supplier will receive both events as outlined in BP007 (See DIN 294) Question 2. A decision was made at the DRG on 29th June to leave the messaging in BPD009 step 145 and instead update the business process model in BPD009 to give Supplier's the option to subscribe to rejections. | Process Model correction | Metering Changes | Change of Metering | MHHSP-BP009 – Change of Metering (Install / Remove / Exchange) , MHHSP-BPD009 MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-95 |  |  | 2023-02-20 | SI Design | NA | Simon Harrison | Programme |  | Typo in the Note box about Auto Alignment of Related/Linked MPANs on the BP002 and BP003 process maps. Change 'Regisatration' to 'Registration' | Implemented |  | Interim Release 1 |  | Update BP002 (& BP003) call out box, also for BPM002 and BPM003 (Forward Migration) | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-96 |  |  | 2023-02-21 | SI Design | 2973 | Arif Jagot | Programme |  | Test-078 - SUPPI -Primary - Means SUPI? | Implemented |  | Interim Release 1 |  | Update Interface Catalogue | Data interface correction | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-97 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.4 | Typo in MHHS-METH001-5.4c "and less than 90 days months different from the UTC Date" - propose removal of months | Implemented |  | Interim Release 2 | 2023-06-23 | Update Method Statement i.e This needs to be 90 days not 90 months the artefact needs to be updated | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-06-16
MHHS-DIN-98 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.5 | Typo in MHHS-METH001 - 5.5 SDS shall use the most recent data a based on the event that triggered the | Implemented |  | Interim Release 2 | 2023-06-23 | Typo error on clause 5.5 within MHHSP-METH001-SDS Validation Estimation v5.0 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-06-16
MHHS-DIN-99 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Working days correction | Clarify that Step 105 in the CoS Transfer read process is Working Days. Currently states 5 days | Implemented |  | Interim Release 2 | 2023-06-23 | Checked with SRO - 5 Working days for Step 105 in process, BPD003C, BR-DS-024.1 and BR-DS-024.2 | Requirement correction | MPAN Ownership | Data Services | MHHSP-BRS001 - SDS Requirements MHHSP-BP003C - Transfer of Reads MHHSP-BPD003C - Transfer of Reads |  |  |  |  | 2023-06-16
MHHS-DIN-100 |  |  | 2023-02-21 | RECCo | NA | Sarah Jones | Regulatory | BP002 to include LDSO as recipient | Step 180 in BP002 and BPD002 does not include LDSO as recipient of traditional meter details as per the wording of the step or the BRS (BR-MS-024) (Code Drafting Log Reference CDD-29) | Implemented |  | Interim Release 2 | 2023-06-23 | Update BP & BPD to align with BRS and add LDSO as recipient of MTDs Updates to BP & BPD002 Forward migration for consistency | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Metering Service MHHSP-BPD002 Forward Migration BP002 and BPD002 |  |  |  |  | 2023-06-16
MHHS-DIN-101 |  | DI-120 | 2023-02-22 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. (Raised as DI 120) | Closed |  |  |  | Included within CSS validation rule update. DUPLICATE See DIN-172 | No Change | MPAN Ownership |  | MHHS-DES138-Interface Catalogue
MHHS-DIN-102 |  |  | 2023-02-22 | St Clements | 2886 | Madison Layton | Software Provider |  | SCS raised the following under MHHS-DIN-7 "MPRS will reject any PUB-031 inlcuding those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist"" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8)" They have followed up with: Just found the change that corresponds to this one in v4.7 interface catalogue – REG0005 in IF-031. Could this also be added to IF-034 so that we can apply the same validation on MDR updates? | Closed |  |  |  | Proposed Change: Add validation "CSS Registration Request ID [DI-849] is valid for Registration Service", with error REG0005 - "CSS Registration Request ID [DI-849] is invalid or unknown" This mirrors a change made in v4.7 to IF-031, agreed as part of the DAG baseline of v4.7 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-103 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory |  | Confirm that D0381 will continue to be used for updates to MPL address. BP010 & BPD010 currently allow emails, SDEP and other agreed forms can be used by Supplier or UMSO to update this - propose that these artefacts are amended to reflect that the D0381 is to be retained (Code Drafting Log Reference CDD-22) | Implemented |  | Interim Release 1 |  | Amend Steps 10, 21, 22 to explicitly use the D0381 rather than current wording | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-104 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Impact of MHHS on SoLR arrangements | Impact of MHHS on SoLR arrangements - possibly needs an Issue Resolution Group discussion to undertake evaluation & impact assessment (Code Drafting Log Reference CDD-23) | Closed |  |  |  | Extensive discussions have been held with Elexon (DIP Manager) to ensure that there is flexibility within the DIP Design to accomdate varied SoLR scenarios. These involve the existing process(s) around change of BMUnits and the ability to transfer ownership of DIP Market Participants. As the solr process does not involve any mass movement / reassignment of MP Identifiers at the MPAN level the core MHHS design is not impacted by Solr per se. |  | All Areas | [6 empty] | 2023-07-14
MHHS-DIN-105 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Related MPAN Business Rules | 1) IF-019 suggests RMP status can be Created or Operational - proposed this can only be Operational for subsidiary MPAN 2) Add validation rule to IF-019 requiring related MPANs to have consistent classification as domestic or non-domestic (reflecting the existing requirements) 3) Clarify what Registration Services should do when MPANs are related/linked and have different MS/MEM providers - is the IF-019 rejected or the MEM for the secondary MEM auto-deappointed? 4) What happens if the IF-019 fails validation by Reg Service at Step 330 in BP010? Design provides no guidance | Implemented |  | Interim Release 2 | 2023-06-23 | 1. Removed reference to Created in the REG1001 validation rule for IF-019 2. We understand there is no existing validation within MPRS and this is not being amended as a result of MHHS implementation. This would require a wider industry change impacting CSS as Domestic Premise Indicator is managed independently of Related MPANs. 3. It would not be rejected, auto-alignment would pick up the discrepancy at the next daily run and de-appoint the export MS and appoint the import MS. 4. As with other rejected flows, the sending party should investigate the error and re-submit as appropriate. | Data interface correction | MPAN Ownership | Change of Registration Data | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-106 |  |  | 2023-02-23 | SI Design | 2955 | Kate Goodman | Testing | IF Routing | Inconsistency in DES138 for UMSO Routing 00-Introduction logs UMSO as the single routing option for Unmetered Service provision, as there can only be one UMSO related to an MPAN PUB-008 provides UMSC, UMSP and UMSI as options for secondary routing This inconsitency needs to be corrected | Implemented |  | Interim Release 2 | 2023-06-23 | IF-008 - Secondary routing rules updated following review with Avanade (see DIN268) |  | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-107 |  |  | 2023-02-24 | SI Design |  | Simon Harrison | Progamme | Update to definition of DI-301 LLF ID in the ESC Reporting Data Catalogue | Definition of DI-301 in the ECS Reporting Data Catalogue needs to be updated as follows 'The Unique Identifier of a set of Line Loss Factors' | Implemented |  | Interim Release 3 | 2023-07-12 | Update to be made in the ECS Internal & External Reports - Data Catalogue tab against DI-301 LLF ID it should read as 'The Unique Identifier of a set of Line Loss Factors' | Data interface correction | Supporting Docs | Reporting Catalogue | MHHSP - ERI011A - ECS Reports - Internal v5.2 MHHSP - ERI011B - ECS Reports - Enternal |  |  |  |  | 2023-07-14
MHHS-DIN-108 |  |  | 2023-02-27 | SI Design | 2966 | Kate Goodman | Testing | IF Routing | Ref:MHHSP-DES138-Interface Catalogue v4.7, IF-038, PUB-020, PUB-039. Document says that UM is relevant to these messages but UM thinks it is not relevant. Please clarify what the situation is. Raised in review of MHHSP-872 by Power Data. | Implemented |  | Interim Release 2 | 2023-06-23 | Covered by Secondary routing updates (See DIN268), changes to IF-020 and IF-039 routing. No changes were required to IF-038. The design allows for Customer Direct flags to be set for any Data Service/ Metering Service (ie Including unmetered). |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-109 |  |  | 2023-02-27 | SI Design |  | Simon Harrison | Programme |  | Call out box in BP002/BP003 on Linked/Related MPANs needs to be updated as it includes reference to email/SDEP rather IF-019 as shown in BP010 | Closed |  |  |  | Confirmed - the call out box on BP002/003 needs to be updated Duplicate of DIN-64 | No Change | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service
MHHS-DIN-110 |  |  | 2023-02-27 | SI Design | 2983 | Kate Goodman | Testing |  | MHHSP-BP005-Data Processing-v4.6, Step 50-160 UMSDS is referencing Submit Required UTC period level consumption data (Step 50) with a arrow going to Receive UTC period level consumption data (Step 160) but no reference of IF-021 on the connection between both - reference should be added? | Implemented |  | Interim Release 1 |  | On Process map requires arrow to be labelled as IF-021 from step 50 to step 160 | Process model correction | Meter to Bank | Data Processing | MHHSP-BP005-Data Processing
MHHS-DIN-111 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Originally raised as T4-COM-1691 on 15th Sept 2022: "MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days " Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5 (Raised as DI-76) | Implemented |  | Interim Release 1 |  | Updated to 2 working days | Requirement correction | MPAN Ownership |  | MHHS-BRS003-Registration Service requirements
MHHS-DIN-112 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54 (Raised as DI-77) | Implemented |  | Interim Release 1 |  | Added note to clarify | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-113 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? (Raised as DI-78) | Closed |  |  |  | Agreed duplicate of DIN-29 and can clsoe | No Change
MHHS-DIN-114 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | EES does not appear to have been added to the routing rules tables on the interface tabs(Raised as DI-79) | Closed |  |  |  | Already present in v5 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-115 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On IF-050, this includes linked MPANs in it, but I don’t think these would ever be populated as you cannot link MPAN at MPAN creation. So EES would only ever get Linkage updates on the IF-20 Is there any value of having this therefore in IF-050?(Raised as DI-80) | Implemented |  | Interim Release 1 |  | Removed Linked MPANs and Related MPANs from IF-050 and added explanatory note | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-116 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | For IF-025, block B032 it states it is "MPAN Legacy Info (Mandatory where event is [SSCandProfileClass], and for Traditional Meters / Optional for other Meters)" It should just read mandtory for event code [SSCandProfileClass] and nothing else, it should not be optional for any of the other event codes(Raised as DI-81) | Implemented |  | Interim Release 1 |  | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-117 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?(Raised as DI-82) | Closed |  |  |  | Discussed with SCS and confirmed it is a limitation of swagger output but should be array of MPAN followed by array of meters followed by array of MAPs repeated per MPAN. Awaiting confirmation can close | No Change | Metering Changes | IF-005 JSON | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-118 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | In relation to the Sender Unique Reference, which is constructed as: S-<Interface>-<Participant Id>-<Role Id>-<Date>-<Sequence> (hex) I would like to comment as follows: • Why is the Unique Reference simply constructed using elements that are already contained in the message as distinct values? This just means the sender has to construct it and the receiver de-construct it? • Is the sequence number expected to be reset each day ? • It would be much easier and more logical for the Sequence to be a distinct item in the message? • Why is the sequence specified as hex? • Even given the expected large number of messages, and based on it being a number(13) (defined as Sting), a standard sequence number per Participant and Role would provide 9,999,999,999,999. If this is still seen as a limitation then it could simply be built from the date, e.g. 202301190000000001, giving a provision for up to 9,999,999,999 messages PER DAY from the same Participant / Role combination, which still enables a read every 30 minutes from every MPAN(Raised as DI-83) | Closed |  |  |  | This is to send a unique reference and is used for auditing purposes. Please note the length of the Sender Unique Reference has been increased at the request of Avanade in 5.1.1. Examples updated |  | MPAN Ownership
MHHS-DIN-119 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | in swagger hub under IF-002 B907 list the B036 block, this is missing numberOfDigitsCumulativeRegister data item(Raised as DI-84) | Implemented |  | Interim Release 1 |  | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue. Swagger will be updated | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-120 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Inconsistency in naming of data item DI-091 In swagger hub: Number-Of-Digits-Cumulative-Register In interface catalogue IF tabs (E.g. IF-002) : Number of Displayed Register Digits In interface catalogue data catalogue tab: Number Of Displayed Register Digits (Cumulative Register)(Raised as DI-85) | Implemented |  | Interim Release 1 |  | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue and updated YAML accordingly | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-121 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0093 comment raised on 12/01/2023 " D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: "It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42 (Raised as DI-86) | Implemented |  | Interim Release 1 |  | Agreed to provide SEG scenario's in IF-005 Use Case guide. currently under review |  | Metering Changes | Change of Segment | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-122 |  | DI-87 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0084 comment raised on 12/01/2023 following the introduction of IF-019 and respective changes in the latest set of released artefacts MHHSP-BP010-Change of Registration Data -v4.5 "Shows Supplier Mastering Import Export Linkage. BSC CP1558 introduced changes to MPRS for the LDSO to manage this via the DB05. IF-019 should go to LDSO who should then produce a DB05 into MPRS." The process diagrams and requirement spreadsheets have been amended to show MPRS loading DB05 as a IF-019 response. DB05 is not a IF-019 response, it is a request from DNO/iDNO to create, amend or remove a import/export linkage. It does not currently have any capacity to include a IF-019 rejection response to trigger a IF-020 rejection response to DIP. (Raised as DI-87) | Implemented |  | Interim Release 1 |  | SCS reviewing preferred option with LDSO's The following changes would be required to the LDSO overview requirements: MHHS-BR-LD-043.3 LDSO Send Import/Export relationship update LDSO must send accepted Import/Export relationship updates to the Registration Service via the appropriate interface DB05 file or other agreed mechanism BP010B Change of registration data 900 MHHS-BR-LD-043.4 LDSO Send Import/Export relationship rejection LDSO must publish rejected Import/Export relationship updates on the Data Integration Platform using the appropriate interface MHHS-IF-020 to Supplier BP010B Change of registration data 900 On BP-010 for Linked Import/Export MPANs the following would be required: 1. Need to add rejected leg from step 900 to DIP 2. Need to add PUB-020 going from the DIP to the Supplier The BPD-010 will need updating accordingly. | Process Model correction | MPAN Ownership |  | MHHSP-BP010-Change of Registration Data MHHSP-BPD010, MHHSP-BRS005, Traceability Matrix
MHHS-DIN-123 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0083 comment raised on 12/01/2023 following the introduction of a new business rule on MPRS in the latest set of released artefacts MHHS-BR-RS-078 "MPRS cannot control how messages are sequenced at CSS and DSP. IF MPRS waits until the DSP responds before sending the Appointment message this could take hours (as this is a batch process) this will result in a delay in the appointment of the MDR. Sequencing requirements should be placed on CSS & DSP to ensure the correct MDR is appointed based on Effective dates provided from MPRS. However, they may not be necessary due to the way this interface works: The C0200 interface uses the PUT Method, which will replace the data held at CSS. Explicit ending of an Appointment is only required for a future dated appointment, this will be sent as one message with the Old and New MDR appointments. For Same Day or Retrospective the new MDR Appointment will Replace the currently set value. This implicitly ends the previous MDR Appointment. On a CoS, the MDR is linked to a Registration not a Metering Point. The previous MDR will end naturally when the Previous Registration becomes securedInactive. An explicit message to end the MDR appointment on the Previous Registration is not required . MPRS will only send two separate updates to CSS when there is a gap in MDR (SDS) appointments. For Example a change of segment to Advanced and then back to Smart. This would need to happen over a short period to generate two messages that could go out of sequence" The MHHS design team rejected with comment "The MHHS design is based upon what was agreed as part of the R044 consultation. This scenario does not reflect our understanding of how the CSS/DCC/DSP interface will work as set out under R044. " This is how C0200 currently works today and the interface is unchanged in R0044. This will put a signfiicant requirement on MPRS that will reduce time available time for other core MHHS development activities with no benefit to industry.(Raised as DI-87) | Closed |  |  |  | No Change - updated in v5.0 | No Change | MPAN Ownership
MHHS-DIN-124 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0089 comment raised on 12/01/2023 "D-021 was meant to give more detail on how L1-L4 validation should be used and provide more error codes for use. This has not been done as far as I can see Blocking resolution to this T4-COM-1749, T4-COM-1769 and T4-COM-1768" Comment was closed as clarified however none of these items have been resolved and we have no dates as to when they will be. comments blocked that were raised initially on 15/09/22 Comment T4-COM-1749: "The Registration Service, as part of its L3/L4 validation should ensure that there is consistency between the data content of the IF-033 issued to the Service Provider and the [returned] content in IF-034 - if this isn't so then message should be returned to Service Provider using ""MSGStatus Message"" mechanism." Does MPRS only need to validate consistency in the data it loads on the IF-033, not the data that is not loaded" Comment T4-COM-1769: "We need validation rules to be defined for this flow, Does not match IF-031, content of the PUB-034 does not match the IF-031. No Proposed Appointment Found, PUB-034, does not link to any Pending IF031s. Define Validation Rules for PUB-034 The 034 content must match the original if-031 content the 034 must have a corresponding IF031 the 034 has already been received for the IF-031 Generic Standard Validation, MPAN exists valid in ISD ETC" Comment T4-COM-2768: "We need some generic codes for standard validation rules such as: Service/Supplier is valid in ISD MPAN exists in MPRS MPAN is not Disconnected Service/Supplier is Valid in MDD (so CSS doesn’t reject updates)" (Raised as DI-89) | Implemented |  | Interim Release 1 |  | Added RMP status check to IF-034 and refined validation rule notes regarding different values received from IF-033 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-125 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | IF Routing | WOA-0091 comment raised on 12/01/23 D-030 "how routing will work in the DIP has not been updated this information is required for our development" MHHS Design Team has closed as clarified however there is still uncertainty around the DIP routing, and there are not dates provided for when the detailed DIP design will be released. This will clock certain elements of development (Raised as DI-90) | Implemented |  | Interim Release 2 | 2023-06-23 | Secondary routing rules updated following review with Avanade (see DIN268) |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-126 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0092 comment raised on 12/01/23 following more infromation around D-022 being clarified "D-022 Following the work off item being agreed on what is required for an MPAN to be traded - it has now been possible to fully assess the optionality of data items in the interfaces Data items still mandatory in interfaces that must be changed to optional: Annual Consumption (IF-001) Incumbent Service Providers (IF-002, IF-033) Incoming MS/DS (IF-037) These are not required at creation, nor at traded, and therefore could be non existent in MPRS when MPRS generates this outgoing IF messages Blocking resolution of T4-COM-1727 and T4-COM-1735" Closed as clarified however none of the issues listed have been resolved Annual consumption still reads madatory on a CoS for IF-001, the issue is MPRS may not have this data item. The item is not required to reach a status of traded, therefore CSS will accept a CoS on this MPAN without annual consumption being populated, and then MPRS will not be able to provide this data item on the IF-001 that results from the CoS. This must be changed to optional OR the definition on what is needed to be traded should be updated to include annual consumption. Incumbent Service Providers is still mandatory on IF-002 for CoS Again as MS is not required to be traded, CSS will accept a CoS request with or without a current MS, and so MPRS will not be able to provide an incumbent MS in these cases. It must be changed to optional or the definition of what is needed to be traded should include MS. Incoming MS/DS is still mandatory on IF-037, there are numerous reasons an appointment may be lapsed, the only change that would gaurantee a new incoming SP that MPRS could send on this flow is a change or SP (CSERV) scenario. For CoS the supplier may not have sent in new appointments, for DEREG there will be no new appoitnments, for SEG the market segment may have changed but the supplier may not have sent in new appointments, same for change of connection type, and for IMPEXP and RELATED the parent MPAN might not have MS/DS appointed at all so there would be no new appointments for MPRS to populate on this flow. This must be changed to madatory ONLY on CSERV (Raised as DI-91) | Implemented |  | Interim Release 1 |  | Discussed with SCS. Covered by clarification on nullable and interface notes- All these issues are resolved by the Mandatory Nullable Solution. Confirmed Annual Consumption block will only be provided where available in Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-127 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 "DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least "Registered", if no DS is appointed then there is already an appropriate Event Code" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone (Raised as DI-92) | Closed |  |  |  | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-128 |  | DI-93 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0095 comment on 12/01/23 "D-009 This is blocking closure of T4-COM-1730. There is a lack of clarity around the treatment of rejection from CSS, between both R044 and the MHHS design artefacts e.g. MHHs-BR-RS-088.1 and MHHS-BR-RS-079 both suggest MPRS would still load the new MDR record and appoint in MPRS despite a rejection from DCC/CSS. Our assumption would be that we do not load a MDR appointment that is rejected from DCC/CSS and we send the IF-035 rejection to notify the DS/Supply of this. However no clarity on what to do if DCC/CSS rejects a MDR end date on a de-appointment T4-COM-1730 was raiseed on 15/09/22 MHHS Design Team Rejected the comment with a statement this is outside of MHHS Scope. How MPRS treats the MS/DS appointment and how it responds over hte DIP is within MHHS design. The requirements we are enquiring about are already included in the MHHS design documents as in scope also. This is a major blocker to MPRS design on MDR appointment processes (Raised as DI-93) | Closed |  |  |  | Discussed with SCS this is a REC requirement. Agreed no error codes will be received, just use a generic response. | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-129 |  | DI-94 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0086 comment on 12/01/23 following the release of the first draft of IF-050 in the revised interface catalogue artefact "Related MPANs and Linked Import Export are not set at MPAN Creation. EES can get these on the IF020 Remove these blocks from IF-050 as they would never be populated" MHHS design team marked as accepted and changed but the blocks still exist in IF-050, these blocks will never be populated and so should be removed from the IF-050 interface(Raised as DI-94) | Closed |  |  |  | Closed - duplicate of DIN-115 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-130 |  | DI-95 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0088 on 12/01/23 "D-011 & D-050 it is still unclear how LLFC and DUoS Tariff ID will be stored and managed in MPRS. DUoS should be an Alias of LLFC and not have its own data item in MPRS. LLFC will be renamed to DUoS Tariff when the old arrangements have ended. LDSO impacts having to maintain two items which will lead to billing issues" Marked as clarified and closed witih a clarification statement to be issued on tuesday 24th January, this clarification statement was not received. Awaiting clarification(Raised as DI-95) | Closed |  |  |  | Email to Madison to check can close |  | MPAN Ownership
MHHS-DIN-131 |  | DI-96 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 is missing business rules: REG1001 - MPAN [DI-063] is at [REG.RMPStatus] not status Created/Operational. This should apply to IF-025. IF-025 is missing a rule that consent granualiry EFD must not be earlier than supply start date. Consent Granularity EFD must not be prior to current consent granularity EFD The Consent Granularity Energy Direction Domestic Premise Indicator Combination must be valid in ISD(Raised as DI-96) | Implemented |  | Interim Release 1 |  | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-132 |  | DI-97 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 IHD update does not include validation rule 1019, does this mean IHD EFD can be prior to current and effectively cancel out the current IHD status completely, or is it just an error and the rule should be added to interface catalogue for IHD?(Raised as DI-97) | Implemented |  | Interim Release 1 |  | Amendment accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-133 |  | DI-98 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 will not allow a SMSO to be set for a non smart meter "REG1022 - SMSO ID Cannot be set where Market Segment is [Reg.Segement]", would a non smart supplier be able to send a B031 SMSO block, they will need to be able to if they are required to clear an old SMSO by populating SMSO as null(Raised as DI-98) | Implemented |  | Interim Release 1 |  | Added new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements | 2023-03-23
MHHS-DIN-134 |  | DI-99 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 "SSC must be valid in ISD. Rejection reason: REG1044 - SSC must be a valid value in ISD" SSC are not yet populated in ISD(Raised as DI-99) | Closed |  |  |  | Clarified that SSC validation will be based on Frozen MDD. Seperate DIN to cover availability of ISD | No Change | MPAN Ownership |  | MHHSP-EM021 ISD Entity Data Map, MHHSP-DES138-Interface Catalogue
MHHS-DIN-135 |  | DI-100 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Should B032 PC and SSC block on IF-025 only be permitted when theres a traditional meter fitted at the MPAN?(Raised as DI-100) | Closed |  |  |  | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-136 |  | DI-101 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | How is the Green Deal Exists defined. Does this mean there's a green deal linked to the MPAN regardless of dates, does it mean there's a green deal currently active or due to become active, or does it mean there is a currently active green deal assigned to the MPAN? (Raised as DI-101) | Implemented |  | Interim Release 1 |  | Remove Green Deal exists (DI-110) from Data Catalogue and IF-050 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-137 |  | DI-102 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-007 Validation rule "Metering Service [S0.SenderID] holds valid previous appointment then Energisation Status EffectiveFrom Date [DI-034] should be < [REG.App End Date] + 10" The way it's curently written suggests MPRS should accept an IF-007 from the previous appointed MS, event if there ETD was greater than 10 days ago, provided the ES EFD date was less than their ETD + 10. E.g the previous MS could send IF-007 two years later with ES EFD of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then a separate rule should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? Linked to DI-41(Raised as DI-102) | Implemented |  | Interim Release 1 |  | REG1003 validation rule updated in IF-007 to constrain energisation updates to 10 days after the MS appointment period |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-138 |  | DI-103 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-034 Submitted rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD | Closed |  |  |  | Duplicate of DIN-176 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-139 |  | DI-104 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Need clarity on what role code should be used in C0200 for MS and MDR appointments Linked to comment T4-COM-1790 which was accepted as design issue raised but then moved to a work off item "We would like to see some indicative Role Codes and DIP IDs so we can populate development systems with this data " | Closed |  |  |  | Send "MDR" as role code as per Registration requirement. Allocation of DTN MPIDs is a seperate issue | No Change | Registration | Existing EMAR I/F | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-140 |  | DI-105 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 | Closed |  |  |  | Discussed with SCS the IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR. Agreed to close | No Change |  |  | MHHSP-BP003A, MHHSP-BRS003 Registration service requirements
MHHS-DIN-141 |  | DI-106 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 | Closed |  |  |  | RECCo consequential change | No Change |  |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-142 |  | DI-107 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | There currently aren't sufficient rules to ensure that a principal primary MPAN is not also a linked export subsidiary MPAN or that a subsidiary secondary MPAN is not also a principal import linked MPAN. The MHHS design either should accommodate both (would need clarity on how to treat cases where MPANs are BOTH principal and subsidiary) OR new rules should be introduced to prevent this occuring AND cleanse existing cases ahead of migration | Implemented |  | Interim Release 1 |  | Validation rules updated for IF-019 | Missing/incorrect validation rule | MPAN Ownership |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-143 |  | DI-108 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Requirements were uplifted in v4.5 to include logic around market segment on related MPANs MHHS-BR-RS-124.1: Registration Service must, in the case of Related MPANs and following derivation of Market Segment for individual MPANs, update the Market Segment for the Primary MPAN and all the Secondary MPANs based on the following rule: 1. If any MPAN in the Related MPAN Group has a (derived) Market Segment of Advanced, then set the Market Segment for all the MPANs to Advanced and set the Market Segment Valid Flag to "Yes" for all the MPANs This specifically cites related primary/secondary and does not mention linked import/export associations at all. But then another requirement implies maybe it should have done: MHHS-BR-RS-127: Registration Service must , in circumstances where the derived market segment is invalid (and has not been overridden by Linked/Related MPAN logic ) Should MHHS-BR-RS-124.1 have applied to linked import/export associations too or is it intended solely for primary/secondary related MPANs? | Implemented |  | Interim Release 1 |  | This should only apply to Related MPANs. Updated RS-127 | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-144 |  | DI-109 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131 This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to: Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. | Closed |  |  |  | Duplicate See DIN-169 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-145 |  | DI-110 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. | Implemented |  | Interim Release 1 |  | Added L as valid value for DI-979 in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-146 |  | DI-111 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. | Implemented |  | Interim Release 1 |  | Agreed with SCS to reuse STD Error Response Section in IF035 to communicate Lapsed Reason . See DIN-145 for summary of updates | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-147 |  | DI-112 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-008 response block is listed as mandatory, however on disconnection the MPAN is de-energised by MPRS automatically. The supplier cannot de-energise after disconnection on the IF-007, it must be automatic at MPRS as per The de-energisation needs to be communicated on the IF-008 but it is not in response to an IF-007 and so we cannot populate the response block. | Implemented |  | Interim Release 1 |  | Data interface change agreed. Added Interface note to IF-008 to cover forced de-energisation changes by Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-148 |  | DI-113 | 2023-02-10 | St Clements | 2864 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-113 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { "confirmingMpid": "string", --* "registrationId": "string" --*, "updateSucceeded": boolean --* } Suggest that DI-0980 is removed from B066 | Closed |  |  |  | Discussed with SCS and agreed to close - note no error codes returned from CSS so will provide generic error code | No Change |  |  | MHHSP-DES138-Interface Catalogue, JSON, YAML
MHHS-DIN-149 |  | DI-114 | 2023-02-10 | St Clements | 2865 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-114 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 On IF-038 validation "REG1073 - Customer Direct Contract already exists for MPAN [DI-063] for that period" The respective validation rule for this states: If Contract End Date [DI-145] <= Max existing active MS contract end dates [Reg.MAX_DCMS_Enddate], EXCEPT IF requesting MS [S1.SenderID] = Currently Active Direct MS [Reg.CurrentActiveDC_MS_DIPID] AND Contract End Date [DI-145] <= existing active MS contract end date [Reg.CurrentDCMS_Enddate] This rule doesn't fully prevent overlapping appointments as does not cover where the MS is not currently contracted MS and ETD > current ETD which should also be rejected. Think a simpler rule would cover this scenario more fully e.g. If there is an active contracted MS/DS, and the submitting MS/DS does not match then reject And then ETD can be greater or later than current ETD for the currently contracts MS/DS anyway so doesn't need specifying? | Closed |  |  |  | SRO Team do not believe that a change is required. Linked to DIN-554 |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-150 |  | DI-115 | 2023-02-10 | St Clements | 2866 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-115 in our log In some place on IF-038 tab there is reference to a future customer direct contract e.g. "OR requesting MS [S1.SenderID] <> Any future Direct MS [Reg.FutureDC_MS_DIPID] " "extended dates will be subject to checking if another Service Provider has registered a separate Customer Direct Contract covering the same period" - this can only happen if there's a future appointment "AND ALSO removing all future periods which may or may not have been accepted and recorded previously." As there is no Effective From Date included in the flow MPRS will store an Effective From Date of the system date at the time of creation of the customer contract indicator. It will not be possible to set one to start in the future as the IF-038 does not include effective from date. Is this the same understanding as the MHHS Design Team? | Closed |  |  |  | As per DI-149 above SRO Design Team do not belive that any changes are required |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-151 |  | DI-116 | 2023-02-10 | St Clements | 2868 | Madison Layton | Software Provider |  | Just spotted a change in v4.7 and raised in our log as DI-116 Artefact: MHHSP-BP010-Change of Registration Data -v4.7 under MPL and GSP Group amendment section, DB02 has been amended in v4.7 to DB002. DB002 is not correct, DB02 was the correct name For reference the DB flows only ever have one 0 in, there is DB01 (MPAN creation), DB02 (MP updates), DB03 (Disconnection) and DB05 (Import/Export Linkages) | Implemented |  | Interim Release 1 |  | BP010A step 10 flow name change to DB02, BP010B step250,step440, Step560 flow name change to DB02, and update BPD descriptions to DB02. | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-152 |  | DI-117 | 2023-02-14 | St Clements | 2912 | Madison Layton | Software Provider |  | On looking more closely at the validation rules for IF-019 spotted a few issues. IF-019 REG-1061 rule for Related Create event code appears to be written incorrectly. The rule and rejection description don't quite align. Rule: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) are not currently part of an import/export relationship Rejection reason: REG1061 - Prosposed MPAN(s) [DI-073] / [DI-074] are already part of a Related MPAN Relationship Should the rule read: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) is currently part of a related primary/secondary relationship? The rule and descriptions also don't appear to fully align for some in import/export section too - REG1052, REG1055, REG1057 and might need some minor tweaks to correct. | Implemented |  | Interim Release 1 |  | REG1061, 1052 and 1055 rules updated. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-153 |  | DI-118 | 2023-02-14 | St Clements | 2913 | Madison Layton | Software Provider |  | On working on detailed design for Related MPANs, noticed the IF-019 interface is missing a rule that the Secondary MPAN must not be a Primary in another Relationship. You could expand REG1064 to include this as the description sounds like it should have been covered here. Rule: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN Description: REG1064 - Proposed Secondary MPAN [DI-074] is already part of a different MPAN Relationship Could amend rule to: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN OR [DI-074] is already in a relationship as a Primary MPAN | Implemented |  | Interim Release 1 |  | REG1064 validation rule updated | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-154 |  | DI-119 | 2023-02-15 | St Clements | 2919 | Madison Layton | Software Provider | IF-019 validation gap on primary and subsidiary MPAN | On further detailed design we’ve spotted a potential design gap. Currently it is possible to enter a state where an MPAN is both a primary and subsidiary MPAN at the same time (e.g. Primary but also export linked or Secondary but also import linked). The current MHHS doesn't accommodate an MPAN being in both states at the same time. We’ve already looked to add rules to try to mitigate this on DB02/DB05 internal flows but would need additional rules on IF-019 to fully prevent this scenario occurring. Rules we think are required: 1. On receipt of IF-019 with event code RelatedCreate or RelatedAdd, the primary MPAN must not have energy direction of Export 2. On receipt of a IF-019 with event code RelatedCreate or RelatedAdd, any listed secondary MPAN must not in an active Import/Export relationship as the Import MPAN 3. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Import MPAN must not be in an active relationship as the secondary MPAN 4. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Export MPAN must not be in an active relationship as the primary MPAN | Implemented |  | Interim Release 3 | 2023-07-12 | Agreed with SCS that changes to IF-19 tab would be made to support Rules 1 and 4. Validation Rules updated accordingly with new Error codes (REG1067/1068) created to support. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-155 |  | DI-120 | 2023-02-15 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. | Closed |  |  |  | see also DIN-172/173. Included in 5.1 DUPLICATE See DIN-172 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-156 |  | DI-121 | 2023-02-24 | St Clements | 3078 | Madison Layton | Software Provider |  | We have logged a new design issue under DI-121. IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP | Closed |  |  |  | Duplicate of DIN-173 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-157 |  | DI-122 | 2023-02-27 | St Clements | 3090 | Madison Layton | Software Provider |  | New design issue (SCC Ref DI-122) for the IF-005 related to REC CP R0032. The current v5.0 validation in the IF-005 does not include the new validation introduced with REC CP R0032 (R0032 is approved and being implemented in the D0312 this June): NEW REC CP R0032 Validation: V Rejected – ESME ID already exists within MRPS and does not match Removed Meter, Associated Import/Export MSID or Related MPAN W Rejected - MSN relates to a Smart Meter Type and the ESME ID is NULL X Rejected – ESME ID Format is Invalid Y Rejected – Number of Displayed Register Digits is NULL and the MSN relates to a Smart Meter Type Z Rejected – Non-Smart Meter Type with Number of Displayed Register Digits populated AA Rejected – Meter Location is invalid AB Rejected – Non-Smart Meter Type with ESME ID populated AC Rejected – Number of Displayed Register Digits is incorrect IF-005 Validation: V not covered, needs to be added as a Level 5 Validation Rule W is already covered by DI-085 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) X is already covered in DI-085 population notes (Level 4 validation RCP1023 Msg Contains Invalid Valid Value Combination(s)) Y is already covered in DI-091 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) Z is not explicitly covered, suggestion: add to DI-091 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AA is covered in the population notes AB is not explicitly covered, suggestion: add to DI-085 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AC not covered, Suggestion: add the following population note from R0032 to DI-091: Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” Summary Please add the following Changes to the IF-005 to align it with the D0312 validation and maintain the same level of Smart Meter data quality in the Registration Service: New Level 5 Validation rule for DI-085 implementing V from the D0312. ESME ID must be unique within MPRS unless it’s a Linked MPAN where the same Smart Meter can be shared across Linked MPANs New population note for DI-091, only to be included for Smart Meter Types New population note for DI-085 , only to be included for Smart Meter Types New population note for DI-091, Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” | Implemented |  | Interim Release 1 |  | New Validation Rules added to IF doc to ensure full coverage and alignment with CP Error codes described | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-158 |  |  | 2023-02-27 | Elexon | 2908 | Derek Weaving | Central Body | Use of CCCs to categorise the data for future charges | As part of the Performance Assurance Working Group discussions on Supplier Charges, we are exploring the use of CCCs to categorise the data for future charges. It is noted that Settlement Period Quality Indicator referenced in the VAS Method statement is for illustrative purposes and would welcome clarity on the following: · What is the intended process to populate the Settlement Period Quality Indicator in the initial ISD Table? · What would be the process to be involved in those activities to determine the categorisations should additional CCCs be required? | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | This DIN has been moved to Interim Release 5 as it is related to DIN-409 which has an objection raised that is pending a discussion to clarify the solution. Name change and field length have been actioned. Reviewing whether any changes to Settlement reports are required Recommending a change to this ISD Data Item: Settlement Period Quality Indicator to be set as per Appendix 1 of MHHSP_METH007 MDS_Method_Statement v5.0 This data item need to be changed to something like ‘Valid Settlement Period Quality Indicator Set’ and the field size needs to be increased. The data catalugue will need the revised data item and the field length will need increasing from 20 to at least 100. This Item also appears in some interfaces that will need to be updated. This is because it represents a set of SPQIs. The initial intention is to populate as per the table and check if any new SPQIs have been introduced in the baseline design Method Statement that are not covered. If new CCCs are introduced the appropriate flags for each new CCC would need to be agreed. However, it is likely that another dimension to the table below would need to be introduced to facilitate new CCCs. Word 'Illustrative' to be removed and will be updated to say Valid Settlement Quality Indicator Set. Change to be made across all impacted Method Statements. New CCC's will require a Modification to the BSC interface requirement. | Missing/incorrect validation rule | Meter to Bank | Volume Allocation Service | MHHSP-METH006_VAS_Method_Statement MHHSP-METH007_MDS_Method_Statement v5.1 ED021 ISD Entity spec MHHSP-DES138-Interface Catalogue ECS report |  |  |  |  | 2023-07-14
MHHS-DIN-159 |  |  | 2023-03-01 | ENWL | 2994 | Paul Band | Network Business | Interfaces for UMSO | DES-138 Interface Inconsistencies vs BSCP7XX for UMSO Discussions with ENWL have highlighted a number of inconsistencies in the Interface Catalogue when it comes to routing for UMSO's. DIN-106 also refers. UMSO is not listed as a recipient in DES-138 for the PUB-008, but this is in the draft BSCP and should be added to the PUB UMSO is not listed as a recipient in DES-138 for the PUB-020, but this is in the draft BSCP - this is not needed in the BSCP as there are no unmetered Related MPANs UMSO is not listed as a recipient in DES-138 for the PUB-035, but this is in the draft BSCP - view that it is unlikely for this flow ever to be used as the appointment will not trigger any processes to need a subsequent update UMSO Is listed as UMSI, not UMSO in PUB-036 in DES-138 UMSO is listed as UMSC, not UMSO in PUB-018 in DES-138 The IF_LIST tab should be reviewed for consistency | Implemented |  | Interim Release 2 | 2023-06-23 | As with DIN-106, there are inconsistencies in the Interface Catalogue for UMSO routing. This has been compounded by a review of the draft BSCP for UMSO, which has added a number of PUB flows going to UMSO that aren't currently in the catalogue. Covered by updated secondary routing rules (see DIN268) Design to check requirements in BSCP and MHHS BPs and ensure the interface catalogue reflects a consistent approach | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue and possibly related business processes and descriptions E2E001 |  |  |  |  | 2023-06-16
MHHS-DIN-160 |  |  | 2023-03-14 | Ovo Energy | 2862 | David Morley | Supplier | BP009 flow addition | Steps 205 and 210 in BP009 wont be completable in the event that theres no comms. I think the process would be workable if there was an exception route here - see red arrow below. | Implemented |  | Interim Release 2 | 2023-06-23 | Update Steps 205 and 210 in BP009 with "Comms Available" line label add flow from step 205 to step 215 with “Not Commissioned / No Comms” line label | Process Model correction | Metering Changes | Change of Metering | MHHS-BP009 |  |  |  |  | 2023-06-16
MHHS-DIN-161 |  |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 requirement correction | MHHS-METH001-5.4c Please confirm the requirement: “where daily advance records are available [either in the past or future] and less than 90 days months different from the UTC Date requiring a daily advance - use the mean actual Meter advance from the closest [4] weeks for the same Day Type (as defined in ISD).” | Closed |  |  |  | Duplicate of DIN 97. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-162 |  |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 typo | MHHS-METH001-5.5 typo “Where DAEs are required to be calculated the SDS shall use the most recent data a based on the event that triggered the estimation.” | Closed |  |  |  | Duplicate of DIN 98. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-06-16
MHHS-DIN-163 |  | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Conditionality Rule for B037 | It is not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure it is unclear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" | Implemented |  | Interim Release 2 | 2023-06-23 | Updated conditionality rule for Block B037 in IF-001, IF-002, IF-033, IF-036: to show that Either DI-075 (Primary MPAN) or DI-079 (Secondary), and not both, should be populated where MPAN (DI-063 above) is part of a group of Related MPAN. |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-164 |  | DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0093 comment raised on 12/01/2023 "" D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692"" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: ""It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period"" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42" | Closed |  |  |  | "This requirement stands - review with SCS in light of SEG scenario. We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error...". Reviewed with SCS and agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-165 |  | DI-122 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | See separate sheet Duplicate of DIN-157 | Closed |  |  |  | CR required to add rules in line with CP R0032 Added Miscellaneous Data Validation to IF-005 to cover REC CP R0032 validation rules Wrapped up into design teams main CR Doesn't need to be raised by SCS | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-166 |  | DI-77 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54" | Implemented |  | Interim Release 1 |  | Added clarification to REG Notes re Consent and Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-167 |  | DI-78 DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? " | Closed |  |  |  | Agree you can't. Could update 1032 rule for USP? Duplicate see DI-29 | No Change
MHHS-DIN-168 |  | DI-92 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 ""DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least ""Registered"", if no DS is appointed then there is already an appropriate Event Code"" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone | Closed |  |  |  | CR for new functionality. "Already covered by no MS/DS appointed - MPRS would try to align MS/DS with principle and couldn't as there's no registration to align this to. Need an extra check that can only autoappoint if there's a registration to prevent MPRS crashing Maybe one for DRG? Jon at RECCO for consequential change? Agree not to build for this scenario as this would be an edge case and close | No Change
MHHS-DIN-169 |  | DI-109 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to:Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. | Implemented |  | Interim Release 1 |  | Simplified MHHS-BR-RS-131 on when to lapse a SEG appointment | Requirement correction | MPAN Ownership |  | MHHSP- BRS003, MHHS-BR-RS-131 | 2023-03-23
MHHS-DIN-170 |  | DI-110 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. | Closed |  |  |  | Duplicate of DIN-145 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-171 |  | DI-113 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { ""confirmingMpid"": ""string"", --* ""registrationId"": ""string"" --*, ""updateSucceeded"": boolean --* } Suggest that DI-0980 is removed from B066" | Closed |  |  |  | Agreed with SCS being retained but due to optionality may have to populate text e.g. contact DSP. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-172 |  | DI-120 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. | Implemented | 2023-04-27 | Interim Release 1 |  | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-173 |  | DI-121 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP | Implemented | 2023-04-27 | Interim Release 1 |  | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-174 |  | DI-72 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a Submitted MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60" | Implemented |  | Interim Release 1 |  | "Agreed- doc updates MDR can have gaps between DS EFD and MDR EFD" Updated REG1083 validation in IF-034 so that it allows MDR Effective from dates >= SSD/ DS Eff From date/Existing MDR Eff from date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-175 |  | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" | Closed |  |  |  | Duplicate entry | No Change | MPAN Ownership
MHHS-DIN-176 |  | DI-103 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-034 new rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD" | Implemented |  | Interim Release 1 |  | Agreed -doc updates Updated REG1082 to apply for both [SDS-MDRUpdate] and [DSAppSPRepsonse] events in IF-034 | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-177 |  | DI-105 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 " | Closed |  |  |  | "Reason for IF-035 is to trigger when SDScan send the Meter info" & The IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR Agreed with SCS no changes are required, they now understand the context agreed to CLOSE | No Change | MPAN Ownership |  | MHHSP-BP003A
MHHS-DIN-178 |  | DI-106 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | MS missing a requirement to send MS updates to CSS | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 | Closed |  |  |  | Closed as discussed with SCS that this is out of scope for MHHS Programme. | No Change | [7 empty] | 2023-07-14
MHHS-DIN-179 |  | DI-111 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. | Closed |  |  |  | Duplicate of DIN-146 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-180 |  | DI-125 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 the Meter Removal is currently not permitted for a prospective MS Is it possible for the MS to need to remove two meters and replace it with one? In which case meterexchange would only allow them to do part of this process (remove 1 and add 1) but not complete it, so SEG could not complete. Should meter removals therefore be allowed for prospective MS? (REG1019) | Implemented |  | Interim Release 1 |  | Revised REG1019 and added REG1027 for MeterRemoval event in IF-005 | Requirement correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-181 |  | DI-126 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Missing Rule on If-005: MAP EFD must not be > removal date | Implemented |  | Interim Release 1 |  | Added new rule for MeterUpdate and MeterHistoryUpdate events so that MAP EFD must not be > removal date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-182 |  | DI-127 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 On exchange - the MAP and IHD groups are for new installation not removed meter - does this need to be clarified? | Implemented |  | Interim Release 1 |  | New note added to IF-005 to clarify that only the newly installed MAP and IHD information is required on MeterExchange | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-183 |  | DI-128 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-005, IHD EFD missing validation in IF-005 (Between install and removal date) | Implemented |  | Interim Release 1 |  | Covered Release 5.1, IF-005, IHD EFD missing validation added | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-184 |  | DI-129 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-005 incorrect validation rule: REG1010: On event code Meter exchange and Meter Install rule states MAP EFD >= Install date, it should be = not >=" | Implemented |  | Interim Release 1 |  | IF-005: Updated to REG1010 (MAP Eff from date check ) to = install date for MeterInstall and MeterExchange | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-185 |  | DI-130 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | It should not be possible to change MDR EFD once set. Need validation rules to enable MPRS to reject if IF-034 is submitted with current MDR but a different EFD. | Implemented |  | Interim Release 1 |  | Agreed - doc updates Covered by L3/4 validation as per updated Validation rule notes | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-186 |  | DI-131 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031, there is currently not enough validation to ensure on a SEG, that the same SP isn't appointed for the current registration. Need additional validation rule: If scenario SEG and current supplier, then SP must not be current SP. | Implemented |  | Interim Release 1 |  | Agreed - doc updates Updated validation rule Added REG1095 in IF-031 to check different Data Service proposed for SEG appointment | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-187 |  | DI-132 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Supplier inability to appoint MS/DS for Principal and Subsidiary MPAN | Unhappy Path Scenario: Receive IF-031 for MPAN that is both Principal and Subsidiary MPAN at the same time. This will be rejected as per REG1038/REG1039 Supplier will be unable to appoint MS/DS for the MPAN or any related/linked subsidiary MPANS. | Closed |  |  |  | Closed, there is an existing to prevent this scenario happening going forward. Agreed with SCS to raise examples in the Data Cleanse Forum. | No Change | [7 empty] | 2023-07-14
MHHS-DIN-188 |  | DI-133 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031 the rule REG1030 reads [DI0-828] in not a valid UMSO in DNO [DI-108]/[DI-109] This should read LDSO not DNO | Implemented |  | Interim Release 1 |  | Tied up with If-005 rejection description flexibility action Change REG1030 to read: REG1030 - [DI0-828] in not a valid UMSO in LDSO[DI-108]/[DI-109] SC change incorporated into 5.1.1 | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-189 |  | DI-134 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On IF-031, REG1036 is written to only apply to USP when it should apply to all scenarios? ""Proposed MDR Date [DI-836] >= [REG.MPAN_SUP_SSD] However don't think this rule is required at all as this is already covered under the REG1036 rule that MDR Date < DS EFD? Linked to DI-66" | Implemented |  | Interim Release 1 |  | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-190 |  | DI-135 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-034 missing validation rule REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational | Implemented |  | Interim Release 1 |  | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-191 |  | DI-136 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Addition of validation rules to MPRS to restrict Retrospective changes | MPRS does not currently prevent Retrospective changes to DUoS Tariff ID or Connection Type. Should MPRS add new validation rules for these items to restrict Retrospective changes? Please can you update DIN-191 to include Disconnection Date & Export Association. We don't currently have any restriction on how far these data items (and the others in DIN-191) can be back dated. This is a retrospective change through the DB interface and not a Manual Amendment. There are no retrospective periods for the following data items, this means the data items could be changed earlier than the settlement window and cause issues for settlement. There are restrictions that these data items must be within MS/Registration periods where appropriate, but the EFD/SSD could still be years into the past. - MDR EFD, - MS EFD, - DS EFD, - IHD Status EFD, - PC EFD, - SSC EFD, - Energisation Status EFD | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | Internal review has taken place as to whether DUOS Tariff ID updates should be retrospective. SC to create PPT Review Internally & with ScS then agree DRG discussion date. LINKED TO DIN-056 above | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-192 |  | DI-137 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | For If-031, scenario SEG, the business process diagram/requirements only describe the appointment lapsing once reaching it's SSD if no SA is received. If we receive a cancellation we would like to lapse the appointment at that point in time (it cannot become secured active after being cancelled) and not wait until the SSD to do this. | Implemented |  | Interim Release 1 |  | Added new requirements to BRS003, MHHS-BR-RS-24.1 and 58.1 | Design Ambiguous | MPAN Ownership |  | MHHSP-BRS003-Registration Requirements | 2023-03-23
MHHS-DIN-193 |  | DI-138 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | The YAML name for metered indicator (Data Item 127) is meteredUnmeteredIndicator. This is then set to true of false. It isn't clear whether true means it's metered or unmetered due to the naming convention. It should be named meteredIndicator instead to make it clear true means metered, false unmetered. | Implemented |  | Interim Release 1 |  | Updated YAML details in the Data Catalogue for DI-127 Metered Indicator. Updated YAML accordingly Updated data catalogue/ YAML | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-194 |  | DI-1 | 2023-03-15 | St Clements | 4475 | Madison Layton | Software Provider |  | For IF-035 what is Event Code [IMS-SendMTD] intended for? If intended for sending to old MS then this should be done via secondary routing on the original IF-035, not via another separate IF-035 message produced by MPRS with different event code. | Closed |  |  |  | This message is effectively a copy of the DSAppAccepted AND/OR MSAppAccepted but sent to the Incumbent (current) Metering Service to act as a trigger for that MS to send MTDs. This should be created by MPRS. Requirements MHHS-BR-RS-053 and MHHS-BR-RS-019 cover Registration Service sending this. Message to check and close | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-195 |  | DI-76 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Originally raised as T4-COM-1691 on 15th Sept 2022: ""MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days "" Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5" | Implemented |  | Interim Release 1 |  | Agreed doc update Also in Reg Notes tab Updated validation rules and Reg notes Updated REG1037 in IF-031 to 2 workings days and updated REG notes, to align with process and requirements | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-196 |  |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Updates are required to clarify nullable fields | Implemented |  | Interim Release 1 |  | Updates to Interface catalogue includes changes to interfaces and block data items which are present and can be null 1. MHHSP - ERI011A - ECS Reports - Internal v5.1: The data catalogue is the only tab that has been updated 2. MHHSP - ERI011B - ECS Reports - External v5.1: The data catalogue, DIP_Common, MHHS-REP-003 and MHHSP-REP-006 have been updated |  | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue, MHHSP-E2E001 End-to-End Solution Architecture MHHSP - ERI011A - ECS Reports - Internal MHHSP - ERI011B - ECS Reports - External | 2023-03-23
MHHS-DIN-197 |  |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Decision taken to document digital signing of interfaces outside of the interface document. | Implemented |  | Interim Release 1 |  | Remove Z0 and ZI blocks from all interfaces. Signing process will be documented in the Code of Connection document. | Technical corrrection | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue Code of Connection | 2023-03-23
MHHS-DIN-198 |  |  | 2023-03-15 | Large Suppliers |  | Haz Elmamon | Large Suppliers | Complex Meter Site | Clarification on complex meter site, passed down from DAG as part of the work off plan, Haz to gather concerns for discussion at DA. LSC Rep provided information to the issue on 22-Mar-23 | Requires Industry Work Group review | 2023-08-31 | Interim Release 6 | 2023-10-18 |  |  | MPAN Ownership | [6 empty] | 2023-07-14
MHHS-DIN-199 |  |  | 2023-03-23 | BGAS | 3460 | Neil Strange | large Suppliers |  | Participant wishes to see the use of standardisation in the interfactions between the SDS and sub roles MDR PSS | Closed |  |  |  | Closed based on recommendation for programme CR to be raised by the Large Supplier Rep | No Change | Supporting Docs | SDS Validation / Extimation | MHHS-DES138-Interface Catalogue
MHHS-DIN-200 |  |  | 2023-03-24 | CGI | 3489 | Chris Beard | Software Provider | Hierarchy definition for selecting correct register reading in the case of multiple readings for the same settlement period | If there are multiple register readings available for the same Settlement Day, where is the hierarchy defined for selecting which should be used? Is this solely based on Reading Method (i.e. 1. A – Actual, 2. C – Customer, 3. E – Estimated by SDS, 4. S – Estimated by Supplier) or is it dependent on other factors such as the Event Code in the IF-041 ([ReadingRemv], [ReadingInstl], [ReadingEnergisationChg], [ReadingCOR], [ReadingOnSite], [ReadingCOS], [DSEstimate], [SupplierAgreedCOS], [ReadingOverride], [ReadingRemote])? | Closed |  |  |  | Reading methods do not apply to Register Readings - recommendation for DIN to be closed. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-201 |  |  | 2023-03-24 | ESG | 3529 | Patricia Parker | Software Provider |  | IF-033 Validation for population into the IF-034 The receiving party business validation rules state “Each Service Provider will need to determine their own validation criteria when processing Appointment Requests. The list below is intended to cover a number of potential possibilities based on the data items made available, and not to suggest that Service Providers needs or should perform such validations.” But should the DI-143 ‘Service Provider Proposed Appointment Response Code’ not form a valid set list (ENUM Vals) in the Data Catalogue so that all parties are working to the same list of applicable codes, rather than this field being a string with a length of 200 field? | Closed |  |  |  | IF-033 has been updated as part of Interim Release 1 and the ENUM Vals will not be updated this is because we will have dynamic error messages which cannot be enumerated. |  | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-202 |  |  | 2023-03-24 | ESG | 3513 | Patricia Parker | Software Provider | Operational Choreography 60 minute turnaround | Registration Responses in connection with the PUB-31 given the NFS requirement is a 60-minute turn-around time. Within the Operational Choreography there is requirements OPC-140: From our understanding this means that when suppliers receive the PUB_032 from the Reg Service rejecting the appointment Request suppliers then have 60 minutes to re-issue a fresh IF_031 appointment. For example, there is a rejection code for 'CSS Reg ID not known', this would suggest that a party is out of sync and would need investigating especially as in this case, the REG ID would have previously been provided on PUB- 002, DI-849 and CSS is the master of the REG ID and not the Registration Service. | Implemented |  | Interim Release 2 | 2023-06-23 | Added suggested text to Ops Choreography. Suggested text is "It is noted that some requests may require manual work and may be as a result of incorrect appointments from the Supplier. The expectation will be 90% of requests are systemically processed within 60 minutes with the residual being processed by the end of the following working day". | Doc Ref correction | Supporting Docs | Operational Choreography | MHHS_OPC001_Operational_Choreography |  |  |  |  | 2023-06-16
MHHS-DIN-203 |  |  | 2023-03-24 | CGI | 3502 | Chris Beard | Software Provider | mapping of Estimation Reason Codes to estimation Methods | MHHSP-METH001 M-13. Can you provide a definitive mapping of Estimation Reason Codes to estimation Methods? For example, LTV to Method 11. When should an SDS use Estimation Codes such as Opt Out, Comms. Fault. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated METH001 section 7.3 to reflect Estimated Methods to Estimated reason codes | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001 |  |  |  |  | 2023-06-16
MHHS-DIN-204 |  |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | De-energised sites | MHHSP-METH001 M-3. Which estimation Method should an SDS use for de-energised MPANs that would result in an estimation code of ‘De-Energised’? Without a specific Method statement to cover de-energisation, we will end up estimating consumption. | Implemented |  | Interim Release 2 | 2023-06-23 | Added Method 13 to reflect de-energised sites within METH001 and updated section 2.29 on METH002. | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001 |  |  |  |  | 2023-06-16
MHHS-DIN-205 |  |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | Removal of Estimation Reason Code "Disconnected" | Can you confirm that the Estimation Reason Code ‘Disconnected’ will be removed from the table in 7.3? | Implemented |  | Interim Release 2 | 2023-06-23 | Removed "Disconnected" from Table 7.3 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-06-16
MHHS-DIN-206 |  |  | 2023-03-27 | St Clements | 3703 | Anna Davis | Software Provider |  | Within the MHHS-E2E001 - End-to-End Solution Architecture, there is reference to MHHS-E2E003-Physical Interface Specifications in 1.3 References section This should be labelled as MHHSP-DES138-Interface Catalogue | Implemented |  | Interim Release 1 |  | Updated 1.3 reference section | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-207 |  | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Clarity on when agent appointments should become effective | There is ambiguity within the design on when agent appointments should become effective, which means that different participants have a different view on when agent appointments should become active. | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | At the DRG held on 4th August it was agreed that Appointments need to become active in UTC. References to local time removed Old solution: Appointments become active at midnight local time. Participants raised objections against the old solution therefore this DIN went to a DRG on 4th Aug for discussion. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-208 |  | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Registration Service rejection of Legacy messages for an MPAN | Within the existing Migration Design, it is stated that the Registration Service should reject all Legacy messages for a given MPAN once a Forward Migration has been initiated for said MPAN. This would prevent a legacy MOP from sending the relevant legacy flows if they need to change a meter when an MPAN is mid migration. | Closed |  |  |  | Closed following internal review with Design, Migration and Code Team. Agreed that current design will stand in that all legacy messages will be rejected following the point the IF-031 is issued. Reaffirm existing guidance that migration should be timed to avoid any planned work. Unplanned work/change occuring during migration should be communicated using an MHHS IF Message once migration has been completed. | Requirement correction | Migration | Migration | Migration Design Migration Requirement |  |  |  |  | 2023-07-14
MHHS-DIN-209 |  | Design Team | 2023-03-30 | Design Team |  | Sean Cooper | SRO Design Team |  | ~ Level 1/2 Error Code "MSG0000 - Success" Added to Interface Intro Section ~ MSG0018 - Timestamp cannot be future removed and explainatory note added to IF Notes Section of DIP Common | Implemented |  | Interim Release 1 |  | Updated actioned in v5.1.1 of IF Doc. This relates to MSG1008 not MSG0018 as originally given in the design issue. MSG0000 Success added. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-210 |  | Design Team | 2023-03-30 | RECCo |  | Sarah Jones | Consultancy |  | Possible change flagged The original view of the Design Team was that this flag and associated info (ie Is a Customer Direct contract in place, who is the DS/MS with that contract, but not the Eff To Date aka Contract End Date) should be visible to incoming Suppliers, for exactly the reasons you suggest i.e. so that in an incoming supplier could factor the existence of a CDC(s) into their acquisition process / pricing etc. I think we also felt that SP’s who weren’t currently appointed, but may have signed a new CDC should also have the ability to set the flag, as it’s the sites that are part of a CDC, but where that SP isn’t the appointed SP that are the most difficult to coral and manage. The position at the moment is that the existence of a CDC would be shared with incoming Suppliers as part of PUB-002, however this would likely be too late in the process to provide the assistance and support required to an incoming supplier (on all aspects of the sale, contract/price in particular) … … therefore, I think it was also envisioned that information about CDC’s would be available via ECS – so prospective suppliers could check in ECS on the CDC position as part of the other pre-acquisition checks they may undertake. Therefore, I think the decision on exactly what information is shared ‘pre-acquisition’ to participants probably sits with yourselves (RECCo) to finalise as part of your ECS Design / DP Assessment. All information in relation to CDC’s will be passed/made available to ECS via receipt of a copy of PUB-039, so what item(s) are displayed and to what parties I think would get covered off as part of that ECS Design activity. | Closed |  |  |  | Closed, as per discussions with RECCo that no design changes are required. | No Change | [7 empty] | 2023-06-16
MHHS-DIN-211 |  | DI-139 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-009 Event Code is referred to as [CSSDeRegistration] in the population notes and swagger open API spec but then B042 block title references event code CSS Deactivation, B042 should reference CSSDeRegistration. | Implemented |  | Interim Release 1 |  | Update B042 to reference CSSDeRegistration | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-212 |  | DI-140 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | MHHSP-BP007-Disconnection-v5.0 is missing IF-050 being sent out on a change to MPAN/RMP Status | Implemented |  | Interim Release 1 |  | to BP007 and BPD007 Requires a flow from Registration Service to EES (IF-050 to DIP, a Publish Change to MPAN/RMP Status process, a PUB-050 from DIP to EES process Receive Change to MPAN/RMP status) starting at step 70 (disconnection). Plus add new step descriptions to the BPD and amend Step 70 description to include IF-050. | Process Model correction | Metering Changes |  | MHHSP-BP007-Disconnection, MHHSP-BPD007-Disconnection
MHHS-DIN-213 |  | DI-141 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Data item 997 in S1 common block is senderId in swagger hub, but senderDIPID in data catalogue | Implemented |  | Interim Release 1 |  | Update swagger to reflect senderDIPID to align to data catalague | Technical corrrection | Technical Artefact | Swagger | JSON,YAML
MHHS-DIN-214 |  | DI-142 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | REG Notes section Queuing of Prospective Appointments Rule 4 ** Rule 4: If App Scenario = 'SEG' and Supplier ID + Appointment Service Start Date = Existing Supplier ID + Service Start Date > (Service Start Date +2 working days) >> Appointments meeting Rule 4 have missed their opportunity, and will be 'Lapsed' (PUB-035) This rule doesn't make logical sense, needs correcting. What is the intended logic to be applied here? | Implemented |  | Interim Release 1 |  | Update to align with validation rule | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-215 |  | DI-143 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 for event code [MeterRemoval] rule REG1002 Sending Metering Service ID [SO.SenderID] is currently appointed OR held a valid appointment for Meter Installation Date [DI-057] This should read removal date not installation date | Implemented |  | Interim Release 1 |  | Updated validation rule REG1002 in IF-005 for event code [MeterRemoval] to refer to Meter Removal Date (DI-058) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-216 |  | DI-144 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-144 On IF-005 MPRS will validate Either current, queued SEG or previous MS If previous and not within 10 working days will reject with REG1003 If not previous, and not current or queued, will reject with REG1027 MPRS will then validate if install date/removal date is within MS period of ownership If not will reject with REG1019 REG1019 need correcting to also include <ETD to apply for previous MS It’s not possible to get a scenario where the If-005 passes the above rules (REG1003, REG1027 AND REG1019) but fails REG1002. Therefore REG1002 is not needed and will never be sent as a rejection code. (Add to DI-43) | Closed |  |  |  | Agreed with SCS that no further change is required | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-217 |  | DI-145 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | On IF-005 REG1019 should also include validation that the installation/removal date concerned is <=Effective to date (ETD) of MS period of ownership | Implemented |  | Interim Release 1 |  | Updated IF-005 validation rule REG1019 to include validation that the removal/install date must be <=Effective to date (ETD) where the update is being provided by previous Metering Service (using their 10 day window) for MeterRemoval, MeterInstall and MeterExchange events. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-218 |  | DI-146 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 for event codes [MeterExchange] and [MeterRemoval], the rule should not reference DI-056 which is the meter ID in the installation block, it should should referenced DI-053 which is the meterId in the removal block | Implemented |  | Interim Release 1 |  | Rule updated not to reference DI-056 which is the meter ID in the installation block, it now references DI-053 which is the meterId in the removal block | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-219 |  | DI-147 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 - for other event codes removal date must be >= to Install date but for [MeterUpdate] the rule states > meter install date. Should be >= | Implemented |  | Interim Release 1 |  | Update rule for [MeterUpdate] to align to other removal date event codes | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-220 |  | DI-148 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1007 unecessary and will never be triggered, it is already covered under REG1001 cannot submit meter install if MPAN is disconnected | Closed |  |  |  | Valid rule to left in as-is but noted cannot be SIT tested | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-221 |  | DI-149 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In the IF-005 guide it states: "When amending the Installation and/or Removal date of a Meter, a supporting MAP history commencing in line with the revised Installation Date must also be provided. Any additional MAPs should be provided in chronological order, each with a ‘MAP Effective From Date’ greater, by at least one day, than the previous." MPRS will accept if the install/removal date is changing AND the MAP History has not been included, there is no requirement in Interface Catalogue or Registration Requirements to reject if MAP history is not provided. | Closed |  |  |  | Believe covered by MeterHistoryUpdate rules, but hopefully won't be an issue pending agreement on MAP discussion… IF-005 use case guide will be updated with outcome. DRG has agreed to remove MAP history therefore in lieu of this decision, this change will not be required. Closed | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-222 |  | DI-150 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | sarah | Implemented |  | Interim Release 1 |  | Updated wording to match existing validation. Guidance only now provided | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-223 |  | DI-151 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005: Need REG1006 to apply to all event codes, e.g. Meter Update on a change to removal date, will need to check that the removal date does not lead to non unique Meter IDs (overlapping dates) MPRS will reject with REG1006 in this scenario | Implemented |  | Interim Release 1 |  | Added REG1006 validation checks to MeterHistoryUpdate and MeterUpdate events. | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-224 |  | DI-152 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 Interface Note below could be read as MeterUpdate event code can be submitted by previous or prospective MS which is not correct "Only the Appointed Metering Service, and for a small window (10 days) to allow for delayed notification of field activities the previously appointed Metering Service; and an incoming Metering Service with a Prospective 'SEG' type appointment may send an IF-005 and update metering details. The [MeterHistoryUpdate] may only ever be used by the Appointed Metering Service. Interface Design assumes that two separate meters with the same 'Meter ID' cannot be installed at the same time. " | Implemented |  | Interim Release 1 |  | Updated | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-225 |  | DI-153 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | DI-849 CSS Registration Request Id does not have a YAML name in the interface catalogue In the swagger hub, the corresponding name is CSSSwitchID which is misspelt | Implemented |  | Interim Release 1 |  | Updated Data Catalogue to CSSRegistrationRequestID, Swagger to follow | Data interface correction |  | Interface Catalogue Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-226 |  | DI-154 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In MHHSP-BPD007 - Disconnection v5.0, the ordering of the steps are out of order. Steps 140, 145 and 150 are for parties receiving the de-appointment notification from the Registration Service, but this is not sent until Step 155. Step 155 “De-Appoint Services” needs to be before Step 140 “DS De-appointment Notification”. Also Step 145 “Receive De-Appointment Notification” is DIP receiving the de-appointment notification to send on, this needs to be after Step 155 and before Step 140 . The ordering should be: • De-appoint services (155) • Receive De-Appointment Notification (145) • DS De-Appointment Notification (140) • MS De-Appointment Notification (150) | Closed |  |  |  | No plans to change step numbers as long as they are unique | No Change |  |  | BPD007
MHHS-DIN-227 |  | DI-155 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1.xlsb, the validation for REG1003 – “Metering Service ID [S0.SenderID] post appointment update period for MPAN [DI-063] has expired” is currently set to “Metering Service [S0.SenderID] holds valid previous appointment then [System Date] should be < [REG.App End Date] + 10 working days”. Should this be <= to allow for the full 10 days? | Implemented |  | Interim Release 1 |  | Changed to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-228 |  | DI-156 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 - IF-005 has the following error for [MeterExchange] & [MeterInstall]:- “REG1020 - MAP Effective Date [DI-054] cannot take place in the future” Should this validation also be valid for [MeterUpdate] and [MeterHistoryUpdate]? | Implemented |  | Interim Release 1 |  | Added to meter update for removal date. Added to MeterUpdate and MeterHistoryUpdate for MAP effective date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-229 |  | DI-157 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 does not have a rule that the SMSO EFD must not be prior to the latest SMSO EFD. We are implementing this rule with error code REG1019 | Implemented |  | Interim Release 1 |  | We are implementing this rule with error code REG1019 Make consistent with others ( PC and ssc + 1 ). Review IHD and SMSO | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-230 |  | DI-158 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 & IF-005 do not have a rejection code where the IHD is invalid. | Closed |  |  |  | DIP will reject non-valid values - no change to docs required | No Change
MHHS-DIN-231 |  | DI-159 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-005 - There is no validation on Meter Removal date [DI-58]. This should be mandatory non nullable for [MeterRemoval],[MeterExchange],[MeterUpdate], but mandatory nullable for [MeterHistoryUpdate] to allow for reinstating a previously removed meter. Currently in redlined v5.1, this data item is optional and non nullable. | Implemented |  | Interim Release 1 |  | Meter Removal changed to nullable, block conditionality updated | Missing/incorrect validation rule | Metering Changes | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-232 |  | DI-160 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-160 on the interface catalogue DCC Service Flag validation rules are specified in IF-025, but DCC Service Flag is not received in this interface. Needs removing. | Implemented |  | Interim Release 1 |  | not needed rules removed. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-233 |  | DI-161 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 – IF-025, where the event type is [ConsentGranularity] Error Code - REG1019 - Consent EffectiveFrom Date [DI-018] must be within Suppliers period of ownership Test Condition - Consent Granularity EffectiveFromDate [DI-018} must be < [Reg.CurrentSupplierEndDate] if exists Should this be <= as it could be on the end date? | Implemented |  | Interim Release 1 |  | Updated to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-234 |  | DI-162 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Registration Services Requirement MHHS-BR-RS-021 should be amended to: Registration Service must, where more than one Metering Service appointment request is received from the same Supplier for the same MPAN CSS Registration Request ID, and for the same date, take the last received Metering Service appointment (based on the Sender timestamp) as containing the correct information. Any earlier appointments should be lapsed. To allow multiple queued service appointments for the same registration will be overly complex to design, code and test, and is likely to cause confusion and issues in live operation. It is much simpler and cleaner to only allow one queued service appointment at a time, per registration. This would still allow the Supplier to replace a queued appointment that's incorrect. The Supplier could submit further changes once the first change has completed, if there is a genuine case of multiple changes to SP in a short period of time. It would not impact on CoS. Our proposal is to allow one pending queued appointment per registration, so could have a queued appoint on current registration AND queued appointment on CoS registration at the same time. | Implemented |  | Interim Release 1 |  | Updated MHHS-BR-RS-021 to refer to CSS Registration Request ID. Added REG1089 - Subsequent appointment received as an error code in the interface spec | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-235 |  | DI-63 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Original wording:- In the business process diagram for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 Update required:- Please close this design issue as CSS0700 is the correct reference for update of status. | Closed |  |  |  | DUPLICATE OF MHHS-DIN-63 | No Change
MHHS-DIN-236 |  | DI-163 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, 02-DIP-COMMON - R0 response - DI-980 Response Message has been updated in Swaggerhub to be an array, but this is not clarified in Interface Spec. DI-979 Response Code should not be an array. | Implemented |  | Interim Release 1 |  | Added note in Introduction section to confirm that DI-980 can be an array Agreed DI-979 Response Code is not an array | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-237 |  | DI-164 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-034 S0 DI-999 Event Code option of [DSAppSPRepsonse] is misspelt. This is also misspelt in Swaggerhub. This could cause differences between systems and should be corrected to [DSAppSPResponse] | Implemented |  | Interim Release 1 |  | Updated typo in IF-034 DI-999. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-238 |  | DI-165 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation on MS/DS EFD being within permitted advanced period. This is covered under migration document but not implemented as a validation rule for IF-031. MHHS-DEL961 Migration Design Document section 6.1.1: For the purposes of the CoA Migration process, the below business rules should be followed by Suppliers regarding the lead time between the submission date of the IF-031 and the requested effective from date of the Migration. a. An effective from date from Same Day +1 up to a maximum of 28 calendar days (inclusive of the 28th day) in the future is permissible. | Implemented |  | Interim Release 1 |  | 28 Day in advance rule added to if-031 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-239 |  | DI-166 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Requirement MHHS-BR-RS-134 states MPRS must automatically de-appoint the MS & DS when the Market Segment Indicator changes to NO. Is this the intended design? | Implemented |  | Interim Release 1 |  | Removed reference to Market Segment Indicator from the requirement MHHS-BR-RS-134. | Requirement correction | MPAN Ownership | Market Segment | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-240 |  | DI-167 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Current validation on IF-031 Rule REG1037 will mean MPRS will lapse any appointment where the system date is greater than appointment EFD + 2 working days. This means if a SEG change fails, and the supplier tries to resubmit the SEG change, with EFD more than 2 working days in the past, MPRS will immediately lapse the appointment. If there is a need to allow retrospective SEG changes, more than 2 working days after EFD, then the wording will need to be amended to apply to max(EFD+2 working days, MPRS system date on receipt of IF-034 + 2 working days) | Implemented |  | Interim Release 1 |  | Introduction of Lapsed Response Codes and Rules in IF-035 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-241 | RS |  | 2023-02-01 | C&C | 3430 | Graham King | Software Provider | Routing rules via the PUB-018 | IF/PUB-018 message with event codes [AddressChg] and [DUOSTariffIDChg]. According to Interface Catalogue routing rules, these events are not communicated to the LDSO role via the PUB-018. We assume that the assumption here is that because these data items are mastered by the LDSO that all internal LDSO systems share this data. This is unlikely to be the case. DUoS billing systems co-exist alongside other LDSO management software and are often supplied by different vendors. They do not and cannot share data sets. Given this real-world separation, would it be possible to make the PUB-018 message available to LDSO in the list of Secondary Routing paths? The alternative would mean developing communication channels between disparate systems, from potentially different software vendors in order to pass information from one to the other. | Closed |  | Interim Release 5 | 2023-09-20 | Closed - Linked to expected LDSO CR26 on DIP Message Optionality - Update as part of wider CR review | [8 empty] | 2023-07-14
MHHS-DIN-242 |  |  | 2023-04-04 | ESG | 3713 | Patricia Parker | Software Provider |  | How will the Metering Service be kept informed of who the currently appointed Data Service are? On BP003 is shows the Metering Service being a recipient of the PUB_036 when a DS appointment becomes effective, however looking at the routing rules in DES138 it does not show ‘MSSC’ or ‘MSAC’ as being recipients? | Closed |  |  |  | Close - changes to Secondary routing make this DIN Moot - Ref DIN-268 | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-243 |  |  | 2023-04-05 | Change Request | N/A | Sean Cooper | Programme | CR-015 E7/E10 Off Peak Consumption Solution | CR015 - Differential Settlement for E7 / E10 Meters for Smart Opt-out customers | Implemented |  | Interim Release 3 | 2023-07-12 | Changes as agreed at DRG and slides circulated. Updated Method 2 and Method 7 within the SDS method statement (METH001). BR-DS-168 & BR-DS-169 added to BRS001. BR-SU-163, BR-SU-164 & BR-SU165 added to BRS004. BP004 text box amended. Creation of x2 New Data Catalogue Items​ OPD Day​ & OPD Proportion​. Changes to IF-024​ Addition of new Event Code [SN-OffPeakDec]​ & Addition of new B-Block BXXX Off-Peak Declaration​ | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue METH001 BRS001 BRS004 BP004 |  |  |  | CR15 | 2023-06-16
MHHS-DIN-244 |  |  | 2023-04-04 | British Gas | 3874 | Neil Strange | Supplier |  | D0275: Until v0.3 of DES196 was released our understanding was that the D0275 would be retained and it’ use was optional. We are feeding this back on the D-025 consultation but don’t want to lose sight of this. Its removal will impact our billing systems and substantially drive up implementation costs. The baselined IF-021 also does not handle the clock change | Closed |  |  |  | Alignment with D0275 D0275 is not part of of the baseline design requirements. If you require this, it is by mutual agreement between parties. NO change required, only clarification. | No Change
MHHS-DIN-245 |  |  | 2023-04-01 | Avanade/ Design Team |  | Grant Sutcliffe | Software Provider | Transaction ID and Correlation ID increase field length to 60 | Transaction Id Could the length specification of the TransactionId be increased to be a max length of 60. The need for this is to cater for a 16 character length hex value (increasing from current length of 6 characters]. This would ensure that we achieve uniqueness. It will also provide headroom for any length increase in other Transaction Id constituents, such as Role. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: T-041-1234567890123-SUP-20230220-619C1F6967838002 [Length = 50] Example from DES138 spreadsheet: T-006-1234567890123-SUP-20220401-1234CC [Length = 40] Correlation Id Could CorrelationId length also be increased to 60 max length of 60 - for the same reason. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: CI-BP-011-20230222-619E0BD1D1FD9000 [Length = 35] Example from DES138 spreadsheet: CI-BP-011-20230222-1234567890123 [Length = 32] | Implemented |  | Interim Release 2 | 2023-06-23 | Updated DIP Transaction ID and DIP Correlation ID to String 60 in Interim Release 1. The examples have been updated to reflected MHHSP-DES138-Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-246 |  |  | 2023-04-12 | Change Request |  |  | DCUSA | CR-019 Replacement of D0242 D0315 for MHHS | CR019 - Replacement of D0242 D0315 for MHHS | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors) and receivers (suppliers) of the flows has identified the desired flow content and now wish to bring this back to the program to ensure that it can be delivered in readiness for migration. REP-900 and REP-901 added to reporting catalogue. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the supercustomer data from settlement (REP-002/002A). There will be removal of certain data items used in the current process and addition of new data items, making population of the D0242 ‘Supercustomer DUoS Daily Statement’/D0315 ‘Embedded Network Supercustomer DUoS Daily Statement’ impossible in their current format for migrated customers. The “MHHS Design: Reporting and Transition Sub Group” identified the need for a new DIP flow to replace the D0242/D0315 last summer but noted that these flows are under DCUSA ownership and so passed the development of the flow content to DCUSA. More information including the proposed Interface can be found on the collaboration base under CR019 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-247 |  | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Update to the Core Design Interface Catalogue (MHHSP-DES138) is required to include the addition of IF-003 | Closed |  |  |  | Closed captured under DIN-434 as part of migration update review IF-003 defined as part of Migration baseline The structure of the IF-003 will be updated to include ‘Incoming Supplier Details.’ The two new data items within the ‘Incoming Supplier Details’ will be: RevMig Incoming Supplier MPID RevMig Incoming Supplier Effective From Date Business Rules: In the case of Smart Meters undergoing Reverse Migration only, the Registration Service will populate the ‘Incoming Supplier Details’ as part of the IF-003 which is sent to the outgoing MS (via the DIP). This is so the outgoing MS can correctly route the Skeleton D0150 to the new Supplier (which in turn enables the new Supplier to generate a D0367). If the D0205 is not sent to the Registration Service before the IF-003 is issued, the data fields used to confirm the identity of the DC and MOP will be blank; no default values will be populated. In this case, the DC and MOP will need to contact the Supplier to initiate a manual transfer of data. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-248 |  | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Updates to the ISD Entities document (EDI021, v5.0) | Closed |  |  |  | To be picked up as part of Migration IA - - new DIN will be raised as required. |  |  |  | EDI021 |  |  |  |  | 2023-07-14
MHHS-DIN-249 |  | Migration Design | 2023-03-27 | Migration Design |  | Matthew Breen | Programme |  | Discussion around the use of BST/UTC during Migration | Closed |  |  |  | DIN is not specific enough. | [8 empty] | 2023-07-14
MHHS-DIN-250 |  |  | 2023-04-06 | Design Team | 3764 | Steve Weston | Programme | Participant ID 10 digit number | This is related to ticket 3764, to update the Interface Specification to ensure the Participant ID is clearly defined as a 10 digit number [0-9] only, and the examples in the Interface Specification align to this, including where this is used as part of the sender unique reference and the examples shows 11 digits, not 10 digits for Participant ID. | Implemented |  | Interim Release 2 | 2023-06-23 | In E2E001 doc Section 4.2.3.2 Section 4.4.4.2 example code for Sender unique Ref and in Transaction ID Section 4.5.5.3 as above DES138 doc Data Catalogue tab: DI-990 example and DI995 Example DIP common tabl DI995 example and the example JSON block (the above easy to change) ALL the IF tabs the JSON block example the Sender Unique Ref contains Participant ID and in every example its longer than 10. JSON/YAML Files: Update JSON examples where Sender Unique Ref and Transaction ID contain a Participant ID example longer than 10. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 Solution Architecture MHHSP-DES138-Interface Catalogue JSON/YAML files |  |  |  |  | 2023-06-16
MHHS-DIN-251 |  |  | 2023-04-06 | Design Team | 3860 | Steve Weston | Programme | IF-041 Population | This is related to ticket 3860, to update the Interface Specification to provide more clarity / notes on the optionality of B064 and B065 blocks in the IF-041 interface. This is in relation to notes / detail about which blocks are mandatory (from a contractual perspective) versus what should be included in the message if the data exists. | Implemented |  | Interim Release 2 | 2023-06-23 | Updates the notes section of IF-041 in order to provide guidance on the minimum population of B064/B065 blocks. This clarifies "When exchanging readings between parties the design assumes that in the most part this will be the Cumulative Register Reading (Block B064). However, at participants request this message also allows for the exchange of Configurable Register Readings (B065) either alongside a Cumulative Reading or in isolation. For the avoidance of doubt the message must contain at least one B064 record and /or one (or more) B065 records [depending on the number of configurable registers], in order to be considered valid. " | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-252 |  |  | 2023-04-06 | Centrica | 3661 | Neil Strange |  |  | We believe there is a Design Gap at Change of Agent and Change of Supplier for Smart Meters which also impacts Migration. Neither the Registration Service, Metering Service nor Data Service will know how the registers are set up and specifically which are active. Consequently the Data Service will not know which registers to send on the IF-041, nor will there be able to calculate consumption correctly without knowing the register set up. The interface catalogue for IF-041 states in respect to this “B065 Block Below Repeated for each set of Configured Register(s) for each Meter” – we do not believe there is a way to give the DS this information. The supplier will set up the smart meter configuration to enable the registers to capture the usage for certain time periods. There is currently no way for the supplier to inform the DS which registers are active at what time of the day - the DS cannot accurately calculate the consumption breakdown based on the reads when there are multiple registers configured. | Closed |  |  |  | DIN closed, Design Team to send email recommending for a CR to be raised. | [8 empty] | 2023-07-14
MHHS-DIN-253 |  |  | 2023-04-12 | British Gas | 3769 | David Hipwell | Large Supplier | Volumetrics | The latest E2E Functional and Non-Functional Requirements MHHS-E2E Requirements V3 which went to V3 on 16/02/2023 appears to focus on message counts and response times. For example:- During transition all meter points (ca. 31M) will be transition between the old and new services. Therefore assuming a linear migration over the year this would result in the load below, hence services shall be capable of processing the following volumes: - average daily volume of 680,000 - peak daily volume of 2.4M 5.0M - annual volume of 248M 500M Analysis of the flows needs to be categorised across all impacted market participant roles including the DIP. Only then will it have meaning for all parties. The calculation needs to take account of the migration period using the MHHS migration volumes according to date (including REVERSE migration). These should be in both message counts and also sizing (e.g. Gb). And include for a BAU day and also migration days. Whilst some calculations can use the total number of MPANs, to be useful these need show also at perhaps for a million MPANs in each role. Only then will all parties be working on a single set of figures. A line in the sand. The NFRs that exist appear to have moved away from any form of technical calculation towards business process figures. But these figures need to go as an input into technical sizing’s, and should have done for DIP – can these be produced and published ? | Requires Industry Work Group review | 2023-09-13 | Interim Release 5 | 2023-09-20 | Revised volumetric analysis is currently being prepared by the Technical Design Team. Expected to be shared with participants at a future DRG meeting. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-254 |  |  | 2023-04-17 | Siemens | 3044 | Tony Mason | Metering Service | Update of Consent, DPI, etc. | this does surprise me and doesn’t seem to correspond to the routing rules in the Interface Specification. A proposed Data Service is not included in the routing tables for the receipt of a PUB-018, for example. I would therefore expect that if a change to DPI occurs between PUB-033 and PUB-036 the proposed Data Service could only be notified on a revised PUB-033 with the Appointment Scenario set to whatever the original scenario was set to – “SEG”, “CSP”, or “COS”. | Closed |  |  |  | Ref notes on the maintenance of these data items in the Regi Info Section of the I/F document. Prospective SPs are not notified of changes to these data items during their prospective period. If these Data items change then the supplier should re-evaluate the SP they have proposed and change the appointments as required. If an SP takes on a supply with different elements/factors to those suggested by the supplier at appointment this is a contractual issue between the SP and the Supplier. | [8 empty] | 2023-06-16
MHHS-DIN-255 |  |  | 2023-04-17 | Elexon | 3983 | Kate Goodman | Testing | Consumption on De-Energised MPAN (IF-013/IF-014) | ConsumptionOnDeEnergised is an Event Code mentioned in the list of data items but is not present in header where the routing info is held - needs to be added to header | Implemented |  | Interim Release 2 | 2023-06-23 | ConsumptiononDeEnergised event moved from IF-013 to IF-014 and added in routing rules. See also DIN332 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-256 |  |  | 2023-04-17 | Elexon | 4169 | Kate Goodman | Testing | IF-014 Block B067 | DI-015 is mentioned in the header wrt routing but is not present in the message itself. It either needs to be removed from header or added into message. | Implemented |  | Interim Release 2 | 2023-06-23 | Block B067 added to IF-014 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-257 |  |  | 2023-04-17 | Elexon | 4172 | Kate Goodman | Testing | B053 repeating block | B051 is a block which repeats for each combination of Load Shape Criteria (denoted with single chevron to show repeat). B053 is another repeating block which is denoted by two chevrons, implying it is nested below B051. But in fact it also repeats for each combination of Load Shape Criteria. Should this just have a single chevron or is there further information that needs to be added to make its double chevron make sense? | Closed |  |  |  | No change required as there will be multiple B053 in each B051 block. | No Change |  |  | none
MHHS-DIN-258 |  |  | 2023-04-19 | ENWL |  | Paul Band | Network Operator | LDSO use of DIP vs internal for Specific messages | There are a number of requirements in the MHHS-BRS005-LDSO document which state that we must obtain various registration data via the DIP and maintain records accordingly such as: MHHS-BR-LD-001-005, MHHS-BR-LD-024, MHHS-BR-LD-030 and MHHS-BR-LD-034 Extrapolating these into requirements for our own systems suggests that we should build databases/tables to store this data and maintain it The requirement is placed upon us as a party under the assertion that all settlement related data should be exchanged between services and parties via the DIP. However LDSO’s are unique in that their data exchange for their party type is split and is typically split by system under these party types. As a consequence we already communicate directly with MPRS as it is already part of our system architecture as a paid for and created service by LDSO’s. | Closed |  |  |  | CR26 has been raised to covere this LDSOs have been advised to raise a Programme Change Request. Discussion at the DRG of the 27/4/23 did not agree on the development of a New Design Principle, A further workshop with LDSOs needs to take place to discuss alternate options and confirm agreement amoungst all DNOs & IDNO on the receipt of publication | [8 empty] | 2023-07-14
MHHS-DIN-259 |  |  | 2023-04-20 | ESG | 3756 | Patricia Parker | Software Provider | BP003C correction | On BP003C under the CoR section there is a note which states that the readings that pass validation should have Meter Reading Status (J0047) set to ‘T’ and when it has failed set it to ‘F’. However as per the REC the group which houses the J0047 group (032 – screenshot below) should only be present where the Meter Reading Flag (J0045) is set to ‘F’. I have checked DES196 and cannot see that the conditionality for that group is changing in the D0010 therefore I can only assume that the note on the process map is incorrect, and it should be talking about the J0045 value instead. Please can you confirm? | Implemented |  | Interim Release 2 | 2023-06-23 | Modification to Note on process to refer to "Meter Reading Flag (J0045)", modify flow label to step230 to "(Read Flag = "T")" Modification to the process note to advise the J0047 would not be present if the meter reading flag (J0045) is set to "T". It will only be present in case the J0045 is set to "F". | Process Model correction | Metering Changes |  | MHHSP-BP003C-Transfer of Reads |  |  |  |  | 2023-06-16
MHHS-DIN-260 |  |  | 2023-04-20 | CGI | 4167 | Dave Webster | Software Provider |  | Swagger definition does not match DES-138 in version 1.0 or 1.1. | Closed |  |  |  | No specific detail provided, however comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1, therefore closed
MHHS-DIN-261 |  |  | 2023-04-20 | Utiliteam | 4245 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. Configurable Register Reading Date/Time is missing. | Implemented |  | Interim Release 2 | 2023-06-23 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue JSON/YAML Files |  |  |  |  | 2023-06-16
MHHS-DIN-262 |  |  | 2023-04-20 | Utiliteam | 4214 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. B070 for IF-031 is wrong. It contains the word DIP in the Swagger, which is not included in DES-138. | Implemented |  | Interim Release 2 | 2023-06-23 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files |  |  |  |  | 2023-06-16
MHHS-DIN-263 |  |  | 2023-04-21 | CGI | 4203 | Dave Webster | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. DI-122-Profile-Class is defined as an integer, but in DES138 it is defined as a string length 2. Needs to be updated in the Swagger. | Implemented |  | Interim Release 2 | 2023-06-23 | Swagger and Data Catalogue aligned to String 2 for DI-122 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files |  |  |  |  | 2023-06-16
MHHS-DIN-264 |  |  | 2023-04-24 | Elexon | 3946 | Rashmi Radhakrishnan | Central Body | Update to CCC Method Statement | One of my colleague pointed out a typo in the CCC method statement attached, and I would like to draw your attention to it and requesting to make necessary amendments. The CCCID starting from 100 to 107 has Market Segment Indicator as “U” and Connection Type Indicator shown as “W”. We think that, for these line items the Connection Type Indictor need be corrected to “U”. For reference please see below picture and this also aligns with ISD entity spec v5.0 (M2 entity). CCC ID Market Segment Indicator Measurement Quantity Consumption Component Indicator Connection Type Indicator 100 U AI C W 101 U AI L W 102 U AE C W 103 U AE L W 104 U AI C W 105 U AI L W 106 U AE C W 107 U AE L W All 'W's' should be 'U's') | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Method Statement will be updated for "W" to be replaced by "U". Please note: ISD entity M5 file has already been updates to reflect the fact that unmetered supplies have a connection type of "U". | Design Ambiguous | Supporting Docs | Method Statement | CCC Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-265 |  |  | 2023-04-25 | Elexon | 4128 | Rashmi Radhakrishnan | Central Body | Validity of Settlement Period quality indicator data set | ISD entity M5 has a filed Settlement Period quality indicator. Is this the complete valid data set for the field Settlement Period quality indicator? I took this below list from interface catalogue v5.0. A = Actual, E= Estimate (UMS Only) A1,A2,A3, AAE1,AAE2,AAE3,EAE1,EAE2,EAE3 (ADV Only) E0 --> E9 = Estimation Method 1 - 9 ZE = De-Energised ZE1--> ZE3 = Zero Estimation Method 1 -3 but the Advanced Data Service Estimation Method Statement has data flags EA1 till EA13 which is not mentioned in the above list. Also, the ISD entity spec M5 example below shows a different data item that is not in the list at all for Unmetered(104 &105). Is this a mistake? | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Interface document will be updated with the full list of settlement period qulity indicators. | Design Ambiguous | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-266 |  |  | 2023-04-26 | ESG | 3899/ 925 | Patricia Parker | Software Provider |  | If the D0300 process is not changing then we believe that DES196 is incorrect and should show added routes to allow the Supplier to send a D0300 to the Data Service Matt M has confirmed - We are working through the exchange of CoS readings as the code drafting has raised some questions about the extent to which the SDS is involved in the D0300 process. For smart meters, the SDS will not have any use for the billing register readings so D0300 process should not apply, or at most could only be missing the total cumulative. However, it likely will still be required for traditional meters. On that basis, I think we can acknowledge that the D0300 will be retained and SVs created for Supplier to SDS for traditional meters. The process for smart meters is being discussed internally as the SDS does not retrieve tariff register readings. There will be an updated version of DES196 issued in the next few weeks to reflect feedback from the DTN flow part 2 consultation issued in late March which will reflect the retention of the D0300. | Closed |  |  |  | Email comms sent to Patricia confirming the D0300 is a Supplier to Supplier flow. Therefore should there be a need to send readings to the DS, this would be done via a D0010/IF-041 with the correct data flags set in both. Based on this there is no requirement to send D0300 to the DS. Matt M confirmed when finalising DES196 he confirmed this in his comment response to ESG. The MSAG Consequential Change - Switch Meter Read Exceptions v1.0 22.06.23 provides a more comprehensive explanation of the MSAG conclusions. No change required to DES196 | Design Ambiguous | Supporting Docs | Method Statement | MHHSP-DES196- D-Flow and Interface Mapping |  |  |  |  | 2023-07-14
MHHS-DIN-267 |  |  | 2023-05-02 | ESG | 4385 | Patricia Parker | Software Provider | RegX Validation Issue | RegExpression on the DI-148-Annual-Consumption use of DT-016-Decimal-9-3 in the 1.1 swagger spec. This needs to be updated to align with DES-138 example of 123456789.123. Regex should be ^-?[0-9]\d{8}(\.\d{3})?$ instead of ^-?[0-9]\d{7}(\.\d{3})?$ | Implemented |  | Interim Release 2 | 2023-06-23 | Swagger v1.2 has been updated accordingly | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files |  |  |  |  | 2023-06-16
MHHS-DIN-268 |  |  | 2023-05-03 | SRO Design |  | Sean Cooper | SI Design | Secondary Routing | It was always the intention to revisit and revise all of the Secondary Routing configuration as part of DIP Detailed Design. Completion of this exercise has also resulted in some changes to other routing parameters. | Implemented |  | Interim Release 2 | 2023-06-23 | Following discussion with Avanade the Secondary routing short codes have been simplified and the routing of each IF revisited based on these revised short codes. These are shown highlighted in BLUE in the routing section of each of the individual IF pages. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-269 |  |  | 2023-05-03 | St Clements | 4424 | Anna Davis | Software Provider | Swagger Alignment to DES-138 | We have also realised that there are a large number of discrepancies for each interface between the data item name in Swagger vs the YAML name in the Interface Catalogue Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity | Implemented |  | Interim Release 2 | 2023-06-23 | Updated inconsistencies in the Interface 01-Data Catalogue and Swagger. Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-270 |  |  | 2023-05-05 | SRO Design | 4557 | Rob Golding | SI Design | Correlation ID | Provide further clarity on how Correlation ID's work. This will impact numerous artefacts including DES-138 and E2E001 | Implemented |  | Interim Release 2 | 2023-06-23 | DES-138 Interfaces updated to reflect correct 'COPY' property on IF routing tables. updated IF-008, 16, 20, 26, 28, 37, 39 and 50 for this DIN. Added *New to IF-020 showing a new correlation ID is needed to be created for these events, others events needed a COPY of the correlation ID. IF-050 had “No” added to show that a Correlation ID is not required. Updated the E2E001 design document with a more detailed worked example in section 5.4 that details how and where the Correlation ID is populated. | Design Ambiguous | Supporting Docs |  | MHHSP-DES138-Interface Catalogue. E2E001. |  |  |  |  | 2023-06-16
MHHS-DIN-271 |  |  | 2023-05-10 | ESG | 4541 | Patricia Parker | Software Provider | Swagger Alignment to DES-138 | S0 and S1 is Mandatory in DES-138 v5.1.1, but is not marked as mandatory in the Swagger 1.1. Swagger needs to be updated to align with DES-138. | Implemented |  | Interim Release 2 | 2023-06-23 | Swagger 1.2 updated so all SO and S1 blocks are mandatory as per DES-138 | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-272 |  |  | 2023-05-10 | SRO Design | 4656 | Rob Golding | SI Design |  | Required to DIP Channel Publication (v1.2 of the swagger) that will allow DCPs to register webhooks on behalf of their clients | Closed |  |  |  | Duplicate of DIN-375
MHHS-DIN-273 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | New MSN Data Type | MHHS Data Type (DT-029) - for Meter ID / Serial number for DI-053, DI-056 and DI-060 added to DES138 01-Data Catalogue, Swagger updated. | Implemented |  | Interim Release 2 | 2023-06-23 | New Data Type created in Swagger v1.2 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-274 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | Missing YAML in DES-138 - DI-073, DI-074, DI-080, DI-111, DI-112, DI-190-194, DI-300, DI-021, DI-022, DI-060, DI-076 | Implemented |  | Interim Release 2 | 2023-06-23 | Missing YAML names for Data Items confirmed and added to 01 - Data Catalogue Note:All DI's upsated except DI-076 has not required a changed. Other DI chnages not listed are picked up as part of DIN261 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-275 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | DI-093 / DI-120 - Data length 2,000 not 200. | Implemented |  | Interim Release 2 | 2023-06-23 | All additional info data items set to len 2000 in Swagger v1.2, DES138 DI-093/120 length updated in 01-Data Catalogue | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-276 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Classifications | MHHS Data Classification - ensure all columns are populated for Public and Restricted ie, MPAN & Address (removall all NULLS). | Implemented |  | Interim Release 2 | 2023-06-23 | Data Classifications added in v5.2.1 where previously there was no entry ( Column I in the Data Catalogue ) | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-277 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Owners in Data Catalouge | MHHS Data Owner - where there are NULL's, this should be updated so all columns provide an owner, mark as N/A (remove all NULLS). | Implemented |  | Interim Release 2 | 2023-06-23 | Metering Service added as Authoritative Source and MHHS Owner in v5.2.1 of DES138 Data Catalogue for DI-190 to DI-195. Previously there was no entry. | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-278 |  |  | 2023-05-10 | SRO Design | 4590 | Rob Golding | SI Design | Addition of indicator for each IF within DES138 | Please can DES138 Interfaces spreadsheet be updated to provide an indicator against each interface (or is it interface & event code) as to whether it can be opted in/out by a recipient. | Initial Assessment/Updating | Pending CR-29 approval | Interim Release 6 | 2023-10-18 | Design Team to add optionality matrix to DES138 | Design Ambiguous |  | Method Statement | [5 empty] | 2023-07-14
MHHS-DIN-279 |  |  | 2023-05-12 | ESG | 4484 | Patricia Parker | Software Provider | Event Code clarifiction for DS when sending back validated customer read on PUB-041 | The BP005 – Data Processing – Process map shows that when a Customer Own Read has been sent to the Data Service from the Supplier in the IF-041, EventCode = ReadingCoR, the Data Service will perform reading validation and issue the PUB-041 back to the Supplier, in the Read Sharing column of the process map. When the Data Service send back the validated customer own read in the PUB-041, what eventcode will they use and where can I find this documented? The previous response says “There is no IF-041 response, check consumption is as expected in PUB-021” is this correct for Customer Own Reads on Smart meters? The map shows otherwise so please can you confirm if the answer or map is correct and if the map is correct, provide information on what event code will be used. | Closed |  |  |  | This is a query not a DIN. Previous response provided is correct .... There is no IF-041 response, check consumption is as expected in PUB-021” | [8 empty] | 2023-07-14
MHHS-DIN-280 |  |  | 2023-05-12 | ESG | 4552 | Patricia Parker | Software Provider |  | DES196 lists the D0386 (Manage Metering Points) as ‘not impacted’ owned by the REC however BP010 shows that the method of maintaining Related MPANs is via the IF_019 / PUB_020 process. Can you confirm whether the D0386 is going to be removed post- MHHS. If not, could you please clarify what process a Supplier should follow post- MHHS. | Closed |  |  |  | D0386 will not be used post migration to MHHS Regime. Management of MPAN relationships will be under taken using IF-019/IF-020 | [8 empty] | 2023-07-14
MHHS-DIN-281 |  | DI-172 | 2023-05-12 | St Clements | 4446 | Madison Layton | Software Provider | BP003 IF-35 flow | MHHS-BR-RS-053 for the incumbent MS to be notified on If-035 DSAppAccepted where meter is advanced or traditional is missing from BP003 business process diagram and steps. Also updates to BP003 and BPD003 forward migration for consistency | Implemented |  | Interim Release 2 | 2023-06-23 | IF-35 flow from step 85 (if accepted where meter is advanced or traditional to Meter Service (incumbent) and additional step 86 to receive appointment response to BP003, and added step 86 and BR-RS-053 ref and details to step 85 to the BPD003 | Process Model correction | Metering Changes |  | MHHSP-BP003-Change of Service - Data Service, BPD003 Forward Migration BP003 and BPD |  |  |  |  | 2023-06-16
MHHS-DIN-282 |  |  | 2023-05-16 | SIMS | 4821 | Martin Freeman | Software Provider | Status code removal | Status Code is included in the E2E001 design response body (4.4.4.2), when this is HTTP Response code and should be removed as this is defined in the callback response. | Implemented |  | Interim Release 2 | 2023-06-23 | Removed from section 4.4.4.2 from the E2E001 design document as this is not required. This now aligns in Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture |  |  |  |  | 2023-06-16
MHHS-DIN-283 |  |  | 2023-05-16 | SIMS | 4826 | Martin Freeman | Software Provider | ID Capitalisation | ID should be capitalised in all places in the Swagger. | Implemented |  | Interim Release 2 | 2023-06-23 | All JSON names now have capitalised ID fields for Swagger 1.2. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-284 |  |  | 2023-05-16 | SIMS | 4828 | Martin Freeman | Software Provider | HTTP Response Code | HTTP Response code for success should be 201 in E2E001 as per Swagger. | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to E2E001 design document in section 4.4.4.1, 4.5.5.1 and 5.3 to align with Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture |  |  |  |  | 2023-06-16
MHHS-DIN-285 |  |  | 2023-05-16 | Elexon |  | Rob Golding | SRO Design Team |  | Add replay / requeue API for Swagger 1.2 to align with existing E2E001 Design. Add additional information / clarity in the E2E001 for Interim Release 2 to align changes between design and Swagger. | Closed |  |  |  | Duplicate of DIN-374
MHHS-DIN-286 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Issue clarification to Participants through DRG that all ECS Reports will be issues via Pattern B. Update of ECS Report Catalouge to reflect this. | Closed |  |  |  | The ECS reports will be via Pattern A. No change is required to the ECS reports
MHHS-DIN-287 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team | Guidance notes for distribution of ECS reports | Create & Issue guidance document on the distribution of ECS Reports. To Contain : - overview of Pattern B Process - Guidance on population of IF-047 - Update of IF-047 Event Codes | Closed |  |  |  | Solution yet to be defined No longer required as pattern B will not be implemented for ECS reports | [8 empty] | 2023-07-14
MHHS-DIN-288 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Update of Swagger with ECS Reporting Structures | Closed |  |  |  | These interfaces are in place from Swagger 1.1. | [8 empty] | 2023-06-16
MHHS-DIN-289 |  |  | 2023-05-17 | SRO Design Team | 4994 | Rob Golding | SRO Design Team | Interfaces for consumption replay | IF-015 / IF-016 - updates to E2E001 to provide clarification on design pattern. Alignments between DES-138 & Swagger alongside this. | Implemented |  | Interim Release 2 | 2023-06-23 | E2E001 design updated (Section 5.1.7) to provide additional information / clarity on these interfaces in relation to Consumption Replay. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture |  |  |  |  | 2023-06-16
MHHS-DIN-290 |  |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Proposal to change all / subset of ECS Reports to Pattern B | Closed |  |  |  | Duplicate | No Change
MHHS-DIN-291 |  |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | As a result of DIN-290 -- Where should the reporting assets be hosted?? DIP solution specified, but what are the other options are availible. Final solution option to be ratified and documentation updated. | Closed |  |  |  | Not hosted as via Pattern A | No Change
MHHS-DIN-292 |  |  | 2023-05-17 | St Clements |  | Madison Layton | Software Provider | ISD Entity M17 | Change required to ISD Entity M17 to add in Market Segment into the table - otherwise it cannot be used to derive consent values which was its original purposes | Implemented |  | Interim Release 2 | 2023-06-23 | 1. Update Table name to "Consent Granularity Valid Combinations" 2. Added Market Segment as new table column 3. Update table to show all valid combinations | Process Model correction | Supporting Docs |  | MHHSP_EDI021_ISD_Entities |  |  |  |  | 2023-06-16
MHHS-DIN-293 |  |  | 2023-05-17 | Design Team |  | Paul Petitt | SRO Design Team |  | Retrospective DIN raised to ensure that any changes that are made in multiple downstream documents (for example CoCo, DIP Logical Design, DIP Physical Design & DIP Security Design) are reflected / updated in LDP assured documents to ensure e2e design / requirements alignment. This was agreed in a DRG Meeting in March 2023. | Implemented |  | Interim Release 1 |  | design changes to E2E001 End-to-End Solution covering points described in DIN details | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-294 |  |  | 2023-05-19 | ESG | 5030 | Luke Speakes | Software Provider | BP007 PUB009 flow | What I need to know is if the supplier will receive a PUB_009 with the Event code of [CSSDeRegistration] because nowhere on the BP007 process map does it show the supplier receiving the PUB_009 following a deactivation but on DES138 it shows the supplier as being a recipient of this event code. Step 95 (ringed below) shows the supplier as receiving the PUB_009 off the back of the Disconnection (event code [MPANDisconnection]) but then no where else on the process map does it have the supplier receiving a subsequent PUB_009 following the successful deactivation. Additional step required from step 130 (maybe 137?) to show both PUB-009 Mpan Disconnection and PUB-009 Deactivation going to supplier | Implemented |  | Interim Release 2 | 2023-06-23 | BP007 change : There is already a flow from Step 85 to Step 95 for PUB009 for disconnection (no change) But need to Add a new step (137) for Receive Deactivation in Supplier lane from Step 130 for PUB-009 MPan deactivation in BP007 And there is already a PUB-037 flow from step 145 to Supplier step 157 for confirmation (so no change there) Addition of step 137 to BPD007 | Process Model correction | Metering Changes | Disconnection | MHHSP-BP007-Disconnection, BPD007 |  |  |  |  | 2023-06-16
MHHS-DIN-295 |  |  | 2023-05-19 | SIMS | 4821 | Martin Freeman | Software Provider | L1/L2 Error Codes | Error code detail updates in DES-138 for Level 1 and Level 2 validation needs to be clarified | Implemented |  | Interim Release 2 | 2023-06-23 | Updates made to Introduction Tab of DES138 in order to clarify Lev1 vs Lev2 error codes. Design is such that participants should expect error code(s) at either level. Further ammendments could be made following Avanade clarifications. | Data interface correction | Supporting Docs |  | DES138 Data interface Definition |  |  |  |  | 2023-06-16
MHHS-DIN-296 |  |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | It is envisioned that Configuration Management of ISD will largely follow the existing customs, practices and processes as are currently in place for managing MDD changes. However, DIN is required to formally confirm the Owner(s) and allowable update mechanisms (Standard or FastTrack) for each of the new ISD Entities outlined in the DIN. | Closed |  |  |  | This is a Code Drafting issue not a Design / DIN issue. Code drafting team will be covering ISD maintenance processes | [8 empty] | 2023-07-14
MHHS-DIN-297 |  |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | What Participants are recognised in the existing / new ISD Participant tables…. How does this link in with the parties recognised by the DIP (and assigned DIP Roles / IDs …. Or Not) …. In particular how are MDRs referenced in ISD? Does this reference need to identify the ‘type’ of MDR? Also, there is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 | Closed |  |  |  | These issues are covered in Release 3 updates (DIN372 & DIN 070) . ISD updated to confirm participants recorded in M16, a new table M18 "DIP Participant Roles" was added. | [8 empty] | 2023-07-14
MHHS-DIN-298 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Update to UMSDS method statement. | As I understand it, you are advising we should A flag the consumption data (even though it isn’t Actual), until the zero charge code D0388 UMS Inventory is received from the UMSO. Therefore - if we have an inventory, regardless of the energisation status of the MPAN, we always use an A Flag. But as you’ve stated, this means an IF-013 will be issued to us as UMSDS, because there is A data, against a De-Energised MPAN. If this is the design/requirement then it is understood – but I would like to call out that this should be detailed within the UMSDS method statement – so I think a DIN is needed to get this requirement added? | Implemented |  | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-299 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | IF-013 update to include UMSO recipient | Further to this (DIN-298), the cause of this IF-013 being issued can only be that the UMSO has not provided the UMSDS with the correct D0388 UMS Inventory to use. Therefore – the UMSO has a requirement to receive the IF-013 to tell them this. However, the Interface Catalogue has not designed that this will get sent to the UMSO. I think this is a Design Issue too, and also needs a DIN raising so that the IF-013 is provided to the UMSO. | Closed |  |  |  | No this is incorrect. UMSO is not involved with Consumption. If IF-021 submission is rejected this is an issue for the DS (incl. UMSDS) to address and Manage. Any issues regarding the metering onsite/energisation status need to be managed by the DS (incl UMSDS) with their appointing Supplier and Partner Metering Service. |  |  |  | DES138 |  |  |  |  | 2023-07-14
MHHS-DIN-300 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | You are advising a Load Shape will always require the E Flag. But as you say if the MPAN is de-energised, that MDS will reject the IF-021. Is this therefore your answer – that MDS will reject the IF-021, and there is nothing that can be done about that, so we just need to accept we will get those rejections? If so, this isn’t really a satisfactory process, to know rejections will be received in this scenario. Can you just confirm that the solution here is we just need to accept we will get these rejections to the IF-021, which we will then simply ignore? If that is the case – again a DIN needs to be raised to write this into the Design so the process is documented. | Implemented |  | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. See DIN 506 which has updated DES138 to show that IF-014 also contains warnings for MPANs with consumption on de-energised sites. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-301 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | the corrective action on this scenario (DIN-300) occurring will be if/when the UMSO provides the UMSDS with a D0388 UMS Inventory – then the UMSDS will stop using and submitting the Load Shape data. There does not seem to be a mechanism in the Design for the UMSO to be made aware of this issue that would be of their making, so again needs raising as a DIN please. | Implemented |  | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. See DIN 506 which has updated DES138 to show that IF-014 also contains warnings for MPANs on de-energised sites. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-302 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | I’ve pulled together the below table. This covers all the possible scenarios of the UMSDS either having or not having the D0388 UMS Inventory. Combined with whether that D0388 UMS Inventory has load associated data within it. Also combined with whether the MPAN is Energised or De-Energised. Here I’ve listed which Settlement Period Quality Indicator should be used, and where applicable, which Estimation Reason Code should be used. Should this be included in the UMSDS Method Statement and if so, are you happy with the below. In Green are steps we understand. In Red, these remain Unknown to us based on the Design and your answers given. In Orange, these are answered based on your guidance on your email of 28 April – but are not specified in the written Design. | Implemented |  | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-303 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.2.3 - Changes to Data formatting to align with Swagger / DES-138 | Implemented |  | Interim Release 1 |  |  | Technical corrrection | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-304 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.4.3 - Case Sensitivity - additional information added to provide clarity on approach | Implemented |  | Interim Release 1 |  |  | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-305 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 5.1.7 - Additional Detail required for IF-47 / ISD to provide clarity on approach / steps | Implemented |  | Interim Release 1 |  |  | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-306 |  |  | 2023-05-22 | Tym Huckin | 3992 | Tym Huckin | Consultancy | Clarification/examples for DI-101 for BST/UTC cross over period | Further clarity / worked examples for UTC Settlement Date (DI-101) for BST / UTC cross over period. | Closed |  |  |  | This is not a design change it is a Question/Clarification . | [8 empty] | 2023-07-14
MHHS-DIN-307 |  |  | 2023-05-22 | CGI | 5042 | Dave Webster | Software Provider |  | Status code incorrectly included in required, although not in Standard Response Body Type. This is in Swagger 1.2. | Closed |  |  |  | Duplicate of DIN-282
MHHS-DIN-308 |  |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | S0 Block required property | Add required property to all the S0 blocks in the interface definition | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger for all Interfaces to mark 3 fields in the S0 block as mandatory. | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-309 |  |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | Swagger Alignment to DES-138 | Define Transaction ID (DI-990) with no Min Length to align with DES-138. This is DT-014. | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (DIP Transaction ID min length removed) | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-310 |  |  | 2023-05-23 | ELEXON | 5173 | Rob Golding | Central Body | Guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 | Guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 are to be applied (if at all), i.e. does the DIP need to consider the effective period and only accept messages on the production system when the message falls within this period? And if so what date within the message should be used as a check? Or the physical date/time of message receipt? Or doesn’t the DIP need to consider these dates at all and no check needs to be applied? | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | This DIN requires an internal workshop with the Design/Technical team. Holding statement to be added to DES138. Validation rules to be added | [8 empty] | 2023-07-14
MHHS-DIN-311 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-985 / DI987 both String 60. Swagger Min and Max Lengths aligned | Implemented |  | Interim Release 2 | 2023-06-23 | Updates made to DES-138 for Length alignment to 60. Updates to Swagger to remove min length for DI-985 and DI-987. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-312 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-984 / DT-009 needs to be updated to be min 3 / max 5 length. | Implemented |  | Interim Release 2 | 2023-06-23 | Sender Role - change on 01 Data Catalogue DI-984 as per description | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface |  |  |  |  | 2023-06-16
MHHS-DIN-313 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S1 - Sender Timestamp updated correctly (from sent timestamp) in Swagger to align with DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (renamed to Sender Timestamp) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-314 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - Publication ID Min Length updated in Swagger 1.2 to be 6 to align with DES-138 (rather than 7) | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Publication ID Min Length now 7, not 6) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-315 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - DIP Correlation ID should have no min length to align with DES-138 (rather than min length of 1) | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (DIP Correlation ID has no min length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-316 |  |  | 2023-05-25 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, all DT-006 and DT-006N should have min length 10 & max length 10 to be consistent. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated DES-138 01-Data Catalogue to align Data Type and provide consistency to Swagger. Removed DI-095 which is no longer used. | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface |  |  |  |  | 2023-06-16
MHHS-DIN-317 |  |  | 2023-05-23 | St Clements |  | Sean Cooper | SRO Design | B9xx array references within Swagger to be updated within DES138 | Update DES138 IF document to include reference to the B9XX Array references held in Swagger | Initial Assessment/Updating |  | Interim Release 7 | 2024-01-19 | Solution yet to be defined | [8 empty] | 2023-07-14
MHHS-DIN-318 |  |  | 2023-05-23 | REC | 5049 | Jonny Moore | Consultancy | Addition of 'Effective from date' data items to RMP Status (regi) and MP Status in IF-050 | While completing the design phase for EES we noted that the following items with the IF-050 do not have an effective from date. - RMP Status (Registration) - MP Status These items currently have an effective from date held in EES and not including this in the IF-050 would have the effect of removing these items from EES. | Closed |  |  |  | REF DIN-508 | No Change | [7 empty] | 2023-07-14
MHHS-DIN-319 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S0 - EventCode to marked as required to align with DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Event Code marked as required) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-320 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, S1 - Environment (DT-013) should have min length 3 & max length 10 to be consistent with values. | Implemented |  | Interim Release 2 | 2023-06-23 | 01-Data Catalogue DI-991 Environment Set Min to 3. However, string length is 10, so max length should be set to 10 | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface definition |  |  |  |  | 2023-06-16
MHHS-DIN-321 |  |  | 2023-05-23 | St Clements | N/A | Sean Cooper | SRO Design | B005 add to IF-036 | Consider adding B005 to IF-036 so that incoming SP knows who previous SP were | Implemented |  | Interim Release 3 | 2023-07-12 | Added B005 to IF-036 so that incoming SP knows who previous SP were. Updated block name to B005 - Incumbent/Outgoing Service Providers | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-322 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B002 - Incoming Supplier MPID - Swagger aligned to DES-138 for min / max lengths | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Incoming supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-323 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B003 - Ougoing Supplier MPID - Swagger aligned to DES-138 for min / max lengths | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Outgoing supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-324 |  |  | 2023-05-24 | EDF | 4780 | Paul Saker | Supplier | NHHSP-BPM00C- Transfer of Reads on Change of Data Service process steps and messages clarification | NHHSP-BPM00C- Transfer of Reads on Change of Data Service details several process steps and messages related to obtaining and sharing register readings between the gaining and losing suppliers to agree a CoS, and to initiating the missing/disputed reads process defined in the Retail Energy Code where CoS reads are missing or need to be disputed/amended. However, it appears that there is no further detail defined within the Design Artefacts regarding how exactly these process steps would work, including amongst other things: • Timing/Operational Choreography – for example it is not clear exactly when losing and gaining suppliers would be expected to attempt to communicate with the meter, or the timescales for sending data obtained between suppliers. • Data to be included in messages – while BPM003C refers to the inclusion of ‘register readings’ in some of the messages it is not clear which registers should be included for smart meters and non-smart meters – for example whether that should just be the registers on a smart meter that the sending supplier uses for billing, or whether that should be all the 48 time of use registers stored on the smart meter. Additional input from Andrew Margan - Within the code workstream, we believe the Operational Choreography document needs to be updated to reflect SLAs. Without this, we can’t complete the Code drafting. If you disagree, we would appreciate an early heads up, so we don’t look disjointed in front of industry. | Closed |  |  |  | This is not an MHHS Design Issue. D300 / Agree Reading SLAs are defined and set by RECCO. We have replicated the existing 5 day window for capture / submission of a reading(s) all other D300 timescales still apply as per RECC process. Register Readings can only be provided on the D0010 - where this is required [for smart meters] it would replicate the current as is process defined in the current DC BSCP | [8 empty] | 2023-07-14
MHHS-DIN-325 |  |  | 2023-05-24 | CGI |  | Dave Webster | Software Provider | Status Code Missing from MsgBody | In the SubmitEvents StandardResponseBodyType object (SubmitEvents ¦ 1.2 ¦ MHHSPROGRAMME ¦ SwaggerHub), it states that “statusCode” is a required field. Yet its’ definition does not exist in the properties of the object. StandardResponseBodyType: type: object properties: transactionID: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-014-DIPTransactionID' senderUniqueReference : $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-995-SenderUniqueReference' correlationId: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-011-CorrelationID' sentTimestamp: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-003-DateTime' senderId : # the sender of this message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' recipientID : # indended (logical) recipient of the message, i.e sender of the original event message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' DIPConnectionProviderId : # physical recipient of the message (if different to recipient Id) $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' message: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-005-StatusErrorMessage' help: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-019-HelpText' serviceTicketURL: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-018-URL' required: - transactionId - sentTimestamp - senderId - recipientId - statusCode - message - help - serviceTicketURL | Implemented |  | Interim Release 2 | 2023-06-23 | This has now been updated in V1.2 of Swagger StatusCode Added to the ResponseBody. | Technical corrrection | Supporting Docs |  | JSON/YAML files
MHHS-DIN-326 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Changes required to DES-138 / interface catalogue given changes in Migration Design e.g. the addition of interface IF003 and potentially ISD. | Closed |  |  |  | Duplicate of 247 | No Change |  |  | None
MHHS-DIN-327 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | IF-005 User Guide | The IF005 User Guide explains how the IF005 should be populated. We have a request for clarification on whether the IF006 will be populated identically or if the Meter ID in the IF006 will reflect the Modified Meter Id in the IF005. Is IF-005 identical to IF-006, or is it with updated MTD's. | Implemented |  | Interim Release 2 | 2023-06-23 | IF-006 should be a facsimile of IF-005. In the case of change of MSN... MSN field will reference the (old) MSN and Modified MSN will be populated with new/revised MSN. All subsequent flows following the IF-006 will only reference the NEW/REVISED MSN. We further clarified this in a change to the Note(s) section on IF-006. | Data interface correction | Supporting Docs |  | DES138 |  |  |  |  | 2023-06-16
MHHS-DIN-328 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | Operational Chorepgraphy Update: Addition of SLA for RS end appointment data to the CSS | The operational choreography does not include an SLA for the RS to send appointment data to the CSS or the timings by which the CSS and DSP should deliver their roles within the process. These need to be added to the operational choreography for clarity, noting the interaction with CR018. | Closed |  |  |  | RECCo confirmed closure of DIN following review of amendments to the Operational Choreography for CR018. ALL Updates between RS and CSS/DSP are existing interactions, covered by existig SLA's document in RECCO documentation. OPSC document was updated per Recco comment to highlight existing RECCO SLA in this area and to ensure primacy of the RECCO documented timings. | [8 empty] | 2023-07-14
MHHS-DIN-329 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Approach on a business rule where the ERDS does not send a MEM de appointment / appointment for an MHHS migration where the same MEM is being appointed under MHHS arrangements e.g. they have the same MPID. The expectation is that smart and advanced MEMs will use the M role code for the interaction with CSS so from their perspective there should be no change. | Closed |  |  |  | ERDS Interfaces are ouf of scope of MHHS. If a change to ERDS interface is required or efficiencies in its existing operation are possible to align with MHHS Design - this would be a consquential change. | No Change | [7 empty] | 2023-07-14
MHHS-DIN-330 |  |  | 2023-05-25 | Ovo Energy | 5225 | David Morley | Supplier | Long Term Vacant | BSCP504 section 4.15.3 stipulates the criteria via which suppliers can classify sites as Long Term Vacant (LTV). BSCP701 stipulates actions that SDS shall take if the supplier nominates that a site is LTV. However, the criteria that suppliers shall use for classifying LTVs in MHHS is missing. Can you please signpost where the new criteria will be located? | Closed |  |  |  | BSCP is responsible for revising the code specification, there are no changes to design specified. Code team will get in touch with the participant.
MHHS-DIN-331 |  |  | 2023-05-25 | MHHS | 4733 | Martin Freeman | Central Body | Secondary Routing | Secondary routing for IF-013 is specified as being conditional upon the value of DI-015. However, DI-015 (Connection Type Indicator) is a property of a repeating block, and there is no constraint in place to suggest that each element in the repeating block must have the same value for this (or any other) property, in which case multiple rules in the routing table could apply simultaneously. The routing table design seems to suggest that only a single rule should apply at a time and that routing should not be derived by blending multiple rules. If this is so, and a message is received where different elements in the B050 have a different Connection Type Indicator then there is no coherent way to implement this in conformance with the routing table. | Implemented |  | Interim Release 2 | 2023-06-23 | Agree there was a routing contradiction for scenarios/periods where a different connection type was in effect. Interface notes section has been updated to direct the use of 'separate' IF-013 messages in such circumstances. Note also makes clear that repeating B050 blocks are acceptable where other elements (not Connection Type) of the CCC vary over the period to be defaulted. | Design Ambiguous | Supporting Docs | Default Consumption | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-332 |  |  | 2023-05-25 | MHHS | 4750 | Martin Freeman | Central Body | IF-013 Routing | In the routing table for IF-013 all rules are conditional upon S0.Eventcode == [ActivePowerDefaulted], which means that for IF-013 message where Eventcode == [ConsumptionOnDeEnergisedMPAN] there is no routing at all, which means when this message is sent to the DIP it will not be routed anywhere and will simply disappear. That's almost certainly an error. | Implemented |  | Interim Release 2 | 2023-06-23 | Event code [ConsumptionReceivedonDeEnMPAN] has been moved from IF-013 to IF-014. The valid event code list and routing rules have now been updated for both interfaces to reflect the move. v1.2 of Swagger also updated to reflect this change Duplicate of DIN 255 | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-333 |  |  | 2023-05-25 | MHHS | 4760 | Martin Freeman | Central Body | Connection Type Required to Support Routing of IF-014 | All of the routing rules specified for IF-014 are conditional upon DI-015 (Connection Type Indicator). But IF-014 does not have any blocks with this property, which means this message won't get routed anywhere. | Implemented |  | Interim Release 2 | 2023-06-23 | Block B067 - Connection Type Added to IF-014 in order to support routing requirements. Swagger v1.2 updated to reflect this change. (Duplicate of DIN256) | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-334 |  |  | 2023-05-25 | MHHS | 4766 | Martin Freeman | Central Body |  | The routing table for IF-018 specifies roles AMSC, UMSC, UMDC for Secondary routing. There are no such roles in either the DES138 nor the E2E001. | Closed |  |  |  | Secondary Routing Review/Changes have superceded this issue - Ref DIN-268
MHHS-DIN-335 |  |  | 2023-05-26 | British Gas/Engage Consulting | 4640 | Neil Strange/ Haz Elmamoum | Consultancy | Four questions on IF004 | IF/PUB-004 – DIP Common Blocks referencing MHHSP-DES138-Interface Catalogue v5.1.1 As a minimum this needs to be referenced in the supplier requirements MHHSP-BRS004-Supplier Overview and MHHSP-BRS002-Metering Service requirements, but to ensure parties get sight of this we would suggest it needs to be included in a business process map and have associated requirements. For IF-004 to be useful to participants DI-999 – Event Code needs to be elaborated e.g. 1- Installation 2- Removal; 3- Exchange; 4 - Found (Where installed by Gas supplier and Elec Supplier takes ownership) C/M/O rules for DI-192, DI-193 and DI-194 need to be explained in the notes – presumably driven by event code Available is spelled incorrectly (available) for DI-192 and DI-194 there are a couple of angles here – 1) ensuring wider awareness and 2) it seems there is a question mark on the governance here as it is odd a flow has been added but industry does not appear to have been sighted on it especially with no associated referencing in artefacts and no process map, so effectively no one has any idea how it is supposed to be used. Although it was formally agreed not to include and use bilaterally....from a Large Supplier Constituency perspective, my members are keen to ensure design clarity and how flows are to be used or not, regardless of their ad-hoc / bilateral nature. | Implemented |  | Interim Release 4 | 2023-08-16 | Updated BP009 Change of Metering to include the "optional" sending of IF-004 from MS via DIP to Supplier, if changes to Comms Hub need to be notified. Included same updated to BPD009 to reflect new BP steps. Other comments have been addressed previously and are reflected in DES138 IF-004 | Process Model correction | Meter to Bank | IF-004 | BP009 Change oF Metering BPD009 Change of Metering |  |  |  |  | 2023-06-16
MHHS-DIN-336 |  |  | 2023-05-26 | MHHS |  | Rob Topley/ Zak Hussain | SI Design | Requirements clean up in iServer | Process Step No. BP Step ID Process Map wording Interface ID Sender Recipient/Service Traceability Requirement Traceability Method Statement iServer Requirement Name iServer Step name Issues Found BP01 170 BP01 - 170 Send Site Tech Details on Metering Service Request MHHS-RS-LD-012.1 #N/A LDSO170a Send Site Tech Details on Metering Service Request Missing (only on BPD and traceability matrix) BP01 175 BP01 - 175 Receive Site Technical Details D0215 LDSO Metering Services MHHS-RS-MS-037.1 #N/A MET175 Receive Site Technical Details Missing (only on BPD and traceability matrix) BP03B 95 BP03B - 95 Manage SP Appointment Amendment Request Response PUB-035 DIP Supplier MHHS-BR-SU-35.1 #N/A SUP095a - Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP03B 96 BP03B - 96 Manage SP Appointment Amendment Request Response PUB-035 DIP Data Services Metering Services MHHS-BR-DS-11.1 #N/A ESP96 – Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP05 315 BP05 - 315 Issue Reading Data MHHS-IF-041 Data Service DIP MHHS-BR-DS098.2 #N/A DAT315 – Issue Reading Data Missing (only on BPD and traceability matrix) BP05 340 BP05 - 340 Process Reading Data PUB-041 DIP Supplier MHHS-BR-SU047.1 #N/A SUP340 Process Reading Data Missing (only on BPD and traceability matrix) BP05 350 BP05 - 350 Process Reading Data PUB-041 DIP LDSO MHHS-BR-LD009.1 #N/A LDSO350 Process Reading Data Missing (only on BPD and traceability matrix) BP010D 1055 BP010D - 1055 Receive updated Legacy information PUB-026 DIP Central Settlements MHHS-BR-RD-018.1 #N/A ECS1055 Receive updated Legacy information Missing (only on BPD and traceability matrix) All these requirements don’t exist on any requirement catalogues, they’ve only ever been on a BPD document or the traceability matrix (which are essentially the same document). Also, the highlighted traceability has a typo and is on a requirements artefact but is wrong on both the BPD and traceability matrix. | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Requirements have been found in BRS001, BRS004, BRS005, BRS014. Models have the correct steps identified. Unable to identify whats missing, checking with the originator. | Doc Ref correction | Supporting Docs | Supporting Docs | BRS001, BRS004, BRS005, BRS014 |  |  |  |  | 2023-07-14
MHHS-DIN-337 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger alignment to DES-138 | R0 - Response Message Min length updated to align with DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Updated R0 - Response in Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-338 |  |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier | BP003 to be updated to clearly show IF-036 going to both Import & Export supplier | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. BP003 to be updated to clearly show IF-036 going to both Import & Export supplier | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | BP003 from Step 255 relable "PUB-36" flow to Step 260 for the Supplier (prospective/incumbent) to state "PUB-036 for Import & Export Supplier" | Process Model correction | MPAN Ownership | Process Models | BP003 |  |  |  |  | 2023-07-14
MHHS-DIN-339 |  |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier | IF-001 to be updated to be additionally sent to the Export supplier rather than just the import | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. IF-001 to be updated to be additionally sent to the Export supplier rather than just the import | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | See 338 as well, Assuming referring to IF031 not IF001, BP003 from step from step 030 new flow to Supplier (prospectice/incumbent) for PUB-031 for import & Export Supplier to new step ¦Receive Initial Appointment request | Process Model correction | MPAN Ownership | Process Models | BP003 |  |  |  |  | 2023-07-14
MHHS-DIN-340 |  |  | 2023-05-26 | UKPN | 4547 | Neal Medley | Network Operator | ELEX-REP-02/02A report | The reports ELEX-REP-02/02A will only contain aggregated data for A(General LLF Class Import and C (General LLF Class Export). The I/F021 can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/014 Rejected Consumption Data Submission and I/F MDS Defaults Applied to any I/F021 data to ensure you are not using rejected data or are missing I/F 021 data in respect of an MPAN. MDS Method Statement to be updated to reflect | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Updated the below test to Section D within MDS Method statement: 17.4 The I/F021 ‘UTC Settlement Period Consumption Data’ can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/F014 Rejected Consumption Data Submission and I/F ‘Notification of Defaulted UTC Settlement Period Consumption Data’ to any I/F021 data to ensure LDSO’s are not using rejected data or are missing I/F 021 data in respect of an MPAN. | Design Ambiguous | Supporting Docs | Method Statement | MDS Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-341 |  |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | MUM Event not required by MDS | For IF-018 the event [MUMIndicator] is routed to MDS and indicates metered/unmetered. This event is not required by MDS as they can infer this from the Market Segment (Advanced, Smart and Unmetered). DIN raised to remove the routing | Implemented |  | Interim Release 2 | 2023-06-23 | MDS Removed as Always Recipiant for Event [MUMIndicator] on IF-018 Routing rules | Data interface correction | Supporting Docs | IF-018 | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-342 |  |  | 2023-05-26 | UKPN | 5194 | Neal Medley | Network Operator | ELEX-REP-02/02A Consumption data clarification | The intent is that the daily volume on actuals or estimates are the sum of the appropriate consumption data. So when added together they should equal the summed Total of the Settlement Period data (Total Uncorrected Volume) barring any rounding errors. The data is given in MWh to six decimal places (i.e. to the nearest Watt hour). I assume DUoS billing only calculates to the nearest unit so would not expect any rounding errors to impact. The A flags are set out in the ELEX-REP-02/02A are the same as those set out in the CCC table in the VAS Method Statement which is also in the MDS Method Statement. I agree the list in the calculations only are missing the full list of SPQI that are deemed to be actuals as set out in the ELEX-REP-02/02A. DIN raised to correct the calculation | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Updated full list of actuals with the MDS Method Statement. The amended list added to the Method statement: A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6. | Method statement correction | Supporting Docs | Method Statement | MDS Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-343 |  |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | Routing rules table | The routing rules on the IF-037 sheet state that MDS will 'always' receive the DSDeApp event code, however the 'Always' column on the IF_LIST does not state Central Settlements for MHHSP-IF-037. IF list needs updating to reflect that the DSDeApp event always routes to MDS | Implemented |  | Interim Release 2 | 2023-06-23 | Decision taken to remove Recipiants (COLs G,H &I) from the IF_list - as just duplication of information contained within each of the IF spreadsheets. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-344 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B005 Custom Block update Swagger to align with DES-138. Current Metering Service MPID Length removed. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138. Current Metering Service MPID Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-345 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B024 Custom Block update Swagger to align with DES-138. DUOS Min Length removed. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138. DUOS Min Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-346 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design |  | IF-001 - B032 Custom Block update DES-138 to align with Swagger. Update DI-122 (Profile Class) to Integer from String-2. | Closed |  |  |  | DI-122 remains as String 2 for Profile Class to support requirements for enumerations. | Data interface correction | Supporting Docs |  | None |  |  |  |  | 2023-06-16
MHHS-DIN-347 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B035 Custom Block - update Swagger to align with DES-138. Remove min length. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-348 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | IF002 correction | IF-002 - B074 Custom Block. Clarification on DI-091. DES-138 says this is 1 digit to the left of the decimal point. Swagger says 5 to 6. DES-138 to be updated to the correct value. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to be an Integer (1), Min of 1, Max of 1, example of 5. This now aligns with DES-138. | Data interface correction |  |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-349 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Correlation ID Issue IF-006 | Routing Rules in DES-138 do not always correctly identity where Correlation ID == Copy ie, it's missing for IF-005 / IF-006 so this needs to be updated correctly across all interfaces. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated IF-006/IF-008/IF-039/If-028/IF-026/IF-016 routing rules to show use of a "Copy" in Correlation ID (ie copied from the preceeding IF txn pairing) | Missing/incorrect validation rule | Supporting Docs |  | DES138 |  |  |  |  | 2023-06-16
MHHS-DIN-350 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-005 B033 to align Swagger with DES-138 (Postcode removal, mandatory modified meter id) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Postcode removal, mandatory modified meter id) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-351 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B071 to align Swagger with DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-353 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B032 to align Swagger with DES-138 (SSC Min Length should be 4) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated SSC Min Length to be 4) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-354 |  |  | 2023-05-30 | SJW |  | Sarah Jones | Consultancy | Design team confirmation for sending of IF-037 and not IF-037 to losing MEM | Please see below details of a new design query related to the Registration Tranche of Code Drafting. We note that in BP011C there is a process whereby the Registration Service will auto de-appoint / appoint agents for secondary related metering points and linked export metering points as part of their validation. The business process only includes the sending of the IF037 to the Losing MEM and not the IF035. Please could you confirm that this is correct and that in this instance the Losing MEM would not receive an IF-035. If this is the case, we think there should be a change to Metering Service requirements MS-018 and 019 to clarify that where the Losing Metering Service receives an IF-037 with no preceding IF-035 then they should send the MTDs at this point. The alternative would be to include the sending of an IF-035 as well as an IF-037 accepting that these would arrive at a similar time. This would align to the process for managing retrospective MEM appointments where we understand that the Losing MEM would receive both the IF-035 and the IF-037. We also suggest amending MS-008, 008.1, 009 and 009.1 to recognise this nuance as follows: MSA/MSS must obtain Export MPAN de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. MSA/MSS should note this message will be automatically triggered when a change of Metering Service has successfully completed for the linked import MPAN or a new MPAN linkage has been put in place where the [linked import / primary related] MPAN has a different appointed Metering Service. Presumably there is a similar impact on the data service requirements that would need to be considered. | Closed |  |  |  | Solution options discussed with SCS. Closed as covered under DIN 560 |  | Supporting Docs | [6 empty] | 2023-07-14
MHHS-DIN-355 |  | DI-179 | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Number of Register Digits | Revisit and confirm IF-005 Cumulative Digits validation rule against latest version of the CP | Implemented |  | Interim Release 2 | 2023-06-23 | All instances of DI-091 (IF-002,IF005,IF-006,IF-033,IF-036) updated to reflect updated logic. IF-005 validation rules updated also to reflect new guidance. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-356 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B073 - update Swagger to align with DES-138 (consumptionAmendmentSupplierReference max length) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated consumptionAmendmentSupplierReference max length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-357 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B902 - update Swagger to align with DES-138 (supplierConsumptionAmendmentRequests typo update) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated supplierConsumptionAmendmentRequests - remove typo) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-358 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-034 B070 - update Swagger to align with DES-138 (contractReferenceMeteringService max length 10) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated contractReferenceMeteringService max length 10) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-359 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: The method statement states that “The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN on notification of the set-up of that MPAN in MHHS-IF-001.” However, it will be the MHHS-IF-036 Registration Service Notification of Service Appointment & Supporting Info that will initially provide the fact that an MPAN has migrated to Central Settlements. | Implemented |  | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement updated with following text in red: 2.3 The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN within 30 calendar days following notification of the set-up of that MPAN in MHHS-IF-036 'Registration Service Notification of Service Appointment & Supporting information' or MHHS-IF-001 ‘Notification of change of Supplier’. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption |  |  |  |  | 2023-07-14
MHHS-DIN-360 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: 3.3 Where a years’ worth of data, >=75% and <100% of actual UTC Period Consumption data (where Settlement Period Quality Indicator = A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6) has been used to calculate the Annual Consumption, the Annual Consumption Quality Indicator should be set to “1”. | Implemented |  | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement updated with following text in red: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption |  |  |  |  | 2023-07-14
MHHS-DIN-361 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Greater than or equal to change for UTC Period Consumption Data | We need to raise a DIN on the AC method Statement and AC requirements: Likewise 3.6 needs to say greater than or equal to 182 days: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. | Implemented |  | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement updated with following text in red: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption |  |  |  |  | 2023-07-14
MHHS-DIN-362 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Section Name change | Section 5 incorrectly named Section 6 needs to be updated: 6. Transition and Next steps | Implemented |  | Interim Release 4 | 2023-08-16 | Section 6 has been updated to Section 5 within AC Method Statement and old section 5.1The initial Annual Consumption calculation, as set out in section 3.7 above may change, depending on the consideration of the working groups during the MHHS Transition requirements work- has been removed | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption |  |  |  |  | 2023-07-14
MHHS-DIN-363 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Load Shaping Service calculations | We may also need to document how this is calculated by the Load Shaping Service in the first year. I believe Helix have developed a calculation and this would need to go in the Load Shaping Method Statement and be referenced in the AC Method Statement. | Closed |  |  |  | Kevin Spencer to arrange a session with Mike Ceney to discuss solution further. Upon further discussion with Kevin Spencer on 4/8/23 it was confirmed this DIN could be closed as the change is in relationn the AC Method Statement. No changes required to the LSS Method Statement | Method statement correction | Supporting Docs | Method Statement | Annual Consumption Meth 10 |  |  |  |  | 2023-07-14
MHHS-DIN-364 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-035 - B066 - mark as mandatory in Swagger as per DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated so B066 is a mandatory for IF-035 custom block) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-365 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-004 - B093 - update Swagger to align with DES-138 (min Length on commsHubGUID / GPF-GAS-GUID) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated min Length on commsHubGUID / GPF-GAS-GUID) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-366 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 custom block - SSC add min length to align with Swagger | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B032 custom block - SSC add min length to align with Swagger) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-367 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 Profile Class - updated Swagger to be a String to align with DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B032 Profile Class Swagger to be a String to align with DES-138) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-368 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-013 - B049 updated Swagger to align with DES-138 (run Number optional) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B049 Swagger to align with DES-138 (run Number now optional) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-369 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | Switch Cancellation Info Note | Update BP002/003 to add informational note that Registration Cancelations will be processed as soon as they are received by SCS from CSS i.e. Apps Lapsed through switch cancelation sent immediatly not held until Proposed App Date. Also updates to Forward Migration BP002/003 for consistency. Changes to OPC added the following words to OPC_190 in the Activity column (section 4.4) “(including Switch Status Updates e.g. Cancelled)” | Implemented |  | Interim Release 2 | 2023-06-23 | BP-002/003 updated to include new informational Note in Supplier swimlane relating to CSS Switch Cancellations. OPC updated to make it clearer that Secured Active Processing includes Switch Status Update processing. to OPC_190 in the Activity column (section 4.4) “(including Switch Status Updates e.g. Cancelled)” | Process Model correction | MPAN Ownership |  | BP002, BP003, OPC001 Forward Migration BP002 & BP003 |  |  |  |  | 2023-06-16
MHHS-DIN-370 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | IF-005 Update Window Guidance for Prev MS | Change IF-005 and Guidance Doc to allow Meter Updates within 10 day window for previous MS | Implemented |  | Interim Release 2 | 2023-06-23 | New validation rule added to IF-005/MeterUpdate to allow previous MS to submit if within 10 day post appointment period. IF-005 User Guide section 9.3 updated to reflect same. | Missing/incorrect validation rule | Supporting Docs |  | DES138, IF-005 User Guide |  |  |  |  | 2023-06-16
MHHS-DIN-371 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team |  | Review design to ensure only Supression of IHD info for advanced segment and NOT "deactivation" of underlying IHD record. | Closed |  |  |  | Confirmed that IHD details will be retained on Smart to Trad Exchange. Any IHD info present will be suppressed (ie not included in msg) if Segement is Advanced. No change required to documentation. Possible data cleanse issue - Dan T. to raise in Data Forum.
MHHS-DIN-372 |  |  | 2023-06-01 | MHHS | 5298 | Rob Golding | Central Body | Mapping Roles | There is a need to master the mapping of Market Participant Role to DIP Role within the MHHS solution. | Implemented |  | Interim Release 3 | 2023-07-12 | New entity M18 created to show the DIP market roles. Minor corrections to M16 to clarify DIP ID field length. | Other | Supporting Docs | ISD Entities | MHHS-EDI-021-ISD_Entities |  |  |  |  | 2023-07-14
MHHS-DIN-373 |  |  | 2023-06-02 | MHHS | 5272 | Rob Golding | Central Body |  | There is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 | Closed |  |  |  | Duplicate of DIN-297
MHHS-DIN-374 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Message Replay & Requeue functionality | Message replay and requeue functionality needs to be added to the DIP API interfaces, which requires changes to the Swagger / YAML definitions. Detail is required in the E2E design documentation to explain how the message replay and requeue functionality will work. | Implemented |  | Interim Release 2 | 2023-06-23 | Updates to the E2E001 design document to provide detail on how the replay and requeue will work. There are updates to Swagger to support new interfaces for /dip-channel/{id}/replay and requeue respectively. There is also a new MessageRequest Schema that is used to pass data into both of these interfaces. To support these changes, section 4.8 has been updated in the E2E001. | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents |  |  |  |  | 2023-06-16
MHHS-DIN-375 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Interface webhook configuration | Updates require to the pubconfig and webhook config to support per interface webhook configuration, alongside changes to support definition of recipient ID and role ID. | Implemented |  | Interim Release 2 | 2023-06-23 | Updates to the E2E001 design document to provide detail on how the webhook configuration will work, with information related to specific interface changes. There are updates to Swagger to support new interfaces for /dip-channel/{id}/pubconfig (POST and DELETE) respectively to support changes defined in the E2E001 (Section 4.5 and 4.5.1 and 4.5.2have been updated to provide more clarity / information). | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents |  |  |  |  | 2023-06-16
MHHS-DIN-352 |  |  | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Obsfucation Text | What text should be used for data obfuscation ? for things like Boolean fields (True/false) | Closed |  |  |  | Closed as this is already included in section 4.3.2 of the E2E001 design document. | [8 empty] | 2023-07-14
MHHS-DIN-376 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-099 changes required to ensure DES-138 displays the correct YAML name / Swagger aligns to this. | Implemented |  | Interim Release 2 | 2023-06-23 | "Register" spelling in name has been corrected in DI099, and DI-099 name correction for IF041 in DES138 | Data interface correction | Supporting Docs |  | DES138 |  |  |  |  | 2023-06-16
MHHS-DIN-377 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-097 | DI-097 - In DES-138, this is defined as a string (2), but the existing data type is an Integer and this is an Integer enumeration. Need to update this to an Integer in both DES-138 and Swagger 1.2. | Closed |  |  |  | Rejected / closed as enumeration of values requires string (2) therefore this is retained to support buisness requirements. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-378 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. | Implemented |  | Interim Release 2 | 2023-06-23 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. This information has now been added to DES-138 5.2.1. | Data interface correction | Supporting Docs |  | DES138 |  |  |  |  | 2023-06-16
MHHS-DIN-379 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-048 | DI-048 - clarity required on whether this is "meter manufacture make and type", rather than just "meter manufacturer". The first is an existing data type and links to the J number, so providing further clarity / rename would quickly ensure alignment in DES-138 and then subsequently in Swagger. | Closed |  |  |  | Rejected / closed as this was discussed as part of previous work off items and description has previously been approved / accepted as Meter Manufacturer. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-380 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-052 | DI-052 in DES-138 currently has 4 enum values ie, - Active Import, Active Export, Reactive Import, Reactive Export. In MDD there are currently 38 options documented. Discussion around whether ISD Entity 47 should be referenced as the list of values allowed. This can then be aligned / referenced in other other documents ie, EMAR will reference ISD Entity 47. | Closed |  |  |  | Rejected / closed as this was discussed as part of previous work off items. Only 4 values are required in MHHS / DIP, therefore only these values are referenced / used as part of the enumeration to avoid bringing data from existing systems into new systems when this is not required. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-381 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-842 | DI-842 - Confirmation that MDR's have DIP ID's? There has been discussion in various forums to understand whether they do and if not, then this data item needs to be removed in DES-138 and Swagger. | Closed |  |  |  | Rejected / closed as MDR's do have DIP ID's, therefore this value will be retained. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-382 |  |  | 2023-05-06 | Design Team | 4570 | Neil Strange | Supplier | D0010 | In BP003C, at CoS traditional CoRs are transferred between suppliers via D0010. We believe this needs to be used for all meter types - as this will be needed for non-communicating smart and advanced meters – and BP003C needs to be amended accordingly. There is no mention of IF-041 and we do not believe that the DIP is expecting an IF/PUB-041 transaction between suppliers. | Implemented |  | Interim Release 2 | 2023-06-23 | Supplier added as a Primary Recipient in the Routing Rules for IF-041 (DES138) - Supplier initiated Reads. Sending supplier would need to populate the DIP ID of Supplier(s) with whom he wished to share the reading. Working Group specifically decided not to discuss /include COR scenarios for Smart Metered Sites however this is not prevented by the Design - a note to this effect has been added to BP003C for clarity. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue BP-003C Transfer of Readings
MHHS-DIN-383 |  |  | 2023-06-07 | RECCO | 4558 | Sarah Jones | Central Body | Change of Segment Scenario | We cannot find anything in the design artefacts stating that the Metering Service is required to notify metering exchanges for change of segment within 2 WDs. We have found the following: MS-094: MSA/MSS must be able to publish Change of Segment Meter Exchange details and reads via the appropriate interfaces, where it is not formally appointed as the Metering Service but does have an accepted prospective appointment (Appointment Scenario = "SEG"). The MSA/MSS must issue the work update to Registration at the earliest opportunity but within [x] days of completion at the latest. OPC 240: Notification of works to be completed by D+3 Working Days (This should provide time for consumption to be provided using new MTDs ahead of the SF run.) The BP011 references the connection type update being provided by LDSOs within 2 WDs. There is no equivalent for metering updates. Will require DRG confirmation on if the 'x' should be 2 or 3 working days | Implemented |  | Interim Release 3 | 2023-07-12 | Updates to be made inline with DRG recommendation to reflect 3 working days | Process Model correction | Supporting Docs | Business Process Documentation | BP011 - Change of Segment DES138-Interface Doc BRS002- Metering Service Requirements BRS003 - Registration Service Requirements BRS005 - LDSO Overview OPC001 - Operational Choreography MHHSP-DES229-IF005_UseCaseguide |  |  |  |  | 2023-07-14
MHHS-DIN-384 |  | DI-174 | 2023-06-07 | St Clements | 4938 | Madison Layton | Software Provider | IF-038 and IF-039 blocks not the same | Block B020, B021 are not the same across interface IF-038 and IF-039. DI-140 and DI-138 (SP DIP ID) are in IF-039 but not in IF-038. Understanding was that with the DIP change that all data items in block are mandatory, the blocks were to be consistently defined across all interfaces. If extra DIP ID DI-138 and DI-140 data items are included in IF-038 then we need a new REG rejection code to allow us to reject where DIP ID is not the same as the sender DIP ID. Alternative is to separate the DI-140/DI-138 into their own blocks included on the IF-039 interface only. | Implemented |  | Interim Release 3 | 2023-07-12 | Block data items were aligned in release 2. New validation rule on IF-38 add to ensure that Sender ID matches MS/DS CDC ID. New Error code REG1076 added to support validation rule. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-385 |  |  | 2023-06-07 | Design Team |  | Steve Weston | SI Design | Correlation ID | S1 Common Block - Correlation ID is mandatory in Swagger, but Optional in DES-138. Swagger should be updated to align. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated S1 Common Block, Sender Correlation ID in Swagger, as this is Optional in DES-138 to support business process and requirements. | Technical corrrection | Supporting Docs |  | JSON/YAML documents |  |  |  |  | 2023-06-16
MHHS-DIN-386 |  | DI-179 | 2023-06-07 | St Clements | 5258 | Madison Layton | Software Provider | Register Digits | REC Change R0102 has been approved by industry to amend the number of display digits validation Where the Meter Type is S1 the Number of Displayed Register Digits value must be either 6 or 5 Where the Meter Type is S2A, S2AD, S2ADE, 2ADF, 2ADEF, 2AEF, 2AF, S2B, S2BD, S2BDE, 2BF,2BDF, 2BDEF or 2BEF the value must be “5”. Where the Meter Type is prefixed with “S2C” the value must be “6”. Where the Meter Type is 2CDEF, 2CF, 2CDF or 2CEF the value must be “6” REG1097 validation on the IF-005 needs correcting with this change, and the population notes for data item DI-091 across multiple interfaces also needs correcting | Closed |  |  |  | Duplicate of Register Digit DIN-355 listed above | Data interface correction | Supporting Docs | Interface Catalogue | Lis
MHHS-DIN-387 |  | DI-180 | 2023-06-09 | St Clements | 5269 | Madison Layton | Software Provider | Uplift metered indicator requirements | There are elements in the requirements that suggest that metered indicator would trigger a change to Market Segment. E.g. MHHSP-BP011-Change of ConType andor Mkt Segment-v5.1 Step 102 MHHSP-BPD011 - Change of Con Type or Market Segment v5.0 Step 102 Which states if there is a change to market segment RS would need to re-evaluate the market segment And MHHS-BR-RS-124 which include in brackets: Change of Connection Type (Change of Unmetered Indicator) MPRS will assess Market Segment against the ISD entity M7 which does not include Metered Indicator. Therefore a change in Metered Indicator in isolation of any other changes to data items in the M7 table/Related MPANs/Linked MPANs, will not trigger a change to Market Segment. As it will not trigger a change MPRS will not re-evaluate Market Segment base on a Metered Indicator change alone. The requirements need uplifting to reflect. | Closed |  |  |  | Closed as discussed and agreed with SCS. | No Change
MHHS-DIN-388 |  |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | IF-036 Custom Routing Rules | Following discussions with SCS agreed that for reasons of complexity it would be better to adopt Primary rather than secondary routing to IF-036. New Requirement created for REGS to undertake the Primary Routing of IF-036. | Closed |  |  |  | Ref DIN-507
MHHS-DIN-389 |  |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | Appointment Start Times | Do we need a formal validation Rule to check that Appointment Start times are referenced as Midnight Local ? Issue raised numerous times with SCS. Waiting for SCS to confirm their position. | Closed |  |  |  | CLOSED - DUPLICATE OF DIN-207 ABOVE
MHHS-DIN-390 |  |  | 2023-06-13 | Siemens | 5534 | Tony Mason | Metering Service Provider | IF/PUB-018 | There appears an inconsistency in the Business Process Map, BP010, and the routing rules for the IF-018 where the Event Code = DUOSTariffIDChg. This information is confirmed to SPs on the IF/PUB-036 and would then be updated where there is a change on the 018 according to the Secondary Routing Rules. This notification is absent on the process diagram. Could you confirm the position and update the documentation accordingly? | Implemented |  | Interim Release 4 | 2023-08-16 | Update BP010B to show Data Service and Metering Service receiving PUB-018 for DUoS Tariff ID updates in line with the routing rules in DES-138. Update BPD010 process description to includes steps to recieve PUB-018 for Data Service and Metering Service. | Process Model correction | Meter to Bank | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-391 |  | DI-182 | 2023-06-13 | St Clements | 5304 | Madison Layton | Software Provider | IF-019 validation gap on principal and subsidiary MPAN | IF-019 is missing validation rules to ensure an MPAN is only listed once in the IF-019, need rules to ensure the sender cannot repeat same Subsidiary MPAN twice in the repeating B090 block, and cannot list the same MPAN as both Principal and Subsidiary in the same IF-019 message | Implemented |  | Interim Release 3 | 2023-07-12 | Created x2 new rules to prevent duplicate MPANS within repeating B90 groups within a single message. Error Code REG1059 created to support validation checks | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-392 |  |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Consent Fields | Raised by SCS. B068/DI-017/DI-018 - This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block B068 updated to be "must be provided" for smart meters. Data items set to mandatory non-nullable. | Implemented |  | Interim Release 2 | 2023-06-23 | Block text updated to show mandatory if smart meter present, and DI-017/D-018 updated to be mandatory non-nullable (applies to IF-026 only) | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-393 |  | DI-181 | 2023-06-13 | St Clements | 5274 | Madison Layton | Software Provider | De-appointment and re-appointment date order | MHHS-BR-RS-128.4 & MHHS-BR-RS-128.5 covers the requirement for MPRS to ensure MS/DS are aligned across Related/Linked MPANS, and where they are not to de-appoint the MS/DS and appoint the correct MS/DS. The de-appointment requirement specifies to set MS/DS ETD to D+1 and the appointment to set the MS/DS EFD to D+2. Why do we need to apply the de-appointment and re-appointment in the future? Would we not be better to use the previous day (D-1) for the de-appointment MS/DS ETD and the current day (D) for the appointment EFD? | Closed |  |  |  | Can Close and SCS have agreed with the Requirement. Needs to be this was as work may have been arranged for the last day | No Change
MHHS-DIN-394 |  |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Annual Consumption Fields | Raised by SCS. B059/B027/DI-0148 This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block updated to be "must be provided" if available, however data items now need to be set to mandatory non-nullable. | Implemented |  | Interim Release 2 | 2023-06-23 | DI-0148 updated to be mandatory no-nulls and data type updated to DT-016 in Data Catalogue. Data Type corrected to DT-016 in IF-002 and IF-036. | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-395 |  |  | 2023-06-13 | St Clements | 5510 | Vicki Holland | Software Provider | Obfuscation of Connection Type Indicator in IF-021 | The DES138 interface catalogue specifies that the data item Connection Type Indicator will be obfuscated for all parties as it is required for routing only. Can this please be changed so that it is visible? The reason for this request is that suppliers often process data differently for the different connection types and therefore its important that they can internally validate or route data according to the connection type of the MPAN. | Implemented |  | Interim Release 3 | 2023-07-12 | Obfuscation of connection type removed from IF-021/IF-013 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-396 |  | DI-183 | 2023-06-13 | St Clements | 5305 | Madison Layton | Software Provider | Update IF-019 REG1001 to only apply to Create and Add event codes | IF-019 REG1001 rule applies to all event codes. The MPAN could be disconnected with linkages still in place. If REG1001 is applied on remove event codes, then there will be not means by which the Supplier/DNO can remove the linkage after a disconnection. Suggest REG1001 rule should only apply to the Create and Add event codes. This would be consistent with the existing validation on the DB05 and D0386. | Implemented |  | Interim Release 3 | 2023-07-12 | IF-019 MPAN Status Validation Rule removed for all "Remove MPAN" Event Codes. i.e. I can still perform remove MPAN from group task if MPAN is disconnected. SCS rejected option of auto de-linkage as part of De-Registration Process. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-397 |  | DI-184 | 2023-06-13 | St Clements | 5306 | Madison Layton | Software Provider | IF-019: REG0007 to only apply to Related event codes and not to Linked Import Export event codes | REG0007 on IF-019 interface is currently written to apply to both Related and Linked MPANs. The intention of this existing rule on D0386 is because Related MPANs switch together, and so changing the relationship during a switch can create a split supply relationship. However Linked MPANs do not switch together and so this is not currently applied to the existing DB05 validation rules. Suggest REG0007 only apply to Related event codes and not to Linked Import Export event codes? | Closed |  |  |  | Following discussions with SCS it has been agreed to prevent all changes to MPAN Linkages whilst an Active Switch is in progress. This is the safest approach when considering both CSS and Auto Alighment functionality considerations. No change to existing Design Documentation required.
MHHS-DIN-398 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD Stores LLF data | Can we have an ISD entity ID for LLF data. This would be required for the API used to retrive the data from ISD data store. Are you happy for us to create and put it in the Guidance note. What is the ask? | Closed
MHHS-DIN-399 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD publishes full data to Elexon Central Systems | Requirement should be reworded to be "ISD must make available the data sets required by LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. ISD must make available the entire current data set to LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. | Closed |  |  |  | Agreed in a session with Elexon 26/07 that the requirements document will not be changed as the requirement has already been fufilled by Elexon in line with the current requirement.
MHHS-DIN-400 |  |  | 2023-06-14 | SRO Design Team | N/A | Sean Cooper | SEO Design | REGS Validation Rule Clarification | REG1089 conditions updated to provide more clarity. Existing wording refered only to a Subsequent App - this is now better defined as an Appointment with a prior/earlier Sender Timestamp. No functional change. | Implemented |  | Interim Release 2 | 2023-06-23 | For IF-031 Validation rule text updated to specifically reference Sender TimeStamps so as to provide more clarity on the nature of the val rule/when generated | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-401 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | IHD/SMSO Fields | IHD Install Status and IHD Status Effective from Date fields should be optional (ie nullable) when providing an IHD update in IF-025/IF-026. SMSO and SMSO Effective from Date fields should be optional (ie nullable) when providing an SMSO update in IF-025/IF-026. | Implemented |  | Interim Release 2 | 2023-06-23 | DI-137/ DI-136 in block B030 updated to Optional (O) in IF-025 and IF-026 DI-134/ DI-135 in block B031 updated to Optional (O) in IF-025 and IF-026 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-402 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Import/Export Fields | Linked Import/Export MPAN and Linked MPAN Energy Direction will always be provided so should not be nullable | Implemented |  | Interim Release 2 | 2023-06-23 | DI-038 updated to Mandatory No nulls and Data Type updated to DT-002 DI-151 updated to Mandatory No nulls On the 01-Data Catalogue | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-403 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Meter Manufacturer Field | Meter Manufacturer is optional (ie nullable) when provided in IF-002, IF-006, IF-033, IF-036 as in IF-005 | Implemented |  | Interim Release 2 | 2023-06-23 | DI-048 updated to Optional (O) in IF-002, IF-006, IF-033, IF-036 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-404 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Proposed Appointment Response Code Field | For Response code A there may not be any text to populate for DI-143 | Implemented |  | Interim Release 2 | 2023-06-23 | DI-143 updated to conditional (C) based on DI-979 = L or R in block B007 in IF-034 and IF-035 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-405 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Response Message Field | For Response code A no text to populate for DI-980 | Implemented |  | Interim Release 2 | 2023-06-23 | DI-980 updated to conditional (C) based on DI-979 = R in block R0 in 02-DIP Common Block tab | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-406 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Sender DIP ID Field | Sender DIP ID should always be provided in S1 Common Block | Implemented |  | Interim Release 2 | 2023-06-23 | DI-997 updated to mandatory (M) in block S1 in 02- DIP - Common Block tab | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-407 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | COS During SEG Issue | Discuss with SCS the option of allowing non-appointed MS to update MTDs even if App has lapsed due to COS activity. If not then need to update process map to call out need for manual exchange of MTDs as Work MS could never submit if IF005 | Closed |  |  |  | Closed, SCS unable to support alternative solution. Design Team have reviewed the existing process map note and believe this already provides enough information for participants. | No Change
MHHS-DIN-408 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD is the master for data contained both within ISD and MDD during Transition | The requirement is a bit ambiguous as could be read as all ISD and all MDD rather than just ISD data + overlapping MDD data. We don't want to be the master for MDD only data | Closed
MHHS-DIN-409 |  |  | 2023-06-14 | St Clements | 5510 | Vicki Holland | Software Provider | ISD Entity M5 – Consumption Component Classes | EDI012 ISD entities document shows that the settlement period quality indicator in entity M5 is a comma separated list of possible values. This will be difficult to use in systems that need to refer to this data. Could this instead show Actual or Estimate? Alternatively could this be split into parent and child entities to avoid a comma separated list? Metering Service ID MPID is incorrect and must be changed to {MS Id} also in ISD Entity M8 | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Amendments relating to “Valid Settlement Period Quality Indicator Set” wording and field length in section M5 of EDI012 ISD entities document. Change also made from Metering Service ID MPID to Metering Service {MS Id} in Entitiy M8. An objection was raised against this DIN. Following discussion at the DRG about this DIN it has now been moved to Interim Release 5. A decision was made at DRG to go with OPTION 2: Change Existing Layout – Remove list element in favour of individual row(s) for each valid combination for the Valid Settlement Period Quality Indicator Set. | Method statement correction | Supporting Docs | Method Statement | Annual Consumption Meth 10
MHHS-DIN-410 |  | DI-487 | 2023-06-14 | St Clements | 5542 | Virginia Patey | Software Provider | DI-487 definition incorrect for REP-002 on Swagger | DI-487 energised MPANs is defined as an Integer in the Interface Specification, yet is defined as a String in Swagger. | Implemented |  | Interim Release 2 | 2023-06-23 | DI-487 updated in Swagger 1.2 to align with Interface specification for REP-002 | Data interface correction | Supporting Docs |  | Swagger 1.2
MHHS-DIN-411 |  | Migration | 2023-06-14 | ESG | 4810 | Patricia Parker | Software Provider | Migration Segment Categorisation | The Migration Design currently specifies that Market Segment needs to be recorded before the Migration phase. This should be changed so that it is no longer required. Until an MPAN is migrated, there is no way of maintaining the market segment between the RS and EES using the legacy interface between these two services. However, meter type and connection type will be available in both the EES and the RS, so Suppliers can use a combination of these values to derive the correct market segment. | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | 03/08: SCS confirmed in a session with SC that they agreed that Segment is a derived value based on Connection Type and MTR. There are validation rules that prevent the migration if Connection Type (and therefore segment) is not already defined in REGS. To address the original question Segment will always be known at the point of migration. Therefore, no changes are required to Migration document. 13/07: John Wiggins to have offline discussion with Sean C as DIN requires wider discussion at DRG to progress SRO Team disagree with this Migration Request. Market Segment must be known prior to the selection of MHHS Service Providers. Market Segment is a derived field based on Connection Type and Meter Type. Connection Type must be set before Migration / Meter Type already known so Market Segement CAN be derived, set and maintained prior to MPAN migration. No change to baseline documentation Required.
MHHS-DIN-412 |  |  | 2023-06-14 | MHHS | 5022 | John Wiggins | Central Body | Update to MDD | Migration request to ensure that Elexon add MHHS as a value to MDD. Page 35 of the Design Document under Reverse Migration states that -A default MPID of ‘MHHS’ will be created for the DC, MOP, DA appointments. Will MHHS be contained within MDD as a valid set as there is no reference in the document to update MDD with this value. | Industry CP Required |  | Interim Release 6 | 2023-10-18 | As the Migration documentation was approved via DAG and following discusion with RecCo and BSC the updates are being documented inThis is being picked up in an update to DES196 Dflow interface
MHHS-DIN-413 |  | Migration | 2023-06-14 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | Reading Type (J0171) will be updated with three new values: Forward Migration CoA Forward Migration CoS Reverse Migration CoS Reading Type (J0171) will no longer use Initial or Final for migration reads between Suppliers or DC/DS but one of the above new codes will be used. Meter Reading Reason Code (J0332) will no longer be used to identify migration reads, all reference to this will be amended to Reading Type (J0171) in the guidance document. | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes. Replaces DIN-442 | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-414 |  |  | 2023-06-14 | British Gas |  | Mohammad Amin Fuggawala | Supplier | D0275 in D-Flow Document | Ref Previous DIN-244. In the "DES196 D-Flow Document" the D0275 is showing as redundant. This is misleading it should be marked as by agreement between contracting Supplier-DS. Document should be updated to reflect this. | Closed |  | Interim Release 5 | 2023-09-20 | Centrica have been notified on closure of DIN. Update was delivered in the published V1.0 of DES-196 as part of July DAG and the updated version is available on the Collaboration Base.
MHHS-DIN-415 | RT |  | 2023-06-14 | Elexon | 5702 | Mike Ceney | Central Body | Routing IF-026 to LSS | IF_026- For Routing Rules it states for Event Code/Conditions [SSC], [ProfileClass] and [SSCandProfileClass] that this should be routed to MDS, is this incorrect as MDS does not use these items in any calculations or outputs, this should state LSS | Implemented |  | Interim Release 2 | 2023-06-23 | IF-026 [SSC] and [ProfileClass] have been removed as of Interim Release 1. Update DES138 IF-026 to route to LSS on event [SSCandProfileClassChange] | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-416 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-001 New App Scenario Code MCS (Migration Change of Supplier) | Create new Appointment Scenario Code of MCS | Implemented |  | Interim Release 3 | 2023-07-12 | IF -031 New valued added to DI-800 data catalogue and Swagger 1.3 updated to reflect new value | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-417 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-002 Validation Rules for Scenario MCS (Migration Change of Supplier) | New Val rule to check MCS is only used for legacy non-migrated MPAN where Supplier is not current supplier (and not in past) | Implemented |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-418 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-003 New App Scenario Code MCA (Migration Change of Agent [Service Provider]) | Create new Appointment Scenario Code of MCA | Implemented |  | Interim Release 3 | 2023-07-12 | IF-031 New valued added to DI-800 data catalogue and Swagger 1.3 updated to reflect new value | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-419 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-004 Validation Rules for Scenario MCA (Migration Change of Agent [Service Provider]) | New Val rule to check MCA is only used for legacy non-migrated MPAN where Supplier is current supplier and now active Switch is in progress (and not in past) | Implemented |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-420 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-005 - IF-31 Check valid MHHS Supplier | If MCS/MCA code used is Supplier a valid MHHS Approved/Registered Supplier | Implemented |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-421 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-006 - Prevent use of Migration Scenario IDs | IF MCS/MCA code used for already migrated mpan - reject appointment for invalid Scenario code(s) | Implemented |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-422 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-007 Connection Type/Segment not yet Populated | New error required if Connection Type, DUos Tariff ID or Segment is not set prior to migration. | Implemented |  | Interim Release 3 | 2023-07-12 | New Validation Rule created for IF-031 to check that MHHS Standing Data is present and aligned. REG0011 Error created to support this validation Rule. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-423 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-008 Auto Realign Functionality | New REGS Requirement - Only action the auto-realign functionality on MPANs where both Linked MPANs are in a Migrated state. | Implemented |  | Interim Release 3 | 2023-07-12 | New Req RS-146 added to REGS Requirements Document to ensure that Auto-Align functionality is only executed if all MPANs in a related and/or linked group have sucessfully migrated to MHHS Operation. | Requirement correction | Meter to Bank | Requirements Documents | BRS-003-Registration Service Requirements
MHHS-DIN-424 |  | DI-185 | 2023-06-16 | St Clements | 5335 | Madison Layton | Software Provider | MPRS access to correlation ID | IF-019 is sent to the LDSO for LinkedImportExport event codes, if the LDSO approves the request they will submit an existing DB05 flow into MPRS. If the DB05 is accepted by MPRS, it will send an IF-020 to the Supplier to confirm the change to Linked Import Export association. However MPRS would not have access to the correlation ID that was received by the LDSO on the IF-019, and so would use a new correlation ID on the IF-020. | Implemented |  | Interim Release 3 | 2023-07-12 | IF20/IF19 Note amended explaining that it will not be possible to Link IF-019/IF020 messages together using Correlation ID , in the case of Linked MPANs. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-425 | SC | Migration | 2023-06-19 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | 8.1.3 step 12 Migration Design Document : Validation Status (J0022) references will be updated to Meter Reading Flag (J0045) | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes. | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-426 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-009 New Rejection Code for D0205/D0203 | Response to a D205 is a D0203. 1. A New Rejection Condition/Code is required where D0205 is received following processing of IF-031. 2. Proposed new D0203rejection code is 62 "MHHS Fwd Migration in Progress or Completed" | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes. | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-427 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-010 ISD Change M16 | No change Required - SCS can use ISD M16 - which contains MIPD/DIP Role and Effctive From date. This can be used to determine if a Supplier is MHHS qualified. This is better apporach that adding a transiant "Qualified Yes/No" field to this table. Therefore NO changes to documentation required. | Closed
MHHS-DIN-428 |  |  | 2023-06-19 | British Gas | 5835 | Neil Strange | Supplier | MEX before SSD scenario | When a CoS is in progress and there is a MEX before SSD, how will new supplier get the MEX details As the incoming supplier has already received the IF36 - would there be a new IF36 or would it be a PUB006? In addition how would the new MS and DS be made aware of this? - the old MS has X days after the job is completed to update the industry and a CoS could have happened before the old MS can update the other participants. | Closed |  |  |  | BAU Design deals with 'regular' MEX before COS type scenarios (note previous MS Update Period - PUB-006 would be issued to impacted parties). Complexity arises where there is a COS overlapiing with Change of Segment/Connection Type (ie SEG Appointment)... Following discussion with SCS - low probably, low occurance vs. complex change. Ref existing guidance on BP016 there would need to be a manual interaction between Supplier and MS. No Change to existing Documentation Required.
MHHS-DIN-429 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-011 Changes to D0170 | 1. Change D0170 flow so that MPRS/Registration Service is valid Sender of this flow. 2. New value for "Request Action Code" is needed to denote a Migrating account and if its CoS or ChgOfSP method. | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes. | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-430 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-12 New Val Rule for IF-019 | Reject any changes to Related MPANs where any MPAN referenced (or in realted group) is subject to an active Migration SP Appointment Process | Implemented |  | Interim Release 3 | 2023-07-12 | New Validation Rules and Error Code created to prevent changes if MCA Appointment Type Exists (Note: prevention if MCS exists is realised through existing check on if Switch is in Progress) | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-431 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-13 Change to D0386 | Change D0386 validation to reject changes to related MPANs if any related MPAN in group is subject to active Migration SP Appointment Process | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes. | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-432 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-014 Appointment on Secondary Related MPAN | Extend existing 1039 check to include MCS.MCA Appointment Scenarios. | Closed |  |  |  | Existing Validation Rule(s) around REG1039 will already cover Migrating MPANs - No Documentation Change Required.
MHHS-DIN-433 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-015 Switch in Progress Mig Rejection | New IF-031 validation to reject MCA/MCS DS and MS Appointments if an [any] active Switch is in progress with NEW Rejection Reason Code (note 1095 code referenced in Migration document has already been used elsewhere) | Implemented |  | Interim Release 3 | 2023-07-12 | New validation rules and REG9XXX Exception codes added to ensure correct usage of MCA/MCS Appointment Scenario Codes. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-434 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-016 New IF-003 | Previously DIN-247, Introduce IF-003, no changes from original proposal. 1. Update DES138 new tab, update IF List. Update New Data Items 2. Review E2E doc. 3. Update secondary Routing Rules (Avenade Techncal Doc) to include 4. Update Swagger | Implemented |  | Interim Release 3 | 2023-07-12 | Add data items DES138-Interface data Cat and to IF-003. Created new Data items: DI-500 MHHS Regime End Date, DI-501 Rev Migration Incoming MOP MPID, DI-502, Rev Migration Incoming MOP Eff From Date, DI-503, Rev Migration Incoming DC MPID DI-504 Rev Migration Incoming DC Eff From Date. Swagger v1.3 updated to reflect new IF-003, Blocks (B096/B095/B094) & Data Items (as above). | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-435 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-017 D0304 & D0303 | 1. New D0304 Validation Rule 2. NewD0304 Rejection Reason Code "Q - MPAN Fwd migration in progress or completed" 3. Change D0303 so as to make "Eff From Settlement Date REGI" a non mandatory data item within the flow (an alternative to suggesting that outgoing MS no longer issues a D303, only the incoming MS would send) | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes. | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-436 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG0-018 D312 | 1. New D03012 Validation Rule 2. New Rejection Reason Code "AD - MPAN Fwd migration in progress or completed" | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes. | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-437 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-019 IF-005 Validation Rule | 1. New val rule to prevent IF-005 while MCS/MCA Appointment is in progress 2. New Error Code (REG9003) | Implemented |  | Interim Release 3 | 2023-07-12 | REG9003 - MHHS MTD Updates cannot be used until Migration has completed, Created and new validation rule added to IF-005 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-438 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-020 REGS Design Clarification | SCS Should issue L1/L2 Msg Status message with RCP1061 for any MPAN at the incorrect status where a DIP Message is received | Implemented |  | Interim Release 3 | 2023-07-12 | This is a Migration Requirment which participants should take into account as part of their Migration Designs. However, for clarity a note has been added to RCP1061 entry in the Intoduction Section of the Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-439 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-021 No Supplier Updates during Rev MIgration (IF-025) | 1. New If-025 val rule to check if Rev Migration Switch is in progress 2. New error code | Implemented |  | Interim Release 3 | 2023-07-12 | REG9002 - Supplier Data Items Cannot be Maintained for Reverse Migration Account, Created and applied to IF-025 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-440 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-022 No CDCs Updates during Rev MIgration (IF-038) | 1. New If-038 val rule to check if Rev Migration Switch is in progress 2. New error code | Implemented |  | Interim Release 3 | 2023-07-12 | "REG9001 - CDC Marker Cannot be applied to Reverse Migration Account", created and applied to IF-038. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-441 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-023 No AC Updates during Rev MIgration (IF-040) | 1. New If-040 val rule to check if Rev Migration Switch is in progress 2. New error code | Implemented |  | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement section 5 has been updated with the text below in red: Where an MPAN is no longer active under MHHS during the transition phase the Market-wide Data Service shall not calculate or submit an annual consumption on the IF/PUB-040. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption
MHHS-DIN-442 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-024 D0010/D0086 New MR Reason Codes | Three new MR Reason Codes for use in D0010: Forward Migration COS / Forward Migration COA / Reverse Migration | Closed |  |  |  | Original migration design. Superceded by DIN-413.
MHHS-DIN-443 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-025 D0055 New Agent App Reason Codes | 1. New Valid value for service reference "REVM" 2. New valid value for Service Level "REVM" | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes. | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-444 | RS |  | 2023-06-19 | ESG |  | Patricia Parker | Software Provider | IF-01 Incoming supplier for Import/Export MPANs | Clarification required with SCS. If it is known that an alternative MPAN has the same SSD then we do not want the old supplier ID as the linked supplier on the IF-01, we want the new supplier to be populated | Closed |  |  |  | Discussed with SCS and they have confirmed that where co-incidnet COS occurs they would look to populate the [new/incoming] Linked Supplier ID.... No change to documentation required.
MHHS-DIN-445 | SB |  | 2023-06-19 | Utiliteam |  | Richard Palmer | Software Provider | Spec of IF-024 in DES138 Interface Catalogue | The Population Notes for DI D-000 in Group S0 has ‘IF-025’. This error was in v5.0, and is still in v5.1.1 | Implemented |  | Interim Release 3 | 2023-07-12 | The Population Notes for DI D-000 in Group S0 has been updated to ‘IF-024’ in IF-024. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-446 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-026 Migration DIP Reporting Reqs | Reqs for x3 new Reports -- Flag at the next DIP DAG | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | Awaiting further internal discussions re DIP Reporting Strategy
MHHS-DIN-447 | SW |  | 2023-06-21 | Kraken | 5980 | Angelos Rizoyannis | Software Provider | Conditional Mandatory not applied in Swagger correctly | IF-041-CustomBlock: The field B065List is stated as optional in the comments, but the API schema does not reflect this. This field that is conditionally optional in DES-138, but this is not defined as such in Swagger ie, OneOf, AnyOf. This needs to be updated in Swagger to align correctly. | Implemented |  | Interim Release 3 | 2023-07-12 | In Swagger 1.3, updated IF-041-CustomBlock: The field B065List and B064List will be either / or as they are defined as conditionally mandatory in DES-138. This uses AnyOf notation in Swagger. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-448 | SW |  | 2023-06-21 | Kraken | 5980 | Angelos Rizoyannis | Software Provider | Mandatory fields not applied correctly in S1 block | S1 Common Block: The 'properties' and 'required' sections of the API schema for the S1 common block have conflicting information. The 'properties' section includes fields like senderTimestamp and senderRoleID, while the 'required' section lists sentTimestamp and senderRole. | Implemented |  | Interim Release 3 | 2023-07-12 | Updated Swagger 1.3 to align properties and required sections so that fields are called senderTimestamp and senderRoleID. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-449 | SC |  | 2023-06-21 | SRO Design Team |  | Sean Cooper | SRO Design | Change to IF-037 | Include Block B002 into IF037 so that outgoing MS is aware of incoming Supplier on a COS. This will allow the SP to populate the D0303 to MAP. | Implemented |  | Interim Release 3 | 2023-07-12 | Block 002 added to IF-037 for use where event code is MSDeapp, this is so that the outgoing MS is informed of who the incoming supplier is so that D303 can be correctly population. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-450 | SC | DI-196 | 2023-06-22 | RECCO |  | Sean Cooper | SRO Design | Change to IF-005 Validation Rules | Change made to IF-005 validation Rules to allow previous MS to update Meter Location only - during the 10 day post appointment period. This will allow for scenarios where there has been relocation only activity immediatly prior to a change in MS. All other MeterUpdate functions apart from Change of Meter Location shall be rejected per wider agreement that only active MS should have the ability to change the characteristics... This change originated from R1 Comments feedback from RECCO | Implemented |  | Interim Release 3 | 2023-07-12 | IF-005 Validation rules updated to include new "REG0008 - Amendment Requested cannot be undertaken by Previous Metering Service" error condition and code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-451 | SC | CR-018 | 2023-06-22 | Design Team |  | Sean Cooper | SRO Design | CR - 018 Registration Service OOH Ops | CR18 looks to specify Registration Service Out-Of-Hours Operations. | Implemented |  | Interim Release 4 | 2023-08-16 | Following feedback provided on the redlined version of the Operational Choreography, and following discussion on CR018 at PSG, the SRO maintained the DAG Chair’s decision to approve the implementation of CR018. CR Contents incorporated into a new Section 7 of Ops Choreography Document. Updates to clarify low level processing details in Section 7 Out-Of-Hours Processes table. Following feedback from DNO Review - Additional updates to replace the term ‘SLA’ with the phrase “target response time(s)”. Changes to Column headings to ‘When’ across the Operational Choreography document to align with Code Drafting convention. Addition of Intro text and removal of text “or Performance Regime” in Section 5. | Technical corrrection | Supporting Docs | Operational Choreography | MHHSP_OPC001_Operational_Choreography
MHHS-DIN-452 | SC |  | 2023-06-22 | SCS |  | Sean Cooper | SRO Design | Refine Consent Checking Rules on IF-031 | Further refine Consent checking rules so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing . Updates to IF-031 validation rules to reflect this change. | Implemented |  | Interim Release 3 | 2023-07-12 | IF-031 validation rules updated per the DIN Details. Consent checking rules added so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-453 | MF | DI-124 | 2023-06-22 | SCS |  | Mike Fensome | SRO Design | Issuing of IF-020's | Highlighted that LDSO's could issue an IF-020 with details of import/export linkages without having received notification from the Supplier | Implemented |  | Interim Release 3 | 2023-07-12 | Added note to IF-019 and IF-020 to inform Suppliers that Import/Export linkages could be received via PUB-020 unprompted by the Supplier issuing IF-019. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-454 | SC |  | 2023-06-26 | SCS |  | Sean Cooper | SRO Design | Update to ISD M7 | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service | Implemented |  | Interim Release 3 | 2023-07-12 | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service. added rule to support REG0011 logic in IF-031. | Requirement correction | Supporting Docs | ISD Document | MHHSP-DES138-Interface Catalogue MHHSP-EDI021-ISD Entities
MHHS-DIN-455 | SC |  | 2023-06-23 | SCS |  | Sean Cooper | SRO Design | Update Op Choreography (Event Move from IF-013 to IF-014) | Update Ops Choreography to take account of the movement of event [ConsumptionOnDeEnergisedMPAN] which was moved from IF-013 to IF-014 (DIN-255). | Implemented |  | Interim Release 3 | 2023-07-12 | IF-014 Deadline split into two. First [ActivePowerRejected] remains UNCHANGED. Deadline for [ConsumptionOnDeEnergisedMPAN] is also UNCHANGED but moved from IF-013 row into IF-014 Row, to mirror the change delivered by (DIN-255). OPC_580 ID details updated in OPC001 Operational Choreography document. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP_OPC001_Operational_Choreography
MHHS-DIN-456 | SC |  | 2023-06-23 | SCS |  | Sean Cooper | SRO Design | Swagger Correction - DI-844 | Corrected x2 invalid referenced to "AssignedMRDRequestEffectiveFromDate" should have been "AssignedMRDEffectiveFromDate" in Block 066 | Implemented |  | Interim Release 3 | 2023-07-12 | Corrected x2 invalid referenced to "AssignedMRDRequestEffectiveFromDate" should have been "AssignedMRDEffectiveFromDate" in Block 066 | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-457 | SC |  | 2023-06-23 | SCS |  | Sean Cooper | SRO Design | Change to DTN Validation of D0350 | Implement DTN Validation of D0350 to prevent future dates | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes. | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-458 | SC |  | 2023-06-23 | SCS |  | Sean Cooper | SR Design | New IF-019 Related MPAN Validation Rule | New Validation Rule required for IF-019 to ensure that only Import MPANs can be related. Add to Create and Add Related - this is per REC Shedulle 28 | Implemented |  | Interim Release 3 | 2023-07-12 | New Rules added to IF-019, [RelatedAdd] and [Related Create] events to ensure only Import MPANs can be in a related Group. New Error code added to support these new rules REG1067 - Only Import MPANs can become Related | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-459 | SB |  | 2023-06-23 | Utiliteam | 5724 | Richard Palmer | Software Provider | Spec of IF-024 in DEL138 Interface Catalogue | A further suggestion re the Interface Spec for the IF-024: The Event Code list in DI D-999 in Group S0 contains [SN-RemoteEnabled] & [SN-RemoteDisabled]. I would suggest that these are invalid for Segments Advanced and Unmetered. Also [SN-Vacant] would appear to be irrelevant for Segment Unmetered, and I doubt that [SN-NoComms] would be valid either. These existed in v5.0, and are still in v5.1.1. Perhaps the routing rules need some improvement? | Closed |  |  |  | No change Required. Useage of these evernt codes is obvious and is described in the Requirments documents as necessary
MHHS-DIN-460 | SB |  | 2023-06-26 | Utiliteam | 5939 | Richard Palmer | Software Provider | PIF-019 structure & Principle -> Principal | Also, in the relationships between MPANs, the ‘main’ one is the ‘Principal’ one – not the ‘Principle’. This will be embarrassing if left uncorrected. It is still in v5.1.2 in IF-019, and it is in many other places. If there is a chance of correction, please take it. | Implemented |  | Interim Release 3 | 2023-07-12 | Spelling mistake corrected in Data Catalogue, IF-019, IF-020. Note YAML name also corrected for DI-073. | Data interface correction | Supporting Docs | Interface Changes | MHHSP-DES138-Interface Catalogue Swagger 1.3
MHHS-DIN-461 | SW |  | 2023-06-26 | Greenbird | 1768 | Fredrik Omland | Software Provider | Misalignment between DES-138 and Swagger for DIP Connection Provider ID | In DES-138, In the S1 block, DI-996 (Connection Provider DIP ID) is defined as Optional. But in Swagger, this is defined as mandatory. | Implemented |  | Interim Release 3 | 2023-07-12 | Updated Swagger 1.3 so DI-996 in S1 block (Connection Provider DIP ID) is Optional to align with DES-138 | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-462 | SW |  | 2023-06-27 | Design Team |  | Steve Weston | SI Design | Schema Optionality incorrectly defined for some Interfaces | In DES-138, there are are a number of Interfaces where the Schema Optionality is defined as Optional, rather than Mandatory. The list of Interfaces are as follows - IF-050 / B022, IF-023 / B053 and IF-013 / B049 | Implemented |  | Interim Release 3 | 2023-07-12 | Updated Schema optionality in DES138 to show that all data items must be present where the block is present in line with updated E2E Solution Architecture for IF-050 / B022, IF-023 / B053 and IF-013 / B049. | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalouge
MHHS-DIN-463 | SW |  | 2023-06-27 | SIMS |  | Kyle Abraham | Software Provider | No ability de-register from receiving Status messages in Swagger | In Swagger, there is a POST method for /statusmessage/config, but there is no DELETE method, so you are unable to delete / de-register for any status messages. Need to update Swagger to ensure this is possible. | Implemented |  | Interim Release 3 | 2023-07-12 | Updates made to Swagger 1.3, so there is a DELETE method for /statusmessage/config, so you are now able to delete / de-register for any status messages. Updated so that all of the Interfaces accept the same 4 security headers required for message signature and validation. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-464 | SW |  | 2023-06-27 | SIMS |  | Kyle Abraham | Software Provider | Clarity required on values expected for /dip-channel/{id} for submitEvents on Swagger | The {id} in /dip-channel/{id} for submitEvents on Swagger should accepts values that are the same as the enumeration in DI-000 to ensure consistency. At the moment, this is not clear in Swagger or E2E001 design, so this needs to be updated to make this clearer. | Implemented |  | Interim Release 3 | 2023-07-12 | Updates made to Swagger 1.3, so there the correct enumerations / values are available to align with values in DI-000 to ensure consistency and avoid any ambiguity between interfaces and reports. Updated to remove PublicationConfig and RestConfig in favour of a single config WebhookConfig. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-465 | SC |  | 2023-06-28 | RECCO |  | Sean Cooper | SRO Design | Update to BP010 - Related MPANs | The process MPAN for Related MPANs does not clear call out the Rejection pathway. Update Business Process to show rejection process. | Implemented |  | Interim Release 3 | 2023-07-12 | BP010B Related MPANs Process updated to show specific Rejection Route. | Process Model correction | Metering Changes | Business Process Documentation | BP010- Changes to MPAN Data
MHHS-DIN-466 | SC | DI-188 | 2023-07-29 | SCS |  | Sean Cooper | SRO Design | Change of MPAN Status during Service Provider Appointment Process. | How should a change of MPAN Status be dealt with whilst there is an ongoing SP Appointment that has not yet reached the stage of IF-034 processing !? If an MPAN is disconnected between PUB-031 acceptance and receipt of PUB-034, the SP PUB-034 Response would be rejected by MPRS due to validation rule REG1001. The appointment would not be progressed but would be stuck in the MPRS queue at status Requested. Could resolve by amending REG1001 validation on IF-034, to not apply to event codes MSAppSPResponse or DSAppSPResponse. | Implemented |  | Interim Release 3 | 2023-07-12 | Resolved following discussion with SCS, Agreed that SCS will take no action until the IF-034 has been processes. A change to REG1001 validation on IF-034, to not apply to event codes MSAppSPResponse or DSAppSPResponse, is required to allow the IF-034 to processes normally (when where MPAN is disconnected)... Following processing of the IF-034 RESG will then immediatly issue an IF-035 with reason code of "1- Lapsed as MPAN Status is Disconnected" ... ... Agreed that this was best resolution both for REGS processing rules and participants as no change to currently expected message patterns/ordering. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-467 | SC |  | 2023-07-29 | ESG |  | Sean Cooper | SRO Design | Review of IF-035/IF036 Data Item Obfuscation | Review of IF-035/IF-036 Data Item Obfuscation | Implemented |  | Interim Release 4 | 2023-08-16 | Various updates to obfuscation on IF-036 to align with IF-035. DI-019/DI-800/DI-809/DI-207 obfuscated for Data Service DI-020/Di-800/DI-126/DI-842/DI-209/Di-844/DI-811/DI-208 /DI-018 obfuscated for Metering Service | Data interface correction | Supporting Docs | Interface Catalogue | MHHS-DES138-Interfaces
MHHS-DIN-468 | SC |  | 2023-07-29 | Helix |  | Sean Cooper | SRO Design | Routing of IF-020 | Helix have confirmed that they DO NOT need to receive Related/Linked MPAN information therefore an update is required to REMOVE MDS from the receipient list for this IF-020 | Implemented |  | Interim Release 3 | 2023-07-12 | IF-020 Routing table has been updated to REMOVE MDS as being a recipient of any IF-020 messages. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-469 | ME |  | 2023-06-30 | SRO Design Team | 2109 | Rob Golding | SRO Design | Removal of Z0 & Z1 data items in ERI011B - ECS Reports External | Z0 & Z1 data items to be removed from from the each of the MHHS reports within ERI011B - ECS Reports External as they are no longer in the common block | Implemented |  | Interim Release 3 | 2023-07-12 | Removed Z0 & Z1 data items from all MHHS reports in ECS external reporting artefact | Data interface correction | Minor | ECS Reports | ERI011B - ECS Reports External
MHHS-DIN-470 | SW |  | 2023-06-29 | Callisto | 1805 | Seth Chapman | Software Provider | Clarity on nullable fields | Section 4.2.2 in the E2E design provides information on Optional / nullable fields, but worked examples would provide further clarity for each of the data types / link to JSON specification. | Implemented |  | Interim Release 3 | 2023-07-12 | Updated section 4.2.2 with worked examples for each data type to provide additional clarity. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-471 | MH |  | 2023-06-30 | Helix |  | Derek Weaving | Central Body | Update to REP-003 in ERI011B - ECS Reports External | R019 parent should be R017 in the ECS Reports External and Swagger | Implemented |  | Interim Release 3 | 2023-07-12 | Updated R019 parent to R017 for REP-003 in ERI011B - ECS Reports External. Swagger v1.3 updated to align with changes within ECS reports artefact. | Data interface correction | Minor | Interface Changes | ERI021 -ECS Reports External Swagger 1.3
MHHS-DIN-472 | SW |  | 2023-06-29 | SRO Design Team | 2006 | Rob Golding | SRO Design | Onboarding migration from Test to Production. | “The programme is to implement a strong PKI policy but as per the diagram states that that on promotion, parties will be able to copy their Test setup and to use that for connecting to the Prod environment. - steps 1-8 - There are no steps in this sequence that test the connectivity to the Live DIP environment. To this point the only connectivity testing has been to the Test environments. This is a significant failure point / risk. At this point Webhooks and certificates will change (mTLS and JSON signing) from those used in Test as well as potentially some of the PKI resources assigned to roles ( those used in test may not be applicable to Prod) we would expect that this would require a new Connectivity proving period with the Prod environment similar to that being developed for CIT. Without such proving, how can the programme assume all parties will connect to the Prod environment successfully and ensure minimal impact to migration events”. | Closed |  |  |  | Solution yet to be defined This an Elexon/DIP Manager deliverable not a programme deliverable
MHHS-DIN-473 | SB |  | 2023-06-30 | MHHS | 2111 | Jason Brogden | Network Operator | Definition of Network Operations | Issue: There is a lack of clarity in the scope of Network Operations activities in testing. Action to Resolve: Add a definition to the Programme Glossary that makes clear the scope of Network Operations (as referenced in Testing material) is equivalent to the scope of LDSO activities in the MHHS Design Baseline: Network Operations systems and services are those that are required to deliver the elements of the MHHS Design Baseline that are allocated to the LDSO role. Communicate this to the DNO and iDNO community and associated service and software providers. For the DIN Log, we can then focus on updates to the BRS to give the necessary clarity on the scope of MHHS Design. Issue: There is a lack of clarity in the scope of LDSO activities in the MHHS Design Baseline as BRS005 implies MHHS-related processing requirements at LDSOs for received DIP messages, whereas the BPs and BPDs define the scope of MHHS as ending at the receipt of DIP messages. BRS005 is described as “For Guidance Only” at the top and this is to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing). Action to Resolve: For the avoidance of doubt and to provide clarity to BRS005, it is proposed to change the “For Guidance Only” note at the top of BRS005 to the following description as per the above: BRS005 is provided For Guidance Only to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing). | Implemented |  | Interim Release 3 | 2023-07-12 | LDSO Requirements document updated with the following text, "BRS005 is provided For Guidance Only to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing)." | Requirement correction | Minor | Business Requirements Documentation | BRS-005 LDSO Overview.xls
MHHS-DIN-474 | ME |  | 2023-07-03 | MHHS |  | Kevin Spencer | SRO Design | Creation of new ECS data items and blocks across multiple reports and/or data catalogue | Report definitions incorrect and require updates and new data items following internal review | Implemented |  | Interim Release 4 | 2023-08-16 | Addition of data items DI-503, DI-505-DI-515 to data catalogue and across ECS reports artefact. MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal Missing data items added to data catalogue Di-403/DI-404/DI-514/DI-515 | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-475 | ME |  | 2023-07-03 | MHHS |  | Kevin Spencer | SRO Design | Update to block names, data items and descriptions | Report definitions incorrect and require updates and new data items following internal review | Implemented |  | Interim Release 4 | 2023-08-16 | Update to block names, DTN references, data items, descriptions and reordering of data item blocks to exisiting reports in MHHSP - ERI011B - ECS Reports - External | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-476 | SW |  | 2023-07-03 | Greenbird | 2035 | Fredrik Omland | Software Provider | Inconsistency between enum fields and nullable definition | Looking at DIP Interfaces Swagger 1.1 (also 1.2 + 1.3), the enum typed fields that are nullable may not comply with OpenAPI specification (for 3.0.x). The topic around enum fields with nullable: true has been clarified/answered by OAS project (amended in spec version 3.0.3 in 2021): (Reference: https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md ) | Implemented |  | Interim Release 3 | 2023-07-12 | To align with Open API spec clarification at https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md, we have updated all Data Types that are nullable and have an enum to align as follows: Following discussion, have decided to align with OpenAPI 3.1 DI-076-Estimation-Reason-Code: description : Used inconjunction with Settlement Period Quality Indicator to explain why data has been estimated type : string nullable: true maxLength : 2 example : '1' enum: - '1' # OptOut - '2' # Missing .. - '8' # Disconnected - '9' # Consumption Amendment - '10' # NonSmart - null The Data Types affected / updated as follows: --- DI-039-Load-Shape-GSP-Group-ID --- DI-076-Estimation-Reason-Code --- DI-096-Site-Visit-Check-Code --- DI-126-Traditional-Fall-Back-Read-Frequency --- DI-137-IHD-Install-Status --- DI-150-Annual-Consumption-Quality-Indicator --- DI-166-Supplier-Consumption-Amendment-Reason-Code | Data interface correction | Minor | Interface Changes | Swagger 1.3
MHHS-DIN-477 | SW |  | 2023-07-03 | MHHS |  | Steve Weston | SRO Design | Swagger alignment to OpenAPI 3.1 specificiation | Align with Open API specification 3.1 to remove nullable :true and replace with type declarion ie, type:[string:”null”] | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Further details of the solution are under discussion/review. | Design Ambiguous | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-478 | SW |  | 2023-07-03 | MHHS |  | Rob Golding | Central Body | IF-021 max number of days of consumption data | In the Release 2 version of DES138 a limit was introduced that asked Participants not to submit more than 150 Settlement Days’ worth of data in a single message. The value of 150 was proposed as this meant a single message would realistically be ~600KB in size. We’ve had some queries regarding this value, the proposal is to increase sizing from 150 to 194 day message and the size increases from 600KB to ~780KB for IF-021 message. ECS will need to validate the message contents. However, rather than letting a ‘large’ IF-021 message traversing though the DIP, the proposal is to limit the IF-021 on ingress to the DIP and a single request will have a limit of 1MB – this will be done at the API level. | Implemented |  | Interim Release 4 | 2023-08-16 | Agreed to limit the number of MQ IDs per IF-021 submission to ONE only and limit settlement days to 200. Swagger has been updated to limit the number of MQIDs to 1. Swagger updated to limit the maximum number of Settlement Days to 200. DES138 also updated to aligned with the above changes for IF-021. | Data interface correction | Minor | DES138 and Swagger | DES-138 and Swagger 1.4
MHHS-DIN-479 | SC |  | 2023-07-03 | SCS |  | Maddison | SCS | Change to Consent Notification on IF-036 | SCS have suggested that B068 should only be required for DSApp Events. | Implemented |  | Interim Release 3 | 2023-07-12 | Block 068 on IF-036 amended to that it is only Mandatory for DSApp Events. | Data interface correction | Supporting Docs | Interface Change | DES138-InterfaceCatalogue
MHHS-DIN-480 | SC | DI-195 | 2023-07-03 | SCS |  | Maddison | SCS | Reverse DIN-105 | SCS have confirmed that it is possible currently and should continue to be possible to manage MPAN Linkages whilst MPAN(s) are at Created Status. Therefore we have reversed the change implemented at part of DIN105 and now allow processing of IF-019 if mpan status = "Created" | Implemented |  | Interim Release 3 | 2023-07-12 | SCS have confirmed that it is possible currently and should continue to be possible to manage MPAN Linkages whilst MPAN(s) are at Created Status. Therefore we have reversed the change implemented as part of DIN105 and now allow processing of IF-019 if mpan status = "Created" | Data interface correction | Supporting Docs | Interface Change | DES138-InterfaceCatalogue
MHHS-DIN-481 | SW |  | 2023-07-06 | Elexon | 2106 | Nigel Rees | Central Body | REP-003 inconsistency between DES-138 | We have a contradiction between the DT-023 and the swagger spec. As there is an example we will implement based on the example but it looks like the person who wrote the ECS report catalogue used the correct convention. e.g. on REP-003 we have DT-023 as NUM (16,6). If we follow the convention used in the DIP interface spec, this would translate to 1234567890123456.123456, however the swagger suggests 123456789.123456 Screenshot from REP003 in external ECS reporting catalogue https://app.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.3#/components/schemas/DT-023-Positive-Decimal-9-6 DT-023-Positive-Decimal-9-6: description: Number (9,6) format type: string pattern : ^[0-9]\d{8}(\.\d{6})?$ example: 123456789.123456 | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Two new data type references have been created DT-024 and DT-024N. For NUM(16,6) data type within ECS reports/ECS data catalogue replace DT-023/DT-023N with DT-024/DT-024N. DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. 31/08: A reconciliation exercise is being carried out internally of the ECS data catalogue to assess data types. Further work may be required to swagger following the reconciliation. | Reporting correction | Minor | ECS Reports | "MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2"
MHHS-DIN-482 | KH |  | 2023-07-10 | C&C | 2394 | Hazel Cotman | Software Provider | Interim Release 2 query - IF-018 | LDSO’s are not detailed as ‘To Parties’ within IF-018 flow, however, the LDSO is a secondary routing party for updates to the Domestic Premise, Energy Direction Indicator, and the Metered Indicator | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | LDSO's added to the To party list of IF-018 | Data interface correction | Minor | Interface Catalogue | DES138
MHHS-DIN-483 | KH |  | 2023-07-10 | BGAS | 2410 | Neil Stranger | Supplier | MHHS Design Query - date/ time in DES138 | In DES138 there are a number of data items that are defined as having a date/time structure, but the name and description only refer to the date element whereas others refer to date and time. Therefore for those that make no reference to time we need to be 100% clear if the time should be when the event occur or should it be defaulted to say midnight. This is to ensure consistent population/use across the market. | Closed |  |  |  | Related to a Design Principle and agreed as per E2E Architecture
MHHS-DIN-484 | SW |  | 2023-07-10 | MHHS | 2352 | Martin Freeman | Central Body | Clarity on RecipientId and SenderID in StandardResponseBodyType | RecipientID in the Standard Response Body is a mandatory field. When submitEvents (or in IR2 dip-channel) is called, the DIP synchronously returns a Standard Response Body. At this point the DIP does not even know what message recipients the message will be routed too, since the response is returned synchronously whereas routing is performed asynchronously. So the DIP has no way to know what to set recipientID to. It is also important to note that a message can be received by multiple recipients, yet this recipientID is a scalar that only supports being set to a single value. So it isn't clear how that could work. | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Update section 4.6.1 in the E2E001 Design document to provide better clarity on how SenderID and RecipientID are populated in the StandardResponseBodyType. Provided worked examples for L1-L6 to illustrate this as examples. Updated Swagger 1.4 to align with the above. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-485 | SW |  | 2023-07-10 | MHHS | 2380 | Steve Weston | Central Body | Unable to identify Recipient on DELETE and some POST methods | For the DELETE methods in Swagger for StatusMessage and PublicationConfig, need to update the method so you can identify the correct recipientID to be used for the method call. Some frameworks will ignore a body on a DELETE method as being incompatible with the semantics of the DELETE method, and the correct RESTful implementation would be something more along the lines of "DELETE dip-channel/{id}/{role}/pubconfig". Which of course raises the question of whether the POST message should be refactored for consistency. The issue is more widespread than just the DELETE methods, it also affects some of the POST methods where a recieipent ID is required | Implemented |  | Interim Release 4 | 2023-08-16 | Design changes required to Swagger 1.4 to support updates to API endpoints for DELETE API verbs to ensure we are able to remove the correct StatusMessage or PublicationConfig for the appropriate recipient combination. The issue also affects some of the POST methods where a recipient ID is required, e.g webhook config. A standard pattern is proposed where a recipeint id is specified in the path. Updates to section 4.5.1 and 4.7 also made to E2E001 design document to ensure the document provides any clarity required. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-486 | SB |  | 2023-07-11 | MHHS | 2107 | Rob Golding | Central Body | DES138 and message addressing information | Please can you raise a DIN to cover the following request from Participant to clarify the From and To Parties at the top of each sheet to align with the role codes the programme is using and defined in the E2E Solution Architecture document. And if these ‘pure’ roles code could be included in the introduction sheet that would certainly help. More detail can be seen in the Ticket | Implemented |  | Interim Release 4 | 2023-08-16 | Update the role codes in DES-138 for the From / To Parties for each of the Interfaces to align with other documents including E2E001. No change to information in the Introductory section in DES-138 required. | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-487 | SW |  | 2023-07-11 | MHHS | 2379 | Martin Freeman | Central Body | Clarity on schema vs data validation failures, with updated examples. | In section 4.4.4.2, there are some examples that incorrectly return a 207 when they have failed schema validation. | Implemented |  | Interim Release 4 | 2023-08-16 | In section 4.4.4.2, there are some examples that incorrectly return a 207 when they have failed schema validation. E2E001 section 4.4.4.2 has been updated to illustrate 2 examples. One that returns a 201 Created (2 messages as part of the HTTP Request, both pass validation) and another example that returns a 207 (2 messages part of the HTTP Request, but 1 does not pass validation). | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-488 | ME |  | 2023-07-11 | MHHS | 1506 | Steve Weston | SRO Design | Correct Reporting Cat vs Swagger | Reinstated DI-484 "Settlement Period Duration" and added into R Groups as required | Implemented |  | Interim Release 4 | 2023-08-16 | Reinstated DI-484 "Settlement Period Duration" and added into R Groups as required in Swagger 1.4 | Data interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-489 | MF |  | 2023-07-11 | Design Team |  | Mike Fensome | SI Design | Schema Optionality incorrectly defined for Common Block | In DES-138, the Common Block shows some fields where the Schema Optionality is defined as Optional, rather than Mandatory. The list of Blocks are as follows - Common Block: S1, D0, A0 | Implemented |  | Interim Release 4 | 2023-08-16 | Update Schema optionality in DES138 to show that all data items must be present where the block is present in line with updated E2E Solution Architecture. Common Blocks impacted: S1, D0, A0 | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-490 | SW |  | 2023-07-11 | MHHS | 2395 | Martin Freeman | Central Body | Level 1 validation clarity for POST /statusmessage be the same as for POST /dip-channel/{id} | The E2E001 v3.2 (section 4.4.3) describes how for the Send Messages API, when the DIP performs level 1 validation, if any message in the request fails validation then the entire request is rejected. Section 4.6 Send Status Messages API does not describe the DIP validation for status messages at all. Should validation for POST /statusmessage be the same as for POST /dip-channel/{id}, in that a level 1 validation failure for any message should fail the entire request, or should messages that pass validation be accepted and messages that fail be rejected independently? | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | This should be consistent across all interfaces in that a schema validation failure for any message should fail the entire request. In the E2E001 design, sections 4.4.3 and 4.6 are to be updated to reflect this / provide the appropriate level of clarity. This issue affects both the http delete operations. Easy to fix, same fix as the post need to include the webconfigas a parameter | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-491 | SB |  | 2023-07-11 | Utilita | 2408 | Adam Barnes | Supplier | DES138 v5.2.1 | IF-035 tab for the bottom 3 entries it still refers to the previous version definition of routing parties – we expect this to be a slight oversight as SDSS is no longer defined as a recognised party? | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18
MHHS-DIN-492 | KH |  | 2023-07-11 | Stark | 2125 | Matthew Peters | Supplier | IF-034 Proposed Appointment Response Code Formatting | The data type within DI-143 block for IF-034 and IF-035 needs to change from String 200 to Array because there is a possibility of getting more than 1 rejection code. | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18
MHHS-DIN-493 | SC |  | 2023-07-12 | SCS |  | Sean Cooper | SRO Design | Changes to IF-019 Secondary MPAN validation | SCS had originally suggested a validation rule to prevent Secondary (Related) MPANs being linked to an Export MPAN. However, RECCO and EON have highlighted there are a very small number of scenarios where this might be the case. Following further discussions with SCS they are now happy to remove this rule (REG1068) | Implemented |  | Interim Release 4 | 2023-08-16 | IF-019 - REG1068 check for Secondary MPAN Linkage to export REMOVED | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-494 | SW |  | 2023-07-12 | Callisto | 2462 | Neil Edney | Software Provider | Incorrect Min and Max Values for DI-091-Number-Of-Displayed-Register-Digits | DI-091-Number-Of-Displayed-Register-Digits currently has a minimum of 1 and maximum of 1, when this should be 5 and 6 respectively to align with DES-138 as this is an Integer. | Closed |  |  |  | This DIN is now superseded by DIN-615 following on from DIN-574. Text against Number of Register Digits field amended to say "per the manufacturer specification". Swagger validation of this field updated to match SCS logical test ie value can be 0-9. This DIN was to ensure there was consistency in Swagger 1.4 to align with DES-138 so that min and max was 5 and 6 respectievly. This objection is related to the values in DES-138, to update from 5 and 6 to 0 and 9, and then align Swagger to the values in DES-138. | No Change
MHHS-DIN-495 | SC |  | 2023-07-12 | Design Team |  | Sean Cooper | SRO Design | Correction to BP003 | IF-035 for Trad/Advanced meters was previously shown as being direct interaction between REGS and MS ... Changed to show message as flowing via the DIP | Implemented |  | Interim Release 3 | 2023-07-12 | IF-035 for Trad/Advanced meters was previously shown as a flow being direct interaction between REGS and MS. Changed to show message as flowing via the DIP (at step 90). Also change applied to Forward migration process for consistency. | Process Model correction | MPAN Ownership | BP003 | MHHSP-BP003-Change of Service - Data Service MHHS-DEL964 BPM-003 - Change of Servie - Data Service - Forward Migration
MHHS-DIN-496 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 | MHHSP-METH001_SDS_Validation_Estimation 5.1 section 2.7 States "SDS shall inform the Supplier using the Meter Reading Reason Code on the IF-041/PUB-41" . There is no Meter Reading Reason Code on the IF-041 in DES138 v5.1.2. Therefore, either Meter Reading Reason Code should be included in DES138, or this requirement should be removed. | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Remove the following from METH001: 'Where consumption data has been deemed invalid the SDS shall inform the Supplier using the Meter Reading Reason Code on the IF-041/PUB-41.'
MHHS-DIN-497 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 | MHHSP-METH001_SDS_Validation_Estimation 5.1 Section 5.4 Where DA records are < 90 days from UTC date this is inconsistent with Method 4, which states "DA is available [either in the past or future] and less than [3] months different from the UTC Date requiring a daily Meter advance". | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Be consistent - use either 90 days or three months within the document
MHHS-DIN-498 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 Method 13 | MHHSP-METH001_SDS_Validation_Estimation 5.1 Method 13 This describes the outcomes for Smart and Advanced meters. Does this imply that traditional meters should have zero consumption submitted to settlements, or should Method 13 text be adjusted to include trad meters? ALSO If actual data is recovered, or an Advance Meter Reading is received, and this indicates zero consumption, should this be submitted to settlements? The first part of the sentence implies it should be submitted, and the brackets imply it shouldn't. | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Alter wording of Method 13 to reflect we shouldn't be sending estimates for Deenergised trad meters as well as Smart and Advanced, AND 'there is no need to submit zero consumption for de-energised MPAN's' needs changing to refer to 'zero ESTIMATED consumption'
MHHS-DIN-499 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Alignemtn of Estimation Reason Codes | METH001 refers to Estimation Reason Code 'Adjustment'. DES138 refers to 'Consumption Amendment' Assume these are the same thing and need to be aligned between both sets of documentation | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Align Method Statements to match the Estimation Reason Codes within DES138
MHHS-DIN-500 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | ISD Entity M17 Example Correction | MHHSP_EDI021_ISD_Entities 5.1 Entity id M17 Industry Standing Data: MHHS Entities/Data Items v5.1 ISD Entity Id M17 - Valid Consent Granularity Combinations, includes combination I¦F¦S¦D. According to Decision 2 in "https://www.ofgem.gov.uk/sites/default/files/docs/2019/06/access_to_data_consultation_ofgem_response_0.pdf" a non-domestic customer is unable to opt out. The OFGEM document states "There will be no opt out possible for microbusinesses in relation to data for settlement purposes". Therefore, I ¦ F ¦ S ¦ D is not a valid combination. | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Remove I ¦ F ¦ S ¦ D from the example list
MHHS-DIN-501 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Addition of Method 13 to METH002 | MHHSP-METH002_ADS_Validation_Estimation 5.1 Section 3.16 States "The below estimation methods are based on those used in the Smart Data Service (SDS) Method Statement. For that reason, methods 0, 1, 6, 11 and 13 have been omitted as they are only applicable to Smart meters." However, method 13 is "Estimation for a Site where Supply is de-energised" and this is included in METH002 in section 2.29. The statement is wrong as some of the methods have been renumbered in METH001 since this was written. | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Update METH002 to add MEthod 13 back in
MHHS-DIN-502 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | SP Quality Indicator Clarification | MHHSP-METH001_SDS_Validation_Estimation 5.1 It is our assumption that if NO estimation is required, the Settlement Period Quality Indicator should be set to "A". This is however, never explicitly mentioned. The only mention of using value "A" is for method 1. | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Update artefacts to clarify when to use A as the SEttlement Period Quality Indicator value
MHHS-DIN-503 | SW |  | 2023-07-13 | SIMS | 2439 | Martin Freeman | Central Body | S1.senderUniqueReference interface component is too small to identify the message interface | DES138 and the E2E001 the S1.senderUniqueReference property has a 3 digit component that contains the interfaceID of the message. However since the reporting interfaces reuse the same interface numbers as the standard interfaces, and some reporting interfaces have 4 character interface identifiers, this means this component is not sufficiently large to unambiguously identify which interface a given senderUniqueReference was generated for. This also applies for TransactionID. | Implemented |  | Interim Release 4 | 2023-08-16 | Update any Data Items that utilise InterfaceID to align with the enumeration of values defined for DI-000 so that this is unique across all interface / report types. This is for data types SenderUniqueReference (DI-995) and TransactionID (DI-990). This change will require updates in DES-138, E2E001 and Swagger 1.4. In DES-138, DT-014 has been updated to String65 from String60 to support Interface being updated from 3 to 8 to align with DI-000 (so for IF-003, rather than 003 being included in the transactionID / senderUniqueReference, this will be IF003 with no hyphen). In Swagger, DT-014 has been updated to max length 65, with examples updated. E2E001 updated examples for senderUniqueReference and TransactionID to align with the above. | Design Ambiguous | Supporting Docs | DES-138, E2E001 and Swagger 1.4 | DES-138-interface catalogue, E2E001 E2E Architecture document and Swagger 1.4
MHHS-DIN-504 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Clarification of link between IF22/IF23 | DES138 IF-022/023 IF an IF-022 or IF-023 is re-issued, can you confirm that they will be reissued as a pair so that the totals align? The issue is if an updated IF-022 is issued with new values, should the SDS/ADS await an updated IF-023, or not? How can the SDS/ADS pair the IF-022 and IF-023 without doing their own summations? | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Update BRS007 to show that a re-run of IF-022 will result in a rerun of IF-023
MHHS-DIN-505 | BK |  | 2023-07-13 | SCS |  | Sean Cooper | SRO Design | DUoS Tariff ID to hold values from 1-3 in length | The DUoS Tariff ID needs to be updated in Swagger and the Interface Catalogue so that it can hold values from 1 to 3 in length in order to align with ISD. | Implemented |  | Interim Release 4 | 2023-08-16 | Update DUoS Tariff ID to hold values from 1 to 3 in length in Swagger and Interface Catalogue | Data interface correction | Supporting Docs | Interface Catalogue and Swagger 1.4 | DES138-InterfaceCatalogue Swagger 1.4
MHHS-DIN-506 | BK |  | 2023-07-13 | Design Team |  | Sean Cooper | SRO Design | Renaming of IF-014 | Rename IF-014 to clarify the purpose | Implemented |  | Interim Release 4 | 2023-08-16 | Changed to "UTC Settlement Period Consumption Data (Warnings & Rejections)". Interface description and notes updated to reflect that IF-014 could also contain warnings for Consumption on De-enegised sites. | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-507 | SC | DI-194 | 2023-07-14 | Design Team |  | Sean Cooper | SRO Design | Clarification of IF-036 Routing Requirements | Update IF-036 to clarify / provide additional info on the routing destinations of IF-036 | Implemented |  | Interim Release 4 | 2023-08-16 | Added following Text: Primary Routing Participants for IF-036 MSAppActive • Supplier (i.e. the supplier who initiated the appointment, either current in the case of Change Of / Update to SP’s, or incoming in the case of a COS) • Metering Service (i.e. the Metering Service being appointed) • [Partner] Data Service (i.e. the Data Service in effect on the App Start Date of the MS Appointment – this could be either an ‘existing’ Data Service in the case of an MS Only appointment OR the ‘incoming’ Data Service with a coincident App Start Date to that of the [incoming] Metering Service • Linked Supplier(s) – (ie the Supplier(s) with responsibility for the Linked [Import/export] MPANs on the App Start Date of the Metering Service Appointment) DSAppActive • Supplier (i.e. the supplier who initiated the appointment, either current in the case of Change Of / Update to SP’s, or incoming in the case of a COS) • Data Service (i.e. the Data Service being appointed) • [Partner] Metering Service (i.e. the Metering Service in effect on the App Start Date of the DS Appointment – this could be either an ‘existing’ Metering Service in the case of an DS Only appointment OR the ‘incoming’ Metering Service with a coincident App Start Date to that of the [incoming] Data Service • Linked Supplier(s) – for Advanced Segment Meters only - (i.e. the Supplier(s) with responsibility for the Linked [Import/export] MPANs on the App Start Date of the Metering Service Appointment) | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-508 | SC |  | 2023-07-17 | Design Team |  | Sean Cooper | SRO Design | Addition of MP Status and RMP Status Effective From Dates to IF-050 | Addition of MP Status and RMP Status Effective From Dates to IF-050 ( Linked to DIN 318 ) | Implemented |  | Interim Release 4 | 2023-08-16 | New Data Items Created and added to IF-050 in block B079 and the data catalogue tab: DI-167 RMP Status Effective From Date DI-168 MP Status Effective from Date (DIN 318 Closed as duplicate) | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-509 | SW |  | 2023-07-18 | MHHS |  | Steve Weston | Central Body | Missing Archival NFR Information | There is no detailed non-functional requirements in relation to data archiving, retrieval, archival tiers, recovery from archival so we need to update the NFR's to ensure these are included. | Open - awaiting assessment |  | Interim Release 5 | 2023-09-20 | Further details of the solution are under discussion/review. | Clarification
MHHS-DIN-510 | SW |  | 2023-07-18 | MHHS | 2675 | Steve Weston | Central Body | Properties on block B047 | The Swagger definition has the properties ‘sp’,’v’,’q’,’e’ and ‘arc’ which matches the items in red. However the data catalogue has different YAML names. YAML Swagger names have to be updated in DES-138 to match the above characters. | Implemented |  | Interim Release 4 | 2023-08-16 | This was done to reduce IF-021 content size, but the DES-138 5.4.1 YAML needs to be updated to align with Swagger 1.4 - the YAML names should be as follows DI-082 ‘sp’ - B052 (IF-022), B047 (IF-021) DI-147 ’v’ - B047(IF-021, 4, 16) DI-083 ’q’ - B047 (IF-021, 14, 16) DI-076 ’e’ - B047 (IF-021, 14, 16) DI-166 ‘arc’ - B073 (IF-027 / 28) Swagger 1.4 has been updated to align for the approrpiate blocks above to ensure consistency across the data catalogue. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-511 | BK | CR027 | 2023-07-18 | Eastern Power Networks |  | Peter Waymont | Network Operator | DUoS E-Billing DIP Message for MHHS | A new flow needs to be introduced for e-billing of site-specific DUoS in the post Market-Wide Half-Hourly Settlement (MHHS) environment because the existing flow uses the DTN and all other DUoS data will be DIP based. The change is required in order to continue to operate the site specific DUoS billing process in the MHHS environment. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the HH data sent by Data Services to the LDSO for use in DUoS billing, using IF-021/IF-013/IF-014. At present DUoS billing systems can send the D2021 data flow as a form of e-billing for site-specific DUoS, using the DTN. As DUoS billing systems will need to interact with the DIP for migrated site-specific billed customers, it is preferable that the outputs are also DIP messages, to enable the parties to move forward completely in the new environment. A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors) and receivers (suppliers) of the flows has identified the desired flow content and now wish to bring this to the Programme to ensure that it can be delivered in readiness for migration. | Closed |  |  |  | COvered as part of CR019
MHHS-DIN-512 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Amendments to Swagger and ECS data catalogue REP-002 | Max length for DI-345 DUoS Tariff Id to be updated in line with ECS data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated to ensure DI-345 DUoS Tariff ID aligns with ECS Data Catalogue - max length of string = 3. | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-513 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Custom block correction REP-002 | Block name to be updated to tariffCharacteristics in Swagger. | Implemented |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated for REP-002 custom block to fix typo from tarrifCharacteristics to tariffCharacteristics to align with ECS Interface Catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-514 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Amendments to Swagger and ECS data catalogue REP-002a | Max length for DI-345 DUoS Tariff Id to be updated in line with ECS data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated to ensure DI-345 DUoS Tariff ID aligns with ECS Data Catalogue - max length of string = 3. | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-515 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Custom block correction REP-002a | Block name to be updated to tariffCharacteristics in Swagger. | Implemented |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated for REP-002 custom block to fix typo from tarrifCharacteristics to tariffCharacteristics to align with ECS Interface Catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-516 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Update DI-300 with Minimum value REP-003 | DI-300 to be updated in swagger with a minimum value of 100 as per ECS data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | DI-300 updated in Swagger 1.4 with a minimum value of 100 as per ECS data catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-517 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update data item type in ECS data catalogue REP-003 | DI-325 data type to be updated in data catalogue to (NUM 4,2) in line with swagger | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to NUM(4,2) for DI-325. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Cataloue correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-518 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Inclusion of Max/Min value for DI-496-REP-003 | Update ECS data catalogue with Min value of 1 and Max value of 48 | Implemented |  | Interim Release 4 | 2023-08-16 | MIn and Max Column of MHHS ECS data catalogue updated with 1 and 48 respectively. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-519 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Max value change in swagger for DI-496 | Update Max value to 48 for DI-496 in swagger | Implemented |  | Interim Release 4 | 2023-08-16 | DI-496 in Swagger 1.4 updated to have a Max value of 48 | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-520 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-359 data type REP003 | Update DI-359 data stype to String 16 in ECS data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-359. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-521 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-360 data type REP003 | Update DI-360 data stype to String 16 in ECS data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-360. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-522 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-362 data type REP003 | Update DI-362 data stype to String 16 in ECS data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-362. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-523 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-324 data type REP003 | Update DI-324 data stype to String 16 in ECS data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-324. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-524 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | DI-363 missing from ECS data catalogue | Update ECS data catalogue by adding in missing DI-363 | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data catalogue updated with the addition of missing data item DI-363. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-525 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-364 data type in REP003 | Update DI-364 data stype to String 17 in ECS data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-364. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-526 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-365 data type in REP003 | Update DI-365 data stype to String 17 in ECS data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-365. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-527 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-366 data type in REP003 | Update DI-366 data stype to String 17 in ECS data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-366. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-528 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-367 data type in REP003 | Update DI-367 data stype to String 17 in ECS data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-367. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-529 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-368 data type in REP003 | Update DI-368 data stype to String 17 in ECS data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-368. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-530 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Wrong data item referenced in swagger | Wrong data item referenced in R022. Daily Period BM Unit Total Allocated Volume must be changed to BM Unit Allocated Demand Disconnection Volume | Implemented |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 has BM Unit Allocated Demand Disconnection Volume (DI-241) in R022 | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-531 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Data type update in swagger for DI-341 | DI-341 data type to be changed to String 18 as per data catalogue | Closed |  |  |  | Closed. This is defined a Integer in the format 9,6 in Swagger. | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-532 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Wrong data item referenced in swagger | Wrong data item referenced in R022. settlementPeriodID must be changed to Settlement Period | Implemented |  | Interim Release 4 | 2023-08-16 | Updated Swagger 1.4 so that R022 references DI-946 (SettlementPeriod) rather than DI-307 (SettlementPeriodID) | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-533 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-339 data type in REP-003 | Update DI-339 data stype to String 17 in ECS data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-339. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-534 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-369 data type in REP-003 | Update DI-369 data stype to String 17 in ECS data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-369. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-535 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-370 data type in REP-003 | Update DI-370 data stype to String 17 in ECS data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-370. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-536 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-322 REP003 | Update Min column of ECS data catalogue with 0 | Implemented |  | Interim Release 4 | 2023-08-16 | DI-322 Minimum column of MHHS ECS data catalouge updated with 0 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-537 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-322 REP003 | Update Max column of ECS data catalogue with 99.99 | Implemented |  | Interim Release 4 | 2023-08-16 | DI-322 Maximum column of MHHS ECS data catalouge updated with 99.99 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-538 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-323 REP003 | Update Min column of ECS data catalogue with 0 | Implemented |  | Interim Release 4 | 2023-08-16 | DI-323 Minimum column of MHHS ECS data catalouge updated with 0 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-539 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-323 REP003 | Update Max column of ECS data catalogue with 99.99 | Implemented |  | Interim Release 4 | 2023-08-16 | DI-323 Maximum column of MHHS ECS data catalouge updated with 99.99 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-540 | SW |  | 2023-07-14 | Elexon | 2684 | Nigel Rees | Central Body | IF-13 run number | In DES-138, Run Number in IF-013 Interface is 3 chars, yet in Swagger and ECS Reports, this is 7 characters long. We need to update DES-138 to align with Swagger and ECS reports. | Implemented |  | Interim Release 4 | 2023-08-16 | Updated IF-013 to show DI-161 (Run number) as number 7 to be consistent with Data Catalogue/ Swagger and Reports | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-541 | MF |  | 2023-07-19 | ESG | 2623 | Patricia Parker | Software Provider | SSC and Profile Class validation | Validation needs to be reviewed to enable the provision of just SSC or Profile Class updates as part of [SSCandProfileClass] event code updates in IF-025 | Implemented |  | Interim Release 4 | 2023-08-16 | Updated conditionality on IF-025 and IF-026 for DI-122 (Profile Class) and DI-123 (SSC) to "Mandatory for Traditional Meters (if changing)" to allow just SSC or Profile class updates to be provided. Validation rules updated accordingly in IF-025. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-542 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-159 in data catalogue REP004 | Update Min column with 25 in data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | DI-159 Minimum column of MHHS ECS data catalouge updated with 25 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-543 | MF |  | 2023-07-19 | Design Team |  | Mike Fensome | SRO Design | IHD, SMSO, SSC and Profile Class conditional validation | Update validation rules to ensure effective from date is provided when IHD, SMSO, SSC or Profile class are updated | Implemented |  | Interim Release 4 | 2023-08-16 | Added conditionality to IF-025 and IF-026 that DI-136 should be provided where DI-137 is not null and DI-135 should be provided wher DI-134 is not null. Added validation rules to IF-025 to ensure conditionality rules are applied for IHD, SMSO, Profile class and SSC with new error code of REG1088 -Effective from date must be provided | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-544 | SW |  | 2023-07-19 | Siemens | 2633 | Tony Mason | Software Provider | Level 4 Validation - Multiple response codes | Unclear from the current E2E design defined in E2E001 for a Level 4 Response code, whether a single transaction with concatenated Response codes be sent back to the DIP for notification to the publisher? Or, would the expectation be that multiple messages be returned with each message quoting the published transaction number? Or, is this at the discretion of the participant? The E2E design should make this clearer, and also provide fleixbility for multiple messages to be returned against the same transaction ID with a response. | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | This will require updates to the E2E design document to make Level 2 and 4 response code expectations clearer, as well as updated Swagger to allow for an array of messages, help and service tickets to be sent per error, per transaction ID. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-545 | ME |  | 2023-07-20 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-496 data type REP004 | Update swagger to show DI-496 as INT (2) | Implemented |  | Interim Release 4 | 2023-08-16 | Update to data type for DI-496 from INT(3) to INT(2) to align with swagger. Update made to MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-546 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Incorrect data item referenced in swagger- REP004 | Incorrect data item referened in R026. SettlementPeriod ID must be replaced with Settlement Period (DI-496) in swagger | Implemented |  | Interim Release 4 | 2023-08-16 | Updated Swagger 1.4 so that R026 references DI-946 (SettlementPeriod) rather than DI-307 (SettlementPeriodID) | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-547 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Missing data item in swagger | In R026, DI-327 missing from swagger v1.3. Should added and defined as per DT-22 | Implemented |  | Interim Release 4 | 2023-08-16 | Updated Swagger 1.4 to include DI-327 (Deemed Supplier Take). Updated R026 to include DI-327 and remove DI-325 so this aligns with ECS Data Catalogue. | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-548 | MH |  | 2023-07-20 | Elexon | 1966 | Rashmi Radhakrishnan | Central Body | Clarification of ISD Transition Requirements | Following MTDSG release of the BRS001 Transition approach and Parallel running requirements v2, ISD would like programme to consider rewording below requirement for more clarity. MHHTR-22 Original: The ELEX-REP-005 Line Loss Factor report will be published at a location on the BSC website/ ELEXON Portal and the URI shall be notified using the Notification of the Publication of a Downloadable Asset IF-047 / PUB-047 to DIP Users prior to M10 and continue post M15. MHHTR-27 Original: The new ISD entities shall be updated be published at a location on the BSC website/ Elexon Portal and the URI shall be notified using the Notification of the Publication of a Downloadable Asset IF-047 / PUB-047 to DIP Users from M10. | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Internal discussion required between Elexon, KS and MH to reword the requirements to reflect the baselined BAU requirements more closely. Session to be arranged once Transition requirements have been handed over to Elexon. 31/08: A session has been arranged with Elexon/MH/ME on Tuesday 5/09 to discuss this DIN and the rewording for the the requirements. | Design Ambiguous | Supporting Docs | ISD Document | ISD Document EDI-021
MHHS-DIN-549 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Incorrect data item referenced in R033 | SettlementPeriodID should be replaced with SettlementPeriod (DI-496), with a MIN value of 1 and Max of 48 in swagger | Initial Assessment/Updating |  | Interim Release 7 | 2024-01-19 | Solution under review/discussion | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-550 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Missing R007 from REP007 | Include R007 within REP007 in swagger | Initial Assessment/Updating |  | Interim Release 8 | 2024-03-20 | Solution under review/discussion | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-551 | ME |  | 2023-07-20 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-083 | Include Min Value of 1 and Max value of 5 to DI--083 in ECS data catalogue to align with swagger and IF data catalogue | Implemented |  | Interim Release 4 | 2023-08-16 | DI-083 Minimum and Maximum column updated with 1 and 5 respectively in MHHS ECS data catalouge Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-552 | SW |  | 2023-07-20 | IMServ | 2356 | Liam Lowey | Software Provider | UTF-8 Encoding for JSON | The E2E001 design document does not specify Encoding for JSON. This needs to be updated to reflect UTF-8 as the JSON Encoding required. | Implemented |  | Interim Release 4 | 2023-08-16 | Add UTF-8 as the JSON encoding required in the E2E001 design document, creating a new section 4.2.5. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-553 | RS |  | 2023-07-20 | Design Team | 2627 | Rob Short | Central Body | Secondary routing for Export | Secondary routing rules need to be updated to allow notification of work prgressed by the Import suppllier (eg disconnection). review required of all related interfaces | Closed |  |  |  | Following review no document changes required. Re Specific case of Disconnection the Link between Import and Export would need to be removed prior to any Disconnection request. If the link remains in place then the DIsconnection request will be rejected by LDSO/REGS.
MHHS-DIN-554 | MF |  | 2023-07-20 | SCS |  | Madison Layton | Software Provider | Validation on Customer Direct Contracts | Revisions to CDC functionaility. - Amend validation to ensure that only one Customer Direct Contract can be applied against an MPAN at any moment in time - Move CDC process(s) onto a new BP10 process map so as to make it clearer that CDC is MPAN not appointment based - add supporting process info to new BP | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. Process map emailed to particpants - added to BP010E and validation rules for IF-038 updated accordingly Agreed changes with SCS, awaiting feedback from RECCO | Design Ambiguous | Supporting Docs | Supporting Docs | BP10 Registration Updates DES138 - Interface Catalogue
MHHS-DIN-555 | MF |  | 2023-07-20 | SCS |  | Madison Layton | Software Provider | Validation of MPID to DIP ID | Carry out validation of MPID to DIP ID during initial IF-031 validation only. | Implemented |  | Interim Release 4 | 2023-08-16 | Set REG1090, REG1091 and REG1092 validation in IF-031 to "No" for Queue processing so it only applies to IF-031 validation. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-556 | KH |  | 2023-07-21 | Stark | 2112 | James Murphy | Supplier | Cumulative/Total Consumption Comparison | The “Cumulative/Total Consumption Comparison” that can be carried out instead of a MAR for meters with integral Outstations is not defined anywhere In BSCP502 it is defined at 4.1.5 – I think this should be lifted and shifted into METH002 Interestingly it appears to be described in the SDS Validation & Estimation Statement (METH001) at 3.12 – 3.16 ADS Method Statement (METH002) needs to be updated | Implemented |  | Interim Release 4 | 2023-08-16 | ADS Method Statement has been updated with "Reconciliation for smart Meter Advance Reconciliation" section 2.21 - 2.25. | Method statement correction | Supporting Docs | Method Statement | METH002 ADS Validation Estimation
MHHS-DIN-557 | RS |  | 2023-07-21 | Elexon | 2745 | Rashmi Radhakrishnan | Central Body | Consistency of the used of ID | Version 5.1 ISD EDI021 Entity specification document, has discrepancies in the usage of ID, Id, id, etc. Inconsistencies to be addressed when updating the design artefact in the future. ISD Entity M3 Usage of ID and Id - Market Participant ID in the table and description are different ISD Entity ID 17 - DUoS Tariff Id GSP Group Id - ISD Entity ID 17 - DUoS Tariff Id table - GSP Group id is with lowercase "i" and Entity Id M4 Load shape categories : GSP Group Id is mentioned as GSP Group ID ISD Entity ID 17 - DUoS Tariff Id Usage of DUoS Id and DUoS Tariff Id ISD Entity Id 4 and 17 - has ID in capital letter Usage if ID and Id to be consistent Entity M4 GSP Group ID- but should be GSP Group Id ISD Entity Id M5 - MHHS Consumption Component Classes CCC ID - for consistency it should be CCC Id | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | All instances of lower /mixed case id have been replaced with "ID" in caps | Data Interface correction | Supporting Docs | Support Docs | ISD Document EDI-021
MHHS-DIN-558 | BK | DI-189 | 2023-07-21 | SCS | 2011 | Madison Layton | Software Provider | Update response codes in IF-035 | IF-035 routing rules references response codes AC and RJ, this should be A and R | Implemented |  | Interim Release 4 | 2023-08-16 | Updated Routing rules in IF-035 to refer to Response code of "R" and "A" for event code [SDS-MDROutcome] rather than "AC" and "RJ" | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-559 | SC |  | 2023-07-24 | SCS |  | Sean Cooper | SRO Design | Clarification of Appointment Scenario Code (Linked MPANs) | Added clarification to IF-036 to confirm that the Appointment Scenario Code used for Secondary MPANs will mirror that applied to the Primary MPAN (eg COS/CSP/Etc). What will be applied in the case of Auto Alignment ? | Implemented |  | Interim Release 4 | 2023-08-16 | Added clarification to IF-036 to confirm that the (DI-800) Appointment Scenario Code used for Secondary MPANs will mirror that applied to the Primary MPAN (eg COS/CSP/Etc). In cases of Auto-Alignment of MPANs the Appointment Scenatio of (ALG - Auto Alignment of MPAN Service Providers) will be applied. ALG added as allowable value in DI-800 ( Data Catalogue and Swagger ) | Design Clarificarion | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue Swagger 1.4
MHHS-DIN-560 | SC |  | 2023-07-24 | SCS |  | Sean Cooper | SRO Design | Design Gap on Sharing MTD in the Case of AutoAlignment of Service Providers | The Design allows for the Auto-Alignment of Service Providers in certain circumstances. However a design gap exists that there is currently no trigger for the outgoing MS to send MTDs to the incoming MS in the case of a pure Auto-Alignment (ie no other MPAN transaction eg. COS/CSP) | Implemented |  | Interim Release 4 | 2023-08-16 | Proposal is to create a new requirements (MS-098 / MS-099) on Smart and Advanced Metering Services to trigger sending of D0149/D0150 (trad) or D0265 (Adv), on receipt of a PUB-037 with De-Appointment Reason Code of “RELATED” or “IMPEXP”. D-Flow(s) should be sent, via DTN, to the new/incoming MS referenced in the PUB-037 flow, where available Issue does not arise for Smart sites as MTDs are fully convayed using the PUB-036. Also not a concern for UMSDS as no MTDs exist. | Design Clarificarion | Minor | MPAN Ownership | BRS-002 Metering Service Requirements
MHHS-DIN-561 |  |  | 2023-07-24 | SCS |  | Sean Cooper | SRO Design | Disconnection of Linked MPANs | No change to desgin required. Design confirmation only. SCS have confirmed that it will be necessary to de-link and MPRN before being able to action a disconnection on it. i.e. Disconnection cannot be performed on a linked MPAN until such time as all links have been removed via (IF-019/IF-020) | Closed |  |  |  | No change Required - Clarification Only
MHHS-DIN-562 |  |  | 2023-07-24 | SCS |  | Sean Cooper | SRO Design | Clarification of IF-014 R0 Population for Event Code [ConsumptionOnDeEnergisedMPAN] | Confirmation at an R0 will be required when issuing an IF-014 with Event Code [ConsumptionOnDeEnergisedMPAN]. DI-979 should be populated with value 'W', DI-980 would remain blank. | Implemented |  | Interim Release 4 | 2023-08-16 | IF-014 updated to clarify that DI-979 should be populated with W. Data Catalouge and Swagger v1.4 updated to reflect this. | Design Clarificarion | Minor | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-563 |  |  | 2023-07-24 | Elexon | 2705 | Ayo O (Helix) | SRO Design | Clarification on Helix Treatment of IF-021 error condition data. | Clarification is required from Helix on exactly how they will manage and process IF-021 messages and how any resulting error/rejections will be managed. This is so that clear guidance can be drawn up on participants should expect to receive errored data etc. In any event design team are clear "the data returned in the IF-014 must only be that data which is rejected." | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | A response was provided to Ayo on 24/07 by design team. Follow up email has been sent for Ayo to confirm whether issue is resolved, thus closing the DIN or whether a call is required with Design team for further resolution.. | Design Clarificarion
MHHS-DIN-564 | SW |  | 2023-07-17 | SIMS | 2704 | Martin Freeman | Central Body | Mandatory Nullable on Swagger | Is Mandatory Nullable (which is how 'optional' properties are described in the DES183) supposed to be marked as Required & nullable in Swagger? Or should these Mandatory Nullable (optional) properties be marked 'not Required' in Swagger? In some interfaces Mandatory Nullable properties are marked 'not required' in Swagger while in others they are 'nullable required'. Need to ensure this is applied consistently across all Interfaces. | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Need to update Swagger implementation so mandatory nullable is treated consistently across all Interfaces as this is not always consistent. Need to updated E2E001 to provide additional clarity on how this applies to Swagger. Need to ensure DES-138 is aligned. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-565 | SW |  | 2023-07-25 | MHHS | 2763, 2713 | Steve Weston | SI Design | Version and Schema Interoperability across environments. | Versioning is covered in Section 8.4 and 8.5 of the E2E001 design, that covers the differences between major, minor and patch versions of an API, the URL required as well as schema versions that are contained in the common block of an Interface. There is confusion around how this will work across different environments so we need to provide additional clarity on the Swagger API versions / Schema versions that must be supported by the DIP and MP’s, alongside scenarios that are envisaged. This will provide information on version uplifts, interoperability required and how long different versions of API / Schemas will be supported for. This needs to covers scenarios where within an environment, we have multiple versions of an API within an environment ie, we may be required in some cases to be backwards compatible with previous versions -- for example -- if we received and processed earlier versions, we can respond with the latest live version. E.g. if we receive PUB-005 on version 1.0.0 we could respond with IF-006 on version 1.0.1 and would not be expected to respond with version 1.0.0. | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Need to provide updates to Section 8.4 and 8.5 to ensure we cover worked examples across different environments for both API versions and Schema versions, interoperabilty required, transition between versions, BAU vs Testing phases and expectations on DIP and MP's. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger 1.4 | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-566 | SW |  | 2023-07-25 | MHHS | 2549 | Steve Weston | SI Design | E2E NFR's need to refined based on actual data | Section 3.1 of MHHS DES001a MHHS Data Integration Platform – Functional Specification – Appendix A Transaction Volumes states that the indicative size of an IF-021 (single days' worth of UTC SP data) is between 1 and 2 KB. The equivalent IF-021s we have successfully submitted to the DIP Simulator are ~4.5 KB as observed in webhook. Can you confirm that this increase in size has been factored into the non-functional requirements? | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Need to update MHHS Data Integration Platform – Functional Specification – Appendix A Transaction Volumes and Non Functional Requirements to update message sizing based on actual numbers. | Design Ambiguous | Supporting Docs | MHHS Data Integration Platform – Functional Specification – Appendix A Transaction Volumes | MHHS Data Integration Platform – Functional Specification – Appendix A Transaction Volumes
MHHS-DIN-567 | SW |  | 2023-07-25 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - Swagger Incorrect | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4. Swagger 1.4 needs to be updated so that it aligns with DES-138. DI-081 to be updated to periodDuration. DI-086 to be updated to supplierEffectiveFromDate. DI-121 to be updated to supplierEffectiveToDate. | Implemented |  | Interim Release 4 | 2023-08-16 | Need to update mismatch between Swagger YAML definition in DES-138 and Swagger 1.4. Swagger 1.4 needs to be updated so that it aligns with DES-138. DI-081 to be updated to periodDuration. DI-086 to be updated to supplierEffectiveFromDate. DI-121 to be updated to supplierEffectiveToDate. | Design Ambiguous | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-568 | SW |  | 2023-07-26 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - DES-138 incorrect | DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) shows in YAML as secondaryRecipientDIPID and primaryRecipientDIPID respectively and this should be updated in DES-138 YAML column so this aligns with Swagger 1.4 ie, DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) | Implemented |  | Interim Release 4 | 2023-08-16 | DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) shows in YAML as secondaryRecipientDIPID and primaryRecipientDIPID respectively and this has been updated in DES-138 YAML column so this aligns with Swagger 1.4 ie, DI-981 (secondaryRecipients) and DI-982 (primaryRecipients). | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-569 | SW |  | 2023-07-26 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - DES-138 incorrect | DI-047, DI-049, DI-210, DI-211 and DI-820 are defined in the Data Catalogue, but not used in any Interfaces so need to be removed from the latest version of DES-138. | Implemented |  | Interim Release 4 | 2023-08-16 | DI-047, DI-049, DI-210, DI-211 and DI-820 are defined in the Data Catalogue, but not used in any Interfaces so need to be removed from the latest version of DES-138. DES-138 needs to be updated to remove these items. | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-570 | MF |  | 2023-07-26 | MHHS |  | Mike Fensome | SRO Design | IF-021 validation rules | IF-021 validation rules need to be updated to align to the MDS and LSS Method statements which include validation for de-energised sites. | Implemented |  | Interim Release 4 | 2023-08-16 | IF-021 Added validation to align with MDS/LSS method statements where estimated data is provided on a de-energised site (ECS1008 - SP End Date/Time [DI-082] contains non-actual consumption for ECS De-Energised MPAN) | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-571 | SW |  | 2023-07-27 | Callisto | 2762 | Dave Peat | Software Provider | Inconsistency for DI-980 Response Message(s) | For DI-980, the YAML name is responseMessages, however in Swagger, there is inconsistencies: R0.responseMessages - this is defined as array of DI-980 (responseMessages) B066.responseMessage - but defined as responseMessages (defined as DI-980 - single) B092.responseMessage - defined as responseMessage (defined as DI-980 - single) We need to update DES-138 / Swagger so there is consistenct application of the words responseMessage (for single response) vs responseMessages (where there is an array of responses). | Implemented |  | Interim Release 4 | 2023-08-16 | I have updated Swagger 1.4 so that DI-980 definition is applied consistently for single response vs array of responses. For single, it will be responseMessage. For an array of messages, it will be responseMessages. To this effect, B066.responseMessages has been updated to be responseMessage. Also, B066 block has been updated to align with DES-138 to be conditionally mandatory, rather than mandatory. | Supporting Docs | Design Ambiguous | Supporting Docs | Swagger 1.4 | DES138-InterfaceCatalogue
MHHS-DIN-572 | SC |  | 2023-07-27 | MHHS |  | Sean Cooper | SRO Design | Clarification of IF-013 Issuance | Clarification is requiired on the circumstances when Helix will issue IF-013. 1. IF-013 is only issued as part of the RF Run i.e. simply to notify Suppliers of what the default consumption for a period(s) is, where no data has been submitted by the DS come the point of RF. … … Should suppliers wish to derive this for pre-RF settlement runs then they are able to do so easily enough using the own data and the published Load Shapes. 2. The second view is that the IF-013 is issued on every settlement run undertaken for sites where no PUB-021 data has been received DIP impact concerns would need to be addressed if Option 2 is the position. | Open - awaiting assessment |  | Interim Release 5 | 2023-09-20 | Further details of the solution are under discussion/review. | Clarification
MHHS-DIN-573 | ME |  | 2023-07-27 | MHHS |  | Kevin Spencer | SRO Design | Update to step 40 of ISD BPM/BPD | Step 40 of MHHSP-BP021 and BPD021 currently ambigious Can the intention of this step be made clearer.? | Implemented |  | Interim Release 4 | 2023-08-16 | Step 40 of ISD BPM and BPD have been updated to say 'Issue ISD Change Notification' to make ithe purpose of the step clearer. | Design Ambiguous | Minor | Supporting Docs | MHHSP-BP021 Industry Standing Data MHHSP-BPD021 Industry Standing Data Business process Descriptions
MHHS-DIN-574 | SC |  | 2023-07-27 | SCS |  | Madison | SCS | Change Of Logic on Smets 1 Number of Digits | Smets 1 Number of digits can be 0 - 9 Replaces previous logic. | Closed |  |  |  | DIN CLOSED as agreed with St Clements and RECCo. DIN-615 supercedes this DIN. The text has been updated as suggested below from RECCo, ‘Where the Meter Type is S1, the value should be populated as per the manufacturer specification.’ However, the logical test for SMETS1 in the DES-138 Interface Catalogue will remain unchanged. DIN-615 also includes updating the Swagger validation of this field to match SCS logical test i.e. value can be 0-9. | No Change
MHHS-DIN-575 | SC |  | 2023-07-27 | SCS |  | Madison | SCS | Requirment for REGS to process IF-040 | SCS would prefer not to process IF-040 now that AC is provided to EES Directly via the DIP. In additional what is the IF-040 processing schedule? | Requires Industry Work Group review |  | Interim Release 6 | 2023-10-18 | SCS to raise at DRG for initial feedback, ahead of raising formal CR
MHHS-DIN-576 | MF |  | 2023-07-27 | SCS |  | Madison | SCS | Cancelling appointments in advance of receipt of PUB-034 | SCS have requested that the design is updated to allow for issuing of a PUB-035 'Lapsed' message, if a switch is 'Cancelled' or otherwise superseded, even prior to issuing / processing of a PUB-034 from the Metering Service or Data Service. ​ | Closed |  |  |  | Following DRG on 4th Aug, it was agreed that St Clements Services were to work-up the topics discussed, and a dedicated workshop would be arranged to discuss this further. St Clements Services have advised the Programme that they will now not be pursuing proposals made at the DRG session and would be reverting to implement to the original design, therefore closure of this DIN.
MHHS-DIN-577 | SW |  | 2023-07-27 | Callisto | 2979 | Neil Edney | Software Provider | DT-983 and DT-000 are missing IF-040 / PUB-040 | DT-983 and DT-000 are missing IF-040 / PUB-040 in Swagger. IF-003, 19, 20 and 50 also need to be added to align with DES_138. | Implemented |  | Interim Release 4 | 2023-08-16 | Need to update Swagger to include IF-040 and PUB-040 in DT-000 and DT-983. I’ve added IF-003 / 019 / 020 / 040 / 050 to DT-000 in Swagger and PUB-003 / 019 / 020 / 040 / 050 to DT-983 in Swagger | Supporting Docs | Design Ambiguous | Supporting Docs | Swagger 1.4
MHHS-DIN-578 | SB |  | 2023-07-28 | RECCo | 2943 | Jonny Moore | Central Body | EFDs, ETDs and Supplier information for Related and Import/Export Linkages | We’ve noticed through the design and build stage of EES that we are not being communicated the EFD and ETD of a Related MPAN set-up or an Import / Export Linkage. Nor are we being informed of the Supplier responsible for creating a Related MPAN relationship. This information is not currently being published in the IF020/PUB020 However, this information is currently available for market participants to view on EES. We had some feedback in the REC MSAG that participants would like to continue to view these items in EES and wonder if this is worth a DWG discussion? | Closed |  | Interim Release 5 | 2023-09-20 | THe Effective From date is not currently shared on the D0386 which was the basis for the IF-019/PUB-020. If EES requires an EFD suggest that the transaction date from the header is used. These updates can only be made by the current Supplier.
MHHS-DIN-579 | SB |  | 2023-07-28 | ENWL | 2444 | Paul Stancliffe | Network Operator | PUB-043 Routing discrepancy | Trying to map flow PUB-43 to our TO BE business processes as these flows are showing on the MHHS - Interface Data Item Catalogue as routing to LDSO. However when trying to align these to the Business Process Diagram BPM011- Change of Connection Type and / or Market Segment V5.0 PUB-43 is not routing to LDSO | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | BP011B from Step 542 new flow for PUB-043 to LDSO new step Manage Change of Connection type Notification | Process Model correction | MPAN Ownership | Supporting Document | BP011B
MHHS-DIN-580 | RS |  | 2023-07-28 | RECCo | 2719 | Sarah Jones | Central Body | Late or Missing Secured Active Messages | understand the approach to managing CSS issues where secured active messages are not received within the expected secured active processing window. We understand the standard ‘happy path’ processing requires secured active notifications to be issued by CSS after the 5pm gate closure window the day before the registration effective from date. However, it was acknowledged when the MHHS design was originally baselined that some notifications may arrive late e.g. after 6pm, or not at all. Rather than developing operational provisions to deal with missing / late secure active notifications, this was highlighted as a risk for later consideration, on the basis the CSS arrangements were still new and the enduring BAU process was subject to change. In light of the CR018 approval, we believe this is now the time to clarify the approach to be taken where CSS notifications are missing or late. | Closed |  |  |  | The Design Team and SRO are actively engaged with St Clements on issues around problematic switches. The plan is for them to provide us with a list of of their issues. We will then go through a process of raising these directly with CSS. Dependent on outcomes we receive back, we will look to discuss this with St Clements with the possibility of raising a CR for a specified data correction tool to align the data and send out the appropriate MHHS flows. | No Change
MHHS-DIN-581 | RS |  | 2023-07-28 | ESG | 2924 | Patricia Parker | Software Provider | Meter Location in DES138 | Currently DI090 in DES138 states 'Values as Per ISD'. These values are not held in ISD, therefore the reference should be changed to 'see Enum Values of the Data Catalogue' - example IF-005 | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Updated population notes for DI-090 to refer to Data Catalogue | Clarification | Supporting Docs | Interfaces | DES-138 Interface Spec
MHHS-DIN-582 | MF |  | 2023-07-28 | Ovo |  | Chris Butterfiled | Supplier | Clarification following CR15 | Supplier Overview requirements v5.1: this refers specifically to Economy 7 / Economy 10 tariffs; we suggest this should be more general and refer to any Time of Use tariff / tariff with switched load to include other variants such as Smart Economy 9 etc. | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Updated SU-163, SU-164 and SU-165 to refer "for switched load tariff (eg. Economy 7/Economy 10) sites" rather than Economy 7/Economy 10 sites | Clarification | Supporting Docs | Interfaces | DES-138 Interface Spec
MHHS-DIN-583 | SB |  | 2023-07-31 | Stark | 2891 | Jon Dennis | Data Service Provider | BP005 Read Sharing for Data Service | can you provide clarification around BP005 Read Sharing for the Data Service, in particular this section of MHHSP-BP005-Data Processing-v5.1 Question: Is the entry point to this section either: Regular Data Collection, e.g. daily remote collection for ADS/SDS Smart? Trigggered by an external process, e.g. Change of Energisation BP009? To answer the above, please can you list all of the processes that lead to Step 170 in BP005. May I also suggest updating BP005 to include this information, perhaps by adding a Step description to the entry point from Data Collection as shown above. Related Question: In BP009 the Data Service is expected to progress to BP005 Step 185. However, unless I am mistaken, BP005 V5.2 does not include Step 185. Please update BP009 with a valid onward step. | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18
MHHS-DIN-584 | SC |  | 2023-07-31 | Design Team |  | Sean Cooper | SRO Design Team | DI-511 Change of Data Type from String to Number in IF-024 | DI-511 Off Peak Declaration Proportion has been changed from String to Number so as to allow for improved Swagger validation of this data item. The new Number val will have a Minimum value = 0 and a Maximum Value = 100. | Implemented |  | Interim Release 4 | 2023-08-16 | DI-511 Off Peak Declaration Proportion has been changed from String to Number so as to allow for improved Swagger validation of this data item. The new Number value will have a Minimum value = 0 and a Maximum Value = 100. (IF-024). Data Catalogue updated accordingly. | Improved Validation of Data Item | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-585 | SC |  | 2023-07-31 | Design Team |  | Sean Cooper | SRO Design Team | Clarification on IF-024 | Clarification update to confirm that B097 Off Peak Declaration is Mandatory only for Event Type [SN-OffPeakDec] | Implemented |  | Interim Release 4 | 2023-08-16 | Clarification update to confirm that B097 Off Peak Declaration is Mandatory only for Event Type [SN-OffPeakDec] | Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-586 | SW | DI-204 | 2023-07-31 | Callisto | 2762 | Neil Edney | Software Provider | Mis-alignment between D0 block YAML in Swagger and DES-138 | DES138, the D0 has the following YAML names which do not align DIPCorrelationID, DIPTimeStamp, DIPTransationID However, swagger has these: initialCorrelationID, transactionTimestamp, transactionID | Implemented |  | Interim Release 4 | 2023-08-16 | Updated DES138 Data Catalogue D0 Common block data items so that YAML names in DES-138 now align with Swagger initialCorrelationID (DI-987), transactionTimestamp (DI-989), transactionID (DI-990) | Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-587 | SW |  | 2023-08-01 | Kraken | 2973 | Angelos Rizoyannis | Software Provider | Mis-alignment between R0 mandatory in Swagger vs DES-138 | In DES-138 in the following interfaces, R0 is marked as mandatory, but not mandatory in Swagger - IF-006, IF-008, IF-014, IF-020, IF-026, IF-028, IF-032, IF-039. | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | In DES-138 in the following interfaces, R0 is marked as mandatory, but not mandatory in Swagger - IF-006, IF-008, IF-014, IF-020, IF-026, IF-028, IF-032, IF-039. Update R0 to be mandatory in these interfaces. | Clarification | Minor | Interfaces | Swagger 1.5
MHHS-DIN-588 | ME |  | 2023-08-02 | Design Team |  | Kevin Spencer | SI Design | Update of ID to Id | A request has come from Elexon to update the ISD Entities document. ID should be changed to Id | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | All instances of ID have been changed to Id | Supporting Document | Minor | Supporting Document | MHHSP_EDI021_ISD_Entities v5.3.2
MHHS-DIN-589 | SB |  | 2023-08-02 | Stark | 2466 | Jon Dennis | Data Service Provider | ADS and SDS Estimation Statements | I have been studying the following two documents: Advanced Data Service Validation and Estimation: Methodology Statement (MHHSP-METH002_ADS_Validation_Estimation v5.1) Smart Data Service Validation and Estimation: Methodology Statement (MHHSP-METH001_SDS_Validation_Estimation v5.1) In particular, Section 3 of the ADS_Validation_Estimation document details the estimation methods where the customer has opted-out of UTC Period consumption data. It references the SDS_Validation_Estimation document where Estimation methods are in Section 7. The 2 method statements have become misaligned when changes to the SDS method statement was updated. | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | We will align the ADS method statement with the SDS method statement to keep it uniform. | Method statement correction | Supporting Docs | Method Statement | ADS Method Statement SDS Method Statement
MHHS-DIN-590 | KH |  | 2023-08-03 | MHHS | 2717 | Martin Freeman | Central Body | Update Role Codes in E2E001 | There is a mismatch between roles codes that are in DES-138 and those that are in E2E001. Role code for Unmetered Supplies Data Services changed from UDS to UMSDS. Need to ensure that all of the role codes referenced in DES-138 are included in E2E001 and that there is a full explanation of what these are. | Open - awaiting assessment |  | Interim Release 5 | 2023-09-20 | Update all the role codes referenced in DES-138 to ensure they are included in E2E001 and that there is a full explanation of what these are. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-591 | KH |  | 2023-08-03 | Elexon | 2974 | Michael Ceney | Central Body | Update to MDS Method statement | The MDS Method Statement Section 2.1 should read: If SP End Date/Time [DI-082] > MDS Run Date (RF) as specified for the SP End Date/Time [DI-082] in the Master Settlement Table in ISD ECS1003 - SP End Date/Time [DI-082] is older than/after to "MDS Run Date (RF) [ISD.RunDate-RFDate]" | Open - awaiting assessment |  | Interim Release 5 | 2023-09-20 | Update MDS Method Statement Section 2.1 to read If SP End Date/Time [DI-082] > MDS Run Date (RF) as specified for the SP End Date/Time [DI-082] in the Master Settlement Table in ISD | Data interface correction | Supporting Docs | Supporting Docs | MDS Method Statement DES138
MHHS-DIN-592 | SW |  | 2023-08-03 | MHHS | 2717 | Martin Freeman | Central Body | Update StatusMessage and StandardResponseBody in E2E001 to provide more clarity | There are inconsistencies between StatusMessage / Standard Response body definitions for what is contained with E2E001 and Swagger, these need to be aligned. Clarity needs to be provided on how TransactionID is populated in Status Message for Level 2 validation and Level 4 validation and for Level 4 validation, how this is sent to original sender. | Open - awaiting assessment |  | Interim Release 5 | 2023-09-20 | Align inconsistencies between StatusMessage / Standard Response body definitions for what is contained with E2E001 and Swagger. Provide clariry on how TransactionID is populated in Status Message for Level 2 validation and Level 4 validation | Data interface correction | Supporting Docs | Interface Catalogue | E2E001 MHHSP-DES138-Interface Catalogue
MHHS-DIN-593 | ME |  | 2023-08-04 | MHHS |  | Kevin Spencer | SI Design | Update to AC Method Statement | Update required to the AC Method Statement to amend calculation where less than 365 days of data is available and a change to section 2.2 to allow calculations to be undertaken on Calendar days | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | The following changes below in red have been made to section 2.2 of the AC Method Statement The Market-wide Data Service (MDS) should schedule the calculation of MPANs requiring a new Annual Consumption for active MPANs evenly across each working day of the month and publish on the first available working day following the calculation. The recalculation shall be performed each month, for every MPAN and every 30 Calendar days +/- 5 Calendar days of the date of the previous calculation. Changes to the calculation of less than 365 days available are no longer reuried as agreed with Heix | Method statement correction | Supporting Docs | Method Statement | Annual Consumption Meth 10
MHHS-DIN-594 | SC | SCS DI-207 | 2023-08-04 | MHHS |  | Sean Cooper | SRO Design | Correction to BP10 Related MPANs | Rejection was incorrectly shown being sent direct from REGS rather than from REGS Via DIP. | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Rejection was incorrectly shown being sent direct from REGS rather than from REGS Via DIP. | Process Model correction | MPAN Ownership | Supporting Document | BP010-Registration Updates
MHHS-DIN-595 | SC | SCS DI-208 | 2023-08-04 | MHHS |  | Sean Cooper | SRO Design | Correction of Type in ISD Doc Table 16 | Correction of type in definition of subscript 3 for table M16 - "Market Participant ID" changed to "Market Participant Role" | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Correction of type in definition of subscript 3 for table M16 - "Market Participant ID" changed to "Market Participant Role" | Clarification | Supporting Docs | Interfaces | E2E001 MHHSP_EDI021_ISD_Entities
MHHS-DIN-596 | SC |  | 2023-08-04 | MHHS |  | Sean Cooper | SRO Design | Clarification of SP Appointment Time(s) | Per DRG decision all SP Appointment times shall be effective from Midnight UTC Time. Clarification added to IF-031/If-036 | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Added validation rule to IF-031 to ensure appointments are made at midnight UTC. Added clarification on Regs Notes tab. | Clarification | Supporting Docs | Interfaces | DES-138 Interface Spec
MHHS-DIN-597 | SC | SCS DI-193 | 2023-08-07 | MHHS |  | Sean Cooper | SRO Design | IF-026 B068 Presence | IF-026 / B068 - SCS requested removal of wording "must be required for smart meter removed" as this is inherent as part of the Event Type. | Implemented |  | Interim Release 4 | 2023-08-16 | IF-026 / B068 - SCS requested removal of wording "must be required for smart meter removed" as this is inherant as part of the Event Type. | Clarification | Supporting Docs | Interface Catalogue | DES-138 Interface Spec
MHHS-DIN-598 | SC | SCS DI-176 | 2023-08-07 | SCS |  | Madison Layton | Software Provider | Incoming Supplier Notifications - Clarification | SCS raised a query around whether certain flows should be copied to an incomming Supplier (PUB-006, PUB008 etc. etc.) The current design does not include copying of these flows to an incoming supplier, (not represented in either Requirements or BP maps). IF-036 (and accompanying D-flows as required) provides suppliers with a clear starting point containing all the information they need to support servicing the customer. Design Team feel any change in this area would require a CR. | Closed |  |  |  | Any change in this area would require changes to the REGS Requirements to implemnt Primary Routing, as copying of such flows could not be performed by DIP Secondary Routing. CR would be required to confirm new requirements and allow for IA on REGS and Suppiers design. Design Team also note that no other issues/DIN raised on this issue, by suppliers or other participants. | Clarification | Clarification - No change Required
MHHS-DIN-599 | BK | SCS DI-198 | 2023-08-07 | SCS |  | Madison Layton | Software Provider | Data Cleansing required on IHD, SMSO and Installation Date | SCS raised a a query on the three items below that are not under the Data Cleanse Plan that may need cleanse work. 1) IHD - Should be populated for smart meters, and only smart meters (not currently validated) 2) SMSO - Should be populated for smart meters and only smart meters (not currently validated) 3) Installation date - Should not be prior to MPAN Creation date (Legacy data integrity issues of meters migrated into MPRS) | Closed |  |  |  | This change has been forwarded onto the Data Cleansing Working Group as it is not a design issue. Design Team also advised SCS to raise these issues within the working group. | Clarification | Clarification - No change Required
MHHS-DIN-600 | ME |  | 2023-08-07 | Elexon | 4566 | Rashmi Radhakrishnan | Central Body | ISD Entity M18 Discrepancy | In the ISD Entity Document the table shows {Effective From Date {DIPRole} and {Effective To Date {DIPRole}, however the exmaple table and column details have been titled as {Effective From Date {MP2DPM} and {Effective To Date {MP2DPM}. These should be changed to align with the first table in entity M18 | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Corrected M18 Col Headings to read "DIPRole" | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-601 | SW |  | 2023-08-07 | Kraken | 4485 | Adrian Serban | Software Provider | Incorrect on M0 common block in IF-018 | In Swagger, it appears the block is correct (M0), but the label is incorrect (M1) for IF-018. The label needs to be updated to M0 to align with the block. This needs to be updated in Swagger so the label is incorrect. In IF-019 and IF-020, there is an inconsitency of use of M1 vs M0. | Closed |  | Interim Release 5 | 2023-09-20 | M1 is used in IF-019 and IF-20. M0 is used in all other IFs where required. Swagger version 1.4 has been reviewed and correctly reflects this position.
MHHS-DIN-602 | RG |  | 2023-08-08 | SRO |  | Rob Golding | Programme | Add Interface, Event Code enumeration to Swagger for interface blocks | Interface and Event code validation and alloawable blocks is missing from the DIP. Rather then getting Avanade to code these dependencies the proposal is to intoduce the restrictions into the Swagger | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Update the swagger for the majority of interfaces where different event codes require different combinations of optionality for the blocks they reference. An example of this has been done already for IF-001 in the new swagger file Interface-001. Estimate 3/4 days effort to complete | Improved error trapping at interface | Minor | Interfaces | Swagger, possibly add clarification to DES138
MHHS-DIN-603 | SW |  | 2023-08-09 | MHHS | 4022, 4700 | Steve Weston | Central Body | Clarity on A0 block being removed | Section 4.2.1 of the E2E001 design has a diagram that shows that the A0 common block is removed by the DIP prior to sending out the message to onward particpants. This is inconsistent with the rest of the design. Section 4.2.1 needs to be updated so that this shows A0 not being removed. | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Update Section 4.2.1 of E2E001 so that this shows A0 not being removed | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger 1.4 | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-604 | SW |  | 2023-08-09 | MHHS | 4945 | Steve Weston | Siemens | Clarity on B066 mandatory on IF-035 | In DES-138, B066 block in IF-035 is shown as mandatory and also defined as mandatory in Swagger. This should be conditionally mandatory as per B019, so this needs to be updated to conditionally mandatory in DES-138 and also in Swagger 1.5. | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Update B066 block in IF-035 to conditional mandatory in DES-138 and Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-605 | SC |  | 2023-08-09 | MHHS |  | Sean Cooper | SRO Design | Update "Switch Cancellation" Info Message Box of BP002 & BP003 | Message updated to make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations will be held awaiting completion of PUB-34 processing. | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Message updated to make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations will be held awaiting completion of PUB-34 processing. | Clarification | Minor | Interfaces | BP002 / BP003 Change of SP
MHHS-DIN-606 | SC |  | 2023-08-09 | MHHS |  | Sean Cooper | SRO Design | Update Ops C to include clarification on issuing of IF-035 | make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations will be held awaiting completion of PUB-34 processing. | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Update OPS Choreography document to clarify processing of IF-035 | Clarification | Supporting Docs | Supporting Document | OPS Choreography
MHHS-DIN-607 | SC |  | 2023-08-10 | SCS |  | Sean Cooper | SRO Design | Update IF-035 Lapsed Reason Code | SCS Request Update IF-035 Lapsed Reason Code from "Switch Cancelled" to "Registration Cancelled" | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | SCS Request Update IF-035 Lapsed Reason Code from "Switch Cancelled" to "Registration Cancelled" | Clarification | Minor | Interfaces | DES-138 Interface Doc
MHHS-DIN-608 | SC | SCS DI-206 | 2023-08-10 | SCS |  | Sean Cooper | SRO Design | Correction of Inaccuracy on BP003 | Steps 86,87,88 added to better reflect that REGS will actually send TWO IF-035 messages not just one. IF-035 [SendMTD] will be issued to Incumbent MS and [AppOutcome] event will be issued to DS/Supplier. BP003 now mirrors the drafting in BP002. There is no change in underlying requirement here - redrafting is simply a more accurate representation of REGS activity. | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Steps 86,87,88 added to better reflect that REGS will actually send TWO IF-035 messages not just one. IF-035 [SendMTD] will be issued to Incumbent MS and [AppOutcome] event will be issued to DS/Supplier. BP003 now mirrors the drafting in BP002. | Clarification | Minor | Interfaces | BP003
MHHS-DIN-609 | SC |  | 2023-08-10 | Helix |  | Sean Cooper | SRO Design | Helix Issuing of IF-040 Annual Consumption Messages | Discussion held with Helix on proposed approach to issuing IF-040 messages. Current design suggests that messages should only be issued on Working Days - Design Team are exploring why this is the case (risk of substantial peak esp on 4 day long weekends). preference would be for Helix to issue IF-040 on each calendar day. | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Waiting feedback from Helix Package 1 Team | Clarification
MHHS-DIN-610 | SC |  | 2023-08-10 | Helix |  | Sean Cooper | SRO Design | Clarification of IF-013 Functionality | Need to validate if IF-013 should be issued after each Settlement Run OR only after RF Run. Also need to validate the IF-10 shout NOT be issued after II Run. | Requires Industry Work Group review | 2023-09-13 | Interim Release 5 | 2023-09-20 | Meeting held with Helix Team - Awaiting feedback before slides can be prepared for DRG meeting | Clarification
MHHS-DIN-611 | KH |  | 2023-08-11 | Elexon | 3986 | Michael Ceney | Central Body | Changes required to MDS Method Statement | Following the release of DIN-332, changing EventCode [ConsumptionOnDe-energisedMpan], the MDS Method Statement needs updating to reflect this change. Section 9.3 states that the an exception report will be provided using IF-013, this needs to show IF-014 is to be used. Please can a new DIN be raised. | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | We will update section 9.3 to state that the report will be provided using IF-014. | Method statement correction | Supporting Docs | Method Statement | MDS Method Statement
MHHS-DIN-612 | SC | PDA Test Issues | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | New IF-019 Validation Rules Re Unmetered Related MPANs | Added x2 new validtion rules to prevent the creation / addition of Related MPANs with a Connection Type of "U - Unmetered". No validation applied to remove so as to allow for the resolution of any historically erroneous links | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Added x2 new validation rules to prevent the creation / addition of Related MPANs with a Connection Type of "U - Unmetered". No validation applied to remove so as to allow for the resolution of any historically erroneous links | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-613 | SC |  | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Remove Reference to SP Appointment Start Time(s) | In line with DRG Decision on 4th Aug - it was agreed that ALL Service Provider Appointments should commence at Midnight UTC. Text against DI-086 and DI-121 has been removed. A new section addressing the treatment of Time has been added to the Additional Information tab of DES-138 | Implemented |  | Interim Release 4 | 2023-08-16 | In line with DRG Decision on 4th Aug - it was agreed that ALL Serive Provider Appointments should commence at Midnight UTC. Text against DI-086 and DI-121 has been removed. A new section addressing the treatment of Time will be added to the Additional Information tab of DES-138 as part of Interim Release 5 (DIN-614) | Design Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-614 | SC |  | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Create new "Time" Advisory Notes in Registration Additional Info Section | SC to create Treatment of Time section | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Added validation rule to IF-031 to ensure appointments are made at midnight UTC. Added clarification on Regs Notes tab. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-615 | SC |  | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Number of Registers Validation | Clarification following on from DIN-574. Text against Number of Register Digits fields amended to say "per the manufacturer specification" . Note text for SCS validation will remain unchanged. Swagger validation of this field updated to match SCS logical test ie value can be 0-9 | Implemented |  | Interim Release 4 | 2023-08-16 | Clarification following on from DIN-574. Text against Number of Register Digits field amended in IF-002, IF-005, IF-006, IF-033, to say "per the manufacturer specification". Note text for SCS validation will remain unchanged. Swagger validation of this field updated to match SCS logical test ie value can be 0-9. | Design Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-616 | SC |  | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Review of COS Transfer of Readings Process Required in light of SP UTC Decision | A Review of BP003C is required to impact assess implications of SP UTC Decision | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | BP003C may need updating follow impact assessment | Clarification
MHHS-DIN-617 | SC | PDA Test Issues | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Note on Discressionary Use of IF-023/IF-040 by Data Service | Missing interface notes on Discretionary Use of IF-023/IF-040 by Data Service | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Added interface notes to clarify Annual Consumption usage in IF-040 and Load Shape Totals in IF-023 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-618 | KH |  | 2023-08-15 | ESG | 5859 | Patricia Parker | Software Provider | Updating routing within DES138 - PUB-026 | Could you please clarify what updates the Metering Service will receive via the PUB_026. From the routing the only update is re the SCCandProfile Class. However, BP010C alludes to the MS receiving an update for the SMSO - could you please confirm which is correct? | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | To update PUB-026 adding MS to the SMSO secondary routing. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-619 | SC | PDA Test Issues | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Draft Umetered Change of Energisation Status Business Process Map | Update BP08 existing or draft Unmetered Specific version. | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Pending feedback from PDA on UMS process
MHHS-DIN-620 | SC | Test Issues | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Remove EES as a Recipient of IF-001 | Remove EES as a Recipient of IF-001 | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Removed EES as a Recipient of IF-001 - EES gets this info from CSS | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-621 | SC |  | 2023-08-17 | MHHS |  | Sean Cooper | SRO Design | Changes to D303 DTN Flow | Need to make "Manufacture and Type" non mandatory in the D303 flow. Follow migration to MHHS it is possible that this data item is not held in REGS and therefore not shared with all MHHS Participants incl. MS who currently would need to provided it on the D303. Discussions were held in Data Working group around back population of this data item but that proposal was REJECTED - therefore only other option is to make this field optional in D303 | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Passed to Matt McC to add to existing industry CP changes.
MHHS-DIN-622 | SC | SCS | 2023-08-17 | SCS |  | Sean Cooper | SRO Design | DIP Validation of Sender Correlation ID | Implement DIP validation to check for incorrect population of Sender Correlation ID. | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Email sent to SCS. Design Team to share requirements with internal DIP Team | Clarification
MHHS-DIN-623 | SC | SCS | 2023-08-17 | SCS |  | Sean Cooper | SRO Design | Change IF-001 Routing | Add SUPL (Linked Supplier) as an additional Primary Receipient of Inital Registration Event | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Add SUPL (Linked Supplier) as an additional Primary Receipient of Inital Registration Event | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-624 | ME |  | 2023-08-18 | MHHS |  | Miriam Ellis | SRO Design | BP013 DDE Updates | MHHS test team have identified discrepancies within the ECS BPM's that require updates to align with the ECS reports. Updates are required to BPM13 DDE | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Updates to BPM013: 1. Removal of MHHS-REP-001 reference 2. Update reference of REP-005 to ELEX-REP-005 3. Reference of MHHS-REP-002A included with BP header 4. Reference of REP-002 changed to ELEX-REP-001 | Clarification | Supporting Docs | Reporting Catalogue | BPM013
MHHS-DIN-625 | SC | SCS | 2023-08-18 | SCS |  | Sean Cooper | SRO Design | B092 should also be array to allow MPRS to populate multiple rejections | B092 should also be array to allow MPRS to populate multiple rejections | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Consider breaking out DI-980 into an array in B092 block of IF-035. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-626 | SC | ESG | 2023-08-22 | ESG |  | Sean Cooper | SRO Design | Update Routing of IF-003 | Routing of this flow should match that of the IF-037 - in that a copy should also be sent to the Supplier. IF-003 Routing table updated to show Supplier as being a receipient of the iF-003 | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Routing of this flow should match that of the IF-037 - in that a copy should also be sent to the Supplier. IF-003 Routing table updated to show Supplier as being a receipient of the iF-003 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-627 | SC | ESG | 2023-08-22 | ESC |  | Sean Cooper | SRO Design | Update Interface Doc "Correlation ID Required" to "Correlation ID Created" | Inconsistancy indentified in the column headings across different IFs. All should read "Correlation ID Created" as this column denotes if the DIP IF should create/copy a DIP Correlation ID value or not. | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Update Interface Doc "Correlation ID Required" to "Correlation ID Created" | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-628 | SC |  | 2023-08-23 |  |  | Sean Cooper | SRO Design | Add in Missing IF-021 Validation | Add NEW validation to ensure that "UTC Settlement Date" has time of Midnight UTC. Added clarification to existing validation rule that time element of "Settlement period end date time" should align with Settlement period duration | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Add NEW validation to ensure that "UTC Settlement Date" has time of Midnight UTC. Added clarification to existing validation rule that time element of "Settlement period end date time" should align with Settlement period duration | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-629 | MF |  | 2023-08-25 |  |  | Mike Fensome | SRO Design | Routing for SUPC on IF-037 | To ensure that the outgoing Supplier are correctly notified of de-appointment of their Service Providers, routing rules for SUPC updated to Primary routing for IF-037 | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | SUPC routing moved from Secondary to Primary for IF-037 for all events | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-630 | MF |  | 2023-08-25 |  | N/A | Mike Fensome | SRO Design | Remove incorrect arrow on BP002 | Arrow incorrectly added into BPOO2 between steps 225 and steps 245 | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Arrow between steps 225 and steps 245 on BP002 removed. Previously added in error. | Process Model correction | Minor | Interfaces | BP002
MHHS-DIN-631 | SC |  | 2023-08-29 |  | N/A | Sean Cooper | SRO Design | Swagger Alignment - Block B051 | Required Data Items field names do not match those specfied in the defintion. | Implemented |  | Interim Release 4 | 2023-08-16 | loadShapeGSPGroup and loadShapeDomesticPremiseIndicator added to Required fields section to align with block definition. | Correction | Minor |  | DES-138 Interface Cat
MHHS-DIN-632 | SC |  | 2023-08-31 | Helix | N/A | Sean Cooper | SRO Design | Header & Footer Requirements for ISD Entity Files | ISD Specification should be updated to include specification/definition of a standard Header and Footer to be applied to each ISD Entity CSV file. | Requires Industry Work Group review |  | Interim Release 6 | 2023-10-18 | DRG to decide on exact content/structure of Header ... Is a footer required? If so what should it include (eg number of Entity entries)
MHHS-DIN-633 | SC |  | 2023-08-31 | Helix | N/A | Sean Cooper | SRO Design | Update to ISD E45 | Update Entity 45 - Market Role code needs to allow Blanks in order to align with other tables in ISD and to provide for [new] Market Participants who dont have a legacy market particpant role code | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Update Entity 45 - Market Role code needs to allow Blanks in order to align with other tables in ISD and to provide for [new MHHS] Market Participants who dont have a legacy market participant role code | Clarification | Supporting Docs | Supporting Document | ISD Entity
MHHS-DIN-634
MHHS-DIN-635
MHHS-DIN-636
MHHS-DIN-637
MHHS-DIN-638
MHHS-DIN-639
MHHS-DIN-640
MHHS-DIN-641
MHHS-DIN-642
MHHS-DIN-643
MHHS-DIN-644
MHHS-DIN-645
MHHS-DIN-646
MHHS-DIN-647
MHHS-DIN-648
MHHS-DIN-649
MHHS-DIN-650
MHHS-DIN-651
MHHS-DIN-652
MHHS-DIN-653
MHHS-DIN-654
MHHS-DIN-655
MHHS-DIN-656
MHHS-DIN-657
MHHS-DIN-658
MHHS-DIN-659
MHHS-DIN-660
MHHS-DIN-661
MHHS-DIN-662
MHHS-DIN-663
MHHS-DIN-664
MHHS-DIN-665
MHHS-DIN-666
MHHS-DIN-667
MHHS-DIN-668
Formulas:
Objection Cut-off Date = IFNA(VLOOKUP([Target Release],[1]!Table2[#All],3,FALSE), " ")

## DIN Compare 170823 (hidden)
DIN Log Compare between 03/08/23 and 17/08/23
Differences
Sheet |  | Range | Old Value | New Value | Description
Log | DIN-586 | C588 |  | DI-204 | Entered Value Added.
Log | DIN-594 | C596 |  | SCS DI-207 | Entered Value Added.
Log | DIN-595 | C597 |  | SCS DI-208 | Entered Value Added.
Log | DIN-597 | C599 |  | SCS DI-193 | Entered Value Added.
Log | DIN-598 | C600 |  | SCS DI-176 | Entered Value Added.
Log | DIN-599 | C601 |  | SCS DI-198 | Entered Value Added.
Log | DIN-608 | C610 |  | SCS DI-206 | Entered Value Added.
Log | DIN-612 | C614 |  | PDA Test Issues | Entered Value Added.
Log | DIN-617 | C619 |  | PDA Test Issues | Entered Value Added.
Log | DIN-619 | C621 |  | PDA Test Issues | Entered Value Added.
Log | DIN-620 | C622 |  | Test Issues | Entered Value Added.
Log | DIN-461 | D463 | 26/06/2023 | 26/06/2023 (26/06/2023 00:00:00) | Entered Value Changed.
Log | DIN-462 | D464 | 27/06/2023 | 27/06/2023 (27/06/2023 00:00:00) | Entered Value Changed.
Log | DIN-463 | D465 | 27/06/2023 | 27/06/2023 (27/06/2023 00:00:00) | Entered Value Changed.
Log | DIN-464 | D466 | 27/06/2023 | 27/06/2023 (27/06/2023 00:00:00) | Entered Value Changed.
Log | DIN-470 | D472 | 29/06/2023 | 29/06/2023 (29/06/2023 00:00:00) | Entered Value Changed.
Log | DIN-472 | D474 | 29/06/2023 | 29/06/2023 (29/06/2023 00:00:00) | Entered Value Changed.
Log | DIN-588 | D590 |  | 02/08/2023 (02/08/2023 00:00:00) | Entered Value Added.
Log | DIN-589 | D591 |  | 02/08/2023 (02/08/2023 00:00:00) | Entered Value Added.
Log | DIN-590 | D592 |  | 03/08/2023 (03/08/2023 00:00:00) | Entered Value Added.
Log | DIN-591 | D593 |  | 03/08/2023 (03/08/2023 00:00:00) | Entered Value Added.
Log | DIN-592 | D594 |  | 03/08/2023 (03/08/2023 00:00:00) | Entered Value Added.
Log | DIN-593 | D595 |  | 04/08/2023 (04/08/2023 00:00:00) | Entered Value Added.
Log | DIN-594 | D596 |  | 04/08/2023 (04/08/2023 00:00:00) | Entered Value Added.
Log | DIN-595 | D597 |  | 04/08/2023 (04/08/2023 00:00:00) | Entered Value Added.
Log | DIN-596 | D598 |  | 04/08/2023 (04/08/2023 00:00:00) | Entered Value Added.
Log | DIN-597 | D599 |  | 07/08/2023 (07/08/2023 00:00:00) | Entered Value Added.
Log | DIN-598 | D600 |  | 07/08/2023 (07/08/2023 00:00:00) | Entered Value Added.
Log | DIN-599 | D601 |  | 07/08/2023 (07/08/2023 00:00:00) | Entered Value Added.
Log | DIN-600 | D602 |  | 07/08/2023 (07/08/2023 00:00:00) | Entered Value Added.
Log | DIN-601 | D603 |  | 07/08/2023 (07/08/2023 00:00:00) | Entered Value Added.
Log | DIN-602 | D604 |  | 08/08/2023 (08/08/2023 00:00:00) | Entered Value Added.
Log | DIN-603 | D605 |  | 09/08/2023 (09/08/2023 00:00:00) | Entered Value Added.
Log | DIN-604 | D606 |  | 09/08/2023 (09/08/2023 00:00:00) | Entered Value Added.
Log | DIN-605 | D607 |  | 09/08/2023 (09/08/2023 00:00:00) | Entered Value Added.
Log | DIN-606 | D608 |  | 09/08/2023 (09/08/2023 00:00:00) | Entered Value Added.
Log | DIN-607 | D609 |  | 10/08/2023 (10/08/2023 00:00:00) | Entered Value Added.
Log | DIN-608 | D610 |  | 10/08/2023 (10/08/2023 00:00:00) | Entered Value Added.
Log | DIN-609 | D611 |  | 10/08/2023 (10/08/2023 00:00:00) | Entered Value Added.
Log | DIN-610 | D612 |  | 10/08/2023 (10/08/2023 00:00:00) | Entered Value Added.
Log | DIN-611 | D613 |  | 11/08/2023 (11/08/2023 00:00:00) | Entered Value Added.
Log | DIN-612 | D614 |  | 14/08/2021 (14/08/2021 00:00:00) | Entered Value Added.
Log | DIN-613 | D615 |  | 14/08/2021 (14/08/2021 00:00:00) | Entered Value Added.
Log | DIN-614 | D616 |  | 14/08/2021 (14/08/2021 00:00:00) | Entered Value Added.
Log | DIN-615 | D617 |  | 14/08/2021 (14/08/2021 00:00:00) | Entered Value Added.
Log | DIN-616 | D618 |  | 14/08/2021 (14/08/2021 00:00:00) | Entered Value Added.
Log | DIN-617 | D619 |  | 14/08/2021 (14/08/2021 00:00:00) | Entered Value Added.
Log | DIN-618 | D620 |  | 15/08/2023 (15/08/2023 00:00:00) | Entered Value Added.
Log | DIN-619 | D621 |  | 14/08/2021 (14/08/2021 00:00:00) | Entered Value Added.
Log | DIN-620 | D622 |  | 14/08/2021 (14/08/2021 00:00:00) | Entered Value Added.
Log | DIN-588 | E590 |  | Design Team | Entered Value Added.
Log | DIN-589 | E591 |  | Stark | Entered Value Added.
Log | DIN-590 | E592 |  | MHHS | Entered Value Added.
Log | DIN-591 | E593 |  | Elexon | Entered Value Added.
Log | DIN-592 | E594 |  | MHHS | Entered Value Added.
Log | DIN-593 | E595 |  | MHHS | Entered Value Added.
Log | DIN-594 | E596 |  | MHHS | Entered Value Added.
Log | DIN-595 | E597 |  | MHHS | Entered Value Added.
Log | DIN-596 | E598 |  | MHHS | Entered Value Added.
Log | DIN-597 | E599 |  | MHHS | Entered Value Added.
Log | DIN-598 | E600 |  | SCS | Entered Value Added.
Log | DIN-599 | E601 |  | SCS | Entered Value Added.
Log | DIN-600 | E602 |  | Elexon | Entered Value Added.
Log | DIN-601 | E603 |  | Kraken | Entered Value Added.
Log | DIN-602 | E604 |  | SRO | Entered Value Added.
Log | DIN-603 | E605 |  | MHHS | Entered Value Added.
Log | DIN-604 | E606 |  | MHHS | Entered Value Added.
Log | DIN-605 | E607 |  | MHHS | Entered Value Added.
Log | DIN-606 | E608 |  | MHHS | Entered Value Added.
Log | DIN-607 | E609 |  | SCS | Entered Value Added.
Log | DIN-608 | E610 |  | SCS | Entered Value Added.
Log | DIN-609 | E611 |  | Helix | Entered Value Added.
Log | DIN-610 | E612 |  | Helix | Entered Value Added.
Log | DIN-611 | E613 |  | Elexon | Entered Value Added.
Log | DIN-612 | E614 |  | MHHS | Entered Value Added.
Log | DIN-613 | E615 |  | MHHS | Entered Value Added.
Log | DIN-614 | E616 |  | MHHS | Entered Value Added.
Log | DIN-615 | E617 |  | MHHS | Entered Value Added.
Log | DIN-616 | E618 |  | MHHS | Entered Value Added.
Log | DIN-617 | E619 |  | MHHS | Entered Value Added.
Log | DIN-618 | E620 |  | ESG | Entered Value Added.
Log | DIN-619 | E621 |  | MHHS | Entered Value Added.
Log | DIN-620 | E622 |  | MHHS | Entered Value Added.
Log | DIN-589 | F591 |  | 2466 | Entered Value Added.
Log | DIN-590 | F592 |  | 2717 | Entered Value Added.
Log | DIN-591 | F593 |  | 2974 | Entered Value Added.
Log | DIN-592 | F594 |  | 2717 | Entered Value Added.
Log | DIN-600 | F602 |  | 4566 | Entered Value Added.
Log | DIN-601 | F603 |  | 4485 | Entered Value Added.
Log | DIN-603 | F605 |  | 4022, 4700 | Entered Value Added.
Log | DIN-604 | F606 |  | 4945 | Entered Value Added.
Log | DIN-611 | F613 |  | 3986 | Entered Value Added.
Log | DIN-618 | F620 |  | 5859 | Entered Value Added.
Log | DIN-588 | G590 |  | Kevin Spencer | Entered Value Added.
Log | DIN-589 | G591 |  | Jon Dennis | Entered Value Added.
Log | DIN-590 | G592 |  | Martin Freeman | Entered Value Added.
Log | DIN-591 | G593 |  | Michael Ceney | Entered Value Added.
Log | DIN-592 | G594 |  | Martin Freeman | Entered Value Added.
Log | DIN-593 | G595 |  | Kevin Spencer | Entered Value Added.
Log | DIN-594 | G596 |  | Sean Cooper | Entered Value Added.
Log | DIN-595 | G597 |  | Sean Cooper | Entered Value Added.
Log | DIN-596 | G598 |  | Sean Cooper | Entered Value Added.
Log | DIN-597 | G599 |  | Sean Cooper | Entered Value Added.
Log | DIN-598 | G600 |  | Madison Layton | Entered Value Added.
Log | DIN-599 | G601 |  | Madison Layton | Entered Value Added.
Log | DIN-600 | G602 |  | Rashmi Radhakrishnan | Entered Value Added.
Log | DIN-601 | G603 |  | Adrian Serban | Entered Value Added.
Log | DIN-602 | G604 |  | Rob Golding | Entered Value Added.
Log | DIN-603 | G605 |  | Steve Weston | Entered Value Added.
Log | DIN-604 | G606 |  | Steve Weston | Entered Value Added.
Log | DIN-605 | G607 |  | Sean Cooper | Entered Value Added.
Log | DIN-606 | G608 |  | Sean Cooper | Entered Value Added.
Log | DIN-607 | G609 |  | Sean Cooper | Entered Value Added.
Log | DIN-608 | G610 |  | Sean Cooper | Entered Value Added.
Log | DIN-609 | G611 |  | Sean Cooper | Entered Value Added.
Log | DIN-610 | G612 |  | Sean Cooper | Entered Value Added.
Log | DIN-611 | G613 |  | Michael Ceney | Entered Value Added.
Log | DIN-612 | G614 |  | Sean Cooper | Entered Value Added.
Log | DIN-613 | G615 |  | Sean Cooper | Entered Value Added.
Log | DIN-614 | G616 |  | Sean Cooper | Entered Value Added.
Log | DIN-615 | G617 |  | Sean Cooper | Entered Value Added.
Log | DIN-616 | G618 |  | Sean Cooper | Entered Value Added.
Log | DIN-617 | G619 |  | Sean Cooper | Entered Value Added.
Log | DIN-618 | G620 |  | Patricia Parker | Entered Value Added.
Log | DIN-619 | G621 |  | Sean Cooper | Entered Value Added.
Log | DIN-620 | G622 |  | Sean Cooper | Entered Value Added.
Log | DIN-588 | H590 |  | SI Design | Entered Value Added.
Log | DIN-589 | H591 |  | Data Service Provider | Entered Value Added.
Log | DIN-590 | H592 |  | Central Body | Entered Value Added.
Log | DIN-591 | H593 |  | Central Body | Entered Value Added.
Log | DIN-592 | H594 |  | Central Body | Entered Value Added.
Log | DIN-593 | H595 |  | SI Design | Entered Value Added.
Log | DIN-594 | H596 |  | SRO Design | Entered Value Added.
Log | DIN-595 | H597 |  | SRO Design | Entered Value Added.
Log | DIN-596 | H598 |  | SRO Design | Entered Value Added.
Log | DIN-597 | H599 |  | SRO Design | Entered Value Added.
Log | DIN-598 | H600 |  | Software Provider | Entered Value Added.
Log | DIN-599 | H601 |  | Software Provider | Entered Value Added.
Log | DIN-600 | H602 |  | Central Body | Entered Value Added.
Log | DIN-601 | H603 |  | Software Provider | Entered Value Added.
Log | DIN-602 | H604 |  | Programme | Entered Value Added.
Log | DIN-603 | H605 |  | Central Body | Entered Value Added.
Log | DIN-604 | H606 |  | Siemens | Entered Value Added.
Log | DIN-605 | H607 |  | SRO Design | Entered Value Added.
Log | DIN-606 | H608 |  | SRO Design | Entered Value Added.
Log | DIN-607 | H609 |  | SRO Design | Entered Value Added.
Log | DIN-608 | H610 |  | SRO Design | Entered Value Added.
Log | DIN-609 | H611 |  | SRO Design | Entered Value Added.
Log | DIN-610 | H612 |  | SRO Design | Entered Value Added.
Log | DIN-611 | H613 |  | Central Body | Entered Value Added.
Log | DIN-612 | H614 |  | SRO Design | Entered Value Added.
Log | DIN-613 | H615 |  | SRO Design | Entered Value Added.
Log | DIN-614 | H616 |  | SRO Design | Entered Value Added.
Log | DIN-615 | H617 |  | SRO Design | Entered Value Added.
Log | DIN-616 | H618 |  | SRO Design | Entered Value Added.
Log | DIN-617 | H619 |  | SRO Design | Entered Value Added.
Log | DIN-618 | H620 |  | Software Provider | Entered Value Added.
Log | DIN-619 | H621 |  | SRO Design | Entered Value Added.
Log | DIN-620 | H622 |  | SRO Design | Entered Value Added.
Log | DIN-328 | I330 |  | Operational Chorepgraphy Update: Addition of SLA for RS end appointment data to the CSS | Entered Value Added.
Log | DIN-563 | I565 | Clarificatioin on Helix Treatment of IF-021 error condition data. | Clarification on Helix Treatment of IF-021 error condition data. | Entered Value Changed.
Log | DIN-588 | I590 |  | Update of ID to Id | Entered Value Added.
Log | DIN-589 | I591 |  | ADS and SDS Estimation Statements | Entered Value Added.
Log | DIN-590 | I592 |  | Update Role Codes in E2E001 | Entered Value Added.
Log | DIN-591 | I593 |  | Update to MDS Method statement | Entered Value Added.
Log | DIN-592 | I594 |  | Update StatusMessage and StandardResponseBody in E2E001 to provide more clarity | Entered Value Added.
Log | DIN-593 | I595 |  | Update to AC Method Statement | Entered Value Added.
Log | DIN-594 | I596 |  | Correction to BP10 Related MPANs | Entered Value Added.
Log | DIN-595 | I597 |  | Correction of Type in ISD Doc Table 16 | Entered Value Added.
Log | DIN-596 | I598 |  | Clarification of SP Appointment Time(s) | Entered Value Added.
Log | DIN-597 | I599 |  | IF-026 B069 Presence | Entered Value Added.
Log | DIN-598 | I600 |  | Incoming Supplier Notifications - Clarification | Entered Value Added.
Log | DIN-599 | I601 |  | Data Cleansing required on IHD, SMSO and Installation Date | Entered Value Added.
Log | DIN-600 | I602 |  | ISD Entity M18 Discrepancy | Entered Value Added.
Log | DIN-601 | I603 |  | Incorrect on M0 common block in IF-018 | Entered Value Added.
Log | DIN-602 | I604 |  | Add Interface, Event Code enumeration to Swagger for interface blocks | Entered Value Added.
Log | DIN-603 | I605 |  | Clarity on A0 block being removed | Entered Value Added.
Log | DIN-604 | I606 |  | Clarity on B066 mandatory on IF-035 | Entered Value Added.
Log | DIN-605 | I607 |  | Update "Switch Cancellation" Info Message Box of BP002 & BP003 | Entered Value Added.
Log | DIN-606 | I608 |  | Update Ops C to include clearification on issuing of IF-035 | Entered Value Added.
Log | DIN-607 | I609 |  | Update IF-035 Lapsed Reason Code | Entered Value Added.
Log | DIN-608 | I610 |  | Correction of Inaccuracy on BP003 | Entered Value Added.
Log | DIN-609 | I611 |  | Helix Issuing of IF-040 Annual Consumption Messages | Entered Value Added.
Log | DIN-610 | I612 |  | Clarification of IF-013 Functionality | Entered Value Added.
Log | DIN-611 | I613 |  | Changes required to MDS Method Statement | Entered Value Added.
Log | DIN-612 | I614 |  | New IF-019 Validation Rules Re Unmetered Related MPANs | Entered Value Added.
Log | DIN-613 | I615 |  | Remove Reference to SP Appointment Start Time(s) | Entered Value Added.
Log | DIN-614 | I616 |  | Create new "Time" Advisory Notes in Registration Additional Info Section | Entered Value Added.
Log | DIN-615 | I617 |  | Number of Registers Validation | Entered Value Added.
Log | DIN-616 | I618 |  | Review of COS Transfer of Readings Process Required in light of SP UTC Decision | Entered Value Added.
Log | DIN-617 | I619 |  | Note on Discressionary Use of IF-023/IF-040 by Data Service | Entered Value Added.
Log | DIN-618 | I620 |  | Updating routing within DES138 - PUB-026 | Entered Value Added.
Log | DIN-619 | I621 |  | Draft Umetered Change of Energisation Status Business Process Map | Entered Value Added.
Log | DIN-620 | I622 |  | Remove EES as a Recipient of IF-001 | Entered Value Added.
Log | DIN-478 | J480 | In the Release 2 version of DES138 a limit was introduced that asked Participants not to submit more than 150 Settlement Days’ worth of data in a single message. The value of 150 was proposed as this meant a single message would realistically be ~600KB in size. We’ve had some queries regarding this value, the proposal is to increase sizing from 150 to 194 day message and the size increases from 600KB to ~780KB for IF-021 message. ECS will need to validate the message contents. However, rather than letting a ‘large’ IF-021 message traversing though the DIP, the proposal is to limit the IF-021 on ingress to the DIP and a single request will have a limit of 1MB – this will done at the API level. | In the Release 2 version of DES138 a limit was introduced that asked Participants not to submit more than 150 Settlement Days’ worth of data in a single message. The value of 150 was proposed as this meant a single message would realistically be ~600KB in size. We’ve had some queries regarding this value, the proposal is to increase sizing from 150 to 194 day message and the size increases from 600KB to ~780KB for IF-021 message. ECS will need to validate the message contents. However, rather than letting a ‘large’ IF-021 message traversing though the DIP, the proposal is to limit the IF-021 on ingress to the DIP and a single request will have a limit of 1MB – this will be done at the API level. | Entered Value Changed.
Log | DIN-485 | J487 | For the DELETE methods in Swagger for StatusMessage and PublicationConfig, need to update the method so you can identify the correct recipientID to be used for the method call. Some frameworks will ignore a body on a DELETE method as being incompatible with the semantics of the DELETE method, and the correct RESTful implementation would be something more along the lines of "DELETE dip-channel/{id}/{role}/pubconfig". Which of course raises the question of whether the POST message should be refactored for consistency. The issue is more widespread han just the DELETE methods, it also affects some of the POST methods where a recieipent ID is required | For the DELETE methods in Swagger for StatusMessage and PublicationConfig, need to update the method so you can identify the correct recipientID to be used for the method call. Some frameworks will ignore a body on a DELETE method as being incompatible with the semantics of the DELETE method, and the correct RESTful implementation would be something more along the lines of "DELETE dip-channel/{id}/{role}/pubconfig". Which of course raises the question of whether the POST message should be refactored for consistency. The issue is more widespread than just the DELETE methods, it also affects some of the POST methods where a recieipent ID is required | Entered Value Changed.
Log | DIN-487 | J489 | In section 4.4.4.2, there are some examples that incorrectly return a 207 when they have failed schema validation. E2E001 needs to be updated to provide different examples of schema vs data validation errors to illustrate how this will be handled correctly. | In section 4.4.4.2, there are some examples that incorrectly return a 207 when they have failed schema validation. | Entered Value Changed.
Log | DIN-588 | J590 |  | A request has come from Elexon to update the ISD Entities document. ID should be changed to Id | Entered Value Added.
Log | DIN-589 | J591 |  | I have been studying the following two documents: Advanced Data Service Validation and Estimation: Methodology Statement (MHHSP-METH002_ADS_Validation_Estimation v5.1) Smart Data Service Validation and Estimation: Methodology Statement (MHHSP-METH001_SDS_Validation_Estimation v5.1) In particular, Section 3 of the ADS_Validation_Estimation document details the estimation methods where the customer has opted-out of UTC Period consumption data. It references the SDS_Validation_Estimation document where Estimation methods are in Section 7. The 2 method statements have become misaligned when changes to the SDS method statement was updated. | Entered Value Added.
Log | DIN-590 | J592 |  | There is a mismatch between roles codes that are in DES-138 and those that are in E2E001. Role code for Unmetered Supplies Data Services changed from UDS to UMSDS. Need to ensure that all of the role codes referenced in DES-138 are included in E2E001 and that there is a full explanation of what these are. | Entered Value Added.
Log | DIN-591 | J593 |  | The MDS Method Statement Section 2.1 should read: If SP End Date/Time [DI-082] > MDS Run Date (RF) as specified for the SP End Date/Time [DI-082] in the Master Settlement Table in ISD ECS1003 - SP End Date/Time [DI-082] is older than/after to "MDS Run Date (RF) [ISD.RunDate-RFDate]" | Entered Value Added.
Log | DIN-592 | J594 |  | There are inconsistencies between StatusMessage / Standard Response body definitions for what is contained with E2E001 and Swagger, these need to be aligned. Clarity needs to be provided on how TransactionID is populated in Status Message for Level 2 validation and Level 4 validation and for Level 4 validation, how this is sent to original sender. | Entered Value Added.
Log | DIN-593 | J595 |  | Update required to the AC Method Statement to amend calculation where less than 365 days of data is available and a change to section 2.2 to allow calculations to be undertaken on Calendar days | Entered Value Added.
Log | DIN-594 | J596 |  | Rejection was incorrectly shown being sent direct from REGS rather than from REGS Via DIP. | Entered Value Added.
Log | DIN-595 | J597 |  | Correction of type in definition of subscript 3 for table M16 - "Market Participant ID" changed to "Market Participant Role" | Entered Value Added.
Log | DIN-596 | J598 |  | Per DRG decision all SP Appointment times shall be effective from Midnight UTC Time. Clarification added to IF-031/If-036 | Entered Value Added.
Log | DIN-597 | J599 |  | IF-026 / B069 - SCS requested removal of wording "must be required for smart meter removed" as this is inherant as part of the Event Type. | Entered Value Added.
Log | DIN-598 | J600 |  | SCS raised a query around whether certain flows should be copied to an incomming Supplier (PUB-006, PUB008 etc. etc.) The current design does not include copying of these flows to an incoming supplier, (not represented in either Requirements or BP maps). IF-036 (and accompanying D-flows as required) provides suppliers with a clear starting point containing all the information they need to support servicing the customer. Design Team feel any change in this area would require a CR. | Entered Value Added.
Log | DIN-599 | J601 |  | SCS raised a a query on the three items below that are not under the Data Cleanse Plan that may need cleanse work. 1) IHD - Should be populated for smart meters, and only smart meters (not currently validated) 2) SMSO - Should be populated for smart meters and only smart meters (not currently validated) 3) Installation date - Should not be prior to MPAN Creation date (Legacy data integrity issues of meters migrated into MPRS) | Entered Value Added.
Log | DIN-600 | J602 |  | In the ISD Entity Document the table shows {Effective From Date {DIPRole} and {Effective To Date {DIPRole}, however the exmaple table and column details have been titled as {Effective From Date {MP2DPM} and {Effective To Date {MP2DPM}. These should be changed to align with the first table in entity M18 | Entered Value Added.
Log | DIN-601 | J603 |  | In Swagger, it appears the block is correct (M0), but the label is incorrect (M1) for IF-018. The label needs to be updated to M0 to align with the block. This needs to be updated in Swagger so the label is incorrect. In IF-019 and IF-020, there is an inconsitency of use of M1 vs M0. | Entered Value Added.
Log | DIN-602 | J604 |  | Interface and Event code validation and alloawable blocks is missing from the DIP. Rather then getting Avanade to code these dependencies the proposal is to intoduce the restrictions into the Swagger | Entered Value Added.
Log | DIN-603 | J605 |  | Section 4.2.1 of the E2E001 design has a diagram that shows that the A0 common block is removed by the DIP prior to sending out the message to onward particpants. This is inconsistent with the rest of the design. Section 4.2.1 needs to be updated so that this shows A0 not being removed. | Entered Value Added.
Log | DIN-604 | J606 |  | In DES-138, B066 block in IF-035 is shown as mandatory and also defined as mandatory in Swagger. This should be conditionally mandatory as per B019, so this needs to be updated to conditionally mandatory in DES-138 and also in Swagger 1.5. | Entered Value Added.
Log | DIN-605 | J607 |  | Message updated to make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations will be held awaiting completion of PUB-34 processing. | Entered Value Added.
Log | DIN-606 | J608 |  | make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations will be held awaiting completion of PUB-34 processing. | Entered Value Added.
Log | DIN-607 | J609 |  | SCS Request Update IF-035 Lapsed Reason Code from "Switch Cancelled" to "Registration Cancelled" | Entered Value Added.
Log | DIN-608 | J610 |  | Steps 86,87,88 added to better reflect that REGS will actually send TWO IF-035 messages not just one. IF-035 [SendMTD] will be issued to Incumbent MS and [AppOutcome] event will be issued to DS/Supplier. BP003 now mirrors the drafting in BP002. There is no change in underlying requirement here - redrafting is simply a more accurate representation of REGS activity. | Entered Value Added.
Log | DIN-609 | J611 |  | Discussion held with Helix on proposed approach to issuing IF-040 messages. Current design suggests that messages should only be issued on Working Days - Design Team are exploring why this is the case (risk of substantial peak esp on 4 day long weekends). preference would be for Helix to issue IF-040 on each calendar day. | Entered Value Added.
Log | DIN-610 | J612 |  | Need to validate if IF-013 should be issued after each Settlement Run OR only after RF Run. Also need to validate the IF-10 shout NOT be issued after II Run. | Entered Value Added.
Log | DIN-611 | J613 |  | Following the release of DIN-332, changing EventCode [ConsumptionOnDe-energisedMpan], the MDS Method Statement needs updating to reflect this change. Section 9.3 states that the an exception report will be provided using IF-013, this needs to show IF-014 is to be used. Please can a new DIN be raised. | Entered Value Added.
Log | DIN-612 | J614 |  | Added x2 new validtion rules to prevent the creation / addition of Related MPANs with a Connection Type of "U - Unmetered". No validation applied to remove so as to allow for the resolution of any historically erroneous links | Entered Value Added.
Log | DIN-613 | J615 |  | In line with DAG Decision on 4th Aug - it was agreed that ALL Serive Provider Appointments should commence at Midnight UTC. Text against DI-086 and Di-121 has been removed. A new section addressing the treatment of Time has been added to the Additional Information tab of DES-138 | Entered Value Added.
Log | DIN-614 | J616 |  | SC to create Treatment of Time section | Entered Value Added.
Log | DIN-615 | J617 |  | Clarification following on from DIN-574. Text against Number of Register Digits field ammended to say "per the manufacturer specification" . Note text for SCS validation will remain unchanged. | Entered Value Added.
Log | DIN-616 | J618 |  | A Review of BP003C is required to impact assess implications of SP UTC Decision | Entered Value Added.
Log | DIN-618 | J620 |  | Could you please clarify what updates the Metering Service will receive via the PUB_026. From the routing the only update is re the SCCandProfile Class. However, BP010C alludes to the MS receiving an update for the SMSO - could you please confirm which is correct? | Entered Value Added.
Log | DIN-619 | J621 |  | Update BP08 existing or draft Unmetered Specific version. | Entered Value Added.
Log | DIN-620 | J622 |  | Remove EES as a Recipient of IF-001 | Entered Value Added.
Log | DIN-207 | K209 | Requires Industry Work Group review | Initial Assessment/Updating | Entered Value Changed.
Log | DIN-258 | K260 | Industry CP Required | Closed | Entered Value Changed.
Log | DIN-278 | K280 | Requires Industry Work Group review | Initial Assessment/Updating | Entered Value Changed.
Log | DIN-362 | K364 | Initial Assessment/Updating | Closed | Entered Value Changed.
Log | DIN-390 | K392 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
Log | DIN-409 | K411 | Ready for Internal Review | Initial Assessment/Updating | Entered Value Changed.
Log | DIN-411 | K413 | Requires Industry Work Group review | Initial Assessment/Updating | Entered Value Changed.
Log | DIN-451 | K453 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
Log | DIN-474 | K476 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
Log | DIN-475 | K477 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
Log | DIN-481 | K483 | Ready for Internal Review | Initial Assessment/Updating | Entered Value Changed.
Log | DIN-482 | K484 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
Log | DIN-485 | K487 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
Log | DIN-486 | K488 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
Log | DIN-487 | K489 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
Log | DIN-494 | K496 | Ready for Internal Review | Initial Assessment/Updating | Entered Value Changed.
Log | DIN-503 | K505 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
Log | DIN-511 | K513 | Open - awaiting assessment | Closed | Entered Value Changed.
Log | DIN-548 | K550 | Open - awaiting assessment | Initial Assessment/Updating | Entered Value Changed.
Log | DIN-552 | K554 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
Log | DIN-568 | K570 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
Log | DIN-571 | K573 | Initial Assessment/Updating | Ready for Internal Review | Entered Value Changed.
Log | DIN-576 | K578 | Requires Industry Work Group review | Closed | Entered Value Changed.
Log | DIN-580 | K582 | Open - awaiting assessment | Closed | Entered Value Changed.
Log | DIN-588 | K590 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-589 | K591 |  | Open - awaiting assessment | Entered Value Added.
Log | DIN-590 | K592 |  | Open - awaiting assessment | Entered Value Added.
Log | DIN-591 | K593 |  | Open - awaiting assessment | Entered Value Added.
Log | DIN-592 | K594 |  | Open - awaiting assessment | Entered Value Added.
Log | DIN-593 | K595 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-594 | K596 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-595 | K597 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-596 | K598 |  | Initial Assessment/Updating | Entered Value Added.
Log | DIN-597 | K599 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-598 | K600 |  | Closed | Entered Value Added.
Log | DIN-599 | K601 |  | Closed | Entered Value Added.
Log | DIN-600 | K602 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-601 | K603 |  | Open - awaiting assessment | Entered Value Added.
Log | DIN-602 | K604 |  | Initial Assessment/Updating | Entered Value Added.
Log | DIN-603 | K605 |  | Initial Assessment/Updating | Entered Value Added.
Log | DIN-604 | K606 |  | Initial Assessment/Updating | Entered Value Added.
Log | DIN-605 | K607 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-606 | K608 |  | Initial Assessment/Updating | Entered Value Added.
Log | DIN-607 | K609 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-608 | K610 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-609 | K611 |  | Initial Assessment/Updating | Entered Value Added.
Log | DIN-610 | K612 |  | Requires Industry Work Group review | Entered Value Added.
Log | DIN-611 | K613 |  | Initial Assessment/Updating | Entered Value Added.
Log | DIN-612 | K614 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-613 | K615 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-614 | K616 |  | Initial Assessment/Updating | Entered Value Added.
Log | DIN-615 | K617 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-616 | K618 |  | Initial Assessment/Updating | Entered Value Added.
Log | DIN-617 | K619 |  | Open - awaiting assessment | Entered Value Added.
Log | DIN-618 | K620 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-619 | K621 |  | Open - awaiting assessment | Entered Value Added.
Log | DIN-620 | K622 |  | Ready for Internal Review | Entered Value Added.
Log | DIN-52 | L54 | 4/27/2023 (27/04/2023 00:00:00) |  | Entered Value Deleted.
Log | DIN-278 | L280 |  | Pending CR-29 approval | Entered Value Added.
Log | DIN-411 | L413 | 8/16/2023 (16/08/2023 00:00:00) |  | Entered Value Deleted.
Log | DIN-576 | L578 | 8/4/2023 (04/08/2023 00:00:00) |  | Entered Value Deleted.
Log | DIN-610 | L612 |  | 8/31/2023 (31/08/2023 00:00:00) | Entered Value Added.
Log | DIN-158 | M160 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
Log | DIN-207 | M209 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
Log | DIN-258 | M260 | Interim Release 5 |  | Entered Value Deleted.
Log | DIN-362 | M364 | Interim Release 5 |  | Entered Value Deleted.
Log | DIN-409 | M411 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
Log | DIN-481 | M483 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
Log | DIN-490 | M492 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
Log | DIN-494 | M496 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
Log | DIN-511 | M513 | Interim Release 5 |  | Entered Value Deleted.
Log | DIN-544 | M546 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
Log | DIN-554 | M556 | Interim Release 4 | Interim Release 5 | Entered Value Changed.
Log | DIN-576 | M578 | Interim Release 5 |  | Entered Value Deleted.
Log | DIN-578 | M580 |  | Interim Release 5 | Entered Value Added.
Log | DIN-588 | M590 |  | Interim Release 4 | Entered Value Added.
Log | DIN-589 | M591 |  | Interim Release 5 | Entered Value Added.
Log | DIN-590 | M592 |  | Interim Release 5 | Entered Value Added.
Log | DIN-591 | M593 |  | Interim Release 5 | Entered Value Added.
Log | DIN-592 | M594 |  | Interim Release 5 | Entered Value Added.
Log | DIN-593 | M595 |  | Interim Release 5 | Entered Value Added.
Log | DIN-594 | M596 |  | Interim Release 5 | Entered Value Added.
Log | DIN-595 | M597 |  | Interim Release 5 | Entered Value Added.
Log | DIN-596 | M598 |  | Interim Release 5 | Entered Value Added.
Log | DIN-597 | M599 |  | Interim Release 4 | Entered Value Added.
Log | DIN-600 | M602 |  | Interim Release 5 | Entered Value Added.
Log | DIN-601 | M603 |  | Interim Release 5 | Entered Value Added.
Log | DIN-602 | M604 |  | Interim Release 5 | Entered Value Added.
Log | DIN-603 | M605 |  | Interim Release 5 | Entered Value Added.
Log | DIN-604 | M606 |  | Interim Release 5 | Entered Value Added.
Log | DIN-605 | M607 |  | Interim Release 5 | Entered Value Added.
Log | DIN-606 | M608 |  | Interim Release 5 | Entered Value Added.
Log | DIN-607 | M609 |  | Interim Release 5 | Entered Value Added.
Log | DIN-608 | M610 |  | Interim Release 5 | Entered Value Added.
Log | DIN-609 | M611 |  | Interim Release 5 | Entered Value Added.
Log | DIN-610 | M612 |  | Interim Release 5 | Entered Value Added.
Log | DIN-611 | M613 |  | Interim Release 5 | Entered Value Added.
Log | DIN-612 | M614 |  | Interim Release 5 | Entered Value Added.
Log | DIN-613 | M615 |  | Interim Release 4 | Entered Value Added.
Log | DIN-614 | M616 |  | Interim Release 5 | Entered Value Added.
Log | DIN-615 | M617 |  | Interim Release 4 | Entered Value Added.
Log | DIN-616 | M618 |  | Interim Release 5 | Entered Value Added.
Log | DIN-617 | M619 |  | Interim Release 5 | Entered Value Added.
Log | DIN-618 | M620 |  | Interim Release 5 | Entered Value Added.
Log | DIN-619 | M621 |  | Interim Release 5 | Entered Value Added.
Log | DIN-620 | M622 |  | Interim Release 5 | Entered Value Added.
Log | DIN-158 | P160 | Recommending a change to this ISD Data Item: Settlement Period Quality Indicator to be set as per Appendix 1 of MHHSP_METH007 MDS_Method_Statement v5.0 This data item need to be changes to something like ‘Valid Settlement Period Quality Indicator Set’ and the field size needs to be increased. The data catalugue will need the revised data item and the field length will need increasing from 20 to at least 50. This Item also appears in some interfaces that will need t be updated This is because it represents a set of SPQIs. The initial intention is to populate as per the table and check if any new SPQIs have been introduced in the baseline design Method Statement that are not covered. If new CCCs are introduced the appropriate flags for each new CCC would need to be agreed. However, it is likely that another dimension to the table below would need to be introduced to facilitate new CCCs. Word 'Illustrative' to be removed and will be updated to say Valid Settlement Quality Indicator Set. Change to be | This DIN has been moved to Interim Release 5 as it is related to DIN-409 which has an objection raised that is pending a discussion to clarify the solution. Recommending a change to this ISD Data Item: Settlement Period Quality Indicator to be set as per Appendix 1 of MHHSP_METH007 MDS_Method_Statement v5.0 This data item need to be changed to something like ‘Valid Settlement Period Quality Indicator Set’ and the field size needs to be increased. The data catalugue will need the revised data item and the field length will need increasing from 20 to at least 100. This Item also appears in some interfaces that will need to be updated. This is because it represents a set of SPQIs. The initial intention is to populate as per the table and check if any new SPQIs have been introduced in the baseline design Method Statement that are not covered. If new CCCs are introduced the appropriate flags for each new CCC would need to be agreed. However, it is likely that another dimension to the table below would ne | Entered Value Changed.
Log | DIN-207 | P209 | Participants have raised objections against the solution therefore this DIN will be taken to the next DRG to provide clarity. Appointments become active at midnight local time. | At the DRG held on 4th August it was agreed that Appointments need to become active in UTC. DIN- was raised to update the relevant artefacts to reflect this decision. Old solution: Appointments become active at midnight local time. Participants raised objections against the old solution therefore this DIN went to a DRG on 4th Aug for discussion. | Entered Value Changed.
Log | DIN-241 | P243 | Linked to expected LDSO CR on DIP Message Optionality - Update as part of wider CR review | Closed - Linked to expected LDSO CR26 on DIP Message Optionality - Update as part of wider CR review | Entered Value Changed.
Log | DIN-258 | P260 | LDSOs have been advised to raise a Programme Change Request. Discussion at the DRG of the 27/4/23 did not agree on the development of a New Design Principle, A further workshop with LDSOs needs to take place to discuss alternate options and confirm agreement amoungst all DNOs & IDNO on the receipt of publication | CR26 has been raised to covere this LDSOs have been advised to raise a Programme Change Request. Discussion at the DRG of the 27/4/23 did not agree on the development of a New Design Principle, A further workshop with LDSOs needs to take place to discuss alternate options and confirm agreement amoungst all DNOs & IDNO on the receipt of publication | Entered Value Changed.
Log | DIN-358 | P360 | Annual Consumption Method Statement updated with following text in red: 1.1 The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN within 30 calendar days following notification of the set-up of that MPAN in MHHS-IF-036 Registration Service Notification of Service Appointment & Supporting information. . | Annual Consumption Method Statement updated with following text in red: 2.3 The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN within 30 calendar days following notification of the set-up of that MPAN in MHHS-IF-036 'Registration Service Notification of Service Appointment & Supporting information' or MHHS-IF-001 ‘Notification of change of Supplier’. | Entered Value Changed.
Log | DIN-362 | P364 | Kevin Spencer to arrange a session with Mike Ceney to discuss solution further. | Kevin Spencer to arrange a session with Mike Ceney to discuss solution further. Upon further discussion with Kevin Spencer on 4/8/23 it was confirmed this DIN could be closed as the change is in relationn the AC Method Statement. No changes required to the LSS Method Statement | Entered Value Changed.
Log | DIN-390 | P392 | Update BP010B to show Data Service and Metering Service receiving IF-018 for DUoS Tariff ID updates in line with the routing rules in DES-138. | Update BP010B to show Data Service and Metering Service receiving PUB-018 for DUoS Tariff ID updates in line with the routing rules in DES-138. Update BPD010 process description to includes steps to recieve PUB-018 for Data Service and Metering Service. | Entered Value Changed.
Log | DIN-409 | P411 | Amendments relating to “Valid Settlement Period Quality Indicator Set” wording and field length in section M5 of EDI012 ISD entities document. Change also made from Metering Service ID MPID to Metering Service {MS Id} in Entitiy M8 | Amendments relating to “Valid Settlement Period Quality Indicator Set” wording and field length in section M5 of EDI012 ISD entities document. Change also made from Metering Service ID MPID to Metering Service {MS Id} in Entitiy M8. An objection was raised against this DIN. Following discussion at the DRG about this DIN it has now been moved to Interim Release 5. A decision was made at DRG to go with OPTION 2: Change Existing Layout – Remove list element in favour of individual row(s) for each valid combination for the Valid Settlement Period Quality Indicator Set. | Entered Value Changed.
Log | DIN-411 | P413 | 13/07: John Wiggins to have offline discussion with Sean C as DIN requires wider discussion at DRG to progress SRO Team disagree with this Migration Request. Market Segment must be known prior to the selection of MHHS Service Providers. Market Segment is a derived field based on Connection Type and Meter Type. Connection Type must be set before Migration / Meter Type already known so Market Segement CAN be derived, set and maintained prior to MPAN migration. No change to baseline documentation Required. | 03/08: SCS confirmed in a session with SC that they agreed that Segment is a derived value based on Connection Type and MTR. There are validation rules that prevent the migration if Connection Type (and therefore segment) is not already defined in REGS. To address the original question Segment will always be known at the point of migration. Therefore, no changes are required to Migration document. 13/07: John Wiggins to have offline discussion with Sean C as DIN requires wider discussion at DRG to progress SRO Team disagree with this Migration Request. Market Segment must be known prior to the selection of MHHS Service Providers. Market Segment is a derived field based on Connection Type and Meter Type. Connection Type must be set before Migration / Meter Type already known so Market Segement CAN be derived, set and maintained prior to MPAN migration. No change to baseline documentation Required. | Entered Value Changed.
Log | DIN-474 | P476 | Addition of data items DI-503-DI-513 to data catalogue and across ECS reports artefact. MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Addition of data items DI-503, DIDI-515 to data catalogue and across ECS reports artefact. MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal Missing data items added to data catalogue Di-403/DI-404/DI-514/DI-515 | Entered Value Changed.
Log | DIN-478 | P480 | Update DES138 so that it is clear that the minimum number of settlement days in a message is increasing from 150 to 194. | Agreed to limit the number of MQ IDs per IF-021 submission to ONE only and limit settlement days to 200. Swagger has been updated to limit the number of MQIDs to 1. Swagger updated to limit the maximum number of Settlement Days to 200. DES138 also updated to aligned with the above changes for IF-021. | Entered Value Changed.
Log | DIN-481 | P483 | Two new data type references have been created DT-024 and DT-024N. For NUM(16,6) data type within ECS reports/ECS data catalogue replace DT-023/DT-023N with DT-024/DT-024N. | Two new data type references have been created DT-024 and DT-024N. For NUM(16,6) data type within ECS reports/ECS data catalogue replace DT-023/DT-023N with DT-024/DT-024N. DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. | Entered Value Changed.
Log | DIN-482 | P484 | Further details of the solution are under discussion/review. | LDSO's added to the To party list of IF-018 | Entered Value Changed.
Log | DIN-485 | P487 | Design changes required to Swagger 1.4 to support updates to API endpoints for DELETE API verbs to ensure we are able to remove the correct StatusMessage or PublicationConfig for the appropriate recipient combination. The isue also affects some of the POST methods where a recipient ID is required, e.g webhook config. A standard pattern is proposed where a recipeint id is specified in the path. Updates will also be made to E2E001 design document to ensure the document provides any clarity required. | Design changes required to Swagger 1.4 to support updates to API endpoints for DELETE API verbs to ensure we are able to remove the correct StatusMessage or PublicationConfig for the appropriate recipient combination. The issue also affects some of the POST methods where a recipient ID is required, e.g webhook config. A standard pattern is proposed where a recipeint id is specified in the path. Updates will also be made to E2E001 design document to ensure the document provides any clarity required. | Entered Value Changed.
Log | DIN-487 | P489 | Updates required to E2E001 design section 4.4.4 to ensure we improve clarity on schema vs data validation errors, with updates to worked examples and JSON examples. | In section 4.4.4.2, there are some examples that incorrectly return a 207 when they have failed schema validation. E2E001 section 4.4.4.2 has been updated to illustrate 2 examples. One that returns a 201 Created (2 messages as part of the HTTP Request, both pass validation) and another example that returns a 207 (2 messages part of the HTTP Request, but 1 does not pass validation). | Entered Value Changed.
Log | DIN-488 | P490 | Reinstated DI-484 "Settlement Period Duration" and added into R Groups as required | Reinstated DI-484 "Settlement Period Duration" and added into R Groups as required in Swagger 1.4 | Entered Value Changed.
Log | DIN-494 | P496 | Swagger 1.4 to be updated for DI-091 minimum is 5 and maximum is 6. Currently this is 1 and 1 respectively which is incorrect. | Swagger 1.4 to be updated for DI-091 minimum is 5 and maximum is 6. Currently this is 1 and 1 respectively which is incorrect. DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. | Entered Value Changed.
Log | DIN-503 | P505 | Update any Data Items that utilise InterfaceID to align with the enumeration of values defined for DI-000 so that this is unique across all interface / report types. This includes data types like SenderUniqueReference (DI-995) and TransactionID (DI-990). This change will require updates in DES-138, E2E001 and Swagger 1.4. | Update any Data Items that utilise InterfaceID to align with the enumeration of values defined for DI-000 so that this is unique across all interface / report types. This is for data types SenderUniqueReference (DI-995) and TransactionID (DI-990). This change will require updates in DES-138, E2E001 and Swagger 1.4. In DES-138, DT-014 has been updated to String65 from String60 to support Interface being updated from 3 to 8 to align with DI-000 (so for IF-003, rather than 003 being included in the transactionID / senderUniqueReference, this will be IF003 with no hyphen). In Swagger, DT-014 has been updated to max length 65, with examples updated. E2E001 updated examples for senderUniqueReference and TransactionID to align with the above. | Entered Value Changed.
Log | DIN-511 | P513 |  | COvered as part of CR019 | Entered Value Added.
Log | DIN-548 | P550 | Reword the requirements to reflect the baselined BAU requirements more closely | Internal discussion required between Elexon, KS and MH to reword the requirements to reflect the baselined BAU requirements more closely. Session to be arranged once Transition requirements have been handed over to Elexon. | Entered Value Changed.
Log | DIN-552 | P554 | Add UTF-8 as the JSON encoding required in the E2E001 design document. | Add UTF-8 as the JSON encoding required in the E2E001 design document, creating a new section 4.2.5. | Entered Value Changed.
Log | DIN-554 | P556 | Agreed changes with SCS, awaiting feedback from RECCO Linked to DIN-149. | DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. Agreed changes with SCS, awaiting feedback from RECCO Linked to DIN-149. | Entered Value Changed.
Log | DIN-568 | P570 | DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) shows in YAML as secondaryRecipientDIPID and primaryRecipientDIPID respectively and this should be updated in DES-138 YAML column so this aligns with Swagger 1.4 ie, DI-981 (secondaryRecipients) and DI-982 (primaryRecipients). DES-138 needs to be updated to align with Swagger. | DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) shows in YAML as secondaryRecipientDIPID and primaryRecipientDIPID respectively and this has been updated in DES-138 YAML column so this aligns with Swagger 1.4 ie, DI-981 (secondaryRecipients) and DI-982 (primaryRecipients). | Entered Value Changed.
Log | DIN-571 | P573 | Need to update DES-138 and Swagger to ensure DI-980 definition is applied consistently for single response vs array of responses. | I have updated Swagger 1.4 so that DI-980 definition is applied consistently for single response vs array of responses. For single, it will be responseMessage. For an array of messages, it will be responseMessages. To this effect, B066.responseMessages has been updated to be responseMessage. Also, B066 block has been updated to align with DES-138 to be conditionally mandatory, rather than mandatory. | Entered Value Changed.
Log | DIN-576 | P578 | Feedback required from industry at next work-group | Following DRG on 4th Aug, it was agreed that St Clements Services were to work-up the topics discussed, and a dedicated workshop would be arranged to discuss this further. St Clements Services have advised the Programme that they will now not be pursuing proposals made at the DRG session and would be reverting to implement to the original design, therefore closure of this DIN. | Entered Value Changed.
Log | DIN-580 | P582 |  | The Design Team and SRO are actively engaged with St Clements on issues around problematic switches. The plan is for them to provide us with a list of of their issues. We will then go through a process of raising these directly with CSS. Dependent on outcomes we receive back, we will look to discuss this with St Clements with the possibility of raising a CR for a specified data correction tool to align the data and send out the appropriate MHHS flows. | Entered Value Added.
Log | DIN-588 | P590 |  | All instances of ID have been changed to Id | Entered Value Added.
Log | DIN-589 | P591 |  | Align the ADS method statement with the SDS method statement to resolve the discrepancy | Entered Value Added.
Log | DIN-593 | P595 |  | The following changes below in red have been made to section 2.2 of the AC Method Statement The Market-wide Data Service (MDS) should schedule the calculation of MPANs requiring a new Annual Consumption for active MPANs evenly across each working day of the month and publish on the first available working day following the calculation. The recalculation shall be performed each month, for every MPAN and every 30 Calendar days +/- 5 Calendar days of the date of the previous calculation. Changes to the calculation of less than 365 days available are no longer reuried as agreed with Heix | Entered Value Added.
Log | DIN-594 | P596 |  | Rejection was incorrectly shown being sent direct from REGS rather than from REGS Via DIP. | Entered Value Added.
Log | DIN-595 | P597 |  | Correction of type in definition of subscript 3 for table M16 - "Market Participant ID" changed to "Market Participant Role" | Entered Value Added.
Log | DIN-597 | P599 |  | IF-026 / B069 - SCS requested removal of wording "must be required for smart meter removed" as this is inherant as part of the Event Type. | Entered Value Added.
Log | DIN-598 | P600 |  | Any change in this area would require changes to the REGS Requirements to implemnt Primary Routing, as copying of such flows could not be performed by DIP Secondary Routing. CR would be required to confirm new requirements and allow for IA on REGS and Suppiers design. Design Team also note that no other issues/DIN raised on this issue, by suppliers or other participants. | Entered Value Added.
Log | DIN-599 | P601 |  | This change has been forwarded onto the Data Cleansing Working Group as it is not a design issue. Design Team also advised SCS to raise these issues within the working group. | Entered Value Added.
Log | DIN-600 | P602 |  | Corrected M18 Col Headings to read "DIPRole" | Entered Value Added.
Log | DIN-601 | P603 |  | This is deliberate. Sean has the details | Entered Value Added.
Log | DIN-602 | P604 |  | Update the swagger for the majority of interfaces where different event codes require different combinations of optionality for the blocks they reference. An example of this has been done already for IF-001 in the new swagger file Interface-001. Estimate 3/4 days effort to complete | Entered Value Added.
Log | DIN-605 | P607 |  | Message updated to make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations will be held awaiting completion of PUB-34 processing. | Entered Value Added.
Log | DIN-606 | P608 |  | Waiting for OPS C document to be copied to R5 folder | Entered Value Added.
Log | DIN-607 | P609 |  | SCS Request Update IF-035 Lapsed Reason Code from "Switch Cancelled" to "Registration Cancelled" | Entered Value Added.
Log | DIN-608 | P610 |  | Steps 86,87,88 added to better reflect that REGS will actually send TWO IF-035 messages not just one. IF-035 [SendMTD] will be issued to Incumbent MS and [AppOutcome] event will be issued to DS/Supplier. BP003 now mirrors the drafting in BP002. | Entered Value Added.
Log | DIN-609 | P611 |  | Waiting feedback from Helix Package 1 Team | Entered Value Added.
Log | DIN-610 | P612 |  | Meeting held with Helix Team - Awaiting feedback before slides can be prepared for DRG meeting | Entered Value Added.
Log | DIN-612 | P614 |  | Added x2 new validtion rules to prevent the creation / addition of Related MPANs with a Connection Type of "U - Unmetered". No validation applied to remove so as to allow for the resolution of any historically erroneous links | Entered Value Added.
Log | DIN-613 | P615 |  | In line with DAG Decision on 4th Aug - it was agreed that ALL Serive Provider Appointments should commence at Midnight UTC. Text against DI-086 and Di-121 has been removed. A new section addressing the treatment of Time will be added to the Additional Information tab of DES-138 as part of R5 (DIN-614) | Entered Value Added.
Log | DIN-615 | P617 |  | Clarification following on from DIN-574. Text against Number of Register Digits field ammended to say "per the manufacturer specification" . Note text for SCS validation will remain unchanged. | Entered Value Added.
Log | DIN-618 | P620 |  | To update PUB-026 adding MS to the SMSO secondary routing. | Entered Value Added.
Log | DIN-620 | P622 |  | Removed EES as a Recipient of IF-001 - EES gets this info from CSS | Entered Value Added.
Log | DIN-482 | Q484 |  | Data interface correction | Entered Value Added.
Log | DIN-580 | Q582 |  | No Change | Entered Value Added.
Log | DIN-588 | Q590 |  | Supporting Document | Entered Value Added.
Log | DIN-593 | Q595 |  | Method statement correction | Entered Value Added.
Log | DIN-596 | Q598 |  | Clarification | Entered Value Added.
Log | DIN-597 | Q599 |  | Clarification | Entered Value Added.
Log | DIN-598 | Q600 |  | Clarification | Entered Value Added.
Log | DIN-599 | Q601 |  | Clarification | Entered Value Added.
Log | DIN-602 | Q604 |  | Improved error trapping at interface | Entered Value Added.
Log | DIN-605 | Q607 |  | Clarification | Entered Value Added.
Log | DIN-482 | R484 |  | Minor | Entered Value Added.
Log | DIN-588 | R590 |  | Minor | Entered Value Added.
Log | DIN-593 | R595 |  | Supporting Docs | Entered Value Added.
Log | DIN-596 | R598 |  | Supporting Docs | Entered Value Added.
Log | DIN-597 | R599 |  | Supporting Docs | Entered Value Added.
Log | DIN-598 | R600 |  | Clarification - No change Required | Entered Value Added.
Log | DIN-599 | R601 |  | Clarification - No change Required | Entered Value Added.
Log | DIN-600 | R602 |  | Minor | Entered Value Added.
Log | DIN-602 | R604 |  | Minor | Entered Value Added.
Log | DIN-605 | R607 |  | Minor | Entered Value Added.
Log | DIN-607 | R609 |  | Minor | Entered Value Added.
Log | DIN-588 | S590 |  | Supporting Document | Entered Value Added.
Log | DIN-593 | S595 |  | Method Statement | Entered Value Added.
Log | DIN-596 | S598 |  | Interfaces | Entered Value Added.
Log | DIN-597 | S599 |  | Interfaces | Entered Value Added.
Log | DIN-600 | S602 |  | Interfaces | Entered Value Added.
Log | DIN-602 | S604 |  | Interfaces | Entered Value Added.
Log | DIN-605 | S607 |  | Interfaces | Entered Value Added.
Log | DIN-607 | S609 |  | Interfaces | Entered Value Added.
Log | DIN-158 | T160 | MHHSP-METH006_VAS_Method_Statement ED021 ISD Entity spec MHHSP-DES138-Interface Catalogue ECS report | MHHSP-METH006_VAS_Method_Statement MHHSP-METH007_MDS_Method_Statement v5.1 ED021 ISD Entity spec MHHSP-DES138-Interface Catalogue ECS report | Entered Value Changed.
Log | DIN-482 | T484 |  | DES138 | Entered Value Added.
Log | DIN-588 | T590 |  | MHHSP_EDI021_ISD_Entities v5.3.2 | Entered Value Added.
Log | DIN-590 | T592 |  | E2E001 MHHSP_EDI021_ISD_Entities | Entered Value Added.
Log | DIN-591 | T593 |  | MDS Method Statement DES138 | Entered Value Added.
Log | DIN-593 | T595 |  | Annual Consumption Meth 10 | Entered Value Added.
Log | DIN-594 | T596 |  | BP010-Registration Updates | Entered Value Added.
Log | DIN-595 | T597 |  | E2E001 MHHSP_EDI021_ISD_Entities | Entered Value Added.
Log | DIN-596 | T598 |  | DES-138 Interface Spec | Entered Value Added.
Log | DIN-597 | T599 |  | DES-138 Interface Spec | Entered Value Added.
Log | DIN-600 | T602 |  | DES-138 Interface Doc | Entered Value Added.
Log | DIN-602 | T604 |  | Swagger, possibly add clarification to DES138 | Entered Value Added.
Log | DIN-605 | T607 |  | BP002 / BP003 Change of SP | Entered Value Added.
Log | DIN-607 | T609 |  | DES-138 Interface Doc | Entered Value Added.

## Backup 030723 (hidden)
DIN ITEM DETAILS | [9 empty] | Scheduling |  |  | DIN IMPACT ASSESSMENT
Reference | other Reference(s) | Date Raised | Organisation | Freshdesk Ticket # | Contact Name | Constituency | Title | Design Issue Notification Details (as notified by participant) | Current Status | Target working Group Date (If Required) | Target Release | Objection Cut-off Date | Design Issue Proposed solution | Justification/Type of Change | Design Area | Design Area - L2 | Artefact(s) Impacted
MHHS-DIN-1 | T4-COM-1744 | 2023-01-30 | St Clements | 2655 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1744 on 15th Sept 2022 MPRS does not currently restrict IHD Installs to Smart Meters, there maybe cases where there is an IHD present but the Meter is Trad (Not compatible with DCC and Customer Switched) Either Allow IHD on all Market Segments OR Cleansing to ensure IHDs are only present on S2 and S1 Meters SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses, as this is still not resolved | Implemented |  | Interim Release 1 |  | Discussed with SCS and agreed to add new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) Added requirements into BRS003. SCS to raise a potential data cleanse. | Requirement correction | MPAN Ownership | SCS Validation | MHHSP-BRS003-Registration Requirements
MHHS-DIN-2 | T4-COM-1745 | 2023-01-30 | St Clements | 2657 | Madison Layton | Software Provider |  | Orginally raised as T4-COM-1745 on 15th Sept 2022 DB002 is not the interface on which MPRS will be informed of a change to import/export relationship, it is DB05. The wrong diagram was updated, the EDI was updated to DB05 not import/export. SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses and artefact updates, to inform the wrong data item diagram was updated. However the diagram for EDI updates is still incorrectly reading DB005 update instead of DB02 | Closed |  |  |  | This appears to have been missed in v4.6 - the arrow on BP-010B from step435 to Step 440 shows DB005 (not DB05, assume that’s a minor typo in the comment) - and this is the Energy Direction Information (EDI) which is wrong. It has cbeen onfirmed that this was updated in v4.7 to go into v5.0 baseline. | No Change |  |  | None
MHHS-DIN-3 | T4-COM-1752 | 2023-01-30 | St Clements | 2661 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1752 on 15th Sept 2022: MHHS-BR-RS-020: "Retro" (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier ) In the D0205 the Supplier can cancel out the current Agent Appointment by setting the EFD to equal the currently stored Appointment EFD. Is this no longer allowed? All Services must be appointed for at least one day valid or not? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: removing the ability for Suppliers to Correct Invalid Service Appointments may not be understood by suppliers. We want to avoid a later Design CR to add this functionality in. SCS has not had a response, feel this is important discuss with Suppliers to avoid later CRs | Closed |  |  |  | The appointment can be resubmitted if it hasn’t been accepted yet. Once accepted, there is a need to maintain contiguous appointment periods. The scenario mentioned is the CoA not linked to a switch, so the acceptance of a new appointment from a particular EFD will ‘lock in’ that date and the previous MS/DS will be de-appointed at midnight on the previous day. This is to ensure that there are no periods left without MS and/or DS in place, which can happen today with D0155/D0151 sequencing issues. As an overall comment, there is not a concept of cancellation of appointments. The only way to alter the appointment is to get a new IF-031 issued. The only way to do this for the scenario presented, would be to issue an IF-031 for the old MS for the original date and an IF-031 for the new MS for the revised date. Requirement MHHS-BR-RS-021 ensures that Registration Service will action the latest received appointment where there are duplicate appointments for the same day. St Clements had requested that we build in a rule saying that you cannot submit a Change of Service Provider (CSP) request for the same Service Provider. It is a bit of a work-around, but we believe sending it as SEG should work, or alternatively a CR would be required to re-look at the interface validation. Closing, as this doesn't require further action - point noted. We have already spoken to a number of suppliers, and will continue to engage to ensure the functionality of the baselined design is understood and any issues picked up as early as possible. Documentation for LDSOs to point at. Pick up in Code Drafting as well. | No Change |  |  | None
MHHS-DIN-4 | T4-COM-1755 | 2023-01-30 | St Clements | 2666 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1755 on 15th Sept 2022: MHHS-BR-RS-071.2 REC CP R062 has been raised to remove the restriction on the number of EDI changes. Will this cause any downstream MHHS issues? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Needs to be aligned with REC Change No responses | Closed |  |  |  | As per original SRO response, the impacts of the REC change need to be dealt with through the REC change process and impact assessment. | No Change |  |  | None
MHHS-DIN-5 | T4-COM-1760 | 2023-01-30 | St Clements | 2667 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1760 on 15th Sept 2022: There are no Registration Service Reports defined in MHHSP-ERI011A. Will there be a requirement for MPRS to produce any Industry Reports for MHHS? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Design for the complete solution must be defined by M5. This is a DBT Design Start Blocker No responses This could significantly increase DBT time as development of reports can be costly and time consuming | Closed |  |  |  | Who is raising these requirements? What happens today? Possibly CC issues Agreed with SCS that reporting requirements will be introduced via the CR process. Reporting requirements are to be added to the programme RAID log | No Change |  |  | None
MHHS-DIN-6 | T4-COM-1761 DI-7 | 2023-01-30 | St Clements | 2668 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1761 on 15th Sept 2022: IF-005, REG1014 First MAP Block, MAP Eff From Date [DI-054] in message, must = MPAN Install date OR >= Eff Form date of all existing MAP Effective From Dates held in Registration prior to first [DI-054] in message I understand that the First MAP must equal the Install Date, I am unsure what the second condition is trying to say? You can not have a Meter Without a MAP. (ignoring customer owned meters where CUST is used) SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: response is incorrect. The Second Rule "Each subsequent MAP Effective From Date [DI-054] must be > MAP Eff From Date in previous block" covers the subsequent overlapping MAPs. The second half of this First Block Rule must be removed. The First Block can only ever equal the install date No responses, the rule has not been amended | Implemented |  | Interim Release 1 |  | This appears valid - the first MAP block can only start at the creation date (assuming the MAP blocks are in chronological order, which they must be if each subsequent map block has an EFD > the last) Currently the design allows 2 ways to amend the MAP History as outlined in Sections 13 and 14 of the IF005 Use Case Guide. Either the Metering Service can provide the full MAP history from the installation date or they can add a new MAP to the existing history, provided it is the next MAP in chronological order. So for example if you have MAPs 1,2 and 3, then you can extend to MAPs 1,2, 3 and 4 using the approach set out in section 14 to extend the MAP history. However if you wanted to set MAP 4 between 2 and 3, you would need to send the whole MAP history from the install date and provide 1,2,4 and 3 as set out in Section 13 to replace MAP history. The second validation rule is required if you are using the extend the MAP history functionality. Added note to REG Notes that where a MAP history is provided it must be in chronological order Added new REG1014 Validation Rule to MeterInstall and MeterExchange events to ensure only 1 MAP block is provided | Data interface correction | MPAN Ownership | SCS Validation | MHHSP-DES138-Interface Catalogue
MHHS-DIN-7 | DI-8, DI-11, DI-12, DI-14 | 2023-01-30 | St Clements | 2669 | Madison Layton | Software Provider |  | MPRS will reject any PUB-031 inlcuding those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8) | Implemented |  | Interim Release 1 |  | See Comments Revised CSS Registration Request ID validation on IF-031, 034 and 025 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | IF General | MHHSP-DES138-Interface Catalogue
MHHS-DIN-8 | N/A | 2023-02-01 | Elexon | 2642 | Sedef Kiris | Central Body |  | We have had the following comment ........... Also just found out that “Metering Service Id” have “MPID” in brackets afterwards, and not “MSID”. We believe it should be MSID | Closed |  |  |  | MPID is the correct term here, it is the metering service MPID. MHHSP_EDI012_ISD_Entities v4.6 Section M8 | No Change |  |  | None
MHHS-DIN-9 | N/A | 2023-01-30 | St Clements | 2672 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: [UpdateSiteTechnicalInfoMS] is not included in the interface catalogue and is not utilised by MPRS. Assume this is related to Issue 99 and needs removing? (raised as DI ID 9) | Implemented |  | Interim Release 1 |  | Removed from IF-005 Guide Section 4.1 | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-10 | N/A | 2023-01-30 | St Clements | 2799/2670 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: Is the currently appointed Meter Service informed of Prospective MS changes? Changes to MTDs can be made by prospective MS (e.g. change meter type to complete SEG market change before the MS can be appointed). As the MS is only prospective at this point the MS may still be lapsed and not take effect. However any MTD updates made would remain within the MPRS system and not be backed out. The current MS would therefore need to be aware of what changes have been made by the prospective MS. (raised as DI ID 10) | Closed |  |  |  | BP009 only talks about the Metering Service, not the current or prospective Metering Service, and it appears only the registration service receive metering service MTD details, not the current MS. Refer to SRO - what is the assumption here, as the alternative route is for registration to update the current MS The design is based on PUB-006, with the Updated Meter details, being sent to the current Metering Service ( BP011A step 280 ) as well as the Prospective Metering Service (Step 275). It is built into the routing rules in PUB-006. | No Change |  |  | None
MHHS-DIN-11 | N/A | 2023-01-30 | St Clements | 2675 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install / Remove Date(s) takes place within the Metering Services period of ownership (or proposed period of ownership for in the case of a prospective SEG appointment) " Sent on 11th Jan: Does not match business rules, as future dated installs are not allowed: "REG1020 - Meter Install Date [DI-057] cannot take place in the future. The proposed MS on a seg will have a future dated EFD, so they only have the +2 day lapse extension period for meter installs (raised as DI ID 11) | Implemented |  | Interim Release 1 |  | Added change of segment scenario's to IF005 USE CASE Guide. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-12 | N/A | 2023-01-30 | St Clements | 2679 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install /Remove Date(s), cannot have taken place in the future" Sent on 11th Jan: It would be useful to have the Change of Segment process covered in this guide. We are not sure how the Prospective MS can exchange meters when their appointment period is in the future (raised as DI ID 12) | Implemented |  | Interim Release 1 |  | Nomenclature issue - requires a reword of this statement to conform to the business rules. Recommend the following update to section 3.2 of the IF005 Use Case Guide to confirm who can make Metering updates Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed BAU metering updates ( For the avoidance of doubt not meter update/meter history updates), it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. The one exception, is during a change of segment, when the incoming Metering Service is able to provide a BAU metering update, where it’s prospective “SEG” appointment is due to become active on the same day. SEG scenario's added to IF005 Use case guide Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-13 | N/A | 2023-01-30 | St Clements | 2683 | Madison Layton | Software Provider |  | Comment on Section 5.1 "validation allows for meter removal at a point following Disconnection if required)" Sent on 11th Jan: This rule prevents this REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational (raised as DI ID 13) | Implemented |  | Interim Release 1 |  | This statement doesn't appear to be a convention. There is no mention of this in E2E001 End to End Solution Architecture. Believe this statement needs to be amended or removed. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. IF-005 validation Rule changed to include meter removal at status Disconnected | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES138-Interface Catalogue, E2E001 End to End Solution Architecture
MHHS-DIN-14 | N/A | 2023-01-30 | St Clements | 2684 | Madison Layton | Software Provider |  | Comment on Section 3.2 "Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed metering updates, it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. " Statement is misleading- the 10 day period is only permitted for install, remove and exchange events, it is not listed for meterUpdate/meterHistoryUpdate in interface catalogue Also the prospective MS should be able to make changes for SEG to enable a market segment change to complete (raised as DI ID 14) | Implemented |  | Interim Release 1 |  | Validation rule(s) updated to constrain 10 day window to non-update events. Test in 3.2 reworded to remove ambiguity. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-15 | N/A | 2023-01-30 | St Clements | 2685 | Madison Layton | Software Provider |  | Comment raised in guide, sent on 11th Jan, that the JSON examples use MPID when it should use DIP ID e.g."distributorID": "SWAL" (raised as DI ID 15) | Implemented |  | Interim Release 1 |  | Corrected to use Dist DIP ID | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-16 | N/A | 2023-01-30 | St Clements | 2686 | Madison Layton | Software Provider |  | Comment on Section 9 " Albeit that these transactions can be ‘clubbed together’ and send as a group in single overarching message/API transaction. " Sent on 11th Jan: As DIP does not protect the sequencing of events (FIFO), is there a risk that the ordering of these updates might arrive out of sequence resulting in the wrong end state? If MS space out their updates it would reduce this risk (raised as DI ID 16) | Implemented |  | Interim Release 1 |  | Clairifcation added to Sec 9.2 to reference Time-Stamps rather than 'clubbing' | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-17 | DI-017 | 2023-01-30 | St Clements | 2690 | Madison Layton | Software Provider |  | Comment on Section 9 "a supporting MAP history commencing in line with the revised Installation Date must also be provided" Sent on 11th Jan: Will the MS know the full MAP history? Risk they could destroy the data. Potential MAP billing issues? (raised as DI ID 17) Ticket sent for background on how current design was reached (3/2/23) | Initial Assessment/Updating | 2023-05-24 | Interim Release 3 | 2023-07-12 | Solution agreed at DRG on what MAP updates are required |  |  |  | None
MHHS-DIN-18 | N/A | 2023-01-30 | St Clements | 2691 | Madison Layton | Software Provider |  | Comment on Section 9 "• When maintaining the MAP History in cases where there is no change in Meter Installation Date then the MAP history provided should commence either with a MAP Effective From Date matching the existing install date of the meter OR be greater than the most recent, already existing, MAP Effective From Date" Sent on 11th Jan: So it's possible to update ALL MAP history back to installation, or add a new MAP, but it's not possible to amend MAP history only part way back (have to go back to installation date instead every time to do this) (raised as DI ID 18) | Closed |  |  |  | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • To update BRS003, requirement MHHS-BR-RS-027 to add “Registration Service must lapse any appointments that fail this validation” • Remove Rejected from Step 225 of BP002/BPD002 • Remove Rejected from label on line after step 215 of BP003. | No Change |  |  | None
MHHS-DIN-19 | N/A | 2023-01-30 | St Clements | 2692 | Madison Layton | Software Provider |  | Comment on Section 10 "E2E Architecture convention states that all data items are provided in each message even where these data items are not changing or are null" Sent on 11th Jan: Some of the items are optional not mandatory which conflicts with this statement. Not all data items need to be provided (raised as DI ID 19) | Implemented |  | Interim Release 1 |  | Update of E2E Doc to allow for Nullable values. | Data interface correction | Meter to Bank |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-20 | N/A | 2023-01-30 | St Clements | 2693 | Madison Layton | Software Provider |  | Comment on Section 13, sent on 11th Jan: What should MPRS do if it holds a MAP not included in the MAPHistory block? (raised as DI ID 20) | Implemented |  | Interim Release 1 |  | Update "all existing history will be replaced by that contained within the message" | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-21 | N/A | 2023-01-30 | St Clements | 2699 | Madison Layton | Software Provider |  | Comment on Section 15.2 "It is understood that currently there a numerous instances of duplicated Meter ID’s, some of which may have overlapping installation dates. " Sent on Jan 11th: Meter id is only unique at mpan. Should not be any instances of conflicted MSNs at MPAN. Can you verify with ECOES? Or we can do a RFI to DNOs but will take time (raised as DI ID 21) | Implemented |  | Interim Release 1 |  | All references to duplicated MSN IDs has been removed from the document | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-22 | N/A | 2023-01-30 | St Clements | 2700 | Madison Layton | Software Provider |  | Comment on Seciton 15.3 "add some kind of suffix (X1, X2) to the existing Meter ID." Sent on Jan 11th: This can take the meter ID over the allowable string length (string 10), in this example it would take it to string(12) and so would be rejected (raised as DI ID 22) | Implemented |  | Interim Release 1 |  | As above, Section 15.3 removed from IF-005 User Guide. | Data interface correction | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-23 | N/A | 2023-01-30 | St Clements | 2701 | Madison Layton | Software Provider |  | Comment on Section 16.3 Sent on Jan 11th: Cancelled Flag Set. Only a logical deletion. Still held in MPRS but not visible to EES/MEM The section implies the record would be fully deleted from MPRS, however this is not correct, MPRS would set a cancellation flag that would indicate the record has effectively been cancelled/logically deleted. It would however remain in the systems database (raised as DI ID 23) | Implemented |  | Interim Release 1 |  | Added a statement at the end of the table in 16.3 to say "NB the registration service will only logically delete the MAP entry with a flag, it will not be deleted from the database." | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-24 | N/A | 2023-01-30 | St Clements | 2702 | Madison Layton | Software Provider |  | Comment on Section 17.2 "situations where multiple existing meters are identified, the selection process should be extended to include Meter Removal date (if provided) else;" Sent on Jan 11th: Shouldn’t be possible, can run an EES or MPRS RFI to confirm. Noting that MSN is only unique at an MPAN level not a databse level Related to DI-21 (raised as DI ID 24) | Implemented |  | Interim Release 1 |  | Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. The wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-25 | N/A | 2023-01-30 | St Clements | 2706 | Madison Layton | Software Provider |  | Comment on Section 17.2 "where multiple meters still exist even after matching on all three data items should be rejected and require manual intervention (i.e. request to LDSO to intervene) ." Sent on Jan 11th: There's no super user functionality for this so how could the LDSO intervene? The LDSO is not able to manually intervene in regards to MTDs, they can for some other data items such as registration data but not MTDs. (raised as DI ID 25) | Implemented |  | Interim Release 1 |  | Reference to LDSO User Removed - agreed with SCS that scenario should not arise provided existing SCS data rules are met | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-26 | N/A | 2023-01-30 | St Clements | 2707 | Madison Layton | Software Provider |  | Comment on Section 17.2 "If the MAP segment is not provided, the existing MAP history should be maintained to greatest degree possible, with ‘trimming’ to align to any revised Install / Remove Dates provided" Sent on Jan 11th: Risk that changing of the Meter Lifespan could result in MAPs being logically deleted. The MS would need to re-apply the MAP history to fit into the new meter Lifespan MS would need to understand this process/constraint (raised as DI ID 26) | Implemented |  | Interim Release 1 |  | Section 17.2 of the guidance document updated. Also added new validation rule REG1014 for MeterHistoryUpdate in IF-005 to ensure MAP is provided when creating a new meter picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-27 | N/A | 2023-01-30 | St Clements | 2708 | Madison Layton | Software Provider |  | Comment on Section 19.2 "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the permanent deletion of data, mirroring the existing functionality associated with the use of the D0312." Sent on Jan 11th: Only logically deleted, still visible in the MPRS History. Just not visible to MEM or EES Existing functionality on D0312 utilises cancellation flags not permanent deletion (raised as DI ID 27) | Implemented |  | Interim Release 1 |  | Reword to reflect the logical deletion. See MHHS-DIN-23 Reword this paragraph to: "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the removal of a MAP from a meters MAP history using a logical flag, mirroring the existing functionality associated with the use of the D0312." NB Main section header is incorrect - should be updated to section 19, rather than a duplicate of section 18. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-28 | N/A | 2023-01-30 | St Clements | 2709 | Madison Layton | Software Provider |  | Comment on Section 19.4 "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories. However, this would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." Sent on Jan 11th: This functionality already exists with the MPAN History Report showing who changed what when for all MPRS data items. Will be extended to include DIP transactional information (raised as DI ID 28) | Implemented |  | Interim Release 1 |  | Proposed Change Reword this paragraph to: "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories, noting that this is also available via the MPAN history report which will be updated with DIP transactional information and could also be used. Any use of EES would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-29 | N/A | 2023-01-30 | St Clements | 2710 | Madison Layton | Software Provider |  | There should be an additional rule for USP, if DI-830/DI-833 is populated, the MS/DS Proposed Effective From Date must equal the currently held EFD for the MS/DS appointment in MPRS (raised as DI 29) | Implemented | 2023-04-27 | Interim Release 1 |  | Added rule for USP scenario in IF-031 to check SP Effective from date. Proposing SCS have flexibility on error codes - requires industry Working Group. Picked up as part of Change of Service Provider review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-30 | N/A | 2023-01-30 | St Clements | 2711 | Madison Layton | Software Provider |  | The IF-035 does not provide the opportunity for MPRS to populate a lapsed reason. Will need to be able to provide a reason for a lapsed appointment, otherwise there'll be a higher volume of unecessary supplier enquries to DNOs which will require more resource and cost. (raised as DI 30) | Implemented |  | Interim Release 1 |  | Additional Data Item on IF-035 for a reason comment - what reasons would these be other than gone beyond the date? Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-31 | N/A | 2023-01-30 | St Clements | 2712 | Madison Layton | Software Provider |  | MHHS-BR-RS-027 "Registration Service must re-run validation, in line with the validation rules set out in the appropriate interface specification, for all Metering Service appointments that have been confirmed to re-process from the Prospective Appointment Queue, to ensure that the appointment is still valid" It is not clear if MPRS would send MSAppRejected or MSAppLapsed if the appointment fails validation after it's been queued? If this is not made clear in the deisgn then there is a risk that we build to use the wrong event code, or if the code should be MSAppRejected then risk that suppliers build a design where they can't process a MSAppRejected after receiving already an MSAppAccepted from MPRS (raised as DI 31) | Implemented |  | Interim Release 1 |  | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • Updated BRS003, requirement MHHS-BR-RS-032 and 66 to show that appointments will be lapsed (not rejected) • Remove Rejected from Step 225 of BP002/BPD002 Also on BP003 leading from step 215 should have the rejected removed. Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Corrections also to BPM002 & BPM003 Forward Migration and BPD002 Froward Migration | Data interface correction | MPAN Ownership |  | MHHSP-BP002-Change of Service - Metering service, BPD002,MHHSP-BRS003-Registration Service requirements MHHSP-DES138-Interface Catalogue, MHHSP-BP003, MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration), MHHS-DEL969-BPD002 (forward migration)
MHHS-DIN-32 | N/A | 2023-01-30 | St Clements | 2713 | Madison Layton | Software Provider |  | The interface catalogue lists setting a removal date as an action that can be used with event code meterUpdate on IF-005, however in the interface catalogue, the block B039 does not list meterUpdate as a event code that can utilise this block. Need greater clarity on whether meterUpdate and meterHistoryUpdate should apply meter installations and meter removals or not. (raised as DI 33) | Implemented |  | Interim Release 1 |  | The definition of a [MeterUpdate] event code is: Allows currently appointed Metering Service to amend the details associated with a currently installed meter. Therefore the appointed Metering Service must be able to remove the meter as part of an update, this is an omission from the design and a small update to IF-005 The design principle that IF-005 works on is that: • BAU transactions (Install/Exchange/Remove) that are in the Metering Services Period of ownership are covered by the Install/Exchange/Remove events • Changes to currently installed metering can be made by the Appointed Metering Service using the Meter Update event. Note this therefore includes, where required, removing the currently installed meter where it is prior to the current period of ownership. • Changes to metering history ( ie not the currently installed meter ) can be made by the Appointed Metering Service using the Meter History Update Proposed changes: Added MeterUpdate as Optional to B039 block in IF-005 and added validation rule to ensure MeterUpdate is not used to remove meters in current period of ownership picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP-DELS229-IF-005 Use Case Guide
MHHS-DIN-33 | T4-COM-1759 | 2023-01-30 | St Clements | 2719 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1759 on 15th Sept 2022: IF-005, REG1011 Install date must be > Creation date, should this REG1011 rule apply also to meter Exchange not just meter install SCS raised as a design blocker on 7th October 2022 Still no resolution, should this rule apply to meterHistoryUpdate at least as this allows for meter installations (raised as DI 34) | Implemented |  | Interim Release 1 |  | An exchange will not be a creation date, and the validation already in place ensures that future installation dates will all follow each other, which means this rule isn't required. ​This shouldn't be needed for exchanges, as its covered by REG1008 (install date >= remove date), as an exchange would replace an existing meter, which at first install would be validated against creation date. Moved REG1011 to cover all scenarios in IF005 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-34 | T4-COM-1774 | 2023-01-30 | St Clements | 2720 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1774 on 15th Sept 2022: IF-005, REG1011 "REG1009 - MAP ID [DI_055] is not valid for MAP Effective Date [DI-054] REG1011 - Install Date [DI-057] for MeterID [DI-056] is prior to MPAN Creation Date There are many meters in MPRS that pre-date the existence of the MAP and also MPRS install dates of 1980 etc. these will break a number of rules. should these be cleansed before MHHS start? If they are valid, then the rules need adjusting"l SCS raised as a design blocker on 7th October 2022 Still no resolution (raised as DI 35) | Closed |  |  |  | This could be a data cleanse requirement which is a consequential change/transition requirement, but for REG1009 - the MAP effective date should be the point at which the MAP took over the meter, and the exchange date should be after this (ie it should be after the date MHHS goes live). For Reg 1011 currently this is only valid on installs (and installs won't occur on legacy meters). If Reg 1011 is valid on exchanges, then the exchange date should also be after the MPAN creation date - if it isn't then the data should be cleansed. Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-35 | N/A | 2023-01-30 | St Clements | 2721 | Madison Layton | Software Provider |  | On the IF-005, should REG1028 (Install date cannot be null or blank) apply to meterinstall, meter exchange and meterupdate too? (raised as DI 36) | Implemented |  | Interim Release 1 |  | Requires amendment to interface validation - look at alternative validation Agree the rule should also apply for those events. Note we believe validation would fail for another reason. Eg REG1019 Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-36 | N/A | 2023-01-30 | St Clements | 2722 | Madison Layton | Software Provider |  | In the summary of error codes box at the bottom of IF-005 tab the rejection reasons need re-aligning to the main block, e.g. REG1001 should read RMP stats must be Created or Operational, not just Operational As a general note across all interfaces, the rejection codes are referenced in numerous places and the respective descriptions are in many places not consistent for the same rejection code (raised as DI 37) | Initial Assessment/Updating | 2023-04-27 | Interim Release 3 | 2023-07-12 | Request flexibility for SCS in error messages provided | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-37 | N/A | 2023-01-30 | St Clements | 2723 | Madison Layton | Software Provider |  | REG1015 (cannot be removed meter) is listed for meterHistoryUpdate in interface catalogue for IF-005. This should actually apply to meterUpdate not meterHistoryUpdate, REG1018 (cannot be installed meter) applies to metering history update (raised as DI 38) | Implemented |  | Interim Release 1 |  | Change accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-38 | N/A | 2023-01-30 | St Clements | 2724 | Madison Layton | Software Provider |  | In the interface catalogue, the IHD block B030 for IF-005 should also be optional for meterUpdate according to the IF-005 guide Section 16 Development Notes "The IHD segment, if provided as part of [MeterUpdate], relating to any currently installed meter should replace/update the IHD details currently held at the MPAN to which that Meter is associated." (raised as DI 39) | Implemented |  | Interim Release 1 |  | Small change to schema operation IHD information may be updated as part of the [MeterUpdate] event. The change is to add [MeterUpdate] event to block B030, so it now reads "B030 - MPAN IHD Information (Optional & may only be used with [MeterInstall],[MeterExchange],[MeterUpdate]) NB this also standardises the use of commas between event codes, rather than using the & symbol. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-39 | N/A | 2023-01-30 | St Clements | 2725 | Madison Layton | Software Provider |  | In interface catalogue for IF-005, there needs to be a rule that if event code MeterInstall is used, then modified meter ID cannot be populated (raised as DI 40) | Implemented |  | Interim Release 1 |  | Update agreed | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-40 |  | 2023-02-01 | SI Design |  |  |  |  | Not used - raised as duplicate in error | Closed
MHHS-DIN-41 | N/A | 2023-01-30 | St Clements | 2730 | Madison Layton | Software Provider |  | In interface catalogue IF-005: The REG1003 reads Metering Service [S0.SenderID] holds valid previous appointment then Meter Install Date [DI-57] should be < [REG.App End Date] + 10 The way it's curently written suggests MPRS should accept an IF-005 from the previous appoint, even if their ETD was greater than 10 days ago, provided the install date was less than their ETD + 10. E.g the previous MS could send IF-005 two years later with Install date of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then REG1002/REG1019 should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? (Raised as DI 41) | Implemented |  | Interim Release 1 |  | Having looked through IF-005 Dates should be within the appointment date, and current deign does give the ability to go outside this Change the validation rule for REG1003 on events [MeterExchange], [MeterInstall] and [MeterRemoval] to "If Metering Service [S0.SenderID] holds valid previous appointment then [system date] < [REG.App End Date] + 10" Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. Rule amended after review by SCS, to remove second "if" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-42 | N/A | 2023-01-30 | St Clements | 2784 | Madison Layton | Software Provider |  | In interface catalogue IF-005: Meter Update should apply validation REG1027 (current MS or prospective MS) not REG1012 (current MS only) to allow the prospective queued MS to update the Meter Type on a SEG change and therfore complete the market segment change and appointment. MHHS-BR-RS-132 . If the SEG prospective appointment was not allowed to update on meterUpdate event code then they would not be able to update the meter type to completed change of market segment, and would not meet the conditions needed to then be appointed in MPRS, their appointment would then lapse and market segment would remain invalid. (Raised as DI 42) | Closed |  |  |  | We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error... | No Change |  |  | None
MHHS-DIN-43 | N/A | 2023-01-30 | St Clements | 2732 | Madison Layton | Software Provider |  | In Interface Catalogue, on If-005, REG1002 and REG1019 are duplicates (install/removal dates should be within MS period of ownership). We can only use one of the rejection codes and descriptions, programme should choose which one to keep and remove the other. (Raised as DI 43) | Closed |  |  |  | These are testing slightly different things. The first test (REG1002) is checking that the Metering Service is an eligible party to send the request ie currently appointed OR was at the time of the install (to cover for previous Metering Services updating in the 10 day window). The second (REG1019) is checking that the Install Date is in the Metering Services period of ownership. So you could have that the Metering Service is currently appointed, but that they weren't at the install date. Eg Today is 2nd Feb, Meter installed on 27th Jan, Sending MS was appointed on 1st Feb REG1002 would pass as they are eligible as the currently appointed MS REG1019 would fail as they are not appointed at the time of the install Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-44 | N/A | 2023-01-30 | St Clements | 2733 | Madison Layton | Software Provider |  | Should the new rule for meter update in IF-005 also apply to meter history update? If no MAP entries provided, and revised Meter Install / Remove Dates result in no valid MAM History then reject with REGE1014 – MAP Eff From Sequence Error (Raised as DI 44) | Implemented |  | Interim Release 1 |  | Added REG1014 ( MAP History ) to IF-005 MeterHistoryUpdate event | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-45 | N/A | 2023-01-30 | St Clements | 2736 | Madison Layton | Software Provider |  | New rule for IF-005 Meter Update REG1017 could be misinterpreted as it currently reads incorrectly - need brackets to correct to how the AND and AND/OR conditions are to be applied If [DI-60] is not null AND Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null) Should read If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null)) (Raised as DI 45) | Implemented |  | Interim Release 1 |  | Clarification of existing design rule Change the validation rule for REG1017 to: "If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null))" picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-46 | N/A | 2023-01-30 | St Clements | 2737 | Madison Layton | Software Provider |  | on IF-005 for Meter Exchange and meter install the rule for REG1027 has been changed, but I'm not sure the wording implements the rule intended exactly? Currently it reads as The MS must be the currently appoint MS AND the install date must be > MS EFD AND the MS must not have proposed MS app with SEG scenario in the queue. If not then reject with REG1027 - Metering Service is not currently appointed and does not hold a Prospective SEG Appointment SHould the rule actually read The MS must be the current MS OR the MS must have a proposed MS App in the queue with SEG scenario And then the other part of the rule about install date > MS should be a separate rule (with REG1019 error code). (Raised as DI 46) | Implemented |  | Interim Release 1 |  | Sent to Mike F for validation - SI believe wording in current documentation is correct. Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. I would suggest the wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. DIN-46 – On review we agree, the date test should always be true if REG1019 is satisfied ( with minor clarification update ), so validation rules should be updated as below: Proposed changes: REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-47 | N/A | 2023-01-30 | St Clements | 2738 | Madison Layton | Software Provider |  | REG1001 on IF-005 does not allow for meters to be removed after a disconnection. Instead should restrict for allow other event codes but allow Status Terminated for MeterRemoval. DES204 CCR-0556 Linked to DI-13 | Implemented |  | Interim Release 1 |  | Rule update required picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-48 | N/A | 2023-01-30 | St Clements | 2739 | Madison Layton | Software Provider |  | Unhappy path scenario:- What happens if, for whatever reason, CSS fails to apply CoS to all the related secondary MPANs MPRS receives IF-031 on primary RMP to change agent, MPRS applies this to all seocndary MPANs too But if the CoS was not received from CSS for secondary MPANs that the secondary MPANs would still currently be held for the wrong supplier Would this cause any issues downstream? (Raised as DI 48) | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | CSS Defects issue. Agreed that Risk would be raised and all CSS related issued assesed at a later date | Other | MPAN Ownership | Related MPANs
MHHS-DIN-49 | N/A | 2023-01-30 | St Clements | 2740 | Madison Layton | Software Provider |  | Unhappy path scenario:- If MPRS sends a IF-033 but never receives back a IF-034 then the rest of the process will not continue. The Supplier will never receive the IF-035 they are waiting for and the SP would never get appointed by MPRS. Is there a process in place to detect/resolve this scenario? (Raised as DI 49) | Closed |  |  |  | There is a requirement for the Supplier to monitor for any delayed responses and request an update if not received in expected timescales. Reviewed with SCS and agreed ticket can be closed | No Change |  |  | None
MHHS-DIN-50 | N/A | 2023-01-30 | St Clements | 2741 | Madison Layton | Software Provider |  | We need clear rules to define what a valid Consent granularity looks like. Current rules don’t mention any validation around EDI. (Raised as DI 50) | Implemented |  | Interim Release 1 |  | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-51 | DI-51 | 2023-01-30 | St Clements | 2747 | Madison Layton | Software Provider |  | Emailed about Refresh functionality on 14th October From: Daniel Tadecicco We have had some feedback from DNOs asking about how systems will recover from System Misalignment because of data errors or significant downtime? We have the D0204 (Supplier) and D0209 (Data Aggregator) Refresh functions today which are not being replaced with a DIP message equivalent. I am aware of the DIP Replay function, but this wouldn’t be of any help if there were data errors, as the DIP would just be replaying the incorrect data. The Source system would need to re-send the corrected data in an agreed format. I know there is a design principle to move away from bulk loads and refreshes of data, Faster Switching took a similar approach. However today, CSS leans heavily on the MPRS Refresh function to get itself back inline and there are REC CP’s being raised to add a Refresh function to CSS for all parties (first CP being R0067). DNO’s are keen to understand the MHHS Programme’s position on this, and if Refresh functionality should be built into MPRS for MHHS. SCENARIO PROVIDED: The most common scenario a refresh would be needed for is when making manual amendments (DI 56), this is needed to reflect the changes that were made back to participants (e.g Supplier, MS, DS, EES etc). Another scenario is if there’s invalid data in MPRS and a message containing this data is therefore rejected by an end participant, the message can’t just be replayed as it’ll continue to be rejected. Would need to correct the invalid data, and then the DNO/iDNO would need to manually trigger a refresh to be generated by MPRS to send the current MPAN information to that end participant. Example in context of MHHS Rule REG1022 is not removed from Interface Catalogue (DI-2) Cleansing to remove IHD Status on MPANs of non-smart segment IHD non smart MPANs aren’t fully cleansed pre go live Switch generated on an uncleansed MPAN IF-002 sent to Supplier with IHD Install status where market segment is not smart Supplier rejects PUB-002 as IHD install status populated IHD status corrected Supplier still can’t load the original IF-002 message as this contains the invalid data, so a refresh would be needed to communicate the MPAN information to Supplier It’s probably unlikely in this example the supplier applies validation on IHD status but it’s just to give an idea of the type of scenario that can happen. As Dan said in his original message, refreshes are currently heavily relied upon since faster switching go live. | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Refresh Functionality was rejected by the Working Groups so not in current design. Scenarios required. Go back to St Clements for specific scenarios | Other | Supporting Docs | Refresh Process?
MHHS-DIN-52 | DI-52 | 2023-01-30 | St Clements | 2748 | Madison Layton | Software Provider |  | For IF-005, REG-1006 and REG1013, would it make sense to include the installation date of the MPAN already in the system in the rejection description too to help MS with triage? | Closed | 2023-04-27 | Interim Release 1 |  | DIN closed as instructed by St Clements. Old comments: Discussed with SCS potential for them to have flexibility on error messages. Industry agreement required. Participant Discussion Required | No Change
MHHS-DIN-53 | N/A | 2023-01-30 | St Clements | 2749 | Madison Layton | Software Provider |  | Requirement on LDSO requirements spreadsheet: MHHS-BR-LD-035 LDSO Maintain DUoS Tariff ID LDSO must set Duos Tariff ID on MPAN creation and maintain DUoS Tariff ID's in line with their Charging Method Statement. This should include updating the Duos Tariff ID, as required, following any updates to Domestic Premise Indicator, Connection Type and Energy Direction Note for MHHS, LLFC ID is being renamed as DUoS Tariff ID to make it clearer what this data item is used for. "BP010B Change of registration data" 250 However missing the respective requirement for Registration Services in the Registration Services Requirements spreadsheet | Closed |  |  |  | Looked through the Registration Services Requirements spreadsheet v4.6 and it looks like DUoS Tariff ID is there - MHHS-BR-RS-091.1, MHHS-BR-RS-121 and MHHS-BR-RS-122 | No Change |  |  | None
MHHS-DIN-54 | N/A | 2023-01-30 | St Clements | 2750 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1699 on 15th Sept 2022: On the IF-031 and IF-035 there are a number of "Proposed" Data items. Should MPRS load these and updated the stored data items. Or are these data items only for passing through to Supplier and Service? SCS raised as a design blocker on 7th October 2022 We have some clarity verbally on this but nothing has been formally documented in the design artefacts. This needs to be reflected somewhere in the requirements. | Implemented |  | Interim Release 1 |  | Added "Appoinments - Data" section in REG Notes to highlight what data becomes effective with the appointment. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-55 | T4-COM-1738 | 2023-01-30 | St Clements | 2751 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1738 on 15th Sept 2022: the DB02 flow updates multiple data items on the IF-018 in one event. Can multiple EventCode be included in one IF-018 or will MPRS need to generate an individual IF-018 for each EventCode? SCS received a blank response and raised as a design blocker on 7th October 2022 | Closed |  |  |  | Original response was that clarification was to be provided on 24th Oct - is this available? Which document? One at a time | No Change |  |  | None
MHHS-DIN-56 | T4-COM-1742 | 2023-01-30 | St Clements | 2752 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1742 on 15th Sept 2022: BSCP604 currently allows LDSO and Suppliers to request manual corrections to Data Items held in MPRS. Will this type of Manually Correction be allowed in MHHS, if yes then this should be added to this business process to capture manual amendments and how these changes are reflected back to DIP users (IF-018 & IF-026, or a new Refresh Message?) SCS received a blank response and raised as a design blocker on 7th October 2022 Another exaple of this: If the MS/DS history is incorrect and cannot be amended via BAU, would the DNO be able to correct this via an exceptional error handling process? | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Original response was: This has been raised as potential consequential change utilising SDEP Nothing in design, would want updates via a flow to maintain sychronisation. Requires a change to implement, request specific data items requested - needs to be related to settlement, needs to be updated via appropriate flow. | Requirement correction | MPAN Ownership | CSS Defects | MHHS-BPD005 Data Processing, MHHS-BRS005 LDSO overview
MHHS-DIN-57 | T4-COM-1748 | 2023-01-30 | St Clements | 2756 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1748 on 15th Sept 2022: "Additional information field DI-120 is String200, where the existing DB03 allows a free text field of 2000 characters" SCS raised as a design blocker on 7th October 2022 This was corrected but then in v4.5 artefacts released there was a change back for DI-120 addition infromation field from string 2000 to string 200 in the interface catalogue data catalogue tab reintroducing the issue. For disconnection additional notes MPRS database holds 2000 characters so this field will need to be string 2000 in the IF interfaces (Raised as DI 57) | Closed |  |  |  | Change to the data catalogue included in the 4.7 baseline | No Change |  |  | None
MHHS-DIN-58 | T4-COM-1789 | 2023-01-30 | St Clements | 2757 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1789 on 15th Sept 2022: "Valid combinations of data in ISD are critical to the MPRS validation development, we must have these defined and agreed before we can start development" SCS raised as a design blocker on 7th October 2022 | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Who is defining valid combinations of data in the ISD? Parties need to define their own data. Currently not part of a plan. | Requirement correction | Supporting Docs | ISD | MHHSP-EM021 ISD Entity Map
MHHS-DIN-59 | T4-COM-1707 | 2023-01-30 | St Clements | 2758 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1707 on 15th Sept 2022: "The Smart DS for Export and Secondary MPANs can be different to the Import/Primary DS as the Customer can choose their own DS for Export and Primary (Smart only)" The IF-031 validation rules have been amended but they are still not corrrectly reflecting the rule. The heading above both rules REG1038 and REG1039 reads: "If event type = [MSApp] OR event type [DSApp] & MPAN Segment is not 'Smart'" This heading should ONLY apply to REG1038 for linked MPANs and should not apply to REG1039 concerning related MPANs It should also have brackets to clarify the logic otherwise it could be misinterpreted e.g. "If event type = [MSApp] OR (event type [DSApp] & MPAN Segment is not 'Smart')" | Implemented |  | Interim Release 1 |  | This seems a valid issue. REG 1039 on linked meters should be allowed for trad meters (eg economy 7) Proposed Change: The logic issue here is that REG1039 caters for related meters, which are applicable to trad as well as smart meters. Remove REG1039 from this validation Change the validation to: "If (event type = [MSApp] OR event type [DSApp]) & MPAN Segment is not 'Smart'" Updated heading above REG1038 and added heading above REG1039 to clarify the validation rule in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-60 | T4-COM-1708 | 2023-01-30 | St Clements | 2759 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1708 on 15th Sept 2022: "The Service Appointment Date must be equal to the SSD or there will be a period with no Service" And T4-COM-1776 also on 15th September 2022 "REG1032 - Metering Service Eff From Date [DI-830] is not contiguous - Appointment must be from [Max[Reg.MPAN_SSD] ,[Reg.ExistingMSAppFrmDate]] for a COS, it can only equal the SSD otherwise there will be a gap" This has been applied incorrectly. In IF031 rules REG1032 now reads that the MS/DS prop EFD must be = Max(SSD, existing MS/DS EFD + 1) This would restrict the MS/DS to setting the new EFD to either SSD or the day after the last MS/DS appointment, and all other dates would be rejected. It should read >= not just =. All four refrences to REG1032 in the validation rules for IF-031 references the +1 day after EFD, but the rejection description in the right hand columns for 'scneario not SEG or CoS' section does not reference this + 1. This should be corrected to be consistent with the other rules. (Raised as DI 60) | Implemented |  | Interim Release 1 |  | Original response to 1708: New rules added to cover all scenarios Original response to 1776: Change to be incorporated into design artefact Updated REG 1032 validation in IF-031, original single rule, split into 2 separate rules picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-61 | T4-COM-1445 | 2023-01-30 | St Clements | 2760 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1445 on 15th Sept 2022: "There is no mechanism to update the Profile Class. We would assume that this would be updated by the Supplier (with business rules restricting when this should be set) and confirmed on the IF-026. Please can you confirm if this is the intention or if it will be updated through another route. If so, the EES would need to know which PUB would confirm the data item had been updated. " Whilst this is now included in the design the validation rules from D0205 have not been carried over, e.g. PC/SSC need to be a valid combination. ISD will need to contain the valid PC/SSC Combinations (previously MDD Entity 11) and the validation rules in the interface catalogue will need to reference this validation against the ISD valid combinations. (Raised as DI 61) | Implemented |  | Interim Release 1 |  | See also DIN-58, need to find out who is defining ISD validation Updated Interface notes in IF-025 to confirm that there is no Profile Class/ SSC combination checks | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-62 | DI-062 | 2023-01-30 | St Clements | 2761 | Madison Layton | Software Provider |  | In the business process diagram for Registration Updates MHHSP-BP010-Change of Registation Data - v4.5, the MPL update section, the C0300 has been changed to C0400 which is incorrect, C0400 is for MAP updates. Address updates are actually sent in the C0600. (Raised as DI 62) Change raised 30 March:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly. | Implemented |  | Interim Release 1 |  | Also in the BPD. MHHS-BR-RS-114 also confirms this should be C0300, this appears to be a straightforward typo. Amend label between Step 20 and Step 30 on BP010A to CSS0300, and update the corresponding BPD description on step 30 Update required:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly in BP010A, BPD010 and in MHHS-BR-RS-114. | Process model correction | Metering Changes | MPAN Updates | MHHSP-BP010-Change of Registration Data MHHSP-BPD010 MHHSP-BRS003
MHHS-DIN-63 | DI-063 | 2023-01-30 | St Clements | 2792 | Madison Layton | Software Provider |  | In the business process diag for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 (Raised as DI 63) | Closed |  |  |  | SCS have now confirmed that C0700 is the correct reference - no need to change documentation - agreed to close | No Change | MPAN Ownership | Disconnection | MHHSP-BP007-Disconnection MHHSP-BPD007
MHHS-DIN-64 | N/A | 2023-01-30 | St Clements | 2793 | Madison Layton | Software Provider |  | In business process diag for change of data service MHHSP-BP003-Change of Service- Data Service-v4.5 and MHHSP-BP002-Change of Service- Metering Service v3.5, this still makes reference to D0386 in the purple note boxes. This should now have changed to IF-019 (Raised as DI 64) | Implemented |  | Interim Release 1 |  | Update notes on BP002 and BP003 from D0386 to IF-019, and for BPM002 & BPM003 (forward migration) | Process model correction | MPAN Ownership | Change of DS | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-65 | N/A | 2023-01-30 | St Clements | 2794 | Madison Layton | Software Provider |  | The business process diagram for change to connection type/market segment has been amended to name only DB01, connection type is set on DB01 but it can then be changed on DB02 (Raised as DI 65) | Implemented |  | Interim Release 1 |  | Update label between step 220 and 225 from "DB-001" to "DB02" | Process model correction | Metering Changes | Market Segement | MHHSP-BP011-Change of Connection Type or Mkt Segment
MHHS-DIN-66 | N/A | 2023-01-30 | St Clements | 2795 | Madison Layton | Software Provider |  | In interface catalogue, on IF-031, shouldn't rule REG1036 (MDR app EFD must be after DS app EFD), be applicable to all scenarios including SEG? Currently under section for if not SEG (Raised as DI 66) | Implemented |  | Interim Release 1 |  | Updated validation rule for REG1036 and made applicable to all scenario's in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-67 | N/A | 2023-01-30 | St Clements | 2796 | Madison Layton | Software Provider |  | Currently no rule on IF-031 that the SP appointment has to be within the prospective suppliers registration period - just that it can't be past dated. This rule will need to be added. (Raised as DI 67) | Closed |  |  |  | Reviewed with SCS and agreed that this validation is covered by existing rules. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-68 | N/A | 2023-01-30 | St Clements | 2797 | Madison Layton | Software Provider |  | If-031 business rule missing If the Scenario is USP, the consent granularity must be the same as the existing consent granularity held within MPRS (Updates should be through IF-025 not through IF-031) (Raised as DI 68) | Implemented |  | Interim Release 1 |  | picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Updated Interface notes in IF-031 to clarify that Registration Service will ignore any differences in Domestic Premise Indicator/ Consent Granularity sent on IF-031 (USP scenario) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-69 | N/A | 2023-02-02 | ESG Global | 2653 | Luke Speakes | Software Provider |  | PUB-033 - Block 029 is conditionally mandatory for DCC Commissioned Meters, but includes DI-025 DCC Service Flag with valid values of A-Active, I-Installed Not Commissioned, N - Non Active. The title of the block, which should define whether it is mandatory or not, is not appropriate if a DCC meter has been installed and not commissioned, or is inactive. Propose following SI and SRO design discussion that title of block 029 is revised to conditionally mandatory for 'DCC Smart Meters' | Implemented |  | Interim Release 1 |  | Concludes this can be resolved by a minor wording change to the block title | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-70 | N/A | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory |  | Elexon is required to maintain a valid list of Meter Data Retrievers in Industry Standing Data, to allow RegService to validate that suitably qualified (DCC and SEC) MDRs are being appointed. Detail is validation of DI-839 in the IF-031 - this is not a validation rule in v4.7 of the interface catalogue. Elexon can infer valid/qualified MDRs from the SECAS list of SEC parties and DCC users, but the public list does not include detail of the role they are qualified in. Discussions with DCC and SECAS are continuing - the validation rule should be added to the catalogue | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | The update to the interface catalogue is minor, but the implications for ISD are significant - how will it source and maintain the data relating to qualified MDRs - a role that will not be qualified under the BSC (it has been assumed that SEC/DCC accession provides sufficient assurance). Frequency of update is expected to be intermittent and infrequent, but should cover new additions and periodic removal of redundant MDRs Need to clarify where this will be captured and reported in ISD 1/3 - SCS (ticket #3034) We need valid list of MDRs in ISD for MPRS also. ISD is the only source of MPID Data for systems to load. SEC do not provide MPRS with Market Participant Domain Data. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue - probable updates to relevant BP/BPD/BRS
MHHS-DIN-71 | N/A | 2023-01-30 | St Clements | 2839 | Madison Layton | Software Provider |  | When would event code [MSDeAppUpdate] and [DSDeAppUpdate] be used for on an IF-037? (Raised as DI 69) | Closed |  |  |  | Reviewed with SCS and it is used to notify the incoming Service Providers when de-appointing and not origanally known. In case of Linked/Related MPANs individual MPANs move through the process. RS need to apply the logic for sending the updated IF-037 to all MPANs. Agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-72 | N/A | 2023-01-30 | St Clements | 2840 | Madison Layton | Software Provider |  | Block B018 on IF-034 and IF-035 should not be mandatory - it will only be provided for smart meters. This needs to be set to mandatory for SDS-MDRUpdate only, optional for DSAppSPResponse (Raised as DI 70) | Implemented |  | Interim Release 1 |  | Updated B018 block to be optional for non Smart on IF-034 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-73 | N/A | 2023-01-30 | St Clements | 2841 | Madison Layton | Software Provider |  | IF-026/IF-025, added new event code [SSCandProfileClass], but still kept in original [SSC] and [ProfileClass] event codes, should the original two have been removed? Particularly as the B032 group says it's madatory where event code is [SSCandProfileClass] and does not refer to [SSC] or [ProfileClass] individual event codes (Raised as DI 71) | Implemented |  | Interim Release 1 |  | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-74 | N/A | 2023-01-30 | St Clements | 2842 | Madison Layton | Software Provider |  | A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a new MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60 (Raised as DI 72) | Implemented |  | Interim Release 1 |  | This appears to be the reciprical change to MHHS-DIN-60 for the response interface Update description to "Check if MDR Eff Date = SSD OR on or after existing MDR Eff From + 1" Update rule to "If [DI-841] <>SSD OR <MDR Eff Date + 1" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-75 | N/A | 2023-01-30 | St Clements | 2843 | Madison Layton | Software Provider |  | On IF-035, overidden the description for Data Item 836 incorrectly with the description for Data Item 838 (Raised as DI 73) | Implemented |  | Interim Release 1 |  | Update the definition field based on the description in the data catalogue for DI-836 on IF-035 (Date From which Supplier would like Nominated MDR to take effect) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-76 | N/A | 2023-01-30 | St Clements | 2844 | Madison Layton | Software Provider |  | Data catalogue - changed the estimation reason code authoritative source to Registration Service, this data item is not received by, sent by or held by registration services and so the authoritative sourse cannot be Registration Service (Raised as DI 74) | Implemented |  | Interim Release 1 |  | The authoriative source has changed between v4.0 (from Data Service) to 4.7 (Registration Service) - have asked why the change was made, and what the authoritative source should actually be. Source updated to SDS/MDS | Data interface correction | Meter to Bank | Estimation | MHHSP-DES138-Interface Catalogue
MHHS-DIN-77 | N/A | 2023-01-30 | St Clements | 2845 | Madison Layton | Software Provider |  | Data catalogue - Added issue 99 items (CT Ratio, Phases etc) DI-170 - DI-180. Was agreed in work off meeting these items are not within the scope of MHHS, to introduce these would require a CR (Raised as DI 75) | Implemented |  | Interim Release 1 |  | these data items don't appear to be used in any interfaces so this could be a relatively simple change to remove 11 items from the data catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-78 | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E0404 requirement is blank - row needs to be deleted | Closed |  |  |  | This update was already incorporated into version 5.0 closing it here | No Change | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-79 | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E21114 typo - should be VAS Output Retention | Implemented |  | Interim Release 1 |  | change as per description | Technical corrrection | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-80 | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHSP-DES138-Interface Catalogue v4.6 - DI-846 Issuing Data Service EZ Name should be scored through in IF/ PUB21 definition | Closed |  |  |  | Completed in V5.0, part can review change as part of Interim Release 2 | No Change | Meter to Bank | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-81 | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier | Correction of step in BP020 | MHHSP - BP020 - Volume Allocation Service (ECS) v4.6 - Step 75 to Step 80 references report “REP-00” - needs correcting | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | BP020 step 75 to step 80 process flow REP list correction BPD020 step 75 & step 80 detail list of REP's correction | Process Model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions
MHHS-DIN-82 | N/A | 2023-02-09 | SI Design | 2716 | Rob Short | SI Design | Missing listed number of reports in BPD002 | Related to DIN-81 - BPD002 lists number of reports at step 75, BP002 does not reflect this list, missing PO275, PO214 and PO213 | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | This relates to BP020 (not BP002), similar to DIN81, reconcile REP list correction on BP020 at step 75 and 80 and reconcile with BPD020 list of REPs | Process model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions
MHHS-DIN-83 | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | BP011 missing PUB-044 flow | A discrepancy with the Interface Catalogue - IF_LIST states MHHSP-IF-044 is sent to Central Settlements, DS, MS, Supplier, LDSO. IF-044 tab states it is sent to Supplier, MDS, LDSO In BP011 the PUB-044 is not sent to DS only Supplier, Settlements and EES | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Add Manage change of segement in LDSO lane on business process BP011C with a PUB-044 flow from step 570 Add new step to BPD011 Interface catalogue is already updated | Process Model correction | Metering Changes | Interface Catalogue | MHHSP-BP011 Change of ConType andor Mkt Segment MHHSP-BPD011 MHHSP-DES138-Interface Catalogue
MHHS-DIN-84 | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | DES-138 IF List Tab Consistancy | IF_LIST states MHHSP-IF-020 is sent to Supplier onlyIF-020 states it is sent to Supplier, Data Service, Metering Service, LDSOIn BP010, the PUB-020 is sent to Central Settlements, CSS, EES, Supplier, Data Service, Metering Service, LDSO.This one looks like its just the Interface Catalogue that needs updating. IF-020 Updated to refect new agreed Routing | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated parties receiving PUB-020 in the IF_LIST, updated PUB-020 routing to include MDS for Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-85 |  | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory |  | Elexon see DIP qualification for new users being part of market entry post-programme, but want to understand how MHHSP will operate qualification during the programme. This is likely to cover the majority of participants. Discussions with SRO colleagues indicate they are assuming this is a process for the Enduring Service Operator to define. Challenge applies to non-BSC DIP participants (e.g. adaptor providers), and considerations under Issue Group 101. SI design has spoken to at least 4 participants who are operating in this space and seeking to understand how they can engage with SIT and other programme activities as a DIP connection provider (E2E Architecture - 3.3.2) | Closed |  |  |  | To be handled as part of the Placing Reliance document | No Change | Qualification | Qualification | New Process - DIP Qualification for New Users
MHHS-DIN-86 |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Invalid Market Segment BP011C requires SMRS to notify the Supplier of an invalid market segment. RegService requirement RS0124 states that SMRS must derive a value for Market Segment based on Connection Type and Meter Type following a Change of Metering, Change of Connection Type (Change of Unmetered Indicator) or Change of Related MPAN relationships. Given that SMRS determines segment as above, when would an invalid market segment occur, giving rise to the processes from step 560 in BP011C? Further, upon receipt of a PUB-045 Market Segment Invalid Advisory Notification, what are the next steps for a Supplier to address the issue? There are no provisions in the IF-025 for Suppliers to update Market Segment. | Closed |  |  | 2023-07-12 | Part of ongoing discussions with Code Drafting team 20/4//23 Code Drafting believe an update needs to be made to the design to update Market Segment via IF-25. This could occur when a Supplier is trying to arrange a change of segment but one of the activities has not completed on time eg the new metering has not been notified. When Registration Service tries to evaluate the segment it may not be compatible. Notification would then go to Supplier to prompt them to chase the required update, in this example chasing the Metering Service to provide the new metering details. Another example is if the LDSO has not notified a change of connection type. The Supplier may also need to send a further SEG appointment if the original has lapsed. | No Change | Metering Changes | Change of Connection Type and/or Market Segment | MHHSP-BP011, MHHSP-BPD011
MHHS-DIN-87 |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Energisation Process Clarification BP009 states that change of energisation status at the same time as meter works means that BP008 will be followed - what is the process when a meter removal and de-energisation are carried out in the same job? Are both D0139 (de-energise) and D0142 (remove meter) and relevant DIP interfaces required. At the moment MEMs only have to send flows relating to meter removal | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Part of ongoing discussions with Code Drafting team Under MHHS design this is two separate events that would require both IF005 and IF007 being sent by the Metering Service ( even if carried out as one job ) Agreed at meeting with SJ on Mo 27th Mar that we would add new Purple Boxes to BP009 and BO008 to make it clear that Remove/DeEn could still be requested and carried out but MS would need to send two interfaces. ALso that DeEn did not need to be notified if meter works completed within same day (ie same rules as today) | Process model correction | Metering Changes | Change of Metering | MHHSP-BP009, MHHSP-BPD009
MHHS-DIN-88 |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Update to Incumbent MS provider for Lapsed Appointments Currently BP002 only addresses the positive confirmation of de-appointment from RegService (PUB-037 - step 140/231), but if there is no secured active, there is no subsequent notification to the incumbent. The prospective MS receives a PUB-035 at step 225. How should the incumbent MS determine when the de-appointment has lapsed? | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Part of ongoing discussions with Code Drafting team why would the incumbant share the MTD via the IF-035 as early sight. IF-37 is the deappoint they code need to reflect . The Metering Service is appointed until they get de-appointed using a PUB-037. They are only receiving the PUB-035 as notification of who to send MTDs to, it is not intended as a notification of de-appointment. SC= Incumbent Metering Service is a term used to refer to the MS appointed at the point another new SP Appointment is accepted (MS or DS), it shall be the Incumbent Metering Service's responsibility to share MTDs (ADV/Trad) to the incoming party. No change recommend CLOSE |  | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Metering Service MHHSP-BPD002
MHHS-DIN-89 |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Customer Details on De-Appointment The MHHS design currently allows for customer data to be deleted or obfuscated by MS on de-appointment. Has obfuscation been confirmed as acceptable under GDPR? | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | Part of ongoing discussions with Code Drafting team PP 14/2- PP to check with Ian / Smitha |  | All Areas
MHHS-DIN-90 |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | MS Appointment for Associated Export Metering Points How will an initial MEM be appointed for a new export MPAN, created post MHHS go live? | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | Part of ongoing discussions with Code Drafting team to have a look at the process that Mpans are in the correct group The daily process monitoring (BP011C) would pick up any linked Export MPANs and ensure that the same Metering Service is appointed as the Import MPAN. If the Export MPAN is not linked, then the BAU appointment process can be followed. |  | Metering Changes | Change of Connection Type / Market Segment | MHHSP-BP011, MHHSP-BPD011
MHHS-DIN-91 | N/A | 2023-02-10 | AWS | 2858 | Duncan Parsons | Software Provider |  | Document MHHS-E2E001 section 3.6 Actor Workflows Summary - Typo in the MSA Outbound. States IF-04, this should be IF-041 | Implemented |  | Interim Release 1 |  | Reference Corrected | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-92 |  | 2023-02-14 | RECCo | 2903, 2805, 2911 | Sarah Jones | Regulatory |  | Customer Direct Contract Flag (D053) Multiple tickets - RECCo, ESG and National Grid - all highlighting the same problem. The 4.7 artefacts do not consistently reflect the agreed position that the Customer Direct Contract flag can only be set by the incumbent Metering Service provider. The validation rules on the IF-038 should be updated The requirements for MS (013) and DS (34) in the respective BRS artefacts should be aligned | Implemented |  | Interim Release 1 |  | Added validation rule REG1075 to IF-038 in the interface catalogue Updated requirements in MS-013 and DS-034 in BRS to reflect the agreed position for D053 1/3 - ticket #3035 - SCS supportive of this change, need more detail. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue, BRS001, BRS002
MHHS-DIN-93 | N/A | 2023-02-14 | Power Data Associates |  | Tom | Data Service Provider | Work off Plan D-034D updates for exceptions to Unmetered Supplies | Work off Plan D-034D updates for exceptions to Unmetered Supplies | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | 1. Section 2.3 of MHHSP-METH004-UMSDS- EM Functions will be updated to make explicit that the following data items are not required by the UMSDS and as such will be ignored. • Consent Granularity (T4-COM-1857) • Domestic/Non-domestic Indicator (T4-COM-1830/1850) • Distributer Id (T4-COM-1826/1842/1845/1858/1859/1864/1865/1871/1875) • DUoS (T4-COM-1856) • LLF Data (T4-COM-1856) • Domestic Premise Indicator (T4-COM-1830/1850) • Metered Indicator- (D-045) 2. MHHSP-METH001- SDS Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 3. MHHSP-METH002- ADS- Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 4. MHHSP-METH009- UMSO Method Statement should be updated to make explicit that the following data items are not required by the UMSO and should be ignored (list to be reviewed and validated). • Consent Granularity • Domestic/Non-domestic Indicator • Distributor Id • DUoS • LLF Data • Domestic Premise Indicator • Metered Indicator | Method statement correction | Supporting Docs |  | MHHSP-METH004-UMSDS MHHSP-METH001- SDS MHHSP-METH002- ADS MHHSP-METH009 - UMSO
MHHS-DIN-94 |  | 2023-02-16 | ESG | 2777 | Patricia | Software Provider | IF-009 Process Map | The IF_009 has 2 event codes: [MPANDisconnection] & [CSSDeRegistration]. [CSSDeRegistration] is listed as having Supplier as Secondary routing however on BP007 there is only reference to the supplier receiving the [MPANDisconnection] flavour of the flow. Please can you clarify which artefact is accurate. MHHSP – BPD009 step 145 states Where the Registration Service has rejected the metering update the DIP will publish the rejection to metering services. Supplier have the option to subscribe to this also. Your response was:- Our reading of this is that regservice will reject the PUB-006 back to sender if the IF-005 fails those rules. So just back to sender, not always meter service or supplier Therefore, does the BPD009 step 145 need to be updated to reflect that as the IF005 can only be generated by Metering Service Smart (MSS) & Metering Service Advanced (MSA) not the Supplier | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Question 1. Supplier will receive both events as outlined in BP007 (See DIN 294) Question 2. BPD009 step 145 updated to show that Supplier cannot choose to receive rejections | Process Model correction | Metering Changes | Disconnection / Change of Metering | MHHSP-BP007-Disconnection MHHSP-BP009 – Change of Metering (Install / Remove / Exchange) MHHSP-DES138-Interface Catalogue
MHHS-DIN-95 |  | 2023-02-20 | SI Design | NA | Simon Harrison | Programme |  | Typo in the Note box about Auto Alignment of Related/Linked MPANs on the BP002 and BP003 process maps. Change 'Regisatration' to 'Registration' | Implemented |  | Interim Release 1 |  | Update BP002 (& BP003) call out box, also for BPM002 and BPM003 (Forward Migration) | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-96 |  | 2023-02-21 | SI Design | 2973 | Arif Jagot | Programme |  | Test-078 - SUPPI -Primary - Means SUPI? | Implemented |  | Interim Release 1 |  | Update Interface Catalogue | Data interface correction | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-97 |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.4 | Typo in MHHS-METH001-5.4c "and less than 90 days months different from the UTC Date" - propose removal of months | Updates Ready to Release |  | Interim Release 2 | 2023-06-23 | Update Method Statement i.e This needs to be 90 days not 90 months the artefact needs to be updated | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-98 |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.5 | Typo in MHHS-METH001 - 5.5 SDS shall use the most recent data a based on the event that triggered the | Updates Ready to Release |  | Interim Release 2 | 2023-06-23 | Typo error on clause 5.5 within MHHSP-METH001-SDS Validation Estimation v5.0 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-99 |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Working days correction | Clarify that Step 105 in the CoS Transfer read process is Working Days. Currently states 5 days | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Checked with SRO - 5 Working days for Step 105 in process, BPD003C, BR-DS-024.1 and BR-DS-024.2 | Requirement correction | MPAN Ownership | Data Services | MHHSP-BRS001 - SDS Requirements MHHSP-BP003C - Transfer of Reads MHHSP-BPD003C - Transfer of Reads
MHHS-DIN-100 |  | 2023-02-21 | RECCo | NA | Sarah Jones | Regulatory | BP002 to include LDSO as recipient | Step 180 in BP002 and BPD002 does not include LDSO as recipient of traditional meter details as per the wording of the step or the BRS (BR-MS-024) (Code Drafting Log Reference CDD-29) | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Update BP & BPD to align with BRS and add LDSO as recipient of MTDs | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Metering Service MHHSP-BPD002
MHHS-DIN-101 | DI-120 | 2023-02-22 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. (Raised as DI 120) | Closed |  |  |  | Included within CSS validation rule update. DUPLICATE See DIN-172 | No Change | MPAN Ownership |  | MHHS-DES138-Interface Catalogue
MHHS-DIN-102 |  | 2023-02-22 | St Clements | 2886 | Madison Layton | Software Provider |  | SCS raised the following under MHHS-DIN-7 "MPRS will reject any PUB-031 inlcuding those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist"" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8)" They have followed up with: Just found the change that corresponds to this one in v4.7 interface catalogue – REG0005 in IF-031. Could this also be added to IF-034 so that we can apply the same validation on MDR updates? | Closed |  |  |  | Proposed Change: Add validation "CSS Registration Request ID [DI-849] is valid for Registration Service", with error REG0005 - "CSS Registration Request ID [DI-849] is invalid or unknown" This mirrors a change made in v4.7 to IF-031, agreed as part of the DAG baseline of v4.7 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-103 |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory |  | Confirm that D0381 will continue to be used for updates to MPL address. BP010 & BPD010 currently allow emails, SDEP and other agreed forms can be used by Supplier or UMSO to update this - propose that these artefacts are amended to reflect that the D0381 is to be retained (Code Drafting Log Reference CDD-22) | Implemented |  | Interim Release 1 |  | Amend Steps 10, 21, 22 to explicitly use the D0381 rather than current wording | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-104 |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory |  | Impact of MHHS on SoLR arrangements - possibly needs an Issue Resolution Group discussion to undertake evaluation & impact assessment (Code Drafting Log Reference CDD-23) | Requires Industry Work Group review | 2023-07-15 | Interim Release 4 | 2023-08-09 | Feels like DA needs to consider how to undertake an evaluation of the MHHS change impact on SoLR arrangements |  | All Areas
MHHS-DIN-105 |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Related MPAN Business Rules | 1) IF-019 suggests RMP status can be Created or Operational - proposed this can only be Operational for subsidiary MPAN 2) Add validation rule to IF-019 requiring related MPANs to have consistent classification as domestic or non-domestic (reflecting the existing requirements) 3) Clarify what Registration Services should do when MPANs are related/linked and have different MS/MEM providers - is the IF-019 rejected or the MEM for the secondary MEM auto-deappointed? 4) What happens if the IF-019 fails validation by Reg Service at Step 330 in BP010? Design provides no guidance | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | 1. Removed reference to Created in the REG1001 validation rule for IF-019 2. We understand there is no existing validation within MPRS and this is not being amended as a result of MHHS implementation. This would require a wider industry change impacting CSS as Domestic Premise Indicator is managed independently of Related MPANs. 3. It would not be rejected, auto-alignment would pick up the discrepancy at the next daily run and de-appoint the export MS and appoint the import MS. 4. As with other rejected flows, the sending party should investigate the error and re-submit as appropriate. | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data BPD010 MHHSP-DES138-Interface Catalogue
MHHS-DIN-106 |  | 2023-02-23 | SI Design | 2955 | Kate Goodman | Testing | IF Routing | Inconsistency in DES138 for UMSO Routing 00-Introduction logs UMSO as the single routing option for Unmetered Service provision, as there can only be one UMSO related to an MPAN PUB-008 provides UMSC, UMSP and UMSI as options for secondary routing This inconsitency needs to be corrected | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Secondary routing rules updated following review with Avanade |  | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-107 |  | 2023-02-24 | SI Design |  | Simon Harrison | Progamme |  | Definition of DI-301 in DES138 is incorrect - it should reflect the D0265 value for LLF ID, at the moment it has the same definition as DI-497 Line Loss Factor | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Confirmed as an error with Kevin in SRO. Only appears in Reporting Data Catalogue DI-307 LLF ID should read as 'The Unique Identifier of a set of Line Loss Factors' |  | All Areas |  | Reporting catalogue
MHHS-DIN-108 |  | 2023-02-27 | SI Design | 2966 | Kate Goodbye | Testing | IF Routing | Ref:MHHSP-DES138-Interface Catalogue v4.7, IF-038, PUB-020, PUB-039. Document says that UM is relevant to these messages but UM thinks it is not relevant. Please clarify what the situation is. Raised in review of MHHSP-872 by Power Data. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Covered by Secondary routing updates |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-109 |  | 2023-02-27 | SI Design |  | Simon Harrison | Programme |  | Call out box in BP002/BP003 on Linked/Related MPANs needs to be updated as it includes reference to email/SDEP rather IF-019 as shown in BP010 | Closed |  |  |  | Confirmed - the call out box on BP002/003 needs to be updated Duplicate of DIN-64 | No Change | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service
MHHS-DIN-110 |  | 2023-02-27 | SI Design | 2983 | Kate Goodman | Testing |  | MHHSP-BP005-Data Processing-v4.6, Step 50-160 UMSDS is referencing Submit Required UTC period level consumption data (Step 50) with a arrow going to Receive UTC period level consumption data (Step 160) but no reference of IF-021 on the connection between both - reference should be added? | Implemented |  | Interim Release 1 |  | On Process map requires arrow to be labelled as IF-021 from step 50 to step 160 | Process model correction | Meter to Bank | Data Processing | MHHSP-BP005-Data Processing
MHHS-DIN-111 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Originally raised as T4-COM-1691 on 15th Sept 2022: "MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days " Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5 (Raised as DI-76) | Implemented |  | Interim Release 1 |  | Updated to 2 working days | Requirement correction | MPAN Ownership |  | MHHS-BRS003-Registration Service requirements
MHHS-DIN-112 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54 (Raised as DI-77) | Implemented |  | Interim Release 1 |  | Added note to clarify | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-113 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? (Raised as DI-78) | Closed |  |  |  | Agreed duplicate of DIN-29 and can clsoe | No Change
MHHS-DIN-114 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | EES does not appear to have been added to the routing rules tables on the interface tabs(Raised as DI-79) | Closed |  |  |  | Already present in v5 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-115 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On IF-050, this includes linked MPANs in it, but I don’t think these would ever be populated as you cannot link MPAN at MPAN creation. So EES would only ever get Linkage updates on the IF-20 Is there any value of having this therefore in IF-050?(Raised as DI-80) | Implemented |  | Interim Release 1 |  | Removed Linked MPANs and Related MPANs from IF-050 and added explanatory note | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-116 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | For IF-025, block B032 it states it is "MPAN Legacy Info (Mandatory where event is [SSCandProfileClass], and for Traditional Meters / Optional for other Meters)" It should just read mandtory for event code [SSCandProfileClass] and nothing else, it should not be optional for any of the other event codes(Raised as DI-81) | Implemented |  | Interim Release 1 |  | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-117 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?(Raised as DI-82) | Closed |  |  |  | Discussed with SCS and confirmed it is a limitation of swagger output but should be array of MPAN followed by array of meters followed by array of MAPs repeated per MPAN. Awaiting confirmation can close | No Change | Metering Changes | IF-005 JSON | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-118 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | In relation to the Sender Unique Reference, which is constructed as: S-<Interface>-<Participant Id>-<Role Id>-<Date>-<Sequence> (hex) I would like to comment as follows: • Why is the Unique Reference simply constructed using elements that are already contained in the message as distinct values? This just means the sender has to construct it and the receiver de-construct it? • Is the sequence number expected to be reset each day ? • It would be much easier and more logical for the Sequence to be a distinct item in the message? • Why is the sequence specified as hex? • Even given the expected large number of messages, and based on it being a number(13) (defined as Sting), a standard sequence number per Participant and Role would provide 9,999,999,999,999. If this is still seen as a limitation then it could simply be built from the date, e.g. 202301190000000001, giving a provision for up to 9,999,999,999 messages PER DAY from the same Participant / Role combination, which still enables a read every 30 minutes from every MPAN(Raised as DI-83) | Closed |  |  | 2023-06-23 | This is to send a unique reference and is used for auditing purposes. Please note the length of the Sender Unique Reference has been increased at the request of Avanade in 5.1.1. Examples updated |  | MPAN Ownership
MHHS-DIN-119 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | in swagger hub under IF-002 B907 list the B036 block, this is missing numberOfDigitsCumulativeRegister data item(Raised as DI-84) | Implemented |  | Interim Release 1 |  | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue. Swagger will be updated | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-120 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Inconsistency in naming of data item DI-091 In swagger hub: Number-Of-Digits-Cumulative-Register In interface catalogue IF tabs (E.g. IF-002) : Number of Displayed Register Digits In interface catalogue data catalogue tab: Number Of Displayed Register Digits (Cumulative Register)(Raised as DI-85) | Implemented |  | Interim Release 1 |  | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue and updated YAML accordingly | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-121 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0093 comment raised on 12/01/2023 " D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: "It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42 (Raised as DI-86) | Implemented |  | Interim Release 1 |  | Agreed to provide SEG scenario's in IF-005 Use Case guide. currently under review |  | Metering Changes | Change of Segment | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-122 | DI-87 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0084 comment raised on 12/01/2023 following the introduction of IF-019 and respective changes in the latest set of released artefacts MHHSP-BP010-Change of Registration Data -v4.5 "Shows Supplier Mastering Import Export Linkage. BSC CP1558 introduced changes to MPRS for the LDSO to manage this via the DB05. IF-019 should go to LDSO who should then produce a DB05 into MPRS." The process diagrams and requirement spreadsheets have been amended to show MPRS loading DB05 as a IF-019 response. DB05 is not a IF-019 response, it is a request from DNO/iDNO to create, amend or remove a import/export linkage. It does not currently have any capacity to include a IF-019 rejection response to trigger a IF-020 rejection response to DIP. (Raised as DI-87) | Implemented |  | Interim Release 1 |  | SCS reviewing preferred option with LDSO's The following changes would be required to the LDSO overview requirements: MHHS-BR-LD-043.3 LDSO Send Import/Export relationship update LDSO must send accepted Import/Export relationship updates to the Registration Service via the appropriate interface DB05 file or other agreed mechanism BP010B Change of registration data 900 MHHS-BR-LD-043.4 LDSO Send Import/Export relationship rejection LDSO must publish rejected Import/Export relationship updates on the Data Integration Platform using the appropriate interface MHHS-IF-020 to Supplier BP010B Change of registration data 900 On BP-010 for Linked Import/Export MPANs the following would be required: 1. Need to add rejected leg from step 900 to DIP 2. Need to add PUB-020 going from the DIP to the Supplier The BPD-010 will need updating accordingly. | Process Model correction | MPAN Ownership |  | MHHSP-BP010-Change of Registration Data MHHSP-BPD010, MHHSP-BRS005, Traceability Matrix
MHHS-DIN-123 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0083 comment raised on 12/01/2023 following the introduction of a new business rule on MPRS in the latest set of released artefacts MHHS-BR-RS-078 "MPRS cannot control how messages are sequenced at CSS and DSP. IF MPRS waits until the DSP responds before sending the Appointment message this could take hours (as this is a batch process) this will result in a delay in the appointment of the MDR. Sequencing requirements should be placed on CSS & DSP to ensure the correct MDR is appointed based on Effective dates provided from MPRS. However, they may not be necessary due to the way this interface works: The C0200 interface uses the PUT Method, which will replace the data held at CSS. Explicit ending of an Appointment is only required for a future dated appointment, this will be sent as one message with the Old and New MDR appointments. For Same Day or Retrospective the new MDR Appointment will Replace the currently set value. This implicitly ends the previous MDR Appointment. On a CoS, the MDR is linked to a Registration not a Metering Point. The previous MDR will end naturally when the Previous Registration becomes securedInactive. An explicit message to end the MDR appointment on the Previous Registration is not required . MPRS will only send two separate updates to CSS when there is a gap in MDR (SDS) appointments. For Example a change of segment to Advanced and then back to Smart. This would need to happen over a short period to generate two messages that could go out of sequence" The MHHS design team rejected with comment "The MHHS design is based upon what was agreed as part of the R044 consultation. This scenario does not reflect our understanding of how the CSS/DCC/DSP interface will work as set out under R044. " This is how C0200 currently works today and the interface is unchanged in R0044. This will put a signfiicant requirement on MPRS that will reduce time available time for other core MHHS development activities with no benefit to industry.(Raised as DI-87) | Closed |  |  |  | No Change - updated in v5.0 | No Change | MPAN Ownership
MHHS-DIN-124 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0089 comment raised on 12/01/2023 "D-021 was meant to give more detail on how L1-L4 validation should be used and provide more error codes for use. This has not been done as far as I can see Blocking resolution to this T4-COM-1749, T4-COM-1769 and T4-COM-1768" Comment was closed as clarified however none of these items have been resolved and we have no dates as to when they will be. comments blocked that were raised initially on 15/09/22 Comment T4-COM-1749: "The Registration Service, as part of its L3/L4 validation should ensure that there is consistency between the data content of the IF-033 issued to the Service Provider and the [returned] content in IF-034 - if this isn't so then message should be returned to Service Provider using ""MSGStatus Message"" mechanism." Does MPRS only need to validate consistency in the data it loads on the IF-033, not the data that is not loaded" Comment T4-COM-1769: "We need validation rules to be defined for this flow, Does not match IF-031, content of the PUB-034 does not match the IF-031. No Proposed Appointment Found, PUB-034, does not link to any Pending IF031s. Define Validation Rules for PUB-034 The 034 content must match the original if-031 content the 034 must have a corresponding IF031 the 034 has already been received for the IF-031 Generic Standard Validation, MPAN exists valid in ISD ETC" Comment T4-COM-2768: "We need some generic codes for standard validation rules such as: Service/Supplier is valid in ISD MPAN exists in MPRS MPAN is not Disconnected Service/Supplier is Valid in MDD (so CSS doesn’t reject updates)" (Raised as DI-89) | Implemented |  | Interim Release 1 |  | Added RMP status check to IF-034 and refined validation rule notes regarding different values received from IF-033 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-125 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | IF Routing | WOA-0091 comment raised on 12/01/23 D-030 "how routing will work in the DIP has not been updated this information is required for our development" MHHS Design Team has closed as clarified however there is still uncertainty around the DIP routing, and there are not dates provided for when the detailed DIP design will be released. This will clock certain elements of development (Raised as DI-90) | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Secondary routing rules updated following review with Avanade |  | MPAN Ownership
MHHS-DIN-126 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0092 comment raised on 12/01/23 following more infromation around D-022 being clarified "D-022 Following the work off item being agreed on what is required for an MPAN to be traded - it has now been possible to fully assess the optionality of data items in the interfaces Data items still mandatory in interfaces that must be changed to optional: Annual Consumption (IF-001) Incumbent Service Providers (IF-002, IF-033) Incoming MS/DS (IF-037) These are not required at creation, nor at traded, and therefore could be non existent in MPRS when MPRS generates this outgoing IF messages Blocking resolution of T4-COM-1727 and T4-COM-1735" Closed as clarified however none of the issues listed have been resolved Annual consumption still reads madatory on a CoS for IF-001, the issue is MPRS may not have this data item. The item is not required to reach a status of traded, therefore CSS will accept a CoS on this MPAN without annual consumption being populated, and then MPRS will not be able to provide this data item on the IF-001 that results from the CoS. This must be changed to optional OR the definition on what is needed to be traded should be updated to include annual consumption. Incumbent Service Providers is still mandatory on IF-002 for CoS Again as MS is not required to be traded, CSS will accept a CoS request with or without a current MS, and so MPRS will not be able to provide an incumbent MS in these cases. It must be changed to optional or the definition of what is needed to be traded should include MS. Incoming MS/DS is still mandatory on IF-037, there are numerous reasons an appointment may be lapsed, the only change that would gaurantee a new incoming SP that MPRS could send on this flow is a change or SP (CSERV) scenario. For CoS the supplier may not have sent in new appointments, for DEREG there will be no new appoitnments, for SEG the market segment may have changed but the supplier may not have sent in new appointments, same for change of connection type, and for IMPEXP and RELATED the parent MPAN might not have MS/DS appointed at all so there would be no new appointments for MPRS to populate on this flow. This must be changed to madatory ONLY on CSERV (Raised as DI-91) | Implemented |  | Interim Release 1 |  | Discussed with SCS. Covered by clarification on nullable and interface notes- All these issues are resolved by the Mandatory Nullable Solution. Confirmed Annual Consumption block will only be provided where available in Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-127 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 "DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least "Registered", if no DS is appointed then there is already an appropriate Event Code" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone (Raised as DI-92) | Closed |  |  |  | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-128 | DI-93 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0095 comment on 12/01/23 "D-009 This is blocking closure of T4-COM-1730. There is a lack of clarity around the treatment of rejection from CSS, between both R044 and the MHHS design artefacts e.g. MHHs-BR-RS-088.1 and MHHS-BR-RS-079 both suggest MPRS would still load the new MDR record and appoint in MPRS despite a rejection from DCC/CSS. Our assumption would be that we do not load a MDR appointment that is rejected from DCC/CSS and we send the IF-035 rejection to notify the DS/Supply of this. However no clarity on what to do if DCC/CSS rejects a MDR end date on a de-appointment T4-COM-1730 was raiseed on 15/09/22 MHHS Design Team Rejected the comment with a statement this is outside of MHHS Scope. How MPRS treats the MS/DS appointment and how it responds over hte DIP is within MHHS design. The requirements we are enquiring about are already included in the MHHS design documents as in scope also. This is a major blocker to MPRS design on MDR appointment processes (Raised as DI-93) | Closed |  |  |  | Discussed with SCS this is a REC requirement. Agreed no error codes will be received, just use a generic response. | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-129 | DI-94 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0086 comment on 12/01/23 following the release of the first draft of IF-050 in the revised interface catalogue artefact "Related MPANs and Linked Import Export are not set at MPAN Creation. EES can get these on the IF020 Remove these blocks from IF-050 as they would never be populated" MHHS design team marked as accepted and changed but the blocks still exist in IF-050, these blocks will never be populated and so should be removed from the IF-050 interface(Raised as DI-94) | Closed |  |  |  | Closed - duplicate of DIN-115 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-130 | DI-95 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0088 on 12/01/23 "D-011 & D-050 it is still unclear how LLFC and DUoS Tariff ID will be stored and managed in MPRS. DUoS should be an Alias of LLFC and not have its own data item in MPRS. LLFC will be renamed to DUoS Tariff when the old arrangements have ended. LDSO impacts having to maintain two items which will lead to billing issues" Marked as clarified and closed witih a clarification statement to be issued on tuesday 24th January, this clarification statement was not received. Awaiting clarification(Raised as DI-95) | Closed |  |  | 2023-06-23 | Email to Madison to check can close |  | MPAN Ownership
MHHS-DIN-131 | DI-96 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 is missing business rules: REG1001 - MPAN [DI-063] is at [REG.RMPStatus] not status Created/Operational. This should apply to IF-025. IF-025 is missing a rule that consent granualiry EFD must not be earlier than supply start date. Consent Granularity EFD must not be prior to current consent granularity EFD The Consent Granularity Energy Direction Domestic Premise Indicator Combination must be valid in ISD(Raised as DI-96) | Implemented |  | Interim Release 1 |  | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-132 | DI-97 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 IHD update does not include validation rule 1019, does this mean IHD EFD can be prior to current and effectively cancel out the current IHD status completely, or is it just an error and the rule should be added to interface catalogue for IHD?(Raised as DI-97) | Implemented |  | Interim Release 1 |  | Amendment accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-133 | DI-98 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 will not allow a SMSO to be set for a non smart meter "REG1022 - SMSO ID Cannot be set where Market Segment is [Reg.Segement]", would a non smart supplier be able to send a B031 SMSO block, they will need to be able to if they are required to clear an old SMSO by populating SMSO as null(Raised as DI-98) | Implemented |  | Interim Release 1 |  | Added new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-134 | DI-99 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 "SSC must be valid in ISD. Rejection reason: REG1044 - SSC must be a valid value in ISD" SSC are not yet populated in ISD(Raised as DI-99) | Closed |  |  |  | Clarified that SSC validation will be based on Frozen MDD. Seperate DIN to cover availability of ISD | No Change | MPAN Ownership |  | MHHSP-EM021 ISD Entity Data Map, MHHSP-DES138-Interface Catalogue
MHHS-DIN-135 | DI-100 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Should B032 PC and SSC block on IF-025 only be permitted when theres a traditional meter fitted at the MPAN?(Raised as DI-100) | Closed |  |  |  | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-136 | DI-101 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | How is the Green Deal Exists defined. Does this mean there's a green deal linked to the MPAN regardless of dates, does it mean there's a green deal currently active or due to become active, or does it mean there is a currently active green deal assigned to the MPAN? (Raised as DI-101) | Implemented |  | Interim Release 1 |  | Remove Green Deal exists (DI-110) from Data Catalogue and IF-050 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-137 | DI-102 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-007 Validation rule "Metering Service [S0.SenderID] holds valid previous appointment then Energisation Status EffectiveFrom Date [DI-034] should be < [REG.App End Date] + 10" The way it's curently written suggests MPRS should accept an IF-007 from the previous appointed MS, event if there ETD was greater than 10 days ago, provided the ES EFD date was less than their ETD + 10. E.g the previous MS could send IF-007 two years later with ES EFD of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then a separate rule should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? Linked to DI-41(Raised as DI-102) | Implemented |  | Interim Release 1 |  | REG1003 validation rule updated in IF-007 to constrain energisation updates to 10 days after the MS appointment period |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-138 | DI-103 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-034 Submitted rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD | Closed |  |  |  | Duplicate of DIN-176 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-139 | DI-104 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Need clarity on what role code should be used in C0200 for MS and MDR appointments Linked to comment T4-COM-1790 which was accepted as design issue raised but then moved to a work off item "We would like to see some indicative Role Codes and DIP IDs so we can populate development systems with this data " | Closed |  |  |  | Send "MDR" as role code as per Registration requirement. Allocation of DTN MPIDs is a seperate issue | No Change | Registration | Existing EMAR I/F | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-140 | DI-105 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 | Closed |  |  |  | Discussed with SCS the IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR. Agreed to close | No Change |  |  | MHHSP-BP003A, MHHSP-BRS003 Registration service requirements
MHHS-DIN-141 | DI-106 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 | Closed |  |  |  | RECCo consequential change | No Change |  |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-142 | DI-107 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | There currently aren't sufficient rules to ensure that a principal primary MPAN is not also a linked export subsidiary MPAN or that a subsidiary secondary MPAN is not also a principal import linked MPAN. The MHHS design either should accommodate both (would need clarity on how to treat cases where MPANs are BOTH principal and subsidiary) OR new rules should be introduced to prevent this occuring AND cleanse existing cases ahead of migration | Implemented |  | Interim Release 1 |  | Validation rules updated for IF-019 | Missing/incorrect validation rule | MPAN Ownership |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-143 | DI-108 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Requirements were uplifted in v4.5 to include logic around market segment on related MPANs MHHS-BR-RS-124.1: Registration Service must, in the case of Related MPANs and following derivation of Market Segment for individual MPANs, update the Market Segment for the Primary MPAN and all the Secondary MPANs based on the following rule: 1. If any MPAN in the Related MPAN Group has a (derived) Market Segment of Advanced, then set the Market Segment for all the MPANs to Advanced and set the Market Segment Valid Flag to "Yes" for all the MPANs This specifically cites related primary/secondary and does not mention linked import/export associations at all. But then another requirement implies maybe it should have done: MHHS-BR-RS-127: Registration Service must , in circumstances where the derived market segment is invalid (and has not been overridden by Linked/Related MPAN logic ) Should MHHS-BR-RS-124.1 have applied to linked import/export associations too or is it intended solely for primary/secondary related MPANs? | Implemented |  | Interim Release 1 |  | This should only apply to Related MPANs. Updated RS-127 | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-144 | DI-109 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131 This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to: Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. | Closed |  |  |  | Duplicate See DIN-169 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-145 | DI-110 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. | Implemented |  | Interim Release 1 |  | Added L as valid value for DI-979 in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-146 | DI-111 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. | Implemented |  | Interim Release 1 |  | Agreed with SCS to reuse STD Error Response Section in IF035 to communicate Lapsed Reason . See DIN-145 for summary of updates | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-147 | DI-112 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-008 response block is listed as mandatory, however on disconnection the MPAN is de-energised by MPRS automatically. The supplier cannot de-energise after disconnection on the IF-007, it must be automatic at MPRS as per The de-energisation needs to be communicated on the IF-008 but it is not in response to an IF-007 and so we cannot populate the response block. | Implemented |  | Interim Release 1 |  | Data interface change agreed. Added Interface note to IF-008 to cover forced de-energisation changes by Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-148 | DI-113 | 2023-02-10 | St Clements | 2864 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-113 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { "confirmingMpid": "string", --* "registrationId": "string" --*, "updateSucceeded": boolean --* } Suggest that DI-0980 is removed from B066 | Closed |  |  |  | Discussed with SCS and agreed to close - note no error codes returned from CSS so will provide generic error code | No Change |  |  | MHHSP-DES138-Interface Catalogue, JSON, YAML
MHHS-DIN-149 | DI-114 | 2023-02-10 | St Clements | 2865 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-114 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 On IF-038 validation "REG1073 - Customer Direct Contract already exists for MPAN [DI-063] for that period" The respective validation rule for this states: If Contract End Date [DI-145] <= Max existing active MS contract end dates [Reg.MAX_DCMS_Enddate], EXCEPT IF requesting MS [S1.SenderID] = Currently Active Direct MS [Reg.CurrentActiveDC_MS_DIPID] AND Contract End Date [DI-145] <= existing active MS contract end date [Reg.CurrentDCMS_Enddate] This rule doesn't fully prevent overlapping appointments as does not cover where the MS is not currently contracted MS and ETD > current ETD which should also be rejected. Think a simpler rule would cover this scenario more fully e.g. If there is an active contracted MS/DS, and the submitting MS/DS does not match then reject And then ETD can be greater or later than current ETD for the currently contracts MS/DS anyway so doesn't need specifying? | Closed |  |  | 2023-06-23 | SRO Team do not belive that a change is required. |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-150 | DI-115 | 2023-02-10 | St Clements | 2866 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-115 in our log In some place on IF-038 tab there is reference to a future customer direct contract e.g. "OR requesting MS [S1.SenderID] <> Any future Direct MS [Reg.FutureDC_MS_DIPID] " "extended dates will be subject to checking if another Service Provider has registered a separate Customer Direct Contract covering the same period" - this can only happen if there's a future appointment "AND ALSO removing all future periods which may or may not have been accepted and recorded previously." As there is no Effective From Date included in the flow MPRS will store an Effective From Date of the system date at the time of creation of the customer contract indicator. It will not be possible to set one to start in the future as the IF-038 does not include effective from date. Is this the same understanding as the MHHS Design Team? | Closed |  |  | 2023-06-23 | As per DI-149 above SRO Design Team do not belive that any changes are required |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-151 | DI-116 | 2023-02-10 | St Clements | 2868 | Madison Layton | Software Provider |  | Just spotted a change in v4.7 and raised in our log as DI-116 Artefact: MHHSP-BP010-Change of Registration Data -v4.7 under MPL and GSP Group amendment section, DB02 has been amended in v4.7 to DB002. DB002 is not correct, DB02 was the correct name For reference the DB flows only ever have one 0 in, there is DB01 (MPAN creation), DB02 (MP updates), DB03 (Disconnection) and DB05 (Import/Export Linkages) | Implemented |  | Interim Release 1 |  | BP010A step 10 flow name change to DB02, BP010B step250,step440, Step560 flow name change to DB02, and update BPD descriptions to DB02. | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-152 | DI-117 | 2023-02-14 | St Clements | 2912 | Madison Layton | Software Provider |  | On looking more closely at the validation rules for IF-019 spotted a few issues. IF-019 REG-1061 rule for Related Create event code appears to be written incorrectly. The rule and rejection description don't quite align. Rule: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) are not currently part of an import/export relationship Rejection reason: REG1061 - Prosposed MPAN(s) [DI-073] / [DI-074] are already part of a Related MPAN Relationship Should the rule read: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) is currently part of a related primary/secondary relationship? The rule and descriptions also don't appear to fully align for some in import/export section too - REG1052, REG1055, REG1057 and might need some minor tweaks to correct. | Implemented |  | Interim Release 1 |  | REG1061, 1052 and 1055 rules updated. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-153 | DI-118 | 2023-02-14 | St Clements | 2913 | Madison Layton | Software Provider |  | On working on detailed design for Related MPANs, noticed the IF-019 interface is missing a rule that the Secondary MPAN must not be a Primary in another Relationship. You could expand REG1064 to include this as the description sounds like it should have been covered here. Rule: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN Description: REG1064 - Proposed Secondary MPAN [DI-074] is already part of a different MPAN Relationship Could amend rule to: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN OR [DI-074] is already in a relationship as a Primary MPAN | Implemented |  | Interim Release 1 |  | REG1064 validation rule updated | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-154 | DI-119 | 2023-02-15 | St Clements | 2919 | Madison Layton | Software Provider | IF-019 validation gap on primary and subsidiary MPAN | On further detailed design we’ve spotted a potential design gap. Currently it is possible to enter a state where an MPAN is both a primary and subsidiary MPAN at the same time (e.g. Primary but also export linked or Secondary but also import linked). The current MHHS doesn't accommodate an MPAN being in both states at the same time. We’ve already looked to add rules to try to mitigate this on DB02/DB05 internal flows but would need additional rules on IF-019 to fully prevent this scenario occurring. Rules we think are required: 1. On receipt of IF-019 with event code RelatedCreate or RelatedAdd, the primary MPAN must not have energy direction of Export 2. On receipt of a IF-019 with event code RelatedCreate or RelatedAdd, any listed secondary MPAN must not in an active Import/Export relationship as the Import MPAN 3. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Import MPAN must not be in an active relationship as the secondary MPAN 4. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Export MPAN must not be in an active relationship as the primary MPAN | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Discuss with SCS | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-155 | DI-120 | 2023-02-15 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. | Closed |  |  |  | see also DIN-172/173. Included in 5.1 DUPLICATE See DIN-172 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-156 | DI-121 | 2023-02-24 | St Clements | 3078 | Madison Layton | Software Provider |  | We have logged a new design issue under DI-121. IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP | Closed |  |  |  | Duplicate of DIN-173 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-157 | DI-122 | 2023-02-27 | St Clements | 3090 | Madison Layton | Software Provider |  | New design issue (SCC Ref DI-122) for the IF-005 related to REC CP R0032. The current v5.0 validation in the IF-005 does not include the new validation introduced with REC CP R0032 (R0032 is approved and being implemented in the D0312 this June): NEW REC CP R0032 Validation: V Rejected – ESME ID already exists within MRPS and does not match Removed Meter, Associated Import/Export MSID or Related MPAN W Rejected - MSN relates to a Smart Meter Type and the ESME ID is NULL X Rejected – ESME ID Format is Invalid Y Rejected – Number of Displayed Register Digits is NULL and the MSN relates to a Smart Meter Type Z Rejected – Non-Smart Meter Type with Number of Displayed Register Digits populated AA Rejected – Meter Location is invalid AB Rejected – Non-Smart Meter Type with ESME ID populated AC Rejected – Number of Displayed Register Digits is incorrect IF-005 Validation: V not covered, needs to be added as a Level 5 Validation Rule W is already covered by DI-085 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) X is already covered in DI-085 population notes (Level 4 validation RCP1023 Msg Contains Invalid Valid Value Combination(s)) Y is already covered in DI-091 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) Z is not explicitly covered, suggestion: add to DI-091 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AA is covered in the population notes AB is not explicitly covered, suggestion: add to DI-085 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AC not covered, Suggestion: add the following population note from R0032 to DI-091: Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” Summary Please add the following Changes to the IF-005 to align it with the D0312 validation and maintain the same level of Smart Meter data quality in the Registration Service: New Level 5 Validation rule for DI-085 implementing V from the D0312. ESME ID must be unique within MPRS unless it’s a Linked MPAN where the same Smart Meter can be shared across Linked MPANs New population note for DI-091, only to be included for Smart Meter Types New population note for DI-085 , only to be included for Smart Meter Types New population note for DI-091, Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” | Implemented |  | Interim Release 1 |  | New Validation Rules added to IF doc to ensure full coverage and alignment with CP Error codes described | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-158 |  | 2023-02-27 | Elexon | 2908 | Derek Weaving | Central Body |  | As part of the Performance Assurance Working Group discussions on Supplier Charges, we are exploring the use of CCCs to categorise the data for future charges. It is noted that Settlement Period Quality Indicator referenced in the VAS Method statement is for illustrative purposes and would welcome clarity on the following: · What is the intended process to populate the Settlement Period Quality Indicator in the initial ISD Table? · What would be the process to be involved in those activities to determine the categorisations should additional CCCs be required? | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | Recommending a change to this ISD Data Item: Settlement Period Quality Indicator to be set as per Appendix 1 of MHHSP_METH007 MDS_Method_Statement v5.0 This data item need to be changes to something like ‘Valid Settlement Period Quality Indicator Set’ and the field size needs to be increased. The data catalugue will need the revised data item and the field length will need increasing from 20 to at least 50. This Item also appears in some interfaces that will need t be updated This is because it represents a set of SPQIs. The initial intention is to populate as per the table and check if any new SPQIs have been introduced in the baseline design Method Statement that are not covered. If new CCCs are introduced the appropriate flags for each new CCC would need to be agreed. However, it is likely that another dimension to the table below would need to be introduced to facilitate new CCCs. |  | Meter to Bank | Volume Allocation Service | MHHSP-METH006_VAS_Method_Statement ED021 ISD Entity spec MHHSP-DES138-Interface Catalogue ECS report
MHHS-DIN-159 |  | 2023-03-01 | ENWL | 2994 | Paul Band | Network Business | Interfaces for UMSO | DES-138 Interface Inconsistencies vs BSCP7XX for UMSO Discussions with ENWL have highlighted a number of inconsistencies in the Interface Catalogue when it comes to routing for UMSO's. DIN-106 also refers. UMSO is not listed as a recipient in DES-138 for the PUB-008, but this is in the draft BSCP and should be added to the PUB UMSO is not listed as a recipient in DES-138 for the PUB-020, but this is in the draft BSCP - this is not needed in the BSCP as there are no unmetered Related MPANs UMSO is not listed as a recipient in DES-138 for the PUB-035, but this is in the draft BSCP - view that it is unlikely for this flow ever to be used as the appointment will not trigger any processes to need a subsequent update UMSO Is listed as UMSI, not UMSO in PUB-036 in DES-138 UMSO is listed as UMSC, not UMSO in PUB-018 in DES-138 The IF_LIST tab should be reviewed for consistency | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | As with DIN-106, there are inconsistencies in the Interface Catalogue for UMSO routing. This has been compounded by a review of the draft BSCP for UMSO, which has added a number of PUB flows going to UMSO that aren't currently in the catalogue. Covered by updated secondary routing rules Design to check requirements in BSCP and MHHS BPs and ensure the interface catalogue reflects a consistent approach | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue and possibly related business processes and descriptions E2E001
MHHS-DIN-160 |  | 2023-03-14 | Ovo Energy | 2862 | David Morley | Supplier | BP009 flow addition | Steps 205 and 210 in BP009 wont be completable in the event that theres no comms. I think the process would be workable if there was an exception route here - see red arrow below. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Update Steps 205 and 210 in BP009 with "Comms Availanble" line label add flow from step 205 to step 215 with “Not Commissioned / No Comms” line label | Process Model correction | Metering Changes | Change of Metering | MHHS-BP009
MHHS-DIN-161 |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 requirement correction | MHHS-METH001-5.4c Please confirm the requirement: “where daily advance records are available [either in the past or future] and less than 90 days months different from the UTC Date requiring a daily advance - use the mean actual Meter advance from the closest [4] weeks for the same Day Type (as defined in ISD).” | Closed |  |  | 2023-06-23 | Duplicate of DIN 97. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-162 |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 typo | MHHS-METH001-5.5 typo “Where DAEs are required to be calculated the SDS shall use the most recent data a based on the event that triggered the estimation.” | Closed |  |  | 2023-06-23 | Duplicate of DIN 98. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-163 | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Conditionality Rule for B037 | It is not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure it is unclear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated conditionality rule for Block B037 in IF-001, IF-002, IF-033, IF-036 |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-164 | DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0093 comment raised on 12/01/2023 "" D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692"" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: ""It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period"" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42" | Closed |  |  |  | "This requirement stands - review with SCS in light of SEG scenario. We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error...". Reviewed with SCS and agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-165 | DI-122 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | See separate sheet Duplicate of DIN-157 | Closed |  |  |  | CR required to add rules in line with CP R0032 Added Miscellaneous Data Validation to IF-005 to cover REC CP R0032 validation rules Wrapped up into design teams main CR Doesn't need to be raised by SCS | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-166 | DI-77 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54" | Implemented |  | Interim Release 1 |  | Added clarification to REG Notes re Consent and Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-167 | DI-78 DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? " | Closed |  |  |  | Agree you can't. Could update 1032 rule for USP? Duplicate see DI-29 | No Change
MHHS-DIN-168 | DI-92 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 ""DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least ""Registered"", if no DS is appointed then there is already an appropriate Event Code"" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone | Closed |  |  |  | CR for new functionality. "Already covered by no MS/DS appointed - MPRS would try to align MS/DS with principle and couldn't as there's no registration to align this to. Need an extra check that can only autoappoint if there's a registration to prevent MPRS crashing Maybe one for DRG? Jon at RECCO for consequential change? Agree not to build for this scenario as this would be an edge case and close | No Change
MHHS-DIN-169 | DI-109 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to:Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. | Implemented |  | Interim Release 1 |  | Simplified MHHS-BR-RS-131 on when to lapse a SEG appointment | Requirement correction | MPAN Ownership |  | MHHSP- BRS003, MHHS-BR-RS-131
MHHS-DIN-170 | DI-110 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. | Closed |  |  |  | Duplicate of DIN-145 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-171 | DI-113 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { ""confirmingMpid"": ""string"", --* ""registrationId"": ""string"" --*, ""updateSucceeded"": boolean --* } Suggest that DI-0980 is removed from B066" | Closed |  |  |  | Agreed with SCS being retained but due to optionality may have to populate text e.g. contact DSP. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-172 | DI-120 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. | Implemented | 2023-04-27 | Interim Release 1 |  | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-173 | DI-121 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP | Implemented | 2023-04-27 | Interim Release 1 |  | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-174 | DI-72 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a Submitted MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60" | Implemented |  | Interim Release 1 |  | "Agreed- doc updates MDR can have gaps between DS EFD and MDR EFD" Updated REG1083 validation in IF-034 so that it allows MDR Effective from dates >= SSD/ DS Eff From date/Existing MDR Eff from date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-175 | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" | Closed |  |  |  | Duplicate entry | No Change | MPAN Ownership
MHHS-DIN-176 | DI-103 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-034 new rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD" | Implemented |  | Interim Release 1 |  | Agreed -doc updates Updated REG1082 to apply for both [SDS-MDRUpdate] and [DSAppSPRepsonse] events in IF-034 | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-177 | DI-105 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 " | Closed |  |  |  | "Reason for IF-035 is to trigger when SDScan send the Meter info" & The IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR Agreed with SCS no changes are required, they now understand the context agreed to CLOSE | No Change | MPAN Ownership |  | MHHSP-BP003A
MHHS-DIN-178 | DI-106 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | "Should this be specified by RECCo not by MHHS Programme - Design Team were asked to remove this requirement previously Assuming we use MEM Role code of M each time, do not send DS Should it be part of consequential change? Concern around assurance - we will build without a requirement to fulfill and may be aske to take it out by assurrance provider" |  | MPAN Ownership | MPAN Ownership | Existing EMAR I/F
MHHS-DIN-179 | DI-111 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. | Closed |  |  |  | Duplicate of DIN-146 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-180 | DI-125 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 the Meter Removal is currently not permitted for a prospective MS Is it possible for the MS to need to remove two meters and replace it with one? In which case meterexchange would only allow them to do part of this process (remove 1 and add 1) but not complete it, so SEG could not complete. Should meter removals therefore be allowed for prospective MS? (REG1019) | Implemented |  | Interim Release 1 |  | Revised REG1019 and added REG1027 for MeterRemoval event in IF-005 | Requirement correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-181 | DI-126 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Missing Rule on If-005: MAP EFD must not be > removal date | Implemented |  | Interim Release 1 |  | Added new rule for MeterUpdate and MeterHistoryUpdate events so that MAP EFD must not be > removal date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-182 | DI-127 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 On exchange - the MAP and IHD groups are for new installation not removed meter - does this need to be clarified? | Implemented |  | Interim Release 1 |  | New note added to IF-005 to clarify that only the newly installed MAP and IHD information is required on MeterExchange | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-183 | DI-128 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-005, IHD EFD missing validation in IF-005 (Between install and removal date) | Implemented |  | Interim Release 1 |  | Covered Release 5.1, IF-005, IHD EFD missing validation added | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-184 | DI-129 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-005 incorrect validation rule: REG1010: On event code Meter exchange and Meter Install rule states MAP EFD >= Install date, it should be = not >=" | Implemented |  | Interim Release 1 |  | IF-005: Updated to REG1010 (MAP Eff from date check ) to = install date for MeterInstall and MeterExchange | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-185 | DI-130 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | It should not be possible to change MDR EFD once set. Need validation rules to enable MPRS to reject if IF-034 is submitted with current MDR but a different EFD. | Implemented |  | Interim Release 1 |  | Agreed - doc updates Covered by L3/4 validation as per updated Validation rule notes | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-186 | DI-131 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031, there is currently not enough validation to ensure on a SEG, that the same SP isn't appointed for the current registration. Need additional validation rule: If scenario SEG and current supplier, then SP must not be current SP. | Implemented |  | Interim Release 1 |  | Agreed - doc updates Updated validation rule Added REG1095 in IF-031 to check different Data Service proposed for SEG appointment | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-187 | DI-132 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Unhappy Path Scenario: Receive IF-031 for MPAN that is both Principal and Subsidiary MPAN at the same time. This will be rejected as per REG1038/REG1039 Supplier will be unable to appoint MS/DS for the MPAN or any related/linked subsidiary MPANS. | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | "How will unhappy path scenarios be considered/impact assessed? Not needed for PIT/SIT" | Process Model correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-188 | DI-133 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031 the rule REG1030 reads [DI0-828] in not a valid UMSO in DNO [DI-108]/[DI-109] This should read LDSO not DNO | Implemented |  | Interim Release 1 |  | Tied up with If-005 rejection description flexibility action Change REG1030 to read: REG1030 - [DI0-828] in not a valid UMSO in LDSO[DI-108]/[DI-109] SC change incorporated into 5.1.1 | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-189 | DI-134 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On IF-031, REG1036 is written to only apply to USP when it should apply to all scenarios? ""Proposed MDR Date [DI-836] >= [REG.MPAN_SUP_SSD] However don't think this rule is required at all as this is already covered under the REG1036 rule that MDR Date < DS EFD? Linked to DI-66" | Implemented |  | Interim Release 1 |  | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-190 | DI-135 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-034 missing validation rule REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational | Implemented |  | Interim Release 1 |  | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-191 | DI-136 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | MPRS does not currently prevent Retrospective changes to DUoS Tariff ID or Connection Type. Should MPRS add new validation rules for these items to restrict Retrospective changes? Updating the DIN with additional item at customers request (Updated on 22/05/23 by KH) Please can you update DIN-191 to include Disconnection Date & Export Association. We don't currently have any restriction on how far these data items (and the others in DIN-191) can be back dated. This is a retrospective change through the DB interface and not a Manual Amendment | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Internal review for whether DUOS Tariff ID updates should be retro | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-192 | DI-137 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | For If-031, scenario SEG, the business process diagram/requirements only describe the appointment lapsing once reaching it's SSD if no SA is received. If we receive a cancellation we would like to lapse the appointment at that point in time (it cannot become secured active after being cancelled) and not wait until the SSD to do this. | Implemented |  | Interim Release 1 |  | Added new requirements to BRS003, MHHS-BR-RS-24.1 and 58.1 | Design Ambiguous | MPAN Ownership |  | MHHSP-BRS003-Registration Requirements
MHHS-DIN-193 | DI-138 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | The YAML name for metered indicator (Data Item 127) is meteredUnmeteredIndicator. This is then set to true of false. It isn't clear whether true means it's metered or unmetered due to the naming convention. It should be named meteredIndicator instead to make it clear true means metered, false unmetered. | Implemented |  | Interim Release 1 |  | Updated YAML details in the Data Catalogue for DI-127 Metered Indicator. Updated YAML accordingly Updated data catalogue/ YAML | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-194 | DI-1 | 2023-03-15 | St Clements | 4475 | Madison Layton | Software Provider |  | For IF-035 what is Event Code [IMS-SendMTD] intended for? If intended for sending to old MS then this should be done via secondary routing on the original IF-035, not via another separate IF-035 message produced by MPRS with different event code. | Closed |  |  | 2023-06-23 | This message is effectively a copy of the DSAppAccepted AND/OR MSAppAccepted but sent to the Incumbent (current) Metering Service to act as a trigger for that MS to send MTDs. This should be created by MPRS. Requirements MHHS-BR-RS-053 and MHHS-BR-RS-019 cover Registration Service sending this. Message to check and close | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-195 | DI-76 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Originally raised as T4-COM-1691 on 15th Sept 2022: ""MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days "" Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5" | Implemented |  | Interim Release 1 |  | Agreed doc update Also in Reg Notes tab Updated validation rules and Reg notes Updated REG1037 in IF-031 to 2 workings days and updated REG notes, to align with process and requirements | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-196 |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Updates are required to clarify nullable fields | Implemented |  | Interim Release 1 |  | Updates to Interface catalogue includes changes to interfaces and block data items which are present and can be null 1. MHHSP - ERI011A - ECS Reports - Internal v5.1: The data catalogue is the only tab that has been updated 2. MHHSP - ERI011B - ECS Reports - External v5.1: The data catalogue, DIP_Common, MHHS-REP-003 and MHHSP-REP-006 have been updated |  | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue, MHHSP-E2E001 End-to-End Solution Architecture MHHSP - ERI011A - ECS Reports - Internal MHHSP - ERI011B - ECS Reports - External
MHHS-DIN-197 |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Decision taken to document digital signing of interfaces outside of the interface document. | Implemented |  | Interim Release 1 |  | Remove Z0 and ZI blocks from all interfaces. Signing process will be documented in the Code of Connection document. | Technical corrrection | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue Code of Connection
MHHS-DIN-198 |  | 2023-03-15 | Large Suppliers |  | Haz Elmamon | Large Suppliers |  | Clarification on complex meter site, passed down from DAG as part of the work off plan, Haz to gather concerns for discussion at DA. LSC Rep provided information to the issue on 22-Mar-23 | Requires Industry Work Group review |  | Interim Release 4 | 2023-08-09 |  |  | MPAN Ownership
MHHS-DIN-199 |  | 2023-03-23 | BGAS | 3460 | Neil Strange | large Suppliers |  | Participant wishes to see the use of standardisation in the interfactions between the SDS and sub roles MDR PSS | Closed |  |  |  | Closed based on recommendation for programme CR to be raised by the Large Supplier Rep | No Change | Supporting Docs | SDS Validation / Extimation | MHHS-DES138-Interface Catalogue
MHHS-DIN-200 |  | 2023-03-24 | CGI | 3489 | Chris Beard | Software Provider |  | If there are multiple register readings available for the same Settlement Day, where is the hierarchy defined for selecting which should be used? Is this solely based on Reading Method (i.e. 1. A – Actual, 2. C – Customer, 3. E – Estimated by SDS, 4. S – Estimated by Supplier) or is it dependent on other factors such as the Event Code in the IF-041 ([ReadingRemv], [ReadingInstl], [ReadingEnergisationChg], [ReadingCOR], [ReadingOnSite], [ReadingCOS], [DSEstimate], [SupplierAgreedCOS], [ReadingOverride], [ReadingRemote])? | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Reading methods do not apply to Register Readings - not sure if question is valid therefore recommendation for DIN to be closed. |  | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-201 |  | 2023-03-24 | ESG | 3529 | Patricia Parker | Software Provider |  | IF-033 Validation for population into the IF-034 The receiving party business validation rules state “Each Service Provider will need to determine their own validation criteria when processing Appointment Requests. The list below is intended to cover a number of potential possibilities based on the data items made available, and not to suggest that Service Providers needs or should perform such validations.” But should the DI-143 ‘Service Provider Proposed Appointment Response Code’ not form a valid set list (ENUM Vals) in the Data Catalogue so that all parties are working to the same list of applicable codes, rather than this field being a string with a length of 200 field? | Closed |  |  | 2023-06-23 | IF-033 has been updated as part of Interim Release 1 and the ENUM Vals will not be updated this is because we will have dynamic error messages which cannot be enumerated. |  | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-202 |  | 2023-03-24 | ESG | 3513 | Patricia Parker | Software Provider | Operational Choreography 60 minute turnaround | Registration Responses in connection with the PUB-31 given the NFS requirement is a 60-minute turn-around time. Within the Operational Choreography there is requirements OPC-140: From our understanding this means that when suppliers receive the PUB_032 from the Reg Service rejecting the appointment Request suppliers then have 60 minutes to re-issue a fresh IF_031 appointment. For example, there is a rejection code for 'CSS Reg ID not known', this would suggest that a party is out of sync and would need investigating especially as in this case, the REG ID would have previously been provided on PUB- 002, DI-849 and CSS is the master of the REG ID and not the Registration Service. | Updates Ready to Release |  | Interim Release 2 | 2023-06-23 | Added suggested text to Ops Choreography. Suggested text is "It is noted that some requests may require manual work and may be as a result of incorrect appointments from the Supplier. The expectation will be 90% of requests are systemically processed within 60 minutes with the residual being processed by the end of the following working day". | Doc Ref correction | Supporting Docs | Operational Choreography | MHHS_OPC001_Operational_Choreography
MHHS-DIN-203 |  | 2023-03-24 | CGI | 3502 | Chris Beard | Software Provider | mapping of Estimation Reason Codes to estimation Methods | MHHSP-METH001 M-13. Can you provide a definitive mapping of Estimation Reason Codes to estimation Methods? For example, LTV to Method 11. When should an SDS use Estimation Codes such as Opt Out, Comms. Fault. | Updates Ready to Release |  | Interim Release 2 | 2023-06-23 | Updated METH001 section 7.3 to reflect Estimated Methods to Estimated reason codes | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001
MHHS-DIN-204 |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | De-energised sites | MHHSP-METH001 M-3. Which estimation Method should an SDS use for de-energised MPANs that would result in an estimation code of ‘De-Energised’? Without a specific Method statement to cover de-energisation, we will end up estimating consumption. | Updates Ready to Release |  | Interim Release 2 | 2023-06-23 | Added Method 13 to reflect de-energised sites. | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001
MHHS-DIN-205 |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | Removal of Estimation Reason Code "Disconnected" | Can you confirm that the Estimation Reason Code ‘Disconnected’ will be removed from the table in 7.3? | Updates Ready to Release |  | Interim Release 2 | 2023-06-23 | Removed "Disconnected" from Table 7.3 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-206 |  | 2023-03-27 | St Clements | 3703 | Anna Davis | Software Provider |  | Within the MHHS-E2E001 - End-to-End Solution Architecture, there is reference to MHHS-E2E003-Physical Interface Specifications in 1.3 References section This should be labelled as MHHSP-DES138-Interface Catalogue | Implemented |  | Interim Release 1 |  | Updated 1.3 reference section | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-207 | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body |  | There is ambiguity within the design on when agent appointments should become effective, which means that different participants have a different view on when agent appointments should become active. | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 |  |  | Migration |  | BP001 & BPD001 BP002 & BPD002 BP003 & BPD003 Migration Design
MHHS-DIN-208 | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body |  | Within the existing Migration Design, it is stated that the Registration Service should reject all Legacy messages for a given MPAN once a Forward Migration has been initiated for said MPAN. This would prevent a legacy MOP from sending the relevant legacy flows if they need to change a meter when an MPAN is mid migration | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 |  |  | Migration |  | Migration Design Document
MHHS-DIN-209 | Design Team | 2023-03-30 | Design Team |  | Sean Cooper | SRO Design Team |  | ~ Level 1/2 Error Code "MSG0000 - Success" Added to Interface Intro Section ~ MSG0018 - Timestamp cannot be future removed and explainatory note added to IF Notes Section of DIP Common | Implemented |  | Interim Release 1 |  | Updated actioned in v5.1.1 of IF Doc. This relates to MSG1008 not MSG0018 as originally given in the design issue. MSG0000 Success added. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-210 | Design Team | 2023-03-30 | RECCo |  | Sarah Jones | Consultancy |  | Possible change flagged The original view of the Design Team was that this flag and associated info (ie Is a Customer Direct contract in place, who is the DS/MS with that contract, but not the Eff To Date aka Contract End Date) should be visible to incoming Suppliers, for exactly the reasons you suggest i.e. so that in an incoming supplier could factor the existence of a CDC(s) into their acquisition process / pricing etc. I think we also felt that SP’s who weren’t currently appointed, but may have signed a new CDC should also have the ability to set the flag, as it’s the sites that are part of a CDC, but where that SP isn’t the appointed SP that are the most difficult to coral and manage. The position at the moment is that the existence of a CDC would be shared with incoming Suppliers as part of PUB-002, however this would likely be too late in the process to provide the assistance and support required to an incoming supplier (on all aspects of the sale, contract/price in particular) … … therefore, I think it was also envisioned that information about CDC’s would be available via ECS – so prospective suppliers could check in ECS on the CDC position as part of the other pre-acquisition checks they may undertake. Therefore, I think the decision on exactly what information is shared ‘pre-acquisition’ to participants probably sits with yourselves (RECCo) to finalise as part of your ECS Design / DP Assessment. All information in relation to CDC’s will be passed/made available to ECS via receipt of a copy of PUB-039, so what item(s) are displayed and to what parties I think would get covered off as part of that ECS Design activity. | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12
MHHS-DIN-211 | DI-139 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-009 Event Code is referred to as [CSSDeRegistration] in the population notes and swagger open API spec but then B042 block title references event code CSS Deactivation, B042 should reference CSSDeRegistration. | Implemented |  | Interim Release 1 |  | Update B042 to reference CSSDeRegistration | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-212 | DI-140 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | MHHSP-BP007-Disconnection-v5.0 is missing IF-050 being sent out on a change to MPAN/RMP Status | Implemented |  | Interim Release 1 |  | to BP007 and BPD007 Requires a flow from Registration Service to EES (IF-050 to DIP, a Publish Change to MPAN/RMP Status process, a PUB-050 from DIP to EES process Receive Change to MPAN/RMP status) starting at step 70 (disconnection). Plus add new step descriptions to the BPD and amend Step 70 description to include IF-050. | Process Model correction | Metering Changes |  | MHHSP-BP007-Disconnection, MHHSP-BPD007-Disconnection
MHHS-DIN-213 | DI-141 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Data item 997 in S1 common block is senderId in swagger hub, but senderDIPID in data catalogue | Implemented |  | Interim Release 1 |  | Update swagger to reflect senderDIPID to align to data catalague | Technical corrrection | Technical Artefact | Swagger | JSON,YAML
MHHS-DIN-214 | DI-142 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | REG Notes section Queuing of Prospective Appointments Rule 4 ** Rule 4: If App Scenario = 'SEG' and Supplier ID + Appointment Service Start Date = Existing Supplier ID + Service Start Date > (Service Start Date +2 working days) >> Appointments meeting Rule 4 have missed their opportunity, and will be 'Lapsed' (PUB-035) This rule doesn't make logical sense, needs correcting. What is the intended logic to be applied here? | Implemented |  | Interim Release 1 |  | Update to align with validation rule | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-215 | DI-143 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 for event code [MeterRemoval] rule REG1002 Sending Metering Service ID [SO.SenderID] is currently appointed OR held a valid appointment for Meter Installation Date [DI-057] This should read removal date not installation date | Implemented |  | Interim Release 1 |  | Updated validation rule REG1002 in IF-005 for event code [MeterRemoval] to refer to Meter Removal Date (DI-058) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-216 | DI-144 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-144 On IF-005 MPRS will validate Either current, queued SEG or previous MS If previous and not within 10 working days will reject with REG1003 If not previous, and not current or queued, will reject with REG1027 MPRS will then validate if install date/removal date is within MS period of ownership If not will reject with REG1019 REG1019 need correcting to also include <ETD to apply for previous MS It’s not possible to get a scenario where the If-005 passes the above rules (REG1003, REG1027 AND REG1019) but fails REG1002. Therefore REG1002 is not needed and will never be sent as a rejection code. (Add to DI-43) | Closed |  |  |  | Agreed with SCS that no further change is required | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-217 | DI-145 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | On IF-005 REG1019 should also include validation that the installation/removal date concerned is <=Effective to date (ETD) of MS period of ownership | Implemented |  | Interim Release 1 |  | Updated IF-005 validation rule REG1019 to include validation that the removal/install date must be <=Effective to date (ETD) where the update is being provided by previous Metering Service (using their 10 day window) for MeterRemoval, MeterInstall and MeterExchange events. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-218 | DI-146 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 for event codes [MeterExchange] and [MeterRemoval], the rule should not reference DI-056 which is the meter ID in the installation block, it should should referenced DI-053 which is the meterId in the removal block | Implemented |  | Interim Release 1 |  | Rule updated not to reference DI-056 which is the meter ID in the installation block, it now references DI-053 which is the meterId in the removal block | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-219 | DI-147 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 - for other event codes removal date must be >= to Install date but for [MeterUpdate] the rule states > meter install date. Should be >= | Implemented |  | Interim Release 1 |  | Update rule for [MeterUpdate] to align to other removal date event codes | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-220 | DI-148 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1007 unecessary and will never be triggered, it is already covered under REG1001 cannot submit meter install if MPAN is disconnected | Closed |  |  |  | Valid rule to left in as-is but noted cannot be SIT tested | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-221 | DI-149 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In the IF-005 guide it states: "When amending the Installation and/or Removal date of a Meter, a supporting MAP history commencing in line with the revised Installation Date must also be provided. Any additional MAPs should be provided in chronological order, each with a ‘MAP Effective From Date’ greater, by at least one day, than the previous." MPRS will accept if the install/removal date is changing AND the MAP History has not been included, there is no requirement in Interface Catalogue or Registration Requirements to reject if MAP history is not provided. | Closed |  |  | 2023-06-23 | Believe covered by MeterHistoryUpdate rules, but hopefully won't be an issue pending agreement on MAP discussion… IF-005 use case guide will be updated with outcome. DRG has agreed to remove MAP history therefore in lieu of this decision, this change will not be required. Closed | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-222 | DI-150 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | sarah | Implemented |  | Interim Release 1 |  | Updated wording to match existing validation. Guidance only now provided | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-223 | DI-151 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005: Need REG1006 to apply to all event codes, e.g. Meter Update on a change to removal date, will need to check that the removal date does not lead to non unique Meter IDs (overlapping dates) MPRS will reject with REG1006 in this scenario | Implemented |  | Interim Release 1 |  | Added REG1006 validation checks to MeterHistoryUpdate and MeterUpdate events. | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-224 | DI-152 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 Interface Note below could be read as MeterUpdate event code can be submitted by previous or prospective MS which is not correct "Only the Appointed Metering Service, and for a small window (10 days) to allow for delayed notification of field activities the previously appointed Metering Service; and an incoming Metering Service with a Prospective 'SEG' type appointment may send an IF-005 and update metering details. The [MeterHistoryUpdate] may only ever be used by the Appointed Metering Service. Interface Design assumes that two separate meters with the same 'Meter ID' cannot be installed at the same time. " | Implemented |  | Interim Release 1 |  | Updated | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-225 | DI-153 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | DI-849 CSS Registration Request Id does not have a YAML name in the interface catalogue In the swagger hub, the corresponding name is CSSSwitchID which is misspelt | Implemented |  | Interim Release 1 |  | Updated Data Catalogue to CSSRegistrationRequestID, Swagger to follow | Data interface correction |  | Interface Catalogue Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-226 | DI-154 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In MHHSP-BPD007 - Disconnection v5.0, the ordering of the steps are out of order. Steps 140, 145 and 150 are for parties receiving the de-appointment notification from the Registration Service, but this is not sent until Step 155. Step 155 “De-Appoint Services” needs to be before Step 140 “DS De-appointment Notification”. Also Step 145 “Receive De-Appointment Notification” is DIP receiving the de-appointment notification to send on, this needs to be after Step 155 and before Step 140 . The ordering should be: • De-appoint services (155) • Receive De-Appointment Notification (145) • DS De-Appointment Notification (140) • MS De-Appointment Notification (150) | Closed |  |  |  | No plans to change step numbers as long as they are unique | No Change |  |  | BPD007
MHHS-DIN-227 | DI-155 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1.xlsb, the validation for REG1003 – “Metering Service ID [S0.SenderID] post appointment update period for MPAN [DI-063] has expired” is currently set to “Metering Service [S0.SenderID] holds valid previous appointment then [System Date] should be < [REG.App End Date] + 10 working days”. Should this be <= to allow for the full 10 days? | Implemented |  | Interim Release 1 |  | Changed to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-228 | DI-156 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 - IF-005 has the following error for [MeterExchange] & [MeterInstall]:- “REG1020 - MAP Effective Date [DI-054] cannot take place in the future” Should this validation also be valid for [MeterUpdate] and [MeterHistoryUpdate]? | Implemented |  | Interim Release 1 |  | Added to meter update for removal date. Added to MeterUpdate and MeterHistoryUpdate for MAP effective date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-229 | DI-157 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 does not have a rule that the SMSO EFD must not be prior to the latest SMSO EFD. We are implementing this rule with error code REG1019 | Implemented |  | Interim Release 1 |  | We are implementing this rule with error code REG1019 Make consistent with others ( PC and ssc + 1 ). Review IHD and SMSO | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-230 | DI-158 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 & IF-005 do not have a rejection code where the IHD is invalid. | Closed |  |  |  | DIP will reject non-valid values - no change to docs required | No Change
MHHS-DIN-231 | DI-159 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-005 - There is no validation on Meter Removal date [DI-58]. This should be mandatory non nullable for [MeterRemoval],[MeterExchange],[MeterUpdate], but mandatory nullable for [MeterHistoryUpdate] to allow for reinstating a previously removed meter. Currently in redlined v5.1, this data item is optional and non nullable. | Implemented |  | Interim Release 1 |  | Meter Removal changed to nullable, block conditionality updated | Missing/incorrect validation rule | Metering Changes | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-232 | DI-160 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-160 on the interface catalogue DCC Service Flag validation rules are specified in IF-025, but DCC Service Flag is not received in this interface. Needs removing. | Implemented |  | Interim Release 1 |  | not needed rules removed. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-233 | DI-161 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 – IF-025, where the event type is [ConsentGranularity] Error Code - REG1019 - Consent EffectiveFrom Date [DI-018] must be within Suppliers period of ownership Test Condition - Consent Granularity EffectiveFromDate [DI-018} must be < [Reg.CurrentSupplierEndDate] if exists Should this be <= as it could be on the end date? | Implemented |  | Interim Release 1 |  | Updated to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-234 | DI-162 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Registration Services Requirement MHHS-BR-RS-021 should be amended to: Registration Service must, where more than one Metering Service appointment request is received from the same Supplier for the same MPAN CSS Registration Request ID, and for the same date, take the last received Metering Service appointment (based on the Sender timestamp) as containing the correct information. Any earlier appointments should be lapsed. To allow multiple queued service appointments for the same registration will be overly complex to design, code and test, and is likely to cause confusion and issues in live operation. It is much simpler and cleaner to only allow one queued service appointment at a time, per registration. This would still allow the Supplier to replace a queued appointment that's incorrect. The Supplier could submit further changes once the first change has completed, if there is a genuine case of multiple changes to SP in a short period of time. It would not impact on CoS. Our proposal is to allow one pending queued appointment per registration, so could have a queued appoint on current registration AND queued appointment on CoS registration at the same time. | Implemented |  | Interim Release 1 |  | Updated MHHS-BR-RS-021 to refer to CSS Registration Request ID. Added REG1089 - Subsequent appointment received as an error code in the interface spec | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-235 | DI-63 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Original wording:- In the business process diagram for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 Update required:- Please close this design issue as CSS0700 is the correct reference for update of status. | Closed |  |  |  | DUPLICATE OF MHHS-DIN-63 | No Change
MHHS-DIN-236 | DI-163 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, 02-DIP-COMMON - R0 response - DI-980 Response Message has been updated in Swaggerhub to be an array, but this is not clarified in Interface Spec. DI-979 Response Code should not be an array. | Implemented |  | Interim Release 1 |  | Added note in Introduction section to confirm that DI-980 can be an array Agreed DI-979 Response Code is not an array | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-237 | DI-164 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-034 S0 DI-999 Event Code option of [DSAppSPRepsonse] is misspelt. This is also misspelt in Swaggerhub. This could cause differences between systems and should be corrected to [DSAppSPResponse] | Implemented |  | Interim Release 1 |  | Updated typo in IF-034 DI-999. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-238 | DI-165 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation on MS/DS EFD being within permitted advanced period. This is covered under migration document but not implemented as a validation rule for IF-031. MHHS-DEL961 Migration Design Document section 6.1.1: For the purposes of the CoA Migration process, the below business rules should be followed by Suppliers regarding the lead time between the submission date of the IF-031 and the requested effective from date of the Migration. a. An effective from date from Same Day +1 up to a maximum of 28 calendar days (inclusive of the 28th day) in the future is permissible. | Implemented |  | Interim Release 1 |  | 28 Day in advance rule added to if-031 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-239 | DI-166 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Requirement MHHS-BR-RS-134 states MPRS must automatically de-appoint the MS & DS when the Market Segment Indicator changes to NO. Is this the intended design? | Implemented |  | Interim Release 1 |  | Removed reference to Market Segment Indicator from the requirement MHHS-BR-RS-134. | Requirement correction | MPAN Ownership | Market Segment | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-240 | DI-167 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Current validation on IF-031 Rule REG1037 will mean MPRS will lapse any appointment where the system date is greater than appointment EFD + 2 working days. This means if a SEG change fails, and the supplier tries to resubmit the SEG change, with EFD more than 2 working days in the past, MPRS will immediately lapse the appointment. If there is a need to allow retrospective SEG changes, more than 2 working days after EFD, then the wording will need to be amended to apply to max(EFD+2 working days, MPRS system date on receipt of IF-034 + 2 working days) | Implemented |  | Interim Release 1 |  | Introduction of Lapsed Response Codes and Rules in IF-035 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-241 |  | 2023-02-01 | C&C | 3430 | Graham King | Software Provider |  | IF/PUB-018 message with event codes [AddressChg] and [DUOSTariffIDChg]. According to Interface Catalogue routing rules, these events are not communicated to the LDSO role via the PUB-018. We assume that the assumption here is that because these data items are mastered by the LDSO that all internal LDSO systems share this data. This is unlikely to be the case. DUoS billing systems co-exist alongside other LDSO management software and are often supplied by different vendors. They do not and cannot share data sets. Given this real-world separation, would it be possible to make the PUB-018 message available to LDSO in the list of Secondary Routing paths? The alternative would mean developing communication channels between disparate systems, from potentially different software vendors in order to pass information from one to the other. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09
MHHS-DIN-242 |  | 2023-04-04 | ESG | 3713 | Patricia Parker | Software Provider |  | How will the Metering Service be kept informed of who the currently appointed Data Service are? On BP003 is shows the Metering Service being a recipient of the PUB_036 when a DS appointment becomes effective, however looking at the routing rules in DES138 it does not show ‘MSSC’ or ‘MSAC’ as being recipients? | Closed |  |  | 2023-06-23 | Close - changes to Secondary routing make this DIN Moot - Ref DIN-268 | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-243 |  | 2023-04-05 | Change Request |  |  | Programme | CR-015 E7/E10 Off Peak Consumption Solution | CR015 - Differential Settlement for E7 / E10 Meters for Smart Opt-out customers | Requires Industry Work Group review | 2023-06-15 | Interim Release 3 | 2023-07-12
MHHS-DIN-244 |  | 2023-04-04 | British Gas | 3874 | Neil Strange | Supplier |  | D0275: Until v0.3 of DES196 was released our understanding was that the D0275 would be retained and it’ use was optional. We are feeding this back on the D-025 consultation but don’t want to lose sight of this. Its removal will impact our billing systems and substantially drive up implementation costs. The baselined IF-021 also does not handle the clock change | Closed |  |  | 2023-06-23 | Alignment with D0275 D0275 is not part of of the baseline design requirements. If you require this, it is by mutual agreement between parties. NO change required, only clarification. | No Change
MHHS-DIN-245 |  | 2023-04-01 | Avanade/ Design Team |  | Grant Sutcliffe | Software Provider | Transaction ID and Correlation ID increase field length to 60 | Transaction Id Could the length specification of the TransactionId be increased to be a max length of 60. The need for this is to cater for a 16 character length hex value (increasing from current length of 6 characters]. This would ensure that we achieve uniqueness. It will also provide headroom for any length increase in other Transaction Id constituents, such as Role. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: T-041-1234567890123-SUP-20230220-619C1F6967838002 [Length = 50] Example from DES138 spreadsheet: T-006-1234567890123-SUP-20220401-1234CC [Length = 40] Correlation Id Could CorrelationId length also be increased to 60 max length of 60 - for the same reason. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: CI-BP-011-20230222-619E0BD1D1FD9000 [Length = 35] Example from DES138 spreadsheet: CI-BP-011-20230222-1234567890123 [Length = 32] | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated DIP Transaction ID and DIP Correlation ID to String 60 in Interim Release 1. The examples have been updated to reflected MHHSP-DES138-Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-246 |  | 2023-04-12 | Change Request |  |  | DCUSA |  | CR019 - Replacement of D0242 D0315 for MHHS | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 |  |  |  | Interface Catalogue
MHHS-DIN-247 | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Update to the Core Design Interface Catalogue (MHHSP-DES138) is required to include the addition of IF-003 | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | IF-003 defined as part of Migration baseline The structure of the IF-003 will be updated to include ‘Incoming Supplier Details.’ The two new data items within the ‘Incoming Supplier Details’ will be: RevMig Incoming Supplier MPID RevMig Incoming Supplier Effective From Date Business Rules: In the case of Smart Meters undergoing Reverse Migration only, the Registration Service will populate the ‘Incoming Supplier Details’ as part of the IF-003 which is sent to the outgoing MS (via the DIP). This is so the outgoing MS can correctly route the Skeleton D0150 to the new Supplier (which in turn enables the new Supplier to generate a D0367). If the D0205 is not sent to the Registration Service before the IF-003 is issued, the data fields used to confirm the identity of the DC and MOP will be blank; no default values will be populated. In this case, the DC and MOP will need to contact the Supplier to initiate a manual transfer of data. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-248 | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Updates to the ISD Entities document (EDI021, v5.0) | Closed |  |  |  | To be picked up as part of Migration IA - - new DIN will be raised as required. |  |  |  | EDI021
MHHS-DIN-249 | Migration Design | 2023-03-27 | Migration Design |  | Matthew Breen | Programme |  | Discussion around the use of BST/UTC during Migration | Closed |  |  |  | DIN is not specific enough.
MHHS-DIN-250 |  | 2023-04-06 | Design Team | 3764 | Steve Weston | Programme | Participant ID 10 digit number | This is related to ticket 3764, to update the Interface Specification to ensure the Participant ID is clearly defined as a 10 digit number [0-9] only, and the examples in the Interface Specification align to this, including where this is used as part of the sender unique reference and the examples shows 11 digits, not 10 digits for Participant ID. | Initial Assessment/Updating |  | Interim Release 2 | 2023-06-23 | In E2E001 doc Section 4.2.3.2 Section 4.4.4.2 example code for Sender unique Ref and in Transaction ID Section 4.5.5.3 as above DES138 doc Data Catalogue tab: DI-990 example and DI995 Example DIP common tabl DI995 example and the example JSON block (the above easy to change) ALL the IF tabs the JSON block example the Sender Unique Ref contains Participant ID and in every example its longer than 10. JSON/YAML Files: Update JSON examples where Sender Unique Ref and Transaction ID contain a Participant ID example longer than 10. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 Solution Architecture MHHSP-DES138-Interface Catalogue JSON/YAML files
MHHS-DIN-251 |  | 2023-04-06 | Design Team | 3860 | Steve Weston | Programme | IF-041 Population | This is related to ticket 3860, to update the Interface Specification to provide more clarity / notes on the optionality of B064 and B065 blocks in the IF-041 interface. This is in relation to notes / detail about which blocks are mandatory (from a contractual perspective) versus what should be included in the message if the data exists. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updates the notes section of IF-041 in order to provide guidance on the minimum population of B064/B065 blocks. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-252 |  | 2023-04-06 | Centrica | 3661 | Neil Strange |  |  | We believe there is a Design Gap at Change of Agent and Change of Supplier for Smart Meters which also impacts Migration. Neither the Registration Service, Metering Service nor Data Service will know how the registers are set up and specifically which are active. Consequently the Data Service will not know which registers to send on the IF-041, nor will there be able to calculate consumption correctly without knowing the register set up. The interface catalogue for IF-041 states in respect to this “B065 Block Below Repeated for each set of Configured Register(s) for each Meter” – we do not believe there is a way to give the DS this information. The supplier will set up the smart meter configuration to enable the registers to capture the usage for certain time periods. There is currently no way for the supplier to inform the DS which registers are active at what time of the day - the DS cannot accurately calculate the consumption breakdown based on the reads when there are multiple registers configured. | Closed |  |  |  | DIN closed, Design Team to send email recommending for a CR to be raised.
MHHS-DIN-253 |  | 2023-04-12 | British Gas | 3769 | David Hipwell | Large Supplier | Volumetrics | The latest E2E Functional and Non-Functional Requirements MHHS-E2E Requirements V3 which went to V3 on 16/02/2023 appears to focus on message counts and response times. For example:- During transition all meter points (ca. 31M) will be transition between the old and new services. Therefore assuming a linear migration over the year this would result in the load below, hence services shall be capable of processing the following volumes: - average daily volume of 680,000 - peak daily volume of 2.4M 5.0M - annual volume of 248M 500M Analysis of the flows needs to be categorised across all impacted market participant roles including the DIP. Only then will it have meaning for all parties. The calculation needs to take account of the migration period using the MHHS migration volumes according to date (including REVERSE migration). These should be in both message counts and also sizing (e.g. Gb). And include for a BAU day and also migration days. Whilst some calculations can use the total number of MPANs, to be useful these need show also at perhaps for a million MPANs in each role. Only then will all parties be working on a single set of figures. A line in the sand. The NFRs that exist appear to have moved away from any form of technical calculation towards business process figures. But these figures need to go as an input into technical sizing’s, and should have done for DIP – can these be produced and published ? | Initial Assessment/Updating |  |  |  | Recommend Close - This is being picked up by the Migration and Transition working group
MHHS-DIN-254 |  | 2023-04-17 | Siemens | 3044 | Tony Mason | Metering Service | Update of Consent, DPI, etc. | this does surprise me and doesn’t seem to correspond to the routing rules in the Interface Specification. A proposed Data Service is not included in the routing tables for the receipt of a PUB-018, for example. I would therefore expect that if a change to DPI occurs between PUB-033 and PUB-036 the proposed Data Service could only be notified on a revised PUB-033 with the Appointment Scenario set to whatever the original scenario was set to – “SEG”, “CSP”, or “COS”. | Closed |  |  | 2023-06-23 | Ref notes on the maintenance of these data items in the Regi Info Section of the I/F document. Prospective SPs are not notified of changes to these data items during their prospective period. If these Data items change then the supplier should re-evaluate the SP they have proposed and change the appointments as required. If an SP takes on a supply with different elements/factors to those suggested by the supplier at appointment this is a contractual issue between the SP and the Supplier.
MHHS-DIN-255 |  | 2023-04-17 | Elexon | 3983 | Kate Goodman | Testing | Consumption on De-Energised MPAN (IF-013/IF-014) | ConsumptionOnDeEnergised is an Event Code mentioned in the list of data items but is not present in header where the routing info is held - needs to be added to header | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | ConsumptiononDeEnergised event moved from IF-013 to IF-014 and added in routing rules | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-256 |  | 2023-04-17 | Elexon | 4169 | Kate Goodman | Testing | IF-014 Block B067 | DI-015 is mentioned in the header wrt routing but is not present in the message itself. It either needs to be removed from header or added into message. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Block B067 added to IF-014 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-257 |  | 2023-04-17 | Elexon | 4172 | Kate Goodman | Testing | B053 repeating block | B051 is a block which repeats for each combination of Load Shape Criteria (denoted with single chevron to show repeat). B053 is another repeating block which is denoted by two chevrons, implying it is nested below B051. But in fact it also repeats for each combination of Load Shape Criteria. Should this just have a single chevron or is there further information that needs to be added to make its double chevron make sense? | Closed |  |  | 2023-06-23 | No change required as there will be multiple B053 in each B051 block. | No Change |  |  | none
MHHS-DIN-258 |  | 2023-04-19 | ENWL |  | Paul Band | Network Operator |  | There are a number of requirements in the MHHS-BRS005-LDSO document which state that we must obtain various registration data via the DIP and maintain records accordingly such as: MHHS-BR-LD-001-005, MHHS-BR-LD-024, MHHS-BR-LD-030 and MHHS-BR-LD-034 Extrapolating these into requirements for our own systems suggests that we should build databases/tables to store this data and maintain it The requirement is placed upon us as a party under the assertion that all settlement related data should be exchanged between services and parties via the DIP. However LDSO’s are unique in that their data exchange for their party type is split and is typically split by system under these party types. As a consequence we already communicate directly with MPRS as it is already part of our system architecture as a paid for and created service by LDSO’s. | Requires Industry Work Group review | 2023-06-29 | Interim Release 4 | 2023-08-09 | Discussion at the DRG of the 27/4/23 did not agree on the development of a New Design Principle, A further workshop with LDSOs needs to take place to discuss alternate options and confirm agreement amoungst all DNOs & IDNO on the receipt of publication
MHHS-DIN-259 |  | 2023-04-20 | ESG | 3756 | Patricia Parker | Software Provider | BP003C correction | On BP003C under the CoR section there is a note which states that the readings that pass validation should have Meter Reading Status (J0047) set to ‘T’ and when it has failed set it to ‘F’. However as per the REC the group which houses the J0047 group (032 – screenshot below) should only be present where the Meter Reading Flag (J0045) is set to ‘F’. I have checked DES196 and cannot see that the conditionality for that group is changing in the D0010 therefore I can only assume that the note on the process map is incorrect, and it should be talking about the J0045 value instead. Please can you confirm? | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Modification to Note on process to refer to "Meter Reading Flag (J0045)", modify flow label to step230 to "(Read Flag = "T")" | Process Model correction | Metering Changes |  | MHHSP-BP003C-Transfer of Reads
MHHS-DIN-260 |  | 2023-04-20 | CGI | 4167 | Dave Webster | Software Provider |  | Swagger definition does not match DES-138 in version 1.0 or 1.1. | Closed |  |  | 2023-06-23 | No specific detail provided, however comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1, therefore closed
MHHS-DIN-261 |  | 2023-04-20 | Utiliteam | 4245 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. Configurable Register Reading Date/Time is missing. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-262 |  | 2023-04-20 | Utiliteam | 4214 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. B070 for IF-031 is wrong. It contains the word DIP in the Swagger, which is not included in DES-138. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-263 |  | 2023-04-21 | CGI | 4203 | Dave Webster | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. DI-122-Profile-Class is defined as an integer, but in DES138 it is defined as a string length 2. Needs to be updated in the Swagger. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Swagger and Data Catalogue aligned to String 2 for DI-122 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-264 |  | 2023-04-24 | Elexon | 3946 | Rashmi Radhakrishnan | Central Body |  | One of my colleague pointed out a typo in the CCC method statement attached, and I would like to draw your attention to it and requesting to make necessary amendments. The CCCID starting from 100 to 107 has Market Segment Indicator as “U” and Connection Type Indicator shown as “W”. We think that, for these line items the Connection Type Indictor need be corrected to “U”. For reference please see below picture and this also aligns with ISD entity spec v5.0 (M2 entity). CCC ID Market Segment Indicator Measurement Quantity Consumption Component Indicator Connection Type Indicator 100 U AI C W 101 U AI L W 102 U AE C W 103 U AE L W 104 U AI C W 105 U AI L W 106 U AE C W 107 U AE L W All 'W's' should be 'U's') | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 |  |  |  |  | CCC Method Statement
MHHS-DIN-265 |  | 2023-04-25 | Elexon | 4128 | Rashmi Radhakrishnan | Central Body |  | ISD entity M5 has a filed Settlement Period quality indicator. Is this the complete valid data set for the field Settlement Period quality indicator? I took this below list from interface catalogue v5.0. A = Actual, E= Estimate (UMS Only) A1,A2,A3, AAE1,AAE2,AAE3,EAE1,EAE2,EAE3 (ADV Only) E0 --> E9 = Estimation Method 1 - 9 ZE = De-Energised ZE1--> ZE3 = Zero Estimation Method 1 -3 but the Advanced Data Service Estimation Method Statement has data flags EA1 till EA13 which is not mentioned in the above list. Also, the ISD entity spec M5 example below shows a different data item that is not in the list at all for Unmetered(104 &105). Is this a mistake? | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | The Freshdesk ticket details redlined changes have been made to the DES240 document
MHHS-DIN-266 |  | 2023-04-26 | ESG | 3899 | Patricia Parker | Software Provider |  | If the D0300 process is not changing then we believe that DES196 is incorrect and should show added routes to allow the Supplier to send a D0300 to the Data Service Matt M has confirmed - We are working through the exchange of CoS readings as the code drafting has raised some questions about the extent to which the SDS is involved in the D0300 process. For smart meters, the SDS will not have any use for the billing register readings so D0300 process should not apply, or at most could only be missing the total cumulative. However, it likely will still be required for traditional meters. On that basis, I think we can acknowledge that the D0300 will be retained and SVs created for Supplier to SDS for traditional meters. The process for smart meters is being discussed internally as the SDS does not retrieve tariff register readings. There will be an updated version of DES196 issued in the next few weeks to reflect feedback from the DTN flow part 2 consultation issued in late March which will reflect the retention of the D0300. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 |  |  |  |  | MHHSP-DES196- D-Flow and Interface Mapping
MHHS-DIN-267 |  | 2023-05-02 | ESG | 4385 | Patricia Parker | Software Provider | RegX Validation Issue | RegExpression on the DI-148-Annual-Consumption use of DT-016-Decimal-9-3 in the 1.1 swagger spec. This needs to be updated to align with DES-138 example of 123456789.123. Regex should be ^-?[0-9]\d{8}(\.\d{3})?$ instead of ^-?[0-9]\d{7}(\.\d{3})?$ | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Swagger v1.2 has been updated accordingly | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files
MHHS-DIN-268 |  | 2023-05-03 | SRO Design |  | Sean Cooper | SI Design | Secondary Routing | It was always the intention to revisit and revise all of the Secondary Routing configuration as part of DIP Detailed Design. Completion of this exercise has also resulted in some changes to other routing parameters. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Following discussion with Avanade the Secondary routing short codes have been simplified and the routing of each IF revisited based in these revised short codes. These are shown highlighted in BLUE in the routing section of each of the individual IF pages. | Technical corrrection | Supporting Docs |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-269 |  | 2023-05-03 | St Clements | 4424 | Anna Davis | Software Provider | Swagger Alignment to DES-138 | We have also realised that there are a large number of discrepancies for each interface between the data item name in Swagger vs the YAML name in the Interface Catalogue Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated inconsistencies in the Interface Data Catalogue and Swagger. Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-270 |  | 2023-05-05 | SRO Design | 4557 | Rob Golding | SI Design | Correlation ID | Provide further clarity on how Correlation ID's work. This will impact numerous artefacts including DES-138 and E2E001 | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | DES-138 Interfaces updated to reflect correct 'COPY / CREATE' property on IF routing tables. Updated the E2E001 design document with a more detailed worked example in section 5.4 that details how and where the Correlation ID is populated. | Design Ambiguous | Supporting Docs |  | MHHSP-DES138-Interface Catalogue. E2E001.
MHHS-DIN-271 |  | 2023-05-10 | ESG | 4541 | Patricia Parker | Software Provider | Swagger Alignment to DES-138 | S0 and S1 is Mandatory in DES-138 v5.1.1, but is not marked as mandatory in the Swagger 1.1. Swagger needs to be updated to align with DES-138. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Swagger 1.2 updated so all SO and S1 blocks are mandatory as per DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-272 |  | 2023-05-10 | SRO Design | 4656 | Rob Golding | SI Design |  | Required to DIP Channel Publication (v1.2 of the swagger) that will allow DCPs to register webhooks on behalf of their clients | Closed |  |  | 2023-06-23 | Dupe of DIN-375
MHHS-DIN-273 |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | New MSN Data Type | MHHS Data Type - for Meter ID / Serial number for DI-053, DI-056 and DI-060 | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | New Data Type created in Swagger v1.2 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-274 |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | Missing YAML in DES-138 - DI-073, DI-074, DI-080, DI-111, DI-112, DI-190-194, DI-300, DI-021, DI-022, DI-060, DI-076 | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Missing YAML names for Data Items confirmed and added to data catalouge | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-275 |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | DI-093 / DI-120 - Data length 2,000 not 200. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | All additional info data items set to len 2000 in Swagger v1.2 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-276 |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Classifications | MHHS Data Classification - ensure all columns are populated for Public and Restricted ie, MPAN & Address (removall all NULLS). | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Data Classifications added v5.2.1 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-277 |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Owners in Data Catalouge | MHHS Data Owner - where there are NULL's, this should be updated so all columns provide an owner, mark as N/A (remove all NULLS). | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Data Owners added v5.2.1 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-278 |  | 2023-05-10 | SRO Design | 4590 | Rob Golding | SI Design |  | Please can DES138 Interfaces spreadsheet be updated to provide an indicator against each interface (or is it interface & event code) as to whether it can be opted in/out by a recipient. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | Subject to ongoing discussion with Avanade. Should be accomodated witin Secondary Routing Solution
MHHS-DIN-279 |  | 2023-05-12 | ESG | 4484 | Patricia Parker | Software Provider |  | The BP005 – Data Processing – Process map shows that when a Customer Own Read has been sent to the Data Service from the Supplier in the IF-041, EventCode = ReadingCoR, the Data Service will perform reading validation and issue the PUB-041 back to the Supplier, in the Read Sharing column of the process map. When the Data Service send back the validated customer own read in the PUB-041, what eventcode will they use and where can I find this documented? The previous response says “There is no IF-041 response, check consumption is as expected in PUB-021” is this correct for Customer Own Reads on Smart meters? The map shows otherwise so please can you confirm if the answer or map is correct and if the map is correct, provide information on what event code will be used. | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12
MHHS-DIN-280 |  | 2023-05-12 | ESG | 4552 | Patricia Parker | Software Provider |  | DES196 lists the D0386 (Manage Metering Points) as ‘not impacted’ owned by the REC however BP010 shows that the method of maintaining Related MPANs is via the IF_019 / PUB_020 process. Can you confirm whether the D0386 is going to be removed post- MHHS. If not, could you please clarify what process a Supplier should follow post- MHHS. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09
MHHS-DIN-281 |  | 2023-05-12 | St Clements | 4446 | Madison Layton | Software Provider | BP003 IF-35 flow | MHHS-BR-RS-053 for the incumbent MS to be notified on If-035 DSAppAccepted where meter is advanced or traditional is missing from BP003 business process diagram and steps | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | IF-35 flow from step 85 (if accepted where meter is advanced or traditional to Meter Service (incumbent) and additional step 86 to receive appointment response to BP003, and added step 86 and BR-RS-053 ref and details to step 85 to the BPD003 | Process Model correction | Metering Changes |  | MHHSP-BP003-Change of Service - Data Service, BPD003
MHHS-DIN-282 |  | 2023-05-16 | SIMS | 4821 | Martin Freeman | Software Provider | Status code removal | Status Code is included in the E2E001 design response body (4.4.4.2), when this is HTTP Response code and should be removed as this is defined in the callback response. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Removed from section 4.4.4.2 from the E2E001 design document as this is not required. This now aligns in Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-283 |  | 2023-05-16 | SIMS | 4826 | Martin Freeman | Software Provider | ID Capitalisation | ID should be capitalised in all places in the Swagger. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | All JSON names now have capitalised ID fields for Swagger 1.2. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-284 |  | 2023-05-16 | SIMS | 4828 | Martin Freeman | Software Provider | HTTP Response Code | HTTP Response code for success should be 201 in E2E001 as per Swagger. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Update made to E2E001 design document in section 4.4.4.1, 4.5.5.1 and 5.3 to align with Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-285 |  | 2023-05-16 | Elexon |  | Rob Golding | SRO Design Team |  | Add replay / requeue API for Swagger 1.2 to align with existing E2E001 Design. Add additional information / clarity in the E2E001 for Interim Release 2 to align changes between design and Swagger. | Closed |  |  | 2023-06-23 | Duplicate of DIN-374
MHHS-DIN-286 |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Issue clarification to Participants through DRG that all ECS Reports will be issues via Pattern B. Update of ECS Report Catalouge to reflect this. | Closed |  |  |  | The ECS reports will be via Pattern A. No change is required to the ECS reports
MHHS-DIN-287 |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Create & Issue guidance document on the distribution of ECS Reports. To Contain : - overview of Pattern B Process - Guidance on population of IF-047 - Update of IF-047 Event Codes | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-288 |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Update of Swagger with ECS Reporting Structures | Closed |  |  | 2023-06-23 | These interfaces are in place from Swagger 1.1.
MHHS-DIN-289 |  | 2023-05-17 | SRO Design Team | 4994 | Rob Golding | SRO Design Team | Interfaces for consumption replay | IF-015 / IF-016 - updates to E2E001 to provide clarification on design pattern. Alignments between DES-138 & Swagger alongside this. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | E2E001 design updated (Section 5.1.7) to provide additional information / clarity on these interfaces in relation to Consumption Replay. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-290 |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Proposal to change all / subset of ECS Reports to Pattern B | Closed |  |  |  | Duplicate | No Change
MHHS-DIN-291 |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | As a result of DIN-290 -- Where should the reporting assets be hosted?? DIP solution specified, but what are the other options are availible. Final solution option to be ratified and documentation updated. | Closed |  |  |  | Not hosted as via Pattern A | No Change
MHHS-DIN-292 |  | 2023-05-17 | St Clements |  | Madison Layton | Software Provider | ISD Entity M17 | Change required to ISD Entity M17 to add in Market Segment into the table - otherwise it cannot be used to derive consent values which was its original purposes | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | 1. Update Table name to "Consent Granularity Valid Combinations" 2. Added Market Segment as new table column 3. Update table to show all valid combinations | Process Model correction | Supporting Docs |  | MHHSP_EDI021_ISD_Entities
MHHS-DIN-293 |  | 2023-05-17 | Design Team |  | Paul Petitt | SRO Design Team |  | Retrospective DIN raised to ensure that any changes that are made in multiple downstream documents (for example CoCo, DIP Logical Design, DIP Physical Design & DIP Security Design) are reflected / updated in LDP assured documents to ensure e2e design / requirements alignment. This was agreed in a DRG Meeting in March 2023. | Implemented |  | Interim Release 1 |  | design changes to E2E001 End-to-End Solution covering points described in DIN details | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-294 |  | 2023-05-19 | ESG | 5030 | Luke Speakes | Software Provider | BP007 PUB009 flow | What I need to know is if the supplier will receive a PUB_009 with the Event code of [CSSDeRegistration] because nowhere on the BP007 process map does it show the supplier receiving the PUB_009 following a deactivation but on DES138 it shows the supplier as being a recipient of this event code. Step 95 (ringed below) shows the supplier as receiving the PUB_009 off the back of the Disconnection (event code [MPANDisconnection]) but then no where else on the process map does it have the supplier receiving a subsequent PUB_009 following the successful deactivation. Additional step required from step 130 (maybe 137?) to show both PUB-009 Mpan Disconnection and PUB-009 Deactivation going to supplier | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | BP007 change : There is already a flow from Step 85 to Step 95 for PUB009 for disconnection (no change) But need to Add a new step (137) for Receive Deactivation in Supplier lane from Step 130 for PUB-009 MPan deactivation in BP007 And there is already a PUB-037 flow from step 145 to Supplier step 157 for confirmation (so no change there) Addition of step 137 to BPD007 | Process Model correction | Metering Changes | Disconnection | MHHSP-BP007-Disconnection, BPD007
MHHS-DIN-295 |  | 2023-05-19 | SIMS | 4821 | Martin Freeman | Software Provider | L1/L2 Error Codes | Error code detail updates in DES-138 for Level 1 and Level 2 validation needs to be clarified | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updates made to Intorduction Tab of DES138 in order to clarify Lev1 vs Lev2 error codes. Design is such that participants should expect error code(s) at either level. Further ammendments could be made following Avande clarifications. | Data interface correction | Supporting Docs |  | DES138 Data interface Definition
MHHS-DIN-296 |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | It is envisioned that Configuration Management of ISD will largely follow the existing customs, practices and processes as are currently in place for managing MDD changes. However, DIN is required to formally confirm the Owner(s) and allowable update mechanisms (Standard or FastTrack) for each of the new ISD Entities outlined in the DIN. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-297 |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | What Participants are recognised in the existing / new ISD Participant tables…. How does this link in with the parties recognised by the DIP (and assigned DIP Roles / IDs …. Or Not) …. In particular how are MDRs referenced in ISD? Does this reference need to identify the ‘type’ of MDR? Also, there is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-298 |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider |  | As I understand it, you are advising we should A flag the consumption data (even though it isn’t Actual), until the zero charge code D0388 UMS Inventory is received from the UMSO. Therefore - if we have an inventory, regardless of the energisation status of the MPAN, we always use an A Flag. But as you’ve stated, this means an IF-013 will be issued to us as UMSDS, because there is A data, against a De-Energised MPAN. If this is the design/requirement then it is understood – but I would like to call out that this should be detailed within the UMSDS method statement – so I think a DIN is needed to get this requirement added? | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12 | UMS method statement |  |  |  | UMSDS Method Statement
MHHS-DIN-299 |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider |  | Further to this (DIN-298), the cause of this IF-013 being issued can only be that the UMSO has not provided the UMSDS will the correct D0388 UMS Inventory to use. Therefore – the UMSO has a requirement to receive the IF-013 to tell them this. However, the Interface Catalogue has not designed that this will get sent to the UMSO. I think this is a Design Issue too, and also needs a DIN raising so that the IF-013 is provided to the UMSO. | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12 |  |  |  |  | DES138
MHHS-DIN-300 |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider |  | You are advising a Load Shape will always require the E Flag. But as you say if the MPAN is de-energised, that MDS will reject the IF-021. Is this therefore your answer – that MDS will reject the IF-021, and there is nothing that can be done about that, so we just need to accept we will get those rejections? If so, this isn’t really a satisfactory process, to know rejections will be received in this scenario. Can you just confirm that the solution here is we just need to accept we will get these rejections to the IF-021, which we will then simply ignore? If that is the case – again a DIN needs to be raised to write this into the Design so the process is documented. | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12 | Requiring clarification dont think this is a Change |  |  |  | UMSDS Method Statement
MHHS-DIN-301 |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider |  | the corrective action on this scenario (DIN-300) occurring will be if/when the UMSO provides the UMSDS with a D0388 UMS Inventory – then the UMSDS will stop using and submitting the Load Shape data. There does not seem to be a mechanism in the Design for the UMSO to be made aware of this issue that would be of their making, so again needs raising as a DIN please. | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12 | same as 299 and 300 |  |  |  | DES138
MHHS-DIN-302 |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider |  | I’ve pulled together the below table. This covers all the possible scenarios of the UMSDS either having or not having the D0388 UMS Inventory. Combined with whether that D0388 UMS Inventory has load associated data within it. Also combined with whether the MPAN is Energised or De-Energised. Here I’ve listed which Settlement Period Quality Indicator should be used, and where applicable, which Estimation Reason Code should be used. Should this be included in the UMSDS Method Statement and if so, are you happy with the below. In Green are steps we understand. In Red, these remain Unknown to us based on the Design and your answers given. In Orange, these are answered based on your guidance on your email of 28 April – but are not specified in the written Design. | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12 | same as above |  |  |  | UMSDS Method Statement
MHHS-DIN-303 |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.2.3 - Changes to Data formatting to align with Swagger / DES-138 | Implemented |  | Interim Release 1 |  |  |  | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-304 |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.4.3 - Case Sensitivity - additional information added to provide clarity on approach | Implemented |  | Interim Release 1 |  |  |  | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-305 |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 5.1.7 - Additional Detail required for IF-47 / ISD to provide clarity on approach / steps | Implemented |  | Interim Release 1 |  |  |  | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-306 |  | 2023-05-22 | Tym Huckin | 3992 | Tym Huckin | Consultancy |  | Provide further clarity / worked examples for UTC Settlement Date (DI-101) for BST / UTC cross over period. | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-307 |  | 2023-05-22 | CGI | 5042 | Dave Webster | Software Provider |  | Status code incorrectly included in required, although not in Standard Response Body Type. This is in Swagger 1.2. | Closed |  |  | 2023-06-23 | Duplicate of DIN-282
MHHS-DIN-308 |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | S0 Block required property | Add required property to all the S0 blocks in the interface definition | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Update made to Swagger for all Interfaces to mark 3 fields in the S0 block as mandatory. | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-309 |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | Swagger Alignment to DES-138 | Define Transaction ID (DI-990) with no Min Length to align with DES-138. This is DT-014. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (DIP Transaction ID min length removed) | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-310 |  | 2023-05-23 | ELEXON | 5173 | Rob Golding | Central Body |  | Please can you raise a DIN to provide some guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 are to be applied (if at all), i.e. does the DIP need to consider the effective period and only accept messages on the production system when the message falls within this period? And if so what date within the message should be used as a check? Or the physical date/time of message receipt? Or doesn’t the DIP need to consider these dates at all and no check needs to be applied? | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12
MHHS-DIN-311 |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-985 / DI987 both String 60. Swagger Min and Max Lengths aligned | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updates made to DES-138 for Length alignment to 60. Updates to Swagger to remove min length for DI-985 and DI-987. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-312 |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-984 / DT-009 needs to be updated to be min 3 / max 5 length. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Sender Role - change as per description | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface
MHHS-DIN-313 |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S1 - Sender Timestamp updated correctly (from sent timestamp) in Swagger to align with DES-138 | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (renamed to Sender Timestamp) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-314 |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - Publication ID Min Length updated in Swagger 1.2 to be 6 to align with DES-138 (rather than 7) | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Publication ID Min Length now 7, not 6) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-315 |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - DIP Correlation ID should have no min length to align with DES-138 (rather than min length of 1) | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (DIP Correlation ID has no min length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-316 |  | 2023-05-25 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, all DT-006 and DT-006N should have min length 10 & max length 10 to be consistent. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated DES-138 to align Data Type and provide consistency to Swagger. Removed DI-095 which is no longer used. | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface
MHHS-DIN-317 |  | 2023-05-23 | St Clements |  | Sean Cooper | SRO Design |  | Update DES138 IF document to include reference to the B9XX Array references held in Swagger | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-318 |  | 2023-05-23 | REC | 5049 | Jonny Moore | Consultancy |  | While completing the design phase for EES we noted that the following items with the IF-050 do not have an effective from date. - RMP Status (Registration) - MP Status These items currently have an effective from date held in EES and not including this in the IF-050 would have the effect of removing these items from EES. | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-319 |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S0 - EventCode to marked as required to align with DES-138 | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Event Code marked as required) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-320 |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, S1 - Environment (DT-013) should have min length 3 & max length 10 to be consistent with values. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Set Min to 3. However, string length is 10, so max length should be set to 10 | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface definition
MHHS-DIN-321 |  | 2023-05-23 | St Clements |  | Sean Cooper | SRO Design |  | Consider adding B005 to IF-036 so that incoming SP knows who previous SP were | Requires Industry Work Group review |  | Interim Release 3 | 2023-07-12
MHHS-DIN-322 |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B002 - Incoming Supplier MPID - Swagger aligned to DES-138 for min / max lengths | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Incoming supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-323 |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B003 - Ougoing Supplier MPID - Swagger aligned to DES-138 for min / max lengths | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Outgoing supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-324 |  | 2023-05-24 | EDF | 4780 | Paul Saker | Supplier |  | NHHSP-BPM00C- Transfer of Reads on Change of Data Service details several process steps and messages related to obtaining and sharing register readings between the gaining and losing suppliers to agree a CoS, and to initiating the missing/disputed reads process defined in the Retail Energy Code where CoS reads are missing or need to be disputed/amended. However, it appears that there is no further detail defined within the Design Artefacts regarding how exactly these process steps would work, including amongst other things: • Timing/Operational Choreography – for example it is not clear exactly when losing and gaining suppliers would be expected to attempt to communicate with the meter, or the timescales for sending data obtained between suppliers. • Data to be included in messages – while BPM003C refers to the inclusion of ‘register readings’ in some of the messages it is not clear which registers should be included for smart meters and non-smart meters – for example whether that should just be the registers on a smart meter that the sending supplier uses for billing, or whether that should be all the 48 time of use registers stored on the smart meter. Additional input from Andrew Margan - Within the code workstream, we believe the Operational Choreography document needs to be updated to reflect SLAs. Without this, we can’t complete the Code drafting. If you disagree, we would appreciate an early heads up, so we don’t look disjointed in front of industry. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-325 |  | 2023-05-24 | CGI |  | Dave Webster | Software Provider | Status Code Missing from MsgBody | In the SubmitEvents StandardResponseBodyType object (SubmitEvents ¦ 1.2 ¦ MHHSPROGRAMME ¦ SwaggerHub), it states that “statusCode” is a required field. Yet its’ definition does not exist in the properties of the object. StandardResponseBodyType: type: object properties: transactionID: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-014-DIPTransactionID' senderUniqueReference : $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-995-SenderUniqueReference' correlationId: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-011-CorrelationID' sentTimestamp: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-003-DateTime' senderId : # the sender of this message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' recipientID : # indended (logical) recipient of the message, i.e sender of the original event message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' DIPConnectionProviderId : # physical recipient of the message (if different to recipient Id) $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' message: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-005-StatusErrorMessage' help: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-019-HelpText' serviceTicketURL: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-018-URL' required: - transactionId - sentTimestamp - senderId - recipientId - statusCode - message - help - serviceTicketURL | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | This has now been updated in V1.2 of Swagger StatusCode Added to the ResponseBody. | Technical corrrection | Supporting Docs |  | JSON/YAML files
MHHS-DIN-326 |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Changes required to DES-138 / interface catalogue given changes in Migration Design e.g. the addition of interface IF003 and potentially ISD. | Closed |  |  |  | Duplicate of 247 | No Change |  |  | None
MHHS-DIN-327 |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | IF-005 User Guide | The IF005 User Guide explains how the IF005 should be populated. We have a request for clarification on whether the IF006 will be populated identically or if the Meter ID in the IF006 will reflect the Modified Meter Id in the IF005. Is IF-005 identical to IF-006, or is it with updated MTD's. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | IF-006 should be a facsimile of IF-005. In the case of change of MSN... MSN field will reference the (old) MSN and Modified MSN will be populated with new/revised MSN. All subsequent flows following the IF-006 will only reference the NEW/REVISED MSN. We further clarified this in a change to the Note(s) section on IF-006. | Data interface correction | Supporting Docs |  | DES138
MHHS-DIN-328 |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | The operational choreography does not include an SLA for the RS to send appointment data to the CSS or the timings by which the CSS and DSP should deliver their roles within the process. These need to be added to the operational choreography for clarity, noting the interaction with CR018. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-329 |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Approach on a business rule where the ERDS does not send a MEM de appointment / appointment for an MHHS migration where the same MEM is being appointed under MHHS arrangements e.g. they have the same MPID. The expectation is that smart and advanced MEMs will use the M role code for the interaction with CSS so from their perspective there should be no change. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-330 |  | 2023-05-25 | Ovo Energy | 5225 | David Morley | Supplier | Long Term Vacant | BSCP504 section 4.15.3 stipulates the criteria via which suppliers can classify sites as Long Term Vacant (LTV). BSCP701 stipulates actions that SDS shall take if the supplier nominates that a site is LTV. However, the criteria that suppliers shall use for classifying LTVs in MHHS is missing. Can you please signpost where the new criteria will be located? | Open - awaiting assessment |  | Interim Release 5 | 2023-09-13 | BSCP is responsible for revising the code specification, there are no changes to design specified.
MHHS-DIN-331 |  | 2023-05-25 | MHHS | 4733 | Martin Freeman | Central Body | Secondary Routing | Secondary routing for IF-013 is specified as being conditional upon the value of DI-015. However, DI-015 (Connection Type Indicator) is a property of a repeating block, and there is no constraint in place to suggest that each element in the repeating block must have the same value for this (or any other) property, in which case multiple rules in the routing table could apply simultaneously. The routing table design seems to suggest that only a single rule should apply at a time and that routing should not be derived by blending multiple rules. If this is so, and a message is received where different elements in the B050 have a different Connection Type Indicator then there is no coherent way to implement this in conformance with the routing table. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Agree there was a routing contradiction for scenarios/periods where a different connection type was in effect. Interface notes section has been updated to direct the use of 'separate' IF-013 messages in such circumstances. Note also makes clear that repeating B050 blocks are acceptable where other elements (not Connection Type) of the CCC vary over the period to be defaulted. | Design Ambiguous | Supporting Docs | Default Consumption | MHHSP-DES138-Interface Catalogue
MHHS-DIN-332 |  | 2023-05-25 | MHHS | 4750 | Martin Freeman | Central Body | IF-013 Routing | In the routing table for IF-013 all rules are conditional upon S0.Eventcode == [ActivePowerDefaulted], which means that for IF-013 message where Eventcode == [ConsumptionOnDeEnergisedMPAN] there is no routing at all, which means when this message is sent to the DIP it will not be routed anywhere and will simply disappear. That's almost certainly an error. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Event code [ConsumptionReceivedonDeEnMPAN] has been moved from IF-013 to IF-014. The valid event code list and routing rules have now been updated for both interfaces to reflect the move. v1.2 of Swagger also updated to reflect this change | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue
MHHS-DIN-333 |  | 2023-05-25 | MHHS | 4760 | Martin Freeman | Central Body | Connection Type Required to Support Routing of IF-014 | All of the routing rules specified for IF-014 are conditional upon DI-015 (Connection Type Indicator). But IF-014 does not have any blocks with this property, which means this message won't get routed anywhere. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Block B067 - Connection Type Added to IF-014 in order to support routing requirments. Swagger v1.2 updated to reflect this change. | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue
MHHS-DIN-334 |  | 2023-05-25 | MHHS | 4766 | Martin Freeman | Central Body |  | The routing table for IF-018 specifies roles AMSC, UMSC, UMDC for Secondary routing. There are no such roles in either the DES138 nor the E2E001. | Closed |  |  | 2023-06-23 | Secondary Routing Review/Changes have superceded this issue - Ref DIN-268
MHHS-DIN-335 |  | 2023-05-26 | British Gas/Engage Consulting | 4640 | Neil Strange/ Haz Elmamoum | Consultancy | Four questions on IF004 | IF/PUB-004 – DIP Common Blocks referencing MHHSP-DES138-Interface Catalogue v5.1.1 As a minimum this needs to be referenced in the supplier requirements MHHSP-BRS004-Supplier Overview and MHHSP-BRS002-Metering Service requirements, but to ensure parties get sight of this we would suggest it needs to be included in a business process map and have associated requirements. For IF-004 to be useful to participants DI-999 – Event Code needs to be elaborated e.g. 1- Installation 2- Removal; 3- Exchange; 4 - Found (Where installed by Gas supplier and Elec Supplier takes ownership) C/M/O rules for DI-192, DI-193 and DI-194 need to be explained in the notes – presumably driven by event code Available is spelled incorrectly (available) for DI-192 and DI-194 there are a couple of angles here – 1) ensuring wider awareness and 2) it seems there is a question mark on the governance here as it is odd a flow has been added but industry does not appear to have been sighted on it especially with no associated referencing in artefacts and no process map, so effectively no one has any idea how it is supposed to be used. Although it was formally agreed not to include and use bilaterally....from a Large Supplier Constituency perspective, my members are keen to ensure design clarity and how flows are to be used or not, regardless of their ad-hoc / bilateral nature. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Optional flow not formally shown as part of the design. Spelling corrections updates, optionaility guidance also updated. | Data interface correction | Supporting Docs | IF-004 | MHHSP-DES138-Interface Catalogue
MHHS-DIN-336 |  | 2023-05-26 | MHHS |  | Rob Topley/ Zak Hussain | SI Design |  | Process Step No. BP Step ID Process Map wording Interface ID Sender Recipient/Service Traceability Requirement Traceability Method Statement iServer Requirement Name iServer Step name Issues Found BP01 170 BP01 - 170 Send Site Tech Details on Metering Service Request MHHS-RS-LD-012.1 #N/A LDSO170a Send Site Tech Details on Metering Service Request Missing (only on BPD and traceability matrix) BP01 175 BP01 - 175 Receive Site Technical Details D0215 LDSO Metering Services MHHS-RS-MS-037.1 #N/A MET175 Receive Site Technical Details Missing (only on BPD and traceability matrix) BP03B 95 BP03B - 95 Manage SP Appointment Amendment Request Response PUB-035 DIP Supplier MHHS-BR-SU-35.1 #N/A SUP095a - Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP03B 96 BP03B - 96 Manage SP Appointment Amendment Request Response PUB-035 DIP Data Services Metering Services MHHS-BR-DS-11.1 #N/A ESP96 – Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP05 315 BP05 - 315 Issue Reading Data MHHS-IF-041 Data Service DIP MHHS-BR-DS098.2 #N/A DAT315 – Issue Reading Data Missing (only on BPD and traceability matrix) BP05 340 BP05 - 340 Process Reading Data PUB-041 DIP Supplier MHHS-BR-SU047.1 #N/A SUP340 Process Reading Data Missing (only on BPD and traceability matrix) BP05 350 BP05 - 350 Process Reading Data PUB-041 DIP LDSO MHHS-BR-LD009.1 #N/A LDSO350 Process Reading Data Missing (only on BPD and traceability matrix) BP010D 1055 BP010D - 1055 Receive updated Legacy information PUB-026 DIP Central Settlements MHHS-BR-RD-018.1 #N/A ECS1055 Receive updated Legacy information Missing (only on BPD and traceability matrix) All these requirements don’t exist on any requirement catalogues, they’ve only ever been on a BPD document or the traceability matrix (which are essentially the same document). Also, the highlighted traceability has a typo and is on a requirements artefact but is wrong on both the BPD and traceability matrix. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-337 |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger alignment to DES-138 | R0 - Response Message Min length updated to align with DES-138 | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated R0 - Response in Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-338 |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier |  | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. BP003 to be updated to clearly show IF-036 going to both Import & Export supplier | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-339 |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier |  | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. IF-001 to be updated to be additionally sent to the Export supplier rather than just the import | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | See 338 as well
MHHS-DIN-340 |  | 2023-05-26 | UKPN | 4547 | Neal Medley | Network Operator |  | The reports ELEX-REP-02/02A will only contain aggregated data for A(General LLF Class Import and C (General LLF Class Export). The I/F021 can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/014 Rejected Consumption Data Submission and I/F MDS Defaults Applied to any I/F021 data to ensure you are not using rejected data or are missing I/F 021 data in respect of an MPAN. MDS Method Statement to be updated to reflect | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-341 |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | MUM Event not required by MDS | For IF-018 the event [MUMIndicator] is routed to MDS and indicates metered/unmetered. This event is not required by MDS as they can infer this from the Market Segment (Advanced, Smart and Unmetered). DIN raised to remove the routing | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | MDS Removed as Always Recipiant for Event [MUMIndicator] | Data interface correction | Supporting Docs | IF-018 | MHHSP-DES138-Interface Catalogue
MHHS-DIN-342 |  | 2023-05-26 | UKPN | 5194 | Neal Medley | Network Operator |  | The intent is that the daily volume on actuals or estimates are the sum of the appropriate consumption data. So when added together they should equal the summed Total of the Settlement Period data (Total Uncorrected Volume) barring any rounding errors. The data is given in MWh to six decimal places (i.e. to the nearest Watt hour). I assume DUoS billing only calculates to the nearest unit so would not expect any rounding errors to impact. The A flags are set out in the ELEX-REP-02/02A are the same as those set out in the CCC table in the VAS Method Statement which is also in the MDS Method Statement. I agree the list in the calculations only are missing the full list of SPQI that are deemed to be actuals as set out in the ELEX-REP-02/02A. DIN raised to correct the calculation | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-343 |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | Routing rules table | The routing rules on the IF-037 sheet state that MDS will 'always' receive the DSDeApp event code, however the 'Always' column on the IF_LIST does not state Central Settlements for MHHSP-IF-037. IF list needs updating to reflect that the DSDeApp event always routes to MDS | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Decision taken to remove Recipiants from this list - as just duplication of information contained within each of the IF spreadsheets. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue
MHHS-DIN-344 |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B005 Custom Block update Swagger to align with DES-138. Current Metering Service MPID Length removed. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138. Current Metering Service MPID Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-345 |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B024 Custom Block update Swagger to align with DES-138. DUOS Min Length removed. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138. DUOS Min Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-346 |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design |  | IF-001 - B032 Custom Block update DES-138 to align with Swagger. Update DI-122 (Profile Class) to Integer from String-2. | Closed |  |  | 2023-06-23 | DI-122 remains as String 2 for Profile Class to support requirements for enumerations. | Data interface correction | Supporting Docs |  | None
MHHS-DIN-347 |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B035 Custom Block - update Swagger to align with DES-138. Remove min length. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-348 |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | IF002 correction | IF-002 - B074 Custom Block. Clarification on DI-091. DES-138 says this is 1 digit to the left of the decimal point. Swagger says 5 to 6. DES-138 to be updated to the correct value. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated Swagger to be an Integer (1), Min of 1, Max of 1, example of 5. This now aligns with DES-138. | Data interface correction |  |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-349 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Correlation ID Issue IF-006 | Routing Rules in DES-138 do not always correctly identity where Correlation ID == Copy ie, it's missing for IF-005 / IF-006 so this needs to be updated correctly across all interfaces. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated IF-006/IF-009/IF-039/If-028/IF-026/IF-016 to show use of a "Copied" Correlation ID (ie copied from the preceeding IF txn pairing) | Data interface correction
MHHS-DIN-350 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-005 B033 to align Swagger with DES-138 (Postcode removal, mandatory modified meter id) | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Postcode removal, mandatory modified meter id) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-351 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B071 to align Swagger with DES-138 | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-352 |  | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Obsfucation Text | What text should be used for data obfuscation ? for things like Boolean fields (True/false) | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-353 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B032 to align Swagger with DES-138 (SSC Min Length should be 4) | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated SSC Min Length to be 4) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-354 |  | 2023-05-30 | SJW |  | Sarah Jones | Consultancy |  | Please see below details of a new design query related to the Registration Tranche of Code Drafting. We note that in BP011C there is a process whereby the Registration Service will auto de-appoint / appoint agents for secondary related metering points and linked export metering points as part of their validation. The business process only includes the sending of the IF037 to the Losing MEM and not the IF035. Please could you confirm that this is correct and that in this instance the Losing MEM would not receive an IF-035. If this is the case, we think there should be a change to Metering Service requirements MS-018 and 019 to clarify that where the Losing Metering Service receives an IF-037 with no preceding IF-035 then they should send the MTDs at this point. The alternative would be to include the sending of an IF-035 as well as an IF-037 accepting that these would arrive at a similar time. This would align to the process for managing retrospective MEM appointments where we understand that the Losing MEM would receive both the IF-035 and the IF-037. We also suggest amending MS-008, 008.1, 009 and 009.1 to recognise this nuance as follows: MSA/MSS must obtain Export MPAN de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. MSA/MSS should note this message will be automatically triggered when a change of Metering Service has successfully completed for the linked import MPAN or a new MPAN linkage has been put in place where the [linked import / primary related] MPAN has a different appointed Metering Service. Presumably there is a similar impact on the data service requirements that would need to be considered. | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12 |  |  | Supporting Docs
MHHS-DIN-355 |  | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Number of Register Digits | Revisit and confirm IF-005 Cumulative Digits validation rule against lastest version of the CP | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | All instances of DI-091 (IF-002,IF005,IF-033,IF-036) updated to reflect updated logic. IF-005 validation rules updated also to reflect new guidance. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue
MHHS-DIN-356 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B073 - update Swagger to align with DES-138 (consumptionAmendmentSupplierReference max length) | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated consumptionAmendmentSupplierReference max length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-357 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B902 - update Swagger to align with DES-138 (supplierConsumptionAmendmentRequests typo update) | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated supplierConsumptionAmendmentRequests - remove typo) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-358 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-034 B070 - update Swagger to align with DES-138 (contractReferenceMeteringService max length 10) | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated contractReferenceMeteringService max length 10) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-359 |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: The method statement states that “The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN on notification of the set-up of that MPAN in MHHS-IF-001.” However, it will be the MHHS-IF-036 Registration Service Notification of Service Appointment & Supporting Info that will initially provide the fact that an MPAN has migrated to Central Settlements. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-360 |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: 3.3 Where a years’ worth of data, >=75% and <100% of actual UTC Period Consumption data (where Settlement Period Quality Indicator = A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6) has been used to calculate the Annual Consumption, the Annual Consumption Quality Indicator should be set to “1”. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-361 |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design |  | We need to raise a DIN on the AC method Statement and AC requirements: Likewise 3.6 needs to say greater than or equal to 182 days: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-362 |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design |  | Section 5 incorrectly named Section 6 needs to be removed: 6. Transition and Next steps | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-363 |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design |  | We may also need to document how the is calculated by the Load Shaping Service in the first year. I believe Helix have developed a calculation and this would need to go in the Load Shaping Method Statement and be referenced in the AC Method Statement. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-364 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-035 - B066 - mark as mandatory in Swagger as per DES-138 | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated so B066 is a mandatory for IF-035 custom block) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-365 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-004 - B093 - update Swagger to align with DES-138 (min Length on commsHubGUID / GPF-GAS-GUID) | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated min Length on commsHubGUID / GPF-GAS-GUID) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-366 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 custom block - SSC add min length to align with Swagger | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B032 custom block - SSC add min length to align with Swagger) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-367 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 Profile Class - updated Swagger to be a String to align with DES-138 | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B032 Profile Class Swagger to be a String to align with DES-138) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-368 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-013 - B049 updated Swagger to align with DES-138 (run Number optional) | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B049 Swagger to align with DES-138 (run Number now optional) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-369 |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | Switch Cancellation Info Note | Update BP002/003 to add informational note that Registration Cancelations will be processed as soon as they are received by SCS from CSS i.e. Apps Lapsed through switch cancelation sent immediatly not held until Proposed App Date. Are changes to OPC also required ?? | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | BP-002/003 updated to include new informational Note in Supplier swimlane relating to CSS Switch Cancellations. OPC updated to make it clearer that Secured Active Processing includes Switch Status Update processing. | Process Model correction
MHHS-DIN-370 |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | IF-005 Update Window Guidance for Prev MS | Change IF-005 and Guidance Doc to allow Meter Updates within 10 day window for previous MS | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | New validation rule added to IF-005/MeterUpdate to allow previous MS to submit if within 10 day post appointment period. IF-005 User Guide updated to reflect same.
MHHS-DIN-371 |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team |  | Review design to ensure only Supression of IHD info for advanced segment and NOT "deactivation" of underlying IHD record. | Closed |  |  | 2023-06-23 | Confirmed that IDH details will be retained on Smart to Trad Exchange. Any IHD info present will be suppressed (ie not included in msg) if Segement is Advanced. No change required to documentation. Possible data clense issue - Dan T. to raise in Data Forum.
MHHS-DIN-372 |  | 2023-06-01 | MHHS | 5298 | Rob Golding | Central Body | Mapping Roles | There is a need to master the mapping of Market Participant Role to DIP Role within the MHHS solution. | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12 | This would seem to best fit within ISD. Specifically Entity #21. Proposed solution is to add DIP Role ID into ISD Entity #21 We would also add validation into Entity M16 to ensure it always references the valid mappings in #21 when a new MPID to DIPID mapping is created
MHHS-DIN-373 |  | 2023-06-02 | MHHS | 5272 | Rob Golding | Central Body |  | There is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 | Closed |  |  | 2023-07-12 | Duplicate of DIN-297
MHHS-DIN-374 |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Message Replay & Requeue functionality | Message replay and requeue functionality needs to be added to the DIP API interfaces, which requires changes to the Swagger / YAML definitions. Detail is required in the E2E design documentation to explain how the message replay and requeue functionality will work. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updates to the E2E001 design document to provide detail on how the replay and requeue will work. There are updates to Swagger to support new interfaces for /dip-channel/{id}/replay and requeue respectively. There is also a new MessageRequest Schema that is used to pass data into both of these interfaces. To support these changes, section 4.8 has been updated in the E2E001. | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents
MHHS-DIN-375 |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Interface webhook configuration | Updates require to the pubconfig and webhook config to support per interface webhook configuration, alongside changes to support definition of recipient ID and role ID. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updates to the E2E001 design document to provide detail on how the webhook configuration will work, with information related to specific interface changes. There are updates to Swagger to support new interfaces for /dip-channel/{id}/pubconfig (POST and DELETE) respectively to support changes defined in the E2E001 (Section 4.5 and 4.5.1 and 4.5.2have been updated to provide more clarity / information). | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents
MHHS-DIN-376 |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-099 changes required to ensure DES-138 displays the correct YAML name / Swagger aligns to this. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | "Register" spelling in name has been corrected in DI099 in DES138 | Data interface correction | Supporting Docs |  | DES138
MHHS-DIN-377 |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-097 | DI-097 - In DES-138, this is defined as a string (2), but the existing data type is an Integer and this is an Integer enumeration. Need to update this to an Integer in both DES-138 and Swagger 1.2. | Closed |  |  | 2023-06-23 | Rejected / closed as enumeration of values requires string (2) therefore this is retained to support buisness requirements. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-378 |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. This information has now been added to DES-138 5.2.1. | Data interface correction | Supporting Docs |  | DES138
MHHS-DIN-379 |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-048 | DI-048 - clarity required on whether this is "meter manufacture make and type", rather than just "meter manufacturer". The first is an existing data type and links to the J number, so providing further clarity / rename would quickly ensure alignment in DES-138 and then subsequently in Swagger. | Closed |  |  | 2023-06-23 | Rejected / closed as this was discussed as part of previous work off items and description has previously been approved / accepted as Meter Manufacturer. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-380 |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-052 | DI-052 in DES-138 currently has 4 enum values ie, - Active Import, Active Export, Reactive Import, Reactive Export. In MDD there are currently 38 options documented. Discussion around whether ISD Entity 47 should be referenced as the list of values allowed. This can then be aligned / referenced in other other documents ie, EMAR will reference ISD Entity 47. | Closed |  |  | 2023-06-23 | Rejected / closed as this was discussed as part of previous work off items. Only 4 values are required in MHHS / DIP, therefore only these values are referenced / used as part of the enumeration to avoid bringing data from existing systems into new systems when this is not required. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-381 |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-842 | DI-842 - Confirmation that MDR's have DIP ID's? There has been discussion in various forums to understand whether they do and if not, then this data item needs to be removed in DES-138 and Swagger. | Closed |  |  | 2023-06-23 | Rejected / closed as MDR's do have DIP ID's, therefore this value will be retained. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-382 |  | 2023-05-06 | Design Team | 4570 | Neil Strange | Supplier | D0010 | In BP003C, at CoS traditional CoRs are transferred between suppliers via D0010. We believe this needs to be used for all meter types - as this will be needed for non-communicating smart and advanced meters – and BP003C needs to be amended accordingly. There is no mention of IF-041 and we do not believe that the DIP is expecting an IF/PUB-041 transaction between suppliers. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Supplier added as a Primary Recipient of Supplier initiated Reads. Sending supplier would need to populate the DIP ID of Supplier(s) with whom he wished to share the reading. Working Group specifically decided not to discuss /include COR scenarios for Smart Metered Sites however this is not prevented by the Design - a note to this effect has been added to BP003C for clarity. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue BP-003C Transfer of Readings
MHHS-DIN-383 |  | 2023-06-07 | RECCO | 4558 | Sarah Jones | Central Body | Change of Segment Scenario | We cannot find anything in the design artefacts stating that the Metering Service is required to notify metering exchanges for change of segment within 2 WDs. We have found the following: MS-094: MSA/MSS must be able to publish Change of Segment Meter Exchange details and reads via the appropriate interfaces, where it is not formally appointed as the Metering Service but does have an accepted prospective appointment (Appointment Scenario = "SEG"). The MSA/MSS must issue the work update to Registration at the earliest opportunity but within [x] days of completion at the latest. OPC 240: Notification of works to be completed by D+3 Working Days (This should provide time for consumption to be provided using new MTDs ahead of the SF run.) The BP011 references the connection type update being provided by LDSOs within 2 WDs. There is no equivalent for metering updates. Will require DRG confirmation on if the 'x' should be 2 or 3 working days | Requires Industry Work Group review | 2023-06-15 | Interim Release 3 | 2023-07-12 | DRG meeting agreed to align with 3WD SLA
MHHS-DIN-384 | DI-174 | 2023-06-07 | St Clements | 4938 | Madison Layton | Software Provider | IF-038 and IF-039 blocks not the same | Block B020, B021 are not the same across interface IF-038 and IF-039. DI-140 and DI-138 (SP DIP ID) are in IF-039 but not in IF-038. Understanding was that with the DIP change that all data items in block are mandatory, the blocks were to be consistently defined across all interfaces. If extra DIP ID DI-138 and DI-140 data items are included in IF-038 then we need a new REG rejection code to allow us to reject where DIP ID is not the same as the sender DIP ID. Alternative is to separate the DI-140/DI-138 into their own blocks included on the IF-039 interface only. | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12 |  | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-385 |  | 2023-06-07 | Design Team |  | Steve Weston | SI Design | Correlation ID | S1 Common Block - Correlation ID is mandatory in Swagger, but Optional in DES-138. Swagger should be updated to align. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Updated S1 Common Block, Sender Correlation ID in Swagger, as this is Optional in DES-138 to support business process and requirements.
MHHS-DIN-386 | DI-179 | 2023-06-07 | St Clements | 5258 | Madison Layton | Software Provider | Register Digits | REC Change R0102 has been approved by industry to amend the number of display digits validation Where the Meter Type is S1 the Number of Displayed Register Digits value must be either 6 or 5 Where the Meter Type is S2A, S2AD, S2ADE, 2ADF, 2ADEF, 2AEF, 2AF, S2B, S2BD, S2BDE, 2BF,2BDF, 2BDEF or 2BEF the value must be “5”. Where the Meter Type is prefixed with “S2C” the value must be “6”. Where the Meter Type is 2CDEF, 2CF, 2CDF or 2CEF the value must be “6” REG1097 validation on the IF-005 needs correcting with this change, and the population notes for data item DI-091 across multiple interfaces also needs correcting | Closed |  |  | 2023-06-23 | Duplicate of Register Digit DIN-355 listed above | Data interface correction | Supporting Docs | Interface Catalogue | Lis
MHHS-DIN-387 | DI-180 | 2023-06-09 | St Clements | 5269 | Madison Layton | Software Provider | Uplift metered indicator requirements | There are elements in the requirements that suggest that metered indicator would trigger a change to Market Segment. E.g. MHHSP-BP011-Change of ConType andor Mkt Segment-v5.1 Step 102 MHHSP-BPD011 - Change of Con Type or Market Segment v5.0 Step 102 Which states if there is a change to market segment RS would need to re-evaluate the market segment And MHHS-BR-RS-124 which include in brackets: Change of Connection Type (Change of Unmetered Indicator) MPRS will assess Market Segment against the ISD entity M7 which does not include Metered Indicator. Therefore a change in Metered Indicator in isolation of any other changes to data items in the M7 table/Related MPANs/Linked MPANs, will not trigger a change to Market Segment. As it will not trigger a change MPRS will not re-evaluate Market Segment base on a Metered Indicator change alone. The requirements need uplifting to reflect. | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-388 |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | IF-036 Custom Routing Rules | Following discussions with SCS agreed that for reasons of complexity it would be better to adopt Primary rather than secondary routing to IF-036. New Requirement created for REGS to undertake the Primary Routing of IF-036. | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-389 |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | Appointment Start Times | Do we need a formal validation Rule to check that Appointment Start times are referenced as Midnight Local ? Issue raised numerous times with SCS. Waiting for Dan to confirm their position. | Open - awaiting assessment
MHHS-DIN-390 |  | 2023-06-13 | Siemens | 5534 | Tony Mason | Metering Service Provider | IF/PUB-018 | There appears an inconsistency in the Business Process Map, BP010, and the routing rules for the IF-018 where the Event Code = DUOSTariffIDChg. This information is confirmed to SPs on the IF/PUB-036 and would then be updated where there is a change on the 018 according to the Secondary Routing Rules. This notification is absent on the process diagram. Could you confirm the position and update the documentation accordingly? | Open - awaiting assessment
MHHS-DIN-391 | DI-182 | 2023-06-13 | St Clements | 5304 | Madison Layton | Software Provider | IF-019 validation gap on principal and subsidiary MPAN | IF-019 is missing validation rules to ensure an MPAN is only listed once in the IF-019, need rules to ensure the sender cannot repeat same Subsidiary MPAN twice in the repeating B090 block, and cannot list the same MPAN as both Principal and Subsidiary in the same IF-019 message | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12 | Create a NEW rule to prevent duplicate MPANS within repeating B90 groups within a single message
MHHS-DIN-392 |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Consent Fields | Raised by SCS. B086/DI-017/DI-018 - This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block B086 updated to be "must be provided" for smart meters. Data items set to mandatory non-nullable. | Ready for Internal Review |  |  |  | Block text updated to show mandatory if smart meter present, and DI-017/D-018 updated to be mandatory non-nullable
MHHS-DIN-393 | DI-181 | 2023-06-13 | St Clements | 5274 | Madison Layton | Software Provider | De-appointment and re-appointment date order | MHHS-BR-RS-128.4 & MHHS-BR-RS-128.5 covers the requirement for MPRS to ensure MS/DS are aligned across Related/Linked MPANS, and where they are not to de-appoint the MS/DS and appoint the correct MS/DS. The de-appointment requirement specifies to set MS/DS ETD to D+1 and the appointment to set the MS/DS EFD to D+2. Why do we need to apply the de-appointment and re-appointment in the future? Would we not be better to use the previous day (D-1) for the de-appointment MS/DS ETD and the current day (D) for the appointment EFD? | Open - awaiting assessment
MHHS-DIN-394 |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Annual Consumption Fields | Raised by SCS. B059/B027/DI-0148 This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block updated to be "must be provided" if availible. Data items set to mandatory non-nullable. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Block text updated to show mandatory if smart meter present, and DI-0148 updated to be mandatory non-nullable
MHHS-DIN-395 |  | 2023-06-13 | St Clements | 5510 | Vicki Holland | Software Provider | Obfuscation of Connection Type Indicator in IF-021 | The DES138 interface catalogue specifies that the data item Connection Type Indicator will be obfuscated for all parties as it is required for routing only. Can this please be changed so that it is visible? The reason for this request is that suppliers often process data differently for the different connection types and therefore its important that they can internally validate or route data according to the connection type of the MPAN. | Open - awaiting assessment
MHHS-DIN-396 | DI-183 | 2023-06-13 | St Clements | 5305 | Madison Layton | Software Provider | Update IF-019 REG1001 to only apply to Create and Add event codes | IF-019 REG1001 rule applies to all event codes. The MPAN could be disconnected with linkages still in place. If REG1001 is applied on remove event codes, then there will be not means by which the Supplier/DNO can remove the linkage after a disconnection. Suggest REG1001 rule should only apply to the Create and Add event codes. This would be consistent with the existing validation on the DB05 and D0386. | Open - awaiting assessment
MHHS-DIN-397 | DI-184 | 2023-06-13 | St Clements | 5306 | Madison Layton | Software Provider |  | REG0007 on the IF-019 interface is currently written to apply to both Related and Linked MPANs. The intention of this existing rule on D0386 is because Related MPANs switch together, and so changing the relationship during a switch can create a split supply relationship. However Linked MPANs do not switch together and so this is not currently applied to the existing DB05 validation rules. Suggest REG0007 only apply to Related event codes and not to Linked Import Export event codes? | Open - awaiting assessment
MHHS-DIN-398 |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD Stores LLF data | Can we have an ISD enity ID for LLF data. This would be required for the API used to retrive the data from ISD data store. Are you happy for us to create and put it in the Guidance note. | Open - awaiting assessment
MHHS-DIN-399 |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD publishes full data to Elexon Central Systems | Requirement should be reworded to be "ISD must make available the data sets required by LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. | Open - awaiting assessment
MHHS-DIN-400 |  | 2023-06-14 | SRO Design Team | N/A | Sean Cooper | SEO Design | REGS Validation Rule Clarification | REG1089 conditions updated to provide more clarity. Existing wording refered only to a Subsequent App - this is now better defined as an Appointment with a prior/earlier Sender Timestamp. No functional change. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | Validation rule text updated to specifically reference Sender TimeStamps so as to provide more clarity on the nature of the val rule/when generated | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-401 |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | IHD/SMSO Fields | IHD Install Status and IHD Status Effective from Date fields should be optional (ie nullable) when providing an IHD update in IF-025/IF-026. SMSO and SMSO Effective from Date fields should be optional (ie nullable) when providing an SMSO update in IF-025/IF-026. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | DI-137/ DI-136 in block B030 updated to Optional (O) in IF-025 and IF-026 DI-134/ DI-135 in block B031 updated to Optional (O) in IF-025 and IF-026 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-402 |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Import/Export Fields | Linked Import/Export MPAN and Linked MPAN Energy Direction will always be provided so should not be nullable | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | DI-038 updated to Mandatory No nulls and Data Type updated to DT-002 DI-151 updated to Mandatory No nulls | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-403 |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Meter Manufacturer Field | Meter Manufacturer is optional (ie nullable) when provided in IF-002, IF-006, IF-033, IF-036 as in IF-005 | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | DI-048 updated to Optional (O) in IF-002, IF-006, IF-033, IF-036 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-404 |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Proposed Appointment Response Code Field | For Response code A there may not be any text to populate for DI-143 | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | DI-143 updated to conditional (C) based on DI-979 = L or R in block B007 in IF-034 and IF-035 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-405 |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Response Message Field | For Response code A no text to populate for DI-980 | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | DI-980 updated to conditional (C) based on DI-979 = R in block R0 in Common Block | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-406 |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Sender DIP ID Field | Sender DIP ID should always be provided in S1 Common Block | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | DI-997 updated to mandatory (M) in block S1 in Common Block | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-407 |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | COS During SEG Issue | Discuss with SCS the option of allowing non-appointed MS to update MTDs even if App has lapsed due to COS activity. If not then need to update process map to call out need for manual exchange of MTDs as Work MS could never submit if IF005 | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-408 |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD is the master for data contained both within ISD and MDD during Transition | The requirement is a bit ambiguous as could be read as all ISD and all MDD rather than just ISD data + overlapping MDD data. We don't want to be the master for MDD only data | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-409 |  | 2023-06-14 | St Clements | 5510 | Vicki Holland | Software Provider | ISD Entity M5 – Consumption Component Classes | EDI012 ISD entities document shows that the settlement period quality indicator in entity M5 is a comma separated list of possible values. This will be difficult to use in systems that need to refer to this data. Could this instead show Actual or Estimate? Alternatively could this be split into parent and child entities to avoid a comma separated list? | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-410 | DI-487 | 2023-06-14 | St Clements | 5542 | Virginia Patey | Software Provider | DI-487 definition incorrect for REP-002 on Swagger | DI-487 energised MPANs is defined as an Integer in the Interface Specification, yet is defined as a String in Swagger. | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | DI-487 updated in Swagger 1.2 to align with Interface specification for REP-002 | Data interface correction | Supporting Docs |  | Swagger 1.2
MHHS-DIN-411 |  | 2023-06-14 | ESG | 4810 | Patricia Parker | Software Provider | Migration Segment Categorisation | The Migration Design currently specifies that Market Segment needs to be recorded before the Migration phase. This should be changed so that it is no longer required. Until an MPAN is migrated, there is no way of maintaining the market segment between the RS and EES using the legacy interface between these two services. However, meter type and connection type will be available in both the EES and the RS, so Suppliers can use a combination of these values to derive the correct market segment. | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-412 |  | 2023-06-14 | MHHS | 5022 | John Wiggins | Central Body | Update to MDD | Migration request to ensure that Elexon add MHHS as a value to MDD. | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-413 |  | 2023-06-14 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | Reading Type (J0171) will be updated with three new values: Forward Migration CoA Forward Migration CoS Reverse Migration CoS Reading Type (J0171) will no longer use Initial or Final for migration reads between Suppliers or DC/DS but one of the above new codes will be used. Meter Reading Reason Code (J0332) will no longer be used to identify migration reads, all reference to this will be amended to Reading Type (J0171) in the guidance document. | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-414 |  | 2023-06-14 | British Gas |  | Mohammad Amin Fuggawala | Supplier | D0275 in D-Flow Document | Ref Previous DIN-244. In the "DES196 D-Flow Document" the D0275 is showing as redundent. This is misleading it should be marked as by agreement between contracting Supplier-DS. Document should be updated to reflect this. | Open - awaiting assessment |  |  |  | Update to DES196 required
MHHS-DIN-415 |  | 2023-06-14 | Elexon | 5702 | Mike Ceney | Central Body | Routing IF-026 to LSS | IF_026- For Routing Rules it states for Event Code/Conditions [SSC], [ProfileClass] and [SSCandProfileClass] that this should be routed to MDS, is this correct as MDS does not use these items in any calculations or outputs, this should state LSS | Ready for Internal Review |  | Interim Release 2 | 2023-06-23 | IF-026 [SSC] and [ProfileClass] have been removed as of Interim Release 1. Update DES138 IF-026 to route to LSS on event [SSCandProfileClassChange] | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-416 | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-001 New App Scenario Code MCS | Create new Appointment Scenario Code of MCS | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-417 | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-002 Validation Rules for Scenario MCS | New Val rule to check MCS is only used for legacy non-migrated MPAN where Supplier is not current supplier | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-418 | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-003 New App Scenario Code MCA | Create new Appointment Scenario Code of MCA | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-419 | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-004 Validation Rules for Scenario MCA | New Val rule to check MCA is only used for legacy non-migrated MPAN where Supplier is current supplier and now active Switch is in progress | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-420 | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-005 - IF-31 Check valid MHHS Supplier | If MCS/MCA code used is Supplier a valid MHHS Approved/Registered Supplier | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-421 | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-006 - Prevent use of Migration Scenario IDs | IF MCS/MCA code used for already migrated mpan - reject appointment for invalid Scenario code(s) | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-422 | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-007 Connection Type/Segment not yet Populated | New error if Connection Type / Segment is not set. Dusos Tariff id ?? | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
MHHS-DIN-423 | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-008 Auto Realign Functionality | New REGS Requirment - Only action the auto-realign functionality on MPANs where both Linked MPANs are in a Migrated state. | Open - awaiting assessment |  | Interim Release 3 | 2023-07-12
DIN Log will be updated by CoP 3/7/23
DIN Log is being updated by CoP Monday 3rd July

## Backup 170723 (hidden)
DIN ITEM DETAILS | [10 empty] | Scheduling |  |  | DIN IMPACT ASSESSMENT |  |  |  |  | DIN OUTCOME
Reference | Created BY | other Reference(s) | Date Raised | Organisation | Freshdesk Ticket # | Contact Name | Constituency | Title | Design Issue Notification Details (as notified by participant) | Current Status | Target working Group Date (If Required) | Target Release | Objection Cut-off Date | Design Issue Proposed solution | Justification/Type of Change | Design Area | Design Area - L2 | Artefact(s) Impacted | DAG Review Date | DAG Outcome | Reason for Rejection/Accept caveats | Design Change Reference Number | Internal Freeze Date
MHHS-DIN-1 |  | T4-COM-1744 | 2023-01-30 | St Clements | 2655 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1744 on 15th Sept 2022 MPRS does not currently restrict IHD Installs to Smart Meters, there maybe cases where there is an IHD present but the Meter is Trad (Not compatible with DCC and Customer Switched) Either Allow IHD on all Market Segments OR Cleansing to ensure IHDs are only present on S2 and S1 Meters SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses, as this is still not resolved | Implemented |  | Interim Release 1 |  | Discussed with SCS and agreed to add new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) Added requirements into BRS003. SCS to raise a potential data cleanse. | Requirement correction | MPAN Ownership | SCS Validation | MHHSP-BRS003-Registration Requirements | 2023-03-23
MHHS-DIN-2 |  | T4-COM-1745 | 2023-01-30 | f | 2657 | Madison Layton | Software Provider |  | Orginally raised as T4-COM-1745 on 15th Sept 2022 DB002 is not the interface on which MPRS will be informed of a change to import/export relationship, it is DB05. The wrong diagram was updated, the EDI was updated to DB05 not import/export. SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses and artefact updates, to inform the wrong data item diagram was updated. However the diagram for EDI updates is still incorrectly reading DB005 update instead of DB02 | Closed |  |  |  | This appears to have been missed in v4.6 - the arrow on BP-010B from step435 to Step 440 shows DB005 (not DB05, assume that’s a minor typo in the comment) - and this is the Energy Direction Information (EDI) which is wrong. It has cbeen onfirmed that this was updated in v4.7 to go into v5.0 baseline. | No Change |  |  | None
MHHS-DIN-3 |  | T4-COM-1752 | 2023-01-30 | St Clements | 2661 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1752 on 15th Sept 2022: MHHS-BR-RS-020: "Retro" (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier ) In the D0205 the Supplier can cancel out the current Agent Appointment by setting the EFD to equal the currently stored Appointment EFD. Is this no longer allowed? All Services must be appointed for at least one day valid or not? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: removing the ability for Suppliers to Correct Invalid Service Appointments may not be understood by suppliers. We want to avoid a later Design CR to add this functionality in. SCS has not had a response, feel this is important discuss with Suppliers to avoid later CRs | Closed |  |  |  | The appointment can be resubmitted if it hasn’t been accepted yet. Once accepted, there is a need to maintain contiguous appointment periods. The scenario mentioned is the CoA not linked to a switch, so the acceptance of a new appointment from a particular EFD will ‘lock in’ that date and the previous MS/DS will be de-appointed at midnight on the previous day. This is to ensure that there are no periods left without MS and/or DS in place, which can happen today with D0155/D0151 sequencing issues. As an overall comment, there is not a concept of cancellation of appointments. The only way to alter the appointment is to get a new IF-031 issued. The only way to do this for the scenario presented, would be to issue an IF-031 for the old MS for the original date and an IF-031 for the new MS for the revised date. Requirement MHHS-BR-RS-021 ensures that Registration Service will action the latest received appointment where there are duplicate appointments for the same day. St Clements had requested that we build in a rule saying that you cannot submit a Change of Service Provider (CSP) request for the same Service Provider. It is a bit of a work-around, but we believe sending it as SEG should work, or alternatively a CR would be required to re-look at the interface validation. Closing, as this doesn't require further action - point noted. We have already spoken to a number of suppliers, and will continue to engage to ensure the functionality of the baselined design is understood and any issues picked up as early as possible. Documentation for LDSOs to point at. Pick up in Code Drafting as well. | No Change |  |  | None
MHHS-DIN-4 |  | T4-COM-1755 | 2023-01-30 | St Clements | 2666 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1755 on 15th Sept 2022: MHHS-BR-RS-071.2 REC CP R062 has been raised to remove the restriction on the number of EDI changes. Will this cause any downstream MHHS issues? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Needs to be aligned with REC Change No responses | Closed |  |  |  | As per original SRO response, the impacts of the REC change need to be dealt with through the REC change process and impact assessment. | No Change |  |  | None
MHHS-DIN-5 |  | T4-COM-1760 | 2023-01-30 | St Clements | 2667 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1760 on 15th Sept 2022: There are no Registration Service Reports defined in MHHSP-ERI011A. Will there be a requirement for MPRS to produce any Industry Reports for MHHS? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Design for the complete solution must be defined by M5. This is a DBT Design Start Blocker No responses This could significantly increase DBT time as development of reports can be costly and time consuming | Closed |  |  |  | Who is raising these requirements? What happens today? Possibly CC issues Agreed with SCS that reporting requirements will be introduced via the CR process. Reporting requirements are to be added to the programme RAID log | No Change |  |  | None
MHHS-DIN-6 |  | T4-COM-1761 DI-7 | 2023-01-30 | St Clements | 2668 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1761 on 15th Sept 2022: IF-005, REG1014 First MAP Block, MAP Eff From Date [DI-054] in message, must = MPAN Install date OR >= Eff Form date of all existing MAP Effective From Dates held in Registration prior to first [DI-054] in message I understand that the First MAP must equal the Install Date, I am unsure what the second condition is trying to say? You can not have a Meter Without a MAP. (ignoring customer owned meters where CUST is used) SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: response is incorrect. The Second Rule "Each subsequent MAP Effective From Date [DI-054] must be > MAP Eff From Date in previous block" covers the subsequent overlapping MAPs. The second half of this First Block Rule must be removed. The First Block can only ever equal the install date No responses, the rule has not been amended | Implemented |  | Interim Release 1 |  | This appears valid - the first MAP block can only start at the creation date (assuming the MAP blocks are in chronological order, which they must be if each subsequent map block has an EFD > the last) Currently the design allows 2 ways to amend the MAP History as outlined in Sections 13 and 14 of the IF005 Use Case Guide. Either the Metering Service can provide the full MAP history from the installation date or they can add a new MAP to the existing history, provided it is the next MAP in chronological order. So for example if you have MAPs 1,2 and 3, then you can extend to MAPs 1,2, 3 and 4 using the approach set out in section 14 to extend the MAP history. However if you wanted to set MAP 4 between 2 and 3, you would need to send the whole MAP history from the install date and provide 1,2,4 and 3 as set out in Section 13 to replace MAP history. The second validation rule is required if you are using the extend the MAP history functionality. Added note to REG Notes that where a MAP history is provided it must be in chronological order Added new REG1014 Validation Rule to MeterInstall and MeterExchange events to ensure only 1 MAP block is provided | Data interface correction | MPAN Ownership | SCS Validation | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-7 |  | DI-8, DI-11, DI-12, DI-14 | 2023-01-30 | St Clements | 2669 | Madison Layton | Software Provider |  | MPRS will reject any PUB-031 inlcuding those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8) | Implemented |  | Interim Release 1 |  | See Comments Revised CSS Registration Request ID validation on IF-031, 034 and 025 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | IF General | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-8 |  | N/A | 2023-02-01 | Elexon | 2642 | Sedef Kiris | Central Body |  | We have had the following comment ........... Also just found out that “Metering Service Id” have “MPID” in brackets afterwards, and not “MSID”. We believe it should be MSID | Closed |  |  |  | MPID is the correct term here, it is the metering service MPID. MHHSP_EDI012_ISD_Entities v4.6 Section M8 | No Change |  |  | None
MHHS-DIN-9 |  | N/A | 2023-01-30 | St Clements | 2672 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: [UpdateSiteTechnicalInfoMS] is not included in the interface catalogue and is not utilised by MPRS. Assume this is related to Issue 99 and needs removing? (raised as DI ID 9) | Implemented |  | Interim Release 1 |  | Removed from IF-005 Guide Section 4.1 | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-10 |  | N/A | 2023-01-30 | St Clements | 2799/2670 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: Is the currently appointed Meter Service informed of Prospective MS changes? Changes to MTDs can be made by prospective MS (e.g. change meter type to complete SEG market change before the MS can be appointed). As the MS is only prospective at this point the MS may still be lapsed and not take effect. However any MTD updates made would remain within the MPRS system and not be backed out. The current MS would therefore need to be aware of what changes have been made by the prospective MS. (raised as DI ID 10) | Closed |  |  |  | BP009 only talks about the Metering Service, not the current or prospective Metering Service, and it appears only the registration service receive metering service MTD details, not the current MS. Refer to SRO - what is the assumption here, as the alternative route is for registration to update the current MS The design is based on PUB-006, with the Updated Meter details, being sent to the current Metering Service ( BP011A step 280 ) as well as the Prospective Metering Service (Step 275). It is built into the routing rules in PUB-006. | No Change |  |  | None
MHHS-DIN-11 |  | N/A | 2023-01-30 | St Clements | 2675 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install / Remove Date(s) takes place within the Metering Services period of ownership (or proposed period of ownership for in the case of a prospective SEG appointment) " Sent on 11th Jan: Does not match business rules, as future dated installs are not allowed: "REG1020 - Meter Install Date [DI-057] cannot take place in the future. The proposed MS on a seg will have a future dated EFD, so they only have the +2 day lapse extension period for meter installs (raised as DI ID 11) | Implemented |  | Interim Release 1 |  | Added change of segment scenario's to IF005 USE CASE Guide. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 |  | Refer back to SCS as additional comentary needed on the issue and bring to next meeting
MHHS-DIN-12 |  | N/A | 2023-01-30 | St Clements | 2679 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install /Remove Date(s), cannot have taken place in the future" Sent on 11th Jan: It would be useful to have the Change of Segment process covered in this guide. We are not sure how the Prospective MS can exchange meters when their appointment period is in the future (raised as DI ID 12) | Implemented |  | Interim Release 1 |  | Nomenclature issue - requires a reword of this statement to conform to the business rules. Recommend the following update to section 3.2 of the IF005 Use Case Guide to confirm who can make Metering updates Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed BAU metering updates ( For the avoidance of doubt not meter update/meter history updates), it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. The one exception, is during a change of segment, when the incoming Metering Service is able to provide a BAU metering update, where it’s prospective “SEG” appointment is due to become active on the same day. SEG scenario's added to IF005 Use case guide Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-13 |  | N/A | 2023-01-30 | St Clements | 2683 | Madison Layton | Software Provider |  | Comment on Section 5.1 "validation allows for meter removal at a point following Disconnection if required)" Sent on 11th Jan: This rule prevents this REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational (raised as DI ID 13) | Implemented |  | Interim Release 1 |  | This statement doesn't appear to be a convention. There is no mention of this in E2E001 End to End Solution Architecture. Believe this statement needs to be amended or removed. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. IF-005 validation Rule changed to include meter removal at status Disconnected | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES138-Interface Catalogue, E2E001 End to End Solution Architecture
MHHS-DIN-14 |  | N/A | 2023-01-30 | St Clements | 2684 | Madison Layton | Software Provider |  | Comment on Section 3.2 "Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed metering updates, it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. " Statement is misleading- the 10 day period is only permitted for install, remove and exchange events, it is not listed for meterUpdate/meterHistoryUpdate in interface catalogue Also the prospective MS should be able to make changes for SEG to enable a market segment change to complete (raised as DI ID 14) | Implemented |  | Interim Release 1 |  | Validation rule(s) updated to constrain 10 day window to non-update events. Test in 3.2 reworded to remove ambiguity. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Refer back to SCS for additional clarity on the requirement and include RecCo and bring to next meeting
MHHS-DIN-15 |  | N/A | 2023-01-30 | St Clements | 2685 | Madison Layton | Software Provider |  | Comment raised in guide, sent on 11th Jan, that the JSON examples use MPID when it should use DIP ID e.g."distributorID": "SWAL" (raised as DI ID 15) | Implemented |  | Interim Release 1 |  | Corrected to use Dist DIP ID | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-16 |  | N/A | 2023-01-30 | St Clements | 2686 | Madison Layton | Software Provider |  | Comment on Section 9 " Albeit that these transactions can be ‘clubbed together’ and send as a group in single overarching message/API transaction. " Sent on 11th Jan: As DIP does not protect the sequencing of events (FIFO), is there a risk that the ordering of these updates might arrive out of sequence resulting in the wrong end state? If MS space out their updates it would reduce this risk (raised as DI ID 16) | Implemented |  | Interim Release 1 |  | Clairifcation added to Sec 9.2 to reference Time-Stamps rather than 'clubbing' | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-17 |  | DI-017 | 2023-01-30 | St Clements | 2690 | Madison Layton | Software Provider | MAP History availability to Metering Service | Section 9 says "a supporting MAP history commencing in line with the revised Installation Date must also be provided" Will the MS know the full MAP history? Risk they could destroy the data. Potential MAP billing issues? | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Solution agreed at DRG on what MAP updates are required. Various document updates required to align with DRG decision to only maintain latest MAP | Missing/incorrect validation rule | Supporting Docs | Various Documents | MHHSP-DES138-Interface Catalogue |  |  |  |  | 14//7
MHHS-DIN-18 |  | N/A | 2023-01-30 | St Clements | 2691 | Madison Layton | Software Provider |  | Comment on Section 9 "• When maintaining the MAP History in cases where there is no change in Meter Installation Date then the MAP history provided should commence either with a MAP Effective From Date matching the existing install date of the meter OR be greater than the most recent, already existing, MAP Effective From Date" Sent on 11th Jan: So it's possible to update ALL MAP history back to installation, or add a new MAP, but it's not possible to amend MAP history only part way back (have to go back to installation date instead every time to do this) (raised as DI ID 18) | Closed |  |  |  | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • To update BRS003, requirement MHHS-BR-RS-027 to add “Registration Service must lapse any appointments that fail this validation” • Remove Rejected from Step 225 of BP002/BPD002 • Remove Rejected from label on line after step 215 of BP003. | No Change |  |  | None
MHHS-DIN-19 |  | N/A | 2023-01-30 | St Clements | 2692 | Madison Layton | Software Provider |  | Comment on Section 10 "E2E Architecture convention states that all data items are provided in each message even where these data items are not changing or are null" Sent on 11th Jan: Some of the items are optional not mandatory which conflicts with this statement. Not all data items need to be provided (raised as DI ID 19) | Implemented |  | Interim Release 1 |  | Update of E2E Doc to allow for Nullable values. | Data interface correction | Meter to Bank |  | MHHSP-E2E001 End-to-End Solution Architecture | 2023-02-23 |  | Defer as a E2E clarification may be needed
MHHS-DIN-20 |  | N/A | 2023-01-30 | St Clements | 2693 | Madison Layton | Software Provider |  | Comment on Section 13, sent on 11th Jan: What should MPRS do if it holds a MAP not included in the MAPHistory block? (raised as DI ID 20) | Implemented |  | Interim Release 1 |  | Update "all existing history will be replaced by that contained within the message" | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-21 |  | N/A | 2023-01-30 | St Clements | 2699 | Madison Layton | Software Provider |  | Comment on Section 15.2 "It is understood that currently there a numerous instances of duplicated Meter ID’s, some of which may have overlapping installation dates. " Sent on Jan 11th: Meter id is only unique at mpan. Should not be any instances of conflicted MSNs at MPAN. Can you verify with ECOES? Or we can do a RFI to DNOs but will take time (raised as DI ID 21) | Implemented |  | Interim Release 1 |  | All references to duplicated MSN IDs has been removed from the document | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-22 |  | N/A | 2023-01-30 | St Clements | 2700 | Madison Layton | Software Provider |  | Comment on Seciton 15.3 "add some kind of suffix (X1, X2) to the existing Meter ID." Sent on Jan 11th: This can take the meter ID over the allowable string length (string 10), in this example it would take it to string(12) and so would be rejected (raised as DI ID 22) | Implemented |  | Interim Release 1 |  | As above, Section 15.3 removed from IF-005 User Guide. | Data interface correction | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-23 |  | N/A | 2023-01-30 | St Clements | 2701 | Madison Layton | Software Provider |  | Comment on Section 16.3 Sent on Jan 11th: Cancelled Flag Set. Only a logical deletion. Still held in MPRS but not visible to EES/MEM The section implies the record would be fully deleted from MPRS, however this is not correct, MPRS would set a cancellation flag that would indicate the record has effectively been cancelled/logically deleted. It would however remain in the systems database (raised as DI ID 23) | Implemented |  | Interim Release 1 |  | Added a statement at the end of the table in 16.3 to say "NB the registration service will only logically delete the MAP entry with a flag, it will not be deleted from the database." | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Accepted
MHHS-DIN-24 |  | N/A | 2023-01-30 | St Clements | 2702 | Madison Layton | Software Provider |  | Comment on Section 17.2 "situations where multiple existing meters are identified, the selection process should be extended to include Meter Removal date (if provided) else;" Sent on Jan 11th: Shouldn’t be possible, can run an EES or MPRS RFI to confirm. Noting that MSN is only unique at an MPAN level not a databse level Related to DI-21 (raised as DI ID 24) | Implemented |  | Interim Release 1 |  | Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. The wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-25 |  | N/A | 2023-01-30 | St Clements | 2706 | Madison Layton | Software Provider |  | Comment on Section 17.2 "where multiple meters still exist even after matching on all three data items should be rejected and require manual intervention (i.e. request to LDSO to intervene) ." Sent on Jan 11th: There's no super user functionality for this so how could the LDSO intervene? The LDSO is not able to manually intervene in regards to MTDs, they can for some other data items such as registration data but not MTDs. (raised as DI ID 25) | Implemented |  | Interim Release 1 |  | Reference to LDSO User Removed - agreed with SCS that scenario should not arise provided existing SCS data rules are met | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-26 |  | N/A | 2023-01-30 | St Clements | 2707 | Madison Layton | Software Provider |  | Comment on Section 17.2 "If the MAP segment is not provided, the existing MAP history should be maintained to greatest degree possible, with ‘trimming’ to align to any revised Install / Remove Dates provided" Sent on Jan 11th: Risk that changing of the Meter Lifespan could result in MAPs being logically deleted. The MS would need to re-apply the MAP history to fit into the new meter Lifespan MS would need to understand this process/constraint (raised as DI ID 26) | Implemented |  | Interim Release 1 |  | Section 17.2 of the guidance document updated. Also added new validation rule REG1014 for MeterHistoryUpdate in IF-005 to ensure MAP is provided when creating a new meter picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-27 |  | N/A | 2023-01-30 | St Clements | 2708 | Madison Layton | Software Provider |  | Comment on Section 19.2 "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the permanent deletion of data, mirroring the existing functionality associated with the use of the D0312." Sent on Jan 11th: Only logically deleted, still visible in the MPRS History. Just not visible to MEM or EES Existing functionality on D0312 utilises cancellation flags not permanent deletion (raised as DI ID 27) | Implemented |  | Interim Release 1 |  | Reword to reflect the logical deletion. See MHHS-DIN-23 Reword this paragraph to: "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the removal of a MAP from a meters MAP history using a logical flag, mirroring the existing functionality associated with the use of the D0312." NB Main section header is incorrect - should be updated to section 19, rather than a duplicate of section 18. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Accepted but note there is another DIN already raised
MHHS-DIN-28 |  | N/A | 2023-01-30 | St Clements | 2709 | Madison Layton | Software Provider |  | Comment on Section 19.4 "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories. However, this would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." Sent on Jan 11th: This functionality already exists with the MPAN History Report showing who changed what when for all MPRS data items. Will be extended to include DIP transactional information (raised as DI ID 28) | Implemented |  | Interim Release 1 |  | Proposed Change Reword this paragraph to: "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories, noting that this is also available via the MPAN history report which will be updated with DIP transactional information and could also be used. Any use of EES would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-29 |  | N/A | 2023-01-30 | St Clements | 2710 | Madison Layton | Software Provider |  | There should be an additional rule for USP, if DI-830/DI-833 is populated, the MS/DS Proposed Effective From Date must equal the currently held EFD for the MS/DS appointment in MPRS (raised as DI 29) | Implemented | 2023-04-27 | Interim Release 1 |  | Added rule for USP scenario in IF-031 to check SP Effective from date. Proposing SCS have flexibility on error codes - requires industry Working Group. Picked up as part of Change of Service Provider review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-30 |  | N/A | 2023-01-30 | St Clements | 2711 | Madison Layton | Software Provider |  | The IF-035 does not provide the opportunity for MPRS to populate a lapsed reason. Will need to be able to provide a reason for a lapsed appointment, otherwise there'll be a higher volume of unecessary supplier enquries to DNOs which will require more resource and cost. (raised as DI 30) | Implemented |  | Interim Release 1 |  | Additional Data Item on IF-035 for a reason comment - what reasons would these be other than gone beyond the date? Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-31 |  | N/A | 2023-01-30 | St Clements | 2712 | Madison Layton | Software Provider |  | MHHS-BR-RS-027 "Registration Service must re-run validation, in line with the validation rules set out in the appropriate interface specification, for all Metering Service appointments that have been confirmed to re-process from the Prospective Appointment Queue, to ensure that the appointment is still valid" It is not clear if MPRS would send MSAppRejected or MSAppLapsed if the appointment fails validation after it's been queued? If this is not made clear in the deisgn then there is a risk that we build to use the wrong event code, or if the code should be MSAppRejected then risk that suppliers build a design where they can't process a MSAppRejected after receiving already an MSAppAccepted from MPRS (raised as DI 31) | Implemented |  | Interim Release 1 |  | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • Updated BRS003, requirement MHHS-BR-RS-032 and 66 to show that appointments will be lapsed (not rejected) • Remove Rejected from Step 225 of BP002/BPD002 Also on BP003 leading from step 215 should have the rejected removed. Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Corrections also to BPM002 & BPM003 Forward Migration and BPD002 Froward Migration | Data interface correction | MPAN Ownership |  | MHHSP-BP002-Change of Service - Metering service, BPD002,MHHSP-BRS003-Registration Service requirements MHHSP-DES138-Interface Catalogue, MHHSP-BP003, MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration), MHHS-DEL969-BPD002 (forward migration) | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-32 |  | N/A | 2023-01-30 | St Clements | 2713 | Madison Layton | Software Provider |  | The interface catalogue lists setting a removal date as an action that can be used with event code meterUpdate on IF-005, however in the interface catalogue, the block B039 does not list meterUpdate as a event code that can utilise this block. Need greater clarity on whether meterUpdate and meterHistoryUpdate should apply meter installations and meter removals or not. (raised as DI 33) | Implemented |  | Interim Release 1 |  | The definition of a [MeterUpdate] event code is: Allows currently appointed Metering Service to amend the details associated with a currently installed meter. Therefore the appointed Metering Service must be able to remove the meter as part of an update, this is an omission from the design and a small update to IF-005 The design principle that IF-005 works on is that: • BAU transactions (Install/Exchange/Remove) that are in the Metering Services Period of ownership are covered by the Install/Exchange/Remove events • Changes to currently installed metering can be made by the Appointed Metering Service using the Meter Update event. Note this therefore includes, where required, removing the currently installed meter where it is prior to the current period of ownership. • Changes to metering history ( ie not the currently installed meter ) can be made by the Appointed Metering Service using the Meter History Update Proposed changes: Added MeterUpdate as Optional to B039 block in IF-005 and added validation rule to ensure MeterUpdate is not used to remove meters in current period of ownership picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP-DELS229-IF-005 Use Case Guide | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-33 |  | T4-COM-1759 | 2023-01-30 | St Clements | 2719 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1759 on 15th Sept 2022: IF-005, REG1011 Install date must be > Creation date, should this REG1011 rule apply also to meter Exchange not just meter install SCS raised as a design blocker on 7th October 2022 Still no resolution, should this rule apply to meterHistoryUpdate at least as this allows for meter installations (raised as DI 34) | Implemented |  | Interim Release 1 |  | An exchange will not be a creation date, and the validation already in place ensures that future installation dates will all follow each other, which means this rule isn't required. ​This shouldn't be needed for exchanges, as its covered by REG1008 (install date >= remove date), as an exchange would replace an existing meter, which at first install would be validated against creation date. Moved REG1011 to cover all scenarios in IF005 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-34 |  | T4-COM-1774 | 2023-01-30 | St Clements | 2720 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1774 on 15th Sept 2022: IF-005, REG1011 "REG1009 - MAP ID [DI_055] is not valid for MAP Effective Date [DI-054] REG1011 - Install Date [DI-057] for MeterID [DI-056] is prior to MPAN Creation Date There are many meters in MPRS that pre-date the existence of the MAP and also MPRS install dates of 1980 etc. these will break a number of rules. should these be cleansed before MHHS start? If they are valid, then the rules need adjusting"l SCS raised as a design blocker on 7th October 2022 Still no resolution (raised as DI 35) | Closed |  |  |  | This could be a data cleanse requirement which is a consequential change/transition requirement, but for REG1009 - the MAP effective date should be the point at which the MAP took over the meter, and the exchange date should be after this (ie it should be after the date MHHS goes live). For Reg 1011 currently this is only valid on installs (and installs won't occur on legacy meters). If Reg 1011 is valid on exchanges, then the exchange date should also be after the MPAN creation date - if it isn't then the data should be cleansed. Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-35 |  | N/A | 2023-01-30 | St Clements | 2721 | Madison Layton | Software Provider |  | On the IF-005, should REG1028 (Install date cannot be null or blank) apply to meterinstall, meter exchange and meterupdate too? (raised as DI 36) | Implemented |  | Interim Release 1 |  | Requires amendment to interface validation - look at alternative validation Agree the rule should also apply for those events. Note we believe validation would fail for another reason. Eg REG1019 Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-36 |  | DI-37 | 2023-01-30 | St Clements | 2722 | Madison Layton | Software Provider | Re-alignment of rejection reasons to main block | In the summary of error codes box at the bottom of IF-005 tab the rejection reasons need re-aligning to the main block, e.g. REG1001 should read RMP stats must be Created or Operational, not just Operational As a general note across all interfaces, the rejection codes are referenced in numerous places and the respective descriptions are in many places not consistent for the same rejection code (raised as DI 37) | Closed |  |  |  | Will be revisited once SCS provide definative Error Code Texts | No Change |  |  |  | 2023-02-23 | 23/2/23 - Not discussed at meeting carry to next meeting
MHHS-DIN-37 |  | N/A | 2023-01-30 | St Clements | 2723 | Madison Layton | Software Provider |  | REG1015 (cannot be removed meter) is listed for meterHistoryUpdate in interface catalogue for IF-005. This should actually apply to meterUpdate not meterHistoryUpdate, REG1018 (cannot be installed meter) applies to metering history update (raised as DI 38) | Implemented |  | Interim Release 1 |  | Change accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-38 |  | N/A | 2023-01-30 | St Clements | 2724 | Madison Layton | Software Provider |  | In the interface catalogue, the IHD block B030 for IF-005 should also be optional for meterUpdate according to the IF-005 guide Section 16 Development Notes "The IHD segment, if provided as part of [MeterUpdate], relating to any currently installed meter should replace/update the IHD details currently held at the MPAN to which that Meter is associated." (raised as DI 39) | Implemented |  | Interim Release 1 |  | Small change to schema operation IHD information may be updated as part of the [MeterUpdate] event. The change is to add [MeterUpdate] event to block B030, so it now reads "B030 - MPAN IHD Information (Optional & may only be used with [MeterInstall],[MeterExchange],[MeterUpdate]) NB this also standardises the use of commas between event codes, rather than using the & symbol. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-39 |  | N/A | 2023-01-30 | St Clements | 2725 | Madison Layton | Software Provider |  | In interface catalogue for IF-005, there needs to be a rule that if event code MeterInstall is used, then modified meter ID cannot be populated (raised as DI 40) | Implemented |  | Interim Release 1 |  | Update agreed | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-40 |  |  | 2023-02-01 | SI Design |  |  |  |  | Not used - raised as duplicate in error | Closed
MHHS-DIN-41 |  | N/A | 2023-01-30 | St Clements | 2730 | Madison Layton | Software Provider |  | In interface catalogue IF-005: The REG1003 reads Metering Service [S0.SenderID] holds valid previous appointment then Meter Install Date [DI-57] should be < [REG.App End Date] + 10 The way it's curently written suggests MPRS should accept an IF-005 from the previous appoint, even if their ETD was greater than 10 days ago, provided the install date was less than their ETD + 10. E.g the previous MS could send IF-005 two years later with Install date of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then REG1002/REG1019 should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? (Raised as DI 41) | Implemented |  | Interim Release 1 |  | Having looked through IF-005 Dates should be within the appointment date, and current deign does give the ability to go outside this Change the validation rule for REG1003 on events [MeterExchange], [MeterInstall] and [MeterRemoval] to "If Metering Service [S0.SenderID] holds valid previous appointment then [system date] < [REG.App End Date] + 10" Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. Rule amended after review by SCS, to remove second "if" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-42 |  | N/A | 2023-01-30 | St Clements | 2784 | Madison Layton | Software Provider |  | In interface catalogue IF-005: Meter Update should apply validation REG1027 (current MS or prospective MS) not REG1012 (current MS only) to allow the prospective queued MS to update the Meter Type on a SEG change and therfore complete the market segment change and appointment. MHHS-BR-RS-132 . If the SEG prospective appointment was not allowed to update on meterUpdate event code then they would not be able to update the meter type to completed change of market segment, and would not meet the conditions needed to then be appointed in MPRS, their appointment would then lapse and market segment would remain invalid. (Raised as DI 42) | Closed |  |  |  | We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error... | No Change |  |  | None
MHHS-DIN-43 |  | N/A | 2023-01-30 | St Clements | 2732 | Madison Layton | Software Provider |  | In Interface Catalogue, on If-005, REG1002 and REG1019 are duplicates (install/removal dates should be within MS period of ownership). We can only use one of the rejection codes and descriptions, programme should choose which one to keep and remove the other. (Raised as DI 43) | Closed |  |  |  | These are testing slightly different things. The first test (REG1002) is checking that the Metering Service is an eligible party to send the request ie currently appointed OR was at the time of the install (to cover for previous Metering Services updating in the 10 day window). The second (REG1019) is checking that the Install Date is in the Metering Services period of ownership. So you could have that the Metering Service is currently appointed, but that they weren't at the install date. Eg Today is 2nd Feb, Meter installed on 27th Jan, Sending MS was appointed on 1st Feb REG1002 would pass as they are eligible as the currently appointed MS REG1019 would fail as they are not appointed at the time of the install Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-44 |  | N/A | 2023-01-30 | St Clements | 2733 | Madison Layton | Software Provider |  | Should the new rule for meter update in IF-005 also apply to meter history update? If no MAP entries provided, and revised Meter Install / Remove Dates result in no valid MAM History then reject with REGE1014 – MAP Eff From Sequence Error (Raised as DI 44) | Implemented |  | Interim Release 1 |  | Added REG1014 ( MAP History ) to IF-005 MeterHistoryUpdate event | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-45 |  | N/A | 2023-01-30 | St Clements | 2736 | Madison Layton | Software Provider |  | New rule for IF-005 Meter Update REG1017 could be misinterpreted as it currently reads incorrectly - need brackets to correct to how the AND and AND/OR conditions are to be applied If [DI-60] is not null AND Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null) Should read If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null)) (Raised as DI 45) | Implemented |  | Interim Release 1 |  | Clarification of existing design rule Change the validation rule for REG1017 to: "If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null))" picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-46 |  | N/A | 2023-01-30 | St Clements | 2737 | Madison Layton | Software Provider |  | on IF-005 for Meter Exchange and meter install the rule for REG1027 has been changed, but I'm not sure the wording implements the rule intended exactly? Currently it reads as The MS must be the currently appoint MS AND the install date must be > MS EFD AND the MS must not have proposed MS app with SEG scenario in the queue. If not then reject with REG1027 - Metering Service is not currently appointed and does not hold a Prospective SEG Appointment SHould the rule actually read The MS must be the current MS OR the MS must have a proposed MS App in the queue with SEG scenario And then the other part of the rule about install date > MS should be a separate rule (with REG1019 error code). (Raised as DI 46) | Implemented |  | Interim Release 1 |  | Sent to Mike F for validation - SI believe wording in current documentation is correct. Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. I would suggest the wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. DIN-46 – On review we agree, the date test should always be true if REG1019 is satisfied ( with minor clarification update ), so validation rules should be updated as below: Proposed changes: REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 |  | Not discussed at meeting carry to next meeting
MHHS-DIN-47 |  | N/A | 2023-01-30 | St Clements | 2738 | Madison Layton | Software Provider |  | REG1001 on IF-005 does not allow for meters to be removed after a disconnection. Instead should restrict for allow other event codes but allow Status Terminated for MeterRemoval. DES204 CCR-0556 Linked to DI-13 | Implemented |  | Interim Release 1 |  | Rule update required picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-48 |  | DI-048 | 2023-01-30 | St Clements | 2739 | Madison Layton | Software Provider | CSS failure to apply CoS to related secondary MPANs | Unhappy path scenario:- What happens if, for whatever reason, CSS fails to apply CoS to all the related secondary MPANs MPRS receives IF-031 on primary RMP to change agent, MPRS applies this to all seocndary MPANs too But if the CoS was not received from CSS for secondary MPANs that the secondary MPANs would still currently be held for the wrong supplier Would this cause any issues downstream? (Raised as DI 48) | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | CSS Defects issue. Agreed that Risk would be raised and all CSS related issued assessed at a later date | Other | MPAN Ownership | Related MPANs | [5 empty] | 2023-07-14
MHHS-DIN-49 |  | N/A | 2023-01-30 | St Clements | 2740 | Madison Layton | Software Provider |  | Unhappy path scenario:- If MPRS sends a IF-033 but never receives back a IF-034 then the rest of the process will not continue. The Supplier will never receive the IF-035 they are waiting for and the SP would never get appointed by MPRS. Is there a process in place to detect/resolve this scenario? (Raised as DI 49) | Closed |  |  |  | There is a requirement for the Supplier to monitor for any delayed responses and request an update if not received in expected timescales. Reviewed with SCS and agreed ticket can be closed | No Change |  |  | None
MHHS-DIN-50 |  | N/A | 2023-01-30 | St Clements | 2741 | Madison Layton | Software Provider |  | We need clear rules to define what a valid Consent granularity looks like. Current rules don’t mention any validation around EDI. (Raised as DI 50) | Implemented |  | Interim Release 1 |  | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-51 |  | DI-51 | 2023-01-30 | St Clements | 2747 | Madison Layton | Software Provider | St Clements Design Query - DI 51 | We have had some feedback from DNOs asking about how systems will recover from System Misalignment because of data errors or significant downtime? We have the D0204 (Supplier) and D0209 (Data Aggregator) Refresh functions today which are not being replaced with a DIP message equivalent. I am aware of the DIP Replay function, but this wouldn’t be of any help if there were data errors, as the DIP would just be replaying the incorrect data. The Source system would need to re-send the corrected data in an agreed format. I know there is a design principle to move away from bulk loads and refreshes of data, Faster Switching took a similar approach. However today, CSS leans heavily on the MPRS Refresh function to get itself back inline and there are REC CP’s being raised to add a Refresh function to CSS for all parties (first CP being R0067). DNO’s are keen to understand the MHHS Programme’s position on and if Refresh functionality should be built into MPRS for MHHS. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | Refresh Functionality was rejected by the Working Groups so not in current design. Scenarios required. | Other | Supporting Docs | Refresh Process? | [5 empty] | 2023-07-14
MHHS-DIN-52 |  | DI-52 | 2023-01-30 | St Clements | 2748 | Madison Layton | Software Provider |  | For IF-005, REG-1006 and REG1013, would it make sense to include the installation date of the MPAN already in the system in the rejection description too to help MS with triage? | Closed | 2023-04-27 |  |  | DIN closed as instructed by St Clements. Old comments: Discussed with SCS potential for them to have flexibility on error messages. Industry agreement required. Participant Discussion Required | No Change |  |  |  | 2023-02-23 |  | Not discussed at meeting carry to next meeting
MHHS-DIN-53 |  | N/A | 2023-01-30 | St Clements | 2749 | Madison Layton | Software Provider |  | Requirement on LDSO requirements spreadsheet: MHHS-BR-LD-035 LDSO Maintain DUoS Tariff ID LDSO must set Duos Tariff ID on MPAN creation and maintain DUoS Tariff ID's in line with their Charging Method Statement. This should include updating the Duos Tariff ID, as required, following any updates to Domestic Premise Indicator, Connection Type and Energy Direction Note for MHHS, LLFC ID is being renamed as DUoS Tariff ID to make it clearer what this data item is used for. "BP010B Change of registration data" 250 However missing the respective requirement for Registration Services in the Registration Services Requirements spreadsheet | Closed |  |  |  | Looked through the Registration Services Requirements spreadsheet v4.6 and it looks like DUoS Tariff ID is there - MHHS-BR-RS-091.1, MHHS-BR-RS-121 and MHHS-BR-RS-122 | No Change |  |  | None
MHHS-DIN-54 |  | N/A | 2023-01-30 | St Clements | 2750 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1699 on 15th Sept 2022: On the IF-031 and IF-035 there are a number of "Proposed" Data items. Should MPRS load these and updated the stored data items. Or are these data items only for passing through to Supplier and Service? SCS raised as a design blocker on 7th October 2022 We have some clarity verbally on this but nothing has been formally documented in the design artefacts. This needs to be reflected somewhere in the requirements. | Implemented |  | Interim Release 1 |  | Added "Appoinments - Data" section in REG Notes to highlight what data becomes effective with the appointment. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-55 |  | T4-COM-1738 | 2023-01-30 | St Clements | 2751 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1738 on 15th Sept 2022: the DB02 flow updates multiple data items on the IF-018 in one event. Can multiple EventCode be included in one IF-018 or will MPRS need to generate an individual IF-018 for each EventCode? SCS received a blank response and raised as a design blocker on 7th October 2022 | Closed |  |  |  | Original response was that clarification was to be provided on 24th Oct - is this available? Which document? One at a time | No Change |  |  | None
MHHS-DIN-56 |  | T4-COM-1742 | 2023-01-30 | St Clements | 2752 | Madison Layton | Software Provider | Manual Correction to MHHS data items | Originally raised as T4-COM-1742 on 15th Sept 2022: BSCP604 currently allows LDSO and Suppliers to request manual corrections to Data Items held in MPRS. Will this type of Manual Correction be allowed in MHHS, if yes then this should be added to the business process to capture manual amendments and how these changes are reflected back to DIP users (IF-018 & IF-026, or a new Refresh Message?) SCS received a blank response and raised as a design blocker on 7th October 2022 Another exaple of this: If the MS/DS history is incorrect and cannot be amended via BAU, would the DNO be able to correct this via an exceptional error handling process? | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | Original response was: This has been raised as potential consequential change utilising SDEP Nothing in design, would want updates via a flow to maintain sychronisation. Requires a change to implement, request specific data items requested - needs to be related to settlement, needs to be updated via appropriate flow. | Requirement correction | MPAN Ownership | CSS Defects | MHHS-BPD005 Data Processing, MHHS-BRS005 LDSO overview |  |  |  |  | 2023-07-14
MHHS-DIN-57 |  | T4-COM-1748 | 2023-01-30 | St Clements | 2756 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1748 on 15th Sept 2022: "Additional information field DI-120 is String200, where the existing DB03 allows a free text field of 2000 characters" SCS raised as a design blocker on 7th October 2022 This was corrected but then in v4.5 artefacts released there was a change back for DI-120 addition infromation field from string 2000 to string 200 in the interface catalogue data catalogue tab reintroducing the issue. For disconnection additional notes MPRS database holds 2000 characters so this field will need to be string 2000 in the IF interfaces (Raised as DI 57) | Closed |  |  |  | Change to the data catalogue included in the 4.7 baseline | No Change |  |  | None
MHHS-DIN-58 |  | T4-COM-1789 | 2023-01-30 | St Clements | 2757 | Madison Layton | Software Provider | Valid combinations of ISD data for MPRS validation development | Originally raised as T4-COM-1789 on 15th Sept 2022: "Valid combinations of data in ISD are critical to the MPRS validation development, we must have these defined and agreed before we can start development" SCS raised as a design blocker on 7th October 2022 | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-13 | Elexon is defining the valid combinations of data in the ISD. Parties need to define their own data. | Requirement correction | Supporting Docs | ISD | MHHSP-EM021 ISD Entity Map |  |  |  |  | 2023-07-14
MHHS-DIN-59 |  | T4-COM-1707 | 2023-01-30 | St Clements | 2758 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1707 on 15th Sept 2022: "The Smart DS for Export and Secondary MPANs can be different to the Import/Primary DS as the Customer can choose their own DS for Export and Primary (Smart only)" The IF-031 validation rules have been amended but they are still not corrrectly reflecting the rule. The heading above both rules REG1038 and REG1039 reads: "If event type = [MSApp] OR event type [DSApp] & MPAN Segment is not 'Smart'" This heading should ONLY apply to REG1038 for linked MPANs and should not apply to REG1039 concerning related MPANs It should also have brackets to clarify the logic otherwise it could be misinterpreted e.g. "If event type = [MSApp] OR (event type [DSApp] & MPAN Segment is not 'Smart')" | Implemented |  | Interim Release 1 |  | This seems a valid issue. REG 1039 on linked meters should be allowed for trad meters (eg economy 7) Proposed Change: The logic issue here is that REG1039 caters for related meters, which are applicable to trad as well as smart meters. Remove REG1039 from this validation Change the validation to: "If (event type = [MSApp] OR event type [DSApp]) & MPAN Segment is not 'Smart'" Updated heading above REG1038 and added heading above REG1039 to clarify the validation rule in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-60 |  | T4-COM-1708 | 2023-01-30 | St Clements | 2759 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1708 on 15th Sept 2022: "The Service Appointment Date must be equal to the SSD or there will be a period with no Service" And T4-COM-1776 also on 15th September 2022 "REG1032 - Metering Service Eff From Date [DI-830] is not contiguous - Appointment must be from [Max[Reg.MPAN_SSD] ,[Reg.ExistingMSAppFrmDate]] for a COS, it can only equal the SSD otherwise there will be a gap" This has been applied incorrectly. In IF031 rules REG1032 now reads that the MS/DS prop EFD must be = Max(SSD, existing MS/DS EFD + 1) This would restrict the MS/DS to setting the new EFD to either SSD or the day after the last MS/DS appointment, and all other dates would be rejected. It should read >= not just =. All four refrences to REG1032 in the validation rules for IF-031 references the +1 day after EFD, but the rejection description in the right hand columns for 'scneario not SEG or CoS' section does not reference this + 1. This should be corrected to be consistent with the other rules. (Raised as DI 60) | Implemented |  | Interim Release 1 |  | Original response to 1708: New rules added to cover all scenarios Original response to 1776: Change to be incorporated into design artefact Updated REG 1032 validation in IF-031, original single rule, split into 2 separate rules picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-61 |  | T4-COM-1445 | 2023-01-30 | St Clements | 2760 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1445 on 15th Sept 2022: "There is no mechanism to update the Profile Class. We would assume that this would be updated by the Supplier (with business rules restricting when this should be set) and confirmed on the IF-026. Please can you confirm if this is the intention or if it will be updated through another route. If so, the EES would need to know which PUB would confirm the data item had been updated. " Whilst this is now included in the design the validation rules from D0205 have not been carried over, e.g. PC/SSC need to be a valid combination. ISD will need to contain the valid PC/SSC Combinations (previously MDD Entity 11) and the validation rules in the interface catalogue will need to reference this validation against the ISD valid combinations. (Raised as DI 61) | Implemented |  | Interim Release 1 |  | See also DIN-58, need to find out who is defining ISD validation Updated Interface notes in IF-025 to confirm that there is no Profile Class/ SSC combination checks | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-62 |  | DI-062 | 2023-01-30 | St Clements | 2761 | Madison Layton | Software Provider |  | In the business process diagram for Registration Updates MHHSP-BP010-Change of Registation Data - v4.5, the MPL update section, the C0300 has been changed to C0400 which is incorrect, C0400 is for MAP updates. Address updates are actually sent in the C0600. (Raised as DI 62) Change raised 30 March:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly. | Implemented |  | Interim Release 1 |  | Also in the BPD. MHHS-BR-RS-114 also confirms this should be C0300, this appears to be a straightforward typo. Amend label between Step 20 and Step 30 on BP010A to CSS0300, and update the corresponding BPD description on step 30 Update required:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly in BP010A, BPD010 and in MHHS-BR-RS-114. | Process model correction | Metering Changes | MPAN Updates | MHHSP-BP010-Change of Registration Data MHHSP-BPD010 MHHSP-BRS003
MHHS-DIN-63 |  | DI-063 | 2023-01-30 | St Clements | 2792 | Madison Layton | Software Provider |  | In the business process diag for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 (Raised as DI 63) | Closed |  |  |  | SCS have now confirmed that C0700 is the correct reference - no need to change documentation - agreed to close | No Change | MPAN Ownership | Disconnection | MHHSP-BP007-Disconnection MHHSP-BPD007
MHHS-DIN-64 |  | N/A | 2023-01-30 | St Clements | 2793 | Madison Layton | Software Provider |  | In business process diag for change of data service MHHSP-BP003-Change of Service- Data Service-v4.5 and MHHSP-BP002-Change of Service- Metering Service v3.5, this still makes reference to D0386 in the purple note boxes. This should now have changed to IF-019 (Raised as DI 64) | Implemented |  | Interim Release 1 |  | Update notes on BP002 and BP003 from D0386 to IF-019, and for BPM002 & BPM003 (forward migration) | Process model correction | MPAN Ownership | Change of DS | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-65 |  | N/A | 2023-01-30 | St Clements | 2794 | Madison Layton | Software Provider |  | The business process diagram for change to connection type/market segment has been amended to name only DB01, connection type is set on DB01 but it can then be changed on DB02 (Raised as DI 65) | Implemented |  | Interim Release 1 |  | Update label between step 220 and 225 from "DB-001" to "DB02" | Process model correction | Metering Changes | Market Segement | MHHSP-BP011-Change of Connection Type or Mkt Segment
MHHS-DIN-66 |  | N/A | 2023-01-30 | St Clements | 2795 | Madison Layton | Software Provider |  | In interface catalogue, on IF-031, shouldn't rule REG1036 (MDR app EFD must be after DS app EFD), be applicable to all scenarios including SEG? Currently under section for if not SEG (Raised as DI 66) | Implemented |  | Interim Release 1 |  | Updated validation rule for REG1036 and made applicable to all scenario's in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-67 |  | N/A | 2023-01-30 | St Clements | 2796 | Madison Layton | Software Provider |  | Currently no rule on IF-031 that the SP appointment has to be within the prospective suppliers registration period - just that it can't be past dated. This rule will need to be added. (Raised as DI 67) | Closed |  |  |  | Reviewed with SCS and agreed that this validation is covered by existing rules. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-68 |  | N/A | 2023-01-30 | St Clements | 2797 | Madison Layton | Software Provider |  | If-031 business rule missing If the Scenario is USP, the consent granularity must be the same as the existing consent granularity held within MPRS (Updates should be through IF-025 not through IF-031) (Raised as DI 68) | Implemented |  | Interim Release 1 |  | picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Updated Interface notes in IF-031 to clarify that Registration Service will ignore any differences in Domestic Premise Indicator/ Consent Granularity sent on IF-031 (USP scenario) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-69 |  | N/A | 2023-02-02 | ESG Global | 2653 | Luke Speakes | Software Provider |  | PUB-033 - Block 029 is conditionally mandatory for DCC Commissioned Meters, but includes DI-025 DCC Service Flag with valid values of A-Active, I-Installed Not Commissioned, N - Non Active. The title of the block, which should define whether it is mandatory or not, is not appropriate if a DCC meter has been installed and not commissioned, or is inactive. Propose following SI and SRO design discussion that title of block 029 is revised to conditionally mandatory for 'DCC Smart Meters' | Implemented |  | Interim Release 1 |  | Concludes this can be resolved by a minor wording change to the block title | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 |  | Not discussed at meeting carry to next meeting
MHHS-DIN-70 |  | N/A | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory | Addition of MDR validation rule | Elexon is required to maintain a valid list of Meter Data Retrievers in Industry Standing Data, to allow RegService to validate they're suitably qualified (DCC and SEC) MDRs are being appointed. | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Design Agreement is to utilise M16 for this purpose. Propose to update ISD document with details and examples to this effect. | Other | Supporting Docs | ISD | MHHSP-DES138-Interface Catalogue - probable updates to relevant BP/BPD/BRS | 2023-02-23 |  | Not discussed at meeting carry to next meeting |  | 2023-07-14
MHHS-DIN-71 |  | N/A | 2023-01-30 | St Clements | 2839 | Madison Layton | Software Provider |  | When would event code [MSDeAppUpdate] and [DSDeAppUpdate] be used for on an IF-037? (Raised as DI 69) | Closed |  |  |  | Reviewed with SCS and it is used to notify the incoming Service Providers when de-appointing and not origanally known. In case of Linked/Related MPANs individual MPANs move through the process. RS need to apply the logic for sending the updated IF-037 to all MPANs. Agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-72 |  | N/A | 2023-01-30 | St Clements | 2840 | Madison Layton | Software Provider |  | Block B018 on IF-034 and IF-035 should not be mandatory - it will only be provided for smart meters. This needs to be set to mandatory for SDS-MDRUpdate only, optional for DSAppSPResponse (Raised as DI 70) | Implemented |  | Interim Release 1 |  | Updated B018 block to be optional for non Smart on IF-034 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-73 |  | N/A | 2023-01-30 | St Clements | 2841 | Madison Layton | Software Provider |  | IF-026/IF-025, added new event code [SSCandProfileClass], but still kept in original [SSC] and [ProfileClass] event codes, should the original two have been removed? Particularly as the B032 group says it's madatory where event code is [SSCandProfileClass] and does not refer to [SSC] or [ProfileClass] individual event codes (Raised as DI 71) | Implemented |  | Interim Release 1 |  | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-74 |  | N/A | 2023-01-30 | St Clements | 2842 | Madison Layton | Software Provider |  | A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a new MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60 (Raised as DI 72) | Implemented |  | Interim Release 1 |  | This appears to be the reciprical change to MHHS-DIN-60 for the response interface Update description to "Check if MDR Eff Date = SSD OR on or after existing MDR Eff From + 1" Update rule to "If [DI-841] <>SSD OR <MDR Eff Date + 1" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-75 |  | N/A | 2023-01-30 | St Clements | 2843 | Madison Layton | Software Provider |  | On IF-035, overidden the description for Data Item 836 incorrectly with the description for Data Item 838 (Raised as DI 73) | Implemented |  | Interim Release 1 |  | Update the definition field based on the description in the data catalogue for DI-836 on IF-035 (Date From which Supplier would like Nominated MDR to take effect) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-76 |  | N/A | 2023-01-30 | St Clements | 2844 | Madison Layton | Software Provider |  | Data catalogue - changed the estimation reason code authoritative source to Registration Service, this data item is not received by, sent by or held by registration services and so the authoritative sourse cannot be Registration Service (Raised as DI 74) | Implemented |  | Interim Release 1 |  | The authoriative source has changed between v4.0 (from Data Service) to 4.7 (Registration Service) - have asked why the change was made, and what the authoritative source should actually be. Source updated to SDS/MDS | Data interface correction | Meter to Bank | Estimation | MHHSP-DES138-Interface Catalogue
MHHS-DIN-77 |  | N/A | 2023-01-30 | St Clements | 2845 | Madison Layton | Software Provider |  | Data catalogue - Added issue 99 items (CT Ratio, Phases etc) DI-170 - DI-180. Was agreed in work off meeting these items are not within the scope of MHHS, to introduce these would require a CR (Raised as DI 75) | Implemented |  | Interim Release 1 |  | these data items don't appear to be used in any interfaces so this could be a relatively simple change to remove 11 items from the data catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-78 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E0404 requirement is blank - row needs to be deleted | Closed |  |  |  | This update was already incorporated into version 5.0 closing it here | No Change | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-79 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E21114 typo - should be VAS Output Retention | Implemented |  | Interim Release 1 |  | change as per description | Technical corrrection | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-80 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHSP-DES138-Interface Catalogue v4.6 - DI-846 Issuing Data Service EZ Name should be scored through in IF/ PUB21 definition | Closed |  |  |  | Completed in V5.0, part can review change as part of Interim Release 2 | No Change | Meter to Bank | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-81 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier | Correction of step in BP020 | MHHSP - BP020 - Volume Allocation Service (ECS) v4.6 - Step 75 to Step 80 references report “REP-00” - needs correcting | Implemented |  | Interim Release 2 | 2023-06-23 | BP020 step 75 to step 80 process flow REP list correction BPD020 step 75 & step 80 detail list of REP's correction | Process Model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions |  |  |  |  | 2023-06-16
MHHS-DIN-82 |  | N/A | 2023-02-09 | SI Design | 2716 | Rob Short | SI Design | Missing listed number of reports in BPD002 | Related to DIN-81 - BPD002 lists number of reports at step 75, BP002 does not reflect this list, missing PO275, PO214 and PO213 | Implemented |  | Interim Release 2 | 2023-06-23 | This relates to BP020 (not BP002), similar to DIN81, reconcile REP list correction on BP020 at step 75 and 80 and reconcile with BPD020 list of REPs | Process model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions |  |  |  |  | 2023-06-16
MHHS-DIN-83 |  | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | BP011 missing PUB-044 flow | A discrepancy with the Interface Catalogue - IF_LIST states MHHSP-IF-044 is sent to Central Settlements, DS, MS, Supplier, LDSO. IF-044 tab states it is sent to Supplier, MDS, LDSO In BP011 the PUB-044 is not sent to DS only Supplier, Settlements and EES | Implemented |  | Interim Release 2 | 2023-06-23 | Add Manage change of segment in LDSO lane on business process BP011C with a PUB-044 flow from step 570 Add new step to BPD011 Interface catalogue is already updated | Process Model correction | Metering Changes | Interface Catalogue | MHHSP-BP011 Change of ConType andor Mkt Segment MHHSP-BPD011 MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-84 |  | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | DES-138 IF List Tab Consistency | IF_LIST states MHHSP-IF-020 is sent to Supplier onlyIF-020 states it is sent to Supplier, Data Service, Metering Service, LDSOIn BP010, the PUB-020 is sent to Central Settlements, CSS, EES, Supplier, Data Service, Metering Service, LDSO.This one looks like its just the Interface Catalogue that needs updating. IF-020 Updated to refect new agreed Routing | Implemented |  | Interim Release 2 | 2023-06-23 | Updated parties receiving PUB-020 in the IF_LIST, updated PUB-020 routing to include MDS for Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-85 |  |  | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory |  | Elexon see DIP qualification for new users being part of market entry post-programme, but want to understand how MHHSP will operate qualification during the programme. This is likely to cover the majority of participants. Discussions with SRO colleagues indicate they are assuming this is a process for the Enduring Service Operator to define. Challenge applies to non-BSC DIP participants (e.g. adaptor providers), and considerations under Issue Group 101. SI design has spoken to at least 4 participants who are operating in this space and seeking to understand how they can engage with SIT and other programme activities as a DIP connection provider (E2E Architecture - 3.3.2) | Closed |  |  |  | To be handled as part of the Placing Reliance document | No Change | Qualification | Qualification | New Process - DIP Qualification for New Users
MHHS-DIN-86 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Invalid Market Segment BP011C requires SMRS to notify the Supplier of an invalid market segment. RegService requirement RS0124 states that SMRS must derive a value for Market Segment based on Connection Type and Meter Type following a Change of Metering, Change of Connection Type (Change of Unmetered Indicator) or Change of Related MPAN relationships. Given that SMRS determines segment as above, when would an invalid market segment occur, giving rise to the processes from step 560 in BP011C? Further, upon receipt of a PUB-045 Market Segment Invalid Advisory Notification, what are the next steps for a Supplier to address the issue? There are no provisions in the IF-025 for Suppliers to update Market Segment. | Closed |  |  | 2023-07-12 | Part of ongoing discussions with Code Drafting team 20/4//23 Code Drafting believe an update needs to be made to the design to update Market Segment via IF-25. This could occur when a Supplier is trying to arrange a change of segment but one of the activities has not completed on time eg the new metering has not been notified. When Registration Service tries to evaluate the segment it may not be compatible. Notification would then go to Supplier to prompt them to chase the required update, in this example chasing the Metering Service to provide the new metering details. Another example is if the LDSO has not notified a change of connection type. The Supplier may also need to send a further SEG appointment if the original has lapsed. | No Change | Metering Changes | Change of Connection Type and/or Market Segment | MHHSP-BP011, MHHSP-BPD011
MHHS-DIN-87 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory | Process clarification for meter removal and de-energisation on same job | Energisation Process Clarification BP009 states that change of energisation status at the same time as meter works means that BP008 will be followed - what is the process when a meter removal and de-energisation are carried out in the same job? Are both D0139 (de-energise) and D0142 (remove meter) and relevant DIP interfaces required. At the moment MEMs only have to send flows relating to meter removal | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | New Purple Boxes to be added in BP009 and BP008 to make it clear that Remove/DeEn could still be requested and carried out but MS would need to send two interfaces. Also that DeEn did not need to be notified if meter works completed within same day (ie same rules as today) | Process model correction | Metering Changes | Change of Metering | MHHSP-BP009, MHHSP-BPD009 |  |  |  |  | 2023-07-14
MHHS-DIN-88 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory | Update to Incumbent MS provider for Lapsed Appointments | Update to Incumbent MS provider for Lapsed Appointments Currently BP002 only addresses the positive confirmation of de-appointment from RegService (PUB-037 - step 140/231), but if there is no secured active, there is no subsequent notification to the incumbent. The prospective MS receives a PUB-035 at step 225. How should the incumbent MS determine when the de-appointment has lapsed? | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Part of ongoing discussions with Code Drafting team why would the incumbant share the MTD via the IF-035 as early sight. IF-37 is the deappoint they code need to reflect . The Metering Service is appointed until they get de-appointed using a PUB-037. They are only receiving the PUB-035 as notification of who to send MTDs to, it is not intended as a notification of de-appointment. SC= Incumbent Metering Service is a term used to refer to the MS appointed at the point another new SP Appointment is accepted (MS or DS), it shall be the Incumbent Metering Service's responsibility to share MTDs (ADV/Trad) to the incoming party. No change recommend CLOSE | Process Model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Metering Service MHHSP-BPD002 |  |  |  |  | 2023-07-14
MHHS-DIN-89 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Customer Details on De-Appointment The MHHS design currently allows for customer data to be deleted or obfuscated by MS on de-appointment. Has obfuscation been confirmed as acceptable under GDPR? | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | Part of ongoing discussions with Code Drafting team |  | All Areas | [6 empty] | 2023-07-14
MHHS-DIN-90 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | MS Appointment for Associated Export Metering Points How will an initial MEM be appointed for a new export MPAN, created post MHHS go live? | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | Part of ongoing discussions with Code Drafting team to have a look at the process that Mpans are in the correct group The daily process monitoring (BP011C) would pick up any linked Export MPANs and ensure that the same Metering Service is appointed as the Import MPAN. If the Export MPAN is not linked, then the BAU appointment process can be followed. |  | Metering Changes | Change of Connection Type / Market Segment | MHHSP-BP011, MHHSP-BPD011 |  |  |  |  | 2023-07-14
MHHS-DIN-91 |  | N/A | 2023-02-10 | AWS | 2858 | Duncan Parsons | Software Provider |  | Document MHHS-E2E001 section 3.6 Actor Workflows Summary - Typo in the MSA Outbound. States IF-04, this should be IF-041 | Implemented |  | Interim Release 1 |  | Reference Corrected | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-92 |  |  | 2023-02-14 | RECCo | 2903, 2805, 2911 | Sarah Jones | Regulatory |  | Customer Direct Contract Flag (D053) Multiple tickets - RECCo, ESG and National Grid - all highlighting the same problem. The 4.7 artefacts do not consistently reflect the agreed position that the Customer Direct Contract flag can only be set by the incumbent Metering Service provider. The validation rules on the IF-038 should be updated The requirements for MS (013) and DS (34) in the respective BRS artefacts should be aligned | Implemented |  | Interim Release 1 |  | Added validation rule REG1075 to IF-038 in the interface catalogue Updated requirements in MS-013 and DS-034 in BRS to reflect the agreed position for D053 1/3 - ticket #3035 - SCS supportive of this change, need more detail. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue, BRS001, BRS002 | 2023-02-23 |  | Accepted but split these into two DINs one of the updates to the BRS and deal with as a minor chnge, the other as a major for the Interface Specification change
MHHS-DIN-93 |  | N/A | 2023-02-14 | Power Data Associates |  | Tom | Data Service Provider | Work off Plan D-034D updates for exceptions to Unmetered Supplies | Work off Plan D-034D updates for exceptions to Unmetered Supplies | Implemented |  | Interim Release 2 | 2023-06-23 | 1. Section 2.3 of MHHSP-METH004-UMSDS- EM Functions will be updated to make explicit that the following data items are not required by the UMSDS and as such will be ignored. • Consent Granularity (T4-COM-1857) • Domestic/Non-domestic Indicator (T4-COM-1830/1850) • Distributer Id (T4-COM-1826/1842/1845/1858/1859/1864/1865/1871/1875) • DUoS (T4-COM-1856) • LLF Data (T4-COM-1856) • Domestic Premise Indicator (T4-COM-1830/1850) • Metered Indicator- (D-045) 2. MHHSP-METH001- SDS Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 3. MHHSP-METH002- ADS- Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 4. MHHSP-METH009- UMSO Method Statement should be updated to make explicit that the following data items are not required by the UMSO and should be ignored (list to be reviewed and validated). • Consent Granularity • Domestic/Non-domestic Indicator • Distributor Id • DUoS • LLF Data • Domestic Premise Indicator • Metered Indicator | Method statement correction | Supporting Docs |  | MHHSP-METH004-UMSDS MHHSP-METH001- SDS MHHSP-METH002- ADS MHHSP-METH009 - UMSO | 2023-02-23 | 23/2/23 - Accepted |  |  | 2023-06-16
MHHS-DIN-94 |  |  | 2023-02-16 | ESG | 2777 | Patricia | Software Provider | IF-005 rejections | The IF_009 has 2 event codes: [MPANDisconnection] & [CSSDeRegistration]. [CSSDeRegistration] is listed as having Supplier as Secondary routing however on BP007 there is only reference to the supplier receiving the [MPANDisconnection] flavour of the flow. Please can you clarify which artefact is accurate. MHHSP – BPD009 step 145 states Where the Registration Service has rejected the metering update the DIP will publish the rejection to metering services. Supplier have the option to subscribe to this also. Your response was:- Our reading of this is that regservice will reject the PUB-006 back to sender if the IF-005 fails those rules. So just back to sender, not always meter service or supplier Therefore, does the BPD009 step 145 need to be updated to reflect that as the IF005 can only be generated by Metering Service Smart (MSS) & Metering Service Advanced (MSA) not the Supplier | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Question 1. Supplier will receive both events as outlined in BP007 (See DIN 294) Question 2. BPD009 step 145 updated to show that Supplier cannot choose to receive rejections. A decision was made at the DRG on 29th June to leave the messaging in BPD009 step 145 and instead update the business process model in BPD009 to give Supplier's the option to subscribe to rejections. | Process Model correction | Metering Changes | Disconnection / Change of Metering | MHHSP-BP007-Disconnection MHHSP-BP009 – Change of Metering (Install / Remove / Exchange) MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-95 |  |  | 2023-02-20 | SI Design | NA | Simon Harrison | Programme |  | Typo in the Note box about Auto Alignment of Related/Linked MPANs on the BP002 and BP003 process maps. Change 'Regisatration' to 'Registration' | Implemented |  | Interim Release 1 |  | Update BP002 (& BP003) call out box, also for BPM002 and BPM003 (Forward Migration) | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-96 |  |  | 2023-02-21 | SI Design | 2973 | Arif Jagot | Programme |  | Test-078 - SUPPI -Primary - Means SUPI? | Implemented |  | Interim Release 1 |  | Update Interface Catalogue | Data interface correction | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-97 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.4 | Typo in MHHS-METH001-5.4c "and less than 90 days months different from the UTC Date" - propose removal of months | Implemented |  | Interim Release 2 | 2023-06-23 | Update Method Statement i.e This needs to be 90 days not 90 months the artefact needs to be updated | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-06-16
MHHS-DIN-98 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.5 | Typo in MHHS-METH001 - 5.5 SDS shall use the most recent data a based on the event that triggered the | Implemented |  | Interim Release 2 | 2023-06-23 | Typo error on clause 5.5 within MHHSP-METH001-SDS Validation Estimation v5.0 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-06-16
MHHS-DIN-99 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Working days correction | Clarify that Step 105 in the CoS Transfer read process is Working Days. Currently states 5 days | Implemented |  | Interim Release 2 | 2023-06-23 | Checked with SRO - 5 Working days for Step 105 in process, BPD003C, BR-DS-024.1 and BR-DS-024.2 | Requirement correction | MPAN Ownership | Data Services | MHHSP-BRS001 - SDS Requirements MHHSP-BP003C - Transfer of Reads MHHSP-BPD003C - Transfer of Reads |  |  |  |  | 2023-06-16
MHHS-DIN-100 |  |  | 2023-02-21 | RECCo | NA | Sarah Jones | Regulatory | BP002 to include LDSO as recipient | Step 180 in BP002 and BPD002 does not include LDSO as recipient of traditional meter details as per the wording of the step or the BRS (BR-MS-024) (Code Drafting Log Reference CDD-29) | Implemented |  | Interim Release 2 | 2023-06-23 | Update BP & BPD to align with BRS and add LDSO as recipient of MTDs Updates to BP & BPD002 Forward migration for consistency | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Metering Service MHHSP-BPD002 Forward Migration BP002 and BPD002 |  |  |  |  | 2023-06-16
MHHS-DIN-101 |  | DI-120 | 2023-02-22 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. (Raised as DI 120) | Closed |  |  |  | Included within CSS validation rule update. DUPLICATE See DIN-172 | No Change | MPAN Ownership |  | MHHS-DES138-Interface Catalogue
MHHS-DIN-102 |  |  | 2023-02-22 | St Clements | 2886 | Madison Layton | Software Provider |  | SCS raised the following under MHHS-DIN-7 "MPRS will reject any PUB-031 inlcuding those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist"" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8)" They have followed up with: Just found the change that corresponds to this one in v4.7 interface catalogue – REG0005 in IF-031. Could this also be added to IF-034 so that we can apply the same validation on MDR updates? | Closed |  |  |  | Proposed Change: Add validation "CSS Registration Request ID [DI-849] is valid for Registration Service", with error REG0005 - "CSS Registration Request ID [DI-849] is invalid or unknown" This mirrors a change made in v4.7 to IF-031, agreed as part of the DAG baseline of v4.7 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-103 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory |  | Confirm that D0381 will continue to be used for updates to MPL address. BP010 & BPD010 currently allow emails, SDEP and other agreed forms can be used by Supplier or UMSO to update this - propose that these artefacts are amended to reflect that the D0381 is to be retained (Code Drafting Log Reference CDD-22) | Implemented |  | Interim Release 1 |  | Amend Steps 10, 21, 22 to explicitly use the D0381 rather than current wording | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-104 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Impact of MHHS on SoLR arrangements | Impact of MHHS on SoLR arrangements - possibly needs an Issue Resolution Group discussion to undertake evaluation & impact assessment (Code Drafting Log Reference CDD-23) | Requires Industry Work Group review | 2023-07-17 | Interim Release 4 | 2023-08-09 | Consideration required on how to undertake an evaluation of the MHHS change impact on SoLR arrangements |  | All Areas | [6 empty] | 2023-07-14
MHHS-DIN-105 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Related MPAN Business Rules | 1) IF-019 suggests RMP status can be Created or Operational - proposed this can only be Operational for subsidiary MPAN 2) Add validation rule to IF-019 requiring related MPANs to have consistent classification as domestic or non-domestic (reflecting the existing requirements) 3) Clarify what Registration Services should do when MPANs are related/linked and have different MS/MEM providers - is the IF-019 rejected or the MEM for the secondary MEM auto-deappointed? 4) What happens if the IF-019 fails validation by Reg Service at Step 330 in BP010? Design provides no guidance | Implemented |  | Interim Release 2 | 2023-06-23 | 1. Removed reference to Created in the REG1001 validation rule for IF-019 2. We understand there is no existing validation within MPRS and this is not being amended as a result of MHHS implementation. This would require a wider industry change impacting CSS as Domestic Premise Indicator is managed independently of Related MPANs. 3. It would not be rejected, auto-alignment would pick up the discrepancy at the next daily run and de-appoint the export MS and appoint the import MS. 4. As with other rejected flows, the sending party should investigate the error and re-submit as appropriate. | Data interface correction | MPAN Ownership | Change of Registration Data | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-106 |  |  | 2023-02-23 | SI Design | 2955 | Kate Goodman | Testing | IF Routing | Inconsistency in DES138 for UMSO Routing 00-Introduction logs UMSO as the single routing option for Unmetered Service provision, as there can only be one UMSO related to an MPAN PUB-008 provides UMSC, UMSP and UMSI as options for secondary routing This inconsitency needs to be corrected | Implemented |  | Interim Release 2 | 2023-06-23 | IF-008 - Secondary routing rules updated following review with Avanade (see DIN268) |  | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-107 |  |  | 2023-02-24 | SI Design |  | Simon Harrison | Progamme | Update to definition of DI-301 LLF ID in the ESC Reporting Data Catalogue | Definition of DI-301 in the ESC Reporting Data Catalogue needs to be updated as follows 'The Unique Identifier of a set of Line Loss Factors' | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Update to be made in the ESC Reporting Data Catalogue against DI-301 LLF ID it should read as 'The Unique Identifier of a set of Line Loss Factors' | Data interface correction | Supporting Docs | Reporting Catalogue | ESC Reporting Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-108 |  |  | 2023-02-27 | SI Design | 2966 | Kate Goodman | Testing | IF Routing | Ref:MHHSP-DES138-Interface Catalogue v4.7, IF-038, PUB-020, PUB-039. Document says that UM is relevant to these messages but UM thinks it is not relevant. Please clarify what the situation is. Raised in review of MHHSP-872 by Power Data. | Implemented |  | Interim Release 2 | 2023-06-23 | Covered by Secondary routing updates (See DIN268), changes to IF-020 and IF-039 routing. No changes were required to IF-038. The design allows for Customer Direct flags to be set for any Data Service/ Metering Service (ie Including unmetered). |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-109 |  |  | 2023-02-27 | SI Design |  | Simon Harrison | Programme |  | Call out box in BP002/BP003 on Linked/Related MPANs needs to be updated as it includes reference to email/SDEP rather IF-019 as shown in BP010 | Closed |  |  |  | Confirmed - the call out box on BP002/003 needs to be updated Duplicate of DIN-64 | No Change | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service
MHHS-DIN-110 |  |  | 2023-02-27 | SI Design | 2983 | Kate Goodman | Testing |  | MHHSP-BP005-Data Processing-v4.6, Step 50-160 UMSDS is referencing Submit Required UTC period level consumption data (Step 50) with a arrow going to Receive UTC period level consumption data (Step 160) but no reference of IF-021 on the connection between both - reference should be added? | Implemented |  | Interim Release 1 |  | On Process map requires arrow to be labelled as IF-021 from step 50 to step 160 | Process model correction | Meter to Bank | Data Processing | MHHSP-BP005-Data Processing
MHHS-DIN-111 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Originally raised as T4-COM-1691 on 15th Sept 2022: "MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days " Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5 (Raised as DI-76) | Implemented |  | Interim Release 1 |  | Updated to 2 working days | Requirement correction | MPAN Ownership |  | MHHS-BRS003-Registration Service requirements
MHHS-DIN-112 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54 (Raised as DI-77) | Implemented |  | Interim Release 1 |  | Added note to clarify | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-113 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? (Raised as DI-78) | Closed |  |  |  | Agreed duplicate of DIN-29 and can clsoe | No Change
MHHS-DIN-114 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | EES does not appear to have been added to the routing rules tables on the interface tabs(Raised as DI-79) | Closed |  |  |  | Already present in v5 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-115 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On IF-050, this includes linked MPANs in it, but I don’t think these would ever be populated as you cannot link MPAN at MPAN creation. So EES would only ever get Linkage updates on the IF-20 Is there any value of having this therefore in IF-050?(Raised as DI-80) | Implemented |  | Interim Release 1 |  | Removed Linked MPANs and Related MPANs from IF-050 and added explanatory note | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-116 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | For IF-025, block B032 it states it is "MPAN Legacy Info (Mandatory where event is [SSCandProfileClass], and for Traditional Meters / Optional for other Meters)" It should just read mandtory for event code [SSCandProfileClass] and nothing else, it should not be optional for any of the other event codes(Raised as DI-81) | Implemented |  | Interim Release 1 |  | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-117 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?(Raised as DI-82) | Closed |  |  |  | Discussed with SCS and confirmed it is a limitation of swagger output but should be array of MPAN followed by array of meters followed by array of MAPs repeated per MPAN. Awaiting confirmation can close | No Change | Metering Changes | IF-005 JSON | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-118 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | In relation to the Sender Unique Reference, which is constructed as: S-<Interface>-<Participant Id>-<Role Id>-<Date>-<Sequence> (hex) I would like to comment as follows: • Why is the Unique Reference simply constructed using elements that are already contained in the message as distinct values? This just means the sender has to construct it and the receiver de-construct it? • Is the sequence number expected to be reset each day ? • It would be much easier and more logical for the Sequence to be a distinct item in the message? • Why is the sequence specified as hex? • Even given the expected large number of messages, and based on it being a number(13) (defined as Sting), a standard sequence number per Participant and Role would provide 9,999,999,999,999. If this is still seen as a limitation then it could simply be built from the date, e.g. 202301190000000001, giving a provision for up to 9,999,999,999 messages PER DAY from the same Participant / Role combination, which still enables a read every 30 minutes from every MPAN(Raised as DI-83) | Closed |  |  | 2023-06-23 | This is to send a unique reference and is used for auditing purposes. Please note the length of the Sender Unique Reference has been increased at the request of Avanade in 5.1.1. Examples updated |  | MPAN Ownership
MHHS-DIN-119 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | in swagger hub under IF-002 B907 list the B036 block, this is missing numberOfDigitsCumulativeRegister data item(Raised as DI-84) | Implemented |  | Interim Release 1 |  | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue. Swagger will be updated | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-120 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Inconsistency in naming of data item DI-091 In swagger hub: Number-Of-Digits-Cumulative-Register In interface catalogue IF tabs (E.g. IF-002) : Number of Displayed Register Digits In interface catalogue data catalogue tab: Number Of Displayed Register Digits (Cumulative Register)(Raised as DI-85) | Implemented |  | Interim Release 1 |  | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue and updated YAML accordingly | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-121 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0093 comment raised on 12/01/2023 " D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: "It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42 (Raised as DI-86) | Implemented |  | Interim Release 1 |  | Agreed to provide SEG scenario's in IF-005 Use Case guide. currently under review |  | Metering Changes | Change of Segment | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-122 |  | DI-87 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0084 comment raised on 12/01/2023 following the introduction of IF-019 and respective changes in the latest set of released artefacts MHHSP-BP010-Change of Registration Data -v4.5 "Shows Supplier Mastering Import Export Linkage. BSC CP1558 introduced changes to MPRS for the LDSO to manage this via the DB05. IF-019 should go to LDSO who should then produce a DB05 into MPRS." The process diagrams and requirement spreadsheets have been amended to show MPRS loading DB05 as a IF-019 response. DB05 is not a IF-019 response, it is a request from DNO/iDNO to create, amend or remove a import/export linkage. It does not currently have any capacity to include a IF-019 rejection response to trigger a IF-020 rejection response to DIP. (Raised as DI-87) | Implemented |  | Interim Release 1 |  | SCS reviewing preferred option with LDSO's The following changes would be required to the LDSO overview requirements: MHHS-BR-LD-043.3 LDSO Send Import/Export relationship update LDSO must send accepted Import/Export relationship updates to the Registration Service via the appropriate interface DB05 file or other agreed mechanism BP010B Change of registration data 900 MHHS-BR-LD-043.4 LDSO Send Import/Export relationship rejection LDSO must publish rejected Import/Export relationship updates on the Data Integration Platform using the appropriate interface MHHS-IF-020 to Supplier BP010B Change of registration data 900 On BP-010 for Linked Import/Export MPANs the following would be required: 1. Need to add rejected leg from step 900 to DIP 2. Need to add PUB-020 going from the DIP to the Supplier The BPD-010 will need updating accordingly. | Process Model correction | MPAN Ownership |  | MHHSP-BP010-Change of Registration Data MHHSP-BPD010, MHHSP-BRS005, Traceability Matrix
MHHS-DIN-123 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0083 comment raised on 12/01/2023 following the introduction of a new business rule on MPRS in the latest set of released artefacts MHHS-BR-RS-078 "MPRS cannot control how messages are sequenced at CSS and DSP. IF MPRS waits until the DSP responds before sending the Appointment message this could take hours (as this is a batch process) this will result in a delay in the appointment of the MDR. Sequencing requirements should be placed on CSS & DSP to ensure the correct MDR is appointed based on Effective dates provided from MPRS. However, they may not be necessary due to the way this interface works: The C0200 interface uses the PUT Method, which will replace the data held at CSS. Explicit ending of an Appointment is only required for a future dated appointment, this will be sent as one message with the Old and New MDR appointments. For Same Day or Retrospective the new MDR Appointment will Replace the currently set value. This implicitly ends the previous MDR Appointment. On a CoS, the MDR is linked to a Registration not a Metering Point. The previous MDR will end naturally when the Previous Registration becomes securedInactive. An explicit message to end the MDR appointment on the Previous Registration is not required . MPRS will only send two separate updates to CSS when there is a gap in MDR (SDS) appointments. For Example a change of segment to Advanced and then back to Smart. This would need to happen over a short period to generate two messages that could go out of sequence" The MHHS design team rejected with comment "The MHHS design is based upon what was agreed as part of the R044 consultation. This scenario does not reflect our understanding of how the CSS/DCC/DSP interface will work as set out under R044. " This is how C0200 currently works today and the interface is unchanged in R0044. This will put a signfiicant requirement on MPRS that will reduce time available time for other core MHHS development activities with no benefit to industry.(Raised as DI-87) | Closed |  |  |  | No Change - updated in v5.0 | No Change | MPAN Ownership
MHHS-DIN-124 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0089 comment raised on 12/01/2023 "D-021 was meant to give more detail on how L1-L4 validation should be used and provide more error codes for use. This has not been done as far as I can see Blocking resolution to this T4-COM-1749, T4-COM-1769 and T4-COM-1768" Comment was closed as clarified however none of these items have been resolved and we have no dates as to when they will be. comments blocked that were raised initially on 15/09/22 Comment T4-COM-1749: "The Registration Service, as part of its L3/L4 validation should ensure that there is consistency between the data content of the IF-033 issued to the Service Provider and the [returned] content in IF-034 - if this isn't so then message should be returned to Service Provider using ""MSGStatus Message"" mechanism." Does MPRS only need to validate consistency in the data it loads on the IF-033, not the data that is not loaded" Comment T4-COM-1769: "We need validation rules to be defined for this flow, Does not match IF-031, content of the PUB-034 does not match the IF-031. No Proposed Appointment Found, PUB-034, does not link to any Pending IF031s. Define Validation Rules for PUB-034 The 034 content must match the original if-031 content the 034 must have a corresponding IF031 the 034 has already been received for the IF-031 Generic Standard Validation, MPAN exists valid in ISD ETC" Comment T4-COM-2768: "We need some generic codes for standard validation rules such as: Service/Supplier is valid in ISD MPAN exists in MPRS MPAN is not Disconnected Service/Supplier is Valid in MDD (so CSS doesn’t reject updates)" (Raised as DI-89) | Implemented |  | Interim Release 1 |  | Added RMP status check to IF-034 and refined validation rule notes regarding different values received from IF-033 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-125 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | IF Routing | WOA-0091 comment raised on 12/01/23 D-030 "how routing will work in the DIP has not been updated this information is required for our development" MHHS Design Team has closed as clarified however there is still uncertainty around the DIP routing, and there are not dates provided for when the detailed DIP design will be released. This will clock certain elements of development (Raised as DI-90) | Implemented |  | Interim Release 2 | 2023-06-23 | Secondary routing rules updated following review with Avanade (see DIN268) |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-126 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0092 comment raised on 12/01/23 following more infromation around D-022 being clarified "D-022 Following the work off item being agreed on what is required for an MPAN to be traded - it has now been possible to fully assess the optionality of data items in the interfaces Data items still mandatory in interfaces that must be changed to optional: Annual Consumption (IF-001) Incumbent Service Providers (IF-002, IF-033) Incoming MS/DS (IF-037) These are not required at creation, nor at traded, and therefore could be non existent in MPRS when MPRS generates this outgoing IF messages Blocking resolution of T4-COM-1727 and T4-COM-1735" Closed as clarified however none of the issues listed have been resolved Annual consumption still reads madatory on a CoS for IF-001, the issue is MPRS may not have this data item. The item is not required to reach a status of traded, therefore CSS will accept a CoS on this MPAN without annual consumption being populated, and then MPRS will not be able to provide this data item on the IF-001 that results from the CoS. This must be changed to optional OR the definition on what is needed to be traded should be updated to include annual consumption. Incumbent Service Providers is still mandatory on IF-002 for CoS Again as MS is not required to be traded, CSS will accept a CoS request with or without a current MS, and so MPRS will not be able to provide an incumbent MS in these cases. It must be changed to optional or the definition of what is needed to be traded should include MS. Incoming MS/DS is still mandatory on IF-037, there are numerous reasons an appointment may be lapsed, the only change that would gaurantee a new incoming SP that MPRS could send on this flow is a change or SP (CSERV) scenario. For CoS the supplier may not have sent in new appointments, for DEREG there will be no new appoitnments, for SEG the market segment may have changed but the supplier may not have sent in new appointments, same for change of connection type, and for IMPEXP and RELATED the parent MPAN might not have MS/DS appointed at all so there would be no new appointments for MPRS to populate on this flow. This must be changed to madatory ONLY on CSERV (Raised as DI-91) | Implemented |  | Interim Release 1 |  | Discussed with SCS. Covered by clarification on nullable and interface notes- All these issues are resolved by the Mandatory Nullable Solution. Confirmed Annual Consumption block will only be provided where available in Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-127 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 "DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least "Registered", if no DS is appointed then there is already an appropriate Event Code" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone (Raised as DI-92) | Closed |  |  |  | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-128 |  | DI-93 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0095 comment on 12/01/23 "D-009 This is blocking closure of T4-COM-1730. There is a lack of clarity around the treatment of rejection from CSS, between both R044 and the MHHS design artefacts e.g. MHHs-BR-RS-088.1 and MHHS-BR-RS-079 both suggest MPRS would still load the new MDR record and appoint in MPRS despite a rejection from DCC/CSS. Our assumption would be that we do not load a MDR appointment that is rejected from DCC/CSS and we send the IF-035 rejection to notify the DS/Supply of this. However no clarity on what to do if DCC/CSS rejects a MDR end date on a de-appointment T4-COM-1730 was raiseed on 15/09/22 MHHS Design Team Rejected the comment with a statement this is outside of MHHS Scope. How MPRS treats the MS/DS appointment and how it responds over hte DIP is within MHHS design. The requirements we are enquiring about are already included in the MHHS design documents as in scope also. This is a major blocker to MPRS design on MDR appointment processes (Raised as DI-93) | Closed |  |  |  | Discussed with SCS this is a REC requirement. Agreed no error codes will be received, just use a generic response. | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-129 |  | DI-94 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0086 comment on 12/01/23 following the release of the first draft of IF-050 in the revised interface catalogue artefact "Related MPANs and Linked Import Export are not set at MPAN Creation. EES can get these on the IF020 Remove these blocks from IF-050 as they would never be populated" MHHS design team marked as accepted and changed but the blocks still exist in IF-050, these blocks will never be populated and so should be removed from the IF-050 interface(Raised as DI-94) | Closed |  |  |  | Closed - duplicate of DIN-115 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-130 |  | DI-95 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0088 on 12/01/23 "D-011 & D-050 it is still unclear how LLFC and DUoS Tariff ID will be stored and managed in MPRS. DUoS should be an Alias of LLFC and not have its own data item in MPRS. LLFC will be renamed to DUoS Tariff when the old arrangements have ended. LDSO impacts having to maintain two items which will lead to billing issues" Marked as clarified and closed witih a clarification statement to be issued on tuesday 24th January, this clarification statement was not received. Awaiting clarification(Raised as DI-95) | Closed |  |  | 2023-06-23 | Email to Madison to check can close |  | MPAN Ownership
MHHS-DIN-131 |  | DI-96 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 is missing business rules: REG1001 - MPAN [DI-063] is at [REG.RMPStatus] not status Created/Operational. This should apply to IF-025. IF-025 is missing a rule that consent granualiry EFD must not be earlier than supply start date. Consent Granularity EFD must not be prior to current consent granularity EFD The Consent Granularity Energy Direction Domestic Premise Indicator Combination must be valid in ISD(Raised as DI-96) | Implemented |  | Interim Release 1 |  | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-132 |  | DI-97 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 IHD update does not include validation rule 1019, does this mean IHD EFD can be prior to current and effectively cancel out the current IHD status completely, or is it just an error and the rule should be added to interface catalogue for IHD?(Raised as DI-97) | Implemented |  | Interim Release 1 |  | Amendment accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-133 |  | DI-98 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 will not allow a SMSO to be set for a non smart meter "REG1022 - SMSO ID Cannot be set where Market Segment is [Reg.Segement]", would a non smart supplier be able to send a B031 SMSO block, they will need to be able to if they are required to clear an old SMSO by populating SMSO as null(Raised as DI-98) | Implemented |  | Interim Release 1 |  | Added new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements | 2023-03-23
MHHS-DIN-134 |  | DI-99 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 "SSC must be valid in ISD. Rejection reason: REG1044 - SSC must be a valid value in ISD" SSC are not yet populated in ISD(Raised as DI-99) | Closed |  |  |  | Clarified that SSC validation will be based on Frozen MDD. Seperate DIN to cover availability of ISD | No Change | MPAN Ownership |  | MHHSP-EM021 ISD Entity Data Map, MHHSP-DES138-Interface Catalogue
MHHS-DIN-135 |  | DI-100 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Should B032 PC and SSC block on IF-025 only be permitted when theres a traditional meter fitted at the MPAN?(Raised as DI-100) | Closed |  |  |  | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-136 |  | DI-101 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | How is the Green Deal Exists defined. Does this mean there's a green deal linked to the MPAN regardless of dates, does it mean there's a green deal currently active or due to become active, or does it mean there is a currently active green deal assigned to the MPAN? (Raised as DI-101) | Implemented |  | Interim Release 1 |  | Remove Green Deal exists (DI-110) from Data Catalogue and IF-050 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-137 |  | DI-102 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-007 Validation rule "Metering Service [S0.SenderID] holds valid previous appointment then Energisation Status EffectiveFrom Date [DI-034] should be < [REG.App End Date] + 10" The way it's curently written suggests MPRS should accept an IF-007 from the previous appointed MS, event if there ETD was greater than 10 days ago, provided the ES EFD date was less than their ETD + 10. E.g the previous MS could send IF-007 two years later with ES EFD of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then a separate rule should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? Linked to DI-41(Raised as DI-102) | Implemented |  | Interim Release 1 |  | REG1003 validation rule updated in IF-007 to constrain energisation updates to 10 days after the MS appointment period |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-138 |  | DI-103 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-034 Submitted rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD | Closed |  |  |  | Duplicate of DIN-176 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-139 |  | DI-104 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Need clarity on what role code should be used in C0200 for MS and MDR appointments Linked to comment T4-COM-1790 which was accepted as design issue raised but then moved to a work off item "We would like to see some indicative Role Codes and DIP IDs so we can populate development systems with this data " | Closed |  |  |  | Send "MDR" as role code as per Registration requirement. Allocation of DTN MPIDs is a seperate issue | No Change | Registration | Existing EMAR I/F | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-140 |  | DI-105 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 | Closed |  |  |  | Discussed with SCS the IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR. Agreed to close | No Change |  |  | MHHSP-BP003A, MHHSP-BRS003 Registration service requirements
MHHS-DIN-141 |  | DI-106 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 | Closed |  |  |  | RECCo consequential change | No Change |  |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-142 |  | DI-107 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | There currently aren't sufficient rules to ensure that a principal primary MPAN is not also a linked export subsidiary MPAN or that a subsidiary secondary MPAN is not also a principal import linked MPAN. The MHHS design either should accommodate both (would need clarity on how to treat cases where MPANs are BOTH principal and subsidiary) OR new rules should be introduced to prevent this occuring AND cleanse existing cases ahead of migration | Implemented |  | Interim Release 1 |  | Validation rules updated for IF-019 | Missing/incorrect validation rule | MPAN Ownership |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-143 |  | DI-108 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Requirements were uplifted in v4.5 to include logic around market segment on related MPANs MHHS-BR-RS-124.1: Registration Service must, in the case of Related MPANs and following derivation of Market Segment for individual MPANs, update the Market Segment for the Primary MPAN and all the Secondary MPANs based on the following rule: 1. If any MPAN in the Related MPAN Group has a (derived) Market Segment of Advanced, then set the Market Segment for all the MPANs to Advanced and set the Market Segment Valid Flag to "Yes" for all the MPANs This specifically cites related primary/secondary and does not mention linked import/export associations at all. But then another requirement implies maybe it should have done: MHHS-BR-RS-127: Registration Service must , in circumstances where the derived market segment is invalid (and has not been overridden by Linked/Related MPAN logic ) Should MHHS-BR-RS-124.1 have applied to linked import/export associations too or is it intended solely for primary/secondary related MPANs? | Implemented |  | Interim Release 1 |  | This should only apply to Related MPANs. Updated RS-127 | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-144 |  | DI-109 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131 This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to: Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. | Closed |  |  |  | Duplicate See DIN-169 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-145 |  | DI-110 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. | Implemented |  | Interim Release 1 |  | Added L as valid value for DI-979 in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-146 |  | DI-111 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. | Implemented |  | Interim Release 1 |  | Agreed with SCS to reuse STD Error Response Section in IF035 to communicate Lapsed Reason . See DIN-145 for summary of updates | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-147 |  | DI-112 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-008 response block is listed as mandatory, however on disconnection the MPAN is de-energised by MPRS automatically. The supplier cannot de-energise after disconnection on the IF-007, it must be automatic at MPRS as per The de-energisation needs to be communicated on the IF-008 but it is not in response to an IF-007 and so we cannot populate the response block. | Implemented |  | Interim Release 1 |  | Data interface change agreed. Added Interface note to IF-008 to cover forced de-energisation changes by Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-148 |  | DI-113 | 2023-02-10 | St Clements | 2864 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-113 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { "confirmingMpid": "string", --* "registrationId": "string" --*, "updateSucceeded": boolean --* } Suggest that DI-0980 is removed from B066 | Closed |  |  |  | Discussed with SCS and agreed to close - note no error codes returned from CSS so will provide generic error code | No Change |  |  | MHHSP-DES138-Interface Catalogue, JSON, YAML
MHHS-DIN-149 |  | DI-114 | 2023-02-10 | St Clements | 2865 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-114 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 On IF-038 validation "REG1073 - Customer Direct Contract already exists for MPAN [DI-063] for that period" The respective validation rule for this states: If Contract End Date [DI-145] <= Max existing active MS contract end dates [Reg.MAX_DCMS_Enddate], EXCEPT IF requesting MS [S1.SenderID] = Currently Active Direct MS [Reg.CurrentActiveDC_MS_DIPID] AND Contract End Date [DI-145] <= existing active MS contract end date [Reg.CurrentDCMS_Enddate] This rule doesn't fully prevent overlapping appointments as does not cover where the MS is not currently contracted MS and ETD > current ETD which should also be rejected. Think a simpler rule would cover this scenario more fully e.g. If there is an active contracted MS/DS, and the submitting MS/DS does not match then reject And then ETD can be greater or later than current ETD for the currently contracts MS/DS anyway so doesn't need specifying? | Closed |  |  | 2023-06-23 | SRO Team do not belive that a change is required. |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-150 |  | DI-115 | 2023-02-10 | St Clements | 2866 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-115 in our log In some place on IF-038 tab there is reference to a future customer direct contract e.g. "OR requesting MS [S1.SenderID] <> Any future Direct MS [Reg.FutureDC_MS_DIPID] " "extended dates will be subject to checking if another Service Provider has registered a separate Customer Direct Contract covering the same period" - this can only happen if there's a future appointment "AND ALSO removing all future periods which may or may not have been accepted and recorded previously." As there is no Effective From Date included in the flow MPRS will store an Effective From Date of the system date at the time of creation of the customer contract indicator. It will not be possible to set one to start in the future as the IF-038 does not include effective from date. Is this the same understanding as the MHHS Design Team? | Closed |  |  | 2023-06-23 | As per DI-149 above SRO Design Team do not belive that any changes are required |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-151 |  | DI-116 | 2023-02-10 | St Clements | 2868 | Madison Layton | Software Provider |  | Just spotted a change in v4.7 and raised in our log as DI-116 Artefact: MHHSP-BP010-Change of Registration Data -v4.7 under MPL and GSP Group amendment section, DB02 has been amended in v4.7 to DB002. DB002 is not correct, DB02 was the correct name For reference the DB flows only ever have one 0 in, there is DB01 (MPAN creation), DB02 (MP updates), DB03 (Disconnection) and DB05 (Import/Export Linkages) | Implemented |  | Interim Release 1 |  | BP010A step 10 flow name change to DB02, BP010B step250,step440, Step560 flow name change to DB02, and update BPD descriptions to DB02. | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-152 |  | DI-117 | 2023-02-14 | St Clements | 2912 | Madison Layton | Software Provider |  | On looking more closely at the validation rules for IF-019 spotted a few issues. IF-019 REG-1061 rule for Related Create event code appears to be written incorrectly. The rule and rejection description don't quite align. Rule: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) are not currently part of an import/export relationship Rejection reason: REG1061 - Prosposed MPAN(s) [DI-073] / [DI-074] are already part of a Related MPAN Relationship Should the rule read: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) is currently part of a related primary/secondary relationship? The rule and descriptions also don't appear to fully align for some in import/export section too - REG1052, REG1055, REG1057 and might need some minor tweaks to correct. | Implemented |  | Interim Release 1 |  | REG1061, 1052 and 1055 rules updated. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-153 |  | DI-118 | 2023-02-14 | St Clements | 2913 | Madison Layton | Software Provider |  | On working on detailed design for Related MPANs, noticed the IF-019 interface is missing a rule that the Secondary MPAN must not be a Primary in another Relationship. You could expand REG1064 to include this as the description sounds like it should have been covered here. Rule: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN Description: REG1064 - Proposed Secondary MPAN [DI-074] is already part of a different MPAN Relationship Could amend rule to: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN OR [DI-074] is already in a relationship as a Primary MPAN | Implemented |  | Interim Release 1 |  | REG1064 validation rule updated | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-154 |  | DI-119 | 2023-02-15 | St Clements | 2919 | Madison Layton | Software Provider | IF-019 validation gap on primary and subsidiary MPAN | On further detailed design we’ve spotted a potential design gap. Currently it is possible to enter a state where an MPAN is both a primary and subsidiary MPAN at the same time (e.g. Primary but also export linked or Secondary but also import linked). The current MHHS doesn't accommodate an MPAN being in both states at the same time. We’ve already looked to add rules to try to mitigate this on DB02/DB05 internal flows but would need additional rules on IF-019 to fully prevent this scenario occurring. Rules we think are required: 1. On receipt of IF-019 with event code RelatedCreate or RelatedAdd, the primary MPAN must not have energy direction of Export 2. On receipt of a IF-019 with event code RelatedCreate or RelatedAdd, any listed secondary MPAN must not in an active Import/Export relationship as the Import MPAN 3. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Import MPAN must not be in an active relationship as the secondary MPAN 4. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Export MPAN must not be in an active relationship as the primary MPAN | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Agreed with SCS that, changes would be made to support Rules 1 and 4. Validation Rules updated accordingly with new Error codes (REG1067/1068) created to support. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-155 |  | DI-120 | 2023-02-15 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. | Closed |  |  |  | see also DIN-172/173. Included in 5.1 DUPLICATE See DIN-172 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-156 |  | DI-121 | 2023-02-24 | St Clements | 3078 | Madison Layton | Software Provider |  | We have logged a new design issue under DI-121. IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP | Closed |  |  |  | Duplicate of DIN-173 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-157 |  | DI-122 | 2023-02-27 | St Clements | 3090 | Madison Layton | Software Provider |  | New design issue (SCC Ref DI-122) for the IF-005 related to REC CP R0032. The current v5.0 validation in the IF-005 does not include the new validation introduced with REC CP R0032 (R0032 is approved and being implemented in the D0312 this June): NEW REC CP R0032 Validation: V Rejected – ESME ID already exists within MRPS and does not match Removed Meter, Associated Import/Export MSID or Related MPAN W Rejected - MSN relates to a Smart Meter Type and the ESME ID is NULL X Rejected – ESME ID Format is Invalid Y Rejected – Number of Displayed Register Digits is NULL and the MSN relates to a Smart Meter Type Z Rejected – Non-Smart Meter Type with Number of Displayed Register Digits populated AA Rejected – Meter Location is invalid AB Rejected – Non-Smart Meter Type with ESME ID populated AC Rejected – Number of Displayed Register Digits is incorrect IF-005 Validation: V not covered, needs to be added as a Level 5 Validation Rule W is already covered by DI-085 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) X is already covered in DI-085 population notes (Level 4 validation RCP1023 Msg Contains Invalid Valid Value Combination(s)) Y is already covered in DI-091 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) Z is not explicitly covered, suggestion: add to DI-091 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AA is covered in the population notes AB is not explicitly covered, suggestion: add to DI-085 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AC not covered, Suggestion: add the following population note from R0032 to DI-091: Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” Summary Please add the following Changes to the IF-005 to align it with the D0312 validation and maintain the same level of Smart Meter data quality in the Registration Service: New Level 5 Validation rule for DI-085 implementing V from the D0312. ESME ID must be unique within MPRS unless it’s a Linked MPAN where the same Smart Meter can be shared across Linked MPANs New population note for DI-091, only to be included for Smart Meter Types New population note for DI-085 , only to be included for Smart Meter Types New population note for DI-091, Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” | Implemented |  | Interim Release 1 |  | New Validation Rules added to IF doc to ensure full coverage and alignment with CP Error codes described | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-158 |  |  | 2023-02-27 | Elexon | 2908 | Derek Weaving | Central Body |  | As part of the Performance Assurance Working Group discussions on Supplier Charges, we are exploring the use of CCCs to categorise the data for future charges. It is noted that Settlement Period Quality Indicator referenced in the VAS Method statement is for illustrative purposes and would welcome clarity on the following: · What is the intended process to populate the Settlement Period Quality Indicator in the initial ISD Table? · What would be the process to be involved in those activities to determine the categorisations should additional CCCs be required? | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | Recommending a change to this ISD Data Item: Settlement Period Quality Indicator to be set as per Appendix 1 of MHHSP_METH007 MDS_Method_Statement v5.0 This data item need to be changes to something like ‘Valid Settlement Period Quality Indicator Set’ and the field size needs to be increased. The data catalugue will need the revised data item and the field length will need increasing from 20 to at least 50. This Item also appears in some interfaces that will need t be updated This is because it represents a set of SPQIs. The initial intention is to populate as per the table and check if any new SPQIs have been introduced in the baseline design Method Statement that are not covered. If new CCCs are introduced the appropriate flags for each new CCC would need to be agreed. However, it is likely that another dimension to the table below would need to be introduced to facilitate new CCCs. |  | Meter to Bank | Volume Allocation Service | MHHSP-METH006_VAS_Method_Statement ED021 ISD Entity spec MHHSP-DES138-Interface Catalogue ECS report |  |  |  |  | 2023-07-14
MHHS-DIN-159 |  |  | 2023-03-01 | ENWL | 2994 | Paul Band | Network Business | Interfaces for UMSO | DES-138 Interface Inconsistencies vs BSCP7XX for UMSO Discussions with ENWL have highlighted a number of inconsistencies in the Interface Catalogue when it comes to routing for UMSO's. DIN-106 also refers. UMSO is not listed as a recipient in DES-138 for the PUB-008, but this is in the draft BSCP and should be added to the PUB UMSO is not listed as a recipient in DES-138 for the PUB-020, but this is in the draft BSCP - this is not needed in the BSCP as there are no unmetered Related MPANs UMSO is not listed as a recipient in DES-138 for the PUB-035, but this is in the draft BSCP - view that it is unlikely for this flow ever to be used as the appointment will not trigger any processes to need a subsequent update UMSO Is listed as UMSI, not UMSO in PUB-036 in DES-138 UMSO is listed as UMSC, not UMSO in PUB-018 in DES-138 The IF_LIST tab should be reviewed for consistency | Implemented |  | Interim Release 2 | 2023-06-23 | As with DIN-106, there are inconsistencies in the Interface Catalogue for UMSO routing. This has been compounded by a review of the draft BSCP for UMSO, which has added a number of PUB flows going to UMSO that aren't currently in the catalogue. Covered by updated secondary routing rules (see DIN268) Design to check requirements in BSCP and MHHS BPs and ensure the interface catalogue reflects a consistent approach | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue and possibly related business processes and descriptions E2E001 |  |  |  |  | 2023-06-16
MHHS-DIN-160 |  |  | 2023-03-14 | Ovo Energy | 2862 | David Morley | Supplier | BP009 flow addition | Steps 205 and 210 in BP009 wont be completable in the event that theres no comms. I think the process would be workable if there was an exception route here - see red arrow below. | Implemented |  | Interim Release 2 | 2023-06-23 | Update Steps 205 and 210 in BP009 with "Comms Available" line label add flow from step 205 to step 215 with “Not Commissioned / No Comms” line label | Process Model correction | Metering Changes | Change of Metering | MHHS-BP009 |  |  |  |  | 2023-06-16
MHHS-DIN-161 |  |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 requirement correction | MHHS-METH001-5.4c Please confirm the requirement: “where daily advance records are available [either in the past or future] and less than 90 days months different from the UTC Date requiring a daily advance - use the mean actual Meter advance from the closest [4] weeks for the same Day Type (as defined in ISD).” | Closed |  |  | 2023-06-23 | Duplicate of DIN 97. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-162 |  |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 typo | MHHS-METH001-5.5 typo “Where DAEs are required to be calculated the SDS shall use the most recent data a based on the event that triggered the estimation.” | Closed |  |  | 2023-06-23 | Duplicate of DIN 98. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-06-16
MHHS-DIN-163 |  | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Conditionality Rule for B037 | It is not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure it is unclear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" | Implemented |  | Interim Release 2 | 2023-06-23 | Updated conditionality rule for Block B037 in IF-001, IF-002, IF-033, IF-036: to show that Either DI-075 (Primary MPAN) or DI-079 (Secondary), and not both, should be populated where MPAN (DI-063 above) is part of a group of Related MPAN. |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-164 |  | DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0093 comment raised on 12/01/2023 "" D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692"" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: ""It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period"" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42" | Closed |  |  |  | "This requirement stands - review with SCS in light of SEG scenario. We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error...". Reviewed with SCS and agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-165 |  | DI-122 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | See separate sheet Duplicate of DIN-157 | Closed |  |  |  | CR required to add rules in line with CP R0032 Added Miscellaneous Data Validation to IF-005 to cover REC CP R0032 validation rules Wrapped up into design teams main CR Doesn't need to be raised by SCS | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-166 |  | DI-77 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54" | Implemented |  | Interim Release 1 |  | Added clarification to REG Notes re Consent and Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-167 |  | DI-78 DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? " | Closed |  |  |  | Agree you can't. Could update 1032 rule for USP? Duplicate see DI-29 | No Change
MHHS-DIN-168 |  | DI-92 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 ""DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least ""Registered"", if no DS is appointed then there is already an appropriate Event Code"" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone | Closed |  |  |  | CR for new functionality. "Already covered by no MS/DS appointed - MPRS would try to align MS/DS with principle and couldn't as there's no registration to align this to. Need an extra check that can only autoappoint if there's a registration to prevent MPRS crashing Maybe one for DRG? Jon at RECCO for consequential change? Agree not to build for this scenario as this would be an edge case and close | No Change
MHHS-DIN-169 |  | DI-109 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to:Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. | Implemented |  | Interim Release 1 |  | Simplified MHHS-BR-RS-131 on when to lapse a SEG appointment | Requirement correction | MPAN Ownership |  | MHHSP- BRS003, MHHS-BR-RS-131 | 2023-03-23
MHHS-DIN-170 |  | DI-110 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. | Closed |  |  |  | Duplicate of DIN-145 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-171 |  | DI-113 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { ""confirmingMpid"": ""string"", --* ""registrationId"": ""string"" --*, ""updateSucceeded"": boolean --* } Suggest that DI-0980 is removed from B066" | Closed |  |  |  | Agreed with SCS being retained but due to optionality may have to populate text e.g. contact DSP. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-172 |  | DI-120 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. | Implemented | 2023-04-27 | Interim Release 1 |  | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-173 |  | DI-121 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP | Implemented | 2023-04-27 | Interim Release 1 |  | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-174 |  | DI-72 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a Submitted MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60" | Implemented |  | Interim Release 1 |  | "Agreed- doc updates MDR can have gaps between DS EFD and MDR EFD" Updated REG1083 validation in IF-034 so that it allows MDR Effective from dates >= SSD/ DS Eff From date/Existing MDR Eff from date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-175 |  | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" | Closed |  |  |  | Duplicate entry | No Change | MPAN Ownership
MHHS-DIN-176 |  | DI-103 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-034 new rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD" | Implemented |  | Interim Release 1 |  | Agreed -doc updates Updated REG1082 to apply for both [SDS-MDRUpdate] and [DSAppSPRepsonse] events in IF-034 | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-177 |  | DI-105 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 " | Closed |  |  |  | "Reason for IF-035 is to trigger when SDScan send the Meter info" & The IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR Agreed with SCS no changes are required, they now understand the context agreed to CLOSE | No Change | MPAN Ownership |  | MHHSP-BP003A
MHHS-DIN-178 |  | DI-106 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | MS missing a requirement to send MS updates to CSS | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 | Closed |  |  |  | Closed as discussed with SCS that this is out of scope for MHHS Programme. | No Change | [7 empty] | 2023-07-14
MHHS-DIN-179 |  | DI-111 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. | Closed |  |  |  | Duplicate of DIN-146 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-180 |  | DI-125 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 the Meter Removal is currently not permitted for a prospective MS Is it possible for the MS to need to remove two meters and replace it with one? In which case meterexchange would only allow them to do part of this process (remove 1 and add 1) but not complete it, so SEG could not complete. Should meter removals therefore be allowed for prospective MS? (REG1019) | Implemented |  | Interim Release 1 |  | Revised REG1019 and added REG1027 for MeterRemoval event in IF-005 | Requirement correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-181 |  | DI-126 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Missing Rule on If-005: MAP EFD must not be > removal date | Implemented |  | Interim Release 1 |  | Added new rule for MeterUpdate and MeterHistoryUpdate events so that MAP EFD must not be > removal date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-182 |  | DI-127 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 On exchange - the MAP and IHD groups are for new installation not removed meter - does this need to be clarified? | Implemented |  | Interim Release 1 |  | New note added to IF-005 to clarify that only the newly installed MAP and IHD information is required on MeterExchange | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-183 |  | DI-128 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-005, IHD EFD missing validation in IF-005 (Between install and removal date) | Implemented |  | Interim Release 1 |  | Covered Release 5.1, IF-005, IHD EFD missing validation added | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-184 |  | DI-129 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-005 incorrect validation rule: REG1010: On event code Meter exchange and Meter Install rule states MAP EFD >= Install date, it should be = not >=" | Implemented |  | Interim Release 1 |  | IF-005: Updated to REG1010 (MAP Eff from date check ) to = install date for MeterInstall and MeterExchange | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-185 |  | DI-130 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | It should not be possible to change MDR EFD once set. Need validation rules to enable MPRS to reject if IF-034 is submitted with current MDR but a different EFD. | Implemented |  | Interim Release 1 |  | Agreed - doc updates Covered by L3/4 validation as per updated Validation rule notes | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-186 |  | DI-131 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031, there is currently not enough validation to ensure on a SEG, that the same SP isn't appointed for the current registration. Need additional validation rule: If scenario SEG and current supplier, then SP must not be current SP. | Implemented |  | Interim Release 1 |  | Agreed - doc updates Updated validation rule Added REG1095 in IF-031 to check different Data Service proposed for SEG appointment | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-187 |  | DI-132 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Supplier inability to appoint MS/DS for Principal and Subsidiary MPAN | Unhappy Path Scenario: Receive IF-031 for MPAN that is both Principal and Subsidiary MPAN at the same time. This will be rejected as per REG1038/REG1039 Supplier will be unable to appoint MS/DS for the MPAN or any related/linked subsidiary MPANS. | Closed |  |  |  | Closed, there is an existing to prevent this scenario happening going forward. Agreed with SCS to raise examples in the Data Cleanse Forum. | No Change | [7 empty] | 2023-07-14
MHHS-DIN-188 |  | DI-133 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031 the rule REG1030 reads [DI0-828] in not a valid UMSO in DNO [DI-108]/[DI-109] This should read LDSO not DNO | Implemented |  | Interim Release 1 |  | Tied up with If-005 rejection description flexibility action Change REG1030 to read: REG1030 - [DI0-828] in not a valid UMSO in LDSO[DI-108]/[DI-109] SC change incorporated into 5.1.1 | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-189 |  | DI-134 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On IF-031, REG1036 is written to only apply to USP when it should apply to all scenarios? ""Proposed MDR Date [DI-836] >= [REG.MPAN_SUP_SSD] However don't think this rule is required at all as this is already covered under the REG1036 rule that MDR Date < DS EFD? Linked to DI-66" | Implemented |  | Interim Release 1 |  | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-190 |  | DI-135 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-034 missing validation rule REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational | Implemented |  | Interim Release 1 |  | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-191 |  | DI-136 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Addition of validation rules to MPRS to restrict Retrospective changes | MPRS does not currently prevent Retrospective changes to DUoS Tariff ID or Connection Type. Should MPRS add new validation rules for these items to restrict Retrospective changes? Please can you update DIN-191 to include Disconnection Date & Export Association. We don't currently have any restriction on how far these data items (and the others in DIN-191) can be back dated. This is a retrospective change through the DB interface and not a Manual Amendment. There are no retrospective periods for the following data items, this means the data items could be changed earlier than the settlement window and cause issues for settlement. There are restrictions that these data items must be within MS/Registration periods where appropriate, but the EFD/SSD could still be years into the past. - MDR EFD - MS EFD - DS EFD - IHD Status EFD - PC EFD - SSC EFD - Energisation Status EFD | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | Internal review to take place as to whether DUOS Tariff ID updates should be retrospective. | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-192 |  | DI-137 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | For If-031, scenario SEG, the business process diagram/requirements only describe the appointment lapsing once reaching it's SSD if no SA is received. If we receive a cancellation we would like to lapse the appointment at that point in time (it cannot become secured active after being cancelled) and not wait until the SSD to do this. | Implemented |  | Interim Release 1 |  | Added new requirements to BRS003, MHHS-BR-RS-24.1 and 58.1 | Design Ambiguous | MPAN Ownership |  | MHHSP-BRS003-Registration Requirements | 2023-03-23
MHHS-DIN-193 |  | DI-138 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | The YAML name for metered indicator (Data Item 127) is meteredUnmeteredIndicator. This is then set to true of false. It isn't clear whether true means it's metered or unmetered due to the naming convention. It should be named meteredIndicator instead to make it clear true means metered, false unmetered. | Implemented |  | Interim Release 1 |  | Updated YAML details in the Data Catalogue for DI-127 Metered Indicator. Updated YAML accordingly Updated data catalogue/ YAML | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-194 |  | DI-1 | 2023-03-15 | St Clements | 4475 | Madison Layton | Software Provider |  | For IF-035 what is Event Code [IMS-SendMTD] intended for? If intended for sending to old MS then this should be done via secondary routing on the original IF-035, not via another separate IF-035 message produced by MPRS with different event code. | Closed |  |  | 2023-06-23 | This message is effectively a copy of the DSAppAccepted AND/OR MSAppAccepted but sent to the Incumbent (current) Metering Service to act as a trigger for that MS to send MTDs. This should be created by MPRS. Requirements MHHS-BR-RS-053 and MHHS-BR-RS-019 cover Registration Service sending this. Message to check and close | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-195 |  | DI-76 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Originally raised as T4-COM-1691 on 15th Sept 2022: ""MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days "" Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5" | Implemented |  | Interim Release 1 |  | Agreed doc update Also in Reg Notes tab Updated validation rules and Reg notes Updated REG1037 in IF-031 to 2 workings days and updated REG notes, to align with process and requirements | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-196 |  |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Updates are required to clarify nullable fields | Implemented |  | Interim Release 1 |  | Updates to Interface catalogue includes changes to interfaces and block data items which are present and can be null 1. MHHSP - ERI011A - ECS Reports - Internal v5.1: The data catalogue is the only tab that has been updated 2. MHHSP - ERI011B - ECS Reports - External v5.1: The data catalogue, DIP_Common, MHHS-REP-003 and MHHSP-REP-006 have been updated |  | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue, MHHSP-E2E001 End-to-End Solution Architecture MHHSP - ERI011A - ECS Reports - Internal MHHSP - ERI011B - ECS Reports - External | 2023-03-23
MHHS-DIN-197 |  |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Decision taken to document digital signing of interfaces outside of the interface document. | Implemented |  | Interim Release 1 |  | Remove Z0 and ZI blocks from all interfaces. Signing process will be documented in the Code of Connection document. | Technical corrrection | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue Code of Connection | 2023-03-23
MHHS-DIN-198 |  |  | 2023-03-15 | Large Suppliers |  | Haz Elmamon | Large Suppliers | Complex Meter Site | Clarification on complex meter site, passed down from DAG as part of the work off plan, Haz to gather concerns for discussion at DA. LSC Rep provided information to the issue on 22-Mar-23 | Requires Industry Work Group review |  | Interim Release 4 | 2023-08-09 |  |  | MPAN Ownership | [6 empty] | 2023-07-14
MHHS-DIN-199 |  |  | 2023-03-23 | BGAS | 3460 | Neil Strange | large Suppliers |  | Participant wishes to see the use of standardisation in the interfactions between the SDS and sub roles MDR PSS | Closed |  |  |  | Closed based on recommendation for programme CR to be raised by the Large Supplier Rep | No Change | Supporting Docs | SDS Validation / Extimation | MHHS-DES138-Interface Catalogue
MHHS-DIN-200 |  |  | 2023-03-24 | CGI | 3489 | Chris Beard | Software Provider | Hierarchy definition for selecting correct register reading in the case of multiple readings for the same settlement period | If there are multiple register readings available for the same Settlement Day, where is the hierarchy defined for selecting which should be used? Is this solely based on Reading Method (i.e. 1. A – Actual, 2. C – Customer, 3. E – Estimated by SDS, 4. S – Estimated by Supplier) or is it dependent on other factors such as the Event Code in the IF-041 ([ReadingRemv], [ReadingInstl], [ReadingEnergisationChg], [ReadingCOR], [ReadingOnSite], [ReadingCOS], [DSEstimate], [SupplierAgreedCOS], [ReadingOverride], [ReadingRemote])? | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Reading methods do not apply to Register Readings - recommendation for DIN to be closed. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-201 |  |  | 2023-03-24 | ESG | 3529 | Patricia Parker | Software Provider |  | IF-033 Validation for population into the IF-034 The receiving party business validation rules state “Each Service Provider will need to determine their own validation criteria when processing Appointment Requests. The list below is intended to cover a number of potential possibilities based on the data items made available, and not to suggest that Service Providers needs or should perform such validations.” But should the DI-143 ‘Service Provider Proposed Appointment Response Code’ not form a valid set list (ENUM Vals) in the Data Catalogue so that all parties are working to the same list of applicable codes, rather than this field being a string with a length of 200 field? | Closed |  |  | 2023-06-23 | IF-033 has been updated as part of Interim Release 1 and the ENUM Vals will not be updated this is because we will have dynamic error messages which cannot be enumerated. |  | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-202 |  |  | 2023-03-24 | ESG | 3513 | Patricia Parker | Software Provider | Operational Choreography 60 minute turnaround | Registration Responses in connection with the PUB-31 given the NFS requirement is a 60-minute turn-around time. Within the Operational Choreography there is requirements OPC-140: From our understanding this means that when suppliers receive the PUB_032 from the Reg Service rejecting the appointment Request suppliers then have 60 minutes to re-issue a fresh IF_031 appointment. For example, there is a rejection code for 'CSS Reg ID not known', this would suggest that a party is out of sync and would need investigating especially as in this case, the REG ID would have previously been provided on PUB- 002, DI-849 and CSS is the master of the REG ID and not the Registration Service. | Implemented |  | Interim Release 2 | 2023-06-23 | Added suggested text to Ops Choreography. Suggested text is "It is noted that some requests may require manual work and may be as a result of incorrect appointments from the Supplier. The expectation will be 90% of requests are systemically processed within 60 minutes with the residual being processed by the end of the following working day". | Doc Ref correction | Supporting Docs | Operational Choreography | MHHS_OPC001_Operational_Choreography |  |  |  |  | 2023-06-16
MHHS-DIN-203 |  |  | 2023-03-24 | CGI | 3502 | Chris Beard | Software Provider | mapping of Estimation Reason Codes to estimation Methods | MHHSP-METH001 M-13. Can you provide a definitive mapping of Estimation Reason Codes to estimation Methods? For example, LTV to Method 11. When should an SDS use Estimation Codes such as Opt Out, Comms. Fault. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated METH001 section 7.3 to reflect Estimated Methods to Estimated reason codes | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001 |  |  |  |  | 2023-06-16
MHHS-DIN-204 |  |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | De-energised sites | MHHSP-METH001 M-3. Which estimation Method should an SDS use for de-energised MPANs that would result in an estimation code of ‘De-Energised’? Without a specific Method statement to cover de-energisation, we will end up estimating consumption. | Implemented |  | Interim Release 2 | 2023-06-23 | Added Method 13 to reflect de-energised sites within METH001 and updated section 2.29 on METH002. | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001 |  |  |  |  | 2023-06-16
MHHS-DIN-205 |  |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | Removal of Estimation Reason Code "Disconnected" | Can you confirm that the Estimation Reason Code ‘Disconnected’ will be removed from the table in 7.3? | Implemented |  | Interim Release 2 | 2023-06-23 | Removed "Disconnected" from Table 7.3 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-06-16
MHHS-DIN-206 |  |  | 2023-03-27 | St Clements | 3703 | Anna Davis | Software Provider |  | Within the MHHS-E2E001 - End-to-End Solution Architecture, there is reference to MHHS-E2E003-Physical Interface Specifications in 1.3 References section This should be labelled as MHHSP-DES138-Interface Catalogue | Implemented |  | Interim Release 1 |  | Updated 1.3 reference section | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-207 |  | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Clarity on when agent appointments should become effective | There is ambiguity within the design on when agent appointments should become effective, which means that different participants have a different view on when agent appointments should become active. | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Appointments become active at midnight local time. | Process Model correction | Migration |  | BP001 & BPD001 BP002 & BPD002 BP003 & BPD003 Migration Design |  |  |  |  | 2023-07-14
MHHS-DIN-208 |  | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Registration Service rejection of Legacy messages for an MPAN | Within the existing Migration Design, it is stated that the Registration Service should reject all Legacy messages for a given MPAN once a Forward Migration has been initiated for said MPAN. This would prevent a legacy MOP from sending the relevant legacy flows if they need to change a meter when an MPAN is mid migration... | Closed | [12 empty] | 2023-07-14
MHHS-DIN-209 |  | Design Team | 2023-03-30 | Design Team |  | Sean Cooper | SRO Design Team |  | ~ Level 1/2 Error Code "MSG0000 - Success" Added to Interface Intro Section ~ MSG0018 - Timestamp cannot be future removed and explainatory note added to IF Notes Section of DIP Common | Implemented |  | Interim Release 1 |  | Updated actioned in v5.1.1 of IF Doc. This relates to MSG1008 not MSG0018 as originally given in the design issue. MSG0000 Success added. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-210 |  | Design Team | 2023-03-30 | RECCo |  | Sarah Jones | Consultancy |  | Possible change flagged The original view of the Design Team was that this flag and associated info (ie Is a Customer Direct contract in place, who is the DS/MS with that contract, but not the Eff To Date aka Contract End Date) should be visible to incoming Suppliers, for exactly the reasons you suggest i.e. so that in an incoming supplier could factor the existence of a CDC(s) into their acquisition process / pricing etc. I think we also felt that SP’s who weren’t currently appointed, but may have signed a new CDC should also have the ability to set the flag, as it’s the sites that are part of a CDC, but where that SP isn’t the appointed SP that are the most difficult to coral and manage. The position at the moment is that the existence of a CDC would be shared with incoming Suppliers as part of PUB-002, however this would likely be too late in the process to provide the assistance and support required to an incoming supplier (on all aspects of the sale, contract/price in particular) … … therefore, I think it was also envisioned that information about CDC’s would be available via ECS – so prospective suppliers could check in ECS on the CDC position as part of the other pre-acquisition checks they may undertake. Therefore, I think the decision on exactly what information is shared ‘pre-acquisition’ to participants probably sits with yourselves (RECCo) to finalise as part of your ECS Design / DP Assessment. All information in relation to CDC’s will be passed/made available to ECS via receipt of a copy of PUB-039, so what item(s) are displayed and to what parties I think would get covered off as part of that ECS Design activity. | Closed |  |  |  | Closed, as per discussions with RECCo that no design changes are required. | No Change | [7 empty] | 2023-06-16
MHHS-DIN-211 |  | DI-139 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-009 Event Code is referred to as [CSSDeRegistration] in the population notes and swagger open API spec but then B042 block title references event code CSS Deactivation, B042 should reference CSSDeRegistration. | Implemented |  | Interim Release 1 |  | Update B042 to reference CSSDeRegistration | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-212 |  | DI-140 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | MHHSP-BP007-Disconnection-v5.0 is missing IF-050 being sent out on a change to MPAN/RMP Status | Implemented |  | Interim Release 1 |  | to BP007 and BPD007 Requires a flow from Registration Service to EES (IF-050 to DIP, a Publish Change to MPAN/RMP Status process, a PUB-050 from DIP to EES process Receive Change to MPAN/RMP status) starting at step 70 (disconnection). Plus add new step descriptions to the BPD and amend Step 70 description to include IF-050. | Process Model correction | Metering Changes |  | MHHSP-BP007-Disconnection, MHHSP-BPD007-Disconnection
MHHS-DIN-213 |  | DI-141 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Data item 997 in S1 common block is senderId in swagger hub, but senderDIPID in data catalogue | Implemented |  | Interim Release 1 |  | Update swagger to reflect senderDIPID to align to data catalague | Technical corrrection | Technical Artefact | Swagger | JSON,YAML
MHHS-DIN-214 |  | DI-142 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | REG Notes section Queuing of Prospective Appointments Rule 4 ** Rule 4: If App Scenario = 'SEG' and Supplier ID + Appointment Service Start Date = Existing Supplier ID + Service Start Date > (Service Start Date +2 working days) >> Appointments meeting Rule 4 have missed their opportunity, and will be 'Lapsed' (PUB-035) This rule doesn't make logical sense, needs correcting. What is the intended logic to be applied here? | Implemented |  | Interim Release 1 |  | Update to align with validation rule | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-215 |  | DI-143 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 for event code [MeterRemoval] rule REG1002 Sending Metering Service ID [SO.SenderID] is currently appointed OR held a valid appointment for Meter Installation Date [DI-057] This should read removal date not installation date | Implemented |  | Interim Release 1 |  | Updated validation rule REG1002 in IF-005 for event code [MeterRemoval] to refer to Meter Removal Date (DI-058) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-216 |  | DI-144 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-144 On IF-005 MPRS will validate Either current, queued SEG or previous MS If previous and not within 10 working days will reject with REG1003 If not previous, and not current or queued, will reject with REG1027 MPRS will then validate if install date/removal date is within MS period of ownership If not will reject with REG1019 REG1019 need correcting to also include <ETD to apply for previous MS It’s not possible to get a scenario where the If-005 passes the above rules (REG1003, REG1027 AND REG1019) but fails REG1002. Therefore REG1002 is not needed and will never be sent as a rejection code. (Add to DI-43) | Closed |  |  |  | Agreed with SCS that no further change is required | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-217 |  | DI-145 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | On IF-005 REG1019 should also include validation that the installation/removal date concerned is <=Effective to date (ETD) of MS period of ownership | Implemented |  | Interim Release 1 |  | Updated IF-005 validation rule REG1019 to include validation that the removal/install date must be <=Effective to date (ETD) where the update is being provided by previous Metering Service (using their 10 day window) for MeterRemoval, MeterInstall and MeterExchange events. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-218 |  | DI-146 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 for event codes [MeterExchange] and [MeterRemoval], the rule should not reference DI-056 which is the meter ID in the installation block, it should should referenced DI-053 which is the meterId in the removal block | Implemented |  | Interim Release 1 |  | Rule updated not to reference DI-056 which is the meter ID in the installation block, it now references DI-053 which is the meterId in the removal block | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-219 |  | DI-147 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 - for other event codes removal date must be >= to Install date but for [MeterUpdate] the rule states > meter install date. Should be >= | Implemented |  | Interim Release 1 |  | Update rule for [MeterUpdate] to align to other removal date event codes | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-220 |  | DI-148 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1007 unecessary and will never be triggered, it is already covered under REG1001 cannot submit meter install if MPAN is disconnected | Closed |  |  |  | Valid rule to left in as-is but noted cannot be SIT tested | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-221 |  | DI-149 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In the IF-005 guide it states: "When amending the Installation and/or Removal date of a Meter, a supporting MAP history commencing in line with the revised Installation Date must also be provided. Any additional MAPs should be provided in chronological order, each with a ‘MAP Effective From Date’ greater, by at least one day, than the previous." MPRS will accept if the install/removal date is changing AND the MAP History has not been included, there is no requirement in Interface Catalogue or Registration Requirements to reject if MAP history is not provided. | Closed |  |  | 2023-06-23 | Believe covered by MeterHistoryUpdate rules, but hopefully won't be an issue pending agreement on MAP discussion… IF-005 use case guide will be updated with outcome. DRG has agreed to remove MAP history therefore in lieu of this decision, this change will not be required. Closed | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-222 |  | DI-150 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | sarah | Implemented |  | Interim Release 1 |  | Updated wording to match existing validation. Guidance only now provided | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-223 |  | DI-151 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005: Need REG1006 to apply to all event codes, e.g. Meter Update on a change to removal date, will need to check that the removal date does not lead to non unique Meter IDs (overlapping dates) MPRS will reject with REG1006 in this scenario | Implemented |  | Interim Release 1 |  | Added REG1006 validation checks to MeterHistoryUpdate and MeterUpdate events. | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-224 |  | DI-152 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 Interface Note below could be read as MeterUpdate event code can be submitted by previous or prospective MS which is not correct "Only the Appointed Metering Service, and for a small window (10 days) to allow for delayed notification of field activities the previously appointed Metering Service; and an incoming Metering Service with a Prospective 'SEG' type appointment may send an IF-005 and update metering details. The [MeterHistoryUpdate] may only ever be used by the Appointed Metering Service. Interface Design assumes that two separate meters with the same 'Meter ID' cannot be installed at the same time. " | Implemented |  | Interim Release 1 |  | Updated | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-225 |  | DI-153 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | DI-849 CSS Registration Request Id does not have a YAML name in the interface catalogue In the swagger hub, the corresponding name is CSSSwitchID which is misspelt | Implemented |  | Interim Release 1 |  | Updated Data Catalogue to CSSRegistrationRequestID, Swagger to follow | Data interface correction |  | Interface Catalogue Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-226 |  | DI-154 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In MHHSP-BPD007 - Disconnection v5.0, the ordering of the steps are out of order. Steps 140, 145 and 150 are for parties receiving the de-appointment notification from the Registration Service, but this is not sent until Step 155. Step 155 “De-Appoint Services” needs to be before Step 140 “DS De-appointment Notification”. Also Step 145 “Receive De-Appointment Notification” is DIP receiving the de-appointment notification to send on, this needs to be after Step 155 and before Step 140 . The ordering should be: • De-appoint services (155) • Receive De-Appointment Notification (145) • DS De-Appointment Notification (140) • MS De-Appointment Notification (150) | Closed |  |  |  | No plans to change step numbers as long as they are unique | No Change |  |  | BPD007
MHHS-DIN-227 |  | DI-155 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1.xlsb, the validation for REG1003 – “Metering Service ID [S0.SenderID] post appointment update period for MPAN [DI-063] has expired” is currently set to “Metering Service [S0.SenderID] holds valid previous appointment then [System Date] should be < [REG.App End Date] + 10 working days”. Should this be <= to allow for the full 10 days? | Implemented |  | Interim Release 1 |  | Changed to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-228 |  | DI-156 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 - IF-005 has the following error for [MeterExchange] & [MeterInstall]:- “REG1020 - MAP Effective Date [DI-054] cannot take place in the future” Should this validation also be valid for [MeterUpdate] and [MeterHistoryUpdate]? | Implemented |  | Interim Release 1 |  | Added to meter update for removal date. Added to MeterUpdate and MeterHistoryUpdate for MAP effective date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-229 |  | DI-157 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 does not have a rule that the SMSO EFD must not be prior to the latest SMSO EFD. We are implementing this rule with error code REG1019 | Implemented |  | Interim Release 1 |  | We are implementing this rule with error code REG1019 Make consistent with others ( PC and ssc + 1 ). Review IHD and SMSO | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-230 |  | DI-158 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 & IF-005 do not have a rejection code where the IHD is invalid. | Closed |  |  |  | DIP will reject non-valid values - no change to docs required | No Change
MHHS-DIN-231 |  | DI-159 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-005 - There is no validation on Meter Removal date [DI-58]. This should be mandatory non nullable for [MeterRemoval],[MeterExchange],[MeterUpdate], but mandatory nullable for [MeterHistoryUpdate] to allow for reinstating a previously removed meter. Currently in redlined v5.1, this data item is optional and non nullable. | Implemented |  | Interim Release 1 |  | Meter Removal changed to nullable, block conditionality updated | Missing/incorrect validation rule | Metering Changes | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-232 |  | DI-160 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-160 on the interface catalogue DCC Service Flag validation rules are specified in IF-025, but DCC Service Flag is not received in this interface. Needs removing. | Implemented |  | Interim Release 1 |  | not needed rules removed. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-233 |  | DI-161 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 – IF-025, where the event type is [ConsentGranularity] Error Code - REG1019 - Consent EffectiveFrom Date [DI-018] must be within Suppliers period of ownership Test Condition - Consent Granularity EffectiveFromDate [DI-018} must be < [Reg.CurrentSupplierEndDate] if exists Should this be <= as it could be on the end date? | Implemented |  | Interim Release 1 |  | Updated to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-234 |  | DI-162 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Registration Services Requirement MHHS-BR-RS-021 should be amended to: Registration Service must, where more than one Metering Service appointment request is received from the same Supplier for the same MPAN CSS Registration Request ID, and for the same date, take the last received Metering Service appointment (based on the Sender timestamp) as containing the correct information. Any earlier appointments should be lapsed. To allow multiple queued service appointments for the same registration will be overly complex to design, code and test, and is likely to cause confusion and issues in live operation. It is much simpler and cleaner to only allow one queued service appointment at a time, per registration. This would still allow the Supplier to replace a queued appointment that's incorrect. The Supplier could submit further changes once the first change has completed, if there is a genuine case of multiple changes to SP in a short period of time. It would not impact on CoS. Our proposal is to allow one pending queued appointment per registration, so could have a queued appoint on current registration AND queued appointment on CoS registration at the same time. | Implemented |  | Interim Release 1 |  | Updated MHHS-BR-RS-021 to refer to CSS Registration Request ID. Added REG1089 - Subsequent appointment received as an error code in the interface spec | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-235 |  | DI-63 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Original wording:- In the business process diagram for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 Update required:- Please close this design issue as CSS0700 is the correct reference for update of status. | Closed |  |  |  | DUPLICATE OF MHHS-DIN-63 | No Change
MHHS-DIN-236 |  | DI-163 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, 02-DIP-COMMON - R0 response - DI-980 Response Message has been updated in Swaggerhub to be an array, but this is not clarified in Interface Spec. DI-979 Response Code should not be an array. | Implemented |  | Interim Release 1 |  | Added note in Introduction section to confirm that DI-980 can be an array Agreed DI-979 Response Code is not an array | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-237 |  | DI-164 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-034 S0 DI-999 Event Code option of [DSAppSPRepsonse] is misspelt. This is also misspelt in Swaggerhub. This could cause differences between systems and should be corrected to [DSAppSPResponse] | Implemented |  | Interim Release 1 |  | Updated typo in IF-034 DI-999. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-238 |  | DI-165 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation on MS/DS EFD being within permitted advanced period. This is covered under migration document but not implemented as a validation rule for IF-031. MHHS-DEL961 Migration Design Document section 6.1.1: For the purposes of the CoA Migration process, the below business rules should be followed by Suppliers regarding the lead time between the submission date of the IF-031 and the requested effective from date of the Migration. a. An effective from date from Same Day +1 up to a maximum of 28 calendar days (inclusive of the 28th day) in the future is permissible. | Implemented |  | Interim Release 1 |  | 28 Day in advance rule added to if-031 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-239 |  | DI-166 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Requirement MHHS-BR-RS-134 states MPRS must automatically de-appoint the MS & DS when the Market Segment Indicator changes to NO. Is this the intended design? | Implemented |  | Interim Release 1 |  | Removed reference to Market Segment Indicator from the requirement MHHS-BR-RS-134. | Requirement correction | MPAN Ownership | Market Segment | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-240 |  | DI-167 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Current validation on IF-031 Rule REG1037 will mean MPRS will lapse any appointment where the system date is greater than appointment EFD + 2 working days. This means if a SEG change fails, and the supplier tries to resubmit the SEG change, with EFD more than 2 working days in the past, MPRS will immediately lapse the appointment. If there is a need to allow retrospective SEG changes, more than 2 working days after EFD, then the wording will need to be amended to apply to max(EFD+2 working days, MPRS system date on receipt of IF-034 + 2 working days) | Implemented |  | Interim Release 1 |  | Introduction of Lapsed Response Codes and Rules in IF-035 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-241 |  |  | 2023-02-01 | C&C | 3430 | Graham King | Software Provider |  | IF/PUB-018 message with event codes [AddressChg] and [DUOSTariffIDChg]. According to Interface Catalogue routing rules, these events are not communicated to the LDSO role via the PUB-018. We assume that the assumption here is that because these data items are mastered by the LDSO that all internal LDSO systems share this data. This is unlikely to be the case. DUoS billing systems co-exist alongside other LDSO management software and are often supplied by different vendors. They do not and cannot share data sets. Given this real-world separation, would it be possible to make the PUB-018 message available to LDSO in the list of Secondary Routing paths? The alternative would mean developing communication channels between disparate systems, from potentially different software vendors in order to pass information from one to the other. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-242 |  |  | 2023-04-04 | ESG | 3713 | Patricia Parker | Software Provider |  | How will the Metering Service be kept informed of who the currently appointed Data Service are? On BP003 is shows the Metering Service being a recipient of the PUB_036 when a DS appointment becomes effective, however looking at the routing rules in DES138 it does not show ‘MSSC’ or ‘MSAC’ as being recipients? | Closed |  |  | 2023-06-23 | Close - changes to Secondary routing make this DIN Moot - Ref DIN-268 | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-243 |  |  | 2023-04-05 | Change Request |  |  | Programme | CR-015 E7/E10 Off Peak Consumption Solution | CR015 - Differential Settlement for E7 / E10 Meters for Smart Opt-out customers | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Changes as agreed at DRG and slides circulated. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | CR15 | 2023-06-16
MHHS-DIN-244 |  |  | 2023-04-04 | British Gas | 3874 | Neil Strange | Supplier |  | D0275: Until v0.3 of DES196 was released our understanding was that the D0275 would be retained and it’ use was optional. We are feeding this back on the D-025 consultation but don’t want to lose sight of this. Its removal will impact our billing systems and substantially drive up implementation costs. The baselined IF-021 also does not handle the clock change | Closed |  |  | 2023-06-23 | Alignment with D0275 D0275 is not part of of the baseline design requirements. If you require this, it is by mutual agreement between parties. NO change required, only clarification. | No Change
MHHS-DIN-245 |  |  | 2023-04-01 | Avanade/ Design Team |  | Grant Sutcliffe | Software Provider | Transaction ID and Correlation ID increase field length to 60 | Transaction Id Could the length specification of the TransactionId be increased to be a max length of 60. The need for this is to cater for a 16 character length hex value (increasing from current length of 6 characters]. This would ensure that we achieve uniqueness. It will also provide headroom for any length increase in other Transaction Id constituents, such as Role. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: T-041-1234567890123-SUP-20230220-619C1F6967838002 [Length = 50] Example from DES138 spreadsheet: T-006-1234567890123-SUP-20220401-1234CC [Length = 40] Correlation Id Could CorrelationId length also be increased to 60 max length of 60 - for the same reason. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: CI-BP-011-20230222-619E0BD1D1FD9000 [Length = 35] Example from DES138 spreadsheet: CI-BP-011-20230222-1234567890123 [Length = 32] | Implemented |  | Interim Release 2 | 2023-06-23 | Updated DIP Transaction ID and DIP Correlation ID to String 60 in Interim Release 1. The examples have been updated to reflected MHHSP-DES138-Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-246 |  |  | 2023-04-12 | Change Request |  |  | DCUSA | CR-019 Replacement of D0242 D0315 for MHHS | CR019 - Replacement of D0242 D0315 for MHHS | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors) and receivers (suppliers) of the flows has identified the desired flow content and now wish to bring this back to the program to ensure that it can be delivered in readiness for migration. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the supercustomer data from settlement (REP-002/002A). There will be removal of certain data items used in the current process and addition of new data items, making population of the D0242 ‘Supercustomer DUoS Daily Statement’/D0315 ‘Embedded Network Supercustomer DUoS Daily Statement’ impossible in their current format for migrated customers. The “MHHS Design: Reporting and Transition Sub Group” identified the need for a new DIP flow to replace the D0242/D0315 last summer but noted that these flows are under DCUSA ownership and so passed the development of the flow content to DCUSA. More information including the proposed Interface can be found on the collaboration base under CR019 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-247 |  | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Update to the Core Design Interface Catalogue (MHHSP-DES138) is required to include the addition of IF-003 | Closed |  |  | 2023-07-12 | Closed captured under DIN-434 as part of migration update review IF-003 defined as part of Migration baseline The structure of the IF-003 will be updated to include ‘Incoming Supplier Details.’ The two new data items within the ‘Incoming Supplier Details’ will be: RevMig Incoming Supplier MPID RevMig Incoming Supplier Effective From Date Business Rules: In the case of Smart Meters undergoing Reverse Migration only, the Registration Service will populate the ‘Incoming Supplier Details’ as part of the IF-003 which is sent to the outgoing MS (via the DIP). This is so the outgoing MS can correctly route the Skeleton D0150 to the new Supplier (which in turn enables the new Supplier to generate a D0367). If the D0205 is not sent to the Registration Service before the IF-003 is issued, the data fields used to confirm the identity of the DC and MOP will be blank; no default values will be populated. In this case, the DC and MOP will need to contact the Supplier to initiate a manual transfer of data. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-248 |  | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Updates to the ISD Entities document (EDI021, v5.0) | Closed |  |  |  | To be picked up as part of Migration IA - - new DIN will be raised as required. |  |  |  | EDI021 |  |  |  |  | 2023-07-14
MHHS-DIN-249 |  | Migration Design | 2023-03-27 | Migration Design |  | Matthew Breen | Programme |  | Discussion around the use of BST/UTC during Migration | Closed |  |  |  | DIN is not specific enough. | [8 empty] | 2023-07-14
MHHS-DIN-250 |  |  | 2023-04-06 | Design Team | 3764 | Steve Weston | Programme | Participant ID 10 digit number | This is related to ticket 3764, to update the Interface Specification to ensure the Participant ID is clearly defined as a 10 digit number [0-9] only, and the examples in the Interface Specification align to this, including where this is used as part of the sender unique reference and the examples shows 11 digits, not 10 digits for Participant ID. | Implemented |  | Interim Release 2 | 2023-06-23 | In E2E001 doc Section 4.2.3.2 Section 4.4.4.2 example code for Sender unique Ref and in Transaction ID Section 4.5.5.3 as above DES138 doc Data Catalogue tab: DI-990 example and DI995 Example DIP common tabl DI995 example and the example JSON block (the above easy to change) ALL the IF tabs the JSON block example the Sender Unique Ref contains Participant ID and in every example its longer than 10. JSON/YAML Files: Update JSON examples where Sender Unique Ref and Transaction ID contain a Participant ID example longer than 10. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 Solution Architecture MHHSP-DES138-Interface Catalogue JSON/YAML files |  |  |  |  | 2023-06-16
MHHS-DIN-251 |  |  | 2023-04-06 | Design Team | 3860 | Steve Weston | Programme | IF-041 Population | This is related to ticket 3860, to update the Interface Specification to provide more clarity / notes on the optionality of B064 and B065 blocks in the IF-041 interface. This is in relation to notes / detail about which blocks are mandatory (from a contractual perspective) versus what should be included in the message if the data exists. | Implemented |  | Interim Release 2 | 2023-06-23 | Updates the notes section of IF-041 in order to provide guidance on the minimum population of B064/B065 blocks. This clarifies "When exchanging readings between parties the design assumes that in the most part this will be the Cumulative Register Reading (Block B064). However, at participants request this message also allows for the exchange of Configurable Register Readings (B065) either alongside a Cumulative Reading or in isolation. For the avoidance of doubt the message must contain at least one B064 record and /or one (or more) B065 records [depending on the number of configurable registers], in order to be considered valid. " | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-252 |  |  | 2023-04-06 | Centrica | 3661 | Neil Strange |  |  | We believe there is a Design Gap at Change of Agent and Change of Supplier for Smart Meters which also impacts Migration. Neither the Registration Service, Metering Service nor Data Service will know how the registers are set up and specifically which are active. Consequently the Data Service will not know which registers to send on the IF-041, nor will there be able to calculate consumption correctly without knowing the register set up. The interface catalogue for IF-041 states in respect to this “B065 Block Below Repeated for each set of Configured Register(s) for each Meter” – we do not believe there is a way to give the DS this information. The supplier will set up the smart meter configuration to enable the registers to capture the usage for certain time periods. There is currently no way for the supplier to inform the DS which registers are active at what time of the day - the DS cannot accurately calculate the consumption breakdown based on the reads when there are multiple registers configured. | Closed |  |  |  | DIN closed, Design Team to send email recommending for a CR to be raised. | [8 empty] | 2023-07-14
MHHS-DIN-253 |  |  | 2023-04-12 | British Gas | 3769 | David Hipwell | Large Supplier | Volumetrics | The latest E2E Functional and Non-Functional Requirements MHHS-E2E Requirements V3 which went to V3 on 16/02/2023 appears to focus on message counts and response times. For example:- During transition all meter points (ca. 31M) will be transition between the old and new services. Therefore assuming a linear migration over the year this would result in the load below, hence services shall be capable of processing the following volumes: - average daily volume of 680,000 - peak daily volume of 2.4M 5.0M - annual volume of 248M 500M Analysis of the flows needs to be categorised across all impacted market participant roles including the DIP. Only then will it have meaning for all parties. The calculation needs to take account of the migration period using the MHHS migration volumes according to date (including REVERSE migration). These should be in both message counts and also sizing (e.g. Gb). And include for a BAU day and also migration days. Whilst some calculations can use the total number of MPANs, to be useful these need show also at perhaps for a million MPANs in each role. Only then will all parties be working on a single set of figures. A line in the sand. The NFRs that exist appear to have moved away from any form of technical calculation towards business process figures. But these figures need to go as an input into technical sizing’s, and should have done for DIP – can these be produced and published ? | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09
MHHS-DIN-254 |  |  | 2023-04-17 | Siemens | 3044 | Tony Mason | Metering Service | Update of Consent, DPI, etc. | this does surprise me and doesn’t seem to correspond to the routing rules in the Interface Specification. A proposed Data Service is not included in the routing tables for the receipt of a PUB-018, for example. I would therefore expect that if a change to DPI occurs between PUB-033 and PUB-036 the proposed Data Service could only be notified on a revised PUB-033 with the Appointment Scenario set to whatever the original scenario was set to – “SEG”, “CSP”, or “COS”. | Closed |  |  | 2023-06-23 | Ref notes on the maintenance of these data items in the Regi Info Section of the I/F document. Prospective SPs are not notified of changes to these data items during their prospective period. If these Data items change then the supplier should re-evaluate the SP they have proposed and change the appointments as required. If an SP takes on a supply with different elements/factors to those suggested by the supplier at appointment this is a contractual issue between the SP and the Supplier. | [8 empty] | 2023-06-16
MHHS-DIN-255 |  |  | 2023-04-17 | Elexon | 3983 | Kate Goodman | Testing | Consumption on De-Energised MPAN (IF-013/IF-014) | ConsumptionOnDeEnergised is an Event Code mentioned in the list of data items but is not present in header where the routing info is held - needs to be added to header | Implemented |  | Interim Release 2 | 2023-06-23 | ConsumptiononDeEnergised event moved from IF-013 to IF-014 and added in routing rules. See also DIN332 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-256 |  |  | 2023-04-17 | Elexon | 4169 | Kate Goodman | Testing | IF-014 Block B067 | DI-015 is mentioned in the header wrt routing but is not present in the message itself. It either needs to be removed from header or added into message. | Implemented |  | Interim Release 2 | 2023-06-23 | Block B067 added to IF-014 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-257 |  |  | 2023-04-17 | Elexon | 4172 | Kate Goodman | Testing | B053 repeating block | B051 is a block which repeats for each combination of Load Shape Criteria (denoted with single chevron to show repeat). B053 is another repeating block which is denoted by two chevrons, implying it is nested below B051. But in fact it also repeats for each combination of Load Shape Criteria. Should this just have a single chevron or is there further information that needs to be added to make its double chevron make sense? | Closed |  |  | 2023-06-23 | No change required as there will be multiple B053 in each B051 block. | No Change |  |  | none
MHHS-DIN-258 |  |  | 2023-04-19 | ENWL |  | Paul Band | Network Operator | LDSO use of DIP vs internal for Specific messages | There are a number of requirements in the MHHS-BRS005-LDSO document which state that we must obtain various registration data via the DIP and maintain records accordingly such as: MHHS-BR-LD-001-005, MHHS-BR-LD-024, MHHS-BR-LD-030 and MHHS-BR-LD-034 Extrapolating these into requirements for our own systems suggests that we should build databases/tables to store this data and maintain it The requirement is placed upon us as a party under the assertion that all settlement related data should be exchanged between services and parties via the DIP. However LDSO’s are unique in that their data exchange for their party type is split and is typically split by system under these party types. As a consequence we already communicate directly with MPRS as it is already part of our system architecture as a paid for and created service by LDSO’s. | Requires Industry Work Group review | 2023-07-17 | Interim Release 4 | 2023-08-09 | Discussion at the DRG of the 27/4/23 did not agree on the development of a New Design Principle, A further workshop with LDSOs needs to take place to discuss alternate options and confirm agreement amoungst all DNOs & IDNO on the receipt of publication | [8 empty] | 2023-07-14
MHHS-DIN-259 |  |  | 2023-04-20 | ESG | 3756 | Patricia Parker | Software Provider | BP003C correction | On BP003C under the CoR section there is a note which states that the readings that pass validation should have Meter Reading Status (J0047) set to ‘T’ and when it has failed set it to ‘F’. However as per the REC the group which houses the J0047 group (032 – screenshot below) should only be present where the Meter Reading Flag (J0045) is set to ‘F’. I have checked DES196 and cannot see that the conditionality for that group is changing in the D0010 therefore I can only assume that the note on the process map is incorrect, and it should be talking about the J0045 value instead. Please can you confirm? | Implemented |  | Interim Release 2 | 2023-06-23 | Modification to Note on process to refer to "Meter Reading Flag (J0045)", modify flow label to step230 to "(Read Flag = "T")" Modification to the process note to advise the J0047 would not be present if the meter reading flag (J0045) is set to "T". It will only be present in case the J0045 is set to "F". | Process Model correction | Metering Changes |  | MHHSP-BP003C-Transfer of Reads |  |  |  |  | 2023-06-16
MHHS-DIN-260 |  |  | 2023-04-20 | CGI | 4167 | Dave Webster | Software Provider |  | Swagger definition does not match DES-138 in version 1.0 or 1.1. | Closed |  |  | 2023-06-23 | No specific detail provided, however comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1, therefore closed
MHHS-DIN-261 |  |  | 2023-04-20 | Utiliteam | 4245 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. Configurable Register Reading Date/Time is missing. | Implemented |  | Interim Release 2 | 2023-06-23 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue JSON/YAML Files |  |  |  |  | 2023-06-16
MHHS-DIN-262 |  |  | 2023-04-20 | Utiliteam | 4214 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. B070 for IF-031 is wrong. It contains the word DIP in the Swagger, which is not included in DES-138. | Implemented |  | Interim Release 2 | 2023-06-23 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files |  |  |  |  | 2023-06-16
MHHS-DIN-263 |  |  | 2023-04-21 | CGI | 4203 | Dave Webster | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. DI-122-Profile-Class is defined as an integer, but in DES138 it is defined as a string length 2. Needs to be updated in the Swagger. | Implemented |  | Interim Release 2 | 2023-06-23 | Swagger and Data Catalogue aligned to String 2 for DI-122 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files |  |  |  |  | 2023-06-16
MHHS-DIN-264 |  |  | 2023-04-24 | Elexon | 3946 | Rashmi Radhakrishnan | Central Body |  | One of my colleague pointed out a typo in the CCC method statement attached, and I would like to draw your attention to it and requesting to make necessary amendments. The CCCID starting from 100 to 107 has Market Segment Indicator as “U” and Connection Type Indicator shown as “W”. We think that, for these line items the Connection Type Indictor need be corrected to “U”. For reference please see below picture and this also aligns with ISD entity spec v5.0 (M2 entity). CCC ID Market Segment Indicator Measurement Quantity Consumption Component Indicator Connection Type Indicator 100 U AI C W 101 U AI L W 102 U AE C W 103 U AE L W 104 U AI C W 105 U AI L W 106 U AE C W 107 U AE L W All 'W's' should be 'U's') | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 |  |  |  |  | CCC Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-265 |  |  | 2023-04-25 | Elexon | 4128 | Rashmi Radhakrishnan | Central Body |  | ISD entity M5 has a filed Settlement Period quality indicator. Is this the complete valid data set for the field Settlement Period quality indicator? I took this below list from interface catalogue v5.0. A = Actual, E= Estimate (UMS Only) A1,A2,A3, AAE1,AAE2,AAE3,EAE1,EAE2,EAE3 (ADV Only) E0 --> E9 = Estimation Method 1 - 9 ZE = De-Energised ZE1--> ZE3 = Zero Estimation Method 1 -3 but the Advanced Data Service Estimation Method Statement has data flags EA1 till EA13 which is not mentioned in the above list. Also, the ISD entity spec M5 example below shows a different data item that is not in the list at all for Unmetered(104 &105). Is this a mistake? | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | The Freshdesk ticket details redlined changes have been made to the DES240 document | [8 empty] | 2023-07-14
MHHS-DIN-266 |  |  | 2023-04-26 | ESG | 3899 | Patricia Parker | Software Provider |  | If the D0300 process is not changing then we believe that DES196 is incorrect and should show added routes to allow the Supplier to send a D0300 to the Data Service Matt M has confirmed - We are working through the exchange of CoS readings as the code drafting has raised some questions about the extent to which the SDS is involved in the D0300 process. For smart meters, the SDS will not have any use for the billing register readings so D0300 process should not apply, or at most could only be missing the total cumulative. However, it likely will still be required for traditional meters. On that basis, I think we can acknowledge that the D0300 will be retained and SVs created for Supplier to SDS for traditional meters. The process for smart meters is being discussed internally as the SDS does not retrieve tariff register readings. There will be an updated version of DES196 issued in the next few weeks to reflect feedback from the DTN flow part 2 consultation issued in late March which will reflect the retention of the D0300. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 |  |  |  |  | MHHSP-DES196- D-Flow and Interface Mapping |  |  |  |  | 2023-07-14
MHHS-DIN-267 |  |  | 2023-05-02 | ESG | 4385 | Patricia Parker | Software Provider | RegX Validation Issue | RegExpression on the DI-148-Annual-Consumption use of DT-016-Decimal-9-3 in the 1.1 swagger spec. This needs to be updated to align with DES-138 example of 123456789.123. Regex should be ^-?[0-9]\d{8}(\.\d{3})?$ instead of ^-?[0-9]\d{7}(\.\d{3})?$ | Implemented |  | Interim Release 2 | 2023-06-23 | Swagger v1.2 has been updated accordingly | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files |  |  |  |  | 2023-06-16
MHHS-DIN-268 |  |  | 2023-05-03 | SRO Design |  | Sean Cooper | SI Design | Secondary Routing | It was always the intention to revisit and revise all of the Secondary Routing configuration as part of DIP Detailed Design. Completion of this exercise has also resulted in some changes to other routing parameters. | Implemented |  | Interim Release 2 | 2023-06-23 | Following discussion with Avanade the Secondary routing short codes have been simplified and the routing of each IF revisited based on these revised short codes. These are shown highlighted in BLUE in the routing section of each of the individual IF pages. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-269 |  |  | 2023-05-03 | St Clements | 4424 | Anna Davis | Software Provider | Swagger Alignment to DES-138 | We have also realised that there are a large number of discrepancies for each interface between the data item name in Swagger vs the YAML name in the Interface Catalogue Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity | Implemented |  | Interim Release 2 | 2023-06-23 | Updated inconsistencies in the Interface 01-Data Catalogue and Swagger. Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-270 |  |  | 2023-05-05 | SRO Design | 4557 | Rob Golding | SI Design | Correlation ID | Provide further clarity on how Correlation ID's work. This will impact numerous artefacts including DES-138 and E2E001 | Implemented |  | Interim Release 2 | 2023-06-23 | DES-138 Interfaces updated to reflect correct 'COPY' property on IF routing tables. updated IF-008, 16, 20, 26, 28, 37, 39 and 50 for this DIN. Added *New to IF-020 showing a new correlation ID is needed to be created for these events, others events needed a COPY of the correlation ID. IF-050 had “No” added to show that a Correlation ID is not required. Updated the E2E001 design document with a more detailed worked example in section 5.4 that details how and where the Correlation ID is populated. | Design Ambiguous | Supporting Docs |  | MHHSP-DES138-Interface Catalogue. E2E001. |  |  |  |  | 2023-06-16
MHHS-DIN-271 |  |  | 2023-05-10 | ESG | 4541 | Patricia Parker | Software Provider | Swagger Alignment to DES-138 | S0 and S1 is Mandatory in DES-138 v5.1.1, but is not marked as mandatory in the Swagger 1.1. Swagger needs to be updated to align with DES-138. | Implemented |  | Interim Release 2 | 2023-06-23 | Swagger 1.2 updated so all SO and S1 blocks are mandatory as per DES-138 | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-272 |  |  | 2023-05-10 | SRO Design | 4656 | Rob Golding | SI Design |  | Required to DIP Channel Publication (v1.2 of the swagger) that will allow DCPs to register webhooks on behalf of their clients | Closed |  |  | 2023-06-23 | Duplicate of DIN-375
MHHS-DIN-273 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | New MSN Data Type | MHHS Data Type (DT-029) - for Meter ID / Serial number for DI-053, DI-056 and DI-060 added to DES138 01-Data Catalogue, Swagger updated. | Implemented |  | Interim Release 2 | 2023-06-23 | New Data Type created in Swagger v1.2 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-274 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | Missing YAML in DES-138 - DI-073, DI-074, DI-080, DI-111, DI-112, DI-190-194, DI-300, DI-021, DI-022, DI-060, DI-076 | Implemented |  | Interim Release 2 | 2023-06-23 | Missing YAML names for Data Items confirmed and added to 01 - Data Catalogue Note:All DI's upsated except DI-076 has not required a changed. Other DI chnages not listed are picked up as part of DIN261 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-275 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | DI-093 / DI-120 - Data length 2,000 not 200. | Implemented |  | Interim Release 2 | 2023-06-23 | All additional info data items set to len 2000 in Swagger v1.2, DES138 DI-093/120 length updated in 01-Data Catalogue | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-276 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Classifications | MHHS Data Classification - ensure all columns are populated for Public and Restricted ie, MPAN & Address (removall all NULLS). | Implemented |  | Interim Release 2 | 2023-06-23 | Data Classifications added in v5.2.1 where previously there was no entry ( Column I in the Data Catalogue ) | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-277 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Owners in Data Catalouge | MHHS Data Owner - where there are NULL's, this should be updated so all columns provide an owner, mark as N/A (remove all NULLS). | Implemented |  | Interim Release 2 | 2023-06-23 | Metering Service added as Authoritative Source and MHHS Owner in v5.2.1 of DES138 Data Catalogue for DI-190 to DI-195. Previously there was no entry. | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-278 |  |  | 2023-05-10 | SRO Design | 4590 | Rob Golding | SI Design |  | Please can DES138 Interfaces spreadsheet be updated to provide an indicator against each interface (or is it interface & event code) as to whether it can be opted in/out by a recipient. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | Subject to ongoing discussion with Avanade. Should be accomodated witin Secondary Routing Solution | [8 empty] | 2023-07-14
MHHS-DIN-279 |  |  | 2023-05-12 | ESG | 4484 | Patricia Parker | Software Provider | Event Code clarifiction for DS when sending back validated customer read on PUB-041 | The BP005 – Data Processing – Process map shows that when a Customer Own Read has been sent to the Data Service from the Supplier in the IF-041, EventCode = ReadingCoR, the Data Service will perform reading validation and issue the PUB-041 back to the Supplier, in the Read Sharing column of the process map. When the Data Service send back the validated customer own read in the PUB-041, what eventcode will they use and where can I find this documented? The previous response says “There is no IF-041 response, check consumption is as expected in PUB-021” is this correct for Customer Own Reads on Smart meters? The map shows otherwise so please can you confirm if the answer or map is correct and if the map is correct, provide information on what event code will be used. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | Solution still yet to be defined | [8 empty] | 2023-07-14
MHHS-DIN-280 |  |  | 2023-05-12 | ESG | 4552 | Patricia Parker | Software Provider |  | DES196 lists the D0386 (Manage Metering Points) as ‘not impacted’ owned by the REC however BP010 shows that the method of maintaining Related MPANs is via the IF_019 / PUB_020 process. Can you confirm whether the D0386 is going to be removed post- MHHS. If not, could you please clarify what process a Supplier should follow post- MHHS. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-281 |  |  | 2023-05-12 | St Clements | 4446 | Madison Layton | Software Provider | BP003 IF-35 flow | MHHS-BR-RS-053 for the incumbent MS to be notified on If-035 DSAppAccepted where meter is advanced or traditional is missing from BP003 business process diagram and steps. Also updates to BP003 and BPD003 forward migration for consistency | Implemented |  | Interim Release 2 | 2023-06-23 | IF-35 flow from step 85 (if accepted where meter is advanced or traditional to Meter Service (incumbent) and additional step 86 to receive appointment response to BP003, and added step 86 and BR-RS-053 ref and details to step 85 to the BPD003 | Process Model correction | Metering Changes |  | MHHSP-BP003-Change of Service - Data Service, BPD003 Forward Migration BP003 and BPD |  |  |  |  | 2023-06-16
MHHS-DIN-282 |  |  | 2023-05-16 | SIMS | 4821 | Martin Freeman | Software Provider | Status code removal | Status Code is included in the E2E001 design response body (4.4.4.2), when this is HTTP Response code and should be removed as this is defined in the callback response. | Implemented |  | Interim Release 2 | 2023-06-23 | Removed from section 4.4.4.2 from the E2E001 design document as this is not required. This now aligns in Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture |  |  |  |  | 2023-06-16
MHHS-DIN-283 |  |  | 2023-05-16 | SIMS | 4826 | Martin Freeman | Software Provider | ID Capitalisation | ID should be capitalised in all places in the Swagger. | Implemented |  | Interim Release 2 | 2023-06-23 | All JSON names now have capitalised ID fields for Swagger 1.2. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-284 |  |  | 2023-05-16 | SIMS | 4828 | Martin Freeman | Software Provider | HTTP Response Code | HTTP Response code for success should be 201 in E2E001 as per Swagger. | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to E2E001 design document in section 4.4.4.1, 4.5.5.1 and 5.3 to align with Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture |  |  |  |  | 2023-06-16
MHHS-DIN-285 |  |  | 2023-05-16 | Elexon |  | Rob Golding | SRO Design Team |  | Add replay / requeue API for Swagger 1.2 to align with existing E2E001 Design. Add additional information / clarity in the E2E001 for Interim Release 2 to align changes between design and Swagger. | Closed |  |  | 2023-06-23 | Duplicate of DIN-374
MHHS-DIN-286 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Issue clarification to Participants through DRG that all ECS Reports will be issues via Pattern B. Update of ECS Report Catalouge to reflect this. | Closed |  |  |  | The ECS reports will be via Pattern A. No change is required to the ECS reports
MHHS-DIN-287 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team | Guidance notes for distribution of ECS reports | Create & Issue guidance document on the distribution of ECS Reports. To Contain : - overview of Pattern B Process - Guidance on population of IF-047 - Update of IF-047 Event Codes | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-13 | [9 empty] | 2023-07-14
MHHS-DIN-288 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Update of Swagger with ECS Reporting Structures | Closed |  |  | 2023-06-23 | These interfaces are in place from Swagger 1.1. | [8 empty] | 2023-06-16
MHHS-DIN-289 |  |  | 2023-05-17 | SRO Design Team | 4994 | Rob Golding | SRO Design Team | Interfaces for consumption replay | IF-015 / IF-016 - updates to E2E001 to provide clarification on design pattern. Alignments between DES-138 & Swagger alongside this. | Implemented |  | Interim Release 2 | 2023-06-23 | E2E001 design updated (Section 5.1.7) to provide additional information / clarity on these interfaces in relation to Consumption Replay. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture |  |  |  |  | 2023-06-16
MHHS-DIN-290 |  |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Proposal to change all / subset of ECS Reports to Pattern B | Closed |  |  |  | Duplicate | No Change
MHHS-DIN-291 |  |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | As a result of DIN-290 -- Where should the reporting assets be hosted?? DIP solution specified, but what are the other options are availible. Final solution option to be ratified and documentation updated. | Closed |  |  |  | Not hosted as via Pattern A | No Change
MHHS-DIN-292 |  |  | 2023-05-17 | St Clements |  | Madison Layton | Software Provider | ISD Entity M17 | Change required to ISD Entity M17 to add in Market Segment into the table - otherwise it cannot be used to derive consent values which was its original purposes | Implemented |  | Interim Release 2 | 2023-06-23 | 1. Update Table name to "Consent Granularity Valid Combinations" 2. Added Market Segment as new table column 3. Update table to show all valid combinations | Process Model correction | Supporting Docs |  | MHHSP_EDI021_ISD_Entities |  |  |  |  | 2023-06-16
MHHS-DIN-293 |  |  | 2023-05-17 | Design Team |  | Paul Petitt | SRO Design Team |  | Retrospective DIN raised to ensure that any changes that are made in multiple downstream documents (for example CoCo, DIP Logical Design, DIP Physical Design & DIP Security Design) are reflected / updated in LDP assured documents to ensure e2e design / requirements alignment. This was agreed in a DRG Meeting in March 2023. | Implemented |  | Interim Release 1 |  | design changes to E2E001 End-to-End Solution covering points described in DIN details | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-294 |  |  | 2023-05-19 | ESG | 5030 | Luke Speakes | Software Provider | BP007 PUB009 flow | What I need to know is if the supplier will receive a PUB_009 with the Event code of [CSSDeRegistration] because nowhere on the BP007 process map does it show the supplier receiving the PUB_009 following a deactivation but on DES138 it shows the supplier as being a recipient of this event code. Step 95 (ringed below) shows the supplier as receiving the PUB_009 off the back of the Disconnection (event code [MPANDisconnection]) but then no where else on the process map does it have the supplier receiving a subsequent PUB_009 following the successful deactivation. Additional step required from step 130 (maybe 137?) to show both PUB-009 Mpan Disconnection and PUB-009 Deactivation going to supplier | Implemented |  | Interim Release 2 | 2023-06-23 | BP007 change : There is already a flow from Step 85 to Step 95 for PUB009 for disconnection (no change) But need to Add a new step (137) for Receive Deactivation in Supplier lane from Step 130 for PUB-009 MPan deactivation in BP007 And there is already a PUB-037 flow from step 145 to Supplier step 157 for confirmation (so no change there) Addition of step 137 to BPD007 | Process Model correction | Metering Changes | Disconnection | MHHSP-BP007-Disconnection, BPD007 |  |  |  |  | 2023-06-16
MHHS-DIN-295 |  |  | 2023-05-19 | SIMS | 4821 | Martin Freeman | Software Provider | L1/L2 Error Codes | Error code detail updates in DES-138 for Level 1 and Level 2 validation needs to be clarified | Implemented |  | Interim Release 2 | 2023-06-23 | Updates made to Introduction Tab of DES138 in order to clarify Lev1 vs Lev2 error codes. Design is such that participants should expect error code(s) at either level. Further ammendments could be made following Avanade clarifications. | Data interface correction | Supporting Docs |  | DES138 Data interface Definition |  |  |  |  | 2023-06-16
MHHS-DIN-296 |  |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | It is envisioned that Configuration Management of ISD will largely follow the existing customs, practices and processes as are currently in place for managing MDD changes. However, DIN is required to formally confirm the Owner(s) and allowable update mechanisms (Standard or FastTrack) for each of the new ISD Entities outlined in the DIN. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-297 |  |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | What Participants are recognised in the existing / new ISD Participant tables…. How does this link in with the parties recognised by the DIP (and assigned DIP Roles / IDs …. Or Not) …. In particular how are MDRs referenced in ISD? Does this reference need to identify the ‘type’ of MDR? Also, there is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-298 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Update to UMSDS method statement. | As I understand it, you are advising we should A flag the consumption data (even though it isn’t Actual), until the zero charge code D0388 UMS Inventory is received from the UMSO. Therefore - if we have an inventory, regardless of the energisation status of the MPAN, we always use an A Flag. But as you’ve stated, this means an IF-013 will be issued to us as UMSDS, because there is A data, against a De-Energised MPAN. If this is the design/requirement then it is understood – but I would like to call out that this should be detailed within the UMSDS method statement – so I think a DIN is needed to get this requirement added? | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Table provided by PDA has been updated and will be shown within section 10, Publish and Data Flags within the UMSDS Method Statement. UMS method statement updated with text to address query. Updated text below: If a D0388 has been received with load associated data and the MPAN is de-energised the load should be calculated, submitted as ‘A’ Flagged but with an Estimation Reason Code of De-energised. | Method statement correction | Supporting Docs |  | UMSDS Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-299 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | IF-013 update to include UMSO recipient | Further to this (DIN-298), the cause of this IF-013 being issued can only be that the UMSO has not provided the UMSDS with the correct D0388 UMS Inventory to use. Therefore – the UMSO has a requirement to receive the IF-013 to tell them this. However, the Interface Catalogue has not designed that this will get sent to the UMSO. I think this is a Design Issue too, and also needs a DIN raising so that the IF-013 is provided to the UMSO. | Closed |  |  |  | No this is incorrect. UMSO is not involved with Consumption. If IF-021 submission is rejected this is an issue for the DS (incl. UMSDS) to address and Manage. Any issues regarding the metering onsite/energisation status need to be managed by the DS (incl UMSDS) with their appointing Supplier and Partner Metering Service. |  |  |  | DES138 |  |  |  |  | 2023-07-14
MHHS-DIN-300 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | You are advising a Load Shape will always require the E Flag. But as you say if the MPAN is de-energised, that MDS will reject the IF-021. Is this therefore your answer – that MDS will reject the IF-021, and there is nothing that can be done about that, so we just need to accept we will get those rejections? If so, this isn’t really a satisfactory process, to know rejections will be received in this scenario. Can you just confirm that the solution here is we just need to accept we will get these rejections to the IF-021, which we will then simply ignore? If that is the case – again a DIN needs to be raised to write this into the Design so the process is documented. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | Table provided by PDA has been updated and will be shown within section 10, Publish and Data Flags within the UMSDS Method Statement. IF-013 recipient list to be updated to include UMSO in DES138 | Method statement correction | Supporting Docs |  | UMSDS Method Statement DES138 |  |  |  |  | 2023-07-14
MHHS-DIN-301 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | the corrective action on this scenario (DIN-300) occurring will be if/when the UMSO provides the UMSDS with a D0388 UMS Inventory – then the UMSDS will stop using and submitting the Load Shape data. There does not seem to be a mechanism in the Design for the UMSO to be made aware of this issue that would be of their making, so again needs raising as a DIN please. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | Table provided by PDA has been updated and will be shown within section 10, Publish and Data Flags within the UMSDS Method Statement. IF-013 recipient list to be updated to include UMSO in DES138 | Method statement correction | Supporting Docs |  | UMSDS Method Statement DES138 |  |  |  |  | 2023-07-14
MHHS-DIN-302 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | I’ve pulled together the below table. This covers all the possible scenarios of the UMSDS either having or not having the D0388 UMS Inventory. Combined with whether that D0388 UMS Inventory has load associated data within it. Also combined with whether the MPAN is Energised or De-Energised. Here I’ve listed which Settlement Period Quality Indicator should be used, and where applicable, which Estimation Reason Code should be used. Should this be included in the UMSDS Method Statement and if so, are you happy with the below. In Green are steps we understand. In Red, these remain Unknown to us based on the Design and your answers given. In Orange, these are answered based on your guidance on your email of 28 April – but are not specified in the written Design. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | Table provided by PDA has been updated and will be shown within section 10, Publish and Data Flags within the UMSDS Method Statement. IF-013 recipient list to be updated to include UMSO in DES138 <--- Design SRO - this is not correct! UMSDS will receive a copy if his submission fails and is not replaced. UMSO/Metering Services are not concerned with Consumption | Method statement correction | Supporting Docs |  | UMSDS Method Statement DES138 |  |  |  |  | 2023-07-14
MHHS-DIN-303 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.2.3 - Changes to Data formatting to align with Swagger / DES-138 | Implemented |  | Interim Release 1 |  |  | Technical corrrection | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-304 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.4.3 - Case Sensitivity - additional information added to provide clarity on approach | Implemented |  | Interim Release 1 |  |  | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-305 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 5.1.7 - Additional Detail required for IF-47 / ISD to provide clarity on approach / steps | Implemented |  | Interim Release 1 |  |  | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-306 |  |  | 2023-05-22 | Tym Huckin | 3992 | Tym Huckin | Consultancy | Clarification/examples for DI-101 for BST/UTC cross over period | Further clarity / worked examples for UTC Settlement Date (DI-101) for BST / UTC cross over period. | Closed |  |  |  | This is not a design change it is a Question/Clarification . | [8 empty] | 2023-07-14
MHHS-DIN-307 |  |  | 2023-05-22 | CGI | 5042 | Dave Webster | Software Provider |  | Status code incorrectly included in required, although not in Standard Response Body Type. This is in Swagger 1.2. | Closed |  |  | 2023-06-23 | Duplicate of DIN-282
MHHS-DIN-308 |  |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | S0 Block required property | Add required property to all the S0 blocks in the interface definition | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger for all Interfaces to mark 3 fields in the S0 block as mandatory. | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-309 |  |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | Swagger Alignment to DES-138 | Define Transaction ID (DI-990) with no Min Length to align with DES-138. This is DT-014. | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (DIP Transaction ID min length removed) | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-310 |  |  | 2023-05-23 | ELEXON | 5173 | Rob Golding | Central Body | Guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 | Guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 are to be applied (if at all), i.e. does the DIP need to consider the effective period and only accept messages on the production system when the message falls within this period? And if so what date within the message should be used as a check? Or the physical date/time of message receipt? Or doesn’t the DIP need to consider these dates at all and no check needs to be applied? | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-13 | This DIN requires an internal workshop with the Design/Technical team. | [8 empty] | 2023-07-14
MHHS-DIN-311 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-985 / DI987 both String 60. Swagger Min and Max Lengths aligned | Implemented |  | Interim Release 2 | 2023-06-23 | Updates made to DES-138 for Length alignment to 60. Updates to Swagger to remove min length for DI-985 and DI-987. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-312 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-984 / DT-009 needs to be updated to be min 3 / max 5 length. | Implemented |  | Interim Release 2 | 2023-06-23 | Sender Role - change on 01 Data Catalogue DI-984 as per description | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface |  |  |  |  | 2023-06-16
MHHS-DIN-313 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S1 - Sender Timestamp updated correctly (from sent timestamp) in Swagger to align with DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (renamed to Sender Timestamp) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-314 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - Publication ID Min Length updated in Swagger 1.2 to be 6 to align with DES-138 (rather than 7) | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Publication ID Min Length now 7, not 6) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-315 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - DIP Correlation ID should have no min length to align with DES-138 (rather than min length of 1) | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (DIP Correlation ID has no min length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-316 |  |  | 2023-05-25 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, all DT-006 and DT-006N should have min length 10 & max length 10 to be consistent. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated DES-138 01-Data Catalogue to align Data Type and provide consistency to Swagger. Removed DI-095 which is no longer used. | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface |  |  |  |  | 2023-06-16
MHHS-DIN-317 |  |  | 2023-05-23 | St Clements |  | Sean Cooper | SRO Design | B9xx array references within Swagger to be updated within DES138 | Update DES138 IF document to include reference to the B9XX Array references held in Swagger | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-13 | [9 empty] | 2023-07-14
MHHS-DIN-318 |  |  | 2023-05-23 | REC | 5049 | Jonny Moore | Consultancy | Addition of 'Effective from date' data items to RMP Status (regi) and MP Status in IF-050 | While completing the design phase for EES we noted that the following items with the IF-050 do not have an effective from date. - RMP Status (Registration) - MP Status These items currently have an effective from date held in EES and not including this in the IF-050 would have the effect of removing these items from EES. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-319 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S0 - EventCode to marked as required to align with DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Event Code marked as required) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-320 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, S1 - Environment (DT-013) should have min length 3 & max length 10 to be consistent with values. | Implemented |  | Interim Release 2 | 2023-06-23 | 01-Data Catalogue DI-991 Environment Set Min to 3. However, string length is 10, so max length should be set to 10 | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface definition |  |  |  |  | 2023-06-16
MHHS-DIN-321 |  |  | 2023-05-23 | St Clements |  | Sean Cooper | SRO Design | B005 add to IF-036 | Consider adding B005 to IF-036 so that incoming SP knows who previous SP were | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Added B005 to IF-036 so that incoming SP knows who previous SP were | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-322 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B002 - Incoming Supplier MPID - Swagger aligned to DES-138 for min / max lengths | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Incoming supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-323 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B003 - Ougoing Supplier MPID - Swagger aligned to DES-138 for min / max lengths | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Outgoing supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-324 |  |  | 2023-05-24 | EDF | 4780 | Paul Saker | Supplier |  | NHHSP-BPM00C- Transfer of Reads on Change of Data Service details several process steps and messages related to obtaining and sharing register readings between the gaining and losing suppliers to agree a CoS, and to initiating the missing/disputed reads process defined in the Retail Energy Code where CoS reads are missing or need to be disputed/amended. However, it appears that there is no further detail defined within the Design Artefacts regarding how exactly these process steps would work, including amongst other things: • Timing/Operational Choreography – for example it is not clear exactly when losing and gaining suppliers would be expected to attempt to communicate with the meter, or the timescales for sending data obtained between suppliers. • Data to be included in messages – while BPM003C refers to the inclusion of ‘register readings’ in some of the messages it is not clear which registers should be included for smart meters and non-smart meters – for example whether that should just be the registers on a smart meter that the sending supplier uses for billing, or whether that should be all the 48 time of use registers stored on the smart meter. Additional input from Andrew Margan - Within the code workstream, we believe the Operational Choreography document needs to be updated to reflect SLAs. Without this, we can’t complete the Code drafting. If you disagree, we would appreciate an early heads up, so we don’t look disjointed in front of industry. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-325 |  |  | 2023-05-24 | CGI |  | Dave Webster | Software Provider | Status Code Missing from MsgBody | In the SubmitEvents StandardResponseBodyType object (SubmitEvents ¦ 1.2 ¦ MHHSPROGRAMME ¦ SwaggerHub), it states that “statusCode” is a required field. Yet its’ definition does not exist in the properties of the object. StandardResponseBodyType: type: object properties: transactionID: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-014-DIPTransactionID' senderUniqueReference : $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-995-SenderUniqueReference' correlationId: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-011-CorrelationID' sentTimestamp: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-003-DateTime' senderId : # the sender of this message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' recipientID : # indended (logical) recipient of the message, i.e sender of the original event message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' DIPConnectionProviderId : # physical recipient of the message (if different to recipient Id) $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' message: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-005-StatusErrorMessage' help: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-019-HelpText' serviceTicketURL: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-018-URL' required: - transactionId - sentTimestamp - senderId - recipientId - statusCode - message - help - serviceTicketURL | Implemented |  | Interim Release 2 | 2023-06-23 | This has now been updated in V1.2 of Swagger StatusCode Added to the ResponseBody. | Technical corrrection | Supporting Docs |  | JSON/YAML files
MHHS-DIN-326 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Changes required to DES-138 / interface catalogue given changes in Migration Design e.g. the addition of interface IF003 and potentially ISD. | Closed |  |  |  | Duplicate of 247 | No Change |  |  | None
MHHS-DIN-327 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | IF-005 User Guide | The IF005 User Guide explains how the IF005 should be populated. We have a request for clarification on whether the IF006 will be populated identically or if the Meter ID in the IF006 will reflect the Modified Meter Id in the IF005. Is IF-005 identical to IF-006, or is it with updated MTD's. | Implemented |  | Interim Release 2 | 2023-06-23 | IF-006 should be a facsimile of IF-005. In the case of change of MSN... MSN field will reference the (old) MSN and Modified MSN will be populated with new/revised MSN. All subsequent flows following the IF-006 will only reference the NEW/REVISED MSN. We further clarified this in a change to the Note(s) section on IF-006. | Data interface correction | Supporting Docs |  | DES138 |  |  |  |  | 2023-06-16
MHHS-DIN-328 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | The operational choreography does not include an SLA for the RS to send appointment data to the CSS or the timings by which the CSS and DSP should deliver their roles within the process. These need to be added to the operational choreography for clarity, noting the interaction with CR018. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-329 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Approach on a business rule where the ERDS does not send a MEM de appointment / appointment for an MHHS migration where the same MEM is being appointed under MHHS arrangements e.g. they have the same MPID. The expectation is that smart and advanced MEMs will use the M role code for the interaction with CSS so from their perspective there should be no change. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-330 |  |  | 2023-05-25 | Ovo Energy | 5225 | David Morley | Supplier | Long Term Vacant | BSCP504 section 4.15.3 stipulates the criteria via which suppliers can classify sites as Long Term Vacant (LTV). BSCP701 stipulates actions that SDS shall take if the supplier nominates that a site is LTV. However, the criteria that suppliers shall use for classifying LTVs in MHHS is missing. Can you please signpost where the new criteria will be located? | Closed |  | Interim Release 5 | 2023-09-13 | BSCP is responsible for revising the code specification, there are no changes to design specified. Code team will get in touch with the participant.
MHHS-DIN-331 |  |  | 2023-05-25 | MHHS | 4733 | Martin Freeman | Central Body | Secondary Routing | Secondary routing for IF-013 is specified as being conditional upon the value of DI-015. However, DI-015 (Connection Type Indicator) is a property of a repeating block, and there is no constraint in place to suggest that each element in the repeating block must have the same value for this (or any other) property, in which case multiple rules in the routing table could apply simultaneously. The routing table design seems to suggest that only a single rule should apply at a time and that routing should not be derived by blending multiple rules. If this is so, and a message is received where different elements in the B050 have a different Connection Type Indicator then there is no coherent way to implement this in conformance with the routing table. | Implemented |  | Interim Release 2 | 2023-06-23 | Agree there was a routing contradiction for scenarios/periods where a different connection type was in effect. Interface notes section has been updated to direct the use of 'separate' IF-013 messages in such circumstances. Note also makes clear that repeating B050 blocks are acceptable where other elements (not Connection Type) of the CCC vary over the period to be defaulted. | Design Ambiguous | Supporting Docs | Default Consumption | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-332 |  |  | 2023-05-25 | MHHS | 4750 | Martin Freeman | Central Body | IF-013 Routing | In the routing table for IF-013 all rules are conditional upon S0.Eventcode == [ActivePowerDefaulted], which means that for IF-013 message where Eventcode == [ConsumptionOnDeEnergisedMPAN] there is no routing at all, which means when this message is sent to the DIP it will not be routed anywhere and will simply disappear. That's almost certainly an error. | Implemented |  | Interim Release 2 | 2023-06-23 | Event code [ConsumptionReceivedonDeEnMPAN] has been moved from IF-013 to IF-014. The valid event code list and routing rules have now been updated for both interfaces to reflect the move. v1.2 of Swagger also updated to reflect this change Duplicate of DIN 255 | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-333 |  |  | 2023-05-25 | MHHS | 4760 | Martin Freeman | Central Body | Connection Type Required to Support Routing of IF-014 | All of the routing rules specified for IF-014 are conditional upon DI-015 (Connection Type Indicator). But IF-014 does not have any blocks with this property, which means this message won't get routed anywhere. | Implemented |  | Interim Release 2 | 2023-06-23 | Block B067 - Connection Type Added to IF-014 in order to support routing requirements. Swagger v1.2 updated to reflect this change. (Duplicate of DIN256) | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-334 |  |  | 2023-05-25 | MHHS | 4766 | Martin Freeman | Central Body |  | The routing table for IF-018 specifies roles AMSC, UMSC, UMDC for Secondary routing. There are no such roles in either the DES138 nor the E2E001. | Closed |  |  | 2023-06-23 | Secondary Routing Review/Changes have superceded this issue - Ref DIN-268
MHHS-DIN-335 |  |  | 2023-05-26 | British Gas/Engage Consulting | 4640 | Neil Strange/ Haz Elmamoum | Consultancy | Four questions on IF004 | IF/PUB-004 – DIP Common Blocks referencing MHHSP-DES138-Interface Catalogue v5.1.1 As a minimum this needs to be referenced in the supplier requirements MHHSP-BRS004-Supplier Overview and MHHSP-BRS002-Metering Service requirements, but to ensure parties get sight of this we would suggest it needs to be included in a business process map and have associated requirements. For IF-004 to be useful to participants DI-999 – Event Code needs to be elaborated e.g. 1- Installation 2- Removal; 3- Exchange; 4 - Found (Where installed by Gas supplier and Elec Supplier takes ownership) C/M/O rules for DI-192, DI-193 and DI-194 need to be explained in the notes – presumably driven by event code Available is spelled incorrectly (available) for DI-192 and DI-194 there are a couple of angles here – 1) ensuring wider awareness and 2) it seems there is a question mark on the governance here as it is odd a flow has been added but industry does not appear to have been sighted on it especially with no associated referencing in artefacts and no process map, so effectively no one has any idea how it is supposed to be used. Although it was formally agreed not to include and use bilaterally....from a Large Supplier Constituency perspective, my members are keen to ensure design clarity and how flows are to be used or not, regardless of their ad-hoc / bilateral nature. | Implemented |  | Interim Release 2 | 2023-06-23 | Optional flow not formally shown as part of the design. Spelling corrections updates, optionaility guidance also updated in the conditionality rule column on IF004 for DI-192, DI-193 and DI-194. | Data interface correction | Supporting Docs | IF-004 | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-336 |  |  | 2023-05-26 | MHHS |  | Rob Topley/ Zak Hussain | SI Design |  | Process Step No. BP Step ID Process Map wording Interface ID Sender Recipient/Service Traceability Requirement Traceability Method Statement iServer Requirement Name iServer Step name Issues Found BP01 170 BP01 - 170 Send Site Tech Details on Metering Service Request MHHS-RS-LD-012.1 #N/A LDSO170a Send Site Tech Details on Metering Service Request Missing (only on BPD and traceability matrix) BP01 175 BP01 - 175 Receive Site Technical Details D0215 LDSO Metering Services MHHS-RS-MS-037.1 #N/A MET175 Receive Site Technical Details Missing (only on BPD and traceability matrix) BP03B 95 BP03B - 95 Manage SP Appointment Amendment Request Response PUB-035 DIP Supplier MHHS-BR-SU-35.1 #N/A SUP095a - Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP03B 96 BP03B - 96 Manage SP Appointment Amendment Request Response PUB-035 DIP Data Services Metering Services MHHS-BR-DS-11.1 #N/A ESP96 – Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP05 315 BP05 - 315 Issue Reading Data MHHS-IF-041 Data Service DIP MHHS-BR-DS098.2 #N/A DAT315 – Issue Reading Data Missing (only on BPD and traceability matrix) BP05 340 BP05 - 340 Process Reading Data PUB-041 DIP Supplier MHHS-BR-SU047.1 #N/A SUP340 Process Reading Data Missing (only on BPD and traceability matrix) BP05 350 BP05 - 350 Process Reading Data PUB-041 DIP LDSO MHHS-BR-LD009.1 #N/A LDSO350 Process Reading Data Missing (only on BPD and traceability matrix) BP010D 1055 BP010D - 1055 Receive updated Legacy information PUB-026 DIP Central Settlements MHHS-BR-RD-018.1 #N/A ECS1055 Receive updated Legacy information Missing (only on BPD and traceability matrix) All these requirements don’t exist on any requirement catalogues, they’ve only ever been on a BPD document or the traceability matrix (which are essentially the same document). Also, the highlighted traceability has a typo and is on a requirements artefact but is wrong on both the BPD and traceability matrix. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-337 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger alignment to DES-138 | R0 - Response Message Min length updated to align with DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Updated R0 - Response in Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-338 |  |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier |  | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. BP003 to be updated to clearly show IF-036 going to both Import & Export supplier | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-339 |  |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier |  | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. IF-001 to be updated to be additionally sent to the Export supplier rather than just the import | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | See 338 as well | [8 empty] | 2023-07-14
MHHS-DIN-340 |  |  | 2023-05-26 | UKPN | 4547 | Neal Medley | Network Operator |  | The reports ELEX-REP-02/02A will only contain aggregated data for A(General LLF Class Import and C (General LLF Class Export). The I/F021 can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/014 Rejected Consumption Data Submission and I/F MDS Defaults Applied to any I/F021 data to ensure you are not using rejected data or are missing I/F 021 data in respect of an MPAN. MDS Method Statement to be updated to reflect | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-341 |  |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | MUM Event not required by MDS | For IF-018 the event [MUMIndicator] is routed to MDS and indicates metered/unmetered. This event is not required by MDS as they can infer this from the Market Segment (Advanced, Smart and Unmetered). DIN raised to remove the routing | Implemented |  | Interim Release 2 | 2023-06-23 | MDS Removed as Always Recipiant for Event [MUMIndicator] on IF-018 Routing rules | Data interface correction | Supporting Docs | IF-018 | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-342 |  |  | 2023-05-26 | UKPN | 5194 | Neal Medley | Network Operator |  | The intent is that the daily volume on actuals or estimates are the sum of the appropriate consumption data. So when added together they should equal the summed Total of the Settlement Period data (Total Uncorrected Volume) barring any rounding errors. The data is given in MWh to six decimal places (i.e. to the nearest Watt hour). I assume DUoS billing only calculates to the nearest unit so would not expect any rounding errors to impact. The A flags are set out in the ELEX-REP-02/02A are the same as those set out in the CCC table in the VAS Method Statement which is also in the MDS Method Statement. I agree the list in the calculations only are missing the full list of SPQI that are deemed to be actuals as set out in the ELEX-REP-02/02A. DIN raised to correct the calculation | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-343 |  |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | Routing rules table | The routing rules on the IF-037 sheet state that MDS will 'always' receive the DSDeApp event code, however the 'Always' column on the IF_LIST does not state Central Settlements for MHHSP-IF-037. IF list needs updating to reflect that the DSDeApp event always routes to MDS | Implemented |  | Interim Release 2 | 2023-06-23 | Decision taken to remove Recipiants (COLs G,H &I) from the IF_list - as just duplication of information contained within each of the IF spreadsheets. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-344 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B005 Custom Block update Swagger to align with DES-138. Current Metering Service MPID Length removed. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138. Current Metering Service MPID Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-345 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B024 Custom Block update Swagger to align with DES-138. DUOS Min Length removed. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138. DUOS Min Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-346 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design |  | IF-001 - B032 Custom Block update DES-138 to align with Swagger. Update DI-122 (Profile Class) to Integer from String-2. | Closed |  |  | 2023-06-23 | DI-122 remains as String 2 for Profile Class to support requirements for enumerations. | Data interface correction | Supporting Docs |  | None |  |  |  |  | 2023-06-16
MHHS-DIN-347 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B035 Custom Block - update Swagger to align with DES-138. Remove min length. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-348 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | IF002 correction | IF-002 - B074 Custom Block. Clarification on DI-091. DES-138 says this is 1 digit to the left of the decimal point. Swagger says 5 to 6. DES-138 to be updated to the correct value. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to be an Integer (1), Min of 1, Max of 1, example of 5. This now aligns with DES-138. | Data interface correction |  |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-349 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Correlation ID Issue IF-006 | Routing Rules in DES-138 do not always correctly identity where Correlation ID == Copy ie, it's missing for IF-005 / IF-006 so this needs to be updated correctly across all interfaces. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated IF-006/IF-008/IF-039/If-028/IF-026/IF-016 routing rules to show use of a "Copy" in Correlation ID (ie copied from the preceeding IF txn pairing) | Missing/incorrect validation rule | Supporting Docs |  | DES138 |  |  |  |  | 2023-06-16
MHHS-DIN-350 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-005 B033 to align Swagger with DES-138 (Postcode removal, mandatory modified meter id) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Postcode removal, mandatory modified meter id) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-351 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B071 to align Swagger with DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-353 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B032 to align Swagger with DES-138 (SSC Min Length should be 4) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated SSC Min Length to be 4) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-354 |  |  | 2023-05-30 | SJW |  | Sarah Jones | Consultancy | Design team confirmation for sending of IF-037 and not IF-037 to losing MEM | Please see below details of a new design query related to the Registration Tranche of Code Drafting. We note that in BP011C there is a process whereby the Registration Service will auto de-appoint / appoint agents for secondary related metering points and linked export metering points as part of their validation. The business process only includes the sending of the IF037 to the Losing MEM and not the IF035. Please could you confirm that this is correct and that in this instance the Losing MEM would not receive an IF-035. If this is the case, we think there should be a change to Metering Service requirements MS-018 and 019 to clarify that where the Losing Metering Service receives an IF-037 with no preceding IF-035 then they should send the MTDs at this point. The alternative would be to include the sending of an IF-035 as well as an IF-037 accepting that these would arrive at a similar time. This would align to the process for managing retrospective MEM appointments where we understand that the Losing MEM would receive both the IF-035 and the IF-037. We also suggest amending MS-008, 008.1, 009 and 009.1 to recognise this nuance as follows: MSA/MSS must obtain Export MPAN de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. MSA/MSS should note this message will be automatically triggered when a change of Metering Service has successfully completed for the linked import MPAN or a new MPAN linkage has been put in place where the [linked import / primary related] MPAN has a different appointed Metering Service. Presumably there is a similar impact on the data service requirements that would need to be considered. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 |  |  | Supporting Docs | [6 empty] | 2023-07-14
MHHS-DIN-355 |  |  | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Number of Register Digits | Revisit and confirm IF-005 Cumulative Digits validation rule against latest version of the CP | Implemented |  | Interim Release 2 | 2023-06-23 | All instances of DI-091 (IF-002,IF005,IF-006,IF-033,IF-036) updated to reflect updated logic. IF-005 validation rules updated also to reflect new guidance. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-356 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B073 - update Swagger to align with DES-138 (consumptionAmendmentSupplierReference max length) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated consumptionAmendmentSupplierReference max length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-357 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B902 - update Swagger to align with DES-138 (supplierConsumptionAmendmentRequests typo update) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated supplierConsumptionAmendmentRequests - remove typo) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-358 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-034 B070 - update Swagger to align with DES-138 (contractReferenceMeteringService max length 10) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated contractReferenceMeteringService max length 10) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-359 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: The method statement states that “The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN on notification of the set-up of that MPAN in MHHS-IF-001.” However, it will be the MHHS-IF-036 Registration Service Notification of Service Appointment & Supporting Info that will initially provide the fact that an MPAN has migrated to Central Settlements. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-360 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: 3.3 Where a years’ worth of data, >=75% and <100% of actual UTC Period Consumption data (where Settlement Period Quality Indicator = A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6) has been used to calculate the Annual Consumption, the Annual Consumption Quality Indicator should be set to “1”. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-361 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design |  | We need to raise a DIN on the AC method Statement and AC requirements: Likewise 3.6 needs to say greater than or equal to 182 days: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-362 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design |  | Section 5 incorrectly named Section 6 needs to be removed: 6. Transition and Next steps | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-363 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design |  | We may also need to document how the is calculated by the Load Shaping Service in the first year. I believe Helix have developed a calculation and this would need to go in the Load Shaping Method Statement and be referenced in the AC Method Statement. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09 | [9 empty] | 2023-07-14
MHHS-DIN-364 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-035 - B066 - mark as mandatory in Swagger as per DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated so B066 is a mandatory for IF-035 custom block) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-365 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-004 - B093 - update Swagger to align with DES-138 (min Length on commsHubGUID / GPF-GAS-GUID) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated min Length on commsHubGUID / GPF-GAS-GUID) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-366 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 custom block - SSC add min length to align with Swagger | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B032 custom block - SSC add min length to align with Swagger) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-367 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 Profile Class - updated Swagger to be a String to align with DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B032 Profile Class Swagger to be a String to align with DES-138) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-368 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-013 - B049 updated Swagger to align with DES-138 (run Number optional) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B049 Swagger to align with DES-138 (run Number now optional) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-369 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | Switch Cancellation Info Note | Update BP002/003 to add informational note that Registration Cancelations will be processed as soon as they are received by SCS from CSS i.e. Apps Lapsed through switch cancelation sent immediatly not held until Proposed App Date. Also updates to Forward Migration BP002/003 for consistency. Changes to OPC added the following words to OPC_190 in the Activity column (section 4.4) “(including Switch Status Updates e.g. Cancelled)” | Implemented |  | Interim Release 2 | 2023-06-23 | BP-002/003 updated to include new informational Note in Supplier swimlane relating to CSS Switch Cancellations. OPC updated to make it clearer that Secured Active Processing includes Switch Status Update processing. to OPC_190 in the Activity column (section 4.4) “(including Switch Status Updates e.g. Cancelled)” | Process Model correction | MPAN Ownership |  | BP002, BP003, OPC001 Forward Migration BP002 & BP003 |  |  |  |  | 2023-06-16
MHHS-DIN-370 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | IF-005 Update Window Guidance for Prev MS | Change IF-005 and Guidance Doc to allow Meter Updates within 10 day window for previous MS | Implemented |  | Interim Release 2 | 2023-06-23 | New validation rule added to IF-005/MeterUpdate to allow previous MS to submit if within 10 day post appointment period. IF-005 User Guide section 9.3 updated to reflect same. | Missing/incorrect validation rule | Supporting Docs |  | DES138, IF-005 User Guide |  |  |  |  | 2023-06-16
MHHS-DIN-371 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team |  | Review design to ensure only Supression of IHD info for advanced segment and NOT "deactivation" of underlying IHD record. | Closed |  |  | 2023-06-23 | Confirmed that IHD details will be retained on Smart to Trad Exchange. Any IHD info present will be suppressed (ie not included in msg) if Segement is Advanced. No change required to documentation. Possible data cleanse issue - Dan T. to raise in Data Forum.
MHHS-DIN-372 |  |  | 2023-06-01 | MHHS | 5298 | Rob Golding | Central Body | Mapping Roles | There is a need to master the mapping of Market Participant Role to DIP Role within the MHHS solution. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | This would seem to best fit within ISD. Specifically Entity #21. Proposed solution is to add DIP Role ID into ISD Entity #21 We would also add validation into Entity M16 to ensure it always references the valid mappings in #21 when a new MPID to DIPID mapping is created | [8 empty] | 2023-07-14
MHHS-DIN-373 |  |  | 2023-06-02 | MHHS | 5272 | Rob Golding | Central Body |  | There is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 | Closed |  |  | 2023-07-12 | Duplicate of DIN-297
MHHS-DIN-374 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Message Replay & Requeue functionality | Message replay and requeue functionality needs to be added to the DIP API interfaces, which requires changes to the Swagger / YAML definitions. Detail is required in the E2E design documentation to explain how the message replay and requeue functionality will work. | Implemented |  | Interim Release 2 | 2023-06-23 | Updates to the E2E001 design document to provide detail on how the replay and requeue will work. There are updates to Swagger to support new interfaces for /dip-channel/{id}/replay and requeue respectively. There is also a new MessageRequest Schema that is used to pass data into both of these interfaces. To support these changes, section 4.8 has been updated in the E2E001. | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents |  |  |  |  | 2023-06-16
MHHS-DIN-375 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Interface webhook configuration | Updates require to the pubconfig and webhook config to support per interface webhook configuration, alongside changes to support definition of recipient ID and role ID. | Implemented |  | Interim Release 2 | 2023-06-23 | Updates to the E2E001 design document to provide detail on how the webhook configuration will work, with information related to specific interface changes. There are updates to Swagger to support new interfaces for /dip-channel/{id}/pubconfig (POST and DELETE) respectively to support changes defined in the E2E001 (Section 4.5 and 4.5.1 and 4.5.2have been updated to provide more clarity / information). | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents |  |  |  |  | 2023-06-16
MHHS-DIN-352 |  |  | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Obsfucation Text | What text should be used for data obfuscation ? for things like Boolean fields (True/false) | Closed |  |  |  | Closed as this is already included in section 4.3.2 of the E2E001 design document. | [8 empty] | 2023-07-14
MHHS-DIN-376 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-099 changes required to ensure DES-138 displays the correct YAML name / Swagger aligns to this. | Implemented |  | Interim Release 2 | 2023-06-23 | "Register" spelling in name has been corrected in DI099, and DI-099 name correction for IF041 in DES138 | Data interface correction | Supporting Docs |  | DES138 |  |  |  |  | 2023-06-16
MHHS-DIN-377 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-097 | DI-097 - In DES-138, this is defined as a string (2), but the existing data type is an Integer and this is an Integer enumeration. Need to update this to an Integer in both DES-138 and Swagger 1.2. | Closed |  |  | 2023-06-23 | Rejected / closed as enumeration of values requires string (2) therefore this is retained to support buisness requirements. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-378 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. | Implemented |  | Interim Release 2 | 2023-06-23 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. This information has now been added to DES-138 5.2.1. | Data interface correction | Supporting Docs |  | DES138 |  |  |  |  | 2023-06-16
MHHS-DIN-379 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-048 | DI-048 - clarity required on whether this is "meter manufacture make and type", rather than just "meter manufacturer". The first is an existing data type and links to the J number, so providing further clarity / rename would quickly ensure alignment in DES-138 and then subsequently in Swagger. | Closed |  |  | 2023-06-23 | Rejected / closed as this was discussed as part of previous work off items and description has previously been approved / accepted as Meter Manufacturer. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-380 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-052 | DI-052 in DES-138 currently has 4 enum values ie, - Active Import, Active Export, Reactive Import, Reactive Export. In MDD there are currently 38 options documented. Discussion around whether ISD Entity 47 should be referenced as the list of values allowed. This can then be aligned / referenced in other other documents ie, EMAR will reference ISD Entity 47. | Closed |  |  | 2023-06-23 | Rejected / closed as this was discussed as part of previous work off items. Only 4 values are required in MHHS / DIP, therefore only these values are referenced / used as part of the enumeration to avoid bringing data from existing systems into new systems when this is not required. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-381 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-842 | DI-842 - Confirmation that MDR's have DIP ID's? There has been discussion in various forums to understand whether they do and if not, then this data item needs to be removed in DES-138 and Swagger. | Closed |  |  | 2023-06-23 | Rejected / closed as MDR's do have DIP ID's, therefore this value will be retained. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-382 |  |  | 2023-05-06 | Design Team | 4570 | Neil Strange | Supplier | D0010 | In BP003C, at CoS traditional CoRs are transferred between suppliers via D0010. We believe this needs to be used for all meter types - as this will be needed for non-communicating smart and advanced meters – and BP003C needs to be amended accordingly. There is no mention of IF-041 and we do not believe that the DIP is expecting an IF/PUB-041 transaction between suppliers. | Implemented |  | Interim Release 2 | 2023-06-23 | Supplier added as a Primary Recipient in the Routing Rules for IF-041 (DES138) - Supplier initiated Reads. Sending supplier would need to populate the DIP ID of Supplier(s) with whom he wished to share the reading. Working Group specifically decided not to discuss /include COR scenarios for Smart Metered Sites however this is not prevented by the Design - a note to this effect has been added to BP003C for clarity. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue BP-003C Transfer of Readings
MHHS-DIN-383 |  |  | 2023-06-07 | RECCO | 4558 | Sarah Jones | Central Body | Change of Segment Scenario | We cannot find anything in the design artefacts stating that the Metering Service is required to notify metering exchanges for change of segment within 2 WDs. We have found the following: MS-094: MSA/MSS must be able to publish Change of Segment Meter Exchange details and reads via the appropriate interfaces, where it is not formally appointed as the Metering Service but does have an accepted prospective appointment (Appointment Scenario = "SEG"). The MSA/MSS must issue the work update to Registration at the earliest opportunity but within [x] days of completion at the latest. OPC 240: Notification of works to be completed by D+3 Working Days (This should provide time for consumption to be provided using new MTDs ahead of the SF run.) The BP011 references the connection type update being provided by LDSOs within 2 WDs. There is no equivalent for metering updates. Will require DRG confirmation on if the 'x' should be 2 or 3 working days | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Updates to be made inline with DRG recommendation to reflect 3 working days | Process Model correction | Supporting Docs | Business Process Documentation | BP011 |  |  |  |  | 2023-07-14
MHHS-DIN-384 |  | DI-174 | 2023-06-07 | St Clements | 4938 | Madison Layton | Software Provider | IF-038 and IF-039 blocks not the same | Block B020, B021 are not the same across interface IF-038 and IF-039. DI-140 and DI-138 (SP DIP ID) are in IF-039 but not in IF-038. Understanding was that with the DIP change that all data items in block are mandatory, the blocks were to be consistently defined across all interfaces. If extra DIP ID DI-138 and DI-140 data items are included in IF-038 then we need a new REG rejection code to allow us to reject where DIP ID is not the same as the sender DIP ID. Alternative is to separate the DI-140/DI-138 into their own blocks included on the IF-039 interface only. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Block data items aligned. New validation rule add to ensure that Sender ID matches MS/DS CDC ID. New Error code REG1076 added to support validation rule. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-385 |  |  | 2023-06-07 | Design Team |  | Steve Weston | SI Design | Correlation ID | S1 Common Block - Correlation ID is mandatory in Swagger, but Optional in DES-138. Swagger should be updated to align. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated S1 Common Block, Sender Correlation ID in Swagger, as this is Optional in DES-138 to support business process and requirements. | Technical corrrection | Supporting Docs |  | JSON/YAML documents |  |  |  |  | 2023-06-16
MHHS-DIN-386 |  | DI-179 | 2023-06-07 | St Clements | 5258 | Madison Layton | Software Provider | Register Digits | REC Change R0102 has been approved by industry to amend the number of display digits validation Where the Meter Type is S1 the Number of Displayed Register Digits value must be either 6 or 5 Where the Meter Type is S2A, S2AD, S2ADE, 2ADF, 2ADEF, 2AEF, 2AF, S2B, S2BD, S2BDE, 2BF,2BDF, 2BDEF or 2BEF the value must be “5”. Where the Meter Type is prefixed with “S2C” the value must be “6”. Where the Meter Type is 2CDEF, 2CF, 2CDF or 2CEF the value must be “6” REG1097 validation on the IF-005 needs correcting with this change, and the population notes for data item DI-091 across multiple interfaces also needs correcting | Closed |  |  | 2023-06-23 | Duplicate of Register Digit DIN-355 listed above | Data interface correction | Supporting Docs | Interface Catalogue | Lis
MHHS-DIN-387 |  | DI-180 | 2023-06-09 | St Clements | 5269 | Madison Layton | Software Provider | Uplift metered indicator requirements | There are elements in the requirements that suggest that metered indicator would trigger a change to Market Segment. E.g. MHHSP-BP011-Change of ConType andor Mkt Segment-v5.1 Step 102 MHHSP-BPD011 - Change of Con Type or Market Segment v5.0 Step 102 Which states if there is a change to market segment RS would need to re-evaluate the market segment And MHHS-BR-RS-124 which include in brackets: Change of Connection Type (Change of Unmetered Indicator) MPRS will assess Market Segment against the ISD entity M7 which does not include Metered Indicator. Therefore a change in Metered Indicator in isolation of any other changes to data items in the M7 table/Related MPANs/Linked MPANs, will not trigger a change to Market Segment. As it will not trigger a change MPRS will not re-evaluate Market Segment base on a Metered Indicator change alone. The requirements need uplifting to reflect. | Closed |  |  |  | Closed as discussed and agreed with SCS. | No Change
MHHS-DIN-388 |  |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | IF-036 Custom Routing Rules | Following discussions with SCS agreed that for reasons of complexity it would be better to adopt Primary rather than secondary routing to IF-036. New Requirement created for REGS to undertake the Primary Routing of IF-036. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | To engage with SCS
MHHS-DIN-389 |  |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | Appointment Start Times | Do we need a formal validation Rule to check that Appointment Start times are referenced as Midnight Local ? Issue raised numerous times with SCS. Waiting for SCS to confirm their position. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | To engage with SCS
MHHS-DIN-390 |  |  | 2023-06-13 | Siemens | 5534 | Tony Mason | Metering Service Provider | IF/PUB-018 | There appears an inconsistency in the Business Process Map, BP010, and the routing rules for the IF-018 where the Event Code = DUOSTariffIDChg. This information is confirmed to SPs on the IF/PUB-036 and would then be updated where there is a change on the 018 according to the Secondary Routing Rules. This notification is absent on the process diagram. Could you confirm the position and update the documentation accordingly? | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Update BP010B to show Data Service and Metering Service receiving IF-018 for DUoS Tariff ID updates in line with the routing rules in DES-138. | Process Model correction | Meter to Bank | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-391 |  | DI-182 | 2023-06-13 | St Clements | 5304 | Madison Layton | Software Provider | IF-019 validation gap on principal and subsidiary MPAN | IF-019 is missing validation rules to ensure an MPAN is only listed once in the IF-019, need rules to ensure the sender cannot repeat same Subsidiary MPAN twice in the repeating B090 block, and cannot list the same MPAN as both Principal and Subsidiary in the same IF-019 message | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Created x2 new rules to prevent duplicate MPANS within repeating B90 groups within a single message. Error Code REG1079 created to support validation checks | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-392 |  |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Consent Fields | Raised by SCS. B068/DI-017/DI-018 - This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block B068 updated to be "must be provided" for smart meters. Data items set to mandatory non-nullable. | Implemented |  | Interim Release 2 |  | Block text updated to show mandatory if smart meter present, and DI-017/D-018 updated to be mandatory non-nullable (applies to IF-026 only) | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-393 |  | DI-181 | 2023-06-13 | St Clements | 5274 | Madison Layton | Software Provider | De-appointment and re-appointment date order | MHHS-BR-RS-128.4 & MHHS-BR-RS-128.5 covers the requirement for MPRS to ensure MS/DS are aligned across Related/Linked MPANS, and where they are not to de-appoint the MS/DS and appoint the correct MS/DS. The de-appointment requirement specifies to set MS/DS ETD to D+1 and the appointment to set the MS/DS EFD to D+2. Why do we need to apply the de-appointment and re-appointment in the future? Would we not be better to use the previous day (D-1) for the de-appointment MS/DS ETD and the current day (D) for the appointment EFD? | Closed |  |  |  | Can Close and SCS have agreed with the Requirement. Needs to be this was as work may have been arranged for the last day | No Change
MHHS-DIN-394 |  |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Annual Consumption Fields | Raised by SCS. B059/B027/DI-0148 This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block updated to be "must be provided" if available, however data items now need to be set to mandatory non-nullable. | Implemented |  | Interim Release 2 |  | DI-0148 updated to be mandatory no-nulls and data type updated to DT-016 in Data Catalogue. Data Type corrected to DT-016 in IF-002 and IF-036. | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-395 |  |  | 2023-06-13 | St Clements | 5510 | Vicki Holland | Software Provider | Obfuscation of Connection Type Indicator in IF-021 | The DES138 interface catalogue specifies that the data item Connection Type Indicator will be obfuscated for all parties as it is required for routing only. Can this please be changed so that it is visible? The reason for this request is that suppliers often process data differently for the different connection types and therefore its important that they can internally validate or route data according to the connection type of the MPAN. | Ready for Internal Review |  | Interim Release 3 |  | Obfuscation of connection type removed from IF-021/IF-013 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-396 |  | DI-183 | 2023-06-13 | St Clements | 5305 | Madison Layton | Software Provider | Update IF-019 REG1001 to only apply to Create and Add event codes | IF-019 REG1001 rule applies to all event codes. The MPAN could be disconnected with linkages still in place. If REG1001 is applied on remove event codes, then there will be not means by which the Supplier/DNO can remove the linkage after a disconnection. Suggest REG1001 rule should only apply to the Create and Add event codes. This would be consistent with the existing validation on the DB05 and D0386. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | IF-019 MPAN Status Validation Rule removed for all "Remove MPAN" Event Codes. i.e. I can still perform remove MPAN from group task if MPAN is disconnected. SCS rejected option of auto de-linkage as part of De-Registration Process. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-397 |  | DI-184 | 2023-06-13 | St Clements | 5306 | Madison Layton | Software Provider | IF-019: REG0007 to only apply to Related event codes and not to Linked Import Export event codes | REG0007 on IF-019 interface is currently written to apply to both Related and Linked MPANs. The intention of this existing rule on D0386 is because Related MPANs switch together, and so changing the relationship during a switch can create a split supply relationship. However Linked MPANs do not switch together and so this is not currently applied to the existing DB05 validation rules. Suggest REG0007 only apply to Related event codes and not to Linked Import Export event codes? | Closed |  |  |  | Following discussions with SCS it has been agreed to prevent all changes to MPAN Linkages whilst an Active Switch is in progress. This is the safest approach when considering both CSS and Auto Alighment functionality considerations. No change to existing Design Documentation required.
MHHS-DIN-398 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD Stores LLF data | Can we have an ISD entity ID for LLF data. This would be required for the API used to retrive the data from ISD data store. Are you happy for us to create and put it in the Guidance note. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-399 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD publishes full data to Elexon Central Systems | Requirement should be reworded to be "ISD must make available the data sets required by LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-400 |  |  | 2023-06-14 | SRO Design Team | N/A | Sean Cooper | SEO Design | REGS Validation Rule Clarification | REG1089 conditions updated to provide more clarity. Existing wording refered only to a Subsequent App - this is now better defined as an Appointment with a prior/earlier Sender Timestamp. No functional change. | Implemented |  | Interim Release 2 |  | For IF-031 Validation rule text updated to specifically reference Sender TimeStamps so as to provide more clarity on the nature of the val rule/when generated | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-401 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | IHD/SMSO Fields | IHD Install Status and IHD Status Effective from Date fields should be optional (ie nullable) when providing an IHD update in IF-025/IF-026. SMSO and SMSO Effective from Date fields should be optional (ie nullable) when providing an SMSO update in IF-025/IF-026. | Implemented |  | Interim Release 2 |  | DI-137/ DI-136 in block B030 updated to Optional (O) in IF-025 and IF-026 DI-134/ DI-135 in block B031 updated to Optional (O) in IF-025 and IF-026 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-402 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Import/Export Fields | Linked Import/Export MPAN and Linked MPAN Energy Direction will always be provided so should not be nullable | Implemented |  | Interim Release 2 |  | DI-038 updated to Mandatory No nulls and Data Type updated to DT-002 DI-151 updated to Mandatory No nulls On the 01-Data Catalogue | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-403 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Meter Manufacturer Field | Meter Manufacturer is optional (ie nullable) when provided in IF-002, IF-006, IF-033, IF-036 as in IF-005 | Implemented |  | Interim Release 2 |  | DI-048 updated to Optional (O) in IF-002, IF-006, IF-033, IF-036 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-404 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Proposed Appointment Response Code Field | For Response code A there may not be any text to populate for DI-143 | Implemented |  | Interim Release 2 |  | DI-143 updated to conditional (C) based on DI-979 = L or R in block B007 in IF-034 and IF-035 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-405 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Response Message Field | For Response code A no text to populate for DI-980 | Implemented |  | Interim Release 2 |  | DI-980 updated to conditional (C) based on DI-979 = R in block R0 in 02-DIP Common Block tab | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-406 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Sender DIP ID Field | Sender DIP ID should always be provided in S1 Common Block | Implemented |  | Interim Release 2 |  | DI-997 updated to mandatory (M) in block S1 in 02- DIP - Common Block tab | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-407 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | COS During SEG Issue | Discuss with SCS the option of allowing non-appointed MS to update MTDs even if App has lapsed due to COS activity. If not then need to update process map to call out need for manual exchange of MTDs as Work MS could never submit if IF005 | Closed |  |  |  | Closed, SCS unable to support alternative solution. Design Team have reviewed the existing process map note and believe this already provides enough information for participants. | No Change
MHHS-DIN-408 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD is the master for data contained both within ISD and MDD during Transition | The requirement is a bit ambiguous as could be read as all ISD and all MDD rather than just ISD data + overlapping MDD data. We don't want to be the master for MDD only data | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-409 |  |  | 2023-06-14 | St Clements | 5510 | Vicki Holland | Software Provider | ISD Entity M5 – Consumption Component Classes | EDI012 ISD entities document shows that the settlement period quality indicator in entity M5 is a comma separated list of possible values. This will be difficult to use in systems that need to refer to this data. Could this instead show Actual or Estimate? Alternatively could this be split into parent and child entities to avoid a comma separated list? | Open - awaiting assessment |  | Interim Release 4 | 2023-08-09
MHHS-DIN-410 |  | DI-487 | 2023-06-14 | St Clements | 5542 | Virginia Patey | Software Provider | DI-487 definition incorrect for REP-002 on Swagger | DI-487 energised MPANs is defined as an Integer in the Interface Specification, yet is defined as a String in Swagger. | Implemented |  | Interim Release 2 |  | DI-487 updated in Swagger 1.2 to align with Interface specification for REP-002 | Data interface correction | Supporting Docs |  | Swagger 1.2
MHHS-DIN-411 |  | Migration | 2023-06-14 | ESG | 4810 | Patricia Parker | Software Provider | Migration Segment Categorisation | The Migration Design currently specifies that Market Segment needs to be recorded before the Migration phase. This should be changed so that it is no longer required. Until an MPAN is migrated, there is no way of maintaining the market segment between the RS and EES using the legacy interface between these two services. However, meter type and connection type will be available in both the EES and the RS, so Suppliers can use a combination of these values to derive the correct market segment. | Closed |  |  |  | SRO Team disgree with this Migration Request. Market Segment must be known prior to the selection of MHHS Service Providers. Market Segment is a derived field based on Connection Type and Meter Type. Connection Type must be set before Migration / Meter Type already known so Market Segement CAN be derived, set and maintained prior to MPAN migration. No change to baseline documentation Required .
MHHS-DIN-412 |  |  | 2023-06-14 | MHHS | 5022 | John Wiggins | Central Body | Update to MDD | Migration request to ensure that Elexon add MHHS as a value to MDD. | Industry CP Required |  | Interim Release 4 | 2023-08-09 | Agreed at meeting on 27/06/23 - MMcK will draft and raise a CP to cover these changes.
MHHS-DIN-413 |  | Migration | 2023-06-14 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | Reading Type (J0171) will be updated with three new values: Forward Migration CoA Forward Migration CoS Reverse Migration CoS Reading Type (J0171) will no longer use Initial or Final for migration reads between Suppliers or DC/DS but one of the above new codes will be used. Meter Reading Reason Code (J0332) will no longer be used to identify migration reads, all reference to this will be amended to Reading Type (J0171) in the guidance document. | Industry CP Required |  | Interim Release 5 | 2023-09-13 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-414 |  |  | 2023-06-14 | British Gas |  | Mohammad Amin Fuggawala | Supplier | D0275 in D-Flow Document | Ref Previous DIN-244. In the "DES196 D-Flow Document" the D0275 is showing as redundent. This is misleading it should be marked as by agreement between contracting Supplier-DS. Document should be updated to reflect this. | Open - awaiting assessment |  | Interim Release 5 | 2023-09-13 | Update to DES196 required
MHHS-DIN-415 | RT |  | 2023-06-14 | Elexon | 5702 | Mike Ceney | Central Body | Routing IF-026 to LSS | IF_026- For Routing Rules it states for Event Code/Conditions [SSC], [ProfileClass] and [SSCandProfileClass] that this should be routed to MDS, is this incorrect as MDS does not use these items in any calculations or outputs, this should state LSS | Implemented |  | Interim Release 2 |  | IF-026 [SSC] and [ProfileClass] have been removed as of Interim Release 1. Update DES138 IF-026 to route to LSS on event [SSCandProfileClassChange] | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-416 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-001 New App Scenario Code MCS | Create new Appointment Scenario Code of MCS | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New valued added to DI-800 Swagger 1.3 updated to reflect new value | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-417 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-002 Validation Rules for Scenario MCS | New Val rule to check MCS is only used for legacy non-migrated MPAN where Supplier is not current supplier (and not in past) | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-418 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-003 New App Scenario Code MCA | Create new Appointment Scenario Code of MCA | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New valued added to DI-800 Swagger 1.3 updated to reflect new value | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-419 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-004 Validation Rules for Scenario MCA | New Val rule to check MCA is only used for legacy non-migrated MPAN where Supplier is current supplier and now active Switch is in progress (and not in past) | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-420 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-005 - IF-31 Check valid MHHS Supplier | If MCS/MCA code used is Supplier a valid MHHS Approved/Registered Supplier | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-421 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-006 - Prevent use of Migration Scenario IDs | IF MCS/MCA code used for already migrated mpan - reject appointment for invalid Scenario code(s) | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-422 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-007 Connection Type/Segment not yet Populated | New error required if Connection Type, DUos Tariff ID or Segment is not set prior to migration. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Validation Rule created for IF-031 to check that MHHS Standing Data is present and aligned. REG0011 Error created to support this validation Rule. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-423 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-008 Auto Realign Functionality | New REGS Requirment - Only action the auto-realign functionality on MPANs where both Linked MPANs are in a Migrated state. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Req RS-146 added to REGS Requirements Document to ensure that Auto-Align functionality is only executed if all MPANs in a related and/or linked group have sucessfully migrated to MHHS Operation. | Requirement correction | Meter to Bank | Requirements Documents | BRS-003-Registration Service Requirements
MHHS-DIN-424 |  | DI-185 | 2023-06-16 | St Clements | 5335 | Madison Layton | Software Provider | MPRS access to correlation ID | IF-019 is sent to the LDSO for LinkedImportExport event codes, if the LDSO approves the request they will submit an existing DB05 flow into MPRS. If the DB05 is accepted by MPRS, it will send an IF-020 to the Supplier to confirm the change to Linked Import Export association. However MPRS would not have access to the correlation ID that was received by the LDSO on the IF-019, and so would use a new correlation ID on the IF-020. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Note explaining that it will not be possible to Link IF-019/IF020 messages together using Correlation ID , in the case of Linked MPANs. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-425 | SC | Migration | 2023-06-19 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | 8.1.3 step 12 Migration Design Document : Validation Status (J0022) references will be updated to Meter Reading Flag (J0045) | Industry CP Required |  | Interim Release 5 | 2023-09-13 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-426 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-009 New Rejection Code for D0205/D0203 | Response to a D205 is a D0203. 1. A New Rejection Condition/Code is required where D0205 is received following processing of IF-031. 2. Proposed new D0203rejection code is 62 "MHHS Fwd Migration in Progress or Completed" | Industry CP Required |  | Interim Release 5 | 2023-09-13 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-427 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-010 ISD Change M16 | No change Required - SCS can use ISD M16 - which contains MIPD/DIP Role and Effctive From date. This can be used to determine if a Supplier is MHHS qualified. This is better apporach that adding a transiant "Qualified Yes/No" field to this table. Therefore NO changes to documentation required. | Closed
MHHS-DIN-428 |  |  | 2023-06-19 | British Gas | 5835 | Neil Strange | Supplier | MEX before SSD scenario | When a CoS is in progress and there is a MEX before SSD, how will new supplier get the MEX details As the incoming supplier has already received the IF36 - would there be a new IF36 or would it be a PUB006? In addition how would the new MS and DS be made aware of this? - the old MS has X days after the job is completed to update the industry and a CoS could have happened before the old MS can update the other participants. | Closed |  |  |  | BAU Design deals with 'regular' MEX before COS type scenarios (note previous MS Update Period - PUB-006 would be issued to impacted parties). Complexity arises where there is a COS overlapiing with Change of Segment/Connection Type (ie SEG Appointment)... Following discussion with SCS - low probably, low occurance vs. complex change. Ref existing guidance on BP016 there would need to be a manual interaction between Supplier and MS. No Change to existing Documentation Required.
MHHS-DIN-429 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-011 Changes to D0170 | 1. Change D0170 flow so that MPRS/Registration Service is valid Sender of this flow. 2. New value for "Request Action Code" is needed to denote a Migrating account and if its CoS or ChgOfSP method. | Industry CP Required |  | Interim Release 5 | 2023-09-13 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-430 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-12 New Val Rule for IF-019 | Reject any changes to Related MPANs where any MPAN referenced (or in realted group) is subject to an active Migration SP Appointment Process | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Validation Rules and Error Code created to prevent changes if MCA Appointment Type Exists (Note: prevention if MCS exists is realised through existing check on if Switch is in Progress) | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-431 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-13 Change to D0386 | Change D0386 validation to reject changes to related MPANs if any related MPAN in group is subject to active Migration SP Appointment Process | Industry CP Required |  | Interim Release 5 | 2023-09-13 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-432 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-014 Appointment on Secondary Related MPAN | Extend existing 1039 check to include MCS.MCA Appointment Scenarios. | Closed |  |  |  | Existing Validation Rule(s) around REG1039 will already cover Migrating MPANs - No Documentation Change Required.
MHHS-DIN-433 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-015 Switch in Progress Mig Rejection | New IF-031 validation to reject MCA/MCS DS and MS Appointments if an [any] active Switch is in progress with NEW Rejection Reason Code (note 1095 code referenced in Migration document has already been used elsewhere) | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New validation rules and REG9XXX Exception codes added to ensure correct usage of MCA/MCS Appointment Scenario Codes. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-434 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-016 New IF-003 | Previously DIN-247, Introduce IF-003, no changes from original proposal. 1. Update DES138 new tab, update IF List. Update New Data Items 2. Review E2E doc. 3. Update secondary Routing Rules (Avenade Techncal Doc) to include 4. Update Swagger | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Add IF-003 to DES138-Interface Cat. Created new Data items: DI-500 MHHS Regime End Date, DI-501 Rev Migration Incoming MOP MPID, DI-502, Rev Migration Incoming MOP Eff From Date, DI-503, Rev Migration Incoming DC MPID DI-504 Rev Migration Incoming DC Eff From Date. Swagger v1.3 updated to reflect new IF-003, Blocks (B096/B095/B094) & Data Items (as above). | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-435 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-017 D0304 & D0303 | 1. New D0304 Validation Rule 2. NewD0304 Rejection Reason Code "Q - MPAN Fwd migration in progress or completed" 3. Change D0303 so as to make "Eff From Settlement Date REGI" a non mandatory data item within the flow (an alternative to suggesting that outgoing MS no longer issues a D303, only the incoming MS would send) | Industry CP Required |  | Interim Release 5 | 2023-09-13 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-436 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG0-018 D312 | 1. New D03012 Validation Rule 2. New Rejection Reason Code "AD - MPAN Fwd migration in progress or completed" | Industry CP Required |  | Interim Release 5 | 2023-09-13 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-437 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-019 IF-005 Validation Rule | 1. New val rule to prevent IF-005 while MCS/MCA Appointment is in progress 2. New Error Code | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | REG9003 - MHHS MTD Updates cannot be used until Migration has completed, Created and new validation rule added to IF-005 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-438 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-020 REGS Design Clarification | SCS Should issue L1/L2 Msg Status message with RCP1061 for any MPAN at the incorrect status where a DIP Message is received | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | This is a Migration Requirment which participants should take into account as part of their Migration Designs. However, for clarity a note has been added to RCP1061 entry in the Intoduction Section of the Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-439 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-021 No Supplier Updates during Rev MIgration (IF-025) | 1. New If-025 val rule to check if Rev Migration Switch is in progress 2. New error code | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | REG9002 - Supplier Data Items Cannot be Maintained for Reverse Migration Account, Created and applied to IF-025 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-440 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-022 No CDCs Updates during Rev MIgration (IF-038) | 1. New If-038 val rule to check if Rev Migration Switch is in progress 2. New error code | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | "REG9001 - CDC Marker Cannot be applied to Reverse Migration Account", created and applied to IF-038. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-441 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-023 No AC Updates during Rev MIgration (IF-040) | 1. New If-040 val rule to check if Rev Migration Switch is in progress 2. New error code | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | Design Team Discussion with SCS required. Design Team minded that this is an invalid requirement. Helix will produce AC provided the site has not completed Reverse Migration, these updated should be accepted, design does not allow for rejection of an AC update.
MHHS-DIN-442 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-024 D0010/D0086 New MR Reason Codes | Three new MR Reason Codes for use in D0010: Forward Migration COS / Forward Migration COA / Reverse Migration | Industry CP Required |  | Interim Release 5 | 2023-09-13 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-443 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-025 D0055 New Agent App Reason Codes | 1. New Valid value for service reference "REVM" 2. New valid value for Service Level "REVM" | Industry CP Required |  | Interim Release 5 | 2023-09-13 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-444 | RS |  | 2023-06-19 | ESG |  | Patricia Parker | Software Provider | IF-01 Incoming supplier for Import/Export MPANs | Clarification required with SCS. If it is known that an alternative MPAN has the same SSD then we do not want the old supplier ID as the linked supplier on the IF-01, we want the new supplier to be populated | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | Confirmation required from SCS
MHHS-DIN-445 | SB |  | 2023-06-19 | Utiliteam |  | Richard Palmer | Software Provider | Spec of IF-024 in DES138 Interface Catalogue | The Population Notes for DI D-000 in Group S0 has ‘IF-025’. This error was in v5.0, and is still in v5.1.1 | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | The Population Notes for DI D-000 in Group S0 has been updated to ‘IF-024’ in IF-024. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-446 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-026 Migration DIP Reporting Reqs | Reqs for x3 new Reports -- Flag at the next DIP DAG | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-13 | Awaiting further internal discussions re DIP Reporting Strategy
MHHS-DIN-447 | SW |  | 2023-06-21 | Kraken | 5980 | Angelos Rizoyannis | Software Provider | Conditional Mandatory not applied in Swagger correctly | IF-041-CustomBlock: The field B065List is stated as optional in the comments, but the API schema does not reflect this. This field that is conditionally optional in DES-138, but this is not defined as such in Swagger ie, OneOf, AnyOf. This needs to be updated in Swagger to align correctly. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | In Swagger 1.3, updated IF-041-CustomBlock: The field B065List and B064List will be either / or as they are defined as conditionally mandatory in DES-138. This uses oneOf notation in Swagger. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-448 | SW |  | 2023-06-21 | Kraken | 5980 | Angelos Rizoyannis | Software Provider | Mandatory fields not applied correctly in S1 block | S1 Common Block: The 'properties' and 'required' sections of the API schema for the S1 common block have conflicting information. The 'properties' section includes fields like senderTimestamp and senderRoleID, while the 'required' section lists sentTimestamp and senderRole. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Updated Swagger 1.3 to align properties and required sections so that fields are called senderTimestamp and senderRoleID. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-449 | SC |  | 2023-06-21 | SRO Design Team |  | Sean Cooper | SRO Design | Change to IF-037 | Include Block B002 into IF037 so that outgoing MS is aware of incoming Supplier on a COS. This will allow the SP to populate the D0303 to MAP. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Block 002 added to IF-037 for use where event code is MSDeapp, this is so that the outgoing MS is informed of who the incoming supplier is so that D303 can be correctly population. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-450 | SC |  | 2023-06-22 | RECCO |  | Sean Cooper | SRO Design | Change to IF-005 Validation Rules | Change made to IF-005 validation Rules to allow previous MS to update Meter Location only - during the 10 day post appointment period. This will allow for scenarios where there has been relocation only activity immediatly prior to a change in MS. All other MeterUpdate functions apart from Change of Meter Location shall be rejected per wider agreement that only active MS should have the ability to change the characteristics... This change originated from R1 Comments feedback from RECCO | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | IF-005 Validation rules updated to include new "REG0008 - Amendment Requested cannot be undertaken by Previous Metering Service" error condition and code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-451 | SC |  | 2023-06-22 |  |  | Sean Cooper | SRO Design | CR - 018 Registration Service OOH Ops | CR18 looks to specify Registration Service Out-Of-Hours Operations. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | CR Contents incorporated into a new Section 7 of Ops Choreography Document | Technical corrrection | Supporting Docs | Operation Choreography | MHHSP_OPC001_Operational_Choreography
MHHS-DIN-452 | SC |  | 2023-06-22 | SCS |  | Sean Cooper | SRO Design | Refine Consent Checking Rules on IF-031 | Further refine Consent checking rules so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing . Updates to IF-031 validation rules to reflect this change. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | IF-031 alidation rules updated per the DIN Details. Consent checking rules added so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-453 | MF |  | 2023-06-22 | SCS |  | Mike Fensome | SRO Design | Issuing of IF-020's | Highlighted that LDSO's could issue an IF-020 with details of import/export linkages without having received notification from the Supplier | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Added note to IF-019 and IF-020 to inform Suppliers that Import/Export linkages could be received via PUB-020 unprompted by the Supplier issuing IF-019. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-454 | SC |  | 2023-06-26 | SCS |  | Sean Cooper | SRO Design | Update to ISD M7 | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service | Requirement correction | Supporting Docs | ISD Document | MHHSP-DES138-Interface Catalogue
MHHS-DIN-455 | SC |  | 2023-06-23 | SCS |  | Sean Cooper | SRO Design | Update Op Choreography (Event Move from IF-013 to IF-014) | Update Ops Choreography to take account of the movement of event [ConsumptionOnDeEnergisedMPAN] which was moved from IF-013 to IF-014 (DIN-255). | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | IF-014 Deadline split into two. First [ActivePowerRejected] remains UNCHANGED. Deadline for [ConsumptionOnDeEnergisedMPAN] is also UNCHANGED but moved from IF-013 row into IF-014 Row, to mirror the change delivered by (DIN-255) | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-456 | SC |  | 2023-06-23 | SCS |  | Sean Cooper | SRO Design | Swagger Correction - DI-844 | Corrected x2 invalid referenced to "AssignedMRDRequestEffectiveFromDate" should have been "AssignedMRDEffectiveFromDate" in Block 066 | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Corrected x2 invalid referenced to "AssignedMRDRequestEffectiveFromDate" should have been "AssignedMRDEffectiveFromDate" in Block 066 | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-457 | SC |  | 2023-06-23 | SCS |  | Sean Cooper | SRO Design | Change to DTN Validation of D0350 | Implement DTN Validation of D0350 to prevent future dates | Industry CP Required |  | Interim Release 4 | 2023-08-09
MHHS-DIN-458 | SC |  | 2023-06-23 | SCS |  | Sean Cooper | SR Design | New IF-019 Related MPAN Validation Rule | New Validation Rule required for IF-019 to ensure that only Import MPANs can be realted. Add to Create and Add Related - this is per REC Shedulle 28 | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Rules added to IF-019, [RelatedAdd] and [Related Create] events to ensure only Import MPANs can be in a related Group. New Error code added to support these new rules REG1067 - Only Import MPANs can become Related | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-459 | SB |  | 2023-06-23 | Utiliteam | 5724 | Richard Palmer | Software Provider | Spec of IF-024 in DEL138 Interface Catalogue | A further suggestion re the Interface Spec for the IF-024: The Event Code list in DI D-999 in Group S0 contains [SN-RemoteEnabled] & [SN-RemoteDisabled]. I would suggest that these are invalid for Segments Advanced and Unmetered. Also [SN-Vacant] would appear to be irrelevant for Segment Unmetered, and I doubt that [SN-NoComms] would be valid either. These existed in v5.0, and are still in v5.1.1. Perhaps the routing rules need some improvement? | Closed |  |  | 2023-08-09 | No change Required. Useage of these evernt codes is obvious and is described in the Requirments documents as necessary
MHHS-DIN-460 | SB |  | 2023-06-26 | Utiliteam | 5939 | Richard Palmer | Software Provider | PIF-019 structure & Principle -> Principal | Also, in the relationships between MPANs, the ‘main’ one is the ‘Principal’ one – not the ‘Principle’. This will be embarrassing if left uncorrected. It is still in v5.1.2 in IF-019, and it is in many other places. If there is a chance of correction, please take it. | Ready for Internal Review |  | Interim Release 3 | 2023-09-13 | Spelling mistake corrected in Data Catallouge, IF-019, IF-020. Note YAML name also corrected for DI-073. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-461 | SW |  | 26/06/2023 | Greenbird | 1768 | Fredrik Omland | Software Provider | Misalignment between DES-138 and Swagger for DIP Connection Provider ID | In DES-138, In the S1 block, DI-996 (Connection Provider DIP ID) is defined as Optional. But in Swagger, this is defined as mandatory. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Updated Swagger 1.3 so DI-996 in S1 block (Connection Provider DIP ID) is Optional to align with DES-138 | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-462 | SW |  | 27/06/2023 | Design Team |  | Steve Weston | SI Design | Schema Optionality incorrectly defined for some Interfaces | In DES-138, there are are a number of Interfaces where the Schema Optionality is defined as Optional, rather than Mandatory. The list of Interfaces are as follows - IF-050 / B022, IF-023 / B053 and IF-013 / B049 | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Updated Schema optionality in DES138 to show that all data items must be present where the block is present in line with updated E2E Solution Architecture for IF-050 / B022, IF-023 / B053 and IF-013 / B049. | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalouge
MHHS-DIN-463 | SW |  | 27/06/2023 | SIMS |  | Kyle Abraham | Software Provider | No ability de-register from receiving Status messages in Swagger | In Swagger, there is a POST method for /statusmessage/config, but there is no DELETE method, so you are unable to delete / de-register for any status messages. Need to update Swagger to ensure this is possible. | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Updates made to Swagger 1.3, so there is a DELETE method for /statusmessage/config, so you are now able to delete / de-register for any status messages. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-464 | SW |  | 27/06/2023 | SIMS |  | Kyle Abraham | Software Provider | Clarity required on values expected for /dip-channel/{id} for submitEvents on Swagger | The {id} in /dip-channel/{id} for submitEvents on Swagger should accepts values that are the same as the enumeration in DI-000 to ensure consistency. At the moment, this is not clear in Swagger or E2E001 design, so this needs to be updated to make this clearer. | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Updates made to Swagger 1.3, so there the correct enumerations / values are available to align with values in DI-000 to ensure consistency and avoid any ambiguity between interfaces and reports. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-465 | SC |  | 2023-06-28 | RECCO |  | Sean Cooper | SRO Design | Update to BP010 - Related MPANs | The process MPAN for Related MPANs does not clear call out the Rejection pathway. Update Business Process to show rejection process. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | BP010 Related MPANs Process updated to show specific Rejection Route. | Process Model correction | Metering Changes | Business Process Documentation | BP010- Changes to MPAN Data
MHHS-DIN-466 | SC | DI-188 | 2023-07-29 | SCS |  | Sean Cooper | SRO Design | Change of MPAN Status during Service Provider Appointment Process. | How should a change of MPAN Status be dealt with whilst there is an ongoing SP Appointment that has not yet reached the stage of IF-034 processing !? If an MPAN is disconnected between PUB-031 acceptance and receipt of PUB-034, the SP PUB-034 Response would be rejected by MPRS due to validation rule REG1001. The appointment would not be progressed but would be stuck in the MPRS queue at status Requested. Could resolve by amending REG1001 validation on IF-034, to not apply to event codes MSAppSPResponse or DSAppSPResponse. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Resolved following discussion with SCS, Agreed that SCS will take no action until the IF-034 has been processes. A change to REG1001 validation on IF-034, to not apply to event codes MSAppSPResponse or DSAppSPResponse, is required to allow the IF-034 to processes normally (when where MPAN is disconnected)... Following processing of the IF-034 RESG will then immediatly issue an IF-035 with reason code of "1- Lapsed as MPAN Status is Disconnected" ... ... Agreed that this was best resolution both for REGS processing rules and participants as no change to currently expected message patterns/ordering. | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalouge
MHHS-DIN-467 | SC |  | 2023-07-29 | ESG |  | Sean Cooper | SRO Design | Review of IF-035/IF036 Data Item Obfuscation | Review of IF-035/IF-036 Data Item Obfuscation | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09
MHHS-DIN-468 | SC |  | 2023-07-29 | Helix |  | Sean Cooper | SRO Design | Routing of IF-020 | Helix have confirmed that they DO NOT need to receive Related/Linked MPAN information therefore an update is required to REMOVE MDS from the receipient list for this IF-020 | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | IF-020 Routing table has been updated to REMOVE MDS as being a recipient of any IF-020 messages. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-469 | ME |  | 2023-06-30 | SRO Design Team | 2109 | Rob Golding | SRO Design | Removal of Z0 & Z1 data items in ERI011B - ECS Reports External | Z0 & Z1 data items to be removed from from the each of the MHHS reports within ERI011B - ECS Reports External as they are no longer in the common block | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Remove Z0 & Z1 data items from all MHHS reports in ECS external reporting artefact | Data interface correction | Minor | ECS Reports | ERI011B - ECS Reports External
MHHS-DIN-470 | SW |  | 29/06/2023 | Callisto | 1805 | Seth Chapman | Software Provider | Clarity on nullable fields | Section 4.2.2 in the E2E design provides information on Optional / nullable fields, but worked examples would provide further clarity for each of the data types / link to JSON specification. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Updated section 4.2.2 with worked examples for each data type to provide additional clarity. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-471 | MH |  | 2023-06-30 | Helix |  | Derek Weaving | Central Body | Update to REP-003 in ERI011B - ECS Reports External | R019 parent should be R017 in the ECS Reports External and Swagger | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Update R019 parent to R017 for REP-003 in ERI011B - ECS Reports External. Swagger v1.3 updated to align with changes within ECS reports artefact. | Data interface correction | Minor | Interface Changes | Swagger 1.3
MHHS-DIN-472 | SW |  | 29/06/2023 | SRO Design Team | 2006 | Rob Golding | SRO Design | Onboarding migration from Test to Production. | “The programme is to implement a strong PKI policy but as per the diagram states that that on promotion, parties will be able to copy their Test setup and to use that for connecting to the Prod environment. - steps 1-8 - There are no steps in this sequence that test the connectivity to the Live DIP environment. To this point the only connectivity testing has been to the Test environments. This is a significant failure point / risk. At this point Webhooks and certificates will change (mTLS and JSON signing) from those used in Test as well as potentially some of the PKI resources assigned to roles ( those used in test may not be applicable to Prod) we would expect that this would require a new Connectivity proving period with the Prod environment similar to that being developed for CIT. Without such proving, how can the programme assume all parties will connect to the Prod environment successfully and ensure minimal impact to migration events”. | Open - awaiting assessment |  | Interim Release 5 | 2023-09-13
MHHS-DIN-473 | SB |  | 2023-06-30 | MHHS | 2111 | Jason Brogden | Network Operator | Definition of Network Operations | Issue: There is a lack of clarity in the scope of Network Operations activities in testing. Action to Resolve: Add a definition to the Programme Glossary that makes clear the scope of Network Operations (as referenced in Testing material) is equivalent to the scope of LDSO activities in the MHHS Design Baseline: Network Operations systems and services are those that are required to deliver the elements of the MHHS Design Baseline that are allocated to the LDSO role. Communicate this to the DNO and iDNO community and associated service and software providers. I think it is important for us to show a united front as a Programme on this as a matter of clarity. For the DIN Log, we can then focus on updates to the BRS to give the necessary clarity on the scope of MHHS Design. Issue: There is a lack of clarity in the scope of LDSO activities in the MHHS Design Baseline as BRS005 implies MHHS-related processing requirements at LDSOs for received DIP messages, whereas the BPs and BPDs define the scope of MHHS as ending at the receipt of DIP messages. BRS005 is described as “For Guidance Only” at the top and this is to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing). Action to Resolve: For the avoidance of doubt and to provide clarity to BRS005, it is proposed to change the “For Guidance Only” note at the top of BRS005 to the following description as per the above: BRS005 is provided For Guidance Only to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing). | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | LDSO Requirements document updated with the following text, "BRS005 is provided For Guidance Only to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing)." | Requirement correction | Minor | Business Requirements Documentation | BRS-005 LDSO Overview.xls
MHHS-DIN-474 | ME |  | 2023-07-03 | MHHS |  | Kevin Spencer | SRO Design | Creation of new ECS data items and blocks across multiple reports and/or data catalogue | Report definitions incorrect and require updates and new data items following internal review | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | Addition of DI-503, DI-504, DI-505 data items across ECS reports artefact. MHHSP - ERI011B - ECS Reports - External v5.2 and MHHSP - ERI011A - ECS Reports - Internal v5.2 | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-475 | ME |  | 2023-07-03 | MHHS |  | Kevin Spencer | SRO Design | Update to block names, data items and descriptions | Report definitions incorrect and require updates and new data items following internal review | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09 | Update to block names, DTN references, data items and descriptions in MHHSP - ERI011B - ECS Reports - External v5.2 | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-476 | SW |  | 2023-07-03 | Greenbird | 2035 | Fredrik Omland | Software Provider | Inconsistency between enum fields and nullable definition | Looking at DIP Interfaces Swagger 1.1 (also 1.2 + 1.3), the enum typed fields that are nullable may not comply with OpenAPI specification (for 3.0.x). The topic around enum fields with nullable: true has been clarified/answered by OAS project (amended in spec version 3.0.3 in 2021): (Reference: https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md ) | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | To align with Open API spec clarification at https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md, we have updated all Data Types that are nullable and have an enum to align as follows: Following discussion, have decided to align with OpenAPI 3.1 DI-076-Estimation-Reason-Code: description : Used inconjunction with Settlement Period Quality Indicator to explain why data has been estimated type : string nullable: true maxLength : 2 example : '1' enum: - '1' # OptOut - '2' # Missing .. - '8' # Disconnected - '9' # Consumption Amendment - '10' # NonSmart - null The Data Types affected / updated as as follows: --- DI-039-Load-Shape-GSP-Group-ID --- DI-076-Estimation-Reason-Code --- DI-096-Site-Visit-Check-Code --- DI-126-Traditional-Fall-Back-Read-Frequency --- DI-137-IHD-Install-Status --- DI-150-Annual-Consumption-Quality-Indicator --- DI-166-Supplier-Consumption-Amendment-Reason-Code | Data interface correction | Minor | Interface Changes | Swagger 1.3
MHHS-DIN-477 | SW |  | 2023-07-03 | MHHS |  | Steve Weston | SRO Design | Swagger alignment to OpenAPI 3.1 specificiation | Align with Open API specification 3.1 to remove nullable :true and replace with type declarion ie, type:[string:”null”] | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-09
MHHS-DIN-478 | SW |  | 2023-07-03 | MHHS |  | Rob Golding |  |  | In the Release 2 version of DES138 a limit was introduced that asked Participants not to submit more than 150 Settlement Days’ worth of data in a single message. The value of 150 was proposed as this meant a single message would realistically be ~600KB in size. We’ve had some queries regarding this value, and given ECS should reject consumption data if it over 194 days old, the proposal is to increase sizing from 150 to 194 day message and the size increases from 600KB to ~780KB for IF-021 message. ECS will need to validate the message contents. However, rather than letting a ‘large’ IF-021 message traversing though the DIP, the proposal is to limit the IF-021 on ingress to the DIP and a single request will have a limit of 1MB – this will done at the API level. | Open - awaiting assessment
MHHS-DIN-479
MHHS-DIN-480
MHHS-DIN-481
MHHS-DIN-482
MHHS-DIN-483
MHHS-DIN-484
MHHS-DIN-485
MHHS-DIN-486
MHHS-DIN-487
MHHS-DIN-488
MHHS-DIN-489
MHHS-DIN-490
MHHS-DIN-491
MHHS-DIN-492
MHHS-DIN-493
MHHS-DIN-494
MHHS-DIN-495
MHHS-DIN-496
MHHS-DIN-497
MHHS-DIN-498
MHHS-DIN-499
MHHS-DIN-500
DIN Log Currently Being Updated

## Backup (hidden)
DIN ITEM DETAILS | [8 empty] | Scheduling |  | DIN IMPACT ASSESSMENT |  |  |  |  | DIN OUTCOME
Reference | other Reference(s) | Date Raised | Organisation | Freshdesk Ticket # | Contact Name | Constituency | Design Issue Notification Details (as notified by participant) | Current Status | Target working Group Date (If Required) | Target Release | Design Issue Proposed solution | Justification/Type of Change | Design Area | Design Area - L2 | Artefact(s) Impacted | DAG Review Date | DAG Outcome | Reason for Rejection/Accept caveats | Design Change Reference Number
MHHS-DIN-1 | T4-COM-1744 | 2023-01-30 | St Clements | 2655 | Madison Layton | Software Provider | Originally raised as T4-COM-1744 on 15th Sept 2022 MPRS does not currently restrict IHD Installs to Smart Meters, there maybe cases where there is an IHD present but the Meter is Trad (Not compatible with DCC and Customer Switched) Either Allow IHD on all Market Segments OR Cleansing to ensure IHDs are only present on S2 and S1 Meters SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses, as this is still not resolved | Updates Verified for Industry Review |  | Interim Release 1 | Discussed with SCS and agreed to add new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) Added requirements into BRS003. SCS to raise a potential data cleanse. | Requirement correction | MPAN Ownership | SCS Validation | MHHSP-BRS003-Registration Requirements | 2023-03-23
MHHS-DIN-2 | T4-COM-1745 | 2023-01-30 | St Clements | 2657 | Madison Layton | Software Provider | Orginally raised as T4-COM-1745 on 15th Sept 2022 DB002 is not the interface on which MPRS will be informed of a change to import/export relationship, it is DB05. The wrong diagram was updated, the EDI was updated to DB05 not import/export. SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses and artefact updates, to inform the wrong data item diagram was updated. However the diagram for EDI updates is still incorrectly reading DB005 update instead of DB02 | Closed |  |  | This appears to have been missed in v4.6 - the arrow on BP-010B from step435 to Step 440 shows DB005 (not DB05, assume that’s a minor typo in the comment) - and this is the Energy Direction Information (EDI) which is wrong. It has cbeen onfirmed that this was updated in v4.7 to go into v5.0 baseline. | No Change |  |  | None
MHHS-DIN-3 | T4-COM-1752 | 2023-01-30 | St Clements | 2661 | Madison Layton | Software Provider | Originally raised as T4-COM-1752 on 15th Sept 2022: MHHS-BR-RS-020: "Retro" (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier ) In the D0205 the Supplier can cancel out the current Agent Appointment by setting the EFD to equal the currently stored Appointment EFD. Is this no longer allowed? All Services must be appointed for at least one day valid or not? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: removing the ability for Suppliers to Correct Invalid Service Appointments may not be understood by suppliers. We want to avoid a later Design CR to add this functionality in. SCS has not had a response, feel this is important discuss with Suppliers to avoid later CRs | Closed |  |  | The appointment can be resubmitted if it hasn’t been accepted yet. Once accepted, there is a need to maintain contiguous appointment periods. The scenario mentioned is the CoA not linked to a switch, so the acceptance of a new appointment from a particular EFD will ‘lock in’ that date and the previous MS/DS will be de-appointed at midnight on the previous day. This is to ensure that there are no periods left without MS and/or DS in place, which can happen today with D0155/D0151 sequencing issues. As an overall comment, there is not a concept of cancellation of appointments. The only way to alter the appointment is to get a new IF-031 issued. The only way to do this for the scenario presented, would be to issue an IF-031 for the old MS for the original date and an IF-031 for the new MS for the revised date. Requirement MHHS-BR-RS-021 ensures that Registration Service will action the latest received appointment where there are duplicate appointments for the same day. St Clements had requested that we build in a rule saying that you cannot submit a Change of Service Provider (CSP) request for the same Service Provider. It is a bit of a work-around, but we believe sending it as SEG should work, or alternatively a CR would be required to re-look at the interface validation. Closing, as this doesn't require further action - point noted. We have already spoken to a number of suppliers, and will continue to engage to ensure the functionality of the baselined design is understood and any issues picked up as early as possible. Documentation for LDSOs to point at. Pick up in Code Drafting as well. | No Change |  |  | None
MHHS-DIN-4 | T4-COM-1755 | 2023-01-30 | St Clements | 2666 | Madison Layton | Software Provider | Originally raised as T4-COM-1755 on 15th Sept 2022: MHHS-BR-RS-071.2 REC CP R062 has been raised to remove the restriction on the number of EDI changes. Will this cause any downstream MHHS issues? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Needs to be aligned with REC Change No responses | Closed |  |  | As per original SRO response, the impacts of the REC change need to be dealt with through the REC change process and impact assessment. | No Change |  |  | None
MHHS-DIN-5 | T4-COM-1760 | 2023-01-30 | St Clements | 2667 | Madison Layton | Software Provider | Originally raised as T4-COM-1760 on 15th Sept 2022: There are no Registration Service Reports defined in MHHSP-ERI011A. Will there be a requirement for MPRS to produce any Industry Reports for MHHS? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Design for the complete solution must be defined by M5. This is a DBT Design Start Blocker No responses This could significantly increase DBT time as development of reports can be costly and time consuming | Closed |  |  | Who is raising these requirements? What happens today? Possibly CC issues Agreed with SCS that reporting requirements will be introduced via the CR process. Reporting requirements are to be added to the programme RAID log | No Change |  |  | None
MHHS-DIN-6 | T4-COM-1761 DI-7 | 2023-01-30 | St Clements | 2668 | Madison Layton | Software Provider | Originally raised as T4-COM-1761 on 15th Sept 2022: IF-005, REG1014 First MAP Block, MAP Eff From Date [DI-054] in message, must = MPAN Install date OR >= Eff Form date of all existing MAP Effective From Dates held in Registration prior to first [DI-054] in message I understand that the First MAP must equal the Install Date, I am unsure what the second condition is trying to say? You can not have a Meter Without a MAP. (ignoring customer owned meters where CUST is used) SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: response is incorrect. The Second Rule "Each subsequent MAP Effective From Date [DI-054] must be > MAP Eff From Date in previous block" covers the subsequent overlapping MAPs. The second half of this First Block Rule must be removed. The First Block can only ever equal the install date No responses, the rule has not been amended | Updates Verified for Industry Review |  | Interim Release 1 | This appears valid - the first MAP block can only start at the creation date (assuming the MAP blocks are in chronological order, which they must be if each subsequent map block has an EFD > the last) Currently the design allows 2 ways to amend the MAP History as outlined in Sections 13 and 14 of the IF005 Use Case Guide. Either the Metering Service can provide the full MAP history from the installation date or they can add a new MAP to the existing history, provided it is the next MAP in chronological order. So for example if you have MAPs 1,2 and 3, then you can extend to MAPs 1,2, 3 and 4 using the approach set out in section 14 to extend the MAP history. However if you wanted to set MAP 4 between 2 and 3, you would need to send the whole MAP history from the install date and provide 1,2,4 and 3 as set out in Section 13 to replace MAP history. The second validation rule is required if you are using the extend the MAP history functionality. Added note to REG Notes that where a MAP history is provided it must be in chronological order Added new REG1014 Validation Rule to MeterInstall and MeterExchange events to ensure only 1 MAP block is provided | Data interface correction | MPAN Ownership | SCS Validation | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-7 | DI-8, DI-11, DI-12, DI-14 | 2023-01-30 | St Clements | 2669 | Madison Layton | Software Provider | MPRS will reject any PUB-031 inlcuding those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8) | Updates Verified for Industry Review |  | Interim Release 1 | See Comments Revised CSS Registration Request ID validation on IF-031, 034 and 025 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | IF General | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-8 | N/A | 2023-02-01 | Elexon | 2642 | Sedef Kiris | Central Body | We have had the following comment ........... Also just found out that “Metering Service Id” have “MPID” in brackets afterwards, and not “MSID”. We believe it should be MSID | Closed |  |  | MPID is the correct term here, it is the metering service MPID. MHHSP_EDI012_ISD_Entities v4.6 Section M8 | No Change |  |  | None
MHHS-DIN-9 | N/A | 2023-01-30 | St Clements | 2672 | Madison Layton | Software Provider | Comment sent on 11th Jan: [UpdateSiteTechnicalInfoMS] is not included in the interface catalogue and is not utilised by MPRS. Assume this is related to Issue 99 and needs removing? (raised as DI ID 9) | Updates Verified for Industry Review |  | Interim Release 1 | Removed from IF-005 Guide Section 4.1 | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-10 | N/A | 2023-01-30 | St Clements | 2799/2670 | Madison Layton | Software Provider | Comment sent on 11th Jan: Is the currently appointed Meter Service informed of Prospective MS changes? Changes to MTDs can be made by prospective MS (e.g. change meter type to complete SEG market change before the MS can be appointed). As the MS is only prospective at this point the MS may still be lapsed and not take effect. However any MTD updates made would remain within the MPRS system and not be backed out. The current MS would therefore need to be aware of what changes have been made by the prospective MS. (raised as DI ID 10) | Closed |  |  | BP009 only talks about the Metering Service, not the current or prospective Metering Service, and it appears only the registration service receive metering service MTD details, not the current MS. Refer to SRO - what is the assumption here, as the alternative route is for registration to update the current MS The design is based on PUB-006, with the Updated Meter details, being sent to the current Metering Service ( BP011A step 280 ) as well as the Prospective Metering Service (Step 275). It is built into the routing rules in PUB-006. | No Change |  |  | None
MHHS-DIN-11 | N/A | 2023-01-30 | St Clements | 2675 | Madison Layton | Software Provider | Comment on Section 5.1 "• Metering activity, as determined by the Install / Remove Date(s) takes place within the Metering Services period of ownership (or proposed period of ownership for in the case of a prospective SEG appointment) " Sent on 11th Jan: Does not match business rules, as future dated installs are not allowed: "REG1020 - Meter Install Date [DI-057] cannot take place in the future. The proposed MS on a seg will have a future dated EFD, so they only have the +2 day lapse extension period for meter installs (raised as DI ID 11) | Updates Verified for Industry Review |  | Interim Release 1 | Added change of segment scenario's to IF005 USE CASE Guide. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 |  | Refer back to SCS as additional comentary needed on the issue and bring to next meeting
MHHS-DIN-12 | N/A | 2023-01-30 | St Clements | 2679 | Madison Layton | Software Provider | Comment on Section 5.1 "• Metering activity, as determined by the Install /Remove Date(s), cannot have taken place in the future" Sent on 11th Jan: It would be useful to have the Change of Segment process covered in this guide. We are not sure how the Prospective MS can exchange meters when their appointment period is in the future (raised as DI ID 12) | Updates Verified for Industry Review |  | Interim Release 1 | Nomenclature issue - requires a reword of this statement to conform to the business rules. Recommend the following update to section 3.2 of the IF005 Use Case Guide to confirm who can make Metering updates Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed BAU metering updates ( For the avoidance of doubt not meter update/meter history updates), it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. The one exception, is during a change of segment, when the incoming Metering Service is able to provide a BAU metering update, where it’s prospective “SEG” appointment is due to become active on the same day. SEG scenario's added to IF005 Use case guide Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-13 | N/A | 2023-01-30 | St Clements | 2683 | Madison Layton | Software Provider | Comment on Section 5.1 "validation allows for meter removal at a point following Disconnection if required)" Sent on 11th Jan: This rule prevents this REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational (raised as DI ID 13) | Updates Verified for Industry Review |  | Interim Release 1 | This statement doesn't appear to be a convention. There is no mention of this in E2E001 End to End Solution Architecture. Believe this statement needs to be amended or removed. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. IF-005 validation Rule changed to include meter removal at status Disconnected | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES138-Interface Catalogue, E2E001 End to End Solution Architecture
MHHS-DIN-14 | N/A | 2023-01-30 | St Clements | 2684 | Madison Layton | Software Provider | Comment on Section 3.2 "Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed metering updates, it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. " Statement is misleading- the 10 day period is only permitted for install, remove and exchange events, it is not listed for meterUpdate/meterHistoryUpdate in interface catalogue Also the prospective MS should be able to make changes for SEG to enable a market segment change to complete (raised as DI ID 14) | Updates Verified for Industry Review |  | Interim Release 1 | Validation rule(s) updated to constrain 10 day window to non-update events. Test in 3.2 reworded to remove ambiguity. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Refer back to SCS for additional clarity on the requirement and include RecCo and bring to next meeting
MHHS-DIN-15 | N/A | 2023-01-30 | St Clements | 2685 | Madison Layton | Software Provider | Comment raised in guide, sent on 11th Jan, that the JSON examples use MPID when it should use DIP ID e.g."distributorID": "SWAL" (raised as DI ID 15) | Updates Verified for Industry Review |  | Interim Release 1 | Corrected to use Dist DIP ID | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-16 | N/A | 2023-01-30 | St Clements | 2686 | Madison Layton | Software Provider | Comment on Section 9 " Albeit that these transactions can be ‘clubbed together’ and send as a group in single overarching message/API transaction. " Sent on 11th Jan: As DIP does not protect the sequencing of events (FIFO), is there a risk that the ordering of these updates might arrive out of sequence resulting in the wrong end state? If MS space out their updates it would reduce this risk (raised as DI ID 16) | Updates Verified for Industry Review |  | Interim Release 1 | Clairifcation added to Sec 9.2 to reference Time-Stamps rather than 'clubbing' | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-17 | N/A | 2023-01-30 | St Clements | 2690 | Madison Layton | Software Provider | Comment on Section 9 "a supporting MAP history commencing in line with the revised Installation Date must also be provided" Sent on 11th Jan: Will the MS know the full MAP history? Risk they could destroy the data. Potential MAP billing issues? (raised as DI ID 17) Ticket sent to Mike Fensome for background on how current design was reached (3/2/23) | Initial Assessment/Updating | 2023-05-24 | Interim Release 3 | Solution agreed at DRG on what MAP updates are required |  |  |  | None
MHHS-DIN-18 | N/A | 2023-01-30 | St Clements | 2691 | Madison Layton | Software Provider | Comment on Section 9 "• When maintaining the MAP History in cases where there is no change in Meter Installation Date then the MAP history provided should commence either with a MAP Effective From Date matching the existing install date of the meter OR be greater than the most recent, already existing, MAP Effective From Date" Sent on 11th Jan: So it's possible to update ALL MAP history back to installation, or add a new MAP, but it's not possible to amend MAP history only part way back (have to go back to installation date instead every time to do this) (raised as DI ID 18) | Closed |  |  | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • To update BRS003, requirement MHHS-BR-RS-027 to add “Registration Service must lapse any appointments that fail this validation” • Remove Rejected from Step 225 of BP002/BPD002 • Remove Rejected from label on line after step 215 of BP003. | No Change |  |  | None
MHHS-DIN-19 | N/A | 2023-01-30 | St Clements | 2692 | Madison Layton | Software Provider | Comment on Section 10 "E2E Architecture convention states that all data items are provided in each message even where these data items are not changing or are null" Sent on 11th Jan: Some of the items are optional not mandatory which conflicts with this statement. Not all data items need to be provided (raised as DI ID 19) | Updates Verified for Industry Review |  | Interim Release 1 | Update of E2E Doc to allow for Nullable values. | Data interface correction | Meter to Bank |  | MHHSP-E2E001 End-to-End Solution Architecture | 2023-02-23 |  | Defer as a E2E clarification may be needed
MHHS-DIN-20 | N/A | 2023-01-30 | St Clements | 2693 | Madison Layton | Software Provider | Comment on Section 13, sent on 11th Jan: What should MPRS do if it holds a MAP not included in the MAPHistory block? (raised as DI ID 20) | Updates Verified for Industry Review |  | Interim Release 1 | Update "all existing history will be replaced by that contained within the message" | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-21 | N/A | 2023-01-30 | St Clements | 2699 | Madison Layton | Software Provider | Comment on Section 15.2 "It is understood that currently there a numerous instances of duplicated Meter ID’s, some of which may have overlapping installation dates. " Sent on Jan 11th: Meter id is only unique at mpan. Should not be any instances of conflicted MSNs at MPAN. Can you verify with ECOES? Or we can do a RFI to DNOs but will take time (raised as DI ID 21) | Updates Verified for Industry Review |  | Interim Release 1 | All references to duplicated MSN IDs has been removed from the document | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-22 | N/A | 2023-01-30 | St Clements | 2700 | Madison Layton | Software Provider | Comment on Seciton 15.3 "add some kind of suffix (X1, X2) to the existing Meter ID." Sent on Jan 11th: This can take the meter ID over the allowable string length (string 10), in this example it would take it to string(12) and so would be rejected (raised as DI ID 22) | Updates Verified for Industry Review |  | Interim Release 1 | As above, Section 15.3 removed from IF-005 User Guide. | Data interface correction | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-23 | N/A | 2023-01-30 | St Clements | 2701 | Madison Layton | Software Provider | Comment on Section 16.3 Sent on Jan 11th: Cancelled Flag Set. Only a logical deletion. Still held in MPRS but not visible to EES/MEM The section implies the record would be fully deleted from MPRS, however this is not correct, MPRS would set a cancellation flag that would indicate the record has effectively been cancelled/logically deleted. It would however remain in the systems database (raised as DI ID 23) | Updates Verified for Industry Review |  | Interim Release 1 | Added a statement at the end of the table in 16.3 to say "NB the registration service will only logically delete the MAP entry with a flag, it will not be deleted from the database." | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Accepted
MHHS-DIN-24 | N/A | 2023-01-30 | St Clements | 2702 | Madison Layton | Software Provider | Comment on Section 17.2 "situations where multiple existing meters are identified, the selection process should be extended to include Meter Removal date (if provided) else;" Sent on Jan 11th: Shouldn’t be possible, can run an EES or MPRS RFI to confirm. Noting that MSN is only unique at an MPAN level not a databse level Related to DI-21 (raised as DI ID 24) | Updates Verified for Industry Review |  | Interim Release 1 | Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. The wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-25 | N/A | 2023-01-30 | St Clements | 2706 | Madison Layton | Software Provider | Comment on Section 17.2 "where multiple meters still exist even after matching on all three data items should be rejected and require manual intervention (i.e. request to LDSO to intervene) ." Sent on Jan 11th: There's no super user functionality for this so how could the LDSO intervene? The LDSO is not able to manually intervene in regards to MTDs, they can for some other data items such as registration data but not MTDs. (raised as DI ID 25) | Updates Verified for Industry Review |  | Interim Release 1 | Reference to LDSO User Removed - agreed with SCS that scenario should not arise provided existing SCS data rules are met | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-26 | N/A | 2023-01-30 | St Clements | 2707 | Madison Layton | Software Provider | Comment on Section 17.2 "If the MAP segment is not provided, the existing MAP history should be maintained to greatest degree possible, with ‘trimming’ to align to any revised Install / Remove Dates provided" Sent on Jan 11th: Risk that changing of the Meter Lifespan could result in MAPs being logically deleted. The MS would need to re-apply the MAP history to fit into the new meter Lifespan MS would need to understand this process/constraint (raised as DI ID 26) | Updates Verified for Industry Review |  | Interim Release 1 | Section 17.2 of the guidance document updated. Also added new validation rule REG1014 for MeterHistoryUpdate in IF-005 to ensure MAP is provided when creating a new meter picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-27 | N/A | 2023-01-30 | St Clements | 2708 | Madison Layton | Software Provider | Comment on Section 19.2 "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the permanent deletion of data, mirroring the existing functionality associated with the use of the D0312." Sent on Jan 11th: Only logically deleted, still visible in the MPRS History. Just not visible to MEM or EES Existing functionality on D0312 utilises cancellation flags not permanent deletion (raised as DI ID 27) | Updates Verified for Industry Review |  | Interim Release 1 | Reword to reflect the logical deletion. See MHHS-DIN-23 Reword this paragraph to: "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the removal of a MAP from a meters MAP history using a logical flag, mirroring the existing functionality associated with the use of the D0312." NB Main section header is incorrect - should be updated to section 19, rather than a duplicate of section 18. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Accepted but note there is another DIN already raised
MHHS-DIN-28 | N/A | 2023-01-30 | St Clements | 2709 | Madison Layton | Software Provider | Comment on Section 19.4 "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories. However, this would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." Sent on Jan 11th: This functionality already exists with the MPAN History Report showing who changed what when for all MPRS data items. Will be extended to include DIP transactional information (raised as DI ID 28) | Updates Verified for Industry Review |  | Interim Release 1 | Proposed Change Reword this paragraph to: "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories, noting that this is also available via the MPAN history report which will be updated with DIP transactional information and could also be used. Any use of EES would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-29 | N/A | 2023-01-30 | St Clements | 2710 | Madison Layton | Software Provider | There should be an additional rule for USP, if DI-830/DI-833 is populated, the MS/DS Proposed Effective From Date must equal the currently held EFD for the MS/DS appointment in MPRS (raised as DI 29) | Updates Verified for Industry Review | 2023-04-27 | Interim Release 1 | Added rule for USP scenario in IF-031 to check SP Effective from date. Proposing SCS have flexibility on error codes - requires industry Working Group. Picked up as part of Change of Service Provider review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-30 | N/A | 2023-01-30 | St Clements | 2711 | Madison Layton | Software Provider | The IF-035 does not provide the opportunity for MPRS to populate a lapsed reason. Will need to be able to provide a reason for a lapsed appointment, otherwise there'll be a higher volume of unecessary supplier enquries to DNOs which will require more resource and cost. (raised as DI 30) | Updates Verified for Industry Review |  | Interim Release 1 | Additional Data Item on IF-035 for a reason comment - what reasons would these be other than gone beyond the date? Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-31 | N/A | 2023-01-30 | St Clements | 2712 | Madison Layton | Software Provider | MHHS-BR-RS-027 "Registration Service must re-run validation, in line with the validation rules set out in the appropriate interface specification, for all Metering Service appointments that have been confirmed to re-process from the Prospective Appointment Queue, to ensure that the appointment is still valid" It is not clear if MPRS would send MSAppRejected or MSAppLapsed if the appointment fails validation after it's been queued? If this is not made clear in the deisgn then there is a risk that we build to use the wrong event code, or if the code should be MSAppRejected then risk that suppliers build a design where they can't process a MSAppRejected after receiving already an MSAppAccepted from MPRS (raised as DI 31) | Updates Verified for Industry Review |  | Interim Release 1 | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • Updated BRS003, requirement MHHS-BR-RS-032 and 66 to show that appointments will be lapsed (not rejected) • Remove Rejected from Step 225 of BP002/BPD002 Also on BP003 leading from step 215 should have the rejected removed. Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership |  | MHHSP-BP002-Change of Service - Metering service, MHHSP-BRS003-Registration Service requirements MHHSP-DES138-Interface Catalogue, MHHSP-BP003 | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-32 | N/A | 2023-01-30 | St Clements | 2713 | Madison Layton | Software Provider | The interface catalogue lists setting a removal date as an action that can be used with event code meterUpdate on IF-005, however in the interface catalogue, the block B039 does not list meterUpdate as a event code that can utilise this block. Need greater clarity on whether meterUpdate and meterHistoryUpdate should apply meter installations and meter removals or not. (raised as DI 33) | Updates Verified for Industry Review |  | Interim Release 1 | The definition of a [MeterUpdate] event code is: Allows currently appointed Metering Service to amend the details associated with a currently installed meter. Therefore the appointed Metering Service must be able to remove the meter as part of an update, this is an omission from the design and a small update to IF-005 The design principle that IF-005 works on is that: • BAU transactions (Install/Exchange/Remove) that are in the Metering Services Period of ownership are covered by the Install/Exchange/Remove events • Changes to currently installed metering can be made by the Appointed Metering Service using the Meter Update event. Note this therefore includes, where required, removing the currently installed meter where it is prior to the current period of ownership. • Changes to metering history ( ie not the currently installed meter ) can be made by the Appointed Metering Service using the Meter History Update Proposed changes: Added MeterUpdate as Optional to B039 block in IF-005 and added validation rule to ensure MeterUpdate is not used to remove meters in current period of ownership picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP-DELS229-IF-005 Use Case Guide | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-33 | T4-COM-1759 | 2023-01-30 | St Clements | 2719 | Madison Layton | Software Provider | Originally raised as T4-COM-1759 on 15th Sept 2022: IF-005, REG1011 Install date must be > Creation date, should this REG1011 rule apply also to meter Exchange not just meter install SCS raised as a design blocker on 7th October 2022 Still no resolution, should this rule apply to meterHistoryUpdate at least as this allows for meter installations (raised as DI 34) | Updates Verified for Industry Review |  | Interim Release 1 | An exchange will not be a creation date, and the validation already in place ensures that future installation dates will all follow each other, which means this rule isn't required. ​This shouldn't be needed for exchanges, as its covered by REG1008 (install date >= remove date), as an exchange would replace an existing meter, which at first install would be validated against creation date. Moved REG1011 to cover all scenarios in IF005 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-34 | T4-COM-1774 | 2023-01-30 | St Clements | 2720 | Madison Layton | Software Provider | Originally raised as T4-COM-1774 on 15th Sept 2022: IF-005, REG1011 "REG1009 - MAP ID [DI_055] is not valid for MAP Effective Date [DI-054] REG1011 - Install Date [DI-057] for MeterID [DI-056] is prior to MPAN Creation Date There are many meters in MPRS that pre-date the existence of the MAP and also MPRS install dates of 1980 etc. these will break a number of rules. should these be cleansed before MHHS start? If they are valid, then the rules need adjusting"l SCS raised as a design blocker on 7th October 2022 Still no resolution (raised as DI 35) | Closed |  |  | This could be a data cleanse requirement which is a consequential change/transition requirement, but for REG1009 - the MAP effective date should be the point at which the MAP took over the meter, and the exchange date should be after this (ie it should be after the date MHHS goes live). For Reg 1011 currently this is only valid on installs (and installs won't occur on legacy meters). If Reg 1011 is valid on exchanges, then the exchange date should also be after the MPAN creation date - if it isn't then the data should be cleansed. Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-35 | N/A | 2023-01-30 | St Clements | 2721 | Madison Layton | Software Provider | On the IF-005, should REG1028 (Install date cannot be null or blank) apply to meterinstall, meter exchange and meterupdate too? (raised as DI 36) | Updates Verified for Industry Review |  | Interim Release 1 | Requires amendment to interface validation - look at alternative validation Agree the rule should also apply for those events. Note we believe validation would fail for another reason. Eg REG1019 Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-36 | N/A | 2023-01-30 | St Clements | 2722 | Madison Layton | Software Provider | In the summary of error codes box at the bottom of IF-005 tab the rejection reasons need re-aligning to the main block, e.g. REG1001 should read RMP stats must be Created or Operational, not just Operational As a general note across all interfaces, the rejection codes are referenced in numerous places and the respective descriptions are in many places not consistent for the same rejection code (raised as DI 37) | Updates Verified for Industry Review | 2023-04-27 | Interim Release 1 | Request flexibility for SCS in error messages provided | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | 23/2/23 - Not discussed at meeting carry to next meeting
MHHS-DIN-37 | N/A | 2023-01-30 | St Clements | 2723 | Madison Layton | Software Provider | REG1015 (cannot be removed meter) is listed for meterHistoryUpdate in interface catalogue for IF-005. This should actually apply to meterUpdate not meterHistoryUpdate, REG1018 (cannot be installed meter) applies to metering history update (raised as DI 38) | Updates Verified for Industry Review |  | Interim Release 1 | Change accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-38 | N/A | 2023-01-30 | St Clements | 2724 | Madison Layton | Software Provider | In the interface catalogue, the IHD block B030 for IF-005 should also be optional for meterUpdate according to the IF-005 guide Section 16 Development Notes "The IHD segment, if provided as part of [MeterUpdate], relating to any currently installed meter should replace/update the IHD details currently held at the MPAN to which that Meter is associated." (raised as DI 39) | Updates Verified for Industry Review |  | Interim Release 1 | Small change to schema operation IHD information may be updated as part of the [MeterUpdate] event. The change is to add [MeterUpdate] event to block B030, so it now reads "B030 - MPAN IHD Information (Optional & may only be used with [MeterInstall],[MeterExchange],[MeterUpdate]) NB this also standardises the use of commas between event codes, rather than using the & symbol. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-39 | N/A | 2023-01-30 | St Clements | 2725 | Madison Layton | Software Provider | In interface catalogue for IF-005, there needs to be a rule that if event code MeterInstall is used, then modified meter ID cannot be populated (raised as DI 40) | Updates Verified for Industry Review |  | Interim Release 1 | Update agreed | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-40 |  | 2023-02-01 | SI Design |  |  |  | Not used - raised as duplicate in error | Closed
MHHS-DIN-41 | N/A | 2023-01-30 | St Clements | 2730 | Madison Layton | Software Provider | In interface catalogue IF-005: The REG1003 reads Metering Service [S0.SenderID] holds valid previous appointment then Meter Install Date [DI-57] should be < [REG.App End Date] + 10 The way it's curently written suggests MPRS should accept an IF-005 from the previous appoint, even if their ETD was greater than 10 days ago, provided the install date was less than their ETD + 10. E.g the previous MS could send IF-005 two years later with Install date of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then REG1002/REG1019 should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? (Raised as DI 41) | Updates Verified for Industry Review |  | Interim Release 1 | Having looked through IF-005 Dates should be within the appointment date, and current deign does give the ability to go outside this Change the validation rule for REG1003 on events [MeterExchange], [MeterInstall] and [MeterRemoval] to "If Metering Service [S0.SenderID] holds valid previous appointment then [system date] < [REG.App End Date] + 10" Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. Rule amended after review by SCS, to remove second "if" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-42 | N/A | 2023-01-30 | St Clements | 2784 | Madison Layton | Software Provider | In interface catalogue IF-005: Meter Update should apply validation REG1027 (current MS or prospective MS) not REG1012 (current MS only) to allow the prospective queued MS to update the Meter Type on a SEG change and therfore complete the market segment change and appointment. MHHS-BR-RS-132 . If the SEG prospective appointment was not allowed to update on meterUpdate event code then they would not be able to update the meter type to completed change of market segment, and would not meet the conditions needed to then be appointed in MPRS, their appointment would then lapse and market segment would remain invalid. (Raised as DI 42) | Closed |  |  | We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error... | No Change |  |  | None
MHHS-DIN-43 | N/A | 2023-01-30 | St Clements | 2732 | Madison Layton | Software Provider | In Interface Catalogue, on If-005, REG1002 and REG1019 are duplicates (install/removal dates should be within MS period of ownership). We can only use one of the rejection codes and descriptions, programme should choose which one to keep and remove the other. (Raised as DI 43) | Closed |  |  | These are testing slightly different things. The first test (REG1002) is checking that the Metering Service is an eligible party to send the request ie currently appointed OR was at the time of the install (to cover for previous Metering Services updating in the 10 day window). The second (REG1019) is checking that the Install Date is in the Metering Services period of ownership. So you could have that the Metering Service is currently appointed, but that they weren't at the install date. Eg Today is 2nd Feb, Meter installed on 27th Jan, Sending MS was appointed on 1st Feb REG1002 would pass as they are eligible as the currently appointed MS REG1019 would fail as they are not appointed at the time of the install Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-44 | N/A | 2023-01-30 | St Clements | 2733 | Madison Layton | Software Provider | Should the new rule for meter update in IF-005 also apply to meter history update? If no MAP entries provided, and revised Meter Install / Remove Dates result in no valid MAM History then reject with REGE1014 – MAP Eff From Sequence Error (Raised as DI 44) | Updates Verified for Industry Review |  | Interim Release 1 | Added REG1014 ( MAP History ) to IF-005 MeterHistoryUpdate event | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-45 | N/A | 2023-01-30 | St Clements | 2736 | Madison Layton | Software Provider | New rule for IF-005 Meter Update REG1017 could be misinterpreted as it currently reads incorrectly - need brackets to correct to how the AND and AND/OR conditions are to be applied If [DI-60] is not null AND Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null) Should read If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null)) (Raised as DI 45) | Updates Verified for Industry Review |  | Interim Release 1 | Clarification of existing design rule Change the validation rule for REG1017 to: "If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null))" picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-46 | N/A | 2023-01-30 | St Clements | 2737 | Madison Layton | Software Provider | on IF-005 for Meter Exchange and meter install the rule for REG1027 has been changed, but I'm not sure the wording implements the rule intended exactly? Currently it reads as The MS must be the currently appoint MS AND the install date must be > MS EFD AND the MS must not have proposed MS app with SEG scenario in the queue. If not then reject with REG1027 - Metering Service is not currently appointed and does not hold a Prospective SEG Appointment SHould the rule actually read The MS must be the current MS OR the MS must have a proposed MS App in the queue with SEG scenario And then the other part of the rule about install date > MS should be a separate rule (with REG1019 error code). (Raised as DI 46) | Updates Verified for Industry Review |  | Interim Release 1 | Sent to Mike F for validation - SI believe wording in current documentation is correct. Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. I would suggest the wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. DIN-46 – On review we agree, the date test should always be true if REG1019 is satisfied ( with minor clarification update ), so validation rules should be updated as below: Proposed changes: REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 |  | Not discussed at meeting carry to next meeting
MHHS-DIN-47 | N/A | 2023-01-30 | St Clements | 2738 | Madison Layton | Software Provider | REG1001 on IF-005 does not allow for meters to be removed after a disconnection. Instead should restrict for allow other event codes but allow Status Terminated for MeterRemoval. DES204 CCR-0556 Linked to DI-13 | Updates Verified for Industry Review |  | Interim Release 1 | Rule update required picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-48 | N/A | 2023-01-30 | St Clements | 2739 | Madison Layton | Software Provider | Unhappy path scenario:- What happens if, for whatever reason, CSS fails to apply CoS to all the related secondary MPANs MPRS receives IF-031 on primary RMP to change agent, MPRS applies this to all seocndary MPANs too But if the CoS was not received from CSS for secondary MPANs that the secondary MPANs would still currently be held for the wrong supplier Would this cause any issues downstream? (Raised as DI 48) | Initial Assessment/Updating |  | Interim Release 3 | CSS Defects issue. Agreed that Risk would be raised and all CSS related issued assesed at a later date | Other | MPAN Ownership | Related MPANs
MHHS-DIN-49 | N/A | 2023-01-30 | St Clements | 2740 | Madison Layton | Software Provider | Unhappy path scenario:- If MPRS sends a IF-033 but never receives back a IF-034 then the rest of the process will not continue. The Supplier will never receive the IF-035 they are waiting for and the SP would never get appointed by MPRS. Is there a process in place to detect/resolve this scenario? (Raised as DI 49) | Closed |  |  | There is a requirement for the Supplier to monitor for any delayed responses and request an update if not received in expected timescales. Reviewed with SCS and agreed ticket can be closed
MHHS-DIN-50 | N/A | 2023-01-30 | St Clements | 2741 | Madison Layton | Software Provider | We need clear rules to define what a valid Consent granularity looks like. Current rules don’t mention any validation around EDI. (Raised as DI 50) | Updates Verified for Industry Review |  | Interim Release 1 | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-51 | DI-51 | 2023-01-30 | St Clements | 2747 | Madison Layton | Software Provider | Emailed about Refresh functionality on 14th October From: Daniel Tadecicco We have had some feedback from DNOs asking about how systems will recover from System Misalignment because of data errors or significant downtime? We have the D0204 (Supplier) and D0209 (Data Aggregator) Refresh functions today which are not being replaced with a DIP message equivalent. I am aware of the DIP Replay function, but this wouldn’t be of any help if there were data errors, as the DIP would just be replaying the incorrect data. The Source system would need to re-send the corrected data in an agreed format. I know there is a design principle to move away from bulk loads and refreshes of data, Faster Switching took a similar approach. However today, CSS leans heavily on the MPRS Refresh function to get itself back inline and there are REC CP’s being raised to add a Refresh function to CSS for all parties (first CP being R0067). DNO’s are keen to understand the MHHS Programme’s position on this, and if Refresh functionality should be built into MPRS for MHHS. SCENARIO PROVIDED: The most common scenario a refresh would be needed for is when making manual amendments (DI 56), this is needed to reflect the changes that were made back to participants (e.g Supplier, MS, DS, EES etc). Another scenario is if there’s invalid data in MPRS and a message containing this data is therefore rejected by an end participant, the message can’t just be replayed as it’ll continue to be rejected. Would need to correct the invalid data, and then the DNO/iDNO would need to manually trigger a refresh to be generated by MPRS to send the current MPAN information to that end participant. Example in context of MHHS Rule REG1022 is not removed from Interface Catalogue (DI-2) Cleansing to remove IHD Status on MPANs of non-smart segment IHD non smart MPANs aren’t fully cleansed pre go live Switch generated on an uncleansed MPAN IF-002 sent to Supplier with IHD Install status where market segment is not smart Supplier rejects PUB-002 as IHD install status populated IHD status corrected Supplier still can’t load the original IF-002 message as this contains the invalid data, so a refresh would be needed to communicate the MPAN information to Supplier It’s probably unlikely in this example the supplier applies validation on IHD status but it’s just to give an idea of the type of scenario that can happen. As Dan said in his original message, refreshes are currently heavily relied upon since faster switching go live. | Initial Assessment/Updating |  | Interim Release 3 | Refresh Functionality was rejected by the Working Groups so not in current design. Scenarios required. Go back to St Clements for specific scenarios | Other | Supporting Docs | Refresh Process?
MHHS-DIN-52 | N/A | 2023-01-30 | St Clements | 2748 | Madison Layton | Software Provider | For IF-005, REG-1006 and REG1013, would it make sense to include the installation date of the MPAN already in the system in the rejection description too to help MS with triage? | Updates Verified for Industry Review | 2023-04-27 | Interim Release 1 | Discussed with SCS potential for them to have flexibility on error messages. Industry agreement required Pariticipant Discussion Required | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 |  | Not discussed at meeting carry to next meeting
MHHS-DIN-53 | N/A | 2023-01-30 | St Clements | 2749 | Madison Layton | Software Provider | Requirement on LDSO requirements spreadsheet: MHHS-BR-LD-035 LDSO Maintain DUoS Tariff ID LDSO must set Duos Tariff ID on MPAN creation and maintain DUoS Tariff ID's in line with their Charging Method Statement. This should include updating the Duos Tariff ID, as required, following any updates to Domestic Premise Indicator, Connection Type and Energy Direction Note for MHHS, LLFC ID is being renamed as DUoS Tariff ID to make it clearer what this data item is used for. "BP010B Change of registration data" 250 However missing the respective requirement for Registration Services in the Registration Services Requirements spreadsheet | Closed |  |  | Looked through the Registration Services Requirements spreadsheet v4.6 and it looks like DUoS Tariff ID is there - MHHS-BR-RS-091.1, MHHS-BR-RS-121 and MHHS-BR-RS-122 | No Change |  |  | None
MHHS-DIN-54 | N/A | 2023-01-30 | St Clements | 2750 | Madison Layton | Software Provider | Originally raised as T4-COM-1699 on 15th Sept 2022: On the IF-031 and IF-035 there are a number of "Proposed" Data items. Should MPRS load these and updated the stored data items. Or are these data items only for passing through to Supplier and Service? SCS raised as a design blocker on 7th October 2022 We have some clarity verbally on this but nothing has been formally documented in the design artefacts. This needs to be reflected somewhere in the requirements. | Updates Verified for Industry Review |  | Interim Release 1 | Added "Appoinments - Data" section in REG Notes to highlight what data becomes effective with the appointment. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-55 | T4-COM-1738 | 2023-01-30 | St Clements | 2751 | Madison Layton | Software Provider | Originally raised as T4-COM-1738 on 15th Sept 2022: the DB02 flow updates multiple data items on the IF-018 in one event. Can multiple EventCode be included in one IF-018 or will MPRS need to generate an individual IF-018 for each EventCode? SCS received a blank response and raised as a design blocker on 7th October 2022 | Closed |  |  | Original response was that clarification was to be provided on 24th Oct - is this available? Which document? One at a time | No Change |  |  | None
MHHS-DIN-56 | T4-COM-1742 | 2023-01-30 | St Clements | 2752 | Madison Layton | Software Provider | Originally raised as T4-COM-1742 on 15th Sept 2022: BSCP604 currently allows LDSO and Suppliers to request manual corrections to Data Items held in MPRS. Will this type of Manually Correction be allowed in MHHS, if yes then this should be added to this business process to capture manual amendments and how these changes are reflected back to DIP users (IF-018 & IF-026, or a new Refresh Message?) SCS received a blank response and raised as a design blocker on 7th October 2022 Another exaple of this: If the MS/DS history is incorrect and cannot be amended via BAU, would the DNO be able to correct this via an exceptional error handling process? | Initial Assessment/Updating |  | Interim Release 3 | Original response was: This has been raised as potential consequential change utilising SDEP Nothing in design, would want updates via a flow to maintain sychronisation. Requires a change to implement, request specific data items requested - needs to be related to settlement, needs to be updated via appropriate flow. |  | MPAN Ownership | CSS Defects | MHHS-BPD005 Data Processing, MHHS-BRS005 LDSO overview
MHHS-DIN-57 | T4-COM-1748 | 2023-01-30 | St Clements | 2756 | Madison Layton | Software Provider | Originally raised as T4-COM-1748 on 15th Sept 2022: "Additional information field DI-120 is String200, where the existing DB03 allows a free text field of 2000 characters" SCS raised as a design blocker on 7th October 2022 This was corrected but then in v4.5 artefacts released there was a change back for DI-120 addition infromation field from string 2000 to string 200 in the interface catalogue data catalogue tab reintroducing the issue. For disconnection additional notes MPRS database holds 2000 characters so this field will need to be string 2000 in the IF interfaces (Raised as DI 57) | Closed |  |  | Change to the data catalogue included in the 4.7 baseline | No Change |  |  | None
MHHS-DIN-58 | T4-COM-1789 | 2023-01-30 | St Clements | 2757 | Madison Layton | Software Provider | Originally raised as T4-COM-1789 on 15th Sept 2022: "Valid combinations of data in ISD are critical to the MPRS validation development, we must have these defined and agreed before we can start development" SCS raised as a design blocker on 7th October 2022 | Initial Assessment/Updating |  | Interim Release 3 | Who is defining valid combinations of data in the ISD? Parties need to define their own data. Currently not part of a plan. |  | Supporting Docs | ISD | MHHSP-EM021 ISD Entity Map
MHHS-DIN-59 | T4-COM-1707 | 2023-01-30 | St Clements | 2758 | Madison Layton | Software Provider | Originally raised as T4-COM-1707 on 15th Sept 2022: "The Smart DS for Export and Secondary MPANs can be different to the Import/Primary DS as the Customer can choose their own DS for Export and Primary (Smart only)" The IF-031 validation rules have been amended but they are still not corrrectly reflecting the rule. The heading above both rules REG1038 and REG1039 reads: "If event type = [MSApp] OR event type [DSApp] & MPAN Segment is not 'Smart'" This heading should ONLY apply to REG1038 for linked MPANs and should not apply to REG1039 concerning related MPANs It should also have brackets to clarify the logic otherwise it could be misinterpreted e.g. "If event type = [MSApp] OR (event type [DSApp] & MPAN Segment is not 'Smart')" | Updates Verified for Industry Review |  | Interim Release 1 | This seems a valid issue. REG 1039 on linked meters should be allowed for trad meters (eg economy 7) Proposed Change: The logic issue here is that REG1039 caters for related meters, which are applicable to trad as well as smart meters. Remove REG1039 from this validation Change the validation to: "If (event type = [MSApp] OR event type [DSApp]) & MPAN Segment is not 'Smart'" Updated heading above REG1038 and added heading above REG1039 to clarify the validation rule in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-60 | T4-COM-1708 | 2023-01-30 | St Clements | 2759 | Madison Layton | Software Provider | Originally raised as T4-COM-1708 on 15th Sept 2022: "The Service Appointment Date must be equal to the SSD or there will be a period with no Service" And T4-COM-1776 also on 15th September 2022 "REG1032 - Metering Service Eff From Date [DI-830] is not contiguous - Appointment must be from [Max[Reg.MPAN_SSD] ,[Reg.ExistingMSAppFrmDate]] for a COS, it can only equal the SSD otherwise there will be a gap" This has been applied incorrectly. In IF031 rules REG1032 now reads that the MS/DS prop EFD must be = Max(SSD, existing MS/DS EFD + 1) This would restrict the MS/DS to setting the new EFD to either SSD or the day after the last MS/DS appointment, and all other dates would be rejected. It should read >= not just =. All four refrences to REG1032 in the validation rules for IF-031 references the +1 day after EFD, but the rejection description in the right hand columns for 'scneario not SEG or CoS' section does not reference this + 1. This should be corrected to be consistent with the other rules. (Raised as DI 60) | Updates Verified for Industry Review |  | Interim Release 1 | Original response to 1708: New rules added to cover all scenarios Original response to 1776: Change to be incorporated into design artefact Updated REG 1032 validation in IF-031, original single rule, split into 2 separate rules picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-61 | T4-COM-1445 | 2023-01-30 | St Clements | 2760 | Madison Layton | Software Provider | Originally raised as T4-COM-1445 on 15th Sept 2022: "There is no mechanism to update the Profile Class. We would assume that this would be updated by the Supplier (with business rules restricting when this should be set) and confirmed on the IF-026. Please can you confirm if this is the intention or if it will be updated through another route. If so, the EES would need to know which PUB would confirm the data item had been updated. " Whilst this is now included in the design the validation rules from D0205 have not been carried over, e.g. PC/SSC need to be a valid combination. ISD will need to contain the valid PC/SSC Combinations (previously MDD Entity 11) and the validation rules in the interface catalogue will need to reference this validation against the ISD valid combinations. (Raised as DI 61) | Updates Verified for Industry Review |  | Interim Release 1 | See also DIN-58, need to find out who is defining ISD validation Updated Interface notes in IF-025 to confirm that there is no Profile Class/ SSC combination checks | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-62 | DI-062 | 2023-01-30 | St Clements | 2761 | Madison Layton | Software Provider | In the business process diagram for Registration Updates MHHSP-BP010-Change of Registation Data - v4.5, the MPL update section, the C0300 has been changed to C0400 which is incorrect, C0400 is for MAP updates. Address updates are actually sent in the C0600. (Raised as DI 62) Change raised 30 March:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly. | Updates Verified for Industry Review |  | Interim Release 1 | Also in the BPD. MHHS-BR-RS-114 also confirms this should be C0300, this appears to be a straightforward typo. Amend label between Step 20 and Step 30 on BP010A to CSS0300, and update the corresponding BPD description on step 30 Update required:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly in BP010A, BPD010 and in MHHS-BR-RS-114. | Process model correction | Metering Changes | MPAN Updates | MHHSP-BP010-Change of Registration Data MHHSP-BPD010 MHHSP-BRS003
MHHS-DIN-63 | DI-063 | 2023-01-30 | St Clements | 2792 | Madison Layton | Software Provider | In the business process diag for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 (Raised as DI 63) | Closed |  |  | SCS have now confirmed that C0700 is the correct reference - no need to change documentation - agreed to close | No Change | MPAN Ownership | Disconnection | MHHSP-BP007-Disconnection MHHSP-BPD007
MHHS-DIN-64 | N/A | 2023-01-30 | St Clements | 2793 | Madison Layton | Software Provider | In business process diag for change of data service MHHSP-BP003-Change of Service- Data Service-v4.5 and MHHSP-BP002-Change of Service- Metering Service v3.5, this still makes reference to D0386 in the purple note boxes. This should now have changed to IF-019 (Raised as DI 64) | Updates Verified for Industry Review |  | Interim Release 1 | Update notes on BP002 and BP003 from D0386 to IF-019 | Process model correction | MPAN Ownership | Change of DS | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service
MHHS-DIN-65 | N/A | 2023-01-30 | St Clements | 2794 | Madison Layton | Software Provider | The business process diagram for change to connection type/market segment has been amended to name only DB01, connection type is set on DB01 but it can then be changed on DB02 (Raised as DI 65) | Updates Verified for Industry Review |  | Interim Release 1 | Update label between step 220 and 225 from "DB-001" to "DB02" | Process model correction | Metering Changes | Market Segement | MHHSP-BP011-Change of Connection Type or Mkt Segment
MHHS-DIN-66 | N/A | 2023-01-30 | St Clements | 2795 | Madison Layton | Software Provider | In interface catalogue, on IF-031, shouldn't rule REG1036 (MDR app EFD must be after DS app EFD), be applicable to all scenarios including SEG? Currently under section for if not SEG (Raised as DI 66) | Updates Verified for Industry Review |  | Interim Release 1 | Updated validation rule for REG1036 and made applicable to all scenario's in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-67 | N/A | 2023-01-30 | St Clements | 2796 | Madison Layton | Software Provider | Currently no rule on IF-031 that the SP appointment has to be within the prospective suppliers registration period - just that it can't be past dated. This rule will need to be added. (Raised as DI 67) | Closed |  |  | Reviewed with SCS and agreed that this validation is covered by existing rules. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-68 | N/A | 2023-01-30 | St Clements | 2797 | Madison Layton | Software Provider | If-031 business rule missing If the Scenario is USP, the consent granularity must be the same as the existing consent granularity held within MPRS (Updates should be through IF-025 not through IF-031) (Raised as DI 68) | Updates Verified for Industry Review |  | Interim Release 1 | picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Updated Interface notes in IF-031 to clarify that Registration Service will ignore any differences in Domestic Premise Indicator/ Consent Granularity sent on IF-031 (USP scenario) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-69 | N/A | 2023-02-02 | ESG Global | 2653 | Luke Speakes | Software Provider | PUB-033 - Block 029 is conditionally mandatory for DCC Commissioned Meters, but includes DI-025 DCC Service Flag with valid values of A-Active, I-Installed Not Commissioned, N - Non Active. The title of the block, which should define whether it is mandatory or not, is not appropriate if a DCC meter has been installed and not commissioned, or is inactive. Propose following SI and SRO design discussion that title of block 029 is revised to conditionally mandatory for 'DCC Smart Meters' | Updates Verified for Industry Review |  | Interim Release 1 | Concludes this can be resolved by a minor wording change to the block title | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 |  | Not discussed at meeting carry to next meeting
MHHS-DIN-70 | N/A | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory | Elexon is required to maintain a valid list of Meter Data Retrievers in Industry Standing Data, to allow RegService to validate that suitably qualified (DCC and SEC) MDRs are being appointed. Detail is validation of DI-839 in the IF-031 - this is not a validation rule in v4.7 of the interface catalogue. Elexon can infer valid/qualified MDRs from the SECAS list of SEC parties and DCC users, but the public list does not include detail of the role they are qualified in. Discussions with DCC and SECAS are continuing - the validation rule should be added to the catalogue | Initial Assessment/Updating |  | Interim Release 3 | The update to the interface catalogue is minor, but the implications for ISD are significant - how will it source and maintain the data relating to qualified MDRs - a role that will not be qualified under the BSC (it has been assumed that SEC/DCC accession provides sufficient assurance). Frequency of update is expected to be intermittent and infrequent, but should cover new additions and periodic removal of redundant MDRs Need to clarify where this will be captured and reported in ISD 1/3 - SCS (ticket #3034) We need valid list of MDRs in ISD for MPRS also. ISD is the only source of MPID Data for systems to load. SEC do not provide MPRS with Market Participant Domain Data. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue - probable updates to relevant BP/BPD/BRS | 2023-02-23 |  | Not discussed at meeting carry to next meeting
MHHS-DIN-71 | N/A | 2023-01-30 | St Clements | 2839 | Madison Layton | Software Provider | When would event code [MSDeAppUpdate] and [DSDeAppUpdate] be used for on an IF-037? (Raised as DI 69) | Closed |  |  | Reviewed with SCS and it is used to notify the incoming Service Providers when de-appointing and not origanally known. In case of Linked/Related MPANs individual MPANs move through the process. RS need to apply the logic for sending the updated IF-037 to all MPANs. Agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-72 | N/A | 2023-01-30 | St Clements | 2840 | Madison Layton | Software Provider | Block B018 on IF-034 and IF-035 should not be mandatory - it will only be provided for smart meters. This needs to be set to mandatory for SDS-MDRUpdate only, optional for DSAppSPResponse (Raised as DI 70) | Updates Verified for Industry Review |  | Interim Release 1 | Updated B018 block to be optional for non Smart on IF-034 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-73 | N/A | 2023-01-30 | St Clements | 2841 | Madison Layton | Software Provider | IF-026/IF-025, added new event code [SSCandProfileClass], but still kept in original [SSC] and [ProfileClass] event codes, should the original two have been removed? Particularly as the B032 group says it's madatory where event code is [SSCandProfileClass] and does not refer to [SSC] or [ProfileClass] individual event codes (Raised as DI 71) | Updates Verified for Industry Review |  | Interim Release 1 | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-74 | N/A | 2023-01-30 | St Clements | 2842 | Madison Layton | Software Provider | A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a new MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60 (Raised as DI 72) | Updates Verified for Industry Review |  | Interim Release 1 | This appears to be the reciprical change to MHHS-DIN-60 for the response interface Update description to "Check if MDR Eff Date = SSD OR on or after existing MDR Eff From + 1" Update rule to "If [DI-841] <>SSD OR <MDR Eff Date + 1" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-75 | N/A | 2023-01-30 | St Clements | 2843 | Madison Layton | Software Provider | On IF-035, overidden the description for Data Item 836 incorrectly with the description for Data Item 838 (Raised as DI 73) | Updates Verified for Industry Review |  | Interim Release 1 | Update the definition field based on the description in the data catalogue for DI-836 on IF-035 (Date From which Supplier would like Nominated MDR to take effect) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-76 | N/A | 2023-01-30 | St Clements | 2844 | Madison Layton | Software Provider | Data catalogue - changed the estimation reason code authoritative source to Registration Service, this data item is not received by, sent by or held by registration services and so the authoritative sourse cannot be Registration Service (Raised as DI 74) | Updates Verified for Industry Review |  | Interim Release 1 | The authoriative source has changed between v4.0 (from Data Service) to 4.7 (Registration Service) - have asked why the change was made, and what the authoritative source should actually be. Source updated to SDS/MDS | Data interface correction | Meter to Bank | Estimation | MHHSP-DES138-Interface Catalogue
MHHS-DIN-77 | N/A | 2023-01-30 | St Clements | 2845 | Madison Layton | Software Provider | Data catalogue - Added issue 99 items (CT Ratio, Phases etc) DI-170 - DI-180. Was agreed in work off meeting these items are not within the scope of MHHS, to introduce these would require a CR (Raised as DI 75) | Updates Verified for Industry Review |  | Interim Release 1 | these data items don't appear to be used in any interfaces so this could be a relatively simple change to remove 11 items from the data catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-78 | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier | MHHS-E2E002 Requirements v2.2 - E2E0404 requirement is blank - row needs to be deleted | Closed |  |  | This update was already incorporated into version 5.0 closing it here | No Change | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-79 | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier | MHHS-E2E002 Requirements v2.2 - E2E21114 typo - should be VAS Output Retention | Updates Verified for Industry Review |  | Interim Release 1 | change as per description | Technical corrrection | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-80 | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier | MHHSP-DES138-Interface Catalogue v4.6 - DI-846 Issuing Data Service EZ Name should be scored through in IF/ PUB21 definition | Closed |  |  | Completed in V5.0, part can review change as part of Interim Release 2 | No Change | Meter to Bank | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-81 | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier | MHHSP - BP020 - Volume Allocation Service (ECS) v4.6 - Step 75 to Step 80 references report “REP-00” - needs correcting | Ready for Internal Review |  | Interim Release 2 | BP020 step 75 to step 80 process flow REP list correction BPD020 step 75 & step 80 detail list of REP's correction | Process Model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions
MHHS-DIN-82 | N/A | 2023-02-09 | SI Design | 2716 | Rob Short | SI Design | Related to DIN-81 - BPD002 lists number of reports at step 75, BP002 does not reflect this list, missing PO275, PO214 and PO213 | Ready for Internal Review |  | Interim Release 2 | This relates to BP020 (not BP002), similar to DIN81, reconcile REP list correction on BP020 at step 75 and 80 and reconcile with BPD020 list of REPs | Process model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions
MHHS-DIN-83 | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | A discrepancy with the Interface Catalogue - IF_LIST states MHHSP-IF-044 is sent to Central Settlements, DS, MS, Supplier, LDSO. IF-044 tab states it is sent to Supplier, MDS, LDSO In BP011 the PUB-044 is not sent to DS only Supplier, Settlements and EES | Ready for Internal Review |  | Interim Release 2 | Add Manage change of segement in LDSO lane on business process BP011C with a PUB-044 flow from step 570 Add new step to BPD011 Interface catalogue is already updated | Process Model correction | Metering Changes | Interface Catalogue | MHHSP-BP011 Change of ConType andor Mkt Segment MHHSP-BPD011 MHHSP-DES138-Interface Catalogue
MHHS-DIN-84 | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | IF_LIST states MHHSP-IF-020 is sent to Supplier onlyIF-020 states it is sent to Supplier, Data Service, Metering Service, LDSOIn BP010, the PUB-020 is sent to Central Settlements, CSS, EES, Supplier, Data Service, Metering Service, LDSO.This one looks like its just the Interface Catalogue that needs updating. IF-020 Updated to refect new agreed Routing | Ready for Internal Review |  | Interim Release 2 | Updated parties receiving PUB-020 in the IF_LIST, updated PUB-020 routing to include MDS for Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-85 |  | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory | Elexon see DIP qualification for new users being part of market entry post-programme, but want to understand how MHHSP will operate qualification during the programme. This is likely to cover the majority of participants. Discussions with SRO colleagues indicate they are assuming this is a process for the Enduring Service Operator to define. Challenge applies to non-BSC DIP participants (e.g. adaptor providers), and considerations under Issue Group 101. SI design has spoken to at least 4 participants who are operating in this space and seeking to understand how they can engage with SIT and other programme activities as a DIP connection provider (E2E Architecture - 3.3.2) | Closed |  |  | To be handled as part of the Placing Reliance document | No Change | Qualification | Qualification | New Process - DIP Qualification for New Users
MHHS-DIN-86 |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory | Invalid Market Segment BP011C requires SMRS to notify the Supplier of an invalid market segment. RegService requirement RS0124 states that SMRS must derive a value for Market Segment based on Connection Type and Meter Type following a Change of Metering, Change of Connection Type (Change of Unmetered Indicator) or Change of Related MPAN relationships. Given that SMRS determines segment as above, when would an invalid market segment occur, giving rise to the processes from step 560 in BP011C? Further, upon receipt of a PUB-045 Market Segment Invalid Advisory Notification, what are the next steps for a Supplier to address the issue? There are no provisions in the IF-025 for Suppliers to update Market Segment. | Initial Assessment/Updating |  | Interim Release 3 | Part of ongoing discussions with Code Drafting team 20/4//23 Code Drafting believe an update needs to be made to the design to update Market Segment via IF-25. This could occur when a Supplier is trying to arrange a change of segment but one of the activities has not completed on time eg the new metering has not been notified. When Registration Service tries to evaluate the segment it may not be compatible. Notification would then go to Supplier to prompt them to chase the required update, in this example chasing the Metering Service to provide the new metering details. Another example is if the LDSO has not notified a change of connection type. The Supplier may also need to send a further SEG appointment if the original has lapsed. | No Change | Metering Changes | Change of Connection Type and/or Market Segment | MHHSP-BP011, MHHSP-BPD011
MHHS-DIN-87 |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory | Energisation Process Clarification BP009 states that change of energisation status at the same time as meter works means that BP008 will be followed - what is the process when a meter removal and de-energisation are carried out in the same job? Are both D0139 (de-energise) and D0142 (remove meter) and relevant DIP interfaces required. At the moment MEMs only have to send flows relating to meter removal | Initial Assessment/Updating |  | Interim Release 3 | Part of ongoing discussions with Code Drafting team Under MHHS design this is two separate events that would require both IF005 and IF007 being sent by the Metering Service ( even if carried out as one job ) Agreed at meeting with SJ on Mo 27th Mar that we would add new Purple Boxes to BP009 and BO008 to make it clear that Remove/DeEn could still be requested and carried out but MS would need to send two interfaces. ALso that DeEn did not need to be notified if meter works completed within same day (ie same rules as today) | Process model correction | Metering Changes | Change of Metering | MHHSP-BP009, MHHSP-BPD009
MHHS-DIN-88 |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory | Update to Incumbent MS provider for Lapsed Appointments Currently BP002 only addresses the positive confirmation of de-appointment from RegService (PUB-037 - step 140/231), but if there is no secured active, there is no subsequent notification to the incumbent. The prospective MS receives a PUB-035 at step 225. How should the incumbent MS determine when the de-appointment has lapsed? | Initial Assessment/Updating |  | Interim Release 3 | Part of ongoing discussions with Code Drafting team why would the incumbant share the MTD via the IF-035 as early sight. IF-37 is the deappoint they code need to reflect . The Metering Service is appointed until they get de-appointed using a PUB-037. They are only receiving the PUB-035 as notification of who to send MTDs to, it is not intended as a notification of de-appointment. SC= Incumbent Metering Service is a term used to refer to the MS appointed at the point another new SP Appointment is accepted (MS or DS), it shall be the Incumbent Metering Service's responsibility to share MTDs (ADV/Trad) to the incoming party. No change recommend CLOSE |  | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Metering Service MHHSP-BPD002
MHHS-DIN-89 |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory | Customer Details on De-Appointment The MHHS design currently allows for customer data to be deleted or obfuscated by MS on de-appointment. Has obfuscation been confirmed as acceptable under GDPR? | Initial Assessment/Updating |  | Interim Release 3 | Part of ongoing discussions with Code Drafting team PP 14/2- PP to check with Ian / Smitha |  | All Areas
MHHS-DIN-90 |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory | MS Appointment for Associated Export Metering Points How will an initial MEM be appointed for a new export MPAN, created post MHHS go live? | Initial Assessment/Updating |  | Interim Release 3 | Part of ongoing discussions with Code Drafting team to have a look at the process that Mpans are in the correct group The daily process monitoring (BP011C) would pick up any linked Export MPANs and ensure that the same Metering Service is appointed as the Import MPAN. If the Export MPAN is not linked, then the BAU appointment process can be followed. |  | Metering Changes | Change of Connection Type / Market Segment | MHHSP-BP011, MHHSP-BPD011
MHHS-DIN-91 | N/A | 2023-02-10 | AWS | 2858 | Duncan Parsons | Software Provider | Document MHHS-E2E001 section 3.6 Actor Workflows Summary - Typo in the MSA Outbound. States IF-04, this should be IF-041 | Updates Verified for Industry Review |  | Interim Release 1 | Reference Corrected | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-92 |  | 2023-02-14 | RECCo | 2903, 2805, 2911 | Sarah Jones | Regulatory | Customer Direct Contract Flag (D053) Multiple tickets - RECCo, ESG and National Grid - all highlighting the same problem. The 4.7 artefacts do not consistently reflect the agreed position that the Customer Direct Contract flag can only be set by the incumbent Metering Service provider. The validation rules on the IF-038 should be updated The requirements for MS (013) and DS (34) in the respective BRS artefacts should be aligned | Updates Verified for Industry Review |  | Interim Release 1 | Added validation rule REG1075 to IF-038 in the interface catalogue Updated requirements in MS-013 and DS-034 in BRS to reflect the agreed position for D053 1/3 - ticket #3035 - SCS supportive of this change, need more detail. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue, BRS001, BRS002 | 2023-02-23 |  | Accepted but split these into two DINs one of the updates to the BRS and deal with as a minor chnge, the other as a major for the Interface Specification change
MHHS-DIN-93 | N/A | 2023-02-14 | Power Data Associates |  | Tom | Consultancy | Work off Plan D-034D updates for exceptions to Unmetered Supplies | Ready for Internal Review |  | Interim Release 2 | 1. Section 2.3 of MHHSP-METH004-UMSDS- EM Functions will be updated to make explicit that the following data items are not required by the UMSDS and as such will be ignored. • Consent Granularity (T4-COM-1857) • Domestic/Non-domestic Indicator (T4-COM-1830/1850) • Distributer Id (T4-COM-1826/1842/1845/1858/1859/1864/1865/1871/1875) • DUoS (T4-COM-1856) • LLF Data (T4-COM-1856) • Domestic Premise Indicator (T4-COM-1830/1850) • Metered Indicator- (D-045) 2. MHHSP-METH001- SDS Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 3. MHHSP-METH002- ADS- Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 4. MHHSP-METH009- UMSO Method Statement should be updated to make explicit that the following data items are not required by the UMSO and should be ignored (list to be reviewed and validated). • Consent Granularity • Domestic/Non-domestic Indicator • Distributor Id • DUoS • LLF Data • Domestic Premise Indicator • Metered Indicator | Method statement correction |  |  | MHHSP-METH004-UMSDS MHHSP-METH001- SDS MHHSP-METH002- ADS MHHSP-METH009 - UMSO | 2023-02-23 | 23/2/23 - Accepted
MHHS-DIN-94 |  | 2023-02-16 | ESG | 2777 | Patricia | Software Provider | The IF_009 has 2 event codes: [MPANDisconnection] & [CSSDeRegistration]. [CSSDeRegistration] is listed as having Supplier as Secondary routing however on BP007 there is only reference to the supplier receiving the [MPANDisconnection] flavour of the flow. Please can you clarify which artefact is accurate. MHHSP – BPD009 step 145 states Where the Registration Service has rejected the metering update the DIP will publish the rejection to metering services. Supplier have the option to subscribe to this also. Your response was:- Our reading of this is that regservice will reject the PUB-006 back to sender if the IF-005 fails those rules. So just back to sender, not always meter service or supplier Therefore, does the BPD009 step 145 need to be updated to reflect that as the IF005 can only be generated by Metering Service Smart (MSS) & Metering Service Advanced (MSA) not the Supplier | Ready for Internal Review |  | Interim Release 2 | Question 1. Supplier will receive both events as outlined in BP007 (See DIN 294) Question 2. BPD009 step 145 updated to show that Supplier cannot choose to receive rejections | Process Model correction | Metering Changes | Disconnection / Change of Metering | MHHSP-BP007-Disconnection MHHSP-BP009 – Change of Metering (Install / Remove / Exchange) MHHSP-DES138-Interface Catalogue
MHHS-DIN-95 |  | 2023-02-20 | SI Design | NA | Simon Harrison | Programme | Typo in the Note box about Auto Alignment of Related/Linked MPANs on the BP002 and BP003 process maps. Change 'Regisatration' to 'Registration' | Updates Verified for Industry Review |  | Interim Release 1 | Update BP002 (& BP003) call out box | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service
MHHS-DIN-96 |  | 2023-02-21 | SI Design | 2973 | Arif Jagot | Programme | Test-078 - SUPPI -Primary - Means SUPI? | Updates Verified for Industry Review |  | Interim Release 1 | Update Interface Catalogue | Data interface correction | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-97 |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Typo in MHHS-METH001-5.4c "and less than 90 days months different from the UTC Date" - propose removal of months | Ready for Internal Review |  | Interim Release 2 | Update Method Statement i.e This needs to be 90 days not 90 months the artefact needs to be updated | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-98 |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Typo in MHHS-METH001 - 5.5 SDS shall use the most recent data a based on the event that triggered the | Ready for Internal Review |  | Interim Release 2 | Typo error on clause 5.5 within MHHSP-METH001-SDS Validation Estimation v5.0 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-99 |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Clarify that Step 105 in the CoS Transfer read process is Working Days. Currently states 5 days | Ready for Internal Review |  | Interim Release 2 | Checked with SRO - 5 Working days for Step 105 in process, BPD003C, BR-DS-024.1 and BR-DS-024.2 | Requirement correction | MPAN Ownership | Data Services | MHHSP-BRS001 - SDS Requirements MHHSP-BP003C - Transfer of Reads MHHSP-BPD003C - Transfer of Reads
MHHS-DIN-100 |  | 2023-02-21 | RECCo | NA | Sarah Jones | Regulatory | Step 180 in BP002 and BPD002 does not include LDSO as recipient of traditional meter details as per the wording of the step or the BRS (BR-MS-024) (Code Drafting Log Reference CDD-29) | Ready for Internal Review |  | Interim Release 2 | Update BP & BPD to align with BRS and add LDSO as recipient of MTDs | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Metering Service MHHSP-BPD002
MHHS-DIN-101 | DI-120 | 2023-02-22 | St Clements | 2930 | Madison Layton | Software Provider | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. (Raised as DI 120) | Closed |  |  | Included within CSS validation rule update. DUPLICATE See DIN-172 | No Change | MPAN Ownership |  | MHHS-DES138-Interface Catalogue
MHHS-DIN-102 |  | 2023-02-22 | St Clements | 2886 | Madison Layton | Software Provider | SCS raised the following under MHHS-DIN-7 "MPRS will reject any PUB-031 inlcuding those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist"" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8)" They have followed up with: Just found the change that corresponds to this one in v4.7 interface catalogue – REG0005 in IF-031. Could this also be added to IF-034 so that we can apply the same validation on MDR updates? | Closed |  |  | Proposed Change: Add validation "CSS Registration Request ID [DI-849] is valid for Registration Service", with error REG0005 - "CSS Registration Request ID [DI-849] is invalid or unknown" This mirrors a change made in v4.7 to IF-031, agreed as part of the DAG baseline of v4.7 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-103 |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Confirm that D0381 will continue to be used for updates to MPL address. BP010 & BPD010 currently allow emails, SDEP and other agreed forms can be used by Supplier or UMSO to update this - propose that these artefacts are amended to reflect that the D0381 is to be retained (Code Drafting Log Reference CDD-22) | Updates Verified for Industry Review |  | Interim Release 1 | Amend Steps 10, 21, 22 to explicitly use the D0381 rather than current wording | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-104 |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Impact of MHHS on SoLR arrangements - possibly needs an Issue Resolution Group discussion to undertake evaluation & impact assessment (Code Drafting Log Reference CDD-23) | Requires Industry Work Group review | 2023-06-15 | Interim Release 3 | Feels like DA needs to consider how to undertake an evaluation of the MHHS change impact on SoLR arrangements |  | All Areas
MHHS-DIN-105 |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Related MPAN Business Rules 1) IF-019 suggests RMP status can be Created or Operational - proposed this can only be Operational for subsidiary MPAN 2) Add validation rule to IF-019 requiring related MPANs to have consistent classification as domestic or non-domestic (reflecting the existing requirements) 3) Clarify what Registration Services should do when MPANs are related/linked and have different MS/MEM providers - is the IF-019 rejected or the MEM for the secondary MEM auto-deappointed? 4) What happens if the IF-019 fails validation by Reg Service at Step 330 in BP010? Design provides no guidance | Ready for Internal Review |  | Interim Release 2 | 1. Removed reference to Created in the REG1001 validation rule for IF-019 2. We understand there is no existing validation within MPRS and this is not being amended as a result of MHHS implementation. This would require a wider industry change impacting CSS as Domestic Premise Indicator is managed independently of Related MPANs. 3. It would not be rejected, auto-alignment would pick up the discrepancy at the next daily run and de-appoint the export MS and appoint the import MS. 4. As with other rejected flows, the sending party should investigate the error and re-submit as appropriate. | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data BPD010 MHHSP-DES138-Interface Catalogue
MHHS-DIN-106 |  | 2023-02-23 | SI Design | 2955 | Kate Goodman | Testing | Inconsistency in DES138 for UMSO Routing 00-Introduction logs UMSO as the single routing option for Unmetered Service provision, as there can only be one UMSO related to an MPAN PUB-008 provides UMSC, UMSP and UMSI as options for secondary routing This inconsitency needs to be corrected | Ready for Internal Review |  | Interim Release 2 | Secondary routing rules updated following review with Avanade |  | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-107 |  | 2023-02-24 | SI Design |  | Simon Harrison | Progamme | Definition of DI-301 in DES138 is incorrect - it should reflect the D0265 value for LLF ID, at the moment it has the same definition as DI-497 Line Loss Factor | Initial Assessment/Updating |  | Interim Release 2 | Confirmed as an error with Kevin in SRO. Only appears in Reporting Data Catalogue DI-307 LLF ID should read as 'The Unique Identifier of a set of Line Loss Factors' |  | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-108 |  | 2023-02-27 | SI Design | 2966 | Kate Goodman | Testing | Ref:MHHSP-DES138-Interface Catalogue v4.7, IF-038, PUB-020, PUB-039. Document says that UM is relevant to these messages but UM thinks it is not relevant. Please clarify what the situation is. Raised in review of MHHSP-872 by Power Data. | Ready for Internal Review |  | Interim Release 2 | Covered by Secondary routing updates |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-109 |  | 2023-02-27 | SI Design |  | Simon Harrison | Programme | Call out box in BP002/BP003 on Linked/Related MPANs needs to be updated as it includes reference to email/SDEP rather IF-019 as shown in BP010 | Closed |  |  | Confirmed - the call out box on BP002/003 needs to be updated Duplicate of DIN-64 | No Change | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service
MHHS-DIN-110 |  | 2023-02-27 | SI Design | 2983 | Kate Goodman | Testing | MHHSP-BP005-Data Processing-v4.6, Step 50-160 UMSDS is referencing Submit Required UTC period level consumption data (Step 50) with a arrow going to Receive UTC period level consumption data (Step 160) but no reference of IF-021 on the connection between both - reference should be added? | Updates Verified for Industry Review |  | Interim Release 1 | On Process map requires arrow to be labelled as IF-021 from step 50 to step 160 | Process model correction | Meter to Bank | Data Processing | MHHSP-BP005-Data Processing
MHHS-DIN-111 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | Originally raised as T4-COM-1691 on 15th Sept 2022: "MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days " Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5 (Raised as DI-76) | Updates Verified for Industry Review |  | Interim Release 1 | Updated to 2 working days | Requirement correction | MPAN Ownership |  | MHHS-BRS003-Registration Service requirements
MHHS-DIN-112 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54 (Raised as DI-77) | Updates Verified for Industry Review |  | Interim Release 1 | Added note to clarify | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-113 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? (Raised as DI-78) | Closed |  |  | Agreed duplicate of DIN-29 and can clsoe | No Change
MHHS-DIN-114 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | EES does not appear to have been added to the routing rules tables on the interface tabs(Raised as DI-79) | Closed |  |  | Already present in v5 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-115 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | On IF-050, this includes linked MPANs in it, but I don’t think these would ever be populated as you cannot link MPAN at MPAN creation. So EES would only ever get Linkage updates on the IF-20 Is there any value of having this therefore in IF-050?(Raised as DI-80) | Updates Verified for Industry Review |  | Interim Release 1 | Removed Linked MPANs and Related MPANs from IF-050 and added explanatory note | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-116 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | For IF-025, block B032 it states it is "MPAN Legacy Info (Mandatory where event is [SSCandProfileClass], and for Traditional Meters / Optional for other Meters)" It should just read mandtory for event code [SSCandProfileClass] and nothing else, it should not be optional for any of the other event codes(Raised as DI-81) | Updates Verified for Industry Review |  | Interim Release 1 | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-117 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?(Raised as DI-82) | Closed |  |  | Discussed with SCS and confirmed it is a limitation of swagger output but should be array of MPAN followed by array of meters followed by array of MAPs repeated per MPAN. Awaiting confirmation can close | No Change | Metering Changes | IF-005 JSON | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-118 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | In relation to the Sender Unique Reference, which is constructed as: S-<Interface>-<Participant Id>-<Role Id>-<Date>-<Sequence> (hex) I would like to comment as follows: • Why is the Unique Reference simply constructed using elements that are already contained in the message as distinct values? This just means the sender has to construct it and the receiver de-construct it? • Is the sequence number expected to be reset each day ? • It would be much easier and more logical for the Sequence to be a distinct item in the message? • Why is the sequence specified as hex? • Even given the expected large number of messages, and based on it being a number(13) (defined as Sting), a standard sequence number per Participant and Role would provide 9,999,999,999,999. If this is still seen as a limitation then it could simply be built from the date, e.g. 202301190000000001, giving a provision for up to 9,999,999,999 messages PER DAY from the same Participant / Role combination, which still enables a read every 30 minutes from every MPAN(Raised as DI-83) | Closed |  | Interim Release 2 | This is to send a unique reference and is used for auditing purposes. Please note the length of the Sender Unique Reference has been increased at the request of Avanade in 5.1.1. Examples updated |  | MPAN Ownership
MHHS-DIN-119 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | in swagger hub under IF-002 B907 list the B036 block, this is missing numberOfDigitsCumulativeRegister data item(Raised as DI-84) | Updates Verified for Industry Review |  | Interim Release 1 | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue. Swagger will be updated | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-120 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | Inconsistency in naming of data item DI-091 In swagger hub: Number-Of-Digits-Cumulative-Register In interface catalogue IF tabs (E.g. IF-002) : Number of Displayed Register Digits In interface catalogue data catalogue tab: Number Of Displayed Register Digits (Cumulative Register)(Raised as DI-85) | Updates Verified for Industry Review |  | Interim Release 1 | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue and updated YAML accordingly | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-121 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | WOA-0093 comment raised on 12/01/2023 " D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: "It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42 (Raised as DI-86) | Updates Verified for Industry Review |  | Interim Release 1 | Agreed to provide SEG scenario's in IF-005 Use Case guide. currently under review |  | Metering Changes | Change of Segment | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-122 | DI-87 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | WOA-0084 comment raised on 12/01/2023 following the introduction of IF-019 and respective changes in the latest set of released artefacts MHHSP-BP010-Change of Registration Data -v4.5 "Shows Supplier Mastering Import Export Linkage. BSC CP1558 introduced changes to MPRS for the LDSO to manage this via the DB05. IF-019 should go to LDSO who should then produce a DB05 into MPRS." The process diagrams and requirement spreadsheets have been amended to show MPRS loading DB05 as a IF-019 response. DB05 is not a IF-019 response, it is a request from DNO/iDNO to create, amend or remove a import/export linkage. It does not currently have any capacity to include a IF-019 rejection response to trigger a IF-020 rejection response to DIP. (Raised as DI-87) | Updates Verified for Industry Review |  | Interim Release 1 | SCS reviewing preferred option with LDSO's The following changes would be required to the LDSO overview requirements: MHHS-BR-LD-043.3 LDSO Send Import/Export relationship update LDSO must send accepted Import/Export relationship updates to the Registration Service via the appropriate interface DB05 file or other agreed mechanism BP010B Change of registration data 900 MHHS-BR-LD-043.4 LDSO Send Import/Export relationship rejection LDSO must publish rejected Import/Export relationship updates on the Data Integration Platform using the appropriate interface MHHS-IF-020 to Supplier BP010B Change of registration data 900 On BP-010 for Linked Import/Export MPANs the following would be required: 1. Need to add rejected leg from step 900 to DIP 2. Need to add PUB-020 going from the DIP to the Supplier The BPD-010 will need updating accordingly. | Process Model correction | MPAN Ownership |  | MHHSP-BP010-Change of Registration Data MHHSP-BPD010, MHHSP-BRS005, Traceability Matrix
MHHS-DIN-123 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | WOA-0083 comment raised on 12/01/2023 following the introduction of a new business rule on MPRS in the latest set of released artefacts MHHS-BR-RS-078 "MPRS cannot control how messages are sequenced at CSS and DSP. IF MPRS waits until the DSP responds before sending the Appointment message this could take hours (as this is a batch process) this will result in a delay in the appointment of the MDR. Sequencing requirements should be placed on CSS & DSP to ensure the correct MDR is appointed based on Effective dates provided from MPRS. However, they may not be necessary due to the way this interface works: The C0200 interface uses the PUT Method, which will replace the data held at CSS. Explicit ending of an Appointment is only required for a future dated appointment, this will be sent as one message with the Old and New MDR appointments. For Same Day or Retrospective the new MDR Appointment will Replace the currently set value. This implicitly ends the previous MDR Appointment. On a CoS, the MDR is linked to a Registration not a Metering Point. The previous MDR will end naturally when the Previous Registration becomes securedInactive. An explicit message to end the MDR appointment on the Previous Registration is not required . MPRS will only send two separate updates to CSS when there is a gap in MDR (SDS) appointments. For Example a change of segment to Advanced and then back to Smart. This would need to happen over a short period to generate two messages that could go out of sequence" The MHHS design team rejected with comment "The MHHS design is based upon what was agreed as part of the R044 consultation. This scenario does not reflect our understanding of how the CSS/DCC/DSP interface will work as set out under R044. " This is how C0200 currently works today and the interface is unchanged in R0044. This will put a signfiicant requirement on MPRS that will reduce time available time for other core MHHS development activities with no benefit to industry.(Raised as DI-87) | Closed |  |  | No Change - updated in v5.0 | No Change | MPAN Ownership
MHHS-DIN-124 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | WOA-0089 comment raised on 12/01/2023 "D-021 was meant to give more detail on how L1-L4 validation should be used and provide more error codes for use. This has not been done as far as I can see Blocking resolution to this T4-COM-1749, T4-COM-1769 and T4-COM-1768" Comment was closed as clarified however none of these items have been resolved and we have no dates as to when they will be. comments blocked that were raised initially on 15/09/22 Comment T4-COM-1749: "The Registration Service, as part of its L3/L4 validation should ensure that there is consistency between the data content of the IF-033 issued to the Service Provider and the [returned] content in IF-034 - if this isn't so then message should be returned to Service Provider using ""MSGStatus Message"" mechanism." Does MPRS only need to validate consistency in the data it loads on the IF-033, not the data that is not loaded" Comment T4-COM-1769: "We need validation rules to be defined for this flow, Does not match IF-031, content of the PUB-034 does not match the IF-031. No Proposed Appointment Found, PUB-034, does not link to any Pending IF031s. Define Validation Rules for PUB-034 The 034 content must match the original if-031 content the 034 must have a corresponding IF031 the 034 has already been received for the IF-031 Generic Standard Validation, MPAN exists valid in ISD ETC" Comment T4-COM-2768: "We need some generic codes for standard validation rules such as: Service/Supplier is valid in ISD MPAN exists in MPRS MPAN is not Disconnected Service/Supplier is Valid in MDD (so CSS doesn’t reject updates)" (Raised as DI-89) | Updates Verified for Industry Review |  | Interim Release 1 | Added RMP status check to IF-034 and refined validation rule notes regarding different values received from IF-033 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-125 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | WOA-0091 comment raised on 12/01/23 D-030 "how routing will work in the DIP has not been updated this information is required for our development" MHHS Design Team has closed as clarified however there is still uncertainty around the DIP routing, and there are not dates provided for when the detailed DIP design will be released. This will clock certain elements of development (Raised as DI-90) | Ready for Internal Review |  | Interim Release 2 | Secondary routing rules updated following review with Avanade |  | MPAN Ownership
MHHS-DIN-126 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | WOA-0092 comment raised on 12/01/23 following more infromation around D-022 being clarified "D-022 Following the work off item being agreed on what is required for an MPAN to be traded - it has now been possible to fully assess the optionality of data items in the interfaces Data items still mandatory in interfaces that must be changed to optional: Annual Consumption (IF-001) Incumbent Service Providers (IF-002, IF-033) Incoming MS/DS (IF-037) These are not required at creation, nor at traded, and therefore could be non existent in MPRS when MPRS generates this outgoing IF messages Blocking resolution of T4-COM-1727 and T4-COM-1735" Closed as clarified however none of the issues listed have been resolved Annual consumption still reads madatory on a CoS for IF-001, the issue is MPRS may not have this data item. The item is not required to reach a status of traded, therefore CSS will accept a CoS on this MPAN without annual consumption being populated, and then MPRS will not be able to provide this data item on the IF-001 that results from the CoS. This must be changed to optional OR the definition on what is needed to be traded should be updated to include annual consumption. Incumbent Service Providers is still mandatory on IF-002 for CoS Again as MS is not required to be traded, CSS will accept a CoS request with or without a current MS, and so MPRS will not be able to provide an incumbent MS in these cases. It must be changed to optional or the definition of what is needed to be traded should include MS. Incoming MS/DS is still mandatory on IF-037, there are numerous reasons an appointment may be lapsed, the only change that would gaurantee a new incoming SP that MPRS could send on this flow is a change or SP (CSERV) scenario. For CoS the supplier may not have sent in new appointments, for DEREG there will be no new appoitnments, for SEG the market segment may have changed but the supplier may not have sent in new appointments, same for change of connection type, and for IMPEXP and RELATED the parent MPAN might not have MS/DS appointed at all so there would be no new appointments for MPRS to populate on this flow. This must be changed to madatory ONLY on CSERV (Raised as DI-91) | Updates Verified for Industry Review |  | Interim Release 1 | Discussed with SCS. Covered by clarification on nullable and interface notes- All these issues are resolved by the Mandatory Nullable Solution. Confirmed Annual Consumption block will only be provided where available in Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-127 |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 "DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least "Registered", if no DS is appointed then there is already an appropriate Event Code" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone (Raised as DI-92) | Closed |  |  | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-128 | DI-93 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | Raised as WOA-0095 comment on 12/01/23 "D-009 This is blocking closure of T4-COM-1730. There is a lack of clarity around the treatment of rejection from CSS, between both R044 and the MHHS design artefacts e.g. MHHs-BR-RS-088.1 and MHHS-BR-RS-079 both suggest MPRS would still load the new MDR record and appoint in MPRS despite a rejection from DCC/CSS. Our assumption would be that we do not load a MDR appointment that is rejected from DCC/CSS and we send the IF-035 rejection to notify the DS/Supply of this. However no clarity on what to do if DCC/CSS rejects a MDR end date on a de-appointment T4-COM-1730 was raiseed on 15/09/22 MHHS Design Team Rejected the comment with a statement this is outside of MHHS Scope. How MPRS treats the MS/DS appointment and how it responds over hte DIP is within MHHS design. The requirements we are enquiring about are already included in the MHHS design documents as in scope also. This is a major blocker to MPRS design on MDR appointment processes (Raised as DI-93) | Closed |  |  | Discussed with SCS this is a REC requirement. Agreed no error codes will be received, just use a generic response. | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-129 | DI-94 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | Raised as WOA-0086 comment on 12/01/23 following the release of the first draft of IF-050 in the revised interface catalogue artefact "Related MPANs and Linked Import Export are not set at MPAN Creation. EES can get these on the IF020 Remove these blocks from IF-050 as they would never be populated" MHHS design team marked as accepted and changed but the blocks still exist in IF-050, these blocks will never be populated and so should be removed from the IF-050 interface(Raised as DI-94) | Closed |  |  | Closed - duplicate of DIN-115 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-130 | DI-95 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | Raised as WOA-0088 on 12/01/23 "D-011 & D-050 it is still unclear how LLFC and DUoS Tariff ID will be stored and managed in MPRS. DUoS should be an Alias of LLFC and not have its own data item in MPRS. LLFC will be renamed to DUoS Tariff when the old arrangements have ended. LDSO impacts having to maintain two items which will lead to billing issues" Marked as clarified and closed witih a clarification statement to be issued on tuesday 24th January, this clarification statement was not received. Awaiting clarification(Raised as DI-95) | Closed |  | Interim Release 2 | Email to Madison to check can close |  | MPAN Ownership
MHHS-DIN-131 | DI-96 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | IF-025 is missing business rules: REG1001 - MPAN [DI-063] is at [REG.RMPStatus] not status Created/Operational. This should apply to IF-025. IF-025 is missing a rule that consent granualiry EFD must not be earlier than supply start date. Consent Granularity EFD must not be prior to current consent granularity EFD The Consent Granularity Energy Direction Domestic Premise Indicator Combination must be valid in ISD(Raised as DI-96) | Updates Verified for Industry Review |  | Interim Release 1 | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-132 | DI-97 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | IF-025 IHD update does not include validation rule 1019, does this mean IHD EFD can be prior to current and effectively cancel out the current IHD status completely, or is it just an error and the rule should be added to interface catalogue for IHD?(Raised as DI-97) | Updates Verified for Industry Review |  | Interim Release 1 | Amendment accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-133 | DI-98 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | IF-025 will not allow a SMSO to be set for a non smart meter "REG1022 - SMSO ID Cannot be set where Market Segment is [Reg.Segement]", would a non smart supplier be able to send a B031 SMSO block, they will need to be able to if they are required to clear an old SMSO by populating SMSO as null(Raised as DI-98) | Updates Verified for Industry Review |  | Interim Release 1 | Added new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements | 2023-03-23
MHHS-DIN-134 | DI-99 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | IF-025 "SSC must be valid in ISD. Rejection reason: REG1044 - SSC must be a valid value in ISD" SSC are not yet populated in ISD(Raised as DI-99) | Closed |  |  | Clarified that SSC validation will be based on Frozen MDD. Seperate DIN to cover availability of ISD | No Change | MPAN Ownership |  | MHHSP-EM021 ISD Entity Data Map, MHHSP-DES138-Interface Catalogue
MHHS-DIN-135 | DI-100 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | Should B032 PC and SSC block on IF-025 only be permitted when theres a traditional meter fitted at the MPAN?(Raised as DI-100) | Closed |  |  | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-136 | DI-101 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | How is the Green Deal Exists defined. Does this mean there's a green deal linked to the MPAN regardless of dates, does it mean there's a green deal currently active or due to become active, or does it mean there is a currently active green deal assigned to the MPAN? (Raised as DI-101) | Updates Verified for Industry Review |  | Interim Release 1 | Remove Green Deal exists (DI-110) from Data Catalogue and IF-050 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-137 | DI-102 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | IF-007 Validation rule "Metering Service [S0.SenderID] holds valid previous appointment then Energisation Status EffectiveFrom Date [DI-034] should be < [REG.App End Date] + 10" The way it's curently written suggests MPRS should accept an IF-007 from the previous appointed MS, event if there ETD was greater than 10 days ago, provided the ES EFD date was less than their ETD + 10. E.g the previous MS could send IF-007 two years later with ES EFD of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then a separate rule should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? Linked to DI-41(Raised as DI-102) | Updates Verified for Industry Review |  | Interim Release 1 | REG1003 validation rule updated in IF-007 to constrain energisation updates to 10 days after the MS appointment period |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-138 | DI-103 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider | IF-034 Submitted rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD | Closed |  |  | Duplicate of DIN-176 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-139 | DI-104 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider | Need clarity on what role code should be used in C0200 for MS and MDR appointments Linked to comment T4-COM-1790 which was accepted as design issue raised but then moved to a work off item "We would like to see some indicative Role Codes and DIP IDs so we can populate development systems with this data " | Closed |  |  | Send "MDR" as role code as per Registration requirement. Allocation of DTN MPIDs is a seperate issue | No Change | Registration | Existing EMAR I/F | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-140 | DI-105 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider | Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 | Closed |  |  | Discussed with SCS the IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR. Agreed to close | No Change |  |  | MHHSP-BP003A, MHHSP-BRS003 Registration service requirements
MHHS-DIN-141 | DI-106 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 | Closed |  |  | RECCo consequential change | No Change |  |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-142 | DI-107 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider | There currently aren't sufficient rules to ensure that a principal primary MPAN is not also a linked export subsidiary MPAN or that a subsidiary secondary MPAN is not also a principal import linked MPAN. The MHHS design either should accommodate both (would need clarity on how to treat cases where MPANs are BOTH principal and subsidiary) OR new rules should be introduced to prevent this occuring AND cleanse existing cases ahead of migration | Updates Verified for Industry Review |  | Interim Release 1 | Validation rules updated for IF-019 | Missing/incorrect validation rule | MPAN Ownership |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-143 | DI-108 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider | Requirements were uplifted in v4.5 to include logic around market segment on related MPANs MHHS-BR-RS-124.1: Registration Service must, in the case of Related MPANs and following derivation of Market Segment for individual MPANs, update the Market Segment for the Primary MPAN and all the Secondary MPANs based on the following rule: 1. If any MPAN in the Related MPAN Group has a (derived) Market Segment of Advanced, then set the Market Segment for all the MPANs to Advanced and set the Market Segment Valid Flag to "Yes" for all the MPANs This specifically cites related primary/secondary and does not mention linked import/export associations at all. But then another requirement implies maybe it should have done: MHHS-BR-RS-127: Registration Service must , in circumstances where the derived market segment is invalid (and has not been overridden by Linked/Related MPAN logic ) Should MHHS-BR-RS-124.1 have applied to linked import/export associations too or is it intended solely for primary/secondary related MPANs? | Updates Verified for Industry Review |  | Interim Release 1 | This should only apply to Related MPANs. Updated RS-127 | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-144 | DI-109 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider | MHHS-BR-RS-131 This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to: Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. | Closed |  |  | See DIN-169 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-145 | DI-110 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. | Updates Verified for Industry Review |  | Interim Release 1 | Added L as valid value for DI-979 in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-146 | DI-111 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. | Updates Verified for Industry Review |  | Interim Release 1 | Agreed with SCS to reuse STD Error Response Section in IF035 to communicate Lapsed Reason . See DIN-145 for summary of updates | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-147 | DI-112 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider | IF-008 response block is listed as mandatory, however on disconnection the MPAN is de-energised by MPRS automatically. The supplier cannot de-energise after disconnection on the IF-007, it must be automatic at MPRS as per The de-energisation needs to be communicated on the IF-008 but it is not in response to an IF-007 and so we cannot populate the response block. | Updates Verified for Industry Review |  | Interim Release 1 | Data interface change agreed. Added Interface note to IF-008 to cover forced de-energisation changes by Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-148 | DI-113 | 2023-02-10 | St Clements | 2864 | Madison Layton | Software Provider | As requested just sending the last three DI’s we have individually through. This one is DI-113 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { "confirmingMpid": "string", --* "registrationId": "string" --*, "updateSucceeded": boolean --* } Suggest that DI-0980 is removed from B066 | Closed |  |  | Discussed with SCS and agreed to close - note no error codes returned from CSS so will provide generic error code | No Change |  |  | MHHSP-DES138-Interface Catalogue, JSON, YAML
MHHS-DIN-149 | DI-114 | 2023-02-10 | St Clements | 2865 | Madison Layton | Software Provider | As requested just sending the last three DI’s we have individually through. This one is DI-114 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 On IF-038 validation "REG1073 - Customer Direct Contract already exists for MPAN [DI-063] for that period" The respective validation rule for this states: If Contract End Date [DI-145] <= Max existing active MS contract end dates [Reg.MAX_DCMS_Enddate], EXCEPT IF requesting MS [S1.SenderID] = Currently Active Direct MS [Reg.CurrentActiveDC_MS_DIPID] AND Contract End Date [DI-145] <= existing active MS contract end date [Reg.CurrentDCMS_Enddate] This rule doesn't fully prevent overlapping appointments as does not cover where the MS is not currently contracted MS and ETD > current ETD which should also be rejected. Think a simpler rule would cover this scenario more fully e.g. If there is an active contracted MS/DS, and the submitting MS/DS does not match then reject And then ETD can be greater or later than current ETD for the currently contracts MS/DS anyway so doesn't need specifying? | Initial Assessment/Updating |  | Interim Release 2 | Waiting Maddie feedback |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-150 | DI-115 | 2023-02-10 | St Clements | 2866 | Madison Layton | Software Provider | As requested just sending the last three DI’s we have individually through. This one is DI-115 in our log In some place on IF-038 tab there is reference to a future customer direct contract e.g. "OR requesting MS [S1.SenderID] <> Any future Direct MS [Reg.FutureDC_MS_DIPID] " "extended dates will be subject to checking if another Service Provider has registered a separate Customer Direct Contract covering the same period" - this can only happen if there's a future appointment "AND ALSO removing all future periods which may or may not have been accepted and recorded previously." As there is no Effective From Date included in the flow MPRS will store an Effective From Date of the system date at the time of creation of the customer contract indicator. It will not be possible to set one to start in the future as the IF-038 does not include effective from date. Is this the same understanding as the MHHS Design Team? | Initial Assessment/Updating |  | Interim Release 2 | Waiting Maddie feedback |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-151 | DI-116 | 2023-02-10 | St Clements | 2868 | Madison Layton | Software Provider | Just spotted a change in v4.7 and raised in our log as DI-116 Artefact: MHHSP-BP010-Change of Registration Data -v4.7 under MPL and GSP Group amendment section, DB02 has been amended in v4.7 to DB002. DB002 is not correct, DB02 was the correct name For reference the DB flows only ever have one 0 in, there is DB01 (MPAN creation), DB02 (MP updates), DB03 (Disconnection) and DB05 (Import/Export Linkages) | Updates Verified for Industry Review |  | Interim Release 1 | BP010A step 10 flow name change to DB02, BP010B step250,step440, Step560 flow name change to DB02, and update BPD descriptions to DB02. | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-152 | DI-117 | 2023-02-14 | St Clements | 2912 | Madison Layton | Software Provider | On looking more closely at the validation rules for IF-019 spotted a few issues. IF-019 REG-1061 rule for Related Create event code appears to be written incorrectly. The rule and rejection description don't quite align. Rule: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) are not currently part of an import/export relationship Rejection reason: REG1061 - Prosposed MPAN(s) [DI-073] / [DI-074] are already part of a Related MPAN Relationship Should the rule read: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) is currently part of a related primary/secondary relationship? The rule and descriptions also don't appear to fully align for some in import/export section too - REG1052, REG1055, REG1057 and might need some minor tweaks to correct. | Updates Verified for Industry Review |  | Interim Release 1 | REG1061, 1052 and 1055 rules updated. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-153 | DI-118 | 2023-02-14 | St Clements | 2913 | Madison Layton | Software Provider | On working on detailed design for Related MPANs, noticed the IF-019 interface is missing a rule that the Secondary MPAN must not be a Primary in another Relationship. You could expand REG1064 to include this as the description sounds like it should have been covered here. Rule: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN Description: REG1064 - Proposed Secondary MPAN [DI-074] is already part of a different MPAN Relationship Could amend rule to: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN OR [DI-074] is already in a relationship as a Primary MPAN | Updates Verified for Industry Review |  | Interim Release 1 | REG1064 validation rule updated | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-154 | DI-119 | 2023-02-15 | St Clements | 2919 | Madison Layton | Software Provider | On further detailed design we’ve spotted a potential design gap. Currently it is possible to enter a state where an MPAN is both a primary and subsidiary MPAN at the same time (e.g. Primary but also export linked or Secondary but also import linked). The current MHHS doesn't accommodate an MPAN being in both states at the same time. We’ve already looked to add rules to try to mitigate this on DB02/DB05 internal flows but would need additional rules on IF-019 to fully prevent this scenario occurring. Rules we think are required: 1. On receipt of IF-019 with event code RelatedCreate or RelatedAdd, the primary MPAN must not have energy direction of Export 2. On receipt of a IF-019 with event code RelatedCreate or RelatedAdd, any listed secondary MPAN must not in an active Import/Export relationship as the Import MPAN 3. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Import MPAN must not be in an active relationship as the secondary MPAN 4. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Export MPAN must not be in an active relationship as the primary MPAN | Initial Assessment/Updating |  | Interim Release 3 | Discuss with SCS | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-155 | DI-120 | 2023-02-15 | St Clements | 2930 | Madison Layton | Software Provider | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. | Closed |  |  | see also DIN-172/173. Included in 5.1 DUPLICATE See DIN-172 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-156 | DI-121 | 2023-02-24 | St Clements | 3078 | Madison Layton | Software Provider | We have logged a new design issue under DI-121. IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP | Closed |  |  | Duplicate of DIN-173 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-157 | DI-122 | 2023-02-27 | St Clements | 3090 | Madison Layton | Software Provider | New design issue (SCC Ref DI-122) for the IF-005 related to REC CP R0032. The current v5.0 validation in the IF-005 does not include the new validation introduced with REC CP R0032 (R0032 is approved and being implemented in the D0312 this June): NEW REC CP R0032 Validation: V Rejected – ESME ID already exists within MRPS and does not match Removed Meter, Associated Import/Export MSID or Related MPAN W Rejected - MSN relates to a Smart Meter Type and the ESME ID is NULL X Rejected – ESME ID Format is Invalid Y Rejected – Number of Displayed Register Digits is NULL and the MSN relates to a Smart Meter Type Z Rejected – Non-Smart Meter Type with Number of Displayed Register Digits populated AA Rejected – Meter Location is invalid AB Rejected – Non-Smart Meter Type with ESME ID populated AC Rejected – Number of Displayed Register Digits is incorrect IF-005 Validation: V not covered, needs to be added as a Level 5 Validation Rule W is already covered by DI-085 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) X is already covered in DI-085 population notes (Level 4 validation RCP1023 Msg Contains Invalid Valid Value Combination(s)) Y is already covered in DI-091 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) Z is not explicitly covered, suggestion: add to DI-091 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AA is covered in the population notes AB is not explicitly covered, suggestion: add to DI-085 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AC not covered, Suggestion: add the following population note from R0032 to DI-091: Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” Summary Please add the following Changes to the IF-005 to align it with the D0312 validation and maintain the same level of Smart Meter data quality in the Registration Service: New Level 5 Validation rule for DI-085 implementing V from the D0312. ESME ID must be unique within MPRS unless it’s a Linked MPAN where the same Smart Meter can be shared across Linked MPANs New population note for DI-091, only to be included for Smart Meter Types New population note for DI-085 , only to be included for Smart Meter Types New population note for DI-091, Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” | Updates Verified for Industry Review |  | Interim Release 1 | New Validation Rules added to IF doc to ensure full coverage and alignment with CP Error codes described | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-158 |  | 2023-02-27 | Elexon | 2908 | Derek Weaving | Central Body | As part of the Performance Assurance Working Group discussions on Supplier Charges, we are exploring the use of CCCs to categorise the data for future charges. It is noted that Settlement Period Quality Indicator referenced in the VAS Method statement is for illustrative purposes and would welcome clarity on the following: · What is the intended process to populate the Settlement Period Quality Indicator in the initial ISD Table? · What would be the process to be involved in those activities to determine the categorisations should additional CCCs be required? | Initial Assessment/Updating |  | Interim Release 3 | Recommending a change to this ISD Data Item: Settlement Period Quality Indicator to be set as per Appendix 1 of MHHSP_METH007 MDS_Method_Statement v5.0 This data item need to be changes to something like ‘Valid Settlement Period Quality Indicator Set’ and the field size needs to be increased. The data catalugue will need the revised data item and the field length will need increasing from 20 to at least 50. This Item also appears in some interfaces that will need t be updated This is because it represents a set of SPQIs. The initial intention is to populate as per the table and check if any new SPQIs have been introduced in the baseline design Method Statement that are not covered. If new CCCs are introduced the appropriate flags for each new CCC would need to be agreed. However, it is likely that another dimension to the table below would need to be introduced to facilitate new CCCs. |  | Meter to Bank | Volume Allocation Service | MHHSP-METH006_VAS_Method_Statement
MHHS-DIN-159 |  | 2023-03-01 | ENWL | 2994 | Paul Band | Network Business | DES-138 Interface Inconsistencies vs BSCP7XX for UMSO Discussions with ENWL have highlighted a number of inconsistencies in the Interface Catalogue when it comes to routing for UMSO's. DIN-106 also refers. UMSO is not listed as a recipient in DES-138 for the PUB-008, but this is in the draft BSCP and should be added to the PUB UMSO is not listed as a recipient in DES-138 for the PUB-020, but this is in the draft BSCP - this is not needed in the BSCP as there are no unmetered Related MPANs UMSO is not listed as a recipient in DES-138 for the PUB-035, but this is in the draft BSCP - view that it is unlikely for this flow ever to be used as the appointment will not trigger any processes to need a subsequent update UMSO Is listed as UMSI, not UMSO in PUB-036 in DES-138 UMSO is listed as UMSC, not UMSO in PUB-018 in DES-138 The IF_LIST tab should be reviewed for consistency | Ready for Internal Review |  | Interim Release 2 | As with DIN-106, there are inconsistencies in the Interface Catalogue for UMSO routing. This has been compounded by a review of the draft BSCP for UMSO, which has added a number of PUB flows going to UMSO that aren't currently in the catalogue. Covered by updated secondary routing rules Design to check requirements in BSCP and MHHS BPs and ensure the interface catalogue reflects a consistent approach |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue and possibly related business processes and descriptions E2E001
MHHS-DIN-160 |  | 2023-03-14 | Ovo Energy | 2862 | David Morley | Supplier | Steps 205 and 210 in BP009 wont be completable in the event that theres no comms. I think the process would be workable if there was an exception route here - see red arrow below. | Ready for Internal Review |  | Interim Release 2 | Update Steps 205 and 210 in BP009 with "Comms Availanble" line label add flow from step 205 to step 215 with “Not Commissioned / No Comms” line label | Process Model correction | Metering Changes | Change of Metering | MHHS-BP009
MHHS-DIN-161 |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | MHHS-METH001-5.4c Please confirm the requirement: “where daily advance records are available [either in the past or future] and less than 90 days months different from the UTC Date requiring a daily advance - use the mean actual Meter advance from the closest [4] weeks for the same Day Type (as defined in ISD).” | Ready for Internal Review |  | Interim Release 2 | Duplicate of DIN 97? | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-162 |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | MHHS-METH001-5.5 typo “Where DAEs are required to be calculated the SDS shall use the most recent data a based on the event that triggered the estimation.” | Ready for Internal Review |  | Interim Release 2 | Duplicate of DIN 98? | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-163 | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | "I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" | Ready for Internal Review |  | Interim Release 2 | Updated conditionality rule for Block B037 in IF-001, IF-002, IF-033, IF-036 |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-164 | DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | "WOA-0093 comment raised on 12/01/2023 "" D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692"" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: ""It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period"" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42" | Closed |  |  | "This requirement stands - review with SCS in light of SEG scenario. We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error...". Reviewed with SCS and agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-165 | DI-122 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | See separate sheet Duplicate of DIN-157 | Closed |  |  | CR required to add rules in line with CP R0032 Added Miscellaneous Data Validation to IF-005 to cover REC CP R0032 validation rules Wrapped up into design teams main CR Doesn't need to be raised by SCS | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-166 | DI-77 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | "On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54" | Updates Verified for Industry Review |  | Interim Release 1 | Added clarification to REG Notes re Consent and Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-167 | DI-78 DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | "Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? " | Closed |  |  | Agree you can't. Could update 1032 rule for USP? Duplicate see DI-29 | No Change
MHHS-DIN-168 | DI-92 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | "WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 ""DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least ""Registered"", if no DS is appointed then there is already an appropriate Event Code"" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone | Closed |  |  | CR for new functionality. "Already covered by no MS/DS appointed - MPRS would try to align MS/DS with principle and couldn't as there's no registration to align this to. Need an extra check that can only autoappoint if there's a registration to prevent MPRS crashing Maybe one for DRG? Jon at RECCO for consequential change? Agree not to build for this scenario as this would be an edge case and close | No Change
MHHS-DIN-169 | DI-109 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | MHHS-BR-RS-131This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to:Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. | Updates Verified for Industry Review |  | Interim Release 1 | Simplified MHHS-BR-RS-131 on when to lapse a SEG appointment | Requirement correction | MPAN Ownership |  | MHHSP- BRS003, MHHS-BR-RS-131 | 2023-03-23
MHHS-DIN-170 | DI-110 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. | Closed |  |  | Duplicate of DIN-145 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-171 | DI-113 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | "Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { ""confirmingMpid"": ""string"", --* ""registrationId"": ""string"" --*, ""updateSucceeded"": boolean --* } Suggest that DI-0980 is removed from B066" | Closed |  |  | Agreed with SCS being retained but due to optionality may have to populate text e.g. contact DSP. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-172 | DI-120 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. | Updates Verified for Industry Review | 2023-04-27 | Interim Release 1 | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-173 | DI-121 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP | Updates Verified for Industry Review | 2023-04-27 | Interim Release 1 | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-174 | DI-72 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | "A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a Submitted MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60" | Updates Verified for Industry Review |  | Interim Release 1 | "Agreed- doc updates MDR can have gaps between DS EFD and MDR EFD" Updated REG1083 validation in IF-034 so that it allows MDR Effective from dates >= SSD/ DS Eff From date/Existing MDR Eff from date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-175 | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | "I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" | Closed |  |  | Duplicate entry | No Change | MPAN Ownership
MHHS-DIN-176 | DI-103 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | "IF-034 new rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD" | Updates Verified for Industry Review |  | Interim Release 1 | Agreed -doc updates Updated REG1082 to apply for both [SDS-MDRUpdate] and [DSAppSPRepsonse] events in IF-034 | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-177 | DI-105 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | "Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 " | Closed |  |  | "Reason for IF-035 is to trigger when SDScan send the Meter info" & The IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR Agreed with SCS no changes are required, they now understand the context agreed to CLOSE | No Change | MPAN Ownership |  | MHHSP-BP003A
MHHS-DIN-178 | DI-106 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 | Initial Assessment/Updating |  | Interim Release 3 | "Should this be specified by RECCo not by MHHS Programme - Design Team were asked to remove this requirement previously Assuming we use MEM Role code of M each time, do not send DS Should it be part of consequential change? Concern around assurance - we will build without a requirement to fulfill and may be aske to take it out by assurrance provider" |  | MPAN Ownership | MPAN Ownership | Existing EMAR I/F
MHHS-DIN-179 | DI-111 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. | Closed |  |  | Duplicate of DIN-146 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-180 | DI-125 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | On If-005 the Meter Removal is currently not permitted for a prospective MS Is it possible for the MS to need to remove two meters and replace it with one? In which case meterexchange would only allow them to do part of this process (remove 1 and add 1) but not complete it, so SEG could not complete. Should meter removals therefore be allowed for prospective MS? (REG1019) | Updates Verified for Industry Review |  | Interim Release 1 | Revised REG1019 and added REG1027 for MeterRemoval event in IF-005 | Requirement correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-181 | DI-126 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Missing Rule on If-005: MAP EFD must not be > removal date | Updates Verified for Industry Review |  | Interim Release 1 | Added new rule for MeterUpdate and MeterHistoryUpdate events so that MAP EFD must not be > removal date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-182 | DI-127 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | On If-005 On exchange - the MAP and IHD groups are for new installation not removed meter - does this need to be clarified? | Updates Verified for Industry Review |  | Interim Release 1 | New note added to IF-005 to clarify that only the newly installed MAP and IHD information is required on MeterExchange | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-183 | DI-128 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | IF-005, IHD EFD missing validation in IF-005 (Between install and removal date) | Updates Verified for Industry Review |  | Interim Release 1 | Covered Release 5.1 | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-184 | DI-129 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | "IF-005 incorrect validation rule: REG1010: On event code Meter exchange and Meter Install rule states MAP EFD >= Install date, it should be = not >=" | Updates Verified for Industry Review |  | Interim Release 1 | IF-005: Updated to REG1010 (MAP Eff from date check ) to = install date for MeterInstall and MeterExchange | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-185 | DI-130 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | It should not be possible to change MDR EFD once set. Need validation rules to enable MPRS to reject if IF-034 is submitted with current MDR but a different EFD. | Updates Verified for Industry Review |  | Interim Release 1 | Agreed - doc updates Covered by L3/4 validation as per updated Validation rule notes | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-186 | DI-131 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | On If-031, there is currently not enough validation to ensure on a SEG, that the same SP isn't appointed for the current registration. Need additional validation rule: If scenario SEG and current supplier, then SP must not be current SP. | Updates Verified for Industry Review |  | Interim Release 1 | Agreed - doc updates Updated validation rule Added REG1095 in IF-031 to check different Data Service proposed for SEG appointment | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-187 | DI-132 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Unhappy Path Scenario: Receive IF-031 for MPAN that is both Principal and Subsidiary MPAN at the same time. This will be rejected as per REG1038/REG1039 Supplier will be unable to appoint MS/DS for the MPAN or any related/linked subsidiary MPANS. | Initial Assessment/Updating |  | Interim Release 3 | "How will unhappy path scenarios be considered/impact assessed? Not needed for PIT/SIT" | Process Model correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-188 | DI-133 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | On If-031 the rule REG1030 reads [DI0-828] in not a valid UMSO in DNO [DI-108]/[DI-109] This should read LDSO not DNO | Updates Verified for Industry Review |  | Interim Release 1 | Tied up with If-005 rejection description flexibility action Change REG1030 to read: REG1030 - [DI0-828] in not a valid UMSO in LDSO[DI-108]/[DI-109] SC change incorporated into 5.1.1 | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-189 | DI-134 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | "On IF-031, REG1036 is written to only apply to USP when it should apply to all scenarios? ""Proposed MDR Date [DI-836] >= [REG.MPAN_SUP_SSD] However don't think this rule is required at all as this is already covered under the REG1036 rule that MDR Date < DS EFD? Linked to DI-66" | Updates Verified for Industry Review |  | Interim Release 1 | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-190 | DI-135 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | On IF-034 missing validation rule REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational | Updates Verified for Industry Review |  | Interim Release 1 | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-191 | DI-136 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | MPRS does not currently prevent Retrospective changes to DUoS Tariff ID or Connection Type. Should MPRS add new validation rules for these items to restrict Retrospective changes? Updating the DIN with additional item at customers request (Updated on 22/05/23 by KH) Please can you update DIN-191 to include Disconnection Date & Export Association. We don't currently have any restriction on how far these data items (and the others in DIN-191) can be back dated. This is a retrospective change through the DB interface and not a Manual Amendment | Initial Assessment/Updating |  | Interim Release 3 | Internal review for whether DUOS Tariff ID updates should be retro | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-192 | DI-137 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | For If-031, scenario SEG, the business process diagram/requirements only describe the appointment lapsing once reaching it's SSD if no SA is received. If we receive a cancellation we would like to lapse the appointment at that point in time (it cannot become secured active after being cancelled) and not wait until the SSD to do this. | Updates Verified for Industry Review |  | Interim Release 1 | Added new requirements to BRS003, MHHS-BR-RS-24.1 and 58.1 | Design Ambiguous | MPAN Ownership |  | MHHSP-BRS003-Registration Requirements | 2023-03-23
MHHS-DIN-193 | DI-138 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | The YAML name for metered indicator (Data Item 127) is meteredUnmeteredIndicator. This is then set to true of false. It isn't clear whether true means it's metered or unmetered due to the naming convention. It should be named meteredIndicator instead to make it clear true means metered, false unmetered. | Updates Verified for Industry Review |  | Interim Release 1 | Updated YAML details in the Data Catalogue for DI-127 Metered Indicator. Updated YAML accordingly Updated data catalogue/ YAML | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-194 | DI-1 | 2023-03-15 | St Clements | 4475 | Madison Layton | Software Provider | For IF-035 what is Event Code [IMS-SendMTD] intended for? If intended for sending to old MS then this should be done via secondary routing on the original IF-035, not via another separate IF-035 message produced by MPRS with different event code. | Closed |  | Interim Release 2 | This message is effectively a copy of the DSAppAccepted AND/OR MSAppAccepted but sent to the Incumbent (current) Metering Service to act as a trigger for that MS to send MTDs. This should be created by MPRS. Requirements MHHS-BR-RS-053 and MHHS-BR-RS-019 cover Registration Service sending this. Message to Maddie to check can close |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-195 | DI-76 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | "Originally raised as T4-COM-1691 on 15th Sept 2022: ""MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days "" Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5" | Updates Verified for Industry Review |  | Interim Release 1 | Agreed doc update Also in Reg Notes tab Updated validation rules and Reg notes Updated REG1037 in IF-031 to 2 workings days and updated REG notes, to align with process and requirements | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-196 |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design | Updates are required to clarify nullable fields | Updates Verified for Industry Review |  | Interim Release 1 | Updates to Interface catalogue includes changes to interfaces and block data items which are present and can be null 1. MHHSP - ERI011A - ECS Reports - Internal v5.1: The data catalogue is the only tab that has been updated 2. MHHSP - ERI011B - ECS Reports - External v5.1: The data catalogue, DIP_Common, MHHS-REP-003 and MHHSP-REP-006 have been updated |  | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue, MHHSP-E2E001 End-to-End Solution Architecture MHHSP - ERI011A - ECS Reports - Internal MHHSP - ERI011B - ECS Reports - External | 2023-03-23
MHHS-DIN-197 |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design | Decision taken to document digital signing of interfaces outside of the interface document. | Updates Verified for Industry Review |  | Interim Release 1 | Remove Z0 and ZI blocks from all interfaces. Signing process will be documented in the Code of Connection document. | Technical corrrection | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue Code of Connection | 2023-03-23
MHHS-DIN-198 |  | 2023-03-15 | Large Suppliers |  | Haz Elmamon | Large Suppliers | Clarification on complex meter site, passed down from DAG as part of the work off plan, Haz to gather concerns for discussion at DA. LSC Rep provided information to the issue on 22-Mar-23 | Requires Industry Work Group review |  | Interim Release 3 |  |  | MPAN Ownership
MHHS-DIN-199 |  | 2023-03-23 | BGAS | 3460 | Neil Strange | large Suppliers | Participant wishes to see the use of standardisation in the interfactions between the SDS and sub roles MDR PSS | Closed |  |  | Closed based on recommendation for programme CR to be raised by the Large Supplier Rep | No Change | Supporting Docs | SDS Validation / Extimation | MHHS-DES138-Interface Catalogue
MHHS-DIN-200 |  | 2023-03-24 | CGI | 3489 | Chris Beard | Software Provider | If there are multiple register readings available for the same Settlement Day, where is the hierarchy defined for selecting which should be used? Is this solely based on Reading Method (i.e. 1. A – Actual, 2. C – Customer, 3. E – Estimated by SDS, 4. S – Estimated by Supplier) or is it dependent on other factors such as the Event Code in the IF-041 ([ReadingRemv], [ReadingInstl], [ReadingEnergisationChg], [ReadingCOR], [ReadingOnSite], [ReadingCOS], [DSEstimate], [SupplierAgreedCOS], [ReadingOverride], [ReadingRemote])? | Initial Assessment/Updating |  | Interim Release 3 | Reading methods do not apply to Register Readings - not sure if question is valid therefore recommendation for DIN to be closed. |  | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-201 |  | 2023-03-24 | ESG | 3529 | Patricia Parker | Software Provider | IF-033 Validation for population into the IF-034 The receiving party business validation rules state “Each Service Provider will need to determine their own validation criteria when processing Appointment Requests. The list below is intended to cover a number of potential possibilities based on the data items made available, and not to suggest that Service Providers needs or should perform such validations.” But should the DI-143 ‘Service Provider Proposed Appointment Response Code’ not form a valid set list (ENUM Vals) in the Data Catalogue so that all parties are working to the same list of applicable codes, rather than this field being a string with a length of 200 field? | Closed |  | Interim Release 2 | IF-033 has been updated as part of Interim Release 1 and the ENUM Vals will not be updated this is because we will have dynamic error messages which cannot be enumerated. |  | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-202 |  | 2023-03-24 | ESG | 3513 | Patricia Parker | Software Provider | Registration Responses in connection with the PUB-31 given the NFS requirement is a 60-minute turn-around time. Within the Operational Choreography there is requirements OPC-140: From our understanding this means that when suppliers receive the PUB_032 from the Reg Service rejecting the appointment Request suppliers then have 60 minutes to re-issue a fresh IF_031 appointment. For example, there is a rejection code for 'CSS Reg ID not known', this would suggest that a party is out of sync and would need investigating especially as in this case, the REG ID would have previously been provided on PUB- 002, DI-849 and CSS is the master of the REG ID and not the Registration Service. | Ready for Internal Review |  | Interim Release 2 | Added suggested text to Ops Choreography | Doc Ref correction | Supporting Docs | Operational Choreography | OPC-140
MHHS-DIN-203 |  | 2023-03-24 | CGI | 3502 | Chris Beard | Software Provider | MHHSP-METH001 M-13. Can you provide a definitive mapping of Estimation Reason Codes to estimation Methods? For example, LTV to Method 11. When should an SDS use Estimation Codes such as Opt Out, Comms. Fault. | Initial Assessment/Updating |  | Interim Release 2 |  |  | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001
MHHS-DIN-204 |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | MHHSP-METH001 M-3. Which estimation Method should an SDS use for de-energised MPANs that would result in an estimation code of ‘De-Energised’? Without a specific Method statement to cover de-energisation, we will end up estimating consumption. | Ready for Internal Review |  | Interim Release 2 | Added Method 13 to reflect de-energised sites. | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001
MHHS-DIN-205 |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | Can you confirm that the Estimation Reason Code ‘Disconnected’ will be removed from the table in 7.3? SRO have advised - Can be removed | Ready for Internal Review |  | Interim Release 2 | Removed "Disconnected" from Table 7.3 |  | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-206 |  | 2023-03-27 | St Clements | 3703 | Anna Davis | Software Provider | Within the MHHS-E2E001 - End-to-End Solution Architecture, there is reference to MHHS-E2E003-Physical Interface Specifications in 1.3 References section This should be labelled as MHHSP-DES138-Interface Catalogue | Updates Verified for Industry Review |  | Interim Release 1 | Updated 1.3 reference section | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-207 | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | There is ambiguity within the design on when agent appointments should become effective, which means that different participants have a different view on when agent appointments should become active. | Requires Industry Work Group review | 2023-06-15 | Interim Release 3 |  |  | Migration |  | BP001 & BPD001 BP002 & BPD002 BP003 & BPD003 Migration Design
MHHS-DIN-208 | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Within the existing Migration Design, it is stated that the Registration Service should reject all Legacy messages for a given MPAN once a Forward Migration has been initiated for said MPAN. This would prevent a legacy MOP from sending the relevant legacy flows if they need to change a meter when an MPAN is mid migration | Initial Assessment/Updating |  | Interim Release 2 |  |  | Migration |  | Migration Design Document
MHHS-DIN-209 | Design Team | 2023-03-30 | Design Team |  | Sean Cooper | SRO Design Team | ~ Level 1/2 Error Code "MSG0000 - Success" Added to Interface Intro Section ~ MSG0018 - Timestamp cannot be future removed and explainatory note added to IF Notes Section of DIP Common | Updates Verified for Industry Review |  | Interim Release 1 | Updated actioned in v5.1.1 of IF Doc. This relates to MSG1008 not MSG0018 as originally given in the design issue. MSG0000 Success added. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-210 | Design Team | 2023-03-30 | RECCo |  | Sarah Jones | Consultancy | Possible change flagged by Sean The original view of the Design Team was that this flag and associated info (ie Is a Customer Direct contract in place, who is the DS/MS with that contract, but not the Eff To Date aka Contract End Date) should be visible to incoming Suppliers, for exactly the reasons you suggest i.e. so that in an incoming supplier could factor the existence of a CDC(s) into their acquisition process / pricing etc. I think we also felt that SP’s who weren’t currently appointed, but may have signed a new CDC should also have the ability to set the flag, as it’s the sites that are part of a CDC, but where that SP isn’t the appointed SP that are the most difficult to coral and manage. The position at the moment is that the existence of a CDC would be shared with incoming Suppliers as part of PUB-002, however this would likely be too late in the process to provide the assistance and support required to an incoming supplier (on all aspects of the sale, contract/price in particular) … … therefore, I think it was also envisioned that information about CDC’s would be available via ECS – so prospective suppliers could check in ECS on the CDC position as part of the other pre-acquisition checks they may undertake. Therefore, I think the decision on exactly what information is shared ‘pre-acquisition’ to participants probably sits with yourselves (RECCo) to finalise as part of your ECS Design / DP Assessment. All information in relation to CDC’s will be passed/made available to ECS via receipt of a copy of PUB-039, so what item(s) are displayed and to what parties I think would get covered off as part of that ECS Design activity. | Initial Assessment/Updating |  | Interim Release 2 | To close, as already discussed with party
MHHS-DIN-211 | DI-139 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | IF-009 Event Code is referred to as [CSSDeRegistration] in the population notes and swagger open API spec but then B042 block title references event code CSS Deactivation, B042 should reference CSSDeRegistration. | Updates Verified for Industry Review |  | Interim Release 1 | Update B042 to reference CSSDeRegistration | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-212 | DI-140 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | MHHSP-BP007-Disconnection-v5.0 is missing IF-050 being sent out on a change to MPAN/RMP Status | Updates Verified for Industry Review |  | Interim Release 1 | to BP007 and BPD007 Requires a flow from Registration Service to EES (IF-050 to DIP, a Publish Change to MPAN/RMP Status process, a PUB-050 from DIP to EES process Receive Change to MPAN/RMP status) starting at step 70 (disconnection). Plus add new step descriptions to the BPD and amend Step 70 description to include IF-050. | Process Model correction | Metering Changes |  | MHHSP-BP007-Disconnection, MHHSP-BPD007-Disconnection
MHHS-DIN-213 | DI-141 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | Data item 997 in S1 common block is senderId in swagger hub, but senderDIPID in data catalogue | Updates Verified for Industry Review |  | Interim Release 1 | Update swagger to reflect senderDIPID to align to data catalague | Data interface correction | Technical Artefact | Swagger | JSON,YAML
MHHS-DIN-214 | DI-142 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | REG Notes section Queuing of Prospective Appointments Rule 4 ** Rule 4: If App Scenario = 'SEG' and Supplier ID + Appointment Service Start Date = Existing Supplier ID + Service Start Date > (Service Start Date +2 working days) >> Appointments meeting Rule 4 have missed their opportunity, and will be 'Lapsed' (PUB-035) This rule doesn't make logical sense, needs correcting. What is the intended logic to be applied here? | Updates Verified for Industry Review |  | Interim Release 1 | Update to align with validation rule | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-215 | DI-143 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | IF-005 for event code [MeterRemoval] rule REG1002 Sending Metering Service ID [SO.SenderID] is currently appointed OR held a valid appointment for Meter Installation Date [DI-057] This should read removal date not installation date | Updates Verified for Industry Review |  | Interim Release 1 | Updated validation rule REG1002 in IF-005 for event code [MeterRemoval] to refer to Meter Removal Date (DI-058) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-216 | DI-144 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | We’ve raised DI-144 On IF-005 MPRS will validate Either current, queued SEG or previous MS If previous and not within 10 working days will reject with REG1003 If not previous, and not current or queued, will reject with REG1027 MPRS will then validate if install date/removal date is within MS period of ownership If not will reject with REG1019 REG1019 need correcting to also include <ETD to apply for previous MS It’s not possible to get a scenario where the If-005 passes the above rules (REG1003, REG1027 AND REG1019) but fails REG1002. Therefore REG1002 is not needed and will never be sent as a rejection code. (Add to DI-43) | Closed |  |  | Agreed with SCS that no further change is required | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-217 | DI-145 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | On IF-005 REG1019 should also include validation that the installation/removal date concerned is <=Effective to date (ETD) of MS period of ownership | Updates Verified for Industry Review |  | Interim Release 1 | Updated IF-005 validation rule REG1019 to include validation that the removal/install date must be <=Effective to date (ETD) where the update is being provided by previous Metering Service (using their 10 day window) for MeterRemoval, MeterInstall and MeterExchange events. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-218 | DI-146 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | IF-005 REG1005 for event codes [MeterExchange] and [MeterRemoval], the rule should not reference DI-056 which is the meter ID in the installation block, it should should referenced DI-053 which is the meterId in the removal block | Updates Verified for Industry Review |  | Interim Release 1 | Rule updated not to reference DI-056 which is the meter ID in the installation block, it now references DI-053 which is the meterId in the removal block | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-219 | DI-147 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | IF-005 REG1005 - for other event codes removal date must be >= to Install date but for [MeterUpdate] the rule states > meter install date. Should be >= | Updates Verified for Industry Review |  | Interim Release 1 | Update rule for [MeterUpdate] to align to other removal date event codes | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-220 | DI-148 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | IF-005 REG1007 unecessary and will never be triggered, it is already covered under REG1001 cannot submit meter install if MPAN is disconnected | Closed |  |  | Valid rule to left in as-is but noted cannot be SIT tested | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-221 | DI-149 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | In the IF-005 guide it states: "When amending the Installation and/or Removal date of a Meter, a supporting MAP history commencing in line with the revised Installation Date must also be provided. Any additional MAPs should be provided in chronological order, each with a ‘MAP Effective From Date’ greater, by at least one day, than the previous." MPRS will accept if the install/removal date is changing AND the MAP History has not been included, there is no requirement in Interface Catalogue or Registration Requirements to reject if MAP history is not provided. | Initial Assessment/Updating |  | Interim Release 2 | Believe covered by MeterHistoryUpdate rules, but hopefully won't be an issue pending agreement on MAP discussion… IF-005 use case guide will be updated with outcome. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-222 | DI-150 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | sarah | Updates Verified for Industry Review |  | Interim Release 1 | Updated wording to match existing validation. Guidance only now provided | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-223 | DI-151 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | IF-005: Need REG1006 to apply to all event codes, e.g. Meter Update on a change to removal date, will need to check that the removal date does not lead to non unique Meter IDs (overlapping dates) MPRS will reject with REG1006 in this scenario | Updates Verified for Industry Review |  | Interim Release 1 | Added REG1006 validation checks to MeterHistoryUpdate and MeterUpdate events. | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-224 | DI-152 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | IF-005 Interface Note below could be read as MeterUpdate event code can be submitted by previous or prospective MS which is not correct "Only the Appointed Metering Service, and for a small window (10 days) to allow for delayed notification of field activities the previously appointed Metering Service; and an incoming Metering Service with a Prospective 'SEG' type appointment may send an IF-005 and update metering details. The [MeterHistoryUpdate] may only ever be used by the Appointed Metering Service. Interface Design assumes that two separate meters with the same 'Meter ID' cannot be installed at the same time. " | Updates Verified for Industry Review |  | Interim Release 1 | Updated | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-225 | DI-153 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | DI-849 CSS Registration Request Id does not have a YAML name in the interface catalogue In the swagger hub, the corresponding name is CSSSwitchID which is misspelt | Updates Verified for Industry Review |  | Interim Release 1 | Updated Data Catalogue to CSSRegistrationRequestID, Swagger to follow | Data interface correction |  | Interface Catalogue Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-226 | DI-154 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | In MHHSP-BPD007 - Disconnection v5.0, the ordering of the steps are out of order. Steps 140, 145 and 150 are for parties receiving the de-appointment notification from the Registration Service, but this is not sent until Step 155. Step 155 “De-Appoint Services” needs to be before Step 140 “DS De-appointment Notification”. Also Step 145 “Receive De-Appointment Notification” is DIP receiving the de-appointment notification to send on, this needs to be after Step 155 and before Step 140 . The ordering should be: • De-appoint services (155) • Receive De-Appointment Notification (145) • DS De-Appointment Notification (140) • MS De-Appointment Notification (150) | Closed |  |  | No plans to change step numbers as long as they are unique | No Change |  |  | BPD007
MHHS-DIN-227 | DI-155 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | Within MHHSP-DES138-Interface Catalogue v5.1.xlsb, the validation for REG1003 – “Metering Service ID [S0.SenderID] post appointment update period for MPAN [DI-063] has expired” is currently set to “Metering Service [S0.SenderID] holds valid previous appointment then [System Date] should be < [REG.App End Date] + 10 working days”. Should this be <= to allow for the full 10 days? | Updates Verified for Industry Review |  | Interim Release 1 | Changed to <= |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-228 | DI-156 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | Within MHHSP-DES138-Interface Catalogue v5.1 - IF-005 has the following error for [MeterExchange] & [MeterInstall]:- “REG1020 - MAP Effective Date [DI-054] cannot take place in the future” Should this validation also be valid for [MeterUpdate] and [MeterHistoryUpdate]? | Updates Verified for Industry Review |  | Interim Release 1 | Added to meter update for removal date. Added to MeterUpdate and MeterHistoryUpdate for MAP effective date |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-229 | DI-157 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 does not have a rule that the SMSO EFD must not be prior to the latest SMSO EFD. We are implementing this rule with error code REG1019 | Updates Verified for Industry Review |  | Interim Release 1 | We are implementing this rule with error code REG1019 Make consistent with others ( PC and ssc + 1 ). Review IHD and SMSO | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-230 | DI-158 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 & IF-005 do not have a rejection code where the IHD is invalid. | Closed |  |  | DIP will reject non-valid values - no change to docs required | No Change
MHHS-DIN-231 | DI-159 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | Within MHHSP-DES138-Interface Catalogue v5.1, IF-005 - There is no validation on Meter Removal date [DI-58]. This should be mandatory non nullable for [MeterRemoval],[MeterExchange],[MeterUpdate], but mandatory nullable for [MeterHistoryUpdate] to allow for reinstating a previously removed meter. Currently in redlined v5.1, this data item is optional and non nullable. | Updates Verified for Industry Review |  | Interim Release 1 | Meter Removal changed to nullable, block conditionality updated |  | Metering Changes | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-232 | DI-160 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | We’ve raised DI-160 on the interface catalogue DCC Service Flag validation rules are specified in IF-025, but DCC Service Flag is not received in this interface. Needs removing. | Updates Verified for Industry Review |  | Interim Release 1 | not needed rules removed. |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-233 | DI-161 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | Within MHHSP-DES138-Interface Catalogue v5.1 – IF-025, where the event type is [ConsentGranularity] Error Code - REG1019 - Consent EffectiveFrom Date [DI-018] must be within Suppliers period of ownership Test Condition - Consent Granularity EffectiveFromDate [DI-018} must be < [Reg.CurrentSupplierEndDate] if exists Should this be <= as it could be on the end date? | Updates Verified for Industry Review |  | Interim Release 1 | Updated to <= |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-234 | DI-162 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | Registration Services Requirement MHHS-BR-RS-021 should be amended to: Registration Service must, where more than one Metering Service appointment request is received from the same Supplier for the same MPAN CSS Registration Request ID, and for the same date, take the last received Metering Service appointment (based on the Sender timestamp) as containing the correct information. Any earlier appointments should be lapsed. To allow multiple queued service appointments for the same registration will be overly complex to design, code and test, and is likely to cause confusion and issues in live operation. It is much simpler and cleaner to only allow one queued service appointment at a time, per registration. This would still allow the Supplier to replace a queued appointment that's incorrect. The Supplier could submit further changes once the first change has completed, if there is a genuine case of multiple changes to SP in a short period of time. It would not impact on CoS. Our proposal is to allow one pending queued appointment per registration, so could have a queued appoint on current registration AND queued appointment on CoS registration at the same time. | Updates Verified for Industry Review |  | Interim Release 1 | Updated MHHS-BR-RS-021 to refer to CSS Registration Request ID. Added REG1089 - Subsequent appointment received as an error code in the interface spec | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-235 | DI-63 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | Original wording:- In the business process diagram for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 Update required:- Please close this design issue as CSS0700 is the correct reference for update of status. | Closed |  |  | DUPLICATE OF MHHS-DIN-63 | No Change
MHHS-DIN-236 | DI-163 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | Within MHHSP-DES138-Interface Catalogue v5.1, 02-DIP-COMMON - R0 response - DI-980 Response Message has been updated in Swaggerhub to be an array, but this is not clarified in Interface Spec. DI-979 Response Code should not be an array. | Updates Verified for Industry Review |  | Interim Release 1 | Added note in Introduction section to confirm that DI-980 can be an array Agreed DI-979 Response Code is not an array | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-237 | DI-164 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | Within MHHSP-DES138-Interface Catalogue v5.1, IF-034 S0 DI-999 Event Code option of [DSAppSPRepsonse] is misspelt. This is also misspelt in Swaggerhub. This could cause differences between systems and should be corrected to [DSAppSPResponse] | Updates Verified for Industry Review |  | Interim Release 1 | Updated typo in IF-034 DI-999. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-238 | DI-165 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | IF-031 is missing validation on MS/DS EFD being within permitted advanced period. This is covered under migration document but not implemented as a validation rule for IF-031. MHHS-DEL961 Migration Design Document section 6.1.1: For the purposes of the CoA Migration process, the below business rules should be followed by Suppliers regarding the lead time between the submission date of the IF-031 and the requested effective from date of the Migration. a. An effective from date from Same Day +1 up to a maximum of 28 calendar days (inclusive of the 28th day) in the future is permissible. | Updates Verified for Industry Review |  | Interim Release 1 | 28 Day in advance rule added to if-031 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-239 | DI-166 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | Requirement MHHS-BR-RS-134 states MPRS must automatically de-appoint the MS & DS when the Market Segment Indicator changes to NO. Is this the intended design? | Updates Verified for Industry Review |  | Interim Release 1 | Removed reference to Market Segment Indicator from the requirement MHHS-BR-RS-134. | Requirement correction | MPAN Ownership | Market Segment | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-240 | DI-167 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider | Current validation on IF-031 Rule REG1037 will mean MPRS will lapse any appointment where the system date is greater than appointment EFD + 2 working days. This means if a SEG change fails, and the supplier tries to resubmit the SEG change, with EFD more than 2 working days in the past, MPRS will immediately lapse the appointment. If there is a need to allow retrospective SEG changes, more than 2 working days after EFD, then the wording will need to be amended to apply to max(EFD+2 working days, MPRS system date on receipt of IF-034 + 2 working days) | Updates Verified for Industry Review |  | Interim Release 1 | Introduction of Lapsed Response Codes and Rules in IF-035 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-241 |  | 2023-02-01 | C&C | 3430 | Graham King | Software Provider | IF/PUB-018 message with event codes [AddressChg] and [DUOSTariffIDChg]. According to Interface Catalogue routing rules, these events are not communicated to the LDSO role via the PUB-018. We assume that the assumption here is that because these data items are mastered by the LDSO that all internal LDSO systems share this data. This is unlikely to be the case. DUoS billing systems co-exist alongside other LDSO management software and are often supplied by different vendors. They do not and cannot share data sets. Given this real-world separation, would it be possible to make the PUB-018 message available to LDSO in the list of Secondary Routing paths? The alternative would mean developing communication channels between disparate systems, from potentially different software vendors in order to pass information from one to the other. | Initial Assessment/Updating |  | Interim Release 3
MHHS-DIN-242 |  | 2023-04-04 | ESG | 3713 | Patricia Parker | Software Provider | Hi How will the Metering Service be kept informed of who the currently appointed Data Service are? On BP003 is shows the Metering Service being a recipient of the PUB_036 when a DS appointment becomes effective, however looking at the routing rules in DES138 it does not show ‘MSSC’ or ‘MSAC’ as being recipients? Kind regards Patricia | Initial Assessment/Updating |  | Interim Release 2 | MSSC and MSAC will be added as recipients | Requirement correction |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-243 |  | 2023-04-05 | Change Request |  |  | Programme | CR015 - Differential Settlement for E7 / E10 Meters for Smart Opt-out customers | Requires Industry Work Group review | 2023-05-24 | Interim Release 2 | [8 empty] | CR15
MHHS-DIN-244 |  | 2023-04-04 | British Gas | 3874 | Neil Strange | Supplier | D0275: Until v0.3 of DES196 was released our understanding was that the D0275 would be retained and it’ use was optional. We are feeding this back on the D-025 consultation but don’t want to lose sight of this. Its removal will impact our billing systems and substantially drive up implementation costs. The baselined IF-021 also does not handle the clock change | Initial Assessment/Updating |  | Interim Release 2 | Alignment with D0275
MHHS-DIN-245 |  | 2023-04-01 | Avanade/ Design Team |  | Grant Sutcliffe | Software Provider | Transaction Id As discussed at stand-up today, could the length specification of the TransactionId be increased to be a max length of 60. The need for this is to cater for a 16 character length hex value (increasing from current length of 6 characters]. This would ensure that we achieve uniqueness. It will also provide headroom for any length increase in other Transaction Id constituents, such as Role. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: T-041-1234567890123-SUP-20230220-619C1F6967838002 [Length = 50] Example from DES138 spreadsheet: T-006-1234567890123-SUP-20220401-1234CC [Length = 40] Correlation Id Could CorrelationId length also be increased to 60 max length of 60 - for the same reason. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: CI-BP-011-20230222-619E0BD1D1FD9000 [Length = 35] Example from DES138 spreadsheet: CI-BP-011-20230222-1234567890123 [Length = 32] | Ready for Internal Review |  | Interim Release 2 | Updated DIP Transaction ID and DIP Correlation ID to String 60 in Interim Release 1 |  |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-246 |  | 2023-04-12 | Change Request |  |  | DCUSA | CR019 - Replacement of D0242 D0315 for MHHS | Initial Assessment/Updating |  | Interim Release 2
MHHS-DIN-247 | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme | Update to the Core Design Interface Catalogue (MHHSP-DES138) is required to include the addition of IF-003 | Initial Assessment/Updating |  | Interim Release 2 | IF-003 defined as part of Migration baseline |  |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-248 | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme | Updates to the ISD Entities document (EDI021, v5.0) | Initial Assessment/Updating |  | Interim Release 2 |  |  |  |  | EDI021
MHHS-DIN-249 | Migration Design | 2023-03-27 | Migration Design |  | Matthew Breen | Programme | Discussion around the use of BST/UTC during Migration | Requires Industry Work Group review | 2023-06-15 | Interim Release 3
MHHS-DIN-250 |  | 2023-04-06 | Design Team | 3764 | Steve Weston | Programme | This is related to ticket 3764, to update the Interface Specification to ensure the Participant ID is clearly defined as a 10 digit number [0-9] only, and the examples in the Interface Specification align to this, including where this is used as part of the sender unique reference and the examples shows 11 digits, not 10 digits for Participant ID. | Initial Assessment/Updating |  | Interim Release 2 | In E2E001 doc Section 4.2.3.2 Section 4.4.4.2 example code for Sender unique Ref and in Transaction ID Section 4.5.4.3 as above DES138 doc Data Catalogue tab: DI-990 example and DI995 Example DIP common tabl DI995 example and the example JSON block (the above easy to change) ALL the IF tabs the JSON block example the Sender Unique Ref contains Participant ID and in every example its longer than 10. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 Solution Architecture MHHSP-DES138-Interface Catalogue
MHHS-DIN-251 |  | 2023-04-06 | Design Team | 3860 | Steve Weston | Programme | This is related to ticket 3860, to update the Interface Specification to provide more clarity / notes on the optionality of B064 and B065 blocks in the IF-041 interface. This is in relation to notes / detail about which blocks are mandatory (from a contractual perspective) versus what should be included in the message if the data exists. | Initial Assessment/Updating |  | Interim Release 2
MHHS-DIN-252 |  | 2023-04-06 | Centrica | 3661 | Neil Strange |  | We believe there is a Design Gap at Change of Agent and Change of Supplier for Smart Meters which also impacts Migration. Neither the Registration Service, Metering Service nor Data Service will know how the registers are set up and specifically which are active. Consequently the Data Service will not know which registers to send on the IF-041, nor will there be able to calculate consumption correctly without knowing the register set up. The interface catalogue for IF-041 states in respect to this “B065 Block Below Repeated for each set of Configured Register(s) for each Meter” – we do not believe there is a way to give the DS this information. The supplier will set up the smart meter configuration to enable the registers to capture the usage for certain time periods. There is currently no way for the supplier to inform the DS which registers are active at what time of the day - the DS cannot accurately calculate the consumption breakdown based on the reads when there are multiple registers configured. | Requires Industry Work Group review | 2023-06-15 | Interim Release 3
MHHS-DIN-253 |  | 2023-04-12 | British Gas | 3769 | David Hipwell | Large Supplier | The latest E2E Functional and Non-Functional Requirements MHHS-E2E Requirements V3 which went to V3 on 16/02/2023 appears to focus on message counts and response times. For example:- During transition all meter points (ca. 31M) will be transition between the old and new services. Therefore assuming a linear migration over the year this would result in the load below, hence services shall be capable of processing the following volumes: - average daily volume of 680,000 - peak daily volume of 2.4M 5.0M - annual volume of 248M 500M Analysis of the flows needs to be categorised across all impacted market participant roles including the DIP. Only then will it have meaning for all parties. The calculation needs to take account of the migration period using the MHHS migration volumes according to date (including REVERSE migration). These should be in both message counts and also sizing (e.g. Gb). And include for a BAU day and also migration days. Whilst some calculations can use the total number of MPANs, to be useful these need show also at perhaps for a million MPANs in each role. Only then will all parties be working on a single set of figures. A line in the sand. The NFRs that exist appear to have moved away from any form of technical calculation towards business process figures. But these figures need to go as an input into technical sizing’s, and should have done for DIP – can these be produced and published ? | Initial Assessment/Updating |  |  | This is being picked up by the Migration and Transition working group
MHHS-DIN-254 |  | 2023-04-17 | Siemens | 3044 | Tony Mason | Metering Service | this does surprise me and doesn’t seem to correspond to the routing rules in the Interface Specification. A proposed Data Service is not included in the routing tables for the receipt of a PUB-018, for example. I would therefore expect that if a change to DPI occurs between PUB-033 and PUB-036 the proposed Data Service could only be notified on a revised PUB-033 with the Appointment Scenario set to whatever the original scenario was set to – “SEG”, “CSP”, or “COS”. | Closed |  | Interim Release 2 | Ref notes on the maintenance of these data items in the Regi Info Section of the I/F document. Prospective SPs are not notified of changes to these data items during their prospective period. If these Data items change then the supplier should re-evaluate the SP they have proposed and change the appointments as required. If an SP takes on a supply with different elements/factors to those suggested by the supplier at appointment this is a contractual issue between the SP and the Supplier.
MHHS-DIN-255 |  | 2023-04-17 | Elexon | 3983 | Kate Goodman | Testing | ConsumptionOnDeEnergised is an Event Code mentioned in the list of data items but is not present in header where the routing info is held - needs to be added to header | Ready for Internal Review |  | Interim Release 2 | ConsumptiononDeEnergised event moved from IF-013 to IF-014 and added in routing rules | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-256 |  | 2023-04-17 | Elexon | 4169 | Kate Goodman | Testing | DI-015 is mentioned in the header wrt routing but is not present in the message itself. It either needs to be removed from header or added into message. | Ready for Internal Review |  | Interim Release 2 | Block B067 added to IF-014 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-257 |  | 2023-04-17 | Elexon | 4172 | Kate Goodman | Testing | B051 is a block which repeats for each combination of Load Shape Criteria (denoted with single chevron to show repeat). B053 is another repeating block which is denoted by two chevrons, implying it is nested below B051. But in fact it also repeats for each combination of Load Shape Criteria. Should this just have a single chevron or is there further information that needs to be added to make its double chevron make sense? | Closed |  | Interim Release 2 | No change required as there will be multiple B053 in each B051 block.
MHHS-DIN-258 |  | 2023-04-19 | ENWL |  | Paul Band | Network Operator | There are a number of requirements in the MHHS-BRS005-LDSO document which state that we must obtain various registration data via the DIP and maintain records accordingly such as: MHHS-BR-LD-001-005, MHHS-BR-LD-024, MHHS-BR-LD-030 and MHHS-BR-LD-034 Extrapolating these into requirements for our own systems suggests that we should build databases/tables to store this data and maintain it The requirement is placed upon us as a party under the assertion that all settlement related data should be exchanged between services and parties via the DIP. However LDSO’s are unique in that their data exchange for their party type is split and is typically split by system under these party types. As a consequence we already communicate directly with MPRS as it is already part of our system architecture as a paid for and created service by LDSO’s. | Requires Industry Work Group review | 2023-04-27 | Interim Release 3 | Discussion at the DRG of the 27/4/23 did not agree on the development of a New Design Principle, A further workshop with LDSOs needs to take place to discuss alternate options and confirm agreement amoungst all DNOs & IDNO on the receipt of publication
MHHS-DIN-259 |  | 2023-04-20 | ESG | 3756 | Patricia Parker | Software Provider | On BP003C under the CoR section there is a note which states that the readings that pass validation should have Meter Reading Status (J0047) set to ‘T’ and when it has failed set it to ‘F’. However as per the REC the group which houses the J0047 group (032 – screenshot below) should only be present where the Meter Reading Flag (J0045) is set to ‘F’. I have checked DES196 and cannot see that the conditionality for that group is changing in the D0010 therefore I can only assume that the note on the process map is incorrect, and it should be talking about the J0045 value instead. Please can you confirm? | Initial Assessment/Updating |  | Interim Release 2
MHHS-DIN-260 |  | 2023-04-20 | CGI | 4167 | Dave Webster | Software Provider | Swagger definition does not match DES-138 in version 1.0 or 1.1. | Ready for Internal Review |  | Interim Release 2 | No specific detail provided, however comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1
MHHS-DIN-261 |  | 2023-04-20 | Utiliteam | 4245 | Richard Palmer | Software Provider | Swagger definition does not match DES-138 in version 1.0 or 1.1. Configurable Register Reading Date/Time is missing. | Ready for Internal Review |  | Interim Release 2 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-262 |  | 2023-04-20 | Utiliteam | 4214 | Richard Palmer | Software Provider | Swagger definition does not match DES-138 in version 1.0 or 1.1. B070 for IF-031 is wrong. It contains the word DIP in the Swagger, which is not included in DES-138. | Ready for Internal Review |  | Interim Release 2 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-263 |  | 2023-04-21 | CGI | 4203 | Dave Webster | Software Provider | Swagger definition does not match DES-138 in version 1.0 or 1.1. DI-122-Profile-Class is defined as an integer, but in DES138 it is defined as a string length 2. Needs to be updated in the Swagger. | Ready for Internal Review |  | Interim Release 2 | Swagger and Data Catalogue aligned to String 2 for DI-122 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-264 |  | 2023-04-24 | Elexon | 3946 | Rashmi Radhakrishnan | Central Body | One of my colleague pointed out a typo in the CCC method statement attached, and I would like to draw your attention to it and requesting to make necessary amendments. The CCCID starting from 100 to 107 has Market Segment Indicator as “U” and Connection Type Indicator shown as “W”. We think that, for these line items the Connection Type Indictor need be corrected to “U”. For reference please see below picture and this also aligns with ISD entity spec v5.0 (M2 entity). CCC ID Market Segment Indicator Measurement Quantity Consumption Component Indicator Connection Type Indicator 100 U AI C W 101 U AI L W 102 U AE C W 103 U AE L W 104 U AI C W 105 U AI L W 106 U AE C W 107 U AE L W All 'W's' should be 'U's') | Initial Assessment/Updating |  | Interim Release 3 |  |  |  |  | CCC Method Statement
MHHS-DIN-265 |  | 2023-04-25 | Elexon | 4128 | Rashmi Radhakrishnan | Central Body | ISD entity M5 has a filed Settlement Period quality indicator. Is this the complete valid data set for the field Settlement Period quality indicator? I took this below list from interface catalogue v5.0. A = Actual, E= Estimate (UMS Only) A1,A2,A3, AAE1,AAE2,AAE3,EAE1,EAE2,EAE3 (ADV Only) E0 --> E9 = Estimation Method 1 - 9 ZE = De-Energised ZE1--> ZE3 = Zero Estimation Method 1 -3 but the Advanced Data Service Estimation Method Statement has data flags EA1 till EA13 which is not mentioned in the above list. Also, the ISD entity spec M5 example below shows a different data item that is not in the list at all for Unmetered(104 &105). Is this a mistake? | Initial Assessment/Updating |  | Interim Release 3 | The Freshdesk ticket details redlined changes have been made to the DES240 document
MHHS-DIN-266 |  | 2023-04-26 | ESG | 3899 | Patricia Parker | Software Provider | If the D0300 process is not changing then we believe that DES196 is incorrect and should show added routes to allow the Supplier to send a D0300 to the Data Service Matt M has confirmed - We are working through the exchange of CoS readings as the code drafting has raised some questions about the extent to which the SDS is involved in the D0300 process. For smart meters, the SDS will not have any use for the billing register readings so D0300 process should not apply, or at most could only be missing the total cumulative. However, it likely will still be required for traditional meters. On that basis, I think we can acknowledge that the D0300 will be retained and SVs created for Supplier to SDS for traditional meters. The process for smart meters is being discussed internally as the SDS does not retrieve tariff register readings. There will be an updated version of DES196 issued in the next few weeks to reflect feedback from the DTN flow part 2 consultation issued in late March which will reflect the retention of the D0300. | Initial Assessment/Updating |  | Interim Release 3 |  |  |  |  | MHHSP-DES196- D-Flow and Interface Mapping
MHHS-DIN-267 |  | 2023-05-02 | ESG | 4385 | Patricia Parker | Software Provider | RegExpression on the DI-148-Annual-Consumption use of DT-016-Decimal-9-3 in the 1.1 swagger spec. This needs to be updated to align with DES-138 example of 123456789.123. Regex should be ^-?[0-9]\d{8}(\.\d{3})?$ instead of ^-?[0-9]\d{7}(\.\d{3})?$ | Ready for Internal Review |  | Interim Release 2 | Swagger v1.2 has been updated accordingly
MHHS-DIN-268 |  | 2023-05-03 | SRO Design |  | Sean Cooper | SI Design | It was always the intention to revisit and revise all of the Secondary Routing configuration as part of DIP Detailed Design. Completion of this exercise has also resulted in so changes to other routing parameters. | Ready for Internal Review |  | Interim Release 2 | Following disucssion with Avanade the Secondary routing short codes have been simplified and the routing of each IF revisited based in these revised short codes. These are shown highlighted in BLUE in the routing section of each of the individual IF pages. | Technical corrrection | Supporting Docs |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-269 |  | 2023-05-03 | St Clements | 4424 | Anna Davis | Software Provider | We have also realised that there are a large number of discrepancies for each interface between the data item name in Swagger vs the YAML name in the Interface Catalogue Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity | Ready for Internal Review |  | Interim Release 2 | Updated inconsistencies in Interface Data Catalogue and Swagger | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-270 |  | 2023-05-05 | SRO Design | 4557 | Rob Goulding | SI Design | Provide further clarity on how Correlation ID's work. This will impact numerous artefacts including DES-138 and E2E001 | Initial Assessment/Updating |  | Interim Release 3
MHHS-DIN-271 |  | 2023-05-10 | ESG | 4541 | Patricia Parker | Software Provider | S0 and S1 is Mandatory in DES-138 v5.1.1, but is not marked as mandatory in the Swagger 1.1. Swagger needs to be updated to align with DES-138. | Initial Assessment/Updating |  | Interim Release 2
MHHS-DIN-272 |  | 2023-05-10 | SRO Design | 4656 | Rob Goulding | SI Design | Required to DIP Channel Publication (v1.2 of the swagger) that will allow DCPs to register webhooks on behalf of their clients | Initial Assessment/Updating |  | Interim Release 2
MHHS-DIN-273 |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | MHHS Data Type - for Meter ID / Serial number for DI-053, DI-056 and DI-060 | Ready for Internal Review |  | Interim Release 2 | New Data Type created in Swagger v1.2 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-274 |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Missing YAML in DES-138 - DI-073, DI-074, DI-080, DI-111, DI-112, DI-190-194, DI-300 | Ready for Internal Review |  | Interim Release 2 | Missing YAML names for Data Items confirmed and added to data catalouge | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-275 |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | DI-093 / DI-120 - Data length 2,000 not 200. | Ready for Internal Review |  | Interim Release 2 | All additional info data items set to len 2000 in Swagger v1.2 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-276 |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | MHHS Data Classification - ensure all columns are populated for Public and Restricted ie, MPAN & Address (removall all NULLS). | Ready for Internal Review |  | Interim Release 2 | Data Classifications added v5.2.1 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-277 |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | MHHS Data Owner - where there are NULL's, this should be updated so all columns provide an owner, mark as N/A (remove all NULLS). | Ready for Internal Review |  | Interim Release 2 | Data Owners added v5.2.1 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-278 |  | 2023-05-10 | SRO Design | 4590 | Rob Golding | SI Design | Please can DES138 Interfaces spreadsheet be updated to provide an indicator against each interface (or is it interface & event code) as to whether it can be opted in/out by a recipient. | Initial Assessment/Updating |  | Interim Release 3 | Subject to ongoing discussion with Avanade. Should be accomodated witin Secondary Routing Solution
MHHS-DIN-279 |  | 2023-05-12 | ESG | 4484 | Patricia Parker | Software Provider | The BP005 – Data Processing – Process map shows that when a Customer Own Read has been sent to the Data Service from the Supplier in the IF-041, EventCode = ReadingCoR, the Data Service will perform reading validation and issue the PUB-041 back to the Supplier, in the Read Sharing column of the process map. When the Data Service send back the validated customer own read in the PUB-041, what eventcode will they use and where can I find this documented? The previous response says “There is no IF-041 response, check consumption is as expected in PUB-021” is this correct for Customer Own Reads on Smart meters? The map shows otherwise so please can you confirm if the answer or map is correct and if the map is correct, provide information on what event code will be used. | Initial Assessment/Updating |  | Interim Release 3
MHHS-DIN-280 |  | 2023-05-12 | ESG | 4552 | Patricia Parker | Software Provider | DES196 lists the D0386 (Manage Metering Points) as ‘not impacted’ owned by the REC however BP010 shows that the method of maintaining Related MPANs is via the IF_019 / PUB_020 process. Can you confirm whether the D0386 is going to be removed post- MHHS. If not, could you please clarify what process a Supplier should follow post- MHHS. | Initial Assessment/Updating |  | Interim Release 3
MHHS-DIN-281 |  | 2023-05-12 | St Clements | 4446 | Madison Layton | Software Provider | MHHS-BR-RS-053 for the incumbent MS to be notified on If-035 DSAppAccepted where meter is advanced or traditional is missing from BP003 business process diagram and steps | Ready for Internal Review |  | Interim Release 2 | IF-35 flow from step 85 (if accepted where meter is advanced or traditional to Meter Service (incumbent) and additional step 86 to receive appointment response to BP003, and added step 86 and BR-RS-053 ref and details to step 85 to the BPD003 | Process Model correction | Metering Changes |  | MHHSP-BP003-Change of Service - Data Service, BPD003
MHHS-DIN-282 |  | 2023-05-16 | SIMS | 4821 | Martin Freeman | Software Provider | Status Code is included in the E2E001 design response body (4.4.4.2), when this is HTTP Response code and should be removed as this is defined in the callback response. | Initial Assessment/Updating |  | Interim Release 2
MHHS-DIN-283 |  | 2023-05-16 | SIMS | 4826 | Martin Freeman | Software Provider | ID should be capitalised in all places in the Swagger. | Initial Assessment/Updating |  | Interim Release 2
MHHS-DIN-284 |  | 2023-05-16 | SIMS | 4828 | Martin Freeman | Software Provider | HTTP Response code for success should be 201 in E2E001 as per Swagger. | Initial Assessment/Updating |  | Interim Release 2
MHHS-DIN-285 |  | 2023-05-16 | Elexon |  | Rob Golding | SRO Design Team | Add replay / requeue API for Swagger 1.2 to align with existing E2E001 Design. Add additional information / clarity in the E2E001 for Interim Release 2 to align changes between design and Swagger. | Initial Assessment/Updating |  | Interim Release 2
MHHS-DIN-286 |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team | Issue clarification to Participants through DRG that all ECS Reports will be issues via Pattern B. Update of ECS Report Catalouge to reflect this. | Closed |  |  | The ECS reports will be via Pattern A. No change is required to the ECS reports
MHHS-DIN-287 |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team | Create & Issue guidance document on the distribution of ECS Reports. To Contain : - overview of Patern B Process - Guidance on population of IF-047 - Update of IF-047 Event Codes | Open - awaiting assessment |  | Interim Release 3
MHHS-DIN-288 |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team | Update of Swagger with ECS Reporting Structures | Open - awaiting assessment |  | Interim Release 2
MHHS-DIN-289 |  | 2023-05-17 | SRO Design Team | 4994 | Rob Golding | SRO Design Team | IF-015 / IF-016 - updates to E2E001 to provide clarification on design pattern. Alignments between DES-138 & Swagger alongside this. | Open - awaiting assessment |  | Interim Release 2
MHHS-DIN-290 |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team | Proposal to change all / subset of ECS Reports to Pattern B | Closed |  |  | Duplicate
MHHS-DIN-291 |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team | As a result of DIN-290 -- Where should the reporting assets be hosted?? DIP solution specified, but what are the other options are availible. Final solution option to be ratified and documentation updated. | Closed |  |  | Not hosted as via Pattern A
MHHS-DIN-292 |  | 2023-05-17 | SCS |  | Madisson | Software Provider | Change required to ISD Entity M17 to add in Market Segment into the table - otherwise it cannot be used to derive consent values which was its original purposes | Open - awaiting assessment |  | Interim Release 2
MHHS-DIN-293 |  | 2023-05-17 | Design Team |  | Paul Petitt | SRO Design Team | Retrospective DIN raised to ensure that any changes that are made in multiple downstream documents (for example CoCo, DIP Logical Design, DIP Physical Design & DIP Security Design) are reflected / updated in LDP assured documents to ensure e2e design / requirements alignment. This was agreed in a DRG Meeting in March 2023. | Updates Verified for Industry Review |  | Interim Release 1 | design changes to E2E001 End-to-End Solution covering points described in DIN details | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-294 |  | 2023-05-19 | ESG | 5030 | Luke Speakes | Software Provider | What I need to know is if the supplier will receive a PUB_009 with the Event code of [CSSDeRegistration] because nowhere on the BP007 process map does it show the supplier receiving the PUB_009 following a deactivation but on DES138 it shows the supplier as being a recipient of this event code. Step 95 (ringed below) shows the supplier as receiving the PUB_009 off the back of the Disconnection (event code [MPANDisconnection]) but then no where else on the process map does it have the supplier receiving a subsequent PUB_009 following the successful deactivation. Additional step required from step 130 (maybe 137?) to show both PUB-009 Mpan Disconnection and PUB-009 Deactivation going to supplier | Initial Assessment/Updating |  | Interim Release 2 | BP007 change : There is already a flow from Step 85 to Step 95 for PUB009 for disconnection (no change) But need to Add a new step (137) for Receive Deactivation in Supplier lane from Step 130 for PUB-009 MPan deactivation in BP007 And there is already a PUB-037 flow from step 145 to Supplier step 157 for confirmation (so no change there) | Process Model correction | Metering Changes | Disconnection | MHHSP-BP007-Disconnection, BPD007
MHHS-DIN-295 |  | 2023-05-19 | SIMS | 4821 | Martin Freeman | Software Provider | Error code detail updates in DES-138 for Level 1 and Level 2 validation needs to be clarified | Ready for Internal Review |  | Interim Release 2 | Updates made to Intorduction Tab of DES138 in order to clarify Lev1 vs Lev2 error codes. Design is such that participants should expect error code(s) at either level. Further ammendments could be made following Avande clarifications.
MHHS-DIN-296 |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design | It is envisioned that Configuration Management of ISD will largely follow the existing customs, practices and processes as are currently in place for managing MDD changes. However, DIN is required to formally confirm the Owner(s) and allowable update mechanisms (Standard or FastTrack) for each of the new ISD Entities outlined in the DIN. | Open - awaiting assessment |  | Interim Release 3
MHHS-DIN-297 |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design | What Participants are recognised in the existing / new ISD Participant tables…. How does this link in with the parties recognised by the DIP (and assigned DIP Roles / IDs …. Or Not) …. In particular how are MDRs referenced in ISD? Does this reference need to identify the ‘type’ of MDR? | Open - awaiting assessment |  | Interim Release 3
MHHS-DIN-298 |  | 2023-05-19 | PowerData Associates | 4273 | Richard French | Consultancy | As I understand it, you are advising we should A flag the consumption data (even though it isn’t Actual), until the zero charge code D0388 UMS Inventory is received from the UMSO. Therefore - if we have an inventory, regardless of the energisation status of the MPAN, we always use an A Flag. But as you’ve stated, this means an IF-013 will be issued to us as UMSDS, because there is A data, against a De-Energised MPAN. If this is the design/requirement then it is understood – but I would like to call out that this should be detailed within the UMSDS method statement – so I think a DIN is needed to get this requirement added? | Open - awaiting assessment |  | Interim Release 3 | UMS method statement |  |  |  | UMSDS Method Statement
MHHS-DIN-299 |  | 2023-05-19 | PowerData Associates | 4273 | Richard French | Consultancy | Further to this (DIN-298), the cause of this IF-013 being issued can only be that the UMSO has not provided the UMSDS will the correct D0388 UMS Inventory to use. Therefore – the UMSO has a requirement to receive the IF-013 to tell them this. However, the Interface Catalogue has not designed that this will get sent to the UMSO. I think this is a Design Issue too, and also needs a DIN raising so that the IF-013 is provided to the UMSO. | Open - awaiting assessment |  | Interim Release 3 |  |  |  |  | DES138
MHHS-DIN-300 |  | 2023-05-19 | PowerData Associates | 4273 | Richard French | Consultancy | You are advising a Load Shape will always require the E Flag. But as you say if the MPAN is de-energised, that MDS will reject the IF-021. Is this therefore your answer – that MDS will reject the IF-021, and there is nothing that can be done about that, so we just need to accept we will get those rejections? If so, this isn’t really a satisfactory process, to know rejections will be received in this scenario. Can you just confirm that the solution here is we just need to accept we will get these rejections to the IF-021, which we will then simply ignore? If that is the case – again a DIN needs to be raised to write this into the Design so the process is documented. | Open - awaiting assessment |  | Interim Release 3 | Requiring clarification dont think this is a Change |  |  |  | UMSDS Method Statement
MHHS-DIN-301 |  | 2023-05-19 | PowerData Associates | 4273 | Richard French | Consultancy | the corrective action on this scenario (DIN-300) occurring will be if/when the UMSO provides the UMSDS with a D0388 UMS Inventory – then the UMSDS will stop using and submitting the Load Shape data. There does not seem to be a mechanism in the Design for the UMSO to be made aware of this issue that would be of their making, so again needs raising as a DIN please. | Open - awaiting assessment |  | Interim Release 3 | same as 299 and 300 |  |  |  | DES138
MHHS-DIN-302 |  | 2023-05-19 | PowerData Associates | 4273 | Richard French | Consultancy | I’ve pulled together the below table. This covers all the possible scenarios of the UMSDS either having or not having the D0388 UMS Inventory. Combined with whether that D0388 UMS Inventory has load associated data within it. Also combined with whether the MPAN is Energised or De-Energised. Here I’ve listed which Settlement Period Quality Indicator should be used, and where applicable, which Estimation Reason Code should be used. Should this be included in the UMSDS Method Statement and if so, are you happy with the below. In Green are steps we understand. In Red, these remain Unknown to us based on the Design and your answers given. In Orange, these are answered based on your guidance on your email of 28 April – but are not specified in the written Design. | Open - awaiting assessment |  | Interim Release 3 | same as above |  |  |  | UMSDS Method Statement
MHHS-DIN-303 |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design | E2E001 - section 4.2.3 - Changes to Data formatting to align with Swagger / DES-138 | Updates Verified for Industry Review |  | Interim Release 1 |  |  | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-304 |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design | E2E001 - section 4.4.3 - Case Sensitivity - additional information added to provide clarity on approach | Updates Verified for Industry Review |  | Interim Release 1 |  |  | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-305 |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design | E2E001 - section 5.1.7 - Additional Detail required for IF-47 / ISD to provide clarity on approach / steps | Updates Verified for Industry Review |  | Interim Release 1 |  |  | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-306 |  | 2023-05-22 | Tym Huckin | 3992 | Tym Huckin | Consultancy | Provide further clarity / worked examples for UTC Settlement Date (DI-101) for BST / UTC cross over period. | Open - awaiting assessment |  | Interim Release 3
MHHS-DIN-307 |  | 2023-05-22 | CGI | 5042 | Dave Webster | Software Provider | Status code incorrectly included in required, although not in Standard Response Body Type. This is in Swagger 1.2. | Open - awaiting assessment |  | Interim Release 2
MHHS-DIN-308 |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | Add required property to all the S0 blocks in the interface definition | Open - awaiting assessment |  | Interim Release 2
MHHS-DIN-309 |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | Define Transaction ID (DI-990) with no Min Length to align with DES-138. This is DT-014. | Open - awaiting assessment |  | Interim Release 2
MHHS-DIN-310 |  | 2023-05-23 | ELEXON | 5173 | Rob Golding | Central Body | Please can you raise a DIN to provide some guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 are to be applied (if at all), i.e. does the DIP need to consider the effective period and only accept messages on the production system when the message falls within this period? And if so what date within the message should be used as a check? Or the physical date/time of message receipt? Or doesn’t the DIP need to consider these dates at all and no check needs to be applied? | Initial Assessment/Updating |  | Interim Release 3
MHHS-DIN-311 |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | DI-985 / DI987 both String 60. Swagger Min and Max Lengths aligned | Ready for Internal Review |  | Interim Release 2 | Updates made to DES-138 for Length alignment to 60. Updates to Swagger to remove min length.
MHHS-DIN-312 |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | DI-984 / DT-009 needs to be updated to be min 3 / max 5 length. | Ready for Internal Review |  | Interim Release 2
MHHS-DIN-313 |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | S1 - Sender Timestamp updated correctly (from sent timestamp) in Swagger to align with DES-138 | Ready for Internal Review |  | Interim Release 2 | Update made to Swagger to align with DES-138
MHHS-DIN-314 |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | D0 - Publication ID Min Length updated in Swagger 1.2 to be 6 to align with DES-138 (rather than 7) | Ready for Internal Review |  | Interim Release 2 | Update made to Swagger to align with DES-138
MHHS-DIN-315 |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | D0 - DIP Correlation ID should have no min length to align with DES-138 (rather than min length of 1) | Ready for Internal Review |  | Interim Release 2 | Update made to Swagger to align with DES-138
MHHS-DIN-316 |  | 2023-05-25 | Design Team |  | Steve Weston | SI Design | In DES-138, all DT-006 and DT-006N should have min length 10 & max length 10 to be consistent. | Ready for Internal Review |  | Interim Release 2 | Updated DES-138 to align Data Type and provide consistency to Swagger. Removed DI-095 which is no longer used.
MHHS-DIN-317 |  | 2023-05-23 | St Clements |  | Sean Cooper | SRO Design | Update DES138 IF document to include reference to the B9XX Array references held in Swagger | Open - awaiting assessment |  | Interim Release 3
MHHS-DIN-318 |  | 2023-05-23 | REC | 5049 | Jonny Moore | Consultancy | While completing the design phase for EES we noted that the following items with the IF-050 do not have an effective from date. - RMP Status (Registration) - MP Status These items currently have an effective from date held in EES and not including this in the IF-050 would have the effect of removing these items from EES. | Open - awaiting assessment
MHHS-DIN-319 |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | S0 - EventCode to marked as required to align with DES-138 | Ready for Internal Review |  | Interim Release 2 | Update made to Swagger to align with DES-138
MHHS-DIN-320 |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | In DES-138, S1 - Environment (DT-013) should have min length 3 & max length 10 to be consistent with values. | Ready for Internal Review |  | Interim Release 2 | Set Min to 3. However, string length is 10, so max length should be set to 10
MHHS-DIN-321 |  | 2023-05-23 | St Clements |  | Sean Cooper | SRO Design | Consider adding B005 to IF-036 so that incoming SP knows who previous SP were | Requires Industry Work Group review |  | Interim Release 3
MHHS-DIN-322 |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | B002 - Incoming Supplier MPID - Swagger aligned to DES-138 for min / max lengths | Ready for Internal Review |  | Interim Release 2 | Update made to Swagger to align with DES-138
MHHS-DIN-323 |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | B003 - Ougoing Supplier MPID - Swagger aligned to DES-138 for min / max lengths | Ready for Internal Review |  | Interim Release 2 | Update made to Swagger to align with DES-138
MHHS-DIN-324 |  | 2023-05-24 | EDF | 4780 | Paul Saker | Supplier | NHHSP-BPM00C- Transfer of Reads on Change of Data Service details several process steps and messages related to obtaining and sharing register readings between the gaining and losing suppliers to agree a CoS, and to initiating the missing/disputed reads process defined in the Retail Energy Code where CoS reads are missing or need to be disputed/amended. However, it appears that there is no further detail defined within the Design Artefacts regarding how exactly these process steps would work, including amongst other things: • Timing/Operational Choreography – for example it is not clear exactly when losing and gaining suppliers would be expected to attempt to communicate with the meter, or the timescales for sending data obtained between suppliers. • Data to be included in messages – while BPM003C refers to the inclusion of ‘register readings’ in some of the messages it is not clear which registers should be included for smart meters and non-smart meters – for example whether that should just be the registers on a smart meter that the sending supplier uses for billing, or whether that should be all the 48 time of use registers stored on the smart meter. Additioanal input from Andrew Margan - Within the code workstream, we believe the Operational Choreography document needs to be updated to reflect SLAs. Without this, we can’t complete the Code drafting. If you disagree, we would appreciate an early heads up, so we don’t look disjointed in front of industry. | Open - awaiting assessment
MHHS-DIN-325 |  | 2023-05-24 | CGI |  | Dave Webster | Software Provider | In the SubmitEvents StandardResponseBodyType object (SubmitEvents ¦ 1.2 ¦ MHHSPROGRAMME ¦ SwaggerHub), it states that “statusCode” is a required field. Yet its’ definition does not exist in the properties of the object. StandardResponseBodyType: type: object properties: transactionID: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-014-DIPTransactionID' senderUniqueReference : $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-995-SenderUniqueReference' correlationId: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-011-CorrelationID' sentTimestamp: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-003-DateTime' senderId : # the sender of this message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' recipientID : # indended (logical) recipient of the message, i.e sender of the original event message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' DIPConnectionProviderId : # physical recipient of the message (if different to recipient Id) $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' message: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-005-StatusErrorMessage' help: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-019-HelpText' serviceTicketURL: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-018-URL' required: - transactionId - sentTimestamp - senderId - recipientId - statusCode - message - help - serviceTicketURL | Ready for Internal Review |  |  | This has now been updated in V1.2 of Swagger StatusCode Added to the ResponseBody.
MHHS-DIN-326 |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | Changes required to DES-138 / interface catalogue given changes in Migration Design e.g. the addition of interface IF003 and potentially ISD. | Open - awaiting assessment
MHHS-DIN-327 |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | The IF005 User Guide explains how the IF005 should be populated. We have a request for clarification on whether the IF006 will be populated identically or if the Meter ID in the IF006 will reflect the Modified Meter Id in the IF005. Is IF-005 identical to IF-006, or is it with updated MTD's. | Open - awaiting assessment
MHHS-DIN-328 |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | The operational choreography does not include an SLA for the RS to send appointment data to the CSS or the timings by which the CSS and DSP should deliver their roles within the process. These need to be added to the operational choreography for clarity, noting the interaction with CR018. | Open - awaiting assessment
MHHS-DIN-329 |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | Approach on a business rule where the ERDS does not send a MEM de appointment / appointment for an MHHS migration where the same MEM is being appointed under MHHS arrangements e.g. they have the same MPID. The expectation is that smart and advanced MEMs will use the M role code for the interaction with CSS so from their perspective there should be no change. | Open - awaiting assessment
MHHS-DIN-330 |  | 2023-05-25 | Ovo Energy | 5225 | David Morley | Supplier | BSCP504 section 4.15.3 stipulates the criteria via which suppliers can classify sites as Long Term Vacant (LTV). BSCP701 stipulates actions that SDS shall take if the supplier nominates that a site is LTV. However, the criteria that suppliers shall use for classifying LTVs in MHHS is missing. Can you please signpost where the new criteria will be located? | Open - awaiting assessment
MHHS-DIN-331 |  | 2023-05-25 | MHHS | 4733 | Martin Freeman | Central Body | Secondary routing for IF-013 is specified as being conditional upon the value of DI-015. However, DI-015 (Connection Type Indicator) is a property of a repeating block, and there is no constraint in place to suggest that each element in the repeating block must have the same value for this (or any other) property, in which case multiple rules in the routing table could apply simultaneously. The routing table design seems to suggest that only a single rule should apply at a time and that routing should not be derived by blending multiple rules. If this is so, and a message is received where different elements in the B050 have a different Connection Type Indicator then there is no coherent way to implement this in conformance with the routing table. | Open - awaiting assessment
MHHS-DIN-332 |  | 2023-05-25 | MHHS | 4750 | Martin Freeman | Central Body | In the routing table for IF-013 all rules are conditional upon S0.Eventcode == [ActivePowerDefaulted], which means that for IF-013 message where Eventcode == [ConsumptionOnDeEnergisedMPAN] there is no routing at all, which means when this message is sent to the DIP it will not be routed anywhere and will simply disappear. That's almost certainly an error. | Open - awaiting assessment
MHHS-DIN-333 |  | 2023-05-25 | MHHS | 4760 | Martin Freeman | Central Body | All of the routing rules specified for IF-014 are conditional upon DI-015 (Connection Type Indicator). But IF-014 does not have any blocks with this property, which means this message won't get routed anywhere. | Open - awaiting assessment
MHHS-DIN-334 |  | 2023-05-25 | MHHS | 4766 | Martin Freeman | Central Body | The routing table for IF-018 specifies roles AMSC, UMSC, UMDC for Secondary routing. There are no such roles in either the DES138 nor the E2E001. | Open - awaiting assessment
MHHS-DIN-335 |  | 2023-05-26 | British Gas/Engage Consulting | 4640 | Neil Strange/ Haz Elmamoum | Consultancy | IF/PUB-004 – DIP Common Blocks referencing MHHSP-DES138-Interface Catalogue v5.1.1 As a minimum this needs to be referenced in the supplier requirements MHHSP-BRS004-Supplier Overview and MHHSP-BRS002-Metering Service requirements, but to ensure parties get sight of this we would suggest it needs to be included in a business process map and have associated requirements. For IF-004 to be useful to participants DI-999 – Event Code needs to be elaborated e.g. 1- Installation 2- Removal; 3- Exchange; 4 - Found (Where installed by Gas supplier and Elec Supplier takes ownership) C/M/O rules for DI-192, DI-193 and DI-194 need to be explained in the notes – presumably driven by event code Available is spelled incorrectly (available) for DI-192 and DI-194 there are a couple of angles here – 1) ensuring wider awareness and 2) it seems there is a question mark on the governance here as it is odd a flow has been added but industry does not appear to have been sighted on it especially with no associated referencing in artefacts and no process map, so effectively no one has any idea how it is supposed to be used. Although it was formally agreed not to include and use bilaterally....from a Large Supplier Constituency perspective, my members are keen to ensure design clarity and how flows are to be used or not, regardless of their ad-hoc / bilateral nature. | Open - awaiting assessment
MHHS-DIN-336 |  | 2023-05-26 | MHHS |  | Rob Topley/ Zak Hussain | SI Design | Process Step No. BP Step ID Process Map wording Interface ID Sender Recipient/Service Traceability Requirement Traceability Method Statement iServer Requirement Name iServer Step name Issues Found BP01 170 BP01 - 170 Send Site Tech Details on Metering Service Request MHHS-RS-LD-012.1 #N/A LDSO170a Send Site Tech Details on Metering Service Request Missing (only on BPD and traceability matrix) BP01 175 BP01 - 175 Receive Site Technical Details D0215 LDSO Metering Services MHHS-RS-MS-037.1 #N/A MET175 Receive Site Technical Details Missing (only on BPD and traceability matrix) BP03B 95 BP03B - 95 Manage SP Appointment Amendment Request Response PUB-035 DIP Supplier MHHS-BR-SU-35.1 #N/A SUP095a - Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP03B 96 BP03B - 96 Manage SP Appointment Amendment Request Response PUB-035 DIP Data Services Metering Services MHHS-BR-DS-11.1 #N/A ESP96 – Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP05 315 BP05 - 315 Issue Reading Data MHHS-IF-041 Data Service DIP MHHS-BR-DS098.2 #N/A DAT315 – Issue Reading Data Missing (only on BPD and traceability matrix) BP05 340 BP05 - 340 Process Reading Data PUB-041 DIP Supplier MHHS-BR-SU047.1 #N/A SUP340 Process Reading Data Missing (only on BPD and traceability matrix) BP05 350 BP05 - 350 Process Reading Data PUB-041 DIP LDSO MHHS-BR-LD009.1 #N/A LDSO350 Process Reading Data Missing (only on BPD and traceability matrix) BP010D 1055 BP010D - 1055 Receive updated Legacy information PUB-026 DIP Central Settlements MHHS-BR-RD-018.1 #N/A ECS1055 Receive updated Legacy information Missing (only on BPD and traceability matrix) All these requirements don’t exist on any requirement catalogues, they’ve only ever been on a BPD document or the traceability matrix (which are essentially the same document). Also, the highlighted traceability has a typo and is on a requirements artefact but is wrong on both the BPD and traceability matrix. | Open - awaiting assessment
MHHS-DIN-337 |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | R0 - Response Message Min length updated to align with DES-138 | Ready for Internal Review |  | Interim Release 2 | Updated Swagger to align with DES-138
MHHS-DIN-338 |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. BP003 to be updated to clearly show IF-036 going to both Import & Export supplier | Open - awaiting assessment
MHHS-DIN-339 |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. IF-001 to be updated to be additionally sent to the Export supplier rather than just the import | Open - awaiting assessment
MHHS-DIN-340 |  | 2023-05-26 | UKPN | 4547 | Neal Medley | Network Operator | The reports ELEX-REP-02/02A will only contain aggregated data for A(General LLF Class Import and C (General LLF Class Export). The I/F021 can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/014 Rejected Consumption Data Submission and I/F MDS Defaults Applied to any I/F021 data to ensure you are not using rejected data or are missing I/F 021 data in respect of an MPAN. MDS Method Statement to be updated to reflect | Open - awaiting assessment
MHHS-DIN-341 |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | For IF-018 the event [MUMIndicator] is routed to MDS and indicates metered/unmetered. This event is not required by MDS as they can infer this from the Market Segment (Advanced, Smart and Unmetered). DIN raised to remove the routing | Open - awaiting assessment
MHHS-DIN-342 |  | 2023-05-26 | UKPN | 5194 | Neal Medley | Network Operator | The intent is that the daily volume on actuals or estimates are the sum of the appropriate consumption data. So when added together they should equal the summed Total of the Settlement Period data (Total Uncorrected Volume) barring any rounding errors. The data is given in MWh to six decimal places (i.e. to the nearest Watt hour). I assume DUoS billing only calculates to the nearest unit so would not expect any rounding errors to impact. The A flags are set out in the ELEX-REP-02/02A are the same as those set out in the CCC table in the VAS Method Statement which is also in the MDS Method Statement. I agree the list in the calculations only are missing the full list of SPQI that are deemed to be actuals as set out in the ELEX-REP-02/02A. DIN raised to correct the calculation | Open - awaiting assessment
MHHS-DIN-343 |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | The routing rules on the IF-037 sheet state that MDS will 'always' receive the DSDeApp event code, however the 'Always' column on the IF_LIST does not state Central Settlements for MHHSP-IF-037. IF list needs updating to reflect that the DSDeApp event always routes to MDS | Open - awaiting assessment
MHHS-DIN-344 |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | IF-001 - B005 Custom Block update Swagger to align with DES-138. Current Metering Service MPID Length removed. | Ready for Internal Review |  | Interim Release 2 | Updated Swagger to align with DES-138
MHHS-DIN-345 |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | IF-001 - B024 Custom Block update Swagger to align with DES-138. DUOS Min Length removed. | Ready for Internal Review |  | Interim Release 2 | Updated Swagger to align with DES-138
MHHS-DIN-346 |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | IF-001 - B0232 Custom Block update DES-138 to align with Swagger. Update to Integer from String-2. | Open - awaiting assessment |  | Interim Release 2
MHHS-DIN-347 |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | IF-001 - B035 Custom Block - update Swagger to align with DES-138. Remove min length. | Ready for Internal Review |  | Interim Release 2 | Updated Swagger to align with DES-138
MHHS-DIN-348 |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | IF-002 - B074 Custom Block. Clarification on DI-091. DES-138 says this is 1 digit to the left of the decimal point. Swagger says 5 to 6. DES-138 to be updated to the correct value. | Open - awaiting assessment |  | Interim Release 2
MHHS-DIN-349 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Routing Rules in DES-138 do not always correctly identity where Correlation ID == Copy ie, it's missing for IF-005 / IF-006 so this needs to be updated correctly across all interfaces. | Open - awaiting assessment |  | Interim Release 2
MHHS-DIN-350 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Align IF-005 B033 to align Swagger with DES-138 (Postcode removal, mandatory modified meter id) | Ready for Internal Review |  | Interim Release 2 | Updated Swagger to align with DES-138
MHHS-DIN-351 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Align IF-033 B071 to align Swagger with DES-138 | Ready for Internal Review |  | Interim Release 2 | Updated Swagger to align with DES-138
MHHS-DIN-352 |  | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | What text should be used for data obfuscation ? | Open - awaiting assessment
MHHS-DIN-353 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Align IF-033 B032 to align Swagger with DES-138 (SSC Min Length | Ready for Internal Review |  | Interim Release 2 | Updated Swagger to align with DES-138
MHHS-DIN-354 |  | 2023-05-30 | SJW |  | Sarah Jones | Consultancy | Please see below details of a new design query related to the Registration Tranche of Code Drafting. We note that in BP011C there is a process whereby the Registration Service will auto de-appoint / appoint agents for secondary related metering points and linked export metering points as part of their validation. The business process only includes the sending of the IF037 to the Losing MEM and not the IF035. Please could you confirm that this is correct and that in this instance the Losing MEM would not receive an IF-035. If this is the case, we think there should be a change to Metering Service requirements MS-018 and 019 to clarify that where the Losing Metering Service receives an IF-037 with no preceding IF-035 then they should send the MTDs at this point. The alternative would be to include the sending of an IF-035 as well as an IF-037 accepting that these would arrive at a similar time. This would align to the process for managing retrospective MEM appointments where we understand that the Losing MEM would receive both the IF-035 and the IF-037. We also suggest amending MS-008, 008.1, 009 and 009.1 to recognise this nuance as follows: MSA/MSS must obtain Export MPAN de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. MSA/MSS should note this message will be automatically triggered when a change of Metering Service has successfully completed for the linked import MPAN or a new MPAN linkage has been put in place where the [linked import / primary related] MPAN has a different appointed Metering Service. Presumably there is a similar impact on the data service requirements that would need to be considered. | Open - awaiting assessment
MHHS-DIN-355 |  | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Revist and confirm IF-005 Cumulative Digits validation rule against lastest version of the CP | Open - awaiting assessment
MHHS-DIN-356 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | IF-027 B073 - update Swagger to align with DES-138 (consumptionAmendmentSupplierReference max length) | Ready for Internal Review |  | Interim Release 2 | Updated Swagger to align with DES-138
MHHS-DIN-357 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | IF-027 B902 - update Swagger to align with DES-138 (supplierConsumptionAmendmentRequests typo update) | Ready for Internal Review |  | Interim Release 2 | Updated Swagger to align with DES-138
MHHS-DIN-358 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | IF-034 B070 - update Swagger to align with DES-138 (contractReferenceMeteringService max length 10) | Ready for Internal Review |  | Interim Release 2 | Updated Swagger to align with DES-138
MHHS-DIN-359 |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | We need to raise a DIN on the AC method Statement and AC requirements: The method statement states that “The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN on notification of the set-up of that MPAN in MHHS-IF-001.” However, it will be the MHHS-IF-036 Registration Service Notification of Service Appointment & Supporting Info that will initially provide the fact that an MPAN has migrated to Central Settlements. | Open - awaiting assessment
MHHS-DIN-360 |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | We need to raise a DIN on the AC method Statement and AC requirements: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: 3.3 Where a years’ worth of data, >=75% and <100% of actual UTC Period Consumption data (where Settlement Period Quality Indicator = A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6) has been used to calculate the Annual Consumption, the Annual Consumption Quality Indicator should be set to “1”. | Open - awaiting assessment
MHHS-DIN-361 |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | We need to raise a DIN on the AC method Statement and AC requirements: Likewise 3.6 needs to say greater than or equal to 182 days: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. | Open - awaiting assessment
MHHS-DIN-362 |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Section 5 incorrectly named Section 6 needs to be removed: 6. Transition and Next steps | Open - awaiting assessment
MHHS-DIN-363 |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | We may also need to document how the is calculated by the Load Shaping Service in the first year. I believe Helix have developed a calculation and this would need to go in the Load Shaping Method Statement and be referenced in the AC Method Statement. | Open - awaiting assessment
MHHS-DIN-364 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | IF-035 - B066 - mark as mandatory in Swagger as per DES-138 | Ready for Internal Review |  | Interim Release 2 | Updated Swagger to align with DES-138
MHHS-DIN-365 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | IF-004- B093 - update Swagger to align with DES-138 (min Length on commsHubGUID / GPF-GAS-GUID) | Ready for Internal Review |  | Interim Release 2 | Updated Swagger to align with DES-138
MHHS-DIN-366 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | IF-025 - SSC add min length to align with Swagger | Ready for Internal Review |  | Interim Release 2 | Updated Swagger to align with DES-138
MHHS-DIN-367 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | IF-025 B032 Profile Class - updated Swagger to be a String to align with DES-138 | Ready for Internal Review |  | Interim Release 2 | Updated Swagger to align with DES-138
MHHS-DIN-368 |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | IF-013 B049 updated Swagger to align with DES-138 (run Number optional) | Ready for Internal Review |  | Interim Release 2 | Updated Swagger to align with DES-138

## St (hidden)
Total DIN Entries | 1
Count by Status
Row Labels | Count of Current Status
Open - awaiting assessment | 27
Initial Assessment/Updating | 39
Requires Industry Work Group review | 6
Closed | 138
Ready for Internal Review | 73
Implemented | 293
Industry CP Required | 11
Grand Total | 587
Count by Release
Row Labels | Count of Target Release
Interim Release 1 | 133
Interim Release 2 | 103
Interim Release 3 | 57
Interim Release 4 | 90
Interim Release 5 | 45
Grand Total | 428
Count By Area by Release

## Backup 010823 (hidden)
DIN ITEM DETAILS | [10 empty] | Scheduling |  |  | DIN IMPACT ASSESSMENT |  |  |  |  | DIN OUTCOME
Reference | Created BY | other Reference(s) | Date Raised | Organisation | Freshdesk Ticket # | Contact Name | Constituency | Title | Design Issue Notification Details (as notified by participant) | Current Status | Target working Group Date (If Required) | Target Release | Objection Cut-off Date | Design Issue Proposed solution | Justification/Type of Change | Design Area | Design Area - L2 | Artefact(s) Impacted | DAG Review Date | DAG Outcome | Reason for Rejection/Accept caveats | Design Change Reference Number | Internal Freeze Date
MHHS-DIN-1 |  | T4-COM-1744 | 2023-01-30 | St Clements | 2655 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1744 on 15th Sept 2022 MPRS does not currently restrict IHD Installs to Smart Meters, there maybe cases where there is an IHD present but the Meter is Trad (Not compatible with DCC and Customer Switched) Either Allow IHD on all Market Segments OR Cleansing to ensure IHDs are only present on S2 and S1 Meters SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses, as this is still not resolved | Implemented |  | Interim Release 1 |  | Discussed with SCS and agreed to add new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) Added requirements into BRS003. SCS to raise a potential data cleanse. | Requirement correction | MPAN Ownership | SCS Validation | MHHSP-BRS003-Registration Requirements | 2023-03-23
MHHS-DIN-2 |  | T4-COM-1745 | 2023-01-30 | St Clements | 2657 | Madison Layton | Software Provider |  | Orginally raised as T4-COM-1745 on 15th Sept 2022 DB002 is not the interface on which MPRS will be informed of a change to import/export relationship, it is DB05. The wrong diagram was updated, the EDI was updated to DB05 not import/export. SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses and artefact updates, to inform the wrong data item diagram was updated. However the diagram for EDI updates is still incorrectly reading DB005 update instead of DB02 | Closed |  |  |  | This appears to have been missed in v4.6 - the arrow on BP-010B from step435 to Step 440 shows DB005 (not DB05, assume that’s a minor typo in the comment) - and this is the Energy Direction Information (EDI) which is wrong. It has cbeen onfirmed that this was updated in v4.7 to go into v5.0 baseline. | No Change |  |  | None
MHHS-DIN-3 |  | T4-COM-1752 | 2023-01-30 | St Clements | 2661 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1752 on 15th Sept 2022: MHHS-BR-RS-020: "Retro" (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier ) In the D0205 the Supplier can cancel out the current Agent Appointment by setting the EFD to equal the currently stored Appointment EFD. Is this no longer allowed? All Services must be appointed for at least one day valid or not? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: removing the ability for Suppliers to Correct Invalid Service Appointments may not be understood by suppliers. We want to avoid a later Design CR to add this functionality in. SCS has not had a response, feel this is important discuss with Suppliers to avoid later CRs | Closed |  |  |  | The appointment can be resubmitted if it hasn’t been accepted yet. Once accepted, there is a need to maintain contiguous appointment periods. The scenario mentioned is the CoA not linked to a switch, so the acceptance of a new appointment from a particular EFD will ‘lock in’ that date and the previous MS/DS will be de-appointed at midnight on the previous day. This is to ensure that there are no periods left without MS and/or DS in place, which can happen today with D0155/D0151 sequencing issues. As an overall comment, there is not a concept of cancellation of appointments. The only way to alter the appointment is to get a new IF-031 issued. The only way to do this for the scenario presented, would be to issue an IF-031 for the old MS for the original date and an IF-031 for the new MS for the revised date. Requirement MHHS-BR-RS-021 ensures that Registration Service will action the latest received appointment where there are duplicate appointments for the same day. St Clements had requested that we build in a rule saying that you cannot submit a Change of Service Provider (CSP) request for the same Service Provider. It is a bit of a work-around, but we believe sending it as SEG should work, or alternatively a CR would be required to re-look at the interface validation. Closing, as this doesn't require further action - point noted. We have already spoken to a number of suppliers, and will continue to engage to ensure the functionality of the baselined design is understood and any issues picked up as early as possible. Documentation for LDSOs to point at. Pick up in Code Drafting as well. | No Change |  |  | None
MHHS-DIN-4 |  | T4-COM-1755 | 2023-01-30 | St Clements | 2666 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1755 on 15th Sept 2022: MHHS-BR-RS-071.2 REC CP R062 has been raised to remove the restriction on the number of EDI changes. Will this cause any downstream MHHS issues? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Needs to be aligned with REC Change No responses | Closed |  |  |  | As per original SRO response, the impacts of the REC change need to be dealt with through the REC change process and impact assessment. | No Change |  |  | None
MHHS-DIN-5 |  | T4-COM-1760 | 2023-01-30 | St Clements | 2667 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1760 on 15th Sept 2022: There are no Registration Service Reports defined in MHHSP-ERI011A. Will there be a requirement for MPRS to produce any Industry Reports for MHHS? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Design for the complete solution must be defined by M5. This is a DBT Design Start Blocker No responses This could significantly increase DBT time as development of reports can be costly and time consuming | Closed |  |  |  | Who is raising these requirements? What happens today? Possibly CC issues Agreed with SCS that reporting requirements will be introduced via the CR process. Reporting requirements are to be added to the programme RAID log | No Change |  |  | None
MHHS-DIN-6 |  | T4-COM-1761 DI-7 | 2023-01-30 | St Clements | 2668 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1761 on 15th Sept 2022: IF-005, REG1014 First MAP Block, MAP Eff From Date [DI-054] in message, must = MPAN Install date OR >= Eff Form date of all existing MAP Effective From Dates held in Registration prior to first [DI-054] in message I understand that the First MAP must equal the Install Date, I am unsure what the second condition is trying to say? You can not have a Meter Without a MAP. (ignoring customer owned meters where CUST is used) SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: response is incorrect. The Second Rule "Each subsequent MAP Effective From Date [DI-054] must be > MAP Eff From Date in previous block" covers the subsequent overlapping MAPs. The second half of this First Block Rule must be removed. The First Block can only ever equal the install date No responses, the rule has not been amended | Implemented |  | Interim Release 1 |  | This appears valid - the first MAP block can only start at the creation date (assuming the MAP blocks are in chronological order, which they must be if each subsequent map block has an EFD > the last) Currently the design allows 2 ways to amend the MAP History as outlined in Sections 13 and 14 of the IF005 Use Case Guide. Either the Metering Service can provide the full MAP history from the installation date or they can add a new MAP to the existing history, provided it is the next MAP in chronological order. So for example if you have MAPs 1,2 and 3, then you can extend to MAPs 1,2, 3 and 4 using the approach set out in section 14 to extend the MAP history. However if you wanted to set MAP 4 between 2 and 3, you would need to send the whole MAP history from the install date and provide 1,2,4 and 3 as set out in Section 13 to replace MAP history. The second validation rule is required if you are using the extend the MAP history functionality. Added note to REG Notes that where a MAP history is provided it must be in chronological order Added new REG1014 Validation Rule to MeterInstall and MeterExchange events to ensure only 1 MAP block is provided | Data interface correction | MPAN Ownership | SCS Validation | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-7 |  | DI-8, DI-11, DI-12, DI-14 | 2023-01-30 | St Clements | 2669 | Madison Layton | Software Provider |  | MPRS will reject any PUB-031 inlcuding those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8) | Implemented |  | Interim Release 1 |  | See Comments Revised CSS Registration Request ID validation on IF-031, 034 and 025 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | IF General | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-8 |  | N/A | 2023-02-01 | Elexon | 2642 | Sedef Kiris | Central Body |  | We have had the following comment ........... Also just found out that “Metering Service Id” have “MPID” in brackets afterwards, and not “MSID”. We believe it should be MSID | Closed |  |  |  | MPID is the correct term here, it is the metering service MPID. MHHSP_EDI012_ISD_Entities v4.6 Section M8 | No Change |  |  | None
MHHS-DIN-9 |  | N/A | 2023-01-30 | St Clements | 2672 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: [UpdateSiteTechnicalInfoMS] is not included in the interface catalogue and is not utilised by MPRS. Assume this is related to Issue 99 and needs removing? (raised as DI ID 9) | Implemented |  | Interim Release 1 |  | Removed from IF-005 Guide Section 4.1 | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-10 |  | N/A | 2023-01-30 | St Clements | 2799/2670 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: Is the currently appointed Meter Service informed of Prospective MS changes? Changes to MTDs can be made by prospective MS (e.g. change meter type to complete SEG market change before the MS can be appointed). As the MS is only prospective at this point the MS may still be lapsed and not take effect. However any MTD updates made would remain within the MPRS system and not be backed out. The current MS would therefore need to be aware of what changes have been made by the prospective MS. (raised as DI ID 10) | Closed |  |  |  | BP009 only talks about the Metering Service, not the current or prospective Metering Service, and it appears only the registration service receive metering service MTD details, not the current MS. Refer to SRO - what is the assumption here, as the alternative route is for registration to update the current MS The design is based on PUB-006, with the Updated Meter details, being sent to the current Metering Service ( BP011A step 280 ) as well as the Prospective Metering Service (Step 275). It is built into the routing rules in PUB-006. | No Change |  |  | None
MHHS-DIN-11 |  | N/A | 2023-01-30 | St Clements | 2675 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install / Remove Date(s) takes place within the Metering Services period of ownership (or proposed period of ownership for in the case of a prospective SEG appointment) " Sent on 11th Jan: Does not match business rules, as future dated installs are not allowed: "REG1020 - Meter Install Date [DI-057] cannot take place in the future. The proposed MS on a seg will have a future dated EFD, so they only have the +2 day lapse extension period for meter installs (raised as DI ID 11) | Implemented |  | Interim Release 1 |  | Added change of segment scenario's to IF005 USE CASE Guide. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 |  | Refer back to SCS as additional comentary needed on the issue and bring to next meeting
MHHS-DIN-12 |  | N/A | 2023-01-30 | St Clements | 2679 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install /Remove Date(s), cannot have taken place in the future" Sent on 11th Jan: It would be useful to have the Change of Segment process covered in this guide. We are not sure how the Prospective MS can exchange meters when their appointment period is in the future (raised as DI ID 12) | Implemented |  | Interim Release 1 |  | Nomenclature issue - requires a reword of this statement to conform to the business rules. Recommend the following update to section 3.2 of the IF005 Use Case Guide to confirm who can make Metering updates Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed BAU metering updates ( For the avoidance of doubt not meter update/meter history updates), it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. The one exception, is during a change of segment, when the incoming Metering Service is able to provide a BAU metering update, where it’s prospective “SEG” appointment is due to become active on the same day. SEG scenario's added to IF005 Use case guide Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-13 |  | N/A | 2023-01-30 | St Clements | 2683 | Madison Layton | Software Provider |  | Comment on Section 5.1 "validation allows for meter removal at a point following Disconnection if required)" Sent on 11th Jan: This rule prevents this REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational (raised as DI ID 13) | Implemented |  | Interim Release 1 |  | This statement doesn't appear to be a convention. There is no mention of this in E2E001 End to End Solution Architecture. Believe this statement needs to be amended or removed. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. IF-005 validation Rule changed to include meter removal at status Disconnected | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES138-Interface Catalogue, E2E001 End to End Solution Architecture
MHHS-DIN-14 |  | N/A | 2023-01-30 | St Clements | 2684 | Madison Layton | Software Provider |  | Comment on Section 3.2 "Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed metering updates, it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. " Statement is misleading- the 10 day period is only permitted for install, remove and exchange events, it is not listed for meterUpdate/meterHistoryUpdate in interface catalogue Also the prospective MS should be able to make changes for SEG to enable a market segment change to complete (raised as DI ID 14) | Implemented |  | Interim Release 1 |  | Validation rule(s) updated to constrain 10 day window to non-update events. Test in 3.2 reworded to remove ambiguity. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Refer back to SCS for additional clarity on the requirement and include RecCo and bring to next meeting
MHHS-DIN-15 |  | N/A | 2023-01-30 | St Clements | 2685 | Madison Layton | Software Provider |  | Comment raised in guide, sent on 11th Jan, that the JSON examples use MPID when it should use DIP ID e.g."distributorID": "SWAL" (raised as DI ID 15) | Implemented |  | Interim Release 1 |  | Corrected to use Dist DIP ID | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-16 |  | N/A | 2023-01-30 | St Clements | 2686 | Madison Layton | Software Provider |  | Comment on Section 9 " Albeit that these transactions can be ‘clubbed together’ and send as a group in single overarching message/API transaction. " Sent on 11th Jan: As DIP does not protect the sequencing of events (FIFO), is there a risk that the ordering of these updates might arrive out of sequence resulting in the wrong end state? If MS space out their updates it would reduce this risk (raised as DI ID 16) | Implemented |  | Interim Release 1 |  | Clairifcation added to Sec 9.2 to reference Time-Stamps rather than 'clubbing' | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-17 |  | DI-017 | 2023-01-30 | St Clements | 2690 | Madison Layton | Software Provider | MAP History availability to Metering Service | Section 9 says "a supporting MAP history commencing in line with the revised Installation Date must also be provided" Will the MS know the full MAP history? Risk they could destroy the data. Potential MAP billing issues? | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Solution agreed at DRG on what MAP updates are required. Various document updates required to align with DRG decision to only maintain latest MAP | Missing/incorrect validation rule | Supporting Docs | Various Documents | MHHSP-DES138-Interface Catalogue |  |  |  |  | 14//7
MHHS-DIN-18 |  | N/A | 2023-01-30 | St Clements | 2691 | Madison Layton | Software Provider |  | Comment on Section 9 "• When maintaining the MAP History in cases where there is no change in Meter Installation Date then the MAP history provided should commence either with a MAP Effective From Date matching the existing install date of the meter OR be greater than the most recent, already existing, MAP Effective From Date" Sent on 11th Jan: So it's possible to update ALL MAP history back to installation, or add a new MAP, but it's not possible to amend MAP history only part way back (have to go back to installation date instead every time to do this) (raised as DI ID 18) | Closed |  |  |  | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • To update BRS003, requirement MHHS-BR-RS-027 to add “Registration Service must lapse any appointments that fail this validation” • Remove Rejected from Step 225 of BP002/BPD002 • Remove Rejected from label on line after step 215 of BP003. | No Change |  |  | None
MHHS-DIN-19 |  | N/A | 2023-01-30 | St Clements | 2692 | Madison Layton | Software Provider |  | Comment on Section 10 "E2E Architecture convention states that all data items are provided in each message even where these data items are not changing or are null" Sent on 11th Jan: Some of the items are optional not mandatory which conflicts with this statement. Not all data items need to be provided (raised as DI ID 19) | Implemented |  | Interim Release 1 |  | Update of E2E Doc to allow for Nullable values. | Data interface correction | Meter to Bank |  | MHHSP-E2E001 End-to-End Solution Architecture | 2023-02-23 |  | Defer as a E2E clarification may be needed
MHHS-DIN-20 |  | N/A | 2023-01-30 | St Clements | 2693 | Madison Layton | Software Provider |  | Comment on Section 13, sent on 11th Jan: What should MPRS do if it holds a MAP not included in the MAPHistory block? (raised as DI ID 20) | Implemented |  | Interim Release 1 |  | Update "all existing history will be replaced by that contained within the message" | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-21 |  | N/A | 2023-01-30 | St Clements | 2699 | Madison Layton | Software Provider |  | Comment on Section 15.2 "It is understood that currently there a numerous instances of duplicated Meter ID’s, some of which may have overlapping installation dates. " Sent on Jan 11th: Meter id is only unique at mpan. Should not be any instances of conflicted MSNs at MPAN. Can you verify with ECOES? Or we can do a RFI to DNOs but will take time (raised as DI ID 21) | Implemented |  | Interim Release 1 |  | All references to duplicated MSN IDs has been removed from the document | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-22 |  | N/A | 2023-01-30 | St Clements | 2700 | Madison Layton | Software Provider |  | Comment on Seciton 15.3 "add some kind of suffix (X1, X2) to the existing Meter ID." Sent on Jan 11th: This can take the meter ID over the allowable string length (string 10), in this example it would take it to string(12) and so would be rejected (raised as DI ID 22) | Implemented |  | Interim Release 1 |  | As above, Section 15.3 removed from IF-005 User Guide. | Data interface correction | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-23 |  | N/A | 2023-01-30 | St Clements | 2701 | Madison Layton | Software Provider |  | Comment on Section 16.3 Sent on Jan 11th: Cancelled Flag Set. Only a logical deletion. Still held in MPRS but not visible to EES/MEM The section implies the record would be fully deleted from MPRS, however this is not correct, MPRS would set a cancellation flag that would indicate the record has effectively been cancelled/logically deleted. It would however remain in the systems database (raised as DI ID 23) | Implemented |  | Interim Release 1 |  | Added a statement at the end of the table in 16.3 to say "NB the registration service will only logically delete the MAP entry with a flag, it will not be deleted from the database." | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Accepted
MHHS-DIN-24 |  | N/A | 2023-01-30 | St Clements | 2702 | Madison Layton | Software Provider |  | Comment on Section 17.2 "situations where multiple existing meters are identified, the selection process should be extended to include Meter Removal date (if provided) else;" Sent on Jan 11th: Shouldn’t be possible, can run an EES or MPRS RFI to confirm. Noting that MSN is only unique at an MPAN level not a databse level Related to DI-21 (raised as DI ID 24) | Implemented |  | Interim Release 1 |  | Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. The wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-25 |  | N/A | 2023-01-30 | St Clements | 2706 | Madison Layton | Software Provider |  | Comment on Section 17.2 "where multiple meters still exist even after matching on all three data items should be rejected and require manual intervention (i.e. request to LDSO to intervene) ." Sent on Jan 11th: There's no super user functionality for this so how could the LDSO intervene? The LDSO is not able to manually intervene in regards to MTDs, they can for some other data items such as registration data but not MTDs. (raised as DI ID 25) | Implemented |  | Interim Release 1 |  | Reference to LDSO User Removed - agreed with SCS that scenario should not arise provided existing SCS data rules are met | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-26 |  | N/A | 2023-01-30 | St Clements | 2707 | Madison Layton | Software Provider |  | Comment on Section 17.2 "If the MAP segment is not provided, the existing MAP history should be maintained to greatest degree possible, with ‘trimming’ to align to any revised Install / Remove Dates provided" Sent on Jan 11th: Risk that changing of the Meter Lifespan could result in MAPs being logically deleted. The MS would need to re-apply the MAP history to fit into the new meter Lifespan MS would need to understand this process/constraint (raised as DI ID 26) | Implemented |  | Interim Release 1 |  | Section 17.2 of the guidance document updated. Also added new validation rule REG1014 for MeterHistoryUpdate in IF-005 to ensure MAP is provided when creating a new meter picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-27 |  | N/A | 2023-01-30 | St Clements | 2708 | Madison Layton | Software Provider |  | Comment on Section 19.2 "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the permanent deletion of data, mirroring the existing functionality associated with the use of the D0312." Sent on Jan 11th: Only logically deleted, still visible in the MPRS History. Just not visible to MEM or EES Existing functionality on D0312 utilises cancellation flags not permanent deletion (raised as DI ID 27) | Implemented |  | Interim Release 1 |  | Reword to reflect the logical deletion. See MHHS-DIN-23 Reword this paragraph to: "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the removal of a MAP from a meters MAP history using a logical flag, mirroring the existing functionality associated with the use of the D0312." NB Main section header is incorrect - should be updated to section 19, rather than a duplicate of section 18. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Accepted but note there is another DIN already raised
MHHS-DIN-28 |  | N/A | 2023-01-30 | St Clements | 2709 | Madison Layton | Software Provider |  | Comment on Section 19.4 "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories. However, this would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." Sent on Jan 11th: This functionality already exists with the MPAN History Report showing who changed what when for all MPRS data items. Will be extended to include DIP transactional information (raised as DI ID 28) | Implemented |  | Interim Release 1 |  | Proposed Change Reword this paragraph to: "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories, noting that this is also available via the MPAN history report which will be updated with DIP transactional information and could also be used. Any use of EES would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-29 |  | N/A | 2023-01-30 | St Clements | 2710 | Madison Layton | Software Provider |  | There should be an additional rule for USP, if DI-830/DI-833 is populated, the MS/DS Proposed Effective From Date must equal the currently held EFD for the MS/DS appointment in MPRS (raised as DI 29) | Implemented | 2023-04-27 | Interim Release 1 |  | Added rule for USP scenario in IF-031 to check SP Effective from date. Proposing SCS have flexibility on error codes - requires industry Working Group. Picked up as part of Change of Service Provider review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-30 |  | N/A | 2023-01-30 | St Clements | 2711 | Madison Layton | Software Provider |  | The IF-035 does not provide the opportunity for MPRS to populate a lapsed reason. Will need to be able to provide a reason for a lapsed appointment, otherwise there'll be a higher volume of unecessary supplier enquries to DNOs which will require more resource and cost. (raised as DI 30) | Implemented |  | Interim Release 1 |  | Additional Data Item on IF-035 for a reason comment - what reasons would these be other than gone beyond the date? Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-31 |  | N/A | 2023-01-30 | St Clements | 2712 | Madison Layton | Software Provider |  | MHHS-BR-RS-027 "Registration Service must re-run validation, in line with the validation rules set out in the appropriate interface specification, for all Metering Service appointments that have been confirmed to re-process from the Prospective Appointment Queue, to ensure that the appointment is still valid" It is not clear if MPRS would send MSAppRejected or MSAppLapsed if the appointment fails validation after it's been queued? If this is not made clear in the deisgn then there is a risk that we build to use the wrong event code, or if the code should be MSAppRejected then risk that suppliers build a design where they can't process a MSAppRejected after receiving already an MSAppAccepted from MPRS (raised as DI 31) | Implemented |  | Interim Release 1 |  | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • Updated BRS003, requirement MHHS-BR-RS-032 and 66 to show that appointments will be lapsed (not rejected) • Remove Rejected from Step 225 of BP002/BPD002 Also on BP003 leading from step 215 should have the rejected removed. Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Corrections also to BPM002 & BPM003 Forward Migration and BPD002 Froward Migration | Data interface correction | MPAN Ownership |  | MHHSP-BP002-Change of Service - Metering service, BPD002,MHHSP-BRS003-Registration Service requirements MHHSP-DES138-Interface Catalogue, MHHSP-BP003, MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration), MHHS-DEL969-BPD002 (forward migration) | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-32 |  | N/A | 2023-01-30 | St Clements | 2713 | Madison Layton | Software Provider |  | The interface catalogue lists setting a removal date as an action that can be used with event code meterUpdate on IF-005, however in the interface catalogue, the block B039 does not list meterUpdate as a event code that can utilise this block. Need greater clarity on whether meterUpdate and meterHistoryUpdate should apply meter installations and meter removals or not. (raised as DI 33) | Implemented |  | Interim Release 1 |  | The definition of a [MeterUpdate] event code is: Allows currently appointed Metering Service to amend the details associated with a currently installed meter. Therefore the appointed Metering Service must be able to remove the meter as part of an update, this is an omission from the design and a small update to IF-005 The design principle that IF-005 works on is that: • BAU transactions (Install/Exchange/Remove) that are in the Metering Services Period of ownership are covered by the Install/Exchange/Remove events • Changes to currently installed metering can be made by the Appointed Metering Service using the Meter Update event. Note this therefore includes, where required, removing the currently installed meter where it is prior to the current period of ownership. • Changes to metering history ( ie not the currently installed meter ) can be made by the Appointed Metering Service using the Meter History Update Proposed changes: Added MeterUpdate as Optional to B039 block in IF-005 and added validation rule to ensure MeterUpdate is not used to remove meters in current period of ownership picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP-DELS229-IF-005 Use Case Guide | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-33 |  | T4-COM-1759 | 2023-01-30 | St Clements | 2719 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1759 on 15th Sept 2022: IF-005, REG1011 Install date must be > Creation date, should this REG1011 rule apply also to meter Exchange not just meter install SCS raised as a design blocker on 7th October 2022 Still no resolution, should this rule apply to meterHistoryUpdate at least as this allows for meter installations (raised as DI 34) | Implemented |  | Interim Release 1 |  | An exchange will not be a creation date, and the validation already in place ensures that future installation dates will all follow each other, which means this rule isn't required. ​This shouldn't be needed for exchanges, as its covered by REG1008 (install date >= remove date), as an exchange would replace an existing meter, which at first install would be validated against creation date. Moved REG1011 to cover all scenarios in IF005 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-34 |  | T4-COM-1774 | 2023-01-30 | St Clements | 2720 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1774 on 15th Sept 2022: IF-005, REG1011 "REG1009 - MAP ID [DI_055] is not valid for MAP Effective Date [DI-054] REG1011 - Install Date [DI-057] for MeterID [DI-056] is prior to MPAN Creation Date There are many meters in MPRS that pre-date the existence of the MAP and also MPRS install dates of 1980 etc. these will break a number of rules. should these be cleansed before MHHS start? If they are valid, then the rules need adjusting"l SCS raised as a design blocker on 7th October 2022 Still no resolution (raised as DI 35) | Closed |  |  |  | This could be a data cleanse requirement which is a consequential change/transition requirement, but for REG1009 - the MAP effective date should be the point at which the MAP took over the meter, and the exchange date should be after this (ie it should be after the date MHHS goes live). For Reg 1011 currently this is only valid on installs (and installs won't occur on legacy meters). If Reg 1011 is valid on exchanges, then the exchange date should also be after the MPAN creation date - if it isn't then the data should be cleansed. Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-35 |  | N/A | 2023-01-30 | St Clements | 2721 | Madison Layton | Software Provider |  | On the IF-005, should REG1028 (Install date cannot be null or blank) apply to meterinstall, meter exchange and meterupdate too? (raised as DI 36) | Implemented |  | Interim Release 1 |  | Requires amendment to interface validation - look at alternative validation Agree the rule should also apply for those events. Note we believe validation would fail for another reason. Eg REG1019 Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-36 |  | DI-37 | 2023-01-30 | St Clements | 2722 | Madison Layton | Software Provider | Re-alignment of rejection reasons to main block | In the summary of error codes box at the bottom of IF-005 tab the rejection reasons need re-aligning to the main block, e.g. REG1001 should read RMP stats must be Created or Operational, not just Operational As a general note across all interfaces, the rejection codes are referenced in numerous places and the respective descriptions are in many places not consistent for the same rejection code (raised as DI 37) | Closed |  |  |  | Will be revisited once SCS provide definative Error Code Texts | No Change |  |  |  | 2023-02-23 | 23/2/23 - Not discussed at meeting carry to next meeting
MHHS-DIN-37 |  | N/A | 2023-01-30 | St Clements | 2723 | Madison Layton | Software Provider |  | REG1015 (cannot be removed meter) is listed for meterHistoryUpdate in interface catalogue for IF-005. This should actually apply to meterUpdate not meterHistoryUpdate, REG1018 (cannot be installed meter) applies to metering history update (raised as DI 38) | Implemented |  | Interim Release 1 |  | Change accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-38 |  | N/A | 2023-01-30 | St Clements | 2724 | Madison Layton | Software Provider |  | In the interface catalogue, the IHD block B030 for IF-005 should also be optional for meterUpdate according to the IF-005 guide Section 16 Development Notes "The IHD segment, if provided as part of [MeterUpdate], relating to any currently installed meter should replace/update the IHD details currently held at the MPAN to which that Meter is associated." (raised as DI 39) | Implemented |  | Interim Release 1 |  | Small change to schema operation IHD information may be updated as part of the [MeterUpdate] event. The change is to add [MeterUpdate] event to block B030, so it now reads "B030 - MPAN IHD Information (Optional & may only be used with [MeterInstall],[MeterExchange],[MeterUpdate]) NB this also standardises the use of commas between event codes, rather than using the & symbol. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-39 |  | N/A | 2023-01-30 | St Clements | 2725 | Madison Layton | Software Provider |  | In interface catalogue for IF-005, there needs to be a rule that if event code MeterInstall is used, then modified meter ID cannot be populated (raised as DI 40) | Implemented |  | Interim Release 1 |  | Update agreed | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-40 |  |  | 2023-02-01 | SI Design |  |  |  |  | Not used - raised as duplicate in error | Closed
MHHS-DIN-41 |  | N/A | 2023-01-30 | St Clements | 2730 | Madison Layton | Software Provider |  | In interface catalogue IF-005: The REG1003 reads Metering Service [S0.SenderID] holds valid previous appointment then Meter Install Date [DI-57] should be < [REG.App End Date] + 10 The way it's curently written suggests MPRS should accept an IF-005 from the previous appoint, even if their ETD was greater than 10 days ago, provided the install date was less than their ETD + 10. E.g the previous MS could send IF-005 two years later with Install date of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then REG1002/REG1019 should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? (Raised as DI 41) | Implemented |  | Interim Release 1 |  | Having looked through IF-005 Dates should be within the appointment date, and current deign does give the ability to go outside this Change the validation rule for REG1003 on events [MeterExchange], [MeterInstall] and [MeterRemoval] to "If Metering Service [S0.SenderID] holds valid previous appointment then [system date] < [REG.App End Date] + 10" Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. Rule amended after review by SCS, to remove second "if" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-42 |  | N/A | 2023-01-30 | St Clements | 2784 | Madison Layton | Software Provider |  | In interface catalogue IF-005: Meter Update should apply validation REG1027 (current MS or prospective MS) not REG1012 (current MS only) to allow the prospective queued MS to update the Meter Type on a SEG change and therfore complete the market segment change and appointment. MHHS-BR-RS-132 . If the SEG prospective appointment was not allowed to update on meterUpdate event code then they would not be able to update the meter type to completed change of market segment, and would not meet the conditions needed to then be appointed in MPRS, their appointment would then lapse and market segment would remain invalid. (Raised as DI 42) | Closed |  |  |  | We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error... | No Change |  |  | None
MHHS-DIN-43 |  | N/A | 2023-01-30 | St Clements | 2732 | Madison Layton | Software Provider |  | In Interface Catalogue, on If-005, REG1002 and REG1019 are duplicates (install/removal dates should be within MS period of ownership). We can only use one of the rejection codes and descriptions, programme should choose which one to keep and remove the other. (Raised as DI 43) | Closed |  |  |  | These are testing slightly different things. The first test (REG1002) is checking that the Metering Service is an eligible party to send the request ie currently appointed OR was at the time of the install (to cover for previous Metering Services updating in the 10 day window). The second (REG1019) is checking that the Install Date is in the Metering Services period of ownership. So you could have that the Metering Service is currently appointed, but that they weren't at the install date. Eg Today is 2nd Feb, Meter installed on 27th Jan, Sending MS was appointed on 1st Feb REG1002 would pass as they are eligible as the currently appointed MS REG1019 would fail as they are not appointed at the time of the install Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-44 |  | N/A | 2023-01-30 | St Clements | 2733 | Madison Layton | Software Provider |  | Should the new rule for meter update in IF-005 also apply to meter history update? If no MAP entries provided, and revised Meter Install / Remove Dates result in no valid MAM History then reject with REGE1014 – MAP Eff From Sequence Error (Raised as DI 44) | Implemented |  | Interim Release 1 |  | Added REG1014 ( MAP History ) to IF-005 MeterHistoryUpdate event | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-45 |  | N/A | 2023-01-30 | St Clements | 2736 | Madison Layton | Software Provider |  | New rule for IF-005 Meter Update REG1017 could be misinterpreted as it currently reads incorrectly - need brackets to correct to how the AND and AND/OR conditions are to be applied If [DI-60] is not null AND Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null) Should read If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null)) (Raised as DI 45) | Implemented |  | Interim Release 1 |  | Clarification of existing design rule Change the validation rule for REG1017 to: "If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null))" picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-46 |  | N/A | 2023-01-30 | St Clements | 2737 | Madison Layton | Software Provider |  | on IF-005 for Meter Exchange and meter install the rule for REG1027 has been changed, but I'm not sure the wording implements the rule intended exactly? Currently it reads as The MS must be the currently appoint MS AND the install date must be > MS EFD AND the MS must not have proposed MS app with SEG scenario in the queue. If not then reject with REG1027 - Metering Service is not currently appointed and does not hold a Prospective SEG Appointment SHould the rule actually read The MS must be the current MS OR the MS must have a proposed MS App in the queue with SEG scenario And then the other part of the rule about install date > MS should be a separate rule (with REG1019 error code). (Raised as DI 46) | Implemented |  | Interim Release 1 |  | Sent to Mike F for validation - SI believe wording in current documentation is correct. Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. I would suggest the wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. DIN-46 – On review we agree, the date test should always be true if REG1019 is satisfied ( with minor clarification update ), so validation rules should be updated as below: Proposed changes: REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 |  | Not discussed at meeting carry to next meeting
MHHS-DIN-47 |  | N/A | 2023-01-30 | St Clements | 2738 | Madison Layton | Software Provider |  | REG1001 on IF-005 does not allow for meters to be removed after a disconnection. Instead should restrict for allow other event codes but allow Status Terminated for MeterRemoval. DES204 CCR-0556 Linked to DI-13 | Implemented |  | Interim Release 1 |  | Rule update required picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-48 |  | DI-048 | 2023-01-30 | St Clements | 2739 | Madison Layton | Software Provider | CSS failure to apply CoS to related secondary MPANs | Unhappy path scenario:- What happens if, for whatever reason, CSS fails to apply CoS to all the related secondary MPANs MPRS receives IF-031 on primary RMP to change agent, MPRS applies this to all seocndary MPANs too But if the CoS was not received from CSS for secondary MPANs that the secondary MPANs would still currently be held for the wrong supplier Would this cause any issues downstream? (Raised as DI 48) | Initial Assessment/Updating |  | Interim Release 6 | 2023-08-09 | CSS Defects issue. Agreed that Risk would be raised and all CSS related issued assessed at a later date | Other | MPAN Ownership | Related MPANs | [5 empty] | 2023-07-14
MHHS-DIN-49 |  | N/A | 2023-01-30 | St Clements | 2740 | Madison Layton | Software Provider |  | Unhappy path scenario:- If MPRS sends a IF-033 but never receives back a IF-034 then the rest of the process will not continue. The Supplier will never receive the IF-035 they are waiting for and the SP would never get appointed by MPRS. Is there a process in place to detect/resolve this scenario? (Raised as DI 49) | Closed |  |  |  | There is a requirement for the Supplier to monitor for any delayed responses and request an update if not received in expected timescales. Reviewed with SCS and agreed ticket can be closed | No Change |  |  | None
MHHS-DIN-50 |  | N/A | 2023-01-30 | St Clements | 2741 | Madison Layton | Software Provider |  | We need clear rules to define what a valid Consent granularity looks like. Current rules don’t mention any validation around EDI. (Raised as DI 50) | Implemented |  | Interim Release 1 |  | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-51 |  | DI-51 | 2023-01-30 | St Clements | 2747 | Madison Layton | Software Provider | St Clements Design Query - DI 51 | We have had some feedback from DNOs asking about how systems will recover from System Misalignment because of data errors or significant downtime? We have the D0204 (Supplier) and D0209 (Data Aggregator) Refresh functions today which are not being replaced with a DIP message equivalent. I am aware of the DIP Replay function, but this wouldn’t be of any help if there were data errors, as the DIP would just be replaying the incorrect data. The Source system would need to re-send the corrected data in an agreed format. I know there is a design principle to move away from bulk loads and refreshes of data, Faster Switching took a similar approach. However today, CSS leans heavily on the MPRS Refresh function to get itself back inline and there are REC CP’s being raised to add a Refresh function to CSS for all parties (first CP being R0067). DNO’s are keen to understand the MHHS Programme’s position on and if Refresh functionality should be built into MPRS for MHHS. | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-20 | Refresh Functionality was rejected by the Working Groups so not in current design. Internal Design Discussion Required on if Programme position has changed on this given CSS Issue / EES Fed via DIP ?? | Other | Supporting Docs | Refresh Process? | [5 empty] | 2023-07-14
MHHS-DIN-52 |  | DI-52 | 2023-01-30 | St Clements | 2748 | Madison Layton | Software Provider |  | For IF-005, REG-1006 and REG1013, would it make sense to include the installation date of the MPAN already in the system in the rejection description too to help MS with triage? | Closed | 2023-04-27 | Interim Release 1 |  | DIN closed as instructed by St Clements. Old comments: Discussed with SCS potential for them to have flexibility on error messages. Industry agreement required. Participant Discussion Required | No Change |  |  |  | 2023-02-23 |  | Not discussed at meeting carry to next meeting
MHHS-DIN-53 |  | N/A | 2023-01-30 | St Clements | 2749 | Madison Layton | Software Provider |  | Requirement on LDSO requirements spreadsheet: MHHS-BR-LD-035 LDSO Maintain DUoS Tariff ID LDSO must set Duos Tariff ID on MPAN creation and maintain DUoS Tariff ID's in line with their Charging Method Statement. This should include updating the Duos Tariff ID, as required, following any updates to Domestic Premise Indicator, Connection Type and Energy Direction Note for MHHS, LLFC ID is being renamed as DUoS Tariff ID to make it clearer what this data item is used for. "BP010B Change of registration data" 250 However missing the respective requirement for Registration Services in the Registration Services Requirements spreadsheet | Closed |  |  |  | Looked through the Registration Services Requirements spreadsheet v4.6 and it looks like DUoS Tariff ID is there - MHHS-BR-RS-091.1, MHHS-BR-RS-121 and MHHS-BR-RS-122 | No Change |  |  | None
MHHS-DIN-54 |  | N/A | 2023-01-30 | St Clements | 2750 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1699 on 15th Sept 2022: On the IF-031 and IF-035 there are a number of "Proposed" Data items. Should MPRS load these and updated the stored data items. Or are these data items only for passing through to Supplier and Service? SCS raised as a design blocker on 7th October 2022 We have some clarity verbally on this but nothing has been formally documented in the design artefacts. This needs to be reflected somewhere in the requirements. | Implemented |  | Interim Release 1 |  | Added "Appoinments - Data" section in REG Notes to highlight what data becomes effective with the appointment. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-55 |  | T4-COM-1738 | 2023-01-30 | St Clements | 2751 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1738 on 15th Sept 2022: the DB02 flow updates multiple data items on the IF-018 in one event. Can multiple EventCode be included in one IF-018 or will MPRS need to generate an individual IF-018 for each EventCode? SCS received a blank response and raised as a design blocker on 7th October 2022 | Closed |  |  |  | Original response was that clarification was to be provided on 24th Oct - is this available? Which document? One at a time | No Change |  |  | None
MHHS-DIN-56 |  | T4-COM-1742 | 2023-01-30 | St Clements | 2752 | Madison Layton | Software Provider | Manual Correction to MHHS data items | Originally raised as T4-COM-1742 on 15th Sept 2022: BSCP604 currently allows LDSO and Suppliers to request manual corrections to Data Items held in MPRS. Will this type of Manual Correction be allowed in MHHS, if yes then this should be added to the business process to capture manual amendments and how these changes are reflected back to DIP users (IF-018 & IF-026, or a new Refresh Message?) SCS received a blank response and raised as a design blocker on 7th October 2022 Another exaple of this: If the MS/DS history is incorrect and cannot be amended via BAU, would the DNO be able to correct this via an exceptional error handling process? | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Internal review required | Requirement correction | MPAN Ownership | CSS Defects | MHHS-BPD005 Data Processing, MHHS-BRS005 LDSO overview |  |  |  |  | 2023-07-14
MHHS-DIN-57 |  | T4-COM-1748 | 2023-01-30 | St Clements | 2756 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1748 on 15th Sept 2022: "Additional information field DI-120 is String200, where the existing DB03 allows a free text field of 2000 characters" SCS raised as a design blocker on 7th October 2022 This was corrected but then in v4.5 artefacts released there was a change back for DI-120 addition infromation field from string 2000 to string 200 in the interface catalogue data catalogue tab reintroducing the issue. For disconnection additional notes MPRS database holds 2000 characters so this field will need to be string 2000 in the IF interfaces (Raised as DI 57) | Closed |  |  |  | Change to the data catalogue included in the 4.7 baseline | No Change |  |  | None
MHHS-DIN-58 |  | T4-COM-1789 | 2023-01-30 | St Clements | 2757 | Madison Layton | Software Provider | Valid combinations of ISD data for MPRS validation development | Originally raised as T4-COM-1789 on 15th Sept 2022: "Valid combinations of data in ISD are critical to the MPRS validation development, we must have these defined and agreed before we can start development" SCS raised as a design blocker on 7th October 2022 | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Elexon is defining the valid combinations of data in the ISD. Parties need to define their own data. | Requirement correction | Supporting Docs | ISD | MHHSP-EM021 ISD Entity Map |  |  |  |  | 2023-07-14
MHHS-DIN-59 |  | T4-COM-1707 | 2023-01-30 | St Clements | 2758 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1707 on 15th Sept 2022: "The Smart DS for Export and Secondary MPANs can be different to the Import/Primary DS as the Customer can choose their own DS for Export and Primary (Smart only)" The IF-031 validation rules have been amended but they are still not corrrectly reflecting the rule. The heading above both rules REG1038 and REG1039 reads: "If event type = [MSApp] OR event type [DSApp] & MPAN Segment is not 'Smart'" This heading should ONLY apply to REG1038 for linked MPANs and should not apply to REG1039 concerning related MPANs It should also have brackets to clarify the logic otherwise it could be misinterpreted e.g. "If event type = [MSApp] OR (event type [DSApp] & MPAN Segment is not 'Smart')" | Implemented |  | Interim Release 1 |  | This seems a valid issue. REG 1039 on linked meters should be allowed for trad meters (eg economy 7) Proposed Change: The logic issue here is that REG1039 caters for related meters, which are applicable to trad as well as smart meters. Remove REG1039 from this validation Change the validation to: "If (event type = [MSApp] OR event type [DSApp]) & MPAN Segment is not 'Smart'" Updated heading above REG1038 and added heading above REG1039 to clarify the validation rule in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-60 |  | T4-COM-1708 | 2023-01-30 | St Clements | 2759 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1708 on 15th Sept 2022: "The Service Appointment Date must be equal to the SSD or there will be a period with no Service" And T4-COM-1776 also on 15th September 2022 "REG1032 - Metering Service Eff From Date [DI-830] is not contiguous - Appointment must be from [Max[Reg.MPAN_SSD] ,[Reg.ExistingMSAppFrmDate]] for a COS, it can only equal the SSD otherwise there will be a gap" This has been applied incorrectly. In IF031 rules REG1032 now reads that the MS/DS prop EFD must be = Max(SSD, existing MS/DS EFD + 1) This would restrict the MS/DS to setting the new EFD to either SSD or the day after the last MS/DS appointment, and all other dates would be rejected. It should read >= not just =. All four refrences to REG1032 in the validation rules for IF-031 references the +1 day after EFD, but the rejection description in the right hand columns for 'scneario not SEG or CoS' section does not reference this + 1. This should be corrected to be consistent with the other rules. (Raised as DI 60) | Implemented |  | Interim Release 1 |  | Original response to 1708: New rules added to cover all scenarios Original response to 1776: Change to be incorporated into design artefact Updated REG 1032 validation in IF-031, original single rule, split into 2 separate rules picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-61 |  | T4-COM-1445 | 2023-01-30 | St Clements | 2760 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1445 on 15th Sept 2022: "There is no mechanism to update the Profile Class. We would assume that this would be updated by the Supplier (with business rules restricting when this should be set) and confirmed on the IF-026. Please can you confirm if this is the intention or if it will be updated through another route. If so, the EES would need to know which PUB would confirm the data item had been updated. " Whilst this is now included in the design the validation rules from D0205 have not been carried over, e.g. PC/SSC need to be a valid combination. ISD will need to contain the valid PC/SSC Combinations (previously MDD Entity 11) and the validation rules in the interface catalogue will need to reference this validation against the ISD valid combinations. (Raised as DI 61) | Implemented |  | Interim Release 1 |  | See also DIN-58, need to find out who is defining ISD validation Updated Interface notes in IF-025 to confirm that there is no Profile Class/ SSC combination checks | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-62 |  | DI-062 | 2023-01-30 | St Clements | 2761 | Madison Layton | Software Provider |  | In the business process diagram for Registration Updates MHHSP-BP010-Change of Registation Data - v4.5, the MPL update section, the C0300 has been changed to C0400 which is incorrect, C0400 is for MAP updates. Address updates are actually sent in the C0600. (Raised as DI 62) Change raised 30 March:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly. | Implemented |  | Interim Release 1 |  | Also in the BPD. MHHS-BR-RS-114 also confirms this should be C0300, this appears to be a straightforward typo. Amend label between Step 20 and Step 30 on BP010A to CSS0300, and update the corresponding BPD description on step 30 Update required:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly in BP010A, BPD010 and in MHHS-BR-RS-114. | Process model correction | Metering Changes | MPAN Updates | MHHSP-BP010-Change of Registration Data MHHSP-BPD010 MHHSP-BRS003
MHHS-DIN-63 |  | DI-063 | 2023-01-30 | St Clements | 2792 | Madison Layton | Software Provider |  | In the business process diag for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 (Raised as DI 63) | Closed |  |  |  | SCS have now confirmed that C0700 is the correct reference - no need to change documentation - agreed to close | No Change | MPAN Ownership | Disconnection | MHHSP-BP007-Disconnection MHHSP-BPD007
MHHS-DIN-64 |  | N/A | 2023-01-30 | St Clements | 2793 | Madison Layton | Software Provider |  | In business process diag for change of data service MHHSP-BP003-Change of Service- Data Service-v4.5 and MHHSP-BP002-Change of Service- Metering Service v3.5, this still makes reference to D0386 in the purple note boxes. This should now have changed to IF-019 (Raised as DI 64) | Implemented |  | Interim Release 1 |  | Update notes on BP002 and BP003 from D0386 to IF-019, and for BPM002 & BPM003 (forward migration) | Process model correction | MPAN Ownership | Change of DS | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-65 |  | N/A | 2023-01-30 | St Clements | 2794 | Madison Layton | Software Provider |  | The business process diagram for change to connection type/market segment has been amended to name only DB01, connection type is set on DB01 but it can then be changed on DB02 (Raised as DI 65) | Implemented |  | Interim Release 1 |  | Update label between step 220 and 225 from "DB-001" to "DB02" | Process model correction | Metering Changes | Market Segement | MHHSP-BP011-Change of Connection Type or Mkt Segment
MHHS-DIN-66 |  | N/A | 2023-01-30 | St Clements | 2795 | Madison Layton | Software Provider |  | In interface catalogue, on IF-031, shouldn't rule REG1036 (MDR app EFD must be after DS app EFD), be applicable to all scenarios including SEG? Currently under section for if not SEG (Raised as DI 66) | Implemented |  | Interim Release 1 |  | Updated validation rule for REG1036 and made applicable to all scenario's in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-67 |  | N/A | 2023-01-30 | St Clements | 2796 | Madison Layton | Software Provider |  | Currently no rule on IF-031 that the SP appointment has to be within the prospective suppliers registration period - just that it can't be past dated. This rule will need to be added. (Raised as DI 67) | Closed |  |  |  | Reviewed with SCS and agreed that this validation is covered by existing rules. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-68 |  | N/A | 2023-01-30 | St Clements | 2797 | Madison Layton | Software Provider |  | If-031 business rule missing If the Scenario is USP, the consent granularity must be the same as the existing consent granularity held within MPRS (Updates should be through IF-025 not through IF-031) (Raised as DI 68) | Implemented |  | Interim Release 1 |  | picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Updated Interface notes in IF-031 to clarify that Registration Service will ignore any differences in Domestic Premise Indicator/ Consent Granularity sent on IF-031 (USP scenario) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-69 |  | N/A | 2023-02-02 | ESG Global | 2653 | Luke Speakes | Software Provider |  | PUB-033 - Block 029 is conditionally mandatory for DCC Commissioned Meters, but includes DI-025 DCC Service Flag with valid values of A-Active, I-Installed Not Commissioned, N - Non Active. The title of the block, which should define whether it is mandatory or not, is not appropriate if a DCC meter has been installed and not commissioned, or is inactive. Propose following SI and SRO design discussion that title of block 029 is revised to conditionally mandatory for 'DCC Smart Meters' | Implemented |  | Interim Release 1 |  | Concludes this can be resolved by a minor wording change to the block title | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 |  | Not discussed at meeting carry to next meeting
MHHS-DIN-70 |  | N/A | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory | Addition of MDR validation rule | Elexon is required to maintain a valid list of Meter Data Retrievers in Industry Standing Data, to allow RegService to validate they're suitably qualified (DCC and SEC) MDRs are being appointed. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Design Agreement is to utilise M16 for this purpose. ISD document updated with details and examples to this effect. | Other | Supporting Docs | ISD | MHHS-EDI-021-ISD_Entities | 2023-02-23 |  | Not discussed at meeting carry to next meeting |  | 2023-07-14
MHHS-DIN-71 |  | N/A | 2023-01-30 | St Clements | 2839 | Madison Layton | Software Provider |  | When would event code [MSDeAppUpdate] and [DSDeAppUpdate] be used for on an IF-037? (Raised as DI 69) | Closed |  |  |  | Reviewed with SCS and it is used to notify the incoming Service Providers when de-appointing and not origanally known. In case of Linked/Related MPANs individual MPANs move through the process. RS need to apply the logic for sending the updated IF-037 to all MPANs. Agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-72 |  | N/A | 2023-01-30 | St Clements | 2840 | Madison Layton | Software Provider |  | Block B018 on IF-034 and IF-035 should not be mandatory - it will only be provided for smart meters. This needs to be set to mandatory for SDS-MDRUpdate only, optional for DSAppSPResponse (Raised as DI 70) | Implemented |  | Interim Release 1 |  | Updated B018 block to be optional for non Smart on IF-034 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-73 |  | N/A | 2023-01-30 | St Clements | 2841 | Madison Layton | Software Provider |  | IF-026/IF-025, added new event code [SSCandProfileClass], but still kept in original [SSC] and [ProfileClass] event codes, should the original two have been removed? Particularly as the B032 group says it's madatory where event code is [SSCandProfileClass] and does not refer to [SSC] or [ProfileClass] individual event codes (Raised as DI 71) | Implemented |  | Interim Release 1 |  | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-74 |  | N/A | 2023-01-30 | St Clements | 2842 | Madison Layton | Software Provider |  | A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a new MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60 (Raised as DI 72) | Implemented |  | Interim Release 1 |  | This appears to be the reciprical change to MHHS-DIN-60 for the response interface Update description to "Check if MDR Eff Date = SSD OR on or after existing MDR Eff From + 1" Update rule to "If [DI-841] <>SSD OR <MDR Eff Date + 1" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-75 |  | N/A | 2023-01-30 | St Clements | 2843 | Madison Layton | Software Provider |  | On IF-035, overidden the description for Data Item 836 incorrectly with the description for Data Item 838 (Raised as DI 73) | Implemented |  | Interim Release 1 |  | Update the definition field based on the description in the data catalogue for DI-836 on IF-035 (Date From which Supplier would like Nominated MDR to take effect) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-76 |  | N/A | 2023-01-30 | St Clements | 2844 | Madison Layton | Software Provider |  | Data catalogue - changed the estimation reason code authoritative source to Registration Service, this data item is not received by, sent by or held by registration services and so the authoritative sourse cannot be Registration Service (Raised as DI 74) | Implemented |  | Interim Release 1 |  | The authoriative source has changed between v4.0 (from Data Service) to 4.7 (Registration Service) - have asked why the change was made, and what the authoritative source should actually be. Source updated to SDS/MDS | Data interface correction | Meter to Bank | Estimation | MHHSP-DES138-Interface Catalogue
MHHS-DIN-77 |  | N/A | 2023-01-30 | St Clements | 2845 | Madison Layton | Software Provider |  | Data catalogue - Added issue 99 items (CT Ratio, Phases etc) DI-170 - DI-180. Was agreed in work off meeting these items are not within the scope of MHHS, to introduce these would require a CR (Raised as DI 75) | Implemented |  | Interim Release 1 |  | these data items don't appear to be used in any interfaces so this could be a relatively simple change to remove 11 items from the data catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-78 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E0404 requirement is blank - row needs to be deleted | Closed |  |  |  | This update was already incorporated into version 5.0 closing it here | No Change | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-79 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E21114 typo - should be VAS Output Retention | Implemented |  | Interim Release 1 |  | change as per description | Technical corrrection | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-80 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHSP-DES138-Interface Catalogue v4.6 - DI-846 Issuing Data Service EZ Name should be scored through in IF/ PUB21 definition | Closed |  |  |  | Completed in V5.0, part can review change as part of Interim Release 2 | No Change | Meter to Bank | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-81 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier | Correction of step in BP020 | MHHSP - BP020 - Volume Allocation Service (ECS) v4.6 - Step 75 to Step 80 references report “REP-00” - needs correcting | Implemented |  | Interim Release 2 | 2023-06-23 | BP020 step 75 to step 80 process flow REP list correction BPD020 step 75 & step 80 detail list of REP's correction | Process Model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions |  |  |  |  | 2023-06-16
MHHS-DIN-82 |  | N/A | 2023-02-09 | SI Design | 2716 | Rob Short | SI Design | Missing listed number of reports in BPD002 | Related to DIN-81 - BPD002 lists number of reports at step 75, BP002 does not reflect this list, missing PO275, PO214 and PO213 | Implemented |  | Interim Release 2 | 2023-06-23 | This relates to BP020 (not BP002), similar to DIN81, reconcile REP list correction on BP020 at step 75 and 80 and reconcile with BPD020 list of REPs | Process model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions |  |  |  |  | 2023-06-16
MHHS-DIN-83 |  | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | BP011 missing PUB-044 flow | A discrepancy with the Interface Catalogue - IF_LIST states MHHSP-IF-044 is sent to Central Settlements, DS, MS, Supplier, LDSO. IF-044 tab states it is sent to Supplier, MDS, LDSO In BP011 the PUB-044 is not sent to DS only Supplier, Settlements and EES | Implemented |  | Interim Release 2 | 2023-06-23 | Add Manage change of segment in LDSO lane on business process BP011C with a PUB-044 flow from step 570 Add new step to BPD011 Interface catalogue is already updated | Process Model correction | Metering Changes | Interface Catalogue | MHHSP-BP011 Change of ConType andor Mkt Segment MHHSP-BPD011 MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-84 |  | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | DES-138 IF List Tab Consistency | IF_LIST states MHHSP-IF-020 is sent to Supplier onlyIF-020 states it is sent to Supplier, Data Service, Metering Service, LDSOIn BP010, the PUB-020 is sent to Central Settlements, CSS, EES, Supplier, Data Service, Metering Service, LDSO.This one looks like its just the Interface Catalogue that needs updating. IF-020 Updated to refect new agreed Routing | Implemented |  | Interim Release 2 | 2023-06-23 | Updated parties receiving PUB-020 in the IF_LIST, updated PUB-020 routing to include MDS for Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-85 |  |  | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory |  | Elexon see DIP qualification for new users being part of market entry post-programme, but want to understand how MHHSP will operate qualification during the programme. This is likely to cover the majority of participants. Discussions with SRO colleagues indicate they are assuming this is a process for the Enduring Service Operator to define. Challenge applies to non-BSC DIP participants (e.g. adaptor providers), and considerations under Issue Group 101. SI design has spoken to at least 4 participants who are operating in this space and seeking to understand how they can engage with SIT and other programme activities as a DIP connection provider (E2E Architecture - 3.3.2) | Closed |  |  |  | To be handled as part of the Placing Reliance document | No Change | Qualification | Qualification | New Process - DIP Qualification for New Users
MHHS-DIN-86 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Invalid Market Segment BP011C requires SMRS to notify the Supplier of an invalid market segment. RegService requirement RS0124 states that SMRS must derive a value for Market Segment based on Connection Type and Meter Type following a Change of Metering, Change of Connection Type (Change of Unmetered Indicator) or Change of Related MPAN relationships. Given that SMRS determines segment as above, when would an invalid market segment occur, giving rise to the processes from step 560 in BP011C? Further, upon receipt of a PUB-045 Market Segment Invalid Advisory Notification, what are the next steps for a Supplier to address the issue? There are no provisions in the IF-025 for Suppliers to update Market Segment. | Closed |  |  | 2023-07-12 | Part of ongoing discussions with Code Drafting team 20/4//23 Code Drafting believe an update needs to be made to the design to update Market Segment via IF-25. This could occur when a Supplier is trying to arrange a change of segment but one of the activities has not completed on time eg the new metering has not been notified. When Registration Service tries to evaluate the segment it may not be compatible. Notification would then go to Supplier to prompt them to chase the required update, in this example chasing the Metering Service to provide the new metering details. Another example is if the LDSO has not notified a change of connection type. The Supplier may also need to send a further SEG appointment if the original has lapsed. | No Change | Metering Changes | Change of Connection Type and/or Market Segment | MHHSP-BP011, MHHSP-BPD011
MHHS-DIN-87 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory | Process clarification for meter removal and de-energisation on same job | Energisation Process Clarification BP009 states that change of energisation status at the same time as meter works means that BP008 will be followed - what is the process when a meter removal and de-energisation are carried out in the same job? Are both D0139 (de-energise) and D0142 (remove meter) and relevant DIP interfaces required. At the moment MEMs only have to send flows relating to meter removal | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Purple Boxes added in BP009 and BP008 to make it clear that Remove/DeEn could still be requested and carried out but MS would need to send two interfaces. Also that DeEn did not need to be notified if meter works completed within same day (ie same rules as today) | Process model correction | Metering Changes | Change of Metering | MHHSP-BP009 |  |  |  |  | 2023-07-14
MHHS-DIN-88 |  |  | 2023-02-09 | RECCo |  | Sarah Jones | Regulatory | Update to Incumbent MS provider for Lapsed Appointments | Update to Incumbent MS provider for Lapsed Appointments Currently BP002 only addresses the positive confirmation of de-appointment from RegService (PUB-037 - step 140/231), but if there is no secured active, there is no subsequent notification to the incumbent. The prospective MS receives a PUB-035 at step 225. How should the incumbent MS determine when the de-appointment has lapsed? | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Part of ongoing discussions with Code Drafting team. It is not expected that the incumbant share the MTD via the IF-035 as early sight. IF-37 is the deappoint code they need to reflect . The Metering Service is appointed until they get de-appointed using a PUB-037. They are only receiving the PUB-035 as notification of who to send MTDs to, it is not intended as a notification of de-appointment. Incumbent Metering Service is a term used to refer to the MS appointed at the point another new SP Appointment is accepted (MS or DS), it shall be the Incumbent Metering Service's responsibility to share MTDs (ADV/Trad) to the incoming party. No change recommend CLOSE | Process Model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Metering Service MHHSP-BPD002 |  |  |  |  | 2023-07-14
MHHS-DIN-89 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Customer Details on De-Appointment The MHHS design currently allows for customer data to be deleted or obfuscated by MS on de-appointment. Has obfuscation been confirmed as acceptable under GDPR? | Closed |  |  |  | Programme has called out the need for data management wrt GDPR. It is for each participant to determine the action required based on their own GDPR Guidelines and policies. |  | All Areas | [6 empty] | 2023-07-14
MHHS-DIN-90 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | MS Appointment for Associated Export Metering Points How will an initial MEM be appointed for a new export MPAN, created post MHHS go live? | Closed |  |  |  | Part of ongoing discussions with Code Drafting team - this is not a Design Issue. Design will operate as described below: The daily process monitoring (BP011C) would pick up any [new] Linked Export MPANs and ensure that the same Metering Service is appointed as the Import MPAN. If the Export MPAN is not linked, then the BAU appointment process can be followed. |  | Metering Changes | Change of Connection Type / Market Segment | MHHSP-BP011, MHHSP-BPD011 |  |  |  |  | 2023-07-14
MHHS-DIN-91 |  | N/A | 2023-02-10 | AWS | 2858 | Duncan Parsons | Software Provider |  | Document MHHS-E2E001 section 3.6 Actor Workflows Summary - Typo in the MSA Outbound. States IF-04, this should be IF-041 | Implemented |  | Interim Release 1 |  | Reference Corrected | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-92 |  |  | 2023-02-14 | RECCo | 2903, 2805, 2911 | Sarah Jones | Regulatory |  | Customer Direct Contract Flag (D053) Multiple tickets - RECCo, ESG and National Grid - all highlighting the same problem. The 4.7 artefacts do not consistently reflect the agreed position that the Customer Direct Contract flag can only be set by the incumbent Metering Service provider. The validation rules on the IF-038 should be updated The requirements for MS (013) and DS (34) in the respective BRS artefacts should be aligned | Implemented |  | Interim Release 1 |  | Added validation rule REG1075 to IF-038 in the interface catalogue Updated requirements in MS-013 and DS-034 in BRS to reflect the agreed position for D053 1/3 - ticket #3035 - SCS supportive of this change, need more detail. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue, BRS001, BRS002 | 2023-02-23 |  | Accepted but split these into two DINs one of the updates to the BRS and deal with as a minor chnge, the other as a major for the Interface Specification change
MHHS-DIN-93 |  | N/A | 2023-02-14 | Power Data Associates |  | Tom | Data Service Provider | Work off Plan D-034D updates for exceptions to Unmetered Supplies | Work off Plan D-034D updates for exceptions to Unmetered Supplies | Implemented |  | Interim Release 2 | 2023-06-23 | 1. Section 2.3 of MHHSP-METH004-UMSDS- EM Functions will be updated to make explicit that the following data items are not required by the UMSDS and as such will be ignored. • Consent Granularity (T4-COM-1857) • Domestic/Non-domestic Indicator (T4-COM-1830/1850) • Distributer Id (T4-COM-1826/1842/1845/1858/1859/1864/1865/1871/1875) • DUoS (T4-COM-1856) • LLF Data (T4-COM-1856) • Domestic Premise Indicator (T4-COM-1830/1850) • Metered Indicator- (D-045) 2. MHHSP-METH001- SDS Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 3. MHHSP-METH002- ADS- Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 4. MHHSP-METH009- UMSO Method Statement should be updated to make explicit that the following data items are not required by the UMSO and should be ignored (list to be reviewed and validated). • Consent Granularity • Domestic/Non-domestic Indicator • Distributor Id • DUoS • LLF Data • Domestic Premise Indicator • Metered Indicator | Method statement correction | Supporting Docs |  | MHHSP-METH004-UMSDS MHHSP-METH001- SDS MHHSP-METH002- ADS MHHSP-METH009 - UMSO | 2023-02-23 | 23/2/23 - Accepted |  |  | 2023-06-16
MHHS-DIN-94 |  |  | 2023-02-16 | ESG | 2777 | Patricia | Software Provider | IF-005 rejections | The IF_009 has 2 event codes: [MPANDisconnection] & [CSSDeRegistration]. [CSSDeRegistration] is listed as having Supplier as Secondary routing however on BP007 there is only reference to the supplier receiving the [MPANDisconnection] flavour of the flow. Please can you clarify which artefact is accurate. MHHSP – BPD009 step 145 states Where the Registration Service has rejected the metering update the DIP will publish the rejection to metering services. Supplier have the option to subscribe to this also. Your response was:- Our reading of this is that regservice will reject the PUB-006 back to sender if the IF-005 fails those rules. So just back to sender, not always meter service or supplier Therefore, does the BPD009 step 145 need to be updated to reflect that as the IF005 can only be generated by Metering Service Smart (MSS) & Metering Service Advanced (MSA) not the Supplier | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Question 1. Supplier will receive both events as outlined in BP007 (See DIN 294) Question 2. BPD009 step 145 updated to show that Supplier cannot choose to receive rejections. A decision was made at the DRG on 29th June to leave the messaging in BPD009 step 145 and instead update the business process model in BPD009 to give Supplier's the option to subscribe to rejections. | Process Model correction | Metering Changes | Disconnection / Change of Metering | MHHSP-BP007-Disconnection MHHSP-BP009 – Change of Metering (Install / Remove / Exchange) MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-95 |  |  | 2023-02-20 | SI Design | NA | Simon Harrison | Programme |  | Typo in the Note box about Auto Alignment of Related/Linked MPANs on the BP002 and BP003 process maps. Change 'Regisatration' to 'Registration' | Implemented |  | Interim Release 1 |  | Update BP002 (& BP003) call out box, also for BPM002 and BPM003 (Forward Migration) | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-96 |  |  | 2023-02-21 | SI Design | 2973 | Arif Jagot | Programme |  | Test-078 - SUPPI -Primary - Means SUPI? | Implemented |  | Interim Release 1 |  | Update Interface Catalogue | Data interface correction | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-97 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.4 | Typo in MHHS-METH001-5.4c "and less than 90 days months different from the UTC Date" - propose removal of months | Implemented |  | Interim Release 2 | 2023-06-23 | Update Method Statement i.e This needs to be 90 days not 90 months the artefact needs to be updated | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-06-16
MHHS-DIN-98 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.5 | Typo in MHHS-METH001 - 5.5 SDS shall use the most recent data a based on the event that triggered the | Implemented |  | Interim Release 2 | 2023-06-23 | Typo error on clause 5.5 within MHHSP-METH001-SDS Validation Estimation v5.0 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-06-16
MHHS-DIN-99 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Working days correction | Clarify that Step 105 in the CoS Transfer read process is Working Days. Currently states 5 days | Implemented |  | Interim Release 2 | 2023-06-23 | Checked with SRO - 5 Working days for Step 105 in process, BPD003C, BR-DS-024.1 and BR-DS-024.2 | Requirement correction | MPAN Ownership | Data Services | MHHSP-BRS001 - SDS Requirements MHHSP-BP003C - Transfer of Reads MHHSP-BPD003C - Transfer of Reads |  |  |  |  | 2023-06-16
MHHS-DIN-100 |  |  | 2023-02-21 | RECCo | NA | Sarah Jones | Regulatory | BP002 to include LDSO as recipient | Step 180 in BP002 and BPD002 does not include LDSO as recipient of traditional meter details as per the wording of the step or the BRS (BR-MS-024) (Code Drafting Log Reference CDD-29) | Implemented |  | Interim Release 2 | 2023-06-23 | Update BP & BPD to align with BRS and add LDSO as recipient of MTDs Updates to BP & BPD002 Forward migration for consistency | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Metering Service MHHSP-BPD002 Forward Migration BP002 and BPD002 |  |  |  |  | 2023-06-16
MHHS-DIN-101 |  | DI-120 | 2023-02-22 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. (Raised as DI 120) | Closed |  |  |  | Included within CSS validation rule update. DUPLICATE See DIN-172 | No Change | MPAN Ownership |  | MHHS-DES138-Interface Catalogue
MHHS-DIN-102 |  |  | 2023-02-22 | St Clements | 2886 | Madison Layton | Software Provider |  | SCS raised the following under MHHS-DIN-7 "MPRS will reject any PUB-031 inlcuding those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist"" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8)" They have followed up with: Just found the change that corresponds to this one in v4.7 interface catalogue – REG0005 in IF-031. Could this also be added to IF-034 so that we can apply the same validation on MDR updates? | Closed |  |  |  | Proposed Change: Add validation "CSS Registration Request ID [DI-849] is valid for Registration Service", with error REG0005 - "CSS Registration Request ID [DI-849] is invalid or unknown" This mirrors a change made in v4.7 to IF-031, agreed as part of the DAG baseline of v4.7 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-103 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory |  | Confirm that D0381 will continue to be used for updates to MPL address. BP010 & BPD010 currently allow emails, SDEP and other agreed forms can be used by Supplier or UMSO to update this - propose that these artefacts are amended to reflect that the D0381 is to be retained (Code Drafting Log Reference CDD-22) | Implemented |  | Interim Release 1 |  | Amend Steps 10, 21, 22 to explicitly use the D0381 rather than current wording | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-104 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Impact of MHHS on SoLR arrangements | Impact of MHHS on SoLR arrangements - possibly needs an Issue Resolution Group discussion to undertake evaluation & impact assessment (Code Drafting Log Reference CDD-23) | Closed |  |  |  | Extensive discussions have been held with Elexon (DIP Manager) to ensure that there is flexibility within the DIP Design to accomdate varied SoLR scenarios. These involve the existing process(s) around change of BMUnits and the ability to transfer ownership of DIP Market Participants. As the solr process does not involve any mass movement / reassignment of MP Identifiers at the MPAN level the core MHHS design is not impacted by Solr per se. |  | All Areas | [6 empty] | 2023-07-14
MHHS-DIN-105 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Related MPAN Business Rules | 1) IF-019 suggests RMP status can be Created or Operational - proposed this can only be Operational for subsidiary MPAN 2) Add validation rule to IF-019 requiring related MPANs to have consistent classification as domestic or non-domestic (reflecting the existing requirements) 3) Clarify what Registration Services should do when MPANs are related/linked and have different MS/MEM providers - is the IF-019 rejected or the MEM for the secondary MEM auto-deappointed? 4) What happens if the IF-019 fails validation by Reg Service at Step 330 in BP010? Design provides no guidance | Implemented |  | Interim Release 2 | 2023-06-23 | 1. Removed reference to Created in the REG1001 validation rule for IF-019 2. We understand there is no existing validation within MPRS and this is not being amended as a result of MHHS implementation. This would require a wider industry change impacting CSS as Domestic Premise Indicator is managed independently of Related MPANs. 3. It would not be rejected, auto-alignment would pick up the discrepancy at the next daily run and de-appoint the export MS and appoint the import MS. 4. As with other rejected flows, the sending party should investigate the error and re-submit as appropriate. | Data interface correction | MPAN Ownership | Change of Registration Data | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-106 |  |  | 2023-02-23 | SI Design | 2955 | Kate Goodman | Testing | IF Routing | Inconsistency in DES138 for UMSO Routing 00-Introduction logs UMSO as the single routing option for Unmetered Service provision, as there can only be one UMSO related to an MPAN PUB-008 provides UMSC, UMSP and UMSI as options for secondary routing This inconsitency needs to be corrected | Implemented |  | Interim Release 2 | 2023-06-23 | IF-008 - Secondary routing rules updated following review with Avanade (see DIN268) |  | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-107 |  |  | 2023-02-24 | SI Design |  | Simon Harrison | Progamme | Update to definition of DI-301 LLF ID in the ESC Reporting Data Catalogue | Definition of DI-301 in the ESC Reporting Data Catalogue needs to be updated as follows 'The Unique Identifier of a set of Line Loss Factors' | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Update to be made in the ESC Reporting Data Catalogue against DI-301 LLF ID it should read as 'The Unique Identifier of a set of Line Loss Factors' | Data interface correction | Supporting Docs | Reporting Catalogue | ESC Reporting Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-108 |  |  | 2023-02-27 | SI Design | 2966 | Kate Goodman | Testing | IF Routing | Ref:MHHSP-DES138-Interface Catalogue v4.7, IF-038, PUB-020, PUB-039. Document says that UM is relevant to these messages but UM thinks it is not relevant. Please clarify what the situation is. Raised in review of MHHSP-872 by Power Data. | Implemented |  | Interim Release 2 | 2023-06-23 | Covered by Secondary routing updates (See DIN268), changes to IF-020 and IF-039 routing. No changes were required to IF-038. The design allows for Customer Direct flags to be set for any Data Service/ Metering Service (ie Including unmetered). |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-109 |  |  | 2023-02-27 | SI Design |  | Simon Harrison | Programme |  | Call out box in BP002/BP003 on Linked/Related MPANs needs to be updated as it includes reference to email/SDEP rather IF-019 as shown in BP010 | Closed |  |  |  | Confirmed - the call out box on BP002/003 needs to be updated Duplicate of DIN-64 | No Change | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service
MHHS-DIN-110 |  |  | 2023-02-27 | SI Design | 2983 | Kate Goodman | Testing |  | MHHSP-BP005-Data Processing-v4.6, Step 50-160 UMSDS is referencing Submit Required UTC period level consumption data (Step 50) with a arrow going to Receive UTC period level consumption data (Step 160) but no reference of IF-021 on the connection between both - reference should be added? | Implemented |  | Interim Release 1 |  | On Process map requires arrow to be labelled as IF-021 from step 50 to step 160 | Process model correction | Meter to Bank | Data Processing | MHHSP-BP005-Data Processing
MHHS-DIN-111 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Originally raised as T4-COM-1691 on 15th Sept 2022: "MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days " Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5 (Raised as DI-76) | Implemented |  | Interim Release 1 |  | Updated to 2 working days | Requirement correction | MPAN Ownership |  | MHHS-BRS003-Registration Service requirements
MHHS-DIN-112 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54 (Raised as DI-77) | Implemented |  | Interim Release 1 |  | Added note to clarify | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-113 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? (Raised as DI-78) | Closed |  |  |  | Agreed duplicate of DIN-29 and can clsoe | No Change
MHHS-DIN-114 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | EES does not appear to have been added to the routing rules tables on the interface tabs(Raised as DI-79) | Closed |  |  |  | Already present in v5 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-115 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On IF-050, this includes linked MPANs in it, but I don’t think these would ever be populated as you cannot link MPAN at MPAN creation. So EES would only ever get Linkage updates on the IF-20 Is there any value of having this therefore in IF-050?(Raised as DI-80) | Implemented |  | Interim Release 1 |  | Removed Linked MPANs and Related MPANs from IF-050 and added explanatory note | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-116 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | For IF-025, block B032 it states it is "MPAN Legacy Info (Mandatory where event is [SSCandProfileClass], and for Traditional Meters / Optional for other Meters)" It should just read mandtory for event code [SSCandProfileClass] and nothing else, it should not be optional for any of the other event codes(Raised as DI-81) | Implemented |  | Interim Release 1 |  | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-117 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?(Raised as DI-82) | Closed |  |  |  | Discussed with SCS and confirmed it is a limitation of swagger output but should be array of MPAN followed by array of meters followed by array of MAPs repeated per MPAN. Awaiting confirmation can close | No Change | Metering Changes | IF-005 JSON | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-118 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | In relation to the Sender Unique Reference, which is constructed as: S-<Interface>-<Participant Id>-<Role Id>-<Date>-<Sequence> (hex) I would like to comment as follows: • Why is the Unique Reference simply constructed using elements that are already contained in the message as distinct values? This just means the sender has to construct it and the receiver de-construct it? • Is the sequence number expected to be reset each day ? • It would be much easier and more logical for the Sequence to be a distinct item in the message? • Why is the sequence specified as hex? • Even given the expected large number of messages, and based on it being a number(13) (defined as Sting), a standard sequence number per Participant and Role would provide 9,999,999,999,999. If this is still seen as a limitation then it could simply be built from the date, e.g. 202301190000000001, giving a provision for up to 9,999,999,999 messages PER DAY from the same Participant / Role combination, which still enables a read every 30 minutes from every MPAN(Raised as DI-83) | Closed |  |  | 2023-06-23 | This is to send a unique reference and is used for auditing purposes. Please note the length of the Sender Unique Reference has been increased at the request of Avanade in 5.1.1. Examples updated |  | MPAN Ownership
MHHS-DIN-119 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | in swagger hub under IF-002 B907 list the B036 block, this is missing numberOfDigitsCumulativeRegister data item(Raised as DI-84) | Implemented |  | Interim Release 1 |  | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue. Swagger will be updated | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-120 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Inconsistency in naming of data item DI-091 In swagger hub: Number-Of-Digits-Cumulative-Register In interface catalogue IF tabs (E.g. IF-002) : Number of Displayed Register Digits In interface catalogue data catalogue tab: Number Of Displayed Register Digits (Cumulative Register)(Raised as DI-85) | Implemented |  | Interim Release 1 |  | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue and updated YAML accordingly | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-121 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0093 comment raised on 12/01/2023 " D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: "It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42 (Raised as DI-86) | Implemented |  | Interim Release 1 |  | Agreed to provide SEG scenario's in IF-005 Use Case guide. currently under review |  | Metering Changes | Change of Segment | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-122 |  | DI-87 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0084 comment raised on 12/01/2023 following the introduction of IF-019 and respective changes in the latest set of released artefacts MHHSP-BP010-Change of Registration Data -v4.5 "Shows Supplier Mastering Import Export Linkage. BSC CP1558 introduced changes to MPRS for the LDSO to manage this via the DB05. IF-019 should go to LDSO who should then produce a DB05 into MPRS." The process diagrams and requirement spreadsheets have been amended to show MPRS loading DB05 as a IF-019 response. DB05 is not a IF-019 response, it is a request from DNO/iDNO to create, amend or remove a import/export linkage. It does not currently have any capacity to include a IF-019 rejection response to trigger a IF-020 rejection response to DIP. (Raised as DI-87) | Implemented |  | Interim Release 1 |  | SCS reviewing preferred option with LDSO's The following changes would be required to the LDSO overview requirements: MHHS-BR-LD-043.3 LDSO Send Import/Export relationship update LDSO must send accepted Import/Export relationship updates to the Registration Service via the appropriate interface DB05 file or other agreed mechanism BP010B Change of registration data 900 MHHS-BR-LD-043.4 LDSO Send Import/Export relationship rejection LDSO must publish rejected Import/Export relationship updates on the Data Integration Platform using the appropriate interface MHHS-IF-020 to Supplier BP010B Change of registration data 900 On BP-010 for Linked Import/Export MPANs the following would be required: 1. Need to add rejected leg from step 900 to DIP 2. Need to add PUB-020 going from the DIP to the Supplier The BPD-010 will need updating accordingly. | Process Model correction | MPAN Ownership |  | MHHSP-BP010-Change of Registration Data MHHSP-BPD010, MHHSP-BRS005, Traceability Matrix
MHHS-DIN-123 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0083 comment raised on 12/01/2023 following the introduction of a new business rule on MPRS in the latest set of released artefacts MHHS-BR-RS-078 "MPRS cannot control how messages are sequenced at CSS and DSP. IF MPRS waits until the DSP responds before sending the Appointment message this could take hours (as this is a batch process) this will result in a delay in the appointment of the MDR. Sequencing requirements should be placed on CSS & DSP to ensure the correct MDR is appointed based on Effective dates provided from MPRS. However, they may not be necessary due to the way this interface works: The C0200 interface uses the PUT Method, which will replace the data held at CSS. Explicit ending of an Appointment is only required for a future dated appointment, this will be sent as one message with the Old and New MDR appointments. For Same Day or Retrospective the new MDR Appointment will Replace the currently set value. This implicitly ends the previous MDR Appointment. On a CoS, the MDR is linked to a Registration not a Metering Point. The previous MDR will end naturally when the Previous Registration becomes securedInactive. An explicit message to end the MDR appointment on the Previous Registration is not required . MPRS will only send two separate updates to CSS when there is a gap in MDR (SDS) appointments. For Example a change of segment to Advanced and then back to Smart. This would need to happen over a short period to generate two messages that could go out of sequence" The MHHS design team rejected with comment "The MHHS design is based upon what was agreed as part of the R044 consultation. This scenario does not reflect our understanding of how the CSS/DCC/DSP interface will work as set out under R044. " This is how C0200 currently works today and the interface is unchanged in R0044. This will put a signfiicant requirement on MPRS that will reduce time available time for other core MHHS development activities with no benefit to industry.(Raised as DI-87) | Closed |  |  |  | No Change - updated in v5.0 | No Change | MPAN Ownership
MHHS-DIN-124 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0089 comment raised on 12/01/2023 "D-021 was meant to give more detail on how L1-L4 validation should be used and provide more error codes for use. This has not been done as far as I can see Blocking resolution to this T4-COM-1749, T4-COM-1769 and T4-COM-1768" Comment was closed as clarified however none of these items have been resolved and we have no dates as to when they will be. comments blocked that were raised initially on 15/09/22 Comment T4-COM-1749: "The Registration Service, as part of its L3/L4 validation should ensure that there is consistency between the data content of the IF-033 issued to the Service Provider and the [returned] content in IF-034 - if this isn't so then message should be returned to Service Provider using ""MSGStatus Message"" mechanism." Does MPRS only need to validate consistency in the data it loads on the IF-033, not the data that is not loaded" Comment T4-COM-1769: "We need validation rules to be defined for this flow, Does not match IF-031, content of the PUB-034 does not match the IF-031. No Proposed Appointment Found, PUB-034, does not link to any Pending IF031s. Define Validation Rules for PUB-034 The 034 content must match the original if-031 content the 034 must have a corresponding IF031 the 034 has already been received for the IF-031 Generic Standard Validation, MPAN exists valid in ISD ETC" Comment T4-COM-2768: "We need some generic codes for standard validation rules such as: Service/Supplier is valid in ISD MPAN exists in MPRS MPAN is not Disconnected Service/Supplier is Valid in MDD (so CSS doesn’t reject updates)" (Raised as DI-89) | Implemented |  | Interim Release 1 |  | Added RMP status check to IF-034 and refined validation rule notes regarding different values received from IF-033 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-125 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | IF Routing | WOA-0091 comment raised on 12/01/23 D-030 "how routing will work in the DIP has not been updated this information is required for our development" MHHS Design Team has closed as clarified however there is still uncertainty around the DIP routing, and there are not dates provided for when the detailed DIP design will be released. This will clock certain elements of development (Raised as DI-90) | Implemented |  | Interim Release 2 | 2023-06-23 | Secondary routing rules updated following review with Avanade (see DIN268) |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-126 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0092 comment raised on 12/01/23 following more infromation around D-022 being clarified "D-022 Following the work off item being agreed on what is required for an MPAN to be traded - it has now been possible to fully assess the optionality of data items in the interfaces Data items still mandatory in interfaces that must be changed to optional: Annual Consumption (IF-001) Incumbent Service Providers (IF-002, IF-033) Incoming MS/DS (IF-037) These are not required at creation, nor at traded, and therefore could be non existent in MPRS when MPRS generates this outgoing IF messages Blocking resolution of T4-COM-1727 and T4-COM-1735" Closed as clarified however none of the issues listed have been resolved Annual consumption still reads madatory on a CoS for IF-001, the issue is MPRS may not have this data item. The item is not required to reach a status of traded, therefore CSS will accept a CoS on this MPAN without annual consumption being populated, and then MPRS will not be able to provide this data item on the IF-001 that results from the CoS. This must be changed to optional OR the definition on what is needed to be traded should be updated to include annual consumption. Incumbent Service Providers is still mandatory on IF-002 for CoS Again as MS is not required to be traded, CSS will accept a CoS request with or without a current MS, and so MPRS will not be able to provide an incumbent MS in these cases. It must be changed to optional or the definition of what is needed to be traded should include MS. Incoming MS/DS is still mandatory on IF-037, there are numerous reasons an appointment may be lapsed, the only change that would gaurantee a new incoming SP that MPRS could send on this flow is a change or SP (CSERV) scenario. For CoS the supplier may not have sent in new appointments, for DEREG there will be no new appoitnments, for SEG the market segment may have changed but the supplier may not have sent in new appointments, same for change of connection type, and for IMPEXP and RELATED the parent MPAN might not have MS/DS appointed at all so there would be no new appointments for MPRS to populate on this flow. This must be changed to madatory ONLY on CSERV (Raised as DI-91) | Implemented |  | Interim Release 1 |  | Discussed with SCS. Covered by clarification on nullable and interface notes- All these issues are resolved by the Mandatory Nullable Solution. Confirmed Annual Consumption block will only be provided where available in Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-127 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 "DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least "Registered", if no DS is appointed then there is already an appropriate Event Code" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone (Raised as DI-92) | Closed |  |  |  | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-128 |  | DI-93 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0095 comment on 12/01/23 "D-009 This is blocking closure of T4-COM-1730. There is a lack of clarity around the treatment of rejection from CSS, between both R044 and the MHHS design artefacts e.g. MHHs-BR-RS-088.1 and MHHS-BR-RS-079 both suggest MPRS would still load the new MDR record and appoint in MPRS despite a rejection from DCC/CSS. Our assumption would be that we do not load a MDR appointment that is rejected from DCC/CSS and we send the IF-035 rejection to notify the DS/Supply of this. However no clarity on what to do if DCC/CSS rejects a MDR end date on a de-appointment T4-COM-1730 was raiseed on 15/09/22 MHHS Design Team Rejected the comment with a statement this is outside of MHHS Scope. How MPRS treats the MS/DS appointment and how it responds over hte DIP is within MHHS design. The requirements we are enquiring about are already included in the MHHS design documents as in scope also. This is a major blocker to MPRS design on MDR appointment processes (Raised as DI-93) | Closed |  |  |  | Discussed with SCS this is a REC requirement. Agreed no error codes will be received, just use a generic response. | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-129 |  | DI-94 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0086 comment on 12/01/23 following the release of the first draft of IF-050 in the revised interface catalogue artefact "Related MPANs and Linked Import Export are not set at MPAN Creation. EES can get these on the IF020 Remove these blocks from IF-050 as they would never be populated" MHHS design team marked as accepted and changed but the blocks still exist in IF-050, these blocks will never be populated and so should be removed from the IF-050 interface(Raised as DI-94) | Closed |  |  |  | Closed - duplicate of DIN-115 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-130 |  | DI-95 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0088 on 12/01/23 "D-011 & D-050 it is still unclear how LLFC and DUoS Tariff ID will be stored and managed in MPRS. DUoS should be an Alias of LLFC and not have its own data item in MPRS. LLFC will be renamed to DUoS Tariff when the old arrangements have ended. LDSO impacts having to maintain two items which will lead to billing issues" Marked as clarified and closed witih a clarification statement to be issued on tuesday 24th January, this clarification statement was not received. Awaiting clarification(Raised as DI-95) | Closed |  |  | 2023-06-23 | Email to Madison to check can close |  | MPAN Ownership
MHHS-DIN-131 |  | DI-96 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 is missing business rules: REG1001 - MPAN [DI-063] is at [REG.RMPStatus] not status Created/Operational. This should apply to IF-025. IF-025 is missing a rule that consent granualiry EFD must not be earlier than supply start date. Consent Granularity EFD must not be prior to current consent granularity EFD The Consent Granularity Energy Direction Domestic Premise Indicator Combination must be valid in ISD(Raised as DI-96) | Implemented |  | Interim Release 1 |  | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-132 |  | DI-97 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 IHD update does not include validation rule 1019, does this mean IHD EFD can be prior to current and effectively cancel out the current IHD status completely, or is it just an error and the rule should be added to interface catalogue for IHD?(Raised as DI-97) | Implemented |  | Interim Release 1 |  | Amendment accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-133 |  | DI-98 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 will not allow a SMSO to be set for a non smart meter "REG1022 - SMSO ID Cannot be set where Market Segment is [Reg.Segement]", would a non smart supplier be able to send a B031 SMSO block, they will need to be able to if they are required to clear an old SMSO by populating SMSO as null(Raised as DI-98) | Implemented |  | Interim Release 1 |  | Added new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements | 2023-03-23
MHHS-DIN-134 |  | DI-99 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 "SSC must be valid in ISD. Rejection reason: REG1044 - SSC must be a valid value in ISD" SSC are not yet populated in ISD(Raised as DI-99) | Closed |  |  |  | Clarified that SSC validation will be based on Frozen MDD. Seperate DIN to cover availability of ISD | No Change | MPAN Ownership |  | MHHSP-EM021 ISD Entity Data Map, MHHSP-DES138-Interface Catalogue
MHHS-DIN-135 |  | DI-100 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Should B032 PC and SSC block on IF-025 only be permitted when theres a traditional meter fitted at the MPAN?(Raised as DI-100) | Closed |  |  |  | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-136 |  | DI-101 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | How is the Green Deal Exists defined. Does this mean there's a green deal linked to the MPAN regardless of dates, does it mean there's a green deal currently active or due to become active, or does it mean there is a currently active green deal assigned to the MPAN? (Raised as DI-101) | Implemented |  | Interim Release 1 |  | Remove Green Deal exists (DI-110) from Data Catalogue and IF-050 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-137 |  | DI-102 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-007 Validation rule "Metering Service [S0.SenderID] holds valid previous appointment then Energisation Status EffectiveFrom Date [DI-034] should be < [REG.App End Date] + 10" The way it's curently written suggests MPRS should accept an IF-007 from the previous appointed MS, event if there ETD was greater than 10 days ago, provided the ES EFD date was less than their ETD + 10. E.g the previous MS could send IF-007 two years later with ES EFD of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then a separate rule should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? Linked to DI-41(Raised as DI-102) | Implemented |  | Interim Release 1 |  | REG1003 validation rule updated in IF-007 to constrain energisation updates to 10 days after the MS appointment period |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-138 |  | DI-103 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-034 Submitted rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD | Closed |  |  |  | Duplicate of DIN-176 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-139 |  | DI-104 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Need clarity on what role code should be used in C0200 for MS and MDR appointments Linked to comment T4-COM-1790 which was accepted as design issue raised but then moved to a work off item "We would like to see some indicative Role Codes and DIP IDs so we can populate development systems with this data " | Closed |  |  |  | Send "MDR" as role code as per Registration requirement. Allocation of DTN MPIDs is a seperate issue | No Change | Registration | Existing EMAR I/F | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-140 |  | DI-105 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 | Closed |  |  |  | Discussed with SCS the IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR. Agreed to close | No Change |  |  | MHHSP-BP003A, MHHSP-BRS003 Registration service requirements
MHHS-DIN-141 |  | DI-106 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 | Closed |  |  |  | RECCo consequential change | No Change |  |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-142 |  | DI-107 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | There currently aren't sufficient rules to ensure that a principal primary MPAN is not also a linked export subsidiary MPAN or that a subsidiary secondary MPAN is not also a principal import linked MPAN. The MHHS design either should accommodate both (would need clarity on how to treat cases where MPANs are BOTH principal and subsidiary) OR new rules should be introduced to prevent this occuring AND cleanse existing cases ahead of migration | Implemented |  | Interim Release 1 |  | Validation rules updated for IF-019 | Missing/incorrect validation rule | MPAN Ownership |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-143 |  | DI-108 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Requirements were uplifted in v4.5 to include logic around market segment on related MPANs MHHS-BR-RS-124.1: Registration Service must, in the case of Related MPANs and following derivation of Market Segment for individual MPANs, update the Market Segment for the Primary MPAN and all the Secondary MPANs based on the following rule: 1. If any MPAN in the Related MPAN Group has a (derived) Market Segment of Advanced, then set the Market Segment for all the MPANs to Advanced and set the Market Segment Valid Flag to "Yes" for all the MPANs This specifically cites related primary/secondary and does not mention linked import/export associations at all. But then another requirement implies maybe it should have done: MHHS-BR-RS-127: Registration Service must , in circumstances where the derived market segment is invalid (and has not been overridden by Linked/Related MPAN logic ) Should MHHS-BR-RS-124.1 have applied to linked import/export associations too or is it intended solely for primary/secondary related MPANs? | Implemented |  | Interim Release 1 |  | This should only apply to Related MPANs. Updated RS-127 | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-144 |  | DI-109 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131 This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to: Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. | Closed |  |  |  | Duplicate See DIN-169 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-145 |  | DI-110 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. | Implemented |  | Interim Release 1 |  | Added L as valid value for DI-979 in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-146 |  | DI-111 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. | Implemented |  | Interim Release 1 |  | Agreed with SCS to reuse STD Error Response Section in IF035 to communicate Lapsed Reason . See DIN-145 for summary of updates | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-147 |  | DI-112 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-008 response block is listed as mandatory, however on disconnection the MPAN is de-energised by MPRS automatically. The supplier cannot de-energise after disconnection on the IF-007, it must be automatic at MPRS as per The de-energisation needs to be communicated on the IF-008 but it is not in response to an IF-007 and so we cannot populate the response block. | Implemented |  | Interim Release 1 |  | Data interface change agreed. Added Interface note to IF-008 to cover forced de-energisation changes by Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-148 |  | DI-113 | 2023-02-10 | St Clements | 2864 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-113 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { "confirmingMpid": "string", --* "registrationId": "string" --*, "updateSucceeded": boolean --* } Suggest that DI-0980 is removed from B066 | Closed |  |  |  | Discussed with SCS and agreed to close - note no error codes returned from CSS so will provide generic error code | No Change |  |  | MHHSP-DES138-Interface Catalogue, JSON, YAML
MHHS-DIN-149 |  | DI-114 | 2023-02-10 | St Clements | 2865 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-114 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 On IF-038 validation "REG1073 - Customer Direct Contract already exists for MPAN [DI-063] for that period" The respective validation rule for this states: If Contract End Date [DI-145] <= Max existing active MS contract end dates [Reg.MAX_DCMS_Enddate], EXCEPT IF requesting MS [S1.SenderID] = Currently Active Direct MS [Reg.CurrentActiveDC_MS_DIPID] AND Contract End Date [DI-145] <= existing active MS contract end date [Reg.CurrentDCMS_Enddate] This rule doesn't fully prevent overlapping appointments as does not cover where the MS is not currently contracted MS and ETD > current ETD which should also be rejected. Think a simpler rule would cover this scenario more fully e.g. If there is an active contracted MS/DS, and the submitting MS/DS does not match then reject And then ETD can be greater or later than current ETD for the currently contracts MS/DS anyway so doesn't need specifying? | Closed |  |  | 2023-06-23 | SRO Team do not belive that a change is required. |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-150 |  | DI-115 | 2023-02-10 | St Clements | 2866 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-115 in our log In some place on IF-038 tab there is reference to a future customer direct contract e.g. "OR requesting MS [S1.SenderID] <> Any future Direct MS [Reg.FutureDC_MS_DIPID] " "extended dates will be subject to checking if another Service Provider has registered a separate Customer Direct Contract covering the same period" - this can only happen if there's a future appointment "AND ALSO removing all future periods which may or may not have been accepted and recorded previously." As there is no Effective From Date included in the flow MPRS will store an Effective From Date of the system date at the time of creation of the customer contract indicator. It will not be possible to set one to start in the future as the IF-038 does not include effective from date. Is this the same understanding as the MHHS Design Team? | Closed |  |  | 2023-06-23 | As per DI-149 above SRO Design Team do not belive that any changes are required |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-151 |  | DI-116 | 2023-02-10 | St Clements | 2868 | Madison Layton | Software Provider |  | Just spotted a change in v4.7 and raised in our log as DI-116 Artefact: MHHSP-BP010-Change of Registration Data -v4.7 under MPL and GSP Group amendment section, DB02 has been amended in v4.7 to DB002. DB002 is not correct, DB02 was the correct name For reference the DB flows only ever have one 0 in, there is DB01 (MPAN creation), DB02 (MP updates), DB03 (Disconnection) and DB05 (Import/Export Linkages) | Implemented |  | Interim Release 1 |  | BP010A step 10 flow name change to DB02, BP010B step250,step440, Step560 flow name change to DB02, and update BPD descriptions to DB02. | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-152 |  | DI-117 | 2023-02-14 | St Clements | 2912 | Madison Layton | Software Provider |  | On looking more closely at the validation rules for IF-019 spotted a few issues. IF-019 REG-1061 rule for Related Create event code appears to be written incorrectly. The rule and rejection description don't quite align. Rule: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) are not currently part of an import/export relationship Rejection reason: REG1061 - Prosposed MPAN(s) [DI-073] / [DI-074] are already part of a Related MPAN Relationship Should the rule read: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) is currently part of a related primary/secondary relationship? The rule and descriptions also don't appear to fully align for some in import/export section too - REG1052, REG1055, REG1057 and might need some minor tweaks to correct. | Implemented |  | Interim Release 1 |  | REG1061, 1052 and 1055 rules updated. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-153 |  | DI-118 | 2023-02-14 | St Clements | 2913 | Madison Layton | Software Provider |  | On working on detailed design for Related MPANs, noticed the IF-019 interface is missing a rule that the Secondary MPAN must not be a Primary in another Relationship. You could expand REG1064 to include this as the description sounds like it should have been covered here. Rule: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN Description: REG1064 - Proposed Secondary MPAN [DI-074] is already part of a different MPAN Relationship Could amend rule to: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN OR [DI-074] is already in a relationship as a Primary MPAN | Implemented |  | Interim Release 1 |  | REG1064 validation rule updated | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-154 |  | DI-119 | 2023-02-15 | St Clements | 2919 | Madison Layton | Software Provider | IF-019 validation gap on primary and subsidiary MPAN | On further detailed design we’ve spotted a potential design gap. Currently it is possible to enter a state where an MPAN is both a primary and subsidiary MPAN at the same time (e.g. Primary but also export linked or Secondary but also import linked). The current MHHS doesn't accommodate an MPAN being in both states at the same time. We’ve already looked to add rules to try to mitigate this on DB02/DB05 internal flows but would need additional rules on IF-019 to fully prevent this scenario occurring. Rules we think are required: 1. On receipt of IF-019 with event code RelatedCreate or RelatedAdd, the primary MPAN must not have energy direction of Export 2. On receipt of a IF-019 with event code RelatedCreate or RelatedAdd, any listed secondary MPAN must not in an active Import/Export relationship as the Import MPAN 3. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Import MPAN must not be in an active relationship as the secondary MPAN 4. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Export MPAN must not be in an active relationship as the primary MPAN | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Agreed with SCS that, changes would be made to support Rules 1 and 4. Validation Rules updated accordingly with new Error codes (REG1067/1068) created to support. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-155 |  | DI-120 | 2023-02-15 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. | Closed |  |  |  | see also DIN-172/173. Included in 5.1 DUPLICATE See DIN-172 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-156 |  | DI-121 | 2023-02-24 | St Clements | 3078 | Madison Layton | Software Provider |  | We have logged a new design issue under DI-121. IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP | Closed |  |  |  | Duplicate of DIN-173 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-157 |  | DI-122 | 2023-02-27 | St Clements | 3090 | Madison Layton | Software Provider |  | New design issue (SCC Ref DI-122) for the IF-005 related to REC CP R0032. The current v5.0 validation in the IF-005 does not include the new validation introduced with REC CP R0032 (R0032 is approved and being implemented in the D0312 this June): NEW REC CP R0032 Validation: V Rejected – ESME ID already exists within MRPS and does not match Removed Meter, Associated Import/Export MSID or Related MPAN W Rejected - MSN relates to a Smart Meter Type and the ESME ID is NULL X Rejected – ESME ID Format is Invalid Y Rejected – Number of Displayed Register Digits is NULL and the MSN relates to a Smart Meter Type Z Rejected – Non-Smart Meter Type with Number of Displayed Register Digits populated AA Rejected – Meter Location is invalid AB Rejected – Non-Smart Meter Type with ESME ID populated AC Rejected – Number of Displayed Register Digits is incorrect IF-005 Validation: V not covered, needs to be added as a Level 5 Validation Rule W is already covered by DI-085 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) X is already covered in DI-085 population notes (Level 4 validation RCP1023 Msg Contains Invalid Valid Value Combination(s)) Y is already covered in DI-091 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) Z is not explicitly covered, suggestion: add to DI-091 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AA is covered in the population notes AB is not explicitly covered, suggestion: add to DI-085 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AC not covered, Suggestion: add the following population note from R0032 to DI-091: Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” Summary Please add the following Changes to the IF-005 to align it with the D0312 validation and maintain the same level of Smart Meter data quality in the Registration Service: New Level 5 Validation rule for DI-085 implementing V from the D0312. ESME ID must be unique within MPRS unless it’s a Linked MPAN where the same Smart Meter can be shared across Linked MPANs New population note for DI-091, only to be included for Smart Meter Types New population note for DI-085 , only to be included for Smart Meter Types New population note for DI-091, Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” | Implemented |  | Interim Release 1 |  | New Validation Rules added to IF doc to ensure full coverage and alignment with CP Error codes described | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-158 |  |  | 2023-02-27 | Elexon | 2908 | Derek Weaving | Central Body |  | As part of the Performance Assurance Working Group discussions on Supplier Charges, we are exploring the use of CCCs to categorise the data for future charges. It is noted that Settlement Period Quality Indicator referenced in the VAS Method statement is for illustrative purposes and would welcome clarity on the following: · What is the intended process to populate the Settlement Period Quality Indicator in the initial ISD Table? · What would be the process to be involved in those activities to determine the categorisations should additional CCCs be required? | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Recommending a change to this ISD Data Item: Settlement Period Quality Indicator to be set as per Appendix 1 of MHHSP_METH007 MDS_Method_Statement v5.0 This data item need to be changes to something like ‘Valid Settlement Period Quality Indicator Set’ and the field size needs to be increased. The data catalugue will need the revised data item and the field length will need increasing from 20 to at least 50. This Item also appears in some interfaces that will need t be updated This is because it represents a set of SPQIs. The initial intention is to populate as per the table and check if any new SPQIs have been introduced in the baseline design Method Statement that are not covered. If new CCCs are introduced the appropriate flags for each new CCC would need to be agreed. However, it is likely that another dimension to the table below would need to be introduced to facilitate new CCCs. |  | Meter to Bank | Volume Allocation Service | MHHSP-METH006_VAS_Method_Statement ED021 ISD Entity spec MHHSP-DES138-Interface Catalogue ECS report |  |  |  |  | 2023-07-14
MHHS-DIN-159 |  |  | 2023-03-01 | ENWL | 2994 | Paul Band | Network Business | Interfaces for UMSO | DES-138 Interface Inconsistencies vs BSCP7XX for UMSO Discussions with ENWL have highlighted a number of inconsistencies in the Interface Catalogue when it comes to routing for UMSO's. DIN-106 also refers. UMSO is not listed as a recipient in DES-138 for the PUB-008, but this is in the draft BSCP and should be added to the PUB UMSO is not listed as a recipient in DES-138 for the PUB-020, but this is in the draft BSCP - this is not needed in the BSCP as there are no unmetered Related MPANs UMSO is not listed as a recipient in DES-138 for the PUB-035, but this is in the draft BSCP - view that it is unlikely for this flow ever to be used as the appointment will not trigger any processes to need a subsequent update UMSO Is listed as UMSI, not UMSO in PUB-036 in DES-138 UMSO is listed as UMSC, not UMSO in PUB-018 in DES-138 The IF_LIST tab should be reviewed for consistency | Implemented |  | Interim Release 2 | 2023-06-23 | As with DIN-106, there are inconsistencies in the Interface Catalogue for UMSO routing. This has been compounded by a review of the draft BSCP for UMSO, which has added a number of PUB flows going to UMSO that aren't currently in the catalogue. Covered by updated secondary routing rules (see DIN268) Design to check requirements in BSCP and MHHS BPs and ensure the interface catalogue reflects a consistent approach | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue and possibly related business processes and descriptions E2E001 |  |  |  |  | 2023-06-16
MHHS-DIN-160 |  |  | 2023-03-14 | Ovo Energy | 2862 | David Morley | Supplier | BP009 flow addition | Steps 205 and 210 in BP009 wont be completable in the event that theres no comms. I think the process would be workable if there was an exception route here - see red arrow below. | Implemented |  | Interim Release 2 | 2023-06-23 | Update Steps 205 and 210 in BP009 with "Comms Available" line label add flow from step 205 to step 215 with “Not Commissioned / No Comms” line label | Process Model correction | Metering Changes | Change of Metering | MHHS-BP009 |  |  |  |  | 2023-06-16
MHHS-DIN-161 |  |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 requirement correction | MHHS-METH001-5.4c Please confirm the requirement: “where daily advance records are available [either in the past or future] and less than 90 days months different from the UTC Date requiring a daily advance - use the mean actual Meter advance from the closest [4] weeks for the same Day Type (as defined in ISD).” | Closed |  |  | 2023-06-23 | Duplicate of DIN 97. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-162 |  |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 typo | MHHS-METH001-5.5 typo “Where DAEs are required to be calculated the SDS shall use the most recent data a based on the event that triggered the estimation.” | Closed |  |  | 2023-06-23 | Duplicate of DIN 98. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-06-16
MHHS-DIN-163 |  | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Conditionality Rule for B037 | It is not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure it is unclear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" | Implemented |  | Interim Release 2 | 2023-06-23 | Updated conditionality rule for Block B037 in IF-001, IF-002, IF-033, IF-036: to show that Either DI-075 (Primary MPAN) or DI-079 (Secondary), and not both, should be populated where MPAN (DI-063 above) is part of a group of Related MPAN. |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-164 |  | DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0093 comment raised on 12/01/2023 "" D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692"" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: ""It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period"" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42" | Closed |  |  |  | "This requirement stands - review with SCS in light of SEG scenario. We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error...". Reviewed with SCS and agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-165 |  | DI-122 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | See separate sheet Duplicate of DIN-157 | Closed |  |  |  | CR required to add rules in line with CP R0032 Added Miscellaneous Data Validation to IF-005 to cover REC CP R0032 validation rules Wrapped up into design teams main CR Doesn't need to be raised by SCS | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-166 |  | DI-77 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54" | Implemented |  | Interim Release 1 |  | Added clarification to REG Notes re Consent and Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-167 |  | DI-78 DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? " | Closed |  |  |  | Agree you can't. Could update 1032 rule for USP? Duplicate see DI-29 | No Change
MHHS-DIN-168 |  | DI-92 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 ""DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least ""Registered"", if no DS is appointed then there is already an appropriate Event Code"" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone | Closed |  |  |  | CR for new functionality. "Already covered by no MS/DS appointed - MPRS would try to align MS/DS with principle and couldn't as there's no registration to align this to. Need an extra check that can only autoappoint if there's a registration to prevent MPRS crashing Maybe one for DRG? Jon at RECCO for consequential change? Agree not to build for this scenario as this would be an edge case and close | No Change
MHHS-DIN-169 |  | DI-109 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to:Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. | Implemented |  | Interim Release 1 |  | Simplified MHHS-BR-RS-131 on when to lapse a SEG appointment | Requirement correction | MPAN Ownership |  | MHHSP- BRS003, MHHS-BR-RS-131 | 2023-03-23
MHHS-DIN-170 |  | DI-110 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. | Closed |  |  |  | Duplicate of DIN-145 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-171 |  | DI-113 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { ""confirmingMpid"": ""string"", --* ""registrationId"": ""string"" --*, ""updateSucceeded"": boolean --* } Suggest that DI-0980 is removed from B066" | Closed |  |  |  | Agreed with SCS being retained but due to optionality may have to populate text e.g. contact DSP. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-172 |  | DI-120 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. | Implemented | 2023-04-27 | Interim Release 1 |  | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-173 |  | DI-121 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP | Implemented | 2023-04-27 | Interim Release 1 |  | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-174 |  | DI-72 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a Submitted MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60" | Implemented |  | Interim Release 1 |  | "Agreed- doc updates MDR can have gaps between DS EFD and MDR EFD" Updated REG1083 validation in IF-034 so that it allows MDR Effective from dates >= SSD/ DS Eff From date/Existing MDR Eff from date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-175 |  | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" | Closed |  |  |  | Duplicate entry | No Change | MPAN Ownership
MHHS-DIN-176 |  | DI-103 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-034 new rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD" | Implemented |  | Interim Release 1 |  | Agreed -doc updates Updated REG1082 to apply for both [SDS-MDRUpdate] and [DSAppSPRepsonse] events in IF-034 | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-177 |  | DI-105 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 " | Closed |  |  |  | "Reason for IF-035 is to trigger when SDScan send the Meter info" & The IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR Agreed with SCS no changes are required, they now understand the context agreed to CLOSE | No Change | MPAN Ownership |  | MHHSP-BP003A
MHHS-DIN-178 |  | DI-106 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | MS missing a requirement to send MS updates to CSS | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 | Closed |  |  |  | Closed as discussed with SCS that this is out of scope for MHHS Programme. | No Change | [7 empty] | 2023-07-14
MHHS-DIN-179 |  | DI-111 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. | Closed |  |  |  | Duplicate of DIN-146 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-180 |  | DI-125 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 the Meter Removal is currently not permitted for a prospective MS Is it possible for the MS to need to remove two meters and replace it with one? In which case meterexchange would only allow them to do part of this process (remove 1 and add 1) but not complete it, so SEG could not complete. Should meter removals therefore be allowed for prospective MS? (REG1019) | Implemented |  | Interim Release 1 |  | Revised REG1019 and added REG1027 for MeterRemoval event in IF-005 | Requirement correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-181 |  | DI-126 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Missing Rule on If-005: MAP EFD must not be > removal date | Implemented |  | Interim Release 1 |  | Added new rule for MeterUpdate and MeterHistoryUpdate events so that MAP EFD must not be > removal date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-182 |  | DI-127 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 On exchange - the MAP and IHD groups are for new installation not removed meter - does this need to be clarified? | Implemented |  | Interim Release 1 |  | New note added to IF-005 to clarify that only the newly installed MAP and IHD information is required on MeterExchange | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-183 |  | DI-128 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-005, IHD EFD missing validation in IF-005 (Between install and removal date) | Implemented |  | Interim Release 1 |  | Covered Release 5.1, IF-005, IHD EFD missing validation added | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-184 |  | DI-129 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-005 incorrect validation rule: REG1010: On event code Meter exchange and Meter Install rule states MAP EFD >= Install date, it should be = not >=" | Implemented |  | Interim Release 1 |  | IF-005: Updated to REG1010 (MAP Eff from date check ) to = install date for MeterInstall and MeterExchange | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-185 |  | DI-130 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | It should not be possible to change MDR EFD once set. Need validation rules to enable MPRS to reject if IF-034 is submitted with current MDR but a different EFD. | Implemented |  | Interim Release 1 |  | Agreed - doc updates Covered by L3/4 validation as per updated Validation rule notes | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-186 |  | DI-131 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031, there is currently not enough validation to ensure on a SEG, that the same SP isn't appointed for the current registration. Need additional validation rule: If scenario SEG and current supplier, then SP must not be current SP. | Implemented |  | Interim Release 1 |  | Agreed - doc updates Updated validation rule Added REG1095 in IF-031 to check different Data Service proposed for SEG appointment | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-187 |  | DI-132 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Supplier inability to appoint MS/DS for Principal and Subsidiary MPAN | Unhappy Path Scenario: Receive IF-031 for MPAN that is both Principal and Subsidiary MPAN at the same time. This will be rejected as per REG1038/REG1039 Supplier will be unable to appoint MS/DS for the MPAN or any related/linked subsidiary MPANS. | Closed |  |  |  | Closed, there is an existing to prevent this scenario happening going forward. Agreed with SCS to raise examples in the Data Cleanse Forum. | No Change | [7 empty] | 2023-07-14
MHHS-DIN-188 |  | DI-133 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031 the rule REG1030 reads [DI0-828] in not a valid UMSO in DNO [DI-108]/[DI-109] This should read LDSO not DNO | Implemented |  | Interim Release 1 |  | Tied up with If-005 rejection description flexibility action Change REG1030 to read: REG1030 - [DI0-828] in not a valid UMSO in LDSO[DI-108]/[DI-109] SC change incorporated into 5.1.1 | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-189 |  | DI-134 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On IF-031, REG1036 is written to only apply to USP when it should apply to all scenarios? ""Proposed MDR Date [DI-836] >= [REG.MPAN_SUP_SSD] However don't think this rule is required at all as this is already covered under the REG1036 rule that MDR Date < DS EFD? Linked to DI-66" | Implemented |  | Interim Release 1 |  | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-190 |  | DI-135 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-034 missing validation rule REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational | Implemented |  | Interim Release 1 |  | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-191 |  | DI-136 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Addition of validation rules to MPRS to restrict Retrospective changes | MPRS does not currently prevent Retrospective changes to DUoS Tariff ID or Connection Type. Should MPRS add new validation rules for these items to restrict Retrospective changes? Please can you update DIN-191 to include Disconnection Date & Export Association. We don't currently have any restriction on how far these data items (and the others in DIN-191) can be back dated. This is a retrospective change through the DB interface and not a Manual Amendment. There are no retrospective periods for the following data items, this means the data items could be changed earlier than the settlement window and cause issues for settlement. There are restrictions that these data items must be within MS/Registration periods where appropriate, but the EFD/SSD could still be years into the past. - MDR EFD, - MS EFD, - DS EFD, - IHD Status EFD, - PC EFD, - SSC EFD, - Energisation Status EFD | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Internal review to take place as to whether DUOS Tariff ID updates should be retrospective. LINKED TO DIN-056 above | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-192 |  | DI-137 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | For If-031, scenario SEG, the business process diagram/requirements only describe the appointment lapsing once reaching it's SSD if no SA is received. If we receive a cancellation we would like to lapse the appointment at that point in time (it cannot become secured active after being cancelled) and not wait until the SSD to do this. | Implemented |  | Interim Release 1 |  | Added new requirements to BRS003, MHHS-BR-RS-24.1 and 58.1 | Design Ambiguous | MPAN Ownership |  | MHHSP-BRS003-Registration Requirements | 2023-03-23
MHHS-DIN-193 |  | DI-138 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | The YAML name for metered indicator (Data Item 127) is meteredUnmeteredIndicator. This is then set to true of false. It isn't clear whether true means it's metered or unmetered due to the naming convention. It should be named meteredIndicator instead to make it clear true means metered, false unmetered. | Implemented |  | Interim Release 1 |  | Updated YAML details in the Data Catalogue for DI-127 Metered Indicator. Updated YAML accordingly Updated data catalogue/ YAML | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-194 |  | DI-1 | 2023-03-15 | St Clements | 4475 | Madison Layton | Software Provider |  | For IF-035 what is Event Code [IMS-SendMTD] intended for? If intended for sending to old MS then this should be done via secondary routing on the original IF-035, not via another separate IF-035 message produced by MPRS with different event code. | Closed |  |  | 2023-06-23 | This message is effectively a copy of the DSAppAccepted AND/OR MSAppAccepted but sent to the Incumbent (current) Metering Service to act as a trigger for that MS to send MTDs. This should be created by MPRS. Requirements MHHS-BR-RS-053 and MHHS-BR-RS-019 cover Registration Service sending this. Message to check and close | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-195 |  | DI-76 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Originally raised as T4-COM-1691 on 15th Sept 2022: ""MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days "" Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5" | Implemented |  | Interim Release 1 |  | Agreed doc update Also in Reg Notes tab Updated validation rules and Reg notes Updated REG1037 in IF-031 to 2 workings days and updated REG notes, to align with process and requirements | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-196 |  |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Updates are required to clarify nullable fields | Implemented |  | Interim Release 1 |  | Updates to Interface catalogue includes changes to interfaces and block data items which are present and can be null 1. MHHSP - ERI011A - ECS Reports - Internal v5.1: The data catalogue is the only tab that has been updated 2. MHHSP - ERI011B - ECS Reports - External v5.1: The data catalogue, DIP_Common, MHHS-REP-003 and MHHSP-REP-006 have been updated |  | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue, MHHSP-E2E001 End-to-End Solution Architecture MHHSP - ERI011A - ECS Reports - Internal MHHSP - ERI011B - ECS Reports - External | 2023-03-23
MHHS-DIN-197 |  |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Decision taken to document digital signing of interfaces outside of the interface document. | Implemented |  | Interim Release 1 |  | Remove Z0 and ZI blocks from all interfaces. Signing process will be documented in the Code of Connection document. | Technical corrrection | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue Code of Connection | 2023-03-23
MHHS-DIN-198 |  |  | 2023-03-15 | Large Suppliers |  | Haz Elmamon | Large Suppliers | Complex Meter Site | Clarification on complex meter site, passed down from DAG as part of the work off plan, Haz to gather concerns for discussion at DA. LSC Rep provided information to the issue on 22-Mar-23 | Requires Industry Work Group review |  | Interim Release 6 | 2023-10-18 |  |  | MPAN Ownership | [6 empty] | 2023-07-14
MHHS-DIN-199 |  |  | 2023-03-23 | BGAS | 3460 | Neil Strange | large Suppliers |  | Participant wishes to see the use of standardisation in the interfactions between the SDS and sub roles MDR PSS | Closed |  |  |  | Closed based on recommendation for programme CR to be raised by the Large Supplier Rep | No Change | Supporting Docs | SDS Validation / Extimation | MHHS-DES138-Interface Catalogue
MHHS-DIN-200 |  |  | 2023-03-24 | CGI | 3489 | Chris Beard | Software Provider | Hierarchy definition for selecting correct register reading in the case of multiple readings for the same settlement period | If there are multiple register readings available for the same Settlement Day, where is the hierarchy defined for selecting which should be used? Is this solely based on Reading Method (i.e. 1. A – Actual, 2. C – Customer, 3. E – Estimated by SDS, 4. S – Estimated by Supplier) or is it dependent on other factors such as the Event Code in the IF-041 ([ReadingRemv], [ReadingInstl], [ReadingEnergisationChg], [ReadingCOR], [ReadingOnSite], [ReadingCOS], [DSEstimate], [SupplierAgreedCOS], [ReadingOverride], [ReadingRemote])? | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Reading methods do not apply to Register Readings - recommendation for DIN to be closed. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-201 |  |  | 2023-03-24 | ESG | 3529 | Patricia Parker | Software Provider |  | IF-033 Validation for population into the IF-034 The receiving party business validation rules state “Each Service Provider will need to determine their own validation criteria when processing Appointment Requests. The list below is intended to cover a number of potential possibilities based on the data items made available, and not to suggest that Service Providers needs or should perform such validations.” But should the DI-143 ‘Service Provider Proposed Appointment Response Code’ not form a valid set list (ENUM Vals) in the Data Catalogue so that all parties are working to the same list of applicable codes, rather than this field being a string with a length of 200 field? | Closed |  |  | 2023-06-23 | IF-033 has been updated as part of Interim Release 1 and the ENUM Vals will not be updated this is because we will have dynamic error messages which cannot be enumerated. |  | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-202 |  |  | 2023-03-24 | ESG | 3513 | Patricia Parker | Software Provider | Operational Choreography 60 minute turnaround | Registration Responses in connection with the PUB-31 given the NFS requirement is a 60-minute turn-around time. Within the Operational Choreography there is requirements OPC-140: From our understanding this means that when suppliers receive the PUB_032 from the Reg Service rejecting the appointment Request suppliers then have 60 minutes to re-issue a fresh IF_031 appointment. For example, there is a rejection code for 'CSS Reg ID not known', this would suggest that a party is out of sync and would need investigating especially as in this case, the REG ID would have previously been provided on PUB- 002, DI-849 and CSS is the master of the REG ID and not the Registration Service. | Implemented |  | Interim Release 2 | 2023-06-23 | Added suggested text to Ops Choreography. Suggested text is "It is noted that some requests may require manual work and may be as a result of incorrect appointments from the Supplier. The expectation will be 90% of requests are systemically processed within 60 minutes with the residual being processed by the end of the following working day". | Doc Ref correction | Supporting Docs | Operational Choreography | MHHS_OPC001_Operational_Choreography |  |  |  |  | 2023-06-16
MHHS-DIN-203 |  |  | 2023-03-24 | CGI | 3502 | Chris Beard | Software Provider | mapping of Estimation Reason Codes to estimation Methods | MHHSP-METH001 M-13. Can you provide a definitive mapping of Estimation Reason Codes to estimation Methods? For example, LTV to Method 11. When should an SDS use Estimation Codes such as Opt Out, Comms. Fault. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated METH001 section 7.3 to reflect Estimated Methods to Estimated reason codes | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001 |  |  |  |  | 2023-06-16
MHHS-DIN-204 |  |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | De-energised sites | MHHSP-METH001 M-3. Which estimation Method should an SDS use for de-energised MPANs that would result in an estimation code of ‘De-Energised’? Without a specific Method statement to cover de-energisation, we will end up estimating consumption. | Implemented |  | Interim Release 2 | 2023-06-23 | Added Method 13 to reflect de-energised sites within METH001 and updated section 2.29 on METH002. | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001 |  |  |  |  | 2023-06-16
MHHS-DIN-205 |  |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | Removal of Estimation Reason Code "Disconnected" | Can you confirm that the Estimation Reason Code ‘Disconnected’ will be removed from the table in 7.3? | Implemented |  | Interim Release 2 | 2023-06-23 | Removed "Disconnected" from Table 7.3 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-06-16
MHHS-DIN-206 |  |  | 2023-03-27 | St Clements | 3703 | Anna Davis | Software Provider |  | Within the MHHS-E2E001 - End-to-End Solution Architecture, there is reference to MHHS-E2E003-Physical Interface Specifications in 1.3 References section This should be labelled as MHHSP-DES138-Interface Catalogue | Implemented |  | Interim Release 1 |  | Updated 1.3 reference section | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-207 |  | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Clarity on when agent appointments should become effective | There is ambiguity within the design on when agent appointments should become effective, which means that different participants have a different view on when agent appointments should become active. | Requires Industry Work Group review | 2023-08-04 | Interim Release 4 | 2023-08-16 | Participants have raised objections against the solution therefore this DIN will be taken to the next DRG to provide clarity. Appointments become active at midnight local time. | Process Model correction | Migration | Migration | BP001 & BPD001 BP002 & BPD002 BP003 & BPD003 Migration Design |  |  |  |  | 2023-07-14
MHHS-DIN-208 |  | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Registration Service rejection of Legacy messages for an MPAN | Within the existing Migration Design, it is stated that the Registration Service should reject all Legacy messages for a given MPAN once a Forward Migration has been initiated for said MPAN. This would prevent a legacy MOP from sending the relevant legacy flows if they need to change a meter when an MPAN is mid migration. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | LINKED to DIN-056 and DIN-191 Above | Requirement correction | Migration | Migration | Migration Design Migration Requirement |  |  |  |  | 2023-07-14
MHHS-DIN-209 |  | Design Team | 2023-03-30 | Design Team |  | Sean Cooper | SRO Design Team |  | ~ Level 1/2 Error Code "MSG0000 - Success" Added to Interface Intro Section ~ MSG0018 - Timestamp cannot be future removed and explainatory note added to IF Notes Section of DIP Common | Implemented |  | Interim Release 1 |  | Updated actioned in v5.1.1 of IF Doc. This relates to MSG1008 not MSG0018 as originally given in the design issue. MSG0000 Success added. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-210 |  | Design Team | 2023-03-30 | RECCo |  | Sarah Jones | Consultancy |  | Possible change flagged The original view of the Design Team was that this flag and associated info (ie Is a Customer Direct contract in place, who is the DS/MS with that contract, but not the Eff To Date aka Contract End Date) should be visible to incoming Suppliers, for exactly the reasons you suggest i.e. so that in an incoming supplier could factor the existence of a CDC(s) into their acquisition process / pricing etc. I think we also felt that SP’s who weren’t currently appointed, but may have signed a new CDC should also have the ability to set the flag, as it’s the sites that are part of a CDC, but where that SP isn’t the appointed SP that are the most difficult to coral and manage. The position at the moment is that the existence of a CDC would be shared with incoming Suppliers as part of PUB-002, however this would likely be too late in the process to provide the assistance and support required to an incoming supplier (on all aspects of the sale, contract/price in particular) … … therefore, I think it was also envisioned that information about CDC’s would be available via ECS – so prospective suppliers could check in ECS on the CDC position as part of the other pre-acquisition checks they may undertake. Therefore, I think the decision on exactly what information is shared ‘pre-acquisition’ to participants probably sits with yourselves (RECCo) to finalise as part of your ECS Design / DP Assessment. All information in relation to CDC’s will be passed/made available to ECS via receipt of a copy of PUB-039, so what item(s) are displayed and to what parties I think would get covered off as part of that ECS Design activity. | Closed |  |  |  | Closed, as per discussions with RECCo that no design changes are required. | No Change | [7 empty] | 2023-06-16
MHHS-DIN-211 |  | DI-139 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-009 Event Code is referred to as [CSSDeRegistration] in the population notes and swagger open API spec but then B042 block title references event code CSS Deactivation, B042 should reference CSSDeRegistration. | Implemented |  | Interim Release 1 |  | Update B042 to reference CSSDeRegistration | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-212 |  | DI-140 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | MHHSP-BP007-Disconnection-v5.0 is missing IF-050 being sent out on a change to MPAN/RMP Status | Implemented |  | Interim Release 1 |  | to BP007 and BPD007 Requires a flow from Registration Service to EES (IF-050 to DIP, a Publish Change to MPAN/RMP Status process, a PUB-050 from DIP to EES process Receive Change to MPAN/RMP status) starting at step 70 (disconnection). Plus add new step descriptions to the BPD and amend Step 70 description to include IF-050. | Process Model correction | Metering Changes |  | MHHSP-BP007-Disconnection, MHHSP-BPD007-Disconnection
MHHS-DIN-213 |  | DI-141 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Data item 997 in S1 common block is senderId in swagger hub, but senderDIPID in data catalogue | Implemented |  | Interim Release 1 |  | Update swagger to reflect senderDIPID to align to data catalague | Technical corrrection | Technical Artefact | Swagger | JSON,YAML
MHHS-DIN-214 |  | DI-142 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | REG Notes section Queuing of Prospective Appointments Rule 4 ** Rule 4: If App Scenario = 'SEG' and Supplier ID + Appointment Service Start Date = Existing Supplier ID + Service Start Date > (Service Start Date +2 working days) >> Appointments meeting Rule 4 have missed their opportunity, and will be 'Lapsed' (PUB-035) This rule doesn't make logical sense, needs correcting. What is the intended logic to be applied here? | Implemented |  | Interim Release 1 |  | Update to align with validation rule | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-215 |  | DI-143 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 for event code [MeterRemoval] rule REG1002 Sending Metering Service ID [SO.SenderID] is currently appointed OR held a valid appointment for Meter Installation Date [DI-057] This should read removal date not installation date | Implemented |  | Interim Release 1 |  | Updated validation rule REG1002 in IF-005 for event code [MeterRemoval] to refer to Meter Removal Date (DI-058) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-216 |  | DI-144 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-144 On IF-005 MPRS will validate Either current, queued SEG or previous MS If previous and not within 10 working days will reject with REG1003 If not previous, and not current or queued, will reject with REG1027 MPRS will then validate if install date/removal date is within MS period of ownership If not will reject with REG1019 REG1019 need correcting to also include <ETD to apply for previous MS It’s not possible to get a scenario where the If-005 passes the above rules (REG1003, REG1027 AND REG1019) but fails REG1002. Therefore REG1002 is not needed and will never be sent as a rejection code. (Add to DI-43) | Closed |  |  |  | Agreed with SCS that no further change is required | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-217 |  | DI-145 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | On IF-005 REG1019 should also include validation that the installation/removal date concerned is <=Effective to date (ETD) of MS period of ownership | Implemented |  | Interim Release 1 |  | Updated IF-005 validation rule REG1019 to include validation that the removal/install date must be <=Effective to date (ETD) where the update is being provided by previous Metering Service (using their 10 day window) for MeterRemoval, MeterInstall and MeterExchange events. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-218 |  | DI-146 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 for event codes [MeterExchange] and [MeterRemoval], the rule should not reference DI-056 which is the meter ID in the installation block, it should should referenced DI-053 which is the meterId in the removal block | Implemented |  | Interim Release 1 |  | Rule updated not to reference DI-056 which is the meter ID in the installation block, it now references DI-053 which is the meterId in the removal block | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-219 |  | DI-147 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 - for other event codes removal date must be >= to Install date but for [MeterUpdate] the rule states > meter install date. Should be >= | Implemented |  | Interim Release 1 |  | Update rule for [MeterUpdate] to align to other removal date event codes | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-220 |  | DI-148 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1007 unecessary and will never be triggered, it is already covered under REG1001 cannot submit meter install if MPAN is disconnected | Closed |  |  |  | Valid rule to left in as-is but noted cannot be SIT tested | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-221 |  | DI-149 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In the IF-005 guide it states: "When amending the Installation and/or Removal date of a Meter, a supporting MAP history commencing in line with the revised Installation Date must also be provided. Any additional MAPs should be provided in chronological order, each with a ‘MAP Effective From Date’ greater, by at least one day, than the previous." MPRS will accept if the install/removal date is changing AND the MAP History has not been included, there is no requirement in Interface Catalogue or Registration Requirements to reject if MAP history is not provided. | Closed |  |  | 2023-06-23 | Believe covered by MeterHistoryUpdate rules, but hopefully won't be an issue pending agreement on MAP discussion… IF-005 use case guide will be updated with outcome. DRG has agreed to remove MAP history therefore in lieu of this decision, this change will not be required. Closed | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-222 |  | DI-150 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | sarah | Implemented |  | Interim Release 1 |  | Updated wording to match existing validation. Guidance only now provided | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-223 |  | DI-151 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005: Need REG1006 to apply to all event codes, e.g. Meter Update on a change to removal date, will need to check that the removal date does not lead to non unique Meter IDs (overlapping dates) MPRS will reject with REG1006 in this scenario | Implemented |  | Interim Release 1 |  | Added REG1006 validation checks to MeterHistoryUpdate and MeterUpdate events. | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-224 |  | DI-152 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 Interface Note below could be read as MeterUpdate event code can be submitted by previous or prospective MS which is not correct "Only the Appointed Metering Service, and for a small window (10 days) to allow for delayed notification of field activities the previously appointed Metering Service; and an incoming Metering Service with a Prospective 'SEG' type appointment may send an IF-005 and update metering details. The [MeterHistoryUpdate] may only ever be used by the Appointed Metering Service. Interface Design assumes that two separate meters with the same 'Meter ID' cannot be installed at the same time. " | Implemented |  | Interim Release 1 |  | Updated | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-225 |  | DI-153 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | DI-849 CSS Registration Request Id does not have a YAML name in the interface catalogue In the swagger hub, the corresponding name is CSSSwitchID which is misspelt | Implemented |  | Interim Release 1 |  | Updated Data Catalogue to CSSRegistrationRequestID, Swagger to follow | Data interface correction |  | Interface Catalogue Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-226 |  | DI-154 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In MHHSP-BPD007 - Disconnection v5.0, the ordering of the steps are out of order. Steps 140, 145 and 150 are for parties receiving the de-appointment notification from the Registration Service, but this is not sent until Step 155. Step 155 “De-Appoint Services” needs to be before Step 140 “DS De-appointment Notification”. Also Step 145 “Receive De-Appointment Notification” is DIP receiving the de-appointment notification to send on, this needs to be after Step 155 and before Step 140 . The ordering should be: • De-appoint services (155) • Receive De-Appointment Notification (145) • DS De-Appointment Notification (140) • MS De-Appointment Notification (150) | Closed |  |  |  | No plans to change step numbers as long as they are unique | No Change |  |  | BPD007
MHHS-DIN-227 |  | DI-155 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1.xlsb, the validation for REG1003 – “Metering Service ID [S0.SenderID] post appointment update period for MPAN [DI-063] has expired” is currently set to “Metering Service [S0.SenderID] holds valid previous appointment then [System Date] should be < [REG.App End Date] + 10 working days”. Should this be <= to allow for the full 10 days? | Implemented |  | Interim Release 1 |  | Changed to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-228 |  | DI-156 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 - IF-005 has the following error for [MeterExchange] & [MeterInstall]:- “REG1020 - MAP Effective Date [DI-054] cannot take place in the future” Should this validation also be valid for [MeterUpdate] and [MeterHistoryUpdate]? | Implemented |  | Interim Release 1 |  | Added to meter update for removal date. Added to MeterUpdate and MeterHistoryUpdate for MAP effective date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-229 |  | DI-157 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 does not have a rule that the SMSO EFD must not be prior to the latest SMSO EFD. We are implementing this rule with error code REG1019 | Implemented |  | Interim Release 1 |  | We are implementing this rule with error code REG1019 Make consistent with others ( PC and ssc + 1 ). Review IHD and SMSO | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-230 |  | DI-158 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 & IF-005 do not have a rejection code where the IHD is invalid. | Closed |  |  |  | DIP will reject non-valid values - no change to docs required | No Change
MHHS-DIN-231 |  | DI-159 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-005 - There is no validation on Meter Removal date [DI-58]. This should be mandatory non nullable for [MeterRemoval],[MeterExchange],[MeterUpdate], but mandatory nullable for [MeterHistoryUpdate] to allow for reinstating a previously removed meter. Currently in redlined v5.1, this data item is optional and non nullable. | Implemented |  | Interim Release 1 |  | Meter Removal changed to nullable, block conditionality updated | Missing/incorrect validation rule | Metering Changes | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-232 |  | DI-160 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-160 on the interface catalogue DCC Service Flag validation rules are specified in IF-025, but DCC Service Flag is not received in this interface. Needs removing. | Implemented |  | Interim Release 1 |  | not needed rules removed. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-233 |  | DI-161 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 – IF-025, where the event type is [ConsentGranularity] Error Code - REG1019 - Consent EffectiveFrom Date [DI-018] must be within Suppliers period of ownership Test Condition - Consent Granularity EffectiveFromDate [DI-018} must be < [Reg.CurrentSupplierEndDate] if exists Should this be <= as it could be on the end date? | Implemented |  | Interim Release 1 |  | Updated to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-234 |  | DI-162 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Registration Services Requirement MHHS-BR-RS-021 should be amended to: Registration Service must, where more than one Metering Service appointment request is received from the same Supplier for the same MPAN CSS Registration Request ID, and for the same date, take the last received Metering Service appointment (based on the Sender timestamp) as containing the correct information. Any earlier appointments should be lapsed. To allow multiple queued service appointments for the same registration will be overly complex to design, code and test, and is likely to cause confusion and issues in live operation. It is much simpler and cleaner to only allow one queued service appointment at a time, per registration. This would still allow the Supplier to replace a queued appointment that's incorrect. The Supplier could submit further changes once the first change has completed, if there is a genuine case of multiple changes to SP in a short period of time. It would not impact on CoS. Our proposal is to allow one pending queued appointment per registration, so could have a queued appoint on current registration AND queued appointment on CoS registration at the same time. | Implemented |  | Interim Release 1 |  | Updated MHHS-BR-RS-021 to refer to CSS Registration Request ID. Added REG1089 - Subsequent appointment received as an error code in the interface spec | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-235 |  | DI-63 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Original wording:- In the business process diagram for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 Update required:- Please close this design issue as CSS0700 is the correct reference for update of status. | Closed |  |  |  | DUPLICATE OF MHHS-DIN-63 | No Change
MHHS-DIN-236 |  | DI-163 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, 02-DIP-COMMON - R0 response - DI-980 Response Message has been updated in Swaggerhub to be an array, but this is not clarified in Interface Spec. DI-979 Response Code should not be an array. | Implemented |  | Interim Release 1 |  | Added note in Introduction section to confirm that DI-980 can be an array Agreed DI-979 Response Code is not an array | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-237 |  | DI-164 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-034 S0 DI-999 Event Code option of [DSAppSPRepsonse] is misspelt. This is also misspelt in Swaggerhub. This could cause differences between systems and should be corrected to [DSAppSPResponse] | Implemented |  | Interim Release 1 |  | Updated typo in IF-034 DI-999. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-238 |  | DI-165 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation on MS/DS EFD being within permitted advanced period. This is covered under migration document but not implemented as a validation rule for IF-031. MHHS-DEL961 Migration Design Document section 6.1.1: For the purposes of the CoA Migration process, the below business rules should be followed by Suppliers regarding the lead time between the submission date of the IF-031 and the requested effective from date of the Migration. a. An effective from date from Same Day +1 up to a maximum of 28 calendar days (inclusive of the 28th day) in the future is permissible. | Implemented |  | Interim Release 1 |  | 28 Day in advance rule added to if-031 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-239 |  | DI-166 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Requirement MHHS-BR-RS-134 states MPRS must automatically de-appoint the MS & DS when the Market Segment Indicator changes to NO. Is this the intended design? | Implemented |  | Interim Release 1 |  | Removed reference to Market Segment Indicator from the requirement MHHS-BR-RS-134. | Requirement correction | MPAN Ownership | Market Segment | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-240 |  | DI-167 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Current validation on IF-031 Rule REG1037 will mean MPRS will lapse any appointment where the system date is greater than appointment EFD + 2 working days. This means if a SEG change fails, and the supplier tries to resubmit the SEG change, with EFD more than 2 working days in the past, MPRS will immediately lapse the appointment. If there is a need to allow retrospective SEG changes, more than 2 working days after EFD, then the wording will need to be amended to apply to max(EFD+2 working days, MPRS system date on receipt of IF-034 + 2 working days) | Implemented |  | Interim Release 1 |  | Introduction of Lapsed Response Codes and Rules in IF-035 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-241 |  |  | 2023-02-01 | C&C | 3430 | Graham King | Software Provider |  | IF/PUB-018 message with event codes [AddressChg] and [DUOSTariffIDChg]. According to Interface Catalogue routing rules, these events are not communicated to the LDSO role via the PUB-018. We assume that the assumption here is that because these data items are mastered by the LDSO that all internal LDSO systems share this data. This is unlikely to be the case. DUoS billing systems co-exist alongside other LDSO management software and are often supplied by different vendors. They do not and cannot share data sets. Given this real-world separation, would it be possible to make the PUB-018 message available to LDSO in the list of Secondary Routing paths? The alternative would mean developing communication channels between disparate systems, from potentially different software vendors in order to pass information from one to the other. | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Linked to expected LDSO CR on DIP Message Optionality - Update as part of wider CR review | [8 empty] | 2023-07-14
MHHS-DIN-242 |  |  | 2023-04-04 | ESG | 3713 | Patricia Parker | Software Provider |  | How will the Metering Service be kept informed of who the currently appointed Data Service are? On BP003 is shows the Metering Service being a recipient of the PUB_036 when a DS appointment becomes effective, however looking at the routing rules in DES138 it does not show ‘MSSC’ or ‘MSAC’ as being recipients? | Closed |  |  | 2023-06-23 | Close - changes to Secondary routing make this DIN Moot - Ref DIN-268 | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-243 |  |  | 2023-04-05 | Change Request | N/A | Sean Cooper | Programme | CR-015 E7/E10 Off Peak Consumption Solution | CR015 - Differential Settlement for E7 / E10 Meters for Smart Opt-out customers | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Changes as agreed at DRG and slides circulated. Updated Method 2 and Method 7 within the SDS method statement (METH001) | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue METH001 BRS001 BRS004 BP004 |  |  |  | CR15 | 2023-06-16
MHHS-DIN-244 |  |  | 2023-04-04 | British Gas | 3874 | Neil Strange | Supplier |  | D0275: Until v0.3 of DES196 was released our understanding was that the D0275 would be retained and it’ use was optional. We are feeding this back on the D-025 consultation but don’t want to lose sight of this. Its removal will impact our billing systems and substantially drive up implementation costs. The baselined IF-021 also does not handle the clock change | Closed |  |  | 2023-06-23 | Alignment with D0275 D0275 is not part of of the baseline design requirements. If you require this, it is by mutual agreement between parties. NO change required, only clarification. | No Change
MHHS-DIN-245 |  |  | 2023-04-01 | Avanade/ Design Team |  | Grant Sutcliffe | Software Provider | Transaction ID and Correlation ID increase field length to 60 | Transaction Id Could the length specification of the TransactionId be increased to be a max length of 60. The need for this is to cater for a 16 character length hex value (increasing from current length of 6 characters]. This would ensure that we achieve uniqueness. It will also provide headroom for any length increase in other Transaction Id constituents, such as Role. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: T-041-1234567890123-SUP-20230220-619C1F6967838002 [Length = 50] Example from DES138 spreadsheet: T-006-1234567890123-SUP-20220401-1234CC [Length = 40] Correlation Id Could CorrelationId length also be increased to 60 max length of 60 - for the same reason. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: CI-BP-011-20230222-619E0BD1D1FD9000 [Length = 35] Example from DES138 spreadsheet: CI-BP-011-20230222-1234567890123 [Length = 32] | Implemented |  | Interim Release 2 | 2023-06-23 | Updated DIP Transaction ID and DIP Correlation ID to String 60 in Interim Release 1. The examples have been updated to reflected MHHSP-DES138-Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-246 |  |  | 2023-04-12 | Change Request |  |  | DCUSA | CR-019 Replacement of D0242 D0315 for MHHS | CR019 - Replacement of D0242 D0315 for MHHS | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors) and receivers (suppliers) of the flows has identified the desired flow content and now wish to bring this back to the program to ensure that it can be delivered in readiness for migration. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the supercustomer data from settlement (REP-002/002A). There will be removal of certain data items used in the current process and addition of new data items, making population of the D0242 ‘Supercustomer DUoS Daily Statement’/D0315 ‘Embedded Network Supercustomer DUoS Daily Statement’ impossible in their current format for migrated customers. The “MHHS Design: Reporting and Transition Sub Group” identified the need for a new DIP flow to replace the D0242/D0315 last summer but noted that these flows are under DCUSA ownership and so passed the development of the flow content to DCUSA. More information including the proposed Interface can be found on the collaboration base under CR019 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-247 |  | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Update to the Core Design Interface Catalogue (MHHSP-DES138) is required to include the addition of IF-003 | Closed |  |  | 2023-07-12 | Closed captured under DIN-434 as part of migration update review IF-003 defined as part of Migration baseline The structure of the IF-003 will be updated to include ‘Incoming Supplier Details.’ The two new data items within the ‘Incoming Supplier Details’ will be: RevMig Incoming Supplier MPID RevMig Incoming Supplier Effective From Date Business Rules: In the case of Smart Meters undergoing Reverse Migration only, the Registration Service will populate the ‘Incoming Supplier Details’ as part of the IF-003 which is sent to the outgoing MS (via the DIP). This is so the outgoing MS can correctly route the Skeleton D0150 to the new Supplier (which in turn enables the new Supplier to generate a D0367). If the D0205 is not sent to the Registration Service before the IF-003 is issued, the data fields used to confirm the identity of the DC and MOP will be blank; no default values will be populated. In this case, the DC and MOP will need to contact the Supplier to initiate a manual transfer of data. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-248 |  | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Updates to the ISD Entities document (EDI021, v5.0) | Closed |  |  |  | To be picked up as part of Migration IA - - new DIN will be raised as required. |  |  |  | EDI021 |  |  |  |  | 2023-07-14
MHHS-DIN-249 |  | Migration Design | 2023-03-27 | Migration Design |  | Matthew Breen | Programme |  | Discussion around the use of BST/UTC during Migration | Closed |  |  |  | DIN is not specific enough. | [8 empty] | 2023-07-14
MHHS-DIN-250 |  |  | 2023-04-06 | Design Team | 3764 | Steve Weston | Programme | Participant ID 10 digit number | This is related to ticket 3764, to update the Interface Specification to ensure the Participant ID is clearly defined as a 10 digit number [0-9] only, and the examples in the Interface Specification align to this, including where this is used as part of the sender unique reference and the examples shows 11 digits, not 10 digits for Participant ID. | Implemented |  | Interim Release 2 | 2023-06-23 | In E2E001 doc Section 4.2.3.2 Section 4.4.4.2 example code for Sender unique Ref and in Transaction ID Section 4.5.5.3 as above DES138 doc Data Catalogue tab: DI-990 example and DI995 Example DIP common tabl DI995 example and the example JSON block (the above easy to change) ALL the IF tabs the JSON block example the Sender Unique Ref contains Participant ID and in every example its longer than 10. JSON/YAML Files: Update JSON examples where Sender Unique Ref and Transaction ID contain a Participant ID example longer than 10. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 Solution Architecture MHHSP-DES138-Interface Catalogue JSON/YAML files |  |  |  |  | 2023-06-16
MHHS-DIN-251 |  |  | 2023-04-06 | Design Team | 3860 | Steve Weston | Programme | IF-041 Population | This is related to ticket 3860, to update the Interface Specification to provide more clarity / notes on the optionality of B064 and B065 blocks in the IF-041 interface. This is in relation to notes / detail about which blocks are mandatory (from a contractual perspective) versus what should be included in the message if the data exists. | Implemented |  | Interim Release 2 | 2023-06-23 | Updates the notes section of IF-041 in order to provide guidance on the minimum population of B064/B065 blocks. This clarifies "When exchanging readings between parties the design assumes that in the most part this will be the Cumulative Register Reading (Block B064). However, at participants request this message also allows for the exchange of Configurable Register Readings (B065) either alongside a Cumulative Reading or in isolation. For the avoidance of doubt the message must contain at least one B064 record and /or one (or more) B065 records [depending on the number of configurable registers], in order to be considered valid. " | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-252 |  |  | 2023-04-06 | Centrica | 3661 | Neil Strange |  |  | We believe there is a Design Gap at Change of Agent and Change of Supplier for Smart Meters which also impacts Migration. Neither the Registration Service, Metering Service nor Data Service will know how the registers are set up and specifically which are active. Consequently the Data Service will not know which registers to send on the IF-041, nor will there be able to calculate consumption correctly without knowing the register set up. The interface catalogue for IF-041 states in respect to this “B065 Block Below Repeated for each set of Configured Register(s) for each Meter” – we do not believe there is a way to give the DS this information. The supplier will set up the smart meter configuration to enable the registers to capture the usage for certain time periods. There is currently no way for the supplier to inform the DS which registers are active at what time of the day - the DS cannot accurately calculate the consumption breakdown based on the reads when there are multiple registers configured. | Closed |  |  |  | DIN closed, Design Team to send email recommending for a CR to be raised. | [8 empty] | 2023-07-14
MHHS-DIN-253 |  |  | 2023-04-12 | British Gas | 3769 | David Hipwell | Large Supplier | Volumetrics | The latest E2E Functional and Non-Functional Requirements MHHS-E2E Requirements V3 which went to V3 on 16/02/2023 appears to focus on message counts and response times. For example:- During transition all meter points (ca. 31M) will be transition between the old and new services. Therefore assuming a linear migration over the year this would result in the load below, hence services shall be capable of processing the following volumes: - average daily volume of 680,000 - peak daily volume of 2.4M 5.0M - annual volume of 248M 500M Analysis of the flows needs to be categorised across all impacted market participant roles including the DIP. Only then will it have meaning for all parties. The calculation needs to take account of the migration period using the MHHS migration volumes according to date (including REVERSE migration). These should be in both message counts and also sizing (e.g. Gb). And include for a BAU day and also migration days. Whilst some calculations can use the total number of MPANs, to be useful these need show also at perhaps for a million MPANs in each role. Only then will all parties be working on a single set of figures. A line in the sand. The NFRs that exist appear to have moved away from any form of technical calculation towards business process figures. But these figures need to go as an input into technical sizing’s, and should have done for DIP – can these be produced and published ? | Requires Industry Work Group review |  | Interim Release 5 | 2023-09-20 | Revised volumetric analysis is currently being prepared by the Technical Design Team. Expected to be shared with participants at a future DRG meeting.
MHHS-DIN-254 |  |  | 2023-04-17 | Siemens | 3044 | Tony Mason | Metering Service | Update of Consent, DPI, etc. | this does surprise me and doesn’t seem to correspond to the routing rules in the Interface Specification. A proposed Data Service is not included in the routing tables for the receipt of a PUB-018, for example. I would therefore expect that if a change to DPI occurs between PUB-033 and PUB-036 the proposed Data Service could only be notified on a revised PUB-033 with the Appointment Scenario set to whatever the original scenario was set to – “SEG”, “CSP”, or “COS”. | Closed |  |  | 2023-06-23 | Ref notes on the maintenance of these data items in the Regi Info Section of the I/F document. Prospective SPs are not notified of changes to these data items during their prospective period. If these Data items change then the supplier should re-evaluate the SP they have proposed and change the appointments as required. If an SP takes on a supply with different elements/factors to those suggested by the supplier at appointment this is a contractual issue between the SP and the Supplier. | [8 empty] | 2023-06-16
MHHS-DIN-255 |  |  | 2023-04-17 | Elexon | 3983 | Kate Goodman | Testing | Consumption on De-Energised MPAN (IF-013/IF-014) | ConsumptionOnDeEnergised is an Event Code mentioned in the list of data items but is not present in header where the routing info is held - needs to be added to header | Implemented |  | Interim Release 2 | 2023-06-23 | ConsumptiononDeEnergised event moved from IF-013 to IF-014 and added in routing rules. See also DIN332 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-256 |  |  | 2023-04-17 | Elexon | 4169 | Kate Goodman | Testing | IF-014 Block B067 | DI-015 is mentioned in the header wrt routing but is not present in the message itself. It either needs to be removed from header or added into message. | Implemented |  | Interim Release 2 | 2023-06-23 | Block B067 added to IF-014 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-257 |  |  | 2023-04-17 | Elexon | 4172 | Kate Goodman | Testing | B053 repeating block | B051 is a block which repeats for each combination of Load Shape Criteria (denoted with single chevron to show repeat). B053 is another repeating block which is denoted by two chevrons, implying it is nested below B051. But in fact it also repeats for each combination of Load Shape Criteria. Should this just have a single chevron or is there further information that needs to be added to make its double chevron make sense? | Closed |  |  | 2023-06-23 | No change required as there will be multiple B053 in each B051 block. | No Change |  |  | none
MHHS-DIN-258 |  |  | 2023-04-19 | ENWL |  | Paul Band | Network Operator | LDSO use of DIP vs internal for Specific messages | There are a number of requirements in the MHHS-BRS005-LDSO document which state that we must obtain various registration data via the DIP and maintain records accordingly such as: MHHS-BR-LD-001-005, MHHS-BR-LD-024, MHHS-BR-LD-030 and MHHS-BR-LD-034 Extrapolating these into requirements for our own systems suggests that we should build databases/tables to store this data and maintain it The requirement is placed upon us as a party under the assertion that all settlement related data should be exchanged between services and parties via the DIP. However LDSO’s are unique in that their data exchange for their party type is split and is typically split by system under these party types. As a consequence we already communicate directly with MPRS as it is already part of our system architecture as a paid for and created service by LDSO’s. | Industry CP Required |  | Interim Release 5 | 2023-09-20 | LDSOs have been advised to raise a Programme Change Request. Discussion at the DRG of the 27/4/23 did not agree on the development of a New Design Principle, A further workshop with LDSOs needs to take place to discuss alternate options and confirm agreement amoungst all DNOs & IDNO on the receipt of publication | [8 empty] | 2023-07-14
MHHS-DIN-259 |  |  | 2023-04-20 | ESG | 3756 | Patricia Parker | Software Provider | BP003C correction | On BP003C under the CoR section there is a note which states that the readings that pass validation should have Meter Reading Status (J0047) set to ‘T’ and when it has failed set it to ‘F’. However as per the REC the group which houses the J0047 group (032 – screenshot below) should only be present where the Meter Reading Flag (J0045) is set to ‘F’. I have checked DES196 and cannot see that the conditionality for that group is changing in the D0010 therefore I can only assume that the note on the process map is incorrect, and it should be talking about the J0045 value instead. Please can you confirm? | Implemented |  | Interim Release 2 | 2023-06-23 | Modification to Note on process to refer to "Meter Reading Flag (J0045)", modify flow label to step230 to "(Read Flag = "T")" Modification to the process note to advise the J0047 would not be present if the meter reading flag (J0045) is set to "T". It will only be present in case the J0045 is set to "F". | Process Model correction | Metering Changes |  | MHHSP-BP003C-Transfer of Reads |  |  |  |  | 2023-06-16
MHHS-DIN-260 |  |  | 2023-04-20 | CGI | 4167 | Dave Webster | Software Provider |  | Swagger definition does not match DES-138 in version 1.0 or 1.1. | Closed |  |  | 2023-06-23 | No specific detail provided, however comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1, therefore closed
MHHS-DIN-261 |  |  | 2023-04-20 | Utiliteam | 4245 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. Configurable Register Reading Date/Time is missing. | Implemented |  | Interim Release 2 | 2023-06-23 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue JSON/YAML Files |  |  |  |  | 2023-06-16
MHHS-DIN-262 |  |  | 2023-04-20 | Utiliteam | 4214 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. B070 for IF-031 is wrong. It contains the word DIP in the Swagger, which is not included in DES-138. | Implemented |  | Interim Release 2 | 2023-06-23 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files |  |  |  |  | 2023-06-16
MHHS-DIN-263 |  |  | 2023-04-21 | CGI | 4203 | Dave Webster | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. DI-122-Profile-Class is defined as an integer, but in DES138 it is defined as a string length 2. Needs to be updated in the Swagger. | Implemented |  | Interim Release 2 | 2023-06-23 | Swagger and Data Catalogue aligned to String 2 for DI-122 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files |  |  |  |  | 2023-06-16
MHHS-DIN-264 |  |  | 2023-04-24 | Elexon | 3946 | Rashmi Radhakrishnan | Central Body |  | One of my colleague pointed out a typo in the CCC method statement attached, and I would like to draw your attention to it and requesting to make necessary amendments. The CCCID starting from 100 to 107 has Market Segment Indicator as “U” and Connection Type Indicator shown as “W”. We think that, for these line items the Connection Type Indictor need be corrected to “U”. For reference please see below picture and this also aligns with ISD entity spec v5.0 (M2 entity). CCC ID Market Segment Indicator Measurement Quantity Consumption Component Indicator Connection Type Indicator 100 U AI C W 101 U AI L W 102 U AE C W 103 U AE L W 104 U AI C W 105 U AI L W 106 U AE C W 107 U AE L W All 'W's' should be 'U's') | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Further details of the solution are under discussion/review. | Design Ambiguous | Supporting Docs | Method Statement | CCC Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-265 |  |  | 2023-04-25 | Elexon | 4128 | Rashmi Radhakrishnan | Central Body |  | ISD entity M5 has a filed Settlement Period quality indicator. Is this the complete valid data set for the field Settlement Period quality indicator? I took this below list from interface catalogue v5.0. A = Actual, E= Estimate (UMS Only) A1,A2,A3, AAE1,AAE2,AAE3,EAE1,EAE2,EAE3 (ADV Only) E0 --> E9 = Estimation Method 1 - 9 ZE = De-Energised ZE1--> ZE3 = Zero Estimation Method 1 -3 but the Advanced Data Service Estimation Method Statement has data flags EA1 till EA13 which is not mentioned in the above list. Also, the ISD entity spec M5 example below shows a different data item that is not in the list at all for Unmetered(104 &105). Is this a mistake? | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | The Freshdesk ticket details redlined changes have been made to the DES240 document. Further details of the solution are under discussion/review. | Design Ambiguous | [7 empty] | 2023-07-14
MHHS-DIN-266 |  |  | 2023-04-26 | ESG | 3899 | Patricia Parker | Software Provider |  | If the D0300 process is not changing then we believe that DES196 is incorrect and should show added routes to allow the Supplier to send a D0300 to the Data Service Matt M has confirmed - We are working through the exchange of CoS readings as the code drafting has raised some questions about the extent to which the SDS is involved in the D0300 process. For smart meters, the SDS will not have any use for the billing register readings so D0300 process should not apply, or at most could only be missing the total cumulative. However, it likely will still be required for traditional meters. On that basis, I think we can acknowledge that the D0300 will be retained and SVs created for Supplier to SDS for traditional meters. The process for smart meters is being discussed internally as the SDS does not retrieve tariff register readings. There will be an updated version of DES196 issued in the next few weeks to reflect feedback from the DTN flow part 2 consultation issued in late March which will reflect the retention of the D0300. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Check with Elexon/Code Drafting that latest version of DES196 contains the D0300 | Design Ambiguous | Supporting Docs | Method Statement | MHHSP-DES196- D-Flow and Interface Mapping |  |  |  |  | 2023-07-14
MHHS-DIN-267 |  |  | 2023-05-02 | ESG | 4385 | Patricia Parker | Software Provider | RegX Validation Issue | RegExpression on the DI-148-Annual-Consumption use of DT-016-Decimal-9-3 in the 1.1 swagger spec. This needs to be updated to align with DES-138 example of 123456789.123. Regex should be ^-?[0-9]\d{8}(\.\d{3})?$ instead of ^-?[0-9]\d{7}(\.\d{3})?$ | Implemented |  | Interim Release 2 | 2023-06-23 | Swagger v1.2 has been updated accordingly | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files |  |  |  |  | 2023-06-16
MHHS-DIN-268 |  |  | 2023-05-03 | SRO Design |  | Sean Cooper | SI Design | Secondary Routing | It was always the intention to revisit and revise all of the Secondary Routing configuration as part of DIP Detailed Design. Completion of this exercise has also resulted in some changes to other routing parameters. | Implemented |  | Interim Release 2 | 2023-06-23 | Following discussion with Avanade the Secondary routing short codes have been simplified and the routing of each IF revisited based on these revised short codes. These are shown highlighted in BLUE in the routing section of each of the individual IF pages. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-269 |  |  | 2023-05-03 | St Clements | 4424 | Anna Davis | Software Provider | Swagger Alignment to DES-138 | We have also realised that there are a large number of discrepancies for each interface between the data item name in Swagger vs the YAML name in the Interface Catalogue Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity | Implemented |  | Interim Release 2 | 2023-06-23 | Updated inconsistencies in the Interface 01-Data Catalogue and Swagger. Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-270 |  |  | 2023-05-05 | SRO Design | 4557 | Rob Golding | SI Design | Correlation ID | Provide further clarity on how Correlation ID's work. This will impact numerous artefacts including DES-138 and E2E001 | Implemented |  | Interim Release 2 | 2023-06-23 | DES-138 Interfaces updated to reflect correct 'COPY' property on IF routing tables. updated IF-008, 16, 20, 26, 28, 37, 39 and 50 for this DIN. Added *New to IF-020 showing a new correlation ID is needed to be created for these events, others events needed a COPY of the correlation ID. IF-050 had “No” added to show that a Correlation ID is not required. Updated the E2E001 design document with a more detailed worked example in section 5.4 that details how and where the Correlation ID is populated. | Design Ambiguous | Supporting Docs |  | MHHSP-DES138-Interface Catalogue. E2E001. |  |  |  |  | 2023-06-16
MHHS-DIN-271 |  |  | 2023-05-10 | ESG | 4541 | Patricia Parker | Software Provider | Swagger Alignment to DES-138 | S0 and S1 is Mandatory in DES-138 v5.1.1, but is not marked as mandatory in the Swagger 1.1. Swagger needs to be updated to align with DES-138. | Implemented |  | Interim Release 2 | 2023-06-23 | Swagger 1.2 updated so all SO and S1 blocks are mandatory as per DES-138 | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-272 |  |  | 2023-05-10 | SRO Design | 4656 | Rob Golding | SI Design |  | Required to DIP Channel Publication (v1.2 of the swagger) that will allow DCPs to register webhooks on behalf of their clients | Closed |  |  | 2023-06-23 | Duplicate of DIN-375
MHHS-DIN-273 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | New MSN Data Type | MHHS Data Type (DT-029) - for Meter ID / Serial number for DI-053, DI-056 and DI-060 added to DES138 01-Data Catalogue, Swagger updated. | Implemented |  | Interim Release 2 | 2023-06-23 | New Data Type created in Swagger v1.2 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-274 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | Missing YAML in DES-138 - DI-073, DI-074, DI-080, DI-111, DI-112, DI-190-194, DI-300, DI-021, DI-022, DI-060, DI-076 | Implemented |  | Interim Release 2 | 2023-06-23 | Missing YAML names for Data Items confirmed and added to 01 - Data Catalogue Note:All DI's upsated except DI-076 has not required a changed. Other DI chnages not listed are picked up as part of DIN261 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-275 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | DI-093 / DI-120 - Data length 2,000 not 200. | Implemented |  | Interim Release 2 | 2023-06-23 | All additional info data items set to len 2000 in Swagger v1.2, DES138 DI-093/120 length updated in 01-Data Catalogue | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-276 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Classifications | MHHS Data Classification - ensure all columns are populated for Public and Restricted ie, MPAN & Address (removall all NULLS). | Implemented |  | Interim Release 2 | 2023-06-23 | Data Classifications added in v5.2.1 where previously there was no entry ( Column I in the Data Catalogue ) | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-277 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Owners in Data Catalouge | MHHS Data Owner - where there are NULL's, this should be updated so all columns provide an owner, mark as N/A (remove all NULLS). | Implemented |  | Interim Release 2 | 2023-06-23 | Metering Service added as Authoritative Source and MHHS Owner in v5.2.1 of DES138 Data Catalogue for DI-190 to DI-195. Previously there was no entry. | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-278 |  |  | 2023-05-10 | SRO Design | 4590 | Rob Golding | SI Design | Addition of indicator for each IF within DES138 | Please can DES138 Interfaces spreadsheet be updated to provide an indicator against each interface (or is it interface & event code) as to whether it can be opted in/out by a recipient. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Design Team to add optionality matrix to DES138 | Design Ambiguous |  | Method Statement | [5 empty] | 2023-07-14
MHHS-DIN-279 |  |  | 2023-05-12 | ESG | 4484 | Patricia Parker | Software Provider | Event Code clarifiction for DS when sending back validated customer read on PUB-041 | The BP005 – Data Processing – Process map shows that when a Customer Own Read has been sent to the Data Service from the Supplier in the IF-041, EventCode = ReadingCoR, the Data Service will perform reading validation and issue the PUB-041 back to the Supplier, in the Read Sharing column of the process map. When the Data Service send back the validated customer own read in the PUB-041, what eventcode will they use and where can I find this documented? The previous response says “There is no IF-041 response, check consumption is as expected in PUB-021” is this correct for Customer Own Reads on Smart meters? The map shows otherwise so please can you confirm if the answer or map is correct and if the map is correct, provide information on what event code will be used. | Closed |  |  |  | This is a query not a DIN. Previous response provided is correct .... There is no IF-041 response, check consumption is as expected in PUB-021” | [8 empty] | 2023-07-14
MHHS-DIN-280 |  |  | 2023-05-12 | ESG | 4552 | Patricia Parker | Software Provider |  | DES196 lists the D0386 (Manage Metering Points) as ‘not impacted’ owned by the REC however BP010 shows that the method of maintaining Related MPANs is via the IF_019 / PUB_020 process. Can you confirm whether the D0386 is going to be removed post- MHHS. If not, could you please clarify what process a Supplier should follow post- MHHS. | Closed |  |  |  | D0386 will not be used post migration to MHHS Regime. Management of MPAN relationships will be under taken using IF-019/IF-020 | [8 empty] | 2023-07-14
MHHS-DIN-281 |  | DI-172 | 2023-05-12 | St Clements | 4446 | Madison Layton | Software Provider | BP003 IF-35 flow | MHHS-BR-RS-053 for the incumbent MS to be notified on If-035 DSAppAccepted where meter is advanced or traditional is missing from BP003 business process diagram and steps. Also updates to BP003 and BPD003 forward migration for consistency | Implemented |  | Interim Release 2 | 2023-06-23 | IF-35 flow from step 85 (if accepted where meter is advanced or traditional to Meter Service (incumbent) and additional step 86 to receive appointment response to BP003, and added step 86 and BR-RS-053 ref and details to step 85 to the BPD003 | Process Model correction | Metering Changes |  | MHHSP-BP003-Change of Service - Data Service, BPD003 Forward Migration BP003 and BPD |  |  |  |  | 2023-06-16
MHHS-DIN-282 |  |  | 2023-05-16 | SIMS | 4821 | Martin Freeman | Software Provider | Status code removal | Status Code is included in the E2E001 design response body (4.4.4.2), when this is HTTP Response code and should be removed as this is defined in the callback response. | Implemented |  | Interim Release 2 | 2023-06-23 | Removed from section 4.4.4.2 from the E2E001 design document as this is not required. This now aligns in Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture |  |  |  |  | 2023-06-16
MHHS-DIN-283 |  |  | 2023-05-16 | SIMS | 4826 | Martin Freeman | Software Provider | ID Capitalisation | ID should be capitalised in all places in the Swagger. | Implemented |  | Interim Release 2 | 2023-06-23 | All JSON names now have capitalised ID fields for Swagger 1.2. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-284 |  |  | 2023-05-16 | SIMS | 4828 | Martin Freeman | Software Provider | HTTP Response Code | HTTP Response code for success should be 201 in E2E001 as per Swagger. | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to E2E001 design document in section 4.4.4.1, 4.5.5.1 and 5.3 to align with Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture |  |  |  |  | 2023-06-16
MHHS-DIN-285 |  |  | 2023-05-16 | Elexon |  | Rob Golding | SRO Design Team |  | Add replay / requeue API for Swagger 1.2 to align with existing E2E001 Design. Add additional information / clarity in the E2E001 for Interim Release 2 to align changes between design and Swagger. | Closed |  |  | 2023-06-23 | Duplicate of DIN-374
MHHS-DIN-286 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Issue clarification to Participants through DRG that all ECS Reports will be issues via Pattern B. Update of ECS Report Catalouge to reflect this. | Closed |  |  |  | The ECS reports will be via Pattern A. No change is required to the ECS reports
MHHS-DIN-287 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team | Guidance notes for distribution of ECS reports | Create & Issue guidance document on the distribution of ECS Reports. To Contain : - overview of Pattern B Process - Guidance on population of IF-047 - Update of IF-047 Event Codes | Closed |  |  |  | Solution yet to be defined No longer required as pattern B will not be implemented for ECS reports | [8 empty] | 2023-07-14
MHHS-DIN-288 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Update of Swagger with ECS Reporting Structures | Closed |  |  | 2023-06-23 | These interfaces are in place from Swagger 1.1. | [8 empty] | 2023-06-16
MHHS-DIN-289 |  |  | 2023-05-17 | SRO Design Team | 4994 | Rob Golding | SRO Design Team | Interfaces for consumption replay | IF-015 / IF-016 - updates to E2E001 to provide clarification on design pattern. Alignments between DES-138 & Swagger alongside this. | Implemented |  | Interim Release 2 | 2023-06-23 | E2E001 design updated (Section 5.1.7) to provide additional information / clarity on these interfaces in relation to Consumption Replay. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture |  |  |  |  | 2023-06-16
MHHS-DIN-290 |  |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Proposal to change all / subset of ECS Reports to Pattern B | Closed |  |  |  | Duplicate | No Change
MHHS-DIN-291 |  |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | As a result of DIN-290 -- Where should the reporting assets be hosted?? DIP solution specified, but what are the other options are availible. Final solution option to be ratified and documentation updated. | Closed |  |  |  | Not hosted as via Pattern A | No Change
MHHS-DIN-292 |  |  | 2023-05-17 | St Clements |  | Madison Layton | Software Provider | ISD Entity M17 | Change required to ISD Entity M17 to add in Market Segment into the table - otherwise it cannot be used to derive consent values which was its original purposes | Implemented |  | Interim Release 2 | 2023-06-23 | 1. Update Table name to "Consent Granularity Valid Combinations" 2. Added Market Segment as new table column 3. Update table to show all valid combinations | Process Model correction | Supporting Docs |  | MHHSP_EDI021_ISD_Entities |  |  |  |  | 2023-06-16
MHHS-DIN-293 |  |  | 2023-05-17 | Design Team |  | Paul Petitt | SRO Design Team |  | Retrospective DIN raised to ensure that any changes that are made in multiple downstream documents (for example CoCo, DIP Logical Design, DIP Physical Design & DIP Security Design) are reflected / updated in LDP assured documents to ensure e2e design / requirements alignment. This was agreed in a DRG Meeting in March 2023. | Implemented |  | Interim Release 1 |  | design changes to E2E001 End-to-End Solution covering points described in DIN details | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-294 |  |  | 2023-05-19 | ESG | 5030 | Luke Speakes | Software Provider | BP007 PUB009 flow | What I need to know is if the supplier will receive a PUB_009 with the Event code of [CSSDeRegistration] because nowhere on the BP007 process map does it show the supplier receiving the PUB_009 following a deactivation but on DES138 it shows the supplier as being a recipient of this event code. Step 95 (ringed below) shows the supplier as receiving the PUB_009 off the back of the Disconnection (event code [MPANDisconnection]) but then no where else on the process map does it have the supplier receiving a subsequent PUB_009 following the successful deactivation. Additional step required from step 130 (maybe 137?) to show both PUB-009 Mpan Disconnection and PUB-009 Deactivation going to supplier | Implemented |  | Interim Release 2 | 2023-06-23 | BP007 change : There is already a flow from Step 85 to Step 95 for PUB009 for disconnection (no change) But need to Add a new step (137) for Receive Deactivation in Supplier lane from Step 130 for PUB-009 MPan deactivation in BP007 And there is already a PUB-037 flow from step 145 to Supplier step 157 for confirmation (so no change there) Addition of step 137 to BPD007 | Process Model correction | Metering Changes | Disconnection | MHHSP-BP007-Disconnection, BPD007 |  |  |  |  | 2023-06-16
MHHS-DIN-295 |  |  | 2023-05-19 | SIMS | 4821 | Martin Freeman | Software Provider | L1/L2 Error Codes | Error code detail updates in DES-138 for Level 1 and Level 2 validation needs to be clarified | Implemented |  | Interim Release 2 | 2023-06-23 | Updates made to Introduction Tab of DES138 in order to clarify Lev1 vs Lev2 error codes. Design is such that participants should expect error code(s) at either level. Further ammendments could be made following Avanade clarifications. | Data interface correction | Supporting Docs |  | DES138 Data interface Definition |  |  |  |  | 2023-06-16
MHHS-DIN-296 |  |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | It is envisioned that Configuration Management of ISD will largely follow the existing customs, practices and processes as are currently in place for managing MDD changes. However, DIN is required to formally confirm the Owner(s) and allowable update mechanisms (Standard or FastTrack) for each of the new ISD Entities outlined in the DIN. | Closed |  |  |  | This is a Code Drafting issue not a Design / DIN issue. Code drafting team will be covering ISD maintenance processes | [8 empty] | 2023-07-14
MHHS-DIN-297 |  |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | What Participants are recognised in the existing / new ISD Participant tables…. How does this link in with the parties recognised by the DIP (and assigned DIP Roles / IDs …. Or Not) …. In particular how are MDRs referenced in ISD? Does this reference need to identify the ‘type’ of MDR? Also, there is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 | Closed |  |  |  | These issues are covered in Release 3 updates (DIN372 & DIN 070) . ISD updated to confirm participants recorded in M16, a new table M18 "DIP Participant Roles" was added. | [8 empty] | 2023-07-14
MHHS-DIN-298 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Update to UMSDS method statement. | As I understand it, you are advising we should A flag the consumption data (even though it isn’t Actual), until the zero charge code D0388 UMS Inventory is received from the UMSO. Therefore - if we have an inventory, regardless of the energisation status of the MPAN, we always use an A Flag. But as you’ve stated, this means an IF-013 will be issued to us as UMSDS, because there is A data, against a De-Energised MPAN. If this is the design/requirement then it is understood – but I would like to call out that this should be detailed within the UMSDS method statement – so I think a DIN is needed to get this requirement added? | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Table provided by PDA has been updated and will be shown within section 10, Publish and Data Flags within the UMSDS Method Statement. UMS method statement updated with text to address query. Updated text below: If a D0388 has been received with load associated data and the MPAN is de-energised the load should be calculated, submitted as ‘A’ Flagged but with an Estimation Reason Code of De-energised. | Method statement correction | Supporting Docs | Method Statement | UMSDS Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-299 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | IF-013 update to include UMSO recipient | Further to this (DIN-298), the cause of this IF-013 being issued can only be that the UMSO has not provided the UMSDS with the correct D0388 UMS Inventory to use. Therefore – the UMSO has a requirement to receive the IF-013 to tell them this. However, the Interface Catalogue has not designed that this will get sent to the UMSO. I think this is a Design Issue too, and also needs a DIN raising so that the IF-013 is provided to the UMSO. | Closed |  |  |  | No this is incorrect. UMSO is not involved with Consumption. If IF-021 submission is rejected this is an issue for the DS (incl. UMSDS) to address and Manage. Any issues regarding the metering onsite/energisation status need to be managed by the DS (incl UMSDS) with their appointing Supplier and Partner Metering Service. |  |  |  | DES138 |  |  |  |  | 2023-07-14
MHHS-DIN-300 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | You are advising a Load Shape will always require the E Flag. But as you say if the MPAN is de-energised, that MDS will reject the IF-021. Is this therefore your answer – that MDS will reject the IF-021, and there is nothing that can be done about that, so we just need to accept we will get those rejections? If so, this isn’t really a satisfactory process, to know rejections will be received in this scenario. Can you just confirm that the solution here is we just need to accept we will get these rejections to the IF-021, which we will then simply ignore? If that is the case – again a DIN needs to be raised to write this into the Design so the process is documented. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Table provided by PDA has been updated and will be shown within section 10, Publish and Data Flags within the UMSDS Method Statement. | Method statement correction | Supporting Docs | Method Statement | UMSDS Method Statement DES138 |  |  |  |  | 2023-07-14
MHHS-DIN-301 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | the corrective action on this scenario (DIN-300) occurring will be if/when the UMSO provides the UMSDS with a D0388 UMS Inventory – then the UMSDS will stop using and submitting the Load Shape data. There does not seem to be a mechanism in the Design for the UMSO to be made aware of this issue that would be of their making, so again needs raising as a DIN please. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Table provided by PDA has been updated and will be shown within section 10, Publish and Data Flags within the UMSDS Method Statement. | Method statement correction | Supporting Docs | Method Statement | UMSDS Method Statement DES138 |  |  |  |  | 2023-07-14
MHHS-DIN-302 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | I’ve pulled together the below table. This covers all the possible scenarios of the UMSDS either having or not having the D0388 UMS Inventory. Combined with whether that D0388 UMS Inventory has load associated data within it. Also combined with whether the MPAN is Energised or De-Energised. Here I’ve listed which Settlement Period Quality Indicator should be used, and where applicable, which Estimation Reason Code should be used. Should this be included in the UMSDS Method Statement and if so, are you happy with the below. In Green are steps we understand. In Red, these remain Unknown to us based on the Design and your answers given. In Orange, these are answered based on your guidance on your email of 28 April – but are not specified in the written Design. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Table provided by PDA has been updated and will be shown within section 10, Publish and Data Flags within the UMSDS Method Statement. | Method statement correction | Supporting Docs | Method Statement | UMSDS Method Statement DES138 |  |  |  |  | 2023-07-14
MHHS-DIN-303 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.2.3 - Changes to Data formatting to align with Swagger / DES-138 | Implemented |  | Interim Release 1 |  |  | Technical corrrection | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-304 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.4.3 - Case Sensitivity - additional information added to provide clarity on approach | Implemented |  | Interim Release 1 |  |  | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-305 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 5.1.7 - Additional Detail required for IF-47 / ISD to provide clarity on approach / steps | Implemented |  | Interim Release 1 |  |  | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-306 |  |  | 2023-05-22 | Tym Huckin | 3992 | Tym Huckin | Consultancy | Clarification/examples for DI-101 for BST/UTC cross over period | Further clarity / worked examples for UTC Settlement Date (DI-101) for BST / UTC cross over period. | Closed |  |  |  | This is not a design change it is a Question/Clarification . | [8 empty] | 2023-07-14
MHHS-DIN-307 |  |  | 2023-05-22 | CGI | 5042 | Dave Webster | Software Provider |  | Status code incorrectly included in required, although not in Standard Response Body Type. This is in Swagger 1.2. | Closed |  |  | 2023-06-23 | Duplicate of DIN-282
MHHS-DIN-308 |  |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | S0 Block required property | Add required property to all the S0 blocks in the interface definition | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger for all Interfaces to mark 3 fields in the S0 block as mandatory. | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-309 |  |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | Swagger Alignment to DES-138 | Define Transaction ID (DI-990) with no Min Length to align with DES-138. This is DT-014. | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (DIP Transaction ID min length removed) | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-310 |  |  | 2023-05-23 | ELEXON | 5173 | Rob Golding | Central Body | Guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 | Guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 are to be applied (if at all), i.e. does the DIP need to consider the effective period and only accept messages on the production system when the message falls within this period? And if so what date within the message should be used as a check? Or the physical date/time of message receipt? Or doesn’t the DIP need to consider these dates at all and no check needs to be applied? | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | This DIN requires an internal workshop with the Design/Technical team. Holding statement to be added to DES138. Validation rules to be added | [8 empty] | 2023-07-14
MHHS-DIN-311 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-985 / DI987 both String 60. Swagger Min and Max Lengths aligned | Implemented |  | Interim Release 2 | 2023-06-23 | Updates made to DES-138 for Length alignment to 60. Updates to Swagger to remove min length for DI-985 and DI-987. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-312 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-984 / DT-009 needs to be updated to be min 3 / max 5 length. | Implemented |  | Interim Release 2 | 2023-06-23 | Sender Role - change on 01 Data Catalogue DI-984 as per description | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface |  |  |  |  | 2023-06-16
MHHS-DIN-313 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S1 - Sender Timestamp updated correctly (from sent timestamp) in Swagger to align with DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (renamed to Sender Timestamp) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-314 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - Publication ID Min Length updated in Swagger 1.2 to be 6 to align with DES-138 (rather than 7) | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Publication ID Min Length now 7, not 6) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-315 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - DIP Correlation ID should have no min length to align with DES-138 (rather than min length of 1) | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (DIP Correlation ID has no min length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-316 |  |  | 2023-05-25 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, all DT-006 and DT-006N should have min length 10 & max length 10 to be consistent. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated DES-138 01-Data Catalogue to align Data Type and provide consistency to Swagger. Removed DI-095 which is no longer used. | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface |  |  |  |  | 2023-06-16
MHHS-DIN-317 |  |  | 2023-05-23 | St Clements |  | Sean Cooper | SRO Design | B9xx array references within Swagger to be updated within DES138 | Update DES138 IF document to include reference to the B9XX Array references held in Swagger | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Solution yet to be defined | [8 empty] | 2023-07-14
MHHS-DIN-318 |  |  | 2023-05-23 | REC | 5049 | Jonny Moore | Consultancy | Addition of 'Effective from date' data items to RMP Status (regi) and MP Status in IF-050 | While completing the design phase for EES we noted that the following items with the IF-050 do not have an effective from date. - RMP Status (Registration) - MP Status These items currently have an effective from date held in EES and not including this in the IF-050 would have the effect of removing these items from EES. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Waiting on SCS Feedback | [8 empty] | 2023-07-14
MHHS-DIN-319 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S0 - EventCode to marked as required to align with DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Event Code marked as required) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-320 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, S1 - Environment (DT-013) should have min length 3 & max length 10 to be consistent with values. | Implemented |  | Interim Release 2 | 2023-06-23 | 01-Data Catalogue DI-991 Environment Set Min to 3. However, string length is 10, so max length should be set to 10 | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface definition |  |  |  |  | 2023-06-16
MHHS-DIN-321 |  |  | 2023-05-23 | St Clements | N/A | Sean Cooper | SRO Design | B005 add to IF-036 | Consider adding B005 to IF-036 so that incoming SP knows who previous SP were | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Added B005 to IF-036 so that incoming SP knows who previous SP were. Updated block name to B005 - Incumbent/Outgoing Service Providers | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-322 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B002 - Incoming Supplier MPID - Swagger aligned to DES-138 for min / max lengths | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Incoming supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-323 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B003 - Ougoing Supplier MPID - Swagger aligned to DES-138 for min / max lengths | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Outgoing supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-324 |  |  | 2023-05-24 | EDF | 4780 | Paul Saker | Supplier |  | NHHSP-BPM00C- Transfer of Reads on Change of Data Service details several process steps and messages related to obtaining and sharing register readings between the gaining and losing suppliers to agree a CoS, and to initiating the missing/disputed reads process defined in the Retail Energy Code where CoS reads are missing or need to be disputed/amended. However, it appears that there is no further detail defined within the Design Artefacts regarding how exactly these process steps would work, including amongst other things: • Timing/Operational Choreography – for example it is not clear exactly when losing and gaining suppliers would be expected to attempt to communicate with the meter, or the timescales for sending data obtained between suppliers. • Data to be included in messages – while BPM003C refers to the inclusion of ‘register readings’ in some of the messages it is not clear which registers should be included for smart meters and non-smart meters – for example whether that should just be the registers on a smart meter that the sending supplier uses for billing, or whether that should be all the 48 time of use registers stored on the smart meter. Additional input from Andrew Margan - Within the code workstream, we believe the Operational Choreography document needs to be updated to reflect SLAs. Without this, we can’t complete the Code drafting. If you disagree, we would appreciate an early heads up, so we don’t look disjointed in front of industry. | Closed |  |  |  | This is not an MHHS Design Issue. D300 / Agree Reading SLAs are defined and set by RECCO. We have replicated the existing 5 day window for capture / submission of a reading(s) all other D300 timescales still apply as per RECC process. Register Readings can only be provided on the D0010 - where this is required [for smart meters] it would replicate the current as is process defined in the current DC BSCP | [8 empty] | 2023-07-14
MHHS-DIN-325 |  |  | 2023-05-24 | CGI |  | Dave Webster | Software Provider | Status Code Missing from MsgBody | In the SubmitEvents StandardResponseBodyType object (SubmitEvents ¦ 1.2 ¦ MHHSPROGRAMME ¦ SwaggerHub), it states that “statusCode” is a required field. Yet its’ definition does not exist in the properties of the object. StandardResponseBodyType: type: object properties: transactionID: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-014-DIPTransactionID' senderUniqueReference : $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-995-SenderUniqueReference' correlationId: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-011-CorrelationID' sentTimestamp: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-003-DateTime' senderId : # the sender of this message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' recipientID : # indended (logical) recipient of the message, i.e sender of the original event message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' DIPConnectionProviderId : # physical recipient of the message (if different to recipient Id) $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' message: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-005-StatusErrorMessage' help: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-019-HelpText' serviceTicketURL: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-018-URL' required: - transactionId - sentTimestamp - senderId - recipientId - statusCode - message - help - serviceTicketURL | Implemented |  | Interim Release 2 | 2023-06-23 | This has now been updated in V1.2 of Swagger StatusCode Added to the ResponseBody. | Technical corrrection | Supporting Docs |  | JSON/YAML files
MHHS-DIN-326 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Changes required to DES-138 / interface catalogue given changes in Migration Design e.g. the addition of interface IF003 and potentially ISD. | Closed |  |  |  | Duplicate of 247 | No Change |  |  | None
MHHS-DIN-327 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | IF-005 User Guide | The IF005 User Guide explains how the IF005 should be populated. We have a request for clarification on whether the IF006 will be populated identically or if the Meter ID in the IF006 will reflect the Modified Meter Id in the IF005. Is IF-005 identical to IF-006, or is it with updated MTD's. | Implemented |  | Interim Release 2 | 2023-06-23 | IF-006 should be a facsimile of IF-005. In the case of change of MSN... MSN field will reference the (old) MSN and Modified MSN will be populated with new/revised MSN. All subsequent flows following the IF-006 will only reference the NEW/REVISED MSN. We further clarified this in a change to the Note(s) section on IF-006. | Data interface correction | Supporting Docs |  | DES138 |  |  |  |  | 2023-06-16
MHHS-DIN-328 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | The operational choreography does not include an SLA for the RS to send appointment data to the CSS or the timings by which the CSS and DSP should deliver their roles within the process. These need to be added to the operational choreography for clarity, noting the interaction with CR018. | Closed |  |  |  | ALL Updates between RS and CSS/DSP are existing interactions, covered by existig SLA's document in RECCO documentation. OPSC document was updated per Recco comment to highlight existing RECCO SLA in this area and to ensure primacy of the RECCO documented timings | [8 empty] | 2023-07-14
MHHS-DIN-329 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Approach on a business rule where the ERDS does not send a MEM de appointment / appointment for an MHHS migration where the same MEM is being appointed under MHHS arrangements e.g. they have the same MPID. The expectation is that smart and advanced MEMs will use the M role code for the interaction with CSS so from their perspective there should be no change. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Further details of the solution are under discussion/review. | [8 empty] | 2023-07-14
MHHS-DIN-330 |  |  | 2023-05-25 | Ovo Energy | 5225 | David Morley | Supplier | Long Term Vacant | BSCP504 section 4.15.3 stipulates the criteria via which suppliers can classify sites as Long Term Vacant (LTV). BSCP701 stipulates actions that SDS shall take if the supplier nominates that a site is LTV. However, the criteria that suppliers shall use for classifying LTVs in MHHS is missing. Can you please signpost where the new criteria will be located? | Closed |  |  | 2023-09-13 | BSCP is responsible for revising the code specification, there are no changes to design specified. Code team will get in touch with the participant.
MHHS-DIN-331 |  |  | 2023-05-25 | MHHS | 4733 | Martin Freeman | Central Body | Secondary Routing | Secondary routing for IF-013 is specified as being conditional upon the value of DI-015. However, DI-015 (Connection Type Indicator) is a property of a repeating block, and there is no constraint in place to suggest that each element in the repeating block must have the same value for this (or any other) property, in which case multiple rules in the routing table could apply simultaneously. The routing table design seems to suggest that only a single rule should apply at a time and that routing should not be derived by blending multiple rules. If this is so, and a message is received where different elements in the B050 have a different Connection Type Indicator then there is no coherent way to implement this in conformance with the routing table. | Implemented |  | Interim Release 2 | 2023-06-23 | Agree there was a routing contradiction for scenarios/periods where a different connection type was in effect. Interface notes section has been updated to direct the use of 'separate' IF-013 messages in such circumstances. Note also makes clear that repeating B050 blocks are acceptable where other elements (not Connection Type) of the CCC vary over the period to be defaulted. | Design Ambiguous | Supporting Docs | Default Consumption | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-332 |  |  | 2023-05-25 | MHHS | 4750 | Martin Freeman | Central Body | IF-013 Routing | In the routing table for IF-013 all rules are conditional upon S0.Eventcode == [ActivePowerDefaulted], which means that for IF-013 message where Eventcode == [ConsumptionOnDeEnergisedMPAN] there is no routing at all, which means when this message is sent to the DIP it will not be routed anywhere and will simply disappear. That's almost certainly an error. | Implemented |  | Interim Release 2 | 2023-06-23 | Event code [ConsumptionReceivedonDeEnMPAN] has been moved from IF-013 to IF-014. The valid event code list and routing rules have now been updated for both interfaces to reflect the move. v1.2 of Swagger also updated to reflect this change Duplicate of DIN 255 | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-333 |  |  | 2023-05-25 | MHHS | 4760 | Martin Freeman | Central Body | Connection Type Required to Support Routing of IF-014 | All of the routing rules specified for IF-014 are conditional upon DI-015 (Connection Type Indicator). But IF-014 does not have any blocks with this property, which means this message won't get routed anywhere. | Implemented |  | Interim Release 2 | 2023-06-23 | Block B067 - Connection Type Added to IF-014 in order to support routing requirements. Swagger v1.2 updated to reflect this change. (Duplicate of DIN256) | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-334 |  |  | 2023-05-25 | MHHS | 4766 | Martin Freeman | Central Body |  | The routing table for IF-018 specifies roles AMSC, UMSC, UMDC for Secondary routing. There are no such roles in either the DES138 nor the E2E001. | Closed |  |  | 2023-06-23 | Secondary Routing Review/Changes have superceded this issue - Ref DIN-268
MHHS-DIN-335 |  |  | 2023-05-26 | British Gas/Engage Consulting | 4640 | Neil Strange/ Haz Elmamoum | Consultancy | Four questions on IF004 | IF/PUB-004 – DIP Common Blocks referencing MHHSP-DES138-Interface Catalogue v5.1.1 As a minimum this needs to be referenced in the supplier requirements MHHSP-BRS004-Supplier Overview and MHHSP-BRS002-Metering Service requirements, but to ensure parties get sight of this we would suggest it needs to be included in a business process map and have associated requirements. For IF-004 to be useful to participants DI-999 – Event Code needs to be elaborated e.g. 1- Installation 2- Removal; 3- Exchange; 4 - Found (Where installed by Gas supplier and Elec Supplier takes ownership) C/M/O rules for DI-192, DI-193 and DI-194 need to be explained in the notes – presumably driven by event code Available is spelled incorrectly (available) for DI-192 and DI-194 there are a couple of angles here – 1) ensuring wider awareness and 2) it seems there is a question mark on the governance here as it is odd a flow has been added but industry does not appear to have been sighted on it especially with no associated referencing in artefacts and no process map, so effectively no one has any idea how it is supposed to be used. Although it was formally agreed not to include and use bilaterally....from a Large Supplier Constituency perspective, my members are keen to ensure design clarity and how flows are to be used or not, regardless of their ad-hoc / bilateral nature. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Update BPM to include sending of Optional Flow at correct point in process | Data interface correction | Supporting Docs | IF-004 | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-336 |  |  | 2023-05-26 | MHHS |  | Rob Topley/ Zak Hussain | SI Design |  | Process Step No. BP Step ID Process Map wording Interface ID Sender Recipient/Service Traceability Requirement Traceability Method Statement iServer Requirement Name iServer Step name Issues Found BP01 170 BP01 - 170 Send Site Tech Details on Metering Service Request MHHS-RS-LD-012.1 #N/A LDSO170a Send Site Tech Details on Metering Service Request Missing (only on BPD and traceability matrix) BP01 175 BP01 - 175 Receive Site Technical Details D0215 LDSO Metering Services MHHS-RS-MS-037.1 #N/A MET175 Receive Site Technical Details Missing (only on BPD and traceability matrix) BP03B 95 BP03B - 95 Manage SP Appointment Amendment Request Response PUB-035 DIP Supplier MHHS-BR-SU-35.1 #N/A SUP095a - Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP03B 96 BP03B - 96 Manage SP Appointment Amendment Request Response PUB-035 DIP Data Services Metering Services MHHS-BR-DS-11.1 #N/A ESP96 – Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP05 315 BP05 - 315 Issue Reading Data MHHS-IF-041 Data Service DIP MHHS-BR-DS098.2 #N/A DAT315 – Issue Reading Data Missing (only on BPD and traceability matrix) BP05 340 BP05 - 340 Process Reading Data PUB-041 DIP Supplier MHHS-BR-SU047.1 #N/A SUP340 Process Reading Data Missing (only on BPD and traceability matrix) BP05 350 BP05 - 350 Process Reading Data PUB-041 DIP LDSO MHHS-BR-LD009.1 #N/A LDSO350 Process Reading Data Missing (only on BPD and traceability matrix) BP010D 1055 BP010D - 1055 Receive updated Legacy information PUB-026 DIP Central Settlements MHHS-BR-RD-018.1 #N/A ECS1055 Receive updated Legacy information Missing (only on BPD and traceability matrix) All these requirements don’t exist on any requirement catalogues, they’ve only ever been on a BPD document or the traceability matrix (which are essentially the same document). Also, the highlighted traceability has a typo and is on a requirements artefact but is wrong on both the BPD and traceability matrix. | Open - awaiting assessment |  | Interim Release 5 | 2023-09-20 | [9 empty] | 2023-07-14
MHHS-DIN-337 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger alignment to DES-138 | R0 - Response Message Min length updated to align with DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Updated R0 - Response in Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-338 |  |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier |  | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. BP003 to be updated to clearly show IF-036 going to both Import & Export supplier | Open - awaiting assessment |  | Interim Release 5 | 2023-09-20 | [9 empty] | 2023-07-14
MHHS-DIN-339 |  |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier |  | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. IF-001 to be updated to be additionally sent to the Export supplier rather than just the import | Open - awaiting assessment |  | Interim Release 5 | 2023-09-20 | See 338 as well | [8 empty] | 2023-07-14
MHHS-DIN-340 |  |  | 2023-05-26 | UKPN | 4547 | Neal Medley | Network Operator |  | The reports ELEX-REP-02/02A will only contain aggregated data for A(General LLF Class Import and C (General LLF Class Export). The I/F021 can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/014 Rejected Consumption Data Submission and I/F MDS Defaults Applied to any I/F021 data to ensure you are not using rejected data or are missing I/F 021 data in respect of an MPAN. MDS Method Statement to be updated to reflect | Open - awaiting assessment |  | Interim Release 5 | 2023-09-20 | [9 empty] | 2023-07-14
MHHS-DIN-341 |  |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | MUM Event not required by MDS | For IF-018 the event [MUMIndicator] is routed to MDS and indicates metered/unmetered. This event is not required by MDS as they can infer this from the Market Segment (Advanced, Smart and Unmetered). DIN raised to remove the routing | Implemented |  | Interim Release 2 | 2023-06-23 | MDS Removed as Always Recipiant for Event [MUMIndicator] on IF-018 Routing rules | Data interface correction | Supporting Docs | IF-018 | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-342 |  |  | 2023-05-26 | UKPN | 5194 | Neal Medley | Network Operator |  | The intent is that the daily volume on actuals or estimates are the sum of the appropriate consumption data. So when added together they should equal the summed Total of the Settlement Period data (Total Uncorrected Volume) barring any rounding errors. The data is given in MWh to six decimal places (i.e. to the nearest Watt hour). I assume DUoS billing only calculates to the nearest unit so would not expect any rounding errors to impact. The A flags are set out in the ELEX-REP-02/02A are the same as those set out in the CCC table in the VAS Method Statement which is also in the MDS Method Statement. I agree the list in the calculations only are missing the full list of SPQI that are deemed to be actuals as set out in the ELEX-REP-02/02A. DIN raised to correct the calculation | Open - awaiting assessment |  | Interim Release 5 | 2023-09-20 | [9 empty] | 2023-07-14
MHHS-DIN-343 |  |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | Routing rules table | The routing rules on the IF-037 sheet state that MDS will 'always' receive the DSDeApp event code, however the 'Always' column on the IF_LIST does not state Central Settlements for MHHSP-IF-037. IF list needs updating to reflect that the DSDeApp event always routes to MDS | Implemented |  | Interim Release 2 | 2023-06-23 | Decision taken to remove Recipiants (COLs G,H &I) from the IF_list - as just duplication of information contained within each of the IF spreadsheets. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-344 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B005 Custom Block update Swagger to align with DES-138. Current Metering Service MPID Length removed. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138. Current Metering Service MPID Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-345 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B024 Custom Block update Swagger to align with DES-138. DUOS Min Length removed. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138. DUOS Min Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-346 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design |  | IF-001 - B032 Custom Block update DES-138 to align with Swagger. Update DI-122 (Profile Class) to Integer from String-2. | Closed |  |  | 2023-06-23 | DI-122 remains as String 2 for Profile Class to support requirements for enumerations. | Data interface correction | Supporting Docs |  | None |  |  |  |  | 2023-06-16
MHHS-DIN-347 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B035 Custom Block - update Swagger to align with DES-138. Remove min length. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-348 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | IF002 correction | IF-002 - B074 Custom Block. Clarification on DI-091. DES-138 says this is 1 digit to the left of the decimal point. Swagger says 5 to 6. DES-138 to be updated to the correct value. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to be an Integer (1), Min of 1, Max of 1, example of 5. This now aligns with DES-138. | Data interface correction |  |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-349 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Correlation ID Issue IF-006 | Routing Rules in DES-138 do not always correctly identity where Correlation ID == Copy ie, it's missing for IF-005 / IF-006 so this needs to be updated correctly across all interfaces. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated IF-006/IF-008/IF-039/If-028/IF-026/IF-016 routing rules to show use of a "Copy" in Correlation ID (ie copied from the preceeding IF txn pairing) | Missing/incorrect validation rule | Supporting Docs |  | DES138 |  |  |  |  | 2023-06-16
MHHS-DIN-350 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-005 B033 to align Swagger with DES-138 (Postcode removal, mandatory modified meter id) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Postcode removal, mandatory modified meter id) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-351 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B071 to align Swagger with DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-353 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B032 to align Swagger with DES-138 (SSC Min Length should be 4) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated SSC Min Length to be 4) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-354 |  |  | 2023-05-30 | SJW |  | Sarah Jones | Consultancy | Design team confirmation for sending of IF-037 and not IF-037 to losing MEM | Please see below details of a new design query related to the Registration Tranche of Code Drafting. We note that in BP011C there is a process whereby the Registration Service will auto de-appoint / appoint agents for secondary related metering points and linked export metering points as part of their validation. The business process only includes the sending of the IF037 to the Losing MEM and not the IF035. Please could you confirm that this is correct and that in this instance the Losing MEM would not receive an IF-035. If this is the case, we think there should be a change to Metering Service requirements MS-018 and 019 to clarify that where the Losing Metering Service receives an IF-037 with no preceding IF-035 then they should send the MTDs at this point. The alternative would be to include the sending of an IF-035 as well as an IF-037 accepting that these would arrive at a similar time. This would align to the process for managing retrospective MEM appointments where we understand that the Losing MEM would receive both the IF-035 and the IF-037. We also suggest amending MS-008, 008.1, 009 and 009.1 to recognise this nuance as follows: MSA/MSS must obtain Export MPAN de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. MSA/MSS should note this message will be automatically triggered when a change of Metering Service has successfully completed for the linked import MPAN or a new MPAN linkage has been put in place where the [linked import / primary related] MPAN has a different appointed Metering Service. Presumably there is a similar impact on the data service requirements that would need to be considered. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Further details of the solution are under discussion/review. |  | Supporting Docs | [6 empty] | 2023-07-14
MHHS-DIN-355 |  |  | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Number of Register Digits | Revisit and confirm IF-005 Cumulative Digits validation rule against latest version of the CP | Implemented |  | Interim Release 2 | 2023-06-23 | All instances of DI-091 (IF-002,IF005,IF-006,IF-033,IF-036) updated to reflect updated logic. IF-005 validation rules updated also to reflect new guidance. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-356 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B073 - update Swagger to align with DES-138 (consumptionAmendmentSupplierReference max length) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated consumptionAmendmentSupplierReference max length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-357 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B902 - update Swagger to align with DES-138 (supplierConsumptionAmendmentRequests typo update) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated supplierConsumptionAmendmentRequests - remove typo) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-358 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-034 B070 - update Swagger to align with DES-138 (contractReferenceMeteringService max length 10) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated contractReferenceMeteringService max length 10) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-359 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: The method statement states that “The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN on notification of the set-up of that MPAN in MHHS-IF-001.” However, it will be the MHHS-IF-036 Registration Service Notification of Service Appointment & Supporting Info that will initially provide the fact that an MPAN has migrated to Central Settlements. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Further details of the solution are under discussion/review. | [8 empty] | 2023-07-14
MHHS-DIN-360 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: 3.3 Where a years’ worth of data, >=75% and <100% of actual UTC Period Consumption data (where Settlement Period Quality Indicator = A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6) has been used to calculate the Annual Consumption, the Annual Consumption Quality Indicator should be set to “1”. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Further details of the solution are under discussion/review. | [8 empty] | 2023-07-14
MHHS-DIN-361 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design |  | We need to raise a DIN on the AC method Statement and AC requirements: Likewise 3.6 needs to say greater than or equal to 182 days: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Further details of the solution are under discussion/review. | [8 empty] | 2023-07-14
MHHS-DIN-362 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design |  | Section 5 incorrectly named Section 6 needs to be removed: 6. Transition and Next steps | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Further details of the solution are under discussion/review. | [8 empty] | 2023-07-14
MHHS-DIN-363 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design |  | We may also need to document how the is calculated by the Load Shaping Service in the first year. I believe Helix have developed a calculation and this would need to go in the Load Shaping Method Statement and be referenced in the AC Method Statement. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Further details of the solution are under discussion/review. | [8 empty] | 2023-07-14
MHHS-DIN-364 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-035 - B066 - mark as mandatory in Swagger as per DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated so B066 is a mandatory for IF-035 custom block) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-365 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-004 - B093 - update Swagger to align with DES-138 (min Length on commsHubGUID / GPF-GAS-GUID) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated min Length on commsHubGUID / GPF-GAS-GUID) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-366 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 custom block - SSC add min length to align with Swagger | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B032 custom block - SSC add min length to align with Swagger) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-367 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 Profile Class - updated Swagger to be a String to align with DES-138 | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B032 Profile Class Swagger to be a String to align with DES-138) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-368 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-013 - B049 updated Swagger to align with DES-138 (run Number optional) | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B049 Swagger to align with DES-138 (run Number now optional) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-369 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | Switch Cancellation Info Note | Update BP002/003 to add informational note that Registration Cancelations will be processed as soon as they are received by SCS from CSS i.e. Apps Lapsed through switch cancelation sent immediatly not held until Proposed App Date. Also updates to Forward Migration BP002/003 for consistency. Changes to OPC added the following words to OPC_190 in the Activity column (section 4.4) “(including Switch Status Updates e.g. Cancelled)” | Implemented |  | Interim Release 2 | 2023-06-23 | BP-002/003 updated to include new informational Note in Supplier swimlane relating to CSS Switch Cancellations. OPC updated to make it clearer that Secured Active Processing includes Switch Status Update processing. to OPC_190 in the Activity column (section 4.4) “(including Switch Status Updates e.g. Cancelled)” | Process Model correction | MPAN Ownership |  | BP002, BP003, OPC001 Forward Migration BP002 & BP003 |  |  |  |  | 2023-06-16
MHHS-DIN-370 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | IF-005 Update Window Guidance for Prev MS | Change IF-005 and Guidance Doc to allow Meter Updates within 10 day window for previous MS | Implemented |  | Interim Release 2 | 2023-06-23 | New validation rule added to IF-005/MeterUpdate to allow previous MS to submit if within 10 day post appointment period. IF-005 User Guide section 9.3 updated to reflect same. | Missing/incorrect validation rule | Supporting Docs |  | DES138, IF-005 User Guide |  |  |  |  | 2023-06-16
MHHS-DIN-371 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team |  | Review design to ensure only Supression of IHD info for advanced segment and NOT "deactivation" of underlying IHD record. | Closed |  |  | 2023-06-23 | Confirmed that IHD details will be retained on Smart to Trad Exchange. Any IHD info present will be suppressed (ie not included in msg) if Segement is Advanced. No change required to documentation. Possible data cleanse issue - Dan T. to raise in Data Forum.
MHHS-DIN-372 |  |  | 2023-06-01 | MHHS | 5298 | Rob Golding | Central Body | Mapping Roles | There is a need to master the mapping of Market Participant Role to DIP Role within the MHHS solution. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | This would seem to best fit within ISD. Specifically Entity #21. Proposed solution is to add DIP Role ID into ISD Entity #21 We would also add validation into Entity M16 to ensure it always references the valid mappings in #21 when a new MPID to DIPID mapping is created | [8 empty] | 2023-07-14
MHHS-DIN-373 |  |  | 2023-06-02 | MHHS | 5272 | Rob Golding | Central Body |  | There is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 | Closed |  |  | 2023-07-12 | Duplicate of DIN-297
MHHS-DIN-374 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Message Replay & Requeue functionality | Message replay and requeue functionality needs to be added to the DIP API interfaces, which requires changes to the Swagger / YAML definitions. Detail is required in the E2E design documentation to explain how the message replay and requeue functionality will work. | Implemented |  | Interim Release 2 | 2023-06-23 | Updates to the E2E001 design document to provide detail on how the replay and requeue will work. There are updates to Swagger to support new interfaces for /dip-channel/{id}/replay and requeue respectively. There is also a new MessageRequest Schema that is used to pass data into both of these interfaces. To support these changes, section 4.8 has been updated in the E2E001. | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents |  |  |  |  | 2023-06-16
MHHS-DIN-375 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Interface webhook configuration | Updates require to the pubconfig and webhook config to support per interface webhook configuration, alongside changes to support definition of recipient ID and role ID. | Implemented |  | Interim Release 2 | 2023-06-23 | Updates to the E2E001 design document to provide detail on how the webhook configuration will work, with information related to specific interface changes. There are updates to Swagger to support new interfaces for /dip-channel/{id}/pubconfig (POST and DELETE) respectively to support changes defined in the E2E001 (Section 4.5 and 4.5.1 and 4.5.2have been updated to provide more clarity / information). | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents |  |  |  |  | 2023-06-16
MHHS-DIN-352 |  |  | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Obsfucation Text | What text should be used for data obfuscation ? for things like Boolean fields (True/false) | Closed |  |  |  | Closed as this is already included in section 4.3.2 of the E2E001 design document. | [8 empty] | 2023-07-14
MHHS-DIN-376 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-099 changes required to ensure DES-138 displays the correct YAML name / Swagger aligns to this. | Implemented |  | Interim Release 2 | 2023-06-23 | "Register" spelling in name has been corrected in DI099, and DI-099 name correction for IF041 in DES138 | Data interface correction | Supporting Docs |  | DES138 |  |  |  |  | 2023-06-16
MHHS-DIN-377 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-097 | DI-097 - In DES-138, this is defined as a string (2), but the existing data type is an Integer and this is an Integer enumeration. Need to update this to an Integer in both DES-138 and Swagger 1.2. | Closed |  |  | 2023-06-23 | Rejected / closed as enumeration of values requires string (2) therefore this is retained to support buisness requirements. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-378 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. | Implemented |  | Interim Release 2 | 2023-06-23 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. This information has now been added to DES-138 5.2.1. | Data interface correction | Supporting Docs |  | DES138 |  |  |  |  | 2023-06-16
MHHS-DIN-379 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-048 | DI-048 - clarity required on whether this is "meter manufacture make and type", rather than just "meter manufacturer". The first is an existing data type and links to the J number, so providing further clarity / rename would quickly ensure alignment in DES-138 and then subsequently in Swagger. | Closed |  |  | 2023-06-23 | Rejected / closed as this was discussed as part of previous work off items and description has previously been approved / accepted as Meter Manufacturer. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-380 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-052 | DI-052 in DES-138 currently has 4 enum values ie, - Active Import, Active Export, Reactive Import, Reactive Export. In MDD there are currently 38 options documented. Discussion around whether ISD Entity 47 should be referenced as the list of values allowed. This can then be aligned / referenced in other other documents ie, EMAR will reference ISD Entity 47. | Closed |  |  | 2023-06-23 | Rejected / closed as this was discussed as part of previous work off items. Only 4 values are required in MHHS / DIP, therefore only these values are referenced / used as part of the enumeration to avoid bringing data from existing systems into new systems when this is not required. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-381 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-842 | DI-842 - Confirmation that MDR's have DIP ID's? There has been discussion in various forums to understand whether they do and if not, then this data item needs to be removed in DES-138 and Swagger. | Closed |  |  | 2023-06-23 | Rejected / closed as MDR's do have DIP ID's, therefore this value will be retained. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-382 |  |  | 2023-05-06 | Design Team | 4570 | Neil Strange | Supplier | D0010 | In BP003C, at CoS traditional CoRs are transferred between suppliers via D0010. We believe this needs to be used for all meter types - as this will be needed for non-communicating smart and advanced meters – and BP003C needs to be amended accordingly. There is no mention of IF-041 and we do not believe that the DIP is expecting an IF/PUB-041 transaction between suppliers. | Implemented |  | Interim Release 2 | 2023-06-23 | Supplier added as a Primary Recipient in the Routing Rules for IF-041 (DES138) - Supplier initiated Reads. Sending supplier would need to populate the DIP ID of Supplier(s) with whom he wished to share the reading. Working Group specifically decided not to discuss /include COR scenarios for Smart Metered Sites however this is not prevented by the Design - a note to this effect has been added to BP003C for clarity. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue BP-003C Transfer of Readings
MHHS-DIN-383 |  |  | 2023-06-07 | RECCO | 4558 | Sarah Jones | Central Body | Change of Segment Scenario | We cannot find anything in the design artefacts stating that the Metering Service is required to notify metering exchanges for change of segment within 2 WDs. We have found the following: MS-094: MSA/MSS must be able to publish Change of Segment Meter Exchange details and reads via the appropriate interfaces, where it is not formally appointed as the Metering Service but does have an accepted prospective appointment (Appointment Scenario = "SEG"). The MSA/MSS must issue the work update to Registration at the earliest opportunity but within [x] days of completion at the latest. OPC 240: Notification of works to be completed by D+3 Working Days (This should provide time for consumption to be provided using new MTDs ahead of the SF run.) The BP011 references the connection type update being provided by LDSOs within 2 WDs. There is no equivalent for metering updates. Will require DRG confirmation on if the 'x' should be 2 or 3 working days | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Updates to be made inline with DRG recommendation to reflect 3 working days | Process Model correction | Supporting Docs | Business Process Documentation | BP011 - Change of Segment DES138-Interface Doc BRS002- Metering Service Requirements BRS001 - Registration Service Requirements BRS005 - LDSO Overview OPS001 - Operational Choreography MHHSP-DES229-IF005_UseCaseguide |  |  |  |  | 2023-07-14
MHHS-DIN-384 |  | DI-174 | 2023-06-07 | St Clements | 4938 | Madison Layton | Software Provider | IF-038 and IF-039 blocks not the same | Block B020, B021 are not the same across interface IF-038 and IF-039. DI-140 and DI-138 (SP DIP ID) are in IF-039 but not in IF-038. Understanding was that with the DIP change that all data items in block are mandatory, the blocks were to be consistently defined across all interfaces. If extra DIP ID DI-138 and DI-140 data items are included in IF-038 then we need a new REG rejection code to allow us to reject where DIP ID is not the same as the sender DIP ID. Alternative is to separate the DI-140/DI-138 into their own blocks included on the IF-039 interface only. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Block data items aligned. New validation rule add to ensure that Sender ID matches MS/DS CDC ID. New Error code REG1076 added to support validation rule. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-385 |  |  | 2023-06-07 | Design Team |  | Steve Weston | SI Design | Correlation ID | S1 Common Block - Correlation ID is mandatory in Swagger, but Optional in DES-138. Swagger should be updated to align. | Implemented |  | Interim Release 2 | 2023-06-23 | Updated S1 Common Block, Sender Correlation ID in Swagger, as this is Optional in DES-138 to support business process and requirements. | Technical corrrection | Supporting Docs |  | JSON/YAML documents |  |  |  |  | 2023-06-16
MHHS-DIN-386 |  | DI-179 | 2023-06-07 | St Clements | 5258 | Madison Layton | Software Provider | Register Digits | REC Change R0102 has been approved by industry to amend the number of display digits validation Where the Meter Type is S1 the Number of Displayed Register Digits value must be either 6 or 5 Where the Meter Type is S2A, S2AD, S2ADE, 2ADF, 2ADEF, 2AEF, 2AF, S2B, S2BD, S2BDE, 2BF,2BDF, 2BDEF or 2BEF the value must be “5”. Where the Meter Type is prefixed with “S2C” the value must be “6”. Where the Meter Type is 2CDEF, 2CF, 2CDF or 2CEF the value must be “6” REG1097 validation on the IF-005 needs correcting with this change, and the population notes for data item DI-091 across multiple interfaces also needs correcting | Closed |  |  | 2023-06-23 | Duplicate of Register Digit DIN-355 listed above | Data interface correction | Supporting Docs | Interface Catalogue | Lis
MHHS-DIN-387 |  | DI-180 | 2023-06-09 | St Clements | 5269 | Madison Layton | Software Provider | Uplift metered indicator requirements | There are elements in the requirements that suggest that metered indicator would trigger a change to Market Segment. E.g. MHHSP-BP011-Change of ConType andor Mkt Segment-v5.1 Step 102 MHHSP-BPD011 - Change of Con Type or Market Segment v5.0 Step 102 Which states if there is a change to market segment RS would need to re-evaluate the market segment And MHHS-BR-RS-124 which include in brackets: Change of Connection Type (Change of Unmetered Indicator) MPRS will assess Market Segment against the ISD entity M7 which does not include Metered Indicator. Therefore a change in Metered Indicator in isolation of any other changes to data items in the M7 table/Related MPANs/Linked MPANs, will not trigger a change to Market Segment. As it will not trigger a change MPRS will not re-evaluate Market Segment base on a Metered Indicator change alone. The requirements need uplifting to reflect. | Closed |  |  |  | Closed as discussed and agreed with SCS. | No Change
MHHS-DIN-388 |  |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | IF-036 Custom Routing Rules | Following discussions with SCS agreed that for reasons of complexity it would be better to adopt Primary rather than secondary routing to IF-036. New Requirement created for REGS to undertake the Primary Routing of IF-036. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | To engage with SCS
MHHS-DIN-389 |  |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | Appointment Start Times | Do we need a formal validation Rule to check that Appointment Start times are referenced as Midnight Local ? Issue raised numerous times with SCS. Waiting for SCS to confirm their position. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | To engage with SCS
MHHS-DIN-390 |  |  | 2023-06-13 | Siemens | 5534 | Tony Mason | Metering Service Provider | IF/PUB-018 | There appears an inconsistency in the Business Process Map, BP010, and the routing rules for the IF-018 where the Event Code = DUOSTariffIDChg. This information is confirmed to SPs on the IF/PUB-036 and would then be updated where there is a change on the 018 according to the Secondary Routing Rules. This notification is absent on the process diagram. Could you confirm the position and update the documentation accordingly? | Initial Assessment/Updating |  | Interim Release 3 | 2023-07-12 | Update BP010B to show Data Service and Metering Service receiving IF-018 for DUoS Tariff ID updates in line with the routing rules in DES-138. | Process Model correction | Meter to Bank | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-391 |  | DI-182 | 2023-06-13 | St Clements | 5304 | Madison Layton | Software Provider | IF-019 validation gap on principal and subsidiary MPAN | IF-019 is missing validation rules to ensure an MPAN is only listed once in the IF-019, need rules to ensure the sender cannot repeat same Subsidiary MPAN twice in the repeating B090 block, and cannot list the same MPAN as both Principal and Subsidiary in the same IF-019 message | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Created x2 new rules to prevent duplicate MPANS within repeating B90 groups within a single message. Error Code REG1079 created to support validation checks | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-392 |  |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Consent Fields | Raised by SCS. B068/DI-017/DI-018 - This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block B068 updated to be "must be provided" for smart meters. Data items set to mandatory non-nullable. | Implemented |  | Interim Release 2 | 2023-06-23 | Block text updated to show mandatory if smart meter present, and DI-017/D-018 updated to be mandatory non-nullable (applies to IF-026 only) | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-393 |  | DI-181 | 2023-06-13 | St Clements | 5274 | Madison Layton | Software Provider | De-appointment and re-appointment date order | MHHS-BR-RS-128.4 & MHHS-BR-RS-128.5 covers the requirement for MPRS to ensure MS/DS are aligned across Related/Linked MPANS, and where they are not to de-appoint the MS/DS and appoint the correct MS/DS. The de-appointment requirement specifies to set MS/DS ETD to D+1 and the appointment to set the MS/DS EFD to D+2. Why do we need to apply the de-appointment and re-appointment in the future? Would we not be better to use the previous day (D-1) for the de-appointment MS/DS ETD and the current day (D) for the appointment EFD? | Closed |  |  |  | Can Close and SCS have agreed with the Requirement. Needs to be this was as work may have been arranged for the last day | No Change
MHHS-DIN-394 |  |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Annual Consumption Fields | Raised by SCS. B059/B027/DI-0148 This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block updated to be "must be provided" if available, however data items now need to be set to mandatory non-nullable. | Implemented |  | Interim Release 2 | 2023-06-23 | DI-0148 updated to be mandatory no-nulls and data type updated to DT-016 in Data Catalogue. Data Type corrected to DT-016 in IF-002 and IF-036. | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-395 |  |  | 2023-06-13 | St Clements | 5510 | Vicki Holland | Software Provider | Obfuscation of Connection Type Indicator in IF-021 | The DES138 interface catalogue specifies that the data item Connection Type Indicator will be obfuscated for all parties as it is required for routing only. Can this please be changed so that it is visible? The reason for this request is that suppliers often process data differently for the different connection types and therefore its important that they can internally validate or route data according to the connection type of the MPAN. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Obfuscation of connection type removed from IF-021/IF-013 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-396 |  | DI-183 | 2023-06-13 | St Clements | 5305 | Madison Layton | Software Provider | Update IF-019 REG1001 to only apply to Create and Add event codes | IF-019 REG1001 rule applies to all event codes. The MPAN could be disconnected with linkages still in place. If REG1001 is applied on remove event codes, then there will be not means by which the Supplier/DNO can remove the linkage after a disconnection. Suggest REG1001 rule should only apply to the Create and Add event codes. This would be consistent with the existing validation on the DB05 and D0386. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | IF-019 MPAN Status Validation Rule removed for all "Remove MPAN" Event Codes. i.e. I can still perform remove MPAN from group task if MPAN is disconnected. SCS rejected option of auto de-linkage as part of De-Registration Process. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-397 |  | DI-184 | 2023-06-13 | St Clements | 5306 | Madison Layton | Software Provider | IF-019: REG0007 to only apply to Related event codes and not to Linked Import Export event codes | REG0007 on IF-019 interface is currently written to apply to both Related and Linked MPANs. The intention of this existing rule on D0386 is because Related MPANs switch together, and so changing the relationship during a switch can create a split supply relationship. However Linked MPANs do not switch together and so this is not currently applied to the existing DB05 validation rules. Suggest REG0007 only apply to Related event codes and not to Linked Import Export event codes? | Closed |  |  |  | Following discussions with SCS it has been agreed to prevent all changes to MPAN Linkages whilst an Active Switch is in progress. This is the safest approach when considering both CSS and Auto Alighment functionality considerations. No change to existing Design Documentation required.
MHHS-DIN-398 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD Stores LLF data | Can we have an ISD entity ID for LLF data. This would be required for the API used to retrive the data from ISD data store. Are you happy for us to create and put it in the Guidance note. | Closed
MHHS-DIN-399 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD publishes full data to Elexon Central Systems | Requirement should be reworded to be "ISD must make available the data sets required by LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. | Closed
MHHS-DIN-400 |  |  | 2023-06-14 | SRO Design Team | N/A | Sean Cooper | SEO Design | REGS Validation Rule Clarification | REG1089 conditions updated to provide more clarity. Existing wording refered only to a Subsequent App - this is now better defined as an Appointment with a prior/earlier Sender Timestamp. No functional change. | Implemented |  | Interim Release 2 | 2023-06-23 | For IF-031 Validation rule text updated to specifically reference Sender TimeStamps so as to provide more clarity on the nature of the val rule/when generated | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-401 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | IHD/SMSO Fields | IHD Install Status and IHD Status Effective from Date fields should be optional (ie nullable) when providing an IHD update in IF-025/IF-026. SMSO and SMSO Effective from Date fields should be optional (ie nullable) when providing an SMSO update in IF-025/IF-026. | Implemented |  | Interim Release 2 | 2023-06-23 | DI-137/ DI-136 in block B030 updated to Optional (O) in IF-025 and IF-026 DI-134/ DI-135 in block B031 updated to Optional (O) in IF-025 and IF-026 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-402 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Import/Export Fields | Linked Import/Export MPAN and Linked MPAN Energy Direction will always be provided so should not be nullable | Implemented |  | Interim Release 2 | 2023-06-23 | DI-038 updated to Mandatory No nulls and Data Type updated to DT-002 DI-151 updated to Mandatory No nulls On the 01-Data Catalogue | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-403 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Meter Manufacturer Field | Meter Manufacturer is optional (ie nullable) when provided in IF-002, IF-006, IF-033, IF-036 as in IF-005 | Implemented |  | Interim Release 2 | 2023-06-23 | DI-048 updated to Optional (O) in IF-002, IF-006, IF-033, IF-036 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-404 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Proposed Appointment Response Code Field | For Response code A there may not be any text to populate for DI-143 | Implemented |  | Interim Release 2 | 2023-06-23 | DI-143 updated to conditional (C) based on DI-979 = L or R in block B007 in IF-034 and IF-035 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-405 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Response Message Field | For Response code A no text to populate for DI-980 | Implemented |  | Interim Release 2 | 2023-06-23 | DI-980 updated to conditional (C) based on DI-979 = R in block R0 in 02-DIP Common Block tab | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-406 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Sender DIP ID Field | Sender DIP ID should always be provided in S1 Common Block | Implemented |  | Interim Release 2 | 2023-06-23 | DI-997 updated to mandatory (M) in block S1 in 02- DIP - Common Block tab | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-407 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | COS During SEG Issue | Discuss with SCS the option of allowing non-appointed MS to update MTDs even if App has lapsed due to COS activity. If not then need to update process map to call out need for manual exchange of MTDs as Work MS could never submit if IF005 | Closed |  |  |  | Closed, SCS unable to support alternative solution. Design Team have reviewed the existing process map note and believe this already provides enough information for participants. | No Change
MHHS-DIN-408 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD is the master for data contained both within ISD and MDD during Transition | The requirement is a bit ambiguous as could be read as all ISD and all MDD rather than just ISD data + overlapping MDD data. We don't want to be the master for MDD only data | Closed
MHHS-DIN-409 |  |  | 2023-06-14 | St Clements | 5510 | Vicki Holland | Software Provider | ISD Entity M5 – Consumption Component Classes | EDI012 ISD entities document shows that the settlement period quality indicator in entity M5 is a comma separated list of possible values. This will be difficult to use in systems that need to refer to this data. Could this instead show Actual or Estimate? Alternatively could this be split into parent and child entities to avoid a comma separated list? | Open - awaiting assessment |  | Interim Release 5 | 2023-09-20
MHHS-DIN-410 |  | DI-487 | 2023-06-14 | St Clements | 5542 | Virginia Patey | Software Provider | DI-487 definition incorrect for REP-002 on Swagger | DI-487 energised MPANs is defined as an Integer in the Interface Specification, yet is defined as a String in Swagger. | Implemented |  | Interim Release 2 | 2023-06-23 | DI-487 updated in Swagger 1.2 to align with Interface specification for REP-002 | Data interface correction | Supporting Docs |  | Swagger 1.2
MHHS-DIN-411 |  | Migration | 2023-06-14 | ESG | 4810 | Patricia Parker | Software Provider | Migration Segment Categorisation | The Migration Design currently specifies that Market Segment needs to be recorded before the Migration phase. This should be changed so that it is no longer required. Until an MPAN is migrated, there is no way of maintaining the market segment between the RS and EES using the legacy interface between these two services. However, meter type and connection type will be available in both the EES and the RS, so Suppliers can use a combination of these values to derive the correct market segment. | Requires Industry Work Group review | 2023-08-16 | Interim Release 6 | 2023-10-20 | 13/07: John Wiggins to have offline discussion with Sean C as DIN requires wider discussion at DRG to progress SRO Team disagree with this Migration Request. Market Segment must be known prior to the selection of MHHS Service Providers. Market Segment is a derived field based on Connection Type and Meter Type. Connection Type must be set before Migration / Meter Type already known so Market Segement CAN be derived, set and maintained prior to MPAN migration. No change to baseline documentation Required.
MHHS-DIN-412 |  |  | 2023-06-14 | MHHS | 5022 | John Wiggins | Central Body | Update to MDD | Migration request to ensure that Elexon add MHHS as a value to MDD. Page 35 of the Design Document under Reverse Migration states that -A default MPID of ‘MHHS’ will be created for the DC, MOP, DA appointments. Will MHHS be contained within MDD as a valid set as there is no reference in the document to update MDD with this value. | Industry CP Required |  | Interim Release 6 | 2023-10-20 | Agreed at meeting on 27/06/23 - MMcK will draft and raise a CP to cover these changes.
MHHS-DIN-413 |  | Migration | 2023-06-14 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | Reading Type (J0171) will be updated with three new values: Forward Migration CoA Forward Migration CoS Reverse Migration CoS Reading Type (J0171) will no longer use Initial or Final for migration reads between Suppliers or DC/DS but one of the above new codes will be used. Meter Reading Reason Code (J0332) will no longer be used to identify migration reads, all reference to this will be amended to Reading Type (J0171) in the guidance document. | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-414 |  |  | 2023-06-14 | British Gas |  | Mohammad Amin Fuggawala | Supplier | D0275 in D-Flow Document | Ref Previous DIN-244. In the "DES196 D-Flow Document" the D0275 is showing as redundent. This is misleading it should be marked as by agreement between contracting Supplier-DS. Document should be updated to reflect this. | Open - awaiting assessment |  | Interim Release 5 | 2023-09-20 | Update to DES196 required
MHHS-DIN-415 | RT |  | 2023-06-14 | Elexon | 5702 | Mike Ceney | Central Body | Routing IF-026 to LSS | IF_026- For Routing Rules it states for Event Code/Conditions [SSC], [ProfileClass] and [SSCandProfileClass] that this should be routed to MDS, is this incorrect as MDS does not use these items in any calculations or outputs, this should state LSS | Implemented |  | Interim Release 2 | 2023-06-23 | IF-026 [SSC] and [ProfileClass] have been removed as of Interim Release 1. Update DES138 IF-026 to route to LSS on event [SSCandProfileClassChange] | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-416 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-001 New App Scenario Code MCS (Migration Change of Supplier) | Create new Appointment Scenario Code of MCS | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New valued added to DI-800 Swagger 1.3 updated to reflect new value | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-417 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-002 Validation Rules for Scenario MCS (Migration Change of Supplier) | New Val rule to check MCS is only used for legacy non-migrated MPAN where Supplier is not current supplier (and not in past) | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-418 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-003 New App Scenario Code MCA (Migration Change of Agent [Service Provider]) | Create new Appointment Scenario Code of MCA | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New valued added to DI-800 Swagger 1.3 updated to reflect new value | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-419 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-004 Validation Rules for Scenario MCA (Migration Change of Agent [Service Provider]) | New Val rule to check MCA is only used for legacy non-migrated MPAN where Supplier is current supplier and now active Switch is in progress (and not in past) | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-420 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-005 - IF-31 Check valid MHHS Supplier | If MCS/MCA code used is Supplier a valid MHHS Approved/Registered Supplier | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-421 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-006 - Prevent use of Migration Scenario IDs | IF MCS/MCA code used for already migrated mpan - reject appointment for invalid Scenario code(s) | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-422 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-007 Connection Type/Segment not yet Populated | New error required if Connection Type, DUos Tariff ID or Segment is not set prior to migration. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Validation Rule created for IF-031 to check that MHHS Standing Data is present and aligned. REG0011 Error created to support this validation Rule. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-423 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-008 Auto Realign Functionality | New REGS Requirment - Only action the auto-realign functionality on MPANs where both Linked MPANs are in a Migrated state. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Req RS-146 added to REGS Requirements Document to ensure that Auto-Align functionality is only executed if all MPANs in a related and/or linked group have sucessfully migrated to MHHS Operation. | Requirement correction | Meter to Bank | Requirements Documents | BRS-003-Registration Service Requirements
MHHS-DIN-424 |  | DI-185 | 2023-06-16 | St Clements | 5335 | Madison Layton | Software Provider | MPRS access to correlation ID | IF-019 is sent to the LDSO for LinkedImportExport event codes, if the LDSO approves the request they will submit an existing DB05 flow into MPRS. If the DB05 is accepted by MPRS, it will send an IF-020 to the Supplier to confirm the change to Linked Import Export association. However MPRS would not have access to the correlation ID that was received by the LDSO on the IF-019, and so would use a new correlation ID on the IF-020. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Note explaining that it will not be possible to Link IF-019/IF020 messages together using Correlation ID , in the case of Linked MPANs. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-425 | SC | Migration | 2023-06-19 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | 8.1.3 step 12 Migration Design Document : Validation Status (J0022) references will be updated to Meter Reading Flag (J0045) | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-426 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-009 New Rejection Code for D0205/D0203 | Response to a D205 is a D0203. 1. A New Rejection Condition/Code is required where D0205 is received following processing of IF-031. 2. Proposed new D0203rejection code is 62 "MHHS Fwd Migration in Progress or Completed" | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-427 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-010 ISD Change M16 | No change Required - SCS can use ISD M16 - which contains MIPD/DIP Role and Effctive From date. This can be used to determine if a Supplier is MHHS qualified. This is better apporach that adding a transiant "Qualified Yes/No" field to this table. Therefore NO changes to documentation required. | Closed
MHHS-DIN-428 |  |  | 2023-06-19 | British Gas | 5835 | Neil Strange | Supplier | MEX before SSD scenario | When a CoS is in progress and there is a MEX before SSD, how will new supplier get the MEX details As the incoming supplier has already received the IF36 - would there be a new IF36 or would it be a PUB006? In addition how would the new MS and DS be made aware of this? - the old MS has X days after the job is completed to update the industry and a CoS could have happened before the old MS can update the other participants. | Closed |  |  |  | BAU Design deals with 'regular' MEX before COS type scenarios (note previous MS Update Period - PUB-006 would be issued to impacted parties). Complexity arises where there is a COS overlapiing with Change of Segment/Connection Type (ie SEG Appointment)... Following discussion with SCS - low probably, low occurance vs. complex change. Ref existing guidance on BP016 there would need to be a manual interaction between Supplier and MS. No Change to existing Documentation Required.
MHHS-DIN-429 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-011 Changes to D0170 | 1. Change D0170 flow so that MPRS/Registration Service is valid Sender of this flow. 2. New value for "Request Action Code" is needed to denote a Migrating account and if its CoS or ChgOfSP method. | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-430 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-12 New Val Rule for IF-019 | Reject any changes to Related MPANs where any MPAN referenced (or in realted group) is subject to an active Migration SP Appointment Process | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Validation Rules and Error Code created to prevent changes if MCA Appointment Type Exists (Note: prevention if MCS exists is realised through existing check on if Switch is in Progress) | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-431 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-13 Change to D0386 | Change D0386 validation to reject changes to related MPANs if any related MPAN in group is subject to active Migration SP Appointment Process | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-432 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-014 Appointment on Secondary Related MPAN | Extend existing 1039 check to include MCS.MCA Appointment Scenarios. | Closed |  |  |  | Existing Validation Rule(s) around REG1039 will already cover Migrating MPANs - No Documentation Change Required.
MHHS-DIN-433 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-015 Switch in Progress Mig Rejection | New IF-031 validation to reject MCA/MCS DS and MS Appointments if an [any] active Switch is in progress with NEW Rejection Reason Code (note 1095 code referenced in Migration document has already been used elsewhere) | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New validation rules and REG9XXX Exception codes added to ensure correct usage of MCA/MCS Appointment Scenario Codes. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-434 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-016 New IF-003 | Previously DIN-247, Introduce IF-003, no changes from original proposal. 1. Update DES138 new tab, update IF List. Update New Data Items 2. Review E2E doc. 3. Update secondary Routing Rules (Avenade Techncal Doc) to include 4. Update Swagger | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Add IF-003 to DES138-Interface Cat. Created new Data items: DI-500 MHHS Regime End Date, DI-501 Rev Migration Incoming MOP MPID, DI-502, Rev Migration Incoming MOP Eff From Date, DI-503, Rev Migration Incoming DC MPID DI-504 Rev Migration Incoming DC Eff From Date. Swagger v1.3 updated to reflect new IF-003, Blocks (B096/B095/B094) & Data Items (as above). | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-435 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-017 D0304 & D0303 | 1. New D0304 Validation Rule 2. NewD0304 Rejection Reason Code "Q - MPAN Fwd migration in progress or completed" 3. Change D0303 so as to make "Eff From Settlement Date REGI" a non mandatory data item within the flow (an alternative to suggesting that outgoing MS no longer issues a D303, only the incoming MS would send) | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-436 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG0-018 D312 | 1. New D03012 Validation Rule 2. New Rejection Reason Code "AD - MPAN Fwd migration in progress or completed" | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-437 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-019 IF-005 Validation Rule | 1. New val rule to prevent IF-005 while MCS/MCA Appointment is in progress 2. New Error Code (REG9003) | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | REG9003 - MHHS MTD Updates cannot be used until Migration has completed, Created and new validation rule added to IF-005 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-438 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-020 REGS Design Clarification | SCS Should issue L1/L2 Msg Status message with RCP1061 for any MPAN at the incorrect status where a DIP Message is received | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | This is a Migration Requirment which participants should take into account as part of their Migration Designs. However, for clarity a note has been added to RCP1061 entry in the Intoduction Section of the Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-439 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-021 No Supplier Updates during Rev MIgration (IF-025) | 1. New If-025 val rule to check if Rev Migration Switch is in progress 2. New error code | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | REG9002 - Supplier Data Items Cannot be Maintained for Reverse Migration Account, Created and applied to IF-025 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-440 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-022 No CDCs Updates during Rev MIgration (IF-038) | 1. New If-038 val rule to check if Rev Migration Switch is in progress 2. New error code | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | "REG9001 - CDC Marker Cannot be applied to Reverse Migration Account", created and applied to IF-038. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-441 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-023 No AC Updates during Rev MIgration (IF-040) | 1. New If-040 val rule to check if Rev Migration Switch is in progress 2. New error code | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Design Team Discussion with SCS required. Design Team minded that this is an invalid requirement. Helix will produce AC provided the site has not completed Reverse Migration, these updated should be accepted, design does not allow for rejection of an AC update.
MHHS-DIN-442 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-024 D0010/D0086 New MR Reason Codes | Three new MR Reason Codes for use in D0010: Forward Migration COS / Forward Migration COA / Reverse Migration | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-443 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-025 D0055 New Agent App Reason Codes | 1. New Valid value for service reference "REVM" 2. New valid value for Service Level "REVM" | Industry CP Required |  | Interim Release 5 | 2023-09-20 | Code Drafting Team/ Elexon will draft and raise a CP to cover these changes.
MHHS-DIN-444 | RS |  | 2023-06-19 | ESG |  | Patricia Parker | Software Provider | IF-01 Incoming supplier for Import/Export MPANs | Clarification required with SCS. If it is known that an alternative MPAN has the same SSD then we do not want the old supplier ID as the linked supplier on the IF-01, we want the new supplier to be populated | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Confirmation required from SCS
MHHS-DIN-445 | SB |  | 2023-06-19 | Utiliteam |  | Richard Palmer | Software Provider | Spec of IF-024 in DES138 Interface Catalogue | The Population Notes for DI D-000 in Group S0 has ‘IF-025’. This error was in v5.0, and is still in v5.1.1 | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | The Population Notes for DI D-000 in Group S0 has been updated to ‘IF-024’ in IF-024. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-446 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-026 Migration DIP Reporting Reqs | Reqs for x3 new Reports -- Flag at the next DIP DAG | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Awaiting further internal discussions re DIP Reporting Strategy
MHHS-DIN-447 | SW |  | 2023-06-21 | Kraken | 5980 | Angelos Rizoyannis | Software Provider | Conditional Mandatory not applied in Swagger correctly | IF-041-CustomBlock: The field B065List is stated as optional in the comments, but the API schema does not reflect this. This field that is conditionally optional in DES-138, but this is not defined as such in Swagger ie, OneOf, AnyOf. This needs to be updated in Swagger to align correctly. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | In Swagger 1.3, updated IF-041-CustomBlock: The field B065List and B064List will be either / or as they are defined as conditionally mandatory in DES-138. This uses oneOf notation in Swagger. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-448 | SW |  | 2023-06-21 | Kraken | 5980 | Angelos Rizoyannis | Software Provider | Mandatory fields not applied correctly in S1 block | S1 Common Block: The 'properties' and 'required' sections of the API schema for the S1 common block have conflicting information. The 'properties' section includes fields like senderTimestamp and senderRoleID, while the 'required' section lists sentTimestamp and senderRole. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Updated Swagger 1.3 to align properties and required sections so that fields are called senderTimestamp and senderRoleID. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-449 | SC |  | 2023-06-21 | SRO Design Team |  | Sean Cooper | SRO Design | Change to IF-037 | Include Block B002 into IF037 so that outgoing MS is aware of incoming Supplier on a COS. This will allow the SP to populate the D0303 to MAP. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Block 002 added to IF-037 for use where event code is MSDeapp, this is so that the outgoing MS is informed of who the incoming supplier is so that D303 can be correctly population. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-450 | SC | DI-196 | 2023-06-22 | RECCO |  | Sean Cooper | SRO Design | Change to IF-005 Validation Rules | Change made to IF-005 validation Rules to allow previous MS to update Meter Location only - during the 10 day post appointment period. This will allow for scenarios where there has been relocation only activity immediatly prior to a change in MS. All other MeterUpdate functions apart from Change of Meter Location shall be rejected per wider agreement that only active MS should have the ability to change the characteristics... This change originated from R1 Comments feedback from RECCO | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | IF-005 Validation rules updated to include new "REG0008 - Amendment Requested cannot be undertaken by Previous Metering Service" error condition and code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-451 | SC |  | 2023-06-22 |  |  | Sean Cooper | SRO Design | CR - 018 Registration Service OOH Ops | CR18 looks to specify Registration Service Out-Of-Hours Operations. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | CR Contents incorporated into a new Section 7 of Ops Choreography Document | Technical corrrection | Supporting Docs | Operation Choreography | MHHSP_OPC001_Operational_Choreography
MHHS-DIN-452 | SC |  | 2023-06-22 | SCS |  | Sean Cooper | SRO Design | Refine Consent Checking Rules on IF-031 | Further refine Consent checking rules so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing . Updates to IF-031 validation rules to reflect this change. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | IF-031 alidation rules updated per the DIN Details. Consent checking rules added so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-453 | MF |  | 2023-06-22 | SCS |  | Mike Fensome | SRO Design | Issuing of IF-020's | Highlighted that LDSO's could issue an IF-020 with details of import/export linkages without having received notification from the Supplier | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Added note to IF-019 and IF-020 to inform Suppliers that Import/Export linkages could be received via PUB-020 unprompted by the Supplier issuing IF-019. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-454 | SC |  | 2023-06-26 | SCS |  | Sean Cooper | SRO Design | Update to ISD M7 | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service | Requirement correction | Supporting Docs | ISD Document | MHHSP-DES138-Interface Catalogue
MHHS-DIN-455 | SC |  | 2023-06-23 | SCS |  | Sean Cooper | SRO Design | Update Op Choreography (Event Move from IF-013 to IF-014) | Update Ops Choreography to take account of the movement of event [ConsumptionOnDeEnergisedMPAN] which was moved from IF-013 to IF-014 (DIN-255). | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | IF-014 Deadline split into two. First [ActivePowerRejected] remains UNCHANGED. Deadline for [ConsumptionOnDeEnergisedMPAN] is also UNCHANGED but moved from IF-013 row into IF-014 Row, to mirror the change delivered by (DIN-255) | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-456 | SC |  | 2023-06-23 | SCS |  | Sean Cooper | SRO Design | Swagger Correction - DI-844 | Corrected x2 invalid referenced to "AssignedMRDRequestEffectiveFromDate" should have been "AssignedMRDEffectiveFromDate" in Block 066 | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Corrected x2 invalid referenced to "AssignedMRDRequestEffectiveFromDate" should have been "AssignedMRDEffectiveFromDate" in Block 066 | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-457 | SC |  | 2023-06-23 | SCS |  | Sean Cooper | SRO Design | Change to DTN Validation of D0350 | Implement DTN Validation of D0350 to prevent future dates | Industry CP Required |  | Interim Release 5 | 2023-09-20
MHHS-DIN-458 | SC |  | 2023-06-23 | SCS |  | Sean Cooper | SR Design | New IF-019 Related MPAN Validation Rule | New Validation Rule required for IF-019 to ensure that only Import MPANs can be realted. Add to Create and Add Related - this is per REC Shedulle 28 | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | New Rules added to IF-019, [RelatedAdd] and [Related Create] events to ensure only Import MPANs can be in a related Group. New Error code added to support these new rules REG1067 - Only Import MPANs can become Related | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-459 | SB |  | 2023-06-23 | Utiliteam | 5724 | Richard Palmer | Software Provider | Spec of IF-024 in DEL138 Interface Catalogue | A further suggestion re the Interface Spec for the IF-024: The Event Code list in DI D-999 in Group S0 contains [SN-RemoteEnabled] & [SN-RemoteDisabled]. I would suggest that these are invalid for Segments Advanced and Unmetered. Also [SN-Vacant] would appear to be irrelevant for Segment Unmetered, and I doubt that [SN-NoComms] would be valid either. These existed in v5.0, and are still in v5.1.1. Perhaps the routing rules need some improvement? | Closed |  |  | 2023-08-09 | No change Required. Useage of these evernt codes is obvious and is described in the Requirments documents as necessary
MHHS-DIN-460 | SB |  | 2023-06-26 | Utiliteam | 5939 | Richard Palmer | Software Provider | PIF-019 structure & Principle -> Principal | Also, in the relationships between MPANs, the ‘main’ one is the ‘Principal’ one – not the ‘Principle’. This will be embarrassing if left uncorrected. It is still in v5.1.2 in IF-019, and it is in many other places. If there is a chance of correction, please take it. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Spelling mistake corrected in Data Catallouge, IF-019, IF-020. Note YAML name also corrected for DI-073. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-461 | SW |  | 26/06/2023 | Greenbird | 1768 | Fredrik Omland | Software Provider | Misalignment between DES-138 and Swagger for DIP Connection Provider ID | In DES-138, In the S1 block, DI-996 (Connection Provider DIP ID) is defined as Optional. But in Swagger, this is defined as mandatory. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Updated Swagger 1.3 so DI-996 in S1 block (Connection Provider DIP ID) is Optional to align with DES-138 | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-462 | SW |  | 27/06/2023 | Design Team |  | Steve Weston | SI Design | Schema Optionality incorrectly defined for some Interfaces | In DES-138, there are are a number of Interfaces where the Schema Optionality is defined as Optional, rather than Mandatory. The list of Interfaces are as follows - IF-050 / B022, IF-023 / B053 and IF-013 / B049 | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Updated Schema optionality in DES138 to show that all data items must be present where the block is present in line with updated E2E Solution Architecture for IF-050 / B022, IF-023 / B053 and IF-013 / B049. | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalouge
MHHS-DIN-463 | SW |  | 27/06/2023 | SIMS |  | Kyle Abraham | Software Provider | No ability de-register from receiving Status messages in Swagger | In Swagger, there is a POST method for /statusmessage/config, but there is no DELETE method, so you are unable to delete / de-register for any status messages. Need to update Swagger to ensure this is possible. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Updates made to Swagger 1.3, so there is a DELETE method for /statusmessage/config, so you are now able to delete / de-register for any status messages. Updated so that all of the Interfaces accept the same 4 security headers required for message signature and validation. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-464 | SW |  | 27/06/2023 | SIMS |  | Kyle Abraham | Software Provider | Clarity required on values expected for /dip-channel/{id} for submitEvents on Swagger | The {id} in /dip-channel/{id} for submitEvents on Swagger should accepts values that are the same as the enumeration in DI-000 to ensure consistency. At the moment, this is not clear in Swagger or E2E001 design, so this needs to be updated to make this clearer. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Updates made to Swagger 1.3, so there the correct enumerations / values are available to align with values in DI-000 to ensure consistency and avoid any ambiguity between interfaces and reports. Updated to remove PublicationConfig and RestConfig in favour of a single config WebhookConfig. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-465 | SC |  | 2023-06-28 | RECCO |  | Sean Cooper | SRO Design | Update to BP010 - Related MPANs | The process MPAN for Related MPANs does not clear call out the Rejection pathway. Update Business Process to show rejection process. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | BP010 Related MPANs Process updated to show specific Rejection Route. | Process Model correction | Metering Changes | Business Process Documentation | BP010- Changes to MPAN Data
MHHS-DIN-466 | SC | DI-188 | 2023-07-29 | SCS |  | Sean Cooper | SRO Design | Change of MPAN Status during Service Provider Appointment Process. | How should a change of MPAN Status be dealt with whilst there is an ongoing SP Appointment that has not yet reached the stage of IF-034 processing !? If an MPAN is disconnected between PUB-031 acceptance and receipt of PUB-034, the SP PUB-034 Response would be rejected by MPRS due to validation rule REG1001. The appointment would not be progressed but would be stuck in the MPRS queue at status Requested. Could resolve by amending REG1001 validation on IF-034, to not apply to event codes MSAppSPResponse or DSAppSPResponse. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Resolved following discussion with SCS, Agreed that SCS will take no action until the IF-034 has been processes. A change to REG1001 validation on IF-034, to not apply to event codes MSAppSPResponse or DSAppSPResponse, is required to allow the IF-034 to processes normally (when where MPAN is disconnected)... Following processing of the IF-034 RESG will then immediatly issue an IF-035 with reason code of "1- Lapsed as MPAN Status is Disconnected" ... ... Agreed that this was best resolution both for REGS processing rules and participants as no change to currently expected message patterns/ordering. | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalouge
MHHS-DIN-467 | SC |  | 2023-07-29 | ESG |  | Sean Cooper | SRO Design | Review of IF-035/IF036 Data Item Obfuscation | Review of IF-035/IF-036 Data Item Obfuscation | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Further details of the solution are under discussion/review.
MHHS-DIN-468 | SC |  | 2023-07-29 | Helix |  | Sean Cooper | SRO Design | Routing of IF-020 | Helix have confirmed that they DO NOT need to receive Related/Linked MPAN information therefore an update is required to REMOVE MDS from the receipient list for this IF-020 | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | IF-020 Routing table has been updated to REMOVE MDS as being a recipient of any IF-020 messages. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-469 | ME |  | 2023-06-30 | SRO Design Team | 2109 | Rob Golding | SRO Design | Removal of Z0 & Z1 data items in ERI011B - ECS Reports External | Z0 & Z1 data items to be removed from from the each of the MHHS reports within ERI011B - ECS Reports External as they are no longer in the common block | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Remove Z0 & Z1 data items from all MHHS reports in ECS external reporting artefact | Data interface correction | Minor | ECS Reports | ERI011B - ECS Reports External
MHHS-DIN-470 | SW |  | 29/06/2023 | Callisto | 1805 | Seth Chapman | Software Provider | Clarity on nullable fields | Section 4.2.2 in the E2E design provides information on Optional / nullable fields, but worked examples would provide further clarity for each of the data types / link to JSON specification. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Updated section 4.2.2 with worked examples for each data type to provide additional clarity. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-471 | MH |  | 2023-06-30 | Helix |  | Derek Weaving | Central Body | Update to REP-003 in ERI011B - ECS Reports External | R019 parent should be R017 in the ECS Reports External and Swagger | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Update R019 parent to R017 for REP-003 in ERI011B - ECS Reports External. Swagger v1.3 updated to align with changes within ECS reports artefact. | Data interface correction | Minor | Interface Changes | Swagger 1.3
MHHS-DIN-472 | SW |  | 29/06/2023 | SRO Design Team | 2006 | Rob Golding | SRO Design | Onboarding migration from Test to Production. | “The programme is to implement a strong PKI policy but as per the diagram states that that on promotion, parties will be able to copy their Test setup and to use that for connecting to the Prod environment. - steps 1-8 - There are no steps in this sequence that test the connectivity to the Live DIP environment. To this point the only connectivity testing has been to the Test environments. This is a significant failure point / risk. At this point Webhooks and certificates will change (mTLS and JSON signing) from those used in Test as well as potentially some of the PKI resources assigned to roles ( those used in test may not be applicable to Prod) we would expect that this would require a new Connectivity proving period with the Prod environment similar to that being developed for CIT. Without such proving, how can the programme assume all parties will connect to the Prod environment successfully and ensure minimal impact to migration events”. | Closed |  |  |  | Solution yet to be defined This an Elexon/DIP Manager deliverable not a programme deliverable
MHHS-DIN-473 | SB |  | 2023-06-30 | MHHS | 2111 | Jason Brogden | Network Operator | Definition of Network Operations | Issue: There is a lack of clarity in the scope of Network Operations activities in testing. Action to Resolve: Add a definition to the Programme Glossary that makes clear the scope of Network Operations (as referenced in Testing material) is equivalent to the scope of LDSO activities in the MHHS Design Baseline: Network Operations systems and services are those that are required to deliver the elements of the MHHS Design Baseline that are allocated to the LDSO role. Communicate this to the DNO and iDNO community and associated service and software providers. For the DIN Log, we can then focus on updates to the BRS to give the necessary clarity on the scope of MHHS Design. Issue: There is a lack of clarity in the scope of LDSO activities in the MHHS Design Baseline as BRS005 implies MHHS-related processing requirements at LDSOs for received DIP messages, whereas the BPs and BPDs define the scope of MHHS as ending at the receipt of DIP messages. BRS005 is described as “For Guidance Only” at the top and this is to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing). Action to Resolve: For the avoidance of doubt and to provide clarity to BRS005, it is proposed to change the “For Guidance Only” note at the top of BRS005 to the following description as per the above: BRS005 is provided For Guidance Only to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing). | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | LDSO Requirements document updated with the following text, "BRS005 is provided For Guidance Only to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing)." | Requirement correction | Minor | Business Requirements Documentation | BRS-005 LDSO Overview.xls
MHHS-DIN-474 | ME |  | 2023-07-03 | MHHS |  | Kevin Spencer | SRO Design | Creation of new ECS data items and blocks across multiple reports and/or data catalogue | Report definitions incorrect and require updates and new data items following internal review | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Addition of DI-503, DI-504, DI-505 data items across ECS reports artefact. MHHSP - ERI011B - ECS Reports - External v5.2 and MHHSP - ERI011A - ECS Reports - Internal v5.2 | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-475 | ME |  | 2023-07-03 | MHHS |  | Kevin Spencer | SRO Design | Update to block names, data items and descriptions | Report definitions incorrect and require updates and new data items following internal review | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Update to block names, DTN references, data items and descriptions in MHHSP - ERI011B - ECS Reports - External v5.2 | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-476 | SW |  | 2023-07-03 | Greenbird | 2035 | Fredrik Omland | Software Provider | Inconsistency between enum fields and nullable definition | Looking at DIP Interfaces Swagger 1.1 (also 1.2 + 1.3), the enum typed fields that are nullable may not comply with OpenAPI specification (for 3.0.x). The topic around enum fields with nullable: true has been clarified/answered by OAS project (amended in spec version 3.0.3 in 2021): (Reference: https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md ) | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | To align with Open API spec clarification at https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md, we have updated all Data Types that are nullable and have an enum to align as follows: Following discussion, have decided to align with OpenAPI 3.1 DI-076-Estimation-Reason-Code: description : Used inconjunction with Settlement Period Quality Indicator to explain why data has been estimated type : string nullable: true maxLength : 2 example : '1' enum: - '1' # OptOut - '2' # Missing .. - '8' # Disconnected - '9' # Consumption Amendment - '10' # NonSmart - null The Data Types affected / updated as as follows: --- DI-039-Load-Shape-GSP-Group-ID --- DI-076-Estimation-Reason-Code --- DI-096-Site-Visit-Check-Code --- DI-126-Traditional-Fall-Back-Read-Frequency --- DI-137-IHD-Install-Status --- DI-150-Annual-Consumption-Quality-Indicator --- DI-166-Supplier-Consumption-Amendment-Reason-Code | Data interface correction | Minor | Interface Changes | Swagger 1.3
MHHS-DIN-477 | SW |  | 2023-07-03 | MHHS |  | Steve Weston | SRO Design | Swagger alignment to OpenAPI 3.1 specificiation | Align with Open API specification 3.1 to remove nullable :true and replace with type declarion ie, type:[string:”null”] | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Further details of the solution are under discussion/review.
MHHS-DIN-478 | SW |  | 2023-07-03 | MHHS |  | Rob Golding | Central Body | IF-021 max number of days of consumption data | In the Release 2 version of DES138 a limit was introduced that asked Participants not to submit more than 150 Settlement Days’ worth of data in a single message. The value of 150 was proposed as this meant a single message would realistically be ~600KB in size. We’ve had some queries regarding this value, and given ECS should reject consumption data if it over 194 days old, the proposal is to increase sizing from 150 to 194 day message and the size increases from 600KB to ~780KB for IF-021 message. ECS will need to validate the message contents. However, rather than letting a ‘large’ IF-021 message traversing though the DIP, the proposal is to limit the IF-021 on ingress to the DIP and a single request will have a limit of 1MB – this will done at the API level. | Requires Industry Work Group review | 2023-07-17 | Interim Release 4 | 2023-08-16 | DIN DETAILS TO BE UPDATED FOLLOWING DRG 17/07/2023
MHHS-DIN-479 | SC |  | 2023-07-03 | SCS |  | Maddison | SCS | Change to Consent Notification on IF-036 | SCS have suggested that B068 should only be required for DSApp Events. | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | Block 068 on IF-036 amended to that it is only Mandatory for DSApp Events. | Data interface correction | Supporting Docs | Interface Change | DES138-InterfaceCatalogue
MHHS-DIN-480 | SC | DI-195 | 2023-07-03 | SCS |  | Maddison | SCS | Reverse DIN-105 | SCS have confirmed that it is possible currently and should continue to be possible to manage MPAN Linkages whilst MPAN(s) are at Created Status. Therefore we have reversed the change implemented at part of DIN105 and now allow processing of IF-019 if mpan status = "Created" | Ready for Internal Review |  | Interim Release 3 | 2023-07-12 | SCS have confirmed that it is possible currently and should continue to be possible to manage MPAN Linkages whilst MPAN(s) are at Created Status. Therefore we have reversed the change implemented at part of DIN105 and now allow processing of IF-019 if mpan status = "Created" | Data interface correction | Supporting Docs | Interface Change | DES138-InterfaceCatalogue
MHHS-DIN-481 | SW |  | 2023-07-06 | Elexon | 2106 | Nigel Rees | Central Body | REP-003 inconsistency between DES-138 | We have a contradiction between the DT-023 and the swagger spec. As there is an example we will implement based on the example but it looks like the person who wrote the ECS report catalogue used the correct convention. e.g. on REP-003 we have DT-023 as NUM (16,6). If we follow the convention used in the DIP interface spec, this would translate to 1234567890123456.123456, however the swagger suggests 123456789.123456 Screenshot from REP003 in external ECS reporting catalogue https://app.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.3#/components/schemas/DT-023-Positive-Decimal-9-6 DT-023-Positive-Decimal-9-6: description: Number (9,6) format type: string pattern : ^[0-9]\d{8}(\.\d{6})?$ example: 123456789.123456 | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Further details of the solution are under discussion/review.
MHHS-DIN-482 | KH |  | 2023-07-10 | C&C | 2394 | Hazel Cotman | Software Provider | Interim Release 2 query - IF-018 | LDSO’s are not detailed as ‘To Parties’ within IF-018 flow, however, the LDSO is a secondary routing party for updates to the Domestic Premise, Energy Direction Indicator, and the Metered Indicator | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Further details of the solution are under discussion/review.
MHHS-DIN-483 | KH |  | 2023-07-10 | BGAS | 2410 | Neil Stranger | Supplier | MHHS Design Query - date/ time in DES138 | In DES138 there are a number of data items that are defined as having a date/time structure, but the name and description only refer to the date element whereas others refer to date and time. Therefore for those that make no reference to time we need to be 100% clear if the time should be when the event occur or should it be defaulted to say midnight. This is to ensure consistent population/use across the market. | Closed |  |  |  | Related to a Design Principle and agreed as per E2E Architecture
MHHS-DIN-484 | SW |  | 2023-07-10 | MHHS | 2352 | Martin Freeman | Central Body | Clarity on RecipientId and SenderID in StandardResponseBodyType | RecipientID in the Standard Response Body is a mandatory field. When submitEvents (or in IR2 dip-channel) is called, the DIP synchronously returns a Standard Response Body. At this point the DIP does not even know what message recipients the message will be routed too, since the response is returned synchronously whereas routing is performed asynchronously. So the DIP has no way to know what to set recipientID to. It is also important to note that a message can be received by multiple recipients, yet this recipientID is a scalar that only supports being set to a single value. So it isn't clear how that could work. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Update section 4.6.1 in the E2E001 Design document to provide better clarity on how SenderID and RecipientID are populated in the StandardResponseBodyType. Provided worked examples for L1-L6 to illustrate this as examples. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-485 | SW |  | 2023-07-10 | MHHS |  | Steve Weston | Central Body | Unable to identify Recipient / Role on DELETE | For the DELETE methods in Swagger for StatusMessage and PublicationConfig, need to update the method so you can identify the correct recipientID and roleID to be used for the method call. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Further details of the solution are under discussion/review. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-486 | SB |  | 2023-07-11 | MHHS | 2107 | Rob Golding | Central Body | DES138 and message addressing information | Please can you raise a DIN to cover the following request from Participant to clarify the From and To Parties at the top of each sheet to align with the role codes the programme is using and defined in the E2E Solution Architecture document. And if these ‘pure’ roles code could be included in the introduction sheet that would certainly help. More detail can be seen in the Ticket | Closed
MHHS-DIN-487 | SW |  | 2023-07-11 | MHHS | 2379 | Martin Freeman | Central Body | Clarity on schema vs data validation failures, with updated examples. | In section 4.4.4.2, there are some examples that incorrectly return a 207 when they have failed schema validation. E2E001 needs to be updated to provide different examples of schema vs data validation errors to illustrate how this will be handled correctly. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Further details of the solution are under discussion/review. | Design Ambiguous | Supporting Docs | E2E Architecture Document
MHHS-DIN-488 | ME |  | 2023-07-11 | MHHS |  | ME | SRO Design | Correct Reporting Cat vs Swagger | Reinstated DI-484 "Settlement Period Duration" and added into R Groups as required | Ready for Internal Review |  | Interim Release 4 | 2023-08-16 | Reinstated DI-484 "Settlement Period Duration" and added into R Groups as required | Data interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-489 | MF |  | 2023-07-11 | Design Team |  | Mike Fensome | SI Design | Schema Optionality incorrectly defined for Common Block | In DES-138, the Common Block shows some fields where the Schema Optionality is defined as Optional, rather than Mandatory. The list of Blocks are as follows - Common Block: S1, D0, A0 | Ready for Internal Review |  | Interim Release 4 | 2023-08-16 | Update Schema optionality in DES138 to show that all data items must be present where the block is present in line with updated E2E Solution Architecture. Common Blocks impacted: S1, D0, A0 | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-490 | SW |  | 2023-07-11 | MHHS | 2395 | Martin Freeman | Central Body | Level 1 validation clarity for POST /statusmessage be the same as for POST /dip-channel/{id} | The E2E001 v3.2 (section 4.4.3) describes how for the Send Messages API, when the DIP performs level 1 validation, if any message in the request fails validation then the entire request is rejected. Section 4.6 Send Status Messages API does not describe the DIP validation for status messages at all. Should validation for POST /statusmessage be the same as for POST /dip-channel/{id}, in that a level 1 validation failure for any message should fail the entire request, or should messages that pass validation be accepted and messages that fail be rejected independently? | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | This should be consistent across all interfaces in that a schema validation failure for any message should fail the entire request. In the E2E001 design, sections 4.4.3 and 4.6 are to be updated to reflect this / provide the appropriate level of clarity. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-491 | SB |  | 2023-07-11 | Utilita | 2408 | Adam Barnes | Supplier | DES138 v5.2.1 | IF-035 tab for the bottom 3 entries it still refers to the previous version definition of routing parties – we expect this to be a slight oversight as SDSS is no longer defined as a recognised party? | Open - awaiting assessment |  | Interim Release 6 | 2023-10-20
MHHS-DIN-492 | KH |  | 2023-07-11 | Stark | 2125 | Matthew Peters | Supplier | IF-034 Proposed Appointment Response Code Formatting | The data type within DI-143 block for IF-034 and IF-035 needs to change from String 200 to Array because there is a possibility of getting more than 1 rejection code. | Open - awaiting assessment |  | Interim Release 6 | 2023-10-20
MHHS-DIN-493 | SC |  | 2023-07-12 | SCS |  | Sean Cooper | SRO Design | Changes to IF-019 Secondary MPAN validation | SCS had originally suggested a validation rule to prevent Secondary (Related) MPANs being linked to an Export MPAN. However, RECCO and EON have highlighted there are a very small number of scenarios where this might be the case. Following further discussions with SCS they are now happy to remove this rule (REG1068) | Ready for Internal Review |  | Interim Release 4 | 2023-08-16 | IF-019 - REG1068 check for Secondary MPAN Linkage to export REMOVED | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-494 | SW |  | 2023-07-12 |  | 2462 | Neil Edney | Software Provider | Incorrect Min and Max Values for DI-091-Number-Of-Displayed-Register-Digits | DI-091-Number-Of-Displayed-Register-Digits currently has a minimum of 1 and maximum of 1, when this should be 5 and 6 respectively to align with DES-138 as this is an Integer. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 to be updated for DI-091 minimum is 5 and maximum is 6. Currently this is 1 and 1 respectively which is incorrect. | Design Ambiguous | Supporting Docs | Swagger | Swagger 1.4
MHHS-DIN-495 | SC |  | 2023-07-12 |  |  | Sean Cooper | SRO Design | Correction to BP003 | IF-035 for Trad/Advanced meters was previously shown as being direct interaction between REGS and MS ... Changed to show message as flowing via the DIP | Ready for Internal Review |  | Interim Release 4 | 2023-08-16 | IF-035 for Trad/Advanced meters was previously shown as being direct interaction between REGS and MS. Changed to show message as flowing via the DIP | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-496 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 | MHHSP-METH001_SDS_Validation_Estimation 5.1 section 2.7 States "SDS shall inform the Supplier using the Meter Reading Reason Code on the IF-041/PUB-41" . There is no Meter Reading Reason Code on the IF-041 in DES138 v5.1.2. Therefore, either Meter Reading Reason Code should be included in DES138, or this requirement should be removed. | Open - awaiting assessment |  | Interim Release 6 | 2023-10-20 | Remove the following from METH001: 'Where consumption data has been deemed invalid the SDS shall inform the Supplier using the Meter Reading Reason Code on the IF-041/PUB-41.'
MHHS-DIN-497 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 | MHHSP-METH001_SDS_Validation_Estimation 5.1 Section 5.4 Where DA records are < 90 days from UTC date this is inconsistent with Method 4, which states "DA is available [either in the past or future] and less than [3] months different from the UTC Date requiring a daily Meter advance". | Open - awaiting assessment |  | Interim Release 6 | 2023-10-20 | Be consistent - use either 90 days or trhee months within the document
MHHS-DIN-498 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 Method 13 | MHHSP-METH001_SDS_Validation_Estimation 5.1 Method 13 This describes the outcomes for Smart and Advanced meters. Does this imply that traditional meters should have zero consumption submitted to settlements, or should Method 13 text be adjusted to include trad meters? ALSO If actual data is recovered, or an Advance Meter Reading is received, and this indicates zero consumption, should this be submitted to settlements? The first part of the sentence implies it should be submitted, and the brackets imply it shouldn't. | Open - awaiting assessment |  | Interim Release 6 | 2023-10-20 | Alter wording of Method 13 to reflect we shouldn't be sending estimates for Deenergised trad meters as well as Smart and Advanced, AND 'there is no need to submit zero consumption for de-energised MPAN's' needs changing to refer to 'zero ESTIMATED consumption'
MHHS-DIN-499 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Alignemtn of Estimation Reason Codes | METH001 refers to Estimation Reason Code 'Adjustment'. DES138 refers to 'Consumption Amendment' Assume these are the same thing and need to be aligned between both sets of documentation | Open - awaiting assessment |  | Interim Release 6 | 2023-10-20 | Align Method Statements to match the Estimation Reason Codes within DES138
MHHS-DIN-500 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | ISD Entity M17 Example Correction | MHHSP_EDI021_ISD_Entities 5.1 Entity id M17 Industry Standing Data: MHHS Entities/Data Items v5.1 ISD Entity Id M17 - Valid Consent Granularity Combinations, includes combination I¦F¦S¦D. According to Decision 2 in "https://www.ofgem.gov.uk/sites/default/files/docs/2019/06/access_to_data_consultation_ofgem_response_0.pdf" a non-domestic customer is unable to opt out. The OFGEM document states "There will be no opt out possible for microbusinesses in relation to data for settlement purposes". Therefore, I ¦ F ¦ S ¦ D is not a valid combination. | Open - awaiting assessment |  | Interim Release 6 | 2023-10-20 | Remove I ¦ F ¦ S ¦ D from the example list
MHHS-DIN-501 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Addition of Method 13 to METH002 | MHHSP-METH002_ADS_Validation_Estimation 5.1 Section 3.16 States "The below estimation methods are based on those used in the Smart Data Service (SDS) Method Statement. For that reason, methods 0, 1, 6, 11 and 13 have been omitted as they are only applicable to Smart meters." However, method 13 is "Estimation for a Site where Supply is de-energised" and this is included in METH002 in section 2.29. The statement is wrong as some of the methods have been renumbered in METH001 since this was written. | Open - awaiting assessment |  | Interim Release 6 | 2023-10-20 | Update METH002 to add MEthod 13 back in
MHHS-DIN-502 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | SP Quality Indicator Clarification | MHHSP-METH001_SDS_Validation_Estimation 5.1 It is our assumption that if NO estimation is required, the Settlement Period Quality Indicator should be set to "A". This is however, never explicitly mentioned. The only mention of using value "A" is for method 1. | Open - awaiting assessment |  | Interim Release 6 | 2023-10-20 | Update artefacts to clarify when to use A as the SEttlement Period Quality Indicator value
MHHS-DIN-503 | SW |  | 2023-07-13 | SIMS | 2439 | Martin Freeman | Central Body | S1.senderUniqueReference interface component is too small to identify the message interface | DES138 and the E2E001 the S1.senderUniqueReference property has a 3 digit component that contains the interfaceID of the message. However since the reporting interfaces reuse the same interface numbers as the standard interfaces, and some reporting interfaces have 4 character interface identifiers, this means this component is not sufficiently large to unambiguously identify which interface a given senderUniqueReference was generated for. This also applies for TransactionID. | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | Update any Data Items that utilise InterfaceID to align with the enumeration of values defined for DI-000 to that this is unique across all interface / report types. This includes data types like SenderUniqueReference (DI-995) and TransactionID (DI-990). This change will require updates in DES-138, E2E001 and Swagger 1.4. | Design Ambiguous | Supporting Docs | DES-138, E2E001 and Swagger 1.4 | DES-138, E2E001 and Swagger 1.4
MHHS-DIN-504 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Clarification of link between IF22/IF23 | DES138 IF-022/023 IF an IF-022 or IF-023 is re-issued, can you confirm that they will be reissued as a pair so that the totals align? The issue is if an updated IF-022 is issued with new values, should the SDS/ADS await an updated IF-023, or not? How can the SDS/ADS pair the IF-022 and IF-023 without doing their own summations? | Open - awaiting assessment |  | Interim Release 6 | 2023-10-20 | Update BRS007 to show that a re-run of IF-022 will result in a rerun of IF-023
MHHS-DIN-505 | BK |  | 2023-07-13 | SCS |  | Sean Cooper | SRO Design | DUoS Tariff ID to hold values from 1-3 in length | The DUoS Tariff ID needs to be updated in Swagger and the Interface Catalogue so that it can hold values from 1 to 3 in length in order to align with ISD. | Ready for Internal Review |  | Interim Release 4 | 2023-08-16 | Update DUoS Tariff ID to hold values from 1 to 3 in length in Swagger and Interface Catalogue | Data interface correction | Supporting Docs | Interface Catalogue and Swagger 1.4 | DES138-InterfaceCatalogue Swagger 1.4
MHHS-DIN-506 | BK |  | 2023-07-13 | Design Team |  | Sean Cooper | SRO Design | Renaming of IF-014 | Rename IF-014 to clarify the purpose | Ready for Internal Review |  | Interim Release 4 | 2023-08-16 | Changed to "UTC Settlement Period Consumption Data (Warnings & Rejections)" | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-507 | SC |  | 2023-07-14 | Design Team |  | Sean COoper | SRO Design | Clarification of IF-036 Routing Requirements | Update IF-036 to clarify / provide additional info on the routing destinations of IF-036 | Ready for Internal Review |  | Interim Release 4 | 2023-08-16 | Added following Text: Primary Routing Participants for IF-036 MSAppActive • Supplier (i.e. the supplier who initiated the appointment, either current in the case of Change Of / Update to SP’s, or incoming in the case of a COS) • Metering Service (i.e. the Metering Service being appointed) • [Partner] Data Service (i.e. the Data Service in effect on the App Start Date of the MS Appointment – this could be either an ‘existing’ Data Service in the case of an MS Only appointment OR the ‘incoming’ Data Service with a coincident App Start Date to that of the [incoming] Metering Service • Linked Supplier(s) – (ie the Supplier(s) with responsibility for the Linked [Import/export] MPANs on the App Start Date of the Metering Service Appointment) DSAppActive • Supplier (i.e. the supplier who initiated the appointment, either current in the case of Change Of / Update to SP’s, or incoming in the case of a COS) • Data Service (i.e. the Data Service being appointed) • [Partner] Metering Service (i.e. the Metering Service in effect on the App Start Date of the DS Appointment – this could be either an ‘existing’ Metering Service in the case of an DS Only appointment OR the ‘incoming’ Metering Service with a coincident App Start Date to that of the [incoming] Data Service • Linked Supplier(s) – for Advanced Segment Meters only - (i.e. the Supplier(s) with responsibility for the Linked [Import/export] MPANs on the App Start Date of the Metering Service Appointment) | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-508 | SC |  | 2023-07-17 | Design Team |  | Sean Cooper | SRO Design | Addition of MP Status and RMP Status Effective From Dates to IF-050 | Addition of MP Status and RMP Status Effective From Dates to IF-050 | Initial Assessment/Updating |  | Interim Release 4 | 2023-08-16 | New Data Items Created DI : DI-167 RMP Status (Registration) DI-168 MP Status | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-509
MHHS-DIN-510
MHHS-DIN-511

## Metadata (hidden)
Constituency | Current Status | SI Initial Assessment | DA Type
Software Provider | Initial Assessment | Clarification - No Further Action | Accept - Minor
Central Body | Awaiting Impact Assessment | Actioned | Accept - Major
Consultancy | Awaiting DA Decision | Accept - Minor | Reject
Data Service Provider | To Confirm with Raiser | Accept - Major
Metering Service Provider | Validate with SRO | Duplicate
Network Business | Rejected | Change Request
Network Operator | Approved by DA | Reject
SI Design | Awaiting DAG Decision | TBD
Supplier | Approved by DAG
Awaiting Assignment to Release
Awaiting Implementation
Closed