## Backup 220923 (hidden)
DIN ITEM DETAILS | [11 empty] | Scheduling |  |  | DIN IMPACT ASSESSMENT |  |  |  |  | DIN OUTCOME
Reference | Created BY | other Reference(s) | Date Raised | Organisation | Freshdesk Ticket # | Contact Name | Constituency | Title | Design Issue Notification Details (as notified by participant) | Related CR | Current Status | Target working Group Date (If Required) | Target Release | Objection Cut-off Date | Design Issue Proposed solution | Justification/Type of Change | Design Area | Design Area - L2 | Artefact(s) Impacted | DAG Review Date | DAG Outcome | Reason for Rejection/Accept caveats | Design Change Reference Number | Internal Freeze Date
MHHS-DIN-1 |  | T4-COM-1744 | 2023-01-30 | St Clements | 2655 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1744 on 15th Sept 2022 MPRS does not currently restrict IHD Installs to Smart Meters, there maybe cases where there is an IHD present but the Meter is Trad (Not compatible with DCC and Customer Switched) Either Allow IHD on all Market Segments OR Cleansing to ensure IHDs are only present on S2 and S1 Meters SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses, as this is still not resolved |  | Implemented |  | Interim Release 1 |  | Discussed with SCS and agreed to add new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) Added requirements into BRS003. SCS to raise a potential data cleanse. | Requirement correction | MPAN Ownership | SCS Validation | MHHSP-BRS003-Registration Requirements | 2023-03-23
MHHS-DIN-2 |  | T4-COM-1745 | 2023-01-30 | St Clements | 2657 | Madison Layton | Software Provider |  | Orginally raised as T4-COM-1745 on 15th Sept 2022 DB002 is not the interface on which MPRS will be informed of a change to import/export relationship, it is DB05. The wrong diagram was updated, the EDI was updated to DB05 not import/export. SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses and artefact updates, to inform the wrong data item diagram was updated. However the diagram for EDI updates is still incorrectly reading DB005 update instead of DB02 |  | Closed |  |  |  | This appears to have been missed in v4.6 - the arrow on BP-010B from step435 to Step 440 shows DB005 (not DB05, assume that’s a minor typo in the comment) - and this is the Energy Direction Information (EDI) which is wrong. It has cbeen onfirmed that this was updated in v4.7 to go into v5.0 baseline. | No Change |  |  | None
MHHS-DIN-3 |  | T4-COM-1752 | 2023-01-30 | St Clements | 2661 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1752 on 15th Sept 2022: MHHS-BR-RS-020: "Retro" (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier ) In the D0205 the Supplier can cancel out the current Agent Appointment by setting the EFD to equal the currently stored Appointment EFD. Is this no longer allowed? All Services must be appointed for at least one day valid or not? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: removing the ability for Suppliers to Correct Invalid Service Appointments may not be understood by suppliers. We want to avoid a later Design CR to add this functionality in. SCS has not had a response, feel this is important discuss with Suppliers to avoid later CRs |  | Closed |  |  |  | The appointment can be resubmitted if it hasn’t been accepted yet. Once accepted, there is a need to maintain contiguous appointment periods. The scenario mentioned is the CoA not linked to a switch, so the acceptance of a new appointment from a particular EFD will ‘lock in’ that date and the previous MS/DS will be de-appointed at midnight on the previous day. This is to ensure that there are no periods left without MS and/or DS in place, which can happen today with D0155/D0151 sequencing issues. As an overall comment, there is not a concept of cancellation of appointments. The only way to alter the appointment is to get a new IF-031 issued. The only way to do this for the scenario presented, would be to issue an IF-031 for the old MS for the original date and an IF-031 for the new MS for the revised date. Requirement MHHS-BR-RS-021 ensures that Registration Service will action the latest received appointment where there are duplicate appointments for the same day. St Clements had requested that we build in a rule saying that you cannot submit a Change of Service Provider (CSP) request for the same Service Provider. It is a bit of a work-around, but we believe sending it as SEG should work, or alternatively a CR would be required to re-look at the interface validation. Closing, as this doesn't require further action - point noted. We have already spoken to a number of suppliers, and will continue to engage to ensure the functionality of the baselined design is understood and any issues picked up as early as possible. Documentation for LDSOs to point at. Pick up in Code Drafting as well. | No Change |  |  | None
MHHS-DIN-4 |  | T4-COM-1755 | 2023-01-30 | St Clements | 2666 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1755 on 15th Sept 2022: MHHS-BR-RS-071.2 REC CP R062 has been raised to remove the restriction on the number of EDI changes. Will this cause any downstream MHHS issues? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Needs to be aligned with REC Change No responses |  | Closed |  |  |  | As per original SRO response, the impacts of the REC change need to be dealt with through the REC change process and impact assessment. | No Change |  |  | None
MHHS-DIN-5 |  | T4-COM-1760 | 2023-01-30 | St Clements | 2667 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1760 on 15th Sept 2022: There are no Registration Service Reports defined in MHHSP-ERI011A. Will there be a requirement for MPRS to produce any Industry Reports for MHHS? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Design for the complete solution must be defined by M5. This is a DBT Design Start Blocker No responses This could significantly increase DBT time as development of reports can be costly and time consuming |  | Closed |  |  |  | Who is raising these requirements? What happens today? Possibly CC issues Agreed with SCS that reporting requirements will be introduced via the CR process. Reporting requirements are to be added to the programme RAID log | No Change |  |  | None
MHHS-DIN-6 |  | T4-COM-1761 DI-7 | 2023-01-30 | St Clements | 2668 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1761 on 15th Sept 2022: IF-005, REG1014 First MAP Block, MAP Eff From Date [DI-054] in message, must = MPAN Install date OR >= Eff Form date of all existing MAP Effective From Dates held in Registration prior to first [DI-054] in message I understand that the First MAP must equal the Install Date, I am unsure what the second condition is trying to say? You can not have a Meter Without a MAP. (ignoring customer owned meters where CUST is used) SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: response is incorrect. The Second Rule "Each subsequent MAP Effective From Date [DI-054] must be > MAP Eff From Date in previous block" covers the subsequent overlapping MAPs. The second half of this First Block Rule must be removed. The First Block can only ever equal the install date No responses, the rule has not been amended |  | Implemented |  | Interim Release 1 |  | This appears valid - the first MAP block can only start at the creation date (assuming the MAP blocks are in chronological order, which they must be if each subsequent map block has an EFD > the last) Currently the design allows 2 ways to amend the MAP History as outlined in Sections 13 and 14 of the IF005 Use Case Guide. Either the Metering Service can provide the full MAP history from the installation date or they can add a new MAP to the existing history, provided it is the next MAP in chronological order. So for example if you have MAPs 1,2 and 3, then you can extend to MAPs 1,2, 3 and 4 using the approach set out in section 14 to extend the MAP history. However if you wanted to set MAP 4 between 2 and 3, you would need to send the whole MAP history from the install date and provide 1,2,4 and 3 as set out in Section 13 to replace MAP history. The second validation rule is required if you are using the extend the MAP history functionality. Added note to REG Notes that where a MAP history is provided it must be in chronological order Added new REG1014 Validation Rule to MeterInstall and MeterExchange events to ensure only 1 MAP block is provided | Data interface correction | MPAN Ownership | SCS Validation | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-7 |  | DI-8, DI-11, DI-12, DI-14 | 2023-01-30 | St Clements | 2669 | Madison Layton | Software Provider |  | MPRS will reject any PUB-031 inlcuding those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8) |  | Implemented |  | Interim Release 1 |  | See Comments Revised CSS Registration Request ID validation on IF-031, 034 and 025 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | IF General | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-8 |  | N/A | 2023-02-01 | Elexon | 2642 | Sedef Kiris | Central Body |  | We have had the following comment ........... Also just found out that “Metering Service Id” have “MPID” in brackets afterwards, and not “MSID”. We believe it should be MSID |  | Closed |  |  |  | MPID is the correct term here, it is the metering service MPID. MHHSP_EDI012_ISD_Entities v4.6 Section M8 | No Change |  |  | None
MHHS-DIN-9 |  | N/A | 2023-01-30 | St Clements | 2672 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: [UpdateSiteTechnicalInfoMS] is not included in the interface catalogue and is not utilised by MPRS. Assume this is related to Issue 99 and needs removing? (raised as DI ID 9) |  | Implemented |  | Interim Release 1 |  | Removed from IF-005 Guide Section 4.1 | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-10 |  | N/A | 2023-01-30 | St Clements | 2799/2670 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: Is the currently appointed Meter Service informed of Prospective MS changes? Changes to MTDs can be made by prospective MS (e.g. change meter type to complete SEG market change before the MS can be appointed). As the MS is only prospective at this point the MS may still be lapsed and not take effect. However any MTD updates made would remain within the MPRS system and not be backed out. The current MS would therefore need to be aware of what changes have been made by the prospective MS. (raised as DI ID 10) |  | Closed |  |  |  | BP009 only talks about the Metering Service, not the current or prospective Metering Service, and it appears only the registration service receive metering service MTD details, not the current MS. Refer to SRO - what is the assumption here, as the alternative route is for registration to update the current MS The design is based on PUB-006, with the Updated Meter details, being sent to the current Metering Service ( BP011A step 280 ) as well as the Prospective Metering Service (Step 275). It is built into the routing rules in PUB-006. | No Change |  |  | None
MHHS-DIN-11 |  | N/A | 2023-01-30 | St Clements | 2675 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install / Remove Date(s) takes place within the Metering Services period of ownership (or proposed period of ownership for in the case of a prospective SEG appointment) " Sent on 11th Jan: Does not match business rules, as future dated installs are not allowed: "REG1020 - Meter Install Date [DI-057] cannot take place in the future. The proposed MS on a seg will have a future dated EFD, so they only have the +2 day lapse extension period for meter installs (raised as DI ID 11) |  | Implemented |  | Interim Release 1 |  | Added change of segment scenario's to IF005 USE CASE Guide. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 |  | Refer back to SCS as additional comentary needed on the issue and bring to next meeting
MHHS-DIN-12 |  | N/A | 2023-01-30 | St Clements | 2679 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install /Remove Date(s), cannot have taken place in the future" Sent on 11th Jan: It would be useful to have the Change of Segment process covered in this guide. We are not sure how the Prospective MS can exchange meters when their appointment period is in the future (raised as DI ID 12) |  | Implemented |  | Interim Release 1 |  | Nomenclature issue - requires a reword of this statement to conform to the business rules. Recommend the following update to section 3.2 of the IF005 Use Case Guide to confirm who can make Metering updates Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed BAU metering updates ( For the avoidance of doubt not meter update/meter history updates), it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. The one exception, is during a change of segment, when the incoming Metering Service is able to provide a BAU metering update, where it’s prospective “SEG” appointment is due to become active on the same day. SEG scenario's added to IF005 Use case guide Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-13 |  | N/A | 2023-01-30 | St Clements | 2683 | Madison Layton | Software Provider |  | Comment on Section 5.1 "validation allows for meter removal at a point following Disconnection if required)" Sent on 11th Jan: This rule prevents this REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational (raised as DI ID 13) |  | Implemented |  | Interim Release 1 |  | This statement doesn't appear to be a convention. There is no mention of this in E2E001 End to End Solution Architecture. Believe this statement needs to be amended or removed. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. IF-005 validation Rule changed to include meter removal at status Disconnected | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES138-Interface Catalogue, E2E001 End to End Solution Architecture
MHHS-DIN-14 |  | N/A | 2023-01-30 | St Clements | 2684 | Madison Layton | Software Provider |  | Comment on Section 3.2 "Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed metering updates, it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. " Statement is misleading- the 10 day period is only permitted for install, remove and exchange events, it is not listed for meterUpdate/meterHistoryUpdate in interface catalogue Also the prospective MS should be able to make changes for SEG to enable a market segment change to complete (raised as DI ID 14) |  | Implemented |  | Interim Release 1 |  | Validation rule(s) updated to constrain 10 day window to non-update events. Test in 3.2 reworded to remove ambiguity. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Refer back to SCS for additional clarity on the requirement and include RecCo and bring to next meeting
MHHS-DIN-15 |  | N/A | 2023-01-30 | St Clements | 2685 | Madison Layton | Software Provider |  | Comment raised in guide, sent on 11th Jan, that the JSON examples use MPID when it should use DIP ID e.g."distributorID": "SWAL" (raised as DI ID 15) |  | Implemented |  | Interim Release 1 |  | Corrected to use Dist DIP ID | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-16 |  | N/A | 2023-01-30 | St Clements | 2686 | Madison Layton | Software Provider |  | Comment on Section 9 " Albeit that these transactions can be ‘clubbed together’ and send as a group in single overarching message/API transaction. " Sent on 11th Jan: As DIP does not protect the sequencing of events (FIFO), is there a risk that the ordering of these updates might arrive out of sequence resulting in the wrong end state? If MS space out their updates it would reduce this risk (raised as DI ID 16) |  | Implemented |  | Interim Release 1 |  | Clairifcation added to Sec 9.2 to reference Time-Stamps rather than 'clubbing' | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-17 |  | DI-017 | 2023-01-30 | St Clements | 2690 | Madison Layton | Software Provider | MAP History availability to Metering Service | Section 9 says "a supporting MAP history commencing in line with the revised Installation Date must also be provided" Will the MS know the full MAP history? Risk they could destroy the data. Potential MAP billing issues? |  | Implemented |  | Interim Release 3 | 2023-07-12 | Solution agreed at DRG on what MAP updates are required. Various document updates required to align with DRG decision to only maintain latest MAP. Removed section 13 from IF005 user guide plus other corrections to doc. Updated DES138 IF005 validation rules. | Missing/incorrect validation rule | Supporting Docs | Various Documents | IF-005 Use Case guide MHHSP-DES138-Interface Catalogue |  |  |  |  | 14//7
MHHS-DIN-18 |  | N/A | 2023-01-30 | St Clements | 2691 | Madison Layton | Software Provider |  | Comment on Section 9 "• When maintaining the MAP History in cases where there is no change in Meter Installation Date then the MAP history provided should commence either with a MAP Effective From Date matching the existing install date of the meter OR be greater than the most recent, already existing, MAP Effective From Date" Sent on 11th Jan: So it's possible to update ALL MAP history back to installation, or add a new MAP, but it's not possible to amend MAP history only part way back (have to go back to installation date instead every time to do this) (raised as DI ID 18) |  | Closed |  |  |  | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • To update BRS003, requirement MHHS-BR-RS-027 to add “Registration Service must lapse any appointments that fail this validation” • Remove Rejected from Step 225 of BP002/BPD002 • Remove Rejected from label on line after step 215 of BP003. | No Change |  |  | None
MHHS-DIN-19 |  | N/A | 2023-01-30 | St Clements | 2692 | Madison Layton | Software Provider |  | Comment on Section 10 "E2E Architecture convention states that all data items are provided in each message even where these data items are not changing or are null" Sent on 11th Jan: Some of the items are optional not mandatory which conflicts with this statement. Not all data items need to be provided (raised as DI ID 19) |  | Implemented |  | Interim Release 1 |  | Update of E2E Doc to allow for Nullable values. | Data interface correction | Meter to Bank |  | MHHSP-E2E001 End-to-End Solution Architecture | 2023-02-23 |  | Defer as a E2E clarification may be needed
MHHS-DIN-20 |  | N/A | 2023-01-30 | St Clements | 2693 | Madison Layton | Software Provider |  | Comment on Section 13, sent on 11th Jan: What should MPRS do if it holds a MAP not included in the MAPHistory block? (raised as DI ID 20) |  | Implemented |  | Interim Release 1 |  | Update "all existing history will be replaced by that contained within the message" | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-21 |  | N/A | 2023-01-30 | St Clements | 2699 | Madison Layton | Software Provider |  | Comment on Section 15.2 "It is understood that currently there a numerous instances of duplicated Meter ID’s, some of which may have overlapping installation dates. " Sent on Jan 11th: Meter id is only unique at mpan. Should not be any instances of conflicted MSNs at MPAN. Can you verify with ECOES? Or we can do a RFI to DNOs but will take time (raised as DI ID 21) |  | Implemented |  | Interim Release 1 |  | All references to duplicated MSN IDs has been removed from the document | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-22 |  | N/A | 2023-01-30 | St Clements | 2700 | Madison Layton | Software Provider |  | Comment on Seciton 15.3 "add some kind of suffix (X1, X2) to the existing Meter ID." Sent on Jan 11th: This can take the meter ID over the allowable string length (string 10), in this example it would take it to string(12) and so would be rejected (raised as DI ID 22) |  | Implemented |  | Interim Release 1 |  | As above, Section 15.3 removed from IF-005 User Guide. | Data interface correction | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-23 |  | N/A | 2023-01-30 | St Clements | 2701 | Madison Layton | Software Provider |  | Comment on Section 16.3 Sent on Jan 11th: Cancelled Flag Set. Only a logical deletion. Still held in MPRS but not visible to EES/MEM The section implies the record would be fully deleted from MPRS, however this is not correct, MPRS would set a cancellation flag that would indicate the record has effectively been cancelled/logically deleted. It would however remain in the systems database (raised as DI ID 23) |  | Implemented |  | Interim Release 1 |  | Added a statement at the end of the table in 16.3 to say "NB the registration service will only logically delete the MAP entry with a flag, it will not be deleted from the database." | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Accepted
MHHS-DIN-24 |  | N/A | 2023-01-30 | St Clements | 2702 | Madison Layton | Software Provider |  | Comment on Section 17.2 "situations where multiple existing meters are identified, the selection process should be extended to include Meter Removal date (if provided) else;" Sent on Jan 11th: Shouldn’t be possible, can run an EES or MPRS RFI to confirm. Noting that MSN is only unique at an MPAN level not a databse level Related to DI-21 (raised as DI ID 24) |  | Implemented |  | Interim Release 1 |  | Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. The wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-25 |  | N/A | 2023-01-30 | St Clements | 2706 | Madison Layton | Software Provider |  | Comment on Section 17.2 "where multiple meters still exist even after matching on all three data items should be rejected and require manual intervention (i.e. request to LDSO to intervene) ." Sent on Jan 11th: There's no super user functionality for this so how could the LDSO intervene? The LDSO is not able to manually intervene in regards to MTDs, they can for some other data items such as registration data but not MTDs. (raised as DI ID 25) |  | Implemented |  | Interim Release 1 |  | Reference to LDSO User Removed - agreed with SCS that scenario should not arise provided existing SCS data rules are met | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-26 |  | N/A | 2023-01-30 | St Clements | 2707 | Madison Layton | Software Provider |  | Comment on Section 17.2 "If the MAP segment is not provided, the existing MAP history should be maintained to greatest degree possible, with ‘trimming’ to align to any revised Install / Remove Dates provided" Sent on Jan 11th: Risk that changing of the Meter Lifespan could result in MAPs being logically deleted. The MS would need to re-apply the MAP history to fit into the new meter Lifespan MS would need to understand this process/constraint (raised as DI ID 26) |  | Implemented |  | Interim Release 1 |  | Section 17.2 of the guidance document updated. Also added new validation rule REG1014 for MeterHistoryUpdate in IF-005 to ensure MAP is provided when creating a new meter picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-03-23
MHHS-DIN-27 |  | N/A | 2023-01-30 | St Clements | 2708 | Madison Layton | Software Provider |  | Comment on Section 19.2 "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the permanent deletion of data, mirroring the existing functionality associated with the use of the D0312." Sent on Jan 11th: Only logically deleted, still visible in the MPRS History. Just not visible to MEM or EES Existing functionality on D0312 utilises cancellation flags not permanent deletion (raised as DI ID 27) |  | Implemented |  | Interim Release 1 |  | Reword to reflect the logical deletion. See MHHS-DIN-23 Reword this paragraph to: "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the removal of a MAP from a meters MAP history using a logical flag, mirroring the existing functionality associated with the use of the D0312." NB Main section header is incorrect - should be updated to section 19, rather than a duplicate of section 18. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Accepted but note there is another DIN already raised
MHHS-DIN-28 |  | N/A | 2023-01-30 | St Clements | 2709 | Madison Layton | Software Provider |  | Comment on Section 19.4 "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories. However, this would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." Sent on Jan 11th: This functionality already exists with the MPAN History Report showing who changed what when for all MPRS data items. Will be extended to include DIP transactional information (raised as DI ID 28) |  | Implemented |  | Interim Release 1 |  | Proposed Change Reword this paragraph to: "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories, noting that this is also available via the MPAN history report which will be updated with DIP transactional information and could also be used. Any use of EES would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-29 |  | N/A | 2023-01-30 | St Clements | 2710 | Madison Layton | Software Provider |  | There should be an additional rule for USP, if DI-830/DI-833 is populated, the MS/DS Proposed Effective From Date must equal the currently held EFD for the MS/DS appointment in MPRS (raised as DI 29) |  | Implemented | 2023-04-27 | Interim Release 1 |  | Added rule for USP scenario in IF-031 to check SP Effective from date. Proposing SCS have flexibility on error codes - requires industry Working Group. Picked up as part of Change of Service Provider review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-30 |  | N/A | 2023-01-30 | St Clements | 2711 | Madison Layton | Software Provider |  | The IF-035 does not provide the opportunity for MPRS to populate a lapsed reason. Will need to be able to provide a reason for a lapsed appointment, otherwise there'll be a higher volume of unecessary supplier enquries to DNOs which will require more resource and cost. (raised as DI 30) |  | Implemented |  | Interim Release 1 |  | Additional Data Item on IF-035 for a reason comment - what reasons would these be other than gone beyond the date? Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-31 |  | N/A | 2023-01-30 | St Clements | 2712 | Madison Layton | Software Provider |  | MHHS-BR-RS-027 "Registration Service must re-run validation, in line with the validation rules set out in the appropriate interface specification, for all Metering Service appointments that have been confirmed to re-process from the Prospective Appointment Queue, to ensure that the appointment is still valid" It is not clear if MPRS would send MSAppRejected or MSAppLapsed if the appointment fails validation after it's been queued? If this is not made clear in the deisgn then there is a risk that we build to use the wrong event code, or if the code should be MSAppRejected then risk that suppliers build a design where they can't process a MSAppRejected after receiving already an MSAppAccepted from MPRS (raised as DI 31) |  | Implemented |  | Interim Release 1 |  | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • Updated BRS003, requirement MHHS-BR-RS-032 and 66 to show that appointments will be lapsed (not rejected) • Remove Rejected from Step 225 of BP002/BPD002 Also on BP003 leading from step 215 should have the rejected removed. Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Corrections also to BPM002 & BPM003 Forward Migration and BPD002 Froward Migration | Data interface correction | MPAN Ownership |  | MHHSP-BP002-Change of Service - Metering service, BPD002,MHHSP-BRS003-Registration Service requirements MHHSP-DES138-Interface Catalogue, MHHSP-BP003, MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration), MHHS-DEL969-BPD002 (forward migration) | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-32 |  | N/A | 2023-01-30 | St Clements | 2713 | Madison Layton | Software Provider |  | The interface catalogue lists setting a removal date as an action that can be used with event code meterUpdate on IF-005, however in the interface catalogue, the block B039 does not list meterUpdate as a event code that can utilise this block. Need greater clarity on whether meterUpdate and meterHistoryUpdate should apply meter installations and meter removals or not. (raised as DI 33) |  | Implemented |  | Interim Release 1 |  | The definition of a [MeterUpdate] event code is: Allows currently appointed Metering Service to amend the details associated with a currently installed meter. Therefore the appointed Metering Service must be able to remove the meter as part of an update, this is an omission from the design and a small update to IF-005 The design principle that IF-005 works on is that: • BAU transactions (Install/Exchange/Remove) that are in the Metering Services Period of ownership are covered by the Install/Exchange/Remove events • Changes to currently installed metering can be made by the Appointed Metering Service using the Meter Update event. Note this therefore includes, where required, removing the currently installed meter where it is prior to the current period of ownership. • Changes to metering history ( ie not the currently installed meter ) can be made by the Appointed Metering Service using the Meter History Update Proposed changes: Added MeterUpdate as Optional to B039 block in IF-005 and added validation rule to ensure MeterUpdate is not used to remove meters in current period of ownership picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP-DELS229-IF-005 Use Case Guide | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-33 |  | T4-COM-1759 | 2023-01-30 | St Clements | 2719 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1759 on 15th Sept 2022: IF-005, REG1011 Install date must be > Creation date, should this REG1011 rule apply also to meter Exchange not just meter install SCS raised as a design blocker on 7th October 2022 Still no resolution, should this rule apply to meterHistoryUpdate at least as this allows for meter installations (raised as DI 34) |  | Implemented |  | Interim Release 1 |  | An exchange will not be a creation date, and the validation already in place ensures that future installation dates will all follow each other, which means this rule isn't required. ​This shouldn't be needed for exchanges, as its covered by REG1008 (install date >= remove date), as an exchange would replace an existing meter, which at first install would be validated against creation date. Moved REG1011 to cover all scenarios in IF005 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-34 |  | T4-COM-1774 | 2023-01-30 | St Clements | 2720 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1774 on 15th Sept 2022: IF-005, REG1011 "REG1009 - MAP ID [DI_055] is not valid for MAP Effective Date [DI-054] REG1011 - Install Date [DI-057] for MeterID [DI-056] is prior to MPAN Creation Date There are many meters in MPRS that pre-date the existence of the MAP and also MPRS install dates of 1980 etc. these will break a number of rules. should these be cleansed before MHHS start? If they are valid, then the rules need adjusting"l SCS raised as a design blocker on 7th October 2022 Still no resolution (raised as DI 35) |  | Closed |  |  |  | This could be a data cleanse requirement which is a consequential change/transition requirement, but for REG1009 - the MAP effective date should be the point at which the MAP took over the meter, and the exchange date should be after this (ie it should be after the date MHHS goes live). For Reg 1011 currently this is only valid on installs (and installs won't occur on legacy meters). If Reg 1011 is valid on exchanges, then the exchange date should also be after the MPAN creation date - if it isn't then the data should be cleansed. Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-35 |  | N/A | 2023-01-30 | St Clements | 2721 | Madison Layton | Software Provider |  | On the IF-005, should REG1028 (Install date cannot be null or blank) apply to meterinstall, meter exchange and meterupdate too? (raised as DI 36) |  | Implemented |  | Interim Release 1 |  | Requires amendment to interface validation - look at alternative validation Agree the rule should also apply for those events. Note we believe validation would fail for another reason. Eg REG1019 Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-36 |  | DI-37 | 2023-01-30 | St Clements | 2722 | Madison Layton | Software Provider | Re-alignment of rejection reasons to main block | In the summary of error codes box at the bottom of IF-005 tab the rejection reasons need re-aligning to the main block, e.g. REG1001 should read RMP stats must be Created or Operational, not just Operational As a general note across all interfaces, the rejection codes are referenced in numerous places and the respective descriptions are in many places not consistent for the same rejection code (raised as DI 37) |  | Closed |  |  |  | Will be revisited once SCS provide definative Error Code Texts | No Change |  |  |  | 2023-02-23 | 23/2/23 - Not discussed at meeting carry to next meeting
MHHS-DIN-37 |  | N/A | 2023-01-30 | St Clements | 2723 | Madison Layton | Software Provider |  | REG1015 (cannot be removed meter) is listed for meterHistoryUpdate in interface catalogue for IF-005. This should actually apply to meterUpdate not meterHistoryUpdate, REG1018 (cannot be installed meter) applies to metering history update (raised as DI 38) |  | Implemented |  | Interim Release 1 |  | Change accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-38 |  | N/A | 2023-01-30 | St Clements | 2724 | Madison Layton | Software Provider |  | In the interface catalogue, the IHD block B030 for IF-005 should also be optional for meterUpdate according to the IF-005 guide Section 16 Development Notes "The IHD segment, if provided as part of [MeterUpdate], relating to any currently installed meter should replace/update the IHD details currently held at the MPAN to which that Meter is associated." (raised as DI 39) |  | Implemented |  | Interim Release 1 |  | Small change to schema operation IHD information may be updated as part of the [MeterUpdate] event. The change is to add [MeterUpdate] event to block B030, so it now reads "B030 - MPAN IHD Information (Optional & may only be used with [MeterInstall],[MeterExchange],[MeterUpdate]) NB this also standardises the use of commas between event codes, rather than using the & symbol. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-39 |  | N/A | 2023-01-30 | St Clements | 2725 | Madison Layton | Software Provider |  | In interface catalogue for IF-005, there needs to be a rule that if event code MeterInstall is used, then modified meter ID cannot be populated (raised as DI 40) |  | Implemented |  | Interim Release 1 |  | Update agreed | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-40 |  |  | 2023-02-01 | SI Design |  |  |  |  | Not used - raised as duplicate in error |  | Closed
MHHS-DIN-41 |  | N/A | 2023-01-30 | St Clements | 2730 | Madison Layton | Software Provider |  | In interface catalogue IF-005: The REG1003 reads Metering Service [S0.SenderID] holds valid previous appointment then Meter Install Date [DI-57] should be < [REG.App End Date] + 10 The way it's curently written suggests MPRS should accept an IF-005 from the previous appoint, even if their ETD was greater than 10 days ago, provided the install date was less than their ETD + 10. E.g the previous MS could send IF-005 two years later with Install date of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then REG1002/REG1019 should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? (Raised as DI 41) |  | Implemented |  | Interim Release 1 |  | Having looked through IF-005 Dates should be within the appointment date, and current deign does give the ability to go outside this Change the validation rule for REG1003 on events [MeterExchange], [MeterInstall] and [MeterRemoval] to "If Metering Service [S0.SenderID] holds valid previous appointment then [system date] < [REG.App End Date] + 10" Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. Rule amended after review by SCS, to remove second "if" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-42 |  | N/A | 2023-01-30 | St Clements | 2784 | Madison Layton | Software Provider |  | In interface catalogue IF-005: Meter Update should apply validation REG1027 (current MS or prospective MS) not REG1012 (current MS only) to allow the prospective queued MS to update the Meter Type on a SEG change and therfore complete the market segment change and appointment. MHHS-BR-RS-132 . If the SEG prospective appointment was not allowed to update on meterUpdate event code then they would not be able to update the meter type to completed change of market segment, and would not meet the conditions needed to then be appointed in MPRS, their appointment would then lapse and market segment would remain invalid. (Raised as DI 42) |  | Closed |  |  |  | We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error... | No Change |  |  | None
MHHS-DIN-43 |  | N/A | 2023-01-30 | St Clements | 2732 | Madison Layton | Software Provider |  | In Interface Catalogue, on If-005, REG1002 and REG1019 are duplicates (install/removal dates should be within MS period of ownership). We can only use one of the rejection codes and descriptions, programme should choose which one to keep and remove the other. (Raised as DI 43) |  | Closed |  |  |  | These are testing slightly different things. The first test (REG1002) is checking that the Metering Service is an eligible party to send the request ie currently appointed OR was at the time of the install (to cover for previous Metering Services updating in the 10 day window). The second (REG1019) is checking that the Install Date is in the Metering Services period of ownership. So you could have that the Metering Service is currently appointed, but that they weren't at the install date. Eg Today is 2nd Feb, Meter installed on 27th Jan, Sending MS was appointed on 1st Feb REG1002 would pass as they are eligible as the currently appointed MS REG1019 would fail as they are not appointed at the time of the install Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-44 |  | N/A | 2023-01-30 | St Clements | 2733 | Madison Layton | Software Provider |  | Should the new rule for meter update in IF-005 also apply to meter history update? If no MAP entries provided, and revised Meter Install / Remove Dates result in no valid MAM History then reject with REGE1014 – MAP Eff From Sequence Error (Raised as DI 44) |  | Implemented |  | Interim Release 1 |  | Added REG1014 ( MAP History ) to IF-005 MeterHistoryUpdate event | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-45 |  | N/A | 2023-01-30 | St Clements | 2736 | Madison Layton | Software Provider |  | New rule for IF-005 Meter Update REG1017 could be misinterpreted as it currently reads incorrectly - need brackets to correct to how the AND and AND/OR conditions are to be applied If [DI-60] is not null AND Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null) Should read If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null)) (Raised as DI 45) |  | Implemented |  | Interim Release 1 |  | Clarification of existing design rule Change the validation rule for REG1017 to: "If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null))" picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-46 |  | N/A | 2023-01-30 | St Clements | 2737 | Madison Layton | Software Provider |  | on IF-005 for Meter Exchange and meter install the rule for REG1027 has been changed, but I'm not sure the wording implements the rule intended exactly? Currently it reads as The MS must be the currently appoint MS AND the install date must be > MS EFD AND the MS must not have proposed MS app with SEG scenario in the queue. If not then reject with REG1027 - Metering Service is not currently appointed and does not hold a Prospective SEG Appointment SHould the rule actually read The MS must be the current MS OR the MS must have a proposed MS App in the queue with SEG scenario And then the other part of the rule about install date > MS should be a separate rule (with REG1019 error code). (Raised as DI 46) |  | Implemented |  | Interim Release 1 |  | Sent to Mike F for validation - SI believe wording in current documentation is correct. Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. I would suggest the wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. DIN-46 – On review we agree, the date test should always be true if REG1019 is satisfied ( with minor clarification update ), so validation rules should be updated as below: Proposed changes: REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 |  | Not discussed at meeting carry to next meeting
MHHS-DIN-47 |  | N/A | 2023-01-30 | St Clements | 2738 | Madison Layton | Software Provider |  | REG1001 on IF-005 does not allow for meters to be removed after a disconnection. Instead should restrict for allow other event codes but allow Status Terminated for MeterRemoval. DES204 CCR-0556 Linked to DI-13 |  | Implemented |  | Interim Release 1 |  | Rule update required picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-48 |  | DI-048 | 2023-01-30 | St Clements | 2739 | Madison Layton | Software Provider | CSS failure to apply CoS to related secondary MPANs | Unhappy path scenario:- What happens if, for whatever reason, CSS fails to apply CoS to all the related secondary MPANs MPRS receives IF-031 on primary RMP to change agent, MPRS applies this to all seocndary MPANs too But if the CoS was not received from CSS for secondary MPANs that the secondary MPANs would still currently be held for the wrong supplier Would this cause any issues downstream? (Raised as DI 48) |  | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | CSS Defects issue. Agreed that Risk would be raised and all CSS related issued assessed at a later date | Other | MPAN Ownership | Related MPANs | [5 empty] | 2023-07-14
MHHS-DIN-49 |  | N/A | 2023-01-30 | St Clements | 2740 | Madison Layton | Software Provider |  | Unhappy path scenario:- If MPRS sends a IF-033 but never receives back a IF-034 then the rest of the process will not continue. The Supplier will never receive the IF-035 they are waiting for and the SP would never get appointed by MPRS. Is there a process in place to detect/resolve this scenario? (Raised as DI 49) |  | Closed |  |  |  | There is a requirement for the Supplier to monitor for any delayed responses and request an update if not received in expected timescales. Reviewed with SCS and agreed ticket can be closed | No Change |  |  | None
MHHS-DIN-50 |  | N/A | 2023-01-30 | St Clements | 2741 | Madison Layton | Software Provider |  | We need clear rules to define what a valid Consent granularity looks like. Current rules don’t mention any validation around EDI. (Raised as DI 50) |  | Implemented |  | Interim Release 1 |  | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-51 |  | DI-51 | 2023-01-30 | St Clements | 2747 | Madison Layton | Software Provider | St Clements Design Query - DI 51 | We have had some feedback from DNOs asking about how systems will recover from System Misalignment because of data errors or significant downtime? We have the D0204 (Supplier) and D0209 (Data Aggregator) Refresh functions today which are not being replaced with a DIP message equivalent. I am aware of the DIP Replay function, but this wouldn’t be of any help if there were data errors, as the DIP would just be replaying the incorrect data. The Source system would need to re-send the corrected data in an agreed format. I know there is a design principle to move away from bulk loads and refreshes of data, Faster Switching took a similar approach. However today, CSS leans heavily on the MPRS Refresh function to get itself back inline and there are REC CP’s being raised to add a Refresh function to CSS for all parties (first CP being R0067). DNO’s are keen to understand the MHHS Programme’s position on and if Refresh functionality should be built into MPRS for MHHS. |  | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | Refresh Functionality was rejected by the Working Groups so not in current design. Internal Design Discussion Required on if Programme position has changed on this given CSS Issue / EES Fed via DIP ?? | Other | Supporting Docs | Refresh Process? | [5 empty] | 2023-07-14
MHHS-DIN-52 |  | DI-52 | 2023-01-30 | St Clements | 2748 | Madison Layton | Software Provider |  | For IF-005, REG-1006 and REG1013, would it make sense to include the installation date of the MPAN already in the system in the rejection description too to help MS with triage? |  | Closed |  |  |  | DIN closed as instructed by St Clements. Old comments: Discussed with SCS potential for them to have flexibility on error messages. Industry agreement required. Participant Discussion Required | No Change |  |  |  | 2023-02-23 |  | Not discussed at meeting carry to next meeting
MHHS-DIN-53 |  | N/A | 2023-01-30 | St Clements | 2749 | Madison Layton | Software Provider |  | Requirement on LDSO requirements spreadsheet: MHHS-BR-LD-035 LDSO Maintain DUoS Tariff ID LDSO must set Duos Tariff ID on MPAN creation and maintain DUoS Tariff ID's in line with their Charging Method Statement. This should include updating the Duos Tariff ID, as required, following any updates to Domestic Premise Indicator, Connection Type and Energy Direction Note for MHHS, LLFC ID is being renamed as DUoS Tariff ID to make it clearer what this data item is used for. "BP010B Change of registration data" 250 However missing the respective requirement for Registration Services in the Registration Services Requirements spreadsheet |  | Closed |  |  |  | Looked through the Registration Services Requirements spreadsheet v4.6 and it looks like DUoS Tariff ID is there - MHHS-BR-RS-091.1, MHHS-BR-RS-121 and MHHS-BR-RS-122 | No Change |  |  | None
MHHS-DIN-54 |  | N/A | 2023-01-30 | St Clements | 2750 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1699 on 15th Sept 2022: On the IF-031 and IF-035 there are a number of "Proposed" Data items. Should MPRS load these and updated the stored data items. Or are these data items only for passing through to Supplier and Service? SCS raised as a design blocker on 7th October 2022 We have some clarity verbally on this but nothing has been formally documented in the design artefacts. This needs to be reflected somewhere in the requirements. |  | Implemented |  | Interim Release 1 |  | Added "Appoinments - Data" section in REG Notes to highlight what data becomes effective with the appointment. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-55 |  | T4-COM-1738 | 2023-01-30 | St Clements | 2751 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1738 on 15th Sept 2022: the DB02 flow updates multiple data items on the IF-018 in one event. Can multiple EventCode be included in one IF-018 or will MPRS need to generate an individual IF-018 for each EventCode? SCS received a blank response and raised as a design blocker on 7th October 2022 |  | Closed |  |  |  | Original response was that clarification was to be provided on 24th Oct - is this available? Which document? One at a time | No Change |  |  | None
MHHS-DIN-56 |  | T4-COM-1742 | 2023-01-30 | St Clements | 2752 | Madison Layton | Software Provider | Manual Correction to MHHS data items | Originally raised as T4-COM-1742 on 15th Sept 2022: BSCP604 currently allows LDSO and Suppliers to request manual corrections to Data Items held in MPRS. Will this type of Manual Correction be allowed in MHHS, if yes then this should be added to the business process to capture manual amendments and how these changes are reflected back to DIP users (IF-018 & IF-026, or a new Refresh Message?) SCS received a blank response and raised as a design blocker on 7th October 2022 Another exaple of this: If the MS/DS history is incorrect and cannot be amended via BAU, would the DNO be able to correct this via an exceptional error handling process? |  | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | Internal review required | Requirement correction | MPAN Ownership | CSS Defects | MHHS-BPD005 Data Processing, MHHS-BRS005 LDSO overview |  |  |  |  | 2023-07-14
MHHS-DIN-57 |  | T4-COM-1748 | 2023-01-30 | St Clements | 2756 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1748 on 15th Sept 2022: "Additional information field DI-120 is String200, where the existing DB03 allows a free text field of 2000 characters" SCS raised as a design blocker on 7th October 2022 This was corrected but then in v4.5 artefacts released there was a change back for DI-120 addition infromation field from string 2000 to string 200 in the interface catalogue data catalogue tab reintroducing the issue. For disconnection additional notes MPRS database holds 2000 characters so this field will need to be string 2000 in the IF interfaces (Raised as DI 57) |  | Closed |  |  |  | Change to the data catalogue included in the 4.7 baseline | No Change |  |  | None
MHHS-DIN-58 |  | T4-COM-1789 | 2023-01-30 | St Clements | 2757 | Madison Layton | Software Provider | Valid combinations of ISD data for MPRS validation development | Originally raised as T4-COM-1789 on 15th Sept 2022: "Valid combinations of data in ISD are critical to the MPRS validation development, we must have these defined and agreed before we can start development" SCS raised as a design blocker on 7th October 2022 |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Elexon is defining the valid combinations of data in the ISD. Parties need to define their own data. | Requirement correction | Supporting Docs | ISD | MHHSP-EM021 ISD Entity Map |  |  |  |  | 2023-07-14
MHHS-DIN-59 |  | T4-COM-1707 | 2023-01-30 | St Clements | 2758 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1707 on 15th Sept 2022: "The Smart DS for Export and Secondary MPANs can be different to the Import/Primary DS as the Customer can choose their own DS for Export and Primary (Smart only)" The IF-031 validation rules have been amended but they are still not corrrectly reflecting the rule. The heading above both rules REG1038 and REG1039 reads: "If event type = [MSApp] OR event type [DSApp] & MPAN Segment is not 'Smart'" This heading should ONLY apply to REG1038 for linked MPANs and should not apply to REG1039 concerning related MPANs It should also have brackets to clarify the logic otherwise it could be misinterpreted e.g. "If event type = [MSApp] OR (event type [DSApp] & MPAN Segment is not 'Smart')" |  | Implemented |  | Interim Release 1 |  | This seems a valid issue. REG 1039 on linked meters should be allowed for trad meters (eg economy 7) Proposed Change: The logic issue here is that REG1039 caters for related meters, which are applicable to trad as well as smart meters. Remove REG1039 from this validation Change the validation to: "If (event type = [MSApp] OR event type [DSApp]) & MPAN Segment is not 'Smart'" Updated heading above REG1038 and added heading above REG1039 to clarify the validation rule in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 | Not discussed at meeting carry to next meeting
MHHS-DIN-60 |  | T4-COM-1708 | 2023-01-30 | St Clements | 2759 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1708 on 15th Sept 2022: "The Service Appointment Date must be equal to the SSD or there will be a period with no Service" And T4-COM-1776 also on 15th September 2022 "REG1032 - Metering Service Eff From Date [DI-830] is not contiguous - Appointment must be from [Max[Reg.MPAN_SSD] ,[Reg.ExistingMSAppFrmDate]] for a COS, it can only equal the SSD otherwise there will be a gap" This has been applied incorrectly. In IF031 rules REG1032 now reads that the MS/DS prop EFD must be = Max(SSD, existing MS/DS EFD + 1) This would restrict the MS/DS to setting the new EFD to either SSD or the day after the last MS/DS appointment, and all other dates would be rejected. It should read >= not just =. All four refrences to REG1032 in the validation rules for IF-031 references the +1 day after EFD, but the rejection description in the right hand columns for 'scneario not SEG or CoS' section does not reference this + 1. This should be corrected to be consistent with the other rules. (Raised as DI 60) |  | Implemented |  | Interim Release 1 |  | Original response to 1708: New rules added to cover all scenarios Original response to 1776: Change to be incorporated into design artefact Updated REG 1032 validation in IF-031, original single rule, split into 2 separate rules picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-61 |  | T4-COM-1445 | 2023-01-30 | St Clements | 2760 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1445 on 15th Sept 2022: "There is no mechanism to update the Profile Class. We would assume that this would be updated by the Supplier (with business rules restricting when this should be set) and confirmed on the IF-026. Please can you confirm if this is the intention or if it will be updated through another route. If so, the EES would need to know which PUB would confirm the data item had been updated. " Whilst this is now included in the design the validation rules from D0205 have not been carried over, e.g. PC/SSC need to be a valid combination. ISD will need to contain the valid PC/SSC Combinations (previously MDD Entity 11) and the validation rules in the interface catalogue will need to reference this validation against the ISD valid combinations. (Raised as DI 61) |  | Implemented |  | Interim Release 1 |  | See also DIN-58, need to find out who is defining ISD validation Updated Interface notes in IF-025 to confirm that there is no Profile Class/ SSC combination checks | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-62 |  | DI-062 | 2023-01-30 | St Clements | 2761 | Madison Layton | Software Provider |  | In the business process diagram for Registration Updates MHHSP-BP010-Change of Registation Data - v4.5, the MPL update section, the C0300 has been changed to C0400 which is incorrect, C0400 is for MAP updates. Address updates are actually sent in the C0600. (Raised as DI 62) Change raised 30 March:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly. |  | Implemented |  | Interim Release 1 |  | Also in the BPD. MHHS-BR-RS-114 also confirms this should be C0300, this appears to be a straightforward typo. Amend label between Step 20 and Step 30 on BP010A to CSS0300, and update the corresponding BPD description on step 30 Update required:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly in BP010A, BPD010 and in MHHS-BR-RS-114. | Process model correction | Metering Changes | MPAN Updates | MHHSP-BP010-Change of Registration Data MHHSP-BPD010 MHHSP-BRS003
MHHS-DIN-63 |  | DI-063 | 2023-01-30 | St Clements | 2792 | Madison Layton | Software Provider |  | In the business process diag for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 (Raised as DI 63) |  | Closed |  |  |  | SCS have now confirmed that C0700 is the correct reference - no need to change documentation - agreed to close | No Change | MPAN Ownership | Disconnection | MHHSP-BP007-Disconnection MHHSP-BPD007
MHHS-DIN-64 |  | N/A | 2023-01-30 | St Clements | 2793 | Madison Layton | Software Provider |  | In business process diag for change of data service MHHSP-BP003-Change of Service- Data Service-v4.5 and MHHSP-BP002-Change of Service- Metering Service v3.5, this still makes reference to D0386 in the purple note boxes. This should now have changed to IF-019 (Raised as DI 64) |  | Implemented |  | Interim Release 1 |  | Update notes on BP002 and BP003 from D0386 to IF-019, and for BPM002 & BPM003 (forward migration) | Process model correction | MPAN Ownership | Change of DS | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-65 |  | N/A | 2023-01-30 | St Clements | 2794 | Madison Layton | Software Provider |  | The business process diagram for change to connection type/market segment has been amended to name only DB01, connection type is set on DB01 but it can then be changed on DB02 (Raised as DI 65) |  | Implemented |  | Interim Release 1 |  | Update label between step 220 and 225 from "DB-001" to "DB02" | Process model correction | Metering Changes | Market Segement | MHHSP-BP011-Change of Connection Type or Mkt Segment
MHHS-DIN-66 |  | N/A | 2023-01-30 | St Clements | 2795 | Madison Layton | Software Provider |  | In interface catalogue, on IF-031, shouldn't rule REG1036 (MDR app EFD must be after DS app EFD), be applicable to all scenarios including SEG? Currently under section for if not SEG (Raised as DI 66) |  | Implemented |  | Interim Release 1 |  | Updated validation rule for REG1036 and made applicable to all scenario's in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-67 |  | N/A | 2023-01-30 | St Clements | 2796 | Madison Layton | Software Provider |  | Currently no rule on IF-031 that the SP appointment has to be within the prospective suppliers registration period - just that it can't be past dated. This rule will need to be added. (Raised as DI 67) |  | Closed |  |  |  | Reviewed with SCS and agreed that this validation is covered by existing rules. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-68 |  | N/A | 2023-01-30 | St Clements | 2797 | Madison Layton | Software Provider |  | If-031 business rule missing If the Scenario is USP, the consent granularity must be the same as the existing consent granularity held within MPRS (Updates should be through IF-025 not through IF-031) (Raised as DI 68) |  | Implemented |  | Interim Release 1 |  | picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Updated Interface notes in IF-031 to clarify that Registration Service will ignore any differences in Domestic Premise Indicator/ Consent Granularity sent on IF-031 (USP scenario) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-69 |  | N/A | 2023-02-02 | ESG Global | 2653 | Luke Speakes | Software Provider |  | PUB-033 - Block 029 is conditionally mandatory for DCC Commissioned Meters, but includes DI-025 DCC Service Flag with valid values of A-Active, I-Installed Not Commissioned, N - Non Active. The title of the block, which should define whether it is mandatory or not, is not appropriate if a DCC meter has been installed and not commissioned, or is inactive. Propose following SI and SRO design discussion that title of block 029 is revised to conditionally mandatory for 'DCC Smart Meters' |  | Implemented |  | Interim Release 1 |  | Concludes this can be resolved by a minor wording change to the block title | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-02-23 |  | Not discussed at meeting carry to next meeting
MHHS-DIN-70 |  | N/A | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory | Addition of MDR validation rule | Elexon is required to maintain a valid list of Meter Data Retrievers in Industry Standing Data, to allow RegService to validate they're suitably qualified (DCC and SEC) MDRs are being appointed. |  | Implemented |  | Interim Release 3 | 2023-07-12 | Design Agreement is to utilise M16 for this purpose. ISD document updated with details and examples to this effect. | Other | Supporting Docs | ISD | MHHS-EDI-021-ISD_Entities | 2023-02-23 |  | Not discussed at meeting carry to next meeting |  | 2023-07-14
MHHS-DIN-71 |  | N/A | 2023-01-30 | St Clements | 2839 | Madison Layton | Software Provider |  | When would event code [MSDeAppUpdate] and [DSDeAppUpdate] be used for on an IF-037? (Raised as DI 69) |  | Closed |  |  |  | Reviewed with SCS and it is used to notify the incoming Service Providers when de-appointing and not origanally known. In case of Linked/Related MPANs individual MPANs move through the process. RS need to apply the logic for sending the updated IF-037 to all MPANs. Agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-72 |  | N/A | 2023-01-30 | St Clements | 2840 | Madison Layton | Software Provider |  | Block B018 on IF-034 and IF-035 should not be mandatory - it will only be provided for smart meters. This needs to be set to mandatory for SDS-MDRUpdate only, optional for DSAppSPResponse (Raised as DI 70) |  | Implemented |  | Interim Release 1 |  | Updated B018 block to be optional for non Smart on IF-034 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-73 |  | N/A | 2023-01-30 | St Clements | 2841 | Madison Layton | Software Provider |  | IF-026/IF-025, added new event code [SSCandProfileClass], but still kept in original [SSC] and [ProfileClass] event codes, should the original two have been removed? Particularly as the B032 group says it's madatory where event code is [SSCandProfileClass] and does not refer to [SSC] or [ProfileClass] individual event codes (Raised as DI 71) |  | Implemented |  | Interim Release 1 |  | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-74 |  | N/A | 2023-01-30 | St Clements | 2842 | Madison Layton | Software Provider |  | A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a new MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60 (Raised as DI 72) |  | Implemented |  | Interim Release 1 |  | This appears to be the reciprical change to MHHS-DIN-60 for the response interface Update description to "Check if MDR Eff Date = SSD OR on or after existing MDR Eff From + 1" Update rule to "If [DI-841] <>SSD OR <MDR Eff Date + 1" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-75 |  | N/A | 2023-01-30 | St Clements | 2843 | Madison Layton | Software Provider |  | On IF-035, overidden the description for Data Item 836 incorrectly with the description for Data Item 838 (Raised as DI 73) |  | Implemented |  | Interim Release 1 |  | Update the definition field based on the description in the data catalogue for DI-836 on IF-035 (Date From which Supplier would like Nominated MDR to take effect) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-76 |  | N/A | 2023-01-30 | St Clements | 2844 | Madison Layton | Software Provider |  | Data catalogue - changed the estimation reason code authoritative source to Registration Service, this data item is not received by, sent by or held by registration services and so the authoritative sourse cannot be Registration Service (Raised as DI 74) |  | Implemented |  | Interim Release 1 |  | The authoriative source has changed between v4.0 (from Data Service) to 4.7 (Registration Service) - have asked why the change was made, and what the authoritative source should actually be. Source updated to SDS/MDS | Data interface correction | Meter to Bank | Estimation | MHHSP-DES138-Interface Catalogue
MHHS-DIN-77 |  | N/A | 2023-01-30 | St Clements | 2845 | Madison Layton | Software Provider |  | Data catalogue - Added issue 99 items (CT Ratio, Phases etc) DI-170 - DI-180. Was agreed in work off meeting these items are not within the scope of MHHS, to introduce these would require a CR (Raised as DI 75) |  | Implemented |  | Interim Release 1 |  | these data items don't appear to be used in any interfaces so this could be a relatively simple change to remove 11 items from the data catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-78 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E0404 requirement is blank - row needs to be deleted |  | Closed |  |  |  | This update was already incorporated into version 5.0 closing it here | No Change | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-79 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E21114 typo - should be VAS Output Retention |  | Implemented |  | Interim Release 1 |  | change as per description | Technical corrrection | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-80 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHSP-DES138-Interface Catalogue v4.6 - DI-846 Issuing Data Service EZ Name should be scored through in IF/ PUB21 definition |  | Closed |  |  |  | Completed in V5.0, part can review change as part of Interim Release 2 | No Change | Meter to Bank | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-81 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier | Correction of step in BP020 | MHHSP - BP020 - Volume Allocation Service (ECS) v4.6 - Step 75 to Step 80 references report “REP-00” - needs correcting |  | Implemented |  | Interim Release 2 | 2023-06-23 | BP020 step 75 to step 80 process flow REP list correction BPD020 step 75 & step 80 detail list of REP's correction | Process Model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions |  |  |  |  | 2023-06-16
MHHS-DIN-82 |  | N/A | 2023-02-09 | SI Design | 2716 | Rob Short | SI Design | Missing listed number of reports in BPD002 | Related to DIN-81 - BPD002 lists number of reports at step 75, BP002 does not reflect this list, missing PO275, PO214 and PO213 |  | Implemented |  | Interim Release 2 | 2023-06-23 | This relates to BP020 (not BP002), similar to DIN81, reconcile REP list correction on BP020 at step 75 and 80 and reconcile with BPD020 list of REPs | Process model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions |  |  |  |  | 2023-06-16
MHHS-DIN-83 |  | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | BP011 missing PUB-044 flow | A discrepancy with the Interface Catalogue - IF_LIST states MHHSP-IF-044 is sent to Central Settlements, DS, MS, Supplier, LDSO. IF-044 tab states it is sent to Supplier, MDS, LDSO In BP011 the PUB-044 is not sent to DS only Supplier, Settlements and EES |  | Implemented |  | Interim Release 2 | 2023-06-23 | Add Manage change of segment in LDSO lane on business process BP011C with a PUB-044 flow from step 570 Add new step to BPD011 Interface catalogue is already updated | Process Model correction | Metering Changes | Interface Catalogue | MHHSP-BP011 Change of ConType andor Mkt Segment MHHSP-BPD011 MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-84 |  | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | DES-138 IF List Tab Consistency | IF_LIST states MHHSP-IF-020 is sent to Supplier onlyIF-020 states it is sent to Supplier, Data Service, Metering Service, LDSOIn BP010, the PUB-020 is sent to Central Settlements, CSS, EES, Supplier, Data Service, Metering Service, LDSO.This one looks like its just the Interface Catalogue that needs updating. IF-020 Updated to refect new agreed Routing |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated parties receiving PUB-020 in the IF_LIST, updated PUB-020 routing to include MDS for Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-85 |  |  | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory |  | Elexon see DIP qualification for new users being part of market entry post-programme, but want to understand how MHHSP will operate qualification during the programme. This is likely to cover the majority of participants. Discussions with SRO colleagues indicate they are assuming this is a process for the Enduring Service Operator to define. Challenge applies to non-BSC DIP participants (e.g. adaptor providers), and considerations under Issue Group 101. SI design has spoken to at least 4 participants who are operating in this space and seeking to understand how they can engage with SIT and other programme activities as a DIP connection provider (E2E Architecture - 3.3.2) |  | Closed |  |  |  | To be handled as part of the Placing Reliance document | No Change | Qualification | Qualification | New Process - DIP Qualification for New Users
MHHS-DIN-86 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Invalid Market Segment BP011C requires SMRS to notify the Supplier of an invalid market segment. RegService requirement RS0124 states that SMRS must derive a value for Market Segment based on Connection Type and Meter Type following a Change of Metering, Change of Connection Type (Change of Unmetered Indicator) or Change of Related MPAN relationships. Given that SMRS determines segment as above, when would an invalid market segment occur, giving rise to the processes from step 560 in BP011C? Further, upon receipt of a PUB-045 Market Segment Invalid Advisory Notification, what are the next steps for a Supplier to address the issue? There are no provisions in the IF-025 for Suppliers to update Market Segment. |  | Closed |  |  |  | Part of ongoing discussions with Code Drafting team 20/4//23 Code Drafting believe an update needs to be made to the design to update Market Segment via IF-25. This could occur when a Supplier is trying to arrange a change of segment but one of the activities has not completed on time eg the new metering has not been notified. When Registration Service tries to evaluate the segment it may not be compatible. Notification would then go to Supplier to prompt them to chase the required update, in this example chasing the Metering Service to provide the new metering details. Another example is if the LDSO has not notified a change of connection type. The Supplier may also need to send a further SEG appointment if the original has lapsed. | No Change | Metering Changes | Change of Connection Type and/or Market Segment | MHHSP-BP011, MHHSP-BPD011
MHHS-DIN-87 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory | Process clarification for meter removal and de-energisation on same job | Energisation Process Clarification BP009 states that change of energisation status at the same time as meter works means that BP008 will be followed - what is the process when a meter removal and de-energisation are carried out in the same job? Are both D0139 (de-energise) and D0142 (remove meter) and relevant DIP interfaces required. At the moment MEMs only have to send flows relating to meter removal |  | Implemented |  | Interim Release 3 | 2023-07-12 | New Purple Boxes added in BP009 and BP008 to make it clear that Remove/DeEn could still be requested and carried out but MS would need to send two interfaces. Also that DeEn did not need to be notified if meter works completed within same day (ie same rules as today) | Process model correction | Metering Changes | Change of Metering | MHHSP-BP009 MHHSP-BP008 |  |  |  |  | 2023-07-14
MHHS-DIN-88 |  |  | 2023-02-09 | RECCo |  | Sarah Jones | Regulatory | Update to Incumbent MS provider for Lapsed Appointments | Update to Incumbent MS provider for Lapsed Appointments Currently BP002 only addresses the positive confirmation of de-appointment from RegService (PUB-037 - step 140/231), but if there is no secured active, there is no subsequent notification to the incumbent. The prospective MS receives a PUB-035 at step 225. How should the incumbent MS determine when the de-appointment has lapsed? |  | Closed |  |  |  | Part of ongoing discussions with Code Drafting team. It is not expected that the incumbant share the MTD via the IF-035 as early sight. IF-37 is the deappoint code they need to reflect . The Metering Service is appointed until they get de-appointed using a PUB-037. They are only receiving the PUB-035 as notification of who to send MTDs to, it is not intended as a notification of de-appointment. Incumbent Metering Service is a term used to refer to the MS appointed at the point another new SP Appointment is accepted (MS or DS), it shall be the Incumbent Metering Service's responsibility to share MTDs (ADV/Trad) to the incoming party. No change recommend CLOSE | [8 empty] | 2023-07-14
MHHS-DIN-89 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Customer Details on De-Appointment The MHHS design currently allows for customer data to be deleted or obfuscated by MS on de-appointment. Has obfuscation been confirmed as acceptable under GDPR? |  | Closed |  |  |  | Programme has called out the need for data management wrt GDPR. It is for each participant to determine the action required based on their own GDPR Guidelines and policies. |  | All Areas | [6 empty] | 2023-07-14
MHHS-DIN-90 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | MS Appointment for Associated Export Metering Points How will an initial MEM be appointed for a new export MPAN, created post MHHS go live? |  | Closed |  |  |  | Part of ongoing discussions with Code Drafting team - this is not a Design Issue. Design will operate as described below: The daily process monitoring (BP011C) would pick up any [new] Linked Export MPANs and ensure that the same Metering Service is appointed as the Import MPAN. If the Export MPAN is not linked, then the BAU appointment process can be followed. |  | Metering Changes | Change of Connection Type / Market Segment | MHHSP-BP011, MHHSP-BPD011 |  |  |  |  | 2023-07-14
MHHS-DIN-91 |  | N/A | 2023-02-10 | AWS | 2858 | Duncan Parsons | Software Provider |  | Document MHHS-E2E001 section 3.6 Actor Workflows Summary - Typo in the MSA Outbound. States IF-04, this should be IF-041 |  | Implemented |  | Interim Release 1 |  | Reference Corrected | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-92 |  |  | 2023-02-14 | RECCo | 2903, 2805, 2911 | Sarah Jones | Regulatory |  | Customer Direct Contract Flag (D053) Multiple tickets - RECCo, ESG and National Grid - all highlighting the same problem. The 4.7 artefacts do not consistently reflect the agreed position that the Customer Direct Contract flag can only be set by the incumbent Metering Service provider. The validation rules on the IF-038 should be updated The requirements for MS (013) and DS (34) in the respective BRS artefacts should be aligned |  | Implemented |  | Interim Release 1 |  | Added validation rule REG1075 to IF-038 in the interface catalogue Updated requirements in MS-013 and DS-034 in BRS to reflect the agreed position for D053 1/3 - ticket #3035 - SCS supportive of this change, need more detail. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue, BRS001, BRS002 | 2023-02-23 |  | Accepted but split these into two DINs one of the updates to the BRS and deal with as a minor chnge, the other as a major for the Interface Specification change
MHHS-DIN-93 |  | N/A | 2023-02-14 | Power Data Associates |  | Tom | Data Service Provider | Work off Plan D-034D updates for exceptions to Unmetered Supplies | Work off Plan D-034D updates for exceptions to Unmetered Supplies |  | Implemented |  | Interim Release 2 | 2023-06-23 | 1. Section 2.3 of MHHSP-METH004-UMSDS- EM Functions will be updated to make explicit that the following data items are not required by the UMSDS and as such will be ignored. • Consent Granularity (T4-COM-1857) • Domestic/Non-domestic Indicator (T4-COM-1830/1850) • Distributer Id (T4-COM-1826/1842/1845/1858/1859/1864/1865/1871/1875) • DUoS (T4-COM-1856) • LLF Data (T4-COM-1856) • Domestic Premise Indicator (T4-COM-1830/1850) • Metered Indicator- (D-045) 2. MHHSP-METH001- SDS Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 3. MHHSP-METH002- ADS- Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 4. MHHSP-METH009- UMSO Method Statement should be updated to make explicit that the following data items are not required by the UMSO and should be ignored (list to be reviewed and validated). • Consent Granularity • Domestic/Non-domestic Indicator • Distributor Id • DUoS • LLF Data • Domestic Premise Indicator • Metered Indicator | Method statement correction | Supporting Docs |  | MHHSP-METH004-UMSDS MHHSP-METH001- SDS MHHSP-METH002- ADS MHHSP-METH009 - UMSO | 2023-02-23 | 23/2/23 - Accepted |  |  | 2023-06-16
MHHS-DIN-94 |  |  | 2023-02-16 | ESG | 2777 | Patricia | Software Provider | IF-005 rejections | The IF_009 has 2 event codes: [MPANDisconnection] & [CSSDeRegistration]. [CSSDeRegistration] is listed as having Supplier as Secondary routing however on BP007 there is only reference to the supplier receiving the [MPANDisconnection] flavour of the flow. Please can you clarify which artefact is accurate. MHHSP – BPD009 step 145 states Where the Registration Service has rejected the metering update the DIP will publish the rejection to metering services. Supplier have the option to subscribe to this also. Your response was:- Our reading of this is that regservice will reject the PUB-006 back to sender if the IF-005 fails those rules. So just back to sender, not always meter service or supplier Therefore, does the BPD009 step 145 need to be updated to reflect that as the IF005 can only be generated by Metering Service Smart (MSS) & Metering Service Advanced (MSA) not the Supplier |  | Implemented |  | Interim Release 3 | 2023-07-12 | Question 1. Supplier will receive both events as outlined in BP007 (See DIN 294) Question 2. A decision was made at the DRG on 29th June to leave the messaging in BPD009 step 145 and instead update the business process model in BPD009 to give Supplier's the option to subscribe to rejections. | Process Model correction | Metering Changes | Change of Metering | MHHSP-BP009 – Change of Metering (Install / Remove / Exchange) , MHHSP-BPD009 MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-95 |  |  | 2023-02-20 | SI Design | NA | Simon Harrison | Programme |  | Typo in the Note box about Auto Alignment of Related/Linked MPANs on the BP002 and BP003 process maps. Change 'Regisatration' to 'Registration' |  | Implemented |  | Interim Release 1 |  | Update BP002 (& BP003) call out box, also for BPM002 and BPM003 (Forward Migration) | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-96 |  |  | 2023-02-21 | SI Design | 2973 | Arif Jagot | Programme |  | Test-078 - SUPPI -Primary - Means SUPI? |  | Implemented |  | Interim Release 1 |  | Update Interface Catalogue | Data interface correction | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-97 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.4 | Typo in MHHS-METH001-5.4c "and less than 90 days months different from the UTC Date" - propose removal of months |  | Implemented |  | Interim Release 2 | 2023-06-23 | Update Method Statement i.e This needs to be 90 days not 90 months the artefact needs to be updated | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-06-16
MHHS-DIN-98 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.5 | Typo in MHHS-METH001 - 5.5 SDS shall use the most recent data a based on the event that triggered the |  | Implemented |  | Interim Release 2 | 2023-06-23 | Typo error on clause 5.5 within MHHSP-METH001-SDS Validation Estimation v5.0 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-06-16
MHHS-DIN-99 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Working days correction | Clarify that Step 105 in the CoS Transfer read process is Working Days. Currently states 5 days |  | Implemented |  | Interim Release 2 | 2023-06-23 | Checked with SRO - 5 Working days for Step 105 in process, BPD003C, BR-DS-024.1 and BR-DS-024.2 | Requirement correction | MPAN Ownership | Data Services | MHHSP-BRS001 - SDS Requirements MHHSP-BP003C - Transfer of Reads MHHSP-BPD003C - Transfer of Reads |  |  |  |  | 2023-06-16
MHHS-DIN-100 |  |  | 2023-02-21 | RECCo | NA | Sarah Jones | Regulatory | BP002 to include LDSO as recipient | Step 180 in BP002 and BPD002 does not include LDSO as recipient of traditional meter details as per the wording of the step or the BRS (BR-MS-024) (Code Drafting Log Reference CDD-29) |  | Implemented |  | Interim Release 2 | 2023-06-23 | Update BP & BPD to align with BRS and add LDSO as recipient of MTDs Updates to BP & BPD002 Forward migration for consistency | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Metering Service MHHSP-BPD002 Forward Migration BP002 and BPD002 |  |  |  |  | 2023-06-16
MHHS-DIN-101 |  | DI-120 | 2023-02-22 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. (Raised as DI 120) |  | Closed |  |  |  | Included within CSS validation rule update. DUPLICATE See DIN-172 | No Change | MPAN Ownership |  | MHHS-DES138-Interface Catalogue
MHHS-DIN-102 |  |  | 2023-02-22 | St Clements | 2886 | Madison Layton | Software Provider |  | SCS raised the following under MHHS-DIN-7 "MPRS will reject any PUB-031 inlcuding those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist"" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8)" They have followed up with: Just found the change that corresponds to this one in v4.7 interface catalogue – REG0005 in IF-031. Could this also be added to IF-034 so that we can apply the same validation on MDR updates? |  | Closed |  |  |  | Proposed Change: Add validation "CSS Registration Request ID [DI-849] is valid for Registration Service", with error REG0005 - "CSS Registration Request ID [DI-849] is invalid or unknown" This mirrors a change made in v4.7 to IF-031, agreed as part of the DAG baseline of v4.7 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-103 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory |  | Confirm that D0381 will continue to be used for updates to MPL address. BP010 & BPD010 currently allow emails, SDEP and other agreed forms can be used by Supplier or UMSO to update this - propose that these artefacts are amended to reflect that the D0381 is to be retained (Code Drafting Log Reference CDD-22) |  | Implemented |  | Interim Release 1 |  | Amend Steps 10, 21, 22 to explicitly use the D0381 rather than current wording | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-104 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Impact of MHHS on SoLR arrangements | Impact of MHHS on SoLR arrangements - possibly needs an Issue Resolution Group discussion to undertake evaluation & impact assessment (Code Drafting Log Reference CDD-23) |  | Closed |  |  |  | Extensive discussions have been held with Elexon (DIP Manager) to ensure that there is flexibility within the DIP Design to accomdate varied SoLR scenarios. These involve the existing process(s) around change of BMUnits and the ability to transfer ownership of DIP Market Participants. As the solr process does not involve any mass movement / reassignment of MP Identifiers at the MPAN level the core MHHS design is not impacted by Solr per se. |  | All Areas | [6 empty] | 2023-07-14
MHHS-DIN-105 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Related MPAN Business Rules | 1) IF-019 suggests RMP status can be Created or Operational - proposed this can only be Operational for subsidiary MPAN 2) Add validation rule to IF-019 requiring related MPANs to have consistent classification as domestic or non-domestic (reflecting the existing requirements) 3) Clarify what Registration Services should do when MPANs are related/linked and have different MS/MEM providers - is the IF-019 rejected or the MEM for the secondary MEM auto-deappointed? 4) What happens if the IF-019 fails validation by Reg Service at Step 330 in BP010? Design provides no guidance |  | Implemented |  | Interim Release 2 | 2023-06-23 | 1. Removed reference to Created in the REG1001 validation rule for IF-019 2. We understand there is no existing validation within MPRS and this is not being amended as a result of MHHS implementation. This would require a wider industry change impacting CSS as Domestic Premise Indicator is managed independently of Related MPANs. 3. It would not be rejected, auto-alignment would pick up the discrepancy at the next daily run and de-appoint the export MS and appoint the import MS. 4. As with other rejected flows, the sending party should investigate the error and re-submit as appropriate. | Data interface correction | MPAN Ownership | Change of Registration Data | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-106 |  |  | 2023-02-23 | SI Design | 2955 | Kate Goodman | Testing | IF Routing | Inconsistency in DES138 for UMSO Routing 00-Introduction logs UMSO as the single routing option for Unmetered Service provision, as there can only be one UMSO related to an MPAN PUB-008 provides UMSC, UMSP and UMSI as options for secondary routing This inconsitency needs to be corrected |  | Implemented |  | Interim Release 2 | 2023-06-23 | IF-008 - Secondary routing rules updated following review with Avanade (see DIN268) |  | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-107 |  |  | 2023-02-24 | SI Design |  | Simon Harrison | Progamme | Update to definition of DI-301 LLF ID in the ESC Reporting Data Catalogue | Definition of DI-301 in the ECS Reporting Data Catalogue needs to be updated as follows 'The Unique Identifier of a set of Line Loss Factors' |  | Implemented |  | Interim Release 3 | 2023-07-12 | Update to be made in the ECS Internal & External Reports - Data Catalogue tab against DI-301 LLF ID it should read as 'The Unique Identifier of a set of Line Loss Factors' | Data interface correction | Supporting Docs | Reporting Catalogue | MHHSP - ERI011A - ECS Reports - Internal v5.2 MHHSP - ERI011B - ECS Reports - Enternal |  |  |  |  | 2023-07-14
MHHS-DIN-108 |  |  | 2023-02-27 | SI Design | 2966 | Kate Goodman | Testing | IF Routing | Ref:MHHSP-DES138-Interface Catalogue v4.7, IF-038, PUB-020, PUB-039. Document says that UM is relevant to these messages but UM thinks it is not relevant. Please clarify what the situation is. Raised in review of MHHSP-872 by Power Data. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Covered by Secondary routing updates (See DIN268), changes to IF-020 and IF-039 routing. No changes were required to IF-038. The design allows for Customer Direct flags to be set for any Data Service/ Metering Service (ie Including unmetered). |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-109 |  |  | 2023-02-27 | SI Design |  | Simon Harrison | Programme |  | Call out box in BP002/BP003 on Linked/Related MPANs needs to be updated as it includes reference to email/SDEP rather IF-019 as shown in BP010 |  | Closed |  |  |  | Confirmed - the call out box on BP002/003 needs to be updated Duplicate of DIN-64 | No Change | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service
MHHS-DIN-110 |  |  | 2023-02-27 | SI Design | 2983 | Kate Goodman | Testing |  | MHHSP-BP005-Data Processing-v4.6, Step 50-160 UMSDS is referencing Submit Required UTC period level consumption data (Step 50) with a arrow going to Receive UTC period level consumption data (Step 160) but no reference of IF-021 on the connection between both - reference should be added? |  | Implemented |  | Interim Release 1 |  | On Process map requires arrow to be labelled as IF-021 from step 50 to step 160 | Process model correction | Meter to Bank | Data Processing | MHHSP-BP005-Data Processing
MHHS-DIN-111 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Originally raised as T4-COM-1691 on 15th Sept 2022: "MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days " Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5 (Raised as DI-76) |  | Implemented |  | Interim Release 1 |  | Updated to 2 working days | Requirement correction | MPAN Ownership |  | MHHS-BRS003-Registration Service requirements
MHHS-DIN-112 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54 (Raised as DI-77) |  | Implemented |  | Interim Release 1 |  | Added note to clarify | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-113 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? (Raised as DI-78) |  | Closed |  |  |  | Agreed duplicate of DIN-29 and can clsoe | No Change
MHHS-DIN-114 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | EES does not appear to have been added to the routing rules tables on the interface tabs(Raised as DI-79) |  | Closed |  |  |  | Already present in v5 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-115 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On IF-050, this includes linked MPANs in it, but I don’t think these would ever be populated as you cannot link MPAN at MPAN creation. So EES would only ever get Linkage updates on the IF-20 Is there any value of having this therefore in IF-050?(Raised as DI-80) |  | Implemented |  | Interim Release 1 |  | Removed Linked MPANs and Related MPANs from IF-050 and added explanatory note | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-116 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | For IF-025, block B032 it states it is "MPAN Legacy Info (Mandatory where event is [SSCandProfileClass], and for Traditional Meters / Optional for other Meters)" It should just read mandtory for event code [SSCandProfileClass] and nothing else, it should not be optional for any of the other event codes(Raised as DI-81) |  | Implemented |  | Interim Release 1 |  | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-117 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?(Raised as DI-82) |  | Closed |  |  |  | Discussed with SCS and confirmed it is a limitation of swagger output but should be array of MPAN followed by array of meters followed by array of MAPs repeated per MPAN. Awaiting confirmation can close | No Change | Metering Changes | IF-005 JSON | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-118 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | In relation to the Sender Unique Reference, which is constructed as: S-<Interface>-<Participant Id>-<Role Id>-<Date>-<Sequence> (hex) I would like to comment as follows: • Why is the Unique Reference simply constructed using elements that are already contained in the message as distinct values? This just means the sender has to construct it and the receiver de-construct it? • Is the sequence number expected to be reset each day ? • It would be much easier and more logical for the Sequence to be a distinct item in the message? • Why is the sequence specified as hex? • Even given the expected large number of messages, and based on it being a number(13) (defined as Sting), a standard sequence number per Participant and Role would provide 9,999,999,999,999. If this is still seen as a limitation then it could simply be built from the date, e.g. 202301190000000001, giving a provision for up to 9,999,999,999 messages PER DAY from the same Participant / Role combination, which still enables a read every 30 minutes from every MPAN(Raised as DI-83) |  | Closed |  |  |  | This is to send a unique reference and is used for auditing purposes. Please note the length of the Sender Unique Reference has been increased at the request of Avanade in 5.1.1. Examples updated |  | MPAN Ownership
MHHS-DIN-119 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | in swagger hub under IF-002 B907 list the B036 block, this is missing numberOfDigitsCumulativeRegister data item(Raised as DI-84) |  | Implemented |  | Interim Release 1 |  | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue. Swagger will be updated | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-120 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Inconsistency in naming of data item DI-091 In swagger hub: Number-Of-Digits-Cumulative-Register In interface catalogue IF tabs (E.g. IF-002) : Number of Displayed Register Digits In interface catalogue data catalogue tab: Number Of Displayed Register Digits (Cumulative Register)(Raised as DI-85) |  | Implemented |  | Interim Release 1 |  | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue and updated YAML accordingly | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-121 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0093 comment raised on 12/01/2023 " D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: "It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42 (Raised as DI-86) |  | Implemented |  | Interim Release 1 |  | Agreed to provide SEG scenario's in IF-005 Use Case guide. currently under review |  | Metering Changes | Change of Segment | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-122 |  | DI-87 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0084 comment raised on 12/01/2023 following the introduction of IF-019 and respective changes in the latest set of released artefacts MHHSP-BP010-Change of Registration Data -v4.5 "Shows Supplier Mastering Import Export Linkage. BSC CP1558 introduced changes to MPRS for the LDSO to manage this via the DB05. IF-019 should go to LDSO who should then produce a DB05 into MPRS." The process diagrams and requirement spreadsheets have been amended to show MPRS loading DB05 as a IF-019 response. DB05 is not a IF-019 response, it is a request from DNO/iDNO to create, amend or remove a import/export linkage. It does not currently have any capacity to include a IF-019 rejection response to trigger a IF-020 rejection response to DIP. (Raised as DI-87) |  | Implemented |  | Interim Release 1 |  | SCS reviewing preferred option with LDSO's The following changes would be required to the LDSO overview requirements: MHHS-BR-LD-043.3 LDSO Send Import/Export relationship update LDSO must send accepted Import/Export relationship updates to the Registration Service via the appropriate interface DB05 file or other agreed mechanism BP010B Change of registration data 900 MHHS-BR-LD-043.4 LDSO Send Import/Export relationship rejection LDSO must publish rejected Import/Export relationship updates on the Data Integration Platform using the appropriate interface MHHS-IF-020 to Supplier BP010B Change of registration data 900 On BP-010 for Linked Import/Export MPANs the following would be required: 1. Need to add rejected leg from step 900 to DIP 2. Need to add PUB-020 going from the DIP to the Supplier The BPD-010 will need updating accordingly. | Process Model correction | MPAN Ownership |  | MHHSP-BP010-Change of Registration Data MHHSP-BPD010, MHHSP-BRS005, Traceability Matrix
MHHS-DIN-123 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0083 comment raised on 12/01/2023 following the introduction of a new business rule on MPRS in the latest set of released artefacts MHHS-BR-RS-078 "MPRS cannot control how messages are sequenced at CSS and DSP. IF MPRS waits until the DSP responds before sending the Appointment message this could take hours (as this is a batch process) this will result in a delay in the appointment of the MDR. Sequencing requirements should be placed on CSS & DSP to ensure the correct MDR is appointed based on Effective dates provided from MPRS. However, they may not be necessary due to the way this interface works: The C0200 interface uses the PUT Method, which will replace the data held at CSS. Explicit ending of an Appointment is only required for a future dated appointment, this will be sent as one message with the Old and New MDR appointments. For Same Day or Retrospective the new MDR Appointment will Replace the currently set value. This implicitly ends the previous MDR Appointment. On a CoS, the MDR is linked to a Registration not a Metering Point. The previous MDR will end naturally when the Previous Registration becomes securedInactive. An explicit message to end the MDR appointment on the Previous Registration is not required . MPRS will only send two separate updates to CSS when there is a gap in MDR (SDS) appointments. For Example a change of segment to Advanced and then back to Smart. This would need to happen over a short period to generate two messages that could go out of sequence" The MHHS design team rejected with comment "The MHHS design is based upon what was agreed as part of the R044 consultation. This scenario does not reflect our understanding of how the CSS/DCC/DSP interface will work as set out under R044. " This is how C0200 currently works today and the interface is unchanged in R0044. This will put a signfiicant requirement on MPRS that will reduce time available time for other core MHHS development activities with no benefit to industry.(Raised as DI-87) |  | Closed |  |  |  | No Change - updated in v5.0 | No Change | MPAN Ownership
MHHS-DIN-124 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0089 comment raised on 12/01/2023 "D-021 was meant to give more detail on how L1-L4 validation should be used and provide more error codes for use. This has not been done as far as I can see Blocking resolution to this T4-COM-1749, T4-COM-1769 and T4-COM-1768" Comment was closed as clarified however none of these items have been resolved and we have no dates as to when they will be. comments blocked that were raised initially on 15/09/22 Comment T4-COM-1749: "The Registration Service, as part of its L3/L4 validation should ensure that there is consistency between the data content of the IF-033 issued to the Service Provider and the [returned] content in IF-034 - if this isn't so then message should be returned to Service Provider using ""MSGStatus Message"" mechanism." Does MPRS only need to validate consistency in the data it loads on the IF-033, not the data that is not loaded" Comment T4-COM-1769: "We need validation rules to be defined for this flow, Does not match IF-031, content of the PUB-034 does not match the IF-031. No Proposed Appointment Found, PUB-034, does not link to any Pending IF031s. Define Validation Rules for PUB-034 The 034 content must match the original if-031 content the 034 must have a corresponding IF031 the 034 has already been received for the IF-031 Generic Standard Validation, MPAN exists valid in ISD ETC" Comment T4-COM-2768: "We need some generic codes for standard validation rules such as: Service/Supplier is valid in ISD MPAN exists in MPRS MPAN is not Disconnected Service/Supplier is Valid in MDD (so CSS doesn’t reject updates)" (Raised as DI-89) |  | Implemented |  | Interim Release 1 |  | Added RMP status check to IF-034 and refined validation rule notes regarding different values received from IF-033 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-125 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | IF Routing | WOA-0091 comment raised on 12/01/23 D-030 "how routing will work in the DIP has not been updated this information is required for our development" MHHS Design Team has closed as clarified however there is still uncertainty around the DIP routing, and there are not dates provided for when the detailed DIP design will be released. This will clock certain elements of development (Raised as DI-90) |  | Implemented |  | Interim Release 2 | 2023-06-23 | Secondary routing rules updated following review with Avanade (see DIN268) |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-126 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0092 comment raised on 12/01/23 following more infromation around D-022 being clarified "D-022 Following the work off item being agreed on what is required for an MPAN to be traded - it has now been possible to fully assess the optionality of data items in the interfaces Data items still mandatory in interfaces that must be changed to optional: Annual Consumption (IF-001) Incumbent Service Providers (IF-002, IF-033) Incoming MS/DS (IF-037) These are not required at creation, nor at traded, and therefore could be non existent in MPRS when MPRS generates this outgoing IF messages Blocking resolution of T4-COM-1727 and T4-COM-1735" Closed as clarified however none of the issues listed have been resolved Annual consumption still reads madatory on a CoS for IF-001, the issue is MPRS may not have this data item. The item is not required to reach a status of traded, therefore CSS will accept a CoS on this MPAN without annual consumption being populated, and then MPRS will not be able to provide this data item on the IF-001 that results from the CoS. This must be changed to optional OR the definition on what is needed to be traded should be updated to include annual consumption. Incumbent Service Providers is still mandatory on IF-002 for CoS Again as MS is not required to be traded, CSS will accept a CoS request with or without a current MS, and so MPRS will not be able to provide an incumbent MS in these cases. It must be changed to optional or the definition of what is needed to be traded should include MS. Incoming MS/DS is still mandatory on IF-037, there are numerous reasons an appointment may be lapsed, the only change that would gaurantee a new incoming SP that MPRS could send on this flow is a change or SP (CSERV) scenario. For CoS the supplier may not have sent in new appointments, for DEREG there will be no new appoitnments, for SEG the market segment may have changed but the supplier may not have sent in new appointments, same for change of connection type, and for IMPEXP and RELATED the parent MPAN might not have MS/DS appointed at all so there would be no new appointments for MPRS to populate on this flow. This must be changed to madatory ONLY on CSERV (Raised as DI-91) |  | Implemented |  | Interim Release 1 |  | Discussed with SCS. Covered by clarification on nullable and interface notes- All these issues are resolved by the Mandatory Nullable Solution. Confirmed Annual Consumption block will only be provided where available in Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-127 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 "DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least "Registered", if no DS is appointed then there is already an appropriate Event Code" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone (Raised as DI-92) |  | Closed |  |  |  | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-128 |  | DI-93 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0095 comment on 12/01/23 "D-009 This is blocking closure of T4-COM-1730. There is a lack of clarity around the treatment of rejection from CSS, between both R044 and the MHHS design artefacts e.g. MHHs-BR-RS-088.1 and MHHS-BR-RS-079 both suggest MPRS would still load the new MDR record and appoint in MPRS despite a rejection from DCC/CSS. Our assumption would be that we do not load a MDR appointment that is rejected from DCC/CSS and we send the IF-035 rejection to notify the DS/Supply of this. However no clarity on what to do if DCC/CSS rejects a MDR end date on a de-appointment T4-COM-1730 was raiseed on 15/09/22 MHHS Design Team Rejected the comment with a statement this is outside of MHHS Scope. How MPRS treats the MS/DS appointment and how it responds over hte DIP is within MHHS design. The requirements we are enquiring about are already included in the MHHS design documents as in scope also. This is a major blocker to MPRS design on MDR appointment processes (Raised as DI-93) |  | Closed |  |  |  | Discussed with SCS this is a REC requirement. Agreed no error codes will be received, just use a generic response. | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-129 |  | DI-94 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0086 comment on 12/01/23 following the release of the first draft of IF-050 in the revised interface catalogue artefact "Related MPANs and Linked Import Export are not set at MPAN Creation. EES can get these on the IF020 Remove these blocks from IF-050 as they would never be populated" MHHS design team marked as accepted and changed but the blocks still exist in IF-050, these blocks will never be populated and so should be removed from the IF-050 interface(Raised as DI-94) |  | Closed |  |  |  | Closed - duplicate of DIN-115 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-130 |  | DI-95 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0088 on 12/01/23 "D-011 & D-050 it is still unclear how LLFC and DUoS Tariff ID will be stored and managed in MPRS. DUoS should be an Alias of LLFC and not have its own data item in MPRS. LLFC will be renamed to DUoS Tariff when the old arrangements have ended. LDSO impacts having to maintain two items which will lead to billing issues" Marked as clarified and closed witih a clarification statement to be issued on tuesday 24th January, this clarification statement was not received. Awaiting clarification(Raised as DI-95) |  | Closed |  |  |  | Email to Madison to check can close |  | MPAN Ownership
MHHS-DIN-131 |  | DI-96 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 is missing business rules: REG1001 - MPAN [DI-063] is at [REG.RMPStatus] not status Created/Operational. This should apply to IF-025. IF-025 is missing a rule that consent granualiry EFD must not be earlier than supply start date. Consent Granularity EFD must not be prior to current consent granularity EFD The Consent Granularity Energy Direction Domestic Premise Indicator Combination must be valid in ISD(Raised as DI-96) |  | Implemented |  | Interim Release 1 |  | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-132 |  | DI-97 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 IHD update does not include validation rule 1019, does this mean IHD EFD can be prior to current and effectively cancel out the current IHD status completely, or is it just an error and the rule should be added to interface catalogue for IHD?(Raised as DI-97) |  | Implemented |  | Interim Release 1 |  | Amendment accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-133 |  | DI-98 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 will not allow a SMSO to be set for a non smart meter "REG1022 - SMSO ID Cannot be set where Market Segment is [Reg.Segement]", would a non smart supplier be able to send a B031 SMSO block, they will need to be able to if they are required to clear an old SMSO by populating SMSO as null(Raised as DI-98) |  | Implemented |  | Interim Release 1 |  | Added new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements | 2023-03-23
MHHS-DIN-134 |  | DI-99 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 "SSC must be valid in ISD. Rejection reason: REG1044 - SSC must be a valid value in ISD" SSC are not yet populated in ISD(Raised as DI-99) |  | Closed |  |  |  | Clarified that SSC validation will be based on Frozen MDD. Seperate DIN to cover availability of ISD | No Change | MPAN Ownership |  | MHHSP-EM021 ISD Entity Data Map, MHHSP-DES138-Interface Catalogue
MHHS-DIN-135 |  | DI-100 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Should B032 PC and SSC block on IF-025 only be permitted when theres a traditional meter fitted at the MPAN?(Raised as DI-100) |  | Closed |  |  |  | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-136 |  | DI-101 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | How is the Green Deal Exists defined. Does this mean there's a green deal linked to the MPAN regardless of dates, does it mean there's a green deal currently active or due to become active, or does it mean there is a currently active green deal assigned to the MPAN? (Raised as DI-101) |  | Implemented |  | Interim Release 1 |  | Remove Green Deal exists (DI-110) from Data Catalogue and IF-050 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-137 |  | DI-102 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-007 Validation rule "Metering Service [S0.SenderID] holds valid previous appointment then Energisation Status EffectiveFrom Date [DI-034] should be < [REG.App End Date] + 10" The way it's curently written suggests MPRS should accept an IF-007 from the previous appointed MS, event if there ETD was greater than 10 days ago, provided the ES EFD date was less than their ETD + 10. E.g the previous MS could send IF-007 two years later with ES EFD of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then a separate rule should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? Linked to DI-41(Raised as DI-102) |  | Implemented |  | Interim Release 1 |  | REG1003 validation rule updated in IF-007 to constrain energisation updates to 10 days after the MS appointment period |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-138 |  | DI-103 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-034 Submitted rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD |  | Closed |  |  |  | Duplicate of DIN-176 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-139 |  | DI-104 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Need clarity on what role code should be used in C0200 for MS and MDR appointments Linked to comment T4-COM-1790 which was accepted as design issue raised but then moved to a work off item "We would like to see some indicative Role Codes and DIP IDs so we can populate development systems with this data " |  | Closed |  |  |  | Send "MDR" as role code as per Registration requirement. Allocation of DTN MPIDs is a seperate issue | No Change | Registration | Existing EMAR I/F | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-140 |  | DI-105 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 |  | Closed |  |  |  | Discussed with SCS the IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR. Agreed to close | No Change |  |  | MHHSP-BP003A, MHHSP-BRS003 Registration service requirements
MHHS-DIN-141 |  | DI-106 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 |  | Closed |  |  |  | RECCo consequential change | No Change |  |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-142 |  | DI-107 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | There currently aren't sufficient rules to ensure that a principal primary MPAN is not also a linked export subsidiary MPAN or that a subsidiary secondary MPAN is not also a principal import linked MPAN. The MHHS design either should accommodate both (would need clarity on how to treat cases where MPANs are BOTH principal and subsidiary) OR new rules should be introduced to prevent this occuring AND cleanse existing cases ahead of migration |  | Implemented |  | Interim Release 1 |  | Validation rules updated for IF-019 | Missing/incorrect validation rule | MPAN Ownership |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-143 |  | DI-108 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Requirements were uplifted in v4.5 to include logic around market segment on related MPANs MHHS-BR-RS-124.1: Registration Service must, in the case of Related MPANs and following derivation of Market Segment for individual MPANs, update the Market Segment for the Primary MPAN and all the Secondary MPANs based on the following rule: 1. If any MPAN in the Related MPAN Group has a (derived) Market Segment of Advanced, then set the Market Segment for all the MPANs to Advanced and set the Market Segment Valid Flag to "Yes" for all the MPANs This specifically cites related primary/secondary and does not mention linked import/export associations at all. But then another requirement implies maybe it should have done: MHHS-BR-RS-127: Registration Service must , in circumstances where the derived market segment is invalid (and has not been overridden by Linked/Related MPAN logic ) Should MHHS-BR-RS-124.1 have applied to linked import/export associations too or is it intended solely for primary/secondary related MPANs? |  | Implemented |  | Interim Release 1 |  | This should only apply to Related MPANs. Updated RS-127 | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-144 |  | DI-109 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131 This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to: Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. |  | Closed |  |  |  | Duplicate See DIN-169 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-145 |  | DI-110 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. |  | Implemented |  | Interim Release 1 |  | Added L as valid value for DI-979 in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-146 |  | DI-111 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. |  | Implemented |  | Interim Release 1 |  | Agreed with SCS to reuse STD Error Response Section in IF035 to communicate Lapsed Reason . See DIN-145 for summary of updates | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-147 |  | DI-112 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-008 response block is listed as mandatory, however on disconnection the MPAN is de-energised by MPRS automatically. The supplier cannot de-energise after disconnection on the IF-007, it must be automatic at MPRS as per The de-energisation needs to be communicated on the IF-008 but it is not in response to an IF-007 and so we cannot populate the response block. |  | Implemented |  | Interim Release 1 |  | Data interface change agreed. Added Interface note to IF-008 to cover forced de-energisation changes by Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-148 |  | DI-113 | 2023-02-10 | St Clements | 2864 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-113 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { "confirmingMpid": "string", --* "registrationId": "string" --*, "updateSucceeded": boolean --* } Suggest that DI-0980 is removed from B066 |  | Closed |  |  |  | Discussed with SCS and agreed to close - note no error codes returned from CSS so will provide generic error code | No Change |  |  | MHHSP-DES138-Interface Catalogue, JSON, YAML
MHHS-DIN-149 |  | DI-114 | 2023-02-10 | St Clements | 2865 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-114 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 On IF-038 validation "REG1073 - Customer Direct Contract already exists for MPAN [DI-063] for that period" The respective validation rule for this states: If Contract End Date [DI-145] <= Max existing active MS contract end dates [Reg.MAX_DCMS_Enddate], EXCEPT IF requesting MS [S1.SenderID] = Currently Active Direct MS [Reg.CurrentActiveDC_MS_DIPID] AND Contract End Date [DI-145] <= existing active MS contract end date [Reg.CurrentDCMS_Enddate] This rule doesn't fully prevent overlapping appointments as does not cover where the MS is not currently contracted MS and ETD > current ETD which should also be rejected. Think a simpler rule would cover this scenario more fully e.g. If there is an active contracted MS/DS, and the submitting MS/DS does not match then reject And then ETD can be greater or later than current ETD for the currently contracts MS/DS anyway so doesn't need specifying? |  | Closed |  |  |  | SRO Team do not believe that a change is required. Linked to DIN-554 |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-150 |  | DI-115 | 2023-02-10 | St Clements | 2866 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-115 in our log In some place on IF-038 tab there is reference to a future customer direct contract e.g. "OR requesting MS [S1.SenderID] <> Any future Direct MS [Reg.FutureDC_MS_DIPID] " "extended dates will be subject to checking if another Service Provider has registered a separate Customer Direct Contract covering the same period" - this can only happen if there's a future appointment "AND ALSO removing all future periods which may or may not have been accepted and recorded previously." As there is no Effective From Date included in the flow MPRS will store an Effective From Date of the system date at the time of creation of the customer contract indicator. It will not be possible to set one to start in the future as the IF-038 does not include effective from date. Is this the same understanding as the MHHS Design Team? |  | Closed |  |  |  | As per DI-149 above SRO Design Team do not belive that any changes are required |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-151 |  | DI-116 | 2023-02-10 | St Clements | 2868 | Madison Layton | Software Provider |  | Just spotted a change in v4.7 and raised in our log as DI-116 Artefact: MHHSP-BP010-Change of Registration Data -v4.7 under MPL and GSP Group amendment section, DB02 has been amended in v4.7 to DB002. DB002 is not correct, DB02 was the correct name For reference the DB flows only ever have one 0 in, there is DB01 (MPAN creation), DB02 (MP updates), DB03 (Disconnection) and DB05 (Import/Export Linkages) |  | Implemented |  | Interim Release 1 |  | BP010A step 10 flow name change to DB02, BP010B step250,step440, Step560 flow name change to DB02, and update BPD descriptions to DB02. | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-152 |  | DI-117 | 2023-02-14 | St Clements | 2912 | Madison Layton | Software Provider |  | On looking more closely at the validation rules for IF-019 spotted a few issues. IF-019 REG-1061 rule for Related Create event code appears to be written incorrectly. The rule and rejection description don't quite align. Rule: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) are not currently part of an import/export relationship Rejection reason: REG1061 - Prosposed MPAN(s) [DI-073] / [DI-074] are already part of a Related MPAN Relationship Should the rule read: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) is currently part of a related primary/secondary relationship? The rule and descriptions also don't appear to fully align for some in import/export section too - REG1052, REG1055, REG1057 and might need some minor tweaks to correct. |  | Implemented |  | Interim Release 1 |  | REG1061, 1052 and 1055 rules updated. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-153 |  | DI-118 | 2023-02-14 | St Clements | 2913 | Madison Layton | Software Provider |  | On working on detailed design for Related MPANs, noticed the IF-019 interface is missing a rule that the Secondary MPAN must not be a Primary in another Relationship. You could expand REG1064 to include this as the description sounds like it should have been covered here. Rule: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN Description: REG1064 - Proposed Secondary MPAN [DI-074] is already part of a different MPAN Relationship Could amend rule to: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN OR [DI-074] is already in a relationship as a Primary MPAN |  | Implemented |  | Interim Release 1 |  | REG1064 validation rule updated | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-154 |  | DI-119 | 2023-02-15 | St Clements | 2919 | Madison Layton | Software Provider | IF-019 validation gap on primary and subsidiary MPAN | On further detailed design we’ve spotted a potential design gap. Currently it is possible to enter a state where an MPAN is both a primary and subsidiary MPAN at the same time (e.g. Primary but also export linked or Secondary but also import linked). The current MHHS doesn't accommodate an MPAN being in both states at the same time. We’ve already looked to add rules to try to mitigate this on DB02/DB05 internal flows but would need additional rules on IF-019 to fully prevent this scenario occurring. Rules we think are required: 1. On receipt of IF-019 with event code RelatedCreate or RelatedAdd, the primary MPAN must not have energy direction of Export 2. On receipt of a IF-019 with event code RelatedCreate or RelatedAdd, any listed secondary MPAN must not in an active Import/Export relationship as the Import MPAN 3. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Import MPAN must not be in an active relationship as the secondary MPAN 4. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Export MPAN must not be in an active relationship as the primary MPAN |  | Implemented |  | Interim Release 3 | 2023-07-12 | Agreed with SCS that changes to IF-19 tab would be made to support Rules 1 and 4. Validation Rules updated accordingly with new Error codes (REG1067/1068) created to support. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-155 |  | DI-120 | 2023-02-15 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. |  | Closed |  |  |  | see also DIN-172/173. Included in 5.1 DUPLICATE See DIN-172 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-156 |  | DI-121 | 2023-02-24 | St Clements | 3078 | Madison Layton | Software Provider |  | We have logged a new design issue under DI-121. IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP |  | Closed |  |  |  | Duplicate of DIN-173 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-157 |  | DI-122 | 2023-02-27 | St Clements | 3090 | Madison Layton | Software Provider |  | New design issue (SCC Ref DI-122) for the IF-005 related to REC CP R0032. The current v5.0 validation in the IF-005 does not include the new validation introduced with REC CP R0032 (R0032 is approved and being implemented in the D0312 this June): NEW REC CP R0032 Validation: V Rejected – ESME ID already exists within MRPS and does not match Removed Meter, Associated Import/Export MSID or Related MPAN W Rejected - MSN relates to a Smart Meter Type and the ESME ID is NULL X Rejected – ESME ID Format is Invalid Y Rejected – Number of Displayed Register Digits is NULL and the MSN relates to a Smart Meter Type Z Rejected – Non-Smart Meter Type with Number of Displayed Register Digits populated AA Rejected – Meter Location is invalid AB Rejected – Non-Smart Meter Type with ESME ID populated AC Rejected – Number of Displayed Register Digits is incorrect IF-005 Validation: V not covered, needs to be added as a Level 5 Validation Rule W is already covered by DI-085 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) X is already covered in DI-085 population notes (Level 4 validation RCP1023 Msg Contains Invalid Valid Value Combination(s)) Y is already covered in DI-091 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) Z is not explicitly covered, suggestion: add to DI-091 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AA is covered in the population notes AB is not explicitly covered, suggestion: add to DI-085 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AC not covered, Suggestion: add the following population note from R0032 to DI-091: Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” Summary Please add the following Changes to the IF-005 to align it with the D0312 validation and maintain the same level of Smart Meter data quality in the Registration Service: New Level 5 Validation rule for DI-085 implementing V from the D0312. ESME ID must be unique within MPRS unless it’s a Linked MPAN where the same Smart Meter can be shared across Linked MPANs New population note for DI-091, only to be included for Smart Meter Types New population note for DI-085 , only to be included for Smart Meter Types New population note for DI-091, Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” |  | Implemented |  | Interim Release 1 |  | New Validation Rules added to IF doc to ensure full coverage and alignment with CP Error codes described | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-158 |  |  | 2023-02-27 | Elexon | 2908 | Derek Weaving | Central Body | Use of CCCs to categorise the data for future charges | As part of the Performance Assurance Working Group discussions on Supplier Charges, we are exploring the use of CCCs to categorise the data for future charges. It is noted that Settlement Period Quality Indicator referenced in the VAS Method statement is for illustrative purposes and would welcome clarity on the following: · What is the intended process to populate the Settlement Period Quality Indicator in the initial ISD Table? · What would be the process to be involved in those activities to determine the categorisations should additional CCCs be required? |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | This DIN has been moved to Interim Release 5 as it is related to DIN-409 which has an objection raised that is pending a discussion to clarify the solution. Name change and field length have been actioned. Reviewing whether any changes to Settlement reports are required Recommending a change to this ISD Data Item: Settlement Period Quality Indicator to be set as per Appendix 1 of MHHSP_METH007 MDS_Method_Statement v5.0 This data item need to be changed to something like ‘Valid Settlement Period Quality Indicator Set’ and the field size needs to be increased. The data catalogue will need the revised data item and the field length will need increasing from 20 to at least 100. This Item also appears in some interfaces that will need to be updated. This is because it represents a set of SPQIs. The initial intention is to populate as per the table and check if any new SPQIs have been introduced in the baseline design Method Statement that are not covered. If new CCCs are introduced the appropriate flags for each new CCC would need to be agreed. However, it is likely that another dimension to the table below would need to be introduced to facilitate new CCCs. Word 'Illustrative' to be removed and will be updated to say Valid Settlement Quality Indicator Set. Change to be made across all impacted Method Statements. New CCC's will require a Modification to the BSC interface requirement. Proposed changes have been reverted to the initial state. Data item Settlement Period Quality Indicator, with a field length of 5. This is due to the agreed solution for DIN409 following DRG where it was agreed the list element would be removed in favour of individual row(s). The word 'Illustrative' will also remain within the Method Statements | Missing/incorrect validation rule | Meter to Bank | Volume Allocation Service | MHHSP-METH006_VAS_Method_Statement MHHSP-METH007_MDS_Method_Statement v5.1 ED021 ISD Entity spec MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-159 |  |  | 2023-03-01 | ENWL | 2994 | Paul Band | Network Business | Interfaces for UMSO | DES-138 Interface Inconsistencies vs BSCP7XX for UMSO Discussions with ENWL have highlighted a number of inconsistencies in the Interface Catalogue when it comes to routing for UMSO's. DIN-106 also refers. UMSO is not listed as a recipient in DES-138 for the PUB-008, but this is in the draft BSCP and should be added to the PUB UMSO is not listed as a recipient in DES-138 for the PUB-020, but this is in the draft BSCP - this is not needed in the BSCP as there are no unmetered Related MPANs UMSO is not listed as a recipient in DES-138 for the PUB-035, but this is in the draft BSCP - view that it is unlikely for this flow ever to be used as the appointment will not trigger any processes to need a subsequent update UMSO Is listed as UMSI, not UMSO in PUB-036 in DES-138 UMSO is listed as UMSC, not UMSO in PUB-018 in DES-138 The IF_LIST tab should be reviewed for consistency |  | Implemented |  | Interim Release 2 | 2023-06-23 | As with DIN-106, there are inconsistencies in the Interface Catalogue for UMSO routing. This has been compounded by a review of the draft BSCP for UMSO, which has added a number of PUB flows going to UMSO that aren't currently in the catalogue. Covered by updated secondary routing rules (see DIN268) Design to check requirements in BSCP and MHHS BPs and ensure the interface catalogue reflects a consistent approach | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue and possibly related business processes and descriptions E2E001 |  |  |  |  | 2023-06-16
MHHS-DIN-160 |  |  | 2023-03-14 | Ovo Energy | 2862 | David Morley | Supplier | BP009 flow addition | Steps 205 and 210 in BP009 wont be completable in the event that theres no comms. I think the process would be workable if there was an exception route here - see red arrow below. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Update Steps 205 and 210 in BP009 with "Comms Available" line label add flow from step 205 to step 215 with “Not Commissioned / No Comms” line label | Process Model correction | Metering Changes | Change of Metering | MHHS-BP009 |  |  |  |  | 2023-06-16
MHHS-DIN-161 |  |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 requirement correction | MHHS-METH001-5.4c Please confirm the requirement: “where daily advance records are available [either in the past or future] and less than 90 days months different from the UTC Date requiring a daily advance - use the mean actual Meter advance from the closest [4] weeks for the same Day Type (as defined in ISD).” |  | Closed |  |  |  | Duplicate of DIN 97. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-162 |  |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 typo | MHHS-METH001-5.5 typo “Where DAEs are required to be calculated the SDS shall use the most recent data a based on the event that triggered the estimation.” |  | Closed |  |  |  | Duplicate of DIN 98. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-06-16
MHHS-DIN-163 |  | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Conditionality Rule for B037 | It is not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure it is unclear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated conditionality rule for Block B037 in IF-001, IF-002, IF-033, IF-036: to show that Either DI-075 (Primary MPAN) or DI-079 (Secondary), and not both, should be populated where MPAN (DI-063 above) is part of a group of Related MPAN. |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-164 |  | DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0093 comment raised on 12/01/2023 "" D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692"" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: ""It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period"" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42" |  | Closed |  |  |  | "This requirement stands - review with SCS in light of SEG scenario. We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error...". Reviewed with SCS and agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-165 |  | DI-122 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | See separate sheet Duplicate of DIN-157 |  | Closed |  |  |  | CR required to add rules in line with CP R0032 Added Miscellaneous Data Validation to IF-005 to cover REC CP R0032 validation rules Wrapped up into design teams main CR Doesn't need to be raised by SCS | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-166 |  | DI-77 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54" |  | Implemented |  | Interim Release 1 |  | Added clarification to REG Notes re Consent and Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-167 |  | DI-78 DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? " |  | Closed |  |  |  | Agree you can't. Could update 1032 rule for USP? Duplicate see DI-29 | No Change
MHHS-DIN-168 |  | DI-92 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 ""DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least ""Registered"", if no DS is appointed then there is already an appropriate Event Code"" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone |  | Closed |  |  |  | CR for new functionality. "Already covered by no MS/DS appointed - MPRS would try to align MS/DS with principle and couldn't as there's no registration to align this to. Need an extra check that can only autoappoint if there's a registration to prevent MPRS crashing Maybe one for DRG? Jon at RECCO for consequential change? Agree not to build for this scenario as this would be an edge case and close | No Change
MHHS-DIN-169 |  | DI-109 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to:Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. |  | Implemented |  | Interim Release 1 |  | Simplified MHHS-BR-RS-131 on when to lapse a SEG appointment | Requirement correction | MPAN Ownership |  | MHHSP- BRS003, MHHS-BR-RS-131 | 2023-03-23
MHHS-DIN-170 |  | DI-110 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. |  | Closed |  |  |  | Duplicate of DIN-145 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-171 |  | DI-113 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { ""confirmingMpid"": ""string"", --* ""registrationId"": ""string"" --*, ""updateSucceeded"": boolean --* } Suggest that DI-0980 is removed from B066" |  | Closed |  |  |  | Agreed with SCS being retained but due to optionality may have to populate text e.g. contact DSP. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-172 |  | DI-120 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. |  | Implemented | 2023-04-27 | Interim Release 1 |  | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-173 |  | DI-121 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP |  | Implemented | 2023-04-27 | Interim Release 1 |  | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-174 |  | DI-72 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a Submitted MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60" |  | Implemented |  | Interim Release 1 |  | "Agreed- doc updates MDR can have gaps between DS EFD and MDR EFD" Updated REG1083 validation in IF-034 so that it allows MDR Effective from dates >= SSD/ DS Eff From date/Existing MDR Eff from date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-175 |  | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" |  | Closed |  |  |  | Duplicate entry | No Change | MPAN Ownership
MHHS-DIN-176 |  | DI-103 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-034 new rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD" |  | Implemented |  | Interim Release 1 |  | Agreed -doc updates Updated REG1082 to apply for both [SDS-MDRUpdate] and [DSAppSPRepsonse] events in IF-034 | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-177 |  | DI-105 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 " |  | Closed |  |  |  | "Reason for IF-035 is to trigger when SDScan send the Meter info" & The IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR Agreed with SCS no changes are required, they now understand the context agreed to CLOSE | No Change | MPAN Ownership |  | MHHSP-BP003A
MHHS-DIN-178 |  | DI-106 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | MS missing a requirement to send MS updates to CSS | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 |  | Closed |  |  |  | Closed as discussed with SCS that this is out of scope for MHHS Programme. | No Change | [7 empty] | 2023-07-14
MHHS-DIN-179 |  | DI-111 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. |  | Closed |  |  |  | Duplicate of DIN-146 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-180 |  | DI-125 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 the Meter Removal is currently not permitted for a prospective MS Is it possible for the MS to need to remove two meters and replace it with one? In which case meterexchange would only allow them to do part of this process (remove 1 and add 1) but not complete it, so SEG could not complete. Should meter removals therefore be allowed for prospective MS? (REG1019) |  | Implemented |  | Interim Release 1 |  | Revised REG1019 and added REG1027 for MeterRemoval event in IF-005 | Requirement correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-181 |  | DI-126 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Missing Rule on If-005: MAP EFD must not be > removal date |  | Implemented |  | Interim Release 1 |  | Added new rule for MeterUpdate and MeterHistoryUpdate events so that MAP EFD must not be > removal date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-182 |  | DI-127 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 On exchange - the MAP and IHD groups are for new installation not removed meter - does this need to be clarified? |  | Implemented |  | Interim Release 1 |  | New note added to IF-005 to clarify that only the newly installed MAP and IHD information is required on MeterExchange | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-183 |  | DI-128 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-005, IHD EFD missing validation in IF-005 (Between install and removal date) |  | Implemented |  | Interim Release 1 |  | Covered Release 5.1, IF-005, IHD EFD missing validation added | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-184 |  | DI-129 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-005 incorrect validation rule: REG1010: On event code Meter exchange and Meter Install rule states MAP EFD >= Install date, it should be = not >=" |  | Implemented |  | Interim Release 1 |  | IF-005: Updated to REG1010 (MAP Eff from date check ) to = install date for MeterInstall and MeterExchange | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-185 |  | DI-130 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | It should not be possible to change MDR EFD once set. Need validation rules to enable MPRS to reject if IF-034 is submitted with current MDR but a different EFD. |  | Implemented |  | Interim Release 1 |  | Agreed - doc updates Covered by L3/4 validation as per updated Validation rule notes | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-186 |  | DI-131 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031, there is currently not enough validation to ensure on a SEG, that the same SP isn't appointed for the current registration. Need additional validation rule: If scenario SEG and current supplier, then SP must not be current SP. |  | Implemented |  | Interim Release 1 |  | Agreed - doc updates Updated validation rule Added REG1095 in IF-031 to check different Data Service proposed for SEG appointment | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-187 |  | DI-132 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Supplier inability to appoint MS/DS for Principal and Subsidiary MPAN | Unhappy Path Scenario: Receive IF-031 for MPAN that is both Principal and Subsidiary MPAN at the same time. This will be rejected as per REG1038/REG1039 Supplier will be unable to appoint MS/DS for the MPAN or any related/linked subsidiary MPANS. |  | Closed |  |  |  | Closed, there is an existing to prevent this scenario happening going forward. Agreed with SCS to raise examples in the Data Cleanse Forum. | No Change | [7 empty] | 2023-07-14
MHHS-DIN-188 |  | DI-133 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031 the rule REG1030 reads [DI0-828] in not a valid UMSO in DNO [DI-108]/[DI-109] This should read LDSO not DNO |  | Implemented |  | Interim Release 1 |  | Tied up with If-005 rejection description flexibility action Change REG1030 to read: REG1030 - [DI0-828] in not a valid UMSO in LDSO[DI-108]/[DI-109] SC change incorporated into 5.1.1 | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-189 |  | DI-134 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On IF-031, REG1036 is written to only apply to USP when it should apply to all scenarios? ""Proposed MDR Date [DI-836] >= [REG.MPAN_SUP_SSD] However don't think this rule is required at all as this is already covered under the REG1036 rule that MDR Date < DS EFD? Linked to DI-66" |  | Implemented |  | Interim Release 1 |  | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-190 |  | DI-135 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-034 missing validation rule REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational |  | Implemented |  | Interim Release 1 |  | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-191 |  | DI-136 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Addition of validation rules to MPRS to restrict Retrospective changes | MPRS does not currently prevent Retrospective changes to DUoS Tariff ID or Connection Type. Should MPRS add new validation rules for these items to restrict Retrospective changes? Please can you update DIN-191 to include Disconnection Date & Export Association. We don't currently have any restriction on how far these data items (and the others in DIN-191) can be back dated. This is a retrospective change through the DB interface and not a Manual Amendment. There are no retrospective periods for the following data items, this means the data items could be changed earlier than the settlement window and cause issues for settlement. There are restrictions that these data items must be within MS/Registration periods where appropriate, but the EFD/SSD could still be years into the past. - MDR EFD, - MS EFD, - DS EFD, - IHD Status EFD, - PC EFD, - SSC EFD, - Energisation Status EFD |  | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | Internal review has taken place as to whether DUOS Tariff ID updates should be retrospective. SC to create PPT Review Internally & with ScS then agree DRG discussion date. LINKED TO DIN-056 above | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-192 |  | DI-137 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | For If-031, scenario SEG, the business process diagram/requirements only describe the appointment lapsing once reaching it's SSD if no SA is received. If we receive a cancellation we would like to lapse the appointment at that point in time (it cannot become secured active after being cancelled) and not wait until the SSD to do this. |  | Implemented |  | Interim Release 1 |  | Added new requirements to BRS003, MHHS-BR-RS-24.1 and 58.1 | Design Ambiguous | MPAN Ownership |  | MHHSP-BRS003-Registration Requirements | 2023-03-23
MHHS-DIN-193 |  | DI-138 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | The YAML name for metered indicator (Data Item 127) is meteredUnmeteredIndicator. This is then set to true of false. It isn't clear whether true means it's metered or unmetered due to the naming convention. It should be named meteredIndicator instead to make it clear true means metered, false unmetered. |  | Implemented |  | Interim Release 1 |  | Updated YAML details in the Data Catalogue for DI-127 Metered Indicator. Updated YAML accordingly Updated data catalogue/ YAML | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-194 |  | DI-1 | 2023-03-15 | St Clements | 4475 | Madison Layton | Software Provider |  | For IF-035 what is Event Code [IMS-SendMTD] intended for? If intended for sending to old MS then this should be done via secondary routing on the original IF-035, not via another separate IF-035 message produced by MPRS with different event code. |  | Closed |  |  |  | This message is effectively a copy of the DSAppAccepted AND/OR MSAppAccepted but sent to the Incumbent (current) Metering Service to act as a trigger for that MS to send MTDs. This should be created by MPRS. Requirements MHHS-BR-RS-053 and MHHS-BR-RS-019 cover Registration Service sending this. Message to check and close | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-195 |  | DI-76 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Originally raised as T4-COM-1691 on 15th Sept 2022: ""MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days "" Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5" |  | Implemented |  | Interim Release 1 |  | Agreed doc update Also in Reg Notes tab Updated validation rules and Reg notes Updated REG1037 in IF-031 to 2 workings days and updated REG notes, to align with process and requirements | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | 2023-03-23
MHHS-DIN-196 |  |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Updates are required to clarify nullable fields |  | Implemented |  | Interim Release 1 |  | Updates to Interface catalogue includes changes to interfaces and block data items which are present and can be null 1. MHHSP - ERI011A - ECS Reports - Internal v5.1: The data catalogue is the only tab that has been updated 2. MHHSP - ERI011B - ECS Reports - External v5.1: The data catalogue, DIP_Common, MHHS-REP-003 and MHHSP-REP-006 have been updated |  | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue, MHHSP-E2E001 End-to-End Solution Architecture MHHSP - ERI011A - ECS Reports - Internal MHHSP - ERI011B - ECS Reports - External | 2023-03-23
MHHS-DIN-197 |  |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Decision taken to document digital signing of interfaces outside of the interface document. |  | Implemented |  | Interim Release 1 |  | Remove Z0 and ZI blocks from all interfaces. Signing process will be documented in the Code of Connection document. | Technical corrrection | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue Code of Connection | 2023-03-23
MHHS-DIN-198 |  |  | 2023-03-15 | Large Suppliers |  | Haz Elmamon | Large Suppliers | Complex Meter Site | Clarification on complex meter site, passed down from DAG as part of the work off plan, Haz to gather concerns for discussion at DA. LSC Rep provided information to the issue on 22-Mar-23 |  | Requires Industry Work Group review | 2023-08-31 | Interim Release 6 | 2023-10-18 |  |  | MPAN Ownership | [6 empty] | 2023-07-14
MHHS-DIN-199 |  |  | 2023-03-23 | BGAS | 3460 | Neil Strange | large Suppliers |  | Participant wishes to see the use of standardisation in the interfactions between the SDS and sub roles MDR PSS |  | Closed |  |  |  | Closed based on recommendation for programme CR to be raised by the Large Supplier Rep | No Change | Supporting Docs | SDS Validation / Extimation | MHHS-DES138-Interface Catalogue
MHHS-DIN-200 |  |  | 2023-03-24 | CGI | 3489 | Chris Beard | Software Provider | Hierarchy definition for selecting correct register reading in the case of multiple readings for the same settlement period | If there are multiple register readings available for the same Settlement Day, where is the hierarchy defined for selecting which should be used? Is this solely based on Reading Method (i.e. 1. A – Actual, 2. C – Customer, 3. E – Estimated by SDS, 4. S – Estimated by Supplier) or is it dependent on other factors such as the Event Code in the IF-041 ([ReadingRemv], [ReadingInstl], [ReadingEnergisationChg], [ReadingCOR], [ReadingOnSite], [ReadingCOS], [DSEstimate], [SupplierAgreedCOS], [ReadingOverride], [ReadingRemote])? |  | Closed |  |  |  | Reading methods do not apply to Register Readings - recommendation for DIN to be closed. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-201 |  |  | 2023-03-24 | ESG | 3529 | Patricia Parker | Software Provider |  | IF-033 Validation for population into the IF-034 The receiving party business validation rules state “Each Service Provider will need to determine their own validation criteria when processing Appointment Requests. The list below is intended to cover a number of potential possibilities based on the data items made available, and not to suggest that Service Providers needs or should perform such validations.” But should the DI-143 ‘Service Provider Proposed Appointment Response Code’ not form a valid set list (ENUM Vals) in the Data Catalogue so that all parties are working to the same list of applicable codes, rather than this field being a string with a length of 200 field? |  | Closed |  |  |  | IF-033 has been updated as part of Interim Release 1 and the ENUM Vals will not be updated this is because we will have dynamic error messages which cannot be enumerated. |  | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-202 |  |  | 2023-03-24 | ESG | 3513 | Patricia Parker | Software Provider | Operational Choreography 60 minute turnaround | Registration Responses in connection with the PUB-31 given the NFS requirement is a 60-minute turn-around time. Within the Operational Choreography there is requirements OPC-140: From our understanding this means that when suppliers receive the PUB_032 from the Reg Service rejecting the appointment Request suppliers then have 60 minutes to re-issue a fresh IF_031 appointment. For example, there is a rejection code for 'CSS Reg ID not known', this would suggest that a party is out of sync and would need investigating especially as in this case, the REG ID would have previously been provided on PUB- 002, DI-849 and CSS is the master of the REG ID and not the Registration Service. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Added suggested text to Ops Choreography. Suggested text is "It is noted that some requests may require manual work and may be as a result of incorrect appointments from the Supplier. The expectation will be 90% of requests are systemically processed within 60 minutes with the residual being processed by the end of the following working day". | Doc Ref correction | Supporting Docs | Operational Choreography | MHHS_OPC001_Operational_Choreography |  |  |  |  | 2023-06-16
MHHS-DIN-203 |  |  | 2023-03-24 | CGI | 3502 | Chris Beard | Software Provider | mapping of Estimation Reason Codes to estimation Methods | MHHSP-METH001 M-13. Can you provide a definitive mapping of Estimation Reason Codes to estimation Methods? For example, LTV to Method 11. When should an SDS use Estimation Codes such as Opt Out, Comms. Fault. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated METH001 section 7.3 to reflect Estimated Methods to Estimated reason codes | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001 |  |  |  |  | 2023-06-16
MHHS-DIN-204 |  |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | De-energised sites | MHHSP-METH001 M-3. Which estimation Method should an SDS use for de-energised MPANs that would result in an estimation code of ‘De-Energised’? Without a specific Method statement to cover de-energisation, we will end up estimating consumption. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Added Method 13 to reflect de-energised sites within METH001 and updated section 2.29 on METH002. | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001 |  |  |  |  | 2023-06-16
MHHS-DIN-205 |  |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | Removal of Estimation Reason Code "Disconnected" | Can you confirm that the Estimation Reason Code ‘Disconnected’ will be removed from the table in 7.3? |  | Implemented |  | Interim Release 2 | 2023-06-23 | Removed "Disconnected" from Table 7.3 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  |  | 2023-06-16
MHHS-DIN-206 |  |  | 2023-03-27 | St Clements | 3703 | Anna Davis | Software Provider |  | Within the MHHS-E2E001 - End-to-End Solution Architecture, there is reference to MHHS-E2E003-Physical Interface Specifications in 1.3 References section This should be labelled as MHHSP-DES138-Interface Catalogue |  | Implemented |  | Interim Release 1 |  | Updated 1.3 reference section | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-207 |  | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Clarity on when agent appointments should become effective | There is ambiguity within the design on when agent appointments should become effective, which means that different participants have a different view on when agent appointments should become active. |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | At the DRG held on 4th August it was agreed that Appointments need to become active in UTC. References to local time removed Old solution: Appointments become active at midnight local time. Participants raised objections against the old solution therefore this DIN went to a DRG on 4th Aug for discussion. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-208 |  | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Registration Service rejection of Legacy messages for an MPAN | Within the existing Migration Design, it is stated that the Registration Service should reject all Legacy messages for a given MPAN once a Forward Migration has been initiated for said MPAN. This would prevent a legacy MOP from sending the relevant legacy flows if they need to change a meter when an MPAN is mid migration. |  | Closed |  |  |  | Closed following internal review with Design, Migration and Code Team. Agreed that current design will stand in that all legacy messages will be rejected following the point the IF-031 is issued. Reaffirm existing guidance that migration should be timed to avoid any planned work. Unplanned work/change occuring during migration should be communicated using an MHHS IF Message once migration has been completed. | Requirement correction | Migration | Migration | Migration Design Migration Requirement |  |  |  |  | 2023-07-14
MHHS-DIN-209 |  | Design Team | 2023-03-30 | Design Team |  | Sean Cooper | SRO Design Team |  | ~ Level 1/2 Error Code "MSG0000 - Success" Added to Interface Intro Section ~ MSG0018 - Timestamp cannot be future removed and explainatory note added to IF Notes Section of DIP Common |  | Implemented |  | Interim Release 1 |  | Updated actioned in v5.1.1 of IF Doc. This relates to MSG1008 not MSG0018 as originally given in the design issue. MSG0000 Success added. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-210 |  | Design Team | 2023-03-30 | RECCo |  | Sarah Jones | Consultancy |  | Possible change flagged The original view of the Design Team was that this flag and associated info (ie Is a Customer Direct contract in place, who is the DS/MS with that contract, but not the Eff To Date aka Contract End Date) should be visible to incoming Suppliers, for exactly the reasons you suggest i.e. so that in an incoming supplier could factor the existence of a CDC(s) into their acquisition process / pricing etc. I think we also felt that SP’s who weren’t currently appointed, but may have signed a new CDC should also have the ability to set the flag, as it’s the sites that are part of a CDC, but where that SP isn’t the appointed SP that are the most difficult to coral and manage. The position at the moment is that the existence of a CDC would be shared with incoming Suppliers as part of PUB-002, however this would likely be too late in the process to provide the assistance and support required to an incoming supplier (on all aspects of the sale, contract/price in particular) … … therefore, I think it was also envisioned that information about CDC’s would be available via ECS – so prospective suppliers could check in ECS on the CDC position as part of the other pre-acquisition checks they may undertake. Therefore, I think the decision on exactly what information is shared ‘pre-acquisition’ to participants probably sits with yourselves (RECCo) to finalise as part of your ECS Design / DP Assessment. All information in relation to CDC’s will be passed/made available to ECS via receipt of a copy of PUB-039, so what item(s) are displayed and to what parties I think would get covered off as part of that ECS Design activity. |  | Closed |  |  |  | Closed, as per discussions with RECCo that no design changes are required. | No Change | [7 empty] | 2023-06-16
MHHS-DIN-211 |  | DI-139 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-009 Event Code is referred to as [CSSDeRegistration] in the population notes and swagger open API spec but then B042 block title references event code CSS Deactivation, B042 should reference CSSDeRegistration. |  | Implemented |  | Interim Release 1 |  | Update B042 to reference CSSDeRegistration | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-212 |  | DI-140 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | MHHSP-BP007-Disconnection-v5.0 is missing IF-050 being sent out on a change to MPAN/RMP Status |  | Implemented |  | Interim Release 1 |  | to BP007 and BPD007 Requires a flow from Registration Service to EES (IF-050 to DIP, a Publish Change to MPAN/RMP Status process, a PUB-050 from DIP to EES process Receive Change to MPAN/RMP status) starting at step 70 (disconnection). Plus add new step descriptions to the BPD and amend Step 70 description to include IF-050. | Process Model correction | Metering Changes |  | MHHSP-BP007-Disconnection, MHHSP-BPD007-Disconnection
MHHS-DIN-213 |  | DI-141 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Data item 997 in S1 common block is senderId in swagger hub, but senderDIPID in data catalogue |  | Implemented |  | Interim Release 1 |  | Update swagger to reflect senderDIPID to align to data catalague | Technical corrrection | Technical Artefact | Swagger | JSON,YAML
MHHS-DIN-214 |  | DI-142 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | REG Notes section Queuing of Prospective Appointments Rule 4 ** Rule 4: If App Scenario = 'SEG' and Supplier ID + Appointment Service Start Date = Existing Supplier ID + Service Start Date > (Service Start Date +2 working days) >> Appointments meeting Rule 4 have missed their opportunity, and will be 'Lapsed' (PUB-035) This rule doesn't make logical sense, needs correcting. What is the intended logic to be applied here? |  | Implemented |  | Interim Release 1 |  | Update to align with validation rule | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-215 |  | DI-143 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 for event code [MeterRemoval] rule REG1002 Sending Metering Service ID [SO.SenderID] is currently appointed OR held a valid appointment for Meter Installation Date [DI-057] This should read removal date not installation date |  | Implemented |  | Interim Release 1 |  | Updated validation rule REG1002 in IF-005 for event code [MeterRemoval] to refer to Meter Removal Date (DI-058) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-216 |  | DI-144 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-144 On IF-005 MPRS will validate Either current, queued SEG or previous MS If previous and not within 10 working days will reject with REG1003 If not previous, and not current or queued, will reject with REG1027 MPRS will then validate if install date/removal date is within MS period of ownership If not will reject with REG1019 REG1019 need correcting to also include <ETD to apply for previous MS It’s not possible to get a scenario where the If-005 passes the above rules (REG1003, REG1027 AND REG1019) but fails REG1002. Therefore REG1002 is not needed and will never be sent as a rejection code. (Add to DI-43) |  | Closed |  |  |  | Agreed with SCS that no further change is required | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-217 |  | DI-145 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | On IF-005 REG1019 should also include validation that the installation/removal date concerned is <=Effective to date (ETD) of MS period of ownership |  | Implemented |  | Interim Release 1 |  | Updated IF-005 validation rule REG1019 to include validation that the removal/install date must be <=Effective to date (ETD) where the update is being provided by previous Metering Service (using their 10 day window) for MeterRemoval, MeterInstall and MeterExchange events. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-218 |  | DI-146 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 for event codes [MeterExchange] and [MeterRemoval], the rule should not reference DI-056 which is the meter ID in the installation block, it should should referenced DI-053 which is the meterId in the removal block |  | Implemented |  | Interim Release 1 |  | Rule updated not to reference DI-056 which is the meter ID in the installation block, it now references DI-053 which is the meterId in the removal block | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-219 |  | DI-147 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 - for other event codes removal date must be >= to Install date but for [MeterUpdate] the rule states > meter install date. Should be >= |  | Implemented |  | Interim Release 1 |  | Update rule for [MeterUpdate] to align to other removal date event codes | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-220 |  | DI-148 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1007 unecessary and will never be triggered, it is already covered under REG1001 cannot submit meter install if MPAN is disconnected |  | Closed |  |  |  | Valid rule to left in as-is but noted cannot be SIT tested | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-221 |  | DI-149 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In the IF-005 guide it states: "When amending the Installation and/or Removal date of a Meter, a supporting MAP history commencing in line with the revised Installation Date must also be provided. Any additional MAPs should be provided in chronological order, each with a ‘MAP Effective From Date’ greater, by at least one day, than the previous." MPRS will accept if the install/removal date is changing AND the MAP History has not been included, there is no requirement in Interface Catalogue or Registration Requirements to reject if MAP history is not provided. |  | Closed |  |  |  | Believe covered by MeterHistoryUpdate rules, but hopefully won't be an issue pending agreement on MAP discussion… IF-005 use case guide will be updated with outcome. DRG has agreed to remove MAP history therefore in lieu of this decision, this change will not be required. Closed | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-222 |  | DI-150 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | sarah |  | Implemented |  | Interim Release 1 |  | Updated wording to match existing validation. Guidance only now provided | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-223 |  | DI-151 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005: Need REG1006 to apply to all event codes, e.g. Meter Update on a change to removal date, will need to check that the removal date does not lead to non unique Meter IDs (overlapping dates) MPRS will reject with REG1006 in this scenario |  | Implemented |  | Interim Release 1 |  | Added REG1006 validation checks to MeterHistoryUpdate and MeterUpdate events. | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-224 |  | DI-152 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 Interface Note below could be read as MeterUpdate event code can be submitted by previous or prospective MS which is not correct "Only the Appointed Metering Service, and for a small window (10 days) to allow for delayed notification of field activities the previously appointed Metering Service; and an incoming Metering Service with a Prospective 'SEG' type appointment may send an IF-005 and update metering details. The [MeterHistoryUpdate] may only ever be used by the Appointed Metering Service. Interface Design assumes that two separate meters with the same 'Meter ID' cannot be installed at the same time. " |  | Implemented |  | Interim Release 1 |  | Updated | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-225 |  | DI-153 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | DI-849 CSS Registration Request Id does not have a YAML name in the interface catalogue In the swagger hub, the corresponding name is CSSSwitchID which is misspelt |  | Implemented |  | Interim Release 1 |  | Updated Data Catalogue to CSSRegistrationRequestID, Swagger to follow | Data interface correction |  | Interface Catalogue Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-226 |  | DI-154 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In MHHSP-BPD007 - Disconnection v5.0, the ordering of the steps are out of order. Steps 140, 145 and 150 are for parties receiving the de-appointment notification from the Registration Service, but this is not sent until Step 155. Step 155 “De-Appoint Services” needs to be before Step 140 “DS De-appointment Notification”. Also Step 145 “Receive De-Appointment Notification” is DIP receiving the de-appointment notification to send on, this needs to be after Step 155 and before Step 140 . The ordering should be: • De-appoint services (155) • Receive De-Appointment Notification (145) • DS De-Appointment Notification (140) • MS De-Appointment Notification (150) |  | Closed |  |  |  | No plans to change step numbers as long as they are unique | No Change |  |  | BPD007
MHHS-DIN-227 |  | DI-155 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1.xlsb, the validation for REG1003 – “Metering Service ID [S0.SenderID] post appointment update period for MPAN [DI-063] has expired” is currently set to “Metering Service [S0.SenderID] holds valid previous appointment then [System Date] should be < [REG.App End Date] + 10 working days”. Should this be <= to allow for the full 10 days? |  | Implemented |  | Interim Release 1 |  | Changed to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-228 |  | DI-156 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 - IF-005 has the following error for [MeterExchange] & [MeterInstall]:- “REG1020 - MAP Effective Date [DI-054] cannot take place in the future” Should this validation also be valid for [MeterUpdate] and [MeterHistoryUpdate]? |  | Implemented |  | Interim Release 1 |  | Added to meter update for removal date. Added to MeterUpdate and MeterHistoryUpdate for MAP effective date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-229 |  | DI-157 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 does not have a rule that the SMSO EFD must not be prior to the latest SMSO EFD. We are implementing this rule with error code REG1019 |  | Implemented |  | Interim Release 1 |  | We are implementing this rule with error code REG1019 Make consistent with others ( PC and ssc + 1 ). Review IHD and SMSO | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-230 |  | DI-158 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 & IF-005 do not have a rejection code where the IHD is invalid. |  | Closed |  |  |  | DIP will reject non-valid values - no change to docs required | No Change
MHHS-DIN-231 |  | DI-159 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-005 - There is no validation on Meter Removal date [DI-58]. This should be mandatory non nullable for [MeterRemoval],[MeterExchange],[MeterUpdate], but mandatory nullable for [MeterHistoryUpdate] to allow for reinstating a previously removed meter. Currently in redlined v5.1, this data item is optional and non nullable. |  | Implemented |  | Interim Release 1 |  | Meter Removal changed to nullable, block conditionality updated | Missing/incorrect validation rule | Metering Changes | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-232 |  | DI-160 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-160 on the interface catalogue DCC Service Flag validation rules are specified in IF-025, but DCC Service Flag is not received in this interface. Needs removing. |  | Implemented |  | Interim Release 1 |  | not needed rules removed. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-233 |  | DI-161 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 – IF-025, where the event type is [ConsentGranularity] Error Code - REG1019 - Consent EffectiveFrom Date [DI-018] must be within Suppliers period of ownership Test Condition - Consent Granularity EffectiveFromDate [DI-018} must be < [Reg.CurrentSupplierEndDate] if exists Should this be <= as it could be on the end date? |  | Implemented |  | Interim Release 1 |  | Updated to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-234 |  | DI-162 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Registration Services Requirement MHHS-BR-RS-021 should be amended to: Registration Service must, where more than one Metering Service appointment request is received from the same Supplier for the same MPAN CSS Registration Request ID, and for the same date, take the last received Metering Service appointment (based on the Sender timestamp) as containing the correct information. Any earlier appointments should be lapsed. To allow multiple queued service appointments for the same registration will be overly complex to design, code and test, and is likely to cause confusion and issues in live operation. It is much simpler and cleaner to only allow one queued service appointment at a time, per registration. This would still allow the Supplier to replace a queued appointment that's incorrect. The Supplier could submit further changes once the first change has completed, if there is a genuine case of multiple changes to SP in a short period of time. It would not impact on CoS. Our proposal is to allow one pending queued appointment per registration, so could have a queued appoint on current registration AND queued appointment on CoS registration at the same time. |  | Implemented |  | Interim Release 1 |  | Updated MHHS-BR-RS-021 to refer to CSS Registration Request ID. Added REG1089 - Subsequent appointment received as an error code in the interface spec | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-235 |  | DI-63 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Original wording:- In the business process diagram for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 Update required:- Please close this design issue as CSS0700 is the correct reference for update of status. |  | Closed |  |  |  | DUPLICATE OF MHHS-DIN-63 | No Change
MHHS-DIN-236 |  | DI-163 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, 02-DIP-COMMON - R0 response - DI-980 Response Message has been updated in Swaggerhub to be an array, but this is not clarified in Interface Spec. DI-979 Response Code should not be an array. |  | Implemented |  | Interim Release 1 |  | Added note in Introduction section to confirm that DI-980 can be an array Agreed DI-979 Response Code is not an array | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-237 |  | DI-164 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-034 S0 DI-999 Event Code option of [DSAppSPRepsonse] is misspelt. This is also misspelt in Swaggerhub. This could cause differences between systems and should be corrected to [DSAppSPResponse] |  | Implemented |  | Interim Release 1 |  | Updated typo in IF-034 DI-999. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-238 |  | DI-165 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation on MS/DS EFD being within permitted advanced period. This is covered under migration document but not implemented as a validation rule for IF-031. MHHS-DEL961 Migration Design Document section 6.1.1: For the purposes of the CoA Migration process, the below business rules should be followed by Suppliers regarding the lead time between the submission date of the IF-031 and the requested effective from date of the Migration. a. An effective from date from Same Day +1 up to a maximum of 28 calendar days (inclusive of the 28th day) in the future is permissible. |  | Implemented |  | Interim Release 1 |  | 28 Day in advance rule added to if-031 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-239 |  | DI-166 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Requirement MHHS-BR-RS-134 states MPRS must automatically de-appoint the MS & DS when the Market Segment Indicator changes to NO. Is this the intended design? |  | Implemented |  | Interim Release 1 |  | Removed reference to Market Segment Indicator from the requirement MHHS-BR-RS-134. | Requirement correction | MPAN Ownership | Market Segment | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-240 |  | DI-167 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Current validation on IF-031 Rule REG1037 will mean MPRS will lapse any appointment where the system date is greater than appointment EFD + 2 working days. This means if a SEG change fails, and the supplier tries to resubmit the SEG change, with EFD more than 2 working days in the past, MPRS will immediately lapse the appointment. If there is a need to allow retrospective SEG changes, more than 2 working days after EFD, then the wording will need to be amended to apply to max(EFD+2 working days, MPRS system date on receipt of IF-034 + 2 working days) |  | Implemented |  | Interim Release 1 |  | Introduction of Lapsed Response Codes and Rules in IF-035 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-241 | RS |  | 2023-02-01 | C&C | 3430 | Graham King | Software Provider | Routing rules via the PUB-018 | IF/PUB-018 message with event codes [AddressChg] and [DUOSTariffIDChg]. According to Interface Catalogue routing rules, these events are not communicated to the LDSO role via the PUB-018. We assume that the assumption here is that because these data items are mastered by the LDSO that all internal LDSO systems share this data. This is unlikely to be the case. DUoS billing systems co-exist alongside other LDSO management software and are often supplied by different vendors. They do not and cannot share data sets. Given this real-world separation, would it be possible to make the PUB-018 message available to LDSO in the list of Secondary Routing paths? The alternative would mean developing communication channels between disparate systems, from potentially different software vendors in order to pass information from one to the other. |  | Closed |  |  |  | Closed - Linked to expected LDSO CR26 on DIP Message Optionality - Update as part of wider CR review | No Change | [7 empty] | 2023-07-14
MHHS-DIN-242 |  |  | 2023-04-04 | ESG | 3713 | Patricia Parker | Software Provider |  | How will the Metering Service be kept informed of who the currently appointed Data Service are? On BP003 is shows the Metering Service being a recipient of the PUB_036 when a DS appointment becomes effective, however looking at the routing rules in DES138 it does not show ‘MSSC’ or ‘MSAC’ as being recipients? |  | Closed |  |  |  | Close - changes to Secondary routing make this DIN Moot - Ref DIN-268 | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-243 |  |  | 2023-04-05 | Change Request | N/A | Sean Cooper | Programme | CR-015 E7/E10 Off Peak Consumption Solution | CR015 - Differential Settlement for E7 / E10 Meters for Smart Opt-out customers | CR015 | Implemented |  | Interim Release 3 | 2023-07-12 | Changes as agreed at DRG and slides circulated. Updated Method 2 and Method 7 within the SDS method statement (METH001). BR-DS-168 & BR-DS-169 added to BRS001. BR-SU-163, BR-SU-164 & BR-SU165 added to BRS004. BP004 text box amended. Creation of x2 New Data Catalogue Items​ OPD Day​ & OPD Proportion​. Changes to IF-024​ Addition of new Event Code [SN-OffPeakDec]​ & Addition of new B-Block BXXX Off-Peak Declaration​ | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue METH001 BRS001 BRS004 BP004 |  |  |  | CR15 | 2023-06-16
MHHS-DIN-244 |  |  | 2023-04-04 | British Gas | 3874 | Neil Strange | Supplier |  | D0275: Until v0.3 of DES196 was released our understanding was that the D0275 would be retained and it’ use was optional. We are feeding this back on the D-025 consultation but don’t want to lose sight of this. Its removal will impact our billing systems and substantially drive up implementation costs. The baselined IF-021 also does not handle the clock change |  | Closed |  |  |  | Alignment with D0275 D0275 is not part of of the baseline design requirements. If you require this, it is by mutual agreement between parties. NO change required, only clarification. | No Change
MHHS-DIN-245 |  |  | 2023-04-01 | Avanade/ Design Team |  | Grant Sutcliffe | Software Provider | Transaction ID and Correlation ID increase field length to 60 | Transaction Id Could the length specification of the TransactionId be increased to be a max length of 60. The need for this is to cater for a 16 character length hex value (increasing from current length of 6 characters]. This would ensure that we achieve uniqueness. It will also provide headroom for any length increase in other Transaction Id constituents, such as Role. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: T-041-1234567890123-SUP-20230220-619C1F6967838002 [Length = 50] Example from DES138 spreadsheet: T-006-1234567890123-SUP-20220401-1234CC [Length = 40] Correlation Id Could CorrelationId length also be increased to 60 max length of 60 - for the same reason. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: CI-BP-011-20230222-619E0BD1D1FD9000 [Length = 35] Example from DES138 spreadsheet: CI-BP-011-20230222-1234567890123 [Length = 32] |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated DIP Transaction ID and DIP Correlation ID to String 60 in Interim Release 1. The examples have been updated to reflected MHHSP-DES138-Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-246 |  |  | 2023-04-12 | Change Request |  |  | DCUSA | CR-019 Replacement of D0242 D0315 for MHHS | CR019 - Replacement of D0242 D0315 for MHHS | CR019 | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors) and receivers (suppliers) of the flows has identified the desired flow content and now wish to bring this back to the program to ensure that it can be delivered in readiness for migration. REP-900 and REP-901 added to reporting catalogue. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the supercustomer data from settlement (REP-002/002A). There will be removal of certain data items used in the current process and addition of new data items, making population of the D0242 ‘Supercustomer DUoS Daily Statement’/D0315 ‘Embedded Network Supercustomer DUoS Daily Statement’ impossible in their current format for migrated customers. The “MHHS Design: Reporting and Transition Sub Group” identified the need for a new DIP flow to replace the D0242/D0315 last summer but noted that these flows are under DCUSA ownership and so passed the development of the flow content to DCUSA. More information including the proposed Interface can be found on the collaboration base under CR019 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-247 |  | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Update to the Core Design Interface Catalogue (MHHSP-DES138) is required to include the addition of IF-003 |  | Closed |  |  |  | Closed captured under DIN-434 as part of migration update review IF-003 defined as part of Migration baseline The structure of the IF-003 will be updated to include ‘Incoming Supplier Details.’ The two new data items within the ‘Incoming Supplier Details’ will be: RevMig Incoming Supplier MPID RevMig Incoming Supplier Effective From Date Business Rules: In the case of Smart Meters undergoing Reverse Migration only, the Registration Service will populate the ‘Incoming Supplier Details’ as part of the IF-003 which is sent to the outgoing MS (via the DIP). This is so the outgoing MS can correctly route the Skeleton D0150 to the new Supplier (which in turn enables the new Supplier to generate a D0367). If the D0205 is not sent to the Registration Service before the IF-003 is issued, the data fields used to confirm the identity of the DC and MOP will be blank; no default values will be populated. In this case, the DC and MOP will need to contact the Supplier to initiate a manual transfer of data. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-248 |  | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Updates to the ISD Entities document (EDI021, v5.0) |  | Closed |  |  |  | To be picked up as part of Migration IA - - new DIN will be raised as required. |  |  |  | EDI021 |  |  |  |  | 2023-07-14
MHHS-DIN-249 |  | Migration Design | 2023-03-27 | Migration Design |  | Matthew Breen | Programme |  | Discussion around the use of BST/UTC during Migration |  | Closed |  |  |  | DIN is not specific enough. | [8 empty] | 2023-07-14
MHHS-DIN-250 |  |  | 2023-04-06 | Design Team | 3764 | Steve Weston | Programme | Participant ID 10 digit number | This is related to ticket 3764, to update the Interface Specification to ensure the Participant ID is clearly defined as a 10 digit number [0-9] only, and the examples in the Interface Specification align to this, including where this is used as part of the sender unique reference and the examples shows 11 digits, not 10 digits for Participant ID. |  | Implemented |  | Interim Release 2 | 2023-06-23 | In E2E001 doc Section 4.2.3.2 Section 4.4.4.2 example code for Sender unique Ref and in Transaction ID Section 4.5.5.3 as above DES138 doc Data Catalogue tab: DI-990 example and DI995 Example DIP common tabl DI995 example and the example JSON block (the above easy to change) ALL the IF tabs the JSON block example the Sender Unique Ref contains Participant ID and in every example its longer than 10. JSON/YAML Files: Update JSON examples where Sender Unique Ref and Transaction ID contain a Participant ID example longer than 10. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 Solution Architecture MHHSP-DES138-Interface Catalogue JSON/YAML files |  |  |  |  | 2023-06-16
MHHS-DIN-251 |  |  | 2023-04-06 | Design Team | 3860 | Steve Weston | Programme | IF-041 Population | This is related to ticket 3860, to update the Interface Specification to provide more clarity / notes on the optionality of B064 and B065 blocks in the IF-041 interface. This is in relation to notes / detail about which blocks are mandatory (from a contractual perspective) versus what should be included in the message if the data exists. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updates the notes section of IF-041 in order to provide guidance on the minimum population of B064/B065 blocks. This clarifies "When exchanging readings between parties the design assumes that in the most part this will be the Cumulative Register Reading (Block B064). However, at participants request this message also allows for the exchange of Configurable Register Readings (B065) either alongside a Cumulative Reading or in isolation. For the avoidance of doubt the message must contain at least one B064 record and /or one (or more) B065 records [depending on the number of configurable registers], in order to be considered valid. " | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-252 |  |  | 2023-04-06 | Centrica | 3661 | Neil Strange |  |  | We believe there is a Design Gap at Change of Agent and Change of Supplier for Smart Meters which also impacts Migration. Neither the Registration Service, Metering Service nor Data Service will know how the registers are set up and specifically which are active. Consequently the Data Service will not know which registers to send on the IF-041, nor will there be able to calculate consumption correctly without knowing the register set up. The interface catalogue for IF-041 states in respect to this “B065 Block Below Repeated for each set of Configured Register(s) for each Meter” – we do not believe there is a way to give the DS this information. The supplier will set up the smart meter configuration to enable the registers to capture the usage for certain time periods. There is currently no way for the supplier to inform the DS which registers are active at what time of the day - the DS cannot accurately calculate the consumption breakdown based on the reads when there are multiple registers configured. |  | Closed |  |  |  | DIN closed, Design Team to send email recommending for a CR to be raised. | [8 empty] | 2023-07-14
MHHS-DIN-253 |  |  | 2023-04-12 | British Gas | 3769 | David Hipwell | Large Supplier | Volumetrics | The latest E2E Functional and Non-Functional Requirements MHHS-E2E Requirements V3 which went to V3 on 16/02/2023 appears to focus on message counts and response times. For example:- During transition all meter points (ca. 31M) will be transition between the old and new services. Therefore assuming a linear migration over the year this would result in the load below, hence services shall be capable of processing the following volumes: - average daily volume of 680,000 - peak daily volume of 2.4M 5.0M - annual volume of 248M 500M Analysis of the flows needs to be categorised across all impacted market participant roles including the DIP. Only then will it have meaning for all parties. The calculation needs to take account of the migration period using the MHHS migration volumes according to date (including REVERSE migration). These should be in both message counts and also sizing (e.g. Gb). And include for a BAU day and also migration days. Whilst some calculations can use the total number of MPANs, to be useful these need show also at perhaps for a million MPANs in each role. Only then will all parties be working on a single set of figures. A line in the sand. The NFRs that exist appear to have moved away from any form of technical calculation towards business process figures. But these figures need to go as an input into technical sizing’s, and should have done for DIP – can these be produced and published ? |  | Initial Assessment/Updating | 2023-09-13 | Interim Release 5 | 2023-09-20 | Volumetrics analysis was presented to DRG on 13th September with some minor comments (see DRG meeting minutes). Updated volumetrics document will be issued as part of IR5. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-254 |  |  | 2023-04-17 | Siemens | 3044 | Tony Mason | Metering Service | Update of Consent, DPI, etc. | this does surprise me and doesn’t seem to correspond to the routing rules in the Interface Specification. A proposed Data Service is not included in the routing tables for the receipt of a PUB-018, for example. I would therefore expect that if a change to DPI occurs between PUB-033 and PUB-036 the proposed Data Service could only be notified on a revised PUB-033 with the Appointment Scenario set to whatever the original scenario was set to – “SEG”, “CSP”, or “COS”. |  | Closed |  |  |  | Ref notes on the maintenance of these data items in the Regi Info Section of the I/F document. Prospective SPs are not notified of changes to these data items during their prospective period. If these Data items change then the supplier should re-evaluate the SP they have proposed and change the appointments as required. If an SP takes on a supply with different elements/factors to those suggested by the supplier at appointment this is a contractual issue between the SP and the Supplier. | [8 empty] | 2023-06-16
MHHS-DIN-255 |  |  | 2023-04-17 | Elexon | 3983 | Kate Goodman | Testing | Consumption on De-Energised MPAN (IF-013/IF-014) | ConsumptionOnDeEnergised is an Event Code mentioned in the list of data items but is not present in header where the routing info is held - needs to be added to header |  | Implemented |  | Interim Release 2 | 2023-06-23 | ConsumptiononDeEnergised event moved from IF-013 to IF-014 and added in routing rules. See also DIN332 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-256 |  |  | 2023-04-17 | Elexon | 4169 | Kate Goodman | Testing | IF-014 Block B067 | DI-015 is mentioned in the header wrt routing but is not present in the message itself. It either needs to be removed from header or added into message. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Block B067 added to IF-014 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-257 |  |  | 2023-04-17 | Elexon | 4172 | Kate Goodman | Testing | B053 repeating block | B051 is a block which repeats for each combination of Load Shape Criteria (denoted with single chevron to show repeat). B053 is another repeating block which is denoted by two chevrons, implying it is nested below B051. But in fact it also repeats for each combination of Load Shape Criteria. Should this just have a single chevron or is there further information that needs to be added to make its double chevron make sense? |  | Closed |  |  |  | No change required as there will be multiple B053 in each B051 block. | No Change |  |  | none
MHHS-DIN-258 |  |  | 2023-04-19 | ENWL |  | Paul Band | Network Operator | LDSO use of DIP vs internal for Specific messages | There are a number of requirements in the MHHS-BRS005-LDSO document which state that we must obtain various registration data via the DIP and maintain records accordingly such as: MHHS-BR-LD-001-005, MHHS-BR-LD-024, MHHS-BR-LD-030 and MHHS-BR-LD-034 Extrapolating these into requirements for our own systems suggests that we should build databases/tables to store this data and maintain it The requirement is placed upon us as a party under the assertion that all settlement related data should be exchanged between services and parties via the DIP. However LDSO’s are unique in that their data exchange for their party type is split and is typically split by system under these party types. As a consequence we already communicate directly with MPRS as it is already part of our system architecture as a paid for and created service by LDSO’s. |  | Closed |  |  |  | CR26 has been raised to covere this LDSOs have been advised to raise a Programme Change Request. Discussion at the DRG of the 27/4/23 did not agree on the development of a New Design Principle, A further workshop with LDSOs needs to take place to discuss alternate options and confirm agreement amoungst all DNOs & IDNO on the receipt of publication | [8 empty] | 2023-07-14
MHHS-DIN-259 |  |  | 2023-04-20 | ESG | 3756 | Patricia Parker | Software Provider | BP003C correction | On BP003C under the CoR section there is a note which states that the readings that pass validation should have Meter Reading Status (J0047) set to ‘T’ and when it has failed set it to ‘F’. However as per the REC the group which houses the J0047 group (032 – screenshot below) should only be present where the Meter Reading Flag (J0045) is set to ‘F’. I have checked DES196 and cannot see that the conditionality for that group is changing in the D0010 therefore I can only assume that the note on the process map is incorrect, and it should be talking about the J0045 value instead. Please can you confirm? |  | Implemented |  | Interim Release 2 | 2023-06-23 | Modification to Note on process to refer to "Meter Reading Flag (J0045)", modify flow label to step230 to "(Read Flag = "T")" Modification to the process note to advise the J0047 would not be present if the meter reading flag (J0045) is set to "T". It will only be present in case the J0045 is set to "F". | Process Model correction | Metering Changes |  | MHHSP-BP003C-Transfer of Reads |  |  |  |  | 2023-06-16
MHHS-DIN-260 |  |  | 2023-04-20 | CGI | 4167 | Dave Webster | Software Provider |  | Swagger definition does not match DES-138 in version 1.0 or 1.1. |  | Closed |  |  |  | No specific detail provided, however comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1, therefore closed
MHHS-DIN-261 |  |  | 2023-04-20 | Utiliteam | 4245 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. Configurable Register Reading Date/Time is missing. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue JSON/YAML Files |  |  |  |  | 2023-06-16
MHHS-DIN-262 |  |  | 2023-04-20 | Utiliteam | 4214 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. B070 for IF-031 is wrong. It contains the word DIP in the Swagger, which is not included in DES-138. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files |  |  |  |  | 2023-06-16
MHHS-DIN-263 |  |  | 2023-04-21 | CGI | 4203 | Dave Webster | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. DI-122-Profile-Class is defined as an integer, but in DES138 it is defined as a string length 2. Needs to be updated in the Swagger. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Swagger and Data Catalogue aligned to String 2 for DI-122 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files |  |  |  |  | 2023-06-16
MHHS-DIN-264 |  |  | 2023-04-24 | Elexon | 3946 | Rashmi Radhakrishnan | Central Body | Update to CCC Method Statement | One of my colleague pointed out a typo in the CCC method statement attached, and I would like to draw your attention to it and requesting to make necessary amendments. The CCCID starting from 100 to 107 has Market Segment Indicator as “U” and Connection Type Indicator shown as “W”. We think that, for these line items the Connection Type Indictor need be corrected to “U”. For reference please see below picture and this also aligns with ISD entity spec v5.0 (M2 entity). CCC ID Market Segment Indicator Measurement Quantity Consumption Component Indicator Connection Type Indicator 100 U AI C W 101 U AI L W 102 U AE C W 103 U AE L W 104 U AI C W 105 U AI L W 106 U AE C W 107 U AE L W All 'W's' should be 'U's') |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Method Statements (MDS & VAS) will be updated for "W" to be replaced by "U"within ISD Table - MHHS Consumption Component Class. Please note: ISD entity M5 file has already been updates to reflect the fact that unmetered supplies have a connection type of "U". | Design Ambiguous | Supporting Docs | Method Statement | MDS Method Statement VAS Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-265 |  |  | 2023-04-25 | Elexon | 4128 | Rashmi Radhakrishnan | Central Body | Validity of Settlement Period quality indicator data set | ISD entity M5 has a filed Settlement Period quality indicator. Is this the complete valid data set for the field Settlement Period quality indicator? I took this below list from interface catalogue v5.0. A = Actual, E= Estimate (UMS Only) A1,A2,A3, AAE1,AAE2,AAE3,EAE1,EAE2,EAE3 (ADV Only) E0 --> E9 = Estimation Method 1 - 9 ZE = De-Energised ZE1--> ZE3 = Zero Estimation Method 1 -3 but the Advanced Data Service Estimation Method Statement has data flags EA1 till EA13 which is not mentioned in the above list. Also, the ISD entity spec M5 example below shows a different data item that is not in the list at all for Unmetered(104 &105). Is this a mistake? |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Interface document will be updated with the full list of settlement period qulity indicators. | Design Ambiguous | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-266 |  |  | 2023-04-26 | ESG | 3899/ 925 | Patricia Parker | Software Provider |  | If the D0300 process is not changing then we believe that DES196 is incorrect and should show added routes to allow the Supplier to send a D0300 to the Data Service Matt M has confirmed - We are working through the exchange of CoS readings as the code drafting has raised some questions about the extent to which the SDS is involved in the D0300 process. For smart meters, the SDS will not have any use for the billing register readings so D0300 process should not apply, or at most could only be missing the total cumulative. However, it likely will still be required for traditional meters. On that basis, I think we can acknowledge that the D0300 will be retained and SVs created for Supplier to SDS for traditional meters. The process for smart meters is being discussed internally as the SDS does not retrieve tariff register readings. There will be an updated version of DES196 issued in the next few weeks to reflect feedback from the DTN flow part 2 consultation issued in late March which will reflect the retention of the D0300. |  | Closed |  |  |  | Email comms sent to Patricia confirming the D0300 is a Supplier to Supplier flow. Therefore should there be a need to send readings to the DS, this would be done via a D0010/IF-041 with the correct data flags set in both. Based on this there is no requirement to send D0300 to the DS. Matt M confirmed when finalising DES196 he confirmed this in his comment response to ESG. The MSAG Consequential Change - Switch Meter Read Exceptions v1.0 22.06.23 provides a more comprehensive explanation of the MSAG conclusions. No change required to DES196 | Design Ambiguous | Supporting Docs | Method Statement | MHHSP-DES196- D-Flow and Interface Mapping |  |  |  |  | 2023-07-14
MHHS-DIN-267 |  |  | 2023-05-02 | ESG | 4385 | Patricia Parker | Software Provider | RegX Validation Issue | RegExpression on the DI-148-Annual-Consumption use of DT-016-Decimal-9-3 in the 1.1 swagger spec. This needs to be updated to align with DES-138 example of 123456789.123. Regex should be ^-?[0-9]\d{8}(\.\d{3})?$ instead of ^-?[0-9]\d{7}(\.\d{3})?$ |  | Implemented |  | Interim Release 2 | 2023-06-23 | Swagger v1.2 has been updated accordingly | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files |  |  |  |  | 2023-06-16
MHHS-DIN-268 |  |  | 2023-05-03 | SRO Design |  | Sean Cooper | SI Design | Secondary Routing | It was always the intention to revisit and revise all of the Secondary Routing configuration as part of DIP Detailed Design. Completion of this exercise has also resulted in some changes to other routing parameters. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Following discussion with Avanade the Secondary routing short codes have been simplified and the routing of each IF revisited based on these revised short codes. These are shown highlighted in BLUE in the routing section of each of the individual IF pages. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-269 |  |  | 2023-05-03 | St Clements | 4424 | Anna Davis | Software Provider | Swagger Alignment to DES-138 | We have also realised that there are a large number of discrepancies for each interface between the data item name in Swagger vs the YAML name in the Interface Catalogue Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated inconsistencies in the Interface 01-Data Catalogue and Swagger. Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-270 |  |  | 2023-05-05 | SRO Design | 4557 | Rob Golding | SI Design | Correlation ID | Provide further clarity on how Correlation ID's work. This will impact numerous artefacts including DES-138 and E2E001 |  | Implemented |  | Interim Release 2 | 2023-06-23 | DES-138 Interfaces updated to reflect correct 'COPY' property on IF routing tables. updated IF-008, 16, 20, 26, 28, 37, 39 and 50 for this DIN. Added *New to IF-020 showing a new correlation ID is needed to be created for these events, others events needed a COPY of the correlation ID. IF-050 had “No” added to show that a Correlation ID is not required. Updated the E2E001 design document with a more detailed worked example in section 5.4 that details how and where the Correlation ID is populated. | Design Ambiguous | Supporting Docs |  | MHHSP-DES138-Interface Catalogue. E2E001. |  |  |  |  | 2023-06-16
MHHS-DIN-271 |  |  | 2023-05-10 | ESG | 4541 | Patricia Parker | Software Provider | Swagger Alignment to DES-138 | S0 and S1 is Mandatory in DES-138 v5.1.1, but is not marked as mandatory in the Swagger 1.1. Swagger needs to be updated to align with DES-138. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Swagger 1.2 updated so all SO and S1 blocks are mandatory as per DES-138 | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-272 |  |  | 2023-05-10 | SRO Design | 4656 | Rob Golding | SI Design |  | Required to DIP Channel Publication (v1.2 of the swagger) that will allow DCPs to register webhooks on behalf of their clients |  | Closed |  |  |  | Duplicate of DIN-375
MHHS-DIN-273 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | New MSN Data Type | MHHS Data Type (DT-029) - for Meter ID / Serial number for DI-053, DI-056 and DI-060 added to DES138 01-Data Catalogue, Swagger updated. |  | Implemented |  | Interim Release 2 | 2023-06-23 | New Data Type created in Swagger v1.2 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-274 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | Missing YAML in DES-138 - DI-073, DI-074, DI-080, DI-111, DI-112, DI-190-194, DI-300, DI-021, DI-022, DI-060, DI-076 |  | Implemented |  | Interim Release 2 | 2023-06-23 | Missing YAML names for Data Items confirmed and added to 01 - Data Catalogue Note:All DI's upsated except DI-076 has not required a changed. Other DI chnages not listed are picked up as part of DIN261 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-275 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | DI-093 / DI-120 - Data length 2,000 not 200. |  | Implemented |  | Interim Release 2 | 2023-06-23 | All additional info data items set to len 2000 in Swagger v1.2, DES138 DI-093/120 length updated in 01-Data Catalogue | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-276 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Classifications | MHHS Data Classification - ensure all columns are populated for Public and Restricted ie, MPAN & Address (removall all NULLS). |  | Implemented |  | Interim Release 2 | 2023-06-23 | Data Classifications added in v5.2.1 where previously there was no entry ( Column I in the Data Catalogue ) | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-277 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Owners in Data Catalouge | MHHS Data Owner - where there are NULL's, this should be updated so all columns provide an owner, mark as N/A (remove all NULLS). |  | Implemented |  | Interim Release 2 | 2023-06-23 | Metering Service added as Authoritative Source and MHHS Owner in v5.2.1 of DES138 Data Catalogue for DI-190 to DI-195. Previously there was no entry. | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-278 |  |  | 2023-05-10 | SRO Design | 4590 | Rob Golding | SI Design | Addition of indicator for each IF within DES138 | Please can DES138 Interfaces spreadsheet be updated to provide an indicator against each interface (or is it interface & event code) as to whether it can be opted in/out by a recipient. |  | Initial Assessment/Updating | Pending CR-29 approval | Interim Release 6 | 2023-10-18 | Design Team to add optionality matrix to DES138 | Design Ambiguous |  | Method Statement | [5 empty] | 2023-07-14
MHHS-DIN-279 |  |  | 2023-05-12 | ESG | 4484 | Patricia Parker | Software Provider | Event Code clarifiction for DS when sending back validated customer read on PUB-041 | The BP005 – Data Processing – Process map shows that when a Customer Own Read has been sent to the Data Service from the Supplier in the IF-041, EventCode = ReadingCoR, the Data Service will perform reading validation and issue the PUB-041 back to the Supplier, in the Read Sharing column of the process map. When the Data Service send back the validated customer own read in the PUB-041, what eventcode will they use and where can I find this documented? The previous response says “There is no IF-041 response, check consumption is as expected in PUB-021” is this correct for Customer Own Reads on Smart meters? The map shows otherwise so please can you confirm if the answer or map is correct and if the map is correct, provide information on what event code will be used. |  | Closed |  |  |  | This is a query not a DIN. Previous response provided is correct .... There is no IF-041 response, check consumption is as expected in PUB-021” | [8 empty] | 2023-07-14
MHHS-DIN-280 |  |  | 2023-05-12 | ESG | 4552 | Patricia Parker | Software Provider |  | DES196 lists the D0386 (Manage Metering Points) as ‘not impacted’ owned by the REC however BP010 shows that the method of maintaining Related MPANs is via the IF_019 / PUB_020 process. Can you confirm whether the D0386 is going to be removed post- MHHS. If not, could you please clarify what process a Supplier should follow post- MHHS. |  | Closed |  |  |  | D0386 will not be used post migration to MHHS Regime. Management of MPAN relationships will be under taken using IF-019/IF-020 | [8 empty] | 2023-07-14
MHHS-DIN-281 |  | DI-172 | 2023-05-12 | St Clements | 4446 | Madison Layton | Software Provider | BP003 IF-35 flow | MHHS-BR-RS-053 for the incumbent MS to be notified on If-035 DSAppAccepted where meter is advanced or traditional is missing from BP003 business process diagram and steps. Also updates to BP003 and BPD003 forward migration for consistency |  | Implemented |  | Interim Release 2 | 2023-06-23 | IF-35 flow from step 85 (if accepted where meter is advanced or traditional to Meter Service (incumbent) and additional step 86 to receive appointment response to BP003, and added step 86 and BR-RS-053 ref and details to step 85 to the BPD003 | Process Model correction | Metering Changes |  | MHHSP-BP003-Change of Service - Data Service, BPD003 Forward Migration BP003 and BPD |  |  |  |  | 2023-06-16
MHHS-DIN-282 |  |  | 2023-05-16 | SIMS | 4821 | Martin Freeman | Software Provider | Status code removal | Status Code is included in the E2E001 design response body (4.4.4.2), when this is HTTP Response code and should be removed as this is defined in the callback response. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Removed from section 4.4.4.2 from the E2E001 design document as this is not required. This now aligns in Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture |  |  |  |  | 2023-06-16
MHHS-DIN-283 |  |  | 2023-05-16 | SIMS | 4826 | Martin Freeman | Software Provider | ID Capitalisation | ID should be capitalised in all places in the Swagger. |  | Implemented |  | Interim Release 2 | 2023-06-23 | All JSON names now have capitalised ID fields for Swagger 1.2. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-284 |  |  | 2023-05-16 | SIMS | 4828 | Martin Freeman | Software Provider | HTTP Response Code | HTTP Response code for success should be 201 in E2E001 as per Swagger. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to E2E001 design document in section 4.4.4.1, 4.5.5.1 and 5.3 to align with Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture |  |  |  |  | 2023-06-16
MHHS-DIN-285 |  |  | 2023-05-16 | Elexon |  | Rob Golding | SRO Design Team |  | Add replay / requeue API for Swagger 1.2 to align with existing E2E001 Design. Add additional information / clarity in the E2E001 for Interim Release 2 to align changes between design and Swagger. |  | Closed |  |  |  | Duplicate of DIN-374
MHHS-DIN-286 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Issue clarification to Participants through DRG that all ECS Reports will be issues via Pattern B. Update of ECS Report Catalouge to reflect this. |  | Closed |  |  |  | The ECS reports will be via Pattern A. No change is required to the ECS reports
MHHS-DIN-287 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team | Guidance notes for distribution of ECS reports | Create & Issue guidance document on the distribution of ECS Reports. To Contain : - overview of Pattern B Process - Guidance on population of IF-047 - Update of IF-047 Event Codes |  | Closed |  |  |  | Solution yet to be defined No longer required as pattern B will not be implemented for ECS reports | [8 empty] | 2023-07-14
MHHS-DIN-288 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Update of Swagger with ECS Reporting Structures |  | Closed |  |  |  | These interfaces are in place from Swagger 1.1. | [8 empty] | 2023-06-16
MHHS-DIN-289 |  |  | 2023-05-17 | SRO Design Team | 4994 | Rob Golding | SRO Design Team | Interfaces for consumption replay | IF-015 / IF-016 - updates to E2E001 to provide clarification on design pattern. Alignments between DES-138 & Swagger alongside this. |  | Implemented |  | Interim Release 2 | 2023-06-23 | E2E001 design updated (Section 5.1.7) to provide additional information / clarity on these interfaces in relation to Consumption Replay. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture |  |  |  |  | 2023-06-16
MHHS-DIN-290 |  |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Proposal to change all / subset of ECS Reports to Pattern B |  | Closed |  |  |  | Duplicate | No Change
MHHS-DIN-291 |  |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | As a result of DIN-290 -- Where should the reporting assets be hosted?? DIP solution specified, but what are the other options are availible. Final solution option to be ratified and documentation updated. |  | Closed |  |  |  | Not hosted as via Pattern A | No Change
MHHS-DIN-292 |  |  | 2023-05-17 | St Clements |  | Madison Layton | Software Provider | ISD Entity M17 | Change required to ISD Entity M17 to add in Market Segment into the table - otherwise it cannot be used to derive consent values which was its original purposes |  | Implemented |  | Interim Release 2 | 2023-06-23 | 1. Update Table name to "Consent Granularity Valid Combinations" 2. Added Market Segment as new table column 3. Update table to show all valid combinations | Process Model correction | Supporting Docs |  | MHHSP_EDI021_ISD_Entities |  |  |  |  | 2023-06-16
MHHS-DIN-293 |  |  | 2023-05-17 | Design Team |  | Paul Petitt | SRO Design Team |  | Retrospective DIN raised to ensure that any changes that are made in multiple downstream documents (for example CoCo, DIP Logical Design, DIP Physical Design & DIP Security Design) are reflected / updated in LDP assured documents to ensure e2e design / requirements alignment. This was agreed in a DRG Meeting in March 2023. |  | Implemented |  | Interim Release 1 |  | design changes to E2E001 End-to-End Solution covering points described in DIN details | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-294 |  |  | 2023-05-19 | ESG | 5030 | Luke Speakes | Software Provider | BP007 PUB009 flow | What I need to know is if the supplier will receive a PUB_009 with the Event code of [CSSDeRegistration] because nowhere on the BP007 process map does it show the supplier receiving the PUB_009 following a deactivation but on DES138 it shows the supplier as being a recipient of this event code. Step 95 (ringed below) shows the supplier as receiving the PUB_009 off the back of the Disconnection (event code [MPANDisconnection]) but then no where else on the process map does it have the supplier receiving a subsequent PUB_009 following the successful deactivation. Additional step required from step 130 (maybe 137?) to show both PUB-009 Mpan Disconnection and PUB-009 Deactivation going to supplier |  | Implemented |  | Interim Release 2 | 2023-06-23 | BP007 change : There is already a flow from Step 85 to Step 95 for PUB009 for disconnection (no change) But need to Add a new step (137) for Receive Deactivation in Supplier lane from Step 130 for PUB-009 MPan deactivation in BP007 And there is already a PUB-037 flow from step 145 to Supplier step 157 for confirmation (so no change there) Addition of step 137 to BPD007 | Process Model correction | Metering Changes | Disconnection | MHHSP-BP007-Disconnection, BPD007 |  |  |  |  | 2023-06-16
MHHS-DIN-295 |  |  | 2023-05-19 | SIMS | 4821 | Martin Freeman | Software Provider | L1/L2 Error Codes | Error code detail updates in DES-138 for Level 1 and Level 2 validation needs to be clarified |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updates made to Introduction Tab of DES138 in order to clarify Lev1 vs Lev2 error codes. Design is such that participants should expect error code(s) at either level. Further ammendments could be made following Avanade clarifications. | Data interface correction | Supporting Docs |  | DES138 Data interface Definition |  |  |  |  | 2023-06-16
MHHS-DIN-296 |  |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | It is envisioned that Configuration Management of ISD will largely follow the existing customs, practices and processes as are currently in place for managing MDD changes. However, DIN is required to formally confirm the Owner(s) and allowable update mechanisms (Standard or FastTrack) for each of the new ISD Entities outlined in the DIN. |  | Closed |  |  |  | This is a Code Drafting issue not a Design / DIN issue. Code drafting team will be covering ISD maintenance processes | [8 empty] | 2023-07-14
MHHS-DIN-297 |  |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | What Participants are recognised in the existing / new ISD Participant tables…. How does this link in with the parties recognised by the DIP (and assigned DIP Roles / IDs …. Or Not) …. In particular how are MDRs referenced in ISD? Does this reference need to identify the ‘type’ of MDR? Also, there is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 |  | Closed |  |  |  | These issues are covered in Release 3 updates (DIN372 & DIN 070) . ISD updated to confirm participants recorded in M16, a new table M18 "DIP Participant Roles" was added. | [8 empty] | 2023-07-14
MHHS-DIN-298 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Update to UMSDS method statement. | As I understand it, you are advising we should A flag the consumption data (even though it isn’t Actual), until the zero charge code D0388 UMS Inventory is received from the UMSO. Therefore - if we have an inventory, regardless of the energisation status of the MPAN, we always use an A Flag. But as you’ve stated, this means an IF-013 will be issued to us as UMSDS, because there is A data, against a De-Energised MPAN. If this is the design/requirement then it is understood – but I would like to call out that this should be detailed within the UMSDS method statement – so I think a DIN is needed to get this requirement added? |  | Implemented |  | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-299 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | IF-013 update to include UMSO recipient | Further to this (DIN-298), the cause of this IF-013 being issued can only be that the UMSO has not provided the UMSDS with the correct D0388 UMS Inventory to use. Therefore – the UMSO has a requirement to receive the IF-013 to tell them this. However, the Interface Catalogue has not designed that this will get sent to the UMSO. I think this is a Design Issue too, and also needs a DIN raising so that the IF-013 is provided to the UMSO. |  | Closed |  |  |  | No this is incorrect. UMSO is not involved with Consumption. If IF-021 submission is rejected this is an issue for the DS (incl. UMSDS) to address and Manage. Any issues regarding the metering onsite/energisation status need to be managed by the DS (incl UMSDS) with their appointing Supplier and Partner Metering Service. |  |  |  | DES138 |  |  |  |  | 2023-07-14
MHHS-DIN-300 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | You are advising a Load Shape will always require the E Flag. But as you say if the MPAN is de-energised, that MDS will reject the IF-021. Is this therefore your answer – that MDS will reject the IF-021, and there is nothing that can be done about that, so we just need to accept we will get those rejections? If so, this isn’t really a satisfactory process, to know rejections will be received in this scenario. Can you just confirm that the solution here is we just need to accept we will get these rejections to the IF-021, which we will then simply ignore? If that is the case – again a DIN needs to be raised to write this into the Design so the process is documented. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. See DIN 506 which has updated DES138 to show that IF-014 also contains warnings for MPANs with consumption on de-energised sites. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-301 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | the corrective action on this scenario (DIN-300) occurring will be if/when the UMSO provides the UMSDS with a D0388 UMS Inventory – then the UMSDS will stop using and submitting the Load Shape data. There does not seem to be a mechanism in the Design for the UMSO to be made aware of this issue that would be of their making, so again needs raising as a DIN please. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. See DIN 506 which has updated DES138 to show that IF-014 also contains warnings for MPANs on de-energised sites. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-302 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | I’ve pulled together the below table. This covers all the possible scenarios of the UMSDS either having or not having the D0388 UMS Inventory. Combined with whether that D0388 UMS Inventory has load associated data within it. Also combined with whether the MPAN is Energised or De-Energised. Here I’ve listed which Settlement Period Quality Indicator should be used, and where applicable, which Estimation Reason Code should be used. Should this be included in the UMSDS Method Statement and if so, are you happy with the below. In Green are steps we understand. In Red, these remain Unknown to us based on the Design and your answers given. In Orange, these are answered based on your guidance on your email of 28 April – but are not specified in the written Design. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-303 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.2.3 - Changes to Data formatting to align with Swagger / DES-138 |  | Implemented |  | Interim Release 1 |  |  | Technical corrrection | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-304 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.4.3 - Case Sensitivity - additional information added to provide clarity on approach |  | Implemented |  | Interim Release 1 |  |  | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-305 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 5.1.7 - Additional Detail required for IF-47 / ISD to provide clarity on approach / steps |  | Implemented |  | Interim Release 1 |  |  | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-306 |  |  | 2023-05-22 | Tym Huckin | 3992 | Tym Huckin | Consultancy | Clarification/examples for DI-101 for BST/UTC cross over period | Further clarity / worked examples for UTC Settlement Date (DI-101) for BST / UTC cross over period. |  | Closed |  |  |  | This is not a design change it is a Question/Clarification . | [8 empty] | 2023-07-14
MHHS-DIN-307 |  |  | 2023-05-22 | CGI | 5042 | Dave Webster | Software Provider |  | Status code incorrectly included in required, although not in Standard Response Body Type. This is in Swagger 1.2. |  | Closed |  |  |  | Duplicate of DIN-282
MHHS-DIN-308 |  |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | S0 Block required property | Add required property to all the S0 blocks in the interface definition |  | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger for all Interfaces to mark 3 fields in the S0 block as mandatory. | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-309 |  |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | Swagger Alignment to DES-138 | Define Transaction ID (DI-990) with no Min Length to align with DES-138. This is DT-014. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (DIP Transaction ID min length removed) | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-310 |  |  | 2023-05-23 | ELEXON | 5173 | Rob Golding | Central Body | Guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 | Guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 are to be applied (if at all), i.e. does the DIP need to consider the effective period and only accept messages on the production system when the message falls within this period? And if so what date within the message should be used as a check? Or the physical date/time of message receipt? Or doesn’t the DIP need to consider these dates at all and no check needs to be applied? |  | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | This DIN requires an internal workshop with the Design/Technical team. Holding statement to be added to DES138. Validation rules to be added | [8 empty] | 2023-07-14
MHHS-DIN-311 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-985 / DI987 both String 60. Swagger Min and Max Lengths aligned |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updates made to DES-138 for Length alignment to 60. Updates to Swagger to remove min length for DI-985 and DI-987. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-312 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-984 / DT-009 needs to be updated to be min 3 / max 5 length. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Sender Role - change on 01 Data Catalogue DI-984 as per description | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface |  |  |  |  | 2023-06-16
MHHS-DIN-313 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S1 - Sender Timestamp updated correctly (from sent timestamp) in Swagger to align with DES-138 |  | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (renamed to Sender Timestamp) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-314 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - Publication ID Min Length updated in Swagger 1.2 to be 6 to align with DES-138 (rather than 7) |  | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Publication ID Min Length now 7, not 6) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-315 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - DIP Correlation ID should have no min length to align with DES-138 (rather than min length of 1) |  | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (DIP Correlation ID has no min length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-316 |  |  | 2023-05-25 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, all DT-006 and DT-006N should have min length 10 & max length 10 to be consistent. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated DES-138 01-Data Catalogue to align Data Type and provide consistency to Swagger. Removed DI-095 which is no longer used. | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface |  |  |  |  | 2023-06-16
MHHS-DIN-317 |  |  | 2023-05-23 | St Clements |  | Sean Cooper | SRO Design | B9xx array references within Swagger to be updated within DES138 | Update DES138 IF document to include reference to the B9XX Array references held in Swagger |  | Initial Assessment/Updating |  | Interim Release 7 | 2024-01-19 | Solution yet to be defined | [8 empty] | 2023-07-14
MHHS-DIN-318 |  |  | 2023-05-23 | REC | 5049 | Jonny Moore | Consultancy | Addition of 'Effective from date' data items to RMP Status (regi) and MP Status in IF-050 | While completing the design phase for EES we noted that the following items with the IF-050 do not have an effective from date. - RMP Status (Registration) - MP Status These items currently have an effective from date held in EES and not including this in the IF-050 would have the effect of removing these items from EES. |  | Closed |  |  |  | REF DIN-508 | No Change | [7 empty] | 2023-07-14
MHHS-DIN-319 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S0 - EventCode to marked as required to align with DES-138 |  | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Event Code marked as required) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-320 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, S1 - Environment (DT-013) should have min length 3 & max length 10 to be consistent with values. |  | Implemented |  | Interim Release 2 | 2023-06-23 | 01-Data Catalogue DI-991 Environment Set Min to 3. However, string length is 10, so max length should be set to 10 | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface definition |  |  |  |  | 2023-06-16
MHHS-DIN-321 |  |  | 2023-05-23 | St Clements | N/A | Sean Cooper | SRO Design | B005 add to IF-036 | Consider adding B005 to IF-036 so that incoming SP knows who previous SP were |  | Implemented |  | Interim Release 3 | 2023-07-12 | Added B005 to IF-036 so that incoming SP knows who previous SP were. Updated block name to B005 - Incumbent/Outgoing Service Providers | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-322 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B002 - Incoming Supplier MPID - Swagger aligned to DES-138 for min / max lengths |  | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Incoming supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-323 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B003 - Ougoing Supplier MPID - Swagger aligned to DES-138 for min / max lengths |  | Implemented |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Outgoing supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-324 |  |  | 2023-05-24 | EDF | 4780 | Paul Saker | Supplier | NHHSP-BPM00C- Transfer of Reads on Change of Data Service process steps and messages clarification | NHHSP-BPM00C- Transfer of Reads on Change of Data Service details several process steps and messages related to obtaining and sharing register readings between the gaining and losing suppliers to agree a CoS, and to initiating the missing/disputed reads process defined in the Retail Energy Code where CoS reads are missing or need to be disputed/amended. However, it appears that there is no further detail defined within the Design Artefacts regarding how exactly these process steps would work, including amongst other things: • Timing/Operational Choreography – for example it is not clear exactly when losing and gaining suppliers would be expected to attempt to communicate with the meter, or the timescales for sending data obtained between suppliers. • Data to be included in messages – while BPM003C refers to the inclusion of ‘register readings’ in some of the messages it is not clear which registers should be included for smart meters and non-smart meters – for example whether that should just be the registers on a smart meter that the sending supplier uses for billing, or whether that should be all the 48 time of use registers stored on the smart meter. Additional input from Andrew Margan - Within the code workstream, we believe the Operational Choreography document needs to be updated to reflect SLAs. Without this, we can’t complete the Code drafting. If you disagree, we would appreciate an early heads up, so we don’t look disjointed in front of industry. |  | Closed |  |  |  | This is not an MHHS Design Issue. D300 / Agree Reading SLAs are defined and set by RECCO. We have replicated the existing 5 day window for capture / submission of a reading(s) all other D300 timescales still apply as per RECC process. Register Readings can only be provided on the D0010 - where this is required [for smart meters] it would replicate the current as is process defined in the current DC BSCP | [8 empty] | 2023-07-14
MHHS-DIN-325 |  |  | 2023-05-24 | CGI |  | Dave Webster | Software Provider | Status Code Missing from MsgBody | In the SubmitEvents StandardResponseBodyType object (SubmitEvents ¦ 1.2 ¦ MHHSPROGRAMME ¦ SwaggerHub), it states that “statusCode” is a required field. Yet its’ definition does not exist in the properties of the object. StandardResponseBodyType: type: object properties: transactionID: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-014-DIPTransactionID' senderUniqueReference : $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-995-SenderUniqueReference' correlationId: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-011-CorrelationID' sentTimestamp: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-003-DateTime' senderId : # the sender of this message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' recipientID : # indended (logical) recipient of the message, i.e sender of the original event message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' DIPConnectionProviderId : # physical recipient of the message (if different to recipient Id) $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' message: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-005-StatusErrorMessage' help: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-019-HelpText' serviceTicketURL: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-018-URL' required: - transactionId - sentTimestamp - senderId - recipientId - statusCode - message - help - serviceTicketURL |  | Implemented |  | Interim Release 2 | 2023-06-23 | This has now been updated in V1.2 of Swagger StatusCode Added to the ResponseBody. | Technical corrrection | Supporting Docs |  | JSON/YAML files
MHHS-DIN-326 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Changes required to DES-138 / interface catalogue given changes in Migration Design e.g. the addition of interface IF003 and potentially ISD. |  | Closed |  |  |  | Duplicate of 247 | No Change |  |  | None
MHHS-DIN-327 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | IF-005 User Guide | The IF005 User Guide explains how the IF005 should be populated. We have a request for clarification on whether the IF006 will be populated identically or if the Meter ID in the IF006 will reflect the Modified Meter Id in the IF005. Is IF-005 identical to IF-006, or is it with updated MTD's. |  | Implemented |  | Interim Release 2 | 2023-06-23 | IF-006 should be a facsimile of IF-005. In the case of change of MSN... MSN field will reference the (old) MSN and Modified MSN will be populated with new/revised MSN. All subsequent flows following the IF-006 will only reference the NEW/REVISED MSN. We further clarified this in a change to the Note(s) section on IF-006. | Data interface correction | Supporting Docs |  | DES138 |  |  |  |  | 2023-06-16
MHHS-DIN-328 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | Operational Choreography Update: Addition of SLA for RS end appointment data to the CSS | The operational choreography does not include an SLA for the RS to send appointment data to the CSS or the timings by which the CSS and DSP should deliver their roles within the process. These need to be added to the operational choreography for clarity, noting the interaction with CR018. | CR018 | Closed |  |  |  | RECCo confirmed closure of DIN following review of amendments to the Operational Choreography for CR018. ALL Updates between RS and CSS/DSP are existing interactions, covered by existig SLA's document in RECCO documentation. OPSC document was updated per Recco comment to highlight existing RECCO SLA in this area and to ensure primacy of the RECCO documented timings. | [8 empty] | 2023-07-14
MHHS-DIN-329 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Approach on a business rule where the ERDS does not send a MEM de appointment / appointment for an MHHS migration where the same MEM is being appointed under MHHS arrangements e.g. they have the same MPID. The expectation is that smart and advanced MEMs will use the M role code for the interaction with CSS so from their perspective there should be no change. |  | Closed |  |  |  | ERDS Interfaces are ouf of scope of MHHS. If a change to ERDS interface is required or efficiencies in its existing operation are possible to align with MHHS Design - this would be a consquential change. | No Change | [7 empty] | 2023-07-14
MHHS-DIN-330 |  |  | 2023-05-25 | Ovo Energy | 5225 | David Morley | Supplier | Long Term Vacant | BSCP504 section 4.15.3 stipulates the criteria via which suppliers can classify sites as Long Term Vacant (LTV). BSCP701 stipulates actions that SDS shall take if the supplier nominates that a site is LTV. However, the criteria that suppliers shall use for classifying LTVs in MHHS is missing. Can you please signpost where the new criteria will be located? |  | Closed |  |  |  | BSCP is responsible for revising the code specification, there are no changes to design specified. Code team will get in touch with the participant.
MHHS-DIN-331 |  |  | 2023-05-25 | MHHS | 4733 | Martin Freeman | Central Body | Secondary Routing | Secondary routing for IF-013 is specified as being conditional upon the value of DI-015. However, DI-015 (Connection Type Indicator) is a property of a repeating block, and there is no constraint in place to suggest that each element in the repeating block must have the same value for this (or any other) property, in which case multiple rules in the routing table could apply simultaneously. The routing table design seems to suggest that only a single rule should apply at a time and that routing should not be derived by blending multiple rules. If this is so, and a message is received where different elements in the B050 have a different Connection Type Indicator then there is no coherent way to implement this in conformance with the routing table. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Agree there was a routing contradiction for scenarios/periods where a different connection type was in effect. Interface notes section has been updated to direct the use of 'separate' IF-013 messages in such circumstances. Note also makes clear that repeating B050 blocks are acceptable where other elements (not Connection Type) of the CCC vary over the period to be defaulted. | Design Ambiguous | Supporting Docs | Default Consumption | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-332 |  |  | 2023-05-25 | MHHS | 4750 | Martin Freeman | Central Body | IF-013 Routing | In the routing table for IF-013 all rules are conditional upon S0.Eventcode == [ActivePowerDefaulted], which means that for IF-013 message where Eventcode == [ConsumptionOnDeEnergisedMPAN] there is no routing at all, which means when this message is sent to the DIP it will not be routed anywhere and will simply disappear. That's almost certainly an error. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Event code [ConsumptionReceivedonDeEnMPAN] has been moved from IF-013 to IF-014. The valid event code list and routing rules have now been updated for both interfaces to reflect the move. v1.2 of Swagger also updated to reflect this change Duplicate of DIN 255 | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-333 |  |  | 2023-05-25 | MHHS | 4760 | Martin Freeman | Central Body | Connection Type Required to Support Routing of IF-014 | All of the routing rules specified for IF-014 are conditional upon DI-015 (Connection Type Indicator). But IF-014 does not have any blocks with this property, which means this message won't get routed anywhere. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Block B067 - Connection Type Added to IF-014 in order to support routing requirements. Swagger v1.2 updated to reflect this change. (Duplicate of DIN256) | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-334 |  |  | 2023-05-25 | MHHS | 4766 | Martin Freeman | Central Body |  | The routing table for IF-018 specifies roles AMSC, UMSC, UMDC for Secondary routing. There are no such roles in either the DES138 nor the E2E001. |  | Closed |  |  |  | Secondary Routing Review/Changes have superceded this issue - Ref DIN-268
MHHS-DIN-335 |  |  | 2023-05-26 | British Gas/Engage Consulting | 4640 | Neil Strange/ Haz Elmamoum | Consultancy | Four questions on IF004 | IF/PUB-004 – DIP Common Blocks referencing MHHSP-DES138-Interface Catalogue v5.1.1 As a minimum this needs to be referenced in the supplier requirements MHHSP-BRS004-Supplier Overview and MHHSP-BRS002-Metering Service requirements, but to ensure parties get sight of this we would suggest it needs to be included in a business process map and have associated requirements. For IF-004 to be useful to participants DI-999 – Event Code needs to be elaborated e.g. 1- Installation 2- Removal; 3- Exchange; 4 - Found (Where installed by Gas supplier and Elec Supplier takes ownership) C/M/O rules for DI-192, DI-193 and DI-194 need to be explained in the notes – presumably driven by event code Available is spelled incorrectly (available) for DI-192 and DI-194 there are a couple of angles here – 1) ensuring wider awareness and 2) it seems there is a question mark on the governance here as it is odd a flow has been added but industry does not appear to have been sighted on it especially with no associated referencing in artefacts and no process map, so effectively no one has any idea how it is supposed to be used. Although it was formally agreed not to include and use bilaterally....from a Large Supplier Constituency perspective, my members are keen to ensure design clarity and how flows are to be used or not, regardless of their ad-hoc / bilateral nature. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Updated BP009 Change of Metering to include the "optional" sending of IF-004 from MS via DIP to Supplier, if changes to Comms Hub need to be notified. Included same updated to BPD009 to reflect new BP steps. Other comments have been addressed previously and are reflected in DES138 IF-004 | Process Model correction | Meter to Bank | IF-004 | BP009 Change oF Metering BPD009 Change of Metering |  |  |  |  | 2023-06-16
MHHS-DIN-336 |  |  | 2023-05-26 | MHHS |  | Rob Topley/ Zak Hussain | SI Design | Requirements clean up in iServer | Process Step No. BP Step ID Process Map wording Interface ID Sender Recipient/Service Traceability Requirement Traceability Method Statement iServer Requirement Name iServer Step name Issues Found BP01 170 BP01 - 170 Send Site Tech Details on Metering Service Request MHHS-RS-LD-012.1 #N/A LDSO170a Send Site Tech Details on Metering Service Request Missing (only on BPD and traceability matrix) BP01 175 BP01 - 175 Receive Site Technical Details D0215 LDSO Metering Services MHHS-RS-MS-037.1 #N/A MET175 Receive Site Technical Details Missing (only on BPD and traceability matrix) BP03B 95 BP03B - 95 Manage SP Appointment Amendment Request Response PUB-035 DIP Supplier MHHS-BR-SU-35.1 #N/A SUP095a - Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP03B 96 BP03B - 96 Manage SP Appointment Amendment Request Response PUB-035 DIP Data Services Metering Services MHHS-BR-DS-11.1 #N/A ESP96 – Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP05 315 BP05 - 315 Issue Reading Data MHHS-IF-041 Data Service DIP MHHS-BR-DS098.2 #N/A DAT315 – Issue Reading Data Missing (only on BPD and traceability matrix) BP05 340 BP05 - 340 Process Reading Data PUB-041 DIP Supplier MHHS-BR-SU047.1 #N/A SUP340 Process Reading Data Missing (only on BPD and traceability matrix) BP05 350 BP05 - 350 Process Reading Data PUB-041 DIP LDSO MHHS-BR-LD009.1 #N/A LDSO350 Process Reading Data Missing (only on BPD and traceability matrix) BP010D 1055 BP010D - 1055 Receive updated Legacy information PUB-026 DIP Central Settlements MHHS-BR-RD-018.1 #N/A ECS1055 Receive updated Legacy information Missing (only on BPD and traceability matrix) All these requirements don’t exist on any requirement catalogues, they’ve only ever been on a BPD document or the traceability matrix (which are essentially the same document). Also, the highlighted traceability has a typo and is on a requirements artefact but is wrong on both the BPD and traceability matrix. |  | Closed |  |  |  | Requirements have been found in BRS001, BRS004, BRS005, BRS014. Models have the correct steps identified. Unable to identify whats missing, checking with the originator. Confirmed with originator no further changes needed | No Change | Supporting Docs | Supporting Docs | BRS001, BRS004, BRS005, BRS014 |  |  |  |  | 2023-07-14
MHHS-DIN-337 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger alignment to DES-138 | R0 - Response Message Min length updated to align with DES-138 |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated R0 - Response in Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-338 |  |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier | BP003 to be updated to clearly show IF-036 going to both Import & Export supplier | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. BP003 to be updated to clearly show IF-036 going to both Import & Export supplier |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | BP003 from Step 255 relable "PUB-36" flow to Step 260 for the Supplier (prospective/incumbent) to state "PUB-036 for Import & Export Supplier". Change Also to be reflected in the BPM-003 for forward migration | Process Model correction | MPAN Ownership | Process Models | BP003 DEL964 BPM-003 forward migration |  |  |  |  | 2023-07-14
MHHS-DIN-339 |  |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier | IF-001 to be updated to be additionally sent to the Export supplier rather than just the import | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. IF-001 to be updated to be additionally sent to the Export supplier rather than just the import |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | See 338 as well, Assuming referring to IF031 not IF001, BP003 from step from step 030 new flow to Supplier (prospectice/incumbent) for PUB-031 for import & Export Supplier to new step Receive Initial DS Appointment request. Update BPD003 with new step. Also change to BP003 has to be reflected in BPM-003 for forward migration. | Process Model correction | MPAN Ownership | Process Models | BP003 BPD003 DEL964 BPM-003 forward migration |  |  |  |  | 2023-07-14
MHHS-DIN-340 |  |  | 2023-05-26 | UKPN | 4547 | Neal Medley | Network Operator | ELEX-REP-02/02A report | The reports ELEX-REP-02/02A will only contain aggregated data for A(General LLF Class Import and C (General LLF Class Export). The I/F021 can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/014 Rejected Consumption Data Submission and I/F MDS Defaults Applied to any I/F021 data to ensure you are not using rejected data or are missing I/F 021 data in respect of an MPAN. MDS Method Statement to be updated to reflect |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Updated the below test to Section D within MDS Method statement: 17.4 The I/F021 ‘UTC Settlement Period Consumption Data’ can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/F014 Rejected Consumption Data Submission and I/F ‘Notification of Defaulted UTC Settlement Period Consumption Data’ to any I/F021 data to ensure LDSO’s are not using rejected data or are missing I/F 021 data in respect of an MPAN. | Design Ambiguous | Supporting Docs | Method Statement | MDS Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-341 |  |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | MUM Event not required by MDS | For IF-018 the event [MUMIndicator] is routed to MDS and indicates metered/unmetered. This event is not required by MDS as they can infer this from the Market Segment (Advanced, Smart and Unmetered). DIN raised to remove the routing |  | Implemented |  | Interim Release 2 | 2023-06-23 | MDS Removed as Always Recipiant for Event [MUMIndicator] on IF-018 Routing rules | Data interface correction | Supporting Docs | IF-018 | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-342 |  |  | 2023-05-26 | UKPN | 5194 | Neal Medley | Network Operator | ELEX-REP-02/02A Consumption data clarification | The intent is that the daily volume on actuals or estimates are the sum of the appropriate consumption data. So when added together they should equal the summed Total of the Settlement Period data (Total Uncorrected Volume) barring any rounding errors. The data is given in MWh to six decimal places (i.e. to the nearest Watt hour). I assume DUoS billing only calculates to the nearest unit so would not expect any rounding errors to impact. The A flags are set out in the ELEX-REP-02/02A are the same as those set out in the CCC table in the VAS Method Statement which is also in the MDS Method Statement. I agree the list in the calculations only are missing the full list of SPQI that are deemed to be actuals as set out in the ELEX-REP-02/02A. DIN raised to correct the calculation |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Updated full list of actuals with the MDS Method Statement. The amended list added to the Method statement: A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6. | Method statement correction | Supporting Docs | Method Statement | MDS Method Statement |  |  |  |  | 2023-07-14
MHHS-DIN-343 |  |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | Routing rules table | The routing rules on the IF-037 sheet state that MDS will 'always' receive the DSDeApp event code, however the 'Always' column on the IF_LIST does not state Central Settlements for MHHSP-IF-037. IF list needs updating to reflect that the DSDeApp event always routes to MDS |  | Implemented |  | Interim Release 2 | 2023-06-23 | Decision taken to remove Recipiants (COLs G,H &I) from the IF_list - as just duplication of information contained within each of the IF spreadsheets. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-06-16
MHHS-DIN-344 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B005 Custom Block update Swagger to align with DES-138. Current Metering Service MPID Length removed. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138. Current Metering Service MPID Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-345 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B024 Custom Block update Swagger to align with DES-138. DUOS Min Length removed. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138. DUOS Min Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-346 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design |  | IF-001 - B032 Custom Block update DES-138 to align with Swagger. Update DI-122 (Profile Class) to Integer from String-2. |  | Closed |  |  |  | DI-122 remains as String 2 for Profile Class to support requirements for enumerations. | Data interface correction | Supporting Docs |  | None |  |  |  |  | 2023-06-16
MHHS-DIN-347 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B035 Custom Block - update Swagger to align with DES-138. Remove min length. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-348 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | IF002 correction | IF-002 - B074 Custom Block. Clarification on DI-091. DES-138 says this is 1 digit to the left of the decimal point. Swagger says 5 to 6. DES-138 to be updated to the correct value. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to be an Integer (1), Min of 1, Max of 1, example of 5. This now aligns with DES-138. | Data interface correction |  |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-349 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Correlation ID Issue IF-006 | Routing Rules in DES-138 do not always correctly identity where Correlation ID == Copy ie, it's missing for IF-005 / IF-006 so this needs to be updated correctly across all interfaces. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated IF-006/IF-008/IF-039/If-028/IF-026/IF-016 routing rules to show use of a "Copy" in Correlation ID (ie copied from the preceeding IF txn pairing) | Missing/incorrect validation rule | Supporting Docs |  | DES138 |  |  |  |  | 2023-06-16
MHHS-DIN-350 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-005 B033 to align Swagger with DES-138 (Postcode removal, mandatory modified meter id) |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Postcode removal, mandatory modified meter id) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-351 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B071 to align Swagger with DES-138 |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-353 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B032 to align Swagger with DES-138 (SSC Min Length should be 4) |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated SSC Min Length to be 4) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-354 |  |  | 2023-05-30 | SJW |  | Sarah Jones | Consultancy | Design team confirmation for sending of IF-037 and not IF-037 to losing MEM | Please see below details of a new design query related to the Registration Tranche of Code Drafting. We note that in BP011C there is a process whereby the Registration Service will auto de-appoint / appoint agents for secondary related metering points and linked export metering points as part of their validation. The business process only includes the sending of the IF037 to the Losing MEM and not the IF035. Please could you confirm that this is correct and that in this instance the Losing MEM would not receive an IF-035. If this is the case, we think there should be a change to Metering Service requirements MS-018 and 019 to clarify that where the Losing Metering Service receives an IF-037 with no preceding IF-035 then they should send the MTDs at this point. The alternative would be to include the sending of an IF-035 as well as an IF-037 accepting that these would arrive at a similar time. This would align to the process for managing retrospective MEM appointments where we understand that the Losing MEM would receive both the IF-035 and the IF-037. We also suggest amending MS-008, 008.1, 009 and 009.1 to recognise this nuance as follows: MSA/MSS must obtain Export MPAN de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. MSA/MSS should note this message will be automatically triggered when a change of Metering Service has successfully completed for the linked import MPAN or a new MPAN linkage has been put in place where the [linked import / primary related] MPAN has a different appointed Metering Service. Presumably there is a similar impact on the data service requirements that would need to be considered. |  | Closed |  |  |  | Solution options discussed with SCS. Closed as covered under DIN 560 |  | Supporting Docs | [6 empty] | 2023-07-14
MHHS-DIN-355 |  | DI-179 | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Number of Register Digits | Revisit and confirm IF-005 Cumulative Digits validation rule against latest version of the CP |  | Implemented |  | Interim Release 2 | 2023-06-23 | All instances of DI-091 (IF-002,IF005,IF-006,IF-033,IF-036) updated to reflect updated logic. IF-005 validation rules updated also to reflect new guidance. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-356 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B073 - update Swagger to align with DES-138 (consumptionAmendmentSupplierReference max length) |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated consumptionAmendmentSupplierReference max length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-357 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B902 - update Swagger to align with DES-138 (supplierConsumptionAmendmentRequests typo update) |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated supplierConsumptionAmendmentRequests - remove typo) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-358 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-034 B070 - update Swagger to align with DES-138 (contractReferenceMeteringService max length 10) |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated contractReferenceMeteringService max length 10) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-359 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: The method statement states that “The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN on notification of the set-up of that MPAN in MHHS-IF-001.” However, it will be the MHHS-IF-036 Registration Service Notification of Service Appointment & Supporting Info that will initially provide the fact that an MPAN has migrated to Central Settlements. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement updated with following text in red: 2.3 The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN within 30 calendar days following notification of the set-up of that MPAN in MHHS-IF-036 'Registration Service Notification of Service Appointment & Supporting information' or MHHS-IF-001 ‘Notification of change of Supplier’. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption |  |  |  |  | 2023-07-14
MHHS-DIN-360 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: 3.3 Where a years’ worth of data, >=75% and <100% of actual UTC Period Consumption data (where Settlement Period Quality Indicator = A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6) has been used to calculate the Annual Consumption, the Annual Consumption Quality Indicator should be set to “1”. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement updated with following text in red: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption |  |  |  |  | 2023-07-14
MHHS-DIN-361 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Greater than or equal to change for UTC Period Consumption Data | We need to raise a DIN on the AC method Statement and AC requirements: Likewise 3.6 needs to say greater than or equal to 182 days: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement updated with following text in red: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption |  |  |  |  | 2023-07-14
MHHS-DIN-362 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Section Name change | Section 5 incorrectly named Section 6 needs to be updated: 6. Transition and Next steps |  | Implemented |  | Interim Release 4 | 2023-08-16 | Section 6 has been updated to Section 5 within AC Method Statement and old section 5.1The initial Annual Consumption calculation, as set out in section 3.7 above may change, depending on the consideration of the working groups during the MHHS Transition requirements work- has been removed | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption |  |  |  |  | 2023-07-14
MHHS-DIN-363 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Load Shaping Service calculations | We may also need to document how this is calculated by the Load Shaping Service in the first year. I believe Helix have developed a calculation and this would need to go in the Load Shaping Method Statement and be referenced in the AC Method Statement. |  | Closed |  |  |  | Kevin Spencer to arrange a session with Mike Ceney to discuss solution further. Upon further discussion with Kevin Spencer on 4/8/23 it was confirmed this DIN could be closed as the change is in relationn the AC Method Statement. No changes required to the LSS Method Statement | Method statement correction | Supporting Docs | Method Statement | Annual Consumption Meth 10 |  |  |  |  | 2023-07-14
MHHS-DIN-364 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-035 - B066 - mark as mandatory in Swagger as per DES-138 |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated so B066 is a mandatory for IF-035 custom block) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-365 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-004 - B093 - update Swagger to align with DES-138 (min Length on commsHubGUID / GPF-GAS-GUID) |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated min Length on commsHubGUID / GPF-GAS-GUID) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-366 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 custom block - SSC add min length to align with Swagger |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B032 custom block - SSC add min length to align with Swagger) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-367 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 Profile Class - updated Swagger to be a String to align with DES-138 |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B032 Profile Class Swagger to be a String to align with DES-138) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-368 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-013 - B049 updated Swagger to align with DES-138 (run Number optional) |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B049 Swagger to align with DES-138 (run Number now optional) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  |  |  |  | 2023-06-16
MHHS-DIN-369 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | Switch Cancellation Info Note | Update BP002/003 to add informational note that Registration Cancelations will be processed as soon as they are received by SCS from CSS i.e. Apps Lapsed through switch cancelation sent immediatly not held until Proposed App Date. Also updates to Forward Migration BP002/003 for consistency. Changes to OPC added the following words to OPC_190 in the Activity column (section 4.4) “(including Switch Status Updates e.g. Cancelled)” |  | Implemented |  | Interim Release 2 | 2023-06-23 | BP-002/003 updated to include new informational Note in Supplier swimlane relating to CSS Switch Cancellations. OPC updated to make it clearer that Secured Active Processing includes Switch Status Update processing. to OPC_190 in the Activity column (section 4.4) “(including Switch Status Updates e.g. Cancelled)” | Process Model correction | MPAN Ownership |  | BP002, BP003, OPC001 Forward Migration BP002 & BP003 |  |  |  |  | 2023-06-16
MHHS-DIN-370 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | IF-005 Update Window Guidance for Prev MS | Change IF-005 and Guidance Doc to allow Meter Updates within 10 day window for previous MS |  | Implemented |  | Interim Release 2 | 2023-06-23 | New validation rule added to IF-005/MeterUpdate to allow previous MS to submit if within 10 day post appointment period. IF-005 User Guide section 9.3 updated to reflect same. | Missing/incorrect validation rule | Supporting Docs |  | DES138, IF-005 User Guide |  |  |  |  | 2023-06-16
MHHS-DIN-371 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team |  | Review design to ensure only Supression of IHD info for advanced segment and NOT "deactivation" of underlying IHD record. |  | Closed |  |  |  | Confirmed that IHD details will be retained on Smart to Trad Exchange. Any IHD info present will be suppressed (ie not included in msg) if Segement is Advanced. No change required to documentation. Possible data cleanse issue - Dan T. to raise in Data Forum.
MHHS-DIN-372 |  |  | 2023-06-01 | MHHS | 5298 | Rob Golding | Central Body | Mapping Roles | There is a need to master the mapping of Market Participant Role to DIP Role within the MHHS solution. |  | Implemented |  | Interim Release 3 | 2023-07-12 | New entity M18 created to show the DIP market roles. Minor corrections to M16 to clarify DIP ID field length. | Other | Supporting Docs | ISD Entities | MHHS-EDI-021-ISD_Entities |  |  |  |  | 2023-07-14
MHHS-DIN-373 |  |  | 2023-06-02 | MHHS | 5272 | Rob Golding | Central Body |  | There is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 |  | Closed |  |  |  | Duplicate of DIN-297
MHHS-DIN-374 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Message Replay & Requeue functionality | Message replay and requeue functionality needs to be added to the DIP API interfaces, which requires changes to the Swagger / YAML definitions. Detail is required in the E2E design documentation to explain how the message replay and requeue functionality will work. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updates to the E2E001 design document to provide detail on how the replay and requeue will work. There are updates to Swagger to support new interfaces for /dip-channel/{id}/replay and requeue respectively. There is also a new MessageRequest Schema that is used to pass data into both of these interfaces. To support these changes, section 4.8 has been updated in the E2E001. | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents |  |  |  |  | 2023-06-16
MHHS-DIN-375 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Interface webhook configuration | Updates require to the pubconfig and webhook config to support per interface webhook configuration, alongside changes to support definition of recipient ID and role ID. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updates to the E2E001 design document to provide detail on how the webhook configuration will work, with information related to specific interface changes. There are updates to Swagger to support new interfaces for /dip-channel/{id}/pubconfig (POST and DELETE) respectively to support changes defined in the E2E001 (Section 4.5 and 4.5.1 and 4.5.2have been updated to provide more clarity / information). | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents |  |  |  |  | 2023-06-16
MHHS-DIN-352 |  |  | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Obsfucation Text | What text should be used for data obfuscation ? for things like Boolean fields (True/false) |  | Closed |  |  |  | Closed as this is already included in section 4.3.2 of the E2E001 design document. | [8 empty] | 2023-07-14
MHHS-DIN-376 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-099 changes required to ensure DES-138 displays the correct YAML name / Swagger aligns to this. |  | Implemented |  | Interim Release 2 | 2023-06-23 | "Register" spelling in name has been corrected in DI099, and DI-099 name correction for IF041 in DES138 | Data interface correction | Supporting Docs |  | DES138 |  |  |  |  | 2023-06-16
MHHS-DIN-377 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-097 | DI-097 - In DES-138, this is defined as a string (2), but the existing data type is an Integer and this is an Integer enumeration. Need to update this to an Integer in both DES-138 and Swagger 1.2. |  | Closed |  |  |  | Rejected / closed as enumeration of values requires string (2) therefore this is retained to support buisness requirements. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-378 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. |  | Implemented |  | Interim Release 2 | 2023-06-23 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. This information has now been added to DES-138 5.2.1. | Data interface correction | Supporting Docs |  | DES138 |  |  |  |  | 2023-06-16
MHHS-DIN-379 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-048 | DI-048 - clarity required on whether this is "meter manufacture make and type", rather than just "meter manufacturer". The first is an existing data type and links to the J number, so providing further clarity / rename would quickly ensure alignment in DES-138 and then subsequently in Swagger. |  | Closed |  |  |  | Rejected / closed as this was discussed as part of previous work off items and description has previously been approved / accepted as Meter Manufacturer. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-380 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-052 | DI-052 in DES-138 currently has 4 enum values ie, - Active Import, Active Export, Reactive Import, Reactive Export. In MDD there are currently 38 options documented. Discussion around whether ISD Entity 47 should be referenced as the list of values allowed. This can then be aligned / referenced in other other documents ie, EMAR will reference ISD Entity 47. |  | Closed |  |  |  | Rejected / closed as this was discussed as part of previous work off items. Only 4 values are required in MHHS / DIP, therefore only these values are referenced / used as part of the enumeration to avoid bringing data from existing systems into new systems when this is not required. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-381 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-842 | DI-842 - Confirmation that MDR's have DIP ID's? There has been discussion in various forums to understand whether they do and if not, then this data item needs to be removed in DES-138 and Swagger. |  | Closed |  |  |  | Rejected / closed as MDR's do have DIP ID's, therefore this value will be retained. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-382 |  |  | 2023-05-06 | Design Team | 4570 | Neil Strange | Supplier | D0010 | In BP003C, at CoS traditional CoRs are transferred between suppliers via D0010. We believe this needs to be used for all meter types - as this will be needed for non-communicating smart and advanced meters – and BP003C needs to be amended accordingly. There is no mention of IF-041 and we do not believe that the DIP is expecting an IF/PUB-041 transaction between suppliers. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Supplier added as a Primary Recipient in the Routing Rules for IF-041 (DES138) - Supplier initiated Reads. Sending supplier would need to populate the DIP ID of Supplier(s) with whom he wished to share the reading. Working Group specifically decided not to discuss /include COR scenarios for Smart Metered Sites however this is not prevented by the Design - a note to this effect has been added to BP003C for clarity. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue BP-003C Transfer of Readings
MHHS-DIN-383 |  |  | 2023-06-07 | RECCO | 4558 | Sarah Jones | Central Body | Change of Segment Scenario | We cannot find anything in the design artefacts stating that the Metering Service is required to notify metering exchanges for change of segment within 2 WDs. We have found the following: MS-094: MSA/MSS must be able to publish Change of Segment Meter Exchange details and reads via the appropriate interfaces, where it is not formally appointed as the Metering Service but does have an accepted prospective appointment (Appointment Scenario = "SEG"). The MSA/MSS must issue the work update to Registration at the earliest opportunity but within [x] days of completion at the latest. OPC 240: Notification of works to be completed by D+3 Working Days (This should provide time for consumption to be provided using new MTDs ahead of the SF run.) The BP011 references the connection type update being provided by LDSOs within 2 WDs. There is no equivalent for metering updates. Will require DRG confirmation on if the 'x' should be 2 or 3 working days |  | Implemented |  | Interim Release 3 | 2023-07-12 | Updates to be made inline with DRG recommendation to reflect 3 working days | Process Model correction | Supporting Docs | Business Process Documentation | BP011 - Change of Segment DES138-Interface Doc BRS002- Metering Service Requirements BRS003 - Registration Service Requirements BRS005 - LDSO Overview OPC001 - Operational Choreography MHHSP-DES229-IF005_UseCaseguide |  |  |  |  | 2023-07-14
MHHS-DIN-384 |  | DI-174 | 2023-06-07 | St Clements | 4938 | Madison Layton | Software Provider | IF-038 and IF-039 blocks not the same | Block B020, B021 are not the same across interface IF-038 and IF-039. DI-140 and DI-138 (SP DIP ID) are in IF-039 but not in IF-038. Understanding was that with the DIP change that all data items in block are mandatory, the blocks were to be consistently defined across all interfaces. If extra DIP ID DI-138 and DI-140 data items are included in IF-038 then we need a new REG rejection code to allow us to reject where DIP ID is not the same as the sender DIP ID. Alternative is to separate the DI-140/DI-138 into their own blocks included on the IF-039 interface only. |  | Implemented |  | Interim Release 3 | 2023-07-12 | Block data items were aligned in release 2. New validation rule on IF-38 add to ensure that Sender ID matches MS/DS CDC ID. New Error code REG1076 added to support validation rule. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  |  | 2023-07-14
MHHS-DIN-385 |  |  | 2023-06-07 | Design Team |  | Steve Weston | SI Design | Correlation ID | S1 Common Block - Correlation ID is mandatory in Swagger, but Optional in DES-138. Swagger should be updated to align. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Updated S1 Common Block, Sender Correlation ID in Swagger, as this is Optional in DES-138 to support business process and requirements. | Technical corrrection | Supporting Docs |  | JSON/YAML documents |  |  |  |  | 2023-06-16
MHHS-DIN-386 |  | DI-179 | 2023-06-07 | St Clements | 5258 | Madison Layton | Software Provider | Register Digits | REC Change R0102 has been approved by industry to amend the number of display digits validation Where the Meter Type is S1 the Number of Displayed Register Digits value must be either 6 or 5 Where the Meter Type is S2A, S2AD, S2ADE, 2ADF, 2ADEF, 2AEF, 2AF, S2B, S2BD, S2BDE, 2BF,2BDF, 2BDEF or 2BEF the value must be “5”. Where the Meter Type is prefixed with “S2C” the value must be “6”. Where the Meter Type is 2CDEF, 2CF, 2CDF or 2CEF the value must be “6” REG1097 validation on the IF-005 needs correcting with this change, and the population notes for data item DI-091 across multiple interfaces also needs correcting |  | Closed |  |  |  | Duplicate of Register Digit DIN-355 listed above | Data interface correction | Supporting Docs | Interface Catalogue | Lis
MHHS-DIN-387 |  | DI-180 | 2023-06-09 | St Clements | 5269 | Madison Layton | Software Provider | Uplift metered indicator requirements | There are elements in the requirements that suggest that metered indicator would trigger a change to Market Segment. E.g. MHHSP-BP011-Change of ConType andor Mkt Segment-v5.1 Step 102 MHHSP-BPD011 - Change of Con Type or Market Segment v5.0 Step 102 Which states if there is a change to market segment RS would need to re-evaluate the market segment And MHHS-BR-RS-124 which include in brackets: Change of Connection Type (Change of Unmetered Indicator) MPRS will assess Market Segment against the ISD entity M7 which does not include Metered Indicator. Therefore a change in Metered Indicator in isolation of any other changes to data items in the M7 table/Related MPANs/Linked MPANs, will not trigger a change to Market Segment. As it will not trigger a change MPRS will not re-evaluate Market Segment base on a Metered Indicator change alone. The requirements need uplifting to reflect. |  | Closed |  |  |  | Closed as discussed and agreed with SCS. | No Change
MHHS-DIN-388 |  |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | IF-036 Custom Routing Rules | Following discussions with SCS agreed that for reasons of complexity it would be better to adopt Primary rather than secondary routing to IF-036. New Requirement created for REGS to undertake the Primary Routing of IF-036. |  | Closed |  |  |  | Ref DIN-507
MHHS-DIN-389 |  |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | Appointment Start Times | Do we need a formal validation Rule to check that Appointment Start times are referenced as Midnight Local ? Issue raised numerous times with SCS. Waiting for SCS to confirm their position. |  | Closed |  |  |  | CLOSED - DUPLICATE OF DIN-207 ABOVE
MHHS-DIN-390 |  |  | 2023-06-13 | Siemens | 5534 | Tony Mason | Metering Service Provider | IF/PUB-018 | There appears an inconsistency in the Business Process Map, BP010, and the routing rules for the IF-018 where the Event Code = DUOSTariffIDChg. This information is confirmed to SPs on the IF/PUB-036 and would then be updated where there is a change on the 018 according to the Secondary Routing Rules. This notification is absent on the process diagram. Could you confirm the position and update the documentation accordingly? |  | Implemented |  | Interim Release 4 | 2023-08-16 | Update BP010B to show Data Service and Metering Service receiving PUB-018 for DUoS Tariff ID updates in line with the routing rules in DES-138. Update BPD010 process description to includes steps to recieve PUB-018 for Data Service and Metering Service. | Process Model correction | Meter to Bank | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-391 |  | DI-182 | 2023-06-13 | St Clements | 5304 | Madison Layton | Software Provider | IF-019 validation gap on principal and subsidiary MPAN | IF-019 is missing validation rules to ensure an MPAN is only listed once in the IF-019, need rules to ensure the sender cannot repeat same Subsidiary MPAN twice in the repeating B090 block, and cannot list the same MPAN as both Principal and Subsidiary in the same IF-019 message |  | Implemented |  | Interim Release 3 | 2023-07-12 | Created x2 new rules to prevent duplicate MPANS within repeating B90 groups within a single message. Error Code REG1059 created to support validation checks | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-392 |  |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Consent Fields | Raised by SCS. B068/DI-017/DI-018 - This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block B068 updated to be "must be provided" for smart meters. Data items set to mandatory non-nullable. |  | Implemented |  | Interim Release 2 | 2023-06-23 | Block text updated to show mandatory if smart meter present, and DI-017/D-018 updated to be mandatory non-nullable (applies to IF-026 only) | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-393 |  | DI-181 | 2023-06-13 | St Clements | 5274 | Madison Layton | Software Provider | De-appointment and re-appointment date order | MHHS-BR-RS-128.4 & MHHS-BR-RS-128.5 covers the requirement for MPRS to ensure MS/DS are aligned across Related/Linked MPANS, and where they are not to de-appoint the MS/DS and appoint the correct MS/DS. The de-appointment requirement specifies to set MS/DS ETD to D+1 and the appointment to set the MS/DS EFD to D+2. Why do we need to apply the de-appointment and re-appointment in the future? Would we not be better to use the previous day (D-1) for the de-appointment MS/DS ETD and the current day (D) for the appointment EFD? |  | Closed |  |  |  | Can Close and SCS have agreed with the Requirement. Needs to be this was as work may have been arranged for the last day | No Change
MHHS-DIN-394 |  |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Annual Consumption Fields | Raised by SCS. B059/B027/DI-0148 This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block updated to be "must be provided" if available, however data items now need to be set to mandatory non-nullable. |  | Implemented |  | Interim Release 2 | 2023-06-23 | DI-0148 updated to be mandatory no-nulls and data type updated to DT-016 in Data Catalogue. Data Type corrected to DT-016 in IF-002 and IF-036. | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-395 |  |  | 2023-06-13 | St Clements | 5510 | Vicki Holland | Software Provider | Obfuscation of Connection Type Indicator in IF-021 | The DES138 interface catalogue specifies that the data item Connection Type Indicator will be obfuscated for all parties as it is required for routing only. Can this please be changed so that it is visible? The reason for this request is that suppliers often process data differently for the different connection types and therefore its important that they can internally validate or route data according to the connection type of the MPAN. |  | Implemented |  | Interim Release 3 | 2023-07-12 | Obfuscation of connection type removed from IF-021/IF-013 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-396 |  | DI-183 | 2023-06-13 | St Clements | 5305 | Madison Layton | Software Provider | Update IF-019 REG1001 to only apply to Create and Add event codes | IF-019 REG1001 rule applies to all event codes. The MPAN could be disconnected with linkages still in place. If REG1001 is applied on remove event codes, then there will be not means by which the Supplier/DNO can remove the linkage after a disconnection. Suggest REG1001 rule should only apply to the Create and Add event codes. This would be consistent with the existing validation on the DB05 and D0386. |  | Implemented |  | Interim Release 3 | 2023-07-12 | IF-019 MPAN Status Validation Rule removed for all "Remove MPAN" Event Codes. i.e. I can still perform remove MPAN from group task if MPAN is disconnected. SCS rejected option of auto de-linkage as part of De-Registration Process. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-397 |  | DI-184 | 2023-06-13 | St Clements | 5306 | Madison Layton | Software Provider | IF-019: REG0007 to only apply to Related event codes and not to Linked Import Export event codes | REG0007 on IF-019 interface is currently written to apply to both Related and Linked MPANs. The intention of this existing rule on D0386 is because Related MPANs switch together, and so changing the relationship during a switch can create a split supply relationship. However Linked MPANs do not switch together and so this is not currently applied to the existing DB05 validation rules. Suggest REG0007 only apply to Related event codes and not to Linked Import Export event codes? |  | Closed |  |  |  | Following discussions with SCS it has been agreed to prevent all changes to MPAN Linkages whilst an Active Switch is in progress. This is the safest approach when considering both CSS and Auto Alighment functionality considerations. No change to existing Design Documentation required.
MHHS-DIN-398 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD Stores LLF data | Can we have an ISD entity ID for LLF data. This would be required for the API used to retrive the data from ISD data store. Are you happy for us to create and put it in the Guidance note. What is the ask? |  | Closed
MHHS-DIN-399 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD publishes full data to Elexon Central Systems | Requirement should be reworded to be "ISD must make available the data sets required by LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. ISD must make available the entire current data set to LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. |  | Closed |  |  |  | Agreed in a session with Elexon 26/07 that the requirements document will not be changed as the requirement has already been fufilled by Elexon in line with the current requirement.
MHHS-DIN-400 |  |  | 2023-06-14 | SRO Design Team | N/A | Sean Cooper | SEO Design | REGS Validation Rule Clarification | REG1089 conditions updated to provide more clarity. Existing wording refered only to a Subsequent App - this is now better defined as an Appointment with a prior/earlier Sender Timestamp. No functional change. |  | Implemented |  | Interim Release 2 | 2023-06-23 | For IF-031 Validation rule text updated to specifically reference Sender TimeStamps so as to provide more clarity on the nature of the val rule/when generated | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-401 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | IHD/SMSO Fields | IHD Install Status and IHD Status Effective from Date fields should be optional (i.e. nullable) when providing an IHD update in IF-025/IF-026. SMSO and SMSO Effective from Date fields should be optional (i.e. nullable) when providing an SMSO update in IF-025/IF-026. |  | Implemented |  | Interim Release 2 | 2023-06-23 | DI-137/ DI-136 in block B030 updated to Optional (O) in IF-025 and IF-026 DI-134/ DI-135 in block B031 updated to Optional (O) in IF-025 and IF-026 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-402 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Import/Export Fields | Linked Import/Export MPAN and Linked MPAN Energy Direction will always be provided so should not be nullable |  | Implemented |  | Interim Release 2 | 2023-06-23 | DI-038 updated to Mandatory No nulls and Data Type updated to DT-002 DI-151 updated to Mandatory No nulls On the 01-Data Catalogue | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-403 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Meter Manufacturer Field | Meter Manufacturer is optional (ie nullable) when provided in IF-002, IF-006, IF-033, IF-036 as in IF-005 |  | Implemented |  | Interim Release 2 | 2023-06-23 | DI-048 updated to Optional (O) in IF-002, IF-006, IF-033, IF-036 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-404 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Proposed Appointment Response Code Field | For Response code A there may not be any text to populate for DI-143 |  | Implemented |  | Interim Release 2 | 2023-06-23 | DI-143 updated to conditional (C) based on DI-979 = L or R in block B007 in IF-034 and IF-035 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-405 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Response Message Field | For Response code A no text to populate for DI-980 |  | Implemented |  | Interim Release 2 | 2023-06-23 | DI-980 updated to conditional (C) based on DI-979 = R in block R0 in 02-DIP Common Block tab | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-406 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Sender DIP ID Field | Sender DIP ID should always be provided in S1 Common Block |  | Implemented |  | Interim Release 2 | 2023-06-23 | DI-997 updated to mandatory (M) in block S1 in 02- DIP - Common Block tab | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-407 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | COS During SEG Issue | Discuss with SCS the option of allowing non-appointed MS to update MTDs even if App has lapsed due to COS activity. If not then need to update process map to call out need for manual exchange of MTDs as Work MS could never submit if IF005 |  | Closed |  |  |  | Closed, SCS unable to support alternative solution. Design Team have reviewed the existing process map note and believe this already provides enough information for participants. | No Change
MHHS-DIN-408 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD is the master for data contained both within ISD and MDD during Transition | The requirement is a bit ambiguous as could be read as all ISD and all MDD rather than just ISD data + overlapping MDD data. We don't want to be the master for MDD only data |  | Closed
MHHS-DIN-409 |  |  | 2023-06-14 | St Clements | 5510 | Vicki Holland | Software Provider | ISD Entity M5 – Consumption Component Classes | EDI012 ISD entities document shows that the settlement period quality indicator in entity M5 is a comma separated list of possible values. This will be difficult to use in systems that need to refer to this data. Could this instead show Actual or Estimate? Alternatively could this be split into parent and child entities to avoid a comma separated list? Metering Service ID MPID is incorrect and must be changed to {MS Id} also in ISD Entity M8 |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Amendments relating to “Valid Settlement Period Quality Indicator Set” wording and field length in section M5 of EDI012 ISD entities document. Change also made from Metering Service ID MPID to Metering Service {MS Id} in Entitiy M8. An objection was raised against this DIN. Following discussion at the DRG about this DIN it has now been moved to Interim Release 5. A decision was made at DRG to go with OPTION 2: Change Existing Layout – Remove list element in favour of individual row(s) for each valid combination for the Valid Settlement Period Quality Indicator Set. Option 2 changes have been implemented to section M5 of EDI021 ISD Entities. Following the change to the layout the amendments to the data item will revert back to its initial name of Settlement Period Quality Indicator. and a data type length of 5 characters | Method statement correction | Supporting Docs | Method Statement | Annual Consumption Meth 10 EDI021 ISD Entities
MHHS-DIN-410 |  | DI-487 | 2023-06-14 | St Clements | 5542 | Virginia Patey | Software Provider | DI-487 definition incorrect for REP-002 on Swagger | DI-487 energised MPANs is defined as an Integer in the Interface Specification, yet is defined as a String in Swagger. |  | Implemented |  | Interim Release 2 | 2023-06-23 | DI-487 updated in Swagger 1.2 to align with Interface specification for REP-002 | Data interface correction | Supporting Docs |  | Swagger 1.2
MHHS-DIN-411 |  | Migration | 2023-06-14 | ESG | 4810 | Patricia Parker | Software Provider | Migration Segment Categorisation | The Migration Design currently specifies that Market Segment needs to be recorded before the Migration phase. This should be changed so that it is no longer required. Until an MPAN is migrated, there is no way of maintaining the market segment between the RS and EES using the legacy interface between these two services. However, meter type and connection type will be available in both the EES and the RS, so Suppliers can use a combination of these values to derive the correct market segment. |  | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | 03/08: SCS confirmed in a session with SC that they agreed that Segment is a derived value based on Connection Type and MTR. There are validation rules that prevent the migration if Connection Type (and therefore segment) is not already defined in REGS. To address the original question Segment will always be known at the point of migration. Therefore, no changes are required to Migration document. 13/07: John Wiggins to have offline discussion with Sean C as DIN requires wider discussion at DRG to progress SRO Team disagree with this Migration Request. Market Segment must be known prior to the selection of MHHS Service Providers. Market Segment is a derived field based on Connection Type and Meter Type. Connection Type must be set before Migration / Meter Type already known so Market Segement CAN be derived, set and maintained prior to MPAN migration. No change to baseline documentation Required.
MHHS-DIN-412 |  |  | 2023-06-14 | MHHS | 5022 | John Wiggins | Central Body | Update to MDD | Migration request to ensure that Elexon add MHHS as a value to MDD. Page 35 of the Design Document under Reverse Migration states that -A default MPID of ‘MHHS’ will be created for the DC, MOP, DA appointments. Will MHHS be contained within MDD as a valid set as there is no reference in the document to update MDD with this value. |  | Industry CP Required |  | Interim Release 6 | 2023-10-18 | As the Migration documentation was approved via DAG and following discusion with RecCo and BSC the updates are being documented inThis is being picked up in an update to DES196 Dflow interface
MHHS-DIN-413 |  | Migration | 2023-06-14 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | Reading Type (J0171) will be updated with three new values: Forward Migration CoA Forward Migration CoS Reverse Migration CoS Reading Type (J0171) will no longer use Initial or Final for migration reads between Suppliers or DC/DS but one of the above new codes will be used. Meter Reading Reason Code (J0332) will no longer be used to identify migration reads, all reference to this will be amended to Reading Type (J0171) in the guidance document. |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | DTN message changes to be added to DES196 as part of IR5” instead of “Industry CP required Code Drafting Team/ Elexon will draft and raise a CP to cover these changes. Replaces DIN-442 | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-414 |  |  | 2023-06-14 | British Gas |  | Mohammad Amin Fuggawala | Supplier | D0275 in D-Flow Document | Ref Previous DIN-244. In the "DES196 D-Flow Document" the D0275 is showing as redundant. This is misleading it should be marked as by agreement between contracting Supplier-DS. Document should be updated to reflect this. |  | Closed |  |  |  | Centrica have been notified on closure of DIN. Update was delivered in the published V1.0 of DES-196 as part of July DAG and the updated version is available on the Collaboration Base. | No Change
MHHS-DIN-415 | RT |  | 2023-06-14 | Elexon | 5702 | Mike Ceney | Central Body | Routing IF-026 to LSS | IF_026- For Routing Rules it states for Event Code/Conditions [SSC], [ProfileClass] and [SSCandProfileClass] that this should be routed to MDS, is this incorrect as MDS does not use these items in any calculations or outputs, this should state LSS |  | Implemented |  | Interim Release 2 | 2023-06-23 | IF-026 [SSC] and [ProfileClass] have been removed as of Interim Release 1. Update DES138 IF-026 to route to LSS on event [SSCandProfileClassChange] | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-416 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-001 New App Scenario Code MCS (Migration Change of Supplier) | Create new Appointment Scenario Code of MCS |  | Implemented |  | Interim Release 3 | 2023-07-12 | IF -031 New valued added to DI-800 data catalogue and Swagger 1.3 updated to reflect new value | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-417 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-002 Validation Rules for Scenario MCS (Migration Change of Supplier) | New Val rule to check MCS is only used for legacy non-migrated MPAN where Supplier is not current supplier (and not in past) |  | Implemented |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-418 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-003 New App Scenario Code MCA (Migration Change of Agent [Service Provider]) | Create new Appointment Scenario Code of MCA |  | Implemented |  | Interim Release 3 | 2023-07-12 | IF-031 New valued added to DI-800 data catalogue and Swagger 1.3 updated to reflect new value | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-419 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-004 Validation Rules for Scenario MCA (Migration Change of Agent [Service Provider]) | New Val rule to check MCA is only used for legacy non-migrated MPAN where Supplier is current supplier and now active Switch is in progress (and not in past) |  | Implemented |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-420 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-005 - IF-31 Check valid MHHS Supplier | If MCS/MCA code used is Supplier a valid MHHS Approved/Registered Supplier |  | Implemented |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-421 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-006 - Prevent use of Migration Scenario IDs | IF MCS/MCA code used for already migrated mpan - reject appointment for invalid Scenario code(s) |  | Implemented |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-422 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-007 Connection Type/Segment not yet Populated | New error required if Connection Type, DUos Tariff ID or Segment is not set prior to migration. |  | Implemented |  | Interim Release 3 | 2023-07-12 | New Validation Rule created for IF-031 to check that MHHS Standing Data is present and aligned. REG0011 Error created to support this validation Rule. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-423 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-008 Auto Realign Functionality | New REGS Requirement - Only action the auto-realign functionality on MPANs where both Linked MPANs are in a Migrated state. |  | Implemented |  | Interim Release 3 | 2023-07-12 | New Req RS-146 added to REGS Requirements Document to ensure that Auto-Align functionality is only executed if all MPANs in a related and/or linked group have sucessfully migrated to MHHS Operation. | Requirement correction | Meter to Bank | Requirements Documents | BRS-003-Registration Service Requirements
MHHS-DIN-424 |  | DI-185 | 2023-06-16 | St Clements | 5335 | Madison Layton | Software Provider | MPRS access to correlation ID | IF-019 is sent to the LDSO for LinkedImportExport event codes, if the LDSO approves the request they will submit an existing DB05 flow into MPRS. If the DB05 is accepted by MPRS, it will send an IF-020 to the Supplier to confirm the change to Linked Import Export association. However MPRS would not have access to the correlation ID that was received by the LDSO on the IF-019, and so would use a new correlation ID on the IF-020. |  | Implemented |  | Interim Release 3 | 2023-07-12 | IF20/IF19 Note amended explaining that it will not be possible to Link IF-019/IF020 messages together using Correlation ID , in the case of Linked MPANs. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-425 | SC | Migration | 2023-06-19 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | 8.1.3 step 12 Migration Design Document : Validation Status (J0022) references will be updated to Meter Reading Flag (J0045) |  | Ready for Internal Review |  | Interim Release 6 | 2023-10-18 | 8.1.3 step 12 Migration Design Document : Validation Status (J0022) references will be updated to Meter Reading Flag (J0045) | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-426 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-009 New Rejection Code for D0205/D0203 | Response to a D205 is a D0203. 1. A New Rejection Condition/Code is required where D0205 is received following processing of IF-031. 2. Proposed new D0203rejection code is 62 "MHHS Fwd Migration in Progress or Completed" |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | DTN message changes to be added to DES196 as part of IR5” instead of “Industry CP required | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-427 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-010 ISD Change M16 | No change Required - SCS can use ISD M16 - which contains MIPD/DIP Role and Effctive From date. This can be used to determine if a Supplier is MHHS qualified. This is better apporach that adding a transiant "Qualified Yes/No" field to this table. Therefore NO changes to documentation required. |  | Closed
MHHS-DIN-428 |  |  | 2023-06-19 | British Gas | 5835 | Neil Strange | Supplier | MEX before SSD scenario | When a CoS is in progress and there is a MEX before SSD, how will new supplier get the MEX details As the incoming supplier has already received the IF36 - would there be a new IF36 or would it be a PUB006? In addition how would the new MS and DS be made aware of this? - the old MS has X days after the job is completed to update the industry and a CoS could have happened before the old MS can update the other participants. |  | Closed |  |  |  | BAU Design deals with 'regular' MEX before COS type scenarios (note previous MS Update Period - PUB-006 would be issued to impacted parties). Complexity arises where there is a COS overlapiing with Change of Segment/Connection Type (ie SEG Appointment)... Following discussion with SCS - low probably, low occurance vs. complex change. Ref existing guidance on BP016 there would need to be a manual interaction between Supplier and MS. No Change to existing Documentation Required.
MHHS-DIN-429 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-011 Changes to D0170 | 1. Change D0170 flow so that MPRS/Registration Service is valid Sender of this flow. 2. New value for "Request Action Code" is needed to denote a Migrating account and if its CoS or ChgOfSP method. |  | Ready for Internal Review |  | Interim Release 6 | 2023-10-18 | DTN message changes to be added to DES196 as part of IR5” instead of “Industry CP required Add new Scenario Variant FROM Electricity Retail Data Agent TO Electricity Supplier | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-430 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-12 New Val Rule for IF-019 | Reject any changes to Related MPANs where any MPAN referenced (or in realted group) is subject to an active Migration SP Appointment Process |  | Implemented |  | Interim Release 3 | 2023-07-12 | New Validation Rules and Error Code created to prevent changes if MCA Appointment Type Exists (Note: prevention if MCS exists is realised through existing check on if Switch is in Progress) | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-431 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-13 Change to D0386 | Change D0386 validation to reject changes to related MPANs if any related MPAN in group is subject to active Migration SP Appointment Process |  | Industry CP Required |  | Interim Release 6 | 2023-10-18 | Change D0386 validation to reject changes to related MPANs if any related MPAN in group is subject to active Migration SP Appointment Process | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-432 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-014 Appointment on Secondary Related MPAN | Extend existing 1039 check to include MCS.MCA Appointment Scenarios. |  | Closed |  |  |  | Existing Validation Rule(s) around REG1039 will already cover Migrating MPANs - No Documentation Change Required.
MHHS-DIN-433 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-015 Switch in Progress Mig Rejection | New IF-031 validation to reject MCA/MCS DS and MS Appointments if an [any] active Switch is in progress with NEW Rejection Reason Code (note 1095 code referenced in Migration document has already been used elsewhere) |  | Implemented |  | Interim Release 3 | 2023-07-12 | New validation rules and REG9XXX Exception codes added to ensure correct usage of MCA/MCS Appointment Scenario Codes. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-434 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-016 New IF-003 | Previously DIN-247, Introduce IF-003, no changes from original proposal. 1. Update DES138 new tab, update IF List. Update New Data Items 2. Review E2E doc. 3. Update secondary Routing Rules (Avenade Techncal Doc) to include 4. Update Swagger |  | Implemented |  | Interim Release 3 | 2023-07-12 | Add data items DES138-Interface data Cat and to IF-003. Created new Data items: DI-500 MHHS Regime End Date, DI-501 Rev Migration Incoming MOP MPID, DI-502, Rev Migration Incoming MOP Eff From Date, DI-503, Rev Migration Incoming DC MPID DI-504 Rev Migration Incoming DC Eff From Date. Swagger v1.3 updated to reflect new IF-003, Blocks (B096/B095/B094) & Data Items (as above). | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-435 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-017 D0304 & D0303 | 1. New D0304 Validation Rule 2. NewD0304 Rejection Reason Code "Q - MPAN Fwd migration in progress or completed" 3. Change D0303 so as to make "Eff From Settlement Date REGI" a non mandatory data item within the flow (an alternative to suggesting that outgoing MS no longer issues a D303, only the incoming MS would send) |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | DTN message changes to be added to DES196 as part of IR5” instead of “Industry CP required | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-436 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG0-018 D312 | 1. New D03012 Validation Rule 2. New Rejection Reason Code "AD - MPAN Fwd migration in progress or completed" |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | DTN message changes to be added to DES196 as part of IR5” instead of “Industry CP required | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-437 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-019 IF-005 Validation Rule | 1. New val rule to prevent IF-005 while MCS/MCA Appointment is in progress 2. New Error Code (REG9003) |  | Implemented |  | Interim Release 3 | 2023-07-12 | REG9003 - MHHS MTD Updates cannot be used until Migration has completed, Created and new validation rule added to IF-005 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-438 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-020 REGS Design Clarification | SCS Should issue L1/L2 Msg Status message with RCP1061 for any MPAN at the incorrect status where a DIP Message is received |  | Implemented |  | Interim Release 3 | 2023-07-12 | This is a Migration Requirment which participants should take into account as part of their Migration Designs. However, for clarity a note has been added to RCP1061 entry in the Intoduction Section of the Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-439 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-021 No Supplier Updates during Rev MIgration (IF-025) | 1. New If-025 val rule to check if Rev Migration Switch is in progress 2. New error code |  | Implemented |  | Interim Release 3 | 2023-07-12 | REG9002 - Supplier Data Items Cannot be Maintained for Reverse Migration Account, Created and applied to IF-025 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-440 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-022 No CDCs Updates during Rev MIgration (IF-038) | 1. New If-038 val rule to check if Rev Migration Switch is in progress 2. New error code |  | Implemented |  | Interim Release 3 | 2023-07-12 | "REG9001 - CDC Marker Cannot be applied to Reverse Migration Account", created and applied to IF-038. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-441 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-023 No AC Updates during Rev MIgration (IF-040) | 1. New If-040 val rule to check if Rev Migration Switch is in progress 2. New error code |  | Implemented |  | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement section 5 has been updated with the text below in red: Where an MPAN is no longer active under MHHS during the transition phase the Market-wide Data Service shall not calculate or submit an annual consumption on the IF/PUB-040. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption
MHHS-DIN-442 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-024 D0010/D0086 New MR Reason Codes | Three new MR Reason Codes for use in D0010: Forward Migration COS / Forward Migration COA / Reverse Migration |  | Closed |  |  |  | Original migration design. Superceded by DIN-413.
MHHS-DIN-443 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-025 D0055 New Agent App Reason Codes | 1. New Valid value for service reference "REVM" 2. New valid value for Service Level "REVM" |  | Closed |  |  |  | do not require a message change, as the two data items in question are free text CHAR(4) that will accept any string that conforms. It’s the recipients that will need to act off it. | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-444 | RS |  | 2023-06-19 | ESG |  | Patricia Parker | Software Provider | IF-01 Incoming supplier for Import/Export MPANs | Clarification required with SCS. If it is known that an alternative MPAN has the same SSD then we do not want the old supplier ID as the linked supplier on the IF-01, we want the new supplier to be populated |  | Closed |  |  |  | Discussed with SCS and they have confirmed that where co-incidnet COS occurs they would look to populate the [new/incoming] Linked Supplier ID.... No change to documentation required.
MHHS-DIN-445 | SB |  | 2023-06-19 | Utiliteam |  | Richard Palmer | Software Provider | Spec of IF-024 in DES138 Interface Catalogue | The Population Notes for DI D-000 in Group S0 has ‘IF-025’. This error was in v5.0, and is still in v5.1.1 |  | Implemented |  | Interim Release 3 | 2023-07-12 | The Population Notes for DI D-000 in Group S0 has been updated to ‘IF-024’ in IF-024. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-446 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-026 Migration DIP Reporting Reqs | Reqs for x3 new Reports -- Flag at the next DIP DAG |  | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | Awaiting further internal discussions re DIP Reporting Strategy
MHHS-DIN-447 | SW |  | 2023-06-21 | Kraken | 5980 | Angelos Rizoyannis | Software Provider | Conditional Mandatory not applied in Swagger correctly | IF-041-CustomBlock: The field B065List is stated as optional in the comments, but the API schema does not reflect this. This field that is conditionally optional in DES-138, but this is not defined as such in Swagger ie, OneOf, AnyOf. This needs to be updated in Swagger to align correctly. |  | Implemented |  | Interim Release 3 | 2023-07-12 | In Swagger 1.3, updated IF-041-CustomBlock: The field B065List and B064List will be either / or as they are defined as conditionally mandatory in DES-138. This uses AnyOf notation in Swagger. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-448 | SW |  | 2023-06-21 | Kraken | 5980 | Angelos Rizoyannis | Software Provider | Mandatory fields not applied correctly in S1 block | S1 Common Block: The 'properties' and 'required' sections of the API schema for the S1 common block have conflicting information. The 'properties' section includes fields like senderTimestamp and senderRoleID, while the 'required' section lists sentTimestamp and senderRole. |  | Implemented |  | Interim Release 3 | 2023-07-12 | Updated Swagger 1.3 to align properties and required sections so that fields are called senderTimestamp and senderRoleID. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-449 | SC |  | 2023-06-21 | SRO Design Team |  | Sean Cooper | SRO Design | Change to IF-037 | Include Block B002 into IF037 so that outgoing MS is aware of incoming Supplier on a COS. This will allow the SP to populate the D0303 to MAP. |  | Implemented |  | Interim Release 3 | 2023-07-12 | Block 002 added to IF-037 for use where event code is MSDeapp, this is so that the outgoing MS is informed of who the incoming supplier is so that D303 can be correctly population. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-450 | SC | DI-196 | 2023-06-22 | RECCO |  | Sean Cooper | SRO Design | Change to IF-005 Validation Rules | Change made to IF-005 validation Rules to allow previous MS to update Meter Location only - during the 10 day post appointment period. This will allow for scenarios where there has been relocation only activity immediatly prior to a change in MS. All other MeterUpdate functions apart from Change of Meter Location shall be rejected per wider agreement that only active MS should have the ability to change the characteristics... This change originated from R1 Comments feedback from RECCO |  | Implemented |  | Interim Release 3 | 2023-07-12 | IF-005 Validation rules updated to include new "REG0008 - Amendment Requested cannot be undertaken by Previous Metering Service" error condition and code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-451 | SC | CR-018 | 2023-06-22 | Design Team |  | Sean Cooper | SRO Design | CR - 018 Registration Service OOH Ops | CR18 looks to specify Registration Service Out-Of-Hours Operations. | CR018 | Implemented |  | Interim Release 4 | 2023-08-16 | Following feedback provided on the redlined version of the Operational Choreography, and following discussion on CR018 at PSG, the SRO maintained the DAG Chair’s decision to approve the implementation of CR018. CR Contents incorporated into a new Section 7 of Ops Choreography Document. Updates to clarify low level processing details in Section 7 Out-Of-Hours Processes table. Following feedback from DNO Review - Additional updates to replace the term ‘SLA’ with the phrase “target response time(s)”. Changes to Column headings to ‘When’ across the Operational Choreography document to align with Code Drafting convention. Addition of Intro text and removal of text “or Performance Regime” in Section 5. | Technical corrrection | Supporting Docs | Operational Choreography | MHHSP_OPC001_Operational_Choreography
MHHS-DIN-452 | SC |  | 2023-06-22 | SCS |  | Sean Cooper | SRO Design | Refine Consent Checking Rules on IF-031 | Further refine Consent checking rules so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing . Updates to IF-031 validation rules to reflect this change. |  | Implemented |  | Interim Release 3 | 2023-07-12 | IF-031 validation rules updated per the DIN Details. Consent checking rules added so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-453 | MF | DI-124 | 2023-06-22 | SCS |  | Mike Fensome | SRO Design | Issuing of IF-020's | Highlighted that LDSO's could issue an IF-020 with details of import/export linkages without having received notification from the Supplier |  | Implemented |  | Interim Release 3 | 2023-07-12 | Added note to IF-019 and IF-020 to inform Suppliers that Import/Export linkages could be received via PUB-020 unprompted by the Supplier issuing IF-019. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-454 | SC |  | 2023-06-26 | SCS |  | Sean Cooper | SRO Design | Update to ISD M7 | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service |  | Implemented |  | Interim Release 3 | 2023-07-12 | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service. added rule to support REG0011 logic in IF-031. | Requirement correction | Supporting Docs | ISD Document | MHHSP-DES138-Interface Catalogue MHHSP-EDI021-ISD Entities
MHHS-DIN-455 | SC |  | 2023-06-23 | SCS |  | Sean Cooper | SRO Design | Update Op Choreography (Event Move from IF-013 to IF-014) | Update Ops Choreography to take account of the movement of event [ConsumptionOnDeEnergisedMPAN] which was moved from IF-013 to IF-014 (DIN-255). |  | Implemented |  | Interim Release 3 | 2023-07-12 | IF-014 Deadline split into two. First [ActivePowerRejected] remains UNCHANGED. Deadline for [ConsumptionOnDeEnergisedMPAN] is also UNCHANGED but moved from IF-013 row into IF-014 Row, to mirror the change delivered by (DIN-255). OPC_580 ID details updated in OPC001 Operational Choreography document. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP_OPC001_Operational_Choreography
MHHS-DIN-456 | SC |  | 2023-06-23 | SCS |  | Sean Cooper | SRO Design | Swagger Correction - DI-844 | Corrected x2 invalid referenced to "AssignedMRDRequestEffectiveFromDate" should have been "AssignedMRDEffectiveFromDate" in Block 066 |  | Implemented |  | Interim Release 3 | 2023-07-12 | Corrected x2 invalid referenced to "AssignedMRDRequestEffectiveFromDate" should have been "AssignedMRDEffectiveFromDate" in Block 066 | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-457 | SC |  | 2023-06-23 | SCS |  | Sean Cooper | SRO Design | Change to DTN Validation of D0350 | Implement DTN Validation of D0350 to prevent future dates |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | DTN message changes to be added to DES196 as part of IR5” instead of “Industry CP required | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-458 | SC |  | 2023-06-23 | SCS |  | Sean Cooper | SR Design | New IF-019 Related MPAN Validation Rule | New Validation Rule required for IF-019 to ensure that only Import MPANs can be related. Add to Create and Add Related - this is per REC Shedulle 28 |  | Implemented |  | Interim Release 3 | 2023-07-12 | New Rules added to IF-019, [RelatedAdd] and [Related Create] events to ensure only Import MPANs can be in a related Group. New Error code added to support these new rules REG1067 - Only Import MPANs can become Related | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-459 | SB |  | 2023-06-23 | Utiliteam | 5724 | Richard Palmer | Software Provider | Spec of IF-024 in DEL138 Interface Catalogue | A further suggestion re the Interface Spec for the IF-024: The Event Code list in DI D-999 in Group S0 contains [SN-RemoteEnabled] & [SN-RemoteDisabled]. I would suggest that these are invalid for Segments Advanced and Unmetered. Also [SN-Vacant] would appear to be irrelevant for Segment Unmetered, and I doubt that [SN-NoComms] would be valid either. These existed in v5.0, and are still in v5.1.1. Perhaps the routing rules need some improvement? |  | Closed |  |  |  | No change Required. Useage of these evernt codes is obvious and is described in the Requirments documents as necessary
MHHS-DIN-460 | SB |  | 2023-06-26 | Utiliteam | 5939 | Richard Palmer | Software Provider | PIF-019 structure & Principle -> Principal | Also, in the relationships between MPANs, the ‘main’ one is the ‘Principal’ one – not the ‘Principle’. This will be embarrassing if left uncorrected. It is still in v5.1.2 in IF-019, and it is in many other places. If there is a chance of correction, please take it. |  | Implemented |  | Interim Release 3 | 2023-07-12 | Spelling mistake corrected in Data Catalogue, IF-019, IF-020. Note YAML name also corrected for DI-073. | Data interface correction | Supporting Docs | Interface Changes | MHHSP-DES138-Interface Catalogue Swagger 1.3
MHHS-DIN-461 | SW |  | 2023-06-26 | Greenbird | 1768 | Fredrik Omland | Software Provider | Misalignment between DES-138 and Swagger for DIP Connection Provider ID | In DES-138, In the S1 block, DI-996 (Connection Provider DIP ID) is defined as Optional. But in Swagger, this is defined as mandatory. |  | Implemented |  | Interim Release 3 | 2023-07-12 | Updated Swagger 1.3 so DI-996 in S1 block (Connection Provider DIP ID) is Optional to align with DES-138 | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-462 | SW |  | 2023-06-27 | Design Team |  | Steve Weston | SI Design | Schema Optionality incorrectly defined for some Interfaces | In DES-138, there are are a number of Interfaces where the Schema Optionality is defined as Optional, rather than Mandatory. The list of Interfaces are as follows - IF-050 / B022, IF-023 / B053 and IF-013 / B049 |  | Implemented |  | Interim Release 3 | 2023-07-12 | Updated Schema optionality in DES138 to show that all data items must be present where the block is present in line with updated E2E Solution Architecture for IF-050 / B022, IF-023 / B053 and IF-013 / B049. | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalouge
MHHS-DIN-463 | SW |  | 2023-06-27 | SIMS |  | Kyle Abraham | Software Provider | No ability de-register from receiving Status messages in Swagger | In Swagger, there is a POST method for /statusmessage/config, but there is no DELETE method, so you are unable to delete / de-register for any status messages. Need to update Swagger to ensure this is possible. |  | Implemented |  | Interim Release 3 | 2023-07-12 | Updates made to Swagger 1.3, so there is a DELETE method for /statusmessage/config, so you are now able to delete / de-register for any status messages. Updated so that all of the Interfaces accept the same 4 security headers required for message signature and validation. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-464 | SW |  | 2023-06-27 | SIMS |  | Kyle Abraham | Software Provider | Clarity required on values expected for /dip-channel/{id} for submitEvents on Swagger | The {id} in /dip-channel/{id} for submitEvents on Swagger should accepts values that are the same as the enumeration in DI-000 to ensure consistency. At the moment, this is not clear in Swagger or E2E001 design, so this needs to be updated to make this clearer. |  | Implemented |  | Interim Release 3 | 2023-07-12 | Updates made to Swagger 1.3, so there the correct enumerations / values are available to align with values in DI-000 to ensure consistency and avoid any ambiguity between interfaces and reports. Updated to remove PublicationConfig and RestConfig in favour of a single config WebhookConfig. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-465 | SC |  | 2023-06-28 | RECCO |  | Sean Cooper | SRO Design | Update to BP010 - Related MPANs | The process MPAN for Related MPANs does not clear call out the Rejection pathway. Update Business Process to show rejection process. |  | Implemented |  | Interim Release 3 | 2023-07-12 | BP010B Related MPANs Process updated to show specific Rejection Route. | Process Model correction | Metering Changes | Business Process Documentation | BP010- Changes to MPAN Data
MHHS-DIN-466 | SC | DI-188 | 2023-07-29 | SCS |  | Sean Cooper | SRO Design | Change of MPAN Status during Service Provider Appointment Process. | How should a change of MPAN Status be dealt with whilst there is an ongoing SP Appointment that has not yet reached the stage of IF-034 processing !? If an MPAN is disconnected between PUB-031 acceptance and receipt of PUB-034, the SP PUB-034 Response would be rejected by MPRS due to validation rule REG1001. The appointment would not be progressed but would be stuck in the MPRS queue at status Requested. Could resolve by amending REG1001 validation on IF-034, to not apply to event codes MSAppSPResponse or DSAppSPResponse. |  | Implemented |  | Interim Release 3 | 2023-07-12 | Resolved following discussion with SCS, Agreed that SCS will take no action until the IF-034 has been processes. A change to REG1001 validation on IF-034, to not apply to event codes MSAppSPResponse or DSAppSPResponse, is required to allow the IF-034 to processes normally (when where MPAN is disconnected)... Following processing of the IF-034 RESG will then immediatly issue an IF-035 with reason code of "1- Lapsed as MPAN Status is Disconnected" ... ... Agreed that this was best resolution both for REGS processing rules and participants as no change to currently expected message patterns/ordering. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-467 | SC |  | 2023-07-29 | ESG |  | Sean Cooper | SRO Design | Review of IF-035/IF036 Data Item Obfuscation | Review of IF-035/IF-036 Data Item Obfuscation |  | Implemented |  | Interim Release 4 | 2023-08-16 | Various updates to obfuscation on IF-036 to align with IF-035. DI-019/DI-800/DI-809/DI-207 obfuscated for Data Service DI-020/Di-800/DI-126/DI-842/DI-209/Di-844/DI-811/DI-208 /DI-018 obfuscated for Metering Service | Data interface correction | Supporting Docs | Interface Catalogue | MHHS-DES138-Interfaces
MHHS-DIN-468 | SC |  | 2023-07-29 | Helix |  | Sean Cooper | SRO Design | Routing of IF-020 | Helix have confirmed that they DO NOT need to receive Related/Linked MPAN information therefore an update is required to REMOVE MDS from the receipient list for this IF-020 |  | Implemented |  | Interim Release 3 | 2023-07-12 | IF-020 Routing table has been updated to REMOVE MDS as being a recipient of any IF-020 messages. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-469 | ME |  | 2023-06-30 | SRO Design Team | 2109 | Rob Golding | SRO Design | Removal of Z0 & Z1 data items in ERI011B - ECS Reports External | Z0 & Z1 data items to be removed from from the each of the MHHS reports within ERI011B - ECS Reports External as they are no longer in the common block |  | Implemented |  | Interim Release 3 | 2023-07-12 | Removed Z0 & Z1 data items from all MHHS reports in ECS external reporting artefact | Data interface correction | Minor | ECS Reports | ERI011B - ECS Reports External
MHHS-DIN-470 | SW |  | 2023-06-29 | Callisto | 1805 | Seth Chapman | Software Provider | Clarity on nullable fields | Section 4.2.2 in the E2E design provides information on Optional / nullable fields, but worked examples would provide further clarity for each of the data types / link to JSON specification. |  | Implemented |  | Interim Release 3 | 2023-07-12 | Updated section 4.2.2 with worked examples for each data type to provide additional clarity. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-471 | MH |  | 2023-06-30 | Helix |  | Derek Weaving | Central Body | Update to REP-003 in ERI011B - ECS Reports External | R019 parent should be R017 in the ECS Reports External and Swagger |  | Implemented |  | Interim Release 3 | 2023-07-12 | Updated R019 parent to R017 for REP-003 in ERI011B - ECS Reports External. Swagger v1.3 updated to align with changes within ECS reports artefact. | Data interface correction | Minor | Interface Changes | ERI021 -ECS Reports External Swagger 1.3
MHHS-DIN-472 | SW |  | 2023-06-29 | SRO Design Team | 2006 | Rob Golding | SRO Design | Onboarding migration from Test to Production. | “The programme is to implement a strong PKI policy but as per the diagram states that that on promotion, parties will be able to copy their Test setup and to use that for connecting to the Prod environment. - steps 1-8 - There are no steps in this sequence that test the connectivity to the Live DIP environment. To this point the only connectivity testing has been to the Test environments. This is a significant failure point / risk. At this point Webhooks and certificates will change (mTLS and JSON signing) from those used in Test as well as potentially some of the PKI resources assigned to roles ( those used in test may not be applicable to Prod) we would expect that this would require a new Connectivity proving period with the Prod environment similar to that being developed for CIT. Without such proving, how can the programme assume all parties will connect to the Prod environment successfully and ensure minimal impact to migration events”. |  | Closed |  |  |  | Solution yet to be defined This an Elexon/DIP Manager deliverable not a programme deliverable
MHHS-DIN-473 | SB |  | 2023-06-30 | MHHS | 2111 | Jason Brogden | Network Operator | Definition of Network Operations | Issue: There is a lack of clarity in the scope of Network Operations activities in testing. Action to Resolve: Add a definition to the Programme Glossary that makes clear the scope of Network Operations (as referenced in Testing material) is equivalent to the scope of LDSO activities in the MHHS Design Baseline: Network Operations systems and services are those that are required to deliver the elements of the MHHS Design Baseline that are allocated to the LDSO role. Communicate this to the DNO and iDNO community and associated service and software providers. For the DIN Log, we can then focus on updates to the BRS to give the necessary clarity on the scope of MHHS Design. Issue: There is a lack of clarity in the scope of LDSO activities in the MHHS Design Baseline as BRS005 implies MHHS-related processing requirements at LDSOs for received DIP messages, whereas the BPs and BPDs define the scope of MHHS as ending at the receipt of DIP messages. BRS005 is described as “For Guidance Only” at the top and this is to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing). Action to Resolve: For the avoidance of doubt and to provide clarity to BRS005, it is proposed to change the “For Guidance Only” note at the top of BRS005 to the following description as per the above: BRS005 is provided For Guidance Only to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing). |  | Implemented |  | Interim Release 3 | 2023-07-12 | LDSO Requirements document updated with the following text, "BRS005 is provided For Guidance Only to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing)." | Requirement correction | Minor | Business Requirements Documentation | BRS-005 LDSO Overview.xls
MHHS-DIN-474 | ME |  | 2023-07-03 | MHHS |  | Kevin Spencer | SRO Design | Creation of new ECS data items and blocks across multiple reports and/or data catalogue | Report definitions incorrect and require updates and new data items following internal review |  | Implemented |  | Interim Release 4 | 2023-08-16 | Addition of data items DI-503, DI-505-DI-515 to data catalogue and across ECS reports artefact. MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal Missing data items added to data catalogue Di-403/DI-404/DI-514/DI-515 | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-475 | ME |  | 2023-07-03 | MHHS |  | Kevin Spencer | SRO Design | Update to block names, data items and descriptions | Report definitions incorrect and require updates and new data items following internal review |  | Implemented |  | Interim Release 4 | 2023-08-16 | Update to block names, DTN references, data items, descriptions and reordering of data item blocks to exisiting reports in MHHSP - ERI011B - ECS Reports - External | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-476 | SW |  | 2023-07-03 | Greenbird | 2035 | Fredrik Omland | Software Provider | Inconsistency between enum fields and nullable definition | Looking at DIP Interfaces Swagger 1.1 (also 1.2 + 1.3), the enum typed fields that are nullable may not comply with OpenAPI specification (for 3.0.x). The topic around enum fields with nullable: true has been clarified/answered by OAS project (amended in spec version 3.0.3 in 2021): (Reference: https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md ) |  | Implemented |  | Interim Release 3 | 2023-07-12 | To align with Open API spec clarification at https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md, we have updated all Data Types that are nullable and have an enum to align as follows: Following discussion, have decided to align with OpenAPI 3.1 DI-076-Estimation-Reason-Code: description : Used inconjunction with Settlement Period Quality Indicator to explain why data has been estimated type : string nullable: true maxLength : 2 example : '1' enum: - '1' # OptOut - '2' # Missing .. - '8' # Disconnected - '9' # Consumption Amendment - '10' # NonSmart - null The Data Types affected / updated as follows: --- DI-039-Load-Shape-GSP-Group-ID --- DI-076-Estimation-Reason-Code --- DI-096-Site-Visit-Check-Code --- DI-126-Traditional-Fall-Back-Read-Frequency --- DI-137-IHD-Install-Status --- DI-150-Annual-Consumption-Quality-Indicator --- DI-166-Supplier-Consumption-Amendment-Reason-Code | Data interface correction | Minor | Interface Changes | Swagger 1.3
MHHS-DIN-477 | SW |  | 2023-07-03 | MHHS |  | Steve Weston | SRO Design | Swagger alignment to OpenAPI 3.1 specificiation | Align with Open API specification 3.1 to remove nullable :true and replace with type declarion ie, type:[string:”null”] |  | Initial Assessment/Updating |  | Interim Release 8 | 2024-03-20 | Further details of the solution are under discussion/review. | Design Ambiguous | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-478 | SW |  | 2023-07-03 | MHHS |  | Rob Golding | Central Body | IF-021 max number of days of consumption data | In the Release 2 version of DES138 a limit was introduced that asked Participants not to submit more than 150 Settlement Days’ worth of data in a single message. The value of 150 was proposed as this meant a single message would realistically be ~600KB in size. We’ve had some queries regarding this value, the proposal is to increase sizing from 150 to 194 day message and the size increases from 600KB to ~780KB for IF-021 message. ECS will need to validate the message contents. However, rather than letting a ‘large’ IF-021 message traversing though the DIP, the proposal is to limit the IF-021 on ingress to the DIP and a single request will have a limit of 1MB – this will be done at the API level. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Agreed to limit the number of MQ IDs per IF-021 submission to ONE only and limit settlement days to 200. Swagger has been updated to limit the number of MQIDs to 1. Swagger updated to limit the maximum number of Settlement Days to 200. DES138 also updated to aligned with the above changes for IF-021. | Data interface correction | Minor | DES138 and Swagger | DES-138 and Swagger 1.4
MHHS-DIN-479 | SC |  | 2023-07-03 | SCS |  | Maddison | SCS | Change to Consent Notification on IF-036 | SCS have suggested that B068 should only be required for DSApp Events. |  | Implemented |  | Interim Release 3 | 2023-07-12 | Block 068 on IF-036 amended to that it is only Mandatory for DSApp Events. | Data interface correction | Supporting Docs | Interface Change | DES138-InterfaceCatalogue
MHHS-DIN-480 | SC | DI-195 | 2023-07-03 | SCS |  | Maddison | SCS | Reverse DIN-105 | SCS have confirmed that it is possible currently and should continue to be possible to manage MPAN Linkages whilst MPAN(s) are at Created Status. Therefore we have reversed the change implemented at part of DIN105 and now allow processing of IF-019 if mpan status = "Created" |  | Implemented |  | Interim Release 3 | 2023-07-12 | SCS have confirmed that it is possible currently and should continue to be possible to manage MPAN Linkages whilst MPAN(s) are at Created Status. Therefore we have reversed the change implemented as part of DIN105 and now allow processing of IF-019 if mpan status = "Created" | Data interface correction | Supporting Docs | Interface Change | DES138-InterfaceCatalogue
MHHS-DIN-481 | SW |  | 2023-07-06 | Elexon | 2106 | Nigel Rees | Central Body | REP-003 inconsistency between DES-138 | We have a contradiction between the DT-023 and the swagger spec. As there is an example we will implement based on the example but it looks like the person who wrote the ECS report catalogue used the correct convention. e.g. on REP-003 we have DT-023 as NUM (16,6). If we follow the convention used in the DIP interface spec, this would translate to 1234567890123456.123456, however the swagger suggests 123456789.123456 Screenshot from REP003 in external ECS reporting catalogue https://app.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.3#/components/schemas/DT-023-Positive-Decimal-9-6 DT-023-Positive-Decimal-9-6: description: Number (9,6) format type: string pattern : ^[0-9]\d{8}(\.\d{6})?$ example: 123456789.123456 |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Two new data type references have been created DT-024 and DT-024N. For NUM(16,6) data type within ECS reports/ECS data catalogue replace DT-023/DT-023N with DT-024/DT-024N. DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. 31/08: A reconciliation exercise is being carried out internally of the ECS data catalogue to assess data types. Further work may be required to swagger following the reconciliation. Reconciliation task has been completed which has resulted in updates to the MHHS Data Types within the ECS Reports data catalogue. MHHS data type references in Swagger have also been updated to align with these changes. An example of how MHHS data types should be interpreted: String 17 should be interpreted as NUM(±9.6) which can be physically represented in this way for a negative number -123456789.123456 or for a positive number it will be 1234567890.123456. The objection has been removed. | Reporting correction | Minor | ECS Reports | "MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2" Swagger
MHHS-DIN-482 | KH |  | 2023-07-10 | C&C | 2394 | Hazel Cotman | Software Provider | Interim Release 2 query - IF-018 | LDSO’s are not detailed as ‘To Parties’ within IF-018 flow, however, the LDSO is a secondary routing party for updates to the Domestic Premise, Energy Direction Indicator, and the Metered Indicator |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | LDSO's added to the To party list of IF-018 | Data interface correction | Minor | Interface Catalogue | DES138
MHHS-DIN-483 | KH |  | 2023-07-10 | BGAS | 2410 | Neil Stranger | Supplier | MHHS Design Query - date/ time in DES138 | In DES138 there are a number of data items that are defined as having a date/time structure, but the name and description only refer to the date element whereas others refer to date and time. Therefore for those that make no reference to time we need to be 100% clear if the time should be when the event occur or should it be defaulted to say midnight. This is to ensure consistent population/use across the market. |  | Closed |  |  |  | Related to a Design Principle and agreed as per E2E Architecture
MHHS-DIN-484 | SW |  | 2023-07-10 | MHHS | 2352 | Martin Freeman | Central Body | Clarity on RecipientId and SenderID in StandardResponseBodyType | RecipientID in the Standard Response Body is a mandatory field. When submitEvents (or in IR2 dip-channel) is called, the DIP synchronously returns a Standard Response Body. At this point the DIP does not even know what message recipients the message will be routed too, since the response is returned synchronously whereas routing is performed asynchronously. So the DIP has no way to know what to set recipientID to. It is also important to note that a message can be received by multiple recipients, yet this recipientID is a scalar that only supports being set to a single value. So it isn't clear how that could work. |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Update section 4.6.1 in the E2E001 Design document to provide better clarity on how SenderID and RecipientID are populated in the StandardResponseBodyType. Provided worked examples for L1-L6 to illustrate this as examples. Updated Swagger 1.4 to align with the above. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-485 | SW |  | 2023-07-10 | MHHS | 2380 | Steve Weston | Central Body | Unable to identify Recipient on DELETE and some POST methods | For the DELETE methods in Swagger for StatusMessage and PublicationConfig, need to update the method so you can identify the correct recipientID to be used for the method call. Some frameworks will ignore a body on a DELETE method as being incompatible with the semantics of the DELETE method, and the correct RESTful implementation would be something more along the lines of "DELETE dip-channel/{id}/{role}/pubconfig". Which of course raises the question of whether the POST message should be refactored for consistency. The issue is more widespread than just the DELETE methods, it also affects some of the POST methods where a recieipent ID is required |  | Implemented |  | Interim Release 4 | 2023-08-16 | Design changes required to Swagger 1.4 to support updates to API endpoints for DELETE API verbs to ensure we are able to remove the correct StatusMessage or PublicationConfig for the appropriate recipient combination. The issue also affects some of the POST methods where a recipient ID is required, e.g webhook config. A standard pattern is proposed where a recipeint id is specified in the path. Updates to section 4.5.1 and 4.7 also made to E2E001 design document to ensure the document provides any clarity required. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-486 | SB |  | 2023-07-11 | MHHS | 2107 | Rob Golding | Central Body | DES138 and message addressing information | Please can you raise a DIN to cover the following request from Participant to clarify the From and To Parties at the top of each sheet to align with the role codes the programme is using and defined in the E2E Solution Architecture document. And if these ‘pure’ roles code could be included in the introduction sheet that would certainly help. More detail can be seen in the Ticket |  | Implemented |  | Interim Release 4 | 2023-08-16 | Update the role codes in DES-138 for the From / To Parties for each of the Interfaces to align with other documents including E2E001. No change to information in the Introductory section in DES-138 required. | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-487 | SW |  | 2023-07-11 | MHHS | 2379 | Martin Freeman | Central Body | Clarity on schema vs data validation failures, with updated examples. | In section 4.4.4.2, there are some examples that incorrectly return a 207 when they have failed schema validation. |  | Implemented |  | Interim Release 4 | 2023-08-16 | In section 4.4.4.2, there are some examples that incorrectly return a 207 when they have failed schema validation. E2E001 section 4.4.4.2 has been updated to illustrate 2 examples. One that returns a 201 Created (2 messages as part of the HTTP Request, both pass validation) and another example that returns a 207 (2 messages part of the HTTP Request, but 1 does not pass validation). | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-488 | ME |  | 2023-07-11 | MHHS | 1506 | Steve Weston | SRO Design | Correct Reporting Cat vs Swagger | Reinstated DI-484 "Settlement Period Duration" and added into R Groups as required |  | Implemented |  | Interim Release 4 | 2023-08-16 | Reinstated DI-484 "Settlement Period Duration" and added into R Groups as required in Swagger 1.4 | Data interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-489 | MF |  | 2023-07-11 | Design Team |  | Mike Fensome | SI Design | Schema Optionality incorrectly defined for Common Block | In DES-138, the Common Block shows some fields where the Schema Optionality is defined as Optional, rather than Mandatory. The list of Blocks are as follows - Common Block: S1, D0, A0 |  | Implemented |  | Interim Release 4 | 2023-08-16 | Update Schema optionality in DES138 to show that all data items must be present where the block is present in line with updated E2E Solution Architecture. Common Blocks impacted: S1, D0, A0 | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-490 | SW |  | 2023-07-11 | MHHS | 2395 | Martin Freeman | Central Body | Level 1 validation clarity for POST /statusmessage be the same as for POST /dip-channel/{id} | The E2E001 v3.2 (section 4.4.3) describes how for the Send Messages API, when the DIP performs level 1 validation, if any message in the request fails validation then the entire request is rejected. Section 4.6 Send Status Messages API does not describe the DIP validation for status messages at all. Should validation for POST /statusmessage be the same as for POST /dip-channel/{id}, in that a level 1 validation failure for any message should fail the entire request, or should messages that pass validation be accepted and messages that fail be rejected independently? |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | This should be consistent across all interfaces in that a schema validation failure for any message should fail the entire request. In the E2E001 design, sections 4.4.3 and 4.6 are to be updated to reflect this / provide the appropriate level of clarity. This issue affects both the http delete operations. Easy to fix, same fix as the post need to include the webconfigas a parameter | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-491 | SB |  | 2023-07-11 | Utilita | 2408 | Adam Barnes | Supplier | DES138 v5.2.1 | IF-035 tab for the bottom 3 entries it still refers to the previous version definition of routing parties – we expect this to be a slight oversight as SDSS is no longer defined as a recognised party? |  | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18
MHHS-DIN-492 | KH |  | 2023-07-11 | Stark | 2125 | Matthew Peters | Supplier | IF-034 Proposed Appointment Response Code Formatting | The data type within DI-143 block for IF-034 and IF-035 needs to change from String 200 to Array because there is a possibility of getting more than 1 rejection code. |  | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18
MHHS-DIN-493 | SC |  | 2023-07-12 | SCS |  | Sean Cooper | SRO Design | Changes to IF-019 Secondary MPAN validation | SCS had originally suggested a validation rule to prevent Secondary (Related) MPANs being linked to an Export MPAN. However, RECCO and EON have highlighted there are a very small number of scenarios where this might be the case. Following further discussions with SCS they are now happy to remove this rule (REG1068) |  | Implemented |  | Interim Release 4 | 2023-08-16 | IF-019 - REG1068 check for Secondary MPAN Linkage to export REMOVED | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-494 | SW |  | 2023-07-12 | Callisto | 2462 | Neil Edney | Software Provider | Incorrect Min and Max Values for DI-091-Number-Of-Displayed-Register-Digits | DI-091-Number-Of-Displayed-Register-Digits currently has a minimum of 1 and maximum of 1, when this should be 5 and 6 respectively to align with DES-138 as this is an Integer. |  | Closed |  |  |  | This DIN is now superseded by DIN-615 following on from DIN-574. Text against Number of Register Digits field amended to say "per the manufacturer specification". Swagger validation of this field updated to match SCS logical test ie value can be 0-9. This DIN was to ensure there was consistency in Swagger 1.4 to align with DES-138 so that min and max was 5 and 6 respectievly. This objection is related to the values in DES-138, to update from 5 and 6 to 0 and 9, and then align Swagger to the values in DES-138. | No Change
MHHS-DIN-495 | SC |  | 2023-07-12 | Design Team |  | Sean Cooper | SRO Design | Correction to BP003 | IF-035 for Trad/Advanced meters was previously shown as being direct interaction between REGS and MS ... Changed to show message as flowing via the DIP |  | Implemented |  | Interim Release 3 | 2023-07-12 | IF-035 for Trad/Advanced meters was previously shown as a flow being direct interaction between REGS and MS. Changed to show message as flowing via the DIP (at step 90). Also change applied to Forward migration process for consistency. | Process Model correction | MPAN Ownership | BP003 | MHHSP-BP003-Change of Service - Data Service MHHS-DEL964 BPM-003 - Change of Servie - Data Service - Forward Migration
MHHS-DIN-496 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 | MHHSP-METH001_SDS_Validation_Estimation 5.1 section 2.7 States "SDS shall inform the Supplier using the Meter Reading Reason Code on the IF-041/PUB-41" . There is no Meter Reading Reason Code on the IF-041 in DES138 v5.1.2. Therefore, either Meter Reading Reason Code should be included in DES138, or this requirement should be removed. |  | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Remove the following from METH001: 'Where consumption data has been deemed invalid the SDS shall inform the Supplier using the Meter Reading Reason Code on the IF-041/PUB-41.'
MHHS-DIN-497 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 | MHHSP-METH001_SDS_Validation_Estimation 5.1 Section 5.4 Where DA records are < 90 days from UTC date this is inconsistent with Method 4, which states "DA is available [either in the past or future] and less than [3] months different from the UTC Date requiring a daily Meter advance". |  | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Be consistent - use either 90 days or three months within the document
MHHS-DIN-498 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 Method 13 | MHHSP-METH001_SDS_Validation_Estimation 5.1 Method 13 This describes the outcomes for Smart and Advanced meters. Does this imply that traditional meters should have zero consumption submitted to settlements, or should Method 13 text be adjusted to include trad meters? ALSO If actual data is recovered, or an Advance Meter Reading is received, and this indicates zero consumption, should this be submitted to settlements? The first part of the sentence implies it should be submitted, and the brackets imply it shouldn't. |  | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Alter wording of Method 13 to reflect we shouldn't be sending estimates for Deenergised trad meters as well as Smart and Advanced, AND 'there is no need to submit zero consumption for de-energised MPAN's' needs changing to refer to 'zero ESTIMATED consumption'
MHHS-DIN-499 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Alignemtn of Estimation Reason Codes | METH001 refers to Estimation Reason Code 'Adjustment'. DES138 refers to 'Consumption Amendment' Assume these are the same thing and need to be aligned between both sets of documentation |  | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Align Method Statements to match the Estimation Reason Codes within DES138
MHHS-DIN-500 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | ISD Entity M17 Example Correction | MHHSP_EDI021_ISD_Entities 5.1 Entity id M17 Industry Standing Data: MHHS Entities/Data Items v5.1 ISD Entity Id M17 - Valid Consent Granularity Combinations, includes combination I¦F¦S¦D. According to Decision 2 in "https://www.ofgem.gov.uk/sites/default/files/docs/2019/06/access_to_data_consultation_ofgem_response_0.pdf" a non-domestic customer is unable to opt out. The OFGEM document states "There will be no opt out possible for microbusinesses in relation to data for settlement purposes". Therefore, I ¦ F ¦ S ¦ D is not a valid combination. |  | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Remove I ¦ F ¦ S ¦ D from the example list
MHHS-DIN-501 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Addition of Method 13 to METH002 | MHHSP-METH002_ADS_Validation_Estimation 5.1 Section 3.16 States "The below estimation methods are based on those used in the Smart Data Service (SDS) Method Statement. For that reason, methods 0, 1, 6, 11 and 13 have been omitted as they are only applicable to Smart meters." However, method 13 is "Estimation for a Site where Supply is de-energised" and this is included in METH002 in section 2.29. The statement is wrong as some of the methods have been renumbered in METH001 since this was written. |  | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Update METH002 to add MEthod 13 back in
MHHS-DIN-502 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | SP Quality Indicator Clarification | MHHSP-METH001_SDS_Validation_Estimation 5.1 It is our assumption that if NO estimation is required, the Settlement Period Quality Indicator should be set to "A". This is however, never explicitly mentioned. The only mention of using value "A" is for method 1. |  | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Update artefacts to clarify when to use A as the SEttlement Period Quality Indicator value
MHHS-DIN-503 | SW |  | 2023-07-13 | SIMS | 2439 | Martin Freeman | Central Body | S1.senderUniqueReference interface component is too small to identify the message interface | DES138 and the E2E001 the S1.senderUniqueReference property has a 3 digit component that contains the interfaceID of the message. However since the reporting interfaces reuse the same interface numbers as the standard interfaces, and some reporting interfaces have 4 character interface identifiers, this means this component is not sufficiently large to unambiguously identify which interface a given senderUniqueReference was generated for. This also applies for TransactionID. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Update any Data Items that utilise InterfaceID to align with the enumeration of values defined for DI-000 so that this is unique across all interface / report types. This is for data types SenderUniqueReference (DI-995) and TransactionID (DI-990). This change will require updates in DES-138, E2E001 and Swagger 1.4. In DES-138, DT-014 has been updated to String65 from String60 to support Interface being updated from 3 to 8 to align with DI-000 (so for IF-003, rather than 003 being included in the transactionID / senderUniqueReference, this will be IF003 with no hyphen). In Swagger, DT-014 has been updated to max length 65, with examples updated. E2E001 updated examples for senderUniqueReference and TransactionID to align with the above. | Design Ambiguous | Supporting Docs | DES-138, E2E001 and Swagger 1.4 | DES-138-interface catalogue, E2E001 E2E Architecture document and Swagger 1.4
MHHS-DIN-504 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Clarification of link between IF22/IF23 | DES138 IF-022/023 IF an IF-022 or IF-023 is re-issued, can you confirm that they will be reissued as a pair so that the totals align? The issue is if an updated IF-022 is issued with new values, should the SDS/ADS await an updated IF-023, or not? How can the SDS/ADS pair the IF-022 and IF-023 without doing their own summations? |  | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Update BRS007 to show that a re-run of IF-022 will result in a rerun of IF-023
MHHS-DIN-505 | BK |  | 2023-07-13 | SCS |  | Sean Cooper | SRO Design | DUoS Tariff ID to hold values from 1-3 in length | The DUoS Tariff ID needs to be updated in Swagger and the Interface Catalogue so that it can hold values from 1 to 3 in length in order to align with ISD. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Update DUoS Tariff ID to hold values from 1 to 3 in length in Swagger and Interface Catalogue | Data interface correction | Supporting Docs | Interface Catalogue and Swagger 1.4 | DES138-InterfaceCatalogue Swagger 1.4
MHHS-DIN-506 | BK |  | 2023-07-13 | Design Team |  | Sean Cooper | SRO Design | Renaming of IF-014 | Rename IF-014 to clarify the purpose |  | Implemented |  | Interim Release 4 | 2023-08-16 | Changed to "UTC Settlement Period Consumption Data (Warnings & Rejections)". Interface description and notes updated to reflect that IF-014 could also contain warnings for Consumption on De-enegised sites. | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-507 | SC | DI-194 | 2023-07-14 | Design Team |  | Sean Cooper | SRO Design | Clarification of IF-036 Routing Requirements | Update IF-036 to clarify / provide additional info on the routing destinations of IF-036 |  | Implemented |  | Interim Release 4 | 2023-08-16 | Added following Text: Primary Routing Participants for IF-036 MSAppActive • Supplier (i.e. the supplier who initiated the appointment, either current in the case of Change Of / Update to SP’s, or incoming in the case of a COS) • Metering Service (i.e. the Metering Service being appointed) • [Partner] Data Service (i.e. the Data Service in effect on the App Start Date of the MS Appointment – this could be either an ‘existing’ Data Service in the case of an MS Only appointment OR the ‘incoming’ Data Service with a coincident App Start Date to that of the [incoming] Metering Service • Linked Supplier(s) – (ie the Supplier(s) with responsibility for the Linked [Import/export] MPANs on the App Start Date of the Metering Service Appointment) DSAppActive • Supplier (i.e. the supplier who initiated the appointment, either current in the case of Change Of / Update to SP’s, or incoming in the case of a COS) • Data Service (i.e. the Data Service being appointed) • [Partner] Metering Service (i.e. the Metering Service in effect on the App Start Date of the DS Appointment – this could be either an ‘existing’ Metering Service in the case of an DS Only appointment OR the ‘incoming’ Metering Service with a coincident App Start Date to that of the [incoming] Data Service • Linked Supplier(s) – for Advanced Segment Meters only - (i.e. the Supplier(s) with responsibility for the Linked [Import/export] MPANs on the App Start Date of the Metering Service Appointment) | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-508 | SC |  | 2023-07-17 | Design Team |  | Sean Cooper | SRO Design | Addition of MP Status and RMP Status Effective From Dates to IF-050 | Addition of MP Status and RMP Status Effective From Dates to IF-050 ( Linked to DIN 318 ) |  | Implemented |  | Interim Release 4 | 2023-08-16 | New Data Items Created and added to IF-050 in block B079 and the data catalogue tab: DI-167 RMP Status Effective From Date DI-168 MP Status Effective from Date (DIN 318 Closed as duplicate) | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-509 | SW |  | 2023-07-18 | MHHS |  | Steve Weston | Central Body | Missing Archival NFR Information | There is no detailed non-functional requirements in relation to data archiving, retrieval, archival tiers, recovery from archival so we need to update the NFR's to ensure these are included. |  | Open - awaiting assessment |  | Interim Release 7 | 2024-01-19 | Further details of the solution are under discussion/review. | Clarification
MHHS-DIN-510 | SW |  | 2023-07-18 | MHHS | 2675 | Steve Weston | Central Body | Properties on block B047 | The Swagger definition has the properties ‘sp’,’v’,’q’,’e’ and ‘arc’ which matches the items in red. However the data catalogue has different YAML names. YAML Swagger names have to be updated in DES-138 to match the above characters. |  | Implemented |  | Interim Release 4 | 2023-08-16 | This was done to reduce IF-021 content size, but the DES-138 5.4.1 YAML needs to be updated to align with Swagger 1.4 - the YAML names should be as follows DI-082 ‘sp’ - B052 (IF-022), B047 (IF-021) DI-147 ’v’ - B047(IF-021, 4, 16) DI-083 ’q’ - B047 (IF-021, 14, 16) DI-076 ’e’ - B047 (IF-021, 14, 16) DI-166 ‘arc’ - B073 (IF-027 / 28) Swagger 1.4 has been updated to align for the approrpiate blocks above to ensure consistency across the data catalogue. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-511 | BK | CR027 | 2023-07-18 | Eastern Power Networks |  | Peter Waymont | Network Operator | DUoS E-Billing DIP Message for MHHS | A new flow needs to be introduced for e-billing of site-specific DUoS in the post Market-Wide Half-Hourly Settlement (MHHS) environment because the existing flow uses the DTN and all other DUoS data will be DIP based. The change is required in order to continue to operate the site specific DUoS billing process in the MHHS environment. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the HH data sent by Data Services to the LDSO for use in DUoS billing, using IF-021/IF-013/IF-014. At present DUoS billing systems can send the D2021 data flow as a form of e-billing for site-specific DUoS, using the DTN. As DUoS billing systems will need to interact with the DIP for migrated site-specific billed customers, it is preferable that the outputs are also DIP messages, to enable the parties to move forward completely in the new environment. A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors) and receivers (suppliers) of the flows has identified the desired flow content and now wish to bring this to the Programme to ensure that it can be delivered in readiness for migration. | CR027 | Closed |  |  |  | Covered as part of CR019
MHHS-DIN-512 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Amendments to Swagger and ECS data catalogue REP-002 | Max length for DI-345 DUoS Tariff Id to be updated in line with ECS data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated to ensure DI-345 DUoS Tariff ID aligns with ECS Data Catalogue - max length of string = 3. | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-513 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Custom block correction REP-002 | Block name to be updated to tariffCharacteristics in Swagger. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated for REP-002 custom block to fix typo from tarrifCharacteristics to tariffCharacteristics to align with ECS Interface Catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-514 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Amendments to Swagger and ECS data catalogue REP-002a | Max length for DI-345 DUoS Tariff Id to be updated in line with ECS data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated to ensure DI-345 DUoS Tariff ID aligns with ECS Data Catalogue - max length of string = 3. | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-515 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Custom block correction REP-002a | Block name to be updated to tariffCharacteristics in Swagger. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated for REP-002 custom block to fix typo from tarrifCharacteristics to tariffCharacteristics to align with ECS Interface Catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-516 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Update DI-300 with Minimum value REP-003 | DI-300 to be updated in swagger with a minimum value of 100 as per ECS data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | DI-300 updated in Swagger 1.4 with a minimum value of 100 as per ECS data catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-517 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update data item type in ECS data catalogue REP-003 | DI-325 data type to be updated in data catalogue to (NUM 4,2) in line with swagger |  | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to NUM(4,2) for DI-325. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Cataloue correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-518 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Inclusion of Max/Min value for DI-496-REP-003 | Update ECS data catalogue with Min value of 1 and Max value of 48 |  | Implemented |  | Interim Release 4 | 2023-08-16 | MIn and Max Column of MHHS ECS data catalogue updated with 1 and 48 respectively. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-519 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Max value change in swagger for DI-496 | Update Max value to 48 for DI-496 in swagger |  | Implemented |  | Interim Release 4 | 2023-08-16 | DI-496 in Swagger 1.4 updated to have a Max value of 48 | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-520 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-359 data type REP003 | Update DI-359 data stype to String 16 in ECS data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-359. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-521 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-360 data type REP003 | Update DI-360 data stype to String 16 in ECS data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-360. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-522 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-362 data type REP003 | Update DI-362 data stype to String 16 in ECS data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-362. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-523 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-324 data type REP003 | Update DI-324 data stype to String 16 in ECS data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-324. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-524 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | DI-363 missing from ECS data catalogue | Update ECS data catalogue by adding in missing DI-363 |  | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data catalogue updated with the addition of missing data item DI-363. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-525 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-364 data type in REP003 | Update DI-364 data stype to String 17 in ECS data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-364. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-526 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-365 data type in REP003 | Update DI-365 data stype to String 17 in ECS data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-365. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-527 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-366 data type in REP003 | Update DI-366 data stype to String 17 in ECS data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-366. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-528 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-367 data type in REP003 | Update DI-367 data stype to String 17 in ECS data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-367. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-529 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-368 data type in REP003 | Update DI-368 data stype to String 17 in ECS data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-368. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-530 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Wrong data item referenced in swagger | Wrong data item referenced in R022. Daily Period BM Unit Total Allocated Volume must be changed to BM Unit Allocated Demand Disconnection Volume |  | Implemented |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 has BM Unit Allocated Demand Disconnection Volume (DI-241) in R022 | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-531 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Data type update in swagger for DI-341 | DI-341 data type to be changed to String 18 as per data catalogue |  | Closed |  |  |  | Closed. This is defined a Integer in the format 9,6 in Swagger. | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-532 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Wrong data item referenced in swagger | Wrong data item referenced in R022. settlementPeriodID must be changed to Settlement Period |  | Implemented |  | Interim Release 4 | 2023-08-16 | Updated Swagger 1.4 so that R022 references DI-946 (SettlementPeriod) rather than DI-307 (SettlementPeriodID) | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-533 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-339 data type in REP-003 | Update DI-339 data stype to String 17 in ECS data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-339. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-534 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-369 data type in REP-003 | Update DI-369 data stype to String 17 in ECS data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-369. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-535 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-370 data type in REP-003 | Update DI-370 data stype to String 17 in ECS data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-370. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-536 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-322 REP003 | Update Min column of ECS data catalogue with 0 |  | Implemented |  | Interim Release 4 | 2023-08-16 | DI-322 Minimum column of MHHS ECS data catalouge updated with 0 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-537 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-322 REP003 | Update Max column of ECS data catalogue with 99.99 |  | Implemented |  | Interim Release 4 | 2023-08-16 | DI-322 Maximum column of MHHS ECS data catalouge updated with 99.99 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-538 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-323 REP003 | Update Min column of ECS data catalogue with 0 |  | Implemented |  | Interim Release 4 | 2023-08-16 | DI-323 Minimum column of MHHS ECS data catalouge updated with 0 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-539 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-323 REP003 | Update Max column of ECS data catalogue with 99.99 |  | Implemented |  | Interim Release 4 | 2023-08-16 | DI-323 Maximum column of MHHS ECS data catalouge updated with 99.99 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-540 | SW |  | 2023-07-14 | Elexon | 2684 | Nigel Rees | Central Body | IF-13 run number | In DES-138, Run Number in IF-013 Interface is 3 chars, yet in Swagger and ECS Reports, this is 7 characters long. We need to update DES-138 to align with Swagger and ECS reports. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Updated IF-013 to show DI-161 (Run number) as number 7 to be consistent with Data Catalogue/ Swagger and Reports | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-541 | MF |  | 2023-07-19 | ESG | 2623 | Patricia Parker | Software Provider | SSC and Profile Class validation | Validation needs to be reviewed to enable the provision of just SSC or Profile Class updates as part of [SSCandProfileClass] event code updates in IF-025 |  | Implemented |  | Interim Release 4 | 2023-08-16 | Updated conditionality on IF-025 and IF-026 for DI-122 (Profile Class) and DI-123 (SSC) to "Mandatory for Traditional Meters (if changing)" to allow just SSC or Profile class updates to be provided. Validation rules updated accordingly in IF-025. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-542 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-159 in data catalogue REP004 | Update Min column with 25 in data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | DI-159 Minimum column of MHHS ECS data catalouge updated with 25 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-543 | MF |  | 2023-07-19 | Design Team |  | Mike Fensome | SRO Design | IHD, SMSO, SSC and Profile Class conditional validation | Update validation rules to ensure effective from date is provided when IHD, SMSO, SSC or Profile class are updated |  | Implemented |  | Interim Release 4 | 2023-08-16 | Added conditionality to IF-025 and IF-026 that DI-136 should be provided where DI-137 is not null and DI-135 should be provided wher DI-134 is not null. Added validation rules to IF-025 to ensure conditionality rules are applied for IHD, SMSO, Profile class and SSC with new error code of REG1088 -Effective from date must be provided | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-544 | SW |  | 2023-07-19 | Siemens | 2633 | Tony Mason | Software Provider | Level 4 Validation - Multiple response codes | Unclear from the current E2E design defined in E2E001 for a Level 4 Response code, whether a single transaction with concatenated Response codes be sent back to the DIP for notification to the publisher? Or, would the expectation be that multiple messages be returned with each message quoting the published transaction number? Or, is this at the discretion of the participant? The E2E design should make this clearer, and also provide fleixbility for multiple messages to be returned against the same transaction ID with a response. |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | This will require updates to the E2E design document to make Level 2 and 4 response code expectations clearer, as well as updated Swagger to allow for an array of messages, help and service tickets to be sent per error, per transaction ID. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-545 | ME |  | 2023-07-20 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-496 data type REP004 | Update swagger to show DI-496 as INT (2) |  | Implemented |  | Interim Release 4 | 2023-08-16 | Update to data type for DI-496 from INT(3) to INT(2) to align with swagger. Update made to MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-546 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Incorrect data item referenced in swagger- REP004 | Incorrect data item referened in R026. SettlementPeriod ID must be replaced with Settlement Period (DI-496) in swagger |  | Implemented |  | Interim Release 4 | 2023-08-16 | Updated Swagger 1.4 so that R026 references DI-946 (SettlementPeriod) rather than DI-307 (SettlementPeriodID) | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-547 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Missing data item in swagger | In R026, DI-327 missing from swagger v1.3. Should added and defined as per DT-22 |  | Implemented |  | Interim Release 4 | 2023-08-16 | Updated Swagger 1.4 to include DI-327 (Deemed Supplier Take). Updated R026 to include DI-327 and remove DI-325 so this aligns with ECS Data Catalogue. | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-548 | MH |  | 2023-07-20 | Elexon | 1966 | Rashmi Radhakrishnan | Central Body | Clarification of ISD Transition Requirements | Following MTDSG release of the BRS001 Transition approach and Parallel running requirements v2, ISD would like programme to consider rewording below requirement for more clarity. MHHTR-22 Original: The ELEX-REP-005 Line Loss Factor report will be published at a location on the BSC website/ ELEXON Portal and the URI shall be notified using the Notification of the Publication of a Downloadable Asset IF-047 / PUB-047 to DIP Users prior to M10 and continue post M15. MHHTR-27 Original: The new ISD entities shall be updated be published at a location on the BSC website/ Elexon Portal and the URI shall be notified using the Notification of the Publication of a Downloadable Asset IF-047 / PUB-047 to DIP Users from M10. |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | The recommended solution from Helix and MHHSP is to align the Transition and End State Design Artefacts to reflect LLF Data is a deliverable of ISD and add two new ISD Entities to reflect this and remove REP-005 from the list of ECS Reports – impacts BRS010, BRS001 (Transition), ERI011B and EDI012. | Design Ambiguous | Supporting Docs | ISD Document | ISD Document EDI-021
MHHS-DIN-549 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Incorrect data item referenced in R033 | SettlementPeriodID should be replaced with SettlementPeriod (DI-496), with a MIN value of 1 and Max of 48 in swagger |  | Initial Assessment/Updating |  | Interim Release 7 | 2024-01-19 | Solution under review/discussion | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-550 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Missing R007 from REP007 | Include R007 within REP007 in swagger |  | Initial Assessment/Updating |  | Interim Release 8 | 2024-03-20 | Solution under review/discussion | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-551 | ME |  | 2023-07-20 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-083 | Include Min Value of 1 and Max value of 5 to DI--083 in ECS data catalogue to align with swagger and IF data catalogue |  | Implemented |  | Interim Release 4 | 2023-08-16 | DI-083 Minimum and Maximum column updated with 1 and 5 respectively in MHHS ECS data catalouge Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-552 | SW |  | 2023-07-20 | IMServ | 2356 | Liam Lowey | Software Provider | UTF-8 Encoding for JSON | The E2E001 design document does not specify Encoding for JSON. This needs to be updated to reflect UTF-8 as the JSON Encoding required. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Add UTF-8 as the JSON encoding required in the E2E001 design document, creating a new section 4.2.5. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-553 | RS |  | 2023-07-20 | Design Team | 2627 | Rob Short | Central Body | Secondary routing for Export | Secondary routing rules need to be updated to allow notification of work prgressed by the Import suppllier (eg disconnection). review required of all related interfaces |  | Closed |  |  |  | Following review no document changes required. Re Specific case of Disconnection the Link between Import and Export would need to be removed prior to any Disconnection request. If the link remains in place then the DIsconnection request will be rejected by LDSO/REGS.
MHHS-DIN-554 | MF |  | 2023-07-20 | SCS |  | Madison Layton | Software Provider | Validation on Customer Direct Contracts | Revisions to CDC functionaility. - Amend validation to ensure that only one Customer Direct Contract can be applied against an MPAN at any moment in time - Move CDC process(s) onto a new BP10 process map so as to make it clearer that CDC is MPAN not appointment based - add supporting process info to new BP |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. Process map emailed to particpants - added to BP010E and validation rules for IF-038 updated accordingly Agreed changes with SCS, & RECCO | Design Ambiguous | Supporting Docs | Supporting Docs | BP10 Registration Updates DES138 - Interface Catalogue
MHHS-DIN-555 | MF |  | 2023-07-20 | SCS |  | Madison Layton | Software Provider | Validation of MPID to DIP ID | Carry out validation of MPID to DIP ID during initial IF-031 validation only. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Set REG1090, REG1091 and REG1092 validation in IF-031 to "No" for Queue processing so it only applies to IF-031 validation. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-556 | KH |  | 2023-07-21 | Stark | 2112 | James Murphy | Supplier | Cumulative/Total Consumption Comparison | The “Cumulative/Total Consumption Comparison” that can be carried out instead of a MAR for meters with integral Outstations is not defined anywhere In BSCP502 it is defined at 4.1.5 – I think this should be lifted and shifted into METH002 Interestingly it appears to be described in the SDS Validation & Estimation Statement (METH001) at 3.12 – 3.16 ADS Method Statement (METH002) needs to be updated |  | Implemented |  | Interim Release 4 | 2023-08-16 | ADS Method Statement has been updated with "Reconciliation for smart Meter Advance Reconciliation" section 2.21 - 2.25. | Method statement correction | Supporting Docs | Method Statement | METH002 ADS Validation Estimation
MHHS-DIN-557 | RS |  | 2023-07-21 | Elexon | 2745 | Rashmi Radhakrishnan | Central Body | Consistency of the used of ID | Version 5.1 ISD EDI021 Entity specification document, has discrepancies in the usage of ID, Id, id, etc. Inconsistencies to be addressed when updating the design artefact in the future. ISD Entity M3 Usage of ID and Id - Market Participant ID in the table and description are different ISD Entity ID 17 - DUoS Tariff Id GSP Group Id - ISD Entity ID 17 - DUoS Tariff Id table - GSP Group id is with lowercase "i" and Entity Id M4 Load shape categories : GSP Group Id is mentioned as GSP Group ID ISD Entity ID 17 - DUoS Tariff Id Usage of DUoS Id and DUoS Tariff Id ISD Entity Id 4 and 17 - has ID in capital letter Usage if ID and Id to be consistent Entity M4 GSP Group ID- but should be GSP Group Id ISD Entity Id M5 - MHHS Consumption Component Classes CCC ID - for consistency it should be CCC Id |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | All instances of lower /mixed case id have been replaced with "ID" in caps | Data Interface correction | Supporting Docs | Support Docs | ISD Document EDI-021
MHHS-DIN-558 | BK | DI-189 | 2023-07-21 | SCS | 2011 | Madison Layton | Software Provider | Update response codes in IF-035 | IF-035 routing rules references response codes AC and RJ, this should be A and R |  | Implemented |  | Interim Release 4 | 2023-08-16 | Updated Routing rules in IF-035 to refer to Response code of "R" and "A" for event code [SDS-MDROutcome] rather than "AC" and "RJ" | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-559 | SC |  | 2023-07-24 | SCS |  | Sean Cooper | SRO Design | Clarification of Appointment Scenario Code (Linked MPANs) | Added clarification to IF-036 to confirm that the Appointment Scenario Code used for Secondary MPANs will mirror that applied to the Primary MPAN (eg COS/CSP/Etc). What will be applied in the case of Auto Alignment ? |  | Implemented |  | Interim Release 4 | 2023-08-16 | Added clarification to IF-036 to confirm that the (DI-800) Appointment Scenario Code used for Secondary MPANs will mirror that applied to the Primary MPAN (eg COS/CSP/Etc). In cases of Auto-Alignment of MPANs the Appointment Scenatio of (ALG - Auto Alignment of MPAN Service Providers) will be applied. ALG added as allowable value in DI-800 ( Data Catalogue and Swagger ) | Design Clarificarion | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue Swagger 1.4
MHHS-DIN-560 | SC |  | 2023-07-24 | SCS |  | Sean Cooper | SRO Design | Design Gap on Sharing MTD in the Case of AutoAlignment of Service Providers | The Design allows for the Auto-Alignment of Service Providers in certain circumstances. However a design gap exists that there is currently no trigger for the outgoing MS to send MTDs to the incoming MS in the case of a pure Auto-Alignment (ie no other MPAN transaction eg. COS/CSP) |  | Implemented |  | Interim Release 4 | 2023-08-16 | Proposal is to create a new requirements (MS-098 / MS-099) on Smart and Advanced Metering Services to trigger sending of D0149/D0150 (trad) or D0265 (Adv), on receipt of a PUB-037 with De-Appointment Reason Code of “RELATED” or “IMPEXP”. D-Flow(s) should be sent, via DTN, to the new/incoming MS referenced in the PUB-037 flow, where available Issue does not arise for Smart sites as MTDs are fully convayed using the PUB-036. Also not a concern for UMSDS as no MTDs exist. | Design Clarificarion | Minor | MPAN Ownership | BRS-002 Metering Service Requirements
MHHS-DIN-561 |  |  | 2023-07-24 | SCS |  | Sean Cooper | SRO Design | Disconnection of Linked MPANs | No change to desgin required. Design confirmation only. SCS have confirmed that it will be necessary to de-link and MPRN before being able to action a disconnection on it. i.e. Disconnection cannot be performed on a linked MPAN until such time as all links have been removed via (IF-019/IF-020) |  | Closed |  |  |  | No change Required - Clarification Only
MHHS-DIN-562 |  |  | 2023-07-24 | SCS |  | Sean Cooper | SRO Design | Clarification of IF-014 R0 Population for Event Code [ConsumptionOnDeEnergisedMPAN] | Confirmation at an R0 will be required when issuing an IF-014 with Event Code [ConsumptionOnDeEnergisedMPAN]. DI-979 should be populated with value 'W', DI-980 would remain blank. |  | Implemented |  | Interim Release 4 | 2023-08-16 | IF-014 updated to clarify that DI-979 should be populated with W. Data Catalouge and Swagger v1.4 updated to reflect this. | Design Clarificarion | Minor | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-563 |  |  | 2023-07-24 | Elexon | 2705 | Ayo O (Helix) | SRO Design | Clarification on Helix Treatment of IF-021 error condition data. | Clarification is required from Helix on exactly how they will manage and process IF-021 messages and how any resulting error/rejections will be managed. This is so that clear guidance can be drawn up on participants should expect to receive errored data etc. In any event design team are clear "the data returned in the IF-014 must only be that data which is rejected." |  | Closed |  |  |  | A response was provided to Ayo on 24/07 by design team. Follow up email has been sent for Ayo to confirm whether issue is resolved, thus closing the DIN or whether a call is required with Design team for further resolution. DIN closed as no response received from Ayo. It is our assumption the feedback provided by the design team was sufficient. | Design Clarificarion
MHHS-DIN-564 | SW |  | 2023-07-17 | SIMS | 2704 | Martin Freeman | Central Body | Mandatory Nullable on Swagger | Is Mandatory Nullable (which is how 'optional' properties are described in the DES138) supposed to be marked as Required & nullable in Swagger? Or should these Mandatory Nullable (optional) properties be marked 'not Required' in Swagger? In some interfaces Mandatory Nullable properties are marked 'not required' in Swagger while in others they are 'nullable required'. Need to ensure this is applied consistently across all Interfaces. |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Need to update Swagger implementation so mandatory nullable is treated consistently across all Interfaces as this is not always consistent. Need to updated E2E001 to provide additional clarity on how this applies to Swagger. Need to ensure DES-138 is aligned. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-565 | SW |  | 2023-07-25 | MHHS | 2763, 2713 | Steve Weston | SI Design | Version and Schema Interoperability across environments. | Versioning is covered in Section 8.4 and 8.5 of the E2E001 design, that covers the differences between major, minor and patch versions of an API, the URL required as well as schema versions that are contained in the common block of an Interface. There is confusion around how this will work across different environments so we need to provide additional clarity on the Swagger API versions / Schema versions that must be supported by the DIP and MP’s, alongside scenarios that are envisaged. This will provide information on version uplifts, interoperability required and how long different versions of API / Schemas will be supported for. This needs to covers scenarios where within an environment, we have multiple versions of an API within an environment ie, we may be required in some cases to be backwards compatible with previous versions -- for example -- if we received and processed earlier versions, we can respond with the latest live version. E.g. if we receive PUB-005 on version 1.0.0 we could respond with IF-006 on version 1.0.1 and would not be expected to respond with version 1.0.0. |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Need to provide updates to Section 8.4 and 8.5 to ensure we cover worked examples across different environments for both API versions and Schema versions, interoperabilty required, transition between versions, BAU vs Testing phases and expectations on DIP and MP's. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger 1.4 | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-566 | SW |  | 2023-07-25 | MHHS | 2549 | Steve Weston | SI Design | E2E NFR's need to refined based on actual data | Section 3.1 of MHHS DES001a MHHS Data Integration Platform – Functional Specification – Appendix A Transaction Volumes states that the indicative size of an IF-021 (single days' worth of UTC SP data) is between 1 and 2 KB. The equivalent IF-021s we have successfully submitted to the DIP Simulator are ~4.5 KB as observed in webhook. Can you confirm that this increase in size has been factored into the non-functional requirements? |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Volumetrics document has been updated to reflect updated file sizing. This is for guidance only and depends on IF-021 messages per transaction. | Design Ambiguous | Supporting Docs | MHHS Data Integration Platform – Functional Specification – Appendix A Transaction Volumes | MHHS Data Integration Platform – Functional Specification – Appendix A Transaction Volumes
MHHS-DIN-567 | SW |  | 2023-07-25 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - Swagger Incorrect | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4. Swagger 1.4 needs to be updated so that it aligns with DES-138. DI-081 to be updated to periodDuration. DI-086 to be updated to supplierEffectiveFromDate. DI-121 to be updated to supplierEffectiveToDate. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Need to update mismatch between Swagger YAML definition in DES-138 and Swagger 1.4. Swagger 1.4 needs to be updated so that it aligns with DES-138. DI-081 to be updated to periodDuration. DI-086 to be updated to supplierEffectiveFromDate. DI-121 to be updated to supplierEffectiveToDate. | Design Ambiguous | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-568 | SW |  | 2023-07-26 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - DES-138 incorrect | DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) shows in YAML as secondaryRecipientDIPID and primaryRecipientDIPID respectively and this should be updated in DES-138 YAML column so this aligns with Swagger 1.4 ie, DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) |  | Implemented |  | Interim Release 4 | 2023-08-16 | DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) shows in YAML as secondaryRecipientDIPID and primaryRecipientDIPID respectively and this has been updated in DES-138 YAML column so this aligns with Swagger 1.4 ie, DI-981 (secondaryRecipients) and DI-982 (primaryRecipients). | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-569 | SW |  | 2023-07-26 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - DES-138 incorrect | DI-047, DI-049, DI-210, DI-211 and DI-820 are defined in the Data Catalogue, but not used in any Interfaces so need to be removed from the latest version of DES-138. |  | Implemented |  | Interim Release 4 | 2023-08-16 | DI-047, DI-049, DI-210, DI-211 and DI-820 are defined in the Data Catalogue, but not used in any Interfaces so need to be removed from the latest version of DES-138. DES-138 needs to be updated to remove these items. | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-570 | MF |  | 2023-07-26 | MHHS |  | Mike Fensome | SRO Design | IF-021 validation rules | IF-021 validation rules need to be updated to align to the MDS and LSS Method statements which include validation for de-energised sites. |  | Implemented |  | Interim Release 4 | 2023-08-16 | IF-021 Added validation to align with MDS/LSS method statements where estimated data is provided on a de-energised site (ECS1008 - SP End Date/Time [DI-082] contains non-actual consumption for ECS De-Energised MPAN) | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-571 | SW |  | 2023-07-27 | Callisto | 2762 | Dave Peat | Software Provider | Inconsistency for DI-980 Response Message(s) | For DI-980, the YAML name is responseMessages, however in Swagger, there is inconsistencies: R0.responseMessages - this is defined as array of DI-980 (responseMessages) B066.responseMessage - but defined as responseMessages (defined as DI-980 - single) B092.responseMessage - defined as responseMessage (defined as DI-980 - single) We need to update DES-138 / Swagger so there is consistenct application of the words responseMessage (for single response) vs responseMessages (where there is an array of responses). |  | Implemented |  | Interim Release 4 | 2023-08-16 | I have updated Swagger 1.4 so that DI-980 definition is applied consistently for single response vs array of responses. For single, it will be responseMessage. For an array of messages, it will be responseMessages. To this effect, B066.responseMessages has been updated to be responseMessage. Also, B066 block has been updated to align with DES-138 to be conditionally mandatory, rather than mandatory. | Supporting Docs | Design Ambiguous | Supporting Docs | Swagger 1.4 | DES138-InterfaceCatalogue
MHHS-DIN-572 | SC |  | 2023-07-27 | MHHS |  | Sean Cooper | SRO Design | Clarification of IF-013 Issuance (also Ref DIN610) | DUPE WITH DIN-610 ~ Clarification is requiired on the circumstances when Helix will issue IF-013. 1. IF-013 is only issued as part of the RF Run i.e. simply to notify Suppliers of what the default consumption for a period(s) is, where no data has been submitted by the DS come the point of RF. Should suppliers wish to derive this for pre-RF settlement runs then they are able to do so easily enough using the own data and the published Load Shapes. 2. The second view is that the IF-013 is issued on every settlement run undertaken for sites where no PUB-021 data has been received DIP impact concerns wrt to volumes of IF-013 would need to be addressed if Option 2 is the position. |  | Closed | 2023-09-13 |  |  | Duplicate of DIN-610 | No Change
MHHS-DIN-573 | ME |  | 2023-07-27 | MHHS |  | Kevin Spencer | SRO Design | Update to step 40 of ISD BPM/BPD | Step 40 of MHHSP-BP021 and BPD021 currently ambigious Can the intention of this step be made clearer.? |  | Implemented |  | Interim Release 4 | 2023-08-16 | Step 40 of ISD BPM and BPD have been updated to say 'Issue ISD Change Notification' to make ithe purpose of the step clearer. | Design Ambiguous | Minor | Supporting Docs | MHHSP-BP021 Industry Standing Data MHHSP-BPD021 Industry Standing Data Business process Descriptions
MHHS-DIN-574 | SC |  | 2023-07-27 | SCS |  | Madison | SCS | Change Of Logic on Smets 1 Number of Digits | Smets 1 Number of digits can be 0 - 9 Replaces previous logic. |  | Closed |  |  |  | DIN CLOSED as agreed with St Clements and RECCo. DIN-615 supercedes this DIN. The text has been updated as suggested below from RECCo, ‘Where the Meter Type is S1, the value should be populated as per the manufacturer specification.’ However, the logical test for SMETS1 in the DES-138 Interface Catalogue will remain unchanged. DIN-615 also includes updating the Swagger validation of this field to match SCS logical test i.e. value can be 0-9. | No Change
MHHS-DIN-575 | SC |  | 2023-07-27 | SCS |  | Madison | SCS | Requirment for REGS to process IF-040 | SCS would prefer not to process IF-040 now that AC is provided to EES Directly via the DIP. In additional what is the IF-040 processing schedule? |  | Requires Industry Work Group review |  | Interim Release 6 | 2023-10-18 | SCS to raise at DRG for initial feedback, ahead of raising formal CR
MHHS-DIN-576 | MF |  | 2023-07-27 | SCS |  | Madison | SCS | Cancelling appointments in advance of receipt of PUB-034 | SCS have requested that the design is updated to allow for issuing of a PUB-035 'Lapsed' message, if a switch is 'Cancelled' or otherwise superseded, even prior to issuing / processing of a PUB-034 from the Metering Service or Data Service. ​ |  | Closed |  |  |  | Following DRG on 4th Aug, it was agreed that St Clements Services were to work-up the topics discussed, and a dedicated workshop would be arranged to discuss this further. St Clements Services have advised the Programme that they will now not be pursuing proposals made at the DRG session and would be reverting to implement to the original design, therefore closure of this DIN.
MHHS-DIN-577 | SW |  | 2023-07-27 | Callisto | 2979 | Neil Edney | Software Provider | DT-983 and DT-000 are missing IF-040 / PUB-040 | DT-983 and DT-000 are missing IF-040 / PUB-040 in Swagger. IF-003, 19, 20 and 50 also need to be added to align with DES_138. |  | Implemented |  | Interim Release 4 | 2023-08-16 | Need to update Swagger to include IF-040 and PUB-040 in DT-000 and DT-983. I’ve added IF-003 / 019 / 020 / 040 / 050 to DT-000 in Swagger and PUB-003 / 019 / 020 / 040 / 050 to DT-983 in Swagger | Supporting Docs | Design Ambiguous | Supporting Docs | Swagger 1.4
MHHS-DIN-578 | SB |  | 2023-07-28 | RECCo | 2943 | Jonny Moore | Central Body | EFDs, ETDs and Supplier information for Related and Import/Export Linkages | We’ve noticed through the design and build stage of EES that we are not being communicated the EFD and ETD of a Related MPAN set-up or an Import / Export Linkage. Nor are we being informed of the Supplier responsible for creating a Related MPAN relationship. This information is not currently being published in the IF020/PUB020 However, this information is currently available for market participants to view on EES. We had some feedback in the REC MSAG that participants would like to continue to view these items in EES and wonder if this is worth a DWG discussion? |  | Closed |  |  |  | RECCo notified on DIN closure. The Effective From date is not currently shared on the D0386 which was the basis for the IF-019/PUB-020. If EES requires an EFD suggest that the transaction date from the header is used. These updates can only be made by the current Supplier. | No Change
MHHS-DIN-579 | SB |  | 2023-07-28 | ENWL | 2444 | Paul Stancliffe | Network Operator | PUB-043 Routing discrepancy | Trying to map flow PUB-43 to our TO BE business processes as these flows are showing on the MHHS - Interface Data Item Catalogue as routing to LDSO. However when trying to align these to the Business Process Diagram BPM011- Change of Connection Type and / or Market Segment V5.0 PUB-43 is not routing to LDSO |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | BP011B from Step 542 new flow for PUB-043 to LDSO new step Manage Change of Connection type Notification | Process Model correction | MPAN Ownership | Supporting Document | BP011B BPD011
MHHS-DIN-580 | RS |  | 2023-07-28 | RECCo | 2719 | Sarah Jones | Central Body | Late or Missing Secured Active Messages | understand the approach to managing CSS issues where secured active messages are not received within the expected secured active processing window. We understand the standard ‘happy path’ processing requires secured active notifications to be issued by CSS after the 5pm gate closure window the day before the registration effective from date. However, it was acknowledged when the MHHS design was originally baselined that some notifications may arrive late e.g. after 6pm, or not at all. Rather than developing operational provisions to deal with missing / late secure active notifications, this was highlighted as a risk for later consideration, on the basis the CSS arrangements were still new and the enduring BAU process was subject to change. In light of the CR018 approval, we believe this is now the time to clarify the approach to be taken where CSS notifications are missing or late. |  | Closed |  |  |  | The Design Team and SRO are actively engaged with St Clements on issues around problematic switches. The plan is for them to provide us with a list of of their issues. We will then go through a process of raising these directly with CSS. Dependent on outcomes we receive back, we will look to discuss this with St Clements with the possibility of raising a CR for a specified data correction tool to align the data and send out the appropriate MHHS flows. | No Change
MHHS-DIN-581 | RS |  | 2023-07-28 | ESG | 2924 | Patricia Parker | Software Provider | Meter Location in DES138 | Currently DI090 in DES138 states 'Values as Per ISD'. These values are not held in ISD, therefore the reference should be changed to 'see Enum Values of the Data Catalogue' - example IF-005 |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Updated population notes for DI-090 to refer to Data Catalogue | Clarification | Supporting Docs | Interfaces | DES-138 Interface Spec
MHHS-DIN-582 | MF |  | 2023-07-28 | Ovo |  | Chris Butterfiled | Supplier | Clarification following CR15 | Supplier Overview requirements v5.1: this refers specifically to Economy 7 / Economy 10 tariffs; we suggest this should be more general and refer to any Time of Use tariff / tariff with switched load to include other variants such as Smart Economy 9 etc. |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Updated SU-163, SU-164 and SU-165 to refer "for switched load tariff (eg. Economy 7/Economy 10) sites" rather than Economy 7/Economy 10 sites | Clarification | Supporting Docs | Interfaces | DES-138 Interface Spec
MHHS-DIN-583 | SB |  | 2023-07-31 | Stark | 2891 | Jon Dennis | Data Service Provider | BP005 Read Sharing for Data Service | can you provide clarification around BP005 Read Sharing for the Data Service, in particular this section of MHHSP-BP005-Data Processing-v5.1 Question: Is the entry point to this section either: Regular Data Collection, e.g. daily remote collection for ADS/SDS Smart? Trigggered by an external process, e.g. Change of Energisation BP009? To answer the above, please can you list all of the processes that lead to Step 170 in BP005. May I also suggest updating BP005 to include this information, perhaps by adding a Step description to the entry point from Data Collection as shown above. Related Question: In BP009 the Data Service is expected to progress to BP005 Step 185. However, unless I am mistaken, BP005 V5.2 does not include Step 185. Please update BP009 with a valid onward step. |  | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18
MHHS-DIN-584 | SC |  | 2023-07-31 | Design Team |  | Sean Cooper | SRO Design Team | DI-511 Change of Data Type from String to Number in IF-024 | DI-511 Off Peak Declaration Proportion has been changed from String to Number so as to allow for improved Swagger validation of this data item. The new Number val will have a Minimum value = 0 and a Maximum Value = 100. |  | Implemented |  | Interim Release 4 | 2023-08-16 | DI-511 Off Peak Declaration Proportion has been changed from String to Number so as to allow for improved Swagger validation of this data item. The new Number value will have a Minimum value = 0 and a Maximum Value = 100. (IF-024). Data Catalogue updated accordingly. | Improved Validation of Data Item | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-585 | SC |  | 2023-07-31 | Design Team |  | Sean Cooper | SRO Design Team | Clarification on IF-024 | Clarification update to confirm that B097 Off Peak Declaration is Mandatory only for Event Type [SN-OffPeakDec] |  | Implemented |  | Interim Release 4 | 2023-08-16 | Clarification update to confirm that B097 Off Peak Declaration is Mandatory only for Event Type [SN-OffPeakDec] | Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-586 | SW | DI-204 | 2023-07-31 | Callisto | 2762 | Neil Edney | Software Provider | Mis-alignment between D0 block YAML in Swagger and DES-138 | DES138, the D0 has the following YAML names which do not align DIPCorrelationID, DIPTimeStamp, DIPTransationID However, swagger has these: initialCorrelationID, transactionTimestamp, transactionID |  | Implemented |  | Interim Release 4 | 2023-08-16 | Updated DES138 Data Catalogue D0 Common block data items so that YAML names in DES-138 now align with Swagger initialCorrelationID (DI-987), transactionTimestamp (DI-989), transactionID (DI-990) | Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-587 | SW |  | 2023-08-01 | Kraken | 2973 | Angelos Rizoyannis | Software Provider | Mis-alignment between R0 mandatory in Swagger vs DES-138 | In DES-138 in the following interfaces, R0 is marked as mandatory, but not mandatory in Swagger - IF-006, IF-008, IF-014, IF-020, IF-026, IF-028, IF-032, IF-039. |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | In DES-138 in the following interfaces, R0 is marked as mandatory, but not mandatory in Swagger - IF-006, IF-008, IF-014, IF-020, IF-026, IF-028, IF-032, IF-039. Update R0 to be mandatory in these interfaces. | Clarification | Minor | Interfaces | Swagger 1.5
MHHS-DIN-588 | ME |  | 2023-08-02 | Design Team |  | Kevin Spencer | SI Design | Update of ID to Id | A request has come from Elexon to update the ISD Entities document. ID should be changed to Id |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | All instances of ID have been changed to Id | Supporting Document | Minor | Supporting Document | MHHSP_EDI021_ISD_Entities v5.3.2
MHHS-DIN-589 | SB |  | 2023-08-02 | Stark | 2466 | Jon Dennis | Data Service Provider | ADS and SDS Estimation Statements | I have been studying the following two documents: Advanced Data Service Validation and Estimation: Methodology Statement (MHHSP-METH002_ADS_Validation_Estimation v5.1) Smart Data Service Validation and Estimation: Methodology Statement (MHHSP-METH001_SDS_Validation_Estimation v5.1) In particular, Section 3 of the ADS_Validation_Estimation document details the estimation methods where the customer has opted-out of UTC Period consumption data. It references the SDS_Validation_Estimation document where Estimation methods are in Section 7. The 2 method statements have become misaligned when changes to the SDS method statement was updated. |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | We will align the ADS method statement with the SDS method statement to keep it uniform. | Method statement correction | Supporting Docs | Method Statement | ADS Method Statement SDS Method Statement
MHHS-DIN-590 | KH |  | 2023-08-03 | MHHS | 2717 | Martin Freeman | Central Body | Update Role Codes in E2E001 | There is a mismatch between roles codes that are in DES-138 and those that are in E2E001. Role code for Unmetered Supplies Data Services changed from UDS to UMSDS. Need to ensure that all of the role codes referenced in DES-138 are included in E2E001 and that there is a full explanation of what these are. |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Update all the role codes referenced in DES-138 to ensure they are included in E2E001 and that there is a full explanation of what these are. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-591 | KH |  | 2023-08-03 | Elexon | 2974 | Michael Ceney | Central Body | Update to MDS Method statement | The MDS Method Statement Section 2.1 should read: If today > MDS Run Date (RF) for SP End Date/Time [DI-082] in the Master Settlement Table in ISD ECS1003 - SP End Date/Time [DI-082] has already passed "MDS Run Date (RF) [ISD.RunDate-RFDate] |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Update DES138 and MDS Method Statement Section 2.1 to read "If today > MDS Run Date (RF) for SP End Date/Time [DI-082] in the Master Settlement Table in ISD ECS1003 - SP End Date/Time [DI-082] has already passed "MDS Run Date (RF) [ISD.RunDate-RFDate]" | Data interface correction | Supporting Docs | Supporting Docs | MDS Method Statement DES138
MHHS-DIN-592 | SW |  | 2023-08-03 | MHHS | 2717 | Martin Freeman | Central Body | Update StatusMessage and StandardResponseBody in E2E001 to provide more clarity | There are inconsistencies between StatusMessage / Standard Response body definitions for what is contained with E2E001 and Swagger, these need to be aligned. Clarity needs to be provided on how TransactionID is populated in Status Message for Level 2 validation and Level 4 validation and for Level 4 validation, how this is sent to original sender. |  | Open - awaiting assessment |  | Interim Release 5 | 2023-09-20 | Align inconsistencies between StatusMessage / Standard Response body definitions for what is contained with E2E001 and Swagger. Provide clariry on how TransactionID is populated in Status Message for Level 2 validation and Level 4 validation | Data interface correction | Supporting Docs | Interface Catalogue | E2E001 MHHSP-DES138-Interface Catalogue
MHHS-DIN-593 | ME |  | 2023-08-04 | MHHS |  | Kevin Spencer | SI Design | Update to AC Method Statement | Update required to the AC Method Statement to amend calculation where less than 365 days of data is available and a change to section 2.2 to allow calculations to be undertaken on Calendar days |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | The following changes below in red have been made to section 2.2 of the AC Method Statement The Market-wide Data Service (MDS) should schedule the calculation of MPANs requiring a new Annual Consumption for active MPANs evenly across each working day of the month and publish on the first available working day following the calculation. The recalculation shall be performed each month, for every MPAN and every 30 Calendar days +/- 5 Calendar days of the date of the previous calculation. Changes to the calculation of less than 365 days available are no longer reuried as agreed with Helix | Method statement correction | Supporting Docs | Method Statement | Annual Consumption Meth 10
MHHS-DIN-594 | SC | SCS DI-207 | 2023-08-04 | MHHS |  | Sean Cooper | SRO Design | Correction to BP10 Related MPANs | Rejection was incorrectly shown being sent direct from REGS rather than from REGS Via DIP. |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Rejection was incorrectly shown being sent direct from REGS rather than from REGS Via DIP. | Process Model correction | MPAN Ownership | Supporting Document | BP010-Registration Updates
MHHS-DIN-595 | SC | SCS DI-208 | 2023-08-04 | MHHS |  | Sean Cooper | SRO Design | Correction of Type in ISD Doc Table 16 | Correction of type in definition of subscript 3 for table M16 - "Market Participant ID" changed to "Market Participant Role" |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Correction of type in definition of subscript 3 for table M16 - "Market Participant ID" changed to "Market Participant Role" | Clarification | Supporting Docs | Interfaces | E2E001 MHHSP_EDI021_ISD_Entities
MHHS-DIN-596 | SC |  | 2023-08-04 | MHHS |  | Sean Cooper | SRO Design | Clarification of SP Appointment Time(s) | Per DRG decision all SP Appointment times shall be effective from Midnight UTC Time. Clarification added to IF-031/If-036 |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Added validation rule to IF-031 to ensure appointments are made at midnight UTC. Added clarification on Regs Notes tab. | Clarification | Supporting Docs | Interfaces | DES-138 Interface Spec
MHHS-DIN-597 | SC | SCS DI-193 | 2023-08-07 | MHHS |  | Sean Cooper | SRO Design | IF-026 B068 Presence | IF-026 / B068 - SCS requested removal of wording "must be required for smart meter removed" as this is inherent as part of the Event Type. |  | Implemented |  | Interim Release 4 | 2023-08-16 | IF-026 / B068 - SCS requested removal of wording "must be required for smart meter removed" as this is inherant as part of the Event Type. | Clarification | Supporting Docs | Interface Catalogue | DES-138 Interface Spec
MHHS-DIN-598 | SC | SCS DI-176 | 2023-08-07 | SCS |  | Madison Layton | Software Provider | Incoming Supplier Notifications - Clarification | SCS raised a query around whether certain flows should be copied to an incomming Supplier (PUB-006, PUB008 etc. etc.) The current design does not include copying of these flows to an incoming supplier, (not represented in either Requirements or BP maps). IF-036 (and accompanying D-flows as required) provides suppliers with a clear starting point containing all the information they need to support servicing the customer. Design Team feel any change in this area would require a CR. |  | Closed |  |  |  | Any change in this area would require changes to the REGS Requirements to implemnt Primary Routing, as copying of such flows could not be performed by DIP Secondary Routing. CR would be required to confirm new requirements and allow for IA on REGS and Suppiers design. Design Team also note that no other issues/DIN raised on this issue, by suppliers or other participants. | Clarification | Clarification - No change Required
MHHS-DIN-599 | BK | SCS DI-198 | 2023-08-07 | SCS |  | Madison Layton | Software Provider | Data Cleansing required on IHD, SMSO and Installation Date | SCS raised a a query on the three items below that are not under the Data Cleanse Plan that may need cleanse work. 1) IHD - Should be populated for smart meters, and only smart meters (not currently validated) 2) SMSO - Should be populated for smart meters and only smart meters (not currently validated) 3) Installation date - Should not be prior to MPAN Creation date (Legacy data integrity issues of meters migrated into MPRS) |  | Closed |  |  |  | This change has been forwarded onto the Data Cleansing Working Group as it is not a design issue. Design Team also advised SCS to raise these issues within the working group. | Clarification | Clarification - No change Required
MHHS-DIN-600 | ME |  | 2023-08-07 | Elexon | 4566 | Rashmi Radhakrishnan | Central Body | ISD Entity M18 Discrepancy | In the ISD Entity Document the table shows {Effective From Date {DIPRole} and {Effective To Date {DIPRole}, however the exmaple table and column details have been titled as {Effective From Date {MP2DPM} and {Effective To Date {MP2DPM}. These should be changed to align with the first table in entity M18 |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Corrected M18 Col Headings to read "DIPRole" | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-601 | SW |  | 2023-08-07 | Kraken | 4485 | Adrian Serban | Software Provider | Incorrect on M0 common block in IF-018 | In Swagger, it appears the block is correct (M0), but the label is incorrect (M1) for IF-018. The label needs to be updated to M0 to align with the block. This needs to be updated in Swagger so the label is incorrect. In IF-019 and IF-020, there is an inconsitency of use of M1 vs M0. |  | Closed |  |  |  | M1 is used in IF-019 and IF-20. M0 is used in all other IFs where required. Swagger version 1.4 has been reviewed and correctly reflects this position. | No Change
MHHS-DIN-602 | RG |  | 2023-08-08 | SRO |  | Rob Golding | Programme | Add Interface, Event Code enumeration to Swagger for interface blocks | Interface and Event code validation and alloawable blocks is missing from the DIP. Rather then getting Avanade to code these dependencies the proposal is to intoduce the restrictions into the Swagger |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Update the swagger for the majority of interfaces where different event codes require different combinations of optionality for the blocks they reference. An example of this has been done already for IF-001 in the new swagger file Interface-001. Estimate 3/4 days effort to complete | Improved error trapping at interface | Minor | Interfaces | Swagger, possibly add clarification to DES138
MHHS-DIN-603 | SW |  | 2023-08-09 | MHHS | 4022, 4700 | Steve Weston | Central Body | Clarity on A0 block being removed | Section 4.2.1 of the E2E001 design has a diagram that shows that the A0 common block is removed by the DIP prior to sending out the message to onward particpants. This is inconsistent with the rest of the design. Section 4.2.1 needs to be updated so that this shows A0 not being removed. |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Update Section 4.2.1 of E2E001 so that this shows A0 not being removed | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger 1.4 | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-604 | SW |  | 2023-08-09 | MHHS | 4945 | Steve Weston | Siemens | Clarity on B066 mandatory on IF-035 | In DES-138, B066 block in IF-035 is shown as mandatory and also defined as mandatory in Swagger. This should be conditionally mandatory as per B019, so this needs to be updated to conditionally mandatory in DES-138 and also in Swagger 1.5. |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Update B066 block in IF-035 to conditional mandatory in DES-138 and Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-605 | SC |  | 2023-08-09 | MHHS |  | Sean Cooper | SRO Design | Update "Switch Cancellation" Info Message Box of BP002 & BP003 | Message updated to make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations will be held awaiting completion of PUB-34 processing. |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Message updated to make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations will be held awaiting completion of PUB-34 processing. | Clarification | Minor | Interfaces | BP002 / BP003 Change of SP
MHHS-DIN-606 | SC |  | 2023-08-09 | MHHS |  | Sean Cooper | SRO Design | Update Ops C to include clarification on issuing of IF-035 | make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations will be held awaiting completion of PUB-34 processing. |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Update OPS Choreography document to clarify processing of IF-035 | Clarification | Supporting Docs | Supporting Document | OPS Choreography
MHHS-DIN-607 | SC |  | 2023-08-10 | SCS |  | Sean Cooper | SRO Design | Update IF-035 Lapsed Reason Code | SCS Request Update IF-035 Lapsed Reason Code from "Switch Cancelled" to "Registration Cancelled" |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | SCS Request Update IF-035 Lapsed Reason Code from "Switch Cancelled" to "Registration Cancelled" | Clarification | Minor | Interfaces | DES-138 Interface Doc
MHHS-DIN-608 | SC | SCS DI-206 | 2023-08-10 | SCS |  | Sean Cooper | SRO Design | Correction of Inaccuracy on BP003 | Steps 86,87,88 added to better reflect that REGS will actually send TWO IF-035 messages not just one. IF-035 [SendMTD] will be issued to Incumbent MS and [AppOutcome] event will be issued to DS/Supplier. BP003 now mirrors the drafting in BP002. There is no change in underlying requirement here - redrafting is simply a more accurate representation of REGS activity. |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Steps 86,87,88 added to better reflect that REGS will actually send TWO IF-035 messages not just one. IF-035 [SendMTD] will be issued to Incumbent MS and [AppOutcome] event will be issued to DS/Supplier. BP003 now mirrors the drafting in BP002. | Clarification | Minor | Interfaces | BP003
MHHS-DIN-609 | SC |  | 2023-08-10 | Helix |  | Sean Cooper | SRO Design | Helix Issuing of IF-040 Annual Consumption Messages | Discussion held with Helix on proposed approach to issuing IF-040 messages. Current design suggests that messages should only be issued on Working Days - Design Team are exploring why this is the case (risk of substantial peak esp on 4 day long weekends). preference would be for Helix to issue IF-040 on each calendar day. |  | Initial Assessment/Updating | 2023-09-13 | Interim Release 5 | 2023-09-20 | Update the OpsC document to set a 24hr rather than a 2hr limit around processing the IF-040 interfaces only | Clarification | Supporting Docs | Supporting Document | OPS Choreography
MHHS-DIN-610 | SC |  | 2023-08-10 | Helix |  | Sean Cooper | SRO Design | Clarification of IF-013 Functionality (also ref 572) | 1. IF-013 is only issued as part of the RF Run i.e. simply to notify Suppliers of what the default consumption for a period(s) is, where no data has been submitted by the DS come the point of RF. … … Should suppliers wish to derive this for pre-RF settlement runs then they are able to do so easily enough using the own data and the published Load Shapes. Need to validate if IF-013 should be issued after each Settlement Run OR only after RF Run. Also need to validate the IF-10 should NOT be issued after II Run. 2. The second view is that the IF-013 is issued on every settlement run undertaken for sites where no PUB-021 data has been received DIP impact concerns wrt to volumes of IF-013 would need to be addressed if Option 2 is the position. Dupe with DIN-572 |  | Initial Assessment/Updating | 2023-09-13 | Interim Release 5 | 2023-09-20 | Following Review at DRG meeting - agreement reached that IF-013 should NOT be sent for the II Run and should only be issued for SF and later Runs. DES-138 IF-013 Additional notes updated to reflect this decision. ----- MDS Method statement also requires update to record this decision. The following text has been added to the Method Statement Restrict sending of IF-013 until the SF Settlement Run | Clarification | Supporting Docs | Supporting Document | DES-138 Interface Catalogue MDS Method Statement
MHHS-DIN-611 | KH |  | 2023-08-11 | Elexon | 3986 | Michael Ceney | Central Body | Changes required to MDS Method Statement | Following the release of DIN-332, changing EventCode [ConsumptionOnDe-energisedMpan], the MDS Method Statement needs updating to reflect this change. Section 9.3 states that the an exception report will be provided using IF-013, this needs to show IF-014 is to be used. Please can a new DIN be raised. |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | We will update section 9.3 to state that the report will be provided using IF-014. | Method statement correction | Supporting Docs | Method Statement | MDS Method Statement
MHHS-DIN-612 | SC | PDA Test Issues | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | New IF-019 Validation Rules Re Unmetered Related MPANs | Added x2 new validtion rules to prevent the creation / addition of Related MPANs with a Connection Type of "U - Unmetered". No validation applied to remove so as to allow for the resolution of any historically erroneous links |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Added x2 new validation rules to prevent the creation / addition of Related MPANs with a Connection Type of "U - Unmetered". No validation applied to remove so as to allow for the resolution of any historically erroneous links | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-613 | SC |  | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Remove Reference to SP Appointment Start Time(s) | In line with DRG Decision on 4th Aug - it was agreed that ALL Service Provider Appointments should commence at Midnight UTC. Text against DI-086 and DI-121 has been removed. A new section addressing the treatment of Time has been added to the Additional Information tab of DES-138 |  | Implemented |  | Interim Release 4 | 2023-08-16 | In line with DRG Decision on 4th Aug - it was agreed that ALL Serive Provider Appointments should commence at Midnight UTC. Text against DI-086 and DI-121 has been removed. A new section addressing the treatment of Time will be added to the Additional Information tab of DES-138 as part of Interim Release 5 (DIN-614) | Design Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-614 | SC |  | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Create new "Time" Advisory Notes in Registration Additional Info Section | SC to create Treatment of Time section |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Added validation rule to IF-031 to ensure appointments are made at midnight UTC. Added clarification on Regs Notes tab. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-615 | SC |  | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Number of Registers Validation | Clarification following on from DIN-574. Text against Number of Register Digits fields amended to say "per the manufacturer specification" . Note text for SCS validation will remain unchanged. Swagger validation of this field updated to match SCS logical test ie value can be 0-9 |  | Implemented |  | Interim Release 4 | 2023-08-16 | Clarification following on from DIN-574. Text against Number of Register Digits field amended in IF-002, IF-005, IF-006, IF-033, to say "per the manufacturer specification". Note text for SCS validation will remain unchanged. Swagger validation of this field updated to match SCS logical test ie value can be 0-9. | Design Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-616 | SC |  | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Review of COS Transfer of Readings Process Required in light of SP UTC Decision | A Review of BP003C is required to impact assess implications of SP UTC Decision |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | BP003C may need updating follow impact assessment | Clarification | Supporting Docs
MHHS-DIN-617 | SC | PDA Test Issues | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Note on Discressionary Use of IF-023/IF-040 by Data Service | Missing interface notes on Discretionary Use of IF-023/IF-040 by Data Service |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Added interface notes to clarify Annual Consumption usage in IF-040 and Load Shape Totals in IF-023 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-618 | KH |  | 2023-08-15 | ESG | 5859 | Patricia Parker | Software Provider | Updating routing within DES138 - PUB-026 | Could you please clarify what updates the Metering Service will receive via the PUB_026. From the routing the only update is re the SCCandProfile Class. However, BP010C alludes to the MS receiving an update for the SMSO - could you please confirm which is correct? |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | To update PUB-026 adding MS to the SMSO secondary routing. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-619 | SC | PDA Test Issues | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Draft Umetered Change of Energisation Status Business Process Map | Update BP08 existing or draft Unmetered Specific version. |  | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 | Pending feedback from PDA on UMS process
MHHS-DIN-620 | SC | Test Issues | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Remove EES as a Recipient of IF-001 | Remove EES as a Recipient of IF-001 | CR028 | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Removed EES as a Recipient of IF-001 - EES gets this info from CSS | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-621 | SC |  | 2023-08-17 | MHHS |  | Sean Cooper | SRO Design | Changes to D303 DTN Flow | Need to make "Manufacture and Type" non mandatory in the D303 flow. Follow migration to MHHS it is possible that this data item is not held in REGS and therefore not shared with all MHHS Participants incl. MS who currently would need to provided it on the D303. Discussions were held in Data Working group around back population of this data item but that proposal was REJECTED - therefore only other option is to make this field optional in D303 |  | Industry CP Required |  | Interim Release 6 | 2023-10-18 | Passed to Matt McC to add to existing industry CP changes.
MHHS-DIN-622 | SC | SCS | 2023-08-17 | SCS |  | Sean Cooper | SRO Design | DIP Validation of Sender Correlation ID | Implement DIP validation to check for incorrect population of Sender Correlation ID. |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Email sent to SCS. Design Team to share requirements with internal DIP Team | Clarification | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-623 | SC | SCS | 2023-08-17 | SCS |  | Sean Cooper | SRO Design | Change IF-001 Routing | Add SUPL (Linked Supplier) as an additional Primary Receipient of Inital Registration Event |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Add SUPL (Linked Supplier) as an additional Primary Receipient of Inital Registration Event | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-624 | ME |  | 2023-08-18 | MHHS |  | Miriam Ellis | SRO Design | BP013 DDE Updates | MHHS test team have identified discrepancies within the ECS BPM's that require updates to align with the ECS reports. Updates are required to BPM13 DDE |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Updates to BPM013: 1. Update reference of MHHS-REP-001 to ELEX-REP-001 in BP header 2. Update reference of REP-005 to ELEX-REP-005 in BP header 3. Reference of MHHS-REP-002A included with BP header 4. Reference of REP-002 changed to ELEX-REP-001 | Clarification | Supporting Docs | Reporting Catalogue | BPM013
MHHS-DIN-625 | SC | SCS | 2023-08-18 | SCS |  | Sean Cooper | SRO Design | B092 should also be array to allow MPRS to populate multiple rejections | B092 should also be array to allow MPRS to populate multiple rejections |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Consider breaking out DI-980 into an array in B092 block of IF-035. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-626 | SC | ESG | 2023-08-22 | ESG |  | Sean Cooper | SRO Design | Update Routing of IF-003 | Routing of this flow should match that of the IF-037 - in that a copy should also be sent to the Supplier. IF-003 Routing table updated to show Supplier as being a receipient of the iF-003 |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Routing of this flow should match that of the IF-037 - in that a copy should also be sent to the Supplier. IF-003 Routing table updated to show Supplier as being a receipient of the iF-003 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-627 | SC | ESG | 2023-08-22 | ESC |  | Sean Cooper | SRO Design | Update Interface Doc "Correlation ID Required" to "Correlation ID Created" | Inconsistancy indentified in the column headings across different IFs. All should read "Correlation ID Created" as this column denotes if the DIP IF should create/copy a DIP Correlation ID value or not. |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Update Interface Doc "Correlation ID Required" to "Correlation ID Created" | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-628 | SC |  | 2023-08-23 | MHHS |  | Sean Cooper | SRO Design | Add in Missing IF-021 Validation | Add NEW validation to ensure that "UTC Settlement Date" has time of Midnight UTC. Added clarification to existing validation rule that time element of "Settlement period end date time" should align with Settlement period duration |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Add NEW validation to ensure that "UTC Settlement Date" has time of Midnight UTC. Added clarification to existing validation rule that time element of "Settlement period end date time" should align with Settlement period duration | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-629 | MF |  | 2023-08-25 | MHHS |  | Mike Fensome | SRO Design | Routing for SUPC on IF-037 | To ensure that the outgoing Supplier are correctly notified of de-appointment of their Service Providers, routing rules for SUPC updated to Primary routing for IF-037 |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | SUPC routing moved from Secondary to Primary for IF-037 for all events | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-630 | MF |  | 2023-08-25 | MHHS | N/A | Mike Fensome | SRO Design | Remove incorrect arrow on BP002 | Arrow incorrectly added into BPOO2 between steps 225 and steps 245 |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Arrow between steps 225 and steps 245 on BP002 removed. Previously added in error. | Process Model correction | Minor | Interfaces | BP002
MHHS-DIN-631 | SC |  | 2023-08-29 | MHHS | N/A | Sean Cooper | SRO Design | Swagger Alignment - Block B051 | Required Data Items field names do not match those specfied in the defintion. |  | Implemented |  | Interim Release 4 | 2023-08-16 | loadShapeGSPGroup and loadShapeDomesticPremiseIndicator added to Required fields section to align with block definition. | Correction | Minor |  | DES-138 Interface Cat
MHHS-DIN-632 | SC |  | 2023-08-31 | Helix | N/A | Sean Cooper | SRO Design | Header & Footer Requirements for ISD Entity Files | ISD Specification should be updated to include specification/definition of a standard Header and Footer to be applied to each ISD Entity CSV file. |  | Requires Industry Work Group review |  | Interim Release 6 | 2023-10-18 | DRG to decide on exact content/structure of Header ... Is a footer required? If so what should it include (eg number of Entity entries)
MHHS-DIN-633 | SC |  | 2023-08-31 | Helix | N/A | Sean Cooper | SRO Design | Update to ISD E45 | Update Entity 45 - Market Role code needs to allow Blanks in order to align with other tables in ISD and to provide for [new] Market Participants who dont have a legacy market particpant role code |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Update Entity 45 - Market Role code needs to allow Blanks in order to align with other tables in ISD and to provide for [new MHHS] Market Participants who dont have a legacy market participant role code | Clarification | Supporting Docs | Supporting Document | ISD Entity
MHHS-DIN-634 | KH |  | 2023-09-01 |  | 6616 | Tym Huckin | Consultancy | Update UMSDS Method Statement with correct comments for Null value | In row 2, where we have a "live" summary but it is de-energised, it says to put "A" actual data flag and use Estimation Reason Code "7", but the DI-076 column in that row says this should be Null. |  | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | Reason code is Null and comments will be updated to: If a D0388 has been received with load associated data and the MPAN is de-energised the load should be calculated, submitted as ‘A’ Flagged but with an Estimation Reason Code of Null | Correction | Minor | Method Statement | UMSDS Method Statement
MHHS-DIN-635 | RG |  | 2023-09-04 | MHHS |  | Rob Golding | SRO Design | Status Code needs tidying in StandardResponseBodyType | 4In the “StandardResponseBodyType” definition, there is a required property called "statusCode" that is not listed among the properties. Could you please address this inconsistency? |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Simple update | Data interface correction | Swagger |  | Swagger
MHHS-DIN-636 | SC |  | 2023-09-04 | MHHS |  | Sean Cooper | SRO Design | Removal of YAML Name Fields from Data Catalogue | Following discussions agreement to remove YAML fields from Data Catalouge. Swagger will be the definitive reference for the Jason/Yaml property labeling etc. |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Following discussions agreement to remove YAML fields from Data Catalogue. Swagger will be the definitive reference for the Json/Yaml property labelling etc. | Data interface correction | Supporting Docs | Interface catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-637 | RG |  | 2023-09-04 | MHHS |  | Rob Golding | SRO Design | Data Catalogue items incorrectly use maxiumim and minimum | String need to be range bounded by maxLength & minLength |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Update swagger | Dat Interface correction | Swagger |  | Swagger
MHHS-DIN-638 | RG |  | 2023-09-04 | MHHS |  | Rob Golding | SRO Design | Block: D0, Field: serviceTicketURL. DES138 specifies 'string max 225', Swagger specifies 'string max 250' | Set to 250 in DES 138 |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | DES138 update, Block: D0, Field: serviceTicketURL set to 250 | Data interface correction | Supporting Docs | interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-639 | RG |  | 2023-09-04 | MHHS |  | Rob Golding | SRO Design | DI-138-Customer-Direct-Contract-Data-Service-DIP-ID & DI-140-Customer-Direct-Contract-Metering-Service-DIP-ID | Update both to be nullable |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Update swagger | Data interface correction | Swagger |  | Swagger
MHHS-DIN-640 | RG |  | 2023-09-05 | MHHS |  | Sean Cooper | SRO Design | Custom Block: B022, Field: Metering Point Postcode. Interface Catalogue specifies CMO as ‘M’ for IF-018, all other interfaces specify CMO as ‘O’. | Update DES138 so that all versions are the same and marked as optional Custom Block: B022, Field: Metering Point Postcode. Interface Catalogue specifies CMO as ‘M’ for IF-018, all other interfaces specify CMO as ‘O’. |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Update DES138 so that all versions are the same and marked as optional | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-641 | RG |  | 2023-09-05 | MHHS |  | Rob Golding | SRO Design | Custom Block: B022, Field: Metering Point Postcode. Interface Catalogue specifies no min length, but min length of 6 specified in Swagger. | Update swagger to align |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Update swagger to align | Data interface correction | Swagger |  | swagger
MHHS-DIN-642 | RS |  | 2023-09-05 | MHHS | 7382 | Rob Golding | SRO Design | NFR0045 Performance Efficiency | this NFR does not clearly define how the DIP will throttle participants where connection are over a mutually shared mTLS connection. Shared mTLS connections will be used by many parties such as DIP Connection Providers, the requirement to use them being placed on parties that will be Placing Reliance on a Connection Provider. Effectively, this means that multiple parties will use the mTLS connection and which, under certain circumstances could see significant increases over that mTLS if more than one party’s message volumes increased. |  | Open - awaiting assessment
MHHS-DIN-643 | RG |  | 2023-09-05 | MHHS |  | Rob Golding | SRO Design | B029 Fields marked as mandatory | B029 Condtitonal mandatory marked as required. Block will be conditional |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Update DES138 & swagger | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue Swagger
MHHS-DIN-644 | RG |  | 2023-09-05 | MHHS |  | Rob Golding | SRO Design | DI-123 Profile Class has a minLength of 2 in Swagger. | add minLength clause |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Update swagger | Data interface correction | Swagger |  | Swagger
MHHS-DIN-645 | RG |  | 2023-09-05 | MHHS |  | Rob Golding | SRO Design | Clarify 'AllRoles' for DIP routing for IF-047 | Update to include MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Update DES138 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-646 | RG |  | 2023-09-05 | MHHS |  | Rob Golding | SRO Design | DT-002N-MPAN requires a minLength of 13 | add minLength clause |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Update swagger | Data interface correction | Swagger |  | Swagger
MHHS-DIN-647 | RG |  | 2023-09-06 | MHHS |  | Rob Golding | SRO Design | Replace reportId with interfaceId in the ECS reports | Replace reportId with interfaceId in the ECS reports to make S0 block consistent across all reports/interfaces |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Update swagger & MHHSP - ERI011B - ECS Reports - External v5.4 | Reporting correction | Supporting Docs |  | MHHSP - ERI011B - ECS Reports - External Swagger
MHHS-DIN-648 | KH |  | 2023-09-06 | St Clements |  | Vicki Holland | Software Provider | DI-496 data item | This data item was given a max value of 48, however the max value should be 50 to allow for the clock change day in October which has 50 settlement periods. |  | Closed |  |  |  | All settlement reports are in UTC and all days have 48 SPs
MHHS-DIN-649 | SC |  | 2023-09-06 | MHHS |  | Sean Cooper | SRO Design | REGS-EES 'Refresh' Flow - IF-051 | Following discussion with SCS and EEC - proposed definition of refresh message iF-051 |  | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | Inital draft reviewed by EES and SCS - revisions to follow.
MHHS-DIN-650 | BK |  | 2023-09-06 | MHHS |  | Rob Golding | SRO Design | Introduction of Compressed Payloads into DIP Messages | Detailed analysis of the some of the ECS reports, specifically REP003, has found that some of the reports can potentially grow to a very large size ~ 12MB. Within MHHS message design there is a notional upper limit for the size of messages which is 1MB, and hence these messages will exceed this constraint. | CR030 | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | The proposal is that the Sender (ECS) compresses the report and base64 encodes the data into the CustomBlock. The recipient will know that a specific message flow is compressed, and hence will need to decompress the payload. The proposal is to use gzip for the compression. This new pattern for compressed payloads will be initially introduced for the following reports: REP-002 LDSO report for DUoS – aggregated data REP-002A Embedded Network report for DUoS – aggregated data REP-003 BM Unit Allocated Demand Volumes to Market Participants REP-004 Supplier Deemed Take Report REP-006 Aggregated Uncorrected volumes by CCC to Market Participants REP-007 VAS Exception Report to Suppliers and BSCCo REP-008 MDS Exception Report to LDSOs REP-009 EMRS Report for Suppliers | Data interface correction | Technical Artefact | Technical Artefact | E2E001 E2E Architecture Document Swagger 1.5 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-651 | MH |  | 2023-09-07 | MHHS |  | Kevin Spencer | SRO Design | Supplier Registration of ABMU/ MPAN mapping DIN | There is a design gap around Supplier ABMU Mapping held by ELEXON. Suppliers will need to register their MPAN/ ABMU Mappings for MHHS. Currently, they send a D0297 to HHDAs to provide the Mapping and can populate the SVA Metering Service Register for MSID Pairs where they are used in the Balancing Mechanism using the P0278 and self-service via ELEXON Kinnect. The issue is that for MHHS the export might be with one Supplier and the import with another. The validation in Kinnect only supports a pair being submitted mapping both import and export to the ABMU. Likewise, the P0278 only supports the provision of MSID pairs. We think a new flow may be needed or the D0297 re-routed to PMP. |  | Open - awaiting assessment
MHHS-DIN-652 | RG |  | 2023-09-07 | SRO Design |  | Rob Golding | SRO Design | DI-091-Number-Of-Displayed-Register-Digits update in DES138 to reflect the range 0-9 | max/min values on DI-091-Number-Of-Displayed-Register-Digits update in DES138 to reflect the range 0-9 |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Update DI-091 in the data catalogue to have the correct min (0)/ max(9) values | Data interface correction | Supporting Docs | Interfaces | DES138 - Interface Doc
MHHS-DIN-653 | RG |  | 2023-09-07 | SRO Design |  | Rob Golding | SRO Design | MO block removed from IF-047 | MO block removed from IF-047 |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | MO block removed from IF-047 | Data interface correction | Supporting Docs | Interfaces | DES138 - Interface Doc
MHHS-DIN-654 | RG |  | 2023-09-07 | SRO Design |  | Rob Golding | SRO Design | RMP/MPO status maxlength | Reduce maxlength to align with eumerated type (50->1) |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | MO block removed from IF-047 | Data interface correction | Supporting Docs | Interfaces | DES138 - Interface Doc
MHHS-DIN-655 | RG |  | 2023-09-08 | SRO Design |  | Fredrik Omland | Software Provider | Add a set no addtional properties to false | Adding a set no addtional properties condtion to the swagger objects improves the validation |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Add addtionalProperties: false to all schema objects in swagger | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-656 | SW |  | 2023-09-11 | SI Design |  | Steve Weston | Central Body | All S1 properties to be mandatory | Ensure all S1 properties are mandatory as per DES-138 in Swagger 1.5 |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Ensure all S1 properties are mandatory as per DES-138 in Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-657 | ME |  | 2023-09-11 | SRO Design |  | Miriam Ellis | SRO Design | NEW ISD Entity | A request has come in from St Clements requesting for a New ISD entity which lists settlement period quality indicators, with a mapping to an actual or estimate indicator. |  | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18 | ISD Entity M19 Settlement Period Quality Indicators has been added to the ISD entity document. | Data interface correction | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-658 | ME |  | 2023-09-12 | SRO Design |  | Miriam Ellis | SRO Design | Updates to ERI011B | Following an internal review of the external ECS reports a few discrepancies have been highlighted that need to be amended |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Changes to ECS External Reports 1. MHHS-REP-006: Block R051 Demand Disconnection Event Details - parent updated to R032 2. Data Catalogue: Format of DI-492, 496, 487, 488, 484 updated to reflect MHHS Data Type | Design Ambiguous | Supporting Docs | Various documents | ECS Reports
MHHS-DIN-659 | RG |  | 2023-09-12 | SRO Design |  | Rob Golding | SRO Design | Update REP007 | Update REP007 to include blocks R007 |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | Update REP007 to include blocks R007 | Design Ambiguous | Supporting Docs | Various documents | ESC Reports
MHHS-DIN-660 | ME |  | 2023-09-12 | St Clements | 4513 | Vicki Holland | Software Provider | Supplier version of REP-002 | St Clements are requesting for one report per supplier that covers all combinations of distributor and GSP group. The current solution for REP-002 is a supplier will receive a report per distributor id |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | REP002 has been split into two separate reports. There is now a Supplier version (MHHS-REP-002) and an LDSO Version (MHHS-REP-002B). Due to this change the MDS BPM/BPD (019) and DDE BPM/BPD (013) have also been updated to include the reference of REP-002B | Reporting correction | Supporting Docs | Various documents | MHHSP - ERI011B - ECS Reports - External v5.4 BP013 Demand Disconnection BPM/BPD v5.1 BP019 Market-wide Data Service BPM/BPD v5.1
MHHS-DIN-661 | RG |  | 2023-09-13 | IMSERV |  | Liam Lowey | Software Provider | Use of the term 'GUID' in messages | Messages are referring to "Device ID" data items as "GUID". For example "GPFGasGUID" in IF-004. However, a Device ID is not a GUID which is 128 bit number with a specific format. The Wikipedia article for GUID gives more information. Instead, Device IDs are 64 bit. This is misleading to implementors and maintainers. Could the naming of the properties be changed to reflect the identifier better? For example this appears to be a collection of 8 bytes in hexidecimal, i.e. a 64-bit quantity or 8 octets. Much like a MAC address or EUI64 for DCC is. Do you have other identifiers like this that require definition could we standardise on a different name for all of them? |  | Initial Assessment/Updating |  | Interim Release 6 | 2023-10-18
MHHS-DIN-662 | SW |  | 2023-09-14 | SI Design |  | Steve Weston | SI Design | Update SortCode and Account Number validation | DT-035-Sortcode and DT-035-Bank Acount Number have incorrect min / max Lengths. Sort Code should be min 6, max 6 with a regex applied for validation. Account number should be min 8 and max 10, with a regex for extra validation |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | DT-035-Sortcode and DT-035-Bank Acount Number have incorrect min / max Lengths. Sort Code should be min 6, max 6 with a regex applied for validation. Account number should be min 8 and max 10, with a regex for extra validation. This needs to be updated in DES-138 and Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-663 | SW |  | 2023-09-14 | SI Design |  | Steve Weston | SI Design | There are missing regular expressions that would improve the swagger schema validation | There are various data types that would benefit from regex added to improve validation. In addition, there could be new data types created / regex added to improve consistency and validation. |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | There are various data types that would benefit from regex added to improve validation. In addition, there could be new data types created / regex added to improve consistency and validation. This needs to be updated in DES-138 and Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-664 | SC |  | 2023-09-14 | St Clems |  | Sean Cooper | SRO Design | Message [Error] Status Message Addressing | Based on feedback from SCS review the Message Status section of E2E to make it clearer that the "Sender ID is system sending the error, so if MPRS was sending an error it would be the REG DIP ID And Recipient ID would be who you are sending the error to – so would be the S1.senderDIPID on the original message" |  | Open - awaiting assessment |  | Interim Release 6 | 2023-10-18 |  |  |  |  | E2E Architecture Doc
MHHS-DIN-665 | SC |  | 2023-09-14 | St Clems |  | Sean Cooper | SRO Design | Tidy up Of "where availible in Registration" usage | IF-001 / IF-002 /IF-036 Block 5 - Block 5 & IF-003 Blocks 095/096 & IF-033 Block 072 & IF-037 Block 10 and 11 heading had a note refering to Interface notes section which explained that block info may not always be availible. This was inconsistant with all other blocks which use the phrasing "Where Availible in the Regisration Service".... Block 5 updated to be consistant. IF Notes on each of these IF remain unaffected. |  | Ready for Internal Review |  | Interim Release 5 | 2023-09-20 | IF-001 / IF-002 /IF-036 Block 5 - Block 5 & IF-003 Blocks 095/096 & IF-033 Block 072 & IF-037 Block 10 and 11 heading had a note refering to Interface notes section which explained that block info may not always be availible. This was inconsistant with all other blocks which use the phrasing "Where Availible in the Regisration Service".... Block 5 updated to be consistant. IF Notes on each of these IF remain unaffected. | Data interface correction | Supporting Docs | Interfaces | DES138 - Interface Doc
MHHS-DIN-666 | SW |  | 2023-09-15 | SI Design |  | Steve Weston | SI Design | Data Type / Data Type Reference inconsistencies between DES-138 & Swagger | Fix any IR5 Data Type / Data Type Reference inconsistencies between DES-138 & Swagger (between Data Catalogue Tab and IF / Common tabs) |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Fix any IR5 Data Type / Data Type Reference inconsistencies between DES-138 & Swagger (between Data Catalogue Tab and IF / Common tabs). This needs to be updated in DES-138 and Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-667 | SW |  | 2023-09-16 | SI Design |  | Steve Weston | SI Design | Mandatory / Optional blocks inconsistencies between DES-138 & Swagger | Fix any IR5 Mandatory / Optional blocks inconsistencies between DES-138 & Swagger |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Fix any IR5 Mandatory / Optional blocks inconsistencies between DES-138 & Swagger. This needs to be updated in DES-138 and Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-668 | SW |  | 2023-09-17 | SI Design |  | Steve Weston | SI Design | Nullable / Optional Data Type / property inconsistencies between DES-138 & Swagger | Fix any IR5 Nullable / Optional Data Type / property inconsistencies between DES-138 & Swagger |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Fix any IR5 Nullable / Optional Data Type / property inconsistencies between DES-138 & Swagger. This needs to be updated in DES-138 and Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-669 | SW |  | 2023-09-18 | SI Design |  | Steve Weston | SI Design | Min / Max Values inconsistencies between DES-138 & Swagger | Fix any IR5 Min / Max Values inconsistencies between DES-138 & Swagger |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Fix any IR5 Min / Max Values inconsistencies between DES-138 & Swagger. This needs to be updated in DES-138 and Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-670 | SW |  | 2023-09-15 | SI Design |  | Steve Weston | SI Design | Unclear whether webhook URL's accept ports | Need to make it clearer in E2E design and Swagger whether port numbers are allowed in webhook / URLs and any formatting / options for environments |  | Initial Assessment/Updating |  | Interim Release 5 | 2023-09-20 | Need to make it clearer in E2E design and Swagger whether port numbers are allowed in webhook / URLs and any formatting / options for environments | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
Formulas:
Objection Cut-off Date = IFNA(VLOOKUP([Target Release],[1]!Table2[#All],3,FALSE), " ")

## DIN Log (2) (hidden)
DIN ITEM DETAILS | [11 empty] | Scheduling |  |  |  |  | DIN IMPACT ASSESSMENT |  |  |  |  | DIN OUTCOME
Reference | Created BY | other Reference(s) | Date Raised | Organisation | Freshdesk Ticket # | Contact Name | Constituency | Title | Design Issue Notification Details (as notified by participant) | Related CR | Current Status | DIN Type | Who is impacted? | Target working Group Date (If Required) | Target Release | Objection Cut-off Date | Design Issue Proposed solution | Justification/Type of Change | Design Area | Design Area - L2 | Artefact(s) Impacted | DAG Review Date | DAG Outcome | Reason for Rejection/Accept caveats | Design Change Reference Number | Internal Freeze Date
MHHS-DIN-1 |  | T4-COM-1744 | 2023-01-30 | St Clements | 2655 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1744 on 15th Sept 2022 MPRS does not currently restrict IHD Installs to Smart Meters, there maybe cases where there is an IHD present but the Meter is Trad (Not compatible with DCC and Customer Switched) Either Allow IHD on all Market Segments OR Cleansing to ensure IHDs are only present on S2 and S1 Meters SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses, as this is still not resolved |  | Implemented |  |  |  | Interim Release 1 |  | Discussed with SCS and agreed to add new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) Added requirements into BRS003. SCS to raise a potential data cleanse. | Requirement correction | MPAN Ownership | SCS Validation | MHHSP-BRS003-Registration Requirements | MHHSP-BRS003-Registration Requirements
MHHS-DIN-2 |  | T4-COM-1745 | 2023-01-30 | St Clements | 2657 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1745 on 15th Sept 2022 DB002 is not the interface on which MPRS will be informed of a change to import/export relationship, it is DB05. The wrong diagram was updated, the EDI was updated to DB05 not import/export. SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses and artefact updates, to inform the wrong data item diagram was updated. However the diagram for EDI updates is still incorrectly reading DB005 update instead of DB02 |  | Closed | [5 empty] | This appears to have been missed in v4.6 - the arrow on BP-010B from step435 to Step 440 shows DB005 (not DB05, assume that’s a minor typo in the comment) - and this is the Energy Direction Information (EDI) which is wrong. It has cbeen onfirmed that this was updated in v4.7 to go into v5.0 baseline. | No Change |  |  | None | None
|  | T4-COM-1752 | 2023-01-30 | St Clements | 2661 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1752 on 15th Sept 2022: MHHS-BR-RS-020: "Retro" (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier ) In the D0205 the Supplier can cancel out the current Agent Appointment by setting the EFD to equal the currently stored Appointment EFD. Is this no longer allowed? All Services must be appointed for at least one day valid or not? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: removing the ability for Suppliers to Correct Invalid Service Appointments may not be understood by suppliers. We want to avoid a later Design CR to add this functionality in. SCS has not had a response, feel this is important discuss with Suppliers to avoid later CRs |  | Closed | [5 empty] | The appointment can be resubmitted if it hasn’t been accepted yet. Once accepted, there is a need to maintain contiguous appointment periods. The scenario mentioned is the CoA not linked to a switch, so the acceptance of a new appointment from a particular EFD will ‘lock in’ that date and the previous MS/DS will be de-appointed at midnight on the previous day. This is to ensure that there are no periods left without MS and/or DS in place, which can happen today with D0155/D0151 sequencing issues. As an overall comment, there is not a concept of cancellation of appointments. The only way to alter the appointment is to get a new IF-031 issued. The only way to do this for the scenario presented, would be to issue an IF-031 for the old MS for the original date and an IF-031 for the new MS for the revised date. Requirement MHHS-BR-RS-021 ensures that Registration Service will action the latest received appointment where there are duplicate appointments for the same day. St Clements had requested that we build in a rule saying that you cannot submit a Change of Service Provider (CSP) request for the same Service Provider. It is a bit of a work-around, but we believe sending it as SEG should work, or alternatively a CR would be required to re-look at the interface validation. Closing, as this doesn't require further action - point noted. We have already spoken to a number of suppliers, and will continue to engage to ensure the functionality of the baselined design is understood and any issues picked up as early as possible. Documentation for LDSOs to point at. Pick up in Code Drafting as well. | No Change |  |  | None | None
MHHS-DIN-4 |  | T4-COM-1755 | 2023-01-30 | St Clements | 2666 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1755 on 15th Sept 2022: MHHS-BR-RS-071.2 REC CP R062 has been raised to remove the restriction on the number of EDI changes. Will this cause any downstream MHHS issues? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Needs to be aligned with REC Change No responses |  | Closed | [5 empty] | As per original SRO response, the impacts of the REC change need to be dealt with through the REC change process and impact assessment. | No Change |  |  | None | None
MHHS-DIN-5 |  | T4-COM-1760 | 2023-01-30 | St Clements | 2667 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1760 on 15th Sept 2022: There are no Registration Service Reports defined in MHHSP-ERI011A. Will there be a requirement for MPRS to produce any Industry Reports for MHHS? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Design for the complete solution must be defined by M5. This is a DBT Design Start Blocker No responses This could significantly increase DBT time as development of reports can be costly and time consuming |  | Closed | [5 empty] | Who is raising these requirements? What happens today? Possibly CC issues Agreed with SCS that reporting requirements will be introduced via the CR process. Reporting requirements are to be added to the programme RAID log | No Change |  |  | None | None
MHHS-DIN-6 |  | T4-COM-1761 DI-7 | 2023-01-30 | St Clements | 2668 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1761 on 15th Sept 2022: IF-005, REG1014 First MAP Block, MAP Eff From Date [DI-054] in message, must = MPAN Install date OR >= Eff Form date of all existing MAP Effective From Dates held in Registration prior to first [DI-054] in message I understand that the First MAP must equal the Install Date, I am unsure what the second condition is trying to say? You can not have a Meter Without a MAP. (ignoring customer owned meters where CUST is used) SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: response is incorrect. The Second Rule "Each subsequent MAP Effective From Date [DI-054] must be > MAP Eff From Date in previous block" covers the subsequent overlapping MAPs. The second half of this First Block Rule must be removed. The First Block can only ever equal the install date No responses, the rule has not been amended |  | Implemented |  |  |  | Interim Release 1 |  | This appears valid - the first MAP block can only start at the creation date (assuming the MAP blocks are in chronological order, which they must be if each subsequent map block has an EFD > the last) Currently the design allows 2 ways to amend the MAP History as outlined in Sections 13 and 14 of the IF005 Use Case Guide. Either the Metering Service can provide the full MAP history from the installation date or they can add a new MAP to the existing history, provided it is the next MAP in chronological order. So for example if you have MAPs 1,2 and 3, then you can extend to MAPs 1,2, 3 and 4 using the approach set out in section 14 to extend the MAP history. However if you wanted to set MAP 4 between 2 and 3, you would need to send the whole MAP history from the install date and provide 1,2,4 and 3 as set out in Section 13 to replace MAP history. The second validation rule is required if you are using the extend the MAP history functionality. Added note to REG Notes that where a MAP history is provided it must be in chronological order Added new REG1014 Validation Rule to MeterInstall and MeterExchange events to ensure only 1 MAP block is provided | Data interface correction | MPAN Ownership | SCS Validation | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-7 |  | DI-8, DI-11, DI-12, DI-14 | 2023-01-30 | St Clements | 2669 | Madison Layton | Software Provider |  | MPRS will reject any PUB-031 including those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8) |  | Implemented |  |  |  | Interim Release 1 |  | See Comments Revised CSS Registration Request ID validation on IF-031, 034 and 025 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | IF General | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-8 |  | N/A | 2023-02-01 | Elexon | 2642 | Sedef Kiris | Central Body |  | We have had the following comment ........... Also just found out that “Metering Service Id” have “MPID” in brackets afterwards, and not “MSID”. We believe it should be MSID |  | Closed | [5 empty] | MPID is the correct term here, it is the metering service MPID. MHHSP_EDI012_ISD_Entities v4.6 Section M8 | No Change |  |  | None | None
MHHS-DIN-9 |  | N/A | 2023-01-30 | St Clements | 2672 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: [UpdateSiteTechnicalInfoMS] is not included in the interface catalogue and is not utilised by MPRS. Assume this is related to Issue 99 and needs removing? (raised as DI ID 9) |  | Implemented |  |  |  | Interim Release 1 |  | Removed from IF-005 Guide Section 4.1 | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-10 |  | N/A | 2023-01-30 | St Clements | 2799/2670 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: Is the currently appointed Meter Service informed of Prospective MS changes? Changes to MTDs can be made by prospective MS (e.g. change meter type to complete SEG market change before the MS can be appointed). As the MS is only prospective at this point the MS may still be lapsed and not take effect. However any MTD updates made would remain within the MPRS system and not be backed out. The current MS would therefore need to be aware of what changes have been made by the prospective MS. (raised as DI ID 10) |  | Closed | [5 empty] | BP009 only talks about the Metering Service, not the current or prospective Metering Service, and it appears only the registration service receive metering service MTD details, not the current MS. Refer to SRO - what is the assumption here, as the alternative route is for registration to update the current MS The design is based on PUB-006, with the Updated Meter details, being sent to the current Metering Service ( BP011A step 280 ) as well as the Prospective Metering Service (Step 275). It is built into the routing rules in PUB-006. | No Change |  |  | None | None
MHHS-DIN-11 |  | N/A | 2023-01-30 | St Clements | 2675 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install / Remove Date(s) takes place within the Metering Services period of ownership (or proposed period of ownership for in the case of a prospective SEG appointment) " Sent on 11th Jan: Does not match business rules, as future dated installs are not allowed: "REG1020 - Meter Install Date [DI-057] cannot take place in the future. The proposed MS on a seg will have a future dated EFD, so they only have the +2 day lapse extension period for meter installs (raised as DI ID 11) |  | Implemented |  |  |  | Interim Release 1 |  | Added change of segment scenario's to IF005 USE CASE Guide. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES229-IF005_UseCaseguide |  | Refer back to SCS as additional comentary needed on the issue and bring to next meeting
MHHS-DIN-12 |  | N/A | 2023-01-30 | St Clements | 2679 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install /Remove Date(s), cannot have taken place in the future" Sent on 11th Jan: It would be useful to have the Change of Segment process covered in this guide. We are not sure how the Prospective MS can exchange meters when their appointment period is in the future (raised as DI ID 12) |  | Implemented |  |  |  | Interim Release 1 |  | Nomenclature issue - requires a reword of this statement to conform to the business rules. Recommend the following update to section 3.2 of the IF005 Use Case Guide to confirm who can make Metering updates Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed BAU metering updates ( For the avoidance of doubt not meter update/meter history updates), it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. The one exception, is during a change of segment, when the incoming Metering Service is able to provide a BAU metering update, where it’s prospective “SEG” appointment is due to become active on the same day. SEG scenario's added to IF005 Use case guide Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-13 |  | N/A | 2023-01-30 | St Clements | 2683 | Madison Layton | Software Provider |  | Comment on Section 5.1 "validation allows for meter removal at a point following Disconnection if required)" Sent on 11th Jan: This rule prevents this REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational (raised as DI ID 13) |  | Implemented |  |  |  | Interim Release 1 |  | This statement doesn't appear to be a convention. There is no mention of this in E2E001 End to End Solution Architecture. Believe this statement needs to be amended or removed. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. IF-005 validation Rule changed to include meter removal at status Disconnected | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES138-Interface Catalogue, E2E001 End to End Solution Architecture | MHHSP-DES138-Interface Catalogue, E2E001 End to End Solution Architecture
MHHS-DIN-14 |  | N/A | 2023-01-30 | St Clements | 2684 | Madison Layton | Software Provider |  | Comment on Section 3.2 "Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed metering updates, it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. " Statement is misleading- the 10 day period is only permitted for install, remove and exchange events, it is not listed for meterUpdate/meterHistoryUpdate in interface catalogue Also the prospective MS should be able to make changes for SEG to enable a market segment change to complete (raised as DI ID 14) |  | Implemented |  |  |  | Interim Release 1 |  | Validation rule(s) updated to constrain 10 day window to non-update events. Test in 3.2 reworded to remove ambiguity. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES229-IF005_UseCaseguide | Refer back to SCS for additional clarity on the requirement and include RecCo and bring to next meeting
MHHS-DIN-15 |  | N/A | 2023-01-30 | St Clements | 2685 | Madison Layton | Software Provider |  | Comment raised in guide, sent on 11th Jan, that the JSON examples use MPID when it should use DIP ID e.g."distributorID": "SWAL" (raised as DI ID 15) |  | Implemented |  |  |  | Interim Release 1 |  | Corrected to use Dist DIP ID | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-16 |  | N/A | 2023-01-30 | St Clements | 2686 | Madison Layton | Software Provider |  | Comment on Section 9 " Albeit that these transactions can be ‘clubbed together’ and send as a group in single overarching message/API transaction. " Sent on 11th Jan: As DIP does not protect the sequencing of events (FIFO), is there a risk that the ordering of these updates might arrive out of sequence resulting in the wrong end state? If MS space out their updates it would reduce this risk (raised as DI ID 16) |  | Implemented |  |  |  | Interim Release 1 |  | Clairifcation added to Sec 9.2 to reference Time-Stamps rather than 'clubbing' | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-17 |  | DI-017 | 2023-01-30 | St Clements | 2690 | Madison Layton | Software Provider | MAP History availability to Metering Service | Section 9 says "a supporting MAP history commencing in line with the revised Installation Date must also be provided" Will the MS know the full MAP history? Risk they could destroy the data. Potential MAP billing issues? |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Solution agreed at DRG on what MAP updates are required. Various document updates required to align with DRG decision to only maintain latest MAP. Removed section 13 from IF005 user guide plus other corrections to doc. Updated DES138 IF005 validation rules. | Missing/incorrect validation rule | Supporting Docs | Various Documents | IF-005 Use Case guide MHHSP-DES138-Interface Catalogue | IF-005 Use Case guide MHHSP-DES138-Interface Catalogue |  |  |  | 14//7
MHHS-DIN-18 |  | N/A | 2023-01-30 | St Clements | 2691 | Madison Layton | Software Provider |  | Comment on Section 9 "• When maintaining the MAP History in cases where there is no change in Meter Installation Date then the MAP history provided should commence either with a MAP Effective From Date matching the existing install date of the meter OR be greater than the most recent, already existing, MAP Effective From Date" Sent on 11th Jan: So it's possible to update ALL MAP history back to installation, or add a new MAP, but it's not possible to amend MAP history only part way back (have to go back to installation date instead every time to do this) (raised as DI ID 18) |  | Closed | [5 empty] | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • To update BRS003, requirement MHHS-BR-RS-027 to add “Registration Service must lapse any appointments that fail this validation” • Remove Rejected from Step 225 of BP002/BPD002 • Remove Rejected from label on line after step 215 of BP003. | No Change |  |  | None | None
MHHS-DIN-19 |  | N/A | 2023-01-30 | St Clements | 2692 | Madison Layton | Software Provider |  | Comment on Section 10 "E2E Architecture convention states that all data items are provided in each message even where these data items are not changing or are null" Sent on 11th Jan: Some of the items are optional not mandatory which conflicts with this statement. Not all data items need to be provided (raised as DI ID 19) |  | Implemented |  |  |  | Interim Release 1 |  | Update of E2E Doc to allow for Nullable values. | Data interface correction | Meter to Bank |  | MHHSP-E2E001 End-to-End Solution Architecture | MHHSP-E2E001 End-to-End Solution Architecture |  | Defer as a E2E clarification may be needed
MHHS-DIN-20 |  | N/A | 2023-01-30 | St Clements | 2693 | Madison Layton | Software Provider |  | Comment on Section 13, sent on 11th Jan: What should MPRS do if it holds a MAP not included in the MAPHistory block? (raised as DI ID 20) |  | Implemented |  |  |  | Interim Release 1 |  | Update "all existing history will be replaced by that contained within the message" | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-21 |  | N/A | 2023-01-30 | St Clements | 2699 | Madison Layton | Software Provider |  | Comment on Section 15.2 "It is understood that currently there a numerous instances of duplicated Meter ID’s, some of which may have overlapping installation dates. " Sent on Jan 11th: Meter id is only unique at mpan. Should not be any instances of conflicted MSNs at MPAN. Can you verify with ECOES? Or we can do a RFI to DNOs but will take time (raised as DI ID 21) |  | Implemented |  |  |  | Interim Release 1 |  | All references to duplicated MSN IDs has been removed from the document | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-22 |  | N/A | 2023-01-30 | St Clements | 2700 | Madison Layton | Software Provider |  | Comment on Seciton 15.3 "add some kind of suffix (X1, X2) to the existing Meter ID." Sent on Jan 11th: This can take the meter ID over the allowable string length (string 10), in this example it would take it to string(12) and so would be rejected (raised as DI ID 22) |  | Implemented |  |  |  | Interim Release 1 |  | As above, Section 15.3 removed from IF-005 User Guide. | Data interface correction | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-23 |  | N/A | 2023-01-30 | St Clements | 2701 | Madison Layton | Software Provider |  | Comment on Section 16.3 Sent on Jan 11th: Cancelled Flag Set. Only a logical deletion. Still held in MPRS but not visible to EES/MEM The section implies the record would be fully deleted from MPRS, however this is not correct, MPRS would set a cancellation flag that would indicate the record has effectively been cancelled/logically deleted. It would however remain in the systems database (raised as DI ID 23) |  | Implemented |  |  |  | Interim Release 1 |  | Added a statement at the end of the table in 16.3 to say "NB the registration service will only logically delete the MAP entry with a flag, it will not be deleted from the database." | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES229-IF005_UseCaseguide | Accepted
MHHS-DIN-24 |  | N/A | 2023-01-30 | St Clements | 2702 | Madison Layton | Software Provider |  | Comment on Section 17.2 "situations where multiple existing meters are identified, the selection process should be extended to include Meter Removal date (if provided) else;" Sent on Jan 11th: Shouldn’t be possible, can run an EES or MPRS RFI to confirm. Noting that MSN is only unique at an MPAN level not a databse level Related to DI-21 (raised as DI ID 24) |  | Implemented |  |  |  | Interim Release 1 |  | Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. The wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-25 |  | N/A | 2023-01-30 | St Clements | 2706 | Madison Layton | Software Provider |  | Comment on Section 17.2 "where multiple meters still exist even after matching on all three data items should be rejected and require manual intervention (i.e. request to LDSO to intervene) ." Sent on Jan 11th: There's no super user functionality for this so how could the LDSO intervene? The LDSO is not able to manually intervene in regards to MTDs, they can for some other data items such as registration data but not MTDs. (raised as DI ID 25) |  | Implemented |  |  |  | Interim Release 1 |  | Reference to LDSO User Removed - agreed with SCS that scenario should not arise provided existing SCS data rules are met | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-26 |  | N/A | 2023-01-30 | St Clements | 2707 | Madison Layton | Software Provider |  | Comment on Section 17.2 "If the MAP segment is not provided, the existing MAP history should be maintained to greatest degree possible, with ‘trimming’ to align to any revised Install / Remove Dates provided" Sent on Jan 11th: Risk that changing of the Meter Lifespan could result in MAPs being logically deleted. The MS would need to re-apply the MAP history to fit into the new meter Lifespan MS would need to understand this process/constraint (raised as DI ID 26) |  | Implemented |  |  |  | Interim Release 1 |  | Section 17.2 of the guidance document updated. Also added new validation rule REG1014 for MeterHistoryUpdate in IF-005 to ensure MAP is provided when creating a new meter picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-27 |  | N/A | 2023-01-30 | St Clements | 2708 | Madison Layton | Software Provider |  | Comment on Section 19.2 "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the permanent deletion of data, mirroring the existing functionality associated with the use of the D0312." Sent on Jan 11th: Only logically deleted, still visible in the MPRS History. Just not visible to MEM or EES Existing functionality on D0312 utilises cancellation flags not permanent deletion (raised as DI ID 27) |  | Implemented |  |  |  | Interim Release 1 |  | Reword to reflect the logical deletion. See MHHS-DIN-23 Reword this paragraph to: "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the removal of a MAP from a meters MAP history using a logical flag, mirroring the existing functionality associated with the use of the D0312." NB Main section header is incorrect - should be updated to section 19, rather than a duplicate of section 18. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES229-IF005_UseCaseguide | Accepted but note there is another DIN already raised
MHHS-DIN-28 |  | N/A | 2023-01-30 | St Clements | 2709 | Madison Layton | Software Provider |  | Comment on Section 19.4 "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories. However, this would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." Sent on Jan 11th: This functionality already exists with the MPAN History Report showing who changed what when for all MPRS data items. Will be extended to include DIP transactional information (raised as DI ID 28) |  | Implemented |  |  |  | Interim Release 1 |  | Proposed Change Reword this paragraph to: "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories, noting that this is also available via the MPAN history report which will be updated with DIP transactional information and could also be used. Any use of EES would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES229-IF005_UseCaseguide | Not discussed at meeting carry to next meeting
MHHS-DIN-29 |  | N/A | 2023-01-30 | St Clements | 2710 | Madison Layton | Software Provider |  | There should be an additional rule for USP, if DI-830/DI-833 is populated, the MS/DS Proposed Effective From Date must equal the currently held EFD for the MS/DS appointment in MPRS (raised as DI 29) |  | Implemented |  |  | 2023-04-27 | Interim Release 1 |  | Added rule for USP scenario in IF-031 to check SP Effective from date. Proposing SCS have flexibility on error codes - requires industry Working Group. Picked up as part of Change of Service Provider review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-30 |  | N/A | 2023-01-30 | St Clements | 2711 | Madison Layton | Software Provider |  | The IF-035 does not provide the opportunity for MPRS to populate a lapsed reason. Will need to be able to provide a reason for a lapsed appointment, otherwise there'll be a higher volume of unecessary supplier enquries to DNOs which will require more resource and cost. (raised as DI 30) |  | Implemented |  |  |  | Interim Release 1 |  | Additional Data Item on IF-035 for a reason comment - what reasons would these be other than gone beyond the date? Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-31 |  | N/A | 2023-01-30 | St Clements | 2712 | Madison Layton | Software Provider |  | MHHS-BR-RS-027 "Registration Service must re-run validation, in line with the validation rules set out in the appropriate interface specification, for all Metering Service appointments that have been confirmed to re-process from the Prospective Appointment Queue, to ensure that the appointment is still valid" It is not clear if MPRS would send MSAppRejected or MSAppLapsed if the appointment fails validation after it's been queued? If this is not made clear in the deisgn then there is a risk that we build to use the wrong event code, or if the code should be MSAppRejected then risk that suppliers build a design where they can't process a MSAppRejected after receiving already an MSAppAccepted from MPRS (raised as DI 31) |  | Implemented |  |  |  | Interim Release 1 |  | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • Updated BRS003, requirement MHHS-BR-RS-032 and 66 to show that appointments will be lapsed (not rejected) • Remove Rejected from Step 225 of BP002/BPD002 Also on BP003 leading from step 215 should have the rejected removed. Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Corrections also to BPM002 & BPM003 Forward Migration and BPD002 Froward Migration | Data interface correction | MPAN Ownership |  | MHHSP-BP002-Change of Service - Metering service, BPD002,MHHSP-BRS003-Registration Service requirements MHHSP-DES138-Interface Catalogue, MHHSP-BP003, MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration), MHHS-DEL969-BPD002 (forward migration) | MHHSP-BP002-Change of Service - Metering service, BPD002,MHHSP-BRS003-Registration Service requirements MHHSP-DES138-Interface Catalogue, MHHSP-BP003, MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration), MHHS-DEL969-BPD002 (forward migration) | Not discussed at meeting carry to next meeting
MHHS-DIN-32 |  | N/A | 2023-01-30 | St Clements | 2713 | Madison Layton | Software Provider |  | The interface catalogue lists setting a removal date as an action that can be used with event code meterUpdate on IF-005, however in the interface catalogue, the block B039 does not list meterUpdate as a event code that can utilise this block. Need greater clarity on whether meterUpdate and meterHistoryUpdate should apply meter installations and meter removals or not. (raised as DI 33) |  | Implemented |  |  |  | Interim Release 1 |  | The definition of a [MeterUpdate] event code is: Allows currently appointed Metering Service to amend the details associated with a currently installed meter. Therefore the appointed Metering Service must be able to remove the meter as part of an update, this is an omission from the design and a small update to IF-005 The design principle that IF-005 works on is that: • BAU transactions (Install/Exchange/Remove) that are in the Metering Services Period of ownership are covered by the Install/Exchange/Remove events • Changes to currently installed metering can be made by the Appointed Metering Service using the Meter Update event. Note this therefore includes, where required, removing the currently installed meter where it is prior to the current period of ownership. • Changes to metering history ( ie not the currently installed meter ) can be made by the Appointed Metering Service using the Meter History Update Proposed changes: Added MeterUpdate as Optional to B039 block in IF-005 and added validation rule to ensure MeterUpdate is not used to remove meters in current period of ownership picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP-DELS229-IF-005 Use Case Guide | MHHSP-DES138-Interface Catalogue MHHSP-DELS229-IF-005 Use Case Guide | Not discussed at meeting carry to next meeting
MHHS-DIN-33 |  | T4-COM-1759 | 2023-01-30 | St Clements | 2719 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1759 on 15th Sept 2022: IF-005, REG1011 Install date must be > Creation date, should this REG1011 rule apply also to meter Exchange not just meter install SCS raised as a design blocker on 7th October 2022 Still no resolution, should this rule apply to meterHistoryUpdate at least as this allows for meter installations (raised as DI 34) |  | Implemented |  |  |  | Interim Release 1 |  | An exchange will not be a creation date, and the validation already in place ensures that future installation dates will all follow each other, which means this rule isn't required. ​This shouldn't be needed for exchanges, as its covered by REG1008 (install date >= remove date), as an exchange would replace an existing meter, which at first install would be validated against creation date. Moved REG1011 to cover all scenarios in IF005 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-34 |  | T4-COM-1774 | 2023-01-30 | St Clements | 2720 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1774 on 15th Sept 2022: IF-005, REG1011 "REG1009 - MAP ID [DI_055] is not valid for MAP Effective Date [DI-054] REG1011 - Install Date [DI-057] for MeterID [DI-056] is prior to MPAN Creation Date There are many meters in MPRS that pre-date the existence of the MAP and also MPRS install dates of 1980 etc. these will break a number of rules. should these be cleansed before MHHS start? If they are valid, then the rules need adjusting"l SCS raised as a design blocker on 7th October 2022 Still no resolution (raised as DI 35) |  | Closed | [5 empty] | This could be a data cleanse requirement which is a consequential change/transition requirement, but for REG1009 - the MAP effective date should be the point at which the MAP took over the meter, and the exchange date should be after this (ie it should be after the date MHHS goes live). For Reg 1011 currently this is only valid on installs (and installs won't occur on legacy meters). If Reg 1011 is valid on exchanges, then the exchange date should also be after the MPAN creation date - if it isn't then the data should be cleansed. Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None | None
MHHS-DIN-35 |  | N/A | 2023-01-30 | St Clements | 2721 | Madison Layton | Software Provider |  | On the IF-005, should REG1028 (Install date cannot be null or blank) apply to meterinstall, meter exchange and meterupdate too? (raised as DI 36) |  | Implemented |  |  |  | Interim Release 1 |  | Requires amendment to interface validation - look at alternative validation Agree the rule should also apply for those events. Note we believe validation would fail for another reason. Eg REG1019 Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-36 |  | DI-37 | 2023-01-30 | St Clements | 2722 | Madison Layton | Software Provider | Re-alignment of rejection reasons to main block | In the summary of error codes box at the bottom of IF-005 tab the rejection reasons need re-aligning to the main block, e.g. REG1001 should read RMP stats must be Created or Operational, not just Operational As a general note across all interfaces, the rejection codes are referenced in numerous places and the respective descriptions are in many places not consistent for the same rejection code (raised as DI 37) |  | Closed | [5 empty] | Will be revisited once SCS provide definative Error Code Texts | No Change |  |  |  |  | 23/2/23 - Not discussed at meeting carry to next meeting
MHHS-DIN-37 |  | N/A | 2023-01-30 | St Clements | 2723 | Madison Layton | Software Provider |  | REG1015 (cannot be removed meter) is listed for meterHistoryUpdate in interface catalogue for IF-005. This should actually apply to meterUpdate not meterHistoryUpdate, REG1018 (cannot be installed meter) applies to metering history update (raised as DI 38) |  | Implemented |  |  |  | Interim Release 1 |  | Change accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-38 |  | N/A | 2023-01-30 | St Clements | 2724 | Madison Layton | Software Provider |  | In the interface catalogue, the IHD block B030 for IF-005 should also be optional for meterUpdate according to the IF-005 guide Section 16 Development Notes "The IHD segment, if provided as part of [MeterUpdate], relating to any currently installed meter should replace/update the IHD details currently held at the MPAN to which that Meter is associated." (raised as DI 39) |  | Implemented |  |  |  | Interim Release 1 |  | Small change to schema operation IHD information may be updated as part of the [MeterUpdate] event. The change is to add [MeterUpdate] event to block B030, so it now reads "B030 - MPAN IHD Information (Optional & may only be used with [MeterInstall],[MeterExchange],[MeterUpdate]) NB this also standardises the use of commas between event codes, rather than using the & symbol. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue | Not discussed at meeting carry to next meeting
MHHS-DIN-39 |  | N/A | 2023-01-30 | St Clements | 2725 | Madison Layton | Software Provider |  | In interface catalogue for IF-005, there needs to be a rule that if event code MeterInstall is used, then modified meter ID cannot be populated (raised as DI 40) |  | Implemented |  |  |  | Interim Release 1 |  | Update agreed | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-40 |  |  | 2023-02-01 | SI Design |  |  |  |  | Not used - raised as duplicate in error |  | Closed
MHHS-DIN-41 |  | N/A | 2023-01-30 | St Clements | 2730 | Madison Layton | Software Provider |  | In interface catalogue IF-005: The REG1003 reads Metering Service [S0.SenderID] holds valid previous appointment then Meter Install Date [DI-57] should be < [REG.App End Date] + 10 The way it's curently written suggests MPRS should accept an IF-005 from the previous appoint, even if their ETD was greater than 10 days ago, provided the install date was less than their ETD + 10. E.g the previous MS could send IF-005 two years later with Install date of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then REG1002/REG1019 should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? (Raised as DI 41) |  | Implemented |  |  |  | Interim Release 1 |  | Having looked through IF-005 Dates should be within the appointment date, and current deign does give the ability to go outside this Change the validation rule for REG1003 on events [MeterExchange], [MeterInstall] and [MeterRemoval] to "If Metering Service [S0.SenderID] holds valid previous appointment then [system date] < [REG.App End Date] + 10" Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. Rule amended after review by SCS, to remove second "if" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue | Not discussed at meeting carry to next meeting
MHHS-DIN-42 |  | N/A | 2023-01-30 | St Clements | 2784 | Madison Layton | Software Provider |  | In interface catalogue IF-005: Meter Update should apply validation REG1027 (current MS or prospective MS) not REG1012 (current MS only) to allow the prospective queued MS to update the Meter Type on a SEG change and therfore complete the market segment change and appointment. MHHS-BR-RS-132 . If the SEG prospective appointment was not allowed to update on meterUpdate event code then they would not be able to update the meter type to completed change of market segment, and would not meet the conditions needed to then be appointed in MPRS, their appointment would then lapse and market segment would remain invalid. (Raised as DI 42) |  | Closed | [5 empty] | We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error... | No Change |  |  | None | None
MHHS-DIN-43 |  | N/A | 2023-01-30 | St Clements | 2732 | Madison Layton | Software Provider |  | In Interface Catalogue, on If-005, REG1002 and REG1019 are duplicates (install/removal dates should be within MS period of ownership). We can only use one of the rejection codes and descriptions, programme should choose which one to keep and remove the other. (Raised as DI 43) |  | Closed | [5 empty] | These are testing slightly different things. The first test (REG1002) is checking that the Metering Service is an eligible party to send the request ie currently appointed OR was at the time of the install (to cover for previous Metering Services updating in the 10 day window). The second (REG1019) is checking that the Install Date is in the Metering Services period of ownership. So you could have that the Metering Service is currently appointed, but that they weren't at the install date. Eg Today is 2nd Feb, Meter installed on 27th Jan, Sending MS was appointed on 1st Feb REG1002 would pass as they are eligible as the currently appointed MS REG1019 would fail as they are not appointed at the time of the install Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None | None
MHHS-DIN-44 |  | N/A | 2023-01-30 | St Clements | 2733 | Madison Layton | Software Provider |  | Should the new rule for meter update in IF-005 also apply to meter history update? If no MAP entries provided, and revised Meter Install / Remove Dates result in no valid MAM History then reject with REGE1014 – MAP Eff From Sequence Error (Raised as DI 44) |  | Implemented |  |  |  | Interim Release 1 |  | Added REG1014 ( MAP History ) to IF-005 MeterHistoryUpdate event | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-45 |  | N/A | 2023-01-30 | St Clements | 2736 | Madison Layton | Software Provider |  | New rule for IF-005 Meter Update REG1017 could be misinterpreted as it currently reads incorrectly - need brackets to correct to how the AND and AND/OR conditions are to be applied If [DI-60] is not null AND Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null) Should read If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null)) (Raised as DI 45) |  | Implemented |  |  |  | Interim Release 1 |  | Clarification of existing design rule Change the validation rule for REG1017 to: "If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null))" picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue | Not discussed at meeting carry to next meeting
MHHS-DIN-46 |  | N/A | 2023-01-30 | St Clements | 2737 | Madison Layton | Software Provider |  | on IF-005 for Meter Exchange and meter install the rule for REG1027 has been changed, but I'm not sure the wording implements the rule intended exactly? Currently it reads as The MS must be the currently appoint MS AND the install date must be > MS EFD AND the MS must not have proposed MS app with SEG scenario in the queue. If not then reject with REG1027 - Metering Service is not currently appointed and does not hold a Prospective SEG Appointment SHould the rule actually read The MS must be the current MS OR the MS must have a proposed MS App in the queue with SEG scenario And then the other part of the rule about install date > MS should be a separate rule (with REG1019 error code). (Raised as DI 46) |  | Implemented |  |  |  | Interim Release 1 |  | Sent to Mike F for validation - SI believe wording in current documentation is correct. Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. I would suggest the wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. DIN-46 – On review we agree, the date test should always be true if REG1019 is satisfied ( with minor clarification update ), so validation rules should be updated as below: Proposed changes: REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  | Not discussed at meeting carry to next meeting
MHHS-DIN-47 |  | N/A | 2023-01-30 | St Clements | 2738 | Madison Layton | Software Provider |  | REG1001 on IF-005 does not allow for meters to be removed after a disconnection. Instead should restrict for allow other event codes but allow Status Terminated for MeterRemoval. DES204 CCR-0556 Linked to DI-13 |  | Implemented |  |  |  | Interim Release 1 |  | Rule update required picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-48 |  | DI-048 | 2023-01-30 | St Clements | 2739 | Madison Layton | Software Provider | CSS failure to apply CoS to related secondary MPANs | Unhappy path scenario:- What happens if, for whatever reason, CSS fails to apply CoS to all the related secondary MPANs MPRS receives IF-031 on primary RMP to change agent, MPRS applies this to all seocndary MPANs too But if the CoS was not received from CSS for secondary MPANs that the secondary MPANs would still currently be held for the wrong supplier Would this cause any issues downstream? (Raised as DI 48) |  | Closed | Design gap | SCS |  |  |  | Change Request to be raised against this | Other | MPAN Ownership | Related MPANs | [5 empty] | 2023-07-14
MHHS-DIN-49 |  | N/A | 2023-01-30 | St Clements | 2740 | Madison Layton | Software Provider |  | Unhappy path scenario:- If MPRS sends a IF-033 but never receives back a IF-034 then the rest of the process will not continue. The Supplier will never receive the IF-035 they are waiting for and the SP would never get appointed by MPRS. Is there a process in place to detect/resolve this scenario? (Raised as DI 49) |  | Closed | [5 empty] | There is a requirement for the Supplier to monitor for any delayed responses and request an update if not received in expected timescales. Reviewed with SCS and agreed ticket can be closed | No Change |  |  | None | None
MHHS-DIN-50 |  | N/A | 2023-01-30 | St Clements | 2741 | Madison Layton | Software Provider |  | We need clear rules to define what a valid Consent granularity looks like. Current rules don’t mention any validation around EDI. (Raised as DI 50) |  | Implemented |  |  |  | Interim Release 1 |  | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-51 |  | DI-51 | 2023-01-30 | St Clements | 2747 | Madison Layton | Software Provider | St Clements Design Query - DI 51 | We have had some feedback from DNOs asking about how systems will recover from System Misalignment because of data errors or significant downtime? We have the D0204 (Supplier) and D0209 (Data Aggregator) Refresh functions today which are not being replaced with a DIP message equivalent. I am aware of the DIP Replay function, but this wouldn’t be of any help if there were data errors, as the DIP would just be replaying the incorrect data. The Source system would need to re-send the corrected data in an agreed format. I know there is a design principle to move away from bulk loads and refreshes of data, Faster Switching took a similar approach. However today, CSS leans heavily on the MPRS Refresh function to get itself back inline and there are REC CP’s being raised to add a Refresh function to CSS for all parties (first CP being R0067). DNO’s are keen to understand the MHHS Programme’s position on and if Refresh functionality should be built into MPRS for MHHS. |  | Closed | Design gap | DNO (SCS), EES (RECCo), DIP |  |  |  | Change Request will be raised against this DIN. Refresh Functionality was rejected by the Working Groups so not in current design. Internal Design Discussion Required on if Programme position has changed on this given CSS Issue / EES Fed via DIP ?? Details provided by the Design Team to SCS and RECCo on the workings of the refresh functionality and get agreement on next steps. | Other | Supporting Docs | Refresh Process? | [5 empty] | 2023-07-14
MHHS-DIN-52 |  | DI-52 | 2023-01-30 | St Clements | 2748 | Madison Layton | Software Provider |  | For IF-005, REG-1006 and REG1013, would it make sense to include the installation date of the MPAN already in the system in the rejection description too to help MS with triage? |  | Closed | [5 empty] | DIN closed as instructed by St Clements. Old comments: Discussed with SCS potential for them to have flexibility on error messages. Industry agreement required. Participant Discussion Required | No Change | [5 empty] | Not discussed at meeting carry to next meeting
MHHS-DIN-53 |  | N/A | 2023-01-30 | St Clements | 2749 | Madison Layton | Software Provider |  | Requirement on LDSO requirements spreadsheet: MHHS-BR-LD-035 LDSO Maintain DUoS Tariff ID LDSO must set Duos Tariff ID on MPAN creation and maintain DUoS Tariff ID's in line with their Charging Method Statement. This should include updating the Duos Tariff ID, as required, following any updates to Domestic Premise Indicator, Connection Type and Energy Direction Note for MHHS, LLFC ID is being renamed as DUoS Tariff ID to make it clearer what this data item is used for. "BP010B Change of registration data" 250 However missing the respective requirement for Registration Services in the Registration Services Requirements spreadsheet |  | Closed | [5 empty] | Looked through the Registration Services Requirements spreadsheet v4.6 and it looks like DUoS Tariff ID is there - MHHS-BR-RS-091.1, MHHS-BR-RS-121 and MHHS-BR-RS-122 | No Change |  |  | None | None
MHHS-DIN-54 |  | N/A | 2023-01-30 | St Clements | 2750 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1699 on 15th Sept 2022: On the IF-031 and IF-035 there are a number of "Proposed" Data items. Should MPRS load these and updated the stored data items. Or are these data items only for passing through to Supplier and Service? SCS raised as a design blocker on 7th October 2022 We have some clarity verbally on this but nothing has been formally documented in the design artefacts. This needs to be reflected somewhere in the requirements. |  | Implemented |  |  |  | Interim Release 1 |  | Added "Appoinments - Data" section in REG Notes to highlight what data becomes effective with the appointment. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-55 |  | T4-COM-1738 | 2023-01-30 | St Clements | 2751 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1738 on 15th Sept 2022: the DB02 flow updates multiple data items on the IF-018 in one event. Can multiple EventCode be included in one IF-018 or will MPRS need to generate an individual IF-018 for each EventCode? SCS received a blank response and raised as a design blocker on 7th October 2022 |  | Closed | [5 empty] | Original response was that clarification was to be provided on 24th Oct - is this available? Which document? One at a time | No Change |  |  | None | None
MHHS-DIN-56 |  | T4-COM-1742 | 2023-01-30 | St Clements | 2752 | Madison Layton | Software Provider | Manual Correction to MHHS data items | Originally raised as T4-COM-1742 on 15th Sept 2022: BSCP604 currently allows LDSO and Suppliers to request manual corrections to Data Items held in MPRS. Will this type of Manual Correction be allowed in MHHS, if yes then this should be added to the business process to capture manual amendments and how these changes are reflected back to DIP users (IF-018 & IF-026, or a new Refresh Message?) SCS received a blank response and raised as a design blocker on 7th October 2022 Another example of this: If the MS/DS history is incorrect and cannot be amended via BAU, would the DNO be able to correct this via an exceptional error handling process? |  | Closed | Design misaligned | LDSO, Supplier and SCS |  |  |  | Covered in the retrospective changes discussion at DRG. | Requirement correction | MPAN Ownership | CSS Defects | MHHS-BPD005 Data Processing, MHHS-BRS005 LDSO overview | MHHS-BPD005 Data Processing, MHHS-BRS005 LDSO overview |  |  |  | 2023-07-14
MHHS-DIN-57 |  | T4-COM-1748 | 2023-01-30 | St Clements | 2756 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1748 on 15th Sept 2022: "Additional information field DI-120 is String200, where the existing DB03 allows a free text field of 2000 characters" SCS raised as a design blocker on 7th October 2022 This was corrected but then in v4.5 artefacts released there was a change back for DI-120 addition information field from string 2000 to string 200 in the interface catalogue data catalogue tab reintroducing the issue. For disconnection additional notes MPRS database holds 2000 characters so this field will need to be string 2000 in the IF interfaces (Raised as DI 57) |  | Closed | [5 empty] | Change to the data catalogue included in the 4.7 baseline | No Change |  |  | None | None
MHHS-DIN-58 |  | T4-COM-1789 | 2023-01-30 | St Clements | 2757 | Madison Layton | Software Provider | Valid combinations of ISD data for MPRS validation development | Originally raised as T4-COM-1789 on 15th Sept 2022: "Valid combinations of data in ISD are critical to the MPRS validation development, we must have these defined and agreed before we can start development" SCS raised as a design blocker on 7th October 2022 |  | Closed | [5 empty] | Elexon has defined the valid combinations of ISD data and these files are available on this link https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/ISD.aspx | No Change | [7 empty] | 2023-07-14
MHHS-DIN-59 |  | T4-COM-1707 | 2023-01-30 | St Clements | 2758 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1707 on 15th Sept 2022: "The Smart DS for Export and Secondary MPANs can be different to the Import/Primary DS as the Customer can choose their own DS for Export and Primary (Smart only)" The IF-031 validation rules have been amended but they are still not corrrectly reflecting the rule. The heading above both rules REG1038 and REG1039 reads: "If event type = [MSApp] OR event type [DSApp] & MPAN Segment is not 'Smart'" This heading should ONLY apply to REG1038 for linked MPANs and should not apply to REG1039 concerning related MPANs It should also have brackets to clarify the logic otherwise it could be misinterpreted e.g. "If event type = [MSApp] OR (event type [DSApp] & MPAN Segment is not 'Smart')" |  | Implemented |  |  |  | Interim Release 1 |  | This seems a valid issue. REG 1039 on linked meters should be allowed for trad meters (eg economy 7) Proposed Change: The logic issue here is that REG1039 caters for related meters, which are applicable to trad as well as smart meters. Remove REG1039 from this validation Change the validation to: "If (event type = [MSApp] OR event type [DSApp]) & MPAN Segment is not 'Smart'" Updated heading above REG1038 and added heading above REG1039 to clarify the validation rule in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue | Not discussed at meeting carry to next meeting
MHHS-DIN-60 |  | T4-COM-1708 | 2023-01-30 | St Clements | 2759 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1708 on 15th Sept 2022: "The Service Appointment Date must be equal to the SSD or there will be a period with no Service" And T4-COM-1776 also on 15th September 2022 "REG1032 - Metering Service Eff From Date [DI-830] is not contiguous - Appointment must be from [Max[Reg.MPAN_SSD] ,[Reg.ExistingMSAppFrmDate]] for a COS, it can only equal the SSD otherwise there will be a gap" This has been applied incorrectly. In IF031 rules REG1032 now reads that the MS/DS prop EFD must be = Max(SSD, existing MS/DS EFD + 1) This would restrict the MS/DS to setting the new EFD to either SSD or the day after the last MS/DS appointment, and all other dates would be rejected. It should read >= not just =. All four refrences to REG1032 in the validation rules for IF-031 references the +1 day after EFD, but the rejection description in the right hand columns for 'scneario not SEG or CoS' section does not reference this + 1. This should be corrected to be consistent with the other rules. (Raised as DI 60) |  | Implemented |  |  |  | Interim Release 1 |  | Original response to 1708: New rules added to cover all scenarios Original response to 1776: Change to be incorporated into design artefact Updated REG 1032 validation in IF-031, original single rule, split into 2 separate rules picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-61 |  | T4-COM-1445 | 2023-01-30 | St Clements | 2760 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1445 on 15th Sept 2022: "There is no mechanism to update the Profile Class. We would assume that this would be updated by the Supplier (with business rules restricting when this should be set) and confirmed on the IF-026. Please can you confirm if this is the intention or if it will be updated through another route. If so, the EES would need to know which PUB would confirm the data item had been updated. " Whilst this is now included in the design the validation rules from D0205 have not been carried over, e.g. PC/SSC need to be a valid combination. ISD will need to contain the valid PC/SSC Combinations (previously MDD Entity 11) and the validation rules in the interface catalogue will need to reference this validation against the ISD valid combinations. (Raised as DI 61) |  | Implemented |  |  |  | Interim Release 1 |  | See also DIN-58, need to find out who is defining ISD validation Updated Interface notes in IF-025 to confirm that there is no Profile Class/ SSC combination checks | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-62 |  | DI-062 | 2023-01-30 | St Clements | 2761 | Madison Layton | Software Provider |  | In the business process diagram for Registration Updates MHHSP-BP010-Change of Registation Data - v4.5, the MPL update section, the C0300 has been changed to C0400 which is incorrect, C0400 is for MAP updates. Address updates are actually sent in the C0600. (Raised as DI 62) Change raised 30 March:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly. |  | Implemented |  |  |  | Interim Release 1 |  | Also in the BPD. MHHS-BR-RS-114 also confirms this should be C0300, this appears to be a straightforward typo. Amend label between Step 20 and Step 30 on BP010A to CSS0300, and update the corresponding BPD description on step 30 Update required:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly in BP010A, BPD010 and in MHHS-BR-RS-114. | Process model correction | Metering Changes | MPAN Updates | MHHSP-BP010-Change of Registration Data MHHSP-BPD010 MHHSP-BRS003 | MHHSP-BP010-Change of Registration Data MHHSP-BPD010 MHHSP-BRS003
MHHS-DIN-63 |  | DI-063 | 2023-01-30 | St Clements | 2792 | Madison Layton | Software Provider |  | In the business process diag for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 (Raised as DI 63) |  | Closed | [5 empty] | SCS have now confirmed that C0700 is the correct reference - no need to change documentation - agreed to close | No Change | MPAN Ownership | Disconnection | MHHSP-BP007-Disconnection MHHSP-BPD007 | MHHSP-BP007-Disconnection MHHSP-BPD007
MHHS-DIN-64 |  | N/A | 2023-01-30 | St Clements | 2793 | Madison Layton | Software Provider |  | In business process diag for change of data service MHHSP-BP003-Change of Service- Data Service-v4.5 and MHHSP-BP002-Change of Service- Metering Service v3.5, this still makes reference to D0386 in the purple note boxes. This should now have changed to IF-019 (Raised as DI 64) |  | Implemented |  |  |  | Interim Release 1 |  | Update notes on BP002 and BP003 from D0386 to IF-019, and for BPM002 & BPM003 (forward migration) | Process model correction | MPAN Ownership | Change of DS | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration) | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-65 |  | N/A | 2023-01-30 | St Clements | 2794 | Madison Layton | Software Provider |  | The business process diagram for change to connection type/market segment has been amended to name only DB01, connection type is set on DB01 but it can then be changed on DB02 (Raised as DI 65) |  | Implemented |  |  |  | Interim Release 1 |  | Update label between step 220 and 225 from "DB-001" to "DB02" | Process model correction | Metering Changes | Market Segement | MHHSP-BP011-Change of Connection Type or Mkt Segment | MHHSP-BP011-Change of Connection Type or Mkt Segment
MHHS-DIN-66 |  | N/A | 2023-01-30 | St Clements | 2795 | Madison Layton | Software Provider |  | In interface catalogue, on IF-031, shouldn't rule REG1036 (MDR app EFD must be after DS app EFD), be applicable to all scenarios including SEG? Currently under section for if not SEG (Raised as DI 66) |  | Implemented |  |  |  | Interim Release 1 |  | Updated validation rule for REG1036 and made applicable to all scenario's in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-67 |  | N/A | 2023-01-30 | St Clements | 2796 | Madison Layton | Software Provider |  | Currently no rule on IF-031 that the SP appointment has to be within the prospective suppliers registration period - just that it can't be past dated. This rule will need to be added. (Raised as DI 67) |  | Closed | [5 empty] | Reviewed with SCS and agreed that this validation is covered by existing rules. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-68 |  | N/A | 2023-01-30 | St Clements | 2797 | Madison Layton | Software Provider |  | If-031 business rule missing If the Scenario is USP, the consent granularity must be the same as the existing consent granularity held within MPRS (Updates should be through IF-025 not through IF-031) (Raised as DI 68) |  | Implemented |  |  |  | Interim Release 1 |  | picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Updated Interface notes in IF-031 to clarify that Registration Service will ignore any differences in Domestic Premise Indicator/ Consent Granularity sent on IF-031 (USP scenario) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-69 |  | N/A | 2023-02-02 | ESG Global | 2653 | Luke Speakes | Software Provider |  | PUB-033 - Block 029 is conditionally mandatory for DCC Commissioned Meters, but includes DI-025 DCC Service Flag with valid values of A-Active, I-Installed Not Commissioned, N - Non Active. The title of the block, which should define whether it is mandatory or not, is not appropriate if a DCC meter has been installed and not commissioned, or is inactive. Propose following SI and SRO design discussion that title of block 029 is revised to conditionally mandatory for 'DCC Smart Meters' |  | Implemented |  |  |  | Interim Release 1 |  | Concludes this can be resolved by a minor wording change to the block title | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  | Not discussed at meeting carry to next meeting
MHHS-DIN-70 |  | N/A | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory | Addition of MDR validation rule | Elexon is required to maintain a valid list of Meter Data Retrievers in Industry Standing Data, to allow RegService to validate they're suitably qualified (DCC and SEC) MDRs are being appointed. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Design Agreement is to utilise M16 for this purpose. ISD document updated with details and examples to this effect. | Other | Supporting Docs | ISD | MHHS-EDI-021-ISD_Entities | MHHS-EDI-021-ISD_Entities |  | Not discussed at meeting carry to next meeting |  | 2023-07-14
MHHS-DIN-71 |  | N/A | 2023-01-30 | St Clements | 2839 | Madison Layton | Software Provider |  | When would event code [MSDeAppUpdate] and [DSDeAppUpdate] be used for on an IF-037? (Raised as DI 69) |  | Closed | [5 empty] | Reviewed with SCS and it is used to notify the incoming Service Providers when de-appointing and not origanally known. In case of Linked/Related MPANs individual MPANs move through the process. RS need to apply the logic for sending the updated IF-037 to all MPANs. Agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-72 |  | N/A | 2023-01-30 | St Clements | 2840 | Madison Layton | Software Provider |  | Block B018 on IF-034 and IF-035 should not be mandatory - it will only be provided for smart meters. This needs to be set to mandatory for SDS-MDRUpdate only, optional for DSAppSPResponse (Raised as DI 70) |  | Implemented |  |  |  | Interim Release 1 |  | Updated B018 block to be optional for non Smart on IF-034 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-73 |  | N/A | 2023-01-30 | St Clements | 2841 | Madison Layton | Software Provider |  | IF-026/IF-025, added new event code [SSCandProfileClass], but still kept in original [SSC] and [ProfileClass] event codes, should the original two have been removed? Particularly as the B032 group says it's madatory where event code is [SSCandProfileClass] and does not refer to [SSC] or [ProfileClass] individual event codes (Raised as DI 71) |  | Implemented |  |  |  | Interim Release 1 |  | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-74 |  | N/A | 2023-01-30 | St Clements | 2842 | Madison Layton | Software Provider |  | A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a new MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60 (Raised as DI 72) |  | Implemented |  |  |  | Interim Release 1 |  | This appears to be the reciprical change to MHHS-DIN-60 for the response interface Update description to "Check if MDR Eff Date = SSD OR on or after existing MDR Eff From + 1" Update rule to "If [DI-841] <>SSD OR <MDR Eff Date + 1" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-75 |  | N/A | 2023-01-30 | St Clements | 2843 | Madison Layton | Software Provider |  | On IF-035, overidden the description for Data Item 836 incorrectly with the description for Data Item 838 (Raised as DI 73) |  | Implemented |  |  |  | Interim Release 1 |  | Update the definition field based on the description in the data catalogue for DI-836 on IF-035 (Date From which Supplier would like Nominated MDR to take effect) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-76 |  | N/A | 2023-01-30 | St Clements | 2844 | Madison Layton | Software Provider |  | Data catalogue - changed the estimation reason code authoritative source to Registration Service, this data item is not received by, sent by or held by registration services and so the authoritative sourse cannot be Registration Service (Raised as DI 74) |  | Implemented |  |  |  | Interim Release 1 |  | The authoriative source has changed between v4.0 (from Data Service) to 4.7 (Registration Service) - have asked why the change was made, and what the authoritative source should actually be. Source updated to SDS/MDS | Data interface correction | Meter to Bank | Estimation | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-77 |  | N/A | 2023-01-30 | St Clements | 2845 | Madison Layton | Software Provider |  | Data catalogue - Added issue 99 items (CT Ratio, Phases etc) DI-170 - DI-180. Was agreed in work off meeting these items are not within the scope of MHHS, to introduce these would require a CR (Raised as DI 75) |  | Implemented |  |  |  | Interim Release 1 |  | these data items don't appear to be used in any interfaces so this could be a relatively simple change to remove 11 items from the data catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-78 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E0404 requirement is blank - row needs to be deleted |  | Closed | [5 empty] | This update was already incorporated into version 5.0 closing it here | No Change | All Areas | Technical Artefact | MHHS-E2E002 Requirements | MHHS-E2E002 Requirements
MHHS-DIN-79 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E21114 typo - should be VAS Output Retention |  | Implemented |  |  |  | Interim Release 1 |  | change as per description | Technical corrrection | All Areas | Technical Artefact | MHHS-E2E002 Requirements | MHHS-E2E002 Requirements
MHHS-DIN-80 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHSP-DES138-Interface Catalogue v4.6 - DI-846 Issuing Data Service EZ Name should be scored through in IF/ PUB21 definition |  | Closed | [5 empty] | Completed in V5.0, part can review change as part of Interim Release 2 | No Change | Meter to Bank | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-81 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier | Correction of step in BP020 | MHHSP - BP020 - Volume Allocation Service (ECS) v4.6 - Step 75 to Step 80 references report “REP-00” - needs correcting |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | BP020 step 75 to step 80 process flow REP list correction BPD020 step 75 & step 80 detail list of REP's correction | Process Model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions |  |  |  | 2023-06-16
MHHS-DIN-82 |  | N/A | 2023-02-09 | SI Design | 2716 | Rob Short | SI Design | Missing listed number of reports in BPD002 | Related to DIN-81 - BPD002 lists number of reports at step 75, BP002 does not reflect this list, missing PO275, PO214 and PO213 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | This relates to BP020 (not BP002), similar to DIN81, reconcile REP list correction on BP020 at step 75 and 80 and reconcile with BPD020 list of REPs | Process model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions |  |  |  | 2023-06-16
MHHS-DIN-83 |  | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | BP011 missing PUB-044 flow | A discrepancy with the Interface Catalogue - IF_LIST states MHHSP-IF-044 is sent to Central Settlements, DS, MS, Supplier, LDSO. IF-044 tab states it is sent to Supplier, MDS, LDSO In BP011 the PUB-044 is not sent to DS only Supplier, Settlements and EES |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Add Manage change of segment in LDSO lane on business process BP011C with a PUB-044 flow from step 570 Add new step to BPD011 Interface catalogue is already updated | Process Model correction | Metering Changes | Interface Catalogue | MHHSP-BP011 Change of ConType andor Mkt Segment MHHSP-BPD011 MHHSP-DES138-Interface Catalogue | MHHSP-BP011 Change of ConType andor Mkt Segment MHHSP-BPD011 MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-84 |  | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | DES-138 IF List Tab Consistency | IF_LIST states MHHSP-IF-020 is sent to Supplier onlyIF-020 states it is sent to Supplier, Data Service, Metering Service, LDSOIn BP010, the PUB-020 is sent to Central Settlements, CSS, EES, Supplier, Data Service, Metering Service, LDSO.This one looks like its just the Interface Catalogue that needs updating. IF-020 Updated to refect new agreed Routing |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated parties receiving PUB-020 in the IF_LIST, updated PUB-020 routing to include MDS for Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-85 |  |  | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory |  | Elexon see DIP qualification for new users being part of market entry post-programme, but want to understand how MHHSP will operate qualification during the programme. This is likely to cover the majority of participants. Discussions with SRO colleagues indicate they are assuming this is a process for the Enduring Service Operator to define. Challenge applies to non-BSC DIP participants (e.g. adaptor providers), and considerations under Issue Group 101. SI design has spoken to at least 4 participants who are operating in this space and seeking to understand how they can engage with SIT and other programme activities as a DIP connection provider (E2E Architecture - 3.3.2) |  | Closed | [5 empty] | To be handled as part of the Placing Reliance document | No Change | Qualification | Qualification | New Process - DIP Qualification for New Users | New Process - DIP Qualification for New Users
MHHS-DIN-86 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Invalid Market Segment BP011C requires SMRS to notify the Supplier of an invalid market segment. RegService requirement RS0124 states that SMRS must derive a value for Market Segment based on Connection Type and Meter Type following a Change of Metering, Change of Connection Type (Change of Unmetered Indicator) or Change of Related MPAN relationships. Given that SMRS determines segment as above, when would an invalid market segment occur, giving rise to the processes from step 560 in BP011C? Further, upon receipt of a PUB-045 Market Segment Invalid Advisory Notification, what are the next steps for a Supplier to address the issue? There are no provisions in the IF-025 for Suppliers to update Market Segment. |  | Closed | [5 empty] | Part of ongoing discussions with Code Drafting team 20/4//23 Code Drafting believe an update needs to be made to the design to update Market Segment via IF-25. This could occur when a Supplier is trying to arrange a change of segment but one of the activities has not completed on time eg the new metering has not been notified. When Registration Service tries to evaluate the segment it may not be compatible. Notification would then go to Supplier to prompt them to chase the required update, in this example chasing the Metering Service to provide the new metering details. Another example is if the LDSO has not notified a change of connection type. The Supplier may also need to send a further SEG appointment if the original has lapsed. | No Change | Metering Changes | Change of Connection Type and/or Market Segment | MHHSP-BP011, MHHSP-BPD011 | MHHSP-BP011, MHHSP-BPD011
MHHS-DIN-87 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory | Process clarification for meter removal and de-energisation on same job | Energisation Process Clarification BP009 states that change of energisation status at the same time as meter works means that BP008 will be followed - what is the process when a meter removal and de-energisation are carried out in the same job? Are both D0139 (de-energise) and D0142 (remove meter) and relevant DIP interfaces required. At the moment MEMs only have to send flows relating to meter removal |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Purple Boxes added in BP009 and BP008 to make it clear that Remove/DeEn could still be requested and carried out but MS would need to send two interfaces. Also that DeEn did not need to be notified if meter works completed within same day (ie same rules as today) | Process model correction | Metering Changes | Change of Metering | MHHSP-BP009 MHHSP-BP008 | MHHSP-BP009 MHHSP-BP008 |  |  |  | 2023-07-14
MHHS-DIN-88 |  |  | 2023-02-09 | RECCo |  | Sarah Jones | Regulatory | Update to Incumbent MS provider for Lapsed Appointments | Update to Incumbent MS provider for Lapsed Appointments Currently BP002 only addresses the positive confirmation of de-appointment from RegService (PUB-037 - step 140/231), but if there is no secured active, there is no subsequent notification to the incumbent. The prospective MS receives a PUB-035 at step 225. How should the incumbent MS determine when the de-appointment has lapsed? |  | Closed | [5 empty] | Part of ongoing discussions with Code Drafting team. It is not expected that the incumbant share the MTD via the IF-035 as early sight. IF-37 is the deappoint code they need to reflect . The Metering Service is appointed until they get de-appointed using a PUB-037. They are only receiving the PUB-035 as notification of who to send MTDs to, it is not intended as a notification of de-appointment. Incumbent Metering Service is a term used to refer to the MS appointed at the point another new SP Appointment is accepted (MS or DS), it shall be the Incumbent Metering Service's responsibility to share MTDs (ADV/Trad) to the incoming party. No change recommend CLOSE | [8 empty] | 2023-07-14
MHHS-DIN-89 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Customer Details on De-Appointment The MHHS design currently allows for customer data to be deleted or obfuscated by MS on de-appointment. Has obfuscation been confirmed as acceptable under GDPR? |  | Closed | [5 empty] | Programme has called out the need for data management wrt GDPR. It is for each participant to determine the action required based on their own GDPR Guidelines and policies. |  | All Areas | [6 empty] | 2023-07-14
MHHS-DIN-90 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | MS Appointment for Associated Export Metering Points How will an initial MEM be appointed for a new export MPAN, created post MHHS go live? |  | Closed | [5 empty] | Part of ongoing discussions with Code Drafting team - this is not a Design Issue. Design will operate as described below: The daily process monitoring (BP011C) would pick up any [new] Linked Export MPANs and ensure that the same Metering Service is appointed as the Import MPAN. If the Export MPAN is not linked, then the BAU appointment process can be followed. |  | Metering Changes | Change of Connection Type / Market Segment | MHHSP-BP011, MHHSP-BPD011 | MHHSP-BP011, MHHSP-BPD011 |  |  |  | 2023-07-14
MHHS-DIN-91 |  | N/A | 2023-02-10 | AWS | 2858 | Duncan Parsons | Software Provider |  | Document MHHS-E2E001 section 3.6 Actor Workflows Summary - Typo in the MSA Outbound. States IF-04, this should be IF-041 |  | Implemented |  |  |  | Interim Release 1 |  | Reference Corrected | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-92 |  |  | 2023-02-14 | RECCo | 2903, 2805, 2911 | Sarah Jones | Regulatory |  | Customer Direct Contract Flag (D053) Multiple tickets - RECCo, ESG and National Grid - all highlighting the same problem. The 4.7 artefacts do not consistently reflect the agreed position that the Customer Direct Contract flag can only be set by the incumbent Metering Service provider. The validation rules on the IF-038 should be updated The requirements for MS (013) and DS (34) in the respective BRS artefacts should be aligned |  | Implemented |  |  |  | Interim Release 1 |  | Added validation rule REG1075 to IF-038 in the interface catalogue Updated requirements in MS-013 and DS-034 in BRS to reflect the agreed position for D053 1/3 - ticket #3035 - SCS supportive of this change, need more detail. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue, BRS001, BRS002 | MHHSP-DES138-Interface Catalogue, BRS001, BRS002 |  | Accepted but split these into two DINs one of the updates to the BRS and deal with as a minor chnge, the other as a major for the Interface Specification change
MHHS-DIN-93 |  | N/A | 2023-02-14 | Power Data Associates |  | Tom | Data Service Provider | Work off Plan D-034D updates for exceptions to Unmetered Supplies | Work off Plan D-034D updates for exceptions to Unmetered Supplies |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | 1. Section 2.3 of MHHSP-METH004-UMSDS- EM Functions will be updated to make explicit that the following data items are not required by the UMSDS and as such will be ignored. • Consent Granularity (T4-COM-1857) • Domestic/Non-domestic Indicator (T4-COM-1830/1850) • Distributer Id (T4-COM-1826/1842/1845/1858/1859/1864/1865/1871/1875) • DUoS (T4-COM-1856) • LLF Data (T4-COM-1856) • Domestic Premise Indicator (T4-COM-1830/1850) • Metered Indicator- (D-045) 2. MHHSP-METH001- SDS Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 3. MHHSP-METH002- ADS- Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 4. MHHSP-METH009- UMSO Method Statement should be updated to make explicit that the following data items are not required by the UMSO and should be ignored (list to be reviewed and validated). • Consent Granularity • Domestic/Non-domestic Indicator • Distributor Id • DUoS • LLF Data • Domestic Premise Indicator • Metered Indicator | Method statement correction | Supporting Docs |  | MHHSP-METH004-UMSDS MHHSP-METH001- SDS MHHSP-METH002- ADS MHHSP-METH009 - UMSO | MHHSP-METH004-UMSDS MHHSP-METH001- SDS MHHSP-METH002- ADS MHHSP-METH009 - UMSO | 23/2/23 - Accepted |  |  | 2023-06-16
MHHS-DIN-94 |  |  | 2023-02-16 | ESG | 2777 | Patricia | Software Provider | IF-005 rejections | The IF_009 has 2 event codes: [MPANDisconnection] & [CSSDeRegistration]. [CSSDeRegistration] is listed as having Supplier as Secondary routing however on BP007 there is only reference to the supplier receiving the [MPANDisconnection] flavour of the flow. Please can you clarify which artefact is accurate. MHHSP – BPD009 step 145 states Where the Registration Service has rejected the metering update the DIP will publish the rejection to metering services. Supplier have the option to subscribe to this also. Your response was:- Our reading of this is that regservice will reject the PUB-006 back to sender if the IF-005 fails those rules. So just back to sender, not always meter service or supplier Therefore, does the BPD009 step 145 need to be updated to reflect that as the IF005 can only be generated by Metering Service Smart (MSS) & Metering Service Advanced (MSA) not the Supplier |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Question 1. Supplier will receive both events as outlined in BP007 (See DIN 294) Question 2. A decision was made at the DRG on 29th June to leave the messaging in BPD009 step 145 and instead update the business process model in BPD009 to give Supplier's the option to subscribe to rejections. | Process Model correction | Metering Changes | Change of Metering | MHHSP-BP009 – Change of Metering (Install / Remove / Exchange) , MHHSP-BPD009 MHHSP-DES138-Interface Catalogue | MHHSP-BP009 – Change of Metering (Install / Remove / Exchange) , MHHSP-BPD009 MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-95 |  |  | 2023-02-20 | SI Design | NA | Simon Harrison | Programme |  | Typo in the Note box about Auto Alignment of Related/Linked MPANs on the BP002 and BP003 process maps. Change 'Regisatration' to 'Registration' |  | Implemented |  |  |  | Interim Release 1 |  | Update BP002 (& BP003) call out box, also for BPM002 and BPM003 (Forward Migration) | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration) | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-96 |  |  | 2023-02-21 | SI Design | 2973 | Arif Jagot | Programme |  | Test-078 - SUPPI -Primary - Means SUPI? |  | Implemented |  |  |  | Interim Release 1 |  | Update Interface Catalogue | Data interface correction | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-97 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.4 | Typo in MHHS-METH001-5.4c "and less than 90 days months different from the UTC Date" - propose removal of months |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update Method Statement i.e This needs to be 90 days not 90 months the artefact needs to be updated | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  | 2023-06-16
MHHS-DIN-98 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.5 | Typo in MHHS-METH001 - 5.5 SDS shall use the most recent data a based on the event that triggered the |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Typo error on clause 5.5 within MHHSP-METH001-SDS Validation Estimation v5.0 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  | 2023-06-16
MHHS-DIN-99 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Working days correction | Clarify that Step 105 in the CoS Transfer read process is Working Days. Currently states 5 days |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Checked with SRO - 5 Working days for Step 105 in process, BPD003C, BR-DS-024.1 and BR-DS-024.2 | Requirement correction | MPAN Ownership | Data Services | MHHSP-BRS001 - SDS Requirements MHHSP-BP003C - Transfer of Reads MHHSP-BPD003C - Transfer of Reads | MHHSP-BRS001 - SDS Requirements MHHSP-BP003C - Transfer of Reads MHHSP-BPD003C - Transfer of Reads |  |  |  | 2023-06-16
MHHS-DIN-100 |  |  | 2023-02-21 | RECCo | NA | Sarah Jones | Regulatory | BP002 to include LDSO as recipient | Step 180 in BP002 and BPD002 does not include LDSO as recipient of traditional meter details as per the wording of the step or the BRS (BR-MS-024) (Code Drafting Log Reference CDD-29) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update BP & BPD to align with BRS and add LDSO as recipient of MTDs Updates to BP & BPD002 Forward migration for consistency | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Metering Service MHHSP-BPD002 Forward Migration BP002 and BPD002 | MHHSP-BP002-Change of Metering Service MHHSP-BPD002 Forward Migration BP002 and BPD002 |  |  |  | 2023-06-16
MHHS-DIN-101 |  | DI-120 | 2023-02-22 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. (Raised as DI 120) |  | Closed | [5 empty] | Included within CSS validation rule update. DUPLICATE See DIN-172 | No Change | MPAN Ownership |  | MHHS-DES138-Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-102 |  |  | 2023-02-22 | St Clements | 2886 | Madison Layton | Software Provider |  | SCS raised the following under MHHS-DIN-7 "MPRS will reject any PUB-031 inlcuding those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist"" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8)" They have followed up with: Just found the change that corresponds to this one in v4.7 interface catalogue – REG0005 in IF-031. Could this also be added to IF-034 so that we can apply the same validation on MDR updates? |  | Closed | [5 empty] | Proposed Change: Add validation "CSS Registration Request ID [DI-849] is valid for Registration Service", with error REG0005 - "CSS Registration Request ID [DI-849] is invalid or unknown" This mirrors a change made in v4.7 to IF-031, agreed as part of the DAG baseline of v4.7 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-103 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory |  | Confirm that D0381 will continue to be used for updates to MPL address. BP010 & BPD010 currently allow emails, SDEP and other agreed forms can be used by Supplier or UMSO to update this - propose that these artefacts are amended to reflect that the D0381 is to be retained (Code Drafting Log Reference CDD-22) |  | Implemented |  |  |  | Interim Release 1 |  | Amend Steps 10, 21, 22 to explicitly use the D0381 rather than current wording | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010 | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-104 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Impact of MHHS on SoLR arrangements | Impact of MHHS on SoLR arrangements - possibly needs an Issue Resolution Group discussion to undertake evaluation & impact assessment (Code Drafting Log Reference CDD-23) |  | Closed | [5 empty] | Extensive discussions have been held with Elexon (DIP Manager) to ensure that there is flexibility within the DIP Design to accomdate varied SoLR scenarios. These involve the existing process(s) around change of BMUnits and the ability to transfer ownership of DIP Market Participants. As the solr process does not involve any mass movement / reassignment of MP Identifiers at the MPAN level the core MHHS design is not impacted by Solr per se. |  | All Areas | [6 empty] | 2023-07-14
MHHS-DIN-105 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Related MPAN Business Rules | 1) IF-019 suggests RMP status can be Created or Operational - proposed this can only be Operational for subsidiary MPAN 2) Add validation rule to IF-019 requiring related MPANs to have consistent classification as domestic or non-domestic (reflecting the existing requirements) 3) Clarify what Registration Services should do when MPANs are related/linked and have different MS/MEM providers - is the IF-019 rejected or the MEM for the secondary MEM auto-deappointed? 4) What happens if the IF-019 fails validation by Reg Service at Step 330 in BP010? Design provides no guidance |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | 1. Removed reference to Created in the REG1001 validation rule for IF-019 2. We understand there is no existing validation within MPRS and this is not being amended as a result of MHHS implementation. This would require a wider industry change impacting CSS as Domestic Premise Indicator is managed independently of Related MPANs. 3. It would not be rejected, auto-alignment would pick up the discrepancy at the next daily run and de-appoint the export MS and appoint the import MS. 4. As with other rejected flows, the sending party should investigate the error and re-submit as appropriate. | Data interface correction | MPAN Ownership | Change of Registration Data | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-106 |  |  | 2023-02-23 | SI Design | 2955 | Kate Goodman | Testing | IF Routing | Inconsistency in DES138 for UMSO Routing 00-Introduction logs UMSO as the single routing option for Unmetered Service provision, as there can only be one UMSO related to an MPAN PUB-008 provides UMSC, UMSP and UMSI as options for secondary routing This inconsitency needs to be corrected |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | IF-008 - Secondary routing rules updated following review with Avanade (see DIN268) |  | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-107 |  |  | 2023-02-24 | SI Design |  | Simon Harrison | Progamme | Update to definition of DI-301 LLF ID in the ESC Reporting Data Catalogue | Definition of DI-301 in the ECS Reporting Data Catalogue needs to be updated as follows 'The Unique Identifier of a set of Line Loss Factors' |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Update to be made in the ECS Internal & External Reports - Data Catalogue tab against DI-301 LLF ID it should read as 'The Unique Identifier of a set of Line Loss Factors' | Data interface correction | Supporting Docs | Reporting Catalogue | MHHSP - ERI011A - ECS Reports - Internal v5.2 MHHSP - ERI011B - ECS Reports - Enternal | MHHSP - ERI011A - ECS Reports - Internal v5.2 MHHSP - ERI011B - ECS Reports - Enternal |  |  |  | 2023-07-14
MHHS-DIN-108 |  |  | 2023-02-27 | SI Design | 2966 | Kate Goodman | Testing | IF Routing | Ref:MHHSP-DES138-Interface Catalogue v4.7, IF-038, PUB-020, PUB-039. Document says that UM is relevant to these messages but UM thinks it is not relevant. Please clarify what the situation is. Raised in review of MHHSP-872 by Power Data. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Covered by Secondary routing updates (See DIN268), changes to IF-020 and IF-039 routing. No changes were required to IF-038. The design allows for Customer Direct flags to be set for any Data Service/ Metering Service (ie Including unmetered). |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-109 |  |  | 2023-02-27 | SI Design |  | Simon Harrison | Programme |  | Call out box in BP002/BP003 on Linked/Related MPANs needs to be updated as it includes reference to email/SDEP rather IF-019 as shown in BP010 |  | Closed | [5 empty] | Confirmed - the call out box on BP002/003 needs to be updated Duplicate of DIN-64 | No Change | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service
MHHS-DIN-110 |  |  | 2023-02-27 | SI Design | 2983 | Kate Goodman | Testing |  | MHHSP-BP005-Data Processing-v4.6, Step 50-160 UMSDS is referencing Submit Required UTC period level consumption data (Step 50) with a arrow going to Receive UTC period level consumption data (Step 160) but no reference of IF-021 on the connection between both - reference should be added? |  | Implemented |  |  |  | Interim Release 1 |  | On Process map requires arrow to be labelled as IF-021 from step 50 to step 160 | Process model correction | Meter to Bank | Data Processing | MHHSP-BP005-Data Processing | MHHSP-BP005-Data Processing
MHHS-DIN-111 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Originally raised as T4-COM-1691 on 15th Sept 2022: "MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days " Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5 (Raised as DI-76) |  | Implemented |  |  |  | Interim Release 1 |  | Updated to 2 working days | Requirement correction | MPAN Ownership |  | MHHS-BRS003-Registration Service requirements | MHHS-BRS003-Registration Service requirements
MHHS-DIN-112 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54 (Raised as DI-77) |  | Implemented |  |  |  | Interim Release 1 |  | Added note to clarify | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-113 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? (Raised as DI-78) |  | Closed | [5 empty] | Agreed duplicate of DIN-29 and can clsoe | No Change
MHHS-DIN-114 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | EES does not appear to have been added to the routing rules tables on the interface tabs(Raised as DI-79) |  | Closed | [5 empty] | Already present in v5 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-115 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On IF-050, this includes linked MPANs in it, but I don’t think these would ever be populated as you cannot link MPAN at MPAN creation. So EES would only ever get Linkage updates on the IF-20 Is there any value of having this therefore in IF-050?(Raised as DI-80) |  | Implemented |  |  |  | Interim Release 1 |  | Removed Linked MPANs and Related MPANs from IF-050 and added explanatory note | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-116 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | For IF-025, block B032 it states it is "MPAN Legacy Info (Mandatory where event is [SSCandProfileClass], and for Traditional Meters / Optional for other Meters)" It should just read mandtory for event code [SSCandProfileClass] and nothing else, it should not be optional for any of the other event codes(Raised as DI-81) |  | Implemented |  |  |  | Interim Release 1 |  | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-117 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?(Raised as DI-82) |  | Closed | [5 empty] | Discussed with SCS and confirmed it is a limitation of swagger output but should be array of MPAN followed by array of meters followed by array of MAPs repeated per MPAN. Awaiting confirmation can close | No Change | Metering Changes | IF-005 JSON | JSON, YAML, MHHSP-DES138-Interface Catalogue | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-118 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | In relation to the Sender Unique Reference, which is constructed as: S-<Interface>-<Participant Id>-<Role Id>-<Date>-<Sequence> (hex) I would like to comment as follows: • Why is the Unique Reference simply constructed using elements that are already contained in the message as distinct values? This just means the sender has to construct it and the receiver de-construct it? • Is the sequence number expected to be reset each day ? • It would be much easier and more logical for the Sequence to be a distinct item in the message? • Why is the sequence specified as hex? • Even given the expected large number of messages, and based on it being a number(13) (defined as Sting), a standard sequence number per Participant and Role would provide 9,999,999,999,999. If this is still seen as a limitation then it could simply be built from the date, e.g. 202301190000000001, giving a provision for up to 9,999,999,999 messages PER DAY from the same Participant / Role combination, which still enables a read every 30 minutes from every MPAN(Raised as DI-83) |  | Closed | [5 empty] | This is to send a unique reference and is used for auditing purposes. Please note the length of the Sender Unique Reference has been increased at the request of Avanade in 5.1.1. Examples updated |  | MPAN Ownership
MHHS-DIN-119 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | in swagger hub under IF-002 B907 list the B036 block, this is missing numberOfDigitsCumulativeRegister data item(Raised as DI-84) |  | Implemented |  |  |  | Interim Release 1 |  | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue. Swagger will be updated | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-120 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Inconsistency in naming of data item DI-091 In swagger hub: Number-Of-Digits-Cumulative-Register In interface catalogue IF tabs (E.g. IF-002) : Number of Displayed Register Digits In interface catalogue data catalogue tab: Number Of Displayed Register Digits (Cumulative Register)(Raised as DI-85) |  | Implemented |  |  |  | Interim Release 1 |  | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue and updated YAML accordingly | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-121 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0093 comment raised on 12/01/2023 " D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: "It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42 (Raised as DI-86) |  | Implemented |  |  |  | Interim Release 1 |  | Agreed to provide SEG scenario's in IF-005 Use Case guide. currently under review |  | Metering Changes | Change of Segment | MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-122 |  | DI-87 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0084 comment raised on 12/01/2023 following the introduction of IF-019 and respective changes in the latest set of released artefacts MHHSP-BP010-Change of Registration Data -v4.5 "Shows Supplier Mastering Import Export Linkage. BSC CP1558 introduced changes to MPRS for the LDSO to manage this via the DB05. IF-019 should go to LDSO who should then produce a DB05 into MPRS." The process diagrams and requirement spreadsheets have been amended to show MPRS loading DB05 as a IF-019 response. DB05 is not a IF-019 response, it is a request from DNO/iDNO to create, amend or remove a import/export linkage. It does not currently have any capacity to include a IF-019 rejection response to trigger a IF-020 rejection response to DIP. (Raised as DI-87) |  | Implemented |  |  |  | Interim Release 1 |  | SCS reviewing preferred option with LDSO's The following changes would be required to the LDSO overview requirements: MHHS-BR-LD-043.3 LDSO Send Import/Export relationship update LDSO must send accepted Import/Export relationship updates to the Registration Service via the appropriate interface DB05 file or other agreed mechanism BP010B Change of registration data 900 MHHS-BR-LD-043.4 LDSO Send Import/Export relationship rejection LDSO must publish rejected Import/Export relationship updates on the Data Integration Platform using the appropriate interface MHHS-IF-020 to Supplier BP010B Change of registration data 900 On BP-010 for Linked Import/Export MPANs the following would be required: 1. Need to add rejected leg from step 900 to DIP 2. Need to add PUB-020 going from the DIP to the Supplier The BPD-010 will need updating accordingly. | Process Model correction | MPAN Ownership |  | MHHSP-BP010-Change of Registration Data MHHSP-BPD010, MHHSP-BRS005, Traceability Matrix | MHHSP-BP010-Change of Registration Data MHHSP-BPD010, MHHSP-BRS005, Traceability Matrix
MHHS-DIN-123 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0083 comment raised on 12/01/2023 following the introduction of a new business rule on MPRS in the latest set of released artefacts MHHS-BR-RS-078 "MPRS cannot control how messages are sequenced at CSS and DSP. IF MPRS waits until the DSP responds before sending the Appointment message this could take hours (as this is a batch process) this will result in a delay in the appointment of the MDR. Sequencing requirements should be placed on CSS & DSP to ensure the correct MDR is appointed based on Effective dates provided from MPRS. However, they may not be necessary due to the way this interface works: The C0200 interface uses the PUT Method, which will replace the data held at CSS. Explicit ending of an Appointment is only required for a future dated appointment, this will be sent as one message with the Old and New MDR appointments. For Same Day or Retrospective the new MDR Appointment will Replace the currently set value. This implicitly ends the previous MDR Appointment. On a CoS, the MDR is linked to a Registration not a Metering Point. The previous MDR will end naturally when the Previous Registration becomes securedInactive. An explicit message to end the MDR appointment on the Previous Registration is not required . MPRS will only send two separate updates to CSS when there is a gap in MDR (SDS) appointments. For Example a change of segment to Advanced and then back to Smart. This would need to happen over a short period to generate two messages that could go out of sequence" The MHHS design team rejected with comment "The MHHS design is based upon what was agreed as part of the R044 consultation. This scenario does not reflect our understanding of how the CSS/DCC/DSP interface will work as set out under R044. " This is how C0200 currently works today and the interface is unchanged in R0044. This will put a signfiicant requirement on MPRS that will reduce time available time for other core MHHS development activities with no benefit to industry.(Raised as DI-87) |  | Closed | [5 empty] | No Change - updated in v5.0 | No Change | MPAN Ownership
MHHS-DIN-124 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0089 comment raised on 12/01/2023 "D-021 was meant to give more detail on how L1-L4 validation should be used and provide more error codes for use. This has not been done as far as I can see Blocking resolution to this T4-COM-1749, T4-COM-1769 and T4-COM-1768" Comment was closed as clarified however none of these items have been resolved and we have no dates as to when they will be. comments blocked that were raised initially on 15/09/22 Comment T4-COM-1749: "The Registration Service, as part of its L3/L4 validation should ensure that there is consistency between the data content of the IF-033 issued to the Service Provider and the [returned] content in IF-034 - if this isn't so then message should be returned to Service Provider using ""MSGStatus Message"" mechanism." Does MPRS only need to validate consistency in the data it loads on the IF-033, not the data that is not loaded" Comment T4-COM-1769: "We need validation rules to be defined for this flow, Does not match IF-031, content of the PUB-034 does not match the IF-031. No Proposed Appointment Found, PUB-034, does not link to any Pending IF031s. Define Validation Rules for PUB-034 The 034 content must match the original if-031 content the 034 must have a corresponding IF031 the 034 has already been received for the IF-031 Generic Standard Validation, MPAN exists valid in ISD ETC" Comment T4-COM-2768: "We need some generic codes for standard validation rules such as: Service/Supplier is valid in ISD MPAN exists in MPRS MPAN is not Disconnected Service/Supplier is Valid in MDD (so CSS doesn’t reject updates)" (Raised as DI-89) |  | Implemented |  |  |  | Interim Release 1 |  | Added RMP status check to IF-034 and refined validation rule notes regarding different values received from IF-033 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-125 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | IF Routing | WOA-0091 comment raised on 12/01/23 D-030 "how routing will work in the DIP has not been updated this information is required for our development" MHHS Design Team has closed as clarified however there is still uncertainty around the DIP routing, and there are not dates provided for when the detailed DIP design will be released. This will clock certain elements of development (Raised as DI-90) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Secondary routing rules updated following review with Avanade (see DIN268) |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-126 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0092 comment raised on 12/01/23 following more infromation around D-022 being clarified "D-022 Following the work off item being agreed on what is required for an MPAN to be traded - it has now been possible to fully assess the optionality of data items in the interfaces Data items still mandatory in interfaces that must be changed to optional: Annual Consumption (IF-001) Incumbent Service Providers (IF-002, IF-033) Incoming MS/DS (IF-037) These are not required at creation, nor at traded, and therefore could be non existent in MPRS when MPRS generates this outgoing IF messages Blocking resolution of T4-COM-1727 and T4-COM-1735" Closed as clarified however none of the issues listed have been resolved Annual consumption still reads madatory on a CoS for IF-001, the issue is MPRS may not have this data item. The item is not required to reach a status of traded, therefore CSS will accept a CoS on this MPAN without annual consumption being populated, and then MPRS will not be able to provide this data item on the IF-001 that results from the CoS. This must be changed to optional OR the definition on what is needed to be traded should be updated to include annual consumption. Incumbent Service Providers is still mandatory on IF-002 for CoS Again as MS is not required to be traded, CSS will accept a CoS request with or without a current MS, and so MPRS will not be able to provide an incumbent MS in these cases. It must be changed to optional or the definition of what is needed to be traded should include MS. Incoming MS/DS is still mandatory on IF-037, there are numerous reasons an appointment may be lapsed, the only change that would gaurantee a new incoming SP that MPRS could send on this flow is a change or SP (CSERV) scenario. For CoS the supplier may not have sent in new appointments, for DEREG there will be no new appoitnments, for SEG the market segment may have changed but the supplier may not have sent in new appointments, same for change of connection type, and for IMPEXP and RELATED the parent MPAN might not have MS/DS appointed at all so there would be no new appointments for MPRS to populate on this flow. This must be changed to madatory ONLY on CSERV (Raised as DI-91) |  | Implemented |  |  |  | Interim Release 1 |  | Discussed with SCS. Covered by clarification on nullable and interface notes- All these issues are resolved by the Mandatory Nullable Solution. Confirmed Annual Consumption block will only be provided where available in Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-127 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 "DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least "Registered", if no DS is appointed then there is already an appropriate Event Code" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone (Raised as DI-92) |  | Closed | [5 empty] | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-128 |  | DI-93 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0095 comment on 12/01/23 "D-009 This is blocking closure of T4-COM-1730. There is a lack of clarity around the treatment of rejection from CSS, between both R044 and the MHHS design artefacts e.g. MHHs-BR-RS-088.1 and MHHS-BR-RS-079 both suggest MPRS would still load the new MDR record and appoint in MPRS despite a rejection from DCC/CSS. Our assumption would be that we do not load a MDR appointment that is rejected from DCC/CSS and we send the IF-035 rejection to notify the DS/Supply of this. However no clarity on what to do if DCC/CSS rejects a MDR end date on a de-appointment T4-COM-1730 was raiseed on 15/09/22 MHHS Design Team Rejected the comment with a statement this is outside of MHHS Scope. How MPRS treats the MS/DS appointment and how it responds over hte DIP is within MHHS design. The requirements we are enquiring about are already included in the MHHS design documents as in scope also. This is a major blocker to MPRS design on MDR appointment processes (Raised as DI-93) |  | Closed | [5 empty] | Discussed with SCS this is a REC requirement. Agreed no error codes will be received, just use a generic response. | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-129 |  | DI-94 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0086 comment on 12/01/23 following the release of the first draft of IF-050 in the revised interface catalogue artefact "Related MPANs and Linked Import Export are not set at MPAN Creation. EES can get these on the IF020 Remove these blocks from IF-050 as they would never be populated" MHHS design team marked as accepted and changed but the blocks still exist in IF-050, these blocks will never be populated and so should be removed from the IF-050 interface(Raised as DI-94) |  | Closed | [5 empty] | Closed - duplicate of DIN-115 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-130 |  | DI-95 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0088 on 12/01/23 "D-011 & D-050 it is still unclear how LLFC and DUoS Tariff ID will be stored and managed in MPRS. DUoS should be an Alias of LLFC and not have its own data item in MPRS. LLFC will be renamed to DUoS Tariff when the old arrangements have ended. LDSO impacts having to maintain two items which will lead to billing issues" Marked as clarified and closed witih a clarification statement to be issued on tuesday 24th January, this clarification statement was not received. Awaiting clarification(Raised as DI-95) |  | Closed | [5 empty] | Email to Madison to check can close |  | MPAN Ownership
MHHS-DIN-131 |  | DI-96 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 is missing business rules: REG1001 - MPAN [DI-063] is at [REG.RMPStatus] not status Created/Operational. This should apply to IF-025. IF-025 is missing a rule that consent granualiry EFD must not be earlier than supply start date. Consent Granularity EFD must not be prior to current consent granularity EFD The Consent Granularity Energy Direction Domestic Premise Indicator Combination must be valid in ISD(Raised as DI-96) |  | Implemented |  |  |  | Interim Release 1 |  | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-132 |  | DI-97 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 IHD update does not include validation rule 1019, does this mean IHD EFD can be prior to current and effectively cancel out the current IHD status completely, or is it just an error and the rule should be added to interface catalogue for IHD?(Raised as DI-97) |  | Implemented |  |  |  | Interim Release 1 |  | Amendment accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-133 |  | DI-98 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 will not allow a SMSO to be set for a non smart meter "REG1022 - SMSO ID Cannot be set where Market Segment is [Reg.Segement]", would a non smart supplier be able to send a B031 SMSO block, they will need to be able to if they are required to clear an old SMSO by populating SMSO as null(Raised as DI-98) |  | Implemented |  |  |  | Interim Release 1 |  | Added new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-134 |  | DI-99 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 "SSC must be valid in ISD. Rejection reason: REG1044 - SSC must be a valid value in ISD" SSC are not yet populated in ISD(Raised as DI-99) |  | Closed | [5 empty] | Clarified that SSC validation will be based on Frozen MDD. Seperate DIN to cover availability of ISD | No Change | MPAN Ownership |  | MHHSP-EM021 ISD Entity Data Map, MHHSP-DES138-Interface Catalogue | MHHSP-EM021 ISD Entity Data Map, MHHSP-DES138-Interface Catalogue
MHHS-DIN-135 |  | DI-100 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Should B032 PC and SSC block on IF-025 only be permitted when theres a traditional meter fitted at the MPAN?(Raised as DI-100) |  | Closed | [5 empty] | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-136 |  | DI-101 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | How is the Green Deal Exists defined. Does this mean there's a green deal linked to the MPAN regardless of dates, does it mean there's a green deal currently active or due to become active, or does it mean there is a currently active green deal assigned to the MPAN? (Raised as DI-101) |  | Implemented |  |  |  | Interim Release 1 |  | Remove Green Deal exists (DI-110) from Data Catalogue and IF-050 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-137 |  | DI-102 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-007 Validation rule "Metering Service [S0.SenderID] holds valid previous appointment then Energisation Status EffectiveFrom Date [DI-034] should be < [REG.App End Date] + 10" The way it's curently written suggests MPRS should accept an IF-007 from the previous appointed MS, event if there ETD was greater than 10 days ago, provided the ES EFD date was less than their ETD + 10. E.g the previous MS could send IF-007 two years later with ES EFD of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then a separate rule should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? Linked to DI-41(Raised as DI-102) |  | Implemented |  |  |  | Interim Release 1 |  | REG1003 validation rule updated in IF-007 to constrain energisation updates to 10 days after the MS appointment period |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-138 |  | DI-103 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-034 Submitted rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD |  | Closed | [5 empty] | Duplicate of DIN-176 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-139 |  | DI-104 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Need clarity on what role code should be used in C0200 for MS and MDR appointments Linked to comment T4-COM-1790 which was accepted as design issue raised but then moved to a work off item "We would like to see some indicative Role Codes and DIP IDs so we can populate development systems with this data " |  | Closed | [5 empty] | Send "MDR" as role code as per Registration requirement. Allocation of DTN MPIDs is a seperate issue | No Change | Registration | Existing EMAR I/F | MHHSP-BRS003-Registration Service requirements | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-140 |  | DI-105 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 |  | Closed | [5 empty] | Discussed with SCS the IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR. Agreed to close | No Change |  |  | MHHSP-BP003A, MHHSP-BRS003 Registration service requirements | MHHSP-BP003A, MHHSP-BRS003 Registration service requirements
MHHS-DIN-141 |  | DI-106 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 |  | Closed | [5 empty] | RECCo consequential change | No Change |  |  | MHHSP-BRS003-Registration Service requirements | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-142 |  | DI-107 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | There currently aren't sufficient rules to ensure that a principal primary MPAN is not also a linked export subsidiary MPAN or that a subsidiary secondary MPAN is not also a principal import linked MPAN. The MHHS design either should accommodate both (would need clarity on how to treat cases where MPANs are BOTH principal and subsidiary) OR new rules should be introduced to prevent this occuring AND cleanse existing cases ahead of migration |  | Implemented |  |  |  | Interim Release 1 |  | Validation rules updated for IF-019 | Missing/incorrect validation rule | MPAN Ownership |  | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-143 |  | DI-108 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Requirements were uplifted in v4.5 to include logic around market segment on related MPANs MHHS-BR-RS-124.1: Registration Service must, in the case of Related MPANs and following derivation of Market Segment for individual MPANs, update the Market Segment for the Primary MPAN and all the Secondary MPANs based on the following rule: 1. If any MPAN in the Related MPAN Group has a (derived) Market Segment of Advanced, then set the Market Segment for all the MPANs to Advanced and set the Market Segment Valid Flag to "Yes" for all the MPANs This specifically cites related primary/secondary and does not mention linked import/export associations at all. But then another requirement implies maybe it should have done: MHHS-BR-RS-127: Registration Service must , in circumstances where the derived market segment is invalid (and has not been overridden by Linked/Related MPAN logic ) Should MHHS-BR-RS-124.1 have applied to linked import/export associations too or is it intended solely for primary/secondary related MPANs? |  | Implemented |  |  |  | Interim Release 1 |  | This should only apply to Related MPANs. Updated RS-127 | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-144 |  | DI-109 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131 This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to: Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. |  | Closed | [5 empty] | Duplicate See DIN-169 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-145 |  | DI-110 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. |  | Implemented |  |  |  | Interim Release 1 |  | Added L as valid value for DI-979 in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-146 |  | DI-111 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. |  | Implemented |  |  |  | Interim Release 1 |  | Agreed with SCS to reuse STD Error Response Section in IF035 to communicate Lapsed Reason . See DIN-145 for summary of updates | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-147 |  | DI-112 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-008 response block is listed as mandatory, however on disconnection the MPAN is de-energised by MPRS automatically. The supplier cannot de-energise after disconnection on the IF-007, it must be automatic at MPRS as per The de-energisation needs to be communicated on the IF-008 but it is not in response to an IF-007 and so we cannot populate the response block. |  | Implemented |  |  |  | Interim Release 1 |  | Data interface change agreed. Added Interface note to IF-008 to cover forced de-energisation changes by Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-148 |  | DI-113 | 2023-02-10 | St Clements | 2864 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-113 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { "confirmingMpid": "string", --* "registrationId": "string" --*, "updateSucceeded": boolean --* } Suggest that DI-0980 is removed from B066 |  | Closed | [5 empty] | Discussed with SCS and agreed to close - note no error codes returned from CSS so will provide generic error code | No Change |  |  | MHHSP-DES138-Interface Catalogue, JSON, YAML | MHHSP-DES138-Interface Catalogue, JSON, YAML
MHHS-DIN-149 |  | DI-114 | 2023-02-10 | St Clements | 2865 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-114 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 On IF-038 validation "REG1073 - Customer Direct Contract already exists for MPAN [DI-063] for that period" The respective validation rule for this states: If Contract End Date [DI-145] <= Max existing active MS contract end dates [Reg.MAX_DCMS_Enddate], EXCEPT IF requesting MS [S1.SenderID] = Currently Active Direct MS [Reg.CurrentActiveDC_MS_DIPID] AND Contract End Date [DI-145] <= existing active MS contract end date [Reg.CurrentDCMS_Enddate] This rule doesn't fully prevent overlapping appointments as does not cover where the MS is not currently contracted MS and ETD > current ETD which should also be rejected. Think a simpler rule would cover this scenario more fully e.g. If there is an active contracted MS/DS, and the submitting MS/DS does not match then reject And then ETD can be greater or later than current ETD for the currently contracts MS/DS anyway so doesn't need specifying? |  | Closed | [5 empty] | SRO Team do not believe that a change is required. Linked to DIN-554 |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-150 |  | DI-115 | 2023-02-10 | St Clements | 2866 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-115 in our log In some place on IF-038 tab there is reference to a future customer direct contract e.g. "OR requesting MS [S1.SenderID] <> Any future Direct MS [Reg.FutureDC_MS_DIPID] " "extended dates will be subject to checking if another Service Provider has registered a separate Customer Direct Contract covering the same period" - this can only happen if there's a future appointment "AND ALSO removing all future periods which may or may not have been accepted and recorded previously." As there is no Effective From Date included in the flow MPRS will store an Effective From Date of the system date at the time of creation of the customer contract indicator. It will not be possible to set one to start in the future as the IF-038 does not include effective from date. Is this the same understanding as the MHHS Design Team? |  | Closed | [5 empty] | As per DI-149 above SRO Design Team do not belive that any changes are required |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-151 |  | DI-116 | 2023-02-10 | St Clements | 2868 | Madison Layton | Software Provider |  | Just spotted a change in v4.7 and raised in our log as DI-116 Artefact: MHHSP-BP010-Change of Registration Data -v4.7 under MPL and GSP Group amendment section, DB02 has been amended in v4.7 to DB002. DB002 is not correct, DB02 was the correct name For reference the DB flows only ever have one 0 in, there is DB01 (MPAN creation), DB02 (MP updates), DB03 (Disconnection) and DB05 (Import/Export Linkages) |  | Implemented |  |  |  | Interim Release 1 |  | BP010A step 10 flow name change to DB02, BP010B step250,step440, Step560 flow name change to DB02, and update BPD descriptions to DB02. | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010 | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-152 |  | DI-117 | 2023-02-14 | St Clements | 2912 | Madison Layton | Software Provider |  | On looking more closely at the validation rules for IF-019 spotted a few issues. IF-019 REG-1061 rule for Related Create event code appears to be written incorrectly. The rule and rejection description don't quite align. Rule: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) are not currently part of an import/export relationship Rejection reason: REG1061 - Prosposed MPAN(s) [DI-073] / [DI-074] are already part of a Related MPAN Relationship Should the rule read: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) is currently part of a related primary/secondary relationship? The rule and descriptions also don't appear to fully align for some in import/export section too - REG1052, REG1055, REG1057 and might need some minor tweaks to correct. |  | Implemented |  |  |  | Interim Release 1 |  | REG1061, 1052 and 1055 rules updated. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-153 |  | DI-118 | 2023-02-14 | St Clements | 2913 | Madison Layton | Software Provider |  | On working on detailed design for Related MPANs, noticed the IF-019 interface is missing a rule that the Secondary MPAN must not be a Primary in another Relationship. You could expand REG1064 to include this as the description sounds like it should have been covered here. Rule: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN Description: REG1064 - Proposed Secondary MPAN [DI-074] is already part of a different MPAN Relationship Could amend rule to: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN OR [DI-074] is already in a relationship as a Primary MPAN |  | Implemented |  |  |  | Interim Release 1 |  | REG1064 validation rule updated | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-154 |  | DI-119 | 2023-02-15 | St Clements | 2919 | Madison Layton | Software Provider | IF-019 validation gap on primary and subsidiary MPAN | On further detailed design we’ve spotted a potential design gap. Currently it is possible to enter a state where an MPAN is both a primary and subsidiary MPAN at the same time (e.g. Primary but also export linked or Secondary but also import linked). The current MHHS doesn't accommodate an MPAN being in both states at the same time. We’ve already looked to add rules to try to mitigate this on DB02/DB05 internal flows but would need additional rules on IF-019 to fully prevent this scenario occurring. Rules we think are required: 1. On receipt of IF-019 with event code RelatedCreate or RelatedAdd, the primary MPAN must not have energy direction of Export 2. On receipt of a IF-019 with event code RelatedCreate or RelatedAdd, any listed secondary MPAN must not in an active Import/Export relationship as the Import MPAN 3. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Import MPAN must not be in an active relationship as the secondary MPAN 4. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Export MPAN must not be in an active relationship as the primary MPAN |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Agreed with SCS that changes to IF-19 tab would be made to support Rules 1 and 4. Validation Rules updated accordingly with new Error codes (REG1067/1068) created to support. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-07-14
MHHS-DIN-155 |  | DI-120 | 2023-02-15 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. |  | Closed | [5 empty] | see also DIN-172/173. Included in 5.1 DUPLICATE See DIN-172 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-156 |  | DI-121 | 2023-02-24 | St Clements | 3078 | Madison Layton | Software Provider |  | We have logged a new design issue under DI-121. IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP |  | Closed | [5 empty] | Duplicate of DIN-173 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-157 |  | DI-122 | 2023-02-27 | St Clements | 3090 | Madison Layton | Software Provider |  | New design issue (SCC Ref DI-122) for the IF-005 related to REC CP R0032. The current v5.0 validation in the IF-005 does not include the new validation introduced with REC CP R0032 (R0032 is approved and being implemented in the D0312 this June): NEW REC CP R0032 Validation: V Rejected – ESME ID already exists within MRPS and does not match Removed Meter, Associated Import/Export MSID or Related MPAN W Rejected - MSN relates to a Smart Meter Type and the ESME ID is NULL X Rejected – ESME ID Format is Invalid Y Rejected – Number of Displayed Register Digits is NULL and the MSN relates to a Smart Meter Type Z Rejected – Non-Smart Meter Type with Number of Displayed Register Digits populated AA Rejected – Meter Location is invalid AB Rejected – Non-Smart Meter Type with ESME ID populated AC Rejected – Number of Displayed Register Digits is incorrect IF-005 Validation: V not covered, needs to be added as a Level 5 Validation Rule W is already covered by DI-085 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) X is already covered in DI-085 population notes (Level 4 validation RCP1023 Msg Contains Invalid Valid Value Combination(s)) Y is already covered in DI-091 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) Z is not explicitly covered, suggestion: add to DI-091 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AA is covered in the population notes AB is not explicitly covered, suggestion: add to DI-085 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AC not covered, Suggestion: add the following population note from R0032 to DI-091: Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” Summary Please add the following Changes to the IF-005 to align it with the D0312 validation and maintain the same level of Smart Meter data quality in the Registration Service: New Level 5 Validation rule for DI-085 implementing V from the D0312. ESME ID must be unique within MPRS unless it’s a Linked MPAN where the same Smart Meter can be shared across Linked MPANs New population note for DI-091, only to be included for Smart Meter Types New population note for DI-085 , only to be included for Smart Meter Types New population note for DI-091, Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” |  | Implemented |  |  |  | Interim Release 1 |  | New Validation Rules added to IF doc to ensure full coverage and alignment with CP Error codes described | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-158 |  |  | 2023-02-27 | Elexon | 2908 | Derek Weaving | Central Body | Use of CCCs to categorise the data for future charges | As part of the Performance Assurance Working Group discussions on Supplier Charges, we are exploring the use of CCCs to categorise the data for future charges. It is noted that Settlement Period Quality Indicator referenced in the VAS Method statement is for illustrative purposes and would welcome clarity on the following: · What is the intended process to populate the Settlement Period Quality Indicator in the initial ISD Table? · What would be the process to be involved in those activities to determine the categorisations should additional CCCs be required? |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | This DIN has been moved to Interim Release 5 as it is related to DIN-409 which has an objection raised that is pending a discussion to clarify the solution. Name change and field length have been actioned. Reviewing whether any changes to Settlement reports are required Recommending a change to this ISD Data Item: Settlement Period Quality Indicator to be set as per Appendix 1 of MHHSP_METH007 MDS_Method_Statement v5.0 This data item need to be changed to something like ‘Valid Settlement Period Quality Indicator Set’ and the field size needs to be increased. The data catalogue will need the revised data item and the field length will need increasing from 20 to at least 100. This Item also appears in some interfaces that will need to be updated. This is because it represents a set of SPQIs. The initial intention is to populate as per the table and check if any new SPQIs have been introduced in the baseline design Method Statement that are not covered. If new CCCs are introduced the appropriate flags for each new CCC would need to be agreed. However, it is likely that another dimension to the table below would need to be introduced to facilitate new CCCs. Word 'Illustrative' to be removed and will be updated to say Valid Settlement Quality Indicator Set. Change to be made across all impacted Method Statements. New CCC's will require a Modification to the BSC interface requirement. Proposed changes have been reverted to the initial state. Data item Settlement Period Quality Indicator, with a field length of 5. This is due to the agreed solution for DIN409 following DRG where it was agreed the list element would be removed in favour of individual row(s). The word 'Illustrative' will also remain within the Method Statements. | Missing/incorrect validation rule | Meter to Bank | Volume Allocation Service | MHHSP-METH006_VAS_Method_Statement MHHSP-METH007_MDS_Method_Statement v5.1 EDI021 ISD Entity spec | MHHSP-METH006_VAS_Method_Statement MHHSP-METH007_MDS_Method_Statement v5.1 EDI021 ISD Entity spec |  |  |  | 2023-07-14
MHHS-DIN-159 |  |  | 2023-03-01 | ENWL | 2994 | Paul Band | Network Business | Interfaces for UMSO | DES-138 Interface Inconsistencies vs BSCP7XX for UMSO Discussions with ENWL have highlighted a number of inconsistencies in the Interface Catalogue when it comes to routing for UMSO's. DIN-106 also refers. UMSO is not listed as a recipient in DES-138 for the PUB-008, but this is in the draft BSCP and should be added to the PUB UMSO is not listed as a recipient in DES-138 for the PUB-020, but this is in the draft BSCP - this is not needed in the BSCP as there are no unmetered Related MPANs UMSO is not listed as a recipient in DES-138 for the PUB-035, but this is in the draft BSCP - view that it is unlikely for this flow ever to be used as the appointment will not trigger any processes to need a subsequent update UMSO Is listed as UMSI, not UMSO in PUB-036 in DES-138 UMSO is listed as UMSC, not UMSO in PUB-018 in DES-138 The IF_LIST tab should be reviewed for consistency |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | As with DIN-106, there are inconsistencies in the Interface Catalogue for UMSO routing. This has been compounded by a review of the draft BSCP for UMSO, which has added a number of PUB flows going to UMSO that aren't currently in the catalogue. Covered by updated secondary routing rules (see DIN268) Design to check requirements in BSCP and MHHS BPs and ensure the interface catalogue reflects a consistent approach | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue and possibly related business processes and descriptions E2E001 | MHHSP-DES138-Interface Catalogue and possibly related business processes and descriptions E2E001 |  |  |  | 2023-06-16
MHHS-DIN-160 |  |  | 2023-03-14 | Ovo Energy | 2862 | David Morley | Supplier | BP009 flow addition | Steps 205 and 210 in BP009 wont be completable in the event that theres no comms. I think the process would be workable if there was an exception route here - see red arrow below. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update Steps 205 and 210 in BP009 with "Comms Available" line label add flow from step 205 to step 215 with “Not Commissioned / No Comms” line label | Process Model correction | Metering Changes | Change of Metering | MHHS-BP009 | MHHS-BP009 |  |  |  | 2023-06-16
MHHS-DIN-161 |  |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 requirement correction | MHHS-METH001-5.4c Please confirm the requirement: “where daily advance records are available [either in the past or future] and less than 90 days months different from the UTC Date requiring a daily advance - use the mean actual Meter advance from the closest [4] weeks for the same Day Type (as defined in ISD).” |  | Closed | [5 empty] | Duplicate of DIN 97. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-162 |  |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 typo | MHHS-METH001-5.5 typo “Where DAEs are required to be calculated the SDS shall use the most recent data a based on the event that triggered the estimation.” |  | Closed | [5 empty] | Duplicate of DIN 98. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  | 2023-06-16
MHHS-DIN-163 |  | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Conditionality Rule for B037 | It is not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure it is unclear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated conditionality rule for Block B037 in IF-001, IF-002, IF-033, IF-036: to show that Either DI-075 (Primary MPAN) or DI-079 (Secondary), and not both, should be populated where MPAN (DI-063 above) is part of a group of Related MPAN. |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-164 |  | DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0093 comment raised on 12/01/2023 "" D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692"" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: ""It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period"" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42" |  | Closed | [5 empty] | "This requirement stands - review with SCS in light of SEG scenario. We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error...". Reviewed with SCS and agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue MHHSP-DES229-IF005_UseCaseguide | MHHSP-DES138-Interface Catalogue MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-165 |  | DI-122 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | See separate sheet Duplicate of DIN-157 |  | Closed | [5 empty] | CR required to add rules in line with CP R0032 Added Miscellaneous Data Validation to IF-005 to cover REC CP R0032 validation rules Wrapped up into design teams main CR Doesn't need to be raised by SCS | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-166 |  | DI-77 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54" |  | Implemented |  |  |  | Interim Release 1 |  | Added clarification to REG Notes re Consent and Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-167 |  | DI-78 DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? " |  | Closed | [5 empty] | Agree you can't. Could update 1032 rule for USP? Duplicate see DI-29 | No Change
MHHS-DIN-168 |  | DI-92 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 ""DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least ""Registered"", if no DS is appointed then there is already an appropriate Event Code"" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone |  | Closed | [5 empty] | CR for new functionality. "Already covered by no MS/DS appointed - MPRS would try to align MS/DS with principle and couldn't as there's no registration to align this to. Need an extra check that can only autoappoint if there's a registration to prevent MPRS crashing Maybe one for DRG? Jon at RECCO for consequential change? Agree not to build for this scenario as this would be an edge case and close | No Change
MHHS-DIN-169 |  | DI-109 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to:Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. |  | Implemented |  |  |  | Interim Release 1 |  | Simplified MHHS-BR-RS-131 on when to lapse a SEG appointment | Requirement correction | MPAN Ownership |  | MHHSP- BRS003, MHHS-BR-RS-131 | MHHSP- BRS003, MHHS-BR-RS-131
MHHS-DIN-170 |  | DI-110 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. |  | Closed | [5 empty] | Duplicate of DIN-145 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-171 |  | DI-113 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { ""confirmingMpid"": ""string"", --* ""registrationId"": ""string"" --*, ""updateSucceeded"": boolean --* } Suggest that DI-0980 is removed from B066" |  | Closed | [5 empty] | Agreed with SCS being retained but due to optionality may have to populate text e.g. contact DSP. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-172 |  | DI-120 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. |  | Implemented |  |  | 2023-04-27 | Interim Release 1 |  | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-173 |  | DI-121 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP |  | Implemented |  |  | 2023-04-27 | Interim Release 1 |  | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-174 |  | DI-72 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a Submitted MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60" |  | Implemented |  |  |  | Interim Release 1 |  | "Agreed- doc updates MDR can have gaps between DS EFD and MDR EFD" Updated REG1083 validation in IF-034 so that it allows MDR Effective from dates >= SSD/ DS Eff From date/Existing MDR Eff from date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-175 |  | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" |  | Closed | [5 empty] | Duplicate entry | No Change | MPAN Ownership
MHHS-DIN-176 |  | DI-103 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-034 new rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD" |  | Implemented |  |  |  | Interim Release 1 |  | Agreed -doc updates Updated REG1082 to apply for both [SDS-MDRUpdate] and [DSAppSPRepsonse] events in IF-034 | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-177 |  | DI-105 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 " |  | Closed | [5 empty] | "Reason for IF-035 is to trigger when SDScan send the Meter info" & The IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR Agreed with SCS no changes are required, they now understand the context agreed to CLOSE | No Change | MPAN Ownership |  | MHHSP-BP003A | MHHSP-BP003A
MHHS-DIN-178 |  | DI-106 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | MS missing a requirement to send MS updates to CSS | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 |  | Closed | [5 empty] | Closed as discussed with SCS that this is out of scope for MHHS Programme. | No Change | [7 empty] | 2023-07-14
MHHS-DIN-179 |  | DI-111 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. |  | Closed | [5 empty] | Duplicate of DIN-146 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-180 |  | DI-125 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 the Meter Removal is currently not permitted for a prospective MS Is it possible for the MS to need to remove two meters and replace it with one? In which case meterexchange would only allow them to do part of this process (remove 1 and add 1) but not complete it, so SEG could not complete. Should meter removals therefore be allowed for prospective MS? (REG1019) |  | Implemented |  |  |  | Interim Release 1 |  | Revised REG1019 and added REG1027 for MeterRemoval event in IF-005 | Requirement correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-181 |  | DI-126 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Missing Rule on If-005: MAP EFD must not be > removal date |  | Implemented |  |  |  | Interim Release 1 |  | Added new rule for MeterUpdate and MeterHistoryUpdate events so that MAP EFD must not be > removal date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-182 |  | DI-127 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 On exchange - the MAP and IHD groups are for new installation not removed meter - does this need to be clarified? |  | Implemented |  |  |  | Interim Release 1 |  | New note added to IF-005 to clarify that only the newly installed MAP and IHD information is required on MeterExchange | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-183 |  | DI-128 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-005, IHD EFD missing validation in IF-005 (Between install and removal date) |  | Implemented |  |  |  | Interim Release 1 |  | Covered Release 5.1, IF-005, IHD EFD missing validation added | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-184 |  | DI-129 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-005 incorrect validation rule: REG1010: On event code Meter exchange and Meter Install rule states MAP EFD >= Install date, it should be = not >=" |  | Implemented |  |  |  | Interim Release 1 |  | IF-005: Updated to REG1010 (MAP Eff from date check ) to = install date for MeterInstall and MeterExchange | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-185 |  | DI-130 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | It should not be possible to change MDR EFD once set. Need validation rules to enable MPRS to reject if IF-034 is submitted with current MDR but a different EFD. |  | Implemented |  |  |  | Interim Release 1 |  | Agreed - doc updates Covered by L3/4 validation as per updated Validation rule notes | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-186 |  | DI-131 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031, there is currently not enough validation to ensure on a SEG, that the same SP isn't appointed for the current registration. Need additional validation rule: If scenario SEG and current supplier, then SP must not be current SP. |  | Implemented |  |  |  | Interim Release 1 |  | Agreed - doc updates Updated validation rule Added REG1095 in IF-031 to check different Data Service proposed for SEG appointment | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-187 |  | DI-132 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Supplier inability to appoint MS/DS for Principal and Subsidiary MPAN | Unhappy Path Scenario: Receive IF-031 for MPAN that is both Principal and Subsidiary MPAN at the same time. This will be rejected as per REG1038/REG1039 Supplier will be unable to appoint MS/DS for the MPAN or any related/linked subsidiary MPANS. |  | Closed | [5 empty] | Closed, there is an existing to prevent this scenario happening going forward. Agreed with SCS to raise examples in the Data Cleanse Forum. | No Change | [7 empty] | 2023-07-14
MHHS-DIN-188 |  | DI-133 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031 the rule REG1030 reads [DI0-828] in not a valid UMSO in DNO [DI-108]/[DI-109] This should read LDSO not DNO |  | Implemented |  |  |  | Interim Release 1 |  | Tied up with If-005 rejection description flexibility action Change REG1030 to read: REG1030 - [DI0-828] in not a valid UMSO in LDSO[DI-108]/[DI-109] SC change incorporated into 5.1.1 | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-189 |  | DI-134 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On IF-031, REG1036 is written to only apply to USP when it should apply to all scenarios? ""Proposed MDR Date [DI-836] >= [REG.MPAN_SUP_SSD] However don't think this rule is required at all as this is already covered under the REG1036 rule that MDR Date < DS EFD? Linked to DI-66" |  | Implemented |  |  |  | Interim Release 1 |  | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-190 |  | DI-135 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-034 missing validation rule REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational |  | Implemented |  |  |  | Interim Release 1 |  | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-191 |  | DI-136 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Addition of validation rules to MPRS to restrict Retrospective changes | MPRS does not currently prevent Retrospective changes to DUoS Tariff ID or Connection Type. Should MPRS add new validation rules for these items to restrict Retrospective changes? Please can you update DIN-191 to include Disconnection Date & Export Association. We don't currently have any restriction on how far these data items (and the others in DIN-191) can be back dated. This is a retrospective change through the DB interface and not a Manual Amendment. There are no retrospective periods for the following data items, this means the data items could be changed earlier than the settlement window and cause issues for settlement. There are restrictions that these data items must be within MS/Registration periods where appropriate, but the EFD/SSD could still be years into the past. - MDR EFD, - MS EFD, - DS EFD, - IHD Status EFD, - PC EFD, - SSC EFD, - Energisation Status EFD |  | Closed | Design gap | LDSO (SCS) |  |  |  | Covered in the retrospective changes discussion at DRG. | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-07-14
MHHS-DIN-192 |  | DI-137 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | For If-031, scenario SEG, the business process diagram/requirements only describe the appointment lapsing once reaching it's SSD if no SA is received. If we receive a cancellation we would like to lapse the appointment at that point in time (it cannot become secured active after being cancelled) and not wait until the SSD to do this. |  | Implemented |  |  |  | Interim Release 1 |  | Added new requirements to BRS003, MHHS-BR-RS-24.1 and 58.1 | Design Ambiguous | MPAN Ownership |  | MHHSP-BRS003-Registration Requirements | MHHSP-BRS003-Registration Requirements
MHHS-DIN-193 |  | DI-138 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | The YAML name for metered indicator (Data Item 127) is meteredUnmeteredIndicator. This is then set to true of false. It isn't clear whether true means it's metered or unmetered due to the naming convention. It should be named meteredIndicator instead to make it clear true means metered, false unmetered. |  | Implemented |  |  |  | Interim Release 1 |  | Updated YAML details in the Data Catalogue for DI-127 Metered Indicator. Updated YAML accordingly Updated data catalogue/ YAML | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-194 |  | DI-1 | 2023-03-15 | St Clements | 4475 | Madison Layton | Software Provider |  | For IF-035 what is Event Code [IMS-SendMTD] intended for? If intended for sending to old MS then this should be done via secondary routing on the original IF-035, not via another separate IF-035 message produced by MPRS with different event code. |  | Closed | [5 empty] | This message is effectively a copy of the DSAppAccepted AND/OR MSAppAccepted but sent to the Incumbent (current) Metering Service to act as a trigger for that MS to send MTDs. This should be created by MPRS. Requirements MHHS-BR-RS-053 and MHHS-BR-RS-019 cover Registration Service sending this. Message to check and close | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-195 |  | DI-76 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Originally raised as T4-COM-1691 on 15th Sept 2022: ""MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days "" Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5" |  | Implemented |  |  |  | Interim Release 1 |  | Agreed doc update Also in Reg Notes tab Updated validation rules and Reg notes Updated REG1037 in IF-031 to 2 workings days and updated REG notes, to align with process and requirements | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-196 |  |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Updates are required to clarify nullable fields |  | Implemented |  |  |  | Interim Release 1 |  | Updates to Interface catalogue includes changes to interfaces and block data items which are present and can be null 1. MHHSP - ERI011A - ECS Reports - Internal v5.1: The data catalogue is the only tab that has been updated 2. MHHSP - ERI011B - ECS Reports - External v5.1: The data catalogue, DIP_Common, MHHS-REP-003 and MHHSP-REP-006 have been updated |  | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue, MHHSP-E2E001 End-to-End Solution Architecture MHHSP - ERI011A - ECS Reports - Internal MHHSP - ERI011B - ECS Reports - External | MHHS-DES138-Interface Catalogue, MHHSP-E2E001 End-to-End Solution Architecture MHHSP - ERI011A - ECS Reports - Internal MHHSP - ERI011B - ECS Reports - External
MHHS-DIN-197 |  |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Decision taken to document digital signing of interfaces outside of the interface document. |  | Implemented |  |  |  | Interim Release 1 |  | Remove Z0 and ZI blocks from all interfaces. Signing process will be documented in the Code of Connection document. | Technical corrrection | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue Code of Connection | MHHS-DES138-Interface Catalogue Code of Connection
MHHS-DIN-198 |  |  | 2023-03-15 | Large Suppliers |  | Haz Elmamon | Large Suppliers | Complex Meter Site | Clarification on complex meter site, passed down from DAG as part of the work off plan, Haz to gather concerns for discussion at DA. LSC Rep provided information to the issue on 22-Mar-23 |  | Closed | Further information required | Large suppliers | [5 empty] | MPAN Ownership | [6 empty] | 2023-07-14
MHHS-DIN-199 |  |  | 2023-03-23 | BGAS | 3460 | Neil Strange | large Suppliers |  | Participant wishes to see the use of standardisation in the interfactions between the SDS and sub roles MDR PSS |  | Closed | [5 empty] | Closed based on recommendation for programme CR to be raised by the Large Supplier Rep | No Change | Supporting Docs | SDS Validation / Extimation | MHHS-DES138-Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-200 |  |  | 2023-03-24 | CGI | 3489 | Chris Beard | Software Provider | Hierarchy definition for selecting correct register reading in the case of multiple readings for the same settlement period | If there are multiple register readings available for the same Settlement Day, where is the hierarchy defined for selecting which should be used? Is this solely based on Reading Method (i.e. 1. A – Actual, 2. C – Customer, 3. E – Estimated by SDS, 4. S – Estimated by Supplier) or is it dependent on other factors such as the Event Code in the IF-041 ([ReadingRemv], [ReadingInstl], [ReadingEnergisationChg], [ReadingCOR], [ReadingOnSite], [ReadingCOS], [DSEstimate], [SupplierAgreedCOS], [ReadingOverride], [ReadingRemote])? |  | Closed | [5 empty] | Reading methods do not apply to Register Readings - recommendation for DIN to be closed. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  | 2023-07-14
MHHS-DIN-201 |  |  | 2023-03-24 | ESG | 3529 | Patricia Parker | Software Provider |  | IF-033 Validation for population into the IF-034 The receiving party business validation rules state “Each Service Provider will need to determine their own validation criteria when processing Appointment Requests. The list below is intended to cover a number of potential possibilities based on the data items made available, and not to suggest that Service Providers needs or should perform such validations.” But should the DI-143 ‘Service Provider Proposed Appointment Response Code’ not form a valid set list (ENUM Vals) in the Data Catalogue so that all parties are working to the same list of applicable codes, rather than this field being a string with a length of 200 field? |  | Closed | [5 empty] | IF-033 has been updated as part of Interim Release 1 and the ENUM Vals will not be updated this is because we will have dynamic error messages which cannot be enumerated. |  | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-202 |  |  | 2023-03-24 | ESG | 3513 | Patricia Parker | Software Provider | Operational Choreography 60 minute turnaround | Registration Responses in connection with the PUB-31 given the NFS requirement is a 60-minute turn-around time. Within the Operational Choreography there is requirements OPC-140: From our understanding this means that when suppliers receive the PUB_032 from the Reg Service rejecting the appointment Request suppliers then have 60 minutes to re-issue a fresh IF_031 appointment. For example, there is a rejection code for 'CSS Reg ID not known', this would suggest that a party is out of sync and would need investigating especially as in this case, the REG ID would have previously been provided on PUB- 002, DI-849 and CSS is the master of the REG ID and not the Registration Service. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Added suggested text to Ops Choreography. Suggested text is "It is noted that some requests may require manual work and may be as a result of incorrect appointments from the Supplier. The expectation will be 90% of requests are systemically processed within 60 minutes with the residual being processed by the end of the following working day". | Doc Ref correction | Supporting Docs | Operational Choreography | MHHS_OPC001_Operational_Choreography | MHHS_OPC001_Operational_Choreography |  |  |  | 2023-06-16
MHHS-DIN-203 |  |  | 2023-03-24 | CGI | 3502 | Chris Beard | Software Provider | mapping of Estimation Reason Codes to estimation Methods | MHHSP-METH001 M-13. Can you provide a definitive mapping of Estimation Reason Codes to estimation Methods? For example, LTV to Method 11. When should an SDS use Estimation Codes such as Opt Out, Comms. Fault. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated METH001 section 7.3 to reflect Estimated Methods to Estimated reason codes | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001 | MHHSP-METH001 |  |  |  | 2023-06-16
MHHS-DIN-204 |  |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | De-energised sites | MHHSP-METH001 M-3. Which estimation Method should an SDS use for de-energised MPANs that would result in an estimation code of ‘De-Energised’? Without a specific Method statement to cover de-energisation, we will end up estimating consumption. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Added Method 13 to reflect de-energised sites within METH001 and updated section 2.29 on METH002. | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001 | MHHSP-METH001 |  |  |  | 2023-06-16
MHHS-DIN-205 |  |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | Removal of Estimation Reason Code "Disconnected" | Can you confirm that the Estimation Reason Code ‘Disconnected’ will be removed from the table in 7.3? |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Removed "Disconnected" from Table 7.3 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement | MHHS-METH001 - SDS Validation and Estimation Method Statement |  |  |  | 2023-06-16
MHHS-DIN-206 |  |  | 2023-03-27 | St Clements | 3703 | Anna Davis | Software Provider |  | Within the MHHS-E2E001 - End-to-End Solution Architecture, there is reference to MHHS-E2E003-Physical Interface Specifications in 1.3 References section This should be labelled as MHHSP-DES138-Interface Catalogue |  | Implemented |  |  |  | Interim Release 1 |  | Updated 1.3 reference section | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-207 |  | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Clarity on when agent appointments should become effective | There is ambiguity within the design on when agent appointments should become effective, which means that different participants have a different view on when agent appointments should become active. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | At the DRG held on 4th August it was agreed that Appointments need to become active in UTC. Further workgroup discussions are being held to review impacts. References to local time removed pending agreement at Working Group/ DAG. Old solution: Appointments become active at midnight local time. Participants raised objections against the old solution therefore this DIN went to a DRG on 4th Aug for discussion. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-07-14
MHHS-DIN-208 |  | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Registration Service rejection of Legacy messages for an MPAN | Within the existing Migration Design, it is stated that the Registration Service should reject all Legacy messages for a given MPAN once a Forward Migration has been initiated for said MPAN. This would prevent a legacy MOP from sending the relevant legacy flows if they need to change a meter when an MPAN is mid migration. |  | Closed | [5 empty] | Closed following internal review with Design, Migration and Code Team. Agreed that current design will stand in that all legacy messages will be rejected following the point the IF-031 is issued. Reaffirm existing guidance that migration should be timed to avoid any planned work. Unplanned work/change occuring during migration should be communicated using an MHHS IF Message once migration has been completed. | Requirement correction | Migration | Migration | Migration Design Migration Requirement | Migration Design Migration Requirement |  |  |  | 2023-07-14
MHHS-DIN-209 |  | Design Team | 2023-03-30 | Design Team |  | Sean Cooper | SRO Design Team |  | ~ Level 1/2 Error Code "MSG0000 - Success" Added to Interface Intro Section ~ MSG0018 - Timestamp cannot be future removed and explainatory note added to IF Notes Section of DIP Common |  | Implemented |  |  |  | Interim Release 1 |  | Updated actioned in v5.1.1 of IF Doc. This relates to MSG1008 not MSG0018 as originally given in the design issue. MSG0000 Success added. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-210 |  | Design Team | 2023-03-30 | RECCo |  | Sarah Jones | Consultancy |  | Possible change flagged The original view of the Design Team was that this flag and associated info (ie Is a Customer Direct contract in place, who is the DS/MS with that contract, but not the Eff To Date aka Contract End Date) should be visible to incoming Suppliers, for exactly the reasons you suggest i.e. so that in an incoming supplier could factor the existence of a CDC(s) into their acquisition process / pricing etc. I think we also felt that SP’s who weren’t currently appointed, but may have signed a new CDC should also have the ability to set the flag, as it’s the sites that are part of a CDC, but where that SP isn’t the appointed SP that are the most difficult to coral and manage. The position at the moment is that the existence of a CDC would be shared with incoming Suppliers as part of PUB-002, however this would likely be too late in the process to provide the assistance and support required to an incoming supplier (on all aspects of the sale, contract/price in particular) … … therefore, I think it was also envisioned that information about CDC’s would be available via ECS – so prospective suppliers could check in ECS on the CDC position as part of the other pre-acquisition checks they may undertake. Therefore, I think the decision on exactly what information is shared ‘pre-acquisition’ to participants probably sits with yourselves (RECCo) to finalise as part of your ECS Design / DP Assessment. All information in relation to CDC’s will be passed/made available to ECS via receipt of a copy of PUB-039, so what item(s) are displayed and to what parties I think would get covered off as part of that ECS Design activity. |  | Closed | [5 empty] | Closed, as per discussions with RECCo that no design changes are required. | No Change | [7 empty] | 2023-06-16
MHHS-DIN-211 |  | DI-139 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-009 Event Code is referred to as [CSSDeRegistration] in the population notes and swagger open API spec but then B042 block title references event code CSS Deactivation, B042 should reference CSSDeRegistration. |  | Implemented |  |  |  | Interim Release 1 |  | Update B042 to reference CSSDeRegistration | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-212 |  | DI-140 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | MHHSP-BP007-Disconnection-v5.0 is missing IF-050 being sent out on a change to MPAN/RMP Status |  | Implemented |  |  |  | Interim Release 1 |  | to BP007 and BPD007 Requires a flow from Registration Service to EES (IF-050 to DIP, a Publish Change to MPAN/RMP Status process, a PUB-050 from DIP to EES process Receive Change to MPAN/RMP status) starting at step 70 (disconnection). Plus add new step descriptions to the BPD and amend Step 70 description to include IF-050. | Process Model correction | Metering Changes |  | MHHSP-BP007-Disconnection, MHHSP-BPD007-Disconnection | MHHSP-BP007-Disconnection, MHHSP-BPD007-Disconnection
MHHS-DIN-213 |  | DI-141 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Data item 997 in S1 common block is senderId in swagger hub, but senderDIPID in data catalogue |  | Implemented |  |  |  | Interim Release 1 |  | Update swagger to reflect senderDIPID to align to data catalague | Technical corrrection | Technical Artefact | Swagger | JSON,YAML | JSON,YAML
MHHS-DIN-214 |  | DI-142 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | REG Notes section Queuing of Prospective Appointments Rule 4 ** Rule 4: If App Scenario = 'SEG' and Supplier ID + Appointment Service Start Date = Existing Supplier ID + Service Start Date > (Service Start Date +2 working days) >> Appointments meeting Rule 4 have missed their opportunity, and will be 'Lapsed' (PUB-035) This rule doesn't make logical sense, needs correcting. What is the intended logic to be applied here? |  | Implemented |  |  |  | Interim Release 1 |  | Update to align with validation rule | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-215 |  | DI-143 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 for event code [MeterRemoval] rule REG1002 Sending Metering Service ID [SO.SenderID] is currently appointed OR held a valid appointment for Meter Installation Date [DI-057] This should read removal date not installation date |  | Implemented |  |  |  | Interim Release 1 |  | Updated validation rule REG1002 in IF-005 for event code [MeterRemoval] to refer to Meter Removal Date (DI-058) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-216 |  | DI-144 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-144 On IF-005 MPRS will validate Either current, queued SEG or previous MS If previous and not within 10 working days will reject with REG1003 If not previous, and not current or queued, will reject with REG1027 MPRS will then validate if install date/removal date is within MS period of ownership If not will reject with REG1019 REG1019 need correcting to also include <ETD to apply for previous MS It’s not possible to get a scenario where the If-005 passes the above rules (REG1003, REG1027 AND REG1019) but fails REG1002. Therefore REG1002 is not needed and will never be sent as a rejection code. (Add to DI-43) |  | Closed | [5 empty] | Agreed with SCS that no further change is required | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-217 |  | DI-145 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | On IF-005 REG1019 should also include validation that the installation/removal date concerned is <=Effective to date (ETD) of MS period of ownership |  | Implemented |  |  |  | Interim Release 1 |  | Updated IF-005 validation rule REG1019 to include validation that the removal/install date must be <=Effective to date (ETD) where the update is being provided by previous Metering Service (using their 10 day window) for MeterRemoval, MeterInstall and MeterExchange events. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-218 |  | DI-146 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 for event codes [MeterExchange] and [MeterRemoval], the rule should not reference DI-056 which is the meter ID in the installation block, it should should referenced DI-053 which is the meterId in the removal block |  | Implemented |  |  |  | Interim Release 1 |  | Rule updated not to reference DI-056 which is the meter ID in the installation block, it now references DI-053 which is the meterId in the removal block | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-219 |  | DI-147 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 - for other event codes removal date must be >= to Install date but for [MeterUpdate] the rule states > meter install date. Should be >= |  | Implemented |  |  |  | Interim Release 1 |  | Update rule for [MeterUpdate] to align to other removal date event codes | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-220 |  | DI-148 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1007 unecessary and will never be triggered, it is already covered under REG1001 cannot submit meter install if MPAN is disconnected |  | Closed | [5 empty] | Valid rule to left in as-is but noted cannot be SIT tested | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-221 |  | DI-149 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In the IF-005 guide it states: "When amending the Installation and/or Removal date of a Meter, a supporting MAP history commencing in line with the revised Installation Date must also be provided. Any additional MAPs should be provided in chronological order, each with a ‘MAP Effective From Date’ greater, by at least one day, than the previous." MPRS will accept if the install/removal date is changing AND the MAP History has not been included, there is no requirement in Interface Catalogue or Registration Requirements to reject if MAP history is not provided. |  | Closed | [5 empty] | Believe covered by MeterHistoryUpdate rules, but hopefully won't be an issue pending agreement on MAP discussion… IF-005 use case guide will be updated with outcome. DRG has agreed to remove MAP history therefore in lieu of this decision, this change will not be required. Closed | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-222 |  | DI-150 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | sarah |  | Implemented |  |  |  | Interim Release 1 |  | Updated wording to match existing validation. Guidance only now provided | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-223 |  | DI-151 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005: Need REG1006 to apply to all event codes, e.g. Meter Update on a change to removal date, will need to check that the removal date does not lead to non unique Meter IDs (overlapping dates) MPRS will reject with REG1006 in this scenario |  | Implemented |  |  |  | Interim Release 1 |  | Added REG1006 validation checks to MeterHistoryUpdate and MeterUpdate events. | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-224 |  | DI-152 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 Interface Note below could be read as MeterUpdate event code can be submitted by previous or prospective MS which is not correct "Only the Appointed Metering Service, and for a small window (10 days) to allow for delayed notification of field activities the previously appointed Metering Service; and an incoming Metering Service with a Prospective 'SEG' type appointment may send an IF-005 and update metering details. The [MeterHistoryUpdate] may only ever be used by the Appointed Metering Service. Interface Design assumes that two separate meters with the same 'Meter ID' cannot be installed at the same time. " |  | Implemented |  |  |  | Interim Release 1 |  | Updated | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-225 |  | DI-153 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | DI-849 CSS Registration Request Id does not have a YAML name in the interface catalogue In the swagger hub, the corresponding name is CSSSwitchID which is misspelt |  | Implemented |  |  |  | Interim Release 1 |  | Updated Data Catalogue to CSSRegistrationRequestID, Swagger to follow | Data interface correction |  | Interface Catalogue Swagger | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-226 |  | DI-154 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In MHHSP-BPD007 - Disconnection v5.0, the ordering of the steps are out of order. Steps 140, 145 and 150 are for parties receiving the de-appointment notification from the Registration Service, but this is not sent until Step 155. Step 155 “De-Appoint Services” needs to be before Step 140 “DS De-appointment Notification”. Also Step 145 “Receive De-Appointment Notification” is DIP receiving the de-appointment notification to send on, this needs to be after Step 155 and before Step 140 . The ordering should be: • De-appoint services (155) • Receive De-Appointment Notification (145) • DS De-Appointment Notification (140) • MS De-Appointment Notification (150) |  | Closed | [5 empty] | No plans to change step numbers as long as they are unique | No Change |  |  | BPD007 | BPD007
MHHS-DIN-227 |  | DI-155 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1.xlsb, the validation for REG1003 – “Metering Service ID [S0.SenderID] post appointment update period for MPAN [DI-063] has expired” is currently set to “Metering Service [S0.SenderID] holds valid previous appointment then [System Date] should be < [REG.App End Date] + 10 working days”. Should this be <= to allow for the full 10 days? |  | Implemented |  |  |  | Interim Release 1 |  | Changed to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-228 |  | DI-156 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 - IF-005 has the following error for [MeterExchange] & [MeterInstall]:- “REG1020 - MAP Effective Date [DI-054] cannot take place in the future” Should this validation also be valid for [MeterUpdate] and [MeterHistoryUpdate]? |  | Implemented |  |  |  | Interim Release 1 |  | Added to meter update for removal date. Added to MeterUpdate and MeterHistoryUpdate for MAP effective date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-229 |  | DI-157 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 does not have a rule that the SMSO EFD must not be prior to the latest SMSO EFD. We are implementing this rule with error code REG1019 |  | Implemented |  |  |  | Interim Release 1 |  | We are implementing this rule with error code REG1019 Make consistent with others ( PC and ssc + 1 ). Review IHD and SMSO | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-230 |  | DI-158 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 & IF-005 do not have a rejection code where the IHD is invalid. |  | Closed | [5 empty] | DIP will reject non-valid values - no change to docs required | No Change
MHHS-DIN-231 |  | DI-159 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-005 - There is no validation on Meter Removal date [DI-58]. This should be mandatory non nullable for [MeterRemoval],[MeterExchange],[MeterUpdate], but mandatory nullable for [MeterHistoryUpdate] to allow for reinstating a previously removed meter. Currently in redlined v5.1, this data item is optional and non nullable. |  | Implemented |  |  |  | Interim Release 1 |  | Meter Removal changed to nullable, block conditionality updated | Missing/incorrect validation rule | Metering Changes | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-232 |  | DI-160 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-160 on the interface catalogue DCC Service Flag validation rules are specified in IF-025, but DCC Service Flag is not received in this interface. Needs removing. |  | Implemented |  |  |  | Interim Release 1 |  | not needed rules removed. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-233 |  | DI-161 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 – IF-025, where the event type is [ConsentGranularity] Error Code - REG1019 - Consent EffectiveFrom Date [DI-018] must be within Suppliers period of ownership Test Condition - Consent Granularity EffectiveFromDate [DI-018} must be < [Reg.CurrentSupplierEndDate] if exists Should this be <= as it could be on the end date? |  | Implemented |  |  |  | Interim Release 1 |  | Updated to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-234 |  | DI-162 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Registration Services Requirement MHHS-BR-RS-021 should be amended to: Registration Service must, where more than one Metering Service appointment request is received from the same Supplier for the same MPAN CSS Registration Request ID, and for the same date, take the last received Metering Service appointment (based on the Sender timestamp) as containing the correct information. Any earlier appointments should be lapsed. To allow multiple queued service appointments for the same registration will be overly complex to design, code and test, and is likely to cause confusion and issues in live operation. It is much simpler and cleaner to only allow one queued service appointment at a time, per registration. This would still allow the Supplier to replace a queued appointment that's incorrect. The Supplier could submit further changes once the first change has completed, if there is a genuine case of multiple changes to SP in a short period of time. It would not impact on CoS. Our proposal is to allow one pending queued appointment per registration, so could have a queued appoint on current registration AND queued appointment on CoS registration at the same time. |  | Implemented |  |  |  | Interim Release 1 |  | Updated MHHS-BR-RS-021 to refer to CSS Registration Request ID. Added REG1089 - Subsequent appointment received as an error code in the interface spec | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-235 |  | DI-63 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Original wording:- In the business process diagram for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 Update required:- Please close this design issue as CSS0700 is the correct reference for update of status. |  | Closed | [5 empty] | DUPLICATE OF MHHS-DIN-63 | No Change
MHHS-DIN-236 |  | DI-163 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, 02-DIP-COMMON - R0 response - DI-980 Response Message has been updated in Swaggerhub to be an array, but this is not clarified in Interface Spec. DI-979 Response Code should not be an array. |  | Implemented |  |  |  | Interim Release 1 |  | Added note in Introduction section to confirm that DI-980 can be an array Agreed DI-979 Response Code is not an array | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-237 |  | DI-164 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-034 S0 DI-999 Event Code option of [DSAppSPRepsonse] is misspelt. This is also misspelt in Swaggerhub. This could cause differences between systems and should be corrected to [DSAppSPResponse] |  | Implemented |  |  |  | Interim Release 1 |  | Updated typo in IF-034 DI-999. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-238 |  | DI-165 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation on MS/DS EFD being within permitted advanced period. This is covered under migration document but not implemented as a validation rule for IF-031. MHHS-DEL961 Migration Design Document section 6.1.1: For the purposes of the CoA Migration process, the below business rules should be followed by Suppliers regarding the lead time between the submission date of the IF-031 and the requested effective from date of the Migration. a. An effective from date from Same Day +1 up to a maximum of 28 calendar days (inclusive of the 28th day) in the future is permissible. |  | Implemented |  |  |  | Interim Release 1 |  | 28 Day in advance rule added to if-031 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-239 |  | DI-166 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Requirement MHHS-BR-RS-134 states MPRS must automatically de-appoint the MS & DS when the Market Segment Indicator changes to NO. Is this the intended design? |  | Implemented |  |  |  | Interim Release 1 |  | Removed reference to Market Segment Indicator from the requirement MHHS-BR-RS-134. | Requirement correction | MPAN Ownership | Market Segment | MHHSP-BRS003-Registration Service requirements | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-240 |  | DI-167 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Current validation on IF-031 Rule REG1037 will mean MPRS will lapse any appointment where the system date is greater than appointment EFD + 2 working days. This means if a SEG change fails, and the supplier tries to resubmit the SEG change, with EFD more than 2 working days in the past, MPRS will immediately lapse the appointment. If there is a need to allow retrospective SEG changes, more than 2 working days after EFD, then the wording will need to be amended to apply to max(EFD+2 working days, MPRS system date on receipt of IF-034 + 2 working days) |  | Implemented |  |  |  | Interim Release 1 |  | Introduction of Lapsed Response Codes and Rules in IF-035 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-241 | RS |  | 2023-02-01 | C&C | 3430 | Graham King | Software Provider | Routing rules via the PUB-018 | IF/PUB-018 message with event codes [AddressChg] and [DUOSTariffIDChg]. According to Interface Catalogue routing rules, these events are not communicated to the LDSO role via the PUB-018. We assume that the assumption here is that because these data items are mastered by the LDSO that all internal LDSO systems share this data. This is unlikely to be the case. DUoS billing systems co-exist alongside other LDSO management software and are often supplied by different vendors. They do not and cannot share data sets. Given this real-world separation, would it be possible to make the PUB-018 message available to LDSO in the list of Secondary Routing paths? The alternative would mean developing communication channels between disparate systems, from potentially different software vendors in order to pass information from one to the other. |  | Closed | [5 empty] | Closed - Linked to expected LDSO CR26 on DIP Message Optionality - Update as part of wider CR review | No Change | [7 empty] | 2023-07-14
MHHS-DIN-242 |  |  | 2023-04-04 | ESG | 3713 | Patricia Parker | Software Provider |  | How will the Metering Service be kept informed of who the currently appointed Data Service are? On BP003 is shows the Metering Service being a recipient of the PUB_036 when a DS appointment becomes effective, however looking at the routing rules in DES138 it does not show ‘MSSC’ or ‘MSAC’ as being recipients? |  | Closed | [5 empty] | Close - changes to Secondary routing make this DIN Moot - Ref DIN-268 | No Change |  |  | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-243 |  |  | 2023-04-05 | Change Request | N/A | Sean Cooper | Programme | CR-015 E7/E10 Off Peak Consumption Solution | CR015 - Differential Settlement for E7 / E10 Meters for Smart Opt-out customers | CR015 | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Changes as agreed at DRG and slides circulated. Updated Method 2 and Method 7 within the SDS method statement (METH001). BR-DS-168 & BR-DS-169 added to BRS001. BR-SU-163, BR-SU-164 & BR-SU165 added to BRS004. BP004 text box amended. Creation of x2 New Data Catalogue Items​ OPD Day​ & OPD Proportion​. Changes to IF-024​ Addition of new Event Code [SN-OffPeakDec]​ & Addition of new B-Block BXXX Off-Peak Declaration​ | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue METH001 BRS001 BRS004 BP004 | MHHSP-DES138-Interface Catalogue METH001 BRS001 BRS004 BP004 |  |  | CR15 | 2023-06-16
MHHS-DIN-244 |  |  | 2023-04-04 | British Gas | 3874 | Neil Strange | Supplier |  | D0275: Until v0.3 of DES196 was released our understanding was that the D0275 would be retained and it’ use was optional. We are feeding this back on the D-025 consultation but don’t want to lose sight of this. Its removal will impact our billing systems and substantially drive up implementation costs. The baselined IF-021 also does not handle the clock change |  | Closed | [5 empty] | Alignment with D0275 D0275 is not part of of the baseline design requirements. If you require this, it is by mutual agreement between parties. NO change required, only clarification. | No Change
MHHS-DIN-245 |  |  | 2023-04-01 | Avanade/ Design Team |  | Grant Sutcliffe | Software Provider | Transaction ID and Correlation ID increase field length to 60 | Transaction Id Could the length specification of the TransactionId be increased to be a max length of 60. The need for this is to cater for a 16 character length hex value (increasing from current length of 6 characters]. This would ensure that we achieve uniqueness. It will also provide headroom for any length increase in other Transaction Id constituents, such as Role. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: T-041-1234567890123-SUP-20230220-619C1F6967838002 [Length = 50] Example from DES138 spreadsheet: T-006-1234567890123-SUP-20220401-1234CC [Length = 40] Correlation Id Could CorrelationId length also be increased to 60 max length of 60 - for the same reason. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: CI-BP-011-20230222-619E0BD1D1FD9000 [Length = 35] Example from DES138 spreadsheet: CI-BP-011-20230222-1234567890123 [Length = 32] |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated DIP Transaction ID and DIP Correlation ID to String 60 in Interim Release 1. The examples have been updated to reflected MHHSP-DES138-Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-246 |  |  | 2023-04-12 | Change Request |  |  | DCUSA | CR-019 Replacement of D0242 D0315 for MHHS | CR019 - Replacement of D0242 D0315 for MHHS | CR019 | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors) and receivers (suppliers) of the flows has identified the desired flow content and now wish to bring this back to the program to ensure that it can be delivered in readiness for migration. REP-900 and REP-901 added to reporting catalogue. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the supercustomer data from settlement (REP-002/002A). There will be removal of certain data items used in the current process and addition of new data items, making population of the D0242 ‘Supercustomer DUoS Daily Statement’/D0315 ‘Embedded Network Supercustomer DUoS Daily Statement’ impossible in their current format for migrated customers. The “MHHS Design: Reporting and Transition Sub Group” identified the need for a new DIP flow to replace the D0242/D0315 last summer but noted that these flows are under DCUSA ownership and so passed the development of the flow content to DCUSA. More information including the proposed Interface can be found on the collaboration base under CR019 This also addresses CR27/DIN511 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-ERI011B External Reports | MHHSP-ERI011B External Reports |  |  |  | 2023-07-14
MHHS-DIN-247 |  | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Update to the Core Design Interface Catalogue (MHHSP-DES138) is required to include the addition of IF-003 |  | Closed | [5 empty] | Closed captured under DIN-434 as part of migration update review IF-003 defined as part of Migration baseline The structure of the IF-003 will be updated to include ‘Incoming Supplier Details.’ The two new data items within the ‘Incoming Supplier Details’ will be: RevMig Incoming Supplier MPID RevMig Incoming Supplier Effective From Date Business Rules: In the case of Smart Meters undergoing Reverse Migration only, the Registration Service will populate the ‘Incoming Supplier Details’ as part of the IF-003 which is sent to the outgoing MS (via the DIP). This is so the outgoing MS can correctly route the Skeleton D0150 to the new Supplier (which in turn enables the new Supplier to generate a D0367). If the D0205 is not sent to the Registration Service before the IF-003 is issued, the data fields used to confirm the identity of the DC and MOP will be blank; no default values will be populated. In this case, the DC and MOP will need to contact the Supplier to initiate a manual transfer of data. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-07-14
MHHS-DIN-248 |  | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Updates to the ISD Entities document (EDI021, v5.0) |  | Closed | [5 empty] | To be picked up as part of Migration IA - - new DIN will be raised as required. |  |  |  | EDI021 | EDI021 |  |  |  | 2023-07-14
MHHS-DIN-249 |  | Migration Design | 2023-03-27 | Migration Design |  | Matthew Breen | Programme |  | Discussion around the use of BST/UTC during Migration |  | Closed | [5 empty] | DIN is not specific enough. | [8 empty] | 2023-07-14
MHHS-DIN-250 |  |  | 2023-04-06 | Design Team | 3764 | Steve Weston | Programme | Participant ID 10 digit number | This is related to ticket 3764, to update the Interface Specification to ensure the Participant ID is clearly defined as a 10 digit number [0-9] only, and the examples in the Interface Specification align to this, including where this is used as part of the sender unique reference and the examples shows 11 digits, not 10 digits for Participant ID. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | In E2E001 doc Section 4.2.3.2 Section 4.4.4.2 example code for Sender unique Ref and in Transaction ID Section 4.5.5.3 as above DES138 doc Data Catalogue tab: DI-990 example and DI995 Example DIP common tabl DI995 example and the example JSON block (the above easy to change) ALL the IF tabs the JSON block example the Sender Unique Ref contains Participant ID and in every example its longer than 10. JSON/YAML Files: Update JSON examples where Sender Unique Ref and Transaction ID contain a Participant ID example longer than 10. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 Solution Architecture MHHSP-DES138-Interface Catalogue JSON/YAML files | MHHSP-E2E001 Solution Architecture MHHSP-DES138-Interface Catalogue JSON/YAML files |  |  |  | 2023-06-16
MHHS-DIN-251 |  |  | 2023-04-06 | Design Team | 3860 | Steve Weston | Programme | IF-041 Population | This is related to ticket 3860, to update the Interface Specification to provide more clarity / notes on the optionality of B064 and B065 blocks in the IF-041 interface. This is in relation to notes / detail about which blocks are mandatory (from a contractual perspective) versus what should be included in the message if the data exists. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updates the notes section of IF-041 in order to provide guidance on the minimum population of B064/B065 blocks. This clarifies "When exchanging readings between parties the design assumes that in the most part this will be the Cumulative Register Reading (Block B064). However, at participants request this message also allows for the exchange of Configurable Register Readings (B065) either alongside a Cumulative Reading or in isolation. For the avoidance of doubt the message must contain at least one B064 record and /or one (or more) B065 records [depending on the number of configurable registers], in order to be considered valid. " | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-252 |  |  | 2023-04-06 | Centrica | 3661 | Neil Strange |  |  | We believe there is a Design Gap at Change of Agent and Change of Supplier for Smart Meters which also impacts Migration. Neither the Registration Service, Metering Service nor Data Service will know how the registers are set up and specifically which are active. Consequently the Data Service will not know which registers to send on the IF-041, nor will there be able to calculate consumption correctly without knowing the register set up. The interface catalogue for IF-041 states in respect to this “B065 Block Below Repeated for each set of Configured Register(s) for each Meter” – we do not believe there is a way to give the DS this information. The supplier will set up the smart meter configuration to enable the registers to capture the usage for certain time periods. There is currently no way for the supplier to inform the DS which registers are active at what time of the day - the DS cannot accurately calculate the consumption breakdown based on the reads when there are multiple registers configured. |  | Closed | [5 empty] | DIN closed, Design Team to send email recommending for a CR to be raised. | [8 empty] | 2023-07-14
MHHS-DIN-253 |  |  | 2023-04-12 | British Gas | 3769 | David Hipwell | Large Supplier | Volumetrics | The latest E2E Functional and Non-Functional Requirements MHHS-E2E Requirements V3 which went to V3 on 16/02/2023 appears to focus on message counts and response times. For example:- During transition all meter points (ca. 31M) will be transition between the old and new services. Therefore assuming a linear migration over the year this would result in the load below, hence services shall be capable of processing the following volumes: - average daily volume of 680,000 - peak daily volume of 2.4M 5.0M - annual volume of 248M 500M Analysis of the flows needs to be categorised across all impacted market participant roles including the DIP. Only then will it have meaning for all parties. The calculation needs to take account of the migration period using the MHHS migration volumes according to date (including REVERSE migration). These should be in both message counts and also sizing (e.g. Gb). And include for a BAU day and also migration days. Whilst some calculations can use the total number of MPANs, to be useful these need show also at perhaps for a million MPANs in each role. Only then will all parties be working on a single set of figures. A line in the sand. The NFRs that exist appear to have moved away from any form of technical calculation towards business process figures. But these figures need to go as an input into technical sizing’s, and should have done for DIP – can these be produced and published ? |  | Updates Ready to Release | Clarification - No change required | DIP Users | 2023-09-13 | Post Go-live Release | 0 | Volumetrics analysis was presented to DRG on 13th September with some minor comments (see DRG meeting minutes). Updated volumetrics document will be issued as part of IR5. The document has been updated to include the following information to support these requests: - Overview of assumptions that form the basis of the volumetrics document. For the purposes of this volumetrics document, this includes things like number of meters, consumptions per day, settlement days per message, MPAN per message, breakdown of smart vs traditional, breakdown of SMETS1 vs 2, those providing Import / Export / Both etc. - There is breakdown of smart meter & traditional meter split that inform actual / estimated reading, alongside patterns for message structure. The 2 patterns explored provide a range used in the scenarios – these are consolidated and individual IF-021 messages. - Additional scenarios that include an average (best-case) distribution of IF-021 messages across a 24 period, as well as scenarios that cover a peak of peak (worst-case) distribution of messages across a 24-hour period. These scenarios align with all NFRs. - The scenarios provide upper and lower message bounds across the day, as well as provide message throughput per hour / second. - Additional scenarios split into 2 sections – with a breakdown for the DIP plus a breakdown for an MP with a portfolio size of 1 million. - Graphs added to show / illustrate distribution of the messages for the scenarios for all traffic into the DIP. Without firm guidance on how each Data Service are likely to submit IF-021 messages four different scenarios are used to help inform average / peak processing volumes as follows, which are detailed in the volumetrics document as follows: - Scenario 1 - Market Participant IF-021 messages equally distributed across a 24-hour period - Scenario 2 - Market Participant IF-021 messages equally distributed across a 6-hour period - Scenario 3 - Market Participant IF-021 messages unequally distributed across a 6-hour period - Scenario 4 - Market Participant IF-021 messages distributed unequally across a 24-hour period using a Monte Carlo simulation model Scenarios 2 & 3 describe extreme patterns of data submission that are very unlikely to occur in reality; they present a worst-case scenario where the patterns of submissions follow the End-to-End requirements to the extreme and Data Services submit data almost simultaneously. Scenario 4 presents a statistical approach where the volume of IF-021 is randomly distributed according to a Monte Carlo simulation. Alternate scenarios, that are not considered BAU, are also presented and included in the Volumetrics document: - Submission after an unplanned Outage for 72 hours as per NFR. - Market Transition / Migration. - Change in Meter Population from 50% to 90% over time. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E004 E2E Architecture - Transaction Volumes | E2E004 E2E Architecture - Transaction Volumes
MHHS-DIN-254 |  |  | 2023-04-17 | Siemens | 3044 | Tony Mason | Metering Service | Update of Consent, DPI, etc. | this does surprise me and doesn’t seem to correspond to the routing rules in the Interface Specification. A proposed Data Service is not included in the routing tables for the receipt of a PUB-018, for example. I would therefore expect that if a change to DPI occurs between PUB-033 and PUB-036 the proposed Data Service could only be notified on a revised PUB-033 with the Appointment Scenario set to whatever the original scenario was set to – “SEG”, “CSP”, or “COS”. |  | Closed | [5 empty] | Ref notes on the maintenance of these data items in the Regi Info Section of the I/F document. Prospective SPs are not notified of changes to these data items during their prospective period. If these Data items change then the supplier should re-evaluate the SP they have proposed and change the appointments as required. If an SP takes on a supply with different elements/factors to those suggested by the supplier at appointment this is a contractual issue between the SP and the Supplier. | [8 empty] | 2023-06-16
MHHS-DIN-255 |  |  | 2023-04-17 | Elexon | 3983 | Kate Goodman | Testing | Consumption on De-Energised MPAN (IF-013/IF-014) | ConsumptionOnDeEnergised is an Event Code mentioned in the list of data items but is not present in header where the routing info is held - needs to be added to header |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | ConsumptiononDeEnergised event moved from IF-013 to IF-014 and added in routing rules. See also DIN332 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-256 |  |  | 2023-04-17 | Elexon | 4169 | Kate Goodman | Testing | IF-014 Block B067 | DI-015 is mentioned in the header wrt routing but is not present in the message itself. It either needs to be removed from header or added into message. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Block B067 added to IF-014 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-257 |  |  | 2023-04-17 | Elexon | 4172 | Kate Goodman | Testing | B053 repeating block | B051 is a block which repeats for each combination of Load Shape Criteria (denoted with single chevron to show repeat). B053 is another repeating block which is denoted by two chevrons, implying it is nested below B051. But in fact it also repeats for each combination of Load Shape Criteria. Should this just have a single chevron or is there further information that needs to be added to make its double chevron make sense? |  | Closed | [5 empty] | No change required as there will be multiple B053 in each B051 block. | No Change |  |  | none | none
MHHS-DIN-258 |  |  | 2023-04-19 | ENWL |  | Paul Band | Network Operator | LDSO use of DIP vs internal for Specific messages | There are a number of requirements in the MHHS-BRS005-LDSO document which state that we must obtain various registration data via the DIP and maintain records accordingly such as: MHHS-BR-LD-001-005, MHHS-BR-LD-024, MHHS-BR-LD-030 and MHHS-BR-LD-034 Extrapolating these into requirements for our own systems suggests that we should build databases/tables to store this data and maintain it The requirement is placed upon us as a party under the assertion that all settlement related data should be exchanged between services and parties via the DIP. However LDSO’s are unique in that their data exchange for their party type is split and is typically split by system under these party types. As a consequence we already communicate directly with MPRS as it is already part of our system architecture as a paid for and created service by LDSO’s. |  | Closed | [5 empty] | CR26 has been raised to covere this LDSOs have been advised to raise a Programme Change Request. Discussion at the DRG of the 27/4/23 did not agree on the development of a New Design Principle, A further workshop with LDSOs needs to take place to discuss alternate options and confirm agreement amoungst all DNOs & IDNO on the receipt of publication | [8 empty] | 2023-07-14
MHHS-DIN-259 |  |  | 2023-04-20 | ESG | 3756 | Patricia Parker | Software Provider | BP003C correction | On BP003C under the CoR section there is a note which states that the readings that pass validation should have Meter Reading Status (J0047) set to ‘T’ and when it has failed set it to ‘F’. However as per the REC the group which houses the J0047 group (032 – screenshot below) should only be present where the Meter Reading Flag (J0045) is set to ‘F’. I have checked DES196 and cannot see that the conditionality for that group is changing in the D0010 therefore I can only assume that the note on the process map is incorrect, and it should be talking about the J0045 value instead. Please can you confirm? |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Modification to Note on process to refer to "Meter Reading Flag (J0045)", modify flow label to step230 to "(Read Flag = "T")" Modification to the process note to advise the J0047 would not be present if the meter reading flag (J0045) is set to "T". It will only be present in case the J0045 is set to "F". | Process Model correction | Metering Changes |  | MHHSP-BP003C-Transfer of Reads | MHHSP-BP003C-Transfer of Reads |  |  |  | 2023-06-16
MHHS-DIN-260 |  |  | 2023-04-20 | CGI | 4167 | Dave Webster | Software Provider |  | Swagger definition does not match DES-138 in version 1.0 or 1.1. |  | Closed | [5 empty] | No specific detail provided, however comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1, therefore closed
MHHS-DIN-261 |  |  | 2023-04-20 | Utiliteam | 4245 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. Configurable Register Reading Date/Time is missing. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue JSON/YAML Files | MHHSP-DES138-Interface Catalogue JSON/YAML Files |  |  |  | 2023-06-16
MHHS-DIN-262 |  |  | 2023-04-20 | Utiliteam | 4214 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. B070 for IF-031 is wrong. It contains the word DIP in the Swagger, which is not included in DES-138. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files | JSON/YAMl Files |  |  |  | 2023-06-16
MHHS-DIN-263 |  |  | 2023-04-21 | CGI | 4203 | Dave Webster | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. DI-122-Profile-Class is defined as an integer, but in DES138 it is defined as a string length 2. Needs to be updated in the Swagger. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Swagger and Data Catalogue aligned to String 2 for DI-122 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files | JSON/YAMl Files |  |  |  | 2023-06-16
MHHS-DIN-264 |  |  | 2023-04-24 | Elexon | 3946 | Rashmi Radhakrishnan | Central Body | Update to CCC Method Statement | One of my colleague pointed out a typo in the CCC method statement attached, and I would like to draw your attention to it and requesting to make necessary amendments. The CCCID starting from 100 to 107 has Market Segment Indicator as “U” and Connection Type Indicator shown as “W”. We think that, for these line items the Connection Type Indictor need be corrected to “U”. For reference please see below picture and this also aligns with ISD entity spec v5.0 (M2 entity). CCC ID Market Segment Indicator Measurement Quantity Consumption Component Indicator Connection Type Indicator 100 U AI C W 101 U AI L W 102 U AE C W 103 U AE L W 104 U AI C W 105 U AI L W 106 U AE C W 107 U AE L W All 'W's' should be 'U's') |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Method Statements (MDS & VAS) will be updated for "W" to be replaced by "U"within ISD Table - MHHS Consumption Component Class. Please note: ISD entity M5 file has already been updated to reflect the fact that unmetered supplies have a connection type of "U". | Design Ambiguous | Supporting Docs | Method Statement | MDS Method Statement VAS Method Statement | MDS Method Statement VAS Method Statement |  |  |  | 2023-07-14
MHHS-DIN-265 |  |  | 2023-04-25 | Elexon | 4128 | Rashmi Radhakrishnan | Central Body | Validity of Settlement Period quality indicator data set | ISD entity M5 has a filed Settlement Period quality indicator. Is this the complete valid data set for the field Settlement Period quality indicator? I took this below list from interface catalogue v5.0. A = Actual, E= Estimate (UMS Only) A1,A2,A3, AAE1,AAE2,AAE3,EAE1,EAE2,EAE3 (ADV Only) E0 --> E9 = Estimation Method 1 - 9 ZE = De-Energised ZE1--> ZE3 = Zero Estimation Method 1 -3 but the Advanced Data Service Estimation Method Statement has data flags EA1 till EA13 which is not mentioned in the above list. Also, the ISD entity spec M5 example below shows a different data item that is not in the list at all for Unmetered(104 &105). Is this a mistake? |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Interface document updated with the full list of settlement period quality indicators for ADS and swagger updated accordingly. within DES138. 02-IF-016/14 and in the data cat. DI-083 "EA1-->EA13 = ADS Estimation Methods" added. | Design Ambiguous | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-07-14
MHHS-DIN-266 |  |  | 2023-04-26 | ESG | 3899/ 925 | Patricia Parker | Software Provider |  | If the D0300 process is not changing then we believe that DES196 is incorrect and should show added routes to allow the Supplier to send a D0300 to the Data Service Matt M has confirmed - We are working through the exchange of CoS readings as the code drafting has raised some questions about the extent to which the SDS is involved in the D0300 process. For smart meters, the SDS will not have any use for the billing register readings so D0300 process should not apply, or at most could only be missing the total cumulative. However, it likely will still be required for traditional meters. On that basis, I think we can acknowledge that the D0300 will be retained and SVs created for Supplier to SDS for traditional meters. The process for smart meters is being discussed internally as the SDS does not retrieve tariff register readings. There will be an updated version of DES196 issued in the next few weeks to reflect feedback from the DTN flow part 2 consultation issued in late March which will reflect the retention of the D0300. |  | Closed | [5 empty] | Email comms sent to Patricia confirming the D0300 is a Supplier to Supplier flow. Therefore should there be a need to send readings to the DS, this would be done via a D0010/IF-041 with the correct data flags set in both. Based on this there is no requirement to send D0300 to the DS. Matt M confirmed when finalising DES196 he confirmed this in his comment response to ESG. The MSAG Consequential Change - Switch Meter Read Exceptions v1.0 22.06.23 provides a more comprehensive explanation of the MSAG conclusions. No change required to DES196 | Design Ambiguous | Supporting Docs | Method Statement | MHHSP-DES196- D-Flow and Interface Mapping | MHHSP-DES196- D-Flow and Interface Mapping |  |  |  | 2023-07-14
MHHS-DIN-267 |  |  | 2023-05-02 | ESG | 4385 | Patricia Parker | Software Provider | RegX Validation Issue | RegExpression on the DI-148-Annual-Consumption use of DT-016-Decimal-9-3 in the 1.1 swagger spec. This needs to be updated to align with DES-138 example of 123456789.123. Regex should be ^-?[0-9]\d{8}(\.\d{3})?$ instead of ^-?[0-9]\d{7}(\.\d{3})?$ |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Swagger v1.2 has been updated accordingly | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files | JSON/YAMl Files |  |  |  | 2023-06-16
MHHS-DIN-268 |  |  | 2023-05-03 | SRO Design |  | Sean Cooper | SI Design | Secondary Routing | It was always the intention to revisit and revise all of the Secondary Routing configuration as part of DIP Detailed Design. Completion of this exercise has also resulted in some changes to other routing parameters. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Following discussion with Avanade the Secondary routing short codes have been simplified and the routing of each IF revisited based on these revised short codes. These are shown highlighted in BLUE in the routing section of each of the individual IF pages. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-269 |  |  | 2023-05-03 | St Clements | 4424 | Anna Davis | Software Provider | Swagger Alignment to DES-138 | We have also realised that there are a large number of discrepancies for each interface between the data item name in Swagger vs the YAML name in the Interface Catalogue Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated inconsistencies in the Interface 01-Data Catalogue and Swagger. Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-270 |  |  | 2023-05-05 | SRO Design | 4557 | Rob Golding | SI Design | Correlation ID | Provide further clarity on how Correlation ID's work. This will impact numerous artefacts including DES-138 and E2E001 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DES-138 Interfaces updated to reflect correct 'COPY' property on IF routing tables. updated IF-008, 16, 20, 26, 28, 37, 39 and 50 for this DIN. Added *New to IF-020 showing a new correlation ID is needed to be created for these events, others events needed a COPY of the correlation ID. IF-050 had “No” added to show that a Correlation ID is not required. Updated the E2E001 design document with a more detailed worked example in section 5.4 that details how and where the Correlation ID is populated. | Design Ambiguous | Supporting Docs |  | MHHSP-DES138-Interface Catalogue. E2E001. | MHHSP-DES138-Interface Catalogue. E2E001. |  |  |  | 2023-06-16
MHHS-DIN-271 |  |  | 2023-05-10 | ESG | 4541 | Patricia Parker | Software Provider | Swagger Alignment to DES-138 | S0 and S1 is Mandatory in DES-138 v5.1.1, but is not marked as mandatory in the Swagger 1.1. Swagger needs to be updated to align with DES-138. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Swagger 1.2 updated so all SO and S1 blocks are mandatory as per DES-138 | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-272 |  |  | 2023-05-10 | SRO Design | 4656 | Rob Golding | SI Design |  | Required to DIP Channel Publication (v1.2 of the swagger) that will allow DCPs to register webhooks on behalf of their clients |  | Closed | [5 empty] | Duplicate of DIN-375
MHHS-DIN-273 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | New MSN Data Type | MHHS Data Type (DT-029) - for Meter ID / Serial number for DI-053, DI-056 and DI-060 added to DES138 01-Data Catalogue, Swagger updated. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | New Data Type created in Swagger v1.2 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-274 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | Missing YAML in DES-138 - DI-073, DI-074, DI-080, DI-111, DI-112, DI-190-194, DI-300, DI-021, DI-022, DI-060, DI-076 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Missing YAML names for Data Items confirmed and added to 01 - Data Catalogue Note:All DI's upsated except DI-076 has not required a changed. Other DI chnages not listed are picked up as part of DIN261 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-275 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | DI-093 / DI-120 - Data length 2,000 not 200. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | All additional info data items set to len 2000 in Swagger v1.2, DES138 DI-093/120 length updated in 01-Data Catalogue | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-276 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Classifications | MHHS Data Classification - ensure all columns are populated for Public and Restricted ie, MPAN & Address (removall all NULLS). |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Data Classifications added in v5.2.1 where previously there was no entry ( Column I in the Data Catalogue ) | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-277 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Owners in Data Catalouge | MHHS Data Owner - where there are NULL's, this should be updated so all columns provide an owner, mark as N/A (remove all NULLS). |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Metering Service added as Authoritative Source and MHHS Owner in v5.2.1 of DES138 Data Catalogue for DI-190 to DI-195. Previously there was no entry. | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-278 |  |  | 2023-05-10 | Design Team | 4590 | Rob Golding | Programme Design | Addition of indicator for each IF within DES138 | Please can DES138 Interfaces spreadsheet be updated to provide an indicator against each interface (or is it interface & event code) as to whether it can be opted in/out by a recipient. | CR029 | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Design Team to add optionality matrix to DES138. Name of worksheet: 04_IF_Optout_Matrix | Design Ambiguous | Supporting Docs |  | DES138 Data interface specification | DES138 Data interface specification |  |  |  | 2023-07-14
MHHS-DIN-279 |  |  | 2023-05-12 | ESG | 4484 | Patricia Parker | Software Provider | Event Code clarifiction for DS when sending back validated customer read on PUB-041 | The BP005 – Data Processing – Process map shows that when a Customer Own Read has been sent to the Data Service from the Supplier in the IF-041, EventCode = ReadingCoR, the Data Service will perform reading validation and issue the PUB-041 back to the Supplier, in the Read Sharing column of the process map. When the Data Service send back the validated customer own read in the PUB-041, what eventcode will they use and where can I find this documented? The previous response says “There is no IF-041 response, check consumption is as expected in PUB-021” is this correct for Customer Own Reads on Smart meters? The map shows otherwise so please can you confirm if the answer or map is correct and if the map is correct, provide information on what event code will be used. |  | Closed | [5 empty] | This is a query not a DIN. Previous response provided is correct .... There is no IF-041 response, check consumption is as expected in PUB-021” | [8 empty] | 2023-07-14
MHHS-DIN-280 |  |  | 2023-05-12 | ESG | 4552 | Patricia Parker | Software Provider |  | DES196 lists the D0386 (Manage Metering Points) as ‘not impacted’ owned by the REC however BP010 shows that the method of maintaining Related MPANs is via the IF_019 / PUB_020 process. Can you confirm whether the D0386 is going to be removed post- MHHS. If not, could you please clarify what process a Supplier should follow post- MHHS. |  | Closed | [5 empty] | D0386 will not be used post migration to MHHS Regime. Management of MPAN relationships will be under taken using IF-019/IF-020 | [8 empty] | 2023-07-14
MHHS-DIN-281 |  | DI-172 | 2023-05-12 | St Clements | 4446 | Madison Layton | Software Provider | BP003 IF-35 flow | MHHS-BR-RS-053 for the incumbent MS to be notified on If-035 DSAppAccepted where meter is advanced or traditional is missing from BP003 business process diagram and steps. Also updates to BP003 and BPD003 forward migration for consistency |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | IF-35 flow from step 85 (if accepted where meter is advanced or traditional to Meter Service (incumbent) and additional step 86 to receive appointment response to BP003, and added step 86 and BR-RS-053 ref and details to step 85 to the BPD003 | Process Model correction | Metering Changes |  | MHHSP-BP003-Change of Service - Data Service, BPD003 Forward Migration BP003 and BPD | MHHSP-BP003-Change of Service - Data Service, BPD003 Forward Migration BP003 and BPD |  |  |  | 2023-06-16
MHHS-DIN-282 |  |  | 2023-05-16 | SIMS | 4821 | Martin Freeman | Software Provider | Status code removal | Status Code is included in the E2E001 design response body (4.4.4.2), when this is HTTP Response code and should be removed as this is defined in the callback response. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Removed from section 4.4.4.2 from the E2E001 design document as this is not required. This now aligns in Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture | MHHSP-E2E001 End-to-End Solution Architecture |  |  |  | 2023-06-16
MHHS-DIN-283 |  |  | 2023-05-16 | SIMS | 4826 | Martin Freeman | Software Provider | ID Capitalisation | ID should be capitalised in all places in the Swagger. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | All JSON names now have capitalised ID fields for Swagger 1.2. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-284 |  |  | 2023-05-16 | SIMS | 4828 | Martin Freeman | Software Provider | HTTP Response Code | HTTP Response code for success should be 201 in E2E001 as per Swagger. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to E2E001 design document in section 4.4.4.1, 4.5.5.1 and 5.3 to align with Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture | MHHSP-E2E001 End-to-End Solution Architecture |  |  |  | 2023-06-16
MHHS-DIN-285 |  |  | 2023-05-16 | Elexon |  | Rob Golding | SRO Design Team |  | Add replay / requeue API for Swagger 1.2 to align with existing E2E001 Design. Add additional information / clarity in the E2E001 for Interim Release 2 to align changes between design and Swagger. |  | Closed | [5 empty] | Duplicate of DIN-374
MHHS-DIN-286 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Issue clarification to Participants through DRG that all ECS Reports will be issues via Pattern B. Update of ECS Report Catalouge to reflect this. |  | Closed | [5 empty] | The ECS reports will be via Pattern A. No change is required to the ECS reports
MHHS-DIN-287 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team | Guidance notes for distribution of ECS reports | Create & Issue guidance document on the distribution of ECS Reports. To Contain : - overview of Pattern B Process - Guidance on population of IF-047 - Update of IF-047 Event Codes |  | Closed | [5 empty] | Solution yet to be defined No longer required as pattern B will not be implemented for ECS reports | [8 empty] | 2023-07-14
MHHS-DIN-288 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Update of Swagger with ECS Reporting Structures |  | Closed | [5 empty] | These interfaces are in place from Swagger 1.1. | [8 empty] | 2023-06-16
MHHS-DIN-289 |  |  | 2023-05-17 | SRO Design Team | 4994 | Rob Golding | SRO Design Team | Interfaces for consumption replay | IF-015 / IF-016 - updates to E2E001 to provide clarification on design pattern. Alignments between DES-138 & Swagger alongside this. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | E2E001 design updated (Section 5.1.7) to provide additional information / clarity on these interfaces in relation to Consumption Replay. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture | MHHSP-E2E001 End-to-End Solution Architecture |  |  |  | 2023-06-16
MHHS-DIN-290 |  |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Proposal to change all / subset of ECS Reports to Pattern B |  | Closed | [5 empty] | Duplicate | No Change
MHHS-DIN-291 |  |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | As a result of DIN-290 -- Where should the reporting assets be hosted?? DIP solution specified, but what are the other options are availible. Final solution option to be ratified and documentation updated. |  | Closed | [5 empty] | Not hosted as via Pattern A | No Change
MHHS-DIN-292 |  |  | 2023-05-17 | St Clements |  | Madison Layton | Software Provider | ISD Entity M17 | Change required to ISD Entity M17 to add in Market Segment into the table - otherwise it cannot be used to derive consent values which was its original purposes |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | 1. Update Table name to "Consent Granularity Valid Combinations" 2. Added Market Segment as new table column 3. Update table to show all valid combinations | Process Model correction | Supporting Docs |  | MHHSP_EDI021_ISD_Entities | MHHSP_EDI021_ISD_Entities |  |  |  | 2023-06-16
MHHS-DIN-293 |  |  | 2023-05-17 | Design Team |  | Paul Petitt | SRO Design Team |  | Retrospective DIN raised to ensure that any changes that are made in multiple downstream documents (for example CoCo, DIP Logical Design, DIP Physical Design & DIP Security Design) are reflected / updated in LDP assured documents to ensure e2e design / requirements alignment. This was agreed in a DRG Meeting in March 2023. |  | Implemented |  |  |  | Interim Release 1 |  | design changes to E2E001 End-to-End Solution covering points described in DIN details | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-294 |  |  | 2023-05-19 | ESG | 5030 | Luke Speakes | Software Provider | BP007 PUB009 flow | What I need to know is if the supplier will receive a PUB_009 with the Event code of [CSSDeRegistration] because nowhere on the BP007 process map does it show the supplier receiving the PUB_009 following a deactivation but on DES138 it shows the supplier as being a recipient of this event code. Step 95 (ringed below) shows the supplier as receiving the PUB_009 off the back of the Disconnection (event code [MPANDisconnection]) but then no where else on the process map does it have the supplier receiving a subsequent PUB_009 following the successful deactivation. Additional step required from step 130 (maybe 137?) to show both PUB-009 Mpan Disconnection and PUB-009 Deactivation going to supplier |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | BP007 change : There is already a flow from Step 85 to Step 95 for PUB009 for disconnection (no change) But need to Add a new step (137) for Receive Deactivation in Supplier lane from Step 130 for PUB-009 MPan deactivation in BP007 And there is already a PUB-037 flow from step 145 to Supplier step 157 for confirmation (so no change there) Addition of step 137 to BPD007 | Process Model correction | Metering Changes | Disconnection | MHHSP-BP007-Disconnection, BPD007 | MHHSP-BP007-Disconnection, BPD007 |  |  |  | 2023-06-16
MHHS-DIN-295 |  |  | 2023-05-19 | SIMS | 4821 | Martin Freeman | Software Provider | L1/L2 Error Codes | Error code detail updates in DES-138 for Level 1 and Level 2 validation needs to be clarified |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updates made to Introduction Tab of DES138 in order to clarify Lev1 vs Lev2 error codes. Design is such that participants should expect error code(s) at either level. Further ammendments could be made following Avanade clarifications. | Data interface correction | Supporting Docs |  | DES138 Data interface Definition | DES138 Data interface Definition |  |  |  | 2023-06-16
MHHS-DIN-296 |  |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | It is envisioned that Configuration Management of ISD will largely follow the existing customs, practices and processes as are currently in place for managing MDD changes. However, DIN is required to formally confirm the Owner(s) and allowable update mechanisms (Standard or FastTrack) for each of the new ISD Entities outlined in the DIN. |  | Closed | [5 empty] | This is a Code Drafting issue not a Design / DIN issue. Code drafting team will be covering ISD maintenance processes | [8 empty] | 2023-07-14
MHHS-DIN-297 |  |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | What Participants are recognised in the existing / new ISD Participant tables…. How does this link in with the parties recognised by the DIP (and assigned DIP Roles / IDs …. Or Not) …. In particular how are MDRs referenced in ISD? Does this reference need to identify the ‘type’ of MDR? Also, there is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 |  | Closed | [5 empty] | These issues are covered in Release 3 updates (DIN372 & DIN 070) . ISD updated to confirm participants recorded in M16, a new table M18 "DIP Participant Roles" was added. | [8 empty] | 2023-07-14
MHHS-DIN-298 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Update to UMSDS method statement. | As I understand it, you are advising we should A flag the consumption data (even though it isn’t Actual), until the zero charge code D0388 UMS Inventory is received from the UMSO. Therefore - if we have an inventory, regardless of the energisation status of the MPAN, we always use an A Flag. But as you’ve stated, this means an IF-013 will be issued to us as UMSDS, because there is A data, against a De-Energised MPAN. If this is the design/requirement then it is understood – but I would like to call out that this should be detailed within the UMSDS method statement – so I think a DIN is needed to get this requirement added? |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement | METH004_UMSDS Method Statement |  |  |  | 2023-07-14
MHHS-DIN-299 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | IF-013 update to include UMSO recipient | Further to this (DIN-298), the cause of this IF-013 being issued can only be that the UMSO has not provided the UMSDS with the correct D0388 UMS Inventory to use. Therefore – the UMSO has a requirement to receive the IF-013 to tell them this. However, the Interface Catalogue has not designed that this will get sent to the UMSO. I think this is a Design Issue too, and also needs a DIN raising so that the IF-013 is provided to the UMSO. |  | Closed | [5 empty] | No this is incorrect. UMSO is not involved with Consumption. If IF-021 submission is rejected this is an issue for the DS (incl. UMSDS) to address and Manage. Any issues regarding the metering onsite/energisation status need to be managed by the DS (incl UMSDS) with their appointing Supplier and Partner Metering Service. |  |  |  | DES138 | DES138 |  |  |  | 2023-07-14
MHHS-DIN-300 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | You are advising a Load Shape will always require the E Flag. But as you say if the MPAN is de-energised, that MDS will reject the IF-021. Is this therefore your answer – that MDS will reject the IF-021, and there is nothing that can be done about that, so we just need to accept we will get those rejections? If so, this isn’t really a satisfactory process, to know rejections will be received in this scenario. Can you just confirm that the solution here is we just need to accept we will get these rejections to the IF-021, which we will then simply ignore? If that is the case – again a DIN needs to be raised to write this into the Design so the process is documented. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. See DIN 506 which has updated DES138 to show that IF-014 also contains warnings for MPANs with consumption on de-energised sites. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement | METH004_UMSDS Method Statement |  |  |  | 2023-07-14
MHHS-DIN-301 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | the corrective action on this scenario (DIN-300) occurring will be if/when the UMSO provides the UMSDS with a D0388 UMS Inventory – then the UMSDS will stop using and submitting the Load Shape data. There does not seem to be a mechanism in the Design for the UMSO to be made aware of this issue that would be of their making, so again needs raising as a DIN please. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. See DIN 506 which has updated DES138 to show that IF-014 also contains warnings for MPANs on de-energised sites. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement | METH004_UMSDS Method Statement |  |  |  | 2023-07-14
MHHS-DIN-302 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | I’ve pulled together the below table. This covers all the possible scenarios of the UMSDS either having or not having the D0388 UMS Inventory. Combined with whether that D0388 UMS Inventory has load associated data within it. Also combined with whether the MPAN is Energised or De-Energised. Here I’ve listed which Settlement Period Quality Indicator should be used, and where applicable, which Estimation Reason Code should be used. Should this be included in the UMSDS Method Statement and if so, are you happy with the below. In Green are steps we understand. In Red, these remain Unknown to us based on the Design and your answers given. In Orange, these are answered based on your guidance on your email of 28 April – but are not specified in the written Design. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement | METH004_UMSDS Method Statement |  |  |  | 2023-07-14
MHHS-DIN-303 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.2.3 - Changes to Data formatting to align with Swagger / DES-138 |  | Implemented |  |  |  | Interim Release 1 |  |  | Technical corrrection | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-304 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.4.3 - Case Sensitivity - additional information added to provide clarity on approach |  | Implemented |  |  |  | Interim Release 1 |  |  | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-305 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 5.1.7 - Additional Detail required for IF-47 / ISD to provide clarity on approach / steps |  | Implemented |  |  |  | Interim Release 1 |  |  | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-306 |  |  | 2023-05-22 | Tym Huckin | 3992 | Tym Huckin | Consultancy | Clarification/examples for DI-101 for BST/UTC cross over period | Further clarity / worked examples for UTC Settlement Date (DI-101) for BST / UTC cross over period. |  | Closed | [5 empty] | This is not a design change it is a Question/Clarification . | [8 empty] | 2023-07-14
MHHS-DIN-307 |  |  | 2023-05-22 | CGI | 5042 | Dave Webster | Software Provider |  | Status code incorrectly included in required, although not in Standard Response Body Type. This is in Swagger 1.2. |  | Closed | [5 empty] | Duplicate of DIN-282
MHHS-DIN-308 |  |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | S0 Block required property | Add required property to all the S0 blocks in the interface definition |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to Swagger for all Interfaces to mark 3 fields in the S0 block as mandatory. | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-309 |  |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | Swagger Alignment to DES-138 | Define Transaction ID (DI-990) with no Min Length to align with DES-138. This is DT-014. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (DIP Transaction ID min length removed) | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-310 |  |  | 2023-05-23 | ELEXON | 5173 | Rob Golding | Central Body | Guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 | Guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 are to be applied (if at all), i.e. does the DIP need to consider the effective period and only accept messages on the production system when the message falls within this period? And if so what date within the message should be used as a check? Or the physical date/time of message receipt? Or doesn’t the DIP need to consider these dates at all and no check needs to be applied? |  | Closed | [5 empty] | This has been included in the DIP onboarding design. | [8 empty] | 2023-07-14
MHHS-DIN-311 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-985 / DI987 both String 60. Swagger Min and Max Lengths aligned |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updates made to DES-138 for Length alignment to 60. Updates to Swagger to remove min length for DI-985 and DI-987. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-312 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-984 / DT-009 needs to be updated to be min 3 / max 5 length. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Sender Role - change on 01 Data Catalogue DI-984 as per description | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface | MHHS-DES138 Data interface |  |  |  | 2023-06-16
MHHS-DIN-313 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S1 - Sender Timestamp updated correctly (from sent timestamp) in Swagger to align with DES-138 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (renamed to Sender Timestamp) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-314 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - Publication ID Min Length updated in Swagger 1.2 to be 6 to align with DES-138 (rather than 7) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Publication ID Min Length now 7, not 6) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-315 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - DIP Correlation ID should have no min length to align with DES-138 (rather than min length of 1) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (DIP Correlation ID has no min length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-316 |  |  | 2023-05-25 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, all DT-006 and DT-006N should have min length 10 & max length 10 to be consistent. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated DES-138 01-Data Catalogue to align Data Type and provide consistency to Swagger. Removed DI-095 which is no longer used. | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface | MHHS-DES138 Data interface |  |  |  | 2023-06-16
MHHS-DIN-317 |  |  | 2023-05-23 | St Clements |  | Sean Cooper | SRO Design | B9xx array references within Swagger to be updated within DES138 | Update DES138 IF document to include reference to the B9XX Array references held in Swagger |  | Initial Assessment/Updating | Design ambiguous | N/A |  | Post Go-live Release | 0 | Solution yet to be defined | Design Ambiguous | Supporting Docs | Interfaces | DES138 | DES138 Interface Catalogue |  |  |  | 2023-07-14
MHHS-DIN-318 |  |  | 2023-05-23 | REC | 5049 | Jonny Moore | Consultancy | Addition of 'Effective from date' data items to RMP Status (regi) and MP Status in IF-050 | While completing the design phase for EES we noted that the following items with the IF-050 do not have an effective from date. - RMP Status (Registration) - MP Status These items currently have an effective from date held in EES and not including this in the IF-050 would have the effect of removing these items from EES. |  | Closed | [5 empty] | REF DIN-508 | No Change | [7 empty] | 2023-07-14
MHHS-DIN-319 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S0 - EventCode to marked as required to align with DES-138 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Event Code marked as required) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-320 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, S1 - Environment (DT-013) should have min length 3 & max length 10 to be consistent with values. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | 01-Data Catalogue DI-991 Environment Set Min to 3. However, string length is 10, so max length should be set to 10 | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface definition | MHHS-DES138 Data interface definition |  |  |  | 2023-06-16
MHHS-DIN-321 |  |  | 2023-05-23 | St Clements | N/A | Sean Cooper | SRO Design | B005 add to IF-036 | Consider adding B005 to IF-036 so that incoming SP knows who previous SP were |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Added B005 to IF-036 so that incoming SP knows who previous SP were. Updated block name to B005 - Incumbent/Outgoing Service Providers | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-07-14
MHHS-DIN-322 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B002 - Incoming Supplier MPID - Swagger aligned to DES-138 for min / max lengths |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Incoming supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-323 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B003 - Ougoing Supplier MPID - Swagger aligned to DES-138 for min / max lengths |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Outgoing supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-324 |  |  | 2023-05-24 | EDF | 4780 | Paul Saker | Supplier | NHHSP-BPM00C- Transfer of Reads on Change of Data Service process steps and messages clarification | NHHSP-BPM00C- Transfer of Reads on Change of Data Service details several process steps and messages related to obtaining and sharing register readings between the gaining and losing suppliers to agree a CoS, and to initiating the missing/disputed reads process defined in the Retail Energy Code where CoS reads are missing or need to be disputed/amended. However, it appears that there is no further detail defined within the Design Artefacts regarding how exactly these process steps would work, including amongst other things: • Timing/Operational Choreography – for example it is not clear exactly when losing and gaining suppliers would be expected to attempt to communicate with the meter, or the timescales for sending data obtained between suppliers. • Data to be included in messages – while BPM003C refers to the inclusion of ‘register readings’ in some of the messages it is not clear which registers should be included for smart meters and non-smart meters – for example whether that should just be the registers on a smart meter that the sending supplier uses for billing, or whether that should be all the 48 time of use registers stored on the smart meter. Additional input from Andrew Margan - Within the code workstream, we believe the Operational Choreography document needs to be updated to reflect SLAs. Without this, we can’t complete the Code drafting. If you disagree, we would appreciate an early heads up, so we don’t look disjointed in front of industry. |  | Closed | [5 empty] | This is not an MHHS Design Issue. D300 / Agree Reading SLAs are defined and set by RECCO. We have replicated the existing 5 day window for capture / submission of a reading(s) all other D300 timescales still apply as per RECC process. Register Readings can only be provided on the D0010 - where this is required [for smart meters] it would replicate the current as is process defined in the current DC BSCP | [8 empty] | 2023-07-14
MHHS-DIN-325 |  |  | 2023-05-24 | CGI |  | Dave Webster | Software Provider | Status Code Missing from MsgBody | In the SubmitEvents StandardResponseBodyType object (SubmitEvents ¦ 1.2 ¦ MHHSPROGRAMME ¦ SwaggerHub), it states that “statusCode” is a required field. Yet its’ definition does not exist in the properties of the object. StandardResponseBodyType: type: object properties: transactionID: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-014-DIPTransactionID' senderUniqueReference : $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-995-SenderUniqueReference' correlationId: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-011-CorrelationID' sentTimestamp: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-003-DateTime' senderId : # the sender of this message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' recipientID : # indended (logical) recipient of the message, i.e sender of the original event message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' DIPConnectionProviderId : # physical recipient of the message (if different to recipient Id) $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' message: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-005-StatusErrorMessage' help: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-019-HelpText' serviceTicketURL: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-018-URL' required: - transactionId - sentTimestamp - senderId - recipientId - statusCode - message - help - serviceTicketURL |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | This has now been updated in V1.2 of Swagger StatusCode Added to the ResponseBody. | Technical corrrection | Supporting Docs |  | JSON/YAML files | JSON/YAML files
MHHS-DIN-326 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Changes required to DES-138 / interface catalogue given changes in Migration Design e.g. the addition of interface IF003 and potentially ISD. |  | Closed | [5 empty] | Duplicate of 247 | No Change |  |  | None | None
MHHS-DIN-327 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | IF-005 User Guide | The IF005 User Guide explains how the IF005 should be populated. We have a request for clarification on whether the IF006 will be populated identically or if the Meter ID in the IF006 will reflect the Modified Meter Id in the IF005. Is IF-005 identical to IF-006, or is it with updated MTD's. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | IF-006 should be a facsimile of IF-005. In the case of change of MSN... MSN field will reference the (old) MSN and Modified MSN will be populated with new/revised MSN. All subsequent flows following the IF-006 will only reference the NEW/REVISED MSN. We further clarified this in a change to the Note(s) section on IF-006. | Data interface correction | Supporting Docs |  | DES138 | DES138 |  |  |  | 2023-06-16
MHHS-DIN-328 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | Operational Choreography Update: Addition of SLA for RS end appointment data to the CSS | The operational choreography does not include an SLA for the RS to send appointment data to the CSS or the timings by which the CSS and DSP should deliver their roles within the process. These need to be added to the operational choreography for clarity, noting the interaction with CR018. | CR018 | Closed | [5 empty] | RECCo confirmed closure of DIN following review of amendments to the Operational Choreography for CR018. ALL Updates between RS and CSS/DSP are existing interactions, covered by existig SLA's document in RECCO documentation. OPSC document was updated per Recco comment to highlight existing RECCO SLA in this area and to ensure primacy of the RECCO documented timings. | [8 empty] | 2023-07-14
MHHS-DIN-329 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Approach on a business rule where the ERDS does not send a MEM de appointment / appointment for an MHHS migration where the same MEM is being appointed under MHHS arrangements e.g. they have the same MPID. The expectation is that smart and advanced MEMs will use the M role code for the interaction with CSS so from their perspective there should be no change. |  | Closed | [5 empty] | ERDS Interfaces are ouf of scope of MHHS. If a change to ERDS interface is required or efficiencies in its existing operation are possible to align with MHHS Design - this would be a consquential change. | No Change | [7 empty] | 2023-07-14
MHHS-DIN-330 |  |  | 2023-05-25 | Ovo Energy | 5225 | David Morley | Supplier | Long Term Vacant | BSCP504 section 4.15.3 stipulates the criteria via which suppliers can classify sites as Long Term Vacant (LTV). BSCP701 stipulates actions that SDS shall take if the supplier nominates that a site is LTV. However, the criteria that suppliers shall use for classifying LTVs in MHHS is missing. Can you please signpost where the new criteria will be located? |  | Closed | [5 empty] | BSCP is responsible for revising the code specification, there are no changes to design specified. Code team will get in touch with the participant.
MHHS-DIN-331 |  |  | 2023-05-25 | MHHS | 4733 | Martin Freeman | Central Body | Secondary Routing | Secondary routing for IF-013 is specified as being conditional upon the value of DI-015. However, DI-015 (Connection Type Indicator) is a property of a repeating block, and there is no constraint in place to suggest that each element in the repeating block must have the same value for this (or any other) property, in which case multiple rules in the routing table could apply simultaneously. The routing table design seems to suggest that only a single rule should apply at a time and that routing should not be derived by blending multiple rules. If this is so, and a message is received where different elements in the B050 have a different Connection Type Indicator then there is no coherent way to implement this in conformance with the routing table. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Agree there was a routing contradiction for scenarios/periods where a different connection type was in effect. Interface notes section has been updated to direct the use of 'separate' IF-013 messages in such circumstances. Note also makes clear that repeating B050 blocks are acceptable where other elements (not Connection Type) of the CCC vary over the period to be defaulted. | Design Ambiguous | Supporting Docs | Default Consumption | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-332 |  |  | 2023-05-25 | MHHS | 4750 | Martin Freeman | Central Body | IF-013 Routing | In the routing table for IF-013 all rules are conditional upon S0.Eventcode == [ActivePowerDefaulted], which means that for IF-013 message where Eventcode == [ConsumptionOnDeEnergisedMPAN] there is no routing at all, which means when this message is sent to the DIP it will not be routed anywhere and will simply disappear. That's almost certainly an error. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Event code [ConsumptionReceivedonDeEnMPAN] has been moved from IF-013 to IF-014. The valid event code list and routing rules have now been updated for both interfaces to reflect the move. v1.2 of Swagger also updated to reflect this change Duplicate of DIN 255 | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-333 |  |  | 2023-05-25 | MHHS | 4760 | Martin Freeman | Central Body | Connection Type Required to Support Routing of IF-014 | All of the routing rules specified for IF-014 are conditional upon DI-015 (Connection Type Indicator). But IF-014 does not have any blocks with this property, which means this message won't get routed anywhere. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Block B067 - Connection Type Added to IF-014 in order to support routing requirements. Swagger v1.2 updated to reflect this change. (Duplicate of DIN256) | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-334 |  |  | 2023-05-25 | MHHS | 4766 | Martin Freeman | Central Body |  | The routing table for IF-018 specifies roles AMSC, UMSC, UMDC for Secondary routing. There are no such roles in either the DES138 nor the E2E001. |  | Closed | [5 empty] | Secondary Routing Review/Changes have superceded this issue - Ref DIN-268
MHHS-DIN-335 |  |  | 2023-05-26 | British Gas/Engage Consulting | 4640 | Neil Strange/ Haz Elmamoum | Consultancy | Four questions on IF004 | IF/PUB-004 – DIP Common Blocks referencing MHHSP-DES138-Interface Catalogue v5.1.1 As a minimum this needs to be referenced in the supplier requirements MHHSP-BRS004-Supplier Overview and MHHSP-BRS002-Metering Service requirements, but to ensure parties get sight of this we would suggest it needs to be included in a business process map and have associated requirements. For IF-004 to be useful to participants DI-999 – Event Code needs to be elaborated e.g. 1- Installation 2- Removal; 3- Exchange; 4 - Found (Where installed by Gas supplier and Elec Supplier takes ownership) C/M/O rules for DI-192, DI-193 and DI-194 need to be explained in the notes – presumably driven by event code Available is spelled incorrectly (available) for DI-192 and DI-194 there are a couple of angles here – 1) ensuring wider awareness and 2) it seems there is a question mark on the governance here as it is odd a flow has been added but industry does not appear to have been sighted on it especially with no associated referencing in artefacts and no process map, so effectively no one has any idea how it is supposed to be used. Although it was formally agreed not to include and use bilaterally....from a Large Supplier Constituency perspective, my members are keen to ensure design clarity and how flows are to be used or not, regardless of their ad-hoc / bilateral nature. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Updated BP009 Change of Metering to include the "optional" sending of IF-004 from MS via DIP to Supplier, if changes to Comms Hub need to be notified. Included same updated to BPD009 to reflect new BP steps. Other comments have been addressed previously and are reflected in DES138 IF-004 | Process Model correction | Meter to Bank | IF-004 | BP009 Change oF Metering BPD009 Change of Metering | BP009 Change oF Metering BPD009 Change of Metering |  |  |  | 2023-06-16
MHHS-DIN-336 |  |  | 2023-05-26 | MHHS |  | Rob Topley/ Zak Hussain | SI Design | Requirements clean up in iServer | Process Step No. BP Step ID Process Map wording Interface ID Sender Recipient/Service Traceability Requirement Traceability Method Statement iServer Requirement Name iServer Step name Issues Found BP01 170 BP01 - 170 Send Site Tech Details on Metering Service Request MHHS-RS-LD-012.1 #N/A LDSO170a Send Site Tech Details on Metering Service Request Missing (only on BPD and traceability matrix) BP01 175 BP01 - 175 Receive Site Technical Details D0215 LDSO Metering Services MHHS-RS-MS-037.1 #N/A MET175 Receive Site Technical Details Missing (only on BPD and traceability matrix) BP03B 95 BP03B - 95 Manage SP Appointment Amendment Request Response PUB-035 DIP Supplier MHHS-BR-SU-35.1 #N/A SUP095a - Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP03B 96 BP03B - 96 Manage SP Appointment Amendment Request Response PUB-035 DIP Data Services Metering Services MHHS-BR-DS-11.1 #N/A ESP96 – Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP05 315 BP05 - 315 Issue Reading Data MHHS-IF-041 Data Service DIP MHHS-BR-DS098.2 #N/A DAT315 – Issue Reading Data Missing (only on BPD and traceability matrix) BP05 340 BP05 - 340 Process Reading Data PUB-041 DIP Supplier MHHS-BR-SU047.1 #N/A SUP340 Process Reading Data Missing (only on BPD and traceability matrix) BP05 350 BP05 - 350 Process Reading Data PUB-041 DIP LDSO MHHS-BR-LD009.1 #N/A LDSO350 Process Reading Data Missing (only on BPD and traceability matrix) BP010D 1055 BP010D - 1055 Receive updated Legacy information PUB-026 DIP Central Settlements MHHS-BR-RD-018.1 #N/A ECS1055 Receive updated Legacy information Missing (only on BPD and traceability matrix) All these requirements don’t exist on any requirement catalogues, they’ve only ever been on a BPD document or the traceability matrix (which are essentially the same document). Also, the highlighted traceability has a typo and is on a requirements artefact but is wrong on both the BPD and traceability matrix. |  | Closed | [5 empty] | Requirements have been found in BRS001, BRS004, BRS005, BRS014. Models have the correct steps identified. Unable to identify whats missing, checking with the originator. Confirmed with originator no further changes needed | No Change | Supporting Docs | Supporting Docs | BRS001, BRS004, BRS005, BRS014 | BRS001, BRS004, BRS005, BRS014 |  |  |  | 2023-07-14
MHHS-DIN-337 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger alignment to DES-138 | R0 - Response Message Min length updated to align with DES-138 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated R0 - Response in Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-338 |  |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier | BP003/BP002 to be updated to clearly show IF-036 going to both Import & Export supplier | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. BP003/BP002 to be updated to clearly show IF-036 going to both Import & Export supplier |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | On an Export Supplier COS, the Service Providers will be de-appointed on notification of the Secured Active. As the Export Supplier is unable to appoint their own Service Providers (in the case of Linked Import/Export), the auto-aligmnment functionality (BP011C) will trigger the correct Service Providers to be appointed and the Service Providers will be notified of the Supplier in IF-036. However this DIN has highlighted the need for the export Supplier to be notified of the Service Provider changes. BP003/BP002 updated from Step 255/245 to re-label "PUB-36" flow to Step 260 for the Supplier (prospective/incumbent) to state "PUB-036 for Import & Export Supplier". Change is not reflected in the BPM-003 for forward migration as linkages only become active when both Import/Export are migrated. See also 339 | Process Model correction | MPAN Ownership | Process Models | BP003 BP002 | BP003 BP002 |  |  |  | 2023-07-14
MHHS-DIN-339 |  |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier | IF-001 to be updated to be additionally sent to the Export supplier rather than just the import | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. IF-001 to be updated to be additionally sent to the Export supplier rather than just the import |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | On an Export Supplier COS, the Service Providers will be de-appointed on notification of the Secured Active. As the Export Supplier is unable to appoint their own Service Providers (in the case of Linked Import/Export), the auto-aligmnment functionality (BP011C) will trigger the correct Service Providers to be appointed and the Service Providers will be notified of the Supplier in IF-036. However this DIN has highlighted the need for the export Supplier to be notified of a new Import Supplier. BP001 updated to re-label "PUB-001" flow for the Supplier (prospective/incumbent) to state "PUB-001 for Import & Export Supplier". See also 338 | Process Model correction | MPAN Ownership | Process Models | BP001 | BP001 |  |  |  | 2023-07-14
MHHS-DIN-340 |  |  | 2023-05-26 | UKPN | 4547 | Neal Medley | Network Operator | ELEX-REP-02/02A report | The reports ELEX-REP-02/02A will only contain aggregated data for A(General LLF Class Import and C (General LLF Class Export). The I/F021 can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/014 Rejected Consumption Data Submission and I/F MDS Defaults Applied to any I/F021 data to ensure you are not using rejected data or are missing I/F 021 data in respect of an MPAN. MDS Method Statement to be updated to reflect |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Updated the below test to Section D within MDS Method statement: 17.4 The I/F021 ‘UTC Settlement Period Consumption Data’ can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/F014 Rejected Consumption Data Submission and I/F ‘Notification of Defaulted UTC Settlement Period Consumption Data’ to any I/F021 data to ensure LDSO’s are not using rejected data or are missing I/F 021 data in respect of an MPAN. | Design Ambiguous | Supporting Docs | Method Statement | MDS Method Statement | MDS Method Statement |  |  |  | 2023-07-14
MHHS-DIN-341 |  |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | MUM Event not required by MDS | For IF-018 the event [MUMIndicator] is routed to MDS and indicates metered/unmetered. This event is not required by MDS as they can infer this from the Market Segment (Advanced, Smart and Unmetered). DIN raised to remove the routing |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | MDS Removed as Always Recipiant for Event [MUMIndicator] on IF-018 Routing rules | Data interface correction | Supporting Docs | IF-018 | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-342 |  |  | 2023-05-26 | UKPN | 5194 | Neal Medley | Network Operator | ELEX-REP-02/02A Consumption data clarification | The intent is that the daily volume on actuals or estimates are the sum of the appropriate consumption data. So when added together they should equal the summed Total of the Settlement Period data (Total Uncorrected Volume) barring any rounding errors. The data is given in MWh to six decimal places (i.e. to the nearest Watt hour). I assume DUoS billing only calculates to the nearest unit so would not expect any rounding errors to impact. The A flags are set out in the ELEX-REP-02/02A are the same as those set out in the CCC table in the VAS Method Statement which is also in the MDS Method Statement. I agree the list in the calculations only are missing the full list of SPQI that are deemed to be actuals as set out in the ELEX-REP-02/02A. DIN raised to correct the calculation |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Updated full list of actuals with the MDS Method Statement. The amended list added to the Method statement: A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6. | Method statement correction | Supporting Docs | Method Statement | MDS Method Statement | MDS Method Statement |  |  |  | 2023-07-14
MHHS-DIN-343 |  |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | Routing rules table | The routing rules on the IF-037 sheet state that MDS will 'always' receive the DSDeApp event code, however the 'Always' column on the IF_LIST does not state Central Settlements for MHHSP-IF-037. IF list needs updating to reflect that the DSDeApp event always routes to MDS |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Decision taken to remove Recipiants (COLs G,H &I) from the IF_list - as just duplication of information contained within each of the IF spreadsheets. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-06-16
MHHS-DIN-344 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B005 Custom Block update Swagger to align with DES-138. Current Metering Service MPID Length removed. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138. Current Metering Service MPID Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-345 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B024 Custom Block update Swagger to align with DES-138. DUOS Min Length removed. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138. DUOS Min Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-346 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design |  | IF-001 - B032 Custom Block update DES-138 to align with Swagger. Update DI-122 (Profile Class) to Integer from String-2. |  | Closed | [5 empty] | DI-122 remains as String 2 for Profile Class to support requirements for enumerations. | Data interface correction | Supporting Docs |  | None | None |  |  |  | 2023-06-16
MHHS-DIN-347 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B035 Custom Block - update Swagger to align with DES-138. Remove min length. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-348 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | IF002 correction | IF-002 - B074 Custom Block. Clarification on DI-091. DES-138 says this is 1 digit to the left of the decimal point. Swagger says 5 to 6. DES-138 to be updated to the correct value. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to be an Integer (1), Min of 1, Max of 1, example of 5. This now aligns with DES-138. | Data interface correction |  |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-349 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Correlation ID Issue IF-006 | Routing Rules in DES-138 do not always correctly identity where Correlation ID == Copy ie, it's missing for IF-005 / IF-006 so this needs to be updated correctly across all interfaces. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated IF-006/IF-008/IF-039/If-028/IF-026/IF-016 routing rules to show use of a "Copy" in Correlation ID (ie copied from the preceeding IF txn pairing) | Missing/incorrect validation rule | Supporting Docs |  | DES138 | DES138 |  |  |  | 2023-06-16
MHHS-DIN-350 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-005 B033 to align Swagger with DES-138 (Postcode removal, mandatory modified meter id) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Postcode removal, mandatory modified meter id) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-351 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B071 to align Swagger with DES-138 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-353 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B032 to align Swagger with DES-138 (SSC Min Length should be 4) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated SSC Min Length to be 4) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-354 |  |  | 2023-05-30 | SJW |  | Sarah Jones | Consultancy | Design team confirmation for sending of IF-037 and not IF-037 to losing MEM | Please see below details of a new design query related to the Registration Tranche of Code Drafting. We note that in BP011C there is a process whereby the Registration Service will auto de-appoint / appoint agents for secondary related metering points and linked export metering points as part of their validation. The business process only includes the sending of the IF037 to the Losing MEM and not the IF035. Please could you confirm that this is correct and that in this instance the Losing MEM would not receive an IF-035. If this is the case, we think there should be a change to Metering Service requirements MS-018 and 019 to clarify that where the Losing Metering Service receives an IF-037 with no preceding IF-035 then they should send the MTDs at this point. The alternative would be to include the sending of an IF-035 as well as an IF-037 accepting that these would arrive at a similar time. This would align to the process for managing retrospective MEM appointments where we understand that the Losing MEM would receive both the IF-035 and the IF-037. We also suggest amending MS-008, 008.1, 009 and 009.1 to recognise this nuance as follows: MSA/MSS must obtain Export MPAN de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. MSA/MSS should note this message will be automatically triggered when a change of Metering Service has successfully completed for the linked import MPAN or a new MPAN linkage has been put in place where the [linked import / primary related] MPAN has a different appointed Metering Service. Presumably there is a similar impact on the data service requirements that would need to be considered. |  | Closed | [5 empty] | Solution options discussed with SCS. Closed as covered under DIN 560 |  | Supporting Docs | [6 empty] | 2023-07-14
MHHS-DIN-355 |  | DI-179 | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Number of Register Digits | Revisit and confirm IF-005 Cumulative Digits validation rule against latest version of the CP |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | All instances of DI-091 (IF-002,IF005,IF-006,IF-033,IF-036) updated to reflect updated logic. IF-005 validation rules updated also to reflect new guidance. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-07-14
MHHS-DIN-356 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B073 - update Swagger to align with DES-138 (consumptionAmendmentSupplierReference max length) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated consumptionAmendmentSupplierReference max length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-357 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B902 - update Swagger to align with DES-138 (supplierConsumptionAmendmentRequests typo update) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated supplierConsumptionAmendmentRequests - remove typo) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-358 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-034 B070 - update Swagger to align with DES-138 (contractReferenceMeteringService max length 10) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated contractReferenceMeteringService max length 10) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-359 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: The method statement states that “The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN on notification of the set-up of that MPAN in MHHS-IF-001.” However, it will be the MHHS-IF-036 Registration Service Notification of Service Appointment & Supporting Info that will initially provide the fact that an MPAN has migrated to Central Settlements. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement updated with following text in red: 2.3 The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN within 30 calendar days following notification of the set-up of that MPAN in MHHS-IF-036 'Registration Service Notification of Service Appointment & Supporting information' or MHHS-IF-001 ‘Notification of change of Supplier’. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption | METH010_Annual_Consumption |  |  |  | 2023-07-14
MHHS-DIN-360 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: 3.3 Where a years’ worth of data, >=75% and <100% of actual UTC Period Consumption data (where Settlement Period Quality Indicator = A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6) has been used to calculate the Annual Consumption, the Annual Consumption Quality Indicator should be set to “1”. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement updated with following text in red: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption | METH010_Annual_Consumption |  |  |  | 2023-07-14
MHHS-DIN-361 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Greater than or equal to change for UTC Period Consumption Data | We need to raise a DIN on the AC method Statement and AC requirements: Likewise 3.6 needs to say greater than or equal to 182 days: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement updated with following text in red: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption | METH010_Annual_Consumption |  |  |  | 2023-07-14
MHHS-DIN-362 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Section Name change | Section 5 incorrectly named Section 6 needs to be updated: 6. Transition and Next steps |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Section 6 has been updated to Section 5 within AC Method Statement and old section 5.1The initial Annual Consumption calculation, as set out in section 3.7 above may change, depending on the consideration of the working groups during the MHHS Transition requirements work- has been removed | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption | METH010_Annual_Consumption |  |  |  | 2023-07-14
MHHS-DIN-363 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Load Shaping Service calculations | We may also need to document how this is calculated by the Load Shaping Service in the first year. I believe Helix have developed a calculation and this would need to go in the Load Shaping Method Statement and be referenced in the AC Method Statement. |  | Closed | [5 empty] | Kevin Spencer to arrange a session with Mike Ceney to discuss solution further. Upon further discussion with Kevin Spencer on 4/8/23 it was confirmed this DIN could be closed as the change is in relationn the AC Method Statement. No changes required to the LSS Method Statement | Method statement correction | Supporting Docs | Method Statement | Annual Consumption Meth 10 | Annual Consumption Meth 10 |  |  |  | 2023-07-14
MHHS-DIN-364 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-035 - B066 - mark as mandatory in Swagger as per DES-138 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated so B066 is a mandatory for IF-035 custom block) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-365 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-004 - B093 - update Swagger to align with DES-138 (min Length on commsHubGUID / GPF-GAS-GUID) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated min Length on commsHubGUID / GPF-GAS-GUID) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-366 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 custom block - SSC add min length to align with Swagger |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B032 custom block - SSC add min length to align with Swagger) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-367 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 Profile Class - updated Swagger to be a String to align with DES-138 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B032 Profile Class Swagger to be a String to align with DES-138) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-368 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-013 - B049 updated Swagger to align with DES-138 (run Number optional) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B049 Swagger to align with DES-138 (run Number now optional) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML | Swagger 1.2 and JSON/YAML |  |  |  | 2023-06-16
MHHS-DIN-369 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | Switch Cancellation Info Note | Update BP002/003 to add informational note that Registration Cancelations will be processed as soon as they are received by SCS from CSS i.e. Apps Lapsed through switch cancelation sent immediatly not held until Proposed App Date. Also updates to Forward Migration BP002/003 for consistency. Changes to OPC added the following words to OPC_190 in the Activity column (section 4.4) “(including Switch Status Updates e.g. Cancelled)” |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | BP-002/003 updated to include new informational Note in Supplier swimlane relating to CSS Switch Cancellations. OPC updated to make it clearer that Secured Active Processing includes Switch Status Update processing. to OPC_190 in the Activity column (section 4.4) “(including Switch Status Updates e.g. Cancelled)” | Process Model correction | MPAN Ownership |  | BP002, BP003, OPC001 Forward Migration BP002 & BP003 | BP002, BP003, OPC001 Forward Migration BP002 & BP003 |  |  |  | 2023-06-16
MHHS-DIN-370 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | IF-005 Update Window Guidance for Prev MS | Change IF-005 and Guidance Doc to allow Meter Updates within 10 day window for previous MS |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | New validation rule added to IF-005/MeterUpdate to allow previous MS to submit if within 10 day post appointment period. IF-005 User Guide section 9.3 updated to reflect same. | Missing/incorrect validation rule | Supporting Docs |  | DES138, IF-005 User Guide | DES138, IF-005 User Guide |  |  |  | 2023-06-16
MHHS-DIN-371 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team |  | Review design to ensure only Supression of IHD info for advanced segment and NOT "deactivation" of underlying IHD record. |  | Closed | [5 empty] | Confirmed that IHD details will be retained on Smart to Trad Exchange. Any IHD info present will be suppressed (ie not included in msg) if Segement is Advanced. No change required to documentation. Possible data cleanse issue - Dan T. to raise in Data Forum.
MHHS-DIN-372 |  |  | 2023-06-01 | MHHS | 5298 | Rob Golding | Central Body | Mapping Roles | There is a need to master the mapping of Market Participant Role to DIP Role within the MHHS solution. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New entity M18 created to show the DIP market roles. Minor corrections to M16 to clarify DIP ID field length. | Other | Supporting Docs | ISD Entities | MHHS-EDI-021-ISD_Entities | MHHS-EDI-021-ISD_Entities |  |  |  | 2023-07-14
MHHS-DIN-373 |  |  | 2023-06-02 | MHHS | 5272 | Rob Golding | Central Body |  | There is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 |  | Closed | [5 empty] | Duplicate of DIN-297
MHHS-DIN-374 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Message Replay & Requeue functionality | Message replay and requeue functionality needs to be added to the DIP API interfaces, which requires changes to the Swagger / YAML definitions. Detail is required in the E2E design documentation to explain how the message replay and requeue functionality will work. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updates to the E2E001 design document to provide detail on how the replay and requeue will work. There are updates to Swagger to support new interfaces for /dip-channel/{id}/replay and requeue respectively. There is also a new MessageRequest Schema that is used to pass data into both of these interfaces. To support these changes, section 4.8 has been updated in the E2E001. | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents | E2E001, Swagger 1.2 and associated JSON/YAML documents |  |  |  | 2023-06-16
MHHS-DIN-375 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Interface webhook configuration | Updates require to the pubconfig and webhook config to support per interface webhook configuration, alongside changes to support definition of recipient ID and role ID. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updates to the E2E001 design document to provide detail on how the webhook configuration will work, with information related to specific interface changes. There are updates to Swagger to support new interfaces for /dip-channel/{id}/pubconfig (POST and DELETE) respectively to support changes defined in the E2E001 (Section 4.5 and 4.5.1 and 4.5.2have been updated to provide more clarity / information). | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents | E2E001, Swagger 1.2 and associated JSON/YAML documents |  |  |  | 2023-06-16
MHHS-DIN-352 |  |  | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Obsfucation Text | What text should be used for data obfuscation ? for things like Boolean fields (True/false) |  | Closed | [5 empty] | Closed as this is already included in section 4.3.2 of the E2E001 design document. | [8 empty] | 2023-07-14
MHHS-DIN-376 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-099 changes required to ensure DES-138 displays the correct YAML name / Swagger aligns to this. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | "Register" spelling in name has been corrected in DI099, and DI-099 name correction for IF041 in DES138 | Data interface correction | Supporting Docs |  | DES138 | DES138 |  |  |  | 2023-06-16
MHHS-DIN-377 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-097 | DI-097 - In DES-138, this is defined as a string (2), but the existing data type is an Integer and this is an Integer enumeration. Need to update this to an Integer in both DES-138 and Swagger 1.2. |  | Closed | [5 empty] | Rejected / closed as enumeration of values requires string (2) therefore this is retained to support buisness requirements. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-378 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. This information has now been added to DES-138 5.2.1. | Data interface correction | Supporting Docs |  | DES138 | DES138 |  |  |  | 2023-06-16
MHHS-DIN-379 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-048 | DI-048 - clarity required on whether this is "meter manufacture make and type", rather than just "meter manufacturer". The first is an existing data type and links to the J number, so providing further clarity / rename would quickly ensure alignment in DES-138 and then subsequently in Swagger. |  | Closed | [5 empty] | Rejected / closed as this was discussed as part of previous work off items and description has previously been approved / accepted as Meter Manufacturer. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-380 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-052 | DI-052 in DES-138 currently has 4 enum values ie, - Active Import, Active Export, Reactive Import, Reactive Export. In MDD there are currently 38 options documented. Discussion around whether ISD Entity 47 should be referenced as the list of values allowed. This can then be aligned / referenced in other other documents ie, EMAR will reference ISD Entity 47. |  | Closed | [5 empty] | Rejected / closed as this was discussed as part of previous work off items. Only 4 values are required in MHHS / DIP, therefore only these values are referenced / used as part of the enumeration to avoid bringing data from existing systems into new systems when this is not required. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-381 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-842 | DI-842 - Confirmation that MDR's have DIP ID's? There has been discussion in various forums to understand whether they do and if not, then this data item needs to be removed in DES-138 and Swagger. |  | Closed | [5 empty] | Rejected / closed as MDR's do have DIP ID's, therefore this value will be retained. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-382 |  |  | 2023-05-06 | Design Team | 4570 | Neil Strange | Supplier | D0010 | In BP003C, at CoS traditional CoRs are transferred between suppliers via D0010. We believe this needs to be used for all meter types - as this will be needed for non-communicating smart and advanced meters – and BP003C needs to be amended accordingly. There is no mention of IF-041 and we do not believe that the DIP is expecting an IF/PUB-041 transaction between suppliers. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Supplier added as a Primary Recipient in the Routing Rules for IF-041 (DES138) - Supplier initiated Reads. Sending supplier would need to populate the DIP ID of Supplier(s) with whom he wished to share the reading. Working Group specifically decided not to discuss /include COR scenarios for Smart Metered Sites however this is not prevented by the Design - a note to this effect has been added to BP003C for clarity. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue BP-003C Transfer of Readings | MHHSP-DES138-Interface Catalogue BP-003C Transfer of Readings
MHHS-DIN-383 |  |  | 2023-06-07 | RECCO | 4558 | Sarah Jones | Central Body | Change of Segment Scenario | We cannot find anything in the design artefacts stating that the Metering Service is required to notify metering exchanges for change of segment within 2 WDs. We have found the following: MS-094: MSA/MSS must be able to publish Change of Segment Meter Exchange details and reads via the appropriate interfaces, where it is not formally appointed as the Metering Service but does have an accepted prospective appointment (Appointment Scenario = "SEG"). The MSA/MSS must issue the work update to Registration at the earliest opportunity but within [x] days of completion at the latest. OPC 240: Notification of works to be completed by D+3 Working Days (This should provide time for consumption to be provided using new MTDs ahead of the SF run.) The BP011 references the connection type update being provided by LDSOs within 2 WDs. There is no equivalent for metering updates. Will require DRG confirmation on if the 'x' should be 2 or 3 working days |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Updates to be made inline with DRG recommendation to reflect 3 working days | Process Model correction | Supporting Docs | Business Process Documentation | BP011 - Change of Segment DES138-Interface Doc BRS002- Metering Service Requirements BRS003 - Registration Service Requirements BRS005 - LDSO Overview OPC001 - Operational Choreography MHHSP-DES229-IF005_UseCaseguide | BP011 - Change of Segment DES138-Interface Doc BRS002- Metering Service Requirements BRS003 - Registration Service Requirements BRS005 - LDSO Overview OPC001 - Operational Choreography MHHSP-DES229-IF005_UseCaseguide |  |  |  | 2023-07-14
MHHS-DIN-384 |  | DI-174 | 2023-06-07 | St Clements | 4938 | Madison Layton | Software Provider | IF-038 and IF-039 blocks not the same | Block B020, B021 are not the same across interface IF-038 and IF-039. DI-140 and DI-138 (SP DIP ID) are in IF-039 but not in IF-038. Understanding was that with the DIP change that all data items in block are mandatory, the blocks were to be consistently defined across all interfaces. If extra DIP ID DI-138 and DI-140 data items are included in IF-038 then we need a new REG rejection code to allow us to reject where DIP ID is not the same as the sender DIP ID. Alternative is to separate the DI-140/DI-138 into their own blocks included on the IF-039 interface only. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Block data items were aligned in release 2. New validation rule on IF-38 add to ensure that Sender ID matches MS/DS CDC ID. New Error code REG1076 added to support validation rule. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue |  |  |  | 2023-07-14
MHHS-DIN-385 |  |  | 2023-06-07 | Design Team |  | Steve Weston | SI Design | Correlation ID | S1 Common Block - Correlation ID is mandatory in Swagger, but Optional in DES-138. Swagger should be updated to align. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated S1 Common Block, Sender Correlation ID in Swagger, as this is Optional in DES-138 to support business process and requirements. | Technical corrrection | Supporting Docs |  | JSON/YAML documents | JSON/YAML documents |  |  |  | 2023-06-16
MHHS-DIN-386 |  | DI-179 | 2023-06-07 | St Clements | 5258 | Madison Layton | Software Provider | Register Digits | REC Change R0102 has been approved by industry to amend the number of display digits validation Where the Meter Type is S1 the Number of Displayed Register Digits value must be either 6 or 5 Where the Meter Type is S2A, S2AD, S2ADE, 2ADF, 2ADEF, 2AEF, 2AF, S2B, S2BD, S2BDE, 2BF,2BDF, 2BDEF or 2BEF the value must be “5”. Where the Meter Type is prefixed with “S2C” the value must be “6”. Where the Meter Type is 2CDEF, 2CF, 2CDF or 2CEF the value must be “6” REG1097 validation on the IF-005 needs correcting with this change, and the population notes for data item DI-091 across multiple interfaces also needs correcting |  | Closed | [5 empty] | Duplicate of Register Digit DIN-355 listed above | Data interface correction | Supporting Docs | Interface Catalogue | Lis | Lis
MHHS-DIN-387 |  | DI-180 | 2023-06-09 | St Clements | 5269 | Madison Layton | Software Provider | Uplift metered indicator requirements | There are elements in the requirements that suggest that metered indicator would trigger a change to Market Segment. E.g. MHHSP-BP011-Change of ConType andor Mkt Segment-v5.1 Step 102 MHHSP-BPD011 - Change of Con Type or Market Segment v5.0 Step 102 Which states if there is a change to market segment RS would need to re-evaluate the market segment And MHHS-BR-RS-124 which include in brackets: Change of Connection Type (Change of Unmetered Indicator) MPRS will assess Market Segment against the ISD entity M7 which does not include Metered Indicator. Therefore a change in Metered Indicator in isolation of any other changes to data items in the M7 table/Related MPANs/Linked MPANs, will not trigger a change to Market Segment. As it will not trigger a change MPRS will not re-evaluate Market Segment base on a Metered Indicator change alone. The requirements need uplifting to reflect. |  | Closed | [5 empty] | Closed as discussed and agreed with SCS. | No Change
MHHS-DIN-388 |  |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | IF-036 Custom Routing Rules | Following discussions with SCS agreed that for reasons of complexity it would be better to adopt Primary rather than secondary routing to IF-036. New Requirement created for REGS to undertake the Primary Routing of IF-036. |  | Closed | [5 empty] | Ref DIN-507
MHHS-DIN-389 |  |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | Appointment Start Times | Do we need a formal validation Rule to check that Appointment Start times are referenced as Midnight Local ? Issue raised numerous times with SCS. Waiting for SCS to confirm their position. |  | Closed | [5 empty] | CLOSED - DUPLICATE OF DIN-207 ABOVE
MHHS-DIN-390 |  |  | 2023-06-13 | Siemens | 5534 | Tony Mason | Metering Service Provider | IF/PUB-018 | There appears an inconsistency in the Business Process Map, BP010, and the routing rules for the IF-018 where the Event Code = DUOSTariffIDChg. This information is confirmed to SPs on the IF/PUB-036 and would then be updated where there is a change on the 018 according to the Secondary Routing Rules. This notification is absent on the process diagram. Could you confirm the position and update the documentation accordingly? |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Update BP010B to show Data Service and Metering Service receiving PUB-018 for DUoS Tariff ID updates in line with the routing rules in DES-138. Update BPD010 process description to includes steps to recieve PUB-018 for Data Service and Metering Service. | Process Model correction | Meter to Bank | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010 | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-391 |  | DI-182 | 2023-06-13 | St Clements | 5304 | Madison Layton | Software Provider | IF-019 validation gap on principal and subsidiary MPAN | IF-019 is missing validation rules to ensure an MPAN is only listed once in the IF-019, need rules to ensure the sender cannot repeat same Subsidiary MPAN twice in the repeating B090 block, and cannot list the same MPAN as both Principal and Subsidiary in the same IF-019 message |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Created x2 new rules to prevent duplicate MPANS within repeating B90 groups within a single message. Error Code REG1059 created to support validation checks | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-392 |  |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Consent Fields | Raised by SCS. B068/DI-017/DI-018 - This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block B068 updated to be "must be provided" for smart meters. Data items set to mandatory non-nullable. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Block text updated to show mandatory if smart meter present, and DI-017/D-018 updated to be mandatory non-nullable (applies to IF-026 only) | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-393 |  | DI-181 | 2023-06-13 | St Clements | 5274 | Madison Layton | Software Provider | De-appointment and re-appointment date order | MHHS-BR-RS-128.4 & MHHS-BR-RS-128.5 covers the requirement for MPRS to ensure MS/DS are aligned across Related/Linked MPANS, and where they are not to de-appoint the MS/DS and appoint the correct MS/DS. The de-appointment requirement specifies to set MS/DS ETD to D+1 and the appointment to set the MS/DS EFD to D+2. Why do we need to apply the de-appointment and re-appointment in the future? Would we not be better to use the previous day (D-1) for the de-appointment MS/DS ETD and the current day (D) for the appointment EFD? |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Discussed with SCS and agreed to update Registration Service requirements to De-appoint on D (MHHS-BR-RS-128.4) and appoint on D+1 (MHHS-BR-RS-128.5) as part of auto-alignment process | Requirement correction | Registration | Auto-alignment | BRS003 | BRS003
MHHS-DIN-394 |  |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Annual Consumption Fields | Raised by SCS. B059/B027/DI-0148 This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block updated to be "must be provided" if available, however data items now need to be set to mandatory non-nullable. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-0148 updated to be mandatory no-nulls and data type updated to DT-016 in Data Catalogue. Data Type corrected to DT-016 in IF-002 and IF-036. | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-395 |  |  | 2023-06-13 | St Clements | 5510 | Vicki Holland | Software Provider | Obfuscation of Connection Type Indicator in IF-021 | The DES138 interface catalogue specifies that the data item Connection Type Indicator will be obfuscated for all parties as it is required for routing only. Can this please be changed so that it is visible? The reason for this request is that suppliers often process data differently for the different connection types and therefore its important that they can internally validate or route data according to the connection type of the MPAN. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Obfuscation of connection type removed from IF-021/IF-013 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-396 |  | DI-183 | 2023-06-13 | St Clements | 5305 | Madison Layton | Software Provider | Update IF-019 REG1001 to only apply to Create and Add event codes | IF-019 REG1001 rule applies to all event codes. The MPAN could be disconnected with linkages still in place. If REG1001 is applied on remove event codes, then there will be not means by which the Supplier/DNO can remove the linkage after a disconnection. Suggest REG1001 rule should only apply to the Create and Add event codes. This would be consistent with the existing validation on the DB05 and D0386. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF-019 MPAN Status Validation Rule removed for all "Remove MPAN" Event Codes. i.e. I can still perform remove MPAN from group task if MPAN is disconnected. SCS rejected option of auto de-linkage as part of De-Registration Process. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-397 |  | DI-184 | 2023-06-13 | St Clements | 5306 | Madison Layton | Software Provider | IF-019: REG0007 to only apply to Related event codes and not to Linked Import Export event codes | REG0007 on IF-019 interface is currently written to apply to both Related and Linked MPANs. The intention of this existing rule on D0386 is because Related MPANs switch together, and so changing the relationship during a switch can create a split supply relationship. However Linked MPANs do not switch together and so this is not currently applied to the existing DB05 validation rules. Suggest REG0007 only apply to Related event codes and not to Linked Import Export event codes? |  | Closed | [5 empty] | Following discussions with SCS it has been agreed to prevent all changes to MPAN Linkages whilst an Active Switch is in progress. This is the safest approach when considering both CSS and Auto Alighment functionality considerations. No change to existing Design Documentation required.
MHHS-DIN-398 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD Stores LLF data | Can we have an ISD entity ID for LLF data. This would be required for the API used to retrive the data from ISD data store. Are you happy for us to create and put it in the Guidance note. |  | Closed
MHHS-DIN-399 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD publishes full data to Elexon Central Systems | Requirement should be reworded to be "ISD must make available the data sets required by LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. ISD must make available the entire current data set to LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. |  | Closed | [5 empty] | Agreed in a session with Elexon 26/07 that the requirements document will not be changed as the requirement has already been fufilled by Elexon in line with the current requirement.
MHHS-DIN-400 |  |  | 2023-06-14 | SRO Design Team | N/A | Sean Cooper | SEO Design | REGS Validation Rule Clarification | REG1089 conditions updated to provide more clarity. Existing wording refered only to a Subsequent App - this is now better defined as an Appointment with a prior/earlier Sender Timestamp. No functional change. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | For IF-031 Validation rule text updated to specifically reference Sender TimeStamps so as to provide more clarity on the nature of the val rule/when generated | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-401 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | IHD/SMSO Fields | IHD Install Status and IHD Status Effective from Date fields should be optional (i.e. nullable) when providing an IHD update in IF-025/IF-026. SMSO and SMSO Effective from Date fields should be optional (i.e. nullable) when providing an SMSO update in IF-025/IF-026. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-137/ DI-136 in block B030 updated to Optional (O) in IF-025 and IF-026 DI-134/ DI-135 in block B031 updated to Optional (O) in IF-025 and IF-026 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-402 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Import/Export Fields | Linked Import/Export MPAN and Linked MPAN Energy Direction will always be provided so should not be nullable |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-038 updated to Mandatory No nulls and Data Type updated to DT-002 DI-151 updated to Mandatory No nulls On the 01-Data Catalogue | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-403 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Meter Manufacturer Field | Meter Manufacturer is optional (ie nullable) when provided in IF-002, IF-006, IF-033, IF-036 as in IF-005 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-048 updated to Optional (O) in IF-002, IF-006, IF-033, IF-036 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-404 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Proposed Appointment Response Code Field | For Response code A there may not be any text to populate for DI-143 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-143 updated to conditional (C) based on DI-979 = L or R in block B007 in IF-034 and IF-035 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-405 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Response Message Field | For Response code A no text to populate for DI-980 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-980 updated to conditional (C) based on DI-979 = R in block R0 in 02-DIP Common Block tab | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-406 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Sender DIP ID Field | Sender DIP ID should always be provided in S1 Common Block |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-997 updated to mandatory (M) in block S1 in 02- DIP - Common Block tab | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-407 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | COS During SEG Issue | Discuss with SCS the option of allowing non-appointed MS to update MTDs even if App has lapsed due to COS activity. If not then need to update process map to call out need for manual exchange of MTDs as Work MS could never submit if IF005 |  | Closed | [5 empty] | Closed, SCS unable to support alternative solution. Design Team have reviewed the existing process map note and believe this already provides enough information for participants. | No Change
MHHS-DIN-408 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD is the master for data contained both within ISD and MDD during Transition | The requirement is a bit ambiguous as could be read as all ISD and all MDD rather than just ISD data + overlapping MDD data. We don't want to be the master for MDD only data |  | Closed
MHHS-DIN-409 |  |  | 2023-06-14 | St Clements | 5510 | Vicki Holland | Software Provider | ISD Entity M5 – Consumption Component Classes | EDI021 ISD entities document shows that the settlement period quality indicator in entity M5 is a comma separated list of possible values. This will be difficult to use in systems that need to refer to this data. Could this instead show Actual or Estimate? Alternatively could this be split into parent and child entities to avoid a comma separated list? Metering Service ID MPID is incorrect and must be changed to {MS Id} also in ISD Entity M8 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Amendments relating to “Valid Settlement Period Quality Indicator Set” wording and field length in section M5 of EDI021 ISD entities document. Change also made from Metering Service ID MPID to Metering Service {MS Id} in Entitiy M8. An objection was raised against this DIN. Following discussion at the DRG about this DIN it has now been moved to Interim Release 5. A decision was made at DRG to go with OPTION 2: Change Existing Layout – Remove list element in favour of individual row(s) for each valid combination for the Valid Settlement Period Quality Indicator Set. Option 2 changes have been implemented to section M5 of EDI021 ISD Entities. Following the change to the layout the amendments to the data item will revert back to its initial name of Settlement Period Quality Indicator. and a data type length of 5 characters | EDI021 ISD Entities | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-410 |  | DI-487 | 2023-06-14 | St Clements | 5542 | Virginia Patey | Software Provider | DI-487 definition incorrect for REP-002 on Swagger | DI-487 energised MPANs is defined as an Integer in the Interface Specification, yet is defined as a String in Swagger. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-487 updated in Swagger 1.2 to align with Interface specification for REP-002 | Data interface correction | Supporting Docs |  | Swagger 1.2 | Swagger 1.2
MHHS-DIN-411 |  | Migration | 2023-06-14 | ESG | 4810 | Patricia Parker | Software Provider | Migration Segment Categorisation | The Migration Design currently specifies that Market Segment needs to be recorded before the Migration phase. This should be changed so that it is no longer required. Until an MPAN is migrated, there is no way of maintaining the market segment between the RS and EES using the legacy interface between these two services. However, meter type and connection type will be available in both the EES and the RS, so Suppliers can use a combination of these values to derive the correct market segment. |  | Closed | [5 empty] | 03/08: SCS confirmed in a session with SC that they agreed that Segment is a derived value based on Connection Type and MTR. There are validation rules that prevent the migration if Connection Type (and therefore segment) is not already defined in REGS. To address the original question Segment will always be known at the point of migration. Therefore, no changes are required to Migration document. 13/07: John Wiggins to have offline discussion with Sean C as DIN requires wider discussion at DRG to progress SRO Team disagree with this Migration Request. Market Segment must be known prior to the selection of MHHS Service Providers. Market Segment is a derived field based on Connection Type and Meter Type. Connection Type must be set before Migration / Meter Type already known so Market Segement CAN be derived, set and maintained prior to MPAN migration. No change to baseline documentation Required.
MHHS-DIN-412 |  |  | 2023-06-14 | MHHS | 5022 | John Wiggins | Central Body | Update to MDD | Migration request to ensure that Elexon add MHHS as a value to MDD. Page 35 of the Design Document under Reverse Migration states that -A default MPID of ‘MHHS’ will be created for the DC, MOP, DA appointments. Will MHHS be contained within MDD as a valid set as there is no reference in the document to update MDD with this value. |  | Closed | Design gap | TBC |  |  |  | As the Migration documentation was approved via DAG and following discusion with RecCo and BSC the updates are being documented in. This is being picked up in an update to DES196 Dflow interface |  |  |  | DES196
MHHS-DIN-413 |  | Migration | 2023-06-14 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | Reading Type (J0171) will be updated with three new values: Forward Migration CoA Forward Migration CoS Reverse Migration CoS Reading Type (J0171) will no longer use Initial or Final for migration reads between Suppliers or DC/DS but one of the above new codes will be used. Meter Reading Reason Code (J0332) will no longer be used to identify migration reads, all reference to this will be amended to Reading Type (J0171) in the guidance document. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | This DIN replaces DIN-442. Introduction of a new worksheet called 'Migration Change' reflecting the D-Flows changes supporting migration. Reading Type (J0171) has three new Reading Type values as follows: V - Forward Migration CoA X - Forward Migration CoS Y - Reverse Migration CoS For the other part of the DIN, "Reading Type (J0171) will no longer use Initial or Final for migration reads between Suppliers or DC/DS but one of the above new codes will be used." - This already exists in the Migration documentation therefore no change on this. | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping | DES196 D-Flow and interface mapping
MHHS-DIN-414 |  |  | 2023-06-14 | British Gas |  | Mohammad Amin Fuggawala | Supplier | D0275 in D-Flow Document | Ref Previous DIN-244. In the "DES196 D-Flow Document" the D0275 is showing as redundant. This is misleading it should be marked as by agreement between contracting Supplier-DS. Document should be updated to reflect this. |  | Closed | [5 empty] | Centrica have been notified on closure of DIN. Update was delivered in the published V1.0 of DES-196 as part of July DAG and the updated version is available on the Collaboration Base. | No Change
MHHS-DIN-415 | RT |  | 2023-06-14 | Elexon | 5702 | Mike Ceney | Central Body | Routing IF-026 to LSS | IF_026- For Routing Rules it states for Event Code/Conditions [SSC], [ProfileClass] and [SSCandProfileClass] that this should be routed to MDS, is this incorrect as MDS does not use these items in any calculations or outputs, this should state LSS |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | IF-026 [SSC] and [ProfileClass] have been removed as of Interim Release 1. Update DES138 IF-026 to route to LSS on event [SSCandProfileClassChange] | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-416 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-001 New App Scenario Code MCS (Migration Change of Supplier) | Create new Appointment Scenario Code of MCS |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF -031 New valued added to DI-800 data catalogue and Swagger 1.3 updated to reflect new value | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-417 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-002 Validation Rules for Scenario MCS (Migration Change of Supplier) | New Val rule to check MCS is only used for legacy non-migrated MPAN where Supplier is not current supplier (and not in past) |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-418 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-003 New App Scenario Code MCA (Migration Change of Agent [Service Provider]) | Create new Appointment Scenario Code of MCA |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF-031 New valued added to DI-800 data catalogue and Swagger 1.3 updated to reflect new value | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-419 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-004 Validation Rules for Scenario MCA (Migration Change of Agent [Service Provider]) | New Val rule to check MCA is only used for legacy non-migrated MPAN where Supplier is current supplier and now active Switch is in progress (and not in past) |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-420 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-005 - IF-31 Check valid MHHS Supplier | If MCS/MCA code used is Supplier a valid MHHS Approved/Registered Supplier |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-421 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-006 - Prevent use of Migration Scenario IDs | IF MCS/MCA code used for already migrated mpan - reject appointment for invalid Scenario code(s) |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-422 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-007 Connection Type/Segment not yet Populated | New error required if Connection Type, DUos Tariff ID or Segment is not set prior to migration. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Validation Rule created for IF-031 to check that MHHS Standing Data is present and aligned. REG0011 Error created to support this validation Rule. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-423 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-008 Auto Realign Functionality | New REGS Requirement - Only action the auto-realign functionality on MPANs where both Linked MPANs are in a Migrated state. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Req RS-146 added to REGS Requirements Document to ensure that Auto-Align functionality is only executed if all MPANs in a related and/or linked group have sucessfully migrated to MHHS Operation. | Requirement correction | Meter to Bank | Requirements Documents | BRS-003-Registration Service Requirements | BRS-003-Registration Service Requirements
MHHS-DIN-424 |  | DI-185 | 2023-06-16 | St Clements | 5335 | Madison Layton | Software Provider | MPRS access to correlation ID | IF-019 is sent to the LDSO for LinkedImportExport event codes, if the LDSO approves the request they will submit an existing DB05 flow into MPRS. If the DB05 is accepted by MPRS, it will send an IF-020 to the Supplier to confirm the change to Linked Import Export association. However MPRS would not have access to the correlation ID that was received by the LDSO on the IF-019, and so would use a new correlation ID on the IF-020. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF20/IF19 Note amended explaining that it will not be possible to Link IF-019/IF020 messages together using Correlation ID , in the case of Linked MPANs. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-425 | SC | Migration | 2023-06-19 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | 8.1.3 step 12 Migration Design Document : Validation Status (J0022) references will be updated to Meter Reading Flag (J0045) |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | 8.1.3 step 12 Migration Design Document : Validation Status (J0022) references will be updated to Meter Reading Flag to T or F (J0045) | Design Ambiguous | Supporting Docs | Interfaces | Migration Design Document | Migration Design Document
MHHS-DIN-426 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG-009 New Rejection Code for D0205/D0203 | Response to a D205 is a D0203. 1. A New Rejection Condition/Code is required where D0205 is received following processing of IF-031. 2. Proposed new D0203rejection code is 62 "MHHS Fwd Migration in Progress or Completed" |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Point 1 already exists in the Migration documentation therefore no change on this. Point 2 is satisfied by updates in DES-196. Introduction of a new worksheet called 'Migration Change' reflecting D-Flows supporting migration. (J0107) Rejection Reason Code 62 added with the following details "MHHS Fwd Migration in Progress or Completed" | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping | DES196 D-Flow and interface mapping
MHHS-DIN-427 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-010 ISD Change M16 | No change Required - SCS can use ISD M16 - which contains MIPD/DIP Role and Effctive From date. This can be used to determine if a Supplier is MHHS qualified. This is better apporach that adding a transiant "Qualified Yes/No" field to this table. Therefore NO changes to documentation required. |  | Closed
MHHS-DIN-428 |  |  | 2023-06-19 | British Gas | 5835 | Neil Strange | Supplier | MEX before SSD scenario | When a CoS is in progress and there is a MEX before SSD, how will new supplier get the MEX details As the incoming supplier has already received the IF36 - would there be a new IF36 or would it be a PUB006? In addition how would the new MS and DS be made aware of this? - the old MS has X days after the job is completed to update the industry and a CoS could have happened before the old MS can update the other participants. |  | Closed | [5 empty] | BAU Design deals with 'regular' MEX before COS type scenarios (note previous MS Update Period - PUB-006 would be issued to impacted parties). Complexity arises where there is a COS overlapiing with Change of Segment/Connection Type (ie SEG Appointment)... Following discussion with SCS - low probably, low occurance vs. complex change. Ref existing guidance on BP016 there would need to be a manual interaction between Supplier and MS. No Change to existing Documentation Required.
MHHS-DIN-429 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG-011 Changes to D0170 | 1. Change D0170 flow so that MPRS/Registration Service is valid Sender of this flow. 2. New value for "Request Action Code" is needed to denote a Migrating account and if its CoS or ChgOfSP method. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Introduction of a new worksheet called 'Migration Change' reflecting the D-Flows changes supporting migration added in DES-196. Point 1. D-Flow ID (D0170) Request for Metering System Related Details new Scenario Variant FROM Electricity Retail Data Agent TO Electricity Supplier added. Point 2. Introduce two new Requested Action Code values as follows: 24 - Migrated Metering Point (CoA) 25 - Migrated Metering Point (CoS) | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping | DES196 D-Flow and interface mapping
MHHS-DIN-430 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-12 New Val Rule for IF-019 | Reject any changes to Related MPANs where any MPAN referenced (or in realted group) is subject to an active Migration SP Appointment Process |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Validation Rules and Error Code created to prevent changes if MCA Appointment Type Exists (Note: prevention if MCS exists is realised through existing check on if Switch is in Progress) | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-431 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-13 Change to D0386 | Change D0386 validation to reject changes to related MPANs if any related MPAN in group is subject to active Migration SP Appointment Process |  | Closed | Design gap | TBC |  |  |  | Update Migration Design Document D0386 validation to reject changes to related MPANs if any related MPAN in group is subject to active Migration SP Appointment Process | Design Ambiguous | Supporting Docs | Interfaces | Migration Design Document | Migration Design Document
MHHS-DIN-432 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-014 Appointment on Secondary Related MPAN | Extend existing 1039 check to include MCS.MCA Appointment Scenarios. |  | Closed | [5 empty] | Existing Validation Rule(s) around REG1039 will already cover Migrating MPANs - No Documentation Change Required.
MHHS-DIN-433 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-015 Switch in Progress Mig Rejection | New IF-031 validation to reject MCA/MCS DS and MS Appointments if an [any] active Switch is in progress with NEW Rejection Reason Code (note 1095 code referenced in Migration document has already been used elsewhere) |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New validation rules and REG9XXX Exception codes added to ensure correct usage of MCA/MCS Appointment Scenario Codes. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-434 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-016 New IF-003 | Previously DIN-247, Introduce IF-003, no changes from original proposal. 1. Update DES138 new tab, update IF List. Update New Data Items 2. Review E2E doc. 3. Update secondary Routing Rules (Avenade Techncal Doc) to include 4. Update Swagger |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Add data items DES138-Interface data Cat and to IF-003. Created new Data items: DI-500 MHHS Regime End Date, DI-501 Rev Migration Incoming MOP MPID, DI-502, Rev Migration Incoming MOP Eff From Date, DI-503, Rev Migration Incoming DC MPID DI-504 Rev Migration Incoming DC Eff From Date. Swagger v1.3 updated to reflect new IF-003, Blocks (B096/B095/B094) & Data Items (as above). | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-435 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG-017 D0304 & D0303 | 1. New D0304 Validation Rule 2. New D0304 Rejection Reason Code "Q - MPAN Fwd migration in progress or completed" 3. Change D0303 so as to make "Eff From Settlement Date REGI" a non mandatory data item within the flow (an alternative to suggesting that outgoing MS no longer issues a D303, only the incoming MS would send) |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Introduction of a new worksheet called 'Migration Change' reflecting the D-Flows changes supporting migration added in DES-196. Point 1 already exists in the Migration documentation therefore no change on this. Point 2 New Response Code Q "MPAN Fwd migration in progress or completed" added against J2255 MPAS D0304 Response Code as part of D0304. Point 3 Change requirement to populate this date from Mandatory to Optional against J0049 Effective from Settlement Date {REGI} as part of D0303. | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping | DES196 D-Flow and interface mapping
MHHS-DIN-436 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG0-018 D312 | 1. New D03012 Validation Rule 2. New Rejection Reason Code "AD - MPAN Fwd migration in progress or completed" |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Point 1 already exists in the Migration documentation therefore no change on this. Point 2 is satisfied by DES-196. Introduction of a new worksheet called 'Migration Change' reflecting D-Flows supporting migration. against J2256 MOP Flow Response Code as part of D0312 | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping | DES196 D-Flow and interface mapping
MHHS-DIN-437 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-019 IF-005 Validation Rule | 1. New val rule to prevent IF-005 while MCS/MCA Appointment is in progress 2. New Error Code (REG9003) |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | REG9003 - MHHS MTD Updates cannot be used until Migration has completed, Created and new validation rule added to IF-005 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-438 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-020 REGS Design Clarification | SCS Should issue L1/L2 Msg Status message with RCP1061 for any MPAN at the incorrect status where a DIP Message is received |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | This is a Migration Requirment which participants should take into account as part of their Migration Designs. However, for clarity a note has been added to RCP1061 entry in the Intoduction Section of the Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-439 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-021 No Supplier Updates during Rev MIgration (IF-025) | 1. New If-025 val rule to check if Rev Migration Switch is in progress 2. New error code |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | REG9002 - Supplier Data Items Cannot be Maintained for Reverse Migration Account, Created and applied to IF-025 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-440 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-022 No CDCs Updates during Rev MIgration (IF-038) | 1. New If-038 val rule to check if Rev Migration Switch is in progress 2. New error code |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | "REG9001 - CDC Marker Cannot be applied to Reverse Migration Account", created and applied to IF-038. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-441 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-023 No AC Updates during Rev MIgration (IF-040) | 1. New If-040 val rule to check if Rev Migration Switch is in progress 2. New error code |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement section 5 has been updated with the text below in red: Where an MPAN is no longer active under MHHS during the transition phase the Market-wide Data Service shall not calculate or submit an annual consumption on the IF/PUB-040. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption | METH010_Annual_Consumption
MHHS-DIN-442 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-024 D0010/D0086 New MR Reason Codes | Three new MR Reason Codes for use in D0010: Forward Migration COS / Forward Migration COA / Reverse Migration |  | Closed | [5 empty] | Original migration design. Superceded by DIN-413.
MHHS-DIN-443 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG-025 D0155 New Agent App Reason Codes | 1. New Valid value for service reference "REVM" 2. New valid value for Service Level "REVM" |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | D-Flow Ref D0155 updated for data items J0274 service reference "REVM" and J0275 Service Level "REVM" in DES-196. | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping | DES196 D-Flow and interface mapping
MHHS-DIN-444 | RS |  | 2023-06-19 | ESG |  | Patricia Parker | Software Provider | IF-01 Incoming supplier for Import/Export MPANs | Clarification required with SCS. If it is known that an alternative MPAN has the same SSD then we do not want the old supplier ID as the linked supplier on the IF-01, we want the new supplier to be populated |  | Closed | [5 empty] | Discussed with SCS and they have confirmed that where co-incidnet COS occurs they would look to populate the [new/incoming] Linked Supplier ID.... No change to documentation required.
MHHS-DIN-445 | SB |  | 2023-06-19 | Utiliteam |  | Richard Palmer | Software Provider | Spec of IF-024 in DES138 Interface Catalogue | The Population Notes for DI D-000 in Group S0 has ‘IF-025’. This error was in v5.0, and is still in v5.1.1 |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | The Population Notes for DI D-000 in Group S0 has been updated to ‘IF-024’ in IF-024. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-446 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-026 Migration DIP Reporting Reqs | Reqs for x4 new Reports -- Flag at the next DIP DAG |  | Closed | [5 empty] | Closed and for the Migration Team to pick up. Awaiting further internal discussions re DIP Reporting Strategy.
MHHS-DIN-447 | SW |  | 2023-06-21 | Kraken | 5980 | Angelos Rizoyannis | Software Provider | Conditional Mandatory not applied in Swagger correctly | IF-041-CustomBlock: The field B065List is stated as optional in the comments, but the API schema does not reflect this. This field that is conditionally optional in DES-138, but this is not defined as such in Swagger ie, OneOf, AnyOf. This needs to be updated in Swagger to align correctly. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | In Swagger 1.3, updated IF-041-CustomBlock: The field B065List and B064List will be either / or as they are defined as conditionally mandatory in DES-138. This uses AnyOf notation in Swagger. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3 | Swagger 1.3
MHHS-DIN-448 | SW |  | 2023-06-21 | Kraken | 5980 | Angelos Rizoyannis | Software Provider | Mandatory fields not applied correctly in S1 block | S1 Common Block: The 'properties' and 'required' sections of the API schema for the S1 common block have conflicting information. The 'properties' section includes fields like senderTimestamp and senderRoleID, while the 'required' section lists sentTimestamp and senderRole. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Updated Swagger 1.3 to align properties and required sections so that fields are called senderTimestamp and senderRoleID. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3 | Swagger 1.3
MHHS-DIN-449 | SC |  | 2023-06-21 | SRO Design Team |  | Sean Cooper | SRO Design | Change to IF-037 | Include Block B002 into IF037 so that outgoing MS is aware of incoming Supplier on a COS. This will allow the SP to populate the D0303 to MAP. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Block 002 added to IF-037 for use where event code is MSDeapp, this is so that the outgoing MS is informed of who the incoming supplier is so that D303 can be correctly population. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-450 | SC | DI-196 | 2023-06-22 | RECCO |  | Sean Cooper | SRO Design | Change to IF-005 Validation Rules | Change made to IF-005 validation Rules to allow previous MS to update Meter Location only - during the 10 day post appointment period. This will allow for scenarios where there has been relocation only activity immediatly prior to a change in MS. All other MeterUpdate functions apart from Change of Meter Location shall be rejected per wider agreement that only active MS should have the ability to change the characteristics... This change originated from R1 Comments feedback from RECCO |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF-005 Validation rules updated to include new "REG0008 - Amendment Requested cannot be undertaken by Previous Metering Service" error condition and code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-451 | SC | CR-018 | 2023-06-22 | Design Team |  | Sean Cooper | SRO Design | CR - 018 Registration Service OOH Ops | CR18 looks to specify Registration Service Out-Of-Hours Operations. | CR018 | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Following feedback provided on the redlined version of the Operational Choreography, and following discussion on CR018 at PSG, the SRO maintained the DAG Chair’s decision to approve the implementation of CR018. CR Contents incorporated into a new Section 7 of Ops Choreography Document. Updates to clarify low level processing details in Section 7 Out-Of-Hours Processes table. Following feedback from DNO Review - Additional updates to replace the term ‘SLA’ with the phrase “target response time(s)”. Changes to Column headings to ‘When’ across the Operational Choreography document to align with Code Drafting convention. Addition of Intro text and removal of text “or Performance Regime” in Section 5. | Technical corrrection | Supporting Docs | Operational Choreography | MHHSP_OPC001_Operational_Choreography | MHHSP_OPC001_Operational_Choreography
MHHS-DIN-452 | SC |  | 2023-06-22 | St Clements |  | Sean Cooper | SRO Design | Refine Consent Checking Rules on IF-031 | Further refine Consent checking rules so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing . Updates to IF-031 validation rules to reflect this change. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF-031 validation rules updated per the DIN Details. Consent checking rules added so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-453 | MF | DI-124 | 2023-06-22 | St Clements |  | Mike Fensome | SRO Design | Issuing of IF-020's | Highlighted that LDSO's could issue an IF-020 with details of import/export linkages without having received notification from the Supplier |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Added note to IF-019 and IF-020 to inform Suppliers that Import/Export linkages could be received via PUB-020 unprompted by the Supplier issuing IF-019. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-454 | SC |  | 2023-06-26 | St Clements |  | Sean Cooper | SRO Design | Update to ISD M7 | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service. added rule to support REG0011 logic in IF-031. | Requirement correction | Supporting Docs | ISD Document | MHHSP-DES138-Interface Catalogue MHHSP-EDI021-ISD Entities | MHHSP-DES138-Interface Catalogue MHHSP-EDI021-ISD Entities
MHHS-DIN-455 | SC |  | 2023-06-23 | St Clements |  | Sean Cooper | SRO Design | Update Op Choreography (Event Move from IF-013 to IF-014) | Update Ops Choreography to take account of the movement of event [ConsumptionOnDeEnergisedMPAN] which was moved from IF-013 to IF-014 (DIN-255). |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF-014 Deadline split into two. First [ActivePowerRejected] remains UNCHANGED. Deadline for [ConsumptionOnDeEnergisedMPAN] is also UNCHANGED but moved from IF-013 row into IF-014 Row, to mirror the change delivered by (DIN-255). OPC_580 ID details updated in OPC001 Operational Choreography document. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP_OPC001_Operational_Choreography | MHHSP-DES138-Interface Catalogue MHHSP_OPC001_Operational_Choreography
MHHS-DIN-456 | SC |  | 2023-06-23 | St Clements |  | Sean Cooper | SRO Design | Swagger Correction - DI-844 | Corrected x2 invalid referenced to "AssignedMRDRequestEffectiveFromDate" should have been "AssignedMRDEffectiveFromDate" in Block 066 |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Corrected x2 invalid referenced to "AssignedMRDRequestEffectiveFromDate" should have been "AssignedMRDEffectiveFromDate" in Block 066 | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3 | Swagger 1.3
MHHS-DIN-457 | SC |  | 2023-06-23 | St Clements |  | Sean Cooper | SRO Design | Change to DTN Validation of D0350 | Implement DTN Validation of D0350 to prevent future dates |  | Implemented | Design gap | TBC |  | Interim Release 8 | 2024-03-20 | CP Required for further clarification | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping | DES196 D-Flow and interface mapping
MHHS-DIN-458 | SC |  | 2023-06-23 | St Clements |  | Sean Cooper | SR Design | New IF-019 Related MPAN Validation Rule | New Validation Rule required for IF-019 to ensure that only Import MPANs can be related. Add to Create and Add Related - this is per REC Shedulle 28 |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Rules added to IF-019, [RelatedAdd] and [Related Create] events to ensure only Import MPANs can be in a related Group. New Error code added to support these new rules REG1067 - Only Import MPANs can become Related | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-459 | SB |  | 2023-06-23 | Utiliteam | 5724 | Richard Palmer | Software Provider | Spec of IF-024 in DEL138 Interface Catalogue | A further suggestion re the Interface Spec for the IF-024: The Event Code list in DI D-999 in Group S0 contains [SN-RemoteEnabled] & [SN-RemoteDisabled]. I would suggest that these are invalid for Segments Advanced and Unmetered. Also [SN-Vacant] would appear to be irrelevant for Segment Unmetered, and I doubt that [SN-NoComms] would be valid either. These existed in v5.0, and are still in v5.1.1. Perhaps the routing rules need some improvement? |  | Closed | [5 empty] | No change Required. Useage of these evernt codes is obvious and is described in the Requirments documents as necessary
MHHS-DIN-460 | SB |  | 2023-06-26 | Utiliteam | 5939 | Richard Palmer | Software Provider | PIF-019 structure & Principle -> Principal | Also, in the relationships between MPANs, the ‘main’ one is the ‘Principal’ one – not the ‘Principle’. This will be embarrassing if left uncorrected. It is still in v5.1.2 in IF-019, and it is in many other places. If there is a chance of correction, please take it. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Spelling mistake corrected in Data Catalogue, IF-019, IF-020. Note YAML name also corrected for DI-073. | Data interface correction | Supporting Docs | Interface Changes | MHHSP-DES138-Interface Catalogue Swagger 1.3 | MHHSP-DES138-Interface Catalogue Swagger 1.3
MHHS-DIN-461 | SW |  | 2023-06-26 | Greenbird | 1768 | Fredrik Omland | Software Provider | Misalignment between DES-138 and Swagger for DIP Connection Provider ID | In DES-138, In the S1 block, DI-996 (Connection Provider DIP ID) is defined as Optional. But in Swagger, this is defined as mandatory. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Updated Swagger 1.3 so DI-996 in S1 block (Connection Provider DIP ID) is Optional to align with DES-138 | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3 | Swagger 1.3
MHHS-DIN-462 | SW |  | 2023-06-27 | Design Team |  | Steve Weston | SI Design | Schema Optionality incorrectly defined for some Interfaces | In DES-138, there are are a number of Interfaces where the Schema Optionality is defined as Optional, rather than Mandatory. The list of Interfaces are as follows - IF-050 / B022, IF-023 / B053 and IF-013 / B049 |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Updated Schema optionality in DES138 to show that all data items must be present where the block is present in line with updated E2E Solution Architecture for IF-050 / B022, IF-023 / B053 and IF-013 / B049. | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalouge | DES138-InterfaceCatalouge
MHHS-DIN-463 | SW |  | 2023-06-27 | SIMS |  | Kyle Abraham | Software Provider | No ability de-register from receiving Status messages in Swagger | In Swagger, there is a POST method for /statusmessage/config, but there is no DELETE method, so you are unable to delete / de-register for any status messages. Need to update Swagger to ensure this is possible. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Updates made to Swagger 1.3, so there is a DELETE method for /statusmessage/config, so you are now able to delete / de-register for any status messages. Updated so that all of the Interfaces accept the same 4 security headers required for message signature and validation. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3 | Swagger 1.3
MHHS-DIN-464 | SW |  | 2023-06-27 | SIMS |  | Kyle Abraham | Software Provider | Clarity required on values expected for /dip-channel/{id} for submitEvents on Swagger | The {id} in /dip-channel/{id} for submitEvents on Swagger should accepts values that are the same as the enumeration in DI-000 to ensure consistency. At the moment, this is not clear in Swagger or E2E001 design, so this needs to be updated to make this clearer. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Updates made to Swagger 1.3, so there the correct enumerations / values are available to align with values in DI-000 to ensure consistency and avoid any ambiguity between interfaces and reports. Updated to remove PublicationConfig and RestConfig in favour of a single config WebhookConfig. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3 | Swagger 1.3
MHHS-DIN-465 | SC |  | 2023-06-28 | RECCO |  | Sean Cooper | SRO Design | Update to BP010 - Related MPANs | The process MPAN for Related MPANs does not clear call out the Rejection pathway. Update Business Process to show rejection process. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | BP010B Related MPANs Process updated to show specific Rejection Route. | Process Model correction | Metering Changes | Business Process Documentation | BP010- Changes to MPAN Data | BP010- Changes to MPAN Data
MHHS-DIN-466 | SC | DI-188 | 2023-07-29 | St Clements |  | Sean Cooper | SRO Design | Change of MPAN Status during Service Provider Appointment Process. | How should a change of MPAN Status be dealt with whilst there is an ongoing SP Appointment that has not yet reached the stage of IF-034 processing !? If an MPAN is disconnected between PUB-031 acceptance and receipt of PUB-034, the SP PUB-034 Response would be rejected by MPRS due to validation rule REG1001. The appointment would not be progressed but would be stuck in the MPRS queue at status Requested. Could resolve by amending REG1001 validation on IF-034, to not apply to event codes MSAppSPResponse or DSAppSPResponse. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Resolved following discussion with SCS, Agreed that SCS will take no action until the IF-034 has been processes. A change to REG1001 validation on IF-034, to not apply to event codes MSAppSPResponse or DSAppSPResponse, is required to allow the IF-034 to processes normally (when where MPAN is disconnected)... Following processing of the IF-034 RESG will then immediatly issue an IF-035 with reason code of "1- Lapsed as MPAN Status is Disconnected" ... ... Agreed that this was best resolution both for REGS processing rules and participants as no change to currently expected message patterns/ordering. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-467 | SC |  | 2023-07-29 | ESG |  | Sean Cooper | SRO Design | Review of IF-035/IF036 Data Item Obfuscation | Review of IF-035/IF-036 Data Item Obfuscation |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Various updates to obfuscation on IF-036 to align with IF-035. DI-019/DI-800/DI-809/DI-207 obfuscated for Data Service DI-020/Di-800/DI-126/DI-842/DI-209/Di-844/DI-811/DI-208 /DI-018 obfuscated for Metering Service | Data interface correction | Supporting Docs | Interface Catalogue | MHHS-DES138-Interfaces | MHHS-DES138-Interfaces
MHHS-DIN-468 | SC |  | 2023-07-29 | Helix |  | Sean Cooper | SRO Design | Routing of IF-020 | Helix have confirmed that they DO NOT need to receive Related/Linked MPAN information therefore an update is required to REMOVE MDS from the receipient list for this IF-020 |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF-020 Routing table has been updated to REMOVE MDS as being a recipient of any IF-020 messages. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-469 | ME |  | 2023-06-30 | SRO Design Team | 2109 | Rob Golding | SRO Design | Removal of Z0 & Z1 data items in ERI011B - ECS Reports External | Z0 & Z1 data items to be removed from from the each of the MHHS reports within ERI011B - ECS Reports External as they are no longer in the common block |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Removed Z0 & Z1 data items from all MHHS reports in ECS external reporting artefact | Data interface correction | Minor | ECS Reports | ERI011B - ECS Reports External | ERI011B - ECS Reports External
MHHS-DIN-470 | SW |  | 2023-06-29 | Callisto | 1805 | Seth Chapman | Software Provider | Clarity on nullable fields | Section 4.2.2 in the E2E design provides information on Optional / nullable fields, but worked examples would provide further clarity for each of the data types / link to JSON specification. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Updated section 4.2.2 with worked examples for each data type to provide additional clarity. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-471 | MH |  | 2023-06-30 | Helix |  | Derek Weaving | Central Body | Update to REP-003 in ERI011B - ECS Reports External | R019 parent should be R017 in the ECS Reports External and Swagger |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Updated R019 parent to R017 for REP-003 in ERI011B - ECS Reports External. Swagger v1.3 updated to align with changes within ECS reports artefact. | Data interface correction | Minor | Interface Changes | ERI021 -ECS Reports External Swagger 1.3 | ERI021 -ECS Reports External Swagger 1.3
MHHS-DIN-472 | SW |  | 2023-06-29 | SRO Design Team | 2006 | Rob Golding | SRO Design | Onboarding migration from Test to Production. | “The programme is to implement a strong PKI policy but as per the diagram states that that on promotion, parties will be able to copy their Test setup and to use that for connecting to the Prod environment. - steps 1-8 - There are no steps in this sequence that test the connectivity to the Live DIP environment. To this point the only connectivity testing has been to the Test environments. This is a significant failure point / risk. At this point Webhooks and certificates will change (mTLS and JSON signing) from those used in Test as well as potentially some of the PKI resources assigned to roles ( those used in test may not be applicable to Prod) we would expect that this would require a new Connectivity proving period with the Prod environment similar to that being developed for CIT. Without such proving, how can the programme assume all parties will connect to the Prod environment successfully and ensure minimal impact to migration events”. |  | Closed | [5 empty] | Solution yet to be defined This an Elexon/DIP Manager deliverable not a programme deliverable
MHHS-DIN-473 | SB |  | 2023-06-30 | MHHS | 2111 | Jason Brogden | Network Operator | Definition of Network Operations | Issue: There is a lack of clarity in the scope of Network Operations activities in testing. Action to Resolve: Add a definition to the Programme Glossary that makes clear the scope of Network Operations (as referenced in Testing material) is equivalent to the scope of LDSO activities in the MHHS Design Baseline: Network Operations systems and services are those that are required to deliver the elements of the MHHS Design Baseline that are allocated to the LDSO role. Communicate this to the DNO and iDNO community and associated service and software providers. For the DIN Log, we can then focus on updates to the BRS to give the necessary clarity on the scope of MHHS Design. Issue: There is a lack of clarity in the scope of LDSO activities in the MHHS Design Baseline as BRS005 implies MHHS-related processing requirements at LDSOs for received DIP messages, whereas the BPs and BPDs define the scope of MHHS as ending at the receipt of DIP messages. BRS005 is described as “For Guidance Only” at the top and this is to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing). Action to Resolve: For the avoidance of doubt and to provide clarity to BRS005, it is proposed to change the “For Guidance Only” note at the top of BRS005 to the following description as per the above: BRS005 is provided For Guidance Only to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing). |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | LDSO Requirements document updated with the following text, "BRS005 is provided For Guidance Only to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing)." | Requirement correction | Minor | Business Requirements Documentation | BRS-005 LDSO Overview.xls | BRS-005 LDSO Overview.xls
MHHS-DIN-474 | ME |  | 2023-07-03 | MHHS |  | Kevin Spencer | SRO Design | Creation of new ECS data items and blocks across multiple reports and/or data catalogue | Report definitions incorrect and require updates and new data items following internal review |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Addition of data items DI-503, DI-505-DI-515 to data catalogue and across ECS reports artefact. MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal Missing data items added to data catalogue Di-403/DI-404/DI-514/DI-515 | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-475 | ME |  | 2023-07-03 | MHHS |  | Kevin Spencer | SRO Design | Update to block names, data items and descriptions | Report definitions incorrect and require updates and new data items following internal review |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Update to block names, DTN references, data items, descriptions and reordering of data item blocks to exisiting reports in MHHSP - ERI011B - ECS Reports - External | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-476 | SW |  | 2023-07-03 | Greenbird | 2035 | Fredrik Omland | Software Provider | Inconsistency between enum fields and nullable definition | Looking at DIP Interfaces Swagger 1.1 (also 1.2 + 1.3), the enum typed fields that are nullable may not comply with OpenAPI specification (for 3.0.x). The topic around enum fields with nullable: true has been clarified/answered by OAS project (amended in spec version 3.0.3 in 2021): (Reference: https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md ) |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | To align with Open API spec clarification at https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md, we have updated all Data Types that are nullable and have an enum to align as follows: Following discussion, have decided to align with OpenAPI 3.1 DI-076-Estimation-Reason-Code: description : Used inconjunction with Settlement Period Quality Indicator to explain why data has been estimated type : string nullable: true maxLength : 2 example : '1' enum: - '1' # OptOut - '2' # Missing .. - '8' # Disconnected - '9' # Consumption Amendment - '10' # NonSmart - null The Data Types affected / updated as follows: --- DI-039-Load-Shape-GSP-Group-ID --- DI-076-Estimation-Reason-Code --- DI-096-Site-Visit-Check-Code --- DI-126-Traditional-Fall-Back-Read-Frequency --- DI-137-IHD-Install-Status --- DI-150-Annual-Consumption-Quality-Indicator --- DI-166-Supplier-Consumption-Amendment-Reason-Code | Data interface correction | Minor | Interface Changes | Swagger 1.3 | Swagger 1.3
MHHS-DIN-477 | SW |  | 2023-07-03 | MHHS |  | Steve Weston | SRO Design | Swagger alignment to OpenAPI 3.1 specificiation | Align with Open API specification 3.1 to remove nullable :true and replace with type declaration ie, type:[string:”null”] | CR049 | Closed | Design ambiguous | DIP Users |  |  |  | Align with Open API specification 3.1 to remove nullable :true and replace with type declaration ie, type:[string:”null”] | Design Ambiguous | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-478 | SW |  | 2023-07-03 | MHHS |  | Rob Golding | Central Body | IF-021 max number of days of consumption data | In the Release 2 version of DES138 a limit was introduced that asked Participants not to submit more than 150 Settlement Days’ worth of data in a single message. The value of 150 was proposed as this meant a single message would realistically be ~600KB in size. We’ve had some queries regarding this value, the proposal is to increase sizing from 150 to 194 day message and the size increases from 600KB to ~780KB for IF-021 message. ECS will need to validate the message contents. However, rather than letting a ‘large’ IF-021 message traversing though the DIP, the proposal is to limit the IF-021 on ingress to the DIP and a single request will have a limit of 1MB – this will be done at the API level. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Agreed to limit the number of MQ IDs per IF-021 submission to ONE only and limit settlement days to 200. Swagger has been updated to limit the number of MQIDs to 1. Swagger updated to limit the maximum number of Settlement Days to 200. DES138 also updated to aligned with the above changes for IF-021. | Data interface correction | Minor | DES138 and Swagger | DES-138 and Swagger 1.4 | DES-138 and Swagger 1.4
MHHS-DIN-479 | SC |  | 2023-07-03 | St Clements |  | Maddison | SCS | Change to Consent Notification on IF-036 | SCS have suggested that B068 should only be required for DSApp Events. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Block 068 on IF-036 amended to that it is only Mandatory for DSApp Events. | Data interface correction | Supporting Docs | Interface Change | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-480 | SC | DI-195 | 2023-07-03 | St Clements |  | Maddison | SCS | Reverse DIN-105 | SCS have confirmed that it is possible currently and should continue to be possible to manage MPAN Linkages whilst MPAN(s) are at Created Status. Therefore we have reversed the change implemented at part of DIN105 and now allow processing of IF-019 if mpan status = "Created" |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | SCS have confirmed that it is possible currently and should continue to be possible to manage MPAN Linkages whilst MPAN(s) are at Created Status. Therefore we have reversed the change implemented as part of DIN105 and now allow processing of IF-019 if mpan status = "Created" | Data interface correction | Supporting Docs | Interface Change | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-481 | SW |  | 2023-07-06 | Elexon | 2106 | Nigel Rees | Central Body | REP-003 inconsistency between DES-138 | We have a contradiction between the DT-023 and the swagger spec. As there is an example we will implement based on the example but it looks like the person who wrote the ECS report catalogue used the correct convention. e.g. on REP-003 we have DT-023 as NUM (16,6). If we follow the convention used in the DIP interface spec, this would translate to 1234567890123456.123456, however the swagger suggests 123456789.123456 Screenshot from REP003 in external ECS reporting catalogue https://app.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.3#/components/schemas/DT-023-Positive-Decimal-9-6 DT-023-Positive-Decimal-9-6: description: Number (9,6) format type: string pattern : ^[0-9]\d{8}(\.\d{6})?$ example: 123456789.123456 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Two new data type references have been created DT-024 and DT-024N. For NUM(16,6) data type within ECS reports/ECS data catalogue replace DT-023/DT-023N with DT-024/DT-024N. DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. 31/08: A reconciliation exercise is being carried out internally of the ECS data catalogue to assess data types. Further work may be required to swagger following the reconciliation. Reconciliation task has been completed which has resulted in updates to the MHHS Data Types within the ECS Reports data catalogue. MHHS data type references in Swagger have also been updated to align with these changes. An example of how MHHS data types should be interpreted: String 17 should be interpreted as NUM(±9.6) which can be physically represented in this way for a negative number -123456789.123456 or for a positive number it will be 1234567890.123456. The objection has been removed. | Reporting correction | Minor | ECS Reports | "MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2" Swagger | "MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2" Swagger
MHHS-DIN-482 | KH |  | 2023-07-10 | C&C | 2394 | Hazel Cotman | Software Provider | Interim Release 2 query - IF-018 | LDSO’s are not detailed as ‘To Parties’ within IF-018 flow, however, the LDSO is a secondary routing party for updates to the Domestic Premise, Energy Direction Indicator, and the Metered Indicator |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | LDSO's added to the To party list of IF-018 | Data interface correction | Minor | Interface Catalogue | DES138 | DES138
MHHS-DIN-483 | KH |  | 2023-07-10 | BGAS | 2410 | Neil Stranger | Supplier | MHHS Design Query - date/ time in DES138 | In DES138 there are a number of data items that are defined as having a date/time structure, but the name and description only refer to the date element whereas others refer to date and time. Therefore for those that make no reference to time we need to be 100% clear if the time should be when the event occur or should it be defaulted to say midnight. This is to ensure consistent population/use across the market. |  | Closed | [5 empty] | Related to a Design Principle and agreed as per E2E Architecture
MHHS-DIN-484 | SW |  | 2023-07-10 | Design Team | 2352 | Martin Freeman | Central Body | Clarity on RecipientId and SenderID in StandardResponseBodyType | RecipientID in the Standard Response Body is a mandatory field. When submitEvents (or in IR2 dip-channel) is called, the DIP synchronously returns a Standard Response Body. At this point the DIP does not even know what message recipients the message will be routed too, since the response is returned synchronously whereas routing is performed asynchronously. So the DIP has no way to know what to set recipientID to. It is also important to note that a message can be received by multiple recipients, yet this recipientID is a scalar that only supports being set to a single value. So it isn't clear how that could work. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | The Sender of the messages becomes the Recipient of the Response this already outlined in the examples in the E2E SA doc. Update section 4.6.1 in the E2E001 Design document to provide better clarity on how SenderID and RecipientID are populated in the StandardResponseBodyType. Updated Swagger 1.5 to align with the above. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-485 | SW |  | 2023-07-10 | MHHS | 2380 | Steve Weston | Central Body | Unable to identify Recipient on DELETE and some POST methods | For the DELETE methods in Swagger for StatusMessage and PublicationConfig, need to update the method so you can identify the correct recipientID to be used for the method call. Some frameworks will ignore a body on a DELETE method as being incompatible with the semantics of the DELETE method, and the correct RESTful implementation would be something more along the lines of "DELETE dip-channel/{id}/{role}/pubconfig". Which of course raises the question of whether the POST message should be refactored for consistency. The issue is more widespread than just the DELETE methods, it also affects some of the POST methods where a recieipent ID is required |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Design changes required to Swagger 1.4 to support updates to API endpoints for DELETE API verbs to ensure we are able to remove the correct StatusMessage or PublicationConfig for the appropriate recipient combination. The issue also affects some of the POST methods where a recipient ID is required, e.g webhook config. A standard pattern is proposed where a recipeint id is specified in the path. Updates to section 4.5.1 and 4.7 also made to E2E001 design document to ensure the document provides any clarity required. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4 | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-486 | SB |  | 2023-07-11 | MHHS | 2107 | Rob Golding | Central Body | DES138 and message addressing information | Please can you raise a DIN to cover the following request from Participant to clarify the From and To Parties at the top of each sheet to align with the role codes the programme is using and defined in the E2E Solution Architecture document. And if these ‘pure’ roles code could be included in the introduction sheet that would certainly help. More detail can be seen in the Ticket |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Update the role codes in DES-138 for the From / To Parties for each of the Interfaces to align with other documents including E2E001. No change to information in the Introductory section in DES-138 required. | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-487 | SW |  | 2023-07-11 | MHHS | 2379 | Martin Freeman | Central Body | Clarity on schema vs data validation failures, with updated examples. | In section 4.4.4.2, there are some examples that incorrectly return a 207 when they have failed schema validation. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | In section 4.4.4.2, there are some examples that incorrectly return a 207 when they have failed schema validation. E2E001 section 4.4.4.2 has been updated to illustrate 2 examples. One that returns a 201 Created (2 messages as part of the HTTP Request, both pass validation) and another example that returns a 207 (2 messages part of the HTTP Request, but 1 does not pass validation). | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document Swagger 1.4 | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-488 | ME |  | 2023-07-11 | MHHS | 1506 | Steve Weston | SRO Design | Correct Reporting Cat vs Swagger | Reinstated DI-484 "Settlement Period Duration" and added into R Groups as required |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Reinstated DI-484 "Settlement Period Duration" and added into R Groups as required in Swagger 1.4 | Data interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4 | Swagger 1.4
MHHS-DIN-489 | MF |  | 2023-07-11 | Design Team |  | Mike Fensome | SI Design | Schema Optionality incorrectly defined for Common Block | In DES-138, the Common Block shows some fields where the Schema Optionality is defined as Optional, rather than Mandatory. The list of Blocks are as follows - Common Block: S1, D0, A0 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Update Schema optionality in DES138 to show that all data items must be present where the block is present in line with updated E2E Solution Architecture. Common Blocks impacted: S1, D0, A0 | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-490 | SW |  | 2023-07-11 | Design Team | 2395 | Martin Freeman | Central Body | Level 1 validation clarity for POST /statusmessage be the same as for POST /dip-channel/{id} | The E2E001 v3.2 (section 4.4.3) describes how for the Send Messages API, when the DIP performs level 1 validation, if any message in the request fails validation then the entire request is rejected. Section 4.6 Send Status Messages API does not describe the DIP validation for status messages at all. Should validation for POST /statusmessage be the same as for POST /dip-channel/{id}, in that a level 1 validation failure for any message should fail the entire request, or should messages that pass validation be accepted and messages that fail be rejected independently? |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | This should be consistent across all interfaces in that a schema validation failure for any message should fail the entire request. In the E2E001 design, sections 4.4.3 and 4.6 are to be updated to reflect this / provide the appropriate level of clarity. This issue affects both the http delete operations. Easy to fix, same fix as the post need to include the webconfigas a parameter | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.5 | E2E001 E2E Architecture Document Swagger 1.5
MHHS-DIN-491 | SB |  | 2023-07-11 | Utilita | 2408 | Adam Barnes | Supplier | IF-035 - Update routing to show XDSS | DES138 v5.2.1 - IF-035 tab for the bottom 3 entries it still refers to the previous version definition of routing parties – we expect this to be a slight oversight as SDSS is no longer defined as a recognised party? |  | Implemented | Error/Correction | N/A |  | Interim Release 8 | 2024-03-20 | Update routing for IF-035 to show XDSS for consistency of the documentation, but it will only ever apply to MPANs in the Smart Segment so will in reality only ever be routed to an SDS. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-492 | KH |  | 2023-07-11 | Stark | 2125 | Matthew Peters | Supplier | IF-034 Proposed Appointment Response Code Formatting | The data type within DI-143 block for IF-034 and IF-035 needs to change from String 200 to Array because there is a possibility of getting more than 1 rejection code. |  | Closed | [5 empty] | Closed - only 1 rejection code is required
MHHS-DIN-493 | SC |  | 2023-07-12 | St Clements |  | Sean Cooper | SRO Design | Changes to IF-019 Secondary MPAN validation | SCS had originally suggested a validation rule to prevent Secondary (Related) MPANs being linked to an Export MPAN. However, RECCO and EON have highlighted there are a very small number of scenarios where this might be the case. Following further discussions with SCS they are now happy to remove this rule (REG1068) |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | IF-019 - REG1068 check for Secondary MPAN Linkage to export REMOVED | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-494 | SW |  | 2023-07-12 | Callisto | 2462 | Neil Edney | Software Provider | Incorrect Min and Max Values for DI-091-Number-Of-Displayed-Register-Digits | DI-091-Number-Of-Displayed-Register-Digits currently has a minimum of 1 and maximum of 1, when this should be 5 and 6 respectively to align with DES-138 as this is an Integer. |  | Closed | [5 empty] | This DIN is now superseded by DIN-615 following on from DIN-574. Text against Number of Register Digits field amended to say "per the manufacturer specification". Swagger validation of this field updated to match SCS logical test ie value can be 0-9. This DIN was to ensure there was consistency in Swagger 1.4 to align with DES-138 so that min and max was 5 and 6 respectievly. This objection is related to the values in DES-138, to update from 5 and 6 to 0 and 9, and then align Swagger to the values in DES-138. | No Change
MHHS-DIN-495 | SC |  | 2023-07-12 | Design Team |  | Sean Cooper | SRO Design | Correction to BP003 | IF-035 for Trad/Advanced meters was previously shown as being direct interaction between REGS and MS ... Changed to show message as flowing via the DIP |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF-035 for Trad/Advanced meters was previously shown as a flow being direct interaction between REGS and MS. Changed to show message as flowing via the DIP (at step 90). Also change applied to Forward migration process for consistency. | Process Model correction | MPAN Ownership | BP003 | MHHSP-BP003-Change of Service - Data Service MHHS-DEL964 BPM-003 - Change of Servie - Data Service - Forward Migration | MHHSP-BP003-Change of Service - Data Service MHHS-DEL964 BPM-003 - Change of Servie - Data Service - Forward Migration
MHHS-DIN-496 | MH | DIN-910 | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 | MHHSP-METH001_SDS_Validation_Estimation 5.1 section 2.7 States "SDS shall inform the Supplier using the Meter Reading Reason Code on the IF-041/PUB-41" . There is no Meter Reading Reason Code on the IF-041 in DES138 v5.1.2. Therefore, either Meter Reading Reason Code should be included in DES138, or this requirement should be removed. |  | Closed | Design ambiguous | N/A |  |  |  | Updated as part of DIN-910 | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-497 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 | MHHSP-METH001_SDS_Validation_Estimation 5.1 Section 5.4 Where DA records are < 90 days from UTC date this is inconsistent with Method 4, which states "DA is available [either in the past or future] and less than [3] months different from the UTC Date requiring a daily Meter advance". |  | Implemented | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Be consistent - use either 90 days or three months within the document Tend to agree – this describes the actual method of estimation so should be included before go-live | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-498 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 Method 13 | MHHSP-METH001_SDS_Validation_Estimation 5.1 Method 13 This describes the outcomes for Smart and Advanced meters. Does this imply that traditional meters should have zero consumption submitted to settlements, or should Method 13 text be adjusted to include trad meters? ALSO If actual data is recovered, or an Advance Meter Reading is received, and this indicates zero consumption, should this be submitted to settlements? The first part of the sentence implies it should be submitted, and the brackets imply it shouldn't. |  | Implemented | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Alter wording of Method 13 to reflect we shouldn't be sending estimates for Deenergised trad meters as well as Smart and Advanced, AND 'there is no need to submit zero consumption for de-energised MPAN's' needs changing to refer to 'zero ESTIMATED consumption' This should be a clarification of previously stated position but agree update should be made to clarify that Zero consumptions are required to be submitted, where encountered, for all MPANs that are not de-energised regardless of segment/meter type. | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-499 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Alignment of Estimation Reason Codes | METH001 refers to Estimation Reason Code 'Adjustment'. DES138 refers to 'Consumption Amendment' Assume these are the same thing and need to be aligned between both sets of documentation |  | Implemented | Design misaligned | N/A |  | Interim Release 8 | 2024-03-20 | Align Method Statements to match the Estimation Reason Codes within DES138 | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-500 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | ISD Entity M17 Example Correction | MHHSP_EDI021_ISD_Entities 5.1 Entity id M17 Industry Standing Data: MHHS Entities/Data Items v5.1 ISD Entity Id M17 - Valid Consent Granularity Combinations, includes combination I¦F¦S¦D. According to Decision 2 in "https://www.ofgem.gov.uk/sites/default/files/docs/2019/06/access_to_data_consultation_ofgem_response_0.pdf" a non-domestic customer is unable to opt out. The OFGEM document states "There will be no opt out possible for microbusinesses in relation to data for settlement purposes". Therefore, I ¦ F ¦ S ¦ D is not a valid combination. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | In ISD Entity ID M17 we have removed "I ¦ F ¦ S ¦ D" from the example list | Design Ambiguous | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-501 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Addition of Method 13 to METH002 | MHHSP-METH002_ADS_Validation_Estimation 5.1 Section 3.16 States "The below estimation methods are based on those used in the Smart Data Service (SDS) Method Statement. For that reason, methods 0, 1, 6, 11 and 13 have been omitted as they are only applicable to Smart meters." However, method 13 is "Estimation for a Site where Supply is de-energised" and this is included in METH002 in section 2.29. The statement is wrong as some of the methods have been renumbered in METH001 since this was written. |  | Implemented | Error/Correction | Smart Data Services |  | Interim Release 7 | 2024-01-19 | Update METH002 to add Method 13 back in | Requirement correction | Supporting Docs | Method Statement | ADS Method Statement | ADS Method Statement
MHHS-DIN-502 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | SP Quality Indicator Clarification | MHHSP-METH001_SDS_Validation_Estimation 5.1 It is our assumption that if NO estimation is required, the Settlement Period Quality Indicator should be set to "A". This is however, never explicitly mentioned. The only mention of using value "A" is for method 1. |  | Implemented | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Update artefacts to clarify when to use A as the Settlement Period Quality Indicator value | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-503 | SW |  | 2023-07-13 | SIMS | 2439 | Martin Freeman | Central Body | S1.senderUniqueReference interface component is too small to identify the message interface | DES138 and the E2E001 the S1.senderUniqueReference property has a 3 digit component that contains the interfaceID of the message. However since the reporting interfaces reuse the same interface numbers as the standard interfaces, and some reporting interfaces have 4 character interface identifiers, this means this component is not sufficiently large to unambiguously identify which interface a given senderUniqueReference was generated for. This also applies for TransactionID. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Update any Data Items that utilise InterfaceID to align with the enumeration of values defined for DI-000 so that this is unique across all interface / report types. This is for data types SenderUniqueReference (DI-995) and TransactionID (DI-990). This change will require updates in DES-138, E2E001 and Swagger 1.4. In DES-138, DT-014 has been updated to String65 from String60 to support Interface being updated from 3 to 8 to align with DI-000 (so for IF-003, rather than 003 being included in the transactionID / senderUniqueReference, this will be IF003 with no hyphen). In Swagger, DT-014 has been updated to max length 65, with examples updated. E2E001 updated examples for senderUniqueReference and TransactionID to align with the above. | Design Ambiguous | Supporting Docs | DES-138, E2E001 and Swagger 1.4 | DES-138-interface catalogue, E2E001 E2E Architecture document and Swagger 1.4 | DES-138-interface catalogue, E2E001 E2E Architecture document and Swagger 1.4
MHHS-DIN-504 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Clarification of link between IF22/IF23 | DES138 IF-022/023 IF an IF-022 or IF-023 is re-issued, can you confirm that they will be reissued as a pair so that the totals align? The issue is if an updated IF-022 is issued with new values, should the SDS/ADS await an updated IF-023, or not? How can the SDS/ADS pair the IF-022 and IF-023 without doing their own summations? |  | Open - awaiting assessment | Clarification - No change required | N/A |  | Post Go-live Release | 0 | Update BRS007 to show that a re-run of IF-022 will result in a rerun of IF-023 |  |  |  | BRS007
MHHS-DIN-505 | BK |  | 2023-07-13 | St Clements |  | Sean Cooper | SRO Design | DUoS Tariff ID to hold values from 1-3 in length | The DUoS Tariff ID needs to be updated in Swagger and the Interface Catalogue so that it can hold values from 1 to 3 in length in order to align with ISD. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Update DUoS Tariff ID to hold values from 1 to 3 in length in Swagger and Interface Catalogue | Data interface correction | Supporting Docs | Interface Catalogue and Swagger 1.4 | DES138-InterfaceCatalogue Swagger 1.4 | DES138-InterfaceCatalogue Swagger 1.4
MHHS-DIN-506 | BK |  | 2023-07-13 | Design Team |  | Sean Cooper | SRO Design | Renaming of IF-014 | Rename IF-014 to clarify the purpose |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Changed to "UTC Settlement Period Consumption Data (Warnings & Rejections)". Interface description and notes updated to reflect that IF-014 could also contain warnings for Consumption on De-enegised sites. | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-507 | SC | DI-194 | 2023-07-14 | Design Team |  | Sean Cooper | SRO Design | Clarification of IF-036 Routing Requirements | Update IF-036 to clarify / provide additional info on the routing destinations of IF-036 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Added following Text: Primary Routing Participants for IF-036 MSAppActive • Supplier (i.e. the supplier who initiated the appointment, either current in the case of Change Of / Update to SP’s, or incoming in the case of a COS) • Metering Service (i.e. the Metering Service being appointed) • [Partner] Data Service (i.e. the Data Service in effect on the App Start Date of the MS Appointment – this could be either an ‘existing’ Data Service in the case of an MS Only appointment OR the ‘incoming’ Data Service with a coincident App Start Date to that of the [incoming] Metering Service • Linked Supplier(s) – (ie the Supplier(s) with responsibility for the Linked [Import/export] MPANs on the App Start Date of the Metering Service Appointment) DSAppActive • Supplier (i.e. the supplier who initiated the appointment, either current in the case of Change Of / Update to SP’s, or incoming in the case of a COS) • Data Service (i.e. the Data Service being appointed) • [Partner] Metering Service (i.e. the Metering Service in effect on the App Start Date of the DS Appointment – this could be either an ‘existing’ Metering Service in the case of an DS Only appointment OR the ‘incoming’ Metering Service with a coincident App Start Date to that of the [incoming] Data Service • Linked Supplier(s) – for Advanced Segment Meters only - (i.e. the Supplier(s) with responsibility for the Linked [Import/export] MPANs on the App Start Date of the Metering Service Appointment) | Data interface correction | Supporting Docs | Interface Catalogue |  | DES138-InterfaceCatalogue
MHHS-DIN-508 | SC |  | 2023-07-17 | Design Team |  | Sean Cooper | SRO Design | Addition of MP Status and RMP Status Effective From Dates to IF-050 | Addition of MP Status and RMP Status Effective From Dates to IF-050 ( Linked to DIN 318 ) |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | New Data Items Created and added to IF-050 in block B079 and the data catalogue tab: DI-167 RMP Status Effective From Date DI-168 MP Status Effective from Date (DIN 318 Closed as duplicate) | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-509 | SW |  | 2023-07-18 | MHHS |  | Steve Weston | Central Body | Missing Archival NFR Information | There is no detailed non-functional requirements in relation to data archiving, retrieval, archival tiers, recovery from archival so we need to update the NFR's to ensure these are included. |  | Open - awaiting assessment | Design ambiguous | DIP Users |  | Post Go-live Release | 0 | Further details of the solution are under discussion/review. | Clarification |  |  | Non-functional Requirements
MHHS-DIN-510 | SW |  | 2023-07-18 | MHHS | 2675 | Steve Weston | Central Body | Properties on block B047 | The Swagger definition has the properties ‘sp’,’v’,’q’,’e’ and ‘arc’ which matches the items in red. However the data catalogue has different YAML names. YAML Swagger names have to be updated in DES-138 to match the above characters. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | This was done to reduce IF-021 content size, but the DES-138 5.4.1 YAML needs to be updated to align with Swagger 1.4 - the YAML names should be as follows DI-082 ‘sp’ - B052 (IF-022), B047 (IF-021) DI-147 ’v’ - B047(IF-021, 4, 16) DI-083 ’q’ - B047 (IF-021, 14, 16) DI-076 ’e’ - B047 (IF-021, 14, 16) DI-166 ‘arc’ - B073 (IF-027 / 28) Swagger 1.4 has been updated to align for the approrpiate blocks above to ensure consistency across the data catalogue. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-511 | BK | CR027 | 2023-07-18 | Eastern Power Networks |  | Peter Waymont | Network Operator | DUoS E-Billing DIP Message for MHHS | A new flow needs to be introduced for e-billing of site-specific DUoS in the post Market-Wide Half-Hourly Settlement (MHHS) environment because the existing flow uses the DTN and all other DUoS data will be DIP based. The change is required in order to continue to operate the site specific DUoS billing process in the MHHS environment. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the HH data sent by Data Services to the LDSO for use in DUoS billing, using IF-021/IF-013/IF-014. At present DUoS billing systems can send the D2021 data flow as a form of e-billing for site-specific DUoS, using the DTN. As DUoS billing systems will need to interact with the DIP for migrated site-specific billed customers, it is preferable that the outputs are also DIP messages, to enable the parties to move forward completely in the new environment. A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors) and receivers (suppliers) of the flows has identified the desired flow content and now wish to bring this to the Programme to ensure that it can be delivered in readiness for migration. | CR027 | Closed | [5 empty] | Covered as part of CR019
MHHS-DIN-512 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Amendments to Swagger and ECS data catalogue REP-002 | Max length for DI-345 DUoS Tariff Id to be updated in line with ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated to ensure DI-345 DUoS Tariff ID aligns with ECS Data Catalogue - max length of string = 3. | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4 | Swagger 1.4
MHHS-DIN-513 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Custom block correction REP-002 | Block name to be updated to tariffCharacteristics in Swagger. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated for REP-002 custom block to fix typo from tarrifCharacteristics to tariffCharacteristics to align with ECS Interface Catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4 | Swagger 1.4
MHHS-DIN-514 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Amendments to Swagger and ECS data catalogue REP-002a | Max length for DI-345 DUoS Tariff Id to be updated in line with ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated to ensure DI-345 DUoS Tariff ID aligns with ECS Data Catalogue - max length of string = 3. | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4 | Swagger 1.4
MHHS-DIN-515 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Custom block correction REP-002a | Block name to be updated to tariffCharacteristics in Swagger. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated for REP-002 custom block to fix typo from tarrifCharacteristics to tariffCharacteristics to align with ECS Interface Catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4 | Swagger 1.4
MHHS-DIN-516 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Update DI-300 with Minimum value REP-003 | DI-300 to be updated in swagger with a minimum value of 100 as per ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-300 updated in Swagger 1.4 with a minimum value of 100 as per ECS data catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4 | Swagger 1.4
MHHS-DIN-517 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update data item type in ECS data catalogue REP-003 | DI-325 data type to be updated in data catalogue to (NUM 4,2) in line with swagger |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to NUM(4,2) for DI-325. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Cataloue correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-518 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Inclusion of Max/Min value for DI-496-REP-003 | Update ECS data catalogue with Min value of 1 and Max value of 48 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MIn and Max Column of MHHS ECS data catalogue updated with 1 and 48 respectively. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-519 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Max value change in swagger for DI-496 | Update Max value to 48 for DI-496 in swagger |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-496 in Swagger 1.4 updated to have a Max value of 48 | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4 | Swagger 1.4
MHHS-DIN-520 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-359 data type REP003 | Update DI-359 data stype to String 16 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-359. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-521 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-360 data type REP003 | Update DI-360 data stype to String 16 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-360. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-522 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-362 data type REP003 | Update DI-362 data stype to String 16 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-362. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-523 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-324 data type REP003 | Update DI-324 data stype to String 16 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-324. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-524 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | DI-363 missing from ECS data catalogue | Update ECS data catalogue by adding in missing DI-363 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data catalogue updated with the addition of missing data item DI-363. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-525 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-364 data type in REP003 | Update DI-364 data stype to String 17 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-364. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-526 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-365 data type in REP003 | Update DI-365 data stype to String 17 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-365. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-527 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-366 data type in REP003 | Update DI-366 data stype to String 17 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-366. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-528 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-367 data type in REP003 | Update DI-367 data stype to String 17 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-367. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-529 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-368 data type in REP003 | Update DI-368 data stype to String 17 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-368. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-530 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Wrong data item referenced in swagger | Wrong data item referenced in R022. Daily Period BM Unit Total Allocated Volume must be changed to BM Unit Allocated Demand Disconnection Volume |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 has BM Unit Allocated Demand Disconnection Volume (DI-241) in R022 | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4 | Swagger 1.4
MHHS-DIN-531 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Data type update in swagger for DI-341 | DI-341 data type to be changed to String 18 as per data catalogue |  | Closed | [5 empty] | Closed. This is defined a Integer in the format 9,6 in Swagger. | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4 | Swagger 1.4
MHHS-DIN-532 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Wrong data item referenced in swagger | Wrong data item referenced in R022. settlementPeriodID must be changed to Settlement Period |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Updated Swagger 1.4 so that R022 references DI-946 (SettlementPeriod) rather than DI-307 (SettlementPeriodID) | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4 | Swagger 1.4
MHHS-DIN-533 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-339 data type in REP-003 | Update DI-339 data stype to String 17 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-339. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-534 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-369 data type in REP-003 | Update DI-369 data stype to String 17 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-369. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-535 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-370 data type in REP-003 | Update DI-370 data stype to String 17 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-370. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-536 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-322 REP003 | Update Min column of ECS data catalogue with 0 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-322 Minimum column of MHHS ECS data catalouge updated with 0 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-537 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-322 REP003 | Update Max column of ECS data catalogue with 99.99 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-322 Maximum column of MHHS ECS data catalouge updated with 99.99 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-538 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-323 REP003 | Update Min column of ECS data catalogue with 0 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-323 Minimum column of MHHS ECS data catalouge updated with 0 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-539 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-323 REP003 | Update Max column of ECS data catalogue with 99.99 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-323 Maximum column of MHHS ECS data catalouge updated with 99.99 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-540 | SW |  | 2023-07-14 | Elexon | 2684 | Nigel Rees | Central Body | IF-13 run number | In DES-138, Run Number in IF-013 Interface is 3 chars, yet in Swagger and ECS Reports, this is 7 characters long. We need to update DES-138 to align with Swagger and ECS reports. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Updated IF-013 to show DI-161 (Run number) as number 7 to be consistent with Data Catalogue/ Swagger and Reports | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-541 | MF |  | 2023-07-19 | ESG | 2623 | Patricia Parker | Software Provider | SSC and Profile Class validation | Validation needs to be reviewed to enable the provision of just SSC or Profile Class updates as part of [SSCandProfileClass] event code updates in IF-025 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Updated conditionality on IF-025 and IF-026 for DI-122 (Profile Class) and DI-123 (SSC) to "Mandatory for Traditional Meters (if changing)" to allow just SSC or Profile class updates to be provided. Validation rules updated accordingly in IF-025. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-542 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-159 in data catalogue REP004 | Update Min column with 25 in data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-159 Minimum column of MHHS ECS data catalouge updated with 25 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-543 | MF |  | 2023-07-19 | Design Team |  | Mike Fensome | SRO Design | IHD, SMSO, SSC and Profile Class conditional validation | Update validation rules to ensure effective from date is provided when IHD, SMSO, SSC or Profile class are updated |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Added conditionality to IF-025 and IF-026 that DI-136 should be provided where DI-137 is not null and DI-135 should be provided wher DI-134 is not null. Added validation rules to IF-025 to ensure conditionality rules are applied for IHD, SMSO, Profile class and SSC with new error code of REG1088 -Effective from date must be provided | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-544 | SW |  | 2023-07-19 | Siemens | 2633 | Tony Mason | Software Provider | Level 4 Validation - Multiple response codes | Unclear from the current E2E design defined in E2E001 for a Level 4 Response code, whether a single transaction with concatenated Response codes be sent back to the DIP for notification to the publisher? Or, would the expectation be that multiple messages be returned with each message quoting the published transaction number? Or, is this at the discretion of the participant? The E2E design should make this clearer, and also provide fleixbility for multiple messages to be returned against the same transaction ID with a response. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | This will require updates to the E2E design document to make Level 2 and 4 response code expectations clearer, as well as updated Swagger to allow for an array of messages, help and service tickets to be sent per error, per transaction ID. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.5 | E2E001 E2E Architecture Document Swagger 1.5
MHHS-DIN-545 | ME |  | 2023-07-20 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-496 data type REP004 | Update swagger to show DI-496 as INT (2) |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Update to data type for DI-496 from INT(3) to INT(2) to align with swagger. Update made to MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-546 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Incorrect data item referenced in swagger- REP004 | Incorrect data item referened in R026. SettlementPeriod ID must be replaced with Settlement Period (DI-496) in swagger |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Updated Swagger 1.4 so that R026 references DI-946 (SettlementPeriod) rather than DI-307 (SettlementPeriodID) | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4 | Swagger 1.4
MHHS-DIN-547 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Missing data item in swagger | In R026, DI-327 missing from swagger v1.3. Should added and defined as per DT-22 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Updated Swagger 1.4 to include DI-327 (Deemed Supplier Take). Updated R026 to include DI-327 and remove DI-325 so this aligns with ECS Data Catalogue. | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4 | Swagger 1.4
MHHS-DIN-548 | MH |  | 2023-07-20 | Elexon | 1966 | Rashmi Radhakrishnan | Central Body | Clarification of ISD Transition Requirements | Following MTDSG release of the BRS001 Transition approach and Parallel running requirements v2, ISD would like programme to consider rewording below requirement for more clarity. MHHTR-22 Original: The ELEX-REP-005 Line Loss Factor report will be published at a location on the BSC website/ ELEXON Portal and the URI shall be notified using the Notification of the Publication of a Downloadable Asset IF-047 / PUB-047 to DIP Users prior to M10 and continue post M15. MHHTR-27 Original: The new ISD entities shall be updated be published at a location on the BSC website/ Elexon Portal and the URI shall be notified using the Notification of the Publication of a Downloadable Asset IF-047 / PUB-047 to DIP Users from M10. |  | Closed | [5 empty] | Duplicate - To be tracked under MHHS-DIN-754 | Design Ambiguous | Supporting Docs | ISD Document | ISD Document EDI-021 | ISD Document EDI-021
MHHS-DIN-549 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Incorrect data item referenced in R033 common block | Incorrect data item referenced in R033 - SettlementPeriodID from MDS/VAS should be replaced with SettlementPeriod (DI-496) from ISD, with a MIN value of 1 and Max of 48 in swagger |  | Closed | [5 empty] | Closed- Swagger should keep the min of 1 and max of 50 settlement periods
MHHS-DIN-550 | ME | DIN-659 | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Missing R007 from REP007 | Include R007 within REP007 in swagger |  | Closed | Design misaligned | DIP |  |  |  | Update swagger: Include R007 within REP007 | Swagger | Supporting Docs | Swagger | Swagger | Swagger
MHHS-DIN-551 | ME |  | 2023-07-20 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-083 | Include Min Value of 1 and Max value of 5 to DI--083 in ECS data catalogue to align with swagger and IF data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-083 Minimum and Maximum column updated with 1 and 5 respectively in MHHS ECS data catalouge Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2 | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-552 | SW |  | 2023-07-20 | IMServ | 2356 | Liam Lowey | Software Provider | UTF-8 Encoding for JSON | The E2E001 design document does not specify Encoding for JSON. This needs to be updated to reflect UTF-8 as the JSON Encoding required. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Add UTF-8 as the JSON encoding required in the E2E001 design document, creating a new section 4.2.5. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4 | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-553 | RS |  | 2023-07-20 | Design Team | 2627 | Rob Short | Central Body | Secondary routing for Export | Secondary routing rules need to be updated to allow notification of work prgressed by the Import suppllier (eg disconnection). review required of all related interfaces |  | Closed | [5 empty] | Following review no document changes required. Re Specific case of Disconnection the Link between Import and Export would need to be removed prior to any Disconnection request. If the link remains in place then the DIsconnection request will be rejected by LDSO/REGS.
MHHS-DIN-554 | MF |  | 2023-07-20 | St Clements |  | Madison Layton | Software Provider | Validation on Customer Direct Contracts | Revisions to CDC functionaility. - Amend validation to ensure that only one Customer Direct Contract can be applied against an MPAN at any moment in time - Move CDC process(s) onto a new BP10 process map so as to make it clearer that CDC is MPAN not appointment based - add supporting process info to new BP |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. Process map emailed to particpants - added to BP010E and validation rules for IF-038 updated accordingly. Business requirements updated to align with process Agreed changes with SCS, & RECCO | Design Ambiguous | Supporting Docs | Supporting Docs | BP10 Registration Updates DES138 - Interface Catalogue BRS001 , BRS002 | BP10 Registration Updates DES138 - Interface Catalogue BRS001 , BRS002
MHHS-DIN-555 | MF |  | 2023-07-20 | St Clements |  | Madison Layton | Software Provider | Validation of MPID to DIP ID | Carry out validation of MPID to DIP ID during initial IF-031 validation only. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Set REG1090, REG1091 and REG1092 validation in IF-031 to "No" for Queue processing so it only applies to IF-031 validation. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-556 | KH |  | 2023-07-21 | Stark | 2112 | James Murphy | Supplier | Cumulative/Total Consumption Comparison | The “Cumulative/Total Consumption Comparison” that can be carried out instead of a MAR for meters with integral Outstations is not defined anywhere In BSCP502 it is defined at 4.1.5 – I think this should be lifted and shifted into METH002 Interestingly it appears to be described in the SDS Validation & Estimation Statement (METH001) at 3.12 – 3.16 ADS Method Statement (METH002) needs to be updated |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | ADS Method Statement has been updated with "Reconciliation for smart Meter Advance Reconciliation" section 2.21 - 2.25. | Method statement correction | Supporting Docs | Method Statement | METH002 ADS Validation Estimation | METH002 ADS Validation Estimation
MHHS-DIN-557 | RS |  | 2023-07-21 | Elexon | 2745 | Rashmi Radhakrishnan | Central Body | Consistency of the use of ID | Version 5.1 ISD EDI021 Entity specification document, has discrepancies in the usage of ID, Id, id, etc. Inconsistencies to be addressed when updating the design artefact in the future. ISD Entity M3 Usage of ID and Id - Market Participant ID in the table and description are different ISD Entity ID 17 - DUoS Tariff Id GSP Group Id - ISD Entity ID 17 - DUoS Tariff Id table - GSP Group id is with lowercase "i" and Entity Id M4 Load shape categories : GSP Group Id is mentioned as GSP Group ID ISD Entity ID 17 - DUoS Tariff Id Usage of DUoS Id and DUoS Tariff Id ISD Entity Id 4 and 17 - has ID in capital letter Usage if ID and Id to be consistent Entity M4 GSP Group ID- but should be GSP Group Id ISD Entity Id M5 - MHHS Consumption Component Classes CCC ID - for consistency it should be CCC Id |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | All instances of lower /mixed case id have been replaced with "ID" in caps Also see DIN588 | Data Interface correction | Supporting Docs | Support Docs | ISD Document EDI-021 | ISD Document EDI-021
MHHS-DIN-558 | BK | DI-189 | 2023-07-21 | St Clements | 2011 | Madison Layton | Software Provider | Update response codes in IF-035 | IF-035 routing rules references response codes AC and RJ, this should be A and R |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Updated Routing rules in IF-035 to refer to Response code of "R" and "A" for event code [SDS-MDROutcome] rather than "AC" and "RJ" | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-559 | SC |  | 2023-07-24 | St Clements |  | Sean Cooper | SRO Design | Clarification of Appointment Scenario Code (Linked MPANs) | Added clarification to IF-036 to confirm that the Appointment Scenario Code used for Secondary MPANs will mirror that applied to the Primary MPAN (eg COS/CSP/Etc). What will be applied in the case of Auto Alignment ? |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Added clarification to IF-036 to confirm that the (DI-800) Appointment Scenario Code used for Secondary MPANs will mirror that applied to the Primary MPAN (eg COS/CSP/Etc). In cases of Auto-Alignment of MPANs the Appointment Scenatio of (ALG - Auto Alignment of MPAN Service Providers) will be applied. ALG added as allowable value in DI-800 ( Data Catalogue and Swagger ) | Design Clarificarion | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue Swagger 1.4 | DES138-InterfaceCatalogue Swagger 1.4
MHHS-DIN-560 | SC |  | 2023-07-24 | St Clements |  | Sean Cooper | SRO Design | Design Gap on Sharing MTD in the Case of AutoAlignment of Service Providers | The Design allows for the Auto-Alignment of Service Providers in certain circumstances. However a design gap exists that there is currently no trigger for the outgoing MS to send MTDs to the incoming MS in the case of a pure Auto-Alignment (ie no other MPAN transaction eg. COS/CSP) |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Proposal is to create a new requirements (MS-098 / MS-099) on Smart and Advanced Metering Services to trigger sending of D0149/D0150 (trad) or D0265 (Adv), on receipt of a PUB-037 with De-Appointment Reason Code of “RELATED” or “IMPEXP”. D-Flow(s) should be sent, via DTN, to the new/incoming MS referenced in the PUB-037 flow, where available Issue does not arise for Smart sites as MTDs are fully convayed using the PUB-036. Also not a concern for UMSDS as no MTDs exist. | Design Clarificarion | Minor | MPAN Ownership | BRS-002 Metering Service Requirements | BRS-002 Metering Service Requirements
MHHS-DIN-561 |  |  | 2023-07-24 | St Clements |  | Sean Cooper | SRO Design | Disconnection of Linked MPANs | No change to desgin required. Design confirmation only. SCS have confirmed that it will be necessary to de-link and MPRN before being able to action a disconnection on it. i.e. Disconnection cannot be performed on a linked MPAN until such time as all links have been removed via (IF-019/IF-020) |  | Closed | [5 empty] | No change Required - Clarification Only
MHHS-DIN-562 |  |  | 2023-07-24 | St Clements |  | Sean Cooper | SRO Design | Clarification of IF-014 R0 Population for Event Code [ConsumptionOnDeEnergisedMPAN] | Confirmation at an R0 will be required when issuing an IF-014 with Event Code [ConsumptionOnDeEnergisedMPAN]. DI-979 should be populated with value 'W', DI-980 would remain blank. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | IF-014 updated to clarify that DI-979 should be populated with W. Data Catalouge and Swagger v1.4 updated to reflect this. | Design Clarificarion | Minor | Interface Catalogue | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-563 |  |  | 2023-07-24 | Elexon | 2705 | Ayo O (Helix) | SRO Design | Clarification on Helix Treatment of IF-021 error condition data. | Clarification is required from Helix on exactly how they will manage and process IF-021 messages and how any resulting error/rejections will be managed. This is so that clear guidance can be drawn up on participants should expect to receive errored data etc. In any event design team are clear "the data returned in the IF-014 must only be that data which is rejected." |  | Closed | [5 empty] | A response was provided to Ayo on 24/07 by design team. Follow up email has been sent for Ayo to confirm whether issue is resolved, thus closing the DIN or whether a call is required with Design team for further resolution. DIN closed as no response received from Ayo. It is our assumption the feedback provided by the design team was sufficient. | Design Clarificarion
MHHS-DIN-564 | SW |  | 2023-07-17 | SIMS | 2704 | Martin Freeman | Central Body | Mandatory Nullable on Swagger | Is Mandatory Nullable (which is how 'optional' properties are described in the DES138) supposed to be marked as Required & nullable in Swagger? Or should these Mandatory Nullable (optional) properties be marked 'not Required' in Swagger? In some interfaces Mandatory Nullable properties are marked 'not required' in Swagger while in others they are 'nullable required'. Need to ensure this is applied consistently across all Interfaces. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Need to update Swagger implementation so mandatory nullable is treated consistently across all Interfaces as this is not always consistent. Need to updated E2E001 to provide additional clarity on how this applies to Swagger. Need to ensure DES-138 is aligned. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | Swagger 1.5 | Swagger 1.5
MHHS-DIN-565 | SW |  | 2023-07-25 | MHHS | 2763, 2713 | Steve Weston | SI Design | Version and Schema Interoperability across environments. | Versioning is covered in Section 8.4 and 8.5 of the E2E001 design, that covers the differences between major, minor and patch versions of an API, the URL required as well as schema versions that are contained in the common block of an Interface. There is confusion around how this will work across different environments so we need to provide additional clarity on the Swagger API versions / Schema versions that must be supported by the DIP and MP’s, alongside scenarios that are envisaged. This will provide information on version uplifts, interoperability required and how long different versions of API / Schemas will be supported for. This needs to covers scenarios where within an environment, we have multiple versions of an API within an environment ie, we may be required in some cases to be backwards compatible with previous versions -- for example -- if we received and processed earlier versions, we can respond with the latest live version. E.g. if we receive PUB-005 on version 1.0.0 we could respond with IF-006 on version 1.0.1 and would not be expected to respond with version 1.0.0. |  | Open - awaiting assessment | Design gap | TBC |  | Post Go-live Release | 0 | Need to provide updates to Section 8.4 and 8.5 to ensure we cover worked examples across different environments for both API versions and Schema versions, interoperabilty required, transition between versions, BAU vs Testing phases and expectations on DIP and MP's. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger
MHHS-DIN-566 | SW |  | 2023-07-25 | MHHS | 2549 | Steve Weston | SI Design | E2E NFR's need to be refined based on actual data | Section 3.1 of MHHS DES001a MHHS Data Integration Platform – Functional Specification – Appendix A Transaction Volumes states that the indicative size of an IF-021 (single days' worth of UTC SP data) is between 1 and 2 KB. The equivalent IF-021s we have successfully submitted to the DIP Simulator are ~4.5 KB as observed in webhook. Can you confirm that this increase in size has been factored into the non-functional requirements? |  | Closed | Clarification - No change required | DIP Users |  |  |  | Agreed to be closed. Volumetrics document has been updated to reflect updated file sizing. This is for guidance only and depends on IF-021 consumptions per transaction. | Design Ambiguous | Supporting Docs | MHHS E2E004 Solution Architecture - Transaction Volumes | MHHS E2E004 - End to End Solution Architecture– Transaction Volumes IF-021 | MHHS E2E004 - End to End Solution Archiecture– Transaction Volumes IF-021
MHHS-DIN-567 | SW |  | 2023-07-25 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - Swagger Incorrect | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4. Swagger 1.4 needs to be updated so that it aligns with DES-138. DI-081 to be updated to periodDuration. DI-086 to be updated to supplierEffectiveFromDate. DI-121 to be updated to supplierEffectiveToDate. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Need to update mismatch between Swagger YAML definition in DES-138 and Swagger 1.4. Swagger 1.4 needs to be updated so that it aligns with DES-138. DI-081 to be updated to periodDuration. DI-086 to be updated to supplierEffectiveFromDate. DI-121 to be updated to supplierEffectiveToDate. | Design Ambiguous | Supporting Docs | Swagger 1.4 | Swagger 1.4 | Swagger 1.4
MHHS-DIN-568 | SW |  | 2023-07-26 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - DES-138 incorrect | DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) shows in YAML as secondaryRecipientDIPID and primaryRecipientDIPID respectively and this should be updated in DES-138 YAML column so this aligns with Swagger 1.4 ie, DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) shows in YAML as secondaryRecipientDIPID and primaryRecipientDIPID respectively and this has been updated in DES-138 YAML column so this aligns with Swagger 1.4 ie, DI-981 (secondaryRecipients) and DI-982 (primaryRecipients). | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-569 | SW |  | 2023-07-26 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - DES-138 incorrect | DI-047, DI-049, DI-210, DI-211 and DI-820 are defined in the Data Catalogue, but not used in any Interfaces so need to be removed from the latest version of DES-138. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-047, DI-049, DI-210, DI-211 and DI-820 are defined in the Data Catalogue, but not used in any Interfaces so need to be removed from the latest version of DES-138. DES-138 needs to be updated to remove these items. | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-570 | MF |  | 2023-07-26 | MHHS |  | Mike Fensome | SRO Design | IF-021 validation rules | IF-021 validation rules need to be updated to align to the MDS and LSS Method statements which include validation for de-energised sites. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | IF-021 Added validation to align with MDS/LSS method statements where estimated data is provided on a de-energised site (ECS1008 - SP End Date/Time [DI-082] contains non-actual consumption for ECS De-Energised MPAN) | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue | DES138-InterfaceCatalogue
MHHS-DIN-571 | SW |  | 2023-07-27 | Callisto | 2762 | Dave Peat | Software Provider | Inconsistency for DI-980 Response Message(s) | For DI-980, the YAML name is responseMessages, however in Swagger, there is inconsistencies: R0.responseMessages - this is defined as array of DI-980 (responseMessages) B066.responseMessage - but defined as responseMessages (defined as DI-980 - single) B092.responseMessage - defined as responseMessage (defined as DI-980 - single) We need to update DES-138 / Swagger so there is consistenct application of the words responseMessage (for single response) vs responseMessages (where there is an array of responses). |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | I have updated Swagger 1.4 so that DI-980 definition is applied consistently for single response vs array of responses. For single, it will be responseMessage. For an array of messages, it will be responseMessages. To this effect, B066.responseMessages has been updated to be responseMessage. Also, B066 block has been updated to align with DES-138 to be conditionally mandatory, rather than mandatory. | Supporting Docs | Design Ambiguous | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-572 | SC |  | 2023-07-27 | MHHS |  | Sean Cooper | SRO Design | Clarification of IF-013 Issuance (also Ref DIN610) | DUPE WITH DIN-610 ~ Clarification is requiired on the circumstances when Helix will issue IF-013. 1. IF-013 is only issued as part of the RF Run i.e. simply to notify Suppliers of what the default consumption for a period(s) is, where no data has been submitted by the DS come the point of RF. Should suppliers wish to derive this for pre-RF settlement runs then they are able to do so easily enough using the own data and the published Load Shapes. 2. The second view is that the IF-013 is issued on every settlement run undertaken for sites where no PUB-021 data has been received DIP impact concerns wrt to volumes of IF-013 would need to be addressed if Option 2 is the position. |  | Closed |  |  | 2023-09-13 |  |  | Duplicate of DIN-610 | No Change
MHHS-DIN-573 | ME |  | 2023-07-27 | MHHS |  | Kevin Spencer | SRO Design | Update to step 40 of ISD BPM/BPD | Step 40 of MHHSP-BP021 and BPD021 currently ambigious Can the intention of this step be made clearer.? |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Step 40 of ISD BPM and BPD have been updated to say 'Issue ISD Change Notification' to make ithe purpose of the step clearer. | Design Ambiguous | Minor | Supporting Docs | MHHSP-BP021 Industry Standing Data MHHSP-BPD021 Industry Standing Data Business process Descriptions | MHHSP-BP021 Industry Standing Data MHHSP-BPD021 Industry Standing Data Business process Descriptions
MHHS-DIN-574 | SC |  | 2023-07-27 | St Clements |  | Madison | SCS | Change Of Logic on Smets 1 Number of Digits | Smets 1 Number of digits can be 0 - 9 Replaces previous logic. |  | Closed | [5 empty] | DIN CLOSED as agreed with St Clements and RECCo. DIN-615 supercedes this DIN. The text has been updated as suggested below from RECCo, ‘Where the Meter Type is S1, the value should be populated as per the manufacturer specification.’ However, the logical test for SMETS1 in the DES-138 Interface Catalogue will remain unchanged. DIN-615 also includes updating the Swagger validation of this field to match SCS logical test i.e. value can be 0-9. | No Change
MHHS-DIN-575 | SC |  | 2023-07-27 | St Clements |  | Madison | SCS | Requirement for REGS to process IF-040 | SCS would prefer not to process IF-040 now that AC is provided to EES Directly via the DIP. In additional what is the IF-040 processing schedule? IF-040 is only sent to appointed Suppliers and Data Services on a 30 day cycle. There could be a 30 day wait until the next MDS generated IF-040. Programme Design: To fill this design gap the programme has made MPRS responsible to load the IF-040 by populating Annual Consumption in the B027 Block on IF-002, IF-001 & IF-036 MPRS Issue: An IF-040 for every energised MPAN must be loaded adding significant overhead to processing. The 24 hr SLA could be difficult to meet without significant hardware investment. | CR039 | Implemented | Change Request | LSDO (SCS), DIP |  | Interim Release 8 | 2024-03-20 | To minimise change and impact on all other participants B027 Block is retained in IF-001, IF-002 & IF-036, but will never need to be provided by Registration Service as it is only required where the data exists in Registration Service. Annual consumption requirements document updated to remove the requirement for REGS to receive PUB-040 and maintain Annual Consumption. BP005 and BPD005 updated to remove REGS receiving Annual Consumption. REGS removed from IF-040 secondary routing in DES-138. On Appointment, Data Service and Supplier will receive the latest PUB-040 with their PUB-036. DIP will be changed to replay the PUB-040 from the Message Archive. Note added to BP003. Change in IR5 SIT Scope to exclude B027 Block Loading for Supplier and Data Services. Remove testing of IF-040 Processing for MPRS Change in IR8 SIT Scope to add DIP IF-040 Replay on Supplier and Data Service Appointment Confirmation | Data interface correction | Supporting Docs | Interfaces | DES138 BP003 BP005 BPD005 BRS012
MHHS-DIN-576 | MF |  | 2023-07-27 | St Clements |  | Madison | SCS | Cancelling appointments in advance of receipt of PUB-034 | SCS have requested that the design is updated to allow for issuing of a PUB-035 'Lapsed' message, if a switch is 'Cancelled' or otherwise superseded, even prior to issuing / processing of a PUB-034 from the Metering Service or Data Service. ​ |  | Closed | [5 empty] | Following DRG on 4th Aug, it was agreed that St Clements Services were to work-up the topics discussed, and a dedicated workshop would be arranged to discuss this further. St Clements Services have advised the Programme that they will now not be pursuing proposals made at the DRG session and would be reverting to implement to the original design, therefore closure of this DIN.
MHHS-DIN-577 | SW |  | 2023-07-27 | Callisto | 2979 | Neil Edney | Software Provider | DT-983 and DT-000 are missing IF-040 / PUB-040 | DT-983 and DT-000 are missing IF-040 / PUB-040 in Swagger. IF-003, 19, 20 and 50 also need to be added to align with DES_138. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Need to update Swagger to include IF-040 and PUB-040 in DT-000 and DT-983. I’ve added IF-003 / 019 / 020 / 040 / 050 to DT-000 in Swagger and PUB-003 / 019 / 020 / 040 / 050 to DT-983 in Swagger | Supporting Docs | Design Ambiguous | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-578 | SB |  | 2023-07-28 | RECCo | 2943 | Jonny Moore | Central Body | EFDs, ETDs and Supplier information for Related and Import/Export Linkages | We’ve noticed through the design and build stage of EES that we are not being communicated the EFD and ETD of a Related MPAN set-up or an Import / Export Linkage. Nor are we being informed of the Supplier responsible for creating a Related MPAN relationship. This information is not currently being published in the IF020/PUB020 However, this information is currently available for market participants to view on EES. We had some feedback in the REC MSAG that participants would like to continue to view these items in EES and wonder if this is worth a DWG discussion? |  | Closed | [5 empty] | RECCo notified on DIN closure. The Effective From date is not currently shared on the D0386 which was the basis for the IF-019/PUB-020. If EES requires an EFD suggest that the transaction date from the header is used. These updates can only be made by the current Supplier. | No Change
MHHS-DIN-579 | SB |  | 2023-07-28 | ENWL | 2444 | Paul Stancliffe | Network Operator | PUB-043 Routing discrepancy | Trying to map flow PUB-43 to our TO BE business processes as these flows are showing on the MHHS - Interface Data Item Catalogue as routing to LDSO. However when trying to align these to the Business Process Diagram BPM011- Change of Connection Type and / or Market Segment V5.0 PUB-43 is not routing to LDSO |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | BP011B from Step 542 new flow for PUB-043 to LDSO new step Manage Change of Connection type Notification | Process Model correction | MPAN Ownership | Supporting Document | BP011B BPD011 | BP011B BPD011
MHHS-DIN-580 | RS |  | 2023-07-28 | RECCo | 2719 | Sarah Jones | Central Body | Late or Missing Secured Active Messages | understand the approach to managing CSS issues where secured active messages are not received within the expected secured active processing window. We understand the standard ‘happy path’ processing requires secured active notifications to be issued by CSS after the 5pm gate closure window the day before the registration effective from date. However, it was acknowledged when the MHHS design was originally baselined that some notifications may arrive late e.g. after 6pm, or not at all. Rather than developing operational provisions to deal with missing / late secure active notifications, this was highlighted as a risk for later consideration, on the basis the CSS arrangements were still new and the enduring BAU process was subject to change. In light of the CR018 approval, we believe this is now the time to clarify the approach to be taken where CSS notifications are missing or late. |  | Closed | [5 empty] | The Design Team and SRO are actively engaged with St Clements on issues around problematic switches. The plan is for them to provide us with a list of of their issues. We will then go through a process of raising these directly with CSS. Dependent on outcomes we receive back, we will look to discuss this with St Clements with the possibility of raising a CR for a specified data correction tool to align the data and send out the appropriate MHHS flows. | No Change
MHHS-DIN-581 | RS |  | 2023-07-28 | ESG | 2924 | Patricia Parker | Software Provider | Meter Location in DES138 | Currently DI090 in DES138 states 'Values as Per ISD'. These values are not held in ISD, therefore the reference should be changed to 'see Enum Values of the Data Catalogue' - example IF-005 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Updated population notes for DI-090 to refer to Data Catalogue, IF's 2,5,6,20.33.36,61,62 | Clarification | Supporting Docs | Interfaces | DES-138 Interface Spec | DES-138 Interface Spec
MHHS-DIN-582 | MF |  | 2023-07-28 | Ovo |  | Chris Butterfiled | Supplier | Clarification following CR15 | Supplier Overview requirements v5.1: this refers specifically to Economy 7 / Economy 10 tariffs; we suggest this should be more general and refer to any Time of Use tariff / tariff with switched load to include other variants such as Smart Economy 9 etc. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Updated SU-163, SU-164 and SU-165 to refer "for switched load tariff (eg. Economy 7/Economy 10) sites" rather than Economy 7/Economy 10 sites | Requirement correction | Supporting Docs | supplier requirements | MHHSP-BRS004 Supplier Overview | MHHSP-BRS004 Supplier Overview
MHHS-DIN-583 | SB |  | 2023-07-31 | Stark | 2891 | Jon Dennis | Data Service Provider | BP005 Read Sharing for Data Service | can you provide clarification around BP005 Read Sharing for the Data Service, in particular this section of MHHSP-BP005-Data Processing-v5.1 Question: Is the entry point to this section either: Regular Data Collection, e.g. daily remote collection for ADS/SDS Smart? Trigggered by an external process, e.g. Change of Energisation BP009? To answer the above, please can you list all of the processes that lead to Step 170 in BP005. May I also suggest updating BP005 to include this information, perhaps by adding a Step description to the entry point from Data Collection as shown above. Related Question: In BP009 the Data Service is expected to progress to BP005 Step 185. However, unless I am mistaken, BP005 V5.2 does not include Step 185. Please update BP009 with a valid onward step. |  | Open - awaiting assessment | Clarification - No change required | Smart Data Services, Advanced Data Services |  | Post Go-live Release | [5 empty] | BP005
MHHS-DIN-584 | SC |  | 2023-07-31 | Design Team |  | Sean Cooper | SRO Design Team | DI-511 Change of Data Type from String to Number in IF-024 | DI-511 Off Peak Declaration Proportion has been changed from String to Number so as to allow for improved Swagger validation of this data item. The new Number val will have a Minimum value = 0 and a Maximum Value = 100. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-511 Off Peak Declaration Proportion has been changed from String to Number so as to allow for improved Swagger validation of this data item. The new Number value will have a Minimum value = 0 and a Maximum Value = 100. (IF-024). Data Catalogue updated accordingly. | Improved Validation of Data Item | Minor | Interface Catalogue | DES-138 Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-585 | SC |  | 2023-07-31 | Design Team |  | Sean Cooper | SRO Design Team | Clarification on IF-024 | Clarification update to confirm that B097 Off Peak Declaration is Mandatory only for Event Type [SN-OffPeakDec] |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Clarification update to confirm that B097 Off Peak Declaration is Mandatory only for Event Type [SN-OffPeakDec] | Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-586 | SW | DI-204 | 2023-07-31 | Callisto | 2762 | Neil Edney | Software Provider | Mis-alignment between D0 block YAML in Swagger and DES-138 | DES138, the D0 has the following YAML names which do not align DIPCorrelationID, DIPTimeStamp, DIPTransationID However, swagger has these: initialCorrelationID, transactionTimestamp, transactionID |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Updated DES138 Data Catalogue D0 Common block data items so that YAML names in DES-138 now align with Swagger initialCorrelationID (DI-987), transactionTimestamp (DI-989), transactionID (DI-990) | Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-587 | SW |  | 2023-08-01 | Kraken | 2973 | Angelos Rizoyannis | Software Provider | Mis-alignment between R0 mandatory in Swagger vs DES-138 | In DES-138 in the following interfaces, R0 is marked as mandatory, but not mandatory in Swagger - IF-006, IF-008, IF-014, IF-020, IF-026, IF-028, IF-032, IF-039. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | In DES-138 in the following interfaces, R0 is marked as mandatory, but not mandatory in Swagger - IF-006, IF-008, IF-014, IF-020, IF-026, IF-028, IF-032, IF-039. Update R0 to be mandatory in these interfaces. | Clarification | Minor | Interfaces | Swagger 1.5 | Swagger 1.5
MHHS-DIN-588 | ME |  | 2023-08-02 | Design Team |  | Kevin Spencer | Programme Design | Update of ID to Id | A request has come from Elexon to update the ISD Entities document. Id should be changed to ID |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | All instances of Id have been changed to ID (see also DIN 557) | Supporting Document | Minor | Supporting Document | MHHSP_EDI021_ISD_Entities v5.3.2 | MHHSP_EDI021_ISD_Entities v5.3.2
MHHS-DIN-589 | SB |  | 2023-08-02 | Stark | 2466 | Jon Dennis | Data Service Provider | ADS and SDS Estimation Statements | I have been studying the following two documents: Advanced Data Service Validation and Estimation: Methodology Statement (MHHSP-METH002_ADS_Validation_Estimation v5.1) Smart Data Service Validation and Estimation: Methodology Statement (MHHSP-METH001_SDS_Validation_Estimation v5.1) In particular, Section 3 of the ADS_Validation_Estimation document details the estimation methods where the customer has opted-out of UTC Period consumption data. It references the SDS_Validation_Estimation document where Estimation methods are in Section 7. The 2 method statements have become misaligned when changes to the SDS method statement was updated. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | We will align the ADS method statement with the SDS method statement to keep it uniform. | Method statement correction | Supporting Docs | Method Statement | ADS Method Statement | ADS Method Statement
MHHS-DIN-590 | KH |  | 2023-08-03 | Design Team | 2717 | Martin Freeman | Central Body | Update Role Codes in E2E001 | There is a mismatch between roles codes that are in DES-138 and those that are in E2E001. Role code for Unmetered Supplies Data Services changed from UDS to UMSDS. Need to ensure that all of the role codes referenced in DES-138 are included in E2E001 and that there is a full explanation of what these are. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update all the role codes referenced in DES-138 to ensure they are included in E2E001 and that there is a full explanation of what these are. | Data interface correction | Supporting Docs | Interface Catalogue | E2E001 E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-591 | KH |  | 2023-08-03 | Elexon | 2974 | Michael Ceney | Central Body | Update to MDS Method statement | The MDS Method Statement Section 2.1 should read: If today > MDS Run Date (RF) for SP End Date/Time [DI-082] in the Master Settlement Table in ISD ECS1003 - SP End Date/Time [DI-082] has already passed "MDS Run Date (RF) [ISD.RunDate-RFDate] |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update DES138 and MDS Method Statement Section 2.1 to read "If today > MDS Run Date (RF) for SP End Date/Time [DI-082] in the Master Settlement Table in ISD ECS1003 - SP End Date/Time [DI-082] has already passed "MDS Run Date (RF) [ISD.RunDate-RFDate]" update ECS1003 in 00-introductions and IF-21 | Data interface correction | Supporting Docs | Supporting Docs | MDS Method Statement MHHSP-DES138-Interface Catalogue | MDS Method Statement MHHSP-DES138-Interface Catalogue
MHHS-DIN-592 | SW |  | 2023-08-03 | Design Team | 2717 | Martin Freeman | Central Body | Update StatusMessage and StandardResponseBody in E2E001 to provide more clarity | There are inconsistencies between StatusMessage / Standard Response body definitions for what is contained with E2E001 and Swagger, these need to be aligned. Clarity needs to be provided on how TransactionID is populated in Status Message for Level 2 validation and Level 4 validation and for Level 4 validation, how this is sent to original sender. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Align inconsistencies between StatusMessage / Standard Response body definitions for what is contained with E2E001 and Swagger. Provide clariry on how TransactionID is populated in Status Message for Level 2 validation and Level 4 validation | Data interface correction | Supporting Docs | Interface Catalogue | E2E001 MHHSP-DES138-Interface Catalogue | E2E001 MHHSP-DES138-Interface Catalogue
MHHS-DIN-593 | ME |  | 2023-08-04 | Design Team |  | Kevin Spencer | Programme Design | Update to AC Method Statement | Update required to the AC Method Statement to amend calculation where less than 365 days of data is available and a change to section 2.2 to allow calculations to be undertaken on Calendar days |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | The following changes below in red have been made to section 2.2 of the AC Method Statement The Market-wide Data Service (MDS) should schedule the calculation of MPANs requiring a new Annual Consumption for active MPANs evenly across each working day of the month and publish on the day the day of the calculation. The recalculation shall be performed each month, for every MPAN and every 30 Calendar days +/- 5 Calendar days of the date of the previous calculation. Changes to the calculation of less than 365 days available are no longer reuried as agreed with Helix | Method statement correction | Supporting Docs | Method Statement | Annual Consumption Meth 10 | Annual Consumption Meth 10
MHHS-DIN-594 | SC | SCS DI-207 | 2023-08-04 | Design Team |  | Sean Cooper | Programme Design | Correction to BP10 Related MPANs | Rejection was incorrectly shown being sent direct from REGS rather than from REGS Via DIP. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Rejection was incorrectly shown being sent direct from REGS rather than from REGS Via DIP. moved the starting point from step 340 to step 360 for rejections on BP010B | Process Model correction | MPAN Ownership | Supporting Document | BP010-Registration Updates | BP010-Registration Updates
MHHS-DIN-595 | SC | SCS DI-208 | 2023-08-04 | Design Team |  | Sean Cooper | Programme Design | Correction of Type in ISD Doc Table 16 | Correction of type in definition of subscript 3 for table M16 - "Market Participant ID" changed to "Market Participant Role" |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Correction of type in definition of subscript 3 for table M16 - "Market Participant ID" changed to "Market Participant Role" | Clarification | Supporting Docs | supporting document | MHHSP_EDI021_ISD_Entities | MHHSP_EDI021_ISD_Entities
MHHS-DIN-596 | SC |  | 2023-08-04 | Design Team |  | Sean Cooper | Programme Design | Clarification of SP Appointment Time(s) | Per DRG decision all SP Appointment times shall be effective from Midnight UTC Time. Clarification added to IF-031/If-036 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Added validation rule to IF-031 to ensure appointments are made at midnight [UTC/Clock]. Pending agreement from Working Group and DAG. | Clarification | Supporting Docs | Interfaces | DES-138 Interface Spec | DES-138 Interface Spec
MHHS-DIN-597 | SC | SCS DI-193 | 2023-08-07 | MHHS |  | Sean Cooper | SRO Design | IF-026 B068 Presence | IF-026 / B068 - SCS requested removal of wording "must be required for smart meter removed" as this is inherent as part of the Event Type. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | IF-026 / B068 - SCS requested removal of wording "must be required for smart meter removed" as this is inherant as part of the Event Type. | Clarification | Supporting Docs | Interface Catalogue | DES-138 Interface Spec | DES-138 Interface Spec
MHHS-DIN-598 | SC | SCS DI-176 | 2023-08-07 | St Clements |  | Madison Layton | Software Provider | Incoming Supplier Notifications - Clarification | SCS raised a query around whether certain flows should be copied to an incomming Supplier (PUB-006, PUB008 etc. etc.) The current design does not include copying of these flows to an incoming supplier, (not represented in either Requirements or BP maps). IF-036 (and accompanying D-flows as required) provides suppliers with a clear starting point containing all the information they need to support servicing the customer. Design Team feel any change in this area would require a CR. |  | Closed | [5 empty] | Any change in this area would require changes to the REGS Requirements to implemnt Primary Routing, as copying of such flows could not be performed by DIP Secondary Routing. CR would be required to confirm new requirements and allow for IA on REGS and Suppiers design. Design Team also note that no other issues/DIN raised on this issue, by suppliers or other participants. | Clarification | Clarification - No change Required
MHHS-DIN-599 | BK | SCS DI-198 | 2023-08-07 | St Clements |  | Madison Layton | Software Provider | Data Cleansing required on IHD, SMSO and Installation Date | SCS raised a a query on the three items below that are not under the Data Cleanse Plan that may need cleanse work. 1) IHD - Should be populated for smart meters, and only smart meters (not currently validated) 2) SMSO - Should be populated for smart meters and only smart meters (not currently validated) 3) Installation date - Should not be prior to MPAN Creation date (Legacy data integrity issues of meters migrated into MPRS) |  | Closed | [5 empty] | This change has been forwarded onto the Data Cleansing Working Group as it is not a design issue. Design Team also advised SCS to raise these issues within the working group. | Clarification | Clarification - No change Required
MHHS-DIN-600 | ME |  | 2023-08-07 | Elexon | 4566 | Rashmi Radhakrishnan | Central Body | ISD Entity M18 Discrepancy | In the ISD Entity Document the table shows {Effective From Date {DIPRole} and {Effective To Date {DIPRole}, however the exmaple table and column details have been titled as {Effective From Date {MP2DPM} and {Effective To Date {MP2DPM}. These should be changed to align with the first table in entity M18 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Corrected M18 Col Headings and column name references to read "DIPRole" | Data interface correction | Supporting Docs | supporting document | MHHSP_EDI021_ISD_Entities | MHHSP_EDI021_ISD_Entities
MHHS-DIN-601 | SW |  | 2023-08-07 | Kraken | 4485 | Adrian Serban | Software Provider | Incorrect on M0 common block in IF-018 | In Swagger, it appears the block is correct (M0), but the label is incorrect (M1) for IF-018. The label needs to be updated to M0 to align with the block. This needs to be updated in Swagger so the label is incorrect. In IF-019 and IF-020, there is an inconsitency of use of M1 vs M0. |  | Closed | [5 empty] | M1 is used in IF-019 and IF-20. M0 is used in all other IFs where required. Swagger version 1.4 has been reviewed and correctly reflects this position. | No Change
MHHS-DIN-602 | RG |  | 2023-08-08 | Design Team |  | Rob Golding | Programme Design | Add Interface, Event Code enumeration to Swagger for interface blocks | Interface and Event code validation and alloawable blocks is missing from the DIP. Rather then getting Avanade to code these dependencies the proposal is to intoduce the restrictions into the Swagger |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update the swagger for the majority of interfaces where different event codes require different combinations of optionality for the blocks they reference. An example of this has been done already for IF-001 in the new swagger file Interface-001. | Improved error trapping at interface | Minor | Interfaces | Swagger 1.5 | Swagger 1.5
MHHS-DIN-603 | SW |  | 2023-08-09 | Design Team | 4022, 4700 | Steve Weston | Central Body | Clarity on A0 block being removed | Section 4.2.1 of the E2E001 design has a diagram that shows that the A0 common block is removed by the DIP prior to sending out the message to onward particpants. This is inconsistent with the rest of the design. Section 4.2.1 needs to be updated so that this shows A0 not being removed. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update Section 4.2.1 of E2E001 figure 4 so that this shows A0 not being removed | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger 1.4 | E2E001 E2E Architecture Document Swagger 1.5 | E2E001 E2E Architecture Document Swagger 1.5
MHHS-DIN-604 | SW |  | 2023-08-09 | Design Team | 4945 | Steve Weston | Siemens | Clarity on B066 mandatory on IF-035 | In DES-138, B066 block in IF-035 is shown as mandatory and also defined as mandatory in Swagger. This should be conditionally mandatory as per B019, so this needs to be updated to conditionally mandatory in DES-138 and also in Swagger 1.5. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update B066 block in IF-035 to mandatory where event code DCC-MDR Outcome Swagger 1.5, no change in DES138 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 | Swagger 1.5
MHHS-DIN-605 | SC |  | 2023-08-09 | Design Team |  | Sean Cooper | Programme Design | Update "Switch Cancellation" Info Message Box of BP002 & BP003 | Message updated to make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations received prior to PUB-34 processing will be managed by normal queue processing. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Message updated to make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Where in the rare scenario a cancellation is received and accepted by the Registration Service before the PUB-034, the Registration Service will not lapse on receipt of the cancellation, instead re-validation the day prior to the appointment start date would trigger a lapse. | Clarification | MPAN Ownership | process | BP002 / BP003 Change of SP | BP002 / BP003 Change of SP
MHHS-DIN-606 | SC |  | 2023-08-09 | Design Team |  | Sean Cooper | Programme Design | Update Ops C to include clarification on issuing of IF-035 | Make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations received prior to PUB-34 processing will be managed by normal queue processing. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update OPS Choreography document (Foot-note to OPC-190) to clarify processing of IF-035 (See DIN-605) | Clarification | Supporting Docs | Supporting Document | MHHSP-OPC001 Operational Choreography | MHHSP-OPC001 Operational Choreography
MHHS-DIN-607 | SC |  | 2023-08-10 | St Clements |  | Sean Cooper | Programme Design | Update IF-035 Lapsed Reason Code | SCS Request Update IF-035 Lapsed Reason Code from "Switch Cancelled" to "Registration Cancelled" |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Updated IF-035 Lapsed Reason Code LP004 from "Switch Cancelled" to "Registration Cancelled" | Clarification | Minor | Interfaces | DES-138 Interface Doc | DES-138 Interface Doc
MHHS-DIN-608 | SC | SCS DI-206 | 2023-08-10 | St Clements |  | Sean Cooper | Programme Design | Correction of Inaccuracy on BP003 | Steps 86,87,88 added to better reflect that REGS will actually send TWO IF-035 messages not just one. IF-035 [SendMTD] will be issued to Incumbent MS and [AppOutcome] event will be issued to DS/Supplier. BP003 now mirrors the drafting in BP002. There is no change in underlying requirement here - redrafting is simply a more accurate representation of REGS activity. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Steps 86,87,88 added to better reflect that REGS will actually send TWO IF-035 messages not just one. IF-035 [SendMTD] will be issued to Incumbent MS and [AppOutcome] event will be issued to DS/Supplier. BP003 now mirrors the drafting in BP002. | Clarification | Minor | Interfaces | BP003 | BP003
MHHS-DIN-609 | SC |  | 2023-08-10 | Helix |  | Sean Cooper | Programme Design | Helix Issuing of IF-040 Annual Consumption Messages | Discussion held with Helix on proposed approach to issuing IF-040 messages. Current design suggests that messages should only be issued on Working Days - Design Team are exploring why this is the case (risk of substantial peak esp on 4 day long weekends). preference would be for Helix to issue IF-040 on each calendar day. |  | Implemented |  |  | 2023-09-13 | Interim Release 5 | 2023-09-20 | Update the OpsC document to set a 24hr rather than a 2hr limit around processing the IF-040 interfaces only | Clarification | Supporting Docs | Supporting Document | OPS Choreography | OPS Choreography
MHHS-DIN-610 | SC |  | 2023-08-10 | Helix |  | Sean Cooper | Programme Design | Clarification of IF-013 Functionality (also ref 572) | 1. IF-013 is only issued as part of the RF Run i.e. simply to notify Suppliers of what the default consumption for a period(s) is, where no data has been submitted by the DS come the point of RF. … … Should suppliers wish to derive this for pre-RF settlement runs then they are able to do so easily enough using the own data and the published Load Shapes. Need to validate if IF-013 should be issued after each Settlement Run OR only after RF Run. Also need to validate the IF-10 should NOT be issued after II Run. 2. The second view is that the IF-013 is issued on every settlement run undertaken for sites where no PUB-021 data has been received DIP impact concerns wrt to volumes of IF-013 would need to be addressed if Option 2 is the position. Dupe with DIN-572 |  | Implemented |  |  | 2023-09-13 | Interim Release 5 | 2023-09-20 | Following Review at DRG meeting - agreement reached that IF-013 should NOT be sent for the II Run and should only be issued for SF and later Runs. DES-138 IF-013 Additional notes updated to reflect this decision. ----- MDS Method statement also requires update to record this decision. The following text has been added to the Method Statement Restrict sending of IF-013 until the SF Settlement Run The following statement has been added to the MDS Method Statement section 9.2 The sending of IF-013 will be restricted until the SF Settlement Run | Clarification | Supporting Docs | Supporting Document | DES-138 Interface Catalogue MDS Method Statement | DES-138 Interface Catalogue MDS Method Statement
MHHS-DIN-611 | KH |  | 2023-08-11 | Elexon | 3986 | Michael Ceney | Central Body | Changes required to MDS Method Statement | Following the release of DIN-332, changing EventCode [ConsumptionOnDe-energisedMpan], the MDS Method Statement needs updating to reflect this change. Section 9.3 states that the an exception report will be provided using IF-013, this needs to show IF-014 is to be used. Please can a new DIN be raised. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | We will update section 9.3 to state that the report will be provided using IF-014. | Method statement correction | Supporting Docs | Method Statement | MDS Method Statement | MDS Method Statement
MHHS-DIN-612 | SC | PDA Test Issues | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | New IF-019 Validation Rules Re Unmetered Related MPANs | Added x2 new validtion rules to prevent the creation / addition of Related MPANs with a Connection Type of "U - Unmetered". No validation applied to remove so as to allow for the resolution of any historically erroneous links |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Added x2 new validation rules to prevent the creation / addition of Related MPANs with a Connection Type of "U - Unmetered". No validation applied to remove so as to allow for the resolution of any historically erroneous links | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-613 | SC |  | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Remove Reference to SP Appointment Start Time(s) | In line with DRG Decision on 4th Aug - it was agreed that ALL Service Provider Appointments should commence at Midnight UTC. Text against DI-086 and DI-121 has been removed. A new section addressing the treatment of Time has been added to the Additional Information tab of DES-138 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | In line with DRG Decision on 4th Aug - it was agreed that ALL Serive Provider Appointments should commence at Midnight UTC. Text against DI-086 and DI-121 has been removed. A new section addressing the treatment of Time will be added to the Additional Information tab of DES-138 as part of Interim Release 5 (DIN-614) | Design Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-614 | SC |  | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | Create new "Time" Advisory Notes in Registration Additional Info Section | SC to create Treatment of Time section |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Add clarification on Regs Notes tab. around appointment time and Transfer read time. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-615 | SC |  | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Number of Registers Validation | Clarification following on from DIN-574. Text against Number of Register Digits fields amended to say "per the manufacturer specification" . Note text for SCS validation will remain unchanged. Swagger validation of this field updated to match SCS logical test ie value can be 0-9 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Clarification following on from DIN-574. Text against Number of Register Digits field amended in IF-002, IF-005, IF-006, IF-033, to say "per the manufacturer specification". Note text for SCS validation will remain unchanged. Swagger validation of this field updated to match SCS logical test ie value can be 0-9. | Design Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-616 | SC |  | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | Review of COS Transfer of Readings Process Required in light of SP UTC Decision | A Review of BP003C is required to impact assess implications of SP UTC Decision |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | BP003C may need updating follow impact assessment | Clarification | Supporting Docs
MHHS-DIN-617 | SC | PDA Test Issues | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | Note on Discretionary Use of IF-023/IF-040 by Data Service | Missing interface notes on Discretionary Use of IF-023/IF-040 by Data Service |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Added interface notes to clarify Annual Consumption usage in IF-040 and Load Shape Totals in IF-023 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-618 | KH |  | 2023-08-15 | ESG | 5859 | Patricia Parker | Software Provider | Updating routing within DES138 - PUB-026 | Could you please clarify what updates the Metering Service will receive via the PUB_026. From the routing the only update is re the SCCandProfile Class. However, BP010C alludes to the MS receiving an update for the SMSO - could you please confirm which is correct? |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | To update PUB-026 adding XMSC to the SMSO secondary routing. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-619 | SC | PDA Test Issues | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Draft Umetered Change of Energisation Status Business Process Map | Update BP08 existing or draft Unmetered Specific version. |  | Closed | [5 empty] | Pending feedback from PDA on UMS process. No feedback provided - closed
MHHS-DIN-620 | SC | Test Issues | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | Remove EES as a Recipient of IF-001 | Remove EES as a Recipient of IF-001 | CR028 | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Removed EES as a Recipient of IF-001 - EES gets this info from CSS | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-621 | SC |  | 2023-08-17 | MHHS |  | Sean Cooper | SRO Design | Changes to D303 DTN Flow | Need to make "Manufacture and Type" non mandatory in the D303 flow. Follow migration to MHHS it is possible that this data item is not held in REGS and therefore not shared with all MHHS Participants incl. MS who currently would need to provided it on the D303. Discussions were held in Data Working group around back population of this data item but that proposal was REJECTED - therefore only other option is to make this field optional in D303 |  | Implemented | Design gap | TBC |  | Interim Release 8 | 2024-03-20 | Passed to Matt McK to add to existing industry CP changes.
MHHS-DIN-622 | SC | SCS | 2023-08-17 | St Clements |  | Sean Cooper | SRO Design | DIP Validation of Sender Correlation ID | Implement DIP validation to check for incorrect population of Sender Correlation ID. |  | Closed | [5 empty] | CR would be required for the DIP to implement Sender Correlation ID validation. Decision to implement Level 3/4 Sender Correlation ID validation is with the recipient. | Clarification
MHHS-DIN-623 | SC | SCS | 2023-08-17 | St Clements |  | Sean Cooper | Programme Design | Change IF-001 Routing | Add SUPL (Linked Supplier) as an additional Primary Receipient of Inital Registration Event |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Add SUPL (Linked Supplier) as an additional Primary Receipient of Inital Registration Event for IF001 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-624 | ME |  | 2023-08-18 | Design Team |  | Miriam Ellis | Programme Design | BP013 DDE Updates | MHHS test team have identified discrepancies within the ECS BPM's that require updates to align with the ECS reports. Updates are required to BPM13 DDE |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Updates to BPM013: 1. Update reference of MHHS-REP-001 to ELEX-REP-001 in BP header 2. Update reference of REP-005 to ELEX-REP-005 in BP header 3. Reference of MHHS-REP-002A included with BP header 4. Reference of REP-002 changed to ELEX-REP-001 | Clarification | Supporting Docs | Reporting Catalogue | BPM013 | BPM013
MHHS-DIN-625 | SC | DI-210 | 2023-08-18 | St Clements | 6221 | Sean Cooper | Programme Design | B092 should also be an array to allow MPRS to populate multiple rejections | B092 should also be array to allow MPRS to populate multiple rejections |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Consider breaking out DI-980 into an array in B092 block of IF-035. Block B099 added containing DI-979 and DI-980 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue Swagger 1.5 | MHHSP-DES138-Interface Catalogue Swagger 1.5
MHHS-DIN-626 | SC | ESG | 2023-08-22 | ESG |  | Sean Cooper | Programme Design | Update Routing of IF-003 | Routing of this flow should match that of the IF-037 - in that a copy should also be sent to the Supplier. IF-003 Routing table updated to show Supplier as being a receipient of the iF-003 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Routing of this flow should match that of the IF-037 - in that a copy should also be sent to the Supplier. IF-003 Routing table updated to show Supplier as being a receipient of the iF-003 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-627 | SC | ESG | 2023-08-22 | ESC |  | Sean Cooper | Programme Design | Update Interface Doc "Correlation ID Required" to "Correlation ID Created" | Inconsistancy indentified in the column headings across different IFs. All should read "Correlation ID Created" as this column denotes if the DIP IF should create/copy a DIP Correlation ID value or not. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update Interface Doc "Correlation ID Required" to "Correlation ID Created" | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-628 | SC |  | 2023-08-23 | Design Team |  | Sean Cooper | Programme Design | Add in Missing IF-021 Validation | Add NEW validation to ensure that "UTC Settlement Date" has time of Midnight UTC. Added clarification to existing validation rule that time element of "Settlement period end date time" should align with Settlement period duration |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Add NEW validation to ensure that "UTC Settlement Date" has time of Midnight UTC. Added clarification to existing validation rule that time element of "Settlement period end date time" should align with Settlement period duration | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-629 | MF |  | 2023-08-25 | Design Team |  | Mike Fensome | Programme Design | Routing for SUPC on IF-037 | To ensure that the outgoing Supplier are correctly notified of de-appointment of their Service Providers, routing rules for SUPC updated to Primary routing for IF-037 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | SUPC routing moved from Secondary to Primary for IF-037 for all events | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-630 | MF |  | 2023-08-25 | Design Team | N/A | Mike Fensome | Programme Design | Remove incorrect arrow on BP002 | Arrow incorrectly added into BPOO2 between steps 225 and steps 245 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Arrow between steps 225 and steps 245 on BP002 removed. Previously added in error. | Process Model correction | Minor | Interfaces | BP002 | BP002
MHHS-DIN-631 | SC |  | 2023-08-29 | MHHS | N/A | Sean Cooper | SRO Design | Swagger Alignment - Block B051 | Required Data Items field names do not match those specfied in the defintion. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | loadShapeGSPGroup and loadShapeDomesticPremiseIndicator added to Required fields section to align with block definition. | Correction | Minor |  | DES-138 Interface Cat | DES-138 Interface Cat
MHHS-DIN-632 | SC |  | 2023-08-31 | Helix | N/A | Sean Cooper | SRO Design | Header & Footer Requirements for ISD Entity Files | ISD Specification should be updated to include specification/definition of a standard Header and Footer to be applied to each ISD Entity CSV file. |  | Initial Assessment/Updating | Design gap | Helix, Suppliers |  | Post Go-live Release | 0 | Decision required on exact content/structure of Header ... Is a footer required? If so what should it include (eg number of Entity entries) | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-633 | SC |  | 2023-08-31 | Helix | N/A | Sean Cooper | Programme Design | Update to ISD E45 | Update Entity 45 - Market Role code needs to allow Blanks in order to align with other tables in ISD and to provide for [new] Market Participants who dont have a legacy market particpant role code |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update Entity 45 - Market Participant Role code needs to allow Blanks (Optional) in order to align with other tables in ISD and to provide for [new MHHS] Market Participants who dont have a legacy market participant role code | Clarification | Supporting Docs | Supporting Document | MHHSP_EDI021_ISD_Entities | MHHSP_EDI021_ISD_Entities
MHHS-DIN-634 | KH |  | 2023-09-01 |  | 6616 | Tym Huckin | Consultancy | Update UMSDS Method Statement with correct comments for Null value | In row 2, where we have a "live" summary but it is de-energised, it says to put "A" actual data flag and use Estimation Reason Code "7", but the DI-076 column in that row says this should be Null. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | In 10.1 the table states in row two that the "Estimation Reason code" is Null and therefore the comments column will be updated to: If a D0388 has been received with load associated data and the MPAN is de-energised the load should be calculated, submitted as ‘A’ Flagged but with an Estimation Reason Code of Null | Correction | Supporting Docs | Method Statement | UMSDS Method Statement | UMSDS Method Statement
MHHS-DIN-635 | RG |  | 2023-09-04 | Design Team |  | Rob Golding | Programme Design | Status Code needs tidying in StandardResponseBodyType | 4In the “StandardResponseBodyType” definition, there is a required property called "statusCode" that is not listed among the properties. Could you please address this inconsistency? |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Simple update | Data interface correction | Swagger |  | Swagger | Swagger
MHHS-DIN-636 | SC |  | 2023-09-04 | Design Team |  | Sean Cooper | Programme Design | Removal of YAML Name Fields from Data Catalogue | Following discussions agreement to remove YAML fields from Data Catalouge. Swagger will be the definitive reference for the Jason/Yaml property labeling etc. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Following discussions agreement to remove YAML fields from Data Catalogue. Swagger will be the definitive reference for the Json/Yaml property labelling etc. | Data interface correction | Supporting Docs | Interface catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-637 | RG |  | 2023-09-04 | Design Team |  | Rob Golding | Programme Design | Data Catalogue items incorrectly use maximum and minimum | String need to be range bounded by maxLength & minLength |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update swagger so that maxLength and minLength are used instead of maximum and minimum | Dat Interface correction | Swagger |  | Swagger | Swagger
MHHS-DIN-638 | RG |  | 2023-09-04 | Design Team |  | Rob Golding | Programme Design | Block: D0, Field: serviceTicketURL. DES138 specifies 'string max 225', Swagger specifies 'string max 250' | Set to 250 in DES 138 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | DES138 update, 01-Data Catalogue & 02- DIP Common : Block: D0, Field: serviceTicketURL (DI-978) set to 250 | Data interface correction | Supporting Docs | interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-639 | RG |  | 2023-09-04 | Design Team |  | Rob Golding | Programme Design | DI-138-Customer-Direct-Contract-Data-Service-DIP-ID & DI-140-Customer-Direct-Contract-Metering-Service-DIP-ID to be nullable | Update both to be nullable |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update swagger so that DI-138-Customer-Direct-Contract-Data-Service-DIP-ID & DI-140-Customer-Direct-Contract-Metering-Service-DIP-ID are DT-006N, i.e. nullable | Data interface correction | Swagger |  | Swagger | Swagger
MHHS-DIN-640 | RG |  | 2023-09-05 | Design Team |  | Sean Cooper | Programme Design | Custom Block: B022, Field: Metering Point Postcode. Interface Catalogue specifies CMO as ‘M’ for IF-018, all other interfaces specify CMO as ‘O’. | Update DES138 so that all versions are the same and marked as optional Custom Block: B022, Field: Metering Point Postcode. Interface Catalogue specifies CMO as ‘M’ for IF-018, all other interfaces specify CMO as ‘O’. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update DES138 so that all versions of B022 are the same and fields marked as optional | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-641 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | Custom Block: B022, Field: Metering Point Postcode. Interface Catalogue specifies no min length, but min length of 6 specified in Swagger. | Update swagger to align |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update swagger to align minlength removed from DT007(N) | Data interface correction | Swagger |  | swagger | swagger
MHHS-DIN-642 | RS |  | 2023-09-05 | MHHS | 7382 | Rob Golding | SRO Design | NFR0045 Performance Efficiency | this NFR does not clearly define how the DIP will throttle participants where connection are over a mutually shared mTLS connection. Shared mTLS connections will be used by many parties such as DIP Connection Providers, the requirement to use them being placed on parties that will be Placing Reliance on a Connection Provider. Effectively, this means that multiple parties will use the mTLS connection and which, under certain circumstances could see significant increases over that mTLS if more than one party’s message volumes increased. |  | Closed | [5 empty] | This item is being managed as part of the DIP work-off plan
MHHS-DIN-643 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | B029 Fields marked as mandatory | B029 Condtitonal mandatory marked as required. Block will be conditional |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update DES138 & swagger | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue Swagger | MHHSP-DES138-Interface Catalogue Swagger
MHHS-DIN-644 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | DI-122 Profile Class has a minLength of 2 in Swagger. | add minLength clause |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update swagger DI-122 Profile Class to minLength =2 in swagger | Data interface correction | Swagger |  | Swagger | Swagger
MHHS-DIN-645 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | Clarify 'AllRoles' for DIP routing for IF-047 | Update to include MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update DES138 IF-047 so that all roles are specified (MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES) | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-646 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | DT-002N-MPAN requires a minLength of 13 | add minLength clause |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update DT-002N-MPAN to min length & max length 13 in swagger | Data interface correction | Swagger |  | Swagger | Swagger
MHHS-DIN-647 | RG |  | 2023-09-06 | Design Team |  | Rob Golding | Programme Design | Replace reportId with interfaceId in the ECS reports | Replace reportId with interfaceId in the ECS reports to make S0 block consistent across all reports/interfaces |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update swagger & MHHSP - ERI011B - ECS Reports - External v5.4 | Reporting correction | Supporting Docs |  | MHHSP - ERI011B - ECS Reports - External Swagger | MHHSP - ERI011B - ECS Reports - External Swagger
MHHS-DIN-648 | KH |  | 2023-09-06 | St Clements |  | Vicki Holland | Software Provider | DI-496 data item | This data item was given a max value of 48, however the max value should be 50 to allow for the clock change day in October which has 50 settlement periods. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | All settlements reports will be in clock time and can have 46, 48 or 50 Settlement Periods. DI-496 is INT(3) to allow for a change to 15 minute Settlement Periods which would require a value of 100 for the Autumn Clock Change in the future. Maximum value in Swagger and ECS Reports to be updated to 50 for half hourly settlement periods. | Reporting correction | Supporting Docs | interface catalogue | MHHSP - ERI011B - ECS Reports - External MHHSP - ERI011A - ECS Reports - Internal Swagger | MHHSP - ERI011B - ECS Reports - External MHHSP - ERI011A - ECS Reports - Internal Swagger
MHHS-DIN-649 | SC |  | 2023-09-06 | MHHS |  | Sean Cooper | SRO Design | REGS-EES 'Refresh' Flow - IF-051 | Following discussion with SCS and EEC - proposed definition of refresh message iF-051 |  | Closed | [5 empty] | Initial draft reviewed by EES and SCS - revisions to follow. Closed as duplicate - refer to DIN-051
MHHS-DIN-650 | BK |  | 2023-09-06 | Design Team |  | Rob Golding | Programme Design | Introduction of Compressed Payloads into DIP Messages | Detailed analysis of the some of the ECS reports, specifically REP003, has found that some of the reports can potentially grow to a very large size ~ 12MB. Within MHHS message design there is a notional upper limit for the size of messages which is 1MB, and hence these messages will exceed this constraint. | CR030 | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | The proposal is that the Sender (ECS) compresses the report and base64 encodes the data into the CustomBlock. The recipient will know that a specific message flow is compressed, and hence will need to decompress the payload. The proposal is to use gzip for the compression. This new pattern for compressed payloads will be initially introduced for the following reports: REP-002 LDSO report for DUoS – aggregated data REP-002A Embedded Network report for DUoS – aggregated data REP-003 BM Unit Allocated Demand Volumes to Market Participants REP-004 Supplier Deemed Take Report REP-006 Aggregated Uncorrected volumes by CCC to Market Participants REP-007 VAS Exception Report to Suppliers and BSCCo REP-008 MDS Exception Report to LDSOs REP-009 EMRS Report for Suppliers A covering statement has been included within the Introduction tab of ECS reports which highlights the changes made to Swagger. | Data interface correction | Technical Artefact | Technical Artefact | Swagger 1.5 MHHSP - ERI011A - ECS Reports - Internal | Swagger 1.5 MHHSP - ERI011A - ECS Reports - Internal
MHHS-DIN-651 | MH |  | 2023-09-07 | MHHS |  | Kevin Spencer | SRO Design | Supplier Registration of ABMU/ MPAN mapping | There is a design gap around Supplier ABMU Mapping held by ELEXON. Suppliers will need to register their MPAN/ ABMU Mappings for MHHS. Currently, they send a D0297 to HHDAs to provide the Mapping and can populate the SVA Metering Service Register for MSID Pairs where they are used in the Balancing Mechanism using the P0278 and self-service via ELEXON Kinnect. The issue is that for MHHS the export might be with one Supplier and the import with another. The validation in Kinnect only supports a pair being submitted mapping both import and export to the ABMU. Likewise, the P0278 only supports the provision of MSID pairs. We think a new flow may be needed or the D0297 re-routed to PMP. |  | Closed | Design gap | Helix | 2024-01-12 |  |  | Pending Helix raising a Change Request
MHHS-DIN-652 | RG |  | 2023-09-07 | Design Team |  | Rob Golding | Programme Design | DI-091-Number-Of-Displayed-Register-Digits update in DES138 to reflect the range 0-9 | DI-091-Number-Of-Displayed-Register-Digits update in DES138 to reflect the range 0-9 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update DI-091 in the data catalogue to have the correct min (0)/ max(9) values | Data interface correction | Supporting Docs | Interfaces | DES138 - Interface Doc | DES138 - Interface Doc
MHHS-DIN-653 | RG |  | 2023-09-07 | Design Team |  | Rob Golding | Programme Design | MO block removed from IF-047 | MO block removed from IF-047 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | M0 block removed from IF-047 | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-654 | RG |  | 2023-09-07 | Design Team |  | Rob Golding | Programme Design | DI-130 RMP and DI-131 MP status maxlength | Reduce maxlength to align with eumerated type (50->1) |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Max length updated to 1 in Swagger for DI-130 RMP and DI-131 MP status | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 | Swagger 1.5
MHHS-DIN-655 | RG |  | 2023-09-08 | Design Team |  | Fredrik Omland | Software Provider | Add a set no additional properties to false | Adding a set no additional properties condition to the swagger objects improves the validation |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Add "additionalProperties: false" to all schema objects in swagger so that no additional properties / fields can be attached to an object that are not specficied in the schema. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 | Swagger 1.5
MHHS-DIN-656 | SW |  | 2023-09-11 | Design Team |  | Steve Weston | Central Body | All S1 properties to be mandatory | Ensure all S1 properties are mandatory as per DES-138 in Swagger 1.5 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Ensure all S1 properties are mandatory nullable as per DES-138 in Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-657 | ME |  | 2023-09-11 | Design Team |  | Miriam Ellis | Programme Design | NEW ISD Entity | A request has come in from St Clements requesting for a New ISD entity which lists settlement period quality indicators, with a mapping to an actual or estimate indicator. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | ISD Entity M19 Settlement Period Quality Indicators has been added to the ISD entity document. | Data interface correction | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-658 | ME |  | 2023-09-12 | Design Team |  | Miriam Ellis | Programme Design | Updates to ERI011B | Following an internal review of the external ECS reports a few discrepancies have been highlighted that need to be amended |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Changes to ECS External Reports 1. MHHS-REP-006: Block R051 Demand Disconnection Event Details - parent updated to R032 2. Data Catalogue: Format of DI-492, 496, 487, 488, 484 updated to reflect MHHS Data Type | Design Ambiguous | Supporting Docs | Various documents | ECS Reports | ECS Reports
MHHS-DIN-659 | RG |  | 2023-09-12 | Design Team |  | Rob Golding | Programme Design | Update REP007 | Update REP007 to include blocks R007 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update REP007 to include blocks R007 | Design Ambiguous | Supporting Docs | Various documents | Swagger 1.5 | Swagger 1.5
MHHS-DIN-660 | ME |  | 2023-09-12 | St Clements | 4513 | Vicki Holland | Software Provider | Supplier version of REP-002 | St Clements are requesting for one report per supplier MPID that covers all combinations of distributor and GSP group. The current solution for REP-002 is a supplier will receive a report per distributor id |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | REP002 has been split into two separate reports. There is now a Supplier version (MHHS-REP-002) and an LDSO Version (MHHS-REP-002B). Due to this change the MDS BPM/BPD (019) and DDE BPM/BPD (013) have also been updated to include the reference of REP-002B | Reporting correction | Supporting Docs | Various documents | MHHSP - ERI011B - ECS Reports - External v5.4 BP013 Demand Disconnection BPM/BPD v5.1 BP019 Market-wide Data Service BPM/BPD v5.1 | MHHSP - ERI011B - ECS Reports - External v5.4 BP013 Demand Disconnection BPM/BPD v5.1 BP019 Market-wide Data Service BPM/BPD v5.1
MHHS-DIN-661 | RG |  | 2023-09-13 | IMSERV |  | Liam Lowey | Software Provider | Use of the term 'GUID' in messages | Messages are referring to "Device ID" data items as "GUID". For example "GPFGasGUID" in IF-004. However, a Device ID is not a GUID which is 128 bit number with a specific format. The Wikipedia article for GUID gives more information. Instead, Device IDs are 64 bit. This is misleading to implementors and maintainers. Could the naming of the properties be changed to reflect the identifier better? For example this appears to be a collection of 8 bytes in hexidecimal, i.e. a 64-bit quantity or 8 octets. Much like a MAC address or EUI64 for DCC is. Do you have other identifiers like this that require definition could we standardise on a different name for all of them? |  | Closed | [5 empty] | No further action taken
MHHS-DIN-662 | SW |  | 2023-09-14 | Design Team |  | Steve Weston | Programme Design | Update Sort Code and Account Number validation | DT-035-Sortcode and DT-035-Bank Acount Number have incorrect min / max Lengths. Sort Code should be min 6, max 8 with a regex applied for validation. Account number should be min 8 and max 10, with a regex for extra validation |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | DT-035-Sortcode and DT-035-Bank Acount Number have incorrect min / max Lengths. Sort Code should be min 6, max 8 with a regex applied for validation. Account number should be min 8 and max 10, with a regex for extra validation. This needs to be updated in ER011B and Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-ERI011B- ECS Reports | Swagger 1.5 MHHSP-ERI011B- ECS Reports
MHHS-DIN-663 | SW |  | 2023-09-14 | Design Team |  | Steve Weston | Programme Design | There are missing regular expressions that would improve the swagger schema validation | There are various data types that would benefit from regex added to improve validation. In addition, there could be new data types created / regex added to improve consistency and validation. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | There are various data types that would benefit from regex added to improve validation. In addition, there could be new data types created / regex added to improve consistency and validation. This needs to be updated in Swagger 1.5. The proposed regexes are for the following data types/items: DT-002 MPAN - DT-026 Group Correction Factor DT-027 MPID | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 | Swagger 1.5
MHHS-DIN-664 | SC |  | 2023-09-14 | St Clements |  | Sean Cooper | SRO Design | Message [Error] Status Message Addressing | Based on feedback from SCS review the Message Status section of E2E to make it clearer that the "Sender ID is system sending the error, so if MPRS was sending an error it would be the REG DIP ID And Recipient ID would be who you are sending the error to – so would be the S1.senderDIPID on the original message" |  | Closed | Design ambiguous | N/A |  |  |  | Clarified with SCS | Design Ambiguous | Supporting Docs | Supporting document | E2E001 - E2E Architecture Doc | E2E001 - E2E Architecture Doc
MHHS-DIN-665 | SC |  | 2023-09-14 | St Clements |  | Sean Cooper | Programme Design | Tidy up Of "where available in Registration" usage | IF-001 / IF-002 /IF-036 Block 5 - Block 5 & IF-003 Blocks 095/096 & IF-033 Block 072 & IF-037 Block 10 and 11 heading had a note refering to Interface notes section which explained that block info may not always be availible. This was inconsistant with all other blocks which use the phrasing "Where Availible in the Regisration Service".... Block 5 updated to be consistant. IF Notes on each of these IF remain unaffected. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | IF-001 / IF-002 /IF-036 Block 5 - Block 5 & IF-003 Blocks 095/096 & IF-033 Block 072 & IF-037 Block 10 and 11 heading had a note refering to Interface notes section which explained that block info may not always be availible. This was inconsistant with all other blocks which use the phrasing "Where Availible in the Regisration Service".... Block 5 updated to be consistant. IF Notes on each of these IF remain unaffected. | Data interface correction | Supporting Docs | Interfaces | DES138 - Interface Doc | DES138 - Interface Doc
MHHS-DIN-666 | SW |  | 2023-09-15 | Design Team |  | Steve Weston | Programme Design | Data Type / Data Type Reference inconsistencies in DES-138. | Fix any IR5 Data Type / Data Type Reference inconsistencies between DES-138 & Swagger (between Data Catalogue Tab and IF / Common tabs) |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Fix any IR5 Data Type / Data Type Reference inconsistencies between DES-138 & Swagger (between Data Catalogue Tab and IF / Common tabs). Data Type Inconsistencies - DES-138 updates DI-000 is defined as a String 8, but in IF-040 and IF-045 this is defined as a String 6, so DES-138 has been updated to align. DI-019 is defined as a string 50 in IF-032, but in IF-034 and 36, is defined as String 10. In IF-035 this is blank. Updated IF-034, 35 and 36 so that DI-019 is a String 50. Swagger updated to align. DI-020 is defined as a string 50 in IF-032, but in IF-034 and 36, is defined as String 10. In IF-035 this is blank. Updated IF-034, 35 and 36 so that DI-020 is a String 50. Swagger updated to align. IF-023, B029, DI-026, DES-138 updated so Data Type is DT-003 to align with Swagger. IF-023, B035, DI-038, DES-138 updated so Data Type is DT-002 to align with Swagger. IF-023, B053, DI-041, DES-138 updated so Data Type is DT-016N to align with Swagger. IF-023, B053, DI-042, DES-138 updated so Data Type is DT-016N to align with Swagger. IF-023, B053, DI-044, DES-138 updated so Data Type is DT-016N to align with Swagger. IF-023, B053, DI-045, DES-138 updated so Data Type is DT-016N to align with Swagger. IF-033, B037, DI-075, DES-138 updated so Data Type is DT-002N to align with Swagger. IF-033, B037, DI-079, DES-138 updated so Data Type is DT-002N to align with Swagger. IF-050, B080, DI-111, DES-138 updated so Data Type is DT-003N to align with Swagger. IF-051, B080, DI-111, DES-138 updated so Data Type is DT-003N to align with Swagger. IF-050, B080, DI-112, DES-138 updated so Data Type is DT-003N to align with Swagger. IF-051, B080, DI-112, DES-138 updated so Data Type is DT-003N to align with Swagger. IF-014, B047, DI-147, DES-138 updated so Data Type is DT-016 to align with Swagger. IF-013, B049, DI-159, DES-138 updated so Data Type is DT-003 to align with Swagger. IF-003, B094, DI-159, DES-500 updated so Data Type is DT-003 to align with Swagger. IF-003, B008, DI-159, DES-813 updated so Data Type is DT-006 to align with Swagger. IF-003, B009, DI-159, DES-816 updated so Data Type is DT-006 to align with Swagger. DIP Common, D0, DI-986 removed Data Type from DES-138 and Swagger. Data Type Inconsistencies – Swagger updates IF-036, B068, DI-018 Swagger updated so Data Type is DT003N to align with DES-138. IF-051, B082, DI-023 Swagger updated so Data Type is DT003N to align with DES-138. IF-038, B021, DI-138, Swagger updated so Data Type is DT-006 to align with DES-138. IF-039, B021, DI-138, Swagger updated so Data Type is DT-006 to align with DES-138. IF-001, B006, DI-139, Swagger updated so Data Type is DT-006 to align with DES-138. IF-038, B020, DI-140, Swagger updated so Data Type is DT-006 to align with DES-138. IF-039, B020, DI-140, Swagger updated so Data Type is DT-006 to align with DES-138. IF-024, B058, DI-152, Swagger updated so Data Type is DT-016 to align with DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-667 | SW |  | 2023-09-16 | Design Team |  | Steve Weston | Programme Design | Mandatory / Optional blocks inconsistencies between DES-138 & Swagger | Fix any IR5 Mandatory / Optional blocks inconsistencies between DES-138 & Swagger |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Fix any IR5 Mandatory / Optional blocks inconsistencies between DES-138 & Swagger. Mandatory / Optional / Nullable Inconsistencies DIP Common, S1, DI-985 is Optional in Swagger and has been updated to be Mandatory to align with DES-138. DIP Common, S1, DI-996 is Optional in Swagger and has been updated to be Mandatory to align with DES-138. IF-013, B049, DI-161 is Optional in Swagger and has been updated to be Mandatory to align with DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-668 | SW |  | 2023-09-17 | Design Team |  | Steve Weston | Programme Design | Nullable / Optional Data Type / property inconsistencies between DES-138 & Swagger | Fix any IR5 Nullable / Optional Data Type / property inconsistencies between DES-138 & Swagger |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Fix any IR5 Nullable / Optional Data Type / property inconsistencies between DES-138 & Swagger. Nullable / No nulls Inconsistencies DI-988 is nullable in DES-138 but no nulls in Swagger, so Swagger to be updated so it is nullable to align with DES-138. DI-123 is nullable in DES-138 but no nulls in Swagger, so Swagger to be updated so it is nullable to align with DES-138. DI-150 is nullable in Swagger, to be updated in Swagger so this is Mandatory no nulls to align with DES-138. DI-018, update DES-138 so value is Mandatory nullable to align with Swagger. DI-138, update DES-138 so value is Mandatory nullable to align with Swagger. DI-023, DI-026 update DES-138 so value is Mandatory nullable to align with Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-669 | SW |  | 2023-09-18 | Design Team |  | Steve Weston | Programme Design | Min / Max Values inconsistencies between DES-138 & Swagger | Fix any IR5 Min / Max Values inconsistencies between DES-138 & Swagger |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Fix any IR5 Min / Max Values inconsistencies between DES-138 & Swagger. Min / Max Inconsistencies DI-019 update Swagger max length to be 50 to align with DES-138 DI-218 update Swagger to align with DES-138 min / max values. DI-300 update Swagger to align with DES-138 min / max values. DI-081 update DES-138 to have a max of 30 to align with Swagger. DI-091 update DES-138 to have a max of 9 to align with Swagger. DI-152 update DES-138 to have a max length of 13 to align with Swagger. DI-161 update DES-138 to align with Swagger value of 9999999. DI-167 update DES-138 to align with Swagger min / max values. DI-168 update DES-138 to align with Swagger min / max values. DI-190 update DES-138 to align with Swagger max value of 50. DI-194 update DES-138 to align with Swagger max value of 50. DI-990 update DES-138 to align with Swagger max value of 65. DI-992 update DES-138 to align with Swagger max value of 10. DI-081 update DES-138 to have a min of 30 to align with Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-670 | SW |  | 2023-09-15 | Design Team |  | Steve Weston | Programme Design | Unclear whether webhook URL's accept ports | Need to make it clearer in E2E design and Swagger whether port numbers are allowed in webhook / URLs and any formatting / options for environments |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Need to make it clearer in E2E design and Swagger whether port numbers are allowed in webhook / URLs and any formatting / options for environments E2E001 Section 4.5 updated | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 E2E001 | Swagger 1.5 E2E001
MHHS-DIN-671 | ME |  | 2023-09-22 | Elexon | 11203 | Rashmi Radhakrishnan | Central Body | Updates to ISD Entities | 1. Make it clear what the data type/length is for Line Loss Factor Identifier. It is currently unclear as it reads 3 characters 2. Following consultation feedback of BSCP707, ISD Entity 23 requires an update to include the word 'Duration' and update to the character length and inclusion of date format |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | 1. Update to ISD Entity M3 - update the length/data type of Line Loss Factor Identifier. Now reads as Up to 3 characters 2. Update to ISD Entity 23 - include the word 'Duration' to Settlement Period. This now reads Settlement Period Duration (Description). Update the data type/length to 50 characters and include a date format of YYYY-MM-DD | Design Ambiguous | Supporting Docs | EDI021 ISD Entities | MHHSP_EDII021_ISD_Entites 5.3 | MHHSP_EDII021_ISD_Entites 5.3
MHHS-DIN-672 | SW |  | 2023-09-19 | Design Team |  | Steve Weston | Programme Design | B033 has 9 required fields, but only available. Naming is also inconsistent for some of the required fields that do not exist. | B033 has 9 required fields, but only 8 are available. Naming is also inconsistent for some of the required fields that do not exist. Swagger needs to be updated to align with available fields and DES-138 mandatory values. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Fix any values in Swagger than do not align with required fields and ensure number of required fields aligns with number of fields available. -metering point postcode removed from required fields in B033 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 | Swagger 1.5
MHHS-DIN-673 | RG |  | 2023-09-21 | Design Team |  | Rob Golding | Programme Design | Floating Point number regexes | DIN 267 inadvertently updated regexes to a pattern which does not align to the agreed format as of Technical Design Working Group Work-Off Issue D-0408th November 2022. The regexes need to align to what was agreed. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update regex patterns for the following data types: DT-016, DT-022, DT-023, DT-024, DT-025, DT-030, DT-031, DT-032, DT-033 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 | Swagger 1.5
MHHS-DIN-674 | SW |  | 2023-09-22 | ESG | 11369 | Kerry O'Donnell | Software Provider | Inconsistent Text description for DI-086 | In the Data Catalogue, DI-086 has a Text Description of "Supplier Effective From Date" but on IF-001 and IF-037, DI-086 has a text description of "Incoming Supplier Effective From Date" |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | In the Data Catalogue, DI-086 has a Text Description of "Supplier Effective From Date" but on IF-001 and IF-037, DI-086 has a text description of "Incoming Supplier Effective From Date". IF-001, IF-037, IF-051 have been updated so that the text description for DI-086 now matches Data Catalogue and Swagger - "Supplier Effective From Date". | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-675 | SC |  | 2023-09-25 | Design Team |  | Sean Cooper | Programme Design | IF-021 IF Consistency Validation Rules | New IF-021 Validation Rules with supporting Error Codes created to ensure validity of IF-021. New Error codes are : ECS1015 - Estimation Reason Code Cannot be Null & ECS1016 - Consumption Amendment Reason Codes Cannot be Null |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | New IF-021 Validation Rules with supporting Error Codes created to ensure validity of IF-021. New Error codes are : ECS1015 - Estimation Reason Code Cannot be Null & ECS1016 - Consumption Amendment Reason Codes Cannot be Null | Missing/incorrect validation rule | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-676 | RS |  | 2023-09-25 | St Clements | 11291 | Rob Golding | SRO Design | CR-018 NFR Change - E2E1009 | There are some NFRs that need tweaking post CR-018 Approval to align with the Registration Service Operating hours - Ie E2E1009. Given that MPRS sits behind an Adapter and does not operate 24/7 (as per CR-018) level 4 processing will operate in the same timeframes as Level 5. It needs tweaking to align with the CR-018 wording of: DIP messages received by the SMRS will be processed between the hours of 05:00 to 18:00 and 21:00 to 23:00 Working Days only. Messages received outside of these hours will be held in a queue until the next processing window. Automated responses to inbound messages (including Level 4 Validation) are expected to be returned within 60 minutes of receipt during the specified operating hours. |  | Closed | Design ambiguous | DIP Users, DIP |  |  |  | This DIN is superceded by CR039.
MHHS-DIN-677 | MF |  | 2023-09-26 | Utiliteam |  | Mike Fensome | Programme Design | Additional information added to IF-020 for Linked MPANs | On linking MPAN's, information is missing in IF-020 ( as provided in IF-002 ) to allow participants to interpret the flow. This needs adding to IF-020. Swagger updated accordingly |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Agreed with SCS, for Import / Export Events ONLY, to add in the blocks that are present in the IF-002 namely B035 Linked MPANs / B-036 Linked Meter Info / B-075 MAP Info to IF-020. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue Swagger 1.5 | MHHSP-DES138-Interface Catalogue Swagger 1.5
MHHS-DIN-678 | ME |  | 2023-09-27 | Elexon | 11684 | Rashmi Radhakrishnan | Central Body | ISD Entities Updates | 1. Entity M14- Master settlement time table Fields: LSS Run Date, Payment Date & Notification Date should be changed to an Optional field. 2. Entity M18- Inconsistencies between M16 field name “ DIP Role Code” and M18 Field name “DIP Market Role”. Two different Field name used. 3. Entity M9 and M10, it appears that the data type length specified in the ISD EDI021 document for Field Unit Description 1, 2, and Manufacturers Designation might not be sufficient based on the data samples. – Datatype/length of these fields needs increasing. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | 1. Entity M14- Master settlement time table Fields LSS Run Date, Payment Date, Notification Date all changed to Optional field. 2. DIP Role Code in Entity M16 updated to DIP Market Role 3. Entity M9 and M10, data type/length for Unit Description 1, 2, and Manufacturers Designation have been incresed to 100 characters | Design Ambiguous | Supporting Docs | EDI021 ISD Entities | MHHSP_EDII021_ISD_Entites | MHHSP_EDII021_ISD_Entites
MHHS-DIN-679 | SC |  | 2023-09-27 | SRO Design |  | Sean Cooper | Elexon | MHHS Process for Additional BMU's Required | Clarification is required around how Additional BMU's will be requested, created and managed under MHHS |  | Closed | [5 empty] | Duplicate of MHHS-DIN-651 | No Change
MHHS-DIN-680 | ME |  | 2023-09-27 | St Clements | 11538 | Vicki Holland | Software Provider | Update to DI-322/DI-323 MHHS data type | The MHHS Data types for DI-322 and DI-323 requires an update to align with the SVA data catalogue as these 2 data items are reported to 9 decimal places. Swagger will also need to be updated to align with the ECS reports |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Updated MHHS data types and definitions for DI-322 and DI-323 within the ECS Data catalogue and where it appears in the reports. The Min and Max values have also been updated due to the change in data type. This change has been made in Swagger. Data types have been updated to a String 20(±9.9). | Reporting correction | Supporting Docs | ECS Reports Swagger REP003 version 010 | MHHSP - ERI011B - ECS Reports - External MHHSP - ERI011A - ECS Reports - Internal Swagger | MHHSP - ERI011B - ECS Reports - External MHHSP - ERI011A - ECS Reports - Internal Swagger
MHHS-DIN-681 | SW |  | 2023-09-28 | ESG | 11492 | Kerry O'Donnell | Software Provider | DI-824 textual decsription in the Interfaces is inconsistent with the textual description in the Data Catalague | DI-824 textual description (Column D) in the Interfaces is inconsistent with the textual description (Column D) in the Data Catalogue. This DIN is to ensure the textual description is consistent in the Interfaces to the Data Catalogue and that found in Swagger. |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Textual description corrected on IF-036 to align with other interfaces | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-682 | MF |  | 2023-09-28 | CGI |  | Dave Webster | Data Service Provider | Remove commissioning flows sent to Data Service on BP009 | BP009 is misaligned with the Data Service requirements and incorrectly shows the Advanced Data Service receiving Commissioning Flows (D0383 and D0384) |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Removed commissioning flows sent to Data Service on BP009 (D0383 and D0384 into step 175). Note BPD was already correct. Updated BRS002 - MHHS-BR-MS-062 accordingly | Process Model correction | Supporting Docs | Process model correction Business requirements | BP009 BRS002 | BP009 BRS002
MHHS-DIN-683 | SW |  | 2023-09-28 | Flui | 11487 | Jason Jackson | Software Provider | E2E refers to T0 and Transaction Wrapper which are no longer required | E2E refers to T0 (section 4.8.2) and Transaction Wrapper (section 5.5) which are no longer required. This needs to be updated in the E2E design and an update provided in relation to Swagger and how this works. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | E2E001 updated to reflect replay design | Design Ambiguous | Supporting Docs | Interfaces | E2E001 | E2E001
MHHS-DIN-684 | ME |  | 2023-10-03 | SRO Design |  | Kevin Spencer | SRO Design | Addition of REP-003A | As part of the Tranche 1 Transition Design and following approval from DAG a new report has been included within ECS Reports, MHHS-REP-003A. The intention is to retain the existing data flows in transition for the non-migrated MPANs and send the new DIP Flows or DTN flows for the migrated MPAN. This is due to the change in the CCCids which have different characteristics in the new world. The ELEX-REP-003A has been developed such that the CCC totals across migrated and non-migrated MPANS can be presented. Suppliers with MPANs in both Legacy and MHHS can expect: D0296 – just legacy data – as now, pipe delimited dataflow received via the DTN REP-D0296 – just MHHS data – still a pipe delimited dataflow received via the DTN – will have a new Dxxxx identifier REP-003 – just MHHS data – a JSON message received via the DIP REP-003a – both legacy and MHHS data – a JSON message received via the DIP |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Inclusion of MHHS-REP-003A to the ECS reports. Swagger has been updated to align with ECS reports catalogue with new reports interface REP-003a and associated common block, custom block and data catalogue items as per reports catalogue. | Reporting correction | Supporting Docs | ECS Reports Swagger REP003A version 001 | MHHSP - ERI011B - ECS Reports - External Swagger | MHHSP - ERI011B - ECS Reports - External Swagger
MHHS-DIN-685 | BK |  | 2023-10-04 | RECCo |  | Sarah Jones | Central Body | Data Item Names and Descriptions | As part of the interface tranche of MHHS code drafting, RECCo has reviewed the information contained within the MHHS Interface Catalogue (DES138) and the ECS Reporting Catalogue (ERI011B) and identified a number of areas where changes to the data item names and descriptions should be progressed in order that these better align to existing code terminology and data item descriptions. We have identified five areas where changes should be made. 1) In the MHHS data catalogue, a number of discrepancies have been identified where the data item name or description is slightly different to the Energy Market Data Specification. In response to this we are either proposing to: a. amend the existing Energy Market Data Specification data item name and / or description via the MHHS code drafting work, or b. change to the data item name and / description in the MHHS data catalogue. 2) We have identified MHHS data items with the same name as existing data items, but a different data format. In particular, data items used to define effective from dates have been established for MHHS as a high resolution datetime data type. To avoid ambiguity / confusion for users, we are proposing to amend the data item description for MHHS date related data items to reflect that they are recording a data and time. 3) The data item used to link to CSS registration activity has been incorrectly referenced as the CSS Registration Request Id. This should be amended to the CSS Registration Id (DI90043) to avoid confusion with the CSS Registration Request Id which is a separate data item (DI90050). 4) The data item (MHHS DI-048) used to identify the meter manufacturer has been established with a different name and description from the existing data item (J0410). This should be amended to the Manufacturers Make and Type to avoid confusion. (Alternatively, if this is expected to be an entirely new data item, then the reference to J0410 should be removed and clarity provided on what data should be used to populate the field). 5) Correct minor typographical errors within the data item names and / or descriptions. | CR024 | Open - awaiting assessment | Change Request | All Participants |  | Post Go-live Release | [5 empty] | DES138 Swagger
MHHS-DIN-686 | BK |  | 2023-10-04 | RECCo |  | Sarah Jones | Central Body | DIP Interface Name Changes | As part of the interface tranche of MHHS code drafting, RECCo has reviewed the information contained within the MHHS Interface Catalogue (DES138) and identified a number of areas where changes to the DIP interface names should be progressed in order that these better align to enduring code terminology. In order to translate the MHHS interface catalogue (in the DES138) into the Energy Market Data Specification, RECCo is seeking to align MHHS interface names to enduring code terminology to avoid future inconsistencies. To meet this aim, we have identified four areas where changes should be made. 1) Removal of references to Metering Service within the interface name. Existing terminology will be retained e.g. MEM in the REC and MOA in the BSC. 2) Replacement of references to Service Providers with Supplier Agents within the interface name, Existing terminology will be retained with Data Services and Metering Services defined as Supplier Agents in both the BSC and REC. 3) Replacement of references to Registration / Registration Service with SMRS. To differentiate from the CSS and ERDS, following agreement with BSCCo that DIP interfaces fall under the scope of the SMRS. 4) Replacement of references to CSS De-Registration with CSS Registration De-Activation to reflect REC code terminology. | CR025 | Open - awaiting assessment | Change Request | All Participants |  | Post Go-live Release | [5 empty] | DES138 Swagger
MHHS-DIN-687 | ZH |  | 2023-10-04 | SI Design |  | Zakir Hussain | SI Design | BP003 updates are missing on BPD003 | For DIN-608 changes there were new steps added to the diagram, these have not been covered in the relevant BPD doc. This includes the new steps being referenced, descriptions, flows etc. |  | Initial Assessment/Updating | Error/Correction | N/A |  | Post Go-live Release | 0 | Add missing BP003 updates to BPD003 | Process Model correction | Supporting Docs | Process model correction | BPD003 | BPD003
MHHS-DIN-688 | ZH |  | 2023-10-04 | SI Design |  | Zakir Hussain | SI Design | BP010E updates are not included in BPD10 | BP10E has not been included in the relevant BPD10 doc. |  | Initial Assessment/Updating | Error/Correction | N/A |  | Post Go-live Release | 0 | BP010E updates are not included in BPD010 | Process Model correction | Supporting Docs | Process model correction | BPD010 | BPD010
MHHS-DIN-689 | RG |  | 2023-10-05 | SRO Design |  | Rob Golding | SRO Design | Minor updates to DES138/Swagger for Sims& Ems audit | Minor differences between DES138 & swagger from sims & ems audit |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Incorporate differences between DES138 & swagger from sims & ems audit | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger | DES138 Swagger
MHHS-DIN-690 | SC |  | 2023-10-09 | SRO Design |  | Sean Cooper | SRO Design | IF Optionality Matrix - MDR | Updated MDR IF Optionality Matrix to reflect correct values per current CR23 Design. Existing Values were not correct |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Updated MDR IF Optionality Matrix to reflect correct values per current CR23 Design. Existing Values were not correct for MDS | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-691 | SC |  | 2023-10-06 | SRO Design |  | Sean Cooper | SRO Design | DI-138 / DI-140 Customer Direct Contract Holder(s) | DI-138 / DI-140 Customer Direct Contract Holder(s) - Changed to Data Type DT006N in DES138 to correctly align with Swagger |  | Implemented |  |  |  | Interim Release 5.1 | 0 | DI-138 / DI-140 Customer Direct Contract Holder(s) - Changed to Data Type DT006N in DES138 to correctly align with Swagger | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-692 | SC |  | 2023-10-06 | SRO Design |  | Sean Cooper | SRO Design | DI-161 Settlement Run Number | DI-161 Settlement Run Number - made mandatory in IF-013 to correctly align with Swagger |  | Implemented |  |  |  | Interim Release 5.1 | 0 | DI-161 Settlement Run Number - made mandatory in IF-013 to correctly align with Swagger | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-693 | SC |  | 2023-10-06 | SRO Design |  | Sean Cooper | SRO Design | DI838 Supplier Nominated Consent | DI838 Supplier Nominated Consent - DES138 Updated to show as Nullable (Swagger already aligned) |  | Implemented |  |  |  | Interim Release 5.1 | 0 | DI838 Supplier Nominated Consent - DES138 Updated to show as Nullable (Swagger already aligned) | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-694 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | Update IF-007-EnergisationStatusChange event code | Update event code [EnergisationStatusFailure] to [EnergisationStatusChange] for IF-007-EnergisationStatusChange |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Update event code [EnergisationStatusFailure] to [EnergisationStatusChange] for IF-007-EnergisationStatusChange | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-695 | SC |  | 2023-10-06 | SRO Design |  | Sean Cooper | SRO Design | IF Optionality Grid - LDSO | LDSO IF Optionality - PUB-009 Corrected from NonApplicable to Optional = YES PUB-013 Corrected from NonApplicable to Optional = YES PUB-026 SSCProfileClass Corrected from N/A to Optional = YES PUB-040 Corrected from N/A to Optional = YES REGS: PUB019 Related MPAN Events corrected from N/A to Optional = No |  | Implemented |  |  |  | Interim Release 5.1 | 0 | LDSO IF Optionality - PUB-009 Corrected from NonApplicable to Optional = YES PUB-013 Corrected from NonApplicable to Optional = YES PUB-026 SSCProfileClass Corrected from N/A to Optional = YES PUB-040 Corrected from N/A to Optional = YES REGS: PUB019 Related MPAN Events corrected from N/A to Optional = No | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-696 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | IF-018 mandatory blocks for Energy Direction & NUM Indicatory | Add B023 is required for IF-018-EnergyDirection and IF-018-MUMIndicator |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Add B023 in IF-018-EnergyDirection and IF-018-MUMIndicator | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-697 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | Add required fields to IF-023 | Add required field to custom block in IF-023 |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Add required field to custom block in IF-023 | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-698 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | Add required field to IF-040 | Add B059 to required field in IF-040 |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Add B059 to required field in IF-040 | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-699 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | IF-036 DSAppActive optional B068 block | Remove B068 from required fields for IF-036 DSAppActive |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Remove B068 from required fields for IF-036 DSAppActive | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-700 | RG |  | 2023-10-09 | SRO Design |  | Rob Golding | SRO Design | Recipient ID specified twice in replay/requeue API | Remove recipient id from request body of API call as already specified on path |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Remove recipient id from request body (in the MessageRequest object) of API call as already specified on path. This applies to replay and requeue API endpoints. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-701 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarification on population of IF-036 | Clarification on population of IF-036 participant ID's |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Provided clarification on IF-036 Interface notes on how B005, B016 and B017 are populated by Registration Service | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue | DES138 Interface Catalogue
MHHS-DIN-702 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarification on use of calendar days for validation rules in IF-025 and IF-034 | Update validation rules to clarify that days refer to calendar days in IF-025 and IF-034 |  | Implemented |  |  |  | Interim Release 5.1 | 0 | IF-025 and IF-034 validation rules updated to clarify using calendar days | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-703 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarify that B032 is only sent where available in Registration Service | Clarify that B032 is only sent where available in Registration Service in IF-001, IF-002, IF-033 and IF-036 |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Updated B032 to show as sent where available in Registration Service in IF-001, IF-002, IF-033 and IF-036 | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-704 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Updated DI-135 and DI-136 to be set to Mandatory in IF-025/IF-026 | Update DI-135 and DI-136 to be set to Mandatory in IF-025/IF-026 and to be non-nullable, so that a date is always provided for SMSO and IHD even where setting the value to null. |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Updated DI-135 and DI-136 to be set to Mandatory in IF-025/IF-026 and to be non-nullable | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-705 | MF | DI-214 | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarify that sending of [IMS-SendMTD] event code on IF-035 should also apply in the case of SEG | Clarified that SEG scenario applies for requirement MHHS-BR-RS-019 to send [IMS-SendMTD] event code on IF-035 |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Added that SEG scenario applies for requirement MHHS-BR-RS-019 to send [IMS-SendMTD] event code on IF-035 in BRS003 | Requirement correction | Supporting Docs | Business Requirements | BRS003 | BRS003
MHHS-DIN-706 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Remove Unmetered check for de-linking Linked Export MPANs (IF-019) | Clarified that Unmetered check will not apply for [LinkedImportExportRemove] event in IF-019 |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Updated validation rules so that Unmetered check will not apply for [LinkedImportExportRemove] event in IF-019. | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-707 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarification on Primary routing for IF-033 | Updated IF-033 to show primary routing is to XMSP and XDSP |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Updated IF-033 to show primary routing is to XMSP and XDSP | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-708 | RG |  | 2023-10-09 | SRO Design |  | Rob Golding | SRO Design | IF-004 B093 block is mandatory | Audit of swagger IF-004 B093 block is mandatory |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Update IF-004 B093 block to mandatory | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-709 | RG |  | 2023-10-09 | SRO Design |  | Rob Golding | SRO Design | IF-021 and IF-014 custom block differences | IF-021/14 have different structure, ideally they should be the same - the B045 block does not need to be an array |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Aligned IF-014 to IF-021 so that multiple B045 blocks are not allowed | Data interface correction | Supporting Docs | Interfaces IF-014 version 010 | DES138, Swagger 1.6 | DES138, Swagger 1.6
MHHS-DIN-710 | RG |  | 2023-10-09 | SRO Design |  | Rob Golding | SRO Design | IF-016 requires update to include IF-013 variant | IF-016 definition needs to include replayed IF-013 data. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | At present in DES-138 only the IF-021/14 variants are described in the IF-016 data, this needs to be extended to include the IF-013 variant. This change has been to be reflected in the Swagger. Added validation rules and response codes to IF-015 to be included in IF-016. | Data interface correction | Supporting Docs | Interfaces IF-015 version 010, IF-016 version 010 | DES138, Swagger 1.6 | DES138, Swagger 1.6
MHHS-DIN-711 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | IF-035 Obsfucation/routing contradiction | IF035 – MDS & LDSO are mentioned in the obfuscation column, however, there is no routing rule for these roles |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Removed LDSO and MDS from obsfuscation rules as LDSO/MDS do not receive IF-035 | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue | DES138 Interface Catalogue
MHHS-DIN-712 | MF | DI-181 | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | De-appointment and re-appointment date order | Set de-appointment and re-appointment dates to D and D+1 for requirements RS-128.7 and RS-128.8 for Data Service appointments to align with DIN-383 (Metering Service appointments) |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Discussed with SCS and agreed to update Registration Service requirements to De-appoint on D (MHHS-BR-RS-128.7) and appoint on D+1 (MHHS-BR-RS-128.8) as part of auto-alignment process | Requirement correction | Supporting Docs | Business Requirements | BRS003 | BRS003
MHHS-DIN-713 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | Rel 1.2.1 S1 updates in swagger | SenderRoleId & SenderTimestamp updated in required section in S1 object to fix problem introduced in v1.2 |  | Implemented |  |  |  | Interim Release 2.1 | 0 | Update sentTimestamp to senderTimestamp, senderRole to senderRoleID in S1 block | Data interface correction | Supporting Docs | Various documents | DES-138 Interface Catalogue Swagger 1.2.1 | DES-138 Interface Catalogue Swagger 1.2.1
MHHS-DIN-714 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | Rel 1.2.1. B033 updates in swagger | Remove meteringPointPostcode from required section of B033 object |  | Implemented |  |  |  | Interim Release 2.1 | 0 | Update B033 remove meteringPointPostCode from B033 | Data interface correction | Supporting Docs | Various documents | DES-138 Interface Catalogue Swagger 1.2.1 | DES-138 Interface Catalogue Swagger 1.2.1
MHHS-DIN-715 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | Rel 1.2.1. D091 update | DI-091 update maximum: 1->9, minimum 1->0 |  | Implemented |  |  |  | Interim Release 2.1 | 0 | Update DI-091-Number-Of-Displayed-Digits to maximum 9 and minimum 0 in the Swagger. Including updates to 01-Data Catalogue, IF-002, IF-005, IF-006, IF-033 in the Interface Catalogue to align with Swagger. | Data interface correction | Supporting Docs | Various documents | DES-138 Interface Catalogue Swagger 1.2.1 | DES-138 Interface Catalogue Swagger 1.2.1
MHHS-DIN-716 | ME |  | 2023-10-10 | Elexon | 13809 | Rashmi Radhakrishnan | Central Body | Update to ISD entity 23 | Additional text provided within the Settlement Period Duration (Description) field requires removal as the correct text has been added |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Desription within Settlement Period Duration (Description) has been updated. The reference for a Settlement period, unique within Settlement Date. Periods ID s are assigned sequentially to each period in local time day The duration of a Settlement Period in minutes | Design Ambiguous | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-717 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | LSS needs to be removed from the obsfucation column in DES138 - IF001 | LSS does not recieve IF-001 and therefore should not referenced in the obsfucation column |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Removed LSS from obsfucation rules in IF-001 as only issued to MDS which is already covered by obsfucation | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue | DES138 Interface Catalogue
MHHS-DIN-718 | ME |  | 2023-10-11 | Elexon | 14165 | Derek Weavering | SRO Design | MHHS-Rep-D0296 alignment with Ddddd Supplier BM Report | A review of the DAG approved MHHS-DEL1613 DES-196 D-Flow and Interface Mapping Supplementary Documents has identified the following: The current Supplier BM Unit Report (D0296) considers all the GSPs that the supplier operates in a single file). However the Ddddd specs in the ECS catalogue and D flow documentation suggest a single file for each supplier’s GSP. We are building ( within Helix) using the current approach where all GSPs appear in the same file. Please can this be raised with the team to ensure the specs also reflect the same |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | MHHS-REP-D0296 has been updated to align with the Ddddd Supplier BM Report. The following link: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx has also been included to the following reports (D0081, D0266, D0276 and D0296) to direct participants to what should be used as the Master version of each report as defined in DTC format. | Reporting correction | Supporting Docs | ERI011B ECS Reports-External | ERI011B ECS Reports-External | ERI011B ECS Reports-External
MHHS-DIN-719 | MF |  | 2023-10-11 | Utiliteam |  | Mike Fensome | SRO Design | Update to DI-103 Configurable Register Id to min length of 1, max length of 2 | Allow Configurable Register ID's (DI-103) to be provided with min length of 1 and max length of 2 in both swagger and DES138 so that, for example, either 1 or 01 are accepted. |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Updated Data Catalogue for DI-103 (Configurable Register ID) to Min length of 1 (from 2) and updated Swagger accordingly. Added REGEX to Swagger. Regex takes the form ^\d{1,2}$ | Data interface correction | Supporting Docs | Interfaces | DES138, Swagger | DES138, Swagger
MHHS-DIN-720 | MF |  | 2023-10-11 | Utiliteam |  | Mike Fensome | SRO Design | Update to DI-122 Profile Class to min length of 1, max length of 2 | Allow Profile Class (DI-122) to be provided with min length of 1 and max length of 2 in both swagger and DES138 so that, for example, either 1 or 01 are accepted. |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Updated Data Catalogue for DI-122 (Profile Class) to Min length of 1 (from 2) and updated Swagger accordingly. Added REGEX to Swagger. Regex takes the form ^\d{1,2}$ | Data interface correction | Supporting Docs | Interfaces | DES138, Swagger | DES138, Swagger
MHHS-DIN-721 | JW |  | 2023-10-11 | Migration Design |  | John Wiggins | Programme | Control needed with MPID's associated to a metering role | For a metering company, only one limited company can ever own an MPID related to one of the three metering roles. Elexon need a control to say that an MPID associated to a metering role can never be owned by more than one company |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Updated ISD Entity 45 with the following comment "Where an MPID is related to the following Market Roles: Meter Operator, Advanced MOA or Smart MOA, the MPID and Market Role combinations must always be assigned to the same Company ID." | Missing/incorrect validation rule | Supporting Docs | ISD Entities | ISD Entities | ISD Entities
MHHS-DIN-722 | RG |  | 2023-10-12 | SRO |  | Rob Golding | SRO Design | Remove Recipient Roles from A0.always object. | Remove Recipient Roles from A0.always object as roles are always resolved to DIP Ids |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Update Swagger to remove Recipient Roles from A0.always | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-723 | RG |  | 2023-10-12 | SRO |  | Rob Golding | SRO Design | OffPeakDeclarationProportion spelt on B097 spelt incorrect | OffPeakDeclarationProportion spelt 'OffPeakDeclatationProportion' on B097. |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Updated spelling in Swagger so that 'OffPeakDeclarationProportion spelt 'OffPeakDeclatationProportion' on B097. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-724 | RG |  | 2023-10-12 | SRO |  | Rob Golding | SRO Design | DT-000 Interface ID to include REP-002A & IF-004 | DT-000 Interface ID to include REP-002B & IF-004 as they are missing |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Add REP-002B & IF-004 to the enumerated list for DT-000 | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-725 | RG |  | 2023-10-12 | SRO |  | Rob Golding | SRO Design | Add individual interface endpoints into the swagger | Add individual interface endpoints into the swagger as this would improve schema validation and better error messaging |  | Closed | [5 empty] | Following a review with the DIP Provider, these changes will not be made in Swagger and error handling will remain as per the IR5 design. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.7 | Swagger 1.7
MHHS-DIN-726 | ME |  | 2023-10-13 | SRO | 14120 | Miriam Ellis | SRO Design | DataType/Example errors in ECS reports data catalogue | A number of errors have been highlighted by Elexon following a review of the updated ECS data catalogue V5.4. There are errors that require an update |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Updates to data types and examples for a number of data items have been made within the data catalogue as well as where the data items appear in each of the documented reports | Reporting correction | Supporting Docs | ER1011B ECS Reports External ER1011A ECS Reports Internal | ER1011B ECS Reports External ER1011A ECS Reports Internal | ER1011B ECS Reports External ER1011A ECS Reports Internal
MHHS-DIN-727 | MF |  | 2023-10-13 | SRO |  | Mike Fensome | SRO Design | Add new routing path for IF-041 | Added routing to give Data Service ability to send on-site read to Supplier |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Added [ReadingOnSite] to routing table for Data Service in IF-041 |  |  |  | DES138 | DES138
MHHS-DIN-728 | ME |  | 2023-10-17 | SJW | 13832 | Sarah Jones | Consultancy | DES138 and ECS Reports misalignment | As part of our work developing the interface code drafting, we have noticed that the S0 Block in the interfaces defined in the DES138 differ from those in the ECS Reporting Catalogue. Specifically, the DES138 includes Schema Version in the S0 block and the ECS Reporting Catalogue does not. Our expectation was that blocks would be identical across the various interfaces. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | All new MHHS ECS reports now includes Schema Version in the S0 blocks. | Reporting correction | Supporting Docs | ERBI011B ECS Reports - External | ERBI011B ECS Reports - External | ERBI011B ECS Reports - External
MHHS-DIN-729 | SW |  | 2023-10-17 | SI Design |  | Steve Weston | SI Design | DI-838 to include null on the enum values | DI-838 in Swagger is mandatory nullable and this is an enumerated list so needs to include null in the enumeration to ensure this aligns to DES_138. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Updated Swagger DI-838 to ensure that null is a value in the enumerated list given this is a mandatory nullable field so that this now aligns to DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.6 | Swagger 1.6
MHHS-DIN-730 | ME |  | 2023-10-17 | Elexon | 13443 | Rashmi Radhakrishnan | Central Body | Update to Company name in Entity 1 | Within Entity 1 of ISD Entities - Market Participant ID there is a character limit of 100 for Registered Company Name but this is not sufficient and require this to be updated to allow up to 160 characters to align with company house. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | The character limit for Registered company name within Entity 1 of ISD Entities document has been increased to 160 | Design Ambiguous | Supporting Docs | ISD Entities | ISD Entities | ISD Entities
MHHS-DIN-731 | RG |  | 2023-10-18 | Elexon |  | Nigel Rees | Central Body | Swagger does not resolve ECS reports | Since the ECS reports are now compressed in DIP messages the ECS report strcutre is not resolved in the swagger. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Added a field to each ECS payload that defines the structure of the corresponding report. This will be an optional item, hence not populated, however it will present the resolved structure of the report. | Design Ambiguous | Supporting Docs | Interfaces All REPs are now version 007 | Swagger 1.6, ER1011B ECS Reports External | Swagger 1.6, ER1011B ECS Reports External
MHHS-DIN-732 | RG |  | 2023-10-19 | SRO |  | Rob Golding | SRO | Routing update on IF-026 not updated | DIN-415 was meant to correct the routing on IF-026 - its still incorrect. The routing for event code [SSCandProfileClass] points to EES, LLS- this should be LSS. The header also needs to align - it currently states Central Settlements (MDS), it should be Central Settlements (LSS) |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Typo corrected LLS changed to LSS | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue | DES138 Interface Catalogue
MHHS-DIN-733 | SC |  | 2023-10-19 | RECCO |  | Jonnny Moore | Recco | Update IF-026 Routing for Change of Consent | EES does not hold consent information - changed routing to remove EES as a receipient of Consent Info |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | EES does not hold consent information - changed routing to remove EES as a receipient of Consent Info in IF-026 | Design Ambiguous | Supporting Docs | Interfaces | DES138 Interface Catalogue | DES138 Interface Catalogue
MHHS-DIN-734 | SC |  | 2023-10-19 | RECCO |  | Jonnny Moore | Recco | Update IF-018 Routing for Dom Premise Indicator | EES does not hold consent information - changed routing to remove EES as a receipient of DPI Info |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | EES gets DPI information from CSS - changed routing to remove EES as a receipient of DPI Info in IF-018 | Design Ambiguous | Supporting Docs | Interfaces | DES138 Interface Catalogue | DES138 Interface Catalogue
MHHS-DIN-735 | MF |  | 2023-10-19 | Drax |  | Georgina Mahoney | Drax | Remove referene to BP007 as input into BP002 and BP003 | Disconnections is not an input into Change of Service Provider, BP007 should be removed from the entry processes. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Removed BP007 as an entry process to BP002 and BP003. De-appointment of Service Providers is covered in BP007. | Process Model correction | Supporting Docs | Process model correction | BP002 BP003 | BP002 BP003
MHHS-DIN-736 | ZH |  | 2023-10-19 | SI Design |  | Zakir Hussain | SI Design | Removing step 36 from BP003 | Step 36 was included initially as part of an earlier DIN but is no longer relevant and therefore needs replacing. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Remove Step 36 and flow from BP003, including any reference to the step in the latest BPD3 Doc | Process Model correction | Supporting Docs | Process model correction | BP003 and BPD003 | BP003 and BPD003
MHHS-DIN-737 | RS |  | 2023-10-19 | ESG |  | Patricia Parker | Software Provider | Custom Block: B022, Field: Metering Point Postcode min length in Swagger | Interface Catalogue specifies no min length, but min length of 6 specified in Swagger. Min length should be 5 for areas such as Liverpool |  | Closed
MHHS-DIN-738 | SC |  | 2023-10-19 | St Clements |  | Sean | SRO Design | Update Schema Version Data Item DI-992 Length | Interfaces across DES-138 need updating to show Schema Version DI-992 as String 10 rather than string 3 |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | DES-138 updated in individual interface to show Schema Version DI-992 as String 10 rather than string 3 | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue | DES138 Interface Catalogue
MHHS-DIN-739 | SC |  | 2023-10-19 | St Clements |  | Sean | SRO Design | Validation of Supplier DIP ID / MPID for IF-035 [SDS-MDRUpdate] | Add validation in IF-034 to ensure that Supplier DIPID and MPID provided matches that of the current supplier held in the registration service - return new Error of REG1084 if this is not the case. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Add validation in IF-034 to ensure that Supplier DIPID and MPID provided matches that of the current supplier held in the registration service - return new Error of REG1084 if this is not the case. | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue | DES138 Interface Catalogue
MHHS-DIN-740 | SC |  | 2023-10-19 | St Clements |  | Sean | SRO Design | IF-018 Routing | DS added as a recipient of IF-018 [DCCEnrolment] |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | DS (XDSC) added as a recipient of IF-018 [DCCEnrolment] in the Secondary Routing | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue | DES138 Interface Catalogue
MHHS-DIN-741 | MF |  | 2023-10-19 | St Clements |  | Mike | SRO Design | Clarification on end dating MDR functionality | Add clarification that the requirement to end date the MDR is fulfilled using existing CSS0200 functionality |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | MHHS-BR-RS-078.1 notes updated to clarify that this requirement is fulfilled using existing CSS0200 functionality | Requirement correction | Registration | Business Requirements | BRS003 Registration Service requirements | BRS003 Registration Service requirements
MHHS-DIN-742 | KH |  | 2023-10-23 | CGI | 13709 | Dave Webster | Software Provider | ADS and SDS Estimation Statements | As a result of DIN-589 which was to align the METH002 (ADS) with METH001 (SDS) method statements, the two documents are still misaligned. “Method 0: ADS processes Supplier provided ‘Agreed’ or ‘Override’ Readings” is the equivalent of “Method 0: SDS processes Supplier provided ‘Agreed’ or ‘Override’ Readings and Consumption Amendments”. However, SDS uses flag E0, but ADS uses flag E8 (from the previous numbering of this method and now not intuitive to determine from the flag which method has been used for estimation). Similar to (1), Method 8 (ADS) = Method 8 (SDS), but would be clearer if flag E9 (ADS) matched the method number and flag in SDS, E8. Similar to (1), Method 9 (ADS) = Method 9 (SDS), but would be clearer if flag E10 (ADS) matched the method number and flag in SDS, E9. “3.13 Where notified by a Supplier that a site is Long Term Vacant (LTV) the ADS shall use Method 12.” LTV check is now Method 11. “3.16 The below estimation methods are based on those used in the Smart Data Service (SDS) Method Statement. For that reason, methods 0, 1, 6, 11 and 13 have been omitted as they are only applicable to Smart meters” – this statement is no longer correct as methods 0 and 11 are present |  | Implemented | Design misaligned | TBC |  | Interim Release 7 | 2024-01-19 | Updates completed in method statement 002 | Requirement correction | Supporting Docs | Method Statement | ADS Method Statement | ADS Method Statement
MHHS-DIN-743 | MF |  | 2023-10-24 | ENWL |  | Paul Band | LDSO | IF-036 Optionality Update | IF-036 changed to optional for LDSO's in line with CR-029 within the Optionality Matrix |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | IF-036 changed to optional for LDSO's inline with CR-029 within the within the Optionality Matrix (name of worksheet in DES-138: 04_IF_OptOut_Matrix) | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue | DES138 Interface Catalogue
MHHS-DIN-744 | MF |  | 2023-10-24 | RECCO |  | Sarah Jones | Central Body | IF-036/037 Routing to MDS | Show that MDS receive IF-036 and IF-037 on BP003 to align with Interface Catalogue |  | Implemented | Design misaligned | N/A |  | Interim Release 7 | 2024-01-19 | Added note to BP003 to highlight that MDS will also receive IF-036 and IF-037. Similar note added to the Migration version BPM003 again just to reference the IF-003 being copied to MDS. Added MDS to IF-003 DSDeAppRM event in DES138 | Process Model correction | Supporting Docs | Process model correction | BP003 BPM003 DES138 | BP003 BPM003 DES138
MHHS-DIN-745 | SW |  | 2023-10-27 | SI Design | 16780 | Madison Layton | Central Body | DI-120 Additional Information should be mandatory nullable | DI-120 was made non nullable in IR5.1 in Swagger. This needs to be corrected so that DI-120 is used in multiple places and needs to be mandatory nullable. |  | Implemented | Design misaligned | DIP Users, DIP |  | Interim Release 7 | 2024-01-19 | Make DI-120 Additional Information Mandatory nullable in Swagger to align with DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-746 | RG |  | 2023-10-27 | IMserv |  | Liam Lowey | Software Provider | Swagger error - Response body doesn't match Sims& Ems implementation | Schema Bug - Different interpretation of the optional field DIPConnectionProviderID: The DIP Sim requires the property field is present, but allows for a NULL value if we are not using a connection provider. The interface spec, does not allow for a NULL value, but instead does make the field optional. So, it appears that the DipSim requires the property, even if NULL. The schema (v1.2.1) does NOT require the property but will NOT permit NULL. Please can you clarify the intention? This appears to be a blocker/breaking difference that means we will not be able to test the same code base against both DIP Sim and DIP. |  | Closed | Error/Correction | DIP Users, DIP |  |  |  | IF we are going to release a 2.2 release then this should be fixed, this has been fixed on the main code thread. This has not been fixed in rel 1.5, hence not included in the 2.2 release. The design perpetuates as described and the DIPSIM needs to align. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-747 | SB |  | 2023-10-27 | OVO | 16574 | Brian Miller | Supplier | CR028 amendment | Routing of the PUB-001 requires amending to reflect the removal of EES as recipient as per CR028 also the Change of Supply documentation redlining requires amending to reflect this |  | Closed | [5 empty] | Notify that this change already exists
MHHS-DIN-748 | RG |  | 2023-10-27 | IMserv |  | Liam Lowey | Software Provider | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength should not have a maxLength validation attribute as it is an integer type. This means the schema itself does not validate against the rules for these types of schemas. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | DI-487-Total-Number-Energised-MPANs maxLength attribute should be length as it is an integer type. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.6 | Swagger 1.6
MHHS-DIN-749 | RG |  | 2023-10-27 | IMserv |  | Liam Lowey | Software Provider | SchemaBug - DipMessage.payload is not a required property | SchemaBug - DipMessage.payload is not a required property, therefore different property names will pass validation without being checked - this means if you spell it "Payload" with a capital P instead it will effectively skip validation resulting in a false positive. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | ‘payload’ needs to be a required attribute for the DIPMessage object. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.6 | Swagger 1.6
MHHS-DIN-750 | RS |  | 2023-10-27 | REC |  | Sarah Jones | Central Body | IF-019/020 Interface notes and REG1066 validation | REG1068 was removed as part of IR4, however the neither related interface note in IF-019 and If-020 or REG1068 in the List of Registration error codes in the introduction tab have been updated. Also REG1066 should be removed for consistency. |  | Implemented | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Remove statement 'where there are multiple Related Import MPANs, the Export MPAN will only be linked with the Primary MPAN in the relationship' from IF-019 and IF-020 Interface notes Remove REG1066 validation rule from IF-019 Remove REG1066 and REG1068 from the List of Registration error codes in the introduction tab of DES138 | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138 Interface Catalogue
MHHS-DIN-751 | RS |  | 2023-10-27 | REC |  | Sarah Jones | Central Body | IF-019/020 Interface notes | Interface note for IF-019 and IF-020 states that for the avoidance of doubt, in all cases it is the LDSO, that must determine if the request to create/modify an MPAN Relationship is valid or not. The ultimate decision to allow the linking or de-linking of a MPAN within a relationship rests with the LDSO. This is correct for linked mpans but not related. Interface note to be updates to be LDSO for linked and supplier for related |  | Implemented | Design ambiguous | LDSO (SCS) |  | Interim Release 8 | 2024-03-20 | Update Interface note for IF-19 and IF-20 to state that for the avoidance of doubt, for Import/Export linkages it is the LDSO, that must determine if the request to create/modify an MPAN Relationship is valid or not. The ultimate decision to allow the linking or de-linking of a MPAN within a relationship rests with the LDSO. Related Metering Point linkages are maintained by the Supplier | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138 Interface Catalogue
MHHS-DIN-752 | RS |  | 2023-10-27 |  |  | Sarah Jones | Central Body | Change of Data Service - Forward migration for Import/Export | Yellow note box on DEL964 BPM003 Forward migration document states Export and Import MPANs will be migrated independently, this process is only relevant to Related MPANs. In addition post migration for Export and Import MPANs, the Registration Service will not automatically appoint both the MPANs to the same MS/DS but it will notify of exceptions. This should read PRE-Migration not Post migrations as per requirement MHHS-Migration-Mis-RS-022 |  | Implemented | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Amend wording to 'In addition Pre migration for Export and Import MPANs, the Registration Service will not automatically appoint both the MPANs to the same MS/DS but it will notify of exceptions'.in DEL964 and DEL963 | Process Model correction | Supporting Docs | Process model correction | DEL964 BPM003 DEL963 BPM002
MHHS-DIN-753 | SB |  | 2023-10-30 | CGI |  | Dave Webster | Software Provider | Reconciliation for smart Meter Advance Reconciliation in METH001 | In METH001, v5.2, section 3.12 it states the MAR should be carried out "at a minimum of once a month". Section 3.15 states "The maximum levels are [±0.7%] where the check is carried out at least on a weekly basis for months data or [±5%] where the check is carried out on a daily basis using daily data." These are contradictory. What is the minimum frequency this check can be carried out, is it weekly or is monthly adequate? If monthly is acceptable, should the tolerance level be [±0.7%] as per a weekly check? |  | Open - awaiting assessment | Design ambiguous | N/A |  | Post Go-live Release |  | Propose the statement in METH001 be updated to the following: Section 3.15 states "The maximum levels are [±0.7%] where the check is carried out at least on a weekly or monthly basis or [±5%] where the check is carried out on a daily basis using daily data." | Method statement correction | Supporting Docs | Method statement correction | METH001
MHHS-DIN-754 | PP |  | 2023-10-30 | Helix |  | Sedef Kiris | Central Body | Alignment of REP-005 and ISD entity | Issue statement: In TOM, Line Loss Factor (LLF) process is a new streamlined process identified with a hybrid solution combining the benefits of Salesforce and Azure to process LLF Data. However there are some ambiguity within the Design Artefacts around how ISD should be publishing LLF Data. In the MHHS BRS10 document, the requirement from MHHS is to publish the full ISD dataset on the BSC Website in a manner that is available to the public access. The data will be available in 3 separate grouping 1. LLF data 2. Master Settlement timetable 3. ISD data including UMS data However, the MHHS ERI011B ECS report document states that Line Loss Factors' specifics for Market Participants will be provided by Elexon as part of the ISD publication in the name of ELEX-REP-005 The LLF data referenced in MHHS BRS10 and ELEX REP 005, as mentioned in MHHS ERI011B, are identical but bear different names leading to confusion and ambiguity. Helix WP3 has identified this ambiguity and would like MHHS to make relevant Design artefact changes to bring more clarity. |  | Implemented | Error/Correction | All Participants |  | Interim Release 7 | 2024-01-19 | This was raised via the change board where a decision was made to push this through as a DIN REP-005 and the LLF data referenced in the design artifacts are essentially one and the same. Helix aims to meet their requirements by adhering to the specifications outlined in the Transition BRS010. To accomplish this, MHHS needs to take the following changes into consideration. The recommended solution from Helix and MHHSP is to align the Transition and End State Design Artefacts to reflect LLF Data is a deliverable of ISD and add two new ISD Entities to reflect this and remove REP-005 from the list of ECS Reports – impacts BRS010, BRS001 (Transition), ERI011B and EDI012. Remove the mention of ELEX REP 005 from MHHS ERI011B ECS report document To enable the ISD to release Line Loss Factor (LLF) data, the LLF data must be integrated into the MHHS EDI021 ISD Entity Specification document. (detailed below entity details) MHHS then align the Transition and End State Design Artefacts to reflect this change i.e All effected Design Artefacts (BRS010, ERI011B ECS report and EDI021 ISD Entity Specification ) to be updated. | Data interface correction | Supporting Docs | Various documents | BRS010, BRS001 (Transition), ERI011B, EDI012 | BRS010, BRS001 (Transition), ERI011B, EDI012
MHHS-DIN-755 | SC |  | 2023-11-01 |  |  | Sean Cooper | SRO Design | Correction to IF-035 Routing Matrix | Previous DIN created a new group B99 for SDS-MDRUpdate Rejections - this new B099 group was not updated in the Routing Matrix. This has now been corrected. |  | Implemented | Design misaligned | LDSO (SCS) |  | Interim Release 7 | 2024-01-19 | Previous DIN created a new group B99 for SDS-MDRUpdate Rejections - this new B099 group was not updated in the Routing Matrix. This has now been corrected. | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue | DES138 Interface Catalogue
MHHS-DIN-756 | SC |  | 2023-11-01 |  |  | Sean Cooper | SRO Design | Addition of IF-003 [ReverseMigration] to BPM-001 | Migration Business Process Map BPM-001 updated to include previously missing issuing of IF-003 [ReverseMigration] event from REGS to MDS, LDSO, and EES. This is triggered off the back of COS completion notice (Secured Active) from CSS to REGS. Note this is required as a definitive reverse migration notification as IF-003 [DSApp] may not always be issued. This is not a change to the migration design - step had simply been ommited from BP map. |  | Implemented | Design ambiguous | N/A |  | Interim Release 7 | 2024-01-19 | Migration Business Process Map BPM-001 updated to include previously missing issuing of IF-003 [ReverseMigNotification] event from REGS to MDS, LDSO, Supplier and EES. This is triggered off the back of COS completion notice (Secured Active) from CSS to REGS. Note this is required as a definative reverse migration notification as IF-003 [DSAppRM] may not always be issued. This is not a change to the migration design - step had simply been ommited from BP map. BPD-001 (Reverse Migration) updated accordingly | Process Model correction | Supporting Docs | Process model correction | BPM001 BPMD001 | BPM001 BPMD001
MHHS-DIN-757 | SC |  | 2023-11-01 |  |  | Sean Cooper |  | Add BP003A Link to BP003M Reverse Migration Map. Remove BP003A link from DEL963-BPM002 Forward migration | Added Missing link to show update to CSS/DCC when SDS is de-appointed on Reverse Migration. Remove the link to BP003A from DEL963-BPM002 as this is only triggered for a Change of Data Service |  | Implemented | Design gap | SDS |  | Interim Release 7 | 2024-01-19 | New process link to BP003A added to BPM003 for Smart meters at step 1008. Remove link to BP003A from DEL963-BPM002 | Process Model correction | Supporting Docs | Process model correction | BPM003 BPM002 | BPM003
MHHS-DIN-758 | SC |  | 2023-11-01 |  |  | Sean Cooper | SRO Design | 5 day check on MDR App Date in IF-034 | Per feedback from SCS, five day check on MDR Eff From Date (DI-841) changed to only apply to SDSMDRUpdate event and NOT normal/regular DS Appointment events. Thus removes clash between this check and 28 day leadtime on regular DS Apps |  | Implemented | Design gap | LDSO (SCS) |  | Interim Release 7 | 2024-01-19 | Per feedback from SCS, five day check on MDR Eff From Date (DI-841) changed to only apply to SDSMDRUpdate event and NOT normal/regular DS Appointment events. Thus removes clash between this check and 28 day leadtime on regular DS Apps. New Rule added specifically for DSSAppSPResonse | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-759 | SC |  | 2023-11-01 |  |  | Sean Cooper | SRO Design | Changes to Proposed Consent logic | Proposed Consent (DI-838) Set to Mandatory, Updated allowable values in DI-838 and DI-017 to include N - No consent. Updated ISD M17 table to include meter group and added N value for all traditional meter combinations. |  | Implemented | Design ambiguous | LDSO (SCS) |  | Interim Release 7 | 2024-01-19 | Proposed Consent (DI-838) Set to Mandatory, Updated allowable values in DI-838 and DI-017 to include N - No consent. Updated ISD M17 table to include meter group and added N value for all traditional meter combinations. | Data interface correction | Supporting Docs | Interfaces | DES138 ISD Entities | DES138
MHHS-DIN-760 | MF |  | 2023-11-01 |  |  | Mike Fensome | SRO Design | UMSDS routing | Updates to align Optionality Matrix and To Parties for UMSDS |  | Implemented | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | Updated IF-024 to remove UMSDS from To Parties. Updated Optionality Matrix to show IF-043 as N/A and IF-018 as Yes for events [DUOSTariffIDChg] and [DomPremInd] for UMSDS | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-761 | MH |  | 2023-11-03 |  | 16609 | Matt Hall |  | BP020 ver 5.1 redlined - REP D0354 | BP020 5.1 references the supplier receiving various VAS reports including REP-D0354, which isn't a VAS report at all, and isn't sent to suppliers, and REP-D0237 which should be REP-P0237 and is an internal report that doesn't go to suppliers |  | Open - awaiting assessment | Design ambiguous | Suppliers |  | Post Go-live Release |  | Review reports contained in BP020 and correct | Process Model correction | Supporting Docs | Process model correction | BP020
MHHS-DIN-762 | MH |  | 2023-11-03 |  |  | Matt Hall | SI Design | DEL961 IF-003 routing to MDS - Update Migration Document | DEL961 needs updating to reflect the clarifications made in DIN-756 that IF-003 should be routed to MDS on [ReverseMigration] and [DSApp] events, not [MSApp] |  | Implemented | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Section 8 of DES961 updated to remove LDSO and Elexon Central Systems receiving MS Deappointment in line with DES-138 | Process Model correction | Supporting Docs | Process model correction | DEL961 - Migration Design Document
MHHS-DIN-763 | RS |  | 2023-11-06 |  | 15975 | Sarah Jones | Central Body | Related Metering Points undergoing Migration | Change to the Registration Service Requirements introduced through IR3 (DIN423). proposed change to RS-146 to remove 'and Related MPANs': Registration must only carry out auto-alignment of Linked MPANs (Import/Export) and Related MPANs if all MPANs in the group have migrated to the MHHS operation. |  | Implemented | Design ambiguous | Suppliers |  | Interim Release 8 | 2024-03-20 | Amend wording to RS-146 from Registration must only carry out auto-alignment of Linked MPANs (Import/Export) and Related MPANs if all MPANs in the group have migrated to the MHHS operation. to Registration must only carry out auto-alignment of Linked MPANs (Import/Export) if all MPANs in the group have migrated to the MHHS operation. | Requirement correction | Registration | Requirement correction | BRS003 - Registration Service Requirements
MHHS-DIN-764 | MF | DI-236 | 2023-11-06 | St Clements |  | Mike Fensome | SRO Design | Additional validation rule in IF-031 to ensure appointments are contiguos | Add new validation rules in IF-031 to ensure that if there is no Service Provider appointed, the Proposed Service Provider Appointment Date is equal to SSD or Previous Service Provider De-appointment Date + 1 |  | Implemented | Design gap | LDSO (SCS) |  | Interim Release 7 | 2024-01-19 | Added two new validation rules in IF-031 to ensure that if there is no Data Service/ Metering Service currently appointed then the Proposed DS/ MS Appointment Date must equal SSD or Previous DS/MS De-appointment Date + 1. Error message of REG 1032 issued if the check fails. | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-765 | SW |  | 2023-11-07 |  | 18247 | Steve Weston | SI Design | Inconsistencies in E2E001 JSON examples with Swagger | There are some minor / non-consequential inconsistencies and spelling mistakes in some of the examples provided in the E2E001 design, that do not align with Swagger that need to be corrected in the E2E001 design document |  | Open - awaiting assessment | Design ambiguous | DIP Users |  | Post Go-live Release |  | In section 4.5.6.3 example JSON, "receive" is incorrectly spelt "recieve" in both the header and payload body. The JSON payload is malformed. There's an extra "{" which is not closed and a missing comma after the second "message. These have both been amended in the E2E001 design to align with Swagger. Section 4.5.6.2 says "Where a field is not written/available/optional, then a null value needs to be written". That's not done in the example, which just omits multiple fields. This has been amended in the E2E001 design to align with Swagger. Section 4.5.6.2 says "The response uses the common Standard Response body" but the example includes "recieveEventCallback", is missing "timestamp", and names the array of responses "events" rather than "messageArray". All of which differ from the Standard Response body defined in https://app.swaggerhub.com/apis/MHHSPROGRAMME/SubmitEvents/1.5.1#/StandardResponse. This has been amended in the E2E001 design to align with Swagger. Is the "message" field meant to contain one of a list of allowed responses? - Is the trailing whitespace in "DIP0000 ok ", no trailing whitespace is required, so this has been updated in all example JSON’s where this applies. - The "DIP0000 ok" value for the "message" field is different to the other success messages used in this doc. E.g section 4.4.4.2 uses "Message OK " to represent success and the DIP simulator uses "message": "MSG0000 - Success". Is one of those the correct one? The message returned should align with the messages defined in the Introduction tab in the DES-138 Interface Catalogue. The DIP simulator is returning the correct values, as is the DIP. In this instance, as above, the example is not quite aligned in the E2E001 design so the messages need to align with what is defined in the Introduction tab in the DES-138 Interface | Design Ambiguous | Supporting Docs | Interfaces | E2E001 | E2E001
MHHS-DIN-766 | ZH | DIN-464 | 2023-11-07 | SIMS |  | Kyle Abraham | Software Provider | Clarity required on values expected for /dip-channel/{id} for submitEvents on Swagger | The {id} in /dip-channel/{id} for submitEvents on Swagger should accept values that are the same as the enumeration in DI-000 to ensure consistency. At the moment, this is not clear in Swagger, so this needs to be updated to make this clearer. |  | Implemented | Design misaligned |  |  | Interim Release 2.2 |  | Updates made to Swagger 1.2.2, so the correct enumerations / values are available to align with values in DI-000 to ensure consistency and avoid any ambiguity between interfaces and reports. Updated to remove PublicationConfig and RestConfig in favour of a single config WebhookConfig. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.2.2 | Swagger 1.2.2
MHHS-DIN-767 | SW | DIN-772 | 2023-11-13 | C&C | 19150 | Chris Lenihan | Software Provider | Swagger incorrect for IF-043 | For IF-043 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-043-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. |  | Implemented | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Update IF-043 so that it uses the required property name is ‘CustomBlock’ but the actual name is ‘IF-043-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger | DES138 Swagger
MHHS-DIN-768 | SW |  | 2023-11-13 |  | 19136 | John Edmonds-Bell | SI Design | Event Code inconsistency between Swagger and ECS Reports for REP-901 | On REP-901 report, the event code in the reports catalogue is defined [DUoS_EmbeddedLDSO_Agg_Inv_Data] and [DUoS_Supplier_Agg_Inv_Data] whereas on the Swagger Document it’s DUoSSupplierInvData. Need to fix this inconsistency innSwagger. |  | Implemented | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Update the ECS reports catalogue to align with Event Code naming standard (used in other Interfaces) and to align with Swagger. On REP-901 report, the event code in the reports catalogue is defined [DUoS_EmbeddedLDSO_Agg_Inv_Data] and [DUoS_Supplier_Agg_Inv_Data] whereas on the Swagger Document it’s DUoSSupplierInvData. Swagger has also been updated to align. | Data interface correction | Supporting Docs | ESC Report | ECS Report Swagger | ECS Report Swagger
MHHS-DIN-769 | RG |  | 2023-11-13 |  |  | Rob Golding | SRO | Updates to MHHSP-ERI011B (IR5) not reflected in the swagger | There appears to be several updates to the reporting spreadsheet that did not have a corresponding update in the swagger. The R901-05 block in Swagger is missing an attribute; DI-613. The spreadsheet has incorrect SVA data types for these two new items |  | Implemented | Design misaligned | Helix, DIP, Suppliers, LDSOs |  | Interim Release 7 | 2024-01-19 | Update R901-05 block in Swagger; DI-613. Update MHHSP-ERI011B; the incorrect SVA data types for these two new items. | Data interface correction | Supporting Docs | Interfaces | MHHSP-ERI011B, Swagger | MHHSP-ERI011B, Swagger
MHHS-DIN-770 | SW | DIN-773 | 2023-11-13 |  | 18780 | Chris Lenihan | Software Provider | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025 | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025. This needs to be updated in the list of enumerated value to be IF-026. |  | Implemented | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025. This needs to be updated in the list of enumerated value to be IF-026 in Swagger. | Design Ambiguous | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-771 | RG |  | 2023-11-13 |  |  | Rob Golding | SRO | R900-03. listOfMPANSOnsite should be listOfMPANSOnSite | Typo in swagger - R900-03. listOfMPANSOnsite should be listOfMPANSOnSite |  | Implemented | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Update R900-03. listOfMPANSOnsite to listOfMPANSOnSite | Design Ambiguous | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-772 | SW | DIN-767 | 2023-11-13 | C&C | 19150 | Chris Lenihan | Software Provider | Swagger incorrect for IF-043 | For IF-043 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-043-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. |  | Implemented | Design misaligned | DIP Users, DIP |  | Interim Release 5.2 |  | Update IF-043 so that it uses the required property name is ‘CustomBlock’ but the actual name is ‘IF-043-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. | Design Ambiguous | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-773 | SW | DIN-770 | 2023-11-13 |  | 18780 | Chris Lenihan | Software Provider | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025 | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025. This needs to be updated in the list of enumerated value to be IF-026. |  | Implemented | Design misaligned | DIP Users, DIP |  | Interim Release 5.2 |  | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025. This needs to be updated in the list of enumerated value to be IF-026 in Swagger. | Design Ambiguous | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-774 | RG |  | 2023-11-15 |  |  | Rob Golding | SRO | IF-020 [LinkedImportExportRemove] & [RelatedRemove] | The B090 block needs to be optional to cope with the scenario where a linked/related meter is removed and it leaves the situation that there are no linked/related meters. Also, on line 64 it mentions a B074 block, however, there is no B074 block in the message |  | Closed | [5 empty] | Fix the swagger and DES138 to reflect this condition | Design Ambiguous | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-775 | MF |  | 2023-11-15 |  |  | Sarah Jones | Central Body | Remove Customer Direct Process from BP002/BP003 | The Customer Direct process has been set out in BP010 (DIN-554) so can be removed from BP002/BP003 to avoid any confusion |  | Open - awaiting assessment | Clarification - No change required | N/A |  | Post Go-live Release |  | Remove Customer Direct process steps from BP002/BP003 | Process Model correction | Supporting Docs | Process Models | BP002 BP003 | BP002 BP003
MHHS-DIN-776 | MH |  | 2003-11-16 | Elexon |  | Sedef Kiris | Central Body | LLF Data and Rep005 | There is some ambiguity within the Design Artefacts around how ISD should be delivering LLF Data and REP-005. ​ BRS010 implies ISD will publish it through a common delivery method as the Master Settlement Timetable and the rest of the ISD entities, but it does not mention REP-005.​ BRS001 (Transition) denotes that REP-005 will be published via the Elexon Portal and will utilise IF-047. ​ ERI011B denotes that the distribution pattern and the report format of REP-005 are to be defined by Elexon. ​ EDI021 does not include any ISD entities for LLF data. ​ REP-005 and the LLF data mentioned in the design artefacts are the same thing, and Helix intend to fulfil their requirements by delivering in line with requirements as laid out in the Transition BRS. ​ Impact: There is a potential lack of clarity amongst Participants around how they are going to receive REP-005, inconsistency in the overall solution of data coming from ISD. |  | Closed | [5 empty] | Duplicate - To be tracked under MHHS-DIN-754
MHHS-DIN-777 | RG | DIN-785 | 2023-11-16 | SRO | 20939 20723 | Rob Golding |  | IF-001-ChangeOfSupplier required fields on CommonBlocks are incorrect | The required fileds on the common block are set to commonblock and customblock, they need to be set to S1 etc. |  | Implemented | Design misaligned | DIP Users |  | Interim Release 5.2 |  | The required fileds on the common block are set to commonblock and customblock, they need to be set to S1 etc. This has been updated in Swagger so the common block in IF-001 now contains the correct required blocks. Only an issue with 5.+ not 2.+ | Design Ambiguous | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-778 | RG |  | 2023-11-17 | Stark |  | Rob Golding | Supplier | Fix enumeration on the PUB domain for the following PUBs; PUB-004, PUB-019, PUB-020, PUB-040 and PUB-050 in DT-983. Same IF's added for DT-000. | There are a number of values missing from the enumeration in the DT-983 for the Interfaces defined. These are PUB-004, PUB-019, PUB-020, PUB-040 and PUB-050. There are a number of values missing from the enumeration in the DT-000 for the Interfaces defined. These are IF-004, IF-019, IF-020, IF-040 and IF-050. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 2.3 |  | PUB-004, PUB-019, PUB-020, PUB-040 and PUB-050 are missing from DT-983 that defines the enumeration of available values, so these have been added. IF-004, IF-019, IF-020, IF-040 and IF-050 are missing from DT-000 that defines the enumeration of available values, so these have been added. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-779 | SC |  | 2023-11-20 | IMServ |  | Sean Cooper |  | Routing for IF-041 | Add Data Service to Primary Routing for SDS issued IF-041's to align with BP003C |  | Implemented | Design misaligned | SDS |  | Interim Release 7 | 2024-01-19 | Added Data Service (where required) to Primary Routing in the SDS row of IF-041 routing table | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-780 | SB |  | 2023-11-21 | St Clements | 19885 | Madison Layton | Central Body | No longer providing examples within the Interface Catalogue | Updates to the swagger and Interface Catalogue will no longer have examples detailed within the Interface catalogue |  | Closed | [5 empty] | Examples are now managed in Swagger
MHHS-DIN-781 | BK | DIN-748, DIN-783 | 2023-11-21 | IMserv |  | Liam Lowey | Software Provider | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength should not have a maxLength validation attribute as it is an integer type. This means the schema itself does not validate against the rules for these types of schemas. |  | Implemented | Design misaligned | DIP Users |  | Interim Release 2.3 |  | DI-487-Total-Number-Energised-MPANs maxLength attribute should be length as it is an integer type. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-782 | BK | DIN-749, DIN-784 | 2023-11-21 | IMserv |  | Liam Lowey | Software Provider | SchemaBug - DipMessage.payload is not a required property | SchemaBug - DipMessage.payload is not a required property, therefore different property names will pass validation without being checked - this means if you spell it "Payload" with a capital P instead it will effectively skip validation resulting in a false positive. |  | Implemented | Design misaligned | DIP Users |  | Interim Release 2.3 |  | ‘payload’ needs to be a required attribute for the DIPMessage object. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-783 | BK | DIN-748, DIN-781 | 2023-11-21 | IMserv |  | Liam Lowey | Software Provider | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength should not have a maxLength validation attribute as it is an integer type. This means the schema itself does not validate against the rules for these types of schemas. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | DI-487-Total-Number-Energised-MPANs maxLength attribute should be length as it is an integer type. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-784 | BK | DIN-749, DIN-782 | 2023-11-21 | IMserv |  | Liam Lowey | Software Provider | SchemaBug - DipMessage.payload is not a required property | SchemaBug - DipMessage.payload is not a required property, therefore different property names will pass validation without being checked - this means if you spell it "Payload" with a capital P instead it will effectively skip validation resulting in a false positive. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger updated so that ‘payload’ has been added as a required attribute for the DIPMessage object. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-785 | BK | DIN-777 | 2023-11-21 | SRO | 20939 20723 | Rob Golding |  | IF-001-ChangeOfSupplier required fields on CommonBlocks are incorrect | The required fields on the common block are set to commonblock and customblock, they need to be set to S1 etc. |  | Implemented | Design misaligned |  |  | Interim Release 7 | 2024-01-19 | Update IF-001-ChangeOfSupplier required fields on CommonBlocks that are incorrect | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-786 | MF | DI-238 | 2023-11-21 | St Clements |  | Mike Fensome |  | Determination of Market Segment Effective From Date | Add clarification on how Registration Service will set Market Segment Effective From Date |  | Implemented | Clarification - No change required | SCS |  | Interim Release 7 | 2024-01-19 | Added new section to REGS_Notes to clarify how Market Segment EFD is set by Registration Service. The table below outlines how the Registration Service will Derive Market Segment Effective From Date, following various 'trigger' events. Market Segment Change Trigger Derived Market Segment EFD Notes Connection Type Connection Type EFD If triggers a change to related/associated MPANs SEG use the same derived EFD, except in the case this is prior to the relationship/association EFD in which case use relationship/association EFD instead Meter Added/Meter Type changed Meter Installation Date Meter Removed Meter Removal Date If trigger is a Meter Exchange use installation date not removal date Relationship Created Relationship EFD Only amend SEG EFD for MPANs where the SEG is changing – SEG of some MPANs in the relationship/association will not be changing Relationship Deleted Relationship ETD Association Created Association EFD Association Deleted Association ETD Where derived EFD is less than the current Market Segment EFD, the current Market Segment EFD will be cancelled to allow for the new one. | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-787 | BK |  | 2023-11-21 | RECCo |  | Sarah Jones | Central Body | Typo in the data item name for DI20228 - DIP Roles / IDs Always Receipient ID (DI-993 in the Interface Catalogue) | It has been noted that there is a typo in the data item name for DI20228 - DIP Roles / IDs Always Recipient ID |  | Implemented | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | Correction of spelling on the word 'Recipient' against DI-993 in the Interface Catalogue | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-788 | SC |  | 2023-11-22 | St Clements |  | Madison Layton | Software Provider | Reconnection of MPAN (provided that CSS DeRegistration has not completed) | New BP009B - would need IF-009 Event Code. "Reconnected" to SUPC only and Re-issue of IF-50 to EES for MPRS Status code. Current MHHS design does not cater for the re-connection of an MPAN that has previously been dis-connected​ Under current operation this is allowed for via a Manual amendment request by the LDSO (Covered by BSCP604) where the MPAN has not been Registration De-activated |  | Implemented | Design gap | St Clements, Suppliers |  | Interim Release 7 | 2024-01-19 | ​Update to BP007 (Disconnection) to show the flows where an MPAN is re-connected ​ Update to BRS003 to add requirement for Registration Service triggering the IF-009 and IF-050 to inform of a re-connection​ Update to BRS004 to add requirement for Suppliers receiving PUB-009 [MPANReconnection]​ Update DES-138 to add new [MPANReconnection] event code to IF-009​ Update to Swagger to add IF-009 MPANReconnection event code variant to Swagger. | Process Model correction | Supporting Docs | Various documents | BP007, BR003, BR004, DES-138, Swagger | BP007, BR003, BR004, DES-138, Swagger
MHHS-DIN-789 | BK | DIN-673 | 2023-11-22 | Design Team |  | Rob Golding | Programme Design | Floating Point number regexes | DIN 267 inadvertently updated regexes to a pattern which does not align to the agreed format as of Technical Design Working Group Work-Off Issue D-0408th November 2022. The regexes need to align to what was agreed. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 2.3 |  | Update regex patterns for the following data types: DT-016, DT-022, DT-023, DT-024, DT-025, DT-030, DT-031, DT-032, DT-033 | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-790 | BK | DIN-791 | 2023-11-22 | Design Team |  | Rob Golding | Programme Design | Number regex - DI-123 | Update regex patterns for the following data type: DI-123 |  | Implemented | Error/Correction | DIP Users |  | Interim Release 2.3 |  | Update regex patterns for the following data type: DI-122 | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-791 | BK | DIN-790 | 2023-11-22 | Design Team |  | Rob Golding | Programme Design | Number regex - DI-123 | Update regex patterns for the following data type: DI-123 |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Added regex patterns for the following data type: DI-123 to use the following pattern: ^\d{4,4}$ | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-792 | BK | DIN-790, DIN-791 | 2023-11-22 | Design Team |  | Rob Golding | Programme Design | Number regex - DI-123 | Update regex patterns for the following data type: DI-123 |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Update regex patterns for the following data type: DI-123 | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-793 | SB |  | 2023-11-23 | St Clements | 21513 | Madison Layton | Central Body | DI-241 - SUPC routing on IF-037 incorrect, should be SUPS | SUPC was moved to primary routing for IR5 release, as per attached. However it was clarified on a COS this would be the old Supplier not the current Supplier, so SUPC will not always be correct. Needs to be changed for clarity, SUPS could be used to indicate IF-037 will be sent to the Supplier that submitted the original SP appointment for the SP being de-appointed? |  | Implemented | Clarification - No change required | St Clements |  | Interim Release 7 | 2024-01-19 | Updated primary routing on IF-037 from SUPC to Supplier. On a COS, Registration Service will send to the old Supplier, on Change of Service Provider to the Current Supplier. | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-794 | MH | DIN-409 | 2023-11-23 | Elexon | 19961 | Sedef Kiris | Central Body | ISD Consumption Component Classes M5 | In the ISD entity, there was an adjustment made by DIN 409 to distinguish the settlement quality indicator with the same CCC ID. While the ISD Entities specification document has been appropriately updated, the corresponding changes have not been reflected in the MDS method statement Appendix 1. This inconsistency is causing confusion. |  | Implemented | Error/Correction | Elexon |  | Interim Release 7 | 2024-01-19 | The example provided in Appendix 1 in the METH007 is wrong and misleading. As a correct example is provided in the ISD Entities document, we'll remove the one in METH007 | Method statement correction | Meter to Bank | Method Statement | METH007 | METH007
MHHS-DIN-795 | MH | DIN-678 | 2023-11-23 | Elexon | 18841 | Rashmi Radhakrishnan | Central Body | ISD M9 Clarification | DIN-678 was to change the length of the following UMS data items in ISD: Unit description 1, 2 and Manufacturer's Designation. But Manufacturer's Designation was not changed in both M9 and M10. This iDIN is to complete that update. |  | Implemented | Design misaligned | Elexon, UMSDS |  | Interim Release 7 | 2024-01-19 | Update Manufacturer's Designation in ISD Entity M9 to up to 100 characters | Requirement correction | Supporting Docs | ISD | EDI021 | EDI021
MHHS-DIN-796 | MF | DIN-234 | 2023-11-23 | St Clements |  | Madison Layton | Software Provider | Clarification on validation of B018 block conditionality in IF-034 | Clarification that SCS will validate that a Smart Meter is present for Block B018 conditionality by checking that DCC Service Flag (DI-025) is A |  | Implemented | Clarification - No change required | SCS |  | Interim Release 7 | 2024-01-19 | Note added to IF-034 interface to clarify that SCS will validate that a Smart Meter is present for Block B018 conditionality by checking that DCC Service Flag (DI-025) is A | Data interface correction | Supporting Docs | Interfaces | DES-138 | DES-138
MHHS-DIN-797 | BK |  | 2023-11-24 | Design Team |  | Rob Golding | Programme Design | Capitalisation in Swagger | E2E001 Architecture document will be updated to reflect the adherence to case sensitivity on the inbound messages, and the removal of the statement in Swagger relating to case insensitivity. |  | Implemented | Design gap | DIP Users |  | Interim Release 2.3 |  | Updating of the Swagger and E2E001 to align to Open API standards in relation to case sensitivity. The Section in the E2E001 is 4.4.3 and Swagger its the removal of a comment at the top of swagger file | Data interface correction | Supporting Docs | Interfaces | Swagger, E2E Architecture Document | Swagger, E2E Architecture Document
MHHS-DIN-798 | BK |  | 2023-11-24 | Design Team |  | Rob Golding | Programme Design | Capitalisation in Swagger | E2E001 Architecture document will be updated to reflect the adherence to case sensitivity on the inbound messages, and the removal of the statement in Swagger relating to case insensitivity. |  | Implemented | Design gap | DIP Users |  | Interim Release 5.2 |  | Updating of the Swagger and E2E001 to align to Open API standards in relation to case sensitivity. The Section in the E2E001 is 4.4.3 and Swagger its the removal of a comment at the top of swagger file | Data interface correction | Supporting Docs | Interfaces | Swagger, E2E Architecture Document | Swagger, E2E Architecture Document
MHHS-DIN-799 | SW |  | 2023-11-24 | Design Team |  | Rob Golding | Programme Design | Capitalisation in Swagger | E2E001 Architecture document will be updated to reflect the adherence to case sensitivity on the inbound messages, and the removal of the statement in Swagger relating to case insensitivity. |  | Implemented | Design gap | DIP Users |  | Interim Release 7 | 2024-01-19 | Updating of the Swagger and E2E001 to align to Open API standards in relation to case sensitivity. The Section in the E2E001 is 4.4.3 and Swagger its the removal of a comment at the top of swagger file | Data interface correction | Supporting Docs | Interfaces | Swagger E2E001 Architecture Document | Swagger, E2E Architecture Document
MHHS-DIN-800 | SW |  | 2023-11-27 | Design Team |  | Steve Weston | Programme Design | ECS Reports Inconsistency with Swagger | Inconsistency between ECS Reports Catalogue and Swagger: REP-002B -- R027 and R013 - Distributor and GSP blocks appear to be missing from REP-002B in Swagger. REP-003 -- R024 contains DI-496 in the ECS reports, but in Swagger it contains DI-307. REP-003 -- R9017 contains correctAndUncorrectComponent does not contain block R018 in the name. REP-004 -- R025 and R026 should have parent of R009 according to ECS catalogue, but Swagger has these defined with no parent. REP-006 -- R003 contains R033. R033 should have DI-496, 374, 359, and 360, but in Swagger, contains 307, 374, 359 & 360. REP-006 -- R051 says parent is R032 in ECS reports catalogue, but R051 does not appear in the Swagger in R032. As a result, R106 or R107 which should be part of R051 is missing. REP-009 -- The R013 block contains R016 in Swagger, but in the ECS Catalogue, this is R013 > R068. REP-900 -- R900-03 contains DI-345 in Swagger, when it should contain DI-612. Also marked incorrectly as required. |  | Closed | Design misaligned | DIP Users |  |  |  | Inconsistency between ECS Reports Catalogue and Swagger. For all items below, Swagger is to be updated to align with the ECS Reports Catalogue: REP-002B -- R027 and R013 - Distributor and GSP blocks are missing from REP-002B in Swagger. Add missing blocks. REP-003 -- R024 contains DI-496 in the ECS reports, but in Swagger it contains DI-307. Update to DI-496. REP-003 -- R9017 contains correctAndUncorrectComponent does not contain block R018 in the name. Update naming. REP-004 -- R025 and R026 should have parent of R009 according to ECS catalogue, but Swagger has these defined with no parent. Update Swagger to align. REP-006 -- R003 contains R033. R033 should have DI-496, 374, 359, and 360, but in Swagger, contains 307, 374, 359 & 360. Update to DI-496. REP-006 -- R051 says parent is R032 in ECS reports catalogue, but R051 does not appear in the Swagger in R032. As a result, R106 or R107 which should be part of R051 is missing. Add the missing blocks to align. REP-009 -- The R013 block contains R016 in Swagger, but in the ECS Catalogue, this is R013 > R068. Update R013 in Swagger to contain R068. REP-900 -- R900-03 contains DI-345 in Swagger, when it should contain DI-612. Also marked incorrectly as required. Update Swagger to use DI-612. Closed as decision made to only align ECS Reports changes to IR7. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-801 | SW |  | 2023-11-27 | Design Team |  | Steve Weston | Programme Design | ECS Reports Inconsistency with Swagger | Inconsistency between ECS Reports Catalogue and Swagger: REP-002B -- R027 and R013 - Distributor and GSP blocks appear to be missing from REP-002B in Swagger. REP-003 -- R024 contains DI-496 in the ECS reports, but in Swagger it contains DI-307. REP-003 -- R9017 contains correctAndUncorrectComponent does not contain block R018 in the name. REP-004 -- R025 and R026 should have parent of R009 according to ECS catalogue, but Swagger has these defined with no parent. REP-006 -- R003 contains R033. R033 should have DI-496, 374, 359, and 360, but in Swagger, contains 307, 374, 359 & 360. REP-006 -- R051 says parent is R032 in ECS reports catalogue, but R051 does not appear in the Swagger in R032. As a result, R106 or R107 which should be part of R051 is missing. REP-009 -- The R013 block contains R016 in Swagger, but in the ECS Catalogue, this is R013 > R068. REP-900 -- R900-03 contains DI-345 in Swagger, when it should contain DI-612. Also marked incorrectly as required. |  | Implemented | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Inconsistency between ECS Reports Catalogue and Swagger. For all items below, Swagger is to be updated to align with the ECS Reports Catalogue: REP-002B -- R027 and R013 - Distributor and GSP blocks are missing from REP-002B in Swagger. Add missing blocks. REP-003 -- R024 contains DI-496 in the ECS reports, but in Swagger it contains DI-307. Update to DI-496. REP-003 -- R9017 contains correctAndUncorrectComponent does not contain block R018 in the name. Update naming. REP-004 -- R025 and R026 should have parent of R009 according to ECS catalogue, but Swagger has these defined with no parent. Update Swagger to align. REP-006 -- R003 contains R033. R033 should have DI-496, 374, 359, and 360, but in Swagger, contains 307, 374, 359 & 360. Update to DI-496. REP-006 -- R051 says parent is R032 in ECS reports catalogue, but R051 does not appear in the Swagger in R032. As a result, R106 or R107 which should be part of R051 is missing. Add the missing blocks to align. REP-009 -- The R013 block contains R016 in Swagger, but in the ECS Catalogue, this is R013 > R068. Update R013 in Swagger to contain R068. REP-900 -- R900-03 contains DI-345 in Swagger, when it should contain DI-612. Also marked incorrectly as required. Update Swagger to use DI-612. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-802 | SW |  | 2023-11-27 | Design Team |  | Steve Weston | Programme Design | Naming standards are inconsistently applied in ECS reports catalogue for nested structures and lists. | Naming standards are inconsistently applied in ECS reports catalogue for nested structures and lists, meaning it you have blocks that contain blocks with the same name, as there is no naming mechanism to easily link nested block name to contains, or back to ECS reports catalogue. |  | Closed | [5 empty] | Implement a new naming standard for ECS reports catalogue. Closed as decision made to only align ECS Reports changes to IR7. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-803 | SW |  | 2023-11-27 | Design Team |  | Steve Weston | Programme Design | Naming standards are inconsistently applied in ECS reports catalogue for nested structures and lists. | Naming standards are inconsistently applied in ECS reports catalogue for nested structures and lists, meaning it you have blocks that contain blocks with the same name, as there is no naming mechanism to easily link nested block name to contains, or back to ECS reports catalogue. |  | Implemented | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Implement a new naming standard for ECS reports catalogue for nested structures and lists. | Data interface correction | Supporting Docs | Interfaces | ECS Reports Catalogue | ECS Reports Catalogue
MHHS-DIN-804 | SB |  | 2023-11-28 | ESG | 22206 | Patricia Parker | Software Provider | Migration clarification | Page 13 of the migration document states the following for Forward Migration CoA 14. The Registration Service will send the IF-036 at the Service Appointment effective from date. The sending of the IF-036 will act as the definitive indicator that a Forward Migration has completed. Is the IF_036 not sent at the Service Appointment effective from date – 1 . Registration Service will have processed all Secured Active Messages and processed the Pending Appointment Queue by 21:00. This will include the production and publication of all required IF-035, IF-036 and IF-037 messages. |  | Closed | Clarification - No change required |  |  |  |  | Already discussed and agreed for SDS to determine solution.
MHHS-DIN-805 | RG |  | 2023-11-29 | SRO |  | Rob Golding | SRO Design | Examples in swagger incorrectly resolved if have a leading 0 | Sims & Ems noted that the example for DI-123-SSC was resolving to the value 83 when in fact it should be 0123. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Tracked down a bug in swaggerhug, doesn't like leading zero on non-string delimted examples. Work around is to string delimit. Also added regular expression pattern - ^\d{4,4}$. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-806 | SW |  | 2023-11-29 | Electralink | 21470 | Roz Turner | Central Body | Details of the compression team are not defined in the E2E001 design document, only in CR030 at a high level | There is currently no detail in the E2E001 of how data should be compressed and uncompressed for the ECS reports, this information is held in CR030 and DRG documentation. This DIN is to update the E2E001 Architecture design document to add a section to explain this in more detail. |  | Closed | [5 empty] | Closed - will be picked up in IR7 as part of DIN-806 | Data interface correction | Supporting Docs | Interfaces | Swagger, E2E Architecture Document | Swagger, E2E Architecture Document
MHHS-DIN-807 | SW |  | 2023-11-29 | Electralink | 21470 | Roz Turner | Central Body | Details of the compression team are not defined in the E2E001 design document, only in CR030 at a high level | There is currently no detail in the E2E001 of how data should be compressed and uncompressed for the ECS reports, this information is held in CR030 and DRG documentation. This DIN is to update the E2E001 Architecture design document to add a section to explain this in more detail. |  | Implemented | Design ambiguous | DIP Users |  | Interim Release 7 | 2024-01-19 | Updated the E2E001 Architecture design document to add a section to explain how data should be compressed and uncompressed for the ECS reports. | Data interface correction | Supporting Docs | Technical Design | E2E001 Architecture Document | E2E Architecture
MHHS-DIN-808 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-007 EnergisationStatusChange/Failure CustomBlocks missing required attribute | Missing required (mandatory) attribute in object (B025 and B040) |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for inclusion of missing attribute in IF-007. This was adding B025 block as required block in the EnergisationStatusChnage variant of IF-007 and adding B040 block as a required block in the EnergisationStatusFailure variant of IF-007. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-809 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-008 EnergisationStatusChange, common block for R0 and CustomBlocks for B025 block missing required attribute | Missing required (mandatory) attribute in object (R0 and B025) |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for inclusion of missing attribute in IF-008. This was adding R0 block as required block in the Common block of IF-008 and adding B025 block as a required block in the CustomBlock of IF-008. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-810 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-004 common block M0 required attribute is missing | Missing required attribute in object |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for inclusion of missing attribute M0 in the required common block in IF-004 | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-811 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-024 missing required attributes in blocks | IF024 SNVacant CustomBlock required B057 IF024 SNRemoteEnabled CustomBlock required B057, B069 IF024 SNSupplierAC CustomBlock required B057, B058 |  | Closed | Error/Correction | DIP Users |  |  |  | Swagger update for inclusion of missing attribute in IF-024 | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-812 | RG | DIN-699 | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-036 missing required attributes for B068 block | Missing required attribute in object |  | Closed | Error/Correction | DIP Users |  |  |  | Swagger update for inclusion of missing attribute in IF-036 | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-813 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-015 incorrect required Custom Block | There is no customblock on IF-015 |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for removal of custom block in IF-015, as there is no CustomBlock on IF-015. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-814 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-045 incorrect name on Custom block | For IF-045 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-045-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for incorrect name of custom block in IF-045, this has been renamed to CustomBlock. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-815 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | DI-838-Supplier-Proposed-Consent-Granularity requires a null enum | This is to match nullable:true from DES-138. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for DI-838 to allow null in the enumerated list of values. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-816 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-001 Custom Block missing addtional properties false attribute | IF-001 Custom Block missing addtional properties false attribute |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for inclusion of missing attribute in IF-001 | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-817 | SW |  | 2023-11-29 | Helix |  | Steve Weston | SI Design | Incorrect examples in Swagger for Integers that start with 0 (bug in Swagger Hub) | There are incorrect examples provided for some properties, for example SSC (DI-123) in B032 in the Submit Events on SwaggerHub. This is partly a bug in Swagger Hub where the properties should not start with a '0'. |  | Closed | Error/Correction | DIP Users |  |  |  | Duplicate of DIN-805
MHHS-DIN-818 | SW |  | 2023-11-29 | Helix |  | Steve Weston | SI Design | IF-014 Payload does not implement B900 block correctly to align with IF-021. | IF-014 should contain a B900 block, not a B900 array. This change was made in IR5 for IF-021, but was only applied to IF-014 in IR6. This DIN is to align with IF-021 for IR5 and ensure that B900 used, not an array of B900's. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update to IF-014 to align with IR6 implementation | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-819 | SW |  | 2023-11-29 | Helix |  | Steve Weston | SI Design | Typo in event code for REP-004 | In REP-004, the eventCode = [SuplierDemandTakeReport], and supplier is spelt incorrectly. This needs to be updated in both the ECS reports catalogue and Swagger |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Update REP-004 and Swagger the eventCode = [SuplierDemandTakeReport], and supplier is spelt incorrectly. | Data interface correction | Supporting Docs | Interfaces | Swagger, ECS Report | Swagger, ECS Report
MHHS-DIN-820 | SW |  | 2023-11-29 | Procode | 21898, 21073 | Steve Weston | SI Design | IF-041 contains B06465list that uses anyOf when this should be oneOf B064 or B065 to align with DES-138. | IF-041 contains B06465list that uses anyOf when this should be one of either B064 or B065 to align with DES-138. This needs to be updated so that this list contains wither a B064 list OR B065 list, not both / either. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update to align IF-041 to DES-138. Any of has been removed from the Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-821 | SW | DIN-820 | 2023-11-29 | Procode | 21898, 21073 | Steve Weston | SI Design | IF-041 contains B064/65 list that uses anyOf when this should be oneOf B064 or B065 to align with DES-138. | IF-041 contains B064/65 list that uses anyOf when this should be one of either B064 or B065 to align with DES-138. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Swagger is aligned to DES-138 to allow one or both B064 and B065. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-822 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-007 EnergisationStatusChange/Failure CustomBlocks missing required attribute | Missing required attribute in object (B025 and B040 respectively are missing from IF-007 EnergisationStatusChange/Failure CustomBlocks. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Missing required attribute in object (B025 and B040 respectively are missing from IF-007 EnergisationStatusChange/Failure CustomBlocks. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-823 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-008 EnergisationStatusChange, common block for R0 and CustomBlocks for B025 block missing required attribute | IF-008 EnergisationStatusChange, common block for R0 and CustomBlocks for B025 block missing required attribute |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Swagger update for inclusion of missing attribute in IF-008 - IF-008 EnergisationStatusChange, common block for R0 and CustomBlocks for B025 block missing required attribute | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-824 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-004 common block M0 required attribute is missing | IF-004 common block M0 required attribute is missing |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | IF-004 common block M0 required attribute is missing, so this has been added in the Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-825 | RG | DIN-881 | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-024 missing required attributes in blocks | IF024 SN-Vacant CustomBlock required B057 IF024 SN-NoComms CustomBlock required B057 IF024 SNRemoteEnabled CustomBlock required B057, B069 IF024 SNSupplierAC CustomBlock required B057, B058 |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Swagger update for inclusion of missing attribute in IF-024 IF024 SN-Vacant CustomBlock required B057 IF024 SN-NoComms CustomBlock required B057 IF024 SNRemoteEnabled CustomBlock required B057, B069 IF024 SNSupplierAC CustomBlock required B057, B058 | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-826 | RG | DIN-699 | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-036 missing required attributes for B068 block | Missing required attribute in object |  | Closed | Error/Correction | DIP Users |  |  |  | Duplicate of DIN-699 Swagger update for inclusion of missing attribute in IF-036 |  |  |  |  | Swagger
MHHS-DIN-827 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-015 incorrect required Custom Block | There is no customblock on IF-015, so this has been removed from this Interface on Swagger. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | There is no customblock on IF-015, so this has been removed from this Interface on Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-828 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-045 incorrect name on Custom block | For IF-045 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-045-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | For IF-045 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-045-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. This change has been made in Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-829 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | DI-838 and DI-017 - require an N - No Consent enum | DI-838-Supplier-Proposed-Consent-Granularity and DI-017 Consent Granularity requires an N - No Consent enum in the list of allowable values. DI-838 needs to be Mandatory no nulls |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Swagger updated so that DI-838-Supplier-Proposed-Consent-Granularity and DI-017 Consent Granularity includes N - No Consent in the list of allowable values. DI-838 updated to be Mandatory no nulls | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-830 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-001 Custom Block missing addtional properties false attribute | IF-001 Custom Block missing addtional properties false attribute |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | IF-001 Custom Block missing addtional properties false attribute. Swagger updated to include this. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-831 | BK | DIN-689 | 2023-11-30 | SI Design |  | Madison Layton | Central Body | DI-120 Additional Information should be mandatory nullable | DI-120 was made non nullable in IR5.1 in Swagger. This needs to be corrected so that DI-120 is used in multiple places and needs to be mandatory nullable. |  | Implemented | Design misaligned | DIP Users, DIP |  | Interim Release 5.2 |  | Make DI-120 Additional Information Mandatory nullable in Swagger to align with DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-832 | RS | DIN-840 | 2023-12-01 | Kraken | 22885 | Henri Naef | Software Provider | [MeterUpdate]) to be added to data item B039 heading for IF-006 | IF-005/IF-006 both contain data item B039, however a difference exists in the header. IF-005 contains "Optional for Event [MeterHistoryUpdate] & [MeterUpdate])" whereas the IF-006 contains only "Optional for Event [MeterHistoryUpdate]) |  | Implemented | Design misaligned |  |  | Interim Release 7 | 2024-01-19 | DES-138 and Swagger updated to include [MeterUpdate] as Optional for B039 in IF-006. | Data interface correction | Supporting Docs | Interfaces | Swagger, DES138 | Swagger, DES138
MHHS-DIN-833 | RS | DIN-841 | 2023-12-01 | UKPN | 23047 | Neal Medley | Network Operator | Routing table to include LDSO for IF-018 | Optionality matrix shows that LDSOs can additionally receive Event Codes [AddressChg], [GSPChg] and [DUOSTariffIDChg]. LDSO to be added to IF-018 secondary routing for these three event codes in DES138 |  | Implemented | Design ambiguous |  |  | Interim Release 7 | 2024-01-19 | DES-138 updated routing table for IF-018 updated to include LDSO for Event Codes [AddressChg], [GSPChg] and [DUOSTariffIDChg]. | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-834 | RG | DIN-818 | 2023-12-01 | SRO |  | Rob Golding | SRO Design | IF-014 - to align with IF-021 | Update DES138 to match swagger |  | Implemented | Design misaligned | DIP Users, DIP |  | Interim Release 5.2 |  | Update IF-014 to match IF-021 | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-835 | RG | MHHS-DIN-836, 882 | 2023-12-04 | Avanade |  | Rob Golding | SRO Design | Add additional error messages to DES138 | Avanade as part of their development work have generated some error codes that need to fed back into DES138: Error Code Error Text MSG1013 Invalid CertifcateIssuerName MSG1014 Certificate has expired MSG1039 Invalid MPAN MSG5001 Internal server error MSG5002 No data contained in request body MSG5003 Unable to determine correlationId requirement. Server configuration error or sender request error MSG5004 Internal server error.Payload not processed |  | Implemented | Design gap | DIP Users, DIP |  | Interim Release 7 |  | Add error codes into the DES-138 Interface Catalogue (00-Introduction Tab) Error Code Error Text MSG1013 Invalid CertifcateIssuerName MSG1014 Certificate has expired MSG1039 Invalid MPAN MSG5001 Internal server error MSG5002 No data contained in request body MSG5003 Unable to determine correlationId requirement. Server configuration error or sender request error MSG5004 Internal server error.Payload not processed | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-836 | RG | MHHS-DIN-835, 882 | 2023-12-04 | SRO |  | Rob Golding | SRO Design | New swagger file ErrorCodes to describe MHHS error messages | New swagger file (Response Codes schema) to capture all message and error codes from DES138. |  | Implemented | Design gap | DIP Users, DIP |  | Interim Release 7 |  | New swagger file (Response Codes schema) to capture all message and error codes from DES138. | Data interface correction | Supporting Docs | Interfaces | Swagger E2E001 Architecture Document | Swagger E2E001
MHHS-DIN-837 | SB |  | 2023-12-05 | ESG | 21835 | Patricia Parker | Software Provider | Migration D0086 Clarification | Page 51 of the migration design document shows the following for the D0086. Data Item ‘Meter Reading Reason Code’ (J0332) related enumeration will include 3 additional values:- a. Enumeration Value: 28; Enumeration Description: Forward Migration CoA b. Enumeration Value: 29; Enumeration Description: Forward Migration CoS c. Enumeration Value: 30; Enumeration Description: Reverse Migration My understanding was that the values should reflect those in the D0010 for the migration so parties where aware of the migration process:- Data Item ‘Reading Type’ (J0171) related enumeration will include 3 additional values: a. Enumeration Value: U; Enumeration Description: Forward Migration CoA b. Enumeration Value: V; Enumeration Description: Forward Migration CoS c. Enumeration Value: Y; Enumeration Description: Reverse Migration |  | Implemented | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | Changes made to the Migration Design Document in section 13.1.4 (D0086) under point 2 (this now aligns with DES196) as follows; Data Item ‘Reading Type’ (J0171) related enumeration will include 3 additional values: Enumeration Value: U; Enumeration Description: Forward Migration CoA Enumeration Value: V; Enumeration Description: Forward Migration CoS Enumeration Value: Y; Enumeration Description: Reverse Migration | Data interface correction | Supporting Docs | Interfaces | Migration Design Document | Migration Design Document
MHHS-DIN-838 | SB |  | 2023-12-05 | British Gas | 23696 | Neil Strange | Supplier | BPD004 v5 - step 270 typo | Can you confirm that the reference to SDS method statement in step 270 of the data collection process description is a typo and should be ADS? This is in BPD004 v5. Looks like a simple cut and paste mistake |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | BPD004 - step 270 update typo from "SDS" to "ADS" | Process Model correction | Supporting Docs | Process Model description document | BPD004
MHHS-DIN-839 | MF |  | 2023-12-05 | ESG |  | Mike Fensome | Software Provider | Confirmation of DT016 data type | Update all references of DT016 to show as string 14 to align with swagger |  | Implemented | Design misaligned |  |  | Interim Release 7 | 2024-01-19 | DT016 updated in DES138 to show as String 14 as per swagger for the following data item references: DI-043 Load Shape 7 Day Rolling Total DI-102 Load Shape Period Value DI-104 Configurable Register Reading | Data interface correction | Supporting Docs | Interfaces | DES138 | Swagger
MHHS-DIN-840 | RS | DIN-832 | 2023-12-01 | Kraken | 22885 | Henri Naef | Software Provider | [MeterUpdate]) to be added to data item B039 heading for IF-006 | IF-005/IF-006 both contain data item B039, however a difference exists in the header. IF-005 contains "Optional for Event [MeterHistoryUpdate] & [MeterUpdate])" whereas the IF-006 contains only "Optional for Event [MeterHistoryUpdate]) |  | Implemented | Design misaligned |  |  | Interim Release 5.2 |  | DES-138 and Swagger updated to include [MeterUpdate] as Optional for B039 in IF-006. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger | DES138 Swagger
MHHS-DIN-841 | RS | DIN-833 | 2023-12-01 | UKPN | 23047 | Neal Medley | Network Operator | Routing table to include LDSO for IF-018 | Optionality matrix shows that LDSOs can additionally receive Event Codes [AddressChg], [GSPChg] and [DUOSTariffIDChg]. LDSO to be added to IF-018 secondary routing for these three event codes in DES138 |  | Implemented | Design ambiguous |  |  | Interim Release 5.2 |  | DES-138 updated routing table for IF-018 updated to include LDSO for Event Codes [AddressChg], [GSPChg] and [DUOSTariffIDChg]. | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-842 | MH |  | 2023-12-06 | St Clements | 22462 | Tom Perryman | Software Provider | REP901, Common Block and Compression | Other REPs have the DIP Distribution Pattern and Report Format defined. This is not the case for the REP900 and REP901 Other REPs have the Routing Rules defined. This is not the case for the REP900 and REP901 |  | Implemented | Design gap |  |  | Interim Release 7 | 2024-01-19 | For REP-900 and REP-901 Add Distribution Pattern: A Add report format: JSON Add routing rules. Updated schema for Swagger to include compressed schema information as per other ECS reports. | Data interface correction | Supporting Docs | Interfaces | ESC Report, Swagger | ESC Report, Swagger
MHHS-DIN-843 | RG | DIN-835,836, 882 | 2023-12-07 | SRO |  | Rob Golding | SRO | Add RCP0000 to DES138 and Swagger as a valid a response code | A 'success'response code is required for MPs to provide a valid L3 response. |  | Implemented | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | RCP0000 added to DES138 and Swagger as a valid a response code. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger | DES138 Swagger E2E001
MHHS-DIN-844 | BK |  | 2023-12-07 | Large Suppliers |  | Graham Wood, Haz Elmamoun | Supplier | Standardisation of Interfaces within the Smart Data Services | This CR seeks to avoid cost and inconsistency in the design by adding OPTIONAL standardised messages to support the Meter Data Retriever SDS sub-role. Parties would be able to choose to implement this or come to bilateral arrangements as currently designed. Standardisation can be achieved by adding additional routing to current DIP messages and creating variants of existing messages. | CR023 | Implemented | Change Request |  |  | Interim Release 7 |  | Updated Business Requirements for parties (SDS/MDR) wishing to take advantage of the standard messages (BRS017) Updated Business Process Diagram (BP017) Updated Message Structures in DES-138 for IF-061, 062, 063, 064, 065. Updated Swagger to align with DES-138 and add new Interfaces. Updated E2E Solution Architect Document | Data interface correction | Supporting Docs | Interfaces | MHHSP-BP017- Optional SDS MDR Standard Interactions BRS017 DES138 Swagger E2E001 Architecture Document | MHHSP-BP007- Optional SDS MDR Standard Interactions BRS017 DES138 Swagger E2E SA
MHHS-DIN-845 | MH |  | 2023-12-12 | St Clements | 24142 | Tom Perryman | Software Provider | REP900 “List of MPANs” field should be mandatory | The REP900 “List of MPANs” field. It is currently optional in the REP900, and should be mandatory. We also believe that Zero should be added as a chargeType. |  | Implemented | Design gap |  |  | Interim Release 7 | 2024-01-19 | REP900 Changes DI-566 ‘List of MPANs on Site’ to be made a mandatory field to enable receivers of the REP900 to correctly identify the MPANs associated to a site. The population of this field is essential to allow the supplier to know what MPANs the DUoS invoice relates to, enabling them to validate the invoice Update to the possible values for DI-596 ‘Charge Type’ to include ZERO, and format all possible values to CAPS. Additional chargeType values have been added to DI-596 in both DES-138 and Swagger. | Data interface correction | Supporting Docs | Interfaces | ECS Report | ECS Report
MHHS-DIN-847 | MF |  | 2023-12-14 |  |  | Madison Layton | Software Provider | Add error code for IF-025 to validate if Null is provided and value is already Null | MPRS needs a level 5 validation rule to enable MPRS to reject the PUB-025 in the following cases: IHD null when there is no active IHD install status held to end date SMSO null when there is no active SMSO held to end date PC null and PC EFD not null, when there is no active PC held to end date SSC null and SSC EFD not null, where there is no active SSC held to end date |  | Implemented | Design gap | SCS |  | Interim Release 7 | 2024-01-19 | Added REG0009 - Null Value cannot be set as Value held is already Null. Added validation rules to enable MPRS to reject the PUB-025 using REG0009 in the following cases: IHD null when there is no active IHD install status held to end date SMSO null when there is no active SMSO held to end date PC null and PC EFD not null, when there is no active PC held to end date SSC null and SSC EFD not null, where there is no active SSC held to end date | Data interface correction | Supporting Docs | Interfaces | DES-138 | DES-138
MHHS-DIN-848 | MF |  | 2023-12-14 |  |  | Madison Layton | Software Provider | Clarification on SP de-appointment effective from date in the case of Atomic Secured Active | In rare scenario's Atomic Secured Active messages could result in an Effective To-date which is before the Effective From Date of the Service Provider Appointment 1. Supplier A active at MPAN 2. CSP received for DS with EFD 8th December 3. CSP gets confirmed 4. MPRS receives an Atomic Secured Active for Supplier B (Atomic means there was no Pending notification) on 13th December with SSD 8th December (or earlier) 5. MPRS must de-appoint the DS with ETD = SSD – 1, in this scenario ETD = 7th December |  | Implemented | Clarification - No change required | SCS, Service Providers, Suppliers |  | Interim Release 7 | 2024-01-19 | Added clarification to IF-037 notes that In rare scenario's Atomic Secured Active messages could result in an Effective To-date which is equal to the Effective From Date of the Service Provider Appointment. And as such the appointment will be deemed as having never taken effect | Data interface correction | Supporting Docs | Interfaces | DES-138 | DES-138
MHHS-DIN-846 | SW |  | 2023-12-13 |  | 24874 | Chris Mingay | Software Provider | B050 consumptionComponentClassID property inconsistency between ECS reports catalogue and Swagger | B050 consumptionComponentClassID property inconsistency between ECS reports catalogue and Swagger. In the ECS reports catalogue, in IR2 and IR5 this is an INT3, min 100 and max 999. This was correct in Swagger 1.2, but in Swagger 1.5, this has reverted to a String3 with min / max values of 3, so does not align to ECS reports catalogue. |  | Implemented | Design misaligned |  |  | Interim Release 7 | 2024-01-19 | Update Swagger to align with ECS reports catalogue for B050 consumptionComponentClassID to be an Integer. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-849 | MF |  | 2023-12-14 |  |  | Madison Layton | Software Provider | Change B099 to be a single block rather than a list in IF-035 | In IF035 SDS-MDROutcome variant, make B099 a single block in the swagger rather than a list. |  | Implemented | Error/Correction | SCS, Service Providers, Suppliers, DIP |  | Interim Release 7 | 2024-01-19 | Swagger updated so that for IF035 SDS-MDROutcome variant, B099 is a single block in the swagger rather than a list. | Data interface correction | Supporting Docs | Interfaces | Swagger DES-138 | Swagger DES-138
MHHS-DIN-850 | MH |  | 2023-12-14 |  |  | Matt Hall | SI Design | CR36 - Clock Time Reads and Appointments | Implementation of the Design Changes required to support CR36 | CR036 | Implemented | Change Request | All Participants |  | Interim Release 7 |  | Update the artefacts as per CR36 | Data interface correction | Supporting Docs | Various documents | BP003, BP003C, DES138, BRS001, BRS003, METH005, METH007 | CR036 Artefacts
MHHS-DIN-851 | MH |  | 2023-12-14 |  | 25624/33640 | Sarah Jones | Central Body | Outstanding Queries to Support Interface Code Drafting | Update the data catalogue in DES-138 to show the correct data types and data type descriptions |  | Open - awaiting assessment | Clarification - No change required | All Participants |  | Post Go-live Release |  | Clean up data catalogue in DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-852 | MH |  | 2023-12-14 |  | 21890 | Mike Ceney | Central Body | ECS Report 006 | Within block R003- CCC Determined Data, the Domestic Premise Indicator (DI-030) is to be populated, I believe this to be incorrect and needs to be removed from the report. This data item is populated at an Mpan level but this report is at BMU level so therefore cannot be populated |  | Implemented | Error/Correction | Helix, Suppliers |  | Interim Release 7 | 2024-01-19 | Remove Domestic Premise Indicator from REP 006 | Data interface correction | Supporting Docs | Interfaces | MHHSP - ERI011B - ECS Reports - External | MHHSP - ERI011B - ECS Reports - External
MHHS-DIN-853 | SB |  | 2023-12-14 |  |  |  | SRO Design Team | Addition of new RetroSpective Date Validation Rules following DRG Review & Sign Off | Amended IF-025 Validation rules for SSC& Profile Class Eff From Date to include Migration Date per reviewed & agreed RetroDates PPT. No changes rquired to any other data items as a result of RetroDates Functionality. |  | Implemented | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | Amended IF-025 Validation rules for SSC& Profile Class Eff From Date to include Migration Date in DES138. | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-854 | SW |  | 2023-12-15 | IMServ | 24832 | Liam Lowey | Software Provider | DI-085 GUID definition | DI-085 GUID definition does not align with Industry definition of a GUID ie, 8 HEX, 4x3 HEX, then 12 HEX, but rather, this refers to an SME GUID that is not a true GUID but rather a EUI base 64 address, akin to an IP v6 address. Need to update the example so that DI-085 provides clarity on whether HEX values are included. |  | Implemented | Design ambiguous |  |  | Interim Release 7 |  | Update example in the DI-085 property to align with a EUI base 64 address, akin to an IP v6 address. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger | DES138 Swagger
MHHS-DIN-855 | SW |  | 2023-12-15 | Callisto | 24828 | Neil Edney | Software Provider | Swagger required properties are not aligned with Swagger property names | There are a number of blocks where the Swagger required properties are not aligned with Swagger property names which will cause a schema validation error incorrectly. B051 - GPSGroupID and domesticPremiseIndicator - properties and required properties do not align. B014 - incomingMeteringServiceEffectiveDate and incomingMeteringServiceDIPEffectiveFromDate - properties and required properties do not align. B021 - customerDirectContractDataServiceEffectiveDIPID and customerDirectContractDataServiceDIPID - properties and required properties do not align. |  | Closed | Design misaligned | [9 empty] | Swagger
MHHS-DIN-856 | PP | ADO Defect 19010 | 2023-12-15 | Programme |  | Paul Pettitt | SI Design | DI-020 example incorrect Length | DI-020 Contract Reference data service has a Max length of 10 chars, the example is 11 |  | Closed | Error/Correction | DIP Users |  |  |  | Corrected in IR5.3 Maximum set to 50 and example is correct.
MHHS-DIN-857 | RG |  | 2023-12-18 | SRO |  | Rob Golding | SRO Design | Ensure all enumerated types have obfuscated values (where needed) (IR 5.3 Release) | Ensure all enumerated type that are obfuscated contain the obfuscated value in the enumerated list. This change affects the following: IF-035 DI-979 Response Code DI-800 Service Provider Appointment Scenario DI-838 Supplier Proposed Consent Granularity DI-126 Traditional Fall Back Read Frequency IF-036 DI-017 Consent Granularity Obfuscated DIP IDs wil be 9999999999 as the regex dictates it needs to be a 10 character numeric string |  | Implemented | Design gap |  |  | Interim Release 5.3 |  | Updated all enumerated type that are obfuscated contain the obfuscated value in the enumerated list. This change affects the following: IF-035 DI-979 Response Code DI-800 Service Provider Appointment Scenario DI-838 Supplier Proposed Consent Granularity DI-126 Traditional Fall Back Read Frequency IF-036 DI-017 Consent Granularity | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-858 | RG |  | 2023-12-18 | SRO |  | Rob Golding | SRO Design | Ensure all enumerated types have obfuscated values (where needed) (IR 7 Release) | Ensure all enumerated type that are obfuscated contain the obfuscated value in the enumerated list. This change affects the the following: IF-035 DI-979 Response Code DI-800 Service Provider Appointment Scenario DI-838 Supplier Proposed Consent Granularity DI-126 Traditional Fall Back Read Frequency IF-036 DI-017 Consent Granularity Obfuscated DIP IDs wil be 9999999999 as the regex dictates it needs to be a 10 character numeric string |  | Implemented | Design gap |  |  | Interim Release 7 | 2024-01-19 | Ensure all enumerated type that are obfuscated contain the obfuscated value in the enumerated list. This change affects the the following: IF-035 DI-979 Response Code DI-800 Service Provider Appointment Scenario DI-838 Supplier Proposed Consent Granularity DI-126 Traditional Fall Back Read Frequency IF-036 DI-017 Consent Granularity Obfuscated DIP IDs wil be 9999999999 as the regex dictates it needs to be a 10 character numeric string | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-859 | MH |  | 2023-12-20 | St Clements | 24142 | Tom Perryman | Software Provider | REP900 invoice | Currently, the REP900 has one or many invoices for each site / invoice data (R900-05 level). This needs to be updated so that the REP900 contains one or many combinations of site and invoice data (R900-04 level). Currently a single D2021 is sent to a supplier containing all their HH invoices produced on that billing day. |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | Correct the REP900 record hierarchy to: Clarification of the record hierarchy to enable the inclusion of multiple invoices on a single REP900 R900-01 Distributor Info - a single Distributor on a REP900 R900-02 Supplier Info - a single Supplier on a REP900 > R900-03 Site Info > R900-04 Invoice Data - one or many combinations of Site and Invoice Data >> R900-05 Invoice Lines - one or many invoice lines for each combination of Site and Invoice Data | Data interface correction | Supporting Docs | Interfaces | Swagger MHHSP - ERI011B - ECS Reports - External | Swagger
MHHS-DIN-860 | RG |  | 2023-12-21 | SRO |  | Rob Golding | SRO Design | Clarification on Webhook callback responses | At present the webhook callbacks are limited in their responses to 200 & 207. The extent of the responses needs to align with the other DIP APIs |  | Implemented | Design gap |  |  | Interim Release 5.3 |  | Aligning participant systems with the DIP in terms of HTTP responses, added in a standard set of response codes to be used in the Swagger. Also described are how HTTP responses received from the DIP should be interpreted, and what HTTP responses the DIP is expecting back from participants webhooks in the E2E Architecture document. | Data interface correction | Supporting Docs | Various documents | Swagger E2E Architecture | Swagger E2E Architecture
MHHS-DIN-861 | RG |  | 2023-12-21 | SRO |  | Rob Golding | SRO Design | Clarification on Webhook callback responses | At present the webhook callbacks are limited in their responses to 200 & 207. The extent of the responses needs to align with the other DIP APIs |  | Implemented | Design gap |  |  | Interim Release 7 |  | Aligning participant systems with the DIP in terms of HTTP responses, added in a standard set of response codes to be used in the Swagger. Also described are how HTTP responses received from the DIP should be interpreted, and what HTTP responses the DIP is expecting back from participants webhooks in the E2E Architecture document. | Data interface correction | Supporting Docs | Various documents | Swagger E2E001 Architecture Document | Swagger, E2E Architecure
MHHS-DIN-862 | RG |  | 2024-01-02 | SRO |  | Rob Golding | SRO Design | REP901 missing event code | The eventcode on REP-901 need correcting to [DUoSEmbeddedLDSOAggInvData] & [DUoSSupplierAggInvData] (or do we have two reports?) |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | Update the following REP-901 data items as follows [DUoSEmbeddedLDSOAggInvData] & [DUoSSupplierAggInvData] to ensure that ECS reports align with naming standards and ensure that Swagger aligns with ECS reports catalogue. | Data interface correction | Supporting Docs | Interfaces | ESC Report, Swagger | ESC Report, Swagger
MHHS-DIN-863 | SB |  | 2024-01-03 | Kraken | 27359 | Henri Naef | Software Provider | IF-019/020 Discrepancy between E2E and Swagger | It looks like in the e2e guide there’s no mention of an M1 block in the common block. However in the swagger documentation for IF019 and IF020 there is. What’s weirder is that for both of those there is no M0 block which the e2e guide says there should be." |  | Open - awaiting assessment |  |  |  | Post Go-live Release |  | Solution under review/discussion | Data interface correction | Supporting Docs | Interfaces | E2E001 Architecture Document
MHHS-DIN-864 | ZH |  | 2024-01-08 | SJW |  | Sarah Jones | Central Body | CR024 - Update of two data items | As flagged at the last DAG and in our email on 21 Dec, RECCo believes there are two incorrect data items in the MHHS design: Manufacturer Code should be Manufacturers Make and Type CSS Registration Request Id should be CSS Registration Id. We believe failure to correct these data item in line with approved CR024 (particularly the CSS Registration Id) may lead to parties including the wrong data items within their design, impacting testing outcomes (both SIT and Qualification) and leading to operational issues post go live. | CR024 | Implemented | Error/Correction |  |  | Interim Release 7 |  | Update the names of both data items in the Swagger and DES138, in the relevant areas. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger | DES138 Swagger
MHHS-DIN-865 | RG |  | 2024-01-12 |  |  |  |  | EMSE ID example has non-hexadecimal chars | DES-138 and the swagger have a non-hex character in the example |  | Closed | [5 empty] | Update example to remove leading S character |  |  |  |  | Swagger, DES138
MHHS-DIN-866 | SW | DIN-880 | 2024-01-16 | Stark | 29309 | Jon Dennis | Software Provider | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD |  | Implemented | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD. Swagger updated to align. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-867 | RG |  | 2024-01-16 | PDA |  | Richard French |  | Remove all references to UDS & UMDS in E2E SA doc | Replace UMDS with UMSDS - multiple instances still exist |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | E2E documentation still contains references to UMDS - this needs to be removed and replaced with UMSDS | Data interface correction | Supporting Docs | Interfaces | E2E001 Architecture Document | E2E001
MHHS-DIN-868 | RS |  | 2024-01-16 |  | 19802 | Rob Short | SI Design | Correction of Advanced Data Service Validation and Estimation (Meth002) | Following review and participant comments, multiple updates are required to correct SDS references in the ADS method statement |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | Updates made to all sections of MHHSP-METH002_ADS_Validation_Estimation | Method statement correction | Supporting Docs | Method Statement | METH002 | METH002
MHHS-DIN-869 | RS |  | 2024-01-16 |  | 19802/20645 | Rob Short | SI Design | ADS Method Alignment | Updates to the ADS estimation methods |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | Update to section 3 of of MHHSP-METH002_ADS_Validation_Estimation | Method statement correction | Supporting Docs | Method Statement | METH002 | METH002
MHHS-DIN-870 | SW |  | 2024-01-17 | St Clements | 26647 | Madison Layton | SI Design | IMS-SendMTD variant for IF-035 does not contain properties B070, B071 and B019 to align with DES-138 | IMS-SendMTD variant for IF-035 does not contain properties B070, B071 and B019 to align with DES-138 - which identifies this variant of a copy of the variants DSAppAccepted and MSAppAccepted |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | Swagger 1.7 IF-035-IMS-SendMTD: should be updated to include B070, B071 and B019 as optional fields in this variant. | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-871 | RG |  | 2024-01-17 | SRO |  | Rob Golding | SRO Design | Changes to E2E SA doc & Swagger for replay message version support | The E2E SA doc (& swagger) needs to be updated to include message version support for replay |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | E2E SA document include a description on message versioning for message replay. This includes changes to section 4.9 and 8.5.2 of the E2E001 design document, removal of section 5.5 (it has been combined into section 4.9). Also updates to Swagger to add version in the MessageRequest object. | Technical corrrection | Supporting Docs | Interfaces | E2E001 Architecture Document Swagger | E2E
MHHS-DIN-872 | RS |  | 2024-01-18 | IMServ | 30201 | Rob Short | SI Design | Historic consumption data following the IF-015 request | Conflicting information in the NOTES section: “The structure and content of this message will be subject to further discussion as part of the 'DIP Detailed Design', as the exact way in which this requirement/functionality is realised may depend on the DIP Solution option(s) chosen. The basis of the functionality is that participants will be 'REPLAYED' facsimiles of the previously submitted IF-021 (SP Consumption Submission) / IF-013 (SP Defaulted) Records - however it may be possible that some kind of 'blended' response, as eluded to here, is also possible.” |  | Implemented | Design gap |  |  | Interim Release 7 |  | Removal of Interface note on IF-16 | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-873 | RS |  | 2024-01-19 | Elexon | 21459 | Phil Milmine | Central Body | Correction to VAS Method Statement | Amendment to section 3.28 around “VAS Defaulting” and the report linked to this process (REP-007) to reflect the manual steps that Elexon would need to take to enable this. |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | Amend text to 17. VAS Re-run where Initial VAR incomplete due to missing MDS or CDCA data 3.28 In the event that the VAS is unable to complete an Initial VAR due to missing data from MDS or CDCA, the VAS shall use replacement data at BSCCo’s discretion to re-run by BM Unit, as per a normal VAS run. Substituted data must be reported to Market Participants. | Method statement correction | Supporting Docs | Method Statement | METH006 | METH006
MHHS-DIN-874 | RG | DIN-829 | 2024-01-23 |  |  | Rob Golding | SRO Design | Consent Granularity not nullable and N - no consent | Implement DIN-829 in 5.x swagger and update DES138 accordingly |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Swagger/ DES138 updated so that DI-838-Supplier-Proposed-Consent-Granularity and DI-017 Consent Granularity includes N - No Consent in the list of allowable values. DI-838 updated to be Mandatory no nulls. DI-838 description updated to align with the data item name in Swagger. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger | DES138 Swagger
MHHS-DIN-875 | SW |  | 2024-01-23 | Kraken | 31011 | Angelos Rizoyannis | SI Design | Swagger objects and descriptions are missing | Missing `type: object` - for the following blocks B079, B080, B081, B082, B083, B090, B091 - Missing `description: ...’ object for R901-08 - Incorrect description - IF-004-Payload08, IF-006-MeterRemoval.CustomBlock, IF-006-MeterExchange.CustomBlock |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Missing `type: object` - for the following blocks - B075, B076, B079, B080, B081, B082, B090, B091 - Missing `description: ...’ object for R901-08 - Incorrect description - IF-004-Payload08, IF-006-MeterRemoval.CustomBlock08, IF-006-MeterExchange.CustomBlock08 Update Swagger to fix above issues. | Technical corrrection | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-876 | RG |  | 2024-01-24 | SRO |  | Rob Golding | SRO Design | IF-003 LDSO routing is secondary not always | DES138 has IF-003 LDSO routing incorrectly specified, the routing is secondary not always |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | Update DES138, IF-003 LDSO routing is secondary not always | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-877 | RG | DIN-620 | 2024-01-24 |  |  | Rob Golding | SRO Design | IF-001 Remove EES (CR023) | DIN-620 was not fully implemented, EES is still mentioned in DES138 IF-001 |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | EES removed DES138 IF-001 | Data interface correction | Supporting Docs | Interfaces | DES138 | DES138
MHHS-DIN-878 | RG | DIN-870 | 2024-01-17 | St Clements | 26647 | Madison Layton | SI Design | IMS-SendMTD variant for IF-035 does not contain properties B070, B071 and B019 to align with DES-138 | IMS-SendMTD variant for IF-035 does not contain properties B070, B071 and B019 to align with DES-138 - which identifies this variant of a copy of the variants DSAppAccepted and MSAppAccepted |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Updated Swagger IF-035-IMS-SendMTD: to include B070, B071 and B019 as optional fields in this variant | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-879 | RG | DIN-849 | 2023-12-14 |  |  | Madison Layton | Software Provider | Change B099 to be a single block rather than a list in IF-035 | In IF035 SDS-MDROutcome variant, make B099 a single block in the swagger rather than a list. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Updated Swagger IF035 SDS-MDROutcome variant, and made B099 a single block rather than a list. This has also necessitated in an update to DES138 to the routing information for IF-035. | Data interface correction | Supporting Docs | Interfaces | Swagger, DES138 | Swagger
MHHS-DIN-880 | MF | DIN-866 | 2024-01-24 |  |  | Jon Dennis | Software Provider | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Updated “MAIN” in DI-059-Meter-Type enum in swagger, to be "MAIN_" to align with ISD | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-881 | MF | DIN-825, DIN-811 | 2024-01-24 | Avanade |  | Rob Golding | SRO Design | IF-024 missing required attributes in blocks | IF024 SN-NoComms CustomBlock required B057 IF-024-SN-RemoteDisabled required B069, B057 |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Update swagger with the following: IF024 SN-Vacant CustomBlock required B057 IF024 SN-NoComms CustomBlock required B057 IF024 SNRemoteEnabled CustomBlock required B057, B069 IF024 SNSupplierAC CustomBlock required B057, B058 | Data interface correction | Supporting Docs | Interfaces | Swagger | Swagger
MHHS-DIN-882 | MF | DIN-835,836, 843 | 2024-01-24 | SRO |  | Rob Golding | SRO Design | New swagger file ErrorCodes to describe MHHS error messages and updates to error messages in DES138 | New swagger file (Response Codes schema) to capture all message and error codes from DES138 including RCP0000 (Message Success) and the following error codes: Error Code Error Text MSG1013 Invalid CertifcateIssuerName MSG1014 Certificate has expired MSG1039 Invalid MPAN MSG5001 Internal server error MSG5002 No data contained in request body MSG5003 Unable to determine correlationId requirement. Server configuration error or sender request error MSG5004 Internal server error.Payload not processed |  | Implemented | Design gap | DIP Users |  | Interim Release 5.4 |  | New swagger file (Response Codes schema) to capture all message and error codes from DES138 DES138 updated with RCP0000 (Message Success) and the following error codes: Error Code Error Text MSG1013 Invalid CertifcateIssuerName MSG1014 Certificate has expired MSG1039 Invalid MPAN MSG5001 Internal server error MSG5002 No data contained in request body MSG5003 Unable to determine correlationId requirement. Server configuration error or sender request error MSG5004 Internal server error.Payload not processed | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger | Swagger
MHHS-DIN-883 | RG |  | 2024-01-24 | SRO | 31749 | Matt McKeon | SRO Design | Data item clashes between DES138 and ECS Reports | We have noticed that there are some DI-REF numbers which have been used twice in DES138 and ERI011B. - Specifically the newer data items introduced for migration start in the 500s, when these are also used in ECS Reports. |  | Implemented | Error/Correction | ECS |  | Interim Release 7 |  | Move duplicated ECS numbers to an unused range | Reporting correction | Supporting Docs | ECS Reports | ERI011B | ERI011B
MHHS-DIN-884 | BK |  | 2024-01-26 | SRO |  | Kevin Spencer | SRO Design | CR032: Replacement of REP080 to use the P210 | The revised design would require: Elexon revise the build of the P0210 to include both non-migrated and migrated consumption. The format and structure will not change. The ESO ingest the P0210, ensuring that its integration and middleware systems can process the file. As per the the integration and middleware diagram, two systems (LIMS and CIS/MFT) will need configuration changes. The ESO regression test its Revenue systems based on the revised P0210 to ensure it continues to meet the requirements for TNUoS and BSUoS reporting. After the end of the Transition Period, if the ELEX-REP-080 report was developed, the existing P0210 file and associated processing of that file would become redundant. | CR032 | Implemented | Change Request |  |  | Interim Release 7 |  | Updates made to the following artefacts; Amended METH006 section 3.7 Removal of REP080 in the ECS Report Update wording in BP020 step 75 to reference the P0210 and subsequent BPD doc | Data interface correction | Supporting Docs | Interfaces | METH006 ESC Report BP020 and BPD020 | METH006 ESC Report BP020 and BPD020
MHHS-DIN-885 | BK |  | 2024-01-26 | SRO |  | Matt McKeon | SRO Design | Add URLs pointing to new DTC format definition documents in ERI011B | Update four tabs of ERI011B to add a URL pointing to new DTC format definition documents for these reports |  | Implemented |  |  |  | Interim Release 7 |  | Update MHHS-REP-D0369 to say ‘Defined in DTC format as D0401 at: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx · Update MHHS-REP-D0370 to say ‘Defined in DTC format as D0402 at: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx · Update MHHS-REP-D0373 to say ‘Defined in DTC format as D0403 at: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx · Update MHHS-REP-D0374 to say ‘Defined in DTC format as D0404 at: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx Grey out all the reports specified above | Reporting correction | Supporting Docs | Interfaces | ERI011B | ERI011B
MHHS-DIN-886 | MF |  | 2024-01-26 | St Clements |  | SCS | Software Provider | Addition of 905 existing meter listing block to all events in IF-006 | Add B905 (existing meter listing) block for all IF-006 event codes in Swagger |  | Implemented |  |  |  | Interim Release 7 |  | Add B905 (existing meter listing) block for all IF-006 event codes in Swagger | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-887 | MF |  | 2024-01-26 | St Clements |  | SCS | Software Provider | Addition of 905 existing meter listing block to all events in IF-006 | Add B905 (existing meter listing) block for all IF-006 event codes in Swagger |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Add B905 (existing meter listing) block for all IF-006 event codes in Swagger | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-888 | SW |  | 2024-01-29 | Kraken |  | Angelos Rizoyannis | Software Provider | Property "type: object" missing from IF-024 variants in Swagger | Property "type: object" missing from IF-024 variants in Swagger. This needs to be added to all variants where this is missing. |  | Implemented |  |  |  | Interim Release 7 |  | Property "type: object" missing from IF-024 variants in Swagger. This needs to be added to all variants where this is missing. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-889 | SW |  | 2024-01-29 | Kraken |  | Angelos Rizoyannis | Software Provider | Property "type: object" missing from IF-024 variants in Swagger | Property "type: object" missing from IF-024 variants in Swagger. This needs to be added to all variants where this is missing. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Property "type: object" missing from IF-024 variants in Swagger. This needs to be added to all variants where this is missing. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-890 | RS |  | 2024-01-29 | CGI |  | Dave Webster | Software Provider | DI-038 (LInked Import/Export Mpan) description | Confusion over wording in DI-038. Where more than one import MPAN exists, this shall be populated with the Primary Import MPAN |  | Implemented |  |  |  | Interim Release 8 | 2024-03-20 | Remove wording 'Where more than one import MPAN exists, this shall be populated with the Primary Import MPAN' from all DI-038 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-891 | SB |  | 2024-01-30 | St Clements | 21513 | SCS | Software Provider | DI-241 - SUPC routing on IF-037 incorrect, should be SUPS | The primary routing for MSDeAppUpdate and DSDeAppUpdate is incorrect, XMSC and XDSC is the currently appoint SP but the flow needs to go to the already de-appointed SPs |  | Implemented |  |  |  | Interim Release 8 | 2024-03-20 | Update Primary Routing to show Previously de-appointed Data Service/ Metering Service | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-892 | RG |  | 2024-01-31 | RDG |  | RDG | SRO | Message Versioning Support: Create DIPMessage variant for egress | Split DipMessage in two, one for ingress (current version) and another for egress (new) in order to support multiversion messages on egress for replay/requeue |  | Implemented |  |  |  | Interim Release 8 | 2024-03-20 | Add new DIPEgressMessage to the swagger in order to split the incoming and outgoing APIs to allow multiversion support | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-893 | RG |  | 2024-01-31 | BJSS |  | Soniya | Software Provider | Regex for GSP Correction factor | We want to check if the regex is correct for GSP Group Correction Factors: ^-?\d{1,9}\.\d{9} The highlighted section suggests the – is optional but GCFs are always positive. Can the regex be updated to reflect this? |  | Implemented |  |  |  | Interim Release 7.1 |  | Regex update in Swagger to enforce only positive numbers. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-894 | RG |  | 2024-01-31 | SIMs & Ems |  | John | Software Provider | DI-123-SSC is nullable in IR7, needs to be the same in IR5.x | B032 eg on IF-002 has property SSC which was made non nullable in 1.5.2 or 1.5.3 has been left nullable in 1.7 |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Update B032 eg on IF-002 has property SSC so that it is non nullable | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-895 | MH |  | 2024-02-01 | St Clements | 31597 | Virginia Patey | Software Provider | REP002s vs IF-21s for DUoS Billing. Follow up from DIN340 | Change required to MDS Method Statement... DIN-340 was raised by UKPN to highlight the fact that while DNOs were to receive the correct IF-021 data, the data on the DUoS Report would also include meter data for most MPANs with a connection type <> ‘W’. Additionally, given the fact that the DNOs require meter data for all sites via either the REP002s or the IF-021s, using different data items to determine the inclusion or exclusion from a particular delivery method risks DNOs not receiving data for some MPANs via either route and thereby negatively impacting their invoicing. Please note that an MS Site Specific LLF Id indicator of ‘B’ (Site Specific Import) or ‘D’ (Site Specific Export) does NOT equate to a connection type <> ‘W’. In fact the MPANs with a MS Site Specific Indicator of ‘B’ or ‘D’ is a very small subset of those with a connection type <> ‘W’. For the avoidance of doubt, the use of the term ‘site specific’ for billing types and MS Site Specific LLF Id indicators are separate things and do not equate to one another. Required Solution: We require the rules for what should be included on the DUoS Report (i.e. the wording for 17.3) to be changed to: The DUoS Report calculations shall only be undertaken for SPC data that is for MPANs with a connection type = ‘W’ 17.4 is not required as DNOs should be using all IF-021 in site specific billing. |  | Implemented | Error/Correction | ECS, DNOs |  | Interim Release 8 | 2024-03-20 | Rules for what should be included on the DUoS Report (i.e. the wording for 17.3) to be changed to: The DUoS Report calculations shall only be undertaken for SPC data that is for MPANs with a connection type = ‘W’ 17.4 is not required as DNOs should be using all IF-021 in site specific billing. | Method statement correction | Supporting Docs | Method Statement | METH007 ERI011B - ECS Reports
MHHS-DIN-896 | MH |  | 2024-02-06 | ESG | 32706 | Patricia Parker | Software Provider | ISD v5.5 (Ref 265) | The two new entities M20 & M21 (DIN-754) do not appear in the table of contents. Can these be added? |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Update the table of contents to include two new entities M20 & M21 (from DIN-754). | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-897 | RG |  | 2024-02-06 | Flui | 32997 | Jason Jackson | Software Provider | IF-001 Change Of Supplier s0 block needs to mandatory | s0 block needs to mandatory, DIN-785 missed off the S0 block, ok in 5.4 not 7. the A0 block is marked as mandatory, it should be S0. (the orignial published DIN stated this was the S1 block, this is an error, in fact it should be the s0 block) |  | Implemented | Error/Correction |  |  | Interim Release 7.1 |  | Minor swagger update to enforce a manadatory field | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-898 | MH |  | 2024-02-07 | Elexon | 31846 | Derek Weaving | Central Body | REP-003 fields - Clarification Request | DI-339 BM Unit Allocated Demand Disconnection Volume Losses should not be in the REP003 The DDE does not calculate losses separately and they are already included in DI-341 volume that sums across all CCCids including the ones for losses. |  | Implemented | Error/Correction | Suppliers |  | Interim Release 7.1 |  | Remove DI-339 and the DI-370 from the REP-003 Swagger update and ECS Report | Technical corrrection | Supporting Docs | Interfaces | Swagger ERI011B - ECS Reports
MHHS-DIN-899 | MH |  | 2024-02-07 | Elexon | 32697 | Rashmi Radhakrishnan | Central Body | IR7 Changes to ISD | In IR7, DIN-759 included an update to ISD Entitiy M17. tHis update was only partially completed. This DIN is to correct it and to add Meter Group to the Entity and also to add N to M15 as previously agreed |  | Implemented | Error/Correction |  |  | Interim Release 7.1 |  | Add Meter Group to the Entity - M17 Add N - No Consent to M15 | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-900 | RG |  | 2024-02-07 | SRO Design |  | RG | SRO Design | IR7 E2E SA Obfuscation rules require updating | Data items that are MPIDs need to be obfuscated to 'XXXX' rather than 'xxxx' so the regex remains unbroken |  | Implemented | Error/Correction |  |  | Interim Release 7.1 |  | MPIDs that are obfuscated will be 'XXXX'. Avanade change, PPs need to be aware. | Technical corrrection | Supporting Docs | Interfaces | E2E Architecture
MHHS-DIN-901 | RG |  | 2024-02-08 | SRO Design |  | RG | SRO Design | DES138 does not include CR23 opting in for MDRs | The IR7 version of DES138 does not include the 'opting' information for MDRs. The following needs to be icluded as opted in PUB-006 [MeterInstall], [MeterRemove], [MeterExchange], [MeterUpdate] PUB-008 [EnergisationStatusChange] PUB-026 [ConsentGranularity], [SMSO], PUB-024 [SN-RemoteEnable], [SN-RemoteDisable], [SN-NoComms] |  | Implemented | Design gap |  |  | Interim Release 7.1 |  | Update DES138 to include the 'opting' information for MDRs in the following PUBS; PUB-006 [MeterInstall], [MeterRemove], [MeterExchange], [MeterUpdate] PUB-008 [EnergisationStatusChange] PUB-026 [ConsentGranularity], [SMSO], PUB-024 [SN-RemoteEnable], [SN-RemoteDisable], [SN-NoComms] | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-902 | MH |  | 2024-02-09 | SRO | 33170 | Andrew Margan | Central Body | Reverse Migration Consistency | Step 190 of MHHS-DEL971 - BPD001 and DEL965 BPM001 - Change Of Supply - Reverse Migration suggest the incoming supplier has a choice of whether to reverse migrate or not. This isn't the case; a reverse migration will only happen where the incoming supplier is not qualified on the MHHS TOM |  | Closed | Error/Correction |  |  |  |  | The Process step is showing the Incoming Supplier choosing whether to start reverse migration or not. In this scenario, the Incoming Supplier is not MHHS qualified. However, they will have to determine if it is a reverse migration scenario based on the info in the D0260/D0217. In that respect they must choose whether they need to follow reverse migration or legacy process
MHHS-DIN-903 | MF |  | 2024-02-12 | Elexon | 34297, 34973 | Raina Jain | Central Body | Missing/ incorrect BPD011 step | Step 211 is missing from “(BP011A) MHHSP-BPD-011” tab in MHHSP-BPD011 - Change of Con Type or Market Segment document." Correct step 275 to show that this applies for successful meter exchanges |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Add step 211 to BPD011 to align with BP011. This shows the Metering Service receiving the Appointment Response (PUB-035) from Registration Service. Update step 275 to show that this applies for successful meter exchanges | Process Model correction | Supporting Docs | Process Requirements Doc | BPD011
MHHS-DIN-904 | RG | DIN-924 | 2024-02-12 | SRO |  | Rob Golding | SRO Design | Missing parameters in webhook callback | The definition in the webhook callback in swagger is missing the definition - $ref: '#/components/parameters/CommonSignatureHeader' - $ref: '#/components/parameters/CommonSignatureDateHeader' - $ref: '#/components/parameters/CommonSHA256Header' - $ref: '#/components/parameters/CommonSignatureCertifcateHeader' |  | Implemented | Clarification - No change required |  |  | Interim Release 5.5 |  | Update to swagger to include missing parameters; aligns with CoCo | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-905 | RG | DIN-864 | 2024-02-14 | SRO |  | Rob Golding | SRO Design | B033 block meterManufacturer IR7 | B033 block meterManufacturer was renamed to manufacturersMakeAndType it wasn't renamed in the 'required' properties |  | Implemented | Error/Correction |  |  | Interim Release 7.1 |  | Update B003 requried fields to include manufacturersMakeAndType | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-906 | RG | DIN-925 | 2024-02-14 | SRO Design |  | Rob Golding | SRO Design | Add MPO Encrypted header parameter to callback | Add a parameter to the callback so that the MTLS cert can be authenticated by the MTLS connection. No impact on MPs, Avanade improving the secuirty handshake on the callback |  | Implemented | Design gap | Avanade |  | Interim Release 5.5 |  | Add MPO Encrypted header parameter to callback | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-907 | RG | DIN-926 | 2024-02-14 | SRO Design |  | Grant Sutcliffe | Avanade | Response codes on delete operations | Standardise response message for successful delete operations on API calls -204 needs to have the text 'No Content' . Need to add other response codes in-line with the other APIs |  | Implemented | Design misaligned |  |  | Interim Release 5.5 |  | Standardise response message for successful delete operations on API calls -204 needs to have the text 'No Content' . Need to add other response codes in-line with the other APIs | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-908 | MF | DI-249 | 2024-02-15 | St Clements |  | Madison Layton | Software Provider | Validation of Appointment start times | Move REG1032 from Migration Only Validation Rules to BAU Validation Rules section in IF-031 |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Move REG1032 from Migration Only Validation Rules to BAU Validation Rules section in IF-031 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-909 | RS |  | 2024-02-15 | EDW | 34934 | Darren Kay | Software Provider | Duplicate requirement reference used in MHHS-E2E002 Requirements v3.1 document | E2E1009 requirement reference is used for Level 4 Processing Times (Asynchronous) and Unplanned Outages in MHHS-E2E002 Requirements v3.1 document. Adjustment required to one of the references |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Remove duplicate reference to requirement in E2E002 doc. | Requirement correction | Supporting Docs | Requirement correction | E2E002 Requirements
MHHS-DIN-910 | MF |  | 2024-02-16 | SRO Design |  | Mike Fensome | SRO Design | Remove sending of IF-041 for invalid meter readings from SDS method statement | SDS Method Statement 2.37 refers to SDS sending an IF-041 where reads are invalid. This is not allowed for in the design and should be removed |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Remove sending of IF-041 for invalid meter readings from SDS method statement | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-911 | MF | DIN-849 | 2024-02-16 | St Clements |  | Madison Layton | Software Provider | Update B099 block to show that it is not an array | Update B099 block (IF-035) in DES138 to align with swagger to show that it is not an array |  | Implemented | Error/Correction |  |  | Interim Release 7.1 |  | Updated B099 block (IF-035) in DES138 to show that it is not an array | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-912 | RG |  | 2024-06-15 | SRO Design |  | Rob Golding | SRO Design | Incorrect 1.7 reference in 1.5.4 swagger | There was a reference to a 1.7 object from 1.5.4. module which meant the 1.5.4. swagger wasaa not resolving correctly |  | Implemented | Error/Correction |  |  | Interim Release 5.4 |  | Swagger rebuilt | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-913 | SB | DIN-503 DIN-780 | 2024-02-14 | St Clements | 19885 | Madison Layton | Software Provider | Missed Update to DES138 | There was a change in swagger in IR4 for senderUniqueReference and transactionID under DIN503. However this wasn’t folded into the Interface Catalogue examples. The examples should have been removed from The DES138 Examples as DIN-780 these still appear in the Interface catalogue |  | Implemented | Clarification - No change required |  |  | Interim Release 8 | 2024-03-20 | Examples against senderUniqueReference and transactionID will be removed from DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-914 | MF |  | 2024-02-19 | EDW |  | Darshun Chauhan | Software Provider | Update DI-082 (Settlement Period Effective to Date/Time) validation rule on IF-021 | Align DI-082 validation rule to check for periods ending on the hour or half-hour to align with MDS requirements |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Update DI-082 (Settlement Period Effective to Date/Time) validation rule on IF-021 to check for periods ending on the hour or half-hour to align with MDS requirements/ build | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-915 | RG | DIN-801, DIN-852 | 2024-02-19 | BJSS |  | Soniya Jakhu | Software Provider | Missing swagger updates to align with DIN-801 - ECS reports REP006 | 1. DIN-801 updates not communicated - Add Supplier R015 block to REP006 2. DI-375 needs to be nullable 3. DI-364 needs to be nullable 4. DIN-852 Updates not communicated to Swagger REP-006 - R003 block |  | Implemented |  |  |  | Interim Release 7.1 |  | Update Swagger to 1. Add Supplier R015 block to REP006 2. DI-375 needs to be nullable 3. DI-364 needs to be nullable 4. REP-006 - R003 block | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-916 | MH |  | 2024-02-21 | Elexon | 35702 | Mike Ceney | Central Body | IF-36 Obfuscation | In the IF-036 flow it states that DI-800 Service Provider Appointment Scenario is obfuscated for MDS, can you please clarify why this is the case. MDS needs this information to determine if this is for Migration (CoA or CoS lead), or a general CoA, it treats the interface differently based on the scenario |  | Implemented | Design gap | Avanade, Helix |  | Interim Release 7.1 |  | Removed the obfuscation of DI-800 in Blocks B014 and B015 in IF-36 | Data interface correction | Supporting Docs | Interfaces | DES138 & Avanade change
MHHS-DIN-917 | RS |  | 2024-02-22 | Callisto | 31823 36576 | Seth Chapman | Data Service Provider | Reverse Migration Process - Missing D0148 | In the reverse migration scenario there is a variation to the standard legacy process in that the D0148 groups for the old agent (271 to DC And 274 to MOP) would include the MHHS services rather than a previous "current world" agent. The documents also do not mention that the new supplier will also appoint a DA |  | Closed | Design gap |  |  |  |  | Migration Design Document (DEL961) updated to include the D0148 for the new DC, DA and MOP. Discussion required on if the old agent/service should be included as Participant believes it could be a bigger change to not include Following review, a CR would be required to make additional amendments to the existing D0148 to include old agents, response provided back to initiator | Process Model correction | Supporting Docs | Supporting document | DEL961
MHHS-DIN-918 | RG |  | 2024-02-22 | SRO Design |  | Rob Golding | SRO Design | DES-138 IF_LIST table incomplete | IF_LIST tab does not include all the MDR interfaces |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Add interfaces IF-061, IF-062, IF-063, IF-064, IF-065 to Interface List in DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-919 | RS | DIN 247, DIN 434 | 2024-02-22 | IMServ | 35161 | Bevis Rotherham | Software Provider | Reverse Migration - IF003 missing supplier fields | The MHHS-DEL961 - Migration Design Document states that IF-003 will be updated to include RevMig Incoming Supplier MPID and RevMig Incoming Supplier Effective From Date fields, however, even in the latest IR7 DES138 document these fields do not exist. There was DIN-247 which specifically referenced these fields and the Business Rules and this was closed as supposedly captured as part of DIN-434, however, DIN-434 doesn't show these fields being implemented, and the latest DES138 doesn’t show these fields against the IF-003. |  | Implemented | Error/Correction |  |  | Interim Release 7.1 |  | Added B002 block to DES138 IF-003 to provide the Incoming Supplier DIP ID, MPID and Effective From Date on a Reverse Migration de-appointment. Note, all Suppliers will need to be allocated a DIP ID in advance of migration. Required fields in swagger equire update to align with DES-138 | Data interface and Swagger correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-920 | RS |  | 2024-02-22 | SCS | 36031 | Daniel Tadecicco | Central Body | DI-250 IF-007 Migration Rejection Code | Currently, the IF-007 can only be rejected using Level 4, MPRS other IFs use a reusable function to apply Migration rules with level 5 validation. We would like to use this function for the IF-007, using the current level 4 rejection would require a specific function for the IF-007 which would not be as maintainable and possibly confusing for receiving parties. |  | Implemented | Design gap | All Participants |  | Interim Release 8.1 |  | Added new validation REG9002 to IF-007 to reject if Reverse Migration is in progress | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-921 | RG | DIN-913 | 2024-02-22 | IMServ |  | Liam Lowey | Software Provider | DES138 - Sender Unique reference example is incorrect | The example sender Unique reference on the DIP_COMMON tab does not contain the full interface id in the string |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | The senderUniqueReference example removed from DIP Common as per DIN 913 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-922 | RG |  | 2024-02-22 | BJSS |  | Sergio Gomes | Software Provider | IF-014 CustomBlock Required list needs updating | Needs to align with properties, should be B900 not B900List |  | Implemented | Error/Correction |  |  | Interim Release 7.1 |  | Required properties should be B900 not B900List only wrong in v7, not v5.4) | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-923 | MF |  | 2024-02-23 | PDA |  | Richard French | Data Service Provider | Clarification on Data Service sending consumption data for periods 47/48 during BST | Clarification around who should send consumption data for settlement periods 47 and 48 in the case of New Connections, Migration and who will receive the IF-013 where no data is provided for HH47 and HH48 during BST |  | Implemented | Design misaligned |  |  | Interim Release 7.1 |  | In the case where no previous Data Service exists following a Change of Data Service ( eg New Connection, Migration) , in BST the responsibility for providing the initial hour of consuption data for Settlement periods 47 and 48 sits with the newly Appointed Data Service. Note the IF-036 notifies whether there is a previous Data Service via Block B005. The Data Service should estimate these periods in line with the relevant Method Statement. The Incoming Data Service will be notified of default data via the IF-013 if no data is submitted for Settlement Periods 47 and 48. However, the Incoming Data Service is not expected to provide data for these two settlement periods where a previous Data Service exists. Minor amendment to IF-021 validation rule to allow the incoming Data Service to send IF-021 for periods 47 and 48 where no previous Data Service exists | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-924 | RG | DIN-904 | 2024-02-12 | SRO |  | Rob Golding | SRO Design | Missing parameters in webhook callback | The definition in the webhook callback in swagger is missing the definition - $ref: '#/components/parameters/CommonSignatureHeader' - $ref: '#/components/parameters/CommonSignatureDateHeader' - $ref: '#/components/parameters/CommonSHA256Header' - $ref: '#/components/parameters/CommonSignatureCertifcateHeader' |  | Implemented | Clarification - No change required |  |  | Interim Release 7.1 |  | Update to swagger to include missing parameters; aligns with CoCo | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-925 | RG | DIN-906 | 2024-02-14 | SRO Design |  | Rob Golding | SRO Design | Add MPO Encrypted header parameter to callback | Add a parameter to the callback so that the MTLS cert can be authenticated by the MTLS connection. No impact on MPs, Avanade improving the secuirty handshake on the callback |  | Implemented | Design gap | Avanade |  | Interim Release 7.1 |  | Add extra parameter the webhook callback. No impact on PPs | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-926 | RG | DIN-907 | 2024-02-14 | SRO Design |  | Grant Sutcliffe | Avanade | Response codes on delete operations | Standardise response message for successful delete operations on API calls -204 needs to have the text 'No Content' . Need to add other response codes in-line with the other APIs |  | Implemented | Design misaligned |  |  | Interim Release 7.1 |  | Swagger update to include response body on codes where they are expected. Awating details. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-927 | RG | DIN-928 | 2024-02-23 | SRO Design |  | Jon Dennis | Stark | IF-037 mandatory block for [DS¦MS]DeAppUpdate event codes | the B010/B011 blocks are mandatory for the [DS¦MS]DeAppUpdate event codes. |  | Implemented | Design misaligned |  |  | Interim Release 5.5 |  | Update swagger to include required blocks for IF-037 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-928 | RG | DIN-927 | 2024-02-23 | SRO Design |  | Jon Dennis | Stark | IF-037 mandatory block for [DS¦MS]DeAppUpdate event codes | the B010/B011 blocks are mandatory for the [DS¦MS]DeAppUpdate event codes. |  | Implemented | Design misaligned |  |  | Interim Release 7.1 |  | Update swagger to include required blocks for IF-037 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-929 | BK |  | 2024-02-23 | UKPN |  | David Yeoman | Network Operator | Change to NFR E2E1009 for DNO & IDNO roles (LDSO, UMSO, Registrations) | The programme has specified several Non-Functional Requirements that market participants must adhere to. Specifically, E2E1009 states: All Services shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes: - up to average hourly volume, mean response time of 6s or less - up to average hourly volume, 90th percentile response time of 12s or less - from average hourly to peak hourly volume, mean response time of 10s or less - from average hourly to peak hourly volume, 90th percentile response time of 16s or less DNOs and iDNO’s intend to use a ‘DIP Adaptor’ to facilitate interfacing to the DIP. The DIP adaptor provides Level 3 validation. Each ‘back office’ system that connects to the DIP Adaptor under each of the 3 DNO and iDNO roles of, Registration Services, UMSO & LDSO is expected to perform Level 4 validation. These DNO and iDNO systems cannot provide the requested Level 4 technical validation responses within 6, 10, 12 or 16 seconds as detailed in E2E1009. | CR040 | Implemented | Change Request | iDNOs, DNOs |  | Interim Release 8 | 2024-03-20 | The change being proposed is that all DNO and iDNO roles and systems are not required to meet the current specified asynchronous response timeframes of E2E1009 NFR. We request the description for E2E1009 be updated to read: All roles under DNO and iDNOs, namely Registration Services, UMSO & LDSO shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes - 60 minutes or less. This should exclude IF-021 for which there is a separate NFR due to the anticipated volumes. This will ensure alignment with the Operational Choreography " | Technical corrrection | Supporting Docs | Interfaces | E2E002 - Requirements
MHHS-DIN-930 | RG | MHHS-DIN-931 | 2024-02-26 |  |  | Rob Golding | SRO Design | Clarification of response codes that need an associated response body in Swagger | Design need to catch up with implementaton and the 400 response needs a response body for /dip-channel/{id} API |  | Implemented | Design gap |  |  | Interim Release 5.5 |  | StandardResponse is included for: 201 - StandardResponse includes an array of StandardResponseBodyType 207 - StandardResponse includes an array of StandardResponseBodyType 400 - if the response is generated by APIM. It has a single StandardResponseBodyType contained in the StandardResponse. (APIM does not deal with individual payloads contained in a request). If the response is generated inside the DIP (L1 errors), an array of StandardResponseBodyType will be returned in the StandardResponse - one for each payload in the request. Responses for all other Status Codes do not contain StandardResponse. | Technical corrrection | Supporting Docs | Interfaces | Swagger, possibly E2E
MHHS-DIN-931 | RG | MHHS-DIN-930 | 2024-02-26 | SRO Design |  | Rob Golding | SRO Design | Clarification of response codes that need an associated response body in Swagger | Design need to catch up with implementaton and the 400 response needs a response body for /dip-channel/{id} API |  | Implemented | Design gap |  |  | Interim Release 7.1 |  | StandardResponse is included for: 201 - StandardResponse includes an array of StandardResponseBodyType 207 - StandardResponse includes an array of StandardResponseBodyType 400 - if the response is generated by APIM. It has a single StandardResponseBodyType contained in the StandardResponse. (APIM does not deal with individual payloads contained in a request). If the response is generated inside the DIP (L1 errors), an array of StandardResponseBodyType will be returned in the StandardResponse - one for each payload in the request. Responses for all other Status Codes do not contain StandardResponse. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-932 | RG |  | 2023-02-27 |  |  | Rob Golding | SRO Design | Replace references to /api.swaggerhub.com/domains/MHHSPROGRAMME with DIP Production URLs | The move to the DIP Production system will require a repointing of the references to the Swagger modules to the production Swagger repository |  | Open - awaiting assessment | Design misaligned |  |  | Post Go-live Release |  | Replace references to /api.swaggerhub.com/domains/MHHSPROGRAMME with DIP Production URLs, awaiting on DIP | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-933 | RG |  | 2024-02-26 |  |  | Rob Golding | SRO Design | Clarification of response codes that need an associated response body in Swagger | Design need to catch up with implementaton and the 400 response needs a response body for /dip-channel/{id} API |  | Closed | [5 empty] | Duplicate of DIN-930
MHHS-DIN-934 | RS |  | 2024-02-27 | St Clements | 36918 | Daniel Tadecicco | Central Body | IF-001 Migration Change of Supplier (MCS Appointment Scenario) | 003.outgoingSupplierDIPID is defined as Mandatory but for an MHHS Migration the old Supplier may not be MHHS Qualified, so we cannot set this B025.MPAN Energisation Status is defined as Mandatory but we will not have a value at the point we trigger the IF-001, which happens before the SP appointments are confirmed. The MHHS Energisation Status is created when the migration completes (IF-036 issued) B035List.importExportMPANSupplierDIPID is defined as Mandatory but the Supplier of an associated MPAN may not be MHHS Qualified. Further request to widen this DIN to other Forward Migration IFs - these items are also on the IF-002, IF-033 & IF-036 |  | Implemented | Data |  |  | Interim Release 8 | 2024-03-20 | Serveral solution options were discussed with SCS on how this might be resolved. Agreed solution is that REGS will populate a 'dummy DIP iD' ie. 9999999999 into the DIP ID field where required to populate a DIP ID but where the referenced party is not qualified. (This impacts IF-003, IF-002, IF-001, IF-033, IF-036) Add new valid value of U - Undetermined to DI-033 to allow a value to be populated during Migration. This will be updated with the actual Energisation Status at the stage the IF-036 is issued and the value has been set in Registration Service | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-935 | SB |  | 2023-02-27 |  | 34656 |  |  | correction of errors in DES240 (Transitional Scaling Weights) | when recently reviewing the transitional scaling weights we have noticed some errors in the values listed in NewCCC_Weights and Existing_CCCs tabs for losses. The scaling weight principles on first tab state that all losses should have a quality rating of 0.4, however on the NewCCC_Weight tab there are 19 Loss CCCs which have a Quality Rating (column G) of either 0.2 or 0.6 for losses - these should all be 0.4. This would change the Scaling Weight in column I. Similarly the scaling weights for losses, on the Existing_CCCs tab, for Measurement Classes F and G should 1.4 as these are equivalent to MC A (for losses). |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Update DES240 to amend Scaling weights for losses so all are 0.4 as detailed in ticket 34656 | Technical corrrection | Supporting Docs | Interfaces | DES240
MHHS-DIN-936 | RG |  | 2024-02-29 | Design Team |  | Rob Golding | SRO Design | HTTP response code back off & retry behaviour | Align E2E SA doc with the regime for each response code |  | Closed | Design misaligned | All Participants |  |  |  | Align E2E SA doc with the regime for each response code | Technical corrrection | Supporting Docs | Supporting document | E2E Architecture Doc
MHHS-DIN-937 | ZH |  | 2024-02-29 |  |  | John Wiggins/Matthew Breen | SRO Design | Align Migration design with wider design changes made for CR028 | The COS Migration tests continue to show EES receiving the IF-001. The EES instance of the IF-001 was removed from the COS process map and the interface catalogue as part of CR028. As such EES will not be able to process the IF-001 and it is inappropriate to include it as part of the baselined test scenarios. |  | Implemented | Design misaligned |  |  | Interim Release 8 | 2024-03-20 | Updates to be made to relevant Migration artefacts to align with the design changes to the COS process map and DES138 in relevance to EES not receiving IF-001. | Process Model correction | Migration | Process Model correction | BPM001, BPD001
MHHS-DIN-938 | MF |  | 2024-03-01 | PDA |  | Richard French | Data Service Provider | Confirmation of dates to use in the D0388 UMS Inventory | Confirm that the UMSO should populate the effective from date to align with the appointment date. So during BST, for example for a 1st July appointment the D0388 UMS Inventory should state 1 July (even though, where no previous Data Service exists, the UMSDS should calculate periods 47 & 48 of the 30th June UTC Settlement Date ). |  | Implemented | Clarification - No change required |  |  | Interim Release 8 | 2024-03-20 | METH009 UMSO Method Statement updated accordingly | Method statement correction | Supporting Docs | Method Statement | METH009
MHHS-DIN-939 | RS |  | 2024-03-01 | St Clements | 36920 | Daniel Tadecicco | Central Body | Difference in lapse behavior for subsequent IF-031 Appointments between enduring and migration | There is a difference in the logic for Migration and Enduring when it comes to lapsing Appointments. In Migration, it allows MPRS to lapse an IF-031 Migration immediately without a matching IF-034. For enduring MPRS must wait for the IF-034 before lapsing. We would like Migration to be aligned with enduring for ease of coding. This would require a change to MHHS-Migration-Can-RS-005 to change the line "In this case, an IF-035 would be sent immediately to cancel the Migration. " to "Any earlier appointments should be lapsed." |  | Implemented | Design ambiguous |  |  | Interim Release 8 |  | Note added to REGS Migration Requirment - MHHS-Migration-Can-RS-005 to confirm functionality | Requirement correction | Migration | Migration Requirements | Migration Requirements Log
MHHS-DIN-940 | MH |  | 2024-03-01 | Helix | 38131 | Rashmi Radhakrishnan | Central Body | M18 - ISD | The M18 example table in EDI021 ISD Entities has values of N/A where the actual values should be blank. |  | Open - awaiting assessment | Error/Correction | All Participants |  | Post Go-live Release |  | Update the example table to show blank fields where the DIP Role does not have an associated MP Role Code | Other | Supporting Docs | ISD Entities | EDI021
MHHS-DIN-941 | RG | DIN-720 | 2023-10-11 | Utiliteam |  | Mike Fensome | SRO Design | Update to DI-122 Profile Class to min length of 1, max length of 2 | Allow Profile Class (DI-122) to be provided with min length of 1 and max length of 2 in both swagger and DES138 so that, for example, either 1 or 01 are accepted. |  | Implemented | Error/Correction |  |  | Interim Release 7.1 |  | Update 7.1 swagger to match 5.4 for DI-122 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-942 | RG |  | 2024-03-05 | St Clements |  | Melissa Brocklehurst | Software Provider | Errors in REP-901 in Swagger | Blocks R901-07 & R901-08 do not align with the defintion in ERI011B s/s. The fields chargeBand, dailyUncorrectedVolumeForChargeBand and totalVolumeChargeForChargeBand need to be removed from R901-07 |  | Implemented | Error/Correction |  |  | Interim Release 7.2 |  | Remove chargeBand, dailyUncorrectedVolumeForChargeBand and totalVolumeChargeForChargeBand fields from R901-07 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-943 | BK |  | 2024-03-05 | Helix |  | Nigel Rees | Central Body | CR034 - Delay to Elexon Level 4 validation response – NFR (1009) | The change being proposed is that Helix does not meet the requirements of E2E1009 NFR. We request the description for E2E1009 be updated to read “All Services shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes - 10minutes or less – excludes IF-021” | CR034 | Implemented | Change Request |  |  | Interim Release 7.1 |  | Updated Level 4 Processing Times (Asynchronous) requirement as follows; All Services with the exception of Helix (VAS,MDS,LSS,ISD) Services shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes - up to average hourly volume, mean response time of 6s or less - up to average hourly volume, 90th percentile response time of 12s or less - from average hourly to peak hourly volume, mean response time of 10s or less - from average hourly to peak hourly volume, 90th percentile response time of 16s or less Helix Services (VAS,MDS,LSS,ISD) shall provide an Asynchronous response time of 10 minutes or less. | Requirement correction | Supporting Docs | Requirements | MHHS-E2E002 Requirements
MHHS-DIN-944 | SB |  | 2024-03-08 | Design Team |  | Paul Pettitt | SI Design | Service Provider appointment Process | The Operational choreography does not align with the Design intent of flexibility with Service Provider Appointment. OP_120 requires clarification |  | Closed | Error/Correction |  |  |  |  | Closed - upholding the objection raised by ReCCo against this DIN
MHHS-DIN-945 | SC |  | 2024-03-13 | RECCo |  | Sarah Jones | Central Body | CR46 - Change of Energy Direction | Remove reference to 'one-time only' change and add guidance that Change of ED will not change hisotric consumption in MDS/Settlements - any changes to hisotric consumption for that MPAN should be via Consumption Ammendment or Trading Dispute | CR046 | Implemented | Change Request | All Participants |  | Interim Release 8.1 |  | "One Time Change" reference removed from BP010B and BPD010B for "Change of Energy Direction" process, Registration Requirements (BRS003), Supplier Overview (BRS004) and LDSO Overview (BRS005). New note added to BP010B to highlight that any historic settlement data will not be amended, this would need to be via Consumption Amendment or Dispute process where required. | Process Model correction | Registration | Business Process Models/ Requirements | BRS003, BRS004, BRS005, BP010 and BP010B
MHHS-DIN-946 | RS |  | 2024-03-13 | St Clements | 39364 41047 | Daniel Tadecicco | Central Body | Use of LP006 - Migration Aborted, Pending Registration Received | MHHS DEL974 has requirement MHHS-Migration-COA(MS)-RS-002 states two event codes MGR_Cancelled_MS and MGR_Cancelled_DS should be created, however this needs to be amended to confirm the use of LP006 |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Update to MHHS-Migration-CoA(MS)-RS-002/MHHS-Migration-CoA(DS)-RS-002 in MHHS-DEL974 and Migration Design Document section 13.2.3 | Technical corrrection | Migration | Supporting document | MHHS-DEL974 Migration Design Document
MHHS-DIN-947 | SC |  | 2024-03-13 | DIP |  | Sean Cooper | Central Body | Changes to Swagger to support Implementation of JSON Error Checking End Points. | Swagger to be updated to include facility for new JSON Message Error Checking End Points and response message. |  | Implemented |  |  |  | Interim Release 7.2 |  | Swagger to be updated to include facility for new JSON Message Error Checking End Points and response message. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-948 | SC |  | 2024-03-14 | St Clements |  | Sean Cooper | SRO Design | Error Code Description Text Updates | Update Error code Text to align with confirmed text provided by SCS |  | Implemented | Design gap |  |  | Interim Release 8 | 2024-03-20 | Update Error code Text to align with confirmed text provided by SCS | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-949 | RS | DIN-1021 | 2024-03-15 | St Clements | 39365 | Daniel Tadecicco | Central Body | MHHS-Migration-CoA(MS)-RS-009 Alignment with IR7 | The IF-031 REG code in the Migration Requirements log for MHHS-Migration-CoA(MS)-RS-009 does not align with IR7 IR7 IF DI-800 = SEG or CSP, COS, USP and MPAN is not migrated (ie operating in old regime) REG9008 - MHHS Scenario Codes cannot be used for UnMigrated MPAN |  | Implemented | Design misaligned |  |  | Interim Release 8 | 2024-03-20 | Update Migration requirements doc to align with DES138 error code (REG9009) and updated Migration doc where relevant to align with DES138 error code (REG9009). | Technical corrrection | Migration | Supporting document | Migration Requirements Log Migration Design Document
MHHS-DIN-950 | SC |  | 2024-03-18 |  |  | Sean Cooper | SRO Design Team | CR44 - IF-051 Refresh Message | CR044 - Please refer to the change request documentation for details | CR044 | Closed | Change Request |  |  |  |  | ~ Swagger changes to include new IF-051 ~ Secondary routing treatment of If-051 [DONE] ~ Add IF-051 data strcutre to DES138 [DONE] | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-951 | SC |  | 2024-03-18 |  |  | Sean Cooper | SRO Design Team | CR45 - SSD Fix Tool | CR045 - Please refer to the change request documentation for details | CR045 | Closed | Change Request |  |  |  |  | ~ Swagger updates to include New De-App Reason Code ~ Swagger New IF-001 Event Codes ~ Add IF-001 Event Codes to DES138 [DONE] ~ Changes to secondary Routing to Support [DONE] ~ Possible SSD Fix Business Process Diagram | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger Potential - BPXXX
MHHS-DIN-952 | RS |  | 2024-03-18 | Datamere | 41267 | Paul O'Neill | Software Provider | Anomolies in DES138 | DI-991 on 02_DIP_Common worksheet states the values can be TBC (eg PROD, PREPROD, UAT, SIT, DEV). Postman states the following: "S1.environmentTag must be one of 'PROD,PREPROD,SIT,UIT,DEV'." Q2 – DI-840 on 02_IF-031 worksheet states the data item is named CSS Registration ID. Postman states the following: property 'CSSRegistrationID' is unsupported for 'B013' block", B013.CSSRegistrationRequestID field is required. |  | Initial Assessment/Updating | Design misaligned | All Participants |  | Post Go-live Release |  | Solution yet to be defined | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-953 | SC |  | 2024-03-18 |  |  | Sean Cooper | SRO Design | New DTN Flows for Existing Retained Settlement D-Flows | Update EDI001 Settlement Reporting Spec to reference New D-Flow References assigned to retained D-Flows |  | Closed | Design misaligned |  |  |  |  | Update EDI001 Settlement Reporting Spec to reference New D-Flow References assigned to retained D-Flows
MHHS-DIN-954 | RG |  | 2024-03-18 | Avande |  | Piotr Penar | Avanade | Add validation endpoints into Swagger | Add validation endpoints into Swagger |  | Closed | [5 empty] | DUPE 954
MHHS-DIN-955 | MH |  | 2024-03-21 |  |  | Matt Hall | SI Design | CR043 - MPAN/ABMU Mapping | DIN to cover the changes required to Design folowing approval of CR043 | CR043 | Implemented | Change Request | Suppliers, MDS |  | Interim Release 8 | 2024-03-20 | New requirements to be added to MDS and Suppliers' BRS documents to cover CR043 | Requirement correction | Supporting Docs | Requirement correction | BRS004-Supplier Overview BRS008 MDS Requirements
MHHS-DIN-956 | ZH |  | 2024-03-21 | MHHS |  | Zakir Hussain | SI Design | Rebranding of D-Flows - DES196 & ERI011b | DIN to align changes made in the DES196 document (latest D-flows added to the doc) to the relevant areas within design |  | Implemented | Design misaligned | All Participants |  | Interim Release 8.1 |  | Update ERI011b and DES196 to reflect use of ECS DTN reports and New D-Flow References assigned to retained D-Flows | Reporting correction | Supporting Docs | Various documents | ECS Report External ERI011b DES196
MHHS-DIN-957 | MF | Test defect 31009 DIN-963 DIN-964 | 2024-03-21 | SI Design |  | Mike Fensome | SI Design | Update swagger in IF-005 | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. |  | Implemented | Error/Correction |  |  | Interim Release 5.5 |  | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-958 | BK | MHHS-DIN-937 | 2024-03-21 | SRO Design |  | John Wiggins/Matthew Breen | SRO Design | Align Migration design with wider design changes made for CR028 | The COS Migration tests continue to show EES receiving the IF-001. The EES instance of the IF-001 was removed from the COS process map and the interface catalogue as part of CR028. As such EES will not be able to process the IF-001 and it is inappropriate to include it as part of the baselined test scenarios. |  | Closed | Design misaligned |  |  |  |  | Updates to be made to relevant Migration artefacts to align with the design changes to the COS process map and DES138 in relevance to EES not receiving IF-001. | Process Model correction | Migration | Process Model correction | BPM001, BPD001, Migration document
MHHS-DIN-959 | BK | MHHS-DIN-942 | 2024-03-21 | St Clements |  | Melissa Brocklehurst | Software Provider | Errors in REP-901 in Swagger | Blocks R901-07 & R901-08 do not align with the defintion in ERI011B s/s. The fields chargeBand, dailyUncorrectedVolumeForChargeBand and totalVolumeChargeForChargeBand need to be removed from R901-07 |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Remove chargeBand, dailyUncorrectedVolumeForChargeBand and totalVolumeChargeForChargeBand fields from R901-07 | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-960 | BK | MHHS-DIN-947 | 2024-03-21 | DIP |  | Sean Cooper | Central Body | Changes to Swagger to support Implementation of JSON Error Checking End Points. | Swagger to be updated to include facility for new JSON Message Error Checking End Points and response message. |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Swagger updated to include facility for new JSON Message Error Checking End Points and response message | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-961 | RG |  | 2024-03-22 | SRO Design |  | Rob Golding | SI Design | Update Environment list to reflect those being delivered by Avanade | Existing list: - PROD - PREPROD - SIT - UIT - DEV Update to add SITB |  | Implemented | Error/Correction |  |  | Interim Release 5.5 |  | Only SITB currently added | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-962 | RG | DIN-1011 | 2024-03-25 | Helix | 42284 | Nigel Rees | Central Body | Make MPAN optional on replay/requeue | Removing MPAN from the mandatory list of parameters for DIP replay/requeue |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Removing MPAN from the mandatory list of parameters for DIP replay/requeue and introduce mandatory/null design pattern on input parameters | Technical corrrection | Supporting Docs | Interfaces | Swagger, E2E SA
MHHS-DIN-963 | MF | Test defect 31009 DIN-964 DIN-957 | 2024-03-21 | SI Design |  | Mike Fensome | SI Design | Update swagger in IF-005 | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. |  | Implemented | Error/Correction |  |  | Interim Release 7.2 |  | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-964 | MF | Test defect 31009 DIN-963 DIN-957 | 2024-03-21 | SI Design |  | Mike Fensome | SI Design | Update swagger in IF-005 | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-965 | RG |  | 2024-03-22 | SRO Design |  | Rob Golding | SI Design | Update Environment list to include SITB | Existing list: - PROD - PREPROD - SIT - UIT - DEV Update to add SITB |  | Implemented | Error/Correction |  |  | Interim Release 7.2 |  | Only SITB currently added | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-966 | SC | Test Defect 31336 DIN-1019 | 2024-03-27 | SRO Design |  | Sean Cooper | SRO Design | Revision to the PUB-004 Secondary routing logic. | SIT DEFECT - 31336 Currently distribution logic states delivery of PUB-004 to SUPC and XMSC. This results in the send of the message (IF-004) being unnecessrily copied in on the PUB-004. Secondary logic should reference sending party and issue to XMSC where sent by SUPC and SUPC where message sent by XMSC. |  | Implemented | Error/Correction |  |  | Interim Release 7.3 |  | SIT DEFECT - 31336 Currently distribution logic states delivery of PUB-004 to SUPC and XMSC. This results in the send of the message (IF-004) being unnecessrily copied in on the PUB-004. Secondary logic should reference sending party and issue to XMSC where sent by SUPC and SUPC where message sent by XMSC. DES138 - IF-004 routing table updated accordingly | Technical corrrection | Supporting Docs | Interfaces | Secondary Routing DES138
MHHS-DIN-967 | MF | Test Defect 31338 | 2024-03-27 | Design Team |  | Mike Fensome | SRO Designn | Update BP010A to show that MPL address updates from UMSO are via "Agreed Communication Method" | Update BP010A to show that MPL address updates from the UMSO are notified via "Agreed Communication Method" |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated BP010A and BPD010A to show that MPL address updates from the UMSO are notified via "Agreed Communication Method". This aligns with BR-MS-064 and reflects that the UMSO cannot currently use D0381 flow | Process Model correction | MPAN Ownership | Business Process Models | BP010A BPD010A
MHHS-DIN-968 | SC |  | 2024-03-27 | Avanade |  | Sean Cooper | SRO Design | MDR Secondary Routing | Following text added to interfaces where MDR is referenced as a Secondary Recipient .... .... "Reference to MDR above assumes that MDR is Qualified for DIP Operations & is opt'ed in for SDS-MDR message exchange" |  | Implemented | Design ambiguous |  |  | Interim Release 8 | 2024-03-20 | Following text added to appropriate interfaces.... .... "Reference to MDR above assumes that MDR is Qualified for DIP Operations & is opt'ed in for SDS-MDR message exchange" | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-969 | SC |  | 2024-03-28 | SCS |  | Sean Cooper | SRO Design | Implementation of REGS Calendar based RF Cut of Date Checking | SCS have confirmed that RF Cut Off Date validation based on the ISD Settlement Calendar cannot be implemented until post go-live. SCS/Programme assessment is that given the other validation rule(s) in place principly the check around Migration Date that this is not an issue. This DIN is to formally record this issue - DIN will be differed. |  | Open - awaiting assessment | Design gap |  |  | Post Go-live Release |  | RF restrictions for MS, DS, MDR, Energisation Status EFDs. Differred DIN captured for reference |  |  |  | ISD
MHHS-DIN-970 | SC |  | 2024-03-28 | SCS |  | Sean Cooper | SRO Deign | Bypassing SSD Check where no SP's are appointed even beyond RF Cut Off Date | Logic check required following implementation of DIN969 to allow for Retrospective Appointment of SP's prior to RF Cut off Date - where Supplier has failed to do this prior to RF cut off date for the SP Appointment Start Date |  | Open - awaiting assessment | Design gap |  |  | Post Go-live Release |  | Logic variation to allow Pre-RF Cut Off Retro Appointments - Differed DIN Captured for Reference |  |  |  | ISD
MHHS-DIN-971 | SC |  | 2024-03-28 |  |  | Sean Cooper | SRO Design | Clarifcation of MPAN Linkage Request Rejection Codes | Programme has been waiting for LDSO confirmation of these codes however this has not been forthcoming todate. In order to finalise the design for other participants the following codes will constitute the go-live design. IE000 - Proposed Linkage Change Accepted IE001 - Proposed Linkage Change Rejected IE099 - Please contact LDSO directly for further advice |  | Implemented | Design gap |  |  | Interim Release 8 | 2024-03-20 | Programme has been waiting for LDSO confirmation of these codes however this has not been forthcoming todate. In order to finalise the design for other participants the following codes will constitue the go-live design. IE000 - Proposed Linkage Change Accepted IE001 - Proposed Linkage Change Rejected IE099 - Please contact LDSO directly for further advice | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-972 | SC |  | 2024-04-02 | SCS |  | Sean Cooper | SRO Design | Migration Reqs: Removal of Reference to IF-040 (Annual Consumption) from the REGS Migration Requirments | Missed CR39 Update - Remove of Reference to IF-040 (Annual Consumption) from the REGS Migration Requirments |  | Implemented | Design misaligned |  |  | Interim Release 8 | 2024-03-20 | Missed CR39 Update - Remove of Reference to IF-040 (Annual Consumption) from the REGS Migration Requirments | Technical corrrection | Migration | Supporting document | Migration Requirements Log
MHHS-DIN-973 | SC | 1038 | 2024-04-02 | SCS |  | Sean Cooper | SRO Design | Migration Reqs: Correct REGS treatment of D0312 where a Forward MIgration is in progress. | Requirment updated to refeclt that IF-035 with Lapsed Reason Code of LP001 (MPAN Disconnected/deRegistered) will be issued for any Pending Service Provider Appointments on receipt of D0312 |  | Implemented | Design ambiguous |  |  | Interim Release 8 | 2024-03-20 | Note added to RESG Migration Requirement MHHS-Migration-Can-RS-006 - to confirm process | Technical corrrection | Migration | Supporting document | Migration Requirements Log
MHHS-DIN-974 | RG | DIN-1012 | 2024-04-02 | EDW Technology |  | Mark Kenney | SRO Design | Align webhookresponse on /statusmessage to /dip-channel | Status messages reponses from the PP systems and the DIP need to align |  | Implemented | Design misaligned | All Participants |  | Interim Release 8.1 |  | Status messages responses from the PP systems and the DIP need to align, also standard message webhook response should return a standard response body on a 400 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-975 | SC |  | 2024-04-02 | SCS |  | Sean Cooper | SRO Design | Migration Reqs: Confirm REGS treatment of related MPANs in Reverse Migration Scenario | Process is not "automatic" with the REGS per se. CSS will issue a switch request for each MPAN, REGS will process each switch request -end result is the same |  | Implemented | Design ambiguous |  |  | Interim Release 8 | 2024-03-20 | Note added to RESG Migration Requirement MHHS-RMigration-CoS-RS-002 to confirm process is not automatic - same end result is achived through CSS functionality | Technical corrrection | Migration | Supporting document | Migration Requirements Log
MHHS-DIN-976 | RG |  | 2024-04-05 | ESG | 44664 | Patricia Parker | SRO Design | Duplicate enumeration values for the DI-596 Charge Type enumeration | Duplicate enumeration values for the DI-596 Charge Type enumeration, CAPAC appears twice |  | Closed | Error/Correction |  |  |  |  | DI-596 Charge Type enumeration, CAPAC appears twice - Need to remove duplicate charge type | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-977 | RG |  | 2024-04-05 | Avanade |  | Rob Golding | SRO Design | Update PROD to PRD in Environment Tag List | Confirmation that Avanade have labeled the Production DIP environment PRD. The DT-013-EnvironmentTag will require updating: Change PROD to PRD and removed PREPROD. Add SITB |  | Implemented | Design misaligned | All Participants |  | Interim Release 8.1 |  | The DT-013-EnvironmentTag will require updating: Change PROD to PRD and removed PREPROD. | Technical corrrection | Supporting Docs | Interfaces | Swagger, E2E SA
MHHS-DIN-978 | RS |  | 2024-04-08 | ESG | 41894 | Patricia Parker | Software Provider | REP-003 and REP-006 have JSON label missing in ERI011b - ECS Reports | REP-003 and REP-006 should have Distribution Pattern A and Report Format JSON in cell H7 as per the other MHHS-REP-XX (eg MHHS-REP-07) |  | Initial Assessment/Updating | Error/Correction | All Participants |  | Post Go-live Release |  | Update REP-003 and REP-006 in ERI011b to match include outlined box as per MHHS-REP-07 | Reporting correction | Supporting Docs | ECS Reports | ERI011B
MHHS-DIN-979 | RS |  | 2024-04-08 | ESG | 41955 | Patricia Parker | Software Provider | DI-819 (De-appointment reason code) in IF-003 should not contain CSERV. Only CSUPP should be used | DES138, IF-003 has DI-819 has the option for CSERV Change of Service Provider in the Population notes column. This should be greyed out leaving just CSUPP change of supplier |  | Closed | Error/Correction | All Participants |  |  |  | Update IF-003 in DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-980 | MH |  | 2024-04-10 | SCS | 44726 | Madison Layton | Software Provider | ISD versioning IR8 | IR8 version of ISD has not included the IR7.1 changes. This needs to be resolved by adding the changes back in. This is only DIN-899 |  | Implemented | Error/Correction | Helix, ISD users |  | Interim Release 8.1 |  | Add DIN-899 changes back in to the latest version of IR8. Updates required were covered by DIN-1033 and changing M15 to include N as No Consent | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-981 | RS |  | 2024-04-11 | Siemens | 41452 | David Baxendale | Data Service Provider | Incorrect Load Shape Off Peak Period | Most of the off-peak periods cover 14 UTC periods (7 Hours) – either 00:00 to 0700 OR 00:30 to 7:30 There is 1 anomaly in METH001 GSP _C Profile Class 4 has 15 UTC periods – 00:00 to 07:30 |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Method statement will need to be corrected to reflect 00:00 - 07:00 also remove minus sign after the 00:30 _K Will also need to check the load shaping method statement as well (Also incorrect in LSS METH005) | Method statement correction | Supporting Docs | Method Statement | METH001 METH005
MHHS-DIN-982 | ZH | DIN-575/1013 | 2024-04-11 | SCS |  | Madison Layton | Software Provider | CR039 implementation | DES138 - IF040 requires removal of REGS in "To Parties" field | CR039 | Implemented | Change Request | REGS |  | Interim Release 8.1 |  | Update IF040 in DES138, removed "Registration Service (REGS)" from "To Parties" field | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-983 | RS |  | 2024-04-11 | MHHS | 36071 | Matt McKeon | Central Body | LLFC Id mandated in retained DTC flow | The Line Loss Factor Class Id is being replaced by the DUoS Tariff Id. The LLFC Id is present in various DTC flows, almost all of which are redundant post MHHS. LLFC Id is an optional field in the D0311 which, according to DES196, is retained post MHHS with the MHHS Change “New rules to clarify that Profile Class and Meter Timeswitch Class [code] should be null if no value exists for MHHS MPANs, LLFC should be populated with the DUoS Tariff Id for MHHS MPANs and EACs should only be provided for non-MHHS MPANs. ”. LLFC Id is a mandatory field in the D0387 which, according to DES196, is retained post MHHS with no changes. |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Replicating the rule in the D0311 in the D0387 seems appropriate. Will add a note to the D0387 and amend DES196. Propose to do this once SIT Cycle 2 has completed, as adding it now would impact DTN flow test scope. | Data interface correction | Supporting Docs | DFlow | DES196
MHHS-DIN-984 | RS | DIN-917 | 2024-04-12 | ESG | 42711 | Patricia Parker | Software Provider | D0148 use within Reverse Migration | DEL961 Migration Document detail does not contain any detail of the use of the D0148 when completing a Reverse Migration as assumed to BAU. Need to reference the use of the New connection process for D0148 as per section 9 of Annex c |  | Implemented | Design ambiguous | All Participants |  | Interim Release 8.1 |  | Add reference to D0148 new connection process (section 9 annex C) to DEL961 (Section 13.1) | Design Ambiguous | Supporting Docs | Migration Design | DEL961
MHHS-DIN-985 | RS | DIN-837 | 2024-04-12 | ESG | 42711 | Patricia Parker | Software Provider | Incorrect meter reading code in section 6.1.3 of DEL961 Migration Design | Secftion 6.1.3 of DEL961 still states Meter Reading Reason Code = 28 (Forward Migration CoA) Instead of Reading Type = U. This should match previously agreed updates of U - Forward Migration CoA V - Forward Migration CoS X - Supplier Agreed Switch Read Y - Reverse Migration CoS As per MHHS impacts to Data Transfer Network (DTN) Flows |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Section 6.1.3 of DEL961 to be updated with U - Forward Migration CoA V - Forward Migration CoS X - Supplier Agreed Switch Read Y - Reverse Migration CoS Remainder of ducument sections to be checked for same disparity | Design Ambiguous | Supporting Docs | Migration Design | DEL961
MHHS-DIN-986 | RS |  | 2024-04-12 | MHHS | 45969 | Test team | Central Body | Incorrect step assigned to migration requirement | DEL974 requirements MHHS-Migration-CoA(MS)-RS-005 and MHHS-Migration-CoA(DS)-RS-005 refer to step 255 of BPM002. No step 255 exists on BPM002. Requirement to be amended to step 710 |  | Initial Assessment/Updating | Error/Correction | All Participants |  | Post Go-live Release |  | Amend requirements MHHS-Migration-CoA(MS)-RS-005 and MHHS-Migration-CoA(DS)-RS-005 to step 710 in DEL947 (Registration Tab, row 19 and 39) | Requirement correction | Migration | Migration Requirements | DEL974
MHHS-DIN-987 | ZH | DIN-676 | 2024-04-15 | SCS |  | Madison Layton | Software Provider | Missing text in NFRs - CR-018 implementation issues | E2E002 was updated as per IR8 however it is missing text that specifies details around when they are applicable |  | Closed | Error/Correction |  |  |  |  | Duplicate of 993 | Requirement correction | Supporting Docs | Requirements | MHHS-E2E002 Requirements
MHHS-DIN-988 | ZH |  | 2024-04-15 | SCS |  | Daniel Tadecicco | Software Provider | Migration design alignment | DES138 requires some updates to align with the migration design documentation |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated IF-003 in DES138 to remove MSDeAppUdateRM & DSDeAppUpdateRM events and removed the accompanying interface note as these events are not used in the case of Reverse Migration Design. Opt In/Out matrix updated accordingly. Swagger updated. | Data interface correction | Supporting Docs | Interfaces | DES138 & Swagger
MHHS-DIN-989 | RG |  | 2024-04-15 | Stark | 45757 | Jon Dennis | Software Provider | DI-596-Charge-Type - CAPAC duplicated in Enum | DI-596-Charge-Type - CAPAC duplicated in Enum -one of the entries needs to be removed |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | remove second CAPAC from enumerated list | Data interface correction | Technical Artefact | Interfaces | Swagger
MHHS-DIN-990 | MF | DI-136 | 2024-04-17 | SCS |  | Madison Layton | Software Provider | Limit effective from updates to RF for appointments and energisation status changes | Update validation rules in IF-031, IF-034 and IF-007 to not allow updates to appintment effective from dates and energisation status effective from dates beyond RF |  | Implemented | Error/Correction | Suppliers, REGS |  | Interim Release 8.1 |  | Update validation rules in IF-031, IF-034 and IF-007 to not allow updates to appintment effective from dates and energisation status effective from dates beyond RF. Added note to REGS Notes to confirm that derived Market Segment Effective from Date cannot be beyond RF. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-991 | MF | DIN-939 | 2024-04-17 | SCS |  | Madison Layton | Software Provider | Confirm migration lapse behavior aligns with BAU operation | Update note on MHHS-MIGRATION-CAN-RS-005 to confirm that lapse notification is only issued after receipt of IF-034 |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated note on MHHS-MIGRATION-CAN-RS-005 to confirm that lapse notification is only issued after receipt of IF-034 | Requirement correction | Migration | Migration Requirements | DEL974
MHHS-DIN-992 | RG | DIN-1014 | 2024-04-17 | Design Team |  | Rob Golding | SRO Design | IF-016-ActivePowerRejected required incorrect | IF-016-ActivePowerRejected required field B900List should be B900 |  | Implemented | Error/Correction | Advanced Data Service |  | Interim Release 8.1 |  | Update: IF-016-ActivePowerRejected required field B900List to B900 | Data interface correction | Technical Artefact | Interfaces | Swagger
MHHS-DIN-993 | MF | DIN-929 | 2024-04-17 | SCS |  | Daniel Tadecicco | Software Provider | Confirmation of LDSO response times | Update E2E1009 in line with CR040 and Operational Choreography to confirm repsonse times specified are within normal operating hours | CR040 | Implemented | Change Request | All Participants |  | Interim Release 8.1 |  | Updated E2E1009 in line with CR040 and Operational Choreography to confirm repsonse times specified are within normal operating hours | Technical corrrection | Supporting Docs | Interfaces | E2E002 - Non-Functional Requirements
MHHS-DIN-994 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Treatment of mixed meter sites | Update registration notes to confirm treatment of mixed meter sites |  | Initial Assessment/Updating | Design ambiguous | REGS |  | Post Go-live Release |  | Update Reg Notes in DES138 to confirm that: • If a mix of Smart and Traditional meters then consider the Meter Group as Smart • If any Advanced meter is fitted then this should be considered as in the Advanced Segment so Meter Group as Advanced. Update REG1042 and REG1043 validation in IF-025 to clarify how mixed meters are validated | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-995 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Correlation ID removed from IF-037 AppUpdate events | Remove Correlation ID from AppUpdate events on IF-037 |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Removed Correlation ID from AppUpdate events on IF-037 | Data interface correction | Supporting Docs | Interfaces | DES138 (No swagger change reqd)
MHHS-DIN-996 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Update description of DI-028 (Reconnection Effective from Date) | Update description of DI-028 to reflect that this is when the Metering Point is reconnected in Registration Service |  | Initial Assessment/Updating | Design ambiguous | All Participants |  | Post Go-live Release |  | Update description of DI-028 to reflect that this is when the Metering Point is reconnected in Registration Service | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-997 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | PUB-007 validation to allow de-energisation on a Disconnected MPAN | Validation should be changed to allow a PUB-007 to De-energise a Disconnected MPAN (De-energise only, energisation would still not be permitted on disconnected MPAN) |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | New Validation to allow a PUB-007 to De-energise a Disconnected MPAN (De-energise only, energisation would still not be permitted on disconnected MPAN) with error code of REG1001 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-998 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Clarification on sending error message on IF-034 where incorrect Service Provider responds | Add note to IF-034 validation rules to confirm that REGS will respond with RCP1063 if the incorrect Service Provider responds |  | Initial Assessment/Updating | Error/Correction | All Participants |  | Post Go-live Release |  | Added note to IF-034 validation rules to confirm that REGS will respond with RCP1063 if the incorrect Service Provider responds | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-999 | MF | DIN-788/1015 | 2024-04-18 | UKPN |  | Neil Madley | Network Operator | Update routing for [MPANReconnection] and add event to Opt/In Out Matrix | On IF-009 add LDSO as secondary routed. Add [MPANReconnection] to the Opt In/ Opt Out Matrix so that LDSO's can opt out of receiving this event. |  | Implemented | Error/Correction |  |  | Interim Release 7.3 |  | On IF-009 added LDSO, SUPC as secondary routed. Added [MPANReconnection] to the Opt In/ Opt Out Matrix so that LDSO's can opt out of receiving this event. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1000 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Update to error message REG1032 to refer to Local Time | Update REG1032 validation on IF-031 in DES-138 to refer to Local Time |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated REG1032 error message on IF-031 in DES-138 to refer to Local Time, where previously referenced UTC. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1001 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Remove REGS requirement MHHS-BR-RS-014.1 | Supplier Nominated DPI is not provided on Metering Service Appointments, so this Requirement is not needed. |  | Initial Assessment/Updating | Error/Correction | REGS |  | Post Go-live Release |  | Removed requirement MHHS-BR-RS-014.1 from BRS-003 to provide Supplier Nominated DPI for Metering Service Appointments. Requirement retained for Data Service Appointments. | Requirement correction | MPAN Ownership | Requirement correction | BRS003 - Registration Service requirements
MHHS-DIN-1002 | MH |  | 2024-04-19 | Helix |  | Rashmi Radhakrishnan | Central Body | ISD M11 and M12 | As per the UMSUG meeting that we attended, For M12, its been agreed that we need to incorporate OFF event to have “NEVER” where there is no OFF event. |  | Implemented | Error/Correction | UMSDS |  | Interim Release 8.1 |  | Added a new permissable value of "NEVER" to the OFF Event data field in ISD Entity M12 | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-1003 | RS |  | 2024-04-19 | National Grid | 43643 | Rachael Prosser | Network Operator | E2E Architecture Document to be updated to include Reference to LDSO and IF-20 | E2E Architecture Document does not include latest updates made to IF-20 for LDSO, review and update required |  | Initial Assessment/Updating | Error/Correction | LDSOs |  | Post Go-live Release |  | Add line advising for the latest representation refer to DES138. RG to to complete review of document | Other | Supporting Docs | Supporting Docs | E2E001
MHHS-DIN-1004 | RS |  | 2024-04-19 | CGI | 47845 | Dave Webster | Software Provider | DES138 OptOut Matrix for IF-003 Supplier | The 04_IF_OptOut_Matrix sheet of DES138 v5.8.1 shows that IF-003 is not received by Supplier (“N/A”), but for all Event Codes the IF-003 message is Primary Routed to Supplier |  | Implemented | Error/Correction | Suppliers |  | Interim Release 8.1 |  | Changed IF-003 for Supplier to No from N/a in DES138 IF Opt out Matrix tab. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1005 | MH |  | 2024-04-19 | Helix | 46469 | Matt Hall | SI Design | METH007 Section D clean up | Currently SEction D in the METH007 doesn't clearly distinguish between REP002/2a and 2b. This is causing some confusion and should be rectified |  | Initial Assessment/Updating | Design ambiguous | All Participants |  | Post Go-live Release |  | Tidy up of Section D in MTH007 to clarify which reports are included, and to clarify which of the REP02 variants require non-W connections include (if any) | Method statement correction | Supporting Docs | Method Statement | METH007
MHHS-DIN-1006 | MH | DIN-087 | 2024-04-19 | RECCo | 46872 | Sarah Jones | Central Body | Outstanding Design Query (DIN087) | As part of the final code drafting checks, we are confirming that all consultation comments have been addressed. We have identified a comment from an early drafting tranche (CD-0558) which queries the requirements to issue a de-energisation notice for meter exchanges. At the time, we were expecting a note to be added to BP008 to make it clear that that ‘DeEn did not need to be notified if meter works completed within same day (ie same rules as today)’ as stated in the DIN log against DIN087. However, BP008 doesn’t appear to have this note included which means we have not been able to close out the code drafting query. |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Add a box to BPM008 to to reflect the proposed solution in DIN-087 | Process Model correction | Supporting Docs | Business Process Diagram | BP008
MHHS-DIN-1007 | RG | DIN-1018 | 2024-04-22 | Avanade |  | Rob Golding | SRO Design | Change request body on Validation Endpoints | Avanade have reviewed the 1.7.1. endpoints and are requesting a chnage so that they are more flexible and align to the submission API |  | Implemented | Error/Correction |  |  | Interim Release 7.3 |  | Avanade have reviewed the 1.7.1. endpoints and are requesting a change so that they are more flexible and align to the submission API | Technical corrrection | Swagger |  | Swagger
MHHS-DIN-1008 | SB |  | 2024-04-23 | British Gas |  | Neil Strange | Supplier | BP-03C Transfer of Reads Clarification | We’ve noticed that on PB03C the IF/PUB016 interface is TBC – looking at DES138 I believe this is confirmed – am I correct? This is in the advanced meters section following successful appointment. |  | Initial Assessment/Updating | Design ambiguous | Advanced Data Service |  | Post Go-live Release |  | Updating IF-016, to include DES138 information | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-1009 | SB |  | 2024-04-23 | MHHS |  | Shaun Magee | Central Body | METH002 Issue with LTV Method statement | Incorrect Method referenced in section 3.13 should be method 11 rather than 12 |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update: Incorrect Method referenced in section 3.13 should be method 11 rather than 12 | Method statement correction | Supporting Docs | Method Statement | METH002
MHHS-DIN-1010 | TR | DIN-762 | 2024-04-23 | RECCo | 46312 | Jonny Moore | Central Body | IF-003 - EES as Recipient | EES not included within the 'To Parties' in DES138 |  | Initial Assessment/Updating | Design misaligned | EES |  | Post Go-live Release |  | DES138 updated to include EES in the 'To Parties' field | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1011 | RG | DIN-962 | 2024-03-25 | Helix | 42284 | Nigel Rees | Central Body | Make MPAN optional on replay/requeue | Removing MPAN from the mandatory list of parameters for DIP replay/requeue |  | Closed | Error/Correction |  |  |  |  | Only implement in IR8 | Technical corrrection | Supporting Docs | Interfaces | Swagger, E2E SA
MHHS-DIN-1012 | RG | DIN-974 | 2024-04-02 | EDW Technology |  | Mark Kenney | SRO Design | Align webhookresponse on /statusmessage to /dip-channel | Status messages reponses from the PP systems and the DIP need to align |  | Implemented | Design misaligned |  |  | Interim Release 7.3 |  | Status messages reponses from the PP systems and the DIP need to align | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-1013 | ZH | DIN-575/982 | 2024-04-11 | SCS |  | Madison Layton | Software Provider | CR039 implementation | DES138 - IF040 requires removal of REGS in "To Parties" field | CR039 | Closed | Error/Correction |  |  |  |  | Update IF040 in DES138, remove "Registration Service (REGS)" from "To Parties" field | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1014 | RG | DIN-992 | 2024-04-17 | SRO Design |  | Rob Golding | SRO Design | IF-016-ActivePowerRejected required incorrect | IF-016-ActivePowerRejected required field B900List should be B900 |  | Implemented | Error/Correction |  |  | Interim Release 7.3 |  | IF-016-ActivePowerRejected required field B900List should be B900 | Data interface correction | Technical Artefact | Interfaces | Swagger
MHHS-DIN-1015 | MF | DIN-999 | 2024-04-18 | UKPN |  | Neil Madley | Network Operator | Update routing for [MPANReconnection] and add event to Opt/In Out Matrix | On IF-009 add LDSO as secondary routed. Add [MPANReconnection] to the Opt In/ Opt Out Matrix so that LDSO's can opt out of receiving this event. |  | Implemented | Error/Correction | LDSOs |  | Interim Release 8.1 |  | On IF-009 added LDSO, SUPC as secondary routed. Added [MPANReconnection] to the Opt In/ Opt Out Matrix so that LDSO's can opt out of receiving this event. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1016 | RG | DIN-1017 | 2024-04-24 |  |  |  |  | REP002 & REP002B require update | Swagger for REP-002 & REP-002B needs to be updated to reflect the defns in ERI011B. REP-002 The ERI011B – ECS Reports spreadsheet has the R027 – Distributor ID as a repeating block, meaning that Suppliers will receive 1 REP-002 for each combination of Distributor and GSP Group. REP-002B Similarly the REP-002B has R009 as a repeating block |  | Implemented | Error/Correction |  |  | Interim Release 7.3 |  | Update swagger to reflect ERI011B | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-1017 | RG | DIN-1016 | 2024-04-24 | Design Team |  | Rob Golding | SRO Design | REP002 & REP002B require update | Swagger for REP-002 & REP-002B needs to be updated to reflect the defns in ERI011B. REP-002 The ERI011B – ECS Reports spreadsheet has the R027 – Distributor ID as a repeating block, meaning that Suppliers will receive 1 REP-002 for each combination of Distributor and GSP Group. REP-002B Similarly the REP-002B has R009 as a repeating block |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update swagger to reflect ERI011B | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-1018 | RG | DIN-1007 | 2024-04-22 | Avanade |  | Rob Golding | SRO Design | Change request body on Validation Endpoints | Avanade have reviewed the 1.7.1. endpoints and are requesting a change so that they are more flexible and align to the submission API |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Avanade have reviewed the 1.7.1. endpoints and are requesting a change so that they are more flexible and align to the submission API | Technical corrrection | Swagger |  | Swagger
MHHS-DIN-1019 | SC | Test Defect 31336/ DIN-966 | 2024-03-27 | Design Team |  | Sean Cooper | SRO Design | Revision to the PUB-004 Secondary routing logic. | SIT DEFECT - 31336 Currently distribution logic states delivery of PUB-004 to SUPC and XMSC. This results in the send of the message (IF-004) being unnecessrily copied in on the PUB-004. Secondary logic should reference sending party and issue to XMSC where sent by SUPC and SUPC where message sent by XMSC. |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | SIT DEFECT - 31336 Currently distribution logic states delivery of PUB-004 to SUPC and XMSC. This results in the send of the message (IF-004) being unnecessrily copied in on the PUB-004. Secondary logic should reference sending party and issue to XMSC where sent by SUPC and SUPC where message sent by XMSC. DIP routing updated as part of IR7 DES138 - IF-004 routing table updated in IR8.1 | Technical corrrection | Supporting Docs | Interfaces | DES138
MHHS-DIN-1020 | RS | DIN-851 | 2024-04-25 | Code |  | Matt McKeon | Central Body | Queries from REC RTS which relate to either DES138 or ERI110B | CD6-320 is pointing out that data item DI-218 has a different name in DES138 (Current Supplier DIP ID) and ERI011B (Daily Supplier MSID Count). CD6-323 is referring to DI-030 and DI-031 in DES138, asking what the distinction is when they have the same name CD6-325 is asking about a data item with the same name but different DI-refs in DES138 (DI-081) and ERI011B (DI-484) |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | CD6-320 - DI-218 no update required not in ERI011B CD6-325 - DI-484 to be corrected to DI-081 in ERI011b - Swagger to also be updated to reflect consistant use of DI-081 | Technical corrrection | Supporting Docs | Interfaces | ERI011B Swagger
MHHS-DIN-1021 | MF | DIN-949 | 2024-04-25 | SCS | 39365 | Daniel Tadecicco | Central Body | Migration Error Code Alignment with DES138 | Update all the error codes in Migration Design Document and Migration Requirements to align with DES138 |  | Implemented | Design misaligned | All Participants |  | Interim Release 8.1 |  | Update Migration requirements doc to align with all DES138 migration error codes and update Migration doc where relevant to reflect the DES138 error codes Updated DES138 error descriptions as follows: REG9010 - Cannot Manage MPAN Relationships for an Unmigrated MPAN REG9002 - Supplier Data Items Cannot be Maintained for an Unmigrated MPAN REG9001 - CDC Marker Cannot be applied to an Unmigrated MPAN Removal of reference to IF-040 and RCP1076 from migration design document | Technical corrrection | Migration | Supporting document | Migration Requirements Log Migration Design Document DES138
MHHS-DIN-1022 | ZH |  | 2024-04-26 | RECCo | 48861 | Sarah Jones | Consultancy | Implementation of CR037 (Migration Message Processing Choreography Update) | Please refer to the CR037 documentation for further details | CR037 | Implemented | Change Request | All Participants |  | Interim Release 8.1 |  | Updated Change of Agent Migration Timings , as per CR037. This includes the Migration Requirements log, Migration Design Document and the E2E non-functional requirements. | Technical corrrection | Migration | Supporting document | Migration Requirements Log Migration Design Document E2E002 - Non-functional requirements
MHHS-DIN-1023 | TR |  | 2024-04-26 | SCS | 46680 | Madison Layton | Software Provider | Meter Location Data Quality | The PUB-005 B033 block is mandatory on all event codes except for [MeterRemoval]. Within this block the Meter Location is mandatory, however F (not known) is permitted. Where MS is updating other MTDs, there is a risk that they will submit Meter Location F ‘not known’ despite Meter Location not having changed. This could lead to poor quality of meter location data within REGS. Potential mitigation could be level 5 validation rule on REGS: if Meter Location held in REGS is not F or null, then DI-090 must not be F. This would ensure Meter Location couldn’t be reverted to F from a previously specified value. |  | Initial Assessment/Updating | Design ambiguous | REGS |  | Post Go-live Release |  | Potential mitigation could be level 5 validation rule on REGS: if Meter Location held in REGS is not F or null, then DI-090 must not be F. This would ensure Meter Location couldn’t be reverted to F from a previously specified value. | Missing/incorrect validation rule | Supporting Docs | Supporting document | DES138
MHHS-DIN-1024 | RG | Test Defect 31491 | 2024-04-26 | Kraken |  | Dave Mclean | Software Provider | Use of Min items =1 to stop arrays with zero items | Messages are being sent with arrays with zero items in, however an array with zero items does not make sense. If minItems is set to 1, then schema validation would not allow arrays with zero items. Also, to improve data validation for nullable strings the minLength needs to be set to 1. |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Add minItems = 1 to array where a zero item array is not allowed, Add to the folllowing objects: B900 B901, B902, B920, B922, B921, B903, B906, B906a, B907, B908, B910, B911, B941 | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-1025 | MF |  | 2024-04-29 | Helix |  | Rashmi Radhakrishnan | Central Body | Update to ISD examples in MHHSP_EDI021_ISD_Entities | Update the examples in M7, M17 and M18 tables to support SIT testing |  | Closed | Design ambiguous | All Participants |  |  |  | Updated the examples in M7, M17 and M18 tables ( MHHSP_EDI021_ISD_Entities v5.7 ) to support SIT testing | Design Ambiguous | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-1026 | RG |  | 2024-04-29 | Kraken |  | Dave Mclean | Software Provider | Remove DT-008 from data types | The request is that as DT-008 is not use can it be removed from the swagger |  | Initial Assessment/Updating | Error/Correction | All Participants |  | Post Go-live Release |  | Remove DT-008 from data types | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-1027 | MF |  | 2024-04-30 | PDA |  | Tom Chevalier via Kevin Spencer | Data Service Provider | Remove reference to UMSDS on Consumption Amendment flow (IF-028) and Opt/In Out Matrix (IF-027) | Currently Consumption Amendment is not utilised by UMSDS so removed reference in the Consumption amendment flows |  | Initial Assessment/Updating | Error/Correction | UMSDS |  | Post Go-live Release |  | Remove UMSDS from "From parties" on IF-028. Updated UMSDS as N/A for IF-027 in Opt/In Out Matrix | Data interface correction | Supporting Docs | Supporting document | DES138
MHHS-DIN-1028 | MF |  | 2024-04-30 | SCS |  | Madison Layton | Software Provider | Update REG1040 description | Update the description for REG1040 to cover both SSC and Profile Class error messages to align with validation rules in IF-025 |  | Initial Assessment/Updating | Error/Correction | Suppliers, REGS |  | Post Go-live Release |  | Update REG1040 to "REG1040 - SSD/ Profile Class Effective From Date must be later than existing" and remove REG1041 in the "Introduction" Tab of DES138 | Data interface correction | Supporting Docs | Supporting document | DES138
MHHS-DIN-1029 | MF |  | 2024-04-30 | SCS |  | Madison Layton | Software Provider | Make B032 block mandatory for [SSCandProfileClass] event in IF-025 and IF-026 | Update Swagger and DES138 to make B032 block mandatory for [SSCandProfileClass] event in IF-025 and IF-026. |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update Swagger and DES138 to make B032 block mandatory for [SSCandProfileClass] event in IF-025 and IF-026. | Data interface correction | Supporting Docs | Supporting document | DES138 & Swagger
MHHS-DIN-1030 | RG | DIN-850 (original IR7 DIN) | 2024-04-30 | Callisto | 50078 | Scott Parkinson | Software Provider | IF037 DSDeApp CustomBlock requires B002 block | Looks as though some of the CR36 changes did not make their way into swagger: the change to include the B002 block in the IF-037 DSDeApp custom block is missing |  | Implemented | Error/Correction |  |  | Interim Release 7.3 |  | Update swagger so that B002 block included in the IF-037 DSDeApp custom block | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1031 | RG |  | 2024-05-01 | EDW Technology | 32016 | Mark Kenny-Jones | Software Provider | Inconsistencies between E2E & Swagger defn of Status Messages | Regarding the SRB that contains empty strings (i.e. the one used to report schema validation errors), are you aware that this does not comply with the current API schema? And if so, are there any plans to either update the schema, or to change the structure of this response so that it does comply with the schema? Specifically, I’m referring to the fact that there are a number of fields in the SRB that have minimum lengths, which an empty string would violate. Similarly, none of the fields are marked as nullable, therefore replacing an empty string with an explicit null value would also violate the schema. Excluding the fields entirely also wouldn’t be an option, as some of the fields are mandatory, and this would also go against the advice in section 4.6.6.2 of the end to end architecture document (E2E001 v3.6) says that “Where a field is not written/available/optional, then a null value needs to be written” |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | The standard Response body has been updated to follow the manadatroy/null design approach. | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1032 | TR |  | 2024-05-01 | ESG |  | Patricia Parker | Software Provider | DI-103-Configurable-Register-ID need to be alpahnumeric | The REGEX in Swagger for DI-103-Configurable-Register-ID which requires numeric values only, the data element should just be a string(2), as per DES-138, to allow numeric or aphla characters. |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update Swagger so the data element is string(2) to allow for numeric and alpha characters | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1033 | MF |  | 2024-05-01 | Helix |  | Rashmi Radhakrishnan | Central Body | Updates to ISD M17/ M7 tables | Updated ISD M17 to add in Meter Group as Char 11 to align with M7 Meter Group. Added allowable values to cover Unmetered in M7 |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated the M17 table to include Meter Group as Char 11. Added Unmetered to Meter Group in both M7 and M17. Updated Meter Type in M7 to “Mandatory. Valid Set as per EMAR1 or U for Unmetered” | Design Ambiguous | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-1034 | RG |  | 2024-05-03 | SCS | 50636 | Mariana Mesaros | Software Provider | REP900 & RE901 are missing schema version ERI011B spreadsheet | REP900 & RE901 are missing schema version in S0 block in ERI011B spreadsheet. The swagger has the schema version |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated ER0I011B with schema version for REP-900/1 | Data interface correction | Supporting Docs | Interfaces | ERI011B
MHHS-DIN-1035 | RG | DIN-850 (original IR7 DIN) DIN-1030 (7.3 DIN) | 2024-04-30 | Callisto | 50078 | Scott Parkinson | Software Provider | IF037 DSDeApp CustomBlock requires B002 block | Looks as though some of the CR36 changes did not make their way into swagger: the change to include the B002 block in the IF-037 DSDeApp custom block is missing |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update swagger so that B002 block included in the IF-037 DSDeApp custom block | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1036 | RG |  | 2024-05-09 | Avanade |  | Ptior Penar | Software Provider | DI-432-Period-Metering-System-Metered-Data requires clarification | DI-432-Period-Metering-System-Metered-Data need to remove multiplier constraint |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update swagger DI-432 | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1037 | RG |  | 2024-05-10 | St Clements | 50045 | Vicki Holland/Tom Perryman | Software Provider | REP900 Changes | Changes to be made to the REP900 are: • REP900-03 to be a parent of REP900-04 • Delete data item DI-563 (LDSO Billing Account Reference) as it is redundant with Site Id and Invoice Number also included in the message • Move the following data items to REP900-04 as they can all change for a site and are specific to the invoice raised: - 612 (Site DUoS Tariff ID), 566 (List of MPANs), 567 (Misaligned multi MPAN site), 568 (Site Capacity) • Update DI-565 LDSO Billing Site ID to data type of String(30) • Add GSP Group ID to the REP900-03 site record |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updates to Swagger & ERI011B | Data interface correction | swagger | Interfaces | Swagger/ERI011B
MHHS-DIN-1038 | MF | DIN 973 | 2024-05-10 | ESG |  | Patricia Parker | Software Provider | Clarify Migration Reqs re D0312 | Requirment updated to refeclt that IF-035 with Lapsed Reason Code of LP001 (MPAN Disconnected/deRegistered) will be issued for any Pending Service Provider Appointments on receipt of MPAN termination (not D0312) |  | Implemented | Error/Correction | REGS |  | Interim Release 8.1 |  | Remove reference to D0312 in the note added to REGS Migration Requirement MHHS-Migration-Can-RS-006 as it is triggered by receipt of a termination of the MPAN from the LDSO following receipt of D0132 | Requirement correction | Migration | Supporting document | Migration Design Requirements
MHHS-DIN-1039 | MF | DIN-946 | 2024-05-10 | ESG |  | Patricia Parker | Software Provider | Update Lapse codes scenario's in DES138 | update DES138 (IF-035) to show LP004 can also apply to MCS scenario and LP006 would only apply to MCA scenario |  | Open - awaiting assessment | Error/Correction | All Participants |  | Post Go-live Release |  | update DES138 (IF-035) to show LP004 can also apply to MCS scenario and LP006 would only apply to MCA scenario | Data interface correction | Supporting Docs | Supporting document | DES138
MHHS-DIN-1040 | RG |  | 2024-05-15 | Kraken | 52894 | Dave MaClean | Software Provider | Migration Deisgn: Missing B095 block in IF-003-MSDeAppRM & missing B096 block in IF-003-DSDeAppRM | Ticket noticed B095 is missing from the IF-003-MSDeAppRM variant. On closer inspection the B096 is also missing from the IF-003-DSDeAppRM |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Both DES138 and the Swagger both need updating: Missing B095 block in IF-003-MSDeAppRM & missing B096 block in IF-003-DSDeAppRM | Data interface correction | Supporting Docs | Interfaces | DES138 & Swagger
MHHS-DIN-1041 | RG |  | 2024-05-16 | MHHS |  |  |  | Alignment of DES138 to message version numbers | The message version numbers in DES138 need to be aligned to the swagger versions, ie. version '011' for release 7.x. Also align IF-061/5 to the other interfaces |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update DES138 to the correct version, update swagger for IF-061/If-062/If-063/IF-064/IF-065 to version '011' so consistent with other IFs |  |  |  | DES138 & Swagger
MHHS-DIN-1042 | RG |  | 2024-05-17 | Kraken | 52894 | Dave MaClean | Software Provider | DI-830 (B070) Swagger/ DES138 descrepancy | The MeteringServiceDIPEffectiveFromDate is from the Data Catalogue on DES138. In the defn of the B070 block the term proposedMeteringServiceEffectiveFromDate is used (ana probabaly the better term to use). However, too late to change, so an update to DES138 to align the B070 to the DC/Swagger is required |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | Update B070 block in DES138 to align with swagger/data catalogue | Data interface correction | Supporting Docs | Supporting document | DES138
MHHS-DIN-1043 | RS |  | 2024-05-21 | Siemens | 53765 | Tony Mason | Metering Service Provider | Method Statement where site is disabled | Method 12 in both SDS and ADS Method statement documents should state the reason code as Disabled, looks like currently a cut & paste from method 11 |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | METH001 (SDS) and METH002 (ADS) to be updated with the following for Method 11 & 12 (replacing SDS with ADS for METH002 - also amending 'Site' to lower case Method 11. Estimation for Long Term Vacant Sites Where the Supplier has notified a Flag to identify that a site is LTV and in cases where no access to consumption data is available, then in the presence of this flag the SDS will estimate zero and set a LTV estimation reason code. This data will be recorded as “ZE2” and the estimation reason code ‘LTV’ should identify as LTV. UTCPDj = 0 Method 12 Estimation where a site where Supply is disabled Where the Supplier has notified a Flag to identify a site where the supply is disabled and in cases where no access to consumption data is possible, then in the presence of this flag the SDS will estimate zero. This data will be recorded as “ZE3” and set the estimation reason code ‘Disabled’. | Method statement correction | Supporting Docs | Supporting document | METH001 METH002
MHHS-DIN-1044 | RG |  | 2024-05-23 | ESG | 54979 | Kerry O'Donnel | Software Provider | IF-009-MPANReconnection has incorrect event code | The event code for IF-009-MPANReconnection need to be [MPANReconnection] rather than [MPANDReconnection] |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | The event code for IF-009-MPANReconnection need to be [MPANReconnection] rather than [MPANDReconnection] | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-1045 | RG |  | 2024-05-29 | SRO |  | Rob Golding | SRO Design | Tidy up of routing rules for IF-041 | The routing rules table for IF-041 requires updating |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | The second and third rows in the routing table in DES138 need to be merged. | Data interface correction | Supporting Docs | Supporting document | DES138
MHHS-DIN-1046 | RS |  | 2024-06-04 | SRO |  | Matt McKeon | SRO Design | Clarifications to the ECS DTN Reports | Retrospective changes made to D0397 - MHHS Supplier Half Hourly Demand Report (now v1.2) D0401 - MHHS Aggregated Disconnected DUoS Report (now v1.1) D0402 - MHHS Supplier Half Hourly Demand Disconnection Report (now v1.1) D0403 - MHHS GSP Group Demand Disconnection Totals Report (now v1.1) D0404 - MHHS Supplier BM Unit Demand Disconnection Report (now v1.1) |  | Implemented | Error/Correction |  |  | Interim Release 7.3 |  | D0397 - Updated the Range of Group 02Z ‘Daily Totals Per Suppler’ from ‘1-1’ to ‘0-*’ D0401 - Amended MM Description to say “A report of Disconnected Volumes by Distributor. Where the report is sent to the Distributor it will contain data for all Suppliers impacted by the Demand Control Event, whereas where it is sent to the Supplier it will only contain data pertaining to that Supplier.” - Renamed DI20306 ‘DUoS Daily Supplier Demand Disconnection Volume’ to ‘DUoS Daily Smart and Unmetered Demand Disconnection Volume’ - Renamed DI20307 ‘DUoS Daily Supplier Demand Disconnection Volume Losses’ to ‘DUoS Daily Smart and Unmetered Demand Disconnection Volume Losses’ - Renamed DI20310 ‘DUoS Supplier Demand Disconnection Volume’ to ‘DUoS Smart and Unmetered Demand Disconnection Volume’ - Renamed DI20311 ‘DUoS Supplier Demand Disconnection Volume Losses’ to ‘DUoS Smart and Unmetered Demand Disconnection Volume Losses’ - Updated the Range of Group 79J ‘Demand Control Event Details‘ from ‘1-*’ to ‘1:1’, so that one report is produced per DDE. D0402 - MHHS Supplier Half Hourly Demand Disconnection Report (now v1.1) - Updated the Range of Group 04K ‘Demand Control Event Details‘ from ‘1-*’ to ‘1:1’, so that one report is produced per DDE. D0403 - Updated the Range of Group 36K ‘Demand Control Event Details‘ from ‘1-*’ to ‘1:1’, so that one report is produced per DDE. D0404 - Updated the Range of Group 43K ‘Demand Control Event Details‘ from ‘1-*’ to ‘1:1’, so that one report is produced per DDE. | Technical corrrection | Supporting Docs | Supporting document | D0397 - MHHS Supplier Half Hourly Demand Report D0401 - MHHS Aggregated Disconnected DUoS Report D0402 - MHHS Supplier Half Hourly Demand Disconnection Report D0403 - MHHS GSP Group Demand Disconnection Totals Report D0404 - MHHS Supplier BM Unit Demand Disconnection Report
MHHS-DIN-1047 | MF | DIN-934 | 2024-06-04 | SCS |  | Daniel Tadecicco | Central Body | Additional value of U for Energisation Status used during Migration | Add new valid value of U - Undefined to DI-033 to allow a value to be populated during Migration. This will be updated with the actual Energisation Status at the stage the IF-036 is issued and the value has been set in Registration Service |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Add U - Undefined as an allowable value to be used for Energisation Status during Migration in DI-033 for IF-001, IF-002 and IF-033 in DES138/ swagger. Participants will be updated with the actual Energisation Status when the IF-036 is issued. Remove U as an allowable value from DI-033 in IF-007 in DES-138. | Data interface correction | Supporting Docs | Interfaces | DES138 & Swagger
MHHS-DIN-1048 | ZH |  | 2024-06-04 | MHHS |  | Zakir Hussain | Consultancy | BRS002 requirements typo | Business Requirements MHHS-BR-MS-071.1 and MHHS-BR-MS-071.2 should be documented within MHHSP-BRS002-Metering Service requirements v5.6 and should apply to both the MSS and MSA Roles. Unfortunately, there is a typo in the Bus Requirement and these are currently showing as DS versions in 3 tabs (all, MSS and MSA) i.e. MHHS-BR-DS-71.1 and MHHS-BR-DS-71.2 which is not aligned to the naming convention around them. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update BRS002-Metering Service Requirements - Change requirement "MHHS-BR-DS-071.1" and "MHHS-BR-DS-071.2" to "MHHS-BR-MS-071.1" and "MHHS-BR-MS-071.2" | Requirement correction | All Areas | Requirements | MHHSP-BRS002
MHHS-DIN-1049 | ZH |  | 2024-06-04 | MHHS |  | Zakir Hussain | Consultancy |  | An exemption has been made in the Qualification process for certain Suppliers. Essentially if a Supplier commits to never supplying Unmetered MPANs they do not have to undertake the qualification tests pertaining to unmetered MPANs – largely as they would have to build capability they would never use. Could I therefore request a DIN be raised to add the following the Supplier Requirements set: · a Supplier not Qualified for UMS shall not migrate UMS MPANs into the new MHHS arrangements. · a Supplier not Qualified for UMS shall not register UMS MPANs in the new MHHS arrangements. This will allow traceability in Qualification assurance to allow qualifying bodies to ask suppliers what controls they have in place to restrict this. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Add the following the Supplier Requirements set: · a Supplier not Qualified for UMS shall not migrate UMS MPANs into the new MHHS arrangements. · a Supplier not Qualified for UMS shall not register UMS MPANs in the new MHHS arrangements. | Requirement correction | All Areas | Requirements | Supplier Requirements Doc
MHHS-DIN-1050 | RG | DIN-211 | 2024-06-06 | SRO |  | Rob Golding | SRO Design | B042 - DI-077 Naming descrepancy | DES-138 has DI-077 named as DI-077-CSS-RMP-DeActivation-Date whilst in swagger the corresponding filed name is CSSMPANDeRegistrationDate. Normally the two should align |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | In swagger th ename of the field is incorrectly titled "CSSMPANDeRegistrationDate". The least change approach is to update DES | Technical corrrection | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-1051 | TR |  | 2024-06-11 | Design Team |  | Tamsyn Robertson | SI Design | MHHS-REP-002B Description Field Update | The Description field in the REP-002B spec is not correct. The reference to Suppliers needs to be removed. The 'To Parties' and 'Routing Rules' are correct. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Change 'Description' field in DES-138 to: 'The report provides aggregated Distribution Use of Systems data for LDSOs or Suppliers in Clock Time.' | Document Correction | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1052 | TR |  | 2024-06-11 | Design Team | 57348 | Tamsyn Robertson | SI Design | ISD entity M2- Typo | The latest version of the ISD spec currently lists M2 - Connection Type Description H as "High Voltage with Current transformer" with a lowercase "t" in "transformer.". BSCP707 Appendix 1 and Appendix 2 has been updated, so this DIN is to align with the correction to the code. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update M2 - Connection Type Description H to: "High Voltage with Current tTransformer" | Document Correction | Supporting Docs | ISD | EDI021 ISD Entities
MHHS-DIN-1053 | TR |  | 2024-06-11 | Opus | 56809 | Lee Eltherington | Supplier | D0397 - Consumption Component Indicator | The Data Item List at the top of the D0397 PDF does not contain the Consumption Component Indicator field that is showing in the dataflow structure. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update the D0397 document to include the Consumption Component Indicator and link to J0162. | Document Correction | Supporting Docs | D-Flow Documents | D0397
MHHS-DIN-1054 | TR |  | 2024-06-11 | ESG | 57833/58471 | Patricia Parker | Software Provider | D0149 - Missing SV | Updates required for the D-flow documentation |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Need all three scenario variants (smart to smart, legacy to smart and smart to legacy). in DTC. Possible error in both the D0149 and D0150. | Document Correction | Supporting Docs | D-Flow Documents | DTC D0149 D0150
MHHS-DIN-1055 | RG |  | 2024-06-12 | Kraken | 58587 | Dave Maclean | Software Provider | IF-006 S0 block missing required properties | InterfaceID, schemaVersion & eventCode fields should be marked as required on the S0 block on the IF-006 interface |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Add required fileds to S0 blocks in all IF-006 variants - InterfaceID, schemaVersion & eventCode | Technical corrrection | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-1056 | RG |  | 2024-06-26 | Avanade |  | Gaurav Agrawal | Software Provider | R900-04 block remove LDSOBillingSiteID from required list | The R900-04 block still has LDSOBillingSiteID in the required parameters - it needs to be removed |  | Open - awaiting assessment | Error/Correction |  |  | Interim Release 8.2 |  | Remove LDSOBillingSiteID from required field in R900-04 | Technical corrrection | Supporting Docs | Swagger | Swagger
MHHS-DIN-1057 | RG |  | 2024-06-26 | SRO Design | 61939 | Rob Golding | SRO Design | DIP L3 webhook response time set to 10 secs | The DIP timeout on a synchronous response was set to 5 seconds, this will be updated to align with the NFRs |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update E2E SA document & requirements with value | Technical corrrection | Supporting Docs | E2E001, E2E002 | E2E001, E2E002
MHHS-DIN-1058 | SB |  | 2024-06-26 | SCS | 62087 | Madison Layton | Central Body | DI-260 Missing MDR and Consent Granularity in MHHS-BR-RS-074 | The Registration Service Requirements is missing the requirement to apply MDR and Consent Granularity to related secondary MPANs when confirming a new Data Service Appointment on a Primary MPAN. Suggested uplift below in red. Detail shown on the Fresh Desk Ticket |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update MHHS-BR-RS-074 | Requirement correction | All Areas | Requirements | REGS Requirements
MHHS-DIN-1059 | RG |  | 2024-06-26 | EDW Tech | 62837 | Kavita Siddle | Central Body | IF-020-RelatedCreate has two unwanted Event Codes | IF-020-RelatedCreate has two unwanted Event Codes [RelatedAdd] and [RelatedRemove]. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Remove the two unwanted Event Codes from the IF-020-RelatedCreate message variant in swagger. Shouldn't affect testing as the messages resove to the same structure | Technical corrrection | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-1060 | RG |  | 2024-06-28 | Avanade |  | Piotr Penar | Software Provider | API Key changes: Add MSG1015 to list of acceptable error codes | Add "MSG1015: X-API Key does not match the sender" error message to Introduction tab on DES-138 and swagger |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update DES138 to include the the new error condition where API key doesn't belong to message sender | Technical corrrection | Supporting Docs | Swagger | DES138 Swagger
MHHS-DIN-1061 | RG |  | 2024-07-01 | Avanade |  | Gaurav Agrawal | SRO Design | Add MSG1039, MSG1040, MSG1041 to list of acceptable error codes | MSG1039:Invalid MPAN MSG1040:Not currently appointed MSG1041:MPAN not known |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update DES138 to include the the new error conditions | Technical corrrection | Supporting Docs | Interfaces | DES138
MHHS-DIN-1062 | RG |  | 2024-07-03 | Wheatley Solutions |  | Chris Mingay | Software Provider | Connection requests are missiing a User Agent which occassionally trigger FW rule | Add User Agent Header to DIP http requests so that identification is clear on interfacing sysems. Avanade ADO ticket no 42340 |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update CoCo (E2E) to add new http header info | Other | All Areas | End to End Documentation | E2E Code of connections document
MHHS-DIN-1063 | TR |  | 2024-07-05 | Helix | 65874 | Riccardo Lampini | Central Body | Measurement Quantity Naming Convention | There are inconsistencies with the use of Measurement Quantity/Measurement Quantity ID within 3 entities as per the ISD Entity Spec and this is not aligned with Swagger/MDS Method Statement |  | Open - awaiting assessment | Error/Correction |  |  | Interim Release 8.2 |  | Update ISD Entity spec, MDS Method Statement to align the terminology with what is used in Swagger. MHHS Both Consumption Component Classes, Load Shape Categories to state 'Measurement Quantity ID'. This is correct in the Measurement Quantity Entity | Document Correction | Supporting Docs | ISD | EDI021 ISD Entities, MDS Method Statement
MHHS-DIN-1064 | TR |  | 2024-07-05 | CGI | 62573 | Dave Webster | Software Provider | PUB-045 for UMSDS | According to DES138 5.8.2 sheet 04_IF_OptOut_Matrix, UMSDS can opt out of receiving an IF-045 [InvalidMarketSegment] message. However, according to sheet 02_IF-045, a UMSDS is not a valid recipient of an IF-045. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update 04_IF_OptOut_Matrix to remove UMSDS from IF-045 [InvalidMarketSegment] | Technical corrrection | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1065 | SB |  | 2024-07-09 | RECCo | 66065 | Jonny Moore | Central Body | Energisatio |  |  | Open - awaiting assessment
MHHS-DIN-1066 | MF |  | 2024-07-10 | EoN |  | Cathy Mulliss | Supplier | Clarification on requirments for maintaining Customer and PSR data by the Data Service | Clarify that the Data Service only has to maintain Customer and PSR data where the data is provided by the Supplier. If the Supplier and Data Service have bilateral agreements whereby this is not required then this data does not have to be shared by the Supplier and maintained by the Data Service . |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | A clarification has been issued as part of the Knowledge Base that Suppliers can make bilateral agreements with Data Services and Meter Reading Services for the provision of meter readings to the Data Service. Where the Data Service does not require Customer/ PSR data to meet their obligations for providing data to Settlements, the Supplier can elect not to share Customer and PSR data to the Data Service. Minor tweak to the requirments to make it clear that this information is only shared and maintained where required. | Document Correction | Meter to Bank | Data Service requirments Supplier Overview | BRS001 BRS004
MHHS-DIN-1067 | RG |  | 2024-07-12 | CGI | 67334 | Chris Beard | Software Provider | Ensure Correlation Id information in E2E001 E2E SA doc aligns to DES138 | Reviewing the E2ESA doc the corrleation Id info need to relect the infromation in DES138 |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Minor update to E2ESA doc | Document Correction |  |  | E2E001
MHHS-DIN-1068 | RG |  | 2024-07-12 | Avanade |  | Piotr Penar | Software Provider | Make the elements of the CommonBlock.S0 mandatory | At present the 3 elements of the S0 block: Interface Id Schema Version Event Code are not marked as mandatory. Marking them as mandatory would block issues with missing fields at schema validation rather than causing the DIP to error |  | Open - awaiting assessment | Error/Correction |  |  | Interim Release 8.2 |  | Add required attributes to all S0 blocks to include the 3 fields (inerfaceId, eventCode & schemaVesrion). Zero impact on PPs as not a structural change | Technical corrrection | Supporting Docs | Swagger | Swagger
MHHS-DIN-1069 | RG |  | 2024-07-18 | Imserv | 68171 | Liam Lowey | Software Provider | Removal of oneOf statements in Swagger to faciliate validation at endpoints | The oneOf statement used in the design of the DIP mesages proves to be an issue for using the swagger to validate with the current endpoint definition. Steps could be made to introduce a version alongside the existing one that removes the oneOfs. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | This could be achieved by PPS having endpoints defined for each IFor PUB Event Code combination as per the new valdiation endpoints | Change Request | Swagger/DIP |  | Swagger
MHHS-DIN-1070 | RG |  | 2024-07-18 | C&C | 67972 | Graham King | Software Provider | Provide replay of status messsages | Request to provide Replay facility for Status Messages |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Woudl need to go into the Avanade backog and be prioiritised accordingly | Change Request | Swagger/DIP |  | Swagger
MHHS-DIN-1071 | MF |  | 2024-07-19 | SCS | 66166 | Daniel Tadecicco | Central Body | Clarification on when migration appointments are lapsed | Migration appointments will only be lapsed following an MPAN being confirmed as CSS de-activated. This is in line with MHHS BAU operation as outlined in MHHS-BR-RS-103. Therefore, MHHS-Migration-Can-RS-006 is redundant and Migration Design should be aligned to the MHHS BAU operation. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Remove MHHS-Migration-Can-RS-006 and clarify migration design (section 6.1.1 bullet 13) aligns to MHHS BAU operation for CSS de-activated MPANs. | Document Correction | Migration | Migration design and requirements | Migration Requirements Log Migration Design Document
MHHS-DIN-1072 | TR |  | 2024-07-22 | Helix | 67485 | Rashmi Radhakrishnan | Central Body | Domestic Premise Indicator Data Type | Data type currently states Boolean but also optional. Needs correcting to allow for null, T and F values |  | Open - awaiting assessment | Error/Correction |  |  | Interim Release 8.2 |  | Update Data Item to Char(1) optional. | Document Correction | Supporting Docs | ISD | ISD Entities Document Swagger DES-138 METHXXX
MHHS-DIN-1073 | SB |  | 2024-07-23 | RECCo | 66065 | Jonny Moore | Central Body | Energisation Status Enumerations | While reviewing the changes made to DES138 for IR8.1 we’ve noticed a discrepancy around the new value of U introduced to the energisation status through DINs 934 and 1047. While the new enumeration has been added in the population notes for the IFs where it will be used, the enumerations held in the data item catalogue have not been updated. As the Energy Market Data Specification (EMDS) stores the enumerations against the data item not the data population rules, we will need this added to the data item catalogue in order for it to be reflected in the EMDS valid set. Without this the value of U will not be a valid value at go-live. Please can the data item within the DES-138 Data Item Catalogue be updated appropriately so we can reflect this in code drafting. |  | Open - awaiting assessment
MHHS-DIN-1074 | PP |  | 2024-07-24 | St Clements | 69275 |  | Central Body | DI-262 B013 CSS Registration ID Block Optionality in Swagger | We’ve spotted an error in implementing DES-138 B013 optionality in swagger. In DES-138 the B013(CSS Registration ID) block optionality is mandatory if available on a series of DIP messages This has been interpreted to mean the block is optional in swagger for a number of the messages. However, for most of the DIP messages the CSS Registration ID is always available and therefore mandatory. The B013 block must be mandatory on the IF-025 IF-031 IF-034 The CSS Registration ID is always available to the Supplier and the Service Provider would always receive a CSS Registration ID in the IF-033 from MPRS. The CSS Registration ID is necessary for the processing of these messages in MPRS. The B013 block should then also be mandatory on the subsequent messages from MPRS namely: IF-026 IF-032 IF-033 IF-035 IF-036 IF-037 It is already mandatory on the IF-001 and IF-002 from MPRS in both DES-138 and Swagger. And for IF-018 the B013 CSS Registration ID block must remain as optional in swagger/mandatory if available in DES-138. IF-018 messages can be generated for MPANs that are not yet registered, and as such no CSS Registration ID would exist for the MPAN. |  | Open - awaiting assessment |  |  |  | Post Go-live Release
MHHS-DIN-1075 | PP |  | 2024-07-24 | St Clements | 69259 |  | Central Body | DI-261 - Level 5 Validation that proposed MS/DS is valid in ISD on EFD | Hi Design Team, We’ve raised DI-261. MPRS currently validates as a level 4 rule that the proposed MS/DS is valid in ISD at the point of receipt of the PUB-031 but there is no validation that the proposed MS/DS is valid on its proposed EFD. For this MPRS would need to validate as a level 5 validation rule. We’ve raised a change for MPRS to validate MS/DS for their proposed EFD and to use REG1081 as this is the closest matching rule in DES-138 currently. DES-138 needs uplifting to amend REG1081 to apply more generally to MDR, MS and DS. |  | Open - awaiting assessment
MHHS-DIN-1076 | TR |  | 2024-07-30 | Programme |  | Tamsyn Robertson | SI Design | ISD Entities Updates | Minor errors in the entties spec to be corrected for completeness. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | M17 - Valid /Consent Granularity Combinations is the title - should be updated to remove "/" - this aligns with BSCP707 drafting M18 - Market Participant Role Code N/A in example should be null. DIP Market Role "LDSO" = DIP Role Description "Licenced Distribution System Operator " not "Licenced Distribution System Operation". DIP Market Role "UMSO" = DIP Role Description "Unmetered Supplies Operator " not "Unmetered Supplied Operator". | Document Correction | Supporting Docs | ISD | ISD Entities Document
MHHS-DIN-1077 | RG |  | 2024-07-30 | Design |  | Paul Pettitt | SI Design | Missing 'II' value in the enumerated field for Di-160 | the 'II' run indicator value list needs to be included in the enumerated list |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | There is currently a workaroind inplace by C&C where they added II to their local enumerated list, but ultimately the list should include II '- II - Interim Information - SF Initial Settlement - R1 First Reconciliation - R2 Second Reconciliation - R3 Third Reconciliation - RF Final Reconciliation - DR Dispute - DF Final Dispute | Technical corrrection | Supporting Docs | Interfaces | DES-138, Swagger
MHHS-DIN-1078 | TR |  | 2024-08-01 | EDW Tech | 67808 | Alexandre Townsend | Software Provider | REP-002 event code correction | REP-002 event code This has an event code of “[DUOSSupplierAggData]”, but the ECS Reports document says the event code is “[DUoSSupplierAggData]” with a lower case o in DUoS. The Dip simulator also expects the lower case spelling. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | [DUOSSupplierAggData] is the correct representation of the event code - update ESC Reports document | Document Correction | Supporting Docs | ESC Reporting | ESC Reports Document
MHHS-DIN-1079 | TR |  | 2024-08-06 | CGI | 70601 | Dave Webster | Software Provider | Sources of Correlation ID | There are a number of Correlation IDs which are created, but I can’t spot where they are subsequently used. IF-003 [ReverseMigNotification] IF-003 [MSDeAppRM] IF-003 [DSDeAppRM] IF-020 [LinkedImportExportCreate] IF-020 [LinkedImportExportAdd] IF-020 [LinkedImportExportRemove] IF-037 [MSDeApp] IF-037 [DSDeApp] IF-065 [MDRInstantaneous] IF-065 [MDRTOU] IF-065 [MDRConsumption] |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update DES-138 Correlation ID Created field IF-003 [ReverseMigNotification] > No IF-003 [MSDeAppRM] > No IF-003 [DSDeAppRM] > No IF-020 [LinkedImportExportCreate] this will contain either the PUB-019’s correlation ID if provided, or in absence of that it’ll contain an LDSO or MPRS generated correlation ID IF-020 [LinkedImportExportAdd] this will contain either the PUB-019’s correlation ID if provided, or in absence of that it’ll contain an LDSO or MPRS generated correlation ID IF-020 [LinkedImportExportRemove] this will contain either the PUB-019’s correlation ID if provided, or in absence of that it’ll contain an LDSO or MPRS generated correlation ID IF-037 [MSDeApp] > No IF-037 [DSDeApp] > No IF-065 [ReadingRemote] > No/Copy | Technical corrrection | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1080 | RG |  | 2024-08-07 | Kraken | 71005 | Angelos Rizoyannis | Software Provider | Request for DIP API to provide message acceptance information | To provide an API that we can query with a list of transaction IDs and/or Sender Unique Reference numbers, including the status of the messages and whether they were accepted by DIP or not. |  | Open - awaiting assessment | Change Request |  |  | Post Go-live Release |  | Solution yet to be defined | Technical corrrection | Supporting Docs | Swagger | Swagger
MHHS-DIN-1081 | TR |  | 2024-08-07 | MDS |  | Vicky Gosar | Central Body | MDS/VAS Method Statement Misalignment - EA12 Flag | MDS method statement refers to ‘E12’ flag while handling missing data. But this ‘E12’ flag doesn’t exist in the CCCs table in VAS method statement. Instead, VAS method statement has reference to ‘EA12’ flag. These need to be aligned - EA12 is correct and aligned to code drafting. |  | Open - awaiting assessment | Error/Correction |  |  | Interim Release 8.2 |  | Update Section 9 of MDS Method Statement to update 'E12' to 'EA12'. For clarity, 'EA12' is the correct representation for this flag | Document Correction | Supporting Docs | MDS Method Statement | METH007
MHHS-DIN-1082 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | Most DIP IDs have enumeration as ISD. However DI-108 has ‘no’ enumeration DI-834 has ‘no’ enumeration DI-847 has a blank enumeration. DIN needed to reflect ISD in enumerations column for these 3 data items. |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update data items: DI-108, DI-834 and DI-847 with the correct enumeration as ISD states that they do have values, whereas DES-138 states they don't (Data catalogue tab) | Technical corrrection | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1083 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-218 current supplier DIP ID has MHHS data type DT-027 which is the data type for MPID. The actual format is correct. DIN needed to correct data type to DT-006. |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update DI-218 data type to "DT-006" rather than "DT-027" | Technical corrrection | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1084 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | Swagger data catalogue doesn’t appear to have DI-218 or 219. DIN to be raised – swagger only change |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update Swagger to include DI-218 and DI-219 from DES-138 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-1085 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-017 Consent Granularity is missing two enumerations in DES138: x # obfuscated value #DIN-858 #- null # DIN-729 need to add null DIN to be raised for additional enumeration x to the list and also to classify Consent Granularity as mandatory nullable |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update DES-138, Data item: DI-017 to include "X" as this is a missing enumeration | Technical corrrection | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1086 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-021 / 22 Customer Direct Contract Metering / Data Service is Boolean. DES138 provides the example Y, Swagger provides example True. The EMDS standards doc defines Boolean as a true or false so assume this should be T or F. DIN to be raised to clarify the examples in both DES138 and Swagger. Not impacting code drafting as this correctly references T/F DI-030 Domestic Premise Indicator - is Boolean. DES138 provides the example T, Swagger provides example True. The EMDS defines Boolean as T or F so swagger example is incorrect. DIN to be raised to clarify the example in Swagger. DI-031 – Load Shape Domestic Premise Indicator – same as above. DIN to be raised to clarify the example in Swagger. EMDS is correct DI-837 Supplier Proposed Domestic Indicator is Boolean but Swagger has example as False. DES138 correctly lists T – Domestic and F – Non Domestic |  | Open - awaiting assessment | Clarification - No change required |  |  | TBC |  | Clarify Boolean data types examples used in swagger and DES-138, example: DI-021 and DI-022 show "Y" in DES-138 and "true" in swagger. Others also highlighted include: DI-030, DI-031, DI-837 | Technical corrrection | Supporting Docs | Interfaces | DES-138 Swagger
MHHS-DIN-1087 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-046 Load Shape Day Total has an MHHS Data Type of DT-016 in swagger. This is missing from DES138 but may not be an issue as not all data items have an MHHS data type. DIN to be raised to add data type DT-016. |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update DI-046 to include the data type "DT-016" to align with swagger | Technical corrrection | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1088 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-059 Meter Type lists the enumerations in swagger. DES138 points to ISD. Believe Swagger shouldn’t have the enumerations. DIN to be raised to update swagger to avoid future dual governance |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update swagger to remove enumeration values and to point to ISD, as per DES-138 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-1089 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-080 Consumption Component Indicator has two enumerations in swagger C and L. No enumerations in DES138 however this is an existing data item which also has M (Metering System Specific Line Loss) as an enumeration. DIN to be raised to add missing enumerations to swagger |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update data item: DI-080 to include "M" as an enumerated value in swagger and DES-138 | Technical corrrection | Supporting Docs | Interfaces | DES-138 Swagger
MHHS-DIN-1090 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-094 Reading Method has totally different enumerations in swagger compared to DES138 DIN to be raised to confirm which is correct |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update DI-094 enumeration values in DES-138 to match swagger. | Technical corrrection | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1091 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-126 Traditional / Fall Back Read Frequency is missing two enumerations in DES138: DIN to be raised to add x as an enumeration in DES138. No issue with the null value as the DI is mandatory nullable - x # Obfuscated value #DIN-858 - null # - DIN-476 - change for nullable enumeration |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update DI-126 with enumeration values from swagger. | Technical corrrection | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1092 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-800 Service Provider Appointment Scenario has a missing enumeration in DES138: xxx # Obfuscated value #DIN-858 DIN to be raised to add xxx as an enumeration in DES138. |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update DI-800 enumeration values in DES-138 to match swagger. | Technical corrrection | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1093 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-819 De Appointment Reason Code lists the enumerations in swagger. DES138 points to ISD. Believe Swagger shouldn’t have the enumerations. DIN to be raised to update swagger to avoid future dual governance |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update swagger to remove enumeration values and to point to ISD, as per DES-138 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-1094 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-838 – Supplier Proposed Consent Granularity has a missing enumeration in DES138: xxx # Obfuscated value #DIN-858 DIN to be raised to add xxx as an enumeration in DES138. |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update DI-838 enumeration values in DES-138 to match swagger. | Technical corrrection | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1095 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-979 Response code has a missing enumeration in DES138: xxx # Obfuscated value #DIN-858 DIN to be raised to add xxx as an enumeration in DES138. |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update DI-979 enumeration values in DES-138 to match swagger. | Technical corrrection | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1096 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-999 Event Code – DES138 is min 3, max 50. Swagger is min 1, max 50. DIN needed to correct DES138 |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update DI-999 min and max values in DES-138 to match swagger. | Technical corrrection | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1097 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DT-016 MHHS data type has been defined differently in ECS and DES138. Is 9,3 string 13 or 14. DIN to be raised to align the definition or specify these as different data types. Note the example in swagger is 789.000 which aligns to neither. |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Solution yet to be defined
MHHS-DIN-1098 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DT032 data type differs in ECS RC compared to swagger. DIN to be raised against data type 032 which states it is string 18 but the example includes 17 characters: -nnnnnnnnn.nnnnnn. The example in swagger is completely different: -10987654321.12 which is string 15. |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Solution yet to be defined
MHHS-DIN-1099 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-545 – Distributor Bank Sort code is string 8 with an example of 6 characters in ECS RC but max 10 in swagger. DIN to be raised to align |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Solution yet to be defined
MHHS-DIN-1100 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-083 BSC Settlement Period Quality Indicator – different enumerations in ECS RC compared to DES138. We have used DES138 which has the fuller set. Din to be raised to add missing enumerations to swagger |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Solution yet to be defined
MHHS-DIN-1101 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | IF003 – aligned although there is a lack of clarity in the B095 and B096 block which don’t say the events they are used in. Swagger has the B095 just for MSDeAppRM and B096 just for DSDeAppRM |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Solution yet to be defined
MHHS-DIN-1102 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | IF013 – Swagger refers to B920 list which is not referenced in DES138. In the swagger common block B920 is defined. This references the B050, B046 and B048 blocks which makes sense but also references B045. B045 just includes Measurement Quantity Id (DI-052) which is on B050 in the IF013. Suggest raising DIN seeking confirmation on whether the B045 is needed as a separate block in the IF013. |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Solution yet to be defined
MHHS-DIN-1103 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | IF016 has an event of consumption request rejected. This is not mentioned against any blocks in DES138 but there is a statement against B067 and B046 that its mandatory except replay request rejected – suggest the latter is an error in DES138 and should say ‘mandatory except consumptionrequestrejected |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Solution yet to be defined
MHHS-DIN-1104 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | IF034 DS App event in swagger includes B070 which is the proposed metering service. DES138 only has this mandatory for MS App event. Looks like swagger error – row 5154 |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Solution yet to be defined
MHHS-DIN-1105 | PP |  | 2024-05-05 | Design |  | Paul Pettitt | Central Body | API Guidance | Need to incorporate the guidance issued relating to the 1MB limits and message batching into the E2E001 Technical Architecture documents |  | Initial Assessment/Updating | Clarification - No change required |  |  | TBC |  | Pertanent sections from the guidance to be included in to the E2E001 solution Architecture document |  |  |  | E2E001
Formulas:
Objection Cut-off Date = IFNA(VLOOKUP([Target Release],[1]!Table2[#All],3,FALSE), " ")
Objection Cut-off Date = IFNA(VLOOKUP([Target Release, row above],[1]!Table2[#All],3,FALSE), " ")

## DIN Log 181024 (hidden)
DIN ITEM DETAILS | [11 empty] | Internal Assessment |  |  |  |  | DIN IMPACT ASSESSMENT
Reference | Created BY | other Reference(s) | Date Raised | Organisation | Freshdesk Ticket # | Contact Name | Constituency | Title | Design Issue Notification Details (as notified by participant) | Related CR | Current Status | DIN Type | Who is impacted? | Target working Group Date (If Required) | Target Release | Objection Cut-off Date | Design Issue Proposed solution | Justification/Type of Change | Design Area | Design Area - L2 | Artefact(s) Impacted
MHHS-DIN-1 |  | T4-COM-1744 | 2023-01-30 | St Clements | 2655 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1744 on 15th Sept 2022 MPRS does not currently restrict IHD Installs to Smart Meters, there maybe cases where there is an IHD present but the Meter is Trad (Not compatible with DCC and Customer Switched) Either Allow IHD on all Market Segments OR Cleansing to ensure IHDs are only present on S2 and S1 Meters SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses, as this is still not resolved |  | Implemented |  |  |  | Interim Release 1 |  | Discussed with SCS and agreed to add new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) Added requirements into BRS003. SCS to raise a potential data cleanse. | Requirement correction | MPAN Ownership | SCS Validation | MHHSP-BRS003-Registration Requirements
MHHS-DIN-2 |  | T4-COM-1745 | 2023-01-30 | St Clements | 2657 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1745 on 15th Sept 2022 DB002 is not the interface on which MPRS will be informed of a change to import/export relationship, it is DB05. The wrong diagram was updated, the EDI was updated to DB05 not import/export. SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses and artefact updates, to inform the wrong data item diagram was updated. However the diagram for EDI updates is still incorrectly reading DB005 update instead of DB02 |  | Closed | [5 empty] | This appears to have been missed in v4.6 - the arrow on BP-010B from step435 to Step 440 shows DB005 (not DB05, assume that’s a minor typo in the comment) - and this is the Energy Direction Information (EDI) which is wrong. It has cbeen onfirmed that this was updated in v4.7 to go into v5.0 baseline. | No Change |  |  | None
|  | T4-COM-1752 | 2023-01-30 | St Clements | 2661 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1752 on 15th Sept 2022: MHHS-BR-RS-020: "Retro" (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier ) In the D0205 the Supplier can cancel out the current Agent Appointment by setting the EFD to equal the currently stored Appointment EFD. Is this no longer allowed? All Services must be appointed for at least one day valid or not? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: removing the ability for Suppliers to Correct Invalid Service Appointments may not be understood by suppliers. We want to avoid a later Design CR to add this functionality in. SCS has not had a response, feel this is important discuss with Suppliers to avoid later CRs |  | Closed | [5 empty] | The appointment can be resubmitted if it hasn’t been accepted yet. Once accepted, there is a need to maintain contiguous appointment periods. The scenario mentioned is the CoA not linked to a switch, so the acceptance of a new appointment from a particular EFD will ‘lock in’ that date and the previous MS/DS will be de-appointed at midnight on the previous day. This is to ensure that there are no periods left without MS and/or DS in place, which can happen today with D0155/D0151 sequencing issues. As an overall comment, there is not a concept of cancellation of appointments. The only way to alter the appointment is to get a new IF-031 issued. The only way to do this for the scenario presented, would be to issue an IF-031 for the old MS for the original date and an IF-031 for the new MS for the revised date. Requirement MHHS-BR-RS-021 ensures that Registration Service will action the latest received appointment where there are duplicate appointments for the same day. St Clements had requested that we build in a rule saying that you cannot submit a Change of Service Provider (CSP) request for the same Service Provider. It is a bit of a work-around, but we believe sending it as SEG should work, or alternatively a CR would be required to re-look at the interface validation. Closing, as this doesn't require further action - point noted. We have already spoken to a number of suppliers, and will continue to engage to ensure the functionality of the baselined design is understood and any issues picked up as early as possible. Documentation for LDSOs to point at. Pick up in Code Drafting as well. | No Change |  |  | None
MHHS-DIN-4 |  | T4-COM-1755 | 2023-01-30 | St Clements | 2666 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1755 on 15th Sept 2022: MHHS-BR-RS-071.2 REC CP R062 has been raised to remove the restriction on the number of EDI changes. Will this cause any downstream MHHS issues? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Needs to be aligned with REC Change No responses |  | Closed | [5 empty] | As per original SRO response, the impacts of the REC change need to be dealt with through the REC change process and impact assessment. | No Change |  |  | None
MHHS-DIN-5 |  | T4-COM-1760 | 2023-01-30 | St Clements | 2667 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1760 on 15th Sept 2022: There are no Registration Service Reports defined in MHHSP-ERI011A. Will there be a requirement for MPRS to produce any Industry Reports for MHHS? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Design for the complete solution must be defined by M5. This is a DBT Design Start Blocker No responses This could significantly increase DBT time as development of reports can be costly and time consuming |  | Closed | [5 empty] | Who is raising these requirements? What happens today? Possibly CC issues Agreed with SCS that reporting requirements will be introduced via the CR process. Reporting requirements are to be added to the programme RAID log | No Change |  |  | None
MHHS-DIN-6 |  | T4-COM-1761 DI-7 | 2023-01-30 | St Clements | 2668 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1761 on 15th Sept 2022: IF-005, REG1014 First MAP Block, MAP Eff From Date [DI-054] in message, must = MPAN Install date OR >= Eff Form date of all existing MAP Effective From Dates held in Registration prior to first [DI-054] in message I understand that the First MAP must equal the Install Date, I am unsure what the second condition is trying to say? You can not have a Meter Without a MAP. (ignoring customer owned meters where CUST is used) SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: response is incorrect. The Second Rule "Each subsequent MAP Effective From Date [DI-054] must be > MAP Eff From Date in previous block" covers the subsequent overlapping MAPs. The second half of this First Block Rule must be removed. The First Block can only ever equal the install date No responses, the rule has not been amended |  | Implemented |  |  |  | Interim Release 1 |  | This appears valid - the first MAP block can only start at the creation date (assuming the MAP blocks are in chronological order, which they must be if each subsequent map block has an EFD > the last) Currently the design allows 2 ways to amend the MAP History as outlined in Sections 13 and 14 of the IF005 Use Case Guide. Either the Metering Service can provide the full MAP history from the installation date or they can add a new MAP to the existing history, provided it is the next MAP in chronological order. So for example if you have MAPs 1,2 and 3, then you can extend to MAPs 1,2, 3 and 4 using the approach set out in section 14 to extend the MAP history. However if you wanted to set MAP 4 between 2 and 3, you would need to send the whole MAP history from the install date and provide 1,2,4 and 3 as set out in Section 13 to replace MAP history. The second validation rule is required if you are using the extend the MAP history functionality. Added note to REG Notes that where a MAP history is provided it must be in chronological order Added new REG1014 Validation Rule to MeterInstall and MeterExchange events to ensure only 1 MAP block is provided | Data interface correction | MPAN Ownership | SCS Validation | MHHSP-DES138-Interface Catalogue
MHHS-DIN-7 |  | DI-8, DI-11, DI-12, DI-14 | 2023-01-30 | St Clements | 2669 | Madison Layton | Software Provider |  | MPRS will reject any PUB-031 including those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8) |  | Implemented |  |  |  | Interim Release 1 |  | See Comments Revised CSS Registration Request ID validation on IF-031, 034 and 025 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | IF General | MHHSP-DES138-Interface Catalogue
MHHS-DIN-8 |  | N/A | 2023-02-01 | Elexon | 2642 | Sedef Kiris | Central Body |  | We have had the following comment ........... Also just found out that “Metering Service Id” have “MPID” in brackets afterwards, and not “MSID”. We believe it should be MSID |  | Closed | [5 empty] | MPID is the correct term here, it is the metering service MPID. MHHSP_EDI012_ISD_Entities v4.6 Section M8 | No Change |  |  | None
MHHS-DIN-9 |  | N/A | 2023-01-30 | St Clements | 2672 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: [UpdateSiteTechnicalInfoMS] is not included in the interface catalogue and is not utilised by MPRS. Assume this is related to Issue 99 and needs removing? (raised as DI ID 9) |  | Implemented |  |  |  | Interim Release 1 |  | Removed from IF-005 Guide Section 4.1 | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-10 |  | N/A | 2023-01-30 | St Clements | 2799/2670 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: Is the currently appointed Meter Service informed of Prospective MS changes? Changes to MTDs can be made by prospective MS (e.g. change meter type to complete SEG market change before the MS can be appointed). As the MS is only prospective at this point the MS may still be lapsed and not take effect. However any MTD updates made would remain within the MPRS system and not be backed out. The current MS would therefore need to be aware of what changes have been made by the prospective MS. (raised as DI ID 10) |  | Closed | [5 empty] | BP009 only talks about the Metering Service, not the current or prospective Metering Service, and it appears only the registration service receive metering service MTD details, not the current MS. Refer to SRO - what is the assumption here, as the alternative route is for registration to update the current MS The design is based on PUB-006, with the Updated Meter details, being sent to the current Metering Service ( BP011A step 280 ) as well as the Prospective Metering Service (Step 275). It is built into the routing rules in PUB-006. | No Change |  |  | None
MHHS-DIN-11 |  | N/A | 2023-01-30 | St Clements | 2675 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install / Remove Date(s) takes place within the Metering Services period of ownership (or proposed period of ownership for in the case of a prospective SEG appointment) " Sent on 11th Jan: Does not match business rules, as future dated installs are not allowed: "REG1020 - Meter Install Date [DI-057] cannot take place in the future. The proposed MS on a seg will have a future dated EFD, so they only have the +2 day lapse extension period for meter installs (raised as DI ID 11) |  | Implemented |  |  |  | Interim Release 1 |  | Added change of segment scenario's to IF005 USE CASE Guide. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-12 |  | N/A | 2023-01-30 | St Clements | 2679 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install /Remove Date(s), cannot have taken place in the future" Sent on 11th Jan: It would be useful to have the Change of Segment process covered in this guide. We are not sure how the Prospective MS can exchange meters when their appointment period is in the future (raised as DI ID 12) |  | Implemented |  |  |  | Interim Release 1 |  | Nomenclature issue - requires a reword of this statement to conform to the business rules. Recommend the following update to section 3.2 of the IF005 Use Case Guide to confirm who can make Metering updates Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed BAU metering updates ( For the avoidance of doubt not meter update/meter history updates), it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. The one exception, is during a change of segment, when the incoming Metering Service is able to provide a BAU metering update, where it’s prospective “SEG” appointment is due to become active on the same day. SEG scenario's added to IF005 Use case guide Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-13 |  | N/A | 2023-01-30 | St Clements | 2683 | Madison Layton | Software Provider |  | Comment on Section 5.1 "validation allows for meter removal at a point following Disconnection if required)" Sent on 11th Jan: This rule prevents this REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational (raised as DI ID 13) |  | Implemented |  |  |  | Interim Release 1 |  | This statement doesn't appear to be a convention. There is no mention of this in E2E001 End to End Solution Architecture. Believe this statement needs to be amended or removed. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. IF-005 validation Rule changed to include meter removal at status Disconnected | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES138-Interface Catalogue, E2E001 End to End Solution Architecture
MHHS-DIN-14 |  | N/A | 2023-01-30 | St Clements | 2684 | Madison Layton | Software Provider |  | Comment on Section 3.2 "Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed metering updates, it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. " Statement is misleading- the 10 day period is only permitted for install, remove and exchange events, it is not listed for meterUpdate/meterHistoryUpdate in interface catalogue Also the prospective MS should be able to make changes for SEG to enable a market segment change to complete (raised as DI ID 14) |  | Implemented |  |  |  | Interim Release 1 |  | Validation rule(s) updated to constrain 10 day window to non-update events. Test in 3.2 reworded to remove ambiguity. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-15 |  | N/A | 2023-01-30 | St Clements | 2685 | Madison Layton | Software Provider |  | Comment raised in guide, sent on 11th Jan, that the JSON examples use MPID when it should use DIP ID e.g."distributorID": "SWAL" (raised as DI ID 15) |  | Implemented |  |  |  | Interim Release 1 |  | Corrected to use Dist DIP ID | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-16 |  | N/A | 2023-01-30 | St Clements | 2686 | Madison Layton | Software Provider |  | Comment on Section 9 " Albeit that these transactions can be ‘clubbed together’ and send as a group in single overarching message/API transaction. " Sent on 11th Jan: As DIP does not protect the sequencing of events (FIFO), is there a risk that the ordering of these updates might arrive out of sequence resulting in the wrong end state? If MS space out their updates it would reduce this risk (raised as DI ID 16) |  | Implemented |  |  |  | Interim Release 1 |  | Clairifcation added to Sec 9.2 to reference Time-Stamps rather than 'clubbing' | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-17 |  | DI-017 | 2023-01-30 | St Clements | 2690 | Madison Layton | Software Provider | MAP History availability to Metering Service | Section 9 says "a supporting MAP history commencing in line with the revised Installation Date must also be provided" Will the MS know the full MAP history? Risk they could destroy the data. Potential MAP billing issues? |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Solution agreed at DRG on what MAP updates are required. Various document updates required to align with DRG decision to only maintain latest MAP. Removed section 13 from IF005 user guide plus other corrections to doc. Updated DES138 IF005 validation rules. | Missing/incorrect validation rule | Supporting Docs | Various Documents | IF-005 Use Case guide MHHSP-DES138-Interface Catalogue
MHHS-DIN-18 |  | N/A | 2023-01-30 | St Clements | 2691 | Madison Layton | Software Provider |  | Comment on Section 9 "• When maintaining the MAP History in cases where there is no change in Meter Installation Date then the MAP history provided should commence either with a MAP Effective From Date matching the existing install date of the meter OR be greater than the most recent, already existing, MAP Effective From Date" Sent on 11th Jan: So it's possible to update ALL MAP history back to installation, or add a new MAP, but it's not possible to amend MAP history only part way back (have to go back to installation date instead every time to do this) (raised as DI ID 18) |  | Closed | [5 empty] | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • To update BRS003, requirement MHHS-BR-RS-027 to add “Registration Service must lapse any appointments that fail this validation” • Remove Rejected from Step 225 of BP002/BPD002 • Remove Rejected from label on line after step 215 of BP003. | No Change |  |  | None
MHHS-DIN-19 |  | N/A | 2023-01-30 | St Clements | 2692 | Madison Layton | Software Provider |  | Comment on Section 10 "E2E Architecture convention states that all data items are provided in each message even where these data items are not changing or are null" Sent on 11th Jan: Some of the items are optional not mandatory which conflicts with this statement. Not all data items need to be provided (raised as DI ID 19) |  | Implemented |  |  |  | Interim Release 1 |  | Update of E2E Doc to allow for Nullable values. | Data interface correction | Meter to Bank |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-20 |  | N/A | 2023-01-30 | St Clements | 2693 | Madison Layton | Software Provider |  | Comment on Section 13, sent on 11th Jan: What should MPRS do if it holds a MAP not included in the MAPHistory block? (raised as DI ID 20) |  | Implemented |  |  |  | Interim Release 1 |  | Update "all existing history will be replaced by that contained within the message" | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-21 |  | N/A | 2023-01-30 | St Clements | 2699 | Madison Layton | Software Provider |  | Comment on Section 15.2 "It is understood that currently there a numerous instances of duplicated Meter ID’s, some of which may have overlapping installation dates. " Sent on Jan 11th: Meter id is only unique at mpan. Should not be any instances of conflicted MSNs at MPAN. Can you verify with ECOES? Or we can do a RFI to DNOs but will take time (raised as DI ID 21) |  | Implemented |  |  |  | Interim Release 1 |  | All references to duplicated MSN IDs has been removed from the document | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-22 |  | N/A | 2023-01-30 | St Clements | 2700 | Madison Layton | Software Provider |  | Comment on Seciton 15.3 "add some kind of suffix (X1, X2) to the existing Meter ID." Sent on Jan 11th: This can take the meter ID over the allowable string length (string 10), in this example it would take it to string(12) and so would be rejected (raised as DI ID 22) |  | Implemented |  |  |  | Interim Release 1 |  | As above, Section 15.3 removed from IF-005 User Guide. | Data interface correction | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-23 |  | N/A | 2023-01-30 | St Clements | 2701 | Madison Layton | Software Provider |  | Comment on Section 16.3 Sent on Jan 11th: Cancelled Flag Set. Only a logical deletion. Still held in MPRS but not visible to EES/MEM The section implies the record would be fully deleted from MPRS, however this is not correct, MPRS would set a cancellation flag that would indicate the record has effectively been cancelled/logically deleted. It would however remain in the systems database (raised as DI ID 23) |  | Implemented |  |  |  | Interim Release 1 |  | Added a statement at the end of the table in 16.3 to say "NB the registration service will only logically delete the MAP entry with a flag, it will not be deleted from the database." | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-24 |  | N/A | 2023-01-30 | St Clements | 2702 | Madison Layton | Software Provider |  | Comment on Section 17.2 "situations where multiple existing meters are identified, the selection process should be extended to include Meter Removal date (if provided) else;" Sent on Jan 11th: Shouldn’t be possible, can run an EES or MPRS RFI to confirm. Noting that MSN is only unique at an MPAN level not a databse level Related to DI-21 (raised as DI ID 24) |  | Implemented |  |  |  | Interim Release 1 |  | Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. The wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-25 |  | N/A | 2023-01-30 | St Clements | 2706 | Madison Layton | Software Provider |  | Comment on Section 17.2 "where multiple meters still exist even after matching on all three data items should be rejected and require manual intervention (i.e. request to LDSO to intervene) ." Sent on Jan 11th: There's no super user functionality for this so how could the LDSO intervene? The LDSO is not able to manually intervene in regards to MTDs, they can for some other data items such as registration data but not MTDs. (raised as DI ID 25) |  | Implemented |  |  |  | Interim Release 1 |  | Reference to LDSO User Removed - agreed with SCS that scenario should not arise provided existing SCS data rules are met | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-26 |  | N/A | 2023-01-30 | St Clements | 2707 | Madison Layton | Software Provider |  | Comment on Section 17.2 "If the MAP segment is not provided, the existing MAP history should be maintained to greatest degree possible, with ‘trimming’ to align to any revised Install / Remove Dates provided" Sent on Jan 11th: Risk that changing of the Meter Lifespan could result in MAPs being logically deleted. The MS would need to re-apply the MAP history to fit into the new meter Lifespan MS would need to understand this process/constraint (raised as DI ID 26) |  | Implemented |  |  |  | Interim Release 1 |  | Section 17.2 of the guidance document updated. Also added new validation rule REG1014 for MeterHistoryUpdate in IF-005 to ensure MAP is provided when creating a new meter picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-27 |  | N/A | 2023-01-30 | St Clements | 2708 | Madison Layton | Software Provider |  | Comment on Section 19.2 "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the permanent deletion of data, mirroring the existing functionality associated with the use of the D0312." Sent on Jan 11th: Only logically deleted, still visible in the MPRS History. Just not visible to MEM or EES Existing functionality on D0312 utilises cancellation flags not permanent deletion (raised as DI ID 27) |  | Implemented |  |  |  | Interim Release 1 |  | Reword to reflect the logical deletion. See MHHS-DIN-23 Reword this paragraph to: "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the removal of a MAP from a meters MAP history using a logical flag, mirroring the existing functionality associated with the use of the D0312." NB Main section header is incorrect - should be updated to section 19, rather than a duplicate of section 18. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-28 |  | N/A | 2023-01-30 | St Clements | 2709 | Madison Layton | Software Provider |  | Comment on Section 19.4 "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories. However, this would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." Sent on Jan 11th: This functionality already exists with the MPAN History Report showing who changed what when for all MPRS data items. Will be extended to include DIP transactional information (raised as DI ID 28) |  | Implemented |  |  |  | Interim Release 1 |  | Proposed Change Reword this paragraph to: "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories, noting that this is also available via the MPAN history report which will be updated with DIP transactional information and could also be used. Any use of EES would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-29 |  | N/A | 2023-01-30 | St Clements | 2710 | Madison Layton | Software Provider |  | There should be an additional rule for USP, if DI-830/DI-833 is populated, the MS/DS Proposed Effective From Date must equal the currently held EFD for the MS/DS appointment in MPRS (raised as DI 29) |  | Implemented |  |  | 2023-04-27 | Interim Release 1 |  | Added rule for USP scenario in IF-031 to check SP Effective from date. Proposing SCS have flexibility on error codes - requires industry Working Group. Picked up as part of Change of Service Provider review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-30 |  | N/A | 2023-01-30 | St Clements | 2711 | Madison Layton | Software Provider |  | The IF-035 does not provide the opportunity for MPRS to populate a lapsed reason. Will need to be able to provide a reason for a lapsed appointment, otherwise there'll be a higher volume of unecessary supplier enquries to DNOs which will require more resource and cost. (raised as DI 30) |  | Implemented |  |  |  | Interim Release 1 |  | Additional Data Item on IF-035 for a reason comment - what reasons would these be other than gone beyond the date? Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-31 |  | N/A | 2023-01-30 | St Clements | 2712 | Madison Layton | Software Provider |  | MHHS-BR-RS-027 "Registration Service must re-run validation, in line with the validation rules set out in the appropriate interface specification, for all Metering Service appointments that have been confirmed to re-process from the Prospective Appointment Queue, to ensure that the appointment is still valid" It is not clear if MPRS would send MSAppRejected or MSAppLapsed if the appointment fails validation after it's been queued? If this is not made clear in the deisgn then there is a risk that we build to use the wrong event code, or if the code should be MSAppRejected then risk that suppliers build a design where they can't process a MSAppRejected after receiving already an MSAppAccepted from MPRS (raised as DI 31) |  | Implemented |  |  |  | Interim Release 1 |  | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • Updated BRS003, requirement MHHS-BR-RS-032 and 66 to show that appointments will be lapsed (not rejected) • Remove Rejected from Step 225 of BP002/BPD002 Also on BP003 leading from step 215 should have the rejected removed. Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Corrections also to BPM002 & BPM003 Forward Migration and BPD002 Froward Migration | Data interface correction | MPAN Ownership |  | MHHSP-BP002-Change of Service - Metering service, BPD002,MHHSP-BRS003-Registration Service requirements MHHSP-DES138-Interface Catalogue, MHHSP-BP003, MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration), MHHS-DEL969-BPD002 (forward migration)
MHHS-DIN-32 |  | N/A | 2023-01-30 | St Clements | 2713 | Madison Layton | Software Provider |  | The interface catalogue lists setting a removal date as an action that can be used with event code meterUpdate on IF-005, however in the interface catalogue, the block B039 does not list meterUpdate as a event code that can utilise this block. Need greater clarity on whether meterUpdate and meterHistoryUpdate should apply meter installations and meter removals or not. (raised as DI 33) |  | Implemented |  |  |  | Interim Release 1 |  | The definition of a [MeterUpdate] event code is: Allows currently appointed Metering Service to amend the details associated with a currently installed meter. Therefore the appointed Metering Service must be able to remove the meter as part of an update, this is an omission from the design and a small update to IF-005 The design principle that IF-005 works on is that: • BAU transactions (Install/Exchange/Remove) that are in the Metering Services Period of ownership are covered by the Install/Exchange/Remove events • Changes to currently installed metering can be made by the Appointed Metering Service using the Meter Update event. Note this therefore includes, where required, removing the currently installed meter where it is prior to the current period of ownership. • Changes to metering history ( ie not the currently installed meter ) can be made by the Appointed Metering Service using the Meter History Update Proposed changes: Added MeterUpdate as Optional to B039 block in IF-005 and added validation rule to ensure MeterUpdate is not used to remove meters in current period of ownership picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP-DELS229-IF-005 Use Case Guide
MHHS-DIN-33 |  | T4-COM-1759 | 2023-01-30 | St Clements | 2719 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1759 on 15th Sept 2022: IF-005, REG1011 Install date must be > Creation date, should this REG1011 rule apply also to meter Exchange not just meter install SCS raised as a design blocker on 7th October 2022 Still no resolution, should this rule apply to meterHistoryUpdate at least as this allows for meter installations (raised as DI 34) |  | Implemented |  |  |  | Interim Release 1 |  | An exchange will not be a creation date, and the validation already in place ensures that future installation dates will all follow each other, which means this rule isn't required. ​This shouldn't be needed for exchanges, as its covered by REG1008 (install date >= remove date), as an exchange would replace an existing meter, which at first install would be validated against creation date. Moved REG1011 to cover all scenarios in IF005 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-34 |  | T4-COM-1774 | 2023-01-30 | St Clements | 2720 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1774 on 15th Sept 2022: IF-005, REG1011 "REG1009 - MAP ID [DI_055] is not valid for MAP Effective Date [DI-054] REG1011 - Install Date [DI-057] for MeterID [DI-056] is prior to MPAN Creation Date There are many meters in MPRS that pre-date the existence of the MAP and also MPRS install dates of 1980 etc. these will break a number of rules. should these be cleansed before MHHS start? If they are valid, then the rules need adjusting"l SCS raised as a design blocker on 7th October 2022 Still no resolution (raised as DI 35) |  | Closed | [5 empty] | This could be a data cleanse requirement which is a consequential change/transition requirement, but for REG1009 - the MAP effective date should be the point at which the MAP took over the meter, and the exchange date should be after this (ie it should be after the date MHHS goes live). For Reg 1011 currently this is only valid on installs (and installs won't occur on legacy meters). If Reg 1011 is valid on exchanges, then the exchange date should also be after the MPAN creation date - if it isn't then the data should be cleansed. Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-35 |  | N/A | 2023-01-30 | St Clements | 2721 | Madison Layton | Software Provider |  | On the IF-005, should REG1028 (Install date cannot be null or blank) apply to meterinstall, meter exchange and meterupdate too? (raised as DI 36) |  | Implemented |  |  |  | Interim Release 1 |  | Requires amendment to interface validation - look at alternative validation Agree the rule should also apply for those events. Note we believe validation would fail for another reason. Eg REG1019 Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-36 |  | DI-37 | 2023-01-30 | St Clements | 2722 | Madison Layton | Software Provider | Re-alignment of rejection reasons to main block | In the summary of error codes box at the bottom of IF-005 tab the rejection reasons need re-aligning to the main block, e.g. REG1001 should read RMP stats must be Created or Operational, not just Operational As a general note across all interfaces, the rejection codes are referenced in numerous places and the respective descriptions are in many places not consistent for the same rejection code (raised as DI 37) |  | Closed | [5 empty] | Will be revisited once SCS provide definative Error Code Texts | No Change
MHHS-DIN-37 |  | N/A | 2023-01-30 | St Clements | 2723 | Madison Layton | Software Provider |  | REG1015 (cannot be removed meter) is listed for meterHistoryUpdate in interface catalogue for IF-005. This should actually apply to meterUpdate not meterHistoryUpdate, REG1018 (cannot be installed meter) applies to metering history update (raised as DI 38) |  | Implemented |  |  |  | Interim Release 1 |  | Change accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-38 |  | N/A | 2023-01-30 | St Clements | 2724 | Madison Layton | Software Provider |  | In the interface catalogue, the IHD block B030 for IF-005 should also be optional for meterUpdate according to the IF-005 guide Section 16 Development Notes "The IHD segment, if provided as part of [MeterUpdate], relating to any currently installed meter should replace/update the IHD details currently held at the MPAN to which that Meter is associated." (raised as DI 39) |  | Implemented |  |  |  | Interim Release 1 |  | Small change to schema operation IHD information may be updated as part of the [MeterUpdate] event. The change is to add [MeterUpdate] event to block B030, so it now reads "B030 - MPAN IHD Information (Optional & may only be used with [MeterInstall],[MeterExchange],[MeterUpdate]) NB this also standardises the use of commas between event codes, rather than using the & symbol. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-39 |  | N/A | 2023-01-30 | St Clements | 2725 | Madison Layton | Software Provider |  | In interface catalogue for IF-005, there needs to be a rule that if event code MeterInstall is used, then modified meter ID cannot be populated (raised as DI 40) |  | Implemented |  |  |  | Interim Release 1 |  | Update agreed | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-40 |  |  | 2023-02-01 | SI Design |  |  |  |  | Not used - raised as duplicate in error |  | Closed
MHHS-DIN-41 |  | N/A | 2023-01-30 | St Clements | 2730 | Madison Layton | Software Provider |  | In interface catalogue IF-005: The REG1003 reads Metering Service [S0.SenderID] holds valid previous appointment then Meter Install Date [DI-57] should be < [REG.App End Date] + 10 The way it's curently written suggests MPRS should accept an IF-005 from the previous appoint, even if their ETD was greater than 10 days ago, provided the install date was less than their ETD + 10. E.g the previous MS could send IF-005 two years later with Install date of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then REG1002/REG1019 should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? (Raised as DI 41) |  | Implemented |  |  |  | Interim Release 1 |  | Having looked through IF-005 Dates should be within the appointment date, and current deign does give the ability to go outside this Change the validation rule for REG1003 on events [MeterExchange], [MeterInstall] and [MeterRemoval] to "If Metering Service [S0.SenderID] holds valid previous appointment then [system date] < [REG.App End Date] + 10" Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. Rule amended after review by SCS, to remove second "if" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-42 |  | N/A | 2023-01-30 | St Clements | 2784 | Madison Layton | Software Provider |  | In interface catalogue IF-005: Meter Update should apply validation REG1027 (current MS or prospective MS) not REG1012 (current MS only) to allow the prospective queued MS to update the Meter Type on a SEG change and therfore complete the market segment change and appointment. MHHS-BR-RS-132 . If the SEG prospective appointment was not allowed to update on meterUpdate event code then they would not be able to update the meter type to completed change of market segment, and would not meet the conditions needed to then be appointed in MPRS, their appointment would then lapse and market segment would remain invalid. (Raised as DI 42) |  | Closed | [5 empty] | We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error... | No Change |  |  | None
MHHS-DIN-43 |  | N/A | 2023-01-30 | St Clements | 2732 | Madison Layton | Software Provider |  | In Interface Catalogue, on If-005, REG1002 and REG1019 are duplicates (install/removal dates should be within MS period of ownership). We can only use one of the rejection codes and descriptions, programme should choose which one to keep and remove the other. (Raised as DI 43) |  | Closed | [5 empty] | These are testing slightly different things. The first test (REG1002) is checking that the Metering Service is an eligible party to send the request ie currently appointed OR was at the time of the install (to cover for previous Metering Services updating in the 10 day window). The second (REG1019) is checking that the Install Date is in the Metering Services period of ownership. So you could have that the Metering Service is currently appointed, but that they weren't at the install date. Eg Today is 2nd Feb, Meter installed on 27th Jan, Sending MS was appointed on 1st Feb REG1002 would pass as they are eligible as the currently appointed MS REG1019 would fail as they are not appointed at the time of the install Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-44 |  | N/A | 2023-01-30 | St Clements | 2733 | Madison Layton | Software Provider |  | Should the new rule for meter update in IF-005 also apply to meter history update? If no MAP entries provided, and revised Meter Install / Remove Dates result in no valid MAM History then reject with REGE1014 – MAP Eff From Sequence Error (Raised as DI 44) |  | Implemented |  |  |  | Interim Release 1 |  | Added REG1014 ( MAP History ) to IF-005 MeterHistoryUpdate event | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-45 |  | N/A | 2023-01-30 | St Clements | 2736 | Madison Layton | Software Provider |  | New rule for IF-005 Meter Update REG1017 could be misinterpreted as it currently reads incorrectly - need brackets to correct to how the AND and AND/OR conditions are to be applied If [DI-60] is not null AND Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null) Should read If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null)) (Raised as DI 45) |  | Implemented |  |  |  | Interim Release 1 |  | Clarification of existing design rule Change the validation rule for REG1017 to: "If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null))" picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-46 |  | N/A | 2023-01-30 | St Clements | 2737 | Madison Layton | Software Provider |  | on IF-005 for Meter Exchange and meter install the rule for REG1027 has been changed, but I'm not sure the wording implements the rule intended exactly? Currently it reads as The MS must be the currently appoint MS AND the install date must be > MS EFD AND the MS must not have proposed MS app with SEG scenario in the queue. If not then reject with REG1027 - Metering Service is not currently appointed and does not hold a Prospective SEG Appointment SHould the rule actually read The MS must be the current MS OR the MS must have a proposed MS App in the queue with SEG scenario And then the other part of the rule about install date > MS should be a separate rule (with REG1019 error code). (Raised as DI 46) |  | Implemented |  |  |  | Interim Release 1 |  | Sent to Mike F for validation - SI believe wording in current documentation is correct. Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. I would suggest the wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. DIN-46 – On review we agree, the date test should always be true if REG1019 is satisfied ( with minor clarification update ), so validation rules should be updated as below: Proposed changes: REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-47 |  | N/A | 2023-01-30 | St Clements | 2738 | Madison Layton | Software Provider |  | REG1001 on IF-005 does not allow for meters to be removed after a disconnection. Instead should restrict for allow other event codes but allow Status Terminated for MeterRemoval. DES204 CCR-0556 Linked to DI-13 |  | Implemented |  |  |  | Interim Release 1 |  | Rule update required picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-48 |  | DI-048 | 2023-01-30 | St Clements | 2739 | Madison Layton | Software Provider | CSS failure to apply CoS to related secondary MPANs | Unhappy path scenario:- What happens if, for whatever reason, CSS fails to apply CoS to all the related secondary MPANs MPRS receives IF-031 on primary RMP to change agent, MPRS applies this to all seocndary MPANs too But if the CoS was not received from CSS for secondary MPANs that the secondary MPANs would still currently be held for the wrong supplier Would this cause any issues downstream? (Raised as DI 48) |  | Closed | Design gap | SCS |  |  |  | Change Request to be raised against this | Other | MPAN Ownership | Related MPANs
MHHS-DIN-49 |  | N/A | 2023-01-30 | St Clements | 2740 | Madison Layton | Software Provider |  | Unhappy path scenario:- If MPRS sends a IF-033 but never receives back a IF-034 then the rest of the process will not continue. The Supplier will never receive the IF-035 they are waiting for and the SP would never get appointed by MPRS. Is there a process in place to detect/resolve this scenario? (Raised as DI 49) |  | Closed | [5 empty] | There is a requirement for the Supplier to monitor for any delayed responses and request an update if not received in expected timescales. Reviewed with SCS and agreed ticket can be closed | No Change |  |  | None
MHHS-DIN-50 |  | N/A | 2023-01-30 | St Clements | 2741 | Madison Layton | Software Provider |  | We need clear rules to define what a valid Consent granularity looks like. Current rules don’t mention any validation around EDI. (Raised as DI 50) |  | Implemented |  |  |  | Interim Release 1 |  | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-51 |  | DI-51 | 2023-01-30 | St Clements | 2747 | Madison Layton | Software Provider | St Clements Design Query - DI 51 | We have had some feedback from DNOs asking about how systems will recover from System Misalignment because of data errors or significant downtime? We have the D0204 (Supplier) and D0209 (Data Aggregator) Refresh functions today which are not being replaced with a DIP message equivalent. I am aware of the DIP Replay function, but this wouldn’t be of any help if there were data errors, as the DIP would just be replaying the incorrect data. The Source system would need to re-send the corrected data in an agreed format. I know there is a design principle to move away from bulk loads and refreshes of data, Faster Switching took a similar approach. However today, CSS leans heavily on the MPRS Refresh function to get itself back inline and there are REC CP’s being raised to add a Refresh function to CSS for all parties (first CP being R0067). DNO’s are keen to understand the MHHS Programme’s position on and if Refresh functionality should be built into MPRS for MHHS. |  | Closed | Design gap | DNO (SCS), EES (RECCo), DIP |  |  |  | Change Request will be raised against this DIN. Refresh Functionality was rejected by the Working Groups so not in current design. Internal Design Discussion Required on if Programme position has changed on this given CSS Issue / EES Fed via DIP ?? Details provided by the Design Team to SCS and RECCo on the workings of the refresh functionality and get agreement on next steps. | Other | Supporting Docs | Refresh Process?
MHHS-DIN-52 |  | DI-52 | 2023-01-30 | St Clements | 2748 | Madison Layton | Software Provider |  | For IF-005, REG-1006 and REG1013, would it make sense to include the installation date of the MPAN already in the system in the rejection description too to help MS with triage? |  | Closed | [5 empty] | DIN closed as instructed by St Clements. Old comments: Discussed with SCS potential for them to have flexibility on error messages. Industry agreement required. Participant Discussion Required | No Change
MHHS-DIN-53 |  | N/A | 2023-01-30 | St Clements | 2749 | Madison Layton | Software Provider |  | Requirement on LDSO requirements spreadsheet: MHHS-BR-LD-035 LDSO Maintain DUoS Tariff ID LDSO must set Duos Tariff ID on MPAN creation and maintain DUoS Tariff ID's in line with their Charging Method Statement. This should include updating the Duos Tariff ID, as required, following any updates to Domestic Premise Indicator, Connection Type and Energy Direction Note for MHHS, LLFC ID is being renamed as DUoS Tariff ID to make it clearer what this data item is used for. "BP010B Change of registration data" 250 However missing the respective requirement for Registration Services in the Registration Services Requirements spreadsheet |  | Closed | [5 empty] | Looked through the Registration Services Requirements spreadsheet v4.6 and it looks like DUoS Tariff ID is there - MHHS-BR-RS-091.1, MHHS-BR-RS-121 and MHHS-BR-RS-122 | No Change |  |  | None
MHHS-DIN-54 |  | N/A | 2023-01-30 | St Clements | 2750 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1699 on 15th Sept 2022: On the IF-031 and IF-035 there are a number of "Proposed" Data items. Should MPRS load these and updated the stored data items. Or are these data items only for passing through to Supplier and Service? SCS raised as a design blocker on 7th October 2022 We have some clarity verbally on this but nothing has been formally documented in the design artefacts. This needs to be reflected somewhere in the requirements. |  | Implemented |  |  |  | Interim Release 1 |  | Added "Appoinments - Data" section in REG Notes to highlight what data becomes effective with the appointment. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-55 |  | T4-COM-1738 | 2023-01-30 | St Clements | 2751 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1738 on 15th Sept 2022: the DB02 flow updates multiple data items on the IF-018 in one event. Can multiple EventCode be included in one IF-018 or will MPRS need to generate an individual IF-018 for each EventCode? SCS received a blank response and raised as a design blocker on 7th October 2022 |  | Closed | [5 empty] | Original response was that clarification was to be provided on 24th Oct - is this available? Which document? One at a time | No Change |  |  | None
MHHS-DIN-56 |  | T4-COM-1742 | 2023-01-30 | St Clements | 2752 | Madison Layton | Software Provider | Manual Correction to MHHS data items | Originally raised as T4-COM-1742 on 15th Sept 2022: BSCP604 currently allows LDSO and Suppliers to request manual corrections to Data Items held in MPRS. Will this type of Manual Correction be allowed in MHHS, if yes then this should be added to the business process to capture manual amendments and how these changes are reflected back to DIP users (IF-018 & IF-026, or a new Refresh Message?) SCS received a blank response and raised as a design blocker on 7th October 2022 Another example of this: If the MS/DS history is incorrect and cannot be amended via BAU, would the DNO be able to correct this via an exceptional error handling process? |  | Closed | Design misaligned | LDSO, Supplier and SCS |  |  |  | Covered in the retrospective changes discussion at DRG. | Requirement correction | MPAN Ownership | CSS Defects | MHHS-BPD005 Data Processing, MHHS-BRS005 LDSO overview
MHHS-DIN-57 |  | T4-COM-1748 | 2023-01-30 | St Clements | 2756 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1748 on 15th Sept 2022: "Additional information field DI-120 is String200, where the existing DB03 allows a free text field of 2000 characters" SCS raised as a design blocker on 7th October 2022 This was corrected but then in v4.5 artefacts released there was a change back for DI-120 addition information field from string 2000 to string 200 in the interface catalogue data catalogue tab reintroducing the issue. For disconnection additional notes MPRS database holds 2000 characters so this field will need to be string 2000 in the IF interfaces (Raised as DI 57) |  | Closed | [5 empty] | Change to the data catalogue included in the 4.7 baseline | No Change |  |  | None
MHHS-DIN-58 |  | T4-COM-1789 | 2023-01-30 | St Clements | 2757 | Madison Layton | Software Provider | Valid combinations of ISD data for MPRS validation development | Originally raised as T4-COM-1789 on 15th Sept 2022: "Valid combinations of data in ISD are critical to the MPRS validation development, we must have these defined and agreed before we can start development" SCS raised as a design blocker on 7th October 2022 |  | Closed | [5 empty] | Elexon has defined the valid combinations of ISD data and these files are available on this link https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/ISD.aspx | No Change
MHHS-DIN-59 |  | T4-COM-1707 | 2023-01-30 | St Clements | 2758 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1707 on 15th Sept 2022: "The Smart DS for Export and Secondary MPANs can be different to the Import/Primary DS as the Customer can choose their own DS for Export and Primary (Smart only)" The IF-031 validation rules have been amended but they are still not corrrectly reflecting the rule. The heading above both rules REG1038 and REG1039 reads: "If event type = [MSApp] OR event type [DSApp] & MPAN Segment is not 'Smart'" This heading should ONLY apply to REG1038 for linked MPANs and should not apply to REG1039 concerning related MPANs It should also have brackets to clarify the logic otherwise it could be misinterpreted e.g. "If event type = [MSApp] OR (event type [DSApp] & MPAN Segment is not 'Smart')" |  | Implemented |  |  |  | Interim Release 1 |  | This seems a valid issue. REG 1039 on linked meters should be allowed for trad meters (eg economy 7) Proposed Change: The logic issue here is that REG1039 caters for related meters, which are applicable to trad as well as smart meters. Remove REG1039 from this validation Change the validation to: "If (event type = [MSApp] OR event type [DSApp]) & MPAN Segment is not 'Smart'" Updated heading above REG1038 and added heading above REG1039 to clarify the validation rule in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-60 |  | T4-COM-1708 | 2023-01-30 | St Clements | 2759 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1708 on 15th Sept 2022: "The Service Appointment Date must be equal to the SSD or there will be a period with no Service" And T4-COM-1776 also on 15th September 2022 "REG1032 - Metering Service Eff From Date [DI-830] is not contiguous - Appointment must be from [Max[Reg.MPAN_SSD] ,[Reg.ExistingMSAppFrmDate]] for a COS, it can only equal the SSD otherwise there will be a gap" This has been applied incorrectly. In IF031 rules REG1032 now reads that the MS/DS prop EFD must be = Max(SSD, existing MS/DS EFD + 1) This would restrict the MS/DS to setting the new EFD to either SSD or the day after the last MS/DS appointment, and all other dates would be rejected. It should read >= not just =. All four refrences to REG1032 in the validation rules for IF-031 references the +1 day after EFD, but the rejection description in the right hand columns for 'scneario not SEG or CoS' section does not reference this + 1. This should be corrected to be consistent with the other rules. (Raised as DI 60) |  | Implemented |  |  |  | Interim Release 1 |  | Original response to 1708: New rules added to cover all scenarios Original response to 1776: Change to be incorporated into design artefact Updated REG 1032 validation in IF-031, original single rule, split into 2 separate rules picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-61 |  | T4-COM-1445 | 2023-01-30 | St Clements | 2760 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1445 on 15th Sept 2022: "There is no mechanism to update the Profile Class. We would assume that this would be updated by the Supplier (with business rules restricting when this should be set) and confirmed on the IF-026. Please can you confirm if this is the intention or if it will be updated through another route. If so, the EES would need to know which PUB would confirm the data item had been updated. " Whilst this is now included in the design the validation rules from D0205 have not been carried over, e.g. PC/SSC need to be a valid combination. ISD will need to contain the valid PC/SSC Combinations (previously MDD Entity 11) and the validation rules in the interface catalogue will need to reference this validation against the ISD valid combinations. (Raised as DI 61) |  | Implemented |  |  |  | Interim Release 1 |  | See also DIN-58, need to find out who is defining ISD validation Updated Interface notes in IF-025 to confirm that there is no Profile Class/ SSC combination checks | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-62 |  | DI-062 | 2023-01-30 | St Clements | 2761 | Madison Layton | Software Provider |  | In the business process diagram for Registration Updates MHHSP-BP010-Change of Registation Data - v4.5, the MPL update section, the C0300 has been changed to C0400 which is incorrect, C0400 is for MAP updates. Address updates are actually sent in the C0600. (Raised as DI 62) Change raised 30 March:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly. |  | Implemented |  |  |  | Interim Release 1 |  | Also in the BPD. MHHS-BR-RS-114 also confirms this should be C0300, this appears to be a straightforward typo. Amend label between Step 20 and Step 30 on BP010A to CSS0300, and update the corresponding BPD description on step 30 Update required:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly in BP010A, BPD010 and in MHHS-BR-RS-114. | Process model correction | Metering Changes | MPAN Updates | MHHSP-BP010-Change of Registration Data MHHSP-BPD010 MHHSP-BRS003
MHHS-DIN-63 |  | DI-063 | 2023-01-30 | St Clements | 2792 | Madison Layton | Software Provider |  | In the business process diag for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 (Raised as DI 63) |  | Closed | [5 empty] | SCS have now confirmed that C0700 is the correct reference - no need to change documentation - agreed to close | No Change | MPAN Ownership | Disconnection | MHHSP-BP007-Disconnection MHHSP-BPD007
MHHS-DIN-64 |  | N/A | 2023-01-30 | St Clements | 2793 | Madison Layton | Software Provider |  | In business process diag for change of data service MHHSP-BP003-Change of Service- Data Service-v4.5 and MHHSP-BP002-Change of Service- Metering Service v3.5, this still makes reference to D0386 in the purple note boxes. This should now have changed to IF-019 (Raised as DI 64) |  | Implemented |  |  |  | Interim Release 1 |  | Update notes on BP002 and BP003 from D0386 to IF-019, and for BPM002 & BPM003 (forward migration) | Process model correction | MPAN Ownership | Change of DS | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-65 |  | N/A | 2023-01-30 | St Clements | 2794 | Madison Layton | Software Provider |  | The business process diagram for change to connection type/market segment has been amended to name only DB01, connection type is set on DB01 but it can then be changed on DB02 (Raised as DI 65) |  | Implemented |  |  |  | Interim Release 1 |  | Update label between step 220 and 225 from "DB-001" to "DB02" | Process model correction | Metering Changes | Market Segement | MHHSP-BP011-Change of Connection Type or Mkt Segment
MHHS-DIN-66 |  | N/A | 2023-01-30 | St Clements | 2795 | Madison Layton | Software Provider |  | In interface catalogue, on IF-031, shouldn't rule REG1036 (MDR app EFD must be after DS app EFD), be applicable to all scenarios including SEG? Currently under section for if not SEG (Raised as DI 66) |  | Implemented |  |  |  | Interim Release 1 |  | Updated validation rule for REG1036 and made applicable to all scenario's in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-67 |  | N/A | 2023-01-30 | St Clements | 2796 | Madison Layton | Software Provider |  | Currently no rule on IF-031 that the SP appointment has to be within the prospective suppliers registration period - just that it can't be past dated. This rule will need to be added. (Raised as DI 67) |  | Closed | [5 empty] | Reviewed with SCS and agreed that this validation is covered by existing rules. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-68 |  | N/A | 2023-01-30 | St Clements | 2797 | Madison Layton | Software Provider |  | If-031 business rule missing If the Scenario is USP, the consent granularity must be the same as the existing consent granularity held within MPRS (Updates should be through IF-025 not through IF-031) (Raised as DI 68) |  | Implemented |  |  |  | Interim Release 1 |  | picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Updated Interface notes in IF-031 to clarify that Registration Service will ignore any differences in Domestic Premise Indicator/ Consent Granularity sent on IF-031 (USP scenario) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-69 |  | N/A | 2023-02-02 | ESG Global | 2653 | Luke Speakes | Software Provider |  | PUB-033 - Block 029 is conditionally mandatory for DCC Commissioned Meters, but includes DI-025 DCC Service Flag with valid values of A-Active, I-Installed Not Commissioned, N - Non Active. The title of the block, which should define whether it is mandatory or not, is not appropriate if a DCC meter has been installed and not commissioned, or is inactive. Propose following SI and SRO design discussion that title of block 029 is revised to conditionally mandatory for 'DCC Smart Meters' |  | Implemented |  |  |  | Interim Release 1 |  | Concludes this can be resolved by a minor wording change to the block title | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-70 |  | N/A | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory | Addition of MDR validation rule | Elexon is required to maintain a valid list of Meter Data Retrievers in Industry Standing Data, to allow RegService to validate they're suitably qualified (DCC and SEC) MDRs are being appointed. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Design Agreement is to utilise M16 for this purpose. ISD document updated with details and examples to this effect. | Other | Supporting Docs | ISD | MHHS-EDI-021-ISD_Entities
MHHS-DIN-71 |  | N/A | 2023-01-30 | St Clements | 2839 | Madison Layton | Software Provider |  | When would event code [MSDeAppUpdate] and [DSDeAppUpdate] be used for on an IF-037? (Raised as DI 69) |  | Closed | [5 empty] | Reviewed with SCS and it is used to notify the incoming Service Providers when de-appointing and not origanally known. In case of Linked/Related MPANs individual MPANs move through the process. RS need to apply the logic for sending the updated IF-037 to all MPANs. Agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-72 |  | N/A | 2023-01-30 | St Clements | 2840 | Madison Layton | Software Provider |  | Block B018 on IF-034 and IF-035 should not be mandatory - it will only be provided for smart meters. This needs to be set to mandatory for SDS-MDRUpdate only, optional for DSAppSPResponse (Raised as DI 70) |  | Implemented |  |  |  | Interim Release 1 |  | Updated B018 block to be optional for non Smart on IF-034 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-73 |  | N/A | 2023-01-30 | St Clements | 2841 | Madison Layton | Software Provider |  | IF-026/IF-025, added new event code [SSCandProfileClass], but still kept in original [SSC] and [ProfileClass] event codes, should the original two have been removed? Particularly as the B032 group says it's madatory where event code is [SSCandProfileClass] and does not refer to [SSC] or [ProfileClass] individual event codes (Raised as DI 71) |  | Implemented |  |  |  | Interim Release 1 |  | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-74 |  | N/A | 2023-01-30 | St Clements | 2842 | Madison Layton | Software Provider |  | A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a new MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60 (Raised as DI 72) |  | Implemented |  |  |  | Interim Release 1 |  | This appears to be the reciprical change to MHHS-DIN-60 for the response interface Update description to "Check if MDR Eff Date = SSD OR on or after existing MDR Eff From + 1" Update rule to "If [DI-841] <>SSD OR <MDR Eff Date + 1" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-75 |  | N/A | 2023-01-30 | St Clements | 2843 | Madison Layton | Software Provider |  | On IF-035, overidden the description for Data Item 836 incorrectly with the description for Data Item 838 (Raised as DI 73) |  | Implemented |  |  |  | Interim Release 1 |  | Update the definition field based on the description in the data catalogue for DI-836 on IF-035 (Date From which Supplier would like Nominated MDR to take effect) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-76 |  | N/A | 2023-01-30 | St Clements | 2844 | Madison Layton | Software Provider |  | Data catalogue - changed the estimation reason code authoritative source to Registration Service, this data item is not received by, sent by or held by registration services and so the authoritative sourse cannot be Registration Service (Raised as DI 74) |  | Implemented |  |  |  | Interim Release 1 |  | The authoriative source has changed between v4.0 (from Data Service) to 4.7 (Registration Service) - have asked why the change was made, and what the authoritative source should actually be. Source updated to SDS/MDS | Data interface correction | Meter to Bank | Estimation | MHHSP-DES138-Interface Catalogue
MHHS-DIN-77 |  | N/A | 2023-01-30 | St Clements | 2845 | Madison Layton | Software Provider |  | Data catalogue - Added issue 99 items (CT Ratio, Phases etc) DI-170 - DI-180. Was agreed in work off meeting these items are not within the scope of MHHS, to introduce these would require a CR (Raised as DI 75) |  | Implemented |  |  |  | Interim Release 1 |  | these data items don't appear to be used in any interfaces so this could be a relatively simple change to remove 11 items from the data catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-78 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E0404 requirement is blank - row needs to be deleted |  | Closed | [5 empty] | This update was already incorporated into version 5.0 closing it here | No Change | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-79 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E21114 typo - should be VAS Output Retention |  | Implemented |  |  |  | Interim Release 1 |  | change as per description | Technical corrrection | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-80 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHSP-DES138-Interface Catalogue v4.6 - DI-846 Issuing Data Service EZ Name should be scored through in IF/ PUB21 definition |  | Closed | [5 empty] | Completed in V5.0, part can review change as part of Interim Release 2 | No Change | Meter to Bank | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-81 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier | Correction of step in BP020 | MHHSP - BP020 - Volume Allocation Service (ECS) v4.6 - Step 75 to Step 80 references report “REP-00” - needs correcting |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | BP020 step 75 to step 80 process flow REP list correction BPD020 step 75 & step 80 detail list of REP's correction | Process Model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions
MHHS-DIN-82 |  | N/A | 2023-02-09 | SI Design | 2716 | Rob Short | SI Design | Missing listed number of reports in BPD002 | Related to DIN-81 - BPD002 lists number of reports at step 75, BP002 does not reflect this list, missing PO275, PO214 and PO213 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | This relates to BP020 (not BP002), similar to DIN81, reconcile REP list correction on BP020 at step 75 and 80 and reconcile with BPD020 list of REPs | Process model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions
MHHS-DIN-83 |  | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | BP011 missing PUB-044 flow | A discrepancy with the Interface Catalogue - IF_LIST states MHHSP-IF-044 is sent to Central Settlements, DS, MS, Supplier, LDSO. IF-044 tab states it is sent to Supplier, MDS, LDSO In BP011 the PUB-044 is not sent to DS only Supplier, Settlements and EES |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Add Manage change of segment in LDSO lane on business process BP011C with a PUB-044 flow from step 570 Add new step to BPD011 Interface catalogue is already updated | Process Model correction | Metering Changes | Interface Catalogue | MHHSP-BP011 Change of ConType andor Mkt Segment MHHSP-BPD011 MHHSP-DES138-Interface Catalogue
MHHS-DIN-84 |  | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | DES-138 IF List Tab Consistency | IF_LIST states MHHSP-IF-020 is sent to Supplier onlyIF-020 states it is sent to Supplier, Data Service, Metering Service, LDSOIn BP010, the PUB-020 is sent to Central Settlements, CSS, EES, Supplier, Data Service, Metering Service, LDSO.This one looks like its just the Interface Catalogue that needs updating. IF-020 Updated to refect new agreed Routing |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated parties receiving PUB-020 in the IF_LIST, updated PUB-020 routing to include MDS for Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-85 |  |  | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory |  | Elexon see DIP qualification for new users being part of market entry post-programme, but want to understand how MHHSP will operate qualification during the programme. This is likely to cover the majority of participants. Discussions with SRO colleagues indicate they are assuming this is a process for the Enduring Service Operator to define. Challenge applies to non-BSC DIP participants (e.g. adaptor providers), and considerations under Issue Group 101. SI design has spoken to at least 4 participants who are operating in this space and seeking to understand how they can engage with SIT and other programme activities as a DIP connection provider (E2E Architecture - 3.3.2) |  | Closed | [5 empty] | To be handled as part of the Placing Reliance document | No Change | Qualification | Qualification | New Process - DIP Qualification for New Users
MHHS-DIN-86 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Invalid Market Segment BP011C requires SMRS to notify the Supplier of an invalid market segment. RegService requirement RS0124 states that SMRS must derive a value for Market Segment based on Connection Type and Meter Type following a Change of Metering, Change of Connection Type (Change of Unmetered Indicator) or Change of Related MPAN relationships. Given that SMRS determines segment as above, when would an invalid market segment occur, giving rise to the processes from step 560 in BP011C? Further, upon receipt of a PUB-045 Market Segment Invalid Advisory Notification, what are the next steps for a Supplier to address the issue? There are no provisions in the IF-025 for Suppliers to update Market Segment. |  | Closed | [5 empty] | Part of ongoing discussions with Code Drafting team 20/4//23 Code Drafting believe an update needs to be made to the design to update Market Segment via IF-25. This could occur when a Supplier is trying to arrange a change of segment but one of the activities has not completed on time eg the new metering has not been notified. When Registration Service tries to evaluate the segment it may not be compatible. Notification would then go to Supplier to prompt them to chase the required update, in this example chasing the Metering Service to provide the new metering details. Another example is if the LDSO has not notified a change of connection type. The Supplier may also need to send a further SEG appointment if the original has lapsed. | No Change | Metering Changes | Change of Connection Type and/or Market Segment | MHHSP-BP011, MHHSP-BPD011
MHHS-DIN-87 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory | Process clarification for meter removal and de-energisation on same job | Energisation Process Clarification BP009 states that change of energisation status at the same time as meter works means that BP008 will be followed - what is the process when a meter removal and de-energisation are carried out in the same job? Are both D0139 (de-energise) and D0142 (remove meter) and relevant DIP interfaces required. At the moment MEMs only have to send flows relating to meter removal |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Purple Boxes added in BP009 and BP008 to make it clear that Remove/DeEn could still be requested and carried out but MS would need to send two interfaces. Also that DeEn did not need to be notified if meter works completed within same day (ie same rules as today) | Process model correction | Metering Changes | Change of Metering | MHHSP-BP009 MHHSP-BP008
MHHS-DIN-88 |  |  | 2023-02-09 | RECCo |  | Sarah Jones | Regulatory | Update to Incumbent MS provider for Lapsed Appointments | Update to Incumbent MS provider for Lapsed Appointments Currently BP002 only addresses the positive confirmation of de-appointment from RegService (PUB-037 - step 140/231), but if there is no secured active, there is no subsequent notification to the incumbent. The prospective MS receives a PUB-035 at step 225. How should the incumbent MS determine when the de-appointment has lapsed? |  | Closed | [5 empty] | Part of ongoing discussions with Code Drafting team. It is not expected that the incumbant share the MTD via the IF-035 as early sight. IF-37 is the deappoint code they need to reflect . The Metering Service is appointed until they get de-appointed using a PUB-037. They are only receiving the PUB-035 as notification of who to send MTDs to, it is not intended as a notification of de-appointment. Incumbent Metering Service is a term used to refer to the MS appointed at the point another new SP Appointment is accepted (MS or DS), it shall be the Incumbent Metering Service's responsibility to share MTDs (ADV/Trad) to the incoming party. No change recommend CLOSE
MHHS-DIN-89 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Customer Details on De-Appointment The MHHS design currently allows for customer data to be deleted or obfuscated by MS on de-appointment. Has obfuscation been confirmed as acceptable under GDPR? |  | Closed | [5 empty] | Programme has called out the need for data management wrt GDPR. It is for each participant to determine the action required based on their own GDPR Guidelines and policies. |  | All Areas
MHHS-DIN-90 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | MS Appointment for Associated Export Metering Points How will an initial MEM be appointed for a new export MPAN, created post MHHS go live? |  | Closed | [5 empty] | Part of ongoing discussions with Code Drafting team - this is not a Design Issue. Design will operate as described below: The daily process monitoring (BP011C) would pick up any [new] Linked Export MPANs and ensure that the same Metering Service is appointed as the Import MPAN. If the Export MPAN is not linked, then the BAU appointment process can be followed. |  | Metering Changes | Change of Connection Type / Market Segment | MHHSP-BP011, MHHSP-BPD011
MHHS-DIN-91 |  | N/A | 2023-02-10 | AWS | 2858 | Duncan Parsons | Software Provider |  | Document MHHS-E2E001 section 3.6 Actor Workflows Summary - Typo in the MSA Outbound. States IF-04, this should be IF-041 |  | Implemented |  |  |  | Interim Release 1 |  | Reference Corrected | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-92 |  |  | 2023-02-14 | RECCo | 2903, 2805, 2911 | Sarah Jones | Regulatory |  | Customer Direct Contract Flag (D053) Multiple tickets - RECCo, ESG and National Grid - all highlighting the same problem. The 4.7 artefacts do not consistently reflect the agreed position that the Customer Direct Contract flag can only be set by the incumbent Metering Service provider. The validation rules on the IF-038 should be updated The requirements for MS (013) and DS (34) in the respective BRS artefacts should be aligned |  | Implemented |  |  |  | Interim Release 1 |  | Added validation rule REG1075 to IF-038 in the interface catalogue Updated requirements in MS-013 and DS-034 in BRS to reflect the agreed position for D053 1/3 - ticket #3035 - SCS supportive of this change, need more detail. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue, BRS001, BRS002
MHHS-DIN-93 |  | N/A | 2023-02-14 | Power Data Associates |  | Tom | Data Service Provider | Work off Plan D-034D updates for exceptions to Unmetered Supplies | Work off Plan D-034D updates for exceptions to Unmetered Supplies |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | 1. Section 2.3 of MHHSP-METH004-UMSDS- EM Functions will be updated to make explicit that the following data items are not required by the UMSDS and as such will be ignored. • Consent Granularity (T4-COM-1857) • Domestic/Non-domestic Indicator (T4-COM-1830/1850) • Distributer Id (T4-COM-1826/1842/1845/1858/1859/1864/1865/1871/1875) • DUoS (T4-COM-1856) • LLF Data (T4-COM-1856) • Domestic Premise Indicator (T4-COM-1830/1850) • Metered Indicator- (D-045) 2. MHHSP-METH001- SDS Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 3. MHHSP-METH002- ADS- Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 4. MHHSP-METH009- UMSO Method Statement should be updated to make explicit that the following data items are not required by the UMSO and should be ignored (list to be reviewed and validated). • Consent Granularity • Domestic/Non-domestic Indicator • Distributor Id • DUoS • LLF Data • Domestic Premise Indicator • Metered Indicator | Method statement correction | Supporting Docs |  | MHHSP-METH004-UMSDS MHHSP-METH001- SDS MHHSP-METH002- ADS MHHSP-METH009 - UMSO
MHHS-DIN-94 |  |  | 2023-02-16 | ESG | 2777 | Patricia | Software Provider | IF-005 rejections | The IF_009 has 2 event codes: [MPANDisconnection] & [CSSDeRegistration]. [CSSDeRegistration] is listed as having Supplier as Secondary routing however on BP007 there is only reference to the supplier receiving the [MPANDisconnection] flavour of the flow. Please can you clarify which artefact is accurate. MHHSP – BPD009 step 145 states Where the Registration Service has rejected the metering update the DIP will publish the rejection to metering services. Supplier have the option to subscribe to this also. Your response was:- Our reading of this is that regservice will reject the PUB-006 back to sender if the IF-005 fails those rules. So just back to sender, not always meter service or supplier Therefore, does the BPD009 step 145 need to be updated to reflect that as the IF005 can only be generated by Metering Service Smart (MSS) & Metering Service Advanced (MSA) not the Supplier |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Question 1. Supplier will receive both events as outlined in BP007 (See DIN 294) Question 2. A decision was made at the DRG on 29th June to leave the messaging in BPD009 step 145 and instead update the business process model in BPD009 to give Supplier's the option to subscribe to rejections. | Process Model correction | Metering Changes | Change of Metering | MHHSP-BP009 – Change of Metering (Install / Remove / Exchange) , MHHSP-BPD009 MHHSP-DES138-Interface Catalogue
MHHS-DIN-95 |  |  | 2023-02-20 | SI Design | NA | Simon Harrison | Programme |  | Typo in the Note box about Auto Alignment of Related/Linked MPANs on the BP002 and BP003 process maps. Change 'Regisatration' to 'Registration' |  | Implemented |  |  |  | Interim Release 1 |  | Update BP002 (& BP003) call out box, also for BPM002 and BPM003 (Forward Migration) | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-96 |  |  | 2023-02-21 | SI Design | 2973 | Arif Jagot | Programme |  | Test-078 - SUPPI -Primary - Means SUPI? |  | Implemented |  |  |  | Interim Release 1 |  | Update Interface Catalogue | Data interface correction | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-97 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.4 | Typo in MHHS-METH001-5.4c "and less than 90 days months different from the UTC Date" - propose removal of months |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update Method Statement i.e This needs to be 90 days not 90 months the artefact needs to be updated | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-98 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.5 | Typo in MHHS-METH001 - 5.5 SDS shall use the most recent data a based on the event that triggered the |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Typo error on clause 5.5 within MHHSP-METH001-SDS Validation Estimation v5.0 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-99 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Working days correction | Clarify that Step 105 in the CoS Transfer read process is Working Days. Currently states 5 days |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Checked with SRO - 5 Working days for Step 105 in process, BPD003C, BR-DS-024.1 and BR-DS-024.2 | Requirement correction | MPAN Ownership | Data Services | MHHSP-BRS001 - SDS Requirements MHHSP-BP003C - Transfer of Reads MHHSP-BPD003C - Transfer of Reads
MHHS-DIN-100 |  |  | 2023-02-21 | RECCo | NA | Sarah Jones | Regulatory | BP002 to include LDSO as recipient | Step 180 in BP002 and BPD002 does not include LDSO as recipient of traditional meter details as per the wording of the step or the BRS (BR-MS-024) (Code Drafting Log Reference CDD-29) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update BP & BPD to align with BRS and add LDSO as recipient of MTDs Updates to BP & BPD002 Forward migration for consistency | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Metering Service MHHSP-BPD002 Forward Migration BP002 and BPD002
MHHS-DIN-101 |  | DI-120 | 2023-02-22 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. (Raised as DI 120) |  | Closed | [5 empty] | Included within CSS validation rule update. DUPLICATE See DIN-172 | No Change | MPAN Ownership |  | MHHS-DES138-Interface Catalogue
MHHS-DIN-102 |  |  | 2023-02-22 | St Clements | 2886 | Madison Layton | Software Provider |  | SCS raised the following under MHHS-DIN-7 "MPRS will reject any PUB-031 inlcuding those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist"" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8)" They have followed up with: Just found the change that corresponds to this one in v4.7 interface catalogue – REG0005 in IF-031. Could this also be added to IF-034 so that we can apply the same validation on MDR updates? |  | Closed | [5 empty] | Proposed Change: Add validation "CSS Registration Request ID [DI-849] is valid for Registration Service", with error REG0005 - "CSS Registration Request ID [DI-849] is invalid or unknown" This mirrors a change made in v4.7 to IF-031, agreed as part of the DAG baseline of v4.7 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-103 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory |  | Confirm that D0381 will continue to be used for updates to MPL address. BP010 & BPD010 currently allow emails, SDEP and other agreed forms can be used by Supplier or UMSO to update this - propose that these artefacts are amended to reflect that the D0381 is to be retained (Code Drafting Log Reference CDD-22) |  | Implemented |  |  |  | Interim Release 1 |  | Amend Steps 10, 21, 22 to explicitly use the D0381 rather than current wording | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-104 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Impact of MHHS on SoLR arrangements | Impact of MHHS on SoLR arrangements - possibly needs an Issue Resolution Group discussion to undertake evaluation & impact assessment (Code Drafting Log Reference CDD-23) |  | Closed | [5 empty] | Extensive discussions have been held with Elexon (DIP Manager) to ensure that there is flexibility within the DIP Design to accomdate varied SoLR scenarios. These involve the existing process(s) around change of BMUnits and the ability to transfer ownership of DIP Market Participants. As the solr process does not involve any mass movement / reassignment of MP Identifiers at the MPAN level the core MHHS design is not impacted by Solr per se. |  | All Areas
MHHS-DIN-105 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Related MPAN Business Rules | 1) IF-019 suggests RMP status can be Created or Operational - proposed this can only be Operational for subsidiary MPAN 2) Add validation rule to IF-019 requiring related MPANs to have consistent classification as domestic or non-domestic (reflecting the existing requirements) 3) Clarify what Registration Services should do when MPANs are related/linked and have different MS/MEM providers - is the IF-019 rejected or the MEM for the secondary MEM auto-deappointed? 4) What happens if the IF-019 fails validation by Reg Service at Step 330 in BP010? Design provides no guidance |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | 1. Removed reference to Created in the REG1001 validation rule for IF-019 2. We understand there is no existing validation within MPRS and this is not being amended as a result of MHHS implementation. This would require a wider industry change impacting CSS as Domestic Premise Indicator is managed independently of Related MPANs. 3. It would not be rejected, auto-alignment would pick up the discrepancy at the next daily run and de-appoint the export MS and appoint the import MS. 4. As with other rejected flows, the sending party should investigate the error and re-submit as appropriate. | Data interface correction | MPAN Ownership | Change of Registration Data | MHHSP-DES138-Interface Catalogue
MHHS-DIN-106 |  |  | 2023-02-23 | SI Design | 2955 | Kate Goodman | Testing | IF Routing | Inconsistency in DES138 for UMSO Routing 00-Introduction logs UMSO as the single routing option for Unmetered Service provision, as there can only be one UMSO related to an MPAN PUB-008 provides UMSC, UMSP and UMSI as options for secondary routing This inconsitency needs to be corrected |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | IF-008 - Secondary routing rules updated following review with Avanade (see DIN268) |  | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-107 |  |  | 2023-02-24 | SI Design |  | Simon Harrison | Progamme | Update to definition of DI-301 LLF ID in the ESC Reporting Data Catalogue | Definition of DI-301 in the ECS Reporting Data Catalogue needs to be updated as follows 'The Unique Identifier of a set of Line Loss Factors' |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Update to be made in the ECS Internal & External Reports - Data Catalogue tab against DI-301 LLF ID it should read as 'The Unique Identifier of a set of Line Loss Factors' | Data interface correction | Supporting Docs | Reporting Catalogue | MHHSP - ERI011A - ECS Reports - Internal v5.2 MHHSP - ERI011B - ECS Reports - Enternal
MHHS-DIN-108 |  |  | 2023-02-27 | SI Design | 2966 | Kate Goodman | Testing | IF Routing | Ref:MHHSP-DES138-Interface Catalogue v4.7, IF-038, PUB-020, PUB-039. Document says that UM is relevant to these messages but UM thinks it is not relevant. Please clarify what the situation is. Raised in review of MHHSP-872 by Power Data. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Covered by Secondary routing updates (See DIN268), changes to IF-020 and IF-039 routing. No changes were required to IF-038. The design allows for Customer Direct flags to be set for any Data Service/ Metering Service (ie Including unmetered). |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-109 |  |  | 2023-02-27 | SI Design |  | Simon Harrison | Programme |  | Call out box in BP002/BP003 on Linked/Related MPANs needs to be updated as it includes reference to email/SDEP rather IF-019 as shown in BP010 |  | Closed | [5 empty] | Confirmed - the call out box on BP002/003 needs to be updated Duplicate of DIN-64 | No Change | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service
MHHS-DIN-110 |  |  | 2023-02-27 | SI Design | 2983 | Kate Goodman | Testing |  | MHHSP-BP005-Data Processing-v4.6, Step 50-160 UMSDS is referencing Submit Required UTC period level consumption data (Step 50) with a arrow going to Receive UTC period level consumption data (Step 160) but no reference of IF-021 on the connection between both - reference should be added? |  | Implemented |  |  |  | Interim Release 1 |  | On Process map requires arrow to be labelled as IF-021 from step 50 to step 160 | Process model correction | Meter to Bank | Data Processing | MHHSP-BP005-Data Processing
MHHS-DIN-111 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Originally raised as T4-COM-1691 on 15th Sept 2022: "MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days " Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5 (Raised as DI-76) |  | Implemented |  |  |  | Interim Release 1 |  | Updated to 2 working days | Requirement correction | MPAN Ownership |  | MHHS-BRS003-Registration Service requirements
MHHS-DIN-112 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54 (Raised as DI-77) |  | Implemented |  |  |  | Interim Release 1 |  | Added note to clarify | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-113 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? (Raised as DI-78) |  | Closed | [5 empty] | Agreed duplicate of DIN-29 and can clsoe | No Change
MHHS-DIN-114 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | EES does not appear to have been added to the routing rules tables on the interface tabs(Raised as DI-79) |  | Closed | [5 empty] | Already present in v5 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-115 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On IF-050, this includes linked MPANs in it, but I don’t think these would ever be populated as you cannot link MPAN at MPAN creation. So EES would only ever get Linkage updates on the IF-20 Is there any value of having this therefore in IF-050?(Raised as DI-80) |  | Implemented |  |  |  | Interim Release 1 |  | Removed Linked MPANs and Related MPANs from IF-050 and added explanatory note | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-116 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | For IF-025, block B032 it states it is "MPAN Legacy Info (Mandatory where event is [SSCandProfileClass], and for Traditional Meters / Optional for other Meters)" It should just read mandtory for event code [SSCandProfileClass] and nothing else, it should not be optional for any of the other event codes(Raised as DI-81) |  | Implemented |  |  |  | Interim Release 1 |  | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-117 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?(Raised as DI-82) |  | Closed | [5 empty] | Discussed with SCS and confirmed it is a limitation of swagger output but should be array of MPAN followed by array of meters followed by array of MAPs repeated per MPAN. Awaiting confirmation can close | No Change | Metering Changes | IF-005 JSON | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-118 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | In relation to the Sender Unique Reference, which is constructed as: S-<Interface>-<Participant Id>-<Role Id>-<Date>-<Sequence> (hex) I would like to comment as follows: • Why is the Unique Reference simply constructed using elements that are already contained in the message as distinct values? This just means the sender has to construct it and the receiver de-construct it? • Is the sequence number expected to be reset each day ? • It would be much easier and more logical for the Sequence to be a distinct item in the message? • Why is the sequence specified as hex? • Even given the expected large number of messages, and based on it being a number(13) (defined as Sting), a standard sequence number per Participant and Role would provide 9,999,999,999,999. If this is still seen as a limitation then it could simply be built from the date, e.g. 202301190000000001, giving a provision for up to 9,999,999,999 messages PER DAY from the same Participant / Role combination, which still enables a read every 30 minutes from every MPAN(Raised as DI-83) |  | Closed | [5 empty] | This is to send a unique reference and is used for auditing purposes. Please note the length of the Sender Unique Reference has been increased at the request of Avanade in 5.1.1. Examples updated |  | MPAN Ownership
MHHS-DIN-119 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | in swagger hub under IF-002 B907 list the B036 block, this is missing numberOfDigitsCumulativeRegister data item(Raised as DI-84) |  | Implemented |  |  |  | Interim Release 1 |  | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue. Swagger will be updated | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-120 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Inconsistency in naming of data item DI-091 In swagger hub: Number-Of-Digits-Cumulative-Register In interface catalogue IF tabs (E.g. IF-002) : Number of Displayed Register Digits In interface catalogue data catalogue tab: Number Of Displayed Register Digits (Cumulative Register)(Raised as DI-85) |  | Implemented |  |  |  | Interim Release 1 |  | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue and updated YAML accordingly | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-121 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0093 comment raised on 12/01/2023 " D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: "It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42 (Raised as DI-86) |  | Implemented |  |  |  | Interim Release 1 |  | Agreed to provide SEG scenario's in IF-005 Use Case guide. currently under review |  | Metering Changes | Change of Segment | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-122 |  | DI-87 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0084 comment raised on 12/01/2023 following the introduction of IF-019 and respective changes in the latest set of released artefacts MHHSP-BP010-Change of Registration Data -v4.5 "Shows Supplier Mastering Import Export Linkage. BSC CP1558 introduced changes to MPRS for the LDSO to manage this via the DB05. IF-019 should go to LDSO who should then produce a DB05 into MPRS." The process diagrams and requirement spreadsheets have been amended to show MPRS loading DB05 as a IF-019 response. DB05 is not a IF-019 response, it is a request from DNO/iDNO to create, amend or remove a import/export linkage. It does not currently have any capacity to include a IF-019 rejection response to trigger a IF-020 rejection response to DIP. (Raised as DI-87) |  | Implemented |  |  |  | Interim Release 1 |  | SCS reviewing preferred option with LDSO's The following changes would be required to the LDSO overview requirements: MHHS-BR-LD-043.3 LDSO Send Import/Export relationship update LDSO must send accepted Import/Export relationship updates to the Registration Service via the appropriate interface DB05 file or other agreed mechanism BP010B Change of registration data 900 MHHS-BR-LD-043.4 LDSO Send Import/Export relationship rejection LDSO must publish rejected Import/Export relationship updates on the Data Integration Platform using the appropriate interface MHHS-IF-020 to Supplier BP010B Change of registration data 900 On BP-010 for Linked Import/Export MPANs the following would be required: 1. Need to add rejected leg from step 900 to DIP 2. Need to add PUB-020 going from the DIP to the Supplier The BPD-010 will need updating accordingly. | Process Model correction | MPAN Ownership |  | MHHSP-BP010-Change of Registration Data MHHSP-BPD010, MHHSP-BRS005, Traceability Matrix
MHHS-DIN-123 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0083 comment raised on 12/01/2023 following the introduction of a new business rule on MPRS in the latest set of released artefacts MHHS-BR-RS-078 "MPRS cannot control how messages are sequenced at CSS and DSP. IF MPRS waits until the DSP responds before sending the Appointment message this could take hours (as this is a batch process) this will result in a delay in the appointment of the MDR. Sequencing requirements should be placed on CSS & DSP to ensure the correct MDR is appointed based on Effective dates provided from MPRS. However, they may not be necessary due to the way this interface works: The C0200 interface uses the PUT Method, which will replace the data held at CSS. Explicit ending of an Appointment is only required for a future dated appointment, this will be sent as one message with the Old and New MDR appointments. For Same Day or Retrospective the new MDR Appointment will Replace the currently set value. This implicitly ends the previous MDR Appointment. On a CoS, the MDR is linked to a Registration not a Metering Point. The previous MDR will end naturally when the Previous Registration becomes securedInactive. An explicit message to end the MDR appointment on the Previous Registration is not required . MPRS will only send two separate updates to CSS when there is a gap in MDR (SDS) appointments. For Example a change of segment to Advanced and then back to Smart. This would need to happen over a short period to generate two messages that could go out of sequence" The MHHS design team rejected with comment "The MHHS design is based upon what was agreed as part of the R044 consultation. This scenario does not reflect our understanding of how the CSS/DCC/DSP interface will work as set out under R044. " This is how C0200 currently works today and the interface is unchanged in R0044. This will put a signfiicant requirement on MPRS that will reduce time available time for other core MHHS development activities with no benefit to industry.(Raised as DI-87) |  | Closed | [5 empty] | No Change - updated in v5.0 | No Change | MPAN Ownership
MHHS-DIN-124 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0089 comment raised on 12/01/2023 "D-021 was meant to give more detail on how L1-L4 validation should be used and provide more error codes for use. This has not been done as far as I can see Blocking resolution to this T4-COM-1749, T4-COM-1769 and T4-COM-1768" Comment was closed as clarified however none of these items have been resolved and we have no dates as to when they will be. comments blocked that were raised initially on 15/09/22 Comment T4-COM-1749: "The Registration Service, as part of its L3/L4 validation should ensure that there is consistency between the data content of the IF-033 issued to the Service Provider and the [returned] content in IF-034 - if this isn't so then message should be returned to Service Provider using ""MSGStatus Message"" mechanism." Does MPRS only need to validate consistency in the data it loads on the IF-033, not the data that is not loaded" Comment T4-COM-1769: "We need validation rules to be defined for this flow, Does not match IF-031, content of the PUB-034 does not match the IF-031. No Proposed Appointment Found, PUB-034, does not link to any Pending IF031s. Define Validation Rules for PUB-034 The 034 content must match the original if-031 content the 034 must have a corresponding IF031 the 034 has already been received for the IF-031 Generic Standard Validation, MPAN exists valid in ISD ETC" Comment T4-COM-2768: "We need some generic codes for standard validation rules such as: Service/Supplier is valid in ISD MPAN exists in MPRS MPAN is not Disconnected Service/Supplier is Valid in MDD (so CSS doesn’t reject updates)" (Raised as DI-89) |  | Implemented |  |  |  | Interim Release 1 |  | Added RMP status check to IF-034 and refined validation rule notes regarding different values received from IF-033 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-125 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | IF Routing | WOA-0091 comment raised on 12/01/23 D-030 "how routing will work in the DIP has not been updated this information is required for our development" MHHS Design Team has closed as clarified however there is still uncertainty around the DIP routing, and there are not dates provided for when the detailed DIP design will be released. This will clock certain elements of development (Raised as DI-90) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Secondary routing rules updated following review with Avanade (see DIN268) |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-126 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0092 comment raised on 12/01/23 following more infromation around D-022 being clarified "D-022 Following the work off item being agreed on what is required for an MPAN to be traded - it has now been possible to fully assess the optionality of data items in the interfaces Data items still mandatory in interfaces that must be changed to optional: Annual Consumption (IF-001) Incumbent Service Providers (IF-002, IF-033) Incoming MS/DS (IF-037) These are not required at creation, nor at traded, and therefore could be non existent in MPRS when MPRS generates this outgoing IF messages Blocking resolution of T4-COM-1727 and T4-COM-1735" Closed as clarified however none of the issues listed have been resolved Annual consumption still reads madatory on a CoS for IF-001, the issue is MPRS may not have this data item. The item is not required to reach a status of traded, therefore CSS will accept a CoS on this MPAN without annual consumption being populated, and then MPRS will not be able to provide this data item on the IF-001 that results from the CoS. This must be changed to optional OR the definition on what is needed to be traded should be updated to include annual consumption. Incumbent Service Providers is still mandatory on IF-002 for CoS Again as MS is not required to be traded, CSS will accept a CoS request with or without a current MS, and so MPRS will not be able to provide an incumbent MS in these cases. It must be changed to optional or the definition of what is needed to be traded should include MS. Incoming MS/DS is still mandatory on IF-037, there are numerous reasons an appointment may be lapsed, the only change that would gaurantee a new incoming SP that MPRS could send on this flow is a change or SP (CSERV) scenario. For CoS the supplier may not have sent in new appointments, for DEREG there will be no new appoitnments, for SEG the market segment may have changed but the supplier may not have sent in new appointments, same for change of connection type, and for IMPEXP and RELATED the parent MPAN might not have MS/DS appointed at all so there would be no new appointments for MPRS to populate on this flow. This must be changed to madatory ONLY on CSERV (Raised as DI-91) |  | Implemented |  |  |  | Interim Release 1 |  | Discussed with SCS. Covered by clarification on nullable and interface notes- All these issues are resolved by the Mandatory Nullable Solution. Confirmed Annual Consumption block will only be provided where available in Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-127 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 "DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least "Registered", if no DS is appointed then there is already an appropriate Event Code" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone (Raised as DI-92) |  | Closed | [5 empty] | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-128 |  | DI-93 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0095 comment on 12/01/23 "D-009 This is blocking closure of T4-COM-1730. There is a lack of clarity around the treatment of rejection from CSS, between both R044 and the MHHS design artefacts e.g. MHHs-BR-RS-088.1 and MHHS-BR-RS-079 both suggest MPRS would still load the new MDR record and appoint in MPRS despite a rejection from DCC/CSS. Our assumption would be that we do not load a MDR appointment that is rejected from DCC/CSS and we send the IF-035 rejection to notify the DS/Supply of this. However no clarity on what to do if DCC/CSS rejects a MDR end date on a de-appointment T4-COM-1730 was raiseed on 15/09/22 MHHS Design Team Rejected the comment with a statement this is outside of MHHS Scope. How MPRS treats the MS/DS appointment and how it responds over hte DIP is within MHHS design. The requirements we are enquiring about are already included in the MHHS design documents as in scope also. This is a major blocker to MPRS design on MDR appointment processes (Raised as DI-93) |  | Closed | [5 empty] | Discussed with SCS this is a REC requirement. Agreed no error codes will be received, just use a generic response. | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-129 |  | DI-94 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0086 comment on 12/01/23 following the release of the first draft of IF-050 in the revised interface catalogue artefact "Related MPANs and Linked Import Export are not set at MPAN Creation. EES can get these on the IF020 Remove these blocks from IF-050 as they would never be populated" MHHS design team marked as accepted and changed but the blocks still exist in IF-050, these blocks will never be populated and so should be removed from the IF-050 interface(Raised as DI-94) |  | Closed | [5 empty] | Closed - duplicate of DIN-115 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-130 |  | DI-95 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0088 on 12/01/23 "D-011 & D-050 it is still unclear how LLFC and DUoS Tariff ID will be stored and managed in MPRS. DUoS should be an Alias of LLFC and not have its own data item in MPRS. LLFC will be renamed to DUoS Tariff when the old arrangements have ended. LDSO impacts having to maintain two items which will lead to billing issues" Marked as clarified and closed witih a clarification statement to be issued on tuesday 24th January, this clarification statement was not received. Awaiting clarification(Raised as DI-95) |  | Closed | [5 empty] | Email to Madison to check can close |  | MPAN Ownership
MHHS-DIN-131 |  | DI-96 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 is missing business rules: REG1001 - MPAN [DI-063] is at [REG.RMPStatus] not status Created/Operational. This should apply to IF-025. IF-025 is missing a rule that consent granualiry EFD must not be earlier than supply start date. Consent Granularity EFD must not be prior to current consent granularity EFD The Consent Granularity Energy Direction Domestic Premise Indicator Combination must be valid in ISD(Raised as DI-96) |  | Implemented |  |  |  | Interim Release 1 |  | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-132 |  | DI-97 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 IHD update does not include validation rule 1019, does this mean IHD EFD can be prior to current and effectively cancel out the current IHD status completely, or is it just an error and the rule should be added to interface catalogue for IHD?(Raised as DI-97) |  | Implemented |  |  |  | Interim Release 1 |  | Amendment accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-133 |  | DI-98 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 will not allow a SMSO to be set for a non smart meter "REG1022 - SMSO ID Cannot be set where Market Segment is [Reg.Segement]", would a non smart supplier be able to send a B031 SMSO block, they will need to be able to if they are required to clear an old SMSO by populating SMSO as null(Raised as DI-98) |  | Implemented |  |  |  | Interim Release 1 |  | Added new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-134 |  | DI-99 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 "SSC must be valid in ISD. Rejection reason: REG1044 - SSC must be a valid value in ISD" SSC are not yet populated in ISD(Raised as DI-99) |  | Closed | [5 empty] | Clarified that SSC validation will be based on Frozen MDD. Seperate DIN to cover availability of ISD | No Change | MPAN Ownership |  | MHHSP-EM021 ISD Entity Data Map, MHHSP-DES138-Interface Catalogue
MHHS-DIN-135 |  | DI-100 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Should B032 PC and SSC block on IF-025 only be permitted when theres a traditional meter fitted at the MPAN?(Raised as DI-100) |  | Closed | [5 empty] | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-136 |  | DI-101 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | How is the Green Deal Exists defined. Does this mean there's a green deal linked to the MPAN regardless of dates, does it mean there's a green deal currently active or due to become active, or does it mean there is a currently active green deal assigned to the MPAN? (Raised as DI-101) |  | Implemented |  |  |  | Interim Release 1 |  | Remove Green Deal exists (DI-110) from Data Catalogue and IF-050 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-137 |  | DI-102 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-007 Validation rule "Metering Service [S0.SenderID] holds valid previous appointment then Energisation Status EffectiveFrom Date [DI-034] should be < [REG.App End Date] + 10" The way it's curently written suggests MPRS should accept an IF-007 from the previous appointed MS, event if there ETD was greater than 10 days ago, provided the ES EFD date was less than their ETD + 10. E.g the previous MS could send IF-007 two years later with ES EFD of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then a separate rule should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? Linked to DI-41(Raised as DI-102) |  | Implemented |  |  |  | Interim Release 1 |  | REG1003 validation rule updated in IF-007 to constrain energisation updates to 10 days after the MS appointment period |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-138 |  | DI-103 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-034 Submitted rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD |  | Closed | [5 empty] | Duplicate of DIN-176 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-139 |  | DI-104 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Need clarity on what role code should be used in C0200 for MS and MDR appointments Linked to comment T4-COM-1790 which was accepted as design issue raised but then moved to a work off item "We would like to see some indicative Role Codes and DIP IDs so we can populate development systems with this data " |  | Closed | [5 empty] | Send "MDR" as role code as per Registration requirement. Allocation of DTN MPIDs is a seperate issue | No Change | Registration | Existing EMAR I/F | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-140 |  | DI-105 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 |  | Closed | [5 empty] | Discussed with SCS the IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR. Agreed to close | No Change |  |  | MHHSP-BP003A, MHHSP-BRS003 Registration service requirements
MHHS-DIN-141 |  | DI-106 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 |  | Closed | [5 empty] | RECCo consequential change | No Change |  |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-142 |  | DI-107 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | There currently aren't sufficient rules to ensure that a principal primary MPAN is not also a linked export subsidiary MPAN or that a subsidiary secondary MPAN is not also a principal import linked MPAN. The MHHS design either should accommodate both (would need clarity on how to treat cases where MPANs are BOTH principal and subsidiary) OR new rules should be introduced to prevent this occuring AND cleanse existing cases ahead of migration |  | Implemented |  |  |  | Interim Release 1 |  | Validation rules updated for IF-019 | Missing/incorrect validation rule | MPAN Ownership |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-143 |  | DI-108 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Requirements were uplifted in v4.5 to include logic around market segment on related MPANs MHHS-BR-RS-124.1: Registration Service must, in the case of Related MPANs and following derivation of Market Segment for individual MPANs, update the Market Segment for the Primary MPAN and all the Secondary MPANs based on the following rule: 1. If any MPAN in the Related MPAN Group has a (derived) Market Segment of Advanced, then set the Market Segment for all the MPANs to Advanced and set the Market Segment Valid Flag to "Yes" for all the MPANs This specifically cites related primary/secondary and does not mention linked import/export associations at all. But then another requirement implies maybe it should have done: MHHS-BR-RS-127: Registration Service must , in circumstances where the derived market segment is invalid (and has not been overridden by Linked/Related MPAN logic ) Should MHHS-BR-RS-124.1 have applied to linked import/export associations too or is it intended solely for primary/secondary related MPANs? |  | Implemented |  |  |  | Interim Release 1 |  | This should only apply to Related MPANs. Updated RS-127 | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-144 |  | DI-109 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131 This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to: Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. |  | Closed | [5 empty] | Duplicate See DIN-169 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-145 |  | DI-110 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. |  | Implemented |  |  |  | Interim Release 1 |  | Added L as valid value for DI-979 in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-146 |  | DI-111 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. |  | Implemented |  |  |  | Interim Release 1 |  | Agreed with SCS to reuse STD Error Response Section in IF035 to communicate Lapsed Reason . See DIN-145 for summary of updates | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-147 |  | DI-112 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-008 response block is listed as mandatory, however on disconnection the MPAN is de-energised by MPRS automatically. The supplier cannot de-energise after disconnection on the IF-007, it must be automatic at MPRS as per The de-energisation needs to be communicated on the IF-008 but it is not in response to an IF-007 and so we cannot populate the response block. |  | Implemented |  |  |  | Interim Release 1 |  | Data interface change agreed. Added Interface note to IF-008 to cover forced de-energisation changes by Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-148 |  | DI-113 | 2023-02-10 | St Clements | 2864 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-113 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { "confirmingMpid": "string", --* "registrationId": "string" --*, "updateSucceeded": boolean --* } Suggest that DI-0980 is removed from B066 |  | Closed | [5 empty] | Discussed with SCS and agreed to close - note no error codes returned from CSS so will provide generic error code | No Change |  |  | MHHSP-DES138-Interface Catalogue, JSON, YAML
MHHS-DIN-149 |  | DI-114 | 2023-02-10 | St Clements | 2865 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-114 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 On IF-038 validation "REG1073 - Customer Direct Contract already exists for MPAN [DI-063] for that period" The respective validation rule for this states: If Contract End Date [DI-145] <= Max existing active MS contract end dates [Reg.MAX_DCMS_Enddate], EXCEPT IF requesting MS [S1.SenderID] = Currently Active Direct MS [Reg.CurrentActiveDC_MS_DIPID] AND Contract End Date [DI-145] <= existing active MS contract end date [Reg.CurrentDCMS_Enddate] This rule doesn't fully prevent overlapping appointments as does not cover where the MS is not currently contracted MS and ETD > current ETD which should also be rejected. Think a simpler rule would cover this scenario more fully e.g. If there is an active contracted MS/DS, and the submitting MS/DS does not match then reject And then ETD can be greater or later than current ETD for the currently contracts MS/DS anyway so doesn't need specifying? |  | Closed | [5 empty] | SRO Team do not believe that a change is required. Linked to DIN-554 |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-150 |  | DI-115 | 2023-02-10 | St Clements | 2866 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-115 in our log In some place on IF-038 tab there is reference to a future customer direct contract e.g. "OR requesting MS [S1.SenderID] <> Any future Direct MS [Reg.FutureDC_MS_DIPID] " "extended dates will be subject to checking if another Service Provider has registered a separate Customer Direct Contract covering the same period" - this can only happen if there's a future appointment "AND ALSO removing all future periods which may or may not have been accepted and recorded previously." As there is no Effective From Date included in the flow MPRS will store an Effective From Date of the system date at the time of creation of the customer contract indicator. It will not be possible to set one to start in the future as the IF-038 does not include effective from date. Is this the same understanding as the MHHS Design Team? |  | Closed | [5 empty] | As per DI-149 above SRO Design Team do not belive that any changes are required |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-151 |  | DI-116 | 2023-02-10 | St Clements | 2868 | Madison Layton | Software Provider |  | Just spotted a change in v4.7 and raised in our log as DI-116 Artefact: MHHSP-BP010-Change of Registration Data -v4.7 under MPL and GSP Group amendment section, DB02 has been amended in v4.7 to DB002. DB002 is not correct, DB02 was the correct name For reference the DB flows only ever have one 0 in, there is DB01 (MPAN creation), DB02 (MP updates), DB03 (Disconnection) and DB05 (Import/Export Linkages) |  | Implemented |  |  |  | Interim Release 1 |  | BP010A step 10 flow name change to DB02, BP010B step250,step440, Step560 flow name change to DB02, and update BPD descriptions to DB02. | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-152 |  | DI-117 | 2023-02-14 | St Clements | 2912 | Madison Layton | Software Provider |  | On looking more closely at the validation rules for IF-019 spotted a few issues. IF-019 REG-1061 rule for Related Create event code appears to be written incorrectly. The rule and rejection description don't quite align. Rule: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) are not currently part of an import/export relationship Rejection reason: REG1061 - Prosposed MPAN(s) [DI-073] / [DI-074] are already part of a Related MPAN Relationship Should the rule read: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) is currently part of a related primary/secondary relationship? The rule and descriptions also don't appear to fully align for some in import/export section too - REG1052, REG1055, REG1057 and might need some minor tweaks to correct. |  | Implemented |  |  |  | Interim Release 1 |  | REG1061, 1052 and 1055 rules updated. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-153 |  | DI-118 | 2023-02-14 | St Clements | 2913 | Madison Layton | Software Provider |  | On working on detailed design for Related MPANs, noticed the IF-019 interface is missing a rule that the Secondary MPAN must not be a Primary in another Relationship. You could expand REG1064 to include this as the description sounds like it should have been covered here. Rule: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN Description: REG1064 - Proposed Secondary MPAN [DI-074] is already part of a different MPAN Relationship Could amend rule to: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN OR [DI-074] is already in a relationship as a Primary MPAN |  | Implemented |  |  |  | Interim Release 1 |  | REG1064 validation rule updated | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-154 |  | DI-119 | 2023-02-15 | St Clements | 2919 | Madison Layton | Software Provider | IF-019 validation gap on primary and subsidiary MPAN | On further detailed design we’ve spotted a potential design gap. Currently it is possible to enter a state where an MPAN is both a primary and subsidiary MPAN at the same time (e.g. Primary but also export linked or Secondary but also import linked). The current MHHS doesn't accommodate an MPAN being in both states at the same time. We’ve already looked to add rules to try to mitigate this on DB02/DB05 internal flows but would need additional rules on IF-019 to fully prevent this scenario occurring. Rules we think are required: 1. On receipt of IF-019 with event code RelatedCreate or RelatedAdd, the primary MPAN must not have energy direction of Export 2. On receipt of a IF-019 with event code RelatedCreate or RelatedAdd, any listed secondary MPAN must not in an active Import/Export relationship as the Import MPAN 3. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Import MPAN must not be in an active relationship as the secondary MPAN 4. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Export MPAN must not be in an active relationship as the primary MPAN |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Agreed with SCS that changes to IF-19 tab would be made to support Rules 1 and 4. Validation Rules updated accordingly with new Error codes (REG1067/1068) created to support. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-155 |  | DI-120 | 2023-02-15 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. |  | Closed | [5 empty] | see also DIN-172/173. Included in 5.1 DUPLICATE See DIN-172 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-156 |  | DI-121 | 2023-02-24 | St Clements | 3078 | Madison Layton | Software Provider |  | We have logged a new design issue under DI-121. IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP |  | Closed | [5 empty] | Duplicate of DIN-173 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-157 |  | DI-122 | 2023-02-27 | St Clements | 3090 | Madison Layton | Software Provider |  | New design issue (SCC Ref DI-122) for the IF-005 related to REC CP R0032. The current v5.0 validation in the IF-005 does not include the new validation introduced with REC CP R0032 (R0032 is approved and being implemented in the D0312 this June): NEW REC CP R0032 Validation: V Rejected – ESME ID already exists within MRPS and does not match Removed Meter, Associated Import/Export MSID or Related MPAN W Rejected - MSN relates to a Smart Meter Type and the ESME ID is NULL X Rejected – ESME ID Format is Invalid Y Rejected – Number of Displayed Register Digits is NULL and the MSN relates to a Smart Meter Type Z Rejected – Non-Smart Meter Type with Number of Displayed Register Digits populated AA Rejected – Meter Location is invalid AB Rejected – Non-Smart Meter Type with ESME ID populated AC Rejected – Number of Displayed Register Digits is incorrect IF-005 Validation: V not covered, needs to be added as a Level 5 Validation Rule W is already covered by DI-085 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) X is already covered in DI-085 population notes (Level 4 validation RCP1023 Msg Contains Invalid Valid Value Combination(s)) Y is already covered in DI-091 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) Z is not explicitly covered, suggestion: add to DI-091 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AA is covered in the population notes AB is not explicitly covered, suggestion: add to DI-085 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AC not covered, Suggestion: add the following population note from R0032 to DI-091: Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” Summary Please add the following Changes to the IF-005 to align it with the D0312 validation and maintain the same level of Smart Meter data quality in the Registration Service: New Level 5 Validation rule for DI-085 implementing V from the D0312. ESME ID must be unique within MPRS unless it’s a Linked MPAN where the same Smart Meter can be shared across Linked MPANs New population note for DI-091, only to be included for Smart Meter Types New population note for DI-085 , only to be included for Smart Meter Types New population note for DI-091, Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” |  | Implemented |  |  |  | Interim Release 1 |  | New Validation Rules added to IF doc to ensure full coverage and alignment with CP Error codes described | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-158 |  |  | 2023-02-27 | Elexon | 2908 | Derek Weaving | Central Body | Use of CCCs to categorise the data for future charges | As part of the Performance Assurance Working Group discussions on Supplier Charges, we are exploring the use of CCCs to categorise the data for future charges. It is noted that Settlement Period Quality Indicator referenced in the VAS Method statement is for illustrative purposes and would welcome clarity on the following: · What is the intended process to populate the Settlement Period Quality Indicator in the initial ISD Table? · What would be the process to be involved in those activities to determine the categorisations should additional CCCs be required? |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | This DIN has been moved to Interim Release 5 as it is related to DIN-409 which has an objection raised that is pending a discussion to clarify the solution. Name change and field length have been actioned. Reviewing whether any changes to Settlement reports are required Recommending a change to this ISD Data Item: Settlement Period Quality Indicator to be set as per Appendix 1 of MHHSP_METH007 MDS_Method_Statement v5.0 This data item need to be changed to something like ‘Valid Settlement Period Quality Indicator Set’ and the field size needs to be increased. The data catalogue will need the revised data item and the field length will need increasing from 20 to at least 100. This Item also appears in some interfaces that will need to be updated. This is because it represents a set of SPQIs. The initial intention is to populate as per the table and check if any new SPQIs have been introduced in the baseline design Method Statement that are not covered. If new CCCs are introduced the appropriate flags for each new CCC would need to be agreed. However, it is likely that another dimension to the table below would need to be introduced to facilitate new CCCs. Word 'Illustrative' to be removed and will be updated to say Valid Settlement Quality Indicator Set. Change to be made across all impacted Method Statements. New CCC's will require a Modification to the BSC interface requirement. Proposed changes have been reverted to the initial state. Data item Settlement Period Quality Indicator, with a field length of 5. This is due to the agreed solution for DIN409 following DRG where it was agreed the list element would be removed in favour of individual row(s). The word 'Illustrative' will also remain within the Method Statements. | Missing/incorrect validation rule | Meter to Bank | Volume Allocation Service | MHHSP-METH006_VAS_Method_Statement MHHSP-METH007_MDS_Method_Statement v5.1 EDI021 ISD Entity spec
MHHS-DIN-159 |  |  | 2023-03-01 | ENWL | 2994 | Paul Band | Network Business | Interfaces for UMSO | DES-138 Interface Inconsistencies vs BSCP7XX for UMSO Discussions with ENWL have highlighted a number of inconsistencies in the Interface Catalogue when it comes to routing for UMSO's. DIN-106 also refers. UMSO is not listed as a recipient in DES-138 for the PUB-008, but this is in the draft BSCP and should be added to the PUB UMSO is not listed as a recipient in DES-138 for the PUB-020, but this is in the draft BSCP - this is not needed in the BSCP as there are no unmetered Related MPANs UMSO is not listed as a recipient in DES-138 for the PUB-035, but this is in the draft BSCP - view that it is unlikely for this flow ever to be used as the appointment will not trigger any processes to need a subsequent update UMSO Is listed as UMSI, not UMSO in PUB-036 in DES-138 UMSO is listed as UMSC, not UMSO in PUB-018 in DES-138 The IF_LIST tab should be reviewed for consistency |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | As with DIN-106, there are inconsistencies in the Interface Catalogue for UMSO routing. This has been compounded by a review of the draft BSCP for UMSO, which has added a number of PUB flows going to UMSO that aren't currently in the catalogue. Covered by updated secondary routing rules (see DIN268) Design to check requirements in BSCP and MHHS BPs and ensure the interface catalogue reflects a consistent approach | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue and possibly related business processes and descriptions E2E001
MHHS-DIN-160 |  |  | 2023-03-14 | Ovo Energy | 2862 | David Morley | Supplier | BP009 flow addition | Steps 205 and 210 in BP009 wont be completable in the event that theres no comms. I think the process would be workable if there was an exception route here - see red arrow below. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update Steps 205 and 210 in BP009 with "Comms Available" line label add flow from step 205 to step 215 with “Not Commissioned / No Comms” line label | Process Model correction | Metering Changes | Change of Metering | MHHS-BP009
MHHS-DIN-161 |  |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 requirement correction | MHHS-METH001-5.4c Please confirm the requirement: “where daily advance records are available [either in the past or future] and less than 90 days months different from the UTC Date requiring a daily advance - use the mean actual Meter advance from the closest [4] weeks for the same Day Type (as defined in ISD).” |  | Closed | [5 empty] | Duplicate of DIN 97. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-162 |  |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 typo | MHHS-METH001-5.5 typo “Where DAEs are required to be calculated the SDS shall use the most recent data a based on the event that triggered the estimation.” |  | Closed | [5 empty] | Duplicate of DIN 98. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-163 |  | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Conditionality Rule for B037 | It is not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure it is unclear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated conditionality rule for Block B037 in IF-001, IF-002, IF-033, IF-036: to show that Either DI-075 (Primary MPAN) or DI-079 (Secondary), and not both, should be populated where MPAN (DI-063 above) is part of a group of Related MPAN. |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-164 |  | DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0093 comment raised on 12/01/2023 "" D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692"" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: ""It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period"" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42" |  | Closed | [5 empty] | "This requirement stands - review with SCS in light of SEG scenario. We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error...". Reviewed with SCS and agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-165 |  | DI-122 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | See separate sheet Duplicate of DIN-157 |  | Closed | [5 empty] | CR required to add rules in line with CP R0032 Added Miscellaneous Data Validation to IF-005 to cover REC CP R0032 validation rules Wrapped up into design teams main CR Doesn't need to be raised by SCS | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-166 |  | DI-77 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54" |  | Implemented |  |  |  | Interim Release 1 |  | Added clarification to REG Notes re Consent and Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-167 |  | DI-78 DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? " |  | Closed | [5 empty] | Agree you can't. Could update 1032 rule for USP? Duplicate see DI-29 | No Change
MHHS-DIN-168 |  | DI-92 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 ""DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least ""Registered"", if no DS is appointed then there is already an appropriate Event Code"" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone |  | Closed | [5 empty] | CR for new functionality. "Already covered by no MS/DS appointed - MPRS would try to align MS/DS with principle and couldn't as there's no registration to align this to. Need an extra check that can only autoappoint if there's a registration to prevent MPRS crashing Maybe one for DRG? Jon at RECCO for consequential change? Agree not to build for this scenario as this would be an edge case and close | No Change
MHHS-DIN-169 |  | DI-109 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to:Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. |  | Implemented |  |  |  | Interim Release 1 |  | Simplified MHHS-BR-RS-131 on when to lapse a SEG appointment | Requirement correction | MPAN Ownership |  | MHHSP- BRS003, MHHS-BR-RS-131
MHHS-DIN-170 |  | DI-110 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. |  | Closed | [5 empty] | Duplicate of DIN-145 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-171 |  | DI-113 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { ""confirmingMpid"": ""string"", --* ""registrationId"": ""string"" --*, ""updateSucceeded"": boolean --* } Suggest that DI-0980 is removed from B066" |  | Closed | [5 empty] | Agreed with SCS being retained but due to optionality may have to populate text e.g. contact DSP. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-172 |  | DI-120 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. |  | Implemented |  |  | 2023-04-27 | Interim Release 1 |  | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-173 |  | DI-121 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP |  | Implemented |  |  | 2023-04-27 | Interim Release 1 |  | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-174 |  | DI-72 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a Submitted MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60" |  | Implemented |  |  |  | Interim Release 1 |  | "Agreed- doc updates MDR can have gaps between DS EFD and MDR EFD" Updated REG1083 validation in IF-034 so that it allows MDR Effective from dates >= SSD/ DS Eff From date/Existing MDR Eff from date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-175 |  | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" |  | Closed | [5 empty] | Duplicate entry | No Change | MPAN Ownership
MHHS-DIN-176 |  | DI-103 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-034 new rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD" |  | Implemented |  |  |  | Interim Release 1 |  | Agreed -doc updates Updated REG1082 to apply for both [SDS-MDRUpdate] and [DSAppSPRepsonse] events in IF-034 | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-177 |  | DI-105 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 " |  | Closed | [5 empty] | "Reason for IF-035 is to trigger when SDScan send the Meter info" & The IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR Agreed with SCS no changes are required, they now understand the context agreed to CLOSE | No Change | MPAN Ownership |  | MHHSP-BP003A
MHHS-DIN-178 |  | DI-106 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | MS missing a requirement to send MS updates to CSS | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 |  | Closed | [5 empty] | Closed as discussed with SCS that this is out of scope for MHHS Programme. | No Change
MHHS-DIN-179 |  | DI-111 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. |  | Closed | [5 empty] | Duplicate of DIN-146 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-180 |  | DI-125 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 the Meter Removal is currently not permitted for a prospective MS Is it possible for the MS to need to remove two meters and replace it with one? In which case meterexchange would only allow them to do part of this process (remove 1 and add 1) but not complete it, so SEG could not complete. Should meter removals therefore be allowed for prospective MS? (REG1019) |  | Implemented |  |  |  | Interim Release 1 |  | Revised REG1019 and added REG1027 for MeterRemoval event in IF-005 | Requirement correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-181 |  | DI-126 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Missing Rule on If-005: MAP EFD must not be > removal date |  | Implemented |  |  |  | Interim Release 1 |  | Added new rule for MeterUpdate and MeterHistoryUpdate events so that MAP EFD must not be > removal date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-182 |  | DI-127 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 On exchange - the MAP and IHD groups are for new installation not removed meter - does this need to be clarified? |  | Implemented |  |  |  | Interim Release 1 |  | New note added to IF-005 to clarify that only the newly installed MAP and IHD information is required on MeterExchange | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-183 |  | DI-128 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-005, IHD EFD missing validation in IF-005 (Between install and removal date) |  | Implemented |  |  |  | Interim Release 1 |  | Covered Release 5.1, IF-005, IHD EFD missing validation added | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-184 |  | DI-129 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-005 incorrect validation rule: REG1010: On event code Meter exchange and Meter Install rule states MAP EFD >= Install date, it should be = not >=" |  | Implemented |  |  |  | Interim Release 1 |  | IF-005: Updated to REG1010 (MAP Eff from date check ) to = install date for MeterInstall and MeterExchange | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-185 |  | DI-130 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | It should not be possible to change MDR EFD once set. Need validation rules to enable MPRS to reject if IF-034 is submitted with current MDR but a different EFD. |  | Implemented |  |  |  | Interim Release 1 |  | Agreed - doc updates Covered by L3/4 validation as per updated Validation rule notes | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-186 |  | DI-131 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031, there is currently not enough validation to ensure on a SEG, that the same SP isn't appointed for the current registration. Need additional validation rule: If scenario SEG and current supplier, then SP must not be current SP. |  | Implemented |  |  |  | Interim Release 1 |  | Agreed - doc updates Updated validation rule Added REG1095 in IF-031 to check different Data Service proposed for SEG appointment | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-187 |  | DI-132 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Supplier inability to appoint MS/DS for Principal and Subsidiary MPAN | Unhappy Path Scenario: Receive IF-031 for MPAN that is both Principal and Subsidiary MPAN at the same time. This will be rejected as per REG1038/REG1039 Supplier will be unable to appoint MS/DS for the MPAN or any related/linked subsidiary MPANS. |  | Closed | [5 empty] | Closed, there is an existing to prevent this scenario happening going forward. Agreed with SCS to raise examples in the Data Cleanse Forum. | No Change
MHHS-DIN-188 |  | DI-133 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031 the rule REG1030 reads [DI0-828] in not a valid UMSO in DNO [DI-108]/[DI-109] This should read LDSO not DNO |  | Implemented |  |  |  | Interim Release 1 |  | Tied up with If-005 rejection description flexibility action Change REG1030 to read: REG1030 - [DI0-828] in not a valid UMSO in LDSO[DI-108]/[DI-109] SC change incorporated into 5.1.1 | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-189 |  | DI-134 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On IF-031, REG1036 is written to only apply to USP when it should apply to all scenarios? ""Proposed MDR Date [DI-836] >= [REG.MPAN_SUP_SSD] However don't think this rule is required at all as this is already covered under the REG1036 rule that MDR Date < DS EFD? Linked to DI-66" |  | Implemented |  |  |  | Interim Release 1 |  | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-190 |  | DI-135 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-034 missing validation rule REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational |  | Implemented |  |  |  | Interim Release 1 |  | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-191 |  | DI-136 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Addition of validation rules to MPRS to restrict Retrospective changes | MPRS does not currently prevent Retrospective changes to DUoS Tariff ID or Connection Type. Should MPRS add new validation rules for these items to restrict Retrospective changes? Please can you update DIN-191 to include Disconnection Date & Export Association. We don't currently have any restriction on how far these data items (and the others in DIN-191) can be back dated. This is a retrospective change through the DB interface and not a Manual Amendment. There are no retrospective periods for the following data items, this means the data items could be changed earlier than the settlement window and cause issues for settlement. There are restrictions that these data items must be within MS/Registration periods where appropriate, but the EFD/SSD could still be years into the past. - MDR EFD, - MS EFD, - DS EFD, - IHD Status EFD, - PC EFD, - SSC EFD, - Energisation Status EFD |  | Closed | Design gap | LDSO (SCS) |  |  |  | Covered in the retrospective changes discussion at DRG. | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-192 |  | DI-137 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | For If-031, scenario SEG, the business process diagram/requirements only describe the appointment lapsing once reaching it's SSD if no SA is received. If we receive a cancellation we would like to lapse the appointment at that point in time (it cannot become secured active after being cancelled) and not wait until the SSD to do this. |  | Implemented |  |  |  | Interim Release 1 |  | Added new requirements to BRS003, MHHS-BR-RS-24.1 and 58.1 | Design Ambiguous | MPAN Ownership |  | MHHSP-BRS003-Registration Requirements
MHHS-DIN-193 |  | DI-138 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | The YAML name for metered indicator (Data Item 127) is meteredUnmeteredIndicator. This is then set to true of false. It isn't clear whether true means it's metered or unmetered due to the naming convention. It should be named meteredIndicator instead to make it clear true means metered, false unmetered. |  | Implemented |  |  |  | Interim Release 1 |  | Updated YAML details in the Data Catalogue for DI-127 Metered Indicator. Updated YAML accordingly Updated data catalogue/ YAML | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-194 |  | DI-1 | 2023-03-15 | St Clements | 4475 | Madison Layton | Software Provider |  | For IF-035 what is Event Code [IMS-SendMTD] intended for? If intended for sending to old MS then this should be done via secondary routing on the original IF-035, not via another separate IF-035 message produced by MPRS with different event code. |  | Closed | [5 empty] | This message is effectively a copy of the DSAppAccepted AND/OR MSAppAccepted but sent to the Incumbent (current) Metering Service to act as a trigger for that MS to send MTDs. This should be created by MPRS. Requirements MHHS-BR-RS-053 and MHHS-BR-RS-019 cover Registration Service sending this. Message to check and close | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-195 |  | DI-76 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Originally raised as T4-COM-1691 on 15th Sept 2022: ""MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days "" Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5" |  | Implemented |  |  |  | Interim Release 1 |  | Agreed doc update Also in Reg Notes tab Updated validation rules and Reg notes Updated REG1037 in IF-031 to 2 workings days and updated REG notes, to align with process and requirements | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-196 |  |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Updates are required to clarify nullable fields |  | Implemented |  |  |  | Interim Release 1 |  | Updates to Interface catalogue includes changes to interfaces and block data items which are present and can be null 1. MHHSP - ERI011A - ECS Reports - Internal v5.1: The data catalogue is the only tab that has been updated 2. MHHSP - ERI011B - ECS Reports - External v5.1: The data catalogue, DIP_Common, MHHS-REP-003 and MHHSP-REP-006 have been updated |  | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue, MHHSP-E2E001 End-to-End Solution Architecture MHHSP - ERI011A - ECS Reports - Internal MHHSP - ERI011B - ECS Reports - External
MHHS-DIN-197 |  |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Decision taken to document digital signing of interfaces outside of the interface document. |  | Implemented |  |  |  | Interim Release 1 |  | Remove Z0 and ZI blocks from all interfaces. Signing process will be documented in the Code of Connection document. | Technical corrrection | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue Code of Connection
MHHS-DIN-198 |  |  | 2023-03-15 | Large Suppliers |  | Haz Elmamon | Large Suppliers | Complex Meter Site | Clarification on complex meter site, passed down from DAG as part of the work off plan, Haz to gather concerns for discussion at DA. LSC Rep provided information to the issue on 22-Mar-23 |  | Closed | Further information required | Large suppliers | [5 empty] | MPAN Ownership
MHHS-DIN-199 |  |  | 2023-03-23 | BGAS | 3460 | Neil Strange | large Suppliers |  | Participant wishes to see the use of standardisation in the interfactions between the SDS and sub roles MDR PSS |  | Closed | [5 empty] | Closed based on recommendation for programme CR to be raised by the Large Supplier Rep | No Change | Supporting Docs | SDS Validation / Extimation | MHHS-DES138-Interface Catalogue
MHHS-DIN-200 |  |  | 2023-03-24 | CGI | 3489 | Chris Beard | Software Provider | Hierarchy definition for selecting correct register reading in the case of multiple readings for the same settlement period | If there are multiple register readings available for the same Settlement Day, where is the hierarchy defined for selecting which should be used? Is this solely based on Reading Method (i.e. 1. A – Actual, 2. C – Customer, 3. E – Estimated by SDS, 4. S – Estimated by Supplier) or is it dependent on other factors such as the Event Code in the IF-041 ([ReadingRemv], [ReadingInstl], [ReadingEnergisationChg], [ReadingCOR], [ReadingOnSite], [ReadingCOS], [DSEstimate], [SupplierAgreedCOS], [ReadingOverride], [ReadingRemote])? |  | Closed | [5 empty] | Reading methods do not apply to Register Readings - recommendation for DIN to be closed. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-201 |  |  | 2023-03-24 | ESG | 3529 | Patricia Parker | Software Provider |  | IF-033 Validation for population into the IF-034 The receiving party business validation rules state “Each Service Provider will need to determine their own validation criteria when processing Appointment Requests. The list below is intended to cover a number of potential possibilities based on the data items made available, and not to suggest that Service Providers needs or should perform such validations.” But should the DI-143 ‘Service Provider Proposed Appointment Response Code’ not form a valid set list (ENUM Vals) in the Data Catalogue so that all parties are working to the same list of applicable codes, rather than this field being a string with a length of 200 field? |  | Closed | [5 empty] | IF-033 has been updated as part of Interim Release 1 and the ENUM Vals will not be updated this is because we will have dynamic error messages which cannot be enumerated. |  | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-202 |  |  | 2023-03-24 | ESG | 3513 | Patricia Parker | Software Provider | Operational Choreography 60 minute turnaround | Registration Responses in connection with the PUB-31 given the NFS requirement is a 60-minute turn-around time. Within the Operational Choreography there is requirements OPC-140: From our understanding this means that when suppliers receive the PUB_032 from the Reg Service rejecting the appointment Request suppliers then have 60 minutes to re-issue a fresh IF_031 appointment. For example, there is a rejection code for 'CSS Reg ID not known', this would suggest that a party is out of sync and would need investigating especially as in this case, the REG ID would have previously been provided on PUB- 002, DI-849 and CSS is the master of the REG ID and not the Registration Service. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Added suggested text to Ops Choreography. Suggested text is "It is noted that some requests may require manual work and may be as a result of incorrect appointments from the Supplier. The expectation will be 90% of requests are systemically processed within 60 minutes with the residual being processed by the end of the following working day". | Doc Ref correction | Supporting Docs | Operational Choreography | MHHS_OPC001_Operational_Choreography
MHHS-DIN-203 |  |  | 2023-03-24 | CGI | 3502 | Chris Beard | Software Provider | mapping of Estimation Reason Codes to estimation Methods | MHHSP-METH001 M-13. Can you provide a definitive mapping of Estimation Reason Codes to estimation Methods? For example, LTV to Method 11. When should an SDS use Estimation Codes such as Opt Out, Comms. Fault. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated METH001 section 7.3 to reflect Estimated Methods to Estimated reason codes | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001
MHHS-DIN-204 |  |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | De-energised sites | MHHSP-METH001 M-3. Which estimation Method should an SDS use for de-energised MPANs that would result in an estimation code of ‘De-Energised’? Without a specific Method statement to cover de-energisation, we will end up estimating consumption. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Added Method 13 to reflect de-energised sites within METH001 and updated section 2.29 on METH002. | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001
MHHS-DIN-205 |  |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | Removal of Estimation Reason Code "Disconnected" | Can you confirm that the Estimation Reason Code ‘Disconnected’ will be removed from the table in 7.3? |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Removed "Disconnected" from Table 7.3 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-206 |  |  | 2023-03-27 | St Clements | 3703 | Anna Davis | Software Provider |  | Within the MHHS-E2E001 - End-to-End Solution Architecture, there is reference to MHHS-E2E003-Physical Interface Specifications in 1.3 References section This should be labelled as MHHSP-DES138-Interface Catalogue |  | Implemented |  |  |  | Interim Release 1 |  | Updated 1.3 reference section | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-207 |  | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Clarity on when agent appointments should become effective | There is ambiguity within the design on when agent appointments should become effective, which means that different participants have a different view on when agent appointments should become active. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | At the DRG held on 4th August it was agreed that Appointments need to become active in UTC. Further workgroup discussions are being held to review impacts. References to local time removed pending agreement at Working Group/ DAG. Old solution: Appointments become active at midnight local time. Participants raised objections against the old solution therefore this DIN went to a DRG on 4th Aug for discussion. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-208 |  | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Registration Service rejection of Legacy messages for an MPAN | Within the existing Migration Design, it is stated that the Registration Service should reject all Legacy messages for a given MPAN once a Forward Migration has been initiated for said MPAN. This would prevent a legacy MOP from sending the relevant legacy flows if they need to change a meter when an MPAN is mid migration. |  | Closed | [5 empty] | Closed following internal review with Design, Migration and Code Team. Agreed that current design will stand in that all legacy messages will be rejected following the point the IF-031 is issued. Reaffirm existing guidance that migration should be timed to avoid any planned work. Unplanned work/change occuring during migration should be communicated using an MHHS IF Message once migration has been completed. | Requirement correction | Migration | Migration | Migration Design Migration Requirement
MHHS-DIN-209 |  | Design Team | 2023-03-30 | Design Team |  | Sean Cooper | SRO Design Team |  | ~ Level 1/2 Error Code "MSG0000 - Success" Added to Interface Intro Section ~ MSG0018 - Timestamp cannot be future removed and explainatory note added to IF Notes Section of DIP Common |  | Implemented |  |  |  | Interim Release 1 |  | Updated actioned in v5.1.1 of IF Doc. This relates to MSG1008 not MSG0018 as originally given in the design issue. MSG0000 Success added. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-210 |  | Design Team | 2023-03-30 | RECCo |  | Sarah Jones | Consultancy |  | Possible change flagged The original view of the Design Team was that this flag and associated info (ie Is a Customer Direct contract in place, who is the DS/MS with that contract, but not the Eff To Date aka Contract End Date) should be visible to incoming Suppliers, for exactly the reasons you suggest i.e. so that in an incoming supplier could factor the existence of a CDC(s) into their acquisition process / pricing etc. I think we also felt that SP’s who weren’t currently appointed, but may have signed a new CDC should also have the ability to set the flag, as it’s the sites that are part of a CDC, but where that SP isn’t the appointed SP that are the most difficult to coral and manage. The position at the moment is that the existence of a CDC would be shared with incoming Suppliers as part of PUB-002, however this would likely be too late in the process to provide the assistance and support required to an incoming supplier (on all aspects of the sale, contract/price in particular) … … therefore, I think it was also envisioned that information about CDC’s would be available via ECS – so prospective suppliers could check in ECS on the CDC position as part of the other pre-acquisition checks they may undertake. Therefore, I think the decision on exactly what information is shared ‘pre-acquisition’ to participants probably sits with yourselves (RECCo) to finalise as part of your ECS Design / DP Assessment. All information in relation to CDC’s will be passed/made available to ECS via receipt of a copy of PUB-039, so what item(s) are displayed and to what parties I think would get covered off as part of that ECS Design activity. |  | Closed | [5 empty] | Closed, as per discussions with RECCo that no design changes are required. | No Change
MHHS-DIN-211 |  | DI-139 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-009 Event Code is referred to as [CSSDeRegistration] in the population notes and swagger open API spec but then B042 block title references event code CSS Deactivation, B042 should reference CSSDeRegistration. |  | Implemented |  |  |  | Interim Release 1 |  | Update B042 to reference CSSDeRegistration | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-212 |  | DI-140 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | MHHSP-BP007-Disconnection-v5.0 is missing IF-050 being sent out on a change to MPAN/RMP Status |  | Implemented |  |  |  | Interim Release 1 |  | to BP007 and BPD007 Requires a flow from Registration Service to EES (IF-050 to DIP, a Publish Change to MPAN/RMP Status process, a PUB-050 from DIP to EES process Receive Change to MPAN/RMP status) starting at step 70 (disconnection). Plus add new step descriptions to the BPD and amend Step 70 description to include IF-050. | Process Model correction | Metering Changes |  | MHHSP-BP007-Disconnection, MHHSP-BPD007-Disconnection
MHHS-DIN-213 |  | DI-141 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Data item 997 in S1 common block is senderId in swagger hub, but senderDIPID in data catalogue |  | Implemented |  |  |  | Interim Release 1 |  | Update swagger to reflect senderDIPID to align to data catalague | Technical corrrection | Technical Artefact | Swagger | JSON,YAML
MHHS-DIN-214 |  | DI-142 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | REG Notes section Queuing of Prospective Appointments Rule 4 ** Rule 4: If App Scenario = 'SEG' and Supplier ID + Appointment Service Start Date = Existing Supplier ID + Service Start Date > (Service Start Date +2 working days) >> Appointments meeting Rule 4 have missed their opportunity, and will be 'Lapsed' (PUB-035) This rule doesn't make logical sense, needs correcting. What is the intended logic to be applied here? |  | Implemented |  |  |  | Interim Release 1 |  | Update to align with validation rule | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-215 |  | DI-143 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 for event code [MeterRemoval] rule REG1002 Sending Metering Service ID [SO.SenderID] is currently appointed OR held a valid appointment for Meter Installation Date [DI-057] This should read removal date not installation date |  | Implemented |  |  |  | Interim Release 1 |  | Updated validation rule REG1002 in IF-005 for event code [MeterRemoval] to refer to Meter Removal Date (DI-058) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-216 |  | DI-144 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-144 On IF-005 MPRS will validate Either current, queued SEG or previous MS If previous and not within 10 working days will reject with REG1003 If not previous, and not current or queued, will reject with REG1027 MPRS will then validate if install date/removal date is within MS period of ownership If not will reject with REG1019 REG1019 need correcting to also include <ETD to apply for previous MS It’s not possible to get a scenario where the If-005 passes the above rules (REG1003, REG1027 AND REG1019) but fails REG1002. Therefore REG1002 is not needed and will never be sent as a rejection code. (Add to DI-43) |  | Closed | [5 empty] | Agreed with SCS that no further change is required | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-217 |  | DI-145 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | On IF-005 REG1019 should also include validation that the installation/removal date concerned is <=Effective to date (ETD) of MS period of ownership |  | Implemented |  |  |  | Interim Release 1 |  | Updated IF-005 validation rule REG1019 to include validation that the removal/install date must be <=Effective to date (ETD) where the update is being provided by previous Metering Service (using their 10 day window) for MeterRemoval, MeterInstall and MeterExchange events. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-218 |  | DI-146 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 for event codes [MeterExchange] and [MeterRemoval], the rule should not reference DI-056 which is the meter ID in the installation block, it should should referenced DI-053 which is the meterId in the removal block |  | Implemented |  |  |  | Interim Release 1 |  | Rule updated not to reference DI-056 which is the meter ID in the installation block, it now references DI-053 which is the meterId in the removal block | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-219 |  | DI-147 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 - for other event codes removal date must be >= to Install date but for [MeterUpdate] the rule states > meter install date. Should be >= |  | Implemented |  |  |  | Interim Release 1 |  | Update rule for [MeterUpdate] to align to other removal date event codes | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-220 |  | DI-148 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1007 unecessary and will never be triggered, it is already covered under REG1001 cannot submit meter install if MPAN is disconnected |  | Closed | [5 empty] | Valid rule to left in as-is but noted cannot be SIT tested | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-221 |  | DI-149 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In the IF-005 guide it states: "When amending the Installation and/or Removal date of a Meter, a supporting MAP history commencing in line with the revised Installation Date must also be provided. Any additional MAPs should be provided in chronological order, each with a ‘MAP Effective From Date’ greater, by at least one day, than the previous." MPRS will accept if the install/removal date is changing AND the MAP History has not been included, there is no requirement in Interface Catalogue or Registration Requirements to reject if MAP history is not provided. |  | Closed | [5 empty] | Believe covered by MeterHistoryUpdate rules, but hopefully won't be an issue pending agreement on MAP discussion… IF-005 use case guide will be updated with outcome. DRG has agreed to remove MAP history therefore in lieu of this decision, this change will not be required. Closed | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-222 |  | DI-150 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | sarah |  | Implemented |  |  |  | Interim Release 1 |  | Updated wording to match existing validation. Guidance only now provided | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-223 |  | DI-151 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005: Need REG1006 to apply to all event codes, e.g. Meter Update on a change to removal date, will need to check that the removal date does not lead to non unique Meter IDs (overlapping dates) MPRS will reject with REG1006 in this scenario |  | Implemented |  |  |  | Interim Release 1 |  | Added REG1006 validation checks to MeterHistoryUpdate and MeterUpdate events. | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-224 |  | DI-152 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 Interface Note below could be read as MeterUpdate event code can be submitted by previous or prospective MS which is not correct "Only the Appointed Metering Service, and for a small window (10 days) to allow for delayed notification of field activities the previously appointed Metering Service; and an incoming Metering Service with a Prospective 'SEG' type appointment may send an IF-005 and update metering details. The [MeterHistoryUpdate] may only ever be used by the Appointed Metering Service. Interface Design assumes that two separate meters with the same 'Meter ID' cannot be installed at the same time. " |  | Implemented |  |  |  | Interim Release 1 |  | Updated | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-225 |  | DI-153 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | DI-849 CSS Registration Request Id does not have a YAML name in the interface catalogue In the swagger hub, the corresponding name is CSSSwitchID which is misspelt |  | Implemented |  |  |  | Interim Release 1 |  | Updated Data Catalogue to CSSRegistrationRequestID, Swagger to follow | Data interface correction |  | Interface Catalogue Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-226 |  | DI-154 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In MHHSP-BPD007 - Disconnection v5.0, the ordering of the steps are out of order. Steps 140, 145 and 150 are for parties receiving the de-appointment notification from the Registration Service, but this is not sent until Step 155. Step 155 “De-Appoint Services” needs to be before Step 140 “DS De-appointment Notification”. Also Step 145 “Receive De-Appointment Notification” is DIP receiving the de-appointment notification to send on, this needs to be after Step 155 and before Step 140 . The ordering should be: • De-appoint services (155) • Receive De-Appointment Notification (145) • DS De-Appointment Notification (140) • MS De-Appointment Notification (150) |  | Closed | [5 empty] | No plans to change step numbers as long as they are unique | No Change |  |  | BPD007
MHHS-DIN-227 |  | DI-155 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1.xlsb, the validation for REG1003 – “Metering Service ID [S0.SenderID] post appointment update period for MPAN [DI-063] has expired” is currently set to “Metering Service [S0.SenderID] holds valid previous appointment then [System Date] should be < [REG.App End Date] + 10 working days”. Should this be <= to allow for the full 10 days? |  | Implemented |  |  |  | Interim Release 1 |  | Changed to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-228 |  | DI-156 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 - IF-005 has the following error for [MeterExchange] & [MeterInstall]:- “REG1020 - MAP Effective Date [DI-054] cannot take place in the future” Should this validation also be valid for [MeterUpdate] and [MeterHistoryUpdate]? |  | Implemented |  |  |  | Interim Release 1 |  | Added to meter update for removal date. Added to MeterUpdate and MeterHistoryUpdate for MAP effective date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-229 |  | DI-157 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 does not have a rule that the SMSO EFD must not be prior to the latest SMSO EFD. We are implementing this rule with error code REG1019 |  | Implemented |  |  |  | Interim Release 1 |  | We are implementing this rule with error code REG1019 Make consistent with others ( PC and ssc + 1 ). Review IHD and SMSO | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-230 |  | DI-158 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 & IF-005 do not have a rejection code where the IHD is invalid. |  | Closed | [5 empty] | DIP will reject non-valid values - no change to docs required | No Change
MHHS-DIN-231 |  | DI-159 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-005 - There is no validation on Meter Removal date [DI-58]. This should be mandatory non nullable for [MeterRemoval],[MeterExchange],[MeterUpdate], but mandatory nullable for [MeterHistoryUpdate] to allow for reinstating a previously removed meter. Currently in redlined v5.1, this data item is optional and non nullable. |  | Implemented |  |  |  | Interim Release 1 |  | Meter Removal changed to nullable, block conditionality updated | Missing/incorrect validation rule | Metering Changes | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-232 |  | DI-160 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-160 on the interface catalogue DCC Service Flag validation rules are specified in IF-025, but DCC Service Flag is not received in this interface. Needs removing. |  | Implemented |  |  |  | Interim Release 1 |  | not needed rules removed. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-233 |  | DI-161 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 – IF-025, where the event type is [ConsentGranularity] Error Code - REG1019 - Consent EffectiveFrom Date [DI-018] must be within Suppliers period of ownership Test Condition - Consent Granularity EffectiveFromDate [DI-018} must be < [Reg.CurrentSupplierEndDate] if exists Should this be <= as it could be on the end date? |  | Implemented |  |  |  | Interim Release 1 |  | Updated to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-234 |  | DI-162 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Registration Services Requirement MHHS-BR-RS-021 should be amended to: Registration Service must, where more than one Metering Service appointment request is received from the same Supplier for the same MPAN CSS Registration Request ID, and for the same date, take the last received Metering Service appointment (based on the Sender timestamp) as containing the correct information. Any earlier appointments should be lapsed. To allow multiple queued service appointments for the same registration will be overly complex to design, code and test, and is likely to cause confusion and issues in live operation. It is much simpler and cleaner to only allow one queued service appointment at a time, per registration. This would still allow the Supplier to replace a queued appointment that's incorrect. The Supplier could submit further changes once the first change has completed, if there is a genuine case of multiple changes to SP in a short period of time. It would not impact on CoS. Our proposal is to allow one pending queued appointment per registration, so could have a queued appoint on current registration AND queued appointment on CoS registration at the same time. |  | Implemented |  |  |  | Interim Release 1 |  | Updated MHHS-BR-RS-021 to refer to CSS Registration Request ID. Added REG1089 - Subsequent appointment received as an error code in the interface spec | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-235 |  | DI-63 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Original wording:- In the business process diagram for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 Update required:- Please close this design issue as CSS0700 is the correct reference for update of status. |  | Closed | [5 empty] | DUPLICATE OF MHHS-DIN-63 | No Change
MHHS-DIN-236 |  | DI-163 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, 02-DIP-COMMON - R0 response - DI-980 Response Message has been updated in Swaggerhub to be an array, but this is not clarified in Interface Spec. DI-979 Response Code should not be an array. |  | Implemented |  |  |  | Interim Release 1 |  | Added note in Introduction section to confirm that DI-980 can be an array Agreed DI-979 Response Code is not an array | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-237 |  | DI-164 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-034 S0 DI-999 Event Code option of [DSAppSPRepsonse] is misspelt. This is also misspelt in Swaggerhub. This could cause differences between systems and should be corrected to [DSAppSPResponse] |  | Implemented |  |  |  | Interim Release 1 |  | Updated typo in IF-034 DI-999. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-238 |  | DI-165 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation on MS/DS EFD being within permitted advanced period. This is covered under migration document but not implemented as a validation rule for IF-031. MHHS-DEL961 Migration Design Document section 6.1.1: For the purposes of the CoA Migration process, the below business rules should be followed by Suppliers regarding the lead time between the submission date of the IF-031 and the requested effective from date of the Migration. a. An effective from date from Same Day +1 up to a maximum of 28 calendar days (inclusive of the 28th day) in the future is permissible. |  | Implemented |  |  |  | Interim Release 1 |  | 28 Day in advance rule added to if-031 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-239 |  | DI-166 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Requirement MHHS-BR-RS-134 states MPRS must automatically de-appoint the MS & DS when the Market Segment Indicator changes to NO. Is this the intended design? |  | Implemented |  |  |  | Interim Release 1 |  | Removed reference to Market Segment Indicator from the requirement MHHS-BR-RS-134. | Requirement correction | MPAN Ownership | Market Segment | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-240 |  | DI-167 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Current validation on IF-031 Rule REG1037 will mean MPRS will lapse any appointment where the system date is greater than appointment EFD + 2 working days. This means if a SEG change fails, and the supplier tries to resubmit the SEG change, with EFD more than 2 working days in the past, MPRS will immediately lapse the appointment. If there is a need to allow retrospective SEG changes, more than 2 working days after EFD, then the wording will need to be amended to apply to max(EFD+2 working days, MPRS system date on receipt of IF-034 + 2 working days) |  | Implemented |  |  |  | Interim Release 1 |  | Introduction of Lapsed Response Codes and Rules in IF-035 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-241 | RS |  | 2023-02-01 | C&C | 3430 | Graham King | Software Provider | Routing rules via the PUB-018 | IF/PUB-018 message with event codes [AddressChg] and [DUOSTariffIDChg]. According to Interface Catalogue routing rules, these events are not communicated to the LDSO role via the PUB-018. We assume that the assumption here is that because these data items are mastered by the LDSO that all internal LDSO systems share this data. This is unlikely to be the case. DUoS billing systems co-exist alongside other LDSO management software and are often supplied by different vendors. They do not and cannot share data sets. Given this real-world separation, would it be possible to make the PUB-018 message available to LDSO in the list of Secondary Routing paths? The alternative would mean developing communication channels between disparate systems, from potentially different software vendors in order to pass information from one to the other. |  | Closed | [5 empty] | Closed - Linked to expected LDSO CR26 on DIP Message Optionality - Update as part of wider CR review | No Change
MHHS-DIN-242 |  |  | 2023-04-04 | ESG | 3713 | Patricia Parker | Software Provider |  | How will the Metering Service be kept informed of who the currently appointed Data Service are? On BP003 is shows the Metering Service being a recipient of the PUB_036 when a DS appointment becomes effective, however looking at the routing rules in DES138 it does not show ‘MSSC’ or ‘MSAC’ as being recipients? |  | Closed | [5 empty] | Close - changes to Secondary routing make this DIN Moot - Ref DIN-268 | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-243 |  |  | 2023-04-05 | Change Request | N/A | Sean Cooper | Programme | CR-015 E7/E10 Off Peak Consumption Solution | CR015 - Differential Settlement for E7 / E10 Meters for Smart Opt-out customers | CR015 | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Changes as agreed at DRG and slides circulated. Updated Method 2 and Method 7 within the SDS method statement (METH001). BR-DS-168 & BR-DS-169 added to BRS001. BR-SU-163, BR-SU-164 & BR-SU165 added to BRS004. BP004 text box amended. Creation of x2 New Data Catalogue Items​ OPD Day​ & OPD Proportion​. Changes to IF-024​ Addition of new Event Code [SN-OffPeakDec]​ & Addition of new B-Block BXXX Off-Peak Declaration​ | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue METH001 BRS001 BRS004 BP004
MHHS-DIN-244 |  |  | 2023-04-04 | British Gas | 3874 | Neil Strange | Supplier |  | D0275: Until v0.3 of DES196 was released our understanding was that the D0275 would be retained and it’ use was optional. We are feeding this back on the D-025 consultation but don’t want to lose sight of this. Its removal will impact our billing systems and substantially drive up implementation costs. The baselined IF-021 also does not handle the clock change |  | Closed | [5 empty] | Alignment with D0275 D0275 is not part of of the baseline design requirements. If you require this, it is by mutual agreement between parties. NO change required, only clarification. | No Change
MHHS-DIN-245 |  |  | 2023-04-01 | Avanade/ Design Team |  | Grant Sutcliffe | Software Provider | Transaction ID and Correlation ID increase field length to 60 | Transaction Id Could the length specification of the TransactionId be increased to be a max length of 60. The need for this is to cater for a 16 character length hex value (increasing from current length of 6 characters]. This would ensure that we achieve uniqueness. It will also provide headroom for any length increase in other Transaction Id constituents, such as Role. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: T-041-1234567890123-SUP-20230220-619C1F6967838002 [Length = 50] Example from DES138 spreadsheet: T-006-1234567890123-SUP-20220401-1234CC [Length = 40] Correlation Id Could CorrelationId length also be increased to 60 max length of 60 - for the same reason. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: CI-BP-011-20230222-619E0BD1D1FD9000 [Length = 35] Example from DES138 spreadsheet: CI-BP-011-20230222-1234567890123 [Length = 32] |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated DIP Transaction ID and DIP Correlation ID to String 60 in Interim Release 1. The examples have been updated to reflected MHHSP-DES138-Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-246 |  |  | 2023-04-12 | Change Request |  |  | DCUSA | CR-019 Replacement of D0242 D0315 for MHHS | CR019 - Replacement of D0242 D0315 for MHHS | CR019 | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors) and receivers (suppliers) of the flows has identified the desired flow content and now wish to bring this back to the program to ensure that it can be delivered in readiness for migration. REP-900 and REP-901 added to reporting catalogue. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the supercustomer data from settlement (REP-002/002A). There will be removal of certain data items used in the current process and addition of new data items, making population of the D0242 ‘Supercustomer DUoS Daily Statement’/D0315 ‘Embedded Network Supercustomer DUoS Daily Statement’ impossible in their current format for migrated customers. The “MHHS Design: Reporting and Transition Sub Group” identified the need for a new DIP flow to replace the D0242/D0315 last summer but noted that these flows are under DCUSA ownership and so passed the development of the flow content to DCUSA. More information including the proposed Interface can be found on the collaboration base under CR019 This also addresses CR27/DIN511 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-ERI011B External Reports
MHHS-DIN-247 |  | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Update to the Core Design Interface Catalogue (MHHSP-DES138) is required to include the addition of IF-003 |  | Closed | [5 empty] | Closed captured under DIN-434 as part of migration update review IF-003 defined as part of Migration baseline The structure of the IF-003 will be updated to include ‘Incoming Supplier Details.’ The two new data items within the ‘Incoming Supplier Details’ will be: RevMig Incoming Supplier MPID RevMig Incoming Supplier Effective From Date Business Rules: In the case of Smart Meters undergoing Reverse Migration only, the Registration Service will populate the ‘Incoming Supplier Details’ as part of the IF-003 which is sent to the outgoing MS (via the DIP). This is so the outgoing MS can correctly route the Skeleton D0150 to the new Supplier (which in turn enables the new Supplier to generate a D0367). If the D0205 is not sent to the Registration Service before the IF-003 is issued, the data fields used to confirm the identity of the DC and MOP will be blank; no default values will be populated. In this case, the DC and MOP will need to contact the Supplier to initiate a manual transfer of data. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-248 |  | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Updates to the ISD Entities document (EDI021, v5.0) |  | Closed | [5 empty] | To be picked up as part of Migration IA - - new DIN will be raised as required. |  |  |  | EDI021
MHHS-DIN-249 |  | Migration Design | 2023-03-27 | Migration Design |  | Matthew Breen | Programme |  | Discussion around the use of BST/UTC during Migration |  | Closed | [5 empty] | DIN is not specific enough.
MHHS-DIN-250 |  |  | 2023-04-06 | Design Team | 3764 | Steve Weston | Programme | Participant ID 10 digit number | This is related to ticket 3764, to update the Interface Specification to ensure the Participant ID is clearly defined as a 10 digit number [0-9] only, and the examples in the Interface Specification align to this, including where this is used as part of the sender unique reference and the examples shows 11 digits, not 10 digits for Participant ID. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | In E2E001 doc Section 4.2.3.2 Section 4.4.4.2 example code for Sender unique Ref and in Transaction ID Section 4.5.5.3 as above DES138 doc Data Catalogue tab: DI-990 example and DI995 Example DIP common tabl DI995 example and the example JSON block (the above easy to change) ALL the IF tabs the JSON block example the Sender Unique Ref contains Participant ID and in every example its longer than 10. JSON/YAML Files: Update JSON examples where Sender Unique Ref and Transaction ID contain a Participant ID example longer than 10. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 Solution Architecture MHHSP-DES138-Interface Catalogue JSON/YAML files
MHHS-DIN-251 |  |  | 2023-04-06 | Design Team | 3860 | Steve Weston | Programme | IF-041 Population | This is related to ticket 3860, to update the Interface Specification to provide more clarity / notes on the optionality of B064 and B065 blocks in the IF-041 interface. This is in relation to notes / detail about which blocks are mandatory (from a contractual perspective) versus what should be included in the message if the data exists. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updates the notes section of IF-041 in order to provide guidance on the minimum population of B064/B065 blocks. This clarifies "When exchanging readings between parties the design assumes that in the most part this will be the Cumulative Register Reading (Block B064). However, at participants request this message also allows for the exchange of Configurable Register Readings (B065) either alongside a Cumulative Reading or in isolation. For the avoidance of doubt the message must contain at least one B064 record and /or one (or more) B065 records [depending on the number of configurable registers], in order to be considered valid. " | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-252 |  |  | 2023-04-06 | Centrica | 3661 | Neil Strange |  |  | We believe there is a Design Gap at Change of Agent and Change of Supplier for Smart Meters which also impacts Migration. Neither the Registration Service, Metering Service nor Data Service will know how the registers are set up and specifically which are active. Consequently the Data Service will not know which registers to send on the IF-041, nor will there be able to calculate consumption correctly without knowing the register set up. The interface catalogue for IF-041 states in respect to this “B065 Block Below Repeated for each set of Configured Register(s) for each Meter” – we do not believe there is a way to give the DS this information. The supplier will set up the smart meter configuration to enable the registers to capture the usage for certain time periods. There is currently no way for the supplier to inform the DS which registers are active at what time of the day - the DS cannot accurately calculate the consumption breakdown based on the reads when there are multiple registers configured. |  | Closed | [5 empty] | DIN closed, Design Team to send email recommending for a CR to be raised.
MHHS-DIN-253 |  |  | 2023-04-12 | British Gas | 3769 | David Hipwell | Large Supplier | Volumetrics | The latest E2E Functional and Non-Functional Requirements MHHS-E2E Requirements V3 which went to V3 on 16/02/2023 appears to focus on message counts and response times. For example:- During transition all meter points (ca. 31M) will be transition between the old and new services. Therefore assuming a linear migration over the year this would result in the load below, hence services shall be capable of processing the following volumes: - average daily volume of 680,000 - peak daily volume of 2.4M 5.0M - annual volume of 248M 500M Analysis of the flows needs to be categorised across all impacted market participant roles including the DIP. Only then will it have meaning for all parties. The calculation needs to take account of the migration period using the MHHS migration volumes according to date (including REVERSE migration). These should be in both message counts and also sizing (e.g. Gb). And include for a BAU day and also migration days. Whilst some calculations can use the total number of MPANs, to be useful these need show also at perhaps for a million MPANs in each role. Only then will all parties be working on a single set of figures. A line in the sand. The NFRs that exist appear to have moved away from any form of technical calculation towards business process figures. But these figures need to go as an input into technical sizing’s, and should have done for DIP – can these be produced and published ? |  | Updates Ready to Release | Clarification - No change required | DIP Users | 2023-09-13 | Post Go-live Release | 0 | Volumetrics analysis was presented to DRG on 13th September with some minor comments (see DRG meeting minutes). Updated volumetrics document will be issued as part of IR5. The document has been updated to include the following information to support these requests: - Overview of assumptions that form the basis of the volumetrics document. For the purposes of this volumetrics document, this includes things like number of meters, consumptions per day, settlement days per message, MPAN per message, breakdown of smart vs traditional, breakdown of SMETS1 vs 2, those providing Import / Export / Both etc. - There is breakdown of smart meter & traditional meter split that inform actual / estimated reading, alongside patterns for message structure. The 2 patterns explored provide a range used in the scenarios – these are consolidated and individual IF-021 messages. - Additional scenarios that include an average (best-case) distribution of IF-021 messages across a 24 period, as well as scenarios that cover a peak of peak (worst-case) distribution of messages across a 24-hour period. These scenarios align with all NFRs. - The scenarios provide upper and lower message bounds across the day, as well as provide message throughput per hour / second. - Additional scenarios split into 2 sections – with a breakdown for the DIP plus a breakdown for an MP with a portfolio size of 1 million. - Graphs added to show / illustrate distribution of the messages for the scenarios for all traffic into the DIP. Without firm guidance on how each Data Service are likely to submit IF-021 messages four different scenarios are used to help inform average / peak processing volumes as follows, which are detailed in the volumetrics document as follows: - Scenario 1 - Market Participant IF-021 messages equally distributed across a 24-hour period - Scenario 2 - Market Participant IF-021 messages equally distributed across a 6-hour period - Scenario 3 - Market Participant IF-021 messages unequally distributed across a 6-hour period - Scenario 4 - Market Participant IF-021 messages distributed unequally across a 24-hour period using a Monte Carlo simulation model Scenarios 2 & 3 describe extreme patterns of data submission that are very unlikely to occur in reality; they present a worst-case scenario where the patterns of submissions follow the End-to-End requirements to the extreme and Data Services submit data almost simultaneously. Scenario 4 presents a statistical approach where the volume of IF-021 is randomly distributed according to a Monte Carlo simulation. Alternate scenarios, that are not considered BAU, are also presented and included in the Volumetrics document: - Submission after an unplanned Outage for 72 hours as per NFR. - Market Transition / Migration. - Change in Meter Population from 50% to 90% over time. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E004 E2E Architecture - Transaction Volumes
MHHS-DIN-254 |  |  | 2023-04-17 | Siemens | 3044 | Tony Mason | Metering Service | Update of Consent, DPI, etc. | this does surprise me and doesn’t seem to correspond to the routing rules in the Interface Specification. A proposed Data Service is not included in the routing tables for the receipt of a PUB-018, for example. I would therefore expect that if a change to DPI occurs between PUB-033 and PUB-036 the proposed Data Service could only be notified on a revised PUB-033 with the Appointment Scenario set to whatever the original scenario was set to – “SEG”, “CSP”, or “COS”. |  | Closed | [5 empty] | Ref notes on the maintenance of these data items in the Regi Info Section of the I/F document. Prospective SPs are not notified of changes to these data items during their prospective period. If these Data items change then the supplier should re-evaluate the SP they have proposed and change the appointments as required. If an SP takes on a supply with different elements/factors to those suggested by the supplier at appointment this is a contractual issue between the SP and the Supplier.
MHHS-DIN-255 |  |  | 2023-04-17 | Elexon | 3983 | Kate Goodman | Testing | Consumption on De-Energised MPAN (IF-013/IF-014) | ConsumptionOnDeEnergised is an Event Code mentioned in the list of data items but is not present in header where the routing info is held - needs to be added to header |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | ConsumptiononDeEnergised event moved from IF-013 to IF-014 and added in routing rules. See also DIN332 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-256 |  |  | 2023-04-17 | Elexon | 4169 | Kate Goodman | Testing | IF-014 Block B067 | DI-015 is mentioned in the header wrt routing but is not present in the message itself. It either needs to be removed from header or added into message. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Block B067 added to IF-014 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-257 |  |  | 2023-04-17 | Elexon | 4172 | Kate Goodman | Testing | B053 repeating block | B051 is a block which repeats for each combination of Load Shape Criteria (denoted with single chevron to show repeat). B053 is another repeating block which is denoted by two chevrons, implying it is nested below B051. But in fact it also repeats for each combination of Load Shape Criteria. Should this just have a single chevron or is there further information that needs to be added to make its double chevron make sense? |  | Closed | [5 empty] | No change required as there will be multiple B053 in each B051 block. | No Change |  |  | none
MHHS-DIN-258 |  |  | 2023-04-19 | ENWL |  | Paul Band | Network Operator | LDSO use of DIP vs internal for Specific messages | There are a number of requirements in the MHHS-BRS005-LDSO document which state that we must obtain various registration data via the DIP and maintain records accordingly such as: MHHS-BR-LD-001-005, MHHS-BR-LD-024, MHHS-BR-LD-030 and MHHS-BR-LD-034 Extrapolating these into requirements for our own systems suggests that we should build databases/tables to store this data and maintain it The requirement is placed upon us as a party under the assertion that all settlement related data should be exchanged between services and parties via the DIP. However LDSO’s are unique in that their data exchange for their party type is split and is typically split by system under these party types. As a consequence we already communicate directly with MPRS as it is already part of our system architecture as a paid for and created service by LDSO’s. |  | Closed | [5 empty] | CR26 has been raised to covere this LDSOs have been advised to raise a Programme Change Request. Discussion at the DRG of the 27/4/23 did not agree on the development of a New Design Principle, A further workshop with LDSOs needs to take place to discuss alternate options and confirm agreement amoungst all DNOs & IDNO on the receipt of publication
MHHS-DIN-259 |  |  | 2023-04-20 | ESG | 3756 | Patricia Parker | Software Provider | BP003C correction | On BP003C under the CoR section there is a note which states that the readings that pass validation should have Meter Reading Status (J0047) set to ‘T’ and when it has failed set it to ‘F’. However as per the REC the group which houses the J0047 group (032 – screenshot below) should only be present where the Meter Reading Flag (J0045) is set to ‘F’. I have checked DES196 and cannot see that the conditionality for that group is changing in the D0010 therefore I can only assume that the note on the process map is incorrect, and it should be talking about the J0045 value instead. Please can you confirm? |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Modification to Note on process to refer to "Meter Reading Flag (J0045)", modify flow label to step230 to "(Read Flag = "T")" Modification to the process note to advise the J0047 would not be present if the meter reading flag (J0045) is set to "T". It will only be present in case the J0045 is set to "F". | Process Model correction | Metering Changes |  | MHHSP-BP003C-Transfer of Reads
MHHS-DIN-260 |  |  | 2023-04-20 | CGI | 4167 | Dave Webster | Software Provider |  | Swagger definition does not match DES-138 in version 1.0 or 1.1. |  | Closed | [5 empty] | No specific detail provided, however comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1, therefore closed
MHHS-DIN-261 |  |  | 2023-04-20 | Utiliteam | 4245 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. Configurable Register Reading Date/Time is missing. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue JSON/YAML Files
MHHS-DIN-262 |  |  | 2023-04-20 | Utiliteam | 4214 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. B070 for IF-031 is wrong. It contains the word DIP in the Swagger, which is not included in DES-138. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files
MHHS-DIN-263 |  |  | 2023-04-21 | CGI | 4203 | Dave Webster | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. DI-122-Profile-Class is defined as an integer, but in DES138 it is defined as a string length 2. Needs to be updated in the Swagger. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Swagger and Data Catalogue aligned to String 2 for DI-122 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files
MHHS-DIN-264 |  |  | 2023-04-24 | Elexon | 3946 | Rashmi Radhakrishnan | Central Body | Update to CCC Method Statement | One of my colleague pointed out a typo in the CCC method statement attached, and I would like to draw your attention to it and requesting to make necessary amendments. The CCCID starting from 100 to 107 has Market Segment Indicator as “U” and Connection Type Indicator shown as “W”. We think that, for these line items the Connection Type Indictor need be corrected to “U”. For reference please see below picture and this also aligns with ISD entity spec v5.0 (M2 entity). CCC ID Market Segment Indicator Measurement Quantity Consumption Component Indicator Connection Type Indicator 100 U AI C W 101 U AI L W 102 U AE C W 103 U AE L W 104 U AI C W 105 U AI L W 106 U AE C W 107 U AE L W All 'W's' should be 'U's') |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Method Statements (MDS & VAS) will be updated for "W" to be replaced by "U"within ISD Table - MHHS Consumption Component Class. Please note: ISD entity M5 file has already been updated to reflect the fact that unmetered supplies have a connection type of "U". | Design Ambiguous | Supporting Docs | Method Statement | MDS Method Statement VAS Method Statement
MHHS-DIN-265 |  |  | 2023-04-25 | Elexon | 4128 | Rashmi Radhakrishnan | Central Body | Validity of Settlement Period quality indicator data set | ISD entity M5 has a filed Settlement Period quality indicator. Is this the complete valid data set for the field Settlement Period quality indicator? I took this below list from interface catalogue v5.0. A = Actual, E= Estimate (UMS Only) A1,A2,A3, AAE1,AAE2,AAE3,EAE1,EAE2,EAE3 (ADV Only) E0 --> E9 = Estimation Method 1 - 9 ZE = De-Energised ZE1--> ZE3 = Zero Estimation Method 1 -3 but the Advanced Data Service Estimation Method Statement has data flags EA1 till EA13 which is not mentioned in the above list. Also, the ISD entity spec M5 example below shows a different data item that is not in the list at all for Unmetered(104 &105). Is this a mistake? |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Interface document updated with the full list of settlement period quality indicators for ADS and swagger updated accordingly. within DES138. 02-IF-016/14 and in the data cat. DI-083 "EA1-->EA13 = ADS Estimation Methods" added. | Design Ambiguous | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-266 |  |  | 2023-04-26 | ESG | 3899/ 925 | Patricia Parker | Software Provider |  | If the D0300 process is not changing then we believe that DES196 is incorrect and should show added routes to allow the Supplier to send a D0300 to the Data Service Matt M has confirmed - We are working through the exchange of CoS readings as the code drafting has raised some questions about the extent to which the SDS is involved in the D0300 process. For smart meters, the SDS will not have any use for the billing register readings so D0300 process should not apply, or at most could only be missing the total cumulative. However, it likely will still be required for traditional meters. On that basis, I think we can acknowledge that the D0300 will be retained and SVs created for Supplier to SDS for traditional meters. The process for smart meters is being discussed internally as the SDS does not retrieve tariff register readings. There will be an updated version of DES196 issued in the next few weeks to reflect feedback from the DTN flow part 2 consultation issued in late March which will reflect the retention of the D0300. |  | Closed | [5 empty] | Email comms sent to Patricia confirming the D0300 is a Supplier to Supplier flow. Therefore should there be a need to send readings to the DS, this would be done via a D0010/IF-041 with the correct data flags set in both. Based on this there is no requirement to send D0300 to the DS. Matt M confirmed when finalising DES196 he confirmed this in his comment response to ESG. The MSAG Consequential Change - Switch Meter Read Exceptions v1.0 22.06.23 provides a more comprehensive explanation of the MSAG conclusions. No change required to DES196 | Design Ambiguous | Supporting Docs | Method Statement | MHHSP-DES196- D-Flow and Interface Mapping
MHHS-DIN-267 |  |  | 2023-05-02 | ESG | 4385 | Patricia Parker | Software Provider | RegX Validation Issue | RegExpression on the DI-148-Annual-Consumption use of DT-016-Decimal-9-3 in the 1.1 swagger spec. This needs to be updated to align with DES-138 example of 123456789.123. Regex should be ^-?[0-9]\d{8}(\.\d{3})?$ instead of ^-?[0-9]\d{7}(\.\d{3})?$ |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Swagger v1.2 has been updated accordingly | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files
MHHS-DIN-268 |  |  | 2023-05-03 | SRO Design |  | Sean Cooper | SI Design | Secondary Routing | It was always the intention to revisit and revise all of the Secondary Routing configuration as part of DIP Detailed Design. Completion of this exercise has also resulted in some changes to other routing parameters. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Following discussion with Avanade the Secondary routing short codes have been simplified and the routing of each IF revisited based on these revised short codes. These are shown highlighted in BLUE in the routing section of each of the individual IF pages. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-269 |  |  | 2023-05-03 | St Clements | 4424 | Anna Davis | Software Provider | Swagger Alignment to DES-138 | We have also realised that there are a large number of discrepancies for each interface between the data item name in Swagger vs the YAML name in the Interface Catalogue Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated inconsistencies in the Interface 01-Data Catalogue and Swagger. Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-270 |  |  | 2023-05-05 | SRO Design | 4557 | Rob Golding | SI Design | Correlation ID | Provide further clarity on how Correlation ID's work. This will impact numerous artefacts including DES-138 and E2E001 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DES-138 Interfaces updated to reflect correct 'COPY' property on IF routing tables. updated IF-008, 16, 20, 26, 28, 37, 39 and 50 for this DIN. Added *New to IF-020 showing a new correlation ID is needed to be created for these events, others events needed a COPY of the correlation ID. IF-050 had “No” added to show that a Correlation ID is not required. Updated the E2E001 design document with a more detailed worked example in section 5.4 that details how and where the Correlation ID is populated. | Design Ambiguous | Supporting Docs |  | MHHSP-DES138-Interface Catalogue. E2E001.
MHHS-DIN-271 |  |  | 2023-05-10 | ESG | 4541 | Patricia Parker | Software Provider | Swagger Alignment to DES-138 | S0 and S1 is Mandatory in DES-138 v5.1.1, but is not marked as mandatory in the Swagger 1.1. Swagger needs to be updated to align with DES-138. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Swagger 1.2 updated so all SO and S1 blocks are mandatory as per DES-138 | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-272 |  |  | 2023-05-10 | SRO Design | 4656 | Rob Golding | SI Design |  | Required to DIP Channel Publication (v1.2 of the swagger) that will allow DCPs to register webhooks on behalf of their clients |  | Closed | [5 empty] | Duplicate of DIN-375
MHHS-DIN-273 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | New MSN Data Type | MHHS Data Type (DT-029) - for Meter ID / Serial number for DI-053, DI-056 and DI-060 added to DES138 01-Data Catalogue, Swagger updated. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | New Data Type created in Swagger v1.2 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-274 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | Missing YAML in DES-138 - DI-073, DI-074, DI-080, DI-111, DI-112, DI-190-194, DI-300, DI-021, DI-022, DI-060, DI-076 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Missing YAML names for Data Items confirmed and added to 01 - Data Catalogue Note:All DI's upsated except DI-076 has not required a changed. Other DI chnages not listed are picked up as part of DIN261 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-275 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | DI-093 / DI-120 - Data length 2,000 not 200. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | All additional info data items set to len 2000 in Swagger v1.2, DES138 DI-093/120 length updated in 01-Data Catalogue | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-276 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Classifications | MHHS Data Classification - ensure all columns are populated for Public and Restricted ie, MPAN & Address (removall all NULLS). |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Data Classifications added in v5.2.1 where previously there was no entry ( Column I in the Data Catalogue ) | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-277 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Owners in Data Catalouge | MHHS Data Owner - where there are NULL's, this should be updated so all columns provide an owner, mark as N/A (remove all NULLS). |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Metering Service added as Authoritative Source and MHHS Owner in v5.2.1 of DES138 Data Catalogue for DI-190 to DI-195. Previously there was no entry. | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-278 |  |  | 2023-05-10 | Design Team | 4590 | Rob Golding | Programme Design | Addition of indicator for each IF within DES138 | Please can DES138 Interfaces spreadsheet be updated to provide an indicator against each interface (or is it interface & event code) as to whether it can be opted in/out by a recipient. | CR029 | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Design Team to add optionality matrix to DES138. Name of worksheet: 04_IF_Optout_Matrix | Design Ambiguous | Supporting Docs |  | DES138 Data interface specification
MHHS-DIN-279 |  |  | 2023-05-12 | ESG | 4484 | Patricia Parker | Software Provider | Event Code clarifiction for DS when sending back validated customer read on PUB-041 | The BP005 – Data Processing – Process map shows that when a Customer Own Read has been sent to the Data Service from the Supplier in the IF-041, EventCode = ReadingCoR, the Data Service will perform reading validation and issue the PUB-041 back to the Supplier, in the Read Sharing column of the process map. When the Data Service send back the validated customer own read in the PUB-041, what eventcode will they use and where can I find this documented? The previous response says “There is no IF-041 response, check consumption is as expected in PUB-021” is this correct for Customer Own Reads on Smart meters? The map shows otherwise so please can you confirm if the answer or map is correct and if the map is correct, provide information on what event code will be used. |  | Closed | [5 empty] | This is a query not a DIN. Previous response provided is correct .... There is no IF-041 response, check consumption is as expected in PUB-021”
MHHS-DIN-280 |  |  | 2023-05-12 | ESG | 4552 | Patricia Parker | Software Provider |  | DES196 lists the D0386 (Manage Metering Points) as ‘not impacted’ owned by the REC however BP010 shows that the method of maintaining Related MPANs is via the IF_019 / PUB_020 process. Can you confirm whether the D0386 is going to be removed post- MHHS. If not, could you please clarify what process a Supplier should follow post- MHHS. |  | Closed | [5 empty] | D0386 will not be used post migration to MHHS Regime. Management of MPAN relationships will be under taken using IF-019/IF-020
MHHS-DIN-281 |  | DI-172 | 2023-05-12 | St Clements | 4446 | Madison Layton | Software Provider | BP003 IF-35 flow | MHHS-BR-RS-053 for the incumbent MS to be notified on If-035 DSAppAccepted where meter is advanced or traditional is missing from BP003 business process diagram and steps. Also updates to BP003 and BPD003 forward migration for consistency |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | IF-35 flow from step 85 (if accepted where meter is advanced or traditional to Meter Service (incumbent) and additional step 86 to receive appointment response to BP003, and added step 86 and BR-RS-053 ref and details to step 85 to the BPD003 | Process Model correction | Metering Changes |  | MHHSP-BP003-Change of Service - Data Service, BPD003 Forward Migration BP003 and BPD
MHHS-DIN-282 |  |  | 2023-05-16 | SIMS | 4821 | Martin Freeman | Software Provider | Status code removal | Status Code is included in the E2E001 design response body (4.4.4.2), when this is HTTP Response code and should be removed as this is defined in the callback response. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Removed from section 4.4.4.2 from the E2E001 design document as this is not required. This now aligns in Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-283 |  |  | 2023-05-16 | SIMS | 4826 | Martin Freeman | Software Provider | ID Capitalisation | ID should be capitalised in all places in the Swagger. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | All JSON names now have capitalised ID fields for Swagger 1.2. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-284 |  |  | 2023-05-16 | SIMS | 4828 | Martin Freeman | Software Provider | HTTP Response Code | HTTP Response code for success should be 201 in E2E001 as per Swagger. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to E2E001 design document in section 4.4.4.1, 4.5.5.1 and 5.3 to align with Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-285 |  |  | 2023-05-16 | Elexon |  | Rob Golding | SRO Design Team |  | Add replay / requeue API for Swagger 1.2 to align with existing E2E001 Design. Add additional information / clarity in the E2E001 for Interim Release 2 to align changes between design and Swagger. |  | Closed | [5 empty] | Duplicate of DIN-374
MHHS-DIN-286 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Issue clarification to Participants through DRG that all ECS Reports will be issues via Pattern B. Update of ECS Report Catalouge to reflect this. |  | Closed | [5 empty] | The ECS reports will be via Pattern A. No change is required to the ECS reports
MHHS-DIN-287 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team | Guidance notes for distribution of ECS reports | Create & Issue guidance document on the distribution of ECS Reports. To Contain : - overview of Pattern B Process - Guidance on population of IF-047 - Update of IF-047 Event Codes |  | Closed | [5 empty] | No longer required as pattern B will not be implemented for ECS reports
MHHS-DIN-288 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Update of Swagger with ECS Reporting Structures |  | Closed | [5 empty] | These interfaces are in place from Swagger 1.1.
MHHS-DIN-289 |  |  | 2023-05-17 | SRO Design Team | 4994 | Rob Golding | SRO Design Team | Interfaces for consumption replay | IF-015 / IF-016 - updates to E2E001 to provide clarification on design pattern. Alignments between DES-138 & Swagger alongside this. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | E2E001 design updated (Section 5.1.7) to provide additional information / clarity on these interfaces in relation to Consumption Replay. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-290 |  |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Proposal to change all / subset of ECS Reports to Pattern B |  | Closed | [5 empty] | Duplicate | No Change
MHHS-DIN-291 |  |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | As a result of DIN-290 -- Where should the reporting assets be hosted?? DIP solution specified, but what are the other options are availible. Final solution option to be ratified and documentation updated. |  | Closed | [5 empty] | Not hosted as via Pattern A | No Change
MHHS-DIN-292 |  |  | 2023-05-17 | St Clements |  | Madison Layton | Software Provider | ISD Entity M17 | Change required to ISD Entity M17 to add in Market Segment into the table - otherwise it cannot be used to derive consent values which was its original purposes |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | 1. Update Table name to "Consent Granularity Valid Combinations" 2. Added Market Segment as new table column 3. Update table to show all valid combinations | Process Model correction | Supporting Docs |  | MHHSP_EDI021_ISD_Entities
MHHS-DIN-293 |  |  | 2023-05-17 | Design Team |  | Paul Petitt | SRO Design Team |  | Retrospective DIN raised to ensure that any changes that are made in multiple downstream documents (for example CoCo, DIP Logical Design, DIP Physical Design & DIP Security Design) are reflected / updated in LDP assured documents to ensure e2e design / requirements alignment. This was agreed in a DRG Meeting in March 2023. |  | Implemented |  |  |  | Interim Release 1 |  | design changes to E2E001 End-to-End Solution covering points described in DIN details | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-294 |  |  | 2023-05-19 | ESG | 5030 | Luke Speakes | Software Provider | BP007 PUB009 flow | What I need to know is if the supplier will receive a PUB_009 with the Event code of [CSSDeRegistration] because nowhere on the BP007 process map does it show the supplier receiving the PUB_009 following a deactivation but on DES138 it shows the supplier as being a recipient of this event code. Step 95 (ringed below) shows the supplier as receiving the PUB_009 off the back of the Disconnection (event code [MPANDisconnection]) but then no where else on the process map does it have the supplier receiving a subsequent PUB_009 following the successful deactivation. Additional step required from step 130 (maybe 137?) to show both PUB-009 Mpan Disconnection and PUB-009 Deactivation going to supplier |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | BP007 change : There is already a flow from Step 85 to Step 95 for PUB009 for disconnection (no change) But need to Add a new step (137) for Receive Deactivation in Supplier lane from Step 130 for PUB-009 MPan deactivation in BP007 And there is already a PUB-037 flow from step 145 to Supplier step 157 for confirmation (so no change there) Addition of step 137 to BPD007 | Process Model correction | Metering Changes | Disconnection | MHHSP-BP007-Disconnection, BPD007
MHHS-DIN-295 |  |  | 2023-05-19 | SIMS | 4821 | Martin Freeman | Software Provider | L1/L2 Error Codes | Error code detail updates in DES-138 for Level 1 and Level 2 validation needs to be clarified |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updates made to Introduction Tab of DES138 in order to clarify Lev1 vs Lev2 error codes. Design is such that participants should expect error code(s) at either level. Further ammendments could be made following Avanade clarifications. | Data interface correction | Supporting Docs |  | DES138 Data interface Definition
MHHS-DIN-296 |  |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | It is envisioned that Configuration Management of ISD will largely follow the existing customs, practices and processes as are currently in place for managing MDD changes. However, DIN is required to formally confirm the Owner(s) and allowable update mechanisms (Standard or FastTrack) for each of the new ISD Entities outlined in the DIN. |  | Closed | [5 empty] | This is a Code Drafting issue not a Design / DIN issue. Code drafting team will be covering ISD maintenance processes
MHHS-DIN-297 |  |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | What Participants are recognised in the existing / new ISD Participant tables…. How does this link in with the parties recognised by the DIP (and assigned DIP Roles / IDs …. Or Not) …. In particular how are MDRs referenced in ISD? Does this reference need to identify the ‘type’ of MDR? Also, there is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 |  | Closed | [5 empty] | These issues are covered in Release 3 updates (DIN372 & DIN 070) . ISD updated to confirm participants recorded in M16, a new table M18 "DIP Participant Roles" was added.
MHHS-DIN-298 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Update to UMSDS method statement. | As I understand it, you are advising we should A flag the consumption data (even though it isn’t Actual), until the zero charge code D0388 UMS Inventory is received from the UMSO. Therefore - if we have an inventory, regardless of the energisation status of the MPAN, we always use an A Flag. But as you’ve stated, this means an IF-013 will be issued to us as UMSDS, because there is A data, against a De-Energised MPAN. If this is the design/requirement then it is understood – but I would like to call out that this should be detailed within the UMSDS method statement – so I think a DIN is needed to get this requirement added? |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement
MHHS-DIN-299 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | IF-013 update to include UMSO recipient | Further to this (DIN-298), the cause of this IF-013 being issued can only be that the UMSO has not provided the UMSDS with the correct D0388 UMS Inventory to use. Therefore – the UMSO has a requirement to receive the IF-013 to tell them this. However, the Interface Catalogue has not designed that this will get sent to the UMSO. I think this is a Design Issue too, and also needs a DIN raising so that the IF-013 is provided to the UMSO. |  | Closed | [5 empty] | No this is incorrect. UMSO is not involved with Consumption. If IF-021 submission is rejected this is an issue for the DS (incl. UMSDS) to address and Manage. Any issues regarding the metering onsite/energisation status need to be managed by the DS (incl UMSDS) with their appointing Supplier and Partner Metering Service. |  |  |  | DES138
MHHS-DIN-300 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | You are advising a Load Shape will always require the E Flag. But as you say if the MPAN is de-energised, that MDS will reject the IF-021. Is this therefore your answer – that MDS will reject the IF-021, and there is nothing that can be done about that, so we just need to accept we will get those rejections? If so, this isn’t really a satisfactory process, to know rejections will be received in this scenario. Can you just confirm that the solution here is we just need to accept we will get these rejections to the IF-021, which we will then simply ignore? If that is the case – again a DIN needs to be raised to write this into the Design so the process is documented. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. See DIN 506 which has updated DES138 to show that IF-014 also contains warnings for MPANs with consumption on de-energised sites. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement
MHHS-DIN-301 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | the corrective action on this scenario (DIN-300) occurring will be if/when the UMSO provides the UMSDS with a D0388 UMS Inventory – then the UMSDS will stop using and submitting the Load Shape data. There does not seem to be a mechanism in the Design for the UMSO to be made aware of this issue that would be of their making, so again needs raising as a DIN please. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. See DIN 506 which has updated DES138 to show that IF-014 also contains warnings for MPANs on de-energised sites. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement
MHHS-DIN-302 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | I’ve pulled together the below table. This covers all the possible scenarios of the UMSDS either having or not having the D0388 UMS Inventory. Combined with whether that D0388 UMS Inventory has load associated data within it. Also combined with whether the MPAN is Energised or De-Energised. Here I’ve listed which Settlement Period Quality Indicator should be used, and where applicable, which Estimation Reason Code should be used. Should this be included in the UMSDS Method Statement and if so, are you happy with the below. In Green are steps we understand. In Red, these remain Unknown to us based on the Design and your answers given. In Orange, these are answered based on your guidance on your email of 28 April – but are not specified in the written Design. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement
MHHS-DIN-303 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.2.3 - Changes to Data formatting to align with Swagger / DES-138 |  | Implemented |  |  |  | Interim Release 1 |  |  | Technical corrrection | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-304 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.4.3 - Case Sensitivity - additional information added to provide clarity on approach |  | Implemented |  |  |  | Interim Release 1 |  |  | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-305 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 5.1.7 - Additional Detail required for IF-47 / ISD to provide clarity on approach / steps |  | Implemented |  |  |  | Interim Release 1 |  |  | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-306 |  |  | 2023-05-22 | Tym Huckin | 3992 | Tym Huckin | Consultancy | Clarification/examples for DI-101 for BST/UTC cross over period | Further clarity / worked examples for UTC Settlement Date (DI-101) for BST / UTC cross over period. |  | Closed | [5 empty] | This is not a design change it is a Question/Clarification .
MHHS-DIN-307 |  |  | 2023-05-22 | CGI | 5042 | Dave Webster | Software Provider |  | Status code incorrectly included in required, although not in Standard Response Body Type. This is in Swagger 1.2. |  | Closed | [5 empty] | Duplicate of DIN-282
MHHS-DIN-308 |  |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | S0 Block required property | Add required property to all the S0 blocks in the interface definition |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to Swagger for all Interfaces to mark 3 fields in the S0 block as mandatory. | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-309 |  |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | Swagger Alignment to DES-138 | Define Transaction ID (DI-990) with no Min Length to align with DES-138. This is DT-014. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (DIP Transaction ID min length removed) | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-310 |  |  | 2023-05-23 | ELEXON | 5173 | Rob Golding | Central Body | Guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 | Guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 are to be applied (if at all), i.e. does the DIP need to consider the effective period and only accept messages on the production system when the message falls within this period? And if so what date within the message should be used as a check? Or the physical date/time of message receipt? Or doesn’t the DIP need to consider these dates at all and no check needs to be applied? |  | Closed | [5 empty] | This has been included in the DIP onboarding design.
MHHS-DIN-311 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-985 / DI987 both String 60. Swagger Min and Max Lengths aligned |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updates made to DES-138 for Length alignment to 60. Updates to Swagger to remove min length for DI-985 and DI-987. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-312 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-984 / DT-009 needs to be updated to be min 3 / max 5 length. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Sender Role - change on 01 Data Catalogue DI-984 as per description | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface
MHHS-DIN-313 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S1 - Sender Timestamp updated correctly (from sent timestamp) in Swagger to align with DES-138 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (renamed to Sender Timestamp) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-314 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - Publication ID Min Length updated in Swagger 1.2 to be 6 to align with DES-138 (rather than 7) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Publication ID Min Length now 7, not 6) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-315 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - DIP Correlation ID should have no min length to align with DES-138 (rather than min length of 1) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (DIP Correlation ID has no min length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-316 |  |  | 2023-05-25 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, all DT-006 and DT-006N should have min length 10 & max length 10 to be consistent. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated DES-138 01-Data Catalogue to align Data Type and provide consistency to Swagger. Removed DI-095 which is no longer used. | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface
MHHS-DIN-317 |  |  | 2023-05-23 | St Clements |  | Sean Cooper | SRO Design | B9xx array references within Swagger to be updated within DES138 | Update DES138 IF document to include reference to the B9XX Array references held in Swagger |  | Initial Assessment/Updating | Design ambiguous | N/A |  | Post Go-live Release |  | Update DES138 IF document to include reference to the B9XX Array references held in Swagger | Design Ambiguous | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-318 |  |  | 2023-05-23 | REC | 5049 | Jonny Moore | Consultancy | Addition of 'Effective from date' data items to RMP Status (regi) and MP Status in IF-050 | While completing the design phase for EES we noted that the following items with the IF-050 do not have an effective from date. - RMP Status (Registration) - MP Status These items currently have an effective from date held in EES and not including this in the IF-050 would have the effect of removing these items from EES. |  | Closed | [5 empty] | REF DIN-508 | No Change
MHHS-DIN-319 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S0 - EventCode to marked as required to align with DES-138 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Event Code marked as required) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-320 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, S1 - Environment (DT-013) should have min length 3 & max length 10 to be consistent with values. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | 01-Data Catalogue DI-991 Environment Set Min to 3. However, string length is 10, so max length should be set to 10 | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface definition
MHHS-DIN-321 |  |  | 2023-05-23 | St Clements | N/A | Sean Cooper | SRO Design | B005 add to IF-036 | Consider adding B005 to IF-036 so that incoming SP knows who previous SP were |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Added B005 to IF-036 so that incoming SP knows who previous SP were. Updated block name to B005 - Incumbent/Outgoing Service Providers | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-322 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B002 - Incoming Supplier MPID - Swagger aligned to DES-138 for min / max lengths |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Incoming supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-323 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B003 - Ougoing Supplier MPID - Swagger aligned to DES-138 for min / max lengths |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Outgoing supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-324 |  |  | 2023-05-24 | EDF | 4780 | Paul Saker | Supplier | NHHSP-BPM00C- Transfer of Reads on Change of Data Service process steps and messages clarification | NHHSP-BPM00C- Transfer of Reads on Change of Data Service details several process steps and messages related to obtaining and sharing register readings between the gaining and losing suppliers to agree a CoS, and to initiating the missing/disputed reads process defined in the Retail Energy Code where CoS reads are missing or need to be disputed/amended. However, it appears that there is no further detail defined within the Design Artefacts regarding how exactly these process steps would work, including amongst other things: • Timing/Operational Choreography – for example it is not clear exactly when losing and gaining suppliers would be expected to attempt to communicate with the meter, or the timescales for sending data obtained between suppliers. • Data to be included in messages – while BPM003C refers to the inclusion of ‘register readings’ in some of the messages it is not clear which registers should be included for smart meters and non-smart meters – for example whether that should just be the registers on a smart meter that the sending supplier uses for billing, or whether that should be all the 48 time of use registers stored on the smart meter. Additional input from Andrew Margan - Within the code workstream, we believe the Operational Choreography document needs to be updated to reflect SLAs. Without this, we can’t complete the Code drafting. If you disagree, we would appreciate an early heads up, so we don’t look disjointed in front of industry. |  | Closed | [5 empty] | This is not an MHHS Design Issue. D300 / Agree Reading SLAs are defined and set by RECCO. We have replicated the existing 5 day window for capture / submission of a reading(s) all other D300 timescales still apply as per RECC process. Register Readings can only be provided on the D0010 - where this is required [for smart meters] it would replicate the current as is process defined in the current DC BSCP
MHHS-DIN-325 |  |  | 2023-05-24 | CGI |  | Dave Webster | Software Provider | Status Code Missing from MsgBody | In the SubmitEvents StandardResponseBodyType object (SubmitEvents ¦ 1.2 ¦ MHHSPROGRAMME ¦ SwaggerHub), it states that “statusCode” is a required field. Yet its’ definition does not exist in the properties of the object. StandardResponseBodyType: type: object properties: transactionID: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-014-DIPTransactionID' senderUniqueReference : $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-995-SenderUniqueReference' correlationId: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-011-CorrelationID' sentTimestamp: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-003-DateTime' senderId : # the sender of this message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' recipientID : # indended (logical) recipient of the message, i.e sender of the original event message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' DIPConnectionProviderId : # physical recipient of the message (if different to recipient Id) $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' message: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-005-StatusErrorMessage' help: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-019-HelpText' serviceTicketURL: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-018-URL' required: - transactionId - sentTimestamp - senderId - recipientId - statusCode - message - help - serviceTicketURL |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | This has now been updated in V1.2 of Swagger StatusCode Added to the ResponseBody. | Technical corrrection | Supporting Docs |  | JSON/YAML files
MHHS-DIN-326 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Changes required to DES-138 / interface catalogue given changes in Migration Design e.g. the addition of interface IF003 and potentially ISD. |  | Closed | [5 empty] | Duplicate of 247 | No Change |  |  | None
MHHS-DIN-327 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | IF-005 User Guide | The IF005 User Guide explains how the IF005 should be populated. We have a request for clarification on whether the IF006 will be populated identically or if the Meter ID in the IF006 will reflect the Modified Meter Id in the IF005. Is IF-005 identical to IF-006, or is it with updated MTD's. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | IF-006 should be a facsimile of IF-005. In the case of change of MSN... MSN field will reference the (old) MSN and Modified MSN will be populated with new/revised MSN. All subsequent flows following the IF-006 will only reference the NEW/REVISED MSN. We further clarified this in a change to the Note(s) section on IF-006. | Data interface correction | Supporting Docs |  | DES138
MHHS-DIN-328 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | Operational Choreography Update: Addition of SLA for RS end appointment data to the CSS | The operational choreography does not include an SLA for the RS to send appointment data to the CSS or the timings by which the CSS and DSP should deliver their roles within the process. These need to be added to the operational choreography for clarity, noting the interaction with CR018. | CR018 | Closed | [5 empty] | RECCo confirmed closure of DIN following review of amendments to the Operational Choreography for CR018. ALL Updates between RS and CSS/DSP are existing interactions, covered by existig SLA's document in RECCO documentation. OPSC document was updated per Recco comment to highlight existing RECCO SLA in this area and to ensure primacy of the RECCO documented timings.
MHHS-DIN-329 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Approach on a business rule where the ERDS does not send a MEM de appointment / appointment for an MHHS migration where the same MEM is being appointed under MHHS arrangements e.g. they have the same MPID. The expectation is that smart and advanced MEMs will use the M role code for the interaction with CSS so from their perspective there should be no change. |  | Closed | [5 empty] | ERDS Interfaces are ouf of scope of MHHS. If a change to ERDS interface is required or efficiencies in its existing operation are possible to align with MHHS Design - this would be a consquential change. | No Change
MHHS-DIN-330 |  |  | 2023-05-25 | Ovo Energy | 5225 | David Morley | Supplier | Long Term Vacant | BSCP504 section 4.15.3 stipulates the criteria via which suppliers can classify sites as Long Term Vacant (LTV). BSCP701 stipulates actions that SDS shall take if the supplier nominates that a site is LTV. However, the criteria that suppliers shall use for classifying LTVs in MHHS is missing. Can you please signpost where the new criteria will be located? |  | Closed | [5 empty] | BSCP is responsible for revising the code specification, there are no changes to design specified. Code team will get in touch with the participant.
MHHS-DIN-331 |  |  | 2023-05-25 | MHHS | 4733 | Martin Freeman | Central Body | Secondary Routing | Secondary routing for IF-013 is specified as being conditional upon the value of DI-015. However, DI-015 (Connection Type Indicator) is a property of a repeating block, and there is no constraint in place to suggest that each element in the repeating block must have the same value for this (or any other) property, in which case multiple rules in the routing table could apply simultaneously. The routing table design seems to suggest that only a single rule should apply at a time and that routing should not be derived by blending multiple rules. If this is so, and a message is received where different elements in the B050 have a different Connection Type Indicator then there is no coherent way to implement this in conformance with the routing table. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Agree there was a routing contradiction for scenarios/periods where a different connection type was in effect. Interface notes section has been updated to direct the use of 'separate' IF-013 messages in such circumstances. Note also makes clear that repeating B050 blocks are acceptable where other elements (not Connection Type) of the CCC vary over the period to be defaulted. | Design Ambiguous | Supporting Docs | Default Consumption | MHHSP-DES138-Interface Catalogue
MHHS-DIN-332 |  |  | 2023-05-25 | MHHS | 4750 | Martin Freeman | Central Body | IF-013 Routing | In the routing table for IF-013 all rules are conditional upon S0.Eventcode == [ActivePowerDefaulted], which means that for IF-013 message where Eventcode == [ConsumptionOnDeEnergisedMPAN] there is no routing at all, which means when this message is sent to the DIP it will not be routed anywhere and will simply disappear. That's almost certainly an error. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Event code [ConsumptionReceivedonDeEnMPAN] has been moved from IF-013 to IF-014. The valid event code list and routing rules have now been updated for both interfaces to reflect the move. v1.2 of Swagger also updated to reflect this change Duplicate of DIN 255 | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue
MHHS-DIN-333 |  |  | 2023-05-25 | MHHS | 4760 | Martin Freeman | Central Body | Connection Type Required to Support Routing of IF-014 | All of the routing rules specified for IF-014 are conditional upon DI-015 (Connection Type Indicator). But IF-014 does not have any blocks with this property, which means this message won't get routed anywhere. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Block B067 - Connection Type Added to IF-014 in order to support routing requirements. Swagger v1.2 updated to reflect this change. (Duplicate of DIN256) | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue
MHHS-DIN-334 |  |  | 2023-05-25 | MHHS | 4766 | Martin Freeman | Central Body |  | The routing table for IF-018 specifies roles AMSC, UMSC, UMDC for Secondary routing. There are no such roles in either the DES138 nor the E2E001. |  | Closed | [5 empty] | Secondary Routing Review/Changes have superceded this issue - Ref DIN-268
MHHS-DIN-335 |  |  | 2023-05-26 | British Gas/Engage Consulting | 4640 | Neil Strange/ Haz Elmamoum | Consultancy | Four questions on IF004 | IF/PUB-004 – DIP Common Blocks referencing MHHSP-DES138-Interface Catalogue v5.1.1 As a minimum this needs to be referenced in the supplier requirements MHHSP-BRS004-Supplier Overview and MHHSP-BRS002-Metering Service requirements, but to ensure parties get sight of this we would suggest it needs to be included in a business process map and have associated requirements. For IF-004 to be useful to participants DI-999 – Event Code needs to be elaborated e.g. 1- Installation 2- Removal; 3- Exchange; 4 - Found (Where installed by Gas supplier and Elec Supplier takes ownership) C/M/O rules for DI-192, DI-193 and DI-194 need to be explained in the notes – presumably driven by event code Available is spelled incorrectly (available) for DI-192 and DI-194 there are a couple of angles here – 1) ensuring wider awareness and 2) it seems there is a question mark on the governance here as it is odd a flow has been added but industry does not appear to have been sighted on it especially with no associated referencing in artefacts and no process map, so effectively no one has any idea how it is supposed to be used. Although it was formally agreed not to include and use bilaterally....from a Large Supplier Constituency perspective, my members are keen to ensure design clarity and how flows are to be used or not, regardless of their ad-hoc / bilateral nature. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Updated BP009 Change of Metering to include the "optional" sending of IF-004 from MS via DIP to Supplier, if changes to Comms Hub need to be notified. Included same updated to BPD009 to reflect new BP steps. Other comments have been addressed previously and are reflected in DES138 IF-004 | Process Model correction | Meter to Bank | IF-004 | BP009 Change oF Metering BPD009 Change of Metering
MHHS-DIN-336 |  |  | 2023-05-26 | MHHS |  | Rob Topley/ Zak Hussain | SI Design | Requirements clean up in iServer | Process Step No. BP Step ID Process Map wording Interface ID Sender Recipient/Service Traceability Requirement Traceability Method Statement iServer Requirement Name iServer Step name Issues Found BP01 170 BP01 - 170 Send Site Tech Details on Metering Service Request MHHS-RS-LD-012.1 #N/A LDSO170a Send Site Tech Details on Metering Service Request Missing (only on BPD and traceability matrix) BP01 175 BP01 - 175 Receive Site Technical Details D0215 LDSO Metering Services MHHS-RS-MS-037.1 #N/A MET175 Receive Site Technical Details Missing (only on BPD and traceability matrix) BP03B 95 BP03B - 95 Manage SP Appointment Amendment Request Response PUB-035 DIP Supplier MHHS-BR-SU-35.1 #N/A SUP095a - Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP03B 96 BP03B - 96 Manage SP Appointment Amendment Request Response PUB-035 DIP Data Services Metering Services MHHS-BR-DS-11.1 #N/A ESP96 – Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP05 315 BP05 - 315 Issue Reading Data MHHS-IF-041 Data Service DIP MHHS-BR-DS098.2 #N/A DAT315 – Issue Reading Data Missing (only on BPD and traceability matrix) BP05 340 BP05 - 340 Process Reading Data PUB-041 DIP Supplier MHHS-BR-SU047.1 #N/A SUP340 Process Reading Data Missing (only on BPD and traceability matrix) BP05 350 BP05 - 350 Process Reading Data PUB-041 DIP LDSO MHHS-BR-LD009.1 #N/A LDSO350 Process Reading Data Missing (only on BPD and traceability matrix) BP010D 1055 BP010D - 1055 Receive updated Legacy information PUB-026 DIP Central Settlements MHHS-BR-RD-018.1 #N/A ECS1055 Receive updated Legacy information Missing (only on BPD and traceability matrix) All these requirements don’t exist on any requirement catalogues, they’ve only ever been on a BPD document or the traceability matrix (which are essentially the same document). Also, the highlighted traceability has a typo and is on a requirements artefact but is wrong on both the BPD and traceability matrix. |  | Closed | [5 empty] | Requirements have been found in BRS001, BRS004, BRS005, BRS014. Models have the correct steps identified. Unable to identify whats missing, checking with the originator. Confirmed with originator no further changes needed | No Change | Supporting Docs | Supporting Docs | BRS001, BRS004, BRS005, BRS014
MHHS-DIN-337 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger alignment to DES-138 | R0 - Response Message Min length updated to align with DES-138 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated R0 - Response in Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-338 |  |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier | BP003/BP002 to be updated to clearly show IF-036 going to both Import & Export supplier | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. BP003/BP002 to be updated to clearly show IF-036 going to both Import & Export supplier |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | On an Export Supplier COS, the Service Providers will be de-appointed on notification of the Secured Active. As the Export Supplier is unable to appoint their own Service Providers (in the case of Linked Import/Export), the auto-aligmnment functionality (BP011C) will trigger the correct Service Providers to be appointed and the Service Providers will be notified of the Supplier in IF-036. However this DIN has highlighted the need for the export Supplier to be notified of the Service Provider changes. BP003/BP002 updated from Step 255/245 to re-label "PUB-36" flow to Step 260 for the Supplier (prospective/incumbent) to state "PUB-036 for Import & Export Supplier". Change is not reflected in the BPM-003 for forward migration as linkages only become active when both Import/Export are migrated. See also 339 | Process Model correction | MPAN Ownership | Process Models | BP003 BP002
MHHS-DIN-339 |  |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier | IF-001 to be updated to be additionally sent to the Export supplier rather than just the import | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. IF-001 to be updated to be additionally sent to the Export supplier rather than just the import |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | On an Export Supplier COS, the Service Providers will be de-appointed on notification of the Secured Active. As the Export Supplier is unable to appoint their own Service Providers (in the case of Linked Import/Export), the auto-aligmnment functionality (BP011C) will trigger the correct Service Providers to be appointed and the Service Providers will be notified of the Supplier in IF-036. However this DIN has highlighted the need for the export Supplier to be notified of a new Import Supplier. BP001 updated to re-label "PUB-001" flow for the Supplier (prospective/incumbent) to state "PUB-001 for Import & Export Supplier". See also 338 | Process Model correction | MPAN Ownership | Process Models | BP001
MHHS-DIN-340 |  |  | 2023-05-26 | UKPN | 4547 | Neal Medley | Network Operator | ELEX-REP-02/02A report | The reports ELEX-REP-02/02A will only contain aggregated data for A(General LLF Class Import and C (General LLF Class Export). The I/F021 can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/014 Rejected Consumption Data Submission and I/F MDS Defaults Applied to any I/F021 data to ensure you are not using rejected data or are missing I/F 021 data in respect of an MPAN. MDS Method Statement to be updated to reflect |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Updated the below test to Section D within MDS Method statement: 17.4 The I/F021 ‘UTC Settlement Period Consumption Data’ can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/F014 Rejected Consumption Data Submission and I/F ‘Notification of Defaulted UTC Settlement Period Consumption Data’ to any I/F021 data to ensure LDSO’s are not using rejected data or are missing I/F 021 data in respect of an MPAN. | Design Ambiguous | Supporting Docs | Method Statement | MDS Method Statement
MHHS-DIN-341 |  |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | MUM Event not required by MDS | For IF-018 the event [MUMIndicator] is routed to MDS and indicates metered/unmetered. This event is not required by MDS as they can infer this from the Market Segment (Advanced, Smart and Unmetered). DIN raised to remove the routing |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | MDS Removed as Always Recipiant for Event [MUMIndicator] on IF-018 Routing rules | Data interface correction | Supporting Docs | IF-018 | MHHSP-DES138-Interface Catalogue
MHHS-DIN-342 |  |  | 2023-05-26 | UKPN | 5194 | Neal Medley | Network Operator | ELEX-REP-02/02A Consumption data clarification | The intent is that the daily volume on actuals or estimates are the sum of the appropriate consumption data. So when added together they should equal the summed Total of the Settlement Period data (Total Uncorrected Volume) barring any rounding errors. The data is given in MWh to six decimal places (i.e. to the nearest Watt hour). I assume DUoS billing only calculates to the nearest unit so would not expect any rounding errors to impact. The A flags are set out in the ELEX-REP-02/02A are the same as those set out in the CCC table in the VAS Method Statement which is also in the MDS Method Statement. I agree the list in the calculations only are missing the full list of SPQI that are deemed to be actuals as set out in the ELEX-REP-02/02A. DIN raised to correct the calculation |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Updated full list of actuals with the MDS Method Statement. The amended list added to the Method statement: A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6. | Method statement correction | Supporting Docs | Method Statement | MDS Method Statement
MHHS-DIN-343 |  |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | Routing rules table | The routing rules on the IF-037 sheet state that MDS will 'always' receive the DSDeApp event code, however the 'Always' column on the IF_LIST does not state Central Settlements for MHHSP-IF-037. IF list needs updating to reflect that the DSDeApp event always routes to MDS |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Decision taken to remove Recipiants (COLs G,H &I) from the IF_list - as just duplication of information contained within each of the IF spreadsheets. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue
MHHS-DIN-344 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B005 Custom Block update Swagger to align with DES-138. Current Metering Service MPID Length removed. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138. Current Metering Service MPID Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-345 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B024 Custom Block update Swagger to align with DES-138. DUOS Min Length removed. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138. DUOS Min Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-346 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design |  | IF-001 - B032 Custom Block update DES-138 to align with Swagger. Update DI-122 (Profile Class) to Integer from String-2. |  | Closed | [5 empty] | DI-122 remains as String 2 for Profile Class to support requirements for enumerations. | Data interface correction | Supporting Docs |  | None
MHHS-DIN-347 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B035 Custom Block - update Swagger to align with DES-138. Remove min length. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-348 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | IF002 correction | IF-002 - B074 Custom Block. Clarification on DI-091. DES-138 says this is 1 digit to the left of the decimal point. Swagger says 5 to 6. DES-138 to be updated to the correct value. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to be an Integer (1), Min of 1, Max of 1, example of 5. This now aligns with DES-138. | Data interface correction |  |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-349 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Correlation ID Issue IF-006 | Routing Rules in DES-138 do not always correctly identity where Correlation ID == Copy ie, it's missing for IF-005 / IF-006 so this needs to be updated correctly across all interfaces. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated IF-006/IF-008/IF-039/If-028/IF-026/IF-016 routing rules to show use of a "Copy" in Correlation ID (ie copied from the preceeding IF txn pairing) | Missing/incorrect validation rule | Supporting Docs |  | DES138
MHHS-DIN-350 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-005 B033 to align Swagger with DES-138 (Postcode removal, mandatory modified meter id) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Postcode removal, mandatory modified meter id) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-351 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B071 to align Swagger with DES-138 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-353 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B032 to align Swagger with DES-138 (SSC Min Length should be 4) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated SSC Min Length to be 4) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-354 |  |  | 2023-05-30 | SJW |  | Sarah Jones | Consultancy | Design team confirmation for sending of IF-037 and not IF-037 to losing MEM | Please see below details of a new design query related to the Registration Tranche of Code Drafting. We note that in BP011C there is a process whereby the Registration Service will auto de-appoint / appoint agents for secondary related metering points and linked export metering points as part of their validation. The business process only includes the sending of the IF037 to the Losing MEM and not the IF035. Please could you confirm that this is correct and that in this instance the Losing MEM would not receive an IF-035. If this is the case, we think there should be a change to Metering Service requirements MS-018 and 019 to clarify that where the Losing Metering Service receives an IF-037 with no preceding IF-035 then they should send the MTDs at this point. The alternative would be to include the sending of an IF-035 as well as an IF-037 accepting that these would arrive at a similar time. This would align to the process for managing retrospective MEM appointments where we understand that the Losing MEM would receive both the IF-035 and the IF-037. We also suggest amending MS-008, 008.1, 009 and 009.1 to recognise this nuance as follows: MSA/MSS must obtain Export MPAN de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. MSA/MSS should note this message will be automatically triggered when a change of Metering Service has successfully completed for the linked import MPAN or a new MPAN linkage has been put in place where the [linked import / primary related] MPAN has a different appointed Metering Service. Presumably there is a similar impact on the data service requirements that would need to be considered. |  | Closed | [5 empty] | Solution options discussed with SCS. Closed as covered under DIN 560 |  | Supporting Docs
MHHS-DIN-355 |  | DI-179 | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Number of Register Digits | Revisit and confirm IF-005 Cumulative Digits validation rule against latest version of the CP |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | All instances of DI-091 (IF-002,IF005,IF-006,IF-033,IF-036) updated to reflect updated logic. IF-005 validation rules updated also to reflect new guidance. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue
MHHS-DIN-356 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B073 - update Swagger to align with DES-138 (consumptionAmendmentSupplierReference max length) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated consumptionAmendmentSupplierReference max length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-357 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B902 - update Swagger to align with DES-138 (supplierConsumptionAmendmentRequests typo update) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated supplierConsumptionAmendmentRequests - remove typo) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-358 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-034 B070 - update Swagger to align with DES-138 (contractReferenceMeteringService max length 10) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated contractReferenceMeteringService max length 10) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-359 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: The method statement states that “The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN on notification of the set-up of that MPAN in MHHS-IF-001.” However, it will be the MHHS-IF-036 Registration Service Notification of Service Appointment & Supporting Info that will initially provide the fact that an MPAN has migrated to Central Settlements. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement updated with following text in red: 2.3 The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN within 30 calendar days following notification of the set-up of that MPAN in MHHS-IF-036 'Registration Service Notification of Service Appointment & Supporting information' or MHHS-IF-001 ‘Notification of change of Supplier’. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption
MHHS-DIN-360 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: 3.3 Where a years’ worth of data, >=75% and <100% of actual UTC Period Consumption data (where Settlement Period Quality Indicator = A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6) has been used to calculate the Annual Consumption, the Annual Consumption Quality Indicator should be set to “1”. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement updated with following text in red: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption
MHHS-DIN-361 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Greater than or equal to change for UTC Period Consumption Data | We need to raise a DIN on the AC method Statement and AC requirements: Likewise 3.6 needs to say greater than or equal to 182 days: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement updated with following text in red: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption
MHHS-DIN-362 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Section Name change | Section 5 incorrectly named Section 6 needs to be updated: 6. Transition and Next steps |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Section 6 has been updated to Section 5 within AC Method Statement and old section 5.1The initial Annual Consumption calculation, as set out in section 3.7 above may change, depending on the consideration of the working groups during the MHHS Transition requirements work- has been removed | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption
MHHS-DIN-363 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Load Shaping Service calculations | We may also need to document how this is calculated by the Load Shaping Service in the first year. I believe Helix have developed a calculation and this would need to go in the Load Shaping Method Statement and be referenced in the AC Method Statement. |  | Closed | [5 empty] | Kevin Spencer to arrange a session with Mike Ceney to discuss solution further. Upon further discussion with Kevin Spencer on 4/8/23 it was confirmed this DIN could be closed as the change is in relationn the AC Method Statement. No changes required to the LSS Method Statement | Method statement correction | Supporting Docs | Method Statement | Annual Consumption Meth 10
MHHS-DIN-364 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-035 - B066 - mark as mandatory in Swagger as per DES-138 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated so B066 is a mandatory for IF-035 custom block) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-365 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-004 - B093 - update Swagger to align with DES-138 (min Length on commsHubGUID / GPF-GAS-GUID) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated min Length on commsHubGUID / GPF-GAS-GUID) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-366 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 custom block - SSC add min length to align with Swagger |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B032 custom block - SSC add min length to align with Swagger) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-367 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 Profile Class - updated Swagger to be a String to align with DES-138 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B032 Profile Class Swagger to be a String to align with DES-138) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-368 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-013 - B049 updated Swagger to align with DES-138 (run Number optional) |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B049 Swagger to align with DES-138 (run Number now optional) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-369 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | Switch Cancellation Info Note | Update BP002/003 to add informational note that Registration Cancelations will be processed as soon as they are received by SCS from CSS i.e. Apps Lapsed through switch cancelation sent immediatly not held until Proposed App Date. Also updates to Forward Migration BP002/003 for consistency. Changes to OPC added the following words to OPC_190 in the Activity column (section 4.4) “(including Switch Status Updates e.g. Cancelled)” |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | BP-002/003 updated to include new informational Note in Supplier swimlane relating to CSS Switch Cancellations. OPC updated to make it clearer that Secured Active Processing includes Switch Status Update processing. to OPC_190 in the Activity column (section 4.4) “(including Switch Status Updates e.g. Cancelled)” | Process Model correction | MPAN Ownership |  | BP002, BP003, OPC001 Forward Migration BP002 & BP003
MHHS-DIN-370 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | IF-005 Update Window Guidance for Prev MS | Change IF-005 and Guidance Doc to allow Meter Updates within 10 day window for previous MS |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | New validation rule added to IF-005/MeterUpdate to allow previous MS to submit if within 10 day post appointment period. IF-005 User Guide section 9.3 updated to reflect same. | Missing/incorrect validation rule | Supporting Docs |  | DES138, IF-005 User Guide
MHHS-DIN-371 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team |  | Review design to ensure only Supression of IHD info for advanced segment and NOT "deactivation" of underlying IHD record. |  | Closed | [5 empty] | Confirmed that IHD details will be retained on Smart to Trad Exchange. Any IHD info present will be suppressed (ie not included in msg) if Segement is Advanced. No change required to documentation. Possible data cleanse issue - Dan T. to raise in Data Forum.
MHHS-DIN-372 |  |  | 2023-06-01 | MHHS | 5298 | Rob Golding | Central Body | Mapping Roles | There is a need to master the mapping of Market Participant Role to DIP Role within the MHHS solution. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New entity M18 created to show the DIP market roles. Minor corrections to M16 to clarify DIP ID field length. | Other | Supporting Docs | ISD Entities | MHHS-EDI-021-ISD_Entities
MHHS-DIN-373 |  |  | 2023-06-02 | MHHS | 5272 | Rob Golding | Central Body |  | There is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 |  | Closed | [5 empty] | Duplicate of DIN-297
MHHS-DIN-374 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Message Replay & Requeue functionality | Message replay and requeue functionality needs to be added to the DIP API interfaces, which requires changes to the Swagger / YAML definitions. Detail is required in the E2E design documentation to explain how the message replay and requeue functionality will work. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updates to the E2E001 design document to provide detail on how the replay and requeue will work. There are updates to Swagger to support new interfaces for /dip-channel/{id}/replay and requeue respectively. There is also a new MessageRequest Schema that is used to pass data into both of these interfaces. To support these changes, section 4.8 has been updated in the E2E001. | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents
MHHS-DIN-375 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Interface webhook configuration | Updates require to the pubconfig and webhook config to support per interface webhook configuration, alongside changes to support definition of recipient ID and role ID. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updates to the E2E001 design document to provide detail on how the webhook configuration will work, with information related to specific interface changes. There are updates to Swagger to support new interfaces for /dip-channel/{id}/pubconfig (POST and DELETE) respectively to support changes defined in the E2E001 (Section 4.5 and 4.5.1 and 4.5.2have been updated to provide more clarity / information). | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents
MHHS-DIN-352 |  |  | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Obsfucation Text | What text should be used for data obfuscation ? for things like Boolean fields (True/false) |  | Closed | [5 empty] | Closed as this is already included in section 4.3.2 of the E2E001 design document.
MHHS-DIN-376 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-099 changes required to ensure DES-138 displays the correct YAML name / Swagger aligns to this. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | "Register" spelling in name has been corrected in DI099, and DI-099 name correction for IF041 in DES138 | Data interface correction | Supporting Docs |  | DES138
MHHS-DIN-377 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-097 | DI-097 - In DES-138, this is defined as a string (2), but the existing data type is an Integer and this is an Integer enumeration. Need to update this to an Integer in both DES-138 and Swagger 1.2. |  | Closed | [5 empty] | Rejected / closed as enumeration of values requires string (2) therefore this is retained to support buisness requirements. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-378 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. This information has now been added to DES-138 5.2.1. | Data interface correction | Supporting Docs |  | DES138
MHHS-DIN-379 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-048 | DI-048 - clarity required on whether this is "meter manufacture make and type", rather than just "meter manufacturer". The first is an existing data type and links to the J number, so providing further clarity / rename would quickly ensure alignment in DES-138 and then subsequently in Swagger. |  | Closed | [5 empty] | Rejected / closed as this was discussed as part of previous work off items and description has previously been approved / accepted as Meter Manufacturer. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-380 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-052 | DI-052 in DES-138 currently has 4 enum values ie, - Active Import, Active Export, Reactive Import, Reactive Export. In MDD there are currently 38 options documented. Discussion around whether ISD Entity 47 should be referenced as the list of values allowed. This can then be aligned / referenced in other other documents ie, EMAR will reference ISD Entity 47. |  | Closed | [5 empty] | Rejected / closed as this was discussed as part of previous work off items. Only 4 values are required in MHHS / DIP, therefore only these values are referenced / used as part of the enumeration to avoid bringing data from existing systems into new systems when this is not required. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-381 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-842 | DI-842 - Confirmation that MDR's have DIP ID's? There has been discussion in various forums to understand whether they do and if not, then this data item needs to be removed in DES-138 and Swagger. |  | Closed | [5 empty] | Rejected / closed as MDR's do have DIP ID's, therefore this value will be retained. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-382 |  |  | 2023-05-06 | Design Team | 4570 | Neil Strange | Supplier | D0010 | In BP003C, at CoS traditional CoRs are transferred between suppliers via D0010. We believe this needs to be used for all meter types - as this will be needed for non-communicating smart and advanced meters – and BP003C needs to be amended accordingly. There is no mention of IF-041 and we do not believe that the DIP is expecting an IF/PUB-041 transaction between suppliers. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Supplier added as a Primary Recipient in the Routing Rules for IF-041 (DES138) - Supplier initiated Reads. Sending supplier would need to populate the DIP ID of Supplier(s) with whom he wished to share the reading. Working Group specifically decided not to discuss /include COR scenarios for Smart Metered Sites however this is not prevented by the Design - a note to this effect has been added to BP003C for clarity. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue BP-003C Transfer of Readings
MHHS-DIN-383 |  |  | 2023-06-07 | RECCO | 4558 | Sarah Jones | Central Body | Change of Segment Scenario | We cannot find anything in the design artefacts stating that the Metering Service is required to notify metering exchanges for change of segment within 2 WDs. We have found the following: MS-094: MSA/MSS must be able to publish Change of Segment Meter Exchange details and reads via the appropriate interfaces, where it is not formally appointed as the Metering Service but does have an accepted prospective appointment (Appointment Scenario = "SEG"). The MSA/MSS must issue the work update to Registration at the earliest opportunity but within [x] days of completion at the latest. OPC 240: Notification of works to be completed by D+3 Working Days (This should provide time for consumption to be provided using new MTDs ahead of the SF run.) The BP011 references the connection type update being provided by LDSOs within 2 WDs. There is no equivalent for metering updates. Will require DRG confirmation on if the 'x' should be 2 or 3 working days |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Updates to be made inline with DRG recommendation to reflect 3 working days | Process Model correction | Supporting Docs | Business Process Documentation | BP011 - Change of Segment DES138-Interface Doc BRS002- Metering Service Requirements BRS003 - Registration Service Requirements BRS005 - LDSO Overview OPC001 - Operational Choreography MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-384 |  | DI-174 | 2023-06-07 | St Clements | 4938 | Madison Layton | Software Provider | IF-038 and IF-039 blocks not the same | Block B020, B021 are not the same across interface IF-038 and IF-039. DI-140 and DI-138 (SP DIP ID) are in IF-039 but not in IF-038. Understanding was that with the DIP change that all data items in block are mandatory, the blocks were to be consistently defined across all interfaces. If extra DIP ID DI-138 and DI-140 data items are included in IF-038 then we need a new REG rejection code to allow us to reject where DIP ID is not the same as the sender DIP ID. Alternative is to separate the DI-140/DI-138 into their own blocks included on the IF-039 interface only. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Block data items were aligned in release 2. New validation rule on IF-38 add to ensure that Sender ID matches MS/DS CDC ID. New Error code REG1076 added to support validation rule. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-385 |  |  | 2023-06-07 | Design Team |  | Steve Weston | SI Design | Correlation ID | S1 Common Block - Correlation ID is mandatory in Swagger, but Optional in DES-138. Swagger should be updated to align. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Updated S1 Common Block, Sender Correlation ID in Swagger, as this is Optional in DES-138 to support business process and requirements. | Technical corrrection | Supporting Docs |  | JSON/YAML documents
MHHS-DIN-386 |  | DI-179 | 2023-06-07 | St Clements | 5258 | Madison Layton | Software Provider | Register Digits | REC Change R0102 has been approved by industry to amend the number of display digits validation Where the Meter Type is S1 the Number of Displayed Register Digits value must be either 6 or 5 Where the Meter Type is S2A, S2AD, S2ADE, 2ADF, 2ADEF, 2AEF, 2AF, S2B, S2BD, S2BDE, 2BF,2BDF, 2BDEF or 2BEF the value must be “5”. Where the Meter Type is prefixed with “S2C” the value must be “6”. Where the Meter Type is 2CDEF, 2CF, 2CDF or 2CEF the value must be “6” REG1097 validation on the IF-005 needs correcting with this change, and the population notes for data item DI-091 across multiple interfaces also needs correcting |  | Closed | [5 empty] | Duplicate of Register Digit DIN-355 listed above | Data interface correction | Supporting Docs | Interface Catalogue | Lis
MHHS-DIN-387 |  | DI-180 | 2023-06-09 | St Clements | 5269 | Madison Layton | Software Provider | Uplift metered indicator requirements | There are elements in the requirements that suggest that metered indicator would trigger a change to Market Segment. E.g. MHHSP-BP011-Change of ConType andor Mkt Segment-v5.1 Step 102 MHHSP-BPD011 - Change of Con Type or Market Segment v5.0 Step 102 Which states if there is a change to market segment RS would need to re-evaluate the market segment And MHHS-BR-RS-124 which include in brackets: Change of Connection Type (Change of Unmetered Indicator) MPRS will assess Market Segment against the ISD entity M7 which does not include Metered Indicator. Therefore a change in Metered Indicator in isolation of any other changes to data items in the M7 table/Related MPANs/Linked MPANs, will not trigger a change to Market Segment. As it will not trigger a change MPRS will not re-evaluate Market Segment base on a Metered Indicator change alone. The requirements need uplifting to reflect. |  | Closed | [5 empty] | Closed as discussed and agreed with SCS. | No Change
MHHS-DIN-388 |  |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | IF-036 Custom Routing Rules | Following discussions with SCS agreed that for reasons of complexity it would be better to adopt Primary rather than secondary routing to IF-036. New Requirement created for REGS to undertake the Primary Routing of IF-036. |  | Closed | [5 empty] | Ref DIN-507
MHHS-DIN-389 |  |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | Appointment Start Times | Do we need a formal validation Rule to check that Appointment Start times are referenced as Midnight Local ? Issue raised numerous times with SCS. Waiting for SCS to confirm their position. |  | Closed | [5 empty] | CLOSED - DUPLICATE OF DIN-207 ABOVE
MHHS-DIN-390 |  |  | 2023-06-13 | Siemens | 5534 | Tony Mason | Metering Service Provider | IF/PUB-018 | There appears an inconsistency in the Business Process Map, BP010, and the routing rules for the IF-018 where the Event Code = DUOSTariffIDChg. This information is confirmed to SPs on the IF/PUB-036 and would then be updated where there is a change on the 018 according to the Secondary Routing Rules. This notification is absent on the process diagram. Could you confirm the position and update the documentation accordingly? |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Update BP010B to show Data Service and Metering Service receiving PUB-018 for DUoS Tariff ID updates in line with the routing rules in DES-138. Update BPD010 process description to includes steps to recieve PUB-018 for Data Service and Metering Service. | Process Model correction | Meter to Bank | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-391 |  | DI-182 | 2023-06-13 | St Clements | 5304 | Madison Layton | Software Provider | IF-019 validation gap on principal and subsidiary MPAN | IF-019 is missing validation rules to ensure an MPAN is only listed once in the IF-019, need rules to ensure the sender cannot repeat same Subsidiary MPAN twice in the repeating B090 block, and cannot list the same MPAN as both Principal and Subsidiary in the same IF-019 message |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Created x2 new rules to prevent duplicate MPANS within repeating B90 groups within a single message. Error Code REG1059 created to support validation checks | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-392 |  |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Consent Fields | Raised by SCS. B068/DI-017/DI-018 - This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block B068 updated to be "must be provided" for smart meters. Data items set to mandatory non-nullable. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | Block text updated to show mandatory if smart meter present, and DI-017/D-018 updated to be mandatory non-nullable (applies to IF-026 only) | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-393 |  | DI-181 | 2023-06-13 | St Clements | 5274 | Madison Layton | Software Provider | De-appointment and re-appointment date order | MHHS-BR-RS-128.4 & MHHS-BR-RS-128.5 covers the requirement for MPRS to ensure MS/DS are aligned across Related/Linked MPANS, and where they are not to de-appoint the MS/DS and appoint the correct MS/DS. The de-appointment requirement specifies to set MS/DS ETD to D+1 and the appointment to set the MS/DS EFD to D+2. Why do we need to apply the de-appointment and re-appointment in the future? Would we not be better to use the previous day (D-1) for the de-appointment MS/DS ETD and the current day (D) for the appointment EFD? |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Discussed with SCS and agreed to update Registration Service requirements to De-appoint on D (MHHS-BR-RS-128.4) and appoint on D+1 (MHHS-BR-RS-128.5) as part of auto-alignment process | Requirement correction | Registration | Auto-alignment | BRS003
MHHS-DIN-394 |  |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Annual Consumption Fields | Raised by SCS. B059/B027/DI-0148 This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block updated to be "must be provided" if available, however data items now need to be set to mandatory non-nullable. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-0148 updated to be mandatory no-nulls and data type updated to DT-016 in Data Catalogue. Data Type corrected to DT-016 in IF-002 and IF-036. | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-395 |  |  | 2023-06-13 | St Clements | 5510 | Vicki Holland | Software Provider | Obfuscation of Connection Type Indicator in IF-021 | The DES138 interface catalogue specifies that the data item Connection Type Indicator will be obfuscated for all parties as it is required for routing only. Can this please be changed so that it is visible? The reason for this request is that suppliers often process data differently for the different connection types and therefore its important that they can internally validate or route data according to the connection type of the MPAN. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Obfuscation of connection type removed from IF-021/IF-013 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-396 |  | DI-183 | 2023-06-13 | St Clements | 5305 | Madison Layton | Software Provider | Update IF-019 REG1001 to only apply to Create and Add event codes | IF-019 REG1001 rule applies to all event codes. The MPAN could be disconnected with linkages still in place. If REG1001 is applied on remove event codes, then there will be not means by which the Supplier/DNO can remove the linkage after a disconnection. Suggest REG1001 rule should only apply to the Create and Add event codes. This would be consistent with the existing validation on the DB05 and D0386. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF-019 MPAN Status Validation Rule removed for all "Remove MPAN" Event Codes. i.e. I can still perform remove MPAN from group task if MPAN is disconnected. SCS rejected option of auto de-linkage as part of De-Registration Process. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-397 |  | DI-184 | 2023-06-13 | St Clements | 5306 | Madison Layton | Software Provider | IF-019: REG0007 to only apply to Related event codes and not to Linked Import Export event codes | REG0007 on IF-019 interface is currently written to apply to both Related and Linked MPANs. The intention of this existing rule on D0386 is because Related MPANs switch together, and so changing the relationship during a switch can create a split supply relationship. However Linked MPANs do not switch together and so this is not currently applied to the existing DB05 validation rules. Suggest REG0007 only apply to Related event codes and not to Linked Import Export event codes? |  | Closed | [5 empty] | Following discussions with SCS it has been agreed to prevent all changes to MPAN Linkages whilst an Active Switch is in progress. This is the safest approach when considering both CSS and Auto Alighment functionality considerations. No change to existing Design Documentation required.
MHHS-DIN-398 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD Stores LLF data | Can we have an ISD entity ID for LLF data. This would be required for the API used to retrive the data from ISD data store. Are you happy for us to create and put it in the Guidance note. |  | Closed
MHHS-DIN-399 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD publishes full data to Elexon Central Systems | Requirement should be reworded to be "ISD must make available the data sets required by LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. ISD must make available the entire current data set to LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. |  | Closed | [5 empty] | Agreed in a session with Elexon 26/07 that the requirements document will not be changed as the requirement has already been fufilled by Elexon in line with the current requirement.
MHHS-DIN-400 |  |  | 2023-06-14 | SRO Design Team | N/A | Sean Cooper | SEO Design | REGS Validation Rule Clarification | REG1089 conditions updated to provide more clarity. Existing wording refered only to a Subsequent App - this is now better defined as an Appointment with a prior/earlier Sender Timestamp. No functional change. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | For IF-031 Validation rule text updated to specifically reference Sender TimeStamps so as to provide more clarity on the nature of the val rule/when generated | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-401 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | IHD/SMSO Fields | IHD Install Status and IHD Status Effective from Date fields should be optional (i.e. nullable) when providing an IHD update in IF-025/IF-026. SMSO and SMSO Effective from Date fields should be optional (i.e. nullable) when providing an SMSO update in IF-025/IF-026. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-137/ DI-136 in block B030 updated to Optional (O) in IF-025 and IF-026 DI-134/ DI-135 in block B031 updated to Optional (O) in IF-025 and IF-026 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-402 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Import/Export Fields | Linked Import/Export MPAN and Linked MPAN Energy Direction will always be provided so should not be nullable |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-038 updated to Mandatory No nulls and Data Type updated to DT-002 DI-151 updated to Mandatory No nulls On the 01-Data Catalogue | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-403 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Meter Manufacturer Field | Meter Manufacturer is optional (ie nullable) when provided in IF-002, IF-006, IF-033, IF-036 as in IF-005 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-048 updated to Optional (O) in IF-002, IF-006, IF-033, IF-036 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-404 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Proposed Appointment Response Code Field | For Response code A there may not be any text to populate for DI-143 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-143 updated to conditional (C) based on DI-979 = L or R in block B007 in IF-034 and IF-035 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-405 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Response Message Field | For Response code A no text to populate for DI-980 |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-980 updated to conditional (C) based on DI-979 = R in block R0 in 02-DIP Common Block tab | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-406 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Sender DIP ID Field | Sender DIP ID should always be provided in S1 Common Block |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-997 updated to mandatory (M) in block S1 in 02- DIP - Common Block tab | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-407 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | COS During SEG Issue | Discuss with SCS the option of allowing non-appointed MS to update MTDs even if App has lapsed due to COS activity. If not then need to update process map to call out need for manual exchange of MTDs as Work MS could never submit if IF005 |  | Closed | [5 empty] | Closed, SCS unable to support alternative solution. Design Team have reviewed the existing process map note and believe this already provides enough information for participants. | No Change
MHHS-DIN-408 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD is the master for data contained both within ISD and MDD during Transition | The requirement is a bit ambiguous as could be read as all ISD and all MDD rather than just ISD data + overlapping MDD data. We don't want to be the master for MDD only data |  | Closed
MHHS-DIN-409 |  |  | 2023-06-14 | St Clements | 5510 | Vicki Holland | Software Provider | ISD Entity M5 – Consumption Component Classes | EDI021 ISD entities document shows that the settlement period quality indicator in entity M5 is a comma separated list of possible values. This will be difficult to use in systems that need to refer to this data. Could this instead show Actual or Estimate? Alternatively could this be split into parent and child entities to avoid a comma separated list? Metering Service ID MPID is incorrect and must be changed to {MS Id} also in ISD Entity M8 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Amendments relating to “Valid Settlement Period Quality Indicator Set” wording and field length in section M5 of EDI021 ISD entities document. Change also made from Metering Service ID MPID to Metering Service {MS Id} in Entitiy M8. An objection was raised against this DIN. Following discussion at the DRG about this DIN it has now been moved to Interim Release 5. A decision was made at DRG to go with OPTION 2: Change Existing Layout – Remove list element in favour of individual row(s) for each valid combination for the Valid Settlement Period Quality Indicator Set. Option 2 changes have been implemented to section M5 of EDI021 ISD Entities. Following the change to the layout the amendments to the data item will revert back to its initial name of Settlement Period Quality Indicator. and a data type length of 5 characters | EDI021 ISD Entities | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-410 |  | DI-487 | 2023-06-14 | St Clements | 5542 | Virginia Patey | Software Provider | DI-487 definition incorrect for REP-002 on Swagger | DI-487 energised MPANs is defined as an Integer in the Interface Specification, yet is defined as a String in Swagger. |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | DI-487 updated in Swagger 1.2 to align with Interface specification for REP-002 | Data interface correction | Supporting Docs |  | Swagger 1.2
MHHS-DIN-411 |  | Migration | 2023-06-14 | ESG | 4810 | Patricia Parker | Software Provider | Migration Segment Categorisation | The Migration Design currently specifies that Market Segment needs to be recorded before the Migration phase. This should be changed so that it is no longer required. Until an MPAN is migrated, there is no way of maintaining the market segment between the RS and EES using the legacy interface between these two services. However, meter type and connection type will be available in both the EES and the RS, so Suppliers can use a combination of these values to derive the correct market segment. |  | Closed | [5 empty] | 03/08: SCS confirmed in a session with SC that they agreed that Segment is a derived value based on Connection Type and MTR. There are validation rules that prevent the migration if Connection Type (and therefore segment) is not already defined in REGS. To address the original question Segment will always be known at the point of migration. Therefore, no changes are required to Migration document. 13/07: John Wiggins to have offline discussion with Sean C as DIN requires wider discussion at DRG to progress SRO Team disagree with this Migration Request. Market Segment must be known prior to the selection of MHHS Service Providers. Market Segment is a derived field based on Connection Type and Meter Type. Connection Type must be set before Migration / Meter Type already known so Market Segement CAN be derived, set and maintained prior to MPAN migration. No change to baseline documentation Required.
MHHS-DIN-412 |  |  | 2023-06-14 | MHHS | 5022 | John Wiggins | Central Body | Update to MDD | Migration request to ensure that Elexon add MHHS as a value to MDD. Page 35 of the Design Document under Reverse Migration states that -A default MPID of ‘MHHS’ will be created for the DC, MOP, DA appointments. Will MHHS be contained within MDD as a valid set as there is no reference in the document to update MDD with this value. |  | Closed | Design gap | TBC |  |  |  | As the Migration documentation was approved via DAG and following discusion with RecCo and BSC the updates are being documented in. This is being picked up in an update to DES196 Dflow interface |  |  |  | DES196
MHHS-DIN-413 |  | Migration | 2023-06-14 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | Reading Type (J0171) will be updated with three new values: Forward Migration CoA Forward Migration CoS Reverse Migration CoS Reading Type (J0171) will no longer use Initial or Final for migration reads between Suppliers or DC/DS but one of the above new codes will be used. Meter Reading Reason Code (J0332) will no longer be used to identify migration reads, all reference to this will be amended to Reading Type (J0171) in the guidance document. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | This DIN replaces DIN-442. Introduction of a new worksheet called 'Migration Change' reflecting the D-Flows changes supporting migration. Reading Type (J0171) has three new Reading Type values as follows: V - Forward Migration CoA X - Forward Migration CoS Y - Reverse Migration CoS For the other part of the DIN, "Reading Type (J0171) will no longer use Initial or Final for migration reads between Suppliers or DC/DS but one of the above new codes will be used." - This already exists in the Migration documentation therefore no change on this. | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-414 |  |  | 2023-06-14 | British Gas |  | Mohammad Amin Fuggawala | Supplier | D0275 in D-Flow Document | Ref Previous DIN-244. In the "DES196 D-Flow Document" the D0275 is showing as redundant. This is misleading it should be marked as by agreement between contracting Supplier-DS. Document should be updated to reflect this. |  | Closed | [5 empty] | Centrica have been notified on closure of DIN. Update was delivered in the published V1.0 of DES-196 as part of July DAG and the updated version is available on the Collaboration Base. | No Change
MHHS-DIN-415 | RT |  | 2023-06-14 | Elexon | 5702 | Mike Ceney | Central Body | Routing IF-026 to LSS | IF_026- For Routing Rules it states for Event Code/Conditions [SSC], [ProfileClass] and [SSCandProfileClass] that this should be routed to MDS, is this incorrect as MDS does not use these items in any calculations or outputs, this should state LSS |  | Implemented |  |  |  | Interim Release 2 | 2023-06-23 | IF-026 [SSC] and [ProfileClass] have been removed as of Interim Release 1. Update DES138 IF-026 to route to LSS on event [SSCandProfileClassChange] | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-416 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-001 New App Scenario Code MCS (Migration Change of Supplier) | Create new Appointment Scenario Code of MCS |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF -031 New valued added to DI-800 data catalogue and Swagger 1.3 updated to reflect new value | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-417 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-002 Validation Rules for Scenario MCS (Migration Change of Supplier) | New Val rule to check MCS is only used for legacy non-migrated MPAN where Supplier is not current supplier (and not in past) |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-418 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-003 New App Scenario Code MCA (Migration Change of Agent [Service Provider]) | Create new Appointment Scenario Code of MCA |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF-031 New valued added to DI-800 data catalogue and Swagger 1.3 updated to reflect new value | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-419 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-004 Validation Rules for Scenario MCA (Migration Change of Agent [Service Provider]) | New Val rule to check MCA is only used for legacy non-migrated MPAN where Supplier is current supplier and now active Switch is in progress (and not in past) |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-420 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-005 - IF-31 Check valid MHHS Supplier | If MCS/MCA code used is Supplier a valid MHHS Approved/Registered Supplier |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-421 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-006 - Prevent use of Migration Scenario IDs | IF MCS/MCA code used for already migrated mpan - reject appointment for invalid Scenario code(s) |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-422 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-007 Connection Type/Segment not yet Populated | New error required if Connection Type, DUos Tariff ID or Segment is not set prior to migration. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Validation Rule created for IF-031 to check that MHHS Standing Data is present and aligned. REG0011 Error created to support this validation Rule. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-423 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-008 Auto Realign Functionality | New REGS Requirement - Only action the auto-realign functionality on MPANs where both Linked MPANs are in a Migrated state. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Req RS-146 added to REGS Requirements Document to ensure that Auto-Align functionality is only executed if all MPANs in a related and/or linked group have sucessfully migrated to MHHS Operation. | Requirement correction | Meter to Bank | Requirements Documents | BRS-003-Registration Service Requirements
MHHS-DIN-424 |  | DI-185 | 2023-06-16 | St Clements | 5335 | Madison Layton | Software Provider | MPRS access to correlation ID | IF-019 is sent to the LDSO for LinkedImportExport event codes, if the LDSO approves the request they will submit an existing DB05 flow into MPRS. If the DB05 is accepted by MPRS, it will send an IF-020 to the Supplier to confirm the change to Linked Import Export association. However MPRS would not have access to the correlation ID that was received by the LDSO on the IF-019, and so would use a new correlation ID on the IF-020. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF20/IF19 Note amended explaining that it will not be possible to Link IF-019/IF020 messages together using Correlation ID , in the case of Linked MPANs. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-425 | SC | Migration | 2023-06-19 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | 8.1.3 step 12 Migration Design Document : Validation Status (J0022) references will be updated to Meter Reading Flag (J0045) |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | 8.1.3 step 12 Migration Design Document : Validation Status (J0022) references will be updated to Meter Reading Flag to T or F (J0045) | Design Ambiguous | Supporting Docs | Interfaces | Migration Design Document
MHHS-DIN-426 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG-009 New Rejection Code for D0205/D0203 | Response to a D205 is a D0203. 1. A New Rejection Condition/Code is required where D0205 is received following processing of IF-031. 2. Proposed new D0203rejection code is 62 "MHHS Fwd Migration in Progress or Completed" |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Point 1 already exists in the Migration documentation therefore no change on this. Point 2 is satisfied by updates in DES-196. Introduction of a new worksheet called 'Migration Change' reflecting D-Flows supporting migration. (J0107) Rejection Reason Code 62 added with the following details "MHHS Fwd Migration in Progress or Completed" | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-427 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-010 ISD Change M16 | No change Required - SCS can use ISD M16 - which contains MIPD/DIP Role and Effctive From date. This can be used to determine if a Supplier is MHHS qualified. This is better apporach that adding a transiant "Qualified Yes/No" field to this table. Therefore NO changes to documentation required. |  | Closed
MHHS-DIN-428 |  |  | 2023-06-19 | British Gas | 5835 | Neil Strange | Supplier | MEX before SSD scenario | When a CoS is in progress and there is a MEX before SSD, how will new supplier get the MEX details As the incoming supplier has already received the IF36 - would there be a new IF36 or would it be a PUB006? In addition how would the new MS and DS be made aware of this? - the old MS has X days after the job is completed to update the industry and a CoS could have happened before the old MS can update the other participants. |  | Closed | [5 empty] | BAU Design deals with 'regular' MEX before COS type scenarios (note previous MS Update Period - PUB-006 would be issued to impacted parties). Complexity arises where there is a COS overlapiing with Change of Segment/Connection Type (ie SEG Appointment)... Following discussion with SCS - low probably, low occurance vs. complex change. Ref existing guidance on BP016 there would need to be a manual interaction between Supplier and MS. No Change to existing Documentation Required.
MHHS-DIN-429 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG-011 Changes to D0170 | 1. Change D0170 flow so that MPRS/Registration Service is valid Sender of this flow. 2. New value for "Request Action Code" is needed to denote a Migrating account and if its CoS or ChgOfSP method. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Introduction of a new worksheet called 'Migration Change' reflecting the D-Flows changes supporting migration added in DES-196. Point 1. D-Flow ID (D0170) Request for Metering System Related Details new Scenario Variant FROM Electricity Retail Data Agent TO Electricity Supplier added. Point 2. Introduce two new Requested Action Code values as follows: 24 - Migrated Metering Point (CoA) 25 - Migrated Metering Point (CoS) | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-430 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-12 New Val Rule for IF-019 | Reject any changes to Related MPANs where any MPAN referenced (or in realted group) is subject to an active Migration SP Appointment Process |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Validation Rules and Error Code created to prevent changes if MCA Appointment Type Exists (Note: prevention if MCS exists is realised through existing check on if Switch is in Progress) | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-431 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-13 Change to D0386 | Change D0386 validation to reject changes to related MPANs if any related MPAN in group is subject to active Migration SP Appointment Process |  | Closed | Design gap | TBC |  |  |  | Update Migration Design Document D0386 validation to reject changes to related MPANs if any related MPAN in group is subject to active Migration SP Appointment Process | Design Ambiguous | Supporting Docs | Interfaces | Migration Design Document
MHHS-DIN-432 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-014 Appointment on Secondary Related MPAN | Extend existing 1039 check to include MCS.MCA Appointment Scenarios. |  | Closed | [5 empty] | Existing Validation Rule(s) around REG1039 will already cover Migrating MPANs - No Documentation Change Required.
MHHS-DIN-433 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-015 Switch in Progress Mig Rejection | New IF-031 validation to reject MCA/MCS DS and MS Appointments if an [any] active Switch is in progress with NEW Rejection Reason Code (note 1095 code referenced in Migration document has already been used elsewhere) |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New validation rules and REG9XXX Exception codes added to ensure correct usage of MCA/MCS Appointment Scenario Codes. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-434 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-016 New IF-003 | Previously DIN-247, Introduce IF-003, no changes from original proposal. 1. Update DES138 new tab, update IF List. Update New Data Items 2. Review E2E doc. 3. Update secondary Routing Rules (Avenade Techncal Doc) to include 4. Update Swagger |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Add data items DES138-Interface data Cat and to IF-003. Created new Data items: DI-500 MHHS Regime End Date, DI-501 Rev Migration Incoming MOP MPID, DI-502, Rev Migration Incoming MOP Eff From Date, DI-503, Rev Migration Incoming DC MPID DI-504 Rev Migration Incoming DC Eff From Date. Swagger v1.3 updated to reflect new IF-003, Blocks (B096/B095/B094) & Data Items (as above). | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-435 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG-017 D0304 & D0303 | 1. New D0304 Validation Rule 2. New D0304 Rejection Reason Code "Q - MPAN Fwd migration in progress or completed" 3. Change D0303 so as to make "Eff From Settlement Date REGI" a non mandatory data item within the flow (an alternative to suggesting that outgoing MS no longer issues a D303, only the incoming MS would send) |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Introduction of a new worksheet called 'Migration Change' reflecting the D-Flows changes supporting migration added in DES-196. Point 1 already exists in the Migration documentation therefore no change on this. Point 2 New Response Code Q "MPAN Fwd migration in progress or completed" added against J2255 MPAS D0304 Response Code as part of D0304. Point 3 Change requirement to populate this date from Mandatory to Optional against J0049 Effective from Settlement Date {REGI} as part of D0303. | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-436 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG0-018 D312 | 1. New D03012 Validation Rule 2. New Rejection Reason Code "AD - MPAN Fwd migration in progress or completed" |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Point 1 already exists in the Migration documentation therefore no change on this. Point 2 is satisfied by DES-196. Introduction of a new worksheet called 'Migration Change' reflecting D-Flows supporting migration. against J2256 MOP Flow Response Code as part of D0312 | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-437 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-019 IF-005 Validation Rule | 1. New val rule to prevent IF-005 while MCS/MCA Appointment is in progress 2. New Error Code (REG9003) |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | REG9003 - MHHS MTD Updates cannot be used until Migration has completed, Created and new validation rule added to IF-005 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-438 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-020 REGS Design Clarification | SCS Should issue L1/L2 Msg Status message with RCP1061 for any MPAN at the incorrect status where a DIP Message is received |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | This is a Migration Requirment which participants should take into account as part of their Migration Designs. However, for clarity a note has been added to RCP1061 entry in the Intoduction Section of the Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-439 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-021 No Supplier Updates during Rev MIgration (IF-025) | 1. New If-025 val rule to check if Rev Migration Switch is in progress 2. New error code |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | REG9002 - Supplier Data Items Cannot be Maintained for Reverse Migration Account, Created and applied to IF-025 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-440 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-022 No CDCs Updates during Rev MIgration (IF-038) | 1. New If-038 val rule to check if Rev Migration Switch is in progress 2. New error code |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | "REG9001 - CDC Marker Cannot be applied to Reverse Migration Account", created and applied to IF-038. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-441 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-023 No AC Updates during Rev MIgration (IF-040) | 1. New If-040 val rule to check if Rev Migration Switch is in progress 2. New error code |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement section 5 has been updated with the text below in red: Where an MPAN is no longer active under MHHS during the transition phase the Market-wide Data Service shall not calculate or submit an annual consumption on the IF/PUB-040. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption
MHHS-DIN-442 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-024 D0010/D0086 New MR Reason Codes | Three new MR Reason Codes for use in D0010: Forward Migration COS / Forward Migration COA / Reverse Migration |  | Closed | [5 empty] | Original migration design. Superceded by DIN-413.
MHHS-DIN-443 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG-025 D0155 New Agent App Reason Codes | 1. New Valid value for service reference "REVM" 2. New valid value for Service Level "REVM" |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | D-Flow Ref D0155 updated for data items J0274 service reference "REVM" and J0275 Service Level "REVM" in DES-196. | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-444 | RS |  | 2023-06-19 | ESG |  | Patricia Parker | Software Provider | IF-01 Incoming supplier for Import/Export MPANs | Clarification required with SCS. If it is known that an alternative MPAN has the same SSD then we do not want the old supplier ID as the linked supplier on the IF-01, we want the new supplier to be populated |  | Closed | [5 empty] | Discussed with SCS and they have confirmed that where co-incidnet COS occurs they would look to populate the [new/incoming] Linked Supplier ID.... No change to documentation required.
MHHS-DIN-445 | SB |  | 2023-06-19 | Utiliteam |  | Richard Palmer | Software Provider | Spec of IF-024 in DES138 Interface Catalogue | The Population Notes for DI D-000 in Group S0 has ‘IF-025’. This error was in v5.0, and is still in v5.1.1 |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | The Population Notes for DI D-000 in Group S0 has been updated to ‘IF-024’ in IF-024. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-446 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-026 Migration DIP Reporting Reqs | Reqs for x4 new Reports -- Flag at the next DIP DAG |  | Closed | [5 empty] | Closed and for the Migration Team to pick up. Awaiting further internal discussions re DIP Reporting Strategy.
MHHS-DIN-447 | SW |  | 2023-06-21 | Kraken | 5980 | Angelos Rizoyannis | Software Provider | Conditional Mandatory not applied in Swagger correctly | IF-041-CustomBlock: The field B065List is stated as optional in the comments, but the API schema does not reflect this. This field that is conditionally optional in DES-138, but this is not defined as such in Swagger ie, OneOf, AnyOf. This needs to be updated in Swagger to align correctly. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | In Swagger 1.3, updated IF-041-CustomBlock: The field B065List and B064List will be either / or as they are defined as conditionally mandatory in DES-138. This uses AnyOf notation in Swagger. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-448 | SW |  | 2023-06-21 | Kraken | 5980 | Angelos Rizoyannis | Software Provider | Mandatory fields not applied correctly in S1 block | S1 Common Block: The 'properties' and 'required' sections of the API schema for the S1 common block have conflicting information. The 'properties' section includes fields like senderTimestamp and senderRoleID, while the 'required' section lists sentTimestamp and senderRole. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Updated Swagger 1.3 to align properties and required sections so that fields are called senderTimestamp and senderRoleID. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-449 | SC |  | 2023-06-21 | SRO Design Team |  | Sean Cooper | SRO Design | Change to IF-037 | Include Block B002 into IF037 so that outgoing MS is aware of incoming Supplier on a COS. This will allow the SP to populate the D0303 to MAP. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Block 002 added to IF-037 for use where event code is MSDeapp, this is so that the outgoing MS is informed of who the incoming supplier is so that D303 can be correctly population. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-450 | SC | DI-196 | 2023-06-22 | RECCO |  | Sean Cooper | SRO Design | Change to IF-005 Validation Rules | Change made to IF-005 validation Rules to allow previous MS to update Meter Location only - during the 10 day post appointment period. This will allow for scenarios where there has been relocation only activity immediatly prior to a change in MS. All other MeterUpdate functions apart from Change of Meter Location shall be rejected per wider agreement that only active MS should have the ability to change the characteristics... This change originated from R1 Comments feedback from RECCO |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF-005 Validation rules updated to include new "REG0008 - Amendment Requested cannot be undertaken by Previous Metering Service" error condition and code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-451 | SC | CR-018 | 2023-06-22 | Design Team |  | Sean Cooper | SRO Design | CR - 018 Registration Service OOH Ops | CR18 looks to specify Registration Service Out-Of-Hours Operations. | CR018 | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Following feedback provided on the redlined version of the Operational Choreography, and following discussion on CR018 at PSG, the SRO maintained the DAG Chair’s decision to approve the implementation of CR018. CR Contents incorporated into a new Section 7 of Ops Choreography Document. Updates to clarify low level processing details in Section 7 Out-Of-Hours Processes table. Following feedback from DNO Review - Additional updates to replace the term ‘SLA’ with the phrase “target response time(s)”. Changes to Column headings to ‘When’ across the Operational Choreography document to align with Code Drafting convention. Addition of Intro text and removal of text “or Performance Regime” in Section 5. | Technical corrrection | Supporting Docs | Operational Choreography | MHHSP_OPC001_Operational_Choreography
MHHS-DIN-452 | SC |  | 2023-06-22 | St Clements |  | Sean Cooper | SRO Design | Refine Consent Checking Rules on IF-031 | Further refine Consent checking rules so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing . Updates to IF-031 validation rules to reflect this change. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF-031 validation rules updated per the DIN Details. Consent checking rules added so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-453 | MF | DI-124 | 2023-06-22 | St Clements |  | Mike Fensome | SRO Design | Issuing of IF-020's | Highlighted that LDSO's could issue an IF-020 with details of import/export linkages without having received notification from the Supplier |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Added note to IF-019 and IF-020 to inform Suppliers that Import/Export linkages could be received via PUB-020 unprompted by the Supplier issuing IF-019. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-454 | SC |  | 2023-06-26 | St Clements |  | Sean Cooper | SRO Design | Update to ISD M7 | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service. added rule to support REG0011 logic in IF-031. | Requirement correction | Supporting Docs | ISD Document | MHHSP-DES138-Interface Catalogue MHHSP-EDI021-ISD Entities
MHHS-DIN-455 | SC |  | 2023-06-23 | St Clements |  | Sean Cooper | SRO Design | Update Op Choreography (Event Move from IF-013 to IF-014) | Update Ops Choreography to take account of the movement of event [ConsumptionOnDeEnergisedMPAN] which was moved from IF-013 to IF-014 (DIN-255). |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF-014 Deadline split into two. First [ActivePowerRejected] remains UNCHANGED. Deadline for [ConsumptionOnDeEnergisedMPAN] is also UNCHANGED but moved from IF-013 row into IF-014 Row, to mirror the change delivered by (DIN-255). OPC_580 ID details updated in OPC001 Operational Choreography document. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP_OPC001_Operational_Choreography
MHHS-DIN-456 | SC |  | 2023-06-23 | St Clements |  | Sean Cooper | SRO Design | Swagger Correction - DI-844 | Corrected x2 invalid referenced to "AssignedMRDRequestEffectiveFromDate" should have been "AssignedMRDEffectiveFromDate" in Block 066 |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Corrected x2 invalid referenced to "AssignedMRDRequestEffectiveFromDate" should have been "AssignedMRDEffectiveFromDate" in Block 066 | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-457 | SC |  | 2023-06-23 | St Clements |  | Sean Cooper | SRO Design | Change to DTN Validation of D0350 | Implement DTN Validation of D0350 to prevent future dates |  | Implemented | Design gap | TBC |  | Interim Release 8 | 2024-03-20 | CP Required for further clarification | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-458 | SC |  | 2023-06-23 | St Clements |  | Sean Cooper | SR Design | New IF-019 Related MPAN Validation Rule | New Validation Rule required for IF-019 to ensure that only Import MPANs can be related. Add to Create and Add Related - this is per REC Shedulle 28 |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | New Rules added to IF-019, [RelatedAdd] and [Related Create] events to ensure only Import MPANs can be in a related Group. New Error code added to support these new rules REG1067 - Only Import MPANs can become Related | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-459 | SB |  | 2023-06-23 | Utiliteam | 5724 | Richard Palmer | Software Provider | Spec of IF-024 in DEL138 Interface Catalogue | A further suggestion re the Interface Spec for the IF-024: The Event Code list in DI D-999 in Group S0 contains [SN-RemoteEnabled] & [SN-RemoteDisabled]. I would suggest that these are invalid for Segments Advanced and Unmetered. Also [SN-Vacant] would appear to be irrelevant for Segment Unmetered, and I doubt that [SN-NoComms] would be valid either. These existed in v5.0, and are still in v5.1.1. Perhaps the routing rules need some improvement? |  | Closed | [5 empty] | No change Required. Useage of these evernt codes is obvious and is described in the Requirments documents as necessary
MHHS-DIN-460 | SB |  | 2023-06-26 | Utiliteam | 5939 | Richard Palmer | Software Provider | PIF-019 structure & Principle -> Principal | Also, in the relationships between MPANs, the ‘main’ one is the ‘Principal’ one – not the ‘Principle’. This will be embarrassing if left uncorrected. It is still in v5.1.2 in IF-019, and it is in many other places. If there is a chance of correction, please take it. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Spelling mistake corrected in Data Catalogue, IF-019, IF-020. Note YAML name also corrected for DI-073. | Data interface correction | Supporting Docs | Interface Changes | MHHSP-DES138-Interface Catalogue Swagger 1.3
MHHS-DIN-461 | SW |  | 2023-06-26 | Greenbird | 1768 | Fredrik Omland | Software Provider | Misalignment between DES-138 and Swagger for DIP Connection Provider ID | In DES-138, In the S1 block, DI-996 (Connection Provider DIP ID) is defined as Optional. But in Swagger, this is defined as mandatory. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Updated Swagger 1.3 so DI-996 in S1 block (Connection Provider DIP ID) is Optional to align with DES-138 | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-462 | SW |  | 2023-06-27 | Design Team |  | Steve Weston | SI Design | Schema Optionality incorrectly defined for some Interfaces | In DES-138, there are are a number of Interfaces where the Schema Optionality is defined as Optional, rather than Mandatory. The list of Interfaces are as follows - IF-050 / B022, IF-023 / B053 and IF-013 / B049 |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Updated Schema optionality in DES138 to show that all data items must be present where the block is present in line with updated E2E Solution Architecture for IF-050 / B022, IF-023 / B053 and IF-013 / B049. | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalouge
MHHS-DIN-463 | SW |  | 2023-06-27 | SIMS |  | Kyle Abraham | Software Provider | No ability de-register from receiving Status messages in Swagger | In Swagger, there is a POST method for /statusmessage/config, but there is no DELETE method, so you are unable to delete / de-register for any status messages. Need to update Swagger to ensure this is possible. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Updates made to Swagger 1.3, so there is a DELETE method for /statusmessage/config, so you are now able to delete / de-register for any status messages. Updated so that all of the Interfaces accept the same 4 security headers required for message signature and validation. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-464 | SW |  | 2023-06-27 | SIMS |  | Kyle Abraham | Software Provider | Clarity required on values expected for /dip-channel/{id} for submitEvents on Swagger | The {id} in /dip-channel/{id} for submitEvents on Swagger should accepts values that are the same as the enumeration in DI-000 to ensure consistency. At the moment, this is not clear in Swagger or E2E001 design, so this needs to be updated to make this clearer. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Updates made to Swagger 1.3, so there the correct enumerations / values are available to align with values in DI-000 to ensure consistency and avoid any ambiguity between interfaces and reports. Updated to remove PublicationConfig and RestConfig in favour of a single config WebhookConfig. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-465 | SC |  | 2023-06-28 | RECCO |  | Sean Cooper | SRO Design | Update to BP010 - Related MPANs | The process MPAN for Related MPANs does not clear call out the Rejection pathway. Update Business Process to show rejection process. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | BP010B Related MPANs Process updated to show specific Rejection Route. | Process Model correction | Metering Changes | Business Process Documentation | BP010- Changes to MPAN Data
MHHS-DIN-466 | SC | DI-188 | 2023-07-29 | St Clements |  | Sean Cooper | SRO Design | Change of MPAN Status during Service Provider Appointment Process. | How should a change of MPAN Status be dealt with whilst there is an ongoing SP Appointment that has not yet reached the stage of IF-034 processing !? If an MPAN is disconnected between PUB-031 acceptance and receipt of PUB-034, the SP PUB-034 Response would be rejected by MPRS due to validation rule REG1001. The appointment would not be progressed but would be stuck in the MPRS queue at status Requested. Could resolve by amending REG1001 validation on IF-034, to not apply to event codes MSAppSPResponse or DSAppSPResponse. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Resolved following discussion with SCS, Agreed that SCS will take no action until the IF-034 has been processes. A change to REG1001 validation on IF-034, to not apply to event codes MSAppSPResponse or DSAppSPResponse, is required to allow the IF-034 to processes normally (when where MPAN is disconnected)... Following processing of the IF-034 RESG will then immediatly issue an IF-035 with reason code of "1- Lapsed as MPAN Status is Disconnected" ... ... Agreed that this was best resolution both for REGS processing rules and participants as no change to currently expected message patterns/ordering. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-467 | SC |  | 2023-07-29 | ESG |  | Sean Cooper | SRO Design | Review of IF-035/IF036 Data Item Obfuscation | Review of IF-035/IF-036 Data Item Obfuscation |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Various updates to obfuscation on IF-036 to align with IF-035. DI-019/DI-800/DI-809/DI-207 obfuscated for Data Service DI-020/Di-800/DI-126/DI-842/DI-209/Di-844/DI-811/DI-208 /DI-018 obfuscated for Metering Service | Data interface correction | Supporting Docs | Interface Catalogue | MHHS-DES138-Interfaces
MHHS-DIN-468 | SC |  | 2023-07-29 | Helix |  | Sean Cooper | SRO Design | Routing of IF-020 | Helix have confirmed that they DO NOT need to receive Related/Linked MPAN information therefore an update is required to REMOVE MDS from the receipient list for this IF-020 |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF-020 Routing table has been updated to REMOVE MDS as being a recipient of any IF-020 messages. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-469 | ME |  | 2023-06-30 | SRO Design Team | 2109 | Rob Golding | SRO Design | Removal of Z0 & Z1 data items in ERI011B - ECS Reports External | Z0 & Z1 data items to be removed from from the each of the MHHS reports within ERI011B - ECS Reports External as they are no longer in the common block |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Removed Z0 & Z1 data items from all MHHS reports in ECS external reporting artefact | Data interface correction | Minor | ECS Reports | ERI011B - ECS Reports External
MHHS-DIN-470 | SW |  | 2023-06-29 | Callisto | 1805 | Seth Chapman | Software Provider | Clarity on nullable fields | Section 4.2.2 in the E2E design provides information on Optional / nullable fields, but worked examples would provide further clarity for each of the data types / link to JSON specification. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Updated section 4.2.2 with worked examples for each data type to provide additional clarity. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-471 | MH |  | 2023-06-30 | Helix |  | Derek Weaving | Central Body | Update to REP-003 in ERI011B - ECS Reports External | R019 parent should be R017 in the ECS Reports External and Swagger |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Updated R019 parent to R017 for REP-003 in ERI011B - ECS Reports External. Swagger v1.3 updated to align with changes within ECS reports artefact. | Data interface correction | Minor | Interface Changes | ERI021 -ECS Reports External Swagger 1.3
MHHS-DIN-472 | SW |  | 2023-06-29 | SRO Design Team | 2006 | Rob Golding | SRO Design | Onboarding migration from Test to Production. | “The programme is to implement a strong PKI policy but as per the diagram states that that on promotion, parties will be able to copy their Test setup and to use that for connecting to the Prod environment. - steps 1-8 - There are no steps in this sequence that test the connectivity to the Live DIP environment. To this point the only connectivity testing has been to the Test environments. This is a significant failure point / risk. At this point Webhooks and certificates will change (mTLS and JSON signing) from those used in Test as well as potentially some of the PKI resources assigned to roles ( those used in test may not be applicable to Prod) we would expect that this would require a new Connectivity proving period with the Prod environment similar to that being developed for CIT. Without such proving, how can the programme assume all parties will connect to the Prod environment successfully and ensure minimal impact to migration events”. |  | Closed | [5 empty] | This an Elexon/DIP Manager deliverable not a programme deliverable
MHHS-DIN-473 | SB |  | 2023-06-30 | MHHS | 2111 | Jason Brogden | Network Operator | Definition of Network Operations | Issue: There is a lack of clarity in the scope of Network Operations activities in testing. Action to Resolve: Add a definition to the Programme Glossary that makes clear the scope of Network Operations (as referenced in Testing material) is equivalent to the scope of LDSO activities in the MHHS Design Baseline: Network Operations systems and services are those that are required to deliver the elements of the MHHS Design Baseline that are allocated to the LDSO role. Communicate this to the DNO and iDNO community and associated service and software providers. For the DIN Log, we can then focus on updates to the BRS to give the necessary clarity on the scope of MHHS Design. Issue: There is a lack of clarity in the scope of LDSO activities in the MHHS Design Baseline as BRS005 implies MHHS-related processing requirements at LDSOs for received DIP messages, whereas the BPs and BPDs define the scope of MHHS as ending at the receipt of DIP messages. BRS005 is described as “For Guidance Only” at the top and this is to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing). Action to Resolve: For the avoidance of doubt and to provide clarity to BRS005, it is proposed to change the “For Guidance Only” note at the top of BRS005 to the following description as per the above: BRS005 is provided For Guidance Only to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing). |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | LDSO Requirements document updated with the following text, "BRS005 is provided For Guidance Only to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing)." | Requirement correction | Minor | Business Requirements Documentation | BRS-005 LDSO Overview.xls
MHHS-DIN-474 | ME |  | 2023-07-03 | MHHS |  | Kevin Spencer | SRO Design | Creation of new ECS data items and blocks across multiple reports and/or data catalogue | Report definitions incorrect and require updates and new data items following internal review |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Addition of data items DI-503, DI-505-DI-515 to data catalogue and across ECS reports artefact. MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal Missing data items added to data catalogue Di-403/DI-404/DI-514/DI-515 | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-475 | ME |  | 2023-07-03 | MHHS |  | Kevin Spencer | SRO Design | Update to block names, data items and descriptions | Report definitions incorrect and require updates and new data items following internal review |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Update to block names, DTN references, data items, descriptions and reordering of data item blocks to exisiting reports in MHHSP - ERI011B - ECS Reports - External | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-476 | SW |  | 2023-07-03 | Greenbird | 2035 | Fredrik Omland | Software Provider | Inconsistency between enum fields and nullable definition | Looking at DIP Interfaces Swagger 1.1 (also 1.2 + 1.3), the enum typed fields that are nullable may not comply with OpenAPI specification (for 3.0.x). The topic around enum fields with nullable: true has been clarified/answered by OAS project (amended in spec version 3.0.3 in 2021): (Reference: https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md ) |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | To align with Open API spec clarification at https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md, we have updated all Data Types that are nullable and have an enum to align as follows: Following discussion, have decided to align with OpenAPI 3.1 DI-076-Estimation-Reason-Code: description : Used inconjunction with Settlement Period Quality Indicator to explain why data has been estimated type : string nullable: true maxLength : 2 example : '1' enum: - '1' # OptOut - '2' # Missing .. - '8' # Disconnected - '9' # Consumption Amendment - '10' # NonSmart - null The Data Types affected / updated as follows: --- DI-039-Load-Shape-GSP-Group-ID --- DI-076-Estimation-Reason-Code --- DI-096-Site-Visit-Check-Code --- DI-126-Traditional-Fall-Back-Read-Frequency --- DI-137-IHD-Install-Status --- DI-150-Annual-Consumption-Quality-Indicator --- DI-166-Supplier-Consumption-Amendment-Reason-Code | Data interface correction | Minor | Interface Changes | Swagger 1.3
MHHS-DIN-477 | SW |  | 2023-07-03 | MHHS |  | Steve Weston | SRO Design | Swagger alignment to OpenAPI 3.1 specificiation | Align with Open API specification 3.1 to remove nullable :true and replace with type declaration ie, type:[string:”null”] | CR049 | Closed | Design ambiguous | DIP Users |  |  |  | Align with Open API specification 3.1 to remove nullable :true and replace with type declaration ie, type:[string:”null”] | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-478 | SW |  | 2023-07-03 | MHHS |  | Rob Golding | Central Body | IF-021 max number of days of consumption data | In the Release 2 version of DES138 a limit was introduced that asked Participants not to submit more than 150 Settlement Days’ worth of data in a single message. The value of 150 was proposed as this meant a single message would realistically be ~600KB in size. We’ve had some queries regarding this value, the proposal is to increase sizing from 150 to 194 day message and the size increases from 600KB to ~780KB for IF-021 message. ECS will need to validate the message contents. However, rather than letting a ‘large’ IF-021 message traversing though the DIP, the proposal is to limit the IF-021 on ingress to the DIP and a single request will have a limit of 1MB – this will be done at the API level. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Agreed to limit the number of MQ IDs per IF-021 submission to ONE only and limit settlement days to 200. Swagger has been updated to limit the number of MQIDs to 1. Swagger updated to limit the maximum number of Settlement Days to 200. DES138 also updated to aligned with the above changes for IF-021. | Data interface correction | Minor | DES138 and Swagger | DES-138 and Swagger 1.4
MHHS-DIN-479 | SC |  | 2023-07-03 | St Clements |  | Maddison | SCS | Change to Consent Notification on IF-036 | SCS have suggested that B068 should only be required for DSApp Events. |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | Block 068 on IF-036 amended to that it is only Mandatory for DSApp Events. | Data interface correction | Supporting Docs | Interface Change | DES138-InterfaceCatalogue
MHHS-DIN-480 | SC | DI-195 | 2023-07-03 | St Clements |  | Maddison | SCS | Reverse DIN-105 | SCS have confirmed that it is possible currently and should continue to be possible to manage MPAN Linkages whilst MPAN(s) are at Created Status. Therefore we have reversed the change implemented at part of DIN105 and now allow processing of IF-019 if mpan status = "Created" |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | SCS have confirmed that it is possible currently and should continue to be possible to manage MPAN Linkages whilst MPAN(s) are at Created Status. Therefore we have reversed the change implemented as part of DIN105 and now allow processing of IF-019 if mpan status = "Created" | Data interface correction | Supporting Docs | Interface Change | DES138-InterfaceCatalogue
MHHS-DIN-481 | SW |  | 2023-07-06 | Elexon | 2106 | Nigel Rees | Central Body | REP-003 inconsistency between DES-138 | We have a contradiction between the DT-023 and the swagger spec. As there is an example we will implement based on the example but it looks like the person who wrote the ECS report catalogue used the correct convention. e.g. on REP-003 we have DT-023 as NUM (16,6). If we follow the convention used in the DIP interface spec, this would translate to 1234567890123456.123456, however the swagger suggests 123456789.123456 Screenshot from REP003 in external ECS reporting catalogue https://app.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.3#/components/schemas/DT-023-Positive-Decimal-9-6 DT-023-Positive-Decimal-9-6: description: Number (9,6) format type: string pattern : ^[0-9]\d{8}(\.\d{6})?$ example: 123456789.123456 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Two new data type references have been created DT-024 and DT-024N. For NUM(16,6) data type within ECS reports/ECS data catalogue replace DT-023/DT-023N with DT-024/DT-024N. DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. 31/08: A reconciliation exercise is being carried out internally of the ECS data catalogue to assess data types. Further work may be required to swagger following the reconciliation. Reconciliation task has been completed which has resulted in updates to the MHHS Data Types within the ECS Reports data catalogue. MHHS data type references in Swagger have also been updated to align with these changes. An example of how MHHS data types should be interpreted: String 17 should be interpreted as NUM(±9.6) which can be physically represented in this way for a negative number -123456789.123456 or for a positive number it will be 1234567890.123456. The objection has been removed. | Reporting correction | Minor | ECS Reports | "MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2" Swagger
MHHS-DIN-482 | KH |  | 2023-07-10 | C&C | 2394 | Hazel Cotman | Software Provider | Interim Release 2 query - IF-018 | LDSO’s are not detailed as ‘To Parties’ within IF-018 flow, however, the LDSO is a secondary routing party for updates to the Domestic Premise, Energy Direction Indicator, and the Metered Indicator |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | LDSO's added to the To party list of IF-018 | Data interface correction | Minor | Interface Catalogue | DES138
MHHS-DIN-483 | KH |  | 2023-07-10 | BGAS | 2410 | Neil Stranger | Supplier | MHHS Design Query - date/ time in DES138 | In DES138 there are a number of data items that are defined as having a date/time structure, but the name and description only refer to the date element whereas others refer to date and time. Therefore for those that make no reference to time we need to be 100% clear if the time should be when the event occur or should it be defaulted to say midnight. This is to ensure consistent population/use across the market. |  | Closed | [5 empty] | Related to a Design Principle and agreed as per E2E Architecture
MHHS-DIN-484 | SW |  | 2023-07-10 | Design Team | 2352 | Martin Freeman | Central Body | Clarity on RecipientId and SenderID in StandardResponseBodyType | RecipientID in the Standard Response Body is a mandatory field. When submitEvents (or in IR2 dip-channel) is called, the DIP synchronously returns a Standard Response Body. At this point the DIP does not even know what message recipients the message will be routed too, since the response is returned synchronously whereas routing is performed asynchronously. So the DIP has no way to know what to set recipientID to. It is also important to note that a message can be received by multiple recipients, yet this recipientID is a scalar that only supports being set to a single value. So it isn't clear how that could work. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | The Sender of the messages becomes the Recipient of the Response this already outlined in the examples in the E2E SA doc. Update section 4.6.1 in the E2E001 Design document to provide better clarity on how SenderID and RecipientID are populated in the StandardResponseBodyType. Updated Swagger 1.5 to align with the above. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-485 | SW |  | 2023-07-10 | MHHS | 2380 | Steve Weston | Central Body | Unable to identify Recipient on DELETE and some POST methods | For the DELETE methods in Swagger for StatusMessage and PublicationConfig, need to update the method so you can identify the correct recipientID to be used for the method call. Some frameworks will ignore a body on a DELETE method as being incompatible with the semantics of the DELETE method, and the correct RESTful implementation would be something more along the lines of "DELETE dip-channel/{id}/{role}/pubconfig". Which of course raises the question of whether the POST message should be refactored for consistency. The issue is more widespread than just the DELETE methods, it also affects some of the POST methods where a recieipent ID is required |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Design changes required to Swagger 1.4 to support updates to API endpoints for DELETE API verbs to ensure we are able to remove the correct StatusMessage or PublicationConfig for the appropriate recipient combination. The issue also affects some of the POST methods where a recipient ID is required, e.g webhook config. A standard pattern is proposed where a recipeint id is specified in the path. Updates to section 4.5.1 and 4.7 also made to E2E001 design document to ensure the document provides any clarity required. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-486 | SB |  | 2023-07-11 | MHHS | 2107 | Rob Golding | Central Body | DES138 and message addressing information | Please can you raise a DIN to cover the following request from Participant to clarify the From and To Parties at the top of each sheet to align with the role codes the programme is using and defined in the E2E Solution Architecture document. And if these ‘pure’ roles code could be included in the introduction sheet that would certainly help. More detail can be seen in the Ticket |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Update the role codes in DES-138 for the From / To Parties for each of the Interfaces to align with other documents including E2E001. No change to information in the Introductory section in DES-138 required. | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-487 | SW |  | 2023-07-11 | MHHS | 2379 | Martin Freeman | Central Body | Clarity on schema vs data validation failures, with updated examples. | In section 4.4.4.2, there are some examples that incorrectly return a 207 when they have failed schema validation. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | In section 4.4.4.2, there are some examples that incorrectly return a 207 when they have failed schema validation. E2E001 section 4.4.4.2 has been updated to illustrate 2 examples. One that returns a 201 Created (2 messages as part of the HTTP Request, both pass validation) and another example that returns a 207 (2 messages part of the HTTP Request, but 1 does not pass validation). | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-488 | ME |  | 2023-07-11 | MHHS | 1506 | Steve Weston | SRO Design | Correct Reporting Cat vs Swagger | Reinstated DI-484 "Settlement Period Duration" and added into R Groups as required |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Reinstated DI-484 "Settlement Period Duration" and added into R Groups as required in Swagger 1.4 | Data interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-489 | MF |  | 2023-07-11 | Design Team |  | Mike Fensome | SI Design | Schema Optionality incorrectly defined for Common Block | In DES-138, the Common Block shows some fields where the Schema Optionality is defined as Optional, rather than Mandatory. The list of Blocks are as follows - Common Block: S1, D0, A0 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Update Schema optionality in DES138 to show that all data items must be present where the block is present in line with updated E2E Solution Architecture. Common Blocks impacted: S1, D0, A0 | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-490 | SW |  | 2023-07-11 | Design Team | 2395 | Martin Freeman | Central Body | Level 1 validation clarity for POST /statusmessage be the same as for POST /dip-channel/{id} | The E2E001 v3.2 (section 4.4.3) describes how for the Send Messages API, when the DIP performs level 1 validation, if any message in the request fails validation then the entire request is rejected. Section 4.6 Send Status Messages API does not describe the DIP validation for status messages at all. Should validation for POST /statusmessage be the same as for POST /dip-channel/{id}, in that a level 1 validation failure for any message should fail the entire request, or should messages that pass validation be accepted and messages that fail be rejected independently? |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | This should be consistent across all interfaces in that a schema validation failure for any message should fail the entire request. In the E2E001 design, sections 4.4.3 and 4.6 are to be updated to reflect this / provide the appropriate level of clarity. This issue affects both the http delete operations. Easy to fix, same fix as the post need to include the webconfigas a parameter | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.5
MHHS-DIN-491 | SB |  | 2023-07-11 | Utilita | 2408 | Adam Barnes | Supplier | IF-035 - Update routing to show XDSS | DES138 v5.2.1 - IF-035 tab for the bottom 3 entries it still refers to the previous version definition of routing parties – we expect this to be a slight oversight as SDSS is no longer defined as a recognised party? |  | Implemented | Error/Correction | N/A |  | Interim Release 8 | 2024-03-20 | Update routing for IF-035 to show XDSS for consistency of the documentation, but it will only ever apply to MPANs in the Smart Segment so will in reality only ever be routed to an SDS. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-492 | KH |  | 2023-07-11 | Stark | 2125 | Matthew Peters | Supplier | IF-034 Proposed Appointment Response Code Formatting | The data type within DI-143 block for IF-034 and IF-035 needs to change from String 200 to Array because there is a possibility of getting more than 1 rejection code. |  | Closed | [5 empty] | Closed - only 1 rejection code is required
MHHS-DIN-493 | SC |  | 2023-07-12 | St Clements |  | Sean Cooper | SRO Design | Changes to IF-019 Secondary MPAN validation | SCS had originally suggested a validation rule to prevent Secondary (Related) MPANs being linked to an Export MPAN. However, RECCO and EON have highlighted there are a very small number of scenarios where this might be the case. Following further discussions with SCS they are now happy to remove this rule (REG1068) |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | IF-019 - REG1068 check for Secondary MPAN Linkage to export REMOVED | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-494 | SW |  | 2023-07-12 | Callisto | 2462 | Neil Edney | Software Provider | Incorrect Min and Max Values for DI-091-Number-Of-Displayed-Register-Digits | DI-091-Number-Of-Displayed-Register-Digits currently has a minimum of 1 and maximum of 1, when this should be 5 and 6 respectively to align with DES-138 as this is an Integer. |  | Closed | [5 empty] | This DIN is now superseded by DIN-615 following on from DIN-574. Text against Number of Register Digits field amended to say "per the manufacturer specification". Swagger validation of this field updated to match SCS logical test ie value can be 0-9. This DIN was to ensure there was consistency in Swagger 1.4 to align with DES-138 so that min and max was 5 and 6 respectievly. This objection is related to the values in DES-138, to update from 5 and 6 to 0 and 9, and then align Swagger to the values in DES-138. | No Change
MHHS-DIN-495 | SC |  | 2023-07-12 | Design Team |  | Sean Cooper | SRO Design | Correction to BP003 | IF-035 for Trad/Advanced meters was previously shown as being direct interaction between REGS and MS ... Changed to show message as flowing via the DIP |  | Implemented |  |  |  | Interim Release 3 | 2023-07-12 | IF-035 for Trad/Advanced meters was previously shown as a flow being direct interaction between REGS and MS. Changed to show message as flowing via the DIP (at step 90). Also change applied to Forward migration process for consistency. | Process Model correction | MPAN Ownership | BP003 | MHHSP-BP003-Change of Service - Data Service MHHS-DEL964 BPM-003 - Change of Servie - Data Service - Forward Migration
MHHS-DIN-496 | MH | DIN-910 | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 | MHHSP-METH001_SDS_Validation_Estimation 5.1 section 2.7 States "SDS shall inform the Supplier using the Meter Reading Reason Code on the IF-041/PUB-41" . There is no Meter Reading Reason Code on the IF-041 in DES138 v5.1.2. Therefore, either Meter Reading Reason Code should be included in DES138, or this requirement should be removed. |  | Closed | Design ambiguous | N/A |  |  |  | Updated as part of DIN-910 | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-497 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 | MHHSP-METH001_SDS_Validation_Estimation 5.1 Section 5.4 Where DA records are < 90 days from UTC date this is inconsistent with Method 4, which states "DA is available [either in the past or future] and less than [3] months different from the UTC Date requiring a daily Meter advance". |  | Implemented | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Be consistent - use either 90 days or three months within the document Tend to agree – this describes the actual method of estimation so should be included before go-live | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-498 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 Method 13 | MHHSP-METH001_SDS_Validation_Estimation 5.1 Method 13 This describes the outcomes for Smart and Advanced meters. Does this imply that traditional meters should have zero consumption submitted to settlements, or should Method 13 text be adjusted to include trad meters? ALSO If actual data is recovered, or an Advance Meter Reading is received, and this indicates zero consumption, should this be submitted to settlements? The first part of the sentence implies it should be submitted, and the brackets imply it shouldn't. |  | Implemented | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Alter wording of Method 13 to reflect we shouldn't be sending estimates for Deenergised trad meters as well as Smart and Advanced, AND 'there is no need to submit zero consumption for de-energised MPAN's' needs changing to refer to 'zero ESTIMATED consumption' This should be a clarification of previously stated position but agree update should be made to clarify that Zero consumptions are required to be submitted, where encountered, for all MPANs that are not de-energised regardless of segment/meter type. | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-499 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Alignment of Estimation Reason Codes | METH001 refers to Estimation Reason Code 'Adjustment'. DES138 refers to 'Consumption Amendment' Assume these are the same thing and need to be aligned between both sets of documentation |  | Implemented | Design misaligned | N/A |  | Interim Release 8 | 2024-03-20 | Align Method Statements to match the Estimation Reason Codes within DES138 | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-500 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | ISD Entity M17 Example Correction | MHHSP_EDI021_ISD_Entities 5.1 Entity id M17 Industry Standing Data: MHHS Entities/Data Items v5.1 ISD Entity Id M17 - Valid Consent Granularity Combinations, includes combination I¦F¦S¦D. According to Decision 2 in "https://www.ofgem.gov.uk/sites/default/files/docs/2019/06/access_to_data_consultation_ofgem_response_0.pdf" a non-domestic customer is unable to opt out. The OFGEM document states "There will be no opt out possible for microbusinesses in relation to data for settlement purposes". Therefore, I ¦ F ¦ S ¦ D is not a valid combination. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | In ISD Entity ID M17 we have removed "I ¦ F ¦ S ¦ D" from the example list | Design Ambiguous | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-501 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Addition of Method 13 to METH002 | MHHSP-METH002_ADS_Validation_Estimation 5.1 Section 3.16 States "The below estimation methods are based on those used in the Smart Data Service (SDS) Method Statement. For that reason, methods 0, 1, 6, 11 and 13 have been omitted as they are only applicable to Smart meters." However, method 13 is "Estimation for a Site where Supply is de-energised" and this is included in METH002 in section 2.29. The statement is wrong as some of the methods have been renumbered in METH001 since this was written. |  | Implemented | Error/Correction | Smart Data Services |  | Interim Release 7 | 2024-01-19 | Update METH002 to add Method 13 back in | Requirement correction | Supporting Docs | Method Statement | ADS Method Statement
MHHS-DIN-502 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | SP Quality Indicator Clarification | MHHSP-METH001_SDS_Validation_Estimation 5.1 It is our assumption that if NO estimation is required, the Settlement Period Quality Indicator should be set to "A". This is however, never explicitly mentioned. The only mention of using value "A" is for method 1. |  | Implemented | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Update artefacts to clarify when to use A as the Settlement Period Quality Indicator value | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-503 | SW |  | 2023-07-13 | SIMS | 2439 | Martin Freeman | Central Body | S1.senderUniqueReference interface component is too small to identify the message interface | DES138 and the E2E001 the S1.senderUniqueReference property has a 3 digit component that contains the interfaceID of the message. However since the reporting interfaces reuse the same interface numbers as the standard interfaces, and some reporting interfaces have 4 character interface identifiers, this means this component is not sufficiently large to unambiguously identify which interface a given senderUniqueReference was generated for. This also applies for TransactionID. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Update any Data Items that utilise InterfaceID to align with the enumeration of values defined for DI-000 so that this is unique across all interface / report types. This is for data types SenderUniqueReference (DI-995) and TransactionID (DI-990). This change will require updates in DES-138, E2E001 and Swagger 1.4. In DES-138, DT-014 has been updated to String65 from String60 to support Interface being updated from 3 to 8 to align with DI-000 (so for IF-003, rather than 003 being included in the transactionID / senderUniqueReference, this will be IF003 with no hyphen). In Swagger, DT-014 has been updated to max length 65, with examples updated. E2E001 updated examples for senderUniqueReference and TransactionID to align with the above. | Design Ambiguous | Supporting Docs | DES-138, E2E001 and Swagger 1.4 | DES-138-interface catalogue, E2E001 E2E Architecture document and Swagger 1.4
MHHS-DIN-504 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Clarification of link between IF22/IF23 | DES138 IF-022/023 IF an IF-022 or IF-023 is re-issued, can you confirm that they will be reissued as a pair so that the totals align? The issue is if an updated IF-022 is issued with new values, should the SDS/ADS await an updated IF-023, or not? How can the SDS/ADS pair the IF-022 and IF-023 without doing their own summations? |  | Open - awaiting assessment | Clarification - No change required | N/A |  | Post Go-live Release | 0 | Update BRS007 to show that a re-run of IF-022 will result in a rerun of IF-023 |  |  | Business Requirements Documentation | BRS007
MHHS-DIN-505 | BK |  | 2023-07-13 | St Clements |  | Sean Cooper | SRO Design | DUoS Tariff ID to hold values from 1-3 in length | The DUoS Tariff ID needs to be updated in Swagger and the Interface Catalogue so that it can hold values from 1 to 3 in length in order to align with ISD. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Update DUoS Tariff ID to hold values from 1 to 3 in length in Swagger and Interface Catalogue | Data interface correction | Supporting Docs | Interface Catalogue and Swagger 1.4 | DES138-InterfaceCatalogue Swagger 1.4
MHHS-DIN-506 | BK |  | 2023-07-13 | Design Team |  | Sean Cooper | SRO Design | Renaming of IF-014 | Rename IF-014 to clarify the purpose |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Changed to "UTC Settlement Period Consumption Data (Warnings & Rejections)". Interface description and notes updated to reflect that IF-014 could also contain warnings for Consumption on De-enegised sites. | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-507 | SC | DI-194 | 2023-07-14 | Design Team |  | Sean Cooper | SRO Design | Clarification of IF-036 Routing Requirements | Update IF-036 to clarify / provide additional info on the routing destinations of IF-036 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Added following Text: Primary Routing Participants for IF-036 MSAppActive • Supplier (i.e. the supplier who initiated the appointment, either current in the case of Change Of / Update to SP’s, or incoming in the case of a COS) • Metering Service (i.e. the Metering Service being appointed) • [Partner] Data Service (i.e. the Data Service in effect on the App Start Date of the MS Appointment – this could be either an ‘existing’ Data Service in the case of an MS Only appointment OR the ‘incoming’ Data Service with a coincident App Start Date to that of the [incoming] Metering Service • Linked Supplier(s) – (ie the Supplier(s) with responsibility for the Linked [Import/export] MPANs on the App Start Date of the Metering Service Appointment) DSAppActive • Supplier (i.e. the supplier who initiated the appointment, either current in the case of Change Of / Update to SP’s, or incoming in the case of a COS) • Data Service (i.e. the Data Service being appointed) • [Partner] Metering Service (i.e. the Metering Service in effect on the App Start Date of the DS Appointment – this could be either an ‘existing’ Metering Service in the case of an DS Only appointment OR the ‘incoming’ Metering Service with a coincident App Start Date to that of the [incoming] Data Service • Linked Supplier(s) – for Advanced Segment Meters only - (i.e. the Supplier(s) with responsibility for the Linked [Import/export] MPANs on the App Start Date of the Metering Service Appointment) | Data interface correction | Supporting Docs | Interface Catalogue
MHHS-DIN-508 | SC |  | 2023-07-17 | Design Team |  | Sean Cooper | SRO Design | Addition of MP Status and RMP Status Effective From Dates to IF-050 | Addition of MP Status and RMP Status Effective From Dates to IF-050 ( Linked to DIN 318 ) |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | New Data Items Created and added to IF-050 in block B079 and the data catalogue tab: DI-167 RMP Status Effective From Date DI-168 MP Status Effective from Date (DIN 318 Closed as duplicate) | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-509 | SW |  | 2023-07-18 | MHHS |  | Steve Weston | Central Body | Missing Archival NFR Information | There is no detailed non-functional requirements in relation to data archiving, retrieval, archival tiers, recovery from archival so we need to update the NFR's to ensure these are included. |  | Open - awaiting assessment | Design ambiguous | DIP Users |  | Post Go-live Release | 0 | Further details of the solution are under discussion/review. | Clarification |  | Business Requirements Documentation | Non-functional Requirements
MHHS-DIN-510 | SW |  | 2023-07-18 | MHHS | 2675 | Steve Weston | Central Body | Properties on block B047 | The Swagger definition has the properties ‘sp’,’v’,’q’,’e’ and ‘arc’ which matches the items in red. However the data catalogue has different YAML names. YAML Swagger names have to be updated in DES-138 to match the above characters. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | This was done to reduce IF-021 content size, but the DES-138 5.4.1 YAML needs to be updated to align with Swagger 1.4 - the YAML names should be as follows DI-082 ‘sp’ - B052 (IF-022), B047 (IF-021) DI-147 ’v’ - B047(IF-021, 4, 16) DI-083 ’q’ - B047 (IF-021, 14, 16) DI-076 ’e’ - B047 (IF-021, 14, 16) DI-166 ‘arc’ - B073 (IF-027 / 28) Swagger 1.4 has been updated to align for the approrpiate blocks above to ensure consistency across the data catalogue. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-511 | BK | CR027 | 2023-07-18 | Eastern Power Networks |  | Peter Waymont | Network Operator | DUoS E-Billing DIP Message for MHHS | A new flow needs to be introduced for e-billing of site-specific DUoS in the post Market-Wide Half-Hourly Settlement (MHHS) environment because the existing flow uses the DTN and all other DUoS data will be DIP based. The change is required in order to continue to operate the site specific DUoS billing process in the MHHS environment. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the HH data sent by Data Services to the LDSO for use in DUoS billing, using IF-021/IF-013/IF-014. At present DUoS billing systems can send the D2021 data flow as a form of e-billing for site-specific DUoS, using the DTN. As DUoS billing systems will need to interact with the DIP for migrated site-specific billed customers, it is preferable that the outputs are also DIP messages, to enable the parties to move forward completely in the new environment. A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors) and receivers (suppliers) of the flows has identified the desired flow content and now wish to bring this to the Programme to ensure that it can be delivered in readiness for migration. | CR027 | Closed | [5 empty] | Covered as part of CR019
MHHS-DIN-512 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Amendments to Swagger and ECS data catalogue REP-002 | Max length for DI-345 DUoS Tariff Id to be updated in line with ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated to ensure DI-345 DUoS Tariff ID aligns with ECS Data Catalogue - max length of string = 3. | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-513 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Custom block correction REP-002 | Block name to be updated to tariffCharacteristics in Swagger. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated for REP-002 custom block to fix typo from tarrifCharacteristics to tariffCharacteristics to align with ECS Interface Catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-514 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Amendments to Swagger and ECS data catalogue REP-002a | Max length for DI-345 DUoS Tariff Id to be updated in line with ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated to ensure DI-345 DUoS Tariff ID aligns with ECS Data Catalogue - max length of string = 3. | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-515 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Custom block correction REP-002a | Block name to be updated to tariffCharacteristics in Swagger. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated for REP-002 custom block to fix typo from tarrifCharacteristics to tariffCharacteristics to align with ECS Interface Catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-516 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Update DI-300 with Minimum value REP-003 | DI-300 to be updated in swagger with a minimum value of 100 as per ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-300 updated in Swagger 1.4 with a minimum value of 100 as per ECS data catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-517 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update data item type in ECS data catalogue REP-003 | DI-325 data type to be updated in data catalogue to (NUM 4,2) in line with swagger |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to NUM(4,2) for DI-325. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Cataloue correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-518 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Inclusion of Max/Min value for DI-496-REP-003 | Update ECS data catalogue with Min value of 1 and Max value of 48 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MIn and Max Column of MHHS ECS data catalogue updated with 1 and 48 respectively. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-519 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Max value change in swagger for DI-496 | Update Max value to 48 for DI-496 in swagger |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-496 in Swagger 1.4 updated to have a Max value of 48 | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-520 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-359 data type REP003 | Update DI-359 data stype to String 16 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-359. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-521 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-360 data type REP003 | Update DI-360 data stype to String 16 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-360. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-522 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-362 data type REP003 | Update DI-362 data stype to String 16 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-362. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-523 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-324 data type REP003 | Update DI-324 data stype to String 16 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-324. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-524 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | DI-363 missing from ECS data catalogue | Update ECS data catalogue by adding in missing DI-363 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data catalogue updated with the addition of missing data item DI-363. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-525 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-364 data type in REP003 | Update DI-364 data stype to String 17 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-364. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-526 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-365 data type in REP003 | Update DI-365 data stype to String 17 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-365. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-527 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-366 data type in REP003 | Update DI-366 data stype to String 17 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-366. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-528 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-367 data type in REP003 | Update DI-367 data stype to String 17 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-367. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-529 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-368 data type in REP003 | Update DI-368 data stype to String 17 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-368. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-530 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Wrong data item referenced in swagger | Wrong data item referenced in R022. Daily Period BM Unit Total Allocated Volume must be changed to BM Unit Allocated Demand Disconnection Volume |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Swagger 1.4 has BM Unit Allocated Demand Disconnection Volume (DI-241) in R022 | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-531 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Data type update in swagger for DI-341 | DI-341 data type to be changed to String 18 as per data catalogue |  | Closed | [5 empty] | Closed. This is defined a Integer in the format 9,6 in Swagger. | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-532 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Wrong data item referenced in swagger | Wrong data item referenced in R022. settlementPeriodID must be changed to Settlement Period |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Updated Swagger 1.4 so that R022 references DI-946 (SettlementPeriod) rather than DI-307 (SettlementPeriodID) | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-533 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-339 data type in REP-003 | Update DI-339 data stype to String 17 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-339. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-534 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-369 data type in REP-003 | Update DI-369 data stype to String 17 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-369. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-535 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-370 data type in REP-003 | Update DI-370 data stype to String 17 in ECS data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-370. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-536 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-322 REP003 | Update Min column of ECS data catalogue with 0 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-322 Minimum column of MHHS ECS data catalouge updated with 0 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-537 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-322 REP003 | Update Max column of ECS data catalogue with 99.99 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-322 Maximum column of MHHS ECS data catalouge updated with 99.99 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-538 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-323 REP003 | Update Min column of ECS data catalogue with 0 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-323 Minimum column of MHHS ECS data catalouge updated with 0 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-539 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-323 REP003 | Update Max column of ECS data catalogue with 99.99 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-323 Maximum column of MHHS ECS data catalouge updated with 99.99 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-540 | SW |  | 2023-07-14 | Elexon | 2684 | Nigel Rees | Central Body | IF-13 run number | In DES-138, Run Number in IF-013 Interface is 3 chars, yet in Swagger and ECS Reports, this is 7 characters long. We need to update DES-138 to align with Swagger and ECS reports. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Updated IF-013 to show DI-161 (Run number) as number 7 to be consistent with Data Catalogue/ Swagger and Reports | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-541 | MF |  | 2023-07-19 | ESG | 2623 | Patricia Parker | Software Provider | SSC and Profile Class validation | Validation needs to be reviewed to enable the provision of just SSC or Profile Class updates as part of [SSCandProfileClass] event code updates in IF-025 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Updated conditionality on IF-025 and IF-026 for DI-122 (Profile Class) and DI-123 (SSC) to "Mandatory for Traditional Meters (if changing)" to allow just SSC or Profile class updates to be provided. Validation rules updated accordingly in IF-025. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-542 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-159 in data catalogue REP004 | Update Min column with 25 in data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-159 Minimum column of MHHS ECS data catalouge updated with 25 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-543 | MF |  | 2023-07-19 | Design Team |  | Mike Fensome | SRO Design | IHD, SMSO, SSC and Profile Class conditional validation | Update validation rules to ensure effective from date is provided when IHD, SMSO, SSC or Profile class are updated |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Added conditionality to IF-025 and IF-026 that DI-136 should be provided where DI-137 is not null and DI-135 should be provided wher DI-134 is not null. Added validation rules to IF-025 to ensure conditionality rules are applied for IHD, SMSO, Profile class and SSC with new error code of REG1088 -Effective from date must be provided | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-544 | SW |  | 2023-07-19 | Siemens | 2633 | Tony Mason | Software Provider | Level 4 Validation - Multiple response codes | Unclear from the current E2E design defined in E2E001 for a Level 4 Response code, whether a single transaction with concatenated Response codes be sent back to the DIP for notification to the publisher? Or, would the expectation be that multiple messages be returned with each message quoting the published transaction number? Or, is this at the discretion of the participant? The E2E design should make this clearer, and also provide fleixbility for multiple messages to be returned against the same transaction ID with a response. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | This will require updates to the E2E design document to make Level 2 and 4 response code expectations clearer, as well as updated Swagger to allow for an array of messages, help and service tickets to be sent per error, per transaction ID. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.5
MHHS-DIN-545 | ME |  | 2023-07-20 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-496 data type REP004 | Update swagger to show DI-496 as INT (2) |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Update to data type for DI-496 from INT(3) to INT(2) to align with swagger. Update made to MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-546 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Incorrect data item referenced in swagger- REP004 | Incorrect data item referened in R026. SettlementPeriod ID must be replaced with Settlement Period (DI-496) in swagger |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Updated Swagger 1.4 so that R026 references DI-946 (SettlementPeriod) rather than DI-307 (SettlementPeriodID) | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-547 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Missing data item in swagger | In R026, DI-327 missing from swagger v1.3. Should added and defined as per DT-22 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Updated Swagger 1.4 to include DI-327 (Deemed Supplier Take). Updated R026 to include DI-327 and remove DI-325 so this aligns with ECS Data Catalogue. | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-548 | MH |  | 2023-07-20 | Elexon | 1966 | Rashmi Radhakrishnan | Central Body | Clarification of ISD Transition Requirements | Following MTDSG release of the BRS001 Transition approach and Parallel running requirements v2, ISD would like programme to consider rewording below requirement for more clarity. MHHTR-22 Original: The ELEX-REP-005 Line Loss Factor report will be published at a location on the BSC website/ ELEXON Portal and the URI shall be notified using the Notification of the Publication of a Downloadable Asset IF-047 / PUB-047 to DIP Users prior to M10 and continue post M15. MHHTR-27 Original: The new ISD entities shall be updated be published at a location on the BSC website/ Elexon Portal and the URI shall be notified using the Notification of the Publication of a Downloadable Asset IF-047 / PUB-047 to DIP Users from M10. |  | Closed | [5 empty] | Duplicate - To be tracked under MHHS-DIN-754 | Design Ambiguous | Supporting Docs | ISD Document | ISD Document EDI-021
MHHS-DIN-549 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Incorrect data item referenced in R033 common block | Incorrect data item referenced in R033 - SettlementPeriodID from MDS/VAS should be replaced with SettlementPeriod (DI-496) from ISD, with a MIN value of 1 and Max of 48 in swagger |  | Closed | [5 empty] | Closed- Swagger should keep the min of 1 and max of 50 settlement periods
MHHS-DIN-550 | ME | DIN-659 | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Missing R007 from REP007 | Include R007 within REP007 in swagger |  | Closed | Design misaligned | DIP |  |  |  | Update swagger: Include R007 within REP007 | Swagger | Supporting Docs | Swagger | Swagger
MHHS-DIN-551 | ME |  | 2023-07-20 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-083 | Include Min Value of 1 and Max value of 5 to DI--083 in ECS data catalogue to align with swagger and IF data catalogue |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-083 Minimum and Maximum column updated with 1 and 5 respectively in MHHS ECS data catalouge Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-552 | SW |  | 2023-07-20 | IMServ | 2356 | Liam Lowey | Software Provider | UTF-8 Encoding for JSON | The E2E001 design document does not specify Encoding for JSON. This needs to be updated to reflect UTF-8 as the JSON Encoding required. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Add UTF-8 as the JSON encoding required in the E2E001 design document, creating a new section 4.2.5. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-553 | RS |  | 2023-07-20 | Design Team | 2627 | Rob Short | Central Body | Secondary routing for Export | Secondary routing rules need to be updated to allow notification of work prgressed by the Import suppllier (eg disconnection). review required of all related interfaces |  | Closed | [5 empty] | Following review no document changes required. Re Specific case of Disconnection the Link between Import and Export would need to be removed prior to any Disconnection request. If the link remains in place then the DIsconnection request will be rejected by LDSO/REGS.
MHHS-DIN-554 | MF |  | 2023-07-20 | St Clements |  | Madison Layton | Software Provider | Validation on Customer Direct Contracts | Revisions to CDC functionaility. - Amend validation to ensure that only one Customer Direct Contract can be applied against an MPAN at any moment in time - Move CDC process(s) onto a new BP10 process map so as to make it clearer that CDC is MPAN not appointment based - add supporting process info to new BP |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. Process map emailed to particpants - added to BP010E and validation rules for IF-038 updated accordingly. Business requirements updated to align with process Agreed changes with SCS, & RECCO | Design Ambiguous | Supporting Docs | Supporting Docs | BP10 Registration Updates DES138 - Interface Catalogue BRS001 , BRS002
MHHS-DIN-555 | MF |  | 2023-07-20 | St Clements |  | Madison Layton | Software Provider | Validation of MPID to DIP ID | Carry out validation of MPID to DIP ID during initial IF-031 validation only. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Set REG1090, REG1091 and REG1092 validation in IF-031 to "No" for Queue processing so it only applies to IF-031 validation. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-556 | KH |  | 2023-07-21 | Stark | 2112 | James Murphy | Supplier | Cumulative/Total Consumption Comparison | The “Cumulative/Total Consumption Comparison” that can be carried out instead of a MAR for meters with integral Outstations is not defined anywhere In BSCP502 it is defined at 4.1.5 – I think this should be lifted and shifted into METH002 Interestingly it appears to be described in the SDS Validation & Estimation Statement (METH001) at 3.12 – 3.16 ADS Method Statement (METH002) needs to be updated |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | ADS Method Statement has been updated with "Reconciliation for smart Meter Advance Reconciliation" section 2.21 - 2.25. | Method statement correction | Supporting Docs | Method Statement | METH002 ADS Validation Estimation
MHHS-DIN-557 | RS |  | 2023-07-21 | Elexon | 2745 | Rashmi Radhakrishnan | Central Body | Consistency of the use of ID | Version 5.1 ISD EDI021 Entity specification document, has discrepancies in the usage of ID, Id, id, etc. Inconsistencies to be addressed when updating the design artefact in the future. ISD Entity M3 Usage of ID and Id - Market Participant ID in the table and description are different ISD Entity ID 17 - DUoS Tariff Id GSP Group Id - ISD Entity ID 17 - DUoS Tariff Id table - GSP Group id is with lowercase "i" and Entity Id M4 Load shape categories : GSP Group Id is mentioned as GSP Group ID ISD Entity ID 17 - DUoS Tariff Id Usage of DUoS Id and DUoS Tariff Id ISD Entity Id 4 and 17 - has ID in capital letter Usage if ID and Id to be consistent Entity M4 GSP Group ID- but should be GSP Group Id ISD Entity Id M5 - MHHS Consumption Component Classes CCC ID - for consistency it should be CCC Id |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | All instances of lower /mixed case id have been replaced with "ID" in caps Also see DIN588 | Data Interface correction | Supporting Docs | Support Docs | ISD Document EDI-021
MHHS-DIN-558 | BK | DI-189 | 2023-07-21 | St Clements | 2011 | Madison Layton | Software Provider | Update response codes in IF-035 | IF-035 routing rules references response codes AC and RJ, this should be A and R |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Updated Routing rules in IF-035 to refer to Response code of "R" and "A" for event code [SDS-MDROutcome] rather than "AC" and "RJ" | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-559 | SC |  | 2023-07-24 | St Clements |  | Sean Cooper | SRO Design | Clarification of Appointment Scenario Code (Linked MPANs) | Added clarification to IF-036 to confirm that the Appointment Scenario Code used for Secondary MPANs will mirror that applied to the Primary MPAN (eg COS/CSP/Etc). What will be applied in the case of Auto Alignment ? |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Added clarification to IF-036 to confirm that the (DI-800) Appointment Scenario Code used for Secondary MPANs will mirror that applied to the Primary MPAN (eg COS/CSP/Etc). In cases of Auto-Alignment of MPANs the Appointment Scenatio of (ALG - Auto Alignment of MPAN Service Providers) will be applied. ALG added as allowable value in DI-800 ( Data Catalogue and Swagger ) | Design Clarificarion | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue Swagger 1.4
MHHS-DIN-560 | SC |  | 2023-07-24 | St Clements |  | Sean Cooper | SRO Design | Design Gap on Sharing MTD in the Case of AutoAlignment of Service Providers | The Design allows for the Auto-Alignment of Service Providers in certain circumstances. However a design gap exists that there is currently no trigger for the outgoing MS to send MTDs to the incoming MS in the case of a pure Auto-Alignment (ie no other MPAN transaction eg. COS/CSP) |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Proposal is to create a new requirements (MS-098 / MS-099) on Smart and Advanced Metering Services to trigger sending of D0149/D0150 (trad) or D0265 (Adv), on receipt of a PUB-037 with De-Appointment Reason Code of “RELATED” or “IMPEXP”. D-Flow(s) should be sent, via DTN, to the new/incoming MS referenced in the PUB-037 flow, where available Issue does not arise for Smart sites as MTDs are fully convayed using the PUB-036. Also not a concern for UMSDS as no MTDs exist. | Design Clarificarion | Minor | MPAN Ownership | BRS-002 Metering Service Requirements
MHHS-DIN-561 |  |  | 2023-07-24 | St Clements |  | Sean Cooper | SRO Design | Disconnection of Linked MPANs | No change to desgin required. Design confirmation only. SCS have confirmed that it will be necessary to de-link and MPRN before being able to action a disconnection on it. i.e. Disconnection cannot be performed on a linked MPAN until such time as all links have been removed via (IF-019/IF-020) |  | Closed | [5 empty] | No change Required - Clarification Only
MHHS-DIN-562 |  |  | 2023-07-24 | St Clements |  | Sean Cooper | SRO Design | Clarification of IF-014 R0 Population for Event Code [ConsumptionOnDeEnergisedMPAN] | Confirmation at an R0 will be required when issuing an IF-014 with Event Code [ConsumptionOnDeEnergisedMPAN]. DI-979 should be populated with value 'W', DI-980 would remain blank. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | IF-014 updated to clarify that DI-979 should be populated with W. Data Catalouge and Swagger v1.4 updated to reflect this. | Design Clarificarion | Minor | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-563 |  |  | 2023-07-24 | Elexon | 2705 | Ayo O (Helix) | SRO Design | Clarification on Helix Treatment of IF-021 error condition data. | Clarification is required from Helix on exactly how they will manage and process IF-021 messages and how any resulting error/rejections will be managed. This is so that clear guidance can be drawn up on participants should expect to receive errored data etc. In any event design team are clear "the data returned in the IF-014 must only be that data which is rejected." |  | Closed | [5 empty] | A response was provided to Ayo on 24/07 by design team. Follow up email has been sent for Ayo to confirm whether issue is resolved, thus closing the DIN or whether a call is required with Design team for further resolution. DIN closed as no response received from Ayo. It is our assumption the feedback provided by the design team was sufficient. | Design Clarificarion
MHHS-DIN-564 | SW |  | 2023-07-17 | SIMS | 2704 | Martin Freeman | Central Body | Mandatory Nullable on Swagger | Is Mandatory Nullable (which is how 'optional' properties are described in the DES138) supposed to be marked as Required & nullable in Swagger? Or should these Mandatory Nullable (optional) properties be marked 'not Required' in Swagger? In some interfaces Mandatory Nullable properties are marked 'not required' in Swagger while in others they are 'nullable required'. Need to ensure this is applied consistently across all Interfaces. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Need to update Swagger implementation so mandatory nullable is treated consistently across all Interfaces as this is not always consistent. Need to updated E2E001 to provide additional clarity on how this applies to Swagger. Need to ensure DES-138 is aligned. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | Swagger 1.5
MHHS-DIN-565 | SW |  | 2023-07-25 | MHHS | 2763, 2713 | Steve Weston | SI Design | Version and Schema Interoperability across environments. | Versioning is covered in Section 8.4 and 8.5 of the E2E001 design, that covers the differences between major, minor and patch versions of an API, the URL required as well as schema versions that are contained in the common block of an Interface. There is confusion around how this will work across different environments so we need to provide additional clarity on the Swagger API versions / Schema versions that must be supported by the DIP and MP’s, alongside scenarios that are envisaged. This will provide information on version uplifts, interoperability required and how long different versions of API / Schemas will be supported for. This needs to covers scenarios where within an environment, we have multiple versions of an API within an environment ie, we may be required in some cases to be backwards compatible with previous versions -- for example -- if we received and processed earlier versions, we can respond with the latest live version. E.g. if we receive PUB-005 on version 1.0.0 we could respond with IF-006 on version 1.0.1 and would not be expected to respond with version 1.0.0. |  | Open - awaiting assessment | Design gap | TBC |  | Post Go-live Release | 0 | Need to provide updates to Section 8.4 and 8.5 to ensure we cover worked examples across different environments for both API versions and Schema versions, interoperabilty required, transition between versions, BAU vs Testing phases and expectations on DIP and MP's. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document Swagger
MHHS-DIN-566 | SW |  | 2023-07-25 | MHHS | 2549 | Steve Weston | SI Design | E2E NFR's need to be refined based on actual data | Section 3.1 of MHHS DES001a MHHS Data Integration Platform – Functional Specification – Appendix A Transaction Volumes states that the indicative size of an IF-021 (single days' worth of UTC SP data) is between 1 and 2 KB. The equivalent IF-021s we have successfully submitted to the DIP Simulator are ~4.5 KB as observed in webhook. Can you confirm that this increase in size has been factored into the non-functional requirements? |  | Closed | Clarification - No change required | DIP Users |  |  |  | Agreed to be closed. Volumetrics document has been updated to reflect updated file sizing. This is for guidance only and depends on IF-021 consumptions per transaction. | Design Ambiguous | Supporting Docs | MHHS E2E004 Solution Architecture - Transaction Volumes | MHHS E2E004 - End to End Solution Architecture– Transaction Volumes IF-021
MHHS-DIN-567 | SW |  | 2023-07-25 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - Swagger Incorrect | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4. Swagger 1.4 needs to be updated so that it aligns with DES-138. DI-081 to be updated to periodDuration. DI-086 to be updated to supplierEffectiveFromDate. DI-121 to be updated to supplierEffectiveToDate. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Need to update mismatch between Swagger YAML definition in DES-138 and Swagger 1.4. Swagger 1.4 needs to be updated so that it aligns with DES-138. DI-081 to be updated to periodDuration. DI-086 to be updated to supplierEffectiveFromDate. DI-121 to be updated to supplierEffectiveToDate. | Design Ambiguous | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-568 | SW |  | 2023-07-26 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - DES-138 incorrect | DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) shows in YAML as secondaryRecipientDIPID and primaryRecipientDIPID respectively and this should be updated in DES-138 YAML column so this aligns with Swagger 1.4 ie, DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) shows in YAML as secondaryRecipientDIPID and primaryRecipientDIPID respectively and this has been updated in DES-138 YAML column so this aligns with Swagger 1.4 ie, DI-981 (secondaryRecipients) and DI-982 (primaryRecipients). | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-569 | SW |  | 2023-07-26 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - DES-138 incorrect | DI-047, DI-049, DI-210, DI-211 and DI-820 are defined in the Data Catalogue, but not used in any Interfaces so need to be removed from the latest version of DES-138. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-047, DI-049, DI-210, DI-211 and DI-820 are defined in the Data Catalogue, but not used in any Interfaces so need to be removed from the latest version of DES-138. DES-138 needs to be updated to remove these items. | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-570 | MF |  | 2023-07-26 | MHHS |  | Mike Fensome | SRO Design | IF-021 validation rules | IF-021 validation rules need to be updated to align to the MDS and LSS Method statements which include validation for de-energised sites. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | IF-021 Added validation to align with MDS/LSS method statements where estimated data is provided on a de-energised site (ECS1008 - SP End Date/Time [DI-082] contains non-actual consumption for ECS De-Energised MPAN) | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-571 | SW |  | 2023-07-27 | Callisto | 2762 | Dave Peat | Software Provider | Inconsistency for DI-980 Response Message(s) | For DI-980, the YAML name is responseMessages, however in Swagger, there is inconsistencies: R0.responseMessages - this is defined as array of DI-980 (responseMessages) B066.responseMessage - but defined as responseMessages (defined as DI-980 - single) B092.responseMessage - defined as responseMessage (defined as DI-980 - single) We need to update DES-138 / Swagger so there is consistenct application of the words responseMessage (for single response) vs responseMessages (where there is an array of responses). |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | I have updated Swagger 1.4 so that DI-980 definition is applied consistently for single response vs array of responses. For single, it will be responseMessage. For an array of messages, it will be responseMessages. To this effect, B066.responseMessages has been updated to be responseMessage. Also, B066 block has been updated to align with DES-138 to be conditionally mandatory, rather than mandatory. | Supporting Docs | Design Ambiguous | Supporting Docs | Swagger 1.4
MHHS-DIN-572 | SC |  | 2023-07-27 | MHHS |  | Sean Cooper | SRO Design | Clarification of IF-013 Issuance (also Ref DIN610) | DUPE WITH DIN-610 ~ Clarification is requiired on the circumstances when Helix will issue IF-013. 1. IF-013 is only issued as part of the RF Run i.e. simply to notify Suppliers of what the default consumption for a period(s) is, where no data has been submitted by the DS come the point of RF. Should suppliers wish to derive this for pre-RF settlement runs then they are able to do so easily enough using the own data and the published Load Shapes. 2. The second view is that the IF-013 is issued on every settlement run undertaken for sites where no PUB-021 data has been received DIP impact concerns wrt to volumes of IF-013 would need to be addressed if Option 2 is the position. |  | Closed |  |  | 2023-09-13 |  |  | Duplicate of DIN-610 | No Change
MHHS-DIN-573 | ME |  | 2023-07-27 | MHHS |  | Kevin Spencer | SRO Design | Update to step 40 of ISD BPM/BPD | Step 40 of MHHSP-BP021 and BPD021 currently ambigious Can the intention of this step be made clearer.? |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Step 40 of ISD BPM and BPD have been updated to say 'Issue ISD Change Notification' to make ithe purpose of the step clearer. | Design Ambiguous | Minor | Supporting Docs | MHHSP-BP021 Industry Standing Data MHHSP-BPD021 Industry Standing Data Business process Descriptions
MHHS-DIN-574 | SC |  | 2023-07-27 | St Clements |  | Madison | SCS | Change Of Logic on Smets 1 Number of Digits | Smets 1 Number of digits can be 0 - 9 Replaces previous logic. |  | Closed | [5 empty] | DIN CLOSED as agreed with St Clements and RECCo. DIN-615 supercedes this DIN. The text has been updated as suggested below from RECCo, ‘Where the Meter Type is S1, the value should be populated as per the manufacturer specification.’ However, the logical test for SMETS1 in the DES-138 Interface Catalogue will remain unchanged. DIN-615 also includes updating the Swagger validation of this field to match SCS logical test i.e. value can be 0-9. | No Change
MHHS-DIN-575 | SC |  | 2023-07-27 | St Clements |  | Madison | SCS | Requirement for REGS to process IF-040 | SCS would prefer not to process IF-040 now that AC is provided to EES Directly via the DIP. In additional what is the IF-040 processing schedule? IF-040 is only sent to appointed Suppliers and Data Services on a 30 day cycle. There could be a 30 day wait until the next MDS generated IF-040. Programme Design: To fill this design gap the programme has made MPRS responsible to load the IF-040 by populating Annual Consumption in the B027 Block on IF-002, IF-001 & IF-036 MPRS Issue: An IF-040 for every energised MPAN must be loaded adding significant overhead to processing. The 24 hr SLA could be difficult to meet without significant hardware investment. | CR039 | Implemented | Change Request | LSDO (SCS), DIP |  | Interim Release 8 | 2024-03-20 | To minimise change and impact on all other participants B027 Block is retained in IF-001, IF-002 & IF-036, but will never need to be provided by Registration Service as it is only required where the data exists in Registration Service. Annual consumption requirements document updated to remove the requirement for REGS to receive PUB-040 and maintain Annual Consumption. BP005 and BPD005 updated to remove REGS receiving Annual Consumption. REGS removed from IF-040 secondary routing in DES-138. On Appointment, Data Service and Supplier will receive the latest PUB-040 with their PUB-036. DIP will be changed to replay the PUB-040 from the Message Archive. Note added to BP003. Change in IR5 SIT Scope to exclude B027 Block Loading for Supplier and Data Services. Remove testing of IF-040 Processing for MPRS Change in IR8 SIT Scope to add DIP IF-040 Replay on Supplier and Data Service Appointment Confirmation | Data interface correction | Supporting Docs | Interfaces | DES138 BP003 BP005 BPD005 BRS012
MHHS-DIN-576 | MF |  | 2023-07-27 | St Clements |  | Madison | SCS | Cancelling appointments in advance of receipt of PUB-034 | SCS have requested that the design is updated to allow for issuing of a PUB-035 'Lapsed' message, if a switch is 'Cancelled' or otherwise superseded, even prior to issuing / processing of a PUB-034 from the Metering Service or Data Service. ​ |  | Closed | [5 empty] | Following DRG on 4th Aug, it was agreed that St Clements Services were to work-up the topics discussed, and a dedicated workshop would be arranged to discuss this further. St Clements Services have advised the Programme that they will now not be pursuing proposals made at the DRG session and would be reverting to implement to the original design, therefore closure of this DIN.
MHHS-DIN-577 | SW |  | 2023-07-27 | Callisto | 2979 | Neil Edney | Software Provider | DT-983 and DT-000 are missing IF-040 / PUB-040 | DT-983 and DT-000 are missing IF-040 / PUB-040 in Swagger. IF-003, 19, 20 and 50 also need to be added to align with DES_138. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Need to update Swagger to include IF-040 and PUB-040 in DT-000 and DT-983. I’ve added IF-003 / 019 / 020 / 040 / 050 to DT-000 in Swagger and PUB-003 / 019 / 020 / 040 / 050 to DT-983 in Swagger | Supporting Docs | Design Ambiguous | Supporting Docs | Swagger 1.4
MHHS-DIN-578 | SB |  | 2023-07-28 | RECCo | 2943 | Jonny Moore | Central Body | EFDs, ETDs and Supplier information for Related and Import/Export Linkages | We’ve noticed through the design and build stage of EES that we are not being communicated the EFD and ETD of a Related MPAN set-up or an Import / Export Linkage. Nor are we being informed of the Supplier responsible for creating a Related MPAN relationship. This information is not currently being published in the IF020/PUB020 However, this information is currently available for market participants to view on EES. We had some feedback in the REC MSAG that participants would like to continue to view these items in EES and wonder if this is worth a DWG discussion? |  | Closed | [5 empty] | RECCo notified on DIN closure. The Effective From date is not currently shared on the D0386 which was the basis for the IF-019/PUB-020. If EES requires an EFD suggest that the transaction date from the header is used. These updates can only be made by the current Supplier. | No Change
MHHS-DIN-579 | SB |  | 2023-07-28 | ENWL | 2444 | Paul Stancliffe | Network Operator | PUB-043 Routing discrepancy | Trying to map flow PUB-43 to our TO BE business processes as these flows are showing on the MHHS - Interface Data Item Catalogue as routing to LDSO. However when trying to align these to the Business Process Diagram BPM011- Change of Connection Type and / or Market Segment V5.0 PUB-43 is not routing to LDSO |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | BP011B from Step 542 new flow for PUB-043 to LDSO new step Manage Change of Connection type Notification | Process Model correction | MPAN Ownership | Supporting Document | BP011B BPD011
MHHS-DIN-580 | RS |  | 2023-07-28 | RECCo | 2719 | Sarah Jones | Central Body | Late or Missing Secured Active Messages | understand the approach to managing CSS issues where secured active messages are not received within the expected secured active processing window. We understand the standard ‘happy path’ processing requires secured active notifications to be issued by CSS after the 5pm gate closure window the day before the registration effective from date. However, it was acknowledged when the MHHS design was originally baselined that some notifications may arrive late e.g. after 6pm, or not at all. Rather than developing operational provisions to deal with missing / late secure active notifications, this was highlighted as a risk for later consideration, on the basis the CSS arrangements were still new and the enduring BAU process was subject to change. In light of the CR018 approval, we believe this is now the time to clarify the approach to be taken where CSS notifications are missing or late. |  | Closed | [5 empty] | The Design Team and SRO are actively engaged with St Clements on issues around problematic switches. The plan is for them to provide us with a list of of their issues. We will then go through a process of raising these directly with CSS. Dependent on outcomes we receive back, we will look to discuss this with St Clements with the possibility of raising a CR for a specified data correction tool to align the data and send out the appropriate MHHS flows. | No Change
MHHS-DIN-581 | RS |  | 2023-07-28 | ESG | 2924 | Patricia Parker | Software Provider | Meter Location in DES138 | Currently DI090 in DES138 states 'Values as Per ISD'. These values are not held in ISD, therefore the reference should be changed to 'see Enum Values of the Data Catalogue' - example IF-005 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Updated population notes for DI-090 to refer to Data Catalogue, IF's 2,5,6,20.33.36,61,62 | Clarification | Supporting Docs | Interfaces | DES-138 Interface Spec
MHHS-DIN-582 | MF |  | 2023-07-28 | Ovo |  | Chris Butterfiled | Supplier | Clarification following CR15 | Supplier Overview requirements v5.1: this refers specifically to Economy 7 / Economy 10 tariffs; we suggest this should be more general and refer to any Time of Use tariff / tariff with switched load to include other variants such as Smart Economy 9 etc. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Updated SU-163, SU-164 and SU-165 to refer "for switched load tariff (eg. Economy 7/Economy 10) sites" rather than Economy 7/Economy 10 sites | Requirement correction | Supporting Docs | supplier requirements | MHHSP-BRS004 Supplier Overview
MHHS-DIN-583 | SB |  | 2023-07-31 | Stark | 2891 | Jon Dennis | Data Service Provider | BP005 Read Sharing for Data Service | can you provide clarification around BP005 Read Sharing for the Data Service, in particular this section of MHHSP-BP005-Data Processing-v5.1 Question: Is the entry point to this section either: Regular Data Collection, e.g. daily remote collection for ADS/SDS Smart? Trigggered by an external process, e.g. Change of Energisation BP008? To answer the above, please can you list all of the processes that lead to Step 170 in BP005. May I also suggest updating BP005 to include this information, perhaps by adding a Step description to the entry point from Data Collection as shown above. Related Question: In BP008 the Data Service is expected to progress to BP005 Step 185. However, unless I am mistaken, BP005 V5.2 does not include Step 185. Please update BP008 with a valid onward step. |  | Open - awaiting assessment | Clarification - No change required | Smart Data Services, Advanced Data Services |  | Post Go-live Release |  | Updates to be made to BP008: - Update to clarify that step 185 is actually step185 of BP008 rather than step185 of BP005 - Update to include note with information around entry points etc. | Process Model correction | All Areas | Process Models | BP005
MHHS-DIN-584 | SC |  | 2023-07-31 | Design Team |  | Sean Cooper | SRO Design Team | DI-511 Change of Data Type from String to Number in IF-024 | DI-511 Off Peak Declaration Proportion has been changed from String to Number so as to allow for improved Swagger validation of this data item. The new Number val will have a Minimum value = 0 and a Maximum Value = 100. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | DI-511 Off Peak Declaration Proportion has been changed from String to Number so as to allow for improved Swagger validation of this data item. The new Number value will have a Minimum value = 0 and a Maximum Value = 100. (IF-024). Data Catalogue updated accordingly. | Improved Validation of Data Item | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-585 | SC |  | 2023-07-31 | Design Team |  | Sean Cooper | SRO Design Team | Clarification on IF-024 | Clarification update to confirm that B097 Off Peak Declaration is Mandatory only for Event Type [SN-OffPeakDec] |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Clarification update to confirm that B097 Off Peak Declaration is Mandatory only for Event Type [SN-OffPeakDec] | Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-586 | SW | DI-204 | 2023-07-31 | Callisto | 2762 | Neil Edney | Software Provider | Mis-alignment between D0 block YAML in Swagger and DES-138 | DES138, the D0 has the following YAML names which do not align DIPCorrelationID, DIPTimeStamp, DIPTransationID However, swagger has these: initialCorrelationID, transactionTimestamp, transactionID |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Updated DES138 Data Catalogue D0 Common block data items so that YAML names in DES-138 now align with Swagger initialCorrelationID (DI-987), transactionTimestamp (DI-989), transactionID (DI-990) | Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-587 | SW |  | 2023-08-01 | Kraken | 2973 | Angelos Rizoyannis | Software Provider | Mis-alignment between R0 mandatory in Swagger vs DES-138 | In DES-138 in the following interfaces, R0 is marked as mandatory, but not mandatory in Swagger - IF-006, IF-008, IF-014, IF-020, IF-026, IF-028, IF-032, IF-039. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | In DES-138 in the following interfaces, R0 is marked as mandatory, but not mandatory in Swagger - IF-006, IF-008, IF-014, IF-020, IF-026, IF-028, IF-032, IF-039. Update R0 to be mandatory in these interfaces. | Clarification | Minor | Interfaces | Swagger 1.5
MHHS-DIN-588 | ME |  | 2023-08-02 | Design Team |  | Kevin Spencer | Programme Design | Update of ID to Id | A request has come from Elexon to update the ISD Entities document. Id should be changed to ID |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | All instances of Id have been changed to ID (see also DIN 557) | Supporting Document | Minor | Supporting Document | MHHSP_EDI021_ISD_Entities v5.3.2
MHHS-DIN-589 | SB |  | 2023-08-02 | Stark | 2466 | Jon Dennis | Data Service Provider | ADS and SDS Estimation Statements | I have been studying the following two documents: Advanced Data Service Validation and Estimation: Methodology Statement (MHHSP-METH002_ADS_Validation_Estimation v5.1) Smart Data Service Validation and Estimation: Methodology Statement (MHHSP-METH001_SDS_Validation_Estimation v5.1) In particular, Section 3 of the ADS_Validation_Estimation document details the estimation methods where the customer has opted-out of UTC Period consumption data. It references the SDS_Validation_Estimation document where Estimation methods are in Section 7. The 2 method statements have become misaligned when changes to the SDS method statement was updated. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | We will align the ADS method statement with the SDS method statement to keep it uniform. | Method statement correction | Supporting Docs | Method Statement | ADS Method Statement
MHHS-DIN-590 | KH |  | 2023-08-03 | Design Team | 2717 | Martin Freeman | Central Body | Update Role Codes in E2E001 | There is a mismatch between roles codes that are in DES-138 and those that are in E2E001. Role code for Unmetered Supplies Data Services changed from UDS to UMSDS. Need to ensure that all of the role codes referenced in DES-138 are included in E2E001 and that there is a full explanation of what these are. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update all the role codes referenced in DES-138 to ensure they are included in E2E001 and that there is a full explanation of what these are. | Data interface correction | Supporting Docs | Interface Catalogue | E2E001 E2E Architecture Document
MHHS-DIN-591 | KH |  | 2023-08-03 | Elexon | 2974 | Michael Ceney | Central Body | Update to MDS Method statement | The MDS Method Statement Section 2.1 should read: If today > MDS Run Date (RF) for SP End Date/Time [DI-082] in the Master Settlement Table in ISD ECS1003 - SP End Date/Time [DI-082] has already passed "MDS Run Date (RF) [ISD.RunDate-RFDate] |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update DES138 and MDS Method Statement Section 2.1 to read "If today > MDS Run Date (RF) for SP End Date/Time [DI-082] in the Master Settlement Table in ISD ECS1003 - SP End Date/Time [DI-082] has already passed "MDS Run Date (RF) [ISD.RunDate-RFDate]" update ECS1003 in 00-introductions and IF-21 | Data interface correction | Supporting Docs | Supporting Docs | MDS Method Statement MHHSP-DES138-Interface Catalogue
MHHS-DIN-592 | SW |  | 2023-08-03 | Design Team | 2717 | Martin Freeman | Central Body | Update StatusMessage and StandardResponseBody in E2E001 to provide more clarity | There are inconsistencies between StatusMessage / Standard Response body definitions for what is contained with E2E001 and Swagger, these need to be aligned. Clarity needs to be provided on how TransactionID is populated in Status Message for Level 2 validation and Level 4 validation and for Level 4 validation, how this is sent to original sender. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Align inconsistencies between StatusMessage / Standard Response body definitions for what is contained with E2E001 and Swagger. Provide clariry on how TransactionID is populated in Status Message for Level 2 validation and Level 4 validation | Data interface correction | Supporting Docs | Interface Catalogue | E2E001 MHHSP-DES138-Interface Catalogue
MHHS-DIN-593 | ME |  | 2023-08-04 | Design Team |  | Kevin Spencer | Programme Design | Update to AC Method Statement | Update required to the AC Method Statement to amend calculation where less than 365 days of data is available and a change to section 2.2 to allow calculations to be undertaken on Calendar days |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | The following changes below in red have been made to section 2.2 of the AC Method Statement The Market-wide Data Service (MDS) should schedule the calculation of MPANs requiring a new Annual Consumption for active MPANs evenly across each working day of the month and publish on the day the day of the calculation. The recalculation shall be performed each month, for every MPAN and every 30 Calendar days +/- 5 Calendar days of the date of the previous calculation. Changes to the calculation of less than 365 days available are no longer reuried as agreed with Helix | Method statement correction | Supporting Docs | Method Statement | Annual Consumption Meth 10
MHHS-DIN-594 | SC | SCS DI-207 | 2023-08-04 | Design Team |  | Sean Cooper | Programme Design | Correction to BP10 Related MPANs | Rejection was incorrectly shown being sent direct from REGS rather than from REGS Via DIP. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Rejection was incorrectly shown being sent direct from REGS rather than from REGS Via DIP. moved the starting point from step 340 to step 360 for rejections on BP010B | Process Model correction | MPAN Ownership | Supporting Document | BP010-Registration Updates
MHHS-DIN-595 | SC | SCS DI-208 | 2023-08-04 | Design Team |  | Sean Cooper | Programme Design | Correction of Type in ISD Doc Table 16 | Correction of type in definition of subscript 3 for table M16 - "Market Participant ID" changed to "Market Participant Role" |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Correction of type in definition of subscript 3 for table M16 - "Market Participant ID" changed to "Market Participant Role" | Clarification | Supporting Docs | supporting document | MHHSP_EDI021_ISD_Entities
MHHS-DIN-596 | SC |  | 2023-08-04 | Design Team |  | Sean Cooper | Programme Design | Clarification of SP Appointment Time(s) | Per DRG decision all SP Appointment times shall be effective from Midnight UTC Time. Clarification added to IF-031/If-036 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Added validation rule to IF-031 to ensure appointments are made at midnight [UTC/Clock]. Pending agreement from Working Group and DAG. | Clarification | Supporting Docs | Interfaces | DES-138 Interface Spec
MHHS-DIN-597 | SC | SCS DI-193 | 2023-08-07 | MHHS |  | Sean Cooper | SRO Design | IF-026 B068 Presence | IF-026 / B068 - SCS requested removal of wording "must be required for smart meter removed" as this is inherent as part of the Event Type. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | IF-026 / B068 - SCS requested removal of wording "must be required for smart meter removed" as this is inherant as part of the Event Type. | Clarification | Supporting Docs | Interface Catalogue | DES-138 Interface Spec
MHHS-DIN-598 | SC | SCS DI-176 | 2023-08-07 | St Clements |  | Madison Layton | Software Provider | Incoming Supplier Notifications - Clarification | SCS raised a query around whether certain flows should be copied to an incomming Supplier (PUB-006, PUB008 etc. etc.) The current design does not include copying of these flows to an incoming supplier, (not represented in either Requirements or BP maps). IF-036 (and accompanying D-flows as required) provides suppliers with a clear starting point containing all the information they need to support servicing the customer. Design Team feel any change in this area would require a CR. |  | Closed | [5 empty] | Any change in this area would require changes to the REGS Requirements to implemnt Primary Routing, as copying of such flows could not be performed by DIP Secondary Routing. CR would be required to confirm new requirements and allow for IA on REGS and Suppiers design. Design Team also note that no other issues/DIN raised on this issue, by suppliers or other participants. | Clarification | Clarification - No change Required
MHHS-DIN-599 | BK | SCS DI-198 | 2023-08-07 | St Clements |  | Madison Layton | Software Provider | Data Cleansing required on IHD, SMSO and Installation Date | SCS raised a a query on the three items below that are not under the Data Cleanse Plan that may need cleanse work. 1) IHD - Should be populated for smart meters, and only smart meters (not currently validated) 2) SMSO - Should be populated for smart meters and only smart meters (not currently validated) 3) Installation date - Should not be prior to MPAN Creation date (Legacy data integrity issues of meters migrated into MPRS) |  | Closed | [5 empty] | This change has been forwarded onto the Data Cleansing Working Group as it is not a design issue. Design Team also advised SCS to raise these issues within the working group. | Clarification | Clarification - No change Required
MHHS-DIN-600 | ME |  | 2023-08-07 | Elexon | 4566 | Rashmi Radhakrishnan | Central Body | ISD Entity M18 Discrepancy | In the ISD Entity Document the table shows {Effective From Date {DIPRole} and {Effective To Date {DIPRole}, however the exmaple table and column details have been titled as {Effective From Date {MP2DPM} and {Effective To Date {MP2DPM}. These should be changed to align with the first table in entity M18 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Corrected M18 Col Headings and column name references to read "DIPRole" | Data interface correction | Supporting Docs | supporting document | MHHSP_EDI021_ISD_Entities
MHHS-DIN-601 | SW |  | 2023-08-07 | Kraken | 4485 | Adrian Serban | Software Provider | Incorrect on M0 common block in IF-018 | In Swagger, it appears the block is correct (M0), but the label is incorrect (M1) for IF-018. The label needs to be updated to M0 to align with the block. This needs to be updated in Swagger so the label is incorrect. In IF-019 and IF-020, there is an inconsitency of use of M1 vs M0. |  | Closed | [5 empty] | M1 is used in IF-019 and IF-20. M0 is used in all other IFs where required. Swagger version 1.4 has been reviewed and correctly reflects this position. | No Change
MHHS-DIN-602 | RG |  | 2023-08-08 | Design Team |  | Rob Golding | Programme Design | Add Interface, Event Code enumeration to Swagger for interface blocks | Interface and Event code validation and alloawable blocks is missing from the DIP. Rather then getting Avanade to code these dependencies the proposal is to intoduce the restrictions into the Swagger |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update the swagger for the majority of interfaces where different event codes require different combinations of optionality for the blocks they reference. An example of this has been done already for IF-001 in the new swagger file Interface-001. | Improved error trapping at interface | Minor | Interfaces | Swagger 1.5
MHHS-DIN-603 | SW |  | 2023-08-09 | Design Team | 4022, 4700 | Steve Weston | Central Body | Clarity on A0 block being removed | Section 4.2.1 of the E2E001 design has a diagram that shows that the A0 common block is removed by the DIP prior to sending out the message to onward particpants. This is inconsistent with the rest of the design. Section 4.2.1 needs to be updated so that this shows A0 not being removed. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update Section 4.2.1 of E2E001 figure 4 so that this shows A0 not being removed | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger 1.4 | E2E001 E2E Architecture Document Swagger 1.5
MHHS-DIN-604 | SW |  | 2023-08-09 | Design Team | 4945 | Steve Weston | Siemens | Clarity on B066 mandatory on IF-035 | In DES-138, B066 block in IF-035 is shown as mandatory and also defined as mandatory in Swagger. This should be conditionally mandatory as per B019, so this needs to be updated to conditionally mandatory in DES-138 and also in Swagger 1.5. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update B066 block in IF-035 to mandatory where event code DCC-MDR Outcome Swagger 1.5, no change in DES138 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-605 | SC |  | 2023-08-09 | Design Team |  | Sean Cooper | Programme Design | Update "Switch Cancellation" Info Message Box of BP002 & BP003 | Message updated to make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations received prior to PUB-34 processing will be managed by normal queue processing. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Message updated to make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Where in the rare scenario a cancellation is received and accepted by the Registration Service before the PUB-034, the Registration Service will not lapse on receipt of the cancellation, instead re-validation the day prior to the appointment start date would trigger a lapse. | Clarification | MPAN Ownership | process | BP002 / BP003 Change of SP
MHHS-DIN-606 | SC |  | 2023-08-09 | Design Team |  | Sean Cooper | Programme Design | Update Ops C to include clarification on issuing of IF-035 | Make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations received prior to PUB-34 processing will be managed by normal queue processing. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update OPS Choreography document (Foot-note to OPC-190) to clarify processing of IF-035 (See DIN-605) | Clarification | Supporting Docs | Supporting Document | MHHSP-OPC001 Operational Choreography
MHHS-DIN-607 | SC |  | 2023-08-10 | St Clements |  | Sean Cooper | Programme Design | Update IF-035 Lapsed Reason Code | SCS Request Update IF-035 Lapsed Reason Code from "Switch Cancelled" to "Registration Cancelled" |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Updated IF-035 Lapsed Reason Code LP004 from "Switch Cancelled" to "Registration Cancelled" | Clarification | Minor | Interfaces | DES-138 Interface Doc
MHHS-DIN-608 | SC | SCS DI-206 | 2023-08-10 | St Clements |  | Sean Cooper | Programme Design | Correction of Inaccuracy on BP003 | Steps 86,87,88 added to better reflect that REGS will actually send TWO IF-035 messages not just one. IF-035 [SendMTD] will be issued to Incumbent MS and [AppOutcome] event will be issued to DS/Supplier. BP003 now mirrors the drafting in BP002. There is no change in underlying requirement here - redrafting is simply a more accurate representation of REGS activity. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Steps 86,87,88 added to better reflect that REGS will actually send TWO IF-035 messages not just one. IF-035 [SendMTD] will be issued to Incumbent MS and [AppOutcome] event will be issued to DS/Supplier. BP003 now mirrors the drafting in BP002. | Clarification | Minor | Interfaces | BP003
MHHS-DIN-609 | SC |  | 2023-08-10 | Helix |  | Sean Cooper | Programme Design | Helix Issuing of IF-040 Annual Consumption Messages | Discussion held with Helix on proposed approach to issuing IF-040 messages. Current design suggests that messages should only be issued on Working Days - Design Team are exploring why this is the case (risk of substantial peak esp on 4 day long weekends). preference would be for Helix to issue IF-040 on each calendar day. |  | Implemented |  |  | 2023-09-13 | Interim Release 5 | 2023-09-20 | Update the OpsC document to set a 24hr rather than a 2hr limit around processing the IF-040 interfaces only | Clarification | Supporting Docs | Supporting Document | OPS Choreography
MHHS-DIN-610 | SC |  | 2023-08-10 | Helix |  | Sean Cooper | Programme Design | Clarification of IF-013 Functionality (also ref 572) | 1. IF-013 is only issued as part of the RF Run i.e. simply to notify Suppliers of what the default consumption for a period(s) is, where no data has been submitted by the DS come the point of RF. … … Should suppliers wish to derive this for pre-RF settlement runs then they are able to do so easily enough using the own data and the published Load Shapes. Need to validate if IF-013 should be issued after each Settlement Run OR only after RF Run. Also need to validate the IF-10 should NOT be issued after II Run. 2. The second view is that the IF-013 is issued on every settlement run undertaken for sites where no PUB-021 data has been received DIP impact concerns wrt to volumes of IF-013 would need to be addressed if Option 2 is the position. Dupe with DIN-572 |  | Implemented |  |  | 2023-09-13 | Interim Release 5 | 2023-09-20 | Following Review at DRG meeting - agreement reached that IF-013 should NOT be sent for the II Run and should only be issued for SF and later Runs. DES-138 IF-013 Additional notes updated to reflect this decision. ----- MDS Method statement also requires update to record this decision. The following text has been added to the Method Statement Restrict sending of IF-013 until the SF Settlement Run The following statement has been added to the MDS Method Statement section 9.2 The sending of IF-013 will be restricted until the SF Settlement Run | Clarification | Supporting Docs | Supporting Document | DES-138 Interface Catalogue MDS Method Statement
MHHS-DIN-611 | KH |  | 2023-08-11 | Elexon | 3986 | Michael Ceney | Central Body | Changes required to MDS Method Statement | Following the release of DIN-332, changing EventCode [ConsumptionOnDe-energisedMpan], the MDS Method Statement needs updating to reflect this change. Section 9.3 states that the an exception report will be provided using IF-013, this needs to show IF-014 is to be used. Please can a new DIN be raised. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | We will update section 9.3 to state that the report will be provided using IF-014. | Method statement correction | Supporting Docs | Method Statement | MDS Method Statement
MHHS-DIN-612 | SC | PDA Test Issues | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | New IF-019 Validation Rules Re Unmetered Related MPANs | Added x2 new validtion rules to prevent the creation / addition of Related MPANs with a Connection Type of "U - Unmetered". No validation applied to remove so as to allow for the resolution of any historically erroneous links |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Added x2 new validation rules to prevent the creation / addition of Related MPANs with a Connection Type of "U - Unmetered". No validation applied to remove so as to allow for the resolution of any historically erroneous links | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-613 | SC |  | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Remove Reference to SP Appointment Start Time(s) | In line with DRG Decision on 4th Aug - it was agreed that ALL Service Provider Appointments should commence at Midnight UTC. Text against DI-086 and DI-121 has been removed. A new section addressing the treatment of Time has been added to the Additional Information tab of DES-138 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | In line with DRG Decision on 4th Aug - it was agreed that ALL Serive Provider Appointments should commence at Midnight UTC. Text against DI-086 and DI-121 has been removed. A new section addressing the treatment of Time will be added to the Additional Information tab of DES-138 as part of Interim Release 5 (DIN-614) | Design Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-614 | SC |  | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | Create new "Time" Advisory Notes in Registration Additional Info Section | SC to create Treatment of Time section |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Add clarification on Regs Notes tab. around appointment time and Transfer read time. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-615 | SC |  | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Number of Registers Validation | Clarification following on from DIN-574. Text against Number of Register Digits fields amended to say "per the manufacturer specification" . Note text for SCS validation will remain unchanged. Swagger validation of this field updated to match SCS logical test ie value can be 0-9 |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | Clarification following on from DIN-574. Text against Number of Register Digits field amended in IF-002, IF-005, IF-006, IF-033, to say "per the manufacturer specification". Note text for SCS validation will remain unchanged. Swagger validation of this field updated to match SCS logical test ie value can be 0-9. | Design Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-616 | SC |  | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | Review of COS Transfer of Readings Process Required in light of SP UTC Decision | A Review of BP003C is required to impact assess implications of SP UTC Decision |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | BP003C may need updating follow impact assessment | Clarification | Supporting Docs
MHHS-DIN-617 | SC | PDA Test Issues | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | Note on Discretionary Use of IF-023/IF-040 by Data Service | Missing interface notes on Discretionary Use of IF-023/IF-040 by Data Service |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Added interface notes to clarify Annual Consumption usage in IF-040 and Load Shape Totals in IF-023 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-618 | KH |  | 2023-08-15 | ESG | 5859 | Patricia Parker | Software Provider | Updating routing within DES138 - PUB-026 | Could you please clarify what updates the Metering Service will receive via the PUB_026. From the routing the only update is re the SCCandProfile Class. However, BP010C alludes to the MS receiving an update for the SMSO - could you please confirm which is correct? |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | To update PUB-026 adding XMSC to the SMSO secondary routing. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-619 | SC | PDA Test Issues | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Draft Umetered Change of Energisation Status Business Process Map | Update BP08 existing or draft Unmetered Specific version. |  | Closed | [5 empty] | Pending feedback from PDA on UMS process. No feedback provided - closed
MHHS-DIN-620 | SC | Test Issues | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | Remove EES as a Recipient of IF-001 | Remove EES as a Recipient of IF-001 | CR028 | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Removed EES as a Recipient of IF-001 - EES gets this info from CSS | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-621 | SC |  | 2023-08-17 | MHHS |  | Sean Cooper | SRO Design | Changes to D303 DTN Flow | Need to make "Manufacture and Type" non mandatory in the D303 flow. Follow migration to MHHS it is possible that this data item is not held in REGS and therefore not shared with all MHHS Participants incl. MS who currently would need to provided it on the D303. Discussions were held in Data Working group around back population of this data item but that proposal was REJECTED - therefore only other option is to make this field optional in D303 |  | Implemented | Design gap | TBC |  | Interim Release 8 | 2024-03-20 | Passed to Matt McK to add to existing industry CP changes.
MHHS-DIN-622 | SC | SCS | 2023-08-17 | St Clements |  | Sean Cooper | SRO Design | DIP Validation of Sender Correlation ID | Implement DIP validation to check for incorrect population of Sender Correlation ID. |  | Closed | [5 empty] | CR would be required for the DIP to implement Sender Correlation ID validation. Decision to implement Level 3/4 Sender Correlation ID validation is with the recipient. | Clarification
MHHS-DIN-623 | SC | SCS | 2023-08-17 | St Clements |  | Sean Cooper | Programme Design | Change IF-001 Routing | Add SUPL (Linked Supplier) as an additional Primary Receipient of Inital Registration Event |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Add SUPL (Linked Supplier) as an additional Primary Receipient of Inital Registration Event for IF001 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-624 | ME |  | 2023-08-18 | Design Team |  | Miriam Ellis | Programme Design | BP013 DDE Updates | MHHS test team have identified discrepancies within the ECS BPM's that require updates to align with the ECS reports. Updates are required to BPM13 DDE |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Updates to BPM013: 1. Update reference of MHHS-REP-001 to ELEX-REP-001 in BP header 2. Update reference of REP-005 to ELEX-REP-005 in BP header 3. Reference of MHHS-REP-002A included with BP header 4. Reference of REP-002 changed to ELEX-REP-001 | Clarification | Supporting Docs | Reporting Catalogue | BPM013
MHHS-DIN-625 | SC | DI-210 | 2023-08-18 | St Clements | 6221 | Sean Cooper | Programme Design | B092 should also be an array to allow MPRS to populate multiple rejections | B092 should also be array to allow MPRS to populate multiple rejections |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Consider breaking out DI-980 into an array in B092 block of IF-035. Block B099 added containing DI-979 and DI-980 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue Swagger 1.5
MHHS-DIN-626 | SC | ESG | 2023-08-22 | ESG |  | Sean Cooper | Programme Design | Update Routing of IF-003 | Routing of this flow should match that of the IF-037 - in that a copy should also be sent to the Supplier. IF-003 Routing table updated to show Supplier as being a receipient of the iF-003 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Routing of this flow should match that of the IF-037 - in that a copy should also be sent to the Supplier. IF-003 Routing table updated to show Supplier as being a receipient of the iF-003 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-627 | SC | ESG | 2023-08-22 | ESC |  | Sean Cooper | Programme Design | Update Interface Doc "Correlation ID Required" to "Correlation ID Created" | Inconsistancy indentified in the column headings across different IFs. All should read "Correlation ID Created" as this column denotes if the DIP IF should create/copy a DIP Correlation ID value or not. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update Interface Doc "Correlation ID Required" to "Correlation ID Created" | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-628 | SC |  | 2023-08-23 | Design Team |  | Sean Cooper | Programme Design | Add in Missing IF-021 Validation | Add NEW validation to ensure that "UTC Settlement Date" has time of Midnight UTC. Added clarification to existing validation rule that time element of "Settlement period end date time" should align with Settlement period duration |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Add NEW validation to ensure that "UTC Settlement Date" has time of Midnight UTC. Added clarification to existing validation rule that time element of "Settlement period end date time" should align with Settlement period duration | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-629 | MF |  | 2023-08-25 | Design Team |  | Mike Fensome | Programme Design | Routing for SUPC on IF-037 | To ensure that the outgoing Supplier are correctly notified of de-appointment of their Service Providers, routing rules for SUPC updated to Primary routing for IF-037 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | SUPC routing moved from Secondary to Primary for IF-037 for all events | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-630 | MF |  | 2023-08-25 | Design Team | N/A | Mike Fensome | Programme Design | Remove incorrect arrow on BP002 | Arrow incorrectly added into BPOO2 between steps 225 and steps 245 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Arrow between steps 225 and steps 245 on BP002 removed. Previously added in error. | Process Model correction | Minor | Interfaces | BP002
MHHS-DIN-631 | SC |  | 2023-08-29 | MHHS | N/A | Sean Cooper | SRO Design | Swagger Alignment - Block B051 | Required Data Items field names do not match those specfied in the defintion. |  | Implemented |  |  |  | Interim Release 4 | 2023-08-16 | loadShapeGSPGroup and loadShapeDomesticPremiseIndicator added to Required fields section to align with block definition. | Correction | Minor |  | DES-138 Interface Cat
MHHS-DIN-632 | SC |  | 2023-08-31 | Helix | N/A | Sean Cooper | SRO Design | Header & Footer Requirements for ISD Entity Files | ISD Specification should be updated to include specification/definition of a standard Header and Footer to be applied to each ISD Entity CSV file. |  | Initial Assessment/Updating | Design gap | Helix, Suppliers |  | Post Go-live Release | 0 | Decision required on exact content/structure of Header ... Is a footer required? If so what should it include (eg number of Entity entries) | Requirement correction | Supporting Docs | ISD | EDI021 ISD Entities Document
MHHS-DIN-633 | SC |  | 2023-08-31 | Helix | N/A | Sean Cooper | Programme Design | Update to ISD E45 | Update Entity 45 - Market Role code needs to allow Blanks in order to align with other tables in ISD and to provide for [new] Market Participants who dont have a legacy market particpant role code |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update Entity 45 - Market Participant Role code needs to allow Blanks (Optional) in order to align with other tables in ISD and to provide for [new MHHS] Market Participants who dont have a legacy market participant role code | Clarification | Supporting Docs | Supporting Document | MHHSP_EDI021_ISD_Entities
MHHS-DIN-634 | KH |  | 2023-09-01 |  | 6616 | Tym Huckin | Consultancy | Update UMSDS Method Statement with correct comments for Null value | In row 2, where we have a "live" summary but it is de-energised, it says to put "A" actual data flag and use Estimation Reason Code "7", but the DI-076 column in that row says this should be Null. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | In 10.1 the table states in row two that the "Estimation Reason code" is Null and therefore the comments column will be updated to: If a D0388 has been received with load associated data and the MPAN is de-energised the load should be calculated, submitted as ‘A’ Flagged but with an Estimation Reason Code of Null | Correction | Supporting Docs | Method Statement | UMSDS Method Statement
MHHS-DIN-635 | RG |  | 2023-09-04 | Design Team |  | Rob Golding | Programme Design | Status Code needs tidying in StandardResponseBodyType | 4In the “StandardResponseBodyType” definition, there is a required property called "statusCode" that is not listed among the properties. Could you please address this inconsistency? |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Simple update | Data interface correction | Swagger |  | Swagger
MHHS-DIN-636 | SC |  | 2023-09-04 | Design Team |  | Sean Cooper | Programme Design | Removal of YAML Name Fields from Data Catalogue | Following discussions agreement to remove YAML fields from Data Catalouge. Swagger will be the definitive reference for the Jason/Yaml property labeling etc. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Following discussions agreement to remove YAML fields from Data Catalogue. Swagger will be the definitive reference for the Json/Yaml property labelling etc. | Data interface correction | Supporting Docs | Interface catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-637 | RG |  | 2023-09-04 | Design Team |  | Rob Golding | Programme Design | Data Catalogue items incorrectly use maximum and minimum | String need to be range bounded by maxLength & minLength |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update swagger so that maxLength and minLength are used instead of maximum and minimum | Dat Interface correction | Swagger |  | Swagger
MHHS-DIN-638 | RG |  | 2023-09-04 | Design Team |  | Rob Golding | Programme Design | Block: D0, Field: serviceTicketURL. DES138 specifies 'string max 225', Swagger specifies 'string max 250' | Set to 250 in DES 138 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | DES138 update, 01-Data Catalogue & 02- DIP Common : Block: D0, Field: serviceTicketURL (DI-978) set to 250 | Data interface correction | Supporting Docs | interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-639 | RG |  | 2023-09-04 | Design Team |  | Rob Golding | Programme Design | DI-138-Customer-Direct-Contract-Data-Service-DIP-ID & DI-140-Customer-Direct-Contract-Metering-Service-DIP-ID to be nullable | Update both to be nullable |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update swagger so that DI-138-Customer-Direct-Contract-Data-Service-DIP-ID & DI-140-Customer-Direct-Contract-Metering-Service-DIP-ID are DT-006N, i.e. nullable | Data interface correction | Swagger |  | Swagger
MHHS-DIN-640 | RG |  | 2023-09-05 | Design Team |  | Sean Cooper | Programme Design | Custom Block: B022, Field: Metering Point Postcode. Interface Catalogue specifies CMO as ‘M’ for IF-018, all other interfaces specify CMO as ‘O’. | Update DES138 so that all versions are the same and marked as optional Custom Block: B022, Field: Metering Point Postcode. Interface Catalogue specifies CMO as ‘M’ for IF-018, all other interfaces specify CMO as ‘O’. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update DES138 so that all versions of B022 are the same and fields marked as optional | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-641 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | Custom Block: B022, Field: Metering Point Postcode. Interface Catalogue specifies no min length, but min length of 6 specified in Swagger. | Update swagger to align |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update swagger to align minlength removed from DT007(N) | Data interface correction | Swagger |  | swagger
MHHS-DIN-642 | RS |  | 2023-09-05 | MHHS | 7382 | Rob Golding | SRO Design | NFR0045 Performance Efficiency | this NFR does not clearly define how the DIP will throttle participants where connection are over a mutually shared mTLS connection. Shared mTLS connections will be used by many parties such as DIP Connection Providers, the requirement to use them being placed on parties that will be Placing Reliance on a Connection Provider. Effectively, this means that multiple parties will use the mTLS connection and which, under certain circumstances could see significant increases over that mTLS if more than one party’s message volumes increased. |  | Closed | [5 empty] | This item is being managed as part of the DIP work-off plan
MHHS-DIN-643 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | B029 Fields marked as mandatory | B029 Condtitonal mandatory marked as required. Block will be conditional |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update DES138 & swagger | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue Swagger
MHHS-DIN-644 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | DI-122 Profile Class has a minLength of 2 in Swagger. | add minLength clause |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update swagger DI-122 Profile Class to minLength =2 in swagger | Data interface correction | Swagger |  | Swagger
MHHS-DIN-645 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | Clarify 'AllRoles' for DIP routing for IF-047 | Update to include MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update DES138 IF-047 so that all roles are specified (MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES) | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-646 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | DT-002N-MPAN requires a minLength of 13 | add minLength clause |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update DT-002N-MPAN to min length & max length 13 in swagger | Data interface correction | Swagger |  | Swagger
MHHS-DIN-647 | RG |  | 2023-09-06 | Design Team |  | Rob Golding | Programme Design | Replace reportId with interfaceId in the ECS reports | Replace reportId with interfaceId in the ECS reports to make S0 block consistent across all reports/interfaces |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update swagger & MHHSP - ERI011B - ECS Reports - External v5.4 | Reporting correction | Supporting Docs |  | MHHSP - ERI011B - ECS Reports - External Swagger
MHHS-DIN-648 | KH |  | 2023-09-06 | St Clements |  | Vicki Holland | Software Provider | DI-496 data item | This data item was given a max value of 48, however the max value should be 50 to allow for the clock change day in October which has 50 settlement periods. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | All settlements reports will be in clock time and can have 46, 48 or 50 Settlement Periods. DI-496 is INT(3) to allow for a change to 15 minute Settlement Periods which would require a value of 100 for the Autumn Clock Change in the future. Maximum value in Swagger and ECS Reports to be updated to 50 for half hourly settlement periods. | Reporting correction | Supporting Docs | interface catalogue | MHHSP - ERI011B - ECS Reports - External MHHSP - ERI011A - ECS Reports - Internal Swagger
MHHS-DIN-649 | SC |  | 2023-09-06 | MHHS |  | Sean Cooper | SRO Design | REGS-EES 'Refresh' Flow - IF-051 | Following discussion with SCS and EEC - proposed definition of refresh message iF-051 |  | Closed | [5 empty] | Initial draft reviewed by EES and SCS - revisions to follow. Closed as duplicate - refer to DIN-051
MHHS-DIN-650 | BK |  | 2023-09-06 | Design Team |  | Rob Golding | Programme Design | Introduction of Compressed Payloads into DIP Messages | Detailed analysis of the some of the ECS reports, specifically REP003, has found that some of the reports can potentially grow to a very large size ~ 12MB. Within MHHS message design there is a notional upper limit for the size of messages which is 1MB, and hence these messages will exceed this constraint. | CR030 | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | The proposal is that the Sender (ECS) compresses the report and base64 encodes the data into the CustomBlock. The recipient will know that a specific message flow is compressed, and hence will need to decompress the payload. The proposal is to use gzip for the compression. This new pattern for compressed payloads will be initially introduced for the following reports: REP-002 LDSO report for DUoS – aggregated data REP-002A Embedded Network report for DUoS – aggregated data REP-003 BM Unit Allocated Demand Volumes to Market Participants REP-004 Supplier Deemed Take Report REP-006 Aggregated Uncorrected volumes by CCC to Market Participants REP-007 VAS Exception Report to Suppliers and BSCCo REP-008 MDS Exception Report to LDSOs REP-009 EMRS Report for Suppliers A covering statement has been included within the Introduction tab of ECS reports which highlights the changes made to Swagger. | Data interface correction | Technical Artefact | Technical Artefact | Swagger 1.5 MHHSP - ERI011A - ECS Reports - Internal
MHHS-DIN-651 | MH |  | 2023-09-07 | MHHS |  | Kevin Spencer | SRO Design | Supplier Registration of ABMU/ MPAN mapping | There is a design gap around Supplier ABMU Mapping held by ELEXON. Suppliers will need to register their MPAN/ ABMU Mappings for MHHS. Currently, they send a D0297 to HHDAs to provide the Mapping and can populate the SVA Metering Service Register for MSID Pairs where they are used in the Balancing Mechanism using the P0278 and self-service via ELEXON Kinnect. The issue is that for MHHS the export might be with one Supplier and the import with another. The validation in Kinnect only supports a pair being submitted mapping both import and export to the ABMU. Likewise, the P0278 only supports the provision of MSID pairs. We think a new flow may be needed or the D0297 re-routed to PMP. |  | Closed | Design gap | Helix | 2024-01-12 |  |  | Pending Helix raising a Change Request
MHHS-DIN-652 | RG |  | 2023-09-07 | Design Team |  | Rob Golding | Programme Design | DI-091-Number-Of-Displayed-Register-Digits update in DES138 to reflect the range 0-9 | DI-091-Number-Of-Displayed-Register-Digits update in DES138 to reflect the range 0-9 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update DI-091 in the data catalogue to have the correct min (0)/ max(9) values | Data interface correction | Supporting Docs | Interfaces | DES138 - Interface Doc
MHHS-DIN-653 | RG |  | 2023-09-07 | Design Team |  | Rob Golding | Programme Design | MO block removed from IF-047 | MO block removed from IF-047 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | M0 block removed from IF-047 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-654 | RG |  | 2023-09-07 | Design Team |  | Rob Golding | Programme Design | DI-130 RMP and DI-131 MP status maxlength | Reduce maxlength to align with eumerated type (50->1) |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Max length updated to 1 in Swagger for DI-130 RMP and DI-131 MP status | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-655 | RG |  | 2023-09-08 | Design Team |  | Fredrik Omland | Software Provider | Add a set no additional properties to false | Adding a set no additional properties condition to the swagger objects improves the validation |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Add "additionalProperties: false" to all schema objects in swagger so that no additional properties / fields can be attached to an object that are not specficied in the schema. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-656 | SW |  | 2023-09-11 | Design Team |  | Steve Weston | Central Body | All S1 properties to be mandatory | Ensure all S1 properties are mandatory as per DES-138 in Swagger 1.5 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Ensure all S1 properties are mandatory nullable as per DES-138 in Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-657 | ME |  | 2023-09-11 | Design Team |  | Miriam Ellis | Programme Design | NEW ISD Entity | A request has come in from St Clements requesting for a New ISD entity which lists settlement period quality indicators, with a mapping to an actual or estimate indicator. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | ISD Entity M19 Settlement Period Quality Indicators has been added to the ISD entity document. | Data interface correction | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-658 | ME |  | 2023-09-12 | Design Team |  | Miriam Ellis | Programme Design | Updates to ERI011B | Following an internal review of the external ECS reports a few discrepancies have been highlighted that need to be amended |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Changes to ECS External Reports 1. MHHS-REP-006: Block R051 Demand Disconnection Event Details - parent updated to R032 2. Data Catalogue: Format of DI-492, 496, 487, 488, 484 updated to reflect MHHS Data Type | Design Ambiguous | Supporting Docs | Various documents | ECS Reports
MHHS-DIN-659 | RG |  | 2023-09-12 | Design Team |  | Rob Golding | Programme Design | Update REP007 | Update REP007 to include blocks R007 |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update REP007 to include blocks R007 | Design Ambiguous | Supporting Docs | Various documents | Swagger 1.5
MHHS-DIN-660 | ME |  | 2023-09-12 | St Clements | 4513 | Vicki Holland | Software Provider | Supplier version of REP-002 | St Clements are requesting for one report per supplier MPID that covers all combinations of distributor and GSP group. The current solution for REP-002 is a supplier will receive a report per distributor id |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | REP002 has been split into two separate reports. There is now a Supplier version (MHHS-REP-002) and an LDSO Version (MHHS-REP-002B). Due to this change the MDS BPM/BPD (019) and DDE BPM/BPD (013) have also been updated to include the reference of REP-002B | Reporting correction | Supporting Docs | Various documents | MHHSP - ERI011B - ECS Reports - External v5.4 BP013 Demand Disconnection BPM/BPD v5.1 BP019 Market-wide Data Service BPM/BPD v5.1
MHHS-DIN-661 | RG |  | 2023-09-13 | IMSERV |  | Liam Lowey | Software Provider | Use of the term 'GUID' in messages | Messages are referring to "Device ID" data items as "GUID". For example "GPFGasGUID" in IF-004. However, a Device ID is not a GUID which is 128 bit number with a specific format. The Wikipedia article for GUID gives more information. Instead, Device IDs are 64 bit. This is misleading to implementors and maintainers. Could the naming of the properties be changed to reflect the identifier better? For example this appears to be a collection of 8 bytes in hexidecimal, i.e. a 64-bit quantity or 8 octets. Much like a MAC address or EUI64 for DCC is. Do you have other identifiers like this that require definition could we standardise on a different name for all of them? |  | Closed | [5 empty] | No further action taken
MHHS-DIN-662 | SW |  | 2023-09-14 | Design Team |  | Steve Weston | Programme Design | Update Sort Code and Account Number validation | DT-035-Sortcode and DT-035-Bank Acount Number have incorrect min / max Lengths. Sort Code should be min 6, max 8 with a regex applied for validation. Account number should be min 8 and max 10, with a regex for extra validation |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | DT-035-Sortcode and DT-035-Bank Acount Number have incorrect min / max Lengths. Sort Code should be min 6, max 8 with a regex applied for validation. Account number should be min 8 and max 10, with a regex for extra validation. This needs to be updated in ER011B and Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-ERI011B- ECS Reports
MHHS-DIN-663 | SW |  | 2023-09-14 | Design Team |  | Steve Weston | Programme Design | There are missing regular expressions that would improve the swagger schema validation | There are various data types that would benefit from regex added to improve validation. In addition, there could be new data types created / regex added to improve consistency and validation. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | There are various data types that would benefit from regex added to improve validation. In addition, there could be new data types created / regex added to improve consistency and validation. This needs to be updated in Swagger 1.5. The proposed regexes are for the following data types/items: DT-002 MPAN - DT-026 Group Correction Factor DT-027 MPID | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-664 | SC |  | 2023-09-14 | St Clements |  | Sean Cooper | SRO Design | Message [Error] Status Message Addressing | Based on feedback from SCS review the Message Status section of E2E to make it clearer that the "Sender ID is system sending the error, so if MPRS was sending an error it would be the REG DIP ID And Recipient ID would be who you are sending the error to – so would be the S1.senderDIPID on the original message" |  | Closed | Design ambiguous | N/A |  |  |  | Clarified with SCS | Design Ambiguous | Supporting Docs | Supporting document | E2E001 - E2E Architecture Doc
MHHS-DIN-665 | SC |  | 2023-09-14 | St Clements |  | Sean Cooper | Programme Design | Tidy up Of "where available in Registration" usage | IF-001 / IF-002 /IF-036 Block 5 - Block 5 & IF-003 Blocks 095/096 & IF-033 Block 072 & IF-037 Block 10 and 11 heading had a note refering to Interface notes section which explained that block info may not always be availible. This was inconsistant with all other blocks which use the phrasing "Where Availible in the Regisration Service".... Block 5 updated to be consistant. IF Notes on each of these IF remain unaffected. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | IF-001 / IF-002 /IF-036 Block 5 - Block 5 & IF-003 Blocks 095/096 & IF-033 Block 072 & IF-037 Block 10 and 11 heading had a note refering to Interface notes section which explained that block info may not always be availible. This was inconsistant with all other blocks which use the phrasing "Where Availible in the Regisration Service".... Block 5 updated to be consistant. IF Notes on each of these IF remain unaffected. | Data interface correction | Supporting Docs | Interfaces | DES138 - Interface Doc
MHHS-DIN-666 | SW |  | 2023-09-15 | Design Team |  | Steve Weston | Programme Design | Data Type / Data Type Reference inconsistencies in DES-138. | Fix any IR5 Data Type / Data Type Reference inconsistencies between DES-138 & Swagger (between Data Catalogue Tab and IF / Common tabs) |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Fix any IR5 Data Type / Data Type Reference inconsistencies between DES-138 & Swagger (between Data Catalogue Tab and IF / Common tabs). Data Type Inconsistencies - DES-138 updates DI-000 is defined as a String 8, but in IF-040 and IF-045 this is defined as a String 6, so DES-138 has been updated to align. DI-019 is defined as a string 50 in IF-032, but in IF-034 and 36, is defined as String 10. In IF-035 this is blank. Updated IF-034, 35 and 36 so that DI-019 is a String 50. Swagger updated to align. DI-020 is defined as a string 50 in IF-032, but in IF-034 and 36, is defined as String 10. In IF-035 this is blank. Updated IF-034, 35 and 36 so that DI-020 is a String 50. Swagger updated to align. IF-023, B029, DI-026, DES-138 updated so Data Type is DT-003 to align with Swagger. IF-023, B035, DI-038, DES-138 updated so Data Type is DT-002 to align with Swagger. IF-023, B053, DI-041, DES-138 updated so Data Type is DT-016N to align with Swagger. IF-023, B053, DI-042, DES-138 updated so Data Type is DT-016N to align with Swagger. IF-023, B053, DI-044, DES-138 updated so Data Type is DT-016N to align with Swagger. IF-023, B053, DI-045, DES-138 updated so Data Type is DT-016N to align with Swagger. IF-033, B037, DI-075, DES-138 updated so Data Type is DT-002N to align with Swagger. IF-033, B037, DI-079, DES-138 updated so Data Type is DT-002N to align with Swagger. IF-050, B080, DI-111, DES-138 updated so Data Type is DT-003N to align with Swagger. IF-051, B080, DI-111, DES-138 updated so Data Type is DT-003N to align with Swagger. IF-050, B080, DI-112, DES-138 updated so Data Type is DT-003N to align with Swagger. IF-051, B080, DI-112, DES-138 updated so Data Type is DT-003N to align with Swagger. IF-014, B047, DI-147, DES-138 updated so Data Type is DT-016 to align with Swagger. IF-013, B049, DI-159, DES-138 updated so Data Type is DT-003 to align with Swagger. IF-003, B094, DI-159, DES-500 updated so Data Type is DT-003 to align with Swagger. IF-003, B008, DI-159, DES-813 updated so Data Type is DT-006 to align with Swagger. IF-003, B009, DI-159, DES-816 updated so Data Type is DT-006 to align with Swagger. DIP Common, D0, DI-986 removed Data Type from DES-138 and Swagger. Data Type Inconsistencies – Swagger updates IF-036, B068, DI-018 Swagger updated so Data Type is DT003N to align with DES-138. IF-051, B082, DI-023 Swagger updated so Data Type is DT003N to align with DES-138. IF-038, B021, DI-138, Swagger updated so Data Type is DT-006 to align with DES-138. IF-039, B021, DI-138, Swagger updated so Data Type is DT-006 to align with DES-138. IF-001, B006, DI-139, Swagger updated so Data Type is DT-006 to align with DES-138. IF-038, B020, DI-140, Swagger updated so Data Type is DT-006 to align with DES-138. IF-039, B020, DI-140, Swagger updated so Data Type is DT-006 to align with DES-138. IF-024, B058, DI-152, Swagger updated so Data Type is DT-016 to align with DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-667 | SW |  | 2023-09-16 | Design Team |  | Steve Weston | Programme Design | Mandatory / Optional blocks inconsistencies between DES-138 & Swagger | Fix any IR5 Mandatory / Optional blocks inconsistencies between DES-138 & Swagger |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Fix any IR5 Mandatory / Optional blocks inconsistencies between DES-138 & Swagger. Mandatory / Optional / Nullable Inconsistencies DIP Common, S1, DI-985 is Optional in Swagger and has been updated to be Mandatory to align with DES-138. DIP Common, S1, DI-996 is Optional in Swagger and has been updated to be Mandatory to align with DES-138. IF-013, B049, DI-161 is Optional in Swagger and has been updated to be Mandatory to align with DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-668 | SW |  | 2023-09-17 | Design Team |  | Steve Weston | Programme Design | Nullable / Optional Data Type / property inconsistencies between DES-138 & Swagger | Fix any IR5 Nullable / Optional Data Type / property inconsistencies between DES-138 & Swagger |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Fix any IR5 Nullable / Optional Data Type / property inconsistencies between DES-138 & Swagger. Nullable / No nulls Inconsistencies DI-988 is nullable in DES-138 but no nulls in Swagger, so Swagger to be updated so it is nullable to align with DES-138. DI-123 is nullable in DES-138 but no nulls in Swagger, so Swagger to be updated so it is nullable to align with DES-138. DI-150 is nullable in Swagger, to be updated in Swagger so this is Mandatory no nulls to align with DES-138. DI-018, update DES-138 so value is Mandatory nullable to align with Swagger. DI-138, update DES-138 so value is Mandatory nullable to align with Swagger. DI-023, DI-026 update DES-138 so value is Mandatory nullable to align with Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-669 | SW |  | 2023-09-18 | Design Team |  | Steve Weston | Programme Design | Min / Max Values inconsistencies between DES-138 & Swagger | Fix any IR5 Min / Max Values inconsistencies between DES-138 & Swagger |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Fix any IR5 Min / Max Values inconsistencies between DES-138 & Swagger. Min / Max Inconsistencies DI-019 update Swagger max length to be 50 to align with DES-138 DI-218 update Swagger to align with DES-138 min / max values. DI-300 update Swagger to align with DES-138 min / max values. DI-081 update DES-138 to have a max of 30 to align with Swagger. DI-091 update DES-138 to have a max of 9 to align with Swagger. DI-152 update DES-138 to have a max length of 13 to align with Swagger. DI-161 update DES-138 to align with Swagger value of 9999999. DI-167 update DES-138 to align with Swagger min / max values. DI-168 update DES-138 to align with Swagger min / max values. DI-190 update DES-138 to align with Swagger max value of 50. DI-194 update DES-138 to align with Swagger max value of 50. DI-990 update DES-138 to align with Swagger max value of 65. DI-992 update DES-138 to align with Swagger max value of 10. DI-081 update DES-138 to have a min of 30 to align with Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-670 | SW |  | 2023-09-15 | Design Team |  | Steve Weston | Programme Design | Unclear whether webhook URL's accept ports | Need to make it clearer in E2E design and Swagger whether port numbers are allowed in webhook / URLs and any formatting / options for environments |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Need to make it clearer in E2E design and Swagger whether port numbers are allowed in webhook / URLs and any formatting / options for environments E2E001 Section 4.5 updated | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 E2E001
MHHS-DIN-671 | ME |  | 2023-09-22 | Elexon | 11203 | Rashmi Radhakrishnan | Central Body | Updates to ISD Entities | 1. Make it clear what the data type/length is for Line Loss Factor Identifier. It is currently unclear as it reads 3 characters 2. Following consultation feedback of BSCP707, ISD Entity 23 requires an update to include the word 'Duration' and update to the character length and inclusion of date format |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | 1. Update to ISD Entity M3 - update the length/data type of Line Loss Factor Identifier. Now reads as Up to 3 characters 2. Update to ISD Entity 23 - include the word 'Duration' to Settlement Period. This now reads Settlement Period Duration (Description). Update the data type/length to 50 characters and include a date format of YYYY-MM-DD | Design Ambiguous | Supporting Docs | EDI021 ISD Entities | MHHSP_EDII021_ISD_Entites 5.3
MHHS-DIN-672 | SW |  | 2023-09-19 | Design Team |  | Steve Weston | Programme Design | B033 has 9 required fields, but only available. Naming is also inconsistent for some of the required fields that do not exist. | B033 has 9 required fields, but only 8 are available. Naming is also inconsistent for some of the required fields that do not exist. Swagger needs to be updated to align with available fields and DES-138 mandatory values. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Fix any values in Swagger than do not align with required fields and ensure number of required fields aligns with number of fields available. -metering point postcode removed from required fields in B033 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-673 | RG |  | 2023-09-21 | Design Team |  | Rob Golding | Programme Design | Floating Point number regexes | DIN 267 inadvertently updated regexes to a pattern which does not align to the agreed format as of Technical Design Working Group Work-Off Issue D-0408th November 2022. The regexes need to align to what was agreed. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Update regex patterns for the following data types: DT-016, DT-022, DT-023, DT-024, DT-025, DT-030, DT-031, DT-032, DT-033 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-674 | SW |  | 2023-09-22 | ESG | 11369 | Kerry O'Donnell | Software Provider | Inconsistent Text description for DI-086 | In the Data Catalogue, DI-086 has a Text Description of "Supplier Effective From Date" but on IF-001 and IF-037, DI-086 has a text description of "Incoming Supplier Effective From Date" |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | In the Data Catalogue, DI-086 has a Text Description of "Supplier Effective From Date" but on IF-001 and IF-037, DI-086 has a text description of "Incoming Supplier Effective From Date". IF-001, IF-037, IF-051 have been updated so that the text description for DI-086 now matches Data Catalogue and Swagger - "Supplier Effective From Date". | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue
MHHS-DIN-675 | SC |  | 2023-09-25 | Design Team |  | Sean Cooper | Programme Design | IF-021 IF Consistency Validation Rules | New IF-021 Validation Rules with supporting Error Codes created to ensure validity of IF-021. New Error codes are : ECS1015 - Estimation Reason Code Cannot be Null & ECS1016 - Consumption Amendment Reason Codes Cannot be Null |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | New IF-021 Validation Rules with supporting Error Codes created to ensure validity of IF-021. New Error codes are : ECS1015 - Estimation Reason Code Cannot be Null & ECS1016 - Consumption Amendment Reason Codes Cannot be Null | Missing/incorrect validation rule | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue
MHHS-DIN-676 | RS |  | 2023-09-25 | St Clements | 11291 | Rob Golding | SRO Design | CR-018 NFR Change - E2E1009 | There are some NFRs that need tweaking post CR-018 Approval to align with the Registration Service Operating hours - Ie E2E1009. Given that MPRS sits behind an Adapter and does not operate 24/7 (as per CR-018) level 4 processing will operate in the same timeframes as Level 5. It needs tweaking to align with the CR-018 wording of: DIP messages received by the SMRS will be processed between the hours of 05:00 to 18:00 and 21:00 to 23:00 Working Days only. Messages received outside of these hours will be held in a queue until the next processing window. Automated responses to inbound messages (including Level 4 Validation) are expected to be returned within 60 minutes of receipt during the specified operating hours. |  | Closed | Design ambiguous | DIP Users, DIP |  |  |  | This DIN is superceded by CR039.
MHHS-DIN-677 | MF |  | 2023-09-26 | Utiliteam |  | Mike Fensome | Programme Design | Additional information added to IF-020 for Linked MPANs | On linking MPAN's, information is missing in IF-020 ( as provided in IF-002 ) to allow participants to interpret the flow. This needs adding to IF-020. Swagger updated accordingly |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | Agreed with SCS, for Import / Export Events ONLY, to add in the blocks that are present in the IF-002 namely B035 Linked MPANs / B-036 Linked Meter Info / B-075 MAP Info to IF-020. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue Swagger 1.5
MHHS-DIN-678 | ME |  | 2023-09-27 | Elexon | 11684 | Rashmi Radhakrishnan | Central Body | ISD Entities Updates | 1. Entity M14- Master settlement time table Fields: LSS Run Date, Payment Date & Notification Date should be changed to an Optional field. 2. Entity M18- Inconsistencies between M16 field name “ DIP Role Code” and M18 Field name “DIP Market Role”. Two different Field name used. 3. Entity M9 and M10, it appears that the data type length specified in the ISD EDI021 document for Field Unit Description 1, 2, and Manufacturers Designation might not be sufficient based on the data samples. – Datatype/length of these fields needs increasing. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | 1. Entity M14- Master settlement time table Fields LSS Run Date, Payment Date, Notification Date all changed to Optional field. 2. DIP Role Code in Entity M16 updated to DIP Market Role 3. Entity M9 and M10, data type/length for Unit Description 1, 2, and Manufacturers Designation have been incresed to 100 characters | Design Ambiguous | Supporting Docs | EDI021 ISD Entities | MHHSP_EDII021_ISD_Entites
MHHS-DIN-679 | SC |  | 2023-09-27 | SRO Design |  | Sean Cooper | Elexon | MHHS Process for Additional BMU's Required | Clarification is required around how Additional BMU's will be requested, created and managed under MHHS |  | Closed | [5 empty] | Duplicate of MHHS-DIN-651 | No Change
MHHS-DIN-680 | ME |  | 2023-09-27 | St Clements | 11538 | Vicki Holland | Software Provider | Update to DI-322/DI-323 MHHS data type | The MHHS Data types for DI-322 and DI-323 requires an update to align with the SVA data catalogue as these 2 data items are reported to 9 decimal places. Swagger will also need to be updated to align with the ECS reports |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Updated MHHS data types and definitions for DI-322 and DI-323 within the ECS Data catalogue and where it appears in the reports. The Min and Max values have also been updated due to the change in data type. This change has been made in Swagger. Data types have been updated to a String 20(±9.9). | Reporting correction | Supporting Docs | ECS Reports Swagger REP003 version 010 | MHHSP - ERI011B - ECS Reports - External MHHSP - ERI011A - ECS Reports - Internal Swagger
MHHS-DIN-681 | SW |  | 2023-09-28 | ESG | 11492 | Kerry O'Donnell | Software Provider | DI-824 textual decsription in the Interfaces is inconsistent with the textual description in the Data Catalague | DI-824 textual description (Column D) in the Interfaces is inconsistent with the textual description (Column D) in the Data Catalogue. This DIN is to ensure the textual description is consistent in the Interfaces to the Data Catalogue and that found in Swagger. |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Textual description corrected on IF-036 to align with other interfaces | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-682 | MF |  | 2023-09-28 | CGI |  | Dave Webster | Data Service Provider | Remove commissioning flows sent to Data Service on BP009 | BP009 is misaligned with the Data Service requirements and incorrectly shows the Advanced Data Service receiving Commissioning Flows (D0383 and D0384) |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Removed commissioning flows sent to Data Service on BP009 (D0383 and D0384 into step 175). Note BPD was already correct. Updated BRS002 - MHHS-BR-MS-062 accordingly | Process Model correction | Supporting Docs | Process model correction Business requirements | BP009 BRS002
MHHS-DIN-683 | SW |  | 2023-09-28 | Flui | 11487 | Jason Jackson | Software Provider | E2E refers to T0 and Transaction Wrapper which are no longer required | E2E refers to T0 (section 4.8.2) and Transaction Wrapper (section 5.5) which are no longer required. This needs to be updated in the E2E design and an update provided in relation to Swagger and how this works. |  | Implemented |  |  |  | Interim Release 5 | 2023-09-20 | E2E001 updated to reflect replay design | Design Ambiguous | Supporting Docs | Interfaces | E2E001
MHHS-DIN-684 | ME |  | 2023-10-03 | SRO Design |  | Kevin Spencer | SRO Design | Addition of REP-003A | As part of the Tranche 1 Transition Design and following approval from DAG a new report has been included within ECS Reports, MHHS-REP-003A. The intention is to retain the existing data flows in transition for the non-migrated MPANs and send the new DIP Flows or DTN flows for the migrated MPAN. This is due to the change in the CCCids which have different characteristics in the new world. The ELEX-REP-003A has been developed such that the CCC totals across migrated and non-migrated MPANS can be presented. Suppliers with MPANs in both Legacy and MHHS can expect: D0296 – just legacy data – as now, pipe delimited dataflow received via the DTN REP-D0296 – just MHHS data – still a pipe delimited dataflow received via the DTN – will have a new Dxxxx identifier REP-003 – just MHHS data – a JSON message received via the DIP REP-003a – both legacy and MHHS data – a JSON message received via the DIP |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Inclusion of MHHS-REP-003A to the ECS reports. Swagger has been updated to align with ECS reports catalogue with new reports interface REP-003a and associated common block, custom block and data catalogue items as per reports catalogue. | Reporting correction | Supporting Docs | ECS Reports Swagger REP003A version 001 | MHHSP - ERI011B - ECS Reports - External Swagger
MHHS-DIN-685 | BK |  | 2023-10-04 | RECCo |  | Sarah Jones | Central Body | Data Item Names and Descriptions | As part of the interface tranche of MHHS code drafting, RECCo has reviewed the information contained within the MHHS Interface Catalogue (DES138) and the ECS Reporting Catalogue (ERI011B) and identified a number of areas where changes to the data item names and descriptions should be progressed in order that these better align to existing code terminology and data item descriptions. We have identified five areas where changes should be made. 1) In the MHHS data catalogue, a number of discrepancies have been identified where the data item name or description is slightly different to the Energy Market Data Specification. In response to this we are either proposing to: a. amend the existing Energy Market Data Specification data item name and / or description via the MHHS code drafting work, or b. change to the data item name and / description in the MHHS data catalogue. 2) We have identified MHHS data items with the same name as existing data items, but a different data format. In particular, data items used to define effective from dates have been established for MHHS as a high resolution datetime data type. To avoid ambiguity / confusion for users, we are proposing to amend the data item description for MHHS date related data items to reflect that they are recording a data and time. 3) The data item used to link to CSS registration activity has been incorrectly referenced as the CSS Registration Request Id. This should be amended to the CSS Registration Id (DI90043) to avoid confusion with the CSS Registration Request Id which is a separate data item (DI90050). 4) The data item (MHHS DI-048) used to identify the meter manufacturer has been established with a different name and description from the existing data item (J0410). This should be amended to the Manufacturers Make and Type to avoid confusion. (Alternatively, if this is expected to be an entirely new data item, then the reference to J0410 should be removed and clarity provided on what data should be used to populate the field). 5) Correct minor typographical errors within the data item names and / or descriptions. | CR024 | Open - awaiting assessment | Change Request | All Participants |  | Post Go-live Release |  | 1) In the MHHS data catalogue, a number of discrepancies have been identified where the data item name or description is slightly different to the Energy Market Data Specification. In response to this we are either proposing to: a. amend the existing Energy Market Data Specification data item name and / or description via the MHHS code drafting work, or b. change to the data item name and / description in the MHHS data catalogue. 2) We have identified MHHS data items with the same name as existing data items, but a different data format. In particular, data items used to define effective from dates have been established for MHHS as a high resolution datetime data type. To avoid ambiguity / confusion for users, we are proposing to amend the data item description for MHHS date related data items to reflect that they are recording a data and time. 3) The data item used to link to CSS registration activity has been incorrectly referenced as the CSS Registration Request Id. This should be amended to the CSS Registration Id (DI90043) to avoid confusion with the CSS Registration Request Id which is a separate data item (DI90050). 4) The data item (MHHS DI-048) used to identify the meter manufacturer has been established with a different name and description from the existing data item (J0410). This should be amended to the Manufacturers Make and Type to avoid confusion. (Alternatively, if this is expected to be an entirely new data item, then the reference to J0410 should be removed and clarity provided on what data should be used to populate the field). 5) Correct minor typographical errors within the data item names and / or descriptions. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger ECS Reports
MHHS-DIN-686 | BK |  | 2023-10-04 | RECCo |  | Sarah Jones | Central Body | DIP Interface Name Changes | As part of the interface tranche of MHHS code drafting, RECCo has reviewed the information contained within the MHHS Interface Catalogue (DES138) and identified a number of areas where changes to the DIP interface names should be progressed in order that these better align to enduring code terminology. In order to translate the MHHS interface catalogue (in the DES138) into the Energy Market Data Specification, RECCo is seeking to align MHHS interface names to enduring code terminology to avoid future inconsistencies. To meet this aim, we have identified four areas where changes should be made. 1) Removal of references to Metering Service within the interface name. Existing terminology will be retained e.g. MEM in the REC and MOA in the BSC. 2) Replacement of references to Service Providers with Supplier Agents within the interface name, Existing terminology will be retained with Data Services and Metering Services defined as Supplier Agents in both the BSC and REC. 3) Replacement of references to Registration / Registration Service with SMRS. To differentiate from the CSS and ERDS, following agreement with BSCCo that DIP interfaces fall under the scope of the SMRS. 4) Replacement of references to CSS De-Registration with CSS Registration De-Activation to reflect REC code terminology. | CR025 | Open - awaiting assessment | Change Request | All Participants |  | Post Go-live Release |  | 1) Removal of references to Metering Service within the interface name. Existing terminology will be retained e.g. MEM in the REC and MOA in the BSC. 2) Replacement of references to Service Providers with Supplier Agents within the interface name, Existing terminology will be retained with Data Services and Metering Services defined as Supplier Agents in both the BSC and REC. 3) Replacement of references to Registration / Registration Service with SMRS. To differentiate from the CSS and ERDS, following agreement with BSCCo that DIP interfaces fall under the scope of the SMRS. 4) Replacement of references to CSS De-Registration with CSS Registration De-Activation to reflect REC code terminology. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-687 | ZH |  | 2023-10-04 | SI Design |  | Zakir Hussain | SI Design | BP003 updates are missing on BPD003 | For DIN-608 changes there were new steps added to the diagram, these have not been covered in the relevant BPD doc. This includes the new steps being referenced, descriptions, flows etc. |  | Initial Assessment/Updating | Error/Correction | N/A |  | Post Go-live Release | 0 | Add missing BP003 updates to BPD003 | Process Model correction | Supporting Docs | Business Process Description | BPD003
MHHS-DIN-688 | ZH |  | 2023-10-04 | SI Design |  | Zakir Hussain | SI Design | BP010E updates are not included in BPD10 | BP10E has not been included in the relevant BPD10 doc. |  | Initial Assessment/Updating | Error/Correction | N/A |  | Post Go-live Release | 0 | BP010E updates are not included in BPD010 | Process Model correction | Supporting Docs | Business Process Description | BPD010
MHHS-DIN-689 | RG |  | 2023-10-05 | SRO Design |  | Rob Golding | SRO Design | Minor updates to DES138/Swagger for Sims& Ems audit | Minor differences between DES138 & swagger from sims & ems audit |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Incorporate differences between DES138 & swagger from sims & ems audit | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-690 | SC |  | 2023-10-09 | SRO Design |  | Sean Cooper | SRO Design | IF Optionality Matrix - MDR | Updated MDR IF Optionality Matrix to reflect correct values per current CR23 Design. Existing Values were not correct |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Updated MDR IF Optionality Matrix to reflect correct values per current CR23 Design. Existing Values were not correct for MDS | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-691 | SC |  | 2023-10-06 | SRO Design |  | Sean Cooper | SRO Design | DI-138 / DI-140 Customer Direct Contract Holder(s) | DI-138 / DI-140 Customer Direct Contract Holder(s) - Changed to Data Type DT006N in DES138 to correctly align with Swagger |  | Implemented |  |  |  | Interim Release 5.1 | 0 | DI-138 / DI-140 Customer Direct Contract Holder(s) - Changed to Data Type DT006N in DES138 to correctly align with Swagger | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-692 | SC |  | 2023-10-06 | SRO Design |  | Sean Cooper | SRO Design | DI-161 Settlement Run Number | DI-161 Settlement Run Number - made mandatory in IF-013 to correctly align with Swagger |  | Implemented |  |  |  | Interim Release 5.1 | 0 | DI-161 Settlement Run Number - made mandatory in IF-013 to correctly align with Swagger | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-693 | SC |  | 2023-10-06 | SRO Design |  | Sean Cooper | SRO Design | DI838 Supplier Nominated Consent | DI838 Supplier Nominated Consent - DES138 Updated to show as Nullable (Swagger already aligned) |  | Implemented |  |  |  | Interim Release 5.1 | 0 | DI838 Supplier Nominated Consent - DES138 Updated to show as Nullable (Swagger already aligned) | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-694 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | Update IF-007-EnergisationStatusChange event code | Update event code [EnergisationStatusFailure] to [EnergisationStatusChange] for IF-007-EnergisationStatusChange |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Update event code [EnergisationStatusFailure] to [EnergisationStatusChange] for IF-007-EnergisationStatusChange | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-695 | SC |  | 2023-10-06 | SRO Design |  | Sean Cooper | SRO Design | IF Optionality Grid - LDSO | LDSO IF Optionality - PUB-009 Corrected from NonApplicable to Optional = YES PUB-013 Corrected from NonApplicable to Optional = YES PUB-026 SSCProfileClass Corrected from N/A to Optional = YES PUB-040 Corrected from N/A to Optional = YES REGS: PUB019 Related MPAN Events corrected from N/A to Optional = No |  | Implemented |  |  |  | Interim Release 5.1 | 0 | LDSO IF Optionality - PUB-009 Corrected from NonApplicable to Optional = YES PUB-013 Corrected from NonApplicable to Optional = YES PUB-026 SSCProfileClass Corrected from N/A to Optional = YES PUB-040 Corrected from N/A to Optional = YES REGS: PUB019 Related MPAN Events corrected from N/A to Optional = No | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-696 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | IF-018 mandatory blocks for Energy Direction & NUM Indicatory | Add B023 is required for IF-018-EnergyDirection and IF-018-MUMIndicator |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Add B023 in IF-018-EnergyDirection and IF-018-MUMIndicator | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-697 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | Add required fields to IF-023 | Add required field to custom block in IF-023 |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Add required field to custom block in IF-023 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-698 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | Add required field to IF-040 | Add B059 to required field in IF-040 |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Add B059 to required field in IF-040 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-699 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | IF-036 DSAppActive optional B068 block | Remove B068 from required fields for IF-036 DSAppActive |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Remove B068 from required fields for IF-036 DSAppActive | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-700 | RG |  | 2023-10-09 | SRO Design |  | Rob Golding | SRO Design | Recipient ID specified twice in replay/requeue API | Remove recipient id from request body of API call as already specified on path |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Remove recipient id from request body (in the MessageRequest object) of API call as already specified on path. This applies to replay and requeue API endpoints. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-701 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarification on population of IF-036 | Clarification on population of IF-036 participant ID's |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Provided clarification on IF-036 Interface notes on how B005, B016 and B017 are populated by Registration Service | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-702 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarification on use of calendar days for validation rules in IF-025 and IF-034 | Update validation rules to clarify that days refer to calendar days in IF-025 and IF-034 |  | Implemented |  |  |  | Interim Release 5.1 | 0 | IF-025 and IF-034 validation rules updated to clarify using calendar days | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-703 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarify that B032 is only sent where available in Registration Service | Clarify that B032 is only sent where available in Registration Service in IF-001, IF-002, IF-033 and IF-036 |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Updated B032 to show as sent where available in Registration Service in IF-001, IF-002, IF-033 and IF-036 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-704 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Updated DI-135 and DI-136 to be set to Mandatory in IF-025/IF-026 | Update DI-135 and DI-136 to be set to Mandatory in IF-025/IF-026 and to be non-nullable, so that a date is always provided for SMSO and IHD even where setting the value to null. |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Updated DI-135 and DI-136 to be set to Mandatory in IF-025/IF-026 and to be non-nullable | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-705 | MF | DI-214 | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarify that sending of [IMS-SendMTD] event code on IF-035 should also apply in the case of SEG | Clarified that SEG scenario applies for requirement MHHS-BR-RS-019 to send [IMS-SendMTD] event code on IF-035 |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Added that SEG scenario applies for requirement MHHS-BR-RS-019 to send [IMS-SendMTD] event code on IF-035 in BRS003 | Requirement correction | Supporting Docs | Business Requirements | BRS003
MHHS-DIN-706 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Remove Unmetered check for de-linking Linked Export MPANs (IF-019) | Clarified that Unmetered check will not apply for [LinkedImportExportRemove] event in IF-019 |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Updated validation rules so that Unmetered check will not apply for [LinkedImportExportRemove] event in IF-019. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-707 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarification on Primary routing for IF-033 | Updated IF-033 to show primary routing is to XMSP and XDSP |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Updated IF-033 to show primary routing is to XMSP and XDSP | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-708 | RG |  | 2023-10-09 | SRO Design |  | Rob Golding | SRO Design | IF-004 B093 block is mandatory | Audit of swagger IF-004 B093 block is mandatory |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Update IF-004 B093 block to mandatory | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-709 | RG |  | 2023-10-09 | SRO Design |  | Rob Golding | SRO Design | IF-021 and IF-014 custom block differences | IF-021/14 have different structure, ideally they should be the same - the B045 block does not need to be an array |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Aligned IF-014 to IF-021 so that multiple B045 blocks are not allowed | Data interface correction | Supporting Docs | Interfaces IF-014 version 010 | DES138, Swagger 1.6
MHHS-DIN-710 | RG |  | 2023-10-09 | SRO Design |  | Rob Golding | SRO Design | IF-016 requires update to include IF-013 variant | IF-016 definition needs to include replayed IF-013 data. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | At present in DES-138 only the IF-021/14 variants are described in the IF-016 data, this needs to be extended to include the IF-013 variant. This change has been to be reflected in the Swagger. Added validation rules and response codes to IF-015 to be included in IF-016. | Data interface correction | Supporting Docs | Interfaces IF-015 version 010, IF-016 version 010 | DES138, Swagger 1.6
MHHS-DIN-711 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | IF-035 Obsfucation/routing contradiction | IF035 – MDS & LDSO are mentioned in the obfuscation column, however, there is no routing rule for these roles |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Removed LDSO and MDS from obsfuscation rules as LDSO/MDS do not receive IF-035 | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-712 | MF | DI-181 | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | De-appointment and re-appointment date order | Set de-appointment and re-appointment dates to D and D+1 for requirements RS-128.7 and RS-128.8 for Data Service appointments to align with DIN-383 (Metering Service appointments) |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Discussed with SCS and agreed to update Registration Service requirements to De-appoint on D (MHHS-BR-RS-128.7) and appoint on D+1 (MHHS-BR-RS-128.8) as part of auto-alignment process | Requirement correction | Supporting Docs | Business Requirements | BRS003
MHHS-DIN-713 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | Rel 1.2.1 S1 updates in swagger | SenderRoleId & SenderTimestamp updated in required section in S1 object to fix problem introduced in v1.2 |  | Implemented |  |  |  | Interim Release 2.1 | 0 | Update sentTimestamp to senderTimestamp, senderRole to senderRoleID in S1 block | Data interface correction | Supporting Docs | Various documents | DES-138 Interface Catalogue Swagger 1.2.1
MHHS-DIN-714 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | Rel 1.2.1. B033 updates in swagger | Remove meteringPointPostcode from required section of B033 object |  | Implemented |  |  |  | Interim Release 2.1 | 0 | Update B033 remove meteringPointPostCode from B033 | Data interface correction | Supporting Docs | Various documents | DES-138 Interface Catalogue Swagger 1.2.1
MHHS-DIN-715 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | Rel 1.2.1. D091 update | DI-091 update maximum: 1->9, minimum 1->0 |  | Implemented |  |  |  | Interim Release 2.1 | 0 | Update DI-091-Number-Of-Displayed-Digits to maximum 9 and minimum 0 in the Swagger. Including updates to 01-Data Catalogue, IF-002, IF-005, IF-006, IF-033 in the Interface Catalogue to align with Swagger. | Data interface correction | Supporting Docs | Various documents | DES-138 Interface Catalogue Swagger 1.2.1
MHHS-DIN-716 | ME |  | 2023-10-10 | Elexon | 13809 | Rashmi Radhakrishnan | Central Body | Update to ISD entity 23 | Additional text provided within the Settlement Period Duration (Description) field requires removal as the correct text has been added |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Desription within Settlement Period Duration (Description) has been updated. The reference for a Settlement period, unique within Settlement Date. Periods ID s are assigned sequentially to each period in local time day The duration of a Settlement Period in minutes | Design Ambiguous | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-717 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | LSS needs to be removed from the obsfucation column in DES138 - IF001 | LSS does not recieve IF-001 and therefore should not referenced in the obsfucation column |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Removed LSS from obsfucation rules in IF-001 as only issued to MDS which is already covered by obsfucation | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-718 | ME |  | 2023-10-11 | Elexon | 14165 | Derek Weavering | SRO Design | MHHS-Rep-D0296 alignment with Ddddd Supplier BM Report | A review of the DAG approved MHHS-DEL1613 DES-196 D-Flow and Interface Mapping Supplementary Documents has identified the following: The current Supplier BM Unit Report (D0296) considers all the GSPs that the supplier operates in a single file). However the Ddddd specs in the ECS catalogue and D flow documentation suggest a single file for each supplier’s GSP. We are building ( within Helix) using the current approach where all GSPs appear in the same file. Please can this be raised with the team to ensure the specs also reflect the same |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | MHHS-REP-D0296 has been updated to align with the Ddddd Supplier BM Report. The following link: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx has also been included to the following reports (D0081, D0266, D0276 and D0296) to direct participants to what should be used as the Master version of each report as defined in DTC format. | Reporting correction | Supporting Docs | ERI011B ECS Reports-External | ERI011B ECS Reports-External
MHHS-DIN-719 | MF |  | 2023-10-11 | Utiliteam |  | Mike Fensome | SRO Design | Update to DI-103 Configurable Register Id to min length of 1, max length of 2 | Allow Configurable Register ID's (DI-103) to be provided with min length of 1 and max length of 2 in both swagger and DES138 so that, for example, either 1 or 01 are accepted. |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Updated Data Catalogue for DI-103 (Configurable Register ID) to Min length of 1 (from 2) and updated Swagger accordingly. Added REGEX to Swagger. Regex takes the form ^\d{1,2}$ | Data interface correction | Supporting Docs | Interfaces | DES138, Swagger
MHHS-DIN-720 | MF |  | 2023-10-11 | Utiliteam |  | Mike Fensome | SRO Design | Update to DI-122 Profile Class to min length of 1, max length of 2 | Allow Profile Class (DI-122) to be provided with min length of 1 and max length of 2 in both swagger and DES138 so that, for example, either 1 or 01 are accepted. |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Updated Data Catalogue for DI-122 (Profile Class) to Min length of 1 (from 2) and updated Swagger accordingly. Added REGEX to Swagger. Regex takes the form ^\d{1,2}$ | Data interface correction | Supporting Docs | Interfaces | DES138, Swagger
MHHS-DIN-721 | JW |  | 2023-10-11 | Migration Design |  | John Wiggins | Programme | Control needed with MPID's associated to a metering role | For a metering company, only one limited company can ever own an MPID related to one of the three metering roles. Elexon need a control to say that an MPID associated to a metering role can never be owned by more than one company |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Updated ISD Entity 45 with the following comment "Where an MPID is related to the following Market Roles: Meter Operator, Advanced MOA or Smart MOA, the MPID and Market Role combinations must always be assigned to the same Company ID." | Missing/incorrect validation rule | Supporting Docs | ISD Entities | ISD Entities
MHHS-DIN-722 | RG |  | 2023-10-12 | SRO |  | Rob Golding | SRO Design | Remove Recipient Roles from A0.always object. | Remove Recipient Roles from A0.always object as roles are always resolved to DIP Ids |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Update Swagger to remove Recipient Roles from A0.always | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-723 | RG |  | 2023-10-12 | SRO |  | Rob Golding | SRO Design | OffPeakDeclarationProportion spelt on B097 spelt incorrect | OffPeakDeclarationProportion spelt 'OffPeakDeclatationProportion' on B097. |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Updated spelling in Swagger so that 'OffPeakDeclarationProportion spelt 'OffPeakDeclatationProportion' on B097. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-724 | RG |  | 2023-10-12 | SRO |  | Rob Golding | SRO Design | DT-000 Interface ID to include REP-002A & IF-004 | DT-000 Interface ID to include REP-002B & IF-004 as they are missing |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Add REP-002B & IF-004 to the enumerated list for DT-000 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-725 | RG |  | 2023-10-12 | SRO |  | Rob Golding | SRO Design | Add individual interface endpoints into the swagger | Add individual interface endpoints into the swagger as this would improve schema validation and better error messaging |  | Closed | [5 empty] | Following a review with the DIP Provider, these changes will not be made in Swagger and error handling will remain as per the IR5 design. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.7
MHHS-DIN-726 | ME |  | 2023-10-13 | SRO | 14120 | Miriam Ellis | SRO Design | DataType/Example errors in ECS reports data catalogue | A number of errors have been highlighted by Elexon following a review of the updated ECS data catalogue V5.4. There are errors that require an update |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Updates to data types and examples for a number of data items have been made within the data catalogue as well as where the data items appear in each of the documented reports | Reporting correction | Supporting Docs | ER1011B ECS Reports External ER1011A ECS Reports Internal | ER1011B ECS Reports External ER1011A ECS Reports Internal
MHHS-DIN-727 | MF |  | 2023-10-13 | SRO |  | Mike Fensome | SRO Design | Add new routing path for IF-041 | Added routing to give Data Service ability to send on-site read to Supplier |  | Implemented |  |  |  | Interim Release 5.1 | 0 | Added [ReadingOnSite] to routing table for Data Service in IF-041 |  |  |  | DES138
MHHS-DIN-728 | ME |  | 2023-10-17 | SJW | 13832 | Sarah Jones | Consultancy | DES138 and ECS Reports misalignment | As part of our work developing the interface code drafting, we have noticed that the S0 Block in the interfaces defined in the DES138 differ from those in the ECS Reporting Catalogue. Specifically, the DES138 includes Schema Version in the S0 block and the ECS Reporting Catalogue does not. Our expectation was that blocks would be identical across the various interfaces. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | All new MHHS ECS reports now includes Schema Version in the S0 blocks. | Reporting correction | Supporting Docs | ERBI011B ECS Reports - External | ERBI011B ECS Reports - External
MHHS-DIN-729 | SW |  | 2023-10-17 | SI Design |  | Steve Weston | SI Design | DI-838 to include null on the enum values | DI-838 in Swagger is mandatory nullable and this is an enumerated list so needs to include null in the enumeration to ensure this aligns to DES_138. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Updated Swagger DI-838 to ensure that null is a value in the enumerated list given this is a mandatory nullable field so that this now aligns to DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.6
MHHS-DIN-730 | ME |  | 2023-10-17 | Elexon | 13443 | Rashmi Radhakrishnan | Central Body | Update to Company name in Entity 1 | Within Entity 1 of ISD Entities - Market Participant ID there is a character limit of 100 for Registered Company Name but this is not sufficient and require this to be updated to allow up to 160 characters to align with company house. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | The character limit for Registered company name within Entity 1 of ISD Entities document has been increased to 160 | Design Ambiguous | Supporting Docs | ISD Entities | ISD Entities
MHHS-DIN-731 | RG |  | 2023-10-18 | Elexon |  | Nigel Rees | Central Body | Swagger does not resolve ECS reports | Since the ECS reports are now compressed in DIP messages the ECS report strcutre is not resolved in the swagger. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Added a field to each ECS payload that defines the structure of the corresponding report. This will be an optional item, hence not populated, however it will present the resolved structure of the report. | Design Ambiguous | Supporting Docs | Interfaces All REPs are now version 007 | Swagger 1.6, ER1011B ECS Reports External
MHHS-DIN-732 | RG |  | 2023-10-19 | SRO |  | Rob Golding | SRO | Routing update on IF-026 not updated | DIN-415 was meant to correct the routing on IF-026 - its still incorrect. The routing for event code [SSCandProfileClass] points to EES, LLS- this should be LSS. The header also needs to align - it currently states Central Settlements (MDS), it should be Central Settlements (LSS) |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Typo corrected LLS changed to LSS | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-733 | SC |  | 2023-10-19 | RECCO |  | Jonnny Moore | Recco | Update IF-026 Routing for Change of Consent | EES does not hold consent information - changed routing to remove EES as a receipient of Consent Info |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | EES does not hold consent information - changed routing to remove EES as a receipient of Consent Info in IF-026 | Design Ambiguous | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-734 | SC |  | 2023-10-19 | RECCO |  | Jonnny Moore | Recco | Update IF-018 Routing for Dom Premise Indicator | EES does not hold consent information - changed routing to remove EES as a receipient of DPI Info |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | EES gets DPI information from CSS - changed routing to remove EES as a receipient of DPI Info in IF-018 | Design Ambiguous | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-735 | MF |  | 2023-10-19 | Drax |  | Georgina Mahoney | Drax | Remove referene to BP007 as input into BP002 and BP003 | Disconnections is not an input into Change of Service Provider, BP007 should be removed from the entry processes. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Removed BP007 as an entry process to BP002 and BP003. De-appointment of Service Providers is covered in BP007. | Process Model correction | Supporting Docs | Process model correction | BP002 BP003
MHHS-DIN-736 | ZH |  | 2023-10-19 | SI Design |  | Zakir Hussain | SI Design | Removing step 36 from BP003 | Step 36 was included initially as part of an earlier DIN but is no longer relevant and therefore needs replacing. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Remove Step 36 and flow from BP003, including any reference to the step in the latest BPD3 Doc | Process Model correction | Supporting Docs | Process model correction | BP003 and BPD003
MHHS-DIN-737 | RS |  | 2023-10-19 | ESG |  | Patricia Parker | Software Provider | Custom Block: B022, Field: Metering Point Postcode min length in Swagger | Interface Catalogue specifies no min length, but min length of 6 specified in Swagger. Min length should be 5 for areas such as Liverpool |  | Closed
MHHS-DIN-738 | SC |  | 2023-10-19 | St Clements |  | Sean | SRO Design | Update Schema Version Data Item DI-992 Length | Interfaces across DES-138 need updating to show Schema Version DI-992 as String 10 rather than string 3 |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | DES-138 updated in individual interface to show Schema Version DI-992 as String 10 rather than string 3 | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-739 | SC |  | 2023-10-19 | St Clements |  | Sean | SRO Design | Validation of Supplier DIP ID / MPID for IF-035 [SDS-MDRUpdate] | Add validation in IF-034 to ensure that Supplier DIPID and MPID provided matches that of the current supplier held in the registration service - return new Error of REG1084 if this is not the case. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | Add validation in IF-034 to ensure that Supplier DIPID and MPID provided matches that of the current supplier held in the registration service - return new Error of REG1084 if this is not the case. | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-740 | SC |  | 2023-10-19 | St Clements |  | Sean | SRO Design | IF-018 Routing | DS added as a recipient of IF-018 [DCCEnrolment] |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | DS (XDSC) added as a recipient of IF-018 [DCCEnrolment] in the Secondary Routing | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-741 | MF |  | 2023-10-19 | St Clements |  | Mike | SRO Design | Clarification on end dating MDR functionality | Add clarification that the requirement to end date the MDR is fulfilled using existing CSS0200 functionality |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | MHHS-BR-RS-078.1 notes updated to clarify that this requirement is fulfilled using existing CSS0200 functionality | Requirement correction | Registration | Business Requirements | BRS003 Registration Service requirements
MHHS-DIN-742 | KH |  | 2023-10-23 | CGI | 13709 | Dave Webster | Software Provider | ADS and SDS Estimation Statements | As a result of DIN-589 which was to align the METH002 (ADS) with METH001 (SDS) method statements, the two documents are still misaligned. “Method 0: ADS processes Supplier provided ‘Agreed’ or ‘Override’ Readings” is the equivalent of “Method 0: SDS processes Supplier provided ‘Agreed’ or ‘Override’ Readings and Consumption Amendments”. However, SDS uses flag E0, but ADS uses flag E8 (from the previous numbering of this method and now not intuitive to determine from the flag which method has been used for estimation). Similar to (1), Method 8 (ADS) = Method 8 (SDS), but would be clearer if flag E9 (ADS) matched the method number and flag in SDS, E8. Similar to (1), Method 9 (ADS) = Method 9 (SDS), but would be clearer if flag E10 (ADS) matched the method number and flag in SDS, E9. “3.13 Where notified by a Supplier that a site is Long Term Vacant (LTV) the ADS shall use Method 12.” LTV check is now Method 11. “3.16 The below estimation methods are based on those used in the Smart Data Service (SDS) Method Statement. For that reason, methods 0, 1, 6, 11 and 13 have been omitted as they are only applicable to Smart meters” – this statement is no longer correct as methods 0 and 11 are present |  | Implemented | Design misaligned | TBC |  | Interim Release 7 | 2024-01-19 | Updates completed in method statement 002 | Requirement correction | Supporting Docs | Method Statement | ADS Method Statement
MHHS-DIN-743 | MF |  | 2023-10-24 | ENWL |  | Paul Band | LDSO | IF-036 Optionality Update | IF-036 changed to optional for LDSO's in line with CR-029 within the Optionality Matrix |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | IF-036 changed to optional for LDSO's inline with CR-029 within the within the Optionality Matrix (name of worksheet in DES-138: 04_IF_OptOut_Matrix) | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-744 | MF |  | 2023-10-24 | RECCO |  | Sarah Jones | Central Body | IF-036/037 Routing to MDS | Show that MDS receive IF-036 and IF-037 on BP003 to align with Interface Catalogue |  | Implemented | Design misaligned | N/A |  | Interim Release 7 | 2024-01-19 | Added note to BP003 to highlight that MDS will also receive IF-036 and IF-037. Similar note added to the Migration version BPM003 again just to reference the IF-003 being copied to MDS. Added MDS to IF-003 DSDeAppRM event in DES138 | Process Model correction | Supporting Docs | Process model correction | BP003 BPM003 DES138
MHHS-DIN-745 | SW |  | 2023-10-27 | SI Design | 16780 | Madison Layton | Central Body | DI-120 Additional Information should be mandatory nullable | DI-120 was made non nullable in IR5.1 in Swagger. This needs to be corrected so that DI-120 is used in multiple places and needs to be mandatory nullable. |  | Implemented | Design misaligned | DIP Users, DIP |  | Interim Release 7 | 2024-01-19 | Make DI-120 Additional Information Mandatory nullable in Swagger to align with DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-746 | RG |  | 2023-10-27 | IMserv |  | Liam Lowey | Software Provider | Swagger error - Response body doesn't match Sims& Ems implementation | Schema Bug - Different interpretation of the optional field DIPConnectionProviderID: The DIP Sim requires the property field is present, but allows for a NULL value if we are not using a connection provider. The interface spec, does not allow for a NULL value, but instead does make the field optional. So, it appears that the DipSim requires the property, even if NULL. The schema (v1.2.1) does NOT require the property but will NOT permit NULL. Please can you clarify the intention? This appears to be a blocker/breaking difference that means we will not be able to test the same code base against both DIP Sim and DIP. |  | Closed | Error/Correction | DIP Users, DIP |  |  |  | IF we are going to release a 2.2 release then this should be fixed, this has been fixed on the main code thread. This has not been fixed in rel 1.5, hence not included in the 2.2 release. The design perpetuates as described and the DIPSIM needs to align. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-747 | SB |  | 2023-10-27 | OVO | 16574 | Brian Miller | Supplier | CR028 amendment | Routing of the PUB-001 requires amending to reflect the removal of EES as recipient as per CR028 also the Change of Supply documentation redlining requires amending to reflect this |  | Closed | [5 empty] | Notify that this change already exists
MHHS-DIN-748 | RG |  | 2023-10-27 | IMserv |  | Liam Lowey | Software Provider | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength should not have a maxLength validation attribute as it is an integer type. This means the schema itself does not validate against the rules for these types of schemas. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | DI-487-Total-Number-Energised-MPANs maxLength attribute should be length as it is an integer type. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.6
MHHS-DIN-749 | RG |  | 2023-10-27 | IMserv |  | Liam Lowey | Software Provider | SchemaBug - DipMessage.payload is not a required property | SchemaBug - DipMessage.payload is not a required property, therefore different property names will pass validation without being checked - this means if you spell it "Payload" with a capital P instead it will effectively skip validation resulting in a false positive. |  | Implemented |  |  |  | Interim Release 6 | 2023-10-18 | ‘payload’ needs to be a required attribute for the DIPMessage object. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.6
MHHS-DIN-750 | RS |  | 2023-10-27 | REC |  | Sarah Jones | Central Body | IF-019/020 Interface notes and REG1066 validation | REG1068 was removed as part of IR4, however the neither related interface note in IF-019 and If-020 or REG1068 in the List of Registration error codes in the introduction tab have been updated. Also REG1066 should be removed for consistency. |  | Implemented | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Remove statement 'where there are multiple Related Import MPANs, the Export MPAN will only be linked with the Primary MPAN in the relationship' from IF-019 and IF-020 Interface notes Remove REG1066 validation rule from IF-019 Remove REG1066 and REG1068 from the List of Registration error codes in the introduction tab of DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-751 | RS |  | 2023-10-27 | REC |  | Sarah Jones | Central Body | IF-019/020 Interface notes | Interface note for IF-019 and IF-020 states that for the avoidance of doubt, in all cases it is the LDSO, that must determine if the request to create/modify an MPAN Relationship is valid or not. The ultimate decision to allow the linking or de-linking of a MPAN within a relationship rests with the LDSO. This is correct for linked mpans but not related. Interface note to be updates to be LDSO for linked and supplier for related |  | Implemented | Design ambiguous | LDSO (SCS) |  | Interim Release 8 | 2024-03-20 | Update Interface note for IF-19 and IF-20 to state that for the avoidance of doubt, for Import/Export linkages it is the LDSO, that must determine if the request to create/modify an MPAN Relationship is valid or not. The ultimate decision to allow the linking or de-linking of a MPAN within a relationship rests with the LDSO. Related Metering Point linkages are maintained by the Supplier | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-752 | RS |  | 2023-10-27 |  |  | Sarah Jones | Central Body | Change of Data Service - Forward migration for Import/Export | Yellow note box on DEL964 BPM003 Forward migration document states Export and Import MPANs will be migrated independently, this process is only relevant to Related MPANs. In addition post migration for Export and Import MPANs, the Registration Service will not automatically appoint both the MPANs to the same MS/DS but it will notify of exceptions. This should read PRE-Migration not Post migrations as per requirement MHHS-Migration-Mis-RS-022 |  | Implemented | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Amend wording to 'In addition Pre migration for Export and Import MPANs, the Registration Service will not automatically appoint both the MPANs to the same MS/DS but it will notify of exceptions'.in DEL964 and DEL963 | Process Model correction | Supporting Docs | Process model correction | DEL964 BPM003 DEL963 BPM002
MHHS-DIN-753 | SB |  | 2023-10-30 | CGI |  | Dave Webster | Software Provider | Reconciliation for smart Meter Advance Reconciliation in METH001 | In METH001, v5.2, section 3.12 it states the MAR should be carried out "at a minimum of once a month". Section 3.15 states "The maximum levels are [±0.7%] where the check is carried out at least on a weekly basis for months data or [±5%] where the check is carried out on a daily basis using daily data." These are contradictory. What is the minimum frequency this check can be carried out, is it weekly or is monthly adequate? If monthly is acceptable, should the tolerance level be [±0.7%] as per a weekly check? |  | Open - awaiting assessment | Design ambiguous | N/A |  | Post Go-live Release |  | Propose the statement in METH001 be updated to the following: Section 3.15 states "The maximum levels are [±0.7%] where the check is carried out at least on a weekly or monthly basis or [±5%] where the check is carried out on a daily basis using daily data." | Method statement correction | Supporting Docs | Method Statement | METH001
MHHS-DIN-754 | PP |  | 2023-10-30 | Helix |  | Sedef Kiris | Central Body | Alignment of REP-005 and ISD entity | Issue statement: In TOM, Line Loss Factor (LLF) process is a new streamlined process identified with a hybrid solution combining the benefits of Salesforce and Azure to process LLF Data. However there are some ambiguity within the Design Artefacts around how ISD should be publishing LLF Data. In the MHHS BRS10 document, the requirement from MHHS is to publish the full ISD dataset on the BSC Website in a manner that is available to the public access. The data will be available in 3 separate grouping 1. LLF data 2. Master Settlement timetable 3. ISD data including UMS data However, the MHHS ERI011B ECS report document states that Line Loss Factors' specifics for Market Participants will be provided by Elexon as part of the ISD publication in the name of ELEX-REP-005 The LLF data referenced in MHHS BRS10 and ELEX REP 005, as mentioned in MHHS ERI011B, are identical but bear different names leading to confusion and ambiguity. Helix WP3 has identified this ambiguity and would like MHHS to make relevant Design artefact changes to bring more clarity. |  | Implemented | Error/Correction | All Participants |  | Interim Release 7 | 2024-01-19 | This was raised via the change board where a decision was made to push this through as a DIN REP-005 and the LLF data referenced in the design artifacts are essentially one and the same. Helix aims to meet their requirements by adhering to the specifications outlined in the Transition BRS010. To accomplish this, MHHS needs to take the following changes into consideration. The recommended solution from Helix and MHHSP is to align the Transition and End State Design Artefacts to reflect LLF Data is a deliverable of ISD and add two new ISD Entities to reflect this and remove REP-005 from the list of ECS Reports – impacts BRS010, BRS001 (Transition), ERI011B and EDI012. Remove the mention of ELEX REP 005 from MHHS ERI011B ECS report document To enable the ISD to release Line Loss Factor (LLF) data, the LLF data must be integrated into the MHHS EDI021 ISD Entity Specification document. (detailed below entity details) MHHS then align the Transition and End State Design Artefacts to reflect this change i.e All effected Design Artefacts (BRS010, ERI011B ECS report and EDI021 ISD Entity Specification ) to be updated. | Data interface correction | Supporting Docs | Various documents | BRS010, BRS001 (Transition), ERI011B, EDI012
MHHS-DIN-755 | SC |  | 2023-11-01 |  |  | Sean Cooper | SRO Design | Correction to IF-035 Routing Matrix | Previous DIN created a new group B99 for SDS-MDRUpdate Rejections - this new B099 group was not updated in the Routing Matrix. This has now been corrected. |  | Implemented | Design misaligned | LDSO (SCS) |  | Interim Release 7 | 2024-01-19 | Previous DIN created a new group B99 for SDS-MDRUpdate Rejections - this new B099 group was not updated in the Routing Matrix. This has now been corrected. | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-756 | SC |  | 2023-11-01 |  |  | Sean Cooper | SRO Design | Addition of IF-003 [ReverseMigration] to BPM-001 | Migration Business Process Map BPM-001 updated to include previously missing issuing of IF-003 [ReverseMigration] event from REGS to MDS, LDSO, and EES. This is triggered off the back of COS completion notice (Secured Active) from CSS to REGS. Note this is required as a definitive reverse migration notification as IF-003 [DSApp] may not always be issued. This is not a change to the migration design - step had simply been ommited from BP map. |  | Implemented | Design ambiguous | N/A |  | Interim Release 7 | 2024-01-19 | Migration Business Process Map BPM-001 updated to include previously missing issuing of IF-003 [ReverseMigNotification] event from REGS to MDS, LDSO, Supplier and EES. This is triggered off the back of COS completion notice (Secured Active) from CSS to REGS. Note this is required as a definative reverse migration notification as IF-003 [DSAppRM] may not always be issued. This is not a change to the migration design - step had simply been ommited from BP map. BPD-001 (Reverse Migration) updated accordingly | Process Model correction | Supporting Docs | Process model correction | BPM001 BPMD001
MHHS-DIN-757 | SC |  | 2023-11-01 |  |  | Sean Cooper |  | Add BP003A Link to BP003M Reverse Migration Map. Remove BP003A link from DEL963-BPM002 Forward migration | Added Missing link to show update to CSS/DCC when SDS is de-appointed on Reverse Migration. Remove the link to BP003A from DEL963-BPM002 as this is only triggered for a Change of Data Service |  | Implemented | Design gap | SDS |  | Interim Release 7 | 2024-01-19 | New process link to BP003A added to BPM003 for Smart meters at step 1008. Remove link to BP003A from DEL963-BPM002 | Process Model correction | Supporting Docs | Process model correction | BPM003 BPM002
MHHS-DIN-758 | SC |  | 2023-11-01 |  |  | Sean Cooper | SRO Design | 5 day check on MDR App Date in IF-034 | Per feedback from SCS, five day check on MDR Eff From Date (DI-841) changed to only apply to SDSMDRUpdate event and NOT normal/regular DS Appointment events. Thus removes clash between this check and 28 day leadtime on regular DS Apps |  | Implemented | Design gap | LDSO (SCS) |  | Interim Release 7 | 2024-01-19 | Per feedback from SCS, five day check on MDR Eff From Date (DI-841) changed to only apply to SDSMDRUpdate event and NOT normal/regular DS Appointment events. Thus removes clash between this check and 28 day leadtime on regular DS Apps. New Rule added specifically for DSSAppSPResonse | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-759 | SC |  | 2023-11-01 |  |  | Sean Cooper | SRO Design | Changes to Proposed Consent logic | Proposed Consent (DI-838) Set to Mandatory, Updated allowable values in DI-838 and DI-017 to include N - No consent. Updated ISD M17 table to include meter group and added N value for all traditional meter combinations. |  | Implemented | Design ambiguous | LDSO (SCS) |  | Interim Release 7 | 2024-01-19 | Proposed Consent (DI-838) Set to Mandatory, Updated allowable values in DI-838 and DI-017 to include N - No consent. Updated ISD M17 table to include meter group and added N value for all traditional meter combinations. | Data interface correction | Supporting Docs | Interfaces | DES138 ISD Entities
MHHS-DIN-760 | MF |  | 2023-11-01 |  |  | Mike Fensome | SRO Design | UMSDS routing | Updates to align Optionality Matrix and To Parties for UMSDS |  | Implemented | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | Updated IF-024 to remove UMSDS from To Parties. Updated Optionality Matrix to show IF-043 as N/A and IF-018 as Yes for events [DUOSTariffIDChg] and [DomPremInd] for UMSDS | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-761 | MH |  | 2023-11-03 |  | 16609 | Matt Hall |  | BP020 ver 5.1 redlined - REP D0354 | BP020 5.1 references the supplier receiving various VAS reports including REP-D0354, which isn't a VAS report at all, and isn't sent to suppliers, and REP-D0237 which should be REP-P0237 and is an internal report that doesn't go to suppliers |  | Open - awaiting assessment | Design ambiguous | Suppliers |  | Post Go-live Release |  | Review reports contained in BP020 and correct | Process Model correction | Supporting Docs | Process Models | BP020
MHHS-DIN-762 | MH |  | 2023-11-03 |  |  | Matt Hall | SI Design | DEL961 IF-003 routing to MDS - Update Migration Document | DEL961 needs updating to reflect the clarifications made in DIN-756 that IF-003 should be routed to MDS on [ReverseMigration] and [DSApp] events, not [MSApp] |  | Implemented | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Section 8 of DES961 updated to remove LDSO and Elexon Central Systems receiving MS Deappointment in line with DES-138 | Process Model correction | Supporting Docs | Process model correction | DEL961 - Migration Design Document
MHHS-DIN-763 | RS |  | 2023-11-06 |  | 15975 | Sarah Jones | Central Body | Related Metering Points undergoing Migration | Change to the Registration Service Requirements introduced through IR3 (DIN423). proposed change to RS-146 to remove 'and Related MPANs': Registration must only carry out auto-alignment of Linked MPANs (Import/Export) and Related MPANs if all MPANs in the group have migrated to the MHHS operation. |  | Implemented | Design ambiguous | Suppliers |  | Interim Release 8 | 2024-03-20 | Amend wording to RS-146 from Registration must only carry out auto-alignment of Linked MPANs (Import/Export) and Related MPANs if all MPANs in the group have migrated to the MHHS operation. to Registration must only carry out auto-alignment of Linked MPANs (Import/Export) if all MPANs in the group have migrated to the MHHS operation. | Requirement correction | Registration | Requirement correction | BRS003 - Registration Service Requirements
MHHS-DIN-764 | MF | DI-236 | 2023-11-06 | St Clements |  | Mike Fensome | SRO Design | Additional validation rule in IF-031 to ensure appointments are contiguos | Add new validation rules in IF-031 to ensure that if there is no Service Provider appointed, the Proposed Service Provider Appointment Date is equal to SSD or Previous Service Provider De-appointment Date + 1 |  | Implemented | Design gap | LDSO (SCS) |  | Interim Release 7 | 2024-01-19 | Added two new validation rules in IF-031 to ensure that if there is no Data Service/ Metering Service currently appointed then the Proposed DS/ MS Appointment Date must equal SSD or Previous DS/MS De-appointment Date + 1. Error message of REG 1032 issued if the check fails. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-765 | SW |  | 2023-11-07 |  | 18247 | Steve Weston | SI Design | Inconsistencies in E2E001 JSON examples with Swagger | There are some minor / non-consequential inconsistencies and spelling mistakes in some of the examples provided in the E2E001 design, that do not align with Swagger that need to be corrected in the E2E001 design document |  | Open - awaiting assessment | Design ambiguous | DIP Users |  | Post Go-live Release |  | In section 4.5.6.3 example JSON, "receive" is incorrectly spelt "recieve" in both the header and payload body. The JSON payload is malformed. There's an extra "{" which is not closed and a missing comma after the second "message. These have both been amended in the E2E001 design to align with Swagger. Section 4.5.6.2 says "Where a field is not written/available/optional, then a null value needs to be written". That's not done in the example, which just omits multiple fields. This has been amended in the E2E001 design to align with Swagger. Section 4.5.6.2 says "The response uses the common Standard Response body" but the example includes "recieveEventCallback", is missing "timestamp", and names the array of responses "events" rather than "messageArray". All of which differ from the Standard Response body defined in https://app.swaggerhub.com/apis/MHHSPROGRAMME/SubmitEvents/1.5.1#/StandardResponse. This has been amended in the E2E001 design to align with Swagger. Is the "message" field meant to contain one of a list of allowed responses? - Is the trailing whitespace in "DIP0000 ok ", no trailing whitespace is required, so this has been updated in all example JSON’s where this applies. - The "DIP0000 ok" value for the "message" field is different to the other success messages used in this doc. E.g section 4.4.4.2 uses "Message OK " to represent success and the DIP simulator uses "message": "MSG0000 - Success". Is one of those the correct one? The message returned should align with the messages defined in the Introduction tab in the DES-138 Interface Catalogue. The DIP simulator is returning the correct values, as is the DIP. In this instance, as above, the example is not quite aligned in the E2E001 design so the messages need to align with what is defined in the Introduction tab in the DES-138 Interface | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 Architecture Document
MHHS-DIN-766 | ZH | DIN-464 | 2023-11-07 | SIMS |  | Kyle Abraham | Software Provider | Clarity required on values expected for /dip-channel/{id} for submitEvents on Swagger | The {id} in /dip-channel/{id} for submitEvents on Swagger should accept values that are the same as the enumeration in DI-000 to ensure consistency. At the moment, this is not clear in Swagger, so this needs to be updated to make this clearer. |  | Implemented | Design misaligned |  |  | Interim Release 2.2 |  | Updates made to Swagger 1.2.2, so the correct enumerations / values are available to align with values in DI-000 to ensure consistency and avoid any ambiguity between interfaces and reports. Updated to remove PublicationConfig and RestConfig in favour of a single config WebhookConfig. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.2.2
MHHS-DIN-767 | SW | DIN-772 | 2023-11-13 | C&C | 19150 | Chris Lenihan | Software Provider | Swagger incorrect for IF-043 | For IF-043 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-043-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. |  | Implemented | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Update IF-043 so that it uses the required property name is ‘CustomBlock’ but the actual name is ‘IF-043-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-768 | SW |  | 2023-11-13 |  | 19136 | John Edmonds-Bell | SI Design | Event Code inconsistency between Swagger and ECS Reports for REP-901 | On REP-901 report, the event code in the reports catalogue is defined [DUoS_EmbeddedLDSO_Agg_Inv_Data] and [DUoS_Supplier_Agg_Inv_Data] whereas on the Swagger Document it’s DUoSSupplierInvData. Need to fix this inconsistency innSwagger. |  | Implemented | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Update the ECS reports catalogue to align with Event Code naming standard (used in other Interfaces) and to align with Swagger. On REP-901 report, the event code in the reports catalogue is defined [DUoS_EmbeddedLDSO_Agg_Inv_Data] and [DUoS_Supplier_Agg_Inv_Data] whereas on the Swagger Document it’s DUoSSupplierInvData. Swagger has also been updated to align. | Data interface correction | Supporting Docs | ESC Report | ECS Report Swagger
MHHS-DIN-769 | RG |  | 2023-11-13 |  |  | Rob Golding | SRO | Updates to MHHSP-ERI011B (IR5) not reflected in the swagger | There appears to be several updates to the reporting spreadsheet that did not have a corresponding update in the swagger. The R901-05 block in Swagger is missing an attribute; DI-613. The spreadsheet has incorrect SVA data types for these two new items |  | Implemented | Design misaligned | Helix, DIP, Suppliers, LDSOs |  | Interim Release 7 | 2024-01-19 | Update R901-05 block in Swagger; DI-613. Update MHHSP-ERI011B; the incorrect SVA data types for these two new items. | Data interface correction | Supporting Docs | Interfaces | MHHSP-ERI011B, Swagger
MHHS-DIN-770 | SW | DIN-773 | 2023-11-13 |  | 18780 | Chris Lenihan | Software Provider | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025 | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025. This needs to be updated in the list of enumerated value to be IF-026. |  | Implemented | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025. This needs to be updated in the list of enumerated value to be IF-026 in Swagger. | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-771 | RG |  | 2023-11-13 |  |  | Rob Golding | SRO | R900-03. listOfMPANSOnsite should be listOfMPANSOnSite | Typo in swagger - R900-03. listOfMPANSOnsite should be listOfMPANSOnSite |  | Implemented | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Update R900-03. listOfMPANSOnsite to listOfMPANSOnSite | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-772 | SW | DIN-767 | 2023-11-13 | C&C | 19150 | Chris Lenihan | Software Provider | Swagger incorrect for IF-043 | For IF-043 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-043-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. |  | Implemented | Design misaligned | DIP Users, DIP |  | Interim Release 5.2 |  | Update IF-043 so that it uses the required property name is ‘CustomBlock’ but the actual name is ‘IF-043-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-773 | SW | DIN-770 | 2023-11-13 |  | 18780 | Chris Lenihan | Software Provider | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025 | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025. This needs to be updated in the list of enumerated value to be IF-026. |  | Implemented | Design misaligned | DIP Users, DIP |  | Interim Release 5.2 |  | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025. This needs to be updated in the list of enumerated value to be IF-026 in Swagger. | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-774 | RG |  | 2023-11-15 |  |  | Rob Golding | SRO | IF-020 [LinkedImportExportRemove] & [RelatedRemove] | The B090 block needs to be optional to cope with the scenario where a linked/related meter is removed and it leaves the situation that there are no linked/related meters. Also, on line 64 it mentions a B074 block, however, there is no B074 block in the message |  | Closed | [5 empty] | Fix the swagger and DES138 to reflect this condition | Design Ambiguous | Supporting Docs | Interfaces | DES138
MHHS-DIN-775 | MF |  | 2023-11-15 |  |  | Sarah Jones | Central Body | Remove Customer Direct Process from BP002/BP003 | The Customer Direct process has been set out in BP010 (DIN-554) so can be removed from BP002/BP003 to avoid any confusion |  | Open - awaiting assessment | Clarification - No change required | N/A |  | Post Go-live Release |  | Remove Customer Direct process steps from BP002/BP003 | Process Model correction | Supporting Docs | Process Models | BP002 BP003
MHHS-DIN-776 | MH |  | 2003-11-16 | Elexon |  | Sedef Kiris | Central Body | LLF Data and Rep005 | There is some ambiguity within the Design Artefacts around how ISD should be delivering LLF Data and REP-005. ​ BRS010 implies ISD will publish it through a common delivery method as the Master Settlement Timetable and the rest of the ISD entities, but it does not mention REP-005.​ BRS001 (Transition) denotes that REP-005 will be published via the Elexon Portal and will utilise IF-047. ​ ERI011B denotes that the distribution pattern and the report format of REP-005 are to be defined by Elexon. ​ EDI021 does not include any ISD entities for LLF data. ​ REP-005 and the LLF data mentioned in the design artefacts are the same thing, and Helix intend to fulfil their requirements by delivering in line with requirements as laid out in the Transition BRS. ​ Impact: There is a potential lack of clarity amongst Participants around how they are going to receive REP-005, inconsistency in the overall solution of data coming from ISD. |  | Closed | [5 empty] | Duplicate - To be tracked under MHHS-DIN-754
MHHS-DIN-777 | RG | DIN-785 | 2023-11-16 | SRO | 20939 20723 | Rob Golding |  | IF-001-ChangeOfSupplier required fields on CommonBlocks are incorrect | The required fileds on the common block are set to commonblock and customblock, they need to be set to S1 etc. |  | Implemented | Design misaligned | DIP Users |  | Interim Release 5.2 |  | The required fileds on the common block are set to commonblock and customblock, they need to be set to S1 etc. This has been updated in Swagger so the common block in IF-001 now contains the correct required blocks. Only an issue with 5.+ not 2.+ | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-778 | RG |  | 2023-11-17 | Stark |  | Rob Golding | Supplier | Fix enumeration on the PUB domain for the following PUBs; PUB-004, PUB-019, PUB-020, PUB-040 and PUB-050 in DT-983. Same IF's added for DT-000. | There are a number of values missing from the enumeration in the DT-983 for the Interfaces defined. These are PUB-004, PUB-019, PUB-020, PUB-040 and PUB-050. There are a number of values missing from the enumeration in the DT-000 for the Interfaces defined. These are IF-004, IF-019, IF-020, IF-040 and IF-050. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 2.3 |  | PUB-004, PUB-019, PUB-020, PUB-040 and PUB-050 are missing from DT-983 that defines the enumeration of available values, so these have been added. IF-004, IF-019, IF-020, IF-040 and IF-050 are missing from DT-000 that defines the enumeration of available values, so these have been added. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-779 | SC |  | 2023-11-20 | IMServ |  | Sean Cooper |  | Routing for IF-041 | Add Data Service to Primary Routing for SDS issued IF-041's to align with BP003C |  | Implemented | Design misaligned | SDS |  | Interim Release 7 | 2024-01-19 | Added Data Service (where required) to Primary Routing in the SDS row of IF-041 routing table | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-780 | SB |  | 2023-11-21 | St Clements | 19885 | Madison Layton | Central Body | No longer providing examples within the Interface Catalogue | Updates to the swagger and Interface Catalogue will no longer have examples detailed within the Interface catalogue |  | Closed | [5 empty] | Examples are now managed in Swagger
MHHS-DIN-781 | BK | DIN-748, DIN-783 | 2023-11-21 | IMserv |  | Liam Lowey | Software Provider | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength should not have a maxLength validation attribute as it is an integer type. This means the schema itself does not validate against the rules for these types of schemas. |  | Implemented | Design misaligned | DIP Users |  | Interim Release 2.3 |  | DI-487-Total-Number-Energised-MPANs maxLength attribute should be length as it is an integer type. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-782 | BK | DIN-749, DIN-784 | 2023-11-21 | IMserv |  | Liam Lowey | Software Provider | SchemaBug - DipMessage.payload is not a required property | SchemaBug - DipMessage.payload is not a required property, therefore different property names will pass validation without being checked - this means if you spell it "Payload" with a capital P instead it will effectively skip validation resulting in a false positive. |  | Implemented | Design misaligned | DIP Users |  | Interim Release 2.3 |  | ‘payload’ needs to be a required attribute for the DIPMessage object. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-783 | BK | DIN-748, DIN-781 | 2023-11-21 | IMserv |  | Liam Lowey | Software Provider | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength should not have a maxLength validation attribute as it is an integer type. This means the schema itself does not validate against the rules for these types of schemas. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | DI-487-Total-Number-Energised-MPANs maxLength attribute should be length as it is an integer type. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-784 | BK | DIN-749, DIN-782 | 2023-11-21 | IMserv |  | Liam Lowey | Software Provider | SchemaBug - DipMessage.payload is not a required property | SchemaBug - DipMessage.payload is not a required property, therefore different property names will pass validation without being checked - this means if you spell it "Payload" with a capital P instead it will effectively skip validation resulting in a false positive. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger updated so that ‘payload’ has been added as a required attribute for the DIPMessage object. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-785 | BK | DIN-777 | 2023-11-21 | SRO | 20939 20723 | Rob Golding |  | IF-001-ChangeOfSupplier required fields on CommonBlocks are incorrect | The required fields on the common block are set to commonblock and customblock, they need to be set to S1 etc. |  | Implemented | Design misaligned |  |  | Interim Release 7 | 2024-01-19 | Update IF-001-ChangeOfSupplier required fields on CommonBlocks that are incorrect | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-786 | MF | DI-238 | 2023-11-21 | St Clements |  | Mike Fensome |  | Determination of Market Segment Effective From Date | Add clarification on how Registration Service will set Market Segment Effective From Date |  | Implemented | Clarification - No change required | SCS |  | Interim Release 7 | 2024-01-19 | Added new section to REGS_Notes to clarify how Market Segment EFD is set by Registration Service. The table below outlines how the Registration Service will Derive Market Segment Effective From Date, following various 'trigger' events. Market Segment Change Trigger Derived Market Segment EFD Notes Connection Type Connection Type EFD If triggers a change to related/associated MPANs SEG use the same derived EFD, except in the case this is prior to the relationship/association EFD in which case use relationship/association EFD instead Meter Added/Meter Type changed Meter Installation Date Meter Removed Meter Removal Date If trigger is a Meter Exchange use installation date not removal date Relationship Created Relationship EFD Only amend SEG EFD for MPANs where the SEG is changing – SEG of some MPANs in the relationship/association will not be changing Relationship Deleted Relationship ETD Association Created Association EFD Association Deleted Association ETD Where derived EFD is less than the current Market Segment EFD, the current Market Segment EFD will be cancelled to allow for the new one. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-787 | BK |  | 2023-11-21 | RECCo |  | Sarah Jones | Central Body | Typo in the data item name for DI20228 - DIP Roles / IDs Always Receipient ID (DI-993 in the Interface Catalogue) | It has been noted that there is a typo in the data item name for DI20228 - DIP Roles / IDs Always Recipient ID |  | Implemented | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | Correction of spelling on the word 'Recipient' against DI-993 in the Interface Catalogue | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-788 | SC |  | 2023-11-22 | St Clements |  | Madison Layton | Software Provider | Reconnection of MPAN (provided that CSS DeRegistration has not completed) | New BP009B - would need IF-009 Event Code. "Reconnected" to SUPC only and Re-issue of IF-50 to EES for MPRS Status code. Current MHHS design does not cater for the re-connection of an MPAN that has previously been dis-connected​ Under current operation this is allowed for via a Manual amendment request by the LDSO (Covered by BSCP604) where the MPAN has not been Registration De-activated |  | Implemented | Design gap | St Clements, Suppliers |  | Interim Release 7 | 2024-01-19 | ​Update to BP007 (Disconnection) to show the flows where an MPAN is re-connected ​ Update to BRS003 to add requirement for Registration Service triggering the IF-009 and IF-050 to inform of a re-connection​ Update to BRS004 to add requirement for Suppliers receiving PUB-009 [MPANReconnection]​ Update DES-138 to add new [MPANReconnection] event code to IF-009​ Update to Swagger to add IF-009 MPANReconnection event code variant to Swagger. | Process Model correction | Supporting Docs | Various documents | BP007, BR003, BR004, DES-138, Swagger
MHHS-DIN-789 | BK | DIN-673 | 2023-11-22 | Design Team |  | Rob Golding | Programme Design | Floating Point number regexes | DIN 267 inadvertently updated regexes to a pattern which does not align to the agreed format as of Technical Design Working Group Work-Off Issue D-0408th November 2022. The regexes need to align to what was agreed. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 2.3 |  | Update regex patterns for the following data types: DT-016, DT-022, DT-023, DT-024, DT-025, DT-030, DT-031, DT-032, DT-033 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-790 | BK | DIN-791 | 2023-11-22 | Design Team |  | Rob Golding | Programme Design | Number regex - DI-123 | Update regex patterns for the following data type: DI-123 |  | Implemented | Error/Correction | DIP Users |  | Interim Release 2.3 |  | Update regex patterns for the following data type: DI-122 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-791 | BK | DIN-790 | 2023-11-22 | Design Team |  | Rob Golding | Programme Design | Number regex - DI-123 | Update regex patterns for the following data type: DI-123 |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Added regex patterns for the following data type: DI-123 to use the following pattern: ^\d{4,4}$ | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-792 | BK | DIN-790, DIN-791 | 2023-11-22 | Design Team |  | Rob Golding | Programme Design | Number regex - DI-123 | Update regex patterns for the following data type: DI-123 |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Update regex patterns for the following data type: DI-123 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-793 | SB |  | 2023-11-23 | St Clements | 21513 | Madison Layton | Central Body | DI-241 - SUPC routing on IF-037 incorrect, should be SUPS | SUPC was moved to primary routing for IR5 release, as per attached. However it was clarified on a COS this would be the old Supplier not the current Supplier, so SUPC will not always be correct. Needs to be changed for clarity, SUPS could be used to indicate IF-037 will be sent to the Supplier that submitted the original SP appointment for the SP being de-appointed? |  | Implemented | Clarification - No change required | St Clements |  | Interim Release 7 | 2024-01-19 | Updated primary routing on IF-037 from SUPC to Supplier. On a COS, Registration Service will send to the old Supplier, on Change of Service Provider to the Current Supplier. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-794 | MH | DIN-409 | 2023-11-23 | Elexon | 19961 | Sedef Kiris | Central Body | ISD Consumption Component Classes M5 | In the ISD entity, there was an adjustment made by DIN 409 to distinguish the settlement quality indicator with the same CCC ID. While the ISD Entities specification document has been appropriately updated, the corresponding changes have not been reflected in the MDS method statement Appendix 1. This inconsistency is causing confusion. |  | Implemented | Error/Correction | Elexon |  | Interim Release 7 | 2024-01-19 | The example provided in Appendix 1 in the METH007 is wrong and misleading. As a correct example is provided in the ISD Entities document, we'll remove the one in METH007 | Method statement correction | Meter to Bank | Method Statement | METH007
MHHS-DIN-795 | MH | DIN-678 | 2023-11-23 | Elexon | 18841 | Rashmi Radhakrishnan | Central Body | ISD M9 Clarification | DIN-678 was to change the length of the following UMS data items in ISD: Unit description 1, 2 and Manufacturer's Designation. But Manufacturer's Designation was not changed in both M9 and M10. This iDIN is to complete that update. |  | Implemented | Design misaligned | Elexon, UMSDS |  | Interim Release 7 | 2024-01-19 | Update Manufacturer's Designation in ISD Entity M9 to up to 100 characters | Requirement correction | Supporting Docs | ISD | EDI021
MHHS-DIN-796 | MF | DIN-234 | 2023-11-23 | St Clements |  | Madison Layton | Software Provider | Clarification on validation of B018 block conditionality in IF-034 | Clarification that SCS will validate that a Smart Meter is present for Block B018 conditionality by checking that DCC Service Flag (DI-025) is A |  | Implemented | Clarification - No change required | SCS |  | Interim Release 7 | 2024-01-19 | Note added to IF-034 interface to clarify that SCS will validate that a Smart Meter is present for Block B018 conditionality by checking that DCC Service Flag (DI-025) is A | Data interface correction | Supporting Docs | Interfaces | DES-138
MHHS-DIN-797 | BK |  | 2023-11-24 | Design Team |  | Rob Golding | Programme Design | Capitalisation in Swagger | E2E001 Architecture document will be updated to reflect the adherence to case sensitivity on the inbound messages, and the removal of the statement in Swagger relating to case insensitivity. |  | Implemented | Design gap | DIP Users |  | Interim Release 2.3 |  | Updating of the Swagger and E2E001 to align to Open API standards in relation to case sensitivity. The Section in the E2E001 is 4.4.3 and Swagger its the removal of a comment at the top of swagger file | Data interface correction | Supporting Docs | Interfaces | Swagger, E2E Architecture Document
MHHS-DIN-798 | BK |  | 2023-11-24 | Design Team |  | Rob Golding | Programme Design | Capitalisation in Swagger | E2E001 Architecture document will be updated to reflect the adherence to case sensitivity on the inbound messages, and the removal of the statement in Swagger relating to case insensitivity. |  | Implemented | Design gap | DIP Users |  | Interim Release 5.2 |  | Updating of the Swagger and E2E001 to align to Open API standards in relation to case sensitivity. The Section in the E2E001 is 4.4.3 and Swagger its the removal of a comment at the top of swagger file | Data interface correction | Supporting Docs | Interfaces | Swagger, E2E Architecture Document
MHHS-DIN-799 | SW |  | 2023-11-24 | Design Team |  | Rob Golding | Programme Design | Capitalisation in Swagger | E2E001 Architecture document will be updated to reflect the adherence to case sensitivity on the inbound messages, and the removal of the statement in Swagger relating to case insensitivity. |  | Implemented | Design gap | DIP Users |  | Interim Release 7 | 2024-01-19 | Updating of the Swagger and E2E001 to align to Open API standards in relation to case sensitivity. The Section in the E2E001 is 4.4.3 and Swagger its the removal of a comment at the top of swagger file | Data interface correction | Supporting Docs | Interfaces | Swagger E2E001 Architecture Document
MHHS-DIN-800 | SW |  | 2023-11-27 | Design Team |  | Steve Weston | Programme Design | ECS Reports Inconsistency with Swagger | Inconsistency between ECS Reports Catalogue and Swagger: REP-002B -- R027 and R013 - Distributor and GSP blocks appear to be missing from REP-002B in Swagger. REP-003 -- R024 contains DI-496 in the ECS reports, but in Swagger it contains DI-307. REP-003 -- R9017 contains correctAndUncorrectComponent does not contain block R018 in the name. REP-004 -- R025 and R026 should have parent of R009 according to ECS catalogue, but Swagger has these defined with no parent. REP-006 -- R003 contains R033. R033 should have DI-496, 374, 359, and 360, but in Swagger, contains 307, 374, 359 & 360. REP-006 -- R051 says parent is R032 in ECS reports catalogue, but R051 does not appear in the Swagger in R032. As a result, R106 or R107 which should be part of R051 is missing. REP-009 -- The R013 block contains R016 in Swagger, but in the ECS Catalogue, this is R013 > R068. REP-900 -- R900-03 contains DI-345 in Swagger, when it should contain DI-612. Also marked incorrectly as required. |  | Closed | Design misaligned | DIP Users |  |  |  | Inconsistency between ECS Reports Catalogue and Swagger. For all items below, Swagger is to be updated to align with the ECS Reports Catalogue: REP-002B -- R027 and R013 - Distributor and GSP blocks are missing from REP-002B in Swagger. Add missing blocks. REP-003 -- R024 contains DI-496 in the ECS reports, but in Swagger it contains DI-307. Update to DI-496. REP-003 -- R9017 contains correctAndUncorrectComponent does not contain block R018 in the name. Update naming. REP-004 -- R025 and R026 should have parent of R009 according to ECS catalogue, but Swagger has these defined with no parent. Update Swagger to align. REP-006 -- R003 contains R033. R033 should have DI-496, 374, 359, and 360, but in Swagger, contains 307, 374, 359 & 360. Update to DI-496. REP-006 -- R051 says parent is R032 in ECS reports catalogue, but R051 does not appear in the Swagger in R032. As a result, R106 or R107 which should be part of R051 is missing. Add the missing blocks to align. REP-009 -- The R013 block contains R016 in Swagger, but in the ECS Catalogue, this is R013 > R068. Update R013 in Swagger to contain R068. REP-900 -- R900-03 contains DI-345 in Swagger, when it should contain DI-612. Also marked incorrectly as required. Update Swagger to use DI-612. Closed as decision made to only align ECS Reports changes to IR7. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-801 | SW |  | 2023-11-27 | Design Team |  | Steve Weston | Programme Design | ECS Reports Inconsistency with Swagger | Inconsistency between ECS Reports Catalogue and Swagger: REP-002B -- R027 and R013 - Distributor and GSP blocks appear to be missing from REP-002B in Swagger. REP-003 -- R024 contains DI-496 in the ECS reports, but in Swagger it contains DI-307. REP-003 -- R9017 contains correctAndUncorrectComponent does not contain block R018 in the name. REP-004 -- R025 and R026 should have parent of R009 according to ECS catalogue, but Swagger has these defined with no parent. REP-006 -- R003 contains R033. R033 should have DI-496, 374, 359, and 360, but in Swagger, contains 307, 374, 359 & 360. REP-006 -- R051 says parent is R032 in ECS reports catalogue, but R051 does not appear in the Swagger in R032. As a result, R106 or R107 which should be part of R051 is missing. REP-009 -- The R013 block contains R016 in Swagger, but in the ECS Catalogue, this is R013 > R068. REP-900 -- R900-03 contains DI-345 in Swagger, when it should contain DI-612. Also marked incorrectly as required. |  | Implemented | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Inconsistency between ECS Reports Catalogue and Swagger. For all items below, Swagger is to be updated to align with the ECS Reports Catalogue: REP-002B -- R027 and R013 - Distributor and GSP blocks are missing from REP-002B in Swagger. Add missing blocks. REP-003 -- R024 contains DI-496 in the ECS reports, but in Swagger it contains DI-307. Update to DI-496. REP-003 -- R9017 contains correctAndUncorrectComponent does not contain block R018 in the name. Update naming. REP-004 -- R025 and R026 should have parent of R009 according to ECS catalogue, but Swagger has these defined with no parent. Update Swagger to align. REP-006 -- R003 contains R033. R033 should have DI-496, 374, 359, and 360, but in Swagger, contains 307, 374, 359 & 360. Update to DI-496. REP-006 -- R051 says parent is R032 in ECS reports catalogue, but R051 does not appear in the Swagger in R032. As a result, R106 or R107 which should be part of R051 is missing. Add the missing blocks to align. REP-009 -- The R013 block contains R016 in Swagger, but in the ECS Catalogue, this is R013 > R068. Update R013 in Swagger to contain R068. REP-900 -- R900-03 contains DI-345 in Swagger, when it should contain DI-612. Also marked incorrectly as required. Update Swagger to use DI-612. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-802 | SW |  | 2023-11-27 | Design Team |  | Steve Weston | Programme Design | Naming standards are inconsistently applied in ECS reports catalogue for nested structures and lists. | Naming standards are inconsistently applied in ECS reports catalogue for nested structures and lists, meaning it you have blocks that contain blocks with the same name, as there is no naming mechanism to easily link nested block name to contains, or back to ECS reports catalogue. |  | Closed | [5 empty] | Implement a new naming standard for ECS reports catalogue. Closed as decision made to only align ECS Reports changes to IR7. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-803 | SW |  | 2023-11-27 | Design Team |  | Steve Weston | Programme Design | Naming standards are inconsistently applied in ECS reports catalogue for nested structures and lists. | Naming standards are inconsistently applied in ECS reports catalogue for nested structures and lists, meaning it you have blocks that contain blocks with the same name, as there is no naming mechanism to easily link nested block name to contains, or back to ECS reports catalogue. |  | Implemented | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Implement a new naming standard for ECS reports catalogue for nested structures and lists. | Data interface correction | Supporting Docs | Interfaces | ECS Reports Catalogue
MHHS-DIN-804 | SB |  | 2023-11-28 | ESG | 22206 | Patricia Parker | Software Provider | Migration clarification | Page 13 of the migration document states the following for Forward Migration CoA 14. The Registration Service will send the IF-036 at the Service Appointment effective from date. The sending of the IF-036 will act as the definitive indicator that a Forward Migration has completed. Is the IF_036 not sent at the Service Appointment effective from date – 1 . Registration Service will have processed all Secured Active Messages and processed the Pending Appointment Queue by 21:00. This will include the production and publication of all required IF-035, IF-036 and IF-037 messages. |  | Closed | Clarification - No change required |  |  |  |  | Already discussed and agreed for SDS to determine solution.
MHHS-DIN-805 | RG |  | 2023-11-29 | SRO |  | Rob Golding | SRO Design | Examples in swagger incorrectly resolved if have a leading 0 | Sims & Ems noted that the example for DI-123-SSC was resolving to the value 83 when in fact it should be 0123. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Tracked down a bug in swaggerhug, doesn't like leading zero on non-string delimted examples. Work around is to string delimit. Also added regular expression pattern - ^\d{4,4}$. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-806 | SW |  | 2023-11-29 | Electralink | 21470 | Roz Turner | Central Body | Details of the compression team are not defined in the E2E001 design document, only in CR030 at a high level | There is currently no detail in the E2E001 of how data should be compressed and uncompressed for the ECS reports, this information is held in CR030 and DRG documentation. This DIN is to update the E2E001 Architecture design document to add a section to explain this in more detail. |  | Closed | [5 empty] | Closed - will be picked up in IR7 as part of DIN-806 | Data interface correction | Supporting Docs | Interfaces | Swagger, E2E Architecture Document
MHHS-DIN-807 | SW |  | 2023-11-29 | Electralink | 21470 | Roz Turner | Central Body | Details of the compression team are not defined in the E2E001 design document, only in CR030 at a high level | There is currently no detail in the E2E001 of how data should be compressed and uncompressed for the ECS reports, this information is held in CR030 and DRG documentation. This DIN is to update the E2E001 Architecture design document to add a section to explain this in more detail. |  | Implemented | Design ambiguous | DIP Users |  | Interim Release 7 | 2024-01-19 | Updated the E2E001 Architecture design document to add a section to explain how data should be compressed and uncompressed for the ECS reports. | Data interface correction | Supporting Docs | Technical Design | E2E001 Architecture Document
MHHS-DIN-808 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-007 EnergisationStatusChange/Failure CustomBlocks missing required attribute | Missing required (mandatory) attribute in object (B025 and B040) |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for inclusion of missing attribute in IF-007. This was adding B025 block as required block in the EnergisationStatusChnage variant of IF-007 and adding B040 block as a required block in the EnergisationStatusFailure variant of IF-007. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-809 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-008 EnergisationStatusChange, common block for R0 and CustomBlocks for B025 block missing required attribute | Missing required (mandatory) attribute in object (R0 and B025) |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for inclusion of missing attribute in IF-008. This was adding R0 block as required block in the Common block of IF-008 and adding B025 block as a required block in the CustomBlock of IF-008. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-810 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-004 common block M0 required attribute is missing | Missing required attribute in object |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for inclusion of missing attribute M0 in the required common block in IF-004 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-811 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-024 missing required attributes in blocks | IF024 SNVacant CustomBlock required B057 IF024 SNRemoteEnabled CustomBlock required B057, B069 IF024 SNSupplierAC CustomBlock required B057, B058 |  | Closed | Error/Correction | DIP Users |  |  |  | Swagger update for inclusion of missing attribute in IF-024 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-812 | RG | DIN-699 | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-036 missing required attributes for B068 block | Missing required attribute in object |  | Closed | Error/Correction | DIP Users |  |  |  | Swagger update for inclusion of missing attribute in IF-036 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-813 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-015 incorrect required Custom Block | There is no customblock on IF-015 |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for removal of custom block in IF-015, as there is no CustomBlock on IF-015. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-814 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-045 incorrect name on Custom block | For IF-045 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-045-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for incorrect name of custom block in IF-045, this has been renamed to CustomBlock. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-815 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | DI-838-Supplier-Proposed-Consent-Granularity requires a null enum | This is to match nullable:true from DES-138. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for DI-838 to allow null in the enumerated list of values. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-816 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-001 Custom Block missing addtional properties false attribute | IF-001 Custom Block missing addtional properties false attribute |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for inclusion of missing attribute in IF-001 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-817 | SW |  | 2023-11-29 | Helix |  | Steve Weston | SI Design | Incorrect examples in Swagger for Integers that start with 0 (bug in Swagger Hub) | There are incorrect examples provided for some properties, for example SSC (DI-123) in B032 in the Submit Events on SwaggerHub. This is partly a bug in Swagger Hub where the properties should not start with a '0'. |  | Closed | Error/Correction | DIP Users |  |  |  | Duplicate of DIN-805
MHHS-DIN-818 | SW |  | 2023-11-29 | Helix |  | Steve Weston | SI Design | IF-014 Payload does not implement B900 block correctly to align with IF-021. | IF-014 should contain a B900 block, not a B900 array. This change was made in IR5 for IF-021, but was only applied to IF-014 in IR6. This DIN is to align with IF-021 for IR5 and ensure that B900 used, not an array of B900's. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update to IF-014 to align with IR6 implementation | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-819 | SW |  | 2023-11-29 | Helix |  | Steve Weston | SI Design | Typo in event code for REP-004 | In REP-004, the eventCode = [SuplierDemandTakeReport], and supplier is spelt incorrectly. This needs to be updated in both the ECS reports catalogue and Swagger |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Update REP-004 and Swagger the eventCode = [SuplierDemandTakeReport], and supplier is spelt incorrectly. | Data interface correction | Supporting Docs | Interfaces | Swagger, ECS Report
MHHS-DIN-820 | SW |  | 2023-11-29 | Procode | 21898, 21073 | Steve Weston | SI Design | IF-041 contains B06465list that uses anyOf when this should be oneOf B064 or B065 to align with DES-138. | IF-041 contains B06465list that uses anyOf when this should be one of either B064 or B065 to align with DES-138. This needs to be updated so that this list contains wither a B064 list OR B065 list, not both / either. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update to align IF-041 to DES-138. Any of has been removed from the Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-821 | SW | DIN-820 | 2023-11-29 | Procode | 21898, 21073 | Steve Weston | SI Design | IF-041 contains B064/65 list that uses anyOf when this should be oneOf B064 or B065 to align with DES-138. | IF-041 contains B064/65 list that uses anyOf when this should be one of either B064 or B065 to align with DES-138. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Swagger is aligned to DES-138 to allow one or both B064 and B065. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-822 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-007 EnergisationStatusChange/Failure CustomBlocks missing required attribute | Missing required attribute in object (B025 and B040 respectively are missing from IF-007 EnergisationStatusChange/Failure CustomBlocks. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Missing required attribute in object (B025 and B040 respectively are missing from IF-007 EnergisationStatusChange/Failure CustomBlocks. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-823 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-008 EnergisationStatusChange, common block for R0 and CustomBlocks for B025 block missing required attribute | IF-008 EnergisationStatusChange, common block for R0 and CustomBlocks for B025 block missing required attribute |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Swagger update for inclusion of missing attribute in IF-008 - IF-008 EnergisationStatusChange, common block for R0 and CustomBlocks for B025 block missing required attribute | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-824 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-004 common block M0 required attribute is missing | IF-004 common block M0 required attribute is missing |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | IF-004 common block M0 required attribute is missing, so this has been added in the Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-825 | RG | DIN-881 | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-024 missing required attributes in blocks | IF024 SN-Vacant CustomBlock required B057 IF024 SN-NoComms CustomBlock required B057 IF024 SNRemoteEnabled CustomBlock required B057, B069 IF024 SNSupplierAC CustomBlock required B057, B058 |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Swagger update for inclusion of missing attribute in IF-024 IF024 SN-Vacant CustomBlock required B057 IF024 SN-NoComms CustomBlock required B057 IF024 SNRemoteEnabled CustomBlock required B057, B069 IF024 SNSupplierAC CustomBlock required B057, B058 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-826 | RG | DIN-699 | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-036 missing required attributes for B068 block | Missing required attribute in object |  | Closed | Error/Correction | DIP Users |  |  |  | Duplicate of DIN-699 Swagger update for inclusion of missing attribute in IF-036
MHHS-DIN-827 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-015 incorrect required Custom Block | There is no customblock on IF-015, so this has been removed from this Interface on Swagger. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | There is no customblock on IF-015, so this has been removed from this Interface on Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-828 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-045 incorrect name on Custom block | For IF-045 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-045-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | For IF-045 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-045-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. This change has been made in Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-829 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | DI-838 and DI-017 - require an N - No Consent enum | DI-838-Supplier-Proposed-Consent-Granularity and DI-017 Consent Granularity requires an N - No Consent enum in the list of allowable values. DI-838 needs to be Mandatory no nulls |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Swagger updated so that DI-838-Supplier-Proposed-Consent-Granularity and DI-017 Consent Granularity includes N - No Consent in the list of allowable values. DI-838 updated to be Mandatory no nulls | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-830 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-001 Custom Block missing addtional properties false attribute | IF-001 Custom Block missing addtional properties false attribute |  | Implemented | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | IF-001 Custom Block missing addtional properties false attribute. Swagger updated to include this. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-831 | BK | DIN-689 | 2023-11-30 | SI Design |  | Madison Layton | Central Body | DI-120 Additional Information should be mandatory nullable | DI-120 was made non nullable in IR5.1 in Swagger. This needs to be corrected so that DI-120 is used in multiple places and needs to be mandatory nullable. |  | Implemented | Design misaligned | DIP Users, DIP |  | Interim Release 5.2 |  | Make DI-120 Additional Information Mandatory nullable in Swagger to align with DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-832 | RS | DIN-840 | 2023-12-01 | Kraken | 22885 | Henri Naef | Software Provider | [MeterUpdate]) to be added to data item B039 heading for IF-006 | IF-005/IF-006 both contain data item B039, however a difference exists in the header. IF-005 contains "Optional for Event [MeterHistoryUpdate] & [MeterUpdate])" whereas the IF-006 contains only "Optional for Event [MeterHistoryUpdate]) |  | Implemented | Design misaligned |  |  | Interim Release 7 | 2024-01-19 | DES-138 and Swagger updated to include [MeterUpdate] as Optional for B039 in IF-006. | Data interface correction | Supporting Docs | Interfaces | Swagger, DES138
MHHS-DIN-833 | RS | DIN-841 | 2023-12-01 | UKPN | 23047 | Neal Medley | Network Operator | Routing table to include LDSO for IF-018 | Optionality matrix shows that LDSOs can additionally receive Event Codes [AddressChg], [GSPChg] and [DUOSTariffIDChg]. LDSO to be added to IF-018 secondary routing for these three event codes in DES138 |  | Implemented | Design ambiguous |  |  | Interim Release 7 | 2024-01-19 | DES-138 updated routing table for IF-018 updated to include LDSO for Event Codes [AddressChg], [GSPChg] and [DUOSTariffIDChg]. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-834 | RG | DIN-818 | 2023-12-01 | SRO |  | Rob Golding | SRO Design | IF-014 - to align with IF-021 | Update DES138 to match swagger |  | Implemented | Design misaligned | DIP Users, DIP |  | Interim Release 5.2 |  | Update IF-014 to match IF-021 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-835 | RG | MHHS-DIN-836, 882 | 2023-12-04 | Avanade |  | Rob Golding | SRO Design | Add additional error messages to DES138 | Avanade as part of their development work have generated some error codes that need to fed back into DES138: Error Code Error Text MSG1013 Invalid CertifcateIssuerName MSG1014 Certificate has expired MSG1039 Invalid MPAN MSG5001 Internal server error MSG5002 No data contained in request body MSG5003 Unable to determine correlationId requirement. Server configuration error or sender request error MSG5004 Internal server error.Payload not processed |  | Implemented | Design gap | DIP Users, DIP |  | Interim Release 7 |  | Add error codes into the DES-138 Interface Catalogue (00-Introduction Tab) Error Code Error Text MSG1013 Invalid CertifcateIssuerName MSG1014 Certificate has expired MSG1039 Invalid MPAN MSG5001 Internal server error MSG5002 No data contained in request body MSG5003 Unable to determine correlationId requirement. Server configuration error or sender request error MSG5004 Internal server error.Payload not processed | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-836 | RG | MHHS-DIN-835, 882 | 2023-12-04 | SRO |  | Rob Golding | SRO Design | New swagger file ErrorCodes to describe MHHS error messages | New swagger file (Response Codes schema) to capture all message and error codes from DES138. |  | Implemented | Design gap | DIP Users, DIP |  | Interim Release 7 |  | New swagger file (Response Codes schema) to capture all message and error codes from DES138. | Data interface correction | Supporting Docs | Interfaces | Swagger E2E001 Architecture Document
MHHS-DIN-837 | SB |  | 2023-12-05 | ESG | 21835 | Patricia Parker | Software Provider | Migration D0086 Clarification | Page 51 of the migration design document shows the following for the D0086. Data Item ‘Meter Reading Reason Code’ (J0332) related enumeration will include 3 additional values:- a. Enumeration Value: 28; Enumeration Description: Forward Migration CoA b. Enumeration Value: 29; Enumeration Description: Forward Migration CoS c. Enumeration Value: 30; Enumeration Description: Reverse Migration My understanding was that the values should reflect those in the D0010 for the migration so parties where aware of the migration process:- Data Item ‘Reading Type’ (J0171) related enumeration will include 3 additional values: a. Enumeration Value: U; Enumeration Description: Forward Migration CoA b. Enumeration Value: V; Enumeration Description: Forward Migration CoS c. Enumeration Value: Y; Enumeration Description: Reverse Migration |  | Implemented | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | Changes made to the Migration Design Document in section 13.1.4 (D0086) under point 2 (this now aligns with DES196) as follows; Data Item ‘Reading Type’ (J0171) related enumeration will include 3 additional values: Enumeration Value: U; Enumeration Description: Forward Migration CoA Enumeration Value: V; Enumeration Description: Forward Migration CoS Enumeration Value: Y; Enumeration Description: Reverse Migration | Data interface correction | Supporting Docs | Interfaces | Migration Design Document
MHHS-DIN-838 | SB |  | 2023-12-05 | British Gas | 23696 | Neil Strange | Supplier | BPD004 v5 - step 270 typo | Can you confirm that the reference to SDS method statement in step 270 of the data collection process description is a typo and should be ADS? This is in BPD004 v5. Looks like a simple cut and paste mistake |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | BPD004 - step 270 update typo from "SDS" to "ADS" | Process Model correction | Supporting Docs | Process Model description document | BPD004
MHHS-DIN-839 | MF |  | 2023-12-05 | ESG |  | Mike Fensome | Software Provider | Confirmation of DT016 data type | Update all references of DT016 to show as string 14 to align with swagger |  | Implemented | Design misaligned |  |  | Interim Release 7 | 2024-01-19 | DT016 updated in DES138 to show as String 14 as per swagger for the following data item references: DI-043 Load Shape 7 Day Rolling Total DI-102 Load Shape Period Value DI-104 Configurable Register Reading | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-840 | RS | DIN-832 | 2023-12-01 | Kraken | 22885 | Henri Naef | Software Provider | [MeterUpdate]) to be added to data item B039 heading for IF-006 | IF-005/IF-006 both contain data item B039, however a difference exists in the header. IF-005 contains "Optional for Event [MeterHistoryUpdate] & [MeterUpdate])" whereas the IF-006 contains only "Optional for Event [MeterHistoryUpdate]) |  | Implemented | Design misaligned |  |  | Interim Release 5.2 |  | DES-138 and Swagger updated to include [MeterUpdate] as Optional for B039 in IF-006. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-841 | RS | DIN-833 | 2023-12-01 | UKPN | 23047 | Neal Medley | Network Operator | Routing table to include LDSO for IF-018 | Optionality matrix shows that LDSOs can additionally receive Event Codes [AddressChg], [GSPChg] and [DUOSTariffIDChg]. LDSO to be added to IF-018 secondary routing for these three event codes in DES138 |  | Implemented | Design ambiguous |  |  | Interim Release 5.2 |  | DES-138 updated routing table for IF-018 updated to include LDSO for Event Codes [AddressChg], [GSPChg] and [DUOSTariffIDChg]. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-842 | MH |  | 2023-12-06 | St Clements | 22462 | Tom Perryman | Software Provider | REP901, Common Block and Compression | Other REPs have the DIP Distribution Pattern and Report Format defined. This is not the case for the REP900 and REP901 Other REPs have the Routing Rules defined. This is not the case for the REP900 and REP901 |  | Implemented | Design gap |  |  | Interim Release 7 | 2024-01-19 | For REP-900 and REP-901 Add Distribution Pattern: A Add report format: JSON Add routing rules. Updated schema for Swagger to include compressed schema information as per other ECS reports. | Data interface correction | Supporting Docs | Interfaces | ESC Report, Swagger
MHHS-DIN-843 | RG | DIN-835,836, 882 | 2023-12-07 | SRO |  | Rob Golding | SRO | Add RCP0000 to DES138 and Swagger as a valid a response code | A 'success'response code is required for MPs to provide a valid L3 response. |  | Implemented | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | RCP0000 added to DES138 and Swagger as a valid a response code. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-844 | BK |  | 2023-12-07 | Large Suppliers |  | Graham Wood, Haz Elmamoun | Supplier | Standardisation of Interfaces within the Smart Data Services | This CR seeks to avoid cost and inconsistency in the design by adding OPTIONAL standardised messages to support the Meter Data Retriever SDS sub-role. Parties would be able to choose to implement this or come to bilateral arrangements as currently designed. Standardisation can be achieved by adding additional routing to current DIP messages and creating variants of existing messages. | CR023 | Implemented | Change Request |  |  | Interim Release 7 |  | Updated Business Requirements for parties (SDS/MDR) wishing to take advantage of the standard messages (BRS017) Updated Business Process Diagram (BP017) Updated Message Structures in DES-138 for IF-061, 062, 063, 064, 065. Updated Swagger to align with DES-138 and add new Interfaces. Updated E2E Solution Architect Document | Data interface correction | Supporting Docs | Interfaces | MHHSP-BP017- Optional SDS MDR Standard Interactions BRS017 DES138 Swagger E2E001 Architecture Document
MHHS-DIN-845 | MH |  | 2023-12-12 | St Clements | 24142 | Tom Perryman | Software Provider | REP900 “List of MPANs” field should be mandatory | The REP900 “List of MPANs” field. It is currently optional in the REP900, and should be mandatory. We also believe that Zero should be added as a chargeType. |  | Implemented | Design gap |  |  | Interim Release 7 | 2024-01-19 | REP900 Changes DI-566 ‘List of MPANs on Site’ to be made a mandatory field to enable receivers of the REP900 to correctly identify the MPANs associated to a site. The population of this field is essential to allow the supplier to know what MPANs the DUoS invoice relates to, enabling them to validate the invoice Update to the possible values for DI-596 ‘Charge Type’ to include ZERO, and format all possible values to CAPS. Additional chargeType values have been added to DI-596 in both DES-138 and Swagger. | Data interface correction | Supporting Docs | Interfaces | ECS Report
MHHS-DIN-847 | MF |  | 2023-12-14 |  |  | Madison Layton | Software Provider | Add error code for IF-025 to validate if Null is provided and value is already Null | MPRS needs a level 5 validation rule to enable MPRS to reject the PUB-025 in the following cases: IHD null when there is no active IHD install status held to end date SMSO null when there is no active SMSO held to end date PC null and PC EFD not null, when there is no active PC held to end date SSC null and SSC EFD not null, where there is no active SSC held to end date |  | Implemented | Design gap | SCS |  | Interim Release 7 | 2024-01-19 | Added REG0009 - Null Value cannot be set as Value held is already Null. Added validation rules to enable MPRS to reject the PUB-025 using REG0009 in the following cases: IHD null when there is no active IHD install status held to end date SMSO null when there is no active SMSO held to end date PC null and PC EFD not null, when there is no active PC held to end date SSC null and SSC EFD not null, where there is no active SSC held to end date | Data interface correction | Supporting Docs | Interfaces | DES-138
MHHS-DIN-848 | MF |  | 2023-12-14 |  |  | Madison Layton | Software Provider | Clarification on SP de-appointment effective from date in the case of Atomic Secured Active | In rare scenario's Atomic Secured Active messages could result in an Effective To-date which is before the Effective From Date of the Service Provider Appointment 1. Supplier A active at MPAN 2. CSP received for DS with EFD 8th December 3. CSP gets confirmed 4. MPRS receives an Atomic Secured Active for Supplier B (Atomic means there was no Pending notification) on 13th December with SSD 8th December (or earlier) 5. MPRS must de-appoint the DS with ETD = SSD – 1, in this scenario ETD = 7th December |  | Implemented | Clarification - No change required | SCS, Service Providers, Suppliers |  | Interim Release 7 | 2024-01-19 | Added clarification to IF-037 notes that In rare scenario's Atomic Secured Active messages could result in an Effective To-date which is equal to the Effective From Date of the Service Provider Appointment. And as such the appointment will be deemed as having never taken effect | Data interface correction | Supporting Docs | Interfaces | DES-138
MHHS-DIN-846 | SW |  | 2023-12-13 |  | 24874 | Chris Mingay | Software Provider | B050 consumptionComponentClassID property inconsistency between ECS reports catalogue and Swagger | B050 consumptionComponentClassID property inconsistency between ECS reports catalogue and Swagger. In the ECS reports catalogue, in IR2 and IR5 this is an INT3, min 100 and max 999. This was correct in Swagger 1.2, but in Swagger 1.5, this has reverted to a String3 with min / max values of 3, so does not align to ECS reports catalogue. |  | Implemented | Design misaligned |  |  | Interim Release 7 | 2024-01-19 | Update Swagger to align with ECS reports catalogue for B050 consumptionComponentClassID to be an Integer. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-849 | MF |  | 2023-12-14 |  |  | Madison Layton | Software Provider | Change B099 to be a single block rather than a list in IF-035 | In IF035 SDS-MDROutcome variant, make B099 a single block in the swagger rather than a list. |  | Implemented | Error/Correction | SCS, Service Providers, Suppliers, DIP |  | Interim Release 7 | 2024-01-19 | Swagger updated so that for IF035 SDS-MDROutcome variant, B099 is a single block in the swagger rather than a list. | Data interface correction | Supporting Docs | Interfaces | Swagger DES-138
MHHS-DIN-850 | MH |  | 2023-12-14 |  |  | Matt Hall | SI Design | CR36 - Clock Time Reads and Appointments | Implementation of the Design Changes required to support CR36 | CR036 | Implemented | Change Request | All Participants |  | Interim Release 7 |  | Update the artefacts as per CR36 | Data interface correction | Supporting Docs | Various documents | BP003, BP003C, DES138, BRS001, BRS003, METH005, METH007
MHHS-DIN-851 | MH |  | 2023-12-14 |  | 25624/33640 | Sarah Jones | Central Body | Outstanding Queries to Support Interface Code Drafting | Update the data catalogue in DES-138 to show the correct data types and data type descriptions |  | Closed | Clarification - No change required | All Participants |  |  |  | Closed as specific DIN's now raised. | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-852 | MH |  | 2023-12-14 |  | 21890 | Mike Ceney | Central Body | ECS Report 006 | Within block R003- CCC Determined Data, the Domestic Premise Indicator (DI-030) is to be populated, I believe this to be incorrect and needs to be removed from the report. This data item is populated at an Mpan level but this report is at BMU level so therefore cannot be populated |  | Implemented | Error/Correction | Helix, Suppliers |  | Interim Release 7 | 2024-01-19 | Remove Domestic Premise Indicator from REP 006 | Data interface correction | Supporting Docs | Interfaces | MHHSP - ERI011B - ECS Reports - External
MHHS-DIN-853 | SB |  | 2023-12-14 |  |  |  | SRO Design Team | Addition of new RetroSpective Date Validation Rules following DRG Review & Sign Off | Amended IF-025 Validation rules for SSC& Profile Class Eff From Date to include Migration Date per reviewed & agreed RetroDates PPT. No changes rquired to any other data items as a result of RetroDates Functionality. |  | Implemented | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | Amended IF-025 Validation rules for SSC& Profile Class Eff From Date to include Migration Date in DES138. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-854 | SW |  | 2023-12-15 | IMServ | 24832 | Liam Lowey | Software Provider | DI-085 GUID definition | DI-085 GUID definition does not align with Industry definition of a GUID ie, 8 HEX, 4x3 HEX, then 12 HEX, but rather, this refers to an SME GUID that is not a true GUID but rather a EUI base 64 address, akin to an IP v6 address. Need to update the example so that DI-085 provides clarity on whether HEX values are included. |  | Implemented | Design ambiguous |  |  | Interim Release 7 |  | Update example in the DI-085 property to align with a EUI base 64 address, akin to an IP v6 address. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-855 | SW |  | 2023-12-15 | Callisto | 24828 | Neil Edney | Software Provider | Swagger required properties are not aligned with Swagger property names | There are a number of blocks where the Swagger required properties are not aligned with Swagger property names which will cause a schema validation error incorrectly. B051 - GPSGroupID and domesticPremiseIndicator - properties and required properties do not align. B014 - incomingMeteringServiceEffectiveDate and incomingMeteringServiceDIPEffectiveFromDate - properties and required properties do not align. B021 - customerDirectContractDataServiceEffectiveDIPID and customerDirectContractDataServiceDIPID - properties and required properties do not align. |  | Closed | Design misaligned
MHHS-DIN-856 | PP | ADO Defect 19010 | 2023-12-15 | Programme |  | Paul Pettitt | SI Design | DI-020 example incorrect Length | DI-020 Contract Reference data service has a Max length of 10 chars, the example is 11 |  | Closed | Error/Correction | DIP Users |  |  |  | Corrected in IR5.3 Maximum set to 50 and example is correct.
MHHS-DIN-857 | RG |  | 2023-12-18 | SRO |  | Rob Golding | SRO Design | Ensure all enumerated types have obfuscated values (where needed) (IR 5.3 Release) | Ensure all enumerated type that are obfuscated contain the obfuscated value in the enumerated list. This change affects the following: IF-035 DI-979 Response Code DI-800 Service Provider Appointment Scenario DI-838 Supplier Proposed Consent Granularity DI-126 Traditional Fall Back Read Frequency IF-036 DI-017 Consent Granularity Obfuscated DIP IDs wil be 9999999999 as the regex dictates it needs to be a 10 character numeric string |  | Implemented | Design gap |  |  | Interim Release 5.3 |  | Updated all enumerated type that are obfuscated contain the obfuscated value in the enumerated list. This change affects the following: IF-035 DI-979 Response Code DI-800 Service Provider Appointment Scenario DI-838 Supplier Proposed Consent Granularity DI-126 Traditional Fall Back Read Frequency IF-036 DI-017 Consent Granularity | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-858 | RG |  | 2023-12-18 | SRO |  | Rob Golding | SRO Design | Ensure all enumerated types have obfuscated values (where needed) (IR 7 Release) | Ensure all enumerated type that are obfuscated contain the obfuscated value in the enumerated list. This change affects the the following: IF-035 DI-979 Response Code DI-800 Service Provider Appointment Scenario DI-838 Supplier Proposed Consent Granularity DI-126 Traditional Fall Back Read Frequency IF-036 DI-017 Consent Granularity Obfuscated DIP IDs wil be 9999999999 as the regex dictates it needs to be a 10 character numeric string |  | Implemented | Design gap |  |  | Interim Release 7 | 2024-01-19 | Ensure all enumerated type that are obfuscated contain the obfuscated value in the enumerated list. This change affects the the following: IF-035 DI-979 Response Code DI-800 Service Provider Appointment Scenario DI-838 Supplier Proposed Consent Granularity DI-126 Traditional Fall Back Read Frequency IF-036 DI-017 Consent Granularity Obfuscated DIP IDs wil be 9999999999 as the regex dictates it needs to be a 10 character numeric string | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-859 | MH |  | 2023-12-20 | St Clements | 24142 | Tom Perryman | Software Provider | REP900 invoice | Currently, the REP900 has one or many invoices for each site / invoice data (R900-05 level). This needs to be updated so that the REP900 contains one or many combinations of site and invoice data (R900-04 level). Currently a single D2021 is sent to a supplier containing all their HH invoices produced on that billing day. |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | Correct the REP900 record hierarchy to: Clarification of the record hierarchy to enable the inclusion of multiple invoices on a single REP900 R900-01 Distributor Info - a single Distributor on a REP900 R900-02 Supplier Info - a single Supplier on a REP900 > R900-03 Site Info > R900-04 Invoice Data - one or many combinations of Site and Invoice Data >> R900-05 Invoice Lines - one or many invoice lines for each combination of Site and Invoice Data | Data interface correction | Supporting Docs | Interfaces | Swagger MHHSP - ERI011B - ECS Reports - External
MHHS-DIN-860 | RG |  | 2023-12-21 | SRO |  | Rob Golding | SRO Design | Clarification on Webhook callback responses | At present the webhook callbacks are limited in their responses to 200 & 207. The extent of the responses needs to align with the other DIP APIs |  | Implemented | Design gap |  |  | Interim Release 5.3 |  | Aligning participant systems with the DIP in terms of HTTP responses, added in a standard set of response codes to be used in the Swagger. Also described are how HTTP responses received from the DIP should be interpreted, and what HTTP responses the DIP is expecting back from participants webhooks in the E2E Architecture document. | Data interface correction | Supporting Docs | Various documents | Swagger E2E Architecture
MHHS-DIN-861 | RG |  | 2023-12-21 | SRO |  | Rob Golding | SRO Design | Clarification on Webhook callback responses | At present the webhook callbacks are limited in their responses to 200 & 207. The extent of the responses needs to align with the other DIP APIs |  | Implemented | Design gap |  |  | Interim Release 7 |  | Aligning participant systems with the DIP in terms of HTTP responses, added in a standard set of response codes to be used in the Swagger. Also described are how HTTP responses received from the DIP should be interpreted, and what HTTP responses the DIP is expecting back from participants webhooks in the E2E Architecture document. | Data interface correction | Supporting Docs | Various documents | Swagger E2E001 Architecture Document
MHHS-DIN-862 | RG |  | 2024-01-02 | SRO |  | Rob Golding | SRO Design | REP901 missing event code | The eventcode on REP-901 need correcting to [DUoSEmbeddedLDSOAggInvData] & [DUoSSupplierAggInvData] (or do we have two reports?) |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | Update the following REP-901 data items as follows [DUoSEmbeddedLDSOAggInvData] & [DUoSSupplierAggInvData] to ensure that ECS reports align with naming standards and ensure that Swagger aligns with ECS reports catalogue. | Data interface correction | Supporting Docs | Interfaces | ESC Report, Swagger
MHHS-DIN-863 | SB |  | 2024-01-03 | Kraken | 27359 | Henri Naef | Software Provider | IF-019/020 Discrepancy between E2E and Swagger | It looks like in the e2e guide there’s no mention of an M1 block in the common block. However in the swagger documentation for IF019 and IF020 there is. What’s weirder is that for both of those there is no M0 block which the e2e guide says there should be." |  | Open - awaiting assessment |  |  |  | Post Go-live Release |  | Solution under review/discussion | Data interface correction | Supporting Docs | E2E Architecture Document | E2E001 Architecture Document
MHHS-DIN-864 | ZH |  | 2024-01-08 | SJW |  | Sarah Jones | Central Body | CR024 - Update of two data items | As flagged at the last DAG and in our email on 21 Dec, RECCo believes there are two incorrect data items in the MHHS design: Manufacturer Code should be Manufacturers Make and Type CSS Registration Request Id should be CSS Registration Id. We believe failure to correct these data item in line with approved CR024 (particularly the CSS Registration Id) may lead to parties including the wrong data items within their design, impacting testing outcomes (both SIT and Qualification) and leading to operational issues post go live. | CR024 | Implemented | Error/Correction |  |  | Interim Release 7 |  | Update the names of both data items in the Swagger and DES138, in the relevant areas. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-865 | RG |  | 2024-01-12 |  |  |  |  | EMSE ID example has non-hexadecimal chars | DES-138 and the swagger have a non-hex character in the example |  | Closed | [5 empty] | Update example to remove leading S character
MHHS-DIN-866 | SW | DIN-880 | 2024-01-16 | Stark | 29309 | Jon Dennis | Software Provider | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD |  | Implemented | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD. Swagger updated to align. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-867 | RG |  | 2024-01-16 | PDA |  | Richard French |  | Remove all references to UDS & UMDS in E2E SA doc | Replace UMDS with UMSDS - multiple instances still exist |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | E2E documentation still contains references to UMDS - this needs to be removed and replaced with UMSDS | Data interface correction | Supporting Docs | Interfaces | E2E001 Architecture Document
MHHS-DIN-868 | RS |  | 2024-01-16 |  | 19802 | Rob Short | SI Design | Correction of Advanced Data Service Validation and Estimation (Meth002) | Following review and participant comments, multiple updates are required to correct SDS references in the ADS method statement |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | Updates made to all sections of MHHSP-METH002_ADS_Validation_Estimation | Method statement correction | Supporting Docs | Method Statement | METH002
MHHS-DIN-869 | RS |  | 2024-01-16 |  | 19802/20645 | Rob Short | SI Design | ADS Method Alignment | Updates to the ADS estimation methods |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | Update to section 3 of of MHHSP-METH002_ADS_Validation_Estimation | Method statement correction | Supporting Docs | Method Statement | METH002
MHHS-DIN-870 | SW |  | 2024-01-17 | St Clements | 26647 | Madison Layton | SI Design | IMS-SendMTD variant for IF-035 does not contain properties B070, B071 and B019 to align with DES-138 | IMS-SendMTD variant for IF-035 does not contain properties B070, B071 and B019 to align with DES-138 - which identifies this variant of a copy of the variants DSAppAccepted and MSAppAccepted |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | Swagger 1.7 IF-035-IMS-SendMTD: should be updated to include B070, B071 and B019 as optional fields in this variant. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-871 | RG |  | 2024-01-17 | SRO |  | Rob Golding | SRO Design | Changes to E2E SA doc & Swagger for replay message version support | The E2E SA doc (& swagger) needs to be updated to include message version support for replay |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | E2E SA document include a description on message versioning for message replay. This includes changes to section 4.9 and 8.5.2 of the E2E001 design document, removal of section 5.5 (it has been combined into section 4.9). Also updates to Swagger to add version in the MessageRequest object. | Technical corrrection | Supporting Docs | Interfaces | E2E001 Architecture Document Swagger
MHHS-DIN-872 | RS |  | 2024-01-18 | IMServ | 30201 | Rob Short | SI Design | Historic consumption data following the IF-015 request | Conflicting information in the NOTES section: “The structure and content of this message will be subject to further discussion as part of the 'DIP Detailed Design', as the exact way in which this requirement/functionality is realised may depend on the DIP Solution option(s) chosen. The basis of the functionality is that participants will be 'REPLAYED' facsimiles of the previously submitted IF-021 (SP Consumption Submission) / IF-013 (SP Defaulted) Records - however it may be possible that some kind of 'blended' response, as eluded to here, is also possible.” |  | Implemented | Design gap |  |  | Interim Release 7 |  | Removal of Interface note on IF-16 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-873 | RS |  | 2024-01-19 | Elexon | 21459 | Phil Milmine | Central Body | Correction to VAS Method Statement | Amendment to section 3.28 around “VAS Defaulting” and the report linked to this process (REP-007) to reflect the manual steps that Elexon would need to take to enable this. |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | Amend text to 17. VAS Re-run where Initial VAR incomplete due to missing MDS or CDCA data 3.28 In the event that the VAS is unable to complete an Initial VAR due to missing data from MDS or CDCA, the VAS shall use replacement data at BSCCo’s discretion to re-run by BM Unit, as per a normal VAS run. Substituted data must be reported to Market Participants. | Method statement correction | Supporting Docs | Method Statement | METH006
MHHS-DIN-874 | RG | DIN-829 | 2024-01-23 |  |  | Rob Golding | SRO Design | Consent Granularity not nullable and N - no consent | Implement DIN-829 in 5.x swagger and update DES138 accordingly |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Swagger/ DES138 updated so that DI-838-Supplier-Proposed-Consent-Granularity and DI-017 Consent Granularity includes N - No Consent in the list of allowable values. DI-838 updated to be Mandatory no nulls. DI-838 description updated to align with the data item name in Swagger. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-875 | SW |  | 2024-01-23 | Kraken | 31011 | Angelos Rizoyannis | SI Design | Swagger objects and descriptions are missing | Missing `type: object` - for the following blocks B079, B080, B081, B082, B083, B090, B091 - Missing `description: ...’ object for R901-08 - Incorrect description - IF-004-Payload08, IF-006-MeterRemoval.CustomBlock, IF-006-MeterExchange.CustomBlock |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Missing `type: object` - for the following blocks - B075, B076, B079, B080, B081, B082, B090, B091 - Missing `description: ...’ object for R901-08 - Incorrect description - IF-004-Payload08, IF-006-MeterRemoval.CustomBlock08, IF-006-MeterExchange.CustomBlock08 Update Swagger to fix above issues. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-876 | RG |  | 2024-01-24 | SRO |  | Rob Golding | SRO Design | IF-003 LDSO routing is secondary not always | DES138 has IF-003 LDSO routing incorrectly specified, the routing is secondary not always |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | Update DES138, IF-003 LDSO routing is secondary not always | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-877 | RG | DIN-620 | 2024-01-24 |  |  | Rob Golding | SRO Design | IF-001 Remove EES (CR023) | DIN-620 was not fully implemented, EES is still mentioned in DES138 IF-001 |  | Implemented | Error/Correction |  |  | Interim Release 7 |  | EES removed DES138 IF-001 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-878 | RG | DIN-870 | 2024-01-17 | St Clements | 26647 | Madison Layton | SI Design | IMS-SendMTD variant for IF-035 does not contain properties B070, B071 and B019 to align with DES-138 | IMS-SendMTD variant for IF-035 does not contain properties B070, B071 and B019 to align with DES-138 - which identifies this variant of a copy of the variants DSAppAccepted and MSAppAccepted |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Updated Swagger IF-035-IMS-SendMTD: to include B070, B071 and B019 as optional fields in this variant | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-879 | RG | DIN-849 | 2023-12-14 |  |  | Madison Layton | Software Provider | Change B099 to be a single block rather than a list in IF-035 | In IF035 SDS-MDROutcome variant, make B099 a single block in the swagger rather than a list. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Updated Swagger IF035 SDS-MDROutcome variant, and made B099 a single block rather than a list. This has also necessitated in an update to DES138 to the routing information for IF-035. | Data interface correction | Supporting Docs | Interfaces | Swagger, DES138
MHHS-DIN-880 | MF | DIN-866 | 2024-01-24 |  |  | Jon Dennis | Software Provider | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Updated “MAIN” in DI-059-Meter-Type enum in swagger, to be "MAIN_" to align with ISD | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-881 | MF | DIN-825, DIN-811 | 2024-01-24 | Avanade |  | Rob Golding | SRO Design | IF-024 missing required attributes in blocks | IF024 SN-NoComms CustomBlock required B057 IF-024-SN-RemoteDisabled required B069, B057 |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Update swagger with the following: IF024 SN-Vacant CustomBlock required B057 IF024 SN-NoComms CustomBlock required B057 IF024 SNRemoteEnabled CustomBlock required B057, B069 IF024 SNSupplierAC CustomBlock required B057, B058 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-882 | MF | DIN-835,836, 843 | 2024-01-24 | SRO |  | Rob Golding | SRO Design | New swagger file ErrorCodes to describe MHHS error messages and updates to error messages in DES138 | New swagger file (Response Codes schema) to capture all message and error codes from DES138 including RCP0000 (Message Success) and the following error codes: Error Code Error Text MSG1013 Invalid CertifcateIssuerName MSG1014 Certificate has expired MSG1039 Invalid MPAN MSG5001 Internal server error MSG5002 No data contained in request body MSG5003 Unable to determine correlationId requirement. Server configuration error or sender request error MSG5004 Internal server error.Payload not processed |  | Implemented | Design gap | DIP Users |  | Interim Release 5.4 |  | New swagger file (Response Codes schema) to capture all message and error codes from DES138 DES138 updated with RCP0000 (Message Success) and the following error codes: Error Code Error Text MSG1013 Invalid CertifcateIssuerName MSG1014 Certificate has expired MSG1039 Invalid MPAN MSG5001 Internal server error MSG5002 No data contained in request body MSG5003 Unable to determine correlationId requirement. Server configuration error or sender request error MSG5004 Internal server error.Payload not processed | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-883 | RG |  | 2024-01-24 | SRO | 31749 | Matt McKeon | SRO Design | Data item clashes between DES138 and ECS Reports | We have noticed that there are some DI-REF numbers which have been used twice in DES138 and ERI011B. - Specifically the newer data items introduced for migration start in the 500s, when these are also used in ECS Reports. |  | Implemented | Error/Correction | ECS |  | Interim Release 7 |  | Move duplicated ECS numbers to an unused range | Reporting correction | Supporting Docs | ECS Reports | ERI011B
MHHS-DIN-884 | BK |  | 2024-01-26 | SRO |  | Kevin Spencer | SRO Design | CR032: Replacement of REP080 to use the P210 | The revised design would require: Elexon revise the build of the P0210 to include both non-migrated and migrated consumption. The format and structure will not change. The ESO ingest the P0210, ensuring that its integration and middleware systems can process the file. As per the the integration and middleware diagram, two systems (LIMS and CIS/MFT) will need configuration changes. The ESO regression test its Revenue systems based on the revised P0210 to ensure it continues to meet the requirements for TNUoS and BSUoS reporting. After the end of the Transition Period, if the ELEX-REP-080 report was developed, the existing P0210 file and associated processing of that file would become redundant. | CR032 | Implemented | Change Request |  |  | Interim Release 7 |  | Updates made to the following artefacts; Amended METH006 section 3.7 Removal of REP080 in the ECS Report Update wording in BP020 step 75 to reference the P0210 and subsequent BPD doc | Data interface correction | Supporting Docs | Interfaces | METH006 ESC Report BP020 and BPD020
MHHS-DIN-885 | BK |  | 2024-01-26 | SRO |  | Matt McKeon | SRO Design | Add URLs pointing to new DTC format definition documents in ERI011B | Update four tabs of ERI011B to add a URL pointing to new DTC format definition documents for these reports |  | Implemented |  |  |  | Interim Release 7 |  | Update MHHS-REP-D0369 to say ‘Defined in DTC format as D0401 at: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx · Update MHHS-REP-D0370 to say ‘Defined in DTC format as D0402 at: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx · Update MHHS-REP-D0373 to say ‘Defined in DTC format as D0403 at: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx · Update MHHS-REP-D0374 to say ‘Defined in DTC format as D0404 at: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx Grey out all the reports specified above | Reporting correction | Supporting Docs | Interfaces | ERI011B
MHHS-DIN-886 | MF |  | 2024-01-26 | St Clements |  | SCS | Software Provider | Addition of 905 existing meter listing block to all events in IF-006 | Add B905 (existing meter listing) block for all IF-006 event codes in Swagger |  | Implemented |  |  |  | Interim Release 7 |  | Add B905 (existing meter listing) block for all IF-006 event codes in Swagger | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-887 | MF |  | 2024-01-26 | St Clements |  | SCS | Software Provider | Addition of 905 existing meter listing block to all events in IF-006 | Add B905 (existing meter listing) block for all IF-006 event codes in Swagger |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Add B905 (existing meter listing) block for all IF-006 event codes in Swagger | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-888 | SW |  | 2024-01-29 | Kraken |  | Angelos Rizoyannis | Software Provider | Property "type: object" missing from IF-024 variants in Swagger | Property "type: object" missing from IF-024 variants in Swagger. This needs to be added to all variants where this is missing. |  | Implemented |  |  |  | Interim Release 7 |  | Property "type: object" missing from IF-024 variants in Swagger. This needs to be added to all variants where this is missing. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-889 | SW |  | 2024-01-29 | Kraken |  | Angelos Rizoyannis | Software Provider | Property "type: object" missing from IF-024 variants in Swagger | Property "type: object" missing from IF-024 variants in Swagger. This needs to be added to all variants where this is missing. |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Property "type: object" missing from IF-024 variants in Swagger. This needs to be added to all variants where this is missing. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-890 | RS |  | 2024-01-29 | CGI |  | Dave Webster | Software Provider | DI-038 (LInked Import/Export Mpan) description | Confusion over wording in DI-038. Where more than one import MPAN exists, this shall be populated with the Primary Import MPAN |  | Implemented |  |  |  | Interim Release 8 | 2024-03-20 | Remove wording 'Where more than one import MPAN exists, this shall be populated with the Primary Import MPAN' from all DI-038 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-891 | SB |  | 2024-01-30 | St Clements | 21513 | SCS | Software Provider | DI-241 - SUPC routing on IF-037 incorrect, should be SUPS | The primary routing for MSDeAppUpdate and DSDeAppUpdate is incorrect, XMSC and XDSC is the currently appoint SP but the flow needs to go to the already de-appointed SPs |  | Implemented |  |  |  | Interim Release 8 | 2024-03-20 | Update Primary Routing to show Previously de-appointed Data Service/ Metering Service | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-892 | RG |  | 2024-01-31 | RDG |  | RDG | SRO | Message Versioning Support: Create DIPMessage variant for egress | Split DipMessage in two, one for ingress (current version) and another for egress (new) in order to support multiversion messages on egress for replay/requeue |  | Implemented |  |  |  | Interim Release 8 | 2024-03-20 | Add new DIPEgressMessage to the swagger in order to split the incoming and outgoing APIs to allow multiversion support | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-893 | RG |  | 2024-01-31 | BJSS |  | Soniya | Software Provider | Regex for GSP Correction factor | We want to check if the regex is correct for GSP Group Correction Factors: ^-?\d{1,9}\.\d{9} The highlighted section suggests the – is optional but GCFs are always positive. Can the regex be updated to reflect this? |  | Implemented |  |  |  | Interim Release 7.1 |  | Regex update in Swagger to enforce only positive numbers. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-894 | RG |  | 2024-01-31 | SIMs & Ems |  | John | Software Provider | DI-123-SSC is nullable in IR7, needs to be the same in IR5.x | B032 eg on IF-002 has property SSC which was made non nullable in 1.5.2 or 1.5.3 has been left nullable in 1.7 |  | Implemented | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Update B032 eg on IF-002 has property SSC so that it is non nullable | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-895 | MH |  | 2024-02-01 | St Clements | 31597 | Virginia Patey | Software Provider | REP002s vs IF-21s for DUoS Billing. Follow up from DIN340 | Change required to MDS Method Statement... DIN-340 was raised by UKPN to highlight the fact that while DNOs were to receive the correct IF-021 data, the data on the DUoS Report would also include meter data for most MPANs with a connection type <> ‘W’. Additionally, given the fact that the DNOs require meter data for all sites via either the REP002s or the IF-021s, using different data items to determine the inclusion or exclusion from a particular delivery method risks DNOs not receiving data for some MPANs via either route and thereby negatively impacting their invoicing. Please note that an MS Site Specific LLF Id indicator of ‘B’ (Site Specific Import) or ‘D’ (Site Specific Export) does NOT equate to a connection type <> ‘W’. In fact the MPANs with a MS Site Specific Indicator of ‘B’ or ‘D’ is a very small subset of those with a connection type <> ‘W’. For the avoidance of doubt, the use of the term ‘site specific’ for billing types and MS Site Specific LLF Id indicators are separate things and do not equate to one another. Required Solution: We require the rules for what should be included on the DUoS Report (i.e. the wording for 17.3) to be changed to: The DUoS Report calculations shall only be undertaken for SPC data that is for MPANs with a connection type = ‘W’ 17.4 is not required as DNOs should be using all IF-021 in site specific billing. |  | Implemented | Error/Correction | ECS, DNOs |  | Interim Release 8 | 2024-03-20 | Rules for what should be included on the DUoS Report (i.e. the wording for 17.3) to be changed to: The DUoS Report calculations shall only be undertaken for SPC data that is for MPANs with a connection type = ‘W’ 17.4 is not required as DNOs should be using all IF-021 in site specific billing. | Method statement correction | Supporting Docs | Method Statement | METH007 ERI011B - ECS Reports
MHHS-DIN-896 | MH |  | 2024-02-06 | ESG | 32706 | Patricia Parker | Software Provider | ISD v5.5 (Ref 265) | The two new entities M20 & M21 (DIN-754) do not appear in the table of contents. Can these be added? |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Update the table of contents to include two new entities M20 & M21 (from DIN-754). | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-897 | RG |  | 2024-02-06 | Flui | 32997 | Jason Jackson | Software Provider | IF-001 Change Of Supplier s0 block needs to mandatory | s0 block needs to mandatory, DIN-785 missed off the S0 block, ok in 5.4 not 7. the A0 block is marked as mandatory, it should be S0. (the orignial published DIN stated this was the S1 block, this is an error, in fact it should be the s0 block) |  | Implemented | Error/Correction |  |  | Interim Release 7.1 |  | Minor swagger update to enforce a manadatory field | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-898 | MH |  | 2024-02-07 | Elexon | 31846 | Derek Weaving | Central Body | REP-003 fields - Clarification Request | DI-339 BM Unit Allocated Demand Disconnection Volume Losses should not be in the REP003 The DDE does not calculate losses separately and they are already included in DI-341 volume that sums across all CCCids including the ones for losses. |  | Implemented | Error/Correction | Suppliers |  | Interim Release 7.1 |  | Remove DI-339 and the DI-370 from the REP-003 Swagger update and ECS Report | Technical corrrection | Supporting Docs | Interfaces | Swagger ERI011B - ECS Reports
MHHS-DIN-899 | MH |  | 2024-02-07 | Elexon | 32697 | Rashmi Radhakrishnan | Central Body | IR7 Changes to ISD | In IR7, DIN-759 included an update to ISD Entitiy M17. tHis update was only partially completed. This DIN is to correct it and to add Meter Group to the Entity and also to add N to M15 as previously agreed |  | Implemented | Error/Correction |  |  | Interim Release 7.1 |  | Add Meter Group to the Entity - M17 Add N - No Consent to M15 | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-900 | RG |  | 2024-02-07 | SRO Design |  | RG | SRO Design | IR7 E2E SA Obfuscation rules require updating | Data items that are MPIDs need to be obfuscated to 'XXXX' rather than 'xxxx' so the regex remains unbroken |  | Implemented | Error/Correction |  |  | Interim Release 7.1 |  | MPIDs that are obfuscated will be 'XXXX'. Avanade change, PPs need to be aware. | Technical corrrection | Supporting Docs | Interfaces | E2E Architecture
MHHS-DIN-901 | RG |  | 2024-02-08 | SRO Design |  | RG | SRO Design | DES138 does not include CR23 opting in for MDRs | The IR7 version of DES138 does not include the 'opting' information for MDRs. The following needs to be icluded as opted in PUB-006 [MeterInstall], [MeterRemove], [MeterExchange], [MeterUpdate] PUB-008 [EnergisationStatusChange] PUB-026 [ConsentGranularity], [SMSO], PUB-024 [SN-RemoteEnable], [SN-RemoteDisable], [SN-NoComms] |  | Implemented | Design gap |  |  | Interim Release 7.1 |  | Update DES138 to include the 'opting' information for MDRs in the following PUBS; PUB-006 [MeterInstall], [MeterRemove], [MeterExchange], [MeterUpdate] PUB-008 [EnergisationStatusChange] PUB-026 [ConsentGranularity], [SMSO], PUB-024 [SN-RemoteEnable], [SN-RemoteDisable], [SN-NoComms] | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-902 | MH |  | 2024-02-09 | SRO | 33170 | Andrew Margan | Central Body | Reverse Migration Consistency | Step 190 of MHHS-DEL971 - BPD001 and DEL965 BPM001 - Change Of Supply - Reverse Migration suggest the incoming supplier has a choice of whether to reverse migrate or not. This isn't the case; a reverse migration will only happen where the incoming supplier is not qualified on the MHHS TOM |  | Closed | Error/Correction |  |  |  |  | The Process step is showing the Incoming Supplier choosing whether to start reverse migration or not. In this scenario, the Incoming Supplier is not MHHS qualified. However, they will have to determine if it is a reverse migration scenario based on the info in the D0260/D0217. In that respect they must choose whether they need to follow reverse migration or legacy process
MHHS-DIN-903 | MF |  | 2024-02-12 | Elexon | 34297, 34973 | Raina Jain | Central Body | Missing/ incorrect BPD011 step | Step 211 is missing from “(BP011A) MHHSP-BPD-011” tab in MHHSP-BPD011 - Change of Con Type or Market Segment document." Correct step 275 to show that this applies for successful meter exchanges |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Add step 211 to BPD011 to align with BP011. This shows the Metering Service receiving the Appointment Response (PUB-035) from Registration Service. Update step 275 to show that this applies for successful meter exchanges | Process Model correction | Supporting Docs | Business Process Description | BPD011
MHHS-DIN-904 | RG | DIN-924 | 2024-02-12 | SRO |  | Rob Golding | SRO Design | Missing parameters in webhook callback | The definition in the webhook callback in swagger is missing the definition - $ref: '#/components/parameters/CommonSignatureHeader' - $ref: '#/components/parameters/CommonSignatureDateHeader' - $ref: '#/components/parameters/CommonSHA256Header' - $ref: '#/components/parameters/CommonSignatureCertifcateHeader' |  | Implemented | Clarification - No change required |  |  | Interim Release 5.5 |  | Update to swagger to include missing parameters; aligns with CoCo | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-905 | RG | DIN-864 | 2024-02-14 | SRO |  | Rob Golding | SRO Design | B033 block meterManufacturer IR7 | B033 block meterManufacturer was renamed to manufacturersMakeAndType it wasn't renamed in the 'required' properties |  | Implemented | Error/Correction |  |  | Interim Release 7.1 |  | Update B003 requried fields to include manufacturersMakeAndType | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-906 | RG | DIN-925 | 2024-02-14 | SRO Design |  | Rob Golding | SRO Design | Add MPO Encrypted header parameter to callback | Add a parameter to the callback so that the MTLS cert can be authenticated by the MTLS connection. No impact on MPs, Avanade improving the secuirty handshake on the callback |  | Implemented | Design gap | Avanade |  | Interim Release 5.5 |  | Add MPO Encrypted header parameter to callback | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-907 | RG | DIN-926 | 2024-02-14 | SRO Design |  | Grant Sutcliffe | Avanade | Response codes on delete operations | Standardise response message for successful delete operations on API calls -204 needs to have the text 'No Content' . Need to add other response codes in-line with the other APIs |  | Implemented | Design misaligned |  |  | Interim Release 5.5 |  | Standardise response message for successful delete operations on API calls -204 needs to have the text 'No Content' . Need to add other response codes in-line with the other APIs | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-908 | MF | DI-249 | 2024-02-15 | St Clements |  | Madison Layton | Software Provider | Validation of Appointment start times | Move REG1032 from Migration Only Validation Rules to BAU Validation Rules section in IF-031 |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Move REG1032 from Migration Only Validation Rules to BAU Validation Rules section in IF-031 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-909 | RS |  | 2024-02-15 | EDW | 34934 | Darren Kay | Software Provider | Duplicate requirement reference used in MHHS-E2E002 Requirements v3.1 document | E2E1009 requirement reference is used for Level 4 Processing Times (Asynchronous) and Unplanned Outages in MHHS-E2E002 Requirements v3.1 document. Adjustment required to one of the references |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Remove duplicate reference to requirement in E2E002 doc. | Requirement correction | Supporting Docs | Requirement correction | E2E002 Requirements
MHHS-DIN-910 | MF |  | 2024-02-16 | SRO Design |  | Mike Fensome | SRO Design | Remove sending of IF-041 for invalid meter readings from SDS method statement | SDS Method Statement 2.37 refers to SDS sending an IF-041 where reads are invalid. This is not allowed for in the design and should be removed |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Remove sending of IF-041 for invalid meter readings from SDS method statement | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-911 | MF | DIN-849 | 2024-02-16 | St Clements |  | Madison Layton | Software Provider | Update B099 block to show that it is not an array | Update B099 block (IF-035) in DES138 to align with swagger to show that it is not an array |  | Implemented | Error/Correction |  |  | Interim Release 7.1 |  | Updated B099 block (IF-035) in DES138 to show that it is not an array | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-912 | RG |  | 2024-06-15 | SRO Design |  | Rob Golding | SRO Design | Incorrect 1.7 reference in 1.5.4 swagger | There was a reference to a 1.7 object from 1.5.4. module which meant the 1.5.4. swagger wasaa not resolving correctly |  | Implemented | Error/Correction |  |  | Interim Release 5.4 |  | Swagger rebuilt | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-913 | SB | DIN-503 DIN-780 | 2024-02-14 | St Clements | 19885 | Madison Layton | Software Provider | Missed Update to DES138 | There was a change in swagger in IR4 for senderUniqueReference and transactionID under DIN503. However this wasn’t folded into the Interface Catalogue examples. The examples should have been removed from The DES138 Examples as DIN-780 these still appear in the Interface catalogue |  | Implemented | Clarification - No change required |  |  | Interim Release 8 | 2024-03-20 | Examples against senderUniqueReference and transactionID will be removed from DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-914 | MF |  | 2024-02-19 | EDW |  | Darshun Chauhan | Software Provider | Update DI-082 (Settlement Period Effective to Date/Time) validation rule on IF-021 | Align DI-082 validation rule to check for periods ending on the hour or half-hour to align with MDS requirements |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Update DI-082 (Settlement Period Effective to Date/Time) validation rule on IF-021 to check for periods ending on the hour or half-hour to align with MDS requirements/ build | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-915 | RG | DIN-801, DIN-852 | 2024-02-19 | BJSS |  | Soniya Jakhu | Software Provider | Missing swagger updates to align with DIN-801 - ECS reports REP006 | 1. DIN-801 updates not communicated - Add Supplier R015 block to REP006 2. DI-375 needs to be nullable 3. DI-364 needs to be nullable 4. DIN-852 Updates not communicated to Swagger REP-006 - R003 block |  | Implemented |  |  |  | Interim Release 7.1 |  | Update Swagger to 1. Add Supplier R015 block to REP006 2. DI-375 needs to be nullable 3. DI-364 needs to be nullable 4. REP-006 - R003 block | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-916 | MH |  | 2024-02-21 | Elexon | 35702 | Mike Ceney | Central Body | IF-36 Obfuscation | In the IF-036 flow it states that DI-800 Service Provider Appointment Scenario is obfuscated for MDS, can you please clarify why this is the case. MDS needs this information to determine if this is for Migration (CoA or CoS lead), or a general CoA, it treats the interface differently based on the scenario |  | Implemented | Design gap | Avanade, Helix |  | Interim Release 7.1 |  | Removed the obfuscation of DI-800 in Blocks B014 and B015 in IF-36 | Data interface correction | Supporting Docs | Interfaces | DES138 & Avanade change
MHHS-DIN-917 | RS |  | 2024-02-22 | Callisto | 31823 36576 | Seth Chapman | Data Service Provider | Reverse Migration Process - Missing D0148 | In the reverse migration scenario there is a variation to the standard legacy process in that the D0148 groups for the old agent (271 to DC And 274 to MOP) would include the MHHS services rather than a previous "current world" agent. The documents also do not mention that the new supplier will also appoint a DA |  | Closed | Design gap |  |  |  |  | Migration Design Document (DEL961) updated to include the D0148 for the new DC, DA and MOP. Discussion required on if the old agent/service should be included as Participant believes it could be a bigger change to not include Following review, a CR would be required to make additional amendments to the existing D0148 to include old agents, response provided back to initiator | Process Model correction | Supporting Docs | Supporting document | DEL961
MHHS-DIN-918 | RG |  | 2024-02-22 | SRO Design |  | Rob Golding | SRO Design | DES-138 IF_LIST table incomplete | IF_LIST tab does not include all the MDR interfaces |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Add interfaces IF-061, IF-062, IF-063, IF-064, IF-065 to Interface List in DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-919 | RS | DIN 247, DIN 434 | 2024-02-22 | IMServ | 35161 | Bevis Rotherham | Software Provider | Reverse Migration - IF003 missing supplier fields | The MHHS-DEL961 - Migration Design Document states that IF-003 will be updated to include RevMig Incoming Supplier MPID and RevMig Incoming Supplier Effective From Date fields, however, even in the latest IR7 DES138 document these fields do not exist. There was DIN-247 which specifically referenced these fields and the Business Rules and this was closed as supposedly captured as part of DIN-434, however, DIN-434 doesn't show these fields being implemented, and the latest DES138 doesn’t show these fields against the IF-003. |  | Implemented | Error/Correction |  |  | Interim Release 7.1 |  | Added B002 block to DES138 IF-003 to provide the Incoming Supplier DIP ID, MPID and Effective From Date on a Reverse Migration de-appointment. Note, all Suppliers will need to be allocated a DIP ID in advance of migration. Required fields in swagger equire update to align with DES-138 | Data interface and Swagger correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-920 | RS |  | 2024-02-22 | SCS | 36031 | Daniel Tadecicco | Central Body | DI-250 IF-007 Migration Rejection Code | Currently, the IF-007 can only be rejected using Level 4, MPRS other IFs use a reusable function to apply Migration rules with level 5 validation. We would like to use this function for the IF-007, using the current level 4 rejection would require a specific function for the IF-007 which would not be as maintainable and possibly confusing for receiving parties. |  | Implemented | Design gap | All Participants |  | Interim Release 8.1 |  | Added new validation REG9002 to IF-007 to reject if Reverse Migration is in progress | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-921 | RG | DIN-913 | 2024-02-22 | IMServ |  | Liam Lowey | Software Provider | DES138 - Sender Unique reference example is incorrect | The example sender Unique reference on the DIP_COMMON tab does not contain the full interface id in the string |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | The senderUniqueReference example removed from DIP Common as per DIN 913 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-922 | RG |  | 2024-02-22 | BJSS |  | Sergio Gomes | Software Provider | IF-014 CustomBlock Required list needs updating | Needs to align with properties, should be B900 not B900List |  | Implemented | Error/Correction |  |  | Interim Release 7.1 |  | Required properties should be B900 not B900List only wrong in v7, not v5.4) | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-923 | MF |  | 2024-02-23 | PDA |  | Richard French | Data Service Provider | Clarification on Data Service sending consumption data for periods 47/48 during BST | Clarification around who should send consumption data for settlement periods 47 and 48 in the case of New Connections, Migration and who will receive the IF-013 where no data is provided for HH47 and HH48 during BST |  | Implemented | Design misaligned |  |  | Interim Release 7.1 |  | In the case where no previous Data Service exists following a Change of Data Service ( eg New Connection, Migration) , in BST the responsibility for providing the initial hour of consuption data for Settlement periods 47 and 48 sits with the newly Appointed Data Service. Note the IF-036 notifies whether there is a previous Data Service via Block B005. The Data Service should estimate these periods in line with the relevant Method Statement. The Incoming Data Service will be notified of default data via the IF-013 if no data is submitted for Settlement Periods 47 and 48. However, the Incoming Data Service is not expected to provide data for these two settlement periods where a previous Data Service exists. Minor amendment to IF-021 validation rule to allow the incoming Data Service to send IF-021 for periods 47 and 48 where no previous Data Service exists | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-924 | RG | DIN-904 | 2024-02-12 | SRO |  | Rob Golding | SRO Design | Missing parameters in webhook callback | The definition in the webhook callback in swagger is missing the definition - $ref: '#/components/parameters/CommonSignatureHeader' - $ref: '#/components/parameters/CommonSignatureDateHeader' - $ref: '#/components/parameters/CommonSHA256Header' - $ref: '#/components/parameters/CommonSignatureCertifcateHeader' |  | Implemented | Clarification - No change required |  |  | Interim Release 7.1 |  | Update to swagger to include missing parameters; aligns with CoCo | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-925 | RG | DIN-906 | 2024-02-14 | SRO Design |  | Rob Golding | SRO Design | Add MPO Encrypted header parameter to callback | Add a parameter to the callback so that the MTLS cert can be authenticated by the MTLS connection. No impact on MPs, Avanade improving the secuirty handshake on the callback |  | Implemented | Design gap | Avanade |  | Interim Release 7.1 |  | Add extra parameter the webhook callback. No impact on PPs | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-926 | RG | DIN-907 | 2024-02-14 | SRO Design |  | Grant Sutcliffe | Avanade | Response codes on delete operations | Standardise response message for successful delete operations on API calls -204 needs to have the text 'No Content' . Need to add other response codes in-line with the other APIs |  | Implemented | Design misaligned |  |  | Interim Release 7.1 |  | Swagger update to include response body on codes where they are expected. Awating details. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-927 | RG | DIN-928 | 2024-02-23 | SRO Design |  | Jon Dennis | Stark | IF-037 mandatory block for [DS¦MS]DeAppUpdate event codes | the B010/B011 blocks are mandatory for the [DS¦MS]DeAppUpdate event codes. |  | Implemented | Design misaligned |  |  | Interim Release 5.5 |  | Update swagger to include required blocks for IF-037 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-928 | RG | DIN-927 | 2024-02-23 | SRO Design |  | Jon Dennis | Stark | IF-037 mandatory block for [DS¦MS]DeAppUpdate event codes | the B010/B011 blocks are mandatory for the [DS¦MS]DeAppUpdate event codes. |  | Implemented | Design misaligned |  |  | Interim Release 7.1 |  | Update swagger to include required blocks for IF-037 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-929 | BK |  | 2024-02-23 | UKPN |  | David Yeoman | Network Operator | Change to NFR E2E1009 for DNO & IDNO roles (LDSO, UMSO, Registrations) | The programme has specified several Non-Functional Requirements that market participants must adhere to. Specifically, E2E1009 states: All Services shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes: - up to average hourly volume, mean response time of 6s or less - up to average hourly volume, 90th percentile response time of 12s or less - from average hourly to peak hourly volume, mean response time of 10s or less - from average hourly to peak hourly volume, 90th percentile response time of 16s or less DNOs and iDNO’s intend to use a ‘DIP Adaptor’ to facilitate interfacing to the DIP. The DIP adaptor provides Level 3 validation. Each ‘back office’ system that connects to the DIP Adaptor under each of the 3 DNO and iDNO roles of, Registration Services, UMSO & LDSO is expected to perform Level 4 validation. These DNO and iDNO systems cannot provide the requested Level 4 technical validation responses within 6, 10, 12 or 16 seconds as detailed in E2E1009. | CR040 | Implemented | Change Request | iDNOs, DNOs |  | Interim Release 8 | 2024-03-20 | The change being proposed is that all DNO and iDNO roles and systems are not required to meet the current specified asynchronous response timeframes of E2E1009 NFR. We request the description for E2E1009 be updated to read: All roles under DNO and iDNOs, namely Registration Services, UMSO & LDSO shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes - 60 minutes or less. This should exclude IF-021 for which there is a separate NFR due to the anticipated volumes. This will ensure alignment with the Operational Choreography " | Technical corrrection | Supporting Docs | Interfaces | E2E002 - Requirements
MHHS-DIN-930 | RG | MHHS-DIN-931 | 2024-02-26 |  |  | Rob Golding | SRO Design | Clarification of response codes that need an associated response body in Swagger | Design need to catch up with implementaton and the 400 response needs a response body for /dip-channel/{id} API |  | Implemented | Design gap |  |  | Interim Release 5.5 |  | StandardResponse is included for: 201 - StandardResponse includes an array of StandardResponseBodyType 207 - StandardResponse includes an array of StandardResponseBodyType 400 - if the response is generated by APIM. It has a single StandardResponseBodyType contained in the StandardResponse. (APIM does not deal with individual payloads contained in a request). If the response is generated inside the DIP (L1 errors), an array of StandardResponseBodyType will be returned in the StandardResponse - one for each payload in the request. Responses for all other Status Codes do not contain StandardResponse. | Technical corrrection | Supporting Docs | Interfaces | Swagger, possibly E2E
MHHS-DIN-931 | RG | MHHS-DIN-930 | 2024-02-26 | SRO Design |  | Rob Golding | SRO Design | Clarification of response codes that need an associated response body in Swagger | Design need to catch up with implementaton and the 400 response needs a response body for /dip-channel/{id} API |  | Implemented | Design gap |  |  | Interim Release 7.1 |  | StandardResponse is included for: 201 - StandardResponse includes an array of StandardResponseBodyType 207 - StandardResponse includes an array of StandardResponseBodyType 400 - if the response is generated by APIM. It has a single StandardResponseBodyType contained in the StandardResponse. (APIM does not deal with individual payloads contained in a request). If the response is generated inside the DIP (L1 errors), an array of StandardResponseBodyType will be returned in the StandardResponse - one for each payload in the request. Responses for all other Status Codes do not contain StandardResponse. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-932 | RG |  | 2023-02-27 |  |  | Rob Golding | SRO Design | Replace references to /api.swaggerhub.com/domains/MHHSPROGRAMME with DIP Production URLs | The move to the DIP Production system will require a repointing of the references to the Swagger modules to the production Swagger repository |  | Open - awaiting assessment | Design misaligned |  |  | Post Go-live Release |  | Replace references to /api.swaggerhub.com/domains/MHHSPROGRAMME with DIP Production URLs, awaiting on DIP | Technical corrrection | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-933 | RG |  | 2024-02-26 |  |  | Rob Golding | SRO Design | Clarification of response codes that need an associated response body in Swagger | Design need to catch up with implementaton and the 400 response needs a response body for /dip-channel/{id} API |  | Closed | [5 empty] | Duplicate of DIN-930
MHHS-DIN-934 | RS |  | 2024-02-27 | St Clements | 36918 | Daniel Tadecicco | Central Body | IF-001 Migration Change of Supplier (MCS Appointment Scenario) | 003.outgoingSupplierDIPID is defined as Mandatory but for an MHHS Migration the old Supplier may not be MHHS Qualified, so we cannot set this B025.MPAN Energisation Status is defined as Mandatory but we will not have a value at the point we trigger the IF-001, which happens before the SP appointments are confirmed. The MHHS Energisation Status is created when the migration completes (IF-036 issued) B035List.importExportMPANSupplierDIPID is defined as Mandatory but the Supplier of an associated MPAN may not be MHHS Qualified. Further request to widen this DIN to other Forward Migration IFs - these items are also on the IF-002, IF-033 & IF-036 |  | Implemented | Data |  |  | Interim Release 8 | 2024-03-20 | Serveral solution options were discussed with SCS on how this might be resolved. Agreed solution is that REGS will populate a 'dummy DIP iD' ie. 9999999999 into the DIP ID field where required to populate a DIP ID but where the referenced party is not qualified. (This impacts IF-003, IF-002, IF-001, IF-033, IF-036) Add new valid value of U - Undetermined to DI-033 to allow a value to be populated during Migration. This will be updated with the actual Energisation Status at the stage the IF-036 is issued and the value has been set in Registration Service | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-935 | SB |  | 2023-02-27 |  | 34656 |  |  | correction of errors in DES240 (Transitional Scaling Weights) | when recently reviewing the transitional scaling weights we have noticed some errors in the values listed in NewCCC_Weights and Existing_CCCs tabs for losses. The scaling weight principles on first tab state that all losses should have a quality rating of 0.4, however on the NewCCC_Weight tab there are 19 Loss CCCs which have a Quality Rating (column G) of either 0.2 or 0.6 for losses - these should all be 0.4. This would change the Scaling Weight in column I. Similarly the scaling weights for losses, on the Existing_CCCs tab, for Measurement Classes F and G should 1.4 as these are equivalent to MC A (for losses). |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Update DES240 to amend Scaling weights for losses so all are 0.4 as detailed in ticket 34656 | Technical corrrection | Supporting Docs | Interfaces | DES240
MHHS-DIN-936 | RG |  | 2024-02-29 | Design Team |  | Rob Golding | SRO Design | HTTP response code back off & retry behaviour | Align E2E SA doc with the regime for each response code |  | Closed | Design misaligned | All Participants |  |  |  | Align E2E SA doc with the regime for each response code | Technical corrrection | Supporting Docs | Supporting document | E2E Architecture Doc
MHHS-DIN-937 | ZH |  | 2024-02-29 |  |  | John Wiggins/Matthew Breen | SRO Design | Align Migration design with wider design changes made for CR028 | The COS Migration tests continue to show EES receiving the IF-001. The EES instance of the IF-001 was removed from the COS process map and the interface catalogue as part of CR028. As such EES will not be able to process the IF-001 and it is inappropriate to include it as part of the baselined test scenarios. |  | Implemented | Design misaligned |  |  | Interim Release 8 | 2024-03-20 | Updates to be made to relevant Migration artefacts to align with the design changes to the COS process map and DES138 in relevance to EES not receiving IF-001. | Process Model correction | Migration | Process Model correction | BPM001, BPD001
MHHS-DIN-938 | MF |  | 2024-03-01 | PDA |  | Richard French | Data Service Provider | Confirmation of dates to use in the D0388 UMS Inventory | Confirm that the UMSO should populate the effective from date to align with the appointment date. So during BST, for example for a 1st July appointment the D0388 UMS Inventory should state 1 July (even though, where no previous Data Service exists, the UMSDS should calculate periods 47 & 48 of the 30th June UTC Settlement Date ). |  | Implemented | Clarification - No change required |  |  | Interim Release 8 | 2024-03-20 | METH009 UMSO Method Statement updated accordingly | Method statement correction | Supporting Docs | Method Statement | METH009
MHHS-DIN-939 | RS |  | 2024-03-01 | St Clements | 36920 | Daniel Tadecicco | Central Body | Difference in lapse behavior for subsequent IF-031 Appointments between enduring and migration | There is a difference in the logic for Migration and Enduring when it comes to lapsing Appointments. In Migration, it allows MPRS to lapse an IF-031 Migration immediately without a matching IF-034. For enduring MPRS must wait for the IF-034 before lapsing. We would like Migration to be aligned with enduring for ease of coding. This would require a change to MHHS-Migration-Can-RS-005 to change the line "In this case, an IF-035 would be sent immediately to cancel the Migration. " to "Any earlier appointments should be lapsed." |  | Implemented | Design ambiguous |  |  | Interim Release 8 |  | Note added to REGS Migration Requirment - MHHS-Migration-Can-RS-005 to confirm functionality | Requirement correction | Migration | Migration Requirements | Migration Requirements Log
MHHS-DIN-940 | MH |  | 2024-03-01 | Helix | 38131 | Rashmi Radhakrishnan | Central Body | M18 - ISD | The M18 example table in EDI021 ISD Entities has values of N/A where the actual values should be blank. |  | Open - awaiting assessment | Error/Correction | All Participants |  | Post Go-live Release |  | Update the example table to show blank fields where the DIP Role does not have an associated MP Role Code | Other | Supporting Docs | ISD | EDI021 ISD Entities Document
MHHS-DIN-941 | RG | DIN-720 | 2023-10-11 | Utiliteam |  | Mike Fensome | SRO Design | Update to DI-122 Profile Class to min length of 1, max length of 2 | Allow Profile Class (DI-122) to be provided with min length of 1 and max length of 2 in both swagger and DES138 so that, for example, either 1 or 01 are accepted. |  | Implemented | Error/Correction |  |  | Interim Release 7.1 |  | Update 7.1 swagger to match 5.4 for DI-122 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-942 | RG |  | 2024-03-05 | St Clements |  | Melissa Brocklehurst | Software Provider | Errors in REP-901 in Swagger | Blocks R901-07 & R901-08 do not align with the defintion in ERI011B s/s. The fields chargeBand, dailyUncorrectedVolumeForChargeBand and totalVolumeChargeForChargeBand need to be removed from R901-07 |  | Implemented | Error/Correction |  |  | Interim Release 7.2 |  | Remove chargeBand, dailyUncorrectedVolumeForChargeBand and totalVolumeChargeForChargeBand fields from R901-07 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-943 | BK |  | 2024-03-05 | Helix |  | Nigel Rees | Central Body | CR034 - Delay to Elexon Level 4 validation response – NFR (1009) | The change being proposed is that Helix does not meet the requirements of E2E1009 NFR. We request the description for E2E1009 be updated to read “All Services shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes - 10minutes or less – excludes IF-021” | CR034 | Implemented | Change Request |  |  | Interim Release 7.1 |  | Updated Level 4 Processing Times (Asynchronous) requirement as follows; All Services with the exception of Helix (VAS,MDS,LSS,ISD) Services shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes - up to average hourly volume, mean response time of 6s or less - up to average hourly volume, 90th percentile response time of 12s or less - from average hourly to peak hourly volume, mean response time of 10s or less - from average hourly to peak hourly volume, 90th percentile response time of 16s or less Helix Services (VAS,MDS,LSS,ISD) shall provide an Asynchronous response time of 10 minutes or less. | Requirement correction | Supporting Docs | Requirements | MHHS-E2E002 Requirements
MHHS-DIN-944 | SB |  | 2024-03-08 | Design Team |  | Paul Pettitt | SI Design | Service Provider appointment Process | The Operational choreography does not align with the Design intent of flexibility with Service Provider Appointment. OP_120 requires clarification |  | Closed | Error/Correction |  |  |  |  | Closed - upholding the objection raised by ReCCo against this DIN
MHHS-DIN-945 | SC |  | 2024-03-13 | RECCo |  | Sarah Jones | Central Body | CR46 - Change of Energy Direction | Remove reference to 'one-time only' change and add guidance that Change of ED will not change hisotric consumption in MDS/Settlements - any changes to hisotric consumption for that MPAN should be via Consumption Ammendment or Trading Dispute | CR046 | Implemented | Change Request | All Participants |  | Interim Release 8.1 |  | "One Time Change" reference removed from BP010B and BPD010B for "Change of Energy Direction" process, Registration Requirements (BRS003), Supplier Overview (BRS004) and LDSO Overview (BRS005). New note added to BP010B to highlight that any historic settlement data will not be amended, this would need to be via Consumption Amendment or Dispute process where required. | Process Model correction | Registration | Business Process Models/ Requirements | BRS003, BRS004, BRS005, BP010 and BP010B
MHHS-DIN-946 | RS |  | 2024-03-13 | St Clements | 39364 41047 | Daniel Tadecicco | Central Body | Use of LP006 - Migration Aborted, Pending Registration Received | MHHS DEL974 has requirement MHHS-Migration-COA(MS)-RS-002 states two event codes MGR_Cancelled_MS and MGR_Cancelled_DS should be created, however this needs to be amended to confirm the use of LP006 |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Update to MHHS-Migration-CoA(MS)-RS-002/MHHS-Migration-CoA(DS)-RS-002 in MHHS-DEL974 and Migration Design Document section 13.2.3 | Technical corrrection | Migration | Supporting document | MHHS-DEL974 Migration Design Document
MHHS-DIN-947 | SC |  | 2024-03-13 | DIP |  | Sean Cooper | Central Body | Changes to Swagger to support Implementation of JSON Error Checking End Points. | Swagger to be updated to include facility for new JSON Message Error Checking End Points and response message. |  | Implemented |  |  |  | Interim Release 7.2 |  | Swagger to be updated to include facility for new JSON Message Error Checking End Points and response message. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-948 | SC |  | 2024-03-14 | St Clements |  | Sean Cooper | SRO Design | Error Code Description Text Updates | Update Error code Text to align with confirmed text provided by SCS |  | Implemented | Design gap |  |  | Interim Release 8 | 2024-03-20 | Update Error code Text to align with confirmed text provided by SCS | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-949 | RS | DIN-1021 | 2024-03-15 | St Clements | 39365 | Daniel Tadecicco | Central Body | MHHS-Migration-CoA(MS)-RS-009 Alignment with IR7 | The IF-031 REG code in the Migration Requirements log for MHHS-Migration-CoA(MS)-RS-009 does not align with IR7 IR7 IF DI-800 = SEG or CSP, COS, USP and MPAN is not migrated (ie operating in old regime) REG9008 - MHHS Scenario Codes cannot be used for UnMigrated MPAN |  | Implemented | Design misaligned |  |  | Interim Release 8 | 2024-03-20 | Update Migration requirements doc to align with DES138 error code (REG9009) and updated Migration doc where relevant to align with DES138 error code (REG9009). | Technical corrrection | Migration | Supporting document | Migration Requirements Log Migration Design Document
MHHS-DIN-950 | SC |  | 2024-03-18 |  |  | Sean Cooper | SRO Design Team | CR44 - IF-051 Refresh Message | CR044 - Please refer to the change request documentation for details | CR044 | Closed | Change Request |  |  |  |  | ~ Swagger changes to include new IF-051 ~ Secondary routing treatment of If-051 [DONE] ~ Add IF-051 data strcutre to DES138 [DONE] | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-951 | SC |  | 2024-03-18 |  |  | Sean Cooper | SRO Design Team | CR45 - SSD Fix Tool | CR045 - Please refer to the change request documentation for details | CR045 | Closed | Change Request |  |  |  |  | ~ Swagger updates to include New De-App Reason Code ~ Swagger New IF-001 Event Codes ~ Add IF-001 Event Codes to DES138 [DONE] ~ Changes to secondary Routing to Support [DONE] ~ Possible SSD Fix Business Process Diagram | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger Potential - BPXXX
MHHS-DIN-952 | RS |  | 2024-03-18 | Datamere | 41267 | Paul O'Neill | Software Provider | Anomolies in DES138 | DI-991 on 02_DIP_Common worksheet states the values can be TBC (eg PROD, PREPROD, UAT, SIT, DEV). Postman states the following: "S1.environmentTag must be one of 'PROD,PREPROD,SIT,UIT,DEV'." Q2 – DI-840 on 02_IF-031 worksheet states the data item is named CSS Registration ID. Postman states the following: property 'CSSRegistrationID' is unsupported for 'B013' block", B013.CSSRegistrationRequestID field is required. |  | Initial Assessment/Updating | Design misaligned | All Participants |  | Post Go-live Release |  | Update DES-138, data items: DI-991 and DI-840 to align them to swagger (please view DIN details notified) DI-849 ( not DI-840 ): "CSS Registration ID" is correct in Swagger and DES138 as per DIN 864 - no change required DI-991: Value need to be updated to match swagger, UAT needs to be changed to UIT | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-953 | SC |  | 2024-03-18 |  |  | Sean Cooper | SRO Design | New DTN Flows for Existing Retained Settlement D-Flows | Update EDI001 Settlement Reporting Spec to reference New D-Flow References assigned to retained D-Flows |  | Closed | Design misaligned |  |  |  |  | Update EDI001 Settlement Reporting Spec to reference New D-Flow References assigned to retained D-Flows
MHHS-DIN-954 | RG |  | 2024-03-18 | Avande |  | Piotr Penar | Avanade | Add validation endpoints into Swagger | Add validation endpoints into Swagger |  | Closed | [5 empty] | DUPE 954
MHHS-DIN-955 | MH |  | 2024-03-21 |  |  | Matt Hall | SI Design | CR043 - MPAN/ABMU Mapping | DIN to cover the changes required to Design folowing approval of CR043 | CR043 | Implemented | Change Request | Suppliers, MDS |  | Interim Release 8 | 2024-03-20 | New requirements to be added to MDS and Suppliers' BRS documents to cover CR043 | Requirement correction | Supporting Docs | Requirement correction | BRS004-Supplier Overview BRS008 MDS Requirements
MHHS-DIN-956 | ZH |  | 2024-03-21 | MHHS |  | Zakir Hussain | SI Design | Rebranding of D-Flows - DES196 & ERI011b | DIN to align changes made in the DES196 document (latest D-flows added to the doc) to the relevant areas within design |  | Implemented | Design misaligned | All Participants |  | Interim Release 8.1 |  | Update ERI011b and DES196 to reflect use of ECS DTN reports and New D-Flow References assigned to retained D-Flows | Reporting correction | Supporting Docs | Various documents | ECS Report External ERI011b DES196
MHHS-DIN-957 | MF | Test defect 31009 DIN-963 DIN-964 | 2024-03-21 | SI Design |  | Mike Fensome | SI Design | Update swagger in IF-005 | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. |  | Implemented | Error/Correction |  |  | Interim Release 5.5 |  | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-958 | BK | MHHS-DIN-937 | 2024-03-21 | SRO Design |  | John Wiggins/Matthew Breen | SRO Design | Align Migration design with wider design changes made for CR028 | The COS Migration tests continue to show EES receiving the IF-001. The EES instance of the IF-001 was removed from the COS process map and the interface catalogue as part of CR028. As such EES will not be able to process the IF-001 and it is inappropriate to include it as part of the baselined test scenarios. |  | Closed | Design misaligned |  |  |  |  | Updates to be made to relevant Migration artefacts to align with the design changes to the COS process map and DES138 in relevance to EES not receiving IF-001. | Process Model correction | Migration | Process Model correction | BPM001, BPD001, Migration document
MHHS-DIN-959 | BK | MHHS-DIN-942 | 2024-03-21 | St Clements |  | Melissa Brocklehurst | Software Provider | Errors in REP-901 in Swagger | Blocks R901-07 & R901-08 do not align with the defintion in ERI011B s/s. The fields chargeBand, dailyUncorrectedVolumeForChargeBand and totalVolumeChargeForChargeBand need to be removed from R901-07 |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Remove chargeBand, dailyUncorrectedVolumeForChargeBand and totalVolumeChargeForChargeBand fields from R901-07 | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-960 | BK | MHHS-DIN-947 | 2024-03-21 | DIP |  | Sean Cooper | Central Body | Changes to Swagger to support Implementation of JSON Error Checking End Points. | Swagger to be updated to include facility for new JSON Message Error Checking End Points and response message. |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Swagger updated to include facility for new JSON Message Error Checking End Points and response message | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-961 | RG |  | 2024-03-22 | SRO Design |  | Rob Golding | SI Design | Update Environment list to reflect those being delivered by Avanade | Existing list: - PROD - PREPROD - SIT - UIT - DEV Update to add SITB |  | Implemented | Error/Correction |  |  | Interim Release 5.5 |  | Only SITB currently added | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-962 | RG | DIN-1011 | 2024-03-25 | Helix | 42284 | Nigel Rees | Central Body | Make MPAN optional on replay/requeue | Removing MPAN from the mandatory list of parameters for DIP replay/requeue |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Removing MPAN from the mandatory list of parameters for DIP replay/requeue and introduce mandatory/null design pattern on input parameters | Technical corrrection | Supporting Docs | Interfaces | Swagger, E2E SA
MHHS-DIN-963 | MF | Test defect 31009 DIN-964 DIN-957 | 2024-03-21 | SI Design |  | Mike Fensome | SI Design | Update swagger in IF-005 | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. |  | Implemented | Error/Correction |  |  | Interim Release 7.2 |  | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-964 | MF | Test defect 31009 DIN-963 DIN-957 | 2024-03-21 | SI Design |  | Mike Fensome | SI Design | Update swagger in IF-005 | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. |  | Implemented | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-965 | RG |  | 2024-03-22 | SRO Design |  | Rob Golding | SI Design | Update Environment list to include SITB | Existing list: - PROD - PREPROD - SIT - UIT - DEV Update to add SITB |  | Implemented | Error/Correction |  |  | Interim Release 7.2 |  | Only SITB currently added | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-966 | SC | Test Defect 31336 DIN-1019 | 2024-03-27 | SRO Design |  | Sean Cooper | SRO Design | Revision to the PUB-004 Secondary routing logic. | SIT DEFECT - 31336 Currently distribution logic states delivery of PUB-004 to SUPC and XMSC. This results in the send of the message (IF-004) being unnecessrily copied in on the PUB-004. Secondary logic should reference sending party and issue to XMSC where sent by SUPC and SUPC where message sent by XMSC. |  | Implemented | Error/Correction |  |  | Interim Release 7.3 |  | SIT DEFECT - 31336 Currently distribution logic states delivery of PUB-004 to SUPC and XMSC. This results in the send of the message (IF-004) being unnecessrily copied in on the PUB-004. Secondary logic should reference sending party and issue to XMSC where sent by SUPC and SUPC where message sent by XMSC. DES138 - IF-004 routing table updated accordingly | Technical corrrection | Supporting Docs | Interfaces | Secondary Routing DES138
MHHS-DIN-967 | MF | Test Defect 31338 | 2024-03-27 | Design Team |  | Mike Fensome | SRO Designn | Update BP010A to show that MPL address updates from UMSO are via "Agreed Communication Method" | Update BP010A to show that MPL address updates from the UMSO are notified via "Agreed Communication Method" |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated BP010A and BPD010A to show that MPL address updates from the UMSO are notified via "Agreed Communication Method". This aligns with BR-MS-064 and reflects that the UMSO cannot currently use D0381 flow | Process Model correction | MPAN Ownership | Business Process Models | BP010A BPD010A
MHHS-DIN-968 | SC |  | 2024-03-27 | Avanade |  | Sean Cooper | SRO Design | MDR Secondary Routing | Following text added to interfaces where MDR is referenced as a Secondary Recipient .... .... "Reference to MDR above assumes that MDR is Qualified for DIP Operations & is opt'ed in for SDS-MDR message exchange" |  | Implemented | Design ambiguous |  |  | Interim Release 8 | 2024-03-20 | Following text added to appropriate interfaces.... .... "Reference to MDR above assumes that MDR is Qualified for DIP Operations & is opt'ed in for SDS-MDR message exchange" | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-969 | SC |  | 2024-03-28 | SCS |  | Sean Cooper | SRO Design | Implementation of REGS Calendar based RF Cut of Date Checking | SCS have confirmed that RF Cut Off Date validation based on the ISD Settlement Calendar cannot be implemented until post go-live. SCS/Programme assessment is that given the other validation rule(s) in place principly the check around Migration Date that this is not an issue. This DIN is to formally record this issue - DIN will be differed. |  | Open - awaiting assessment | Design gap |  |  | Post Go-live Release |  | RF restrictions for MS, DS, MDR, Energisation Status EFDs. Differred DIN captured for reference
MHHS-DIN-970 | SC |  | 2024-03-28 | SCS |  | Sean Cooper | SRO Deign | Bypassing SSD Check where no SP's are appointed even beyond RF Cut Off Date | Logic check required following implementation of DIN969 to allow for Retrospective Appointment of SP's prior to RF Cut off Date - where Supplier has failed to do this prior to RF cut off date for the SP Appointment Start Date |  | Open - awaiting assessment | Design gap |  |  | Post Go-live Release |  | Logic variation to allow Pre-RF Cut Off Retro Appointments - Differed DIN Captured for Reference |  | Supporting Docs | ISD | EDI021 ISD Entities Document
MHHS-DIN-971 | SC |  | 2024-03-28 |  |  | Sean Cooper | SRO Design | Clarifcation of MPAN Linkage Request Rejection Codes | Programme has been waiting for LDSO confirmation of these codes however this has not been forthcoming todate. In order to finalise the design for other participants the following codes will constitute the go-live design. IE000 - Proposed Linkage Change Accepted IE001 - Proposed Linkage Change Rejected IE099 - Please contact LDSO directly for further advice |  | Implemented | Design gap |  |  | Interim Release 8 | 2024-03-20 | Programme has been waiting for LDSO confirmation of these codes however this has not been forthcoming todate. In order to finalise the design for other participants the following codes will constitue the go-live design. IE000 - Proposed Linkage Change Accepted IE001 - Proposed Linkage Change Rejected IE099 - Please contact LDSO directly for further advice | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-972 | SC |  | 2024-04-02 | SCS |  | Sean Cooper | SRO Design | Migration Reqs: Removal of Reference to IF-040 (Annual Consumption) from the REGS Migration Requirments | Missed CR39 Update - Remove of Reference to IF-040 (Annual Consumption) from the REGS Migration Requirments |  | Implemented | Design misaligned |  |  | Interim Release 8 | 2024-03-20 | Missed CR39 Update - Remove of Reference to IF-040 (Annual Consumption) from the REGS Migration Requirments | Technical corrrection | Migration | Supporting document | Migration Requirements Log
MHHS-DIN-973 | SC | 1038 | 2024-04-02 | SCS |  | Sean Cooper | SRO Design | Migration Reqs: Correct REGS treatment of D0312 where a Forward MIgration is in progress. | Requirment updated to refeclt that IF-035 with Lapsed Reason Code of LP001 (MPAN Disconnected/deRegistered) will be issued for any Pending Service Provider Appointments on receipt of D0312 |  | Implemented | Design ambiguous |  |  | Interim Release 8 | 2024-03-20 | Note added to RESG Migration Requirement MHHS-Migration-Can-RS-006 - to confirm process | Technical corrrection | Migration | Supporting document | Migration Requirements Log
MHHS-DIN-974 | RG | DIN-1012 | 2024-04-02 | EDW Technology |  | Mark Kenney | SRO Design | Align webhookresponse on /statusmessage to /dip-channel | Status messages reponses from the PP systems and the DIP need to align |  | Implemented | Design misaligned | All Participants |  | Interim Release 8.1 |  | Status messages responses from the PP systems and the DIP need to align, also standard message webhook response should return a standard response body on a 400 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-975 | SC |  | 2024-04-02 | SCS |  | Sean Cooper | SRO Design | Migration Reqs: Confirm REGS treatment of related MPANs in Reverse Migration Scenario | Process is not "automatic" with the REGS per se. CSS will issue a switch request for each MPAN, REGS will process each switch request -end result is the same |  | Implemented | Design ambiguous |  |  | Interim Release 8 | 2024-03-20 | Note added to RESG Migration Requirement MHHS-RMigration-CoS-RS-002 to confirm process is not automatic - same end result is achived through CSS functionality | Technical corrrection | Migration | Supporting document | Migration Requirements Log
MHHS-DIN-976 | RG |  | 2024-04-05 | ESG | 44664 | Patricia Parker | SRO Design | Duplicate enumeration values for the DI-596 Charge Type enumeration | Duplicate enumeration values for the DI-596 Charge Type enumeration, CAPAC appears twice |  | Closed | Error/Correction |  |  |  |  | DI-596 Charge Type enumeration, CAPAC appears twice - Need to remove duplicate charge type | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-977 | RG |  | 2024-04-05 | Avanade |  | Rob Golding | SRO Design | Update PROD to PRD in Environment Tag List | Confirmation that Avanade have labeled the Production DIP environment PRD. The DT-013-EnvironmentTag will require updating: Change PROD to PRD and removed PREPROD. Add SITB |  | Implemented | Design misaligned | All Participants |  | Interim Release 8.1 |  | The DT-013-EnvironmentTag will require updating: Change PROD to PRD and removed PREPROD. | Technical corrrection | Supporting Docs | Interfaces | Swagger, E2E SA
MHHS-DIN-978 | RS |  | 2024-04-08 | ESG | 41894 | Patricia Parker | Software Provider | REP-003 and REP-006 have JSON label missing in ERI011b - ECS Reports | REP-003 and REP-006 should have Distribution Pattern A and Report Format JSON in cell H7 as per the other MHHS-REP-XX (eg MHHS-REP-07) |  | Initial Assessment/Updating | Error/Correction | All Participants |  | Post Go-live Release |  | Update REP-003 and REP-006 in ERI011b to match include outlined box as per MHHS-REP-07 | Reporting correction | Supporting Docs | ESC Reporting | ERI011B ESC Reports Document
MHHS-DIN-979 | RS |  | 2024-04-08 | ESG | 41955 | Patricia Parker | Software Provider | DI-819 (De-appointment reason code) in IF-003 should not contain CSERV. Only CSUPP should be used | DES138, IF-003 has DI-819 has the option for CSERV Change of Service Provider in the Population notes column. This should be greyed out leaving just CSUPP change of supplier |  | Closed | Error/Correction | All Participants |  |  |  | Update IF-003 in DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-980 | MH |  | 2024-04-10 | SCS | 44726 | Madison Layton | Software Provider | ISD versioning IR8 | IR8 version of ISD has not included the IR7.1 changes. This needs to be resolved by adding the changes back in. This is only DIN-899 |  | Implemented | Error/Correction | Helix, ISD users |  | Interim Release 8.1 |  | Add DIN-899 changes back in to the latest version of IR8. Updates required were covered by DIN-1033 and changing M15 to include N as No Consent | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-981 | RS |  | 2024-04-11 | Siemens | 41452 | David Baxendale | Data Service Provider | Incorrect Load Shape Off Peak Period | Most of the off-peak periods cover 14 UTC periods (7 Hours) – either 00:00 to 0700 OR 00:30 to 7:30 There is 1 anomaly in METH001 GSP _C Profile Class 4 has 15 UTC periods – 00:00 to 07:30 |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Method statement will need to be corrected to reflect 00:00 - 07:00 also remove minus sign after the 00:30 _K Will also need to check the load shaping method statement as well (Also incorrect in LSS METH005) | Method statement correction | Supporting Docs | Method Statement | METH001 METH005
MHHS-DIN-982 | ZH | DIN-575/1013 | 2024-04-11 | SCS |  | Madison Layton | Software Provider | CR039 implementation | DES138 - IF040 requires removal of REGS in "To Parties" field | CR039 | Implemented | Change Request | REGS |  | Interim Release 8.1 |  | Update IF040 in DES138, removed "Registration Service (REGS)" from "To Parties" field | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-983 | RS |  | 2024-04-11 | MHHS | 36071 | Matt McKeon | Central Body | LLFC Id mandated in retained DTC flow | The Line Loss Factor Class Id is being replaced by the DUoS Tariff Id. The LLFC Id is present in various DTC flows, almost all of which are redundant post MHHS. LLFC Id is an optional field in the D0311 which, according to DES196, is retained post MHHS with the MHHS Change “New rules to clarify that Profile Class and Meter Timeswitch Class [code] should be null if no value exists for MHHS MPANs, LLFC should be populated with the DUoS Tariff Id for MHHS MPANs and EACs should only be provided for non-MHHS MPANs. ”. LLFC Id is a mandatory field in the D0387 which, according to DES196, is retained post MHHS with no changes. |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Replicating the rule in the D0311 in the D0387 seems appropriate. Will add a note to the D0387 and amend DES196. Propose to do this once SIT Cycle 2 has completed, as adding it now would impact DTN flow test scope. | Data interface correction | Supporting Docs | DFlow | DES196
MHHS-DIN-984 | RS | DIN-917 | 2024-04-12 | ESG | 42711 | Patricia Parker | Software Provider | D0148 use within Reverse Migration | DEL961 Migration Document detail does not contain any detail of the use of the D0148 when completing a Reverse Migration as assumed to BAU. Need to reference the use of the New connection process for D0148 as per section 9 of Annex c |  | Implemented | Design ambiguous | All Participants |  | Interim Release 8.1 |  | Add reference to D0148 new connection process (section 9 annex C) to DEL961 (Section 13.1) | Design Ambiguous | Supporting Docs | Migration Design | DEL961
MHHS-DIN-985 | RS | DIN-837 | 2024-04-12 | ESG | 42711 | Patricia Parker | Software Provider | Incorrect meter reading code in section 6.1.3 of DEL961 Migration Design | Secftion 6.1.3 of DEL961 still states Meter Reading Reason Code = 28 (Forward Migration CoA) Instead of Reading Type = U. This should match previously agreed updates of U - Forward Migration CoA V - Forward Migration CoS X - Supplier Agreed Switch Read Y - Reverse Migration CoS As per MHHS impacts to Data Transfer Network (DTN) Flows |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Section 6.1.3 of DEL961 to be updated with U - Forward Migration CoA V - Forward Migration CoS X - Supplier Agreed Switch Read Y - Reverse Migration CoS Remainder of ducument sections to be checked for same disparity | Design Ambiguous | Supporting Docs | Migration Design | DEL961
MHHS-DIN-986 | RS |  | 2024-04-12 | MHHS | 45969 | Test team | Central Body | Incorrect step assigned to migration requirement | DEL974 requirements MHHS-Migration-CoA(MS)-RS-005 and MHHS-Migration-CoA(DS)-RS-005 refer to step 255 of BPM002. No step 255 exists on BPM002. Requirement to be amended to step 710 |  | Initial Assessment/Updating | Error/Correction | All Participants |  | Post Go-live Release |  | Amend requirements MHHS-Migration-CoA(MS)-RS-005 and MHHS-Migration-CoA(DS)-RS-005 to step 710 in DEL947 (Registration Tab, row 19 and 39) | Requirement correction | Migration | Migration Requirements | DEL974
MHHS-DIN-987 | ZH | DIN-676 | 2024-04-15 | SCS |  | Madison Layton | Software Provider | Missing text in NFRs - CR-018 implementation issues | E2E002 was updated as per IR8 however it is missing text that specifies details around when they are applicable |  | Closed | Error/Correction |  |  |  |  | Duplicate of 993 | Requirement correction | Supporting Docs | Requirements | MHHS-E2E002 Requirements
MHHS-DIN-988 | ZH |  | 2024-04-15 | SCS |  | Daniel Tadecicco | Software Provider | Migration design alignment | DES138 requires some updates to align with the migration design documentation |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated IF-003 in DES138 to remove MSDeAppUdateRM & DSDeAppUpdateRM events and removed the accompanying interface note as these events are not used in the case of Reverse Migration Design. Opt In/Out matrix updated accordingly. Swagger updated. | Data interface correction | Supporting Docs | Interfaces | DES138 & Swagger
MHHS-DIN-989 | RG |  | 2024-04-15 | Stark | 45757 | Jon Dennis | Software Provider | DI-596-Charge-Type - CAPAC duplicated in Enum | DI-596-Charge-Type - CAPAC duplicated in Enum -one of the entries needs to be removed |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | remove second CAPAC from enumerated list | Data interface correction | Technical Artefact | Interfaces | Swagger
MHHS-DIN-990 | MF | DI-136 | 2024-04-17 | SCS |  | Madison Layton | Software Provider | Limit effective from updates to RF for appointments and energisation status changes | Update validation rules in IF-031, IF-034 and IF-007 to not allow updates to appintment effective from dates and energisation status effective from dates beyond RF |  | Implemented | Error/Correction | Suppliers, REGS |  | Interim Release 8.1 |  | Update validation rules in IF-031, IF-034 and IF-007 to not allow updates to appintment effective from dates and energisation status effective from dates beyond RF. Added note to REGS Notes to confirm that derived Market Segment Effective from Date cannot be beyond RF. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-991 | MF | DIN-939 | 2024-04-17 | SCS |  | Madison Layton | Software Provider | Confirm migration lapse behavior aligns with BAU operation | Update note on MHHS-MIGRATION-CAN-RS-005 to confirm that lapse notification is only issued after receipt of IF-034 |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated note on MHHS-MIGRATION-CAN-RS-005 to confirm that lapse notification is only issued after receipt of IF-034 | Requirement correction | Migration | Migration Requirements | DEL974
MHHS-DIN-992 | RG | DIN-1014 | 2024-04-17 | Design Team |  | Rob Golding | SRO Design | IF-016-ActivePowerRejected required incorrect | IF-016-ActivePowerRejected required field B900List should be B900 |  | Implemented | Error/Correction | Advanced Data Service |  | Interim Release 8.1 |  | Update: IF-016-ActivePowerRejected required field B900List to B900 | Data interface correction | Technical Artefact | Interfaces | Swagger
MHHS-DIN-993 | MF | DIN-929 | 2024-04-17 | SCS |  | Daniel Tadecicco | Software Provider | Confirmation of LDSO response times | Update E2E1009 in line with CR040 and Operational Choreography to confirm repsonse times specified are within normal operating hours | CR040 | Implemented | Change Request | All Participants |  | Interim Release 8.1 |  | Updated E2E1009 in line with CR040 and Operational Choreography to confirm repsonse times specified are within normal operating hours | Technical corrrection | Supporting Docs | Interfaces | E2E002 - Non-Functional Requirements
MHHS-DIN-994 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Treatment of mixed meter sites | Update registration notes to confirm treatment of mixed meter sites |  | Initial Assessment/Updating | Design ambiguous | REGS |  | Post Go-live Release |  | Update Reg Notes in DES138 to confirm that: • If a mix of Smart and Traditional meters then consider the Meter Group as Smart • If any Advanced meter is fitted then this should be considered as in the Advanced Segment so Meter Group as Advanced. Update REG1042 and REG1043 validation in IF-025 to clarify how mixed meters are validated | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-995 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Correlation ID removed from IF-037 AppUpdate events | Remove Correlation ID from AppUpdate events on IF-037 |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Removed Correlation ID from AppUpdate events on IF-037 | Data interface correction | Supporting Docs | Interfaces | DES138 (No swagger change reqd)
MHHS-DIN-996 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Update description of DI-028 (Reconnection Effective from Date) | Update description of DI-028 to reflect that this is when the Metering Point is reconnected in Registration Service |  | Initial Assessment/Updating | Design ambiguous | All Participants |  | Post Go-live Release |  | Update description of DI-028 to reflect that this is when the Metering Point is reconnected in Registration Service | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-997 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | PUB-007 validation to allow de-energisation on a Disconnected MPAN | Validation should be changed to allow a PUB-007 to De-energise a Disconnected MPAN (De-energise only, energisation would still not be permitted on disconnected MPAN) |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | New Validation to allow a PUB-007 to De-energise a Disconnected MPAN (De-energise only, energisation would still not be permitted on disconnected MPAN) with error code of REG1001 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-998 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Clarification on sending error message on IF-034 where incorrect Service Provider responds | Add note to IF-034 validation rules to confirm that REGS will respond with RCP1063 if the incorrect Service Provider responds |  | Initial Assessment/Updating | Error/Correction | All Participants |  | Post Go-live Release |  | Added note to IF-034 validation rules to confirm that REGS will respond with RCP1063 if the incorrect Service Provider responds | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-999 | MF | DIN-788/1015 | 2024-04-18 | UKPN |  | Neil Madley | Network Operator | Update routing for [MPANReconnection] and add event to Opt/In Out Matrix | On IF-009 add LDSO as secondary routed. Add [MPANReconnection] to the Opt In/ Opt Out Matrix so that LDSO's can opt out of receiving this event. |  | Implemented | Error/Correction |  |  | Interim Release 7.3 |  | On IF-009 added LDSO, SUPC as secondary routed. Added [MPANReconnection] to the Opt In/ Opt Out Matrix so that LDSO's can opt out of receiving this event. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1000 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Update to error message REG1032 to refer to Local Time | Update REG1032 validation on IF-031 in DES-138 to refer to Local Time |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated REG1032 error message on IF-031 in DES-138 to refer to Local Time, where previously referenced UTC. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1001 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Remove REGS requirement MHHS-BR-RS-014.1 | Supplier Nominated DPI is not provided on Metering Service Appointments, so this Requirement is not needed. |  | Initial Assessment/Updating | Error/Correction | REGS |  | Post Go-live Release |  | Removed requirement MHHS-BR-RS-014.1 from BRS-003 to provide Supplier Nominated DPI for Metering Service Appointments. Requirement retained for Data Service Appointments. | Requirement correction | MPAN Ownership | Business Requirements Documentation | BRS003 - Registration Service requirements
MHHS-DIN-1002 | MH |  | 2024-04-19 | Helix |  | Rashmi Radhakrishnan | Central Body | ISD M11 and M12 | As per the UMSUG meeting that we attended, For M12, its been agreed that we need to incorporate OFF event to have “NEVER” where there is no OFF event. |  | Implemented | Error/Correction | UMSDS |  | Interim Release 8.1 |  | Added a new permissable value of "NEVER" to the OFF Event data field in ISD Entity M12 | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-1003 | RS |  | 2024-04-19 | National Grid | 43643 | Rachael Prosser | Network Operator | E2E Architecture Document to be updated to include Reference to LDSO and IF-20 | E2E Architecture Document does not include latest updates made to IF-20 for LDSO, review and update required |  | Initial Assessment/Updating | Error/Correction | LDSOs |  | Post Go-live Release |  | Add line advising for the latest representation refer to DES138. RG to to complete review of document | Other | Supporting Docs | E2E Architecture Document | E2E001 Architecture Document
MHHS-DIN-1004 | RS |  | 2024-04-19 | CGI | 47845 | Dave Webster | Software Provider | DES138 OptOut Matrix for IF-003 Supplier | The 04_IF_OptOut_Matrix sheet of DES138 v5.8.1 shows that IF-003 is not received by Supplier (“N/A”), but for all Event Codes the IF-003 message is Primary Routed to Supplier |  | Implemented | Error/Correction | Suppliers |  | Interim Release 8.1 |  | Changed IF-003 for Supplier to No from N/a in DES138 IF Opt out Matrix tab. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1005 | MH |  | 2024-04-19 | Helix | 46469 | Matt Hall | SI Design | METH007 Section D clean up | Currently SEction D in the METH007 doesn't clearly distinguish between REP002/2a and 2b. This is causing some confusion and should be rectified |  | Initial Assessment/Updating | Design ambiguous | All Participants |  | Post Go-live Release |  | Tidy up of Section D in MTH007 to clarify which reports are included, and to clarify which of the REP02 variants require non-W connections include (if any) | Method statement correction | Supporting Docs | Method Statement | METH007
MHHS-DIN-1006 | MH | DIN-087 | 2024-04-19 | RECCo | 46872 | Sarah Jones | Central Body | Outstanding Design Query (DIN087) | As part of the final code drafting checks, we are confirming that all consultation comments have been addressed. We have identified a comment from an early drafting tranche (CD-0558) which queries the requirements to issue a de-energisation notice for meter exchanges. At the time, we were expecting a note to be added to BP008 to make it clear that that ‘DeEn did not need to be notified if meter works completed within same day (ie same rules as today)’ as stated in the DIN log against DIN087. However, BP008 doesn’t appear to have this note included which means we have not been able to close out the code drafting query. |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Add a box to BPM008 to to reflect the proposed solution in DIN-087 | Process Model correction | Supporting Docs | Business Process Diagram | BP008
MHHS-DIN-1007 | RG | DIN-1018 | 2024-04-22 | Avanade |  | Rob Golding | SRO Design | Change request body on Validation Endpoints | Avanade have reviewed the 1.7.1. endpoints and are requesting a chnage so that they are more flexible and align to the submission API |  | Implemented | Error/Correction |  |  | Interim Release 7.3 |  | Avanade have reviewed the 1.7.1. endpoints and are requesting a change so that they are more flexible and align to the submission API | Technical corrrection | Swagger |  | Swagger
MHHS-DIN-1008 | SB |  | 2024-04-23 | British Gas |  | Neil Strange | Supplier | BP-03C Transfer of Reads Clarification | We’ve noticed that on BP03C the IF/PUB016 interface is TBC – looking at DES138 I believe this is confirmed – am I correct? This is in the advanced meters section following successful appointment. |  | Initial Assessment/Updating | Design ambiguous | Advanced Data Service |  | Post Go-live Release |  | Updating BP003C to remove TBC from IF/PUB-016 (Step 815 to Step 820) | Process Model correction | Supporting Docs | Business Process Diagram | BP003C
MHHS-DIN-1009 | SB |  | 2024-04-23 | MHHS |  | Shaun Magee | Central Body | METH002 Issue with LTV Method statement | Incorrect Method referenced in section 3.13 should be method 11 rather than 12 |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update: Incorrect Method referenced in section 3.13 should be method 11 rather than 12 | Method statement correction | Supporting Docs | Method Statement | METH002
MHHS-DIN-1010 | TR | DIN-762 | 2024-04-23 | RECCo | 46312 | Jonny Moore | Central Body | IF-003 - EES as Recipient | EES not included within the 'To Parties' in DES138 |  | Initial Assessment/Updating | Design misaligned | EES |  | Post Go-live Release |  | DES138 updated to include EES in the 'To Parties' field | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1011 | RG | DIN-962 | 2024-03-25 | Helix | 42284 | Nigel Rees | Central Body | Make MPAN optional on replay/requeue | Removing MPAN from the mandatory list of parameters for DIP replay/requeue |  | Closed | Error/Correction |  |  |  |  | Only implement in IR8 | Technical corrrection | Supporting Docs | Interfaces | Swagger, E2E SA
MHHS-DIN-1012 | RG | DIN-974 | 2024-04-02 | EDW Technology |  | Mark Kenney | SRO Design | Align webhookresponse on /statusmessage to /dip-channel | Status messages reponses from the PP systems and the DIP need to align |  | Implemented | Design misaligned |  |  | Interim Release 7.3 |  | Status messages reponses from the PP systems and the DIP need to align | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-1013 | ZH | DIN-575/982 | 2024-04-11 | SCS |  | Madison Layton | Software Provider | CR039 implementation | DES138 - IF040 requires removal of REGS in "To Parties" field | CR039 | Closed | Error/Correction |  |  |  |  | Update IF040 in DES138, remove "Registration Service (REGS)" from "To Parties" field | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1014 | RG | DIN-992 | 2024-04-17 | SRO Design |  | Rob Golding | SRO Design | IF-016-ActivePowerRejected required incorrect | IF-016-ActivePowerRejected required field B900List should be B900 |  | Implemented | Error/Correction |  |  | Interim Release 7.3 |  | IF-016-ActivePowerRejected required field B900List should be B900 | Data interface correction | Technical Artefact | Interfaces | Swagger
MHHS-DIN-1015 | MF | DIN-999 | 2024-04-18 | UKPN |  | Neil Madley | Network Operator | Update routing for [MPANReconnection] and add event to Opt/In Out Matrix | On IF-009 add LDSO as secondary routed. Add [MPANReconnection] to the Opt In/ Opt Out Matrix so that LDSO's can opt out of receiving this event. |  | Implemented | Error/Correction | LDSOs |  | Interim Release 8.1 |  | On IF-009 added LDSO, SUPC as secondary routed. Added [MPANReconnection] to the Opt In/ Opt Out Matrix so that LDSO's can opt out of receiving this event. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1016 | RG | DIN-1017 | 2024-04-24 |  |  |  |  | REP002 & REP002B require update | Swagger for REP-002 & REP-002B needs to be updated to reflect the defns in ERI011B. REP-002 The ERI011B – ECS Reports spreadsheet has the R027 – Distributor ID as a repeating block, meaning that Suppliers will receive 1 REP-002 for each combination of Distributor and GSP Group. REP-002B Similarly the REP-002B has R009 as a repeating block |  | Implemented | Error/Correction |  |  | Interim Release 7.3 |  | Update swagger to reflect ERI011B | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-1017 | RG | DIN-1016 | 2024-04-24 | Design Team |  | Rob Golding | SRO Design | REP002 & REP002B require update | Swagger for REP-002 & REP-002B needs to be updated to reflect the defns in ERI011B. REP-002 The ERI011B – ECS Reports spreadsheet has the R027 – Distributor ID as a repeating block, meaning that Suppliers will receive 1 REP-002 for each combination of Distributor and GSP Group. REP-002B Similarly the REP-002B has R009 as a repeating block |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update swagger to reflect ERI011B | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-1018 | RG | DIN-1007 | 2024-04-22 | Avanade |  | Rob Golding | SRO Design | Change request body on Validation Endpoints | Avanade have reviewed the 1.7.1. endpoints and are requesting a change so that they are more flexible and align to the submission API |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Avanade have reviewed the 1.7.1. endpoints and are requesting a change so that they are more flexible and align to the submission API | Technical corrrection | Swagger |  | Swagger
MHHS-DIN-1019 | SC | Test Defect 31336/ DIN-966 | 2024-03-27 | Design Team |  | Sean Cooper | SRO Design | Revision to the PUB-004 Secondary routing logic. | SIT DEFECT - 31336 Currently distribution logic states delivery of PUB-004 to SUPC and XMSC. This results in the send of the message (IF-004) being unnecessrily copied in on the PUB-004. Secondary logic should reference sending party and issue to XMSC where sent by SUPC and SUPC where message sent by XMSC. |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | SIT DEFECT - 31336 Currently distribution logic states delivery of PUB-004 to SUPC and XMSC. This results in the send of the message (IF-004) being unnecessrily copied in on the PUB-004. Secondary logic should reference sending party and issue to XMSC where sent by SUPC and SUPC where message sent by XMSC. DIP routing updated as part of IR7 DES138 - IF-004 routing table updated in IR8.1 | Technical corrrection | Supporting Docs | Interfaces | DES138
MHHS-DIN-1020 | RS | DIN-851 | 2024-04-25 | Code |  | Matt McKeon | Central Body | Queries from REC RTS which relate to either DES138 or ERI110B | CD6-320 is pointing out that data item DI-218 has a different name in DES138 (Current Supplier DIP ID) and ERI011B (Daily Supplier MSID Count). CD6-323 is referring to DI-030 and DI-031 in DES138, asking what the distinction is when they have the same name CD6-325 is asking about a data item with the same name but different DI-refs in DES138 (DI-081) and ERI011B (DI-484) |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | CD6-320 - DI-218 no update required not in ERI011B CD6-325 - DI-484 to be corrected to DI-081 in ERI011b - Swagger to also be updated to reflect consistant use of DI-081 | Technical corrrection | Supporting Docs | Interfaces | ERI011B Swagger
MHHS-DIN-1021 | MF | DIN-949 | 2024-04-25 | SCS | 39365 | Daniel Tadecicco | Central Body | Migration Error Code Alignment with DES138 | Update all the error codes in Migration Design Document and Migration Requirements to align with DES138 |  | Implemented | Design misaligned | All Participants |  | Interim Release 8.1 |  | Update Migration requirements doc to align with all DES138 migration error codes and update Migration doc where relevant to reflect the DES138 error codes Updated DES138 error descriptions as follows: REG9010 - Cannot Manage MPAN Relationships for an Unmigrated MPAN REG9002 - Supplier Data Items Cannot be Maintained for an Unmigrated MPAN REG9001 - CDC Marker Cannot be applied to an Unmigrated MPAN Removal of reference to IF-040 and RCP1076 from migration design document | Technical corrrection | Migration | Supporting document | Migration Requirements Log Migration Design Document DES138
MHHS-DIN-1022 | ZH |  | 2024-04-26 | RECCo | 48861 | Sarah Jones | Consultancy | Implementation of CR037 (Migration Message Processing Choreography Update) | Please refer to the CR037 documentation for further details | CR037 | Implemented | Change Request | All Participants |  | Interim Release 8.1 |  | Updated Change of Agent Migration Timings , as per CR037. This includes the Migration Requirements log, Migration Design Document and the E2E non-functional requirements. | Technical corrrection | Migration | Supporting document | Migration Requirements Log Migration Design Document E2E002 - Non-functional requirements
MHHS-DIN-1023 | TR |  | 2024-04-26 | SCS | 46680 | Madison Layton | Software Provider | Meter Location Data Quality | The PUB-005 B033 block is mandatory on all event codes except for [MeterRemoval]. Within this block the Meter Location is mandatory, however F (not known) is permitted. Where MS is updating other MTDs, there is a risk that they will submit Meter Location F ‘not known’ despite Meter Location not having changed. This could lead to poor quality of meter location data within REGS. Potential mitigation could be level 5 validation rule on REGS: if Meter Location held in REGS is not F or null, then DI-090 must not be F. This would ensure Meter Location couldn’t be reverted to F from a previously specified value. |  | Initial Assessment/Updating | Design ambiguous | REGS |  | Post Go-live Release |  | Potential mitigation could be level 5 validation rule on REGS: if Meter Location held in REGS is not F or null, then DI-090 must not be F. This would ensure Meter Location couldn’t be reverted to F from a previously specified value. | Missing/incorrect validation rule | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1024 | RG | Test Defect 31491 | 2024-04-26 | Kraken |  | Dave Mclean | Software Provider | Use of Min items =1 to stop arrays with zero items | Messages are being sent with arrays with zero items in, however an array with zero items does not make sense. If minItems is set to 1, then schema validation would not allow arrays with zero items. Also, to improve data validation for nullable strings the minLength needs to be set to 1. |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Add minItems = 1 to array where a zero item array is not allowed, Add to the folllowing objects: B900 B901, B902, B920, B922, B921, B903, B906, B906a, B907, B908, B910, B911, B941 | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-1025 | MF |  | 2024-04-29 | Helix |  | Rashmi Radhakrishnan | Central Body | Update to ISD examples in MHHSP_EDI021_ISD_Entities | Update the examples in M7, M17 and M18 tables to support SIT testing |  | Closed | Design ambiguous | All Participants |  |  |  | Updated the examples in M7, M17 and M18 tables ( MHHSP_EDI021_ISD_Entities v5.7 ) to support SIT testing | Design Ambiguous | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-1026 | RG |  | 2024-04-29 | Kraken |  | Dave Mclean | Software Provider | Remove DT-008 from data types | The request is that as DT-008 is not use can it be removed from the swagger |  | Initial Assessment/Updating | Error/Correction | All Participants |  | Post Go-live Release |  | Remove DT-008 from data types | Data interface correction | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-1027 | MF |  | 2024-04-30 | PDA |  | Tom Chevalier via Kevin Spencer | Data Service Provider | Remove reference to UMSDS on Consumption Amendment flow (IF-028) and Opt/In Out Matrix (IF-027) | Currently Consumption Amendment is not utilised by UMSDS so removed reference in the Consumption amendment flows |  | Initial Assessment/Updating | Error/Correction | UMSDS |  | Post Go-live Release |  | Remove UMSDS from "From parties" on IF-028. Updated UMSDS as N/A for IF-027 in Opt/In Out Matrix. BP016 references UMSDS to be removed. | Data interface correction | Supporting Docs | Interface Documentation | DES-138 BP016
MHHS-DIN-1028 | MF |  | 2024-04-30 | SCS |  | Madison Layton | Software Provider | Update REG1040 description | Update the description for REG1040 to cover both SSC and Profile Class error messages to align with validation rules in IF-025 |  | Initial Assessment/Updating | Error/Correction | Suppliers, REGS |  | Post Go-live Release |  | Update REG1040 to "REG1040 - SSD/ Profile Class Effective From Date must be later than existing" and remove REG1041 in the "Introduction" Tab of DES138 | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1029 | MF |  | 2024-04-30 | SCS |  | Madison Layton | Software Provider | Make B032 block mandatory for [SSCandProfileClass] event in IF-025 and IF-026 | Update Swagger and DES138 to make B032 block mandatory for [SSCandProfileClass] event in IF-025 and IF-026. |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update Swagger and DES138 to make B032 block mandatory for [SSCandProfileClass] event in IF-025 and IF-026. | Data interface correction | Supporting Docs | Supporting document | DES138 & Swagger
MHHS-DIN-1030 | RG | DIN-850 (original IR7 DIN) | 2024-04-30 | Callisto | 50078 | Scott Parkinson | Software Provider | IF037 DSDeApp CustomBlock requires B002 block | Looks as though some of the CR36 changes did not make their way into swagger: the change to include the B002 block in the IF-037 DSDeApp custom block is missing |  | Implemented | Error/Correction |  |  | Interim Release 7.3 |  | Update swagger so that B002 block included in the IF-037 DSDeApp custom block | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1031 | RG |  | 2024-05-01 | EDW Technology | 32016 | Mark Kenny-Jones | Software Provider | Inconsistencies between E2E & Swagger defn of Status Messages | Regarding the SRB that contains empty strings (i.e. the one used to report schema validation errors), are you aware that this does not comply with the current API schema? And if so, are there any plans to either update the schema, or to change the structure of this response so that it does comply with the schema? Specifically, I’m referring to the fact that there are a number of fields in the SRB that have minimum lengths, which an empty string would violate. Similarly, none of the fields are marked as nullable, therefore replacing an empty string with an explicit null value would also violate the schema. Excluding the fields entirely also wouldn’t be an option, as some of the fields are mandatory, and this would also go against the advice in section 4.6.6.2 of the end to end architecture document (E2E001 v3.6) says that “Where a field is not written/available/optional, then a null value needs to be written” |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | The standard Response body has been updated to follow the manadatroy/null design approach. | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1032 | TR |  | 2024-05-01 | ESG |  | Patricia Parker | Software Provider | DI-103-Configurable-Register-ID need to be alpahnumeric | The REGEX in Swagger for DI-103-Configurable-Register-ID which requires numeric values only, the data element should just be a string(2), as per DES-138, to allow numeric or aphla characters. |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update Swagger so the data element is string(2) to allow for numeric and alpha characters | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1033 | MF |  | 2024-05-01 | Helix |  | Rashmi Radhakrishnan | Central Body | Updates to ISD M17/ M7 tables | Updated ISD M17 to add in Meter Group as Char 11 to align with M7 Meter Group. Added allowable values to cover Unmetered in M7 |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated the M17 table to include Meter Group as Char 11. Added Unmetered to Meter Group in both M7 and M17. Updated Meter Type in M7 to “Mandatory. Valid Set as per EMAR1 or U for Unmetered” | Design Ambiguous | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-1034 | RG |  | 2024-05-03 | SCS | 50636 | Mariana Mesaros | Software Provider | REP900 & RE901 are missing schema version ERI011B spreadsheet | REP900 & RE901 are missing schema version in S0 block in ERI011B spreadsheet. The swagger has the schema version |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated ER0I011B with schema version for REP-900/1 | Data interface correction | Supporting Docs | Interfaces | ERI011B
MHHS-DIN-1035 | RG | DIN-850 (original IR7 DIN) DIN-1030 (7.3 DIN) | 2024-04-30 | Callisto | 50078 | Scott Parkinson | Software Provider | IF037 DSDeApp CustomBlock requires B002 block | Looks as though some of the CR36 changes did not make their way into swagger: the change to include the B002 block in the IF-037 DSDeApp custom block is missing |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update swagger so that B002 block included in the IF-037 DSDeApp custom block | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1036 | RG |  | 2024-05-09 | Avanade |  | Ptior Penar | Software Provider | DI-432-Period-Metering-System-Metered-Data requires clarification | DI-432-Period-Metering-System-Metered-Data need to remove multiplier constraint |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update swagger DI-432 | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1037 | RG |  | 2024-05-10 | St Clements | 50045 | Vicki Holland/Tom Perryman | Software Provider | REP900 Changes | Changes to be made to the REP900 are: • REP900-03 to be a parent of REP900-04 • Delete data item DI-563 (LDSO Billing Account Reference) as it is redundant with Site Id and Invoice Number also included in the message • Move the following data items to REP900-04 as they can all change for a site and are specific to the invoice raised: - 612 (Site DUoS Tariff ID), 566 (List of MPANs), 567 (Misaligned multi MPAN site), 568 (Site Capacity) • Update DI-565 LDSO Billing Site ID to data type of String(30) • Add GSP Group ID to the REP900-03 site record |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updates to Swagger & ERI011B | Data interface correction | swagger | Interfaces | Swagger/ERI011B
MHHS-DIN-1038 | MF | DIN 973 | 2024-05-10 | ESG |  | Patricia Parker | Software Provider | Clarify Migration Reqs re D0312 | Requirment updated to refeclt that IF-035 with Lapsed Reason Code of LP001 (MPAN Disconnected/deRegistered) will be issued for any Pending Service Provider Appointments on receipt of MPAN termination (not D0312) |  | Implemented | Error/Correction | REGS |  | Interim Release 8.1 |  | Remove reference to D0312 in the note added to REGS Migration Requirement MHHS-Migration-Can-RS-006 as it is triggered by receipt of a termination of the MPAN from the LDSO following receipt of D0132 | Requirement correction | Migration | Supporting document | Migration Design Requirements
MHHS-DIN-1039 | MF | DIN-946 | 2024-05-10 | ESG |  | Patricia Parker | Software Provider | Update Lapse codes scenario's in DES138 | update DES138 (IF-035) to show LP004 can also apply to MCS scenario and LP006 would only apply to MCA scenario |  | Open - awaiting assessment | Error/Correction | All Participants |  | Post Go-live Release |  | update DES138 (IF-035) to show LP004 can also apply to MCS scenario and LP006 would only apply to MCA scenario | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1040 | RG |  | 2024-05-15 | Kraken | 52894 | Dave MaClean | Software Provider | Migration Deisgn: Missing B095 block in IF-003-MSDeAppRM & missing B096 block in IF-003-DSDeAppRM | Ticket noticed B095 is missing from the IF-003-MSDeAppRM variant. On closer inspection the B096 is also missing from the IF-003-DSDeAppRM |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Both DES138 and the Swagger both need updating: Missing B095 block in IF-003-MSDeAppRM & missing B096 block in IF-003-DSDeAppRM | Data interface correction | Supporting Docs | Interfaces | DES138 & Swagger
MHHS-DIN-1041 | RG |  | 2024-05-16 | MHHS |  |  |  | Alignment of DES138 to message version numbers | The message version numbers in DES138 need to be aligned to the swagger versions, ie. version '011' for release 7.x. Also align IF-061/5 to the other interfaces |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update DES138 to the correct version, update swagger for IF-061/If-062/If-063/IF-064/IF-065 to version '011' so consistent with other IFs |  |  |  | DES138 & Swagger
MHHS-DIN-1042 | RG |  | 2024-05-17 | Kraken | 52894 | Dave MaClean | Software Provider | DI-830 (B070) Swagger/ DES138 descrepancy | The MeteringServiceDIPEffectiveFromDate is from the Data Catalogue on DES138. In the defn of the B070 block the term proposedMeteringServiceEffectiveFromDate is used (ana probabaly the better term to use). However, too late to change, so an update to DES138 to align the B070 to the DC/Swagger is required |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | Update B070 block in DES138 to align with swagger/data catalogue | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1043 | RS |  | 2024-05-21 | Siemens | 53765 | Tony Mason | Metering Service Provider | Method Statement where site is disabled | Method 12 in both SDS and ADS Method statement documents should state the reason code as Disabled, looks like currently a cut & paste from method 11 |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | METH001 (SDS) and METH002 (ADS) to be updated with the following for Method 11 & 12 (replacing SDS with ADS for METH002 - also amending 'Site' to lower case Method 11. Estimation for Long Term Vacant Sites Where the Supplier has notified a Flag to identify that a site is LTV and in cases where no access to consumption data is available, then in the presence of this flag the SDS will estimate zero and set a LTV estimation reason code. This data will be recorded as “ZE2” and the estimation reason code ‘LTV’ should identify as LTV. UTCPDj = 0 Method 12 Estimation where a site where Supply is disabled Where the Supplier has notified a Flag to identify a site where the supply is disabled and in cases where no access to consumption data is possible, then in the presence of this flag the SDS will estimate zero. This data will be recorded as “ZE3” and set the estimation reason code ‘Disabled’. | Method statement correction | Supporting Docs | Method Statement | METH001 METH002
MHHS-DIN-1044 | RG |  | 2024-05-23 | ESG | 54979 | Kerry O'Donnel | Software Provider | IF-009-MPANReconnection has incorrect event code | The event code for IF-009-MPANReconnection need to be [MPANReconnection] rather than [MPANDReconnection] |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | The event code for IF-009-MPANReconnection need to be [MPANReconnection] rather than [MPANDReconnection] | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-1045 | RG |  | 2024-05-29 | SRO |  | Rob Golding | SRO Design | Tidy up of routing rules for IF-041 | The routing rules table for IF-041 requires updating |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | The second and third rows in the routing table in DES138 need to be merged. | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1046 | RS |  | 2024-06-04 | SRO |  | Matt McKeon | SRO Design | Clarifications to the ECS DTN Reports | Retrospective changes made to D0397 - MHHS Supplier Half Hourly Demand Report (now v1.2) D0401 - MHHS Aggregated Disconnected DUoS Report (now v1.1) D0402 - MHHS Supplier Half Hourly Demand Disconnection Report (now v1.1) D0403 - MHHS GSP Group Demand Disconnection Totals Report (now v1.1) D0404 - MHHS Supplier BM Unit Demand Disconnection Report (now v1.1) |  | Implemented | Error/Correction |  |  | Interim Release 7.3 |  | D0397 - Updated the Range of Group 02Z ‘Daily Totals Per Suppler’ from ‘1-1’ to ‘0-*’ D0401 - Amended MM Description to say “A report of Disconnected Volumes by Distributor. Where the report is sent to the Distributor it will contain data for all Suppliers impacted by the Demand Control Event, whereas where it is sent to the Supplier it will only contain data pertaining to that Supplier.” - Renamed DI20306 ‘DUoS Daily Supplier Demand Disconnection Volume’ to ‘DUoS Daily Smart and Unmetered Demand Disconnection Volume’ - Renamed DI20307 ‘DUoS Daily Supplier Demand Disconnection Volume Losses’ to ‘DUoS Daily Smart and Unmetered Demand Disconnection Volume Losses’ - Renamed DI20310 ‘DUoS Supplier Demand Disconnection Volume’ to ‘DUoS Smart and Unmetered Demand Disconnection Volume’ - Renamed DI20311 ‘DUoS Supplier Demand Disconnection Volume Losses’ to ‘DUoS Smart and Unmetered Demand Disconnection Volume Losses’ - Updated the Range of Group 79J ‘Demand Control Event Details‘ from ‘1-*’ to ‘1:1’, so that one report is produced per DDE. D0402 - MHHS Supplier Half Hourly Demand Disconnection Report (now v1.1) - Updated the Range of Group 04K ‘Demand Control Event Details‘ from ‘1-*’ to ‘1:1’, so that one report is produced per DDE. D0403 - Updated the Range of Group 36K ‘Demand Control Event Details‘ from ‘1-*’ to ‘1:1’, so that one report is produced per DDE. D0404 - Updated the Range of Group 43K ‘Demand Control Event Details‘ from ‘1-*’ to ‘1:1’, so that one report is produced per DDE. | Technical corrrection | Supporting Docs | Supporting document | D0397 - MHHS Supplier Half Hourly Demand Report D0401 - MHHS Aggregated Disconnected DUoS Report D0402 - MHHS Supplier Half Hourly Demand Disconnection Report D0403 - MHHS GSP Group Demand Disconnection Totals Report D0404 - MHHS Supplier BM Unit Demand Disconnection Report
MHHS-DIN-1047 | MF | DIN-934 | 2024-06-04 | SCS |  | Daniel Tadecicco | Central Body | Additional value of U for Energisation Status used during Migration | Add new valid value of U - Undefined to DI-033 to allow a value to be populated during Migration. This will be updated with the actual Energisation Status at the stage the IF-036 is issued and the value has been set in Registration Service |  | Implemented | Error/Correction | All Participants |  | Interim Release 8.1 |  | Add U - Undefined as an allowable value to be used for Energisation Status during Migration in DI-033 for IF-001, IF-002 and IF-033 in DES138/ swagger. Participants will be updated with the actual Energisation Status when the IF-036 is issued. Remove U as an allowable value from DI-033 in IF-007 in DES-138. | Data interface correction | Supporting Docs | Interfaces | DES138 & Swagger
MHHS-DIN-1048 | ZH |  | 2024-06-04 | MHHS |  | Zakir Hussain | Consultancy | BRS002 requirements typo | Business Requirements MHHS-BR-MS-071.1 and MHHS-BR-MS-071.2 should be documented within MHHSP-BRS002-Metering Service requirements v5.6 and should apply to both the MSS and MSA Roles. Unfortunately, there is a typo in the Bus Requirement and these are currently showing as DS versions in 3 tabs (all, MSS and MSA) i.e. MHHS-BR-DS-71.1 and MHHS-BR-DS-71.2 which is not aligned to the naming convention around them. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update BRS002-Metering Service Requirements - Change requirement "MHHS-BR-DS-071.1" and "MHHS-BR-DS-071.2" to "MHHS-BR-MS-071.1" and "MHHS-BR-MS-071.2" | Requirement correction | All Areas | Business Requirements Documentation | MHHSP-BRS002
MHHS-DIN-1049 | ZH |  | 2024-06-04 | MHHS |  | Zakir Hussain | Consultancy |  | An exemption has been made in the Qualification process for certain Suppliers. Essentially if a Supplier commits to never supplying Unmetered MPANs they do not have to undertake the qualification tests pertaining to unmetered MPANs – largely as they would have to build capability they would never use. Could I therefore request a DIN be raised to add the following the Supplier Requirements set: · a Supplier not Qualified for UMS shall not migrate UMS MPANs into the new MHHS arrangements. · a Supplier not Qualified for UMS shall not register UMS MPANs in the new MHHS arrangements. This will allow traceability in Qualification assurance to allow qualifying bodies to ask suppliers what controls they have in place to restrict this. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Add the following the Supplier Requirements set: · a Supplier not Qualified for UMS shall not migrate UMS MPANs into the new MHHS arrangements. · a Supplier not Qualified for UMS shall not register UMS MPANs in the new MHHS arrangements. | Requirement correction | All Areas | Business Requirements Documentation | Supplier Requirements Doc
MHHS-DIN-1050 | RG | DIN-211 | 2024-06-06 | SRO |  | Rob Golding | SRO Design | B042 - DI-077 Naming descrepancy | DES-138 has DI-077 named as DI-077-CSS-RMP-DeActivation-Date whilst in swagger the corresponding filed name is CSSMPANDeRegistrationDate. Normally the two should align |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | The YAML DI name in Swagger is aligned with DES-138 and reflects CR024 ie DI-077-CSS-RMP-DeActivation-Date. However the YAML name of the field in swagger is titled "CSSMPANDeRegistrationDate". If required for consistency, the change would be to update the YAML name in swagger to be consistent with the YAML DI name ie CSSRMPDeActivationDate. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-1051 | TR |  | 2024-06-11 | Design Team |  | Tamsyn Robertson | SI Design | MHHS-REP-002B Description Field Update | The Description field in the REP-002B spec is not correct. The reference to Suppliers needs to be removed. The 'To Parties' and 'Routing Rules' are correct. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Change 'Description' field in DES-138 to: 'The report provides aggregated Distribution Use of Systems data for LDSOs or Suppliers in Clock Time.' | Document Correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1052 | TR |  | 2024-06-11 | Design Team | 57348 | Tamsyn Robertson | SI Design | ISD entity M2- Typo | The latest version of the ISD spec currently lists M2 - Connection Type Description H as "High Voltage with Current transformer" with a lowercase "t" in "transformer.". BSCP707 Appendix 1 and Appendix 2 has been updated, so this DIN is to align with the correction to the code. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update M2 - Connection Type Description H to: "High Voltage with Current tTransformer" | Document Correction | Supporting Docs | ISD | EDI021 ISD Entities Document
MHHS-DIN-1053 | TR |  | 2024-06-11 | Opus | 56809 | Lee Eltherington | Supplier | D0397 - Consumption Component Indicator | The Data Item List at the top of the D0397 PDF does not contain the Consumption Component Indicator field that is showing in the dataflow structure. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update the D0397 document to include the Consumption Component Indicator and link to J0162. | Document Correction | Supporting Docs | D-Flow Documents | D0397
MHHS-DIN-1054 | TR |  | 2024-06-11 | ESG | 57833/58471 | Patricia Parker | Software Provider | D0149 - Missing SV | Updates required for the D-flow documentation |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Need all three scenario variants (smart to smart, legacy to smart and smart to legacy). in DTC. Possible error in both the D0149 and D0150. | Document Correction | Supporting Docs | D-Flow Documents | DTC D0149 D0150
MHHS-DIN-1055 | RG |  | 2024-06-12 | Kraken | 58587 | Dave Maclean | Software Provider | IF-006 S0 block missing required properties | InterfaceID, schemaVersion & eventCode fields should be marked as required on the S0 block on the IF-006 interface |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Add required fileds to S0 blocks in all IF-006 variants - InterfaceID, schemaVersion & eventCode | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-1056 | RG |  | 2024-06-26 | Avanade |  | Gaurav Agrawal | Software Provider | R900-04 block remove LDSOBillingSiteID from required list | The R900-04 block still has LDSOBillingSiteID in the required parameters - it needs to be removed |  | Implemented | Error/Correction |  |  | Interim Release 8.2 |  | Remove LDSOBillingSiteID from required field in R900-04 | Technical corrrection | Supporting Docs | Swagger | Swagger
MHHS-DIN-1057 | RG |  | 2024-06-26 | SRO Design | 61939 | Rob Golding | SRO Design | DIP L3 webhook response time set to 10 secs | The DIP timeout on a synchronous response was set to 5 seconds, this will be updated to align with the NFRs |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update E2E SA document & requirements with value | Technical corrrection | Supporting Docs | E2E Architecture Document | E2E001, E2E002
MHHS-DIN-1058 | SB |  | 2024-06-26 | SCS | 62087 | Madison Layton | Central Body | DI-260 Missing MDR and Consent Granularity in MHHS-BR-RS-074 | The Registration Service Requirements is missing the requirement to apply MDR and Consent Granularity to related secondary MPANs when confirming a new Data Service Appointment on a Primary MPAN. Suggested uplift below in red. Detail shown on the Fresh Desk Ticket |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update MHHS-BR-RS-074 | Requirement correction | Registration | Business Requirements Documentation | REGS Requirements
MHHS-DIN-1059 | RG |  | 2024-06-26 | EDW Tech | 62837 | Kavita Siddle | Central Body | IF-020-RelatedCreate has two unwanted Event Codes | IF-020-RelatedCreate has two unwanted Event Codes [RelatedAdd] and [RelatedRemove]. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Remove the two unwanted Event Codes from the IF-020-RelatedCreate message variant in swagger. Shouldn't affect testing as the messages resove to the same structure | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-1060 | RG |  | 2024-06-28 | Avanade |  | Piotr Penar | Software Provider | API Key changes: Add MSG1015 to list of acceptable error codes | Add "MSG1015: X-API Key does not match the sender" error message to Introduction tab on DES-138 and swagger |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update DES138 to include the the new error condition where API key doesn't belong to message sender | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-1061 | RG |  | 2024-07-01 | Avanade |  | Gaurav Agrawal | SRO Design | Add MSG1039, MSG1040, MSG1041 to list of acceptable error codes | MSG1039:Invalid MPAN MSG1040:Not currently appointed MSG1041:MPAN not known |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update DES138 to include the the new error conditions | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1062 | RG |  | 2024-07-03 | Wheatley Solutions |  | Chris Mingay | Software Provider | Connection requests are missiing a User Agent which occassionally trigger FW rule | Add User Agent Header to DIP http requests so that identification is clear on interfacing sysems. Avanade ADO ticket no 42340 |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update CoCo (E2E) to add new http header info | Other | Supporting Docs | E2E Architecture Document | E2E Code of connections document
MHHS-DIN-1063 | TR |  | 2024-07-05 | Helix | 65874 | Riccardo Lampini | Central Body | Measurement Quantity Naming Convention | There are inconsistencies with the use of Measurement Quantity/Measurement Quantity ID within 3 entities as per the ISD Entity Spec and this is not aligned with Swagger/MDS Method Statement |  | Implemented | Error/Correction |  |  | Interim Release 8.2 |  | Update ISD Entity spec and Method Statemenst to align the terminology with what is used in Swagger. MHHS Both Consumption Component Classes (M5) and Load Shape Categories (M4) to state 'Measurement Quantity ID'. This is correct in the Measurement Quantity Entity. Reference tables in Method Statements to be updated. | Document Correction | Supporting Docs | ISD | EDI021 ISD Entities METH001 (SDS) METH002 (ADS) METH004 (UMSDS) METH005 (LSS) METH006 (VAS)
MHHS-DIN-1064 | TR |  | 2024-07-05 | CGI | 62573 | Dave Webster | Software Provider | PUB-045 for UMSDS | According to DES138 5.8.2 sheet 04_IF_OptOut_Matrix, UMSDS can opt out of receiving an IF-045 [InvalidMarketSegment] message. However, according to sheet 02_IF-045, a UMSDS is not a valid recipient of an IF-045. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update 04_IF_OptOut_Matrix to remove UMSDS from IF-045 [InvalidMarketSegment] | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1065 | SB |  | 2024-07-09 | RECCo | 66065 | Jonny Moore | Central Body | Energisation | closed captured in 1073 |  | Closed
MHHS-DIN-1066 | MF |  | 2024-07-10 | EoN |  | Cathy Mulliss | Supplier | Clarification on requirments for maintaining Customer and PSR data by the Data Service | Clarify that the Data Service only has to maintain Customer and PSR data where the data is provided by the Supplier. If the Supplier and Data Service have bilateral agreements whereby this is not required then this data does not have to be shared by the Supplier and maintained by the Data Service . |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | A clarification has been issued as part of the Knowledge Base that Suppliers can make bilateral agreements with Data Services and Meter Reading Services for the provision of meter readings to the Data Service. Where the Data Service does not require Customer/ PSR data to meet their obligations for providing data to Settlements, the Supplier can elect not to share Customer and PSR data to the Data Service. Minor tweak to the requirments to make it clear that this information is only shared and maintained where required. | Document Correction | Meter to Bank | Business Requirements Documentation | BRS001 BRS004
MHHS-DIN-1067 | RG |  | 2024-07-12 | CGI | 67334 | Chris Beard | Software Provider | Ensure Correlation Id information in E2E001 E2E SA doc aligns to DES138 | Reviewing the E2ESA doc the corrleation Id info need to relect the infromation in DES138 |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Minor update to E2ESA doc | Document Correction | Supporting Docs | E2E Architecture Document | E2E001 Architecture Document
MHHS-DIN-1068 | RG |  | 2024-07-12 | Avanade |  | Piotr Penar | Software Provider | Make the elements of the CommonBlock.S0 mandatory | At present the 3 elements of the S0 block: Interface Id Schema Version Event Code are not marked as mandatory. Marking them as mandatory would block issues with missing fields at schema validation rather than causing the DIP to error |  | Implemented | Error/Correction |  |  | Interim Release 8.2 |  | Add required attributes to all S0 blocks to include the 3 fields (inerfaceId, eventCode & schemaVesrion). Zero impact on PPs as not a structural change | Technical corrrection | Supporting Docs | Swagger | Swagger
MHHS-DIN-1069 | RG |  | 2024-07-18 | Imserv | 68171 | Liam Lowey | Software Provider | Removal of oneOf statements in Swagger to faciliate validation at endpoints | The oneOf statement used in the design of the DIP mesages proves to be an issue for using the swagger to validate with the current endpoint definition. Steps could be made to introduce a version alongside the existing one that removes the oneOfs. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | This could be achieved by PPS having endpoints defined for each IFor PUB Event Code combination as per the new valdiation endpoints | Change Request | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-1070 | RG |  | 2024-07-18 | C&C | 67972 | Graham King | Software Provider | Provide replay of status messsages | Request to provide Replay facility for Status Messages |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Woudl need to go into the Avanade backog and be prioiritised accordingly | Change Request | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-1071 | MF |  | 2024-07-19 | SCS | 66166 | Daniel Tadecicco | Central Body | Clarification on when migration appointments are lapsed | Migration appointments will only be lapsed following an MPAN being confirmed as CSS de-activated. This is in line with MHHS BAU operation as outlined in MHHS-BR-RS-103. Therefore, MHHS-Migration-Can-RS-006 is redundant and Migration Design should be aligned to the MHHS BAU operation. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Remove MHHS-Migration-Can-RS-006 and clarify migration design (section 6.1.1 bullet 13) aligns to MHHS BAU operation for CSS de-activated MPANs. | Document Correction | Migration | Migration Requirements | Migration Requirements Log Migration Design Document
MHHS-DIN-1072 | TR |  | 2024-07-22 | Helix | 67485 | Rashmi Radhakrishnan | Central Body | Domestic Premise Indicator Data Type (ISD and DI-031 Data Items) | Both the ISD M4 Domestic Premise Indicator and DI-031 currently have a data type of Boolean but optional. Needs correcting to allow for null, T and F values. |  | Implemented | Error/Correction |  |  | Interim Release 8.2 |  | The ISD Data Item (Domestic Premise Indicator) in ISD Entity M4 to be updated to 'Load Shape Domestic Premise Indicator', this is to align with the DES-138 Data Item DI-031. The ISD Entity Data Item must also be updated to Character (1) optional to allow null values for Advanced Load Shapes. For clarity, acceptable values for the 'Load Shape Domestic Premises Indicator' are 'T', 'F' or 'null'. All reference tables to be updated. UMSDS LSC has a value of null in the Domestic Premise Indicator field - this is incorrect (Unmetered should always be Non-domestic). The LSS Method Statement is correct. UMSDS Method Statement to be updated with 'F' as the LSC value associated to Unmetered. ISD Entity M17 to be updated to remove the row supporting Domestic Unmetered. | Document Correction | Supporting Docs | ISD | ISD Entities Document Swagger DES-138 METH001 (SDS) METH002 (ADS) METH004 (UMSDS) METH005 (LSS)
MHHS-DIN-1073 | SB |  | 2024-07-23 | RECCo | 66065 | Jonny Moore | Central Body | Energisation Status Enumerations | While reviewing the changes made to DES138 for IR8.1 we’ve noticed a discrepancy around the new value of U introduced to the energisation status through DINs 934 and 1047. While the new enumeration has been added in the population notes for the IFs where it will be used, the enumerations held in the data item catalogue have not been updated. As the Energy Market Data Specification (EMDS) stores the enumerations against the data item not the data population rules, we will need this added to the data item catalogue in order for it to be reflected in the EMDS valid set. Without this the value of U will not be a valid value at go-live. Please can the data item within the DES-138 Data Item Catalogue be updated appropriately so we can reflect this in code drafting. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | DES-138 data catalogue to be updated to include the value of "U" for the energisation status | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1074 | PP |  | 2024-07-24 | St Clements | 69275 |  | Central Body | DI-262 B013 CSS Registration ID Block Optionality in Swagger | We’ve spotted an error in implementing DES-138 B013 optionality in swagger. In DES-138 the B013(CSS Registration ID) block optionality is mandatory if available on a series of DIP messages This has been interpreted to mean the block is optional in swagger for a number of the messages. However, for most of the DIP messages the CSS Registration ID is always available and therefore mandatory. The B013 block must be mandatory on the IF-025 IF-031 IF-034 The CSS Registration ID is always available to the Supplier and the Service Provider would always receive a CSS Registration ID in the IF-033 from MPRS. The CSS Registration ID is necessary for the processing of these messages in MPRS. The B013 block should then also be mandatory on the subsequent messages from MPRS namely: IF-026 IF-032 IF-033 IF-035 IF-036 IF-037 It is already mandatory on the IF-001 and IF-002 from MPRS in both DES-138 and Swagger. And for IF-018 the B013 CSS Registration ID block must remain as optional in swagger/mandatory if available in DES-138. IF-018 messages can be generated for MPANs that are not yet registered, and as such no CSS Registration ID would exist for the MPAN. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Align DES-138 and swagger on the B013 block | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-1075 | PP |  | 2024-07-24 | St Clements | 69259 |  | Central Body | DI-261 - Level 5 Validation that proposed MS/DS is valid in ISD on EFD | Hi Design Team, We’ve raised DI-261. MPRS currently validates as a level 4 rule that the proposed MS/DS is valid in ISD at the point of receipt of the PUB-031 but there is no validation that the proposed MS/DS is valid on its proposed EFD. For this MPRS would need to validate as a level 5 validation rule. We’ve raised a change for MPRS to validate MS/DS for their proposed EFD and to use REG1081 as this is the closest matching rule in DES-138 currently. DES-138 needs uplifting to amend REG1081 to apply more generally to MDR, MS and DS. |  | Open - awaiting assessment |  |  |  | Post Go-live Release |  | Update DES-138, REG1081 to apply more generally to MDR, MS and DS. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1076 | TR |  | 2024-07-30 | Programme |  | Tamsyn Robertson | SI Design | ISD Entities Updates | Minor errors in the entties spec to be corrected for completeness. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | M17 - Valid /Consent Granularity Combinations is the title - should be updated to remove "/" - this aligns with BSCP707 drafting M18 - Market Participant Role Code N/A in example should be null. DIP Market Role "LDSO" = DIP Role Description "Licenced Distribution System Operator " not "Licenced Distribution System Operation". DIP Market Role "UMSO" = DIP Role Description "Unmetered Supplies Operator " not "Unmetered Supplied Operator". | Document Correction | Supporting Docs | ISD | EDI021 ISD Entities Document
MHHS-DIN-1077 | RG |  | 2024-07-30 | Design |  | Paul Pettitt | SI Design | Missing 'II' value in the enumerated field for Di-160 | the 'II' run indicator value list needs to be included in the enumerated list |  | Implemented | Error/Correction |  |  | Interim Release 8.2 |  | There is currently a workaroind inplace by C&C where they added II to their local enumerated list, but ultimately the list should include II '- II - Interim Information - SF Initial Settlement - R1 First Reconciliation - R2 Second Reconciliation - R3 Third Reconciliation - RF Final Reconciliation - DR Dispute - DF Final Dispute | Technical corrrection | Supporting Docs | Interfaces | DES-138, Swagger, ERI011B
MHHS-DIN-1078 | TR |  | 2024-08-01 | EDW Tech | 67808 | Alexandre Townsend | Software Provider | REP-002 event code correction | REP-002 event code This has an event code of “[DUOSSupplierAggData]”, but the ECS Reports document says the event code is “[DUoSSupplierAggData]” with a lower case o in DUoS. The Dip simulator also expects the lower case spelling. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | [DUOSSupplierAggData] is the correct representation of the event code - update ESC Reports document | Document Correction | Supporting Docs | ESC Reporting | ERI011B ESC Reports Document
MHHS-DIN-1079 | TR |  | 2024-08-06 | CGI | 70601 | Dave Webster | Software Provider | Sources of Correlation ID | There are a number of Correlation IDs which are created, but I can’t spot where they are subsequently used. IF-003 [ReverseMigNotification] IF-003 [MSDeAppRM] IF-003 [DSDeAppRM] IF-020 [LinkedImportExportCreate] IF-020 [LinkedImportExportAdd] IF-020 [LinkedImportExportRemove] IF-037 [MSDeApp] IF-037 [DSDeApp] IF-065 [MDRInstantaneous] IF-065 [MDRTOU] IF-065 [MDRConsumption] |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update DES-138 Correlation ID Created field IF-003 [ReverseMigNotification] > No IF-003 [MSDeAppRM] > No IF-003 [DSDeAppRM] > No IF-020 [LinkedImportExportCreate] this will contain either the PUB-019’s correlation ID if provided, or in absence of that it’ll contain an LDSO or MPRS generated correlation ID IF-020 [LinkedImportExportAdd] this will contain either the PUB-019’s correlation ID if provided, or in absence of that it’ll contain an LDSO or MPRS generated correlation ID IF-020 [LinkedImportExportRemove] this will contain either the PUB-019’s correlation ID if provided, or in absence of that it’ll contain an LDSO or MPRS generated correlation ID IF-037 [MSDeApp] > No IF-037 [DSDeApp] > No IF-065 [ReadingRemote] > No/Copy | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1080 | RG |  | 2024-08-07 | Kraken | 71005 | Angelos Rizoyannis | Software Provider | Request for DIP API to provide message acceptance information | To provide an API that we can query with a list of transaction IDs and/or Sender Unique Reference numbers, including the status of the messages and whether they were accepted by DIP or not. |  | Open - awaiting assessment | Change Request |  |  | Post Go-live Release |  | Build an API that can be queried, with a list of transaction IDs and/or Sender Unique Reference numbers, including the status of the messages and whether they were accepted by DIP or not. Currently available manually, API requested for automation. | Technical corrrection | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-1081 | TR |  | 2024-08-07 | MDS |  | Vicky Gosar | Central Body | MDS/VAS Method Statement Misalignment - EA12 Flag | MDS method statement refers to ‘E12’ flag while handling missing data. But this ‘E12’ flag doesn’t exist in the CCCs table in VAS method statement. Instead, VAS method statement has reference to ‘EA12’ flag. These need to be aligned - EA12 is correct and aligned to code drafting. |  | Implemented | Error/Correction |  |  | Interim Release 8.2 |  | Update Section 9 (and 14) of MDS Method Statement to update 'E12' to 'EA12'. For clarity, 'EA12' is the correct representation for this flag | Document Correction | Supporting Docs | MDS Method Statement | METH007 (MDS)
MHHS-DIN-1082 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | Most DIP IDs have enumeration as ISD. However DI-108 has ‘no’ enumeration DI-834 has ‘no’ enumeration DI-847 has a blank enumeration. DIN needed to reflect ISD in enumerations column for these 3 data items. |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | Re-opened as post go-live fix. For consistency, update DES-138 Data Catalgue to show enumeration is taken from ISD for DI-108, DI-834 and DI-847. No change to swagger. | Document Correction | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1083 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-218 current supplier DIP ID has MHHS data type DT-027 which is the data type for MPID. The actual format is correct. DIN needed to correct data type to DT-006. |  | Closed | Error/Correction |  |  |  |  | No update required as this data item is not used in MHHS Design (ie not referenced in any interfaces). DIN 1084 removes the Data items from DES138. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1084 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | Swagger data catalogue doesn’t appear to have DI-218 or 219. DIN to be raised – swagger only change |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | DI-218 and DI-219 to be removed from DES138 as they are not referenced in any interfaces and not required for MHHS design | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1085 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-017 Consent Granularity is missing two enumerations in DES138: x # obfuscated value #DIN-858 #- null # DIN-729 need to add null DIN to be raised for additional enumeration x to the list and also to classify Consent Granularity as mandatory nullable |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | Update DES-138, Data item: DI-017 to include "X" as this is a missing enumeration | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1086 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-021 / 22 Customer Direct Contract Metering / Data Service is Boolean. DES138 provides the example Y, Swagger provides example True. The EMDS standards doc defines Boolean as a true or false so assume this should be T or F. DIN to be raised to clarify the examples in both DES138 and Swagger. Not impacting code drafting as this correctly references T/F DI-030 Domestic Premise Indicator - is Boolean. DES138 provides the example T, Swagger provides example True. The EMDS defines Boolean as T or F so swagger example is incorrect. DIN to be raised to clarify the example in Swagger. DI-031 – Load Shape Domestic Premise Indicator – same as above. DIN to be raised to clarify the example in Swagger. EMDS is correct DI-837 Supplier Proposed Domestic Indicator is Boolean but Swagger has example as False. DES138 correctly lists T – Domestic and F – Non Domestic |  | Closed | Clarification - No change required |  |  |  |  | Clarify Boolean data types examples used in swagger and DES-138, example: DI-021 and DI-022 show "Y" in DES-138 and "true" in swagger. Others also highlighted include: DI-030, DI-031, DI-837 Following the implementation of DIN-1114 we are closing this DIN as a duplicate | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-1087 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-046 Load Shape Day Total has an MHHS Data Type of DT-016 in swagger. This is missing from DES138 but may not be an issue as not all data items have an MHHS data type. DIN to be raised to add data type DT-016. |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | Update DI-046 to include the data type "DT-016" to align with swagger | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1088 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-059 Meter Type lists the enumerations in swagger. DES138 points to ISD. Believe Swagger shouldn’t have the enumerations. DIN to be raised to update swagger to avoid future dual governance |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | Registration Service validates that data entered is in line with ISD in IF-005 and therefore enumeration is not necessary for DI-059. Update swagger to remove enumeration values if required to avoid having to update swagger for any ISD updates to this data. | Data interface correction | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-1089 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-080 Consumption Component Indicator has two enumerations in swagger C and L. No enumerations in DES138 however this is an existing data item which also has M (Metering System Specific Line Loss) as an enumeration. DIN to be raised to add missing enumerations to swagger |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | The MHHS design does not require M as an enumerated value for DI-080. M is only required for legacy processes. No change to DES138 or swagger required as M should not be used in MHHS processes | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-1090 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-094 Reading Method has totally different enumerations in swagger compared to DES138 DIN to be raised to confirm which is correct |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | The X&Y values were added to DES-138 as part of CR036 design when we were looking at deriving a read for midnight clock. These were removed from the design as part of the final changes on CR036, however was missed from DES-138 updates. Change should be to remove X and Y from DES138. Values to align with swagger ie A, C, E and S. The data catalogue should be updated to align as part of the DIN | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1091 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-126 Traditional / Fall Back Read Frequency is missing two enumerations in DES138: DIN to be raised to add x as an enumeration in DES138. No issue with the null value as the DI is mandatory nullable - x # Obfuscated value #DIN-858 - null # - DIN-476 - change for nullable enumeration |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | Update DI-126 in DES-138 Data Catalogue with enumeration values from swagger ( ie to include x ). | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1092 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-800 Service Provider Appointment Scenario has a missing enumeration in DES138: xxx # Obfuscated value #DIN-858 DIN to be raised to add xxx as an enumeration in DES138. |  | Closed | Error/Correction |  |  | Post Go-live Release |  | Update DI-800 enumeration values in DES-138 to match swagger. Closed following implementation of DIN 1123 in IR8.3 which has removed the obfuscation from DI-800 | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1093 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-819 De Appointment Reason Code lists the enumerations in swagger. DES138 points to ISD. Believe Swagger shouldn’t have the enumerations. DIN to be raised to update swagger to avoid future dual governance |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | Update swagger to remove enumeration values and to point to ISD, as per DES-138 Deappointment reason codes are not held in ISD. Update DES138 Data Catalogue DI-819 to align with swagger and values outlined in population notes of IF-037 | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1094 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-838 – Supplier Proposed Consent Granularity has a missing enumeration in DES138: xxx # Obfuscated value #DIN-858 DIN to be raised to add xxx as an enumeration in DES138. |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | Update DI-838 enumeration values in DES-138 to match swagger. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1095 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-979 Response code has a missing enumeration in DES138: xxx # Obfuscated value #DIN-858 DIN to be raised to add xxx as an enumeration in DES138. |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | Update DI-979 enumeration values in DES-138 to match swagger. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1096 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-999 Event Code – DES138 is min 3, max 50. Swagger is min 1, max 50. DIN needed to correct DES138 |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | Update DI-999 min and max values in DES-138 to match swagger. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1097 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DT-016 MHHS data type has been defined differently in ECS and DES138. Is 9,3 string 13 or 14. DIN to be raised to align the definition or specify these as different data types. Note the example in swagger is 789.000 which aligns to neither. |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | DT-016 data type to be aligned across DES-138 and swagger. Swagger allows "^-?\\d{1,9}\\.\\d{3}$". This is a maximum of string 14 and a minimum of string 5. The Regex determines this. DES-138 Data Catalogue is string 14. Update to show Min and Max string length. External reporting catalogue is string 13. Update External Reporting Catalogue to string 14 | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1098 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DT032 data type differs in ECS RC compared to swagger. DIN to be raised against data type 032 which states it is string 18 but the example includes 17 characters: -nnnnnnnnn.nnnnnn. The example in swagger is completely different: -10987654321.12 which is string 15. |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | DT-032 data type needs to be aligned across External Reports Catalogue and swagger. Swagger allows "^-?\\d{1,14}\\.\\d{2}$". This is a maximum of 18 and therefore agrees with External Reports. External Reports Data Catalogue is String 18 Examples need to be updated to add quotes around them so they export correctly. Swagger example is fine. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-1099 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-545 – Distributor Bank Sort code is string 8 with an example of 6 characters in ECS RC but max 10 in swagger. DIN to be raised to align |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | DI-545 needs to align across the ECS reports and swagger. DI-545 is data type DT-035 Sort Code which is defined as Min/Max length 6 in swagger. ECS reports has as String 8 in line with DIN 662. Original CR027 requested string length 6. Need confirmation from LDSO's whether 6 or 8 is correct. If 8 required would expect as a defect in SIT. | Technical corrrection | Supporting Docs | Interface Documentation | ECS Reports Swagger
MHHS-DIN-1100 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-083 BSC Settlement Period Quality Indicator – different enumerations in ECS RC compared to DES138. We have used DES138 which has the fuller set. Din to be raised to add missing enumerations to swagger |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | DI-083 needs to be aligned across design: DES138 and swagger align - no change required. ECS reports data catalogue to align with DES138 data catalogue. MHHS-REP-009 DI-083 population notes to be updated accordingly. Other References to DI-083 in the REPS highlight that examples are shown - No change required | Technical corrrection | Supporting Docs | Interface Documentation | ECS Reports
MHHS-DIN-1101 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | IF003 – aligned although there is a lack of clarity in the B095 and B096 block which don’t say the events they are used in. Swagger has the B095 just for MSDeAppRM and B096 just for DSDeAppRM |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | This is defined already in DES138 Re-opened as post go live release update to DES138: Block B095 to highlight the MOP Details are provided for [MSDeAppRM] where available in the Registration Service Block B096 to highlight Incoming DC Details are provided for [DSDeAppRM] where available in the Registration Service | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1102 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | IF013 – Swagger refers to B920 list which is not referenced in DES138. In the swagger common block B920 is defined. This references the B050, B046 and B048 blocks which makes sense but also references B045. B045 just includes Measurement Quantity Id (DI-052) which is on B050 in the IF013. Suggest raising DIN seeking confirmation on whether the B045 is needed as a separate block in the IF013. |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | Re-opened as post go live release update. The use of Blocks 9xx is used in swagger to define arrays, intentially not referenced in DES-138 However, there is an error in the description of the B920 block which refers to Block B045, this should reference Block B050. Recognise that the block is labelled incorrectly, but a change to the block would impact all participants. | Technical corrrection | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-1103 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | IF016 has an event of consumption request rejected. This is not mentioned against any blocks in DES138 but there is a statement against B067 and B046 that its mandatory except replay request rejected – suggest the latter is an error in DES138 and should say ‘mandatory except consumptionrequestrejected |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | IF-016 needs updating in DES-138 to align with swagger. Update conditions for B046 and B067 blocks to state "Mandatory except for [ConsumptionRequestRejected]" | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1104 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | IF034 DS App event in swagger includes B070 which is the proposed metering service. DES138 only has this mandatory for MS App event. Looks like swagger error – row 5154 |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | IF-034 would need updating in swagger to align with DES138 as the B070 block is not required for [DSAppSPResponse]. However, as the B070 block is optional for this event the swagger currently does work. | Technical corrrection | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-1105 | PP |  | 2024-05-05 | Design |  | Paul Pettitt | Central Body | API Guidance | Need to incorporate the guidance issued relating to the 1MB limits and message batching into the E2E001 Technical Architecture documents |  | Implemented | Clarification - No change required |  |  | Interim Release 8.2 |  | Pertinent sections from the guidance to be included in to the E2E001 solution Architecture document |  | Supporting Docs | E2E Architecture Document | E2E001
MHHS-DIN-1106 | 46 | Defect 37835 | 2024-08-14 | Design |  | Amy Loder | Software Provider | B907 Block requires mandatroy properties | In the IF-002 interface the B907 is required for linked MPANs. In the B907 the fields are not marked as mandatory. The issue also affects the B910, B908 & B911 blocks |  | Implemented | Error/Correction |  |  | Interim Release 8.2 |  | Updates to swagger to mark elements required in these blocks. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-1107 | RS |  | 2024-08-15 | Design | 72837 & 78768 | Neil Strange | Supplier | Removal of requirement MHHS-Migration-Can-Sup-001 | Do not believe this requirement is needed. For Forward Migration CoA we are only de-appointing the legacy agent when the migration is confirmed by Pub-036 Therefore this requirement is redundant – a cancellation due to CoS will mean that we will not have got this far and won’t receive PUB-036. |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | Suggest removal of requirement | Migration requirements | Migration | Migration Requirements | DEL2430, BP-003, BPM-003
MHHS-DIN-1108 | RS |  | 2024-08-16 | Design |  | Rob Short | Central Body | Removal of requirement MHHSP-BRS014-ECS-BR-RD-018 Meter Indicator is not sent to MDS as per DES138 | Update to process map and removal of requirement required as MDS do not need the [MUMIndicator] as shown in routing in DES138 |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Removal of requirement MHHSP-BRS014-ECS-BR-RD-018 and update to BP010 to remove from swim lane | ECS requirements | Supporting Docs | Business Requirements Documentation | BRS014 BP010B step 620 BPD010
MHHS-DIN-1109 | PP |  | 2024-08-16 | Design |  | Paul Pettitt | Software Provider | Guidance Note Required | Create Guidance note covering the population of the Consent granularity following defect 38353 |  | Open - awaiting assessment | Clarification - No change required |  |  | Post Go-live Release |  | Create Guidance note covering the population of the Consent granularity following defect 38353 | Guidance | Guidance | Guidance | Guidance note
MHHS-DIN-1110 | RG |  | 2024-08-20 | Design | 74698 | Richard French | Software Provider | Incorrect version number | Incorrect version number on IF-033, shows 009, should be 011 in DES-138 |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Minor update in DES-138 | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1111 | RS | Defect 37939/37984 | 2024-08-20 | Design |  | Richard French | Software Provider | Further explaination regarding same day/retro appointment of MS/DS | IF-036 has current statement - Depending on the actions of the Supplier, Blocks B16/B17 may not always be known to the Registration Service at the time IF-036 is published. As there is no re-publication Service Providers may need to reference EES(Ecoes) or liaise with their appointing Supplier for confirmation of any missing Partner Service. |  | Open - awaiting assessment | Clarification - No change required |  |  | Post Go-live Release |  | Further explaination added to IF-036 note in DES138 | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1112 | SB | Defect 39963/38352/39202 | 2024-09-03 | Design |  | Steve Bradford | Central Body | Correlation ID for Related/Linked MPANS Within PUB-031 | The IF-036 does not have the ability to populate a correlation ID for a Linked/Related MPAN. New event codes maybe required for LINKED/Related scenarios additionally a similar issue has been identified with the IF-008 |  | Updates Ready to Release | Error/Correction |  |  | Interim Release 8.4 |  | Discuss options with SCS with the potential to introduce new event codes specifically to support Linked/Related MPANS | Data interface correction | Interface Documentation | Interface Documentation | DES-138
MHHS-DIN-1113 | SB | Defect 39989 | 2024-09-03 | Design |  | Steve Bradford | Central Body | REP-901 Error in the swagger Regex pattern | When producing the report for an Export tariff the following field: Data Block: R901-08 Data Item: totalVolumeChargeForChargeBand is generating a negative number. According to the RegEx pattern in the Schema a negative value is not allowed, despite the fact that the example value is a negative: |  | Implemented | Error/Correction |  |  | Interim Release 8.3 |  | Amendement to Swagger to allow for the Data Block: R901-08 Data Item: totalVolumeChargeForChargeBand to be amended to include the ability for a negative to be allowed. Update the regex pattern for DT-032-Decimal-14-2, DT-031-Positive-Decimal-2-2 and DT-033N-Decimal-15-5 (unused at present) |  | Interface Documentation | Interface Documentation | Swagger
MHHS-DIN-1114 | SB |  | 2024-09-03 | Design |  | Steve Bradford | Central Body | Clarification On Boolean definitions | Following a number of Defects being raised in SIT Inconsistent applications of Boolean have been idnetified in various parts of the design. The lack of consistency is causing implementation issues for Participants |  | Implemented | Error/Correction |  |  | Interim Release 8.3 |  | Amend design artefacts to align with the agreed Boolean definition as per Swagger and guidance documentation. DI-021 = changes to DES-138 (IF-001 and IF-002) DI-022 = changes to DES-138 (IF-001 and IF-002) DI-030 = changes to DES-138 (IF-001, IF-013, IF-016, IF-018, IF036) and ERI011b (REP-901) DI-127 = changes to DES-138 (IF-001, IF-002, IF-018, IF-033, IF-036, IF-043, IF-044 and IF-050) DI-357 = changes to ERI011b (R003 and R003A) DI-486 = changes to ERI011b (REP-002, REP-002a and REP-002b) DI-567 = changes to ERI011b (REP-900) DI-837 = changes to DES-138 (IF-031, IF-032, IF-033, IF-034 and IF-035) |  | Interface Documentation | Interface Documentation | DES-138 Swagger ECS Reporting
MHHS-DIN-1115 | SB |  | 2024-09-03 | Design |  | Steve Bradford | Central Body | DI-988 Replay Indicator Amend to Mandatory No Nulls to align with DIN-1114 | The DI-988 is currently set to Mandatory Nullable, as part of the DIN-1114 alignment would be to amend this to Mandatory no nulls |  | Implemented | Error/Correction |  |  | Interim Release 8.3 |  | Amend DI-988 to be a Mandatory value rather than Mandatory no nulls. This impacts DES-138 and Swagger. |  | Interface Documentation | Interface Documentation | Swagger DES-138
MHHS-DIN-1116 | PP |  | 2024-09-04 | LDSO |  | Paul Pettitt | Central Body | CR054 Updates to Non-Functional Requirement | Updates to NF requirements to reflect the original volumes included GAS metering that needs to be removed, Removal of a duplicate requirements, and definition of 'All Service' | CR054 | Implemented | Error/Correction |  |  | Interim Release 8.3 |  | Update the Non-functional requirements document E2E002 with updates as approved in CR054 |  | Non-Functional Requirements Documentation | Non-Functional Requirements Documentation | E2E002
MHHS-DIN-1117 | SB | 39966 | 2024-09-04 | Helix | 75833 | Nigel Rees | Central Body | Duplicate consumption data for LSS and MDS roles | We have come across an anomaly in our testing. We have registered for interfaces for both LSS and MDS including the Consumption interface. We are receiving duplicate consumption messages which will mean double the already significant consumption load in production. We believe we need to register the interfaces for both LSS and MDS roles so people querying the DIP can audit flows for both roles. Obviously receiving duplicate data is inefficient and costly. It will also mean our performance tests at current levels are invalid. |  | Implemented | Error/Correction |  |  | Interim Release 8.3 |  | Update the Always routing of the IF-21 to only go to the Role LSS, to amend DES138 IF-021 |  | Interface Documentation |  | DES-138
MHHS-DIN-1118 | ZH |  | 2024-09-04 | Design | 77726 | Dave Webster | Software Provider | DES-138 Typo in IF-023 | The definition of an IF-023 in DES138 v5.8.2 has the following: DI-045 Load Shape Day Peak Total The sum of Period Values (kWh) for settlement periods (15 to 48) or (1 and 16 to 48). UTC times 7pm – Midnight DI-044 Load Shape Day Off-Peak Total The sum of Period Values for settlement periods (kWh) (1 to 14) or (2 to 15). UTC times Midnight -7pm These should say 7am rather than 7pm. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update DI-045 and DI-046 where it says "7pm" to "7am" in the description field for IF-023 | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1119 | RG | DIN-1056 | 2024-09-06 | EDW Tech | 76498 | Mark Kenny-Jones | Software Provider | GSP Group ID & LDSOBillingSiteID should be mandated for the R900-03 block | Previously LDSOBillingSiteID was removed from the required list for the R900-4 block (DIN-1056), the required field should have been moved to the R900-03 block. GSP Group Id needs to be marked as required too. |  | Implemented |  |  |  | Interim Release 8.3 |  | Update swagger to include LDSOBillingSiteID in the required field for R900-03 | Data interface correction | Interface Documentation | Interface Documentation | Swagger
MHHS-DIN-1120 | RG |  | 2024-09-09 | Design |  | Rob Golding | SRO Design | Duplicate DT033 | At present there are two DT-033s defined in the Data Type Catalogue: DT-033-Decimal-15-5 & DT-033-Email. DT-033 E-mail will moved to DT-036. DI-600 on the REP-900 tab is not aligned with the Data Catalogue - REP-900 DI-600 to be updated to String19. |  | Implemented |  |  |  | Interim Release 8.3 |  | Swagger update DT-033-Email to DT-036-Email. ERI011B has been updated to change DT-033 to DT-036 for DI-533. | Data interface correction | Interface Documentation | Interface Documentation | Swagger, ERI011B
MHHS-DIN-1121 | RS |  | 2024-09-10 | Elexon | 78399 | Colin Berry | Central Body | No associated Enumeration Value for DI-143 'Proposed Appointment Response Code' | The DI-143 ‘Proposed Appointment Response Code’ is defined in the ‘Data Catalogue’ tab in DES138 v5.8.2 as “String(200)”, with no associated Enumeration Values required (“ENUM Y/N” = N) and the “EXAMPLE” is given as ‘SP000’ and the “String Format” is given as ‘XXnn’, which is not consistent with “String(200)”. |  | Open - awaiting assessment |  |  |  | Post Go-live Release |  |  | Data interface correction |  | Interface Documentation | DES-138
MHHS-DIN-1122 | ZH |  | 2024-09-10 | Design | 78142 | Kamlesh Patel | Central Body | Duplicate requirement reference used in BRS003 | There are two requirements "MHHS-BR-RS-071.13" in the latest BRS003 document |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update the requirement that references step 340 with a new number e.g. "XX.132" | Document Correction | Meter to Bank | Business Requirements Documentation | BRS003 BPD010
MHHS-DIN-1123 | MF |  | 2024-09-13 | Design |  | Dave McLean | Metering Service Provider | Removal of Obfuscation for IF-035 [IMS-SendMTD] in DI-800 | Remove the obfuscation for Service Provider Appointment Scenario (DI-800) from IF-035 so that the Metering Service can distinguish a Change of Segment Appointment when no MTDs are required. |  | Implemented |  |  |  | Interim Release 8.3 |  | Remove DIP obfuscation from DI-800 in IF-035 | Data interface correction | Interface Documentation | Interface Documentation | Swagger, DES-138
MHHS-DIN-1124 | TR |  | 2024-09-17 | Elexon | 76217 | Rashmi Radhakrishnan | Central Body | VPSR - Business Rule | C05 and DF4 - As the Switch events are data type ‘Time’ you cannot have Timer (Off), PECUS (Off) in that field. |  | Open - awaiting assessment |  |  |  | Post Go-live Release |  | Add the following Business Rule to ISD Entities Spec: Where a Switch Event is ‘NULL’ but followed by a % Power Level that is not ‘NULL’ then it is deemed that a Switch Event has occurred driven by the Timer or PECUS. | Missing validation rule | ISD | ISD | ISD Entities Document
MHHS-DIN-1125 | ZH |  | 2024-09-23 | MHHS | 80549 | Natasha Tomic | Central Body | Incorrect requirement: MHHS-BR-MS-026 | The following requirement (MHHS-BR-MS-026) should be removed from the MHHSP-BRS002-Metering Service requirements v5.6.xlsx (sharepoint.com) on the UMSO tab as it is not applicable for UMSO role. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Update Metering Service Requirments to remove MHHS-BR-MS-026 from the UMSO tab | Document Correction | Meter to Bank | Business Requirements Documentation | BRS002
MHHS-DIN-1126 | RG | 40889 | 2024-09-25 | Energy Assets |  | Thomas Johnson | Software Provider | Incorrect event code used in IF-015/16 - documentation update | There is a descrpancy between the IF-015/016 design note and Swagger/DES-138. The design note has an event code of [RequestRejected] in DES138/Swagger [ConsumptionRequestRejected]. Design note needs to update to match swagger/des138 |  | Open - awaiting assessment | Error/Correction |  |  |  |  | Documentation update | Document Correction | Interfaces | Design Note | IF-015/016 Design note
MHHS-DIN-1127 | RS |  | 2024-09-26 | MHHS | 81161 | Kamlesh Patel | Central Body | Incorrect requirement: MHHS-Migration-CoA(MS)-RS-006 | The following requirement (MHHS-Migration-CoA(MS)-RS-006) should be removed from the Migration requirements (DEL974 Registartion Service tab) as it is not applicable for REGS to send the MS variant to ECS |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release |  | Solution yet to be defined | Document Correction | Migration Requirements | Business Requirements Documentation | DEL974 Migration Design requirements log
MHHS-DIN-1128 | MF | Defect 39963 | 2024-09-26 | SCS |  | Madison Layton | Software Provider | Null correlation ID's on IF-008 | Update Correlation ID section and notes for IF-008 to highlight that where an unsolicited IF-008 is issued the correlation ID will be null (ie not copied as there is no IF-007 to copy it from ) |  | Ready for Internal Review | Error/Correction |  |  | Interim Release 8.4 |  | Update DIP to allow Null correlation ID's for IF-008 and update DES138 to show that a null correlation ID may be issued where an unsolicited IF-008 is issued | Data interface correction | Interface Documentation | Interface Documentation | DES-138 DIP-050
MHHS-DIN-1129 | RG |  | 2024-09-27 | Avanade |  | Piotr Penar | Software Provider | Add validation end-points for all REPs | Avanade have requested that the validation end-points are added to the swagger |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update swagger to include the extra valdiation end-points | Data interface correction | Swagger | Interface Documentation | Swagger
MHHS-DIN-1130 | TR |  | 2024-10-02 | Design |  | Tamsyn Robertson | SI Design | SDS Method 7 additional scenario coverage | Method 7 should be used for non-smart meters with switched load, smart meters non-comms with switched load where historical data is available or opted out smart meters with switched load.Currently, the smart meters non-comms with switched load where historical data is available scenario is missing from Method 7. |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Add the smart meters non-comms with switched load where historical data is available scenario to Method 7 | Missing scenario | Method Statement | SDS Method Statement | METH001 (SDS)
MHHS-DIN-1131 | TR |  | 2024-10-02 | Helix | 68335 | Rashmi Radhakrishnan | Central Body | Data Tye update - DUoS Tariff Domestic Premise Indicator | An LDSO expressed concerns about including this, given they are not responsible for providing this data, it was agreed to raise a DIN to modify the "DUoS Tariff Domestic Premise Indicator" to a one character from Boolean to include True/False/NULL option. In cases where the data is unavailable, NULL can be used as the value, and agreed that this change can be developed after post-go-live (after M10). Supporting NULL as an option will be used for NHH export tariffs. |  | Open - awaiting assessment |  |  |  | TBC |  | "DUoS Tariff Domestic Premise Indicator" to be updated to an optional 1 Char Data Type. Acceptable values = T, F or NULL. |  | ISD and Reporting |  | ISD (Entity 17) ERI011b
MHHS-DIN-1132 | SB |  | 2024-10-03 | Callisto | 82101 | Christie Pace | Data Service Provider | Migration requirement & design Misalignment | There appears to be a miss alignment with DEL974 Requirements v1.2 log and DEL961 Migration design document v1.4. MHHS-RMigration-CoA(DS)-DC-005 still holds previous values for Reading Type and Meter reading Readon Code for the D0010. |  | Open - awaiting assessment | Error/Correction |  |  | Post Go-live Release
MHHS-DIN-1133 | RG | Defect 41296 | 2024-10-07 | BUUK |  | Stuart Riding |  | IF-020 event codes are duplicated in IF-020-RelatedCreate | BUUK have a query against IF-020. Its's not causing an issue as all the messages for the event codes RelatedCreate, RelatedAdd, RelatedRemove will all resolve to the same structure as they are all identical. However, it does not align to the design pattern we have adopted elsewhere in the swagger definitions where each event code is explicitly defined. |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update swagger to remove the RelatedAdd & RelatedRemove evenot codes from the IF-020-RelatedCreate variant | Data interface correction | Swagger | Interface Documentation | Swagger
MHHS-DIN-1134 | TR |  | 2024-10-07 | C&C | 85111 | Hazel Cotman | Software Provider | Invalid UMSO Requirements | MHHS-BR-MS-041 and MHHS-BR-MS-042 are not applicable to Unmetered MPANs. These are to be removed from the UMSO requirement set. |  | Open - awaiting assessment | Error/Correction |  |  | TBC |  | Update Metering Service Requirments to remove MHHS-BR-MS-041 and MHHS-BR-MS-042 from the UMSO tab | Requirement Clarification | Requirements | Metering Service Requirements | BRS002-Metering Service requirements
MHHS-DIN-1135 | SB | DIN1128 | 2024-10-11 | SCS |  | Madison Layton | Software Provider | Null correlation ID's on IF-035 | Update Correlation ID section and notes for IF-034 to highlight that where an unsolicited IF-035 is issued the correlation ID will be null |  | Initial Assessment/Updating | Error/Correction |  |  | Interim Release 8.4 |  | Update DES-138: Correlation ID section and notes for IF-034 to highlight that where an unsolicited IF-035 is issued the correlation ID will be null | Data interface correction | Interface Documentation | Interface Documentation | DES-138
MHHS-DIN-1136 | MF | DIN 1106 | 2024-10-11 | RECCO |  | Sarah Jones | Central Body | Incorrect update to B075 block in DES138 | In fixing defect 37835 under DIN 1106 an incorrect update was made to DES138. The MAP block will always be provided by the Registration Service and should be confirmed as mandatory |  | Initial Assessment/Updating | Error/Correction |  |  | Post Go-live Release |  | Update DES138, B075 block in interfaces IF-002, IF-006, IF-020, IF-033 and IF-036 to state Mandatory for each Meter Provided | Data interface correction | Interface Documentation | Interface Documentation | DES-138
MHHS-DIN-1137
MHHS-DIN-1138
MHHS-DIN-1139
MHHS-DIN-1140
MHHS-DIN-1141
MHHS-DIN-1142
MHHS-DIN-1143
Formulas:
Objection Cut-off Date = IFNA(VLOOKUP([Target Release],[1]!Table2[#All],3,FALSE), " ")
Objection Cut-off Date = IFNA(VLOOKUP([Target Release, row above],[1]!Table2[#All],3,FALSE), " ")

## 020625 (hidden)
DIN ITEM DETAILS | [13 empty] | Internal Assessment |  |  |  |  | DIN IMPACT ASSESSMENT |  |  |  |  | DIN OUTCOME |  |  |  |  | Incremental Release 1
Reference | Created BY | other Reference(s) | Date Raised | Organisation | Freshdesk Ticket # | Contact Name | Constituency | Title | Design Issue Notification Details (as notified by participant) | Related CR | Current Status | Testing Defect DIN? | Testing Defect Reference # | DIN Type | Who is impacted? | Target working Group Date (If Required) | Target Release | Objection Cut-off Date | Target working Group Date (If Required) | Target Release | Objection Cut-off Date | Design Issue Proposed solution | Justification/Type of Change | Design Area | Design Area - L2 | Artefact(s) Impacted | Design Change Reference Number | Internal Freeze Date
MHHS-DIN-1 |  | T4-COM-1744 | 2023-01-30 | St Clements | 2655 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1744 on 15th Sept 2022 MPRS does not currently restrict IHD Installs to Smart Meters, there maybe cases where there is an IHD present but the Meter is Trad (Not compatible with DCC and Customer Switched) Either Allow IHD on all Market Segments OR Cleansing to ensure IHDs are only present on S2 and S1 Meters SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses, as this is still not resolved |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Discussed with SCS and agreed to add new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) Added requirements into BRS003. SCS to raise a potential data cleanse. | Requirement correction | MPAN Ownership | SCS Validation | MHHSP-BRS003-Registration Requirements
MHHS-DIN-2 |  | T4-COM-1745 | 2023-01-30 | St Clements | 2657 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1745 on 15th Sept 2022 DB002 is not the interface on which MPRS will be informed of a change to import/export relationship, it is DB05. The wrong diagram was updated, the EDI was updated to DB05 not import/export. SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses and artefact updates, to inform the wrong data item diagram was updated. However the diagram for EDI updates is still incorrectly reading DB005 update instead of DB02 |  | Closed | [6 empty] | #REF! |  |  | #REF! | This appears to have been missed in v4.6 - the arrow on BP-010B from step435 to Step 440 shows DB005 (not DB05, assume that’s a minor typo in the comment) - and this is the Energy Direction Information (EDI) which is wrong. It has cbeen onfirmed that this was updated in v4.7 to go into v5.0 baseline. | No Change |  |  | None
MHHS-DIN-3 |  | T4-COM-1752 | 2023-01-30 | St Clements | 2661 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1752 on 15th Sept 2022: MHHS-BR-RS-020: "Retro" (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier ) In the D0205 the Supplier can cancel out the current Agent Appointment by setting the EFD to equal the currently stored Appointment EFD. Is this no longer allowed? All Services must be appointed for at least one day valid or not? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: removing the ability for Suppliers to Correct Invalid Service Appointments may not be understood by suppliers. We want to avoid a later Design CR to add this functionality in. SCS has not had a response, feel this is important discuss with Suppliers to avoid later CRs |  | Closed | [6 empty] | #REF! |  |  | #REF! | The appointment can be resubmitted if it hasn’t been accepted yet. Once accepted, there is a need to maintain contiguous appointment periods. The scenario mentioned is the CoA not linked to a switch, so the acceptance of a new appointment from a particular EFD will ‘lock in’ that date and the previous MS/DS will be de-appointed at midnight on the previous day. This is to ensure that there are no periods left without MS and/or DS in place, which can happen today with D0155/D0151 sequencing issues. As an overall comment, there is not a concept of cancellation of appointments. The only way to alter the appointment is to get a new IF-031 issued. The only way to do this for the scenario presented, would be to issue an IF-031 for the old MS for the original date and an IF-031 for the new MS for the revised date. Requirement MHHS-BR-RS-021 ensures that Registration Service will action the latest received appointment where there are duplicate appointments for the same day. St Clements had requested that we build in a rule saying that you cannot submit a Change of Service Provider (CSP) request for the same Service Provider. It is a bit of a work-around, but we believe sending it as SEG should work, or alternatively a CR would be required to re-look at the interface validation. Closing, as this doesn't require further action - point noted. We have already spoken to a number of suppliers, and will continue to engage to ensure the functionality of the baselined design is understood and any issues picked up as early as possible. Documentation for LDSOs to point at. Pick up in Code Drafting as well. | No Change |  |  | None
MHHS-DIN-4 |  | T4-COM-1755 | 2023-01-30 | St Clements | 2666 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1755 on 15th Sept 2022: MHHS-BR-RS-071.2 REC CP R062 has been raised to remove the restriction on the number of EDI changes. Will this cause any downstream MHHS issues? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Needs to be aligned with REC Change No responses |  | Closed | [6 empty] | #REF! |  |  | #REF! | As per original SRO response, the impacts of the REC change need to be dealt with through the REC change process and impact assessment. | No Change |  |  | None
MHHS-DIN-5 |  | T4-COM-1760 | 2023-01-30 | St Clements | 2667 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1760 on 15th Sept 2022: There are no Registration Service Reports defined in MHHSP-ERI011A. Will there be a requirement for MPRS to produce any Industry Reports for MHHS? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Design for the complete solution must be defined by M5. This is a DBT Design Start Blocker No responses This could significantly increase DBT time as development of reports can be costly and time consuming |  | Closed | [6 empty] | #REF! |  |  | #REF! | Who is raising these requirements? What happens today? Possibly CC issues Agreed with SCS that reporting requirements will be introduced via the CR process. Reporting requirements are to be added to the programme RAID log | No Change |  |  | None
MHHS-DIN-6 |  | T4-COM-1761 DI-7 | 2023-01-30 | St Clements | 2668 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1761 on 15th Sept 2022: IF-005, REG1014 First MAP Block, MAP Eff From Date [DI-054] in message, must = MPAN Install date OR >= Eff Form date of all existing MAP Effective From Dates held in Registration prior to first [DI-054] in message I understand that the First MAP must equal the Install Date, I am unsure what the second condition is trying to say? You can not have a Meter Without a MAP. (ignoring customer owned meters where CUST is used) SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: response is incorrect. The Second Rule "Each subsequent MAP Effective From Date [DI-054] must be > MAP Eff From Date in previous block" covers the subsequent overlapping MAPs. The second half of this First Block Rule must be removed. The First Block can only ever equal the install date No responses, the rule has not been amended |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | This appears valid - the first MAP block can only start at the creation date (assuming the MAP blocks are in chronological order, which they must be if each subsequent map block has an EFD > the last) Currently the design allows 2 ways to amend the MAP History as outlined in Sections 13 and 14 of the IF005 Use Case Guide. Either the Metering Service can provide the full MAP history from the installation date or they can add a new MAP to the existing history, provided it is the next MAP in chronological order. So for example if you have MAPs 1,2 and 3, then you can extend to MAPs 1,2, 3 and 4 using the approach set out in section 14 to extend the MAP history. However if you wanted to set MAP 4 between 2 and 3, you would need to send the whole MAP history from the install date and provide 1,2,4 and 3 as set out in Section 13 to replace MAP history. The second validation rule is required if you are using the extend the MAP history functionality. Added note to REG Notes that where a MAP history is provided it must be in chronological order Added new REG1014 Validation Rule to MeterInstall and MeterExchange events to ensure only 1 MAP block is provided | Data interface correction | MPAN Ownership | SCS Validation | MHHSP-DES138-Interface Catalogue
MHHS-DIN-7 |  | DI-8, DI-11, DI-12, DI-14 | 2023-01-30 | St Clements | 2669 | Madison Layton | Software Provider |  | MPRS will reject any PUB-031 including those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | See Comments Revised CSS Registration Request ID validation on IF-031, 034 and 025 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | IF General | MHHSP-DES138-Interface Catalogue
MHHS-DIN-8 |  | N/A | 2023-02-01 | Elexon | 2642 | Sedef Kiris | Central Body |  | We have had the following comment ........... Also just found out that “Metering Service Id” have “MPID” in brackets afterwards, and not “MSID”. We believe it should be MSID |  | Closed | [6 empty] | #REF! |  |  | #REF! | MPID is the correct term here, it is the metering service MPID. MHHSP_EDI012_ISD_Entities v4.6 Section M8 | No Change |  |  | None
MHHS-DIN-9 |  | N/A | 2023-01-30 | St Clements | 2672 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: [UpdateSiteTechnicalInfoMS] is not included in the interface catalogue and is not utilised by MPRS. Assume this is related to Issue 99 and needs removing? (raised as DI ID 9) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Removed from IF-005 Guide Section 4.1 | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-10 |  | N/A | 2023-01-30 | St Clements | 2799/2670 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: Is the currently appointed Meter Service informed of Prospective MS changes? Changes to MTDs can be made by prospective MS (e.g. change meter type to complete SEG market change before the MS can be appointed). As the MS is only prospective at this point the MS may still be lapsed and not take effect. However any MTD updates made would remain within the MPRS system and not be backed out. The current MS would therefore need to be aware of what changes have been made by the prospective MS. (raised as DI ID 10) |  | Closed | [6 empty] | #REF! |  |  | #REF! | BP009 only talks about the Metering Service, not the current or prospective Metering Service, and it appears only the registration service receive metering service MTD details, not the current MS. Refer to SRO - what is the assumption here, as the alternative route is for registration to update the current MS The design is based on PUB-006, with the Updated Meter details, being sent to the current Metering Service ( BP011A step 280 ) as well as the Prospective Metering Service (Step 275). It is built into the routing rules in PUB-006. | No Change |  |  | None
MHHS-DIN-11 |  | N/A | 2023-01-30 | St Clements | 2675 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install / Remove Date(s) takes place within the Metering Services period of ownership (or proposed period of ownership for in the case of a prospective SEG appointment) " Sent on 11th Jan: Does not match business rules, as future dated installs are not allowed: "REG1020 - Meter Install Date [DI-057] cannot take place in the future. The proposed MS on a seg will have a future dated EFD, so they only have the +2 day lapse extension period for meter installs (raised as DI ID 11) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Added change of segment scenario's to IF005 USE CASE Guide. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-12 |  | N/A | 2023-01-30 | St Clements | 2679 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install /Remove Date(s), cannot have taken place in the future" Sent on 11th Jan: It would be useful to have the Change of Segment process covered in this guide. We are not sure how the Prospective MS can exchange meters when their appointment period is in the future (raised as DI ID 12) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Nomenclature issue - requires a reword of this statement to conform to the business rules. Recommend the following update to section 3.2 of the IF005 Use Case Guide to confirm who can make Metering updates Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed BAU metering updates ( For the avoidance of doubt not meter update/meter history updates), it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. The one exception, is during a change of segment, when the incoming Metering Service is able to provide a BAU metering update, where it’s prospective “SEG” appointment is due to become active on the same day. SEG scenario's added to IF005 Use case guide Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-13 |  | N/A | 2023-01-30 | St Clements | 2683 | Madison Layton | Software Provider |  | Comment on Section 5.1 "validation allows for meter removal at a point following Disconnection if required)" Sent on 11th Jan: This rule prevents this REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational (raised as DI ID 13) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | This statement doesn't appear to be a convention. There is no mention of this in E2E001 End to End Solution Architecture. Believe this statement needs to be amended or removed. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. IF-005 validation Rule changed to include meter removal at status Disconnected | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES138-Interface Catalogue, E2E001 End to End Solution Architecture
MHHS-DIN-14 |  | N/A | 2023-01-30 | St Clements | 2684 | Madison Layton | Software Provider |  | Comment on Section 3.2 "Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed metering updates, it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. " Statement is misleading- the 10 day period is only permitted for install, remove and exchange events, it is not listed for meterUpdate/meterHistoryUpdate in interface catalogue Also the prospective MS should be able to make changes for SEG to enable a market segment change to complete (raised as DI ID 14) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Validation rule(s) updated to constrain 10 day window to non-update events. Test in 3.2 reworded to remove ambiguity. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-15 |  | N/A | 2023-01-30 | St Clements | 2685 | Madison Layton | Software Provider |  | Comment raised in guide, sent on 11th Jan, that the JSON examples use MPID when it should use DIP ID e.g."distributorID": "SWAL" (raised as DI ID 15) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Corrected to use Dist DIP ID | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-16 |  | N/A | 2023-01-30 | St Clements | 2686 | Madison Layton | Software Provider |  | Comment on Section 9 " Albeit that these transactions can be ‘clubbed together’ and send as a group in single overarching message/API transaction. " Sent on 11th Jan: As DIP does not protect the sequencing of events (FIFO), is there a risk that the ordering of these updates might arrive out of sequence resulting in the wrong end state? If MS space out their updates it would reduce this risk (raised as DI ID 16) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Clairifcation added to Sec 9.2 to reference Time-Stamps rather than 'clubbing' | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-17 |  | DI-017 | 2023-01-30 | St Clements | 2690 | Madison Layton | Software Provider | MAP History availability to Metering Service | Section 9 says "a supporting MAP history commencing in line with the revised Installation Date must also be provided" Will the MS know the full MAP history? Risk they could destroy the data. Potential MAP billing issues? |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Solution agreed at DRG on what MAP updates are required. Various document updates required to align with DRG decision to only maintain latest MAP. Removed section 13 from IF005 user guide plus other corrections to doc. Updated DES138 IF005 validation rules. | Missing/incorrect validation rule | Supporting Docs | Various Documents | IF-005 Use Case guide MHHSP-DES138-Interface Catalogue |  | 14//7
MHHS-DIN-18 |  | N/A | 2023-01-30 | St Clements | 2691 | Madison Layton | Software Provider |  | Comment on Section 9 "• When maintaining the MAP History in cases where there is no change in Meter Installation Date then the MAP history provided should commence either with a MAP Effective From Date matching the existing install date of the meter OR be greater than the most recent, already existing, MAP Effective From Date" Sent on 11th Jan: So it's possible to update ALL MAP history back to installation, or add a new MAP, but it's not possible to amend MAP history only part way back (have to go back to installation date instead every time to do this) (raised as DI ID 18) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • To update BRS003, requirement MHHS-BR-RS-027 to add “Registration Service must lapse any appointments that fail this validation” • Remove Rejected from Step 225 of BP002/BPD002 • Remove Rejected from label on line after step 215 of BP003. | No Change |  |  | None
MHHS-DIN-19 |  | N/A | 2023-01-30 | St Clements | 2692 | Madison Layton | Software Provider |  | Comment on Section 10 "E2E Architecture convention states that all data items are provided in each message even where these data items are not changing or are null" Sent on 11th Jan: Some of the items are optional not mandatory which conflicts with this statement. Not all data items need to be provided (raised as DI ID 19) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Update of E2E Doc to allow for Nullable values. | Data interface correction | Meter to Bank |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-20 |  | N/A | 2023-01-30 | St Clements | 2693 | Madison Layton | Software Provider |  | Comment on Section 13, sent on 11th Jan: What should MPRS do if it holds a MAP not included in the MAPHistory block? (raised as DI ID 20) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Update "all existing history will be replaced by that contained within the message" | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-21 |  | N/A | 2023-01-30 | St Clements | 2699 | Madison Layton | Software Provider |  | Comment on Section 15.2 "It is understood that currently there a numerous instances of duplicated Meter ID’s, some of which may have overlapping installation dates. " Sent on Jan 11th: Meter id is only unique at mpan. Should not be any instances of conflicted MSNs at MPAN. Can you verify with ECOES? Or we can do a RFI to DNOs but will take time (raised as DI ID 21) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | All references to duplicated MSN IDs has been removed from the document | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-22 |  | N/A | 2023-01-30 | St Clements | 2700 | Madison Layton | Software Provider |  | Comment on Seciton 15.3 "add some kind of suffix (X1, X2) to the existing Meter ID." Sent on Jan 11th: This can take the meter ID over the allowable string length (string 10), in this example it would take it to string(12) and so would be rejected (raised as DI ID 22) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | As above, Section 15.3 removed from IF-005 User Guide. | Data interface correction | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-23 |  | N/A | 2023-01-30 | St Clements | 2701 | Madison Layton | Software Provider |  | Comment on Section 16.3 Sent on Jan 11th: Cancelled Flag Set. Only a logical deletion. Still held in MPRS but not visible to EES/MEM The section implies the record would be fully deleted from MPRS, however this is not correct, MPRS would set a cancellation flag that would indicate the record has effectively been cancelled/logically deleted. It would however remain in the systems database (raised as DI ID 23) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Added a statement at the end of the table in 16.3 to say "NB the registration service will only logically delete the MAP entry with a flag, it will not be deleted from the database." | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-24 |  | N/A | 2023-01-30 | St Clements | 2702 | Madison Layton | Software Provider |  | Comment on Section 17.2 "situations where multiple existing meters are identified, the selection process should be extended to include Meter Removal date (if provided) else;" Sent on Jan 11th: Shouldn’t be possible, can run an EES or MPRS RFI to confirm. Noting that MSN is only unique at an MPAN level not a databse level Related to DI-21 (raised as DI ID 24) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. The wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-25 |  | N/A | 2023-01-30 | St Clements | 2706 | Madison Layton | Software Provider |  | Comment on Section 17.2 "where multiple meters still exist even after matching on all three data items should be rejected and require manual intervention (i.e. request to LDSO to intervene) ." Sent on Jan 11th: There's no super user functionality for this so how could the LDSO intervene? The LDSO is not able to manually intervene in regards to MTDs, they can for some other data items such as registration data but not MTDs. (raised as DI ID 25) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Reference to LDSO User Removed - agreed with SCS that scenario should not arise provided existing SCS data rules are met | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-26 |  | N/A | 2023-01-30 | St Clements | 2707 | Madison Layton | Software Provider |  | Comment on Section 17.2 "If the MAP segment is not provided, the existing MAP history should be maintained to greatest degree possible, with ‘trimming’ to align to any revised Install / Remove Dates provided" Sent on Jan 11th: Risk that changing of the Meter Lifespan could result in MAPs being logically deleted. The MS would need to re-apply the MAP history to fit into the new meter Lifespan MS would need to understand this process/constraint (raised as DI ID 26) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Section 17.2 of the guidance document updated. Also added new validation rule REG1014 for MeterHistoryUpdate in IF-005 to ensure MAP is provided when creating a new meter picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-27 |  | N/A | 2023-01-30 | St Clements | 2708 | Madison Layton | Software Provider |  | Comment on Section 19.2 "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the permanent deletion of data, mirroring the existing functionality associated with the use of the D0312." Sent on Jan 11th: Only logically deleted, still visible in the MPRS History. Just not visible to MEM or EES Existing functionality on D0312 utilises cancellation flags not permanent deletion (raised as DI ID 27) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Reword to reflect the logical deletion. See MHHS-DIN-23 Reword this paragraph to: "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the removal of a MAP from a meters MAP history using a logical flag, mirroring the existing functionality associated with the use of the D0312." NB Main section header is incorrect - should be updated to section 19, rather than a duplicate of section 18. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-28 |  | N/A | 2023-01-30 | St Clements | 2709 | Madison Layton | Software Provider |  | Comment on Section 19.4 "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories. However, this would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." Sent on Jan 11th: This functionality already exists with the MPAN History Report showing who changed what when for all MPRS data items. Will be extended to include DIP transactional information (raised as DI ID 28) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Proposed Change Reword this paragraph to: "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories, noting that this is also available via the MPAN history report which will be updated with DIP transactional information and could also be used. Any use of EES would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-29 |  | N/A | 2023-01-30 | St Clements | 2710 | Madison Layton | Software Provider |  | There should be an additional rule for USP, if DI-830/DI-833 is populated, the MS/DS Proposed Effective From Date must equal the currently held EFD for the MS/DS appointment in MPRS (raised as DI 29) |  | Implemented |  |  |  |  | 2023-04-27 | Interim Release 1 | #REF! | 2023-04-27 | Interim Release 1 | #REF! | Added rule for USP scenario in IF-031 to check SP Effective from date. Proposing SCS have flexibility on error codes - requires industry Working Group. Picked up as part of Change of Service Provider review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-30 |  | N/A | 2023-01-30 | St Clements | 2711 | Madison Layton | Software Provider |  | The IF-035 does not provide the opportunity for MPRS to populate a lapsed reason. Will need to be able to provide a reason for a lapsed appointment, otherwise there'll be a higher volume of unecessary supplier enquries to DNOs which will require more resource and cost. (raised as DI 30) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Additional Data Item on IF-035 for a reason comment - what reasons would these be other than gone beyond the date? Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-31 |  | N/A | 2023-01-30 | St Clements | 2712 | Madison Layton | Software Provider |  | MHHS-BR-RS-027 "Registration Service must re-run validation, in line with the validation rules set out in the appropriate interface specification, for all Metering Service appointments that have been confirmed to re-process from the Prospective Appointment Queue, to ensure that the appointment is still valid" It is not clear if MPRS would send MSAppRejected or MSAppLapsed if the appointment fails validation after it's been queued? If this is not made clear in the deisgn then there is a risk that we build to use the wrong event code, or if the code should be MSAppRejected then risk that suppliers build a design where they can't process a MSAppRejected after receiving already an MSAppAccepted from MPRS (raised as DI 31) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • Updated BRS003, requirement MHHS-BR-RS-032 and 66 to show that appointments will be lapsed (not rejected) • Remove Rejected from Step 225 of BP002/BPD002 Also on BP003 leading from step 215 should have the rejected removed. Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Corrections also to BPM002 & BPM003 Forward Migration and BPD002 Froward Migration | Data interface correction | MPAN Ownership |  | MHHSP-BP002-Change of Service - Metering service, BPD002,MHHSP-BRS003-Registration Service requirements MHHSP-DES138-Interface Catalogue, MHHSP-BP003, MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration), MHHS-DEL969-BPD002 (forward migration)
MHHS-DIN-32 |  | N/A | 2023-01-30 | St Clements | 2713 | Madison Layton | Software Provider |  | The interface catalogue lists setting a removal date as an action that can be used with event code meterUpdate on IF-005, however in the interface catalogue, the block B039 does not list meterUpdate as a event code that can utilise this block. Need greater clarity on whether meterUpdate and meterHistoryUpdate should apply meter installations and meter removals or not. (raised as DI 33) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | The definition of a [MeterUpdate] event code is: Allows currently appointed Metering Service to amend the details associated with a currently installed meter. Therefore the appointed Metering Service must be able to remove the meter as part of an update, this is an omission from the design and a small update to IF-005 The design principle that IF-005 works on is that: • BAU transactions (Install/Exchange/Remove) that are in the Metering Services Period of ownership are covered by the Install/Exchange/Remove events • Changes to currently installed metering can be made by the Appointed Metering Service using the Meter Update event. Note this therefore includes, where required, removing the currently installed meter where it is prior to the current period of ownership. • Changes to metering history ( ie not the currently installed meter ) can be made by the Appointed Metering Service using the Meter History Update Proposed changes: Added MeterUpdate as Optional to B039 block in IF-005 and added validation rule to ensure MeterUpdate is not used to remove meters in current period of ownership picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP-DELS229-IF-005 Use Case Guide
MHHS-DIN-33 |  | T4-COM-1759 | 2023-01-30 | St Clements | 2719 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1759 on 15th Sept 2022: IF-005, REG1011 Install date must be > Creation date, should this REG1011 rule apply also to meter Exchange not just meter install SCS raised as a design blocker on 7th October 2022 Still no resolution, should this rule apply to meterHistoryUpdate at least as this allows for meter installations (raised as DI 34) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | An exchange will not be a creation date, and the validation already in place ensures that future installation dates will all follow each other, which means this rule isn't required. ​This shouldn't be needed for exchanges, as its covered by REG1008 (install date >= remove date), as an exchange would replace an existing meter, which at first install would be validated against creation date. Moved REG1011 to cover all scenarios in IF005 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-34 |  | T4-COM-1774 | 2023-01-30 | St Clements | 2720 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1774 on 15th Sept 2022: IF-005, REG1011 "REG1009 - MAP ID [DI_055] is not valid for MAP Effective Date [DI-054] REG1011 - Install Date [DI-057] for MeterID [DI-056] is prior to MPAN Creation Date There are many meters in MPRS that pre-date the existence of the MAP and also MPRS install dates of 1980 etc. these will break a number of rules. should these be cleansed before MHHS start? If they are valid, then the rules need adjusting"l SCS raised as a design blocker on 7th October 2022 Still no resolution (raised as DI 35) |  | Closed | [6 empty] | #REF! |  |  | #REF! | This could be a data cleanse requirement which is a consequential change/transition requirement, but for REG1009 - the MAP effective date should be the point at which the MAP took over the meter, and the exchange date should be after this (ie it should be after the date MHHS goes live). For Reg 1011 currently this is only valid on installs (and installs won't occur on legacy meters). If Reg 1011 is valid on exchanges, then the exchange date should also be after the MPAN creation date - if it isn't then the data should be cleansed. Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-35 |  | N/A | 2023-01-30 | St Clements | 2721 | Madison Layton | Software Provider |  | On the IF-005, should REG1028 (Install date cannot be null or blank) apply to meterinstall, meter exchange and meterupdate too? (raised as DI 36) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Requires amendment to interface validation - look at alternative validation Agree the rule should also apply for those events. Note we believe validation would fail for another reason. Eg REG1019 Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-36 |  | DI-37 | 2023-01-30 | St Clements | 2722 | Madison Layton | Software Provider | Re-alignment of rejection reasons to main block | In the summary of error codes box at the bottom of IF-005 tab the rejection reasons need re-aligning to the main block, e.g. REG1001 should read RMP stats must be Created or Operational, not just Operational As a general note across all interfaces, the rejection codes are referenced in numerous places and the respective descriptions are in many places not consistent for the same rejection code (raised as DI 37) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Will be revisited once SCS provide definative Error Code Texts | No Change
MHHS-DIN-37 |  | N/A | 2023-01-30 | St Clements | 2723 | Madison Layton | Software Provider |  | REG1015 (cannot be removed meter) is listed for meterHistoryUpdate in interface catalogue for IF-005. This should actually apply to meterUpdate not meterHistoryUpdate, REG1018 (cannot be installed meter) applies to metering history update (raised as DI 38) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Change accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-38 |  | N/A | 2023-01-30 | St Clements | 2724 | Madison Layton | Software Provider |  | In the interface catalogue, the IHD block B030 for IF-005 should also be optional for meterUpdate according to the IF-005 guide Section 16 Development Notes "The IHD segment, if provided as part of [MeterUpdate], relating to any currently installed meter should replace/update the IHD details currently held at the MPAN to which that Meter is associated." (raised as DI 39) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Small change to schema operation IHD information may be updated as part of the [MeterUpdate] event. The change is to add [MeterUpdate] event to block B030, so it now reads "B030 - MPAN IHD Information (Optional & may only be used with [MeterInstall],[MeterExchange],[MeterUpdate]) NB this also standardises the use of commas between event codes, rather than using the & symbol. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-39 |  | N/A | 2023-01-30 | St Clements | 2725 | Madison Layton | Software Provider |  | In interface catalogue for IF-005, there needs to be a rule that if event code MeterInstall is used, then modified meter ID cannot be populated (raised as DI 40) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Update agreed | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-40 |  |  | 2023-02-01 | SI Design |  |  |  |  | Not used - raised as duplicate in error |  | Closed | [6 empty] | #REF! |  |  | #REF!
MHHS-DIN-41 |  | N/A | 2023-01-30 | St Clements | 2730 | Madison Layton | Software Provider |  | In interface catalogue IF-005: The REG1003 reads Metering Service [S0.SenderID] holds valid previous appointment then Meter Install Date [DI-57] should be < [REG.App End Date] + 10 The way it's curently written suggests MPRS should accept an IF-005 from the previous appoint, even if their ETD was greater than 10 days ago, provided the install date was less than their ETD + 10. E.g the previous MS could send IF-005 two years later with Install date of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then REG1002/REG1019 should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? (Raised as DI 41) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Having looked through IF-005 Dates should be within the appointment date, and current deign does give the ability to go outside this Change the validation rule for REG1003 on events [MeterExchange], [MeterInstall] and [MeterRemoval] to "If Metering Service [S0.SenderID] holds valid previous appointment then [system date] < [REG.App End Date] + 10" Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. Rule amended after review by SCS, to remove second "if" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-42 |  | N/A | 2023-01-30 | St Clements | 2784 | Madison Layton | Software Provider |  | In interface catalogue IF-005: Meter Update should apply validation REG1027 (current MS or prospective MS) not REG1012 (current MS only) to allow the prospective queued MS to update the Meter Type on a SEG change and therfore complete the market segment change and appointment. MHHS-BR-RS-132 . If the SEG prospective appointment was not allowed to update on meterUpdate event code then they would not be able to update the meter type to completed change of market segment, and would not meet the conditions needed to then be appointed in MPRS, their appointment would then lapse and market segment would remain invalid. (Raised as DI 42) |  | Closed | [6 empty] | #REF! |  |  | #REF! | We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error... | No Change |  |  | None
MHHS-DIN-43 |  | N/A | 2023-01-30 | St Clements | 2732 | Madison Layton | Software Provider |  | In Interface Catalogue, on If-005, REG1002 and REG1019 are duplicates (install/removal dates should be within MS period of ownership). We can only use one of the rejection codes and descriptions, programme should choose which one to keep and remove the other. (Raised as DI 43) |  | Closed | [6 empty] | #REF! |  |  | #REF! | These are testing slightly different things. The first test (REG1002) is checking that the Metering Service is an eligible party to send the request ie currently appointed OR was at the time of the install (to cover for previous Metering Services updating in the 10 day window). The second (REG1019) is checking that the Install Date is in the Metering Services period of ownership. So you could have that the Metering Service is currently appointed, but that they weren't at the install date. Eg Today is 2nd Feb, Meter installed on 27th Jan, Sending MS was appointed on 1st Feb REG1002 would pass as they are eligible as the currently appointed MS REG1019 would fail as they are not appointed at the time of the install Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-44 |  | N/A | 2023-01-30 | St Clements | 2733 | Madison Layton | Software Provider |  | Should the new rule for meter update in IF-005 also apply to meter history update? If no MAP entries provided, and revised Meter Install / Remove Dates result in no valid MAM History then reject with REGE1014 – MAP Eff From Sequence Error (Raised as DI 44) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Added REG1014 ( MAP History ) to IF-005 MeterHistoryUpdate event | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-45 |  | N/A | 2023-01-30 | St Clements | 2736 | Madison Layton | Software Provider |  | New rule for IF-005 Meter Update REG1017 could be misinterpreted as it currently reads incorrectly - need brackets to correct to how the AND and AND/OR conditions are to be applied If [DI-60] is not null AND Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null) Should read If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null)) (Raised as DI 45) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Clarification of existing design rule Change the validation rule for REG1017 to: "If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null))" picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-46 |  | N/A | 2023-01-30 | St Clements | 2737 | Madison Layton | Software Provider |  | on IF-005 for Meter Exchange and meter install the rule for REG1027 has been changed, but I'm not sure the wording implements the rule intended exactly? Currently it reads as The MS must be the currently appoint MS AND the install date must be > MS EFD AND the MS must not have proposed MS app with SEG scenario in the queue. If not then reject with REG1027 - Metering Service is not currently appointed and does not hold a Prospective SEG Appointment SHould the rule actually read The MS must be the current MS OR the MS must have a proposed MS App in the queue with SEG scenario And then the other part of the rule about install date > MS should be a separate rule (with REG1019 error code). (Raised as DI 46) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Sent to Mike F for validation - SI believe wording in current documentation is correct. Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. I would suggest the wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. DIN-46 – On review we agree, the date test should always be true if REG1019 is satisfied ( with minor clarification update ), so validation rules should be updated as below: Proposed changes: REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-47 |  | N/A | 2023-01-30 | St Clements | 2738 | Madison Layton | Software Provider |  | REG1001 on IF-005 does not allow for meters to be removed after a disconnection. Instead should restrict for allow other event codes but allow Status Terminated for MeterRemoval. DES204 CCR-0556 Linked to DI-13 |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Rule update required picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-48 |  | DI-048 | 2023-01-30 | St Clements | 2739 | Madison Layton | Software Provider | CSS failure to apply CoS to related secondary MPANs | Unhappy path scenario:- What happens if, for whatever reason, CSS fails to apply CoS to all the related secondary MPANs MPRS receives IF-031 on primary RMP to change agent, MPRS applies this to all seocndary MPANs too But if the CoS was not received from CSS for secondary MPANs that the secondary MPANs would still currently be held for the wrong supplier Would this cause any issues downstream? (Raised as DI 48) |  | Closed | No |  | Design gap | SCS |  |  | #REF! |  |  | #REF! | Change Request to be raised against this | Other | MPAN Ownership | Related MPANs |  |  | 2023-07-14
MHHS-DIN-49 |  | N/A | 2023-01-30 | St Clements | 2740 | Madison Layton | Software Provider |  | Unhappy path scenario:- If MPRS sends a IF-033 but never receives back a IF-034 then the rest of the process will not continue. The Supplier will never receive the IF-035 they are waiting for and the SP would never get appointed by MPRS. Is there a process in place to detect/resolve this scenario? (Raised as DI 49) |  | Closed | [6 empty] | #REF! |  |  | #REF! | There is a requirement for the Supplier to monitor for any delayed responses and request an update if not received in expected timescales. Reviewed with SCS and agreed ticket can be closed | No Change |  |  | None
MHHS-DIN-50 |  | N/A | 2023-01-30 | St Clements | 2741 | Madison Layton | Software Provider |  | We need clear rules to define what a valid Consent granularity looks like. Current rules don’t mention any validation around EDI. (Raised as DI 50) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-51 |  | DI-51 | 2023-01-30 | St Clements | 2747 | Madison Layton | Software Provider | St Clements Design Query - DI 51 | We have had some feedback from DNOs asking about how systems will recover from System Misalignment because of data errors or significant downtime? We have the D0204 (Supplier) and D0209 (Data Aggregator) Refresh functions today which are not being replaced with a DIP message equivalent. I am aware of the DIP Replay function, but this wouldn’t be of any help if there were data errors, as the DIP would just be replaying the incorrect data. The Source system would need to re-send the corrected data in an agreed format. I know there is a design principle to move away from bulk loads and refreshes of data, Faster Switching took a similar approach. However today, CSS leans heavily on the MPRS Refresh function to get itself back inline and there are REC CP’s being raised to add a Refresh function to CSS for all parties (first CP being R0067). DNO’s are keen to understand the MHHS Programme’s position on and if Refresh functionality should be built into MPRS for MHHS. |  | Closed | No |  | Design gap | DNO (SCS), EES (RECCo), DIP |  |  | #REF! |  |  | #REF! | Change Request will be raised against this DIN. Refresh Functionality was rejected by the Working Groups so not in current design. Internal Design Discussion Required on if Programme position has changed on this given CSS Issue / EES Fed via DIP ?? Details provided by the Design Team to SCS and RECCo on the workings of the refresh functionality and get agreement on next steps. | Other | Supporting Docs | Refresh Process? |  |  | 2023-07-14
MHHS-DIN-52 |  | DI-52 | 2023-01-30 | St Clements | 2748 | Madison Layton | Software Provider |  | For IF-005, REG-1006 and REG1013, would it make sense to include the installation date of the MPAN already in the system in the rejection description too to help MS with triage? |  | Closed | [6 empty] | #REF! |  |  | #REF! | DIN closed as instructed by St Clements. Old comments: Discussed with SCS potential for them to have flexibility on error messages. Industry agreement required. Participant Discussion Required | No Change
MHHS-DIN-53 |  | N/A | 2023-01-30 | St Clements | 2749 | Madison Layton | Software Provider |  | Requirement on LDSO requirements spreadsheet: MHHS-BR-LD-035 LDSO Maintain DUoS Tariff ID LDSO must set Duos Tariff ID on MPAN creation and maintain DUoS Tariff ID's in line with their Charging Method Statement. This should include updating the Duos Tariff ID, as required, following any updates to Domestic Premise Indicator, Connection Type and Energy Direction Note for MHHS, LLFC ID is being renamed as DUoS Tariff ID to make it clearer what this data item is used for. "BP010B Change of registration data" 250 However missing the respective requirement for Registration Services in the Registration Services Requirements spreadsheet |  | Closed | [6 empty] | #REF! |  |  | #REF! | Looked through the Registration Services Requirements spreadsheet v4.6 and it looks like DUoS Tariff ID is there - MHHS-BR-RS-091.1, MHHS-BR-RS-121 and MHHS-BR-RS-122 | No Change |  |  | None
MHHS-DIN-54 |  | N/A | 2023-01-30 | St Clements | 2750 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1699 on 15th Sept 2022: On the IF-031 and IF-035 there are a number of "Proposed" Data items. Should MPRS load these and updated the stored data items. Or are these data items only for passing through to Supplier and Service? SCS raised as a design blocker on 7th October 2022 We have some clarity verbally on this but nothing has been formally documented in the design artefacts. This needs to be reflected somewhere in the requirements. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Added "Appoinments - Data" section in REG Notes to highlight what data becomes effective with the appointment. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-55 |  | T4-COM-1738 | 2023-01-30 | St Clements | 2751 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1738 on 15th Sept 2022: the DB02 flow updates multiple data items on the IF-018 in one event. Can multiple EventCode be included in one IF-018 or will MPRS need to generate an individual IF-018 for each EventCode? SCS received a blank response and raised as a design blocker on 7th October 2022 |  | Closed | [6 empty] | #REF! |  |  | #REF! | Original response was that clarification was to be provided on 24th Oct - is this available? Which document? One at a time | No Change |  |  | None
MHHS-DIN-56 |  | T4-COM-1742 | 2023-01-30 | St Clements | 2752 | Madison Layton | Software Provider | Manual Correction to MHHS data items | Originally raised as T4-COM-1742 on 15th Sept 2022: BSCP604 currently allows LDSO and Suppliers to request manual corrections to Data Items held in MPRS. Will this type of Manual Correction be allowed in MHHS, if yes then this should be added to the business process to capture manual amendments and how these changes are reflected back to DIP users (IF-018 & IF-026, or a new Refresh Message?) SCS received a blank response and raised as a design blocker on 7th October 2022 Another example of this: If the MS/DS history is incorrect and cannot be amended via BAU, would the DNO be able to correct this via an exceptional error handling process? |  | Closed | No |  | Design misaligned | LDSO, Supplier and SCS | [6 empty] | Covered in the retrospective changes discussion at DRG. | Requirement correction | MPAN Ownership | CSS Defects | MHHS-BPD005 Data Processing, MHHS-BRS005 LDSO overview |  | 2023-07-14
MHHS-DIN-57 |  | T4-COM-1748 | 2023-01-30 | St Clements | 2756 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1748 on 15th Sept 2022: "Additional information field DI-120 is String200, where the existing DB03 allows a free text field of 2000 characters" SCS raised as a design blocker on 7th October 2022 This was corrected but then in v4.5 artefacts released there was a change back for DI-120 addition information field from string 2000 to string 200 in the interface catalogue data catalogue tab reintroducing the issue. For disconnection additional notes MPRS database holds 2000 characters so this field will need to be string 2000 in the IF interfaces (Raised as DI 57) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Change to the data catalogue included in the 4.7 baseline | No Change |  |  | None
MHHS-DIN-58 |  | T4-COM-1789 | 2023-01-30 | St Clements | 2757 | Madison Layton | Software Provider | Valid combinations of ISD data for MPRS validation development | Originally raised as T4-COM-1789 on 15th Sept 2022: "Valid combinations of data in ISD are critical to the MPRS validation development, we must have these defined and agreed before we can start development" SCS raised as a design blocker on 7th October 2022 |  | Closed | [10 empty] | Elexon has defined the valid combinations of ISD data and these files are available on this link https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/ISD.aspx | No Change |  |  |  |  | 2023-07-14
MHHS-DIN-59 |  | T4-COM-1707 | 2023-01-30 | St Clements | 2758 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1707 on 15th Sept 2022: "The Smart DS for Export and Secondary MPANs can be different to the Import/Primary DS as the Customer can choose their own DS for Export and Primary (Smart only)" The IF-031 validation rules have been amended but they are still not corrrectly reflecting the rule. The heading above both rules REG1038 and REG1039 reads: "If event type = [MSApp] OR event type [DSApp] & MPAN Segment is not 'Smart'" This heading should ONLY apply to REG1038 for linked MPANs and should not apply to REG1039 concerning related MPANs It should also have brackets to clarify the logic otherwise it could be misinterpreted e.g. "If event type = [MSApp] OR (event type [DSApp] & MPAN Segment is not 'Smart')" |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | This seems a valid issue. REG 1039 on linked meters should be allowed for trad meters (eg economy 7) Proposed Change: The logic issue here is that REG1039 caters for related meters, which are applicable to trad as well as smart meters. Remove REG1039 from this validation Change the validation to: "If (event type = [MSApp] OR event type [DSApp]) & MPAN Segment is not 'Smart'" Updated heading above REG1038 and added heading above REG1039 to clarify the validation rule in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-60 |  | T4-COM-1708 | 2023-01-30 | St Clements | 2759 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1708 on 15th Sept 2022: "The Service Appointment Date must be equal to the SSD or there will be a period with no Service" And T4-COM-1776 also on 15th September 2022 "REG1032 - Metering Service Eff From Date [DI-830] is not contiguous - Appointment must be from [Max[Reg.MPAN_SSD] ,[Reg.ExistingMSAppFrmDate]] for a COS, it can only equal the SSD otherwise there will be a gap" This has been applied incorrectly. In IF031 rules REG1032 now reads that the MS/DS prop EFD must be = Max(SSD, existing MS/DS EFD + 1) This would restrict the MS/DS to setting the new EFD to either SSD or the day after the last MS/DS appointment, and all other dates would be rejected. It should read >= not just =. All four refrences to REG1032 in the validation rules for IF-031 references the +1 day after EFD, but the rejection description in the right hand columns for 'scneario not SEG or CoS' section does not reference this + 1. This should be corrected to be consistent with the other rules. (Raised as DI 60) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Original response to 1708: New rules added to cover all scenarios Original response to 1776: Change to be incorporated into design artefact Updated REG 1032 validation in IF-031, original single rule, split into 2 separate rules picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-61 |  | T4-COM-1445 | 2023-01-30 | St Clements | 2760 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1445 on 15th Sept 2022: "There is no mechanism to update the Profile Class. We would assume that this would be updated by the Supplier (with business rules restricting when this should be set) and confirmed on the IF-026. Please can you confirm if this is the intention or if it will be updated through another route. If so, the EES would need to know which PUB would confirm the data item had been updated. " Whilst this is now included in the design the validation rules from D0205 have not been carried over, e.g. PC/SSC need to be a valid combination. ISD will need to contain the valid PC/SSC Combinations (previously MDD Entity 11) and the validation rules in the interface catalogue will need to reference this validation against the ISD valid combinations. (Raised as DI 61) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | See also DIN-58, need to find out who is defining ISD validation Updated Interface notes in IF-025 to confirm that there is no Profile Class/ SSC combination checks | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-62 |  | DI-062 | 2023-01-30 | St Clements | 2761 | Madison Layton | Software Provider |  | In the business process diagram for Registration Updates MHHSP-BP010-Change of Registation Data - v4.5, the MPL update section, the C0300 has been changed to C0400 which is incorrect, C0400 is for MAP updates. Address updates are actually sent in the C0600. (Raised as DI 62) Change raised 30 March:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Also in the BPD. MHHS-BR-RS-114 also confirms this should be C0300, this appears to be a straightforward typo. Amend label between Step 20 and Step 30 on BP010A to CSS0300, and update the corresponding BPD description on step 30 Update required:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly in BP010A, BPD010 and in MHHS-BR-RS-114. | Process model correction | Metering Changes | MPAN Updates | MHHSP-BP010-Change of Registration Data MHHSP-BPD010 MHHSP-BRS003
MHHS-DIN-63 |  | DI-063 | 2023-01-30 | St Clements | 2792 | Madison Layton | Software Provider |  | In the business process diag for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 (Raised as DI 63) |  | Closed | [6 empty] | #REF! |  |  | #REF! | SCS have now confirmed that C0700 is the correct reference - no need to change documentation - agreed to close | No Change | MPAN Ownership | Disconnection | MHHSP-BP007-Disconnection MHHSP-BPD007
MHHS-DIN-64 |  | N/A | 2023-01-30 | St Clements | 2793 | Madison Layton | Software Provider |  | In business process diag for change of data service MHHSP-BP003-Change of Service- Data Service-v4.5 and MHHSP-BP002-Change of Service- Metering Service v3.5, this still makes reference to D0386 in the purple note boxes. This should now have changed to IF-019 (Raised as DI 64) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Update notes on BP002 and BP003 from D0386 to IF-019, and for BPM002 & BPM003 (forward migration) | Process model correction | MPAN Ownership | Change of DS | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-65 |  | N/A | 2023-01-30 | St Clements | 2794 | Madison Layton | Software Provider |  | The business process diagram for change to connection type/market segment has been amended to name only DB01, connection type is set on DB01 but it can then be changed on DB02 (Raised as DI 65) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Update label between step 220 and 225 from "DB-001" to "DB02" | Process model correction | Metering Changes | Market Segement | MHHSP-BP011-Change of Connection Type or Mkt Segment
MHHS-DIN-66 |  | N/A | 2023-01-30 | St Clements | 2795 | Madison Layton | Software Provider |  | In interface catalogue, on IF-031, shouldn't rule REG1036 (MDR app EFD must be after DS app EFD), be applicable to all scenarios including SEG? Currently under section for if not SEG (Raised as DI 66) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated validation rule for REG1036 and made applicable to all scenario's in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-67 |  | N/A | 2023-01-30 | St Clements | 2796 | Madison Layton | Software Provider |  | Currently no rule on IF-031 that the SP appointment has to be within the prospective suppliers registration period - just that it can't be past dated. This rule will need to be added. (Raised as DI 67) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Reviewed with SCS and agreed that this validation is covered by existing rules. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-68 |  | N/A | 2023-01-30 | St Clements | 2797 | Madison Layton | Software Provider |  | If-031 business rule missing If the Scenario is USP, the consent granularity must be the same as the existing consent granularity held within MPRS (Updates should be through IF-025 not through IF-031) (Raised as DI 68) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Updated Interface notes in IF-031 to clarify that Registration Service will ignore any differences in Domestic Premise Indicator/ Consent Granularity sent on IF-031 (USP scenario) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-69 |  | N/A | 2023-02-02 | ESG Global | 2653 | Luke Speakes | Software Provider |  | PUB-033 - Block 029 is conditionally mandatory for DCC Commissioned Meters, but includes DI-025 DCC Service Flag with valid values of A-Active, I-Installed Not Commissioned, N - Non Active. The title of the block, which should define whether it is mandatory or not, is not appropriate if a DCC meter has been installed and not commissioned, or is inactive. Propose following SI and SRO design discussion that title of block 029 is revised to conditionally mandatory for 'DCC Smart Meters' |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Concludes this can be resolved by a minor wording change to the block title | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-70 |  | N/A | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory | Addition of MDR validation rule | Elexon is required to maintain a valid list of Meter Data Retrievers in Industry Standing Data, to allow RegService to validate they're suitably qualified (DCC and SEC) MDRs are being appointed. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Design Agreement is to utilise M16 for this purpose. ISD document updated with details and examples to this effect. | Other | Supporting Docs | ISD | MHHS-EDI-021-ISD_Entities |  | 2023-07-14
MHHS-DIN-71 |  | N/A | 2023-01-30 | St Clements | 2839 | Madison Layton | Software Provider |  | When would event code [MSDeAppUpdate] and [DSDeAppUpdate] be used for on an IF-037? (Raised as DI 69) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Reviewed with SCS and it is used to notify the incoming Service Providers when de-appointing and not origanally known. In case of Linked/Related MPANs individual MPANs move through the process. RS need to apply the logic for sending the updated IF-037 to all MPANs. Agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-72 |  | N/A | 2023-01-30 | St Clements | 2840 | Madison Layton | Software Provider |  | Block B018 on IF-034 and IF-035 should not be mandatory - it will only be provided for smart meters. This needs to be set to mandatory for SDS-MDRUpdate only, optional for DSAppSPResponse (Raised as DI 70) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated B018 block to be optional for non Smart on IF-034 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-73 |  | N/A | 2023-01-30 | St Clements | 2841 | Madison Layton | Software Provider |  | IF-026/IF-025, added new event code [SSCandProfileClass], but still kept in original [SSC] and [ProfileClass] event codes, should the original two have been removed? Particularly as the B032 group says it's madatory where event code is [SSCandProfileClass] and does not refer to [SSC] or [ProfileClass] individual event codes (Raised as DI 71) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-74 |  | N/A | 2023-01-30 | St Clements | 2842 | Madison Layton | Software Provider |  | A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a new MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60 (Raised as DI 72) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | This appears to be the reciprical change to MHHS-DIN-60 for the response interface Update description to "Check if MDR Eff Date = SSD OR on or after existing MDR Eff From + 1" Update rule to "If [DI-841] <>SSD OR <MDR Eff Date + 1" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-75 |  | N/A | 2023-01-30 | St Clements | 2843 | Madison Layton | Software Provider |  | On IF-035, overidden the description for Data Item 836 incorrectly with the description for Data Item 838 (Raised as DI 73) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Update the definition field based on the description in the data catalogue for DI-836 on IF-035 (Date From which Supplier would like Nominated MDR to take effect) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-76 |  | N/A | 2023-01-30 | St Clements | 2844 | Madison Layton | Software Provider |  | Data catalogue - changed the estimation reason code authoritative source to Registration Service, this data item is not received by, sent by or held by registration services and so the authoritative sourse cannot be Registration Service (Raised as DI 74) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | The authoriative source has changed between v4.0 (from Data Service) to 4.7 (Registration Service) - have asked why the change was made, and what the authoritative source should actually be. Source updated to SDS/MDS | Data interface correction | Meter to Bank | Estimation | MHHSP-DES138-Interface Catalogue
MHHS-DIN-77 |  | N/A | 2023-01-30 | St Clements | 2845 | Madison Layton | Software Provider |  | Data catalogue - Added issue 99 items (CT Ratio, Phases etc) DI-170 - DI-180. Was agreed in work off meeting these items are not within the scope of MHHS, to introduce these would require a CR (Raised as DI 75) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | these data items don't appear to be used in any interfaces so this could be a relatively simple change to remove 11 items from the data catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-78 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E0404 requirement is blank - row needs to be deleted |  | Closed | [6 empty] | #REF! |  |  | #REF! | This update was already incorporated into version 5.0 closing it here | No Change | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-79 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E21114 typo - should be VAS Output Retention |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | change as per description | Technical corrrection | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-80 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHSP-DES138-Interface Catalogue v4.6 - DI-846 Issuing Data Service EZ Name should be scored through in IF/ PUB21 definition |  | Closed | [6 empty] | #REF! |  |  | #REF! | Completed in V5.0, part can review change as part of Interim Release 2 | No Change | Meter to Bank | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-81 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier | Correction of step in BP020 | MHHSP - BP020 - Volume Allocation Service (ECS) v4.6 - Step 75 to Step 80 references report “REP-00” - needs correcting |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | BP020 step 75 to step 80 process flow REP list correction BPD020 step 75 & step 80 detail list of REP's correction | Process Model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions |  | 2023-06-16
MHHS-DIN-82 |  | N/A | 2023-02-09 | SI Design | 2716 | Rob Short | SI Design | Missing listed number of reports in BPD002 | Related to DIN-81 - BPD002 lists number of reports at step 75, BP002 does not reflect this list, missing PO275, PO214 and PO213 |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | This relates to BP020 (not BP002), similar to DIN81, reconcile REP list correction on BP020 at step 75 and 80 and reconcile with BPD020 list of REPs | Process model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions |  | 2023-06-16
MHHS-DIN-83 |  | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | BP011 missing PUB-044 flow | A discrepancy with the Interface Catalogue - IF_LIST states MHHSP-IF-044 is sent to Central Settlements, DS, MS, Supplier, LDSO. IF-044 tab states it is sent to Supplier, MDS, LDSO In BP011 the PUB-044 is not sent to DS only Supplier, Settlements and EES |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Add Manage change of segment in LDSO lane on business process BP011C with a PUB-044 flow from step 570 Add new step to BPD011 Interface catalogue is already updated | Process Model correction | Metering Changes | Interface Catalogue | MHHSP-BP011 Change of ConType andor Mkt Segment MHHSP-BPD011 MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-84 |  | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | DES-138 IF List Tab Consistency | IF_LIST states MHHSP-IF-020 is sent to Supplier onlyIF-020 states it is sent to Supplier, Data Service, Metering Service, LDSOIn BP010, the PUB-020 is sent to Central Settlements, CSS, EES, Supplier, Data Service, Metering Service, LDSO.This one looks like its just the Interface Catalogue that needs updating. IF-020 Updated to refect new agreed Routing |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated parties receiving PUB-020 in the IF_LIST, updated PUB-020 routing to include MDS for Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-85 |  |  | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory |  | Elexon see DIP qualification for new users being part of market entry post-programme, but want to understand how MHHSP will operate qualification during the programme. This is likely to cover the majority of participants. Discussions with SRO colleagues indicate they are assuming this is a process for the Enduring Service Operator to define. Challenge applies to non-BSC DIP participants (e.g. adaptor providers), and considerations under Issue Group 101. SI design has spoken to at least 4 participants who are operating in this space and seeking to understand how they can engage with SIT and other programme activities as a DIP connection provider (E2E Architecture - 3.3.2) |  | Closed | [6 empty] | #REF! |  |  | #REF! | To be handled as part of the Placing Reliance document | No Change | Qualification | Qualification | New Process - DIP Qualification for New Users
MHHS-DIN-86 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Invalid Market Segment BP011C requires SMRS to notify the Supplier of an invalid market segment. RegService requirement RS0124 states that SMRS must derive a value for Market Segment based on Connection Type and Meter Type following a Change of Metering, Change of Connection Type (Change of Unmetered Indicator) or Change of Related MPAN relationships. Given that SMRS determines segment as above, when would an invalid market segment occur, giving rise to the processes from step 560 in BP011C? Further, upon receipt of a PUB-045 Market Segment Invalid Advisory Notification, what are the next steps for a Supplier to address the issue? There are no provisions in the IF-025 for Suppliers to update Market Segment. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Part of ongoing discussions with Code Drafting team 20/4//23 Code Drafting believe an update needs to be made to the design to update Market Segment via IF-25. This could occur when a Supplier is trying to arrange a change of segment but one of the activities has not completed on time eg the new metering has not been notified. When Registration Service tries to evaluate the segment it may not be compatible. Notification would then go to Supplier to prompt them to chase the required update, in this example chasing the Metering Service to provide the new metering details. Another example is if the LDSO has not notified a change of connection type. The Supplier may also need to send a further SEG appointment if the original has lapsed. | No Change | Metering Changes | Change of Connection Type and/or Market Segment | MHHSP-BP011, MHHSP-BPD011
MHHS-DIN-87 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory | Process clarification for meter removal and de-energisation on same job | Energisation Process Clarification BP009 states that change of energisation status at the same time as meter works means that BP008 will be followed - what is the process when a meter removal and de-energisation are carried out in the same job? Are both D0139 (de-energise) and D0142 (remove meter) and relevant DIP interfaces required. At the moment MEMs only have to send flows relating to meter removal |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | New Purple Boxes added in BP009 and BP008 to make it clear that Remove/DeEn could still be requested and carried out but MS would need to send two interfaces. Also that DeEn did not need to be notified if meter works completed within same day (ie same rules as today) | Process model correction | Metering Changes | Change of Metering | MHHSP-BP009 MHHSP-BP008 |  | 2023-07-14
MHHS-DIN-88 |  |  | 2023-02-09 | RECCo |  | Sarah Jones | Regulatory | Update to Incumbent MS provider for Lapsed Appointments | Update to Incumbent MS provider for Lapsed Appointments Currently BP002 only addresses the positive confirmation of de-appointment from RegService (PUB-037 - step 140/231), but if there is no secured active, there is no subsequent notification to the incumbent. The prospective MS receives a PUB-035 at step 225. How should the incumbent MS determine when the de-appointment has lapsed? |  | Closed | [10 empty] | Part of ongoing discussions with Code Drafting team. It is not expected that the incumbant share the MTD via the IF-035 as early sight. IF-37 is the deappoint code they need to reflect . The Metering Service is appointed until they get de-appointed using a PUB-037. They are only receiving the PUB-035 as notification of who to send MTDs to, it is not intended as a notification of de-appointment. Incumbent Metering Service is a term used to refer to the MS appointed at the point another new SP Appointment is accepted (MS or DS), it shall be the Incumbent Metering Service's responsibility to share MTDs (ADV/Trad) to the incoming party. No change recommend CLOSE | [5 empty] | 2023-07-14
MHHS-DIN-89 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Customer Details on De-Appointment The MHHS design currently allows for customer data to be deleted or obfuscated by MS on de-appointment. Has obfuscation been confirmed as acceptable under GDPR? |  | Closed | [6 empty] | #REF! |  |  | #REF! | Programme has called out the need for data management wrt GDPR. It is for each participant to determine the action required based on their own GDPR Guidelines and policies. |  | All Areas |  |  |  | 2023-07-14
MHHS-DIN-90 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | MS Appointment for Associated Export Metering Points How will an initial MEM be appointed for a new export MPAN, created post MHHS go live? |  | Closed | [6 empty] | #REF! |  |  | #REF! | Part of ongoing discussions with Code Drafting team - this is not a Design Issue. Design will operate as described below: The daily process monitoring (BP011C) would pick up any [new] Linked Export MPANs and ensure that the same Metering Service is appointed as the Import MPAN. If the Export MPAN is not linked, then the BAU appointment process can be followed. |  | Metering Changes | Change of Connection Type / Market Segment | MHHSP-BP011, MHHSP-BPD011 |  | 2023-07-14
MHHS-DIN-91 |  | N/A | 2023-02-10 | AWS | 2858 | Duncan Parsons | Software Provider |  | Document MHHS-E2E001 section 3.6 Actor Workflows Summary - Typo in the MSA Outbound. States IF-04, this should be IF-041 |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Reference Corrected | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-92 |  |  | 2023-02-14 | RECCo | 2903, 2805, 2911 | Sarah Jones | Regulatory |  | Customer Direct Contract Flag (D053) Multiple tickets - RECCo, ESG and National Grid - all highlighting the same problem. The 4.7 artefacts do not consistently reflect the agreed position that the Customer Direct Contract flag can only be set by the incumbent Metering Service provider. The validation rules on the IF-038 should be updated The requirements for MS (013) and DS (34) in the respective BRS artefacts should be aligned |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Added validation rule REG1075 to IF-038 in the interface catalogue Updated requirements in MS-013 and DS-034 in BRS to reflect the agreed position for D053 1/3 - ticket #3035 - SCS supportive of this change, need more detail. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue, BRS001, BRS002
MHHS-DIN-93 |  | N/A | 2023-02-14 | Power Data Associates |  | Tom | Data Service Provider | Work off Plan D-034D updates for exceptions to Unmetered Supplies | Work off Plan D-034D updates for exceptions to Unmetered Supplies |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | 1. Section 2.3 of MHHSP-METH004-UMSDS- EM Functions will be updated to make explicit that the following data items are not required by the UMSDS and as such will be ignored. • Consent Granularity (T4-COM-1857) • Domestic/Non-domestic Indicator (T4-COM-1830/1850) • Distributer Id (T4-COM-1826/1842/1845/1858/1859/1864/1865/1871/1875) • DUoS (T4-COM-1856) • LLF Data (T4-COM-1856) • Domestic Premise Indicator (T4-COM-1830/1850) • Metered Indicator- (D-045) 2. MHHSP-METH001- SDS Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 3. MHHSP-METH002- ADS- Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 4. MHHSP-METH009- UMSO Method Statement should be updated to make explicit that the following data items are not required by the UMSO and should be ignored (list to be reviewed and validated). • Consent Granularity • Domestic/Non-domestic Indicator • Distributor Id • DUoS • LLF Data • Domestic Premise Indicator • Metered Indicator | Method statement correction | Supporting Docs |  | MHHSP-METH004-UMSDS MHHSP-METH001- SDS MHHSP-METH002- ADS MHHSP-METH009 - UMSO |  | 2023-06-16
MHHS-DIN-94 |  |  | 2023-02-16 | ESG | 2777 | Patricia | Software Provider | IF-005 rejections | The IF_009 has 2 event codes: [MPANDisconnection] & [CSSDeRegistration]. [CSSDeRegistration] is listed as having Supplier as Secondary routing however on BP007 there is only reference to the supplier receiving the [MPANDisconnection] flavour of the flow. Please can you clarify which artefact is accurate. MHHSP – BPD009 step 145 states Where the Registration Service has rejected the metering update the DIP will publish the rejection to metering services. Supplier have the option to subscribe to this also. Your response was:- Our reading of this is that regservice will reject the PUB-006 back to sender if the IF-005 fails those rules. So just back to sender, not always meter service or supplier Therefore, does the BPD009 step 145 need to be updated to reflect that as the IF005 can only be generated by Metering Service Smart (MSS) & Metering Service Advanced (MSA) not the Supplier |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Question 1. Supplier will receive both events as outlined in BP007 (See DIN 294) Question 2. A decision was made at the DRG on 29th June to leave the messaging in BPD009 step 145 and instead update the business process model in BPD009 to give Supplier's the option to subscribe to rejections. | Process Model correction | Metering Changes | Change of Metering | MHHSP-BP009 – Change of Metering (Install / Remove / Exchange) , MHHSP-BPD009 MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-95 |  |  | 2023-02-20 | SI Design | NA | Simon Harrison | Programme |  | Typo in the Note box about Auto Alignment of Related/Linked MPANs on the BP002 and BP003 process maps. Change 'Regisatration' to 'Registration' |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Update BP002 (& BP003) call out box, also for BPM002 and BPM003 (Forward Migration) | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-96 |  |  | 2023-02-21 | SI Design | 2973 | Arif Jagot | Programme |  | Test-078 - SUPPI -Primary - Means SUPI? |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Update Interface Catalogue | Data interface correction | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-97 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.4 | Typo in MHHS-METH001-5.4c "and less than 90 days months different from the UTC Date" - propose removal of months |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Update Method Statement i.e This needs to be 90 days not 90 months the artefact needs to be updated | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  | 2023-06-16
MHHS-DIN-98 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.5 | Typo in MHHS-METH001 - 5.5 SDS shall use the most recent data a based on the event that triggered the |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Typo error on clause 5.5 within MHHSP-METH001-SDS Validation Estimation v5.0 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  | 2023-06-16
MHHS-DIN-99 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Working days correction | Clarify that Step 105 in the CoS Transfer read process is Working Days. Currently states 5 days |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Checked with SRO - 5 Working days for Step 105 in process, BPD003C, BR-DS-024.1 and BR-DS-024.2 | Requirement correction | MPAN Ownership | Data Services | MHHSP-BRS001 - SDS Requirements MHHSP-BP003C - Transfer of Reads MHHSP-BPD003C - Transfer of Reads |  | 2023-06-16
MHHS-DIN-100 |  |  | 2023-02-21 | RECCo | NA | Sarah Jones | Regulatory | BP002 to include LDSO as recipient | Step 180 in BP002 and BPD002 does not include LDSO as recipient of traditional meter details as per the wording of the step or the BRS (BR-MS-024) (Code Drafting Log Reference CDD-29) |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Update BP & BPD to align with BRS and add LDSO as recipient of MTDs Updates to BP & BPD002 Forward migration for consistency | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Metering Service MHHSP-BPD002 Forward Migration BP002 and BPD002 |  | 2023-06-16
MHHS-DIN-101 |  | DI-120 | 2023-02-22 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. (Raised as DI 120) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Included within CSS validation rule update. DUPLICATE See DIN-172 | No Change | MPAN Ownership |  | MHHS-DES138-Interface Catalogue
MHHS-DIN-102 |  |  | 2023-02-22 | St Clements | 2886 | Madison Layton | Software Provider |  | SCS raised the following under MHHS-DIN-7 "MPRS will reject any PUB-031 inlcuding those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist"" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8)" They have followed up with: Just found the change that corresponds to this one in v4.7 interface catalogue – REG0005 in IF-031. Could this also be added to IF-034 so that we can apply the same validation on MDR updates? |  | Closed | [6 empty] | #REF! |  |  | #REF! | Proposed Change: Add validation "CSS Registration Request ID [DI-849] is valid for Registration Service", with error REG0005 - "CSS Registration Request ID [DI-849] is invalid or unknown" This mirrors a change made in v4.7 to IF-031, agreed as part of the DAG baseline of v4.7 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-103 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory |  | Confirm that D0381 will continue to be used for updates to MPL address. BP010 & BPD010 currently allow emails, SDEP and other agreed forms can be used by Supplier or UMSO to update this - propose that these artefacts are amended to reflect that the D0381 is to be retained (Code Drafting Log Reference CDD-22) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Amend Steps 10, 21, 22 to explicitly use the D0381 rather than current wording | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-104 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Impact of MHHS on SoLR arrangements | Impact of MHHS on SoLR arrangements - possibly needs an Issue Resolution Group discussion to undertake evaluation & impact assessment (Code Drafting Log Reference CDD-23) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Extensive discussions have been held with Elexon (DIP Manager) to ensure that there is flexibility within the DIP Design to accomdate varied SoLR scenarios. These involve the existing process(s) around change of BMUnits and the ability to transfer ownership of DIP Market Participants. As the solr process does not involve any mass movement / reassignment of MP Identifiers at the MPAN level the core MHHS design is not impacted by Solr per se. |  | All Areas |  |  |  | 2023-07-14
MHHS-DIN-105 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Related MPAN Business Rules | 1) IF-019 suggests RMP status can be Created or Operational - proposed this can only be Operational for subsidiary MPAN 2) Add validation rule to IF-019 requiring related MPANs to have consistent classification as domestic or non-domestic (reflecting the existing requirements) 3) Clarify what Registration Services should do when MPANs are related/linked and have different MS/MEM providers - is the IF-019 rejected or the MEM for the secondary MEM auto-deappointed? 4) What happens if the IF-019 fails validation by Reg Service at Step 330 in BP010? Design provides no guidance |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | 1. Removed reference to Created in the REG1001 validation rule for IF-019 2. We understand there is no existing validation within MPRS and this is not being amended as a result of MHHS implementation. This would require a wider industry change impacting CSS as Domestic Premise Indicator is managed independently of Related MPANs. 3. It would not be rejected, auto-alignment would pick up the discrepancy at the next daily run and de-appoint the export MS and appoint the import MS. 4. As with other rejected flows, the sending party should investigate the error and re-submit as appropriate. | Data interface correction | MPAN Ownership | Change of Registration Data | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-106 |  |  | 2023-02-23 | SI Design | 2955 | Kate Goodman | Testing | IF Routing | Inconsistency in DES138 for UMSO Routing 00-Introduction logs UMSO as the single routing option for Unmetered Service provision, as there can only be one UMSO related to an MPAN PUB-008 provides UMSC, UMSP and UMSI as options for secondary routing This inconsitency needs to be corrected |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | IF-008 - Secondary routing rules updated following review with Avanade (see DIN268) |  | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-107 |  |  | 2023-02-24 | SI Design |  | Simon Harrison | Progamme | Update to definition of DI-301 LLF ID in the ESC Reporting Data Catalogue | Definition of DI-301 in the ECS Reporting Data Catalogue needs to be updated as follows 'The Unique Identifier of a set of Line Loss Factors' |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Update to be made in the ECS Internal & External Reports - Data Catalogue tab against DI-301 LLF ID it should read as 'The Unique Identifier of a set of Line Loss Factors' | Data interface correction | Supporting Docs | Reporting Catalogue | MHHSP - ERI011A - ECS Reports - Internal v5.2 MHHSP - ERI011B - ECS Reports - Enternal |  | 2023-07-14
MHHS-DIN-108 |  |  | 2023-02-27 | SI Design | 2966 | Kate Goodman | Testing | IF Routing | Ref:MHHSP-DES138-Interface Catalogue v4.7, IF-038, PUB-020, PUB-039. Document says that UM is relevant to these messages but UM thinks it is not relevant. Please clarify what the situation is. Raised in review of MHHSP-872 by Power Data. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Covered by Secondary routing updates (See DIN268), changes to IF-020 and IF-039 routing. No changes were required to IF-038. The design allows for Customer Direct flags to be set for any Data Service/ Metering Service (ie Including unmetered). |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-109 |  |  | 2023-02-27 | SI Design |  | Simon Harrison | Programme |  | Call out box in BP002/BP003 on Linked/Related MPANs needs to be updated as it includes reference to email/SDEP rather IF-019 as shown in BP010 |  | Closed | [6 empty] | #REF! |  |  | #REF! | Confirmed - the call out box on BP002/003 needs to be updated Duplicate of DIN-64 | No Change | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service
MHHS-DIN-110 |  |  | 2023-02-27 | SI Design | 2983 | Kate Goodman | Testing |  | MHHSP-BP005-Data Processing-v4.6, Step 50-160 UMSDS is referencing Submit Required UTC period level consumption data (Step 50) with a arrow going to Receive UTC period level consumption data (Step 160) but no reference of IF-021 on the connection between both - reference should be added? |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | On Process map requires arrow to be labelled as IF-021 from step 50 to step 160 | Process model correction | Meter to Bank | Data Processing | MHHSP-BP005-Data Processing
MHHS-DIN-111 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Originally raised as T4-COM-1691 on 15th Sept 2022: "MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days " Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5 (Raised as DI-76) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated to 2 working days | Requirement correction | MPAN Ownership |  | MHHS-BRS003-Registration Service requirements
MHHS-DIN-112 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54 (Raised as DI-77) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Added note to clarify | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-113 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? (Raised as DI-78) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Agreed duplicate of DIN-29 and can clsoe | No Change
MHHS-DIN-114 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | EES does not appear to have been added to the routing rules tables on the interface tabs(Raised as DI-79) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Already present in v5 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-115 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On IF-050, this includes linked MPANs in it, but I don’t think these would ever be populated as you cannot link MPAN at MPAN creation. So EES would only ever get Linkage updates on the IF-20 Is there any value of having this therefore in IF-050?(Raised as DI-80) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Removed Linked MPANs and Related MPANs from IF-050 and added explanatory note | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-116 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | For IF-025, block B032 it states it is "MPAN Legacy Info (Mandatory where event is [SSCandProfileClass], and for Traditional Meters / Optional for other Meters)" It should just read mandtory for event code [SSCandProfileClass] and nothing else, it should not be optional for any of the other event codes(Raised as DI-81) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-117 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?(Raised as DI-82) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Discussed with SCS and confirmed it is a limitation of swagger output but should be array of MPAN followed by array of meters followed by array of MAPs repeated per MPAN. Awaiting confirmation can close | No Change | Metering Changes | IF-005 JSON | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-118 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | In relation to the Sender Unique Reference, which is constructed as: S-<Interface>-<Participant Id>-<Role Id>-<Date>-<Sequence> (hex) I would like to comment as follows: • Why is the Unique Reference simply constructed using elements that are already contained in the message as distinct values? This just means the sender has to construct it and the receiver de-construct it? • Is the sequence number expected to be reset each day ? • It would be much easier and more logical for the Sequence to be a distinct item in the message? • Why is the sequence specified as hex? • Even given the expected large number of messages, and based on it being a number(13) (defined as Sting), a standard sequence number per Participant and Role would provide 9,999,999,999,999. If this is still seen as a limitation then it could simply be built from the date, e.g. 202301190000000001, giving a provision for up to 9,999,999,999 messages PER DAY from the same Participant / Role combination, which still enables a read every 30 minutes from every MPAN(Raised as DI-83) |  | Closed | [6 empty] | #REF! |  |  | #REF! | This is to send a unique reference and is used for auditing purposes. Please note the length of the Sender Unique Reference has been increased at the request of Avanade in 5.1.1. Examples updated |  | MPAN Ownership
MHHS-DIN-119 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | in swagger hub under IF-002 B907 list the B036 block, this is missing numberOfDigitsCumulativeRegister data item(Raised as DI-84) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue. Swagger will be updated | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-120 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Inconsistency in naming of data item DI-091 In swagger hub: Number-Of-Digits-Cumulative-Register In interface catalogue IF tabs (E.g. IF-002) : Number of Displayed Register Digits In interface catalogue data catalogue tab: Number Of Displayed Register Digits (Cumulative Register)(Raised as DI-85) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue and updated YAML accordingly | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-121 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0093 comment raised on 12/01/2023 " D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: "It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42 (Raised as DI-86) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Agreed to provide SEG scenario's in IF-005 Use Case guide. currently under review |  | Metering Changes | Change of Segment | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-122 |  | DI-87 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0084 comment raised on 12/01/2023 following the introduction of IF-019 and respective changes in the latest set of released artefacts MHHSP-BP010-Change of Registration Data -v4.5 "Shows Supplier Mastering Import Export Linkage. BSC CP1558 introduced changes to MPRS for the LDSO to manage this via the DB05. IF-019 should go to LDSO who should then produce a DB05 into MPRS." The process diagrams and requirement spreadsheets have been amended to show MPRS loading DB05 as a IF-019 response. DB05 is not a IF-019 response, it is a request from DNO/iDNO to create, amend or remove a import/export linkage. It does not currently have any capacity to include a IF-019 rejection response to trigger a IF-020 rejection response to DIP. (Raised as DI-87) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | SCS reviewing preferred option with LDSO's The following changes would be required to the LDSO overview requirements: MHHS-BR-LD-043.3 LDSO Send Import/Export relationship update LDSO must send accepted Import/Export relationship updates to the Registration Service via the appropriate interface DB05 file or other agreed mechanism BP010B Change of registration data 900 MHHS-BR-LD-043.4 LDSO Send Import/Export relationship rejection LDSO must publish rejected Import/Export relationship updates on the Data Integration Platform using the appropriate interface MHHS-IF-020 to Supplier BP010B Change of registration data 900 On BP-010 for Linked Import/Export MPANs the following would be required: 1. Need to add rejected leg from step 900 to DIP 2. Need to add PUB-020 going from the DIP to the Supplier The BPD-010 will need updating accordingly. | Process Model correction | MPAN Ownership |  | MHHSP-BP010-Change of Registration Data MHHSP-BPD010, MHHSP-BRS005, Traceability Matrix
MHHS-DIN-123 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0083 comment raised on 12/01/2023 following the introduction of a new business rule on MPRS in the latest set of released artefacts MHHS-BR-RS-078 "MPRS cannot control how messages are sequenced at CSS and DSP. IF MPRS waits until the DSP responds before sending the Appointment message this could take hours (as this is a batch process) this will result in a delay in the appointment of the MDR. Sequencing requirements should be placed on CSS & DSP to ensure the correct MDR is appointed based on Effective dates provided from MPRS. However, they may not be necessary due to the way this interface works: The C0200 interface uses the PUT Method, which will replace the data held at CSS. Explicit ending of an Appointment is only required for a future dated appointment, this will be sent as one message with the Old and New MDR appointments. For Same Day or Retrospective the new MDR Appointment will Replace the currently set value. This implicitly ends the previous MDR Appointment. On a CoS, the MDR is linked to a Registration not a Metering Point. The previous MDR will end naturally when the Previous Registration becomes securedInactive. An explicit message to end the MDR appointment on the Previous Registration is not required . MPRS will only send two separate updates to CSS when there is a gap in MDR (SDS) appointments. For Example a change of segment to Advanced and then back to Smart. This would need to happen over a short period to generate two messages that could go out of sequence" The MHHS design team rejected with comment "The MHHS design is based upon what was agreed as part of the R044 consultation. This scenario does not reflect our understanding of how the CSS/DCC/DSP interface will work as set out under R044. " This is how C0200 currently works today and the interface is unchanged in R0044. This will put a signfiicant requirement on MPRS that will reduce time available time for other core MHHS development activities with no benefit to industry.(Raised as DI-87) |  | Closed | [6 empty] | #REF! |  |  | #REF! | No Change - updated in v5.0 | No Change | MPAN Ownership
MHHS-DIN-124 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0089 comment raised on 12/01/2023 "D-021 was meant to give more detail on how L1-L4 validation should be used and provide more error codes for use. This has not been done as far as I can see Blocking resolution to this T4-COM-1749, T4-COM-1769 and T4-COM-1768" Comment was closed as clarified however none of these items have been resolved and we have no dates as to when they will be. comments blocked that were raised initially on 15/09/22 Comment T4-COM-1749: "The Registration Service, as part of its L3/L4 validation should ensure that there is consistency between the data content of the IF-033 issued to the Service Provider and the [returned] content in IF-034 - if this isn't so then message should be returned to Service Provider using ""MSGStatus Message"" mechanism." Does MPRS only need to validate consistency in the data it loads on the IF-033, not the data that is not loaded" Comment T4-COM-1769: "We need validation rules to be defined for this flow, Does not match IF-031, content of the PUB-034 does not match the IF-031. No Proposed Appointment Found, PUB-034, does not link to any Pending IF031s. Define Validation Rules for PUB-034 The 034 content must match the original if-031 content the 034 must have a corresponding IF031 the 034 has already been received for the IF-031 Generic Standard Validation, MPAN exists valid in ISD ETC" Comment T4-COM-2768: "We need some generic codes for standard validation rules such as: Service/Supplier is valid in ISD MPAN exists in MPRS MPAN is not Disconnected Service/Supplier is Valid in MDD (so CSS doesn’t reject updates)" (Raised as DI-89) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Added RMP status check to IF-034 and refined validation rule notes regarding different values received from IF-033 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-125 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | IF Routing | WOA-0091 comment raised on 12/01/23 D-030 "how routing will work in the DIP has not been updated this information is required for our development" MHHS Design Team has closed as clarified however there is still uncertainty around the DIP routing, and there are not dates provided for when the detailed DIP design will be released. This will clock certain elements of development (Raised as DI-90) |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Secondary routing rules updated following review with Avanade (see DIN268) |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-126 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0092 comment raised on 12/01/23 following more infromation around D-022 being clarified "D-022 Following the work off item being agreed on what is required for an MPAN to be traded - it has now been possible to fully assess the optionality of data items in the interfaces Data items still mandatory in interfaces that must be changed to optional: Annual Consumption (IF-001) Incumbent Service Providers (IF-002, IF-033) Incoming MS/DS (IF-037) These are not required at creation, nor at traded, and therefore could be non existent in MPRS when MPRS generates this outgoing IF messages Blocking resolution of T4-COM-1727 and T4-COM-1735" Closed as clarified however none of the issues listed have been resolved Annual consumption still reads madatory on a CoS for IF-001, the issue is MPRS may not have this data item. The item is not required to reach a status of traded, therefore CSS will accept a CoS on this MPAN without annual consumption being populated, and then MPRS will not be able to provide this data item on the IF-001 that results from the CoS. This must be changed to optional OR the definition on what is needed to be traded should be updated to include annual consumption. Incumbent Service Providers is still mandatory on IF-002 for CoS Again as MS is not required to be traded, CSS will accept a CoS request with or without a current MS, and so MPRS will not be able to provide an incumbent MS in these cases. It must be changed to optional or the definition of what is needed to be traded should include MS. Incoming MS/DS is still mandatory on IF-037, there are numerous reasons an appointment may be lapsed, the only change that would gaurantee a new incoming SP that MPRS could send on this flow is a change or SP (CSERV) scenario. For CoS the supplier may not have sent in new appointments, for DEREG there will be no new appoitnments, for SEG the market segment may have changed but the supplier may not have sent in new appointments, same for change of connection type, and for IMPEXP and RELATED the parent MPAN might not have MS/DS appointed at all so there would be no new appointments for MPRS to populate on this flow. This must be changed to madatory ONLY on CSERV (Raised as DI-91) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Discussed with SCS. Covered by clarification on nullable and interface notes- All these issues are resolved by the Mandatory Nullable Solution. Confirmed Annual Consumption block will only be provided where available in Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-127 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 "DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least "Registered", if no DS is appointed then there is already an appropriate Event Code" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone (Raised as DI-92) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-128 |  | DI-93 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0095 comment on 12/01/23 "D-009 This is blocking closure of T4-COM-1730. There is a lack of clarity around the treatment of rejection from CSS, between both R044 and the MHHS design artefacts e.g. MHHs-BR-RS-088.1 and MHHS-BR-RS-079 both suggest MPRS would still load the new MDR record and appoint in MPRS despite a rejection from DCC/CSS. Our assumption would be that we do not load a MDR appointment that is rejected from DCC/CSS and we send the IF-035 rejection to notify the DS/Supply of this. However no clarity on what to do if DCC/CSS rejects a MDR end date on a de-appointment T4-COM-1730 was raiseed on 15/09/22 MHHS Design Team Rejected the comment with a statement this is outside of MHHS Scope. How MPRS treats the MS/DS appointment and how it responds over hte DIP is within MHHS design. The requirements we are enquiring about are already included in the MHHS design documents as in scope also. This is a major blocker to MPRS design on MDR appointment processes (Raised as DI-93) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Discussed with SCS this is a REC requirement. Agreed no error codes will be received, just use a generic response. | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-129 |  | DI-94 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0086 comment on 12/01/23 following the release of the first draft of IF-050 in the revised interface catalogue artefact "Related MPANs and Linked Import Export are not set at MPAN Creation. EES can get these on the IF020 Remove these blocks from IF-050 as they would never be populated" MHHS design team marked as accepted and changed but the blocks still exist in IF-050, these blocks will never be populated and so should be removed from the IF-050 interface(Raised as DI-94) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Closed - duplicate of DIN-115 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-130 |  | DI-95 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0088 on 12/01/23 "D-011 & D-050 it is still unclear how LLFC and DUoS Tariff ID will be stored and managed in MPRS. DUoS should be an Alias of LLFC and not have its own data item in MPRS. LLFC will be renamed to DUoS Tariff when the old arrangements have ended. LDSO impacts having to maintain two items which will lead to billing issues" Marked as clarified and closed witih a clarification statement to be issued on tuesday 24th January, this clarification statement was not received. Awaiting clarification(Raised as DI-95) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Email to Madison to check can close |  | MPAN Ownership
MHHS-DIN-131 |  | DI-96 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 is missing business rules: REG1001 - MPAN [DI-063] is at [REG.RMPStatus] not status Created/Operational. This should apply to IF-025. IF-025 is missing a rule that consent granualiry EFD must not be earlier than supply start date. Consent Granularity EFD must not be prior to current consent granularity EFD The Consent Granularity Energy Direction Domestic Premise Indicator Combination must be valid in ISD(Raised as DI-96) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-132 |  | DI-97 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 IHD update does not include validation rule 1019, does this mean IHD EFD can be prior to current and effectively cancel out the current IHD status completely, or is it just an error and the rule should be added to interface catalogue for IHD?(Raised as DI-97) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Amendment accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-133 |  | DI-98 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 will not allow a SMSO to be set for a non smart meter "REG1022 - SMSO ID Cannot be set where Market Segment is [Reg.Segement]", would a non smart supplier be able to send a B031 SMSO block, they will need to be able to if they are required to clear an old SMSO by populating SMSO as null(Raised as DI-98) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Added new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-134 |  | DI-99 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 "SSC must be valid in ISD. Rejection reason: REG1044 - SSC must be a valid value in ISD" SSC are not yet populated in ISD(Raised as DI-99) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Clarified that SSC validation will be based on Frozen MDD. Seperate DIN to cover availability of ISD | No Change | MPAN Ownership |  | MHHSP-EM021 ISD Entity Data Map, MHHSP-DES138-Interface Catalogue
MHHS-DIN-135 |  | DI-100 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Should B032 PC and SSC block on IF-025 only be permitted when theres a traditional meter fitted at the MPAN?(Raised as DI-100) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-136 |  | DI-101 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | How is the Green Deal Exists defined. Does this mean there's a green deal linked to the MPAN regardless of dates, does it mean there's a green deal currently active or due to become active, or does it mean there is a currently active green deal assigned to the MPAN? (Raised as DI-101) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Remove Green Deal exists (DI-110) from Data Catalogue and IF-050 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-137 |  | DI-102 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-007 Validation rule "Metering Service [S0.SenderID] holds valid previous appointment then Energisation Status EffectiveFrom Date [DI-034] should be < [REG.App End Date] + 10" The way it's curently written suggests MPRS should accept an IF-007 from the previous appointed MS, event if there ETD was greater than 10 days ago, provided the ES EFD date was less than their ETD + 10. E.g the previous MS could send IF-007 two years later with ES EFD of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then a separate rule should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? Linked to DI-41(Raised as DI-102) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | REG1003 validation rule updated in IF-007 to constrain energisation updates to 10 days after the MS appointment period |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-138 |  | DI-103 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-034 Submitted rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD |  | Closed | [6 empty] | #REF! |  |  | #REF! | Duplicate of DIN-176 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-139 |  | DI-104 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Need clarity on what role code should be used in C0200 for MS and MDR appointments Linked to comment T4-COM-1790 which was accepted as design issue raised but then moved to a work off item "We would like to see some indicative Role Codes and DIP IDs so we can populate development systems with this data " |  | Closed | [6 empty] | #REF! |  |  | #REF! | Send "MDR" as role code as per Registration requirement. Allocation of DTN MPIDs is a seperate issue | No Change | Registration | Existing EMAR I/F | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-140 |  | DI-105 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 |  | Closed | [6 empty] | #REF! |  |  | #REF! | Discussed with SCS the IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR. Agreed to close | No Change |  |  | MHHSP-BP003A, MHHSP-BRS003 Registration service requirements
MHHS-DIN-141 |  | DI-106 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 |  | Closed | [6 empty] | #REF! |  |  | #REF! | RECCo consequential change | No Change |  |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-142 |  | DI-107 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | There currently aren't sufficient rules to ensure that a principal primary MPAN is not also a linked export subsidiary MPAN or that a subsidiary secondary MPAN is not also a principal import linked MPAN. The MHHS design either should accommodate both (would need clarity on how to treat cases where MPANs are BOTH principal and subsidiary) OR new rules should be introduced to prevent this occuring AND cleanse existing cases ahead of migration |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Validation rules updated for IF-019 | Missing/incorrect validation rule | MPAN Ownership |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-143 |  | DI-108 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Requirements were uplifted in v4.5 to include logic around market segment on related MPANs MHHS-BR-RS-124.1: Registration Service must, in the case of Related MPANs and following derivation of Market Segment for individual MPANs, update the Market Segment for the Primary MPAN and all the Secondary MPANs based on the following rule: 1. If any MPAN in the Related MPAN Group has a (derived) Market Segment of Advanced, then set the Market Segment for all the MPANs to Advanced and set the Market Segment Valid Flag to "Yes" for all the MPANs This specifically cites related primary/secondary and does not mention linked import/export associations at all. But then another requirement implies maybe it should have done: MHHS-BR-RS-127: Registration Service must , in circumstances where the derived market segment is invalid (and has not been overridden by Linked/Related MPAN logic ) Should MHHS-BR-RS-124.1 have applied to linked import/export associations too or is it intended solely for primary/secondary related MPANs? |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | This should only apply to Related MPANs. Updated RS-127 | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-144 |  | DI-109 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131 This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to: Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Duplicate See DIN-169 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-145 |  | DI-110 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Added L as valid value for DI-979 in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-146 |  | DI-111 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Agreed with SCS to reuse STD Error Response Section in IF035 to communicate Lapsed Reason . See DIN-145 for summary of updates | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-147 |  | DI-112 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-008 response block is listed as mandatory, however on disconnection the MPAN is de-energised by MPRS automatically. The supplier cannot de-energise after disconnection on the IF-007, it must be automatic at MPRS as per The de-energisation needs to be communicated on the IF-008 but it is not in response to an IF-007 and so we cannot populate the response block. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Data interface change agreed. Added Interface note to IF-008 to cover forced de-energisation changes by Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-148 |  | DI-113 | 2023-02-10 | St Clements | 2864 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-113 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { "confirmingMpid": "string", --* "registrationId": "string" --*, "updateSucceeded": boolean --* } Suggest that DI-0980 is removed from B066 |  | Closed | [6 empty] | #REF! |  |  | #REF! | Discussed with SCS and agreed to close - note no error codes returned from CSS so will provide generic error code | No Change |  |  | MHHSP-DES138-Interface Catalogue, JSON, YAML
MHHS-DIN-149 |  | DI-114 | 2023-02-10 | St Clements | 2865 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-114 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 On IF-038 validation "REG1073 - Customer Direct Contract already exists for MPAN [DI-063] for that period" The respective validation rule for this states: If Contract End Date [DI-145] <= Max existing active MS contract end dates [Reg.MAX_DCMS_Enddate], EXCEPT IF requesting MS [S1.SenderID] = Currently Active Direct MS [Reg.CurrentActiveDC_MS_DIPID] AND Contract End Date [DI-145] <= existing active MS contract end date [Reg.CurrentDCMS_Enddate] This rule doesn't fully prevent overlapping appointments as does not cover where the MS is not currently contracted MS and ETD > current ETD which should also be rejected. Think a simpler rule would cover this scenario more fully e.g. If there is an active contracted MS/DS, and the submitting MS/DS does not match then reject And then ETD can be greater or later than current ETD for the currently contracts MS/DS anyway so doesn't need specifying? |  | Closed | [6 empty] | #REF! |  |  | #REF! | SRO Team do not believe that a change is required. Linked to DIN-554 |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-150 |  | DI-115 | 2023-02-10 | St Clements | 2866 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-115 in our log In some place on IF-038 tab there is reference to a future customer direct contract e.g. "OR requesting MS [S1.SenderID] <> Any future Direct MS [Reg.FutureDC_MS_DIPID] " "extended dates will be subject to checking if another Service Provider has registered a separate Customer Direct Contract covering the same period" - this can only happen if there's a future appointment "AND ALSO removing all future periods which may or may not have been accepted and recorded previously." As there is no Effective From Date included in the flow MPRS will store an Effective From Date of the system date at the time of creation of the customer contract indicator. It will not be possible to set one to start in the future as the IF-038 does not include effective from date. Is this the same understanding as the MHHS Design Team? |  | Closed | [6 empty] | #REF! |  |  | #REF! | As per DI-149 above SRO Design Team do not belive that any changes are required |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-151 |  | DI-116 | 2023-02-10 | St Clements | 2868 | Madison Layton | Software Provider |  | Just spotted a change in v4.7 and raised in our log as DI-116 Artefact: MHHSP-BP010-Change of Registration Data -v4.7 under MPL and GSP Group amendment section, DB02 has been amended in v4.7 to DB002. DB002 is not correct, DB02 was the correct name For reference the DB flows only ever have one 0 in, there is DB01 (MPAN creation), DB02 (MP updates), DB03 (Disconnection) and DB05 (Import/Export Linkages) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | BP010A step 10 flow name change to DB02, BP010B step250,step440, Step560 flow name change to DB02, and update BPD descriptions to DB02. | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-152 |  | DI-117 | 2023-02-14 | St Clements | 2912 | Madison Layton | Software Provider |  | On looking more closely at the validation rules for IF-019 spotted a few issues. IF-019 REG-1061 rule for Related Create event code appears to be written incorrectly. The rule and rejection description don't quite align. Rule: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) are not currently part of an import/export relationship Rejection reason: REG1061 - Prosposed MPAN(s) [DI-073] / [DI-074] are already part of a Related MPAN Relationship Should the rule read: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) is currently part of a related primary/secondary relationship? The rule and descriptions also don't appear to fully align for some in import/export section too - REG1052, REG1055, REG1057 and might need some minor tweaks to correct. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | REG1061, 1052 and 1055 rules updated. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-153 |  | DI-118 | 2023-02-14 | St Clements | 2913 | Madison Layton | Software Provider |  | On working on detailed design for Related MPANs, noticed the IF-019 interface is missing a rule that the Secondary MPAN must not be a Primary in another Relationship. You could expand REG1064 to include this as the description sounds like it should have been covered here. Rule: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN Description: REG1064 - Proposed Secondary MPAN [DI-074] is already part of a different MPAN Relationship Could amend rule to: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN OR [DI-074] is already in a relationship as a Primary MPAN |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | REG1064 validation rule updated | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-154 |  | DI-119 | 2023-02-15 | St Clements | 2919 | Madison Layton | Software Provider | IF-019 validation gap on primary and subsidiary MPAN | On further detailed design we’ve spotted a potential design gap. Currently it is possible to enter a state where an MPAN is both a primary and subsidiary MPAN at the same time (e.g. Primary but also export linked or Secondary but also import linked). The current MHHS doesn't accommodate an MPAN being in both states at the same time. We’ve already looked to add rules to try to mitigate this on DB02/DB05 internal flows but would need additional rules on IF-019 to fully prevent this scenario occurring. Rules we think are required: 1. On receipt of IF-019 with event code RelatedCreate or RelatedAdd, the primary MPAN must not have energy direction of Export 2. On receipt of a IF-019 with event code RelatedCreate or RelatedAdd, any listed secondary MPAN must not in an active Import/Export relationship as the Import MPAN 3. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Import MPAN must not be in an active relationship as the secondary MPAN 4. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Export MPAN must not be in an active relationship as the primary MPAN |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Agreed with SCS that changes to IF-19 tab would be made to support Rules 1 and 4. Validation Rules updated accordingly with new Error codes (REG1067/1068) created to support. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  | 2023-07-14
MHHS-DIN-155 |  | DI-120 | 2023-02-15 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. |  | Closed | [6 empty] | #REF! |  |  | #REF! | see also DIN-172/173. Included in 5.1 DUPLICATE See DIN-172 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-156 |  | DI-121 | 2023-02-24 | St Clements | 3078 | Madison Layton | Software Provider |  | We have logged a new design issue under DI-121. IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP |  | Closed | [6 empty] | #REF! |  |  | #REF! | Duplicate of DIN-173 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-157 |  | DI-122 | 2023-02-27 | St Clements | 3090 | Madison Layton | Software Provider |  | New design issue (SCC Ref DI-122) for the IF-005 related to REC CP R0032. The current v5.0 validation in the IF-005 does not include the new validation introduced with REC CP R0032 (R0032 is approved and being implemented in the D0312 this June): NEW REC CP R0032 Validation: V Rejected – ESME ID already exists within MRPS and does not match Removed Meter, Associated Import/Export MSID or Related MPAN W Rejected - MSN relates to a Smart Meter Type and the ESME ID is NULL X Rejected – ESME ID Format is Invalid Y Rejected – Number of Displayed Register Digits is NULL and the MSN relates to a Smart Meter Type Z Rejected – Non-Smart Meter Type with Number of Displayed Register Digits populated AA Rejected – Meter Location is invalid AB Rejected – Non-Smart Meter Type with ESME ID populated AC Rejected – Number of Displayed Register Digits is incorrect IF-005 Validation: V not covered, needs to be added as a Level 5 Validation Rule W is already covered by DI-085 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) X is already covered in DI-085 population notes (Level 4 validation RCP1023 Msg Contains Invalid Valid Value Combination(s)) Y is already covered in DI-091 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) Z is not explicitly covered, suggestion: add to DI-091 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AA is covered in the population notes AB is not explicitly covered, suggestion: add to DI-085 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AC not covered, Suggestion: add the following population note from R0032 to DI-091: Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” Summary Please add the following Changes to the IF-005 to align it with the D0312 validation and maintain the same level of Smart Meter data quality in the Registration Service: New Level 5 Validation rule for DI-085 implementing V from the D0312. ESME ID must be unique within MPRS unless it’s a Linked MPAN where the same Smart Meter can be shared across Linked MPANs New population note for DI-091, only to be included for Smart Meter Types New population note for DI-085 , only to be included for Smart Meter Types New population note for DI-091, Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | New Validation Rules added to IF doc to ensure full coverage and alignment with CP Error codes described | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-158 |  |  | 2023-02-27 | Elexon | 2908 | Derek Weaving | Central Body | Use of CCCs to categorise the data for future charges | As part of the Performance Assurance Working Group discussions on Supplier Charges, we are exploring the use of CCCs to categorise the data for future charges. It is noted that Settlement Period Quality Indicator referenced in the VAS Method statement is for illustrative purposes and would welcome clarity on the following: · What is the intended process to populate the Settlement Period Quality Indicator in the initial ISD Table? · What would be the process to be involved in those activities to determine the categorisations should additional CCCs be required? |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | This DIN has been moved to Interim Release 5 as it is related to DIN-409 which has an objection raised that is pending a discussion to clarify the solution. Name change and field length have been actioned. Reviewing whether any changes to Settlement reports are required Recommending a change to this ISD Data Item: Settlement Period Quality Indicator to be set as per Appendix 1 of MHHSP_METH007 MDS_Method_Statement v5.0 This data item need to be changed to something like ‘Valid Settlement Period Quality Indicator Set’ and the field size needs to be increased. The data catalogue will need the revised data item and the field length will need increasing from 20 to at least 100. This Item also appears in some interfaces that will need to be updated. This is because it represents a set of SPQIs. The initial intention is to populate as per the table and check if any new SPQIs have been introduced in the baseline design Method Statement that are not covered. If new CCCs are introduced the appropriate flags for each new CCC would need to be agreed. However, it is likely that another dimension to the table below would need to be introduced to facilitate new CCCs. Word 'Illustrative' to be removed and will be updated to say Valid Settlement Quality Indicator Set. Change to be made across all impacted Method Statements. New CCC's will require a Modification to the BSC interface requirement. Proposed changes have been reverted to the initial state. Data item Settlement Period Quality Indicator, with a field length of 5. This is due to the agreed solution for DIN409 following DRG where it was agreed the list element would be removed in favour of individual row(s). The word 'Illustrative' will also remain within the Method Statements. | Missing/incorrect validation rule | Meter to Bank | Volume Allocation Service | MHHSP-METH006_VAS_Method_Statement MHHSP-METH007_MDS_Method_Statement v5.1 EDI021 ISD Entity spec |  | 2023-07-14
MHHS-DIN-159 |  |  | 2023-03-01 | ENWL | 2994 | Paul Band | Network Business | Interfaces for UMSO | DES-138 Interface Inconsistencies vs BSCP7XX for UMSO Discussions with ENWL have highlighted a number of inconsistencies in the Interface Catalogue when it comes to routing for UMSO's. DIN-106 also refers. UMSO is not listed as a recipient in DES-138 for the PUB-008, but this is in the draft BSCP and should be added to the PUB UMSO is not listed as a recipient in DES-138 for the PUB-020, but this is in the draft BSCP - this is not needed in the BSCP as there are no unmetered Related MPANs UMSO is not listed as a recipient in DES-138 for the PUB-035, but this is in the draft BSCP - view that it is unlikely for this flow ever to be used as the appointment will not trigger any processes to need a subsequent update UMSO Is listed as UMSI, not UMSO in PUB-036 in DES-138 UMSO is listed as UMSC, not UMSO in PUB-018 in DES-138 The IF_LIST tab should be reviewed for consistency |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | As with DIN-106, there are inconsistencies in the Interface Catalogue for UMSO routing. This has been compounded by a review of the draft BSCP for UMSO, which has added a number of PUB flows going to UMSO that aren't currently in the catalogue. Covered by updated secondary routing rules (see DIN268) Design to check requirements in BSCP and MHHS BPs and ensure the interface catalogue reflects a consistent approach | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue and possibly related business processes and descriptions E2E001 |  | 2023-06-16
MHHS-DIN-160 |  |  | 2023-03-14 | Ovo Energy | 2862 | David Morley | Supplier | BP009 flow addition | Steps 205 and 210 in BP009 wont be completable in the event that theres no comms. I think the process would be workable if there was an exception route here - see red arrow below. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Update Steps 205 and 210 in BP009 with "Comms Available" line label add flow from step 205 to step 215 with “Not Commissioned / No Comms” line label | Process Model correction | Metering Changes | Change of Metering | MHHS-BP009 |  | 2023-06-16
MHHS-DIN-161 |  |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 requirement correction | MHHS-METH001-5.4c Please confirm the requirement: “where daily advance records are available [either in the past or future] and less than 90 days months different from the UTC Date requiring a daily advance - use the mean actual Meter advance from the closest [4] weeks for the same Day Type (as defined in ISD).” |  | Closed | [6 empty] | #REF! |  |  | #REF! | Duplicate of DIN 97. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-162 |  |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 typo | MHHS-METH001-5.5 typo “Where DAEs are required to be calculated the SDS shall use the most recent data a based on the event that triggered the estimation.” |  | Closed | [6 empty] | #REF! |  |  | #REF! | Duplicate of DIN 98. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  | 2023-06-16
MHHS-DIN-163 |  | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Conditionality Rule for B037 | It is not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure it is unclear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated conditionality rule for Block B037 in IF-001, IF-002, IF-033, IF-036: to show that Either DI-075 (Primary MPAN) or DI-079 (Secondary), and not both, should be populated where MPAN (DI-063 above) is part of a group of Related MPAN. |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-164 |  | DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0093 comment raised on 12/01/2023 "" D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692"" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: ""It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period"" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42" |  | Closed | [6 empty] | #REF! |  |  | #REF! | "This requirement stands - review with SCS in light of SEG scenario. We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error...". Reviewed with SCS and agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-165 |  | DI-122 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | See separate sheet Duplicate of DIN-157 |  | Closed | [6 empty] | #REF! |  |  | #REF! | CR required to add rules in line with CP R0032 Added Miscellaneous Data Validation to IF-005 to cover REC CP R0032 validation rules Wrapped up into design teams main CR Doesn't need to be raised by SCS | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-166 |  | DI-77 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54" |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Added clarification to REG Notes re Consent and Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-167 |  | DI-78 DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? " |  | Closed | [6 empty] | #REF! |  |  | #REF! | Agree you can't. Could update 1032 rule for USP? Duplicate see DI-29 | No Change
MHHS-DIN-168 |  | DI-92 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 ""DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least ""Registered"", if no DS is appointed then there is already an appropriate Event Code"" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone |  | Closed | [6 empty] | #REF! |  |  | #REF! | CR for new functionality. "Already covered by no MS/DS appointed - MPRS would try to align MS/DS with principle and couldn't as there's no registration to align this to. Need an extra check that can only autoappoint if there's a registration to prevent MPRS crashing Maybe one for DRG? Jon at RECCO for consequential change? Agree not to build for this scenario as this would be an edge case and close | No Change
MHHS-DIN-169 |  | DI-109 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to:Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Simplified MHHS-BR-RS-131 on when to lapse a SEG appointment | Requirement correction | MPAN Ownership |  | MHHSP- BRS003, MHHS-BR-RS-131
MHHS-DIN-170 |  | DI-110 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Duplicate of DIN-145 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-171 |  | DI-113 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { ""confirmingMpid"": ""string"", --* ""registrationId"": ""string"" --*, ""updateSucceeded"": boolean --* } Suggest that DI-0980 is removed from B066" |  | Closed | [6 empty] | #REF! |  |  | #REF! | Agreed with SCS being retained but due to optionality may have to populate text e.g. contact DSP. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-172 |  | DI-120 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. |  | Implemented |  |  |  |  | 2023-04-27 | Interim Release 1 | #REF! | 2023-04-27 | Interim Release 1 | #REF! | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-173 |  | DI-121 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP |  | Implemented |  |  |  |  | 2023-04-27 | Interim Release 1 | #REF! | 2023-04-27 | Interim Release 1 | #REF! | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-174 |  | DI-72 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a Submitted MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60" |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | "Agreed- doc updates MDR can have gaps between DS EFD and MDR EFD" Updated REG1083 validation in IF-034 so that it allows MDR Effective from dates >= SSD/ DS Eff From date/Existing MDR Eff from date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-175 |  | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" |  | Closed | [6 empty] | #REF! |  |  | #REF! | Duplicate entry | No Change | MPAN Ownership
MHHS-DIN-176 |  | DI-103 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-034 new rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD" |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Agreed -doc updates Updated REG1082 to apply for both [SDS-MDRUpdate] and [DSAppSPRepsonse] events in IF-034 | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-177 |  | DI-105 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 " |  | Closed | [6 empty] | #REF! |  |  | #REF! | "Reason for IF-035 is to trigger when SDScan send the Meter info" & The IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR Agreed with SCS no changes are required, they now understand the context agreed to CLOSE | No Change | MPAN Ownership |  | MHHSP-BP003A
MHHS-DIN-178 |  | DI-106 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | MS missing a requirement to send MS updates to CSS | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 |  | Closed | [6 empty] | #REF! |  |  | #REF! | Closed as discussed with SCS that this is out of scope for MHHS Programme. | No Change |  |  |  |  | 2023-07-14
MHHS-DIN-179 |  | DI-111 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Duplicate of DIN-146 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-180 |  | DI-125 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 the Meter Removal is currently not permitted for a prospective MS Is it possible for the MS to need to remove two meters and replace it with one? In which case meterexchange would only allow them to do part of this process (remove 1 and add 1) but not complete it, so SEG could not complete. Should meter removals therefore be allowed for prospective MS? (REG1019) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Revised REG1019 and added REG1027 for MeterRemoval event in IF-005 | Requirement correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-181 |  | DI-126 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Missing Rule on If-005: MAP EFD must not be > removal date |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Added new rule for MeterUpdate and MeterHistoryUpdate events so that MAP EFD must not be > removal date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-182 |  | DI-127 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 On exchange - the MAP and IHD groups are for new installation not removed meter - does this need to be clarified? |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | New note added to IF-005 to clarify that only the newly installed MAP and IHD information is required on MeterExchange | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-183 |  | DI-128 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-005, IHD EFD missing validation in IF-005 (Between install and removal date) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Covered Release 5.1, IF-005, IHD EFD missing validation added | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-184 |  | DI-129 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-005 incorrect validation rule: REG1010: On event code Meter exchange and Meter Install rule states MAP EFD >= Install date, it should be = not >=" |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | IF-005: Updated to REG1010 (MAP Eff from date check ) to = install date for MeterInstall and MeterExchange | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-185 |  | DI-130 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | It should not be possible to change MDR EFD once set. Need validation rules to enable MPRS to reject if IF-034 is submitted with current MDR but a different EFD. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Agreed - doc updates Covered by L3/4 validation as per updated Validation rule notes | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-186 |  | DI-131 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031, there is currently not enough validation to ensure on a SEG, that the same SP isn't appointed for the current registration. Need additional validation rule: If scenario SEG and current supplier, then SP must not be current SP. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Agreed - doc updates Updated validation rule Added REG1095 in IF-031 to check different Data Service proposed for SEG appointment | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-187 |  | DI-132 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Supplier inability to appoint MS/DS for Principal and Subsidiary MPAN | Unhappy Path Scenario: Receive IF-031 for MPAN that is both Principal and Subsidiary MPAN at the same time. This will be rejected as per REG1038/REG1039 Supplier will be unable to appoint MS/DS for the MPAN or any related/linked subsidiary MPANS. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Closed, there is an existing to prevent this scenario happening going forward. Agreed with SCS to raise examples in the Data Cleanse Forum. | No Change |  |  |  |  | 2023-07-14
MHHS-DIN-188 |  | DI-133 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031 the rule REG1030 reads [DI0-828] in not a valid UMSO in DNO [DI-108]/[DI-109] This should read LDSO not DNO |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Tied up with If-005 rejection description flexibility action Change REG1030 to read: REG1030 - [DI0-828] in not a valid UMSO in LDSO[DI-108]/[DI-109] SC change incorporated into 5.1.1 | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-189 |  | DI-134 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On IF-031, REG1036 is written to only apply to USP when it should apply to all scenarios? ""Proposed MDR Date [DI-836] >= [REG.MPAN_SUP_SSD] However don't think this rule is required at all as this is already covered under the REG1036 rule that MDR Date < DS EFD? Linked to DI-66" |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-190 |  | DI-135 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-034 missing validation rule REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-191 |  | DI-136 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Addition of validation rules to MPRS to restrict Retrospective changes | MPRS does not currently prevent Retrospective changes to DUoS Tariff ID or Connection Type. Should MPRS add new validation rules for these items to restrict Retrospective changes? Please can you update DIN-191 to include Disconnection Date & Export Association. We don't currently have any restriction on how far these data items (and the others in DIN-191) can be back dated. This is a retrospective change through the DB interface and not a Manual Amendment. There are no retrospective periods for the following data items, this means the data items could be changed earlier than the settlement window and cause issues for settlement. There are restrictions that these data items must be within MS/Registration periods where appropriate, but the EFD/SSD could still be years into the past. - MDR EFD, - MS EFD, - DS EFD, - IHD Status EFD, - PC EFD, - SSC EFD, - Energisation Status EFD |  | Closed | No |  | Design gap | LDSO (SCS) |  |  | #REF! |  |  | #REF! | Covered in the retrospective changes discussion at DRG. | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  | 2023-07-14
MHHS-DIN-192 |  | DI-137 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | For If-031, scenario SEG, the business process diagram/requirements only describe the appointment lapsing once reaching it's SSD if no SA is received. If we receive a cancellation we would like to lapse the appointment at that point in time (it cannot become secured active after being cancelled) and not wait until the SSD to do this. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Added new requirements to BRS003, MHHS-BR-RS-24.1 and 58.1 | Design Ambiguous | MPAN Ownership |  | MHHSP-BRS003-Registration Requirements
MHHS-DIN-193 |  | DI-138 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | The YAML name for metered indicator (Data Item 127) is meteredUnmeteredIndicator. This is then set to true of false. It isn't clear whether true means it's metered or unmetered due to the naming convention. It should be named meteredIndicator instead to make it clear true means metered, false unmetered. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated YAML details in the Data Catalogue for DI-127 Metered Indicator. Updated YAML accordingly Updated data catalogue/ YAML | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-194 |  | DI-1 | 2023-03-15 | St Clements | 4475 | Madison Layton | Software Provider |  | For IF-035 what is Event Code [IMS-SendMTD] intended for? If intended for sending to old MS then this should be done via secondary routing on the original IF-035, not via another separate IF-035 message produced by MPRS with different event code. |  | Closed | [6 empty] | #REF! |  |  | #REF! | This message is effectively a copy of the DSAppAccepted AND/OR MSAppAccepted but sent to the Incumbent (current) Metering Service to act as a trigger for that MS to send MTDs. This should be created by MPRS. Requirements MHHS-BR-RS-053 and MHHS-BR-RS-019 cover Registration Service sending this. Message to check and close | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-195 |  | DI-76 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Originally raised as T4-COM-1691 on 15th Sept 2022: ""MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days "" Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5" |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Agreed doc update Also in Reg Notes tab Updated validation rules and Reg notes Updated REG1037 in IF-031 to 2 workings days and updated REG notes, to align with process and requirements | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-196 |  |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Updates are required to clarify nullable fields |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updates to Interface catalogue includes changes to interfaces and block data items which are present and can be null 1. MHHSP - ERI011A - ECS Reports - Internal v5.1: The data catalogue is the only tab that has been updated 2. MHHSP - ERI011B - ECS Reports - External v5.1: The data catalogue, DIP_Common, MHHS-REP-003 and MHHSP-REP-006 have been updated |  | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue, MHHSP-E2E001 End-to-End Solution Architecture MHHSP - ERI011A - ECS Reports - Internal MHHSP - ERI011B - ECS Reports - External
MHHS-DIN-197 |  |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Decision taken to document digital signing of interfaces outside of the interface document. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Remove Z0 and ZI blocks from all interfaces. Signing process will be documented in the Code of Connection document. | Technical corrrection | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue Code of Connection
MHHS-DIN-198 |  |  | 2023-03-15 | Large Suppliers |  | Haz Elmamon | Large Suppliers | Complex Meter Site | Clarification on complex meter site, passed down from DAG as part of the work off plan, Haz to gather concerns for discussion at DA. LSC Rep provided information to the issue on 22-Mar-23 |  | Closed | No |  | Further information required | Large suppliers | [8 empty] | MPAN Ownership |  |  |  | 2023-07-14
MHHS-DIN-199 |  |  | 2023-03-23 | BGAS | 3460 | Neil Strange | large Suppliers |  | Participant wishes to see the use of standardisation in the interfactions between the SDS and sub roles MDR PSS |  | Closed | [6 empty] | #REF! |  |  | #REF! | Closed based on recommendation for programme CR to be raised by the Large Supplier Rep | No Change | Supporting Docs | SDS Validation / Extimation | MHHS-DES138-Interface Catalogue
MHHS-DIN-200 |  |  | 2023-03-24 | CGI | 3489 | Chris Beard | Software Provider | Hierarchy definition for selecting correct register reading in the case of multiple readings for the same settlement period | If there are multiple register readings available for the same Settlement Day, where is the hierarchy defined for selecting which should be used? Is this solely based on Reading Method (i.e. 1. A – Actual, 2. C – Customer, 3. E – Estimated by SDS, 4. S – Estimated by Supplier) or is it dependent on other factors such as the Event Code in the IF-041 ([ReadingRemv], [ReadingInstl], [ReadingEnergisationChg], [ReadingCOR], [ReadingOnSite], [ReadingCOS], [DSEstimate], [SupplierAgreedCOS], [ReadingOverride], [ReadingRemote])? |  | Closed | [10 empty] | Reading methods do not apply to Register Readings - recommendation for DIN to be closed. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  | 2023-07-14
MHHS-DIN-201 |  |  | 2023-03-24 | ESG | 3529 | Patricia Parker | Software Provider |  | IF-033 Validation for population into the IF-034 The receiving party business validation rules state “Each Service Provider will need to determine their own validation criteria when processing Appointment Requests. The list below is intended to cover a number of potential possibilities based on the data items made available, and not to suggest that Service Providers needs or should perform such validations.” But should the DI-143 ‘Service Provider Proposed Appointment Response Code’ not form a valid set list (ENUM Vals) in the Data Catalogue so that all parties are working to the same list of applicable codes, rather than this field being a string with a length of 200 field? |  | Closed | [6 empty] | #REF! |  |  | #REF! | IF-033 has been updated as part of Interim Release 1 and the ENUM Vals will not be updated this is because we will have dynamic error messages which cannot be enumerated. |  | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-202 |  |  | 2023-03-24 | ESG | 3513 | Patricia Parker | Software Provider | Operational Choreography 60 minute turnaround | Registration Responses in connection with the PUB-31 given the NFS requirement is a 60-minute turn-around time. Within the Operational Choreography there is requirements OPC-140: From our understanding this means that when suppliers receive the PUB_032 from the Reg Service rejecting the appointment Request suppliers then have 60 minutes to re-issue a fresh IF_031 appointment. For example, there is a rejection code for 'CSS Reg ID not known', this would suggest that a party is out of sync and would need investigating especially as in this case, the REG ID would have previously been provided on PUB- 002, DI-849 and CSS is the master of the REG ID and not the Registration Service. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Added suggested text to Ops Choreography. Suggested text is "It is noted that some requests may require manual work and may be as a result of incorrect appointments from the Supplier. The expectation will be 90% of requests are systemically processed within 60 minutes with the residual being processed by the end of the following working day". | Doc Ref correction | Supporting Docs | Operational Choreography | MHHS_OPC001_Operational_Choreography |  | 2023-06-16
MHHS-DIN-203 |  |  | 2023-03-24 | CGI | 3502 | Chris Beard | Software Provider | mapping of Estimation Reason Codes to estimation Methods | MHHSP-METH001 M-13. Can you provide a definitive mapping of Estimation Reason Codes to estimation Methods? For example, LTV to Method 11. When should an SDS use Estimation Codes such as Opt Out, Comms. Fault. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated METH001 section 7.3 to reflect Estimated Methods to Estimated reason codes | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001 |  | 2023-06-16
MHHS-DIN-204 |  |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | De-energised sites | MHHSP-METH001 M-3. Which estimation Method should an SDS use for de-energised MPANs that would result in an estimation code of ‘De-Energised’? Without a specific Method statement to cover de-energisation, we will end up estimating consumption. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Added Method 13 to reflect de-energised sites within METH001 and updated section 2.29 on METH002. | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001 |  | 2023-06-16
MHHS-DIN-205 |  |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | Removal of Estimation Reason Code "Disconnected" | Can you confirm that the Estimation Reason Code ‘Disconnected’ will be removed from the table in 7.3? |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Removed "Disconnected" from Table 7.3 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement |  | 2023-06-16
MHHS-DIN-206 |  |  | 2023-03-27 | St Clements | 3703 | Anna Davis | Software Provider |  | Within the MHHS-E2E001 - End-to-End Solution Architecture, there is reference to MHHS-E2E003-Physical Interface Specifications in 1.3 References section This should be labelled as MHHSP-DES138-Interface Catalogue |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated 1.3 reference section | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-207 |  | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Clarity on when agent appointments should become effective | There is ambiguity within the design on when agent appointments should become effective, which means that different participants have a different view on when agent appointments should become active. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | At the DRG held on 4th August it was agreed that Appointments need to become active in UTC. Further workgroup discussions are being held to review impacts. References to local time removed pending agreement at Working Group/ DAG. Old solution: Appointments become active at midnight local time. Participants raised objections against the old solution therefore this DIN went to a DRG on 4th Aug for discussion. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  | 2023-07-14
MHHS-DIN-208 |  | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Registration Service rejection of Legacy messages for an MPAN | Within the existing Migration Design, it is stated that the Registration Service should reject all Legacy messages for a given MPAN once a Forward Migration has been initiated for said MPAN. This would prevent a legacy MOP from sending the relevant legacy flows if they need to change a meter when an MPAN is mid migration. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Closed following internal review with Design, Migration and Code Team. Agreed that current design will stand in that all legacy messages will be rejected following the point the IF-031 is issued. Reaffirm existing guidance that migration should be timed to avoid any planned work. Unplanned work/change occuring during migration should be communicated using an MHHS IF Message once migration has been completed. | Requirement correction | Migration | Migration | Migration Design Migration Requirement |  | 2023-07-14
MHHS-DIN-209 |  | Design Team | 2023-03-30 | Design Team |  | Sean Cooper | SRO Design Team |  | ~ Level 1/2 Error Code "MSG0000 - Success" Added to Interface Intro Section ~ MSG0018 - Timestamp cannot be future removed and explainatory note added to IF Notes Section of DIP Common |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated actioned in v5.1.1 of IF Doc. This relates to MSG1008 not MSG0018 as originally given in the design issue. MSG0000 Success added. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-210 |  | Design Team | 2023-03-30 | RECCo |  | Sarah Jones | Consultancy |  | Possible change flagged The original view of the Design Team was that this flag and associated info (ie Is a Customer Direct contract in place, who is the DS/MS with that contract, but not the Eff To Date aka Contract End Date) should be visible to incoming Suppliers, for exactly the reasons you suggest i.e. so that in an incoming supplier could factor the existence of a CDC(s) into their acquisition process / pricing etc. I think we also felt that SP’s who weren’t currently appointed, but may have signed a new CDC should also have the ability to set the flag, as it’s the sites that are part of a CDC, but where that SP isn’t the appointed SP that are the most difficult to coral and manage. The position at the moment is that the existence of a CDC would be shared with incoming Suppliers as part of PUB-002, however this would likely be too late in the process to provide the assistance and support required to an incoming supplier (on all aspects of the sale, contract/price in particular) … … therefore, I think it was also envisioned that information about CDC’s would be available via ECS – so prospective suppliers could check in ECS on the CDC position as part of the other pre-acquisition checks they may undertake. Therefore, I think the decision on exactly what information is shared ‘pre-acquisition’ to participants probably sits with yourselves (RECCo) to finalise as part of your ECS Design / DP Assessment. All information in relation to CDC’s will be passed/made available to ECS via receipt of a copy of PUB-039, so what item(s) are displayed and to what parties I think would get covered off as part of that ECS Design activity. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Closed, as per discussions with RECCo that no design changes are required. | No Change |  |  |  |  | 2023-06-16
MHHS-DIN-211 |  | DI-139 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-009 Event Code is referred to as [CSSDeRegistration] in the population notes and swagger open API spec but then B042 block title references event code CSS Deactivation, B042 should reference CSSDeRegistration. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Update B042 to reference CSSDeRegistration | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-212 |  | DI-140 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | MHHSP-BP007-Disconnection-v5.0 is missing IF-050 being sent out on a change to MPAN/RMP Status |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | to BP007 and BPD007 Requires a flow from Registration Service to EES (IF-050 to DIP, a Publish Change to MPAN/RMP Status process, a PUB-050 from DIP to EES process Receive Change to MPAN/RMP status) starting at step 70 (disconnection). Plus add new step descriptions to the BPD and amend Step 70 description to include IF-050. | Process Model correction | Metering Changes |  | MHHSP-BP007-Disconnection, MHHSP-BPD007-Disconnection
MHHS-DIN-213 |  | DI-141 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Data item 997 in S1 common block is senderId in swagger hub, but senderDIPID in data catalogue |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Update swagger to reflect senderDIPID to align to data catalague | Technical corrrection | Technical Artefact | Swagger | JSON,YAML
MHHS-DIN-214 |  | DI-142 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | REG Notes section Queuing of Prospective Appointments Rule 4 ** Rule 4: If App Scenario = 'SEG' and Supplier ID + Appointment Service Start Date = Existing Supplier ID + Service Start Date > (Service Start Date +2 working days) >> Appointments meeting Rule 4 have missed their opportunity, and will be 'Lapsed' (PUB-035) This rule doesn't make logical sense, needs correcting. What is the intended logic to be applied here? |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Update to align with validation rule | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-215 |  | DI-143 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 for event code [MeterRemoval] rule REG1002 Sending Metering Service ID [SO.SenderID] is currently appointed OR held a valid appointment for Meter Installation Date [DI-057] This should read removal date not installation date |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated validation rule REG1002 in IF-005 for event code [MeterRemoval] to refer to Meter Removal Date (DI-058) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-216 |  | DI-144 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-144 On IF-005 MPRS will validate Either current, queued SEG or previous MS If previous and not within 10 working days will reject with REG1003 If not previous, and not current or queued, will reject with REG1027 MPRS will then validate if install date/removal date is within MS period of ownership If not will reject with REG1019 REG1019 need correcting to also include <ETD to apply for previous MS It’s not possible to get a scenario where the If-005 passes the above rules (REG1003, REG1027 AND REG1019) but fails REG1002. Therefore REG1002 is not needed and will never be sent as a rejection code. (Add to DI-43) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Agreed with SCS that no further change is required | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-217 |  | DI-145 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | On IF-005 REG1019 should also include validation that the installation/removal date concerned is <=Effective to date (ETD) of MS period of ownership |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated IF-005 validation rule REG1019 to include validation that the removal/install date must be <=Effective to date (ETD) where the update is being provided by previous Metering Service (using their 10 day window) for MeterRemoval, MeterInstall and MeterExchange events. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-218 |  | DI-146 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 for event codes [MeterExchange] and [MeterRemoval], the rule should not reference DI-056 which is the meter ID in the installation block, it should should referenced DI-053 which is the meterId in the removal block |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Rule updated not to reference DI-056 which is the meter ID in the installation block, it now references DI-053 which is the meterId in the removal block | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-219 |  | DI-147 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 - for other event codes removal date must be >= to Install date but for [MeterUpdate] the rule states > meter install date. Should be >= |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Update rule for [MeterUpdate] to align to other removal date event codes | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-220 |  | DI-148 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1007 unecessary and will never be triggered, it is already covered under REG1001 cannot submit meter install if MPAN is disconnected |  | Closed | [6 empty] | #REF! |  |  | #REF! | Valid rule to left in as-is but noted cannot be SIT tested | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-221 |  | DI-149 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In the IF-005 guide it states: "When amending the Installation and/or Removal date of a Meter, a supporting MAP history commencing in line with the revised Installation Date must also be provided. Any additional MAPs should be provided in chronological order, each with a ‘MAP Effective From Date’ greater, by at least one day, than the previous." MPRS will accept if the install/removal date is changing AND the MAP History has not been included, there is no requirement in Interface Catalogue or Registration Requirements to reject if MAP history is not provided. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Believe covered by MeterHistoryUpdate rules, but hopefully won't be an issue pending agreement on MAP discussion… IF-005 use case guide will be updated with outcome. DRG has agreed to remove MAP history therefore in lieu of this decision, this change will not be required. Closed | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-222 |  | DI-150 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | sarah |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated wording to match existing validation. Guidance only now provided | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-223 |  | DI-151 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005: Need REG1006 to apply to all event codes, e.g. Meter Update on a change to removal date, will need to check that the removal date does not lead to non unique Meter IDs (overlapping dates) MPRS will reject with REG1006 in this scenario |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Added REG1006 validation checks to MeterHistoryUpdate and MeterUpdate events. | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-224 |  | DI-152 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 Interface Note below could be read as MeterUpdate event code can be submitted by previous or prospective MS which is not correct "Only the Appointed Metering Service, and for a small window (10 days) to allow for delayed notification of field activities the previously appointed Metering Service; and an incoming Metering Service with a Prospective 'SEG' type appointment may send an IF-005 and update metering details. The [MeterHistoryUpdate] may only ever be used by the Appointed Metering Service. Interface Design assumes that two separate meters with the same 'Meter ID' cannot be installed at the same time. " |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-225 |  | DI-153 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | DI-849 CSS Registration Request Id does not have a YAML name in the interface catalogue In the swagger hub, the corresponding name is CSSSwitchID which is misspelt |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated Data Catalogue to CSSRegistrationRequestID, Swagger to follow | Data interface correction |  | Interface Catalogue Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-226 |  | DI-154 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In MHHSP-BPD007 - Disconnection v5.0, the ordering of the steps are out of order. Steps 140, 145 and 150 are for parties receiving the de-appointment notification from the Registration Service, but this is not sent until Step 155. Step 155 “De-Appoint Services” needs to be before Step 140 “DS De-appointment Notification”. Also Step 145 “Receive De-Appointment Notification” is DIP receiving the de-appointment notification to send on, this needs to be after Step 155 and before Step 140 . The ordering should be: • De-appoint services (155) • Receive De-Appointment Notification (145) • DS De-Appointment Notification (140) • MS De-Appointment Notification (150) |  | Closed | [6 empty] | #REF! |  |  | #REF! | No plans to change step numbers as long as they are unique | No Change |  |  | BPD007
MHHS-DIN-227 |  | DI-155 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1.xlsb, the validation for REG1003 – “Metering Service ID [S0.SenderID] post appointment update period for MPAN [DI-063] has expired” is currently set to “Metering Service [S0.SenderID] holds valid previous appointment then [System Date] should be < [REG.App End Date] + 10 working days”. Should this be <= to allow for the full 10 days? |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Changed to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-228 |  | DI-156 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 - IF-005 has the following error for [MeterExchange] & [MeterInstall]:- “REG1020 - MAP Effective Date [DI-054] cannot take place in the future” Should this validation also be valid for [MeterUpdate] and [MeterHistoryUpdate]? |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Added to meter update for removal date. Added to MeterUpdate and MeterHistoryUpdate for MAP effective date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-229 |  | DI-157 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 does not have a rule that the SMSO EFD must not be prior to the latest SMSO EFD. We are implementing this rule with error code REG1019 |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | We are implementing this rule with error code REG1019 Make consistent with others ( PC and ssc + 1 ). Review IHD and SMSO | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-230 |  | DI-158 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 & IF-005 do not have a rejection code where the IHD is invalid. |  | Closed | [6 empty] | #REF! |  |  | #REF! | DIP will reject non-valid values - no change to docs required | No Change
MHHS-DIN-231 |  | DI-159 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-005 - There is no validation on Meter Removal date [DI-58]. This should be mandatory non nullable for [MeterRemoval],[MeterExchange],[MeterUpdate], but mandatory nullable for [MeterHistoryUpdate] to allow for reinstating a previously removed meter. Currently in redlined v5.1, this data item is optional and non nullable. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Meter Removal changed to nullable, block conditionality updated | Missing/incorrect validation rule | Metering Changes | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-232 |  | DI-160 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-160 on the interface catalogue DCC Service Flag validation rules are specified in IF-025, but DCC Service Flag is not received in this interface. Needs removing. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | not needed rules removed. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-233 |  | DI-161 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 – IF-025, where the event type is [ConsentGranularity] Error Code - REG1019 - Consent EffectiveFrom Date [DI-018] must be within Suppliers period of ownership Test Condition - Consent Granularity EffectiveFromDate [DI-018} must be < [Reg.CurrentSupplierEndDate] if exists Should this be <= as it could be on the end date? |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-234 |  | DI-162 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Registration Services Requirement MHHS-BR-RS-021 should be amended to: Registration Service must, where more than one Metering Service appointment request is received from the same Supplier for the same MPAN CSS Registration Request ID, and for the same date, take the last received Metering Service appointment (based on the Sender timestamp) as containing the correct information. Any earlier appointments should be lapsed. To allow multiple queued service appointments for the same registration will be overly complex to design, code and test, and is likely to cause confusion and issues in live operation. It is much simpler and cleaner to only allow one queued service appointment at a time, per registration. This would still allow the Supplier to replace a queued appointment that's incorrect. The Supplier could submit further changes once the first change has completed, if there is a genuine case of multiple changes to SP in a short period of time. It would not impact on CoS. Our proposal is to allow one pending queued appointment per registration, so could have a queued appoint on current registration AND queued appointment on CoS registration at the same time. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated MHHS-BR-RS-021 to refer to CSS Registration Request ID. Added REG1089 - Subsequent appointment received as an error code in the interface spec | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-235 |  | DI-63 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Original wording:- In the business process diagram for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 Update required:- Please close this design issue as CSS0700 is the correct reference for update of status. |  | Closed | [6 empty] | #REF! |  |  | #REF! | DUPLICATE OF MHHS-DIN-63 | No Change
MHHS-DIN-236 |  | DI-163 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, 02-DIP-COMMON - R0 response - DI-980 Response Message has been updated in Swaggerhub to be an array, but this is not clarified in Interface Spec. DI-979 Response Code should not be an array. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Added note in Introduction section to confirm that DI-980 can be an array Agreed DI-979 Response Code is not an array | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-237 |  | DI-164 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-034 S0 DI-999 Event Code option of [DSAppSPRepsonse] is misspelt. This is also misspelt in Swaggerhub. This could cause differences between systems and should be corrected to [DSAppSPResponse] |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Updated typo in IF-034 DI-999. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-238 |  | DI-165 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation on MS/DS EFD being within permitted advanced period. This is covered under migration document but not implemented as a validation rule for IF-031. MHHS-DEL961 Migration Design Document section 6.1.1: For the purposes of the CoA Migration process, the below business rules should be followed by Suppliers regarding the lead time between the submission date of the IF-031 and the requested effective from date of the Migration. a. An effective from date from Same Day +1 up to a maximum of 28 calendar days (inclusive of the 28th day) in the future is permissible. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | 28 Day in advance rule added to if-031 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-239 |  | DI-166 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Requirement MHHS-BR-RS-134 states MPRS must automatically de-appoint the MS & DS when the Market Segment Indicator changes to NO. Is this the intended design? |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Removed reference to Market Segment Indicator from the requirement MHHS-BR-RS-134. | Requirement correction | MPAN Ownership | Market Segment | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-240 |  | DI-167 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Current validation on IF-031 Rule REG1037 will mean MPRS will lapse any appointment where the system date is greater than appointment EFD + 2 working days. This means if a SEG change fails, and the supplier tries to resubmit the SEG change, with EFD more than 2 working days in the past, MPRS will immediately lapse the appointment. If there is a need to allow retrospective SEG changes, more than 2 working days after EFD, then the wording will need to be amended to apply to max(EFD+2 working days, MPRS system date on receipt of IF-034 + 2 working days) |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | Introduction of Lapsed Response Codes and Rules in IF-035 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-241 | RS |  | 2023-02-01 | C&C | 3430 | Graham King | Software Provider | Routing rules via the PUB-018 | IF/PUB-018 message with event codes [AddressChg] and [DUOSTariffIDChg]. According to Interface Catalogue routing rules, these events are not communicated to the LDSO role via the PUB-018. We assume that the assumption here is that because these data items are mastered by the LDSO that all internal LDSO systems share this data. This is unlikely to be the case. DUoS billing systems co-exist alongside other LDSO management software and are often supplied by different vendors. They do not and cannot share data sets. Given this real-world separation, would it be possible to make the PUB-018 message available to LDSO in the list of Secondary Routing paths? The alternative would mean developing communication channels between disparate systems, from potentially different software vendors in order to pass information from one to the other. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Closed - Linked to expected LDSO CR26 on DIP Message Optionality - Update as part of wider CR review | No Change |  |  |  |  | 2023-07-14
MHHS-DIN-242 |  |  | 2023-04-04 | ESG | 3713 | Patricia Parker | Software Provider |  | How will the Metering Service be kept informed of who the currently appointed Data Service are? On BP003 is shows the Metering Service being a recipient of the PUB_036 when a DS appointment becomes effective, however looking at the routing rules in DES138 it does not show ‘MSSC’ or ‘MSAC’ as being recipients? |  | Closed | [6 empty] | #REF! |  |  | #REF! | Close - changes to Secondary routing make this DIN Moot - Ref DIN-268 | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-243 |  |  | 2023-04-05 | Change Request | N/A | Sean Cooper | Programme | CR-015 E7/E10 Off Peak Consumption Solution | CR015 - Differential Settlement for E7 / E10 Meters for Smart Opt-out customers | CR015 | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Changes as agreed at DRG and slides circulated. Updated Method 2 and Method 7 within the SDS method statement (METH001). BR-DS-168 & BR-DS-169 added to BRS001. BR-SU-163, BR-SU-164 & BR-SU165 added to BRS004. BP004 text box amended. Creation of x2 New Data Catalogue Items​ OPD Day​ & OPD Proportion​. Changes to IF-024​ Addition of new Event Code [SN-OffPeakDec]​ & Addition of new B-Block BXXX Off-Peak Declaration​ | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue METH001 BRS001 BRS004 BP004 | CR15 | 2023-06-16
MHHS-DIN-244 |  |  | 2023-04-04 | British Gas | 3874 | Neil Strange | Supplier |  | D0275: Until v0.3 of DES196 was released our understanding was that the D0275 would be retained and it’ use was optional. We are feeding this back on the D-025 consultation but don’t want to lose sight of this. Its removal will impact our billing systems and substantially drive up implementation costs. The baselined IF-021 also does not handle the clock change |  | Closed | [6 empty] | #REF! |  |  | #REF! | Alignment with D0275 D0275 is not part of of the baseline design requirements. If you require this, it is by mutual agreement between parties. NO change required, only clarification. | No Change
MHHS-DIN-245 |  |  | 2023-04-01 | Avanade/ Design Team |  | Grant Sutcliffe | Software Provider | Transaction ID and Correlation ID increase field length to 60 | Transaction Id Could the length specification of the TransactionId be increased to be a max length of 60. The need for this is to cater for a 16 character length hex value (increasing from current length of 6 characters]. This would ensure that we achieve uniqueness. It will also provide headroom for any length increase in other Transaction Id constituents, such as Role. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: T-041-1234567890123-SUP-20230220-619C1F6967838002 [Length = 50] Example from DES138 spreadsheet: T-006-1234567890123-SUP-20220401-1234CC [Length = 40] Correlation Id Could CorrelationId length also be increased to 60 max length of 60 - for the same reason. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: CI-BP-011-20230222-619E0BD1D1FD9000 [Length = 35] Example from DES138 spreadsheet: CI-BP-011-20230222-1234567890123 [Length = 32] |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated DIP Transaction ID and DIP Correlation ID to String 60 in Interim Release 1. The examples have been updated to reflected MHHSP-DES138-Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-246 |  |  | 2023-04-12 | Change Request |  |  | DCUSA | CR-019 Replacement of D0242 D0315 for MHHS | CR019 - Replacement of D0242 D0315 for MHHS | CR019 | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors) and receivers (suppliers) of the flows has identified the desired flow content and now wish to bring this back to the program to ensure that it can be delivered in readiness for migration. REP-900 and REP-901 added to reporting catalogue. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the supercustomer data from settlement (REP-002/002A). There will be removal of certain data items used in the current process and addition of new data items, making population of the D0242 ‘Supercustomer DUoS Daily Statement’/D0315 ‘Embedded Network Supercustomer DUoS Daily Statement’ impossible in their current format for migrated customers. The “MHHS Design: Reporting and Transition Sub Group” identified the need for a new DIP flow to replace the D0242/D0315 last summer but noted that these flows are under DCUSA ownership and so passed the development of the flow content to DCUSA. More information including the proposed Interface can be found on the collaboration base under CR019 This also addresses CR27/DIN511 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-ERI011B External Reports |  | 2023-07-14
MHHS-DIN-247 |  | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Update to the Core Design Interface Catalogue (MHHSP-DES138) is required to include the addition of IF-003 |  | Closed | [6 empty] | #REF! |  |  | #REF! | Closed captured under DIN-434 as part of migration update review IF-003 defined as part of Migration baseline The structure of the IF-003 will be updated to include ‘Incoming Supplier Details.’ The two new data items within the ‘Incoming Supplier Details’ will be: RevMig Incoming Supplier MPID RevMig Incoming Supplier Effective From Date Business Rules: In the case of Smart Meters undergoing Reverse Migration only, the Registration Service will populate the ‘Incoming Supplier Details’ as part of the IF-003 which is sent to the outgoing MS (via the DIP). This is so the outgoing MS can correctly route the Skeleton D0150 to the new Supplier (which in turn enables the new Supplier to generate a D0367). If the D0205 is not sent to the Registration Service before the IF-003 is issued, the data fields used to confirm the identity of the DC and MOP will be blank; no default values will be populated. In this case, the DC and MOP will need to contact the Supplier to initiate a manual transfer of data. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue |  | 2023-07-14
MHHS-DIN-248 |  | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Updates to the ISD Entities document (EDI021, v5.0) |  | Closed | [6 empty] | #REF! |  |  | #REF! | To be picked up as part of Migration IA - - new DIN will be raised as required. |  |  |  | EDI021 |  | 2023-07-14
MHHS-DIN-249 |  | Migration Design | 2023-03-27 | Migration Design |  | Matthew Breen | Programme |  | Discussion around the use of BST/UTC during Migration |  | Closed | [6 empty] | #REF! |  |  | #REF! | DIN is not specific enough. | [5 empty] | 2023-07-14
MHHS-DIN-250 |  |  | 2023-04-06 | Design Team | 3764 | Steve Weston | Programme | Participant ID 10 digit number | This is related to ticket 3764, to update the Interface Specification to ensure the Participant ID is clearly defined as a 10 digit number [0-9] only, and the examples in the Interface Specification align to this, including where this is used as part of the sender unique reference and the examples shows 11 digits, not 10 digits for Participant ID. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | In E2E001 doc Section 4.2.3.2 Section 4.4.4.2 example code for Sender unique Ref and in Transaction ID Section 4.5.5.3 as above DES138 doc Data Catalogue tab: DI-990 example and DI995 Example DIP common tabl DI995 example and the example JSON block (the above easy to change) ALL the IF tabs the JSON block example the Sender Unique Ref contains Participant ID and in every example its longer than 10. JSON/YAML Files: Update JSON examples where Sender Unique Ref and Transaction ID contain a Participant ID example longer than 10. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 Solution Architecture MHHSP-DES138-Interface Catalogue JSON/YAML files |  | 2023-06-16
MHHS-DIN-251 |  |  | 2023-04-06 | Design Team | 3860 | Steve Weston | Programme | IF-041 Population | This is related to ticket 3860, to update the Interface Specification to provide more clarity / notes on the optionality of B064 and B065 blocks in the IF-041 interface. This is in relation to notes / detail about which blocks are mandatory (from a contractual perspective) versus what should be included in the message if the data exists. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updates the notes section of IF-041 in order to provide guidance on the minimum population of B064/B065 blocks. This clarifies "When exchanging readings between parties the design assumes that in the most part this will be the Cumulative Register Reading (Block B064). However, at participants request this message also allows for the exchange of Configurable Register Readings (B065) either alongside a Cumulative Reading or in isolation. For the avoidance of doubt the message must contain at least one B064 record and /or one (or more) B065 records [depending on the number of configurable registers], in order to be considered valid. " | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-252 |  |  | 2023-04-06 | Centrica | 3661 | Neil Strange |  |  | We believe there is a Design Gap at Change of Agent and Change of Supplier for Smart Meters which also impacts Migration. Neither the Registration Service, Metering Service nor Data Service will know how the registers are set up and specifically which are active. Consequently the Data Service will not know which registers to send on the IF-041, nor will there be able to calculate consumption correctly without knowing the register set up. The interface catalogue for IF-041 states in respect to this “B065 Block Below Repeated for each set of Configured Register(s) for each Meter” – we do not believe there is a way to give the DS this information. The supplier will set up the smart meter configuration to enable the registers to capture the usage for certain time periods. There is currently no way for the supplier to inform the DS which registers are active at what time of the day - the DS cannot accurately calculate the consumption breakdown based on the reads when there are multiple registers configured. |  | Closed | [6 empty] | #REF! |  |  | #REF! | DIN closed, Design Team to send email recommending for a CR to be raised. | [5 empty] | 2023-07-14
MHHS-DIN-253 |  |  | 2023-04-12 | British Gas | 3769 | David Hipwell | Large Supplier | Volumetrics | The latest E2E Functional and Non-Functional Requirements MHHS-E2E Requirements V3 which went to V3 on 16/02/2023 appears to focus on message counts and response times. For example:- During transition all meter points (ca. 31M) will be transition between the old and new services. Therefore assuming a linear migration over the year this would result in the load below, hence services shall be capable of processing the following volumes: - average daily volume of 680,000 - peak daily volume of 2.4M 5.0M - annual volume of 248M 500M Analysis of the flows needs to be categorised across all impacted market participant roles including the DIP. Only then will it have meaning for all parties. The calculation needs to take account of the migration period using the MHHS migration volumes according to date (including REVERSE migration). These should be in both message counts and also sizing (e.g. Gb). And include for a BAU day and also migration days. Whilst some calculations can use the total number of MPANs, to be useful these need show also at perhaps for a million MPANs in each role. Only then will all parties be working on a single set of figures. A line in the sand. The NFRs that exist appear to have moved away from any form of technical calculation towards business process figures. But these figures need to go as an input into technical sizing’s, and should have done for DIP – can these be produced and published ? |  | closed | No |  | Clarification - No change required | DIP Users | 2023-09-13 |  | #REF! | 2023-09-13 |  | #REF! | Closed - NFR volumes have been agreed following implementation of CR054 | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E004 E2E Architecture - Transaction Volumes
MHHS-DIN-254 |  |  | 2023-04-17 | Siemens | 3044 | Tony Mason | Metering Service | Update of Consent, DPI, etc. | this does surprise me and doesn’t seem to correspond to the routing rules in the Interface Specification. A proposed Data Service is not included in the routing tables for the receipt of a PUB-018, for example. I would therefore expect that if a change to DPI occurs between PUB-033 and PUB-036 the proposed Data Service could only be notified on a revised PUB-033 with the Appointment Scenario set to whatever the original scenario was set to – “SEG”, “CSP”, or “COS”. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Ref notes on the maintenance of these data items in the Regi Info Section of the I/F document. Prospective SPs are not notified of changes to these data items during their prospective period. If these Data items change then the supplier should re-evaluate the SP they have proposed and change the appointments as required. If an SP takes on a supply with different elements/factors to those suggested by the supplier at appointment this is a contractual issue between the SP and the Supplier. | [5 empty] | 2023-06-16
MHHS-DIN-255 |  |  | 2023-04-17 | Elexon | 3983 | Kate Goodman | Testing | Consumption on De-Energised MPAN (IF-013/IF-014) | ConsumptionOnDeEnergised is an Event Code mentioned in the list of data items but is not present in header where the routing info is held - needs to be added to header |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | ConsumptiononDeEnergised event moved from IF-013 to IF-014 and added in routing rules. See also DIN332 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-256 |  |  | 2023-04-17 | Elexon | 4169 | Kate Goodman | Testing | IF-014 Block B067 | DI-015 is mentioned in the header wrt routing but is not present in the message itself. It either needs to be removed from header or added into message. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Block B067 added to IF-014 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-257 |  |  | 2023-04-17 | Elexon | 4172 | Kate Goodman | Testing | B053 repeating block | B051 is a block which repeats for each combination of Load Shape Criteria (denoted with single chevron to show repeat). B053 is another repeating block which is denoted by two chevrons, implying it is nested below B051. But in fact it also repeats for each combination of Load Shape Criteria. Should this just have a single chevron or is there further information that needs to be added to make its double chevron make sense? |  | Closed | [6 empty] | #REF! |  |  | #REF! | No change required as there will be multiple B053 in each B051 block. | No Change |  |  | none
MHHS-DIN-258 |  |  | 2023-04-19 | ENWL |  | Paul Band | Network Operator | LDSO use of DIP vs internal for Specific messages | There are a number of requirements in the MHHS-BRS005-LDSO document which state that we must obtain various registration data via the DIP and maintain records accordingly such as: MHHS-BR-LD-001-005, MHHS-BR-LD-024, MHHS-BR-LD-030 and MHHS-BR-LD-034 Extrapolating these into requirements for our own systems suggests that we should build databases/tables to store this data and maintain it The requirement is placed upon us as a party under the assertion that all settlement related data should be exchanged between services and parties via the DIP. However LDSO’s are unique in that their data exchange for their party type is split and is typically split by system under these party types. As a consequence we already communicate directly with MPRS as it is already part of our system architecture as a paid for and created service by LDSO’s. |  | Closed | [6 empty] | #REF! |  |  | #REF! | CR26 has been raised to covere this LDSOs have been advised to raise a Programme Change Request. Discussion at the DRG of the 27/4/23 did not agree on the development of a New Design Principle, A further workshop with LDSOs needs to take place to discuss alternate options and confirm agreement amoungst all DNOs & IDNO on the receipt of publication | [5 empty] | 2023-07-14
MHHS-DIN-259 |  |  | 2023-04-20 | ESG | 3756 | Patricia Parker | Software Provider | BP003C correction | On BP003C under the CoR section there is a note which states that the readings that pass validation should have Meter Reading Status (J0047) set to ‘T’ and when it has failed set it to ‘F’. However as per the REC the group which houses the J0047 group (032 – screenshot below) should only be present where the Meter Reading Flag (J0045) is set to ‘F’. I have checked DES196 and cannot see that the conditionality for that group is changing in the D0010 therefore I can only assume that the note on the process map is incorrect, and it should be talking about the J0045 value instead. Please can you confirm? |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Modification to Note on process to refer to "Meter Reading Flag (J0045)", modify flow label to step230 to "(Read Flag = "T")" Modification to the process note to advise the J0047 would not be present if the meter reading flag (J0045) is set to "T". It will only be present in case the J0045 is set to "F". | Process Model correction | Metering Changes |  | MHHSP-BP003C-Transfer of Reads |  | 2023-06-16
MHHS-DIN-260 |  |  | 2023-04-20 | CGI | 4167 | Dave Webster | Software Provider |  | Swagger definition does not match DES-138 in version 1.0 or 1.1. |  | Closed | [6 empty] | #REF! |  |  | #REF! | No specific detail provided, however comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1, therefore closed
MHHS-DIN-261 |  |  | 2023-04-20 | Utiliteam | 4245 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. Configurable Register Reading Date/Time is missing. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue JSON/YAML Files |  | 2023-06-16
MHHS-DIN-262 |  |  | 2023-04-20 | Utiliteam | 4214 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. B070 for IF-031 is wrong. It contains the word DIP in the Swagger, which is not included in DES-138. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files |  | 2023-06-16
MHHS-DIN-263 |  |  | 2023-04-21 | CGI | 4203 | Dave Webster | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. DI-122-Profile-Class is defined as an integer, but in DES138 it is defined as a string length 2. Needs to be updated in the Swagger. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Swagger and Data Catalogue aligned to String 2 for DI-122 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files |  | 2023-06-16
MHHS-DIN-264 |  |  | 2023-04-24 | Elexon | 3946 | Rashmi Radhakrishnan | Central Body | Update to CCC Method Statement | One of my colleague pointed out a typo in the CCC method statement attached, and I would like to draw your attention to it and requesting to make necessary amendments. The CCCID starting from 100 to 107 has Market Segment Indicator as “U” and Connection Type Indicator shown as “W”. We think that, for these line items the Connection Type Indictor need be corrected to “U”. For reference please see below picture and this also aligns with ISD entity spec v5.0 (M2 entity). CCC ID Market Segment Indicator Measurement Quantity Consumption Component Indicator Connection Type Indicator 100 U AI C W 101 U AI L W 102 U AE C W 103 U AE L W 104 U AI C W 105 U AI L W 106 U AE C W 107 U AE L W All 'W's' should be 'U's') |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Method Statements (MDS & VAS) will be updated for "W" to be replaced by "U"within ISD Table - MHHS Consumption Component Class. Please note: ISD entity M5 file has already been updated to reflect the fact that unmetered supplies have a connection type of "U". | Design Ambiguous | Supporting Docs | Method Statement | MDS Method Statement VAS Method Statement |  | 2023-07-14
MHHS-DIN-265 |  |  | 2023-04-25 | Elexon | 4128 | Rashmi Radhakrishnan | Central Body | Validity of Settlement Period quality indicator data set | ISD entity M5 has a filed Settlement Period quality indicator. Is this the complete valid data set for the field Settlement Period quality indicator? I took this below list from interface catalogue v5.0. A = Actual, E= Estimate (UMS Only) A1,A2,A3, AAE1,AAE2,AAE3,EAE1,EAE2,EAE3 (ADV Only) E0 --> E9 = Estimation Method 1 - 9 ZE = De-Energised ZE1--> ZE3 = Zero Estimation Method 1 -3 but the Advanced Data Service Estimation Method Statement has data flags EA1 till EA13 which is not mentioned in the above list. Also, the ISD entity spec M5 example below shows a different data item that is not in the list at all for Unmetered(104 &105). Is this a mistake? |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Interface document updated with the full list of settlement period quality indicators for ADS and swagger updated accordingly. within DES138. 02-IF-016/14 and in the data cat. DI-083 "EA1-->EA13 = ADS Estimation Methods" added. | Design Ambiguous | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  | 2023-07-14
MHHS-DIN-266 |  |  | 2023-04-26 | ESG | 3899/ 925 | Patricia Parker | Software Provider |  | If the D0300 process is not changing then we believe that DES196 is incorrect and should show added routes to allow the Supplier to send a D0300 to the Data Service Matt M has confirmed - We are working through the exchange of CoS readings as the code drafting has raised some questions about the extent to which the SDS is involved in the D0300 process. For smart meters, the SDS will not have any use for the billing register readings so D0300 process should not apply, or at most could only be missing the total cumulative. However, it likely will still be required for traditional meters. On that basis, I think we can acknowledge that the D0300 will be retained and SVs created for Supplier to SDS for traditional meters. The process for smart meters is being discussed internally as the SDS does not retrieve tariff register readings. There will be an updated version of DES196 issued in the next few weeks to reflect feedback from the DTN flow part 2 consultation issued in late March which will reflect the retention of the D0300. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Email comms sent to Patricia confirming the D0300 is a Supplier to Supplier flow. Therefore should there be a need to send readings to the DS, this would be done via a D0010/IF-041 with the correct data flags set in both. Based on this there is no requirement to send D0300 to the DS. Matt M confirmed when finalising DES196 he confirmed this in his comment response to ESG. The MSAG Consequential Change - Switch Meter Read Exceptions v1.0 22.06.23 provides a more comprehensive explanation of the MSAG conclusions. No change required to DES196 | Design Ambiguous | Supporting Docs | Method Statement | MHHSP-DES196- D-Flow and Interface Mapping |  | 2023-07-14
MHHS-DIN-267 |  |  | 2023-05-02 | ESG | 4385 | Patricia Parker | Software Provider | RegX Validation Issue | RegExpression on the DI-148-Annual-Consumption use of DT-016-Decimal-9-3 in the 1.1 swagger spec. This needs to be updated to align with DES-138 example of 123456789.123. Regex should be ^-?[0-9]\d{8}(\.\d{3})?$ instead of ^-?[0-9]\d{7}(\.\d{3})?$ |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Swagger v1.2 has been updated accordingly | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files |  | 2023-06-16
MHHS-DIN-268 |  |  | 2023-05-03 | SRO Design |  | Sean Cooper | SI Design | Secondary Routing | It was always the intention to revisit and revise all of the Secondary Routing configuration as part of DIP Detailed Design. Completion of this exercise has also resulted in some changes to other routing parameters. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Following discussion with Avanade the Secondary routing short codes have been simplified and the routing of each IF revisited based on these revised short codes. These are shown highlighted in BLUE in the routing section of each of the individual IF pages. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-269 |  |  | 2023-05-03 | St Clements | 4424 | Anna Davis | Software Provider | Swagger Alignment to DES-138 | We have also realised that there are a large number of discrepancies for each interface between the data item name in Swagger vs the YAML name in the Interface Catalogue Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated inconsistencies in the Interface 01-Data Catalogue and Swagger. Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-270 |  |  | 2023-05-05 | SRO Design | 4557 | Rob Golding | SI Design | Correlation ID | Provide further clarity on how Correlation ID's work. This will impact numerous artefacts including DES-138 and E2E001 |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | DES-138 Interfaces updated to reflect correct 'COPY' property on IF routing tables. updated IF-008, 16, 20, 26, 28, 37, 39 and 50 for this DIN. Added *New to IF-020 showing a new correlation ID is needed to be created for these events, others events needed a COPY of the correlation ID. IF-050 had “No” added to show that a Correlation ID is not required. Updated the E2E001 design document with a more detailed worked example in section 5.4 that details how and where the Correlation ID is populated. | Design Ambiguous | Supporting Docs |  | MHHSP-DES138-Interface Catalogue. E2E001. |  | 2023-06-16
MHHS-DIN-271 |  |  | 2023-05-10 | ESG | 4541 | Patricia Parker | Software Provider | Swagger Alignment to DES-138 | S0 and S1 is Mandatory in DES-138 v5.1.1, but is not marked as mandatory in the Swagger 1.1. Swagger needs to be updated to align with DES-138. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Swagger 1.2 updated so all SO and S1 blocks are mandatory as per DES-138 | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-272 |  |  | 2023-05-10 | SRO Design | 4656 | Rob Golding | SI Design |  | Required to DIP Channel Publication (v1.2 of the swagger) that will allow DCPs to register webhooks on behalf of their clients |  | Closed | [6 empty] | #REF! |  |  | #REF! | Duplicate of DIN-375
MHHS-DIN-273 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | New MSN Data Type | MHHS Data Type (DT-029) - for Meter ID / Serial number for DI-053, DI-056 and DI-060 added to DES138 01-Data Catalogue, Swagger updated. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | New Data Type created in Swagger v1.2 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-274 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | Missing YAML in DES-138 - DI-073, DI-074, DI-080, DI-111, DI-112, DI-190-194, DI-300, DI-021, DI-022, DI-060, DI-076 |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Missing YAML names for Data Items confirmed and added to 01 - Data Catalogue Note:All DI's upsated except DI-076 has not required a changed. Other DI chnages not listed are picked up as part of DIN261 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-275 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | DI-093 / DI-120 - Data length 2,000 not 200. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | All additional info data items set to len 2000 in Swagger v1.2, DES138 DI-093/120 length updated in 01-Data Catalogue | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-276 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Classifications | MHHS Data Classification - ensure all columns are populated for Public and Restricted ie, MPAN & Address (removall all NULLS). |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Data Classifications added in v5.2.1 where previously there was no entry ( Column I in the Data Catalogue ) | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-277 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Owners in Data Catalouge | MHHS Data Owner - where there are NULL's, this should be updated so all columns provide an owner, mark as N/A (remove all NULLS). |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Metering Service added as Authoritative Source and MHHS Owner in v5.2.1 of DES138 Data Catalogue for DI-190 to DI-195. Previously there was no entry. | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-278 |  |  | 2023-05-10 | Design Team | 4590 | Rob Golding | Programme Design | Addition of indicator for each IF within DES138 | Please can DES138 Interfaces spreadsheet be updated to provide an indicator against each interface (or is it interface & event code) as to whether it can be opted in/out by a recipient. | CR029 | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Design Team to add optionality matrix to DES138. Name of worksheet: 04_IF_Optout_Matrix | Design Ambiguous | Supporting Docs |  | DES138 Data interface specification |  | 2023-07-14
MHHS-DIN-279 |  |  | 2023-05-12 | ESG | 4484 | Patricia Parker | Software Provider | Event Code clarifiction for DS when sending back validated customer read on PUB-041 | The BP005 – Data Processing – Process map shows that when a Customer Own Read has been sent to the Data Service from the Supplier in the IF-041, EventCode = ReadingCoR, the Data Service will perform reading validation and issue the PUB-041 back to the Supplier, in the Read Sharing column of the process map. When the Data Service send back the validated customer own read in the PUB-041, what eventcode will they use and where can I find this documented? The previous response says “There is no IF-041 response, check consumption is as expected in PUB-021” is this correct for Customer Own Reads on Smart meters? The map shows otherwise so please can you confirm if the answer or map is correct and if the map is correct, provide information on what event code will be used. |  | Closed | [6 empty] | #REF! |  |  | #REF! | This is a query not a DIN. Previous response provided is correct .... There is no IF-041 response, check consumption is as expected in PUB-021” | [5 empty] | 2023-07-14
MHHS-DIN-280 |  |  | 2023-05-12 | ESG | 4552 | Patricia Parker | Software Provider |  | DES196 lists the D0386 (Manage Metering Points) as ‘not impacted’ owned by the REC however BP010 shows that the method of maintaining Related MPANs is via the IF_019 / PUB_020 process. Can you confirm whether the D0386 is going to be removed post- MHHS. If not, could you please clarify what process a Supplier should follow post- MHHS. |  | Closed | [6 empty] | #REF! |  |  | #REF! | D0386 will not be used post migration to MHHS Regime. Management of MPAN relationships will be under taken using IF-019/IF-020 | [5 empty] | 2023-07-14
MHHS-DIN-281 |  | DI-172 | 2023-05-12 | St Clements | 4446 | Madison Layton | Software Provider | BP003 IF-35 flow | MHHS-BR-RS-053 for the incumbent MS to be notified on If-035 DSAppAccepted where meter is advanced or traditional is missing from BP003 business process diagram and steps. Also updates to BP003 and BPD003 forward migration for consistency |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | IF-35 flow from step 85 (if accepted where meter is advanced or traditional to Meter Service (incumbent) and additional step 86 to receive appointment response to BP003, and added step 86 and BR-RS-053 ref and details to step 85 to the BPD003 | Process Model correction | Metering Changes |  | MHHSP-BP003-Change of Service - Data Service, BPD003 Forward Migration BP003 and BPD |  | 2023-06-16
MHHS-DIN-282 |  |  | 2023-05-16 | SIMS | 4821 | Martin Freeman | Software Provider | Status code removal | Status Code is included in the E2E001 design response body (4.4.4.2), when this is HTTP Response code and should be removed as this is defined in the callback response. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Removed from section 4.4.4.2 from the E2E001 design document as this is not required. This now aligns in Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture |  | 2023-06-16
MHHS-DIN-283 |  |  | 2023-05-16 | SIMS | 4826 | Martin Freeman | Software Provider | ID Capitalisation | ID should be capitalised in all places in the Swagger. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | All JSON names now have capitalised ID fields for Swagger 1.2. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-284 |  |  | 2023-05-16 | SIMS | 4828 | Martin Freeman | Software Provider | HTTP Response Code | HTTP Response code for success should be 201 in E2E001 as per Swagger. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Update made to E2E001 design document in section 4.4.4.1, 4.5.5.1 and 5.3 to align with Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture |  | 2023-06-16
MHHS-DIN-285 |  |  | 2023-05-16 | Elexon |  | Rob Golding | SRO Design Team |  | Add replay / requeue API for Swagger 1.2 to align with existing E2E001 Design. Add additional information / clarity in the E2E001 for Interim Release 2 to align changes between design and Swagger. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Duplicate of DIN-374
MHHS-DIN-286 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Issue clarification to Participants through DRG that all ECS Reports will be issues via Pattern B. Update of ECS Report Catalouge to reflect this. |  | Closed | [6 empty] | #REF! |  |  | #REF! | The ECS reports will be via Pattern A. No change is required to the ECS reports
MHHS-DIN-287 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team | Guidance notes for distribution of ECS reports | Create & Issue guidance document on the distribution of ECS Reports. To Contain : - overview of Pattern B Process - Guidance on population of IF-047 - Update of IF-047 Event Codes |  | Closed | [6 empty] | #REF! |  |  | #REF! | No longer required as pattern B will not be implemented for ECS reports | [5 empty] | 2023-07-14
MHHS-DIN-288 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Update of Swagger with ECS Reporting Structures |  | Closed | [6 empty] | #REF! |  |  | #REF! | These interfaces are in place from Swagger 1.1. | [5 empty] | 2023-06-16
MHHS-DIN-289 |  |  | 2023-05-17 | SRO Design Team | 4994 | Rob Golding | SRO Design Team | Interfaces for consumption replay | IF-015 / IF-016 - updates to E2E001 to provide clarification on design pattern. Alignments between DES-138 & Swagger alongside this. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | E2E001 design updated (Section 5.1.7) to provide additional information / clarity on these interfaces in relation to Consumption Replay. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture |  | 2023-06-16
MHHS-DIN-290 |  |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Proposal to change all / subset of ECS Reports to Pattern B |  | Closed | [6 empty] | #REF! |  |  | #REF! | Duplicate | No Change
MHHS-DIN-291 |  |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | As a result of DIN-290 -- Where should the reporting assets be hosted?? DIP solution specified, but what are the other options are availible. Final solution option to be ratified and documentation updated. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Not hosted as via Pattern A | No Change
MHHS-DIN-292 |  |  | 2023-05-17 | St Clements |  | Madison Layton | Software Provider | ISD Entity M17 | Change required to ISD Entity M17 to add in Market Segment into the table - otherwise it cannot be used to derive consent values which was its original purposes |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | 1. Update Table name to "Consent Granularity Valid Combinations" 2. Added Market Segment as new table column 3. Update table to show all valid combinations | Process Model correction | Supporting Docs |  | MHHSP_EDI021_ISD_Entities |  | 2023-06-16
MHHS-DIN-293 |  |  | 2023-05-17 | Design Team |  | Paul Petitt | SRO Design Team |  | Retrospective DIN raised to ensure that any changes that are made in multiple downstream documents (for example CoCo, DIP Logical Design, DIP Physical Design & DIP Security Design) are reflected / updated in LDP assured documents to ensure e2e design / requirements alignment. This was agreed in a DRG Meeting in March 2023. |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! | design changes to E2E001 End-to-End Solution covering points described in DIN details | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-294 |  |  | 2023-05-19 | ESG | 5030 | Luke Speakes | Software Provider | BP007 PUB009 flow | What I need to know is if the supplier will receive a PUB_009 with the Event code of [CSSDeRegistration] because nowhere on the BP007 process map does it show the supplier receiving the PUB_009 following a deactivation but on DES138 it shows the supplier as being a recipient of this event code. Step 95 (ringed below) shows the supplier as receiving the PUB_009 off the back of the Disconnection (event code [MPANDisconnection]) but then no where else on the process map does it have the supplier receiving a subsequent PUB_009 following the successful deactivation. Additional step required from step 130 (maybe 137?) to show both PUB-009 Mpan Disconnection and PUB-009 Deactivation going to supplier |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | BP007 change : There is already a flow from Step 85 to Step 95 for PUB009 for disconnection (no change) But need to Add a new step (137) for Receive Deactivation in Supplier lane from Step 130 for PUB-009 MPan deactivation in BP007 And there is already a PUB-037 flow from step 145 to Supplier step 157 for confirmation (so no change there) Addition of step 137 to BPD007 | Process Model correction | Metering Changes | Disconnection | MHHSP-BP007-Disconnection, BPD007 |  | 2023-06-16
MHHS-DIN-295 |  |  | 2023-05-19 | SIMS | 4821 | Martin Freeman | Software Provider | L1/L2 Error Codes | Error code detail updates in DES-138 for Level 1 and Level 2 validation needs to be clarified |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updates made to Introduction Tab of DES138 in order to clarify Lev1 vs Lev2 error codes. Design is such that participants should expect error code(s) at either level. Further ammendments could be made following Avanade clarifications. | Data interface correction | Supporting Docs |  | DES138 Data interface Definition |  | 2023-06-16
MHHS-DIN-296 |  |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | It is envisioned that Configuration Management of ISD will largely follow the existing customs, practices and processes as are currently in place for managing MDD changes. However, DIN is required to formally confirm the Owner(s) and allowable update mechanisms (Standard or FastTrack) for each of the new ISD Entities outlined in the DIN. |  | Closed | [6 empty] | #REF! |  |  | #REF! | This is a Code Drafting issue not a Design / DIN issue. Code drafting team will be covering ISD maintenance processes | [5 empty] | 2023-07-14
MHHS-DIN-297 |  |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | What Participants are recognised in the existing / new ISD Participant tables…. How does this link in with the parties recognised by the DIP (and assigned DIP Roles / IDs …. Or Not) …. In particular how are MDRs referenced in ISD? Does this reference need to identify the ‘type’ of MDR? Also, there is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 |  | Closed | [6 empty] | #REF! |  |  | #REF! | These issues are covered in Release 3 updates (DIN372 & DIN 070) . ISD updated to confirm participants recorded in M16, a new table M18 "DIP Participant Roles" was added. | [5 empty] | 2023-07-14
MHHS-DIN-298 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Update to UMSDS method statement. | As I understand it, you are advising we should A flag the consumption data (even though it isn’t Actual), until the zero charge code D0388 UMS Inventory is received from the UMSO. Therefore - if we have an inventory, regardless of the energisation status of the MPAN, we always use an A Flag. But as you’ve stated, this means an IF-013 will be issued to us as UMSDS, because there is A data, against a De-Energised MPAN. If this is the design/requirement then it is understood – but I would like to call out that this should be detailed within the UMSDS method statement – so I think a DIN is needed to get this requirement added? |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement |  | 2023-07-14
MHHS-DIN-299 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | IF-013 update to include UMSO recipient | Further to this (DIN-298), the cause of this IF-013 being issued can only be that the UMSO has not provided the UMSDS with the correct D0388 UMS Inventory to use. Therefore – the UMSO has a requirement to receive the IF-013 to tell them this. However, the Interface Catalogue has not designed that this will get sent to the UMSO. I think this is a Design Issue too, and also needs a DIN raising so that the IF-013 is provided to the UMSO. |  | Closed | [6 empty] | #REF! |  |  | #REF! | No this is incorrect. UMSO is not involved with Consumption. If IF-021 submission is rejected this is an issue for the DS (incl. UMSDS) to address and Manage. Any issues regarding the metering onsite/energisation status need to be managed by the DS (incl UMSDS) with their appointing Supplier and Partner Metering Service. |  |  |  | DES138 |  | 2023-07-14
MHHS-DIN-300 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | You are advising a Load Shape will always require the E Flag. But as you say if the MPAN is de-energised, that MDS will reject the IF-021. Is this therefore your answer – that MDS will reject the IF-021, and there is nothing that can be done about that, so we just need to accept we will get those rejections? If so, this isn’t really a satisfactory process, to know rejections will be received in this scenario. Can you just confirm that the solution here is we just need to accept we will get these rejections to the IF-021, which we will then simply ignore? If that is the case – again a DIN needs to be raised to write this into the Design so the process is documented. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. See DIN 506 which has updated DES138 to show that IF-014 also contains warnings for MPANs with consumption on de-energised sites. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement |  | 2023-07-14
MHHS-DIN-301 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | the corrective action on this scenario (DIN-300) occurring will be if/when the UMSO provides the UMSDS with a D0388 UMS Inventory – then the UMSDS will stop using and submitting the Load Shape data. There does not seem to be a mechanism in the Design for the UMSO to be made aware of this issue that would be of their making, so again needs raising as a DIN please. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. See DIN 506 which has updated DES138 to show that IF-014 also contains warnings for MPANs on de-energised sites. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement |  | 2023-07-14
MHHS-DIN-302 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | I’ve pulled together the below table. This covers all the possible scenarios of the UMSDS either having or not having the D0388 UMS Inventory. Combined with whether that D0388 UMS Inventory has load associated data within it. Also combined with whether the MPAN is Energised or De-Energised. Here I’ve listed which Settlement Period Quality Indicator should be used, and where applicable, which Estimation Reason Code should be used. Should this be included in the UMSDS Method Statement and if so, are you happy with the below. In Green are steps we understand. In Red, these remain Unknown to us based on the Design and your answers given. In Orange, these are answered based on your guidance on your email of 28 April – but are not specified in the written Design. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement |  | 2023-07-14
MHHS-DIN-303 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.2.3 - Changes to Data formatting to align with Swagger / DES-138 |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! |  | Technical corrrection | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-304 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.4.3 - Case Sensitivity - additional information added to provide clarity on approach |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! |  | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-305 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 5.1.7 - Additional Detail required for IF-47 / ISD to provide clarity on approach / steps |  | Implemented | [5 empty] | Interim Release 1 | #REF! |  | Interim Release 1 | #REF! |  | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-306 |  |  | 2023-05-22 | Tym Huckin | 3992 | Tym Huckin | Consultancy | Clarification/examples for DI-101 for BST/UTC cross over period | Further clarity / worked examples for UTC Settlement Date (DI-101) for BST / UTC cross over period. |  | Closed | [6 empty] | #REF! |  |  | #REF! | This is not a design change it is a Question/Clarification . | [5 empty] | 2023-07-14
MHHS-DIN-307 |  |  | 2023-05-22 | CGI | 5042 | Dave Webster | Software Provider |  | Status code incorrectly included in required, although not in Standard Response Body Type. This is in Swagger 1.2. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Duplicate of DIN-282
MHHS-DIN-308 |  |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | S0 Block required property | Add required property to all the S0 blocks in the interface definition |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Update made to Swagger for all Interfaces to mark 3 fields in the S0 block as mandatory. | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-309 |  |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | Swagger Alignment to DES-138 | Define Transaction ID (DI-990) with no Min Length to align with DES-138. This is DT-014. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Update made to Swagger to align with DES-138 (DIP Transaction ID min length removed) | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-310 |  |  | 2023-05-23 | ELEXON | 5173 | Rob Golding | Central Body | Guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 | Guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 are to be applied (if at all), i.e. does the DIP need to consider the effective period and only accept messages on the production system when the message falls within this period? And if so what date within the message should be used as a check? Or the physical date/time of message receipt? Or doesn’t the DIP need to consider these dates at all and no check needs to be applied? |  | Closed | [6 empty] | #REF! |  |  | #REF! | This has been included in the DIP onboarding design. | [5 empty] | 2023-07-14
MHHS-DIN-311 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-985 / DI987 both String 60. Swagger Min and Max Lengths aligned |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updates made to DES-138 for Length alignment to 60. Updates to Swagger to remove min length for DI-985 and DI-987. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-312 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-984 / DT-009 needs to be updated to be min 3 / max 5 length. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Sender Role - change on 01 Data Catalogue DI-984 as per description | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface |  | 2023-06-16
MHHS-DIN-313 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S1 - Sender Timestamp updated correctly (from sent timestamp) in Swagger to align with DES-138 |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Update made to Swagger to align with DES-138 (renamed to Sender Timestamp) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-314 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - Publication ID Min Length updated in Swagger 1.2 to be 6 to align with DES-138 (rather than 7) |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Update made to Swagger to align with DES-138 (Publication ID Min Length now 7, not 6) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-315 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - DIP Correlation ID should have no min length to align with DES-138 (rather than min length of 1) |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Update made to Swagger to align with DES-138 (DIP Correlation ID has no min length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-316 |  |  | 2023-05-25 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, all DT-006 and DT-006N should have min length 10 & max length 10 to be consistent. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated DES-138 01-Data Catalogue to align Data Type and provide consistency to Swagger. Removed DI-095 which is no longer used. | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface |  | 2023-06-16
MHHS-DIN-317 |  |  | 2023-05-23 | St Clements |  | Sean Cooper | SRO Design | B9xx array references within Swagger to be updated within DES138 | Update DES138 IF document to include reference to the B9XX Array references held in Swagger |  | Closed | No |  | Design ambiguous | N/A | [6 empty] | B Blocks are oulined in the swagger definition and are utilised for managing nested arrays to translate the logical to phyiscal design. These are not maintained in EMDS. | Design Ambiguous | Supporting Docs | Interface Documentation | DES-138 |  | 2023-07-14
MHHS-DIN-318 |  |  | 2023-05-23 | REC | 5049 | Jonny Moore | Consultancy | Addition of 'Effective from date' data items to RMP Status (regi) and MP Status in IF-050 | While completing the design phase for EES we noted that the following items with the IF-050 do not have an effective from date. - RMP Status (Registration) - MP Status These items currently have an effective from date held in EES and not including this in the IF-050 would have the effect of removing these items from EES. |  | Closed | [6 empty] | #REF! |  |  | #REF! | REF DIN-508 | No Change |  |  |  |  | 2023-07-14
MHHS-DIN-319 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S0 - EventCode to marked as required to align with DES-138 |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Update made to Swagger to align with DES-138 (Event Code marked as required) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-320 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, S1 - Environment (DT-013) should have min length 3 & max length 10 to be consistent with values. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | 01-Data Catalogue DI-991 Environment Set Min to 3. However, string length is 10, so max length should be set to 10 | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface definition |  | 2023-06-16
MHHS-DIN-321 |  |  | 2023-05-23 | St Clements | N/A | Sean Cooper | SRO Design | B005 add to IF-036 | Consider adding B005 to IF-036 so that incoming SP knows who previous SP were |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Added B005 to IF-036 so that incoming SP knows who previous SP were. Updated block name to B005 - Incumbent/Outgoing Service Providers | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  | 2023-07-14
MHHS-DIN-322 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B002 - Incoming Supplier MPID - Swagger aligned to DES-138 for min / max lengths |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Update made to Swagger to align with DES-138 (Incoming supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-323 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B003 - Ougoing Supplier MPID - Swagger aligned to DES-138 for min / max lengths |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Update made to Swagger to align with DES-138 (Outgoing supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-324 |  |  | 2023-05-24 | EDF | 4780 | Paul Saker | Supplier | NHHSP-BPM00C- Transfer of Reads on Change of Data Service process steps and messages clarification | NHHSP-BPM00C- Transfer of Reads on Change of Data Service details several process steps and messages related to obtaining and sharing register readings between the gaining and losing suppliers to agree a CoS, and to initiating the missing/disputed reads process defined in the Retail Energy Code where CoS reads are missing or need to be disputed/amended. However, it appears that there is no further detail defined within the Design Artefacts regarding how exactly these process steps would work, including amongst other things: • Timing/Operational Choreography – for example it is not clear exactly when losing and gaining suppliers would be expected to attempt to communicate with the meter, or the timescales for sending data obtained between suppliers. • Data to be included in messages – while BPM003C refers to the inclusion of ‘register readings’ in some of the messages it is not clear which registers should be included for smart meters and non-smart meters – for example whether that should just be the registers on a smart meter that the sending supplier uses for billing, or whether that should be all the 48 time of use registers stored on the smart meter. Additional input from Andrew Margan - Within the code workstream, we believe the Operational Choreography document needs to be updated to reflect SLAs. Without this, we can’t complete the Code drafting. If you disagree, we would appreciate an early heads up, so we don’t look disjointed in front of industry. |  | Closed | [6 empty] | #REF! |  |  | #REF! | This is not an MHHS Design Issue. D300 / Agree Reading SLAs are defined and set by RECCO. We have replicated the existing 5 day window for capture / submission of a reading(s) all other D300 timescales still apply as per RECC process. Register Readings can only be provided on the D0010 - where this is required [for smart meters] it would replicate the current as is process defined in the current DC BSCP | [5 empty] | 2023-07-14
MHHS-DIN-325 |  |  | 2023-05-24 | CGI |  | Dave Webster | Software Provider | Status Code Missing from MsgBody | In the SubmitEvents StandardResponseBodyType object (SubmitEvents ¦ 1.2 ¦ MHHSPROGRAMME ¦ SwaggerHub), it states that “statusCode” is a required field. Yet its’ definition does not exist in the properties of the object. StandardResponseBodyType: type: object properties: transactionID: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-014-DIPTransactionID' senderUniqueReference : $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-995-SenderUniqueReference' correlationId: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-011-CorrelationID' sentTimestamp: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-003-DateTime' senderId : # the sender of this message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' recipientID : # indended (logical) recipient of the message, i.e sender of the original event message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' DIPConnectionProviderId : # physical recipient of the message (if different to recipient Id) $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' message: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-005-StatusErrorMessage' help: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-019-HelpText' serviceTicketURL: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-018-URL' required: - transactionId - sentTimestamp - senderId - recipientId - statusCode - message - help - serviceTicketURL |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | This has now been updated in V1.2 of Swagger StatusCode Added to the ResponseBody. | Technical corrrection | Supporting Docs |  | JSON/YAML files
MHHS-DIN-326 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Changes required to DES-138 / interface catalogue given changes in Migration Design e.g. the addition of interface IF003 and potentially ISD. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Duplicate of 247 | No Change |  |  | None
MHHS-DIN-327 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | IF-005 User Guide | The IF005 User Guide explains how the IF005 should be populated. We have a request for clarification on whether the IF006 will be populated identically or if the Meter ID in the IF006 will reflect the Modified Meter Id in the IF005. Is IF-005 identical to IF-006, or is it with updated MTD's. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | IF-006 should be a facsimile of IF-005. In the case of change of MSN... MSN field will reference the (old) MSN and Modified MSN will be populated with new/revised MSN. All subsequent flows following the IF-006 will only reference the NEW/REVISED MSN. We further clarified this in a change to the Note(s) section on IF-006. | Data interface correction | Supporting Docs |  | DES138 |  | 2023-06-16
MHHS-DIN-328 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | Operational Choreography Update: Addition of SLA for RS end appointment data to the CSS | The operational choreography does not include an SLA for the RS to send appointment data to the CSS or the timings by which the CSS and DSP should deliver their roles within the process. These need to be added to the operational choreography for clarity, noting the interaction with CR018. | CR018 | Closed | [6 empty] | #REF! |  |  | #REF! | RECCo confirmed closure of DIN following review of amendments to the Operational Choreography for CR018. ALL Updates between RS and CSS/DSP are existing interactions, covered by existig SLA's document in RECCO documentation. OPSC document was updated per Recco comment to highlight existing RECCO SLA in this area and to ensure primacy of the RECCO documented timings. | [5 empty] | 2023-07-14
MHHS-DIN-329 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Approach on a business rule where the ERDS does not send a MEM de appointment / appointment for an MHHS migration where the same MEM is being appointed under MHHS arrangements e.g. they have the same MPID. The expectation is that smart and advanced MEMs will use the M role code for the interaction with CSS so from their perspective there should be no change. |  | Closed | [6 empty] | #REF! |  |  | #REF! | ERDS Interfaces are ouf of scope of MHHS. If a change to ERDS interface is required or efficiencies in its existing operation are possible to align with MHHS Design - this would be a consquential change. | No Change |  |  |  |  | 2023-07-14
MHHS-DIN-330 |  |  | 2023-05-25 | Ovo Energy | 5225 | David Morley | Supplier | Long Term Vacant | BSCP504 section 4.15.3 stipulates the criteria via which suppliers can classify sites as Long Term Vacant (LTV). BSCP701 stipulates actions that SDS shall take if the supplier nominates that a site is LTV. However, the criteria that suppliers shall use for classifying LTVs in MHHS is missing. Can you please signpost where the new criteria will be located? |  | Closed | [6 empty] | #REF! |  |  | #REF! | BSCP is responsible for revising the code specification, there are no changes to design specified. Code team will get in touch with the participant.
MHHS-DIN-331 |  |  | 2023-05-25 | MHHS | 4733 | Martin Freeman | Central Body | Secondary Routing | Secondary routing for IF-013 is specified as being conditional upon the value of DI-015. However, DI-015 (Connection Type Indicator) is a property of a repeating block, and there is no constraint in place to suggest that each element in the repeating block must have the same value for this (or any other) property, in which case multiple rules in the routing table could apply simultaneously. The routing table design seems to suggest that only a single rule should apply at a time and that routing should not be derived by blending multiple rules. If this is so, and a message is received where different elements in the B050 have a different Connection Type Indicator then there is no coherent way to implement this in conformance with the routing table. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Agree there was a routing contradiction for scenarios/periods where a different connection type was in effect. Interface notes section has been updated to direct the use of 'separate' IF-013 messages in such circumstances. Note also makes clear that repeating B050 blocks are acceptable where other elements (not Connection Type) of the CCC vary over the period to be defaulted. | Design Ambiguous | Supporting Docs | Default Consumption | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-332 |  |  | 2023-05-25 | MHHS | 4750 | Martin Freeman | Central Body | IF-013 Routing | In the routing table for IF-013 all rules are conditional upon S0.Eventcode == [ActivePowerDefaulted], which means that for IF-013 message where Eventcode == [ConsumptionOnDeEnergisedMPAN] there is no routing at all, which means when this message is sent to the DIP it will not be routed anywhere and will simply disappear. That's almost certainly an error. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Event code [ConsumptionReceivedonDeEnMPAN] has been moved from IF-013 to IF-014. The valid event code list and routing rules have now been updated for both interfaces to reflect the move. v1.2 of Swagger also updated to reflect this change Duplicate of DIN 255 | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-333 |  |  | 2023-05-25 | MHHS | 4760 | Martin Freeman | Central Body | Connection Type Required to Support Routing of IF-014 | All of the routing rules specified for IF-014 are conditional upon DI-015 (Connection Type Indicator). But IF-014 does not have any blocks with this property, which means this message won't get routed anywhere. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Block B067 - Connection Type Added to IF-014 in order to support routing requirements. Swagger v1.2 updated to reflect this change. (Duplicate of DIN256) | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-334 |  |  | 2023-05-25 | MHHS | 4766 | Martin Freeman | Central Body |  | The routing table for IF-018 specifies roles AMSC, UMSC, UMDC for Secondary routing. There are no such roles in either the DES138 nor the E2E001. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Secondary Routing Review/Changes have superceded this issue - Ref DIN-268
MHHS-DIN-335 |  |  | 2023-05-26 | British Gas/Engage Consulting | 4640 | Neil Strange/ Haz Elmamoum | Consultancy | Four questions on IF004 | IF/PUB-004 – DIP Common Blocks referencing MHHSP-DES138-Interface Catalogue v5.1.1 As a minimum this needs to be referenced in the supplier requirements MHHSP-BRS004-Supplier Overview and MHHSP-BRS002-Metering Service requirements, but to ensure parties get sight of this we would suggest it needs to be included in a business process map and have associated requirements. For IF-004 to be useful to participants DI-999 – Event Code needs to be elaborated e.g. 1- Installation 2- Removal; 3- Exchange; 4 - Found (Where installed by Gas supplier and Elec Supplier takes ownership) C/M/O rules for DI-192, DI-193 and DI-194 need to be explained in the notes – presumably driven by event code Available is spelled incorrectly (available) for DI-192 and DI-194 there are a couple of angles here – 1) ensuring wider awareness and 2) it seems there is a question mark on the governance here as it is odd a flow has been added but industry does not appear to have been sighted on it especially with no associated referencing in artefacts and no process map, so effectively no one has any idea how it is supposed to be used. Although it was formally agreed not to include and use bilaterally....from a Large Supplier Constituency perspective, my members are keen to ensure design clarity and how flows are to be used or not, regardless of their ad-hoc / bilateral nature. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Updated BP009 Change of Metering to include the "optional" sending of IF-004 from MS via DIP to Supplier, if changes to Comms Hub need to be notified. Included same updated to BPD009 to reflect new BP steps. Other comments have been addressed previously and are reflected in DES138 IF-004 | Process Model correction | Meter to Bank | IF-004 | BP009 Change oF Metering BPD009 Change of Metering |  | 2023-06-16
MHHS-DIN-336 |  |  | 2023-05-26 | MHHS |  | Rob Topley/ Zak Hussain | SI Design | Requirements clean up in iServer | Process Step No. BP Step ID Process Map wording Interface ID Sender Recipient/Service Traceability Requirement Traceability Method Statement iServer Requirement Name iServer Step name Issues Found BP01 170 BP01 - 170 Send Site Tech Details on Metering Service Request MHHS-RS-LD-012.1 #N/A LDSO170a Send Site Tech Details on Metering Service Request Missing (only on BPD and traceability matrix) BP01 175 BP01 - 175 Receive Site Technical Details D0215 LDSO Metering Services MHHS-RS-MS-037.1 #N/A MET175 Receive Site Technical Details Missing (only on BPD and traceability matrix) BP03B 95 BP03B - 95 Manage SP Appointment Amendment Request Response PUB-035 DIP Supplier MHHS-BR-SU-35.1 #N/A SUP095a - Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP03B 96 BP03B - 96 Manage SP Appointment Amendment Request Response PUB-035 DIP Data Services Metering Services MHHS-BR-DS-11.1 #N/A ESP96 – Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP05 315 BP05 - 315 Issue Reading Data MHHS-IF-041 Data Service DIP MHHS-BR-DS098.2 #N/A DAT315 – Issue Reading Data Missing (only on BPD and traceability matrix) BP05 340 BP05 - 340 Process Reading Data PUB-041 DIP Supplier MHHS-BR-SU047.1 #N/A SUP340 Process Reading Data Missing (only on BPD and traceability matrix) BP05 350 BP05 - 350 Process Reading Data PUB-041 DIP LDSO MHHS-BR-LD009.1 #N/A LDSO350 Process Reading Data Missing (only on BPD and traceability matrix) BP010D 1055 BP010D - 1055 Receive updated Legacy information PUB-026 DIP Central Settlements MHHS-BR-RD-018.1 #N/A ECS1055 Receive updated Legacy information Missing (only on BPD and traceability matrix) All these requirements don’t exist on any requirement catalogues, they’ve only ever been on a BPD document or the traceability matrix (which are essentially the same document). Also, the highlighted traceability has a typo and is on a requirements artefact but is wrong on both the BPD and traceability matrix. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Requirements have been found in BRS001, BRS004, BRS005, BRS014. Models have the correct steps identified. Unable to identify whats missing, checking with the originator. Confirmed with originator no further changes needed | No Change | Supporting Docs | Supporting Docs | BRS001, BRS004, BRS005, BRS014 |  | 2023-07-14
MHHS-DIN-337 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger alignment to DES-138 | R0 - Response Message Min length updated to align with DES-138 |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated R0 - Response in Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-338 |  |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier | BP003/BP002 to be updated to clearly show IF-036 going to both Import & Export supplier | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. BP003/BP002 to be updated to clearly show IF-036 going to both Import & Export supplier |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | On an Export Supplier COS, the Service Providers will be de-appointed on notification of the Secured Active. As the Export Supplier is unable to appoint their own Service Providers (in the case of Linked Import/Export), the auto-aligmnment functionality (BP011C) will trigger the correct Service Providers to be appointed and the Service Providers will be notified of the Supplier in IF-036. However this DIN has highlighted the need for the export Supplier to be notified of the Service Provider changes. BP003/BP002 updated from Step 255/245 to re-label "PUB-36" flow to Step 260 for the Supplier (prospective/incumbent) to state "PUB-036 for Import & Export Supplier". Change is not reflected in the BPM-003 for forward migration as linkages only become active when both Import/Export are migrated. See also 339 | Process Model correction | MPAN Ownership | Process Models | BP003 BP002 |  | 2023-07-14
MHHS-DIN-339 |  |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier | IF-001 to be updated to be additionally sent to the Export supplier rather than just the import | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. IF-001 to be updated to be additionally sent to the Export supplier rather than just the import |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | On an Export Supplier COS, the Service Providers will be de-appointed on notification of the Secured Active. As the Export Supplier is unable to appoint their own Service Providers (in the case of Linked Import/Export), the auto-aligmnment functionality (BP011C) will trigger the correct Service Providers to be appointed and the Service Providers will be notified of the Supplier in IF-036. However this DIN has highlighted the need for the export Supplier to be notified of a new Import Supplier. BP001 updated to re-label "PUB-001" flow for the Supplier (prospective/incumbent) to state "PUB-001 for Import & Export Supplier". See also 338 | Process Model correction | MPAN Ownership | Process Models | BP001 |  | 2023-07-14
MHHS-DIN-340 |  |  | 2023-05-26 | UKPN | 4547 | Neal Medley | Network Operator | ELEX-REP-02/02A report | The reports ELEX-REP-02/02A will only contain aggregated data for A(General LLF Class Import and C (General LLF Class Export). The I/F021 can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/014 Rejected Consumption Data Submission and I/F MDS Defaults Applied to any I/F021 data to ensure you are not using rejected data or are missing I/F 021 data in respect of an MPAN. MDS Method Statement to be updated to reflect |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Updated the below test to Section D within MDS Method statement: 17.4 The I/F021 ‘UTC Settlement Period Consumption Data’ can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/F014 Rejected Consumption Data Submission and I/F ‘Notification of Defaulted UTC Settlement Period Consumption Data’ to any I/F021 data to ensure LDSO’s are not using rejected data or are missing I/F 021 data in respect of an MPAN. | Design Ambiguous | Supporting Docs | Method Statement | MDS Method Statement |  | 2023-07-14
MHHS-DIN-341 |  |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | MUM Event not required by MDS | For IF-018 the event [MUMIndicator] is routed to MDS and indicates metered/unmetered. This event is not required by MDS as they can infer this from the Market Segment (Advanced, Smart and Unmetered). DIN raised to remove the routing |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | MDS Removed as Always Recipiant for Event [MUMIndicator] on IF-018 Routing rules | Data interface correction | Supporting Docs | IF-018 | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-342 |  |  | 2023-05-26 | UKPN | 5194 | Neal Medley | Network Operator | ELEX-REP-02/02A Consumption data clarification | The intent is that the daily volume on actuals or estimates are the sum of the appropriate consumption data. So when added together they should equal the summed Total of the Settlement Period data (Total Uncorrected Volume) barring any rounding errors. The data is given in MWh to six decimal places (i.e. to the nearest Watt hour). I assume DUoS billing only calculates to the nearest unit so would not expect any rounding errors to impact. The A flags are set out in the ELEX-REP-02/02A are the same as those set out in the CCC table in the VAS Method Statement which is also in the MDS Method Statement. I agree the list in the calculations only are missing the full list of SPQI that are deemed to be actuals as set out in the ELEX-REP-02/02A. DIN raised to correct the calculation |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Updated full list of actuals with the MDS Method Statement. The amended list added to the Method statement: A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6. | Method statement correction | Supporting Docs | Method Statement | MDS Method Statement |  | 2023-07-14
MHHS-DIN-343 |  |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | Routing rules table | The routing rules on the IF-037 sheet state that MDS will 'always' receive the DSDeApp event code, however the 'Always' column on the IF_LIST does not state Central Settlements for MHHSP-IF-037. IF list needs updating to reflect that the DSDeApp event always routes to MDS |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Decision taken to remove Recipiants (COLs G,H &I) from the IF_list - as just duplication of information contained within each of the IF spreadsheets. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue |  | 2023-06-16
MHHS-DIN-344 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B005 Custom Block update Swagger to align with DES-138. Current Metering Service MPID Length removed. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated Swagger to align with DES-138. Current Metering Service MPID Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-345 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B024 Custom Block update Swagger to align with DES-138. DUOS Min Length removed. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated Swagger to align with DES-138. DUOS Min Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-346 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design |  | IF-001 - B032 Custom Block update DES-138 to align with Swagger. Update DI-122 (Profile Class) to Integer from String-2. |  | Closed | [6 empty] | #REF! |  |  | #REF! | DI-122 remains as String 2 for Profile Class to support requirements for enumerations. | Data interface correction | Supporting Docs |  | None |  | 2023-06-16
MHHS-DIN-347 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B035 Custom Block - update Swagger to align with DES-138. Remove min length. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-348 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | IF002 correction | IF-002 - B074 Custom Block. Clarification on DI-091. DES-138 says this is 1 digit to the left of the decimal point. Swagger says 5 to 6. DES-138 to be updated to the correct value. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated Swagger to be an Integer (1), Min of 1, Max of 1, example of 5. This now aligns with DES-138. | Data interface correction |  |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-349 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Correlation ID Issue IF-006 | Routing Rules in DES-138 do not always correctly identity where Correlation ID == Copy ie, it's missing for IF-005 / IF-006 so this needs to be updated correctly across all interfaces. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated IF-006/IF-008/IF-039/If-028/IF-026/IF-016 routing rules to show use of a "Copy" in Correlation ID (ie copied from the preceeding IF txn pairing) | Missing/incorrect validation rule | Supporting Docs |  | DES138 |  | 2023-06-16
MHHS-DIN-350 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-005 B033 to align Swagger with DES-138 (Postcode removal, mandatory modified meter id) |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated Swagger to align with DES-138 (Postcode removal, mandatory modified meter id) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-351 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B071 to align Swagger with DES-138 |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-353 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B032 to align Swagger with DES-138 (SSC Min Length should be 4) |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated Swagger to align with DES-138 (Updated SSC Min Length to be 4) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-354 |  |  | 2023-05-30 | SJW |  | Sarah Jones | Consultancy | Design team confirmation for sending of IF-037 and not IF-037 to losing MEM | Please see below details of a new design query related to the Registration Tranche of Code Drafting. We note that in BP011C there is a process whereby the Registration Service will auto de-appoint / appoint agents for secondary related metering points and linked export metering points as part of their validation. The business process only includes the sending of the IF037 to the Losing MEM and not the IF035. Please could you confirm that this is correct and that in this instance the Losing MEM would not receive an IF-035. If this is the case, we think there should be a change to Metering Service requirements MS-018 and 019 to clarify that where the Losing Metering Service receives an IF-037 with no preceding IF-035 then they should send the MTDs at this point. The alternative would be to include the sending of an IF-035 as well as an IF-037 accepting that these would arrive at a similar time. This would align to the process for managing retrospective MEM appointments where we understand that the Losing MEM would receive both the IF-035 and the IF-037. We also suggest amending MS-008, 008.1, 009 and 009.1 to recognise this nuance as follows: MSA/MSS must obtain Export MPAN de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. MSA/MSS should note this message will be automatically triggered when a change of Metering Service has successfully completed for the linked import MPAN or a new MPAN linkage has been put in place where the [linked import / primary related] MPAN has a different appointed Metering Service. Presumably there is a similar impact on the data service requirements that would need to be considered. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Solution options discussed with SCS. Closed as covered under DIN 560 |  | Supporting Docs |  |  |  | 2023-07-14
MHHS-DIN-355 |  | DI-179 | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Number of Register Digits | Revisit and confirm IF-005 Cumulative Digits validation rule against latest version of the CP |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | All instances of DI-091 (IF-002,IF005,IF-006,IF-033,IF-036) updated to reflect updated logic. IF-005 validation rules updated also to reflect new guidance. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue |  | 2023-07-14
MHHS-DIN-356 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B073 - update Swagger to align with DES-138 (consumptionAmendmentSupplierReference max length) |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated Swagger to align with DES-138 (Updated consumptionAmendmentSupplierReference max length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-357 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B902 - update Swagger to align with DES-138 (supplierConsumptionAmendmentRequests typo update) |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated Swagger to align with DES-138 (Updated supplierConsumptionAmendmentRequests - remove typo) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-358 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-034 B070 - update Swagger to align with DES-138 (contractReferenceMeteringService max length 10) |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated Swagger to align with DES-138 (Updated contractReferenceMeteringService max length 10) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-359 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: The method statement states that “The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN on notification of the set-up of that MPAN in MHHS-IF-001.” However, it will be the MHHS-IF-036 Registration Service Notification of Service Appointment & Supporting Info that will initially provide the fact that an MPAN has migrated to Central Settlements. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Annual Consumption Method Statement updated with following text in red: 2.3 The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN within 30 calendar days following notification of the set-up of that MPAN in MHHS-IF-036 'Registration Service Notification of Service Appointment & Supporting information' or MHHS-IF-001 ‘Notification of change of Supplier’. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption |  | 2023-07-14
MHHS-DIN-360 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: 3.3 Where a years’ worth of data, >=75% and <100% of actual UTC Period Consumption data (where Settlement Period Quality Indicator = A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6) has been used to calculate the Annual Consumption, the Annual Consumption Quality Indicator should be set to “1”. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Annual Consumption Method Statement updated with following text in red: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption |  | 2023-07-14
MHHS-DIN-361 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Greater than or equal to change for UTC Period Consumption Data | We need to raise a DIN on the AC method Statement and AC requirements: Likewise 3.6 needs to say greater than or equal to 182 days: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Annual Consumption Method Statement updated with following text in red: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption |  | 2023-07-14
MHHS-DIN-362 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Section Name change | Section 5 incorrectly named Section 6 needs to be updated: 6. Transition and Next steps |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Section 6 has been updated to Section 5 within AC Method Statement and old section 5.1The initial Annual Consumption calculation, as set out in section 3.7 above may change, depending on the consideration of the working groups during the MHHS Transition requirements work- has been removed | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption |  | 2023-07-14
MHHS-DIN-363 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Load Shaping Service calculations | We may also need to document how this is calculated by the Load Shaping Service in the first year. I believe Helix have developed a calculation and this would need to go in the Load Shaping Method Statement and be referenced in the AC Method Statement. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Kevin Spencer to arrange a session with Mike Ceney to discuss solution further. Upon further discussion with Kevin Spencer on 4/8/23 it was confirmed this DIN could be closed as the change is in relationn the AC Method Statement. No changes required to the LSS Method Statement | Method statement correction | Supporting Docs | Method Statement | Annual Consumption Meth 10 |  | 2023-07-14
MHHS-DIN-364 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-035 - B066 - mark as mandatory in Swagger as per DES-138 |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated Swagger to align with DES-138 (Updated so B066 is a mandatory for IF-035 custom block) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-365 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-004 - B093 - update Swagger to align with DES-138 (min Length on commsHubGUID / GPF-GAS-GUID) |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated Swagger to align with DES-138 (Updated min Length on commsHubGUID / GPF-GAS-GUID) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-366 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 custom block - SSC add min length to align with Swagger |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated Swagger to align with DES-138 (Updated B032 custom block - SSC add min length to align with Swagger) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-367 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 Profile Class - updated Swagger to be a String to align with DES-138 |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated Swagger to align with DES-138 (Updated B032 Profile Class Swagger to be a String to align with DES-138) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-368 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-013 - B049 updated Swagger to align with DES-138 (run Number optional) |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated Swagger to align with DES-138 (Updated B049 Swagger to align with DES-138 (run Number now optional) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML |  | 2023-06-16
MHHS-DIN-369 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | Switch Cancellation Info Note | Update BP002/003 to add informational note that Registration Cancelations will be processed as soon as they are received by SCS from CSS i.e. Apps Lapsed through switch cancelation sent immediatly not held until Proposed App Date. Also updates to Forward Migration BP002/003 for consistency. Changes to OPC added the following words to OPC_190 in the Activity column (section 4.4) “(including Switch Status Updates e.g. Cancelled)” |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | BP-002/003 updated to include new informational Note in Supplier swimlane relating to CSS Switch Cancellations. OPC updated to make it clearer that Secured Active Processing includes Switch Status Update processing. to OPC_190 in the Activity column (section 4.4) “(including Switch Status Updates e.g. Cancelled)” | Process Model correction | MPAN Ownership |  | BP002, BP003, OPC001 Forward Migration BP002 & BP003 |  | 2023-06-16
MHHS-DIN-370 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | IF-005 Update Window Guidance for Prev MS | Change IF-005 and Guidance Doc to allow Meter Updates within 10 day window for previous MS |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | New validation rule added to IF-005/MeterUpdate to allow previous MS to submit if within 10 day post appointment period. IF-005 User Guide section 9.3 updated to reflect same. | Missing/incorrect validation rule | Supporting Docs |  | DES138, IF-005 User Guide |  | 2023-06-16
MHHS-DIN-371 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team |  | Review design to ensure only Supression of IHD info for advanced segment and NOT "deactivation" of underlying IHD record. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Confirmed that IHD details will be retained on Smart to Trad Exchange. Any IHD info present will be suppressed (ie not included in msg) if Segement is Advanced. No change required to documentation. Possible data cleanse issue - Dan T. to raise in Data Forum.
MHHS-DIN-372 |  |  | 2023-06-01 | MHHS | 5298 | Rob Golding | Central Body | Mapping Roles | There is a need to master the mapping of Market Participant Role to DIP Role within the MHHS solution. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | New entity M18 created to show the DIP market roles. Minor corrections to M16 to clarify DIP ID field length. | Other | Supporting Docs | ISD Entities | MHHS-EDI-021-ISD_Entities |  | 2023-07-14
MHHS-DIN-373 |  |  | 2023-06-02 | MHHS | 5272 | Rob Golding | Central Body |  | There is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 |  | Closed | [6 empty] | #REF! |  |  | #REF! | Duplicate of DIN-297
MHHS-DIN-374 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Message Replay & Requeue functionality | Message replay and requeue functionality needs to be added to the DIP API interfaces, which requires changes to the Swagger / YAML definitions. Detail is required in the E2E design documentation to explain how the message replay and requeue functionality will work. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updates to the E2E001 design document to provide detail on how the replay and requeue will work. There are updates to Swagger to support new interfaces for /dip-channel/{id}/replay and requeue respectively. There is also a new MessageRequest Schema that is used to pass data into both of these interfaces. To support these changes, section 4.8 has been updated in the E2E001. | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents |  | 2023-06-16
MHHS-DIN-375 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Interface webhook configuration | Updates require to the pubconfig and webhook config to support per interface webhook configuration, alongside changes to support definition of recipient ID and role ID. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updates to the E2E001 design document to provide detail on how the webhook configuration will work, with information related to specific interface changes. There are updates to Swagger to support new interfaces for /dip-channel/{id}/pubconfig (POST and DELETE) respectively to support changes defined in the E2E001 (Section 4.5 and 4.5.1 and 4.5.2have been updated to provide more clarity / information). | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents |  | 2023-06-16
MHHS-DIN-352 |  |  | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Obsfucation Text | What text should be used for data obfuscation ? for things like Boolean fields (True/false) |  | Closed | [6 empty] | #REF! |  |  | #REF! | Closed as this is already included in section 4.3.2 of the E2E001 design document. | [5 empty] | 2023-07-14
MHHS-DIN-376 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-099 changes required to ensure DES-138 displays the correct YAML name / Swagger aligns to this. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | "Register" spelling in name has been corrected in DI099, and DI-099 name correction for IF041 in DES138 | Data interface correction | Supporting Docs |  | DES138 |  | 2023-06-16
MHHS-DIN-377 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-097 | DI-097 - In DES-138, this is defined as a string (2), but the existing data type is an Integer and this is an Integer enumeration. Need to update this to an Integer in both DES-138 and Swagger 1.2. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Rejected / closed as enumeration of values requires string (2) therefore this is retained to support buisness requirements. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-378 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. This information has now been added to DES-138 5.2.1. | Data interface correction | Supporting Docs |  | DES138 |  | 2023-06-16
MHHS-DIN-379 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-048 | DI-048 - clarity required on whether this is "meter manufacture make and type", rather than just "meter manufacturer". The first is an existing data type and links to the J number, so providing further clarity / rename would quickly ensure alignment in DES-138 and then subsequently in Swagger. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Rejected / closed as this was discussed as part of previous work off items and description has previously been approved / accepted as Meter Manufacturer. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-380 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-052 | DI-052 in DES-138 currently has 4 enum values ie, - Active Import, Active Export, Reactive Import, Reactive Export. In MDD there are currently 38 options documented. Discussion around whether ISD Entity 47 should be referenced as the list of values allowed. This can then be aligned / referenced in other other documents ie, EMAR will reference ISD Entity 47. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Rejected / closed as this was discussed as part of previous work off items. Only 4 values are required in MHHS / DIP, therefore only these values are referenced / used as part of the enumeration to avoid bringing data from existing systems into new systems when this is not required. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-381 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-842 | DI-842 - Confirmation that MDR's have DIP ID's? There has been discussion in various forums to understand whether they do and if not, then this data item needs to be removed in DES-138 and Swagger. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Rejected / closed as MDR's do have DIP ID's, therefore this value will be retained. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-382 |  |  | 2023-05-06 | Design Team | 4570 | Neil Strange | Supplier | D0010 | In BP003C, at CoS traditional CoRs are transferred between suppliers via D0010. We believe this needs to be used for all meter types - as this will be needed for non-communicating smart and advanced meters – and BP003C needs to be amended accordingly. There is no mention of IF-041 and we do not believe that the DIP is expecting an IF/PUB-041 transaction between suppliers. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Supplier added as a Primary Recipient in the Routing Rules for IF-041 (DES138) - Supplier initiated Reads. Sending supplier would need to populate the DIP ID of Supplier(s) with whom he wished to share the reading. Working Group specifically decided not to discuss /include COR scenarios for Smart Metered Sites however this is not prevented by the Design - a note to this effect has been added to BP003C for clarity. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue BP-003C Transfer of Readings
MHHS-DIN-383 |  |  | 2023-06-07 | RECCO | 4558 | Sarah Jones | Central Body | Change of Segment Scenario | We cannot find anything in the design artefacts stating that the Metering Service is required to notify metering exchanges for change of segment within 2 WDs. We have found the following: MS-094: MSA/MSS must be able to publish Change of Segment Meter Exchange details and reads via the appropriate interfaces, where it is not formally appointed as the Metering Service but does have an accepted prospective appointment (Appointment Scenario = "SEG"). The MSA/MSS must issue the work update to Registration at the earliest opportunity but within [x] days of completion at the latest. OPC 240: Notification of works to be completed by D+3 Working Days (This should provide time for consumption to be provided using new MTDs ahead of the SF run.) The BP011 references the connection type update being provided by LDSOs within 2 WDs. There is no equivalent for metering updates. Will require DRG confirmation on if the 'x' should be 2 or 3 working days |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Updates to be made inline with DRG recommendation to reflect 3 working days | Process Model correction | Supporting Docs | Business Process Documentation | BP011 - Change of Segment DES138-Interface Doc BRS002- Metering Service Requirements BRS003 - Registration Service Requirements BRS005 - LDSO Overview OPC001 - Operational Choreography MHHSP-DES229-IF005_UseCaseguide |  | 2023-07-14
MHHS-DIN-384 |  | DI-174 | 2023-06-07 | St Clements | 4938 | Madison Layton | Software Provider | IF-038 and IF-039 blocks not the same | Block B020, B021 are not the same across interface IF-038 and IF-039. DI-140 and DI-138 (SP DIP ID) are in IF-039 but not in IF-038. Understanding was that with the DIP change that all data items in block are mandatory, the blocks were to be consistently defined across all interfaces. If extra DIP ID DI-138 and DI-140 data items are included in IF-038 then we need a new REG rejection code to allow us to reject where DIP ID is not the same as the sender DIP ID. Alternative is to separate the DI-140/DI-138 into their own blocks included on the IF-039 interface only. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Block data items were aligned in release 2. New validation rule on IF-38 add to ensure that Sender ID matches MS/DS CDC ID. New Error code REG1076 added to support validation rule. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue |  | 2023-07-14
MHHS-DIN-385 |  |  | 2023-06-07 | Design Team |  | Steve Weston | SI Design | Correlation ID | S1 Common Block - Correlation ID is mandatory in Swagger, but Optional in DES-138. Swagger should be updated to align. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Updated S1 Common Block, Sender Correlation ID in Swagger, as this is Optional in DES-138 to support business process and requirements. | Technical corrrection | Supporting Docs |  | JSON/YAML documents |  | 2023-06-16
MHHS-DIN-386 |  | DI-179 | 2023-06-07 | St Clements | 5258 | Madison Layton | Software Provider | Register Digits | REC Change R0102 has been approved by industry to amend the number of display digits validation Where the Meter Type is S1 the Number of Displayed Register Digits value must be either 6 or 5 Where the Meter Type is S2A, S2AD, S2ADE, 2ADF, 2ADEF, 2AEF, 2AF, S2B, S2BD, S2BDE, 2BF,2BDF, 2BDEF or 2BEF the value must be “5”. Where the Meter Type is prefixed with “S2C” the value must be “6”. Where the Meter Type is 2CDEF, 2CF, 2CDF or 2CEF the value must be “6” REG1097 validation on the IF-005 needs correcting with this change, and the population notes for data item DI-091 across multiple interfaces also needs correcting |  | Closed | [6 empty] | #REF! |  |  | #REF! | Duplicate of Register Digit DIN-355 listed above | Data interface correction | Supporting Docs | Interface Catalogue | Lis
MHHS-DIN-387 |  | DI-180 | 2023-06-09 | St Clements | 5269 | Madison Layton | Software Provider | Uplift metered indicator requirements | There are elements in the requirements that suggest that metered indicator would trigger a change to Market Segment. E.g. MHHSP-BP011-Change of ConType andor Mkt Segment-v5.1 Step 102 MHHSP-BPD011 - Change of Con Type or Market Segment v5.0 Step 102 Which states if there is a change to market segment RS would need to re-evaluate the market segment And MHHS-BR-RS-124 which include in brackets: Change of Connection Type (Change of Unmetered Indicator) MPRS will assess Market Segment against the ISD entity M7 which does not include Metered Indicator. Therefore a change in Metered Indicator in isolation of any other changes to data items in the M7 table/Related MPANs/Linked MPANs, will not trigger a change to Market Segment. As it will not trigger a change MPRS will not re-evaluate Market Segment base on a Metered Indicator change alone. The requirements need uplifting to reflect. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Closed as discussed and agreed with SCS. | No Change
MHHS-DIN-388 |  |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | IF-036 Custom Routing Rules | Following discussions with SCS agreed that for reasons of complexity it would be better to adopt Primary rather than secondary routing to IF-036. New Requirement created for REGS to undertake the Primary Routing of IF-036. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Ref DIN-507
MHHS-DIN-389 |  |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | Appointment Start Times | Do we need a formal validation Rule to check that Appointment Start times are referenced as Midnight Local ? Issue raised numerous times with SCS. Waiting for SCS to confirm their position. |  | Closed | [6 empty] | #REF! |  |  | #REF! | CLOSED - DUPLICATE OF DIN-207 ABOVE
MHHS-DIN-390 |  |  | 2023-06-13 | Siemens | 5534 | Tony Mason | Metering Service Provider | IF/PUB-018 | There appears an inconsistency in the Business Process Map, BP010, and the routing rules for the IF-018 where the Event Code = DUOSTariffIDChg. This information is confirmed to SPs on the IF/PUB-036 and would then be updated where there is a change on the 018 according to the Secondary Routing Rules. This notification is absent on the process diagram. Could you confirm the position and update the documentation accordingly? |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Update BP010B to show Data Service and Metering Service receiving PUB-018 for DUoS Tariff ID updates in line with the routing rules in DES-138. Update BPD010 process description to includes steps to recieve PUB-018 for Data Service and Metering Service. | Process Model correction | Meter to Bank | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-391 |  | DI-182 | 2023-06-13 | St Clements | 5304 | Madison Layton | Software Provider | IF-019 validation gap on principal and subsidiary MPAN | IF-019 is missing validation rules to ensure an MPAN is only listed once in the IF-019, need rules to ensure the sender cannot repeat same Subsidiary MPAN twice in the repeating B090 block, and cannot list the same MPAN as both Principal and Subsidiary in the same IF-019 message |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Created x2 new rules to prevent duplicate MPANS within repeating B90 groups within a single message. Error Code REG1059 created to support validation checks | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-392 |  |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Consent Fields | Raised by SCS. B068/DI-017/DI-018 - This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block B068 updated to be "must be provided" for smart meters. Data items set to mandatory non-nullable. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | Block text updated to show mandatory if smart meter present, and DI-017/D-018 updated to be mandatory non-nullable (applies to IF-026 only) | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-393 |  | DI-181 | 2023-06-13 | St Clements | 5274 | Madison Layton | Software Provider | De-appointment and re-appointment date order | MHHS-BR-RS-128.4 & MHHS-BR-RS-128.5 covers the requirement for MPRS to ensure MS/DS are aligned across Related/Linked MPANS, and where they are not to de-appoint the MS/DS and appoint the correct MS/DS. The de-appointment requirement specifies to set MS/DS ETD to D+1 and the appointment to set the MS/DS EFD to D+2. Why do we need to apply the de-appointment and re-appointment in the future? Would we not be better to use the previous day (D-1) for the de-appointment MS/DS ETD and the current day (D) for the appointment EFD? |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Discussed with SCS and agreed to update Registration Service requirements to De-appoint on D (MHHS-BR-RS-128.4) and appoint on D+1 (MHHS-BR-RS-128.5) as part of auto-alignment process | Requirement correction | Registration | Auto-alignment | BRS003
MHHS-DIN-394 |  |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Annual Consumption Fields | Raised by SCS. B059/B027/DI-0148 This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block updated to be "must be provided" if available, however data items now need to be set to mandatory non-nullable. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | DI-0148 updated to be mandatory no-nulls and data type updated to DT-016 in Data Catalogue. Data Type corrected to DT-016 in IF-002 and IF-036. | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-395 |  |  | 2023-06-13 | St Clements | 5510 | Vicki Holland | Software Provider | Obfuscation of Connection Type Indicator in IF-021 | The DES138 interface catalogue specifies that the data item Connection Type Indicator will be obfuscated for all parties as it is required for routing only. Can this please be changed so that it is visible? The reason for this request is that suppliers often process data differently for the different connection types and therefore its important that they can internally validate or route data according to the connection type of the MPAN. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Obfuscation of connection type removed from IF-021/IF-013 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-396 |  | DI-183 | 2023-06-13 | St Clements | 5305 | Madison Layton | Software Provider | Update IF-019 REG1001 to only apply to Create and Add event codes | IF-019 REG1001 rule applies to all event codes. The MPAN could be disconnected with linkages still in place. If REG1001 is applied on remove event codes, then there will be not means by which the Supplier/DNO can remove the linkage after a disconnection. Suggest REG1001 rule should only apply to the Create and Add event codes. This would be consistent with the existing validation on the DB05 and D0386. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | IF-019 MPAN Status Validation Rule removed for all "Remove MPAN" Event Codes. i.e. I can still perform remove MPAN from group task if MPAN is disconnected. SCS rejected option of auto de-linkage as part of De-Registration Process. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-397 |  | DI-184 | 2023-06-13 | St Clements | 5306 | Madison Layton | Software Provider | IF-019: REG0007 to only apply to Related event codes and not to Linked Import Export event codes | REG0007 on IF-019 interface is currently written to apply to both Related and Linked MPANs. The intention of this existing rule on D0386 is because Related MPANs switch together, and so changing the relationship during a switch can create a split supply relationship. However Linked MPANs do not switch together and so this is not currently applied to the existing DB05 validation rules. Suggest REG0007 only apply to Related event codes and not to Linked Import Export event codes? |  | Closed | [6 empty] | #REF! |  |  | #REF! | Following discussions with SCS it has been agreed to prevent all changes to MPAN Linkages whilst an Active Switch is in progress. This is the safest approach when considering both CSS and Auto Alighment functionality considerations. No change to existing Design Documentation required.
MHHS-DIN-398 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD Stores LLF data | Can we have an ISD entity ID for LLF data. This would be required for the API used to retrive the data from ISD data store. Are you happy for us to create and put it in the Guidance note. |  | Closed | [6 empty] | #REF! |  |  | #REF!
MHHS-DIN-399 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD publishes full data to Elexon Central Systems | Requirement should be reworded to be "ISD must make available the data sets required by LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. ISD must make available the entire current data set to LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Agreed in a session with Elexon 26/07 that the requirements document will not be changed as the requirement has already been fufilled by Elexon in line with the current requirement.
MHHS-DIN-400 |  |  | 2023-06-14 | SRO Design Team | N/A | Sean Cooper | SEO Design | REGS Validation Rule Clarification | REG1089 conditions updated to provide more clarity. Existing wording refered only to a Subsequent App - this is now better defined as an Appointment with a prior/earlier Sender Timestamp. No functional change. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | For IF-031 Validation rule text updated to specifically reference Sender TimeStamps so as to provide more clarity on the nature of the val rule/when generated | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-401 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | IHD/SMSO Fields | IHD Install Status and IHD Status Effective from Date fields should be optional (i.e. nullable) when providing an IHD update in IF-025/IF-026. SMSO and SMSO Effective from Date fields should be optional (i.e. nullable) when providing an SMSO update in IF-025/IF-026. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | DI-137/ DI-136 in block B030 updated to Optional (O) in IF-025 and IF-026 DI-134/ DI-135 in block B031 updated to Optional (O) in IF-025 and IF-026 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-402 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Import/Export Fields | Linked Import/Export MPAN and Linked MPAN Energy Direction will always be provided so should not be nullable |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | DI-038 updated to Mandatory No nulls and Data Type updated to DT-002 DI-151 updated to Mandatory No nulls On the 01-Data Catalogue | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-403 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Meter Manufacturer Field | Meter Manufacturer is optional (ie nullable) when provided in IF-002, IF-006, IF-033, IF-036 as in IF-005 |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | DI-048 updated to Optional (O) in IF-002, IF-006, IF-033, IF-036 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-404 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Proposed Appointment Response Code Field | For Response code A there may not be any text to populate for DI-143 |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | DI-143 updated to conditional (C) based on DI-979 = L or R in block B007 in IF-034 and IF-035 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-405 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Response Message Field | For Response code A no text to populate for DI-980 |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | DI-980 updated to conditional (C) based on DI-979 = R in block R0 in 02-DIP Common Block tab | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-406 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Sender DIP ID Field | Sender DIP ID should always be provided in S1 Common Block |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | DI-997 updated to mandatory (M) in block S1 in 02- DIP - Common Block tab | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-407 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | COS During SEG Issue | Discuss with SCS the option of allowing non-appointed MS to update MTDs even if App has lapsed due to COS activity. If not then need to update process map to call out need for manual exchange of MTDs as Work MS could never submit if IF005 |  | Closed | [6 empty] | #REF! |  |  | #REF! | Closed, SCS unable to support alternative solution. Design Team have reviewed the existing process map note and believe this already provides enough information for participants. | No Change
MHHS-DIN-408 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD is the master for data contained both within ISD and MDD during Transition | The requirement is a bit ambiguous as could be read as all ISD and all MDD rather than just ISD data + overlapping MDD data. We don't want to be the master for MDD only data |  | Closed | [6 empty] | #REF! |  |  | #REF!
MHHS-DIN-409 |  |  | 2023-06-14 | St Clements | 5510 | Vicki Holland | Software Provider | ISD Entity M5 – Consumption Component Classes | EDI021 ISD entities document shows that the settlement period quality indicator in entity M5 is a comma separated list of possible values. This will be difficult to use in systems that need to refer to this data. Could this instead show Actual or Estimate? Alternatively could this be split into parent and child entities to avoid a comma separated list? Metering Service ID MPID is incorrect and must be changed to {MS Id} also in ISD Entity M8 |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Amendments relating to “Valid Settlement Period Quality Indicator Set” wording and field length in section M5 of EDI021 ISD entities document. Change also made from Metering Service ID MPID to Metering Service {MS Id} in Entitiy M8. An objection was raised against this DIN. Following discussion at the DRG about this DIN it has now been moved to Interim Release 5. A decision was made at DRG to go with OPTION 2: Change Existing Layout – Remove list element in favour of individual row(s) for each valid combination for the Valid Settlement Period Quality Indicator Set. Option 2 changes have been implemented to section M5 of EDI021 ISD Entities. Following the change to the layout the amendments to the data item will revert back to its initial name of Settlement Period Quality Indicator. and a data type length of 5 characters | EDI021 ISD Entities | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-410 |  | DI-487 | 2023-06-14 | St Clements | 5542 | Virginia Patey | Software Provider | DI-487 definition incorrect for REP-002 on Swagger | DI-487 energised MPANs is defined as an Integer in the Interface Specification, yet is defined as a String in Swagger. |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | DI-487 updated in Swagger 1.2 to align with Interface specification for REP-002 | Data interface correction | Supporting Docs |  | Swagger 1.2
MHHS-DIN-411 |  | Migration | 2023-06-14 | ESG | 4810 | Patricia Parker | Software Provider | Migration Segment Categorisation | The Migration Design currently specifies that Market Segment needs to be recorded before the Migration phase. This should be changed so that it is no longer required. Until an MPAN is migrated, there is no way of maintaining the market segment between the RS and EES using the legacy interface between these two services. However, meter type and connection type will be available in both the EES and the RS, so Suppliers can use a combination of these values to derive the correct market segment. |  | Closed | [6 empty] | #REF! |  |  | #REF! | 03/08: SCS confirmed in a session with SC that they agreed that Segment is a derived value based on Connection Type and MTR. There are validation rules that prevent the migration if Connection Type (and therefore segment) is not already defined in REGS. To address the original question Segment will always be known at the point of migration. Therefore, no changes are required to Migration document. 13/07: John Wiggins to have offline discussion with Sean C as DIN requires wider discussion at DRG to progress SRO Team disagree with this Migration Request. Market Segment must be known prior to the selection of MHHS Service Providers. Market Segment is a derived field based on Connection Type and Meter Type. Connection Type must be set before Migration / Meter Type already known so Market Segement CAN be derived, set and maintained prior to MPAN migration. No change to baseline documentation Required.
MHHS-DIN-412 |  |  | 2023-06-14 | MHHS | 5022 | John Wiggins | Central Body | Update to MDD | Migration request to ensure that Elexon add MHHS as a value to MDD. Page 35 of the Design Document under Reverse Migration states that -A default MPID of ‘MHHS’ will be created for the DC, MOP, DA appointments. Will MHHS be contained within MDD as a valid set as there is no reference in the document to update MDD with this value. |  | Closed | No |  | Design gap | TBC |  |  | #REF! |  |  | #REF! | As the Migration documentation was approved via DAG and following discusion with RecCo and BSC the updates are being documented in. This is being picked up in an update to DES196 Dflow interface |  |  |  | DES196
MHHS-DIN-413 |  | Migration | 2023-06-14 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | Reading Type (J0171) will be updated with three new values: Forward Migration CoA Forward Migration CoS Reverse Migration CoS Reading Type (J0171) will no longer use Initial or Final for migration reads between Suppliers or DC/DS but one of the above new codes will be used. Meter Reading Reason Code (J0332) will no longer be used to identify migration reads, all reference to this will be amended to Reading Type (J0171) in the guidance document. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | This DIN replaces DIN-442. Introduction of a new worksheet called 'Migration Change' reflecting the D-Flows changes supporting migration. Reading Type (J0171) has three new Reading Type values as follows: V - Forward Migration CoA X - Forward Migration CoS Y - Reverse Migration CoS For the other part of the DIN, "Reading Type (J0171) will no longer use Initial or Final for migration reads between Suppliers or DC/DS but one of the above new codes will be used." - This already exists in the Migration documentation therefore no change on this. | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-414 |  |  | 2023-06-14 | British Gas |  | Mohammad Amin Fuggawala | Supplier | D0275 in D-Flow Document | Ref Previous DIN-244. In the "DES196 D-Flow Document" the D0275 is showing as redundant. This is misleading it should be marked as by agreement between contracting Supplier-DS. Document should be updated to reflect this. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Centrica have been notified on closure of DIN. Update was delivered in the published V1.0 of DES-196 as part of July DAG and the updated version is available on the Collaboration Base. | No Change
MHHS-DIN-415 | RT |  | 2023-06-14 | Elexon | 5702 | Mike Ceney | Central Body | Routing IF-026 to LSS | IF_026- For Routing Rules it states for Event Code/Conditions [SSC], [ProfileClass] and [SSCandProfileClass] that this should be routed to MDS, is this incorrect as MDS does not use these items in any calculations or outputs, this should state LSS |  | Implemented | [5 empty] | Interim Release 2 | #REF! |  | Interim Release 2 | #REF! | IF-026 [SSC] and [ProfileClass] have been removed as of Interim Release 1. Update DES138 IF-026 to route to LSS on event [SSCandProfileClassChange] | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-416 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-001 New App Scenario Code MCS (Migration Change of Supplier) | Create new Appointment Scenario Code of MCS |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | IF -031 New valued added to DI-800 data catalogue and Swagger 1.3 updated to reflect new value | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-417 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-002 Validation Rules for Scenario MCS (Migration Change of Supplier) | New Val rule to check MCS is only used for legacy non-migrated MPAN where Supplier is not current supplier (and not in past) |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-418 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-003 New App Scenario Code MCA (Migration Change of Agent [Service Provider]) | Create new Appointment Scenario Code of MCA |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | IF-031 New valued added to DI-800 data catalogue and Swagger 1.3 updated to reflect new value | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-419 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-004 Validation Rules for Scenario MCA (Migration Change of Agent [Service Provider]) | New Val rule to check MCA is only used for legacy non-migrated MPAN where Supplier is current supplier and now active Switch is in progress (and not in past) |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-420 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-005 - IF-31 Check valid MHHS Supplier | If MCS/MCA code used is Supplier a valid MHHS Approved/Registered Supplier |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-421 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-006 - Prevent use of Migration Scenario IDs | IF MCS/MCA code used for already migrated mpan - reject appointment for invalid Scenario code(s) |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-422 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-007 Connection Type/Segment not yet Populated | New error required if Connection Type, DUos Tariff ID or Segment is not set prior to migration. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | New Validation Rule created for IF-031 to check that MHHS Standing Data is present and aligned. REG0011 Error created to support this validation Rule. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-423 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-008 Auto Realign Functionality | New REGS Requirement - Only action the auto-realign functionality on MPANs where both Linked MPANs are in a Migrated state. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | New Req RS-146 added to REGS Requirements Document to ensure that Auto-Align functionality is only executed if all MPANs in a related and/or linked group have sucessfully migrated to MHHS Operation. | Requirement correction | Meter to Bank | Requirements Documents | BRS-003-Registration Service Requirements
MHHS-DIN-424 |  | DI-185 | 2023-06-16 | St Clements | 5335 | Madison Layton | Software Provider | MPRS access to correlation ID | IF-019 is sent to the LDSO for LinkedImportExport event codes, if the LDSO approves the request they will submit an existing DB05 flow into MPRS. If the DB05 is accepted by MPRS, it will send an IF-020 to the Supplier to confirm the change to Linked Import Export association. However MPRS would not have access to the correlation ID that was received by the LDSO on the IF-019, and so would use a new correlation ID on the IF-020. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | IF20/IF19 Note amended explaining that it will not be possible to Link IF-019/IF020 messages together using Correlation ID , in the case of Linked MPANs. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-425 | SC | Migration | 2023-06-19 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | 8.1.3 step 12 Migration Design Document : Validation Status (J0022) references will be updated to Meter Reading Flag (J0045) |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | 8.1.3 step 12 Migration Design Document : Validation Status (J0022) references will be updated to Meter Reading Flag to T or F (J0045) | Design Ambiguous | Supporting Docs | Interfaces | Migration Design Document
MHHS-DIN-426 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG-009 New Rejection Code for D0205/D0203 | Response to a D205 is a D0203. 1. A New Rejection Condition/Code is required where D0205 is received following processing of IF-031. 2. Proposed new D0203rejection code is 62 "MHHS Fwd Migration in Progress or Completed" |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Point 1 already exists in the Migration documentation therefore no change on this. Point 2 is satisfied by updates in DES-196. Introduction of a new worksheet called 'Migration Change' reflecting D-Flows supporting migration. (J0107) Rejection Reason Code 62 added with the following details "MHHS Fwd Migration in Progress or Completed" | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-427 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-010 ISD Change M16 | No change Required - SCS can use ISD M16 - which contains MIPD/DIP Role and Effctive From date. This can be used to determine if a Supplier is MHHS qualified. This is better apporach that adding a transiant "Qualified Yes/No" field to this table. Therefore NO changes to documentation required. |  | Closed | [6 empty] | #REF! |  |  | #REF!
MHHS-DIN-428 |  |  | 2023-06-19 | British Gas | 5835 | Neil Strange | Supplier | MEX before SSD scenario | When a CoS is in progress and there is a MEX before SSD, how will new supplier get the MEX details As the incoming supplier has already received the IF36 - would there be a new IF36 or would it be a PUB006? In addition how would the new MS and DS be made aware of this? - the old MS has X days after the job is completed to update the industry and a CoS could have happened before the old MS can update the other participants. |  | Closed | [6 empty] | #REF! |  |  | #REF! | BAU Design deals with 'regular' MEX before COS type scenarios (note previous MS Update Period - PUB-006 would be issued to impacted parties). Complexity arises where there is a COS overlapiing with Change of Segment/Connection Type (ie SEG Appointment)... Following discussion with SCS - low probably, low occurance vs. complex change. Ref existing guidance on BP016 there would need to be a manual interaction between Supplier and MS. No Change to existing Documentation Required.
MHHS-DIN-429 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG-011 Changes to D0170 | 1. Change D0170 flow so that MPRS/Registration Service is valid Sender of this flow. 2. New value for "Request Action Code" is needed to denote a Migrating account and if its CoS or ChgOfSP method. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Introduction of a new worksheet called 'Migration Change' reflecting the D-Flows changes supporting migration added in DES-196. Point 1. D-Flow ID (D0170) Request for Metering System Related Details new Scenario Variant FROM Electricity Retail Data Agent TO Electricity Supplier added. Point 2. Introduce two new Requested Action Code values as follows: 24 - Migrated Metering Point (CoA) 25 - Migrated Metering Point (CoS) | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-430 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-12 New Val Rule for IF-019 | Reject any changes to Related MPANs where any MPAN referenced (or in realted group) is subject to an active Migration SP Appointment Process |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | New Validation Rules and Error Code created to prevent changes if MCA Appointment Type Exists (Note: prevention if MCS exists is realised through existing check on if Switch is in Progress) | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-431 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-13 Change to D0386 | Change D0386 validation to reject changes to related MPANs if any related MPAN in group is subject to active Migration SP Appointment Process |  | Closed | No |  | Design gap | TBC |  |  | #REF! |  |  | #REF! | Update Migration Design Document D0386 validation to reject changes to related MPANs if any related MPAN in group is subject to active Migration SP Appointment Process | Design Ambiguous | Supporting Docs | Interfaces | Migration Design Document
MHHS-DIN-432 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-014 Appointment on Secondary Related MPAN | Extend existing 1039 check to include MCS.MCA Appointment Scenarios. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Existing Validation Rule(s) around REG1039 will already cover Migrating MPANs - No Documentation Change Required.
MHHS-DIN-433 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-015 Switch in Progress Mig Rejection | New IF-031 validation to reject MCA/MCS DS and MS Appointments if an [any] active Switch is in progress with NEW Rejection Reason Code (note 1095 code referenced in Migration document has already been used elsewhere) |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | New validation rules and REG9XXX Exception codes added to ensure correct usage of MCA/MCS Appointment Scenario Codes. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-434 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-016 New IF-003 | Previously DIN-247, Introduce IF-003, no changes from original proposal. 1. Update DES138 new tab, update IF List. Update New Data Items 2. Review E2E doc. 3. Update secondary Routing Rules (Avenade Techncal Doc) to include 4. Update Swagger |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Add data items DES138-Interface data Cat and to IF-003. Created new Data items: DI-500 MHHS Regime End Date, DI-501 Rev Migration Incoming MOP MPID, DI-502, Rev Migration Incoming MOP Eff From Date, DI-503, Rev Migration Incoming DC MPID DI-504 Rev Migration Incoming DC Eff From Date. Swagger v1.3 updated to reflect new IF-003, Blocks (B096/B095/B094) & Data Items (as above). | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-435 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG-017 D0304 & D0303 | 1. New D0304 Validation Rule 2. New D0304 Rejection Reason Code "Q - MPAN Fwd migration in progress or completed" 3. Change D0303 so as to make "Eff From Settlement Date REGI" a non mandatory data item within the flow (an alternative to suggesting that outgoing MS no longer issues a D303, only the incoming MS would send) |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Introduction of a new worksheet called 'Migration Change' reflecting the D-Flows changes supporting migration added in DES-196. Point 1 already exists in the Migration documentation therefore no change on this. Point 2 New Response Code Q "MPAN Fwd migration in progress or completed" added against J2255 MPAS D0304 Response Code as part of D0304. Point 3 Change requirement to populate this date from Mandatory to Optional against J0049 Effective from Settlement Date {REGI} as part of D0303. | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-436 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG0-018 D312 | 1. New D03012 Validation Rule 2. New Rejection Reason Code "AD - MPAN Fwd migration in progress or completed" |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Point 1 already exists in the Migration documentation therefore no change on this. Point 2 is satisfied by DES-196. Introduction of a new worksheet called 'Migration Change' reflecting D-Flows supporting migration. against J2256 MOP Flow Response Code as part of D0312 | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-437 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-019 IF-005 Validation Rule | 1. New val rule to prevent IF-005 while MCS/MCA Appointment is in progress 2. New Error Code (REG9003) |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | REG9003 - MHHS MTD Updates cannot be used until Migration has completed, Created and new validation rule added to IF-005 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-438 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-020 REGS Design Clarification | SCS Should issue L1/L2 Msg Status message with RCP1061 for any MPAN at the incorrect status where a DIP Message is received |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | This is a Migration Requirment which participants should take into account as part of their Migration Designs. However, for clarity a note has been added to RCP1061 entry in the Intoduction Section of the Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-439 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-021 No Supplier Updates during Rev MIgration (IF-025) | 1. New If-025 val rule to check if Rev Migration Switch is in progress 2. New error code |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | REG9002 - Supplier Data Items Cannot be Maintained for Reverse Migration Account, Created and applied to IF-025 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-440 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-022 No CDCs Updates during Rev MIgration (IF-038) | 1. New If-038 val rule to check if Rev Migration Switch is in progress 2. New error code |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | "REG9001 - CDC Marker Cannot be applied to Reverse Migration Account", created and applied to IF-038. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-441 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-023 No AC Updates during Rev MIgration (IF-040) | 1. New If-040 val rule to check if Rev Migration Switch is in progress 2. New error code |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Annual Consumption Method Statement section 5 has been updated with the text below in red: Where an MPAN is no longer active under MHHS during the transition phase the Market-wide Data Service shall not calculate or submit an annual consumption on the IF/PUB-040. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption
MHHS-DIN-442 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-024 D0010/D0086 New MR Reason Codes | Three new MR Reason Codes for use in D0010: Forward Migration COS / Forward Migration COA / Reverse Migration |  | Closed | [6 empty] | #REF! |  |  | #REF! | Original migration design. Superceded by DIN-413.
MHHS-DIN-443 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG-025 D0155 New Agent App Reason Codes | 1. New Valid value for service reference "REVM" 2. New valid value for Service Level "REVM" |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | D-Flow Ref D0155 updated for data items J0274 service reference "REVM" and J0275 Service Level "REVM" in DES-196. | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-444 | RS |  | 2023-06-19 | ESG |  | Patricia Parker | Software Provider | IF-01 Incoming supplier for Import/Export MPANs | Clarification required with SCS. If it is known that an alternative MPAN has the same SSD then we do not want the old supplier ID as the linked supplier on the IF-01, we want the new supplier to be populated |  | Closed | [6 empty] | #REF! |  |  | #REF! | Discussed with SCS and they have confirmed that where co-incidnet COS occurs they would look to populate the [new/incoming] Linked Supplier ID.... No change to documentation required.
MHHS-DIN-445 | SB |  | 2023-06-19 | Utiliteam |  | Richard Palmer | Software Provider | Spec of IF-024 in DES138 Interface Catalogue | The Population Notes for DI D-000 in Group S0 has ‘IF-025’. This error was in v5.0, and is still in v5.1.1 |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | The Population Notes for DI D-000 in Group S0 has been updated to ‘IF-024’ in IF-024. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-446 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-026 Migration DIP Reporting Reqs | Reqs for x4 new Reports -- Flag at the next DIP DAG |  | Closed | No | [5 empty] | #REF! |  |  | #REF! | Closed and for the Migration Team to pick up. Awaiting further internal discussions re DIP Reporting Strategy.
MHHS-DIN-447 | SW |  | 2023-06-21 | Kraken | 5980 | Angelos Rizoyannis | Software Provider | Conditional Mandatory not applied in Swagger correctly | IF-041-CustomBlock: The field B065List is stated as optional in the comments, but the API schema does not reflect this. This field that is conditionally optional in DES-138, but this is not defined as such in Swagger ie, OneOf, AnyOf. This needs to be updated in Swagger to align correctly. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | In Swagger 1.3, updated IF-041-CustomBlock: The field B065List and B064List will be either / or as they are defined as conditionally mandatory in DES-138. This uses AnyOf notation in Swagger. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-448 | SW |  | 2023-06-21 | Kraken | 5980 | Angelos Rizoyannis | Software Provider | Mandatory fields not applied correctly in S1 block | S1 Common Block: The 'properties' and 'required' sections of the API schema for the S1 common block have conflicting information. The 'properties' section includes fields like senderTimestamp and senderRoleID, while the 'required' section lists sentTimestamp and senderRole. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Updated Swagger 1.3 to align properties and required sections so that fields are called senderTimestamp and senderRoleID. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-449 | SC |  | 2023-06-21 | SRO Design Team |  | Sean Cooper | SRO Design | Change to IF-037 | Include Block B002 into IF037 so that outgoing MS is aware of incoming Supplier on a COS. This will allow the SP to populate the D0303 to MAP. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Block 002 added to IF-037 for use where event code is MSDeapp, this is so that the outgoing MS is informed of who the incoming supplier is so that D303 can be correctly population. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-450 | SC | DI-196 | 2023-06-22 | RECCO |  | Sean Cooper | SRO Design | Change to IF-005 Validation Rules | Change made to IF-005 validation Rules to allow previous MS to update Meter Location only - during the 10 day post appointment period. This will allow for scenarios where there has been relocation only activity immediatly prior to a change in MS. All other MeterUpdate functions apart from Change of Meter Location shall be rejected per wider agreement that only active MS should have the ability to change the characteristics... This change originated from R1 Comments feedback from RECCO |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | IF-005 Validation rules updated to include new "REG0008 - Amendment Requested cannot be undertaken by Previous Metering Service" error condition and code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-451 | SC | CR-018 | 2023-06-22 | Design Team |  | Sean Cooper | SRO Design | CR - 018 Registration Service OOH Ops | CR18 looks to specify Registration Service Out-Of-Hours Operations. | CR018 | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Following feedback provided on the redlined version of the Operational Choreography, and following discussion on CR018 at PSG, the SRO maintained the DAG Chair’s decision to approve the implementation of CR018. CR Contents incorporated into a new Section 7 of Ops Choreography Document. Updates to clarify low level processing details in Section 7 Out-Of-Hours Processes table. Following feedback from DNO Review - Additional updates to replace the term ‘SLA’ with the phrase “target response time(s)”. Changes to Column headings to ‘When’ across the Operational Choreography document to align with Code Drafting convention. Addition of Intro text and removal of text “or Performance Regime” in Section 5. | Technical corrrection | Supporting Docs | Operational Choreography | MHHSP_OPC001_Operational_Choreography
MHHS-DIN-452 | SC |  | 2023-06-22 | St Clements |  | Sean Cooper | SRO Design | Refine Consent Checking Rules on IF-031 | Further refine Consent checking rules so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing . Updates to IF-031 validation rules to reflect this change. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | IF-031 validation rules updated per the DIN Details. Consent checking rules added so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-453 | MF | DI-124 | 2023-06-22 | St Clements |  | Mike Fensome | SRO Design | Issuing of IF-020's | Highlighted that LDSO's could issue an IF-020 with details of import/export linkages without having received notification from the Supplier |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Added note to IF-019 and IF-020 to inform Suppliers that Import/Export linkages could be received via PUB-020 unprompted by the Supplier issuing IF-019. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-454 | SC |  | 2023-06-26 | St Clements |  | Sean Cooper | SRO Design | Update to ISD M7 | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service. added rule to support REG0011 logic in IF-031. | Requirement correction | Supporting Docs | ISD Document | MHHSP-DES138-Interface Catalogue MHHSP-EDI021-ISD Entities
MHHS-DIN-455 | SC |  | 2023-06-23 | St Clements |  | Sean Cooper | SRO Design | Update Op Choreography (Event Move from IF-013 to IF-014) | Update Ops Choreography to take account of the movement of event [ConsumptionOnDeEnergisedMPAN] which was moved from IF-013 to IF-014 (DIN-255). |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | IF-014 Deadline split into two. First [ActivePowerRejected] remains UNCHANGED. Deadline for [ConsumptionOnDeEnergisedMPAN] is also UNCHANGED but moved from IF-013 row into IF-014 Row, to mirror the change delivered by (DIN-255). OPC_580 ID details updated in OPC001 Operational Choreography document. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP_OPC001_Operational_Choreography
MHHS-DIN-456 | SC |  | 2023-06-23 | St Clements |  | Sean Cooper | SRO Design | Swagger Correction - DI-844 | Corrected x2 invalid referenced to "AssignedMRDRequestEffectiveFromDate" should have been "AssignedMRDEffectiveFromDate" in Block 066 |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Corrected x2 invalid referenced to "AssignedMRDRequestEffectiveFromDate" should have been "AssignedMRDEffectiveFromDate" in Block 066 | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-457 | SC |  | 2023-06-23 | St Clements |  | Sean Cooper | SRO Design | Change to DTN Validation of D0350 | Implement DTN Validation of D0350 to prevent future dates |  | Implemented | No |  | Design gap | TBC |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | CP Required for further clarification | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-458 | SC |  | 2023-06-23 | St Clements |  | Sean Cooper | SR Design | New IF-019 Related MPAN Validation Rule | New Validation Rule required for IF-019 to ensure that only Import MPANs can be related. Add to Create and Add Related - this is per REC Shedulle 28 |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | New Rules added to IF-019, [RelatedAdd] and [Related Create] events to ensure only Import MPANs can be in a related Group. New Error code added to support these new rules REG1067 - Only Import MPANs can become Related | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-459 | SB |  | 2023-06-23 | Utiliteam | 5724 | Richard Palmer | Software Provider | Spec of IF-024 in DEL138 Interface Catalogue | A further suggestion re the Interface Spec for the IF-024: The Event Code list in DI D-999 in Group S0 contains [SN-RemoteEnabled] & [SN-RemoteDisabled]. I would suggest that these are invalid for Segments Advanced and Unmetered. Also [SN-Vacant] would appear to be irrelevant for Segment Unmetered, and I doubt that [SN-NoComms] would be valid either. These existed in v5.0, and are still in v5.1.1. Perhaps the routing rules need some improvement? |  | Closed | [6 empty] | #REF! |  |  | #REF! | No change Required. Useage of these evernt codes is obvious and is described in the Requirments documents as necessary
MHHS-DIN-460 | SB |  | 2023-06-26 | Utiliteam | 5939 | Richard Palmer | Software Provider | PIF-019 structure & Principle -> Principal | Also, in the relationships between MPANs, the ‘main’ one is the ‘Principal’ one – not the ‘Principle’. This will be embarrassing if left uncorrected. It is still in v5.1.2 in IF-019, and it is in many other places. If there is a chance of correction, please take it. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Spelling mistake corrected in Data Catalogue, IF-019, IF-020. Note YAML name also corrected for DI-073. | Data interface correction | Supporting Docs | Interface Changes | MHHSP-DES138-Interface Catalogue Swagger 1.3
MHHS-DIN-461 | SW |  | 2023-06-26 | Greenbird | 1768 | Fredrik Omland | Software Provider | Misalignment between DES-138 and Swagger for DIP Connection Provider ID | In DES-138, In the S1 block, DI-996 (Connection Provider DIP ID) is defined as Optional. But in Swagger, this is defined as mandatory. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Updated Swagger 1.3 so DI-996 in S1 block (Connection Provider DIP ID) is Optional to align with DES-138 | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-462 | SW |  | 2023-06-27 | Design Team |  | Steve Weston | SI Design | Schema Optionality incorrectly defined for some Interfaces | In DES-138, there are are a number of Interfaces where the Schema Optionality is defined as Optional, rather than Mandatory. The list of Interfaces are as follows - IF-050 / B022, IF-023 / B053 and IF-013 / B049 |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Updated Schema optionality in DES138 to show that all data items must be present where the block is present in line with updated E2E Solution Architecture for IF-050 / B022, IF-023 / B053 and IF-013 / B049. | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalouge
MHHS-DIN-463 | SW |  | 2023-06-27 | SIMS |  | Kyle Abraham | Software Provider | No ability de-register from receiving Status messages in Swagger | In Swagger, there is a POST method for /statusmessage/config, but there is no DELETE method, so you are unable to delete / de-register for any status messages. Need to update Swagger to ensure this is possible. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Updates made to Swagger 1.3, so there is a DELETE method for /statusmessage/config, so you are now able to delete / de-register for any status messages. Updated so that all of the Interfaces accept the same 4 security headers required for message signature and validation. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-464 | SW |  | 2023-06-27 | SIMS |  | Kyle Abraham | Software Provider | Clarity required on values expected for /dip-channel/{id} for submitEvents on Swagger | The {id} in /dip-channel/{id} for submitEvents on Swagger should accepts values that are the same as the enumeration in DI-000 to ensure consistency. At the moment, this is not clear in Swagger or E2E001 design, so this needs to be updated to make this clearer. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Updates made to Swagger 1.3, so there the correct enumerations / values are available to align with values in DI-000 to ensure consistency and avoid any ambiguity between interfaces and reports. Updated to remove PublicationConfig and RestConfig in favour of a single config WebhookConfig. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3 |  |  | Interim Release 2.2
MHHS-DIN-465 | SC |  | 2023-06-28 | RECCO |  | Sean Cooper | SRO Design | Update to BP010 - Related MPANs | The process MPAN for Related MPANs does not clear call out the Rejection pathway. Update Business Process to show rejection process. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | BP010B Related MPANs Process updated to show specific Rejection Route. | Process Model correction | Metering Changes | Business Process Documentation | BP010- Changes to MPAN Data
MHHS-DIN-466 | SC | DI-188 | 2023-07-29 | St Clements |  | Sean Cooper | SRO Design | Change of MPAN Status during Service Provider Appointment Process. | How should a change of MPAN Status be dealt with whilst there is an ongoing SP Appointment that has not yet reached the stage of IF-034 processing !? If an MPAN is disconnected between PUB-031 acceptance and receipt of PUB-034, the SP PUB-034 Response would be rejected by MPRS due to validation rule REG1001. The appointment would not be progressed but would be stuck in the MPRS queue at status Requested. Could resolve by amending REG1001 validation on IF-034, to not apply to event codes MSAppSPResponse or DSAppSPResponse. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Resolved following discussion with SCS, Agreed that SCS will take no action until the IF-034 has been processes. A change to REG1001 validation on IF-034, to not apply to event codes MSAppSPResponse or DSAppSPResponse, is required to allow the IF-034 to processes normally (when where MPAN is disconnected)... Following processing of the IF-034 RESG will then immediatly issue an IF-035 with reason code of "1- Lapsed as MPAN Status is Disconnected" ... ... Agreed that this was best resolution both for REGS processing rules and participants as no change to currently expected message patterns/ordering. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-467 | SC |  | 2023-07-29 | ESG |  | Sean Cooper | SRO Design | Review of IF-035/IF036 Data Item Obfuscation | Review of IF-035/IF-036 Data Item Obfuscation |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Various updates to obfuscation on IF-036 to align with IF-035. DI-019/DI-800/DI-809/DI-207 obfuscated for Data Service DI-020/Di-800/DI-126/DI-842/DI-209/Di-844/DI-811/DI-208 /DI-018 obfuscated for Metering Service | Data interface correction | Supporting Docs | Interface Catalogue | MHHS-DES138-Interfaces
MHHS-DIN-468 | SC |  | 2023-07-29 | Helix |  | Sean Cooper | SRO Design | Routing of IF-020 | Helix have confirmed that they DO NOT need to receive Related/Linked MPAN information therefore an update is required to REMOVE MDS from the receipient list for this IF-020 |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | IF-020 Routing table has been updated to REMOVE MDS as being a recipient of any IF-020 messages. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-469 | ME |  | 2023-06-30 | SRO Design Team | 2109 | Rob Golding | SRO Design | Removal of Z0 & Z1 data items in ERI011B - ECS Reports External | Z0 & Z1 data items to be removed from from the each of the MHHS reports within ERI011B - ECS Reports External as they are no longer in the common block |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Removed Z0 & Z1 data items from all MHHS reports in ECS external reporting artefact | Data interface correction | Minor | ECS Reports | ERI011B - ECS Reports External
MHHS-DIN-470 | SW |  | 2023-06-29 | Callisto | 1805 | Seth Chapman | Software Provider | Clarity on nullable fields | Section 4.2.2 in the E2E design provides information on Optional / nullable fields, but worked examples would provide further clarity for each of the data types / link to JSON specification. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Updated section 4.2.2 with worked examples for each data type to provide additional clarity. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-471 | MH |  | 2023-06-30 | Helix |  | Derek Weaving | Central Body | Update to REP-003 in ERI011B - ECS Reports External | R019 parent should be R017 in the ECS Reports External and Swagger |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Updated R019 parent to R017 for REP-003 in ERI011B - ECS Reports External. Swagger v1.3 updated to align with changes within ECS reports artefact. | Data interface correction | Minor | Interface Changes | ERI021 -ECS Reports External Swagger 1.3
MHHS-DIN-472 | SW |  | 2023-06-29 | SRO Design Team | 2006 | Rob Golding | SRO Design | Onboarding migration from Test to Production. | “The programme is to implement a strong PKI policy but as per the diagram states that that on promotion, parties will be able to copy their Test setup and to use that for connecting to the Prod environment. - steps 1-8 - There are no steps in this sequence that test the connectivity to the Live DIP environment. To this point the only connectivity testing has been to the Test environments. This is a significant failure point / risk. At this point Webhooks and certificates will change (mTLS and JSON signing) from those used in Test as well as potentially some of the PKI resources assigned to roles ( those used in test may not be applicable to Prod) we would expect that this would require a new Connectivity proving period with the Prod environment similar to that being developed for CIT. Without such proving, how can the programme assume all parties will connect to the Prod environment successfully and ensure minimal impact to migration events”. |  | Closed | [6 empty] | #REF! |  |  | #REF! | This an Elexon/DIP Manager deliverable not a programme deliverable
MHHS-DIN-473 | SB |  | 2023-06-30 | MHHS | 2111 | Jason Brogden | Network Operator | Definition of Network Operations | Issue: There is a lack of clarity in the scope of Network Operations activities in testing. Action to Resolve: Add a definition to the Programme Glossary that makes clear the scope of Network Operations (as referenced in Testing material) is equivalent to the scope of LDSO activities in the MHHS Design Baseline: Network Operations systems and services are those that are required to deliver the elements of the MHHS Design Baseline that are allocated to the LDSO role. Communicate this to the DNO and iDNO community and associated service and software providers. For the DIN Log, we can then focus on updates to the BRS to give the necessary clarity on the scope of MHHS Design. Issue: There is a lack of clarity in the scope of LDSO activities in the MHHS Design Baseline as BRS005 implies MHHS-related processing requirements at LDSOs for received DIP messages, whereas the BPs and BPDs define the scope of MHHS as ending at the receipt of DIP messages. BRS005 is described as “For Guidance Only” at the top and this is to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing). Action to Resolve: For the avoidance of doubt and to provide clarity to BRS005, it is proposed to change the “For Guidance Only” note at the top of BRS005 to the following description as per the above: BRS005 is provided For Guidance Only to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing). |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | LDSO Requirements document updated with the following text, "BRS005 is provided For Guidance Only to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing)." | Requirement correction | Minor | Business Requirements Documentation | BRS-005 LDSO Overview.xls
MHHS-DIN-474 | ME |  | 2023-07-03 | MHHS |  | Kevin Spencer | SRO Design | Creation of new ECS data items and blocks across multiple reports and/or data catalogue | Report definitions incorrect and require updates and new data items following internal review |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Addition of data items DI-503, DI-505-DI-515 to data catalogue and across ECS reports artefact. MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal Missing data items added to data catalogue Di-403/DI-404/DI-514/DI-515 | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-475 | ME |  | 2023-07-03 | MHHS |  | Kevin Spencer | SRO Design | Update to block names, data items and descriptions | Report definitions incorrect and require updates and new data items following internal review |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Update to block names, DTN references, data items, descriptions and reordering of data item blocks to exisiting reports in MHHSP - ERI011B - ECS Reports - External | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-476 | SW |  | 2023-07-03 | Greenbird | 2035 | Fredrik Omland | Software Provider | Inconsistency between enum fields and nullable definition | Looking at DIP Interfaces Swagger 1.1 (also 1.2 + 1.3), the enum typed fields that are nullable may not comply with OpenAPI specification (for 3.0.x). The topic around enum fields with nullable: true has been clarified/answered by OAS project (amended in spec version 3.0.3 in 2021): (Reference: https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md ) |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | To align with Open API spec clarification at https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md, we have updated all Data Types that are nullable and have an enum to align as follows: Following discussion, have decided to align with OpenAPI 3.1 DI-076-Estimation-Reason-Code: description : Used inconjunction with Settlement Period Quality Indicator to explain why data has been estimated type : string nullable: true maxLength : 2 example : '1' enum: - '1' # OptOut - '2' # Missing .. - '8' # Disconnected - '9' # Consumption Amendment - '10' # NonSmart - null The Data Types affected / updated as follows: --- DI-039-Load-Shape-GSP-Group-ID --- DI-076-Estimation-Reason-Code --- DI-096-Site-Visit-Check-Code --- DI-126-Traditional-Fall-Back-Read-Frequency --- DI-137-IHD-Install-Status --- DI-150-Annual-Consumption-Quality-Indicator --- DI-166-Supplier-Consumption-Amendment-Reason-Code | Data interface correction | Minor | Interface Changes | Swagger 1.3
MHHS-DIN-477 | SW |  | 2023-07-03 | MHHS |  | Steve Weston | SRO Design | Swagger alignment to OpenAPI 3.1 specificiation | Align with Open API specification 3.1 to remove nullable :true and replace with type declaration ie, type:[string:”null”] | CR049 | Closed | No |  | Design ambiguous | DIP Users | [6 empty] | Align with Open API specification 3.1 to remove nullable :true and replace with type declaration ie, type:[string:”null”] | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-478 | SW |  | 2023-07-03 | MHHS |  | Rob Golding | Central Body | IF-021 max number of days of consumption data | In the Release 2 version of DES138 a limit was introduced that asked Participants not to submit more than 150 Settlement Days’ worth of data in a single message. The value of 150 was proposed as this meant a single message would realistically be ~600KB in size. We’ve had some queries regarding this value, the proposal is to increase sizing from 150 to 194 day message and the size increases from 600KB to ~780KB for IF-021 message. ECS will need to validate the message contents. However, rather than letting a ‘large’ IF-021 message traversing though the DIP, the proposal is to limit the IF-021 on ingress to the DIP and a single request will have a limit of 1MB – this will be done at the API level. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Agreed to limit the number of MQ IDs per IF-021 submission to ONE only and limit settlement days to 200. Swagger has been updated to limit the number of MQIDs to 1. Swagger updated to limit the maximum number of Settlement Days to 200. DES138 also updated to aligned with the above changes for IF-021. | Data interface correction | Minor | DES138 and Swagger | DES-138 and Swagger 1.4
MHHS-DIN-479 | SC |  | 2023-07-03 | St Clements |  | Maddison | SCS | Change to Consent Notification on IF-036 | SCS have suggested that B068 should only be required for DSApp Events. |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | Block 068 on IF-036 amended to that it is only Mandatory for DSApp Events. | Data interface correction | Supporting Docs | Interface Change | DES138-InterfaceCatalogue
MHHS-DIN-480 | SC | DI-195 | 2023-07-03 | St Clements |  | Maddison | SCS | Reverse DIN-105 | SCS have confirmed that it is possible currently and should continue to be possible to manage MPAN Linkages whilst MPAN(s) are at Created Status. Therefore we have reversed the change implemented at part of DIN105 and now allow processing of IF-019 if mpan status = "Created" |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | SCS have confirmed that it is possible currently and should continue to be possible to manage MPAN Linkages whilst MPAN(s) are at Created Status. Therefore we have reversed the change implemented as part of DIN105 and now allow processing of IF-019 if mpan status = "Created" | Data interface correction | Supporting Docs | Interface Change | DES138-InterfaceCatalogue
MHHS-DIN-481 | SW |  | 2023-07-06 | Elexon | 2106 | Nigel Rees | Central Body | REP-003 inconsistency between DES-138 | We have a contradiction between the DT-023 and the swagger spec. As there is an example we will implement based on the example but it looks like the person who wrote the ECS report catalogue used the correct convention. e.g. on REP-003 we have DT-023 as NUM (16,6). If we follow the convention used in the DIP interface spec, this would translate to 1234567890123456.123456, however the swagger suggests 123456789.123456 Screenshot from REP003 in external ECS reporting catalogue https://app.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.3#/components/schemas/DT-023-Positive-Decimal-9-6 DT-023-Positive-Decimal-9-6: description: Number (9,6) format type: string pattern : ^[0-9]\d{8}(\.\d{6})?$ example: 123456789.123456 |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Two new data type references have been created DT-024 and DT-024N. For NUM(16,6) data type within ECS reports/ECS data catalogue replace DT-023/DT-023N with DT-024/DT-024N. DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. 31/08: A reconciliation exercise is being carried out internally of the ECS data catalogue to assess data types. Further work may be required to swagger following the reconciliation. Reconciliation task has been completed which has resulted in updates to the MHHS Data Types within the ECS Reports data catalogue. MHHS data type references in Swagger have also been updated to align with these changes. An example of how MHHS data types should be interpreted: String 17 should be interpreted as NUM(±9.6) which can be physically represented in this way for a negative number -123456789.123456 or for a positive number it will be 1234567890.123456. The objection has been removed. | Reporting correction | Minor | ECS Reports | "MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2" Swagger
MHHS-DIN-482 | KH |  | 2023-07-10 | C&C | 2394 | Hazel Cotman | Software Provider | Interim Release 2 query - IF-018 | LDSO’s are not detailed as ‘To Parties’ within IF-018 flow, however, the LDSO is a secondary routing party for updates to the Domestic Premise, Energy Direction Indicator, and the Metered Indicator |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | LDSO's added to the To party list of IF-018 | Data interface correction | Minor | Interface Catalogue | DES138
MHHS-DIN-483 | KH |  | 2023-07-10 | BGAS | 2410 | Neil Stranger | Supplier | MHHS Design Query - date/ time in DES138 | In DES138 there are a number of data items that are defined as having a date/time structure, but the name and description only refer to the date element whereas others refer to date and time. Therefore for those that make no reference to time we need to be 100% clear if the time should be when the event occur or should it be defaulted to say midnight. This is to ensure consistent population/use across the market. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Related to a Design Principle and agreed as per E2E Architecture
MHHS-DIN-484 | SW |  | 2023-07-10 | Design Team | 2352 | Martin Freeman | Central Body | Clarity on RecipientId and SenderID in StandardResponseBodyType | RecipientID in the Standard Response Body is a mandatory field. When submitEvents (or in IR2 dip-channel) is called, the DIP synchronously returns a Standard Response Body. At this point the DIP does not even know what message recipients the message will be routed too, since the response is returned synchronously whereas routing is performed asynchronously. So the DIP has no way to know what to set recipientID to. It is also important to note that a message can be received by multiple recipients, yet this recipientID is a scalar that only supports being set to a single value. So it isn't clear how that could work. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | The Sender of the messages becomes the Recipient of the Response this already outlined in the examples in the E2E SA doc. Update section 4.6.1 in the E2E001 Design document to provide better clarity on how SenderID and RecipientID are populated in the StandardResponseBodyType. Updated Swagger 1.5 to align with the above. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-485 | SW |  | 2023-07-10 | MHHS | 2380 | Steve Weston | Central Body | Unable to identify Recipient on DELETE and some POST methods | For the DELETE methods in Swagger for StatusMessage and PublicationConfig, need to update the method so you can identify the correct recipientID to be used for the method call. Some frameworks will ignore a body on a DELETE method as being incompatible with the semantics of the DELETE method, and the correct RESTful implementation would be something more along the lines of "DELETE dip-channel/{id}/{role}/pubconfig". Which of course raises the question of whether the POST message should be refactored for consistency. The issue is more widespread than just the DELETE methods, it also affects some of the POST methods where a recieipent ID is required |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Design changes required to Swagger 1.4 to support updates to API endpoints for DELETE API verbs to ensure we are able to remove the correct StatusMessage or PublicationConfig for the appropriate recipient combination. The issue also affects some of the POST methods where a recipient ID is required, e.g webhook config. A standard pattern is proposed where a recipeint id is specified in the path. Updates to section 4.5.1 and 4.7 also made to E2E001 design document to ensure the document provides any clarity required. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-486 | SB |  | 2023-07-11 | MHHS | 2107 | Rob Golding | Central Body | DES138 and message addressing information | Please can you raise a DIN to cover the following request from Participant to clarify the From and To Parties at the top of each sheet to align with the role codes the programme is using and defined in the E2E Solution Architecture document. And if these ‘pure’ roles code could be included in the introduction sheet that would certainly help. More detail can be seen in the Ticket |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Update the role codes in DES-138 for the From / To Parties for each of the Interfaces to align with other documents including E2E001. No change to information in the Introductory section in DES-138 required. | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-487 | SW |  | 2023-07-11 | MHHS | 2379 | Martin Freeman | Central Body | Clarity on schema vs data validation failures, with updated examples. | In section 4.4.4.2, there are some examples that incorrectly return a 207 when they have failed schema validation. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | In section 4.4.4.2, there are some examples that incorrectly return a 207 when they have failed schema validation. E2E001 section 4.4.4.2 has been updated to illustrate 2 examples. One that returns a 201 Created (2 messages as part of the HTTP Request, both pass validation) and another example that returns a 207 (2 messages part of the HTTP Request, but 1 does not pass validation). | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-488 | ME |  | 2023-07-11 | MHHS | 1506 | Steve Weston | SRO Design | Correct Reporting Cat vs Swagger | Reinstated DI-484 "Settlement Period Duration" and added into R Groups as required |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Reinstated DI-484 "Settlement Period Duration" and added into R Groups as required in Swagger 1.4 | Data interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-489 | MF |  | 2023-07-11 | Design Team |  | Mike Fensome | SI Design | Schema Optionality incorrectly defined for Common Block | In DES-138, the Common Block shows some fields where the Schema Optionality is defined as Optional, rather than Mandatory. The list of Blocks are as follows - Common Block: S1, D0, A0 |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Update Schema optionality in DES138 to show that all data items must be present where the block is present in line with updated E2E Solution Architecture. Common Blocks impacted: S1, D0, A0 | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-490 | SW |  | 2023-07-11 | Design Team | 2395 | Martin Freeman | Central Body | Level 1 validation clarity for POST /statusmessage be the same as for POST /dip-channel/{id} | The E2E001 v3.2 (section 4.4.3) describes how for the Send Messages API, when the DIP performs level 1 validation, if any message in the request fails validation then the entire request is rejected. Section 4.6 Send Status Messages API does not describe the DIP validation for status messages at all. Should validation for POST /statusmessage be the same as for POST /dip-channel/{id}, in that a level 1 validation failure for any message should fail the entire request, or should messages that pass validation be accepted and messages that fail be rejected independently? |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | This should be consistent across all interfaces in that a schema validation failure for any message should fail the entire request. In the E2E001 design, sections 4.4.3 and 4.6 are to be updated to reflect this / provide the appropriate level of clarity. This issue affects both the http delete operations. Easy to fix, same fix as the post need to include the webconfigas a parameter | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.5
MHHS-DIN-491 | SB |  | 2023-07-11 | Utilita | 2408 | Adam Barnes | Supplier | IF-035 - Update routing to show XDSS | DES138 v5.2.1 - IF-035 tab for the bottom 3 entries it still refers to the previous version definition of routing parties – we expect this to be a slight oversight as SDSS is no longer defined as a recognised party? |  | Implemented | No |  | Error/Correction | N/A |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Update routing for IF-035 to show XDSS for consistency of the documentation, but it will only ever apply to MPANs in the Smart Segment so will in reality only ever be routed to an SDS. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-492 | KH |  | 2023-07-11 | Stark | 2125 | Matthew Peters | Supplier | IF-034 Proposed Appointment Response Code Formatting | The data type within DI-143 block for IF-034 and IF-035 needs to change from String 200 to Array because there is a possibility of getting more than 1 rejection code. |  | Closed | No | [5 empty] | #REF! |  |  | #REF! | Closed - only 1 rejection code is required
MHHS-DIN-493 | SC |  | 2023-07-12 | St Clements |  | Sean Cooper | SRO Design | Changes to IF-019 Secondary MPAN validation | SCS had originally suggested a validation rule to prevent Secondary (Related) MPANs being linked to an Export MPAN. However, RECCO and EON have highlighted there are a very small number of scenarios where this might be the case. Following further discussions with SCS they are now happy to remove this rule (REG1068) |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | IF-019 - REG1068 check for Secondary MPAN Linkage to export REMOVED | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-494 | SW |  | 2023-07-12 | Callisto | 2462 | Neil Edney | Software Provider | Incorrect Min and Max Values for DI-091-Number-Of-Displayed-Register-Digits | DI-091-Number-Of-Displayed-Register-Digits currently has a minimum of 1 and maximum of 1, when this should be 5 and 6 respectively to align with DES-138 as this is an Integer. |  | Closed | [6 empty] | #REF! |  |  | #REF! | This DIN is now superseded by DIN-615 following on from DIN-574. Text against Number of Register Digits field amended to say "per the manufacturer specification". Swagger validation of this field updated to match SCS logical test ie value can be 0-9. This DIN was to ensure there was consistency in Swagger 1.4 to align with DES-138 so that min and max was 5 and 6 respectievly. This objection is related to the values in DES-138, to update from 5 and 6 to 0 and 9, and then align Swagger to the values in DES-138. | No Change
MHHS-DIN-495 | SC |  | 2023-07-12 | Design Team |  | Sean Cooper | SRO Design | Correction to BP003 | IF-035 for Trad/Advanced meters was previously shown as being direct interaction between REGS and MS ... Changed to show message as flowing via the DIP |  | Implemented | [5 empty] | Interim Release 3 | #REF! |  | Interim Release 3 | #REF! | IF-035 for Trad/Advanced meters was previously shown as a flow being direct interaction between REGS and MS. Changed to show message as flowing via the DIP (at step 90). Also change applied to Forward migration process for consistency. | Process Model correction | MPAN Ownership | BP003 | MHHSP-BP003-Change of Service - Data Service MHHS-DEL964 BPM-003 - Change of Servie - Data Service - Forward Migration
MHHS-DIN-496 | MH | DIN-910 | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 | MHHSP-METH001_SDS_Validation_Estimation 5.1 section 2.7 States "SDS shall inform the Supplier using the Meter Reading Reason Code on the IF-041/PUB-41" . There is no Meter Reading Reason Code on the IF-041 in DES138 v5.1.2. Therefore, either Meter Reading Reason Code should be included in DES138, or this requirement should be removed. |  | Closed | No |  | Design ambiguous | N/A |  |  | #REF! |  |  | #REF! | Updated as part of DIN-910 | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-497 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 | MHHSP-METH001_SDS_Validation_Estimation 5.1 Section 5.4 Where DA records are < 90 days from UTC date this is inconsistent with Method 4, which states "DA is available [either in the past or future] and less than [3] months different from the UTC Date requiring a daily Meter advance". |  | Implemented | No |  | Design ambiguous | N/A |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Be consistent - use either 90 days or three months within the document Tend to agree – this describes the actual method of estimation so should be included before go-live | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-498 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 Method 13 | MHHSP-METH001_SDS_Validation_Estimation 5.1 Method 13 This describes the outcomes for Smart and Advanced meters. Does this imply that traditional meters should have zero consumption submitted to settlements, or should Method 13 text be adjusted to include trad meters? ALSO If actual data is recovered, or an Advance Meter Reading is received, and this indicates zero consumption, should this be submitted to settlements? The first part of the sentence implies it should be submitted, and the brackets imply it shouldn't. |  | Implemented | No |  | Design ambiguous | N/A |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Alter wording of Method 13 to reflect we shouldn't be sending estimates for Deenergised trad meters as well as Smart and Advanced, AND 'there is no need to submit zero consumption for de-energised MPAN's' needs changing to refer to 'zero ESTIMATED consumption' This should be a clarification of previously stated position but agree update should be made to clarify that Zero consumptions are required to be submitted, where encountered, for all MPANs that are not de-energised regardless of segment/meter type. | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-499 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Alignment of Estimation Reason Codes | METH001 refers to Estimation Reason Code 'Adjustment'. DES138 refers to 'Consumption Amendment' Assume these are the same thing and need to be aligned between both sets of documentation |  | Implemented | No |  | Design misaligned | N/A |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Align Method Statements to match the Estimation Reason Codes within DES138 | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-500 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | ISD Entity M17 Example Correction | MHHSP_EDI021_ISD_Entities 5.1 Entity id M17 Industry Standing Data: MHHS Entities/Data Items v5.1 ISD Entity Id M17 - Valid Consent Granularity Combinations, includes combination I¦F¦S¦D. According to Decision 2 in "https://www.ofgem.gov.uk/sites/default/files/docs/2019/06/access_to_data_consultation_ofgem_response_0.pdf" a non-domestic customer is unable to opt out. The OFGEM document states "There will be no opt out possible for microbusinesses in relation to data for settlement purposes". Therefore, I ¦ F ¦ S ¦ D is not a valid combination. |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | In ISD Entity ID M17 we have removed "I ¦ F ¦ S ¦ D" from the example list | Design Ambiguous | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-501 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Addition of Method 13 to METH002 | MHHSP-METH002_ADS_Validation_Estimation 5.1 Section 3.16 States "The below estimation methods are based on those used in the Smart Data Service (SDS) Method Statement. For that reason, methods 0, 1, 6, 11 and 13 have been omitted as they are only applicable to Smart meters." However, method 13 is "Estimation for a Site where Supply is de-energised" and this is included in METH002 in section 2.29. The statement is wrong as some of the methods have been renumbered in METH001 since this was written. |  | Implemented | No |  | Error/Correction | Smart Data Services |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Update METH002 to add Method 13 back in | Requirement correction | Supporting Docs | Method Statement | ADS Method Statement
MHHS-DIN-502 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | SP Quality Indicator Clarification | MHHSP-METH001_SDS_Validation_Estimation 5.1 It is our assumption that if NO estimation is required, the Settlement Period Quality Indicator should be set to "A". This is however, never explicitly mentioned. The only mention of using value "A" is for method 1. |  | Implemented | No |  | Design ambiguous | N/A |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Update artefacts to clarify when to use A as the Settlement Period Quality Indicator value | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-503 | SW |  | 2023-07-13 | SIMS | 2439 | Martin Freeman | Central Body | S1.senderUniqueReference interface component is too small to identify the message interface | DES138 and the E2E001 the S1.senderUniqueReference property has a 3 digit component that contains the interfaceID of the message. However since the reporting interfaces reuse the same interface numbers as the standard interfaces, and some reporting interfaces have 4 character interface identifiers, this means this component is not sufficiently large to unambiguously identify which interface a given senderUniqueReference was generated for. This also applies for TransactionID. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Update any Data Items that utilise InterfaceID to align with the enumeration of values defined for DI-000 so that this is unique across all interface / report types. This is for data types SenderUniqueReference (DI-995) and TransactionID (DI-990). This change will require updates in DES-138, E2E001 and Swagger 1.4. In DES-138, DT-014 has been updated to String65 from String60 to support Interface being updated from 3 to 8 to align with DI-000 (so for IF-003, rather than 003 being included in the transactionID / senderUniqueReference, this will be IF003 with no hyphen). In Swagger, DT-014 has been updated to max length 65, with examples updated. E2E001 updated examples for senderUniqueReference and TransactionID to align with the above. | Design Ambiguous | Supporting Docs | DES-138, E2E001 and Swagger 1.4 | DES-138-interface catalogue, E2E001 E2E Architecture document and Swagger 1.4
MHHS-DIN-504 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Clarification of link between IF22/IF23 | DES138 IF-022/023 IF an IF-022 or IF-023 is re-issued, can you confirm that they will be reissued as a pair so that the totals align? The issue is if an updated IF-022 is issued with new values, should the SDS/ADS await an updated IF-023, or not? How can the SDS/ADS pair the IF-022 and IF-023 without doing their own summations? |  | Assessment Complete / Implementation Deferred | No |  | Clarification - No change required | N/A |  | Post Go-live Release | #REF! |  | Post Go-live Release | #REF! | Update BRS007 to show that a re-run of IF-022 will result in a rerun of IF-023 |  |  | Business Requirements Documentation | BRS007
MHHS-DIN-505 | BK |  | 2023-07-13 | St Clements |  | Sean Cooper | SRO Design | DUoS Tariff ID to hold values from 1-3 in length | The DUoS Tariff ID needs to be updated in Swagger and the Interface Catalogue so that it can hold values from 1 to 3 in length in order to align with ISD. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Update DUoS Tariff ID to hold values from 1 to 3 in length in Swagger and Interface Catalogue | Data interface correction | Supporting Docs | Interface Catalogue and Swagger 1.4 | DES138-InterfaceCatalogue Swagger 1.4
MHHS-DIN-506 | BK |  | 2023-07-13 | Design Team |  | Sean Cooper | SRO Design | Renaming of IF-014 | Rename IF-014 to clarify the purpose |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Changed to "UTC Settlement Period Consumption Data (Warnings & Rejections)". Interface description and notes updated to reflect that IF-014 could also contain warnings for Consumption on De-enegised sites. | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-507 | SC | DI-194 | 2023-07-14 | Design Team |  | Sean Cooper | SRO Design | Clarification of IF-036 Routing Requirements | Update IF-036 to clarify / provide additional info on the routing destinations of IF-036 |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Added following Text: Primary Routing Participants for IF-036 MSAppActive • Supplier (i.e. the supplier who initiated the appointment, either current in the case of Change Of / Update to SP’s, or incoming in the case of a COS) • Metering Service (i.e. the Metering Service being appointed) • [Partner] Data Service (i.e. the Data Service in effect on the App Start Date of the MS Appointment – this could be either an ‘existing’ Data Service in the case of an MS Only appointment OR the ‘incoming’ Data Service with a coincident App Start Date to that of the [incoming] Metering Service • Linked Supplier(s) – (ie the Supplier(s) with responsibility for the Linked [Import/export] MPANs on the App Start Date of the Metering Service Appointment) DSAppActive • Supplier (i.e. the supplier who initiated the appointment, either current in the case of Change Of / Update to SP’s, or incoming in the case of a COS) • Data Service (i.e. the Data Service being appointed) • [Partner] Metering Service (i.e. the Metering Service in effect on the App Start Date of the DS Appointment – this could be either an ‘existing’ Metering Service in the case of an DS Only appointment OR the ‘incoming’ Metering Service with a coincident App Start Date to that of the [incoming] Data Service • Linked Supplier(s) – for Advanced Segment Meters only - (i.e. the Supplier(s) with responsibility for the Linked [Import/export] MPANs on the App Start Date of the Metering Service Appointment) | Data interface correction | Supporting Docs | Interface Catalogue
MHHS-DIN-508 | SC |  | 2023-07-17 | Design Team |  | Sean Cooper | SRO Design | Addition of MP Status and RMP Status Effective From Dates to IF-050 | Addition of MP Status and RMP Status Effective From Dates to IF-050 ( Linked to DIN 318 ) |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | New Data Items Created and added to IF-050 in block B079 and the data catalogue tab: DI-167 RMP Status Effective From Date DI-168 MP Status Effective from Date (DIN 318 Closed as duplicate) | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-509 | SW |  | 2023-07-18 | MHHS |  | Steve Weston | Central Body | Missing Archival NFR Information | There is no detailed non-functional requirements in relation to data archiving, retrieval, archival tiers, recovery from archival so we need to update the NFR's to ensure these are included. |  | Closed | No |  | Design ambiguous | DIP Users |  |  | #REF! |  |  | #REF! | NFR requirements outline a two year archival requirement | Clarification |  | Business Requirements Documentation | Non-functional Requirements
MHHS-DIN-510 | SW |  | 2023-07-18 | MHHS | 2675 | Steve Weston | Central Body | Properties on block B047 | The Swagger definition has the properties ‘sp’,’v’,’q’,’e’ and ‘arc’ which matches the items in red. However the data catalogue has different YAML names. YAML Swagger names have to be updated in DES-138 to match the above characters. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | This was done to reduce IF-021 content size, but the DES-138 5.4.1 YAML needs to be updated to align with Swagger 1.4 - the YAML names should be as follows DI-082 ‘sp’ - B052 (IF-022), B047 (IF-021) DI-147 ’v’ - B047(IF-021, 4, 16) DI-083 ’q’ - B047 (IF-021, 14, 16) DI-076 ’e’ - B047 (IF-021, 14, 16) DI-166 ‘arc’ - B073 (IF-027 / 28) Swagger 1.4 has been updated to align for the approrpiate blocks above to ensure consistency across the data catalogue. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-511 | BK | CR027 | 2023-07-18 | Eastern Power Networks |  | Peter Waymont | Network Operator | DUoS E-Billing DIP Message for MHHS | A new flow needs to be introduced for e-billing of site-specific DUoS in the post Market-Wide Half-Hourly Settlement (MHHS) environment because the existing flow uses the DTN and all other DUoS data will be DIP based. The change is required in order to continue to operate the site specific DUoS billing process in the MHHS environment. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the HH data sent by Data Services to the LDSO for use in DUoS billing, using IF-021/IF-013/IF-014. At present DUoS billing systems can send the D2021 data flow as a form of e-billing for site-specific DUoS, using the DTN. As DUoS billing systems will need to interact with the DIP for migrated site-specific billed customers, it is preferable that the outputs are also DIP messages, to enable the parties to move forward completely in the new environment. A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors) and receivers (suppliers) of the flows has identified the desired flow content and now wish to bring this to the Programme to ensure that it can be delivered in readiness for migration. | CR027 | Closed | [6 empty] | #REF! |  |  | #REF! | Covered as part of CR019
MHHS-DIN-512 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Amendments to Swagger and ECS data catalogue REP-002 | Max length for DI-345 DUoS Tariff Id to be updated in line with ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Swagger 1.4 updated to ensure DI-345 DUoS Tariff ID aligns with ECS Data Catalogue - max length of string = 3. | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-513 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Custom block correction REP-002 | Block name to be updated to tariffCharacteristics in Swagger. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Swagger 1.4 updated for REP-002 custom block to fix typo from tarrifCharacteristics to tariffCharacteristics to align with ECS Interface Catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-514 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Amendments to Swagger and ECS data catalogue REP-002a | Max length for DI-345 DUoS Tariff Id to be updated in line with ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Swagger 1.4 updated to ensure DI-345 DUoS Tariff ID aligns with ECS Data Catalogue - max length of string = 3. | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-515 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Custom block correction REP-002a | Block name to be updated to tariffCharacteristics in Swagger. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Swagger 1.4 updated for REP-002 custom block to fix typo from tarrifCharacteristics to tariffCharacteristics to align with ECS Interface Catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-516 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Update DI-300 with Minimum value REP-003 | DI-300 to be updated in swagger with a minimum value of 100 as per ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | DI-300 updated in Swagger 1.4 with a minimum value of 100 as per ECS data catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-517 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update data item type in ECS data catalogue REP-003 | DI-325 data type to be updated in data catalogue to (NUM 4,2) in line with swagger |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | MHHS Data Type column of MHHS ECS data catalouge updated to NUM(4,2) for DI-325. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Cataloue correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-518 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Inclusion of Max/Min value for DI-496-REP-003 | Update ECS data catalogue with Min value of 1 and Max value of 48 |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | MIn and Max Column of MHHS ECS data catalogue updated with 1 and 48 respectively. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-519 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Max value change in swagger for DI-496 | Update Max value to 48 for DI-496 in swagger |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | DI-496 in Swagger 1.4 updated to have a Max value of 48 | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-520 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-359 data type REP003 | Update DI-359 data stype to String 16 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-359. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-521 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-360 data type REP003 | Update DI-360 data stype to String 16 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 |  | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-360. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-522 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-362 data type REP003 | Update DI-362 data stype to String 16 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-362. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-523 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-324 data type REP003 | Update DI-324 data stype to String 16 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-324. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-524 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | DI-363 missing from ECS data catalogue | Update ECS data catalogue by adding in missing DI-363 |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | MHHS Data catalogue updated with the addition of missing data item DI-363. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-525 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-364 data type in REP003 | Update DI-364 data stype to String 17 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-364. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-526 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-365 data type in REP003 | Update DI-365 data stype to String 17 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-365. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-527 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-366 data type in REP003 | Update DI-366 data stype to String 17 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-366. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-528 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-367 data type in REP003 | Update DI-367 data stype to String 17 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-367. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-529 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-368 data type in REP003 | Update DI-368 data stype to String 17 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-368. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-530 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Wrong data item referenced in swagger | Wrong data item referenced in R022. Daily Period BM Unit Total Allocated Volume must be changed to BM Unit Allocated Demand Disconnection Volume |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Swagger 1.4 has BM Unit Allocated Demand Disconnection Volume (DI-241) in R022 | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-531 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Data type update in swagger for DI-341 | DI-341 data type to be changed to String 18 as per data catalogue |  | Closed | [6 empty] | #REF! |  |  | #REF! | Closed. This is defined a Integer in the format 9,6 in Swagger. | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-532 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Wrong data item referenced in swagger | Wrong data item referenced in R022. settlementPeriodID must be changed to Settlement Period |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Updated Swagger 1.4 so that R022 references DI-946 (SettlementPeriod) rather than DI-307 (SettlementPeriodID) | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-533 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-339 data type in REP-003 | Update DI-339 data stype to String 17 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-339. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-534 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-369 data type in REP-003 | Update DI-369 data stype to String 17 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-369. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-535 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-370 data type in REP-003 | Update DI-370 data stype to String 17 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-370. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-536 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-322 REP003 | Update Min column of ECS data catalogue with 0 |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | DI-322 Minimum column of MHHS ECS data catalouge updated with 0 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-537 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-322 REP003 | Update Max column of ECS data catalogue with 99.99 |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | DI-322 Maximum column of MHHS ECS data catalouge updated with 99.99 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-538 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-323 REP003 | Update Min column of ECS data catalogue with 0 |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | DI-323 Minimum column of MHHS ECS data catalouge updated with 0 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-539 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-323 REP003 | Update Max column of ECS data catalogue with 99.99 |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | DI-323 Maximum column of MHHS ECS data catalouge updated with 99.99 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-540 | SW |  | 2023-07-14 | Elexon | 2684 | Nigel Rees | Central Body | IF-13 run number | In DES-138, Run Number in IF-013 Interface is 3 chars, yet in Swagger and ECS Reports, this is 7 characters long. We need to update DES-138 to align with Swagger and ECS reports. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Updated IF-013 to show DI-161 (Run number) as number 7 to be consistent with Data Catalogue/ Swagger and Reports | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-541 | MF |  | 2023-07-19 | ESG | 2623 | Patricia Parker | Software Provider | SSC and Profile Class validation | Validation needs to be reviewed to enable the provision of just SSC or Profile Class updates as part of [SSCandProfileClass] event code updates in IF-025 |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Updated conditionality on IF-025 and IF-026 for DI-122 (Profile Class) and DI-123 (SSC) to "Mandatory for Traditional Meters (if changing)" to allow just SSC or Profile class updates to be provided. Validation rules updated accordingly in IF-025. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-542 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-159 in data catalogue REP004 | Update Min column with 25 in data catalogue |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | DI-159 Minimum column of MHHS ECS data catalouge updated with 25 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-543 | MF |  | 2023-07-19 | Design Team |  | Mike Fensome | SRO Design | IHD, SMSO, SSC and Profile Class conditional validation | Update validation rules to ensure effective from date is provided when IHD, SMSO, SSC or Profile class are updated |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Added conditionality to IF-025 and IF-026 that DI-136 should be provided where DI-137 is not null and DI-135 should be provided wher DI-134 is not null. Added validation rules to IF-025 to ensure conditionality rules are applied for IHD, SMSO, Profile class and SSC with new error code of REG1088 -Effective from date must be provided | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-544 | SW |  | 2023-07-19 | Siemens | 2633 | Tony Mason | Software Provider | Level 4 Validation - Multiple response codes | Unclear from the current E2E design defined in E2E001 for a Level 4 Response code, whether a single transaction with concatenated Response codes be sent back to the DIP for notification to the publisher? Or, would the expectation be that multiple messages be returned with each message quoting the published transaction number? Or, is this at the discretion of the participant? The E2E design should make this clearer, and also provide fleixbility for multiple messages to be returned against the same transaction ID with a response. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | This will require updates to the E2E design document to make Level 2 and 4 response code expectations clearer, as well as updated Swagger to allow for an array of messages, help and service tickets to be sent per error, per transaction ID. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.5
MHHS-DIN-545 | ME |  | 2023-07-20 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-496 data type REP004 | Update swagger to show DI-496 as INT (2) |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Update to data type for DI-496 from INT(3) to INT(2) to align with swagger. Update made to MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-546 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Incorrect data item referenced in swagger- REP004 | Incorrect data item referened in R026. SettlementPeriod ID must be replaced with Settlement Period (DI-496) in swagger |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Updated Swagger 1.4 so that R026 references DI-946 (SettlementPeriod) rather than DI-307 (SettlementPeriodID) | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-547 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Missing data item in swagger | In R026, DI-327 missing from swagger v1.3. Should added and defined as per DT-22 |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Updated Swagger 1.4 to include DI-327 (Deemed Supplier Take). Updated R026 to include DI-327 and remove DI-325 so this aligns with ECS Data Catalogue. | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-548 | MH |  | 2023-07-20 | Elexon | 1966 | Rashmi Radhakrishnan | Central Body | Clarification of ISD Transition Requirements | Following MTDSG release of the BRS001 Transition approach and Parallel running requirements v2, ISD would like programme to consider rewording below requirement for more clarity. MHHTR-22 Original: The ELEX-REP-005 Line Loss Factor report will be published at a location on the BSC website/ ELEXON Portal and the URI shall be notified using the Notification of the Publication of a Downloadable Asset IF-047 / PUB-047 to DIP Users prior to M10 and continue post M15. MHHTR-27 Original: The new ISD entities shall be updated be published at a location on the BSC website/ Elexon Portal and the URI shall be notified using the Notification of the Publication of a Downloadable Asset IF-047 / PUB-047 to DIP Users from M10. |  | Closed | No | [9 empty] | Duplicate - To be tracked under MHHS-DIN-754 | Design Ambiguous | Supporting Docs | ISD Document | ISD Document EDI-021
MHHS-DIN-549 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Incorrect data item referenced in R033 common block | Incorrect data item referenced in R033 - SettlementPeriodID from MDS/VAS should be replaced with SettlementPeriod (DI-496) from ISD, with a MIN value of 1 and Max of 48 in swagger |  | Closed | No | [9 empty] | Closed- Swagger should keep the min of 1 and max of 50 settlement periods
MHHS-DIN-550 | ME | DIN-659 | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Missing R007 from REP007 | Include R007 within REP007 in swagger |  | Closed | No |  | Design misaligned | DIP |  |  | #REF! |  |  | #REF! | Update swagger: Include R007 within REP007 | Swagger | Supporting Docs | Swagger | Swagger
MHHS-DIN-551 | ME |  | 2023-07-20 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-083 | Include Min Value of 1 and Max value of 5 to DI--083 in ECS data catalogue to align with swagger and IF data catalogue |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | DI-083 Minimum and Maximum column updated with 1 and 5 respectively in MHHS ECS data catalouge Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-552 | SW |  | 2023-07-20 | IMServ | 2356 | Liam Lowey | Software Provider | UTF-8 Encoding for JSON | The E2E001 design document does not specify Encoding for JSON. This needs to be updated to reflect UTF-8 as the JSON Encoding required. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Add UTF-8 as the JSON encoding required in the E2E001 design document, creating a new section 4.2.5. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-553 | RS |  | 2023-07-20 | Design Team | 2627 | Rob Short | Central Body | Secondary routing for Export | Secondary routing rules need to be updated to allow notification of work prgressed by the Import suppllier (eg disconnection). review required of all related interfaces |  | Closed | [6 empty] | #REF! |  |  | #REF! | Following review no document changes required. Re Specific case of Disconnection the Link between Import and Export would need to be removed prior to any Disconnection request. If the link remains in place then the DIsconnection request will be rejected by LDSO/REGS.
MHHS-DIN-554 | MF |  | 2023-07-20 | St Clements |  | Madison Layton | Software Provider | Validation on Customer Direct Contracts | Revisions to CDC functionaility. - Amend validation to ensure that only one Customer Direct Contract can be applied against an MPAN at any moment in time - Move CDC process(s) onto a new BP10 process map so as to make it clearer that CDC is MPAN not appointment based - add supporting process info to new BP |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. Process map emailed to particpants - added to BP010E and validation rules for IF-038 updated accordingly. Business requirements updated to align with process Agreed changes with SCS, & RECCO | Design Ambiguous | Supporting Docs | Supporting Docs | BP10 Registration Updates DES138 - Interface Catalogue BRS001 , BRS002
MHHS-DIN-555 | MF |  | 2023-07-20 | St Clements |  | Madison Layton | Software Provider | Validation of MPID to DIP ID | Carry out validation of MPID to DIP ID during initial IF-031 validation only. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Set REG1090, REG1091 and REG1092 validation in IF-031 to "No" for Queue processing so it only applies to IF-031 validation. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-556 | KH |  | 2023-07-21 | Stark | 2112 | James Murphy | Supplier | Cumulative/Total Consumption Comparison | The “Cumulative/Total Consumption Comparison” that can be carried out instead of a MAR for meters with integral Outstations is not defined anywhere In BSCP502 it is defined at 4.1.5 – I think this should be lifted and shifted into METH002 Interestingly it appears to be described in the SDS Validation & Estimation Statement (METH001) at 3.12 – 3.16 ADS Method Statement (METH002) needs to be updated |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | ADS Method Statement has been updated with "Reconciliation for smart Meter Advance Reconciliation" section 2.21 - 2.25. | Method statement correction | Supporting Docs | Method Statement | METH002 ADS Validation Estimation
MHHS-DIN-557 | RS |  | 2023-07-21 | Elexon | 2745 | Rashmi Radhakrishnan | Central Body | Consistency of the use of ID | Version 5.1 ISD EDI021 Entity specification document, has discrepancies in the usage of ID, Id, id, etc. Inconsistencies to be addressed when updating the design artefact in the future. ISD Entity M3 Usage of ID and Id - Market Participant ID in the table and description are different ISD Entity ID 17 - DUoS Tariff Id GSP Group Id - ISD Entity ID 17 - DUoS Tariff Id table - GSP Group id is with lowercase "i" and Entity Id M4 Load shape categories : GSP Group Id is mentioned as GSP Group ID ISD Entity ID 17 - DUoS Tariff Id Usage of DUoS Id and DUoS Tariff Id ISD Entity Id 4 and 17 - has ID in capital letter Usage if ID and Id to be consistent Entity M4 GSP Group ID- but should be GSP Group Id ISD Entity Id M5 - MHHS Consumption Component Classes CCC ID - for consistency it should be CCC Id |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | All instances of lower /mixed case id have been replaced with "ID" in caps Also see DIN588 | Data Interface correction | Supporting Docs | Support Docs | ISD Document EDI-021
MHHS-DIN-558 | BK | DI-189 | 2023-07-21 | St Clements | 2011 | Madison Layton | Software Provider | Update response codes in IF-035 | IF-035 routing rules references response codes AC and RJ, this should be A and R |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Updated Routing rules in IF-035 to refer to Response code of "R" and "A" for event code [SDS-MDROutcome] rather than "AC" and "RJ" | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-559 | SC |  | 2023-07-24 | St Clements |  | Sean Cooper | SRO Design | Clarification of Appointment Scenario Code (Linked MPANs) | Added clarification to IF-036 to confirm that the Appointment Scenario Code used for Secondary MPANs will mirror that applied to the Primary MPAN (eg COS/CSP/Etc). What will be applied in the case of Auto Alignment ? |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 |  | Interim Release 4 | 2023-08-16 | Added clarification to IF-036 to confirm that the (DI-800) Appointment Scenario Code used for Secondary MPANs will mirror that applied to the Primary MPAN (eg COS/CSP/Etc). In cases of Auto-Alignment of MPANs the Appointment Scenatio of (ALG - Auto Alignment of MPAN Service Providers) will be applied. ALG added as allowable value in DI-800 ( Data Catalogue and Swagger ) | Design Clarificarion | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue Swagger 1.4
MHHS-DIN-560 | SC |  | 2023-07-24 | St Clements |  | Sean Cooper | SRO Design | Design Gap on Sharing MTD in the Case of AutoAlignment of Service Providers | The Design allows for the Auto-Alignment of Service Providers in certain circumstances. However a design gap exists that there is currently no trigger for the outgoing MS to send MTDs to the incoming MS in the case of a pure Auto-Alignment (ie no other MPAN transaction eg. COS/CSP) |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Proposal is to create a new requirements (MS-098 / MS-099) on Smart and Advanced Metering Services to trigger sending of D0149/D0150 (trad) or D0265 (Adv), on receipt of a PUB-037 with De-Appointment Reason Code of “RELATED” or “IMPEXP”. D-Flow(s) should be sent, via DTN, to the new/incoming MS referenced in the PUB-037 flow, where available Issue does not arise for Smart sites as MTDs are fully convayed using the PUB-036. Also not a concern for UMSDS as no MTDs exist. | Design Clarificarion | Minor | MPAN Ownership | BRS-002 Metering Service Requirements
MHHS-DIN-561 |  |  | 2023-07-24 | St Clements |  | Sean Cooper | SRO Design | Disconnection of Linked MPANs | No change to desgin required. Design confirmation only. SCS have confirmed that it will be necessary to de-link and MPRN before being able to action a disconnection on it. i.e. Disconnection cannot be performed on a linked MPAN until such time as all links have been removed via (IF-019/IF-020) |  | Closed | [6 empty] | #REF! |  |  | #REF! | No change Required - Clarification Only
MHHS-DIN-562 |  |  | 2023-07-24 | St Clements |  | Sean Cooper | SRO Design | Clarification of IF-014 R0 Population for Event Code [ConsumptionOnDeEnergisedMPAN] | Confirmation at an R0 will be required when issuing an IF-014 with Event Code [ConsumptionOnDeEnergisedMPAN]. DI-979 should be populated with value 'W', DI-980 would remain blank. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | IF-014 updated to clarify that DI-979 should be populated with W. Data Catalouge and Swagger v1.4 updated to reflect this. | Design Clarificarion | Minor | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-563 |  |  | 2023-07-24 | Elexon | 2705 | Ayo O (Helix) | SRO Design | Clarification on Helix Treatment of IF-021 error condition data. | Clarification is required from Helix on exactly how they will manage and process IF-021 messages and how any resulting error/rejections will be managed. This is so that clear guidance can be drawn up on participants should expect to receive errored data etc. In any event design team are clear "the data returned in the IF-014 must only be that data which is rejected." |  | Closed | [6 empty] | #REF! |  |  | #REF! | A response was provided to Ayo on 24/07 by design team. Follow up email has been sent for Ayo to confirm whether issue is resolved, thus closing the DIN or whether a call is required with Design team for further resolution. DIN closed as no response received from Ayo. It is our assumption the feedback provided by the design team was sufficient. | Design Clarificarion
MHHS-DIN-564 | SW |  | 2023-07-17 | SIMS | 2704 | Martin Freeman | Central Body | Mandatory Nullable on Swagger | Is Mandatory Nullable (which is how 'optional' properties are described in the DES138) supposed to be marked as Required & nullable in Swagger? Or should these Mandatory Nullable (optional) properties be marked 'not Required' in Swagger? In some interfaces Mandatory Nullable properties are marked 'not required' in Swagger while in others they are 'nullable required'. Need to ensure this is applied consistently across all Interfaces. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Need to update Swagger implementation so mandatory nullable is treated consistently across all Interfaces as this is not always consistent. Need to updated E2E001 to provide additional clarity on how this applies to Swagger. Need to ensure DES-138 is aligned. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | Swagger 1.5
MHHS-DIN-565 | SW |  | 2023-07-25 | MHHS | 2763, 2713 | Steve Weston | SI Design | Version and Schema Interoperability across environments. | Versioning is covered in Section 8.4 and 8.5 of the E2E001 design, that covers the differences between major, minor and patch versions of an API, the URL required as well as schema versions that are contained in the common block of an Interface. There is confusion around how this will work across different environments so we need to provide additional clarity on the Swagger API versions / Schema versions that must be supported by the DIP and MP’s, alongside scenarios that are envisaged. This will provide information on version uplifts, interoperability required and how long different versions of API / Schemas will be supported for. This needs to covers scenarios where within an environment, we have multiple versions of an API within an environment ie, we may be required in some cases to be backwards compatible with previous versions -- for example -- if we received and processed earlier versions, we can respond with the latest live version. E.g. if we receive PUB-005 on version 1.0.0 we could respond with IF-006 on version 1.0.1 and would not be expected to respond with version 1.0.0. |  | Assessment Complete / Implementation Deferred | No |  | Design gap | TBC |  | Post Go-live Release | #REF! |  | Post Go-live Release | #REF! | Need to provide updates to Section 8.4 and 8.5 to ensure we cover worked examples across different environments for both API versions and Schema versions, interoperabilty required, transition between versions, BAU vs Testing phases and expectations on DIP and MP's. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document Swagger
MHHS-DIN-566 | SW |  | 2023-07-25 | MHHS | 2549 | Steve Weston | SI Design | E2E NFR's need to be refined based on actual data | Section 3.1 of MHHS DES001a MHHS Data Integration Platform – Functional Specification – Appendix A Transaction Volumes states that the indicative size of an IF-021 (single days' worth of UTC SP data) is between 1 and 2 KB. The equivalent IF-021s we have successfully submitted to the DIP Simulator are ~4.5 KB as observed in webhook. Can you confirm that this increase in size has been factored into the non-functional requirements? |  | Closed | No |  | Clarification - No change required | DIP Users |  |  | #REF! |  |  | #REF! | Agreed to be closed. Volumetrics document has been updated to reflect updated file sizing. This is for guidance only and depends on IF-021 consumptions per transaction. | Design Ambiguous | Supporting Docs | MHHS E2E004 Solution Architecture - Transaction Volumes | MHHS E2E004 - End to End Solution Architecture– Transaction Volumes IF-021
MHHS-DIN-567 | SW |  | 2023-07-25 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - Swagger Incorrect | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4. Swagger 1.4 needs to be updated so that it aligns with DES-138. DI-081 to be updated to periodDuration. DI-086 to be updated to supplierEffectiveFromDate. DI-121 to be updated to supplierEffectiveToDate. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Need to update mismatch between Swagger YAML definition in DES-138 and Swagger 1.4. Swagger 1.4 needs to be updated so that it aligns with DES-138. DI-081 to be updated to periodDuration. DI-086 to be updated to supplierEffectiveFromDate. DI-121 to be updated to supplierEffectiveToDate. | Design Ambiguous | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-568 | SW |  | 2023-07-26 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - DES-138 incorrect | DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) shows in YAML as secondaryRecipientDIPID and primaryRecipientDIPID respectively and this should be updated in DES-138 YAML column so this aligns with Swagger 1.4 ie, DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) shows in YAML as secondaryRecipientDIPID and primaryRecipientDIPID respectively and this has been updated in DES-138 YAML column so this aligns with Swagger 1.4 ie, DI-981 (secondaryRecipients) and DI-982 (primaryRecipients). | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-569 | SW |  | 2023-07-26 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - DES-138 incorrect | DI-047, DI-049, DI-210, DI-211 and DI-820 are defined in the Data Catalogue, but not used in any Interfaces so need to be removed from the latest version of DES-138. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | DI-047, DI-049, DI-210, DI-211 and DI-820 are defined in the Data Catalogue, but not used in any Interfaces so need to be removed from the latest version of DES-138. DES-138 needs to be updated to remove these items. | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-570 | MF |  | 2023-07-26 | MHHS |  | Mike Fensome | SRO Design | IF-021 validation rules | IF-021 validation rules need to be updated to align to the MDS and LSS Method statements which include validation for de-energised sites. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | IF-021 Added validation to align with MDS/LSS method statements where estimated data is provided on a de-energised site (ECS1008 - SP End Date/Time [DI-082] contains non-actual consumption for ECS De-Energised MPAN) | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-571 | SW |  | 2023-07-27 | Callisto | 2762 | Dave Peat | Software Provider | Inconsistency for DI-980 Response Message(s) | For DI-980, the YAML name is responseMessages, however in Swagger, there is inconsistencies: R0.responseMessages - this is defined as array of DI-980 (responseMessages) B066.responseMessage - but defined as responseMessages (defined as DI-980 - single) B092.responseMessage - defined as responseMessage (defined as DI-980 - single) We need to update DES-138 / Swagger so there is consistenct application of the words responseMessage (for single response) vs responseMessages (where there is an array of responses). |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | I have updated Swagger 1.4 so that DI-980 definition is applied consistently for single response vs array of responses. For single, it will be responseMessage. For an array of messages, it will be responseMessages. To this effect, B066.responseMessages has been updated to be responseMessage. Also, B066 block has been updated to align with DES-138 to be conditionally mandatory, rather than mandatory. | Supporting Docs | Design Ambiguous | Supporting Docs | Swagger 1.4
MHHS-DIN-572 | SC |  | 2023-07-27 | MHHS |  | Sean Cooper | SRO Design | Clarification of IF-013 Issuance (also Ref DIN610) | DUPE WITH DIN-610 ~ Clarification is requiired on the circumstances when Helix will issue IF-013. 1. IF-013 is only issued as part of the RF Run i.e. simply to notify Suppliers of what the default consumption for a period(s) is, where no data has been submitted by the DS come the point of RF. Should suppliers wish to derive this for pre-RF settlement runs then they are able to do so easily enough using the own data and the published Load Shapes. 2. The second view is that the IF-013 is issued on every settlement run undertaken for sites where no PUB-021 data has been received DIP impact concerns wrt to volumes of IF-013 would need to be addressed if Option 2 is the position. |  | Closed |  |  |  |  | 2023-09-13 |  | #REF! | 2023-09-13 |  | #REF! | Duplicate of DIN-610 | No Change
MHHS-DIN-573 | ME |  | 2023-07-27 | MHHS |  | Kevin Spencer | SRO Design | Update to step 40 of ISD BPM/BPD | Step 40 of MHHSP-BP021 and BPD021 currently ambigious Can the intention of this step be made clearer.? |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Step 40 of ISD BPM and BPD have been updated to say 'Issue ISD Change Notification' to make ithe purpose of the step clearer. | Design Ambiguous | Minor | Supporting Docs | MHHSP-BP021 Industry Standing Data MHHSP-BPD021 Industry Standing Data Business process Descriptions
MHHS-DIN-574 | SC |  | 2023-07-27 | St Clements |  | Madison | SCS | Change Of Logic on Smets 1 Number of Digits | Smets 1 Number of digits can be 0 - 9 Replaces previous logic. |  | Closed | [6 empty] | #REF! |  |  | #REF! | DIN CLOSED as agreed with St Clements and RECCo. DIN-615 supercedes this DIN. The text has been updated as suggested below from RECCo, ‘Where the Meter Type is S1, the value should be populated as per the manufacturer specification.’ However, the logical test for SMETS1 in the DES-138 Interface Catalogue will remain unchanged. DIN-615 also includes updating the Swagger validation of this field to match SCS logical test i.e. value can be 0-9. | No Change
MHHS-DIN-575 | SC |  | 2023-07-27 | St Clements |  | Madison | SCS | Requirement for REGS to process IF-040 | SCS would prefer not to process IF-040 now that AC is provided to EES Directly via the DIP. In additional what is the IF-040 processing schedule? IF-040 is only sent to appointed Suppliers and Data Services on a 30 day cycle. There could be a 30 day wait until the next MDS generated IF-040. Programme Design: To fill this design gap the programme has made MPRS responsible to load the IF-040 by populating Annual Consumption in the B027 Block on IF-002, IF-001 & IF-036 MPRS Issue: An IF-040 for every energised MPAN must be loaded adding significant overhead to processing. The 24 hr SLA could be difficult to meet without significant hardware investment. | CR039 | Implemented | No |  | Change Request | LSDO (SCS), DIP |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | To minimise change and impact on all other participants B027 Block is retained in IF-001, IF-002 & IF-036, but will never need to be provided by Registration Service as it is only required where the data exists in Registration Service. Annual consumption requirements document updated to remove the requirement for REGS to receive PUB-040 and maintain Annual Consumption. BP005 and BPD005 updated to remove REGS receiving Annual Consumption. REGS removed from IF-040 secondary routing in DES-138. On Appointment, Data Service and Supplier will receive the latest PUB-040 with their PUB-036. DIP will be changed to replay the PUB-040 from the Message Archive. Note added to BP003. Change in IR5 SIT Scope to exclude B027 Block Loading for Supplier and Data Services. Remove testing of IF-040 Processing for MPRS Change in IR8 SIT Scope to add DIP IF-040 Replay on Supplier and Data Service Appointment Confirmation | Data interface correction | Supporting Docs | Interfaces | DES138 BP003 BP005 BPD005 BRS012
MHHS-DIN-576 | MF |  | 2023-07-27 | St Clements |  | Madison | SCS | Cancelling appointments in advance of receipt of PUB-034 | SCS have requested that the design is updated to allow for issuing of a PUB-035 'Lapsed' message, if a switch is 'Cancelled' or otherwise superseded, even prior to issuing / processing of a PUB-034 from the Metering Service or Data Service. ​ |  | Closed | [6 empty] | #REF! |  |  | #REF! | Following DRG on 4th Aug, it was agreed that St Clements Services were to work-up the topics discussed, and a dedicated workshop would be arranged to discuss this further. St Clements Services have advised the Programme that they will now not be pursuing proposals made at the DRG session and would be reverting to implement to the original design, therefore closure of this DIN.
MHHS-DIN-577 | SW |  | 2023-07-27 | Callisto | 2979 | Neil Edney | Software Provider | DT-983 and DT-000 are missing IF-040 / PUB-040 | DT-983 and DT-000 are missing IF-040 / PUB-040 in Swagger. IF-003, 19, 20 and 50 also need to be added to align with DES_138. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Need to update Swagger to include IF-040 and PUB-040 in DT-000 and DT-983. I’ve added IF-003 / 019 / 020 / 040 / 050 to DT-000 in Swagger and PUB-003 / 019 / 020 / 040 / 050 to DT-983 in Swagger | Supporting Docs | Design Ambiguous | Supporting Docs | Swagger 1.4
MHHS-DIN-578 | SB |  | 2023-07-28 | RECCo | 2943 | Jonny Moore | Central Body | EFDs, ETDs and Supplier information for Related and Import/Export Linkages | We’ve noticed through the design and build stage of EES that we are not being communicated the EFD and ETD of a Related MPAN set-up or an Import / Export Linkage. Nor are we being informed of the Supplier responsible for creating a Related MPAN relationship. This information is not currently being published in the IF020/PUB020 However, this information is currently available for market participants to view on EES. We had some feedback in the REC MSAG that participants would like to continue to view these items in EES and wonder if this is worth a DWG discussion? |  | Closed | [6 empty] | #REF! |  |  | #REF! | RECCo notified on DIN closure. The Effective From date is not currently shared on the D0386 which was the basis for the IF-019/PUB-020. If EES requires an EFD suggest that the transaction date from the header is used. These updates can only be made by the current Supplier. | No Change
MHHS-DIN-579 | SB |  | 2023-07-28 | ENWL | 2444 | Paul Stancliffe | Network Operator | PUB-043 Routing discrepancy | Trying to map flow PUB-43 to our TO BE business processes as these flows are showing on the MHHS - Interface Data Item Catalogue as routing to LDSO. However when trying to align these to the Business Process Diagram BPM011- Change of Connection Type and / or Market Segment V5.0 PUB-43 is not routing to LDSO |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | BP011B from Step 542 new flow for PUB-043 to LDSO new step Manage Change of Connection type Notification | Process Model correction | MPAN Ownership | Supporting Document | BP011B BPD011
MHHS-DIN-580 | RS |  | 2023-07-28 | RECCo | 2719 | Sarah Jones | Central Body | Late or Missing Secured Active Messages | understand the approach to managing CSS issues where secured active messages are not received within the expected secured active processing window. We understand the standard ‘happy path’ processing requires secured active notifications to be issued by CSS after the 5pm gate closure window the day before the registration effective from date. However, it was acknowledged when the MHHS design was originally baselined that some notifications may arrive late e.g. after 6pm, or not at all. Rather than developing operational provisions to deal with missing / late secure active notifications, this was highlighted as a risk for later consideration, on the basis the CSS arrangements were still new and the enduring BAU process was subject to change. In light of the CR018 approval, we believe this is now the time to clarify the approach to be taken where CSS notifications are missing or late. |  | Closed | [6 empty] | #REF! |  |  | #REF! | The Design Team and SRO are actively engaged with St Clements on issues around problematic switches. The plan is for them to provide us with a list of of their issues. We will then go through a process of raising these directly with CSS. Dependent on outcomes we receive back, we will look to discuss this with St Clements with the possibility of raising a CR for a specified data correction tool to align the data and send out the appropriate MHHS flows. | No Change
MHHS-DIN-581 | RS |  | 2023-07-28 | ESG | 2924 | Patricia Parker | Software Provider | Meter Location in DES138 | Currently DI090 in DES138 states 'Values as Per ISD'. These values are not held in ISD, therefore the reference should be changed to 'see Enum Values of the Data Catalogue' - example IF-005 |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Updated population notes for DI-090 to refer to Data Catalogue, IF's 2,5,6,20.33.36,61,62 | Clarification | Supporting Docs | Interfaces | DES-138 Interface Spec
MHHS-DIN-582 | MF |  | 2023-07-28 | Ovo |  | Chris Butterfiled | Supplier | Clarification following CR15 | Supplier Overview requirements v5.1: this refers specifically to Economy 7 / Economy 10 tariffs; we suggest this should be more general and refer to any Time of Use tariff / tariff with switched load to include other variants such as Smart Economy 9 etc. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Updated SU-163, SU-164 and SU-165 to refer "for switched load tariff (eg. Economy 7/Economy 10) sites" rather than Economy 7/Economy 10 sites | Requirement correction | Supporting Docs | supplier requirements | MHHSP-BRS004 Supplier Overview
MHHS-DIN-583 | SB |  | 2023-07-31 | Stark | 2891 | Jon Dennis | Data Service Provider | BP005 Read Sharing for Data Service | can you provide clarification around BP005 Read Sharing for the Data Service, in particular this section of MHHSP-BP005-Data Processing-v5.1 Question: Is the entry point to this section either: Regular Data Collection, e.g. daily remote collection for ADS/SDS Smart? Trigggered by an external process, e.g. Change of Energisation BP008? To answer the above, please can you list all of the processes that lead to Step 170 in BP005. May I also suggest updating BP005 to include this information, perhaps by adding a Step description to the entry point from Data Collection as shown above. Related Question: In BP008 the Data Service is expected to progress to BP005 Step 185. However, unless I am mistaken, BP005 V5.2 does not include Step 185. Please update BP008 with a valid onward step. |  | Assessment Complete / Implementation Deferred | No |  | Clarification - No change required | Smart Data Services, Advanced Data Services |  | Post Go-live Release |  |  | Post Go-live Release |  | Updates to be made to BP008: - Update to clarify that step 185 is actually step185 of BP008 rather than step185 of BP005 - Update to include note with information around entry points etc. | Process Model correction | All Areas | Process Models | BP005
MHHS-DIN-584 | SC |  | 2023-07-31 | Design Team |  | Sean Cooper | SRO Design Team | DI-511 Change of Data Type from String to Number in IF-024 | DI-511 Off Peak Declaration Proportion has been changed from String to Number so as to allow for improved Swagger validation of this data item. The new Number val will have a Minimum value = 0 and a Maximum Value = 100. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | DI-511 Off Peak Declaration Proportion has been changed from String to Number so as to allow for improved Swagger validation of this data item. The new Number value will have a Minimum value = 0 and a Maximum Value = 100. (IF-024). Data Catalogue updated accordingly. | Improved Validation of Data Item | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-585 | SC |  | 2023-07-31 | Design Team |  | Sean Cooper | SRO Design Team | Clarification on IF-024 | Clarification update to confirm that B097 Off Peak Declaration is Mandatory only for Event Type [SN-OffPeakDec] |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Clarification update to confirm that B097 Off Peak Declaration is Mandatory only for Event Type [SN-OffPeakDec] | Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-586 | SW | DI-204 | 2023-07-31 | Callisto | 2762 | Neil Edney | Software Provider | Mis-alignment between D0 block YAML in Swagger and DES-138 | DES138, the D0 has the following YAML names which do not align DIPCorrelationID, DIPTimeStamp, DIPTransationID However, swagger has these: initialCorrelationID, transactionTimestamp, transactionID |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Updated DES138 Data Catalogue D0 Common block data items so that YAML names in DES-138 now align with Swagger initialCorrelationID (DI-987), transactionTimestamp (DI-989), transactionID (DI-990) | Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-587 | SW |  | 2023-08-01 | Kraken | 2973 | Angelos Rizoyannis | Software Provider | Mis-alignment between R0 mandatory in Swagger vs DES-138 | In DES-138 in the following interfaces, R0 is marked as mandatory, but not mandatory in Swagger - IF-006, IF-008, IF-014, IF-020, IF-026, IF-028, IF-032, IF-039. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | In DES-138 in the following interfaces, R0 is marked as mandatory, but not mandatory in Swagger - IF-006, IF-008, IF-014, IF-020, IF-026, IF-028, IF-032, IF-039. Update R0 to be mandatory in these interfaces. | Clarification | Minor | Interfaces | Swagger 1.5
MHHS-DIN-588 | ME |  | 2023-08-02 | Design Team |  | Kevin Spencer | Programme Design | Update of ID to Id | A request has come from Elexon to update the ISD Entities document. Id should be changed to ID |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | All instances of Id have been changed to ID (see also DIN 557) | Supporting Document | Minor | Supporting Document | MHHSP_EDI021_ISD_Entities v5.3.2
MHHS-DIN-589 | SB |  | 2023-08-02 | Stark | 2466 | Jon Dennis | Data Service Provider | ADS and SDS Estimation Statements | I have been studying the following two documents: Advanced Data Service Validation and Estimation: Methodology Statement (MHHSP-METH002_ADS_Validation_Estimation v5.1) Smart Data Service Validation and Estimation: Methodology Statement (MHHSP-METH001_SDS_Validation_Estimation v5.1) In particular, Section 3 of the ADS_Validation_Estimation document details the estimation methods where the customer has opted-out of UTC Period consumption data. It references the SDS_Validation_Estimation document where Estimation methods are in Section 7. The 2 method statements have become misaligned when changes to the SDS method statement was updated. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | We will align the ADS method statement with the SDS method statement to keep it uniform. | Method statement correction | Supporting Docs | Method Statement | ADS Method Statement
MHHS-DIN-590 | KH |  | 2023-08-03 | Design Team | 2717 | Martin Freeman | Central Body | Update Role Codes in E2E001 | There is a mismatch between roles codes that are in DES-138 and those that are in E2E001. Role code for Unmetered Supplies Data Services changed from UDS to UMSDS. Need to ensure that all of the role codes referenced in DES-138 are included in E2E001 and that there is a full explanation of what these are. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update all the role codes referenced in DES-138 to ensure they are included in E2E001 and that there is a full explanation of what these are. | Data interface correction | Supporting Docs | Interface Catalogue | E2E001 E2E Architecture Document
MHHS-DIN-591 | KH |  | 2023-08-03 | Elexon | 2974 | Michael Ceney | Central Body | Update to MDS Method statement | The MDS Method Statement Section 2.1 should read: If today > MDS Run Date (RF) for SP End Date/Time [DI-082] in the Master Settlement Table in ISD ECS1003 - SP End Date/Time [DI-082] has already passed "MDS Run Date (RF) [ISD.RunDate-RFDate] |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update DES138 and MDS Method Statement Section 2.1 to read "If today > MDS Run Date (RF) for SP End Date/Time [DI-082] in the Master Settlement Table in ISD ECS1003 - SP End Date/Time [DI-082] has already passed "MDS Run Date (RF) [ISD.RunDate-RFDate]" update ECS1003 in 00-introductions and IF-21 | Data interface correction | Supporting Docs | Supporting Docs | MDS Method Statement MHHSP-DES138-Interface Catalogue
MHHS-DIN-592 | SW |  | 2023-08-03 | Design Team | 2717 | Martin Freeman | Central Body | Update StatusMessage and StandardResponseBody in E2E001 to provide more clarity | There are inconsistencies between StatusMessage / Standard Response body definitions for what is contained with E2E001 and Swagger, these need to be aligned. Clarity needs to be provided on how TransactionID is populated in Status Message for Level 2 validation and Level 4 validation and for Level 4 validation, how this is sent to original sender. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Align inconsistencies between StatusMessage / Standard Response body definitions for what is contained with E2E001 and Swagger. Provide clariry on how TransactionID is populated in Status Message for Level 2 validation and Level 4 validation | Data interface correction | Supporting Docs | Interface Catalogue | E2E001 MHHSP-DES138-Interface Catalogue
MHHS-DIN-593 | ME |  | 2023-08-04 | Design Team |  | Kevin Spencer | Programme Design | Update to AC Method Statement | Update required to the AC Method Statement to amend calculation where less than 365 days of data is available and a change to section 2.2 to allow calculations to be undertaken on Calendar days |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | The following changes below in red have been made to section 2.2 of the AC Method Statement The Market-wide Data Service (MDS) should schedule the calculation of MPANs requiring a new Annual Consumption for active MPANs evenly across each working day of the month and publish on the day the day of the calculation. The recalculation shall be performed each month, for every MPAN and every 30 Calendar days +/- 5 Calendar days of the date of the previous calculation. Changes to the calculation of less than 365 days available are no longer reuried as agreed with Helix | Method statement correction | Supporting Docs | Method Statement | Annual Consumption Meth 10
MHHS-DIN-594 | SC | SCS DI-207 | 2023-08-04 | Design Team |  | Sean Cooper | Programme Design | Correction to BP10 Related MPANs | Rejection was incorrectly shown being sent direct from REGS rather than from REGS Via DIP. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Rejection was incorrectly shown being sent direct from REGS rather than from REGS Via DIP. moved the starting point from step 340 to step 360 for rejections on BP010B | Process Model correction | MPAN Ownership | Supporting Document | BP010-Registration Updates
MHHS-DIN-595 | SC | SCS DI-208 | 2023-08-04 | Design Team |  | Sean Cooper | Programme Design | Correction of Type in ISD Doc Table 16 | Correction of type in definition of subscript 3 for table M16 - "Market Participant ID" changed to "Market Participant Role" |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Correction of type in definition of subscript 3 for table M16 - "Market Participant ID" changed to "Market Participant Role" | Clarification | Supporting Docs | supporting document | MHHSP_EDI021_ISD_Entities
MHHS-DIN-596 | SC |  | 2023-08-04 | Design Team |  | Sean Cooper | Programme Design | Clarification of SP Appointment Time(s) | Per DRG decision all SP Appointment times shall be effective from Midnight UTC Time. Clarification added to IF-031/If-036 |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Added validation rule to IF-031 to ensure appointments are made at midnight [UTC/Clock]. Pending agreement from Working Group and DAG. | Clarification | Supporting Docs | Interfaces | DES-138 Interface Spec
MHHS-DIN-597 | SC | SCS DI-193 | 2023-08-07 | MHHS |  | Sean Cooper | SRO Design | IF-026 B068 Presence | IF-026 / B068 - SCS requested removal of wording "must be required for smart meter removed" as this is inherent as part of the Event Type. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | IF-026 / B068 - SCS requested removal of wording "must be required for smart meter removed" as this is inherant as part of the Event Type. | Clarification | Supporting Docs | Interface Catalogue | DES-138 Interface Spec
MHHS-DIN-598 | SC | SCS DI-176 | 2023-08-07 | St Clements |  | Madison Layton | Software Provider | Incoming Supplier Notifications - Clarification | SCS raised a query around whether certain flows should be copied to an incomming Supplier (PUB-006, PUB008 etc. etc.) The current design does not include copying of these flows to an incoming supplier, (not represented in either Requirements or BP maps). IF-036 (and accompanying D-flows as required) provides suppliers with a clear starting point containing all the information they need to support servicing the customer. Design Team feel any change in this area would require a CR. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Any change in this area would require changes to the REGS Requirements to implemnt Primary Routing, as copying of such flows could not be performed by DIP Secondary Routing. CR would be required to confirm new requirements and allow for IA on REGS and Suppiers design. Design Team also note that no other issues/DIN raised on this issue, by suppliers or other participants. | Clarification | Clarification - No change Required
MHHS-DIN-599 | BK | SCS DI-198 | 2023-08-07 | St Clements |  | Madison Layton | Software Provider | Data Cleansing required on IHD, SMSO and Installation Date | SCS raised a a query on the three items below that are not under the Data Cleanse Plan that may need cleanse work. 1) IHD - Should be populated for smart meters, and only smart meters (not currently validated) 2) SMSO - Should be populated for smart meters and only smart meters (not currently validated) 3) Installation date - Should not be prior to MPAN Creation date (Legacy data integrity issues of meters migrated into MPRS) |  | Closed | [6 empty] | #REF! |  |  | #REF! | This change has been forwarded onto the Data Cleansing Working Group as it is not a design issue. Design Team also advised SCS to raise these issues within the working group. | Clarification | Clarification - No change Required
MHHS-DIN-600 | ME |  | 2023-08-07 | Elexon | 4566 | Rashmi Radhakrishnan | Central Body | ISD Entity M18 Discrepancy | In the ISD Entity Document the table shows {Effective From Date {DIPRole} and {Effective To Date {DIPRole}, however the exmaple table and column details have been titled as {Effective From Date {MP2DPM} and {Effective To Date {MP2DPM}. These should be changed to align with the first table in entity M18 |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Corrected M18 Col Headings and column name references to read "DIPRole" | Data interface correction | Supporting Docs | supporting document | MHHSP_EDI021_ISD_Entities
MHHS-DIN-601 | SW |  | 2023-08-07 | Kraken | 4485 | Adrian Serban | Software Provider | Incorrect on M0 common block in IF-018 | In Swagger, it appears the block is correct (M0), but the label is incorrect (M1) for IF-018. The label needs to be updated to M0 to align with the block. This needs to be updated in Swagger so the label is incorrect. In IF-019 and IF-020, there is an inconsitency of use of M1 vs M0. |  | Closed | [6 empty] | #REF! |  |  | #REF! | M1 is used in IF-019 and IF-20. M0 is used in all other IFs where required. Swagger version 1.4 has been reviewed and correctly reflects this position. | No Change
MHHS-DIN-602 | RG |  | 2023-08-08 | Design Team |  | Rob Golding | Programme Design | Add Interface, Event Code enumeration to Swagger for interface blocks | Interface and Event code validation and alloawable blocks is missing from the DIP. Rather then getting Avanade to code these dependencies the proposal is to intoduce the restrictions into the Swagger |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update the swagger for the majority of interfaces where different event codes require different combinations of optionality for the blocks they reference. An example of this has been done already for IF-001 in the new swagger file Interface-001. | Improved error trapping at interface | Minor | Interfaces | Swagger 1.5
MHHS-DIN-603 | SW |  | 2023-08-09 | Design Team | 4022, 4700 | Steve Weston | Central Body | Clarity on A0 block being removed | Section 4.2.1 of the E2E001 design has a diagram that shows that the A0 common block is removed by the DIP prior to sending out the message to onward particpants. This is inconsistent with the rest of the design. Section 4.2.1 needs to be updated so that this shows A0 not being removed. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update Section 4.2.1 of E2E001 figure 4 so that this shows A0 not being removed | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger 1.4 | E2E001 E2E Architecture Document Swagger 1.5
MHHS-DIN-604 | SW |  | 2023-08-09 | Design Team | 4945 | Steve Weston | Siemens | Clarity on B066 mandatory on IF-035 | In DES-138, B066 block in IF-035 is shown as mandatory and also defined as mandatory in Swagger. This should be conditionally mandatory as per B019, so this needs to be updated to conditionally mandatory in DES-138 and also in Swagger 1.5. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update B066 block in IF-035 to mandatory where event code DCC-MDR Outcome Swagger 1.5, no change in DES138 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-605 | SC |  | 2023-08-09 | Design Team |  | Sean Cooper | Programme Design | Update "Switch Cancellation" Info Message Box of BP002 & BP003 | Message updated to make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations received prior to PUB-34 processing will be managed by normal queue processing. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Message updated to make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Where in the rare scenario a cancellation is received and accepted by the Registration Service before the PUB-034, the Registration Service will not lapse on receipt of the cancellation, instead re-validation the day prior to the appointment start date would trigger a lapse. | Clarification | MPAN Ownership | process | BP002 / BP003 Change of SP
MHHS-DIN-606 | SC |  | 2023-08-09 | Design Team |  | Sean Cooper | Programme Design | Update Ops C to include clarification on issuing of IF-035 | Make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations received prior to PUB-34 processing will be managed by normal queue processing. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update OPS Choreography document (Foot-note to OPC-190) to clarify processing of IF-035 (See DIN-605) | Clarification | Supporting Docs | Supporting Document | MHHSP-OPC001 Operational Choreography
MHHS-DIN-607 | SC |  | 2023-08-10 | St Clements |  | Sean Cooper | Programme Design | Update IF-035 Lapsed Reason Code | SCS Request Update IF-035 Lapsed Reason Code from "Switch Cancelled" to "Registration Cancelled" |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Updated IF-035 Lapsed Reason Code LP004 from "Switch Cancelled" to "Registration Cancelled" | Clarification | Minor | Interfaces | DES-138 Interface Doc
MHHS-DIN-608 | SC | SCS DI-206 | 2023-08-10 | St Clements |  | Sean Cooper | Programme Design | Correction of Inaccuracy on BP003 | Steps 86,87,88 added to better reflect that REGS will actually send TWO IF-035 messages not just one. IF-035 [SendMTD] will be issued to Incumbent MS and [AppOutcome] event will be issued to DS/Supplier. BP003 now mirrors the drafting in BP002. There is no change in underlying requirement here - redrafting is simply a more accurate representation of REGS activity. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Steps 86,87,88 added to better reflect that REGS will actually send TWO IF-035 messages not just one. IF-035 [SendMTD] will be issued to Incumbent MS and [AppOutcome] event will be issued to DS/Supplier. BP003 now mirrors the drafting in BP002. | Clarification | Minor | Interfaces | BP003
MHHS-DIN-609 | SC |  | 2023-08-10 | Helix |  | Sean Cooper | Programme Design | Helix Issuing of IF-040 Annual Consumption Messages | Discussion held with Helix on proposed approach to issuing IF-040 messages. Current design suggests that messages should only be issued on Working Days - Design Team are exploring why this is the case (risk of substantial peak esp on 4 day long weekends). preference would be for Helix to issue IF-040 on each calendar day. |  | Implemented |  |  |  |  | 2023-09-13 | Interim Release 5 | #REF! | 2023-09-13 | Interim Release 5 | #REF! | Update the OpsC document to set a 24hr rather than a 2hr limit around processing the IF-040 interfaces only | Clarification | Supporting Docs | Supporting Document | OPS Choreography
MHHS-DIN-610 | SC |  | 2023-08-10 | Helix |  | Sean Cooper | Programme Design | Clarification of IF-013 Functionality (also ref 572) | 1. IF-013 is only issued as part of the RF Run i.e. simply to notify Suppliers of what the default consumption for a period(s) is, where no data has been submitted by the DS come the point of RF. … … Should suppliers wish to derive this for pre-RF settlement runs then they are able to do so easily enough using the own data and the published Load Shapes. Need to validate if IF-013 should be issued after each Settlement Run OR only after RF Run. Also need to validate the IF-10 should NOT be issued after II Run. 2. The second view is that the IF-013 is issued on every settlement run undertaken for sites where no PUB-021 data has been received DIP impact concerns wrt to volumes of IF-013 would need to be addressed if Option 2 is the position. Dupe with DIN-572 |  | Implemented |  |  |  |  | 2023-09-13 | Interim Release 5 | #REF! | 2023-09-13 | Interim Release 5 | #REF! | Following Review at DRG meeting - agreement reached that IF-013 should NOT be sent for the II Run and should only be issued for SF and later Runs. DES-138 IF-013 Additional notes updated to reflect this decision. ----- MDS Method statement also requires update to record this decision. The following text has been added to the Method Statement Restrict sending of IF-013 until the SF Settlement Run The following statement has been added to the MDS Method Statement section 9.2 The sending of IF-013 will be restricted until the SF Settlement Run | Clarification | Supporting Docs | Supporting Document | DES-138 Interface Catalogue MDS Method Statement
MHHS-DIN-611 | KH |  | 2023-08-11 | Elexon | 3986 | Michael Ceney | Central Body | Changes required to MDS Method Statement | Following the release of DIN-332, changing EventCode [ConsumptionOnDe-energisedMpan], the MDS Method Statement needs updating to reflect this change. Section 9.3 states that the an exception report will be provided using IF-013, this needs to show IF-014 is to be used. Please can a new DIN be raised. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | We will update section 9.3 to state that the report will be provided using IF-014. | Method statement correction | Supporting Docs | Method Statement | MDS Method Statement
MHHS-DIN-612 | SC | PDA Test Issues | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | New IF-019 Validation Rules Re Unmetered Related MPANs | Added x2 new validtion rules to prevent the creation / addition of Related MPANs with a Connection Type of "U - Unmetered". No validation applied to remove so as to allow for the resolution of any historically erroneous links |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Added x2 new validation rules to prevent the creation / addition of Related MPANs with a Connection Type of "U - Unmetered". No validation applied to remove so as to allow for the resolution of any historically erroneous links | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-613 | SC |  | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Remove Reference to SP Appointment Start Time(s) | In line with DRG Decision on 4th Aug - it was agreed that ALL Service Provider Appointments should commence at Midnight UTC. Text against DI-086 and DI-121 has been removed. A new section addressing the treatment of Time has been added to the Additional Information tab of DES-138 |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | In line with DRG Decision on 4th Aug - it was agreed that ALL Serive Provider Appointments should commence at Midnight UTC. Text against DI-086 and DI-121 has been removed. A new section addressing the treatment of Time will be added to the Additional Information tab of DES-138 as part of Interim Release 5 (DIN-614) | Design Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-614 | SC |  | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | Create new "Time" Advisory Notes in Registration Additional Info Section | SC to create Treatment of Time section |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Add clarification on Regs Notes tab. around appointment time and Transfer read time. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-615 | SC |  | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Number of Registers Validation | Clarification following on from DIN-574. Text against Number of Register Digits fields amended to say "per the manufacturer specification" . Note text for SCS validation will remain unchanged. Swagger validation of this field updated to match SCS logical test ie value can be 0-9 |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | Clarification following on from DIN-574. Text against Number of Register Digits field amended in IF-002, IF-005, IF-006, IF-033, to say "per the manufacturer specification". Note text for SCS validation will remain unchanged. Swagger validation of this field updated to match SCS logical test ie value can be 0-9. | Design Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-616 | SC |  | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | Review of COS Transfer of Readings Process Required in light of SP UTC Decision | A Review of BP003C is required to impact assess implications of SP UTC Decision |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | BP003C may need updating follow impact assessment | Clarification | Supporting Docs
MHHS-DIN-617 | SC | PDA Test Issues | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | Note on Discretionary Use of IF-023/IF-040 by Data Service | Missing interface notes on Discretionary Use of IF-023/IF-040 by Data Service |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Added interface notes to clarify Annual Consumption usage in IF-040 and Load Shape Totals in IF-023 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-618 | KH |  | 2023-08-15 | ESG | 5859 | Patricia Parker | Software Provider | Updating routing within DES138 - PUB-026 | Could you please clarify what updates the Metering Service will receive via the PUB_026. From the routing the only update is re the SCCandProfile Class. However, BP010C alludes to the MS receiving an update for the SMSO - could you please confirm which is correct? |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | To update PUB-026 adding XMSC to the SMSO secondary routing. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-619 | SC | PDA Test Issues | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Draft Umetered Change of Energisation Status Business Process Map | Update BP08 existing or draft Unmetered Specific version. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Pending feedback from PDA on UMS process. No feedback provided - closed
MHHS-DIN-620 | SC | Test Issues | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | Remove EES as a Recipient of IF-001 | Remove EES as a Recipient of IF-001 | CR028 | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Removed EES as a Recipient of IF-001 - EES gets this info from CSS | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-621 | SC |  | 2023-08-17 | MHHS |  | Sean Cooper | SRO Design | Changes to D303 DTN Flow | Need to make "Manufacture and Type" non mandatory in the D303 flow. Follow migration to MHHS it is possible that this data item is not held in REGS and therefore not shared with all MHHS Participants incl. MS who currently would need to provided it on the D303. Discussions were held in Data Working group around back population of this data item but that proposal was REJECTED - therefore only other option is to make this field optional in D303 |  | Implemented | No |  | Design gap | TBC |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Passed to Matt McK to add to existing industry CP changes.
MHHS-DIN-622 | SC | SCS | 2023-08-17 | St Clements |  | Sean Cooper | SRO Design | DIP Validation of Sender Correlation ID | Implement DIP validation to check for incorrect population of Sender Correlation ID. |  | Closed | [6 empty] | #REF! |  |  | #REF! | CR would be required for the DIP to implement Sender Correlation ID validation. Decision to implement Level 3/4 Sender Correlation ID validation is with the recipient. | Clarification
MHHS-DIN-623 | SC | SCS | 2023-08-17 | St Clements |  | Sean Cooper | Programme Design | Change IF-001 Routing | Add SUPL (Linked Supplier) as an additional Primary Receipient of Inital Registration Event |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Add SUPL (Linked Supplier) as an additional Primary Receipient of Inital Registration Event for IF001 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-624 | ME |  | 2023-08-18 | Design Team |  | Miriam Ellis | Programme Design | BP013 DDE Updates | MHHS test team have identified discrepancies within the ECS BPM's that require updates to align with the ECS reports. Updates are required to BPM13 DDE |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Updates to BPM013: 1. Update reference of MHHS-REP-001 to ELEX-REP-001 in BP header 2. Update reference of REP-005 to ELEX-REP-005 in BP header 3. Reference of MHHS-REP-002A included with BP header 4. Reference of REP-002 changed to ELEX-REP-001 | Clarification | Supporting Docs | Reporting Catalogue | BPM013
MHHS-DIN-625 | SC | DI-210 | 2023-08-18 | St Clements | 6221 | Sean Cooper | Programme Design | B092 should also be an array to allow MPRS to populate multiple rejections | B092 should also be array to allow MPRS to populate multiple rejections |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Consider breaking out DI-980 into an array in B092 block of IF-035. Block B099 added containing DI-979 and DI-980 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue Swagger 1.5
MHHS-DIN-626 | SC | ESG | 2023-08-22 | ESG |  | Sean Cooper | Programme Design | Update Routing of IF-003 | Routing of this flow should match that of the IF-037 - in that a copy should also be sent to the Supplier. IF-003 Routing table updated to show Supplier as being a receipient of the iF-003 |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Routing of this flow should match that of the IF-037 - in that a copy should also be sent to the Supplier. IF-003 Routing table updated to show Supplier as being a receipient of the iF-003 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-627 | SC | ESG | 2023-08-22 | ESC |  | Sean Cooper | Programme Design | Update Interface Doc "Correlation ID Required" to "Correlation ID Created" | Inconsistancy indentified in the column headings across different IFs. All should read "Correlation ID Created" as this column denotes if the DIP IF should create/copy a DIP Correlation ID value or not. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update Interface Doc "Correlation ID Required" to "Correlation ID Created" | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-628 | SC |  | 2023-08-23 | Design Team |  | Sean Cooper | Programme Design | Add in Missing IF-021 Validation | Add NEW validation to ensure that "UTC Settlement Date" has time of Midnight UTC. Added clarification to existing validation rule that time element of "Settlement period end date time" should align with Settlement period duration |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Add NEW validation to ensure that "UTC Settlement Date" has time of Midnight UTC. Added clarification to existing validation rule that time element of "Settlement period end date time" should align with Settlement period duration | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-629 | MF |  | 2023-08-25 | Design Team |  | Mike Fensome | Programme Design | Routing for SUPC on IF-037 | To ensure that the outgoing Supplier are correctly notified of de-appointment of their Service Providers, routing rules for SUPC updated to Primary routing for IF-037 |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | SUPC routing moved from Secondary to Primary for IF-037 for all events | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-630 | MF |  | 2023-08-25 | Design Team | N/A | Mike Fensome | Programme Design | Remove incorrect arrow on BP002 | Arrow incorrectly added into BPOO2 between steps 225 and steps 245 |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Arrow between steps 225 and steps 245 on BP002 removed. Previously added in error. | Process Model correction | Minor | Interfaces | BP002
MHHS-DIN-631 | SC |  | 2023-08-29 | MHHS | N/A | Sean Cooper | SRO Design | Swagger Alignment - Block B051 | Required Data Items field names do not match those specfied in the defintion. |  | Implemented | [5 empty] | Interim Release 4 | #REF! |  | Interim Release 4 | #REF! | loadShapeGSPGroup and loadShapeDomesticPremiseIndicator added to Required fields section to align with block definition. | Correction | Minor |  | DES-138 Interface Cat
MHHS-DIN-632 | SC |  | 2023-08-31 | Helix | N/A | Sean Cooper | SRO Design | Header & Footer Requirements for ISD Entity Files | ISD Specification should be updated to include specification/definition of a standard Header and Footer to be applied to each ISD Entity CSV file. |  | Assessment Complete / Implementation Deferred | No |  | Design gap | Helix, Suppliers |  | Post Go-live Release | #REF! |  | Post Go-live Release | #REF! | Decision required on exact content/structure of Header ... Is a footer required? If so what should it include (eg number of Entity entries) | Requirement correction | Supporting Docs | ISD | EDI021 ISD Entities Document
MHHS-DIN-633 | SC |  | 2023-08-31 | Helix | N/A | Sean Cooper | Programme Design | Update to ISD E45 | Update Entity 45 - Market Role code needs to allow Blanks in order to align with other tables in ISD and to provide for [new] Market Participants who dont have a legacy market particpant role code |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update Entity 45 - Market Participant Role code needs to allow Blanks (Optional) in order to align with other tables in ISD and to provide for [new MHHS] Market Participants who dont have a legacy market participant role code | Clarification | Supporting Docs | Supporting Document | MHHSP_EDI021_ISD_Entities
MHHS-DIN-634 | KH |  | 2023-09-01 |  | 6616 | Tym Huckin | Consultancy | Update UMSDS Method Statement with correct comments for Null value | In row 2, where we have a "live" summary but it is de-energised, it says to put "A" actual data flag and use Estimation Reason Code "7", but the DI-076 column in that row says this should be Null. |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | In 10.1 the table states in row two that the "Estimation Reason code" is Null and therefore the comments column will be updated to: If a D0388 has been received with load associated data and the MPAN is de-energised the load should be calculated, submitted as ‘A’ Flagged but with an Estimation Reason Code of Null | Correction | Supporting Docs | Method Statement | UMSDS Method Statement
MHHS-DIN-635 | RG |  | 2023-09-04 | Design Team |  | Rob Golding | Programme Design | Status Code needs tidying in StandardResponseBodyType | 4In the “StandardResponseBodyType” definition, there is a required property called "statusCode" that is not listed among the properties. Could you please address this inconsistency? |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Simple update | Data interface correction | Swagger |  | Swagger
MHHS-DIN-636 | SC |  | 2023-09-04 | Design Team |  | Sean Cooper | Programme Design | Removal of YAML Name Fields from Data Catalogue | Following discussions agreement to remove YAML fields from Data Catalouge. Swagger will be the definitive reference for the Jason/Yaml property labeling etc. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Following discussions agreement to remove YAML fields from Data Catalogue. Swagger will be the definitive reference for the Json/Yaml property labelling etc. | Data interface correction | Supporting Docs | Interface catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-637 | RG |  | 2023-09-04 | Design Team |  | Rob Golding | Programme Design | Data Catalogue items incorrectly use maximum and minimum | String need to be range bounded by maxLength & minLength |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update swagger so that maxLength and minLength are used instead of maximum and minimum | Dat Interface correction | Swagger |  | Swagger
MHHS-DIN-638 | RG |  | 2023-09-04 | Design Team |  | Rob Golding | Programme Design | Block: D0, Field: serviceTicketURL. DES138 specifies 'string max 225', Swagger specifies 'string max 250' | Set to 250 in DES 138 |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | DES138 update, 01-Data Catalogue & 02- DIP Common : Block: D0, Field: serviceTicketURL (DI-978) set to 250 | Data interface correction | Supporting Docs | interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-639 | RG |  | 2023-09-04 | Design Team |  | Rob Golding | Programme Design | DI-138-Customer-Direct-Contract-Data-Service-DIP-ID & DI-140-Customer-Direct-Contract-Metering-Service-DIP-ID to be nullable | Update both to be nullable |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update swagger so that DI-138-Customer-Direct-Contract-Data-Service-DIP-ID & DI-140-Customer-Direct-Contract-Metering-Service-DIP-ID are DT-006N, i.e. nullable | Data interface correction | Swagger |  | Swagger
MHHS-DIN-640 | RG |  | 2023-09-05 | Design Team |  | Sean Cooper | Programme Design | Custom Block: B022, Field: Metering Point Postcode. Interface Catalogue specifies CMO as ‘M’ for IF-018, all other interfaces specify CMO as ‘O’. | Update DES138 so that all versions are the same and marked as optional Custom Block: B022, Field: Metering Point Postcode. Interface Catalogue specifies CMO as ‘M’ for IF-018, all other interfaces specify CMO as ‘O’. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update DES138 so that all versions of B022 are the same and fields marked as optional | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-641 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | Custom Block: B022, Field: Metering Point Postcode. Interface Catalogue specifies no min length, but min length of 6 specified in Swagger. | Update swagger to align |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update swagger to align minlength removed from DT007(N) | Data interface correction | Swagger |  | swagger
MHHS-DIN-642 | RS |  | 2023-09-05 | MHHS | 7382 | Rob Golding | SRO Design | NFR0045 Performance Efficiency | this NFR does not clearly define how the DIP will throttle participants where connection are over a mutually shared mTLS connection. Shared mTLS connections will be used by many parties such as DIP Connection Providers, the requirement to use them being placed on parties that will be Placing Reliance on a Connection Provider. Effectively, this means that multiple parties will use the mTLS connection and which, under certain circumstances could see significant increases over that mTLS if more than one party’s message volumes increased. |  | Closed | No | [9 empty] | This item is being managed as part of the DIP work-off plan
MHHS-DIN-643 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | B029 Fields marked as mandatory | B029 Condtitonal mandatory marked as required. Block will be conditional |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update DES138 & swagger | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue Swagger
MHHS-DIN-644 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | DI-122 Profile Class has a minLength of 2 in Swagger. | add minLength clause |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update swagger DI-122 Profile Class to minLength =2 in swagger | Data interface correction | Swagger |  | Swagger
MHHS-DIN-645 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | Clarify 'AllRoles' for DIP routing for IF-047 | Update to include MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update DES138 IF-047 so that all roles are specified (MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES) | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-646 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | DT-002N-MPAN requires a minLength of 13 | add minLength clause |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update DT-002N-MPAN to min length & max length 13 in swagger | Data interface correction | Swagger |  | Swagger
MHHS-DIN-647 | RG |  | 2023-09-06 | Design Team |  | Rob Golding | Programme Design | Replace reportId with interfaceId in the ECS reports | Replace reportId with interfaceId in the ECS reports to make S0 block consistent across all reports/interfaces |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update swagger & MHHSP - ERI011B - ECS Reports - External v5.4 | Reporting correction | Supporting Docs |  | MHHSP - ERI011B - ECS Reports - External Swagger
MHHS-DIN-648 | KH |  | 2023-09-06 | St Clements |  | Vicki Holland | Software Provider | DI-496 data item | This data item was given a max value of 48, however the max value should be 50 to allow for the clock change day in October which has 50 settlement periods. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | All settlements reports will be in clock time and can have 46, 48 or 50 Settlement Periods. DI-496 is INT(3) to allow for a change to 15 minute Settlement Periods which would require a value of 100 for the Autumn Clock Change in the future. Maximum value in Swagger and ECS Reports to be updated to 50 for half hourly settlement periods. | Reporting correction | Supporting Docs | interface catalogue | MHHSP - ERI011B - ECS Reports - External MHHSP - ERI011A - ECS Reports - Internal Swagger
MHHS-DIN-649 | SC |  | 2023-09-06 | MHHS |  | Sean Cooper | SRO Design | REGS-EES 'Refresh' Flow - IF-051 | Following discussion with SCS and EEC - proposed definition of refresh message iF-051 |  | Closed | [6 empty] | #REF! |  |  | #REF! | Initial draft reviewed by EES and SCS - revisions to follow. Closed as duplicate - refer to DIN-051
MHHS-DIN-650 | BK |  | 2023-09-06 | Design Team |  | Rob Golding | Programme Design | Introduction of Compressed Payloads into DIP Messages | Detailed analysis of the some of the ECS reports, specifically REP003, has found that some of the reports can potentially grow to a very large size ~ 12MB. Within MHHS message design there is a notional upper limit for the size of messages which is 1MB, and hence these messages will exceed this constraint. | CR030 | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | The proposal is that the Sender (ECS) compresses the report and base64 encodes the data into the CustomBlock. The recipient will know that a specific message flow is compressed, and hence will need to decompress the payload. The proposal is to use gzip for the compression. This new pattern for compressed payloads will be initially introduced for the following reports: REP-002 LDSO report for DUoS – aggregated data REP-002A Embedded Network report for DUoS – aggregated data REP-003 BM Unit Allocated Demand Volumes to Market Participants REP-004 Supplier Deemed Take Report REP-006 Aggregated Uncorrected volumes by CCC to Market Participants REP-007 VAS Exception Report to Suppliers and BSCCo REP-008 MDS Exception Report to LDSOs REP-009 EMRS Report for Suppliers A covering statement has been included within the Introduction tab of ECS reports which highlights the changes made to Swagger. | Data interface correction | Technical Artefact | Technical Artefact | Swagger 1.5 MHHSP - ERI011A - ECS Reports - Internal
MHHS-DIN-651 | MH |  | 2023-09-07 | MHHS |  | Kevin Spencer | SRO Design | Supplier Registration of ABMU/ MPAN mapping | There is a design gap around Supplier ABMU Mapping held by ELEXON. Suppliers will need to register their MPAN/ ABMU Mappings for MHHS. Currently, they send a D0297 to HHDAs to provide the Mapping and can populate the SVA Metering Service Register for MSID Pairs where they are used in the Balancing Mechanism using the P0278 and self-service via ELEXON Kinnect. The issue is that for MHHS the export might be with one Supplier and the import with another. The validation in Kinnect only supports a pair being submitted mapping both import and export to the ABMU. Likewise, the P0278 only supports the provision of MSID pairs. We think a new flow may be needed or the D0297 re-routed to PMP. |  | Closed | No |  | Design gap | Helix | 2024-01-12 |  | #REF! | 2024-01-12 |  | #REF! | Pending Helix raising a Change Request
MHHS-DIN-652 | RG |  | 2023-09-07 | Design Team |  | Rob Golding | Programme Design | DI-091-Number-Of-Displayed-Register-Digits update in DES138 to reflect the range 0-9 | DI-091-Number-Of-Displayed-Register-Digits update in DES138 to reflect the range 0-9 |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update DI-091 in the data catalogue to have the correct min (0)/ max(9) values | Data interface correction | Supporting Docs | Interfaces | DES138 - Interface Doc
MHHS-DIN-653 | RG |  | 2023-09-07 | Design Team |  | Rob Golding | Programme Design | MO block removed from IF-047 | MO block removed from IF-047 |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | M0 block removed from IF-047 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-654 | RG |  | 2023-09-07 | Design Team |  | Rob Golding | Programme Design | DI-130 RMP and DI-131 MP status maxlength | Reduce maxlength to align with eumerated type (50->1) |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Max length updated to 1 in Swagger for DI-130 RMP and DI-131 MP status | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-655 | RG |  | 2023-09-08 | Design Team |  | Fredrik Omland | Software Provider | Add a set no additional properties to false | Adding a set no additional properties condition to the swagger objects improves the validation |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Add "additionalProperties: false" to all schema objects in swagger so that no additional properties / fields can be attached to an object that are not specficied in the schema. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-656 | SW |  | 2023-09-11 | Design Team |  | Steve Weston | Central Body | All S1 properties to be mandatory | Ensure all S1 properties are mandatory as per DES-138 in Swagger 1.5 |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Ensure all S1 properties are mandatory nullable as per DES-138 in Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-657 | ME |  | 2023-09-11 | Design Team |  | Miriam Ellis | Programme Design | NEW ISD Entity | A request has come in from St Clements requesting for a New ISD entity which lists settlement period quality indicators, with a mapping to an actual or estimate indicator. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | ISD Entity M19 Settlement Period Quality Indicators has been added to the ISD entity document. | Data interface correction | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-658 | ME |  | 2023-09-12 | Design Team |  | Miriam Ellis | Programme Design | Updates to ERI011B | Following an internal review of the external ECS reports a few discrepancies have been highlighted that need to be amended |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Changes to ECS External Reports 1. MHHS-REP-006: Block R051 Demand Disconnection Event Details - parent updated to R032 2. Data Catalogue: Format of DI-492, 496, 487, 488, 484 updated to reflect MHHS Data Type | Design Ambiguous | Supporting Docs | Various documents | ECS Reports
MHHS-DIN-659 | RG |  | 2023-09-12 | Design Team |  | Rob Golding | Programme Design | Update REP007 | Update REP007 to include blocks R007 |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update REP007 to include blocks R007 | Design Ambiguous | Supporting Docs | Various documents | Swagger 1.5
MHHS-DIN-660 | ME |  | 2023-09-12 | St Clements | 4513 | Vicki Holland | Software Provider | Supplier version of REP-002 | St Clements are requesting for one report per supplier MPID that covers all combinations of distributor and GSP group. The current solution for REP-002 is a supplier will receive a report per distributor id |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | REP002 has been split into two separate reports. There is now a Supplier version (MHHS-REP-002) and an LDSO Version (MHHS-REP-002B). Due to this change the MDS BPM/BPD (019) and DDE BPM/BPD (013) have also been updated to include the reference of REP-002B | Reporting correction | Supporting Docs | Various documents | MHHSP - ERI011B - ECS Reports - External v5.4 BP013 Demand Disconnection BPM/BPD v5.1 BP019 Market-wide Data Service BPM/BPD v5.1
MHHS-DIN-661 | RG |  | 2023-09-13 | IMSERV |  | Liam Lowey | Software Provider | Use of the term 'GUID' in messages | Messages are referring to "Device ID" data items as "GUID". For example "GPFGasGUID" in IF-004. However, a Device ID is not a GUID which is 128 bit number with a specific format. The Wikipedia article for GUID gives more information. Instead, Device IDs are 64 bit. This is misleading to implementors and maintainers. Could the naming of the properties be changed to reflect the identifier better? For example this appears to be a collection of 8 bytes in hexidecimal, i.e. a 64-bit quantity or 8 octets. Much like a MAC address or EUI64 for DCC is. Do you have other identifiers like this that require definition could we standardise on a different name for all of them? |  | Closed | [6 empty] | #REF! |  |  | #REF! | No further action taken
MHHS-DIN-662 | SW |  | 2023-09-14 | Design Team |  | Steve Weston | Programme Design | Update Sort Code and Account Number validation | DT-035-Sortcode and DT-035-Bank Acount Number have incorrect min / max Lengths. Sort Code should be min 6, max 8 with a regex applied for validation. Account number should be min 8 and max 10, with a regex for extra validation |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | DT-035-Sortcode and DT-035-Bank Acount Number have incorrect min / max Lengths. Sort Code should be min 6, max 8 with a regex applied for validation. Account number should be min 8 and max 10, with a regex for extra validation. This needs to be updated in ER011B and Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-ERI011B- ECS Reports
MHHS-DIN-663 | SW |  | 2023-09-14 | Design Team |  | Steve Weston | Programme Design | There are missing regular expressions that would improve the swagger schema validation | There are various data types that would benefit from regex added to improve validation. In addition, there could be new data types created / regex added to improve consistency and validation. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | There are various data types that would benefit from regex added to improve validation. In addition, there could be new data types created / regex added to improve consistency and validation. This needs to be updated in Swagger 1.5. The proposed regexes are for the following data types/items: DT-002 MPAN - DT-026 Group Correction Factor DT-027 MPID | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-664 | SC |  | 2023-09-14 | St Clements |  | Sean Cooper | SRO Design | Message [Error] Status Message Addressing | Based on feedback from SCS review the Message Status section of E2E to make it clearer that the "Sender ID is system sending the error, so if MPRS was sending an error it would be the REG DIP ID And Recipient ID would be who you are sending the error to – so would be the S1.senderDIPID on the original message" |  | Closed | No |  | Design ambiguous | N/A | [6 empty] | Clarified with SCS | Design Ambiguous | Supporting Docs | Supporting document | E2E001 - E2E Architecture Doc
MHHS-DIN-665 | SC |  | 2023-09-14 | St Clements |  | Sean Cooper | Programme Design | Tidy up Of "where available in Registration" usage | IF-001 / IF-002 /IF-036 Block 5 - Block 5 & IF-003 Blocks 095/096 & IF-033 Block 072 & IF-037 Block 10 and 11 heading had a note refering to Interface notes section which explained that block info may not always be availible. This was inconsistant with all other blocks which use the phrasing "Where Availible in the Regisration Service".... Block 5 updated to be consistant. IF Notes on each of these IF remain unaffected. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | IF-001 / IF-002 /IF-036 Block 5 - Block 5 & IF-003 Blocks 095/096 & IF-033 Block 072 & IF-037 Block 10 and 11 heading had a note refering to Interface notes section which explained that block info may not always be availible. This was inconsistant with all other blocks which use the phrasing "Where Availible in the Regisration Service".... Block 5 updated to be consistant. IF Notes on each of these IF remain unaffected. | Data interface correction | Supporting Docs | Interfaces | DES138 - Interface Doc
MHHS-DIN-666 | SW |  | 2023-09-15 | Design Team |  | Steve Weston | Programme Design | Data Type / Data Type Reference inconsistencies in DES-138. | Fix any IR5 Data Type / Data Type Reference inconsistencies between DES-138 & Swagger (between Data Catalogue Tab and IF / Common tabs) |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Fix any IR5 Data Type / Data Type Reference inconsistencies between DES-138 & Swagger (between Data Catalogue Tab and IF / Common tabs). Data Type Inconsistencies - DES-138 updates DI-000 is defined as a String 8, but in IF-040 and IF-045 this is defined as a String 6, so DES-138 has been updated to align. DI-019 is defined as a string 50 in IF-032, but in IF-034 and 36, is defined as String 10. In IF-035 this is blank. Updated IF-034, 35 and 36 so that DI-019 is a String 50. Swagger updated to align. DI-020 is defined as a string 50 in IF-032, but in IF-034 and 36, is defined as String 10. In IF-035 this is blank. Updated IF-034, 35 and 36 so that DI-020 is a String 50. Swagger updated to align. IF-023, B029, DI-026, DES-138 updated so Data Type is DT-003 to align with Swagger. IF-023, B035, DI-038, DES-138 updated so Data Type is DT-002 to align with Swagger. IF-023, B053, DI-041, DES-138 updated so Data Type is DT-016N to align with Swagger. IF-023, B053, DI-042, DES-138 updated so Data Type is DT-016N to align with Swagger. IF-023, B053, DI-044, DES-138 updated so Data Type is DT-016N to align with Swagger. IF-023, B053, DI-045, DES-138 updated so Data Type is DT-016N to align with Swagger. IF-033, B037, DI-075, DES-138 updated so Data Type is DT-002N to align with Swagger. IF-033, B037, DI-079, DES-138 updated so Data Type is DT-002N to align with Swagger. IF-050, B080, DI-111, DES-138 updated so Data Type is DT-003N to align with Swagger. IF-051, B080, DI-111, DES-138 updated so Data Type is DT-003N to align with Swagger. IF-050, B080, DI-112, DES-138 updated so Data Type is DT-003N to align with Swagger. IF-051, B080, DI-112, DES-138 updated so Data Type is DT-003N to align with Swagger. IF-014, B047, DI-147, DES-138 updated so Data Type is DT-016 to align with Swagger. IF-013, B049, DI-159, DES-138 updated so Data Type is DT-003 to align with Swagger. IF-003, B094, DI-159, DES-500 updated so Data Type is DT-003 to align with Swagger. IF-003, B008, DI-159, DES-813 updated so Data Type is DT-006 to align with Swagger. IF-003, B009, DI-159, DES-816 updated so Data Type is DT-006 to align with Swagger. DIP Common, D0, DI-986 removed Data Type from DES-138 and Swagger. Data Type Inconsistencies – Swagger updates IF-036, B068, DI-018 Swagger updated so Data Type is DT003N to align with DES-138. IF-051, B082, DI-023 Swagger updated so Data Type is DT003N to align with DES-138. IF-038, B021, DI-138, Swagger updated so Data Type is DT-006 to align with DES-138. IF-039, B021, DI-138, Swagger updated so Data Type is DT-006 to align with DES-138. IF-001, B006, DI-139, Swagger updated so Data Type is DT-006 to align with DES-138. IF-038, B020, DI-140, Swagger updated so Data Type is DT-006 to align with DES-138. IF-039, B020, DI-140, Swagger updated so Data Type is DT-006 to align with DES-138. IF-024, B058, DI-152, Swagger updated so Data Type is DT-016 to align with DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-667 | SW |  | 2023-09-16 | Design Team |  | Steve Weston | Programme Design | Mandatory / Optional blocks inconsistencies between DES-138 & Swagger | Fix any IR5 Mandatory / Optional blocks inconsistencies between DES-138 & Swagger |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Fix any IR5 Mandatory / Optional blocks inconsistencies between DES-138 & Swagger. Mandatory / Optional / Nullable Inconsistencies DIP Common, S1, DI-985 is Optional in Swagger and has been updated to be Mandatory to align with DES-138. DIP Common, S1, DI-996 is Optional in Swagger and has been updated to be Mandatory to align with DES-138. IF-013, B049, DI-161 is Optional in Swagger and has been updated to be Mandatory to align with DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-668 | SW |  | 2023-09-17 | Design Team |  | Steve Weston | Programme Design | Nullable / Optional Data Type / property inconsistencies between DES-138 & Swagger | Fix any IR5 Nullable / Optional Data Type / property inconsistencies between DES-138 & Swagger |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Fix any IR5 Nullable / Optional Data Type / property inconsistencies between DES-138 & Swagger. Nullable / No nulls Inconsistencies DI-988 is nullable in DES-138 but no nulls in Swagger, so Swagger to be updated so it is nullable to align with DES-138. DI-123 is nullable in DES-138 but no nulls in Swagger, so Swagger to be updated so it is nullable to align with DES-138. DI-150 is nullable in Swagger, to be updated in Swagger so this is Mandatory no nulls to align with DES-138. DI-018, update DES-138 so value is Mandatory nullable to align with Swagger. DI-138, update DES-138 so value is Mandatory nullable to align with Swagger. DI-023, DI-026 update DES-138 so value is Mandatory nullable to align with Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-669 | SW |  | 2023-09-18 | Design Team |  | Steve Weston | Programme Design | Min / Max Values inconsistencies between DES-138 & Swagger | Fix any IR5 Min / Max Values inconsistencies between DES-138 & Swagger |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Fix any IR5 Min / Max Values inconsistencies between DES-138 & Swagger. Min / Max Inconsistencies DI-019 update Swagger max length to be 50 to align with DES-138 DI-218 update Swagger to align with DES-138 min / max values. DI-300 update Swagger to align with DES-138 min / max values. DI-081 update DES-138 to have a max of 30 to align with Swagger. DI-091 update DES-138 to have a max of 9 to align with Swagger. DI-152 update DES-138 to have a max length of 13 to align with Swagger. DI-161 update DES-138 to align with Swagger value of 9999999. DI-167 update DES-138 to align with Swagger min / max values. DI-168 update DES-138 to align with Swagger min / max values. DI-190 update DES-138 to align with Swagger max value of 50. DI-194 update DES-138 to align with Swagger max value of 50. DI-990 update DES-138 to align with Swagger max value of 65. DI-992 update DES-138 to align with Swagger max value of 10. DI-081 update DES-138 to have a min of 30 to align with Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-670 | SW |  | 2023-09-15 | Design Team |  | Steve Weston | Programme Design | Unclear whether webhook URL's accept ports | Need to make it clearer in E2E design and Swagger whether port numbers are allowed in webhook / URLs and any formatting / options for environments |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Need to make it clearer in E2E design and Swagger whether port numbers are allowed in webhook / URLs and any formatting / options for environments E2E001 Section 4.5 updated | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 E2E001
MHHS-DIN-671 | ME |  | 2023-09-22 | Elexon | 11203 | Rashmi Radhakrishnan | Central Body | Updates to ISD Entities | 1. Make it clear what the data type/length is for Line Loss Factor Identifier. It is currently unclear as it reads 3 characters 2. Following consultation feedback of BSCP707, ISD Entity 23 requires an update to include the word 'Duration' and update to the character length and inclusion of date format |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 |  | Interim Release 5 | 2023-09-20 | 1. Update to ISD Entity M3 - update the length/data type of Line Loss Factor Identifier. Now reads as Up to 3 characters 2. Update to ISD Entity 23 - include the word 'Duration' to Settlement Period. This now reads Settlement Period Duration (Description). Update the data type/length to 50 characters and include a date format of YYYY-MM-DD | Design Ambiguous | Supporting Docs | EDI021 ISD Entities | MHHSP_EDII021_ISD_Entites 5.3
MHHS-DIN-672 | SW |  | 2023-09-19 | Design Team |  | Steve Weston | Programme Design | B033 has 9 required fields, but only available. Naming is also inconsistent for some of the required fields that do not exist. | B033 has 9 required fields, but only 8 are available. Naming is also inconsistent for some of the required fields that do not exist. Swagger needs to be updated to align with available fields and DES-138 mandatory values. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Fix any values in Swagger than do not align with required fields and ensure number of required fields aligns with number of fields available. -metering point postcode removed from required fields in B033 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-673 | RG |  | 2023-09-21 | Design Team |  | Rob Golding | Programme Design | Floating Point number regexes | DIN 267 inadvertently updated regexes to a pattern which does not align to the agreed format as of Technical Design Working Group Work-Off Issue D-0408th November 2022. The regexes need to align to what was agreed. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Update regex patterns for the following data types: DT-016, DT-022, DT-023, DT-024, DT-025, DT-030, DT-031, DT-032, DT-033 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-674 | SW |  | 2023-09-22 | ESG | 11369 | Kerry O'Donnell | Software Provider | Inconsistent Text description for DI-086 | In the Data Catalogue, DI-086 has a Text Description of "Supplier Effective From Date" but on IF-001 and IF-037, DI-086 has a text description of "Incoming Supplier Effective From Date" |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | In the Data Catalogue, DI-086 has a Text Description of "Supplier Effective From Date" but on IF-001 and IF-037, DI-086 has a text description of "Incoming Supplier Effective From Date". IF-001, IF-037, IF-051 have been updated so that the text description for DI-086 now matches Data Catalogue and Swagger - "Supplier Effective From Date". | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue
MHHS-DIN-675 | SC |  | 2023-09-25 | Design Team |  | Sean Cooper | Programme Design | IF-021 IF Consistency Validation Rules | New IF-021 Validation Rules with supporting Error Codes created to ensure validity of IF-021. New Error codes are : ECS1015 - Estimation Reason Code Cannot be Null & ECS1016 - Consumption Amendment Reason Codes Cannot be Null |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | New IF-021 Validation Rules with supporting Error Codes created to ensure validity of IF-021. New Error codes are : ECS1015 - Estimation Reason Code Cannot be Null & ECS1016 - Consumption Amendment Reason Codes Cannot be Null | Missing/incorrect validation rule | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue
MHHS-DIN-676 | RS |  | 2023-09-25 | St Clements | 11291 | Rob Golding | SRO Design | CR-018 NFR Change - E2E1009 | There are some NFRs that need tweaking post CR-018 Approval to align with the Registration Service Operating hours - Ie E2E1009. Given that MPRS sits behind an Adapter and does not operate 24/7 (as per CR-018) level 4 processing will operate in the same timeframes as Level 5. It needs tweaking to align with the CR-018 wording of: DIP messages received by the SMRS will be processed between the hours of 05:00 to 18:00 and 21:00 to 23:00 Working Days only. Messages received outside of these hours will be held in a queue until the next processing window. Automated responses to inbound messages (including Level 4 Validation) are expected to be returned within 60 minutes of receipt during the specified operating hours. |  | Closed | No |  | Design ambiguous | DIP Users, DIP |  |  | #REF! |  |  | #REF! | This DIN is superceded by CR039.
MHHS-DIN-677 | MF |  | 2023-09-26 | Utiliteam |  | Mike Fensome | Programme Design | Additional information added to IF-020 for Linked MPANs | On linking MPAN's, information is missing in IF-020 ( as provided in IF-002 ) to allow participants to interpret the flow. This needs adding to IF-020. Swagger updated accordingly |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | Agreed with SCS, for Import / Export Events ONLY, to add in the blocks that are present in the IF-002 namely B035 Linked MPANs / B-036 Linked Meter Info / B-075 MAP Info to IF-020. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue Swagger 1.5
MHHS-DIN-678 | ME |  | 2023-09-27 | Elexon | 11684 | Rashmi Radhakrishnan | Central Body | ISD Entities Updates | 1. Entity M14- Master settlement time table Fields: LSS Run Date, Payment Date & Notification Date should be changed to an Optional field. 2. Entity M18- Inconsistencies between M16 field name “ DIP Role Code” and M18 Field name “DIP Market Role”. Two different Field name used. 3. Entity M9 and M10, it appears that the data type length specified in the ISD EDI021 document for Field Unit Description 1, 2, and Manufacturers Designation might not be sufficient based on the data samples. – Datatype/length of these fields needs increasing. |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | 1. Entity M14- Master settlement time table Fields LSS Run Date, Payment Date, Notification Date all changed to Optional field. 2. DIP Role Code in Entity M16 updated to DIP Market Role 3. Entity M9 and M10, data type/length for Unit Description 1, 2, and Manufacturers Designation have been incresed to 100 characters | Design Ambiguous | Supporting Docs | EDI021 ISD Entities | MHHSP_EDII021_ISD_Entites
MHHS-DIN-679 | SC |  | 2023-09-27 | SRO Design |  | Sean Cooper | Elexon | MHHS Process for Additional BMU's Required | Clarification is required around how Additional BMU's will be requested, created and managed under MHHS |  | Closed | No | [5 empty] | #REF! |  |  | #REF! | Duplicate of MHHS-DIN-651 | No Change
MHHS-DIN-680 | ME |  | 2023-09-27 | St Clements | 11538 | Vicki Holland | Software Provider | Update to DI-322/DI-323 MHHS data type | The MHHS Data types for DI-322 and DI-323 requires an update to align with the SVA data catalogue as these 2 data items are reported to 9 decimal places. Swagger will also need to be updated to align with the ECS reports |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Updated MHHS data types and definitions for DI-322 and DI-323 within the ECS Data catalogue and where it appears in the reports. The Min and Max values have also been updated due to the change in data type. This change has been made in Swagger. Data types have been updated to a String 20(±9.9). | Reporting correction | Supporting Docs | ECS Reports Swagger REP003 version 010 | MHHSP - ERI011B - ECS Reports - External MHHSP - ERI011A - ECS Reports - Internal Swagger
MHHS-DIN-681 | SW |  | 2023-09-28 | ESG | 11492 | Kerry O'Donnell | Software Provider | DI-824 textual decsription in the Interfaces is inconsistent with the textual description in the Data Catalague | DI-824 textual description (Column D) in the Interfaces is inconsistent with the textual description (Column D) in the Data Catalogue. This DIN is to ensure the textual description is consistent in the Interfaces to the Data Catalogue and that found in Swagger. |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Textual description corrected on IF-036 to align with other interfaces | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-682 | MF |  | 2023-09-28 | CGI |  | Dave Webster | Data Service Provider | Remove commissioning flows sent to Data Service on BP009 | BP009 is misaligned with the Data Service requirements and incorrectly shows the Advanced Data Service receiving Commissioning Flows (D0383 and D0384) |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Removed commissioning flows sent to Data Service on BP009 (D0383 and D0384 into step 175). Note BPD was already correct. Updated BRS002 - MHHS-BR-MS-062 accordingly | Process Model correction | Supporting Docs | Process model correction Business requirements | BP009 BRS002
MHHS-DIN-683 | SW |  | 2023-09-28 | Flui | 11487 | Jason Jackson | Software Provider | E2E refers to T0 and Transaction Wrapper which are no longer required | E2E refers to T0 (section 4.8.2) and Transaction Wrapper (section 5.5) which are no longer required. This needs to be updated in the E2E design and an update provided in relation to Swagger and how this works. |  | Implemented | [5 empty] | Interim Release 5 | #REF! |  | Interim Release 5 | #REF! | E2E001 updated to reflect replay design | Design Ambiguous | Supporting Docs | Interfaces | E2E001
MHHS-DIN-684 | ME |  | 2023-10-03 | SRO Design |  | Kevin Spencer | SRO Design | Addition of REP-003A | As part of the Tranche 1 Transition Design and following approval from DAG a new report has been included within ECS Reports, MHHS-REP-003A. The intention is to retain the existing data flows in transition for the non-migrated MPANs and send the new DIP Flows or DTN flows for the migrated MPAN. This is due to the change in the CCCids which have different characteristics in the new world. The ELEX-REP-003A has been developed such that the CCC totals across migrated and non-migrated MPANS can be presented. Suppliers with MPANs in both Legacy and MHHS can expect: D0296 – just legacy data – as now, pipe delimited dataflow received via the DTN REP-D0296 – just MHHS data – still a pipe delimited dataflow received via the DTN – will have a new Dxxxx identifier REP-003 – just MHHS data – a JSON message received via the DIP REP-003a – both legacy and MHHS data – a JSON message received via the DIP |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Inclusion of MHHS-REP-003A to the ECS reports. Swagger has been updated to align with ECS reports catalogue with new reports interface REP-003a and associated common block, custom block and data catalogue items as per reports catalogue. | Reporting correction | Supporting Docs | ECS Reports Swagger REP003A version 001 | MHHSP - ERI011B - ECS Reports - External Swagger
MHHS-DIN-685 | BK |  | 2023-10-04 | RECCo |  | Sarah Jones | Central Body | Data Item Names and Descriptions | As part of the interface tranche of MHHS code drafting, RECCo has reviewed the information contained within the MHHS Interface Catalogue (DES138) and the ECS Reporting Catalogue (ERI011B) and identified a number of areas where changes to the data item names and descriptions should be progressed in order that these better align to existing code terminology and data item descriptions. We have identified five areas where changes should be made. 1) In the MHHS data catalogue, a number of discrepancies have been identified where the data item name or description is slightly different to the Energy Market Data Specification. In response to this we are either proposing to: a. amend the existing Energy Market Data Specification data item name and / or description via the MHHS code drafting work, or b. change to the data item name and / description in the MHHS data catalogue. 2) We have identified MHHS data items with the same name as existing data items, but a different data format. In particular, data items used to define effective from dates have been established for MHHS as a high resolution datetime data type. To avoid ambiguity / confusion for users, we are proposing to amend the data item description for MHHS date related data items to reflect that they are recording a data and time. 3) The data item used to link to CSS registration activity has been incorrectly referenced as the CSS Registration Request Id. This should be amended to the CSS Registration Id (DI90043) to avoid confusion with the CSS Registration Request Id which is a separate data item (DI90050). 4) The data item (MHHS DI-048) used to identify the meter manufacturer has been established with a different name and description from the existing data item (J0410). This should be amended to the Manufacturers Make and Type to avoid confusion. (Alternatively, if this is expected to be an entirely new data item, then the reference to J0410 should be removed and clarity provided on what data should be used to populate the field). 5) Correct minor typographical errors within the data item names and / or descriptions. | CR024 | Assessment Complete / Implementation Deferred | No |  | Change Request | All Participants |  | Post Go-live Release |  |  | Post Go-live Release |  | 1) In the MHHS data catalogue, a number of discrepancies have been identified where the data item name or description is slightly different to the Energy Market Data Specification. In response to this we are either proposing to: a. amend the existing Energy Market Data Specification data item name and / or description via the MHHS code drafting work, or b. change to the data item name and / description in the MHHS data catalogue. 2) We have identified MHHS data items with the same name as existing data items, but a different data format. In particular, data items used to define effective from dates have been established for MHHS as a high resolution datetime data type. To avoid ambiguity / confusion for users, we are proposing to amend the data item description for MHHS date related data items to reflect that they are recording a data and time. 3) The data item used to link to CSS registration activity has been incorrectly referenced as the CSS Registration Request Id. This should be amended to the CSS Registration Id (DI90043) to avoid confusion with the CSS Registration Request Id which is a separate data item (DI90050). Fixed under DIN-864 4) The data item (MHHS DI-048) used to identify the meter manufacturer has been established with a different name and description from the existing data item (J0410). This should be amended to the Manufacturers Make and Type to avoid confusion. (Alternatively, if this is expected to be an entirely new data item, then the reference to J0410 should be removed and clarity provided on what data should be used to populate the field). Fixed under DIN-864 5) Correct minor typographical errors within the data item names and / or descriptions. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger ECS Reports
MHHS-DIN-686 | BK |  | 2023-10-04 | RECCo |  | Sarah Jones | Central Body | DIP Interface Name Changes | As part of the interface tranche of MHHS code drafting, RECCo has reviewed the information contained within the MHHS Interface Catalogue (DES138) and identified a number of areas where changes to the DIP interface names should be progressed in order that these better align to enduring code terminology. In order to translate the MHHS interface catalogue (in the DES138) into the Energy Market Data Specification, RECCo is seeking to align MHHS interface names to enduring code terminology to avoid future inconsistencies. To meet this aim, we have identified four areas where changes should be made. 1) Removal of references to Metering Service within the interface name. Existing terminology will be retained e.g. MEM in the REC and MOA in the BSC. 2) Replacement of references to Service Providers with Supplier Agents within the interface name, Existing terminology will be retained with Data Services and Metering Services defined as Supplier Agents in both the BSC and REC. 3) Replacement of references to Registration / Registration Service with SMRS. To differentiate from the CSS and ERDS, following agreement with BSCCo that DIP interfaces fall under the scope of the SMRS. 4) Replacement of references to CSS De-Registration with CSS Registration De-Activation to reflect REC code terminology. | CR025 | Assessment Complete / Implementation Deferred | No |  | Change Request | All Participants |  | Post Go-live Release |  |  | Post Go-live Release |  | 1) Removal of references to Metering Service within the interface name. Existing terminology will be retained e.g. MEM in the REC and MOA in the BSC. 2) Replacement of references to Service Providers with Supplier Agents within the interface name, Existing terminology will be retained with Data Services and Metering Services defined as Supplier Agents in both the BSC and REC. 3) Replacement of references to Registration / Registration Service with SMRS. To differentiate from the CSS and ERDS, following agreement with BSCCo that DIP interfaces fall under the scope of the SMRS. 4) Replacement of references to CSS De-Registration with CSS Registration De-Activation to reflect REC code terminology. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-687 | ZH |  | 2023-10-04 | SI Design |  | Zakir Hussain | SI Design | BP003 updates are missing on BPD003 | For DIN-608 changes there were new steps added to the diagram, these have not been covered in the relevant BPD doc. This includes the new steps being referenced, descriptions, flows etc. |  | Assessment Complete / Implementation Deferred | No |  | Error/Correction | N/A |  | Post Go-live Release | #REF! |  | Post Go-live Release | #REF! | Add missing BP003 updates to BPD003 | Process Model correction | Supporting Docs | Business Process Description | BPD003
MHHS-DIN-688 | ZH |  | 2023-10-04 | SI Design |  | Zakir Hussain | SI Design | BP010E updates are not included in BPD10 | BP10E has not been included in the relevant BPD10 doc. |  | Assessment Complete / Implementation Deferred | No |  | Error/Correction | N/A |  | Post Go-live Release | #REF! |  | Post Go-live Release | #REF! | Add BP010E updates to BPD010 | Process Model correction | Supporting Docs | Business Process Description | BPD010
MHHS-DIN-689 | RG |  | 2023-10-05 | SRO Design |  | Rob Golding | SRO Design | Minor updates to DES138/Swagger for Sims& Ems audit | Minor differences between DES138 & swagger from sims & ems audit |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Incorporate differences between DES138 & swagger from sims & ems audit | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-690 | SC |  | 2023-10-09 | SRO Design |  | Sean Cooper | SRO Design | IF Optionality Matrix - MDR | Updated MDR IF Optionality Matrix to reflect correct values per current CR23 Design. Existing Values were not correct |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Updated MDR IF Optionality Matrix to reflect correct values per current CR23 Design. Existing Values were not correct for MDS | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-691 | SC |  | 2023-10-06 | SRO Design |  | Sean Cooper | SRO Design | DI-138 / DI-140 Customer Direct Contract Holder(s) | DI-138 / DI-140 Customer Direct Contract Holder(s) - Changed to Data Type DT006N in DES138 to correctly align with Swagger |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | DI-138 / DI-140 Customer Direct Contract Holder(s) - Changed to Data Type DT006N in DES138 to correctly align with Swagger | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-692 | SC |  | 2023-10-06 | SRO Design |  | Sean Cooper | SRO Design | DI-161 Settlement Run Number | DI-161 Settlement Run Number - made mandatory in IF-013 to correctly align with Swagger |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | DI-161 Settlement Run Number - made mandatory in IF-013 to correctly align with Swagger | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-693 | SC |  | 2023-10-06 | SRO Design |  | Sean Cooper | SRO Design | DI838 Supplier Nominated Consent | DI838 Supplier Nominated Consent - DES138 Updated to show as Nullable (Swagger already aligned) |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | DI838 Supplier Nominated Consent - DES138 Updated to show as Nullable (Swagger already aligned) | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-694 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | Update IF-007-EnergisationStatusChange event code | Update event code [EnergisationStatusFailure] to [EnergisationStatusChange] for IF-007-EnergisationStatusChange |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Update event code [EnergisationStatusFailure] to [EnergisationStatusChange] for IF-007-EnergisationStatusChange | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-695 | SC |  | 2023-10-06 | SRO Design |  | Sean Cooper | SRO Design | IF Optionality Grid - LDSO | LDSO IF Optionality - PUB-009 Corrected from NonApplicable to Optional = YES PUB-013 Corrected from NonApplicable to Optional = YES PUB-026 SSCProfileClass Corrected from N/A to Optional = YES PUB-040 Corrected from N/A to Optional = YES REGS: PUB019 Related MPAN Events corrected from N/A to Optional = No |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | LDSO IF Optionality - PUB-009 Corrected from NonApplicable to Optional = YES PUB-013 Corrected from NonApplicable to Optional = YES PUB-026 SSCProfileClass Corrected from N/A to Optional = YES PUB-040 Corrected from N/A to Optional = YES REGS: PUB019 Related MPAN Events corrected from N/A to Optional = No | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-696 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | IF-018 mandatory blocks for Energy Direction & NUM Indicatory | Add B023 is required for IF-018-EnergyDirection and IF-018-MUMIndicator |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Add B023 in IF-018-EnergyDirection and IF-018-MUMIndicator | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-697 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | Add required fields to IF-023 | Add required field to custom block in IF-023 |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Add required field to custom block in IF-023 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-698 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | Add required field to IF-040 | Add B059 to required field in IF-040 |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Add B059 to required field in IF-040 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-699 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | IF-036 DSAppActive optional B068 block | Remove B068 from required fields for IF-036 DSAppActive |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Remove B068 from required fields for IF-036 DSAppActive | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-700 | RG |  | 2023-10-09 | SRO Design |  | Rob Golding | SRO Design | Recipient ID specified twice in replay/requeue API | Remove recipient id from request body of API call as already specified on path |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Remove recipient id from request body (in the MessageRequest object) of API call as already specified on path. This applies to replay and requeue API endpoints. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-701 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarification on population of IF-036 | Clarification on population of IF-036 participant ID's |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Provided clarification on IF-036 Interface notes on how B005, B016 and B017 are populated by Registration Service | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-702 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarification on use of calendar days for validation rules in IF-025 and IF-034 | Update validation rules to clarify that days refer to calendar days in IF-025 and IF-034 |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | IF-025 and IF-034 validation rules updated to clarify using calendar days | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-703 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarify that B032 is only sent where available in Registration Service | Clarify that B032 is only sent where available in Registration Service in IF-001, IF-002, IF-033 and IF-036 |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Updated B032 to show as sent where available in Registration Service in IF-001, IF-002, IF-033 and IF-036 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-704 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Updated DI-135 and DI-136 to be set to Mandatory in IF-025/IF-026 | Update DI-135 and DI-136 to be set to Mandatory in IF-025/IF-026 and to be non-nullable, so that a date is always provided for SMSO and IHD even where setting the value to null. |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Updated DI-135 and DI-136 to be set to Mandatory in IF-025/IF-026 and to be non-nullable | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-705 | MF | DI-214 | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarify that sending of [IMS-SendMTD] event code on IF-035 should also apply in the case of SEG | Clarified that SEG scenario applies for requirement MHHS-BR-RS-019 to send [IMS-SendMTD] event code on IF-035 |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Added that SEG scenario applies for requirement MHHS-BR-RS-019 to send [IMS-SendMTD] event code on IF-035 in BRS003 | Requirement correction | Supporting Docs | Business Requirements | BRS003
MHHS-DIN-706 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Remove Unmetered check for de-linking Linked Export MPANs (IF-019) | Clarified that Unmetered check will not apply for [LinkedImportExportRemove] event in IF-019 |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Updated validation rules so that Unmetered check will not apply for [LinkedImportExportRemove] event in IF-019. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-707 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarification on Primary routing for IF-033 | Updated IF-033 to show primary routing is to XMSP and XDSP |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Updated IF-033 to show primary routing is to XMSP and XDSP | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-708 | RG |  | 2023-10-09 | SRO Design |  | Rob Golding | SRO Design | IF-004 B093 block is mandatory | Audit of swagger IF-004 B093 block is mandatory |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Update IF-004 B093 block to mandatory | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-709 | RG |  | 2023-10-09 | SRO Design |  | Rob Golding | SRO Design | IF-021 and IF-014 custom block differences | IF-021/14 have different structure, ideally they should be the same - the B045 block does not need to be an array |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Aligned IF-014 to IF-021 so that multiple B045 blocks are not allowed | Data interface correction | Supporting Docs | Interfaces IF-014 version 010 | DES138, Swagger 1.6
MHHS-DIN-710 | RG |  | 2023-10-09 | SRO Design |  | Rob Golding | SRO Design | IF-016 requires update to include IF-013 variant | IF-016 definition needs to include replayed IF-013 data. |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | At present in DES-138 only the IF-021/14 variants are described in the IF-016 data, this needs to be extended to include the IF-013 variant. This change has been to be reflected in the Swagger. Added validation rules and response codes to IF-015 to be included in IF-016. | Data interface correction | Supporting Docs | Interfaces IF-015 version 010, IF-016 version 010 | DES138, Swagger 1.6
MHHS-DIN-711 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | IF-035 Obsfucation/routing contradiction | IF035 – MDS & LDSO are mentioned in the obfuscation column, however, there is no routing rule for these roles |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Removed LDSO and MDS from obsfuscation rules as LDSO/MDS do not receive IF-035 | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-712 | MF | DI-181 | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | De-appointment and re-appointment date order | Set de-appointment and re-appointment dates to D and D+1 for requirements RS-128.7 and RS-128.8 for Data Service appointments to align with DIN-383 (Metering Service appointments) |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Discussed with SCS and agreed to update Registration Service requirements to De-appoint on D (MHHS-BR-RS-128.7) and appoint on D+1 (MHHS-BR-RS-128.8) as part of auto-alignment process | Requirement correction | Supporting Docs | Business Requirements | BRS003
MHHS-DIN-713 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | Rel 1.2.1 S1 updates in swagger | SenderRoleId & SenderTimestamp updated in required section in S1 object to fix problem introduced in v1.2 |  | Implemented | [5 empty] | Interim Release 2.1 | #REF! |  | Interim Release 2.1 | #REF! | Update sentTimestamp to senderTimestamp, senderRole to senderRoleID in S1 block | Data interface correction | Supporting Docs | Various documents | DES-138 Interface Catalogue Swagger 1.2.1
MHHS-DIN-714 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | Rel 1.2.1. B033 updates in swagger | Remove meteringPointPostcode from required section of B033 object |  | Implemented | [5 empty] | Interim Release 2.1 | #REF! |  | Interim Release 2.1 | #REF! | Update B033 remove meteringPointPostCode from B033 | Data interface correction | Supporting Docs | Various documents | DES-138 Interface Catalogue Swagger 1.2.1
MHHS-DIN-715 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | Rel 1.2.1. D091 update | DI-091 update maximum: 1->9, minimum 1->0 |  | Implemented | [5 empty] | Interim Release 2.1 | #REF! |  | Interim Release 2.1 | #REF! | Update DI-091-Number-Of-Displayed-Digits to maximum 9 and minimum 0 in the Swagger. Including updates to 01-Data Catalogue, IF-002, IF-005, IF-006, IF-033 in the Interface Catalogue to align with Swagger. | Data interface correction | Supporting Docs | Various documents | DES-138 Interface Catalogue Swagger 1.2.1
MHHS-DIN-716 | ME |  | 2023-10-10 | Elexon | 13809 | Rashmi Radhakrishnan | Central Body | Update to ISD entity 23 | Additional text provided within the Settlement Period Duration (Description) field requires removal as the correct text has been added |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Desription within Settlement Period Duration (Description) has been updated. The reference for a Settlement period, unique within Settlement Date. Periods ID s are assigned sequentially to each period in local time day The duration of a Settlement Period in minutes | Design Ambiguous | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-717 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | LSS needs to be removed from the obsfucation column in DES138 - IF001 | LSS does not recieve IF-001 and therefore should not referenced in the obsfucation column |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Removed LSS from obsfucation rules in IF-001 as only issued to MDS which is already covered by obsfucation | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-718 | ME |  | 2023-10-11 | Elexon | 14165 | Derek Weavering | SRO Design | MHHS-Rep-D0296 alignment with Ddddd Supplier BM Report | A review of the DAG approved MHHS-DEL1613 DES-196 D-Flow and Interface Mapping Supplementary Documents has identified the following: The current Supplier BM Unit Report (D0296) considers all the GSPs that the supplier operates in a single file). However the Ddddd specs in the ECS catalogue and D flow documentation suggest a single file for each supplier’s GSP. We are building ( within Helix) using the current approach where all GSPs appear in the same file. Please can this be raised with the team to ensure the specs also reflect the same |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | MHHS-REP-D0296 has been updated to align with the Ddddd Supplier BM Report. The following link: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx has also been included to the following reports (D0081, D0266, D0276 and D0296) to direct participants to what should be used as the Master version of each report as defined in DTC format. | Reporting correction | Supporting Docs | ERI011B ECS Reports-External | ERI011B ECS Reports-External
MHHS-DIN-719 | MF |  | 2023-10-11 | Utiliteam |  | Mike Fensome | SRO Design | Update to DI-103 Configurable Register Id to min length of 1, max length of 2 | Allow Configurable Register ID's (DI-103) to be provided with min length of 1 and max length of 2 in both swagger and DES138 so that, for example, either 1 or 01 are accepted. |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Updated Data Catalogue for DI-103 (Configurable Register ID) to Min length of 1 (from 2) and updated Swagger accordingly. Added REGEX to Swagger. Regex takes the form ^\d{1,2}$ | Data interface correction | Supporting Docs | Interfaces | DES138, Swagger
MHHS-DIN-720 | MF |  | 2023-10-11 | Utiliteam |  | Mike Fensome | SRO Design | Update to DI-122 Profile Class to min length of 1, max length of 2 | Allow Profile Class (DI-122) to be provided with min length of 1 and max length of 2 in both swagger and DES138 so that, for example, either 1 or 01 are accepted. |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Updated Data Catalogue for DI-122 (Profile Class) to Min length of 1 (from 2) and updated Swagger accordingly. Added REGEX to Swagger. Regex takes the form ^\d{1,2}$ | Data interface correction | Supporting Docs | Interfaces | DES138, Swagger
MHHS-DIN-721 | JW |  | 2023-10-11 | Migration Design |  | John Wiggins | Programme | Control needed with MPID's associated to a metering role | For a metering company, only one limited company can ever own an MPID related to one of the three metering roles. Elexon need a control to say that an MPID associated to a metering role can never be owned by more than one company |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Updated ISD Entity 45 with the following comment "Where an MPID is related to the following Market Roles: Meter Operator, Advanced MOA or Smart MOA, the MPID and Market Role combinations must always be assigned to the same Company ID." | Missing/incorrect validation rule | Supporting Docs | ISD Entities | ISD Entities
MHHS-DIN-722 | RG |  | 2023-10-12 | SRO |  | Rob Golding | SRO Design | Remove Recipient Roles from A0.always object. | Remove Recipient Roles from A0.always object as roles are always resolved to DIP Ids |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Update Swagger to remove Recipient Roles from A0.always | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-723 | RG |  | 2023-10-12 | SRO |  | Rob Golding | SRO Design | OffPeakDeclarationProportion spelt on B097 spelt incorrect | OffPeakDeclarationProportion spelt 'OffPeakDeclatationProportion' on B097. |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Updated spelling in Swagger so that 'OffPeakDeclarationProportion spelt 'OffPeakDeclatationProportion' on B097. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-724 | RG |  | 2023-10-12 | SRO |  | Rob Golding | SRO Design | DT-000 Interface ID to include REP-002A & IF-004 | DT-000 Interface ID to include REP-002B & IF-004 as they are missing |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Add REP-002B & IF-004 to the enumerated list for DT-000 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-725 | RG |  | 2023-10-12 | SRO |  | Rob Golding | SRO Design | Add individual interface endpoints into the swagger | Add individual interface endpoints into the swagger as this would improve schema validation and better error messaging |  | Closed | [6 empty] | #REF! |  |  | #REF! | Following a review with the DIP Provider, these changes will not be made in Swagger and error handling will remain as per the IR5 design. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.7
MHHS-DIN-726 | ME |  | 2023-10-13 | SRO | 14120 | Miriam Ellis | SRO Design | DataType/Example errors in ECS reports data catalogue | A number of errors have been highlighted by Elexon following a review of the updated ECS data catalogue V5.4. There are errors that require an update |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Updates to data types and examples for a number of data items have been made within the data catalogue as well as where the data items appear in each of the documented reports | Reporting correction | Supporting Docs | ER1011B ECS Reports External ER1011A ECS Reports Internal | ER1011B ECS Reports External ER1011A ECS Reports Internal
MHHS-DIN-727 | MF |  | 2023-10-13 | SRO |  | Mike Fensome | SRO Design | Add new routing path for IF-041 | Added routing to give Data Service ability to send on-site read to Supplier |  | Implemented | [5 empty] | Interim Release 5.1 | #REF! |  | Interim Release 5.1 | #REF! | Added [ReadingOnSite] to routing table for Data Service in IF-041 |  |  |  | DES138
MHHS-DIN-728 | ME |  | 2023-10-17 | SJW | 13832 | Sarah Jones | Consultancy | DES138 and ECS Reports misalignment | As part of our work developing the interface code drafting, we have noticed that the S0 Block in the interfaces defined in the DES138 differ from those in the ECS Reporting Catalogue. Specifically, the DES138 includes Schema Version in the S0 block and the ECS Reporting Catalogue does not. Our expectation was that blocks would be identical across the various interfaces. |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | All new MHHS ECS reports now includes Schema Version in the S0 blocks. | Reporting correction | Supporting Docs | ERBI011B ECS Reports - External | ERBI011B ECS Reports - External
MHHS-DIN-729 | SW |  | 2023-10-17 | SI Design |  | Steve Weston | SI Design | DI-838 to include null on the enum values | DI-838 in Swagger is mandatory nullable and this is an enumerated list so needs to include null in the enumeration to ensure this aligns to DES_138. |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Updated Swagger DI-838 to ensure that null is a value in the enumerated list given this is a mandatory nullable field so that this now aligns to DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.6
MHHS-DIN-730 | ME |  | 2023-10-17 | Elexon | 13443 | Rashmi Radhakrishnan | Central Body | Update to Company name in Entity 1 | Within Entity 1 of ISD Entities - Market Participant ID there is a character limit of 100 for Registered Company Name but this is not sufficient and require this to be updated to allow up to 160 characters to align with company house. |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | The character limit for Registered company name within Entity 1 of ISD Entities document has been increased to 160 | Design Ambiguous | Supporting Docs | ISD Entities | ISD Entities
MHHS-DIN-731 | RG |  | 2023-10-18 | Elexon |  | Nigel Rees | Central Body | Swagger does not resolve ECS reports | Since the ECS reports are now compressed in DIP messages the ECS report strcutre is not resolved in the swagger. |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Added a field to each ECS payload that defines the structure of the corresponding report. This will be an optional item, hence not populated, however it will present the resolved structure of the report. | Design Ambiguous | Supporting Docs | Interfaces All REPs are now version 007 | Swagger 1.6, ER1011B ECS Reports External
MHHS-DIN-732 | RG |  | 2023-10-19 | SRO |  | Rob Golding | SRO | Routing update on IF-026 not updated | DIN-415 was meant to correct the routing on IF-026 - its still incorrect. The routing for event code [SSCandProfileClass] points to EES, LLS- this should be LSS. The header also needs to align - it currently states Central Settlements (MDS), it should be Central Settlements (LSS) |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Typo corrected LLS changed to LSS | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-733 | SC |  | 2023-10-19 | RECCO |  | Jonnny Moore | Recco | Update IF-026 Routing for Change of Consent | EES does not hold consent information - changed routing to remove EES as a receipient of Consent Info |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | EES does not hold consent information - changed routing to remove EES as a receipient of Consent Info in IF-026 | Design Ambiguous | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-734 | SC |  | 2023-10-19 | RECCO |  | Jonnny Moore | Recco | Update IF-018 Routing for Dom Premise Indicator | EES does not hold consent information - changed routing to remove EES as a receipient of DPI Info |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | EES gets DPI information from CSS - changed routing to remove EES as a receipient of DPI Info in IF-018 | Design Ambiguous | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-735 | MF |  | 2023-10-19 | Drax |  | Georgina Mahoney | Drax | Remove referene to BP007 as input into BP002 and BP003 | Disconnections is not an input into Change of Service Provider, BP007 should be removed from the entry processes. |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Removed BP007 as an entry process to BP002 and BP003. De-appointment of Service Providers is covered in BP007. | Process Model correction | Supporting Docs | Process model correction | BP002 BP003
MHHS-DIN-736 | ZH |  | 2023-10-19 | SI Design |  | Zakir Hussain | SI Design | Removing step 36 from BP003 | Step 36 was included initially as part of an earlier DIN but is no longer relevant and therefore needs replacing. |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Remove Step 36 and flow from BP003, including any reference to the step in the latest BPD3 Doc | Process Model correction | Supporting Docs | Process model correction | BP003 and BPD003
MHHS-DIN-737 | RS |  | 2023-10-19 | ESG |  | Patricia Parker | Software Provider | Custom Block: B022, Field: Metering Point Postcode min length in Swagger | Interface Catalogue specifies no min length, but min length of 6 specified in Swagger. Min length should be 5 for areas such as Liverpool |  | Closed
MHHS-DIN-738 | SC |  | 2023-10-19 | St Clements |  | Sean | SRO Design | Update Schema Version Data Item DI-992 Length | Interfaces across DES-138 need updating to show Schema Version DI-992 as String 10 rather than string 3 |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | DES-138 updated in individual interface to show Schema Version DI-992 as String 10 rather than string 3 | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-739 | SC |  | 2023-10-19 | St Clements |  | Sean | SRO Design | Validation of Supplier DIP ID / MPID for IF-035 [SDS-MDRUpdate] | Add validation in IF-034 to ensure that Supplier DIPID and MPID provided matches that of the current supplier held in the registration service - return new Error of REG1084 if this is not the case. |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | Add validation in IF-034 to ensure that Supplier DIPID and MPID provided matches that of the current supplier held in the registration service - return new Error of REG1084 if this is not the case. | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-740 | SC |  | 2023-10-19 | St Clements |  | Sean | SRO Design | IF-018 Routing | DS added as a recipient of IF-018 [DCCEnrolment] |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | DS (XDSC) added as a recipient of IF-018 [DCCEnrolment] in the Secondary Routing | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-741 | MF |  | 2023-10-19 | St Clements |  | Mike | SRO Design | Clarification on end dating MDR functionality | Add clarification that the requirement to end date the MDR is fulfilled using existing CSS0200 functionality |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | MHHS-BR-RS-078.1 notes updated to clarify that this requirement is fulfilled using existing CSS0200 functionality | Requirement correction | Registration | Business Requirements | BRS003 Registration Service requirements
MHHS-DIN-742 | KH |  | 2023-10-23 | CGI | 13709 | Dave Webster | Software Provider | ADS and SDS Estimation Statements | As a result of DIN-589 which was to align the METH002 (ADS) with METH001 (SDS) method statements, the two documents are still misaligned. “Method 0: ADS processes Supplier provided ‘Agreed’ or ‘Override’ Readings” is the equivalent of “Method 0: SDS processes Supplier provided ‘Agreed’ or ‘Override’ Readings and Consumption Amendments”. However, SDS uses flag E0, but ADS uses flag E8 (from the previous numbering of this method and now not intuitive to determine from the flag which method has been used for estimation). Similar to (1), Method 8 (ADS) = Method 8 (SDS), but would be clearer if flag E9 (ADS) matched the method number and flag in SDS, E8. Similar to (1), Method 9 (ADS) = Method 9 (SDS), but would be clearer if flag E10 (ADS) matched the method number and flag in SDS, E9. “3.13 Where notified by a Supplier that a site is Long Term Vacant (LTV) the ADS shall use Method 12.” LTV check is now Method 11. “3.16 The below estimation methods are based on those used in the Smart Data Service (SDS) Method Statement. For that reason, methods 0, 1, 6, 11 and 13 have been omitted as they are only applicable to Smart meters” – this statement is no longer correct as methods 0 and 11 are present |  | Implemented | No |  | Design misaligned | TBC |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Updates completed in method statement 002 | Requirement correction | Supporting Docs | Method Statement | ADS Method Statement
MHHS-DIN-743 | MF |  | 2023-10-24 | ENWL |  | Paul Band | LDSO | IF-036 Optionality Update | IF-036 changed to optional for LDSO's in line with CR-029 within the Optionality Matrix |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | IF-036 changed to optional for LDSO's inline with CR-029 within the within the Optionality Matrix (name of worksheet in DES-138: 04_IF_OptOut_Matrix) | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-744 | MF |  | 2023-10-24 | RECCO |  | Sarah Jones | Central Body | IF-036/037 Routing to MDS | Show that MDS receive IF-036 and IF-037 on BP003 to align with Interface Catalogue |  | Implemented | No |  | Design misaligned | N/A |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Added note to BP003 to highlight that MDS will also receive IF-036 and IF-037. Similar note added to the Migration version BPM003 again just to reference the IF-003 being copied to MDS. Added MDS to IF-003 DSDeAppRM event in DES138 | Process Model correction | Supporting Docs | Process model correction | BP003 BPM003 DES138
MHHS-DIN-745 | SW |  | 2023-10-27 | SI Design | 16780 | Madison Layton | Central Body | DI-120 Additional Information should be mandatory nullable | DI-120 was made non nullable in IR5.1 in Swagger. This needs to be corrected so that DI-120 is used in multiple places and needs to be mandatory nullable. |  | Implemented | No |  | Design misaligned | DIP Users, DIP |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Make DI-120 Additional Information Mandatory nullable in Swagger to align with DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-746 | RG |  | 2023-10-27 | IMserv |  | Liam Lowey | Software Provider | Swagger error - Response body doesn't match Sims& Ems implementation | Schema Bug - Different interpretation of the optional field DIPConnectionProviderID: The DIP Sim requires the property field is present, but allows for a NULL value if we are not using a connection provider. The interface spec, does not allow for a NULL value, but instead does make the field optional. So, it appears that the DipSim requires the property, even if NULL. The schema (v1.2.1) does NOT require the property but will NOT permit NULL. Please can you clarify the intention? This appears to be a blocker/breaking difference that means we will not be able to test the same code base against both DIP Sim and DIP. |  | Closed | Yes | TBC | Error/Correction | DIP Users, DIP |  |  | #REF! |  |  | #REF! | IF we are going to release a 2.2 release then this should be fixed, this has been fixed on the main code thread. This has not been fixed in rel 1.5, hence not included in the 2.2 release. The design perpetuates as described and the DIPSIM needs to align. | Data interface correction | Supporting Docs | Interfaces | Swagger |  |  | Interim Release 2.2
MHHS-DIN-747 | SB |  | 2023-10-27 | OVO | 16574 | Brian Miller | Supplier | CR028 amendment | Routing of the PUB-001 requires amending to reflect the removal of EES as recipient as per CR028 also the Change of Supply documentation redlining requires amending to reflect this |  | Closed | [6 empty] | #REF! |  |  | #REF! | Notify that this change already exists
MHHS-DIN-748 | RG |  | 2023-10-27 | IMserv |  | Liam Lowey | Software Provider | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength should not have a maxLength validation attribute as it is an integer type. This means the schema itself does not validate against the rules for these types of schemas. |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | DI-487-Total-Number-Energised-MPANs maxLength attribute should be length as it is an integer type. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.6
MHHS-DIN-749 | RG |  | 2023-10-27 | IMserv |  | Liam Lowey | Software Provider | SchemaBug - DipMessage.payload is not a required property | SchemaBug - DipMessage.payload is not a required property, therefore different property names will pass validation without being checked - this means if you spell it "Payload" with a capital P instead it will effectively skip validation resulting in a false positive. |  | Implemented | [5 empty] | Interim Release 6 | #REF! |  | Interim Release 6 | #REF! | ‘payload’ needs to be a required attribute for the DIPMessage object. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.6
MHHS-DIN-750 | RS |  | 2023-10-27 | REC |  | Sarah Jones | Central Body | IF-019/020 Interface notes and REG1066 validation | REG1068 was removed as part of IR4, however the neither related interface note in IF-019 and If-020 or REG1068 in the List of Registration error codes in the introduction tab have been updated. Also REG1066 should be removed for consistency. |  | Implemented | No |  | Design ambiguous | N/A |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Remove statement 'where there are multiple Related Import MPANs, the Export MPAN will only be linked with the Primary MPAN in the relationship' from IF-019 and IF-020 Interface notes Remove REG1066 validation rule from IF-019 Remove REG1066 and REG1068 from the List of Registration error codes in the introduction tab of DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-751 | RS |  | 2023-10-27 | REC |  | Sarah Jones | Central Body | IF-019/020 Interface notes | Interface note for IF-019 and IF-020 states that for the avoidance of doubt, in all cases it is the LDSO, that must determine if the request to create/modify an MPAN Relationship is valid or not. The ultimate decision to allow the linking or de-linking of a MPAN within a relationship rests with the LDSO. This is correct for linked mpans but not related. Interface note to be updates to be LDSO for linked and supplier for related |  | Implemented | No |  | Design ambiguous | LDSO (SCS) |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Update Interface note for IF-19 and IF-20 to state that for the avoidance of doubt, for Import/Export linkages it is the LDSO, that must determine if the request to create/modify an MPAN Relationship is valid or not. The ultimate decision to allow the linking or de-linking of a MPAN within a relationship rests with the LDSO. Related Metering Point linkages are maintained by the Supplier | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-752 | RS |  | 2023-10-27 |  |  | Sarah Jones | Central Body | Change of Data Service - Forward migration for Import/Export | Yellow note box on DEL964 BPM003 Forward migration document states Export and Import MPANs will be migrated independently, this process is only relevant to Related MPANs. In addition post migration for Export and Import MPANs, the Registration Service will not automatically appoint both the MPANs to the same MS/DS but it will notify of exceptions. This should read PRE-Migration not Post migrations as per requirement MHHS-Migration-Mis-RS-022 |  | Implemented | No |  | Design ambiguous | N/A |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Amend wording to 'In addition Pre migration for Export and Import MPANs, the Registration Service will not automatically appoint both the MPANs to the same MS/DS but it will notify of exceptions'.in DEL964 and DEL963 | Process Model correction | Supporting Docs | Process model correction | DEL964 BPM003 DEL963 BPM002
MHHS-DIN-753 | SB |  | 2023-10-30 | CGI |  | Dave Webster | Software Provider | Reconciliation for smart Meter Advance Reconciliation in METH001 | In METH001, v5.2, section 3.12 it states the MAR should be carried out "at a minimum of once a month". Section 3.15 states "The maximum levels are [±0.7%] where the check is carried out at least on a weekly basis for months data or [±5%] where the check is carried out on a daily basis using daily data." These are contradictory. What is the minimum frequency this check can be carried out, is it weekly or is monthly adequate? If monthly is acceptable, should the tolerance level be [±0.7%] as per a weekly check? |  | Assessment Complete / Implementation Deferred | No |  | Design ambiguous | N/A |  | Post Go-live Release |  |  | Post Go-live Release |  | Propose the statement in METH001 be updated to the following: Section 3.15 states "The maximum levels are [±0.7%] where the check is carried out at least on a weekly or monthly basis or [±5%] where the check is carried out on a daily basis using daily data." | Method statement correction | Supporting Docs | Method Statement | METH001
MHHS-DIN-754 | PP |  | 2023-10-30 | Helix |  | Sedef Kiris | Central Body | Alignment of REP-005 and ISD entity | Issue statement: In TOM, Line Loss Factor (LLF) process is a new streamlined process identified with a hybrid solution combining the benefits of Salesforce and Azure to process LLF Data. However there are some ambiguity within the Design Artefacts around how ISD should be publishing LLF Data. In the MHHS BRS10 document, the requirement from MHHS is to publish the full ISD dataset on the BSC Website in a manner that is available to the public access. The data will be available in 3 separate grouping 1. LLF data 2. Master Settlement timetable 3. ISD data including UMS data However, the MHHS ERI011B ECS report document states that Line Loss Factors' specifics for Market Participants will be provided by Elexon as part of the ISD publication in the name of ELEX-REP-005 The LLF data referenced in MHHS BRS10 and ELEX REP 005, as mentioned in MHHS ERI011B, are identical but bear different names leading to confusion and ambiguity. Helix WP3 has identified this ambiguity and would like MHHS to make relevant Design artefact changes to bring more clarity. |  | Implemented | No |  | Error/Correction | All Participants |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | This was raised via the change board where a decision was made to push this through as a DIN REP-005 and the LLF data referenced in the design artifacts are essentially one and the same. Helix aims to meet their requirements by adhering to the specifications outlined in the Transition BRS010. To accomplish this, MHHS needs to take the following changes into consideration. The recommended solution from Helix and MHHSP is to align the Transition and End State Design Artefacts to reflect LLF Data is a deliverable of ISD and add two new ISD Entities to reflect this and remove REP-005 from the list of ECS Reports – impacts BRS010, BRS001 (Transition), ERI011B and EDI012. Remove the mention of ELEX REP 005 from MHHS ERI011B ECS report document To enable the ISD to release Line Loss Factor (LLF) data, the LLF data must be integrated into the MHHS EDI021 ISD Entity Specification document. (detailed below entity details) MHHS then align the Transition and End State Design Artefacts to reflect this change i.e All effected Design Artefacts (BRS010, ERI011B ECS report and EDI021 ISD Entity Specification ) to be updated. | Data interface correction | Supporting Docs | Various documents | BRS010, BRS001 (Transition), ERI011B, EDI012
MHHS-DIN-755 | SC |  | 2023-11-01 |  |  | Sean Cooper | SRO Design | Correction to IF-035 Routing Matrix | Previous DIN created a new group B99 for SDS-MDRUpdate Rejections - this new B099 group was not updated in the Routing Matrix. This has now been corrected. |  | Implemented | No |  | Design misaligned | LDSO (SCS) |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Previous DIN created a new group B99 for SDS-MDRUpdate Rejections - this new B099 group was not updated in the Routing Matrix. This has now been corrected. | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-756 | SC |  | 2023-11-01 |  |  | Sean Cooper | SRO Design | Addition of IF-003 [ReverseMigration] to BPM-001 | Migration Business Process Map BPM-001 updated to include previously missing issuing of IF-003 [ReverseMigration] event from REGS to MDS, LDSO, and EES. This is triggered off the back of COS completion notice (Secured Active) from CSS to REGS. Note this is required as a definitive reverse migration notification as IF-003 [DSApp] may not always be issued. This is not a change to the migration design - step had simply been ommited from BP map. |  | Implemented | No |  | Design ambiguous | N/A |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Migration Business Process Map BPM-001 updated to include previously missing issuing of IF-003 [ReverseMigNotification] event from REGS to MDS, LDSO, Supplier and EES. This is triggered off the back of COS completion notice (Secured Active) from CSS to REGS. Note this is required as a definative reverse migration notification as IF-003 [DSAppRM] may not always be issued. This is not a change to the migration design - step had simply been ommited from BP map. BPD-001 (Reverse Migration) updated accordingly | Process Model correction | Supporting Docs | Process model correction | BPM001 BPMD001
MHHS-DIN-757 | SC |  | 2023-11-01 |  |  | Sean Cooper |  | Add BP003A Link to BP003M Reverse Migration Map. Remove BP003A link from DEL963-BPM002 Forward migration | Added Missing link to show update to CSS/DCC when SDS is de-appointed on Reverse Migration. Remove the link to BP003A from DEL963-BPM002 as this is only triggered for a Change of Data Service |  | Implemented | No |  | Design gap | SDS |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | New process link to BP003A added to BPM003 for Smart meters at step 1008. Remove link to BP003A from DEL963-BPM002 | Process Model correction | Supporting Docs | Process model correction | BPM003 BPM002
MHHS-DIN-758 | SC |  | 2023-11-01 |  |  | Sean Cooper | SRO Design | 5 day check on MDR App Date in IF-034 | Per feedback from SCS, five day check on MDR Eff From Date (DI-841) changed to only apply to SDSMDRUpdate event and NOT normal/regular DS Appointment events. Thus removes clash between this check and 28 day leadtime on regular DS Apps |  | Implemented | No |  | Design gap | LDSO (SCS) |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Per feedback from SCS, five day check on MDR Eff From Date (DI-841) changed to only apply to SDSMDRUpdate event and NOT normal/regular DS Appointment events. Thus removes clash between this check and 28 day leadtime on regular DS Apps. New Rule added specifically for DSSAppSPResonse | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-759 | SC |  | 2023-11-01 |  |  | Sean Cooper | SRO Design | Changes to Proposed Consent logic | Proposed Consent (DI-838) Set to Mandatory, Updated allowable values in DI-838 and DI-017 to include N - No consent. Updated ISD M17 table to include meter group and added N value for all traditional meter combinations. |  | Implemented | No |  | Design ambiguous | LDSO (SCS) |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Proposed Consent (DI-838) Set to Mandatory, Updated allowable values in DI-838 and DI-017 to include N - No consent. Updated ISD M17 table to include meter group and added N value for all traditional meter combinations. | Data interface correction | Supporting Docs | Interfaces | DES138 ISD Entities
MHHS-DIN-760 | MF |  | 2023-11-01 |  |  | Mike Fensome | SRO Design | UMSDS routing | Updates to align Optionality Matrix and To Parties for UMSDS |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Updated IF-024 to remove UMSDS from To Parties. Updated Optionality Matrix to show IF-043 as N/A and IF-018 as Yes for events [DUOSTariffIDChg] and [DomPremInd] for UMSDS | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-761 | MH |  | 2023-11-03 |  | 16609 | Matt Hall |  | BP020 ver 5.1 redlined - REP D0354 | BP020 5.1 references the supplier receiving various VAS reports including REP-D0354, which isn't a VAS report at all, and isn't sent to suppliers, and REP-D0237 which should be REP-P0237 and is an internal report that doesn't go to suppliers |  | Assessment Complete / Implementation Deferred | No |  | Design ambiguous | Suppliers |  | Post Go-live Release |  |  | Post Go-live Release |  | Review reports contained in BP020 and correct | Process Model correction | Supporting Docs | Process Models | BP020
MHHS-DIN-762 | MH |  | 2023-11-03 |  |  | Matt Hall | SI Design | DEL961 IF-003 routing to MDS - Update Migration Document | DEL961 needs updating to reflect the clarifications made in DIN-756 that IF-003 should be routed to MDS on [ReverseMigration] and [DSApp] events, not [MSApp] |  | Implemented | No |  | Design ambiguous | N/A |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Section 8 of DES961 updated to remove LDSO and Elexon Central Systems receiving MS Deappointment in line with DES-138 | Process Model correction | Supporting Docs | Process model correction | DEL961 - Migration Design Document
MHHS-DIN-763 | RS |  | 2023-11-06 |  | 15975 | Sarah Jones | Central Body | Related Metering Points undergoing Migration | Change to the Registration Service Requirements introduced through IR3 (DIN423). proposed change to RS-146 to remove 'and Related MPANs': Registration must only carry out auto-alignment of Linked MPANs (Import/Export) and Related MPANs if all MPANs in the group have migrated to the MHHS operation. |  | Implemented | No |  | Design ambiguous | Suppliers |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Amend wording to RS-146 from Registration must only carry out auto-alignment of Linked MPANs (Import/Export) and Related MPANs if all MPANs in the group have migrated to the MHHS operation. to Registration must only carry out auto-alignment of Linked MPANs (Import/Export) if all MPANs in the group have migrated to the MHHS operation. | Requirement correction | Registration | Requirement correction | BRS003 - Registration Service Requirements
MHHS-DIN-764 | MF | DI-236 | 2023-11-06 | St Clements |  | Mike Fensome | SRO Design | Additional validation rule in IF-031 to ensure appointments are contiguos | Add new validation rules in IF-031 to ensure that if there is no Service Provider appointed, the Proposed Service Provider Appointment Date is equal to SSD or Previous Service Provider De-appointment Date + 1 |  | Implemented | No |  | Design gap | LDSO (SCS) |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Added two new validation rules in IF-031 to ensure that if there is no Data Service/ Metering Service currently appointed then the Proposed DS/ MS Appointment Date must equal SSD or Previous DS/MS De-appointment Date + 1. Error message of REG 1032 issued if the check fails. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-765 | SW |  | 2023-11-07 |  | 18247 | Steve Weston | SI Design | Inconsistencies in E2E001 JSON examples with Swagger | There are some minor / non-consequential inconsistencies and spelling mistakes in some of the examples provided in the E2E001 design, that do not align with Swagger that need to be corrected in the E2E001 design document |  | Closed | No |  | Design ambiguous | DIP Users | [6 empty] | No material change required to design documents | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 Architecture Document
MHHS-DIN-766 | ZH | DIN-464 | 2023-11-07 | SIMS |  | Kyle Abraham | Software Provider | Clarity required on values expected for /dip-channel/{id} for submitEvents on Swagger | The {id} in /dip-channel/{id} for submitEvents on Swagger should accept values that are the same as the enumeration in DI-000 to ensure consistency. At the moment, this is not clear in Swagger, so this needs to be updated to make this clearer. |  | Implemented | Yes |  | Design misaligned |  |  | Interim Release 2.2 |  |  | Interim Release 2.2 |  | Updates made to Swagger 1.2.2, so the correct enumerations / values are available to align with values in DI-000 to ensure consistency and avoid any ambiguity between interfaces and reports. Updated to remove PublicationConfig and RestConfig in favour of a single config WebhookConfig. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.2.2
MHHS-DIN-767 | SW | DIN-772 | 2023-11-13 | C&C | 19150 | Chris Lenihan | Software Provider | Swagger incorrect for IF-043 | For IF-043 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-043-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. |  | Implemented | No |  | Design misaligned | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Update IF-043 so that it uses the required property name is ‘CustomBlock’ but the actual name is ‘IF-043-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-768 | SW |  | 2023-11-13 |  | 19136 | John Edmonds-Bell | SI Design | Event Code inconsistency between Swagger and ECS Reports for REP-901 | On REP-901 report, the event code in the reports catalogue is defined [DUoS_EmbeddedLDSO_Agg_Inv_Data] and [DUoS_Supplier_Agg_Inv_Data] whereas on the Swagger Document it’s DUoSSupplierInvData. Need to fix this inconsistency innSwagger. |  | Implemented | No |  | Design misaligned | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Update the ECS reports catalogue to align with Event Code naming standard (used in other Interfaces) and to align with Swagger. On REP-901 report, the event code in the reports catalogue is defined [DUoS_EmbeddedLDSO_Agg_Inv_Data] and [DUoS_Supplier_Agg_Inv_Data] whereas on the Swagger Document it’s DUoSSupplierInvData. Swagger has also been updated to align. | Data interface correction | Supporting Docs | ESC Report | ECS Report Swagger
MHHS-DIN-769 | RG |  | 2023-11-13 |  |  | Rob Golding | SRO | Updates to MHHSP-ERI011B (IR5) not reflected in the swagger | There appears to be several updates to the reporting spreadsheet that did not have a corresponding update in the swagger. The R901-05 block in Swagger is missing an attribute; DI-613. The spreadsheet has incorrect SVA data types for these two new items |  | Implemented | No |  | Design misaligned | Helix, DIP, Suppliers, LDSOs |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Update R901-05 block in Swagger; DI-613. Update MHHSP-ERI011B; the incorrect SVA data types for these two new items. | Data interface correction | Supporting Docs | Interfaces | MHHSP-ERI011B, Swagger
MHHS-DIN-770 | SW | DIN-773 | 2023-11-13 |  | 18780 | Chris Lenihan | Software Provider | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025 | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025. This needs to be updated in the list of enumerated value to be IF-026. |  | Implemented | No |  | Design misaligned | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025. This needs to be updated in the list of enumerated value to be IF-026 in Swagger. | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-771 | RG |  | 2023-11-13 |  |  | Rob Golding | SRO | R900-03. listOfMPANSOnsite should be listOfMPANSOnSite | Typo in swagger - R900-03. listOfMPANSOnsite should be listOfMPANSOnSite |  | Implemented | No |  | Design misaligned | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Update R900-03. listOfMPANSOnsite to listOfMPANSOnSite | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-772 | SW | DIN-767 | 2023-11-13 | C&C | 19150 | Chris Lenihan | Software Provider | Swagger incorrect for IF-043 | For IF-043 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-043-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. |  | Implemented | Yes |  | Design misaligned | DIP Users, DIP |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | Update IF-043 so that it uses the required property name is ‘CustomBlock’ but the actual name is ‘IF-043-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-773 | SW | DIN-770 | 2023-11-13 |  | 18780 | Chris Lenihan | Software Provider | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025 | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025. This needs to be updated in the list of enumerated value to be IF-026. |  | Implemented | Yes |  | Design misaligned | DIP Users, DIP |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025. This needs to be updated in the list of enumerated value to be IF-026 in Swagger. | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-774 | RG |  | 2023-11-15 |  |  | Rob Golding | SRO | IF-020 [LinkedImportExportRemove] & [RelatedRemove] | The B090 block needs to be optional to cope with the scenario where a linked/related meter is removed and it leaves the situation that there are no linked/related meters. Also, on line 64 it mentions a B074 block, however, there is no B074 block in the message |  | Closed | [10 empty] | Fix the swagger and DES138 to reflect this condition | Design Ambiguous | Supporting Docs | Interfaces | DES138
MHHS-DIN-775 | MF |  | 2023-11-15 |  |  | Sarah Jones | Central Body | Remove Customer Direct Process from BP002/BP003 | The Customer Direct process has been set out in BP010 (DIN-554) so can be removed from BP002/BP003 to avoid any confusion |  | Assessment Complete / Implementation Deferred | No |  | Clarification - No change required | N/A |  | Post Go-live Release |  |  | Post Go-live Release |  | Remove Customer Direct process steps from BP002/BP003 | Process Model correction | Supporting Docs | Process Models | BP002 BP003
MHHS-DIN-776 | MH |  | 2003-11-16 | Elexon |  | Sedef Kiris | Central Body | LLF Data and Rep005 | There is some ambiguity within the Design Artefacts around how ISD should be delivering LLF Data and REP-005. ​ BRS010 implies ISD will publish it through a common delivery method as the Master Settlement Timetable and the rest of the ISD entities, but it does not mention REP-005.​ BRS001 (Transition) denotes that REP-005 will be published via the Elexon Portal and will utilise IF-047. ​ ERI011B denotes that the distribution pattern and the report format of REP-005 are to be defined by Elexon. ​ EDI021 does not include any ISD entities for LLF data. ​ REP-005 and the LLF data mentioned in the design artefacts are the same thing, and Helix intend to fulfil their requirements by delivering in line with requirements as laid out in the Transition BRS. ​ Impact: There is a potential lack of clarity amongst Participants around how they are going to receive REP-005, inconsistency in the overall solution of data coming from ISD. |  | Closed | [6 empty] | #REF! |  |  | #REF! | Duplicate - To be tracked under MHHS-DIN-754
MHHS-DIN-777 | RG | DIN-785 | 2023-11-16 | SRO | 20939 20723 | Rob Golding |  | IF-001-ChangeOfSupplier required fields on CommonBlocks are incorrect | The required fileds on the common block are set to commonblock and customblock, they need to be set to S1 etc. |  | Implemented | Yes |  | Design misaligned | DIP Users |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | The required fileds on the common block are set to commonblock and customblock, they need to be set to S1 etc. This has been updated in Swagger so the common block in IF-001 now contains the correct required blocks. Only an issue with 5.+ not 2.+ | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-778 | RG |  | 2023-11-17 | Stark |  | Rob Golding | Supplier | Fix enumeration on the PUB domain for the following PUBs; PUB-004, PUB-019, PUB-020, PUB-040 and PUB-050 in DT-983. Same IF's added for DT-000. | There are a number of values missing from the enumeration in the DT-983 for the Interfaces defined. These are PUB-004, PUB-019, PUB-020, PUB-040 and PUB-050. There are a number of values missing from the enumeration in the DT-000 for the Interfaces defined. These are IF-004, IF-019, IF-020, IF-040 and IF-050. |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 2.3 |  |  | Interim Release 2.3 |  | PUB-004, PUB-019, PUB-020, PUB-040 and PUB-050 are missing from DT-983 that defines the enumeration of available values, so these have been added. IF-004, IF-019, IF-020, IF-040 and IF-050 are missing from DT-000 that defines the enumeration of available values, so these have been added. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-779 | SC |  | 2023-11-20 | IMServ |  | Sean Cooper |  | Routing for IF-041 | Add Data Service to Primary Routing for SDS issued IF-041's to align with BP003C |  | Implemented |  |  | Design misaligned | SDS |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Added Data Service (where required) to Primary Routing in the SDS row of IF-041 routing table | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-780 | SB |  | 2023-11-21 | St Clements | 19885 | Madison Layton | Central Body | No longer providing examples within the Interface Catalogue | Updates to the swagger and Interface Catalogue will no longer have examples detailed within the Interface catalogue |  | Closed | No | [5 empty] | #REF! |  |  | #REF! | Examples are now managed in Swagger
MHHS-DIN-781 | BK | DIN-748, DIN-783 | 2023-11-21 | IMserv |  | Liam Lowey | Software Provider | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength should not have a maxLength validation attribute as it is an integer type. This means the schema itself does not validate against the rules for these types of schemas. |  | Implemented | Yes |  | Design misaligned | DIP Users |  | Interim Release 2.3 |  |  | Interim Release 2.3 |  | DI-487-Total-Number-Energised-MPANs maxLength attribute should be length as it is an integer type. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-782 | BK | DIN-749, DIN-784 | 2023-11-21 | IMserv |  | Liam Lowey | Software Provider | SchemaBug - DipMessage.payload is not a required property | SchemaBug - DipMessage.payload is not a required property, therefore different property names will pass validation without being checked - this means if you spell it "Payload" with a capital P instead it will effectively skip validation resulting in a false positive. |  | Implemented | Yes |  | Design misaligned | DIP Users |  | Interim Release 2.3 |  |  | Interim Release 2.3 |  | ‘payload’ needs to be a required attribute for the DIPMessage object. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-783 | BK | DIN-748, DIN-781 | 2023-11-21 | IMserv |  | Liam Lowey | Software Provider | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength should not have a maxLength validation attribute as it is an integer type. This means the schema itself does not validate against the rules for these types of schemas. |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | DI-487-Total-Number-Energised-MPANs maxLength attribute should be length as it is an integer type. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-784 | BK | DIN-749, DIN-782 | 2023-11-21 | IMserv |  | Liam Lowey | Software Provider | SchemaBug - DipMessage.payload is not a required property | SchemaBug - DipMessage.payload is not a required property, therefore different property names will pass validation without being checked - this means if you spell it "Payload" with a capital P instead it will effectively skip validation resulting in a false positive. |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | Swagger updated so that ‘payload’ has been added as a required attribute for the DIPMessage object. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-785 | BK | DIN-777 | 2023-11-21 | SRO | 20939 20723 | Rob Golding |  | IF-001-ChangeOfSupplier required fields on CommonBlocks are incorrect | The required fields on the common block are set to commonblock and customblock, they need to be set to S1 etc. |  | Implemented | Yes |  | Design misaligned |  |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Update IF-001-ChangeOfSupplier required fields on CommonBlocks that are incorrect | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-786 | MF | DI-238 | 2023-11-21 | St Clements |  | Mike Fensome |  | Determination of Market Segment Effective From Date | Add clarification on how Registration Service will set Market Segment Effective From Date |  | Implemented | No |  | Clarification - No change required | SCS |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Added new section to REGS_Notes to clarify how Market Segment EFD is set by Registration Service. The table below outlines how the Registration Service will Derive Market Segment Effective From Date, following various 'trigger' events. Market Segment Change Trigger Derived Market Segment EFD Notes Connection Type Connection Type EFD If triggers a change to related/associated MPANs SEG use the same derived EFD, except in the case this is prior to the relationship/association EFD in which case use relationship/association EFD instead Meter Added/Meter Type changed Meter Installation Date Meter Removed Meter Removal Date If trigger is a Meter Exchange use installation date not removal date Relationship Created Relationship EFD Only amend SEG EFD for MPANs where the SEG is changing – SEG of some MPANs in the relationship/association will not be changing Relationship Deleted Relationship ETD Association Created Association EFD Association Deleted Association ETD Where derived EFD is less than the current Market Segment EFD, the current Market Segment EFD will be cancelled to allow for the new one. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-787 | BK |  | 2023-11-21 | RECCo |  | Sarah Jones | Central Body | Typo in the data item name for DI20228 - DIP Roles / IDs Always Receipient ID (DI-993 in the Interface Catalogue) | It has been noted that there is a typo in the data item name for DI20228 - DIP Roles / IDs Always Recipient ID |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Correction of spelling on the word 'Recipient' against DI-993 in the Interface Catalogue | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-788 | SC |  | 2023-11-22 | St Clements |  | Madison Layton | Software Provider | Reconnection of MPAN (provided that CSS DeRegistration has not completed) | New BP009B - would need IF-009 Event Code. "Reconnected" to SUPC only and Re-issue of IF-50 to EES for MPRS Status code. Current MHHS design does not cater for the re-connection of an MPAN that has previously been dis-connected​ Under current operation this is allowed for via a Manual amendment request by the LDSO (Covered by BSCP604) where the MPAN has not been Registration De-activated |  | Implemented | No |  | Design gap | St Clements, Suppliers |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | ​Update to BP007 (Disconnection) to show the flows where an MPAN is re-connected ​ Update to BRS003 to add requirement for Registration Service triggering the IF-009 and IF-050 to inform of a re-connection​ Update to BRS004 to add requirement for Suppliers receiving PUB-009 [MPANReconnection]​ Update DES-138 to add new [MPANReconnection] event code to IF-009​ Update to Swagger to add IF-009 MPANReconnection event code variant to Swagger. | Process Model correction | Supporting Docs | Various documents | BP007, BR003, BR004, DES-138, Swagger
MHHS-DIN-789 | BK | DIN-673 | 2023-11-22 | Design Team |  | Rob Golding | Programme Design | Floating Point number regexes | DIN 267 inadvertently updated regexes to a pattern which does not align to the agreed format as of Technical Design Working Group Work-Off Issue D-0408th November 2022. The regexes need to align to what was agreed. |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 2.3 |  |  | Interim Release 2.3 |  | Update regex patterns for the following data types: DT-016, DT-022, DT-023, DT-024, DT-025, DT-030, DT-031, DT-032, DT-033 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-790 | BK | DIN-791 | 2023-11-22 | Design Team |  | Rob Golding | Programme Design | Number regex - DI-123 | Update regex patterns for the following data type: DI-123 |  | Implemented | Yes | 17678 | Error/Correction | DIP Users |  | Interim Release 2.3 |  |  | Interim Release 2.3 |  | Update regex patterns for the following data type: DI-122 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-791 | BK | DIN-790 | 2023-11-22 | Design Team |  | Rob Golding | Programme Design | Number regex - DI-123 | Update regex patterns for the following data type: DI-123 |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | Added regex patterns for the following data type: DI-123 to use the following pattern: ^\d{4,4}$ | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-792 | BK | DIN-790, DIN-791 | 2023-11-22 | Design Team |  | Rob Golding | Programme Design | Number regex - DI-123 | Update regex patterns for the following data type: DI-123 |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Update regex patterns for the following data type: DI-123 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-793 | SB |  | 2023-11-23 | St Clements | 21513 | Madison Layton | Central Body | DI-241 - SUPC routing on IF-037 incorrect, should be SUPS | SUPC was moved to primary routing for IR5 release, as per attached. However it was clarified on a COS this would be the old Supplier not the current Supplier, so SUPC will not always be correct. Needs to be changed for clarity, SUPS could be used to indicate IF-037 will be sent to the Supplier that submitted the original SP appointment for the SP being de-appointed? |  | Implemented | No |  | Clarification - No change required | St Clements |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Updated primary routing on IF-037 from SUPC to Supplier. On a COS, Registration Service will send to the old Supplier, on Change of Service Provider to the Current Supplier. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-794 | MH | DIN-409 | 2023-11-23 | Elexon | 19961 | Sedef Kiris | Central Body | ISD Consumption Component Classes M5 | In the ISD entity, there was an adjustment made by DIN 409 to distinguish the settlement quality indicator with the same CCC ID. While the ISD Entities specification document has been appropriately updated, the corresponding changes have not been reflected in the MDS method statement Appendix 1. This inconsistency is causing confusion. |  | Implemented | No |  | Error/Correction | Elexon |  | Interim Release 7 | 2024-01-19 |  | Interim Release 7 | 2024-01-19 | The example provided in Appendix 1 in the METH007 is wrong and misleading. As a correct example is provided in the ISD Entities document, we'll remove the one in METH007 | Method statement correction | Meter to Bank | Method Statement | METH007
MHHS-DIN-795 | MH | DIN-678 | 2023-11-23 | Elexon | 18841 | Rashmi Radhakrishnan | Central Body | ISD M9 Clarification | DIN-678 was to change the length of the following UMS data items in ISD: Unit description 1, 2 and Manufacturer's Designation. But Manufacturer's Designation was not changed in both M9 and M10. This iDIN is to complete that update. |  | Implemented | No |  | Design misaligned | Elexon, UMSDS |  | Interim Release 7 | 2024-01-19 |  | Interim Release 7 | 2024-01-19 | Update Manufacturer's Designation in ISD Entity M9 to up to 100 characters | Requirement correction | Supporting Docs | ISD | EDI021
MHHS-DIN-796 | MF | DIN-234 | 2023-11-23 | St Clements |  | Madison Layton | Software Provider | Clarification on validation of B018 block conditionality in IF-034 | Clarification that SCS will validate that a Smart Meter is present for Block B018 conditionality by checking that DCC Service Flag (DI-025) is A |  | Implemented | No |  | Clarification - No change required | SCS |  | Interim Release 7 | 2024-01-19 |  | Interim Release 7 | 2024-01-19 | Note added to IF-034 interface to clarify that SCS will validate that a Smart Meter is present for Block B018 conditionality by checking that DCC Service Flag (DI-025) is A | Data interface correction | Supporting Docs | Interfaces | DES-138
MHHS-DIN-797 | BK |  | 2023-11-24 | Design Team |  | Rob Golding | Programme Design | Capitalisation in Swagger | E2E001 Architecture document will be updated to reflect the adherence to case sensitivity on the inbound messages, and the removal of the statement in Swagger relating to case insensitivity. |  | Implemented | Yes |  | Design gap | DIP Users |  | Interim Release 2.3 |  |  | Interim Release 2.3 |  | Updating of the Swagger and E2E001 to align to Open API standards in relation to case sensitivity. The Section in the E2E001 is 4.4.3 and Swagger its the removal of a comment at the top of swagger file | Data interface correction | Supporting Docs | Interfaces | Swagger, E2E Architecture Document
MHHS-DIN-798 | BK |  | 2023-11-24 | Design Team |  | Rob Golding | Programme Design | Capitalisation in Swagger | E2E001 Architecture document will be updated to reflect the adherence to case sensitivity on the inbound messages, and the removal of the statement in Swagger relating to case insensitivity. |  | Implemented | Yes |  | Design gap | DIP Users |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | Updating of the Swagger and E2E001 to align to Open API standards in relation to case sensitivity. The Section in the E2E001 is 4.4.3 and Swagger its the removal of a comment at the top of swagger file | Data interface correction | Supporting Docs | Interfaces | Swagger, E2E Architecture Document
MHHS-DIN-799 | SW |  | 2023-11-24 | Design Team |  | Rob Golding | Programme Design | Capitalisation in Swagger | E2E001 Architecture document will be updated to reflect the adherence to case sensitivity on the inbound messages, and the removal of the statement in Swagger relating to case insensitivity. |  | Implemented | Yes |  | Design gap | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Updating of the Swagger and E2E001 to align to Open API standards in relation to case sensitivity. The Section in the E2E001 is 4.4.3 and Swagger its the removal of a comment at the top of swagger file | Data interface correction | Supporting Docs | Interfaces | Swagger E2E001 Architecture Document
MHHS-DIN-800 | SW |  | 2023-11-27 | Design Team |  | Steve Weston | Programme Design | ECS Reports Inconsistency with Swagger | Inconsistency between ECS Reports Catalogue and Swagger: REP-002B -- R027 and R013 - Distributor and GSP blocks appear to be missing from REP-002B in Swagger. REP-003 -- R024 contains DI-496 in the ECS reports, but in Swagger it contains DI-307. REP-003 -- R9017 contains correctAndUncorrectComponent does not contain block R018 in the name. REP-004 -- R025 and R026 should have parent of R009 according to ECS catalogue, but Swagger has these defined with no parent. REP-006 -- R003 contains R033. R033 should have DI-496, 374, 359, and 360, but in Swagger, contains 307, 374, 359 & 360. REP-006 -- R051 says parent is R032 in ECS reports catalogue, but R051 does not appear in the Swagger in R032. As a result, R106 or R107 which should be part of R051 is missing. REP-009 -- The R013 block contains R016 in Swagger, but in the ECS Catalogue, this is R013 > R068. REP-900 -- R900-03 contains DI-345 in Swagger, when it should contain DI-612. Also marked incorrectly as required. |  | Closed |  |  | Design misaligned | DIP Users | [6 empty] | Inconsistency between ECS Reports Catalogue and Swagger. For all items below, Swagger is to be updated to align with the ECS Reports Catalogue: REP-002B -- R027 and R013 - Distributor and GSP blocks are missing from REP-002B in Swagger. Add missing blocks. REP-003 -- R024 contains DI-496 in the ECS reports, but in Swagger it contains DI-307. Update to DI-496. REP-003 -- R9017 contains correctAndUncorrectComponent does not contain block R018 in the name. Update naming. REP-004 -- R025 and R026 should have parent of R009 according to ECS catalogue, but Swagger has these defined with no parent. Update Swagger to align. REP-006 -- R003 contains R033. R033 should have DI-496, 374, 359, and 360, but in Swagger, contains 307, 374, 359 & 360. Update to DI-496. REP-006 -- R051 says parent is R032 in ECS reports catalogue, but R051 does not appear in the Swagger in R032. As a result, R106 or R107 which should be part of R051 is missing. Add the missing blocks to align. REP-009 -- The R013 block contains R016 in Swagger, but in the ECS Catalogue, this is R013 > R068. Update R013 in Swagger to contain R068. REP-900 -- R900-03 contains DI-345 in Swagger, when it should contain DI-612. Also marked incorrectly as required. Update Swagger to use DI-612. Closed as decision made to only align ECS Reports changes to IR7. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-801 | SW |  | 2023-11-27 | Design Team |  | Steve Weston | Programme Design | ECS Reports Inconsistency with Swagger | Inconsistency between ECS Reports Catalogue and Swagger: REP-002B -- R027 and R013 - Distributor and GSP blocks appear to be missing from REP-002B in Swagger. REP-003 -- R024 contains DI-496 in the ECS reports, but in Swagger it contains DI-307. REP-003 -- R9017 contains correctAndUncorrectComponent does not contain block R018 in the name. REP-004 -- R025 and R026 should have parent of R009 according to ECS catalogue, but Swagger has these defined with no parent. REP-006 -- R003 contains R033. R033 should have DI-496, 374, 359, and 360, but in Swagger, contains 307, 374, 359 & 360. REP-006 -- R051 says parent is R032 in ECS reports catalogue, but R051 does not appear in the Swagger in R032. As a result, R106 or R107 which should be part of R051 is missing. REP-009 -- The R013 block contains R016 in Swagger, but in the ECS Catalogue, this is R013 > R068. REP-900 -- R900-03 contains DI-345 in Swagger, when it should contain DI-612. Also marked incorrectly as required. |  | Implemented |  |  | Design misaligned | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Inconsistency between ECS Reports Catalogue and Swagger. For all items below, Swagger is to be updated to align with the ECS Reports Catalogue: REP-002B -- R027 and R013 - Distributor and GSP blocks are missing from REP-002B in Swagger. Add missing blocks. REP-003 -- R024 contains DI-496 in the ECS reports, but in Swagger it contains DI-307. Update to DI-496. REP-003 -- R9017 contains correctAndUncorrectComponent does not contain block R018 in the name. Update naming. REP-004 -- R025 and R026 should have parent of R009 according to ECS catalogue, but Swagger has these defined with no parent. Update Swagger to align. REP-006 -- R003 contains R033. R033 should have DI-496, 374, 359, and 360, but in Swagger, contains 307, 374, 359 & 360. Update to DI-496. REP-006 -- R051 says parent is R032 in ECS reports catalogue, but R051 does not appear in the Swagger in R032. As a result, R106 or R107 which should be part of R051 is missing. Add the missing blocks to align. REP-009 -- The R013 block contains R016 in Swagger, but in the ECS Catalogue, this is R013 > R068. Update R013 in Swagger to contain R068. REP-900 -- R900-03 contains DI-345 in Swagger, when it should contain DI-612. Also marked incorrectly as required. Update Swagger to use DI-612. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-802 | SW |  | 2023-11-27 | Design Team |  | Steve Weston | Programme Design | Naming standards are inconsistently applied in ECS reports catalogue for nested structures and lists. | Naming standards are inconsistently applied in ECS reports catalogue for nested structures and lists, meaning it you have blocks that contain blocks with the same name, as there is no naming mechanism to easily link nested block name to contains, or back to ECS reports catalogue. |  | Closed | [10 empty] | Implement a new naming standard for ECS reports catalogue. Closed as decision made to only align ECS Reports changes to IR7. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-803 | SW |  | 2023-11-27 | Design Team |  | Steve Weston | Programme Design | Naming standards are inconsistently applied in ECS reports catalogue for nested structures and lists. | Naming standards are inconsistently applied in ECS reports catalogue for nested structures and lists, meaning it you have blocks that contain blocks with the same name, as there is no naming mechanism to easily link nested block name to contains, or back to ECS reports catalogue. |  | Implemented |  |  | Design misaligned | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Implement a new naming standard for ECS reports catalogue for nested structures and lists. | Data interface correction | Supporting Docs | Interfaces | ECS Reports Catalogue
MHHS-DIN-804 | SB |  | 2023-11-28 | ESG | 22206 | Patricia Parker | Software Provider | Migration clarification | Page 13 of the migration document states the following for Forward Migration CoA 14. The Registration Service will send the IF-036 at the Service Appointment effective from date. The sending of the IF-036 will act as the definitive indicator that a Forward Migration has completed. Is the IF_036 not sent at the Service Appointment effective from date – 1 . Registration Service will have processed all Secured Active Messages and processed the Pending Appointment Queue by 21:00. This will include the production and publication of all required IF-035, IF-036 and IF-037 messages. |  | Closed |  |  | Clarification - No change required | [7 empty] | Already discussed and agreed for SDS to determine solution.
MHHS-DIN-805 | RG |  | 2023-11-29 | SRO |  | Rob Golding | SRO Design | Examples in swagger incorrectly resolved if have a leading 0 | Sims & Ems noted that the example for DI-123-SSC was resolving to the value 83 when in fact it should be 0123. |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Tracked down a bug in swaggerhug, doesn't like leading zero on non-string delimted examples. Work around is to string delimit. Also added regular expression pattern - ^\d{4,4}$. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-806 | SW |  | 2023-11-29 | Electralink | 21470 | Roz Turner | Central Body | Details of the compression team are not defined in the E2E001 design document, only in CR030 at a high level | There is currently no detail in the E2E001 of how data should be compressed and uncompressed for the ECS reports, this information is held in CR030 and DRG documentation. This DIN is to update the E2E001 Architecture design document to add a section to explain this in more detail. |  | Closed | Yes | [9 empty] | Closed - will be picked up in IR7 as part of DIN-806 | Data interface correction | Supporting Docs | Interfaces | Swagger, E2E Architecture Document
MHHS-DIN-807 | SW |  | 2023-11-29 | Electralink | 21470 | Roz Turner | Central Body | Details of the compression team are not defined in the E2E001 design document, only in CR030 at a high level | There is currently no detail in the E2E001 of how data should be compressed and uncompressed for the ECS reports, this information is held in CR030 and DRG documentation. This DIN is to update the E2E001 Architecture design document to add a section to explain this in more detail. |  | Implemented |  |  | Design ambiguous | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Updated the E2E001 Architecture design document to add a section to explain how data should be compressed and uncompressed for the ECS reports. | Data interface correction | Supporting Docs | Technical Design | E2E001 Architecture Document
MHHS-DIN-808 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-007 EnergisationStatusChange/Failure CustomBlocks missing required attribute | Missing required (mandatory) attribute in object (B025 and B040) |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | Swagger update for inclusion of missing attribute in IF-007. This was adding B025 block as required block in the EnergisationStatusChnage variant of IF-007 and adding B040 block as a required block in the EnergisationStatusFailure variant of IF-007. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-809 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-008 EnergisationStatusChange, common block for R0 and CustomBlocks for B025 block missing required attribute | Missing required (mandatory) attribute in object (R0 and B025) |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | Swagger update for inclusion of missing attribute in IF-008. This was adding R0 block as required block in the Common block of IF-008 and adding B025 block as a required block in the CustomBlock of IF-008. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-810 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-004 common block M0 required attribute is missing | Missing required attribute in object |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | Swagger update for inclusion of missing attribute M0 in the required common block in IF-004 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-811 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-024 missing required attributes in blocks | IF024 SNVacant CustomBlock required B057 IF024 SNRemoteEnabled CustomBlock required B057, B069 IF024 SNSupplierAC CustomBlock required B057, B058 |  | Closed | Yes |  | Error/Correction | DIP Users | [6 empty] | Swagger update for inclusion of missing attribute in IF-024 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-812 | RG | DIN-699 | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-036 missing required attributes for B068 block | Missing required attribute in object |  | Closed | Yes |  | Error/Correction | DIP Users | [6 empty] | Swagger update for inclusion of missing attribute in IF-036 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-813 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-015 incorrect required Custom Block | There is no customblock on IF-015 |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | Swagger update for removal of custom block in IF-015, as there is no CustomBlock on IF-015. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-814 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-045 incorrect name on Custom block | For IF-045 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-045-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | Swagger update for incorrect name of custom block in IF-045, this has been renamed to CustomBlock. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-815 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | DI-838-Supplier-Proposed-Consent-Granularity requires a null enum | This is to match nullable:true from DES-138. |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | Swagger update for DI-838 to allow null in the enumerated list of values. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-816 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-001 Custom Block missing addtional properties false attribute | IF-001 Custom Block missing addtional properties false attribute |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | Swagger update for inclusion of missing attribute in IF-001 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-817 | SW |  | 2023-11-29 | Helix |  | Steve Weston | SI Design | Incorrect examples in Swagger for Integers that start with 0 (bug in Swagger Hub) | There are incorrect examples provided for some properties, for example SSC (DI-123) in B032 in the Submit Events on SwaggerHub. This is partly a bug in Swagger Hub where the properties should not start with a '0'. |  | Closed |  |  | Error/Correction | DIP Users |  |  | #REF! |  |  | #REF! | Duplicate of DIN-805
MHHS-DIN-818 | SW |  | 2023-11-29 | Helix |  | Steve Weston | SI Design | IF-014 Payload does not implement B900 block correctly to align with IF-021. | IF-014 should contain a B900 block, not a B900 array. This change was made in IR5 for IF-021, but was only applied to IF-014 in IR6. This DIN is to align with IF-021 for IR5 and ensure that B900 used, not an array of B900's. |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | Swagger update to IF-014 to align with IR6 implementation | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-819 | SW |  | 2023-11-29 | Helix |  | Steve Weston | SI Design | Typo in event code for REP-004 | In REP-004, the eventCode = [SuplierDemandTakeReport], and supplier is spelt incorrectly. This needs to be updated in both the ECS reports catalogue and Swagger |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Update REP-004 and Swagger the eventCode = [SuplierDemandTakeReport], and supplier is spelt incorrectly. | Data interface correction | Supporting Docs | Interfaces | Swagger, ECS Report
MHHS-DIN-820 | SW |  | 2023-11-29 | Procode | 21898, 21073 | Steve Weston | SI Design | IF-041 contains B06465list that uses anyOf when this should be oneOf B064 or B065 to align with DES-138. | IF-041 contains B06465list that uses anyOf when this should be one of either B064 or B065 to align with DES-138. This needs to be updated so that this list contains wither a B064 list OR B065 list, not both / either. |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | Swagger update to align IF-041 to DES-138. Any of has been removed from the Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-821 | SW | DIN-820 | 2023-11-29 | Procode | 21898, 21073 | Steve Weston | SI Design | IF-041 contains B064/65 list that uses anyOf when this should be oneOf B064 or B065 to align with DES-138. | IF-041 contains B064/65 list that uses anyOf when this should be one of either B064 or B065 to align with DES-138. |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Swagger is aligned to DES-138 to allow one or both B064 and B065. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-822 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-007 EnergisationStatusChange/Failure CustomBlocks missing required attribute | Missing required attribute in object (B025 and B040 respectively are missing from IF-007 EnergisationStatusChange/Failure CustomBlocks. |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Missing required attribute in object (B025 and B040 respectively are missing from IF-007 EnergisationStatusChange/Failure CustomBlocks. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-823 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-008 EnergisationStatusChange, common block for R0 and CustomBlocks for B025 block missing required attribute | IF-008 EnergisationStatusChange, common block for R0 and CustomBlocks for B025 block missing required attribute |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Swagger update for inclusion of missing attribute in IF-008 - IF-008 EnergisationStatusChange, common block for R0 and CustomBlocks for B025 block missing required attribute | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-824 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-004 common block M0 required attribute is missing | IF-004 common block M0 required attribute is missing |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | IF-004 common block M0 required attribute is missing, so this has been added in the Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-825 | RG | DIN-881 | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-024 missing required attributes in blocks | IF024 SN-Vacant CustomBlock required B057 IF024 SN-NoComms CustomBlock required B057 IF024 SNRemoteEnabled CustomBlock required B057, B069 IF024 SNSupplierAC CustomBlock required B057, B058 |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Swagger update for inclusion of missing attribute in IF-024 IF024 SN-Vacant CustomBlock required B057 IF024 SN-NoComms CustomBlock required B057 IF024 SNRemoteEnabled CustomBlock required B057, B069 IF024 SNSupplierAC CustomBlock required B057, B058 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-826 | RG | DIN-699 | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-036 missing required attributes for B068 block | Missing required attribute in object |  | Closed |  |  | Error/Correction | DIP Users |  |  | #REF! |  |  | #REF! | Duplicate of DIN-699 Swagger update for inclusion of missing attribute in IF-036
MHHS-DIN-827 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-015 incorrect required Custom Block | There is no customblock on IF-015, so this has been removed from this Interface on Swagger. |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | There is no customblock on IF-015, so this has been removed from this Interface on Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-828 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-045 incorrect name on Custom block | For IF-045 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-045-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | For IF-045 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-045-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. This change has been made in Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-829 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | DI-838 and DI-017 - require an N - No Consent enum | DI-838-Supplier-Proposed-Consent-Granularity and DI-017 Consent Granularity requires an N - No Consent enum in the list of allowable values. DI-838 needs to be Mandatory no nulls |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Swagger updated so that DI-838-Supplier-Proposed-Consent-Granularity and DI-017 Consent Granularity includes N - No Consent in the list of allowable values. DI-838 updated to be Mandatory no nulls | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-830 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-001 Custom Block missing addtional properties false attribute | IF-001 Custom Block missing addtional properties false attribute |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | IF-001 Custom Block missing addtional properties false attribute. Swagger updated to include this. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-831 | BK | DIN-689 | 2023-11-30 | SI Design |  | Madison Layton | Central Body | DI-120 Additional Information should be mandatory nullable | DI-120 was made non nullable in IR5.1 in Swagger. This needs to be corrected so that DI-120 is used in multiple places and needs to be mandatory nullable. |  | Implemented | Yes |  | Design misaligned | DIP Users, DIP |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | Make DI-120 Additional Information Mandatory nullable in Swagger to align with DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-832 | RS | DIN-840 | 2023-12-01 | Kraken | 22885 | Henri Naef | Software Provider | [MeterUpdate]) to be added to data item B039 heading for IF-006 | IF-005/IF-006 both contain data item B039, however a difference exists in the header. IF-005 contains "Optional for Event [MeterHistoryUpdate] & [MeterUpdate])" whereas the IF-006 contains only "Optional for Event [MeterHistoryUpdate]) |  | Implemented |  |  | Design misaligned |  |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | DES-138 and Swagger updated to include [MeterUpdate] as Optional for B039 in IF-006. | Data interface correction | Supporting Docs | Interfaces | Swagger, DES138
MHHS-DIN-833 | RS | DIN-841 | 2023-12-01 | UKPN | 23047 | Neal Medley | Network Operator | Routing table to include LDSO for IF-018 | Optionality matrix shows that LDSOs can additionally receive Event Codes [AddressChg], [GSPChg] and [DUOSTariffIDChg]. LDSO to be added to IF-018 secondary routing for these three event codes in DES138 |  | Implemented |  |  | Design ambiguous |  |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | DES-138 updated routing table for IF-018 updated to include LDSO for Event Codes [AddressChg], [GSPChg] and [DUOSTariffIDChg]. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-834 | RG | DIN-818 | 2023-12-01 | SRO |  | Rob Golding | SRO Design | IF-014 - to align with IF-021 | Update DES138 to match swagger |  | Implemented |  |  | Design misaligned | DIP Users, DIP |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | Update IF-014 to match IF-021 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-835 | RG | MHHS-DIN-836, 882 | 2023-12-04 | Avanade |  | Rob Golding | SRO Design | Add additional error messages to DES138 | Avanade as part of their development work have generated some error codes that need to fed back into DES138: Error Code Error Text MSG1013 Invalid CertifcateIssuerName MSG1014 Certificate has expired MSG1039 Invalid MPAN MSG5001 Internal server error MSG5002 No data contained in request body MSG5003 Unable to determine correlationId requirement. Server configuration error or sender request error MSG5004 Internal server error.Payload not processed |  | Implemented |  |  | Design gap | DIP Users, DIP |  | Interim Release 7 |  |  | Interim Release 7 |  | Add error codes into the DES-138 Interface Catalogue (00-Introduction Tab) Error Code Error Text MSG1013 Invalid CertifcateIssuerName MSG1014 Certificate has expired MSG1039 Invalid MPAN MSG5001 Internal server error MSG5002 No data contained in request body MSG5003 Unable to determine correlationId requirement. Server configuration error or sender request error MSG5004 Internal server error.Payload not processed | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-836 | RG | MHHS-DIN-835, 882 | 2023-12-04 | SRO |  | Rob Golding | SRO Design | New swagger file ErrorCodes to describe MHHS error messages | New swagger file (Response Codes schema) to capture all message and error codes from DES138. |  | Implemented |  |  | Design gap | DIP Users, DIP |  | Interim Release 7 |  |  | Interim Release 7 |  | New swagger file (Response Codes schema) to capture all message and error codes from DES138. | Data interface correction | Supporting Docs | Interfaces | Swagger E2E001 Architecture Document
MHHS-DIN-837 | SB |  | 2023-12-05 | ESG | 21835 | Patricia Parker | Software Provider | Migration D0086 Clarification | Page 51 of the migration design document shows the following for the D0086. Data Item ‘Meter Reading Reason Code’ (J0332) related enumeration will include 3 additional values:- a. Enumeration Value: 28; Enumeration Description: Forward Migration CoA b. Enumeration Value: 29; Enumeration Description: Forward Migration CoS c. Enumeration Value: 30; Enumeration Description: Reverse Migration My understanding was that the values should reflect those in the D0010 for the migration so parties where aware of the migration process:- Data Item ‘Reading Type’ (J0171) related enumeration will include 3 additional values: a. Enumeration Value: U; Enumeration Description: Forward Migration CoA b. Enumeration Value: V; Enumeration Description: Forward Migration CoS c. Enumeration Value: Y; Enumeration Description: Reverse Migration |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7 | 2024-01-19 |  | Interim Release 7 | 2024-01-19 | Changes made to the Migration Design Document in section 13.1.4 (D0086) under point 2 (this now aligns with DES196) as follows; Data Item ‘Reading Type’ (J0171) related enumeration will include 3 additional values: Enumeration Value: U; Enumeration Description: Forward Migration CoA Enumeration Value: V; Enumeration Description: Forward Migration CoS Enumeration Value: Y; Enumeration Description: Reverse Migration | Data interface correction | Supporting Docs | Interfaces | Migration Design Document
MHHS-DIN-838 | SB |  | 2023-12-05 | British Gas | 23696 | Neil Strange | Supplier | BPD004 v5 - step 270 typo | Can you confirm that the reference to SDS method statement in step 270 of the data collection process description is a typo and should be ADS? This is in BPD004 v5. Looks like a simple cut and paste mistake |  | Implemented | No |  | Error/Correction |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | BPD004 - step 270 update typo from "SDS" to "ADS" | Process Model correction | Supporting Docs | Process Model description document | BPD004
MHHS-DIN-839 | MF |  | 2023-12-05 | ESG |  | Mike Fensome | Software Provider | Confirmation of DT016 data type | Update all references of DT016 to show as string 14 to align with swagger |  | Implemented | No |  | Design misaligned |  |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | DT016 updated in DES138 to show as String 14 as per swagger for the following data item references: DI-043 Load Shape 7 Day Rolling Total DI-102 Load Shape Period Value DI-104 Configurable Register Reading | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-840 | RS | DIN-832 | 2023-12-01 | Kraken | 22885 | Henri Naef | Software Provider | [MeterUpdate]) to be added to data item B039 heading for IF-006 | IF-005/IF-006 both contain data item B039, however a difference exists in the header. IF-005 contains "Optional for Event [MeterHistoryUpdate] & [MeterUpdate])" whereas the IF-006 contains only "Optional for Event [MeterHistoryUpdate]) |  | Implemented | No |  | Design misaligned |  |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | DES-138 and Swagger updated to include [MeterUpdate] as Optional for B039 in IF-006. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-841 | RS | DIN-833 | 2023-12-01 | UKPN | 23047 | Neal Medley | Network Operator | Routing table to include LDSO for IF-018 | Optionality matrix shows that LDSOs can additionally receive Event Codes [AddressChg], [GSPChg] and [DUOSTariffIDChg]. LDSO to be added to IF-018 secondary routing for these three event codes in DES138 |  | Implemented | No |  | Design ambiguous |  |  | Interim Release 5.2 |  |  | Interim Release 5.2 |  | DES-138 updated routing table for IF-018 updated to include LDSO for Event Codes [AddressChg], [GSPChg] and [DUOSTariffIDChg]. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-842 | MH |  | 2023-12-06 | St Clements | 22462 | Tom Perryman | Software Provider | REP901, Common Block and Compression | Other REPs have the DIP Distribution Pattern and Report Format defined. This is not the case for the REP900 and REP901 Other REPs have the Routing Rules defined. This is not the case for the REP900 and REP901 |  | Implemented | No |  | Design gap |  |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | For REP-900 and REP-901 Add Distribution Pattern: A Add report format: JSON Add routing rules. Updated schema for Swagger to include compressed schema information as per other ECS reports. | Data interface correction | Supporting Docs | Interfaces | ESC Report, Swagger
MHHS-DIN-843 | RG | DIN-835,836, 882 | 2023-12-07 | SRO |  | Rob Golding | SRO | Add RCP0000 to DES138 and Swagger as a valid a response code | A 'success'response code is required for MPs to provide a valid L3 response. |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | RCP0000 added to DES138 and Swagger as a valid a response code. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-844 | BK |  | 2023-12-07 | Large Suppliers |  | Graham Wood, Haz Elmamoun | Supplier | Standardisation of Interfaces within the Smart Data Services | This CR seeks to avoid cost and inconsistency in the design by adding OPTIONAL standardised messages to support the Meter Data Retriever SDS sub-role. Parties would be able to choose to implement this or come to bilateral arrangements as currently designed. Standardisation can be achieved by adding additional routing to current DIP messages and creating variants of existing messages. | CR023 | Implemented | No |  | Change Request |  |  | Interim Release 7 |  |  | Interim Release 7 |  | Updated Business Requirements for parties (SDS/MDR) wishing to take advantage of the standard messages (BRS017) Updated Business Process Diagram (BP017) Updated Message Structures in DES-138 for IF-061, 062, 063, 064, 065. Updated Swagger to align with DES-138 and add new Interfaces. Updated E2E Solution Architect Document | Data interface correction | Supporting Docs | Interfaces | MHHSP-BP017- Optional SDS MDR Standard Interactions BRS017 DES138 Swagger E2E001 Architecture Document
MHHS-DIN-845 | MH |  | 2023-12-12 | St Clements | 24142 | Tom Perryman | Software Provider | REP900 “List of MPANs” field should be mandatory | The REP900 “List of MPANs” field. It is currently optional in the REP900, and should be mandatory. We also believe that Zero should be added as a chargeType. |  | Implemented | No |  | Design gap |  |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | REP900 Changes DI-566 ‘List of MPANs on Site’ to be made a mandatory field to enable receivers of the REP900 to correctly identify the MPANs associated to a site. The population of this field is essential to allow the supplier to know what MPANs the DUoS invoice relates to, enabling them to validate the invoice Update to the possible values for DI-596 ‘Charge Type’ to include ZERO, and format all possible values to CAPS. Additional chargeType values have been added to DI-596 in both DES-138 and Swagger. | Data interface correction | Supporting Docs | Interfaces | ECS Report
MHHS-DIN-847 | MF |  | 2023-12-14 |  |  | Madison Layton | Software Provider | Add error code for IF-025 to validate if Null is provided and value is already Null | MPRS needs a level 5 validation rule to enable MPRS to reject the PUB-025 in the following cases: IHD null when there is no active IHD install status held to end date SMSO null when there is no active SMSO held to end date PC null and PC EFD not null, when there is no active PC held to end date SSC null and SSC EFD not null, where there is no active SSC held to end date |  | Implemented | No |  | Design gap | SCS |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Added REG0009 - Null Value cannot be set as Value held is already Null. Added validation rules to enable MPRS to reject the PUB-025 using REG0009 in the following cases: IHD null when there is no active IHD install status held to end date SMSO null when there is no active SMSO held to end date PC null and PC EFD not null, when there is no active PC held to end date SSC null and SSC EFD not null, where there is no active SSC held to end date | Data interface correction | Supporting Docs | Interfaces | DES-138
MHHS-DIN-848 | MF |  | 2023-12-14 |  |  | Madison Layton | Software Provider | Clarification on SP de-appointment effective from date in the case of Atomic Secured Active | In rare scenario's Atomic Secured Active messages could result in an Effective To-date which is before the Effective From Date of the Service Provider Appointment 1. Supplier A active at MPAN 2. CSP received for DS with EFD 8th December 3. CSP gets confirmed 4. MPRS receives an Atomic Secured Active for Supplier B (Atomic means there was no Pending notification) on 13th December with SSD 8th December (or earlier) 5. MPRS must de-appoint the DS with ETD = SSD – 1, in this scenario ETD = 7th December |  | Implemented | No |  | Clarification - No change required | SCS, Service Providers, Suppliers |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Added clarification to IF-037 notes that In rare scenario's Atomic Secured Active messages could result in an Effective To-date which is equal to the Effective From Date of the Service Provider Appointment. And as such the appointment will be deemed as having never taken effect | Data interface correction | Supporting Docs | Interfaces | DES-138
MHHS-DIN-846 | SW |  | 2023-12-13 |  | 24874 | Chris Mingay | Software Provider | B050 consumptionComponentClassID property inconsistency between ECS reports catalogue and Swagger | B050 consumptionComponentClassID property inconsistency between ECS reports catalogue and Swagger. In the ECS reports catalogue, in IR2 and IR5 this is an INT3, min 100 and max 999. This was correct in Swagger 1.2, but in Swagger 1.5, this has reverted to a String3 with min / max values of 3, so does not align to ECS reports catalogue. |  | Implemented | No |  | Design misaligned |  |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Update Swagger to align with ECS reports catalogue for B050 consumptionComponentClassID to be an Integer. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-849 | MF |  | 2023-12-14 |  |  | Madison Layton | Software Provider | Change B099 to be a single block rather than a list in IF-035 | In IF035 SDS-MDROutcome variant, make B099 a single block in the swagger rather than a list. |  | Implemented | No |  | Error/Correction | SCS, Service Providers, Suppliers, DIP |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | Swagger updated so that for IF035 SDS-MDROutcome variant, B099 is a single block in the swagger rather than a list. | Data interface correction | Supporting Docs | Interfaces | Swagger DES-138
MHHS-DIN-850 | MH |  | 2023-12-14 |  |  | Matt Hall | SI Design | CR36 - Clock Time Reads and Appointments | Implementation of the Design Changes required to support CR36 | CR036 | Implemented | No |  | Change Request | All Participants |  | Interim Release 7 |  |  | Interim Release 7 |  | Update the artefacts as per CR36 | Data interface correction | Supporting Docs | Various documents | BP003, BP003C, DES138, BRS001, BRS003, METH005, METH007
MHHS-DIN-851 | MH |  | 2023-12-14 |  | 25624/33640 | Sarah Jones | Central Body | Outstanding Queries to Support Interface Code Drafting | Update the data catalogue in DES-138 to show the correct data types and data type descriptions |  | Closed | No |  | Clarification - No change required | All Participants | [6 empty] | Closed as specific DIN's now raised. | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-852 | MH |  | 2023-12-14 |  | 21890 | Mike Ceney | Central Body | ECS Report 006 | Within block R003- CCC Determined Data, the Domestic Premise Indicator (DI-030) is to be populated, I believe this to be incorrect and needs to be removed from the report. This data item is populated at an Mpan level but this report is at BMU level so therefore cannot be populated |  | Implemented | No |  | Error/Correction | Helix, Suppliers |  | Interim Release 7 | 2024-01-19 |  | Interim Release 7 | 2024-01-19 | Remove Domestic Premise Indicator from REP 006 | Data interface correction | Supporting Docs | Interfaces | MHHSP - ERI011B - ECS Reports - External
MHHS-DIN-853 | SB |  | 2023-12-14 |  |  |  | SRO Design Team | Addition of new RetroSpective Date Validation Rules following DRG Review & Sign Off | Amended IF-025 Validation rules for SSC& Profile Class Eff From Date to include Migration Date per reviewed & agreed RetroDates PPT. No changes rquired to any other data items as a result of RetroDates Functionality. |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7 | 2024-01-19 |  | Interim Release 7 | 2024-01-19 | Amended IF-025 Validation rules for SSC& Profile Class Eff From Date to include Migration Date in DES138. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-854 | SW |  | 2023-12-15 | IMServ | 24832 | Liam Lowey | Software Provider | DI-085 GUID definition | DI-085 GUID definition does not align with Industry definition of a GUID ie, 8 HEX, 4x3 HEX, then 12 HEX, but rather, this refers to an SME GUID that is not a true GUID but rather a EUI base 64 address, akin to an IP v6 address. Need to update the example so that DI-085 provides clarity on whether HEX values are included. |  | Implemented | No |  | Design ambiguous |  |  | Interim Release 7 |  |  | Interim Release 7 |  | Update example in the DI-085 property to align with a EUI base 64 address, akin to an IP v6 address. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-855 | SW |  | 2023-12-15 | Callisto | 24828 | Neil Edney | Software Provider | Swagger required properties are not aligned with Swagger property names | There are a number of blocks where the Swagger required properties are not aligned with Swagger property names which will cause a schema validation error incorrectly. B051 - GPSGroupID and domesticPremiseIndicator - properties and required properties do not align. B014 - incomingMeteringServiceEffectiveDate and incomingMeteringServiceDIPEffectiveFromDate - properties and required properties do not align. B021 - customerDirectContractDataServiceEffectiveDIPID and customerDirectContractDataServiceDIPID - properties and required properties do not align. |  | Closed | No |  | Design misaligned
MHHS-DIN-856 | PP | ADO Defect 19010 | 2023-12-15 | Programme |  | Paul Pettitt | SI Design | DI-020 example incorrect Length | DI-020 Contract Reference data service has a Max length of 10 chars, the example is 11 |  | Closed | Yes | 19010 | Error/Correction | DIP Users | [6 empty] | Corrected in IR5.3 Maximum set to 50 and example is correct.
MHHS-DIN-857 | RG |  | 2023-12-18 | SRO |  | Rob Golding | SRO Design | Ensure all enumerated types have obfuscated values (where needed) (IR 5.3 Release) | Ensure all enumerated type that are obfuscated contain the obfuscated value in the enumerated list. This change affects the following: IF-035 DI-979 Response Code DI-800 Service Provider Appointment Scenario DI-838 Supplier Proposed Consent Granularity DI-126 Traditional Fall Back Read Frequency IF-036 DI-017 Consent Granularity Obfuscated DIP IDs wil be 9999999999 as the regex dictates it needs to be a 10 character numeric string |  | Implemented | Yes | 18999 | Design gap |  |  | Interim Release 5.3 |  |  | Interim Release 5.3 |  | Updated all enumerated type that are obfuscated contain the obfuscated value in the enumerated list. This change affects the following: IF-035 DI-979 Response Code DI-800 Service Provider Appointment Scenario DI-838 Supplier Proposed Consent Granularity DI-126 Traditional Fall Back Read Frequency IF-036 DI-017 Consent Granularity | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-858 | RG |  | 2023-12-18 | SRO |  | Rob Golding | SRO Design | Ensure all enumerated types have obfuscated values (where needed) (IR 7 Release) | Ensure all enumerated type that are obfuscated contain the obfuscated value in the enumerated list. This change affects the the following: IF-035 DI-979 Response Code DI-800 Service Provider Appointment Scenario DI-838 Supplier Proposed Consent Granularity DI-126 Traditional Fall Back Read Frequency IF-036 DI-017 Consent Granularity Obfuscated DIP IDs wil be 9999999999 as the regex dictates it needs to be a 10 character numeric string |  | Implemented | Yes | 18999 | Design gap |  |  | Interim Release 7 | 2024-01-19 |  | Interim Release 7 | 2024-01-19 | Ensure all enumerated type that are obfuscated contain the obfuscated value in the enumerated list. This change affects the the following: IF-035 DI-979 Response Code DI-800 Service Provider Appointment Scenario DI-838 Supplier Proposed Consent Granularity DI-126 Traditional Fall Back Read Frequency IF-036 DI-017 Consent Granularity Obfuscated DIP IDs wil be 9999999999 as the regex dictates it needs to be a 10 character numeric string | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-859 | MH |  | 2023-12-20 | St Clements | 24142 | Tom Perryman | Software Provider | REP900 invoice | Currently, the REP900 has one or many invoices for each site / invoice data (R900-05 level). This needs to be updated so that the REP900 contains one or many combinations of site and invoice data (R900-04 level). Currently a single D2021 is sent to a supplier containing all their HH invoices produced on that billing day. |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7 |  |  | Interim Release 7 |  | Correct the REP900 record hierarchy to: Clarification of the record hierarchy to enable the inclusion of multiple invoices on a single REP900 R900-01 Distributor Info - a single Distributor on a REP900 R900-02 Supplier Info - a single Supplier on a REP900 > R900-03 Site Info > R900-04 Invoice Data - one or many combinations of Site and Invoice Data >> R900-05 Invoice Lines - one or many invoice lines for each combination of Site and Invoice Data | Data interface correction | Supporting Docs | Interfaces | Swagger MHHSP - ERI011B - ECS Reports - External
MHHS-DIN-860 | RG |  | 2023-12-21 | SRO |  | Rob Golding | SRO Design | Clarification on Webhook callback responses | At present the webhook callbacks are limited in their responses to 200 & 207. The extent of the responses needs to align with the other DIP APIs |  | Implemented | Yes | 19120 | Design gap |  |  | Interim Release 5.3 |  |  | Interim Release 5.3 |  | Aligning participant systems with the DIP in terms of HTTP responses, added in a standard set of response codes to be used in the Swagger. Also described are how HTTP responses received from the DIP should be interpreted, and what HTTP responses the DIP is expecting back from participants webhooks in the E2E Architecture document. | Data interface correction | Supporting Docs | Various documents | Swagger E2E Architecture
MHHS-DIN-861 | RG |  | 2023-12-21 | SRO |  | Rob Golding | SRO Design | Clarification on Webhook callback responses | At present the webhook callbacks are limited in their responses to 200 & 207. The extent of the responses needs to align with the other DIP APIs |  | Implemented | Yes | 19120 | Design gap |  |  | Interim Release 7 |  |  | Interim Release 7 |  | Aligning participant systems with the DIP in terms of HTTP responses, added in a standard set of response codes to be used in the Swagger. Also described are how HTTP responses received from the DIP should be interpreted, and what HTTP responses the DIP is expecting back from participants webhooks in the E2E Architecture document. | Data interface correction | Supporting Docs | Various documents | Swagger E2E001 Architecture Document
MHHS-DIN-862 | RG |  | 2024-01-02 | SRO |  | Rob Golding | SRO Design | REP901 missing event code | The eventcode on REP-901 need correcting to [DUoSEmbeddedLDSOAggInvData] & [DUoSSupplierAggInvData] (or do we have two reports?) |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7 |  |  | Interim Release 7 |  | Update the following REP-901 data items as follows [DUoSEmbeddedLDSOAggInvData] & [DUoSSupplierAggInvData] to ensure that ECS reports align with naming standards and ensure that Swagger aligns with ECS reports catalogue. | Data interface correction | Supporting Docs | Interfaces | ESC Report, Swagger
MHHS-DIN-863 | SB |  | 2024-01-03 | Kraken | 27359 | Henri Naef | Software Provider | IF-019/020 Discrepancy between E2E and Swagger | It looks like in the e2e guide there’s no mention of an M1 block in the common block. However in the swagger documentation for IF019 and IF020 there is. What’s weirder is that for both of those there is no M0 block which the e2e guide says there should be." |  | Assessment Complete / Implementation Deferred | No |  |  |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update E2E solution architecture to align with Swagger/ DES138 | Data interface correction | Supporting Docs | E2E Architecture Document | E2E001 Architecture Document
MHHS-DIN-864 | ZH |  | 2024-01-08 | SJW |  | Sarah Jones | Central Body | CR024 - Update of two data items | As flagged at the last DAG and in our email on 21 Dec, RECCo believes there are two incorrect data items in the MHHS design: Manufacturer Code should be Manufacturers Make and Type CSS Registration Request Id should be CSS Registration Id. We believe failure to correct these data item in line with approved CR024 (particularly the CSS Registration Id) may lead to parties including the wrong data items within their design, impacting testing outcomes (both SIT and Qualification) and leading to operational issues post go live. | CR024 | Implemented | No |  | Error/Correction |  |  | Interim Release 7 |  |  | Interim Release 7 |  | Update the names of both data items in the Swagger and DES138, in the relevant areas. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-865 | RG |  | 2024-01-12 |  |  |  |  | EMSE ID example has non-hexadecimal chars | DES-138 and the swagger have a non-hex character in the example |  | Closed | Yes | 23294 | [8 empty] | Update example to remove leading S character
MHHS-DIN-866 | SW | DIN-880 | 2024-01-16 | Stark | 29309 | Jon Dennis | Software Provider | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7 | #REF! |  | Interim Release 7 | #REF! | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD. Swagger updated to align. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-867 | RG |  | 2024-01-16 | PDA |  | Richard French |  | Remove all references to UDS & UMDS in E2E SA doc | Replace UMDS with UMSDS - multiple instances still exist |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7 |  |  | Interim Release 7 |  | E2E documentation still contains references to UMDS - this needs to be removed and replaced with UMSDS | Data interface correction | Supporting Docs | Interfaces | E2E001 Architecture Document
MHHS-DIN-868 | RS |  | 2024-01-16 |  | 19802 | Rob Short | SI Design | Correction of Advanced Data Service Validation and Estimation (Meth002) | Following review and participant comments, multiple updates are required to correct SDS references in the ADS method statement |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7 |  |  | Interim Release 7 |  | Updates made to all sections of MHHSP-METH002_ADS_Validation_Estimation | Method statement correction | Supporting Docs | Method Statement | METH002
MHHS-DIN-869 | RS |  | 2024-01-16 |  | 19802/20645 | Rob Short | SI Design | ADS Method Alignment | Updates to the ADS estimation methods |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7 |  |  | Interim Release 7 |  | Update to section 3 of of MHHSP-METH002_ADS_Validation_Estimation | Method statement correction | Supporting Docs | Method Statement | METH002
MHHS-DIN-870 | SW |  | 2024-01-17 | St Clements | 26647 | Madison Layton | SI Design | IMS-SendMTD variant for IF-035 does not contain properties B070, B071 and B019 to align with DES-138 | IMS-SendMTD variant for IF-035 does not contain properties B070, B071 and B019 to align with DES-138 - which identifies this variant of a copy of the variants DSAppAccepted and MSAppAccepted |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7 |  |  | Interim Release 7 |  | Swagger 1.7 IF-035-IMS-SendMTD: should be updated to include B070, B071 and B019 as optional fields in this variant. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-871 | RG |  | 2024-01-17 | SRO |  | Rob Golding | SRO Design | Changes to E2E SA doc & Swagger for replay message version support | The E2E SA doc (& swagger) needs to be updated to include message version support for replay |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7 |  |  | Interim Release 7 |  | E2E SA document include a description on message versioning for message replay. This includes changes to section 4.9 and 8.5.2 of the E2E001 design document, removal of section 5.5 (it has been combined into section 4.9). Also updates to Swagger to add version in the MessageRequest object. | Technical corrrection | Supporting Docs | Interfaces | E2E001 Architecture Document Swagger
MHHS-DIN-872 | RS |  | 2024-01-18 | IMServ | 30201 | Rob Short | SI Design | Historic consumption data following the IF-015 request | Conflicting information in the NOTES section: “The structure and content of this message will be subject to further discussion as part of the 'DIP Detailed Design', as the exact way in which this requirement/functionality is realised may depend on the DIP Solution option(s) chosen. The basis of the functionality is that participants will be 'REPLAYED' facsimiles of the previously submitted IF-021 (SP Consumption Submission) / IF-013 (SP Defaulted) Records - however it may be possible that some kind of 'blended' response, as eluded to here, is also possible.” |  | Implemented |  |  | Design gap |  |  | Interim Release 7 |  |  | Interim Release 7 |  | Removal of Interface note on IF-16 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-873 | RS |  | 2024-01-19 | Elexon | 21459 | Phil Milmine | Central Body | Correction to VAS Method Statement | Amendment to section 3.28 around “VAS Defaulting” and the report linked to this process (REP-007) to reflect the manual steps that Elexon would need to take to enable this. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7 |  |  | Interim Release 7 |  | Amend text to 17. VAS Re-run where Initial VAR incomplete due to missing MDS or CDCA data 3.28 In the event that the VAS is unable to complete an Initial VAR due to missing data from MDS or CDCA, the VAS shall use replacement data at BSCCo’s discretion to re-run by BM Unit, as per a normal VAS run. Substituted data must be reported to Market Participants. | Method statement correction | Supporting Docs | Method Statement | METH006
MHHS-DIN-874 | RG | DIN-829 | 2024-01-23 |  |  | Rob Golding | SRO Design | Consent Granularity not nullable and N - no consent | Implement DIN-829 in 5.x swagger and update DES138 accordingly |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 5.4 |  |  | Interim Release 5.4 |  | Swagger/ DES138 updated so that DI-838-Supplier-Proposed-Consent-Granularity and DI-017 Consent Granularity includes N - No Consent in the list of allowable values. DI-838 updated to be Mandatory no nulls. DI-838 description updated to align with the data item name in Swagger. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-875 | SW |  | 2024-01-23 | Kraken | 31011 | Angelos Rizoyannis | SI Design | Swagger objects and descriptions are missing | Missing `type: object` - for the following blocks B079, B080, B081, B082, B083, B090, B091 - Missing `description: ...’ object for R901-08 - Incorrect description - IF-004-Payload08, IF-006-MeterRemoval.CustomBlock, IF-006-MeterExchange.CustomBlock |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Missing `type: object` - for the following blocks - B075, B076, B079, B080, B081, B082, B090, B091 - Missing `description: ...’ object for R901-08 - Incorrect description - IF-004-Payload08, IF-006-MeterRemoval.CustomBlock08, IF-006-MeterExchange.CustomBlock08 Update Swagger to fix above issues. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-876 | RG |  | 2024-01-24 | SRO |  | Rob Golding | SRO Design | IF-003 LDSO routing is secondary not always | DES138 has IF-003 LDSO routing incorrectly specified, the routing is secondary not always |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7 |  |  | Interim Release 7 |  | Update DES138, IF-003 LDSO routing is secondary not always | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-877 | RG | DIN-620 | 2024-01-24 |  |  | Rob Golding | SRO Design | IF-001 Remove EES (CR023) | DIN-620 was not fully implemented, EES is still mentioned in DES138 IF-001 |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7 |  |  | Interim Release 7 |  | EES removed DES138 IF-001 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-878 | RG | DIN-870 | 2024-01-17 | St Clements | 26647 | Madison Layton | SI Design | IMS-SendMTD variant for IF-035 does not contain properties B070, B071 and B019 to align with DES-138 | IMS-SendMTD variant for IF-035 does not contain properties B070, B071 and B019 to align with DES-138 - which identifies this variant of a copy of the variants DSAppAccepted and MSAppAccepted |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 5.4 |  |  | Interim Release 5.4 |  | Updated Swagger IF-035-IMS-SendMTD: to include B070, B071 and B019 as optional fields in this variant | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-879 | RG | DIN-849 | 2023-12-14 |  |  | Madison Layton | Software Provider | Change B099 to be a single block rather than a list in IF-035 | In IF035 SDS-MDROutcome variant, make B099 a single block in the swagger rather than a list. |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 5.4 |  |  | Interim Release 5.4 |  | Updated Swagger IF035 SDS-MDROutcome variant, and made B099 a single block rather than a list. This has also necessitated in an update to DES138 to the routing information for IF-035. | Data interface correction | Supporting Docs | Interfaces | Swagger, DES138
MHHS-DIN-880 | MF | DIN-866 | 2024-01-24 |  |  | Jon Dennis | Software Provider | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 5.4 |  |  | Interim Release 5.4 |  | Updated “MAIN” in DI-059-Meter-Type enum in swagger, to be "MAIN_" to align with ISD | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-881 | MF | DIN-825, DIN-811 | 2024-01-24 | Avanade |  | Rob Golding | SRO Design | IF-024 missing required attributes in blocks | IF024 SN-NoComms CustomBlock required B057 IF-024-SN-RemoteDisabled required B069, B057 |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 5.4 |  |  | Interim Release 5.4 |  | Update swagger with the following: IF024 SN-Vacant CustomBlock required B057 IF024 SN-NoComms CustomBlock required B057 IF024 SNRemoteEnabled CustomBlock required B057, B069 IF024 SNSupplierAC CustomBlock required B057, B058 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-882 | MF | DIN-835,836, 843 | 2024-01-24 | SRO |  | Rob Golding | SRO Design | New swagger file ErrorCodes to describe MHHS error messages and updates to error messages in DES138 | New swagger file (Response Codes schema) to capture all message and error codes from DES138 including RCP0000 (Message Success) and the following error codes: Error Code Error Text MSG1013 Invalid CertifcateIssuerName MSG1014 Certificate has expired MSG1039 Invalid MPAN MSG5001 Internal server error MSG5002 No data contained in request body MSG5003 Unable to determine correlationId requirement. Server configuration error or sender request error MSG5004 Internal server error.Payload not processed |  | Implemented |  |  | Design gap | DIP Users |  | Interim Release 5.4 |  |  | Interim Release 5.4 |  | New swagger file (Response Codes schema) to capture all message and error codes from DES138 DES138 updated with RCP0000 (Message Success) and the following error codes: Error Code Error Text MSG1013 Invalid CertifcateIssuerName MSG1014 Certificate has expired MSG1039 Invalid MPAN MSG5001 Internal server error MSG5002 No data contained in request body MSG5003 Unable to determine correlationId requirement. Server configuration error or sender request error MSG5004 Internal server error.Payload not processed | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-883 | RG |  | 2024-01-24 | SRO | 31749 | Matt McKeon | SRO Design | Data item clashes between DES138 and ECS Reports | We have noticed that there are some DI-REF numbers which have been used twice in DES138 and ERI011B. - Specifically the newer data items introduced for migration start in the 500s, when these are also used in ECS Reports. |  | Implemented |  |  | Error/Correction | ECS |  | Interim Release 7 |  |  | Interim Release 7 |  | Move duplicated ECS numbers to an unused range | Reporting correction | Supporting Docs | ECS Reports | ERI011B
MHHS-DIN-884 | BK |  | 2024-01-26 | SRO |  | Kevin Spencer | SRO Design | CR032: Replacement of REP080 to use the P210 | The revised design would require: Elexon revise the build of the P0210 to include both non-migrated and migrated consumption. The format and structure will not change. The ESO ingest the P0210, ensuring that its integration and middleware systems can process the file. As per the the integration and middleware diagram, two systems (LIMS and CIS/MFT) will need configuration changes. The ESO regression test its Revenue systems based on the revised P0210 to ensure it continues to meet the requirements for TNUoS and BSUoS reporting. After the end of the Transition Period, if the ELEX-REP-080 report was developed, the existing P0210 file and associated processing of that file would become redundant. | CR032 | Implemented |  |  | Change Request |  |  | Interim Release 7 |  |  | Interim Release 7 |  | Updates made to the following artefacts; Amended METH006 section 3.7 Removal of REP080 in the ECS Report Update wording in BP020 step 75 to reference the P0210 and subsequent BPD doc | Data interface correction | Supporting Docs | Interfaces | METH006 ESC Report BP020 and BPD020
MHHS-DIN-885 | BK |  | 2024-01-26 | SRO |  | Matt McKeon | SRO Design | Add URLs pointing to new DTC format definition documents in ERI011B | Update four tabs of ERI011B to add a URL pointing to new DTC format definition documents for these reports |  | Implemented | [5 empty] | Interim Release 7 |  |  | Interim Release 7 |  | Update MHHS-REP-D0369 to say ‘Defined in DTC format as D0401 at: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx · Update MHHS-REP-D0370 to say ‘Defined in DTC format as D0402 at: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx · Update MHHS-REP-D0373 to say ‘Defined in DTC format as D0403 at: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx · Update MHHS-REP-D0374 to say ‘Defined in DTC format as D0404 at: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx Grey out all the reports specified above | Reporting correction | Supporting Docs | Interfaces | ERI011B
MHHS-DIN-886 | MF |  | 2024-01-26 | St Clements |  | SCS | Software Provider | Addition of 905 existing meter listing block to all events in IF-006 | Add B905 (existing meter listing) block for all IF-006 event codes in Swagger |  | Implemented | [5 empty] | Interim Release 7 |  |  | Interim Release 7 |  | Add B905 (existing meter listing) block for all IF-006 event codes in Swagger | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-887 | MF |  | 2024-01-26 | St Clements |  | SCS | Software Provider | Addition of 905 existing meter listing block to all events in IF-006 | Add B905 (existing meter listing) block for all IF-006 event codes in Swagger |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 5.4 |  |  | Interim Release 5.4 |  | Add B905 (existing meter listing) block for all IF-006 event codes in Swagger | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-888 | SW |  | 2024-01-29 | Kraken |  | Angelos Rizoyannis | Software Provider | Property "type: object" missing from IF-024 variants in Swagger | Property "type: object" missing from IF-024 variants in Swagger. This needs to be added to all variants where this is missing. |  | Implemented | [5 empty] | Interim Release 7 |  |  | Interim Release 7 |  | Property "type: object" missing from IF-024 variants in Swagger. This needs to be added to all variants where this is missing. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-889 | SW |  | 2024-01-29 | Kraken |  | Angelos Rizoyannis | Software Provider | Property "type: object" missing from IF-024 variants in Swagger | Property "type: object" missing from IF-024 variants in Swagger. This needs to be added to all variants where this is missing. |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 5.4 |  |  | Interim Release 5.4 |  | Property "type: object" missing from IF-024 variants in Swagger. This needs to be added to all variants where this is missing. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-890 | RS |  | 2024-01-29 | CGI |  | Dave Webster | Software Provider | DI-038 (LInked Import/Export Mpan) description | Confusion over wording in DI-038. Where more than one import MPAN exists, this shall be populated with the Primary Import MPAN |  | Implemented | [5 empty] | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Remove wording 'Where more than one import MPAN exists, this shall be populated with the Primary Import MPAN' from all DI-038 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-891 | SB |  | 2024-01-30 | St Clements | 21513 | SCS | Software Provider | DI-241 - SUPC routing on IF-037 incorrect, should be SUPS | The primary routing for MSDeAppUpdate and DSDeAppUpdate is incorrect, XMSC and XDSC is the currently appoint SP but the flow needs to go to the already de-appointed SPs |  | Implemented | [5 empty] | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Update Primary Routing to show Previously de-appointed Data Service/ Metering Service | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-892 | RG |  | 2024-01-31 | RDG |  | RDG | SRO | Message Versioning Support: Create DIPMessage variant for egress | Split DipMessage in two, one for ingress (current version) and another for egress (new) in order to support multiversion messages on egress for replay/requeue |  | Implemented | [5 empty] | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Add new DIPEgressMessage to the swagger in order to split the incoming and outgoing APIs to allow multiversion support | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-893 | RG |  | 2024-01-31 | BJSS |  | Soniya | Software Provider | Regex for GSP Correction factor | We want to check if the regex is correct for GSP Group Correction Factors: ^-?\d{1,9}\.\d{9} The highlighted section suggests the – is optional but GCFs are always positive. Can the regex be updated to reflect this? |  | Implemented | [5 empty] | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Regex update in Swagger to enforce only positive numbers. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-894 | RG |  | 2024-01-31 | SIMs & Ems |  | John | Software Provider | DI-123-SSC is nullable in IR7, needs to be the same in IR5.x | B032 eg on IF-002 has property SSC which was made non nullable in 1.5.2 or 1.5.3 has been left nullable in 1.7 |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 5.4 |  |  | Interim Release 5.4 |  | Update B032 eg on IF-002 has property SSC so that it is non nullable | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-895 | MH |  | 2024-02-01 | St Clements | 31597 | Virginia Patey | Software Provider | REP002s vs IF-21s for DUoS Billing. Follow up from DIN340 | Change required to MDS Method Statement... DIN-340 was raised by UKPN to highlight the fact that while DNOs were to receive the correct IF-021 data, the data on the DUoS Report would also include meter data for most MPANs with a connection type <> ‘W’. Additionally, given the fact that the DNOs require meter data for all sites via either the REP002s or the IF-021s, using different data items to determine the inclusion or exclusion from a particular delivery method risks DNOs not receiving data for some MPANs via either route and thereby negatively impacting their invoicing. Please note that an MS Site Specific LLF Id indicator of ‘B’ (Site Specific Import) or ‘D’ (Site Specific Export) does NOT equate to a connection type <> ‘W’. In fact the MPANs with a MS Site Specific Indicator of ‘B’ or ‘D’ is a very small subset of those with a connection type <> ‘W’. For the avoidance of doubt, the use of the term ‘site specific’ for billing types and MS Site Specific LLF Id indicators are separate things and do not equate to one another. Required Solution: We require the rules for what should be included on the DUoS Report (i.e. the wording for 17.3) to be changed to: The DUoS Report calculations shall only be undertaken for SPC data that is for MPANs with a connection type = ‘W’ 17.4 is not required as DNOs should be using all IF-021 in site specific billing. |  | Implemented | No |  | Error/Correction | ECS, DNOs |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Rules for what should be included on the DUoS Report (i.e. the wording for 17.3) to be changed to: The DUoS Report calculations shall only be undertaken for SPC data that is for MPANs with a connection type = ‘W’ 17.4 is not required as DNOs should be using all IF-021 in site specific billing. | Method statement correction | Supporting Docs | Method Statement | METH007 ERI011B - ECS Reports
MHHS-DIN-896 | MH |  | 2024-02-06 | ESG | 32706 | Patricia Parker | Software Provider | ISD v5.5 (Ref 265) | The two new entities M20 & M21 (DIN-754) do not appear in the table of contents. Can these be added? |  | Implemented | No |  | Error/Correction |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Update the table of contents to include two new entities M20 & M21 (from DIN-754). | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-897 | RG |  | 2024-02-06 | Flui | 32997 | Jason Jackson | Software Provider | IF-001 Change Of Supplier s0 block needs to mandatory | s0 block needs to mandatory, DIN-785 missed off the S0 block, ok in 5.4 not 7. the A0 block is marked as mandatory, it should be S0. (the orignial published DIN stated this was the S1 block, this is an error, in fact it should be the s0 block) |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Minor swagger update to enforce a manadatory field | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-898 | MH |  | 2024-02-07 | Elexon | 31846 | Derek Weaving | Central Body | REP-003 fields - Clarification Request | DI-339 BM Unit Allocated Demand Disconnection Volume Losses should not be in the REP003 The DDE does not calculate losses separately and they are already included in DI-341 volume that sums across all CCCids including the ones for losses. |  | Implemented | No |  | Error/Correction | Suppliers |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Remove DI-339 and the DI-370 from the REP-003 Swagger update and ECS Report | Technical corrrection | Supporting Docs | Interfaces | Swagger ERI011B - ECS Reports
MHHS-DIN-899 | MH |  | 2024-02-07 | Elexon | 32697 | Rashmi Radhakrishnan | Central Body | IR7 Changes to ISD | In IR7, DIN-759 included an update to ISD Entitiy M17. tHis update was only partially completed. This DIN is to correct it and to add Meter Group to the Entity and also to add N to M15 as previously agreed |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Add Meter Group to the Entity - M17 Add N - No Consent to M15 | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-900 | RG |  | 2024-02-07 | SRO Design |  | RG | SRO Design | IR7 E2E SA Obfuscation rules require updating | Data items that are MPIDs need to be obfuscated to 'XXXX' rather than 'xxxx' so the regex remains unbroken |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | MPIDs that are obfuscated will be 'XXXX'. Avanade change, PPs need to be aware. | Technical corrrection | Supporting Docs | Interfaces | E2E Architecture
MHHS-DIN-901 | RG |  | 2024-02-08 | SRO Design |  | RG | SRO Design | DES138 does not include CR23 opting in for MDRs | The IR7 version of DES138 does not include the 'opting' information for MDRs. The following needs to be icluded as opted in PUB-006 [MeterInstall], [MeterRemove], [MeterExchange], [MeterUpdate] PUB-008 [EnergisationStatusChange] PUB-026 [ConsentGranularity], [SMSO], PUB-024 [SN-RemoteEnable], [SN-RemoteDisable], [SN-NoComms] |  | Implemented | No |  | Design gap |  |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Update DES138 to include the 'opting' information for MDRs in the following PUBS; PUB-006 [MeterInstall], [MeterRemove], [MeterExchange], [MeterUpdate] PUB-008 [EnergisationStatusChange] PUB-026 [ConsentGranularity], [SMSO], PUB-024 [SN-RemoteEnable], [SN-RemoteDisable], [SN-NoComms] | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-902 | MH |  | 2024-02-09 | SRO | 33170 | Andrew Margan | Central Body | Reverse Migration Consistency | Step 190 of MHHS-DEL971 - BPD001 and DEL965 BPM001 - Change Of Supply - Reverse Migration suggest the incoming supplier has a choice of whether to reverse migrate or not. This isn't the case; a reverse migration will only happen where the incoming supplier is not qualified on the MHHS TOM |  | Closed | No |  | Error/Correction |  |  |  | #REF! |  |  | #REF! | The Process step is showing the Incoming Supplier choosing whether to start reverse migration or not. In this scenario, the Incoming Supplier is not MHHS qualified. However, they will have to determine if it is a reverse migration scenario based on the info in the D0260/D0217. In that respect they must choose whether they need to follow reverse migration or legacy process
MHHS-DIN-903 | MF |  | 2024-02-12 | Elexon | 34297, 34973 | Raina Jain | Central Body | Missing/ incorrect BPD011 step | Step 211 is missing from “(BP011A) MHHSP-BPD-011” tab in MHHSP-BPD011 - Change of Con Type or Market Segment document." Correct step 275 to show that this applies for successful meter exchanges |  | Assessment Complete / Implementation Deferred | No |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Add step 211 to BPD011 to align with BP011. This shows the Metering Service receiving the Appointment Response (PUB-035) from Registration Service. Update step 275 to show that this applies for successful meter exchanges | Process Model correction | Supporting Docs | Business Process Description | BPD011
MHHS-DIN-904 | RG | DIN-924 | 2024-02-12 | SRO |  | Rob Golding | SRO Design | Missing parameters in webhook callback | The definition in the webhook callback in swagger is missing the definition - $ref: '#/components/parameters/CommonSignatureHeader' - $ref: '#/components/parameters/CommonSignatureDateHeader' - $ref: '#/components/parameters/CommonSHA256Header' - $ref: '#/components/parameters/CommonSignatureCertifcateHeader' |  | Implemented | No |  | Clarification - No change required |  |  | Interim Release 5.5 |  |  | Interim Release 5.5 |  | Update to swagger to include missing parameters; aligns with CoCo | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-905 | RG | DIN-864 | 2024-02-14 | SRO |  | Rob Golding | SRO Design | B033 block meterManufacturer IR7 | B033 block meterManufacturer was renamed to manufacturersMakeAndType it wasn't renamed in the 'required' properties |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Update B003 requried fields to include manufacturersMakeAndType | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-906 | RG | DIN-925 | 2024-02-14 | SRO Design |  | Rob Golding | SRO Design | Add MPO Encrypted header parameter to callback | Add a parameter to the callback so that the MTLS cert can be authenticated by the MTLS connection. No impact on MPs, Avanade improving the secuirty handshake on the callback |  | Implemented | No |  | Design gap | Avanade |  | Interim Release 5.5 |  |  | Interim Release 5.5 |  | Add MPO Encrypted header parameter to callback | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-907 | RG | DIN-926 | 2024-02-14 | SRO Design |  | Grant Sutcliffe | Avanade | Response codes on delete operations | Standardise response message for successful delete operations on API calls -204 needs to have the text 'No Content' . Need to add other response codes in-line with the other APIs |  | Implemented | No |  | Design misaligned |  |  | Interim Release 5.5 |  |  | Interim Release 5.5 |  | Standardise response message for successful delete operations on API calls -204 needs to have the text 'No Content' . Need to add other response codes in-line with the other APIs | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-908 | MF | DI-249 | 2024-02-15 | St Clements |  | Madison Layton | Software Provider | Validation of Appointment start times | Move REG1032 from Migration Only Validation Rules to BAU Validation Rules section in IF-031 |  | Implemented | No |  | Error/Correction |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Move REG1032 from Migration Only Validation Rules to BAU Validation Rules section in IF-031 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-909 | RS |  | 2024-02-15 | EDW | 34934 | Darren Kay | Software Provider | Duplicate requirement reference used in MHHS-E2E002 Requirements v3.1 document | E2E1009 requirement reference is used for Level 4 Processing Times (Asynchronous) and Unplanned Outages in MHHS-E2E002 Requirements v3.1 document. Adjustment required to one of the references |  | Implemented | No |  | Error/Correction |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Remove duplicate reference to requirement in E2E002 doc. | Requirement correction | Supporting Docs | Requirement correction | E2E002 Requirements
MHHS-DIN-910 | MF |  | 2024-02-16 | SRO Design |  | Mike Fensome | SRO Design | Remove sending of IF-041 for invalid meter readings from SDS method statement | SDS Method Statement 2.37 refers to SDS sending an IF-041 where reads are invalid. This is not allowed for in the design and should be removed |  | Implemented | No |  | Error/Correction |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Remove sending of IF-041 for invalid meter readings from SDS method statement | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-911 | MF | DIN-849 | 2024-02-16 | St Clements |  | Madison Layton | Software Provider | Update B099 block to show that it is not an array | Update B099 block (IF-035) in DES138 to align with swagger to show that it is not an array |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Updated B099 block (IF-035) in DES138 to show that it is not an array | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-912 | RG |  | 2024-06-15 | SRO Design |  | Rob Golding | SRO Design | Incorrect 1.7 reference in 1.5.4 swagger | There was a reference to a 1.7 object from 1.5.4. module which meant the 1.5.4. swagger wasaa not resolving correctly |  | Implemented | No |  | Error/Correction |  |  | Interim Release 5.4 |  |  | Interim Release 5.4 |  | Swagger rebuilt | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-913 | SB | DIN-503 DIN-780 | 2024-02-14 | St Clements | 19885 | Madison Layton | Software Provider | Missed Update to DES138 | There was a change in swagger in IR4 for senderUniqueReference and transactionID under DIN503. However this wasn’t folded into the Interface Catalogue examples. The examples should have been removed from The DES138 Examples as DIN-780 these still appear in the Interface catalogue |  | Implemented | No |  | Clarification - No change required |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Examples against senderUniqueReference and transactionID will be removed from DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-914 | MF |  | 2024-02-19 | EDW |  | Darshun Chauhan | Software Provider | Update DI-082 (Settlement Period Effective to Date/Time) validation rule on IF-021 | Align DI-082 validation rule to check for periods ending on the hour or half-hour to align with MDS requirements |  | Implemented | No |  | Error/Correction |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Update DI-082 (Settlement Period Effective to Date/Time) validation rule on IF-021 to check for periods ending on the hour or half-hour to align with MDS requirements/ build | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-915 | RG | DIN-801, DIN-852 | 2024-02-19 | BJSS |  | Soniya Jakhu | Software Provider | Missing swagger updates to align with DIN-801 - ECS reports REP006 | 1. DIN-801 updates not communicated - Add Supplier R015 block to REP006 2. DI-375 needs to be nullable 3. DI-364 needs to be nullable 4. DIN-852 Updates not communicated to Swagger REP-006 - R003 block |  | Implemented | No |  |  |  |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Update Swagger to 1. Add Supplier R015 block to REP006 2. DI-375 needs to be nullable 3. DI-364 needs to be nullable 4. REP-006 - R003 block | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-916 | MH |  | 2024-02-21 | Elexon | 35702 | Mike Ceney | Central Body | IF-36 Obfuscation | In the IF-036 flow it states that DI-800 Service Provider Appointment Scenario is obfuscated for MDS, can you please clarify why this is the case. MDS needs this information to determine if this is for Migration (CoA or CoS lead), or a general CoA, it treats the interface differently based on the scenario |  | Implemented | No |  | Design gap | Avanade, Helix |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Removed the obfuscation of DI-800 in Blocks B014 and B015 in IF-36 | Data interface correction | Supporting Docs | Interfaces | DES138 & Avanade change
MHHS-DIN-917 | RS |  | 2024-02-22 | Callisto | 31823 36576 | Seth Chapman | Data Service Provider | Reverse Migration Process - Missing D0148 | In the reverse migration scenario there is a variation to the standard legacy process in that the D0148 groups for the old agent (271 to DC And 274 to MOP) would include the MHHS services rather than a previous "current world" agent. The documents also do not mention that the new supplier will also appoint a DA |  | Closed |  |  | Design gap |  |  |  | #REF! |  |  | #REF! | Migration Design Document (DEL961) updated to include the D0148 for the new DC, DA and MOP. Discussion required on if the old agent/service should be included as Participant believes it could be a bigger change to not include Following review, a CR would be required to make additional amendments to the existing D0148 to include old agents, response provided back to initiator | Process Model correction | Supporting Docs | Supporting document | DEL961
MHHS-DIN-918 | RG |  | 2024-02-22 | SRO Design |  | Rob Golding | SRO Design | DES-138 IF_LIST table incomplete | IF_LIST tab does not include all the MDR interfaces |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Add interfaces IF-061, IF-062, IF-063, IF-064, IF-065 to Interface List in DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-919 | RS | DIN 247, DIN 434 | 2024-02-22 | IMServ | 35161 | Bevis Rotherham | Software Provider | Reverse Migration - IF003 missing supplier fields | The MHHS-DEL961 - Migration Design Document states that IF-003 will be updated to include RevMig Incoming Supplier MPID and RevMig Incoming Supplier Effective From Date fields, however, even in the latest IR7 DES138 document these fields do not exist. There was DIN-247 which specifically referenced these fields and the Business Rules and this was closed as supposedly captured as part of DIN-434, however, DIN-434 doesn't show these fields being implemented, and the latest DES138 doesn’t show these fields against the IF-003. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Added B002 block to DES138 IF-003 to provide the Incoming Supplier DIP ID, MPID and Effective From Date on a Reverse Migration de-appointment. Note, all Suppliers will need to be allocated a DIP ID in advance of migration. Required fields in swagger equire update to align with DES-138 | Data interface and Swagger correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-920 | RS |  | 2024-02-22 | SCS | 36031 | Daniel Tadecicco | Central Body | DI-250 IF-007 Migration Rejection Code | Currently, the IF-007 can only be rejected using Level 4, MPRS other IFs use a reusable function to apply Migration rules with level 5 validation. We would like to use this function for the IF-007, using the current level 4 rejection would require a specific function for the IF-007 which would not be as maintainable and possibly confusing for receiving parties. |  | Implemented |  |  | Design gap | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Added new validation REG9002 to IF-007 to reject if Reverse Migration is in progress | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-921 | RG | DIN-913 | 2024-02-22 | IMServ |  | Liam Lowey | Software Provider | DES138 - Sender Unique reference example is incorrect | The example sender Unique reference on the DIP_COMMON tab does not contain the full interface id in the string |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | The senderUniqueReference example removed from DIP Common as per DIN 913 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-922 | RG |  | 2024-02-22 | BJSS |  | Sergio Gomes | Software Provider | IF-014 CustomBlock Required list needs updating | Needs to align with properties, should be B900 not B900List |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Required properties should be B900 not B900List only wrong in v7, not v5.4) | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-923 | MF |  | 2024-02-23 | PDA |  | Richard French | Data Service Provider | Clarification on Data Service sending consumption data for periods 47/48 during BST | Clarification around who should send consumption data for settlement periods 47 and 48 in the case of New Connections, Migration and who will receive the IF-013 where no data is provided for HH47 and HH48 during BST |  | Implemented |  |  | Design misaligned |  |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | In the case where no previous Data Service exists following a Change of Data Service ( eg New Connection, Migration) , in BST the responsibility for providing the initial hour of consuption data for Settlement periods 47 and 48 sits with the newly Appointed Data Service. Note the IF-036 notifies whether there is a previous Data Service via Block B005. The Data Service should estimate these periods in line with the relevant Method Statement. The Incoming Data Service will be notified of default data via the IF-013 if no data is submitted for Settlement Periods 47 and 48. However, the Incoming Data Service is not expected to provide data for these two settlement periods where a previous Data Service exists. Minor amendment to IF-021 validation rule to allow the incoming Data Service to send IF-021 for periods 47 and 48 where no previous Data Service exists | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-924 | RG | DIN-904 | 2024-02-12 | SRO |  | Rob Golding | SRO Design | Missing parameters in webhook callback | The definition in the webhook callback in swagger is missing the definition - $ref: '#/components/parameters/CommonSignatureHeader' - $ref: '#/components/parameters/CommonSignatureDateHeader' - $ref: '#/components/parameters/CommonSHA256Header' - $ref: '#/components/parameters/CommonSignatureCertifcateHeader' |  | Implemented | No |  | Clarification - No change required |  |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Update to swagger to include missing parameters; aligns with CoCo | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-925 | RG | DIN-906 | 2024-02-14 | SRO Design |  | Rob Golding | SRO Design | Add MPO Encrypted header parameter to callback | Add a parameter to the callback so that the MTLS cert can be authenticated by the MTLS connection. No impact on MPs, Avanade improving the secuirty handshake on the callback |  | Implemented | No |  | Design gap | Avanade |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Add extra parameter the webhook callback. No impact on PPs | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-926 | RG | DIN-907 | 2024-02-14 | SRO Design |  | Grant Sutcliffe | Avanade | Response codes on delete operations | Standardise response message for successful delete operations on API calls -204 needs to have the text 'No Content' . Need to add other response codes in-line with the other APIs |  | Implemented | No |  | Design misaligned |  |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Swagger update to include response body on codes where they are expected. Awating details. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-927 | RG | DIN-928 | 2024-02-23 | SRO Design |  | Jon Dennis | Stark | IF-037 mandatory block for [DS¦MS]DeAppUpdate event codes | the B010/B011 blocks are mandatory for the [DS¦MS]DeAppUpdate event codes. |  | Implemented |  |  | Design misaligned |  |  | Interim Release 5.5 |  |  | Interim Release 5.5 |  | Update swagger to include required blocks for IF-037 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-928 | RG | DIN-927 | 2024-02-23 | SRO Design |  | Jon Dennis | Stark | IF-037 mandatory block for [DS¦MS]DeAppUpdate event codes | the B010/B011 blocks are mandatory for the [DS¦MS]DeAppUpdate event codes. |  | Implemented |  |  | Design misaligned |  |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Update swagger to include required blocks for IF-037 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-929 | BK |  | 2024-02-23 | UKPN |  | David Yeoman | Network Operator | Change to NFR E2E1009 for DNO & IDNO roles (LDSO, UMSO, Registrations) | The programme has specified several Non-Functional Requirements that market participants must adhere to. Specifically, E2E1009 states: All Services shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes: - up to average hourly volume, mean response time of 6s or less - up to average hourly volume, 90th percentile response time of 12s or less - from average hourly to peak hourly volume, mean response time of 10s or less - from average hourly to peak hourly volume, 90th percentile response time of 16s or less DNOs and iDNO’s intend to use a ‘DIP Adaptor’ to facilitate interfacing to the DIP. The DIP adaptor provides Level 3 validation. Each ‘back office’ system that connects to the DIP Adaptor under each of the 3 DNO and iDNO roles of, Registration Services, UMSO & LDSO is expected to perform Level 4 validation. These DNO and iDNO systems cannot provide the requested Level 4 technical validation responses within 6, 10, 12 or 16 seconds as detailed in E2E1009. | CR040 | Implemented |  |  | Change Request | iDNOs, DNOs |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | The change being proposed is that all DNO and iDNO roles and systems are not required to meet the current specified asynchronous response timeframes of E2E1009 NFR. We request the description for E2E1009 be updated to read: All roles under DNO and iDNOs, namely Registration Services, UMSO & LDSO shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes - 60 minutes or less. This should exclude IF-021 for which there is a separate NFR due to the anticipated volumes. This will ensure alignment with the Operational Choreography " | Technical corrrection | Supporting Docs | Interfaces | E2E002 - Requirements
MHHS-DIN-930 | RG | MHHS-DIN-931 | 2024-02-26 |  |  | Rob Golding | SRO Design | Clarification of response codes that need an associated response body in Swagger | Design need to catch up with implementaton and the 400 response needs a response body for /dip-channel/{id} API |  | Implemented |  |  | Design gap |  |  | Interim Release 5.5 |  |  | Interim Release 5.5 |  | StandardResponse is included for: 201 - StandardResponse includes an array of StandardResponseBodyType 207 - StandardResponse includes an array of StandardResponseBodyType 400 - if the response is generated by APIM. It has a single StandardResponseBodyType contained in the StandardResponse. (APIM does not deal with individual payloads contained in a request). If the response is generated inside the DIP (L1 errors), an array of StandardResponseBodyType will be returned in the StandardResponse - one for each payload in the request. Responses for all other Status Codes do not contain StandardResponse. | Technical corrrection | Supporting Docs | Interfaces | Swagger, possibly E2E
MHHS-DIN-931 | RG | MHHS-DIN-930 | 2024-02-26 | SRO Design |  | Rob Golding | SRO Design | Clarification of response codes that need an associated response body in Swagger | Design need to catch up with implementaton and the 400 response needs a response body for /dip-channel/{id} API |  | Implemented |  |  | Design gap |  |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | StandardResponse is included for: 201 - StandardResponse includes an array of StandardResponseBodyType 207 - StandardResponse includes an array of StandardResponseBodyType 400 - if the response is generated by APIM. It has a single StandardResponseBodyType contained in the StandardResponse. (APIM does not deal with individual payloads contained in a request). If the response is generated inside the DIP (L1 errors), an array of StandardResponseBodyType will be returned in the StandardResponse - one for each payload in the request. Responses for all other Status Codes do not contain StandardResponse. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-932 | RG |  | 2023-02-27 |  |  | Rob Golding | SRO Design | Replace references to /api.swaggerhub.com/domains/MHHSPROGRAMME with DIP Production URLs | The move to the DIP Production system will require a repointing of the references to the Swagger modules to the production Swagger repository |  | Assessment Complete / Implementation Deferred |  |  | Design misaligned |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Replace references to /api.swaggerhub.com/domains/MHHSPROGRAMME with DIP Production URLs, awaiting on DIP | Technical corrrection | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-933 | RG |  | 2024-02-26 |  |  | Rob Golding | SRO Design | Clarification of response codes that need an associated response body in Swagger | Design need to catch up with implementaton and the 400 response needs a response body for /dip-channel/{id} API |  | Closed | [10 empty] | Duplicate of DIN-930
MHHS-DIN-934 | RS |  | 2024-02-27 | St Clements | 36918 | Daniel Tadecicco | Central Body | IF-001 Migration Change of Supplier (MCS Appointment Scenario) | 003.outgoingSupplierDIPID is defined as Mandatory but for an MHHS Migration the old Supplier may not be MHHS Qualified, so we cannot set this B025.MPAN Energisation Status is defined as Mandatory but we will not have a value at the point we trigger the IF-001, which happens before the SP appointments are confirmed. The MHHS Energisation Status is created when the migration completes (IF-036 issued) B035List.importExportMPANSupplierDIPID is defined as Mandatory but the Supplier of an associated MPAN may not be MHHS Qualified. Further request to widen this DIN to other Forward Migration IFs - these items are also on the IF-002, IF-033 & IF-036 |  | Implemented |  |  | Data |  |  | Interim Release 8 | 2024-03-20 |  | Interim Release 8 | 2024-03-20 | Serveral solution options were discussed with SCS on how this might be resolved. Agreed solution is that REGS will populate a 'dummy DIP iD' ie. 9999999999 into the DIP ID field where required to populate a DIP ID but where the referenced party is not qualified. (This impacts IF-003, IF-002, IF-001, IF-033, IF-036) Add new valid value of U - Undetermined to DI-033 to allow a value to be populated during Migration. This will be updated with the actual Energisation Status at the stage the IF-036 is issued and the value has been set in Registration Service | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-935 | SB |  | 2023-02-27 |  | 34656 |  |  | correction of errors in DES240 (Transitional Scaling Weights) | when recently reviewing the transitional scaling weights we have noticed some errors in the values listed in NewCCC_Weights and Existing_CCCs tabs for losses. The scaling weight principles on first tab state that all losses should have a quality rating of 0.4, however on the NewCCC_Weight tab there are 19 Loss CCCs which have a Quality Rating (column G) of either 0.2 or 0.6 for losses - these should all be 0.4. This would change the Scaling Weight in column I. Similarly the scaling weights for losses, on the Existing_CCCs tab, for Measurement Classes F and G should 1.4 as these are equivalent to MC A (for losses). |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Update DES240 to amend Scaling weights for losses so all are 0.4 as detailed in ticket 34656 | Technical corrrection | Supporting Docs | Interfaces | DES240
MHHS-DIN-936 | RG |  | 2024-02-29 | Design Team |  | Rob Golding | SRO Design | HTTP response code back off & retry behaviour | Align E2E SA doc with the regime for each response code |  | Closed |  |  | Design misaligned | All Participants | [6 empty] | Align E2E SA doc with the regime for each response code | Technical corrrection | Supporting Docs | Supporting document | E2E Architecture Doc
MHHS-DIN-937 | ZH |  | 2024-02-29 |  |  | John Wiggins/Matthew Breen | SRO Design | Align Migration design with wider design changes made for CR028 | The COS Migration tests continue to show EES receiving the IF-001. The EES instance of the IF-001 was removed from the COS process map and the interface catalogue as part of CR028. As such EES will not be able to process the IF-001 and it is inappropriate to include it as part of the baselined test scenarios. |  | Implemented |  |  | Design misaligned |  |  | Interim Release 8 | 2024-03-20 |  | Interim Release 8 | 2024-03-20 | Updates to be made to relevant Migration artefacts to align with the design changes to the COS process map and DES138 in relevance to EES not receiving IF-001. | Process Model correction | Migration | Process Model correction | BPM001, BPD001
MHHS-DIN-938 | MF |  | 2024-03-01 | PDA |  | Richard French | Data Service Provider | Confirmation of dates to use in the D0388 UMS Inventory | Confirm that the UMSO should populate the effective from date to align with the appointment date. So during BST, for example for a 1st July appointment the D0388 UMS Inventory should state 1 July (even though, where no previous Data Service exists, the UMSDS should calculate periods 47 & 48 of the 30th June UTC Settlement Date ). |  | Implemented |  |  | Clarification - No change required |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | METH009 UMSO Method Statement updated accordingly | Method statement correction | Supporting Docs | Method Statement | METH009
MHHS-DIN-939 | RS |  | 2024-03-01 | St Clements | 36920 | Daniel Tadecicco | Central Body | Difference in lapse behavior for subsequent IF-031 Appointments between enduring and migration | There is a difference in the logic for Migration and Enduring when it comes to lapsing Appointments. In Migration, it allows MPRS to lapse an IF-031 Migration immediately without a matching IF-034. For enduring MPRS must wait for the IF-034 before lapsing. We would like Migration to be aligned with enduring for ease of coding. This would require a change to MHHS-Migration-Can-RS-005 to change the line "In this case, an IF-035 would be sent immediately to cancel the Migration. " to "Any earlier appointments should be lapsed." |  | Implemented |  |  | Design ambiguous |  |  | Interim Release 8 |  |  | Interim Release 8 |  | Note added to REGS Migration Requirment - MHHS-Migration-Can-RS-005 to confirm functionality | Requirement correction | Migration | Migration Requirements | Migration Requirements Log
MHHS-DIN-940 | MH |  | 2024-03-01 | Helix | 38131 | Rashmi Radhakrishnan | Central Body | M18 - ISD | The M18 example table in EDI021 ISD Entities has values of N/A where the actual values should be blank. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction | All Participants |  | Post Go-live Release |  |  | Post Go-live Release |  | Update the example table to show blank fields where the DIP Role does not have an associated MP Role Code | Other | Supporting Docs | ISD | EDI021 ISD Entities Document
MHHS-DIN-941 | RG | DIN-720 | 2023-10-11 | Utiliteam |  | Mike Fensome | SRO Design | Update to DI-122 Profile Class to min length of 1, max length of 2 | Allow Profile Class (DI-122) to be provided with min length of 1 and max length of 2 in both swagger and DES138 so that, for example, either 1 or 01 are accepted. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Update 7.1 swagger to match 5.4 for DI-122 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-942 | RG |  | 2024-03-05 | St Clements |  | Melissa Brocklehurst | Software Provider | Errors in REP-901 in Swagger | Blocks R901-07 & R901-08 do not align with the defintion in ERI011B s/s. The fields chargeBand, dailyUncorrectedVolumeForChargeBand and totalVolumeChargeForChargeBand need to be removed from R901-07 |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.2 |  |  | Interim Release 7.2 |  | Remove chargeBand, dailyUncorrectedVolumeForChargeBand and totalVolumeChargeForChargeBand fields from R901-07 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-943 | BK |  | 2024-03-05 | Helix |  | Nigel Rees | Central Body | CR034 - Delay to Elexon Level 4 validation response – NFR (1009) | The change being proposed is that Helix does not meet the requirements of E2E1009 NFR. We request the description for E2E1009 be updated to read “All Services shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes - 10minutes or less – excludes IF-021” | CR034 | Implemented |  |  | Change Request |  |  | Interim Release 7.1 |  |  | Interim Release 7.1 |  | Updated Level 4 Processing Times (Asynchronous) requirement as follows; All Services with the exception of Helix (VAS,MDS,LSS,ISD) Services shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes - up to average hourly volume, mean response time of 6s or less - up to average hourly volume, 90th percentile response time of 12s or less - from average hourly to peak hourly volume, mean response time of 10s or less - from average hourly to peak hourly volume, 90th percentile response time of 16s or less Helix Services (VAS,MDS,LSS,ISD) shall provide an Asynchronous response time of 10 minutes or less. | Requirement correction | Supporting Docs | Requirements | MHHS-E2E002 Requirements
MHHS-DIN-944 | SB |  | 2024-03-08 | Design Team |  | Paul Pettitt | SI Design | Service Provider appointment Process | The Operational choreography does not align with the Design intent of flexibility with Service Provider Appointment. OP_120 requires clarification |  | Closed |  |  | Error/Correction | [7 empty] | Closed - upholding the objection raised by ReCCo against this DIN
MHHS-DIN-945 | SC |  | 2024-03-13 | RECCo |  | Sarah Jones | Central Body | CR46 - Change of Energy Direction | Remove reference to 'one-time only' change and add guidance that Change of ED will not change hisotric consumption in MDS/Settlements - any changes to hisotric consumption for that MPAN should be via Consumption Ammendment or Trading Dispute | CR046 | Implemented |  |  | Change Request | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | "One Time Change" reference removed from BP010B and BPD010B for "Change of Energy Direction" process, Registration Requirements (BRS003), Supplier Overview (BRS004) and LDSO Overview (BRS005). New note added to BP010B to highlight that any historic settlement data will not be amended, this would need to be via Consumption Amendment or Dispute process where required. | Process Model correction | Registration | Business Process Models/ Requirements | BRS003, BRS004, BRS005, BP010 and BP010B
MHHS-DIN-946 | RS |  | 2024-03-13 | St Clements | 39364 41047 | Daniel Tadecicco | Central Body | Use of LP006 - Migration Aborted, Pending Registration Received | MHHS DEL974 has requirement MHHS-Migration-COA(MS)-RS-002 states two event codes MGR_Cancelled_MS and MGR_Cancelled_DS should be created, however this needs to be amended to confirm the use of LP006 |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Update to MHHS-Migration-CoA(MS)-RS-002/MHHS-Migration-CoA(DS)-RS-002 in MHHS-DEL974 and Migration Design Document section 13.2.3 | Technical corrrection | Migration | Supporting document | MHHS-DEL974 Migration Design Document
MHHS-DIN-947 | SC |  | 2024-03-13 | DIP |  | Sean Cooper | Central Body | Changes to Swagger to support Implementation of JSON Error Checking End Points. | Swagger to be updated to include facility for new JSON Message Error Checking End Points and response message. |  | Implemented | [5 empty] | Interim Release 7.2 |  |  | Interim Release 7.2 |  | Swagger to be updated to include facility for new JSON Message Error Checking End Points and response message. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-948 | SC |  | 2024-03-14 | St Clements |  | Sean Cooper | SRO Design | Error Code Description Text Updates | Update Error code Text to align with confirmed text provided by SCS |  | Implemented |  |  | Design gap |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Update Error code Text to align with confirmed text provided by SCS | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-949 | RS | DIN-1021 | 2024-03-15 | St Clements | 39365 | Daniel Tadecicco | Central Body | MHHS-Migration-CoA(MS)-RS-009 Alignment with IR7 | The IF-031 REG code in the Migration Requirements log for MHHS-Migration-CoA(MS)-RS-009 does not align with IR7 IR7 IF DI-800 = SEG or CSP, COS, USP and MPAN is not migrated (ie operating in old regime) REG9008 - MHHS Scenario Codes cannot be used for UnMigrated MPAN |  | Implemented |  |  | Design misaligned |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Update Migration requirements doc to align with DES138 error code (REG9009) and updated Migration doc where relevant to align with DES138 error code (REG9009). | Technical corrrection | Migration | Supporting document | Migration Requirements Log Migration Design Document
MHHS-DIN-950 | SC |  | 2024-03-18 |  |  | Sean Cooper | SRO Design Team | CR44 - IF-051 Refresh Message | CR044 - Please refer to the change request documentation for details | CR044 | Closed |  |  | Change Request | [7 empty] | ~ Swagger changes to include new IF-051 ~ Secondary routing treatment of If-051 [DONE] ~ Add IF-051 data strcutre to DES138 [DONE] | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-951 | SC |  | 2024-03-18 |  |  | Sean Cooper | SRO Design Team | CR45 - SSD Fix Tool | CR045 - Please refer to the change request documentation for details | CR045 | Closed |  |  | Change Request | [7 empty] | ~ Swagger updates to include New De-App Reason Code ~ Swagger New IF-001 Event Codes ~ Add IF-001 Event Codes to DES138 [DONE] ~ Changes to secondary Routing to Support [DONE] ~ Possible SSD Fix Business Process Diagram | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger Potential - BPXXX
MHHS-DIN-952 | RS |  | 2024-03-18 | Datamere | 41267 | Paul O'Neill | Software Provider | Anomolies in DES138 | DI-991 on 02_DIP_Common worksheet states the values can be TBC (eg PROD, PREPROD, UAT, SIT, DEV). Postman states the following: "S1.environmentTag must be one of 'PROD,PREPROD,SIT,UIT,DEV'." Q2 – DI-840 on 02_IF-031 worksheet states the data item is named CSS Registration ID. Postman states the following: property 'CSSRegistrationID' is unsupported for 'B013' block", B013.CSSRegistrationRequestID field is required. |  | Assessment Complete / Implementation Deferred |  |  | Design misaligned | All Participants |  | Post Go-live Release |  |  | Post Go-live Release |  | Update DES-138, data items: DI-991 and DI-840 to align them to swagger (please view DIN details notified) DI-849 ( not DI-840 ): "CSS Registration ID" is correct in Swagger and DES138 as per DIN 864 - no change required DI-991: Value need to be updated to match swagger, UAT needs to be changed to UIT | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-953 | SC |  | 2024-03-18 |  |  | Sean Cooper | SRO Design | New DTN Flows for Existing Retained Settlement D-Flows | Update EDI001 Settlement Reporting Spec to reference New D-Flow References assigned to retained D-Flows |  | Closed |  |  | Design misaligned | [7 empty] | Update EDI001 Settlement Reporting Spec to reference New D-Flow References assigned to retained D-Flows
MHHS-DIN-954 | RG |  | 2024-03-18 | Avande |  | Piotr Penar | Avanade | Add validation endpoints into Swagger | Add validation endpoints into Swagger |  | Closed | [10 empty] | DUPE 954
MHHS-DIN-955 | MH |  | 2024-03-21 |  |  | Matt Hall | SI Design | CR043 - MPAN/ABMU Mapping | DIN to cover the changes required to Design folowing approval of CR043 | CR043 | Implemented |  |  | Change Request | Suppliers, MDS |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | New requirements to be added to MDS and Suppliers' BRS documents to cover CR043 | Requirement correction | Supporting Docs | Requirement correction | BRS004-Supplier Overview BRS008 MDS Requirements
MHHS-DIN-956 | ZH |  | 2024-03-21 | MHHS |  | Zakir Hussain | SI Design | Rebranding of D-Flows - DES196 & ERI011b | DIN to align changes made in the DES196 document (latest D-flows added to the doc) to the relevant areas within design |  | Implemented | No |  | Design misaligned | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Update ERI011b and DES196 to reflect use of ECS DTN reports and New D-Flow References assigned to retained D-Flows | Reporting correction | Supporting Docs | Various documents | ECS Report External ERI011b DES196
MHHS-DIN-957 | MF | Test defect 31009 DIN-963 DIN-964 | 2024-03-21 | SI Design |  | Mike Fensome | SI Design | Update swagger in IF-005 | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. |  | Implemented | Yes | 31009 | Error/Correction |  |  | Interim Release 5.5 |  |  | Interim Release 5.5 |  | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-958 | BK | MHHS-DIN-937 | 2024-03-21 | SRO Design |  | John Wiggins/Matthew Breen | SRO Design | Align Migration design with wider design changes made for CR028 | The COS Migration tests continue to show EES receiving the IF-001. The EES instance of the IF-001 was removed from the COS process map and the interface catalogue as part of CR028. As such EES will not be able to process the IF-001 and it is inappropriate to include it as part of the baselined test scenarios. |  | Closed |  |  | Design misaligned | [7 empty] | Updates to be made to relevant Migration artefacts to align with the design changes to the COS process map and DES138 in relevance to EES not receiving IF-001. | Process Model correction | Migration | Process Model correction | BPM001, BPD001, Migration document
MHHS-DIN-959 | BK | MHHS-DIN-942 | 2024-03-21 | St Clements |  | Melissa Brocklehurst | Software Provider | Errors in REP-901 in Swagger | Blocks R901-07 & R901-08 do not align with the defintion in ERI011B s/s. The fields chargeBand, dailyUncorrectedVolumeForChargeBand and totalVolumeChargeForChargeBand need to be removed from R901-07 |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Remove chargeBand, dailyUncorrectedVolumeForChargeBand and totalVolumeChargeForChargeBand fields from R901-07 | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-960 | BK | MHHS-DIN-947 | 2024-03-21 | DIP |  | Sean Cooper | Central Body | Changes to Swagger to support Implementation of JSON Error Checking End Points. | Swagger to be updated to include facility for new JSON Message Error Checking End Points and response message. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Swagger updated to include facility for new JSON Message Error Checking End Points and response message | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-961 | RG |  | 2024-03-22 | SRO Design |  | Rob Golding | SI Design | Update Environment list to reflect those being delivered by Avanade | Existing list: - PROD - PREPROD - SIT - UIT - DEV Update to add SITB |  | Implemented |  |  | Error/Correction |  |  | Interim Release 5.5 |  |  | Interim Release 5.5 |  | Only SITB currently added | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-962 | RG | DIN-1011 | 2024-03-25 | Helix | 42284 | Nigel Rees | Central Body | Make MPAN optional on replay/requeue | Removing MPAN from the mandatory list of parameters for DIP replay/requeue |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Removing MPAN from the mandatory list of parameters for DIP replay/requeue and introduce mandatory/null design pattern on input parameters | Technical corrrection | Supporting Docs | Interfaces | Swagger, E2E SA
MHHS-DIN-963 | MF | Test defect 31009 DIN-964 DIN-957 | 2024-03-21 | SI Design |  | Mike Fensome | SI Design | Update swagger in IF-005 | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. |  | Implemented | Yes | 31009 | Error/Correction |  |  | Interim Release 7.2 |  |  | Interim Release 7.2 |  | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-964 | MF | Test defect 31009 DIN-963 DIN-957 | 2024-03-21 | SI Design |  | Mike Fensome | SI Design | Update swagger in IF-005 | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. |  | Implemented | Yes | 31009 | Error/Correction |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-965 | RG |  | 2024-03-22 | SRO Design |  | Rob Golding | SI Design | Update Environment list to include SITB | Existing list: - PROD - PREPROD - SIT - UIT - DEV Update to add SITB |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.2 |  |  | Interim Release 7.2 |  | Only SITB currently added | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-966 | SC | Test Defect 31336 DIN-1019 | 2024-03-27 | SRO Design |  | Sean Cooper | SRO Design | Revision to the PUB-004 Secondary routing logic. | SIT DEFECT - 31336 Currently distribution logic states delivery of PUB-004 to SUPC and XMSC. This results in the send of the message (IF-004) being unnecessrily copied in on the PUB-004. Secondary logic should reference sending party and issue to XMSC where sent by SUPC and SUPC where message sent by XMSC. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.3 |  |  | Interim Release 7.3 |  | SIT DEFECT - 31336 Currently distribution logic states delivery of PUB-004 to SUPC and XMSC. This results in the send of the message (IF-004) being unnecessrily copied in on the PUB-004. Secondary logic should reference sending party and issue to XMSC where sent by SUPC and SUPC where message sent by XMSC. DES138 - IF-004 routing table updated accordingly | Technical corrrection | Supporting Docs | Interfaces | Secondary Routing DES138
MHHS-DIN-967 | MF | Test Defect 31338 | 2024-03-27 | Design Team |  | Mike Fensome | SRO Designn | Update BP010A to show that MPL address updates from UMSO are via "Agreed Communication Method" | Update BP010A to show that MPL address updates from the UMSO are notified via "Agreed Communication Method" |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Updated BP010A and BPD010A to show that MPL address updates from the UMSO are notified via "Agreed Communication Method". This aligns with BR-MS-064 and reflects that the UMSO cannot currently use D0381 flow | Process Model correction | MPAN Ownership | Business Process Models | BP010A BPD010A
MHHS-DIN-968 | SC |  | 2024-03-27 | Avanade |  | Sean Cooper | SRO Design | MDR Secondary Routing | Following text added to interfaces where MDR is referenced as a Secondary Recipient .... .... "Reference to MDR above assumes that MDR is Qualified for DIP Operations & is opt'ed in for SDS-MDR message exchange" |  | Implemented |  |  | Design ambiguous |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Following text added to appropriate interfaces.... .... "Reference to MDR above assumes that MDR is Qualified for DIP Operations & is opt'ed in for SDS-MDR message exchange" | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-969 | SC |  | 2024-03-28 | SCS |  | Sean Cooper | SRO Design | Implementation of REGS Calendar based RF Cut of Date Checking | SCS have confirmed that RF Cut Off Date validation based on the ISD Settlement Calendar cannot be implemented until post go-live. SCS/Programme assessment is that given the other validation rule(s) in place principly the check around Migration Date that this is not an issue. This DIN is to formally record this issue - DIN will be differed. |  | Assessment Complete / Implementation Deferred |  |  | Design gap |  |  | Post Go-live Release |  |  | Post Go-live Release |  | RF restrictions for MS, DS, MDR, Energisation Status EFDs. Deferred DIN captured for reference
MHHS-DIN-970 | SC |  | 2024-03-28 | SCS |  | Sean Cooper | SRO Deign | Bypassing SSD Check where no SP's are appointed even beyond RF Cut Off Date | Logic check required following implementation of DIN969 to allow for Retrospective Appointment of SP's prior to RF Cut off Date - where Supplier has failed to do this prior to RF cut off date for the SP Appointment Start Date |  | Assessment Complete / Implementation Deferred |  |  | Design gap |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Logic variation to allow Pre-RF Cut Off Retro Appointments - Defered DIN Captured for Reference |  | Supporting Docs | ISD | EDI021 ISD Entities Document
MHHS-DIN-971 | SC |  | 2024-03-28 |  |  | Sean Cooper | SRO Design | Clarifcation of MPAN Linkage Request Rejection Codes | Programme has been waiting for LDSO confirmation of these codes however this has not been forthcoming todate. In order to finalise the design for other participants the following codes will constitute the go-live design. IE000 - Proposed Linkage Change Accepted IE001 - Proposed Linkage Change Rejected IE099 - Please contact LDSO directly for further advice |  | Implemented |  |  | Design gap |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Programme has been waiting for LDSO confirmation of these codes however this has not been forthcoming todate. In order to finalise the design for other participants the following codes will constitue the go-live design. IE000 - Proposed Linkage Change Accepted IE001 - Proposed Linkage Change Rejected IE099 - Please contact LDSO directly for further advice | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-972 | SC |  | 2024-04-02 | SCS |  | Sean Cooper | SRO Design | Migration Reqs: Removal of Reference to IF-040 (Annual Consumption) from the REGS Migration Requirments | Missed CR39 Update - Remove of Reference to IF-040 (Annual Consumption) from the REGS Migration Requirments |  | Implemented |  |  | Design misaligned |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Missed CR39 Update - Remove of Reference to IF-040 (Annual Consumption) from the REGS Migration Requirments | Technical corrrection | Migration | Supporting document | Migration Requirements Log
MHHS-DIN-973 | SC | 1038 | 2024-04-02 | SCS |  | Sean Cooper | SRO Design | Migration Reqs: Correct REGS treatment of D0312 where a Forward MIgration is in progress. | Requirment updated to refeclt that IF-035 with Lapsed Reason Code of LP001 (MPAN Disconnected/deRegistered) will be issued for any Pending Service Provider Appointments on receipt of D0312 |  | Implemented |  |  | Design ambiguous |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Note added to RESG Migration Requirement MHHS-Migration-Can-RS-006 - to confirm process | Technical corrrection | Migration | Supporting document | Migration Requirements Log
MHHS-DIN-974 | RG | DIN-1012 | 2024-04-02 | EDW Technology |  | Mark Kenney | SRO Design | Align webhookresponse on /statusmessage to /dip-channel | Status messages reponses from the PP systems and the DIP need to align |  | Implemented |  |  | Design misaligned | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Status messages responses from the PP systems and the DIP need to align, also standard message webhook response should return a standard response body on a 400 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-975 | SC |  | 2024-04-02 | SCS |  | Sean Cooper | SRO Design | Migration Reqs: Confirm REGS treatment of related MPANs in Reverse Migration Scenario | Process is not "automatic" with the REGS per se. CSS will issue a switch request for each MPAN, REGS will process each switch request -end result is the same |  | Implemented |  |  | Design ambiguous |  |  | Interim Release 8 | #REF! |  | Interim Release 8 | #REF! | Note added to RESG Migration Requirement MHHS-RMigration-CoS-RS-002 to confirm process is not automatic - same end result is achived through CSS functionality | Technical corrrection | Migration | Supporting document | Migration Requirements Log
MHHS-DIN-976 | RG |  | 2024-04-05 | ESG | 44664 | Patricia Parker | SRO Design | Duplicate enumeration values for the DI-596 Charge Type enumeration | Duplicate enumeration values for the DI-596 Charge Type enumeration, CAPAC appears twice |  | Closed |  |  | Error/Correction | [7 empty] | DI-596 Charge Type enumeration, CAPAC appears twice - Need to remove duplicate charge type | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-977 | RG |  | 2024-04-05 | Avanade |  | Rob Golding | SRO Design | Update PROD to PRD in Environment Tag List | Confirmation that Avanade have labeled the Production DIP environment PRD. The DT-013-EnvironmentTag will require updating: Change PROD to PRD and removed PREPROD. Add SITB |  | Implemented |  |  | Design misaligned | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | The DT-013-EnvironmentTag will require updating: Change PROD to PRD and removed PREPROD. | Technical corrrection | Supporting Docs | Interfaces | Swagger, E2E SA
MHHS-DIN-978 | RS |  | 2024-04-08 | ESG | 41894 | Patricia Parker | Software Provider | REP-003 and REP-006 have JSON label missing in ERI011b - ECS Reports | REP-003 and REP-006 should have Distribution Pattern A and Report Format JSON in cell H7 as per the other MHHS-REP-XX (eg MHHS-REP-07) |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction | All Participants |  | Post Go-live Release |  |  | Post Go-live Release |  | Update REP-003 and REP-006 in ERI011b to match include outlined box as per MHHS-REP-07 | Reporting correction | Supporting Docs | ESC Reporting | ERI011B ESC Reports Document
MHHS-DIN-979 | RS |  | 2024-04-08 | ESG | 41955 | Patricia Parker | Software Provider | DI-819 (De-appointment reason code) in IF-003 should not contain CSERV. Only CSUPP should be used | DES138, IF-003 has DI-819 has the option for CSERV Change of Service Provider in the Population notes column. This should be greyed out leaving just CSUPP change of supplier |  | Closed |  |  | Error/Correction | All Participants | [6 empty] | Update IF-003 in DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-980 | MH |  | 2024-04-10 | SCS | 44726 | Madison Layton | Software Provider | ISD versioning IR8 | IR8 version of ISD has not included the IR7.1 changes. This needs to be resolved by adding the changes back in. This is only DIN-899 |  | Implemented |  |  | Error/Correction | Helix, ISD users |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Add DIN-899 changes back in to the latest version of IR8. Updates required were covered by DIN-1033 and changing M15 to include N as No Consent | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-981 | RS |  | 2024-04-11 | Siemens | 41452 | David Baxendale | Data Service Provider | Incorrect Load Shape Off Peak Period | Most of the off-peak periods cover 14 UTC periods (7 Hours) – either 00:00 to 0700 OR 00:30 to 7:30 There is 1 anomaly in METH001 GSP _C Profile Class 4 has 15 UTC periods – 00:00 to 07:30 |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Method statement will need to be corrected to reflect 00:00 - 07:00 also remove minus sign after the 00:30 _K Will also need to check the load shaping method statement as well (Also incorrect in LSS METH005) | Method statement correction | Supporting Docs | Method Statement | METH001 METH005
MHHS-DIN-982 | ZH | DIN-575/1013 | 2024-04-11 | SCS |  | Madison Layton | Software Provider | CR039 implementation | DES138 - IF040 requires removal of REGS in "To Parties" field | CR039 | Implemented |  |  | Change Request | REGS |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Update IF040 in DES138, removed "Registration Service (REGS)" from "To Parties" field | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-983 | RS |  | 2024-04-11 | MHHS | 36071 | Matt McKeon | Central Body | LLFC Id mandated in retained DTC flow | The Line Loss Factor Class Id is being replaced by the DUoS Tariff Id. The LLFC Id is present in various DTC flows, almost all of which are redundant post MHHS. LLFC Id is an optional field in the D0311 which, according to DES196, is retained post MHHS with the MHHS Change “New rules to clarify that Profile Class and Meter Timeswitch Class [code] should be null if no value exists for MHHS MPANs, LLFC should be populated with the DUoS Tariff Id for MHHS MPANs and EACs should only be provided for non-MHHS MPANs. ”. LLFC Id is a mandatory field in the D0387 which, according to DES196, is retained post MHHS with no changes. |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Replicating the rule in the D0311 in the D0387 seems appropriate. Will add a note to the D0387 and amend DES196. Propose to do this once SIT Cycle 2 has completed, as adding it now would impact DTN flow test scope. | Data interface correction | Supporting Docs | DFlow | DES196
MHHS-DIN-984 | RS | DIN-917 | 2024-04-12 | ESG | 42711 | Patricia Parker | Software Provider | D0148 use within Reverse Migration | DEL961 Migration Document detail does not contain any detail of the use of the D0148 when completing a Reverse Migration as assumed to BAU. Need to reference the use of the New connection process for D0148 as per section 9 of Annex c |  | Implemented |  |  | Design ambiguous | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Add reference to D0148 new connection process (section 9 annex C) to DEL961 (Section 13.1) | Design Ambiguous | Supporting Docs | Migration Design | DEL961
MHHS-DIN-985 | RS | DIN-837 | 2024-04-12 | ESG | 42711 | Patricia Parker | Software Provider | Incorrect meter reading code in section 6.1.3 of DEL961 Migration Design | Secftion 6.1.3 of DEL961 still states Meter Reading Reason Code = 28 (Forward Migration CoA) Instead of Reading Type = U. This should match previously agreed updates of U - Forward Migration CoA V - Forward Migration CoS X - Supplier Agreed Switch Read Y - Reverse Migration CoS As per MHHS impacts to Data Transfer Network (DTN) Flows |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Section 6.1.3 of DEL961 to be updated with U - Forward Migration CoA V - Forward Migration CoS X - Supplier Agreed Switch Read Y - Reverse Migration CoS Remainder of ducument sections to be checked for same disparity | Design Ambiguous | Supporting Docs | Migration Design | DEL961
MHHS-DIN-986 | RS |  | 2024-04-12 | MHHS | 45969 | Test team | Central Body | Incorrect step assigned to migration requirement | DEL974 requirements MHHS-Migration-CoA(MS)-RS-005 and MHHS-Migration-CoA(DS)-RS-005 refer to step 255 of BPM002. No step 255 exists on BPM002. Requirement to be amended to step 710 |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction | All Participants |  | Post Go-live Release |  |  | Post Go-live Release |  | Amend requirements MHHS-Migration-CoA(MS)-RS-005 and MHHS-Migration-CoA(DS)-RS-005 to step 710 in DEL947 (Registration Tab, row 19 and 39) | Requirement correction | Migration | Migration Requirements | DEL974
MHHS-DIN-987 | ZH | DIN-676 | 2024-04-15 | SCS |  | Madison Layton | Software Provider | Missing text in NFRs - CR-018 implementation issues | E2E002 was updated as per IR8 however it is missing text that specifies details around when they are applicable |  | Closed |  |  | Error/Correction | [7 empty] | Duplicate of 993 | Requirement correction | Supporting Docs | Requirements | MHHS-E2E002 Requirements
MHHS-DIN-988 | ZH |  | 2024-04-15 | SCS |  | Daniel Tadecicco | Software Provider | Migration design alignment | DES138 requires some updates to align with the migration design documentation |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Updated IF-003 in DES138 to remove MSDeAppUdateRM & DSDeAppUpdateRM events and removed the accompanying interface note as these events are not used in the case of Reverse Migration Design. Opt In/Out matrix updated accordingly. Swagger updated. | Data interface correction | Supporting Docs | Interfaces | DES138 & Swagger
MHHS-DIN-989 | RG |  | 2024-04-15 | Stark | 45757 | Jon Dennis | Software Provider | DI-596-Charge-Type - CAPAC duplicated in Enum | DI-596-Charge-Type - CAPAC duplicated in Enum -one of the entries needs to be removed |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | remove second CAPAC from enumerated list | Data interface correction | Technical Artefact | Interfaces | Swagger
MHHS-DIN-990 | MF | DI-136 | 2024-04-17 | SCS |  | Madison Layton | Software Provider | Limit effective from updates to RF for appointments and energisation status changes | Update validation rules in IF-031, IF-034 and IF-007 to not allow updates to appintment effective from dates and energisation status effective from dates beyond RF |  | Implemented |  |  | Error/Correction | Suppliers, REGS |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Update validation rules in IF-031, IF-034 and IF-007 to not allow updates to appintment effective from dates and energisation status effective from dates beyond RF. Added note to REGS Notes to confirm that derived Market Segment Effective from Date cannot be beyond RF. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-991 | MF | DIN-939 | 2024-04-17 | SCS |  | Madison Layton | Software Provider | Confirm migration lapse behavior aligns with BAU operation | Update note on MHHS-MIGRATION-CAN-RS-005 to confirm that lapse notification is only issued after receipt of IF-034 |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Updated note on MHHS-MIGRATION-CAN-RS-005 to confirm that lapse notification is only issued after receipt of IF-034 | Requirement correction | Migration | Migration Requirements | DEL974
MHHS-DIN-992 | RG | DIN-1014 | 2024-04-17 | Design Team |  | Rob Golding | SRO Design | IF-016-ActivePowerRejected required incorrect | IF-016-ActivePowerRejected required field B900List should be B900 |  | Implemented |  |  | Error/Correction | Advanced Data Service |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Update: IF-016-ActivePowerRejected required field B900List to B900 | Data interface correction | Technical Artefact | Interfaces | Swagger
MHHS-DIN-993 | MF | DIN-929 | 2024-04-17 | SCS |  | Daniel Tadecicco | Software Provider | Confirmation of LDSO response times | Update E2E1009 in line with CR040 and Operational Choreography to confirm repsonse times specified are within normal operating hours | CR040 | Implemented |  |  | Change Request | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Updated E2E1009 in line with CR040 and Operational Choreography to confirm repsonse times specified are within normal operating hours | Technical corrrection | Supporting Docs | Interfaces | E2E002 - Non-Functional Requirements
MHHS-DIN-994 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Treatment of mixed meter sites | Update registration notes to confirm treatment of mixed meter sites |  | Assessment Complete / Implementation Deferred |  |  | Design ambiguous | REGS |  | Post Go-live Release |  |  | Post Go-live Release |  | Update Reg Notes in DES138 to confirm that: • If a mix of Smart and Traditional meters then consider the Meter Group as Smart • If any Advanced meter is fitted then this should be considered as in the Advanced Segment so Meter Group as Advanced. Update REG1042 and REG1043 validation in IF-025 to clarify how mixed meters are validated | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-995 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Correlation ID removed from IF-037 AppUpdate events | Remove Correlation ID from AppUpdate events on IF-037 |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Removed Correlation ID from AppUpdate events on IF-037 | Data interface correction | Supporting Docs | Interfaces | DES138 (No swagger change reqd)
MHHS-DIN-996 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Update description of DI-028 (Reconnection Effective from Date) | Update description of DI-028 to reflect that this is when the Metering Point is reconnected in Registration Service |  | Assessment Complete / Implementation Deferred |  |  | Design ambiguous | All Participants |  | Post Go-live Release |  |  | Post Go-live Release |  | Update description of DI-028 to reflect that this is when the Metering Point is reconnected in Registration Service | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-997 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | PUB-007 validation to allow de-energisation on a Disconnected MPAN | Validation should be changed to allow a PUB-007 to De-energise a Disconnected MPAN (De-energise only, energisation would still not be permitted on disconnected MPAN) |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | New Validation to allow a PUB-007 to De-energise a Disconnected MPAN (De-energise only, energisation would still not be permitted on disconnected MPAN) with error code of REG1001 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-998 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Clarification on sending error message on IF-034 where incorrect Service Provider responds | Add note to IF-034 validation rules to confirm that REGS will respond with RCP1063 if the incorrect Service Provider responds |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction | All Participants |  | Post Go-live Release |  |  | Post Go-live Release |  | Add note to IF-034 validation rules to confirm that REGS will respond with RCP1063 if the incorrect Service Provider responds | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-999 | MF | DIN-788/1015 | 2024-04-18 | UKPN |  | Neil Madley | Network Operator | Update routing for [MPANReconnection] and add event to Opt/In Out Matrix | On IF-009 add LDSO as secondary routed. Add [MPANReconnection] to the Opt In/ Opt Out Matrix so that LDSO's can opt out of receiving this event. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.3 |  |  | Interim Release 7.3 |  | On IF-009 added LDSO, SUPC as secondary routed. Added [MPANReconnection] to the Opt In/ Opt Out Matrix so that LDSO's can opt out of receiving this event. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1000 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Update to error message REG1032 to refer to Local Time | Update REG1032 validation on IF-031 in DES-138 to refer to Local Time |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Updated REG1032 error message on IF-031 in DES-138 to refer to Local Time, where previously referenced UTC. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1001 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Remove REGS requirement MHHS-BR-RS-014.1 | Supplier Nominated DPI is not provided on Metering Service Appointments, so this Requirement is not needed. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction | REGS |  | Post Go-live Release |  |  | Post Go-live Release |  | Remove requirement MHHS-BR-RS-014.1 from BRS-003 to provide Supplier Nominated DPI for Metering Service Appointments. Requirement retained for Data Service Appointments. | Requirement correction | MPAN Ownership | Business Requirements Documentation | BRS003 - Registration Service requirements
MHHS-DIN-1002 | MH |  | 2024-04-19 | Helix |  | Rashmi Radhakrishnan | Central Body | ISD M11 and M12 | As per the UMSUG meeting that we attended, For M12, its been agreed that we need to incorporate OFF event to have “NEVER” where there is no OFF event. |  | Implemented |  |  | Error/Correction | UMSDS |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Added a new permissable value of "NEVER" to the OFF Event data field in ISD Entity M12 | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-1003 | RS |  | 2024-04-19 | National Grid | 43643 | Rachael Prosser | Network Operator | E2E Architecture Document to be updated to include Reference to LDSO and IF-20 | E2E Architecture Document does not include latest updates made to IF-20 for LDSO, review and update required |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction | LDSOs |  | Post Go-live Release |  |  | Post Go-live Release |  | Add line advising for the latest representation refer to DES138. RG to to complete review of document | Other | Supporting Docs | E2E Architecture Document | E2E001 Architecture Document
MHHS-DIN-1004 | RS |  | 2024-04-19 | CGI | 47845 | Dave Webster | Software Provider | DES138 OptOut Matrix for IF-003 Supplier | The 04_IF_OptOut_Matrix sheet of DES138 v5.8.1 shows that IF-003 is not received by Supplier (“N/A”), but for all Event Codes the IF-003 message is Primary Routed to Supplier |  | Implemented |  |  | Error/Correction | Suppliers |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Changed IF-003 for Supplier to No from N/a in DES138 IF Opt out Matrix tab. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1005 | MH |  | 2024-04-19 | Helix | 46469 | Matt Hall | SI Design | METH007 Section D clean up | Currently SEction D in the METH007 doesn't clearly distinguish between REP002/2a and 2b. This is causing some confusion and should be rectified |  | Assessment Complete / Implementation Deferred |  |  | Design ambiguous | All Participants |  | Post Go-live Release |  |  | Post Go-live Release |  | Tidy up of Section D in MTH007 to clarify which reports are included, and to clarify which of the REP02 variants require non-W connections include (if any) | Method statement correction | Supporting Docs | Method Statement | METH007
MHHS-DIN-1006 | MH | DIN-087 | 2024-04-19 | RECCo | 46872 | Sarah Jones | Central Body | Outstanding Design Query (DIN087) | As part of the final code drafting checks, we are confirming that all consultation comments have been addressed. We have identified a comment from an early drafting tranche (CD-0558) which queries the requirements to issue a de-energisation notice for meter exchanges. At the time, we were expecting a note to be added to BP008 to make it clear that that ‘DeEn did not need to be notified if meter works completed within same day (ie same rules as today)’ as stated in the DIN log against DIN087. However, BP008 doesn’t appear to have this note included which means we have not been able to close out the code drafting query. |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Add a box to BPM008 to to reflect the proposed solution in DIN-087 | Process Model correction | Supporting Docs | Business Process Diagram | BP008
MHHS-DIN-1007 | RG | DIN-1018 | 2024-04-22 | Avanade |  | Rob Golding | SRO Design | Change request body on Validation Endpoints | Avanade have reviewed the 1.7.1. endpoints and are requesting a chnage so that they are more flexible and align to the submission API |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.3 |  |  | Interim Release 7.3 |  | Avanade have reviewed the 1.7.1. endpoints and are requesting a change so that they are more flexible and align to the submission API | Technical corrrection | Swagger |  | Swagger
MHHS-DIN-1008 | SB |  | 2024-04-23 | British Gas |  | Neil Strange | Supplier | BP-03C Transfer of Reads Clarification | We’ve noticed that on BP03C the IF/PUB016 interface is TBC – looking at DES138 I believe this is confirmed – am I correct? This is in the advanced meters section following successful appointment. |  | Assessment Complete / Implementation Deferred |  |  | Design ambiguous | Advanced Data Service |  | Post Go-live Release |  |  | Post Go-live Release |  | Updating BP003C to remove TBC from IF/PUB-016 (Step 815 to Step 820) | Process Model correction | Supporting Docs | Business Process Diagram | BP003C
MHHS-DIN-1009 | SB |  | 2024-04-23 | MHHS |  | Shaun Magee | Central Body | METH002 Issue with LTV Method statement | Incorrect Method referenced in section 3.13 should be method 11 rather than 12 |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Update: Incorrect Method referenced in section 3.13 should be method 11 rather than 12 | Method statement correction | Supporting Docs | Method Statement | METH002
MHHS-DIN-1010 | TR | DIN-762 | 2024-04-23 | RECCo | 46312 | Jonny Moore | Central Body | IF-003 - EES as Recipient | EES not included within the 'To Parties' in DES138 |  | Assessment Complete / Implementation Deferred |  |  | Design misaligned | EES |  | Post Go-live Release |  |  | Post Go-live Release |  | DES138 updated to include EES in the 'To Parties' field | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1011 | RG | DIN-962 | 2024-03-25 | Helix | 42284 | Nigel Rees | Central Body | Make MPAN optional on replay/requeue | Removing MPAN from the mandatory list of parameters for DIP replay/requeue |  | Closed |  |  | Error/Correction | [7 empty] | Only implement in IR8 | Technical corrrection | Supporting Docs | Interfaces | Swagger, E2E SA
MHHS-DIN-1012 | RG | DIN-974 | 2024-04-02 | EDW Technology |  | Mark Kenney | SRO Design | Align webhookresponse on /statusmessage to /dip-channel | Status messages reponses from the PP systems and the DIP need to align |  | Implemented |  |  | Design misaligned |  |  | Interim Release 7.3 |  |  | Interim Release 7.3 |  | Status messages reponses from the PP systems and the DIP need to align | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-1013 | ZH | DIN-575/982 | 2024-04-11 | SCS |  | Madison Layton | Software Provider | CR039 implementation | DES138 - IF040 requires removal of REGS in "To Parties" field | CR039 | Closed |  |  | Error/Correction | [7 empty] | Update IF040 in DES138, remove "Registration Service (REGS)" from "To Parties" field | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1014 | RG | DIN-992 | 2024-04-17 | SRO Design |  | Rob Golding | SRO Design | IF-016-ActivePowerRejected required incorrect | IF-016-ActivePowerRejected required field B900List should be B900 |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.3 |  |  | Interim Release 7.3 |  | IF-016-ActivePowerRejected required field B900List should be B900 | Data interface correction | Technical Artefact | Interfaces | Swagger
MHHS-DIN-1015 | MF | DIN-999 | 2024-04-18 | UKPN |  | Neil Madley | Network Operator | Update routing for [MPANReconnection] and add event to Opt/In Out Matrix | On IF-009 add LDSO as secondary routed. Add [MPANReconnection] to the Opt In/ Opt Out Matrix so that LDSO's can opt out of receiving this event. |  | Implemented |  |  | Error/Correction | LDSOs |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | On IF-009 added LDSO, SUPC as secondary routed. Added [MPANReconnection] to the Opt In/ Opt Out Matrix so that LDSO's can opt out of receiving this event. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1016 | RG | DIN-1017 | 2024-04-24 |  |  |  |  | REP002 & REP002B require update | Swagger for REP-002 & REP-002B needs to be updated to reflect the defns in ERI011B. REP-002 The ERI011B – ECS Reports spreadsheet has the R027 – Distributor ID as a repeating block, meaning that Suppliers will receive 1 REP-002 for each combination of Distributor and GSP Group. REP-002B Similarly the REP-002B has R009 as a repeating block |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.3 |  |  | Interim Release 7.3 |  | Update swagger to reflect ERI011B | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-1017 | RG | DIN-1016 | 2024-04-24 | Design Team |  | Rob Golding | SRO Design | REP002 & REP002B require update | Swagger for REP-002 & REP-002B needs to be updated to reflect the defns in ERI011B. REP-002 The ERI011B – ECS Reports spreadsheet has the R027 – Distributor ID as a repeating block, meaning that Suppliers will receive 1 REP-002 for each combination of Distributor and GSP Group. REP-002B Similarly the REP-002B has R009 as a repeating block |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Update swagger to reflect ERI011B | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-1018 | RG | DIN-1007 | 2024-04-22 | Avanade |  | Rob Golding | SRO Design | Change request body on Validation Endpoints | Avanade have reviewed the 1.7.1. endpoints and are requesting a change so that they are more flexible and align to the submission API |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Avanade have reviewed the 1.7.1. endpoints and are requesting a change so that they are more flexible and align to the submission API | Technical corrrection | Swagger |  | Swagger
MHHS-DIN-1019 | SC | Test Defect 31336/ DIN-966 | 2024-03-27 | Design Team |  | Sean Cooper | SRO Design | Revision to the PUB-004 Secondary routing logic. | SIT DEFECT - 31336 Currently distribution logic states delivery of PUB-004 to SUPC and XMSC. This results in the send of the message (IF-004) being unnecessrily copied in on the PUB-004. Secondary logic should reference sending party and issue to XMSC where sent by SUPC and SUPC where message sent by XMSC. |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | SIT DEFECT - 31336 Currently distribution logic states delivery of PUB-004 to SUPC and XMSC. This results in the send of the message (IF-004) being unnecessrily copied in on the PUB-004. Secondary logic should reference sending party and issue to XMSC where sent by SUPC and SUPC where message sent by XMSC. DIP routing updated as part of IR7 DES138 - IF-004 routing table updated in IR8.1 | Technical corrrection | Supporting Docs | Interfaces | DES138
MHHS-DIN-1020 | RS | DIN-851 | 2024-04-25 | Code |  | Matt McKeon | Central Body | Queries from REC RTS which relate to either DES138 or ERI110B | CD6-320 is pointing out that data item DI-218 has a different name in DES138 (Current Supplier DIP ID) and ERI011B (Daily Supplier MSID Count). CD6-323 is referring to DI-030 and DI-031 in DES138, asking what the distinction is when they have the same name CD6-325 is asking about a data item with the same name but different DI-refs in DES138 (DI-081) and ERI011B (DI-484) |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | CD6-320 - DI-218 no update required not in ERI011B CD6-325 - DI-484 to be corrected to DI-081 in ERI011b - Swagger to also be updated to reflect consistant use of DI-081 | Technical corrrection | Supporting Docs | Interfaces | ERI011B Swagger
MHHS-DIN-1021 | MF | DIN-949 | 2024-04-25 | SCS | 39365 | Daniel Tadecicco | Central Body | Migration Error Code Alignment with DES138 | Update all the error codes in Migration Design Document and Migration Requirements to align with DES138 |  | Implemented |  |  | Design misaligned | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Update Migration requirements doc to align with all DES138 migration error codes and update Migration doc where relevant to reflect the DES138 error codes Updated DES138 error descriptions as follows: REG9010 - Cannot Manage MPAN Relationships for an Unmigrated MPAN REG9002 - Supplier Data Items Cannot be Maintained for an Unmigrated MPAN REG9001 - CDC Marker Cannot be applied to an Unmigrated MPAN Removal of reference to IF-040 and RCP1076 from migration design document | Technical corrrection | Migration | Supporting document | Migration Requirements Log Migration Design Document DES138
MHHS-DIN-1022 | ZH |  | 2024-04-26 | RECCo | 48861 | Sarah Jones | Consultancy | Implementation of CR037 (Migration Message Processing Choreography Update) | Please refer to the CR037 documentation for further details | CR037 | Implemented |  |  | Change Request | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Updated Change of Agent Migration Timings , as per CR037. This includes the Migration Requirements log, Migration Design Document and the E2E non-functional requirements. | Technical corrrection | Migration | Supporting document | Migration Requirements Log Migration Design Document E2E002 - Non-functional requirements
MHHS-DIN-1023 | TR |  | 2024-04-26 | SCS | 46680 | Madison Layton | Software Provider | Meter Location Data Quality | The PUB-005 B033 block is mandatory on all event codes except for [MeterRemoval]. Within this block the Meter Location is mandatory, however F (not known) is permitted. Where MS is updating other MTDs, there is a risk that they will submit Meter Location F ‘not known’ despite Meter Location not having changed. This could lead to poor quality of meter location data within REGS. Potential mitigation could be level 5 validation rule on REGS: if Meter Location held in REGS is not F or null, then DI-090 must not be F. This would ensure Meter Location couldn’t be reverted to F from a previously specified value. |  | Assessment Complete / Implementation Deferred |  |  | Design ambiguous | REGS |  | Post Go-live Release |  |  | Post Go-live Release |  | Potential mitigation could be level 5 validation rule on REGS: if Meter Location held in REGS is not F or null, then DI-090 must not be F. This would ensure Meter Location couldn’t be reverted to F from a previously specified value. | Missing/incorrect validation rule | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1024 | RG | Test Defect 31491 | 2024-04-26 | Kraken |  | Dave Mclean | Software Provider | Use of Min items =1 to stop arrays with zero items | Messages are being sent with arrays with zero items in, however an array with zero items does not make sense. If minItems is set to 1, then schema validation would not allow arrays with zero items. Also, to improve data validation for nullable strings the minLength needs to be set to 1. |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Add minItems = 1 to array where a zero item array is not allowed, Add to the folllowing objects: B900 B901, B902, B920, B922, B921, B903, B906, B906a, B907, B908, B910, B911, B941 | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-1025 | MF |  | 2024-04-29 | Helix |  | Rashmi Radhakrishnan | Central Body | Update to ISD examples in MHHSP_EDI021_ISD_Entities | Update the examples in M7, M17 and M18 tables to support SIT testing |  | Closed |  |  | Design ambiguous | All Participants | [6 empty] | Updated the examples in M7, M17 and M18 tables ( MHHSP_EDI021_ISD_Entities v5.7 ) to support SIT testing | Design Ambiguous | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-1026 | RG |  | 2024-04-29 | Kraken |  | Dave Mclean | Software Provider | Remove DT-008 from data types | The request is that as DT-008 is not use can it be removed from the swagger |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction | All Participants |  | Post Go-live Release |  |  | Post Go-live Release |  | Remove DT-008 from data types | Data interface correction | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-1027 | MF |  | 2024-04-30 | PDA |  | Tom Chevalier via Kevin Spencer | Data Service Provider | Remove reference to UMSDS on Consumption Amendment flow (IF-028) and Opt/In Out Matrix (IF-027) | Currently Consumption Amendment is not utilised by UMSDS so removed reference in the Consumption amendment flows |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction | UMSDS |  | Post Go-live Release |  |  | Post Go-live Release |  | Remove UMSDS from "From parties" on IF-028. Updated UMSDS as N/A for IF-027 in Opt/In Out Matrix. BP016 references UMSDS to be removed. | Data interface correction | Supporting Docs | Interface Documentation | DES-138 BP016
MHHS-DIN-1028 | MF |  | 2024-04-30 | SCS |  | Madison Layton | Software Provider | Update REG1040 description | Update the description for REG1040 to cover both SSC and Profile Class error messages to align with validation rules in IF-025 |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction | Suppliers, REGS |  | Post Go-live Release |  |  | Post Go-live Release |  | Update REG1040 to "REG1040 - SSD/ Profile Class Effective From Date must be later than existing" and remove REG1041 in the "Introduction" Tab of DES138 | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1029 | MF |  | 2024-04-30 | SCS |  | Madison Layton | Software Provider | Make B032 block mandatory for [SSCandProfileClass] event in IF-025 and IF-026 | Update Swagger and DES138 to make B032 block mandatory for [SSCandProfileClass] event in IF-025 and IF-026. |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Update Swagger and DES138 to make B032 block mandatory for [SSCandProfileClass] event in IF-025 and IF-026. | Data interface correction | Supporting Docs | Supporting document | DES138 & Swagger
MHHS-DIN-1030 | RG | DIN-850 (original IR7 DIN) | 2024-04-30 | Callisto | 50078 | Scott Parkinson | Software Provider | IF037 DSDeApp CustomBlock requires B002 block | Looks as though some of the CR36 changes did not make their way into swagger: the change to include the B002 block in the IF-037 DSDeApp custom block is missing |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.3 |  |  | Interim Release 7.3 |  | Update swagger so that B002 block included in the IF-037 DSDeApp custom block | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1031 | RG |  | 2024-05-01 | EDW Technology | 32016 | Mark Kenny-Jones | Software Provider | Inconsistencies between E2E & Swagger defn of Status Messages | Regarding the SRB that contains empty strings (i.e. the one used to report schema validation errors), are you aware that this does not comply with the current API schema? And if so, are there any plans to either update the schema, or to change the structure of this response so that it does comply with the schema? Specifically, I’m referring to the fact that there are a number of fields in the SRB that have minimum lengths, which an empty string would violate. Similarly, none of the fields are marked as nullable, therefore replacing an empty string with an explicit null value would also violate the schema. Excluding the fields entirely also wouldn’t be an option, as some of the fields are mandatory, and this would also go against the advice in section 4.6.6.2 of the end to end architecture document (E2E001 v3.6) says that “Where a field is not written/available/optional, then a null value needs to be written” |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | The standard Response body has been updated to follow the manadatroy/null design approach. | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1032 | TR |  | 2024-05-01 | ESG |  | Patricia Parker | Software Provider | DI-103-Configurable-Register-ID need to be alpahnumeric | The REGEX in Swagger for DI-103-Configurable-Register-ID which requires numeric values only, the data element should just be a string(2), as per DES-138, to allow numeric or aphla characters. |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Update Swagger so the data element is string(2) to allow for numeric and alpha characters | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1033 | MF |  | 2024-05-01 | Helix |  | Rashmi Radhakrishnan | Central Body | Updates to ISD M17/ M7 tables | Updated ISD M17 to add in Meter Group as Char 11 to align with M7 Meter Group. Added allowable values to cover Unmetered in M7 |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Updated the M17 table to include Meter Group as Char 11. Added Unmetered to Meter Group in both M7 and M17. Updated Meter Type in M7 to “Mandatory. Valid Set as per EMAR1 or U for Unmetered” | Design Ambiguous | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-1034 | RG |  | 2024-05-03 | SCS | 50636 | Mariana Mesaros | Software Provider | REP900 & RE901 are missing schema version ERI011B spreadsheet | REP900 & RE901 are missing schema version in S0 block in ERI011B spreadsheet. The swagger has the schema version |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Updated ER0I011B with schema version for REP-900/1 | Data interface correction | Supporting Docs | Interfaces | ERI011B
MHHS-DIN-1035 | RG | DIN-850 (original IR7 DIN) DIN-1030 (7.3 DIN) | 2024-04-30 | Callisto | 50078 | Scott Parkinson | Software Provider | IF037 DSDeApp CustomBlock requires B002 block | Looks as though some of the CR36 changes did not make their way into swagger: the change to include the B002 block in the IF-037 DSDeApp custom block is missing |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Update swagger so that B002 block included in the IF-037 DSDeApp custom block | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1036 | RG |  | 2024-05-09 | Avanade |  | Ptior Penar | Software Provider | DI-432-Period-Metering-System-Metered-Data requires clarification | DI-432-Period-Metering-System-Metered-Data need to remove multiplier constraint |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Update swagger DI-432 | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1037 | RG |  | 2024-05-10 | St Clements | 50045 | Vicki Holland/Tom Perryman | Software Provider | REP900 Changes | Changes to be made to the REP900 are: • REP900-03 to be a parent of REP900-04 • Delete data item DI-563 (LDSO Billing Account Reference) as it is redundant with Site Id and Invoice Number also included in the message • Move the following data items to REP900-04 as they can all change for a site and are specific to the invoice raised: - 612 (Site DUoS Tariff ID), 566 (List of MPANs), 567 (Misaligned multi MPAN site), 568 (Site Capacity) • Update DI-565 LDSO Billing Site ID to data type of String(30) • Add GSP Group ID to the REP900-03 site record |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Updates to Swagger & ERI011B | Data interface correction | swagger | Interfaces | Swagger/ERI011B
MHHS-DIN-1038 | MF | DIN 973 | 2024-05-10 | ESG |  | Patricia Parker | Software Provider | Clarify Migration Reqs re D0312 | Requirment updated to refeclt that IF-035 with Lapsed Reason Code of LP001 (MPAN Disconnected/deRegistered) will be issued for any Pending Service Provider Appointments on receipt of MPAN termination (not D0312) |  | Implemented |  |  | Error/Correction | REGS |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Remove reference to D0312 in the note added to REGS Migration Requirement MHHS-Migration-Can-RS-006 as it is triggered by receipt of a termination of the MPAN from the LDSO following receipt of D0132 | Requirement correction | Migration | Supporting document | Migration Design Requirements
MHHS-DIN-1039 | MF | DIN-946 | 2024-05-10 | ESG |  | Patricia Parker | Software Provider | Update Lapse codes scenario's in DES138 | update DES138 (IF-035) to show LP004 can also apply to MCS scenario and LP006 would only apply to MCA scenario |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction | All Participants |  | Post Go-live Release |  |  | Post Go-live Release |  | update DES138 (IF-035) to show LP004 can also apply to MCS scenario and LP006 would only apply to MCA scenario | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1040 | RG |  | 2024-05-15 | Kraken | 52894 | Dave MaClean | Software Provider | Migration Deisgn: Missing B095 block in IF-003-MSDeAppRM & missing B096 block in IF-003-DSDeAppRM | Ticket noticed B095 is missing from the IF-003-MSDeAppRM variant. On closer inspection the B096 is also missing from the IF-003-DSDeAppRM |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Both DES138 and the Swagger both need updating: Missing B095 block in IF-003-MSDeAppRM & missing B096 block in IF-003-DSDeAppRM | Data interface correction | Supporting Docs | Interfaces | DES138 & Swagger
MHHS-DIN-1041 | RG |  | 2024-05-16 | MHHS |  |  |  | Alignment of DES138 to message version numbers | The message version numbers in DES138 need to be aligned to the swagger versions, ie. version '011' for release 7.x. Also align IF-061/5 to the other interfaces |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Update DES138 to the correct version, update swagger for IF-061/If-062/If-063/IF-064/IF-065 to version '011' so consistent with other IFs |  |  |  | DES138 & Swagger
MHHS-DIN-1042 | RG |  | 2024-05-17 | Kraken | 52894 | Dave MaClean | Software Provider | DI-830 (B070) Swagger/ DES138 descrepancy | The MeteringServiceDIPEffectiveFromDate is from the Data Catalogue on DES138. In the defn of the B070 block the term proposedMeteringServiceEffectiveFromDate is used (ana probabaly the better term to use). However, too late to change, so an update to DES138 to align the B070 to the DC/Swagger is required |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update B070 block in DES138 to align with swagger/data catalogue | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1043 | RS |  | 2024-05-21 | Siemens | 53765 | Tony Mason | Metering Service Provider | Method Statement where site is disabled | Method 12 in both SDS and ADS Method statement documents should state the reason code as Disabled, looks like currently a cut & paste from method 11 |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | METH001 (SDS) and METH002 (ADS) to be updated with the following for Method 11 & 12 (replacing SDS with ADS for METH002 - also amending 'Site' to lower case Method 11. Estimation for Long Term Vacant Sites Where the Supplier has notified a Flag to identify that a site is LTV and in cases where no access to consumption data is available, then in the presence of this flag the SDS will estimate zero and set a LTV estimation reason code. This data will be recorded as “ZE2” and the estimation reason code ‘LTV’ should identify as LTV. UTCPDj = 0 Method 12 Estimation where a site where Supply is disabled Where the Supplier has notified a Flag to identify a site where the supply is disabled and in cases where no access to consumption data is possible, then in the presence of this flag the SDS will estimate zero. This data will be recorded as “ZE3” and set the estimation reason code ‘Disabled’. | Method statement correction | Supporting Docs | Method Statement | METH001 METH002
MHHS-DIN-1044 | RG |  | 2024-05-23 | ESG | 54979 | Kerry O'Donnel | Software Provider | IF-009-MPANReconnection has incorrect event code | The event code for IF-009-MPANReconnection need to be [MPANReconnection] rather than [MPANDReconnection] |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | The event code for IF-009-MPANReconnection need to be [MPANReconnection] rather than [MPANDReconnection] | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-1045 | RG |  | 2024-05-29 | SRO |  | Rob Golding | SRO Design | Tidy up of routing rules for IF-041 | The routing rules table for IF-041 requires updating |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | The second and third rows in the routing table in DES138 need to be merged. | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1046 | RS |  | 2024-06-04 | SRO |  | Matt McKeon | SRO Design | Clarifications to the ECS DTN Reports | Retrospective changes made to D0397 - MHHS Supplier Half Hourly Demand Report (now v1.2) D0401 - MHHS Aggregated Disconnected DUoS Report (now v1.1) D0402 - MHHS Supplier Half Hourly Demand Disconnection Report (now v1.1) D0403 - MHHS GSP Group Demand Disconnection Totals Report (now v1.1) D0404 - MHHS Supplier BM Unit Demand Disconnection Report (now v1.1) |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.3 |  |  | Interim Release 7.3 |  | D0397 - Updated the Range of Group 02Z ‘Daily Totals Per Suppler’ from ‘1-1’ to ‘0-*’ D0401 - Amended MM Description to say “A report of Disconnected Volumes by Distributor. Where the report is sent to the Distributor it will contain data for all Suppliers impacted by the Demand Control Event, whereas where it is sent to the Supplier it will only contain data pertaining to that Supplier.” - Renamed DI20306 ‘DUoS Daily Supplier Demand Disconnection Volume’ to ‘DUoS Daily Smart and Unmetered Demand Disconnection Volume’ - Renamed DI20307 ‘DUoS Daily Supplier Demand Disconnection Volume Losses’ to ‘DUoS Daily Smart and Unmetered Demand Disconnection Volume Losses’ - Renamed DI20310 ‘DUoS Supplier Demand Disconnection Volume’ to ‘DUoS Smart and Unmetered Demand Disconnection Volume’ - Renamed DI20311 ‘DUoS Supplier Demand Disconnection Volume Losses’ to ‘DUoS Smart and Unmetered Demand Disconnection Volume Losses’ - Updated the Range of Group 79J ‘Demand Control Event Details‘ from ‘1-*’ to ‘1:1’, so that one report is produced per DDE. D0402 - MHHS Supplier Half Hourly Demand Disconnection Report (now v1.1) - Updated the Range of Group 04K ‘Demand Control Event Details‘ from ‘1-*’ to ‘1:1’, so that one report is produced per DDE. D0403 - Updated the Range of Group 36K ‘Demand Control Event Details‘ from ‘1-*’ to ‘1:1’, so that one report is produced per DDE. D0404 - Updated the Range of Group 43K ‘Demand Control Event Details‘ from ‘1-*’ to ‘1:1’, so that one report is produced per DDE. | Technical corrrection | Supporting Docs | Supporting document | D0397 - MHHS Supplier Half Hourly Demand Report D0401 - MHHS Aggregated Disconnected DUoS Report D0402 - MHHS Supplier Half Hourly Demand Disconnection Report D0403 - MHHS GSP Group Demand Disconnection Totals Report D0404 - MHHS Supplier BM Unit Demand Disconnection Report
MHHS-DIN-1047 | MF | DIN-934 | 2024-06-04 | SCS |  | Daniel Tadecicco | Central Body | Additional value of U for Energisation Status used during Migration | Add new valid value of U - Undefined to DI-033 to allow a value to be populated during Migration. This will be updated with the actual Energisation Status at the stage the IF-036 is issued and the value has been set in Registration Service |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  |  | Interim Release 8.1 |  | Add U - Undefined as an allowable value to be used for Energisation Status during Migration in DI-033 for IF-001, IF-002 and IF-033 in DES138/ swagger. Participants will be updated with the actual Energisation Status when the IF-036 is issued. Remove U as an allowable value from DI-033 in IF-007 in DES-138. | Data interface correction | Supporting Docs | Interfaces | DES138 & Swagger
MHHS-DIN-1048 | ZH |  | 2024-06-04 | MHHS |  | Zakir Hussain | Consultancy | BRS002 requirements typo | Business Requirements MHHS-BR-MS-071.1 and MHHS-BR-MS-071.2 should be documented within MHHSP-BRS002-Metering Service requirements v5.6 and should apply to both the MSS and MSA Roles. Unfortunately, there is a typo in the Bus Requirement and these are currently showing as DS versions in 3 tabs (all, MSS and MSA) i.e. MHHS-BR-DS-71.1 and MHHS-BR-DS-71.2 which is not aligned to the naming convention around them. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update BRS002-Metering Service Requirements - Change requirement "MHHS-BR-DS-071.1" and "MHHS-BR-DS-071.2" to "MHHS-BR-MS-071.1" and "MHHS-BR-MS-071.2" | Requirement correction | All Areas | Business Requirements Documentation | MHHSP-BRS002
MHHS-DIN-1049 | ZH |  | 2024-06-04 | MHHS |  | Zakir Hussain | Consultancy |  | An exemption has been made in the Qualification process for certain Suppliers. Essentially if a Supplier commits to never supplying Unmetered MPANs they do not have to undertake the qualification tests pertaining to unmetered MPANs – largely as they would have to build capability they would never use. Could I therefore request a DIN be raised to add the following the Supplier Requirements set: · a Supplier not Qualified for UMS shall not migrate UMS MPANs into the new MHHS arrangements. · a Supplier not Qualified for UMS shall not register UMS MPANs in the new MHHS arrangements. This will allow traceability in Qualification assurance to allow qualifying bodies to ask suppliers what controls they have in place to restrict this. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Add the following the Supplier Requirements set: · a Supplier not Qualified for UMS shall not migrate UMS MPANs into the new MHHS arrangements. · a Supplier not Qualified for UMS shall not register UMS MPANs in the new MHHS arrangements. | Requirement correction | All Areas | Business Requirements Documentation | Supplier Requirements Doc
MHHS-DIN-1050 | RG | DIN-211 | 2024-06-06 | SRO |  | Rob Golding | SRO Design | B042 - DI-077 Naming descrepancy | DES-138 has DI-077 named as DI-077-CSS-RMP-DeActivation-Date whilst in swagger the corresponding filed name is CSSMPANDeRegistrationDate. Normally the two should align |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | The YAML DI name in Swagger is aligned with DES-138 and reflects CR024 ie DI-077-CSS-RMP-DeActivation-Date. However the YAML name of the field in swagger is titled "CSSMPANDeRegistrationDate". If required for consistency, the change would be to update the YAML name in swagger to be consistent with the YAML DI name ie CSSRMPDeActivationDate. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-1051 | TR |  | 2024-06-11 | Design Team |  | Tamsyn Robertson | SI Design | MHHS-REP-002B Description Field Update | The Description field in the REP-002B spec is not correct. The reference to Suppliers needs to be removed. The 'To Parties' and 'Routing Rules' are correct. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Change 'Description' field in DES-138 to: 'The report provides aggregated Distribution Use of Systems data for LDSOs or Suppliers in Clock Time.' | Document Correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1052 | TR |  | 2024-06-11 | Design Team | 57348 | Tamsyn Robertson | SI Design | ISD entity M2- Typo | The latest version of the ISD spec currently lists M2 - Connection Type Description H as "High Voltage with Current transformer" with a lowercase "t" in "transformer.". BSCP707 Appendix 1 and Appendix 2 has been updated, so this DIN is to align with the correction to the code. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update M2 - Connection Type Description H to: "High Voltage with Current tTransformer" | Document Correction | Supporting Docs | ISD | EDI021 ISD Entities Document
MHHS-DIN-1053 | TR |  | 2024-06-11 | Opus | 56809 | Lee Eltherington | Supplier | D0397 - Consumption Component Indicator | The Data Item List at the top of the D0397 PDF does not contain the Consumption Component Indicator field that is showing in the dataflow structure. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update the D0397 document to include the Consumption Component Indicator and link to J0162. | Document Correction | Supporting Docs | D-Flow Documents | D0397
MHHS-DIN-1054 | TR |  | 2024-06-11 | ESG | 57833/58471 | Patricia Parker | Software Provider | D0149 - Missing SV | Updates required for the D-flow documentation |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Need all three scenario variants (smart to smart, legacy to smart and smart to legacy). in DTC. Possible error in both the D0149 and D0150. | Document Correction | Supporting Docs | D-Flow Documents | DTC D0149 D0150
MHHS-DIN-1055 | RG |  | 2024-06-12 | Kraken | 58587 | Dave Maclean | Software Provider | IF-006 S0 block missing required properties | InterfaceID, schemaVersion & eventCode fields should be marked as required on the S0 block on the IF-006 interface |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.2 |  |  | Interim Release 8.2 |  | Add required fileds to S0 blocks in all IF-006 variants - InterfaceID, schemaVersion & eventCode | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-1056 | RG |  | 2024-06-26 | Avanade |  | Gaurav Agrawal | Software Provider | R900-04 block remove LDSOBillingSiteID from required list | The R900-04 block still has LDSOBillingSiteID in the required parameters - it needs to be removed |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.2 |  |  | Interim Release 8.2 |  | Remove LDSOBillingSiteID from required field in R900-04 | Technical corrrection | Supporting Docs | Swagger | Swagger
MHHS-DIN-1057 | RG |  | 2024-06-26 | SRO Design | 61939 | Rob Golding | SRO Design | DIP L3 webhook response time set to 10 secs | The DIP timeout on a synchronous response was set to 5 seconds, this will be updated to align with the NFRs |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update E2E SA document & requirements with value | Technical corrrection | Supporting Docs | E2E Architecture Document | E2E001, E2E002
MHHS-DIN-1058 | SB |  | 2024-06-26 | SCS | 62087 | Madison Layton | Central Body | DI-260 Missing MDR and Consent Granularity in MHHS-BR-RS-074 | The Registration Service Requirements is missing the requirement to apply MDR and Consent Granularity to related secondary MPANs when confirming a new Data Service Appointment on a Primary MPAN. Suggested uplift below in red. Detail shown on the Fresh Desk Ticket |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update MHHS-BR-RS-074 to include additional detail | Requirement correction | Registration | Business Requirements Documentation | REGS Requirements
MHHS-DIN-1059 | RG | DIN-1133 (Defect 41296) | 2024-06-26 | EDW Tech | 62837 | Kavita Siddle | Central Body | IF-020-RelatedCreate has two unwanted Event Codes | IF-020-RelatedCreate has two unwanted Event Codes [RelatedAdd] and [RelatedRemove]. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Remove the two unwanted Event Codes from the IF-020-RelatedCreate message variant in swagger. Shouldn't affect testing as the messages resolve to the same structure | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-1060 | RG |  | 2024-06-28 | Avanade |  | Piotr Penar | Software Provider | Align error codes to final DIP design | Align error codes to final DIP design |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.10 |  |  | Interim Release 8.10 |  | Update DES138 Introduction Tab to include the final DIP design error codes and add an explanation for actions to take on receipt of these error messages. Corrected Error Codes documented in IF-015. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1061 | RG |  | 2024-07-01 | Avanade |  | Gaurav Agrawal | SRO Design | Update swagger error codes to align with final DIP design | Update the error codes documented in swagger to align with final DIP design. Note this is documentation change only as swagger is not used for generating the error codes |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update documentation of error codes in swagger to align to the final DIP design. Note this is a documentation update only. | Technical corrrection | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-1062 | RG |  | 2024-07-03 | Wheatley Solutions |  | Chris Mingay | Software Provider | Connection requests are missiing a User Agent which occassionally trigger FW rule | Add User Agent Header to DIP http requests so that identification is clear on interfacing sysems. Avanade ADO ticket no 42340 |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update CoCo (E2E) to add new http header info | Other | Supporting Docs | E2E Architecture Document | E2E Code of connections document
MHHS-DIN-1063 | TR |  | 2024-07-05 | Helix | 65874 | Riccardo Lampini | Central Body | Measurement Quantity Naming Convention | There are inconsistencies with the use of Measurement Quantity/Measurement Quantity ID within 3 entities as per the ISD Entity Spec and this is not aligned with Swagger/MDS Method Statement |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.2 |  |  | Interim Release 8.2 |  | Update ISD Entity spec and Method Statemenst to align the terminology with what is used in Swagger. MHHS Both Consumption Component Classes (M5) and Load Shape Categories (M4) to state 'Measurement Quantity ID'. This is correct in the Measurement Quantity Entity. Reference tables in Method Statements to be updated. | Document Correction | Supporting Docs | ISD | EDI021 ISD Entities METH001 (SDS) METH002 (ADS) METH004 (UMSDS) METH005 (LSS) METH006 (VAS)
MHHS-DIN-1064 | TR |  | 2024-07-05 | CGI | 62573 | Dave Webster | Software Provider | PUB-045 for UMSDS | According to DES138 5.8.2 sheet 04_IF_OptOut_Matrix, UMSDS can opt out of receiving an IF-045 [InvalidMarketSegment] message. However, according to sheet 02_IF-045, a UMSDS is not a valid recipient of an IF-045. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update 04_IF_OptOut_Matrix to remove UMSDS from IF-045 [InvalidMarketSegment] | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1065 | SB |  | 2024-07-09 | RECCo | 66065 | Jonny Moore | Central Body | Energisation | closed captured in 1073 |  | Closed
MHHS-DIN-1066 | MF |  | 2024-07-10 | EoN |  | Cathy Mulliss | Supplier | Clarification on requirments for maintaining Customer and PSR data by the Data Service | Clarify that the Data Service only has to maintain Customer and PSR data where the data is provided by the Supplier. If the Supplier and Data Service have bilateral agreements whereby this is not required then this data does not have to be shared by the Supplier and maintained by the Data Service . |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | A clarification has been issued as part of the Knowledge Base that Suppliers can make bilateral agreements with Data Services and Meter Reading Services for the provision of meter readings to the Data Service. Where the Data Service does not require Customer/ PSR data to meet their obligations for providing data to Settlements, the Supplier can elect not to share Customer and PSR data to the Data Service. Minor tweak to the requirments to make it clear that this information is only shared and maintained where required. | Document Correction | Meter to Bank | Business Requirements Documentation | BRS001 BRS004
MHHS-DIN-1067 | RG |  | 2024-07-12 | CGI | 67334 | Chris Beard | Software Provider | Ensure Correlation Id information in E2E001 E2E SA doc aligns to DES138 | Reviewing the E2ESA doc the corrleation Id info need to relect the infromation in DES138 |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Minor update to E2ESA doc | Document Correction | Supporting Docs | E2E Architecture Document | E2E001 Architecture Document
MHHS-DIN-1068 | RG |  | 2024-07-12 | Avanade |  | Piotr Penar | Software Provider | Make the elements of the CommonBlock.S0 mandatory | At present the 3 elements of the S0 block: Interface Id Schema Version Event Code are not marked as mandatory. Marking them as mandatory would block issues with missing fields at schema validation rather than causing the DIP to error |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.2 |  |  | Interim Release 8.2 |  | Add required attributes to all S0 blocks to include the 3 fields (inerfaceId, eventCode & schemaVesrion). Zero impact on PPs as not a structural change | Technical corrrection | Supporting Docs | Swagger | Swagger
MHHS-DIN-1069 | RG |  | 2024-07-18 | Imserv | 68171 | Liam Lowey | Software Provider | Removal of oneOf statements in Swagger to faciliate validation at endpoints | The oneOf statement used in the design of the DIP mesages proves to be an issue for using the swagger to validate with the current endpoint definition. Steps could be made to introduce a version alongside the existing one that removes the oneOfs. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | This could be achieved by PPS having endpoints defined for each IFor PUB Event Code combination as per the new valdiation endpoints | Change Request | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-1070 | RG |  | 2024-07-18 | C&C | 67972 | Graham King | Software Provider | Provide replay of status messsages | Request to provide Replay facility for Status Messages |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Woudl need to go into the Avanade backog and be prioiritised accordingly | Change Request | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-1071 | MF |  | 2024-07-19 | SCS | 66166 | Daniel Tadecicco | Central Body | Clarification on when migration appointments are lapsed | Migration appointments will only be lapsed following an MPAN being confirmed as CSS de-activated. This is in line with MHHS BAU operation as outlined in MHHS-BR-RS-103. Therefore, MHHS-Migration-Can-RS-006 is redundant and Migration Design should be aligned to the MHHS BAU operation. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Remove MHHS-Migration-Can-RS-006 and clarify migration design (section 6.1.1 bullet 13) aligns to MHHS BAU operation for CSS de-activated MPANs. | Document Correction | Migration | Migration Requirements | Migration Requirements Log Migration Design Document
MHHS-DIN-1072 | TR |  | 2024-07-22 | Helix | 67485 | Rashmi Radhakrishnan | Central Body | Domestic Premise Indicator Data Type (ISD and DI-031 Data Items) | Both the ISD M4 Domestic Premise Indicator and DI-031 currently have a data type of Boolean but optional. Needs correcting to allow for null, T and F values. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.2 |  |  | Interim Release 8.2 |  | The ISD Data Item (Domestic Premise Indicator) in ISD Entity M4 to be updated to 'Load Shape Domestic Premise Indicator', this is to align with the DES-138 Data Item DI-031. The ISD Entity Data Item must also be updated to Character (1) optional to allow null values for Advanced Load Shapes. For clarity, acceptable values for the 'Load Shape Domestic Premises Indicator' are 'T', 'F' or 'null'. All reference tables to be updated. UMSDS LSC has a value of null in the Domestic Premise Indicator field - this is incorrect (Unmetered should always be Non-domestic). The LSS Method Statement is correct. UMSDS Method Statement to be updated with 'F' as the LSC value associated to Unmetered. ISD Entity M17 to be updated to remove the row supporting Domestic Unmetered. | Document Correction | Supporting Docs | ISD | ISD Entities Document Swagger DES-138 METH001 (SDS) METH002 (ADS) METH004 (UMSDS) METH005 (LSS)
MHHS-DIN-1073 | SB |  | 2024-07-23 | RECCo | 66065 | Jonny Moore | Central Body | Energisation Status Enumerations | While reviewing the changes made to DES138 for IR8.1 we’ve noticed a discrepancy around the new value of U introduced to the energisation status through DINs 934 and 1047. While the new enumeration has been added in the population notes for the IFs where it will be used, the enumerations held in the data item catalogue have not been updated. As the Energy Market Data Specification (EMDS) stores the enumerations against the data item not the data population rules, we will need this added to the data item catalogue in order for it to be reflected in the EMDS valid set. Without this the value of U will not be a valid value at go-live. Please can the data item within the DES-138 Data Item Catalogue be updated appropriately so we can reflect this in code drafting. |  | Assessment Complete / Implementation Deferred | No |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | DES-138 data catalogue to be updated to include the value of "U" for the energisation status | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1074 | PP |  | 2024-07-24 | St Clements | 69275 |  | Central Body | DI-262 B013 CSS Registration ID Block Optionality in Swagger | We’ve spotted an error in implementing DES-138 B013 optionality in swagger. In DES-138 the B013(CSS Registration ID) block optionality is mandatory if available on a series of DIP messages This has been interpreted to mean the block is optional in swagger for a number of the messages. However, for most of the DIP messages the CSS Registration ID is always available and therefore mandatory. The B013 block must be mandatory on the IF-025 IF-031 IF-034 The CSS Registration ID is always available to the Supplier and the Service Provider would always receive a CSS Registration ID in the IF-033 from MPRS. The CSS Registration ID is necessary for the processing of these messages in MPRS. The B013 block should then also be mandatory on the subsequent messages from MPRS namely: IF-026 IF-032 IF-033 IF-035 IF-036 IF-037 It is already mandatory on the IF-001 and IF-002 from MPRS in both DES-138 and Swagger. And for IF-018 the B013 CSS Registration ID block must remain as optional in swagger/mandatory if available in DES-138. IF-018 messages can be generated for MPANs that are not yet registered, and as such no CSS Registration ID would exist for the MPAN. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Align DES-138 and swagger on the B013 block | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-1075 | PP |  | 2024-07-24 | St Clements | 69259 |  | Central Body | DI-261 - Level 5 Validation that proposed MS/DS is valid in ISD on EFD | Hi Design Team, We’ve raised DI-261. MPRS currently validates as a level 4 rule that the proposed MS/DS is valid in ISD at the point of receipt of the PUB-031 but there is no validation that the proposed MS/DS is valid on its proposed EFD. For this MPRS would need to validate as a level 5 validation rule. We’ve raised a change for MPRS to validate MS/DS for their proposed EFD and to use REG1081 as this is the closest matching rule in DES-138 currently. DES-138 needs uplifting to amend REG1081 to apply more generally to MDR, MS and DS. |  | Assessment Complete / Implementation Deferred | [5 empty] | Post Go-live Release |  |  | Post Go-live Release |  | Update DES-138, REG1081 to apply more generally to MDR, MS and DS. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1076 | TR |  | 2024-07-30 | Programme |  | Tamsyn Robertson | SI Design | ISD Entities Updates | Minor errors in the entities spec to be corrected for completeness. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | M17 - Valid /Consent Granularity Combinations is the title - should be updated to remove "/" - this aligns with BSCP707 drafting M18 - Market Participant Role Code N/A in example should be null. DIP Market Role "LDSO" = DIP Role Description "Licenced Distribution System Operator " not "Licenced Distribution System Operation". DIP Market Role "UMSO" = DIP Role Description "Unmetered Supplies Operator " not "Unmetered Supplied Operator". | Document Correction | Supporting Docs | ISD | EDI021 ISD Entities Document
MHHS-DIN-1077 | RG |  | 2024-07-30 | Design |  | Paul Pettitt | SI Design | Missing 'II' value in the enumerated field for Di-160 | the 'II' run indicator value list needs to be included in the enumerated list |  | Implemented | Yes | 37985 | Error/Correction |  |  | Interim Release 8.2 |  |  | Interim Release 8.2 |  | There is currently a workaroind inplace by C&C where they added II to their local enumerated list, but ultimately the list should include II '- II - Interim Information - SF Initial Settlement - R1 First Reconciliation - R2 Second Reconciliation - R3 Third Reconciliation - RF Final Reconciliation - DR Dispute - DF Final Dispute | Technical corrrection | Supporting Docs | Interfaces | DES-138, Swagger, ERI011B
MHHS-DIN-1078 | TR |  | 2024-08-01 | EDW Tech | 67808 | Alexandre Townsend | Software Provider | REP-002 event code correction | REP-002 event code This has an event code of “[DUOSSupplierAggData]”, but the ECS Reports document says the event code is “[DUoSSupplierAggData]” with a lower case o in DUoS. The Dip simulator also expects the lower case spelling. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | [DUOSSupplierAggData] is the correct representation of the event code - update ESC Reports document | Document Correction | Supporting Docs | ESC Reporting | ERI011B ESC Reports Document
MHHS-DIN-1079 | TR |  | 2024-08-06 | CGI | 70601 | Dave Webster | Software Provider | Sources of Correlation ID | There are a number of Correlation IDs which are created, but I can’t spot where they are subsequently used. IF-003 [ReverseMigNotification] IF-003 [MSDeAppRM] IF-003 [DSDeAppRM] IF-020 [LinkedImportExportCreate] IF-020 [LinkedImportExportAdd] IF-020 [LinkedImportExportRemove] IF-037 [MSDeApp] IF-037 [DSDeApp] IF-065 [MDRInstantaneous] IF-065 [MDRTOU] IF-065 [MDRConsumption] |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update DES-138 Correlation ID Created field IF-003 [ReverseMigNotification] > No IF-003 [MSDeAppRM] > No IF-003 [DSDeAppRM] > No IF-020 [LinkedImportExportCreate] this will contain either the PUB-019’s correlation ID if provided, or in absence of that it’ll contain an LDSO or MPRS generated correlation ID IF-020 [LinkedImportExportAdd] this will contain either the PUB-019’s correlation ID if provided, or in absence of that it’ll contain an LDSO or MPRS generated correlation ID IF-020 [LinkedImportExportRemove] this will contain either the PUB-019’s correlation ID if provided, or in absence of that it’ll contain an LDSO or MPRS generated correlation ID IF-037 [MSDeApp] > No IF-037 [DSDeApp] > No IF-065 [ReadingRemote] > No/Copy | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1080 | RG |  | 2024-08-07 | Kraken | 71005 | Angelos Rizoyannis | Software Provider | Request for DIP API to provide message acceptance information | To provide an API that we can query with a list of transaction IDs and/or Sender Unique Reference numbers, including the status of the messages and whether they were accepted by DIP or not. |  | Assessment Complete / Implementation Deferred |  |  | Change Request |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Build an API that can be queried, with a list of transaction IDs and/or Sender Unique Reference numbers, including the status of the messages and whether they were accepted by DIP or not. Currently available manually, API requested for automation. | Technical corrrection | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-1081 | TR |  | 2024-08-07 | MDS |  | Vicky Gosar | Central Body | MDS/VAS Method Statement Misalignment - EA12 Flag | MDS method statement refers to ‘E12’ flag while handling missing data. But this ‘E12’ flag doesn’t exist in the CCCs table in VAS method statement. Instead, VAS method statement has reference to ‘EA12’ flag. These need to be aligned - EA12 is correct and aligned to code drafting. |  | Implemented | Yes | 36240 | Error/Correction |  |  | Interim Release 8.2 |  |  | Interim Release 8.2 |  | Update Section 9 (and 14) of MDS Method Statement to update 'E12' to 'EA12'. For clarity, 'EA12' is the correct representation for this flag | Document Correction | Supporting Docs | MDS Method Statement | METH007 (MDS)
MHHS-DIN-1082 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | Most DIP IDs have enumeration as ISD. However DI-108 has ‘no’ enumeration DI-834 has ‘no’ enumeration DI-847 has a blank enumeration. DIN needed to reflect ISD in enumerations column for these 3 data items. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Re-opened as post go-live fix. For consistency, update DES-138 Data Catalgue to show enumeration is taken from ISD for DI-108, DI-834 and DI-847. No change to swagger. | Document Correction | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1083 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-218 current supplier DIP ID has MHHS data type DT-027 which is the data type for MPID. The actual format is correct. DIN needed to correct data type to DT-006. |  | Closed |  |  | Error/Correction | [7 empty] | No update required as this data item is not used in MHHS Design (ie not referenced in any interfaces). DIN 1084 removes the Data items from DES138. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1084 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | Swagger data catalogue doesn’t appear to have DI-218 or 219. DIN to be raised – swagger only change |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | DI-218 and DI-219 to be removed from DES138 as they are not referenced in any interfaces and not required for MHHS design | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1085 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-017 Consent Granularity is missing two enumerations in DES138: x # obfuscated value #DIN-858 #- null # DIN-729 need to add null DIN to be raised for additional enumeration x to the list and also to classify Consent Granularity as mandatory nullable |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update DES-138, Data item: DI-017 to include "X" as this is a missing enumeration | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1086 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-021 / 22 Customer Direct Contract Metering / Data Service is Boolean. DES138 provides the example Y, Swagger provides example True. The EMDS standards doc defines Boolean as a true or false so assume this should be T or F. DIN to be raised to clarify the examples in both DES138 and Swagger. Not impacting code drafting as this correctly references T/F DI-030 Domestic Premise Indicator - is Boolean. DES138 provides the example T, Swagger provides example True. The EMDS defines Boolean as T or F so swagger example is incorrect. DIN to be raised to clarify the example in Swagger. DI-031 – Load Shape Domestic Premise Indicator – same as above. DIN to be raised to clarify the example in Swagger. EMDS is correct DI-837 Supplier Proposed Domestic Indicator is Boolean but Swagger has example as False. DES138 correctly lists T – Domestic and F – Non Domestic |  | Closed |  |  | Clarification - No change required | [7 empty] | Clarify Boolean data types examples used in swagger and DES-138, example: DI-021 and DI-022 show "Y" in DES-138 and "true" in swagger. Others also highlighted include: DI-030, DI-031, DI-837 Following the implementation of DIN-1114 we are closing this DIN as a duplicate | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-1087 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-046 Load Shape Day Total has an MHHS Data Type of DT-016 in swagger. This is missing from DES138 but may not be an issue as not all data items have an MHHS data type. DIN to be raised to add data type DT-016. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update DI-046 to include the data type "DT-016" to align with swagger | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1088 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-059 Meter Type lists the enumerations in swagger. DES138 points to ISD. Believe Swagger shouldn’t have the enumerations. DIN to be raised to update swagger to avoid future dual governance |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Registration Service validates that data entered is in line with ISD in IF-005 and therefore enumeration is not necessary for DI-059. Update swagger to remove enumeration values if required to avoid having to update swagger for any ISD updates to this data. | Data interface correction | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-1089 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-080 Consumption Component Indicator has two enumerations in swagger C and L. No enumerations in DES138 however this is an existing data item which also has M (Metering System Specific Line Loss) as an enumeration. DIN to be raised to add missing enumerations to swagger |  | Closed |  |  | Error/Correction | [7 empty] | The MHHS design does not require M as an enumerated value for DI-080. M is only required for legacy processes. No change to DES138 or swagger required as M should not be used in MHHS processes. M can continue to be used in D-flows for legacy purposes in the J0162 data item. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-1090 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-094 Reading Method has totally different enumerations in swagger compared to DES138 DIN to be raised to confirm which is correct |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | The X&Y values were added to DES-138 as part of CR036 design when we were looking at deriving a read for midnight clock. These were removed from the design as part of the final changes on CR036, however was missed from DES-138 updates. Change should be to remove X and Y from DES138. Values to align with swagger ie A, C, E and S. The data catalogue should be updated to align as part of the DIN | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1091 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-126 Traditional / Fall Back Read Frequency is missing two enumerations in DES138: DIN to be raised to add x as an enumeration in DES138. No issue with the null value as the DI is mandatory nullable - x # Obfuscated value #DIN-858 - null # - DIN-476 - change for nullable enumeration |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update DI-126 in DES-138 Data Catalogue with enumeration values from swagger ( ie to include x ). | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1092 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-800 Service Provider Appointment Scenario has a missing enumeration in DES138: xxx # Obfuscated value #DIN-858 DIN to be raised to add xxx as an enumeration in DES138. |  | Closed |  |  | Error/Correction | [7 empty] | Update DI-800 enumeration values in DES-138 to match swagger. Closed following implementation of DIN 1123 in IR8.3 which has removed the obfuscation from DI-800 | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1093 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-819 De Appointment Reason Code lists the enumerations in swagger. DES138 points to ISD. Believe Swagger shouldn’t have the enumerations. DIN to be raised to update swagger to avoid future dual governance |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update swagger to remove enumeration values and to point to ISD, as per DES-138 Deappointment reason codes are not held in ISD. Update DES138 Data Catalogue DI-819 to align with swagger and values outlined in population notes of IF-037 | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1094 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-838 – Supplier Proposed Consent Granularity has a missing enumeration in DES138: xxx # Obfuscated value #DIN-858 DIN to be raised to add xxx as an enumeration in DES138. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update DI-838 enumeration values in DES-138 to match swagger. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1095 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-979 Response code has a missing enumeration in DES138: xxx # Obfuscated value #DIN-858 DIN to be raised to add xxx as an enumeration in DES138. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update DI-979 enumeration values in DES-138 to match swagger. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1096 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-999 Event Code – DES138 is min 3, max 50. Swagger is min 1, max 50. DIN needed to correct DES138 |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update DI-999 min and max values in DES-138 to match swagger. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1097 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DT-016 MHHS data type has been defined differently in ECS and DES138. Is 9,3 string 13 or 14. DIN to be raised to align the definition or specify these as different data types. Note the example in swagger is 789.000 which aligns to neither. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | DT-016 data type to be aligned across DES-138 and swagger. Swagger allows "^-?\\d{1,9}\\.\\d{3}$". This is a maximum of string 14 and a minimum of string 5. The Regex determines this. DES-138 Data Catalogue is string 14. Update to show Min and Max string length. External reporting catalogue is string 13. Update External Reporting Catalogue to string 14 | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1098 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DT032 data type differs in ECS RC compared to swagger. DIN to be raised against data type 032 which states it is string 18 but the example includes 17 characters: -nnnnnnnnn.nnnnnn. The example in swagger is completely different: -10987654321.12 which is string 15. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | DT-032 data type needs to be aligned across External Reports Catalogue and swagger. Swagger allows "^-?\\d{1,14}\\.\\d{2}$". This is a maximum of 18 and therefore agrees with External Reports. External Reports Data Catalogue is String 18 Examples need to be updated to add quotes around them so they export correctly. Swagger example is fine. | Technical corrrection | Supporting Docs | Interface Documentation | DES-138 Swagger
MHHS-DIN-1099 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-545 – Distributor Bank Sort code is string 8 with an example of 6 characters in ECS RC but max 10 in swagger. DIN to be raised to align |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | DI-545 needs to align across the ECS reports and swagger. DI-545 is data type DT-035 Sort Code which is defined as Min/Max length 6 in swagger. ECS reports has as String 8 in line with DIN 662. Original CR027 requested string length 6. LDSO's are providing as string 6 in SIT. Solution is to update DI-545 in the reporting catalogue to string 6 | Technical corrrection | Supporting Docs | Interface Documentation | ECS Reports Swagger
MHHS-DIN-1100 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | DI-083 BSC Settlement Period Quality Indicator – different enumerations in ECS RC compared to DES138. We have used DES138 which has the fuller set. Din to be raised to add missing enumerations to swagger |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | DI-083 needs to be aligned across design: DES138 and swagger align - no change required. ECS reports data catalogue to align with DES138 data catalogue. MHHS-REP-009 DI-083 population notes to be updated accordingly. Other References to DI-083 in the REPS highlight that examples are shown - No change required | Technical corrrection | Supporting Docs | Interface Documentation | ECS Reports
MHHS-DIN-1101 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | IF003 – aligned although there is a lack of clarity in the B095 and B096 block which don’t say the events they are used in. Swagger has the B095 just for MSDeAppRM and B096 just for DSDeAppRM |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | This is defined already in DES138 Re-opened as post go live release update to DES138: Block B095 to highlight the MOP Details are provided for [MSDeAppRM] where available in the Registration Service Block B096 to highlight Incoming DC Details are provided for [DSDeAppRM] where available in the Registration Service | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1102 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | IF013 – Swagger refers to B920 list which is not referenced in DES138. In the swagger common block B920 is defined. This references the B050, B046 and B048 blocks which makes sense but also references B045. B045 just includes Measurement Quantity Id (DI-052) which is on B050 in the IF013. Suggest raising DIN seeking confirmation on whether the B045 is needed as a separate block in the IF013. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Re-opened as post go live release update. The use of Blocks 9xx is used in swagger to define arrays, intentially not referenced in DES-138 However, there is an error in the description of the B920 block which refers to Block B045, this should reference Block B050. Recognise that the block is labelled incorrectly, but a change to the block would impact all participants. | Technical corrrection | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-1103 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | IF016 has an event of consumption request rejected. This is not mentioned against any blocks in DES138 but there is a statement against B067 and B046 that its mandatory except replay request rejected – suggest the latter is an error in DES138 and should say ‘mandatory except consumptionrequestrejected |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | IF-016 needs updating in DES-138 to align with swagger. Update conditions for B046 and B067 blocks to state "Mandatory except for [ConsumptionRequestRejected]" | Technical corrrection | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1104 | ZH |  | 2024-08-08 | RECCo | 72733 | Sarah Jones | Central Body | Code Drafting Alignment | IF034 DS App event in swagger includes B070 which is the proposed metering service. DES138 only has this mandatory for MS App event. Looks like swagger error – row 5154 |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | IF-034 would need updating in swagger to align with DES138 as the B070 block is not required for [DSAppSPResponse]. However, as the B070 block is optional for this event the swagger currently does work. | Technical corrrection | Supporting Docs | Interface Documentation | Swagger
MHHS-DIN-1105 | PP |  | 2024-05-05 | Design |  | Paul Pettitt | Central Body | API Guidance | Need to incorporate the guidance issued relating to the 1MB limits and message batching into the E2E001 Technical Architecture documents |  | Implemented |  |  | Clarification - No change required |  |  | Interim Release 8.2 |  |  | Interim Release 8.2 |  | Pertinent sections from the guidance to be included in to the E2E001 solution Architecture document |  | Supporting Docs | E2E Architecture Document | E2E001
MHHS-DIN-1106 | 46 | Defect 37835 | 2024-08-14 | Design |  | Amy Loder | Software Provider | B907 Block requires mandatroy properties | In the IF-002 interface the B907 is required for linked MPANs. In the B907 the fields are not marked as mandatory. The issue also affects the B910, B908 & B911 blocks |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.2 |  |  | Interim Release 8.2 |  | Updates to swagger to mark elements required in these blocks. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-1107 | RS |  | 2024-08-15 | Design | 72837 & 78768 | Neil Strange | Supplier | Removal of requirement MHHS-Migration-Can-Sup-001 | Do not believe this requirement is needed. For Forward Migration CoA we are only de-appointing the legacy agent when the migration is confirmed by Pub-036 Therefore this requirement is redundant – a cancellation due to CoS will mean that we will not have got this far and won’t receive PUB-036. |  | Closed |  |  | Error/Correction | [7 empty] | After discussion with JW, MF and REC input, DIN closed with no changes made as the requirement is still valid based on the IF-035 not the IF-036 | Migration requirements | Migration | Migration Requirements | DEL2430, BP-003, BPM-003
MHHS-DIN-1108 | RS |  | 2024-08-16 | Design |  | Rob Short | Central Body | Removal of requirement MHHSP-BRS014-ECS-BR-RD-018 Meter Indicator is not sent to MDS as per DES138 | Update to process map and removal of requirement required as MDS do not need the [MUMIndicator] as shown in routing in DES138 |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Removal of requirement MHHSP-BRS014-ECS-BR-RD-018 and update to BP010 to remove from swim lane | ECS requirements | Supporting Docs | Business Requirements Documentation | BRS014 BP010B step 620 BPD010
MHHS-DIN-1109 | PP |  | 2024-08-16 | Design |  | Paul Pettitt | Software Provider | Guidance Note Required | Create Guidance note covering the population of the Consent granularity following defect 38353 |  | Closed |  |  | Clarification - No change required | [7 empty] | Closed as no further clarification required following resolution of defect 38353. The Metering Service receives the Consent Granularity effective from date obfuscated as per DES-138 | Guidance | Guidance | Guidance | Guidance note
MHHS-DIN-1110 | RG |  | 2024-08-20 | Design | 74698 | Richard French | Software Provider | Incorrect version number | Incorrect version number on IF-033, shows 009, should be 011 in DES-138 |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Minor update in DES-138 | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1111 | RS | Defect 37939/37984 | 2024-08-20 | Design |  | Richard French | Software Provider | Further explaination regarding same day/retro appointment of MS/DS | IF-036 has current statement - Depending on the actions of the Supplier, Blocks B16/B17 may not always be known to the Registration Service at the time IF-036 is published. As there is no re-publication Service Providers may need to reference EES(Ecoes) or liaise with their appointing Supplier for confirmation of any missing Partner Service. |  | Assessment Complete / Implementation Deferred |  |  | Clarification - No change required |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Further explaination to be added to IF-036 note in DES138 | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1112 | SB | Defect 39963/38352/39202 | 2024-09-03 | Design |  | Steve Bradford | Central Body | Correlation ID for Related/Linked MPANS Within PUB-036 | The IF-036 does not have the ability to populate a correlation ID for a Linked/Related MPAN. New event codes maybe required for LINKED/Related scenarios additionally a similar issue has been identified with the IF-008 |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.4 |  |  | Interim Release 8.4 |  | Updated DES138 routing table and population notes covering IF-036 to show the inheriting of correlation ID's for Related and Linked/Import MPANs | Data interface correction | Interface Documentation | Interface Documentation | DES-138
MHHS-DIN-1113 | SB | Defect 39989 | 2024-09-03 | Design |  | Steve Bradford | Central Body | REP-901 Error in the swagger Regex pattern | When producing the report for an Export tariff the following field: Data Block: R901-08 Data Item: totalVolumeChargeForChargeBand is generating a negative number. According to the RegEx pattern in the Schema a negative value is not allowed, despite the fact that the example value is a negative: |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.3 |  |  | Interim Release 8.3 |  | Amendement to Swagger to allow for the Data Block: R901-08 Data Item: totalVolumeChargeForChargeBand to be amended to include the ability for a negative to be allowed. Update the regex pattern for DT-032-Decimal-14-2, DT-031-Positive-Decimal-2-2 and DT-033N-Decimal-15-5 (unused at present) |  | Interface Documentation | Interface Documentation | Swagger
MHHS-DIN-1114 | SB |  | 2024-09-03 | Design |  | Steve Bradford | Central Body | Clarification On Boolean definitions | Following a number of Defects being raised in SIT Inconsistent applications of Boolean have been idnetified in various parts of the design. The lack of consistency is causing implementation issues for Participants |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.3 |  |  | Interim Release 8.3 |  | Amend design artefacts to align with the agreed Boolean definition as per Swagger and guidance documentation. DI-021 = changes to DES-138 (IF-001 and IF-002) DI-022 = changes to DES-138 (IF-001 and IF-002) DI-030 = changes to DES-138 (IF-001, IF-013, IF-016, IF-018, IF036) and ERI011b (REP-901) DI-127 = changes to DES-138 (IF-001, IF-002, IF-018, IF-033, IF-036, IF-043, IF-044 and IF-050) DI-357 = changes to ERI011b (R003 and R003A) DI-486 = changes to ERI011b (REP-002, REP-002a and REP-002b) DI-567 = changes to ERI011b (REP-900) DI-837 = changes to DES-138 (IF-031, IF-032, IF-033, IF-034 and IF-035) |  | Interface Documentation | Interface Documentation | DES-138 Swagger ECS Reporting
MHHS-DIN-1115 | SB |  | 2024-09-03 | Design |  | Steve Bradford | Central Body | DI-988 Replay Indicator Amend to Mandatory No Nulls to align with DIN-1114 | The DI-988 is currently set to Mandatory Nullable, as part of the DIN-1114 alignment would be to amend this to Mandatory no nulls |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.3 |  |  | Interim Release 8.3 |  | Amend design artefacts to align with the agreed Boolean definition as per Swagger and guidance documentation. DI-021 = changes to DES-138 (IF-001 and IF-002) DI-022 = changes to DES-138 (IF-001 and IF-002) DI-030 = changes to DES-138 (IF-001, IF-013, IF-016, IF-018, IF036) and ERI011b (REP-901) DI-127 = changes to DES-138 (IF-001, IF-002, IF-018, IF-033, IF-036, IF-043, IF-044 and IF-050) DI-357 = changes to ERI011b (R003 and R003A) DI-486 = changes to ERI011b (REP-002, REP-002a and REP-002b) DI-567 = changes to ERI011b (REP-900) DI-837 = changes to DES-138 (IF-031, IF-032, IF-033, IF-034 and IF-035) |  | Interface Documentation | Interface Documentation | Swagger DES-138
MHHS-DIN-1116 | PP |  | 2024-09-04 | LDSO |  | Paul Pettitt | Central Body | CR054 Updates to Non-Functional Requirement | Updates to NF requirements to reflect the original volumes included GAS metering that needs to be removed, Removal of a duplicate requirements, and definition of 'All Service' | CR054 | Implemented |  |  | Error/Correction |  |  | Interim Release 8.3 |  |  | Interim Release 8.3 |  | Update the Non-functional requirements document E2E002 with updates as approved in CR054 |  | Non-Functional Requirements Documentation | Non-Functional Requirements Documentation | E2E002
MHHS-DIN-1117 | SB | 39966 | 2024-09-04 | Helix | 75833 | Nigel Rees | Central Body | Duplicate consumption data for LSS and MDS roles | We have come across an anomaly in our testing. We have registered for interfaces for both LSS and MDS including the Consumption interface. We are receiving duplicate consumption messages which will mean double the already significant consumption load in production. We believe we need to register the interfaces for both LSS and MDS roles so people querying the DIP can audit flows for both roles. Obviously receiving duplicate data is inefficient and costly. It will also mean our performance tests at current levels are invalid. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.3 |  |  | Interim Release 8.3 |  | Update the Always routing of the IF-21 to only go to the Role LSS, to amend DES138 IF-021 |  | Interface Documentation |  | DES-138
MHHS-DIN-1118 | ZH |  | 2024-09-04 | Design | 77726 | Dave Webster | Software Provider | DES-138 Typo in IF-023 | The definition of an IF-023 in DES138 v5.8.2 has the following: DI-045 Load Shape Day Peak Total The sum of Period Values (kWh) for settlement periods (15 to 48) or (1 and 16 to 48). UTC times 7pm – Midnight DI-044 Load Shape Day Off-Peak Total The sum of Period Values for settlement periods (kWh) (1 to 14) or (2 to 15). UTC times Midnight -7pm These should say 7am rather than 7pm. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update DI-045 and DI-046 where it says "7pm" to "7am" in the description field for IF-023 | Data interface correction | Supporting Docs | Interface Documentation | DES-138
MHHS-DIN-1119 | RG | DIN-1056 | 2024-09-06 | EDW Tech | 76498 | Mark Kenny-Jones | Software Provider | GSP Group ID & LDSOBillingSiteID should be mandated for the R900-03 block | Previously LDSOBillingSiteID was removed from the required list for the R900-4 block (DIN-1056), the required field should have been moved to the R900-03 block. GSP Group Id needs to be marked as required too. |  | Implemented | [5 empty] | Interim Release 8.3 |  |  | Interim Release 8.3 |  | Update swagger to include LDSOBillingSiteID in the required field for R900-03 | Data interface correction | Interface Documentation | Interface Documentation | Swagger
MHHS-DIN-1120 | RG |  | 2024-09-09 | Design |  | Rob Golding | SRO Design | Duplicate DT033 | At present there are two DT-033s defined in the Data Type Catalogue: DT-033-Decimal-15-5 & DT-033-Email. DT-033 E-mail will moved to DT-036. DI-600 on the REP-900 tab is not aligned with the Data Catalogue - REP-900 DI-600 to be updated to String19. |  | Implemented | [5 empty] | Interim Release 8.3 |  |  | Interim Release 8.3 |  | Swagger update DT-033-Email to DT-036-Email. ERI011B has been updated to change DT-033 to DT-036 for DI-533. | Data interface correction | Interface Documentation | Interface Documentation | Swagger, ERI011B
MHHS-DIN-1121 | RS |  | 2024-09-10 | Elexon | 78399 | Colin Berry | Central Body | No associated Enumeration Value for DI-143 'Proposed Appointment Response Code' | The DI-143 ‘Proposed Appointment Response Code’ is defined in the ‘Data Catalogue’ tab in DES138 v5.8.2 as “String(200)”, with no associated Enumeration Values required (“ENUM Y/N” = N) and the “EXAMPLE” is given as ‘SP000’ and the “String Format” is given as ‘XXnn’, which is not consistent with “String(200)”. |  | Assessment Complete / Implementation Deferred | [5 empty] | Post Go-live Release |  |  | Post Go-live Release |  | Add Enumeration values to DI-143 as outlined in IF-033 | Data interface correction |  | Interface Documentation | DES-138
MHHS-DIN-1122 | ZH |  | 2024-09-10 | Design | 78142 | Kamlesh Patel | Central Body | Duplicate requirement reference used in BRS003 | There are two requirements "MHHS-BR-RS-071.13" in the latest BRS003 document |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update the requirement that references step 340 with a new number e.g. "XX.132" | Document Correction | Meter to Bank | Business Requirements Documentation | BRS003 BPD010
MHHS-DIN-1123 | MF |  | 2024-09-13 | Design |  | Dave McLean | Metering Service Provider | Removal of Obfuscation for IF-035 [IMS-SendMTD] in DI-800 | Remove the obfuscation for Service Provider Appointment Scenario (DI-800) from IF-035 so that the Metering Service can distinguish a Change of Segment Appointment when no MTDs are required. |  | Implemented | [5 empty] | Interim Release 8.3 |  |  | Interim Release 8.3 |  | Remove DIP obfuscation from DI-800 in IF-035 | Data interface correction | Interface Documentation | Interface Documentation | Swagger, DES-138
MHHS-DIN-1124 | TR |  | 2024-09-17 | Elexon | 76217 | Rashmi Radhakrishnan | Central Body | VPSR - Business Rule | C05 and DF4 - As the Switch events are data type ‘Time’ you cannot have Timer (Off), PECUS (Off) in that field. |  | Assessment Complete / Implementation Deferred | [5 empty] | Post Go-live Release |  |  | Post Go-live Release |  | Add the following Business Rule to ISD Entities Spec: Where a Switch Event is ‘NULL’ but followed by a % Power Level that is not ‘NULL’ then it is deemed that a Switch Event has occurred driven by the Timer or PECUS. | Missing validation rule | ISD | ISD | ISD Entities Document
MHHS-DIN-1125 | ZH | Non SIT LDSO defect 48823 | 2024-09-23 | MHHS | 80549 | Natasha Tomic | Central Body | Incorrect requirement: MHHS-BR-MS-026 | The following requirement (MHHS-BR-MS-026) should be removed from the MHHSP-BRS002-Metering Service requirements v5.6.xlsx (sharepoint.com) on the UMSO tab as it is not applicable for UMSO role. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.9 |  |  | Interim Release 8.9 |  | Update Metering Service Requirments to remove MHHS-BR-MS-026 from the UMSO tab | Document Correction | Meter to Bank | Business Requirements Documentation | BRS002
MHHS-DIN-1126 | RG | 40889 | 2024-09-25 | Energy Assets |  | Thomas Johnson | Software Provider | Incorrect event code used in IF-015/16 - documentation update | There is a descrpancy between the IF-015/016 design note and Swagger/DES-138. The design note has an event code of [RequestRejected] in DES138/Swagger [ConsumptionRequestRejected]. Design note needs to update to match swagger/des138 |  | Closed |  |  | Error/Correction | [7 empty] | We do not update DIP Design Notes or release them to Participants | Document Correction | Interfaces | Design Note | IF-015/016 Design note
MHHS-DIN-1127 | RS |  | 2024-09-26 | MHHS | 81161 | Kamlesh Patel | Central Body | Incorrect requirement: MHHS-Migration-CoA(MS)-RS-006 | The following requirement (MHHS-Migration-CoA(MS)-RS-006) should be removed from the Migration requirements (DEL974 Registartion Service tab) as it is not applicable for REGS to send the MS variant to ECS |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Remove requirement MHHS-Migration-CoA(MS)-RS-006 | Document Correction | Migration Requirements | Business Requirements Documentation | DEL974 Migration Design requirements log
MHHS-DIN-1128 | MF | Defect 39963 | 2024-09-26 | SCS |  | Madison Layton | Software Provider | Null correlation ID's on IF-008 | Update Correlation ID section and notes for IF-008 to highlight that where an unsolicited IF-008 is issued the correlation ID will be null (ie not copied as there is no IF-007 to copy it from ) |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.4 |  |  | Interim Release 8.4 |  | Update DIP to allow Null correlation ID's for IF-008 and update DES138 to show that a null correlation ID may be issued where an unsolicited IF-008 is issued | Data interface correction | Interface Documentation | Interface Documentation | DES-138 DIP-050
MHHS-DIN-1129 | RG |  | 2024-09-27 | Avanade |  | Piotr Penar | Software Provider | Add validation end-points for all REPs | Avanade have requested that the validation end-points are added to the swagger |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update swagger to include the extra valdiation end-points | Data interface correction | Swagger | Interface Documentation | Swagger
MHHS-DIN-1130 | TR |  | 2024-10-02 | Design |  | Tamsyn Robertson | SI Design | SDS Method 7 additional scenario coverage | Method 7 should be used for non-smart meters with switched load, smart meters non-comms with switched load where historical data is available or opted out smart meters with switched load.Currently, the smart meters non-comms with switched load where historical data is available scenario is missing from Method 7. |  | Open - awaiting assessment | Yes | 40588 | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Add the smart meters non-comms with switched load where historical data is available scenario to Method 7 | Missing scenario | Method Statement | SDS Method Statement | METH001 (SDS)
MHHS-DIN-1131 | TR |  | 2024-10-02 | Helix | 68335 | Rashmi Radhakrishnan | Central Body | Data Tye update - DUoS Tariff Domestic Premise Indicator | An LDSO expressed concerns about including this, given they are not responsible for providing this data, it was agreed to raise a DIN to modify the "DUoS Tariff Domestic Premise Indicator" to a one character from Boolean to include True/False/NULL option. In cases where the data is unavailable, NULL can be used as the value, and agreed that this change can be developed after post-go-live (after M10). Supporting NULL as an option will be used for NHH export tariffs. |  | Assessment Complete / Implementation Deferred | [5 empty] | Post Go-live Release |  |  | Post Go-live Release |  | "DUoS Tariff Domestic Premise Indicator" to be updated to an optional 1 Char Data Type. Acceptable values = T, F or NULL. |  | ISD and Reporting |  | ISD (Entity 17) ERI011b
MHHS-DIN-1132 | SB |  | 2024-10-03 | Callisto | 82101 | Christie Pace | Data Service Provider | Migration requirement & design Misalignment | There appears to be a miss alignment with DEL974 Requirements v1.2 log and DEL961 Migration design document v1.4. MHHS-RMigration-CoA(DS)-DC-005 still holds previous values for Reading Type and Meter reading Reason Code for the D0010. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update Migration Design requirements to align to Migration Design Document as per DIN-413. (ie remove reference to Meter Reason Reading Code)
MHHS-DIN-1133 | RG | Defect 41296 | 2024-10-07 | BUUK |  | Stuart Riding |  | IF-020 event codes are duplicated in IF-020-RelatedCreate | BUUK have a query against IF-020. Its's not causing an issue as all the messages for the event codes RelatedCreate, RelatedAdd, RelatedRemove will all resolve to the same structure as they are all identical. However, it does not align to the design pattern we have adopted elsewhere in the swagger definitions where each event code is explicitly defined. |  | Closed |  |  | Error/Correction | [7 empty] | Closed - duplicate of DIN-1059 Update swagger to remove the RelatedAdd & RelatedRemove event codes from the IF-020-RelatedCreate variant | Data interface correction | Swagger | Interface Documentation | Swagger
MHHS-DIN-1134 | TR |  | 2024-10-07 | C&C | 85111 | Hazel Cotman | Software Provider | Invalid UMSO Requirements | MHHS-BR-MS-041 and MHHS-BR-MS-042 are not applicable to Unmetered MPANs. These are to be removed from the UMSO requirement set. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update Metering Service Requirments to remove MHHS-BR-MS-041 and MHHS-BR-MS-042 from the UMSO tab | Requirement Clarification | Requirements | Metering Service Requirements | BRS002-Metering Service requirements
MHHS-DIN-1135 | SB | DIN1128 | 2024-10-11 | SCS |  | Madison Layton | Software Provider | Null correlation ID's on IF-035 | Update Correlation ID section and notes for IF-035 to highlight that where an unsolicited IF-035 is issued the correlation ID will be null |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.4 |  |  | Interim Release 8.4 |  | Update DES-138: Correlation ID section and notes for IF-035 to highlight that where an unsolicited IF-035 is issued the correlation ID will be null | Data interface correction | Interface Documentation | Interface Documentation | DES-138
MHHS-DIN-1136 | MF | DIN 1106 Defect 37835 | 2024-10-11 | RECCO |  | Sarah Jones | Central Body | Incorrect update to B075 block in DES138 | In fixing defect 37835 under DIN 1106 an incorrect update was made to DES138. The MAP block will always be provided by the Registration Service where a meter is provided. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.5 |  |  | Interim Release 8.5 |  | Update DES138, B075 block in interfaces IF-002, IF-006, IF-020, IF-033 and IF-036 to state Mandatory for each Meter Provided | Data interface correction | Interface Documentation | Interface Documentation | DES-138
MHHS-DIN-1137 | MF |  | 2024-10-15 | Avanade |  | Grant Sutcliffe | Software Provider | Swagger update to enforce DIP validation on callbackURL | The DIP will provde an error if the callbackURL is not included in DIP channel pubconfig and status message config messages ( schema type WebhookConfig ). Update swagger to enforce population of this data item |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update swagger to make callbackURL as Mandatory in the API |  |  |  | Swagger
MHHS-DIN-1138 | PP |  | 2024-10-21 | RECCO |  | Jonny Moore | Central Body | Batching of ERDS to CSS Agent Appointment Files | An issue has been identifed whereby multithreading used by CSS Adaptors operated by Electricty Registration Data Agents (ERDAs) may switch the order of the messages and send the CSS00200 messages to the CSS in the incorrect order. There is no mechanism within the CSS to identify the order in which the messages should be received. | CR056 | Implemented |  |  | Change Request |  |  | Interim Release 8.5 |  |  | Interim Release 8.5 |  | roposed Changes to Operational Choreography Update to table 4.4 ‘Activity Required at Secured Active Window. Remove the actions ‘Registration Service Issues CSS Sync Message updating MDR’ and ‘CSS updates DCC of MDR’ from 20.00 – 21.00 window. Add ‘Registration Issues single CSS Sync Message (CSS00200) updating MDR and / or MS’ and CSS updates Smart DSP of MDR and / or MS’ into 20.00 – 23.00 window. Update to Section 7.0 ‘Out of Hours Processing’ CSS Messages Requirement to be updated to ‘Required to be issued as a messge file in the Secured Active Processing window on all Calendar Days. | Choreography Correction |  | Operational Choreography | Operational Choreography
MHHS-DIN-1139 | TR |  | 2024-10-22 | Energy Assets | 87773 | Andrew Ford | Data Service Provider | ADS Meter Advance Reconciliation | There are a couple of issues with both the Method and Code Drafting. There is no exchange between the ADS' so we need to redraft the wording in both documents. |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | There is no exchange between the ADSs so we need to redraft the wording in both documents to say something like 'initial register reading from the meter' and not refer to 'on site' or old ADS. Also the Code drafting refers to below CoP 10 whereas the drafting is for CoP10 meters
MHHS-DIN-1140 | SB |  | 2024-10-24 | RECCO | 85432 | Jonny Moore | Central Body | New Connections through Transition Period | Section 8.1.1 of DEL-961 covers how MPRS will default data on the D0217 / D0260 if the MPAN had never been present in Trad arrangements (so a MHHS new connection) this section does not state that all new MPANs must be created as MHHS. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.10 |  |  | Interim Release 8.10 |  | Add clarification to the Migration design to confirm all New Connections are created in the MHHS environment post go-live
MHHS-DIN-1141 | MF |  | 2024-10-24 | RECCO |  | Sarah Jones | Central Body | Data types are inconsistent for DT024 | Examples and the actual Data Types are inconsisent in the Reporting Catalogue to swagger for items marked as DT024 in the Reporting Catalogue |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update reporting catalogue to align with swagger for items marked as DT024 in the Reporting Catalogue. Update the examples to ensure they conform to the swagger definition | Technical corrrection | Supporting Docs | Interface Documentation | ECS Reports
MHHS-DIN-1142 | MF |  | 2024-10-24 | SCS |  | Madison Layton | Software Provider | Remove REGS validation for B018 block population | During SIT, due to data quality issues, it has become apparent that Registration Service cannot validate that a smart meter is present for Block B018 conditionality by checking that the DCC Service Flag (DI-025) is A. This is blocking valid IF-034 requests. This validation needs to be removed from REGS. Data Services are responsbile for ensuring an MDR is submitted when required for a Smart Meter. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.5 |  |  | Interim Release 8.5 |  | Remove the following IF-034 Interface note: Registration Service will validate that a smart meter is present for Block B018 conditionality by checking that DCC Service Flag (DI-025) is A | Data interface correction | Interface Documentation | Interface Documentation | DES-138
MHHS-DIN-1143 | TR | Defect 42420 | 2024-10-25 | SI Design |  | Tamsyn Robertson | SI Design | D0398 alignment to code | MDS Run Number (J2325) is no longer used and has been replaced in the D0398 by Run Number (J1087). This has been corrected in the code drafting, the design document needs to be brought into alignment |  | Implemented | Yes | 42420 | Error/Correction |  |  | Interim Release 8.5 |  |  | Interim Release 8.5 |  | Update required to the D0398. Run Number (J1087) to replace MDS Run Number (J2325). | Data interface correction | Interface Documentation | Interface Documentation | D0398
MHHS-DIN-1144 | TR |  | 2024-10-29 | Elexon |  | Jonathan Gill | Central Body | MDS Business Process - Minor Update | Step 130 has a disconnected arrow, this needs to be updated |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Step 95 should connect to step 130 via the 'and' | Business Process Model Correction | Process Model | MDS Business Process | BP019
MHHS-DIN-1145 | TR |  | 2024-10-29 | Elexon |  | Jonathan Gill | Central Body | VAS Business Process - Minor Update | Step 120 states "MDS produces performance assurance data" when it should be "VAS Produces Performance Assurance report. This is correct in the BPD |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Step 120 should state "VAS Produces Performance Assurance report" | Business Process Model Correction | Process Model | VAS Business Process | BP020
MHHS-DIN-1146 | TR | Defect 42700 | 2024-10-31 | SI Design |  | Tamsyn Robertson | SI Design | Missing Scenario Variant - D0010 | DEL1712 does not include the Supplier>ADS Scenario Variant. Consequently this is missing from the code drafting and not included within the DTC routing rules. |  | Implemented | Yes | 42700 | Error/Correction |  |  | Interim Release 8.5 |  |  | Interim Release 8.5 |  | Add Supplier>ADS Scenario Variant to D0010 in the DEL1712 MHHS impacts to BSC owned Data Flows | Data interface correction | Dflow | Dflow | DEL1712
MHHS-DIN-1147 | PP | 42818 | 2024-11-05 |  |  |  |  | IF-033 - Clarity of the state of SEG being for existing segment not proposed | This was a topic of conversation during the design phase and agreement was reached that when an IF-033 is issued and the scenario is SEG the DI-050 Market Segment Indicator is the current not the to be, the fact that you are being appointed as a Smart or Advanced data service will be the tell as to what the segment is changing to, this will also be indicated by the DIP ID used in the appointment. A SEG will not change a smart to smart or advanced to advanced and should be rejected if that is the case. Similarly on the rare occasion of a unmetered the DIP ID being appointed will be one of a UMSDS. As for guidance we can add a clarification into the DES138 IF-033 and knowledgebase. |  | Open - awaiting assessment | [5 empty] | Post Go-live Release |  |  | Post Go-live Release
MHHS-DIN-1148 | RS | Defect 42711 | 2024-11-06 | SI Design |  | Rob Golding | Central Body | Implementation of REGEX to REP003A | Add that REGEX pattern to the DataTypes.yaml schema docs in future schema versions |  | Assessment Complete / Implementation Deferred | Yes | 42711 | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Add agreed REGEX as per discussion on ADO defect |  |  |  | Swagger
MHHS-DIN-1149 | RS | 91711 | 2024-11-06 | PDA | 91711 | Richard French | Data Service Provider | Removal of Data Service receiving PUB-009 in the Operational Choreography document OPC_320 | PUB-009 is not routed to the data service as confirmed in DES138. Operational choreography document OPC_320 to be updated to remove reference to Data service as the Data service receive the PUB-037 to advise of disconnection |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | PUB-009 is not routed to the data service as confirmed in DES138. Operational choreography document OPC_320 to be updated to remove reference to Data service as the Data service receive the PUB-037 to advise of disconnection | Data interface correction | Interface Documentation | Interface Documentation | Operational Choreography
MHHS-DIN-1150 | RS |  | 2024-11-06 | National Grid | 90489 | Joe Keogh | Network Operator | Removal of statement regarding further updates for IF-019 LDSO Linked Import/Export Response Codes | Update to DES138 IF-019, removing the statement “This section will be populated further following the Code Drafting Requirements/Rules around Linking of Import and Export MPANs” This should of been removed under DIN-971 when codes agreed and put into design |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update to DES138 IF-019, removing the statement “This section will be populated further following the Code Drafting Requirements/Rules around Linking of Import and Export MPANs” This should of been removed under DIN-971 when codes agreed and put into design | Data interface correction | Interface Documentation | Interface Documentation | DES138
MHHS-DIN-1151 | RS |  | 2024-11-08 | CGI | 91117 | Dave Webster | Software Provider | DI-152 to be updated to include .nnn | DI-155 currently has String format of nnnnnnnnn and example of 2500.000, however should follow MHHS Data type DT-016 string~14 nnnnnnnnn.nnn |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update DI-155 to follow MHHS Data type DT-016 string~14 nnnnnnnnn.nnn in DES138 | Data interface correction | Interface Documentation | Interface Documentation | DES138
MHHS-DIN-1152 | TR |  | 2024-11-11 | SCS | 92672 | Madison Layton | Software Provider | OPC001 IF-040 Routing Error | Registrations Service does not consume IF-040 but it’s been listed in OPC_061 |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Remove reference to REGS in OPC_061 | Requirement correction | Operational Chorography | Operational Chorography | OPC001
MHHS-DIN-1153 | TR |  | 2024-11-11 | EON | 88065 | Helen Banks | Supplier | ERI011b End State Settlement Runs | II (Interim Initial) is missing from the end state list |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | ERI011b references to End State List to be updated to include II run | Reporting Correction | Reporting | ECS Reports | ERI011b
MHHS-DIN-1154 | MF |  | 2024-11-11 | SCS |  | Madison Layton | Software Provider | IF-005 IHD Advance segment validation | Switch off REG1022 Advance segment IHD validation as this is preventing IF-005's being successfully submitted for a Smart Change of Segment |  | Implemented | Yes | 42570 | Error/Correction |  |  | Interim Release 8.6 |  |  | Interim Release 8.6 |  | Remove REG1022 Advance segment IHD validation from IF-005 in DES138 | Data interface correction | Interface Documentation | Interface Documentation | DES138
MHHS-DIN-1155 | TR |  | 2024-11-19 | Helix | 93701 | Rashmi Radhakrishnan | Central Body | Update to MHHSP-EM021 ISD Entity Map | We identified the need to update the MHHS baseline document MHHSP-EM021 ISD Entity Map v5.0.xlsx as some of the entities listed as FROZEN but it shouldn’t be. Currently, Annex S4 lists only four MDD entities that require updates between M10 and M16. However, Elexon believes there are additional MDD entities that may also fall into this category. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.7 |  |  | Interim Release 8.7 |  | Updates to MHHSP-EM021: Settlement Day, Yearly Season Details, Settlement Calendar, Settlement, Default Profile Coefficients and GSP Group Correction Scaling Facto MDD entities to be updated to be frozen at the end of migration. | Requirement correction | ISD | ISD Entity Mapping | MHHSP-EM021 ISD Entity Map MHHS-DEL1726-BSC-Section_ S_Annex_S-4v0.5 Transition_Rules
MHHS-DIN-1156 | PP |  | RecCo |  | 94862 | Jonny Moorw | Central Body | Missing CR056 update in Migration Threshhold Document | As noted in the text of CR56, changes to the Migration Threshold Document are required to recognise that CSS will now only receive one CSS02000 message per migration rather than two. This is important as the Migration Threshold Document will be designated as part of the ‘Migration Plan’ referenced in Code and the CSS Migration Requirements also point to this document. | CR056 | Initial Assessment/Updating |  |  | Error/Correction |  |  | TBC |  |  | TBC |  | Migration Threshold Document will be updated to reflect that CSS will now only receive one CSS02000 message per migration rather than two.
MHHS-DIN-1157 | TR |  | 2024-11-20 | Itron | 94107 | Gregg Stuart | Metering Service Provider | Advanced Load Shaping to be separated from Reactive Power within ADS Method Statement | There is a section heading missing from the Method Statement (and BSCP702), which make it seem like 2.45 and 2.46 relate to Reactive Power - this is incorrect. Sections 2.45 and 2.46 should have their own heading 'Advanced Load Shapes'. Advanced Load Shaping is used in Standard Methods g and h. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.6 |  |  | Interim Release 8.6 |  | Sections 2.45 and 2.46 should have their own heading 'Advanced Load Shapes'.
MHHS-DIN-1158 | RS |  | 2024-11-27 | Ensek | 92077 | Ed Hall | Software Provider | Event Code DI-999 on PUB-041 in reply to the Suppliers COR | Under the current design for the Data Service would need to populate the DI-999 with ReadingOnSite in reply to the Suppliers ReadingCOR, it is possible that the ReadingCOR should be made available for the DS event |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Include ReadingCOR for DS Event code for IF-041 in DES138 | Data interface correction | Interface Documentation | Interface Documentation | DES138
MHHS-DIN-1159 | RS |  | 2024-11-27 | RECCo | 92859 | Jonny Moore | Central Body | Validation Rule REG1044 States ‘SSC must be a valid value in ISD’ however the SSC is not included with the ISD data set. | REG1044 should remove any reference to ISD in both the introduction tab and IF-025 in DES138 |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | DES138 to be updated as follows: The note on the IF-025 will state the following: For the avoidance of doubt validation will be based on the 'frozen MDD table' and will be on Profile Class and SSC values in isolation (i.e. no PC-SSC Combination checks). ​REG1044 will state the following on both the IF-025 and the introduction: if [DI-123] does not exist in [ISD.SSC_Valid_Set] REG1044 - SSC must be a valid value in ISD | Data interface correction | Interface Documentation | Interface Documentation | DES138
MHHS-DIN-1160 | TR |  | 2024-11-29 | UKPN | 95246 | Neal Medley | Network Operator | REP-900 structure (ERI011b and Swagger) | The DI-587 postcode is expected to be nullable but incorrectly recorded as a DT-007. |  | Open - awaiting assessment | [5 empty] | Post Go-live Release |  |  | Post Go-live Release |  | the Data Type associated with DI-578 should be DT-007N in ERI011b and Swagger | Reporting correction | Reporting | Reporting | ERI011b Swagger
MHHS-DIN-1161 | RS |  | 2024-12-16 | ESG | 99426 | Patricia Parker | Software Provider | PUB_036 - DI-800 = ALG - Swagger not in line | ALG is only applicable to DI-800 in the PUB-036 in DES138, however it is incorrectly listed under that field on Swagger for IF-031. The IF-031 ALG should not form part of DI-800 as the alignment is initiated by REGS |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Removal of ALG for DI-800 in IF-031 in swagger | Data interface correction | Interface Documentation | Swagger | Swagger
MHHS-DIN-1162 | TR |  | 2024-12-20 | Itron | 99458 | Gregg Stuart | Data Service Provider | Differences between BSCP502 & 702 (and method statement 002) | There is a discrepancy between the wording of BSCP502, BSCP702 & Method statement 002. The first paragraph of 4.8.1 which is the established way of working with integral outstation meters. BSCP702 does not make this distinction and so potentially places an workload on the ADS to perform the on-site MAR depending on interpretation, one which is unjustifiable in terms of cost & manpower to any market participant. BSCP502 further clarifies the comparison check tolerances under a different section. Method statement 002, makes no distinction between (mini)-MAR (section 4.1.5 of BSCP502) which has a different set of tolerances or a site visit MAR, further confusing the situation. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.8 |  |  | Interim Release 8.8 |  | Alignment with existing processes (BSCP 502). Wording to be confirmed.
MHHS-DIN-1163 | SB |  | 2024-12-23 | UGP | 98697 | Ben Wetherill | Supplier | BP-011 Process Description and Diagram | BP-011 process indicates in Step 80, that the LDSO will issue commissioning D flows to the metering service, referencing both the D0383 and the D0384. My understanding of the current world is that the LDSO should only be responsible for issuing the D0383. |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Remove reference to D0384 from BP-011 step 80 as this is incorrectly referenced as routing does not allow this to be sent from DNO to Metering Service. This has been checked in the code drafting which only references the D0383.
MHHS-DIN-1164 | SB |  | 2024-12-23 | CGI | 96045 | Dave Webster | Consultancy | D0383 from MOP to MSA | The Business Process Map for “MHHS-DEL963 - BPM-002 - Change of Service - Metering Service - Forward Migration v1.2 .pdf” show the D0383 being sent from “Metering Service (Old) / Outgoing MOP” to “Metering Service (New)”: There is no mention of the D0383 being sent in a forward migration scenario within the “MHHS-DEL961 - Migration Design Document v1.4.pdf”. The “D0383 - Pre Transition Release - Notification of Commissioning Information.pdf” has new SVs but does not have one for MOP to MSA. Please can you confirm whether the MOP should be sending D0383 to the MSA on a Forward Migration. All the above is also relevant for the D0384, so please can you also confirm the same for D0384. |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Align DEL-963 with the business process map BPM-002 referencing the D0383/D0384 flows being required for forward migration. Also review the Transition Release - Notification of Commissioning Information.pdf” to determine if this should also have the new SV for MOP to MSA
MHHS-DIN-1165 | SB | Testing Defect 46477 | 2025-01-07 | Ensek |  | Jothi Varutharajan | Software Provider | CR-044 Alignment of data flows | Following implementation of CR-043 it has been identified that changes that are required to D0294/D0295 & D0297 have not been made to the DES-196 document. This was picked up as part of SIT testing | CR044 | Implemented |  |  | Error/Correction |  |  | Interim Release 8.7 |  |  | Interim Release 8.7 |  | Amend DES-196 to align with the CR-043 solution for D0294/D0295, D0297 |  |  |  | DES196
MHHS-DIN-1166 | PP |  | 2025-01-08 | Design |  | Paul Pettitt | Programme | CR059 updates to the design | Following approval of CR059 updates to varios design artefacts to reflect the replacement of REP-020 with D0357 | CR059 | Implemented |  |  | Change Request |  |  | Interim Release 8.7 |  |  | Interim Release 8.7 |  | Following approval of CR059 updates to varios design artefacts to reflect the replacement of REP-020 with D0357 |  |  |  | DEL196 DES138 Business Process Docs ERI011b
MHHS-DIN-1167 | RG |  | 2025-01-13 | DM | 103832 | Liam Lowey | Imserv | 401 certificate/API key errors | The 401 response code is used to cover a range of different error conditions for the error around cert and authentication the ask is to programmatically differentiate between the scenarios as it observed that the DIP does already provide a message that we could use to do this. However, it’s not documented as part of the design and so of course could be subject to change in future. |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Avanade to improve the information produced from a 401 message |  |  |  | E2E Solution Architecure
MHHS-DIN-1168 | RS |  | 2025-01-20 | Design | 105154 | Nicola Farley | MHHS | Operational Choreography discrepancy | discrepancy in the Operational Choreography document. OPC_360 and OPC_370 both have LDSO listed as Processor but they don’t receive the IF-22 and IF-23. |  | Open - awaiting assessment | [5 empty] | TBC |  |  | TBC
MHHS-DIN-1169 | PP |  | 2025-01-27 | Design | 106687 | Paul Pettitt | MHHS | Missing REP-008 reference in BPD019 | BPD015 is meeing the reference to REP-008 on Step 105 |  | Assessment Complete / Implementation Deferred |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update to BPD-019 to include the reference to REP-008
MHHS-DIN-1170 | RG |  | 2025-01-31 | Design | 88477 | Nigel Roberts | Software Provider | Updates to CoCo | Nigels reports the CoCo needs to be aligned with current practive re certificate handling- see freshdesk ticket for details |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update CoCo and enduriong DIP Manger documents |  |  |  | CoCo
MHHS-DIN-1171 | SB |  | 2025-01-31 | ESG | 107098 | Patricia Parker | Software Provider | Operational Choreography Duplication of references | The following OPC's require reviewing as there appears to be some duplication in the operational choreography. OPC -120 & OPC-390 appear to be duplicated. |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release
MHHS-DIN-1172 | MF |  | 2025-01-31 | CGI | 103041 | Dave Webster | Software Provider | IF-041 routing | DES138 needs updating to show the IF-041 is secondary routed to the outgoing and incoming Supplier when sent by the Data Service to support sharing of COS reads where required. Also clarification on the sending of the IF-041 by Metering Service on a Change of Segment. Allow primary routing of IF-041 to the other Data Service where required when sent by a Data Service |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.8 |  |  | Interim Release 8.8 |  | Update DES138 IF-041 routing rules for SDS/DS to highlight that both the incoming and outgoing Supplier will recieve the read where required for a COS. Added primary routing to Data Service where required to cover routing from a DS to another DS during a COS/ Change of Service Provider. For a change of segment, clarification on IF-041 routing that meter removal reads need to be sent by the Metering Service prior to the segment change and install reads need to be sent after the segment change. | Data interface correction | Interface Documentation |  | DES138
MHHS-DIN-1173 | SB |  | 2025-02-04 | UGP | 104970 | Ben Wetherill | Supplier | BP-016 Consumption Amendment | The step description in the BPD states that at step 110 the supplier may receive the PUB-027 (From the DS):However, the interface ID column for step 110 in the BPD references the PUB-028, as does the diagram (And the interface catalogue shows that the IF-027 routing is from Supplier to the DS). |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | PUB-027 requires amending to PUB-028 in the instances identified in the BPD-016 step 110
MHHS-DIN-1174 | TR |  | 2025-02-17 | RECCo | 105967 | Sarah Jones | Central Body | Data Item Correction | The DES138 contain two data items for additional information – DI-093 and DI-120. Both are used in Swagger. DI-093 is Additional Information SiteVisit and DI-120 is Additional Information. |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | update the reporting catalogue to refer to DI-093 as Additional Information Site Visit as per existing Swagger definition. | Reporting correction | Interface Documentation |  | ERI011b
MHHS-DIN-1175 | TR | DIN-898 | 2025-02-17 | RECCo | 105967 | Sarah Jones | Central Body | REP-003 ECS/Swagger Alignment | DIN-898 was not successfully implemented. Only a change was made to ESC Report spec, Swagger was not updated. ECS and Swagger need to be aligned. |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Add DI-339 and DI-370 back into the respective blocks in the ECS. | Reporting correction | Interface Documentation |  | ERI011b
MHHS-DIN-1176 | TR |  | 2025-02-17 | RECCo | 105967 | Sarah Jones | Central Body | REP-080 (CR032 clarification) | ELEX REP-080 has been replaced by the revised P210 (CR032). This needs to be clear in the ECS document as it is currently confusing participants |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | ELEX REP-080 has been replaced by the revised P210 (CR032). ECS needs to be updated to signpost to the revised P210 | Reporting correction | Interface Documentation |  | ERI011b
MHHS-DIN-1177 | TR | 108951, 109443, 110877 | 2025-02-17 | EON | 108246 | EON | Supplier | Microbusiness Consent | ISD only allows a non-domestic customer to be settled HH in the combinations. Micro business customers may opt out of sharing HH data for settlement purposes if they do not take an agreed contract out as that makes them an “!old system Customer” under condition 47.4 (b), so for non-domestic suppliers not being able to do so will have an impact on our ability comply with this condition where requested |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.9 |  |  | Interim Release 8.9 |  | Update ISD Enties to note that non-domestic/import/opt out combinations only apply to micro businesses, otherwise it could be deemed to apply to any non-domestic site. | Requirement Clarfication | ISD |  | ISD Entities
MHHS-DIN-1178 | TR |  | 2025-02-19 | Programme |  | Matt McKeon | SI Design | ESC Solution Documents and ERI011b alignment | There are a number of misalignements between what has been documented in the Solution Documents(D0397, D0398, D0399, D0400, D0401, D0402, D0403, D0404) and ERI011b. This DIN seeks to cover the updates to the solution documents only. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.10 |  |  | Interim Release 8.10 |  | Update ECS Solution Documents to align with ERI011b | Reporting correction | Interface Documentation |  | D0397, D0398, D0399, D0400, D0401, D0402, D0403, D0404
MHHS-DIN-1179 | RS |  | 2025-02-25 | Migration Design | 112321 | Anna Davis | SI Design | Update to Service Provider Response Codes | Update to the service provider response codes - SP012 and SP013 have been added as Service Provider Response Codes on the IF-033 tab. |  | Open - awaiting assessment |  |  | Error/Correction | [7 empty] | Update to IF-033 |  |  |  | DES138
MHHS-DIN-1180 | RS | 48675 | 2025-02-26 | St Clements |  | Madison Layton | Central Body | Domestic Premise indicator being sent to incorrect Data Service on COS | Currently as part of the COS processes the IF-018 is being sent at the same time as secured active whenever a change of the DPI occurs. this could mean that the IF-018 is processed prior to the new agent being appointed meaning it is sent to the old de-appointed agent. The new DPI detail is included in the IF-001 and IF-36 for the incoming party |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.9 |  |  | Interim Release 8.9 |  | Removal of the IF-018 being sent in the COS scenario, placing reliance solely on the IF-001 and IF-036. Requirement MHHS-BR-RS-117 (registration requirement) to be updated to stipulate not to be included in COS | Requirement Clarfication | Requirements |  | BRS003
MHHS-DIN-1181 | RS | 48293 | 2025-02-26 | St Clements |  | Madison Layton | Central Body | Update to validation rules for IF-031 Linked and related | REG1038 and REG1039 are currently marked as NO for repeat for queue. As part ofthe defect triage is was noted by St Clements that both of these should be updated to a YES |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.9 |  |  | Interim Release 8.9 |  | Update REG1038 and 1039 Repeat for queue indicators to YES in IF-031 | Data interface correction | Interface Documentation |  | DES138
MHHS-DIN-1182 | TR |  | 2025-03-04 | Helix |  | Riccardo Lampini | Central Body | VAS Method Statement Update | clarify sign convention to be used in performing calculation in Section 14, point 3.24 of the VAS Method Statement |  | Open - awaiting assessment |  |  | Error/Correction |  |  | TBC |  |  | TBC |  | Add the following statement: "Where data is summed over all Consumption Component Classes ‘N’, where, in such summation, values associated with Consumption Component Classes associated with Third Party Generating Plant (AE) comprised in MPANs shall be subtracted and values associated with all other Consumption Component Classes shall be added." | Method statement correction | VAS |  | METH006
MHHS-DIN-1183 | RS |  | 2025-03-11 | Design | 113226 | Matt McKeon | Central Body | D0036 requires ADS SV | As part of the migration design (section 6.3.3) the D0036 is sent to the ADS on forward migration. This is also confirmed in Migration requirement MHHS-Migration-CoA(DS)-DC-001. There is currently no SV for ADS in the DTN for D0036 and DES196 also states not required post go-live |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.10 |  |  | Interim Release 8.10 |  | New SV to be added to DTN for D0036, DES196 to be updated to reflect D0036 continues for Migration | Data interface correction | Interface Documentation |  | DES196
MHHS-DIN-1184 | TR |  | 2025-03-12 | Design | 114155/114811 | Matt McKeon | Central Body | DES-196 Clarifications | DES-196 does show the new Scenario Variants (SV) for the D0170. It also shows that the D0265 is being replaced by REP-005. This is no longer the case, as LLF data now forms part of ISD. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.10 |  |  | Interim Release 8.10 |  | New SVs to be added to D0170 on REC change tab. D0265 to be updated to reference ISD | Design Clarification | Interface Documentation |  | DES196
MHHS-DIN-1185 | RS |  | 2025-03-13 | CGI | 114514 | Steve Thomas | Software Provider | IF-026 Events for Unmetered | DES138 shows certain Event codes being secondary routed to XDSC and XMSC for IF-026. The 'To Parties' include UMSDS and UMSO within this, however as unmetered, these events would not be applicable to UMSDS and UMSO |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Removal of UMSDS and UMSO from 'To Parties' row in IF-026 Des138. ADS/SDS, MSA/MSS to remain Remove MS requirement MHHS-BR-MS-066.6 in UMSO tab and adjust MHHS-BR-MS-066.6 to MSS/MSA in all MS requirements tab Remove DS requirement MHHS-BR-DS-130.6 in UMSDS tab and adjust MHHS-BR-DS-130.6 to ADS/SDS in all DS requirements tab | Data interface correction | Interface Documentation |  | DES138
MHHS-DIN-1186 | MF |  | 2025-03-18 | National Grid | 90489 | Joe Keogh | Network Operator | IF-020 Error Codes | Update DES138 IE001 error code in IF-019 to correct typo and allow flexible response to provide explanation for the rejection |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8.10 |  |  | Interim Release 8.10 |  | Update IE001 error message documented in IF-019 from: IE001 - Proposed Linkge Change Rejected to: IE001 - Proposed Linkage Change Rejected - <Explanation of why rejected> | Data interface correction | Interface Documentation |  | DES138
MHHS-DIN-1187 | RS |  | 2025-03-20 | British Gas | 115898 | Neil Strange |  | MHHSP ERI011B | Hi Design Team The ECS reports artefact ​xlsx icon MHHSP - ERI011B - ECS Reports - External v5.9.xlsx has the following link on worksheets MHHS-Rep-D0081 onwards (all DTN distribution pattern reports) https://mhhs-support.freshdesk.com/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx - this is broken – you get a 403 error – can you update/ correct please? |  | Open - awaiting assessment | [10 empty] | https://www.mhhsprogramme.co.uk/design/baselined-design-artefacts/mhhs-impacts-to-data-transfer-network-dtn-flows
MHHS-DIN-1188 | MF |  | 2025-03-24 | RECCO | 117785 | Sarah Jones |  | Sending of IF-035 [IMS-SendMTD] on Change of Segment | Update BP011 to add clarification that the IF-035 [IMS-SendMTD] message is sent by Registration for a Change of Segment. Confirm that Metering Services are not required to send MTDs when the scenario is SEG. |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Change the wording on BP011A between steps 155 to 160 from "Not Required for SEG" to "Although the IF-035 [IMS-SendMTD] message is sent by Registration Service, Metering Services are not required to issue MTD's for a SEG scenario."
MHHS-DIN-1189 | SB |  | 2025-04-11 | RECCO | 122887 | Jonny Moore |  | Inconsistencies in the Migration Thresholds Document | Inconsistencies as follows: The CSS Table states that two CSS02900 'Smart Metering RMP Synchronisation' messages are sent from the CSS into the DSP. Whereas the DSP is only receiving one message. The DSP table is correct and the CSS table requires updating to reflect only one CSS02900 message being sent. The DSP Table states that a CSS07000 message is received. This message is a confirmation of the CSS02900 and should be sent to the CSS. The Sent/Received column requires updating to show the message being sent. This is reflected in the CSS07000 message being received by CSS. The Registration Service (SMRS) sends the CSS00200 into CSS and also receives the CSS07000 acknowledgement. Neither of these messages are reflected in the Registration Service Table. |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Amend the MHHS Migration Thresholds Document section 9.6/9.7 as detailed.
MHHS-DIN-1190 | PP |  | 2025-04-23 | BG | 123286 | Neil Strange |  | Rep-900, the DI-087 -“Supplier DIP ID” error | The Data Item DI-087 Supplier ID in inconsistent, the Report REP-900 state its a string 5 where it should be a string 10 in accordanc with all other definition and swagger |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update the REP-900 report to align with a String 10 definition |  | Interrface documentation |  | ERI011B
MHHS-DIN-1191 | TR |  | 2025-04-23 | ESG/RECCo | 125187 | Particia Parker | RECCo | D0383 requirement to send to Supplier | documentation published by the MHHS programme and the REC say that the flow does go to the Supplier, we believe this documentation is incorrect and needs to be updated to remove any reference to the Supplier receiving the D0383 data flow |  | Open - awaiting assessment | No |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update MS Requirements and BP009 to remove reference to D0383 being sent to the Supplier | Requirement Clarfication | Change of Metering |  | BP009 and MS Requirements
MHHS-DIN-1192 | TR |  | 2025-04-23 | SI Design |  | Stuart Scott | SI Design | IF-021- MDS Method Statement/DES-138 misalignement | ECS1013 has been removed from DES-138 IF-021 spec. This creates misalignemnt between DES138 and the MDS Method Statement |  | Open - awaiting assessment | Yes | 53394 | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Update IF-021 tab: 1. reinstate row 69 2. remove row 70 | Requirement Clarfication | Interface documentation |  | DES138
MHHS-DIN-1193 | MF |  | 2025-04-25 | SRO Design |  | Mike Fensome | SRO Design | IF-003 routing mis-alignment | Update Migration requirements to align with DES138 as the LDSO's receive the IF-003[ReverseMigNotification] event code not [DSDeAppRM] and [MSDeAppRM] event codes. |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Remove requirements MHHS-RMigration-CoA(MS)-LDSO-001 and MHHS-RMigration-CoA(DS)-LDSO-001 | Requirement Clarfication | Migration requirements |  | Migration requirements
MHHS-DIN-1194 | MF |  | 2025-04-28 | SRO Design |  | Mike Fensome | SRO Design | Change of segment (Advanced to Smart) for Linked/Related MPANs | A workaround needs to be used for Change of Segment from Advanced to Smart where Linked or Related MPANs are in place as the Export MPAN is unable to be updated with the new metering details to cause the segment to change. The workaround involves de-linking the MPANs before carrying out the change of segment and then re-linking after. This DIN is to create an enduring fix so the workaround is not required and would allow Registration Service to accept the metering update for the Export/Secondary MPAN if their is a valid appointment in place for the Incoming Metering Service on the Import/Primary MPAN. |  | Assessment Complete / Implementation Deferred | Yes | 47469 | Error/Correction |  |  | Post Go-live Release |  |  | Post Go-live Release |  | Clarify requirements to confirm Registration Service can accept meter updates for a Change of Segment from the incoming Metering Service if a SEG appointment exists on the Import/ Primary MPAN. Also clarify that the segment change for both Import and Export MPAN are updated to Smart at the same time. | Requirement Clarfication | Registration requirements |  | Registration requirements
MHHS-DIN-1195 | RG |  | 2025-05-07 | DIP Manager | 128559 | Rob Golding | DIP Manager | Strictr structure for R0 block | Descrpancy between DIp and DIP simulatro highlighted thet the R0 block could have a tighter descrption to avaoid ambiguity |  | Open - awaiting assessment |  |  | Error/Correction | [5 empty] | Post Go-live Release |  | Update defn of R0 block in swagger |  | Swagger
MHHS-DIN-1196
MHHS-DIN-1197
MHHS-DIN-1198
MHHS-DIN-1199

## Introduction
Design Issue Notification Log
Summary Stats
Purpose
This document provides a record of the items raised for consideration by the Design Advisory Group along with their status through the assessment and subsequent approval process steps.
Note, this document a working document and will be regularly updated (targeting 1st and 10th working day of each month)
Prioritisation
Design Issues will be prioritised based on the following criteria:
Criticality to keeping the Programme on plan
Impact on multiple participants restricting entry into or completion of a milestone
Functional Area - updating design artefacts from the same design area e.g. MPAN Ownership, Meter to Bank
DIN to Artefact Alignment - updating design artefacts covering multiple notifications e.g. MHHSP-DES138 Interface Catalogue
Typographical errors
Design Review Process
A high level process has been included in TAB 'Design Update Process' this details the major steps that a DIN will go though from identification to implementation.
Release Schedule
A draft release schedule has been included in TAB 'Release Timeline'. this will be updated periodically to show progress.
Currently the schedule shows the next three releases know as 'Interim Release 1,2,3.....
We have allocated those DIN that have been or are being assessed to a release, Note this ordering may change should higher priority changes be required.
Industry Input Sessions
Where it is believed that a DIN requires a specific working group session, these have been highlighted against each of the DINs. The alignment of the session in relation to the prospective release has been considered but may change should the working session not reach agreement or higher priority changes be required
Current DIN Status
Each DIN has been categorised to one of the following

## Change History
Change History
Date | Reason for Change | Comments
2023-04-13 | Refreshed spreadsheet adding in new TABs for Introduction, Process and Timeline
2023-04-14 | Published to Collaboration Base
2023-04-19 | Added DINs 254 - 258
2023-05-17 | updated with latest view of DINs
2023-05-22 | Updated with DIN 290 - 305
2023-06-01 | Updated with DIN 306 - 368
2023-06-15 | updated to include new Fast-Track Process, Realignment of Releases, Objection window dates added
2023-07-03 | Updated with the latest DINs reflecting the proposed content of IR3
2023-07-06 | Updated the Status of IR2 Dins to implmented following deployment on the 5/7/23
2023-07-17 | Updated to include revised Objection dates and latest DINs. An extra Tab has been included to show differences from the previous DIN log Version
2023-08-01 | Updated to capture new DINs ahead of release of IR3, DIN log will be updated again on 3/8 folloing IR3 deployment
2023-08-03 | Updated Status to reflect IR3 implementation
2023-08-17 | Updated to reflect the current DIN status and closure of IR4 Objection window
2023-08-31 | Updated Status to reflect IR4 implementation and the latest DINs reflecting the proposed content of IR5
2023-09-07 | Update timeline to show release through to IR11
2023-09-15 | Updated to reflect new DINs solutions and stats
2023-09-22 | Updated to give the latest position following analysis on alignment of swagger and DES138 and update to the solution of a number of DINs
2023-10-05 | Updated Status to reflect IR5 implementation
2023-10-11 | Updated Status to reflect IR2.1 implementation
2023-10-18 | Updated Status to reflect IR5.1 implementation
2023-11-01 | Updated Status to reflect IR6 implementation
2023-11-10 | Updated Status to reflect IR2.2 implementation
2023-11-24 | Updated Release timeline Tab
2023-11-30 | Updated Status to reflect IR2.3 implementation
2023-12-14 | Updated Status to reflect IR5.2 implementation
2024-01-12 | Updated to capture new DINs ahead of release of IR5.3 and IR7. DIN log will be updated again on following IR5.3 deployment.
2024-01-19 | Updated Status to reflect IR5.3 implementation and to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday).
2024-01-26 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday) and to reflect IR5.4 DINs.
2024-02-02 | Updated Status to reflect IR7 implementation and to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday).
2024-02-09 | Updated Status to reflect IR5.4 implementation and to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday).
2024-02-16 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday).
2024-02-23 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday) and to reflect IR5.5, IR7.1 and IR8 DINs.
2024-03-01 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday).
2024-03-08 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday).
2024-03-15 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday) and reflect IR8 DINs.
2024-03-22 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday)
2024-03-28 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday) and reflect IR8, IR5.5 and IR7.2 DINs.
2024-04-09 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday) and reflect implementation of IR8, IR5.5 and IR7.2 DINs.
2024-04-15 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday)
2024-04-19 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday) | DIN-897: Description updated following discrepency found
2024-04-26 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday)
2024-05-03 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday)
2024-05-10 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday). | Including two new columns; "Who is impacted?" and "DIN Type" which will provide more details on each DIN
2024-05-17 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday).
2024-05-22 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday) and reflect latest updates to IR8.1.
2024-05-31 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday).
2024-06-14 | Update to show latest view of DINs as part of the DIN Log new weekly publishing (every Friday) and reflect latest updates to IR8.1.
2024-07-02 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-07-08 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-07-15 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-07-29 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-08-09 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-08-16 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-08-23 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-09-02 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-09-09 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-09-16 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-09-20 | Update to show latest view of DINs as part of the DIN Log new weekly publishing and reflect latest updates to IR8.3.
2024-09-30 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-10-09 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-10-11 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-10-18 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-10-28 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-11-01 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-11-08 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-11-15 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-11-22 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-11-29 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-12-06 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-12-13 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-12-20 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2024-12-27 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2025-01-03 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2025-01-10 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2025-01-17 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2025-01-24 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2025-01-31 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2025-02-07 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2025-02-14 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2025-02-21 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2025-02-28 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2025-03-07 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2025-03-14 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2025-03-21 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2025-03-28 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2025-04-04 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2025-04-11 | Update to show latest view of DINs as part of the DIN Log new weekly publishing.
2025-04-18 | Update to show latest view of DINs as part of the DIN Log
2025-04-25 | Update to show latest view of DINs as part of the DIN Log
2025-05-02 | Update to show latest view of DINs as part of the DIN Log
2025-05-09 | Update to show latest view of DINs as part of the DIN Log
2025-05-16 | Update to show latest view of DINs as part of the DIN Log
2025-05-23 | Update to show latest view of DINs as part of the DIN Log
2025-05-30 | Update to show latest view of DINs as part of the DIN Log
2025-06-02 | Update to show latest view of DINs as part of the DIN Log
2025-06-06 | Update to show latest view of DINs as part of the DIN Log
2025-06-13 | Update to show latest view of DINs as part of the DIN Log
2025-06-20 | Update to show latest view of DINs as part of the DIN Log
2025-06-27 | Update to show latest view of DINs as part of the DIN Log
2025-07-04 | Update to show latest view of DINs as part of the DIN Log
2025-07-11 | Update to show latest view of DINs as part of the DIN Log
2025-07-18 | Update to show latest view of DINs as part of the DIN Log

## DIN Log 230824 (hidden)
DIN ITEM DETAILS | [13 empty] | Internal Assessment |  |  |  |  | DIN IMPACT ASSESSMENT
Reference | Created BY | other Reference(s) | Date Raised | Organisation | Freshdesk Ticket # | Contact Name | Constituency | Title | Design Issue Notification Details (as notified by participant) | Related CR | Current Status | Testing Defect DIN? | Testing Defect Reference # | DIN Type | Who is impacted? | Target working Group Date (If Required) | Target Release | Objection Cut-off Date | Design Issue Proposed solution | Justification/Type of Change | Design Area | Design Area - L2 | Artefact(s) Impacted
MHHS-DIN-1 |  | T4-COM-1744 | 2023-01-30 | St Clements | 2655 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1744 on 15th Sept 2022 MPRS does not currently restrict IHD Installs to Smart Meters, there maybe cases where there is an IHD present but the Meter is Trad (Not compatible with DCC and Customer Switched) Either Allow IHD on all Market Segments OR Cleansing to ensure IHDs are only present on S2 and S1 Meters SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses, as this is still not resolved |  | Implemented | [5 empty] | Interim Release 1 |  | Discussed with SCS and agreed to add new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) Added requirements into BRS003. SCS to raise a potential data cleanse. | Requirement correction | MPAN Ownership | SCS Validation | MHHSP-BRS003-Registration Requirements
MHHS-DIN-2 |  | T4-COM-1745 | 2023-01-30 | St Clements | 2657 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1745 on 15th Sept 2022 DB002 is not the interface on which MPRS will be informed of a change to import/export relationship, it is DB05. The wrong diagram was updated, the EDI was updated to DB05 not import/export. SCS submitted an objection on 7th October 2022 to the closure of this comment following the comment responses and artefact updates, to inform the wrong data item diagram was updated. However the diagram for EDI updates is still incorrectly reading DB005 update instead of DB02 |  | Closed | [7 empty] | This appears to have been missed in v4.6 - the arrow on BP-010B from step435 to Step 440 shows DB005 (not DB05, assume that’s a minor typo in the comment) - and this is the Energy Direction Information (EDI) which is wrong. It has cbeen onfirmed that this was updated in v4.7 to go into v5.0 baseline. | No Change |  |  | None
|  | T4-COM-1752 | 2023-01-30 | St Clements | 2661 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1752 on 15th Sept 2022: MHHS-BR-RS-020: "Retro" (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier ) In the D0205 the Supplier can cancel out the current Agent Appointment by setting the EFD to equal the currently stored Appointment EFD. Is this no longer allowed? All Services must be appointed for at least one day valid or not? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: removing the ability for Suppliers to Correct Invalid Service Appointments may not be understood by suppliers. We want to avoid a later Design CR to add this functionality in. SCS has not had a response, feel this is important discuss with Suppliers to avoid later CRs |  | Closed | [7 empty] | The appointment can be resubmitted if it hasn’t been accepted yet. Once accepted, there is a need to maintain contiguous appointment periods. The scenario mentioned is the CoA not linked to a switch, so the acceptance of a new appointment from a particular EFD will ‘lock in’ that date and the previous MS/DS will be de-appointed at midnight on the previous day. This is to ensure that there are no periods left without MS and/or DS in place, which can happen today with D0155/D0151 sequencing issues. As an overall comment, there is not a concept of cancellation of appointments. The only way to alter the appointment is to get a new IF-031 issued. The only way to do this for the scenario presented, would be to issue an IF-031 for the old MS for the original date and an IF-031 for the new MS for the revised date. Requirement MHHS-BR-RS-021 ensures that Registration Service will action the latest received appointment where there are duplicate appointments for the same day. St Clements had requested that we build in a rule saying that you cannot submit a Change of Service Provider (CSP) request for the same Service Provider. It is a bit of a work-around, but we believe sending it as SEG should work, or alternatively a CR would be required to re-look at the interface validation. Closing, as this doesn't require further action - point noted. We have already spoken to a number of suppliers, and will continue to engage to ensure the functionality of the baselined design is understood and any issues picked up as early as possible. Documentation for LDSOs to point at. Pick up in Code Drafting as well. | No Change |  |  | None
MHHS-DIN-4 |  | T4-COM-1755 | 2023-01-30 | St Clements | 2666 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1755 on 15th Sept 2022: MHHS-BR-RS-071.2 REC CP R062 has been raised to remove the restriction on the number of EDI changes. Will this cause any downstream MHHS issues? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Needs to be aligned with REC Change No responses |  | Closed | [7 empty] | As per original SRO response, the impacts of the REC change need to be dealt with through the REC change process and impact assessment. | No Change |  |  | None
MHHS-DIN-5 |  | T4-COM-1760 | 2023-01-30 | St Clements | 2667 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1760 on 15th Sept 2022: There are no Registration Service Reports defined in MHHSP-ERI011A. Will there be a requirement for MPRS to produce any Industry Reports for MHHS? SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: Design for the complete solution must be defined by M5. This is a DBT Design Start Blocker No responses This could significantly increase DBT time as development of reports can be costly and time consuming |  | Closed | [7 empty] | Who is raising these requirements? What happens today? Possibly CC issues Agreed with SCS that reporting requirements will be introduced via the CR process. Reporting requirements are to be added to the programme RAID log | No Change |  |  | None
MHHS-DIN-6 |  | T4-COM-1761 DI-7 | 2023-01-30 | St Clements | 2668 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1761 on 15th Sept 2022: IF-005, REG1014 First MAP Block, MAP Eff From Date [DI-054] in message, must = MPAN Install date OR >= Eff Form date of all existing MAP Effective From Dates held in Registration prior to first [DI-054] in message I understand that the First MAP must equal the Install Date, I am unsure what the second condition is trying to say? You can not have a Meter Without a MAP. (ignoring customer owned meters where CUST is used) SCS raised objection to comment response on 7th October 2022 with following explanation: Objection: response is incorrect. The Second Rule "Each subsequent MAP Effective From Date [DI-054] must be > MAP Eff From Date in previous block" covers the subsequent overlapping MAPs. The second half of this First Block Rule must be removed. The First Block can only ever equal the install date No responses, the rule has not been amended |  | Implemented | [5 empty] | Interim Release 1 |  | This appears valid - the first MAP block can only start at the creation date (assuming the MAP blocks are in chronological order, which they must be if each subsequent map block has an EFD > the last) Currently the design allows 2 ways to amend the MAP History as outlined in Sections 13 and 14 of the IF005 Use Case Guide. Either the Metering Service can provide the full MAP history from the installation date or they can add a new MAP to the existing history, provided it is the next MAP in chronological order. So for example if you have MAPs 1,2 and 3, then you can extend to MAPs 1,2, 3 and 4 using the approach set out in section 14 to extend the MAP history. However if you wanted to set MAP 4 between 2 and 3, you would need to send the whole MAP history from the install date and provide 1,2,4 and 3 as set out in Section 13 to replace MAP history. The second validation rule is required if you are using the extend the MAP history functionality. Added note to REG Notes that where a MAP history is provided it must be in chronological order Added new REG1014 Validation Rule to MeterInstall and MeterExchange events to ensure only 1 MAP block is provided | Data interface correction | MPAN Ownership | SCS Validation | MHHSP-DES138-Interface Catalogue
MHHS-DIN-7 |  | DI-8, DI-11, DI-12, DI-14 | 2023-01-30 | St Clements | 2669 | Madison Layton | Software Provider |  | MPRS will reject any PUB-031 including those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8) |  | Implemented | [5 empty] | Interim Release 1 |  | See Comments Revised CSS Registration Request ID validation on IF-031, 034 and 025 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | IF General | MHHSP-DES138-Interface Catalogue
MHHS-DIN-8 |  | N/A | 2023-02-01 | Elexon | 2642 | Sedef Kiris | Central Body |  | We have had the following comment ........... Also just found out that “Metering Service Id” have “MPID” in brackets afterwards, and not “MSID”. We believe it should be MSID |  | Closed | [7 empty] | MPID is the correct term here, it is the metering service MPID. MHHSP_EDI012_ISD_Entities v4.6 Section M8 | No Change |  |  | None
MHHS-DIN-9 |  | N/A | 2023-01-30 | St Clements | 2672 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: [UpdateSiteTechnicalInfoMS] is not included in the interface catalogue and is not utilised by MPRS. Assume this is related to Issue 99 and needs removing? (raised as DI ID 9) |  | Implemented | [5 empty] | Interim Release 1 |  | Removed from IF-005 Guide Section 4.1 | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-10 |  | N/A | 2023-01-30 | St Clements | 2799/2670 | Madison Layton | Software Provider |  | Comment sent on 11th Jan: Is the currently appointed Meter Service informed of Prospective MS changes? Changes to MTDs can be made by prospective MS (e.g. change meter type to complete SEG market change before the MS can be appointed). As the MS is only prospective at this point the MS may still be lapsed and not take effect. However any MTD updates made would remain within the MPRS system and not be backed out. The current MS would therefore need to be aware of what changes have been made by the prospective MS. (raised as DI ID 10) |  | Closed | [7 empty] | BP009 only talks about the Metering Service, not the current or prospective Metering Service, and it appears only the registration service receive metering service MTD details, not the current MS. Refer to SRO - what is the assumption here, as the alternative route is for registration to update the current MS The design is based on PUB-006, with the Updated Meter details, being sent to the current Metering Service ( BP011A step 280 ) as well as the Prospective Metering Service (Step 275). It is built into the routing rules in PUB-006. | No Change |  |  | None
MHHS-DIN-11 |  | N/A | 2023-01-30 | St Clements | 2675 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install / Remove Date(s) takes place within the Metering Services period of ownership (or proposed period of ownership for in the case of a prospective SEG appointment) " Sent on 11th Jan: Does not match business rules, as future dated installs are not allowed: "REG1020 - Meter Install Date [DI-057] cannot take place in the future. The proposed MS on a seg will have a future dated EFD, so they only have the +2 day lapse extension period for meter installs (raised as DI ID 11) |  | Implemented | [5 empty] | Interim Release 1 |  | Added change of segment scenario's to IF005 USE CASE Guide. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-12 |  | N/A | 2023-01-30 | St Clements | 2679 | Madison Layton | Software Provider |  | Comment on Section 5.1 "• Metering activity, as determined by the Install /Remove Date(s), cannot have taken place in the future" Sent on 11th Jan: It would be useful to have the Change of Segment process covered in this guide. We are not sure how the Prospective MS can exchange meters when their appointment period is in the future (raised as DI ID 12) |  | Implemented | [5 empty] | Interim Release 1 |  | Nomenclature issue - requires a reword of this statement to conform to the business rules. Recommend the following update to section 3.2 of the IF005 Use Case Guide to confirm who can make Metering updates Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed BAU metering updates ( For the avoidance of doubt not meter update/meter history updates), it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. The one exception, is during a change of segment, when the incoming Metering Service is able to provide a BAU metering update, where it’s prospective “SEG” appointment is due to become active on the same day. SEG scenario's added to IF005 Use case guide Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-13 |  | N/A | 2023-01-30 | St Clements | 2683 | Madison Layton | Software Provider |  | Comment on Section 5.1 "validation allows for meter removal at a point following Disconnection if required)" Sent on 11th Jan: This rule prevents this REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational (raised as DI ID 13) |  | Implemented | [5 empty] | Interim Release 1 |  | This statement doesn't appear to be a convention. There is no mention of this in E2E001 End to End Solution Architecture. Believe this statement needs to be amended or removed. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. IF-005 validation Rule changed to include meter removal at status Disconnected | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES138-Interface Catalogue, E2E001 End to End Solution Architecture
MHHS-DIN-14 |  | N/A | 2023-01-30 | St Clements | 2684 | Madison Layton | Software Provider |  | Comment on Section 3.2 "Apart from a small window, currently defined as [10] days, at the end of a Metering Service’s appointment, to allow for recent or delayed metering updates, it is only the ‘currently appointed’ Metering Service that may make updates to the current and/or historic metering history stored in the Registration Service. " Statement is misleading- the 10 day period is only permitted for install, remove and exchange events, it is not listed for meterUpdate/meterHistoryUpdate in interface catalogue Also the prospective MS should be able to make changes for SEG to enable a market segment change to complete (raised as DI ID 14) |  | Implemented | [5 empty] | Interim Release 1 |  | Validation rule(s) updated to constrain 10 day window to non-update events. Test in 3.2 reworded to remove ambiguity. | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-15 |  | N/A | 2023-01-30 | St Clements | 2685 | Madison Layton | Software Provider |  | Comment raised in guide, sent on 11th Jan, that the JSON examples use MPID when it should use DIP ID e.g."distributorID": "SWAL" (raised as DI ID 15) |  | Implemented | [5 empty] | Interim Release 1 |  | Corrected to use Dist DIP ID | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-16 |  | N/A | 2023-01-30 | St Clements | 2686 | Madison Layton | Software Provider |  | Comment on Section 9 " Albeit that these transactions can be ‘clubbed together’ and send as a group in single overarching message/API transaction. " Sent on 11th Jan: As DIP does not protect the sequencing of events (FIFO), is there a risk that the ordering of these updates might arrive out of sequence resulting in the wrong end state? If MS space out their updates it would reduce this risk (raised as DI ID 16) |  | Implemented | [5 empty] | Interim Release 1 |  | Clairifcation added to Sec 9.2 to reference Time-Stamps rather than 'clubbing' | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-17 |  | DI-017 | 2023-01-30 | St Clements | 2690 | Madison Layton | Software Provider | MAP History availability to Metering Service | Section 9 says "a supporting MAP history commencing in line with the revised Installation Date must also be provided" Will the MS know the full MAP history? Risk they could destroy the data. Potential MAP billing issues? |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Solution agreed at DRG on what MAP updates are required. Various document updates required to align with DRG decision to only maintain latest MAP. Removed section 13 from IF005 user guide plus other corrections to doc. Updated DES138 IF005 validation rules. | Missing/incorrect validation rule | Supporting Docs | Various Documents | IF-005 Use Case guide MHHSP-DES138-Interface Catalogue
MHHS-DIN-18 |  | N/A | 2023-01-30 | St Clements | 2691 | Madison Layton | Software Provider |  | Comment on Section 9 "• When maintaining the MAP History in cases where there is no change in Meter Installation Date then the MAP history provided should commence either with a MAP Effective From Date matching the existing install date of the meter OR be greater than the most recent, already existing, MAP Effective From Date" Sent on 11th Jan: So it's possible to update ALL MAP history back to installation, or add a new MAP, but it's not possible to amend MAP history only part way back (have to go back to installation date instead every time to do this) (raised as DI ID 18) |  | Closed | [7 empty] | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • To update BRS003, requirement MHHS-BR-RS-027 to add “Registration Service must lapse any appointments that fail this validation” • Remove Rejected from Step 225 of BP002/BPD002 • Remove Rejected from label on line after step 215 of BP003. | No Change |  |  | None
MHHS-DIN-19 |  | N/A | 2023-01-30 | St Clements | 2692 | Madison Layton | Software Provider |  | Comment on Section 10 "E2E Architecture convention states that all data items are provided in each message even where these data items are not changing or are null" Sent on 11th Jan: Some of the items are optional not mandatory which conflicts with this statement. Not all data items need to be provided (raised as DI ID 19) |  | Implemented | [5 empty] | Interim Release 1 |  | Update of E2E Doc to allow for Nullable values. | Data interface correction | Meter to Bank |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-20 |  | N/A | 2023-01-30 | St Clements | 2693 | Madison Layton | Software Provider |  | Comment on Section 13, sent on 11th Jan: What should MPRS do if it holds a MAP not included in the MAPHistory block? (raised as DI ID 20) |  | Implemented | [5 empty] | Interim Release 1 |  | Update "all existing history will be replaced by that contained within the message" | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-21 |  | N/A | 2023-01-30 | St Clements | 2699 | Madison Layton | Software Provider |  | Comment on Section 15.2 "It is understood that currently there a numerous instances of duplicated Meter ID’s, some of which may have overlapping installation dates. " Sent on Jan 11th: Meter id is only unique at mpan. Should not be any instances of conflicted MSNs at MPAN. Can you verify with ECOES? Or we can do a RFI to DNOs but will take time (raised as DI ID 21) |  | Implemented | [5 empty] | Interim Release 1 |  | All references to duplicated MSN IDs has been removed from the document | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-22 |  | N/A | 2023-01-30 | St Clements | 2700 | Madison Layton | Software Provider |  | Comment on Seciton 15.3 "add some kind of suffix (X1, X2) to the existing Meter ID." Sent on Jan 11th: This can take the meter ID over the allowable string length (string 10), in this example it would take it to string(12) and so would be rejected (raised as DI ID 22) |  | Implemented | [5 empty] | Interim Release 1 |  | As above, Section 15.3 removed from IF-005 User Guide. | Data interface correction | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-23 |  | N/A | 2023-01-30 | St Clements | 2701 | Madison Layton | Software Provider |  | Comment on Section 16.3 Sent on Jan 11th: Cancelled Flag Set. Only a logical deletion. Still held in MPRS but not visible to EES/MEM The section implies the record would be fully deleted from MPRS, however this is not correct, MPRS would set a cancellation flag that would indicate the record has effectively been cancelled/logically deleted. It would however remain in the systems database (raised as DI ID 23) |  | Implemented | [5 empty] | Interim Release 1 |  | Added a statement at the end of the table in 16.3 to say "NB the registration service will only logically delete the MAP entry with a flag, it will not be deleted from the database." | Data interface correction | Meter to Bank | IF005 User Guide | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-24 |  | N/A | 2023-01-30 | St Clements | 2702 | Madison Layton | Software Provider |  | Comment on Section 17.2 "situations where multiple existing meters are identified, the selection process should be extended to include Meter Removal date (if provided) else;" Sent on Jan 11th: Shouldn’t be possible, can run an EES or MPRS RFI to confirm. Noting that MSN is only unique at an MPAN level not a databse level Related to DI-21 (raised as DI ID 24) |  | Implemented | [5 empty] | Interim Release 1 |  | Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. The wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | Meter to Bank | CSC Validation Rules | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-25 |  | N/A | 2023-01-30 | St Clements | 2706 | Madison Layton | Software Provider |  | Comment on Section 17.2 "where multiple meters still exist even after matching on all three data items should be rejected and require manual intervention (i.e. request to LDSO to intervene) ." Sent on Jan 11th: There's no super user functionality for this so how could the LDSO intervene? The LDSO is not able to manually intervene in regards to MTDs, they can for some other data items such as registration data but not MTDs. (raised as DI ID 25) |  | Implemented | [5 empty] | Interim Release 1 |  | Reference to LDSO User Removed - agreed with SCS that scenario should not arise provided existing SCS data rules are met | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-26 |  | N/A | 2023-01-30 | St Clements | 2707 | Madison Layton | Software Provider |  | Comment on Section 17.2 "If the MAP segment is not provided, the existing MAP history should be maintained to greatest degree possible, with ‘trimming’ to align to any revised Install / Remove Dates provided" Sent on Jan 11th: Risk that changing of the Meter Lifespan could result in MAPs being logically deleted. The MS would need to re-apply the MAP history to fit into the new meter Lifespan MS would need to understand this process/constraint (raised as DI ID 26) |  | Implemented | [5 empty] | Interim Release 1 |  | Section 17.2 of the guidance document updated. Also added new validation rule REG1014 for MeterHistoryUpdate in IF-005 to ensure MAP is provided when creating a new meter picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-27 |  | N/A | 2023-01-30 | St Clements | 2708 | Madison Layton | Software Provider |  | Comment on Section 19.2 "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the permanent deletion of data, mirroring the existing functionality associated with the use of the D0312." Sent on Jan 11th: Only logically deleted, still visible in the MPRS History. Just not visible to MEM or EES Existing functionality on D0312 utilises cancellation flags not permanent deletion (raised as DI ID 27) |  | Implemented | [5 empty] | Interim Release 1 |  | Reword to reflect the logical deletion. See MHHS-DIN-23 Reword this paragraph to: "Currently it is assumed that amendments to asset history, using IF-005 [MeterUpdate] and [MeterHistoryUpdate] transactions, may result in the removal of a MAP from a meters MAP history using a logical flag, mirroring the existing functionality associated with the use of the D0312." NB Main section header is incorrect - should be updated to section 19, rather than a duplicate of section 18. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-28 |  | N/A | 2023-01-30 | St Clements | 2709 | Madison Layton | Software Provider |  | Comment on Section 19.4 "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories. However, this would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." Sent on Jan 11th: This functionality already exists with the MPAN History Report showing who changed what when for all MPRS data items. Will be extended to include DIP transactional information (raised as DI ID 28) |  | Implemented | [5 empty] | Interim Release 1 |  | Proposed Change Reword this paragraph to: "MHHS Design Team also recognises that EES may also have a role to play in maintaining and providing visibility of asset and asset change histories, noting that this is also available via the MPAN history report which will be updated with DIP transactional information and could also be used. Any use of EES would be considered to be a ‘Consequential Change’, for consideration of EES/REC stakeholders, and outside of the direct scope of the MHHS Design." picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Guidance Document | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-29 |  | N/A | 2023-01-30 | St Clements | 2710 | Madison Layton | Software Provider |  | There should be an additional rule for USP, if DI-830/DI-833 is populated, the MS/DS Proposed Effective From Date must equal the currently held EFD for the MS/DS appointment in MPRS (raised as DI 29) |  | Implemented |  |  |  |  | 2023-04-27 | Interim Release 1 |  | Added rule for USP scenario in IF-031 to check SP Effective from date. Proposing SCS have flexibility on error codes - requires industry Working Group. Picked up as part of Change of Service Provider review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-30 |  | N/A | 2023-01-30 | St Clements | 2711 | Madison Layton | Software Provider |  | The IF-035 does not provide the opportunity for MPRS to populate a lapsed reason. Will need to be able to provide a reason for a lapsed appointment, otherwise there'll be a higher volume of unecessary supplier enquries to DNOs which will require more resource and cost. (raised as DI 30) |  | Implemented | [5 empty] | Interim Release 1 |  | Additional Data Item on IF-035 for a reason comment - what reasons would these be other than gone beyond the date? Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-31 |  | N/A | 2023-01-30 | St Clements | 2712 | Madison Layton | Software Provider |  | MHHS-BR-RS-027 "Registration Service must re-run validation, in line with the validation rules set out in the appropriate interface specification, for all Metering Service appointments that have been confirmed to re-process from the Prospective Appointment Queue, to ensure that the appointment is still valid" It is not clear if MPRS would send MSAppRejected or MSAppLapsed if the appointment fails validation after it's been queued? If this is not made clear in the deisgn then there is a risk that we build to use the wrong event code, or if the code should be MSAppRejected then risk that suppliers build a design where they can't process a MSAppRejected after receiving already an MSAppAccepted from MPRS (raised as DI 31) |  | Implemented | [5 empty] | Interim Release 1 |  | Clarify the wording to show [MSAppLapsed] in documentation Proposed changes to clarify existing design is: • Updated BRS003, requirement MHHS-BR-RS-032 and 66 to show that appointments will be lapsed (not rejected) • Remove Rejected from Step 225 of BP002/BPD002 Also on BP003 leading from step 215 should have the rejected removed. Added L as valid value for DI-979in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Corrections also to BPM002 & BPM003 Forward Migration and BPD002 Froward Migration | Data interface correction | MPAN Ownership |  | MHHSP-BP002-Change of Service - Metering service, BPD002,MHHSP-BRS003-Registration Service requirements MHHSP-DES138-Interface Catalogue, MHHSP-BP003, MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration), MHHS-DEL969-BPD002 (forward migration)
MHHS-DIN-32 |  | N/A | 2023-01-30 | St Clements | 2713 | Madison Layton | Software Provider |  | The interface catalogue lists setting a removal date as an action that can be used with event code meterUpdate on IF-005, however in the interface catalogue, the block B039 does not list meterUpdate as a event code that can utilise this block. Need greater clarity on whether meterUpdate and meterHistoryUpdate should apply meter installations and meter removals or not. (raised as DI 33) |  | Implemented | [5 empty] | Interim Release 1 |  | The definition of a [MeterUpdate] event code is: Allows currently appointed Metering Service to amend the details associated with a currently installed meter. Therefore the appointed Metering Service must be able to remove the meter as part of an update, this is an omission from the design and a small update to IF-005 The design principle that IF-005 works on is that: • BAU transactions (Install/Exchange/Remove) that are in the Metering Services Period of ownership are covered by the Install/Exchange/Remove events • Changes to currently installed metering can be made by the Appointed Metering Service using the Meter Update event. Note this therefore includes, where required, removing the currently installed meter where it is prior to the current period of ownership. • Changes to metering history ( ie not the currently installed meter ) can be made by the Appointed Metering Service using the Meter History Update Proposed changes: Added MeterUpdate as Optional to B039 block in IF-005 and added validation rule to ensure MeterUpdate is not used to remove meters in current period of ownership picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP-DELS229-IF-005 Use Case Guide
MHHS-DIN-33 |  | T4-COM-1759 | 2023-01-30 | St Clements | 2719 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1759 on 15th Sept 2022: IF-005, REG1011 Install date must be > Creation date, should this REG1011 rule apply also to meter Exchange not just meter install SCS raised as a design blocker on 7th October 2022 Still no resolution, should this rule apply to meterHistoryUpdate at least as this allows for meter installations (raised as DI 34) |  | Implemented | [5 empty] | Interim Release 1 |  | An exchange will not be a creation date, and the validation already in place ensures that future installation dates will all follow each other, which means this rule isn't required. ​This shouldn't be needed for exchanges, as its covered by REG1008 (install date >= remove date), as an exchange would replace an existing meter, which at first install would be validated against creation date. Moved REG1011 to cover all scenarios in IF005 picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-34 |  | T4-COM-1774 | 2023-01-30 | St Clements | 2720 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1774 on 15th Sept 2022: IF-005, REG1011 "REG1009 - MAP ID [DI_055] is not valid for MAP Effective Date [DI-054] REG1011 - Install Date [DI-057] for MeterID [DI-056] is prior to MPAN Creation Date There are many meters in MPRS that pre-date the existence of the MAP and also MPRS install dates of 1980 etc. these will break a number of rules. should these be cleansed before MHHS start? If they are valid, then the rules need adjusting"l SCS raised as a design blocker on 7th October 2022 Still no resolution (raised as DI 35) |  | Closed | [7 empty] | This could be a data cleanse requirement which is a consequential change/transition requirement, but for REG1009 - the MAP effective date should be the point at which the MAP took over the meter, and the exchange date should be after this (ie it should be after the date MHHS goes live). For Reg 1011 currently this is only valid on installs (and installs won't occur on legacy meters). If Reg 1011 is valid on exchanges, then the exchange date should also be after the MPAN creation date - if it isn't then the data should be cleansed. Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-35 |  | N/A | 2023-01-30 | St Clements | 2721 | Madison Layton | Software Provider |  | On the IF-005, should REG1028 (Install date cannot be null or blank) apply to meterinstall, meter exchange and meterupdate too? (raised as DI 36) |  | Implemented | [5 empty] | Interim Release 1 |  | Requires amendment to interface validation - look at alternative validation Agree the rule should also apply for those events. Note we believe validation would fail for another reason. Eg REG1019 Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-36 |  | DI-37 | 2023-01-30 | St Clements | 2722 | Madison Layton | Software Provider | Re-alignment of rejection reasons to main block | In the summary of error codes box at the bottom of IF-005 tab the rejection reasons need re-aligning to the main block, e.g. REG1001 should read RMP stats must be Created or Operational, not just Operational As a general note across all interfaces, the rejection codes are referenced in numerous places and the respective descriptions are in many places not consistent for the same rejection code (raised as DI 37) |  | Closed | [7 empty] | Will be revisited once SCS provide definative Error Code Texts | No Change
MHHS-DIN-37 |  | N/A | 2023-01-30 | St Clements | 2723 | Madison Layton | Software Provider |  | REG1015 (cannot be removed meter) is listed for meterHistoryUpdate in interface catalogue for IF-005. This should actually apply to meterUpdate not meterHistoryUpdate, REG1018 (cannot be installed meter) applies to metering history update (raised as DI 38) |  | Implemented | [5 empty] | Interim Release 1 |  | Change accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-38 |  | N/A | 2023-01-30 | St Clements | 2724 | Madison Layton | Software Provider |  | In the interface catalogue, the IHD block B030 for IF-005 should also be optional for meterUpdate according to the IF-005 guide Section 16 Development Notes "The IHD segment, if provided as part of [MeterUpdate], relating to any currently installed meter should replace/update the IHD details currently held at the MPAN to which that Meter is associated." (raised as DI 39) |  | Implemented | [5 empty] | Interim Release 1 |  | Small change to schema operation IHD information may be updated as part of the [MeterUpdate] event. The change is to add [MeterUpdate] event to block B030, so it now reads "B030 - MPAN IHD Information (Optional & may only be used with [MeterInstall],[MeterExchange],[MeterUpdate]) NB this also standardises the use of commas between event codes, rather than using the & symbol. picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-39 |  | N/A | 2023-01-30 | St Clements | 2725 | Madison Layton | Software Provider |  | In interface catalogue for IF-005, there needs to be a rule that if event code MeterInstall is used, then modified meter ID cannot be populated (raised as DI 40) |  | Implemented | [5 empty] | Interim Release 1 |  | Update agreed | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-40 |  |  | 2023-02-01 | SI Design |  |  |  |  | Not used - raised as duplicate in error |  | Closed
MHHS-DIN-41 |  | N/A | 2023-01-30 | St Clements | 2730 | Madison Layton | Software Provider |  | In interface catalogue IF-005: The REG1003 reads Metering Service [S0.SenderID] holds valid previous appointment then Meter Install Date [DI-57] should be < [REG.App End Date] + 10 The way it's curently written suggests MPRS should accept an IF-005 from the previous appoint, even if their ETD was greater than 10 days ago, provided the install date was less than their ETD + 10. E.g the previous MS could send IF-005 two years later with Install date of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then REG1002/REG1019 should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? (Raised as DI 41) |  | Implemented | [5 empty] | Interim Release 1 |  | Having looked through IF-005 Dates should be within the appointment date, and current deign does give the ability to go outside this Change the validation rule for REG1003 on events [MeterExchange], [MeterInstall] and [MeterRemoval] to "If Metering Service [S0.SenderID] holds valid previous appointment then [system date] < [REG.App End Date] + 10" Picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. Rule amended after review by SCS, to remove second "if" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-42 |  | N/A | 2023-01-30 | St Clements | 2784 | Madison Layton | Software Provider |  | In interface catalogue IF-005: Meter Update should apply validation REG1027 (current MS or prospective MS) not REG1012 (current MS only) to allow the prospective queued MS to update the Meter Type on a SEG change and therfore complete the market segment change and appointment. MHHS-BR-RS-132 . If the SEG prospective appointment was not allowed to update on meterUpdate event code then they would not be able to update the meter type to completed change of market segment, and would not meet the conditions needed to then be appointed in MPRS, their appointment would then lapse and market segment would remain invalid. (Raised as DI 42) |  | Closed | [7 empty] | We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error... | No Change |  |  | None
MHHS-DIN-43 |  | N/A | 2023-01-30 | St Clements | 2732 | Madison Layton | Software Provider |  | In Interface Catalogue, on If-005, REG1002 and REG1019 are duplicates (install/removal dates should be within MS period of ownership). We can only use one of the rejection codes and descriptions, programme should choose which one to keep and remove the other. (Raised as DI 43) |  | Closed | [7 empty] | These are testing slightly different things. The first test (REG1002) is checking that the Metering Service is an eligible party to send the request ie currently appointed OR was at the time of the install (to cover for previous Metering Services updating in the 10 day window). The second (REG1019) is checking that the Install Date is in the Metering Services period of ownership. So you could have that the Metering Service is currently appointed, but that they weren't at the install date. Eg Today is 2nd Feb, Meter installed on 27th Jan, Sending MS was appointed on 1st Feb REG1002 would pass as they are eligible as the currently appointed MS REG1019 would fail as they are not appointed at the time of the install Closed 27/2 - picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | No Change |  |  | None
MHHS-DIN-44 |  | N/A | 2023-01-30 | St Clements | 2733 | Madison Layton | Software Provider |  | Should the new rule for meter update in IF-005 also apply to meter history update? If no MAP entries provided, and revised Meter Install / Remove Dates result in no valid MAM History then reject with REGE1014 – MAP Eff From Sequence Error (Raised as DI 44) |  | Implemented | [5 empty] | Interim Release 1 |  | Added REG1014 ( MAP History ) to IF-005 MeterHistoryUpdate event | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-45 |  | N/A | 2023-01-30 | St Clements | 2736 | Madison Layton | Software Provider |  | New rule for IF-005 Meter Update REG1017 could be misinterpreted as it currently reads incorrectly - need brackets to correct to how the AND and AND/OR conditions are to be applied If [DI-60] is not null AND Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null) Should read If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null)) (Raised as DI 45) |  | Implemented | [5 empty] | Interim Release 1 |  | Clarification of existing design rule Change the validation rule for REG1017 to: "If [DI-60] is not null AND (Meter Install Date [DI-057] <> {Reg.InstallDate} for Meter [DI-59] AND/OR Meter Removal Date [DI-058] <> {Reg.RemoveDate} for Meter [DI-059] (noting that Removal date could be null))" picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-46 |  | N/A | 2023-01-30 | St Clements | 2737 | Madison Layton | Software Provider |  | on IF-005 for Meter Exchange and meter install the rule for REG1027 has been changed, but I'm not sure the wording implements the rule intended exactly? Currently it reads as The MS must be the currently appoint MS AND the install date must be > MS EFD AND the MS must not have proposed MS app with SEG scenario in the queue. If not then reject with REG1027 - Metering Service is not currently appointed and does not hold a Prospective SEG Appointment SHould the rule actually read The MS must be the current MS OR the MS must have a proposed MS App in the queue with SEG scenario And then the other part of the rule about install date > MS should be a separate rule (with REG1019 error code). (Raised as DI 46) |  | Implemented | [5 empty] | Interim Release 1 |  | Sent to Mike F for validation - SI believe wording in current documentation is correct. Agree this could be worded better and also turned from being a negative test ( what is invalid ) to a positive test ( what is valid ) as per other validation rules in IF005. I would suggest the wording could be clarified to: Metering Service [SO.Sender] is NOT the currently appointed Metering Service ORAND (Meter Installation Date [DI-057] > Current MS Eff From Date AND MS [SO.Sender] does not have a Proposed MS App with Scenario "SEG" in the app queue) In the case of the second test within brackets, it cannot equal the current MS Eff from Date as the new MS must be appointed and that cannot be on the same day, therefore you cannot rely on REG1019. DIN-46 – On review we agree, the date test should always be true if REG1019 is satisfied ( with minor clarification update ), so validation rules should be updated as below: Proposed changes: REG1027 Validation Rule in IF005: Metering Service [SO.Sender] is the currently appointed Metering Service OR MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue REG1019 Validation Rule in IF005: Meter Installation Date [DI-057] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date (In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) Meter Removal Date [DI-058] >= Metering Service [SO.SendingPartyID] Appointment Effective From Date (Registration) OR Proposed Appointment Effective From date ( In case of SEG, where MS [SO.Sender] does have a Proposed MS App with Scenario "SEG" in the appointment queue ) picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-47 |  | N/A | 2023-01-30 | St Clements | 2738 | Madison Layton | Software Provider |  | REG1001 on IF-005 does not allow for meters to be removed after a disconnection. Instead should restrict for allow other event codes but allow Status Terminated for MeterRemoval. DES204 CCR-0556 Linked to DI-13 |  | Implemented | [5 empty] | Interim Release 1 |  | Rule update required picked up as part of IF-005 User Guide review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-48 |  | DI-048 | 2023-01-30 | St Clements | 2739 | Madison Layton | Software Provider | CSS failure to apply CoS to related secondary MPANs | Unhappy path scenario:- What happens if, for whatever reason, CSS fails to apply CoS to all the related secondary MPANs MPRS receives IF-031 on primary RMP to change agent, MPRS applies this to all seocndary MPANs too But if the CoS was not received from CSS for secondary MPANs that the secondary MPANs would still currently be held for the wrong supplier Would this cause any issues downstream? (Raised as DI 48) |  | Closed | No |  | Design gap | SCS |  |  |  | Change Request to be raised against this | Other | MPAN Ownership | Related MPANs
MHHS-DIN-49 |  | N/A | 2023-01-30 | St Clements | 2740 | Madison Layton | Software Provider |  | Unhappy path scenario:- If MPRS sends a IF-033 but never receives back a IF-034 then the rest of the process will not continue. The Supplier will never receive the IF-035 they are waiting for and the SP would never get appointed by MPRS. Is there a process in place to detect/resolve this scenario? (Raised as DI 49) |  | Closed | [7 empty] | There is a requirement for the Supplier to monitor for any delayed responses and request an update if not received in expected timescales. Reviewed with SCS and agreed ticket can be closed | No Change |  |  | None
MHHS-DIN-50 |  | N/A | 2023-01-30 | St Clements | 2741 | Madison Layton | Software Provider |  | We need clear rules to define what a valid Consent granularity looks like. Current rules don’t mention any validation around EDI. (Raised as DI 50) |  | Implemented | [5 empty] | Interim Release 1 |  | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-51 |  | DI-51 | 2023-01-30 | St Clements | 2747 | Madison Layton | Software Provider | St Clements Design Query - DI 51 | We have had some feedback from DNOs asking about how systems will recover from System Misalignment because of data errors or significant downtime? We have the D0204 (Supplier) and D0209 (Data Aggregator) Refresh functions today which are not being replaced with a DIP message equivalent. I am aware of the DIP Replay function, but this wouldn’t be of any help if there were data errors, as the DIP would just be replaying the incorrect data. The Source system would need to re-send the corrected data in an agreed format. I know there is a design principle to move away from bulk loads and refreshes of data, Faster Switching took a similar approach. However today, CSS leans heavily on the MPRS Refresh function to get itself back inline and there are REC CP’s being raised to add a Refresh function to CSS for all parties (first CP being R0067). DNO’s are keen to understand the MHHS Programme’s position on and if Refresh functionality should be built into MPRS for MHHS. |  | Closed | No |  | Design gap | DNO (SCS), EES (RECCo), DIP |  |  |  | Change Request will be raised against this DIN. Refresh Functionality was rejected by the Working Groups so not in current design. Internal Design Discussion Required on if Programme position has changed on this given CSS Issue / EES Fed via DIP ?? Details provided by the Design Team to SCS and RECCo on the workings of the refresh functionality and get agreement on next steps. | Other | Supporting Docs | Refresh Process?
MHHS-DIN-52 |  | DI-52 | 2023-01-30 | St Clements | 2748 | Madison Layton | Software Provider |  | For IF-005, REG-1006 and REG1013, would it make sense to include the installation date of the MPAN already in the system in the rejection description too to help MS with triage? |  | Closed | [7 empty] | DIN closed as instructed by St Clements. Old comments: Discussed with SCS potential for them to have flexibility on error messages. Industry agreement required. Participant Discussion Required | No Change
MHHS-DIN-53 |  | N/A | 2023-01-30 | St Clements | 2749 | Madison Layton | Software Provider |  | Requirement on LDSO requirements spreadsheet: MHHS-BR-LD-035 LDSO Maintain DUoS Tariff ID LDSO must set Duos Tariff ID on MPAN creation and maintain DUoS Tariff ID's in line with their Charging Method Statement. This should include updating the Duos Tariff ID, as required, following any updates to Domestic Premise Indicator, Connection Type and Energy Direction Note for MHHS, LLFC ID is being renamed as DUoS Tariff ID to make it clearer what this data item is used for. "BP010B Change of registration data" 250 However missing the respective requirement for Registration Services in the Registration Services Requirements spreadsheet |  | Closed | [7 empty] | Looked through the Registration Services Requirements spreadsheet v4.6 and it looks like DUoS Tariff ID is there - MHHS-BR-RS-091.1, MHHS-BR-RS-121 and MHHS-BR-RS-122 | No Change |  |  | None
MHHS-DIN-54 |  | N/A | 2023-01-30 | St Clements | 2750 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1699 on 15th Sept 2022: On the IF-031 and IF-035 there are a number of "Proposed" Data items. Should MPRS load these and updated the stored data items. Or are these data items only for passing through to Supplier and Service? SCS raised as a design blocker on 7th October 2022 We have some clarity verbally on this but nothing has been formally documented in the design artefacts. This needs to be reflected somewhere in the requirements. |  | Implemented | [5 empty] | Interim Release 1 |  | Added "Appoinments - Data" section in REG Notes to highlight what data becomes effective with the appointment. picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-55 |  | T4-COM-1738 | 2023-01-30 | St Clements | 2751 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1738 on 15th Sept 2022: the DB02 flow updates multiple data items on the IF-018 in one event. Can multiple EventCode be included in one IF-018 or will MPRS need to generate an individual IF-018 for each EventCode? SCS received a blank response and raised as a design blocker on 7th October 2022 |  | Closed | [7 empty] | Original response was that clarification was to be provided on 24th Oct - is this available? Which document? One at a time | No Change |  |  | None
MHHS-DIN-56 |  | T4-COM-1742 | 2023-01-30 | St Clements | 2752 | Madison Layton | Software Provider | Manual Correction to MHHS data items | Originally raised as T4-COM-1742 on 15th Sept 2022: BSCP604 currently allows LDSO and Suppliers to request manual corrections to Data Items held in MPRS. Will this type of Manual Correction be allowed in MHHS, if yes then this should be added to the business process to capture manual amendments and how these changes are reflected back to DIP users (IF-018 & IF-026, or a new Refresh Message?) SCS received a blank response and raised as a design blocker on 7th October 2022 Another example of this: If the MS/DS history is incorrect and cannot be amended via BAU, would the DNO be able to correct this via an exceptional error handling process? |  | Closed | No |  | Design misaligned | LDSO, Supplier and SCS |  |  |  | Covered in the retrospective changes discussion at DRG. | Requirement correction | MPAN Ownership | CSS Defects | MHHS-BPD005 Data Processing, MHHS-BRS005 LDSO overview
MHHS-DIN-57 |  | T4-COM-1748 | 2023-01-30 | St Clements | 2756 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1748 on 15th Sept 2022: "Additional information field DI-120 is String200, where the existing DB03 allows a free text field of 2000 characters" SCS raised as a design blocker on 7th October 2022 This was corrected but then in v4.5 artefacts released there was a change back for DI-120 addition information field from string 2000 to string 200 in the interface catalogue data catalogue tab reintroducing the issue. For disconnection additional notes MPRS database holds 2000 characters so this field will need to be string 2000 in the IF interfaces (Raised as DI 57) |  | Closed | [7 empty] | Change to the data catalogue included in the 4.7 baseline | No Change |  |  | None
MHHS-DIN-58 |  | T4-COM-1789 | 2023-01-30 | St Clements | 2757 | Madison Layton | Software Provider | Valid combinations of ISD data for MPRS validation development | Originally raised as T4-COM-1789 on 15th Sept 2022: "Valid combinations of data in ISD are critical to the MPRS validation development, we must have these defined and agreed before we can start development" SCS raised as a design blocker on 7th October 2022 |  | Closed | [7 empty] | Elexon has defined the valid combinations of ISD data and these files are available on this link https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/ISD.aspx | No Change
MHHS-DIN-59 |  | T4-COM-1707 | 2023-01-30 | St Clements | 2758 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1707 on 15th Sept 2022: "The Smart DS for Export and Secondary MPANs can be different to the Import/Primary DS as the Customer can choose their own DS for Export and Primary (Smart only)" The IF-031 validation rules have been amended but they are still not corrrectly reflecting the rule. The heading above both rules REG1038 and REG1039 reads: "If event type = [MSApp] OR event type [DSApp] & MPAN Segment is not 'Smart'" This heading should ONLY apply to REG1038 for linked MPANs and should not apply to REG1039 concerning related MPANs It should also have brackets to clarify the logic otherwise it could be misinterpreted e.g. "If event type = [MSApp] OR (event type [DSApp] & MPAN Segment is not 'Smart')" |  | Implemented | [5 empty] | Interim Release 1 |  | This seems a valid issue. REG 1039 on linked meters should be allowed for trad meters (eg economy 7) Proposed Change: The logic issue here is that REG1039 caters for related meters, which are applicable to trad as well as smart meters. Remove REG1039 from this validation Change the validation to: "If (event type = [MSApp] OR event type [DSApp]) & MPAN Segment is not 'Smart'" Updated heading above REG1038 and added heading above REG1039 to clarify the validation rule in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-60 |  | T4-COM-1708 | 2023-01-30 | St Clements | 2759 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1708 on 15th Sept 2022: "The Service Appointment Date must be equal to the SSD or there will be a period with no Service" And T4-COM-1776 also on 15th September 2022 "REG1032 - Metering Service Eff From Date [DI-830] is not contiguous - Appointment must be from [Max[Reg.MPAN_SSD] ,[Reg.ExistingMSAppFrmDate]] for a COS, it can only equal the SSD otherwise there will be a gap" This has been applied incorrectly. In IF031 rules REG1032 now reads that the MS/DS prop EFD must be = Max(SSD, existing MS/DS EFD + 1) This would restrict the MS/DS to setting the new EFD to either SSD or the day after the last MS/DS appointment, and all other dates would be rejected. It should read >= not just =. All four refrences to REG1032 in the validation rules for IF-031 references the +1 day after EFD, but the rejection description in the right hand columns for 'scneario not SEG or CoS' section does not reference this + 1. This should be corrected to be consistent with the other rules. (Raised as DI 60) |  | Implemented | [5 empty] | Interim Release 1 |  | Original response to 1708: New rules added to cover all scenarios Original response to 1776: Change to be incorporated into design artefact Updated REG 1032 validation in IF-031, original single rule, split into 2 separate rules picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-61 |  | T4-COM-1445 | 2023-01-30 | St Clements | 2760 | Madison Layton | Software Provider |  | Originally raised as T4-COM-1445 on 15th Sept 2022: "There is no mechanism to update the Profile Class. We would assume that this would be updated by the Supplier (with business rules restricting when this should be set) and confirmed on the IF-026. Please can you confirm if this is the intention or if it will be updated through another route. If so, the EES would need to know which PUB would confirm the data item had been updated. " Whilst this is now included in the design the validation rules from D0205 have not been carried over, e.g. PC/SSC need to be a valid combination. ISD will need to contain the valid PC/SSC Combinations (previously MDD Entity 11) and the validation rules in the interface catalogue will need to reference this validation against the ISD valid combinations. (Raised as DI 61) |  | Implemented | [5 empty] | Interim Release 1 |  | See also DIN-58, need to find out who is defining ISD validation Updated Interface notes in IF-025 to confirm that there is no Profile Class/ SSC combination checks | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-62 |  | DI-062 | 2023-01-30 | St Clements | 2761 | Madison Layton | Software Provider |  | In the business process diagram for Registration Updates MHHSP-BP010-Change of Registation Data - v4.5, the MPL update section, the C0300 has been changed to C0400 which is incorrect, C0400 is for MAP updates. Address updates are actually sent in the C0600. (Raised as DI 62) Change raised 30 March:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly. |  | Implemented | [5 empty] | Interim Release 1 |  | Also in the BPD. MHHS-BR-RS-114 also confirms this should be C0300, this appears to be a straightforward typo. Amend label between Step 20 and Step 30 on BP010A to CSS0300, and update the corresponding BPD description on step 30 Update required:- The CSS reference for address location changes are CSS0600, not CSS0400. Please change accordingly in BP010A, BPD010 and in MHHS-BR-RS-114. | Process model correction | Metering Changes | MPAN Updates | MHHSP-BP010-Change of Registration Data MHHSP-BPD010 MHHSP-BRS003
MHHS-DIN-63 |  | DI-063 | 2023-01-30 | St Clements | 2792 | Madison Layton | Software Provider |  | In the business process diag for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 (Raised as DI 63) |  | Closed | [7 empty] | SCS have now confirmed that C0700 is the correct reference - no need to change documentation - agreed to close | No Change | MPAN Ownership | Disconnection | MHHSP-BP007-Disconnection MHHSP-BPD007
MHHS-DIN-64 |  | N/A | 2023-01-30 | St Clements | 2793 | Madison Layton | Software Provider |  | In business process diag for change of data service MHHSP-BP003-Change of Service- Data Service-v4.5 and MHHSP-BP002-Change of Service- Metering Service v3.5, this still makes reference to D0386 in the purple note boxes. This should now have changed to IF-019 (Raised as DI 64) |  | Implemented | [5 empty] | Interim Release 1 |  | Update notes on BP002 and BP003 from D0386 to IF-019, and for BPM002 & BPM003 (forward migration) | Process model correction | MPAN Ownership | Change of DS | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-65 |  | N/A | 2023-01-30 | St Clements | 2794 | Madison Layton | Software Provider |  | The business process diagram for change to connection type/market segment has been amended to name only DB01, connection type is set on DB01 but it can then be changed on DB02 (Raised as DI 65) |  | Implemented | [5 empty] | Interim Release 1 |  | Update label between step 220 and 225 from "DB-001" to "DB02" | Process model correction | Metering Changes | Market Segement | MHHSP-BP011-Change of Connection Type or Mkt Segment
MHHS-DIN-66 |  | N/A | 2023-01-30 | St Clements | 2795 | Madison Layton | Software Provider |  | In interface catalogue, on IF-031, shouldn't rule REG1036 (MDR app EFD must be after DS app EFD), be applicable to all scenarios including SEG? Currently under section for if not SEG (Raised as DI 66) |  | Implemented | [5 empty] | Interim Release 1 |  | Updated validation rule for REG1036 and made applicable to all scenario's in IF-031 picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-67 |  | N/A | 2023-01-30 | St Clements | 2796 | Madison Layton | Software Provider |  | Currently no rule on IF-031 that the SP appointment has to be within the prospective suppliers registration period - just that it can't be past dated. This rule will need to be added. (Raised as DI 67) |  | Closed | [7 empty] | Reviewed with SCS and agreed that this validation is covered by existing rules. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-68 |  | N/A | 2023-01-30 | St Clements | 2797 | Madison Layton | Software Provider |  | If-031 business rule missing If the Scenario is USP, the consent granularity must be the same as the existing consent granularity held within MPRS (Updates should be through IF-025 not through IF-031) (Raised as DI 68) |  | Implemented | [5 empty] | Interim Release 1 |  | picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. Updated Interface notes in IF-031 to clarify that Registration Service will ignore any differences in Domestic Premise Indicator/ Consent Granularity sent on IF-031 (USP scenario) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-69 |  | N/A | 2023-02-02 | ESG Global | 2653 | Luke Speakes | Software Provider |  | PUB-033 - Block 029 is conditionally mandatory for DCC Commissioned Meters, but includes DI-025 DCC Service Flag with valid values of A-Active, I-Installed Not Commissioned, N - Non Active. The title of the block, which should define whether it is mandatory or not, is not appropriate if a DCC meter has been installed and not commissioned, or is inactive. Propose following SI and SRO design discussion that title of block 029 is revised to conditionally mandatory for 'DCC Smart Meters' |  | Implemented | [5 empty] | Interim Release 1 |  | Concludes this can be resolved by a minor wording change to the block title | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-70 |  | N/A | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory | Addition of MDR validation rule | Elexon is required to maintain a valid list of Meter Data Retrievers in Industry Standing Data, to allow RegService to validate they're suitably qualified (DCC and SEC) MDRs are being appointed. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Design Agreement is to utilise M16 for this purpose. ISD document updated with details and examples to this effect. | Other | Supporting Docs | ISD | MHHS-EDI-021-ISD_Entities
MHHS-DIN-71 |  | N/A | 2023-01-30 | St Clements | 2839 | Madison Layton | Software Provider |  | When would event code [MSDeAppUpdate] and [DSDeAppUpdate] be used for on an IF-037? (Raised as DI 69) |  | Closed | [7 empty] | Reviewed with SCS and it is used to notify the incoming Service Providers when de-appointing and not origanally known. In case of Linked/Related MPANs individual MPANs move through the process. RS need to apply the logic for sending the updated IF-037 to all MPANs. Agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-72 |  | N/A | 2023-01-30 | St Clements | 2840 | Madison Layton | Software Provider |  | Block B018 on IF-034 and IF-035 should not be mandatory - it will only be provided for smart meters. This needs to be set to mandatory for SDS-MDRUpdate only, optional for DSAppSPResponse (Raised as DI 70) |  | Implemented | [5 empty] | Interim Release 1 |  | Updated B018 block to be optional for non Smart on IF-034 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-73 |  | N/A | 2023-01-30 | St Clements | 2841 | Madison Layton | Software Provider |  | IF-026/IF-025, added new event code [SSCandProfileClass], but still kept in original [SSC] and [ProfileClass] event codes, should the original two have been removed? Particularly as the B032 group says it's madatory where event code is [SSCandProfileClass] and does not refer to [SSC] or [ProfileClass] individual event codes (Raised as DI 71) |  | Implemented | [5 empty] | Interim Release 1 |  | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 Picked up as part of CoSP review, will be approved by DA as a single update, rather than individual comments. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-74 |  | N/A | 2023-01-30 | St Clements | 2842 | Madison Layton | Software Provider |  | A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a new MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60 (Raised as DI 72) |  | Implemented | [5 empty] | Interim Release 1 |  | This appears to be the reciprical change to MHHS-DIN-60 for the response interface Update description to "Check if MDR Eff Date = SSD OR on or after existing MDR Eff From + 1" Update rule to "If [DI-841] <>SSD OR <MDR Eff Date + 1" | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-75 |  | N/A | 2023-01-30 | St Clements | 2843 | Madison Layton | Software Provider |  | On IF-035, overidden the description for Data Item 836 incorrectly with the description for Data Item 838 (Raised as DI 73) |  | Implemented | [5 empty] | Interim Release 1 |  | Update the definition field based on the description in the data catalogue for DI-836 on IF-035 (Date From which Supplier would like Nominated MDR to take effect) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-76 |  | N/A | 2023-01-30 | St Clements | 2844 | Madison Layton | Software Provider |  | Data catalogue - changed the estimation reason code authoritative source to Registration Service, this data item is not received by, sent by or held by registration services and so the authoritative sourse cannot be Registration Service (Raised as DI 74) |  | Implemented | [5 empty] | Interim Release 1 |  | The authoriative source has changed between v4.0 (from Data Service) to 4.7 (Registration Service) - have asked why the change was made, and what the authoritative source should actually be. Source updated to SDS/MDS | Data interface correction | Meter to Bank | Estimation | MHHSP-DES138-Interface Catalogue
MHHS-DIN-77 |  | N/A | 2023-01-30 | St Clements | 2845 | Madison Layton | Software Provider |  | Data catalogue - Added issue 99 items (CT Ratio, Phases etc) DI-170 - DI-180. Was agreed in work off meeting these items are not within the scope of MHHS, to introduce these would require a CR (Raised as DI 75) |  | Implemented | [5 empty] | Interim Release 1 |  | these data items don't appear to be used in any interfaces so this could be a relatively simple change to remove 11 items from the data catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-78 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E0404 requirement is blank - row needs to be deleted |  | Closed | [7 empty] | This update was already incorporated into version 5.0 closing it here | No Change | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-79 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHS-E2E002 Requirements v2.2 - E2E21114 typo - should be VAS Output Retention |  | Implemented | [5 empty] | Interim Release 1 |  | change as per description | Technical corrrection | All Areas | Technical Artefact | MHHS-E2E002 Requirements
MHHS-DIN-80 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier |  | MHHSP-DES138-Interface Catalogue v4.6 - DI-846 Issuing Data Service EZ Name should be scored through in IF/ PUB21 definition |  | Closed | [7 empty] | Completed in V5.0, part can review change as part of Interim Release 2 | No Change | Meter to Bank | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-81 |  | N/A | 2023-02-03 | British Gas | 2716 | Neil Strange | Supplier | Correction of step in BP020 | MHHSP - BP020 - Volume Allocation Service (ECS) v4.6 - Step 75 to Step 80 references report “REP-00” - needs correcting |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | BP020 step 75 to step 80 process flow REP list correction BPD020 step 75 & step 80 detail list of REP's correction | Process Model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions
MHHS-DIN-82 |  | N/A | 2023-02-09 | SI Design | 2716 | Rob Short | SI Design | Missing listed number of reports in BPD002 | Related to DIN-81 - BPD002 lists number of reports at step 75, BP002 does not reflect this list, missing PO275, PO214 and PO213 |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | This relates to BP020 (not BP002), similar to DIN81, reconcile REP list correction on BP020 at step 75 and 80 and reconcile with BPD020 list of REPs | Process model correction | Meter to Bank | Volume Allocation Service | MHHSP-BP020 Volume Allocation Service, MHHS-BPD020 Volume Allocation Service process descriptions
MHHS-DIN-83 |  | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | BP011 missing PUB-044 flow | A discrepancy with the Interface Catalogue - IF_LIST states MHHSP-IF-044 is sent to Central Settlements, DS, MS, Supplier, LDSO. IF-044 tab states it is sent to Supplier, MDS, LDSO In BP011 the PUB-044 is not sent to DS only Supplier, Settlements and EES |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Add Manage change of segment in LDSO lane on business process BP011C with a PUB-044 flow from step 570 Add new step to BPD011 Interface catalogue is already updated | Process Model correction | Metering Changes | Interface Catalogue | MHHSP-BP011 Change of ConType andor Mkt Segment MHHSP-BPD011 MHHSP-DES138-Interface Catalogue
MHHS-DIN-84 |  | N/A | 2023-02-01 | CGI | 2638 | Dave Webster | Software Provider | DES-138 IF List Tab Consistency | IF_LIST states MHHSP-IF-020 is sent to Supplier onlyIF-020 states it is sent to Supplier, Data Service, Metering Service, LDSOIn BP010, the PUB-020 is sent to Central Settlements, CSS, EES, Supplier, Data Service, Metering Service, LDSO.This one looks like its just the Interface Catalogue that needs updating. IF-020 Updated to refect new agreed Routing |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated parties receiving PUB-020 in the IF_LIST, updated PUB-020 routing to include MDS for Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-85 |  |  | 2023-02-07 | Elexon | 2391 | Anna Millar | Regulatory |  | Elexon see DIP qualification for new users being part of market entry post-programme, but want to understand how MHHSP will operate qualification during the programme. This is likely to cover the majority of participants. Discussions with SRO colleagues indicate they are assuming this is a process for the Enduring Service Operator to define. Challenge applies to non-BSC DIP participants (e.g. adaptor providers), and considerations under Issue Group 101. SI design has spoken to at least 4 participants who are operating in this space and seeking to understand how they can engage with SIT and other programme activities as a DIP connection provider (E2E Architecture - 3.3.2) |  | Closed | [7 empty] | To be handled as part of the Placing Reliance document | No Change | Qualification | Qualification | New Process - DIP Qualification for New Users
MHHS-DIN-86 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Invalid Market Segment BP011C requires SMRS to notify the Supplier of an invalid market segment. RegService requirement RS0124 states that SMRS must derive a value for Market Segment based on Connection Type and Meter Type following a Change of Metering, Change of Connection Type (Change of Unmetered Indicator) or Change of Related MPAN relationships. Given that SMRS determines segment as above, when would an invalid market segment occur, giving rise to the processes from step 560 in BP011C? Further, upon receipt of a PUB-045 Market Segment Invalid Advisory Notification, what are the next steps for a Supplier to address the issue? There are no provisions in the IF-025 for Suppliers to update Market Segment. |  | Closed | [7 empty] | Part of ongoing discussions with Code Drafting team 20/4//23 Code Drafting believe an update needs to be made to the design to update Market Segment via IF-25. This could occur when a Supplier is trying to arrange a change of segment but one of the activities has not completed on time eg the new metering has not been notified. When Registration Service tries to evaluate the segment it may not be compatible. Notification would then go to Supplier to prompt them to chase the required update, in this example chasing the Metering Service to provide the new metering details. Another example is if the LDSO has not notified a change of connection type. The Supplier may also need to send a further SEG appointment if the original has lapsed. | No Change | Metering Changes | Change of Connection Type and/or Market Segment | MHHSP-BP011, MHHSP-BPD011
MHHS-DIN-87 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory | Process clarification for meter removal and de-energisation on same job | Energisation Process Clarification BP009 states that change of energisation status at the same time as meter works means that BP008 will be followed - what is the process when a meter removal and de-energisation are carried out in the same job? Are both D0139 (de-energise) and D0142 (remove meter) and relevant DIP interfaces required. At the moment MEMs only have to send flows relating to meter removal |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | New Purple Boxes added in BP009 and BP008 to make it clear that Remove/DeEn could still be requested and carried out but MS would need to send two interfaces. Also that DeEn did not need to be notified if meter works completed within same day (ie same rules as today) | Process model correction | Metering Changes | Change of Metering | MHHSP-BP009 MHHSP-BP008
MHHS-DIN-88 |  |  | 2023-02-09 | RECCo |  | Sarah Jones | Regulatory | Update to Incumbent MS provider for Lapsed Appointments | Update to Incumbent MS provider for Lapsed Appointments Currently BP002 only addresses the positive confirmation of de-appointment from RegService (PUB-037 - step 140/231), but if there is no secured active, there is no subsequent notification to the incumbent. The prospective MS receives a PUB-035 at step 225. How should the incumbent MS determine when the de-appointment has lapsed? |  | Closed | [7 empty] | Part of ongoing discussions with Code Drafting team. It is not expected that the incumbant share the MTD via the IF-035 as early sight. IF-37 is the deappoint code they need to reflect . The Metering Service is appointed until they get de-appointed using a PUB-037. They are only receiving the PUB-035 as notification of who to send MTDs to, it is not intended as a notification of de-appointment. Incumbent Metering Service is a term used to refer to the MS appointed at the point another new SP Appointment is accepted (MS or DS), it shall be the Incumbent Metering Service's responsibility to share MTDs (ADV/Trad) to the incoming party. No change recommend CLOSE
MHHS-DIN-89 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | Customer Details on De-Appointment The MHHS design currently allows for customer data to be deleted or obfuscated by MS on de-appointment. Has obfuscation been confirmed as acceptable under GDPR? |  | Closed | [7 empty] | Programme has called out the need for data management wrt GDPR. It is for each participant to determine the action required based on their own GDPR Guidelines and policies. |  | All Areas
MHHS-DIN-90 |  |  | 2023-02-09 | RECCo | 2587 | Sarah Jones | Regulatory |  | MS Appointment for Associated Export Metering Points How will an initial MEM be appointed for a new export MPAN, created post MHHS go live? |  | Closed | [7 empty] | Part of ongoing discussions with Code Drafting team - this is not a Design Issue. Design will operate as described below: The daily process monitoring (BP011C) would pick up any [new] Linked Export MPANs and ensure that the same Metering Service is appointed as the Import MPAN. If the Export MPAN is not linked, then the BAU appointment process can be followed. |  | Metering Changes | Change of Connection Type / Market Segment | MHHSP-BP011, MHHSP-BPD011
MHHS-DIN-91 |  | N/A | 2023-02-10 | AWS | 2858 | Duncan Parsons | Software Provider |  | Document MHHS-E2E001 section 3.6 Actor Workflows Summary - Typo in the MSA Outbound. States IF-04, this should be IF-041 |  | Implemented | [5 empty] | Interim Release 1 |  | Reference Corrected | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-92 |  |  | 2023-02-14 | RECCo | 2903, 2805, 2911 | Sarah Jones | Regulatory |  | Customer Direct Contract Flag (D053) Multiple tickets - RECCo, ESG and National Grid - all highlighting the same problem. The 4.7 artefacts do not consistently reflect the agreed position that the Customer Direct Contract flag can only be set by the incumbent Metering Service provider. The validation rules on the IF-038 should be updated The requirements for MS (013) and DS (34) in the respective BRS artefacts should be aligned |  | Implemented | [5 empty] | Interim Release 1 |  | Added validation rule REG1075 to IF-038 in the interface catalogue Updated requirements in MS-013 and DS-034 in BRS to reflect the agreed position for D053 1/3 - ticket #3035 - SCS supportive of this change, need more detail. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue, BRS001, BRS002
MHHS-DIN-93 |  | N/A | 2023-02-14 | Power Data Associates |  | Tom | Data Service Provider | Work off Plan D-034D updates for exceptions to Unmetered Supplies | Work off Plan D-034D updates for exceptions to Unmetered Supplies |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | 1. Section 2.3 of MHHSP-METH004-UMSDS- EM Functions will be updated to make explicit that the following data items are not required by the UMSDS and as such will be ignored. • Consent Granularity (T4-COM-1857) • Domestic/Non-domestic Indicator (T4-COM-1830/1850) • Distributer Id (T4-COM-1826/1842/1845/1858/1859/1864/1865/1871/1875) • DUoS (T4-COM-1856) • LLF Data (T4-COM-1856) • Domestic Premise Indicator (T4-COM-1830/1850) • Metered Indicator- (D-045) 2. MHHSP-METH001- SDS Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 3. MHHSP-METH002- ADS- Validation & Estimation will be updated to make explicit that the Metered Indicator data item is not required and should be ignored 4. MHHSP-METH009- UMSO Method Statement should be updated to make explicit that the following data items are not required by the UMSO and should be ignored (list to be reviewed and validated). • Consent Granularity • Domestic/Non-domestic Indicator • Distributor Id • DUoS • LLF Data • Domestic Premise Indicator • Metered Indicator | Method statement correction | Supporting Docs |  | MHHSP-METH004-UMSDS MHHSP-METH001- SDS MHHSP-METH002- ADS MHHSP-METH009 - UMSO
MHHS-DIN-94 |  |  | 2023-02-16 | ESG | 2777 | Patricia | Software Provider | IF-005 rejections | The IF_009 has 2 event codes: [MPANDisconnection] & [CSSDeRegistration]. [CSSDeRegistration] is listed as having Supplier as Secondary routing however on BP007 there is only reference to the supplier receiving the [MPANDisconnection] flavour of the flow. Please can you clarify which artefact is accurate. MHHSP – BPD009 step 145 states Where the Registration Service has rejected the metering update the DIP will publish the rejection to metering services. Supplier have the option to subscribe to this also. Your response was:- Our reading of this is that regservice will reject the PUB-006 back to sender if the IF-005 fails those rules. So just back to sender, not always meter service or supplier Therefore, does the BPD009 step 145 need to be updated to reflect that as the IF005 can only be generated by Metering Service Smart (MSS) & Metering Service Advanced (MSA) not the Supplier |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Question 1. Supplier will receive both events as outlined in BP007 (See DIN 294) Question 2. A decision was made at the DRG on 29th June to leave the messaging in BPD009 step 145 and instead update the business process model in BPD009 to give Supplier's the option to subscribe to rejections. | Process Model correction | Metering Changes | Change of Metering | MHHSP-BP009 – Change of Metering (Install / Remove / Exchange) , MHHSP-BPD009 MHHSP-DES138-Interface Catalogue
MHHS-DIN-95 |  |  | 2023-02-20 | SI Design | NA | Simon Harrison | Programme |  | Typo in the Note box about Auto Alignment of Related/Linked MPANs on the BP002 and BP003 process maps. Change 'Regisatration' to 'Registration' |  | Implemented | [5 empty] | Interim Release 1 |  | Update BP002 (& BP003) call out box, also for BPM002 and BPM003 (Forward Migration) | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service MHHSP-DEL963-BPM002 (forward migration), MHHSP-DEL964-BPM003 (forward migration)
MHHS-DIN-96 |  |  | 2023-02-21 | SI Design | 2973 | Arif Jagot | Programme |  | Test-078 - SUPPI -Primary - Means SUPI? |  | Implemented | [5 empty] | Interim Release 1 |  | Update Interface Catalogue | Data interface correction | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-97 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.4 | Typo in MHHS-METH001-5.4c "and less than 90 days months different from the UTC Date" - propose removal of months |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Update Method Statement i.e This needs to be 90 days not 90 months the artefact needs to be updated | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-98 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Missing wording in MHHS-METH001 in section 5.5 | Typo in MHHS-METH001 - 5.5 SDS shall use the most recent data a based on the event that triggered the |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Typo error on clause 5.5 within MHHSP-METH001-SDS Validation Estimation v5.0 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-99 |  |  | 2023-02-21 | CGI | 2888 | Simon Harrison | Software Provider | Working days correction | Clarify that Step 105 in the CoS Transfer read process is Working Days. Currently states 5 days |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Checked with SRO - 5 Working days for Step 105 in process, BPD003C, BR-DS-024.1 and BR-DS-024.2 | Requirement correction | MPAN Ownership | Data Services | MHHSP-BRS001 - SDS Requirements MHHSP-BP003C - Transfer of Reads MHHSP-BPD003C - Transfer of Reads
MHHS-DIN-100 |  |  | 2023-02-21 | RECCo | NA | Sarah Jones | Regulatory | BP002 to include LDSO as recipient | Step 180 in BP002 and BPD002 does not include LDSO as recipient of traditional meter details as per the wording of the step or the BRS (BR-MS-024) (Code Drafting Log Reference CDD-29) |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Update BP & BPD to align with BRS and add LDSO as recipient of MTDs Updates to BP & BPD002 Forward migration for consistency | Process model correction | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Metering Service MHHSP-BPD002 Forward Migration BP002 and BPD002
MHHS-DIN-101 |  | DI-120 | 2023-02-22 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. (Raised as DI 120) |  | Closed | [7 empty] | Included within CSS validation rule update. DUPLICATE See DIN-172 | No Change | MPAN Ownership |  | MHHS-DES138-Interface Catalogue
MHHS-DIN-102 |  |  | 2023-02-22 | St Clements | 2886 | Madison Layton | Software Provider |  | SCS raised the following under MHHS-DIN-7 "MPRS will reject any PUB-031 inlcuding those with Scenario CoS where the Registration Request ID (CSS Reg ID) cannot be found in MPRS with “CSS Registration Request Id (registrationId) does not exist"" This is not currently reflected in the design artefacts, interface catalgoue should be updated to include this rule (raised as DI ID 8)" They have followed up with: Just found the change that corresponds to this one in v4.7 interface catalogue – REG0005 in IF-031. Could this also be added to IF-034 so that we can apply the same validation on MDR updates? |  | Closed | [7 empty] | Proposed Change: Add validation "CSS Registration Request ID [DI-849] is valid for Registration Service", with error REG0005 - "CSS Registration Request ID [DI-849] is invalid or unknown" This mirrors a change made in v4.7 to IF-031, agreed as part of the DAG baseline of v4.7 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-103 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory |  | Confirm that D0381 will continue to be used for updates to MPL address. BP010 & BPD010 currently allow emails, SDEP and other agreed forms can be used by Supplier or UMSO to update this - propose that these artefacts are amended to reflect that the D0381 is to be retained (Code Drafting Log Reference CDD-22) |  | Implemented | [5 empty] | Interim Release 1 |  | Amend Steps 10, 21, 22 to explicitly use the D0381 rather than current wording | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-104 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Impact of MHHS on SoLR arrangements | Impact of MHHS on SoLR arrangements - possibly needs an Issue Resolution Group discussion to undertake evaluation & impact assessment (Code Drafting Log Reference CDD-23) |  | Closed | [7 empty] | Extensive discussions have been held with Elexon (DIP Manager) to ensure that there is flexibility within the DIP Design to accomdate varied SoLR scenarios. These involve the existing process(s) around change of BMUnits and the ability to transfer ownership of DIP Market Participants. As the solr process does not involve any mass movement / reassignment of MP Identifiers at the MPAN level the core MHHS design is not impacted by Solr per se. |  | All Areas
MHHS-DIN-105 |  |  | 2023-02-23 | RECCo | NA | Sarah Jones | Regulatory | Related MPAN Business Rules | 1) IF-019 suggests RMP status can be Created or Operational - proposed this can only be Operational for subsidiary MPAN 2) Add validation rule to IF-019 requiring related MPANs to have consistent classification as domestic or non-domestic (reflecting the existing requirements) 3) Clarify what Registration Services should do when MPANs are related/linked and have different MS/MEM providers - is the IF-019 rejected or the MEM for the secondary MEM auto-deappointed? 4) What happens if the IF-019 fails validation by Reg Service at Step 330 in BP010? Design provides no guidance |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | 1. Removed reference to Created in the REG1001 validation rule for IF-019 2. We understand there is no existing validation within MPRS and this is not being amended as a result of MHHS implementation. This would require a wider industry change impacting CSS as Domestic Premise Indicator is managed independently of Related MPANs. 3. It would not be rejected, auto-alignment would pick up the discrepancy at the next daily run and de-appoint the export MS and appoint the import MS. 4. As with other rejected flows, the sending party should investigate the error and re-submit as appropriate. | Data interface correction | MPAN Ownership | Change of Registration Data | MHHSP-DES138-Interface Catalogue
MHHS-DIN-106 |  |  | 2023-02-23 | SI Design | 2955 | Kate Goodman | Testing | IF Routing | Inconsistency in DES138 for UMSO Routing 00-Introduction logs UMSO as the single routing option for Unmetered Service provision, as there can only be one UMSO related to an MPAN PUB-008 provides UMSC, UMSP and UMSI as options for secondary routing This inconsitency needs to be corrected |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | IF-008 - Secondary routing rules updated following review with Avanade (see DIN268) |  | All Areas | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-107 |  |  | 2023-02-24 | SI Design |  | Simon Harrison | Progamme | Update to definition of DI-301 LLF ID in the ESC Reporting Data Catalogue | Definition of DI-301 in the ECS Reporting Data Catalogue needs to be updated as follows 'The Unique Identifier of a set of Line Loss Factors' |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Update to be made in the ECS Internal & External Reports - Data Catalogue tab against DI-301 LLF ID it should read as 'The Unique Identifier of a set of Line Loss Factors' | Data interface correction | Supporting Docs | Reporting Catalogue | MHHSP - ERI011A - ECS Reports - Internal v5.2 MHHSP - ERI011B - ECS Reports - Enternal
MHHS-DIN-108 |  |  | 2023-02-27 | SI Design | 2966 | Kate Goodman | Testing | IF Routing | Ref:MHHSP-DES138-Interface Catalogue v4.7, IF-038, PUB-020, PUB-039. Document says that UM is relevant to these messages but UM thinks it is not relevant. Please clarify what the situation is. Raised in review of MHHSP-872 by Power Data. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Covered by Secondary routing updates (See DIN268), changes to IF-020 and IF-039 routing. No changes were required to IF-038. The design allows for Customer Direct flags to be set for any Data Service/ Metering Service (ie Including unmetered). |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-109 |  |  | 2023-02-27 | SI Design |  | Simon Harrison | Programme |  | Call out box in BP002/BP003 on Linked/Related MPANs needs to be updated as it includes reference to email/SDEP rather IF-019 as shown in BP010 |  | Closed | [7 empty] | Confirmed - the call out box on BP002/003 needs to be updated Duplicate of DIN-64 | No Change | MPAN Ownership | Change of Service | MHHSP-BP002-Change of Service - Metering Service MHHSP-BP003-Change of Service - Change of Data Service
MHHS-DIN-110 |  |  | 2023-02-27 | SI Design | 2983 | Kate Goodman | Testing |  | MHHSP-BP005-Data Processing-v4.6, Step 50-160 UMSDS is referencing Submit Required UTC period level consumption data (Step 50) with a arrow going to Receive UTC period level consumption data (Step 160) but no reference of IF-021 on the connection between both - reference should be added? |  | Implemented | [5 empty] | Interim Release 1 |  | On Process map requires arrow to be labelled as IF-021 from step 50 to step 160 | Process model correction | Meter to Bank | Data Processing | MHHSP-BP005-Data Processing
MHHS-DIN-111 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Originally raised as T4-COM-1691 on 15th Sept 2022: "MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days " Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5 (Raised as DI-76) |  | Implemented | [5 empty] | Interim Release 1 |  | Updated to 2 working days | Requirement correction | MPAN Ownership |  | MHHS-BRS003-Registration Service requirements
MHHS-DIN-112 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54 (Raised as DI-77) |  | Implemented | [5 empty] | Interim Release 1 |  | Added note to clarify | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-113 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? (Raised as DI-78) |  | Closed | [7 empty] | Agreed duplicate of DIN-29 and can clsoe | No Change
MHHS-DIN-114 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | EES does not appear to have been added to the routing rules tables on the interface tabs(Raised as DI-79) |  | Closed | [7 empty] | Already present in v5 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-115 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | On IF-050, this includes linked MPANs in it, but I don’t think these would ever be populated as you cannot link MPAN at MPAN creation. So EES would only ever get Linkage updates on the IF-20 Is there any value of having this therefore in IF-050?(Raised as DI-80) |  | Implemented | [5 empty] | Interim Release 1 |  | Removed Linked MPANs and Related MPANs from IF-050 and added explanatory note | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-116 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | For IF-025, block B032 it states it is "MPAN Legacy Info (Mandatory where event is [SSCandProfileClass], and for Traditional Meters / Optional for other Meters)" It should just read mandtory for event code [SSCandProfileClass] and nothing else, it should not be optional for any of the other event codes(Raised as DI-81) |  | Implemented | [5 empty] | Interim Release 1 |  | Updated B032 block in IF-025/IF-026 to just allow [SSCandProfileClass] and to clarify optionality. Removed [SSC] and [ProfileClass] events from IF-025 and IF-026. Removed SSC and Profile Class validation from IF-025 and IF-026 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-117 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?(Raised as DI-82) |  | Closed | [7 empty] | Discussed with SCS and confirmed it is a limitation of swagger output but should be array of MPAN followed by array of meters followed by array of MAPs repeated per MPAN. Awaiting confirmation can close | No Change | Metering Changes | IF-005 JSON | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-118 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | In relation to the Sender Unique Reference, which is constructed as: S-<Interface>-<Participant Id>-<Role Id>-<Date>-<Sequence> (hex) I would like to comment as follows: • Why is the Unique Reference simply constructed using elements that are already contained in the message as distinct values? This just means the sender has to construct it and the receiver de-construct it? • Is the sequence number expected to be reset each day ? • It would be much easier and more logical for the Sequence to be a distinct item in the message? • Why is the sequence specified as hex? • Even given the expected large number of messages, and based on it being a number(13) (defined as Sting), a standard sequence number per Participant and Role would provide 9,999,999,999,999. If this is still seen as a limitation then it could simply be built from the date, e.g. 202301190000000001, giving a provision for up to 9,999,999,999 messages PER DAY from the same Participant / Role combination, which still enables a read every 30 minutes from every MPAN(Raised as DI-83) |  | Closed | [7 empty] | This is to send a unique reference and is used for auditing purposes. Please note the length of the Sender Unique Reference has been increased at the request of Avanade in 5.1.1. Examples updated |  | MPAN Ownership
MHHS-DIN-119 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | in swagger hub under IF-002 B907 list the B036 block, this is missing numberOfDigitsCumulativeRegister data item(Raised as DI-84) |  | Implemented | [5 empty] | Interim Release 1 |  | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue. Swagger will be updated | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-120 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Inconsistency in naming of data item DI-091 In swagger hub: Number-Of-Digits-Cumulative-Register In interface catalogue IF tabs (E.g. IF-002) : Number of Displayed Register Digits In interface catalogue data catalogue tab: Number Of Displayed Register Digits (Cumulative Register)(Raised as DI-85) |  | Implemented | [5 empty] | Interim Release 1 |  | Updated DI-091 to Number Of Displayed Register Digits in the Data Catalogue and updated YAML accordingly | Data interface correction | MPAN Ownership |  | JSON, YAML, MHHSP-DES138-Interface Catalogue
MHHS-DIN-121 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0093 comment raised on 12/01/2023 " D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: "It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42 (Raised as DI-86) |  | Implemented | [5 empty] | Interim Release 1 |  | Agreed to provide SEG scenario's in IF-005 Use Case guide. currently under review |  | Metering Changes | Change of Segment | MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-122 |  | DI-87 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0084 comment raised on 12/01/2023 following the introduction of IF-019 and respective changes in the latest set of released artefacts MHHSP-BP010-Change of Registration Data -v4.5 "Shows Supplier Mastering Import Export Linkage. BSC CP1558 introduced changes to MPRS for the LDSO to manage this via the DB05. IF-019 should go to LDSO who should then produce a DB05 into MPRS." The process diagrams and requirement spreadsheets have been amended to show MPRS loading DB05 as a IF-019 response. DB05 is not a IF-019 response, it is a request from DNO/iDNO to create, amend or remove a import/export linkage. It does not currently have any capacity to include a IF-019 rejection response to trigger a IF-020 rejection response to DIP. (Raised as DI-87) |  | Implemented | [5 empty] | Interim Release 1 |  | SCS reviewing preferred option with LDSO's The following changes would be required to the LDSO overview requirements: MHHS-BR-LD-043.3 LDSO Send Import/Export relationship update LDSO must send accepted Import/Export relationship updates to the Registration Service via the appropriate interface DB05 file or other agreed mechanism BP010B Change of registration data 900 MHHS-BR-LD-043.4 LDSO Send Import/Export relationship rejection LDSO must publish rejected Import/Export relationship updates on the Data Integration Platform using the appropriate interface MHHS-IF-020 to Supplier BP010B Change of registration data 900 On BP-010 for Linked Import/Export MPANs the following would be required: 1. Need to add rejected leg from step 900 to DIP 2. Need to add PUB-020 going from the DIP to the Supplier The BPD-010 will need updating accordingly. | Process Model correction | MPAN Ownership |  | MHHSP-BP010-Change of Registration Data MHHSP-BPD010, MHHSP-BRS005, Traceability Matrix
MHHS-DIN-123 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0083 comment raised on 12/01/2023 following the introduction of a new business rule on MPRS in the latest set of released artefacts MHHS-BR-RS-078 "MPRS cannot control how messages are sequenced at CSS and DSP. IF MPRS waits until the DSP responds before sending the Appointment message this could take hours (as this is a batch process) this will result in a delay in the appointment of the MDR. Sequencing requirements should be placed on CSS & DSP to ensure the correct MDR is appointed based on Effective dates provided from MPRS. However, they may not be necessary due to the way this interface works: The C0200 interface uses the PUT Method, which will replace the data held at CSS. Explicit ending of an Appointment is only required for a future dated appointment, this will be sent as one message with the Old and New MDR appointments. For Same Day or Retrospective the new MDR Appointment will Replace the currently set value. This implicitly ends the previous MDR Appointment. On a CoS, the MDR is linked to a Registration not a Metering Point. The previous MDR will end naturally when the Previous Registration becomes securedInactive. An explicit message to end the MDR appointment on the Previous Registration is not required . MPRS will only send two separate updates to CSS when there is a gap in MDR (SDS) appointments. For Example a change of segment to Advanced and then back to Smart. This would need to happen over a short period to generate two messages that could go out of sequence" The MHHS design team rejected with comment "The MHHS design is based upon what was agreed as part of the R044 consultation. This scenario does not reflect our understanding of how the CSS/DCC/DSP interface will work as set out under R044. " This is how C0200 currently works today and the interface is unchanged in R0044. This will put a signfiicant requirement on MPRS that will reduce time available time for other core MHHS development activities with no benefit to industry.(Raised as DI-87) |  | Closed | [7 empty] | No Change - updated in v5.0 | No Change | MPAN Ownership
MHHS-DIN-124 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0089 comment raised on 12/01/2023 "D-021 was meant to give more detail on how L1-L4 validation should be used and provide more error codes for use. This has not been done as far as I can see Blocking resolution to this T4-COM-1749, T4-COM-1769 and T4-COM-1768" Comment was closed as clarified however none of these items have been resolved and we have no dates as to when they will be. comments blocked that were raised initially on 15/09/22 Comment T4-COM-1749: "The Registration Service, as part of its L3/L4 validation should ensure that there is consistency between the data content of the IF-033 issued to the Service Provider and the [returned] content in IF-034 - if this isn't so then message should be returned to Service Provider using ""MSGStatus Message"" mechanism." Does MPRS only need to validate consistency in the data it loads on the IF-033, not the data that is not loaded" Comment T4-COM-1769: "We need validation rules to be defined for this flow, Does not match IF-031, content of the PUB-034 does not match the IF-031. No Proposed Appointment Found, PUB-034, does not link to any Pending IF031s. Define Validation Rules for PUB-034 The 034 content must match the original if-031 content the 034 must have a corresponding IF031 the 034 has already been received for the IF-031 Generic Standard Validation, MPAN exists valid in ISD ETC" Comment T4-COM-2768: "We need some generic codes for standard validation rules such as: Service/Supplier is valid in ISD MPAN exists in MPRS MPAN is not Disconnected Service/Supplier is Valid in MDD (so CSS doesn’t reject updates)" (Raised as DI-89) |  | Implemented | [5 empty] | Interim Release 1 |  | Added RMP status check to IF-034 and refined validation rule notes regarding different values received from IF-033 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-125 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider | IF Routing | WOA-0091 comment raised on 12/01/23 D-030 "how routing will work in the DIP has not been updated this information is required for our development" MHHS Design Team has closed as clarified however there is still uncertainty around the DIP routing, and there are not dates provided for when the detailed DIP design will be released. This will clock certain elements of development (Raised as DI-90) |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Secondary routing rules updated following review with Avanade (see DIN268) |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-126 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0092 comment raised on 12/01/23 following more infromation around D-022 being clarified "D-022 Following the work off item being agreed on what is required for an MPAN to be traded - it has now been possible to fully assess the optionality of data items in the interfaces Data items still mandatory in interfaces that must be changed to optional: Annual Consumption (IF-001) Incumbent Service Providers (IF-002, IF-033) Incoming MS/DS (IF-037) These are not required at creation, nor at traded, and therefore could be non existent in MPRS when MPRS generates this outgoing IF messages Blocking resolution of T4-COM-1727 and T4-COM-1735" Closed as clarified however none of the issues listed have been resolved Annual consumption still reads madatory on a CoS for IF-001, the issue is MPRS may not have this data item. The item is not required to reach a status of traded, therefore CSS will accept a CoS on this MPAN without annual consumption being populated, and then MPRS will not be able to provide this data item on the IF-001 that results from the CoS. This must be changed to optional OR the definition on what is needed to be traded should be updated to include annual consumption. Incumbent Service Providers is still mandatory on IF-002 for CoS Again as MS is not required to be traded, CSS will accept a CoS request with or without a current MS, and so MPRS will not be able to provide an incumbent MS in these cases. It must be changed to optional or the definition of what is needed to be traded should include MS. Incoming MS/DS is still mandatory on IF-037, there are numerous reasons an appointment may be lapsed, the only change that would gaurantee a new incoming SP that MPRS could send on this flow is a change or SP (CSERV) scenario. For CoS the supplier may not have sent in new appointments, for DEREG there will be no new appoitnments, for SEG the market segment may have changed but the supplier may not have sent in new appointments, same for change of connection type, and for IMPEXP and RELATED the parent MPAN might not have MS/DS appointed at all so there would be no new appointments for MPRS to populate on this flow. This must be changed to madatory ONLY on CSERV (Raised as DI-91) |  | Implemented | [5 empty] | Interim Release 1 |  | Discussed with SCS. Covered by clarification on nullable and interface notes- All these issues are resolved by the Mandatory Nullable Solution. Confirmed Annual Consumption block will only be provided where available in Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-127 |  |  | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 "DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least "Registered", if no DS is appointed then there is already an appropriate Event Code" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone (Raised as DI-92) |  | Closed | [7 empty] | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-128 |  | DI-93 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0095 comment on 12/01/23 "D-009 This is blocking closure of T4-COM-1730. There is a lack of clarity around the treatment of rejection from CSS, between both R044 and the MHHS design artefacts e.g. MHHs-BR-RS-088.1 and MHHS-BR-RS-079 both suggest MPRS would still load the new MDR record and appoint in MPRS despite a rejection from DCC/CSS. Our assumption would be that we do not load a MDR appointment that is rejected from DCC/CSS and we send the IF-035 rejection to notify the DS/Supply of this. However no clarity on what to do if DCC/CSS rejects a MDR end date on a de-appointment T4-COM-1730 was raiseed on 15/09/22 MHHS Design Team Rejected the comment with a statement this is outside of MHHS Scope. How MPRS treats the MS/DS appointment and how it responds over hte DIP is within MHHS design. The requirements we are enquiring about are already included in the MHHS design documents as in scope also. This is a major blocker to MPRS design on MDR appointment processes (Raised as DI-93) |  | Closed | [7 empty] | Discussed with SCS this is a REC requirement. Agreed no error codes will be received, just use a generic response. | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-129 |  | DI-94 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0086 comment on 12/01/23 following the release of the first draft of IF-050 in the revised interface catalogue artefact "Related MPANs and Linked Import Export are not set at MPAN Creation. EES can get these on the IF020 Remove these blocks from IF-050 as they would never be populated" MHHS design team marked as accepted and changed but the blocks still exist in IF-050, these blocks will never be populated and so should be removed from the IF-050 interface(Raised as DI-94) |  | Closed | [7 empty] | Closed - duplicate of DIN-115 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-130 |  | DI-95 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Raised as WOA-0088 on 12/01/23 "D-011 & D-050 it is still unclear how LLFC and DUoS Tariff ID will be stored and managed in MPRS. DUoS should be an Alias of LLFC and not have its own data item in MPRS. LLFC will be renamed to DUoS Tariff when the old arrangements have ended. LDSO impacts having to maintain two items which will lead to billing issues" Marked as clarified and closed witih a clarification statement to be issued on tuesday 24th January, this clarification statement was not received. Awaiting clarification(Raised as DI-95) |  | Closed | [7 empty] | Email to Madison to check can close |  | MPAN Ownership
MHHS-DIN-131 |  | DI-96 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 is missing business rules: REG1001 - MPAN [DI-063] is at [REG.RMPStatus] not status Created/Operational. This should apply to IF-025. IF-025 is missing a rule that consent granualiry EFD must not be earlier than supply start date. Consent Granularity EFD must not be prior to current consent granularity EFD The Consent Granularity Energy Direction Domestic Premise Indicator Combination must be valid in ISD(Raised as DI-96) |  | Implemented | [5 empty] | Interim Release 1 |  | Updated consent validation rules in IF-025 (REG1001, REG1022 and1019) and IF-031 (REG1022) | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-132 |  | DI-97 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 IHD update does not include validation rule 1019, does this mean IHD EFD can be prior to current and effectively cancel out the current IHD status completely, or is it just an error and the rule should be added to interface catalogue for IHD?(Raised as DI-97) |  | Implemented | [5 empty] | Interim Release 1 |  | Amendment accepted | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-133 |  | DI-98 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 will not allow a SMSO to be set for a non smart meter "REG1022 - SMSO ID Cannot be set where Market Segment is [Reg.Segement]", would a non smart supplier be able to send a B031 SMSO block, they will need to be able to if they are required to clear an old SMSO by populating SMSO as null(Raised as DI-98) |  | Implemented | [5 empty] | Interim Release 1 |  | Added new requirement on Registration Service not to send SMSO and IHD information on non Smart segments (MHHS-BR-RS-004.2) | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-134 |  | DI-99 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-025 "SSC must be valid in ISD. Rejection reason: REG1044 - SSC must be a valid value in ISD" SSC are not yet populated in ISD(Raised as DI-99) |  | Closed | [7 empty] | Clarified that SSC validation will be based on Frozen MDD. Seperate DIN to cover availability of ISD | No Change | MPAN Ownership |  | MHHSP-EM021 ISD Entity Data Map, MHHSP-DES138-Interface Catalogue
MHHS-DIN-135 |  | DI-100 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | Should B032 PC and SSC block on IF-025 only be permitted when theres a traditional meter fitted at the MPAN?(Raised as DI-100) |  | Closed | [7 empty] | Agreed no functionality required. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-136 |  | DI-101 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | How is the Green Deal Exists defined. Does this mean there's a green deal linked to the MPAN regardless of dates, does it mean there's a green deal currently active or due to become active, or does it mean there is a currently active green deal assigned to the MPAN? (Raised as DI-101) |  | Implemented | [5 empty] | Interim Release 1 |  | Remove Green Deal exists (DI-110) from Data Catalogue and IF-050 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-137 |  | DI-102 | 2023-01-31 | St Clements |  | Madison Layton | Software Provider |  | IF-007 Validation rule "Metering Service [S0.SenderID] holds valid previous appointment then Energisation Status EffectiveFrom Date [DI-034] should be < [REG.App End Date] + 10" The way it's curently written suggests MPRS should accept an IF-007 from the previous appointed MS, event if there ETD was greater than 10 days ago, provided the ES EFD date was less than their ETD + 10. E.g the previous MS could send IF-007 two years later with ES EFD of their ETD + 10 days. Should it actually read: If Metering Service [S0.SenderID] holds valid previous appointment then system date < [REG.App End Date] + 10 and then a separate rule should then apply to ensure install/removal dates are withing period of ownership This would then allow the previous MS to submit IF-005 only up to 10 days after their appointment period and not beyond it, and ensure install dates must still be within their appointment period, which assume is intention of the rule? Linked to DI-41(Raised as DI-102) |  | Implemented | [5 empty] | Interim Release 1 |  | REG1003 validation rule updated in IF-007 to constrain energisation updates to 10 days after the MS appointment period |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-138 |  | DI-103 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-034 Submitted rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD |  | Closed | [7 empty] | Duplicate of DIN-176 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-139 |  | DI-104 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Need clarity on what role code should be used in C0200 for MS and MDR appointments Linked to comment T4-COM-1790 which was accepted as design issue raised but then moved to a work off item "We would like to see some indicative Role Codes and DIP IDs so we can populate development systems with this data " |  | Closed | [7 empty] | Send "MDR" as role code as per Registration requirement. Allocation of DTN MPIDs is a seperate issue | No Change | Registration | Existing EMAR I/F | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-140 |  | DI-105 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 |  | Closed | [7 empty] | Discussed with SCS the IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR. Agreed to close | No Change |  |  | MHHSP-BP003A, MHHSP-BRS003 Registration service requirements
MHHS-DIN-141 |  | DI-106 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 |  | Closed | [7 empty] | RECCo consequential change | No Change |  |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-142 |  | DI-107 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | There currently aren't sufficient rules to ensure that a principal primary MPAN is not also a linked export subsidiary MPAN or that a subsidiary secondary MPAN is not also a principal import linked MPAN. The MHHS design either should accommodate both (would need clarity on how to treat cases where MPANs are BOTH principal and subsidiary) OR new rules should be introduced to prevent this occuring AND cleanse existing cases ahead of migration |  | Implemented | [5 empty] | Interim Release 1 |  | Validation rules updated for IF-019 | Missing/incorrect validation rule | MPAN Ownership |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-143 |  | DI-108 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | Requirements were uplifted in v4.5 to include logic around market segment on related MPANs MHHS-BR-RS-124.1: Registration Service must, in the case of Related MPANs and following derivation of Market Segment for individual MPANs, update the Market Segment for the Primary MPAN and all the Secondary MPANs based on the following rule: 1. If any MPAN in the Related MPAN Group has a (derived) Market Segment of Advanced, then set the Market Segment for all the MPANs to Advanced and set the Market Segment Valid Flag to "Yes" for all the MPANs This specifically cites related primary/secondary and does not mention linked import/export associations at all. But then another requirement implies maybe it should have done: MHHS-BR-RS-127: Registration Service must , in circumstances where the derived market segment is invalid (and has not been overridden by Linked/Related MPAN logic ) Should MHHS-BR-RS-124.1 have applied to linked import/export associations too or is it intended solely for primary/secondary related MPANs? |  | Implemented | [5 empty] | Interim Release 1 |  | This should only apply to Related MPANs. Updated RS-127 | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-144 |  | DI-109 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131 This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to: Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. |  | Closed | [7 empty] | Duplicate See DIN-169 | No Change | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-145 |  | DI-110 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. |  | Implemented | [5 empty] | Interim Release 1 |  | Added L as valid value for DI-979 in IF-035/ Data Catalogue. Added validation rule that L cannot be provided with IF-034 and added new error code. Updated DI-143 to be called Proposed Appointment Response Code in IF-034, IF-035 and Data Catalogue. Added Lapsed value error codes in IF-035. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-146 |  | DI-111 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. |  | Implemented | [5 empty] | Interim Release 1 |  | Agreed with SCS to reuse STD Error Response Section in IF035 to communicate Lapsed Reason . See DIN-145 for summary of updates | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-147 |  | DI-112 | 2023-02-06 | St Clements |  | Madison Layton | Software Provider |  | IF-008 response block is listed as mandatory, however on disconnection the MPAN is de-energised by MPRS automatically. The supplier cannot de-energise after disconnection on the IF-007, it must be automatic at MPRS as per The de-energisation needs to be communicated on the IF-008 but it is not in response to an IF-007 and so we cannot populate the response block. |  | Implemented | [5 empty] | Interim Release 1 |  | Data interface change agreed. Added Interface note to IF-008 to cover forced de-energisation changes by Registration Service | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-148 |  | DI-113 | 2023-02-10 | St Clements | 2864 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-113 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { "confirmingMpid": "string", --* "registrationId": "string" --*, "updateSucceeded": boolean --* } Suggest that DI-0980 is removed from B066 |  | Closed | [7 empty] | Discussed with SCS and agreed to close - note no error codes returned from CSS so will provide generic error code | No Change |  |  | MHHSP-DES138-Interface Catalogue, JSON, YAML
MHHS-DIN-149 |  | DI-114 | 2023-02-10 | St Clements | 2865 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-114 in our log Artefact: MHHSP-DES138-Interface Catalogue v4.6 On IF-038 validation "REG1073 - Customer Direct Contract already exists for MPAN [DI-063] for that period" The respective validation rule for this states: If Contract End Date [DI-145] <= Max existing active MS contract end dates [Reg.MAX_DCMS_Enddate], EXCEPT IF requesting MS [S1.SenderID] = Currently Active Direct MS [Reg.CurrentActiveDC_MS_DIPID] AND Contract End Date [DI-145] <= existing active MS contract end date [Reg.CurrentDCMS_Enddate] This rule doesn't fully prevent overlapping appointments as does not cover where the MS is not currently contracted MS and ETD > current ETD which should also be rejected. Think a simpler rule would cover this scenario more fully e.g. If there is an active contracted MS/DS, and the submitting MS/DS does not match then reject And then ETD can be greater or later than current ETD for the currently contracts MS/DS anyway so doesn't need specifying? |  | Closed | [7 empty] | SRO Team do not believe that a change is required. Linked to DIN-554 |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-150 |  | DI-115 | 2023-02-10 | St Clements | 2866 | Madison Layton | Software Provider |  | As requested just sending the last three DI’s we have individually through. This one is DI-115 in our log In some place on IF-038 tab there is reference to a future customer direct contract e.g. "OR requesting MS [S1.SenderID] <> Any future Direct MS [Reg.FutureDC_MS_DIPID] " "extended dates will be subject to checking if another Service Provider has registered a separate Customer Direct Contract covering the same period" - this can only happen if there's a future appointment "AND ALSO removing all future periods which may or may not have been accepted and recorded previously." As there is no Effective From Date included in the flow MPRS will store an Effective From Date of the system date at the time of creation of the customer contract indicator. It will not be possible to set one to start in the future as the IF-038 does not include effective from date. Is this the same understanding as the MHHS Design Team? |  | Closed | [7 empty] | As per DI-149 above SRO Design Team do not belive that any changes are required |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-151 |  | DI-116 | 2023-02-10 | St Clements | 2868 | Madison Layton | Software Provider |  | Just spotted a change in v4.7 and raised in our log as DI-116 Artefact: MHHSP-BP010-Change of Registration Data -v4.7 under MPL and GSP Group amendment section, DB02 has been amended in v4.7 to DB002. DB002 is not correct, DB02 was the correct name For reference the DB flows only ever have one 0 in, there is DB01 (MPAN creation), DB02 (MP updates), DB03 (Disconnection) and DB05 (Import/Export Linkages) |  | Implemented | [5 empty] | Interim Release 1 |  | BP010A step 10 flow name change to DB02, BP010B step250,step440, Step560 flow name change to DB02, and update BPD descriptions to DB02. | Process model correction | MPAN Ownership | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-152 |  | DI-117 | 2023-02-14 | St Clements | 2912 | Madison Layton | Software Provider |  | On looking more closely at the validation rules for IF-019 spotted a few issues. IF-019 REG-1061 rule for Related Create event code appears to be written incorrectly. The rule and rejection description don't quite align. Rule: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) are not currently part of an import/export relationship Rejection reason: REG1061 - Prosposed MPAN(s) [DI-073] / [DI-074] are already part of a Related MPAN Relationship Should the rule read: If Event = [RelatedCreate] and (MPAN [DI-073] or MPAN [DI-074]) is currently part of a related primary/secondary relationship? The rule and descriptions also don't appear to fully align for some in import/export section too - REG1052, REG1055, REG1057 and might need some minor tweaks to correct. |  | Implemented | [5 empty] | Interim Release 1 |  | REG1061, 1052 and 1055 rules updated. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-153 |  | DI-118 | 2023-02-14 | St Clements | 2913 | Madison Layton | Software Provider |  | On working on detailed design for Related MPANs, noticed the IF-019 interface is missing a rule that the Secondary MPAN must not be a Primary in another Relationship. You could expand REG1064 to include this as the description sounds like it should have been covered here. Rule: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN Description: REG1064 - Proposed Secondary MPAN [DI-074] is already part of a different MPAN Relationship Could amend rule to: If Event = [RelatedAdd] and [DI-074] is linked to a different primary mpan ie [DI-073] <> Primary MPAN OR [DI-074] is already in a relationship as a Primary MPAN |  | Implemented | [5 empty] | Interim Release 1 |  | REG1064 validation rule updated | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-154 |  | DI-119 | 2023-02-15 | St Clements | 2919 | Madison Layton | Software Provider | IF-019 validation gap on primary and subsidiary MPAN | On further detailed design we’ve spotted a potential design gap. Currently it is possible to enter a state where an MPAN is both a primary and subsidiary MPAN at the same time (e.g. Primary but also export linked or Secondary but also import linked). The current MHHS doesn't accommodate an MPAN being in both states at the same time. We’ve already looked to add rules to try to mitigate this on DB02/DB05 internal flows but would need additional rules on IF-019 to fully prevent this scenario occurring. Rules we think are required: 1. On receipt of IF-019 with event code RelatedCreate or RelatedAdd, the primary MPAN must not have energy direction of Export 2. On receipt of a IF-019 with event code RelatedCreate or RelatedAdd, any listed secondary MPAN must not in an active Import/Export relationship as the Import MPAN 3. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Import MPAN must not be in an active relationship as the secondary MPAN 4. On receipt of a IF-019 with event code LinkedImportExportCreate or LinkedImportExportAdd, the Export MPAN must not be in an active relationship as the primary MPAN |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Agreed with SCS that changes to IF-19 tab would be made to support Rules 1 and 4. Validation Rules updated accordingly with new Error codes (REG1067/1068) created to support. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-155 |  | DI-120 | 2023-02-15 | St Clements | 2930 | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. |  | Closed | [7 empty] | see also DIN-172/173. Included in 5.1 DUPLICATE See DIN-172 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-156 |  | DI-121 | 2023-02-24 | St Clements | 3078 | Madison Layton | Software Provider |  | We have logged a new design issue under DI-121. IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP |  | Closed | [7 empty] | Duplicate of DIN-173 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-157 |  | DI-122 | 2023-02-27 | St Clements | 3090 | Madison Layton | Software Provider |  | New design issue (SCC Ref DI-122) for the IF-005 related to REC CP R0032. The current v5.0 validation in the IF-005 does not include the new validation introduced with REC CP R0032 (R0032 is approved and being implemented in the D0312 this June): NEW REC CP R0032 Validation: V Rejected – ESME ID already exists within MRPS and does not match Removed Meter, Associated Import/Export MSID or Related MPAN W Rejected - MSN relates to a Smart Meter Type and the ESME ID is NULL X Rejected – ESME ID Format is Invalid Y Rejected – Number of Displayed Register Digits is NULL and the MSN relates to a Smart Meter Type Z Rejected – Non-Smart Meter Type with Number of Displayed Register Digits populated AA Rejected – Meter Location is invalid AB Rejected – Non-Smart Meter Type with ESME ID populated AC Rejected – Number of Displayed Register Digits is incorrect IF-005 Validation: V not covered, needs to be added as a Level 5 Validation Rule W is already covered by DI-085 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) X is already covered in DI-085 population notes (Level 4 validation RCP1023 Msg Contains Invalid Valid Value Combination(s)) Y is already covered in DI-091 Optionality Rules (Level 4 validation RCP1021 Msg Mandatory Data Item Missing) Z is not explicitly covered, suggestion: add to DI-091 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AA is covered in the population notes AB is not explicitly covered, suggestion: add to DI-085 population notes to say Smart Items on non smart meters will be rejected with RECP1023) AC not covered, Suggestion: add the following population note from R0032 to DI-091: Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” Summary Please add the following Changes to the IF-005 to align it with the D0312 validation and maintain the same level of Smart Meter data quality in the Registration Service: New Level 5 Validation rule for DI-085 implementing V from the D0312. ESME ID must be unique within MPRS unless it’s a Linked MPAN where the same Smart Meter can be shared across Linked MPANs New population note for DI-091, only to be included for Smart Meter Types New population note for DI-085 , only to be included for Smart Meter Types New population note for DI-091, Where the Meter Type is S1, the value should be populated as per the manufacturer specification. Where the Meter Type is S2AD, S2ADE, S2B, S2BD or S2BDE the value should be “5”. Where the Meter Type is prefixed with “S2C” the value should be “6” |  | Implemented | [5 empty] | Interim Release 1 |  | New Validation Rules added to IF doc to ensure full coverage and alignment with CP Error codes described | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-158 |  |  | 2023-02-27 | Elexon | 2908 | Derek Weaving | Central Body | Use of CCCs to categorise the data for future charges | As part of the Performance Assurance Working Group discussions on Supplier Charges, we are exploring the use of CCCs to categorise the data for future charges. It is noted that Settlement Period Quality Indicator referenced in the VAS Method statement is for illustrative purposes and would welcome clarity on the following: · What is the intended process to populate the Settlement Period Quality Indicator in the initial ISD Table? · What would be the process to be involved in those activities to determine the categorisations should additional CCCs be required? |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | This DIN has been moved to Interim Release 5 as it is related to DIN-409 which has an objection raised that is pending a discussion to clarify the solution. Name change and field length have been actioned. Reviewing whether any changes to Settlement reports are required Recommending a change to this ISD Data Item: Settlement Period Quality Indicator to be set as per Appendix 1 of MHHSP_METH007 MDS_Method_Statement v5.0 This data item need to be changed to something like ‘Valid Settlement Period Quality Indicator Set’ and the field size needs to be increased. The data catalogue will need the revised data item and the field length will need increasing from 20 to at least 100. This Item also appears in some interfaces that will need to be updated. This is because it represents a set of SPQIs. The initial intention is to populate as per the table and check if any new SPQIs have been introduced in the baseline design Method Statement that are not covered. If new CCCs are introduced the appropriate flags for each new CCC would need to be agreed. However, it is likely that another dimension to the table below would need to be introduced to facilitate new CCCs. Word 'Illustrative' to be removed and will be updated to say Valid Settlement Quality Indicator Set. Change to be made across all impacted Method Statements. New CCC's will require a Modification to the BSC interface requirement. Proposed changes have been reverted to the initial state. Data item Settlement Period Quality Indicator, with a field length of 5. This is due to the agreed solution for DIN409 following DRG where it was agreed the list element would be removed in favour of individual row(s). The word 'Illustrative' will also remain within the Method Statements. | Missing/incorrect validation rule | Meter to Bank | Volume Allocation Service | MHHSP-METH006_VAS_Method_Statement MHHSP-METH007_MDS_Method_Statement v5.1 EDI021 ISD Entity spec
MHHS-DIN-159 |  |  | 2023-03-01 | ENWL | 2994 | Paul Band | Network Business | Interfaces for UMSO | DES-138 Interface Inconsistencies vs BSCP7XX for UMSO Discussions with ENWL have highlighted a number of inconsistencies in the Interface Catalogue when it comes to routing for UMSO's. DIN-106 also refers. UMSO is not listed as a recipient in DES-138 for the PUB-008, but this is in the draft BSCP and should be added to the PUB UMSO is not listed as a recipient in DES-138 for the PUB-020, but this is in the draft BSCP - this is not needed in the BSCP as there are no unmetered Related MPANs UMSO is not listed as a recipient in DES-138 for the PUB-035, but this is in the draft BSCP - view that it is unlikely for this flow ever to be used as the appointment will not trigger any processes to need a subsequent update UMSO Is listed as UMSI, not UMSO in PUB-036 in DES-138 UMSO is listed as UMSC, not UMSO in PUB-018 in DES-138 The IF_LIST tab should be reviewed for consistency |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | As with DIN-106, there are inconsistencies in the Interface Catalogue for UMSO routing. This has been compounded by a review of the draft BSCP for UMSO, which has added a number of PUB flows going to UMSO that aren't currently in the catalogue. Covered by updated secondary routing rules (see DIN268) Design to check requirements in BSCP and MHHS BPs and ensure the interface catalogue reflects a consistent approach | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue and possibly related business processes and descriptions E2E001
MHHS-DIN-160 |  |  | 2023-03-14 | Ovo Energy | 2862 | David Morley | Supplier | BP009 flow addition | Steps 205 and 210 in BP009 wont be completable in the event that theres no comms. I think the process would be workable if there was an exception route here - see red arrow below. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Update Steps 205 and 210 in BP009 with "Comms Available" line label add flow from step 205 to step 215 with “Not Commissioned / No Comms” line label | Process Model correction | Metering Changes | Change of Metering | MHHS-BP009
MHHS-DIN-161 |  |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 requirement correction | MHHS-METH001-5.4c Please confirm the requirement: “where daily advance records are available [either in the past or future] and less than 90 days months different from the UTC Date requiring a daily advance - use the mean actual Meter advance from the closest [4] weeks for the same Day Type (as defined in ISD).” |  | Closed | [7 empty] | Duplicate of DIN 97. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-162 |  |  | 2023-03-14 | CGI | 3383 | Dave Webster | Consultancy | METHOD001 typo | MHHS-METH001-5.5 typo “Where DAEs are required to be calculated the SDS shall use the most recent data a based on the event that triggered the estimation.” |  | Closed | [7 empty] | Duplicate of DIN 98. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-163 |  | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Conditionality Rule for B037 | It is not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure it is unclear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated conditionality rule for Block B037 in IF-001, IF-002, IF-033, IF-036: to show that Either DI-075 (Primary MPAN) or DI-079 (Secondary), and not both, should be populated where MPAN (DI-063 above) is part of a group of Related MPAN. |  | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-164 |  | DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0093 comment raised on 12/01/2023 "" D-019 This document was not included as part of the M5 baselined work off item Blocking resolution to T4-COM-1692"" Whilst the IF-005 guide has now been released it does not clarify and resolve the T4-COM-1692 which was raised on 15/09/2022 MHHS-BR-RS-132: ""It is not possible to future date a meter installation or removal, it is always retrospective, so it won't be possible for this activity to happen within the Prospective MS appointment period"" To enable MPRS to do this the validation rules reflected in the interface catalogue and IF-005 must allow the prospective appointment to make changes on a SEG scenario. Linked to DI-42" |  | Closed | [7 empty] | "This requirement stands - review with SCS in light of SEG scenario. We believe REG1012 is correct for Meter Update. Design has been based on SEG only accommodating the BAU Meter Install, Exchange or Removal events. The Meter Type will be updated during the Meter Exchange or Meter Install event. In case of an error being sent in one of these events, Metering Service would have to do a cosmetic exchange to correct the error...". Reviewed with SCS and agreed to close | No Change |  |  | MHHSP-DES138-Interface Catalogue MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-165 |  | DI-122 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | See separate sheet Duplicate of DIN-157 |  | Closed | [7 empty] | CR required to add rules in line with CP R0032 Added Miscellaneous Data Validation to IF-005 to cover REC CP R0032 validation rules Wrapped up into design teams main CR Doesn't need to be raised by SCS | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-166 |  | DI-77 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On a succesful implementation of DS App, MPRS applies consent granularity, should it also apply the change to all child MPANs? Linked to DI-54" |  | Implemented | [5 empty] | Interim Release 1 |  | Added clarification to REG Notes re Consent and Related MPANs | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-167 |  | DI-78 DI-86 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Can the supplier change the EFD of the MS/DS. Assume not? If IF-031received with USP and the EFD is different to the current MS/DS EFD, how should MPRS respond? Reject? Update SP EFD in MPRs? " |  | Closed | [7 empty] | Agree you can't. Could update 1032 rule for USP? Duplicate see DI-29 | No Change
MHHS-DIN-168 |  | DI-92 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "WOA-0094 raised on 12/01/23 for a comment still unresolved that was raised 15/09/22 ""DI-022 T4-COM-1717 which is linked to D-022 has not yet been resolved It is possible for a Traded Import to be associated with an Untraded Export and vice versa. In this case the Untraded Associated MPAN may not be registered to a Supplier and therefore won't have an Aligned MS and DS. This MPAN will be Invalid as it must be Registered and Traded. I think we need an Extra IF045 Event Code to cover this scenario where the Associated Import or Export is not Traded this scenario is not possible for Related MPANs, as the Supplier must be the Same Supplier for the Primary and Secondary therefore they must both be at least ""Registered"", if no DS is appointed then there is already an appropriate Event Code"" This was rejected by MHHS Design Team under the M5 work off items but should still be tracked and resolved as a design issue outside of the M5 milestone |  | Closed | [7 empty] | CR for new functionality. "Already covered by no MS/DS appointed - MPRS would try to align MS/DS with principle and couldn't as there's no registration to align this to. Need an extra check that can only autoappoint if there's a registration to prevent MPRS crashing Maybe one for DRG? Jon at RECCO for consequential change? Agree not to build for this scenario as this would be an edge case and close | No Change
MHHS-DIN-169 |  | DI-109 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | MHHS-BR-RS-131This requirement has been overcomplicated as it's trying to, unecessarly, accomodate for other requirements already defined elsewhere. MPRS must be able to reject or lapse for other valid reasons e.g. reject if invalid in ISD, lapse if disconnected and deregistered, which this rule currently conflicts with. Suggest this requirement should be simplified to:Registration Service must, where the Appointment reason is SEG, only send a lapsed/rejected appointment notification to the Service Provider if it is 2 working days (configurable) beyond the appointment date, unless the appointment date is less than the system date and the Supplier requesting the appointment does not match the current Supplier. |  | Implemented | [5 empty] | Interim Release 1 |  | Simplified MHHS-BR-RS-131 on when to lapse a SEG appointment | Requirement correction | MPAN Ownership |  | MHHSP- BRS003, MHHS-BR-RS-131
MHHS-DIN-170 |  | DI-110 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-035 response block B007 is currently stated as mandatory. This can't be populated for event code [MSAppLapsed] or [DSAppLapsed]. |  | Closed | [7 empty] | Duplicate of DIN-145 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-171 |  | DI-113 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Artefact: MHHSP-DES138-Interface Catalogue v4.6 IF-035 B066 DI-980 The Message we receive back from CSS does not contain any further information other than the outcome of the MDR Appointment. Therefore B066 DI-980 will never be populated. Here is what we get from CSS: ContextType: ERDA SupplierArrangedAppointmentUpdateNotification Data: { ""confirmingMpid"": ""string"", --* ""registrationId"": ""string"" --*, ""updateSucceeded"": boolean --* } Suggest that DI-0980 is removed from B066" |  | Closed | [7 empty] | Agreed with SCS being retained but due to optionality may have to populate text e.g. contact DSP. Close | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-172 |  | DI-120 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Noticed IF-031 is missing validation to ensure on CoS scenario the Supplier is the pending supplier not the current supplier. The CoS scenario should only be used as part of a CoS process as validation may differ slightly from other scenario types. The current supplier should instead use CSP or SEG as is appropriate. |  | Implemented |  |  |  |  | 2023-04-27 | Interim Release 1 |  | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-173 |  | DI-121 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation to ensure on SEG scenario the Supplier is either the current Supplier or the Pending supplier. Previous Suppliers should not be able to amend the SP |  | Implemented |  |  |  |  | 2023-04-27 | Interim Release 1 |  | Validation rules updated to better match App Secnario with Supplier/SP. Requesting flexiblity on error messages | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-174 |  | DI-72 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "A new rule has been added in v4.5, for IF-034, where the MDR EFD must = either SSD or existing MDR EFD + 1 It should be possible to set a Submitted MDR EFD > existing MDR EFD (not just = existing MDR EFD + 1) This should have read >= not = Supect this is linked to DI-60" |  | Implemented | [5 empty] | Interim Release 1 |  | "Agreed- doc updates MDR can have gaps between DS EFD and MDR EFD" Updated REG1083 validation in IF-034 so that it allows MDR Effective from dates >= SSD/ DS Eff From date/Existing MDR Eff from date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-175 |  | DI-82 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "I’m not clear what is expected in the B908List structure, which provides the Meter and MAP details for Related MPANs. The Swagger OpenAPI Specification, shows the following structure: “B908List”: [ {“existingMeter”: { “primaryMPAN”: “<MPAN 1>”, ”secondaryMPAN”: “<MPAN 3>”}, “historyMAP”: [ {“ existingMeter”: {“meterID”: “LY4545T”, “meterType”: “S1”, “ESMEGUID”: “RT-67-FE-RT-54-FG-TR”, “meterLocation”: “T”, “numberOfDigitsCumulativeRegister”: 5, “meterInstallationDate”: “2022-03-21T19:05:00+00:00” }, “historyMAP”: [ {“meterAssetProvider”: “MAP1”, “meterAssetProviderEffectiveFromDate”:“2020-06-11T16:25:00+00:00” }, {“meterAssetProvider”: “MAP2”, “meterAssetProviderEffectiveFromDate”:“2022-03-21T19:05:00+00:00” } ] } } ] From the above structure I don’t think its clear which MPAN the meter details actually relate to. If we assume the pending message was for MPAN 2 (secondary) and MPAN 1 is the Primary and MPAN 3 another secondary, the meter details would need to be provided in the B908List (Related-MPAN-Meter-MAP) for MPAN 1 and MPAN 3 so how are the meter details linked to the appropriate MPAN?" |  | Closed | [7 empty] | Duplicate entry | No Change | MPAN Ownership
MHHS-DIN-176 |  | DI-103 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-034 new rule: if event = [SDS-MDRUpdate] and [DI-841] > SYSDATE + 5 This should apply to DS Response event code too, not only MDR Update code, as this would also include a MDR EFD" |  | Implemented | [5 empty] | Interim Release 1 |  | Agreed -doc updates Updated REG1082 to apply for both [SDS-MDRUpdate] and [DSAppSPRepsonse] events in IF-034 | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-177 |  | DI-105 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Is IF-035 required on a de-appointment of MDR Diagram MHHSP-BP003A-CSSandDCC Update - v4.5.pdf suggests an IF-035 is not required on De-Appointment but the Registration Service requirements say send an IF-035 for every response from DSP MHHS-BR-RS-080 " |  | Closed | [7 empty] | "Reason for IF-035 is to trigger when SDScan send the Meter info" & The IF-035 is used to confirm the outcome of the new MDR not the deappointment of the old MDR Agreed with SCS no changes are required, they now understand the context agreed to CLOSE | No Change | MPAN Ownership |  | MHHSP-BP003A
MHHS-DIN-178 |  | DI-106 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | MS missing a requirement to send MS updates to CSS | Missing a requirement to send MS updates to CSS on C0200 like there is for MDR MHHS-BR-RS-078 |  | Closed | [7 empty] | Closed as discussed with SCS that this is out of scope for MHHS Programme. | No Change
MHHS-DIN-179 |  | DI-111 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-035 The Service Provider Proposed Appointment Response Code population notes currently states this should be populated with IF-034 response provided by service provider but the IF-034 could have been initiated by DS to update MDR and therefore not have a response block. |  | Closed | [7 empty] | Duplicate of DIN-146 | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-180 |  | DI-125 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 the Meter Removal is currently not permitted for a prospective MS Is it possible for the MS to need to remove two meters and replace it with one? In which case meterexchange would only allow them to do part of this process (remove 1 and add 1) but not complete it, so SEG could not complete. Should meter removals therefore be allowed for prospective MS? (REG1019) |  | Implemented | [5 empty] | Interim Release 1 |  | Revised REG1019 and added REG1027 for MeterRemoval event in IF-005 | Requirement correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-181 |  | DI-126 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | Missing Rule on If-005: MAP EFD must not be > removal date |  | Implemented | [5 empty] | Interim Release 1 |  | Added new rule for MeterUpdate and MeterHistoryUpdate events so that MAP EFD must not be > removal date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-182 |  | DI-127 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-005 On exchange - the MAP and IHD groups are for new installation not removed meter - does this need to be clarified? |  | Implemented | [5 empty] | Interim Release 1 |  | New note added to IF-005 to clarify that only the newly installed MAP and IHD information is required on MeterExchange | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-183 |  | DI-128 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | IF-005, IHD EFD missing validation in IF-005 (Between install and removal date) |  | Implemented | [5 empty] | Interim Release 1 |  | Covered Release 5.1, IF-005, IHD EFD missing validation added | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-184 |  | DI-129 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "IF-005 incorrect validation rule: REG1010: On event code Meter exchange and Meter Install rule states MAP EFD >= Install date, it should be = not >=" |  | Implemented | [5 empty] | Interim Release 1 |  | IF-005: Updated to REG1010 (MAP Eff from date check ) to = install date for MeterInstall and MeterExchange | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-185 |  | DI-130 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | It should not be possible to change MDR EFD once set. Need validation rules to enable MPRS to reject if IF-034 is submitted with current MDR but a different EFD. |  | Implemented | [5 empty] | Interim Release 1 |  | Agreed - doc updates Covered by L3/4 validation as per updated Validation rule notes | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-186 |  | DI-131 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031, there is currently not enough validation to ensure on a SEG, that the same SP isn't appointed for the current registration. Need additional validation rule: If scenario SEG and current supplier, then SP must not be current SP. |  | Implemented | [5 empty] | Interim Release 1 |  | Agreed - doc updates Updated validation rule Added REG1095 in IF-031 to check different Data Service proposed for SEG appointment | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-187 |  | DI-132 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Supplier inability to appoint MS/DS for Principal and Subsidiary MPAN | Unhappy Path Scenario: Receive IF-031 for MPAN that is both Principal and Subsidiary MPAN at the same time. This will be rejected as per REG1038/REG1039 Supplier will be unable to appoint MS/DS for the MPAN or any related/linked subsidiary MPANS. |  | Closed | [7 empty] | Closed, there is an existing to prevent this scenario happening going forward. Agreed with SCS to raise examples in the Data Cleanse Forum. | No Change
MHHS-DIN-188 |  | DI-133 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On If-031 the rule REG1030 reads [DI0-828] in not a valid UMSO in DNO [DI-108]/[DI-109] This should read LDSO not DNO |  | Implemented | [5 empty] | Interim Release 1 |  | Tied up with If-005 rejection description flexibility action Change REG1030 to read: REG1030 - [DI0-828] in not a valid UMSO in LDSO[DI-108]/[DI-109] SC change incorporated into 5.1.1 | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-189 |  | DI-134 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "On IF-031, REG1036 is written to only apply to USP when it should apply to all scenarios? ""Proposed MDR Date [DI-836] >= [REG.MPAN_SUP_SSD] However don't think this rule is required at all as this is already covered under the REG1036 rule that MDR Date < DS EFD? Linked to DI-66" |  | Implemented | [5 empty] | Interim Release 1 |  | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-190 |  | DI-135 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | On IF-034 missing validation rule REG1001 - MPAN [DI-073/DI-074] is at [REG.MPStatus]/[REG.RMPStatus] not status Created/Operational |  | Implemented | [5 empty] | Interim Release 1 |  | Agreed - doc updates Updated validation rules | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-191 |  | DI-136 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider | Addition of validation rules to MPRS to restrict Retrospective changes | MPRS does not currently prevent Retrospective changes to DUoS Tariff ID or Connection Type. Should MPRS add new validation rules for these items to restrict Retrospective changes? Please can you update DIN-191 to include Disconnection Date & Export Association. We don't currently have any restriction on how far these data items (and the others in DIN-191) can be back dated. This is a retrospective change through the DB interface and not a Manual Amendment. There are no retrospective periods for the following data items, this means the data items could be changed earlier than the settlement window and cause issues for settlement. There are restrictions that these data items must be within MS/Registration periods where appropriate, but the EFD/SSD could still be years into the past. - MDR EFD, - MS EFD, - DS EFD, - IHD Status EFD, - PC EFD, - SSC EFD, - Energisation Status EFD |  | Closed | No |  | Design gap | LDSO (SCS) |  |  |  | Covered in the retrospective changes discussion at DRG. | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-192 |  | DI-137 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | For If-031, scenario SEG, the business process diagram/requirements only describe the appointment lapsing once reaching it's SSD if no SA is received. If we receive a cancellation we would like to lapse the appointment at that point in time (it cannot become secured active after being cancelled) and not wait until the SSD to do this. |  | Implemented | [5 empty] | Interim Release 1 |  | Added new requirements to BRS003, MHHS-BR-RS-24.1 and 58.1 | Design Ambiguous | MPAN Ownership |  | MHHSP-BRS003-Registration Requirements
MHHS-DIN-193 |  | DI-138 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | The YAML name for metered indicator (Data Item 127) is meteredUnmeteredIndicator. This is then set to true of false. It isn't clear whether true means it's metered or unmetered due to the naming convention. It should be named meteredIndicator instead to make it clear true means metered, false unmetered. |  | Implemented | [5 empty] | Interim Release 1 |  | Updated YAML details in the Data Catalogue for DI-127 Metered Indicator. Updated YAML accordingly Updated data catalogue/ YAML | Design Ambiguous | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-194 |  | DI-1 | 2023-03-15 | St Clements | 4475 | Madison Layton | Software Provider |  | For IF-035 what is Event Code [IMS-SendMTD] intended for? If intended for sending to old MS then this should be done via secondary routing on the original IF-035, not via another separate IF-035 message produced by MPRS with different event code. |  | Closed | [7 empty] | This message is effectively a copy of the DSAppAccepted AND/OR MSAppAccepted but sent to the Incumbent (current) Metering Service to act as a trigger for that MS to send MTDs. This should be created by MPRS. Requirements MHHS-BR-RS-053 and MHHS-BR-RS-019 cover Registration Service sending this. Message to check and close | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-195 |  | DI-76 | 2023-03-15 | St Clements |  | Madison Layton | Software Provider |  | "Originally raised as T4-COM-1691 on 15th Sept 2022: ""MHHS-BR-RS-131 rule is in conflict with the change of Segment diagram, the rule says wait 5 days beyond the appointment date, but the Business process Diagram says 2 days "" Whilst the MHHS-BR-RS-131 rule was updated to 2 days in the MHHSP-BRS003-Registration Service requirements, the Interface Catalogue, under IF-031 REG1037 for SEG still reads 5 Interface catalogue needs updating to reflect +2 not +5" |  | Implemented | [5 empty] | Interim Release 1 |  | Agreed doc update Also in Reg Notes tab Updated validation rules and Reg notes Updated REG1037 in IF-031 to 2 workings days and updated REG notes, to align with process and requirements | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-196 |  |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Updates are required to clarify nullable fields |  | Implemented | [5 empty] | Interim Release 1 |  | Updates to Interface catalogue includes changes to interfaces and block data items which are present and can be null 1. MHHSP - ERI011A - ECS Reports - Internal v5.1: The data catalogue is the only tab that has been updated 2. MHHSP - ERI011B - ECS Reports - External v5.1: The data catalogue, DIP_Common, MHHS-REP-003 and MHHSP-REP-006 have been updated |  | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue, MHHSP-E2E001 End-to-End Solution Architecture MHHSP - ERI011A - ECS Reports - Internal MHHSP - ERI011B - ECS Reports - External
MHHS-DIN-197 |  |  | 2023-03-15 | Avanade/ Design Team |  | Paul Pettitt | SI Design |  | Decision taken to document digital signing of interfaces outside of the interface document. |  | Implemented | [5 empty] | Interim Release 1 |  | Remove Z0 and ZI blocks from all interfaces. Signing process will be documented in the Code of Connection document. | Technical corrrection | All Areas | Interface Catalogue | MHHS-DES138-Interface Catalogue Code of Connection
MHHS-DIN-198 |  |  | 2023-03-15 | Large Suppliers |  | Haz Elmamon | Large Suppliers | Complex Meter Site | Clarification on complex meter site, passed down from DAG as part of the work off plan, Haz to gather concerns for discussion at DA. LSC Rep provided information to the issue on 22-Mar-23 |  | Closed | No |  | Further information required | Large suppliers | [5 empty] | MPAN Ownership
MHHS-DIN-199 |  |  | 2023-03-23 | BGAS | 3460 | Neil Strange | large Suppliers |  | Participant wishes to see the use of standardisation in the interfactions between the SDS and sub roles MDR PSS |  | Closed | [7 empty] | Closed based on recommendation for programme CR to be raised by the Large Supplier Rep | No Change | Supporting Docs | SDS Validation / Extimation | MHHS-DES138-Interface Catalogue
MHHS-DIN-200 |  |  | 2023-03-24 | CGI | 3489 | Chris Beard | Software Provider | Hierarchy definition for selecting correct register reading in the case of multiple readings for the same settlement period | If there are multiple register readings available for the same Settlement Day, where is the hierarchy defined for selecting which should be used? Is this solely based on Reading Method (i.e. 1. A – Actual, 2. C – Customer, 3. E – Estimated by SDS, 4. S – Estimated by Supplier) or is it dependent on other factors such as the Event Code in the IF-041 ([ReadingRemv], [ReadingInstl], [ReadingEnergisationChg], [ReadingCOR], [ReadingOnSite], [ReadingCOS], [DSEstimate], [SupplierAgreedCOS], [ReadingOverride], [ReadingRemote])? |  | Closed | [7 empty] | Reading methods do not apply to Register Readings - recommendation for DIN to be closed. | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-201 |  |  | 2023-03-24 | ESG | 3529 | Patricia Parker | Software Provider |  | IF-033 Validation for population into the IF-034 The receiving party business validation rules state “Each Service Provider will need to determine their own validation criteria when processing Appointment Requests. The list below is intended to cover a number of potential possibilities based on the data items made available, and not to suggest that Service Providers needs or should perform such validations.” But should the DI-143 ‘Service Provider Proposed Appointment Response Code’ not form a valid set list (ENUM Vals) in the Data Catalogue so that all parties are working to the same list of applicable codes, rather than this field being a string with a length of 200 field? |  | Closed | [7 empty] | IF-033 has been updated as part of Interim Release 1 and the ENUM Vals will not be updated this is because we will have dynamic error messages which cannot be enumerated. |  | MPAN Ownership | Interface Catalogue | MHHS-DES138-Interface Catalogue
MHHS-DIN-202 |  |  | 2023-03-24 | ESG | 3513 | Patricia Parker | Software Provider | Operational Choreography 60 minute turnaround | Registration Responses in connection with the PUB-31 given the NFS requirement is a 60-minute turn-around time. Within the Operational Choreography there is requirements OPC-140: From our understanding this means that when suppliers receive the PUB_032 from the Reg Service rejecting the appointment Request suppliers then have 60 minutes to re-issue a fresh IF_031 appointment. For example, there is a rejection code for 'CSS Reg ID not known', this would suggest that a party is out of sync and would need investigating especially as in this case, the REG ID would have previously been provided on PUB- 002, DI-849 and CSS is the master of the REG ID and not the Registration Service. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Added suggested text to Ops Choreography. Suggested text is "It is noted that some requests may require manual work and may be as a result of incorrect appointments from the Supplier. The expectation will be 90% of requests are systemically processed within 60 minutes with the residual being processed by the end of the following working day". | Doc Ref correction | Supporting Docs | Operational Choreography | MHHS_OPC001_Operational_Choreography
MHHS-DIN-203 |  |  | 2023-03-24 | CGI | 3502 | Chris Beard | Software Provider | mapping of Estimation Reason Codes to estimation Methods | MHHSP-METH001 M-13. Can you provide a definitive mapping of Estimation Reason Codes to estimation Methods? For example, LTV to Method 11. When should an SDS use Estimation Codes such as Opt Out, Comms. Fault. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated METH001 section 7.3 to reflect Estimated Methods to Estimated reason codes | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001
MHHS-DIN-204 |  |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | De-energised sites | MHHSP-METH001 M-3. Which estimation Method should an SDS use for de-energised MPANs that would result in an estimation code of ‘De-Energised’? Without a specific Method statement to cover de-energisation, we will end up estimating consumption. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Added Method 13 to reflect de-energised sites within METH001 and updated section 2.29 on METH002. | Method statement correction | Supporting Docs | SDS Validation / Extimation | MHHSP-METH001
MHHS-DIN-205 |  |  | 2023-03-24 | CGI | 3490 | Chris Beard | Software Provider | Removal of Estimation Reason Code "Disconnected" | Can you confirm that the Estimation Reason Code ‘Disconnected’ will be removed from the table in 7.3? |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Removed "Disconnected" from Table 7.3 | Method statement correction | Supporting Docs | SDS Validation / Estimation | MHHS-METH001 - SDS Validation and Estimation Method Statement
MHHS-DIN-206 |  |  | 2023-03-27 | St Clements | 3703 | Anna Davis | Software Provider |  | Within the MHHS-E2E001 - End-to-End Solution Architecture, there is reference to MHHS-E2E003-Physical Interface Specifications in 1.3 References section This should be labelled as MHHSP-DES138-Interface Catalogue |  | Implemented | [5 empty] | Interim Release 1 |  | Updated 1.3 reference section | Doc Ref correction | All Areas | Technical Artefact | MHHS-E2E001 End-to-End Solution Architecture
MHHS-DIN-207 |  | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Clarity on when agent appointments should become effective | There is ambiguity within the design on when agent appointments should become effective, which means that different participants have a different view on when agent appointments should become active. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | At the DRG held on 4th August it was agreed that Appointments need to become active in UTC. Further workgroup discussions are being held to review impacts. References to local time removed pending agreement at Working Group/ DAG. Old solution: Appointments become active at midnight local time. Participants raised objections against the old solution therefore this DIN went to a DRG on 4th Aug for discussion. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-208 |  | Migration Design | 2023-03-30 | Migration Design |  | Matthew Breen | Central Body | Registration Service rejection of Legacy messages for an MPAN | Within the existing Migration Design, it is stated that the Registration Service should reject all Legacy messages for a given MPAN once a Forward Migration has been initiated for said MPAN. This would prevent a legacy MOP from sending the relevant legacy flows if they need to change a meter when an MPAN is mid migration. |  | Closed | [7 empty] | Closed following internal review with Design, Migration and Code Team. Agreed that current design will stand in that all legacy messages will be rejected following the point the IF-031 is issued. Reaffirm existing guidance that migration should be timed to avoid any planned work. Unplanned work/change occuring during migration should be communicated using an MHHS IF Message once migration has been completed. | Requirement correction | Migration | Migration | Migration Design Migration Requirement
MHHS-DIN-209 |  | Design Team | 2023-03-30 | Design Team |  | Sean Cooper | SRO Design Team |  | ~ Level 1/2 Error Code "MSG0000 - Success" Added to Interface Intro Section ~ MSG0018 - Timestamp cannot be future removed and explainatory note added to IF Notes Section of DIP Common |  | Implemented | [5 empty] | Interim Release 1 |  | Updated actioned in v5.1.1 of IF Doc. This relates to MSG1008 not MSG0018 as originally given in the design issue. MSG0000 Success added. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-210 |  | Design Team | 2023-03-30 | RECCo |  | Sarah Jones | Consultancy |  | Possible change flagged The original view of the Design Team was that this flag and associated info (ie Is a Customer Direct contract in place, who is the DS/MS with that contract, but not the Eff To Date aka Contract End Date) should be visible to incoming Suppliers, for exactly the reasons you suggest i.e. so that in an incoming supplier could factor the existence of a CDC(s) into their acquisition process / pricing etc. I think we also felt that SP’s who weren’t currently appointed, but may have signed a new CDC should also have the ability to set the flag, as it’s the sites that are part of a CDC, but where that SP isn’t the appointed SP that are the most difficult to coral and manage. The position at the moment is that the existence of a CDC would be shared with incoming Suppliers as part of PUB-002, however this would likely be too late in the process to provide the assistance and support required to an incoming supplier (on all aspects of the sale, contract/price in particular) … … therefore, I think it was also envisioned that information about CDC’s would be available via ECS – so prospective suppliers could check in ECS on the CDC position as part of the other pre-acquisition checks they may undertake. Therefore, I think the decision on exactly what information is shared ‘pre-acquisition’ to participants probably sits with yourselves (RECCo) to finalise as part of your ECS Design / DP Assessment. All information in relation to CDC’s will be passed/made available to ECS via receipt of a copy of PUB-039, so what item(s) are displayed and to what parties I think would get covered off as part of that ECS Design activity. |  | Closed | [7 empty] | Closed, as per discussions with RECCo that no design changes are required. | No Change
MHHS-DIN-211 |  | DI-139 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-009 Event Code is referred to as [CSSDeRegistration] in the population notes and swagger open API spec but then B042 block title references event code CSS Deactivation, B042 should reference CSSDeRegistration. |  | Implemented | [5 empty] | Interim Release 1 |  | Update B042 to reference CSSDeRegistration | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-212 |  | DI-140 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | MHHSP-BP007-Disconnection-v5.0 is missing IF-050 being sent out on a change to MPAN/RMP Status |  | Implemented | [5 empty] | Interim Release 1 |  | to BP007 and BPD007 Requires a flow from Registration Service to EES (IF-050 to DIP, a Publish Change to MPAN/RMP Status process, a PUB-050 from DIP to EES process Receive Change to MPAN/RMP status) starting at step 70 (disconnection). Plus add new step descriptions to the BPD and amend Step 70 description to include IF-050. | Process Model correction | Metering Changes |  | MHHSP-BP007-Disconnection, MHHSP-BPD007-Disconnection
MHHS-DIN-213 |  | DI-141 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Data item 997 in S1 common block is senderId in swagger hub, but senderDIPID in data catalogue |  | Implemented | [5 empty] | Interim Release 1 |  | Update swagger to reflect senderDIPID to align to data catalague | Technical corrrection | Technical Artefact | Swagger | JSON,YAML
MHHS-DIN-214 |  | DI-142 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | REG Notes section Queuing of Prospective Appointments Rule 4 ** Rule 4: If App Scenario = 'SEG' and Supplier ID + Appointment Service Start Date = Existing Supplier ID + Service Start Date > (Service Start Date +2 working days) >> Appointments meeting Rule 4 have missed their opportunity, and will be 'Lapsed' (PUB-035) This rule doesn't make logical sense, needs correcting. What is the intended logic to be applied here? |  | Implemented | [5 empty] | Interim Release 1 |  | Update to align with validation rule | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-215 |  | DI-143 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 for event code [MeterRemoval] rule REG1002 Sending Metering Service ID [SO.SenderID] is currently appointed OR held a valid appointment for Meter Installation Date [DI-057] This should read removal date not installation date |  | Implemented | [5 empty] | Interim Release 1 |  | Updated validation rule REG1002 in IF-005 for event code [MeterRemoval] to refer to Meter Removal Date (DI-058) | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-216 |  | DI-144 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-144 On IF-005 MPRS will validate Either current, queued SEG or previous MS If previous and not within 10 working days will reject with REG1003 If not previous, and not current or queued, will reject with REG1027 MPRS will then validate if install date/removal date is within MS period of ownership If not will reject with REG1019 REG1019 need correcting to also include <ETD to apply for previous MS It’s not possible to get a scenario where the If-005 passes the above rules (REG1003, REG1027 AND REG1019) but fails REG1002. Therefore REG1002 is not needed and will never be sent as a rejection code. (Add to DI-43) |  | Closed | [7 empty] | Agreed with SCS that no further change is required | No Change | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-217 |  | DI-145 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | On IF-005 REG1019 should also include validation that the installation/removal date concerned is <=Effective to date (ETD) of MS period of ownership |  | Implemented | [5 empty] | Interim Release 1 |  | Updated IF-005 validation rule REG1019 to include validation that the removal/install date must be <=Effective to date (ETD) where the update is being provided by previous Metering Service (using their 10 day window) for MeterRemoval, MeterInstall and MeterExchange events. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-218 |  | DI-146 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 for event codes [MeterExchange] and [MeterRemoval], the rule should not reference DI-056 which is the meter ID in the installation block, it should should referenced DI-053 which is the meterId in the removal block |  | Implemented | [5 empty] | Interim Release 1 |  | Rule updated not to reference DI-056 which is the meter ID in the installation block, it now references DI-053 which is the meterId in the removal block | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-219 |  | DI-147 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1005 - for other event codes removal date must be >= to Install date but for [MeterUpdate] the rule states > meter install date. Should be >= |  | Implemented | [5 empty] | Interim Release 1 |  | Update rule for [MeterUpdate] to align to other removal date event codes | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-220 |  | DI-148 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 REG1007 unecessary and will never be triggered, it is already covered under REG1001 cannot submit meter install if MPAN is disconnected |  | Closed | [7 empty] | Valid rule to left in as-is but noted cannot be SIT tested | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-221 |  | DI-149 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In the IF-005 guide it states: "When amending the Installation and/or Removal date of a Meter, a supporting MAP history commencing in line with the revised Installation Date must also be provided. Any additional MAPs should be provided in chronological order, each with a ‘MAP Effective From Date’ greater, by at least one day, than the previous." MPRS will accept if the install/removal date is changing AND the MAP History has not been included, there is no requirement in Interface Catalogue or Registration Requirements to reject if MAP history is not provided. |  | Closed | [7 empty] | Believe covered by MeterHistoryUpdate rules, but hopefully won't be an issue pending agreement on MAP discussion… IF-005 use case guide will be updated with outcome. DRG has agreed to remove MAP history therefore in lieu of this decision, this change will not be required. Closed | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-222 |  | DI-150 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | sarah |  | Implemented | [5 empty] | Interim Release 1 |  | Updated wording to match existing validation. Guidance only now provided | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-223 |  | DI-151 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005: Need REG1006 to apply to all event codes, e.g. Meter Update on a change to removal date, will need to check that the removal date does not lead to non unique Meter IDs (overlapping dates) MPRS will reject with REG1006 in this scenario |  | Implemented | [5 empty] | Interim Release 1 |  | Added REG1006 validation checks to MeterHistoryUpdate and MeterUpdate events. | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-224 |  | DI-152 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-005 Interface Note below could be read as MeterUpdate event code can be submitted by previous or prospective MS which is not correct "Only the Appointed Metering Service, and for a small window (10 days) to allow for delayed notification of field activities the previously appointed Metering Service; and an incoming Metering Service with a Prospective 'SEG' type appointment may send an IF-005 and update metering details. The [MeterHistoryUpdate] may only ever be used by the Appointed Metering Service. Interface Design assumes that two separate meters with the same 'Meter ID' cannot be installed at the same time. " |  | Implemented | [5 empty] | Interim Release 1 |  | Updated | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-225 |  | DI-153 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | DI-849 CSS Registration Request Id does not have a YAML name in the interface catalogue In the swagger hub, the corresponding name is CSSSwitchID which is misspelt |  | Implemented | [5 empty] | Interim Release 1 |  | Updated Data Catalogue to CSSRegistrationRequestID, Swagger to follow | Data interface correction |  | Interface Catalogue Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-226 |  | DI-154 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | In MHHSP-BPD007 - Disconnection v5.0, the ordering of the steps are out of order. Steps 140, 145 and 150 are for parties receiving the de-appointment notification from the Registration Service, but this is not sent until Step 155. Step 155 “De-Appoint Services” needs to be before Step 140 “DS De-appointment Notification”. Also Step 145 “Receive De-Appointment Notification” is DIP receiving the de-appointment notification to send on, this needs to be after Step 155 and before Step 140 . The ordering should be: • De-appoint services (155) • Receive De-Appointment Notification (145) • DS De-Appointment Notification (140) • MS De-Appointment Notification (150) |  | Closed | [7 empty] | No plans to change step numbers as long as they are unique | No Change |  |  | BPD007
MHHS-DIN-227 |  | DI-155 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1.xlsb, the validation for REG1003 – “Metering Service ID [S0.SenderID] post appointment update period for MPAN [DI-063] has expired” is currently set to “Metering Service [S0.SenderID] holds valid previous appointment then [System Date] should be < [REG.App End Date] + 10 working days”. Should this be <= to allow for the full 10 days? |  | Implemented | [5 empty] | Interim Release 1 |  | Changed to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-228 |  | DI-156 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 - IF-005 has the following error for [MeterExchange] & [MeterInstall]:- “REG1020 - MAP Effective Date [DI-054] cannot take place in the future” Should this validation also be valid for [MeterUpdate] and [MeterHistoryUpdate]? |  | Implemented | [5 empty] | Interim Release 1 |  | Added to meter update for removal date. Added to MeterUpdate and MeterHistoryUpdate for MAP effective date | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-229 |  | DI-157 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 does not have a rule that the SMSO EFD must not be prior to the latest SMSO EFD. We are implementing this rule with error code REG1019 |  | Implemented | [5 empty] | Interim Release 1 |  | We are implementing this rule with error code REG1019 Make consistent with others ( PC and ssc + 1 ). Review IHD and SMSO | Data Interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-230 |  | DI-158 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-025 & IF-005 do not have a rejection code where the IHD is invalid. |  | Closed | [7 empty] | DIP will reject non-valid values - no change to docs required | No Change
MHHS-DIN-231 |  | DI-159 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-005 - There is no validation on Meter Removal date [DI-58]. This should be mandatory non nullable for [MeterRemoval],[MeterExchange],[MeterUpdate], but mandatory nullable for [MeterHistoryUpdate] to allow for reinstating a previously removed meter. Currently in redlined v5.1, this data item is optional and non nullable. |  | Implemented | [5 empty] | Interim Release 1 |  | Meter Removal changed to nullable, block conditionality updated | Missing/incorrect validation rule | Metering Changes | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-232 |  | DI-160 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | We’ve raised DI-160 on the interface catalogue DCC Service Flag validation rules are specified in IF-025, but DCC Service Flag is not received in this interface. Needs removing. |  | Implemented | [5 empty] | Interim Release 1 |  | not needed rules removed. | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-233 |  | DI-161 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1 – IF-025, where the event type is [ConsentGranularity] Error Code - REG1019 - Consent EffectiveFrom Date [DI-018] must be within Suppliers period of ownership Test Condition - Consent Granularity EffectiveFromDate [DI-018} must be < [Reg.CurrentSupplierEndDate] if exists Should this be <= as it could be on the end date? |  | Implemented | [5 empty] | Interim Release 1 |  | Updated to <= | Missing/incorrect validation rule | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-234 |  | DI-162 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Registration Services Requirement MHHS-BR-RS-021 should be amended to: Registration Service must, where more than one Metering Service appointment request is received from the same Supplier for the same MPAN CSS Registration Request ID, and for the same date, take the last received Metering Service appointment (based on the Sender timestamp) as containing the correct information. Any earlier appointments should be lapsed. To allow multiple queued service appointments for the same registration will be overly complex to design, code and test, and is likely to cause confusion and issues in live operation. It is much simpler and cleaner to only allow one queued service appointment at a time, per registration. This would still allow the Supplier to replace a queued appointment that's incorrect. The Supplier could submit further changes once the first change has completed, if there is a genuine case of multiple changes to SP in a short period of time. It would not impact on CoS. Our proposal is to allow one pending queued appointment per registration, so could have a queued appoint on current registration AND queued appointment on CoS registration at the same time. |  | Implemented | [5 empty] | Interim Release 1 |  | Updated MHHS-BR-RS-021 to refer to CSS Registration Request ID. Added REG1089 - Subsequent appointment received as an error code in the interface spec | Requirement correction | MPAN Ownership |  | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-235 |  | DI-63 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Original wording:- In the business process diagram for Disconnections MHHSP-BP007- Disconnection-v4.5 the C0300 has been changed to C0700 which is incorrect, a C0700 message does not exist. It should be C0300 Update required:- Please close this design issue as CSS0700 is the correct reference for update of status. |  | Closed | [7 empty] | DUPLICATE OF MHHS-DIN-63 | No Change
MHHS-DIN-236 |  | DI-163 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, 02-DIP-COMMON - R0 response - DI-980 Response Message has been updated in Swaggerhub to be an array, but this is not clarified in Interface Spec. DI-979 Response Code should not be an array. |  | Implemented | [5 empty] | Interim Release 1 |  | Added note in Introduction section to confirm that DI-980 can be an array Agreed DI-979 Response Code is not an array | Data interface correction |  | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-237 |  | DI-164 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Within MHHSP-DES138-Interface Catalogue v5.1, IF-034 S0 DI-999 Event Code option of [DSAppSPRepsonse] is misspelt. This is also misspelt in Swaggerhub. This could cause differences between systems and should be corrected to [DSAppSPResponse] |  | Implemented | [5 empty] | Interim Release 1 |  | Updated typo in IF-034 DI-999. | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-238 |  | DI-165 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | IF-031 is missing validation on MS/DS EFD being within permitted advanced period. This is covered under migration document but not implemented as a validation rule for IF-031. MHHS-DEL961 Migration Design Document section 6.1.1: For the purposes of the CoA Migration process, the below business rules should be followed by Suppliers regarding the lead time between the submission date of the IF-031 and the requested effective from date of the Migration. a. An effective from date from Same Day +1 up to a maximum of 28 calendar days (inclusive of the 28th day) in the future is permissible. |  | Implemented | [5 empty] | Interim Release 1 |  | 28 Day in advance rule added to if-031 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-239 |  | DI-166 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Requirement MHHS-BR-RS-134 states MPRS must automatically de-appoint the MS & DS when the Market Segment Indicator changes to NO. Is this the intended design? |  | Implemented | [5 empty] | Interim Release 1 |  | Removed reference to Market Segment Indicator from the requirement MHHS-BR-RS-134. | Requirement correction | MPAN Ownership | Market Segment | MHHSP-BRS003-Registration Service requirements
MHHS-DIN-240 |  | DI-167 | 2023-02-01 | St Clements |  | Madison Layton | Software Provider |  | Current validation on IF-031 Rule REG1037 will mean MPRS will lapse any appointment where the system date is greater than appointment EFD + 2 working days. This means if a SEG change fails, and the supplier tries to resubmit the SEG change, with EFD more than 2 working days in the past, MPRS will immediately lapse the appointment. If there is a need to allow retrospective SEG changes, more than 2 working days after EFD, then the wording will need to be amended to apply to max(EFD+2 working days, MPRS system date on receipt of IF-034 + 2 working days) |  | Implemented | [5 empty] | Interim Release 1 |  | Introduction of Lapsed Response Codes and Rules in IF-035 | Data interface correction | MPAN Ownership | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-241 | RS |  | 2023-02-01 | C&C | 3430 | Graham King | Software Provider | Routing rules via the PUB-018 | IF/PUB-018 message with event codes [AddressChg] and [DUOSTariffIDChg]. According to Interface Catalogue routing rules, these events are not communicated to the LDSO role via the PUB-018. We assume that the assumption here is that because these data items are mastered by the LDSO that all internal LDSO systems share this data. This is unlikely to be the case. DUoS billing systems co-exist alongside other LDSO management software and are often supplied by different vendors. They do not and cannot share data sets. Given this real-world separation, would it be possible to make the PUB-018 message available to LDSO in the list of Secondary Routing paths? The alternative would mean developing communication channels between disparate systems, from potentially different software vendors in order to pass information from one to the other. |  | Closed | [7 empty] | Closed - Linked to expected LDSO CR26 on DIP Message Optionality - Update as part of wider CR review | No Change
MHHS-DIN-242 |  |  | 2023-04-04 | ESG | 3713 | Patricia Parker | Software Provider |  | How will the Metering Service be kept informed of who the currently appointed Data Service are? On BP003 is shows the Metering Service being a recipient of the PUB_036 when a DS appointment becomes effective, however looking at the routing rules in DES138 it does not show ‘MSSC’ or ‘MSAC’ as being recipients? |  | Closed | [7 empty] | Close - changes to Secondary routing make this DIN Moot - Ref DIN-268 | No Change |  |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-243 |  |  | 2023-04-05 | Change Request | N/A | Sean Cooper | Programme | CR-015 E7/E10 Off Peak Consumption Solution | CR015 - Differential Settlement for E7 / E10 Meters for Smart Opt-out customers | CR015 | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Changes as agreed at DRG and slides circulated. Updated Method 2 and Method 7 within the SDS method statement (METH001). BR-DS-168 & BR-DS-169 added to BRS001. BR-SU-163, BR-SU-164 & BR-SU165 added to BRS004. BP004 text box amended. Creation of x2 New Data Catalogue Items​ OPD Day​ & OPD Proportion​. Changes to IF-024​ Addition of new Event Code [SN-OffPeakDec]​ & Addition of new B-Block BXXX Off-Peak Declaration​ | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue METH001 BRS001 BRS004 BP004
MHHS-DIN-244 |  |  | 2023-04-04 | British Gas | 3874 | Neil Strange | Supplier |  | D0275: Until v0.3 of DES196 was released our understanding was that the D0275 would be retained and it’ use was optional. We are feeding this back on the D-025 consultation but don’t want to lose sight of this. Its removal will impact our billing systems and substantially drive up implementation costs. The baselined IF-021 also does not handle the clock change |  | Closed | [7 empty] | Alignment with D0275 D0275 is not part of of the baseline design requirements. If you require this, it is by mutual agreement between parties. NO change required, only clarification. | No Change
MHHS-DIN-245 |  |  | 2023-04-01 | Avanade/ Design Team |  | Grant Sutcliffe | Software Provider | Transaction ID and Correlation ID increase field length to 60 | Transaction Id Could the length specification of the TransactionId be increased to be a max length of 60. The need for this is to cater for a 16 character length hex value (increasing from current length of 6 characters]. This would ensure that we achieve uniqueness. It will also provide headroom for any length increase in other Transaction Id constituents, such as Role. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: T-041-1234567890123-SUP-20230220-619C1F6967838002 [Length = 50] Example from DES138 spreadsheet: T-006-1234567890123-SUP-20220401-1234CC [Length = 40] Correlation Id Could CorrelationId length also be increased to 60 max length of 60 - for the same reason. Length specified in MHHSP-DES138-Interface Catalogue v5.0.xlsb: String50 Example we generate: CI-BP-011-20230222-619E0BD1D1FD9000 [Length = 35] Example from DES138 spreadsheet: CI-BP-011-20230222-1234567890123 [Length = 32] |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated DIP Transaction ID and DIP Correlation ID to String 60 in Interim Release 1. The examples have been updated to reflected MHHSP-DES138-Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-246 |  |  | 2023-04-12 | Change Request |  |  | DCUSA | CR-019 Replacement of D0242 D0315 for MHHS | CR019 - Replacement of D0242 D0315 for MHHS | CR019 | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors) and receivers (suppliers) of the flows has identified the desired flow content and now wish to bring this back to the program to ensure that it can be delivered in readiness for migration. REP-900 and REP-901 added to reporting catalogue. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the supercustomer data from settlement (REP-002/002A). There will be removal of certain data items used in the current process and addition of new data items, making population of the D0242 ‘Supercustomer DUoS Daily Statement’/D0315 ‘Embedded Network Supercustomer DUoS Daily Statement’ impossible in their current format for migrated customers. The “MHHS Design: Reporting and Transition Sub Group” identified the need for a new DIP flow to replace the D0242/D0315 last summer but noted that these flows are under DCUSA ownership and so passed the development of the flow content to DCUSA. More information including the proposed Interface can be found on the collaboration base under CR019 This also addresses CR27/DIN511 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-ERI011B External Reports
MHHS-DIN-247 |  | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Update to the Core Design Interface Catalogue (MHHSP-DES138) is required to include the addition of IF-003 |  | Closed | [7 empty] | Closed captured under DIN-434 as part of migration update review IF-003 defined as part of Migration baseline The structure of the IF-003 will be updated to include ‘Incoming Supplier Details.’ The two new data items within the ‘Incoming Supplier Details’ will be: RevMig Incoming Supplier MPID RevMig Incoming Supplier Effective From Date Business Rules: In the case of Smart Meters undergoing Reverse Migration only, the Registration Service will populate the ‘Incoming Supplier Details’ as part of the IF-003 which is sent to the outgoing MS (via the DIP). This is so the outgoing MS can correctly route the Skeleton D0150 to the new Supplier (which in turn enables the new Supplier to generate a D0367). If the D0205 is not sent to the Registration Service before the IF-003 is issued, the data fields used to confirm the identity of the DC and MOP will be blank; no default values will be populated. In this case, the DC and MOP will need to contact the Supplier to initiate a manual transfer of data. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-248 |  | Migration Design | 2023-04-05 | Migration Design |  | Matthew Breen | Programme |  | Updates to the ISD Entities document (EDI021, v5.0) |  | Closed | [7 empty] | To be picked up as part of Migration IA - - new DIN will be raised as required. |  |  |  | EDI021
MHHS-DIN-249 |  | Migration Design | 2023-03-27 | Migration Design |  | Matthew Breen | Programme |  | Discussion around the use of BST/UTC during Migration |  | Closed | [7 empty] | DIN is not specific enough.
MHHS-DIN-250 |  |  | 2023-04-06 | Design Team | 3764 | Steve Weston | Programme | Participant ID 10 digit number | This is related to ticket 3764, to update the Interface Specification to ensure the Participant ID is clearly defined as a 10 digit number [0-9] only, and the examples in the Interface Specification align to this, including where this is used as part of the sender unique reference and the examples shows 11 digits, not 10 digits for Participant ID. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | In E2E001 doc Section 4.2.3.2 Section 4.4.4.2 example code for Sender unique Ref and in Transaction ID Section 4.5.5.3 as above DES138 doc Data Catalogue tab: DI-990 example and DI995 Example DIP common tabl DI995 example and the example JSON block (the above easy to change) ALL the IF tabs the JSON block example the Sender Unique Ref contains Participant ID and in every example its longer than 10. JSON/YAML Files: Update JSON examples where Sender Unique Ref and Transaction ID contain a Participant ID example longer than 10. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 Solution Architecture MHHSP-DES138-Interface Catalogue JSON/YAML files
MHHS-DIN-251 |  |  | 2023-04-06 | Design Team | 3860 | Steve Weston | Programme | IF-041 Population | This is related to ticket 3860, to update the Interface Specification to provide more clarity / notes on the optionality of B064 and B065 blocks in the IF-041 interface. This is in relation to notes / detail about which blocks are mandatory (from a contractual perspective) versus what should be included in the message if the data exists. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updates the notes section of IF-041 in order to provide guidance on the minimum population of B064/B065 blocks. This clarifies "When exchanging readings between parties the design assumes that in the most part this will be the Cumulative Register Reading (Block B064). However, at participants request this message also allows for the exchange of Configurable Register Readings (B065) either alongside a Cumulative Reading or in isolation. For the avoidance of doubt the message must contain at least one B064 record and /or one (or more) B065 records [depending on the number of configurable registers], in order to be considered valid. " | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-252 |  |  | 2023-04-06 | Centrica | 3661 | Neil Strange |  |  | We believe there is a Design Gap at Change of Agent and Change of Supplier for Smart Meters which also impacts Migration. Neither the Registration Service, Metering Service nor Data Service will know how the registers are set up and specifically which are active. Consequently the Data Service will not know which registers to send on the IF-041, nor will there be able to calculate consumption correctly without knowing the register set up. The interface catalogue for IF-041 states in respect to this “B065 Block Below Repeated for each set of Configured Register(s) for each Meter” – we do not believe there is a way to give the DS this information. The supplier will set up the smart meter configuration to enable the registers to capture the usage for certain time periods. There is currently no way for the supplier to inform the DS which registers are active at what time of the day - the DS cannot accurately calculate the consumption breakdown based on the reads when there are multiple registers configured. |  | Closed | [7 empty] | DIN closed, Design Team to send email recommending for a CR to be raised.
MHHS-DIN-253 |  |  | 2023-04-12 | British Gas | 3769 | David Hipwell | Large Supplier | Volumetrics | The latest E2E Functional and Non-Functional Requirements MHHS-E2E Requirements V3 which went to V3 on 16/02/2023 appears to focus on message counts and response times. For example:- During transition all meter points (ca. 31M) will be transition between the old and new services. Therefore assuming a linear migration over the year this would result in the load below, hence services shall be capable of processing the following volumes: - average daily volume of 680,000 - peak daily volume of 2.4M 5.0M - annual volume of 248M 500M Analysis of the flows needs to be categorised across all impacted market participant roles including the DIP. Only then will it have meaning for all parties. The calculation needs to take account of the migration period using the MHHS migration volumes according to date (including REVERSE migration). These should be in both message counts and also sizing (e.g. Gb). And include for a BAU day and also migration days. Whilst some calculations can use the total number of MPANs, to be useful these need show also at perhaps for a million MPANs in each role. Only then will all parties be working on a single set of figures. A line in the sand. The NFRs that exist appear to have moved away from any form of technical calculation towards business process figures. But these figures need to go as an input into technical sizing’s, and should have done for DIP – can these be produced and published ? |  | Updates Ready to Release | No |  | Clarification - No change required | DIP Users | 2023-09-13 | Post Go-live Release | 0 | Volumetrics analysis was presented to DRG on 13th September with some minor comments (see DRG meeting minutes). Updated volumetrics document will be issued as part of IR5. The document has been updated to include the following information to support these requests: - Overview of assumptions that form the basis of the volumetrics document. For the purposes of this volumetrics document, this includes things like number of meters, consumptions per day, settlement days per message, MPAN per message, breakdown of smart vs traditional, breakdown of SMETS1 vs 2, those providing Import / Export / Both etc. - There is breakdown of smart meter & traditional meter split that inform actual / estimated reading, alongside patterns for message structure. The 2 patterns explored provide a range used in the scenarios – these are consolidated and individual IF-021 messages. - Additional scenarios that include an average (best-case) distribution of IF-021 messages across a 24 period, as well as scenarios that cover a peak of peak (worst-case) distribution of messages across a 24-hour period. These scenarios align with all NFRs. - The scenarios provide upper and lower message bounds across the day, as well as provide message throughput per hour / second. - Additional scenarios split into 2 sections – with a breakdown for the DIP plus a breakdown for an MP with a portfolio size of 1 million. - Graphs added to show / illustrate distribution of the messages for the scenarios for all traffic into the DIP. Without firm guidance on how each Data Service are likely to submit IF-021 messages four different scenarios are used to help inform average / peak processing volumes as follows, which are detailed in the volumetrics document as follows: - Scenario 1 - Market Participant IF-021 messages equally distributed across a 24-hour period - Scenario 2 - Market Participant IF-021 messages equally distributed across a 6-hour period - Scenario 3 - Market Participant IF-021 messages unequally distributed across a 6-hour period - Scenario 4 - Market Participant IF-021 messages distributed unequally across a 24-hour period using a Monte Carlo simulation model Scenarios 2 & 3 describe extreme patterns of data submission that are very unlikely to occur in reality; they present a worst-case scenario where the patterns of submissions follow the End-to-End requirements to the extreme and Data Services submit data almost simultaneously. Scenario 4 presents a statistical approach where the volume of IF-021 is randomly distributed according to a Monte Carlo simulation. Alternate scenarios, that are not considered BAU, are also presented and included in the Volumetrics document: - Submission after an unplanned Outage for 72 hours as per NFR. - Market Transition / Migration. - Change in Meter Population from 50% to 90% over time. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E004 E2E Architecture - Transaction Volumes
MHHS-DIN-254 |  |  | 2023-04-17 | Siemens | 3044 | Tony Mason | Metering Service | Update of Consent, DPI, etc. | this does surprise me and doesn’t seem to correspond to the routing rules in the Interface Specification. A proposed Data Service is not included in the routing tables for the receipt of a PUB-018, for example. I would therefore expect that if a change to DPI occurs between PUB-033 and PUB-036 the proposed Data Service could only be notified on a revised PUB-033 with the Appointment Scenario set to whatever the original scenario was set to – “SEG”, “CSP”, or “COS”. |  | Closed | [7 empty] | Ref notes on the maintenance of these data items in the Regi Info Section of the I/F document. Prospective SPs are not notified of changes to these data items during their prospective period. If these Data items change then the supplier should re-evaluate the SP they have proposed and change the appointments as required. If an SP takes on a supply with different elements/factors to those suggested by the supplier at appointment this is a contractual issue between the SP and the Supplier.
MHHS-DIN-255 |  |  | 2023-04-17 | Elexon | 3983 | Kate Goodman | Testing | Consumption on De-Energised MPAN (IF-013/IF-014) | ConsumptionOnDeEnergised is an Event Code mentioned in the list of data items but is not present in header where the routing info is held - needs to be added to header |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | ConsumptiononDeEnergised event moved from IF-013 to IF-014 and added in routing rules. See also DIN332 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-256 |  |  | 2023-04-17 | Elexon | 4169 | Kate Goodman | Testing | IF-014 Block B067 | DI-015 is mentioned in the header wrt routing but is not present in the message itself. It either needs to be removed from header or added into message. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Block B067 added to IF-014 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-257 |  |  | 2023-04-17 | Elexon | 4172 | Kate Goodman | Testing | B053 repeating block | B051 is a block which repeats for each combination of Load Shape Criteria (denoted with single chevron to show repeat). B053 is another repeating block which is denoted by two chevrons, implying it is nested below B051. But in fact it also repeats for each combination of Load Shape Criteria. Should this just have a single chevron or is there further information that needs to be added to make its double chevron make sense? |  | Closed | [7 empty] | No change required as there will be multiple B053 in each B051 block. | No Change |  |  | none
MHHS-DIN-258 |  |  | 2023-04-19 | ENWL |  | Paul Band | Network Operator | LDSO use of DIP vs internal for Specific messages | There are a number of requirements in the MHHS-BRS005-LDSO document which state that we must obtain various registration data via the DIP and maintain records accordingly such as: MHHS-BR-LD-001-005, MHHS-BR-LD-024, MHHS-BR-LD-030 and MHHS-BR-LD-034 Extrapolating these into requirements for our own systems suggests that we should build databases/tables to store this data and maintain it The requirement is placed upon us as a party under the assertion that all settlement related data should be exchanged between services and parties via the DIP. However LDSO’s are unique in that their data exchange for their party type is split and is typically split by system under these party types. As a consequence we already communicate directly with MPRS as it is already part of our system architecture as a paid for and created service by LDSO’s. |  | Closed | [7 empty] | CR26 has been raised to covere this LDSOs have been advised to raise a Programme Change Request. Discussion at the DRG of the 27/4/23 did not agree on the development of a New Design Principle, A further workshop with LDSOs needs to take place to discuss alternate options and confirm agreement amoungst all DNOs & IDNO on the receipt of publication
MHHS-DIN-259 |  |  | 2023-04-20 | ESG | 3756 | Patricia Parker | Software Provider | BP003C correction | On BP003C under the CoR section there is a note which states that the readings that pass validation should have Meter Reading Status (J0047) set to ‘T’ and when it has failed set it to ‘F’. However as per the REC the group which houses the J0047 group (032 – screenshot below) should only be present where the Meter Reading Flag (J0045) is set to ‘F’. I have checked DES196 and cannot see that the conditionality for that group is changing in the D0010 therefore I can only assume that the note on the process map is incorrect, and it should be talking about the J0045 value instead. Please can you confirm? |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Modification to Note on process to refer to "Meter Reading Flag (J0045)", modify flow label to step230 to "(Read Flag = "T")" Modification to the process note to advise the J0047 would not be present if the meter reading flag (J0045) is set to "T". It will only be present in case the J0045 is set to "F". | Process Model correction | Metering Changes |  | MHHSP-BP003C-Transfer of Reads
MHHS-DIN-260 |  |  | 2023-04-20 | CGI | 4167 | Dave Webster | Software Provider |  | Swagger definition does not match DES-138 in version 1.0 or 1.1. |  | Closed | [7 empty] | No specific detail provided, however comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1, therefore closed
MHHS-DIN-261 |  |  | 2023-04-20 | Utiliteam | 4245 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. Configurable Register Reading Date/Time is missing. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue JSON/YAML Files
MHHS-DIN-262 |  |  | 2023-04-20 | Utiliteam | 4214 | Richard Palmer | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. B070 for IF-031 is wrong. It contains the word DIP in the Swagger, which is not included in DES-138. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Comparison exercise undertaken in swagger 1.2 vs Data Catalogue 5.2.1 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files
MHHS-DIN-263 |  |  | 2023-04-21 | CGI | 4203 | Dave Webster | Software Provider | Swagger Alignment to DES-138 | Swagger definition does not match DES-138 in version 1.0 or 1.1. DI-122-Profile-Class is defined as an integer, but in DES138 it is defined as a string length 2. Needs to be updated in the Swagger. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Swagger and Data Catalogue aligned to String 2 for DI-122 | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files
MHHS-DIN-264 |  |  | 2023-04-24 | Elexon | 3946 | Rashmi Radhakrishnan | Central Body | Update to CCC Method Statement | One of my colleague pointed out a typo in the CCC method statement attached, and I would like to draw your attention to it and requesting to make necessary amendments. The CCCID starting from 100 to 107 has Market Segment Indicator as “U” and Connection Type Indicator shown as “W”. We think that, for these line items the Connection Type Indictor need be corrected to “U”. For reference please see below picture and this also aligns with ISD entity spec v5.0 (M2 entity). CCC ID Market Segment Indicator Measurement Quantity Consumption Component Indicator Connection Type Indicator 100 U AI C W 101 U AI L W 102 U AE C W 103 U AE L W 104 U AI C W 105 U AI L W 106 U AE C W 107 U AE L W All 'W's' should be 'U's') |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Method Statements (MDS & VAS) will be updated for "W" to be replaced by "U"within ISD Table - MHHS Consumption Component Class. Please note: ISD entity M5 file has already been updated to reflect the fact that unmetered supplies have a connection type of "U". | Design Ambiguous | Supporting Docs | Method Statement | MDS Method Statement VAS Method Statement
MHHS-DIN-265 |  |  | 2023-04-25 | Elexon | 4128 | Rashmi Radhakrishnan | Central Body | Validity of Settlement Period quality indicator data set | ISD entity M5 has a filed Settlement Period quality indicator. Is this the complete valid data set for the field Settlement Period quality indicator? I took this below list from interface catalogue v5.0. A = Actual, E= Estimate (UMS Only) A1,A2,A3, AAE1,AAE2,AAE3,EAE1,EAE2,EAE3 (ADV Only) E0 --> E9 = Estimation Method 1 - 9 ZE = De-Energised ZE1--> ZE3 = Zero Estimation Method 1 -3 but the Advanced Data Service Estimation Method Statement has data flags EA1 till EA13 which is not mentioned in the above list. Also, the ISD entity spec M5 example below shows a different data item that is not in the list at all for Unmetered(104 &105). Is this a mistake? |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Interface document updated with the full list of settlement period quality indicators for ADS and swagger updated accordingly. within DES138. 02-IF-016/14 and in the data cat. DI-083 "EA1-->EA13 = ADS Estimation Methods" added. | Design Ambiguous | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-266 |  |  | 2023-04-26 | ESG | 3899/ 925 | Patricia Parker | Software Provider |  | If the D0300 process is not changing then we believe that DES196 is incorrect and should show added routes to allow the Supplier to send a D0300 to the Data Service Matt M has confirmed - We are working through the exchange of CoS readings as the code drafting has raised some questions about the extent to which the SDS is involved in the D0300 process. For smart meters, the SDS will not have any use for the billing register readings so D0300 process should not apply, or at most could only be missing the total cumulative. However, it likely will still be required for traditional meters. On that basis, I think we can acknowledge that the D0300 will be retained and SVs created for Supplier to SDS for traditional meters. The process for smart meters is being discussed internally as the SDS does not retrieve tariff register readings. There will be an updated version of DES196 issued in the next few weeks to reflect feedback from the DTN flow part 2 consultation issued in late March which will reflect the retention of the D0300. |  | Closed | [7 empty] | Email comms sent to Patricia confirming the D0300 is a Supplier to Supplier flow. Therefore should there be a need to send readings to the DS, this would be done via a D0010/IF-041 with the correct data flags set in both. Based on this there is no requirement to send D0300 to the DS. Matt M confirmed when finalising DES196 he confirmed this in his comment response to ESG. The MSAG Consequential Change - Switch Meter Read Exceptions v1.0 22.06.23 provides a more comprehensive explanation of the MSAG conclusions. No change required to DES196 | Design Ambiguous | Supporting Docs | Method Statement | MHHSP-DES196- D-Flow and Interface Mapping
MHHS-DIN-267 |  |  | 2023-05-02 | ESG | 4385 | Patricia Parker | Software Provider | RegX Validation Issue | RegExpression on the DI-148-Annual-Consumption use of DT-016-Decimal-9-3 in the 1.1 swagger spec. This needs to be updated to align with DES-138 example of 123456789.123. Regex should be ^-?[0-9]\d{8}(\.\d{3})?$ instead of ^-?[0-9]\d{7}(\.\d{3})?$ |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Swagger v1.2 has been updated accordingly | Technical corrrection | Supporting Docs | Interface Catalogue/Swagger | JSON/YAMl Files
MHHS-DIN-268 |  |  | 2023-05-03 | SRO Design |  | Sean Cooper | SI Design | Secondary Routing | It was always the intention to revisit and revise all of the Secondary Routing configuration as part of DIP Detailed Design. Completion of this exercise has also resulted in some changes to other routing parameters. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Following discussion with Avanade the Secondary routing short codes have been simplified and the routing of each IF revisited based on these revised short codes. These are shown highlighted in BLUE in the routing section of each of the individual IF pages. | Data interface correction | Supporting Docs |  | MHHSP-DES138-Interface Catalogue
MHHS-DIN-269 |  |  | 2023-05-03 | St Clements | 4424 | Anna Davis | Software Provider | Swagger Alignment to DES-138 | We have also realised that there are a large number of discrepancies for each interface between the data item name in Swagger vs the YAML name in the Interface Catalogue Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated inconsistencies in the Interface 01-Data Catalogue and Swagger. Examples are:- Spelling mistakes - Nominated vs Nominared / Prosposed vs Proposed / PremisesIndicator vs PremiseIndicator Capitalisation – Id vs ID Abbreviations – eg Eff or Effective / MS or Metering System / trad vs traditional Inconsistent labelling – eg Proposed vs Prospective / Consent vs Consent Granularity | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-270 |  |  | 2023-05-05 | SRO Design | 4557 | Rob Golding | SI Design | Correlation ID | Provide further clarity on how Correlation ID's work. This will impact numerous artefacts including DES-138 and E2E001 |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | DES-138 Interfaces updated to reflect correct 'COPY' property on IF routing tables. updated IF-008, 16, 20, 26, 28, 37, 39 and 50 for this DIN. Added *New to IF-020 showing a new correlation ID is needed to be created for these events, others events needed a COPY of the correlation ID. IF-050 had “No” added to show that a Correlation ID is not required. Updated the E2E001 design document with a more detailed worked example in section 5.4 that details how and where the Correlation ID is populated. | Design Ambiguous | Supporting Docs |  | MHHSP-DES138-Interface Catalogue. E2E001.
MHHS-DIN-271 |  |  | 2023-05-10 | ESG | 4541 | Patricia Parker | Software Provider | Swagger Alignment to DES-138 | S0 and S1 is Mandatory in DES-138 v5.1.1, but is not marked as mandatory in the Swagger 1.1. Swagger needs to be updated to align with DES-138. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Swagger 1.2 updated so all SO and S1 blocks are mandatory as per DES-138 | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-272 |  |  | 2023-05-10 | SRO Design | 4656 | Rob Golding | SI Design |  | Required to DIP Channel Publication (v1.2 of the swagger) that will allow DCPs to register webhooks on behalf of their clients |  | Closed | [7 empty] | Duplicate of DIN-375
MHHS-DIN-273 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | New MSN Data Type | MHHS Data Type (DT-029) - for Meter ID / Serial number for DI-053, DI-056 and DI-060 added to DES138 01-Data Catalogue, Swagger updated. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | New Data Type created in Swagger v1.2 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-274 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | Missing YAML in DES-138 - DI-073, DI-074, DI-080, DI-111, DI-112, DI-190-194, DI-300, DI-021, DI-022, DI-060, DI-076 |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Missing YAML names for Data Items confirmed and added to 01 - Data Catalogue Note:All DI's upsated except DI-076 has not required a changed. Other DI chnages not listed are picked up as part of DIN261 | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-275 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Swagger Alignment to DES-138 | DI-093 / DI-120 - Data length 2,000 not 200. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | All additional info data items set to len 2000 in Swagger v1.2, DES138 DI-093/120 length updated in 01-Data Catalogue | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-276 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Classifications | MHHS Data Classification - ensure all columns are populated for Public and Restricted ie, MPAN & Address (removall all NULLS). |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Data Classifications added in v5.2.1 where previously there was no entry ( Column I in the Data Catalogue ) | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-277 |  |  | 2023-05-10 | RECCo | 4199 | Sarah Jones | Consultancy | Data Owners in Data Catalouge | MHHS Data Owner - where there are NULL's, this should be updated so all columns provide an owner, mark as N/A (remove all NULLS). |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Metering Service added as Authoritative Source and MHHS Owner in v5.2.1 of DES138 Data Catalogue for DI-190 to DI-195. Previously there was no entry. | Data interface correction | Supporting Docs | Interface Catalogue/Swagger | MHHSP-DES138-Interface Catalogue
MHHS-DIN-278 |  |  | 2023-05-10 | Design Team | 4590 | Rob Golding | Programme Design | Addition of indicator for each IF within DES138 | Please can DES138 Interfaces spreadsheet be updated to provide an indicator against each interface (or is it interface & event code) as to whether it can be opted in/out by a recipient. | CR029 | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Design Team to add optionality matrix to DES138. Name of worksheet: 04_IF_Optout_Matrix | Design Ambiguous | Supporting Docs |  | DES138 Data interface specification
MHHS-DIN-279 |  |  | 2023-05-12 | ESG | 4484 | Patricia Parker | Software Provider | Event Code clarifiction for DS when sending back validated customer read on PUB-041 | The BP005 – Data Processing – Process map shows that when a Customer Own Read has been sent to the Data Service from the Supplier in the IF-041, EventCode = ReadingCoR, the Data Service will perform reading validation and issue the PUB-041 back to the Supplier, in the Read Sharing column of the process map. When the Data Service send back the validated customer own read in the PUB-041, what eventcode will they use and where can I find this documented? The previous response says “There is no IF-041 response, check consumption is as expected in PUB-021” is this correct for Customer Own Reads on Smart meters? The map shows otherwise so please can you confirm if the answer or map is correct and if the map is correct, provide information on what event code will be used. |  | Closed | [7 empty] | This is a query not a DIN. Previous response provided is correct .... There is no IF-041 response, check consumption is as expected in PUB-021”
MHHS-DIN-280 |  |  | 2023-05-12 | ESG | 4552 | Patricia Parker | Software Provider |  | DES196 lists the D0386 (Manage Metering Points) as ‘not impacted’ owned by the REC however BP010 shows that the method of maintaining Related MPANs is via the IF_019 / PUB_020 process. Can you confirm whether the D0386 is going to be removed post- MHHS. If not, could you please clarify what process a Supplier should follow post- MHHS. |  | Closed | [7 empty] | D0386 will not be used post migration to MHHS Regime. Management of MPAN relationships will be under taken using IF-019/IF-020
MHHS-DIN-281 |  | DI-172 | 2023-05-12 | St Clements | 4446 | Madison Layton | Software Provider | BP003 IF-35 flow | MHHS-BR-RS-053 for the incumbent MS to be notified on If-035 DSAppAccepted where meter is advanced or traditional is missing from BP003 business process diagram and steps. Also updates to BP003 and BPD003 forward migration for consistency |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | IF-35 flow from step 85 (if accepted where meter is advanced or traditional to Meter Service (incumbent) and additional step 86 to receive appointment response to BP003, and added step 86 and BR-RS-053 ref and details to step 85 to the BPD003 | Process Model correction | Metering Changes |  | MHHSP-BP003-Change of Service - Data Service, BPD003 Forward Migration BP003 and BPD
MHHS-DIN-282 |  |  | 2023-05-16 | SIMS | 4821 | Martin Freeman | Software Provider | Status code removal | Status Code is included in the E2E001 design response body (4.4.4.2), when this is HTTP Response code and should be removed as this is defined in the callback response. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Removed from section 4.4.4.2 from the E2E001 design document as this is not required. This now aligns in Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-283 |  |  | 2023-05-16 | SIMS | 4826 | Martin Freeman | Software Provider | ID Capitalisation | ID should be capitalised in all places in the Swagger. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | All JSON names now have capitalised ID fields for Swagger 1.2. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-284 |  |  | 2023-05-16 | SIMS | 4828 | Martin Freeman | Software Provider | HTTP Response Code | HTTP Response code for success should be 201 in E2E001 as per Swagger. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Update made to E2E001 design document in section 4.4.4.1, 4.5.5.1 and 5.3 to align with Swagger 1.2. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-285 |  |  | 2023-05-16 | Elexon |  | Rob Golding | SRO Design Team |  | Add replay / requeue API for Swagger 1.2 to align with existing E2E001 Design. Add additional information / clarity in the E2E001 for Interim Release 2 to align changes between design and Swagger. |  | Closed | [7 empty] | Duplicate of DIN-374
MHHS-DIN-286 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Issue clarification to Participants through DRG that all ECS Reports will be issues via Pattern B. Update of ECS Report Catalouge to reflect this. |  | Closed | [7 empty] | The ECS reports will be via Pattern A. No change is required to the ECS reports
MHHS-DIN-287 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team | Guidance notes for distribution of ECS reports | Create & Issue guidance document on the distribution of ECS Reports. To Contain : - overview of Pattern B Process - Guidance on population of IF-047 - Update of IF-047 Event Codes |  | Closed | [7 empty] | Solution yet to be defined No longer required as pattern B will not be implemented for ECS reports
MHHS-DIN-288 |  |  | 2023-05-16 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Update of Swagger with ECS Reporting Structures |  | Closed | [7 empty] | These interfaces are in place from Swagger 1.1.
MHHS-DIN-289 |  |  | 2023-05-17 | SRO Design Team | 4994 | Rob Golding | SRO Design Team | Interfaces for consumption replay | IF-015 / IF-016 - updates to E2E001 to provide clarification on design pattern. Alignments between DES-138 & Swagger alongside this. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | E2E001 design updated (Section 5.1.7) to provide additional information / clarity on these interfaces in relation to Consumption Replay. | Data interface correction | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-290 |  |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | Proposal to change all / subset of ECS Reports to Pattern B |  | Closed | [7 empty] | Duplicate | No Change
MHHS-DIN-291 |  |  | 2023-05-17 | SRO Design Team |  | Rob Golding | SRO Design Team |  | As a result of DIN-290 -- Where should the reporting assets be hosted?? DIP solution specified, but what are the other options are availible. Final solution option to be ratified and documentation updated. |  | Closed | [7 empty] | Not hosted as via Pattern A | No Change
MHHS-DIN-292 |  |  | 2023-05-17 | St Clements |  | Madison Layton | Software Provider | ISD Entity M17 | Change required to ISD Entity M17 to add in Market Segment into the table - otherwise it cannot be used to derive consent values which was its original purposes |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | 1. Update Table name to "Consent Granularity Valid Combinations" 2. Added Market Segment as new table column 3. Update table to show all valid combinations | Process Model correction | Supporting Docs |  | MHHSP_EDI021_ISD_Entities
MHHS-DIN-293 |  |  | 2023-05-17 | Design Team |  | Paul Petitt | SRO Design Team |  | Retrospective DIN raised to ensure that any changes that are made in multiple downstream documents (for example CoCo, DIP Logical Design, DIP Physical Design & DIP Security Design) are reflected / updated in LDP assured documents to ensure e2e design / requirements alignment. This was agreed in a DRG Meeting in March 2023. |  | Implemented | [5 empty] | Interim Release 1 |  | design changes to E2E001 End-to-End Solution covering points described in DIN details | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-294 |  |  | 2023-05-19 | ESG | 5030 | Luke Speakes | Software Provider | BP007 PUB009 flow | What I need to know is if the supplier will receive a PUB_009 with the Event code of [CSSDeRegistration] because nowhere on the BP007 process map does it show the supplier receiving the PUB_009 following a deactivation but on DES138 it shows the supplier as being a recipient of this event code. Step 95 (ringed below) shows the supplier as receiving the PUB_009 off the back of the Disconnection (event code [MPANDisconnection]) but then no where else on the process map does it have the supplier receiving a subsequent PUB_009 following the successful deactivation. Additional step required from step 130 (maybe 137?) to show both PUB-009 Mpan Disconnection and PUB-009 Deactivation going to supplier |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | BP007 change : There is already a flow from Step 85 to Step 95 for PUB009 for disconnection (no change) But need to Add a new step (137) for Receive Deactivation in Supplier lane from Step 130 for PUB-009 MPan deactivation in BP007 And there is already a PUB-037 flow from step 145 to Supplier step 157 for confirmation (so no change there) Addition of step 137 to BPD007 | Process Model correction | Metering Changes | Disconnection | MHHSP-BP007-Disconnection, BPD007
MHHS-DIN-295 |  |  | 2023-05-19 | SIMS | 4821 | Martin Freeman | Software Provider | L1/L2 Error Codes | Error code detail updates in DES-138 for Level 1 and Level 2 validation needs to be clarified |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updates made to Introduction Tab of DES138 in order to clarify Lev1 vs Lev2 error codes. Design is such that participants should expect error code(s) at either level. Further ammendments could be made following Avanade clarifications. | Data interface correction | Supporting Docs |  | DES138 Data interface Definition
MHHS-DIN-296 |  |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | It is envisioned that Configuration Management of ISD will largely follow the existing customs, practices and processes as are currently in place for managing MDD changes. However, DIN is required to formally confirm the Owner(s) and allowable update mechanisms (Standard or FastTrack) for each of the new ISD Entities outlined in the DIN. |  | Closed | [7 empty] | This is a Code Drafting issue not a Design / DIN issue. Code drafting team will be covering ISD maintenance processes
MHHS-DIN-297 |  |  | 2023-05-19 | SRO Design Team |  | Sean Cooper | SI Design |  | What Participants are recognised in the existing / new ISD Participant tables…. How does this link in with the parties recognised by the DIP (and assigned DIP Roles / IDs …. Or Not) …. In particular how are MDRs referenced in ISD? Does this reference need to identify the ‘type’ of MDR? Also, there is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 |  | Closed | [7 empty] | These issues are covered in Release 3 updates (DIN372 & DIN 070) . ISD updated to confirm participants recorded in M16, a new table M18 "DIP Participant Roles" was added.
MHHS-DIN-298 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Update to UMSDS method statement. | As I understand it, you are advising we should A flag the consumption data (even though it isn’t Actual), until the zero charge code D0388 UMS Inventory is received from the UMSO. Therefore - if we have an inventory, regardless of the energisation status of the MPAN, we always use an A Flag. But as you’ve stated, this means an IF-013 will be issued to us as UMSDS, because there is A data, against a De-Energised MPAN. If this is the design/requirement then it is understood – but I would like to call out that this should be detailed within the UMSDS method statement – so I think a DIN is needed to get this requirement added? |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement
MHHS-DIN-299 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | IF-013 update to include UMSO recipient | Further to this (DIN-298), the cause of this IF-013 being issued can only be that the UMSO has not provided the UMSDS with the correct D0388 UMS Inventory to use. Therefore – the UMSO has a requirement to receive the IF-013 to tell them this. However, the Interface Catalogue has not designed that this will get sent to the UMSO. I think this is a Design Issue too, and also needs a DIN raising so that the IF-013 is provided to the UMSO. |  | Closed | [7 empty] | No this is incorrect. UMSO is not involved with Consumption. If IF-021 submission is rejected this is an issue for the DS (incl. UMSDS) to address and Manage. Any issues regarding the metering onsite/energisation status need to be managed by the DS (incl UMSDS) with their appointing Supplier and Partner Metering Service. |  |  |  | DES138
MHHS-DIN-300 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | You are advising a Load Shape will always require the E Flag. But as you say if the MPAN is de-energised, that MDS will reject the IF-021. Is this therefore your answer – that MDS will reject the IF-021, and there is nothing that can be done about that, so we just need to accept we will get those rejections? If so, this isn’t really a satisfactory process, to know rejections will be received in this scenario. Can you just confirm that the solution here is we just need to accept we will get these rejections to the IF-021, which we will then simply ignore? If that is the case – again a DIN needs to be raised to write this into the Design so the process is documented. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. See DIN 506 which has updated DES138 to show that IF-014 also contains warnings for MPANs with consumption on de-energised sites. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement
MHHS-DIN-301 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | the corrective action on this scenario (DIN-300) occurring will be if/when the UMSO provides the UMSDS with a D0388 UMS Inventory – then the UMSDS will stop using and submitting the Load Shape data. There does not seem to be a mechanism in the Design for the UMSO to be made aware of this issue that would be of their making, so again needs raising as a DIN please. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. See DIN 506 which has updated DES138 to show that IF-014 also contains warnings for MPANs on de-energised sites. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement
MHHS-DIN-302 |  |  | 2023-05-19 | Power Data Associates | 4273 | Richard French | Data Service Provider | Clarification of rejection of IF-021 | I’ve pulled together the below table. This covers all the possible scenarios of the UMSDS either having or not having the D0388 UMS Inventory. Combined with whether that D0388 UMS Inventory has load associated data within it. Also combined with whether the MPAN is Energised or De-Energised. Here I’ve listed which Settlement Period Quality Indicator should be used, and where applicable, which Estimation Reason Code should be used. Should this be included in the UMSDS Method Statement and if so, are you happy with the below. In Green are steps we understand. In Red, these remain Unknown to us based on the Design and your answers given. In Orange, these are answered based on your guidance on your email of 28 April – but are not specified in the written Design. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Table provided by PDA and SRO Design has been updated in section 10, Publish and Data Flags within the UMSDS Method Statement. | Method statement correction | Supporting Docs | Method Statement | METH004_UMSDS Method Statement
MHHS-DIN-303 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.2.3 - Changes to Data formatting to align with Swagger / DES-138 |  | Implemented | [5 empty] | Interim Release 1 |  |  | Technical corrrection | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-304 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 4.4.3 - Case Sensitivity - additional information added to provide clarity on approach |  | Implemented | [5 empty] | Interim Release 1 |  |  | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-305 |  |  | 2023-05-18 | Design Team | 4811 | Steve Weston | SI Design |  | E2E001 - section 5.1.7 - Additional Detail required for IF-47 / ISD to provide clarity on approach / steps |  | Implemented | [5 empty] | Interim Release 1 |  |  | Design Ambiguous | Supporting Docs |  | MHHSP-E2E001 End-to-End Solution Architecture
MHHS-DIN-306 |  |  | 2023-05-22 | Tym Huckin | 3992 | Tym Huckin | Consultancy | Clarification/examples for DI-101 for BST/UTC cross over period | Further clarity / worked examples for UTC Settlement Date (DI-101) for BST / UTC cross over period. |  | Closed | [7 empty] | This is not a design change it is a Question/Clarification .
MHHS-DIN-307 |  |  | 2023-05-22 | CGI | 5042 | Dave Webster | Software Provider |  | Status code incorrectly included in required, although not in Standard Response Body Type. This is in Swagger 1.2. |  | Closed | [7 empty] | Duplicate of DIN-282
MHHS-DIN-308 |  |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | S0 Block required property | Add required property to all the S0 blocks in the interface definition |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Update made to Swagger for all Interfaces to mark 3 fields in the S0 block as mandatory. | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-309 |  |  | 2023-05-23 | Design Team |  | Rob Golding | SI Design | Swagger Alignment to DES-138 | Define Transaction ID (DI-990) with no Min Length to align with DES-138. This is DT-014. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (DIP Transaction ID min length removed) | Technical corrrection | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-310 |  |  | 2023-05-23 | ELEXON | 5173 | Rob Golding | Central Body | Guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 | Guidance on how the Effective From Date {MM2DPM} & Effective To Date {MM2DPM} in ISD M16 are to be applied (if at all), i.e. does the DIP need to consider the effective period and only accept messages on the production system when the message falls within this period? And if so what date within the message should be used as a check? Or the physical date/time of message receipt? Or doesn’t the DIP need to consider these dates at all and no check needs to be applied? |  | Closed | [7 empty] | This has been included in the DIP onboarding design.
MHHS-DIN-311 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-985 / DI987 both String 60. Swagger Min and Max Lengths aligned |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updates made to DES-138 for Length alignment to 60. Updates to Swagger to remove min length for DI-985 and DI-987. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-312 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-984 / DT-009 needs to be updated to be min 3 / max 5 length. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Sender Role - change on 01 Data Catalogue DI-984 as per description | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface
MHHS-DIN-313 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S1 - Sender Timestamp updated correctly (from sent timestamp) in Swagger to align with DES-138 |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (renamed to Sender Timestamp) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-314 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - Publication ID Min Length updated in Swagger 1.2 to be 6 to align with DES-138 (rather than 7) |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Publication ID Min Length now 7, not 6) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-315 |  |  | 2023-05-23 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | D0 - DIP Correlation ID should have no min length to align with DES-138 (rather than min length of 1) |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (DIP Correlation ID has no min length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-316 |  |  | 2023-05-25 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, all DT-006 and DT-006N should have min length 10 & max length 10 to be consistent. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated DES-138 01-Data Catalogue to align Data Type and provide consistency to Swagger. Removed DI-095 which is no longer used. | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface
MHHS-DIN-317 |  |  | 2023-05-23 | St Clements |  | Sean Cooper | SRO Design | B9xx array references within Swagger to be updated within DES138 | Update DES138 IF document to include reference to the B9XX Array references held in Swagger |  | Initial Assessment/Updating | No |  | Design ambiguous | N/A |  | Post Go-live Release | 0 | Solution yet to be defined | Design Ambiguous | Supporting Docs | Interfaces | DES138
MHHS-DIN-318 |  |  | 2023-05-23 | REC | 5049 | Jonny Moore | Consultancy | Addition of 'Effective from date' data items to RMP Status (regi) and MP Status in IF-050 | While completing the design phase for EES we noted that the following items with the IF-050 do not have an effective from date. - RMP Status (Registration) - MP Status These items currently have an effective from date held in EES and not including this in the IF-050 would have the effect of removing these items from EES. |  | Closed | [7 empty] | REF DIN-508 | No Change
MHHS-DIN-319 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | S0 - EventCode to marked as required to align with DES-138 |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Event Code marked as required) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-320 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | In DES-138, S1 - Environment (DT-013) should have min length 3 & max length 10 to be consistent with values. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | 01-Data Catalogue DI-991 Environment Set Min to 3. However, string length is 10, so max length should be set to 10 | Data interface correction | Supporting Docs |  | MHHS-DES138 Data interface definition
MHHS-DIN-321 |  |  | 2023-05-23 | St Clements | N/A | Sean Cooper | SRO Design | B005 add to IF-036 | Consider adding B005 to IF-036 so that incoming SP knows who previous SP were |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Added B005 to IF-036 so that incoming SP knows who previous SP were. Updated block name to B005 - Incumbent/Outgoing Service Providers | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-322 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B002 - Incoming Supplier MPID - Swagger aligned to DES-138 for min / max lengths |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Incoming supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-323 |  |  | 2023-05-24 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | B003 - Ougoing Supplier MPID - Swagger aligned to DES-138 for min / max lengths |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Update made to Swagger to align with DES-138 (Outgoing supplier MPIDs min / max lengths updated) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-324 |  |  | 2023-05-24 | EDF | 4780 | Paul Saker | Supplier | NHHSP-BPM00C- Transfer of Reads on Change of Data Service process steps and messages clarification | NHHSP-BPM00C- Transfer of Reads on Change of Data Service details several process steps and messages related to obtaining and sharing register readings between the gaining and losing suppliers to agree a CoS, and to initiating the missing/disputed reads process defined in the Retail Energy Code where CoS reads are missing or need to be disputed/amended. However, it appears that there is no further detail defined within the Design Artefacts regarding how exactly these process steps would work, including amongst other things: • Timing/Operational Choreography – for example it is not clear exactly when losing and gaining suppliers would be expected to attempt to communicate with the meter, or the timescales for sending data obtained between suppliers. • Data to be included in messages – while BPM003C refers to the inclusion of ‘register readings’ in some of the messages it is not clear which registers should be included for smart meters and non-smart meters – for example whether that should just be the registers on a smart meter that the sending supplier uses for billing, or whether that should be all the 48 time of use registers stored on the smart meter. Additional input from Andrew Margan - Within the code workstream, we believe the Operational Choreography document needs to be updated to reflect SLAs. Without this, we can’t complete the Code drafting. If you disagree, we would appreciate an early heads up, so we don’t look disjointed in front of industry. |  | Closed | [7 empty] | This is not an MHHS Design Issue. D300 / Agree Reading SLAs are defined and set by RECCO. We have replicated the existing 5 day window for capture / submission of a reading(s) all other D300 timescales still apply as per RECC process. Register Readings can only be provided on the D0010 - where this is required [for smart meters] it would replicate the current as is process defined in the current DC BSCP
MHHS-DIN-325 |  |  | 2023-05-24 | CGI |  | Dave Webster | Software Provider | Status Code Missing from MsgBody | In the SubmitEvents StandardResponseBodyType object (SubmitEvents ¦ 1.2 ¦ MHHSPROGRAMME ¦ SwaggerHub), it states that “statusCode” is a required field. Yet its’ definition does not exist in the properties of the object. StandardResponseBodyType: type: object properties: transactionID: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-014-DIPTransactionID' senderUniqueReference : $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-995-SenderUniqueReference' correlationId: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-011-CorrelationID' sentTimestamp: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-003-DateTime' senderId : # the sender of this message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' recipientID : # indended (logical) recipient of the message, i.e sender of the original event message $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' DIPConnectionProviderId : # physical recipient of the message (if different to recipient Id) $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-006-DIPParticipantID' message: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-005-StatusErrorMessage' help: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-019-HelpText' serviceTicketURL: $ref: 'https://api.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.2#/components/schemas/DT-018-URL' required: - transactionId - sentTimestamp - senderId - recipientId - statusCode - message - help - serviceTicketURL |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | This has now been updated in V1.2 of Swagger StatusCode Added to the ResponseBody. | Technical corrrection | Supporting Docs |  | JSON/YAML files
MHHS-DIN-326 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Changes required to DES-138 / interface catalogue given changes in Migration Design e.g. the addition of interface IF003 and potentially ISD. |  | Closed | [7 empty] | Duplicate of 247 | No Change |  |  | None
MHHS-DIN-327 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | IF-005 User Guide | The IF005 User Guide explains how the IF005 should be populated. We have a request for clarification on whether the IF006 will be populated identically or if the Meter ID in the IF006 will reflect the Modified Meter Id in the IF005. Is IF-005 identical to IF-006, or is it with updated MTD's. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | IF-006 should be a facsimile of IF-005. In the case of change of MSN... MSN field will reference the (old) MSN and Modified MSN will be populated with new/revised MSN. All subsequent flows following the IF-006 will only reference the NEW/REVISED MSN. We further clarified this in a change to the Note(s) section on IF-006. | Data interface correction | Supporting Docs |  | DES138
MHHS-DIN-328 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body | Operational Choreography Update: Addition of SLA for RS end appointment data to the CSS | The operational choreography does not include an SLA for the RS to send appointment data to the CSS or the timings by which the CSS and DSP should deliver their roles within the process. These need to be added to the operational choreography for clarity, noting the interaction with CR018. | CR018 | Closed | [7 empty] | RECCo confirmed closure of DIN following review of amendments to the Operational Choreography for CR018. ALL Updates between RS and CSS/DSP are existing interactions, covered by existig SLA's document in RECCO documentation. OPSC document was updated per Recco comment to highlight existing RECCO SLA in this area and to ensure primacy of the RECCO documented timings.
MHHS-DIN-329 |  |  | 2023-05-25 | RECCO | 4824 | Sarah Jones | Central Body |  | Approach on a business rule where the ERDS does not send a MEM de appointment / appointment for an MHHS migration where the same MEM is being appointed under MHHS arrangements e.g. they have the same MPID. The expectation is that smart and advanced MEMs will use the M role code for the interaction with CSS so from their perspective there should be no change. |  | Closed | [7 empty] | ERDS Interfaces are ouf of scope of MHHS. If a change to ERDS interface is required or efficiencies in its existing operation are possible to align with MHHS Design - this would be a consquential change. | No Change
MHHS-DIN-330 |  |  | 2023-05-25 | Ovo Energy | 5225 | David Morley | Supplier | Long Term Vacant | BSCP504 section 4.15.3 stipulates the criteria via which suppliers can classify sites as Long Term Vacant (LTV). BSCP701 stipulates actions that SDS shall take if the supplier nominates that a site is LTV. However, the criteria that suppliers shall use for classifying LTVs in MHHS is missing. Can you please signpost where the new criteria will be located? |  | Closed | [7 empty] | BSCP is responsible for revising the code specification, there are no changes to design specified. Code team will get in touch with the participant.
MHHS-DIN-331 |  |  | 2023-05-25 | MHHS | 4733 | Martin Freeman | Central Body | Secondary Routing | Secondary routing for IF-013 is specified as being conditional upon the value of DI-015. However, DI-015 (Connection Type Indicator) is a property of a repeating block, and there is no constraint in place to suggest that each element in the repeating block must have the same value for this (or any other) property, in which case multiple rules in the routing table could apply simultaneously. The routing table design seems to suggest that only a single rule should apply at a time and that routing should not be derived by blending multiple rules. If this is so, and a message is received where different elements in the B050 have a different Connection Type Indicator then there is no coherent way to implement this in conformance with the routing table. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Agree there was a routing contradiction for scenarios/periods where a different connection type was in effect. Interface notes section has been updated to direct the use of 'separate' IF-013 messages in such circumstances. Note also makes clear that repeating B050 blocks are acceptable where other elements (not Connection Type) of the CCC vary over the period to be defaulted. | Design Ambiguous | Supporting Docs | Default Consumption | MHHSP-DES138-Interface Catalogue
MHHS-DIN-332 |  |  | 2023-05-25 | MHHS | 4750 | Martin Freeman | Central Body | IF-013 Routing | In the routing table for IF-013 all rules are conditional upon S0.Eventcode == [ActivePowerDefaulted], which means that for IF-013 message where Eventcode == [ConsumptionOnDeEnergisedMPAN] there is no routing at all, which means when this message is sent to the DIP it will not be routed anywhere and will simply disappear. That's almost certainly an error. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Event code [ConsumptionReceivedonDeEnMPAN] has been moved from IF-013 to IF-014. The valid event code list and routing rules have now been updated for both interfaces to reflect the move. v1.2 of Swagger also updated to reflect this change Duplicate of DIN 255 | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue
MHHS-DIN-333 |  |  | 2023-05-25 | MHHS | 4760 | Martin Freeman | Central Body | Connection Type Required to Support Routing of IF-014 | All of the routing rules specified for IF-014 are conditional upon DI-015 (Connection Type Indicator). But IF-014 does not have any blocks with this property, which means this message won't get routed anywhere. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Block B067 - Connection Type Added to IF-014 in order to support routing requirements. Swagger v1.2 updated to reflect this change. (Duplicate of DIN256) | Data interface correction | Supporting Docs | Consumption | MHHSP-DES138-Interface Catalogue
MHHS-DIN-334 |  |  | 2023-05-25 | MHHS | 4766 | Martin Freeman | Central Body |  | The routing table for IF-018 specifies roles AMSC, UMSC, UMDC for Secondary routing. There are no such roles in either the DES138 nor the E2E001. |  | Closed | [7 empty] | Secondary Routing Review/Changes have superceded this issue - Ref DIN-268
MHHS-DIN-335 |  |  | 2023-05-26 | British Gas/Engage Consulting | 4640 | Neil Strange/ Haz Elmamoum | Consultancy | Four questions on IF004 | IF/PUB-004 – DIP Common Blocks referencing MHHSP-DES138-Interface Catalogue v5.1.1 As a minimum this needs to be referenced in the supplier requirements MHHSP-BRS004-Supplier Overview and MHHSP-BRS002-Metering Service requirements, but to ensure parties get sight of this we would suggest it needs to be included in a business process map and have associated requirements. For IF-004 to be useful to participants DI-999 – Event Code needs to be elaborated e.g. 1- Installation 2- Removal; 3- Exchange; 4 - Found (Where installed by Gas supplier and Elec Supplier takes ownership) C/M/O rules for DI-192, DI-193 and DI-194 need to be explained in the notes – presumably driven by event code Available is spelled incorrectly (available) for DI-192 and DI-194 there are a couple of angles here – 1) ensuring wider awareness and 2) it seems there is a question mark on the governance here as it is odd a flow has been added but industry does not appear to have been sighted on it especially with no associated referencing in artefacts and no process map, so effectively no one has any idea how it is supposed to be used. Although it was formally agreed not to include and use bilaterally....from a Large Supplier Constituency perspective, my members are keen to ensure design clarity and how flows are to be used or not, regardless of their ad-hoc / bilateral nature. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Updated BP009 Change of Metering to include the "optional" sending of IF-004 from MS via DIP to Supplier, if changes to Comms Hub need to be notified. Included same updated to BPD009 to reflect new BP steps. Other comments have been addressed previously and are reflected in DES138 IF-004 | Process Model correction | Meter to Bank | IF-004 | BP009 Change oF Metering BPD009 Change of Metering
MHHS-DIN-336 |  |  | 2023-05-26 | MHHS |  | Rob Topley/ Zak Hussain | SI Design | Requirements clean up in iServer | Process Step No. BP Step ID Process Map wording Interface ID Sender Recipient/Service Traceability Requirement Traceability Method Statement iServer Requirement Name iServer Step name Issues Found BP01 170 BP01 - 170 Send Site Tech Details on Metering Service Request MHHS-RS-LD-012.1 #N/A LDSO170a Send Site Tech Details on Metering Service Request Missing (only on BPD and traceability matrix) BP01 175 BP01 - 175 Receive Site Technical Details D0215 LDSO Metering Services MHHS-RS-MS-037.1 #N/A MET175 Receive Site Technical Details Missing (only on BPD and traceability matrix) BP03B 95 BP03B - 95 Manage SP Appointment Amendment Request Response PUB-035 DIP Supplier MHHS-BR-SU-35.1 #N/A SUP095a - Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP03B 96 BP03B - 96 Manage SP Appointment Amendment Request Response PUB-035 DIP Data Services Metering Services MHHS-BR-DS-11.1 #N/A ESP96 – Manage SP Appointment Amendment Request Response Missing (only on BPD and traceability matrix) BP05 315 BP05 - 315 Issue Reading Data MHHS-IF-041 Data Service DIP MHHS-BR-DS098.2 #N/A DAT315 – Issue Reading Data Missing (only on BPD and traceability matrix) BP05 340 BP05 - 340 Process Reading Data PUB-041 DIP Supplier MHHS-BR-SU047.1 #N/A SUP340 Process Reading Data Missing (only on BPD and traceability matrix) BP05 350 BP05 - 350 Process Reading Data PUB-041 DIP LDSO MHHS-BR-LD009.1 #N/A LDSO350 Process Reading Data Missing (only on BPD and traceability matrix) BP010D 1055 BP010D - 1055 Receive updated Legacy information PUB-026 DIP Central Settlements MHHS-BR-RD-018.1 #N/A ECS1055 Receive updated Legacy information Missing (only on BPD and traceability matrix) All these requirements don’t exist on any requirement catalogues, they’ve only ever been on a BPD document or the traceability matrix (which are essentially the same document). Also, the highlighted traceability has a typo and is on a requirements artefact but is wrong on both the BPD and traceability matrix. |  | Closed | [7 empty] | Requirements have been found in BRS001, BRS004, BRS005, BRS014. Models have the correct steps identified. Unable to identify whats missing, checking with the originator. Confirmed with originator no further changes needed | No Change | Supporting Docs | Supporting Docs | BRS001, BRS004, BRS005, BRS014
MHHS-DIN-337 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger alignment to DES-138 | R0 - Response Message Min length updated to align with DES-138 |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated R0 - Response in Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-338 |  |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier | BP003/BP002 to be updated to clearly show IF-036 going to both Import & Export supplier | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. BP003/BP002 to be updated to clearly show IF-036 going to both Import & Export supplier |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | On an Export Supplier COS, the Service Providers will be de-appointed on notification of the Secured Active. As the Export Supplier is unable to appoint their own Service Providers (in the case of Linked Import/Export), the auto-aligmnment functionality (BP011C) will trigger the correct Service Providers to be appointed and the Service Providers will be notified of the Supplier in IF-036. However this DIN has highlighted the need for the export Supplier to be notified of the Service Provider changes. BP003/BP002 updated from Step 255/245 to re-label "PUB-36" flow to Step 260 for the Supplier (prospective/incumbent) to state "PUB-036 for Import & Export Supplier". Change is not reflected in the BPM-003 for forward migration as linkages only become active when both Import/Export are migrated. See also 339 | Process Model correction | MPAN Ownership | Process Models | BP003 BP002
MHHS-DIN-339 |  |  | 2023-05-26 | British Gas | 4583 | Neil Strange | Supplier | IF-001 to be updated to be additionally sent to the Export supplier rather than just the import | The whole process which you have mentioned here is based on the Supplier triggering the Agent Appointment process to appoint the metering service. Which is NOT applicable for Export meters. The question is therefore how will the MS know that there has been a change in supplier and update their records if the IF31 is not triggered by the new supplier. Also your answer below looks at BP003 , but this not part of the DS appointment process (Which the incoming supplier can control for Export meters) but the MS appointment process – which the incoming export supplier cannot appoint as per the rules under linked MPANs. IF-001 to be updated to be additionally sent to the Export supplier rather than just the import |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | On an Export Supplier COS, the Service Providers will be de-appointed on notification of the Secured Active. As the Export Supplier is unable to appoint their own Service Providers (in the case of Linked Import/Export), the auto-aligmnment functionality (BP011C) will trigger the correct Service Providers to be appointed and the Service Providers will be notified of the Supplier in IF-036. However this DIN has highlighted the need for the export Supplier to be notified of a new Import Supplier. BP001 updated to re-label "PUB-001" flow for the Supplier (prospective/incumbent) to state "PUB-001 for Import & Export Supplier". See also 338 | Process Model correction | MPAN Ownership | Process Models | BP001
MHHS-DIN-340 |  |  | 2023-05-26 | UKPN | 4547 | Neal Medley | Network Operator | ELEX-REP-02/02A report | The reports ELEX-REP-02/02A will only contain aggregated data for A(General LLF Class Import and C (General LLF Class Export). The I/F021 can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/014 Rejected Consumption Data Submission and I/F MDS Defaults Applied to any I/F021 data to ensure you are not using rejected data or are missing I/F 021 data in respect of an MPAN. MDS Method Statement to be updated to reflect |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Updated the below test to Section D within MDS Method statement: 17.4 The I/F021 ‘UTC Settlement Period Consumption Data’ can be subscribed to by the LDSOs for all MPANs that are not whole current (Connection Type not equal to W). The LDSOs will need a process to derive whether the data provided on the IF0-21 is Site Specific or General using the DUoS Tariff Id associated with the MPAN which is provided in the I/F 021 in order to avoid double charging. Additionally, the LDSO will need to process the I/F014 Rejected Consumption Data Submission and I/F ‘Notification of Defaulted UTC Settlement Period Consumption Data’ to any I/F021 data to ensure LDSO’s are not using rejected data or are missing I/F 021 data in respect of an MPAN. | Design Ambiguous | Supporting Docs | Method Statement | MDS Method Statement
MHHS-DIN-341 |  |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | MUM Event not required by MDS | For IF-018 the event [MUMIndicator] is routed to MDS and indicates metered/unmetered. This event is not required by MDS as they can infer this from the Market Segment (Advanced, Smart and Unmetered). DIN raised to remove the routing |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | MDS Removed as Always Recipiant for Event [MUMIndicator] on IF-018 Routing rules | Data interface correction | Supporting Docs | IF-018 | MHHSP-DES138-Interface Catalogue
MHHS-DIN-342 |  |  | 2023-05-26 | UKPN | 5194 | Neal Medley | Network Operator | ELEX-REP-02/02A Consumption data clarification | The intent is that the daily volume on actuals or estimates are the sum of the appropriate consumption data. So when added together they should equal the summed Total of the Settlement Period data (Total Uncorrected Volume) barring any rounding errors. The data is given in MWh to six decimal places (i.e. to the nearest Watt hour). I assume DUoS billing only calculates to the nearest unit so would not expect any rounding errors to impact. The A flags are set out in the ELEX-REP-02/02A are the same as those set out in the CCC table in the VAS Method Statement which is also in the MDS Method Statement. I agree the list in the calculations only are missing the full list of SPQI that are deemed to be actuals as set out in the ELEX-REP-02/02A. DIN raised to correct the calculation |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Updated full list of actuals with the MDS Method Statement. The amended list added to the Method statement: A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6. | Method statement correction | Supporting Docs | Method Statement | MDS Method Statement
MHHS-DIN-343 |  |  | 2023-05-26 | Elexon | 5171 | Ayo Ojo | Central Body | Routing rules table | The routing rules on the IF-037 sheet state that MDS will 'always' receive the DSDeApp event code, however the 'Always' column on the IF_LIST does not state Central Settlements for MHHSP-IF-037. IF list needs updating to reflect that the DSDeApp event always routes to MDS |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Decision taken to remove Recipiants (COLs G,H &I) from the IF_list - as just duplication of information contained within each of the IF spreadsheets. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue
MHHS-DIN-344 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B005 Custom Block update Swagger to align with DES-138. Current Metering Service MPID Length removed. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138. Current Metering Service MPID Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-345 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B024 Custom Block update Swagger to align with DES-138. DUOS Min Length removed. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138. DUOS Min Length removed. | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-346 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design |  | IF-001 - B032 Custom Block update DES-138 to align with Swagger. Update DI-122 (Profile Class) to Integer from String-2. |  | Closed | [7 empty] | DI-122 remains as String 2 for Profile Class to support requirements for enumerations. | Data interface correction | Supporting Docs |  | None
MHHS-DIN-347 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-001 - B035 Custom Block - update Swagger to align with DES-138. Remove min length. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-348 |  |  | 2023-05-26 | Design Team |  | Steve Weston | SI Design | IF002 correction | IF-002 - B074 Custom Block. Clarification on DI-091. DES-138 says this is 1 digit to the left of the decimal point. Swagger says 5 to 6. DES-138 to be updated to the correct value. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated Swagger to be an Integer (1), Min of 1, Max of 1, example of 5. This now aligns with DES-138. | Data interface correction |  |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-349 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Correlation ID Issue IF-006 | Routing Rules in DES-138 do not always correctly identity where Correlation ID == Copy ie, it's missing for IF-005 / IF-006 so this needs to be updated correctly across all interfaces. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated IF-006/IF-008/IF-039/If-028/IF-026/IF-016 routing rules to show use of a "Copy" in Correlation ID (ie copied from the preceeding IF txn pairing) | Missing/incorrect validation rule | Supporting Docs |  | DES138
MHHS-DIN-350 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-005 B033 to align Swagger with DES-138 (Postcode removal, mandatory modified meter id) |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Postcode removal, mandatory modified meter id) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-351 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B071 to align Swagger with DES-138 |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-353 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | Align IF-033 B032 to align Swagger with DES-138 (SSC Min Length should be 4) |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated SSC Min Length to be 4) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-354 |  |  | 2023-05-30 | SJW |  | Sarah Jones | Consultancy | Design team confirmation for sending of IF-037 and not IF-037 to losing MEM | Please see below details of a new design query related to the Registration Tranche of Code Drafting. We note that in BP011C there is a process whereby the Registration Service will auto de-appoint / appoint agents for secondary related metering points and linked export metering points as part of their validation. The business process only includes the sending of the IF037 to the Losing MEM and not the IF035. Please could you confirm that this is correct and that in this instance the Losing MEM would not receive an IF-035. If this is the case, we think there should be a change to Metering Service requirements MS-018 and 019 to clarify that where the Losing Metering Service receives an IF-037 with no preceding IF-035 then they should send the MTDs at this point. The alternative would be to include the sending of an IF-035 as well as an IF-037 accepting that these would arrive at a similar time. This would align to the process for managing retrospective MEM appointments where we understand that the Losing MEM would receive both the IF-035 and the IF-037. We also suggest amending MS-008, 008.1, 009 and 009.1 to recognise this nuance as follows: MSA/MSS must obtain Export MPAN de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. MSA/MSS should note this message will be automatically triggered when a change of Metering Service has successfully completed for the linked import MPAN or a new MPAN linkage has been put in place where the [linked import / primary related] MPAN has a different appointed Metering Service. Presumably there is a similar impact on the data service requirements that would need to be considered. |  | Closed | [7 empty] | Solution options discussed with SCS. Closed as covered under DIN 560 |  | Supporting Docs
MHHS-DIN-355 |  | DI-179 | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Number of Register Digits | Revisit and confirm IF-005 Cumulative Digits validation rule against latest version of the CP |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | All instances of DI-091 (IF-002,IF005,IF-006,IF-033,IF-036) updated to reflect updated logic. IF-005 validation rules updated also to reflect new guidance. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue
MHHS-DIN-356 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B073 - update Swagger to align with DES-138 (consumptionAmendmentSupplierReference max length) |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated consumptionAmendmentSupplierReference max length) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-357 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-027 B902 - update Swagger to align with DES-138 (supplierConsumptionAmendmentRequests typo update) |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated supplierConsumptionAmendmentRequests - remove typo) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-358 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-034 B070 - update Swagger to align with DES-138 (contractReferenceMeteringService max length 10) |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated contractReferenceMeteringService max length 10) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-359 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: The method statement states that “The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN on notification of the set-up of that MPAN in MHHS-IF-001.” However, it will be the MHHS-IF-036 Registration Service Notification of Service Appointment & Supporting Info that will initially provide the fact that an MPAN has migrated to Central Settlements. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement updated with following text in red: 2.3 The Market-wide Data Service should calculate an Annual Consumption for a newly created MPAN within 30 calendar days following notification of the set-up of that MPAN in MHHS-IF-036 'Registration Service Notification of Service Appointment & Supporting information' or MHHS-IF-001 ‘Notification of change of Supplier’. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption
MHHS-DIN-360 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | AC Method Statement | We need to raise a DIN on the AC method Statement and AC requirements: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: 3.3 Where a years’ worth of data, >=75% and <100% of actual UTC Period Consumption data (where Settlement Period Quality Indicator = A, A1, A2, A3, AAE1, AAE2, AAE3, E2 or E6) has been used to calculate the Annual Consumption, the Annual Consumption Quality Indicator should be set to “1”. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement updated with following text in red: 3.3. need amending to >=75% to avoid an issue if it is exactly 75%: | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption
MHHS-DIN-361 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Greater than or equal to change for UTC Period Consumption Data | We need to raise a DIN on the AC method Statement and AC requirements: Likewise 3.6 needs to say greater than or equal to 182 days: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement updated with following text in red: 3.6 For each MPAN ‘k’ where fewer than 365 days and greater than or equal to 182 days of UTC Period Consumption data is available, the Market-wide Data Service (MDS) will derive the Annual Consumption (ANN_CONY) by summing the available consumption for each UTC Period and scale to 365 days the Annual Consumption the Annual Consumption Quality Indicator should be set to ‘4’. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption
MHHS-DIN-362 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Section Name change | Section 5 incorrectly named Section 6 needs to be updated: 6. Transition and Next steps |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Section 6 has been updated to Section 5 within AC Method Statement and old section 5.1The initial Annual Consumption calculation, as set out in section 3.7 above may change, depending on the consideration of the working groups during the MHHS Transition requirements work- has been removed | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption
MHHS-DIN-363 |  |  | 2023-05-30 | Design Team |  | Kevin Spencer | SI Design | Load Shaping Service calculations | We may also need to document how this is calculated by the Load Shaping Service in the first year. I believe Helix have developed a calculation and this would need to go in the Load Shaping Method Statement and be referenced in the AC Method Statement. |  | Closed | [7 empty] | Kevin Spencer to arrange a session with Mike Ceney to discuss solution further. Upon further discussion with Kevin Spencer on 4/8/23 it was confirmed this DIN could be closed as the change is in relationn the AC Method Statement. No changes required to the LSS Method Statement | Method statement correction | Supporting Docs | Method Statement | Annual Consumption Meth 10
MHHS-DIN-364 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-035 - B066 - mark as mandatory in Swagger as per DES-138 |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated so B066 is a mandatory for IF-035 custom block) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-365 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-004 - B093 - update Swagger to align with DES-138 (min Length on commsHubGUID / GPF-GAS-GUID) |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated min Length on commsHubGUID / GPF-GAS-GUID) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-366 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 custom block - SSC add min length to align with Swagger |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B032 custom block - SSC add min length to align with Swagger) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-367 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-025 - B032 Profile Class - updated Swagger to be a String to align with DES-138 |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B032 Profile Class Swagger to be a String to align with DES-138) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-368 |  |  | 2023-05-30 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | IF-013 - B049 updated Swagger to align with DES-138 (run Number optional) |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated Swagger to align with DES-138 (Updated B049 Swagger to align with DES-138 (run Number now optional) | Data interface correction | Supporting Docs |  | Swagger 1.2 and JSON/YAML
MHHS-DIN-369 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | Switch Cancellation Info Note | Update BP002/003 to add informational note that Registration Cancelations will be processed as soon as they are received by SCS from CSS i.e. Apps Lapsed through switch cancelation sent immediatly not held until Proposed App Date. Also updates to Forward Migration BP002/003 for consistency. Changes to OPC added the following words to OPC_190 in the Activity column (section 4.4) “(including Switch Status Updates e.g. Cancelled)” |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | BP-002/003 updated to include new informational Note in Supplier swimlane relating to CSS Switch Cancellations. OPC updated to make it clearer that Secured Active Processing includes Switch Status Update processing. to OPC_190 in the Activity column (section 4.4) “(including Switch Status Updates e.g. Cancelled)” | Process Model correction | MPAN Ownership |  | BP002, BP003, OPC001 Forward Migration BP002 & BP003
MHHS-DIN-370 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team | IF-005 Update Window Guidance for Prev MS | Change IF-005 and Guidance Doc to allow Meter Updates within 10 day window for previous MS |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | New validation rule added to IF-005/MeterUpdate to allow previous MS to submit if within 10 day post appointment period. IF-005 User Guide section 9.3 updated to reflect same. | Missing/incorrect validation rule | Supporting Docs |  | DES138, IF-005 User Guide
MHHS-DIN-371 |  |  | 2023-06-01 | SRO Design Team |  | Sean Cooper | SRO Design Team |  | Review design to ensure only Supression of IHD info for advanced segment and NOT "deactivation" of underlying IHD record. |  | Closed | [7 empty] | Confirmed that IHD details will be retained on Smart to Trad Exchange. Any IHD info present will be suppressed (ie not included in msg) if Segement is Advanced. No change required to documentation. Possible data cleanse issue - Dan T. to raise in Data Forum.
MHHS-DIN-372 |  |  | 2023-06-01 | MHHS | 5298 | Rob Golding | Central Body | Mapping Roles | There is a need to master the mapping of Market Participant Role to DIP Role within the MHHS solution. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | New entity M18 created to show the DIP market roles. Minor corrections to M16 to clarify DIP ID field length. | Other | Supporting Docs | ISD Entities | MHHS-EDI-021-ISD_Entities
MHHS-DIN-373 |  |  | 2023-06-02 | MHHS | 5272 | Rob Golding | Central Body |  | There is a need to provide clarification on which market roles and DIP roles will be covered in the new ISD entities #45 & M16 |  | Closed | [7 empty] | Duplicate of DIN-297
MHHS-DIN-374 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Message Replay & Requeue functionality | Message replay and requeue functionality needs to be added to the DIP API interfaces, which requires changes to the Swagger / YAML definitions. Detail is required in the E2E design documentation to explain how the message replay and requeue functionality will work. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updates to the E2E001 design document to provide detail on how the replay and requeue will work. There are updates to Swagger to support new interfaces for /dip-channel/{id}/replay and requeue respectively. There is also a new MessageRequest Schema that is used to pass data into both of these interfaces. To support these changes, section 4.8 has been updated in the E2E001. | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents
MHHS-DIN-375 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Interface webhook configuration | Updates require to the pubconfig and webhook config to support per interface webhook configuration, alongside changes to support definition of recipient ID and role ID. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updates to the E2E001 design document to provide detail on how the webhook configuration will work, with information related to specific interface changes. There are updates to Swagger to support new interfaces for /dip-channel/{id}/pubconfig (POST and DELETE) respectively to support changes defined in the E2E001 (Section 4.5 and 4.5.1 and 4.5.2have been updated to provide more clarity / information). | Design Ambiguous | Supporting Docs |  | E2E001, Swagger 1.2 and associated JSON/YAML documents
MHHS-DIN-352 |  |  | 2023-05-30 | Design Team |  | Sean Cooper | SRO Design | Obsfucation Text | What text should be used for data obfuscation ? for things like Boolean fields (True/false) |  | Closed | [7 empty] | Closed as this is already included in section 4.3.2 of the E2E001 design document.
MHHS-DIN-376 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-099 changes required to ensure DES-138 displays the correct YAML name / Swagger aligns to this. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | "Register" spelling in name has been corrected in DI099, and DI-099 name correction for IF041 in DES138 | Data interface correction | Supporting Docs |  | DES138
MHHS-DIN-377 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-097 | DI-097 - In DES-138, this is defined as a string (2), but the existing data type is an Integer and this is an Integer enumeration. Need to update this to an Integer in both DES-138 and Swagger 1.2. |  | Closed | [7 empty] | Rejected / closed as enumeration of values requires string (2) therefore this is retained to support buisness requirements. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-378 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | Swagger Alignment to DES-138 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | DI-195 - in DES-138, information is missing in relation to Definition, Nullable, Min Length, Max Length, Type, Enum, Vals and YAML information. This information has now been added to DES-138 5.2.1. | Data interface correction | Supporting Docs |  | DES138
MHHS-DIN-379 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-048 | DI-048 - clarity required on whether this is "meter manufacture make and type", rather than just "meter manufacturer". The first is an existing data type and links to the J number, so providing further clarity / rename would quickly ensure alignment in DES-138 and then subsequently in Swagger. |  | Closed | [7 empty] | Rejected / closed as this was discussed as part of previous work off items and description has previously been approved / accepted as Meter Manufacturer. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-380 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-052 | DI-052 in DES-138 currently has 4 enum values ie, - Active Import, Active Export, Reactive Import, Reactive Export. In MDD there are currently 38 options documented. Discussion around whether ISD Entity 47 should be referenced as the list of values allowed. This can then be aligned / referenced in other other documents ie, EMAR will reference ISD Entity 47. |  | Closed | [7 empty] | Rejected / closed as this was discussed as part of previous work off items. Only 4 values are required in MHHS / DIP, therefore only these values are referenced / used as part of the enumeration to avoid bringing data from existing systems into new systems when this is not required. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-381 |  |  | 2023-06-02 | Design Team |  | Steve Weston | SI Design | DI-842 | DI-842 - Confirmation that MDR's have DIP ID's? There has been discussion in various forums to understand whether they do and if not, then this data item needs to be removed in DES-138 and Swagger. |  | Closed | [7 empty] | Rejected / closed as MDR's do have DIP ID's, therefore this value will be retained. No changes to DES-138 and no changes to Swagger.
MHHS-DIN-382 |  |  | 2023-05-06 | Design Team | 4570 | Neil Strange | Supplier | D0010 | In BP003C, at CoS traditional CoRs are transferred between suppliers via D0010. We believe this needs to be used for all meter types - as this will be needed for non-communicating smart and advanced meters – and BP003C needs to be amended accordingly. There is no mention of IF-041 and we do not believe that the DIP is expecting an IF/PUB-041 transaction between suppliers. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Supplier added as a Primary Recipient in the Routing Rules for IF-041 (DES138) - Supplier initiated Reads. Sending supplier would need to populate the DIP ID of Supplier(s) with whom he wished to share the reading. Working Group specifically decided not to discuss /include COR scenarios for Smart Metered Sites however this is not prevented by the Design - a note to this effect has been added to BP003C for clarity. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue BP-003C Transfer of Readings
MHHS-DIN-383 |  |  | 2023-06-07 | RECCO | 4558 | Sarah Jones | Central Body | Change of Segment Scenario | We cannot find anything in the design artefacts stating that the Metering Service is required to notify metering exchanges for change of segment within 2 WDs. We have found the following: MS-094: MSA/MSS must be able to publish Change of Segment Meter Exchange details and reads via the appropriate interfaces, where it is not formally appointed as the Metering Service but does have an accepted prospective appointment (Appointment Scenario = "SEG"). The MSA/MSS must issue the work update to Registration at the earliest opportunity but within [x] days of completion at the latest. OPC 240: Notification of works to be completed by D+3 Working Days (This should provide time for consumption to be provided using new MTDs ahead of the SF run.) The BP011 references the connection type update being provided by LDSOs within 2 WDs. There is no equivalent for metering updates. Will require DRG confirmation on if the 'x' should be 2 or 3 working days |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Updates to be made inline with DRG recommendation to reflect 3 working days | Process Model correction | Supporting Docs | Business Process Documentation | BP011 - Change of Segment DES138-Interface Doc BRS002- Metering Service Requirements BRS003 - Registration Service Requirements BRS005 - LDSO Overview OPC001 - Operational Choreography MHHSP-DES229-IF005_UseCaseguide
MHHS-DIN-384 |  | DI-174 | 2023-06-07 | St Clements | 4938 | Madison Layton | Software Provider | IF-038 and IF-039 blocks not the same | Block B020, B021 are not the same across interface IF-038 and IF-039. DI-140 and DI-138 (SP DIP ID) are in IF-039 but not in IF-038. Understanding was that with the DIP change that all data items in block are mandatory, the blocks were to be consistently defined across all interfaces. If extra DIP ID DI-138 and DI-140 data items are included in IF-038 then we need a new REG rejection code to allow us to reject where DIP ID is not the same as the sender DIP ID. Alternative is to separate the DI-140/DI-138 into their own blocks included on the IF-039 interface only. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Block data items were aligned in release 2. New validation rule on IF-38 add to ensure that Sender ID matches MS/DS CDC ID. New Error code REG1076 added to support validation rule. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-385 |  |  | 2023-06-07 | Design Team |  | Steve Weston | SI Design | Correlation ID | S1 Common Block - Correlation ID is mandatory in Swagger, but Optional in DES-138. Swagger should be updated to align. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Updated S1 Common Block, Sender Correlation ID in Swagger, as this is Optional in DES-138 to support business process and requirements. | Technical corrrection | Supporting Docs |  | JSON/YAML documents
MHHS-DIN-386 |  | DI-179 | 2023-06-07 | St Clements | 5258 | Madison Layton | Software Provider | Register Digits | REC Change R0102 has been approved by industry to amend the number of display digits validation Where the Meter Type is S1 the Number of Displayed Register Digits value must be either 6 or 5 Where the Meter Type is S2A, S2AD, S2ADE, 2ADF, 2ADEF, 2AEF, 2AF, S2B, S2BD, S2BDE, 2BF,2BDF, 2BDEF or 2BEF the value must be “5”. Where the Meter Type is prefixed with “S2C” the value must be “6”. Where the Meter Type is 2CDEF, 2CF, 2CDF or 2CEF the value must be “6” REG1097 validation on the IF-005 needs correcting with this change, and the population notes for data item DI-091 across multiple interfaces also needs correcting |  | Closed | [7 empty] | Duplicate of Register Digit DIN-355 listed above | Data interface correction | Supporting Docs | Interface Catalogue | Lis
MHHS-DIN-387 |  | DI-180 | 2023-06-09 | St Clements | 5269 | Madison Layton | Software Provider | Uplift metered indicator requirements | There are elements in the requirements that suggest that metered indicator would trigger a change to Market Segment. E.g. MHHSP-BP011-Change of ConType andor Mkt Segment-v5.1 Step 102 MHHSP-BPD011 - Change of Con Type or Market Segment v5.0 Step 102 Which states if there is a change to market segment RS would need to re-evaluate the market segment And MHHS-BR-RS-124 which include in brackets: Change of Connection Type (Change of Unmetered Indicator) MPRS will assess Market Segment against the ISD entity M7 which does not include Metered Indicator. Therefore a change in Metered Indicator in isolation of any other changes to data items in the M7 table/Related MPANs/Linked MPANs, will not trigger a change to Market Segment. As it will not trigger a change MPRS will not re-evaluate Market Segment base on a Metered Indicator change alone. The requirements need uplifting to reflect. |  | Closed | [7 empty] | Closed as discussed and agreed with SCS. | No Change
MHHS-DIN-388 |  |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | IF-036 Custom Routing Rules | Following discussions with SCS agreed that for reasons of complexity it would be better to adopt Primary rather than secondary routing to IF-036. New Requirement created for REGS to undertake the Primary Routing of IF-036. |  | Closed | [7 empty] | Ref DIN-507
MHHS-DIN-389 |  |  | 2023-06-07 | Design Team |  | Sean Cooper | SRO Design | Appointment Start Times | Do we need a formal validation Rule to check that Appointment Start times are referenced as Midnight Local ? Issue raised numerous times with SCS. Waiting for SCS to confirm their position. |  | Closed | [7 empty] | CLOSED - DUPLICATE OF DIN-207 ABOVE
MHHS-DIN-390 |  |  | 2023-06-13 | Siemens | 5534 | Tony Mason | Metering Service Provider | IF/PUB-018 | There appears an inconsistency in the Business Process Map, BP010, and the routing rules for the IF-018 where the Event Code = DUOSTariffIDChg. This information is confirmed to SPs on the IF/PUB-036 and would then be updated where there is a change on the 018 according to the Secondary Routing Rules. This notification is absent on the process diagram. Could you confirm the position and update the documentation accordingly? |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Update BP010B to show Data Service and Metering Service receiving PUB-018 for DUoS Tariff ID updates in line with the routing rules in DES-138. Update BPD010 process description to includes steps to recieve PUB-018 for Data Service and Metering Service. | Process Model correction | Meter to Bank | Change of Registration Data | MHHSP-BP010-Change of Registration Data MHHSP-BPD010
MHHS-DIN-391 |  | DI-182 | 2023-06-13 | St Clements | 5304 | Madison Layton | Software Provider | IF-019 validation gap on principal and subsidiary MPAN | IF-019 is missing validation rules to ensure an MPAN is only listed once in the IF-019, need rules to ensure the sender cannot repeat same Subsidiary MPAN twice in the repeating B090 block, and cannot list the same MPAN as both Principal and Subsidiary in the same IF-019 message |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Created x2 new rules to prevent duplicate MPANS within repeating B90 groups within a single message. Error Code REG1059 created to support validation checks | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-392 |  |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Consent Fields | Raised by SCS. B068/DI-017/DI-018 - This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block B068 updated to be "must be provided" for smart meters. Data items set to mandatory non-nullable. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | Block text updated to show mandatory if smart meter present, and DI-017/D-018 updated to be mandatory non-nullable (applies to IF-026 only) | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-393 |  | DI-181 | 2023-06-13 | St Clements | 5274 | Madison Layton | Software Provider | De-appointment and re-appointment date order | MHHS-BR-RS-128.4 & MHHS-BR-RS-128.5 covers the requirement for MPRS to ensure MS/DS are aligned across Related/Linked MPANS, and where they are not to de-appoint the MS/DS and appoint the correct MS/DS. The de-appointment requirement specifies to set MS/DS ETD to D+1 and the appointment to set the MS/DS EFD to D+2. Why do we need to apply the de-appointment and re-appointment in the future? Would we not be better to use the previous day (D-1) for the de-appointment MS/DS ETD and the current day (D) for the appointment EFD? |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Discussed with SCS and agreed to update Registration Service requirements to De-appoint on D (MHHS-BR-RS-128.4) and appoint on D+1 (MHHS-BR-RS-128.5) as part of auto-alignment process | Requirement correction | Registration | Auto-alignment | BRS003
MHHS-DIN-394 |  |  | 2023-06-13 | St Clements |  | Sean Cooper | SRO Design | Annual Consumption Fields | Raised by SCS. B059/B027/DI-0148 This block had not undergone the same treatment as other blocks wrt to the Nullable fields update. Block updated to be "must be provided" if available, however data items now need to be set to mandatory non-nullable. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | DI-0148 updated to be mandatory no-nulls and data type updated to DT-016 in Data Catalogue. Data Type corrected to DT-016 in IF-002 and IF-036. | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-395 |  |  | 2023-06-13 | St Clements | 5510 | Vicki Holland | Software Provider | Obfuscation of Connection Type Indicator in IF-021 | The DES138 interface catalogue specifies that the data item Connection Type Indicator will be obfuscated for all parties as it is required for routing only. Can this please be changed so that it is visible? The reason for this request is that suppliers often process data differently for the different connection types and therefore its important that they can internally validate or route data according to the connection type of the MPAN. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Obfuscation of connection type removed from IF-021/IF-013 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-396 |  | DI-183 | 2023-06-13 | St Clements | 5305 | Madison Layton | Software Provider | Update IF-019 REG1001 to only apply to Create and Add event codes | IF-019 REG1001 rule applies to all event codes. The MPAN could be disconnected with linkages still in place. If REG1001 is applied on remove event codes, then there will be not means by which the Supplier/DNO can remove the linkage after a disconnection. Suggest REG1001 rule should only apply to the Create and Add event codes. This would be consistent with the existing validation on the DB05 and D0386. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | IF-019 MPAN Status Validation Rule removed for all "Remove MPAN" Event Codes. i.e. I can still perform remove MPAN from group task if MPAN is disconnected. SCS rejected option of auto de-linkage as part of De-Registration Process. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-397 |  | DI-184 | 2023-06-13 | St Clements | 5306 | Madison Layton | Software Provider | IF-019: REG0007 to only apply to Related event codes and not to Linked Import Export event codes | REG0007 on IF-019 interface is currently written to apply to both Related and Linked MPANs. The intention of this existing rule on D0386 is because Related MPANs switch together, and so changing the relationship during a switch can create a split supply relationship. However Linked MPANs do not switch together and so this is not currently applied to the existing DB05 validation rules. Suggest REG0007 only apply to Related event codes and not to Linked Import Export event codes? |  | Closed | [7 empty] | Following discussions with SCS it has been agreed to prevent all changes to MPAN Linkages whilst an Active Switch is in progress. This is the safest approach when considering both CSS and Auto Alighment functionality considerations. No change to existing Design Documentation required.
MHHS-DIN-398 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD Stores LLF data | Can we have an ISD entity ID for LLF data. This would be required for the API used to retrive the data from ISD data store. Are you happy for us to create and put it in the Guidance note. |  | Closed
MHHS-DIN-399 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD publishes full data to Elexon Central Systems | Requirement should be reworded to be "ISD must make available the data sets required by LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. ISD must make available the entire current data set to LSS, MDS and VAS. This includes the Master Settlement Timetable to all 3 services and LLF data to MDS. |  | Closed | [7 empty] | Agreed in a session with Elexon 26/07 that the requirements document will not be changed as the requirement has already been fufilled by Elexon in line with the current requirement.
MHHS-DIN-400 |  |  | 2023-06-14 | SRO Design Team | N/A | Sean Cooper | SEO Design | REGS Validation Rule Clarification | REG1089 conditions updated to provide more clarity. Existing wording refered only to a Subsequent App - this is now better defined as an Appointment with a prior/earlier Sender Timestamp. No functional change. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | For IF-031 Validation rule text updated to specifically reference Sender TimeStamps so as to provide more clarity on the nature of the val rule/when generated | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-401 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | IHD/SMSO Fields | IHD Install Status and IHD Status Effective from Date fields should be optional (i.e. nullable) when providing an IHD update in IF-025/IF-026. SMSO and SMSO Effective from Date fields should be optional (i.e. nullable) when providing an SMSO update in IF-025/IF-026. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | DI-137/ DI-136 in block B030 updated to Optional (O) in IF-025 and IF-026 DI-134/ DI-135 in block B031 updated to Optional (O) in IF-025 and IF-026 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-402 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Import/Export Fields | Linked Import/Export MPAN and Linked MPAN Energy Direction will always be provided so should not be nullable |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | DI-038 updated to Mandatory No nulls and Data Type updated to DT-002 DI-151 updated to Mandatory No nulls On the 01-Data Catalogue | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-403 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Meter Manufacturer Field | Meter Manufacturer is optional (ie nullable) when provided in IF-002, IF-006, IF-033, IF-036 as in IF-005 |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | DI-048 updated to Optional (O) in IF-002, IF-006, IF-033, IF-036 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-404 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Proposed Appointment Response Code Field | For Response code A there may not be any text to populate for DI-143 |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | DI-143 updated to conditional (C) based on DI-979 = L or R in block B007 in IF-034 and IF-035 | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-405 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Response Message Field | For Response code A no text to populate for DI-980 |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | DI-980 updated to conditional (C) based on DI-979 = R in block R0 in 02-DIP Common Block tab | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-406 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | Sender DIP ID Field | Sender DIP ID should always be provided in S1 Common Block |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | DI-997 updated to mandatory (M) in block S1 in 02- DIP - Common Block tab | Data interface correction | Supporting Docs |  | MHHS-DES138-InterfaceSpecfiication
MHHS-DIN-407 |  |  | 2023-06-14 | St Clements |  | Mike Fensome | SRO Design | COS During SEG Issue | Discuss with SCS the option of allowing non-appointed MS to update MTDs even if App has lapsed due to COS activity. If not then need to update process map to call out need for manual exchange of MTDs as Work MS could never submit if IF005 |  | Closed | [7 empty] | Closed, SCS unable to support alternative solution. Design Team have reviewed the existing process map note and believe this already provides enough information for participants. | No Change
MHHS-DIN-408 |  |  | 2023-06-13 | Elexon | 4505 | Sedef Kiris | Central Body | ISD is the master for data contained both within ISD and MDD during Transition | The requirement is a bit ambiguous as could be read as all ISD and all MDD rather than just ISD data + overlapping MDD data. We don't want to be the master for MDD only data |  | Closed
MHHS-DIN-409 |  |  | 2023-06-14 | St Clements | 5510 | Vicki Holland | Software Provider | ISD Entity M5 – Consumption Component Classes | EDI021 ISD entities document shows that the settlement period quality indicator in entity M5 is a comma separated list of possible values. This will be difficult to use in systems that need to refer to this data. Could this instead show Actual or Estimate? Alternatively could this be split into parent and child entities to avoid a comma separated list? Metering Service ID MPID is incorrect and must be changed to {MS Id} also in ISD Entity M8 |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Amendments relating to “Valid Settlement Period Quality Indicator Set” wording and field length in section M5 of EDI021 ISD entities document. Change also made from Metering Service ID MPID to Metering Service {MS Id} in Entitiy M8. An objection was raised against this DIN. Following discussion at the DRG about this DIN it has now been moved to Interim Release 5. A decision was made at DRG to go with OPTION 2: Change Existing Layout – Remove list element in favour of individual row(s) for each valid combination for the Valid Settlement Period Quality Indicator Set. Option 2 changes have been implemented to section M5 of EDI021 ISD Entities. Following the change to the layout the amendments to the data item will revert back to its initial name of Settlement Period Quality Indicator. and a data type length of 5 characters | EDI021 ISD Entities | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-410 |  | DI-487 | 2023-06-14 | St Clements | 5542 | Virginia Patey | Software Provider | DI-487 definition incorrect for REP-002 on Swagger | DI-487 energised MPANs is defined as an Integer in the Interface Specification, yet is defined as a String in Swagger. |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | DI-487 updated in Swagger 1.2 to align with Interface specification for REP-002 | Data interface correction | Supporting Docs |  | Swagger 1.2
MHHS-DIN-411 |  | Migration | 2023-06-14 | ESG | 4810 | Patricia Parker | Software Provider | Migration Segment Categorisation | The Migration Design currently specifies that Market Segment needs to be recorded before the Migration phase. This should be changed so that it is no longer required. Until an MPAN is migrated, there is no way of maintaining the market segment between the RS and EES using the legacy interface between these two services. However, meter type and connection type will be available in both the EES and the RS, so Suppliers can use a combination of these values to derive the correct market segment. |  | Closed | [7 empty] | 03/08: SCS confirmed in a session with SC that they agreed that Segment is a derived value based on Connection Type and MTR. There are validation rules that prevent the migration if Connection Type (and therefore segment) is not already defined in REGS. To address the original question Segment will always be known at the point of migration. Therefore, no changes are required to Migration document. 13/07: John Wiggins to have offline discussion with Sean C as DIN requires wider discussion at DRG to progress SRO Team disagree with this Migration Request. Market Segment must be known prior to the selection of MHHS Service Providers. Market Segment is a derived field based on Connection Type and Meter Type. Connection Type must be set before Migration / Meter Type already known so Market Segement CAN be derived, set and maintained prior to MPAN migration. No change to baseline documentation Required.
MHHS-DIN-412 |  |  | 2023-06-14 | MHHS | 5022 | John Wiggins | Central Body | Update to MDD | Migration request to ensure that Elexon add MHHS as a value to MDD. Page 35 of the Design Document under Reverse Migration states that -A default MPID of ‘MHHS’ will be created for the DC, MOP, DA appointments. Will MHHS be contained within MDD as a valid set as there is no reference in the document to update MDD with this value. |  | Closed | No |  | Design gap | TBC |  |  |  | As the Migration documentation was approved via DAG and following discusion with RecCo and BSC the updates are being documented in. This is being picked up in an update to DES196 Dflow interface |  |  |  | DES196
MHHS-DIN-413 |  | Migration | 2023-06-14 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | Reading Type (J0171) will be updated with three new values: Forward Migration CoA Forward Migration CoS Reverse Migration CoS Reading Type (J0171) will no longer use Initial or Final for migration reads between Suppliers or DC/DS but one of the above new codes will be used. Meter Reading Reason Code (J0332) will no longer be used to identify migration reads, all reference to this will be amended to Reading Type (J0171) in the guidance document. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | This DIN replaces DIN-442. Introduction of a new worksheet called 'Migration Change' reflecting the D-Flows changes supporting migration. Reading Type (J0171) has three new Reading Type values as follows: V - Forward Migration CoA X - Forward Migration CoS Y - Reverse Migration CoS For the other part of the DIN, "Reading Type (J0171) will no longer use Initial or Final for migration reads between Suppliers or DC/DS but one of the above new codes will be used." - This already exists in the Migration documentation therefore no change on this. | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-414 |  |  | 2023-06-14 | British Gas |  | Mohammad Amin Fuggawala | Supplier | D0275 in D-Flow Document | Ref Previous DIN-244. In the "DES196 D-Flow Document" the D0275 is showing as redundant. This is misleading it should be marked as by agreement between contracting Supplier-DS. Document should be updated to reflect this. |  | Closed | [7 empty] | Centrica have been notified on closure of DIN. Update was delivered in the published V1.0 of DES-196 as part of July DAG and the updated version is available on the Collaboration Base. | No Change
MHHS-DIN-415 | RT |  | 2023-06-14 | Elexon | 5702 | Mike Ceney | Central Body | Routing IF-026 to LSS | IF_026- For Routing Rules it states for Event Code/Conditions [SSC], [ProfileClass] and [SSCandProfileClass] that this should be routed to MDS, is this incorrect as MDS does not use these items in any calculations or outputs, this should state LSS |  | Implemented | [5 empty] | Interim Release 2 | 2023-06-23 | IF-026 [SSC] and [ProfileClass] have been removed as of Interim Release 1. Update DES138 IF-026 to route to LSS on event [SSCandProfileClassChange] | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-416 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-001 New App Scenario Code MCS (Migration Change of Supplier) | Create new Appointment Scenario Code of MCS |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | IF -031 New valued added to DI-800 data catalogue and Swagger 1.3 updated to reflect new value | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-417 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-002 Validation Rules for Scenario MCS (Migration Change of Supplier) | New Val rule to check MCS is only used for legacy non-migrated MPAN where Supplier is not current supplier (and not in past) |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-418 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-003 New App Scenario Code MCA (Migration Change of Agent [Service Provider]) | Create new Appointment Scenario Code of MCA |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | IF-031 New valued added to DI-800 data catalogue and Swagger 1.3 updated to reflect new value | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-419 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-004 Validation Rules for Scenario MCA (Migration Change of Agent [Service Provider]) | New Val rule to check MCA is only used for legacy non-migrated MPAN where Supplier is current supplier and now active Switch is in progress (and not in past) |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-420 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-005 - IF-31 Check valid MHHS Supplier | If MCS/MCA code used is Supplier a valid MHHS Approved/Registered Supplier |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-421 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-006 - Prevent use of Migration Scenario IDs | IF MCS/MCA code used for already migrated mpan - reject appointment for invalid Scenario code(s) |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | New Validation Rule added to IF-031 with supporting Error Code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-422 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-007 Connection Type/Segment not yet Populated | New error required if Connection Type, DUos Tariff ID or Segment is not set prior to migration. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | New Validation Rule created for IF-031 to check that MHHS Standing Data is present and aligned. REG0011 Error created to support this validation Rule. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-423 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-008 Auto Realign Functionality | New REGS Requirement - Only action the auto-realign functionality on MPANs where both Linked MPANs are in a Migrated state. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | New Req RS-146 added to REGS Requirements Document to ensure that Auto-Align functionality is only executed if all MPANs in a related and/or linked group have sucessfully migrated to MHHS Operation. | Requirement correction | Meter to Bank | Requirements Documents | BRS-003-Registration Service Requirements
MHHS-DIN-424 |  | DI-185 | 2023-06-16 | St Clements | 5335 | Madison Layton | Software Provider | MPRS access to correlation ID | IF-019 is sent to the LDSO for LinkedImportExport event codes, if the LDSO approves the request they will submit an existing DB05 flow into MPRS. If the DB05 is accepted by MPRS, it will send an IF-020 to the Supplier to confirm the change to Linked Import Export association. However MPRS would not have access to the correlation ID that was received by the LDSO on the IF-019, and so would use a new correlation ID on the IF-020. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | IF20/IF19 Note amended explaining that it will not be possible to Link IF-019/IF020 messages together using Correlation ID , in the case of Linked MPANs. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-425 | SC | Migration | 2023-06-19 | ESG | 5215 | Patricia Parker | Software Provider | Migration Meter Reading | 8.1.3 step 12 Migration Design Document : Validation Status (J0022) references will be updated to Meter Reading Flag (J0045) |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | 8.1.3 step 12 Migration Design Document : Validation Status (J0022) references will be updated to Meter Reading Flag to T or F (J0045) | Design Ambiguous | Supporting Docs | Interfaces | Migration Design Document
MHHS-DIN-426 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG-009 New Rejection Code for D0205/D0203 | Response to a D205 is a D0203. 1. A New Rejection Condition/Code is required where D0205 is received following processing of IF-031. 2. Proposed new D0203rejection code is 62 "MHHS Fwd Migration in Progress or Completed" |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Point 1 already exists in the Migration documentation therefore no change on this. Point 2 is satisfied by updates in DES-196. Introduction of a new worksheet called 'Migration Change' reflecting D-Flows supporting migration. (J0107) Rejection Reason Code 62 added with the following details "MHHS Fwd Migration in Progress or Completed" | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-427 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-010 ISD Change M16 | No change Required - SCS can use ISD M16 - which contains MIPD/DIP Role and Effctive From date. This can be used to determine if a Supplier is MHHS qualified. This is better apporach that adding a transiant "Qualified Yes/No" field to this table. Therefore NO changes to documentation required. |  | Closed
MHHS-DIN-428 |  |  | 2023-06-19 | British Gas | 5835 | Neil Strange | Supplier | MEX before SSD scenario | When a CoS is in progress and there is a MEX before SSD, how will new supplier get the MEX details As the incoming supplier has already received the IF36 - would there be a new IF36 or would it be a PUB006? In addition how would the new MS and DS be made aware of this? - the old MS has X days after the job is completed to update the industry and a CoS could have happened before the old MS can update the other participants. |  | Closed | [7 empty] | BAU Design deals with 'regular' MEX before COS type scenarios (note previous MS Update Period - PUB-006 would be issued to impacted parties). Complexity arises where there is a COS overlapiing with Change of Segment/Connection Type (ie SEG Appointment)... Following discussion with SCS - low probably, low occurance vs. complex change. Ref existing guidance on BP016 there would need to be a manual interaction between Supplier and MS. No Change to existing Documentation Required.
MHHS-DIN-429 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG-011 Changes to D0170 | 1. Change D0170 flow so that MPRS/Registration Service is valid Sender of this flow. 2. New value for "Request Action Code" is needed to denote a Migrating account and if its CoS or ChgOfSP method. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Introduction of a new worksheet called 'Migration Change' reflecting the D-Flows changes supporting migration added in DES-196. Point 1. D-Flow ID (D0170) Request for Metering System Related Details new Scenario Variant FROM Electricity Retail Data Agent TO Electricity Supplier added. Point 2. Introduce two new Requested Action Code values as follows: 24 - Migrated Metering Point (CoA) 25 - Migrated Metering Point (CoS) | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-430 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-12 New Val Rule for IF-019 | Reject any changes to Related MPANs where any MPAN referenced (or in realted group) is subject to an active Migration SP Appointment Process |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | New Validation Rules and Error Code created to prevent changes if MCA Appointment Type Exists (Note: prevention if MCS exists is realised through existing check on if Switch is in Progress) | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-431 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-13 Change to D0386 | Change D0386 validation to reject changes to related MPANs if any related MPAN in group is subject to active Migration SP Appointment Process |  | Closed | No |  | Design gap | TBC |  |  |  | Update Migration Design Document D0386 validation to reject changes to related MPANs if any related MPAN in group is subject to active Migration SP Appointment Process | Design Ambiguous | Supporting Docs | Interfaces | Migration Design Document
MHHS-DIN-432 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-014 Appointment on Secondary Related MPAN | Extend existing 1039 check to include MCS.MCA Appointment Scenarios. |  | Closed | [7 empty] | Existing Validation Rule(s) around REG1039 will already cover Migrating MPANs - No Documentation Change Required.
MHHS-DIN-433 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-015 Switch in Progress Mig Rejection | New IF-031 validation to reject MCA/MCS DS and MS Appointments if an [any] active Switch is in progress with NEW Rejection Reason Code (note 1095 code referenced in Migration document has already been used elsewhere) |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | New validation rules and REG9XXX Exception codes added to ensure correct usage of MCA/MCS Appointment Scenario Codes. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-434 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-016 New IF-003 | Previously DIN-247, Introduce IF-003, no changes from original proposal. 1. Update DES138 new tab, update IF List. Update New Data Items 2. Review E2E doc. 3. Update secondary Routing Rules (Avenade Techncal Doc) to include 4. Update Swagger |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Add data items DES138-Interface data Cat and to IF-003. Created new Data items: DI-500 MHHS Regime End Date, DI-501 Rev Migration Incoming MOP MPID, DI-502, Rev Migration Incoming MOP Eff From Date, DI-503, Rev Migration Incoming DC MPID DI-504 Rev Migration Incoming DC Eff From Date. Swagger v1.3 updated to reflect new IF-003, Blocks (B096/B095/B094) & Data Items (as above). | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-435 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG-017 D0304 & D0303 | 1. New D0304 Validation Rule 2. New D0304 Rejection Reason Code "Q - MPAN Fwd migration in progress or completed" 3. Change D0303 so as to make "Eff From Settlement Date REGI" a non mandatory data item within the flow (an alternative to suggesting that outgoing MS no longer issues a D303, only the incoming MS would send) |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Introduction of a new worksheet called 'Migration Change' reflecting the D-Flows changes supporting migration added in DES-196. Point 1 already exists in the Migration documentation therefore no change on this. Point 2 New Response Code Q "MPAN Fwd migration in progress or completed" added against J2255 MPAS D0304 Response Code as part of D0304. Point 3 Change requirement to populate this date from Mandatory to Optional against J0049 Effective from Settlement Date {REGI} as part of D0303. | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-436 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG0-018 D312 | 1. New D03012 Validation Rule 2. New Rejection Reason Code "AD - MPAN Fwd migration in progress or completed" |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Point 1 already exists in the Migration documentation therefore no change on this. Point 2 is satisfied by DES-196. Introduction of a new worksheet called 'Migration Change' reflecting D-Flows supporting migration. against J2256 MOP Flow Response Code as part of D0312 | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-437 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-019 IF-005 Validation Rule | 1. New val rule to prevent IF-005 while MCS/MCA Appointment is in progress 2. New Error Code (REG9003) |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | REG9003 - MHHS MTD Updates cannot be used until Migration has completed, Created and new validation rule added to IF-005 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-438 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-020 REGS Design Clarification | SCS Should issue L1/L2 Msg Status message with RCP1061 for any MPAN at the incorrect status where a DIP Message is received |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | This is a Migration Requirment which participants should take into account as part of their Migration Designs. However, for clarity a note has been added to RCP1061 entry in the Intoduction Section of the Interface Catalogue. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-439 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-021 No Supplier Updates during Rev MIgration (IF-025) | 1. New If-025 val rule to check if Rev Migration Switch is in progress 2. New error code |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | REG9002 - Supplier Data Items Cannot be Maintained for Reverse Migration Account, Created and applied to IF-025 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-440 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-022 No CDCs Updates during Rev MIgration (IF-038) | 1. New If-038 val rule to check if Rev Migration Switch is in progress 2. New error code |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | "REG9001 - CDC Marker Cannot be applied to Reverse Migration Account", created and applied to IF-038. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-441 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-023 No AC Updates during Rev MIgration (IF-040) | 1. New If-040 val rule to check if Rev Migration Switch is in progress 2. New error code |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Annual Consumption Method Statement section 5 has been updated with the text below in red: Where an MPAN is no longer active under MHHS during the transition phase the Market-wide Data Service shall not calculate or submit an annual consumption on the IF/PUB-040. | Method statement correction | Supporting Docs | Method Statement | METH010_Annual_Consumption
MHHS-DIN-442 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-024 D0010/D0086 New MR Reason Codes | Three new MR Reason Codes for use in D0010: Forward Migration COS / Forward Migration COA / Reverse Migration |  | Closed | [7 empty] | Original migration design. Superceded by DIN-413.
MHHS-DIN-443 | SC | Migration | 2023-06-12 | Design Team |  | Sean Cooper | Programme Design | MIG-025 D0155 New Agent App Reason Codes | 1. New Valid value for service reference "REVM" 2. New valid value for Service Level "REVM" |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | D-Flow Ref D0155 updated for data items J0274 service reference "REVM" and J0275 Service Level "REVM" in DES-196. | Design Ambiguous | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-444 | RS |  | 2023-06-19 | ESG |  | Patricia Parker | Software Provider | IF-01 Incoming supplier for Import/Export MPANs | Clarification required with SCS. If it is known that an alternative MPAN has the same SSD then we do not want the old supplier ID as the linked supplier on the IF-01, we want the new supplier to be populated |  | Closed | [7 empty] | Discussed with SCS and they have confirmed that where co-incidnet COS occurs they would look to populate the [new/incoming] Linked Supplier ID.... No change to documentation required.
MHHS-DIN-445 | SB |  | 2023-06-19 | Utiliteam |  | Richard Palmer | Software Provider | Spec of IF-024 in DES138 Interface Catalogue | The Population Notes for DI D-000 in Group S0 has ‘IF-025’. This error was in v5.0, and is still in v5.1.1 |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | The Population Notes for DI D-000 in Group S0 has been updated to ‘IF-024’ in IF-024. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-446 | SC | Migration | 2023-06-12 | SRO Design Team |  | Sean Cooper | SRO Design | MIG-026 Migration DIP Reporting Reqs | Reqs for x4 new Reports -- Flag at the next DIP DAG |  | Closed | No | [6 empty] | Closed and for the Migration Team to pick up. Awaiting further internal discussions re DIP Reporting Strategy.
MHHS-DIN-447 | SW |  | 2023-06-21 | Kraken | 5980 | Angelos Rizoyannis | Software Provider | Conditional Mandatory not applied in Swagger correctly | IF-041-CustomBlock: The field B065List is stated as optional in the comments, but the API schema does not reflect this. This field that is conditionally optional in DES-138, but this is not defined as such in Swagger ie, OneOf, AnyOf. This needs to be updated in Swagger to align correctly. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | In Swagger 1.3, updated IF-041-CustomBlock: The field B065List and B064List will be either / or as they are defined as conditionally mandatory in DES-138. This uses AnyOf notation in Swagger. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-448 | SW |  | 2023-06-21 | Kraken | 5980 | Angelos Rizoyannis | Software Provider | Mandatory fields not applied correctly in S1 block | S1 Common Block: The 'properties' and 'required' sections of the API schema for the S1 common block have conflicting information. The 'properties' section includes fields like senderTimestamp and senderRoleID, while the 'required' section lists sentTimestamp and senderRole. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Updated Swagger 1.3 to align properties and required sections so that fields are called senderTimestamp and senderRoleID. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-449 | SC |  | 2023-06-21 | SRO Design Team |  | Sean Cooper | SRO Design | Change to IF-037 | Include Block B002 into IF037 so that outgoing MS is aware of incoming Supplier on a COS. This will allow the SP to populate the D0303 to MAP. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Block 002 added to IF-037 for use where event code is MSDeapp, this is so that the outgoing MS is informed of who the incoming supplier is so that D303 can be correctly population. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-450 | SC | DI-196 | 2023-06-22 | RECCO |  | Sean Cooper | SRO Design | Change to IF-005 Validation Rules | Change made to IF-005 validation Rules to allow previous MS to update Meter Location only - during the 10 day post appointment period. This will allow for scenarios where there has been relocation only activity immediatly prior to a change in MS. All other MeterUpdate functions apart from Change of Meter Location shall be rejected per wider agreement that only active MS should have the ability to change the characteristics... This change originated from R1 Comments feedback from RECCO |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | IF-005 Validation rules updated to include new "REG0008 - Amendment Requested cannot be undertaken by Previous Metering Service" error condition and code. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-451 | SC | CR-018 | 2023-06-22 | Design Team |  | Sean Cooper | SRO Design | CR - 018 Registration Service OOH Ops | CR18 looks to specify Registration Service Out-Of-Hours Operations. | CR018 | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Following feedback provided on the redlined version of the Operational Choreography, and following discussion on CR018 at PSG, the SRO maintained the DAG Chair’s decision to approve the implementation of CR018. CR Contents incorporated into a new Section 7 of Ops Choreography Document. Updates to clarify low level processing details in Section 7 Out-Of-Hours Processes table. Following feedback from DNO Review - Additional updates to replace the term ‘SLA’ with the phrase “target response time(s)”. Changes to Column headings to ‘When’ across the Operational Choreography document to align with Code Drafting convention. Addition of Intro text and removal of text “or Performance Regime” in Section 5. | Technical corrrection | Supporting Docs | Operational Choreography | MHHSP_OPC001_Operational_Choreography
MHHS-DIN-452 | SC |  | 2023-06-22 | St Clements |  | Sean Cooper | SRO Design | Refine Consent Checking Rules on IF-031 | Further refine Consent checking rules so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing . Updates to IF-031 validation rules to reflect this change. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | IF-031 validation rules updated per the DIN Details. Consent checking rules added so that SEG appointments are NOT validated as part of IF-031 but are checked as part of Queue Processing. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-453 | MF | DI-124 | 2023-06-22 | St Clements |  | Mike Fensome | SRO Design | Issuing of IF-020's | Highlighted that LDSO's could issue an IF-020 with details of import/export linkages without having received notification from the Supplier |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Added note to IF-019 and IF-020 to inform Suppliers that Import/Export linkages could be received via PUB-020 unprompted by the Supplier issuing IF-019. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-454 | SC |  | 2023-06-26 | St Clements |  | Sean Cooper | SRO Design | Update to ISD M7 | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Added 'placeholder' row in this table for 'Unmetered' so as to support various validation processes to be undertaken by the Registration Service. added rule to support REG0011 logic in IF-031. | Requirement correction | Supporting Docs | ISD Document | MHHSP-DES138-Interface Catalogue MHHSP-EDI021-ISD Entities
MHHS-DIN-455 | SC |  | 2023-06-23 | St Clements |  | Sean Cooper | SRO Design | Update Op Choreography (Event Move from IF-013 to IF-014) | Update Ops Choreography to take account of the movement of event [ConsumptionOnDeEnergisedMPAN] which was moved from IF-013 to IF-014 (DIN-255). |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | IF-014 Deadline split into two. First [ActivePowerRejected] remains UNCHANGED. Deadline for [ConsumptionOnDeEnergisedMPAN] is also UNCHANGED but moved from IF-013 row into IF-014 Row, to mirror the change delivered by (DIN-255). OPC_580 ID details updated in OPC001 Operational Choreography document. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue MHHSP_OPC001_Operational_Choreography
MHHS-DIN-456 | SC |  | 2023-06-23 | St Clements |  | Sean Cooper | SRO Design | Swagger Correction - DI-844 | Corrected x2 invalid referenced to "AssignedMRDRequestEffectiveFromDate" should have been "AssignedMRDEffectiveFromDate" in Block 066 |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Corrected x2 invalid referenced to "AssignedMRDRequestEffectiveFromDate" should have been "AssignedMRDEffectiveFromDate" in Block 066 | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-457 | SC |  | 2023-06-23 | St Clements |  | Sean Cooper | SRO Design | Change to DTN Validation of D0350 | Implement DTN Validation of D0350 to prevent future dates |  | Implemented | No |  | Design gap | TBC |  | Interim Release 8 | 2024-03-20 | CP Required for further clarification | Data interface correction | Supporting Docs | Interfaces | DES196 D-Flow and interface mapping
MHHS-DIN-458 | SC |  | 2023-06-23 | St Clements |  | Sean Cooper | SR Design | New IF-019 Related MPAN Validation Rule | New Validation Rule required for IF-019 to ensure that only Import MPANs can be related. Add to Create and Add Related - this is per REC Shedulle 28 |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | New Rules added to IF-019, [RelatedAdd] and [Related Create] events to ensure only Import MPANs can be in a related Group. New Error code added to support these new rules REG1067 - Only Import MPANs can become Related | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-459 | SB |  | 2023-06-23 | Utiliteam | 5724 | Richard Palmer | Software Provider | Spec of IF-024 in DEL138 Interface Catalogue | A further suggestion re the Interface Spec for the IF-024: The Event Code list in DI D-999 in Group S0 contains [SN-RemoteEnabled] & [SN-RemoteDisabled]. I would suggest that these are invalid for Segments Advanced and Unmetered. Also [SN-Vacant] would appear to be irrelevant for Segment Unmetered, and I doubt that [SN-NoComms] would be valid either. These existed in v5.0, and are still in v5.1.1. Perhaps the routing rules need some improvement? |  | Closed | [7 empty] | No change Required. Useage of these evernt codes is obvious and is described in the Requirments documents as necessary
MHHS-DIN-460 | SB |  | 2023-06-26 | Utiliteam | 5939 | Richard Palmer | Software Provider | PIF-019 structure & Principle -> Principal | Also, in the relationships between MPANs, the ‘main’ one is the ‘Principal’ one – not the ‘Principle’. This will be embarrassing if left uncorrected. It is still in v5.1.2 in IF-019, and it is in many other places. If there is a chance of correction, please take it. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Spelling mistake corrected in Data Catalogue, IF-019, IF-020. Note YAML name also corrected for DI-073. | Data interface correction | Supporting Docs | Interface Changes | MHHSP-DES138-Interface Catalogue Swagger 1.3
MHHS-DIN-461 | SW |  | 2023-06-26 | Greenbird | 1768 | Fredrik Omland | Software Provider | Misalignment between DES-138 and Swagger for DIP Connection Provider ID | In DES-138, In the S1 block, DI-996 (Connection Provider DIP ID) is defined as Optional. But in Swagger, this is defined as mandatory. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Updated Swagger 1.3 so DI-996 in S1 block (Connection Provider DIP ID) is Optional to align with DES-138 | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-462 | SW |  | 2023-06-27 | Design Team |  | Steve Weston | SI Design | Schema Optionality incorrectly defined for some Interfaces | In DES-138, there are are a number of Interfaces where the Schema Optionality is defined as Optional, rather than Mandatory. The list of Interfaces are as follows - IF-050 / B022, IF-023 / B053 and IF-013 / B049 |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Updated Schema optionality in DES138 to show that all data items must be present where the block is present in line with updated E2E Solution Architecture for IF-050 / B022, IF-023 / B053 and IF-013 / B049. | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalouge
MHHS-DIN-463 | SW |  | 2023-06-27 | SIMS |  | Kyle Abraham | Software Provider | No ability de-register from receiving Status messages in Swagger | In Swagger, there is a POST method for /statusmessage/config, but there is no DELETE method, so you are unable to delete / de-register for any status messages. Need to update Swagger to ensure this is possible. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Updates made to Swagger 1.3, so there is a DELETE method for /statusmessage/config, so you are now able to delete / de-register for any status messages. Updated so that all of the Interfaces accept the same 4 security headers required for message signature and validation. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-464 | SW |  | 2023-06-27 | SIMS |  | Kyle Abraham | Software Provider | Clarity required on values expected for /dip-channel/{id} for submitEvents on Swagger | The {id} in /dip-channel/{id} for submitEvents on Swagger should accepts values that are the same as the enumeration in DI-000 to ensure consistency. At the moment, this is not clear in Swagger or E2E001 design, so this needs to be updated to make this clearer. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Updates made to Swagger 1.3, so there the correct enumerations / values are available to align with values in DI-000 to ensure consistency and avoid any ambiguity between interfaces and reports. Updated to remove PublicationConfig and RestConfig in favour of a single config WebhookConfig. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.3
MHHS-DIN-465 | SC |  | 2023-06-28 | RECCO |  | Sean Cooper | SRO Design | Update to BP010 - Related MPANs | The process MPAN for Related MPANs does not clear call out the Rejection pathway. Update Business Process to show rejection process. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | BP010B Related MPANs Process updated to show specific Rejection Route. | Process Model correction | Metering Changes | Business Process Documentation | BP010- Changes to MPAN Data
MHHS-DIN-466 | SC | DI-188 | 2023-07-29 | St Clements |  | Sean Cooper | SRO Design | Change of MPAN Status during Service Provider Appointment Process. | How should a change of MPAN Status be dealt with whilst there is an ongoing SP Appointment that has not yet reached the stage of IF-034 processing !? If an MPAN is disconnected between PUB-031 acceptance and receipt of PUB-034, the SP PUB-034 Response would be rejected by MPRS due to validation rule REG1001. The appointment would not be progressed but would be stuck in the MPRS queue at status Requested. Could resolve by amending REG1001 validation on IF-034, to not apply to event codes MSAppSPResponse or DSAppSPResponse. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Resolved following discussion with SCS, Agreed that SCS will take no action until the IF-034 has been processes. A change to REG1001 validation on IF-034, to not apply to event codes MSAppSPResponse or DSAppSPResponse, is required to allow the IF-034 to processes normally (when where MPAN is disconnected)... Following processing of the IF-034 RESG will then immediatly issue an IF-035 with reason code of "1- Lapsed as MPAN Status is Disconnected" ... ... Agreed that this was best resolution both for REGS processing rules and participants as no change to currently expected message patterns/ordering. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-467 | SC |  | 2023-07-29 | ESG |  | Sean Cooper | SRO Design | Review of IF-035/IF036 Data Item Obfuscation | Review of IF-035/IF-036 Data Item Obfuscation |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Various updates to obfuscation on IF-036 to align with IF-035. DI-019/DI-800/DI-809/DI-207 obfuscated for Data Service DI-020/Di-800/DI-126/DI-842/DI-209/Di-844/DI-811/DI-208 /DI-018 obfuscated for Metering Service | Data interface correction | Supporting Docs | Interface Catalogue | MHHS-DES138-Interfaces
MHHS-DIN-468 | SC |  | 2023-07-29 | Helix |  | Sean Cooper | SRO Design | Routing of IF-020 | Helix have confirmed that they DO NOT need to receive Related/Linked MPAN information therefore an update is required to REMOVE MDS from the receipient list for this IF-020 |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | IF-020 Routing table has been updated to REMOVE MDS as being a recipient of any IF-020 messages. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-469 | ME |  | 2023-06-30 | SRO Design Team | 2109 | Rob Golding | SRO Design | Removal of Z0 & Z1 data items in ERI011B - ECS Reports External | Z0 & Z1 data items to be removed from from the each of the MHHS reports within ERI011B - ECS Reports External as they are no longer in the common block |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Removed Z0 & Z1 data items from all MHHS reports in ECS external reporting artefact | Data interface correction | Minor | ECS Reports | ERI011B - ECS Reports External
MHHS-DIN-470 | SW |  | 2023-06-29 | Callisto | 1805 | Seth Chapman | Software Provider | Clarity on nullable fields | Section 4.2.2 in the E2E design provides information on Optional / nullable fields, but worked examples would provide further clarity for each of the data types / link to JSON specification. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Updated section 4.2.2 with worked examples for each data type to provide additional clarity. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-471 | MH |  | 2023-06-30 | Helix |  | Derek Weaving | Central Body | Update to REP-003 in ERI011B - ECS Reports External | R019 parent should be R017 in the ECS Reports External and Swagger |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Updated R019 parent to R017 for REP-003 in ERI011B - ECS Reports External. Swagger v1.3 updated to align with changes within ECS reports artefact. | Data interface correction | Minor | Interface Changes | ERI021 -ECS Reports External Swagger 1.3
MHHS-DIN-472 | SW |  | 2023-06-29 | SRO Design Team | 2006 | Rob Golding | SRO Design | Onboarding migration from Test to Production. | “The programme is to implement a strong PKI policy but as per the diagram states that that on promotion, parties will be able to copy their Test setup and to use that for connecting to the Prod environment. - steps 1-8 - There are no steps in this sequence that test the connectivity to the Live DIP environment. To this point the only connectivity testing has been to the Test environments. This is a significant failure point / risk. At this point Webhooks and certificates will change (mTLS and JSON signing) from those used in Test as well as potentially some of the PKI resources assigned to roles ( those used in test may not be applicable to Prod) we would expect that this would require a new Connectivity proving period with the Prod environment similar to that being developed for CIT. Without such proving, how can the programme assume all parties will connect to the Prod environment successfully and ensure minimal impact to migration events”. |  | Closed | [7 empty] | Solution yet to be defined This an Elexon/DIP Manager deliverable not a programme deliverable
MHHS-DIN-473 | SB |  | 2023-06-30 | MHHS | 2111 | Jason Brogden | Network Operator | Definition of Network Operations | Issue: There is a lack of clarity in the scope of Network Operations activities in testing. Action to Resolve: Add a definition to the Programme Glossary that makes clear the scope of Network Operations (as referenced in Testing material) is equivalent to the scope of LDSO activities in the MHHS Design Baseline: Network Operations systems and services are those that are required to deliver the elements of the MHHS Design Baseline that are allocated to the LDSO role. Communicate this to the DNO and iDNO community and associated service and software providers. For the DIN Log, we can then focus on updates to the BRS to give the necessary clarity on the scope of MHHS Design. Issue: There is a lack of clarity in the scope of LDSO activities in the MHHS Design Baseline as BRS005 implies MHHS-related processing requirements at LDSOs for received DIP messages, whereas the BPs and BPDs define the scope of MHHS as ending at the receipt of DIP messages. BRS005 is described as “For Guidance Only” at the top and this is to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing). Action to Resolve: For the avoidance of doubt and to provide clarity to BRS005, it is proposed to change the “For Guidance Only” note at the top of BRS005 to the following description as per the above: BRS005 is provided For Guidance Only to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing). |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | LDSO Requirements document updated with the following text, "BRS005 is provided For Guidance Only to reflect that it was derived to aid LDSO participants in their understanding of the MHHS design, to help LDSOs navigate where there are requirements set out in various Design Artefacts and to help LDSOs understand how they might use MHHS data received in DIP messages (e.g. use for DUoS billing as required). It is not intended to introduce new requirements for processing DIP messages received at LDSOs (e.g. maintaining records) that are not covered by other Design Artefacts and are already covered in existing non-MHHS Code requirements (e.g. DCUSA). This is consistent with the current scope of the BSC (e.g. generation, sending and receipt of the D0030 but not onward processing)." | Requirement correction | Minor | Business Requirements Documentation | BRS-005 LDSO Overview.xls
MHHS-DIN-474 | ME |  | 2023-07-03 | MHHS |  | Kevin Spencer | SRO Design | Creation of new ECS data items and blocks across multiple reports and/or data catalogue | Report definitions incorrect and require updates and new data items following internal review |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Addition of data items DI-503, DI-505-DI-515 to data catalogue and across ECS reports artefact. MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal Missing data items added to data catalogue Di-403/DI-404/DI-514/DI-515 | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-475 | ME |  | 2023-07-03 | MHHS |  | Kevin Spencer | SRO Design | Update to block names, data items and descriptions | Report definitions incorrect and require updates and new data items following internal review |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Update to block names, DTN references, data items, descriptions and reordering of data item blocks to exisiting reports in MHHSP - ERI011B - ECS Reports - External | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-476 | SW |  | 2023-07-03 | Greenbird | 2035 | Fredrik Omland | Software Provider | Inconsistency between enum fields and nullable definition | Looking at DIP Interfaces Swagger 1.1 (also 1.2 + 1.3), the enum typed fields that are nullable may not comply with OpenAPI specification (for 3.0.x). The topic around enum fields with nullable: true has been clarified/answered by OAS project (amended in spec version 3.0.3 in 2021): (Reference: https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md ) |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | To align with Open API spec clarification at https://github.com/OAI/OpenAPI-Specification/blob/main/proposals/2019-10-31-Clarify-Nullable.md, we have updated all Data Types that are nullable and have an enum to align as follows: Following discussion, have decided to align with OpenAPI 3.1 DI-076-Estimation-Reason-Code: description : Used inconjunction with Settlement Period Quality Indicator to explain why data has been estimated type : string nullable: true maxLength : 2 example : '1' enum: - '1' # OptOut - '2' # Missing .. - '8' # Disconnected - '9' # Consumption Amendment - '10' # NonSmart - null The Data Types affected / updated as follows: --- DI-039-Load-Shape-GSP-Group-ID --- DI-076-Estimation-Reason-Code --- DI-096-Site-Visit-Check-Code --- DI-126-Traditional-Fall-Back-Read-Frequency --- DI-137-IHD-Install-Status --- DI-150-Annual-Consumption-Quality-Indicator --- DI-166-Supplier-Consumption-Amendment-Reason-Code | Data interface correction | Minor | Interface Changes | Swagger 1.3
MHHS-DIN-477 | SW |  | 2023-07-03 | MHHS |  | Steve Weston | SRO Design | Swagger alignment to OpenAPI 3.1 specificiation | Align with Open API specification 3.1 to remove nullable :true and replace with type declaration ie, type:[string:”null”] | CR049 | Closed | No |  | Design ambiguous | DIP Users |  |  |  | Align with Open API specification 3.1 to remove nullable :true and replace with type declaration ie, type:[string:”null”] | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-478 | SW |  | 2023-07-03 | MHHS |  | Rob Golding | Central Body | IF-021 max number of days of consumption data | In the Release 2 version of DES138 a limit was introduced that asked Participants not to submit more than 150 Settlement Days’ worth of data in a single message. The value of 150 was proposed as this meant a single message would realistically be ~600KB in size. We’ve had some queries regarding this value, the proposal is to increase sizing from 150 to 194 day message and the size increases from 600KB to ~780KB for IF-021 message. ECS will need to validate the message contents. However, rather than letting a ‘large’ IF-021 message traversing though the DIP, the proposal is to limit the IF-021 on ingress to the DIP and a single request will have a limit of 1MB – this will be done at the API level. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Agreed to limit the number of MQ IDs per IF-021 submission to ONE only and limit settlement days to 200. Swagger has been updated to limit the number of MQIDs to 1. Swagger updated to limit the maximum number of Settlement Days to 200. DES138 also updated to aligned with the above changes for IF-021. | Data interface correction | Minor | DES138 and Swagger | DES-138 and Swagger 1.4
MHHS-DIN-479 | SC |  | 2023-07-03 | St Clements |  | Maddison | SCS | Change to Consent Notification on IF-036 | SCS have suggested that B068 should only be required for DSApp Events. |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | Block 068 on IF-036 amended to that it is only Mandatory for DSApp Events. | Data interface correction | Supporting Docs | Interface Change | DES138-InterfaceCatalogue
MHHS-DIN-480 | SC | DI-195 | 2023-07-03 | St Clements |  | Maddison | SCS | Reverse DIN-105 | SCS have confirmed that it is possible currently and should continue to be possible to manage MPAN Linkages whilst MPAN(s) are at Created Status. Therefore we have reversed the change implemented at part of DIN105 and now allow processing of IF-019 if mpan status = "Created" |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | SCS have confirmed that it is possible currently and should continue to be possible to manage MPAN Linkages whilst MPAN(s) are at Created Status. Therefore we have reversed the change implemented as part of DIN105 and now allow processing of IF-019 if mpan status = "Created" | Data interface correction | Supporting Docs | Interface Change | DES138-InterfaceCatalogue
MHHS-DIN-481 | SW |  | 2023-07-06 | Elexon | 2106 | Nigel Rees | Central Body | REP-003 inconsistency between DES-138 | We have a contradiction between the DT-023 and the swagger spec. As there is an example we will implement based on the example but it looks like the person who wrote the ECS report catalogue used the correct convention. e.g. on REP-003 we have DT-023 as NUM (16,6). If we follow the convention used in the DIP interface spec, this would translate to 1234567890123456.123456, however the swagger suggests 123456789.123456 Screenshot from REP003 in external ECS reporting catalogue https://app.swaggerhub.com/domains/MHHSPROGRAMME/DataTypes/1.3#/components/schemas/DT-023-Positive-Decimal-9-6 DT-023-Positive-Decimal-9-6: description: Number (9,6) format type: string pattern : ^[0-9]\d{8}(\.\d{6})?$ example: 123456789.123456 |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Two new data type references have been created DT-024 and DT-024N. For NUM(16,6) data type within ECS reports/ECS data catalogue replace DT-023/DT-023N with DT-024/DT-024N. DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. 31/08: A reconciliation exercise is being carried out internally of the ECS data catalogue to assess data types. Further work may be required to swagger following the reconciliation. Reconciliation task has been completed which has resulted in updates to the MHHS Data Types within the ECS Reports data catalogue. MHHS data type references in Swagger have also been updated to align with these changes. An example of how MHHS data types should be interpreted: String 17 should be interpreted as NUM(±9.6) which can be physically represented in this way for a negative number -123456789.123456 or for a positive number it will be 1234567890.123456. The objection has been removed. | Reporting correction | Minor | ECS Reports | "MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2" Swagger
MHHS-DIN-482 | KH |  | 2023-07-10 | C&C | 2394 | Hazel Cotman | Software Provider | Interim Release 2 query - IF-018 | LDSO’s are not detailed as ‘To Parties’ within IF-018 flow, however, the LDSO is a secondary routing party for updates to the Domestic Premise, Energy Direction Indicator, and the Metered Indicator |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | LDSO's added to the To party list of IF-018 | Data interface correction | Minor | Interface Catalogue | DES138
MHHS-DIN-483 | KH |  | 2023-07-10 | BGAS | 2410 | Neil Stranger | Supplier | MHHS Design Query - date/ time in DES138 | In DES138 there are a number of data items that are defined as having a date/time structure, but the name and description only refer to the date element whereas others refer to date and time. Therefore for those that make no reference to time we need to be 100% clear if the time should be when the event occur or should it be defaulted to say midnight. This is to ensure consistent population/use across the market. |  | Closed | [7 empty] | Related to a Design Principle and agreed as per E2E Architecture
MHHS-DIN-484 | SW |  | 2023-07-10 | Design Team | 2352 | Martin Freeman | Central Body | Clarity on RecipientId and SenderID in StandardResponseBodyType | RecipientID in the Standard Response Body is a mandatory field. When submitEvents (or in IR2 dip-channel) is called, the DIP synchronously returns a Standard Response Body. At this point the DIP does not even know what message recipients the message will be routed too, since the response is returned synchronously whereas routing is performed asynchronously. So the DIP has no way to know what to set recipientID to. It is also important to note that a message can be received by multiple recipients, yet this recipientID is a scalar that only supports being set to a single value. So it isn't clear how that could work. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | The Sender of the messages becomes the Recipient of the Response this already outlined in the examples in the E2E SA doc. Update section 4.6.1 in the E2E001 Design document to provide better clarity on how SenderID and RecipientID are populated in the StandardResponseBodyType. Updated Swagger 1.5 to align with the above. | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document
MHHS-DIN-485 | SW |  | 2023-07-10 | MHHS | 2380 | Steve Weston | Central Body | Unable to identify Recipient on DELETE and some POST methods | For the DELETE methods in Swagger for StatusMessage and PublicationConfig, need to update the method so you can identify the correct recipientID to be used for the method call. Some frameworks will ignore a body on a DELETE method as being incompatible with the semantics of the DELETE method, and the correct RESTful implementation would be something more along the lines of "DELETE dip-channel/{id}/{role}/pubconfig". Which of course raises the question of whether the POST message should be refactored for consistency. The issue is more widespread than just the DELETE methods, it also affects some of the POST methods where a recieipent ID is required |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Design changes required to Swagger 1.4 to support updates to API endpoints for DELETE API verbs to ensure we are able to remove the correct StatusMessage or PublicationConfig for the appropriate recipient combination. The issue also affects some of the POST methods where a recipient ID is required, e.g webhook config. A standard pattern is proposed where a recipeint id is specified in the path. Updates to section 4.5.1 and 4.7 also made to E2E001 design document to ensure the document provides any clarity required. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-486 | SB |  | 2023-07-11 | MHHS | 2107 | Rob Golding | Central Body | DES138 and message addressing information | Please can you raise a DIN to cover the following request from Participant to clarify the From and To Parties at the top of each sheet to align with the role codes the programme is using and defined in the E2E Solution Architecture document. And if these ‘pure’ roles code could be included in the introduction sheet that would certainly help. More detail can be seen in the Ticket |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Update the role codes in DES-138 for the From / To Parties for each of the Interfaces to align with other documents including E2E001. No change to information in the Introductory section in DES-138 required. | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-487 | SW |  | 2023-07-11 | MHHS | 2379 | Martin Freeman | Central Body | Clarity on schema vs data validation failures, with updated examples. | In section 4.4.4.2, there are some examples that incorrectly return a 207 when they have failed schema validation. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | In section 4.4.4.2, there are some examples that incorrectly return a 207 when they have failed schema validation. E2E001 section 4.4.4.2 has been updated to illustrate 2 examples. One that returns a 201 Created (2 messages as part of the HTTP Request, both pass validation) and another example that returns a 207 (2 messages part of the HTTP Request, but 1 does not pass validation). | Design Ambiguous | Supporting Docs | E2E Architecture Document | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-488 | ME |  | 2023-07-11 | MHHS | 1506 | Steve Weston | SRO Design | Correct Reporting Cat vs Swagger | Reinstated DI-484 "Settlement Period Duration" and added into R Groups as required |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Reinstated DI-484 "Settlement Period Duration" and added into R Groups as required in Swagger 1.4 | Data interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-489 | MF |  | 2023-07-11 | Design Team |  | Mike Fensome | SI Design | Schema Optionality incorrectly defined for Common Block | In DES-138, the Common Block shows some fields where the Schema Optionality is defined as Optional, rather than Mandatory. The list of Blocks are as follows - Common Block: S1, D0, A0 |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Update Schema optionality in DES138 to show that all data items must be present where the block is present in line with updated E2E Solution Architecture. Common Blocks impacted: S1, D0, A0 | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-490 | SW |  | 2023-07-11 | Design Team | 2395 | Martin Freeman | Central Body | Level 1 validation clarity for POST /statusmessage be the same as for POST /dip-channel/{id} | The E2E001 v3.2 (section 4.4.3) describes how for the Send Messages API, when the DIP performs level 1 validation, if any message in the request fails validation then the entire request is rejected. Section 4.6 Send Status Messages API does not describe the DIP validation for status messages at all. Should validation for POST /statusmessage be the same as for POST /dip-channel/{id}, in that a level 1 validation failure for any message should fail the entire request, or should messages that pass validation be accepted and messages that fail be rejected independently? |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | This should be consistent across all interfaces in that a schema validation failure for any message should fail the entire request. In the E2E001 design, sections 4.4.3 and 4.6 are to be updated to reflect this / provide the appropriate level of clarity. This issue affects both the http delete operations. Easy to fix, same fix as the post need to include the webconfigas a parameter | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.5
MHHS-DIN-491 | SB |  | 2023-07-11 | Utilita | 2408 | Adam Barnes | Supplier | IF-035 - Update routing to show XDSS | DES138 v5.2.1 - IF-035 tab for the bottom 3 entries it still refers to the previous version definition of routing parties – we expect this to be a slight oversight as SDSS is no longer defined as a recognised party? |  | Implemented | No |  | Error/Correction | N/A |  | Interim Release 8 | 2024-03-20 | Update routing for IF-035 to show XDSS for consistency of the documentation, but it will only ever apply to MPANs in the Smart Segment so will in reality only ever be routed to an SDS. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-492 | KH |  | 2023-07-11 | Stark | 2125 | Matthew Peters | Supplier | IF-034 Proposed Appointment Response Code Formatting | The data type within DI-143 block for IF-034 and IF-035 needs to change from String 200 to Array because there is a possibility of getting more than 1 rejection code. |  | Closed | No | [6 empty] | Closed - only 1 rejection code is required
MHHS-DIN-493 | SC |  | 2023-07-12 | St Clements |  | Sean Cooper | SRO Design | Changes to IF-019 Secondary MPAN validation | SCS had originally suggested a validation rule to prevent Secondary (Related) MPANs being linked to an Export MPAN. However, RECCO and EON have highlighted there are a very small number of scenarios where this might be the case. Following further discussions with SCS they are now happy to remove this rule (REG1068) |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | IF-019 - REG1068 check for Secondary MPAN Linkage to export REMOVED | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-494 | SW |  | 2023-07-12 | Callisto | 2462 | Neil Edney | Software Provider | Incorrect Min and Max Values for DI-091-Number-Of-Displayed-Register-Digits | DI-091-Number-Of-Displayed-Register-Digits currently has a minimum of 1 and maximum of 1, when this should be 5 and 6 respectively to align with DES-138 as this is an Integer. |  | Closed | [7 empty] | This DIN is now superseded by DIN-615 following on from DIN-574. Text against Number of Register Digits field amended to say "per the manufacturer specification". Swagger validation of this field updated to match SCS logical test ie value can be 0-9. This DIN was to ensure there was consistency in Swagger 1.4 to align with DES-138 so that min and max was 5 and 6 respectievly. This objection is related to the values in DES-138, to update from 5 and 6 to 0 and 9, and then align Swagger to the values in DES-138. | No Change
MHHS-DIN-495 | SC |  | 2023-07-12 | Design Team |  | Sean Cooper | SRO Design | Correction to BP003 | IF-035 for Trad/Advanced meters was previously shown as being direct interaction between REGS and MS ... Changed to show message as flowing via the DIP |  | Implemented | [5 empty] | Interim Release 3 | 2023-07-12 | IF-035 for Trad/Advanced meters was previously shown as a flow being direct interaction between REGS and MS. Changed to show message as flowing via the DIP (at step 90). Also change applied to Forward migration process for consistency. | Process Model correction | MPAN Ownership | BP003 | MHHSP-BP003-Change of Service - Data Service MHHS-DEL964 BPM-003 - Change of Servie - Data Service - Forward Migration
MHHS-DIN-496 | MH | DIN-910 | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 | MHHSP-METH001_SDS_Validation_Estimation 5.1 section 2.7 States "SDS shall inform the Supplier using the Meter Reading Reason Code on the IF-041/PUB-41" . There is no Meter Reading Reason Code on the IF-041 in DES138 v5.1.2. Therefore, either Meter Reading Reason Code should be included in DES138, or this requirement should be removed. |  | Closed | No |  | Design ambiguous | N/A |  |  |  | Updated as part of DIN-910 | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-497 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 | MHHSP-METH001_SDS_Validation_Estimation 5.1 Section 5.4 Where DA records are < 90 days from UTC date this is inconsistent with Method 4, which states "DA is available [either in the past or future] and less than [3] months different from the UTC Date requiring a daily Meter advance". |  | Implemented | No |  | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Be consistent - use either 90 days or three months within the document Tend to agree – this describes the actual method of estimation so should be included before go-live | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-498 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Correction to METH001 Method 13 | MHHSP-METH001_SDS_Validation_Estimation 5.1 Method 13 This describes the outcomes for Smart and Advanced meters. Does this imply that traditional meters should have zero consumption submitted to settlements, or should Method 13 text be adjusted to include trad meters? ALSO If actual data is recovered, or an Advance Meter Reading is received, and this indicates zero consumption, should this be submitted to settlements? The first part of the sentence implies it should be submitted, and the brackets imply it shouldn't. |  | Implemented | No |  | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Alter wording of Method 13 to reflect we shouldn't be sending estimates for Deenergised trad meters as well as Smart and Advanced, AND 'there is no need to submit zero consumption for de-energised MPAN's' needs changing to refer to 'zero ESTIMATED consumption' This should be a clarification of previously stated position but agree update should be made to clarify that Zero consumptions are required to be submitted, where encountered, for all MPANs that are not de-energised regardless of segment/meter type. | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-499 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Alignment of Estimation Reason Codes | METH001 refers to Estimation Reason Code 'Adjustment'. DES138 refers to 'Consumption Amendment' Assume these are the same thing and need to be aligned between both sets of documentation |  | Implemented | No |  | Design misaligned | N/A |  | Interim Release 8 | 2024-03-20 | Align Method Statements to match the Estimation Reason Codes within DES138 | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-500 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | ISD Entity M17 Example Correction | MHHSP_EDI021_ISD_Entities 5.1 Entity id M17 Industry Standing Data: MHHS Entities/Data Items v5.1 ISD Entity Id M17 - Valid Consent Granularity Combinations, includes combination I¦F¦S¦D. According to Decision 2 in "https://www.ofgem.gov.uk/sites/default/files/docs/2019/06/access_to_data_consultation_ofgem_response_0.pdf" a non-domestic customer is unable to opt out. The OFGEM document states "There will be no opt out possible for microbusinesses in relation to data for settlement purposes". Therefore, I ¦ F ¦ S ¦ D is not a valid combination. |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | In ISD Entity ID M17 we have removed "I ¦ F ¦ S ¦ D" from the example list | Design Ambiguous | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-501 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Addition of Method 13 to METH002 | MHHSP-METH002_ADS_Validation_Estimation 5.1 Section 3.16 States "The below estimation methods are based on those used in the Smart Data Service (SDS) Method Statement. For that reason, methods 0, 1, 6, 11 and 13 have been omitted as they are only applicable to Smart meters." However, method 13 is "Estimation for a Site where Supply is de-energised" and this is included in METH002 in section 2.29. The statement is wrong as some of the methods have been renumbered in METH001 since this was written. |  | Implemented | No |  | Error/Correction | Smart Data Services |  | Interim Release 7 | 2024-01-19 | Update METH002 to add Method 13 back in | Requirement correction | Supporting Docs | Method Statement | ADS Method Statement
MHHS-DIN-502 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | SP Quality Indicator Clarification | MHHSP-METH001_SDS_Validation_Estimation 5.1 It is our assumption that if NO estimation is required, the Settlement Period Quality Indicator should be set to "A". This is however, never explicitly mentioned. The only mention of using value "A" is for method 1. |  | Implemented | No |  | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Update artefacts to clarify when to use A as the Settlement Period Quality Indicator value | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-503 | SW |  | 2023-07-13 | SIMS | 2439 | Martin Freeman | Central Body | S1.senderUniqueReference interface component is too small to identify the message interface | DES138 and the E2E001 the S1.senderUniqueReference property has a 3 digit component that contains the interfaceID of the message. However since the reporting interfaces reuse the same interface numbers as the standard interfaces, and some reporting interfaces have 4 character interface identifiers, this means this component is not sufficiently large to unambiguously identify which interface a given senderUniqueReference was generated for. This also applies for TransactionID. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Update any Data Items that utilise InterfaceID to align with the enumeration of values defined for DI-000 so that this is unique across all interface / report types. This is for data types SenderUniqueReference (DI-995) and TransactionID (DI-990). This change will require updates in DES-138, E2E001 and Swagger 1.4. In DES-138, DT-014 has been updated to String65 from String60 to support Interface being updated from 3 to 8 to align with DI-000 (so for IF-003, rather than 003 being included in the transactionID / senderUniqueReference, this will be IF003 with no hyphen). In Swagger, DT-014 has been updated to max length 65, with examples updated. E2E001 updated examples for senderUniqueReference and TransactionID to align with the above. | Design Ambiguous | Supporting Docs | DES-138, E2E001 and Swagger 1.4 | DES-138-interface catalogue, E2E001 E2E Architecture document and Swagger 1.4
MHHS-DIN-504 | MH |  | 2023-07-13 | CGI | 2549 | Dave Webster | Software Provider | Clarification of link between IF22/IF23 | DES138 IF-022/023 IF an IF-022 or IF-023 is re-issued, can you confirm that they will be reissued as a pair so that the totals align? The issue is if an updated IF-022 is issued with new values, should the SDS/ADS await an updated IF-023, or not? How can the SDS/ADS pair the IF-022 and IF-023 without doing their own summations? |  | Open - awaiting assessment | No |  | Clarification - No change required | N/A |  | Post Go-live Release | 0 | Update BRS007 to show that a re-run of IF-022 will result in a rerun of IF-023 |  |  |  | BRS007
MHHS-DIN-505 | BK |  | 2023-07-13 | St Clements |  | Sean Cooper | SRO Design | DUoS Tariff ID to hold values from 1-3 in length | The DUoS Tariff ID needs to be updated in Swagger and the Interface Catalogue so that it can hold values from 1 to 3 in length in order to align with ISD. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Update DUoS Tariff ID to hold values from 1 to 3 in length in Swagger and Interface Catalogue | Data interface correction | Supporting Docs | Interface Catalogue and Swagger 1.4 | DES138-InterfaceCatalogue Swagger 1.4
MHHS-DIN-506 | BK |  | 2023-07-13 | Design Team |  | Sean Cooper | SRO Design | Renaming of IF-014 | Rename IF-014 to clarify the purpose |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Changed to "UTC Settlement Period Consumption Data (Warnings & Rejections)". Interface description and notes updated to reflect that IF-014 could also contain warnings for Consumption on De-enegised sites. | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-507 | SC | DI-194 | 2023-07-14 | Design Team |  | Sean Cooper | SRO Design | Clarification of IF-036 Routing Requirements | Update IF-036 to clarify / provide additional info on the routing destinations of IF-036 |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Added following Text: Primary Routing Participants for IF-036 MSAppActive • Supplier (i.e. the supplier who initiated the appointment, either current in the case of Change Of / Update to SP’s, or incoming in the case of a COS) • Metering Service (i.e. the Metering Service being appointed) • [Partner] Data Service (i.e. the Data Service in effect on the App Start Date of the MS Appointment – this could be either an ‘existing’ Data Service in the case of an MS Only appointment OR the ‘incoming’ Data Service with a coincident App Start Date to that of the [incoming] Metering Service • Linked Supplier(s) – (ie the Supplier(s) with responsibility for the Linked [Import/export] MPANs on the App Start Date of the Metering Service Appointment) DSAppActive • Supplier (i.e. the supplier who initiated the appointment, either current in the case of Change Of / Update to SP’s, or incoming in the case of a COS) • Data Service (i.e. the Data Service being appointed) • [Partner] Metering Service (i.e. the Metering Service in effect on the App Start Date of the DS Appointment – this could be either an ‘existing’ Metering Service in the case of an DS Only appointment OR the ‘incoming’ Metering Service with a coincident App Start Date to that of the [incoming] Data Service • Linked Supplier(s) – for Advanced Segment Meters only - (i.e. the Supplier(s) with responsibility for the Linked [Import/export] MPANs on the App Start Date of the Metering Service Appointment) | Data interface correction | Supporting Docs | Interface Catalogue
MHHS-DIN-508 | SC |  | 2023-07-17 | Design Team |  | Sean Cooper | SRO Design | Addition of MP Status and RMP Status Effective From Dates to IF-050 | Addition of MP Status and RMP Status Effective From Dates to IF-050 ( Linked to DIN 318 ) |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | New Data Items Created and added to IF-050 in block B079 and the data catalogue tab: DI-167 RMP Status Effective From Date DI-168 MP Status Effective from Date (DIN 318 Closed as duplicate) | Data interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-509 | SW |  | 2023-07-18 | MHHS |  | Steve Weston | Central Body | Missing Archival NFR Information | There is no detailed non-functional requirements in relation to data archiving, retrieval, archival tiers, recovery from archival so we need to update the NFR's to ensure these are included. |  | Open - awaiting assessment | No |  | Design ambiguous | DIP Users |  | Post Go-live Release | 0 | Further details of the solution are under discussion/review. | Clarification |  |  | Non-functional Requirements
MHHS-DIN-510 | SW |  | 2023-07-18 | MHHS | 2675 | Steve Weston | Central Body | Properties on block B047 | The Swagger definition has the properties ‘sp’,’v’,’q’,’e’ and ‘arc’ which matches the items in red. However the data catalogue has different YAML names. YAML Swagger names have to be updated in DES-138 to match the above characters. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | This was done to reduce IF-021 content size, but the DES-138 5.4.1 YAML needs to be updated to align with Swagger 1.4 - the YAML names should be as follows DI-082 ‘sp’ - B052 (IF-022), B047 (IF-021) DI-147 ’v’ - B047(IF-021, 4, 16) DI-083 ’q’ - B047 (IF-021, 14, 16) DI-076 ’e’ - B047 (IF-021, 14, 16) DI-166 ‘arc’ - B073 (IF-027 / 28) Swagger 1.4 has been updated to align for the approrpiate blocks above to ensure consistency across the data catalogue. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-511 | BK | CR027 | 2023-07-18 | Eastern Power Networks |  | Peter Waymont | Network Operator | DUoS E-Billing DIP Message for MHHS | A new flow needs to be introduced for e-billing of site-specific DUoS in the post Market-Wide Half-Hourly Settlement (MHHS) environment because the existing flow uses the DTN and all other DUoS data will be DIP based. The change is required in order to continue to operate the site specific DUoS billing process in the MHHS environment. MHHS introduces new data flows using the Data Integration Platform (DIP) and JavaScript Object Notation (JSON) format, including for the HH data sent by Data Services to the LDSO for use in DUoS billing, using IF-021/IF-013/IF-014. At present DUoS billing systems can send the D2021 data flow as a form of e-billing for site-specific DUoS, using the DTN. As DUoS billing systems will need to interact with the DIP for migrated site-specific billed customers, it is preferable that the outputs are also DIP messages, to enable the parties to move forward completely in the new environment. A DCUSA change was raised and a working group, comprising the senders (LDSOs/distributors) and receivers (suppliers) of the flows has identified the desired flow content and now wish to bring this to the Programme to ensure that it can be delivered in readiness for migration. | CR027 | Closed | [7 empty] | Covered as part of CR019
MHHS-DIN-512 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Amendments to Swagger and ECS data catalogue REP-002 | Max length for DI-345 DUoS Tariff Id to be updated in line with ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated to ensure DI-345 DUoS Tariff ID aligns with ECS Data Catalogue - max length of string = 3. | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-513 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Custom block correction REP-002 | Block name to be updated to tariffCharacteristics in Swagger. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated for REP-002 custom block to fix typo from tarrifCharacteristics to tariffCharacteristics to align with ECS Interface Catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-514 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Amendments to Swagger and ECS data catalogue REP-002a | Max length for DI-345 DUoS Tariff Id to be updated in line with ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated to ensure DI-345 DUoS Tariff ID aligns with ECS Data Catalogue - max length of string = 3. | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-515 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Custom block correction REP-002a | Block name to be updated to tariffCharacteristics in Swagger. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Swagger 1.4 updated for REP-002 custom block to fix typo from tarrifCharacteristics to tariffCharacteristics to align with ECS Interface Catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-516 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Update DI-300 with Minimum value REP-003 | DI-300 to be updated in swagger with a minimum value of 100 as per ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | DI-300 updated in Swagger 1.4 with a minimum value of 100 as per ECS data catalogue | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-517 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update data item type in ECS data catalogue REP-003 | DI-325 data type to be updated in data catalogue to (NUM 4,2) in line with swagger |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to NUM(4,2) for DI-325. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Cataloue correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-518 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Inclusion of Max/Min value for DI-496-REP-003 | Update ECS data catalogue with Min value of 1 and Max value of 48 |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | MIn and Max Column of MHHS ECS data catalogue updated with 1 and 48 respectively. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-519 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Max value change in swagger for DI-496 | Update Max value to 48 for DI-496 in swagger |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | DI-496 in Swagger 1.4 updated to have a Max value of 48 | Data Interface correction | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-520 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-359 data type REP003 | Update DI-359 data stype to String 16 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-359. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-521 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-360 data type REP003 | Update DI-360 data stype to String 16 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-360. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-522 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-362 data type REP003 | Update DI-362 data stype to String 16 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-362. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-523 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-324 data type REP003 | Update DI-324 data stype to String 16 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 16 for DI-324. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-524 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | DI-363 missing from ECS data catalogue | Update ECS data catalogue by adding in missing DI-363 |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | MHHS Data catalogue updated with the addition of missing data item DI-363. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-525 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-364 data type in REP003 | Update DI-364 data stype to String 17 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-364. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-526 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-365 data type in REP003 | Update DI-365 data stype to String 17 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-365. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-527 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-366 data type in REP003 | Update DI-366 data stype to String 17 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-366. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-528 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-367 data type in REP003 | Update DI-367 data stype to String 17 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-367. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-529 | ME |  | 2023-07-18 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-368 data type in REP003 | Update DI-368 data stype to String 17 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-368. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-530 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Wrong data item referenced in swagger | Wrong data item referenced in R022. Daily Period BM Unit Total Allocated Volume must be changed to BM Unit Allocated Demand Disconnection Volume |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Swagger 1.4 has BM Unit Allocated Demand Disconnection Volume (DI-241) in R022 | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-531 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Data type update in swagger for DI-341 | DI-341 data type to be changed to String 18 as per data catalogue |  | Closed | [7 empty] | Closed. This is defined a Integer in the format 9,6 in Swagger. | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-532 | ME |  | 2023-07-18 | MHHS | 1506 | Steve Weston | Central Body | Wrong data item referenced in swagger | Wrong data item referenced in R022. settlementPeriodID must be changed to Settlement Period |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Updated Swagger 1.4 so that R022 references DI-946 (SettlementPeriod) rather than DI-307 (SettlementPeriodID) | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-533 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-339 data type in REP-003 | Update DI-339 data stype to String 17 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-339. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-534 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-369 data type in REP-003 | Update DI-369 data stype to String 17 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-369. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-535 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Deisgn | Update to DI-370 data type in REP-003 | Update DI-370 data stype to String 17 in ECS data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | MHHS Data Type column of MHHS ECS data catalouge updated to String 17 for DI-370. Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-536 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-322 REP003 | Update Min column of ECS data catalogue with 0 |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | DI-322 Minimum column of MHHS ECS data catalouge updated with 0 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-537 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-322 REP003 | Update Max column of ECS data catalogue with 99.99 |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | DI-322 Maximum column of MHHS ECS data catalouge updated with 99.99 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-538 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-323 REP003 | Update Min column of ECS data catalogue with 0 |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | DI-323 Minimum column of MHHS ECS data catalouge updated with 0 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-539 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-323 REP003 | Update Max column of ECS data catalogue with 99.99 |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | DI-323 Maximum column of MHHS ECS data catalouge updated with 99.99 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-540 | SW |  | 2023-07-14 | Elexon | 2684 | Nigel Rees | Central Body | IF-13 run number | In DES-138, Run Number in IF-013 Interface is 3 chars, yet in Swagger and ECS Reports, this is 7 characters long. We need to update DES-138 to align with Swagger and ECS reports. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Updated IF-013 to show DI-161 (Run number) as number 7 to be consistent with Data Catalogue/ Swagger and Reports | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-541 | MF |  | 2023-07-19 | ESG | 2623 | Patricia Parker | Software Provider | SSC and Profile Class validation | Validation needs to be reviewed to enable the provision of just SSC or Profile Class updates as part of [SSCandProfileClass] event code updates in IF-025 |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Updated conditionality on IF-025 and IF-026 for DI-122 (Profile Class) and DI-123 (SSC) to "Mandatory for Traditional Meters (if changing)" to allow just SSC or Profile class updates to be provided. Validation rules updated accordingly in IF-025. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-542 | ME |  | 2023-07-19 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-159 in data catalogue REP004 | Update Min column with 25 in data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | DI-159 Minimum column of MHHS ECS data catalouge updated with 25 to align with swagger 1.3 | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-543 | MF |  | 2023-07-19 | Design Team |  | Mike Fensome | SRO Design | IHD, SMSO, SSC and Profile Class conditional validation | Update validation rules to ensure effective from date is provided when IHD, SMSO, SSC or Profile class are updated |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Added conditionality to IF-025 and IF-026 that DI-136 should be provided where DI-137 is not null and DI-135 should be provided wher DI-134 is not null. Added validation rules to IF-025 to ensure conditionality rules are applied for IHD, SMSO, Profile class and SSC with new error code of REG1088 -Effective from date must be provided | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-544 | SW |  | 2023-07-19 | Siemens | 2633 | Tony Mason | Software Provider | Level 4 Validation - Multiple response codes | Unclear from the current E2E design defined in E2E001 for a Level 4 Response code, whether a single transaction with concatenated Response codes be sent back to the DIP for notification to the publisher? Or, would the expectation be that multiple messages be returned with each message quoting the published transaction number? Or, is this at the discretion of the participant? The E2E design should make this clearer, and also provide fleixbility for multiple messages to be returned against the same transaction ID with a response. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | This will require updates to the E2E design document to make Level 2 and 4 response code expectations clearer, as well as updated Swagger to allow for an array of messages, help and service tickets to be sent per error, per transaction ID. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.5
MHHS-DIN-545 | ME |  | 2023-07-20 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-496 data type REP004 | Update swagger to show DI-496 as INT (2) |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Update to data type for DI-496 from INT(3) to INT(2) to align with swagger. Update made to MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Reporting correction | Minor | ECS Reports | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-546 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Incorrect data item referenced in swagger- REP004 | Incorrect data item referened in R026. SettlementPeriod ID must be replaced with Settlement Period (DI-496) in swagger |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Updated Swagger 1.4 so that R026 references DI-946 (SettlementPeriod) rather than DI-307 (SettlementPeriodID) | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-547 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Missing data item in swagger | In R026, DI-327 missing from swagger v1.3. Should added and defined as per DT-22 |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Updated Swagger 1.4 to include DI-327 (Deemed Supplier Take). Updated R026 to include DI-327 and remove DI-325 so this aligns with ECS Data Catalogue. | Swagger | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-548 | MH |  | 2023-07-20 | Elexon | 1966 | Rashmi Radhakrishnan | Central Body | Clarification of ISD Transition Requirements | Following MTDSG release of the BRS001 Transition approach and Parallel running requirements v2, ISD would like programme to consider rewording below requirement for more clarity. MHHTR-22 Original: The ELEX-REP-005 Line Loss Factor report will be published at a location on the BSC website/ ELEXON Portal and the URI shall be notified using the Notification of the Publication of a Downloadable Asset IF-047 / PUB-047 to DIP Users prior to M10 and continue post M15. MHHTR-27 Original: The new ISD entities shall be updated be published at a location on the BSC website/ Elexon Portal and the URI shall be notified using the Notification of the Publication of a Downloadable Asset IF-047 / PUB-047 to DIP Users from M10. |  | Closed | No | [6 empty] | Duplicate - To be tracked under MHHS-DIN-754 | Design Ambiguous | Supporting Docs | ISD Document | ISD Document EDI-021
MHHS-DIN-549 | ME |  | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Incorrect data item referenced in R033 common block | Incorrect data item referenced in R033 - SettlementPeriodID from MDS/VAS should be replaced with SettlementPeriod (DI-496) from ISD, with a MIN value of 1 and Max of 48 in swagger |  | Closed | No | [6 empty] | Closed- Swagger should keep the min of 1 and max of 50 settlement periods
MHHS-DIN-550 | ME | DIN-659 | 2023-07-20 | MHHS | 1506 | Steve Weston | Central Body | Missing R007 from REP007 | Include R007 within REP007 in swagger |  | Closed | No |  | Design misaligned | DIP |  |  |  | Update swagger: Include R007 within REP007 | Swagger | Supporting Docs | Swagger | Swagger
MHHS-DIN-551 | ME |  | 2023-07-20 | Design Team | 1506 | Miriam Ellis | SRO Design | Update to DI-083 | Include Min Value of 1 and Max value of 5 to DI--083 in ECS data catalogue to align with swagger and IF data catalogue |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | DI-083 Minimum and Maximum column updated with 1 and 5 respectively in MHHS ECS data catalouge Documents updated MHHSP - ERI011B - ECS Reports - External and MHHSP - ERI011A - ECS Reports - Internal | Data Interface correction | Supporting Docs | ECS Data Catalogue | MHHSP - ERI011B - ECS Reports - External v5.2 MHHSP - ERI011A - ECS Reports - Internal v5.2
MHHS-DIN-552 | SW |  | 2023-07-20 | IMServ | 2356 | Liam Lowey | Software Provider | UTF-8 Encoding for JSON | The E2E001 design document does not specify Encoding for JSON. This needs to be updated to reflect UTF-8 as the JSON Encoding required. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Add UTF-8 as the JSON encoding required in the E2E001 design document, creating a new section 4.2.5. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger 1.4
MHHS-DIN-553 | RS |  | 2023-07-20 | Design Team | 2627 | Rob Short | Central Body | Secondary routing for Export | Secondary routing rules need to be updated to allow notification of work prgressed by the Import suppllier (eg disconnection). review required of all related interfaces |  | Closed | [7 empty] | Following review no document changes required. Re Specific case of Disconnection the Link between Import and Export would need to be removed prior to any Disconnection request. If the link remains in place then the DIsconnection request will be rejected by LDSO/REGS.
MHHS-DIN-554 | MF |  | 2023-07-20 | St Clements |  | Madison Layton | Software Provider | Validation on Customer Direct Contracts | Revisions to CDC functionaility. - Amend validation to ensure that only one Customer Direct Contract can be applied against an MPAN at any moment in time - Move CDC process(s) onto a new BP10 process map so as to make it clearer that CDC is MPAN not appointment based - add supporting process info to new BP |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | DIN moved to Interim Release 5 due to objection raised pending discussion to clarify solution. Process map emailed to particpants - added to BP010E and validation rules for IF-038 updated accordingly. Business requirements updated to align with process Agreed changes with SCS, & RECCO | Design Ambiguous | Supporting Docs | Supporting Docs | BP10 Registration Updates DES138 - Interface Catalogue BRS001 , BRS002
MHHS-DIN-555 | MF |  | 2023-07-20 | St Clements |  | Madison Layton | Software Provider | Validation of MPID to DIP ID | Carry out validation of MPID to DIP ID during initial IF-031 validation only. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Set REG1090, REG1091 and REG1092 validation in IF-031 to "No" for Queue processing so it only applies to IF-031 validation. | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-556 | KH |  | 2023-07-21 | Stark | 2112 | James Murphy | Supplier | Cumulative/Total Consumption Comparison | The “Cumulative/Total Consumption Comparison” that can be carried out instead of a MAR for meters with integral Outstations is not defined anywhere In BSCP502 it is defined at 4.1.5 – I think this should be lifted and shifted into METH002 Interestingly it appears to be described in the SDS Validation & Estimation Statement (METH001) at 3.12 – 3.16 ADS Method Statement (METH002) needs to be updated |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | ADS Method Statement has been updated with "Reconciliation for smart Meter Advance Reconciliation" section 2.21 - 2.25. | Method statement correction | Supporting Docs | Method Statement | METH002 ADS Validation Estimation
MHHS-DIN-557 | RS |  | 2023-07-21 | Elexon | 2745 | Rashmi Radhakrishnan | Central Body | Consistency of the use of ID | Version 5.1 ISD EDI021 Entity specification document, has discrepancies in the usage of ID, Id, id, etc. Inconsistencies to be addressed when updating the design artefact in the future. ISD Entity M3 Usage of ID and Id - Market Participant ID in the table and description are different ISD Entity ID 17 - DUoS Tariff Id GSP Group Id - ISD Entity ID 17 - DUoS Tariff Id table - GSP Group id is with lowercase "i" and Entity Id M4 Load shape categories : GSP Group Id is mentioned as GSP Group ID ISD Entity ID 17 - DUoS Tariff Id Usage of DUoS Id and DUoS Tariff Id ISD Entity Id 4 and 17 - has ID in capital letter Usage if ID and Id to be consistent Entity M4 GSP Group ID- but should be GSP Group Id ISD Entity Id M5 - MHHS Consumption Component Classes CCC ID - for consistency it should be CCC Id |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | All instances of lower /mixed case id have been replaced with "ID" in caps Also see DIN588 | Data Interface correction | Supporting Docs | Support Docs | ISD Document EDI-021
MHHS-DIN-558 | BK | DI-189 | 2023-07-21 | St Clements | 2011 | Madison Layton | Software Provider | Update response codes in IF-035 | IF-035 routing rules references response codes AC and RJ, this should be A and R |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Updated Routing rules in IF-035 to refer to Response code of "R" and "A" for event code [SDS-MDROutcome] rather than "AC" and "RJ" | Data Interface correction | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-559 | SC |  | 2023-07-24 | St Clements |  | Sean Cooper | SRO Design | Clarification of Appointment Scenario Code (Linked MPANs) | Added clarification to IF-036 to confirm that the Appointment Scenario Code used for Secondary MPANs will mirror that applied to the Primary MPAN (eg COS/CSP/Etc). What will be applied in the case of Auto Alignment ? |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Added clarification to IF-036 to confirm that the (DI-800) Appointment Scenario Code used for Secondary MPANs will mirror that applied to the Primary MPAN (eg COS/CSP/Etc). In cases of Auto-Alignment of MPANs the Appointment Scenatio of (ALG - Auto Alignment of MPAN Service Providers) will be applied. ALG added as allowable value in DI-800 ( Data Catalogue and Swagger ) | Design Clarificarion | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue Swagger 1.4
MHHS-DIN-560 | SC |  | 2023-07-24 | St Clements |  | Sean Cooper | SRO Design | Design Gap on Sharing MTD in the Case of AutoAlignment of Service Providers | The Design allows for the Auto-Alignment of Service Providers in certain circumstances. However a design gap exists that there is currently no trigger for the outgoing MS to send MTDs to the incoming MS in the case of a pure Auto-Alignment (ie no other MPAN transaction eg. COS/CSP) |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Proposal is to create a new requirements (MS-098 / MS-099) on Smart and Advanced Metering Services to trigger sending of D0149/D0150 (trad) or D0265 (Adv), on receipt of a PUB-037 with De-Appointment Reason Code of “RELATED” or “IMPEXP”. D-Flow(s) should be sent, via DTN, to the new/incoming MS referenced in the PUB-037 flow, where available Issue does not arise for Smart sites as MTDs are fully convayed using the PUB-036. Also not a concern for UMSDS as no MTDs exist. | Design Clarificarion | Minor | MPAN Ownership | BRS-002 Metering Service Requirements
MHHS-DIN-561 |  |  | 2023-07-24 | St Clements |  | Sean Cooper | SRO Design | Disconnection of Linked MPANs | No change to desgin required. Design confirmation only. SCS have confirmed that it will be necessary to de-link and MPRN before being able to action a disconnection on it. i.e. Disconnection cannot be performed on a linked MPAN until such time as all links have been removed via (IF-019/IF-020) |  | Closed | [7 empty] | No change Required - Clarification Only
MHHS-DIN-562 |  |  | 2023-07-24 | St Clements |  | Sean Cooper | SRO Design | Clarification of IF-014 R0 Population for Event Code [ConsumptionOnDeEnergisedMPAN] | Confirmation at an R0 will be required when issuing an IF-014 with Event Code [ConsumptionOnDeEnergisedMPAN]. DI-979 should be populated with value 'W', DI-980 would remain blank. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | IF-014 updated to clarify that DI-979 should be populated with W. Data Catalouge and Swagger v1.4 updated to reflect this. | Design Clarificarion | Minor | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-563 |  |  | 2023-07-24 | Elexon | 2705 | Ayo O (Helix) | SRO Design | Clarification on Helix Treatment of IF-021 error condition data. | Clarification is required from Helix on exactly how they will manage and process IF-021 messages and how any resulting error/rejections will be managed. This is so that clear guidance can be drawn up on participants should expect to receive errored data etc. In any event design team are clear "the data returned in the IF-014 must only be that data which is rejected." |  | Closed | [7 empty] | A response was provided to Ayo on 24/07 by design team. Follow up email has been sent for Ayo to confirm whether issue is resolved, thus closing the DIN or whether a call is required with Design team for further resolution. DIN closed as no response received from Ayo. It is our assumption the feedback provided by the design team was sufficient. | Design Clarificarion
MHHS-DIN-564 | SW |  | 2023-07-17 | SIMS | 2704 | Martin Freeman | Central Body | Mandatory Nullable on Swagger | Is Mandatory Nullable (which is how 'optional' properties are described in the DES138) supposed to be marked as Required & nullable in Swagger? Or should these Mandatory Nullable (optional) properties be marked 'not Required' in Swagger? In some interfaces Mandatory Nullable properties are marked 'not required' in Swagger while in others they are 'nullable required'. Need to ensure this is applied consistently across all Interfaces. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Need to update Swagger implementation so mandatory nullable is treated consistently across all Interfaces as this is not always consistent. Need to updated E2E001 to provide additional clarity on how this applies to Swagger. Need to ensure DES-138 is aligned. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | Swagger 1.5
MHHS-DIN-565 | SW |  | 2023-07-25 | MHHS | 2763, 2713 | Steve Weston | SI Design | Version and Schema Interoperability across environments. | Versioning is covered in Section 8.4 and 8.5 of the E2E001 design, that covers the differences between major, minor and patch versions of an API, the URL required as well as schema versions that are contained in the common block of an Interface. There is confusion around how this will work across different environments so we need to provide additional clarity on the Swagger API versions / Schema versions that must be supported by the DIP and MP’s, alongside scenarios that are envisaged. This will provide information on version uplifts, interoperability required and how long different versions of API / Schemas will be supported for. This needs to covers scenarios where within an environment, we have multiple versions of an API within an environment ie, we may be required in some cases to be backwards compatible with previous versions -- for example -- if we received and processed earlier versions, we can respond with the latest live version. E.g. if we receive PUB-005 on version 1.0.0 we could respond with IF-006 on version 1.0.1 and would not be expected to respond with version 1.0.0. |  | Open - awaiting assessment | No |  | Design gap | TBC |  | Post Go-live Release | 0 | Need to provide updates to Section 8.4 and 8.5 to ensure we cover worked examples across different environments for both API versions and Schema versions, interoperabilty required, transition between versions, BAU vs Testing phases and expectations on DIP and MP's. | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger | E2E001 E2E Architecture Document Swagger
MHHS-DIN-566 | SW |  | 2023-07-25 | MHHS | 2549 | Steve Weston | SI Design | E2E NFR's need to be refined based on actual data | Section 3.1 of MHHS DES001a MHHS Data Integration Platform – Functional Specification – Appendix A Transaction Volumes states that the indicative size of an IF-021 (single days' worth of UTC SP data) is between 1 and 2 KB. The equivalent IF-021s we have successfully submitted to the DIP Simulator are ~4.5 KB as observed in webhook. Can you confirm that this increase in size has been factored into the non-functional requirements? |  | Closed | No |  | Clarification - No change required | DIP Users |  |  |  | Agreed to be closed. Volumetrics document has been updated to reflect updated file sizing. This is for guidance only and depends on IF-021 consumptions per transaction. | Design Ambiguous | Supporting Docs | MHHS E2E004 Solution Architecture - Transaction Volumes | MHHS E2E004 - End to End Solution Architecture– Transaction Volumes IF-021
MHHS-DIN-567 | SW |  | 2023-07-25 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - Swagger Incorrect | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4. Swagger 1.4 needs to be updated so that it aligns with DES-138. DI-081 to be updated to periodDuration. DI-086 to be updated to supplierEffectiveFromDate. DI-121 to be updated to supplierEffectiveToDate. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Need to update mismatch between Swagger YAML definition in DES-138 and Swagger 1.4. Swagger 1.4 needs to be updated so that it aligns with DES-138. DI-081 to be updated to periodDuration. DI-086 to be updated to supplierEffectiveFromDate. DI-121 to be updated to supplierEffectiveToDate. | Design Ambiguous | Supporting Docs | Swagger 1.4 | Swagger 1.4
MHHS-DIN-568 | SW |  | 2023-07-26 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - DES-138 incorrect | DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) shows in YAML as secondaryRecipientDIPID and primaryRecipientDIPID respectively and this should be updated in DES-138 YAML column so this aligns with Swagger 1.4 ie, DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | DI-981 (secondaryRecipients) and DI-982 (primaryRecipients) shows in YAML as secondaryRecipientDIPID and primaryRecipientDIPID respectively and this has been updated in DES-138 YAML column so this aligns with Swagger 1.4 ie, DI-981 (secondaryRecipients) and DI-982 (primaryRecipients). | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-569 | SW |  | 2023-07-26 | MHHS | 2762 | Steve Weston | SI Design | Mismatch between Swagger YAML definition in DES-138 and Swagger 1.4 - DES-138 incorrect | DI-047, DI-049, DI-210, DI-211 and DI-820 are defined in the Data Catalogue, but not used in any Interfaces so need to be removed from the latest version of DES-138. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | DI-047, DI-049, DI-210, DI-211 and DI-820 are defined in the Data Catalogue, but not used in any Interfaces so need to be removed from the latest version of DES-138. DES-138 needs to be updated to remove these items. | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-570 | MF |  | 2023-07-26 | MHHS |  | Mike Fensome | SRO Design | IF-021 validation rules | IF-021 validation rules need to be updated to align to the MDS and LSS Method statements which include validation for de-energised sites. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | IF-021 Added validation to align with MDS/LSS method statements where estimated data is provided on a de-energised site (ECS1008 - SP End Date/Time [DI-082] contains non-actual consumption for ECS De-Energised MPAN) | Design Ambiguous | Supporting Docs | Interface Catalogue | DES138-InterfaceCatalogue
MHHS-DIN-571 | SW |  | 2023-07-27 | Callisto | 2762 | Dave Peat | Software Provider | Inconsistency for DI-980 Response Message(s) | For DI-980, the YAML name is responseMessages, however in Swagger, there is inconsistencies: R0.responseMessages - this is defined as array of DI-980 (responseMessages) B066.responseMessage - but defined as responseMessages (defined as DI-980 - single) B092.responseMessage - defined as responseMessage (defined as DI-980 - single) We need to update DES-138 / Swagger so there is consistenct application of the words responseMessage (for single response) vs responseMessages (where there is an array of responses). |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | I have updated Swagger 1.4 so that DI-980 definition is applied consistently for single response vs array of responses. For single, it will be responseMessage. For an array of messages, it will be responseMessages. To this effect, B066.responseMessages has been updated to be responseMessage. Also, B066 block has been updated to align with DES-138 to be conditionally mandatory, rather than mandatory. | Supporting Docs | Design Ambiguous | Supporting Docs | Swagger 1.4
MHHS-DIN-572 | SC |  | 2023-07-27 | MHHS |  | Sean Cooper | SRO Design | Clarification of IF-013 Issuance (also Ref DIN610) | DUPE WITH DIN-610 ~ Clarification is requiired on the circumstances when Helix will issue IF-013. 1. IF-013 is only issued as part of the RF Run i.e. simply to notify Suppliers of what the default consumption for a period(s) is, where no data has been submitted by the DS come the point of RF. Should suppliers wish to derive this for pre-RF settlement runs then they are able to do so easily enough using the own data and the published Load Shapes. 2. The second view is that the IF-013 is issued on every settlement run undertaken for sites where no PUB-021 data has been received DIP impact concerns wrt to volumes of IF-013 would need to be addressed if Option 2 is the position. |  | Closed |  |  |  |  | 2023-09-13 |  |  | Duplicate of DIN-610 | No Change
MHHS-DIN-573 | ME |  | 2023-07-27 | MHHS |  | Kevin Spencer | SRO Design | Update to step 40 of ISD BPM/BPD | Step 40 of MHHSP-BP021 and BPD021 currently ambigious Can the intention of this step be made clearer.? |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Step 40 of ISD BPM and BPD have been updated to say 'Issue ISD Change Notification' to make ithe purpose of the step clearer. | Design Ambiguous | Minor | Supporting Docs | MHHSP-BP021 Industry Standing Data MHHSP-BPD021 Industry Standing Data Business process Descriptions
MHHS-DIN-574 | SC |  | 2023-07-27 | St Clements |  | Madison | SCS | Change Of Logic on Smets 1 Number of Digits | Smets 1 Number of digits can be 0 - 9 Replaces previous logic. |  | Closed | [7 empty] | DIN CLOSED as agreed with St Clements and RECCo. DIN-615 supercedes this DIN. The text has been updated as suggested below from RECCo, ‘Where the Meter Type is S1, the value should be populated as per the manufacturer specification.’ However, the logical test for SMETS1 in the DES-138 Interface Catalogue will remain unchanged. DIN-615 also includes updating the Swagger validation of this field to match SCS logical test i.e. value can be 0-9. | No Change
MHHS-DIN-575 | SC |  | 2023-07-27 | St Clements |  | Madison | SCS | Requirement for REGS to process IF-040 | SCS would prefer not to process IF-040 now that AC is provided to EES Directly via the DIP. In additional what is the IF-040 processing schedule? IF-040 is only sent to appointed Suppliers and Data Services on a 30 day cycle. There could be a 30 day wait until the next MDS generated IF-040. Programme Design: To fill this design gap the programme has made MPRS responsible to load the IF-040 by populating Annual Consumption in the B027 Block on IF-002, IF-001 & IF-036 MPRS Issue: An IF-040 for every energised MPAN must be loaded adding significant overhead to processing. The 24 hr SLA could be difficult to meet without significant hardware investment. | CR039 | Implemented | No |  | Change Request | LSDO (SCS), DIP |  | Interim Release 8 | 2024-03-20 | To minimise change and impact on all other participants B027 Block is retained in IF-001, IF-002 & IF-036, but will never need to be provided by Registration Service as it is only required where the data exists in Registration Service. Annual consumption requirements document updated to remove the requirement for REGS to receive PUB-040 and maintain Annual Consumption. BP005 and BPD005 updated to remove REGS receiving Annual Consumption. REGS removed from IF-040 secondary routing in DES-138. On Appointment, Data Service and Supplier will receive the latest PUB-040 with their PUB-036. DIP will be changed to replay the PUB-040 from the Message Archive. Note added to BP003. Change in IR5 SIT Scope to exclude B027 Block Loading for Supplier and Data Services. Remove testing of IF-040 Processing for MPRS Change in IR8 SIT Scope to add DIP IF-040 Replay on Supplier and Data Service Appointment Confirmation | Data interface correction | Supporting Docs | Interfaces | DES138 BP003 BP005 BPD005 BRS012
MHHS-DIN-576 | MF |  | 2023-07-27 | St Clements |  | Madison | SCS | Cancelling appointments in advance of receipt of PUB-034 | SCS have requested that the design is updated to allow for issuing of a PUB-035 'Lapsed' message, if a switch is 'Cancelled' or otherwise superseded, even prior to issuing / processing of a PUB-034 from the Metering Service or Data Service. ​ |  | Closed | [7 empty] | Following DRG on 4th Aug, it was agreed that St Clements Services were to work-up the topics discussed, and a dedicated workshop would be arranged to discuss this further. St Clements Services have advised the Programme that they will now not be pursuing proposals made at the DRG session and would be reverting to implement to the original design, therefore closure of this DIN.
MHHS-DIN-577 | SW |  | 2023-07-27 | Callisto | 2979 | Neil Edney | Software Provider | DT-983 and DT-000 are missing IF-040 / PUB-040 | DT-983 and DT-000 are missing IF-040 / PUB-040 in Swagger. IF-003, 19, 20 and 50 also need to be added to align with DES_138. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Need to update Swagger to include IF-040 and PUB-040 in DT-000 and DT-983. I’ve added IF-003 / 019 / 020 / 040 / 050 to DT-000 in Swagger and PUB-003 / 019 / 020 / 040 / 050 to DT-983 in Swagger | Supporting Docs | Design Ambiguous | Supporting Docs | Swagger 1.4
MHHS-DIN-578 | SB |  | 2023-07-28 | RECCo | 2943 | Jonny Moore | Central Body | EFDs, ETDs and Supplier information for Related and Import/Export Linkages | We’ve noticed through the design and build stage of EES that we are not being communicated the EFD and ETD of a Related MPAN set-up or an Import / Export Linkage. Nor are we being informed of the Supplier responsible for creating a Related MPAN relationship. This information is not currently being published in the IF020/PUB020 However, this information is currently available for market participants to view on EES. We had some feedback in the REC MSAG that participants would like to continue to view these items in EES and wonder if this is worth a DWG discussion? |  | Closed | [7 empty] | RECCo notified on DIN closure. The Effective From date is not currently shared on the D0386 which was the basis for the IF-019/PUB-020. If EES requires an EFD suggest that the transaction date from the header is used. These updates can only be made by the current Supplier. | No Change
MHHS-DIN-579 | SB |  | 2023-07-28 | ENWL | 2444 | Paul Stancliffe | Network Operator | PUB-043 Routing discrepancy | Trying to map flow PUB-43 to our TO BE business processes as these flows are showing on the MHHS - Interface Data Item Catalogue as routing to LDSO. However when trying to align these to the Business Process Diagram BPM011- Change of Connection Type and / or Market Segment V5.0 PUB-43 is not routing to LDSO |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | BP011B from Step 542 new flow for PUB-043 to LDSO new step Manage Change of Connection type Notification | Process Model correction | MPAN Ownership | Supporting Document | BP011B BPD011
MHHS-DIN-580 | RS |  | 2023-07-28 | RECCo | 2719 | Sarah Jones | Central Body | Late or Missing Secured Active Messages | understand the approach to managing CSS issues where secured active messages are not received within the expected secured active processing window. We understand the standard ‘happy path’ processing requires secured active notifications to be issued by CSS after the 5pm gate closure window the day before the registration effective from date. However, it was acknowledged when the MHHS design was originally baselined that some notifications may arrive late e.g. after 6pm, or not at all. Rather than developing operational provisions to deal with missing / late secure active notifications, this was highlighted as a risk for later consideration, on the basis the CSS arrangements were still new and the enduring BAU process was subject to change. In light of the CR018 approval, we believe this is now the time to clarify the approach to be taken where CSS notifications are missing or late. |  | Closed | [7 empty] | The Design Team and SRO are actively engaged with St Clements on issues around problematic switches. The plan is for them to provide us with a list of of their issues. We will then go through a process of raising these directly with CSS. Dependent on outcomes we receive back, we will look to discuss this with St Clements with the possibility of raising a CR for a specified data correction tool to align the data and send out the appropriate MHHS flows. | No Change
MHHS-DIN-581 | RS |  | 2023-07-28 | ESG | 2924 | Patricia Parker | Software Provider | Meter Location in DES138 | Currently DI090 in DES138 states 'Values as Per ISD'. These values are not held in ISD, therefore the reference should be changed to 'see Enum Values of the Data Catalogue' - example IF-005 |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Updated population notes for DI-090 to refer to Data Catalogue, IF's 2,5,6,20.33.36,61,62 | Clarification | Supporting Docs | Interfaces | DES-138 Interface Spec
MHHS-DIN-582 | MF |  | 2023-07-28 | Ovo |  | Chris Butterfiled | Supplier | Clarification following CR15 | Supplier Overview requirements v5.1: this refers specifically to Economy 7 / Economy 10 tariffs; we suggest this should be more general and refer to any Time of Use tariff / tariff with switched load to include other variants such as Smart Economy 9 etc. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Updated SU-163, SU-164 and SU-165 to refer "for switched load tariff (eg. Economy 7/Economy 10) sites" rather than Economy 7/Economy 10 sites | Requirement correction | Supporting Docs | supplier requirements | MHHSP-BRS004 Supplier Overview
MHHS-DIN-583 | SB |  | 2023-07-31 | Stark | 2891 | Jon Dennis | Data Service Provider | BP005 Read Sharing for Data Service | can you provide clarification around BP005 Read Sharing for the Data Service, in particular this section of MHHSP-BP005-Data Processing-v5.1 Question: Is the entry point to this section either: Regular Data Collection, e.g. daily remote collection for ADS/SDS Smart? Trigggered by an external process, e.g. Change of Energisation BP009? To answer the above, please can you list all of the processes that lead to Step 170 in BP005. May I also suggest updating BP005 to include this information, perhaps by adding a Step description to the entry point from Data Collection as shown above. Related Question: In BP009 the Data Service is expected to progress to BP005 Step 185. However, unless I am mistaken, BP005 V5.2 does not include Step 185. Please update BP009 with a valid onward step. |  | Open - awaiting assessment | No |  | Clarification - No change required | Smart Data Services, Advanced Data Services |  | Post Go-live Release | [5 empty] | BP005
MHHS-DIN-584 | SC |  | 2023-07-31 | Design Team |  | Sean Cooper | SRO Design Team | DI-511 Change of Data Type from String to Number in IF-024 | DI-511 Off Peak Declaration Proportion has been changed from String to Number so as to allow for improved Swagger validation of this data item. The new Number val will have a Minimum value = 0 and a Maximum Value = 100. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | DI-511 Off Peak Declaration Proportion has been changed from String to Number so as to allow for improved Swagger validation of this data item. The new Number value will have a Minimum value = 0 and a Maximum Value = 100. (IF-024). Data Catalogue updated accordingly. | Improved Validation of Data Item | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-585 | SC |  | 2023-07-31 | Design Team |  | Sean Cooper | SRO Design Team | Clarification on IF-024 | Clarification update to confirm that B097 Off Peak Declaration is Mandatory only for Event Type [SN-OffPeakDec] |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Clarification update to confirm that B097 Off Peak Declaration is Mandatory only for Event Type [SN-OffPeakDec] | Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-586 | SW | DI-204 | 2023-07-31 | Callisto | 2762 | Neil Edney | Software Provider | Mis-alignment between D0 block YAML in Swagger and DES-138 | DES138, the D0 has the following YAML names which do not align DIPCorrelationID, DIPTimeStamp, DIPTransationID However, swagger has these: initialCorrelationID, transactionTimestamp, transactionID |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Updated DES138 Data Catalogue D0 Common block data items so that YAML names in DES-138 now align with Swagger initialCorrelationID (DI-987), transactionTimestamp (DI-989), transactionID (DI-990) | Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-587 | SW |  | 2023-08-01 | Kraken | 2973 | Angelos Rizoyannis | Software Provider | Mis-alignment between R0 mandatory in Swagger vs DES-138 | In DES-138 in the following interfaces, R0 is marked as mandatory, but not mandatory in Swagger - IF-006, IF-008, IF-014, IF-020, IF-026, IF-028, IF-032, IF-039. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | In DES-138 in the following interfaces, R0 is marked as mandatory, but not mandatory in Swagger - IF-006, IF-008, IF-014, IF-020, IF-026, IF-028, IF-032, IF-039. Update R0 to be mandatory in these interfaces. | Clarification | Minor | Interfaces | Swagger 1.5
MHHS-DIN-588 | ME |  | 2023-08-02 | Design Team |  | Kevin Spencer | Programme Design | Update of ID to Id | A request has come from Elexon to update the ISD Entities document. Id should be changed to ID |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | All instances of Id have been changed to ID (see also DIN 557) | Supporting Document | Minor | Supporting Document | MHHSP_EDI021_ISD_Entities v5.3.2
MHHS-DIN-589 | SB |  | 2023-08-02 | Stark | 2466 | Jon Dennis | Data Service Provider | ADS and SDS Estimation Statements | I have been studying the following two documents: Advanced Data Service Validation and Estimation: Methodology Statement (MHHSP-METH002_ADS_Validation_Estimation v5.1) Smart Data Service Validation and Estimation: Methodology Statement (MHHSP-METH001_SDS_Validation_Estimation v5.1) In particular, Section 3 of the ADS_Validation_Estimation document details the estimation methods where the customer has opted-out of UTC Period consumption data. It references the SDS_Validation_Estimation document where Estimation methods are in Section 7. The 2 method statements have become misaligned when changes to the SDS method statement was updated. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | We will align the ADS method statement with the SDS method statement to keep it uniform. | Method statement correction | Supporting Docs | Method Statement | ADS Method Statement
MHHS-DIN-590 | KH |  | 2023-08-03 | Design Team | 2717 | Martin Freeman | Central Body | Update Role Codes in E2E001 | There is a mismatch between roles codes that are in DES-138 and those that are in E2E001. Role code for Unmetered Supplies Data Services changed from UDS to UMSDS. Need to ensure that all of the role codes referenced in DES-138 are included in E2E001 and that there is a full explanation of what these are. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update all the role codes referenced in DES-138 to ensure they are included in E2E001 and that there is a full explanation of what these are. | Data interface correction | Supporting Docs | Interface Catalogue | E2E001 E2E Architecture Document
MHHS-DIN-591 | KH |  | 2023-08-03 | Elexon | 2974 | Michael Ceney | Central Body | Update to MDS Method statement | The MDS Method Statement Section 2.1 should read: If today > MDS Run Date (RF) for SP End Date/Time [DI-082] in the Master Settlement Table in ISD ECS1003 - SP End Date/Time [DI-082] has already passed "MDS Run Date (RF) [ISD.RunDate-RFDate] |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update DES138 and MDS Method Statement Section 2.1 to read "If today > MDS Run Date (RF) for SP End Date/Time [DI-082] in the Master Settlement Table in ISD ECS1003 - SP End Date/Time [DI-082] has already passed "MDS Run Date (RF) [ISD.RunDate-RFDate]" update ECS1003 in 00-introductions and IF-21 | Data interface correction | Supporting Docs | Supporting Docs | MDS Method Statement MHHSP-DES138-Interface Catalogue
MHHS-DIN-592 | SW |  | 2023-08-03 | Design Team | 2717 | Martin Freeman | Central Body | Update StatusMessage and StandardResponseBody in E2E001 to provide more clarity | There are inconsistencies between StatusMessage / Standard Response body definitions for what is contained with E2E001 and Swagger, these need to be aligned. Clarity needs to be provided on how TransactionID is populated in Status Message for Level 2 validation and Level 4 validation and for Level 4 validation, how this is sent to original sender. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Align inconsistencies between StatusMessage / Standard Response body definitions for what is contained with E2E001 and Swagger. Provide clariry on how TransactionID is populated in Status Message for Level 2 validation and Level 4 validation | Data interface correction | Supporting Docs | Interface Catalogue | E2E001 MHHSP-DES138-Interface Catalogue
MHHS-DIN-593 | ME |  | 2023-08-04 | Design Team |  | Kevin Spencer | Programme Design | Update to AC Method Statement | Update required to the AC Method Statement to amend calculation where less than 365 days of data is available and a change to section 2.2 to allow calculations to be undertaken on Calendar days |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | The following changes below in red have been made to section 2.2 of the AC Method Statement The Market-wide Data Service (MDS) should schedule the calculation of MPANs requiring a new Annual Consumption for active MPANs evenly across each working day of the month and publish on the day the day of the calculation. The recalculation shall be performed each month, for every MPAN and every 30 Calendar days +/- 5 Calendar days of the date of the previous calculation. Changes to the calculation of less than 365 days available are no longer reuried as agreed with Helix | Method statement correction | Supporting Docs | Method Statement | Annual Consumption Meth 10
MHHS-DIN-594 | SC | SCS DI-207 | 2023-08-04 | Design Team |  | Sean Cooper | Programme Design | Correction to BP10 Related MPANs | Rejection was incorrectly shown being sent direct from REGS rather than from REGS Via DIP. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Rejection was incorrectly shown being sent direct from REGS rather than from REGS Via DIP. moved the starting point from step 340 to step 360 for rejections on BP010B | Process Model correction | MPAN Ownership | Supporting Document | BP010-Registration Updates
MHHS-DIN-595 | SC | SCS DI-208 | 2023-08-04 | Design Team |  | Sean Cooper | Programme Design | Correction of Type in ISD Doc Table 16 | Correction of type in definition of subscript 3 for table M16 - "Market Participant ID" changed to "Market Participant Role" |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Correction of type in definition of subscript 3 for table M16 - "Market Participant ID" changed to "Market Participant Role" | Clarification | Supporting Docs | supporting document | MHHSP_EDI021_ISD_Entities
MHHS-DIN-596 | SC |  | 2023-08-04 | Design Team |  | Sean Cooper | Programme Design | Clarification of SP Appointment Time(s) | Per DRG decision all SP Appointment times shall be effective from Midnight UTC Time. Clarification added to IF-031/If-036 |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Added validation rule to IF-031 to ensure appointments are made at midnight [UTC/Clock]. Pending agreement from Working Group and DAG. | Clarification | Supporting Docs | Interfaces | DES-138 Interface Spec
MHHS-DIN-597 | SC | SCS DI-193 | 2023-08-07 | MHHS |  | Sean Cooper | SRO Design | IF-026 B068 Presence | IF-026 / B068 - SCS requested removal of wording "must be required for smart meter removed" as this is inherent as part of the Event Type. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | IF-026 / B068 - SCS requested removal of wording "must be required for smart meter removed" as this is inherant as part of the Event Type. | Clarification | Supporting Docs | Interface Catalogue | DES-138 Interface Spec
MHHS-DIN-598 | SC | SCS DI-176 | 2023-08-07 | St Clements |  | Madison Layton | Software Provider | Incoming Supplier Notifications - Clarification | SCS raised a query around whether certain flows should be copied to an incomming Supplier (PUB-006, PUB008 etc. etc.) The current design does not include copying of these flows to an incoming supplier, (not represented in either Requirements or BP maps). IF-036 (and accompanying D-flows as required) provides suppliers with a clear starting point containing all the information they need to support servicing the customer. Design Team feel any change in this area would require a CR. |  | Closed | [7 empty] | Any change in this area would require changes to the REGS Requirements to implemnt Primary Routing, as copying of such flows could not be performed by DIP Secondary Routing. CR would be required to confirm new requirements and allow for IA on REGS and Suppiers design. Design Team also note that no other issues/DIN raised on this issue, by suppliers or other participants. | Clarification | Clarification - No change Required
MHHS-DIN-599 | BK | SCS DI-198 | 2023-08-07 | St Clements |  | Madison Layton | Software Provider | Data Cleansing required on IHD, SMSO and Installation Date | SCS raised a a query on the three items below that are not under the Data Cleanse Plan that may need cleanse work. 1) IHD - Should be populated for smart meters, and only smart meters (not currently validated) 2) SMSO - Should be populated for smart meters and only smart meters (not currently validated) 3) Installation date - Should not be prior to MPAN Creation date (Legacy data integrity issues of meters migrated into MPRS) |  | Closed | [7 empty] | This change has been forwarded onto the Data Cleansing Working Group as it is not a design issue. Design Team also advised SCS to raise these issues within the working group. | Clarification | Clarification - No change Required
MHHS-DIN-600 | ME |  | 2023-08-07 | Elexon | 4566 | Rashmi Radhakrishnan | Central Body | ISD Entity M18 Discrepancy | In the ISD Entity Document the table shows {Effective From Date {DIPRole} and {Effective To Date {DIPRole}, however the exmaple table and column details have been titled as {Effective From Date {MP2DPM} and {Effective To Date {MP2DPM}. These should be changed to align with the first table in entity M18 |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Corrected M18 Col Headings and column name references to read "DIPRole" | Data interface correction | Supporting Docs | supporting document | MHHSP_EDI021_ISD_Entities
MHHS-DIN-601 | SW |  | 2023-08-07 | Kraken | 4485 | Adrian Serban | Software Provider | Incorrect on M0 common block in IF-018 | In Swagger, it appears the block is correct (M0), but the label is incorrect (M1) for IF-018. The label needs to be updated to M0 to align with the block. This needs to be updated in Swagger so the label is incorrect. In IF-019 and IF-020, there is an inconsitency of use of M1 vs M0. |  | Closed | [7 empty] | M1 is used in IF-019 and IF-20. M0 is used in all other IFs where required. Swagger version 1.4 has been reviewed and correctly reflects this position. | No Change
MHHS-DIN-602 | RG |  | 2023-08-08 | Design Team |  | Rob Golding | Programme Design | Add Interface, Event Code enumeration to Swagger for interface blocks | Interface and Event code validation and alloawable blocks is missing from the DIP. Rather then getting Avanade to code these dependencies the proposal is to intoduce the restrictions into the Swagger |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update the swagger for the majority of interfaces where different event codes require different combinations of optionality for the blocks they reference. An example of this has been done already for IF-001 in the new swagger file Interface-001. | Improved error trapping at interface | Minor | Interfaces | Swagger 1.5
MHHS-DIN-603 | SW |  | 2023-08-09 | Design Team | 4022, 4700 | Steve Weston | Central Body | Clarity on A0 block being removed | Section 4.2.1 of the E2E001 design has a diagram that shows that the A0 common block is removed by the DIP prior to sending out the message to onward particpants. This is inconsistent with the rest of the design. Section 4.2.1 needs to be updated so that this shows A0 not being removed. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update Section 4.2.1 of E2E001 figure 4 so that this shows A0 not being removed | Design Ambiguous | Supporting Docs | E2E Architecture Document Swagger 1.4 | E2E001 E2E Architecture Document Swagger 1.5
MHHS-DIN-604 | SW |  | 2023-08-09 | Design Team | 4945 | Steve Weston | Siemens | Clarity on B066 mandatory on IF-035 | In DES-138, B066 block in IF-035 is shown as mandatory and also defined as mandatory in Swagger. This should be conditionally mandatory as per B019, so this needs to be updated to conditionally mandatory in DES-138 and also in Swagger 1.5. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update B066 block in IF-035 to mandatory where event code DCC-MDR Outcome Swagger 1.5, no change in DES138 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-605 | SC |  | 2023-08-09 | Design Team |  | Sean Cooper | Programme Design | Update "Switch Cancellation" Info Message Box of BP002 & BP003 | Message updated to make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations received prior to PUB-34 processing will be managed by normal queue processing. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Message updated to make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Where in the rare scenario a cancellation is received and accepted by the Registration Service before the PUB-034, the Registration Service will not lapse on receipt of the cancellation, instead re-validation the day prior to the appointment start date would trigger a lapse. | Clarification | MPAN Ownership | process | BP002 / BP003 Change of SP
MHHS-DIN-606 | SC |  | 2023-08-09 | Design Team |  | Sean Cooper | Programme Design | Update Ops C to include clarification on issuing of IF-035 | Make it clearer that IF-035 will be issued prior to queue processing but only in cases where PUB-034 has already been processed. Cancellations received prior to PUB-34 processing will be managed by normal queue processing. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update OPS Choreography document (Foot-note to OPC-190) to clarify processing of IF-035 (See DIN-605) | Clarification | Supporting Docs | Supporting Document | MHHSP-OPC001 Operational Choreography
MHHS-DIN-607 | SC |  | 2023-08-10 | St Clements |  | Sean Cooper | Programme Design | Update IF-035 Lapsed Reason Code | SCS Request Update IF-035 Lapsed Reason Code from "Switch Cancelled" to "Registration Cancelled" |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Updated IF-035 Lapsed Reason Code LP004 from "Switch Cancelled" to "Registration Cancelled" | Clarification | Minor | Interfaces | DES-138 Interface Doc
MHHS-DIN-608 | SC | SCS DI-206 | 2023-08-10 | St Clements |  | Sean Cooper | Programme Design | Correction of Inaccuracy on BP003 | Steps 86,87,88 added to better reflect that REGS will actually send TWO IF-035 messages not just one. IF-035 [SendMTD] will be issued to Incumbent MS and [AppOutcome] event will be issued to DS/Supplier. BP003 now mirrors the drafting in BP002. There is no change in underlying requirement here - redrafting is simply a more accurate representation of REGS activity. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Steps 86,87,88 added to better reflect that REGS will actually send TWO IF-035 messages not just one. IF-035 [SendMTD] will be issued to Incumbent MS and [AppOutcome] event will be issued to DS/Supplier. BP003 now mirrors the drafting in BP002. | Clarification | Minor | Interfaces | BP003
MHHS-DIN-609 | SC |  | 2023-08-10 | Helix |  | Sean Cooper | Programme Design | Helix Issuing of IF-040 Annual Consumption Messages | Discussion held with Helix on proposed approach to issuing IF-040 messages. Current design suggests that messages should only be issued on Working Days - Design Team are exploring why this is the case (risk of substantial peak esp on 4 day long weekends). preference would be for Helix to issue IF-040 on each calendar day. |  | Implemented |  |  |  |  | 2023-09-13 | Interim Release 5 | 2023-09-20 | Update the OpsC document to set a 24hr rather than a 2hr limit around processing the IF-040 interfaces only | Clarification | Supporting Docs | Supporting Document | OPS Choreography
MHHS-DIN-610 | SC |  | 2023-08-10 | Helix |  | Sean Cooper | Programme Design | Clarification of IF-013 Functionality (also ref 572) | 1. IF-013 is only issued as part of the RF Run i.e. simply to notify Suppliers of what the default consumption for a period(s) is, where no data has been submitted by the DS come the point of RF. … … Should suppliers wish to derive this for pre-RF settlement runs then they are able to do so easily enough using the own data and the published Load Shapes. Need to validate if IF-013 should be issued after each Settlement Run OR only after RF Run. Also need to validate the IF-10 should NOT be issued after II Run. 2. The second view is that the IF-013 is issued on every settlement run undertaken for sites where no PUB-021 data has been received DIP impact concerns wrt to volumes of IF-013 would need to be addressed if Option 2 is the position. Dupe with DIN-572 |  | Implemented |  |  |  |  | 2023-09-13 | Interim Release 5 | 2023-09-20 | Following Review at DRG meeting - agreement reached that IF-013 should NOT be sent for the II Run and should only be issued for SF and later Runs. DES-138 IF-013 Additional notes updated to reflect this decision. ----- MDS Method statement also requires update to record this decision. The following text has been added to the Method Statement Restrict sending of IF-013 until the SF Settlement Run The following statement has been added to the MDS Method Statement section 9.2 The sending of IF-013 will be restricted until the SF Settlement Run | Clarification | Supporting Docs | Supporting Document | DES-138 Interface Catalogue MDS Method Statement
MHHS-DIN-611 | KH |  | 2023-08-11 | Elexon | 3986 | Michael Ceney | Central Body | Changes required to MDS Method Statement | Following the release of DIN-332, changing EventCode [ConsumptionOnDe-energisedMpan], the MDS Method Statement needs updating to reflect this change. Section 9.3 states that the an exception report will be provided using IF-013, this needs to show IF-014 is to be used. Please can a new DIN be raised. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | We will update section 9.3 to state that the report will be provided using IF-014. | Method statement correction | Supporting Docs | Method Statement | MDS Method Statement
MHHS-DIN-612 | SC | PDA Test Issues | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | New IF-019 Validation Rules Re Unmetered Related MPANs | Added x2 new validtion rules to prevent the creation / addition of Related MPANs with a Connection Type of "U - Unmetered". No validation applied to remove so as to allow for the resolution of any historically erroneous links |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Added x2 new validation rules to prevent the creation / addition of Related MPANs with a Connection Type of "U - Unmetered". No validation applied to remove so as to allow for the resolution of any historically erroneous links | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-613 | SC |  | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Remove Reference to SP Appointment Start Time(s) | In line with DRG Decision on 4th Aug - it was agreed that ALL Service Provider Appointments should commence at Midnight UTC. Text against DI-086 and DI-121 has been removed. A new section addressing the treatment of Time has been added to the Additional Information tab of DES-138 |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | In line with DRG Decision on 4th Aug - it was agreed that ALL Serive Provider Appointments should commence at Midnight UTC. Text against DI-086 and DI-121 has been removed. A new section addressing the treatment of Time will be added to the Additional Information tab of DES-138 as part of Interim Release 5 (DIN-614) | Design Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-614 | SC |  | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | Create new "Time" Advisory Notes in Registration Additional Info Section | SC to create Treatment of Time section |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Add clarification on Regs Notes tab. around appointment time and Transfer read time. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-615 | SC |  | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Number of Registers Validation | Clarification following on from DIN-574. Text against Number of Register Digits fields amended to say "per the manufacturer specification" . Note text for SCS validation will remain unchanged. Swagger validation of this field updated to match SCS logical test ie value can be 0-9 |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | Clarification following on from DIN-574. Text against Number of Register Digits field amended in IF-002, IF-005, IF-006, IF-033, to say "per the manufacturer specification". Note text for SCS validation will remain unchanged. Swagger validation of this field updated to match SCS logical test ie value can be 0-9. | Design Clarification | Minor | Interface Catalogue | DES-138 Interface Catalogue
MHHS-DIN-616 | SC |  | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | Review of COS Transfer of Readings Process Required in light of SP UTC Decision | A Review of BP003C is required to impact assess implications of SP UTC Decision |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | BP003C may need updating follow impact assessment | Clarification | Supporting Docs
MHHS-DIN-617 | SC | PDA Test Issues | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | Note on Discretionary Use of IF-023/IF-040 by Data Service | Missing interface notes on Discretionary Use of IF-023/IF-040 by Data Service |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Added interface notes to clarify Annual Consumption usage in IF-040 and Load Shape Totals in IF-023 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-618 | KH |  | 2023-08-15 | ESG | 5859 | Patricia Parker | Software Provider | Updating routing within DES138 - PUB-026 | Could you please clarify what updates the Metering Service will receive via the PUB_026. From the routing the only update is re the SCCandProfile Class. However, BP010C alludes to the MS receiving an update for the SMSO - could you please confirm which is correct? |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | To update PUB-026 adding XMSC to the SMSO secondary routing. | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-619 | SC | PDA Test Issues | 2021-08-14 | MHHS |  | Sean Cooper | SRO Design | Draft Umetered Change of Energisation Status Business Process Map | Update BP08 existing or draft Unmetered Specific version. |  | Closed | [7 empty] | Pending feedback from PDA on UMS process. No feedback provided - closed
MHHS-DIN-620 | SC | Test Issues | 2021-08-14 | Design Team |  | Sean Cooper | Programme Design | Remove EES as a Recipient of IF-001 | Remove EES as a Recipient of IF-001 | CR028 | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Removed EES as a Recipient of IF-001 - EES gets this info from CSS | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-621 | SC |  | 2023-08-17 | MHHS |  | Sean Cooper | SRO Design | Changes to D303 DTN Flow | Need to make "Manufacture and Type" non mandatory in the D303 flow. Follow migration to MHHS it is possible that this data item is not held in REGS and therefore not shared with all MHHS Participants incl. MS who currently would need to provided it on the D303. Discussions were held in Data Working group around back population of this data item but that proposal was REJECTED - therefore only other option is to make this field optional in D303 |  | Implemented | No |  | Design gap | TBC |  | Interim Release 8 | 2024-03-20 | Passed to Matt McK to add to existing industry CP changes.
MHHS-DIN-622 | SC | SCS | 2023-08-17 | St Clements |  | Sean Cooper | SRO Design | DIP Validation of Sender Correlation ID | Implement DIP validation to check for incorrect population of Sender Correlation ID. |  | Closed | [7 empty] | CR would be required for the DIP to implement Sender Correlation ID validation. Decision to implement Level 3/4 Sender Correlation ID validation is with the recipient. | Clarification
MHHS-DIN-623 | SC | SCS | 2023-08-17 | St Clements |  | Sean Cooper | Programme Design | Change IF-001 Routing | Add SUPL (Linked Supplier) as an additional Primary Receipient of Inital Registration Event |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Add SUPL (Linked Supplier) as an additional Primary Receipient of Inital Registration Event for IF001 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-624 | ME |  | 2023-08-18 | Design Team |  | Miriam Ellis | Programme Design | BP013 DDE Updates | MHHS test team have identified discrepancies within the ECS BPM's that require updates to align with the ECS reports. Updates are required to BPM13 DDE |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Updates to BPM013: 1. Update reference of MHHS-REP-001 to ELEX-REP-001 in BP header 2. Update reference of REP-005 to ELEX-REP-005 in BP header 3. Reference of MHHS-REP-002A included with BP header 4. Reference of REP-002 changed to ELEX-REP-001 | Clarification | Supporting Docs | Reporting Catalogue | BPM013
MHHS-DIN-625 | SC | DI-210 | 2023-08-18 | St Clements | 6221 | Sean Cooper | Programme Design | B092 should also be an array to allow MPRS to populate multiple rejections | B092 should also be array to allow MPRS to populate multiple rejections |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Consider breaking out DI-980 into an array in B092 block of IF-035. Block B099 added containing DI-979 and DI-980 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue Swagger 1.5
MHHS-DIN-626 | SC | ESG | 2023-08-22 | ESG |  | Sean Cooper | Programme Design | Update Routing of IF-003 | Routing of this flow should match that of the IF-037 - in that a copy should also be sent to the Supplier. IF-003 Routing table updated to show Supplier as being a receipient of the iF-003 |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Routing of this flow should match that of the IF-037 - in that a copy should also be sent to the Supplier. IF-003 Routing table updated to show Supplier as being a receipient of the iF-003 | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-627 | SC | ESG | 2023-08-22 | ESC |  | Sean Cooper | Programme Design | Update Interface Doc "Correlation ID Required" to "Correlation ID Created" | Inconsistancy indentified in the column headings across different IFs. All should read "Correlation ID Created" as this column denotes if the DIP IF should create/copy a DIP Correlation ID value or not. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update Interface Doc "Correlation ID Required" to "Correlation ID Created" | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-628 | SC |  | 2023-08-23 | Design Team |  | Sean Cooper | Programme Design | Add in Missing IF-021 Validation | Add NEW validation to ensure that "UTC Settlement Date" has time of Midnight UTC. Added clarification to existing validation rule that time element of "Settlement period end date time" should align with Settlement period duration |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Add NEW validation to ensure that "UTC Settlement Date" has time of Midnight UTC. Added clarification to existing validation rule that time element of "Settlement period end date time" should align with Settlement period duration | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-629 | MF |  | 2023-08-25 | Design Team |  | Mike Fensome | Programme Design | Routing for SUPC on IF-037 | To ensure that the outgoing Supplier are correctly notified of de-appointment of their Service Providers, routing rules for SUPC updated to Primary routing for IF-037 |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | SUPC routing moved from Secondary to Primary for IF-037 for all events | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-630 | MF |  | 2023-08-25 | Design Team | N/A | Mike Fensome | Programme Design | Remove incorrect arrow on BP002 | Arrow incorrectly added into BPOO2 between steps 225 and steps 245 |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Arrow between steps 225 and steps 245 on BP002 removed. Previously added in error. | Process Model correction | Minor | Interfaces | BP002
MHHS-DIN-631 | SC |  | 2023-08-29 | MHHS | N/A | Sean Cooper | SRO Design | Swagger Alignment - Block B051 | Required Data Items field names do not match those specfied in the defintion. |  | Implemented | [5 empty] | Interim Release 4 | 2023-08-16 | loadShapeGSPGroup and loadShapeDomesticPremiseIndicator added to Required fields section to align with block definition. | Correction | Minor |  | DES-138 Interface Cat
MHHS-DIN-632 | SC |  | 2023-08-31 | Helix | N/A | Sean Cooper | SRO Design | Header & Footer Requirements for ISD Entity Files | ISD Specification should be updated to include specification/definition of a standard Header and Footer to be applied to each ISD Entity CSV file. |  | Initial Assessment/Updating | No |  | Design gap | Helix, Suppliers |  | Post Go-live Release | 0 | Decision required on exact content/structure of Header ... Is a footer required? If so what should it include (eg number of Entity entries) | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-633 | SC |  | 2023-08-31 | Helix | N/A | Sean Cooper | Programme Design | Update to ISD E45 | Update Entity 45 - Market Role code needs to allow Blanks in order to align with other tables in ISD and to provide for [new] Market Participants who dont have a legacy market particpant role code |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update Entity 45 - Market Participant Role code needs to allow Blanks (Optional) in order to align with other tables in ISD and to provide for [new MHHS] Market Participants who dont have a legacy market participant role code | Clarification | Supporting Docs | Supporting Document | MHHSP_EDI021_ISD_Entities
MHHS-DIN-634 | KH |  | 2023-09-01 |  | 6616 | Tym Huckin | Consultancy | Update UMSDS Method Statement with correct comments for Null value | In row 2, where we have a "live" summary but it is de-energised, it says to put "A" actual data flag and use Estimation Reason Code "7", but the DI-076 column in that row says this should be Null. |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | In 10.1 the table states in row two that the "Estimation Reason code" is Null and therefore the comments column will be updated to: If a D0388 has been received with load associated data and the MPAN is de-energised the load should be calculated, submitted as ‘A’ Flagged but with an Estimation Reason Code of Null | Correction | Supporting Docs | Method Statement | UMSDS Method Statement
MHHS-DIN-635 | RG |  | 2023-09-04 | Design Team |  | Rob Golding | Programme Design | Status Code needs tidying in StandardResponseBodyType | 4In the “StandardResponseBodyType” definition, there is a required property called "statusCode" that is not listed among the properties. Could you please address this inconsistency? |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Simple update | Data interface correction | Swagger |  | Swagger
MHHS-DIN-636 | SC |  | 2023-09-04 | Design Team |  | Sean Cooper | Programme Design | Removal of YAML Name Fields from Data Catalogue | Following discussions agreement to remove YAML fields from Data Catalouge. Swagger will be the definitive reference for the Jason/Yaml property labeling etc. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Following discussions agreement to remove YAML fields from Data Catalogue. Swagger will be the definitive reference for the Json/Yaml property labelling etc. | Data interface correction | Supporting Docs | Interface catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-637 | RG |  | 2023-09-04 | Design Team |  | Rob Golding | Programme Design | Data Catalogue items incorrectly use maximum and minimum | String need to be range bounded by maxLength & minLength |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update swagger so that maxLength and minLength are used instead of maximum and minimum | Dat Interface correction | Swagger |  | Swagger
MHHS-DIN-638 | RG |  | 2023-09-04 | Design Team |  | Rob Golding | Programme Design | Block: D0, Field: serviceTicketURL. DES138 specifies 'string max 225', Swagger specifies 'string max 250' | Set to 250 in DES 138 |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | DES138 update, 01-Data Catalogue & 02- DIP Common : Block: D0, Field: serviceTicketURL (DI-978) set to 250 | Data interface correction | Supporting Docs | interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-639 | RG |  | 2023-09-04 | Design Team |  | Rob Golding | Programme Design | DI-138-Customer-Direct-Contract-Data-Service-DIP-ID & DI-140-Customer-Direct-Contract-Metering-Service-DIP-ID to be nullable | Update both to be nullable |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update swagger so that DI-138-Customer-Direct-Contract-Data-Service-DIP-ID & DI-140-Customer-Direct-Contract-Metering-Service-DIP-ID are DT-006N, i.e. nullable | Data interface correction | Swagger |  | Swagger
MHHS-DIN-640 | RG |  | 2023-09-05 | Design Team |  | Sean Cooper | Programme Design | Custom Block: B022, Field: Metering Point Postcode. Interface Catalogue specifies CMO as ‘M’ for IF-018, all other interfaces specify CMO as ‘O’. | Update DES138 so that all versions are the same and marked as optional Custom Block: B022, Field: Metering Point Postcode. Interface Catalogue specifies CMO as ‘M’ for IF-018, all other interfaces specify CMO as ‘O’. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update DES138 so that all versions of B022 are the same and fields marked as optional | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-641 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | Custom Block: B022, Field: Metering Point Postcode. Interface Catalogue specifies no min length, but min length of 6 specified in Swagger. | Update swagger to align |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update swagger to align minlength removed from DT007(N) | Data interface correction | Swagger |  | swagger
MHHS-DIN-642 | RS |  | 2023-09-05 | MHHS | 7382 | Rob Golding | SRO Design | NFR0045 Performance Efficiency | this NFR does not clearly define how the DIP will throttle participants where connection are over a mutually shared mTLS connection. Shared mTLS connections will be used by many parties such as DIP Connection Providers, the requirement to use them being placed on parties that will be Placing Reliance on a Connection Provider. Effectively, this means that multiple parties will use the mTLS connection and which, under certain circumstances could see significant increases over that mTLS if more than one party’s message volumes increased. |  | Closed | No | [6 empty] | This item is being managed as part of the DIP work-off plan
MHHS-DIN-643 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | B029 Fields marked as mandatory | B029 Condtitonal mandatory marked as required. Block will be conditional |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update DES138 & swagger | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue Swagger
MHHS-DIN-644 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | DI-122 Profile Class has a minLength of 2 in Swagger. | add minLength clause |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update swagger DI-122 Profile Class to minLength =2 in swagger | Data interface correction | Swagger |  | Swagger
MHHS-DIN-645 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | Clarify 'AllRoles' for DIP routing for IF-047 | Update to include MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update DES138 IF-047 so that all roles are specified (MSA, ADS, SDS, MSS, UMSO, UMSDS, REGS, SUP, LDSO, EES) | Data interface correction | Supporting Docs | Interface Catalogue | MHHSP-DES138-Interface Catalogue
MHHS-DIN-646 | RG |  | 2023-09-05 | Design Team |  | Rob Golding | Programme Design | DT-002N-MPAN requires a minLength of 13 | add minLength clause |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update DT-002N-MPAN to min length & max length 13 in swagger | Data interface correction | Swagger |  | Swagger
MHHS-DIN-647 | RG |  | 2023-09-06 | Design Team |  | Rob Golding | Programme Design | Replace reportId with interfaceId in the ECS reports | Replace reportId with interfaceId in the ECS reports to make S0 block consistent across all reports/interfaces |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update swagger & MHHSP - ERI011B - ECS Reports - External v5.4 | Reporting correction | Supporting Docs |  | MHHSP - ERI011B - ECS Reports - External Swagger
MHHS-DIN-648 | KH |  | 2023-09-06 | St Clements |  | Vicki Holland | Software Provider | DI-496 data item | This data item was given a max value of 48, however the max value should be 50 to allow for the clock change day in October which has 50 settlement periods. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | All settlements reports will be in clock time and can have 46, 48 or 50 Settlement Periods. DI-496 is INT(3) to allow for a change to 15 minute Settlement Periods which would require a value of 100 for the Autumn Clock Change in the future. Maximum value in Swagger and ECS Reports to be updated to 50 for half hourly settlement periods. | Reporting correction | Supporting Docs | interface catalogue | MHHSP - ERI011B - ECS Reports - External MHHSP - ERI011A - ECS Reports - Internal Swagger
MHHS-DIN-649 | SC |  | 2023-09-06 | MHHS |  | Sean Cooper | SRO Design | REGS-EES 'Refresh' Flow - IF-051 | Following discussion with SCS and EEC - proposed definition of refresh message iF-051 |  | Closed | [7 empty] | Initial draft reviewed by EES and SCS - revisions to follow. Closed as duplicate - refer to DIN-051
MHHS-DIN-650 | BK |  | 2023-09-06 | Design Team |  | Rob Golding | Programme Design | Introduction of Compressed Payloads into DIP Messages | Detailed analysis of the some of the ECS reports, specifically REP003, has found that some of the reports can potentially grow to a very large size ~ 12MB. Within MHHS message design there is a notional upper limit for the size of messages which is 1MB, and hence these messages will exceed this constraint. | CR030 | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | The proposal is that the Sender (ECS) compresses the report and base64 encodes the data into the CustomBlock. The recipient will know that a specific message flow is compressed, and hence will need to decompress the payload. The proposal is to use gzip for the compression. This new pattern for compressed payloads will be initially introduced for the following reports: REP-002 LDSO report for DUoS – aggregated data REP-002A Embedded Network report for DUoS – aggregated data REP-003 BM Unit Allocated Demand Volumes to Market Participants REP-004 Supplier Deemed Take Report REP-006 Aggregated Uncorrected volumes by CCC to Market Participants REP-007 VAS Exception Report to Suppliers and BSCCo REP-008 MDS Exception Report to LDSOs REP-009 EMRS Report for Suppliers A covering statement has been included within the Introduction tab of ECS reports which highlights the changes made to Swagger. | Data interface correction | Technical Artefact | Technical Artefact | Swagger 1.5 MHHSP - ERI011A - ECS Reports - Internal
MHHS-DIN-651 | MH |  | 2023-09-07 | MHHS |  | Kevin Spencer | SRO Design | Supplier Registration of ABMU/ MPAN mapping | There is a design gap around Supplier ABMU Mapping held by ELEXON. Suppliers will need to register their MPAN/ ABMU Mappings for MHHS. Currently, they send a D0297 to HHDAs to provide the Mapping and can populate the SVA Metering Service Register for MSID Pairs where they are used in the Balancing Mechanism using the P0278 and self-service via ELEXON Kinnect. The issue is that for MHHS the export might be with one Supplier and the import with another. The validation in Kinnect only supports a pair being submitted mapping both import and export to the ABMU. Likewise, the P0278 only supports the provision of MSID pairs. We think a new flow may be needed or the D0297 re-routed to PMP. |  | Closed | No |  | Design gap | Helix | 2024-01-12 |  |  | Pending Helix raising a Change Request
MHHS-DIN-652 | RG |  | 2023-09-07 | Design Team |  | Rob Golding | Programme Design | DI-091-Number-Of-Displayed-Register-Digits update in DES138 to reflect the range 0-9 | DI-091-Number-Of-Displayed-Register-Digits update in DES138 to reflect the range 0-9 |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update DI-091 in the data catalogue to have the correct min (0)/ max(9) values | Data interface correction | Supporting Docs | Interfaces | DES138 - Interface Doc
MHHS-DIN-653 | RG |  | 2023-09-07 | Design Team |  | Rob Golding | Programme Design | MO block removed from IF-047 | MO block removed from IF-047 |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | M0 block removed from IF-047 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-654 | RG |  | 2023-09-07 | Design Team |  | Rob Golding | Programme Design | DI-130 RMP and DI-131 MP status maxlength | Reduce maxlength to align with eumerated type (50->1) |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Max length updated to 1 in Swagger for DI-130 RMP and DI-131 MP status | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-655 | RG |  | 2023-09-08 | Design Team |  | Fredrik Omland | Software Provider | Add a set no additional properties to false | Adding a set no additional properties condition to the swagger objects improves the validation |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Add "additionalProperties: false" to all schema objects in swagger so that no additional properties / fields can be attached to an object that are not specficied in the schema. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-656 | SW |  | 2023-09-11 | Design Team |  | Steve Weston | Central Body | All S1 properties to be mandatory | Ensure all S1 properties are mandatory as per DES-138 in Swagger 1.5 |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Ensure all S1 properties are mandatory nullable as per DES-138 in Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-657 | ME |  | 2023-09-11 | Design Team |  | Miriam Ellis | Programme Design | NEW ISD Entity | A request has come in from St Clements requesting for a New ISD entity which lists settlement period quality indicators, with a mapping to an actual or estimate indicator. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | ISD Entity M19 Settlement Period Quality Indicators has been added to the ISD entity document. | Data interface correction | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-658 | ME |  | 2023-09-12 | Design Team |  | Miriam Ellis | Programme Design | Updates to ERI011B | Following an internal review of the external ECS reports a few discrepancies have been highlighted that need to be amended |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Changes to ECS External Reports 1. MHHS-REP-006: Block R051 Demand Disconnection Event Details - parent updated to R032 2. Data Catalogue: Format of DI-492, 496, 487, 488, 484 updated to reflect MHHS Data Type | Design Ambiguous | Supporting Docs | Various documents | ECS Reports
MHHS-DIN-659 | RG |  | 2023-09-12 | Design Team |  | Rob Golding | Programme Design | Update REP007 | Update REP007 to include blocks R007 |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update REP007 to include blocks R007 | Design Ambiguous | Supporting Docs | Various documents | Swagger 1.5
MHHS-DIN-660 | ME |  | 2023-09-12 | St Clements | 4513 | Vicki Holland | Software Provider | Supplier version of REP-002 | St Clements are requesting for one report per supplier MPID that covers all combinations of distributor and GSP group. The current solution for REP-002 is a supplier will receive a report per distributor id |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | REP002 has been split into two separate reports. There is now a Supplier version (MHHS-REP-002) and an LDSO Version (MHHS-REP-002B). Due to this change the MDS BPM/BPD (019) and DDE BPM/BPD (013) have also been updated to include the reference of REP-002B | Reporting correction | Supporting Docs | Various documents | MHHSP - ERI011B - ECS Reports - External v5.4 BP013 Demand Disconnection BPM/BPD v5.1 BP019 Market-wide Data Service BPM/BPD v5.1
MHHS-DIN-661 | RG |  | 2023-09-13 | IMSERV |  | Liam Lowey | Software Provider | Use of the term 'GUID' in messages | Messages are referring to "Device ID" data items as "GUID". For example "GPFGasGUID" in IF-004. However, a Device ID is not a GUID which is 128 bit number with a specific format. The Wikipedia article for GUID gives more information. Instead, Device IDs are 64 bit. This is misleading to implementors and maintainers. Could the naming of the properties be changed to reflect the identifier better? For example this appears to be a collection of 8 bytes in hexidecimal, i.e. a 64-bit quantity or 8 octets. Much like a MAC address or EUI64 for DCC is. Do you have other identifiers like this that require definition could we standardise on a different name for all of them? |  | Closed | [7 empty] | No further action taken
MHHS-DIN-662 | SW |  | 2023-09-14 | Design Team |  | Steve Weston | Programme Design | Update Sort Code and Account Number validation | DT-035-Sortcode and DT-035-Bank Acount Number have incorrect min / max Lengths. Sort Code should be min 6, max 8 with a regex applied for validation. Account number should be min 8 and max 10, with a regex for extra validation |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | DT-035-Sortcode and DT-035-Bank Acount Number have incorrect min / max Lengths. Sort Code should be min 6, max 8 with a regex applied for validation. Account number should be min 8 and max 10, with a regex for extra validation. This needs to be updated in ER011B and Swagger 1.5 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-ERI011B- ECS Reports
MHHS-DIN-663 | SW |  | 2023-09-14 | Design Team |  | Steve Weston | Programme Design | There are missing regular expressions that would improve the swagger schema validation | There are various data types that would benefit from regex added to improve validation. In addition, there could be new data types created / regex added to improve consistency and validation. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | There are various data types that would benefit from regex added to improve validation. In addition, there could be new data types created / regex added to improve consistency and validation. This needs to be updated in Swagger 1.5. The proposed regexes are for the following data types/items: DT-002 MPAN - DT-026 Group Correction Factor DT-027 MPID | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-664 | SC |  | 2023-09-14 | St Clements |  | Sean Cooper | SRO Design | Message [Error] Status Message Addressing | Based on feedback from SCS review the Message Status section of E2E to make it clearer that the "Sender ID is system sending the error, so if MPRS was sending an error it would be the REG DIP ID And Recipient ID would be who you are sending the error to – so would be the S1.senderDIPID on the original message" |  | Closed | No |  | Design ambiguous | N/A |  |  |  | Clarified with SCS | Design Ambiguous | Supporting Docs | Supporting document | E2E001 - E2E Architecture Doc
MHHS-DIN-665 | SC |  | 2023-09-14 | St Clements |  | Sean Cooper | Programme Design | Tidy up Of "where available in Registration" usage | IF-001 / IF-002 /IF-036 Block 5 - Block 5 & IF-003 Blocks 095/096 & IF-033 Block 072 & IF-037 Block 10 and 11 heading had a note refering to Interface notes section which explained that block info may not always be availible. This was inconsistant with all other blocks which use the phrasing "Where Availible in the Regisration Service".... Block 5 updated to be consistant. IF Notes on each of these IF remain unaffected. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | IF-001 / IF-002 /IF-036 Block 5 - Block 5 & IF-003 Blocks 095/096 & IF-033 Block 072 & IF-037 Block 10 and 11 heading had a note refering to Interface notes section which explained that block info may not always be availible. This was inconsistant with all other blocks which use the phrasing "Where Availible in the Regisration Service".... Block 5 updated to be consistant. IF Notes on each of these IF remain unaffected. | Data interface correction | Supporting Docs | Interfaces | DES138 - Interface Doc
MHHS-DIN-666 | SW |  | 2023-09-15 | Design Team |  | Steve Weston | Programme Design | Data Type / Data Type Reference inconsistencies in DES-138. | Fix any IR5 Data Type / Data Type Reference inconsistencies between DES-138 & Swagger (between Data Catalogue Tab and IF / Common tabs) |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Fix any IR5 Data Type / Data Type Reference inconsistencies between DES-138 & Swagger (between Data Catalogue Tab and IF / Common tabs). Data Type Inconsistencies - DES-138 updates DI-000 is defined as a String 8, but in IF-040 and IF-045 this is defined as a String 6, so DES-138 has been updated to align. DI-019 is defined as a string 50 in IF-032, but in IF-034 and 36, is defined as String 10. In IF-035 this is blank. Updated IF-034, 35 and 36 so that DI-019 is a String 50. Swagger updated to align. DI-020 is defined as a string 50 in IF-032, but in IF-034 and 36, is defined as String 10. In IF-035 this is blank. Updated IF-034, 35 and 36 so that DI-020 is a String 50. Swagger updated to align. IF-023, B029, DI-026, DES-138 updated so Data Type is DT-003 to align with Swagger. IF-023, B035, DI-038, DES-138 updated so Data Type is DT-002 to align with Swagger. IF-023, B053, DI-041, DES-138 updated so Data Type is DT-016N to align with Swagger. IF-023, B053, DI-042, DES-138 updated so Data Type is DT-016N to align with Swagger. IF-023, B053, DI-044, DES-138 updated so Data Type is DT-016N to align with Swagger. IF-023, B053, DI-045, DES-138 updated so Data Type is DT-016N to align with Swagger. IF-033, B037, DI-075, DES-138 updated so Data Type is DT-002N to align with Swagger. IF-033, B037, DI-079, DES-138 updated so Data Type is DT-002N to align with Swagger. IF-050, B080, DI-111, DES-138 updated so Data Type is DT-003N to align with Swagger. IF-051, B080, DI-111, DES-138 updated so Data Type is DT-003N to align with Swagger. IF-050, B080, DI-112, DES-138 updated so Data Type is DT-003N to align with Swagger. IF-051, B080, DI-112, DES-138 updated so Data Type is DT-003N to align with Swagger. IF-014, B047, DI-147, DES-138 updated so Data Type is DT-016 to align with Swagger. IF-013, B049, DI-159, DES-138 updated so Data Type is DT-003 to align with Swagger. IF-003, B094, DI-159, DES-500 updated so Data Type is DT-003 to align with Swagger. IF-003, B008, DI-159, DES-813 updated so Data Type is DT-006 to align with Swagger. IF-003, B009, DI-159, DES-816 updated so Data Type is DT-006 to align with Swagger. DIP Common, D0, DI-986 removed Data Type from DES-138 and Swagger. Data Type Inconsistencies – Swagger updates IF-036, B068, DI-018 Swagger updated so Data Type is DT003N to align with DES-138. IF-051, B082, DI-023 Swagger updated so Data Type is DT003N to align with DES-138. IF-038, B021, DI-138, Swagger updated so Data Type is DT-006 to align with DES-138. IF-039, B021, DI-138, Swagger updated so Data Type is DT-006 to align with DES-138. IF-001, B006, DI-139, Swagger updated so Data Type is DT-006 to align with DES-138. IF-038, B020, DI-140, Swagger updated so Data Type is DT-006 to align with DES-138. IF-039, B020, DI-140, Swagger updated so Data Type is DT-006 to align with DES-138. IF-024, B058, DI-152, Swagger updated so Data Type is DT-016 to align with DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-667 | SW |  | 2023-09-16 | Design Team |  | Steve Weston | Programme Design | Mandatory / Optional blocks inconsistencies between DES-138 & Swagger | Fix any IR5 Mandatory / Optional blocks inconsistencies between DES-138 & Swagger |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Fix any IR5 Mandatory / Optional blocks inconsistencies between DES-138 & Swagger. Mandatory / Optional / Nullable Inconsistencies DIP Common, S1, DI-985 is Optional in Swagger and has been updated to be Mandatory to align with DES-138. DIP Common, S1, DI-996 is Optional in Swagger and has been updated to be Mandatory to align with DES-138. IF-013, B049, DI-161 is Optional in Swagger and has been updated to be Mandatory to align with DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-668 | SW |  | 2023-09-17 | Design Team |  | Steve Weston | Programme Design | Nullable / Optional Data Type / property inconsistencies between DES-138 & Swagger | Fix any IR5 Nullable / Optional Data Type / property inconsistencies between DES-138 & Swagger |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Fix any IR5 Nullable / Optional Data Type / property inconsistencies between DES-138 & Swagger. Nullable / No nulls Inconsistencies DI-988 is nullable in DES-138 but no nulls in Swagger, so Swagger to be updated so it is nullable to align with DES-138. DI-123 is nullable in DES-138 but no nulls in Swagger, so Swagger to be updated so it is nullable to align with DES-138. DI-150 is nullable in Swagger, to be updated in Swagger so this is Mandatory no nulls to align with DES-138. DI-018, update DES-138 so value is Mandatory nullable to align with Swagger. DI-138, update DES-138 so value is Mandatory nullable to align with Swagger. DI-023, DI-026 update DES-138 so value is Mandatory nullable to align with Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-669 | SW |  | 2023-09-18 | Design Team |  | Steve Weston | Programme Design | Min / Max Values inconsistencies between DES-138 & Swagger | Fix any IR5 Min / Max Values inconsistencies between DES-138 & Swagger |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Fix any IR5 Min / Max Values inconsistencies between DES-138 & Swagger. Min / Max Inconsistencies DI-019 update Swagger max length to be 50 to align with DES-138 DI-218 update Swagger to align with DES-138 min / max values. DI-300 update Swagger to align with DES-138 min / max values. DI-081 update DES-138 to have a max of 30 to align with Swagger. DI-091 update DES-138 to have a max of 9 to align with Swagger. DI-152 update DES-138 to have a max length of 13 to align with Swagger. DI-161 update DES-138 to align with Swagger value of 9999999. DI-167 update DES-138 to align with Swagger min / max values. DI-168 update DES-138 to align with Swagger min / max values. DI-190 update DES-138 to align with Swagger max value of 50. DI-194 update DES-138 to align with Swagger max value of 50. DI-990 update DES-138 to align with Swagger max value of 65. DI-992 update DES-138 to align with Swagger max value of 10. DI-081 update DES-138 to have a min of 30 to align with Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 MHHSP-DES138-Interface Catalogue
MHHS-DIN-670 | SW |  | 2023-09-15 | Design Team |  | Steve Weston | Programme Design | Unclear whether webhook URL's accept ports | Need to make it clearer in E2E design and Swagger whether port numbers are allowed in webhook / URLs and any formatting / options for environments |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Need to make it clearer in E2E design and Swagger whether port numbers are allowed in webhook / URLs and any formatting / options for environments E2E001 Section 4.5 updated | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5 E2E001
MHHS-DIN-671 | ME |  | 2023-09-22 | Elexon | 11203 | Rashmi Radhakrishnan | Central Body | Updates to ISD Entities | 1. Make it clear what the data type/length is for Line Loss Factor Identifier. It is currently unclear as it reads 3 characters 2. Following consultation feedback of BSCP707, ISD Entity 23 requires an update to include the word 'Duration' and update to the character length and inclusion of date format |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | 1. Update to ISD Entity M3 - update the length/data type of Line Loss Factor Identifier. Now reads as Up to 3 characters 2. Update to ISD Entity 23 - include the word 'Duration' to Settlement Period. This now reads Settlement Period Duration (Description). Update the data type/length to 50 characters and include a date format of YYYY-MM-DD | Design Ambiguous | Supporting Docs | EDI021 ISD Entities | MHHSP_EDII021_ISD_Entites 5.3
MHHS-DIN-672 | SW |  | 2023-09-19 | Design Team |  | Steve Weston | Programme Design | B033 has 9 required fields, but only available. Naming is also inconsistent for some of the required fields that do not exist. | B033 has 9 required fields, but only 8 are available. Naming is also inconsistent for some of the required fields that do not exist. Swagger needs to be updated to align with available fields and DES-138 mandatory values. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Fix any values in Swagger than do not align with required fields and ensure number of required fields aligns with number of fields available. -metering point postcode removed from required fields in B033 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-673 | RG |  | 2023-09-21 | Design Team |  | Rob Golding | Programme Design | Floating Point number regexes | DIN 267 inadvertently updated regexes to a pattern which does not align to the agreed format as of Technical Design Working Group Work-Off Issue D-0408th November 2022. The regexes need to align to what was agreed. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Update regex patterns for the following data types: DT-016, DT-022, DT-023, DT-024, DT-025, DT-030, DT-031, DT-032, DT-033 | Data interface correction | Supporting Docs | Interfaces | Swagger 1.5
MHHS-DIN-674 | SW |  | 2023-09-22 | ESG | 11369 | Kerry O'Donnell | Software Provider | Inconsistent Text description for DI-086 | In the Data Catalogue, DI-086 has a Text Description of "Supplier Effective From Date" but on IF-001 and IF-037, DI-086 has a text description of "Incoming Supplier Effective From Date" |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | In the Data Catalogue, DI-086 has a Text Description of "Supplier Effective From Date" but on IF-001 and IF-037, DI-086 has a text description of "Incoming Supplier Effective From Date". IF-001, IF-037, IF-051 have been updated so that the text description for DI-086 now matches Data Catalogue and Swagger - "Supplier Effective From Date". | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue
MHHS-DIN-675 | SC |  | 2023-09-25 | Design Team |  | Sean Cooper | Programme Design | IF-021 IF Consistency Validation Rules | New IF-021 Validation Rules with supporting Error Codes created to ensure validity of IF-021. New Error codes are : ECS1015 - Estimation Reason Code Cannot be Null & ECS1016 - Consumption Amendment Reason Codes Cannot be Null |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | New IF-021 Validation Rules with supporting Error Codes created to ensure validity of IF-021. New Error codes are : ECS1015 - Estimation Reason Code Cannot be Null & ECS1016 - Consumption Amendment Reason Codes Cannot be Null | Missing/incorrect validation rule | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue
MHHS-DIN-676 | RS |  | 2023-09-25 | St Clements | 11291 | Rob Golding | SRO Design | CR-018 NFR Change - E2E1009 | There are some NFRs that need tweaking post CR-018 Approval to align with the Registration Service Operating hours - Ie E2E1009. Given that MPRS sits behind an Adapter and does not operate 24/7 (as per CR-018) level 4 processing will operate in the same timeframes as Level 5. It needs tweaking to align with the CR-018 wording of: DIP messages received by the SMRS will be processed between the hours of 05:00 to 18:00 and 21:00 to 23:00 Working Days only. Messages received outside of these hours will be held in a queue until the next processing window. Automated responses to inbound messages (including Level 4 Validation) are expected to be returned within 60 minutes of receipt during the specified operating hours. |  | Closed | No |  | Design ambiguous | DIP Users, DIP |  |  |  | This DIN is superceded by CR039.
MHHS-DIN-677 | MF |  | 2023-09-26 | Utiliteam |  | Mike Fensome | Programme Design | Additional information added to IF-020 for Linked MPANs | On linking MPAN's, information is missing in IF-020 ( as provided in IF-002 ) to allow participants to interpret the flow. This needs adding to IF-020. Swagger updated accordingly |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | Agreed with SCS, for Import / Export Events ONLY, to add in the blocks that are present in the IF-002 namely B035 Linked MPANs / B-036 Linked Meter Info / B-075 MAP Info to IF-020. | Data interface correction | Supporting Docs | Interfaces | MHHSP-DES138-Interface Catalogue Swagger 1.5
MHHS-DIN-678 | ME |  | 2023-09-27 | Elexon | 11684 | Rashmi Radhakrishnan | Central Body | ISD Entities Updates | 1. Entity M14- Master settlement time table Fields: LSS Run Date, Payment Date & Notification Date should be changed to an Optional field. 2. Entity M18- Inconsistencies between M16 field name “ DIP Role Code” and M18 Field name “DIP Market Role”. Two different Field name used. 3. Entity M9 and M10, it appears that the data type length specified in the ISD EDI021 document for Field Unit Description 1, 2, and Manufacturers Designation might not be sufficient based on the data samples. – Datatype/length of these fields needs increasing. |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | 1. Entity M14- Master settlement time table Fields LSS Run Date, Payment Date, Notification Date all changed to Optional field. 2. DIP Role Code in Entity M16 updated to DIP Market Role 3. Entity M9 and M10, data type/length for Unit Description 1, 2, and Manufacturers Designation have been incresed to 100 characters | Design Ambiguous | Supporting Docs | EDI021 ISD Entities | MHHSP_EDII021_ISD_Entites
MHHS-DIN-679 | SC |  | 2023-09-27 | SRO Design |  | Sean Cooper | Elexon | MHHS Process for Additional BMU's Required | Clarification is required around how Additional BMU's will be requested, created and managed under MHHS |  | Closed | No | [6 empty] | Duplicate of MHHS-DIN-651 | No Change
MHHS-DIN-680 | ME |  | 2023-09-27 | St Clements | 11538 | Vicki Holland | Software Provider | Update to DI-322/DI-323 MHHS data type | The MHHS Data types for DI-322 and DI-323 requires an update to align with the SVA data catalogue as these 2 data items are reported to 9 decimal places. Swagger will also need to be updated to align with the ECS reports |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Updated MHHS data types and definitions for DI-322 and DI-323 within the ECS Data catalogue and where it appears in the reports. The Min and Max values have also been updated due to the change in data type. This change has been made in Swagger. Data types have been updated to a String 20(±9.9). | Reporting correction | Supporting Docs | ECS Reports Swagger REP003 version 010 | MHHSP - ERI011B - ECS Reports - External MHHSP - ERI011A - ECS Reports - Internal Swagger
MHHS-DIN-681 | SW |  | 2023-09-28 | ESG | 11492 | Kerry O'Donnell | Software Provider | DI-824 textual decsription in the Interfaces is inconsistent with the textual description in the Data Catalague | DI-824 textual description (Column D) in the Interfaces is inconsistent with the textual description (Column D) in the Data Catalogue. This DIN is to ensure the textual description is consistent in the Interfaces to the Data Catalogue and that found in Swagger. |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Textual description corrected on IF-036 to align with other interfaces | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-682 | MF |  | 2023-09-28 | CGI |  | Dave Webster | Data Service Provider | Remove commissioning flows sent to Data Service on BP009 | BP009 is misaligned with the Data Service requirements and incorrectly shows the Advanced Data Service receiving Commissioning Flows (D0383 and D0384) |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Removed commissioning flows sent to Data Service on BP009 (D0383 and D0384 into step 175). Note BPD was already correct. Updated BRS002 - MHHS-BR-MS-062 accordingly | Process Model correction | Supporting Docs | Process model correction Business requirements | BP009 BRS002
MHHS-DIN-683 | SW |  | 2023-09-28 | Flui | 11487 | Jason Jackson | Software Provider | E2E refers to T0 and Transaction Wrapper which are no longer required | E2E refers to T0 (section 4.8.2) and Transaction Wrapper (section 5.5) which are no longer required. This needs to be updated in the E2E design and an update provided in relation to Swagger and how this works. |  | Implemented | [5 empty] | Interim Release 5 | 2023-09-20 | E2E001 updated to reflect replay design | Design Ambiguous | Supporting Docs | Interfaces | E2E001
MHHS-DIN-684 | ME |  | 2023-10-03 | SRO Design |  | Kevin Spencer | SRO Design | Addition of REP-003A | As part of the Tranche 1 Transition Design and following approval from DAG a new report has been included within ECS Reports, MHHS-REP-003A. The intention is to retain the existing data flows in transition for the non-migrated MPANs and send the new DIP Flows or DTN flows for the migrated MPAN. This is due to the change in the CCCids which have different characteristics in the new world. The ELEX-REP-003A has been developed such that the CCC totals across migrated and non-migrated MPANS can be presented. Suppliers with MPANs in both Legacy and MHHS can expect: D0296 – just legacy data – as now, pipe delimited dataflow received via the DTN REP-D0296 – just MHHS data – still a pipe delimited dataflow received via the DTN – will have a new Dxxxx identifier REP-003 – just MHHS data – a JSON message received via the DIP REP-003a – both legacy and MHHS data – a JSON message received via the DIP |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Inclusion of MHHS-REP-003A to the ECS reports. Swagger has been updated to align with ECS reports catalogue with new reports interface REP-003a and associated common block, custom block and data catalogue items as per reports catalogue. | Reporting correction | Supporting Docs | ECS Reports Swagger REP003A version 001 | MHHSP - ERI011B - ECS Reports - External Swagger
MHHS-DIN-685 | BK |  | 2023-10-04 | RECCo |  | Sarah Jones | Central Body | Data Item Names and Descriptions | As part of the interface tranche of MHHS code drafting, RECCo has reviewed the information contained within the MHHS Interface Catalogue (DES138) and the ECS Reporting Catalogue (ERI011B) and identified a number of areas where changes to the data item names and descriptions should be progressed in order that these better align to existing code terminology and data item descriptions. We have identified five areas where changes should be made. 1) In the MHHS data catalogue, a number of discrepancies have been identified where the data item name or description is slightly different to the Energy Market Data Specification. In response to this we are either proposing to: a. amend the existing Energy Market Data Specification data item name and / or description via the MHHS code drafting work, or b. change to the data item name and / description in the MHHS data catalogue. 2) We have identified MHHS data items with the same name as existing data items, but a different data format. In particular, data items used to define effective from dates have been established for MHHS as a high resolution datetime data type. To avoid ambiguity / confusion for users, we are proposing to amend the data item description for MHHS date related data items to reflect that they are recording a data and time. 3) The data item used to link to CSS registration activity has been incorrectly referenced as the CSS Registration Request Id. This should be amended to the CSS Registration Id (DI90043) to avoid confusion with the CSS Registration Request Id which is a separate data item (DI90050). 4) The data item (MHHS DI-048) used to identify the meter manufacturer has been established with a different name and description from the existing data item (J0410). This should be amended to the Manufacturers Make and Type to avoid confusion. (Alternatively, if this is expected to be an entirely new data item, then the reference to J0410 should be removed and clarity provided on what data should be used to populate the field). 5) Correct minor typographical errors within the data item names and / or descriptions. | CR024 | Open - awaiting assessment | No |  | Change Request | All Participants |  | Post Go-live Release | [5 empty] | DES138 Swagger
MHHS-DIN-686 | BK |  | 2023-10-04 | RECCo |  | Sarah Jones | Central Body | DIP Interface Name Changes | As part of the interface tranche of MHHS code drafting, RECCo has reviewed the information contained within the MHHS Interface Catalogue (DES138) and identified a number of areas where changes to the DIP interface names should be progressed in order that these better align to enduring code terminology. In order to translate the MHHS interface catalogue (in the DES138) into the Energy Market Data Specification, RECCo is seeking to align MHHS interface names to enduring code terminology to avoid future inconsistencies. To meet this aim, we have identified four areas where changes should be made. 1) Removal of references to Metering Service within the interface name. Existing terminology will be retained e.g. MEM in the REC and MOA in the BSC. 2) Replacement of references to Service Providers with Supplier Agents within the interface name, Existing terminology will be retained with Data Services and Metering Services defined as Supplier Agents in both the BSC and REC. 3) Replacement of references to Registration / Registration Service with SMRS. To differentiate from the CSS and ERDS, following agreement with BSCCo that DIP interfaces fall under the scope of the SMRS. 4) Replacement of references to CSS De-Registration with CSS Registration De-Activation to reflect REC code terminology. | CR025 | Open - awaiting assessment | No |  | Change Request | All Participants |  | Post Go-live Release | [5 empty] | DES138 Swagger
MHHS-DIN-687 | ZH |  | 2023-10-04 | SI Design |  | Zakir Hussain | SI Design | BP003 updates are missing on BPD003 | For DIN-608 changes there were new steps added to the diagram, these have not been covered in the relevant BPD doc. This includes the new steps being referenced, descriptions, flows etc. |  | Initial Assessment/Updating | No |  | Error/Correction | N/A |  | Post Go-live Release | 0 | Add missing BP003 updates to BPD003 | Process Model correction | Supporting Docs | Process model correction | BPD003
MHHS-DIN-688 | ZH |  | 2023-10-04 | SI Design |  | Zakir Hussain | SI Design | BP010E updates are not included in BPD10 | BP10E has not been included in the relevant BPD10 doc. |  | Initial Assessment/Updating | No |  | Error/Correction | N/A |  | Post Go-live Release | 0 | BP010E updates are not included in BPD010 | Process Model correction | Supporting Docs | Process model correction | BPD010
MHHS-DIN-689 | RG |  | 2023-10-05 | SRO Design |  | Rob Golding | SRO Design | Minor updates to DES138/Swagger for Sims& Ems audit | Minor differences between DES138 & swagger from sims & ems audit |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Incorporate differences between DES138 & swagger from sims & ems audit | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-690 | SC |  | 2023-10-09 | SRO Design |  | Sean Cooper | SRO Design | IF Optionality Matrix - MDR | Updated MDR IF Optionality Matrix to reflect correct values per current CR23 Design. Existing Values were not correct |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Updated MDR IF Optionality Matrix to reflect correct values per current CR23 Design. Existing Values were not correct for MDS | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-691 | SC |  | 2023-10-06 | SRO Design |  | Sean Cooper | SRO Design | DI-138 / DI-140 Customer Direct Contract Holder(s) | DI-138 / DI-140 Customer Direct Contract Holder(s) - Changed to Data Type DT006N in DES138 to correctly align with Swagger |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | DI-138 / DI-140 Customer Direct Contract Holder(s) - Changed to Data Type DT006N in DES138 to correctly align with Swagger | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-692 | SC |  | 2023-10-06 | SRO Design |  | Sean Cooper | SRO Design | DI-161 Settlement Run Number | DI-161 Settlement Run Number - made mandatory in IF-013 to correctly align with Swagger |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | DI-161 Settlement Run Number - made mandatory in IF-013 to correctly align with Swagger | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-693 | SC |  | 2023-10-06 | SRO Design |  | Sean Cooper | SRO Design | DI838 Supplier Nominated Consent | DI838 Supplier Nominated Consent - DES138 Updated to show as Nullable (Swagger already aligned) |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | DI838 Supplier Nominated Consent - DES138 Updated to show as Nullable (Swagger already aligned) | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-694 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | Update IF-007-EnergisationStatusChange event code | Update event code [EnergisationStatusFailure] to [EnergisationStatusChange] for IF-007-EnergisationStatusChange |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Update event code [EnergisationStatusFailure] to [EnergisationStatusChange] for IF-007-EnergisationStatusChange | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-695 | SC |  | 2023-10-06 | SRO Design |  | Sean Cooper | SRO Design | IF Optionality Grid - LDSO | LDSO IF Optionality - PUB-009 Corrected from NonApplicable to Optional = YES PUB-013 Corrected from NonApplicable to Optional = YES PUB-026 SSCProfileClass Corrected from N/A to Optional = YES PUB-040 Corrected from N/A to Optional = YES REGS: PUB019 Related MPAN Events corrected from N/A to Optional = No |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | LDSO IF Optionality - PUB-009 Corrected from NonApplicable to Optional = YES PUB-013 Corrected from NonApplicable to Optional = YES PUB-026 SSCProfileClass Corrected from N/A to Optional = YES PUB-040 Corrected from N/A to Optional = YES REGS: PUB019 Related MPAN Events corrected from N/A to Optional = No | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-696 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | IF-018 mandatory blocks for Energy Direction & NUM Indicatory | Add B023 is required for IF-018-EnergyDirection and IF-018-MUMIndicator |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Add B023 in IF-018-EnergyDirection and IF-018-MUMIndicator | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-697 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | Add required fields to IF-023 | Add required field to custom block in IF-023 |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Add required field to custom block in IF-023 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-698 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | Add required field to IF-040 | Add B059 to required field in IF-040 |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Add B059 to required field in IF-040 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-699 | RG |  | 2023-10-06 | SRO Design |  | Rob Golding | SRO Design | IF-036 DSAppActive optional B068 block | Remove B068 from required fields for IF-036 DSAppActive |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Remove B068 from required fields for IF-036 DSAppActive | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-700 | RG |  | 2023-10-09 | SRO Design |  | Rob Golding | SRO Design | Recipient ID specified twice in replay/requeue API | Remove recipient id from request body of API call as already specified on path |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Remove recipient id from request body (in the MessageRequest object) of API call as already specified on path. This applies to replay and requeue API endpoints. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-701 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarification on population of IF-036 | Clarification on population of IF-036 participant ID's |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Provided clarification on IF-036 Interface notes on how B005, B016 and B017 are populated by Registration Service | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-702 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarification on use of calendar days for validation rules in IF-025 and IF-034 | Update validation rules to clarify that days refer to calendar days in IF-025 and IF-034 |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | IF-025 and IF-034 validation rules updated to clarify using calendar days | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-703 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarify that B032 is only sent where available in Registration Service | Clarify that B032 is only sent where available in Registration Service in IF-001, IF-002, IF-033 and IF-036 |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Updated B032 to show as sent where available in Registration Service in IF-001, IF-002, IF-033 and IF-036 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-704 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Updated DI-135 and DI-136 to be set to Mandatory in IF-025/IF-026 | Update DI-135 and DI-136 to be set to Mandatory in IF-025/IF-026 and to be non-nullable, so that a date is always provided for SMSO and IHD even where setting the value to null. |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Updated DI-135 and DI-136 to be set to Mandatory in IF-025/IF-026 and to be non-nullable | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-705 | MF | DI-214 | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarify that sending of [IMS-SendMTD] event code on IF-035 should also apply in the case of SEG | Clarified that SEG scenario applies for requirement MHHS-BR-RS-019 to send [IMS-SendMTD] event code on IF-035 |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Added that SEG scenario applies for requirement MHHS-BR-RS-019 to send [IMS-SendMTD] event code on IF-035 in BRS003 | Requirement correction | Supporting Docs | Business Requirements | BRS003
MHHS-DIN-706 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Remove Unmetered check for de-linking Linked Export MPANs (IF-019) | Clarified that Unmetered check will not apply for [LinkedImportExportRemove] event in IF-019 |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Updated validation rules so that Unmetered check will not apply for [LinkedImportExportRemove] event in IF-019. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-707 | MF |  | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | Clarification on Primary routing for IF-033 | Updated IF-033 to show primary routing is to XMSP and XDSP |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Updated IF-033 to show primary routing is to XMSP and XDSP | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-708 | RG |  | 2023-10-09 | SRO Design |  | Rob Golding | SRO Design | IF-004 B093 block is mandatory | Audit of swagger IF-004 B093 block is mandatory |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Update IF-004 B093 block to mandatory | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-709 | RG |  | 2023-10-09 | SRO Design |  | Rob Golding | SRO Design | IF-021 and IF-014 custom block differences | IF-021/14 have different structure, ideally they should be the same - the B045 block does not need to be an array |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Aligned IF-014 to IF-021 so that multiple B045 blocks are not allowed | Data interface correction | Supporting Docs | Interfaces IF-014 version 010 | DES138, Swagger 1.6
MHHS-DIN-710 | RG |  | 2023-10-09 | SRO Design |  | Rob Golding | SRO Design | IF-016 requires update to include IF-013 variant | IF-016 definition needs to include replayed IF-013 data. |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | At present in DES-138 only the IF-021/14 variants are described in the IF-016 data, this needs to be extended to include the IF-013 variant. This change has been to be reflected in the Swagger. Added validation rules and response codes to IF-015 to be included in IF-016. | Data interface correction | Supporting Docs | Interfaces IF-015 version 010, IF-016 version 010 | DES138, Swagger 1.6
MHHS-DIN-711 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | IF-035 Obsfucation/routing contradiction | IF035 – MDS & LDSO are mentioned in the obfuscation column, however, there is no routing rule for these roles |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Removed LDSO and MDS from obsfuscation rules as LDSO/MDS do not receive IF-035 | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-712 | MF | DI-181 | 2023-10-09 | St Clements |  | Mike Fensome | SRO Design | De-appointment and re-appointment date order | Set de-appointment and re-appointment dates to D and D+1 for requirements RS-128.7 and RS-128.8 for Data Service appointments to align with DIN-383 (Metering Service appointments) |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Discussed with SCS and agreed to update Registration Service requirements to De-appoint on D (MHHS-BR-RS-128.7) and appoint on D+1 (MHHS-BR-RS-128.8) as part of auto-alignment process | Requirement correction | Supporting Docs | Business Requirements | BRS003
MHHS-DIN-713 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | Rel 1.2.1 S1 updates in swagger | SenderRoleId & SenderTimestamp updated in required section in S1 object to fix problem introduced in v1.2 |  | Implemented | [5 empty] | Interim Release 2.1 | 0 | Update sentTimestamp to senderTimestamp, senderRole to senderRoleID in S1 block | Data interface correction | Supporting Docs | Various documents | DES-138 Interface Catalogue Swagger 1.2.1
MHHS-DIN-714 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | Rel 1.2.1. B033 updates in swagger | Remove meteringPointPostcode from required section of B033 object |  | Implemented | [5 empty] | Interim Release 2.1 | 0 | Update B033 remove meteringPointPostCode from B033 | Data interface correction | Supporting Docs | Various documents | DES-138 Interface Catalogue Swagger 1.2.1
MHHS-DIN-715 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | Rel 1.2.1. D091 update | DI-091 update maximum: 1->9, minimum 1->0 |  | Implemented | [5 empty] | Interim Release 2.1 | 0 | Update DI-091-Number-Of-Displayed-Digits to maximum 9 and minimum 0 in the Swagger. Including updates to 01-Data Catalogue, IF-002, IF-005, IF-006, IF-033 in the Interface Catalogue to align with Swagger. | Data interface correction | Supporting Docs | Various documents | DES-138 Interface Catalogue Swagger 1.2.1
MHHS-DIN-716 | ME |  | 2023-10-10 | Elexon | 13809 | Rashmi Radhakrishnan | Central Body | Update to ISD entity 23 | Additional text provided within the Settlement Period Duration (Description) field requires removal as the correct text has been added |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Desription within Settlement Period Duration (Description) has been updated. The reference for a Settlement period, unique within Settlement Date. Periods ID s are assigned sequentially to each period in local time day The duration of a Settlement Period in minutes | Design Ambiguous | Supporting Docs | EDI021 ISD Entities | EDI021 ISD Entities
MHHS-DIN-717 | RG |  | 2023-10-10 | SRO Design |  | Rob Golding | SRO Design | LSS needs to be removed from the obsfucation column in DES138 - IF001 | LSS does not recieve IF-001 and therefore should not referenced in the obsfucation column |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Removed LSS from obsfucation rules in IF-001 as only issued to MDS which is already covered by obsfucation | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-718 | ME |  | 2023-10-11 | Elexon | 14165 | Derek Weavering | SRO Design | MHHS-Rep-D0296 alignment with Ddddd Supplier BM Report | A review of the DAG approved MHHS-DEL1613 DES-196 D-Flow and Interface Mapping Supplementary Documents has identified the following: The current Supplier BM Unit Report (D0296) considers all the GSPs that the supplier operates in a single file). However the Ddddd specs in the ECS catalogue and D flow documentation suggest a single file for each supplier’s GSP. We are building ( within Helix) using the current approach where all GSPs appear in the same file. Please can this be raised with the team to ensure the specs also reflect the same |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | MHHS-REP-D0296 has been updated to align with the Ddddd Supplier BM Report. The following link: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx has also been included to the following reports (D0081, D0266, D0276 and D0296) to direct participants to what should be used as the Master version of each report as defined in DTC format. | Reporting correction | Supporting Docs | ERI011B ECS Reports-External | ERI011B ECS Reports-External
MHHS-DIN-719 | MF |  | 2023-10-11 | Utiliteam |  | Mike Fensome | SRO Design | Update to DI-103 Configurable Register Id to min length of 1, max length of 2 | Allow Configurable Register ID's (DI-103) to be provided with min length of 1 and max length of 2 in both swagger and DES138 so that, for example, either 1 or 01 are accepted. |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Updated Data Catalogue for DI-103 (Configurable Register ID) to Min length of 1 (from 2) and updated Swagger accordingly. Added REGEX to Swagger. Regex takes the form ^\d{1,2}$ | Data interface correction | Supporting Docs | Interfaces | DES138, Swagger
MHHS-DIN-720 | MF |  | 2023-10-11 | Utiliteam |  | Mike Fensome | SRO Design | Update to DI-122 Profile Class to min length of 1, max length of 2 | Allow Profile Class (DI-122) to be provided with min length of 1 and max length of 2 in both swagger and DES138 so that, for example, either 1 or 01 are accepted. |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Updated Data Catalogue for DI-122 (Profile Class) to Min length of 1 (from 2) and updated Swagger accordingly. Added REGEX to Swagger. Regex takes the form ^\d{1,2}$ | Data interface correction | Supporting Docs | Interfaces | DES138, Swagger
MHHS-DIN-721 | JW |  | 2023-10-11 | Migration Design |  | John Wiggins | Programme | Control needed with MPID's associated to a metering role | For a metering company, only one limited company can ever own an MPID related to one of the three metering roles. Elexon need a control to say that an MPID associated to a metering role can never be owned by more than one company |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Updated ISD Entity 45 with the following comment "Where an MPID is related to the following Market Roles: Meter Operator, Advanced MOA or Smart MOA, the MPID and Market Role combinations must always be assigned to the same Company ID." | Missing/incorrect validation rule | Supporting Docs | ISD Entities | ISD Entities
MHHS-DIN-722 | RG |  | 2023-10-12 | SRO |  | Rob Golding | SRO Design | Remove Recipient Roles from A0.always object. | Remove Recipient Roles from A0.always object as roles are always resolved to DIP Ids |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Update Swagger to remove Recipient Roles from A0.always | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-723 | RG |  | 2023-10-12 | SRO |  | Rob Golding | SRO Design | OffPeakDeclarationProportion spelt on B097 spelt incorrect | OffPeakDeclarationProportion spelt 'OffPeakDeclatationProportion' on B097. |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Updated spelling in Swagger so that 'OffPeakDeclarationProportion spelt 'OffPeakDeclatationProportion' on B097. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-724 | RG |  | 2023-10-12 | SRO |  | Rob Golding | SRO Design | DT-000 Interface ID to include REP-002A & IF-004 | DT-000 Interface ID to include REP-002B & IF-004 as they are missing |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Add REP-002B & IF-004 to the enumerated list for DT-000 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-725 | RG |  | 2023-10-12 | SRO |  | Rob Golding | SRO Design | Add individual interface endpoints into the swagger | Add individual interface endpoints into the swagger as this would improve schema validation and better error messaging |  | Closed | [7 empty] | Following a review with the DIP Provider, these changes will not be made in Swagger and error handling will remain as per the IR5 design. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.7
MHHS-DIN-726 | ME |  | 2023-10-13 | SRO | 14120 | Miriam Ellis | SRO Design | DataType/Example errors in ECS reports data catalogue | A number of errors have been highlighted by Elexon following a review of the updated ECS data catalogue V5.4. There are errors that require an update |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Updates to data types and examples for a number of data items have been made within the data catalogue as well as where the data items appear in each of the documented reports | Reporting correction | Supporting Docs | ER1011B ECS Reports External ER1011A ECS Reports Internal | ER1011B ECS Reports External ER1011A ECS Reports Internal
MHHS-DIN-727 | MF |  | 2023-10-13 | SRO |  | Mike Fensome | SRO Design | Add new routing path for IF-041 | Added routing to give Data Service ability to send on-site read to Supplier |  | Implemented | [5 empty] | Interim Release 5.1 | 0 | Added [ReadingOnSite] to routing table for Data Service in IF-041 |  |  |  | DES138
MHHS-DIN-728 | ME |  | 2023-10-17 | SJW | 13832 | Sarah Jones | Consultancy | DES138 and ECS Reports misalignment | As part of our work developing the interface code drafting, we have noticed that the S0 Block in the interfaces defined in the DES138 differ from those in the ECS Reporting Catalogue. Specifically, the DES138 includes Schema Version in the S0 block and the ECS Reporting Catalogue does not. Our expectation was that blocks would be identical across the various interfaces. |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | All new MHHS ECS reports now includes Schema Version in the S0 blocks. | Reporting correction | Supporting Docs | ERBI011B ECS Reports - External | ERBI011B ECS Reports - External
MHHS-DIN-729 | SW |  | 2023-10-17 | SI Design |  | Steve Weston | SI Design | DI-838 to include null on the enum values | DI-838 in Swagger is mandatory nullable and this is an enumerated list so needs to include null in the enumeration to ensure this aligns to DES_138. |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Updated Swagger DI-838 to ensure that null is a value in the enumerated list given this is a mandatory nullable field so that this now aligns to DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.6
MHHS-DIN-730 | ME |  | 2023-10-17 | Elexon | 13443 | Rashmi Radhakrishnan | Central Body | Update to Company name in Entity 1 | Within Entity 1 of ISD Entities - Market Participant ID there is a character limit of 100 for Registered Company Name but this is not sufficient and require this to be updated to allow up to 160 characters to align with company house. |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | The character limit for Registered company name within Entity 1 of ISD Entities document has been increased to 160 | Design Ambiguous | Supporting Docs | ISD Entities | ISD Entities
MHHS-DIN-731 | RG |  | 2023-10-18 | Elexon |  | Nigel Rees | Central Body | Swagger does not resolve ECS reports | Since the ECS reports are now compressed in DIP messages the ECS report strcutre is not resolved in the swagger. |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Added a field to each ECS payload that defines the structure of the corresponding report. This will be an optional item, hence not populated, however it will present the resolved structure of the report. | Design Ambiguous | Supporting Docs | Interfaces All REPs are now version 007 | Swagger 1.6, ER1011B ECS Reports External
MHHS-DIN-732 | RG |  | 2023-10-19 | SRO |  | Rob Golding | SRO | Routing update on IF-026 not updated | DIN-415 was meant to correct the routing on IF-026 - its still incorrect. The routing for event code [SSCandProfileClass] points to EES, LLS- this should be LSS. The header also needs to align - it currently states Central Settlements (MDS), it should be Central Settlements (LSS) |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Typo corrected LLS changed to LSS | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-733 | SC |  | 2023-10-19 | RECCO |  | Jonnny Moore | Recco | Update IF-026 Routing for Change of Consent | EES does not hold consent information - changed routing to remove EES as a receipient of Consent Info |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | EES does not hold consent information - changed routing to remove EES as a receipient of Consent Info in IF-026 | Design Ambiguous | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-734 | SC |  | 2023-10-19 | RECCO |  | Jonnny Moore | Recco | Update IF-018 Routing for Dom Premise Indicator | EES does not hold consent information - changed routing to remove EES as a receipient of DPI Info |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | EES gets DPI information from CSS - changed routing to remove EES as a receipient of DPI Info in IF-018 | Design Ambiguous | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-735 | MF |  | 2023-10-19 | Drax |  | Georgina Mahoney | Drax | Remove referene to BP007 as input into BP002 and BP003 | Disconnections is not an input into Change of Service Provider, BP007 should be removed from the entry processes. |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Removed BP007 as an entry process to BP002 and BP003. De-appointment of Service Providers is covered in BP007. | Process Model correction | Supporting Docs | Process model correction | BP002 BP003
MHHS-DIN-736 | ZH |  | 2023-10-19 | SI Design |  | Zakir Hussain | SI Design | Removing step 36 from BP003 | Step 36 was included initially as part of an earlier DIN but is no longer relevant and therefore needs replacing. |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Remove Step 36 and flow from BP003, including any reference to the step in the latest BPD3 Doc | Process Model correction | Supporting Docs | Process model correction | BP003 and BPD003
MHHS-DIN-737 | RS |  | 2023-10-19 | ESG |  | Patricia Parker | Software Provider | Custom Block: B022, Field: Metering Point Postcode min length in Swagger | Interface Catalogue specifies no min length, but min length of 6 specified in Swagger. Min length should be 5 for areas such as Liverpool |  | Closed
MHHS-DIN-738 | SC |  | 2023-10-19 | St Clements |  | Sean | SRO Design | Update Schema Version Data Item DI-992 Length | Interfaces across DES-138 need updating to show Schema Version DI-992 as String 10 rather than string 3 |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | DES-138 updated in individual interface to show Schema Version DI-992 as String 10 rather than string 3 | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-739 | SC |  | 2023-10-19 | St Clements |  | Sean | SRO Design | Validation of Supplier DIP ID / MPID for IF-035 [SDS-MDRUpdate] | Add validation in IF-034 to ensure that Supplier DIPID and MPID provided matches that of the current supplier held in the registration service - return new Error of REG1084 if this is not the case. |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | Add validation in IF-034 to ensure that Supplier DIPID and MPID provided matches that of the current supplier held in the registration service - return new Error of REG1084 if this is not the case. | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-740 | SC |  | 2023-10-19 | St Clements |  | Sean | SRO Design | IF-018 Routing | DS added as a recipient of IF-018 [DCCEnrolment] |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | DS (XDSC) added as a recipient of IF-018 [DCCEnrolment] in the Secondary Routing | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-741 | MF |  | 2023-10-19 | St Clements |  | Mike | SRO Design | Clarification on end dating MDR functionality | Add clarification that the requirement to end date the MDR is fulfilled using existing CSS0200 functionality |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | MHHS-BR-RS-078.1 notes updated to clarify that this requirement is fulfilled using existing CSS0200 functionality | Requirement correction | Registration | Business Requirements | BRS003 Registration Service requirements
MHHS-DIN-742 | KH |  | 2023-10-23 | CGI | 13709 | Dave Webster | Software Provider | ADS and SDS Estimation Statements | As a result of DIN-589 which was to align the METH002 (ADS) with METH001 (SDS) method statements, the two documents are still misaligned. “Method 0: ADS processes Supplier provided ‘Agreed’ or ‘Override’ Readings” is the equivalent of “Method 0: SDS processes Supplier provided ‘Agreed’ or ‘Override’ Readings and Consumption Amendments”. However, SDS uses flag E0, but ADS uses flag E8 (from the previous numbering of this method and now not intuitive to determine from the flag which method has been used for estimation). Similar to (1), Method 8 (ADS) = Method 8 (SDS), but would be clearer if flag E9 (ADS) matched the method number and flag in SDS, E8. Similar to (1), Method 9 (ADS) = Method 9 (SDS), but would be clearer if flag E10 (ADS) matched the method number and flag in SDS, E9. “3.13 Where notified by a Supplier that a site is Long Term Vacant (LTV) the ADS shall use Method 12.” LTV check is now Method 11. “3.16 The below estimation methods are based on those used in the Smart Data Service (SDS) Method Statement. For that reason, methods 0, 1, 6, 11 and 13 have been omitted as they are only applicable to Smart meters” – this statement is no longer correct as methods 0 and 11 are present |  | Implemented | No |  | Design misaligned | TBC |  | Interim Release 7 | 2024-01-19 | Updates completed in method statement 002 | Requirement correction | Supporting Docs | Method Statement | ADS Method Statement
MHHS-DIN-743 | MF |  | 2023-10-24 | ENWL |  | Paul Band | LDSO | IF-036 Optionality Update | IF-036 changed to optional for LDSO's in line with CR-029 within the Optionality Matrix |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | IF-036 changed to optional for LDSO's inline with CR-029 within the within the Optionality Matrix (name of worksheet in DES-138: 04_IF_OptOut_Matrix) | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-744 | MF |  | 2023-10-24 | RECCO |  | Sarah Jones | Central Body | IF-036/037 Routing to MDS | Show that MDS receive IF-036 and IF-037 on BP003 to align with Interface Catalogue |  | Implemented | No |  | Design misaligned | N/A |  | Interim Release 7 | 2024-01-19 | Added note to BP003 to highlight that MDS will also receive IF-036 and IF-037. Similar note added to the Migration version BPM003 again just to reference the IF-003 being copied to MDS. Added MDS to IF-003 DSDeAppRM event in DES138 | Process Model correction | Supporting Docs | Process model correction | BP003 BPM003 DES138
MHHS-DIN-745 | SW |  | 2023-10-27 | SI Design | 16780 | Madison Layton | Central Body | DI-120 Additional Information should be mandatory nullable | DI-120 was made non nullable in IR5.1 in Swagger. This needs to be corrected so that DI-120 is used in multiple places and needs to be mandatory nullable. |  | Implemented | No |  | Design misaligned | DIP Users, DIP |  | Interim Release 7 | 2024-01-19 | Make DI-120 Additional Information Mandatory nullable in Swagger to align with DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-746 | RG |  | 2023-10-27 | IMserv |  | Liam Lowey | Software Provider | Swagger error - Response body doesn't match Sims& Ems implementation | Schema Bug - Different interpretation of the optional field DIPConnectionProviderID: The DIP Sim requires the property field is present, but allows for a NULL value if we are not using a connection provider. The interface spec, does not allow for a NULL value, but instead does make the field optional. So, it appears that the DipSim requires the property, even if NULL. The schema (v1.2.1) does NOT require the property but will NOT permit NULL. Please can you clarify the intention? This appears to be a blocker/breaking difference that means we will not be able to test the same code base against both DIP Sim and DIP. |  | Closed | Yes | TBC | Error/Correction | DIP Users, DIP |  |  |  | IF we are going to release a 2.2 release then this should be fixed, this has been fixed on the main code thread. This has not been fixed in rel 1.5, hence not included in the 2.2 release. The design perpetuates as described and the DIPSIM needs to align. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-747 | SB |  | 2023-10-27 | OVO | 16574 | Brian Miller | Supplier | CR028 amendment | Routing of the PUB-001 requires amending to reflect the removal of EES as recipient as per CR028 also the Change of Supply documentation redlining requires amending to reflect this |  | Closed | [7 empty] | Notify that this change already exists
MHHS-DIN-748 | RG |  | 2023-10-27 | IMserv |  | Liam Lowey | Software Provider | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength should not have a maxLength validation attribute as it is an integer type. This means the schema itself does not validate against the rules for these types of schemas. |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | DI-487-Total-Number-Energised-MPANs maxLength attribute should be length as it is an integer type. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.6
MHHS-DIN-749 | RG |  | 2023-10-27 | IMserv |  | Liam Lowey | Software Provider | SchemaBug - DipMessage.payload is not a required property | SchemaBug - DipMessage.payload is not a required property, therefore different property names will pass validation without being checked - this means if you spell it "Payload" with a capital P instead it will effectively skip validation resulting in a false positive. |  | Implemented | [5 empty] | Interim Release 6 | 2023-10-18 | ‘payload’ needs to be a required attribute for the DIPMessage object. | Data interface correction | Supporting Docs | Interfaces | Swagger 1.6
MHHS-DIN-750 | RS |  | 2023-10-27 | REC |  | Sarah Jones | Central Body | IF-019/020 Interface notes and REG1066 validation | REG1068 was removed as part of IR4, however the neither related interface note in IF-019 and If-020 or REG1068 in the List of Registration error codes in the introduction tab have been updated. Also REG1066 should be removed for consistency. |  | Implemented | No |  | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Remove statement 'where there are multiple Related Import MPANs, the Export MPAN will only be linked with the Primary MPAN in the relationship' from IF-019 and IF-020 Interface notes Remove REG1066 validation rule from IF-019 Remove REG1066 and REG1068 from the List of Registration error codes in the introduction tab of DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-751 | RS |  | 2023-10-27 | REC |  | Sarah Jones | Central Body | IF-019/020 Interface notes | Interface note for IF-019 and IF-020 states that for the avoidance of doubt, in all cases it is the LDSO, that must determine if the request to create/modify an MPAN Relationship is valid or not. The ultimate decision to allow the linking or de-linking of a MPAN within a relationship rests with the LDSO. This is correct for linked mpans but not related. Interface note to be updates to be LDSO for linked and supplier for related |  | Implemented | No |  | Design ambiguous | LDSO (SCS) |  | Interim Release 8 | 2024-03-20 | Update Interface note for IF-19 and IF-20 to state that for the avoidance of doubt, for Import/Export linkages it is the LDSO, that must determine if the request to create/modify an MPAN Relationship is valid or not. The ultimate decision to allow the linking or de-linking of a MPAN within a relationship rests with the LDSO. Related Metering Point linkages are maintained by the Supplier | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-752 | RS |  | 2023-10-27 |  |  | Sarah Jones | Central Body | Change of Data Service - Forward migration for Import/Export | Yellow note box on DEL964 BPM003 Forward migration document states Export and Import MPANs will be migrated independently, this process is only relevant to Related MPANs. In addition post migration for Export and Import MPANs, the Registration Service will not automatically appoint both the MPANs to the same MS/DS but it will notify of exceptions. This should read PRE-Migration not Post migrations as per requirement MHHS-Migration-Mis-RS-022 |  | Implemented | No |  | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Amend wording to 'In addition Pre migration for Export and Import MPANs, the Registration Service will not automatically appoint both the MPANs to the same MS/DS but it will notify of exceptions'.in DEL964 and DEL963 | Process Model correction | Supporting Docs | Process model correction | DEL964 BPM003 DEL963 BPM002
MHHS-DIN-753 | SB |  | 2023-10-30 | CGI |  | Dave Webster | Software Provider | Reconciliation for smart Meter Advance Reconciliation in METH001 | In METH001, v5.2, section 3.12 it states the MAR should be carried out "at a minimum of once a month". Section 3.15 states "The maximum levels are [±0.7%] where the check is carried out at least on a weekly basis for months data or [±5%] where the check is carried out on a daily basis using daily data." These are contradictory. What is the minimum frequency this check can be carried out, is it weekly or is monthly adequate? If monthly is acceptable, should the tolerance level be [±0.7%] as per a weekly check? |  | Open - awaiting assessment | No |  | Design ambiguous | N/A |  | Post Go-live Release |  | Propose the statement in METH001 be updated to the following: Section 3.15 states "The maximum levels are [±0.7%] where the check is carried out at least on a weekly or monthly basis or [±5%] where the check is carried out on a daily basis using daily data." | Method statement correction | Supporting Docs | Method statement correction | METH001
MHHS-DIN-754 | PP |  | 2023-10-30 | Helix |  | Sedef Kiris | Central Body | Alignment of REP-005 and ISD entity | Issue statement: In TOM, Line Loss Factor (LLF) process is a new streamlined process identified with a hybrid solution combining the benefits of Salesforce and Azure to process LLF Data. However there are some ambiguity within the Design Artefacts around how ISD should be publishing LLF Data. In the MHHS BRS10 document, the requirement from MHHS is to publish the full ISD dataset on the BSC Website in a manner that is available to the public access. The data will be available in 3 separate grouping 1. LLF data 2. Master Settlement timetable 3. ISD data including UMS data However, the MHHS ERI011B ECS report document states that Line Loss Factors' specifics for Market Participants will be provided by Elexon as part of the ISD publication in the name of ELEX-REP-005 The LLF data referenced in MHHS BRS10 and ELEX REP 005, as mentioned in MHHS ERI011B, are identical but bear different names leading to confusion and ambiguity. Helix WP3 has identified this ambiguity and would like MHHS to make relevant Design artefact changes to bring more clarity. |  | Implemented | No |  | Error/Correction | All Participants |  | Interim Release 7 | 2024-01-19 | This was raised via the change board where a decision was made to push this through as a DIN REP-005 and the LLF data referenced in the design artifacts are essentially one and the same. Helix aims to meet their requirements by adhering to the specifications outlined in the Transition BRS010. To accomplish this, MHHS needs to take the following changes into consideration. The recommended solution from Helix and MHHSP is to align the Transition and End State Design Artefacts to reflect LLF Data is a deliverable of ISD and add two new ISD Entities to reflect this and remove REP-005 from the list of ECS Reports – impacts BRS010, BRS001 (Transition), ERI011B and EDI012. Remove the mention of ELEX REP 005 from MHHS ERI011B ECS report document To enable the ISD to release Line Loss Factor (LLF) data, the LLF data must be integrated into the MHHS EDI021 ISD Entity Specification document. (detailed below entity details) MHHS then align the Transition and End State Design Artefacts to reflect this change i.e All effected Design Artefacts (BRS010, ERI011B ECS report and EDI021 ISD Entity Specification ) to be updated. | Data interface correction | Supporting Docs | Various documents | BRS010, BRS001 (Transition), ERI011B, EDI012
MHHS-DIN-755 | SC |  | 2023-11-01 |  |  | Sean Cooper | SRO Design | Correction to IF-035 Routing Matrix | Previous DIN created a new group B99 for SDS-MDRUpdate Rejections - this new B099 group was not updated in the Routing Matrix. This has now been corrected. |  | Implemented | No |  | Design misaligned | LDSO (SCS) |  | Interim Release 7 | 2024-01-19 | Previous DIN created a new group B99 for SDS-MDRUpdate Rejections - this new B099 group was not updated in the Routing Matrix. This has now been corrected. | Data interface correction | Supporting Docs | Interfaces | DES138 Interface Catalogue
MHHS-DIN-756 | SC |  | 2023-11-01 |  |  | Sean Cooper | SRO Design | Addition of IF-003 [ReverseMigration] to BPM-001 | Migration Business Process Map BPM-001 updated to include previously missing issuing of IF-003 [ReverseMigration] event from REGS to MDS, LDSO, and EES. This is triggered off the back of COS completion notice (Secured Active) from CSS to REGS. Note this is required as a definitive reverse migration notification as IF-003 [DSApp] may not always be issued. This is not a change to the migration design - step had simply been ommited from BP map. |  | Implemented | No |  | Design ambiguous | N/A |  | Interim Release 7 | 2024-01-19 | Migration Business Process Map BPM-001 updated to include previously missing issuing of IF-003 [ReverseMigNotification] event from REGS to MDS, LDSO, Supplier and EES. This is triggered off the back of COS completion notice (Secured Active) from CSS to REGS. Note this is required as a definative reverse migration notification as IF-003 [DSAppRM] may not always be issued. This is not a change to the migration design - step had simply been ommited from BP map. BPD-001 (Reverse Migration) updated accordingly | Process Model correction | Supporting Docs | Process model correction | BPM001 BPMD001
MHHS-DIN-757 | SC |  | 2023-11-01 |  |  | Sean Cooper |  | Add BP003A Link to BP003M Reverse Migration Map. Remove BP003A link from DEL963-BPM002 Forward migration | Added Missing link to show update to CSS/DCC when SDS is de-appointed on Reverse Migration. Remove the link to BP003A from DEL963-BPM002 as this is only triggered for a Change of Data Service |  | Implemented | No |  | Design gap | SDS |  | Interim Release 7 | 2024-01-19 | New process link to BP003A added to BPM003 for Smart meters at step 1008. Remove link to BP003A from DEL963-BPM002 | Process Model correction | Supporting Docs | Process model correction | BPM003 BPM002
MHHS-DIN-758 | SC |  | 2023-11-01 |  |  | Sean Cooper | SRO Design | 5 day check on MDR App Date in IF-034 | Per feedback from SCS, five day check on MDR Eff From Date (DI-841) changed to only apply to SDSMDRUpdate event and NOT normal/regular DS Appointment events. Thus removes clash between this check and 28 day leadtime on regular DS Apps |  | Implemented | No |  | Design gap | LDSO (SCS) |  | Interim Release 7 | 2024-01-19 | Per feedback from SCS, five day check on MDR Eff From Date (DI-841) changed to only apply to SDSMDRUpdate event and NOT normal/regular DS Appointment events. Thus removes clash between this check and 28 day leadtime on regular DS Apps. New Rule added specifically for DSSAppSPResonse | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-759 | SC |  | 2023-11-01 |  |  | Sean Cooper | SRO Design | Changes to Proposed Consent logic | Proposed Consent (DI-838) Set to Mandatory, Updated allowable values in DI-838 and DI-017 to include N - No consent. Updated ISD M17 table to include meter group and added N value for all traditional meter combinations. |  | Implemented | No |  | Design ambiguous | LDSO (SCS) |  | Interim Release 7 | 2024-01-19 | Proposed Consent (DI-838) Set to Mandatory, Updated allowable values in DI-838 and DI-017 to include N - No consent. Updated ISD M17 table to include meter group and added N value for all traditional meter combinations. | Data interface correction | Supporting Docs | Interfaces | DES138 ISD Entities
MHHS-DIN-760 | MF |  | 2023-11-01 |  |  | Mike Fensome | SRO Design | UMSDS routing | Updates to align Optionality Matrix and To Parties for UMSDS |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | Updated IF-024 to remove UMSDS from To Parties. Updated Optionality Matrix to show IF-043 as N/A and IF-018 as Yes for events [DUOSTariffIDChg] and [DomPremInd] for UMSDS | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-761 | MH |  | 2023-11-03 |  | 16609 | Matt Hall |  | BP020 ver 5.1 redlined - REP D0354 | BP020 5.1 references the supplier receiving various VAS reports including REP-D0354, which isn't a VAS report at all, and isn't sent to suppliers, and REP-D0237 which should be REP-P0237 and is an internal report that doesn't go to suppliers |  | Open - awaiting assessment | No |  | Design ambiguous | Suppliers |  | Post Go-live Release |  | Review reports contained in BP020 and correct | Process Model correction | Supporting Docs | Process model correction | BP020
MHHS-DIN-762 | MH |  | 2023-11-03 |  |  | Matt Hall | SI Design | DEL961 IF-003 routing to MDS - Update Migration Document | DEL961 needs updating to reflect the clarifications made in DIN-756 that IF-003 should be routed to MDS on [ReverseMigration] and [DSApp] events, not [MSApp] |  | Implemented | No |  | Design ambiguous | N/A |  | Interim Release 8 | 2024-03-20 | Section 8 of DES961 updated to remove LDSO and Elexon Central Systems receiving MS Deappointment in line with DES-138 | Process Model correction | Supporting Docs | Process model correction | DEL961 - Migration Design Document
MHHS-DIN-763 | RS |  | 2023-11-06 |  | 15975 | Sarah Jones | Central Body | Related Metering Points undergoing Migration | Change to the Registration Service Requirements introduced through IR3 (DIN423). proposed change to RS-146 to remove 'and Related MPANs': Registration must only carry out auto-alignment of Linked MPANs (Import/Export) and Related MPANs if all MPANs in the group have migrated to the MHHS operation. |  | Implemented | No |  | Design ambiguous | Suppliers |  | Interim Release 8 | 2024-03-20 | Amend wording to RS-146 from Registration must only carry out auto-alignment of Linked MPANs (Import/Export) and Related MPANs if all MPANs in the group have migrated to the MHHS operation. to Registration must only carry out auto-alignment of Linked MPANs (Import/Export) if all MPANs in the group have migrated to the MHHS operation. | Requirement correction | Registration | Requirement correction | BRS003 - Registration Service Requirements
MHHS-DIN-764 | MF | DI-236 | 2023-11-06 | St Clements |  | Mike Fensome | SRO Design | Additional validation rule in IF-031 to ensure appointments are contiguos | Add new validation rules in IF-031 to ensure that if there is no Service Provider appointed, the Proposed Service Provider Appointment Date is equal to SSD or Previous Service Provider De-appointment Date + 1 |  | Implemented | No |  | Design gap | LDSO (SCS) |  | Interim Release 7 | 2024-01-19 | Added two new validation rules in IF-031 to ensure that if there is no Data Service/ Metering Service currently appointed then the Proposed DS/ MS Appointment Date must equal SSD or Previous DS/MS De-appointment Date + 1. Error message of REG 1032 issued if the check fails. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-765 | SW |  | 2023-11-07 |  | 18247 | Steve Weston | SI Design | Inconsistencies in E2E001 JSON examples with Swagger | There are some minor / non-consequential inconsistencies and spelling mistakes in some of the examples provided in the E2E001 design, that do not align with Swagger that need to be corrected in the E2E001 design document |  | Open - awaiting assessment | No |  | Design ambiguous | DIP Users |  | Post Go-live Release |  | In section 4.5.6.3 example JSON, "receive" is incorrectly spelt "recieve" in both the header and payload body. The JSON payload is malformed. There's an extra "{" which is not closed and a missing comma after the second "message. These have both been amended in the E2E001 design to align with Swagger. Section 4.5.6.2 says "Where a field is not written/available/optional, then a null value needs to be written". That's not done in the example, which just omits multiple fields. This has been amended in the E2E001 design to align with Swagger. Section 4.5.6.2 says "The response uses the common Standard Response body" but the example includes "recieveEventCallback", is missing "timestamp", and names the array of responses "events" rather than "messageArray". All of which differ from the Standard Response body defined in https://app.swaggerhub.com/apis/MHHSPROGRAMME/SubmitEvents/1.5.1#/StandardResponse. This has been amended in the E2E001 design to align with Swagger. Is the "message" field meant to contain one of a list of allowed responses? - Is the trailing whitespace in "DIP0000 ok ", no trailing whitespace is required, so this has been updated in all example JSON’s where this applies. - The "DIP0000 ok" value for the "message" field is different to the other success messages used in this doc. E.g section 4.4.4.2 uses "Message OK " to represent success and the DIP simulator uses "message": "MSG0000 - Success". Is one of those the correct one? The message returned should align with the messages defined in the Introduction tab in the DES-138 Interface Catalogue. The DIP simulator is returning the correct values, as is the DIP. In this instance, as above, the example is not quite aligned in the E2E001 design so the messages need to align with what is defined in the Introduction tab in the DES-138 Interface | Design Ambiguous | Supporting Docs | Interfaces | E2E001
MHHS-DIN-766 | ZH | DIN-464 | 2023-11-07 | SIMS |  | Kyle Abraham | Software Provider | Clarity required on values expected for /dip-channel/{id} for submitEvents on Swagger | The {id} in /dip-channel/{id} for submitEvents on Swagger should accept values that are the same as the enumeration in DI-000 to ensure consistency. At the moment, this is not clear in Swagger, so this needs to be updated to make this clearer. |  | Implemented | Yes |  | Design misaligned |  |  | Interim Release 2.2 |  | Updates made to Swagger 1.2.2, so the correct enumerations / values are available to align with values in DI-000 to ensure consistency and avoid any ambiguity between interfaces and reports. Updated to remove PublicationConfig and RestConfig in favour of a single config WebhookConfig. | Data interface correction | Supporting Docs | Interface Changes | Swagger 1.2.2
MHHS-DIN-767 | SW | DIN-772 | 2023-11-13 | C&C | 19150 | Chris Lenihan | Software Provider | Swagger incorrect for IF-043 | For IF-043 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-043-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. |  | Implemented | No |  | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Update IF-043 so that it uses the required property name is ‘CustomBlock’ but the actual name is ‘IF-043-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-768 | SW |  | 2023-11-13 |  | 19136 | John Edmonds-Bell | SI Design | Event Code inconsistency between Swagger and ECS Reports for REP-901 | On REP-901 report, the event code in the reports catalogue is defined [DUoS_EmbeddedLDSO_Agg_Inv_Data] and [DUoS_Supplier_Agg_Inv_Data] whereas on the Swagger Document it’s DUoSSupplierInvData. Need to fix this inconsistency innSwagger. |  | Implemented | No |  | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Update the ECS reports catalogue to align with Event Code naming standard (used in other Interfaces) and to align with Swagger. On REP-901 report, the event code in the reports catalogue is defined [DUoS_EmbeddedLDSO_Agg_Inv_Data] and [DUoS_Supplier_Agg_Inv_Data] whereas on the Swagger Document it’s DUoSSupplierInvData. Swagger has also been updated to align. | Data interface correction | Supporting Docs | ESC Report | ECS Report Swagger
MHHS-DIN-769 | RG |  | 2023-11-13 |  |  | Rob Golding | SRO | Updates to MHHSP-ERI011B (IR5) not reflected in the swagger | There appears to be several updates to the reporting spreadsheet that did not have a corresponding update in the swagger. The R901-05 block in Swagger is missing an attribute; DI-613. The spreadsheet has incorrect SVA data types for these two new items |  | Implemented | No |  | Design misaligned | Helix, DIP, Suppliers, LDSOs |  | Interim Release 7 | 2024-01-19 | Update R901-05 block in Swagger; DI-613. Update MHHSP-ERI011B; the incorrect SVA data types for these two new items. | Data interface correction | Supporting Docs | Interfaces | MHHSP-ERI011B, Swagger
MHHS-DIN-770 | SW | DIN-773 | 2023-11-13 |  | 18780 | Chris Lenihan | Software Provider | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025 | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025. This needs to be updated in the list of enumerated value to be IF-026. |  | Implemented | No |  | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025. This needs to be updated in the list of enumerated value to be IF-026 in Swagger. | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-771 | RG |  | 2023-11-13 |  |  | Rob Golding | SRO | R900-03. listOfMPANSOnsite should be listOfMPANSOnSite | Typo in swagger - R900-03. listOfMPANSOnsite should be listOfMPANSOnSite |  | Implemented | No |  | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Update R900-03. listOfMPANSOnsite to listOfMPANSOnSite | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-772 | SW | DIN-767 | 2023-11-13 | C&C | 19150 | Chris Lenihan | Software Provider | Swagger incorrect for IF-043 | For IF-043 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-043-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. |  | Implemented | Yes |  | Design misaligned | DIP Users, DIP |  | Interim Release 5.2 |  | Update IF-043 so that it uses the required property name is ‘CustomBlock’ but the actual name is ‘IF-043-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-773 | SW | DIN-770 | 2023-11-13 |  | 18780 | Chris Lenihan | Software Provider | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025 | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025. This needs to be updated in the list of enumerated value to be IF-026. |  | Implemented | Yes |  | Design misaligned | DIP Users, DIP |  | Interim Release 5.2 |  | Swagger for IF-026 for variant IF-026-SSCandProfileClass contains incorrect enumeration for IF-025. This needs to be updated in the list of enumerated value to be IF-026 in Swagger. | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-774 | RG |  | 2023-11-15 |  |  | Rob Golding | SRO | IF-020 [LinkedImportExportRemove] & [RelatedRemove] | The B090 block needs to be optional to cope with the scenario where a linked/related meter is removed and it leaves the situation that there are no linked/related meters. Also, on line 64 it mentions a B074 block, however, there is no B074 block in the message |  | Closed | [7 empty] | Fix the swagger and DES138 to reflect this condition | Design Ambiguous | Supporting Docs | Interfaces | DES138
MHHS-DIN-775 | MF |  | 2023-11-15 |  |  | Sarah Jones | Central Body | Remove Customer Direct Process from BP002/BP003 | The Customer Direct process has been set out in BP010 (DIN-554) so can be removed from BP002/BP003 to avoid any confusion |  | Open - awaiting assessment | No |  | Clarification - No change required | N/A |  | Post Go-live Release |  | Remove Customer Direct process steps from BP002/BP003 | Process Model correction | Supporting Docs | Process Models | BP002 BP003
MHHS-DIN-776 | MH |  | 2003-11-16 | Elexon |  | Sedef Kiris | Central Body | LLF Data and Rep005 | There is some ambiguity within the Design Artefacts around how ISD should be delivering LLF Data and REP-005. ​ BRS010 implies ISD will publish it through a common delivery method as the Master Settlement Timetable and the rest of the ISD entities, but it does not mention REP-005.​ BRS001 (Transition) denotes that REP-005 will be published via the Elexon Portal and will utilise IF-047. ​ ERI011B denotes that the distribution pattern and the report format of REP-005 are to be defined by Elexon. ​ EDI021 does not include any ISD entities for LLF data. ​ REP-005 and the LLF data mentioned in the design artefacts are the same thing, and Helix intend to fulfil their requirements by delivering in line with requirements as laid out in the Transition BRS. ​ Impact: There is a potential lack of clarity amongst Participants around how they are going to receive REP-005, inconsistency in the overall solution of data coming from ISD. |  | Closed | [7 empty] | Duplicate - To be tracked under MHHS-DIN-754
MHHS-DIN-777 | RG | DIN-785 | 2023-11-16 | SRO | 20939 20723 | Rob Golding |  | IF-001-ChangeOfSupplier required fields on CommonBlocks are incorrect | The required fileds on the common block are set to commonblock and customblock, they need to be set to S1 etc. |  | Implemented | Yes |  | Design misaligned | DIP Users |  | Interim Release 5.2 |  | The required fileds on the common block are set to commonblock and customblock, they need to be set to S1 etc. This has been updated in Swagger so the common block in IF-001 now contains the correct required blocks. Only an issue with 5.+ not 2.+ | Design Ambiguous | Supporting Docs | Interfaces | Swagger
MHHS-DIN-778 | RG |  | 2023-11-17 | Stark |  | Rob Golding | Supplier | Fix enumeration on the PUB domain for the following PUBs; PUB-004, PUB-019, PUB-020, PUB-040 and PUB-050 in DT-983. Same IF's added for DT-000. | There are a number of values missing from the enumeration in the DT-983 for the Interfaces defined. These are PUB-004, PUB-019, PUB-020, PUB-040 and PUB-050. There are a number of values missing from the enumeration in the DT-000 for the Interfaces defined. These are IF-004, IF-019, IF-020, IF-040 and IF-050. |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 2.3 |  | PUB-004, PUB-019, PUB-020, PUB-040 and PUB-050 are missing from DT-983 that defines the enumeration of available values, so these have been added. IF-004, IF-019, IF-020, IF-040 and IF-050 are missing from DT-000 that defines the enumeration of available values, so these have been added. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-779 | SC |  | 2023-11-20 | IMServ |  | Sean Cooper |  | Routing for IF-041 | Add Data Service to Primary Routing for SDS issued IF-041's to align with BP003C |  | Implemented |  |  | Design misaligned | SDS |  | Interim Release 7 | 2024-01-19 | Added Data Service (where required) to Primary Routing in the SDS row of IF-041 routing table | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-780 | SB |  | 2023-11-21 | St Clements | 19885 | Madison Layton | Central Body | No longer providing examples within the Interface Catalogue | Updates to the swagger and Interface Catalogue will no longer have examples detailed within the Interface catalogue |  | Closed | No | [6 empty] | Examples are now managed in Swagger
MHHS-DIN-781 | BK | DIN-748, DIN-783 | 2023-11-21 | IMserv |  | Liam Lowey | Software Provider | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength should not have a maxLength validation attribute as it is an integer type. This means the schema itself does not validate against the rules for these types of schemas. |  | Implemented | Yes |  | Design misaligned | DIP Users |  | Interim Release 2.3 |  | DI-487-Total-Number-Energised-MPANs maxLength attribute should be length as it is an integer type. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-782 | BK | DIN-749, DIN-784 | 2023-11-21 | IMserv |  | Liam Lowey | Software Provider | SchemaBug - DipMessage.payload is not a required property | SchemaBug - DipMessage.payload is not a required property, therefore different property names will pass validation without being checked - this means if you spell it "Payload" with a capital P instead it will effectively skip validation resulting in a false positive. |  | Implemented | Yes |  | Design misaligned | DIP Users |  | Interim Release 2.3 |  | ‘payload’ needs to be a required attribute for the DIPMessage object. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-783 | BK | DIN-748, DIN-781 | 2023-11-21 | IMserv |  | Liam Lowey | Software Provider | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength | Schema Bug - DI-487-Total-Number-Energised-MPANs.maxLength should not have a maxLength validation attribute as it is an integer type. This means the schema itself does not validate against the rules for these types of schemas. |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  | DI-487-Total-Number-Energised-MPANs maxLength attribute should be length as it is an integer type. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-784 | BK | DIN-749, DIN-782 | 2023-11-21 | IMserv |  | Liam Lowey | Software Provider | SchemaBug - DipMessage.payload is not a required property | SchemaBug - DipMessage.payload is not a required property, therefore different property names will pass validation without being checked - this means if you spell it "Payload" with a capital P instead it will effectively skip validation resulting in a false positive. |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger updated so that ‘payload’ has been added as a required attribute for the DIPMessage object. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-785 | BK | DIN-777 | 2023-11-21 | SRO | 20939 20723 | Rob Golding |  | IF-001-ChangeOfSupplier required fields on CommonBlocks are incorrect | The required fields on the common block are set to commonblock and customblock, they need to be set to S1 etc. |  | Implemented | Yes |  | Design misaligned |  |  | Interim Release 7 | 2024-01-19 | Update IF-001-ChangeOfSupplier required fields on CommonBlocks that are incorrect | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-786 | MF | DI-238 | 2023-11-21 | St Clements |  | Mike Fensome |  | Determination of Market Segment Effective From Date | Add clarification on how Registration Service will set Market Segment Effective From Date |  | Implemented | No |  | Clarification - No change required | SCS |  | Interim Release 7 | 2024-01-19 | Added new section to REGS_Notes to clarify how Market Segment EFD is set by Registration Service. The table below outlines how the Registration Service will Derive Market Segment Effective From Date, following various 'trigger' events. Market Segment Change Trigger Derived Market Segment EFD Notes Connection Type Connection Type EFD If triggers a change to related/associated MPANs SEG use the same derived EFD, except in the case this is prior to the relationship/association EFD in which case use relationship/association EFD instead Meter Added/Meter Type changed Meter Installation Date Meter Removed Meter Removal Date If trigger is a Meter Exchange use installation date not removal date Relationship Created Relationship EFD Only amend SEG EFD for MPANs where the SEG is changing – SEG of some MPANs in the relationship/association will not be changing Relationship Deleted Relationship ETD Association Created Association EFD Association Deleted Association ETD Where derived EFD is less than the current Market Segment EFD, the current Market Segment EFD will be cancelled to allow for the new one. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-787 | BK |  | 2023-11-21 | RECCo |  | Sarah Jones | Central Body | Typo in the data item name for DI20228 - DIP Roles / IDs Always Receipient ID (DI-993 in the Interface Catalogue) | It has been noted that there is a typo in the data item name for DI20228 - DIP Roles / IDs Always Recipient ID |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | Correction of spelling on the word 'Recipient' against DI-993 in the Interface Catalogue | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-788 | SC |  | 2023-11-22 | St Clements |  | Madison Layton | Software Provider | Reconnection of MPAN (provided that CSS DeRegistration has not completed) | New BP009B - would need IF-009 Event Code. "Reconnected" to SUPC only and Re-issue of IF-50 to EES for MPRS Status code. Current MHHS design does not cater for the re-connection of an MPAN that has previously been dis-connected​ Under current operation this is allowed for via a Manual amendment request by the LDSO (Covered by BSCP604) where the MPAN has not been Registration De-activated |  | Implemented | No |  | Design gap | St Clements, Suppliers |  | Interim Release 7 | 2024-01-19 | ​Update to BP007 (Disconnection) to show the flows where an MPAN is re-connected ​ Update to BRS003 to add requirement for Registration Service triggering the IF-009 and IF-050 to inform of a re-connection​ Update to BRS004 to add requirement for Suppliers receiving PUB-009 [MPANReconnection]​ Update DES-138 to add new [MPANReconnection] event code to IF-009​ Update to Swagger to add IF-009 MPANReconnection event code variant to Swagger. | Process Model correction | Supporting Docs | Various documents | BP007, BR003, BR004, DES-138, Swagger
MHHS-DIN-789 | BK | DIN-673 | 2023-11-22 | Design Team |  | Rob Golding | Programme Design | Floating Point number regexes | DIN 267 inadvertently updated regexes to a pattern which does not align to the agreed format as of Technical Design Working Group Work-Off Issue D-0408th November 2022. The regexes need to align to what was agreed. |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 2.3 |  | Update regex patterns for the following data types: DT-016, DT-022, DT-023, DT-024, DT-025, DT-030, DT-031, DT-032, DT-033 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-790 | BK | DIN-791 | 2023-11-22 | Design Team |  | Rob Golding | Programme Design | Number regex - DI-123 | Update regex patterns for the following data type: DI-123 |  | Implemented | Yes | 17678 | Error/Correction | DIP Users |  | Interim Release 2.3 |  | Update regex patterns for the following data type: DI-122 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-791 | BK | DIN-790 | 2023-11-22 | Design Team |  | Rob Golding | Programme Design | Number regex - DI-123 | Update regex patterns for the following data type: DI-123 |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Added regex patterns for the following data type: DI-123 to use the following pattern: ^\d{4,4}$ | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-792 | BK | DIN-790, DIN-791 | 2023-11-22 | Design Team |  | Rob Golding | Programme Design | Number regex - DI-123 | Update regex patterns for the following data type: DI-123 |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Update regex patterns for the following data type: DI-123 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-793 | SB |  | 2023-11-23 | St Clements | 21513 | Madison Layton | Central Body | DI-241 - SUPC routing on IF-037 incorrect, should be SUPS | SUPC was moved to primary routing for IR5 release, as per attached. However it was clarified on a COS this would be the old Supplier not the current Supplier, so SUPC will not always be correct. Needs to be changed for clarity, SUPS could be used to indicate IF-037 will be sent to the Supplier that submitted the original SP appointment for the SP being de-appointed? |  | Implemented | No |  | Clarification - No change required | St Clements |  | Interim Release 7 | 2024-01-19 | Updated primary routing on IF-037 from SUPC to Supplier. On a COS, Registration Service will send to the old Supplier, on Change of Service Provider to the Current Supplier. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-794 | MH | DIN-409 | 2023-11-23 | Elexon | 19961 | Sedef Kiris | Central Body | ISD Consumption Component Classes M5 | In the ISD entity, there was an adjustment made by DIN 409 to distinguish the settlement quality indicator with the same CCC ID. While the ISD Entities specification document has been appropriately updated, the corresponding changes have not been reflected in the MDS method statement Appendix 1. This inconsistency is causing confusion. |  | Implemented | No |  | Error/Correction | Elexon |  | Interim Release 7 | 2024-01-19 | The example provided in Appendix 1 in the METH007 is wrong and misleading. As a correct example is provided in the ISD Entities document, we'll remove the one in METH007 | Method statement correction | Meter to Bank | Method Statement | METH007
MHHS-DIN-795 | MH | DIN-678 | 2023-11-23 | Elexon | 18841 | Rashmi Radhakrishnan | Central Body | ISD M9 Clarification | DIN-678 was to change the length of the following UMS data items in ISD: Unit description 1, 2 and Manufacturer's Designation. But Manufacturer's Designation was not changed in both M9 and M10. This iDIN is to complete that update. |  | Implemented | No |  | Design misaligned | Elexon, UMSDS |  | Interim Release 7 | 2024-01-19 | Update Manufacturer's Designation in ISD Entity M9 to up to 100 characters | Requirement correction | Supporting Docs | ISD | EDI021
MHHS-DIN-796 | MF | DIN-234 | 2023-11-23 | St Clements |  | Madison Layton | Software Provider | Clarification on validation of B018 block conditionality in IF-034 | Clarification that SCS will validate that a Smart Meter is present for Block B018 conditionality by checking that DCC Service Flag (DI-025) is A |  | Implemented | No |  | Clarification - No change required | SCS |  | Interim Release 7 | 2024-01-19 | Note added to IF-034 interface to clarify that SCS will validate that a Smart Meter is present for Block B018 conditionality by checking that DCC Service Flag (DI-025) is A | Data interface correction | Supporting Docs | Interfaces | DES-138
MHHS-DIN-797 | BK |  | 2023-11-24 | Design Team |  | Rob Golding | Programme Design | Capitalisation in Swagger | E2E001 Architecture document will be updated to reflect the adherence to case sensitivity on the inbound messages, and the removal of the statement in Swagger relating to case insensitivity. |  | Implemented | Yes |  | Design gap | DIP Users |  | Interim Release 2.3 |  | Updating of the Swagger and E2E001 to align to Open API standards in relation to case sensitivity. The Section in the E2E001 is 4.4.3 and Swagger its the removal of a comment at the top of swagger file | Data interface correction | Supporting Docs | Interfaces | Swagger, E2E Architecture Document
MHHS-DIN-798 | BK |  | 2023-11-24 | Design Team |  | Rob Golding | Programme Design | Capitalisation in Swagger | E2E001 Architecture document will be updated to reflect the adherence to case sensitivity on the inbound messages, and the removal of the statement in Swagger relating to case insensitivity. |  | Implemented | Yes |  | Design gap | DIP Users |  | Interim Release 5.2 |  | Updating of the Swagger and E2E001 to align to Open API standards in relation to case sensitivity. The Section in the E2E001 is 4.4.3 and Swagger its the removal of a comment at the top of swagger file | Data interface correction | Supporting Docs | Interfaces | Swagger, E2E Architecture Document
MHHS-DIN-799 | SW |  | 2023-11-24 | Design Team |  | Rob Golding | Programme Design | Capitalisation in Swagger | E2E001 Architecture document will be updated to reflect the adherence to case sensitivity on the inbound messages, and the removal of the statement in Swagger relating to case insensitivity. |  | Implemented | Yes |  | Design gap | DIP Users |  | Interim Release 7 | 2024-01-19 | Updating of the Swagger and E2E001 to align to Open API standards in relation to case sensitivity. The Section in the E2E001 is 4.4.3 and Swagger its the removal of a comment at the top of swagger file | Data interface correction | Supporting Docs | Interfaces | Swagger E2E001 Architecture Document
MHHS-DIN-800 | SW |  | 2023-11-27 | Design Team |  | Steve Weston | Programme Design | ECS Reports Inconsistency with Swagger | Inconsistency between ECS Reports Catalogue and Swagger: REP-002B -- R027 and R013 - Distributor and GSP blocks appear to be missing from REP-002B in Swagger. REP-003 -- R024 contains DI-496 in the ECS reports, but in Swagger it contains DI-307. REP-003 -- R9017 contains correctAndUncorrectComponent does not contain block R018 in the name. REP-004 -- R025 and R026 should have parent of R009 according to ECS catalogue, but Swagger has these defined with no parent. REP-006 -- R003 contains R033. R033 should have DI-496, 374, 359, and 360, but in Swagger, contains 307, 374, 359 & 360. REP-006 -- R051 says parent is R032 in ECS reports catalogue, but R051 does not appear in the Swagger in R032. As a result, R106 or R107 which should be part of R051 is missing. REP-009 -- The R013 block contains R016 in Swagger, but in the ECS Catalogue, this is R013 > R068. REP-900 -- R900-03 contains DI-345 in Swagger, when it should contain DI-612. Also marked incorrectly as required. |  | Closed |  |  | Design misaligned | DIP Users |  |  |  | Inconsistency between ECS Reports Catalogue and Swagger. For all items below, Swagger is to be updated to align with the ECS Reports Catalogue: REP-002B -- R027 and R013 - Distributor and GSP blocks are missing from REP-002B in Swagger. Add missing blocks. REP-003 -- R024 contains DI-496 in the ECS reports, but in Swagger it contains DI-307. Update to DI-496. REP-003 -- R9017 contains correctAndUncorrectComponent does not contain block R018 in the name. Update naming. REP-004 -- R025 and R026 should have parent of R009 according to ECS catalogue, but Swagger has these defined with no parent. Update Swagger to align. REP-006 -- R003 contains R033. R033 should have DI-496, 374, 359, and 360, but in Swagger, contains 307, 374, 359 & 360. Update to DI-496. REP-006 -- R051 says parent is R032 in ECS reports catalogue, but R051 does not appear in the Swagger in R032. As a result, R106 or R107 which should be part of R051 is missing. Add the missing blocks to align. REP-009 -- The R013 block contains R016 in Swagger, but in the ECS Catalogue, this is R013 > R068. Update R013 in Swagger to contain R068. REP-900 -- R900-03 contains DI-345 in Swagger, when it should contain DI-612. Also marked incorrectly as required. Update Swagger to use DI-612. Closed as decision made to only align ECS Reports changes to IR7. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-801 | SW |  | 2023-11-27 | Design Team |  | Steve Weston | Programme Design | ECS Reports Inconsistency with Swagger | Inconsistency between ECS Reports Catalogue and Swagger: REP-002B -- R027 and R013 - Distributor and GSP blocks appear to be missing from REP-002B in Swagger. REP-003 -- R024 contains DI-496 in the ECS reports, but in Swagger it contains DI-307. REP-003 -- R9017 contains correctAndUncorrectComponent does not contain block R018 in the name. REP-004 -- R025 and R026 should have parent of R009 according to ECS catalogue, but Swagger has these defined with no parent. REP-006 -- R003 contains R033. R033 should have DI-496, 374, 359, and 360, but in Swagger, contains 307, 374, 359 & 360. REP-006 -- R051 says parent is R032 in ECS reports catalogue, but R051 does not appear in the Swagger in R032. As a result, R106 or R107 which should be part of R051 is missing. REP-009 -- The R013 block contains R016 in Swagger, but in the ECS Catalogue, this is R013 > R068. REP-900 -- R900-03 contains DI-345 in Swagger, when it should contain DI-612. Also marked incorrectly as required. |  | Implemented |  |  | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Inconsistency between ECS Reports Catalogue and Swagger. For all items below, Swagger is to be updated to align with the ECS Reports Catalogue: REP-002B -- R027 and R013 - Distributor and GSP blocks are missing from REP-002B in Swagger. Add missing blocks. REP-003 -- R024 contains DI-496 in the ECS reports, but in Swagger it contains DI-307. Update to DI-496. REP-003 -- R9017 contains correctAndUncorrectComponent does not contain block R018 in the name. Update naming. REP-004 -- R025 and R026 should have parent of R009 according to ECS catalogue, but Swagger has these defined with no parent. Update Swagger to align. REP-006 -- R003 contains R033. R033 should have DI-496, 374, 359, and 360, but in Swagger, contains 307, 374, 359 & 360. Update to DI-496. REP-006 -- R051 says parent is R032 in ECS reports catalogue, but R051 does not appear in the Swagger in R032. As a result, R106 or R107 which should be part of R051 is missing. Add the missing blocks to align. REP-009 -- The R013 block contains R016 in Swagger, but in the ECS Catalogue, this is R013 > R068. Update R013 in Swagger to contain R068. REP-900 -- R900-03 contains DI-345 in Swagger, when it should contain DI-612. Also marked incorrectly as required. Update Swagger to use DI-612. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-802 | SW |  | 2023-11-27 | Design Team |  | Steve Weston | Programme Design | Naming standards are inconsistently applied in ECS reports catalogue for nested structures and lists. | Naming standards are inconsistently applied in ECS reports catalogue for nested structures and lists, meaning it you have blocks that contain blocks with the same name, as there is no naming mechanism to easily link nested block name to contains, or back to ECS reports catalogue. |  | Closed | [7 empty] | Implement a new naming standard for ECS reports catalogue. Closed as decision made to only align ECS Reports changes to IR7. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-803 | SW |  | 2023-11-27 | Design Team |  | Steve Weston | Programme Design | Naming standards are inconsistently applied in ECS reports catalogue for nested structures and lists. | Naming standards are inconsistently applied in ECS reports catalogue for nested structures and lists, meaning it you have blocks that contain blocks with the same name, as there is no naming mechanism to easily link nested block name to contains, or back to ECS reports catalogue. |  | Implemented |  |  | Design misaligned | DIP Users |  | Interim Release 7 | 2024-01-19 | Implement a new naming standard for ECS reports catalogue for nested structures and lists. | Data interface correction | Supporting Docs | Interfaces | ECS Reports Catalogue
MHHS-DIN-804 | SB |  | 2023-11-28 | ESG | 22206 | Patricia Parker | Software Provider | Migration clarification | Page 13 of the migration document states the following for Forward Migration CoA 14. The Registration Service will send the IF-036 at the Service Appointment effective from date. The sending of the IF-036 will act as the definitive indicator that a Forward Migration has completed. Is the IF_036 not sent at the Service Appointment effective from date – 1 . Registration Service will have processed all Secured Active Messages and processed the Pending Appointment Queue by 21:00. This will include the production and publication of all required IF-035, IF-036 and IF-037 messages. |  | Closed |  |  | Clarification - No change required |  |  |  |  | Already discussed and agreed for SDS to determine solution.
MHHS-DIN-805 | RG |  | 2023-11-29 | SRO |  | Rob Golding | SRO Design | Examples in swagger incorrectly resolved if have a leading 0 | Sims & Ems noted that the example for DI-123-SSC was resolving to the value 83 when in fact it should be 0123. |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Tracked down a bug in swaggerhug, doesn't like leading zero on non-string delimted examples. Work around is to string delimit. Also added regular expression pattern - ^\d{4,4}$. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-806 | SW |  | 2023-11-29 | Electralink | 21470 | Roz Turner | Central Body | Details of the compression team are not defined in the E2E001 design document, only in CR030 at a high level | There is currently no detail in the E2E001 of how data should be compressed and uncompressed for the ECS reports, this information is held in CR030 and DRG documentation. This DIN is to update the E2E001 Architecture design document to add a section to explain this in more detail. |  | Closed | Yes | [6 empty] | Closed - will be picked up in IR7 as part of DIN-806 | Data interface correction | Supporting Docs | Interfaces | Swagger, E2E Architecture Document
MHHS-DIN-807 | SW |  | 2023-11-29 | Electralink | 21470 | Roz Turner | Central Body | Details of the compression team are not defined in the E2E001 design document, only in CR030 at a high level | There is currently no detail in the E2E001 of how data should be compressed and uncompressed for the ECS reports, this information is held in CR030 and DRG documentation. This DIN is to update the E2E001 Architecture design document to add a section to explain this in more detail. |  | Implemented |  |  | Design ambiguous | DIP Users |  | Interim Release 7 | 2024-01-19 | Updated the E2E001 Architecture design document to add a section to explain how data should be compressed and uncompressed for the ECS reports. | Data interface correction | Supporting Docs | Technical Design | E2E001 Architecture Document
MHHS-DIN-808 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-007 EnergisationStatusChange/Failure CustomBlocks missing required attribute | Missing required (mandatory) attribute in object (B025 and B040) |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for inclusion of missing attribute in IF-007. This was adding B025 block as required block in the EnergisationStatusChnage variant of IF-007 and adding B040 block as a required block in the EnergisationStatusFailure variant of IF-007. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-809 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-008 EnergisationStatusChange, common block for R0 and CustomBlocks for B025 block missing required attribute | Missing required (mandatory) attribute in object (R0 and B025) |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for inclusion of missing attribute in IF-008. This was adding R0 block as required block in the Common block of IF-008 and adding B025 block as a required block in the CustomBlock of IF-008. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-810 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-004 common block M0 required attribute is missing | Missing required attribute in object |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for inclusion of missing attribute M0 in the required common block in IF-004 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-811 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-024 missing required attributes in blocks | IF024 SNVacant CustomBlock required B057 IF024 SNRemoteEnabled CustomBlock required B057, B069 IF024 SNSupplierAC CustomBlock required B057, B058 |  | Closed | Yes |  | Error/Correction | DIP Users |  |  |  | Swagger update for inclusion of missing attribute in IF-024 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-812 | RG | DIN-699 | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-036 missing required attributes for B068 block | Missing required attribute in object |  | Closed | Yes |  | Error/Correction | DIP Users |  |  |  | Swagger update for inclusion of missing attribute in IF-036 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-813 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-015 incorrect required Custom Block | There is no customblock on IF-015 |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for removal of custom block in IF-015, as there is no CustomBlock on IF-015. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-814 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-045 incorrect name on Custom block | For IF-045 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-045-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for incorrect name of custom block in IF-045, this has been renamed to CustomBlock. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-815 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | DI-838-Supplier-Proposed-Consent-Granularity requires a null enum | This is to match nullable:true from DES-138. |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for DI-838 to allow null in the enumerated list of values. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-816 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-001 Custom Block missing addtional properties false attribute | IF-001 Custom Block missing addtional properties false attribute |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update for inclusion of missing attribute in IF-001 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-817 | SW |  | 2023-11-29 | Helix |  | Steve Weston | SI Design | Incorrect examples in Swagger for Integers that start with 0 (bug in Swagger Hub) | There are incorrect examples provided for some properties, for example SSC (DI-123) in B032 in the Submit Events on SwaggerHub. This is partly a bug in Swagger Hub where the properties should not start with a '0'. |  | Closed |  |  | Error/Correction | DIP Users |  |  |  | Duplicate of DIN-805
MHHS-DIN-818 | SW |  | 2023-11-29 | Helix |  | Steve Weston | SI Design | IF-014 Payload does not implement B900 block correctly to align with IF-021. | IF-014 should contain a B900 block, not a B900 array. This change was made in IR5 for IF-021, but was only applied to IF-014 in IR6. This DIN is to align with IF-021 for IR5 and ensure that B900 used, not an array of B900's. |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update to IF-014 to align with IR6 implementation | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-819 | SW |  | 2023-11-29 | Helix |  | Steve Weston | SI Design | Typo in event code for REP-004 | In REP-004, the eventCode = [SuplierDemandTakeReport], and supplier is spelt incorrectly. This needs to be updated in both the ECS reports catalogue and Swagger |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Update REP-004 and Swagger the eventCode = [SuplierDemandTakeReport], and supplier is spelt incorrectly. | Data interface correction | Supporting Docs | Interfaces | Swagger, ECS Report
MHHS-DIN-820 | SW |  | 2023-11-29 | Procode | 21898, 21073 | Steve Weston | SI Design | IF-041 contains B06465list that uses anyOf when this should be oneOf B064 or B065 to align with DES-138. | IF-041 contains B06465list that uses anyOf when this should be one of either B064 or B065 to align with DES-138. This needs to be updated so that this list contains wither a B064 list OR B065 list, not both / either. |  | Implemented | Yes |  | Error/Correction | DIP Users |  | Interim Release 5.2 |  | Swagger update to align IF-041 to DES-138. Any of has been removed from the Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-821 | SW | DIN-820 | 2023-11-29 | Procode | 21898, 21073 | Steve Weston | SI Design | IF-041 contains B064/65 list that uses anyOf when this should be oneOf B064 or B065 to align with DES-138. | IF-041 contains B064/65 list that uses anyOf when this should be one of either B064 or B065 to align with DES-138. |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Swagger is aligned to DES-138 to allow one or both B064 and B065. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-822 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-007 EnergisationStatusChange/Failure CustomBlocks missing required attribute | Missing required attribute in object (B025 and B040 respectively are missing from IF-007 EnergisationStatusChange/Failure CustomBlocks. |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Missing required attribute in object (B025 and B040 respectively are missing from IF-007 EnergisationStatusChange/Failure CustomBlocks. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-823 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-008 EnergisationStatusChange, common block for R0 and CustomBlocks for B025 block missing required attribute | IF-008 EnergisationStatusChange, common block for R0 and CustomBlocks for B025 block missing required attribute |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Swagger update for inclusion of missing attribute in IF-008 - IF-008 EnergisationStatusChange, common block for R0 and CustomBlocks for B025 block missing required attribute | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-824 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-004 common block M0 required attribute is missing | IF-004 common block M0 required attribute is missing |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | IF-004 common block M0 required attribute is missing, so this has been added in the Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-825 | RG | DIN-881 | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-024 missing required attributes in blocks | IF024 SN-Vacant CustomBlock required B057 IF024 SN-NoComms CustomBlock required B057 IF024 SNRemoteEnabled CustomBlock required B057, B069 IF024 SNSupplierAC CustomBlock required B057, B058 |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Swagger update for inclusion of missing attribute in IF-024 IF024 SN-Vacant CustomBlock required B057 IF024 SN-NoComms CustomBlock required B057 IF024 SNRemoteEnabled CustomBlock required B057, B069 IF024 SNSupplierAC CustomBlock required B057, B058 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-826 | RG | DIN-699 | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-036 missing required attributes for B068 block | Missing required attribute in object |  | Closed |  |  | Error/Correction | DIP Users |  |  |  | Duplicate of DIN-699 Swagger update for inclusion of missing attribute in IF-036
MHHS-DIN-827 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-015 incorrect required Custom Block | There is no customblock on IF-015, so this has been removed from this Interface on Swagger. |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | There is no customblock on IF-015, so this has been removed from this Interface on Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-828 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-045 incorrect name on Custom block | For IF-045 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-045-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | For IF-045 the validation is failing due to the Custom Block. The required property name is ‘CustomBlock’ but the actual name is ‘IF-045-CustomBlock’ so Swagger needs to be updated to align to be CustomBlock. This change has been made in Swagger. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-829 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | DI-838 and DI-017 - require an N - No Consent enum | DI-838-Supplier-Proposed-Consent-Granularity and DI-017 Consent Granularity requires an N - No Consent enum in the list of allowable values. DI-838 needs to be Mandatory no nulls |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | Swagger updated so that DI-838-Supplier-Proposed-Consent-Granularity and DI-017 Consent Granularity includes N - No Consent in the list of allowable values. DI-838 updated to be Mandatory no nulls | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-830 | RG |  | 2023-11-29 | Avanade |  | Rob Golding | SRO Design | IF-001 Custom Block missing addtional properties false attribute | IF-001 Custom Block missing addtional properties false attribute |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 7 | 2024-01-19 | IF-001 Custom Block missing addtional properties false attribute. Swagger updated to include this. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-831 | BK | DIN-689 | 2023-11-30 | SI Design |  | Madison Layton | Central Body | DI-120 Additional Information should be mandatory nullable | DI-120 was made non nullable in IR5.1 in Swagger. This needs to be corrected so that DI-120 is used in multiple places and needs to be mandatory nullable. |  | Implemented | Yes |  | Design misaligned | DIP Users, DIP |  | Interim Release 5.2 |  | Make DI-120 Additional Information Mandatory nullable in Swagger to align with DES-138. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-832 | RS | DIN-840 | 2023-12-01 | Kraken | 22885 | Henri Naef | Software Provider | [MeterUpdate]) to be added to data item B039 heading for IF-006 | IF-005/IF-006 both contain data item B039, however a difference exists in the header. IF-005 contains "Optional for Event [MeterHistoryUpdate] & [MeterUpdate])" whereas the IF-006 contains only "Optional for Event [MeterHistoryUpdate]) |  | Implemented |  |  | Design misaligned |  |  | Interim Release 7 | 2024-01-19 | DES-138 and Swagger updated to include [MeterUpdate] as Optional for B039 in IF-006. | Data interface correction | Supporting Docs | Interfaces | Swagger, DES138
MHHS-DIN-833 | RS | DIN-841 | 2023-12-01 | UKPN | 23047 | Neal Medley | Network Operator | Routing table to include LDSO for IF-018 | Optionality matrix shows that LDSOs can additionally receive Event Codes [AddressChg], [GSPChg] and [DUOSTariffIDChg]. LDSO to be added to IF-018 secondary routing for these three event codes in DES138 |  | Implemented |  |  | Design ambiguous |  |  | Interim Release 7 | 2024-01-19 | DES-138 updated routing table for IF-018 updated to include LDSO for Event Codes [AddressChg], [GSPChg] and [DUOSTariffIDChg]. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-834 | RG | DIN-818 | 2023-12-01 | SRO |  | Rob Golding | SRO Design | IF-014 - to align with IF-021 | Update DES138 to match swagger |  | Implemented |  |  | Design misaligned | DIP Users, DIP |  | Interim Release 5.2 |  | Update IF-014 to match IF-021 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-835 | RG | MHHS-DIN-836, 882 | 2023-12-04 | Avanade |  | Rob Golding | SRO Design | Add additional error messages to DES138 | Avanade as part of their development work have generated some error codes that need to fed back into DES138: Error Code Error Text MSG1013 Invalid CertifcateIssuerName MSG1014 Certificate has expired MSG1039 Invalid MPAN MSG5001 Internal server error MSG5002 No data contained in request body MSG5003 Unable to determine correlationId requirement. Server configuration error or sender request error MSG5004 Internal server error.Payload not processed |  | Implemented |  |  | Design gap | DIP Users, DIP |  | Interim Release 7 |  | Add error codes into the DES-138 Interface Catalogue (00-Introduction Tab) Error Code Error Text MSG1013 Invalid CertifcateIssuerName MSG1014 Certificate has expired MSG1039 Invalid MPAN MSG5001 Internal server error MSG5002 No data contained in request body MSG5003 Unable to determine correlationId requirement. Server configuration error or sender request error MSG5004 Internal server error.Payload not processed | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-836 | RG | MHHS-DIN-835, 882 | 2023-12-04 | SRO |  | Rob Golding | SRO Design | New swagger file ErrorCodes to describe MHHS error messages | New swagger file (Response Codes schema) to capture all message and error codes from DES138. |  | Implemented |  |  | Design gap | DIP Users, DIP |  | Interim Release 7 |  | New swagger file (Response Codes schema) to capture all message and error codes from DES138. | Data interface correction | Supporting Docs | Interfaces | Swagger E2E001 Architecture Document
MHHS-DIN-837 | SB |  | 2023-12-05 | ESG | 21835 | Patricia Parker | Software Provider | Migration D0086 Clarification | Page 51 of the migration design document shows the following for the D0086. Data Item ‘Meter Reading Reason Code’ (J0332) related enumeration will include 3 additional values:- a. Enumeration Value: 28; Enumeration Description: Forward Migration CoA b. Enumeration Value: 29; Enumeration Description: Forward Migration CoS c. Enumeration Value: 30; Enumeration Description: Reverse Migration My understanding was that the values should reflect those in the D0010 for the migration so parties where aware of the migration process:- Data Item ‘Reading Type’ (J0171) related enumeration will include 3 additional values: a. Enumeration Value: U; Enumeration Description: Forward Migration CoA b. Enumeration Value: V; Enumeration Description: Forward Migration CoS c. Enumeration Value: Y; Enumeration Description: Reverse Migration |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | Changes made to the Migration Design Document in section 13.1.4 (D0086) under point 2 (this now aligns with DES196) as follows; Data Item ‘Reading Type’ (J0171) related enumeration will include 3 additional values: Enumeration Value: U; Enumeration Description: Forward Migration CoA Enumeration Value: V; Enumeration Description: Forward Migration CoS Enumeration Value: Y; Enumeration Description: Reverse Migration | Data interface correction | Supporting Docs | Interfaces | Migration Design Document
MHHS-DIN-838 | SB |  | 2023-12-05 | British Gas | 23696 | Neil Strange | Supplier | BPD004 v5 - step 270 typo | Can you confirm that the reference to SDS method statement in step 270 of the data collection process description is a typo and should be ADS? This is in BPD004 v5. Looks like a simple cut and paste mistake |  | Implemented | No |  | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | BPD004 - step 270 update typo from "SDS" to "ADS" | Process Model correction | Supporting Docs | Process Model description document | BPD004
MHHS-DIN-839 | MF |  | 2023-12-05 | ESG |  | Mike Fensome | Software Provider | Confirmation of DT016 data type | Update all references of DT016 to show as string 14 to align with swagger |  | Implemented | No |  | Design misaligned |  |  | Interim Release 7 | 2024-01-19 | DT016 updated in DES138 to show as String 14 as per swagger for the following data item references: DI-043 Load Shape 7 Day Rolling Total DI-102 Load Shape Period Value DI-104 Configurable Register Reading | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-840 | RS | DIN-832 | 2023-12-01 | Kraken | 22885 | Henri Naef | Software Provider | [MeterUpdate]) to be added to data item B039 heading for IF-006 | IF-005/IF-006 both contain data item B039, however a difference exists in the header. IF-005 contains "Optional for Event [MeterHistoryUpdate] & [MeterUpdate])" whereas the IF-006 contains only "Optional for Event [MeterHistoryUpdate]) |  | Implemented | No |  | Design misaligned |  |  | Interim Release 5.2 |  | DES-138 and Swagger updated to include [MeterUpdate] as Optional for B039 in IF-006. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-841 | RS | DIN-833 | 2023-12-01 | UKPN | 23047 | Neal Medley | Network Operator | Routing table to include LDSO for IF-018 | Optionality matrix shows that LDSOs can additionally receive Event Codes [AddressChg], [GSPChg] and [DUOSTariffIDChg]. LDSO to be added to IF-018 secondary routing for these three event codes in DES138 |  | Implemented | No |  | Design ambiguous |  |  | Interim Release 5.2 |  | DES-138 updated routing table for IF-018 updated to include LDSO for Event Codes [AddressChg], [GSPChg] and [DUOSTariffIDChg]. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-842 | MH |  | 2023-12-06 | St Clements | 22462 | Tom Perryman | Software Provider | REP901, Common Block and Compression | Other REPs have the DIP Distribution Pattern and Report Format defined. This is not the case for the REP900 and REP901 Other REPs have the Routing Rules defined. This is not the case for the REP900 and REP901 |  | Implemented | No |  | Design gap |  |  | Interim Release 7 | 2024-01-19 | For REP-900 and REP-901 Add Distribution Pattern: A Add report format: JSON Add routing rules. Updated schema for Swagger to include compressed schema information as per other ECS reports. | Data interface correction | Supporting Docs | Interfaces | ESC Report, Swagger
MHHS-DIN-843 | RG | DIN-835,836, 882 | 2023-12-07 | SRO |  | Rob Golding | SRO | Add RCP0000 to DES138 and Swagger as a valid a response code | A 'success'response code is required for MPs to provide a valid L3 response. |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | RCP0000 added to DES138 and Swagger as a valid a response code. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-844 | BK |  | 2023-12-07 | Large Suppliers |  | Graham Wood, Haz Elmamoun | Supplier | Standardisation of Interfaces within the Smart Data Services | This CR seeks to avoid cost and inconsistency in the design by adding OPTIONAL standardised messages to support the Meter Data Retriever SDS sub-role. Parties would be able to choose to implement this or come to bilateral arrangements as currently designed. Standardisation can be achieved by adding additional routing to current DIP messages and creating variants of existing messages. | CR023 | Implemented | No |  | Change Request |  |  | Interim Release 7 |  | Updated Business Requirements for parties (SDS/MDR) wishing to take advantage of the standard messages (BRS017) Updated Business Process Diagram (BP017) Updated Message Structures in DES-138 for IF-061, 062, 063, 064, 065. Updated Swagger to align with DES-138 and add new Interfaces. Updated E2E Solution Architect Document | Data interface correction | Supporting Docs | Interfaces | MHHSP-BP017- Optional SDS MDR Standard Interactions BRS017 DES138 Swagger E2E001 Architecture Document
MHHS-DIN-845 | MH |  | 2023-12-12 | St Clements | 24142 | Tom Perryman | Software Provider | REP900 “List of MPANs” field should be mandatory | The REP900 “List of MPANs” field. It is currently optional in the REP900, and should be mandatory. We also believe that Zero should be added as a chargeType. |  | Implemented | No |  | Design gap |  |  | Interim Release 7 | 2024-01-19 | REP900 Changes DI-566 ‘List of MPANs on Site’ to be made a mandatory field to enable receivers of the REP900 to correctly identify the MPANs associated to a site. The population of this field is essential to allow the supplier to know what MPANs the DUoS invoice relates to, enabling them to validate the invoice Update to the possible values for DI-596 ‘Charge Type’ to include ZERO, and format all possible values to CAPS. Additional chargeType values have been added to DI-596 in both DES-138 and Swagger. | Data interface correction | Supporting Docs | Interfaces | ECS Report
MHHS-DIN-847 | MF |  | 2023-12-14 |  |  | Madison Layton | Software Provider | Add error code for IF-025 to validate if Null is provided and value is already Null | MPRS needs a level 5 validation rule to enable MPRS to reject the PUB-025 in the following cases: IHD null when there is no active IHD install status held to end date SMSO null when there is no active SMSO held to end date PC null and PC EFD not null, when there is no active PC held to end date SSC null and SSC EFD not null, where there is no active SSC held to end date |  | Implemented | No |  | Design gap | SCS |  | Interim Release 7 | 2024-01-19 | Added REG0009 - Null Value cannot be set as Value held is already Null. Added validation rules to enable MPRS to reject the PUB-025 using REG0009 in the following cases: IHD null when there is no active IHD install status held to end date SMSO null when there is no active SMSO held to end date PC null and PC EFD not null, when there is no active PC held to end date SSC null and SSC EFD not null, where there is no active SSC held to end date | Data interface correction | Supporting Docs | Interfaces | DES-138
MHHS-DIN-848 | MF |  | 2023-12-14 |  |  | Madison Layton | Software Provider | Clarification on SP de-appointment effective from date in the case of Atomic Secured Active | In rare scenario's Atomic Secured Active messages could result in an Effective To-date which is before the Effective From Date of the Service Provider Appointment 1. Supplier A active at MPAN 2. CSP received for DS with EFD 8th December 3. CSP gets confirmed 4. MPRS receives an Atomic Secured Active for Supplier B (Atomic means there was no Pending notification) on 13th December with SSD 8th December (or earlier) 5. MPRS must de-appoint the DS with ETD = SSD – 1, in this scenario ETD = 7th December |  | Implemented | No |  | Clarification - No change required | SCS, Service Providers, Suppliers |  | Interim Release 7 | 2024-01-19 | Added clarification to IF-037 notes that In rare scenario's Atomic Secured Active messages could result in an Effective To-date which is equal to the Effective From Date of the Service Provider Appointment. And as such the appointment will be deemed as having never taken effect | Data interface correction | Supporting Docs | Interfaces | DES-138
MHHS-DIN-846 | SW |  | 2023-12-13 |  | 24874 | Chris Mingay | Software Provider | B050 consumptionComponentClassID property inconsistency between ECS reports catalogue and Swagger | B050 consumptionComponentClassID property inconsistency between ECS reports catalogue and Swagger. In the ECS reports catalogue, in IR2 and IR5 this is an INT3, min 100 and max 999. This was correct in Swagger 1.2, but in Swagger 1.5, this has reverted to a String3 with min / max values of 3, so does not align to ECS reports catalogue. |  | Implemented | No |  | Design misaligned |  |  | Interim Release 7 | 2024-01-19 | Update Swagger to align with ECS reports catalogue for B050 consumptionComponentClassID to be an Integer. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-849 | MF |  | 2023-12-14 |  |  | Madison Layton | Software Provider | Change B099 to be a single block rather than a list in IF-035 | In IF035 SDS-MDROutcome variant, make B099 a single block in the swagger rather than a list. |  | Implemented | No |  | Error/Correction | SCS, Service Providers, Suppliers, DIP |  | Interim Release 7 | 2024-01-19 | Swagger updated so that for IF035 SDS-MDROutcome variant, B099 is a single block in the swagger rather than a list. | Data interface correction | Supporting Docs | Interfaces | Swagger DES-138
MHHS-DIN-850 | MH |  | 2023-12-14 |  |  | Matt Hall | SI Design | CR36 - Clock Time Reads and Appointments | Implementation of the Design Changes required to support CR36 | CR036 | Implemented | No |  | Change Request | All Participants |  | Interim Release 7 |  | Update the artefacts as per CR36 | Data interface correction | Supporting Docs | Various documents | BP003, BP003C, DES138, BRS001, BRS003, METH005, METH007
MHHS-DIN-851 | MH |  | 2023-12-14 |  | 25624/33640 | Sarah Jones | Central Body | Outstanding Queries to Support Interface Code Drafting | Update the data catalogue in DES-138 to show the correct data types and data type descriptions |  | Open - awaiting assessment | No |  | Clarification - No change required | All Participants |  | Post Go-live Release |  | Clean up data catalogue in DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-852 | MH |  | 2023-12-14 |  | 21890 | Mike Ceney | Central Body | ECS Report 006 | Within block R003- CCC Determined Data, the Domestic Premise Indicator (DI-030) is to be populated, I believe this to be incorrect and needs to be removed from the report. This data item is populated at an Mpan level but this report is at BMU level so therefore cannot be populated |  | Implemented | No |  | Error/Correction | Helix, Suppliers |  | Interim Release 7 | 2024-01-19 | Remove Domestic Premise Indicator from REP 006 | Data interface correction | Supporting Docs | Interfaces | MHHSP - ERI011B - ECS Reports - External
MHHS-DIN-853 | SB |  | 2023-12-14 |  |  |  | SRO Design Team | Addition of new RetroSpective Date Validation Rules following DRG Review & Sign Off | Amended IF-025 Validation rules for SSC& Profile Class Eff From Date to include Migration Date per reviewed & agreed RetroDates PPT. No changes rquired to any other data items as a result of RetroDates Functionality. |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | Amended IF-025 Validation rules for SSC& Profile Class Eff From Date to include Migration Date in DES138. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-854 | SW |  | 2023-12-15 | IMServ | 24832 | Liam Lowey | Software Provider | DI-085 GUID definition | DI-085 GUID definition does not align with Industry definition of a GUID ie, 8 HEX, 4x3 HEX, then 12 HEX, but rather, this refers to an SME GUID that is not a true GUID but rather a EUI base 64 address, akin to an IP v6 address. Need to update the example so that DI-085 provides clarity on whether HEX values are included. |  | Implemented | No |  | Design ambiguous |  |  | Interim Release 7 |  | Update example in the DI-085 property to align with a EUI base 64 address, akin to an IP v6 address. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-855 | SW |  | 2023-12-15 | Callisto | 24828 | Neil Edney | Software Provider | Swagger required properties are not aligned with Swagger property names | There are a number of blocks where the Swagger required properties are not aligned with Swagger property names which will cause a schema validation error incorrectly. B051 - GPSGroupID and domesticPremiseIndicator - properties and required properties do not align. B014 - incomingMeteringServiceEffectiveDate and incomingMeteringServiceDIPEffectiveFromDate - properties and required properties do not align. B021 - customerDirectContractDataServiceEffectiveDIPID and customerDirectContractDataServiceDIPID - properties and required properties do not align. |  | Closed | No |  | Design misaligned
MHHS-DIN-856 | PP | ADO Defect 19010 | 2023-12-15 | Programme |  | Paul Pettitt | SI Design | DI-020 example incorrect Length | DI-020 Contract Reference data service has a Max length of 10 chars, the example is 11 |  | Closed | Yes | 19010 | Error/Correction | DIP Users |  |  |  | Corrected in IR5.3 Maximum set to 50 and example is correct.
MHHS-DIN-857 | RG |  | 2023-12-18 | SRO |  | Rob Golding | SRO Design | Ensure all enumerated types have obfuscated values (where needed) (IR 5.3 Release) | Ensure all enumerated type that are obfuscated contain the obfuscated value in the enumerated list. This change affects the following: IF-035 DI-979 Response Code DI-800 Service Provider Appointment Scenario DI-838 Supplier Proposed Consent Granularity DI-126 Traditional Fall Back Read Frequency IF-036 DI-017 Consent Granularity Obfuscated DIP IDs wil be 9999999999 as the regex dictates it needs to be a 10 character numeric string |  | Implemented | Yes | 18999 | Design gap |  |  | Interim Release 5.3 |  | Updated all enumerated type that are obfuscated contain the obfuscated value in the enumerated list. This change affects the following: IF-035 DI-979 Response Code DI-800 Service Provider Appointment Scenario DI-838 Supplier Proposed Consent Granularity DI-126 Traditional Fall Back Read Frequency IF-036 DI-017 Consent Granularity | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-858 | RG |  | 2023-12-18 | SRO |  | Rob Golding | SRO Design | Ensure all enumerated types have obfuscated values (where needed) (IR 7 Release) | Ensure all enumerated type that are obfuscated contain the obfuscated value in the enumerated list. This change affects the the following: IF-035 DI-979 Response Code DI-800 Service Provider Appointment Scenario DI-838 Supplier Proposed Consent Granularity DI-126 Traditional Fall Back Read Frequency IF-036 DI-017 Consent Granularity Obfuscated DIP IDs wil be 9999999999 as the regex dictates it needs to be a 10 character numeric string |  | Implemented | Yes | 18999 | Design gap |  |  | Interim Release 7 | 2024-01-19 | Ensure all enumerated type that are obfuscated contain the obfuscated value in the enumerated list. This change affects the the following: IF-035 DI-979 Response Code DI-800 Service Provider Appointment Scenario DI-838 Supplier Proposed Consent Granularity DI-126 Traditional Fall Back Read Frequency IF-036 DI-017 Consent Granularity Obfuscated DIP IDs wil be 9999999999 as the regex dictates it needs to be a 10 character numeric string | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-859 | MH |  | 2023-12-20 | St Clements | 24142 | Tom Perryman | Software Provider | REP900 invoice | Currently, the REP900 has one or many invoices for each site / invoice data (R900-05 level). This needs to be updated so that the REP900 contains one or many combinations of site and invoice data (R900-04 level). Currently a single D2021 is sent to a supplier containing all their HH invoices produced on that billing day. |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7 |  | Correct the REP900 record hierarchy to: Clarification of the record hierarchy to enable the inclusion of multiple invoices on a single REP900 R900-01 Distributor Info - a single Distributor on a REP900 R900-02 Supplier Info - a single Supplier on a REP900 > R900-03 Site Info > R900-04 Invoice Data - one or many combinations of Site and Invoice Data >> R900-05 Invoice Lines - one or many invoice lines for each combination of Site and Invoice Data | Data interface correction | Supporting Docs | Interfaces | Swagger MHHSP - ERI011B - ECS Reports - External
MHHS-DIN-860 | RG |  | 2023-12-21 | SRO |  | Rob Golding | SRO Design | Clarification on Webhook callback responses | At present the webhook callbacks are limited in their responses to 200 & 207. The extent of the responses needs to align with the other DIP APIs |  | Implemented | Yes | 19120 | Design gap |  |  | Interim Release 5.3 |  | Aligning participant systems with the DIP in terms of HTTP responses, added in a standard set of response codes to be used in the Swagger. Also described are how HTTP responses received from the DIP should be interpreted, and what HTTP responses the DIP is expecting back from participants webhooks in the E2E Architecture document. | Data interface correction | Supporting Docs | Various documents | Swagger E2E Architecture
MHHS-DIN-861 | RG |  | 2023-12-21 | SRO |  | Rob Golding | SRO Design | Clarification on Webhook callback responses | At present the webhook callbacks are limited in their responses to 200 & 207. The extent of the responses needs to align with the other DIP APIs |  | Implemented | Yes | 19120 | Design gap |  |  | Interim Release 7 |  | Aligning participant systems with the DIP in terms of HTTP responses, added in a standard set of response codes to be used in the Swagger. Also described are how HTTP responses received from the DIP should be interpreted, and what HTTP responses the DIP is expecting back from participants webhooks in the E2E Architecture document. | Data interface correction | Supporting Docs | Various documents | Swagger E2E001 Architecture Document
MHHS-DIN-862 | RG |  | 2024-01-02 | SRO |  | Rob Golding | SRO Design | REP901 missing event code | The eventcode on REP-901 need correcting to [DUoSEmbeddedLDSOAggInvData] & [DUoSSupplierAggInvData] (or do we have two reports?) |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7 |  | Update the following REP-901 data items as follows [DUoSEmbeddedLDSOAggInvData] & [DUoSSupplierAggInvData] to ensure that ECS reports align with naming standards and ensure that Swagger aligns with ECS reports catalogue. | Data interface correction | Supporting Docs | Interfaces | ESC Report, Swagger
MHHS-DIN-863 | SB |  | 2024-01-03 | Kraken | 27359 | Henri Naef | Software Provider | IF-019/020 Discrepancy between E2E and Swagger | It looks like in the e2e guide there’s no mention of an M1 block in the common block. However in the swagger documentation for IF019 and IF020 there is. What’s weirder is that for both of those there is no M0 block which the e2e guide says there should be." |  | Open - awaiting assessment | No |  |  |  |  | Post Go-live Release |  | Solution under review/discussion | Data interface correction | Supporting Docs | Interfaces | E2E001 Architecture Document
MHHS-DIN-864 | ZH |  | 2024-01-08 | SJW |  | Sarah Jones | Central Body | CR024 - Update of two data items | As flagged at the last DAG and in our email on 21 Dec, RECCo believes there are two incorrect data items in the MHHS design: Manufacturer Code should be Manufacturers Make and Type CSS Registration Request Id should be CSS Registration Id. We believe failure to correct these data item in line with approved CR024 (particularly the CSS Registration Id) may lead to parties including the wrong data items within their design, impacting testing outcomes (both SIT and Qualification) and leading to operational issues post go live. | CR024 | Implemented | No |  | Error/Correction |  |  | Interim Release 7 |  | Update the names of both data items in the Swagger and DES138, in the relevant areas. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-865 | RG |  | 2024-01-12 |  |  |  |  | EMSE ID example has non-hexadecimal chars | DES-138 and the swagger have a non-hex character in the example |  | Closed | Yes | 23294 | [5 empty] | Update example to remove leading S character
MHHS-DIN-866 | SW | DIN-880 | 2024-01-16 | Stark | 29309 | Jon Dennis | Software Provider | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7 | 2024-01-19 | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD. Swagger updated to align. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-867 | RG |  | 2024-01-16 | PDA |  | Richard French |  | Remove all references to UDS & UMDS in E2E SA doc | Replace UMDS with UMSDS - multiple instances still exist |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7 |  | E2E documentation still contains references to UMDS - this needs to be removed and replaced with UMSDS | Data interface correction | Supporting Docs | Interfaces | E2E001 Architecture Document
MHHS-DIN-868 | RS |  | 2024-01-16 |  | 19802 | Rob Short | SI Design | Correction of Advanced Data Service Validation and Estimation (Meth002) | Following review and participant comments, multiple updates are required to correct SDS references in the ADS method statement |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7 |  | Updates made to all sections of MHHSP-METH002_ADS_Validation_Estimation | Method statement correction | Supporting Docs | Method Statement | METH002
MHHS-DIN-869 | RS |  | 2024-01-16 |  | 19802/20645 | Rob Short | SI Design | ADS Method Alignment | Updates to the ADS estimation methods |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7 |  | Update to section 3 of of MHHSP-METH002_ADS_Validation_Estimation | Method statement correction | Supporting Docs | Method Statement | METH002
MHHS-DIN-870 | SW |  | 2024-01-17 | St Clements | 26647 | Madison Layton | SI Design | IMS-SendMTD variant for IF-035 does not contain properties B070, B071 and B019 to align with DES-138 | IMS-SendMTD variant for IF-035 does not contain properties B070, B071 and B019 to align with DES-138 - which identifies this variant of a copy of the variants DSAppAccepted and MSAppAccepted |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7 |  | Swagger 1.7 IF-035-IMS-SendMTD: should be updated to include B070, B071 and B019 as optional fields in this variant. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-871 | RG |  | 2024-01-17 | SRO |  | Rob Golding | SRO Design | Changes to E2E SA doc & Swagger for replay message version support | The E2E SA doc (& swagger) needs to be updated to include message version support for replay |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7 |  | E2E SA document include a description on message versioning for message replay. This includes changes to section 4.9 and 8.5.2 of the E2E001 design document, removal of section 5.5 (it has been combined into section 4.9). Also updates to Swagger to add version in the MessageRequest object. | Technical corrrection | Supporting Docs | Interfaces | E2E001 Architecture Document Swagger
MHHS-DIN-872 | RS |  | 2024-01-18 | IMServ | 30201 | Rob Short | SI Design | Historic consumption data following the IF-015 request | Conflicting information in the NOTES section: “The structure and content of this message will be subject to further discussion as part of the 'DIP Detailed Design', as the exact way in which this requirement/functionality is realised may depend on the DIP Solution option(s) chosen. The basis of the functionality is that participants will be 'REPLAYED' facsimiles of the previously submitted IF-021 (SP Consumption Submission) / IF-013 (SP Defaulted) Records - however it may be possible that some kind of 'blended' response, as eluded to here, is also possible.” |  | Implemented |  |  | Design gap |  |  | Interim Release 7 |  | Removal of Interface note on IF-16 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-873 | RS |  | 2024-01-19 | Elexon | 21459 | Phil Milmine | Central Body | Correction to VAS Method Statement | Amendment to section 3.28 around “VAS Defaulting” and the report linked to this process (REP-007) to reflect the manual steps that Elexon would need to take to enable this. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7 |  | Amend text to 17. VAS Re-run where Initial VAR incomplete due to missing MDS or CDCA data 3.28 In the event that the VAS is unable to complete an Initial VAR due to missing data from MDS or CDCA, the VAS shall use replacement data at BSCCo’s discretion to re-run by BM Unit, as per a normal VAS run. Substituted data must be reported to Market Participants. | Method statement correction | Supporting Docs | Method Statement | METH006
MHHS-DIN-874 | RG | DIN-829 | 2024-01-23 |  |  | Rob Golding | SRO Design | Consent Granularity not nullable and N - no consent | Implement DIN-829 in 5.x swagger and update DES138 accordingly |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Swagger/ DES138 updated so that DI-838-Supplier-Proposed-Consent-Granularity and DI-017 Consent Granularity includes N - No Consent in the list of allowable values. DI-838 updated to be Mandatory no nulls. DI-838 description updated to align with the data item name in Swagger. | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-875 | SW |  | 2024-01-23 | Kraken | 31011 | Angelos Rizoyannis | SI Design | Swagger objects and descriptions are missing | Missing `type: object` - for the following blocks B079, B080, B081, B082, B083, B090, B091 - Missing `description: ...’ object for R901-08 - Incorrect description - IF-004-Payload08, IF-006-MeterRemoval.CustomBlock, IF-006-MeterExchange.CustomBlock |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Missing `type: object` - for the following blocks - B075, B076, B079, B080, B081, B082, B090, B091 - Missing `description: ...’ object for R901-08 - Incorrect description - IF-004-Payload08, IF-006-MeterRemoval.CustomBlock08, IF-006-MeterExchange.CustomBlock08 Update Swagger to fix above issues. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-876 | RG |  | 2024-01-24 | SRO |  | Rob Golding | SRO Design | IF-003 LDSO routing is secondary not always | DES138 has IF-003 LDSO routing incorrectly specified, the routing is secondary not always |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7 |  | Update DES138, IF-003 LDSO routing is secondary not always | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-877 | RG | DIN-620 | 2024-01-24 |  |  | Rob Golding | SRO Design | IF-001 Remove EES (CR023) | DIN-620 was not fully implemented, EES is still mentioned in DES138 IF-001 |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7 |  | EES removed DES138 IF-001 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-878 | RG | DIN-870 | 2024-01-17 | St Clements | 26647 | Madison Layton | SI Design | IMS-SendMTD variant for IF-035 does not contain properties B070, B071 and B019 to align with DES-138 | IMS-SendMTD variant for IF-035 does not contain properties B070, B071 and B019 to align with DES-138 - which identifies this variant of a copy of the variants DSAppAccepted and MSAppAccepted |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Updated Swagger IF-035-IMS-SendMTD: to include B070, B071 and B019 as optional fields in this variant | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-879 | RG | DIN-849 | 2023-12-14 |  |  | Madison Layton | Software Provider | Change B099 to be a single block rather than a list in IF-035 | In IF035 SDS-MDROutcome variant, make B099 a single block in the swagger rather than a list. |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Updated Swagger IF035 SDS-MDROutcome variant, and made B099 a single block rather than a list. This has also necessitated in an update to DES138 to the routing information for IF-035. | Data interface correction | Supporting Docs | Interfaces | Swagger, DES138
MHHS-DIN-880 | MF | DIN-866 | 2024-01-24 |  |  | Jon Dennis | Software Provider | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD | DI-059 Contains “MAIN” in DI-059-Meter-Type enum, should be MAIN_ to align with ISD |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Updated “MAIN” in DI-059-Meter-Type enum in swagger, to be "MAIN_" to align with ISD | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-881 | MF | DIN-825, DIN-811 | 2024-01-24 | Avanade |  | Rob Golding | SRO Design | IF-024 missing required attributes in blocks | IF024 SN-NoComms CustomBlock required B057 IF-024-SN-RemoteDisabled required B069, B057 |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Update swagger with the following: IF024 SN-Vacant CustomBlock required B057 IF024 SN-NoComms CustomBlock required B057 IF024 SNRemoteEnabled CustomBlock required B057, B069 IF024 SNSupplierAC CustomBlock required B057, B058 | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-882 | MF | DIN-835,836, 843 | 2024-01-24 | SRO |  | Rob Golding | SRO Design | New swagger file ErrorCodes to describe MHHS error messages and updates to error messages in DES138 | New swagger file (Response Codes schema) to capture all message and error codes from DES138 including RCP0000 (Message Success) and the following error codes: Error Code Error Text MSG1013 Invalid CertifcateIssuerName MSG1014 Certificate has expired MSG1039 Invalid MPAN MSG5001 Internal server error MSG5002 No data contained in request body MSG5003 Unable to determine correlationId requirement. Server configuration error or sender request error MSG5004 Internal server error.Payload not processed |  | Implemented |  |  | Design gap | DIP Users |  | Interim Release 5.4 |  | New swagger file (Response Codes schema) to capture all message and error codes from DES138 DES138 updated with RCP0000 (Message Success) and the following error codes: Error Code Error Text MSG1013 Invalid CertifcateIssuerName MSG1014 Certificate has expired MSG1039 Invalid MPAN MSG5001 Internal server error MSG5002 No data contained in request body MSG5003 Unable to determine correlationId requirement. Server configuration error or sender request error MSG5004 Internal server error.Payload not processed | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-883 | RG |  | 2024-01-24 | SRO | 31749 | Matt McKeon | SRO Design | Data item clashes between DES138 and ECS Reports | We have noticed that there are some DI-REF numbers which have been used twice in DES138 and ERI011B. - Specifically the newer data items introduced for migration start in the 500s, when these are also used in ECS Reports. |  | Implemented |  |  | Error/Correction | ECS |  | Interim Release 7 |  | Move duplicated ECS numbers to an unused range | Reporting correction | Supporting Docs | ECS Reports | ERI011B
MHHS-DIN-884 | BK |  | 2024-01-26 | SRO |  | Kevin Spencer | SRO Design | CR032: Replacement of REP080 to use the P210 | The revised design would require: Elexon revise the build of the P0210 to include both non-migrated and migrated consumption. The format and structure will not change. The ESO ingest the P0210, ensuring that its integration and middleware systems can process the file. As per the the integration and middleware diagram, two systems (LIMS and CIS/MFT) will need configuration changes. The ESO regression test its Revenue systems based on the revised P0210 to ensure it continues to meet the requirements for TNUoS and BSUoS reporting. After the end of the Transition Period, if the ELEX-REP-080 report was developed, the existing P0210 file and associated processing of that file would become redundant. | CR032 | Implemented |  |  | Change Request |  |  | Interim Release 7 |  | Updates made to the following artefacts; Amended METH006 section 3.7 Removal of REP080 in the ECS Report Update wording in BP020 step 75 to reference the P0210 and subsequent BPD doc | Data interface correction | Supporting Docs | Interfaces | METH006 ESC Report BP020 and BPD020
MHHS-DIN-885 | BK |  | 2024-01-26 | SRO |  | Matt McKeon | SRO Design | Add URLs pointing to new DTC format definition documents in ERI011B | Update four tabs of ERI011B to add a URL pointing to new DTC format definition documents for these reports |  | Implemented | [5 empty] | Interim Release 7 |  | Update MHHS-REP-D0369 to say ‘Defined in DTC format as D0401 at: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx · Update MHHS-REP-D0370 to say ‘Defined in DTC format as D0402 at: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx · Update MHHS-REP-D0373 to say ‘Defined in DTC format as D0403 at: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx · Update MHHS-REP-D0374 to say ‘Defined in DTC format as D0404 at: https://mhhsprogramme.sharepoint.com/sites/Market-wideHalfHourlySettlement/SitePages/Data-Transfer-Network-flows.aspx Grey out all the reports specified above | Reporting correction | Supporting Docs | Interfaces | ERI011B
MHHS-DIN-886 | MF |  | 2024-01-26 | St Clements |  | SCS | Software Provider | Addition of 905 existing meter listing block to all events in IF-006 | Add B905 (existing meter listing) block for all IF-006 event codes in Swagger |  | Implemented | [5 empty] | Interim Release 7 |  | Add B905 (existing meter listing) block for all IF-006 event codes in Swagger | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-887 | MF |  | 2024-01-26 | St Clements |  | SCS | Software Provider | Addition of 905 existing meter listing block to all events in IF-006 | Add B905 (existing meter listing) block for all IF-006 event codes in Swagger |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Add B905 (existing meter listing) block for all IF-006 event codes in Swagger | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-888 | SW |  | 2024-01-29 | Kraken |  | Angelos Rizoyannis | Software Provider | Property "type: object" missing from IF-024 variants in Swagger | Property "type: object" missing from IF-024 variants in Swagger. This needs to be added to all variants where this is missing. |  | Implemented | [5 empty] | Interim Release 7 |  | Property "type: object" missing from IF-024 variants in Swagger. This needs to be added to all variants where this is missing. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-889 | SW |  | 2024-01-29 | Kraken |  | Angelos Rizoyannis | Software Provider | Property "type: object" missing from IF-024 variants in Swagger | Property "type: object" missing from IF-024 variants in Swagger. This needs to be added to all variants where this is missing. |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Property "type: object" missing from IF-024 variants in Swagger. This needs to be added to all variants where this is missing. | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-890 | RS |  | 2024-01-29 | CGI |  | Dave Webster | Software Provider | DI-038 (LInked Import/Export Mpan) description | Confusion over wording in DI-038. Where more than one import MPAN exists, this shall be populated with the Primary Import MPAN |  | Implemented | [5 empty] | Interim Release 8 | 2024-03-20 | Remove wording 'Where more than one import MPAN exists, this shall be populated with the Primary Import MPAN' from all DI-038 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-891 | SB |  | 2024-01-30 | St Clements | 21513 | SCS | Software Provider | DI-241 - SUPC routing on IF-037 incorrect, should be SUPS | The primary routing for MSDeAppUpdate and DSDeAppUpdate is incorrect, XMSC and XDSC is the currently appoint SP but the flow needs to go to the already de-appointed SPs |  | Implemented | [5 empty] | Interim Release 8 | 2024-03-20 | Update Primary Routing to show Previously de-appointed Data Service/ Metering Service | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-892 | RG |  | 2024-01-31 | RDG |  | RDG | SRO | Message Versioning Support: Create DIPMessage variant for egress | Split DipMessage in two, one for ingress (current version) and another for egress (new) in order to support multiversion messages on egress for replay/requeue |  | Implemented | [5 empty] | Interim Release 8 | 2024-03-20 | Add new DIPEgressMessage to the swagger in order to split the incoming and outgoing APIs to allow multiversion support | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-893 | RG |  | 2024-01-31 | BJSS |  | Soniya | Software Provider | Regex for GSP Correction factor | We want to check if the regex is correct for GSP Group Correction Factors: ^-?\d{1,9}\.\d{9} The highlighted section suggests the – is optional but GCFs are always positive. Can the regex be updated to reflect this? |  | Implemented | [5 empty] | Interim Release 7.1 |  | Regex update in Swagger to enforce only positive numbers. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-894 | RG |  | 2024-01-31 | SIMs & Ems |  | John | Software Provider | DI-123-SSC is nullable in IR7, needs to be the same in IR5.x | B032 eg on IF-002 has property SSC which was made non nullable in 1.5.2 or 1.5.3 has been left nullable in 1.7 |  | Implemented |  |  | Error/Correction | DIP Users |  | Interim Release 5.4 |  | Update B032 eg on IF-002 has property SSC so that it is non nullable | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-895 | MH |  | 2024-02-01 | St Clements | 31597 | Virginia Patey | Software Provider | REP002s vs IF-21s for DUoS Billing. Follow up from DIN340 | Change required to MDS Method Statement... DIN-340 was raised by UKPN to highlight the fact that while DNOs were to receive the correct IF-021 data, the data on the DUoS Report would also include meter data for most MPANs with a connection type <> ‘W’. Additionally, given the fact that the DNOs require meter data for all sites via either the REP002s or the IF-021s, using different data items to determine the inclusion or exclusion from a particular delivery method risks DNOs not receiving data for some MPANs via either route and thereby negatively impacting their invoicing. Please note that an MS Site Specific LLF Id indicator of ‘B’ (Site Specific Import) or ‘D’ (Site Specific Export) does NOT equate to a connection type <> ‘W’. In fact the MPANs with a MS Site Specific Indicator of ‘B’ or ‘D’ is a very small subset of those with a connection type <> ‘W’. For the avoidance of doubt, the use of the term ‘site specific’ for billing types and MS Site Specific LLF Id indicators are separate things and do not equate to one another. Required Solution: We require the rules for what should be included on the DUoS Report (i.e. the wording for 17.3) to be changed to: The DUoS Report calculations shall only be undertaken for SPC data that is for MPANs with a connection type = ‘W’ 17.4 is not required as DNOs should be using all IF-021 in site specific billing. |  | Implemented | No |  | Error/Correction | ECS, DNOs |  | Interim Release 8 | 2024-03-20 | Rules for what should be included on the DUoS Report (i.e. the wording for 17.3) to be changed to: The DUoS Report calculations shall only be undertaken for SPC data that is for MPANs with a connection type = ‘W’ 17.4 is not required as DNOs should be using all IF-021 in site specific billing. | Method statement correction | Supporting Docs | Method Statement | METH007 ERI011B - ECS Reports
MHHS-DIN-896 | MH |  | 2024-02-06 | ESG | 32706 | Patricia Parker | Software Provider | ISD v5.5 (Ref 265) | The two new entities M20 & M21 (DIN-754) do not appear in the table of contents. Can these be added? |  | Implemented | No |  | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Update the table of contents to include two new entities M20 & M21 (from DIN-754). | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-897 | RG |  | 2024-02-06 | Flui | 32997 | Jason Jackson | Software Provider | IF-001 Change Of Supplier s0 block needs to mandatory | s0 block needs to mandatory, DIN-785 missed off the S0 block, ok in 5.4 not 7. the A0 block is marked as mandatory, it should be S0. (the orignial published DIN stated this was the S1 block, this is an error, in fact it should be the s0 block) |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7.1 |  | Minor swagger update to enforce a manadatory field | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-898 | MH |  | 2024-02-07 | Elexon | 31846 | Derek Weaving | Central Body | REP-003 fields - Clarification Request | DI-339 BM Unit Allocated Demand Disconnection Volume Losses should not be in the REP003 The DDE does not calculate losses separately and they are already included in DI-341 volume that sums across all CCCids including the ones for losses. |  | Implemented | No |  | Error/Correction | Suppliers |  | Interim Release 7.1 |  | Remove DI-339 and the DI-370 from the REP-003 Swagger update and ECS Report | Technical corrrection | Supporting Docs | Interfaces | Swagger ERI011B - ECS Reports
MHHS-DIN-899 | MH |  | 2024-02-07 | Elexon | 32697 | Rashmi Radhakrishnan | Central Body | IR7 Changes to ISD | In IR7, DIN-759 included an update to ISD Entitiy M17. tHis update was only partially completed. This DIN is to correct it and to add Meter Group to the Entity and also to add N to M15 as previously agreed |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7.1 |  | Add Meter Group to the Entity - M17 Add N - No Consent to M15 | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-900 | RG |  | 2024-02-07 | SRO Design |  | RG | SRO Design | IR7 E2E SA Obfuscation rules require updating | Data items that are MPIDs need to be obfuscated to 'XXXX' rather than 'xxxx' so the regex remains unbroken |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7.1 |  | MPIDs that are obfuscated will be 'XXXX'. Avanade change, PPs need to be aware. | Technical corrrection | Supporting Docs | Interfaces | E2E Architecture
MHHS-DIN-901 | RG |  | 2024-02-08 | SRO Design |  | RG | SRO Design | DES138 does not include CR23 opting in for MDRs | The IR7 version of DES138 does not include the 'opting' information for MDRs. The following needs to be icluded as opted in PUB-006 [MeterInstall], [MeterRemove], [MeterExchange], [MeterUpdate] PUB-008 [EnergisationStatusChange] PUB-026 [ConsentGranularity], [SMSO], PUB-024 [SN-RemoteEnable], [SN-RemoteDisable], [SN-NoComms] |  | Implemented | No |  | Design gap |  |  | Interim Release 7.1 |  | Update DES138 to include the 'opting' information for MDRs in the following PUBS; PUB-006 [MeterInstall], [MeterRemove], [MeterExchange], [MeterUpdate] PUB-008 [EnergisationStatusChange] PUB-026 [ConsentGranularity], [SMSO], PUB-024 [SN-RemoteEnable], [SN-RemoteDisable], [SN-NoComms] | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-902 | MH |  | 2024-02-09 | SRO | 33170 | Andrew Margan | Central Body | Reverse Migration Consistency | Step 190 of MHHS-DEL971 - BPD001 and DEL965 BPM001 - Change Of Supply - Reverse Migration suggest the incoming supplier has a choice of whether to reverse migrate or not. This isn't the case; a reverse migration will only happen where the incoming supplier is not qualified on the MHHS TOM |  | Closed | No |  | Error/Correction |  |  |  |  | The Process step is showing the Incoming Supplier choosing whether to start reverse migration or not. In this scenario, the Incoming Supplier is not MHHS qualified. However, they will have to determine if it is a reverse migration scenario based on the info in the D0260/D0217. In that respect they must choose whether they need to follow reverse migration or legacy process
MHHS-DIN-903 | MF |  | 2024-02-12 | Elexon | 34297, 34973 | Raina Jain | Central Body | Missing/ incorrect BPD011 step | Step 211 is missing from “(BP011A) MHHSP-BPD-011” tab in MHHSP-BPD011 - Change of Con Type or Market Segment document." Correct step 275 to show that this applies for successful meter exchanges |  | Open - awaiting assessment | No |  | Error/Correction |  |  | Post Go-live Release |  | Add step 211 to BPD011 to align with BP011. This shows the Metering Service receiving the Appointment Response (PUB-035) from Registration Service. Update step 275 to show that this applies for successful meter exchanges | Process Model correction | Supporting Docs | Process Requirements Doc | BPD011
MHHS-DIN-904 | RG | DIN-924 | 2024-02-12 | SRO |  | Rob Golding | SRO Design | Missing parameters in webhook callback | The definition in the webhook callback in swagger is missing the definition - $ref: '#/components/parameters/CommonSignatureHeader' - $ref: '#/components/parameters/CommonSignatureDateHeader' - $ref: '#/components/parameters/CommonSHA256Header' - $ref: '#/components/parameters/CommonSignatureCertifcateHeader' |  | Implemented | No |  | Clarification - No change required |  |  | Interim Release 5.5 |  | Update to swagger to include missing parameters; aligns with CoCo | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-905 | RG | DIN-864 | 2024-02-14 | SRO |  | Rob Golding | SRO Design | B033 block meterManufacturer IR7 | B033 block meterManufacturer was renamed to manufacturersMakeAndType it wasn't renamed in the 'required' properties |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7.1 |  | Update B003 requried fields to include manufacturersMakeAndType | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-906 | RG | DIN-925 | 2024-02-14 | SRO Design |  | Rob Golding | SRO Design | Add MPO Encrypted header parameter to callback | Add a parameter to the callback so that the MTLS cert can be authenticated by the MTLS connection. No impact on MPs, Avanade improving the secuirty handshake on the callback |  | Implemented | No |  | Design gap | Avanade |  | Interim Release 5.5 |  | Add MPO Encrypted header parameter to callback | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-907 | RG | DIN-926 | 2024-02-14 | SRO Design |  | Grant Sutcliffe | Avanade | Response codes on delete operations | Standardise response message for successful delete operations on API calls -204 needs to have the text 'No Content' . Need to add other response codes in-line with the other APIs |  | Implemented | No |  | Design misaligned |  |  | Interim Release 5.5 |  | Standardise response message for successful delete operations on API calls -204 needs to have the text 'No Content' . Need to add other response codes in-line with the other APIs | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-908 | MF | DI-249 | 2024-02-15 | St Clements |  | Madison Layton | Software Provider | Validation of Appointment start times | Move REG1032 from Migration Only Validation Rules to BAU Validation Rules section in IF-031 |  | Implemented | No |  | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Move REG1032 from Migration Only Validation Rules to BAU Validation Rules section in IF-031 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-909 | RS |  | 2024-02-15 | EDW | 34934 | Darren Kay | Software Provider | Duplicate requirement reference used in MHHS-E2E002 Requirements v3.1 document | E2E1009 requirement reference is used for Level 4 Processing Times (Asynchronous) and Unplanned Outages in MHHS-E2E002 Requirements v3.1 document. Adjustment required to one of the references |  | Implemented | No |  | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Remove duplicate reference to requirement in E2E002 doc. | Requirement correction | Supporting Docs | Requirement correction | E2E002 Requirements
MHHS-DIN-910 | MF |  | 2024-02-16 | SRO Design |  | Mike Fensome | SRO Design | Remove sending of IF-041 for invalid meter readings from SDS method statement | SDS Method Statement 2.37 refers to SDS sending an IF-041 where reads are invalid. This is not allowed for in the design and should be removed |  | Implemented | No |  | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Remove sending of IF-041 for invalid meter readings from SDS method statement | Method statement correction | Supporting Docs | Method Statement | METH001 SDS Validation Estimation
MHHS-DIN-911 | MF | DIN-849 | 2024-02-16 | St Clements |  | Madison Layton | Software Provider | Update B099 block to show that it is not an array | Update B099 block (IF-035) in DES138 to align with swagger to show that it is not an array |  | Implemented | No |  | Error/Correction |  |  | Interim Release 7.1 |  | Updated B099 block (IF-035) in DES138 to show that it is not an array | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-912 | RG |  | 2024-06-15 | SRO Design |  | Rob Golding | SRO Design | Incorrect 1.7 reference in 1.5.4 swagger | There was a reference to a 1.7 object from 1.5.4. module which meant the 1.5.4. swagger wasaa not resolving correctly |  | Implemented | No |  | Error/Correction |  |  | Interim Release 5.4 |  | Swagger rebuilt | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-913 | SB | DIN-503 DIN-780 | 2024-02-14 | St Clements | 19885 | Madison Layton | Software Provider | Missed Update to DES138 | There was a change in swagger in IR4 for senderUniqueReference and transactionID under DIN503. However this wasn’t folded into the Interface Catalogue examples. The examples should have been removed from The DES138 Examples as DIN-780 these still appear in the Interface catalogue |  | Implemented | No |  | Clarification - No change required |  |  | Interim Release 8 | 2024-03-20 | Examples against senderUniqueReference and transactionID will be removed from DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-914 | MF |  | 2024-02-19 | EDW |  | Darshun Chauhan | Software Provider | Update DI-082 (Settlement Period Effective to Date/Time) validation rule on IF-021 | Align DI-082 validation rule to check for periods ending on the hour or half-hour to align with MDS requirements |  | Implemented | No |  | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Update DI-082 (Settlement Period Effective to Date/Time) validation rule on IF-021 to check for periods ending on the hour or half-hour to align with MDS requirements/ build | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-915 | RG | DIN-801, DIN-852 | 2024-02-19 | BJSS |  | Soniya Jakhu | Software Provider | Missing swagger updates to align with DIN-801 - ECS reports REP006 | 1. DIN-801 updates not communicated - Add Supplier R015 block to REP006 2. DI-375 needs to be nullable 3. DI-364 needs to be nullable 4. DIN-852 Updates not communicated to Swagger REP-006 - R003 block |  | Implemented | No |  |  |  |  | Interim Release 7.1 |  | Update Swagger to 1. Add Supplier R015 block to REP006 2. DI-375 needs to be nullable 3. DI-364 needs to be nullable 4. REP-006 - R003 block | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-916 | MH |  | 2024-02-21 | Elexon | 35702 | Mike Ceney | Central Body | IF-36 Obfuscation | In the IF-036 flow it states that DI-800 Service Provider Appointment Scenario is obfuscated for MDS, can you please clarify why this is the case. MDS needs this information to determine if this is for Migration (CoA or CoS lead), or a general CoA, it treats the interface differently based on the scenario |  | Implemented | No |  | Design gap | Avanade, Helix |  | Interim Release 7.1 |  | Removed the obfuscation of DI-800 in Blocks B014 and B015 in IF-36 | Data interface correction | Supporting Docs | Interfaces | DES138 & Avanade change
MHHS-DIN-917 | RS |  | 2024-02-22 | Callisto | 31823 36576 | Seth Chapman | Data Service Provider | Reverse Migration Process - Missing D0148 | In the reverse migration scenario there is a variation to the standard legacy process in that the D0148 groups for the old agent (271 to DC And 274 to MOP) would include the MHHS services rather than a previous "current world" agent. The documents also do not mention that the new supplier will also appoint a DA |  | Closed |  |  | Design gap |  |  |  |  | Migration Design Document (DEL961) updated to include the D0148 for the new DC, DA and MOP. Discussion required on if the old agent/service should be included as Participant believes it could be a bigger change to not include Following review, a CR would be required to make additional amendments to the existing D0148 to include old agents, response provided back to initiator | Process Model correction | Supporting Docs | Supporting document | DEL961
MHHS-DIN-918 | RG |  | 2024-02-22 | SRO Design |  | Rob Golding | SRO Design | DES-138 IF_LIST table incomplete | IF_LIST tab does not include all the MDR interfaces |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Add interfaces IF-061, IF-062, IF-063, IF-064, IF-065 to Interface List in DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-919 | RS | DIN 247, DIN 434 | 2024-02-22 | IMServ | 35161 | Bevis Rotherham | Software Provider | Reverse Migration - IF003 missing supplier fields | The MHHS-DEL961 - Migration Design Document states that IF-003 will be updated to include RevMig Incoming Supplier MPID and RevMig Incoming Supplier Effective From Date fields, however, even in the latest IR7 DES138 document these fields do not exist. There was DIN-247 which specifically referenced these fields and the Business Rules and this was closed as supposedly captured as part of DIN-434, however, DIN-434 doesn't show these fields being implemented, and the latest DES138 doesn’t show these fields against the IF-003. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.1 |  | Added B002 block to DES138 IF-003 to provide the Incoming Supplier DIP ID, MPID and Effective From Date on a Reverse Migration de-appointment. Note, all Suppliers will need to be allocated a DIP ID in advance of migration. Required fields in swagger equire update to align with DES-138 | Data interface and Swagger correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-920 | RS |  | 2024-02-22 | SCS | 36031 | Daniel Tadecicco | Central Body | DI-250 IF-007 Migration Rejection Code | Currently, the IF-007 can only be rejected using Level 4, MPRS other IFs use a reusable function to apply Migration rules with level 5 validation. We would like to use this function for the IF-007, using the current level 4 rejection would require a specific function for the IF-007 which would not be as maintainable and possibly confusing for receiving parties. |  | Implemented |  |  | Design gap | All Participants |  | Interim Release 8.1 |  | Added new validation REG9002 to IF-007 to reject if Reverse Migration is in progress | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-921 | RG | DIN-913 | 2024-02-22 | IMServ |  | Liam Lowey | Software Provider | DES138 - Sender Unique reference example is incorrect | The example sender Unique reference on the DIP_COMMON tab does not contain the full interface id in the string |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | The senderUniqueReference example removed from DIP Common as per DIN 913 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-922 | RG |  | 2024-02-22 | BJSS |  | Sergio Gomes | Software Provider | IF-014 CustomBlock Required list needs updating | Needs to align with properties, should be B900 not B900List |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.1 |  | Required properties should be B900 not B900List only wrong in v7, not v5.4) | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-923 | MF |  | 2024-02-23 | PDA |  | Richard French | Data Service Provider | Clarification on Data Service sending consumption data for periods 47/48 during BST | Clarification around who should send consumption data for settlement periods 47 and 48 in the case of New Connections, Migration and who will receive the IF-013 where no data is provided for HH47 and HH48 during BST |  | Implemented |  |  | Design misaligned |  |  | Interim Release 7.1 |  | In the case where no previous Data Service exists following a Change of Data Service ( eg New Connection, Migration) , in BST the responsibility for providing the initial hour of consuption data for Settlement periods 47 and 48 sits with the newly Appointed Data Service. Note the IF-036 notifies whether there is a previous Data Service via Block B005. The Data Service should estimate these periods in line with the relevant Method Statement. The Incoming Data Service will be notified of default data via the IF-013 if no data is submitted for Settlement Periods 47 and 48. However, the Incoming Data Service is not expected to provide data for these two settlement periods where a previous Data Service exists. Minor amendment to IF-021 validation rule to allow the incoming Data Service to send IF-021 for periods 47 and 48 where no previous Data Service exists | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-924 | RG | DIN-904 | 2024-02-12 | SRO |  | Rob Golding | SRO Design | Missing parameters in webhook callback | The definition in the webhook callback in swagger is missing the definition - $ref: '#/components/parameters/CommonSignatureHeader' - $ref: '#/components/parameters/CommonSignatureDateHeader' - $ref: '#/components/parameters/CommonSHA256Header' - $ref: '#/components/parameters/CommonSignatureCertifcateHeader' |  | Implemented | No |  | Clarification - No change required |  |  | Interim Release 7.1 |  | Update to swagger to include missing parameters; aligns with CoCo | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-925 | RG | DIN-906 | 2024-02-14 | SRO Design |  | Rob Golding | SRO Design | Add MPO Encrypted header parameter to callback | Add a parameter to the callback so that the MTLS cert can be authenticated by the MTLS connection. No impact on MPs, Avanade improving the secuirty handshake on the callback |  | Implemented | No |  | Design gap | Avanade |  | Interim Release 7.1 |  | Add extra parameter the webhook callback. No impact on PPs | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-926 | RG | DIN-907 | 2024-02-14 | SRO Design |  | Grant Sutcliffe | Avanade | Response codes on delete operations | Standardise response message for successful delete operations on API calls -204 needs to have the text 'No Content' . Need to add other response codes in-line with the other APIs |  | Implemented | No |  | Design misaligned |  |  | Interim Release 7.1 |  | Swagger update to include response body on codes where they are expected. Awating details. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-927 | RG | DIN-928 | 2024-02-23 | SRO Design |  | Jon Dennis | Stark | IF-037 mandatory block for [DS¦MS]DeAppUpdate event codes | the B010/B011 blocks are mandatory for the [DS¦MS]DeAppUpdate event codes. |  | Implemented |  |  | Design misaligned |  |  | Interim Release 5.5 |  | Update swagger to include required blocks for IF-037 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-928 | RG | DIN-927 | 2024-02-23 | SRO Design |  | Jon Dennis | Stark | IF-037 mandatory block for [DS¦MS]DeAppUpdate event codes | the B010/B011 blocks are mandatory for the [DS¦MS]DeAppUpdate event codes. |  | Implemented |  |  | Design misaligned |  |  | Interim Release 7.1 |  | Update swagger to include required blocks for IF-037 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-929 | BK |  | 2024-02-23 | UKPN |  | David Yeoman | Network Operator | Change to NFR E2E1009 for DNO & IDNO roles (LDSO, UMSO, Registrations) | The programme has specified several Non-Functional Requirements that market participants must adhere to. Specifically, E2E1009 states: All Services shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes: - up to average hourly volume, mean response time of 6s or less - up to average hourly volume, 90th percentile response time of 12s or less - from average hourly to peak hourly volume, mean response time of 10s or less - from average hourly to peak hourly volume, 90th percentile response time of 16s or less DNOs and iDNO’s intend to use a ‘DIP Adaptor’ to facilitate interfacing to the DIP. The DIP adaptor provides Level 3 validation. Each ‘back office’ system that connects to the DIP Adaptor under each of the 3 DNO and iDNO roles of, Registration Services, UMSO & LDSO is expected to perform Level 4 validation. These DNO and iDNO systems cannot provide the requested Level 4 technical validation responses within 6, 10, 12 or 16 seconds as detailed in E2E1009. | CR040 | Implemented |  |  | Change Request | iDNOs, DNOs |  | Interim Release 8 | 2024-03-20 | The change being proposed is that all DNO and iDNO roles and systems are not required to meet the current specified asynchronous response timeframes of E2E1009 NFR. We request the description for E2E1009 be updated to read: All roles under DNO and iDNOs, namely Registration Services, UMSO & LDSO shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes - 60 minutes or less. This should exclude IF-021 for which there is a separate NFR due to the anticipated volumes. This will ensure alignment with the Operational Choreography " | Technical corrrection | Supporting Docs | Interfaces | E2E002 - Requirements
MHHS-DIN-930 | RG | MHHS-DIN-931 | 2024-02-26 |  |  | Rob Golding | SRO Design | Clarification of response codes that need an associated response body in Swagger | Design need to catch up with implementaton and the 400 response needs a response body for /dip-channel/{id} API |  | Implemented |  |  | Design gap |  |  | Interim Release 5.5 |  | StandardResponse is included for: 201 - StandardResponse includes an array of StandardResponseBodyType 207 - StandardResponse includes an array of StandardResponseBodyType 400 - if the response is generated by APIM. It has a single StandardResponseBodyType contained in the StandardResponse. (APIM does not deal with individual payloads contained in a request). If the response is generated inside the DIP (L1 errors), an array of StandardResponseBodyType will be returned in the StandardResponse - one for each payload in the request. Responses for all other Status Codes do not contain StandardResponse. | Technical corrrection | Supporting Docs | Interfaces | Swagger, possibly E2E
MHHS-DIN-931 | RG | MHHS-DIN-930 | 2024-02-26 | SRO Design |  | Rob Golding | SRO Design | Clarification of response codes that need an associated response body in Swagger | Design need to catch up with implementaton and the 400 response needs a response body for /dip-channel/{id} API |  | Implemented |  |  | Design gap |  |  | Interim Release 7.1 |  | StandardResponse is included for: 201 - StandardResponse includes an array of StandardResponseBodyType 207 - StandardResponse includes an array of StandardResponseBodyType 400 - if the response is generated by APIM. It has a single StandardResponseBodyType contained in the StandardResponse. (APIM does not deal with individual payloads contained in a request). If the response is generated inside the DIP (L1 errors), an array of StandardResponseBodyType will be returned in the StandardResponse - one for each payload in the request. Responses for all other Status Codes do not contain StandardResponse. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-932 | RG |  | 2023-02-27 |  |  | Rob Golding | SRO Design | Replace references to /api.swaggerhub.com/domains/MHHSPROGRAMME with DIP Production URLs | The move to the DIP Production system will require a repointing of the references to the Swagger modules to the production Swagger repository |  | Open - awaiting assessment |  |  | Design misaligned |  |  | Post Go-live Release |  | Replace references to /api.swaggerhub.com/domains/MHHSPROGRAMME with DIP Production URLs, awaiting on DIP | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-933 | RG |  | 2024-02-26 |  |  | Rob Golding | SRO Design | Clarification of response codes that need an associated response body in Swagger | Design need to catch up with implementaton and the 400 response needs a response body for /dip-channel/{id} API |  | Closed | [7 empty] | Duplicate of DIN-930
MHHS-DIN-934 | RS |  | 2024-02-27 | St Clements | 36918 | Daniel Tadecicco | Central Body | IF-001 Migration Change of Supplier (MCS Appointment Scenario) | 003.outgoingSupplierDIPID is defined as Mandatory but for an MHHS Migration the old Supplier may not be MHHS Qualified, so we cannot set this B025.MPAN Energisation Status is defined as Mandatory but we will not have a value at the point we trigger the IF-001, which happens before the SP appointments are confirmed. The MHHS Energisation Status is created when the migration completes (IF-036 issued) B035List.importExportMPANSupplierDIPID is defined as Mandatory but the Supplier of an associated MPAN may not be MHHS Qualified. Further request to widen this DIN to other Forward Migration IFs - these items are also on the IF-002, IF-033 & IF-036 |  | Implemented |  |  | Data |  |  | Interim Release 8 | 2024-03-20 | Serveral solution options were discussed with SCS on how this might be resolved. Agreed solution is that REGS will populate a 'dummy DIP iD' ie. 9999999999 into the DIP ID field where required to populate a DIP ID but where the referenced party is not qualified. (This impacts IF-003, IF-002, IF-001, IF-033, IF-036) Add new valid value of U - Undetermined to DI-033 to allow a value to be populated during Migration. This will be updated with the actual Energisation Status at the stage the IF-036 is issued and the value has been set in Registration Service | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-935 | SB |  | 2023-02-27 |  | 34656 |  |  | correction of errors in DES240 (Transitional Scaling Weights) | when recently reviewing the transitional scaling weights we have noticed some errors in the values listed in NewCCC_Weights and Existing_CCCs tabs for losses. The scaling weight principles on first tab state that all losses should have a quality rating of 0.4, however on the NewCCC_Weight tab there are 19 Loss CCCs which have a Quality Rating (column G) of either 0.2 or 0.6 for losses - these should all be 0.4. This would change the Scaling Weight in column I. Similarly the scaling weights for losses, on the Existing_CCCs tab, for Measurement Classes F and G should 1.4 as these are equivalent to MC A (for losses). |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Update DES240 to amend Scaling weights for losses so all are 0.4 as detailed in ticket 34656 | Technical corrrection | Supporting Docs | Interfaces | DES240
MHHS-DIN-936 | RG |  | 2024-02-29 | Design Team |  | Rob Golding | SRO Design | HTTP response code back off & retry behaviour | Align E2E SA doc with the regime for each response code |  | Closed |  |  | Design misaligned | All Participants |  |  |  | Align E2E SA doc with the regime for each response code | Technical corrrection | Supporting Docs | Supporting document | E2E Architecture Doc
MHHS-DIN-937 | ZH |  | 2024-02-29 |  |  | John Wiggins/Matthew Breen | SRO Design | Align Migration design with wider design changes made for CR028 | The COS Migration tests continue to show EES receiving the IF-001. The EES instance of the IF-001 was removed from the COS process map and the interface catalogue as part of CR028. As such EES will not be able to process the IF-001 and it is inappropriate to include it as part of the baselined test scenarios. |  | Implemented |  |  | Design misaligned |  |  | Interim Release 8 | 2024-03-20 | Updates to be made to relevant Migration artefacts to align with the design changes to the COS process map and DES138 in relevance to EES not receiving IF-001. | Process Model correction | Migration | Process Model correction | BPM001, BPD001
MHHS-DIN-938 | MF |  | 2024-03-01 | PDA |  | Richard French | Data Service Provider | Confirmation of dates to use in the D0388 UMS Inventory | Confirm that the UMSO should populate the effective from date to align with the appointment date. So during BST, for example for a 1st July appointment the D0388 UMS Inventory should state 1 July (even though, where no previous Data Service exists, the UMSDS should calculate periods 47 & 48 of the 30th June UTC Settlement Date ). |  | Implemented |  |  | Clarification - No change required |  |  | Interim Release 8 | 2024-03-20 | METH009 UMSO Method Statement updated accordingly | Method statement correction | Supporting Docs | Method Statement | METH009
MHHS-DIN-939 | RS |  | 2024-03-01 | St Clements | 36920 | Daniel Tadecicco | Central Body | Difference in lapse behavior for subsequent IF-031 Appointments between enduring and migration | There is a difference in the logic for Migration and Enduring when it comes to lapsing Appointments. In Migration, it allows MPRS to lapse an IF-031 Migration immediately without a matching IF-034. For enduring MPRS must wait for the IF-034 before lapsing. We would like Migration to be aligned with enduring for ease of coding. This would require a change to MHHS-Migration-Can-RS-005 to change the line "In this case, an IF-035 would be sent immediately to cancel the Migration. " to "Any earlier appointments should be lapsed." |  | Implemented |  |  | Design ambiguous |  |  | Interim Release 8 |  | Note added to REGS Migration Requirment - MHHS-Migration-Can-RS-005 to confirm functionality | Requirement correction | Migration | Migration Requirements | Migration Requirements Log
MHHS-DIN-940 | MH |  | 2024-03-01 | Helix | 38131 | Rashmi Radhakrishnan | Central Body | M18 - ISD | The M18 example table in EDI021 ISD Entities has values of N/A where the actual values should be blank. |  | Open - awaiting assessment |  |  | Error/Correction | All Participants |  | Post Go-live Release |  | Update the example table to show blank fields where the DIP Role does not have an associated MP Role Code | Other | Supporting Docs | ISD Entities | EDI021
MHHS-DIN-941 | RG | DIN-720 | 2023-10-11 | Utiliteam |  | Mike Fensome | SRO Design | Update to DI-122 Profile Class to min length of 1, max length of 2 | Allow Profile Class (DI-122) to be provided with min length of 1 and max length of 2 in both swagger and DES138 so that, for example, either 1 or 01 are accepted. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.1 |  | Update 7.1 swagger to match 5.4 for DI-122 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-942 | RG |  | 2024-03-05 | St Clements |  | Melissa Brocklehurst | Software Provider | Errors in REP-901 in Swagger | Blocks R901-07 & R901-08 do not align with the defintion in ERI011B s/s. The fields chargeBand, dailyUncorrectedVolumeForChargeBand and totalVolumeChargeForChargeBand need to be removed from R901-07 |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.2 |  | Remove chargeBand, dailyUncorrectedVolumeForChargeBand and totalVolumeChargeForChargeBand fields from R901-07 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-943 | BK |  | 2024-03-05 | Helix |  | Nigel Rees | Central Body | CR034 - Delay to Elexon Level 4 validation response – NFR (1009) | The change being proposed is that Helix does not meet the requirements of E2E1009 NFR. We request the description for E2E1009 be updated to read “All Services shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes - 10minutes or less – excludes IF-021” | CR034 | Implemented |  |  | Change Request |  |  | Interim Release 7.1 |  | Updated Level 4 Processing Times (Asynchronous) requirement as follows; All Services with the exception of Helix (VAS,MDS,LSS,ISD) Services shall provide an asynchronous response (Level 4 validation) to a message within the following timeframes - up to average hourly volume, mean response time of 6s or less - up to average hourly volume, 90th percentile response time of 12s or less - from average hourly to peak hourly volume, mean response time of 10s or less - from average hourly to peak hourly volume, 90th percentile response time of 16s or less Helix Services (VAS,MDS,LSS,ISD) shall provide an Asynchronous response time of 10 minutes or less. | Requirement correction | Supporting Docs | Requirements | MHHS-E2E002 Requirements
MHHS-DIN-944 | SB |  | 2024-03-08 | Design Team |  | Paul Pettitt | SI Design | Service Provider appointment Process | The Operational choreography does not align with the Design intent of flexibility with Service Provider Appointment. OP_120 requires clarification |  | Closed |  |  | Error/Correction |  |  |  |  | Closed - upholding the objection raised by ReCCo against this DIN
MHHS-DIN-945 | SC |  | 2024-03-13 | RECCo |  | Sarah Jones | Central Body | CR46 - Change of Energy Direction | Remove reference to 'one-time only' change and add guidance that Change of ED will not change hisotric consumption in MDS/Settlements - any changes to hisotric consumption for that MPAN should be via Consumption Ammendment or Trading Dispute | CR046 | Implemented |  |  | Change Request | All Participants |  | Interim Release 8.1 |  | "One Time Change" reference removed from BP010B and BPD010B for "Change of Energy Direction" process, Registration Requirements (BRS003), Supplier Overview (BRS004) and LDSO Overview (BRS005). New note added to BP010B to highlight that any historic settlement data will not be amended, this would need to be via Consumption Amendment or Dispute process where required. | Process Model correction | Registration | Business Process Models/ Requirements | BRS003, BRS004, BRS005, BP010 and BP010B
MHHS-DIN-946 | RS |  | 2024-03-13 | St Clements | 39364 41047 | Daniel Tadecicco | Central Body | Use of LP006 - Migration Aborted, Pending Registration Received | MHHS DEL974 has requirement MHHS-Migration-COA(MS)-RS-002 states two event codes MGR_Cancelled_MS and MGR_Cancelled_DS should be created, however this needs to be amended to confirm the use of LP006 |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Update to MHHS-Migration-CoA(MS)-RS-002/MHHS-Migration-CoA(DS)-RS-002 in MHHS-DEL974 and Migration Design Document section 13.2.3 | Technical corrrection | Migration | Supporting document | MHHS-DEL974 Migration Design Document
MHHS-DIN-947 | SC |  | 2024-03-13 | DIP |  | Sean Cooper | Central Body | Changes to Swagger to support Implementation of JSON Error Checking End Points. | Swagger to be updated to include facility for new JSON Message Error Checking End Points and response message. |  | Implemented | [5 empty] | Interim Release 7.2 |  | Swagger to be updated to include facility for new JSON Message Error Checking End Points and response message. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-948 | SC |  | 2024-03-14 | St Clements |  | Sean Cooper | SRO Design | Error Code Description Text Updates | Update Error code Text to align with confirmed text provided by SCS |  | Implemented |  |  | Design gap |  |  | Interim Release 8 | 2024-03-20 | Update Error code Text to align with confirmed text provided by SCS | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-949 | RS | DIN-1021 | 2024-03-15 | St Clements | 39365 | Daniel Tadecicco | Central Body | MHHS-Migration-CoA(MS)-RS-009 Alignment with IR7 | The IF-031 REG code in the Migration Requirements log for MHHS-Migration-CoA(MS)-RS-009 does not align with IR7 IR7 IF DI-800 = SEG or CSP, COS, USP and MPAN is not migrated (ie operating in old regime) REG9008 - MHHS Scenario Codes cannot be used for UnMigrated MPAN |  | Implemented |  |  | Design misaligned |  |  | Interim Release 8 | 2024-03-20 | Update Migration requirements doc to align with DES138 error code (REG9009) and updated Migration doc where relevant to align with DES138 error code (REG9009). | Technical corrrection | Migration | Supporting document | Migration Requirements Log Migration Design Document
MHHS-DIN-950 | SC |  | 2024-03-18 |  |  | Sean Cooper | SRO Design Team | CR44 - IF-051 Refresh Message | CR044 - Please refer to the change request documentation for details | CR044 | Closed |  |  | Change Request |  |  |  |  | ~ Swagger changes to include new IF-051 ~ Secondary routing treatment of If-051 [DONE] ~ Add IF-051 data strcutre to DES138 [DONE] | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-951 | SC |  | 2024-03-18 |  |  | Sean Cooper | SRO Design Team | CR45 - SSD Fix Tool | CR045 - Please refer to the change request documentation for details | CR045 | Closed |  |  | Change Request |  |  |  |  | ~ Swagger updates to include New De-App Reason Code ~ Swagger New IF-001 Event Codes ~ Add IF-001 Event Codes to DES138 [DONE] ~ Changes to secondary Routing to Support [DONE] ~ Possible SSD Fix Business Process Diagram | Data interface correction | Supporting Docs | Interfaces | DES138 Swagger Potential - BPXXX
MHHS-DIN-952 | RS |  | 2024-03-18 | Datamere | 41267 | Paul O'Neill | Software Provider | Anomolies in DES138 | DI-991 on 02_DIP_Common worksheet states the values can be TBC (eg PROD, PREPROD, UAT, SIT, DEV). Postman states the following: "S1.environmentTag must be one of 'PROD,PREPROD,SIT,UIT,DEV'." Q2 – DI-840 on 02_IF-031 worksheet states the data item is named CSS Registration ID. Postman states the following: property 'CSSRegistrationID' is unsupported for 'B013' block", B013.CSSRegistrationRequestID field is required. |  | Initial Assessment/Updating |  |  | Design misaligned | All Participants |  | Post Go-live Release |  | Solution yet to be defined | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-953 | SC |  | 2024-03-18 |  |  | Sean Cooper | SRO Design | New DTN Flows for Existing Retained Settlement D-Flows | Update EDI001 Settlement Reporting Spec to reference New D-Flow References assigned to retained D-Flows |  | Closed |  |  | Design misaligned |  |  |  |  | Update EDI001 Settlement Reporting Spec to reference New D-Flow References assigned to retained D-Flows
MHHS-DIN-954 | RG |  | 2024-03-18 | Avande |  | Piotr Penar | Avanade | Add validation endpoints into Swagger | Add validation endpoints into Swagger |  | Closed | [7 empty] | DUPE 954
MHHS-DIN-955 | MH |  | 2024-03-21 |  |  | Matt Hall | SI Design | CR043 - MPAN/ABMU Mapping | DIN to cover the changes required to Design folowing approval of CR043 | CR043 | Implemented |  |  | Change Request | Suppliers, MDS |  | Interim Release 8 | 2024-03-20 | New requirements to be added to MDS and Suppliers' BRS documents to cover CR043 | Requirement correction | Supporting Docs | Requirement correction | BRS004-Supplier Overview BRS008 MDS Requirements
MHHS-DIN-956 | ZH |  | 2024-03-21 | MHHS |  | Zakir Hussain | SI Design | Rebranding of D-Flows - DES196 & ERI011b | DIN to align changes made in the DES196 document (latest D-flows added to the doc) to the relevant areas within design |  | Implemented | No |  | Design misaligned | All Participants |  | Interim Release 8.1 |  | Update ERI011b and DES196 to reflect use of ECS DTN reports and New D-Flow References assigned to retained D-Flows | Reporting correction | Supporting Docs | Various documents | ECS Report External ERI011b DES196
MHHS-DIN-957 | MF | Test defect 31009 DIN-963 DIN-964 | 2024-03-21 | SI Design |  | Mike Fensome | SI Design | Update swagger in IF-005 | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. |  | Implemented | Yes | 31009 | Error/Correction |  |  | Interim Release 5.5 |  | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-958 | BK | MHHS-DIN-937 | 2024-03-21 | SRO Design |  | John Wiggins/Matthew Breen | SRO Design | Align Migration design with wider design changes made for CR028 | The COS Migration tests continue to show EES receiving the IF-001. The EES instance of the IF-001 was removed from the COS process map and the interface catalogue as part of CR028. As such EES will not be able to process the IF-001 and it is inappropriate to include it as part of the baselined test scenarios. |  | Closed |  |  | Design misaligned |  |  |  |  | Updates to be made to relevant Migration artefacts to align with the design changes to the COS process map and DES138 in relevance to EES not receiving IF-001. | Process Model correction | Migration | Process Model correction | BPM001, BPD001, Migration document
MHHS-DIN-959 | BK | MHHS-DIN-942 | 2024-03-21 | St Clements |  | Melissa Brocklehurst | Software Provider | Errors in REP-901 in Swagger | Blocks R901-07 & R901-08 do not align with the defintion in ERI011B s/s. The fields chargeBand, dailyUncorrectedVolumeForChargeBand and totalVolumeChargeForChargeBand need to be removed from R901-07 |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Remove chargeBand, dailyUncorrectedVolumeForChargeBand and totalVolumeChargeForChargeBand fields from R901-07 | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-960 | BK | MHHS-DIN-947 | 2024-03-21 | DIP |  | Sean Cooper | Central Body | Changes to Swagger to support Implementation of JSON Error Checking End Points. | Swagger to be updated to include facility for new JSON Message Error Checking End Points and response message. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Swagger updated to include facility for new JSON Message Error Checking End Points and response message | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-961 | RG |  | 2024-03-22 | SRO Design |  | Rob Golding | SI Design | Update Environment list to reflect those being delivered by Avanade | Existing list: - PROD - PREPROD - SIT - UIT - DEV Update to add SITB |  | Implemented |  |  | Error/Correction |  |  | Interim Release 5.5 |  | Only SITB currently added | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-962 | RG | DIN-1011 | 2024-03-25 | Helix | 42284 | Nigel Rees | Central Body | Make MPAN optional on replay/requeue | Removing MPAN from the mandatory list of parameters for DIP replay/requeue |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Removing MPAN from the mandatory list of parameters for DIP replay/requeue and introduce mandatory/null design pattern on input parameters | Technical corrrection | Supporting Docs | Interfaces | Swagger, E2E SA
MHHS-DIN-963 | MF | Test defect 31009 DIN-964 DIN-957 | 2024-03-21 | SI Design |  | Mike Fensome | SI Design | Update swagger in IF-005 | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. |  | Implemented | Yes | 31009 | Error/Correction |  |  | Interim Release 7.2 |  | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-964 | MF | Test defect 31009 DIN-963 DIN-957 | 2024-03-21 | SI Design |  | Mike Fensome | SI Design | Update swagger in IF-005 | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. |  | Implemented | Yes | 31009 | Error/Correction |  |  | Interim Release 8 | 2024-03-20 | Update swagger for events codes [MeterUpdate] and [MeterHistoryUpdate] so that B906a block is used rather than existing B906 (ie use 906a block rather than 906) . This will ensure the B034 block is optional for these events. Note, no change is required to IF-006 as this already uses 906a. | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-965 | RG |  | 2024-03-22 | SRO Design |  | Rob Golding | SI Design | Update Environment list to include SITB | Existing list: - PROD - PREPROD - SIT - UIT - DEV Update to add SITB |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.2 |  | Only SITB currently added | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-966 | SC | Test Defect 31336 DIN-1019 | 2024-03-27 | SRO Design |  | Sean Cooper | SRO Design | Revision to the PUB-004 Secondary routing logic. | SIT DEFECT - 31336 Currently distribution logic states delivery of PUB-004 to SUPC and XMSC. This results in the send of the message (IF-004) being unnecessrily copied in on the PUB-004. Secondary logic should reference sending party and issue to XMSC where sent by SUPC and SUPC where message sent by XMSC. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.3 |  | SIT DEFECT - 31336 Currently distribution logic states delivery of PUB-004 to SUPC and XMSC. This results in the send of the message (IF-004) being unnecessrily copied in on the PUB-004. Secondary logic should reference sending party and issue to XMSC where sent by SUPC and SUPC where message sent by XMSC. DES138 - IF-004 routing table updated accordingly | Technical corrrection | Supporting Docs | Interfaces | Secondary Routing DES138
MHHS-DIN-967 | MF | Test Defect 31338 | 2024-03-27 | Design Team |  | Mike Fensome | SRO Designn | Update BP010A to show that MPL address updates from UMSO are via "Agreed Communication Method" | Update BP010A to show that MPL address updates from the UMSO are notified via "Agreed Communication Method" |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated BP010A and BPD010A to show that MPL address updates from the UMSO are notified via "Agreed Communication Method". This aligns with BR-MS-064 and reflects that the UMSO cannot currently use D0381 flow | Process Model correction | MPAN Ownership | Business Process Models | BP010A BPD010A
MHHS-DIN-968 | SC |  | 2024-03-27 | Avanade |  | Sean Cooper | SRO Design | MDR Secondary Routing | Following text added to interfaces where MDR is referenced as a Secondary Recipient .... .... "Reference to MDR above assumes that MDR is Qualified for DIP Operations & is opt'ed in for SDS-MDR message exchange" |  | Implemented |  |  | Design ambiguous |  |  | Interim Release 8 | 2024-03-20 | Following text added to appropriate interfaces.... .... "Reference to MDR above assumes that MDR is Qualified for DIP Operations & is opt'ed in for SDS-MDR message exchange" | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-969 | SC |  | 2024-03-28 | SCS |  | Sean Cooper | SRO Design | Implementation of REGS Calendar based RF Cut of Date Checking | SCS have confirmed that RF Cut Off Date validation based on the ISD Settlement Calendar cannot be implemented until post go-live. SCS/Programme assessment is that given the other validation rule(s) in place principly the check around Migration Date that this is not an issue. This DIN is to formally record this issue - DIN will be differed. |  | Open - awaiting assessment |  |  | Design gap |  |  | Post Go-live Release |  | RF restrictions for MS, DS, MDR, Energisation Status EFDs. Differred DIN captured for reference |  |  |  | ISD
MHHS-DIN-970 | SC |  | 2024-03-28 | SCS |  | Sean Cooper | SRO Deign | Bypassing SSD Check where no SP's are appointed even beyond RF Cut Off Date | Logic check required following implementation of DIN969 to allow for Retrospective Appointment of SP's prior to RF Cut off Date - where Supplier has failed to do this prior to RF cut off date for the SP Appointment Start Date |  | Open - awaiting assessment |  |  | Design gap |  |  | Post Go-live Release |  | Logic variation to allow Pre-RF Cut Off Retro Appointments - Differed DIN Captured for Reference |  |  |  | ISD
MHHS-DIN-971 | SC |  | 2024-03-28 |  |  | Sean Cooper | SRO Design | Clarifcation of MPAN Linkage Request Rejection Codes | Programme has been waiting for LDSO confirmation of these codes however this has not been forthcoming todate. In order to finalise the design for other participants the following codes will constitute the go-live design. IE000 - Proposed Linkage Change Accepted IE001 - Proposed Linkage Change Rejected IE099 - Please contact LDSO directly for further advice |  | Implemented |  |  | Design gap |  |  | Interim Release 8 | 2024-03-20 | Programme has been waiting for LDSO confirmation of these codes however this has not been forthcoming todate. In order to finalise the design for other participants the following codes will constitue the go-live design. IE000 - Proposed Linkage Change Accepted IE001 - Proposed Linkage Change Rejected IE099 - Please contact LDSO directly for further advice | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-972 | SC |  | 2024-04-02 | SCS |  | Sean Cooper | SRO Design | Migration Reqs: Removal of Reference to IF-040 (Annual Consumption) from the REGS Migration Requirments | Missed CR39 Update - Remove of Reference to IF-040 (Annual Consumption) from the REGS Migration Requirments |  | Implemented |  |  | Design misaligned |  |  | Interim Release 8 | 2024-03-20 | Missed CR39 Update - Remove of Reference to IF-040 (Annual Consumption) from the REGS Migration Requirments | Technical corrrection | Migration | Supporting document | Migration Requirements Log
MHHS-DIN-973 | SC | 1038 | 2024-04-02 | SCS |  | Sean Cooper | SRO Design | Migration Reqs: Correct REGS treatment of D0312 where a Forward MIgration is in progress. | Requirment updated to refeclt that IF-035 with Lapsed Reason Code of LP001 (MPAN Disconnected/deRegistered) will be issued for any Pending Service Provider Appointments on receipt of D0312 |  | Implemented |  |  | Design ambiguous |  |  | Interim Release 8 | 2024-03-20 | Note added to RESG Migration Requirement MHHS-Migration-Can-RS-006 - to confirm process | Technical corrrection | Migration | Supporting document | Migration Requirements Log
MHHS-DIN-974 | RG | DIN-1012 | 2024-04-02 | EDW Technology |  | Mark Kenney | SRO Design | Align webhookresponse on /statusmessage to /dip-channel | Status messages reponses from the PP systems and the DIP need to align |  | Implemented |  |  | Design misaligned | All Participants |  | Interim Release 8.1 |  | Status messages responses from the PP systems and the DIP need to align, also standard message webhook response should return a standard response body on a 400 | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-975 | SC |  | 2024-04-02 | SCS |  | Sean Cooper | SRO Design | Migration Reqs: Confirm REGS treatment of related MPANs in Reverse Migration Scenario | Process is not "automatic" with the REGS per se. CSS will issue a switch request for each MPAN, REGS will process each switch request -end result is the same |  | Implemented |  |  | Design ambiguous |  |  | Interim Release 8 | 2024-03-20 | Note added to RESG Migration Requirement MHHS-RMigration-CoS-RS-002 to confirm process is not automatic - same end result is achived through CSS functionality | Technical corrrection | Migration | Supporting document | Migration Requirements Log
MHHS-DIN-976 | RG |  | 2024-04-05 | ESG | 44664 | Patricia Parker | SRO Design | Duplicate enumeration values for the DI-596 Charge Type enumeration | Duplicate enumeration values for the DI-596 Charge Type enumeration, CAPAC appears twice |  | Closed |  |  | Error/Correction |  |  |  |  | DI-596 Charge Type enumeration, CAPAC appears twice - Need to remove duplicate charge type | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-977 | RG |  | 2024-04-05 | Avanade |  | Rob Golding | SRO Design | Update PROD to PRD in Environment Tag List | Confirmation that Avanade have labeled the Production DIP environment PRD. The DT-013-EnvironmentTag will require updating: Change PROD to PRD and removed PREPROD. Add SITB |  | Implemented |  |  | Design misaligned | All Participants |  | Interim Release 8.1 |  | The DT-013-EnvironmentTag will require updating: Change PROD to PRD and removed PREPROD. | Technical corrrection | Supporting Docs | Interfaces | Swagger, E2E SA
MHHS-DIN-978 | RS |  | 2024-04-08 | ESG | 41894 | Patricia Parker | Software Provider | REP-003 and REP-006 have JSON label missing in ERI011b - ECS Reports | REP-003 and REP-006 should have Distribution Pattern A and Report Format JSON in cell H7 as per the other MHHS-REP-XX (eg MHHS-REP-07) |  | Initial Assessment/Updating |  |  | Error/Correction | All Participants |  | Post Go-live Release |  | Update REP-003 and REP-006 in ERI011b to match include outlined box as per MHHS-REP-07 | Reporting correction | Supporting Docs | ECS Reports | ERI011B
MHHS-DIN-979 | RS |  | 2024-04-08 | ESG | 41955 | Patricia Parker | Software Provider | DI-819 (De-appointment reason code) in IF-003 should not contain CSERV. Only CSUPP should be used | DES138, IF-003 has DI-819 has the option for CSERV Change of Service Provider in the Population notes column. This should be greyed out leaving just CSUPP change of supplier |  | Closed |  |  | Error/Correction | All Participants |  |  |  | Update IF-003 in DES138 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-980 | MH |  | 2024-04-10 | SCS | 44726 | Madison Layton | Software Provider | ISD versioning IR8 | IR8 version of ISD has not included the IR7.1 changes. This needs to be resolved by adding the changes back in. This is only DIN-899 |  | Implemented |  |  | Error/Correction | Helix, ISD users |  | Interim Release 8.1 |  | Add DIN-899 changes back in to the latest version of IR8. Updates required were covered by DIN-1033 and changing M15 to include N as No Consent | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-981 | RS |  | 2024-04-11 | Siemens | 41452 | David Baxendale | Data Service Provider | Incorrect Load Shape Off Peak Period | Most of the off-peak periods cover 14 UTC periods (7 Hours) – either 00:00 to 0700 OR 00:30 to 7:30 There is 1 anomaly in METH001 GSP _C Profile Class 4 has 15 UTC periods – 00:00 to 07:30 |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Method statement will need to be corrected to reflect 00:00 - 07:00 also remove minus sign after the 00:30 _K Will also need to check the load shaping method statement as well (Also incorrect in LSS METH005) | Method statement correction | Supporting Docs | Method Statement | METH001 METH005
MHHS-DIN-982 | ZH | DIN-575/1013 | 2024-04-11 | SCS |  | Madison Layton | Software Provider | CR039 implementation | DES138 - IF040 requires removal of REGS in "To Parties" field | CR039 | Implemented |  |  | Change Request | REGS |  | Interim Release 8.1 |  | Update IF040 in DES138, removed "Registration Service (REGS)" from "To Parties" field | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-983 | RS |  | 2024-04-11 | MHHS | 36071 | Matt McKeon | Central Body | LLFC Id mandated in retained DTC flow | The Line Loss Factor Class Id is being replaced by the DUoS Tariff Id. The LLFC Id is present in various DTC flows, almost all of which are redundant post MHHS. LLFC Id is an optional field in the D0311 which, according to DES196, is retained post MHHS with the MHHS Change “New rules to clarify that Profile Class and Meter Timeswitch Class [code] should be null if no value exists for MHHS MPANs, LLFC should be populated with the DUoS Tariff Id for MHHS MPANs and EACs should only be provided for non-MHHS MPANs. ”. LLFC Id is a mandatory field in the D0387 which, according to DES196, is retained post MHHS with no changes. |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Replicating the rule in the D0311 in the D0387 seems appropriate. Will add a note to the D0387 and amend DES196. Propose to do this once SIT Cycle 2 has completed, as adding it now would impact DTN flow test scope. | Data interface correction | Supporting Docs | DFlow | DES196
MHHS-DIN-984 | RS | DIN-917 | 2024-04-12 | ESG | 42711 | Patricia Parker | Software Provider | D0148 use within Reverse Migration | DEL961 Migration Document detail does not contain any detail of the use of the D0148 when completing a Reverse Migration as assumed to BAU. Need to reference the use of the New connection process for D0148 as per section 9 of Annex c |  | Implemented |  |  | Design ambiguous | All Participants |  | Interim Release 8.1 |  | Add reference to D0148 new connection process (section 9 annex C) to DEL961 (Section 13.1) | Design Ambiguous | Supporting Docs | Migration Design | DEL961
MHHS-DIN-985 | RS | DIN-837 | 2024-04-12 | ESG | 42711 | Patricia Parker | Software Provider | Incorrect meter reading code in section 6.1.3 of DEL961 Migration Design | Secftion 6.1.3 of DEL961 still states Meter Reading Reason Code = 28 (Forward Migration CoA) Instead of Reading Type = U. This should match previously agreed updates of U - Forward Migration CoA V - Forward Migration CoS X - Supplier Agreed Switch Read Y - Reverse Migration CoS As per MHHS impacts to Data Transfer Network (DTN) Flows |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Section 6.1.3 of DEL961 to be updated with U - Forward Migration CoA V - Forward Migration CoS X - Supplier Agreed Switch Read Y - Reverse Migration CoS Remainder of ducument sections to be checked for same disparity | Design Ambiguous | Supporting Docs | Migration Design | DEL961
MHHS-DIN-986 | RS |  | 2024-04-12 | MHHS | 45969 | Test team | Central Body | Incorrect step assigned to migration requirement | DEL974 requirements MHHS-Migration-CoA(MS)-RS-005 and MHHS-Migration-CoA(DS)-RS-005 refer to step 255 of BPM002. No step 255 exists on BPM002. Requirement to be amended to step 710 |  | Initial Assessment/Updating |  |  | Error/Correction | All Participants |  | Post Go-live Release |  | Amend requirements MHHS-Migration-CoA(MS)-RS-005 and MHHS-Migration-CoA(DS)-RS-005 to step 710 in DEL947 (Registration Tab, row 19 and 39) | Requirement correction | Migration | Migration Requirements | DEL974
MHHS-DIN-987 | ZH | DIN-676 | 2024-04-15 | SCS |  | Madison Layton | Software Provider | Missing text in NFRs - CR-018 implementation issues | E2E002 was updated as per IR8 however it is missing text that specifies details around when they are applicable |  | Closed |  |  | Error/Correction |  |  |  |  | Duplicate of 993 | Requirement correction | Supporting Docs | Requirements | MHHS-E2E002 Requirements
MHHS-DIN-988 | ZH |  | 2024-04-15 | SCS |  | Daniel Tadecicco | Software Provider | Migration design alignment | DES138 requires some updates to align with the migration design documentation |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated IF-003 in DES138 to remove MSDeAppUdateRM & DSDeAppUpdateRM events and removed the accompanying interface note as these events are not used in the case of Reverse Migration Design. Opt In/Out matrix updated accordingly. Swagger updated. | Data interface correction | Supporting Docs | Interfaces | DES138 & Swagger
MHHS-DIN-989 | RG |  | 2024-04-15 | Stark | 45757 | Jon Dennis | Software Provider | DI-596-Charge-Type - CAPAC duplicated in Enum | DI-596-Charge-Type - CAPAC duplicated in Enum -one of the entries needs to be removed |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | remove second CAPAC from enumerated list | Data interface correction | Technical Artefact | Interfaces | Swagger
MHHS-DIN-990 | MF | DI-136 | 2024-04-17 | SCS |  | Madison Layton | Software Provider | Limit effective from updates to RF for appointments and energisation status changes | Update validation rules in IF-031, IF-034 and IF-007 to not allow updates to appintment effective from dates and energisation status effective from dates beyond RF |  | Implemented |  |  | Error/Correction | Suppliers, REGS |  | Interim Release 8.1 |  | Update validation rules in IF-031, IF-034 and IF-007 to not allow updates to appintment effective from dates and energisation status effective from dates beyond RF. Added note to REGS Notes to confirm that derived Market Segment Effective from Date cannot be beyond RF. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-991 | MF | DIN-939 | 2024-04-17 | SCS |  | Madison Layton | Software Provider | Confirm migration lapse behavior aligns with BAU operation | Update note on MHHS-MIGRATION-CAN-RS-005 to confirm that lapse notification is only issued after receipt of IF-034 |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated note on MHHS-MIGRATION-CAN-RS-005 to confirm that lapse notification is only issued after receipt of IF-034 | Requirement correction | Migration | Migration Requirements | DEL974
MHHS-DIN-992 | RG | DIN-1014 | 2024-04-17 | Design Team |  | Rob Golding | SRO Design | IF-016-ActivePowerRejected required incorrect | IF-016-ActivePowerRejected required field B900List should be B900 |  | Implemented |  |  | Error/Correction | Advanced Data Service |  | Interim Release 8.1 |  | Update: IF-016-ActivePowerRejected required field B900List to B900 | Data interface correction | Technical Artefact | Interfaces | Swagger
MHHS-DIN-993 | MF | DIN-929 | 2024-04-17 | SCS |  | Daniel Tadecicco | Software Provider | Confirmation of LDSO response times | Update E2E1009 in line with CR040 and Operational Choreography to confirm repsonse times specified are within normal operating hours | CR040 | Implemented |  |  | Change Request | All Participants |  | Interim Release 8.1 |  | Updated E2E1009 in line with CR040 and Operational Choreography to confirm repsonse times specified are within normal operating hours | Technical corrrection | Supporting Docs | Interfaces | E2E002 - Non-Functional Requirements
MHHS-DIN-994 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Treatment of mixed meter sites | Update registration notes to confirm treatment of mixed meter sites |  | Initial Assessment/Updating |  |  | Design ambiguous | REGS |  | Post Go-live Release |  | Update Reg Notes in DES138 to confirm that: • If a mix of Smart and Traditional meters then consider the Meter Group as Smart • If any Advanced meter is fitted then this should be considered as in the Advanced Segment so Meter Group as Advanced. Update REG1042 and REG1043 validation in IF-025 to clarify how mixed meters are validated | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-995 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Correlation ID removed from IF-037 AppUpdate events | Remove Correlation ID from AppUpdate events on IF-037 |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Removed Correlation ID from AppUpdate events on IF-037 | Data interface correction | Supporting Docs | Interfaces | DES138 (No swagger change reqd)
MHHS-DIN-996 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Update description of DI-028 (Reconnection Effective from Date) | Update description of DI-028 to reflect that this is when the Metering Point is reconnected in Registration Service |  | Initial Assessment/Updating |  |  | Design ambiguous | All Participants |  | Post Go-live Release |  | Update description of DI-028 to reflect that this is when the Metering Point is reconnected in Registration Service | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-997 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | PUB-007 validation to allow de-energisation on a Disconnected MPAN | Validation should be changed to allow a PUB-007 to De-energise a Disconnected MPAN (De-energise only, energisation would still not be permitted on disconnected MPAN) |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | New Validation to allow a PUB-007 to De-energise a Disconnected MPAN (De-energise only, energisation would still not be permitted on disconnected MPAN) with error code of REG1001 | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-998 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Clarification on sending error message on IF-034 where incorrect Service Provider responds | Add note to IF-034 validation rules to confirm that REGS will respond with RCP1063 if the incorrect Service Provider responds |  | Initial Assessment/Updating |  |  | Error/Correction | All Participants |  | Post Go-live Release |  | Added note to IF-034 validation rules to confirm that REGS will respond with RCP1063 if the incorrect Service Provider responds | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-999 | MF | DIN-788/1015 | 2024-04-18 | UKPN |  | Neil Madley | Network Operator | Update routing for [MPANReconnection] and add event to Opt/In Out Matrix | On IF-009 add LDSO as secondary routed. Add [MPANReconnection] to the Opt In/ Opt Out Matrix so that LDSO's can opt out of receiving this event. |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.3 |  | On IF-009 added LDSO, SUPC as secondary routed. Added [MPANReconnection] to the Opt In/ Opt Out Matrix so that LDSO's can opt out of receiving this event. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1000 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Update to error message REG1032 to refer to Local Time | Update REG1032 validation on IF-031 in DES-138 to refer to Local Time |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated REG1032 error message on IF-031 in DES-138 to refer to Local Time, where previously referenced UTC. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1001 | MF |  | 2024-04-18 | SCS |  | Madison Layton | Software Provider | Remove REGS requirement MHHS-BR-RS-014.1 | Supplier Nominated DPI is not provided on Metering Service Appointments, so this Requirement is not needed. |  | Initial Assessment/Updating |  |  | Error/Correction | REGS |  | Post Go-live Release |  | Removed requirement MHHS-BR-RS-014.1 from BRS-003 to provide Supplier Nominated DPI for Metering Service Appointments. Requirement retained for Data Service Appointments. | Requirement correction | MPAN Ownership | Requirement correction | BRS003 - Registration Service requirements
MHHS-DIN-1002 | MH |  | 2024-04-19 | Helix |  | Rashmi Radhakrishnan | Central Body | ISD M11 and M12 | As per the UMSUG meeting that we attended, For M12, its been agreed that we need to incorporate OFF event to have “NEVER” where there is no OFF event. |  | Implemented |  |  | Error/Correction | UMSDS |  | Interim Release 8.1 |  | Added a new permissable value of "NEVER" to the OFF Event data field in ISD Entity M12 | Requirement correction | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-1003 | RS |  | 2024-04-19 | National Grid | 43643 | Rachael Prosser | Network Operator | E2E Architecture Document to be updated to include Reference to LDSO and IF-20 | E2E Architecture Document does not include latest updates made to IF-20 for LDSO, review and update required |  | Initial Assessment/Updating |  |  | Error/Correction | LDSOs |  | Post Go-live Release |  | Add line advising for the latest representation refer to DES138. RG to to complete review of document | Other | Supporting Docs | Supporting Docs | E2E001
MHHS-DIN-1004 | RS |  | 2024-04-19 | CGI | 47845 | Dave Webster | Software Provider | DES138 OptOut Matrix for IF-003 Supplier | The 04_IF_OptOut_Matrix sheet of DES138 v5.8.1 shows that IF-003 is not received by Supplier (“N/A”), but for all Event Codes the IF-003 message is Primary Routed to Supplier |  | Implemented |  |  | Error/Correction | Suppliers |  | Interim Release 8.1 |  | Changed IF-003 for Supplier to No from N/a in DES138 IF Opt out Matrix tab. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1005 | MH |  | 2024-04-19 | Helix | 46469 | Matt Hall | SI Design | METH007 Section D clean up | Currently SEction D in the METH007 doesn't clearly distinguish between REP002/2a and 2b. This is causing some confusion and should be rectified |  | Initial Assessment/Updating |  |  | Design ambiguous | All Participants |  | Post Go-live Release |  | Tidy up of Section D in MTH007 to clarify which reports are included, and to clarify which of the REP02 variants require non-W connections include (if any) | Method statement correction | Supporting Docs | Method Statement | METH007
MHHS-DIN-1006 | MH | DIN-087 | 2024-04-19 | RECCo | 46872 | Sarah Jones | Central Body | Outstanding Design Query (DIN087) | As part of the final code drafting checks, we are confirming that all consultation comments have been addressed. We have identified a comment from an early drafting tranche (CD-0558) which queries the requirements to issue a de-energisation notice for meter exchanges. At the time, we were expecting a note to be added to BP008 to make it clear that that ‘DeEn did not need to be notified if meter works completed within same day (ie same rules as today)’ as stated in the DIN log against DIN087. However, BP008 doesn’t appear to have this note included which means we have not been able to close out the code drafting query. |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Add a box to BPM008 to to reflect the proposed solution in DIN-087 | Process Model correction | Supporting Docs | Business Process Diagram | BP008
MHHS-DIN-1007 | RG | DIN-1018 | 2024-04-22 | Avanade |  | Rob Golding | SRO Design | Change request body on Validation Endpoints | Avanade have reviewed the 1.7.1. endpoints and are requesting a chnage so that they are more flexible and align to the submission API |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.3 |  | Avanade have reviewed the 1.7.1. endpoints and are requesting a change so that they are more flexible and align to the submission API | Technical corrrection | Swagger |  | Swagger
MHHS-DIN-1008 | SB |  | 2024-04-23 | British Gas |  | Neil Strange | Supplier | BP-03C Transfer of Reads Clarification | We’ve noticed that on PB03C the IF/PUB016 interface is TBC – looking at DES138 I believe this is confirmed – am I correct? This is in the advanced meters section following successful appointment. |  | Initial Assessment/Updating |  |  | Design ambiguous | Advanced Data Service |  | Post Go-live Release |  | Updating IF-016, to include DES138 information | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-1009 | SB |  | 2024-04-23 | MHHS |  | Shaun Magee | Central Body | METH002 Issue with LTV Method statement | Incorrect Method referenced in section 3.13 should be method 11 rather than 12 |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update: Incorrect Method referenced in section 3.13 should be method 11 rather than 12 | Method statement correction | Supporting Docs | Method Statement | METH002
MHHS-DIN-1010 | TR | DIN-762 | 2024-04-23 | RECCo | 46312 | Jonny Moore | Central Body | IF-003 - EES as Recipient | EES not included within the 'To Parties' in DES138 |  | Initial Assessment/Updating |  |  | Design misaligned | EES |  | Post Go-live Release |  | DES138 updated to include EES in the 'To Parties' field | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1011 | RG | DIN-962 | 2024-03-25 | Helix | 42284 | Nigel Rees | Central Body | Make MPAN optional on replay/requeue | Removing MPAN from the mandatory list of parameters for DIP replay/requeue |  | Closed |  |  | Error/Correction |  |  |  |  | Only implement in IR8 | Technical corrrection | Supporting Docs | Interfaces | Swagger, E2E SA
MHHS-DIN-1012 | RG | DIN-974 | 2024-04-02 | EDW Technology |  | Mark Kenney | SRO Design | Align webhookresponse on /statusmessage to /dip-channel | Status messages reponses from the PP systems and the DIP need to align |  | Implemented |  |  | Design misaligned |  |  | Interim Release 7.3 |  | Status messages reponses from the PP systems and the DIP need to align | Technical corrrection | Supporting Docs | Interfaces | Swagger
MHHS-DIN-1013 | ZH | DIN-575/982 | 2024-04-11 | SCS |  | Madison Layton | Software Provider | CR039 implementation | DES138 - IF040 requires removal of REGS in "To Parties" field | CR039 | Closed |  |  | Error/Correction |  |  |  |  | Update IF040 in DES138, remove "Registration Service (REGS)" from "To Parties" field | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1014 | RG | DIN-992 | 2024-04-17 | SRO Design |  | Rob Golding | SRO Design | IF-016-ActivePowerRejected required incorrect | IF-016-ActivePowerRejected required field B900List should be B900 |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.3 |  | IF-016-ActivePowerRejected required field B900List should be B900 | Data interface correction | Technical Artefact | Interfaces | Swagger
MHHS-DIN-1015 | MF | DIN-999 | 2024-04-18 | UKPN |  | Neil Madley | Network Operator | Update routing for [MPANReconnection] and add event to Opt/In Out Matrix | On IF-009 add LDSO as secondary routed. Add [MPANReconnection] to the Opt In/ Opt Out Matrix so that LDSO's can opt out of receiving this event. |  | Implemented |  |  | Error/Correction | LDSOs |  | Interim Release 8.1 |  | On IF-009 added LDSO, SUPC as secondary routed. Added [MPANReconnection] to the Opt In/ Opt Out Matrix so that LDSO's can opt out of receiving this event. | Data interface correction | Supporting Docs | Interfaces | DES138
MHHS-DIN-1016 | RG | DIN-1017 | 2024-04-24 |  |  |  |  | REP002 & REP002B require update | Swagger for REP-002 & REP-002B needs to be updated to reflect the defns in ERI011B. REP-002 The ERI011B – ECS Reports spreadsheet has the R027 – Distributor ID as a repeating block, meaning that Suppliers will receive 1 REP-002 for each combination of Distributor and GSP Group. REP-002B Similarly the REP-002B has R009 as a repeating block |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.3 |  | Update swagger to reflect ERI011B | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-1017 | RG | DIN-1016 | 2024-04-24 | Design Team |  | Rob Golding | SRO Design | REP002 & REP002B require update | Swagger for REP-002 & REP-002B needs to be updated to reflect the defns in ERI011B. REP-002 The ERI011B – ECS Reports spreadsheet has the R027 – Distributor ID as a repeating block, meaning that Suppliers will receive 1 REP-002 for each combination of Distributor and GSP Group. REP-002B Similarly the REP-002B has R009 as a repeating block |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update swagger to reflect ERI011B | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-1018 | RG | DIN-1007 | 2024-04-22 | Avanade |  | Rob Golding | SRO Design | Change request body on Validation Endpoints | Avanade have reviewed the 1.7.1. endpoints and are requesting a change so that they are more flexible and align to the submission API |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Avanade have reviewed the 1.7.1. endpoints and are requesting a change so that they are more flexible and align to the submission API | Technical corrrection | Swagger |  | Swagger
MHHS-DIN-1019 | SC | Test Defect 31336/ DIN-966 | 2024-03-27 | Design Team |  | Sean Cooper | SRO Design | Revision to the PUB-004 Secondary routing logic. | SIT DEFECT - 31336 Currently distribution logic states delivery of PUB-004 to SUPC and XMSC. This results in the send of the message (IF-004) being unnecessrily copied in on the PUB-004. Secondary logic should reference sending party and issue to XMSC where sent by SUPC and SUPC where message sent by XMSC. |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | SIT DEFECT - 31336 Currently distribution logic states delivery of PUB-004 to SUPC and XMSC. This results in the send of the message (IF-004) being unnecessrily copied in on the PUB-004. Secondary logic should reference sending party and issue to XMSC where sent by SUPC and SUPC where message sent by XMSC. DIP routing updated as part of IR7 DES138 - IF-004 routing table updated in IR8.1 | Technical corrrection | Supporting Docs | Interfaces | DES138
MHHS-DIN-1020 | RS | DIN-851 | 2024-04-25 | Code |  | Matt McKeon | Central Body | Queries from REC RTS which relate to either DES138 or ERI110B | CD6-320 is pointing out that data item DI-218 has a different name in DES138 (Current Supplier DIP ID) and ERI011B (Daily Supplier MSID Count). CD6-323 is referring to DI-030 and DI-031 in DES138, asking what the distinction is when they have the same name CD6-325 is asking about a data item with the same name but different DI-refs in DES138 (DI-081) and ERI011B (DI-484) |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | CD6-320 - DI-218 no update required not in ERI011B CD6-325 - DI-484 to be corrected to DI-081 in ERI011b - Swagger to also be updated to reflect consistant use of DI-081 | Technical corrrection | Supporting Docs | Interfaces | ERI011B Swagger
MHHS-DIN-1021 | MF | DIN-949 | 2024-04-25 | SCS | 39365 | Daniel Tadecicco | Central Body | Migration Error Code Alignment with DES138 | Update all the error codes in Migration Design Document and Migration Requirements to align with DES138 |  | Implemented |  |  | Design misaligned | All Participants |  | Interim Release 8.1 |  | Update Migration requirements doc to align with all DES138 migration error codes and update Migration doc where relevant to reflect the DES138 error codes Updated DES138 error descriptions as follows: REG9010 - Cannot Manage MPAN Relationships for an Unmigrated MPAN REG9002 - Supplier Data Items Cannot be Maintained for an Unmigrated MPAN REG9001 - CDC Marker Cannot be applied to an Unmigrated MPAN Removal of reference to IF-040 and RCP1076 from migration design document | Technical corrrection | Migration | Supporting document | Migration Requirements Log Migration Design Document DES138
MHHS-DIN-1022 | ZH |  | 2024-04-26 | RECCo | 48861 | Sarah Jones | Consultancy | Implementation of CR037 (Migration Message Processing Choreography Update) | Please refer to the CR037 documentation for further details | CR037 | Implemented |  |  | Change Request | All Participants |  | Interim Release 8.1 |  | Updated Change of Agent Migration Timings , as per CR037. This includes the Migration Requirements log, Migration Design Document and the E2E non-functional requirements. | Technical corrrection | Migration | Supporting document | Migration Requirements Log Migration Design Document E2E002 - Non-functional requirements
MHHS-DIN-1023 | TR |  | 2024-04-26 | SCS | 46680 | Madison Layton | Software Provider | Meter Location Data Quality | The PUB-005 B033 block is mandatory on all event codes except for [MeterRemoval]. Within this block the Meter Location is mandatory, however F (not known) is permitted. Where MS is updating other MTDs, there is a risk that they will submit Meter Location F ‘not known’ despite Meter Location not having changed. This could lead to poor quality of meter location data within REGS. Potential mitigation could be level 5 validation rule on REGS: if Meter Location held in REGS is not F or null, then DI-090 must not be F. This would ensure Meter Location couldn’t be reverted to F from a previously specified value. |  | Initial Assessment/Updating |  |  | Design ambiguous | REGS |  | Post Go-live Release |  | Potential mitigation could be level 5 validation rule on REGS: if Meter Location held in REGS is not F or null, then DI-090 must not be F. This would ensure Meter Location couldn’t be reverted to F from a previously specified value. | Missing/incorrect validation rule | Supporting Docs | Supporting document | DES138
MHHS-DIN-1024 | RG | Test Defect 31491 | 2024-04-26 | Kraken |  | Dave Mclean | Software Provider | Use of Min items =1 to stop arrays with zero items | Messages are being sent with arrays with zero items in, however an array with zero items does not make sense. If minItems is set to 1, then schema validation would not allow arrays with zero items. Also, to improve data validation for nullable strings the minLength needs to be set to 1. |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Add minItems = 1 to array where a zero item array is not allowed, Add to the folllowing objects: B900 B901, B902, B920, B922, B921, B903, B906, B906a, B907, B908, B910, B911, B941 | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-1025 | MF |  | 2024-04-29 | Helix |  | Rashmi Radhakrishnan | Central Body | Update to ISD examples in MHHSP_EDI021_ISD_Entities | Update the examples in M7, M17 and M18 tables to support SIT testing |  | Closed |  |  | Design ambiguous | All Participants |  |  |  | Updated the examples in M7, M17 and M18 tables ( MHHSP_EDI021_ISD_Entities v5.7 ) to support SIT testing | Design Ambiguous | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-1026 | RG |  | 2024-04-29 | Kraken |  | Dave Mclean | Software Provider | Remove DT-008 from data types | The request is that as DT-008 is not use can it be removed from the swagger |  | Initial Assessment/Updating |  |  | Error/Correction | All Participants |  | Post Go-live Release |  | Remove DT-008 from data types | Data interface correction | Swagger | Interfaces | Swagger
MHHS-DIN-1027 | MF |  | 2024-04-30 | PDA |  | Tom Chevalier via Kevin Spencer | Data Service Provider | Remove reference to UMSDS on Consumption Amendment flow (IF-028) and Opt/In Out Matrix (IF-027) | Currently Consumption Amendment is not utilised by UMSDS so removed reference in the Consumption amendment flows |  | Initial Assessment/Updating |  |  | Error/Correction | UMSDS |  | Post Go-live Release |  | Remove UMSDS from "From parties" on IF-028. Updated UMSDS as N/A for IF-027 in Opt/In Out Matrix | Data interface correction | Supporting Docs | Supporting document | DES138
MHHS-DIN-1028 | MF |  | 2024-04-30 | SCS |  | Madison Layton | Software Provider | Update REG1040 description | Update the description for REG1040 to cover both SSC and Profile Class error messages to align with validation rules in IF-025 |  | Initial Assessment/Updating |  |  | Error/Correction | Suppliers, REGS |  | Post Go-live Release |  | Update REG1040 to "REG1040 - SSD/ Profile Class Effective From Date must be later than existing" and remove REG1041 in the "Introduction" Tab of DES138 | Data interface correction | Supporting Docs | Supporting document | DES138
MHHS-DIN-1029 | MF |  | 2024-04-30 | SCS |  | Madison Layton | Software Provider | Make B032 block mandatory for [SSCandProfileClass] event in IF-025 and IF-026 | Update Swagger and DES138 to make B032 block mandatory for [SSCandProfileClass] event in IF-025 and IF-026. |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update Swagger and DES138 to make B032 block mandatory for [SSCandProfileClass] event in IF-025 and IF-026. | Data interface correction | Supporting Docs | Supporting document | DES138 & Swagger
MHHS-DIN-1030 | RG | DIN-850 (original IR7 DIN) | 2024-04-30 | Callisto | 50078 | Scott Parkinson | Software Provider | IF037 DSDeApp CustomBlock requires B002 block | Looks as though some of the CR36 changes did not make their way into swagger: the change to include the B002 block in the IF-037 DSDeApp custom block is missing |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.3 |  | Update swagger so that B002 block included in the IF-037 DSDeApp custom block | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1031 | RG |  | 2024-05-01 | EDW Technology | 32016 | Mark Kenny-Jones | Software Provider | Inconsistencies between E2E & Swagger defn of Status Messages | Regarding the SRB that contains empty strings (i.e. the one used to report schema validation errors), are you aware that this does not comply with the current API schema? And if so, are there any plans to either update the schema, or to change the structure of this response so that it does comply with the schema? Specifically, I’m referring to the fact that there are a number of fields in the SRB that have minimum lengths, which an empty string would violate. Similarly, none of the fields are marked as nullable, therefore replacing an empty string with an explicit null value would also violate the schema. Excluding the fields entirely also wouldn’t be an option, as some of the fields are mandatory, and this would also go against the advice in section 4.6.6.2 of the end to end architecture document (E2E001 v3.6) says that “Where a field is not written/available/optional, then a null value needs to be written” |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | The standard Response body has been updated to follow the manadatroy/null design approach. | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1032 | TR |  | 2024-05-01 | ESG |  | Patricia Parker | Software Provider | DI-103-Configurable-Register-ID need to be alpahnumeric | The REGEX in Swagger for DI-103-Configurable-Register-ID which requires numeric values only, the data element should just be a string(2), as per DES-138, to allow numeric or aphla characters. |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update Swagger so the data element is string(2) to allow for numeric and alpha characters | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1033 | MF |  | 2024-05-01 | Helix |  | Rashmi Radhakrishnan | Central Body | Updates to ISD M17/ M7 tables | Updated ISD M17 to add in Meter Group as Char 11 to align with M7 Meter Group. Added allowable values to cover Unmetered in M7 |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated the M17 table to include Meter Group as Char 11. Added Unmetered to Meter Group in both M7 and M17. Updated Meter Type in M7 to “Mandatory. Valid Set as per EMAR1 or U for Unmetered” | Design Ambiguous | Supporting Docs | ISD document | ISD Entity
MHHS-DIN-1034 | RG |  | 2024-05-03 | SCS | 50636 | Mariana Mesaros | Software Provider | REP900 & RE901 are missing schema version ERI011B spreadsheet | REP900 & RE901 are missing schema version in S0 block in ERI011B spreadsheet. The swagger has the schema version |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updated ER0I011B with schema version for REP-900/1 | Data interface correction | Supporting Docs | Interfaces | ERI011B
MHHS-DIN-1035 | RG | DIN-850 (original IR7 DIN) DIN-1030 (7.3 DIN) | 2024-04-30 | Callisto | 50078 | Scott Parkinson | Software Provider | IF037 DSDeApp CustomBlock requires B002 block | Looks as though some of the CR36 changes did not make their way into swagger: the change to include the B002 block in the IF-037 DSDeApp custom block is missing |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update swagger so that B002 block included in the IF-037 DSDeApp custom block | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1036 | RG |  | 2024-05-09 | Avanade |  | Ptior Penar | Software Provider | DI-432-Period-Metering-System-Metered-Data requires clarification | DI-432-Period-Metering-System-Metered-Data need to remove multiplier constraint |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update swagger DI-432 | Data interface correction | swagger | Interfaces | Swagger
MHHS-DIN-1037 | RG |  | 2024-05-10 | St Clements | 50045 | Vicki Holland/Tom Perryman | Software Provider | REP900 Changes | Changes to be made to the REP900 are: • REP900-03 to be a parent of REP900-04 • Delete data item DI-563 (LDSO Billing Account Reference) as it is redundant with Site Id and Invoice Number also included in the message • Move the following data items to REP900-04 as they can all change for a site and are specific to the invoice raised: - 612 (Site DUoS Tariff ID), 566 (List of MPANs), 567 (Misaligned multi MPAN site), 568 (Site Capacity) • Update DI-565 LDSO Billing Site ID to data type of String(30) • Add GSP Group ID to the REP900-03 site record |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Updates to Swagger & ERI011B | Data interface correction | swagger | Interfaces | Swagger/ERI011B
MHHS-DIN-1038 | MF | DIN 973 | 2024-05-10 | ESG |  | Patricia Parker | Software Provider | Clarify Migration Reqs re D0312 | Requirment updated to refeclt that IF-035 with Lapsed Reason Code of LP001 (MPAN Disconnected/deRegistered) will be issued for any Pending Service Provider Appointments on receipt of MPAN termination (not D0312) |  | Implemented |  |  | Error/Correction | REGS |  | Interim Release 8.1 |  | Remove reference to D0312 in the note added to REGS Migration Requirement MHHS-Migration-Can-RS-006 as it is triggered by receipt of a termination of the MPAN from the LDSO following receipt of D0132 | Requirement correction | Migration | Supporting document | Migration Design Requirements
MHHS-DIN-1039 | MF | DIN-946 | 2024-05-10 | ESG |  | Patricia Parker | Software Provider | Update Lapse codes scenario's in DES138 | update DES138 (IF-035) to show LP004 can also apply to MCS scenario and LP006 would only apply to MCA scenario |  | Open - awaiting assessment |  |  | Error/Correction | All Participants |  | Post Go-live Release |  | update DES138 (IF-035) to show LP004 can also apply to MCS scenario and LP006 would only apply to MCA scenario | Data interface correction | Supporting Docs | Supporting document | DES138
MHHS-DIN-1040 | RG |  | 2024-05-15 | Kraken | 52894 | Dave MaClean | Software Provider | Migration Deisgn: Missing B095 block in IF-003-MSDeAppRM & missing B096 block in IF-003-DSDeAppRM | Ticket noticed B095 is missing from the IF-003-MSDeAppRM variant. On closer inspection the B096 is also missing from the IF-003-DSDeAppRM |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Both DES138 and the Swagger both need updating: Missing B095 block in IF-003-MSDeAppRM & missing B096 block in IF-003-DSDeAppRM | Data interface correction | Supporting Docs | Interfaces | DES138 & Swagger
MHHS-DIN-1041 | RG |  | 2024-05-16 | MHHS |  |  |  | Alignment of DES138 to message version numbers | The message version numbers in DES138 need to be aligned to the swagger versions, ie. version '011' for release 7.x. Also align IF-061/5 to the other interfaces |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Update DES138 to the correct version, update swagger for IF-061/If-062/If-063/IF-064/IF-065 to version '011' so consistent with other IFs |  |  |  | DES138 & Swagger
MHHS-DIN-1042 | RG |  | 2024-05-17 | Kraken | 52894 | Dave MaClean | Software Provider | DI-830 (B070) Swagger/ DES138 descrepancy | The MeteringServiceDIPEffectiveFromDate is from the Data Catalogue on DES138. In the defn of the B070 block the term proposedMeteringServiceEffectiveFromDate is used (ana probabaly the better term to use). However, too late to change, so an update to DES138 to align the B070 to the DC/Swagger is required |  | Initial Assessment/Updating |  |  | Error/Correction |  |  | Post Go-live Release |  | Update B070 block in DES138 to align with swagger/data catalogue | Data interface correction | Supporting Docs | Supporting document | DES138
MHHS-DIN-1043 | RS |  | 2024-05-21 | Siemens | 53765 | Tony Mason | Metering Service Provider | Method Statement where site is disabled | Method 12 in both SDS and ADS Method statement documents should state the reason code as Disabled, looks like currently a cut & paste from method 11 |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | METH001 (SDS) and METH002 (ADS) to be updated with the following for Method 11 & 12 (replacing SDS with ADS for METH002 - also amending 'Site' to lower case Method 11. Estimation for Long Term Vacant Sites Where the Supplier has notified a Flag to identify that a site is LTV and in cases where no access to consumption data is available, then in the presence of this flag the SDS will estimate zero and set a LTV estimation reason code. This data will be recorded as “ZE2” and the estimation reason code ‘LTV’ should identify as LTV. UTCPDj = 0 Method 12 Estimation where a site where Supply is disabled Where the Supplier has notified a Flag to identify a site where the supply is disabled and in cases where no access to consumption data is possible, then in the presence of this flag the SDS will estimate zero. This data will be recorded as “ZE3” and set the estimation reason code ‘Disabled’. | Method statement correction | Supporting Docs | Supporting document | METH001 METH002
MHHS-DIN-1044 | RG |  | 2024-05-23 | ESG | 54979 | Kerry O'Donnel | Software Provider | IF-009-MPANReconnection has incorrect event code | The event code for IF-009-MPANReconnection need to be [MPANReconnection] rather than [MPANDReconnection] |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | The event code for IF-009-MPANReconnection need to be [MPANReconnection] rather than [MPANDReconnection] | Data interface correction | Supporting Docs | Interfaces | Swagger
MHHS-DIN-1045 | RG |  | 2024-05-29 | SRO |  | Rob Golding | SRO Design | Tidy up of routing rules for IF-041 | The routing rules table for IF-041 requires updating |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | The second and third rows in the routing table in DES138 need to be merged. | Data interface correction | Supporting Docs | Supporting document | DES138
MHHS-DIN-1046 | RS |  | 2024-06-04 | SRO |  | Matt McKeon | SRO Design | Clarifications to the ECS DTN Reports | Retrospective changes made to D0397 - MHHS Supplier Half Hourly Demand Report (now v1.2) D0401 - MHHS Aggregated Disconnected DUoS Report (now v1.1) D0402 - MHHS Supplier Half Hourly Demand Disconnection Report (now v1.1) D0403 - MHHS GSP Group Demand Disconnection Totals Report (now v1.1) D0404 - MHHS Supplier BM Unit Demand Disconnection Report (now v1.1) |  | Implemented |  |  | Error/Correction |  |  | Interim Release 7.3 |  | D0397 - Updated the Range of Group 02Z ‘Daily Totals Per Suppler’ from ‘1-1’ to ‘0-*’ D0401 - Amended MM Description to say “A report of Disconnected Volumes by Distributor. Where the report is sent to the Distributor it will contain data for all Suppliers impacted by the Demand Control Event, whereas where it is sent to the Supplier it will only contain data pertaining to that Supplier.” - Renamed DI20306 ‘DUoS Daily Supplier Demand Disconnection Volume’ to ‘DUoS Daily Smart and Unmetered Demand Disconnection Volume’ - Renamed DI20307 ‘DUoS Daily Supplier Demand Disconnection Volume Losses’ to ‘DUoS Daily Smart and Unmetered Demand Disconnection Volume Losses’ - Renamed DI20310 ‘DUoS Supplier Demand Disconnection Volume’ to ‘DUoS Smart and Unmetered Demand Disconnection Volume’ - Renamed DI20311 ‘DUoS Supplier Demand Disconnection Volume Losses’ to ‘DUoS Smart and Unmetered Demand Disconnection Volume Losses’ - Updated the Range of Group 79J ‘Demand Control Event Details‘ from ‘1-*’ to ‘1:1’, so that one report is produced per DDE. D0402 - MHHS Supplier Half Hourly Demand Disconnection Report (now v1.1) - Updated the Range of Group 04K ‘Demand Control Event Details‘ from ‘1-*’ to ‘1:1’, so that one report is produced per DDE. D0403 - Updated the Range of Group 36K ‘Demand Control Event Details‘ from ‘1-*’ to ‘1:1’, so that one report is produced per DDE. D0404 - Updated the Range of Group 43K ‘Demand Control Event Details‘ from ‘1-*’ to ‘1:1’, so that one report is produced per DDE. | Technical corrrection | Supporting Docs | Supporting document | D0397 - MHHS Supplier Half Hourly Demand Report D0401 - MHHS Aggregated Disconnected DUoS Report D0402 - MHHS Supplier Half Hourly Demand Disconnection Report D0403 - MHHS GSP Group Demand Disconnection Totals Report D0404 - MHHS Supplier BM Unit Demand Disconnection Report
MHHS-DIN-1047 | MF | DIN-934 | 2024-06-04 | SCS |  | Daniel Tadecicco | Central Body | Additional value of U for Energisation Status used during Migration | Add new valid value of U - Undefined to DI-033 to allow a value to be populated during Migration. This will be updated with the actual Energisation Status at the stage the IF-036 is issued and the value has been set in Registration Service |  | Implemented |  |  | Error/Correction | All Participants |  | Interim Release 8.1 |  | Add U - Undefined as an allowable value to be used for Energisation Status during Migration in DI-033 for IF-001, IF-002 and IF-033 in DES138/ swagger. Participants will be updated with the actual Energisation Status when the IF-036 is issued. Remove U as an allowable value from DI-033 in IF-007 in DES-138. | Data interface correction | Supporting Docs | Interfaces | DES138 & Swagger
MHHS-DIN-1048 | ZH |  | 2024-06-04 | MHHS |  | Zakir Hussain | Consultancy | BRS002 requirements typo | Business Requirements MHHS-BR-MS-071.1 and MHHS-BR-MS-071.2 should be documented within MHHSP-BRS002-Metering Service requirements v5.6 and should apply to both the MSS and MSA Roles. Unfortunately, there is a typo in the Bus Requirement and these are currently showing as DS versions in 3 tabs (all, MSS and MSA) i.e. MHHS-BR-DS-71.1 and MHHS-BR-DS-71.2 which is not aligned to the naming convention around them. |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | Update BRS002-Metering Service Requirements - Change requirement "MHHS-BR-DS-071.1" and "MHHS-BR-DS-071.2" to "MHHS-BR-MS-071.1" and "MHHS-BR-MS-071.2" | Requirement correction | All Areas | Requirements | MHHSP-BRS002
MHHS-DIN-1049 | ZH |  | 2024-06-04 | MHHS |  | Zakir Hussain | Consultancy |  | An exemption has been made in the Qualification process for certain Suppliers. Essentially if a Supplier commits to never supplying Unmetered MPANs they do not have to undertake the qualification tests pertaining to unmetered MPANs – largely as they would have to build capability they would never use. Could I therefore request a DIN be raised to add the following the Supplier Requirements set: · a Supplier not Qualified for UMS shall not migrate UMS MPANs into the new MHHS arrangements. · a Supplier not Qualified for UMS shall not register UMS MPANs in the new MHHS arrangements. This will allow traceability in Qualification assurance to allow qualifying bodies to ask suppliers what controls they have in place to restrict this. |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | Add the following the Supplier Requirements set: · a Supplier not Qualified for UMS shall not migrate UMS MPANs into the new MHHS arrangements. · a Supplier not Qualified for UMS shall not register UMS MPANs in the new MHHS arrangements. | Requirement correction | All Areas | Requirements | Supplier Requirements Doc
MHHS-DIN-1050 | RG | DIN-211 | 2024-06-06 | SRO |  | Rob Golding | SRO Design | B042 - DI-077 Naming descrepancy | DES-138 has DI-077 named as DI-077-CSS-RMP-DeActivation-Date whilst in swagger the corresponding filed name is CSSMPANDeRegistrationDate. Normally the two should align |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | In swagger th ename of the field is incorrectly titled "CSSMPANDeRegistrationDate". The least change approach is to update DES | Technical corrrection | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-1051 | TR |  | 2024-06-11 | Design Team |  | Tamsyn Robertson | SI Design | MHHS-REP-002B Description Field Update | The Description field in the REP-002B spec is not correct. The reference to Suppliers needs to be removed. The 'To Parties' and 'Routing Rules' are correct. |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | Change 'Description' field in DES-138 to: 'The report provides aggregated Distribution Use of Systems data for LDSOs or Suppliers in Clock Time.' | Document Correction | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1052 | TR |  | 2024-06-11 | Design Team | 57348 | Tamsyn Robertson | SI Design | ISD entity M2- Typo | The latest version of the ISD spec currently lists M2 - Connection Type Description H as "High Voltage with Current transformer" with a lowercase "t" in "transformer.". BSCP707 Appendix 1 and Appendix 2 has been updated, so this DIN is to align with the correction to the code. |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | Update M2 - Connection Type Description H to: "High Voltage with Current tTransformer" | Document Correction | Supporting Docs | ISD | EDI021 ISD Entities
MHHS-DIN-1053 | TR |  | 2024-06-11 | Opus | 56809 | Lee Eltherington | Supplier | D0397 - Consumption Component Indicator | The Data Item List at the top of the D0397 PDF does not contain the Consumption Component Indicator field that is showing in the dataflow structure. |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | Update the D0397 document to include the Consumption Component Indicator and link to J0162. | Document Correction | Supporting Docs | D-Flow Documents | D0397
MHHS-DIN-1054 | TR |  | 2024-06-11 | ESG | 57833/58471 | Patricia Parker | Software Provider | D0149 - Missing SV | Updates required for the D-flow documentation |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | Need all three scenario variants (smart to smart, legacy to smart and smart to legacy). in DTC. Possible error in both the D0149 and D0150. | Document Correction | Supporting Docs | D-Flow Documents | DTC D0149 D0150
MHHS-DIN-1055 | RG |  | 2024-06-12 | Kraken | 58587 | Dave Maclean | Software Provider | IF-006 S0 block missing required properties | InterfaceID, schemaVersion & eventCode fields should be marked as required on the S0 block on the IF-006 interface |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | Add required fileds to S0 blocks in all IF-006 variants - InterfaceID, schemaVersion & eventCode | Technical corrrection | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-1056 | RG |  | 2024-06-26 | Avanade |  | Gaurav Agrawal | Software Provider | R900-04 block remove LDSOBillingSiteID from required list | The R900-04 block still has LDSOBillingSiteID in the required parameters - it needs to be removed |  | Ready for Internal Review |  |  | Error/Correction |  |  | Interim Release 8.2 |  | Remove LDSOBillingSiteID from required field in R900-04 | Technical corrrection | Supporting Docs | Swagger | Swagger
MHHS-DIN-1057 | RG |  | 2024-06-26 | SRO Design | 61939 | Rob Golding | SRO Design | DIP L3 webhook response time set to 10 secs | The DIP timeout on a synchronous response was set to 5 seconds, this will be updated to align with the NFRs |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | Update E2E SA document & requirements with value | Technical corrrection | Supporting Docs | E2E001, E2E002 | E2E001, E2E002
MHHS-DIN-1058 | SB |  | 2024-06-26 | SCS | 62087 | Madison Layton | Central Body | DI-260 Missing MDR and Consent Granularity in MHHS-BR-RS-074 | The Registration Service Requirements is missing the requirement to apply MDR and Consent Granularity to related secondary MPANs when confirming a new Data Service Appointment on a Primary MPAN. Suggested uplift below in red. Detail shown on the Fresh Desk Ticket |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | Update MHHS-BR-RS-074 | Requirement correction | All Areas | Requirements | REGS Requirements
MHHS-DIN-1059 | RG |  | 2024-06-26 | EDW Tech | 62837 | Kavita Siddle | Central Body | IF-020-RelatedCreate has two unwanted Event Codes | IF-020-RelatedCreate has two unwanted Event Codes [RelatedAdd] and [RelatedRemove]. |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | Remove the two unwanted Event Codes from the IF-020-RelatedCreate message variant in swagger. Shouldn't affect testing as the messages resove to the same structure | Technical corrrection | Supporting Docs | Interfaces | DES138 Swagger
MHHS-DIN-1060 | RG |  | 2024-06-28 | Avanade |  | Piotr Penar | Software Provider | API Key changes: Add MSG1015 to list of acceptable error codes | Add "MSG1015: X-API Key does not match the sender" error message to Introduction tab on DES-138 and swagger |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | Update DES138 to include the the new error condition where API key doesn't belong to message sender | Technical corrrection | Supporting Docs | Swagger | DES138 Swagger
MHHS-DIN-1061 | RG |  | 2024-07-01 | Avanade |  | Gaurav Agrawal | SRO Design | Add MSG1039, MSG1040, MSG1041 to list of acceptable error codes | MSG1039:Invalid MPAN MSG1040:Not currently appointed MSG1041:MPAN not known |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | Update DES138 to include the the new error conditions | Technical corrrection | Supporting Docs | Interfaces | DES138
MHHS-DIN-1062 | RG |  | 2024-07-03 | Wheatley Solutions |  | Chris Mingay | Software Provider | Connection requests are missiing a User Agent which occassionally trigger FW rule | Add User Agent Header to DIP http requests so that identification is clear on interfacing sysems. Avanade ADO ticket no 42340 |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | Update CoCo (E2E) to add new http header info | Other | All Areas | End to End Documentation | E2E Code of connections document
MHHS-DIN-1063 | TR |  | 2024-07-05 | Helix | 65874 | Riccardo Lampini | Central Body | Measurement Quantity Naming Convention | There are inconsistencies with the use of Measurement Quantity/Measurement Quantity ID within 3 entities as per the ISD Entity Spec and this is not aligned with Swagger/MDS Method Statement |  | Ready for Internal Review |  |  | Error/Correction |  |  | Interim Release 8.2 |  | Update ISD Entity spec and method statement to align the terminology with what is used in Swagger. MHHS Both Consumption Component Classes, Load Shape Categories to state 'Measurement Quantity ID'. This is correct in the Measurement Quantity Entity | Document Correction | Supporting Docs | ISD | EDI021 ISD Entities METH001 (SDS) METH002 (ADS) METH004 (UMSDS) METH005 (LSS) METH006 (VAS)
MHHS-DIN-1064 | TR |  | 2024-07-05 | CGI | 62573 | Dave Webster | Software Provider | PUB-045 for UMSDS | According to DES138 5.8.2 sheet 04_IF_OptOut_Matrix, UMSDS can opt out of receiving an IF-045 [InvalidMarketSegment] message. However, according to sheet 02_IF-045, a UMSDS is not a valid recipient of an IF-045. |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | Update 04_IF_OptOut_Matrix to remove UMSDS from IF-045 [InvalidMarketSegment] | Technical corrrection | Supporting Docs | Interfaces | DES-138
MHHS-DIN-1065 | SB |  | 2024-07-09 | RECCo | 66065 | Jonny Moore | Central Body | Energisatio |  |  | Open - awaiting assessment
MHHS-DIN-1066 | MF |  | 2024-07-10 | EoN |  | Cathy Mulliss | Supplier | Clarification on requirments for maintaining Customer and PSR data by the Data Service | Clarify that the Data Service only has to maintain Customer and PSR data where the data is provided by the Supplier. If the Supplier and Data Service have bilateral agreements whereby this is not required then this data does not have to be shared by the Supplier and maintained by the Data Service . |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | A clarification has been issued as part of the Knowledge Base that Suppliers can make bilateral agreements with Data Services and Meter Reading Services for the provision of meter readings to the Data Service. Where the Data Service does not require Customer/ PSR data to meet their obligations for providing data to Settlements, the Supplier can elect not to share Customer and PSR data to the Data Service. Minor tweak to the requirments to make it clear that this information is only shared and maintained where required. | Document Correction | Meter to Bank | Data Service requirments Supplier Overview | BRS001 BRS004
MHHS-DIN-1067 | RG |  | 2024-07-12 | CGI | 67334 | Chris Beard | Software Provider | Ensure Correlation Id information in E2E001 E2E SA doc aligns to DES138 | Reviewing the E2ESA doc the corrleation Id info need to relect the infromation in DES138 |  | Open - awaiting assessment |  |  | Error/Correction |  |  | Post Go-live Release |  | Minor update to E2ESA doc | Document Correction |  |  | E2E001