## SIT Readiness Tracker
SIT Stage | CIT Interval | Owner (PP/SI) | Task Category | Task | Start Date | Finish Date | Status (RAG) | Commentary | Forecast Date | Milestone Tier | Milestone ID
CIT | All | SI | Milestone | Notification of Production Data Cut issued to relevant participants |  | 2023-06-19 | Green |  |  | T3 | T3-TE-0011
CIT | All | SI | Deliverables | SIT Component Integration Test Approach & Plan approved |  | 2023-07-19 | Green |  |  | T3 | T3-TE-0012
CIT | All | SI | Deliverables | SIT Component Integration Test Data Approach and Plan approved |  | 2023-07-19 | Green
CIT | All | SI | Deliverables | SIT Component Integration Testing Test scenarios approved |  | 2023-08-16 | Green |  |  | T3 | T3-TE-0014
CIT | All | SI | Deliverables | SIT Component Integration Testing Test Cases approved |  | 2019-01-01 | Green | Note - amended plan and milestones to agreed at Aug TMAG. |  | T3 | T3-TE-0069
CIT | All | SI | Deliverables | Environment Approach & Plan - CIT Iteration |  | 2023-08-16 | Green | Note - new milestone agreed at July TMAG. |  | T3 | New Milestone to be added
CIT | All | SI | Data | Production data cut GONG decision |  | 2023-08-16 | Green |  |  | T3 | T3-TE-0017
CIT | All | SI | Data | Take Data Cut | 2023-08-19 | 2023-08-19 | Green
CIT | All | SI | Data | Data cut from relevant participants' production systems completed |  | 2023-08-21 | Green |  |  | T2 | T2-TE-0200
CIT | All | SI | Data | Check and Transmit Data to SI (EES Only) | 2023-08-21 | 2023-08-25 | Green
CIT | All | SI | Data | Data Sharing Agreements Complete |  | 2023-08-25 | Green |  |  | T3 | New Milestone to be added
CIT | All | SI | Deliverables | Requirements Traceability Matrix |  | 2023-10-06 | Green
CIT | 1 | PP | PIT | PIT Approach and Plan |  | 2023-07-07 | Green
CIT | 1 | SI | PIT Assurance | Assurance of PIT Approach and Plan | 2023-07-07 | 2023-07-21 | Green
CIT | 1 | PP | PIT | PIT Requirements to Test Traceability Matrix |  | 2023-08-04 | Green
CIT | 1 | SI | PIT Assurance | Assurance of Requirements to Test Traceability Matrix | 2023-08-04 | 2023-08-18 | Green
CIT | 1 | PP | PIT | PIT Test Scenarios |  | 2023-08-04 | Green
CIT | 1 | SI | PIT Assurance | Assurance of PIT Test Scenarios | 2023-08-04 | 2023-08-18 | Green
CIT | 1 | PP | PIT | PIT Test Readiness Reports | In Line with PP’s PIT Execution Plan |  | Green
CIT | 1 | SI / PP | Envs | SIT Participants' SIT A environments ready to start connectivity proving (incl certificates and security compliance) CIT Interval 1 |  | 2023-09-01 | Green | Note - New Onboarding Plan will result in new tasks and dates for certificates (pending Aug TMAG approval) |  | T3 | T3-TE-0019
CIT | 1 | PP | PIT | PIT Execution | In Line with PP’s PIT Execution Plan | 2023-09-29 | Green
CIT | 1 | PP | PIT | PIT Test Execution Progress Reports | In Line with PP’s PIT Execution Plan |  | Green
CIT | 1 | PP | PIT | PPs Issue Draft PIT Completion Report |  | 2023-09-08 | Green
CIT | 1 | SI | PIT Assurance | Draft PIT Completion Reports assured by SI | 2023-09-08 | 2023-09-29 | Green
CIT | 1 | PP | PIT | PPs Issue Final PIT Completion Report |  | 2023-09-29 | Green
CIT | 1 | SI | PIT Assurance | PP Final PIT Completion Reports assured by SI | 2023-09-29 | 2023-10-06 | Green
CIT | 1 | SI | PIT | PP PIT Evidence assured by SI | 2023-09-08 | 2023-10-06 | Green
CIT | 1 | SI | Data | Run Data Allocation for CIT INT 1 | 2023-09-04 | 2023-09-07 | Green
CIT | 1 | SI | Data | Cleanse and populate data post-cut | 2023-09-08 | 2023-09-13 | Green
CIT | 1 | SI | Data | Transmit data sets to PPs - CIT INT 1 | 2023-09-14 | 2023-09-15 | Green
CIT | 1 | PP | Data | PP Load test data sets to test environment | 2023-09-18 | 2023-09-22 | Green
CIT | 1 | PP | Data | PP check data integrity on test environment | 2023-09-25 | 2023-09-29 | Green
CIT | 1 | PP | Envs | Environment Connectivity proving has been successfully completed and evidence assured by the SI (If applicable) |  | 2023-09-29 | Green | Note - New Onboarding Plan will result in task being amended (pending Aug TMAG approval)
CIT | 1 | PP | Release | MHHS code deployed to SIT PPs' envs |  | 2023-09-29 | Green
CIT | 1 | SI | ADO | Test Management Tool Users Requested |  | 2023-09-22 | Green
CIT | 1 | PP | ADO | Test Management Tool Users Provided |  | 2023-09-29 | Green
CIT | 1 | PP | Resources | Participants have confirmed they have resources with the requisite skills and system access to support the test stage execution and defect management process |  | 2023-09-29 | Green
CIT | 1 | SI / PP | Test Management | PP Test execution schedule confirmed with PP |  | 2023-09-29 | Green
CIT | 1 | PP | Deliverables | PP Issues CIT Test Readiness Report |  | 2023-09-29 | Green
CIT | 1 | SI | Test Assurance | PP CIT Test Readiness Reports Assured by SI | 2023-09-29 | 2023-10-06 | Green
CIT | 1 | SI | ADO | Test Management Tool Users Set up |  | 2023-10-06 | Green
CIT | 1 | SI | ADO | Tests loaded in ADO |  | 2023-10-06 | Green
CIT | 1 | SI | ADO | Tests allocated to participant ADO Instance |  | 2023-10-06 | Green
CIT | 1 | SI | Tooling | Test stubs & Harnesses set up and ready |  | 2023-10-06 | Green
CIT | 1 | SI | Test Management | Test reporting has been set up |  | 2023-10-06 | Green
CIT | 1 | SI | Test Management | Test Meetings Scheduled with PPs |  | 2023-10-06 | Green
CIT | 1 | SI | Defect Management | Defect reporting has been set up |  | 2023-10-06 | Green
CIT | 1 | SI | Defect Management | Defect Meetings Scheduled with PPs |  | 2023-10-06 | Green
CIT | 1 | SI | Envs | Environment Management Meetings Set Up |  | 2023-10-06 | Green
CIT | 1 | SI | Deliverables | SI Issues Overarching CIT Test Readiness Report |  | 2023-10-06 | Green
CIT | 1 | SI | Deliverables | SI Overarching CIT Test Readiness Report reviewed by SITWG / IPA | 2023-10-06 | 2023-10-13 | Green
CIT | 1 | PP | ADO | PP verifies that tests have been allocated correctly |  | 2023-10-13 | Green
CIT | 1 | SI / PP | ADO | Test Management Tool Training Complete |  | 2023-10-20 | Green
CIT | 1 | SI | Milestone | SIT Component Integration Testing 1 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) |  | 2023-10-23 | Green |  |  | T2 | T2-TE-0250
CIT | 1 | SI | Milestone | Component Integration Testing Interval 1 Start |  | 2023-10-30 | Green |  |  | T3 | T3-TE-0060
CIT | 1 | SI | Milestone | System Integration Testing Start (M9) - PSG |  | 2023-10-30 | Green |  |  | T1 | T1-TE-1000
Please Note - RAG status is illustrative only

## Sheet1 (hidden)
PP Organisation | b. If you are proposing to delegate any of your testing to a 3 rd party [3] | a. What Roles (and MPIDs) you plan to Qualify via SIT
Belsize | Utiliteam | Suppler
British Gas | Callisto | MOP = MSS / MSA
British Gas | ENSEK | TILL Supplier
E | ESG | Suppler
E.ON Next | Kraken Tech. | E.ON Next plan to qualify in the supplier role via SIT.
E.ON UK Energy Services Ltd | Wheatley Solutions | MSS for both the EMEB and MIDE MPIDs.​
E.ON UK Energy Services Ltd | Exit Group NATP MPID | MSA both the EMEB and MIDE MPIDs.​
EDF | ESG | MSS & MSA
Edgware | Utiliteam | Suppler
Energy Assets | ESG | MSS & MSA
nPower Business Solutions | Wheatley Solutions | Advanced Data Services (MSA) for the NATP MPID
nPower Business Solutions | Yes – Although, this is part of a procurement exercise which hasn’t yet concluded so I can’t confirm the name of the provider just at the moment. However the testing will be fully delegated to that appointed 3rd party. | Advanced Data Services (ADS) for the NATP MPID
Octopus | Kraken Tech. | Supplier
Ovo | ESG | MSS & MSA
Ovo | ESG | Supplier
Rebel Energy | ESG | Suppler
Siemens | (blank) | (blank)
Stark | Wheatley Solutions | MPID that will qualify in for MSA and MSS
Unify | Seaglass | Suppler - TLWD
Grand Total

## Sheet2 (hidden)
Placing Reliance Proposals by Roles
PP Organisation | Delegated 3 rd party | Roles (and MPIDs) you plan to Qualify via SIT
British Gas | Callisto | MOP = MSS / MSA
British Gas | ENSEK | TILL Supplier
E | ESG | Suppler
EDF | ESG | MSS & MSA
Energy Assets | ESG | MSS & MSA
Ovo | ESG | MSS & MSA
Ovo | ESG | Supplier
Rebel Energy | ESG | Suppler
E.ON UK Energy Services Ltd | Exit Group NATP MPID | MSA both the EMEB and MIDE MPIDs.​
E.ON Next | Kraken Tech. | E.ON Next plan to qualify in the supplier role via SIT.
Octopus | Kraken Tech. | Supplier
Unify | Seaglass | Suppler - TLWD
Belsize | Utiliteam | Suppler
Edgware | Utiliteam | Suppler
E.ON UK Energy Services Ltd | Wheatley Solutions | MSS for both the EMEB and MIDE MPIDs.​
nPower Business Solutions | Wheatley Solutions | Advanced Data Services (MSA) for the NATP MPID
Stark | Wheatley Solutions | MPID that will qualify in for MSA and MSS
nPower Business Solutions | Yes – procurement exercise on going | Advanced Data Services (ADS) for the NATP MPID
Siemens | Intent declared no proposal submitted to date