## Dataflow-specific comments
Data Flow Id | Data Flow Name | Owner | Impact Category Tab | Comment Owner | Response Comment | Comment Action/Response
D0001 | Request Metering System Investigation | BSC | Go-Live Change (BSC) | British Gas | Notes - Typo 'D001' should be 'D0001'. | Corrected notes field as per comment
D0005 | Instruction on Action | BSC | Go-Live Change (BSC) | British Gas | Notes - Typo 'D005' should be 'D0005'. | Corrected notes field as per comment
D0012 | Confirmation of the Inclusion of the Metering Point in the Reading Schedules | BSC | Redundant post-MHHS | ESG Global | When will MHHSP determine if the D0012 is to be retained for traditional meters. This needs to be defined asap as this has an impact on design and build. This is no longer required as this is covered in the new MHHS message | Current view remains that D0012 is not required on an enduring basis - will confirm by next DAG meeting. This has been noted in v0.5 of DES196.
D0019 | Metering System EAC/AA Data | BSC | Redundant post-MHHS | ESG Global | Does the IF-040 Notification of Annual Comsumption not replace the AA element of the D0019 | Yes, Annual Consumption will be similar to the AA in the D0019, but as an input to estimation rather than as a fundamental component of NHH settlement data.
D0179 | Confirmation of Energisation/De-Energisation of Prepayment Meter | REC | Go-Live Change (REC) | ESG Global | Does this not require- Add new SV for MSS and MSA | Yes, this is reflected in the REC MSAG attachments but was not in the summary file - now added.
D0217 | Notification to New Supplier of Site Information | BSC | D Flow Overview | British Gas | Unclear how industry will identify the relationship of the Service Provider and if held by customer or supplier. D0217 is currently prior agent appointment. This means data will be default until updated later | Will confirm by end of July if there is an information gap between the IF-002 and D0217 as suggested.
D0242 | Supercustomer DUoS Daily Statement | DCUSA | Redundant post-MHHS | ESG Global | Could you please confirm if the D0242 will be retained. My understanding is that this iscovered CR019 MHHS-DIN-246 for delivery as part of interim R3. Suppliers will receive the ELX-REP-002 ‘LDSO or Supplier report for DUoS – aggregated data’ and the ELX-REP-002A ‘Embedded Network report for DUoS – aggregated data’ over the DIP, for whole current MPANs, from the SVAA. The replacement flow(s) proposed will provide the equivalent charging data to the D0242/D0315. Suppliers and Embedded Networks will need to aggregate the DUoS charges on the DTN and DIP flows to understand their total charges until all MPANs on the Network have been migrated. | Yes, ESG understanding is correct - DES196 amended to reflect the arrangements described here.
D0275 | Validated Half Hourly Advances | BSC | D Flow Overview | British Gas | The related interface column implies that IF-021 is replacing D0275 - but since the BSC tab states that the D0275 will be enhanced with the ADS and SDS roles we believe you should say something like IF-021 (optional) for clarity. | Wording clarified to state that IF-021 must be used for settlement purposes, but D0275 can be used for other purposes where bilaterally agreed.
D0275 | Validated Half Hourly Advances | BSC | Go-Live Change (BSC) | ESG Global | There appears to be a contradiction in the notes message and the specific comments. Could you please confirm how the D0275 will be handled and under what scenarios ans over what period. | Second paragraph is confusing. It intended to say that the use of these flows under the old settlement arrangements will remain until runoff is complete, i.e. any SVs sent or received by DCs and/or DA.
D0300 | Disputed Readings or Missing Readings on Change of Supplier | REC | Go-Live Change (REC) | ESG Global | Could you please clarify if the D0300 will be issued to the DS as it is our understanding that this flow is only going to be used between Suppliers | D0300 process will be a Supplier to Supplier process only - this is reflected in the REC MSAG documents.
D0300 | Disputed Readings or Missing Readings on Change of Supplier | REC | Go-Live Change (REC) | Ovo | This should be a trad/non-comms meter issue only. Process 3.4 of BSCP701 details how the SDS needs the cumulative reg to calculate Period Consumption Data - see step 3.4.1. This is the basis for the D0300 read dispute process for MHHS using only the cumulative. If the CoS read, which is provided to the incoming supplier in step 3.1.17 of BSCP701, is not the cumulative, then subsequent reads would probably fail tolerance checks. This would cause a D0300 issue. The 4 month settlement window means that this could cause unresolvable settlement imbalance. This is problematic for suppliers, as all our trad NHH sites are settled on the register read. A decision on how to proceed is needed. | REC notes that the MSAG solution document clarifies that the D0010 would be sent to the SDS for traditional meters (at register level) and the IF-041 would be sent for smart meters. The change introduced a new reading type value to identify where a read on a D0010 relates to an agreed CoS read, so these two mechanisms mean there is no requirement to send a D0300 to the SDS.
D0367 | Smart Meter Configuration Details | REC | D Flow Overview | British Gas | We remain concerned that this is being removed without a replacement DIP message - we have raised DIN-252 but now read from the DIN log that a CR is expected. | The IF-041 is agnostic of the configuration of the meter. The only time the configuration will be required is for trad meters where a D0149/D0150 is received outside of the DIP, and the reads would be sent on the D0010.
D0375 | Disconnected MSIDs and Estimated Half Hourly Demand Disconnection Volumes | BSC | Redundant post-MHHS | ESG Global | The notes column appears to contradict the specific comments which states it will be retained | This is probably semantics around use of "retained". A message in the structure of the D0375 will be retained from ESO to BSCCo, but as this SV is not defined in the EMDS, removing all the other SVs will mean the SVA uses of the flow will no longer exist.
D0379 | Half Hourly Advances UTC | BSC | Redundant post-MHHS | ESG Global | Does this not be x-referenced to the D0275 and therefore the rules applied to the D0275 should also be applicable to the D0379. | Yes, this has been called out in the slides for DAG, as our view is that either the D0275 or D0379 should be retained for optional use, rather than both.
D0396 | SIP Event Completed | REC | D Flow Overview | British Gas | Flow not included in the list. | Newly introduced flow - added to Overview / Enduring
Daaa-Dhhhh | Supplier Half Hourly Demand Report (MHHS) etc | BSC | D Flow Overview | British Gas | Don't think it is very helpful to put non-d flows here - suggest referring to the external or internal reports artefacts. In any case you've referred to these in the context of the d flow which was the intention of this document | Approach to be clarified at DAG. This is intentional as it is not correct to classify the old D-flow reports as being amended, which caused confusion and under-counting.

## General comments
Comment Area | Comment Action/Response
ECS Reports | ECS Reports are listed under their future names of Daaaa, Dbbbb, etc rather than as the flow they will replace, as this created ambiguity as to which tab they shoud sit on. The existing SVAA reports are listed on the 'Redundant post-MHHS' tab.
Optional HH consumption Dataflows | D0275 will be re-purposed for optional use under MHHS. Need DAG recommendation with regard to D0379 - a higher precision flow should be preferable as this aligns with the precision level of the IF-021.
Misalignment with previously published CCIAG documentation for REC Changes | Clarified that these documents have been superseded by outputs from the REC MSAG meeting on 15 June 2023, available on the REC Portal. (https://recportal.co.uk/web/msag/solution-documents)