## Comments
MHHS-DEL2878 - Non-SIT LDSO Test Data Approach & Plan Consultation Comments Log
*Organisation: |  |  | Please add your comments to the template below, ensuring that you fill all of the mandatory columns marked with an *. If you have no comments and want to confirm you have reviewed the document, please input 'Confirmed Reviewed' in the Comment box and 'n/a' for the remaining boxes. Where mandatory columns have not been filled, these comments may be rejected or the sender may be asked to provide more detail.
*Constituency:
*Comment Owner Anonymised:
*Date:
Comment ID | *Ref # | *Comment | *Suggested Change | *Impact of not making the Change | *Comment Owner | Programme Response
1 | 3 Objectives | This is regarding the non-functional and operational requirement. If due to some reason, we will utilise most of the test data in QT functional testing. Then in this case, what's the contingency planning to utilise the data in QT NFT and OT? | Provide proper contingency planning and use the lesson learnt from MHHS SIT. |  | Northern Powergrid | Functional Test Cases can be re-used for NFT and OT irrespective of data end state (for example change of status due to Functional Test Requirements) - No additional data/data amendments will be required to satisfy NFT/OT
2 | 3 Objectives | Can we use the leftover functional test data without tweaking them before utilise them in Non-functional and Operational testing? | Provide more clarity on the steps to utilise the functional test data without much effort. |  | Northern Powergrid | Functional Test Cases can be re-used for NFT and OT irrespective of data end state (for example change of status due to Functional Test Requirements) - No additional data/data amendments will be required to satisfy NFT/OT
3 | Section 3 "MPANs provided for Functional Testing will be re-used" | Define 're-used' if the MPAN has already changed status during Functional Testing then will the data be in the correct state to support additional NF and Operational testing. | Will further data conditioning be required or is the intention to run Functional and NF/Operational tests as part of the same test scripts/step? | Lack of clarity. Potential that data is not available for NF/Operational testing | Paul Band/ENWL | Functional Test Cases can be re-used for NFT and OT irrespective of data end state (for example change of status due to Functional Test Requirements) - No additional data/data amendments will be required to satisfy NFT/OT

## Validation (hidden)
Yes
No