## Schedule
March 2022 |  |  |  |  | April 2022 |  |  |  |  | May 2022 |  |  |  |  | June 2022
| Tue 1st | Wed 2nd | Thu 3rd | Fri 4th | Mon 4th | Tue 5th | Wed 6th | Thu 7th | Fri 8th | Mon 2nd | Tue 3rd | Wed 4th | Thu 5th | Fri 6th | Mon 6th | Tue 7th | Wed 8th | Thu 9th | Fri 10th
| Governance Meetings: | Governance Meetings: BPRWG | Governance Meetings: TDWG | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: DAG Papers Issued BPRWG | Governance Meetings: TDWG | Governance Meetings: |  | Governance Meetings: | Governance Meetings: DAG Papers Issued BPRWG | Governance Meetings: TDWG | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: DAG | Governance Meetings: | Governance Meetings:
| BPRWG Review: Tranche 1- 1st Review |  |  |  | BPRWG Review: Tranche 1- 2nd Comment Review |  |  |  |  | Bank Holiday | BPRWG Review: Tranche 2- 2nd Review |  |  |  | BPRWG Review: Tranche 3- 2nd Review
| Review Drop In Sessions |  |  |  | Tranche 2- 1st Review | [5 empty] | Tranche 3- 1st Review |  |  |  | Tranche 4- 1st Review
| Sub-Group Papers Issued: Elexon Central Systems | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: Data Service Requirements | Sub-Group Papers Issued: Elexon Central Systems | Sub-Group Papers Issued: Security | Sub-Group Papers Issued: TDWG | Sub-Group Papers Issued: |  | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: TDWG | Sub-Group Papers Issued:
| Sub-Group Meetings: | Sub-Group Meetings: PM: Security Working Group | Sub-Group Meetings: AM: Related MPANs PM: DNO Interactions PM: TDWG | Sub-Group Meetings: AM: Elexon Central Systems- VAS | Sub-Group Meetings: | Sub-Group Meetings: AM: Advanced PM: Unmetered | Sub-Group Meetings: | Sub-Group Meetings: AM: Data Service Requirements- Drop In Only PM: TDWG | Sub-Group Meetings: AM: Elexon Central Systems |  | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: PM: TDWG | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: PM: Security Working Group | Sub-Group Meetings: | Sub-Group Meetings:
Mon 7th | Tue 8th | Wed 9th | Thu 10h | Fri 11tth | Mon 11th | Tue 12th | Wed 13th | Thu 14th | Fri 15th | Mon 9th | Tue 10th | Wed 11th | Thu 12th | Fri 13th | Mon 13th | Tue 14th | Wed 15th | Thu 16th | Fri 17th
Governance Meetings: | Governance Meetings: | Governance Meetings: DAG | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: DAG | Governance Meetings: |  | Governance Meetings: | Governance Meetings: | Governance Meetings: DAG | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: DAG Papers Issued | Governance Meetings: | Governance Meetings:
BPRWG Review: Tranche 1- 1st Review | Tranche 1- 1st Comment Review |  |  |  | Tranche 1- 2nd Comment Review |  |  |  | Bank Holiday | BPRWG Review: Tranche 2- 2nd Review |  |  |  |  | BPRWG Review: Tranche 3- 2nd Comment Review/ Tranche 4- 1st Comment Review
[5 empty] | Tranche 2- 1st Review |  |  |  |  | Tranche 3- 1st Review
Sub-Group Papers Issued: | Sub-Group Papers Issued: Registration | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: Elexon Central Systems | Sub-Group Papers Issued: | Sub-Group Papers Issued: TDWG |  | Sub-Group Papers Issued: Registration Service Requirements | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: TDWG | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued:
Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: AM: Data Service Requirements- Drop In Only | Sub-Group Meetings: PM: Security Working Group | Sub-Group Meetings: |  | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: PM: Security Working Group | Sub-Group Meetings: AM: Registration Service Requirements- Drop In Only | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: PM: TDWG | Sub-Group Meetings:
Mon 14th | Tue 15th | Wed 16th | Thu 17th | Fri 18th | Mon 18th | Tue 19th | Wed 20th | Thu 21st | Fri 22nd | Mon 16th | Tue 17th | Wed 18th | Thu 19th | Fri 20th | Mon 20th | Tue 21st | Wed 22nd | Thu 23rd | Fri 24th
Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: |  | Governance Meetings: | Governance Meetings: DAG Papers Issued | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: DAG Papers Issued | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: DAG | Governance Meetings: | Governance Meetings:
BPRWG Review: Tranche 1- 2nd Comment Review |  |  |  |  | Bank Holiday | BPRWG Review: Tranche 2- 1st Comment Review |  |  |  | BPRWG Review: Tranche 2- 2nd Comment Review/ Tranche 3- 1st Comment Review |  |  |  |  | BPRWG Review: Tranche 4- 2nd Review
Sub-Group Papers Issued: | Sub-Group Papers Issued: Elexon Central Systems | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: |  | Sub-Group Papers Issued: Elexon Central Systems Metering Service Requirements Registration- Change of Segment | Sub-Group Papers Issued: Security | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: TDWG | Sub-Group Papers Issued:
Sub-Group Meetings: | Sub-Group Meetings: AM: Registration- Service Appointments | Sub-Group Meetings: | Sub-Group Meetings: AM: DNO/IDNO Interactions PM: TDWG | Sub-Group Meetings: AM: Elexon Central Systems- ISD |  | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: AM: Metering Service Requirements- Drop In Only PM: TDWG | Sub-Group Meetings: AM: Elexon Central Systems | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: AM: Registration Service Requirements- Drop In Only PM: TDWG | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings:
Mon 21st | Tue 22nd | Wed 23rd | Thu 24th | Fri 25th | Mon 25th | Tue 26th | Wed 27th | Thu 28th | Fri 29th | Mon 23rd | Tue 24th | Wed 25th | Thu 26th | Fri 27th | Mon 27th | Tue 28th | Wed 29th | Thu 30th
Governance Meetings: | Governance Meetings: | Governance Meetings: DAG | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: BPRWG Papers Issued DAG | Governance Meetings: TDWG Papers Issued | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: BPRWG Papers Issued DAG | Governance Meetings: TDWG Papers Issued | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings:
BPRWG Review: Tranche 1- 2nd Review |  |  |  |  | BPRWG Review: Tranche 2- 1st Comment Review |  |  |  |  | BPRWG Review: Tranche 2- 2nd Comment Review/ Tranche 3 1st Comment Review |  |  |  |  | BPRWG Review: Tranche 4- 2nd Review
Sub-Group Papers Issued: | Sub-Group Papers Issued: Elexon Central Systems Registration | Sub-Group Papers Issued: | Sub-Group Papers Issued: Metering Service | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: Elexon Central Systems | Sub-Group Papers Issued: | Sub-Group Papers Issued: TDWG | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued:
Sub-Group Meetings: | Sub-Group Meetings: AM: Registration- Service Appointments | Sub-Group Meetings: | Sub-Group Meetings: PM: TDWG | Sub-Group Meetings: AM: Elexon Central Systems- Reporting | Sub-Group Meetings: | Sub-Group Meetings: AM: Registration- Change of Segment | Sub-Group Meetings: PM: Security Working Group | Sub-Group Meetings: AM: Metering Service Requirements- Drop In Only | Sub-Group Meetings: AM: Elexon Central Systems | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: PM: Security Working Group | Sub-Group Meetings: TDWG | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings: PM: TDWG
Mon 28th | Tue 29th | Wed 30th | Thu 31st | Fri 1st | [5 empty] | Mon 30th | Tue 31st | Wed 1st | Thu 2nd | Fri 3rd
Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: | Governance Meetings: | [5 empty] | Governance Meetings: | Governance Meetings: | Governance Meetings: DAG Papers Issued BPRWG | Bank Holiday | Bank Holiday
BPRWG Review: Tranche 1- 2nd Review | [9 empty] | BPRWG Review: Tranche 3- 2nd Review
Tranche 4- 1st Review
Sub-Group Papers Issued: | Sub-Group Papers Issued: Elexon Central Systems Advanced Unmetered | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued: | [5 empty] | Sub-Group Papers Issued: | Sub-Group Papers Issued: | Sub-Group Papers Issued:
Sub-Group Meetings: | Sub-Group Meetings: AM: Registration- Service Appointments PM: DNO/IDNO Interactions | Sub-Group Meetings: PM: Security Working Group | Sub-Group Meetings: PM:Metering Service | Sub-Group Meetings: AM: Elexon Central Systems | [5 empty] | Sub-Group Meetings: | Sub-Group Meetings: | Sub-Group Meetings:
MHHSP - Working Group Schedule