## Slide 1: Minutes and Actions Review (1 of 2)
Ref | Date | Action | Owner | Due Date | Update
DAG06-01 | 09/03/2022 | Review alignment between related MPAN modifications and design subgroup | Programme (Ian Smith) | 27/04/2022 | ONGOING - Programme (Design Workstream) have reviewed internally and discussion to be held with DAG Member (CH) upon return from leave.
DAG07-03 | 23/03/2022 | Programme to bring future versions of DIP Functional Specification and Non-Functional Requirements to DAG, once further updates incorporated | Programme (Design Team) | 11/05/2022 | ONGOING – Documents issued ex-committee for comment following DAG on 11 May 2022. Updated version to be issued with June DAG post meeting papers.
DAG08-01 | 13/04/2022 | Bring updated DIP Functional Specification and Non-Functional Requirements to the next DAG for approval | Programme (Ian Smith) | 11/05/2022 | RECOMMEND CLOSED – see above ACTION DAG07-03.
DAG08-02 | 13/04/2022 | Issue call for agenda items or discussion topics prior to mobilisation of CCIAG | Programme (PMO) | 11/05/2022 | ONGOING - CCIAG Terms of Reference issued ex-committee for comment following DAG on 11 May 2022. Notice of group issued via The Clock and first meeting date to be scheduled. Call for discussion topics to be issued with notice of mobilisation of group.
DAG08-10 | 13/04/2022 | Bring design elements of RAID log for review at next meeting | Programme (PMO) | 11/05/2022 | RECOMMEND CLOSED - Programme RAID Manager attending DAG to provide overview. To be discussed under agenda item 8 of 08 June 2022 DAG meeting.
DAG09-01 | 11/05/2022 | Liaise with Programme SRO team to present information to DAG on the IPA work package related to the scope of independent assurance on Programme design work | Chair | 08/06/2022 | RECOMMEND CLOSED - MHHS IPA Baseline Assurance Health Check ToR published with DAG papers for 08 June 2022 meeting.
DAG09-02 | 11/05/2022 | Share list of the design document repository user group volunteers with DAG members | Programme (Paul Pettitt) | 18/05/2022 | RECOMMEND CLOSED – volunteers include three industry parties from data services and central systems organisations.
DAG09-03 | 11/05/2022 | Provide detailed action plan for resolution of open design issues against T1 design artefacts | Programme (Claire Silk) | 25/05/2022 | ONGOING - Status and next steps clarified for outstanding issues. Scheduling still in progress
DAG09-04 | 11/05/2022 | Produce guidance outlining how parties can engage with design artefact review process, including how issues can be raised | Programme (Claire Silk) | 25/05/2022 | RECOMMEND CLOSED - MHHS-DES06 Design Artefact Review Process published on MHHS Portal and communicated to Working Groups
Approval of Minutes from previous meeting held 11 May 2022
Outstanding actions:

## Slide 2: Minutes and Actions Review (2 of 2)
Ref | Date | Action | Owner | Due Date | Update
DAG09-05 | 11/05/2022 | Programme to liaise with Programme Participants who have queries on the Programme Design Team’s responses to comments on the Tranche 1 design artefacts | Programme (Ian Smith) | 08/06/2022 | ONGOING - Status and next steps clarified for outstanding issues. Scheduling still in progress
DAG09-06 | 11/05/2022 | Advise constituents who have expressed concerns on Programme responses to comments on Tranche 1 design artefacts to contact the Programme Design Team (Design@mhhsprogramme.co.uk) | DAG Members | 08/06/2022 | 
DAG09-07 | 11/05/2022 | Add dependency to outstanding design issues log to capture ongoing assessment of MDR TRT requirements in relation to SEC MP162 | Programme (Ian Smith) | 18/05/2022 | RECOMMEND CLOSED - Routing Matrix present on Dependencies List
DAG09-08 | 11/05/2022 | Add dependency to outstanding design issues log under routing to ensure other mechanisms for publishing data to other parties is captured | Programme (Ian Smith) | 18/05/2022 | RECOMMEND CLOSED - Routing Matrix present on Dependencies List
DAG09-09 | 11/05/2022 | Add dependency to outstanding design issues log regarding technical resolution of delivery of load shape data to non-DIP actors | Programme (Ian Smith) | 18/05/2022 | RECOMMEND CLOSED - Non-DIP recipients of LSS resolution on Dependencies List
DAG09-10 | 11/05/2022 | Add dependency to outstanding design issues log relating to ensuring design collateral is sufficient to enable code drafting. IS to review example of this and confirm sufficient for code drafting. | Programme (Ian Smith) | 08/06/2022 | ONGOING - Issue captured and prototyping to be scheduled
DAG09-11 | 11/05/2022 | Add dependency to outstanding design issues log regarding Programme approach to resolving material design issues which emanate from design assurance process. | Programme (Ian Smith) | 08/06/2022 | ONGOING - Approach to be communicated
DAG09-12 | 11/05/2022 | Provide a clear plan for the resolution of the recorded outstanding issues related to the Tranche 1 design artefact approval | Programme (Design Team) | 25/05/2022 | ONGOING - Status and next steps clarified for outstanding issues. Scheduling still in progress
DAG09-13 | 11/05/2022 | Consider whether further extraordinary DAG meeting required to discuss latest information relating to the Smart Energy Code (SEC) Modification Proposal (MP) 162 | Programme (Design Team) |  | ONGOING - have not identified a requirement at this point however recognise that this may materialise so will continue to assess
DAG09-14 | 11/05/2022 | Issue correspondence to DAG members seeking approval decisions on the latest Data Integration Platform (DIP) Functional Specification and Non-Functional Requirements document, and approval of the Consequential Change Implementation Advisory Group (CCIAG) draft Terms of Reference, and seeking comments on the code drafting principles provided by the Cross Code Advisory Group (CCAG) | Programme (PMO) | 13/05/2022 | RECOMMEND CLOSED - Correspondence issued to DAG members 13/05/2022.
DAG09-15 | 11/05/2022 | Review length forward DAG meetings to ensure sufficient time to discuss all agenda items | Programme (PMO) | 13/05/2022 | RECOMMEND CLOSED - Meeting durations reviewed and June/July meetings set at longer duration, commensurate to volume/importance of items to be discussed.