## PPIR Question List
Section | Question | Applicable for | Format
Section 1: Introduction
Introduction | Please confirm your organisations name. | Suppliers & Agents | Free text
| Please confirm your organisations MPID. | Suppliers & Agents | Free text
| Please confirm the name of the person completing the form. | Suppliers & Agents | Free text
| Please confirm the company email address of the person completing the form. | Suppliers & Agents | Free text
| Please share who the responsible Migration contact is in your organisation for ensuring all in scope MPANs are migrated my M15. | Suppliers & Agents | Free text
| Please share the email address of the responsible Migration contact in your organisation for ensuring all in scope MPANs are migrated my M15. | Suppliers & Agents | Free text
| Please confirm your organisations role. | Suppliers & Agents | Supplier or Agent
Section 2: Exclusions and Remediations
Issue 1: Traditional meters installed on CT connection types | Do you have any Traditional meters installed on a CT connection type within your Portfolio? | Suppliers | Y/N
| How many MPANs within your portfolio are currently affected by this issue? | Suppliers | Number
| Is remediator work currently underway? | Suppliers | Y/N
| How long do you anticipate this activity to take to complete? | Suppliers | Option list in months
| What is the target completion date for resolving affected MPANs for this issue? | Suppliers | Date range
| Do you have any constraints affecting the completion of this remediation activity ahead of your migration completion date?. If so, please provide detail. | Suppliers | Free text
Issue 2: Related MPANs with different meter types | Do you have any Related MPANs with different meter types within your Portfolio? | Suppliers | Y/N
| How many MPANs within your portfolio are currently affected by this issue? | Suppliers | Number
| Is remediator work currently underway? | Suppliers | Y/N
| How long do you anticipate this activity to take to complete? | Suppliers | Option list in months
| What is the target completion date for resolving affected MPANs for this issue? | Suppliers | Date range
| Do you have any constraints affecting the completion of this remediation activity ahead of your migration completion date?. If so, please provide detail. | Suppliers | Free text
Issue 3: Missing CSS Registration ID | Do you have any MPANs that currently do not have a CSS Registration ID populated within your portfolio? | Suppliers | Y/N
| How many MPANs within your portfolio are currently affected by this issue? | Suppliers | Number
| Is remediator work currently underway? | Suppliers | Y/N
| How long do you anticipate this activity to take to complete? | Suppliers | Option list in months
| What is the target completion date for resolving affected MPANs for this issue? | Suppliers | Date range
| Do you have any constraints affecting the completion of this remediation activity ahead of your migration completion date?. If so, please provide detail. | Suppliers | Free text
Issue 4: Missing Meter Data (Energised) within MPRS | Are you responsible for any (Energised) MPANs that has Missing Meter Data within MPRS? | Suppliers | Y/N
| How many MPANs within your portfolio are currently affected by this issue? | Suppliers | Number
| Is remediator work currently underway? | Suppliers | Y/N
| How long do you anticipate this activity to take to complete? | Suppliers | Option list in months
| What is the target completion date for resolving affected MPANs for this issue? | Suppliers | Date range
| Do you have any constraints affecting the completion of this remediation activity ahead of your migration completion date?. If so, please provide detail. | Suppliers | Free text
Issue 5: SMETS 1 FOC incorrectly configured | Do you have any SMETS 1 FOC meters within your portfolio that have not been successfully reconfigured by the DCC? | Suppliers | Y/N
| How many MPANs within your portfolio are currently affected by this issue? | Suppliers | Number
| Is remediator work currently underway? | Suppliers | Y/N
| How long do you anticipate this activity to take to complete? | Suppliers | Option list in months
| What is the target completion date for resolving affected MPANs for this issue? | Suppliers | Date range
| Do you have any constraints affecting the completion of this remediation activity ahead of your migration completion date?. If so, please provide detail. | Suppliers | Free text
Issue 6: CHECK meter types in MPRS | Are you responsible for any MPANs that have a meter type of CHECK in MPRS within your Portfolio? | Suppliers | Y/N
| How many MPANs within your portfolio are currently affected by this issue? | Suppliers | Number
| Is remediator work currently underway? | Suppliers | Y/N
| How long do you anticipate this activity to take to complete? | Suppliers | Option list in months
| What is the target completion date for resolving affected MPANs for this issue? | Suppliers | Date range
| Do you have any constraints affecting the completion of this remediation activity ahead of your migration completion date?. If so, please provide detail. | Suppliers | Free text
Issue 7: Smart meters and CT connection types | Do you have any Smart meters with a CT connection type within your Portfolio? | Suppliers | Y/N
| How many MPANs within your portfolio are currently affected by this issue? | Suppliers | Number
| Is remediator work currently underway? | Suppliers | Y/N
| How long do you anticipate this activity to take to complete? | Suppliers | Option list in months
| What is the target completion date for resolving affected MPANs for this issue? | Suppliers | Date range
| Do you have any constraints affecting the completion of this remediation activity ahead of your migration completion date?. If so, please provide detail. | Suppliers | Free text
Issue 8: Linked import and export MPANs with different connection types | Do you have any linked import and export MPANs that have different connection types within your Portfolio? | Suppliers | Y/N
| How many MPANs within your portfolio are currently affected by this issue? | Suppliers | Number
| Is remediator work currently underway? | Suppliers | Y/N
| How long do you anticipate this activity to take to complete? | Suppliers | Option list in months
| What is the target completion date for resolving affected MPANs for this issue? | Suppliers | Date range
| Do you have any constraints affecting the completion of this remediation activity ahead of your migration completion date?. If so, please provide detail. | Suppliers | Free text
Issue 9: Linked import and export MPANs with different meter groups | Do you have any linked import and export MPANs with different meter groups within your Portfolio? | Suppliers | Y/N
| How many MPANs within your portfolio are currently affected by this issue? | Suppliers | Number
| Is remediator work currently underway? | Suppliers | Y/N
| How long do you anticipate this activity to take to complete? | Suppliers | Option list in months
| What is the target completion date for resolving affected MPANs for this issue? | Suppliers | Date range
| Do you have any constraints affecting the completion of this remediation activity ahead of your migration completion date?. If so, please provide detail. | Suppliers | Free text
Issue 10: Related MPANs with different connection types | Do you have any Related MPANs with different connection types within your Portfolio? | Suppliers | Y/N
| How many MPANs within your portfolio are currently affected by this issue? | Suppliers | Number
| Is remediator work currently underway? | Suppliers | Y/N
| How long do you anticipate this activity to take to complete? | Suppliers | Option list in months
| What is the target completion date for resolving affected MPANs for this issue? | Suppliers | Date range
| Do you have any constraints affecting the completion of this remediation activity ahead of your migration completion date?. If so, please provide detail. | Suppliers | Free text
Issue 11: NHH unmetered MPAN | Do you have any NHH unmetered MPANs within your Portfolio? | Suppliers | Y/N
| How many MPANs within your portfolio are currently affected by this issue? | Suppliers | Number
| Is remediator work currently underway? | Suppliers | Y/N
| How long do you anticipate this activity to take to complete? | Suppliers | Option list in months
| What is the target completion date for resolving affected MPANs for this issue? | Suppliers | Date range
| Do you have any constraints affecting the completion of this remediation activity ahead of your migration completion date?. If so, please provide detail. | Suppliers | Free text
Issue 12: Domestic Unmetered MPANs | Do you have any unmetered MPANs with a DPI of True within your Portfolio? | Suppliers | Y/N
| How many MPANs within your portfolio are currently affected by this issue? | Suppliers | Number
| Is remediator work currently underway? | Suppliers | Y/N
| How long do you anticipate this activity to take to complete? | Suppliers | Option list in months
| What is the target completion date for resolving affected MPANs for this issue? | Suppliers | Date range
| Do you have any constraints affecting the completion of this remediation activity ahead of your migration completion date?. If so, please provide detail. | Suppliers | Free text
Issue 13: Linked & Related Import and Export MPANs with Export MPAN Missing meter data | Do you have any linked and related import and export where the Export MPAN is missing meter data within your Portfolio? | Suppliers | Y/N
| How many MPANs within your portfolio are currently affected by this issue? | Suppliers | Number
| Is remediator work currently underway? | Suppliers | Y/N
| How long do you anticipate this activity to take to complete? | Suppliers | Option list in months
| What is the target completion date for resolving affected MPANs for this issue? | Suppliers | Date range
| Do you have any constraints affecting the completion of this remediation activity ahead of your migration completion date?. If so, please provide detail. | Suppliers | Free text
Section 3: Trading Status of X
Trading Status of X | Do you currently have any MPANs within your portfolio that has a Trading Status of X? | Suppliers | Y/N
| How many MPANs with a Trading Status of X do you have within your portfolio? | Suppliers | Number
| Is remediator work currently underway? | Suppliers | Y/N
| How long do you anticipate this activity to take to complete? | Suppliers | Option list in months
| What is your target completion date to have de-registered the meter point or have the LDSO disconnect the status of MPANs with a Trading Status of X? | Suppliers | Date range
| Please self-declare your understanding that all MPANs with Trading Status's of R, T and X within your portfolio must be migrated by M15 (Full transition complete) to ensure compliance with your BSC Obligations. | Suppliers | Y/N
Section 4: Complex Sites
Complex Sites | Do you have complex sites, shared SVA metering arrangements, and private networks within your portfolio? | Suppliers & Agents | Y/N
| How many complex sites, shared SVA metering arrangements and private networks are you currently responsible for? | Suppliers & Agents | Number
Closing Question
Closing Question | Are there any additional issue that you are aware of that will impact a MPANs successful Migration that the Programme is not presently reporting against? If yes, please provide detail and also quantify the issue. | Suppliers & Agents | Free text

## Exclusions & Remediation List
ID | Issue Type | MPAN Volume | Description | Migration Status | Migration Commentary | Remedial Action | Industry Owner (Responsible Party) | Responsible Code (Change) | Current Status | Target Date | RAID Item | Code Change
1 | Traditional meters installed on CT connection types |  | The design does not support traditional meters installed on CT connections. Migration should not be attempted for these specific MPANs until this issue is resolved. The traditional meter should be exchanged for an advanced meter prior to migration; or, if the meter cannot be exchanged the MPAN should not be migrated until a BSC change to support this scenario is implemented. | Blocked | 1.b Pot Unmigratable without change due to design. Only Blocked if you intend to migrate the traditional CT meter | 1a. Supplier and MOP identify MPANs with a traditional meter on a CT connection and replace that meter for an advanced meter; or | 1a. Supplier | BSC | In Progress |  | i217 | YES
[6 empty] | 1b. Supplier and MOP follow process set out within BSC change xxxx (when implemented); or | 1b. Supplier & MOP | BSC | Blocked | 2026-06-26
|  | 6000 |  |  |  | 1c. Supplier and MOP determine that connection is not CT and request LDSO amend the connection type to W | 1c. Supplier & MOP & LDSO | BSC | In Progress
[6 empty] | 2. Following 1a or b MOP sends correct D0312 to MPRS | 2. Supplier & MOP | REC | In Progress
[6 empty] | 3. Following 1c LDSO sends DB02 to MPRS, MPRS will re-evaluate the market segment from advanced to smart | 3. LDSO | BSC | In Progress
[6 empty] | 4. Supplier can migrate the MPAN once correction made. | 4. Supplier |  | Partially Blocked | 2026-06-26
2 | Related MPANs with different meter types |  | Related MPANs with different meter groups which create different market segments (e.g. smart and advanced) will cause exceptions if the MPAN migration is attempted. The design doesn’t support related MPANs with two different market segments. | Partially Blocked | Trad CT scenario of related are currently UNMIGRATABLE in current stage blocked until code change implemented. Remaining scenarios defer until cleansing activity has been completed |  |  |  | In Progress |  | i234 | YES
|  | 8400 |  |  |  | 1. Supplier unrelates MPANs if relationship not required for billing purposes, by sending the D0386; or | 1. Supplier | REC
[6 empty] | 2. If required for billing purposes; Supplier must not migrate until: | 2. Supplier | REC | In Progress
[6 empty] | 3. Meter exchanges are completed to align the meter group across all MPANs; or | 3. Supplier | REC | In Progress
[6 empty] | 4. Industry change to MHHS design implemented to support different meter groups. | 4. Code Body | BSC | Blocked | 2026-06-26
[6 empty] | 5. Supplier can migrate MPAN following step 1, 3 or 4. | 5. Supplier |  | Partially Blocked | 2026-06-26
3 | CSS Registration ID | TBC | If Registration ID is not populated within the IF-031, the message will be rejected by the Registration Service. There is a potential issue that suppliers do not have complete Registration ID records. A conflict currently exists between the Registration Service functionality and the baselined design / codes. | Defer | Unmigratable in current stage. Defer until cleansing activity has been completed | 1. Supplier to populate CSS RegistrationID | 1. Supplier | REC | In Progress |  | R1198 | YES
[6 empty] | 2. Migrate MPAN | 2. Supplier |  | In Progress
4 | Missing Meter Data (Energised) within MPRS |  | MPANs which do not have meter data populated within MPRS at the point of market segment population in September 2025 will be set to a market segment of advanced. In many instances a smart meter is installed on this site, unless the correct meter data is populated by the MOP in MPRS only advanced agents could be appointed when the MPAN is migrated. The Supplier should not attempt migration until the correct data is populated via the D0312 flow. | Defer | Possible to migrate, however it would have to be migrated within the Advanced segment. If this is incorrect, Supplier would be required to complete a change of segment | 1. Supplier and MOP identity MPANs with missing meter data within MPRS. Utilising the REC performance assurance reporting and EES reporting. | 1. Supplier | REC | In Progress |  | i145 | NO
|  | 17000 |  |  |  | 2. MOP sends correct D0312 to MPRS. | 2. Supplier | REC | In Progress
[6 empty] | 3. If the D0312 meter type is smart or traditional MPRS will re-evaluate the market segment from advanced to smart. | 3. LDSO (automated process) | REC | In Progress
[6 empty] | 4. Supplier can migrate the MPAN once correction made. | 4. Supplier |  | In Progress
5 | SMETS 1 FOC incorrectly configured | c. 2,300,000 | SMETS1 meters impacted by the incorrect recording of HH interval data | Defer | Possible to migrated however the HH settlement data may be incorrect | 1. DCC to implement a fix to allow the reconfiguring of the SMETS1 Meters to resolve the identified issue to ensure all consumption data retrieved from these meters is accurate. | 1. DCC | SEC | DONE | 2026-01-12 | R1201 | NO
[6 empty] | 2. Suppliers to work with MOPs to resolve non communicated MPANs and to then Migrate once fix has been applied | 2. Supplier |  | In Progress
6 | CHECK meter types in MPRS | 50 | MOPs should not send CHECK meters within a D0312 to MPRS. CHECK meters are not supported within the design and will cause migrations to fail if attempted. CHECK meters will need to be removed via the D0312 prior to that MPAN being migrated. | Defer | Unmigratable in current stage. Defer until cleansing activity has been completed | 1. MOP removes CHECK meter from MPRS via D0312. | 1. Supplier | REC | In Progress |  | i230 | NO
[6 empty] | 2. Supplier can initiate migration for MPAN once correction made | 2. Supplier |  | In Progress
7 | Smart meters and CT connection types |  | It is not possible for smart meters to be installed on CT connection types, so a clear data quality issue exists. These MPANs will not migrate successfully and will cause exceptions if migration is attempted before they are fixed. | Defer | Unmigratable in current stage. Defer until cleansing activity has been completed | 1. Supplier checks that smart meter installation is valid, if valid 2, if not valid 3 | 1. Supplier | REC | In Progress |  | i231 | NO
[6 empty] | 2. Supplier raises a request with the LDSO to correct connection type to WC. | 2. Supplier | BSC | In Progress
|  | 600 |  |  |  | 3. MOP correct meter type to valid value which is supported by CT connection type and send new D0312. | 3. Supplier | REC | In Progress
[6 empty] | 4. Supplier can initiate migration for MPAN once correction made | 4. Supplier |  | In Progress
8 | Linked import and export MPANs with different connection types | 2000 | The design doesn’t support linked MPANs within different market segments. Exceptions will be created preventing the successful migration of an MPAN if attempted. The data misalignment should be resolved if the linkage is correct, or the linkage should be removed if the data for the respective MPANs is correct. | Defer | Unmigratable in current stage. Defer until cleansing activity has been completed | 1. LDSO check the connection types and amends if incorrect or de-links the MPANs if correct. | 1. LDSO | BSC | In Progress |  | i232 | NO
[6 empty] | 2. Supplier can then migrate the MPAN | 2. Supplier | BSC | In Progress
9 | Linked import and export MPANs with different meter groups | 330 | The design doesn’t support linked MPANs within different market segments. Exceptions will be created preventing the successful migration of an MPAN if attempted. The data misalignment should be resolved if the linkage is correct, or the linkage should be removed if the data for the respective MPANs is correct. | Defer | Unmigratable in current stage. Defer until cleansing activity has been completed | 1. Supplier investigates the linked MPANs and changes the meter type if incorrect, if the other MPAN is with another Supplier and that Suppliers meter type is incorrect then they should raise an SDEP to that Supplier to update; or | 1. Supplier | BSC | In Progress |  | i218 | NO
[6 empty] | 2. Supplier believes the MPANs should not be linked and requests, via SDEP, that the LDSO de-links them. | 2. Supplier | BSC | In Progress
[6 empty] | 3. Following 1 or 2 completion the MPAN can be migrated. | 3. Supplier | BSC | In Progress
10 | Related MPANs with different connection types |  | Related MPANs with different connection types will cause exceptions if the MPAN migration is attempted. The design doesn’t support related MPANs with two different market segments. | Defer | Unmigratable in current stage. Defer until cleansing activity has been completed | 1. LDSO investigates exceptions and corrects connection type if incorrect, or | 1. LDSO | BSC | In Progress |  | i233 | NO
|  | 300 |  |  |  | 2. LDSO raises SDEP and instructs the Supplier to unrelate | 2. LDSO | REC | In Progress
[6 empty] | 3. Supplier unrelates if instructed to by LDSO, by sending the D0386 | 3. Supplier | REC | In Progress
[6 empty] | 4. Supplier can migrate MPAN following step 1 or step 3. | 4. Supplier |  | In Progress
11 | NHH unmetered MPAN | 2500 | NHH MPANs cannot be migrated to MHHS, only HH MPANs can be migrated. | Defer | Unmigratable in current stage. Defer until P434 Obligation has completed | 1. Change measurement class of MPAN from NHH to HH. | 1. Supplier | BSC | In Progress |  | R897 | NO
[6 empty] | 2. De-register any secondary unmetered MPANs | 2. Supplier |  | In Progress
[6 empty] | 3. Migrate MPAN | 2. Supplier | BSC | In Progress
12 | Domestic Unmetered MPANs | 50 | ~50 MPANs impacted | Defer | Unmigratable in current stage. Defer until cleansing activity has been completed | 1. Change DPI to Non-Domestic as per process set out in REC | 1. Supplier | REC | In Progress |  | i224 | NO
|  |  | Domestic Unmetered MPANs cannot be migrated to MHHS. |  |  | 2. Migrate MPAN | 2. Supplier |  | In Progress
13 | Linked & Related Import and Export MPANs with Export MPAN Missing meter data | TBC | MPANs which do not have meter data populated within MPRS at the point of market segment population in September 2025 will be set to a market segment of advanced. In the instance of linked or related Import and Export MPANs where the Export MPAN is missing meter data, the Export MPAN will default to the Advanced segment. This will result in the Import MPAN also defaulting to advanced even if it is correctly set to Smart. | Defer | Possible to migrate, however should the segment incorrectly default it would cause significant operational intervention to resolve within the MHHS arrange | 1. Solution to be discussed at MHHS Expert Group | 1. Supplier | BSC | In Progress |  |  | TBC