## Cover Sheet
LDSO QT - Test Cases
Version | Description | Author | Status | Date
1 | Start Test Cases | Non SIT QT Team |  | 2024-02-12
2 | Test Lead Review | Non SIT QT Team |  | 2024-02-21
3 | Review Comments Incorporated | Non SIT QT Team |  | 2024-02-26
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## BP002_TestScenarios
Test Scenario ID | LDSO Role (s) | Theme | Business Process | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scenarios Size) | Priority
TS_BP002_01 | Registration Service | MPAN Ownership | BP002 Change of Service - Metering Service | Validate that the Registration Service issues response to an Initial 'Metering Service Appointment' Request | In this scenario a Supplier (Test Harness) is generating an initial Metering Service appointment request to the Registration Service who will receive, process, validate and update their records accordingly and issue a response, accepted or rejected, back to the Supplier (Test Harness). | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Supplier (Test Harness) generating the initial Metering Service appointment request to the Registration Service. End Point The end point will be the Supplier (Test Harness) receiving the response to the request. | For Metered Supply: • Where the Supplier has initiated the request for Change of Service Provider (CSP) process for Segment S (Smart), Accepted request and Related MPAN • Where the Supplier has initiated the request for Change of Segment (SEG) process (Segment changed from X-> Y (Advanced to Smart), Accepted request and Linked Import/Export MPAN • Rejection reasons: Change of Service Provider (CSP) for a Segment S and Single MPAN |  | 3 | H | VH
TS_BP002_02 | Registration Service/UMSO | MPAN Ownership | BP002 Change of Service - Metering Service | Unmetered Supply - Validate that Registration Service sends a valid request for Metering Service appointment to the new UMSO service and the UMSO service verifies appointment request and responds back with the Metering Service proposed Appointment response to Registration Service | In this scenario, Registration Service sending the Metering Service appointment request to UMSO service and UMSO service receives and validates the request and sends a response back to the registration service for valid requests. Registration Service validates and maintains Reponses in the background until they are confirmed as live appointments. | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the registration service sending the valid only MS proposed requests to the UMSO. End Point The end point will be the UMSO service receiving the outcomes of the request. | For Unmetered Supply: • If the appointment request is valid and correct, UMSO will accept the appointment request for Segment U and Single MPAN • If the appointment request is invalid the UMSO will reject the appointment and apply the relevant rejection reason and send all responses back to the Registration Service for Segment U and Single MPAN |  | 2 | M | VH
TS_BP002_03 | Registration Service/UMSO | MPAN Ownership | BP002 Change of Service - Metering Service | Unmetered Supply - Validate that the Registration Service is sending the Metering Service Appointment Notification to UMSO, EES (Test Harness) and Data Service (Test Harness) | In this scenario, the Registration Service is generating an appointment notification to the UMSO, EES (Test Harness) and Data Service (Test Harness) The Registration Service will process the "On the day" and "Retro" appointments and for "Prospective" appointments the Registration Service will process and validate Prospective Metering Service appointments held in a queue . For valid Metering Service appointments, the Prospective Appointment confirmed as Effective will be sent to UMSO to process and update their records accordingly. EES and Data Service simulated by Test Harness will receive appointment notification for validation as per agreed validation rules. (Prospective route- CSS validation mechanism to be confirmed) | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be management of accepted appointment responses . End Point The end point will be the UMSO receiving the information about the appointment and updating their records accordingly. EES (Test Harness) and Data Service (Test Harness) will receive and validate the message. | For Unmetered Supply: • Where the "On the day" appointment date (Service Appointment start date = processing date AND existing supplier = requesting supplier) occurs for: Segment U (UMSO) for Change of Supply (COS) • Where the "Retro" appointment date (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier) occurs for: Segment U (UMSO) for Change of Supply (COS) • Where the "Prospective" appointment date (any future date) occurs for: Segment U (UMSO) for Change of Supply (COS) |  | 3 | VH | VH
TS_BP002_04 | Registration Service/LDSO | MPAN Ownership | BP002 Change of Service - Metering Service | Metered Supply - Validate that the Registration Service is sending the Metering Service Appointment Notification & MTDs (Meter Technical Details) to LDSO, Metering Service (Test Harness), EES (Test Harness), Data Service (Test Harness) and Supplier (Test Harness) | In this scenario, the Registration Service is generating an appointment notification & MTDs (Meter Technical Details) to LDSO, Metering Service (Test Harness), EES (Test Harness) and Data Service (Test Harness) The Registration Service will process the "On the day" and "Retro" appointments and for "Prospective" appointments, the Registration Service will process and validate Prospective Metering Service appointments held in a queue. For valid Metering Service appointments, the Prospective Appointment confirmed as Effective and MTD (Meter Technical Details) will be sent to LDSO service to process and update their records accordingly. Metering Service (Test Harness), EES (Test Harness), Data Service (Test Harness) and Supplier (Test Harness) will receive and validate the message. (Prospective route- CSS validation mechanism to be confirmed) | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be management of Prospective Service Provider appointment responses event. End Point The end point will be the LDSO receiving the information about the appointment of the Metering Service and MTD and to update their records accordingly. Metering Service (Test Harness), EES (Test Harness), Data Service (Test Harness) and Supplier (Test Harness) will receive and validate the message. | For Metered Supply: • Where the "On the day" appointment date (Service Appointment start date = processing date AND existing supplier = requesting supplier) occurs for: Segment A (Advanced) for Change of Supply (COS) with Single MPAN • Where the "Retro" appointment date (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier) occurs for: Segment S (Smart) for Change of Supply (COS) with Single MPAN • Where the "On the day" appointment date (Service Appointment start date = processing date AND existing supplier = requesting supplier) occurs for: Segment A (Advanced) for Change of Supply (COS) for Related MPAN • Where the "Prospective" appointment date (any future date) occurs for: Segment A (Advanced) for Change of Supply (COS) with Related MPAN • Where the "Prospective" appointment date (any future date) occurs for: Segment S (Smart) for Change of Supply (COS) for Linked Import/Export MPAN |  | 5 | VH | VH
TS_BP002_05 | Registration Service/LDSO | MPAN Ownership | BP002 Change of Service - Metering Service | Validate that the Registration Service will issue a de-appointment notification to LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness) | In this scenario, Registration Service will issue a de-appointment notification to LDSO The Registration Service will process the "On the day" and "Retro" appointments and for "Prospective" appointments, the Registration Service will process and validate Prospective Metering Service appointments held in a queue. For valid Metering Service appointments, Registration Service will issue a de-appointment notification to LDSO Service to process and update their records accordingly. The Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness) will receive and validate the message. (Prospective route- CSS validation mechanism to be confirmed) | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be management of accepted appointment responses End Point The end point will be the LDSO receiving the information about the de- appointment of the metering service and to update their records accordingly. Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness) will receive and validate the message. | For Metered Supply: • Where the "On the day" appointment date (Service Appointment start date = processing date AND existing supplier = requesting supplier) occurs for: Segment A (Advanced) for Change of Supply (COS) with single MPAN • Where the "Retro" appointment date (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier) occurs for: Segment S (Smart) for Change of Supply (COS) with Single MPAN • Where the "On the day" appointment date (Service Appointment start date = processing date AND existing supplier = requesting supplier) occurs for: Segment A (Advanced) for Change of Service Provider (CSP) for Related MPAN • Where the "Prospective" appointment date (any future date) occurs for: Segment A (Advanced) for Change of Supply (COS) with Related MPAN • Where the "Prospective" appointment date (any future date) occurs for: Segment S (Smart) for Change of Supply (COS) for Linked Import/Export MPAN |  | 5 | VH | VH
TS_BP002_06 | Registration Service/UMSO | MPAN Ownership | BP002 Change of Service - Metering Service | Validate that the Registration Service publishes a Registration Service Appointment Status Notification to UMSO (for Unmetered Supply only), Metering Service (Test Harness) & Supplier (Test Harness) where the proposed Metering Service appointment has lapsed | In this scenario the Registration Service is generating a Registration Service Appointment Status Notification to UMSO (for Unmetered Supply only), New Metering service (Test Harness) and Supplier (Test Harness) for lapsed prospective appointments. The test harness will receive and validate the message. | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be management of accepted appointment responses End Point The end point will be the UMSO (for Unmetered Supply only), New Metering Service (Test Harness) and Supplier (Test Harness) receiving the information about the lapsed appointment. The test harness will receive and validate the message. | • Where the "Prospective" appointment date has lapsed (Appointment Start Date is less than, greater than or equal to the Supply End Date) occurs for Segment U (UMSO) for Change of Supply (COS) that results in Lapsed outcome (MSAppLapsed) • Where the "Prospective" appointment date has lapsed (Appointment Start Date is less than, greater than or equal to the Supply End Date) occurs for Segment S (Smart) with Linked MPAN for Change of Supply (COS) that results in Lapsed outcome (MSAppLapsed) • Where the "Prospective" appointment date has lapsed (Appointment Start Date is less than, greater than or equal to the Supply End Date) occurs for Segment A (Advanced) with Related MPAN for Change of Supply (COS) that results in Lapsed outcome (MSAppLapsed) |  | 3 | VH | VH
TS_BP002_07 | Registration Service | MPAN Ownership | BP002 Change of Service - Metering Service | Validate that the Registration Service issues De-Appointment Notification to Metering Service (Test Harness) and Incumbent Supplier (Test Harness) for • Linked MPAN • Related MPAN | In this scenario the Registration Service publishing a Metering Service Notification of Service De-appointment to Metering Service (Test Harness) and Incumbent Supplier (Test Harness) for • Linked export MPANs • Linked related MPANs The Registration Service will process the "On the day" and "Retro" appointments and for "Prospective" appointments, the Registration Service will process and validate Prospective Metering Service appointments held in a queue. For valid Metering Service appointments, Registration Service will issue a de-appointment notification message to the Metering Service (Test Harness) and Incumbent Supplier (Test Harness) will receive and validate the message as per the validation rules. (Prospective route- CSS validation mechanism to be confirmed) | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be management of Prospective Service Provider appointment responses event. End Point The ending point will be to Metering Service (Test Harness) and Incumbent Supplier (Test Harness) receiving the information about the de- appointment. The test harness will receive and validate the message. | For Metered Supply: • Where the "On the day" appointment date (Service Appointment start date = processing date AND existing supplier = requesting supplier) occurs for Segment S for Change of Supply (COS) with : - Linked MPANs - Related MPANs • Where the "Retro" appointment date (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier) occurs for Segment A (Advanced) for Change of Supply (COS) with : - Linked MPANs - Related MPANs • Where the "Prospective" appointment date (any future date) occurs for Segment S (Smart) for Change of Supply (COS) with : - Linked MPANs - Related MPANs |  | 6 | VH | VH
TS_BP002_08 | Registration Service | MPAN Ownership | BP002 Change of Service - Metering Service | Validate that the Registration Service issues Appointment Notification to Metering Service (Test Harness) and Supplier (Test Harness) for Linked and Related MPANs | In this scenario the Registration Service is generating a "Appointment Notification for linked and related" MPANs to Metering Service (Test Harness). The Registration Service will process the "On the day" and "Retro" appointments and for "Prospective" appointments, the Registration Service will process and validate Prospective Metering Service appointments held in a queue. For valid Metering Service appointments, the Registration Service issues Appointment Notification for Linked and Related MPAN to The Metering Service (Test Harness) and Incumbent Supplier (Test Harness) will receive and validate the message as per the validation rules. (Prospective route- CSS validation mechanism to be confirmed) | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be management of Prospective Service Provider appointment responses event. End point The end point will be Metering Service (Test Harness) and Supplier (Test Harness) receiving the appointment notification. The test harness will receive and validate the message. | For Metered Supply: • Where the "On the day" appointment date (Service Appointment start date = processing date AND existing supplier = requesting supplier) occurs for Segment S for Change of Supply (COS) with : - Linked MPANs - Related MPANs • Where the "Retro" appointment date (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier) occurs for Segment A (Advanced) for Change of Supply (COS) with : - Linked MPANs - Related MPANs • Where the "Prospective" appointment date (any future date) occurs for Segment S (Smart) for Change of Supply (COS) with : - Linked MPANs - Related MPANs |  | 6 | VH | VH
TS_BP002_09 | Registration Service | MPAN Ownership | BP002 Change of Service - Metering Service | Validate that the Registration Service issue Registration Service Appointment Status Notification to Old Metering Service (Test Harness) for Traditional/Advanced Meters | In this scenario, the Registration Service is issuing Registration Service Appointment Status Notification to Old Metering Service (Test Harness) The Registration Service will publish a Registration Service Appointment Status Notification to the Old Metering Service (Test Harness) confirming the Metering Service request has been accepted for a Traditional or Advanced Meter. The Metering Service (Test Harness) will receive and validate the message as per the validation rules. | The boundaries for this scenario are as follows: Start Point Registration service receiving the Accepted MS Appointment Reponses. End Point The end point will be Metering Service (Test Harness) receiving the Registration Service Appointment Status Notification. The test harness will receive and validate the message. | For Metered Supply: • Where the metering service is for Segment S (Traditional Meter) and Linked Import/Export MPAN for COS (Change of Supply) with an Accepted outcome • Where the metering service is for Segment A (Advanced Meter) and Related MPAN for COS (Change of Supply) with an Accepted outcome |  | 2 | VH | VH
TS_BP002_10 | Registration Service/UMSO | MPAN Ownership | BP002 Change of Service - Metering Service | Validate that the Registration Service issue Registration Service Appointment Status Notification to UMSO (for Unmetered Supply only), Metering Service (Test Harness for Metered Supply only) and Supplier (Test Harness) irrespective of being Accepted/Rejected | In this scenario, the Registration Service is issuing Registration Service Appointment Status Notification to UMSO (for Unmetered Supply only), Metering Service (Test Harness for Metered Supply only) and Supplier (Test Harness) irrespective of being Accepted/Rejected The Registration Service will publish Registration Service Appointment Status Notification to UMSO (for Unmetered Supply only), Metering Service (Test Harness for Metered Supply only) and Supplier (Test Harness) irrespective of being Accepted/Rejected. The Metering Service (Test Harness) and Supplier (Test Harness) will receive and validate the message as per the validation rules. | The boundaries for this scenario are as follows: Start Point Registration service receiving the outcome of the MS Appointment Request. End Point The end point will be to UMSO (for unmetered supply), Metering Service (Test Harness) and Supplier (Test Harness) receiving the Registration Service Appointment Status Notification. The test harness will receive and validate the message. | For Unmetered Supply: • Where the metering service is for Segment U (UMSO) for COS (Change of Supply) with an Accepted response • Where the metering service is for Segment U (UMSO) for COS (Change of Supply) with Rejected response For Metered Supply: • Where the metering service is for Segment S (Traditional Meter) and Linked Import/Export MPAN for COS (Change of Supply) with an Accepted response • Where the metering service is for Segment A (Advanced Meter) and Related MPAN for COS (Change of Supply) with Rejected response |  | 4 | VH | VH
TS_BP002_11 | Registration Service | MPAN Ownership | BP002 Change of Service - Metering Service | Metered Supply: Validate that the Registration Service sends a valid request for Metering Service Appointment to the New Metering Service (Test Harness) | In this scenario Registration Service is sending the Metering Service Appointment Request with the specified Domestic Indicator. The test harness simulating the New Metering Service will receive and validate the message as per agreed validation rules. The harness will generate a message for the proposed Metering Service Appointment Request back to the Registration Service. | The boundaries for this scenario are as follows Starting point The starting point for this scenario will be the Registration Service sending the valid only "MS Proposed Requests" to the New Metering Service (test harness). End point The ending point will be the Registration Service receiving the outcomes of the request. | • Where Domestic premise indicator is True (domestic). (1) (COS) Change of Supplier process, Segment S (Smart), Accepted request and single MPAN. (2) (SEG) Change of segment process, Segment A (Advanced), Accepted request and linked related MPANs. (3) (COS) New Connection process for Segment S, Accepted request and linked import/export MPANs. • Where Domestic premise indicators is False (non- domestic). (4) (CSP) Change of service provider process, Segment A (Advanced), Accepted request, single MPAN. • Where the outcome is rejected. (5) Rejection reasons: COS for a Segment S and single MPAN. |  | 5 | VH | VH

## TC_BP002_05_01
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP002_05_01 | Registration services sending De-Appointment Notification to the LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness) | TS_BP002_05 | • Segment A • Single MPAN • "On the Day" processing. Where Service Appointment start date = processing date AND existing supplier = requesting supplier Pre requisites IF-031 with the following characteristics • (DI-999) Event Code = [MSApp] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed MS Effective From Date" = (as per the condition for "On the Day" processing) IF-032 accepted response (response to IF-031) with the following characteristics • (DI-999) Event Code = [MSAppInitialResp] • (DI-979) Response Code = A (Accept) IF-033 with the following characteristics • (DI-999) Event Code = [MSAppSPRequest] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed MS Effective From Date" = (as per the condition for "On the Day" processing) • (DI-979) Response Code = A (Accept) IF-034 accepted response (response to IF-033) with the following characteristics • (DI-999) Event Code = [MSAppSPResponse] • (DI-979) Response Code = A (Accept) Test data The "IF-037 Notification of Service De-Appointment" from the Registration Services to the LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness) with the following characteristics: • (DI-999) Event Code = [MSDeApp] • (DI-819) De-Appointment Reason Code = CSUPP (Change of Supply) | The "IF-037 Notification of Service De-Appointment" from the Registration services sending to the LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness)
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP002 - Step 100 | MHHS-BR-RS-020 (On the day) MHHS-BR-RS-023 (On the day) | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must, in cases where the proposed Metering Service appointment is accepted, determine the processing path to be followed: • "On the day" (Service Appointment start date = processing date AND existing supplier = requesting supplier ) Registration Service must process "On the day" Metering Service appointments as soon as they are identified ie should not be held in the queue, for any longer than is necessary, ahead of the CSS COS secured notifications being received. | Y | Registration Services taking the data through the "On the Day" processing route
2 | BP002 - Step 130 | MHHS-BR-RS-030 MHHS-BR-RS-031 MHHS-BR-RS-033.1 | Registration Service | DIP | IF-037 | Registration Service sends "IF-037" to the DIP Registration Service must publish a Registration Service Notification of Service De-appointment using the appropriate interface on the Data Integration Platform where the end date for the incumbent Metering Service has been confirmed by a CSS secured notification. Registration Service must publish a Registration Service Notification of Service De-appointment using the appropriate interface on the Data Integration Platform where a Change of Metering Service only appointment is confirmed | Y | Registration Services sending the IF-037 to the DIP
3 | BP002 - Step 140 & Step 145 | MHHS-BR-LD-002 | DIP | LDSO | PUB-037 | DIP sending PUB-037 to LDSO LDSO must obtain Data Service de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. In the case where Related MPANs or Import/Export linked MPANs exist, for the Advanced and UMS Market Segments, LDSO should expect to receive de-appointment notifications for all the MPANs in the Related MPAN or Import/Export group. | Y | DIP sending PUB-037 to LDSO LDSO obtaining all recored as defined by the the requirment (MHHS-BR-LD-004) and updating their records accordingly
4 | BP002 - Step 140, Step 150, Step 231 & Step 146 | MHHS-BR-MS-005 | DIP | Supplier(Outgoing/Incumbant) (Test Harness) Old Metering Service (Test Harness) EES (Test Harness) | PUB-037 | DIP sends PUB-037 to Supplier(Outgoing/Incumbant) (Test Harness), Old Metering Service (Test Harness) and EES (Test Harness). | N | DIP sending PUB-037 to Supplier(Outgoing/Incumbant) (Test Harness), Old Metering Service (Test Harness) and EES (Test Harness).

## TC_BP002_05_02
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP002_05_02 | Registration services sending De-Appointment Notification to the LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness) | TS_BP002_05 | • Segment S • Single MPAN • "Retro" processing. Where Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier Pre requisites. IF-031 with the following characteristics • (DI-999) Event Code = [MSApp] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed MS Effective From Date" = (as per the condition for "Retro" processing) IF-032 accepted response (response to IF-031) with the following characteristics • (DI-999) Event Code = [MSAppInitialResp] • (DI-979) Response Code = A (Accept) IF-033 with the following characteristics • (DI-999) Event Code = [MSAppSPRequest] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed MS Effective From Date" = (as per the condition for "Retro" processing) • (DI-979) Response Code = A (Accept) IF-034 accepted response (response to IF-033) with the following characteristics • (DI-999) Event Code = [MSAppSPResponse] • (DI-979) Response Code = A (Accept) Test data The "IF-037 Notification of Service De-Appointment" from the Registration Services to the LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness) with the following characteristics: • (DI-999) Event Code = [MSDeApp] • (DI-819) De-Appointment Reason Code = CSUPP (Change of Supply) | The "IF-037 Notification of Service De-Appointment" from the Registration services sending to the LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness)
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP002 - Step 100 | MHHS-BR-RS-020 (Retro) MHHS-BR-RS-023 (Retro) | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must, in cases where the proposed Metering Service appointment is accepted, determine the processing path to be followed: • "Retro" (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier ) Registration Service must process "Retro" Data Service appointments as soon as they are identified ie should not be held in the queue, for any longer than is necessary, ahead of the CSS COS secured notifications being received. | Y | Registration Services taking the data through the "Retro" processing route
2 | BP002 - Step 130 | MHHS-BR-RS-030 MHHS-BR-RS-031 MHHS-BR-RS-033.1 | Registration Service | DIP | IF-037 | Registration Service sends "IF-037" to the DIP Registration Service must publish a Registration Service Notification of Service De-appointment using the appropriate interface on the Data Integration Platform where the end date for the incumbent Metering Service has been confirmed by a CSS secured notification. Registration Service must publish a Registration Service Notification of Service De-appointment using the appropriate interface on the Data Integration Platform where a Change of Metering Service only appointment is confirmed | Y | Registration Services sending the IF-037 to the DIP
3 | BP002 - Step 140 & Step 145 | MHHS-BR-LD-002 | DIP | LDSO | PUB-037 | DIP sending PUB-037 to LDSO LDSO must obtain Data Service de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. In the case where Related MPANs or Import/Export linked MPANs exist, for the Advanced and UMS Market Segments, LDSO should expect to receive de-appointment notifications for all the MPANs in the Related MPAN or Import/Export group. | Y | DIP sending PUB-037 to LDSO LDSO obtaining all recored as defined by the the requirment (MHHS-BR-LD-004) and updating their records accordingly
4 | BP002 - Step 140, Step 150, Step 231 & Step 146 | MHHS-BR-MS-005 | DIP | Supplier(Outgoing/Incumbant) (Test Harness) Old Metering Service (Test Harness) EES (Test Harness) | PUB-037 | DIP sends PUB-037 to Supplier(Outgoing/Incumbant) (Test Harness), Old Metering Service (Test Harness) and EES (Test Harness). | N | DIP sending PUB-037 to Supplier(Outgoing/Incumbant) (Test Harness), Old Metering Service (Test Harness) and EES (Test Harness).

## TC_BP002_05_03
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP002_05_03 | Registration services sending De-Appointment Notification to the LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness) | TS_BP002_05 | • Segment A • Related MPAN • "On the Day" processing. Where Service Appointment start date = processing date AND existing supplier = requesting supplier Pre requisites. IF-031 with the following characteristics • (DI-999) Event Code = [MSApp] • (DI-800) Service Provider Appointment Scenario = CSP (Change of Service Provider) • (DI-833) "Proposed MS Effective From Date" = (as per the condition for "On the Day" processing) IF-032 accepted response (response to IF-031) with the following characteristics • (DI-999) Event Code = [MSAppInitialResp] • (DI-979) Response Code = A (Accept) IF-033 with the following characteristics • (DI-999) Event Code = [MSAppSPRequest] • (DI-800) Service Provider Appointment Scenario = CSP (Change of Service Provider) • (DI-833) "Proposed MS Effective From Date" = (as per the condition for "On the Day" processing) • (DI-979) Response Code = A (Accept) IF-034 accepted response (response to IF-033) with the following characteristics • (DI-999) Event Code = [MSAppSPResponse] • (DI-979) Response Code = A (Accept) Test data The "IF-037 Notification of Service De-Appointment" from the Registration Services to the LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness) with the following characteristics: • (DI-999) Event Code = [MSDeApp] • (DI-819) De-Appointment Reason Code = CSERV (Change of Service Provider) | The "IF-037 Notification of Service De-Appointment" from the Registration services sending to the LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness)
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP002 - Step 100 | MHHS-BR-RS-020 (On the day) MHHS-BR-RS-023 (On the day) | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must, in cases where the proposed Metering Service appointment is accepted, determine the processing path to be followed: • "On the day" (Service Appointment start date = processing date AND existing supplier = requesting supplier ) Registration Service must process "On the day" Metering Service appointments as soon as they are identified ie should not be held in the queue, for any longer than is necessary, ahead of the CSS COS secured notifications being received. | Y | Registration Services taking the data through the "on the Day" processing route
2 | BP002 - Step 130 | MHHS-BR-RS-030 MHHS-BR-RS-031 MHHS-BR-RS-033.1 | Registration Service | DIP | IF-037 | Registration Service sends "IF-037" to the DIP Registration Service must publish a Registration Service Notification of Service De-appointment using the appropriate interface on the Data Integration Platform where the end date for the incumbent Metering Service has been confirmed by a CSS secured notification. Registration Service must publish a Registration Service Notification of Service De-appointment using the appropriate interface on the Data Integration Platform where a Change of Metering Service only appointment is confirmed | Y | Registration Services sending the IF-037 to the DIP
3 | BP002 - Step 140 & Step 145 | MHHS-BR-LD-002 | DIP | LDSO | PUB-037 | DIP sending PUB-037 to LDSO LDSO must obtain Data Service de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. In the case where Related MPANs or Import/Export linked MPANs exist, for the Advanced and UMS Market Segments, LDSO should expect to receive de-appointment notifications for all the MPANs in the Related MPAN or Import/Export group. | Y | DIP sending PUB-037 to LDSO LDSO obtaining all recored as defined by the the requirment (MHHS-BR-LD-004) and updating their records accordingly
4 | BP002 - Step 140, Step 150, Step 231 & Step 146 | MHHS-BR-MS-005 | DIP | Supplier(Outgoing/Incumbant) (Test Harness) Old Metering Service (Test Harness) EES (Test Harness) | PUB-037 | DIP sends PUB-037 to Supplier(Outgoing/Incumbant) (Test Harness), Old Metering Service (Test Harness) and EES (Test Harness). | N | DIP sending PUB-037 to Supplier(Outgoing/Incumbant) (Test Harness), Old Metering Service (Test Harness) and EES (Test Harness).

## TC_BP002_05_04
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP002_05_04 | Registration services sending De-Appointment Notification to the LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness) | TS_BP002_05 | • Segment A • Related MPAN • "Prospective" processing. Where a new Supplier ID and Supply Start Date combination (notified by a CSS COS secured notification) exactly matches the Supplier ID and Appointment start date of a prospective Data Service then this prospective appointment should be processed. (58) Pre requisites. IF-031 with the following characteristics • (DI-999) Event Code = [MSApp] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed MS Effective From Date" = (as per the condition for "Prospective" processing) IF-032 accepted response (response to IF-031) with the following characteristics • (DI-999) Event Code = [MSAppInitialResp] • (DI-979) Response Code = A (Accept) IF-033 with the following characteristics • (DI-999)Event Code = [MSAppSPRequest] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed MS Effective From Date" = (as per the condition for "Prospective" processing) • (DI-979) Response Code = A (Accept) IF-034 accepted response (response to IF-033) with the following characteristics • (DI-999) Event Code = [MSAppSPResponse] • (DI-979) Response Code = A (Accept) Test data The "IF-037 Notification of Service De-Appointment" from the Registration Services to the LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness) with the following characteristics: • (DI-999) Event Code = [MSDeApp] • (DI-819) De-Appointment Reason Code = CSUPP (Change of Supply) | The "IF-037 Notification of Service De-Appointment" from the Registration services sending to the LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness)
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP002 - Step 100 | MHHS-BR-RS-020 (Prospective) MHHS-BR-RS-021 (Prospective) | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must, in cases where the proposed Metering Service appointment is accepted, determine the processing path to be followed: •"Prospective" Processing | Y | Registration Services taking the data through the "Prospective" processing route
2 | BP002 - Step 101 | MHHS-BR-RS-022 (Prospective) | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must be able to hold Prospective Metering Service appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received. | Y | Registration Services "holding" the appointment data in Queue
3 | BP002 - Step 120 | MHHS-BR-RS-024 (Prospective) MHHS-BR-RS-025 (Prospective for Change of Supply) MHHS-BR-RS-027 (Prospective) | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must, following receipt of the CSS COS secured notifications, process Prospective Appointments from the Prospective Appointment Queue, where the current Supplier ID matches the Supplier ID that requested a prospective Metering Service appointment AND the Metering Service Start Date equals the System Date + 1 but is less than the [future] Supply End Date. Registration Service must re-run validation, in line with the validation rules set out in the appropriate interface specification, for all Metering Service appointments that have been confirmed to re-process from the Prospective Appointment Queue, to ensure that the appointment is still valid. | Y | Resistration Services processing the appointment data where the current Supplier ID matches the Supplier ID that requested a prospective Metering Service appointment AND the Metering Service Start Date equals the System Date + 1 but is less than the [future] Supply End Date. Registration Services Re running validation rules for all Metering Service Appointments that have been confirmed to check if they are still valid.
4 | BP002 - Step 130 | MHHS-BR-RS-030 MHHS-BR-RS-031 MHHS-BR-RS-033.1 | Registration Service | DIP | IF-037 | Registration Service sends "IF-037" to the DIP Registration Service must publish a Registration Service Notification of Service De-appointment using the appropriate interface on the Data Integration Platform where the end date for the incumbent Metering Service has been confirmed by a CSS secured notification. Registration Service must publish a Registration Service Notification of Service De-appointment using the appropriate interface on the Data Integration Platform where a Change of Metering Service only appointment is confirmed | Y | Registration Services sending the IF-037 to the DIP
5 | BP002 - Step 140 & Step 145 | MHHS-BR-LD-002 | DIP | LDSO | PUB-037 | DIP sending PUB-037 to LDSO LDSO must obtain Data Service de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. In the case where Related MPANs or Import/Export linked MPANs exist, for the Advanced and UMS Market Segments, LDSO should expect to receive de-appointment notifications for all the MPANs in the Related MPAN or Import/Export group. | Y | DIP sending PUB-037 to LDSO LDSO obtaining all recored as defined by the the requirment (MHHS-BR-LD-004) and updating their records accordingly
6 | BP002 - Step 140, Step 150, Step 231 & Step 146 | MHHS-BR-MS-005 | DIP | Supplier(Outgoing/Incumbant) (Test Harness) Old Metering Service (Test Harness) EES (Test Harness) | PUB-037 | DIP sends PUB-037 to Supplier(Outgoing/Incumbant) (Test Harness), Old Metering Service (Test Harness) and EES (Test Harness). | N | DIP sending PUB-037 to Supplier(Outgoing/Incumbant) (Test Harness), Old Metering Service (Test Harness) and EES (Test Harness).

## TC_BP002_05_05
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP002_05_05 | Registration services sending De-Appointment Notification to the LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness) | TS_BP002_05 | • Segment S • Linked Import/Export MPAN • "Prospective" processing - Where the current Supplier ID matches the Supplier ID that requested a prospective Data Service appointment AND the Data Service Start Date equals the System Date + 1 but is less than the Supply End Date. (59) Pre requisites. IF-031 with the following characteristics • (DI-999) Event Code = [MSApp] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed DS Effective From Date" = (as per the condition for "Prospective" processing) IF-032 accepted response (response to IF-031) with the following characteristics • (DI-999) Event Code = [MSAppInitialResp] • (DI-979) Response Code = A (Accept) IF-033 with the following characteristics • (DI-999) Event Code = [MSAppSPRequest] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed MS Effective From Date" = (as per the condition for "Prospective" processing) • (DI-979) Response Code = A (Accept) IF-034 accepted response (response to IF-033) with the following characteristics • (DI-999) Event Code = [MSAppSPResponse] • (DI-979) Response Code = A (Accept) Test data The "IF-037 Notification of Service De-Appointment" from the Registration Services to the LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness) with the following characteristics: • (DI-999) Event Code = [MSDeApp] • (DI-819) De-Appointment Reason Code = CSUPP (Change of Supply) | The "IF-037 Notification of Service De-Appointment" from the Registration services sending to the LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness)
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP002 - Step 100 | MHHS-BR-RS-020 (Prospective) MHHS-BR-RS-021 (Prospective) | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must, in cases where the proposed Metering Service appointment is accepted, determine the processing path to be followed: •"Prospective" Processing | Y | Registration Services taking the data through the "Prospective" processing route
2 | BP002 - Step 101 | MHHS-BR-RS-022 (Prospective) | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must be able to hold Prospective Metering Service appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received. | Y | Registration Services "holding" the appointment data in Queue
3 | BP002 - Step 120 | MHHS-BR-RS-024 (Prospective) MHHS-BR-RS-025 (Prospective for Change of Supply) MHHS-BR-RS-027 (Prospective) | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must, following receipt of the CSS COS secured notifications, process Prospective Appointments from the Prospective Appointment Queue, where the current Supplier ID matches the Supplier ID that requested a prospective Metering Service appointment AND the Metering Service Start Date equals the System Date + 1 but is less than the [future] Supply End Date. Registration Service must re-run validation, in line with the validation rules set out in the appropriate interface specification, for all Metering Service appointments that have been confirmed to re-process from the Prospective Appointment Queue, to ensure that the appointment is still valid. | Y | Resistration Services processing the appointment data where the current Supplier ID matches the Supplier ID that requested a prospective Metering Service appointment AND the Metering Service Start Date equals the System Date + 1 but is less than the [future] Supply End Date. Registration Services Re running validation rules for all Metering Service Appointments that have been confirmed to check if they are still valid.
4 | BP002 - Step 130 | MHHS-BR-RS-030 MHHS-BR-RS-031 MHHS-BR-RS-033.1 | Registration Service | DIP | IF-037 | Registration Service sends "IF-037" to the DIP Registration Service must publish a Registration Service Notification of Service De-appointment using the appropriate interface on the Data Integration Platform where the end date for the incumbent Metering Service has been confirmed by a CSS secured notification. Registration Service must publish a Registration Service Notification of Service De-appointment using the appropriate interface on the Data Integration Platform where a Change of Metering Service only appointment is confirmed | Y | Registration Services sending the IF-037 to the DIP
5 | BP002 - Step 140 & Step 145 | MHHS-BR-LD-002 | DIP | LDSO | PUB-037 | DIP sending PUB-037 to LDSO LDSO must obtain Data Service de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. In the case where Related MPANs or Import/Export linked MPANs exist, for the Advanced and UMS Market Segments, LDSO should expect to receive de-appointment notifications for all the MPANs in the Related MPAN or Import/Export group. | Y | DIP sending PUB-037 to LDSO LDSO obtaining all recored as defined by the the requirment (MHHS-BR-LD-004) and updating their records accordingly
6 | BP002 - Step 140, Step 150, Step 231 & Step 146 | MHHS-BR-MS-005 | DIP | Supplier(Outgoing/Incumbant) (Test Harness) Old Metering Service (Test Harness) EES (Test Harness) | PUB-037 | DIP sends PUB-037 to Supplier(Outgoing/Incumbant) (Test Harness), Old Metering Service (Test Harness) and EES (Test Harness). | N | DIP sending PUB-037 to Supplier(Outgoing/Incumbant) (Test Harness), Old Metering Service (Test Harness) and EES (Test Harness).

## Test Scenario Requirements
| denotes - req part of BSC Assessment Criteria | denotes - req OOS of BSC Assessment Criteria | denotes - req still in question |  | Highlighted to mention that the requirements are mentioned under different BP in BRS documents & not for BP011A
Test Scenario ID | Test Scenario Title | Link to Requirement ID | Role | Business Process Steps | Requirements Detail | Interface ID | Supporting Information
TS_BP002_01 | Validate that the Registration Service issues response to an Initial 'Metering Service Appointment' Request | MHHS-BR-RS-009 | Registration Service | 30 | Registration Service must obtain Supplier Service Appointment Requests for a proposed Metering Service via the appropriate interface on the Data Integration Platform. The DIP will receive the appointment details from Supplier and publish them to Registrations. | PUB-031 (From DIP to Registration Services) | PUB-031 - Appointment scenario = "CSP", "COS" or "SEG"
|  | MHHS-BR-RS-010 | Registration Service | 40 | Registration Service must validate Supplier Service Appointment Requests received from DIP for a proposed Metering Service in line with the validation rules set out in the appropriate interface specification (MHHS-IF-031). Also, validate the contet of the message. | PUB-031 (From DIP to Registration Services) | Appointment scenario = "CSP" or "COS" (See change of segment process for "SEG")
|  | MHHS-BR-RS-011 (Accepted) MHHS-BR-RS-012 (Rejected) | Registration Service | 45 | Registration Service must publish a Registration Service Response to Supplier Service Appointment Request, using the appropriate interface on the Data Integration Platform: 1. with either initial acceptance of the proposed Metering Service where validation rules are met. Or, 2. with a rejection of the proposed Metering Service and associated rejection reason, where validation rules are not met. | MHHS-IF-032 (From Registration Services to DIP) | MHHS-IF-032 - Appointment scenario = "CSP", "COS" or "SEG"
TS_BP002_02 | Validate that Registration Service sends a valid request for Metering Service appointment to the new UMSO service and the UMSO service verifies appointment request and responds back with the Metering Service proposed Appointment response to Registration Service | MHHS-BR-RS-014.1 MHHS-BR-RS-015 | Registration Service | 60 | MHHS-BR-RS-014.1: Registration Service must notify the Proposed Domestic Premise Indicator provided by the Supplier, advised in the Suppliers Appointment Service Request, when sending a Registration Service Request for Service Appointment. MHHS-BR-RS-015: Registration Service must publish a Registration Service Request for Service Appointment for the proposed Metering Service using the appropriate interface on the Data Integration Platform where initial validation rules are met. | MHHS-IF-033 (From Registration Services to DIP) for MHHS-BR-RS-015 | MHHS-IF-033 - Appointment scenario = "CSP", "COS" or "SEG"
|  | MHHS-BR-MS-001 | UMSO | 70 | Metering Service will receive an appointment from the Supplier via the Registration Service. Metering Service must process and validate the appointment request as per the validation rules. Metering Service should be aware that an acceptance will result in the transfer of linked MPAN(s) | PUB-033 (From DIP to Metering Service)
|  | MHHS-BR-MS-002 MHHS-BR-MS-003 | UMSO | 75 | Metering Service must publish a response: 1. If the appointment request is valid and correct, the Metering Service will accept the appointment request. At this point the appointment remains "prospective" and there is a possibility that it may need to be lapsed at a later stage. 2. If the appointment request is invalid the Metering Service will reject the appointment and apply the relevant rejection reason and send all responses back to the Registration Service. | MHHS-IF-034 (From Metering Service to DIP) for MHHS-BR-MS-002
|  | MHHS-BR-RS-016 MHHS-BR-RS-017 | Registration Service | 85 | Registration Service must obtain Service Provider Response to Appointment Requests from the proposed Metering Service via the appropriate interface on the Data Integration Platform and maintain accepted responses in the background until the Effective from date when it will reflect as a live appointment | PUB-034 (From DIP to Registration Services) for MHHS-BR-RS-016 | PUB-034 - Appointment scenario = "CSP", "COS" or "SEG"
TS_BP002_03 | Unmetered Supply - Validate that the Registration Service is sending the Metering Service Appointment Notification to UMSO, EES (Test Harness) and Data Service (Test Harness) | MHHS-BR-RS-020 MHHS-BR-RS-021 MHHS-BR-RS-023 | Registration Service | 100 | Registration Service must, in cases where the proposed Metering Service appointment is accepted, determine the processing path to be followed: 1. "On the day" (Service Appointment start date = processing date AND existing supplier = requesting supplier ) , 2. "Retro" (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier ) 3. "Prospective" (All other appointments)
|  | MHHS-BR-RS-022 | Registration Service | 101 | Registration Service must be able to hold Prospective Metering Service appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received.
|  | MHHS-BR-RS-024 MHHS-BR-RS-025 (OOS) MHHS-BR-RS-027 (OOS) MHHS-BR-RS-028 MHHS-BR-RS-029 (OOS) | Registration Service | 120 | 1. Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. Where a new Supplier ID and Supply Start Date combination (notified by a CSS COS secured notification) exactly matches the Supplier ID and Appointment start date of a prospective Metering Service then this prospective appointment should be processed. 2. Registration Service must, following receipt of the CSS COS secured notifications, process Prospective Appointments from the Prospective Appointment Queue, where the current Supplier ID matches the Supplier ID that requested a prospective Metering Service appointment AND the Metering Service Start Date equals the System Date + 1 but is less than the [future] Supply End Date. 3. Registration Service must lapse prospective appointment requests following receipt of the CSS COS secured notifications, where the existing Supplier requested the new Metering Service Appointment, but the Appointment Start Date is less than, greater than or equal to the Supply End Date |  | For matching, there will be an ISD table to map DIP ID/ DIP Role Code identifiers and legacy MPIDs and Role Codes MHHS-BR-RS-027, Appointment scenario = "CSP", "COS" or "SEG" MHHS-BR-RS-028, Appointment scenario = "CSP", "COS" or "SEG" For MHHS-BR-RS-029, Appointment scenario = "CSP" or "SEG"
|  |  | Registration Service | 125 | For prospective appointments the Registration Service will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect.
|  | MHHS-BR-RS-033 | Registration Service | 240 | Registration Service must publish a Registration Service Notification of Service Appointment & Supporting Info with registration and metering details via the appropriate interface on the Data Integration Platform when a Metering Service appointment has been confirmed and will become effective. | MHHS-IF-036 (From Registration Service to DIP) | MHHS-IF-036 to Metering Service, Data Service, Supplier, Market-wide Data Service and LDSO Appointment scenario = "CSP", "COS" or "SEG" Domestic Premise Indicator notified should be as held in the Registration System as provided by CSS.
|  |  | DIP | 245 | The DIP will publish the Reg. Serv. Notification of Service App. & Supporting Info message. This will go to the Metering Service and the Smart Data Service as it will contain the Smart Meter technical details.
|  | MHHS-BR-MS-007 | UMSO | 195 | Metering Service must obtain Registration Service Notification of Service Appointment & Supporting Info updates, with confirmed Metering Service appointments, via the appropriate interface on the Data Integration Platform and update records with MPAN and Meter Technical Details (ADS and SDS only). For the avoidance of doubt this is the message that indicates that an appointment will/has taken effect. | PUB-036 (From DIP to Metering Service (New)) | Note: for Smart meters PUB-036 contains all the Meter Technical Detail required ( No additional D-flow as is the case with Trad and Advanced )
|  |  | EES | 283 | EES will receive notification from the DIP containing the Smart MTD's and confirmation of the new Metering Service | PUB-036 (From DIP to EES)
|  |  | Data Service | 270 | The New/Existing Data Service will receive notification from the DIP containing the Smart MTD's and confirmation of the new Metering Service | PUB-036 (From DIP to Data Service)
TS_BP002_04 | Metered Supply - Validate that the Registration Service is sending the Metering Service Appointment Notification & MTDs (Meter Technical Details) to LDSO, Metering Service (Test Harness), EES (Test Harness), Data Service (Test Harness) and Supplier (Test Harness) | MHHS-BR-RS-020 MHHS-BR-RS-021 MHHS-BR-RS-023 | Registration Service | 100 | Registration Service must, in cases where the proposed Metering Service appointment is accepted, determine the processing path to be followed: 1. "On the day" (Service Appointment start date = processing date AND existing supplier = requesting supplier ) , 2. "Retro" (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier ) 3. "Prospective" (All other appointments)
|  | MHHS-BR-RS-022 | Registration Service | 101 | Registration Service must be able to hold Prospective Metering Service appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received.
|  | MHHS-BR-RS-024 MHHS-BR-RS-025 (OOS) MHHS-BR-RS-027 (OOS) MHHS-BR-RS-028 MHHS-BR-RS-029 (OOS) | Registration Service | 120 | 1. Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. Where a new Supplier ID and Supply Start Date combination (notified by a CSS COS secured notification) exactly matches the Supplier ID and Appointment start date of a prospective Metering Service then this prospective appointment should be processed. 2. Registration Service must, following receipt of the CSS COS secured notifications, process Prospective Appointments from the Prospective Appointment Queue, where the current Supplier ID matches the Supplier ID that requested a prospective Metering Service appointment AND the Metering Service Start Date equals the System Date + 1 but is less than the [future] Supply End Date. 3. Registration Service must lapse prospective appointment requests following receipt of the CSS COS secured notifications, where the existing Supplier requested the new Metering Service Appointment, but the Appointment Start Date is less than, greater than or equal to the Supply End Date |  | For matching, there will be an ISD table to map DIP ID/ DIP Role Code identifiers and legacy MPIDs and Role Codes MHHS-BR-RS-027, Appointment scenario = "CSP", "COS" or "SEG" MHHS-BR-RS-028, Appointment scenario = "CSP", "COS" or "SEG" For MHHS-BR-RS-029, Appointment scenario = "CSP" or "SEG"
|  |  | Registration Service | 125 | For prospective appointments the Registration Service will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect.
|  | MHHS-BR-RS-033 | Registration Service | 240 | Registration Service must publish a Registration Service Notification of Service Appointment & Supporting Info with registration and metering details via the appropriate interface on the Data Integration Platform when a Metering Service appointment has been confirmed and will become effective. | MHHS-IF-036 (From Registration Service to DIP) | MHHS-IF-036 to Metering Service, Data Service, Supplier, Market-wide Data Service and LDSO Appointment scenario = "CSP", "COS" or "SEG" Domestic Premise Indicator notified should be as held in the Registration System as provided by CSS.
|  |  | DIP | 245 | The DIP will publish the Reg. Serv. Notification of Service App. & Supporting Info message. This will go to the Metering Service and the Smart Data Service as it will contain the Smart Meter technical details.
|  | MHHS-BR-LD-003 | LDSO | 280 | LDSO must obtain Metering Service notification updates via the appropriate interface on the Data Integration Platform, maintain records accordingly and investigate any discrepancies with data received from the Metering Service via the DTN. In the case where Related MPANs or Import/Export linked meters exist, LDSO should expect to receive appointment notifications for all the MPANs in the Related MPAN or Import/Export group. | PUB-036 (From DIP to LDSO)
|  | MHHS-BR-LD-003 | LDSO | 281 | The LDSO will need to manage and discrepancies between the MTD's received from Metering Services and the MTD's received from the Registration Service. | PUB-036 (From DIP to LDSO)
|  |  | LDSO | 282 | LDSO will continue with any BAU activity that may be required
|  | MHHS-BR-MS-007 | Metering Service | 195 | Metering Service must obtain Registration Service Notification of Service Appointment & Supporting Info updates, with confirmed Metering Service appointments, via the appropriate interface on the Data Integration Platform and update records with MPAN and Meter Technical Details (ADS and SDS only). For the avoidance of doubt this is the message that indicates that an appointment will/has taken effect. | PUB-036 (From DIP to Metering Service (New)) | Note: for Smart meters PUB-036 contains all the Meter Technical Detail required ( No additional D-flow as is the case with Trad and Advanced )
|  |  | EES | 283 | EES will receive notification from the DIP containing the Smart MTD's and confirmation of the new Metering Service | PUB-036 (From DIP to EES)
|  |  | Data Service | 270 | The New/Existing Data Service will receive notification from the DIP containing the Smart MTD's and confirmation of the new Metering Service | PUB-036 (From DIP to Data Service)
|  |  | Supplier | 260 | Supplier will manage the Metering Service appointment and meter technical details received via D-flows | PUB-036 (From DIP to Supplier)
TS_BP002_05 | Validate that the Registration Service will issue a de-appointment notification to LDSO, Incumbent Supplier (Test Harness), Metering Service (Test Harness) and EES (Test Harness) | MHHS-BR-RS-020 MHHS-BR-RS-021 MHHS-BR-RS-023 | Registration Service | 100 | Registration Service must, in cases where the proposed Metering Service appointment is accepted, determine the processing path to be followed: 1. "On the day" (Service Appointment start date = processing date AND existing supplier = requesting supplier ) , 2. "Retro" (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier ) 3. "Prospective" (All other appointments)
|  | MHHS-BR-RS-022 | Registration Service | 101 | Registration Service must be able to hold Prospective Metering Service appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received.
|  | MHHS-BR-RS-024.1 (can't find in BPD002) | Registration Service | 120 | Registration Service must publish a Registration Service Appointment Status Notification, to lapse the proposed appointment, using the appropriate interface on the Data Integration Platform where a CSS switch cancellation notification has been received where the Effective from date of the Metering Service matches the [now cancelled] Supply Start Date for that Supplier. |  | MHHS-IF-035 - Appointment scenario = "COS" or "SEG"
|  | MHHS-BR-RS-028 | Registration Service | 120 | Registration Service must lapse prospective appointment requests, following receipt of the CSS COS secured notifications and checking for appointments to process, where remaining prospective appointment start dates can no longer be achieved (Metering Service Appointment Start Date <= System Date)
|  | MHHS-BR-RS-029 | Registration Service | 120 | Registration Service must lapse prospective appointment requests following receipt of the CSS COS secured notifications, where the existing Supplier requested the new Metering Service Appointment, but the Appointment Start Date is greater than or equal to the Supply End Date.
|  |  | Registration Service | 125 | For prospective appointments the Registration Service will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect.
|  | MHHS-BR-RS-030 MHHS-BR-RS-031 MHHS-BR-RS-033.1 | Registration Service | 130 | Registration Service must publish a Registration Service Notification of Service De-appointment using the appropriate interface on the Data Integration Platform where: 1. the end date for the incumbent Metering Service has been confirmed by a CSS secured notification. 2. a Change of Metering Service only appointment is confirmed . | MHHS-IF-037 (From Registration Service to DIP) | For MHHS-BR-RS-030 : MHHS-IF-037 - Old Metering Service, LDSO, Old Supplier Appointment scenario = "COS"/"SEG" For MHHS-BR-RS-031 : MHHS-IF-037 - Old Metering Service, LDSO, Incumbent Supplier Appointment scenario = "CSP"/"SEG"
|  |  | DIP | 140 | This DIP will publish the de-appointment message to the previous Metering Service
|  | MHHS-BR-LD-002 | LDSO | 145 | LDSO must obtain Metering Service de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. In the case where Related MPANs or Import/Export linked meters exist, LDSO should expect to receive de-appointment notifications for all the MPANs in the Related MPAN or Import/Export group. | PUB-037 (From DIP to LDSO)
|  |  | EES (Test Harness) | 146 | EES can choose to subscribe to the de-appointment of Metering Service notification. | PUB-037 (From DIP to EES)
|  |  | Incumbent Supplier (Test Harness) | 150 | The old Supplier will receive notification that Metering Service has been de-appointed | PUB-037 (From DIP to Supplier)
|  | MHHS-BR-MS-005 | UMSO | 231 | Metering Service must obtain Registration Service Notification of Service De-Appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly | PUB-037 (From DIP to Metering Service) | PUB-037 A second notification will be received, if the first notification does not identify the new Metering Service.
TS_BP002_06 | Validate that the Registration Service publishes a Registration Service Appointment Status Notification to UMSO (for Unmetered Supply only), Metering Service (Test Harness) & Supplier (Test Harness) where the proposed Metering Service appointment has lapsed or is rejected | MHHS-BR-RS-020 MHHS-BR-RS-021 MHHS-BR-RS-023 | Registration Service | 100 | Registration Service must, in cases where the proposed Metering Service appointment is accepted, determine the processing path to be followed: 1. "On the day" (Service Appointment start date = processing date AND existing supplier = requesting supplier ) , 2. "Retro" (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier ) 3. "Prospective" (All other appointments)
|  | MHHS-BR-RS-022 | Registration Service | 101 | Registration Service must be able to hold Prospective Metering Service appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received.
|  | MHHS-BR-RS-024.1 (can't find in BPD002) | Registration Service | 120 | Registration Service must publish a Registration Service Appointment Status Notification, to lapse the proposed appointment, using the appropriate interface on the Data Integration Platform where a CSS switch cancellation notification has been received where the Effective from date of the Metering Service matches the [now cancelled] Supply Start Date for that Supplier. |  | MHHS-IF-035 - Appointment scenario = "COS" or "SEG"
|  | MHHS-BR-RS-028 | Registration Service | 120 | Registration Service must lapse prospective appointment requests, following receipt of the CSS COS secured notifications and checking for appointments to process, where remaining prospective appointment start dates can no longer be achieved (Metering Service Appointment Start Date <= System Date)
|  | MHHS-BR-RS-029 | Registration Service | 120 | Registration Service must lapse prospective appointment requests following receipt of the CSS COS secured notifications, where the existing Supplier requested the new Metering Service Appointment, but the Appointment Start Date is greater than or equal to the Supply End Date.
|  |  | Registration Service | 125 | For prospective appointments the Registration Service will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect.
|  | MHHS-BR-RS-032 | Registration Service | 220 | Registration Service must publish a Registration Service Appointment Status Notification (MSAppLapsed) using the appropriate interface on the Data Integration Platform where the proposed Metering Service appointment has lapsed or is rejected following failed validation | MHHS-IF-035 (From Registration Service to DIP) | MHHS-IF-035 - Appointment scenario = "CSP", "COS" or "SEG"
|  |  | DIP | 225 | The DIP will publish the Registration Service Proposed Appointment Request Outcome to notify the Metering Service their appointment is no longer valid. They will also notify Supplier that the appointment has been voided.
|  | MHHS-BR-MS-025 | UMSO | 230 | Metering Service must obtain Registration Service Appointment Status Notifications, with Metering Service lapsed appointments, via the appropriate interface on the Data Integration Platform and update records accordingly so as to ensure that that the appointment does not become effective. Metering Service must delete meter technical details received for all lapsed appointments within 30 days. | PUB-035 (From DIP to Metering Service)
|  |  | Supplier | 95 | Supplier will receive the publication of the Metering Service response to the appointment. Any appointments that have rejected will need to be reviewed and corrected and a new corrected appointment will need to be sent. Any successful appointments will remain in a pending status until the effective from date. | PUB-035 (From DIP to Supplier)
TS_BP002_07 | Validate that the Registration Service issues De-Appointment Notification to Metering Service (Test Harness) and Incumbent Supplier (Test Harness) for • Linked MPAN • Related MPAN | MHHS-BR-RS-034 (Linked Export) MHHS-BR-RS-037 (Linked Related) | Registration Service | 710 | 1. Registration Service must check for any linked Export/Related MPANs when a Metering Service appointment has been confirmed. 2. Registration Service must check for any linked Related MPANs when a Metering Service appointment has been confirmed. |  | For MHHS-BR-RS-034, Note this is limited to utilising the new “Associated Import/Export MPAN” data item being introduced by CP1558. MHHS-BR-RS-037, Note this is limited to utilising the Primary/Secondary MPAN relationship held in registration
|  | MHHS-BR-RS-035 (Linked Export) MHHS-BR-RS-038 (Linked Related) | Registration Service | 720 | 1. Registration Service must automatically publish an Export MPAN de-appointment, with a reason of "IMPEXP", via the appropriate interface on the Data Integration Platform for any linked Export MPANs. The same new Metering Service and effective date should be notified. 2. Registration Service must automatically publish a Related MPAN de-appointment, with a reason of "RELATE", via the appropriate interface on the Data Integration Platform for any linked Related MPANs. The same new Metering Service and effective date should be notified. | MHHS-IF-037 (From Registration Service to DIP) | MHHS-IF-037 - Old Metering Service, LDSO, Old/Incumbent Supplier
|  |  | DIP | 740 | The DIP will publish PUB-037 to Metering Services and Supplier to confirm the de-appointment | PUB-037 (From DIP to Metering Service)
|  | MHHS-BR-MS-009 (Linked Export) MHHS-BR-MS-009.1 (Linked Related) | MSA/MSS | 760 | MSA/MSS must obtain Export MPAN de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. MSA/MSS should note this message will be automatically triggered when a change of Metering Service has successfully completed for the linked import MPAN. MSA/MSS must obtain Related MPAN de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. MSA/MSS should note this message will be automatically triggered when a change of Metering Service has successfully completed for the Primary Related MPAN. | PUB-037 (From DIP to Metering Service)
TS_BP002_08 | Validate that the Registration Service issues Appointment Notification to Metering Service and Supplier (Test Harness) for Linked and Related MPANs | MHHS-BR-RS-034 (Linked Export) MHHS-BR-RS-037 (Linked Related) | Registration Service | 710 | 1. Registration Service must check for any linked Export/Related MPANs when a Metering Service appointment has been confirmed. 2. Registration Service must check for any linked Related MPANs when a Metering Service appointment has been confirmed. |  | For MHHS-BR-RS-034, Note this is limited to utilising the new “Associated Import/Export MPAN” data item being introduced by CP1558. MHHS-BR-RS-037, Note this is limited to utilising the Primary/Secondary MPAN relationship held in registration
|  | MHHS-BR-RS-036 (Linked Export) MHHS-BR-RS-039 (Linked Related) - OOS | Registration Service | 770 | 1. Registration Service must automatically publish an Export MPAN appointment confirmation via the appropriate interface on the Data Integration Platform for any linked Export MPANs. The same new Metering Service and effective date should be notified. 2. Registration Service must automatically publish a Related MPAN appointment confirmation via the appropriate interface on the Data Integration Platform for any linked Related MPANs. The same new Metering Service and effective date should be notified. | MHHS-IF-036 (From Registration Service to DIP) | MHHS-IF-036 to Metering Service, Data Service, Supplier, Market-wide Data Service and LDSO Domestic Premise Indicator notified should be as held in the Registration System as provided by CSS.
|  |  | DIP | 780 | The DIP will publish PUB-036 to Metering Services and Supplier to confirm the appointment | PUB-036 (From DIP to Metering Service)
|  | MHHS-BR-MS-008 (Linked Export) MHHS-BR-MS-008.1 (Linked Related) | MSA/MSS | 790 | MSA/MSS must obtain Export MPAN appointments via the appropriate interface on the Data Integration Platform and update records with registration and metering details. MSA/MSS should note this message will be automatically triggered when a change of Metering Service has successfully completed for the linked import MPAN. ( ie acceptance of the Export MPAN was implicit in the accepting the appointment to the Import MPAN ) MSA/MSS must obtain Related MPAN appointments via the appropriate interface on the Data Integration Platform and update records with registration and metering details. MSA/MSS should note this message will be automatically triggered when a change of Metering Service has successfully completed for the Primary Related MPAN. | PUB-036 (From DIP to Metering Service)
TS_BP002_09 | Validate that the Registration Service issue Registration Service Appointment Status Notification to Old Metering Service (Test Harness) for Traditional/Advanced Meters | MHHS-BR-RS-016 MHHS-BR-RS-017 | Registration Service | 85 | Registration Service must obtain Service Provider Response to Appointment Requests from the proposed Metering Service via the appropriate interface on the Data Integration Platform and maintain accepted responses in the background until the Effective from date when it will reflect as a live appointment | PUB-034 (From DIP to Registration Services) for MHHS-BR-RS-016 | MHHS-IF-035 - Appointment scenario = "CSP", "COS" or "SEG"
|  | MHHS-BR-RS-019 | Registration Service | 86 | Registration Service must, where a Traditional or Advanced Meter is installed, publish a Registration Service Appointment Status Notification to the incumbent Metering Service, where the proposed Metering Service has accepted. | MHHS-IF-035 (From DIP to Registration Services) | MHHS-IF-035 - Appointment scenario = "CSP", "COS" or "SEG" Note, Meter Type would need to be looked up in ISD in order to identify whether a meter is Smart or Traditional
|  |  | DIP | 90 | The DIP will publish the successful Metering Service appointments to the existing Metering Service. This is for non smart only. Existing Metering Service must send all relevant metering technical details to the prospective/new Metering Service provided by the Registration Service
|  | MHHS-BR-MS-006 | Metering Service | 160 | The existing Metering Service will receive notification of who the prospective Metering Service is from the Registrations service. Metering Service will send the meter technical details to the prospective Metering Service. No transfer of data is required for SMART. Advanced Metering Services will send a D0268 and SDS for non-smart Metering Services will send D0150 & D0149. Metering Services must issue all MTD's for linked export/related MPANS | PUB-035 (From DIP to Existing Metering Service)
TS_BP002_10 | Validate that the Registration Service issue Registration Service Appointment Status Notification to UMSO (for Unmetered Supply only), Metering Service (Test Harness for Metered Supply only) and Supplier (Test Harness) irrespective of being Accepted/Rejected | MHHS-BR-RS-016 MHHS-BR-RS-017 | Registration Service | 85 | Registration Service must obtain Service Provider Response to Appointment Requests from the proposed Metering Service via the appropriate interface on the Data Integration Platform and maintain accepted responses in the background until the Effective from date when it will reflect as a live appointment | PUB-034 (From DIP to Registration Services) for MHHS-BR-RS-016
|  | MHHS-BR-RS-018 | Registration Service | 87 | Registration Service must publish a Registration Service Appointment Status Notification to the Supplier and Metering Service confirming the Metering Service response using the appropriate interface on the Data Integration Platform | MHHS-IF-035 (From Registration Services to DIP)
|  |  | DIP | 91 | The DIP will publish the Metering Service response to the appointment to Supplier.
|  | MHHS-BR-MS-006.1 | UMSO | 92 | Metering Service must obtain Registration Service Appointment Status Notification updates, acknowledging the Prospective Metering Service accepted/rejected appointments, via the appropriate interface on the Data Integration Platform and maintain records accordingly | PUB-035 (From DIP to Metering Service)
|  |  | Supplier | 95 | Supplier will receive the publication of the Metering Service response to the appointment. Any appointments that have rejected will need to be reviewed and corrected and a new corrected appointment will need to be sent. Any successful appointments will remain in a pending status until the effective from date. | PUB-035 (From DIP to Supplier)
TS_BP002_11 | Metered Supply: Validate that the Registration Service sends a valid request for Metering Service Appointment to the New Metering Service (Test Harness) | MHHS-BR-RS-014.1 MHHS-BR-RS-015 | Registration Service | 60 | MHHS-BR-RS-014.1: Registration Service must notify the Proposed Domestic Premise Indicator provided by the Supplier, advised in the Suppliers Appointment Service Request, when sending a Registration Service Request for Service Appointment. MHHS-BR-RS-015: Registration Service must publish a Registration Service Request for Service Appointment for the proposed Metering Service using the appropriate interface on the Data Integration Platform where initial validation rules are met. | MHHS-IF-033 (From Registration Services to DIP) for MHHS-BR-RS-015 | MHHS-IF-033 - Appointment scenario = "CSP", "COS" or "SEG"
|  | MHHS-BR-MS-001 | Metering Service | 70 | Metering Service will receive an appointment from the Supplier via the Registration Service. Metering Service must process and validate the appointment request as per the validation rules. Metering Service should be aware that an acceptance will result in the transfer of linked MPAN(s) | PUB-033 (From DIP to Metering Service)
|  | MHHS-BR-MS-002 MHHS-BR-MS-003 | Metering Service | 75 | Metering Service must publish a response: 1. If the appointment request is valid and correct, the Metering Service will accept the appointment request. At this point the appointment remains "prospective" and there is a possibility that it may need to be lapsed at a later stage. 2. If the appointment request is invalid the Metering Service will reject the appointment and apply the relevant rejection reason and send all responses back to the Registration Service. | MHHS-IF-034 (From Metering Service to DIP) for MHHS-BR-MS-002
|  | MHHS-BR-RS-016 MHHS-BR-RS-017 | Registration Service | 85 | Registration Service must obtain Service Provider Response to Appointment Requests from the proposed Metering Service via the appropriate interface on the Data Integration Platform and maintain accepted responses in the background until the Effective from date when it will reflect as a live appointment | PUB-034 (From DIP to Registration Services) for MHHS-BR-RS-016 | PUB-034 - Appointment scenario = "CSP", "COS" or "SEG"
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be a unique ID and created when each scenario is added
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be the participants role in delivery Multiple roles could be covered in 1 scenario
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is a unique number of the requirement link to the requirement spreadsheet Each requirement should be linked to the Design and Assessment criteria
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each scenario will be linked to Business Processes
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: An ID will be displayed if there is an interface linked to a scenario