## Sheet3 (hidden)
Proposed LDSO QT Scenario | SIT Scenario
Scenario ID | Scenario ID | SITFTS-0050
Role | Scenario Title | Create MPAN
Theme | Theme | New Connection
Business Process | Description | Create an MPAN through new connection process, appoint services and install meter. & Energise the MPAN
Functional Category | Functional Category | Create MPAN
Scenario Title | Functional Area 1 | New Connection |  |  | Business Process Steps
Description | Functional Area 2 | New MPAN, New Connection successful
Boundaries | Creator | Shaun Magee, Dan Gee |  |  | Interface Description
Test Case Variables | Priority | High |  |  | Regression flag
Optionality | Scenario size | Large
Number of test cases | Business Process | BP001, BP002, BP003, BP010B(Related), BP010C (Linked), BP009, BP008, (+BP003A for Smart meters) |  |  | Precondition Test Harness
Scenario size | Boundaries | Processing ends once the Meter is Installed (if not Unmetered) and Energisation has occurred |  |  | Precondition Other
Priority | Test Case Variables | (1) Smart, import+export, forward-dated (MPAN Creation current date)
Systems under test |  | (2) Traditional, single MPAN, forward-dated (MPAN Creation current date)
|  | (3) Advanced Single MPAN, forward-dated (MPAN Creation current date) |  |  | Test evidence
(4) Unmetered, single MPAN, forward-dated (MPAN Creation current date)
| Exception Codes | NA |  |  | Role (simulated)
LDSO Test Case | SIT Test Case
No.
Test Case Id | Test Case Id
Test Case Title | Test Case Title
Test Case Link | Test Case Link
Test Data Requirements | Test Data Requirements
Traceability Requirement |  |  | Test outcome
Test Harness |  |  | Test Harness
Key Validation & Test Evidence |  |  | Interface
BP Step |  |  | requirement
Service initiating process | SIT Test Steps |  | test evidence
Service Recepint Processor
Interface | Test Case Title |  | SITFTS-0050 - Smart Metered
Evidecne Reuiqred | Key Journey | Events | New MPAN Initial Registration - Start
| Step No. |  | 10
| Business Process |  | BP001
| BP Step |  | 5
| Traceability Requirement |  | MHHS-BR-LD-010.1 | MHHS-BR-LD-010.2
| Service Producing Trigger |  | LDSO
| Input/Trigger |  | DB01
| Message Input Event Code |  | N/A
| Service Recipient Processor of Input/Trigger |  | REGS
| Test Step |  | LDSO creates 2 MPAN'S for Import/Export linked MPAN and issues DB01 REGS
| Key Validation & Test Evidence |  | Import/Export Mpan creation and linkage required
| Evidence | Required | Y

## Cover Sheet
LDSO QT - Test Scenarios
Version | Description | Author | Status | Date
V 0.1 | Initial Draft of BP003 Test Scenarios | Non SIT LDSO QT Test Team |  | 2024-01-19
| Review by SIT |  |  | 2024-01-23
V0.2 | Amendments - incorporating SIT comments | Non SIT LDSO QT Test Team |  | 2024-01-24
V0.3 | Amendments - incorporating changes after clarifications from Design Team | Non SIT LDSO QT Test Team | In Progress | 2024-01-29
v0.4 | Amendments after Code Bodies Review & Final check |  |  | 2024-01-31
v0.5 | Amendments made after data team input |  |  | 2024-02-07
v0.6 | Start Test Cases |  |  | 2024-02-12
v0.7 | TC_BP003B_03_01 - Changed from Linked Related to Related in Test Data Requirements | Raina | Completed | 2024-05-30
v0.8 | More detail added to the linked and related tests | Kam | Completed | 2024-10-14
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## TC_BP003B_03_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP003B_03_01 | BP003B Validate when a change of MDR is initiated by the Smart Data Service (Test Harness). The IF-034 "Service Provider Appointment Request Response" is sent to the Registration Service. Segment S Linked Related MPAN | TS_BP003_03 | • Segment S (Smart) • Related (For related primary and secondary mpans only 1 instance of the the IF-034) Actual Test The tester will initiate the change of MDR from the smart data service test harness by triggering a IF-034 (for the primary mpan) to the Registration Services with the following characteristics. • (DI-999) Event Code = [SDS-MDRUpdate] • (DI-979) Response Code = Accepted | The change of MDR is initiated by the Smart Data Service (Test Harness). The IF-034 "Service Provider Appointment Request Response" is sent to the Registration Service, who will receive, validate and update their records accordingly.
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP003B -Step 226 to 80 | NA | Smart Data Service (Test Harness) | DIP | MHHS-IF-034 9 (for the primary) | In this Test the Service Provider = Data Service SDS Initiated Change of MDR. They will issue MHHS-IF-034 to the DIP 1 instance for the primary | n | In this Test the Service Provider = Data Service SDS Initiated Change of MDR. They will issue MHHS-IF-034 to the DIP
4 | BP003B -Step 80 and 85 and 100 and 110 | MHHS-BR-RS-086.1 (obtain) MHHS-BR-RS-087 (validate) MHHS-BR-RS-088.1 (Flavour 2) MHHS-BR-RS-088.3 (related) | DIP | Registration Service | PUB-034 (for the primary) | DP publishes "Service Provider Appointment Request Response" to the Registration Service (86.1) Registration Service must obtain SDS initiated change of MDR requests via the appropriate interface on the Data Integration Platform and maintain records accordingly (87) Registration Service must validate Service Provider Response to Appointment Requests from the proposed Service Provider and SDS initiated change of MDR requests in line with the validation rules set out in the appropriate interface specification (MHHS-IF-034). (88.1) Registration Service must, where the MDR has been updated (or if the same MDR is provided and the CSS update flag for the appointment shows as failed), inform CSS of the MDR. Where CSS /DCC also require to an update move to BP003A. (88,3)Registration Service must, in the case of an accepted Data Service update, apply the updated Contract Reference, MDR (SDS Smart MPANs) and Read Frequency (Advanced/SDS MPANs) for any Secondary Related MPANs and publish a Registration Service Appointment Status Notification using the appropriate interface on the Data Integration Platform. 1 instance for the primary | y | Registration Services receiving and validating the DIP message. Registration Services updating their records accordingly. Where CSS /DCC also require an update move to BP003A. This test is for a smart data service with related mpans so only validate the smart data service and related mpans aspects of the requirements.