## Sheet3 (hidden)
Proposed LDSO QT Scenario | SIT Scenario
Scenario ID | Scenario ID | SITFTS-0050
Role | Scenario Title | Create MPAN
Theme | Theme | New Connection
Business Process | Description | Create an MPAN through new connection process, appoint services and install meter. & Energise the MPAN
Functional Category | Functional Category | Create MPAN
Scenario Title | Functional Area 1 | New Connection |  |  | Business Process Steps
Description | Functional Area 2 | New MPAN, New Connection successful
Boundaries | Creator | Shaun Magee, Dan Gee |  |  | Interface Description
Test Case Variables | Priority | High |  |  | Regression flag
Optionality | Scenario size | Large
Number of test cases | Business Process | BP001, BP002, BP003, BP010B(Related), BP010C (Linked), BP009, BP008, (+BP003A for Smart meters) |  |  | Precondition Test Harness
Scenario size | Boundaries | Processing ends once the Meter is Installed (if not Unmetered) and Energisation has occurred |  |  | Precondition Other
Priority | Test Case Variables | (1) Smart, import+export, forward-dated (MPAN Creation current date)
Systems under test |  | (2) Traditional, single MPAN, forward-dated (MPAN Creation current date)
|  | (3) Advanced Single MPAN, forward-dated (MPAN Creation current date) |  |  | Test evidence
(4) Unmetered, single MPAN, forward-dated (MPAN Creation current date)
| Exception Codes | NA |  |  | Role (simulated)
LDSO Test Case | SIT Test Case
No.
Test Case Id | Test Case Id
Test Case Title | Test Case Title
Test Case Link | Test Case Link
Test Data Requirements | Test Data Requirements
Traceability Requirement |  |  | Test outcome
Test Harness |  |  | Test Harness
Key Validation & Test Evidence |  |  | Interface
BP Step |  |  | requirement
Service initiating process | SIT Test Steps |  | test evidence
Service Recepint Processor
Interface | Test Case Title |  | SITFTS-0050 - Smart Metered
Evidecne Reuiqred | Key Journey | Events | New MPAN Initial Registration - Start
| Step No. |  | 10
| Business Process |  | BP001
| BP Step |  | 5
| Traceability Requirement |  | MHHS-BR-LD-010.1 | MHHS-BR-LD-010.2
| Service Producing Trigger |  | LDSO
| Input/Trigger |  | DB01
| Message Input Event Code |  | N/A
| Service Recipient Processor of Input/Trigger |  | REGS
| Test Step |  | LDSO creates 2 MPAN'S for Import/Export linked MPAN and issues DB01 REGS
| Key Validation & Test Evidence |  | Import/Export Mpan creation and linkage required
| Evidence | Required | Y

## Cover Sheet
LDSO QT - Test Scenarios
Version | Description | Author | Status | Date
V 0.1 | Initial Draft of BP003 Test Scenarios | Non SIT LDSO QT Test Team |  | 2024-01-19
| Review by SIT |  |  | 2024-01-23
V0.2 | Amendments - incorporating SIT comments | Non SIT LDSO QT Test Team |  | 2024-01-24
V0.3 | Amendments - incorporating changes after clarifications from Design Team | Non SIT LDSO QT Test Team | In Progress | 2024-01-29
v0.4 | Amendments after Code Bodies Review & Final check |  |  | 2024-01-31
| Amendments made after data team input |  |  | 2024-02-07
| Start Test Cases |  |  | 12/02.2024
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## TC_BP003_05_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP003_05_01 | Registration services sending De-Appointment Notification to the LDSO, Old Data Service (Test Harness). EES (Test Harness). Suppler (Test Harness) | TS_BP003_05 | • Segment A • Single MPAN • "On the Day" processing. Where Service Appointment start date = processing date AND existing supplier = requesting supplier Pre requisites. IF-031 with the following characteristics • (DI-999)Event Code = [DSApp] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed DS Effective From Date" = (as per the condition for "On the Day" processing) IF-032 accepted response (response to IF-031) with the following characteristics • (DI-999)Event Code = [DSAppInitialResp] • (DI-979) Response Code = Accepted IF-033 with the following characteristics • (DI-999)Event Code = [DSAppSPRequest] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed DS Effective From Date" = (as per the condition for "On the Day" processing) • (DI-979) Response Code = Accepted IF-034 accepted response (response to IF-033) with the following characteristics • (DI-999)Event Code = [DSAppSPResponse] • (DI-979) Response Code = Accepted Test data The "IF-037 Notification of Service De-Appointment" from the Registration Services to the LDSO, Old Data Service (Test Harness) and EES (Test Harness). • (DI-999) Event Code = [DSDeApp] • (DI-819) De-Appointment Reason Code = CSUPP (Change of Supply) | The "IF-037 Notification of Service De-Appointment" from the Registration services sending to the LDSO, Old Data Service (Test Harness). EES (Test Harness). Suppler (Test Harness)
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP003 -Step 100 | MHHS-BR-RS-054 (on the day) MHHS-BR-RS-057 (on the day) | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must, in cases where the proposed Data Service appointment is accepted, determine the processing path to be followed: • "On the day" (Service Appointment start date = processing date AND existing supplier = requesting supplier ) Registration Service must process "On the day" Data Service appointments as soon as they are identified i.e. should not be held in the queue, for any longer than is necessary, ahead of the CSS COS secured notifications being received. | y | Registration Services taking the data through the "on the Day" processing route
2 | BP003 -Step 130 | NA (on the Day has non) | Registration Service (internal processing) | DIP | IF-037 | Registration Service sends "IF-037" to the DIP | n | Registration Services sending the IF0-37 to the DIP
3 | BP003 -Step 140 - 145 | MHHS-BR-LD-004 | DIP | LDSO | PUB-037 | LDSO must obtain Data Service de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. In the case where Related MPANs or Import/Export linked MPANs exist, for the Advanced and UMS Market Segments, LDSO should expect to receive de-appointment notifications for all the MPANs in the Related MPAN or Import/Export group. | y | DIP sending PUB-036 to LDSO LDSO obtaining all recorded as defined by the requirement (MHHS-BR-LD-004) and updating their records accordingly
4 | BP003 -Step 140 - 146 BP003 -Step 140 - 96 BP003 -Step 140 -150 | NA | DIP | EES (Test Harness) End Old Data Service (Test Harness) End Suppler outgoing/incumbent (Test Harness) End | PUB-037 | DIP sends PUB-037 to EES (Test Harness) DIP sends PUB-037 to old Data Service (Test Harness) DIP sends PUB-037 to Suppler outgoing/incumbent (Test Harness) | n | DIP sends PUB-037 to EES (Test Harness) DIP sends PUB-037 to old Data Service (Test Harness) DIP sends PUB-037 to Suppler outgoing/incumbent (Test Harness)

## TC_BP003_05_02
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP003_05_02 | Registration services sending De-Appointment Notification to the LDSO, Old Data Service (Test Harness). EES (Test Harness). Suppler (Test Harness) | TS_BP003_04 | • Segment A • Linked Related MPANs • "On the Day" processing. Where Service Appointment start date = processing date AND existing supplier = requesting supplier Pre requisites. IF-031 with the following characteristics • (DI-999)Event Code = [DSApp] • (DI-800) Service Provider Appointment Scenario = CSP (Change of Service Provider) • (DI-833) "Proposed DS Effective From Date" = (as per the condition for "On the Day" processing) IF-032 accepted response (response to IF-031) with the following characteristics • (DI-999)Event Code = [DSAppInitialResp] • (DI-979) Response Code = Accepted IF-033 with the following characteristics • (DI-999)Event Code = [DSAppSPRequest] • (DI-800) Service Provider Appointment Scenario = CSP (Change of Service Provider) • (DI-833) "Proposed DS Effective From Date" = (as per the condition for "On the Day" processing) • (DI-979) Response Code = Accepted IF-034 accepted response (response to IF-033) with the following characteristics • (DI-999)Event Code = [DSAppSPResponse] • (DI-979) Response Code = Accepted Test data The "IF-037 Notification of Service De-Appointment" from the Registration Services to the LDSO, Old Data Service (Test Harness) and EES (Test Harness). • (DI-999) Event Code = [DSDeApp] • (DI-819) De-Appointment Reason Code = CSERV (Change of Service Provider) | The "IF-037 Notification of Service De-Appointment" from the Registration services sending to the LDSO, Old Data Service (Test Harness). EES (Test Harness). Suppler (Test Harness)
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP003 -Step 100 | MHHS-BR-RS-054 (on the day) MHHS-BR-RS-057 (on the day) | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must, in cases where the proposed Data Service appointment is accepted, determine the processing path to be followed: • "On the day" (Service Appointment start date = processing date AND existing supplier = requesting supplier ) Registration Service must process "On the day" Data Service appointments as soon as they are identified i.e. should not be held in the queue, for any longer than is necessary, ahead of the CSS COS secured notifications being received. | y | Registration Services taking the data through the "on the Day" processing route
2 | BP003 -Step 130 | MHHS-BR-RS-065 | Registration Service (internal processing) | DIP | IF-037 | Registration Service must publish a Registration Service Notification of Service De-appointment using the appropriate interface on the Data Integration Platform where a Change of Data Service only appointment is confirmed | y | Registration Services sending the IF0-37 to the DIP
3 | BP003 -Step 140 - 145 | MHHS-BR-LD-004 | DIP | LDSO |  | LDSO must obtain Data Service de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. In the case where Related MPANs or Import/Export linked MPANs exist, for the Advanced and UMS Market Segments, LDSO should expect to receive de-appointment notifications for all the MPANs in the Related MPAN or Import/Export group. | y | DIP sending PUB-036 to LDSO LDSO obtaining all recorded as defined by the requirement (MHHS-BR-LD-004) and updating their records accordingly
4 | BP003 -Step 140 - 146 BP003 -Step 140 - 96 BP003 -Step 140 -150 | NA | DIP | EES (Test Harness) End Old Data Service (Test Harness) End Suppler outgoing/incumbent (Test Harness) End | PUB-037 | DIP sends PUB-037 to EES (Test Harness) DIP sends PUB-037 to old Data Service (Test Harness) DIP sends PUB-037 to Suppler outgoing/incumbent (Test Harness) | n | DIP sends PUB-037 to EES (Test Harness) DIP sends PUB-037 to old Data Service (Test Harness) DIP sends PUB-037 to Suppler outgoing/incumbent (Test Harness)

## TC_BP003_05_03
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP003_05_03 | Registration services sending De-Appointment Notification to the LDSO, Old Data Service (Test Harness). EES (Test Harness). Suppler (Test Harness) | TS_BP003_04 | • Segment S • Single MPAN • "Retro" processing. Where Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier Pre requisites. IF-031 with the following characteristics • (DI-999)Event Code = [DSApp] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed DS Effective From Date" = (as per the condition for "Retro" processing) IF-032 accepted response (response to IF-031) with the following characteristics • (DI-999)Event Code = [DSAppInitialResp] • (DI-979) Response Code = Accepted IF-033 with the following characteristics • (DI-999)Event Code = [DSAppSPRequest] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed DS Effective From Date" = (as per the condition for "Retro" processing) • (DI-979) Response Code = Accepted IF-034 accepted response (response to IF-033) with the following characteristics • (DI-999)Event Code = [DSAppSPResponse] • (DI-979) Response Code = Accepted Test data The "IF-037 Notification of Service De-Appointment" from the Registration Services to the LDSO, Old Data Service (Test Harness) and EES (Test Harness). • (DI-999) Event Code = [DSDeApp] • (DI-819) De-Appointment Reason Code = CSUPP (Change of Supply) | The "IF-037 Notification of Service De-Appointment" from the Registration services sending to the LDSO, Old Data Service (Test Harness). EES (Test Harness). Suppler (Test Harness)
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP003 -Step 100 | MHHS-BR-RS-054 (Retro) MHHS-BR-RS-057 (Retro) | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must, in cases where the proposed Data Service appointment is accepted, determine the processing path to be followed: • "Retro" (Service Appointment start date = Previous Service Appointment End Date +1 AND Service Appointment start date< processing date AND Existing Supplier = Requesting Supplier ) Registration Service must process "Retro" Data Service appointments as soon as they are identified i.e. should not be held in the queue, for any longer than is necessary, ahead of the CSS COS secured notifications being received. | y | Registration Services taking the data through the "Retro" processing route
2 | BP003 -Step 130 | NA (Retro has non) | Registration Service (internal processing) | DIP | IF-037 | Registration Service sends "IF-037" to the DIP | n | Registration Services sending the IF0-37 to the DIP
3 | BP003 -Step 140 - 145 | MHHS-BR-LD-004 | DIP | LDSO | PUB-037 | LDSO must obtain Data Service de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. In the case where Related MPANs or Import/Export linked MPANs exist, for the Advanced and UMS Market Segments, LDSO should expect to receive de-appointment notifications for all the MPANs in the Related MPAN or Import/Export group. | y | DIP sending PUB-036 to LDSO LDSO obtaining all recorded as defined by the requirement (MHHS-BR-LD-004) and updating their records accordingly
4 | BP003 -Step 140 - 146 BP003 -Step 140 - 96 BP003 -Step 140 -150 | NA | DIP | EES (Test Harness) End Old Data Service (Test Harness) End Suppler outgoing/incumbent (Test Harness) End | PUB-037 | DIP sends PUB-037 to EES (Test Harness) DIP sends PUB-037 to old Data Service (Test Harness) DIP sends PUB-037 to Suppler outgoing/incumbent (Test Harness) | n | DIP sends PUB-037 to EES (Test Harness) DIP sends PUB-037 to old Data Service (Test Harness) DIP sends PUB-037 to Suppler outgoing/incumbent (Test Harness)

## TC_BP003_05_04
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP003_05_04 | Registration services sending De-Appointment Notification to the LDSO, Old Data Service (Test Harness). EES (Test Harness). Suppler (Test Harness) | TS_BP003_04 | • Segment A • Liked Related MPANs • "Perspective" processing. Where a new Supplier ID and Supply Start Date combination (notified by a CSS COS secured notification) exactly matches the Supplier ID and Appointment start date of a prospective Data Service then this prospective appointment should be processed. (58) Pre requisites. IF-031 with the following characteristics • (DI-999)Event Code = [DSApp] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed DS Effective From Date" = (as per the condition for "Perspective" processing) IF-032 accepted response (response to IF-031) with the following characteristics • (DI-999)Event Code = [DSAppInitialResp] • (DI-979) Response Code = Accepted IF-033 with the following characteristics • (DI-999)Event Code = [DSAppSPRequest] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed DS Effective From Date" = (as per the condition for "Perspective" processing) • (DI-979) Response Code = Accepted IF-034 accepted response (response to IF-033) with the following characteristics • (DI-999)Event Code = [DSAppSPResponse] • (DI-979) Response Code = Accepted Test data The "IF-037 Notification of Service De-Appointment" from the Registration Services to the LDSO, Old Data Service (Test Harness) and EES (Test Harness). • (DI-999) Event Code = [DSDeApp] • (DI-819) De-Appointment Reason Code = CSUPP (Change of Supply) | The "IF-037 Notification of Service De-Appointment" from the Registration services sending to the LDSO, Old Data Service (Test Harness). EES (Test Harness). Suppler (Test Harness)
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP003 -Step 100 | MHHS-BR-RS-054 (Perspective) (Step 100) MHHS-BR-RS-056 (Perspective) (Step 101) MHHS-BR-RS-058 (Perspective) (Step 120) MHHS-BR-RS-061 (Perspective) (Step 120) | Registration Service (internal processing) | Registration Service (internal processing) | NA | Step 100 (54)Registration Service must, in cases where the proposed Data Service appointment is accepted, determine the processing path to be followed: •"Prospective" Processing Step 101 (56) Registration Service must be able to hold Prospective Data Service appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received. Step 120 (61) Registration Service must re-run validation, in line with the validation rules set out in the appropriate interface specification, for all Data Service appointments that have been confirmed to re-process from the Prospective Appointment Queue, to ensure that the appointment is still valid 58)Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. Where a new Supplier ID and Supply Start Date combination (notified by a CSS COS secured notification) exactly matches the Supplier ID and Appointment start date of a prospective Data Service then this prospective appointment should be processed. | y | Step 100 Registration Services taking the data through the "Perspective" processing route Step 101 Registration Services "holding" the appointment data in Queue Step 120 Registration Services Re running validation rules for all Data Service Appointments that have been confirmed to check if they are still valid. Registration Services processing the appointment data Where a new Supplier ID and Supply Start Date combination (notified by a CSS COS secured notification) exactly matches the Supplier ID and Appointment start date of a prospective Data Service.
2 | BP003 -Step 130 | MHHS-BR-RS-064 | Registration Service (internal processing) | DIP | IF-037 | Registration Service sends "IF-037" to the DIP Registration Service must publish a Registration Service Notification of Service De-appointment using the appropriate interface on the Data Integration Platform where the end date for the incumbent Data Service has been confirmed by a CSS secured notification. | y | Registration Services sending the IF0-37 to the DIP
3 | BP003 -Step 140 - 145 | MHHS-BR-LD-004 | DIP | LDSO | PUB-037 | LDSO must obtain Data Service de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. In the case where Related MPANs or Import/Export linked MPANs exist, for the Advanced and UMS Market Segments, LDSO should expect to receive de-appointment notifications for all the MPANs in the Related MPAN or Import/Export group. | y | DIP sending PUB-036 to LDSO LDSO obtaining all recorded as defined by the requirement (MHHS-BR-LD-004) and updating their records accordingly
4 | BP003 -Step 140 - 146 BP003 -Step 140 - 96 BP003 -Step 140 -150 | NA | DIP | EES (Test Harness) End Old Data Service (Test Harness) End Suppler outgoing/incumbent (Test Harness) End | PUB-037 | DIP sends PUB-037 to EES (Test Harness) DIP sends PUB-037 to old Data Service (Test Harness) DIP sends PUB-037 to Suppler outgoing/incumbent (Test Harness) | n | DIP sends PUB-037 to EES (Test Harness) DIP sends PUB-037 to old Data Service (Test Harness) DIP sends PUB-037 to Suppler outgoing/incumbent (Test Harness)

## TC_BP003_05_05
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP003_05_05 | Registration services sending De-Appointment Notification to the LDSO, Old Data Service (Test Harness). EES (Test Harness). Suppler (Test Harness) | TS_BP003_04 | • Segment S • Linked Import/Export MPANs • "Perspective" processing. Where the current Supplier ID matches the Supplier ID that requested a prospective Data Service appointment AND the Data Service Start Date equals the System Date + 1 but is less than the Supply End Date. (59) Pre requisites. IF-031 with the following characteristics • (DI-999)Event Code = [DSApp] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed DS Effective From Date" = (as per the condition for "Perspective" processing) IF-032 accepted response (response to IF-031) with the following characteristics • (DI-999)Event Code = [DSAppInitialResp] • (DI-979) Response Code = Accepted IF-033 with the following characteristics • (DI-999)Event Code = [DSAppSPRequest] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed DS Effective From Date" = (as per the condition for "Perspective" processing) • (DI-979) Response Code = Accepted IF-034 accepted response (response to IF-033) with the following characteristics • (DI-999)Event Code = [DSAppSPResponse] • (DI-979) Response Code = Accepted Test data The "IF-037 Notification of Service De-Appointment" from the Registration Services to the LDSO, Old Data Service (Test Harness) and EES (Test Harness). • (DI-999) Event Code = [DSDeApp] • (DI-819) De-Appointment Reason Code = CSUPP (Change of Supply) | The "IF-037 Notification of Service De-Appointment" from the Registration services sending to the LDSO, Old Data Service (Test Harness). EES (Test Harness). Suppler (Test Harness)
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP003 -Step 100 to 101 to 120 | MHHS-BR-RS-054 (Perspective) (Step 100) MHHS-BR-RS-056 (Perspective) (Step 101) MHHS-BR-RS-059 (Perspective) (Step 120) MHHS-BR-RS-061 (Perspective) (Step 120) | Registration Service (internal processing) | Registration Service (internal processing) | NA | Step 100 (54)Registration Service must, in cases where the proposed Data Service appointment is accepted, determine the processing path to be followed: •"Prospective" Processing Step 101 (56) Registration Service must be able to hold Prospective Data Service appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received. Step 120 (61) Registration Service must re-run validation, in line with the validation rules set out in the appropriate interface specification, for all Data Service appointments that have been confirmed to re-process from the Prospective Appointment Queue, to ensure that the appointment is still valid 59)Registration Service must, following receipt of the CSS COS secured notifications, process Prospective Appointments from the Prospective Appointment Queue, where the current Supplier ID matches the Supplier ID that requested a prospective Data Service appointment AND the Data Service Start Date equals the System Date + 1 but is less than the Supply End Date. | y | Step 100 Registration Services taking the data through the "Perspective" processing route Step 101 Registration Services "holding" the appointment data in Queue Step 120 Registration Services Re running validation rules for all Data Service Appointments that have been confirmed to check if they are still valid. Registration Services processing the appointment data, where the current Supplier ID matches the Supplier ID that requested a prospective Data Service appointment AND the Data Service Start Date equals the System Date + 1 but is less than the Supply End Date.
2 | BP003 -Step 130 | MHHS-BR-RS-064 | Registration Service (internal processing) | DIP | IF-037 | Registration Service sends "IF-037" to the DIP Registration Service must publish a Registration Service Notification of Service De-appointment using the appropriate interface on the Data Integration Platform where the end date for the incumbent Data Service has been confirmed by a CSS secured notification. | y | Registration Services sending the IF0-37 to the DIP
3 | BP003 -Step 140 - 145 | MHHS-BR-LD-004 | DIP | LDSO | PUB-037 | LDSO must obtain Data Service de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. In the case where Related MPANs or Import/Export linked MPANs exist, for the Advanced and UMS Market Segments, LDSO should expect to receive de-appointment notifications for all the MPANs in the Related MPAN or Import/Export group. | y | DIP sending PUB-036 to LDSO LDSO obtaining all recorded as defined by the requirement (MHHS-BR-LD-004) and updating their records accordingly
4 | BP003 -Step 140 - 146 BP003 -Step 140 - 96 BP003 -Step 140 -150 | NA | DIP | EES (Test Harness) End Old Data Service (Test Harness) End Suppler outgoing/incumbent (Test Harness) End | PUB-037 | DIP sends PUB-037 to EES (Test Harness) DIP sends PUB-037 to old Data Service (Test Harness) DIP sends PUB-037 to Suppler outgoing/incumbent (Test Harness) | n | DIP sends PUB-037 to EES (Test Harness) DIP sends PUB-037 to old Data Service (Test Harness) DIP sends PUB-037 to Suppler outgoing/incumbent (Test Harness)