## Sheet3 (hidden)
Proposed LDSO QT Scenario | SIT Scenario
Scenario ID | Scenario ID | SITFTS-0050
Role | Scenario Title | Create MPAN
Theme | Theme | New Connection
Business Process | Description | Create an MPAN through new connection process, appoint services and install meter. & Energise the MPAN
Functional Category | Functional Category | Create MPAN
Scenario Title | Functional Area 1 | New Connection |  |  | Business Process Steps
Description | Functional Area 2 | New MPAN, New Connection successful
Boundaries | Creator | Shaun Magee, Dan Gee |  |  | Interface Description
Test Case Variables | Priority | High |  |  | Regression flag
Optionality | Scenario size | Large
Number of test cases | Business Process | BP001, BP002, BP003, BP010B(Related), BP010C (Linked), BP009, BP008, (+BP003A for Smart meters) |  |  | Precondition Test Harness
Scenario size | Boundaries | Processing ends once the Meter is Installed (if not Unmetered) and Energisation has occurred |  |  | Precondition Other
Priority | Test Case Variables | (1) Smart, import+export, forward-dated (MPAN Creation current date)
Systems under test |  | (2) Traditional, single MPAN, forward-dated (MPAN Creation current date)
|  | (3) Advanced Single MPAN, forward-dated (MPAN Creation current date) |  |  | Test evidence
(4) Unmetered, single MPAN, forward-dated (MPAN Creation current date)
| Exception Codes | NA |  |  | Role (simulated)
LDSO Test Case | SIT Test Case
No.
Test Case Id | Test Case Id
Test Case Title | Test Case Title
Test Case Link | Test Case Link
Test Data Requirements | Test Data Requirements
Traceability Requirement |  |  | Test outcome
Test Harness |  |  | Test Harness
Key Validation & Test Evidence |  |  | Interface
BP Step |  |  | requirement
Service initiating process | SIT Test Steps |  | test evidence
Service Recepint Processor
Interface | Test Case Title |  | SITFTS-0050 - Smart Metered
Evidecne Reuiqred | Key Journey | Events | New MPAN Initial Registration - Start
| Step No. |  | 10
| Business Process |  | BP001
| BP Step |  | 5
| Traceability Requirement |  | MHHS-BR-LD-010.1 | MHHS-BR-LD-010.2
| Service Producing Trigger |  | LDSO
| Input/Trigger |  | DB01
| Message Input Event Code |  | N/A
| Service Recipient Processor of Input/Trigger |  | REGS
| Test Step |  | LDSO creates 2 MPAN'S for Import/Export linked MPAN and issues DB01 REGS
| Key Validation & Test Evidence |  | Import/Export Mpan creation and linkage required
| Evidence | Required | Y

## Cover Sheet
LDSO QT - Test Scenarios
Version | Description | Author | Status | Date
V 0.1 | Initial Draft of BP003 Test Scenarios | Non SIT LDSO QT Test Team |  | 2024-01-19
| Review by SIT |  |  | 2024-01-23
V0.2 | Amendments - incorporating SIT comments | Non SIT LDSO QT Test Team |  | 2024-01-24
V0.3 | Amendments - incorporating changes after clarifications from Design Team | Non SIT LDSO QT Test Team | In Progress | 2024-01-29
v0.4 | Amendments after Code Bodies Review & Final check |  |  | 2024-01-31
| Amendments made after data team input |  |  | 2024-02-07
| Start Test Cases |  |  | 12/02.2024
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## TC_BP003_06_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP003_06_01 | Registration Service sending an Appointment Status Notification to the new data service and Supplier (Test Harness) for lapsed appointments | TS_BP003_06 | • Segment S • Liked Import/Export MPANs • "Perspective" processing. • Lapse Condition = Registration Service must lapse prospective appointment requests, following receipt of the CSS COS secured notifications and checking for appointments to process, where remaining prospective appointment start dates can no longer be achieved (Data Service Appointment Start Date <= System Date) (62) Pre requisites. IF-031 with the following characteristics • (DI-999)Event Code = [DSApp] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed DS Effective From Date" = (as per the condition for "Perspective" processing) IF-032 accepted response (response to IF-031) with the following characteristics • (DI-999)Event Code = [DSAppInitialResp] • (DI-979) Response Code = Accepted IF-033 with the following characteristics • (DI-999)Event Code = [DSAppSPRequest] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed DS Effective From Date" = (as per the condition for "Perspective" processing) • (DI-979) Response Code = Accepted IF-034 accepted response (response to IF-033) with the following characteristics • (DI-999)Event Code = [DSAppSPResponse] • (DI-979) Response Code = Accepted Test data The "IF-035 Registration Service Appointment Status Notification" from the Registration Services the new Data Service (Test Harness) and Suppler (Test Harness). • (DI-999) Event Code = [DSAppLapsed] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) | The "IF-035 Registration Service Appointment Status Notification" from the Registration services sending to the new data service and Supplier (Test Harness) for lapsed appointments
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP003 -Step 100 | MHHS-BR-RS-054 (Perspective) MHHS-BR-RS-055 (Lapsed) | Registration Service (internal processing) | Registration Service (internal processing) | NA | (54) Registration Service must, in cases where the proposed Data Service appointment is accepted, determine the processing path to be followed: •"Prospective" Processing (55) Registration Service must, where more than one Data Service appointment request is received from the same Supplier for the same MPAN and for the same date, take the last received Data Service appointment (based on the Sender timestamp) as containing the correct information. (For this Req this might actually happen on Step 40) | y | Registration Services taking the data through the "Perspective" processing route Registration Service receives two Data Service appointment request from the same Supplier for the same MPAN and for the same date, takes the last received Data Service appointment (based on the Sender timestamp)as containing the correct information. The data for that record is moved to the next step. (This might actually happen on Step 40)
2 | BP003 -Step 101 | MHHS-BR-RS-056 (Perspective) | Registration Service (internal processing) | Registration Service (internal processing) | NA | (56) Registration Service must be able to hold Prospective Data Service appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received. | y | Registration Services "holding" the appointment data in Queue
3 | BP003 -Step 120 | MHHS-BR-RS-058 (Perspective) MHHS-BR-RS-062 (Lapse) | Registration Service (internal processing) | Registration Service (internal processing) | NA | (61) Registration Service must re-run validation, in line with the validation rules set out in the appropriate interface specification, for all Data Service appointments that have been confirmed to re-process from the Prospective Appointment Queue, to ensure that the appointment is still valid (62) Registration Service must lapse prospective appointment requests, following receipt of the CSS COS secured notifications and checking for appointments to process, where remaining prospective appointment start dates can no longer be achieved (Data Service Appointment Start Date <= System Date) | y | Registration Services Re running validation rules for all Data Service Appointments that have been confirmed to check if they are still valid. Registration Services determines the appointment to be lapsed
4 | BP003 -Step 210 | MHHS-BR-RS-066 (Lapsed) | Registration Service | DIP | IF-035 | Registration Service sends "IF-035" to the DIP Registration Service must publish a Registration Service Appointment Status Notification (DSAppLapsed) using the appropriate interface on the Data Integration Platform where the proposed Data Service appointment has lapsed or is rejected following failed validation | y | Registration Services sending the IF0-35 to the DIP
5 | BP003 -Step 215 -231 BP003 -Step 140 -150 | NA | DIP | New Data Service (Test Harness) End Suppler (Test Harness) End | PUB-035 | DIP sends PUB-035 to new Data Service (Test Harness) DIP sends PUB-035 to Suppler(Test Harness) | n | DIP sends PUB-035 to new Data Service (Test Harness) DIP sends PUB-035 to Suppler(Test Harness)

## TC_BP003_06_02
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP003_06_02 | Registration Service sending an Appointment Status Notification to the new data service and Supplier (Test Harness) for lapsed appointments | TS_BP003_06 | • Segment A • Liked Related MPANs • "Perspective" processing. • Lapse Condition = Registration Service must lapse prospective appointment requests following receipt of the CSS COS secured notifications, where the existing Supplier requested the new Data Service Appointment, but the Appointment Start Date is greater than or equal to the Supply End Date.(63) Pre requisites. IF-031 with the following characteristics • (DI-999)Event Code = [DSApp] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed DS Effective From Date" = (as per the condition for "Perspective" processing) IF-032 accepted response (response to IF-031) with the following characteristics • (DI-999)Event Code = [DSAppInitialResp] • (DI-979) Response Code = Accepted IF-033 with the following characteristics • (DI-999)Event Code = [DSAppSPRequest] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) • (DI-833) "Proposed DS Effective From Date" = (as per the condition for "Perspective" processing) • (DI-979) Response Code = Accepted IF-034 accepted response (response to IF-033) with the following characteristics • (DI-999)Event Code = [DSAppSPResponse] • (DI-979) Response Code = Accepted Test data The "IF-035 Registration Service Appointment Status Notification" from the Registration Services the new Data Service (Test Harness) and Suppler (Test Harness). • (DI-999) Event Code = [DSAppLapsed] • (DI-800) Service Provider Appointment Scenario = COS (Change of Supply) | The "IF-035 Registration Service Appointment Status Notification" from the Registration services sending to the new data service and Supplier (Test Harness) for lapsed appointments
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP003 -Step 100 | MHHS-BR-RS-054 (Perspective) MHHS-BR-RS-055 (Lapsed) | Registration Service (internal processing) | Registration Service (internal processing) | NA | (54) Registration Service must, in cases where the proposed Data Service appointment is accepted, determine the processing path to be followed: •"Prospective" Processing (55) Registration Service must, where more than one Data Service appointment request is received from the same Supplier for the same MPAN and for the same date, take the last received Data Service appointment (based on the Sender timestamp) as containing the correct information. (For this Req this might actually happen on Step 40) | y | Registration Services taking the data through the "Perspective" processing route Registration Service receives two Data Service appointment request from the same Supplier for the same MPAN and for the same date, takes the last received Data Service appointment (based on the Sender timestamp)as containing the correct information. The data for that record is moved to the next step. (this might actually happen on Step 40)
2 | BP003 -Step 101 | MHHS-BR-RS-056 (Perspective) | Registration Service (internal processing) | Registration Service (internal processing) | NA | (56) Registration Service must be able to hold Prospective Data Service appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received. | y | Registration Services "holding" the appointment data in Queue
3 | BP003 -Step 120 | MHHS-BR-RS-058 (Perspective) MHHS-BR-RS-063 (Lapsed) | Registration Service (internal processing) | Registration Service (internal processing) | NA | (61) Registration Service must re-run validation, in line with the validation rules set out in the appropriate interface specification, for all Data Service appointments that have been confirmed to re-process from the Prospective Appointment Queue, to ensure that the appointment is still valid (63) Registration Service must lapse prospective appointment requests following receipt of the CSS COS secured notifications, where the existing Supplier requested the new Data Service Appointment, but the Appointment Start Date is greater than or equal to the Supply End Date. | y | Registration Services Re running validation rules for all Data Service Appointments that have been confirmed to check if they are still valid. Registration Services determines the appointment to be lapsed
4 | BP003 -Step 210 | MHHS-BR-RS-066 (Lapsed) | Registration Service | DIP | IF-035 | Registration Service sends "IF-035" to the DIP Registration Service must publish a Registration Service Appointment Status Notification (DSAppLapsed) using the appropriate interface on the Data Integration Platform where the proposed Data Service appointment has lapsed or is rejected following failed validation | y | Registration Services sending the IF0-35 to the DIP
5 | BP003 -Step 215 -231 BP003 -Step 140 -150 | NA | DIP | New Data Service (Test Harness) End Suppler (Test Harness) End | PUB-035 | DIP sends PUB-035 to new Data Service (Test Harness) DIP sends PUB-035 to Suppler(Test Harness) | n | DIP sends PUB-035 to new Data Service (Test Harness) DIP sends PUB-035 to Suppler(Test Harness)