## CoverSheet
QT - Test Scenarios
Version | Description | Author | Date
v0.1 | Initial Draft | Expleo Test Team | 2024-03-08
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## Test Scenario BP005
Test Scenario ID | Role (s) | Theme | Business Process | Functional Category | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scnarios Size) | Priority | Expleo Comments
TS_BP005_001 | LDSO | Data Processing | BP005 Data Processing |  | LDSO receive the level consumption data | DIP will receive the UTC Period level consumption data from Data services via IF-21 after Data Services submitted the valid consumption data to settlements. DIP will then publish the UTC period level consumption data to the relevant parties. All parties including LDSO will then receive the UTC period level consumption data | Start point The start point for this scenario would be Data Services (Test Harness) submitting the UTC period level consumption data to LDSO and all the other relevant parties via the DIP End point The end point for this scenario would be the LDSO as well as the (Test Harnesses) BSC Central Settlements and Supplier will receive PUB-021 via the DIP to confirm that they have received the UTC period level consumption data | • Segment U • Segment S • Segment A • Segment A - Reactive Power |  | 5 | M | M
TS_BP005_002 | LDSO | Data Processing - Read Sharing | BP005 Data Processing |  | LDSO receiving cumulative readings | Data services have received cumulative read data which have been recovered from a meter. This read data will then validated following the validation and estimation method statement. Once successful, Data Services will issue a IF-041 to DIP and DIP will send the readings to LDSO | Start point The start point for this scenario would be Data Services (Test Harness) submitting the cumulative readings to LDSO and all the other relevant parties via the DIP End point The end point for this scenario would be the LDSO as well as the (Test Harness) Supplier will receive PUB-041 via the DIP to confirm that they have received the cumulative read data | • Segment S - Smart • Segment A |  | 2 | M | M
TS_BP005_003 | LDSO | Data Processing - Sharing of Annual Consumption | BP005 Data Processing |  | LDSO and Registration Services receiving an Annual Consumption | BSC Central Settlement will calculate an annual consumption and send it to DIP. DIP will receive this via IF-040 and then issue this via PUB-040 to LDSO and registration services as well as all the relevant parties. | Start point The start point for this scenario would be Central Settlement (Test Harness) submitting Annual Consumption to LDSO, registration services and all the other relevant parties via the DIP End point The end point for this scenario would be the LDSO, Registration Services and all the relevant parties will receive PUB-040 via the DIP to confirm that they have received the Annual Consumption | • Segment S - Smart • Segment A |  | 2 | M | M
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be a unique ID and created when each scenario is added
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be the participants role in delivery Multiple roles could be covered in 1 scenario
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each scenario will be linked to Business Processes
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The test scenario description field will outline the objective of the test
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The field will show any other variance related to the test scenario which needs to be considered
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The number of test cases created/related to the test scenario
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This field will outline the size and difficulty of the test scenario Will be flagged as S, M & L
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will outline the priority of the test scenario Flagged as VH, H, M & L

## BP005_03_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP005_03_01 | LDSO and Registration Services receiving an Annual Consumption - Segment S - Smart | TS_BP005_03 | Test Data • Segment S - Smart • Single MPAN Data Items for IF-040 • DI-999 Event Code - [ReadingOnSite] • DI-088 - Cumulative Register Reading | LDSO and Registration Services receiving an Annual Consumption
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 400 to 410 | N/A | Central Settlement (Test Harness) | DIP | IF-040 | Central Settlement have calculated the annual consumption and sent it to DIP via IF-40. DIP has received this. | N | Not required
2 | 410 to 420 420 to 470 | MHHS-BR-AC-009 | DIP | LDSO | PUB-040 | DIP have publish the annual consumption to LDSO via PUB-041 and LDSO has received the annual consumption | Y | To ensure that the data from DIP to LDSO has been received and their systems have been updated
3 | 410 to 420 420 to 450 | MHHS-BR-AC-006 MHHS-BR-AC-007 | DIP | Registration Services | PUB-040 | DIP has publish the annual consumption to Registration Services via PUB-041 and Registration Services has received the annual consumption | Y | To ensure that the data from DIP to Registration Services has been received and their systems have been updated
4 | 410 to 420 420 to 460, 471, 430 & 440 | N/A | DIP | Supplier (Test Harness) EES (Test Harness) Data Services (Test Harness) UMSDS (Test Harness) | PUB-040 | DIP has publish the annual consumption to the other relevant parties via PUB-041 and those parties have received the annual consumption | N | Not required

## BP005_03_02
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP005_03_01 | LDSO and Registration Services receiving an Annual Consumption - Segment A - Advanced | TS_BP005_03 | Test Data • Segment A - Advanced • Linked MPAN - 2 MPANs required Data Items for IF-040 • DI-999 Event Code - [DSEstimate] • DI-094 - Reading Method - E = Estimate by SDS | LDSO and Registration Services receiving an Annual Consumption
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 400 to 410 | N/A | Central Settlement (Test Harness) | DIP | IF-040 | Central Settlement have calculated the annual consumption and sent it to DIP via IF-40. DIP has received this. | N | Not required
2 | 410 to 420 420 to 470 | MHHS-BR-AC-009 | DIP | LDSO | PUB-040 | DIP have publish the annual consumption to LDSO via PUB-041 and LDSO has received the annual consumption | Y | To ensure that the data from DIP to LDSO has been received their systems have been updated
3 | 410 to 420 420 to 450 | MHHS-BR-AC-006 MHHS-BR-AC-007 | DIP | Registration Services | PUB-040 | DIP has publish the annual consumption to Registration Services via PUB-041 and Registration Services has received the annual consumption | Y | To ensure that the data from DIP to Registration Services has been received their systems have been updated
4 | 410 to 420 420 to 460, 471, 430 & 440 | N/A | DIP | Supplier (Test Harness) EES (Test Harness) Data Services (Test Harness) UMSDS (Test Harness) | PUB-040 | DIP has publish the annual consumption to the other relevant parties via PUB-041 and those parties have received the annual consumption | N | Not required