## CoverSheet
QT - Test Scenarios
Version | Description | Author | Date
v0.1 | Initial Draft | Non SIT LDSO QT Test Team | 2022-11-29
v2.0 | Updated following the review with Code Bodies | Non SIT LDSO QT Test Team | 2024-01-31
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## BP007 Test Scenarios
Test Scenario ID | Role (s) | Theme | Business Process | Functional Category | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scenarios Size) | Priority | Expleo Comments
TS_BP007_001 | LDSO/Registration Services | Metering Changes | BP007 Disconnection |  | LDSO intitated discconection | LDSO initiates meter disconnection process. Registration services request for a change of MPAN/RMP status in EES (Test Harness). LDSO, EES (Test Harness) and Supplier (Test Harness) will receive notification that disconnection has been updated with the Registration Service | Harness as end point for EES | - MPAN created in error - No active Supplier • Metered • UMS-Only is Unmetered • Customer initiated disconnection - (passing through UMSO double check that this is UMSO and back to LDSO) - Customer requests disconnection - Disconnection Accepted Emergency disconnections |  | 7 | M | L | Should testing start from Step 31 or from Step 70? How do we test Step 32? LDSO may need to disconnect sites in emergency scenarios. Where an LDSO has initiated a disconnection in cases of emergency they must where possible update the Metering Service of the meter removal Systems not in scope • Suppler • EES Disconnect meter point (Step 40) will run through to registration services via Internal DB03 start the Disconnection (Step 70) • Step 126 (DIP) Publish Change MPAN/RMP Status (MHHS-IF-050) TO • Step 127 (EES) Receive Change to MPAN/RMP Status (PUB-050) (END) All Business process are not in scope for LDSO QT BSC Aseessment Criteria
TS_BP007_002 | LDSO/Registration Services | Metering Changes | BP007 Disconnection |  | LDSO disconnects meter point - Receive Disconnection Publication via subscription service | LDSO initiates meter disconnection process to update the registrations system. LDSO receives notification that the disconnection has been updated with Registration Service | Harness as end point for a Supplier and end point for EES | • Non-Metered - Manage Failure message (validation) - Notification received in LDSO - MPAN created in error - No active Supplier • Metered - Manage Failure message (validation) - Notification received in LDSO • UMS-Only - Manage Failure message (validation) - Notification received in LDSO • Customer initiated disconnection - (passing through UMSO and back to LDSO) - Customer requests disconnection - Disconnection Accepted Failure scenarios |  | 5 | M | L | Should testing start from Step 31 or from Step 70? How do we test Step 32? LDSO may need to disconnect sites in emergency scenarios. Where an LDSO has initiated a disconnection in cases of emergency they must where possible update the Metering Service of the meter removal Disconnect meter point (Step 40) will run through to registration services via Internal DB03 start the Disconnection (Step 70) • Step 85 - (DIP) DIP will publish the disconnection notification (MHHS-IF-009) but will fail validation TO • Step 90 - Registration Service will receive a failed message from DIP where the Registration Notification of Disconnection has failed validation (END) All Business process are not in scope for LDSO QT BSC Aseessment Criteria apart from MHHS-BR-RS-137
TS_BP007_003 | LDSO/UMSO | Metering Changes | BP007 Disconnection |  | UMSO notify customer of disconnection | UMSO have received a request from LDSO to initiate disconnection via an agreed communication method (email). UMSO will then notify the customer of the disconnection ( to be reviewed and possibly inlcuded in the scenarios 2) | N/A | • UMS-Only |  | 1 | M | L | How is step 30 tested? What has triggered step 30 to initiate disconnection? All Business process are not in scope for LDSO QT BSC Aseessment Criteria
TS_BP007_004 | LDSO | Metering Changes | BP007 Disconnection |  | Customer requests disconnection - Disconnection Rejected - Notify customer | Customer requests for the MPAN to be disconnected via an agreed communication method (email). LDSO will receive the request to disconnect the meter point from customers. If the disconnection process has been rejected from LDSO, LDSO will inform the customer via the agreed communication method that the ( how to do that) disconnection will not be actioned. | Harness as end point for a Supplier | • Customer initiated - Customer notified of rejection - Manage customers disconnection request |  | 2 | M | L | All Business process are not in scope for LDSO QT BSC Aseessment Criteria
TS_BP007_005 | LDSO/Registration Services | Metering Changes | BP007 Disconnection |  | Update Registration - Deactivate | Registration services will receive a CSS2860 to inform them of an MPAN deactivation. LDSO will then receive notification that the Registration has been De-activated | Harness as start point for CSS Harness as end point for Central Settlement, ESS & Supplier | • Update registration - publish deactivation notification |  | 1 | M | L | All Business process are not in scope for LDSO QT BSC Aseessment Criteria
TS_BP007_006 | LDSO/UMSO/Registration Services | Metering Changes | BP007 Disconnection |  | Update Registration - De-appoint services - Deactivate | Registration services will receive a CSS2860 to inform them of an MPAN deactivation. Registration Service will send out the de-appointment notification to the service providers. UMSO and LDSO will receive notification that all appointed services have been de-appointed | Harness as start point for CSS Harness as end point for Central Settlement, ESS & Supplier | • Update registration - LDSO receives notification to de-appoint - UMSO receives notification to de-appoint |  | 2 | M | L | All Business process are not in scope for LDSO QT BSC Aseessment Criteria
[9 empty] | Total TC | 23
TS_BP07_01 | LDSO/UMSO/Registration Services | Metering Changes | BP007 Disconnection |  | LDSO Initiated Disconnection | In this scenario a LDSO is initiating, either for a UMS, metered or non-metered site, a disconnection of a metering point and issuing DB03 messages to registration services. Registration services generating Notification of LDSO Disconnection / CSS De-Registration and ESS Updates messages and this being published and received by LDSO, ESS & Supplier. For UMS site, this scenario would also include UMSO initiating disconnection and informing customer. | Start point The starting point for this scenario would be LDSO initiating disconnection. End point The end point this for scenario would be (PUB-09) LDSO Disconnection / CSS De-Registration received by LDSO End point for out of scope roles (PUB-050) ESS update being received by ESS (Test Harness) (PUB-09) LDSO Disconnection / CSS De-Registration received by ESS & Supplier (Test Harness) | Where this disconnection is initiated by LDSO for UMS site. This variance would cover LDSO/UMSO/Registration Services Where this disconnection is initiated by LDSO for metered site. This variance would cover LDSO/ Registration Services Where this disconnection is initiated by LDSO and there is no meter on site. This variance would cover LDSO/Registration Services Where this disconnection is initiated by LDSO and registration Service has received a failed message where the Registration Notification of Disconnection has failed DIP validation. | If LDSO has opted out of receiving PUB-009, they do not need to run this test via DIP but should provide evidence of receiving this information via alternative mechanism | 4 | M
TS_BP07_02 | LDSO/UMSO/Registration Services | Metering Changes | BP007 Disconnection |  | Supplier and Customer Initiated Disconnection | In this scenario a Supplier or a Customer is initiating, either for a UMS or metered, a disconnection of a metering point to LDSO. LDSO either accepting issuing DB03 messages to registration services or confirming rejection back to the supplier or customer. If accepted, Registration services generating Notification of LDSO Disconnection / CSS De-Registration and ESS Updates messages and this being published and received by LDSO, ESS & Supplier. For UMS site, this scenario would also include UMSO initiating disconnection and informing customer. | Start point The starting point for this scenario would be LDSO receiving initiating disconnection request from either a supplier or a customer. End point The end point this for scenario would be (PUB-09) LDSO Disconnection / CSS De-Registration received by LDSO End point for out of scope roles (PUB-050) ESS update being received by ESS (Test Harness) (PUB-09) LDSO Disconnection / CSS De-Registration received by ESS & Supplier (Test Harness) | Where this disconnection is initiated by customer for UMS site and is accepted by LDSO. This variance would cover LDSO/UMSO/Registration Services Where this disconnection is initiated by customer for UMS site and is rejected by LDSO. This variance would cover LDSO/UMSO/Registration Services Where this disconnection is initiated by customer for metered site and is accepted by LDSO. This variance would cover LDSO/ Registration Services. Where this disconnection is initiated by customer for metered site and is rejected by LDSO. This variance would cover LDSO/ Registration Services. Where this disconnection is initiated by as supplier for UMS site and is accepted by LDSO. This variance would cover LDSO/UMSO/Registration Services. Where this disconnection is initiated by supplier for UMS site and is rejected by LDSO. This variance would cover LDSO/UMSO/Registration Services Where this disconnection is initiated by supplier for metered site and is accepted by LDSO. This variance would cover LDSO/ Registration Services. Where this disconnection is initiated by supplier for metered site and is rejected by LDSO. This variance would cover LDSO/ Registration Services. Where this disconnection is initiated by either customer or a supplier and registration Service has received a failed message where the Registration Notification of Disconnection has failed DIP validation. | If LDSO has opted out of receiving PUB-009, they do not need to run this test via DIP but should provide evidence of receiving this information via alternative mechanism | 9 | M
TS_BP07_03 | LDSO/UMSO/Registration Services | Metering Changes | BP007 Disconnection |  | Registration Services sending Notification of LDSO Disconnection / CSS De-Registration and Notification of De-Appointment. | In this scenario a registration services is updating the MPAN is deactivated and sending a Notification of LDSO Disconnection / CSS De-Registration and Notification of De-Appointment. LDSO and UMSO is receiving a Notification of De-Appointment. | Start point The start point of this scenario is registration Services updating that an MPAN is deactivated. The CSS message CSS2860 will not be stubbed by programme provided test harnesses. LDSO may need to simulate this themselves. The end point this for scenario would be (PUB-37) Notification of De-Appointment received by LDSO End point for out of scope PUB-37) Notification of De-Appointment received by Data Service, Supplier and metering services (test Harness) (PUB-09) LDSO Disconnection / CSS De-Registration received by ESS (Test Harness)& Central Settlement Systems. |  | If LDSO has opted out of receiving PUB-037, they do not need to run this test via DIP but should provide evidence of receiving this information via alternative mechanism | 2 | L
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be a unique ID and created when each scenario is added
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be the participants role in delivery Multiple roles could be covered in 1 scenario
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each scenario will be linked to Business Processes
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The test scenario description field will outline the objective of the test
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The field will show any other variance related to the test scenario which needs to be considered
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The number of test cases created/related to the test scenario
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This field will outline the size and difficulty of the test scenario Will be flagged as S, M & L
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will outline the priority of the test scenario Flagged as VH, H, M & L

## BP007_01_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP007_01_01 | LDSO Initiated Disconnection - UMS site | TS_BP007_01 | Test Data • Segment U - UMSO • Single MPAN Data for IF-050 • DI-999 - Event Code = [MPStatusChange] • DI-131 - MP Status - X = Disconnected Data for IF-009 • DI-999 - Event Code = [MPANDisconnection] • DI-027 - Disconnection Effective From Date | LDSO initiated Disconnection - UMS Site PUB-009 LDSO Disconnection being received by LDSO, ESS (Test Harness) & Supplier (Test Harness) PUB-050 ESS (Test Harness) has been updated and received change of MPAN status
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 30 to 40 | MHHS-BR-LD-013 MHHS-BR-LD-014 MHHS-BR-MS-038 | UMSO | LDSO | UMS Only/Agreed method of communication | LDSO received notification from UMSO to initiate disconnection | Y | Need to ensure that the notification that the agreed method of communication has been sent from UMSO to the recipient LDSO. Both evidences are required
2 | 40 to 70 | MHHS-BR-LD-015 MHHS-BR-LD-018 | LDSO | Registration Services | Internal DB03 | LDSO has physically disconnected the connection to the property and sent an update to registration services | Y | To ensure that the process between LDSO and RS has been successful
3 | 70 to 126 | MHHS-BR-RS-097 MHHS-BR-RS-098 MHHS-BR-RS-099 | Registration Services | DIP | MHHS-IF-050 | Registration services has received the update that the meter point have been disconnected. They will send MHHS-IF-050 to DIP | Y | Need to ensure that registration services has received the update to disconnect and the MHHS-IF-050 messages have been sent to DIP
4 | 127 | N/A | DIP | EES (Test Harness) | PUB-050 | EES (Test Harness) received PUB-050 notification of change of MPAN/RMP status | N | Not required
5 | 70 to 85 | MHHS-BR-RS-097 MHHS-BR-RS-098 MHHS-BR-RS-099 | Registration Services | DIP | MHHS-IF-009 | Registration services has received the update that the meter point have been disconnected. They will send MHHS-IF-009 to DIP | Y | Need to ensure that registration services has received the update to disconnect and the MHHS-IF-009 messages have been sent to DIP
6 | 85 to 86 | MHHS-BR-LD-020 | DIP | LDSO | PUB-009 | LDSO have received notification from the DIP that the disconnection has been updated with the Registration Service | Y | Need to ensure that LDSO have received the notification of the update for the disconnection and LDSO system has been updated
7 | 85 to 86, 87 & 95 | N/A | DIP | Supplier (Test Harness) EES (Test Harness) | PUB-009 | DIP will publish the disconnection notification to the recipients | N | Not required

## BP007_01_02
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP007_01_02 | LDSO Initiated Disconnection - Metered | TS_BP007_01 | Test Data • Segment A - Advanced • Linked MPAN Data for IF-050 • DI-999 - Event Code = [MPStatusChange] • DI-131 - MP Status - X = Disconnected Data for IF-009 • DI-999 - Event Code = [MPANDisconnection] • DI-027 - Disconnection Effective From Date | LDSO initiated Disconnection - Metered PUB-009 LDSO Disconnection being received by LDSO, ESS (Test Harness) & Supplier (Test Harness) PUB-050 ESS (Test Harness) has been updated and received change of MPAN status
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 32 to 40 | MHHS-BR-LD-015 | LDSO | LDSO | N/A | LDSO has initiated a disconnection on a metered site | Y | Need to ensure that the notification that the agreed method of communication has been sent from UMSO to the recipient LDSO. Both evidences are required
2 | 40 to 70 | MHHS-BR-LD-015 MHHS-BR-LD-018 | LDSO | Registration Services | Internal DB03 | LDSO has physically disconnected the connection to the property and sent an update to registration services | Y | To ensure that the process between LDSO and RS has been successful
3 | 70 to 126 | MHHS-BR-RS-097 MHHS-BR-RS-098 MHHS-BR-RS-099 | Registration Services | DIP | MHHS-IF-050 | Registration services has received the update that the meter point have been disconnected. They will send MHHS-IF-050 to DIP | Y | Need to ensure that registration services has received the update to disconnect and the MHHS-IF-050 messages have been sent to DIP
4 | 127 | N/A | DIP | EES (Test Harness) | PUB-050 | EES (Test Harness) received PUB-050 notification of change of MPAN/RMP status | N | Not required
5 | 70 to 85 | MHHS-BR-RS-097 MHHS-BR-RS-098 MHHS-BR-RS-099 | Registration Services | DIP | MHHS-IF-009 | Registration services has received the update that the meter point have been disconnected. They will send MHHS-IF-009 to DIP | Y | Need to ensure that registration services has received the update to disconnect and the MHHS-IF-009 messages have been sent to DIP
6 | 85 to 86 | MHHS-BR-LD-020 | DIP | LDSO | PUB-009 | LDSO have received notification from the DIP that the disconnection has been updated with the Registration Service | Y | Need to ensure that LDSO have received the notification of the update for the disconnection
7 | 85 to 86, 87 & 95 | N/A | DIP | Supplier (Test Harness) EES (Test Harness) | PUB-009 | DIP will publish the disconnection notification to the recipients | N | Not required

## BP007_01_03
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP007_01_03 | LDSO Initiated Disconnection - No Meter on site | TS_BP007_01 | Test Data • Segment S - No smart meter fitted • Related MPAN Data for IF-050 • DI-999 - Event Code = [MPStatusChange] • DI-131 - MP Status - X = Disconnected Data for IF-009 • DI-999 - Event Code = [MPANDisconnection] • DI-027 - Disconnection Effective From Date | LDSO initiated Disconnection - No Meter on site PUB-009 LDSO Disconnection being received by LDSO, ESS (Test Harness) & Supplier (Test Harness) PUB-050 ESS (Test Harness) has been updated and received change of MPAN status
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 35 to 40 | MHHS-BR-LD-015 | LDSO | LDSO | N/A | LDSO has initiated an MPAN disconnection on a non-metered site | Y | Need to ensure that the notification that the agreed method of communication has been sent from UMSO to the recipient LDSO. Both evidences are required
2 | 40 to 70 | MHHS-BR-LD-015 MHHS-BR-LD-018 | LDSO | Registration Services | Internal DB03 | LDSO has physically disconnected the connection to the property and sent an update to registration services | Y | To ensure that the process between LDSO and RS has been successful
3 | 70 to 126 | MHHS-BR-RS-097 MHHS-BR-RS-098 MHHS-BR-RS-099 | Registration Services | DIP | MHHS-IF-050 | Registration services has received the update that the meter point have been disconnected. They will send MHHS-IF-050 to DIP | Y | Need to ensure that registration services has received the update to disconnect and the MHHS-IF-050 messages have been sent to DIP
4 | 127 | N/A | DIP | EES (Test Harness) | PUB-050 | EES (Test Harness) received PUB-050 notification of change of MPAN/RMP status | N | Not required
5 | 70 to 85 | MHHS-BR-RS-097 MHHS-BR-RS-098 MHHS-BR-RS-099 | Registration Services | DIP | MHHS-IF-009 | Registration services has received the update that the meter point have been disconnected. They will send MHHS-IF-009 to DIP | Y | Need to ensure that registration services has received the update to disconnect and the MHHS-IF-009 messages have been sent to DIP
6 | 85 to 86 | MHHS-BR-LD-020 | DIP | LDSO | PUB-009 | LDSO have received notification from the DIP that the disconnection has been updated with the Registration Service | Y | Need to ensure that LDSO have received the notification of the update for the disconnection
7 | 85 to 86, 87 & 95 | N/A | DIP | Supplier (Test Harness) EES (Test Harness) | PUB-009 | DIP will publish the disconnection notification to the recipients | N | Not required

## BP007_01_04
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP007_01_04 | LDSO Initiated Disconnection - No Meter on site - Failed Validation | TS_BP007_01 | Test Data • Segment S - No smart meter fitted • Related MPAN Data for IF-050 • DI-999 - Event Code = [MPStatusChange] • DI-131 - MP Status - X = Disconnected Data for IF-009 • DI-999 - Event Code = [MPANDisconnection] • DI-027 - Disconnection Effective From Date - Invalid date to be entered | Registration Services have received a failure notification that the disconnection has failed DIP validation
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 31 to 35 | MHHS-BR-LD-015 | LDSO | LDSO | N/A | LDSO has initiated an MPAN disconnection on a non-metered site | Y | Need to ensure that the notification that the agreed method of communication has been sent from UMSO to the recipient LDSO. Both evidences are required
2 | 40 to 70 | MHHS-BR-LD-015 MHHS-BR-LD-018 | LDSO | Registration Services | Internal DB03 | LDSO has physically disconnected the connection to the property and sent an update to registration services | Y | To ensure that the process between LDSO and RS has been successful
3 | 70 to 85 | MHHS-BR-RS-097 MHHS-BR-RS-098 MHHS-BR-RS-099 | Registration Services | DIP | MHHS-IF-009 | Registration services has received the update that the meter point have been disconnected. They will send MHHS-IF-009 to DIP | Y | Need to ensure that registration services has received the update to disconnect and the MHHS-IF-009 messages have been sent to DIP
4 | 85 to 90 | MHHS-BR-RS-137 | DIP | Registration Services | PUB-009 | Registration Service should receive a failed message from DIP where the Registration Notification of Disconnection has failed DIP validation | Y | This needs to be captured to ensure that the registration services has received the failure of disconnection message from DIP for failed validation