## Cover Sheet
LDSO QT - Test Cases
Version | Description | Author | Status | Date
1 | Start Test Cases | Non SIT QT Team |  | 2024-02-16
2 | Test Lead Review | Non SIT QT Team |  | 2024-02-19
3 | Review Comments Incorporated | Non SIT QT Team |  | 2024-02-20
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## BP008 Test Scenarios
Test Scenario ID | LDSO Role (s) | Theme | Business Process | Steps | Requirements | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scenarios Size) | Priority | Expleo Comments
TS_BP008_01 | LDSO | Metering Changes | BP008 - Change of Energisation Status | START • Step 10 (Request Energisation Status Change) • Step 15 (Manage Request for Energisation Status Change) • Step 20 (Energisation Status Outcome & Reading(s) if Required) • Step 30 (Manage Energisation Change Request Outcome) END | • MHHS-BR-LD-022 • MHHS-BR-LD-023 | Metered Supply: Validate that the LDSO issues response to the Energisation Change Request | In this scenario, a Supplier (Test Harness) is generating an Energisation Change request to the LDSO who will receive, process a change in energisation status, and issue the out come of the request and readings (if required) to the Metering Service (Test Harness) | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Supplier (test harness) generating the initial Energisation Change request to the LDSO. (D0134) End Point The end point will be the LDSO sending the response to the request to Metering Service (Test Harness). | • Where the Supplier request has initiated the request for Segment S (Smart) and Energisation Status "E - Energised" • Where the Supplier has initiated the request for Non Smart Meters and Energisation Status "E - Energised" • Where the Supplier has initiated the request for Segment A (Advanced) and Energisation Status "D - De-Energised" |  | 3 | M | VH
TS_BP008_02 | UMSO/Registration Service | Metering Changes | BP008 - Change of Energisation Status | START • Step 64 (START POINT) • Step 65 (Request from LDSO/Supplier/Customer OR UMSO initiated Change in energisation) • Step 70 (Logical Change) • Step 75 (Data Collection BP004) • Step 80 (Update Registrations with Change in Energisation status) • Step 90 (DIP) (Publish Updates of Energisation status) • Step 95 (Supplier) (Rejection or unable to action received from MS/LDSO) • Step 105 (Registration Service) (Receive Update of Energisation status via subscription) END | • MHHS-BR-MS-047 • MHHS-BR-MS-048 • MHHS-BR-MS-049 • MHHS-BR-RS-104 | Unmetered Supply: Validate that the Registration Service will Receive Change of Energisation Via Subscription from UMSO for an accepted request and rejected request will be received by Supplier (Test Harness) | In this scenario, Registration Service will Receive Change of Energisation Via Subscription from UMSO Once, UMSO has received the request to change the energisation, it will make the logical changes in their system. Once the change has been made, the UMSO will send the updates to the UMSDS and the Registration Service with the new energisation status via the DIP. Any request that has received "Rejected" response or "Unable to Action Request" response will go to Supplier (Test Harness). | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the UMSO receiving Change of Energisation initiated from either Supplier (Test Harness), LDSO, Customer or UMSO. End Point The end point will be the Registration Service receiving Change of Energisation Via Subscription Service. Any request that has received "Rejected" response or "Unable to Action Request" response will go to Supplier (Test Harness). | • An accepted response for request initiated by Supplier for Segment U (UMSO) and Energisation Status "E - Energised" • An accepted response for request initiated by LDSO for Segment U (UMSO) and Energisation Status "D - De-Energised" |  | 2 | M | VH
TS_BP008_03 | Registration Service/LDSO/UMSO | Metering Changes | BP008 - Change of Energisation Status | START • Step 105 (Receive Update of Energisation status via subscription) • Step 110 (Registrations validation) • Step 115 (Update Energisation Change/correction) • Step 125 (Energisation Status Change Outcome) • Step 135 (Publish Update of Energisation status Acceptance) • Step 165 (Receive Change of Energisation Via Subscription Service) • Step 140 (UMSO) (Validate Updates and manage Rejections) • Step 155 (Data Service) (Receive Change of Energisation Via Subscription Service) • Step 156 (EES) (Receive Change of Energisation Via Subscription Service) • Step 160 (Central Settlements) (Receive Change of Energisation Via Subscription Service) • Step 175 (Supplier) (Receive Change of Energisation Via Subscription Service) END | • MHHS-BR-RS-104 • MHHS-BR-RS-105 • MHHS-BR-RS-107 • MHHS-BR-LD-024 | Unmetered Supply: Validate that the LDSO, UMSO will Receive Change of Energisation Via Subscription Service | In this scenario, LDSO will Receive Change of Energisation Via Subscription Service The Registration Service will receive the energisation update via the DIP and will validate the energisation change as per the registration validation rules. For a valid/accepted update, the Registration Service will update their system and EES (Test Harness) to reflect the new energisation status. The accepted outcome will also be sent to UMSO to confirm the change has been updated, Central Settlements, LDSO, Supplier (Test Harness) and Data Services (Test Harness) | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Registration Service receiving Change of Energisation Via Subscription. End Point The end point will be the UMSO (for Unmetered Supply only) and LDSO receiving Change of Energisation Via Subscription Service. The accepted response will also reach EES (Test Harness), Supplier (Test Harness, Data Services (Test Harness) and Central Settlements (Test Harness). | • Where the Supplier has initiated for Segment U (UMSO) and Energisation Status "E - Energised" and response is Accepted • Where the LDSO has initiated the request for Segment U (UMSO) and Energisation Status "D - De-Energised" and response is Accepted |  | 2 | M | VH
TS_BP008_04 | Registration Service | Metering Changes | BP008 - Change of Energisation Status | START • Step 80 (Update Registrations with Change in Energisation status) • Step 90 (DIP) (Publish Updates of Energisation status) • Step 95 (Supplier) (Rejection or unable to action received from MS/LDSO) • Step 105 (Registration Service) (Receive Update of Energisation status via subscription) END | • MHHS-BR-MS-049 • MHHS-BR-RS-104 • MHHS-BR-MS-042.1 | Metered Supply: Validate that the Registration Service will Receive Change of Energisation Via Subscription for Metered Supply (Smart/Advanced/Non Smart) for an accepted request | In this scenario, Registration Service will Receive Change of Energisation Via Subscription from Metering Service (Test Harness) for Metered Supply (Smart/Advanced/Non Smart). The Metering Service (Test Harness) will change the energisation status as per Suppliers/LDSO request for an Advanced/Smart/Non Smart Meters. All Metering Services will update the Registration Service with the new energisation status via the DIP. | The boundaries for this scenario are as follows: Start Point The starting point for this scenario can be either of the following: 1. The Metering Service (Test Harness) receiving update for Change of Energisation initiated for for Smart/Advanced/Non Smart. 2. Metering Service (Test Harness) receiving Rejected requests from Supplier (Test Harness) End Point The end point will be the Registration Service receiving Change of Energisation Via Subscription Service. Any request that has received "Rejected" response or "Unable to Action Request" response will go to Supplier (Test Harness). | • An accepted response for request initiated by Supplier for Segment A Advanced Meters and Energisation Status "D - De-Energised" • An accepted response for request initiated by Supplier for Segment S Traditional Meters and Energisation Status "D - De-Energised" • An accepted response for request initiated by Supplier for Segment S Smart Meters and Energisation Status "E - Energised" • An accepted response for request initiated by Supplier for Traditional Prepayment Meters and Energisation Status "E - Energised" |  | 4 | H | VH
TS_BP008_05 | Registration Service/LDSO | Metering Changes | BP008 - Change of Energisation Status | START • Step 105 (Receive Update of Energisation status via subscription) • Step 110 (Registrations validation) • Step 115 (Update Energisation Change/correction) • Step 125 (Energisation Status Change Outcome) • Step 135 (Publish Update of Energisation status Acceptance) • Step 165 (Receive Change of Energisation Via Subscription Service) • Step 140 (Metering Service) (Validate Updates and manage Rejections) • Step 155 (Data Service) (Receive Change of Energisation Via Subscription Service) • Step 156 (EES) (Receive Change of Energisation Via Subscription Service) • Step 160 (Central Settlements) (Receive Change of Energisation Via Subscription Service) • Step 175 (Supplier) (Receive Change of Energisation Via Subscription Service) END | • MHHS-BR-RS-104 • MHHS-BR-RS-105 • MHHS-BR-RS-107 • MHHS-BR-LD-024 | Metered Supply: Validate that the LDSO and Metering Service (Test Harness) will Receive Change of Energisation Via Subscription Service | In this scenario, LDSO will Receive Change of Energisation Via Subscription Service The Registration Service will receive the energisation update via the DIP and will validate the energisation change as per the registration validation rules. For a valid/accepted update, the Registration Service will update their system and EES (Test Harness) to reflect the new energisation status. The accepted outcome will also be sent to Metering Services (Test Harness) to confirm the change has been updated, central settlements, LDSO, Supplier (Test Harness) and Data Services (Test Harness) | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Registration Service receiving Change of Energisation Via Subscription. End Point The end point will be the LDSO receiving Change of Energisation Via Subscription Service. The accepted response will also reach EES (Test Harness), Metering Services (Test Harness), Supplier (Test Harness, Data Services (Test Harness) and Central Settlements (Test Harness). | • Where the Supplier request has initiated for Segment A (Advanced) and Energisation Status "E - Energised" and response is Accepted • Where the Supplier has initiated for Non Smart Traditional Meters and Energisation Status "E - Energised" and response is Accepted • Where the LDSO has initiated the request for Segment S (Smart) and Energisation Status "D - De-Energised" and response is Accepted |  | 3 | M | VH
TS_BP008_06 | LDSO | Metering Changes | BP008 - Change of Energisation Status | START • Step 35 (Capture cumulative read(s) (HH download if Available/Required)) • Step 36 (PUB-041 Publish Cumulative Reads) • Step 171 (Receive cumulative reads) • Step 170 (Supplier) (Receive Cumulative Read(s)) • Step 150 (Data Service) (Receive Cumulative Read for Energisation Change ) END | • MHHS-BR-MS-043 • MHHS-BR-MS-044 • MHHS-BR-LD-025 | Validate that the LDSO will Receive Cumulative Read(s) | In this scenario, LDSO will Receive Cumulative Read(s) For Smart or Advanced metering - Where possible Metering Service (Test Harness) will capture the cumulative register readings relating to the change of energisation and will publish it to LDSO via DIP. | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Registration Service receiving Change of Energisation Via Subscription. End Point The end point will be the LDSO receiving Cumulative Read(s) relating to the change of energisation from DIP. Data Service (Test Harness) and Supplier (Test Harness) will also receive the cumulative register reads from DIP. | • Cumulative reads received for Segment A (Advanced) and Single MPAN and Energisation Status "E - Energised" • Cumulative reads received for Segment S (Smart) and Linked Related MPAN and Energisation Status "D - De-Energised" |  | 2 | M | VH
TS_BP008_07 | Registration Service/UMSO | Metering Changes | BP008 - Change of Energisation Status | START • Step 105 (Receive Update of Energisation status via subscription) • Step 110 (Registrations validation) • Step 120 (Reject Energisation update) • Step 125 (Energisation Status Change Outcome) • Step 126 (Manage Message Failure) • Step 130 (Publish Update of Energisation status Rejection) • Step 140 (Validate Updates and manage Rejections) END | • MHHS-BR-RS-104 • MHHS-BR-RS-105 • MHHS-BR-RS-106 • MHHS-BR-MS-050 | Validate that the Registration Service will manage rejected Energisation Updates | In this scenario, Registration Service will manage rejected Energisation Updates and Message Failures The Registration Service will validate the energisation change as per the registration validation rules. If the update is invalid, the Registration Service will reject the update of the new energisation status and send this back to the UMSO (for Unmetered Supply) & Metering Services (Test Harness for Metered Supply) via the DIP. The rejection will include the reason why this has been rejected.The DIP will send Registration Service a failed message where the Registration Service Notification of Change of Energisation Status has failed DIP validation. Suppliers may choose to subscribe to this in order to manage their contractual agreements with Metering Services. | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Registration Service receiving Change of Energisation Via Subscription and performing validations as per the registration validation rules. End Point The end point will be the Registration Service receiving a failed message where the Registration Service Notification of Change of Energisation Status has failed DIP validation. Registration Service will also send the status to UMSO (for Unmetered Supply) & Metering Services (Test Harness for Metered Supply) via the DIP. | • A rejected response for request initiated by Supplier for Segment A and Energisation Status "E - Energised" • A rejected response for request initiated by Supplier for Segment S and Energisation Status "D - De-Energised" • A rejected response for request initiated by Supplier for Segment U and Energisation Status "D - De-Energised" |  | 3 | H | VH

## TC_BP008_04_01
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP008_04_01 | Metered Supply: Registration Service will receive Change of Energisation Via Subscription for Metered Supply - Advanced | TS_BP008_04 | Test Data • Segment A • Energisation Status = D (De-Energised) • Change of Energisation Request received from Supplier • Accepted Response IF-007 accepted response with the following characteristics: • (DI-999) Event Code = [EnergisationStatusChange] • (DI-033) Energisation Status = D (De-Energised) | Registration Service will receive Change of Energisation Via Subscription through IF-007
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP008 - Step 80 | MHHS-BR-MS-049 | Metering Service (Test Harness) | DIP | IF-007 | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface (IF-007) | N | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via IF-007
2 | BP008 - Step 90 & Step 105 | MHHS-BR-RS-104 | DIP | Registration Service | PUB-007 | Registration Service must obtain details of a successful change of energisation request from the Metering Service via the appropriate interface on the Data Integration Platform | Y | Registration Service must obtain details of a successful change of energisation request via PUB-007

## TC_BP008_04_02
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP008_04_02 | Metered Supply: Registration Service will receive Change of Energisation Via Subscription for Metered Supply - Smart (Traditional) | TS_BP008_04 | Test Data • Segment S (Traditional) • Energisation Status = D (De-Energised) • Change of Energisation Request received from Supplier • Accepted Response IF-007 accepted response with the following characteristics: • (DI-999) Event Code = [EnergisationStatusChange] • (DI-033) Energisation Status = D (De-Energised) | Registration Service will receive Change of Energisation Via Subscription through IF-007
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP008 - Step 80 | MHHS-BR-MS-049 | Metering Service (Test Harness) | DIP | IF-007 | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface (IF-007) | N | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via IF-007
2 | BP008 - Step 90 & Step 105 | MHHS-BR-RS-104 | DIP | Registration Service | PUB-007 | Registration Service must obtain details of a successful change of energisation request from the Metering Service via the appropriate interface on the Data Integration Platform | Y | Registration Service must obtain details of a successful change of energisation request via PUB-007

## TC_BP008_04_03
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP008_04_03 | Metered Supply: Registration Service will receive Change of Energisation Via Subscription for Metered Supply - Smart (Smart) | TS_BP008_04 | Test Data • Segment S (Smart) • Energisation Status = E (Energised) • Change of Energisation Request received from Supplier • Accepted Response IF-007 accepted response with the following characteristics: • (DI-999) Event Code = [EnergisationStatusChange] • (DI-033) Energisation Status = E (Energised) | Registration Service will receive Change of Energisation Via Subscription through IF-007
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP008 - Step 80 | MHHS-BR-MS-049 | Metering Service (Test Harness) | DIP | IF-007 | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface (IF-007) | N | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via IF-007
2 | BP008 - Step 90 & Step 105 | MHHS-BR-RS-104 | DIP | Registration Service | PUB-007 | Registration Service must obtain details of a successful change of energisation request from the Metering Service via the appropriate interface on the Data Integration Platform | Y | Registration Service must obtain details of a successful change of energisation request via PUB-007

## TC_BP008_04_04
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP008_04_04 | Metered Supply: Registration Service will receive Change of Energisation Via Subscription for Metered Supply - Smart (Traditional) Prepayment | TS_BP008_04 | Test Data • Segment S (Traditional) Prepayment • Energisation Status = E (Energised) • Change of Energisation Request received from Supplier • Accepted Response IF-007 accepted response with the following characteristics: • (DI-999) Event Code = [EnergisationStatusChange] • (DI-033) Energisation Status = E (Energised) | Registration Service will receive Change of Energisation Via Subscription through IF-007
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP008 - Step 80 | MHHS-BR-MS-049 | Metering Service (Test Harness) | DIP | IF-007 | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface (IF-007) | N | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via IF-007
2 | BP008 - Step 90 & Step 105 | MHHS-BR-RS-104 | DIP | Registration Service | PUB-007 | Registration Service must obtain details of a successful change of energisation request from the Metering Service via the appropriate interface on the Data Integration Platform | Y | Registration Service must obtain details of a successful change of energisation request via PUB-007

## Test Scenario Requirements
| denotes - req part of BSC Assessment Criteria | denotes - req OOS of BSC Assessment Criteria | denotes - req still in question
Test Scenario ID | Test Scenario Title | Link to Requirement ID | Role | Business Process Steps | Requirements Detail | Interface ID | Supporting Information | Optionality
TS_BP008_01 | Validate that the LDSO issues response to the Energisation Change Request |  | Supplier | 10 | Supplier must, on identifying a need to change energisation status for an MPAN, request the Meter Service or LDSO (as appropriate) to change the energisation status via the appropriate interface. | • D0134 (From Supplier to LDSO & Metering Service)
|  | MHHS-BR-LD-022 | LDSO | 15 | LDSO must be able to receive a change of energisation status request via the appropriate interface. | • D0134 (From Supplier to LDSO) | D0134 on DTN
|  | MHHS-BR-LD-023 | LDSO | 20 | LDSO must be able to process a change in energisation status and provide the outcome and reads, where appropriate, to the Metering Service via the appropriate interface. | • D0139 (From LDSO to Metering Service) • D0179 (From LDSO to Metering Service) - For Pre-payment meter | D0139, D0179 on DTN
|  | MHHS-BR-MS-042 |  | 30 | On receipt of the D0139 or D0179 from the LDSO, Metering Service will take the necessary action. | • D0139 (From LDSO to Metering Service) • D0179 (From LDSO to Metering Service) - For Pre-payment meter
TS_BP008_02 | Unmetered Supply: Validate that the Registration Service will Receive Change of Energisation Via Subscription from UMSO for an accepted request and rejected request will be received by UMSO and Supplier (Test Harness) |  | UMSO | 64 | When UMS require an energisation change they will follow this process. Any pre activity required to identify that an energisation change is required will be BAU processes
|  | MHHS-BR-MS-047 | UMSO | 65 | UMSO must be able to receive and process details for a UMS change of energisation request received from the supplier, customer or LDSO via agreed communication method
|  | MHHS-BR-MS-048 | UMSO | 70 | UMSO must update the Unmetered Supplies Inventory in line with the energisation change, as set out in the UMSO Method Statement.
|  |  |  | 75 | Once the change has been made by the UMSO they progress to BP004 in order to send the updates to the UMSDS
|  | MHHS-BR-MS-049 | Metering Service | 80 | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface
|  |  | DIP | 90 | The DIP will receive all the updates for the change of energisation from the Metering Services via MHHS-IF-007 and publish this to the Registration Service
|  | MHHS-BR-RS-104 | Registration Service | 105 | Registration Service must obtain details of a successful change of energisation request from the Metering Service via the appropriate interface on the Data Integration Platform | PUB-007
TS_BP008_03 | Unmetered Supply: Validate that the LDSO, UMSO will Receive Change of Energisation Via Subscription Service | MHHS-BR-MS-049 | Metering Service | 80 | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface | MHHS-IF-007 | MHHS-IF-007 to Registration Service | None
|  |  | DIP | 90 | The DIP will receive all the updates for the change of energisation from the Metering Services via MHHS-IF-007 and publish this to the Registration Service | PUB-007 (From DIP to Registration Service)
|  | MHHS-BR-RS-104 | Registration Service | 105 | Registration Service must obtain details of a successful change of energisation request from the Metering Service via the appropriate interface on the Data Integration Platform | PUB-007
|  | MHHS-BR-RS-105 | Registration Service | 110 | Registration Service must carry out validation in line with the validation rules set out in the appropriate interface specification (MHHS-IF-007).
|  | MHHS-BR-RS-107 | Registration Service | 115 | Registration Service must, on passing all validation rules, update Registration Service systems and publish acceptance of the energisation update on the Data Integration Platform via the appropriate interface | MHHS-IF-008 | MHHS-IF-008 to Central Settlements, Supplier, LDSO, Metering Service and Data Service
|  |  | DIP | 125 | The DIP will receive MHHS-IF-008 with the outcome of the request to change the energisation status
|  |  | DIP | 135 | The DIP will publish the updated energisation status to Metering Services to confirm the change has been updated. This will also be published to central settlements, LDSO, Supplier and Data Services.
|  | MHHS-BR-LD-024 | LDSO | 165 | LDSO will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to LDSO)
|  | MHHS-BR-MS-050 | UMSO | 140 | Metering services will take the appropriate action on receipt of PUB-008. Where the energisation update has been rejected Metering Service will need to review the reason why and ensure this is corrected and resend MHHS-IF-007 with the correct information | PUB-008 (From DIP to UMSO)
|  |  | ADS/SDS | 155 | Data Service will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to Data Service)
|  |  | EES | 156 | EES will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to EES)
|  |  | Central Settlements | 160 | Central settlements will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to Central Settlements)
|  |  | Supplier | 175 | Supplier will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to Supplier)
TS_BP008_04 | Metered Supply: Validate that the Registration Service will Receive Change of Energisation Via Subscription for Metered Supply (Smart/Advanced/Non Smart) | MHHS-BR-MS-049 | Metering Service | 80 | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface | MHHS-IF-007 | MHHS-IF-007 to Registration Service | None
|  |  | DIP | 90 | The DIP will receive all the updates for the change of energisation from the Metering Services via MHHS-IF-007 and publish this to the Registration Service | PUB-007 (From DIP to Registration Service)
|  |  | Supplier | 95 | Supplier will receive notification from Metering Services where the request for energisation change has been rejected or was unable to be changed. Metering Service will also notify Supplier where this notification has come from the LDSO | PUB-007 (From DIP to Supplier)
|  | MHHS-BR-RS-104 | Registration Service | 105 | Registration Service must publish a Registration Service Request for Service Appointment for the proposed Metering Service using the appropriate interface on the Data Integration Platform where initial validation rules are met. | MHHS-IF-033 | MHHS-IF-033 - Appointment scenario = "CSP", "COS" or "SEG"
TS_BP008_05 | Metered Supply: Validate that the LDSO and Metering Service (Test Harness) will Receive Change of Energisation Via Subscription Service | MHHS-BR-MS-049 | Metering Service | 80 | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface | MHHS-IF-007 | MHHS-IF-007 to Registration Service | None
|  |  | DIP | 90 | The DIP will receive all the updates for the change of energisation from the Metering Services via MHHS-IF-007 and publish this to the Registration Service | PUB-007 (From DIP to Registration Service)
|  | MHHS-BR-RS-104 | Registration Service | 105 | Registration Service must obtain details of a successful change of energisation request from the Metering Service via the appropriate interface on the Data Integration Platform | PUB-007
|  | MHHS-BR-RS-105 | Registration Service | 110 | Registration Service must carry out validation in line with the validation rules set out in the appropriate interface specification (MHHS-IF-007).
|  | MHHS-BR-RS-107 | Registration Service | 115 | Registration Service must, on passing all validation rules, update Registration Service systems and publish acceptance of the energisation update on the Data Integration Platform via the appropriate interface | MHHS-IF-008 | MHHS-IF-008 to Central Settlements, Supplier, LDSO, Metering Service and Data Service
|  |  | DIP | 125 | The DIP will receive MHHS-IF-008 with the outcome of the request to change the energisation status
|  |  | DIP | 135 | The DIP will publish the updated energisation status to Metering Services to confirm the change has been updated. This will also be published to central settlements, LDSO, Supplier and Data Services.
|  | MHHS-BR-LD-024 | LDSO | 165 | LDSO will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to LDSO)
|  | MHHS-BR-MS-050 | UMSO | 140 | Metering services will take the appropriate action on receipt of PUB-008. Where the energisation update has been rejected Metering Service will need to review the reason why and ensure this is corrected and resend MHHS-IF-007 with the correct information | PUB-008 (From DIP to UMSO)
|  |  | ADS/SDS | 155 | Data Service will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to Data Service)
|  |  | EES | 156 | EES will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to EES)
|  |  | Central Settlements | 160 | Central settlements will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to Central Settlements)
|  |  | Supplier | 175 | Supplier will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to Supplier)
TS_BP008_06 | Validate that the LDSO will Receive Cumulative Read(s) | MHHS-BR-MS-043 | MSA/MSS | 35 | MSA/MSS must be able to capture Advanced and Smart cumulative reads and publish the reads to the Data Integration Platform via the appropriate interface | MHHS-IF-041 | MHHS-IF-041 to LDSO, Supplier & Data Service | MSS - Service Smart Meters
|  | MHHS-BR-MS-044 | MSA/MSS | 35 | MSA/MSS should attempt to recover UTC Period Level Consumption Data, for Advanced and Smart meters ( not UMS or Traditional), in line with contractual agreements and share via an agreed mechanism |  |  | MSS - Service Smart Meters
|  |  | DIP | 36 | On receipt of MHHS-IF-041 the DIP will publish the cumulative reads | PUB-041 (From DIP to Supplier & Data Service)
|  | MHHS-BR-LD-025 | LDSO | 171 | LDSO must receive Change of Energisation cumulative reads sent by the Metering Service via the appropriate interface and maintain records accordingly | PUB-041 (From DIP to LDSO)
|  |  | Supplier | 170 | Supplier will receive the cumulative register reads relating to the change of energisation via MHHS-IF-041. | PUB-041 (From DIP to Supplier)
|  |  | Data Service | 150 | Data Service will receive the cumulative register reads relating to the change of energisation via MHHS-IF-041. | PUB-041 (From DIP to Data Service)
TS_BP008_07 | Validate that the Registration Service will manage rejected Energisation Updates and Message Failures | MHHS-BR-MS-049 | Metering Service | 80 | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface | MHHS-IF-007 | MHHS-IF-007 to Registration Service | None
|  |  | DIP | 90 | The DIP will receive all the updates for the change of energisation from the Metering Services via MHHS-IF-007 and publish this to the Registration Service | PUB-007 (From DIP to Registration Service)
|  | MHHS-BR-RS-104 | Registration Service | 105 | Registration Service must publish a Registration Service Request for Service Appointment for the proposed Metering Service using the appropriate interface on the Data Integration Platform where initial validation rules are met. | MHHS-IF-033 | MHHS-IF-033 - Appointment scenario = "CSP", "COS" or "SEG"
|  | MHHS-BR-RS-105 | Registration Service | 110 | Registration Service must carry out validation in line with the validation rules set out in the appropriate interface specification (MHHS-IF-007).
|  | MHHS-BR-RS-106 | Registration Service | 120 | Registration Service must, on failure of any validation rules, publish a rejection of the energisation update to the Metering Service, with associated failure reason, on the Data Integration Platform via the appropriate interface | MHHS-IF-008
|  |  | DIP | 125 | The DIP will receive MHHS-IF-008 with the outcome of the request to change the energisation status
|  |  | DIP | 130 | The DIP will publish the rejection of the energisation update to Metering Services. Suppliers may choose to subscribe to this in order to manage their contractual agreements with Metering Services | PUB-008 (From DIP to Metering Service)
|  | MHHS-BR-MS-050 | UMSO | 140 | Metering Service must be able to obtain and process Registration Service Notification of Change of Energisation Status updates via the appropriate interface on the Data Integration Platform. Any rejections should be investigated and re-submitted as appropriate. | PUB-008 | PUB-008 | None