## Cover Sheet
LDSO QT - Test Cases
Version | Description | Author | Status | Date
1 | Start Test Cases | Non SIT QT Team |  | 2024-02-16
2 | Test Lead Review | Non SIT QT Team |  | 2024-02-19
3 | Review Comments Incorporated | Non SIT QT Team |  | 2024-02-20
4 | Changes associated with Linked/Related MPAN | LDSO QT - Test Cases | Complete | 2024-10-16
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## BP008 Test Scenarios
Test Scenario ID | LDSO Role (s) | Theme | Business Process | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scenarios Size) | Priority | Expleo Comments
TS_BP008_02 | UMSO/Registration Service | Metering Changes | BP008 - Change of Energisation Status | Unmetered Supply: Validate that the Registration Service will Receive Change of Energisation Via Subscription from UMSO for an accepted request | In this scenario, Registration Service will Receive Change of Energisation Via Subscription from UMSO Once, UMSO has received the request to change the energisation, it will make the logical changes in their system. Once the change has been made, the UMSO will send the updates to the UMSDS and the Registration Service with the new energisation status via the DIP. | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the UMSO receiving Change of Energisation initiated from either Supplier or LDSO. End Point The end point will be the Registration Service receiving Change of Energisation Via Subscription Service. | • An accepted response for request initiated by Supplier for Segment U (UMSO) and Energisation Status "E - Energised" • An accepted response for request initiated by LDSO for Segment U (UMSO) and Energisation Status "D - De-Energised" |  | 2 | M | VH
TS_BP008_03 | Registration Service/LDSO/UMSO | Metering Changes | BP008 - Change of Energisation Status | Unmetered Supply: Validate that the LDSO, UMSO will Receive Change of Energisation Via Subscription Service | In this scenario, LDSO will Receive Change of Energisation Via Subscription Service The Registration Service will receive the energisation update via the DIP and will validate the energisation change as per the registration validation rules. For a valid/accepted update, the Registration Service will update their system and EES (Test Harness) to reflect the new energisation status. The accepted outcome will also be sent to UMSO to confirm the change has been updated, Central Settlements, LDSO, Supplier (Test Harness) and Data Services (Test Harness) | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Registration Service receiving Change of Energisation Via Subscription. End Point The end point will be the UMSO (for Unmetered Supply only) and LDSO receiving Change of Energisation Via Subscription Service. The accepted response will also reach EES (Test Harness), Supplier (Test Harness, Data Services (Test Harness) and Central Settlements (Test Harness). | • Where the Supplier has initiated for Segment U (UMSO) and Energisation Status "E - Energised" and response is Accepted • Where the LDSO has initiated the request for Segment U (UMSO) and Energisation Status "D - De-Energised" and response is Accepted |  | 2 | M | VH
TS_BP008_05 | Registration Service/LDSO | Metering Changes | BP008 - Change of Energisation Status | Metered Supply: Validate that the LDSO and Metering Service (Test Harness) will Receive Change of Energisation Via Subscription Service | In this scenario, Registration Service will Receive Change of Energisation Via Subscription from Metering Service (Test Harness) for Metered Supply and LDSO will Receive Change of Energisation Via Subscription Service. The Metering Service (Test Harness) will change the energisation status as per Suppliers/LDSO request for an Advanced/Smart/Non Smart Meters. All Metering Services will update the Registration Service with the new energisation status via the DIP. The Registration Service will receive the energisation update via the DIP and will validate the energisation change as per the registration validation rules. For a valid/accepted update, the Registration Service will update their system and EES (Test Harness) to reflect the new energisation status. The accepted outcome will also be sent to Metering Services (Test Harness) to confirm the change has been updated, central settlements, LDSO, Supplier (Test Harness) and Data Services (Test Harness) | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the The Metering Service (Test Harness) receiving update for Change of Energisation and sending it to Registration Service. End Point The end point will be the LDSO receiving Change of Energisation Via Subscription Service. The accepted response will also reach EES (Test Harness), Metering Services (Test Harness), Supplier (Test Harness, Data Services (Test Harness) and Central Settlements (Test Harness). | • Where the Supplier request has initiated for Segment A (Advanced) with Energisation Status "E - Energised" and response is Accepted • Where the Supplier has initiated for Non Smart Traditional Meters with Energisation Status "E - Energised" and response is Accepted • Where the Supplier has initiated the request for Segment S (Traditional) with Energisation Status "D - De-Energised" and response is Accepted • Where the Supplier has initiated the request for Segment A with Energisation Status "D - De-Energised" and response is Accepted • Where the Supplier has initiated the request for Segment S with Energisation Status "E - Energised" and response is Accepted |  | 5 | M | VH
TS_BP008_06 | LDSO | Metering Changes | BP008 - Change of Energisation Status | Validate that the LDSO will Receive Cumulative Read(s) | In this scenario, LDSO will Receive Cumulative Read(s) For Smart or Advanced metering - Where possible Metering Service (Test Harness) will capture the cumulative register readings relating to the change of energisation and will publish it to LDSO via DIP. | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Registration Service receiving Change of Energisation Via Subscription. End Point The end point will be the LDSO receiving Cumulative Read(s) relating to the change of energisation from DIP. Data Service (Test Harness) and Supplier (Test Harness) will also receive the cumulative register reads from DIP. | • Cumulative reads received for Segment A (Advanced) and Single MPAN and Energisation Status "E - Energised" • Cumulative reads received for Segment S (Smart) and Linked Related MPAN and Energisation Status "D - De-Energised" |  | 2 | M | VH
TS_BP008_07 | Registration Service/UMSO | Metering Changes | BP008 - Change of Energisation Status | Validate that the Registration Service will manage rejected Energisation Updates | In this scenario, Registration Service will manage rejected Energisation Updates and Message Failures The Registration Service will validate the energisation change as per the registration validation rules. If the update is invalid, the Registration Service will reject the update of the new energisation status and send this back to the UMSO (for Unmetered Supply) & Metering Services (Test Harness for Metered Supply) via the DIP. The rejection will include the reason why this has been rejected.The DIP will send Registration Service a failed message where the Registration Service Notification of Change of Energisation Status has failed DIP validation. Suppliers may choose to subscribe to this in order to manage their contractual agreements with Metering Services. | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Registration Service receiving Change of Energisation Via Subscription and performing validations as per the registration validation rules. End Point The end point will be the Registration Service receiving a failed message where the Registration Service Notification of Change of Energisation Status has failed DIP validation. Registration Service will also send the status to UMSO (for Unmetered Supply) & Metering Services (Test Harness for Metered Supply) via the DIP. | • A rejected response for request initiated by Supplier for Segment A and Energisation Status "E - Energised" • A rejected response for request initiated by Supplier for Segment S and Energisation Status "D - De-Energised" • A rejected response for request initiated by Supplier for Segment U and Energisation Status "D - De-Energised" |  | 3 | H | VH

## TC_BP008_05_01
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP008_05_01 | LDSO and Metering Service (Test Harness) will Receive Change of Energisation Via Subscription Service - Accepted - for Segment A, Related MPAN | TS_BP008_05 | Test Data • Segment A • Related MPAN • Change in Energisation Status from E (Energised) to D (De-Energised). Data should have MPAN in Energised state. Data from test harness should generate message that Energisation Status has changed to De-Energized. • Change of Energisation Request received from Supplier • Accepted Response Actual testing: 2 instances of IF-007 (1 for primary and 1 for secondary) are generated with the following characteristics: • (DI-999) Event Code = [EnergisationStatusChange] • (DI-033) Energisation Status = D (De-Energised) 2 instances of IF-008 (1 for primary and 1 for secondary) are sent with the following characteristics: • (DI-999) Event Code = [EnergisationStatusChange] • (DI-979) Response Code = A (Accept) • (DI-033) Energisation Status = D (De-Energised) | IF-008 will publish the updated energisation status to LDSO, Metering Service (Test Harness), Data Service (Test Harness), EES (Test Harness), Central Settlements (Test Harness) and Supplier (Test Harness) to confirm the change has been updated.
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP008 - Step 80 | MHHS-BR-MS-049 | Metering Service (Test Harness) | DIP | IF-007 (for primary) IF-007 (for secondary) | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface (IF-007) 1 instance for primary MPAN 1 instance for secondary MPAN | N | Metering Service to provide updated energisation status details to DIP via IF-007 1 instance for primary MPAN 1 instance for secondary MPAN
2 | BP008 - Step 90 & Step 105 | MHHS-BR-RS-104 | DIP | Registration Service | PUB-007 (for primary) PUB-007 (for secondary) | Registration Service must obtain details of a successful change of energisation request from the Metering Service via the appropriate interface (PUB-007) on the Data Integration Platform 1 instance for primary MPAN 1 instance for secondary MPAN | Y | Registration Service must obtain details of a successful change of energisation request via PUB-007 1 instance for primary MPAN 1 instance for secondary MPAN
3 | BP008 - Step 110 | MHHS-BR-RS-105 | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must carry out validation in line with the validation rules set out in the appropriate interface specification. | N | Registration Service must carry out the validations
4 | BP008 - Step 115 | MHHS-BR-RS-107 | Registration Service | DIP | IF-008 (for primary) IF-008 (for secondary) | Registration Service must, on passing all validation rules, update Registration Service systems and publish acceptance of the energisation update on the Data Integration Platform via the appropriate interface (IF-008) 1 instance for primary MPAN 1 instance for secondary MPAN | Y | Registration Service must update their systems and publish acceptance of energisation update via IF-008 1 instance for primary MPAN 1 instance for secondary MPAN
5 | BP008 - Step 125, Step 135 & Step 165 | MHHS-BR-LD-024 | DIP | LDSO | PUB-008 (for primary) PUB-008 (for secondary) | The DIP will receive IF-008 with the outcome of the request to change the energisation status and publish the updated energisation status to LDSO. LDSO will receive notification of the energisation change via PUB-008 1 instance for primary MPAN 1 instance for secondary MPAN | Y | LDSO receiving notification of the energisation change via PUB-008 and updating records accordingly 1 instance for primary MPAN 1 instance for secondary MPAN
6 | BP008 - Step 135, Step 140, Step 155, Step 156 & Step 175 | NA | DIP | Metering Service (Test Harness) Data Service (Test Harness) EES (Test Harness) Supplier (Test Harness) | PUB-008 (for primary) (MS) PUB-008 (for secondary) (MS) PUB-008 (for primary) (DS) PUB-008 (for secondary) (DS) PUB-008 (for primary) (EES) PUB-008 (for secondary) (EES) PUB-008 (for primary) (SUP) PUB-008 (for secondary) (SUP) | The DIP will receive IF-008 with the outcome of the request to change the energisation status and publish the updated energisation status to Metering Service (Test Harness), Data Services (Test Harness), EES (Test Harness) and Supplier (Test Harness). Metering Service, Data Service, EES and Supplier will receive notification of the energisation change via PUB-008 1 instance for primary MPAN for each party 1 instance for secondary MPAN for each party | N | A message to validate the notification of the energisation change via PUB-008 by Metering Service (Test Harness), Data Services (Test Harness), EES (Test Harness) and Supplier (Test Harness) 1 instance for primary MPAN for each party 1 instance for secondary MPAN for each party
7 | BP008 - Step 135 & Step 160 | NA | DIP | Central Settlements (Test Harness) | PUB-008 (for primary) PUB-008 (for secondary) | The DIP will receive IF-008 with the outcome of the request to change the energisation status and publish the updated energisation status to Central Settlements (Test Harness). Central Settlements will receive notification of the energisation change via PUB-008 1 instance for primary MPAN 1 instance for secondary MPAN | Y | A message to validate the notification of the energisation change via PUB-008 by Central Settlements (Test Harness) 1 instance for primary MPAN 1 instance for secondary MPAN

## TC_BP008_05_02
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP008_05_02 | LDSO and Metering Service (Test Harness) will Receive Change of Energisation Via Subscription Service - Accepted - for Non Smart Traditional Meter with Linked Import/Export MPAN | TS_BP008_05 | Test Data • Non Smart Traditional • Linked Import/Export MPAN • Change in Energisation Status from E (Energised) to D (De-Energised). Data should have MPAN in Energised state. Data from test harness should generate message that Energisation Status has changed to De-Energized. • Change of Energisation Request received from Supplier • Accepted Response Actual Testing: 2 instances of IF-007 (1 for import & 1 for export) are sent with the following characteristics: • (DI-999) Event Code = [EnergisationStatusChange] • (DI-033) Energisation Status = D (De-Energised) 2 instances of IF-008 (1 for import & 1 for export) are sent with the following characteristics: • (DI-999) Event Code = [EnergisationStatusChange] • (DI-979) Response Code = A (Accept) • (DI-033) Energisation Status = D (De-Energised) | IF-008 will publish the updated energisation status to LDSO, Metering Service (Test Harness), Data Service (Test Harness), EES (Test Harness), Central Settlements (Test Harness) and Supplier (Test Harness) to confirm the change has been updated.
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP008 - Step 80 | MHHS-BR-MS-049 | Metering Service (Test Harness) | DIP | IF-007 (for import) IF-007 (for export) | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface (IF-007) 1 instance for import MPAN 1 instance for export MPAN | N | Metering Service to provide updated energisation status details to DIP via IF-007 1 instance for import MPAN 1 instance for export MPAN
2 | BP008 - Step 90 & Step 105 | MHHS-BR-RS-104 | DIP | Registration Service | PUB-007 (for import) PUB-007 (for export) | Registration Service must obtain details of a successful change of energisation request from the Metering Service via the appropriate interface (PUB-007) on the Data Integration Platform 1 instance for import MPAN 1 instance for export MPAN | Y | Registration Service must obtain details of a successful change of energisation request via PUB-007 1 instance for import MPAN 1 instance for export MPAN
3 | BP008 - Step 110 | MHHS-BR-RS-105 | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must carry out validation in line with the validation rules set out in the appropriate interface specification. | N | Registration Service must carry out the validations
4 | BP008 - Step 115 | MHHS-BR-RS-107 | Registration Service | DIP | IF-008 (for import) IF-008 (for export) | Registration Service must, on passing all validation rules, update Registration Service systems and publish acceptance of the energisation update on the Data Integration Platform via the appropriate interface (IF-008) 1 instance for import MPAN 1 instance for export MPAN | Y | Registration Service must update their systems and publish acceptance of energisation update via IF-008 1 instance for import MPAN 1 instance for export MPAN
5 | BP008 - Step 125, Step 135 & Step 165 | MHHS-BR-LD-024 | DIP | LDSO | PUB-008 (for import) PUB-008 (for export) | The DIP will receive IF-008 with the outcome of the request to change the energisation status and publish the updated energisation status to LDSO. LDSO will receive notification of the energisation change via PUB-008 1 instance for import MPAN 1 instance for export MPAN | Y | LDSO receiving notification of the energisation change via PUB-008 and updating records accordingly 1 instance for import MPAN 1 instance for export MPAN
6 | BP008 - Step 135, Step 140, Step 155, Step 156 & Step 175 | NA | DIP | Metering Service (Test Harness) Data Service (Test Harness) EES (Test Harness) Supplier (Test Harness) | PUB-008 (for import) (MS) PUB-008 (for export) (MS) PUB-008 (for import) (DS) PUB-008 (for export) (DS) PUB-008 (for import) (EES) PUB-008 (for export) (EES) PUB-008 (for import) (SUP) PUB-008 (for export) (SUP) | The DIP will receive IF-008 with the outcome of the request to change the energisation status and publish the updated energisation status to Metering Service (Test Harness), Data Services (Test Harness), EES (Test Harness) and Supplier (Test Harness). Metering Service, Data Service, EES and Supplier will receive notification of the energisation change via PUB-008 1 instance for import MPAN for each party 1 instance for export MPAN for each party | N | A message to validate the notification of the energisation change via PUB-008 by Metering Service (Test Harness), Data Services (Test Harness), EES (Test Harness) and Supplier (Test Harness) 1 instance for import MPAN for each party 1 instance for export MPAN for each party
7 | BP008 - Step 135 & Step 160 | NA | DIP | Central Settlements (Test Harness) | PUB-008 (for import) PUB-008 (for export) | The DIP will receive IF-008 with the outcome of the request to change the energisation status and publish the updated energisation status to Central Settlements (Test Harness). Central Settlements will receive notification of the energisation change via PUB-008 1 instance for import MPAN 1 instance for export MPAN | Y | A message to validate the notification of the energisation change via PUB-008 by Central Settlements (Test Harness) 1 instance for import MPAN 1 instance for export MPAN

## TC_BP008_05_03
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP008_05_03 | LDSO and Metering Service (Test Harness for Metered Supply) will Receive Change of Energisation Via Subscription Service - Accepted - for Segment S (Traditional) Prepayment, Related MPAN | TS_BP008_05 | Test Data • Segment S (Traditional) Prepayment • Related MPAN • Change in Energisation Status from D (De-Energised) to E (Energised). Data should have MPAN in De-Energised state. Data from test harness should generate message that Energisation Status has changed to Energized. • Change of Energisation Request received from Supplier • Accepted Response Actual Testing: 2 instances of IF-007 (1 for primary and 1 for secondary) are sent with the following characteristics: • (DI-999) Event Code = [EnergisationStatusChange] • (DI-033) Energisation Status = E (Energised) 2 instances of IF-008 (1 for primary and 1 for secondary) are sent with the following characteristics: • (DI-999) Event Code = [EnergisationStatusChange] • (DI-979) Response Code = A (Accept) • (DI-033) Energisation Status = E (Energised) | IF-008 will publish the updated energisation status to LDSO, Metering Service (Test Harness), Data Service (Test Harness), EES (Test Harness), Central Settlements (Test Harness) and Supplier (Test Harness) to confirm the change has been updated.
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP008 - Step 80 | MHHS-BR-MS-049 | Metering Service (Test Harness) | DIP | IF-007 (for primary) IF-007 (for secondary) | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface (IF-007) 1 instance for primary MPAN 1 instance for secondary MPAN | N | Metering Service to provide updated energisation status details to DIP via IF-007 1 instance for primary MPAN 1 instance for secondary MPAN
2 | BP008 - Step 90 & Step 105 | MHHS-BR-RS-104 | DIP | Registration Service | PUB-007 (for primary) PUB-007 (for secondary) | Registration Service must obtain details of a successful change of energisation request from the Metering Service via the appropriate interface (PUB-007) on the Data Integration Platform 1 instance for primary MPAN 1 instance for secondary MPAN | Y | Registration Service must obtain details of a successful change of energisation request via PUB-007 1 instance for primary MPAN 1 instance for secondary MPAN
3 | BP008 - Step 110 | MHHS-BR-RS-105 | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must carry out validation in line with the validation rules set out in the appropriate interface specification. | N | Registration Service must carry out the validations
4 | BP008 - Step 115 | MHHS-BR-RS-107 | Registration Service | DIP | IF-008 (for primary) IF-008 (for secondary) | Registration Service must, on passing all validation rules, update Registration Service systems and publish acceptance of the energisation update on the Data Integration Platform via the appropriate interface (IF-008) 1 instance for primary MPAN 1 instance for secondary MPAN | Y | Registration Service must update their systems and publish acceptance of energisation update via IF-008 1 instance for primary MPAN 1 instance for secondary MPAN
5 | BP008 - Step 125, Step 135 & Step 165 | MHHS-BR-LD-024 | DIP | LDSO | PUB-008 (for primary) PUB-008 (for secondary) | The DIP will receive IF-008 with the outcome of the request to change the energisation status and publish the updated energisation status to LDSO. LDSO will receive notification of the energisation change via PUB-008 1 instance for primary MPAN 1 instance for secondary MPAN | Y | LDSO receiving notification of the energisation change via PUB-008 and update their records accordingly 1 instance for primary MPAN 1 instance for secondary MPAN
6 | BP008 - Step 135, Step 140, Step 155, Step 156 & Step 175 | NA | DIP | Metering Service (Test Harness) Data Service (Test Harness) EES (Test Harness) Supplier (Test Harness) | PUB-008 (for primary) (MS) PUB-008 (for secondary) (MS) PUB-008 (for primary) (DS) PUB-008 (for secondary) (DS) PUB-008 (for primary) (EES) PUB-008 (for secondary) (EES) PUB-008 (for primary) (SUP) PUB-008 (for secondary) (SUP) | The DIP will receive IF-008 with the outcome of the request to change the energisation status and publish the updated energisation status to Metering Service (Test Harness), Data Services (Test Harness), EES (Test Harness) and Supplier (Test Harness). Metering Service, Data Service, EES and Supplier will receive notification of the energisation change via PUB-008 1 instance for primary MPAN for each party 1 instance for secondary MPAN for each party | N | A message to validate the notification of the energisation change via PUB-008 by Metering Service (Test Harness), Data Services (Test Harness), EES (Test Harness) and Supplier (Test Harness) 1 instance for primary MPAN for each party 1 instance for secondary MPAN for each party
7 | BP008 - Step 135 & Step 160 | NA | DIP | Central Settlements (Test Harness) | PUB-008 (for primary) PUB-008 (for secondary) | The DIP will receive IF-008 with the outcome of the request to change the energisation status and publish the updated energisation status to Central Settlements (Test Harness). Central Settlements will receive notification of the energisation change via PUB-008 1 instance for primary MPAN 1 instance for secondary MPAN | Y | A message to validate the notification of the energisation change via PUB-008 by Central Settlements (Test Harness) 1 instance for primary MPAN 1 instance for secondary MPAN

## TC_BP008_05_04
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP008_05_04 | LDSO and Metering Service (Test Harness for Metered Supply) will Receive Change of Energisation Via Subscription Service - Accepted - for Segment A, Linked Import/Export MPAN | TS_BP008_05 | Test Data • Segment A • Linked Import/Export MPAN • Change in Energisation Status from D (De-Energised) to E (Energised). Data should have MPAN in De-Energised state. Data from test harness should generate message that Energisation Status has changed to Energized. • Change of Energisation Request received from Supplier • Accepted Response Actual Testing: 2 instances of IF-007 (1 for import & 1 for export) are sent with the following characteristics: • (DI-999) Event Code = [EnergisationStatusChange] • (DI-033) Energisation Status = E (Energised) 2 instances of IF-008 (1 for import & 1 for export) are sent with the following characteristics: • (DI-999) Event Code = [EnergisationStatusChange] • (DI-979) Response Code = A (Accept) • (DI-033) Energisation Status = E (Energised) | IF-008 will publish the updated energisation status to LDSO, Metering Service (Test Harness), Data Service (Test Harness), EES (Test Harness), Central Settlements (Test Harness) and Supplier (Test Harness) to confirm the change has been updated.
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP008 - Step 80 | MHHS-BR-MS-049 | Metering Service (Test Harness) | DIP | IF-007 (for import) IF-007 (for export) | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface (IF-007) 1 instance for import MPAN 1 instance for export MPAN | N | Metering Service to provide updated energisation status details to DIP via IF-007 1 instance for import MPAN 1 instance for export MPAN
2 | BP008 - Step 90 & Step 105 | MHHS-BR-RS-104 | DIP | Registration Service | PUB-007 (for import) PUB-007 (for export) | Registration Service must obtain details of a successful change of energisation request from the Metering Service via the appropriate interface (PUB-007) on the Data Integration Platform 1 instance for import MPAN 1 instance for export MPAN | Y | Registration Service must obtain details of a successful change of energisation request via PUB-007 1 instance for import MPAN 1 instance for export MPAN
3 | BP008 - Step 110 | MHHS-BR-RS-105 | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must carry out validation in line with the validation rules set out in the appropriate interface specification. | N | Registration Service must carry out the validations
4 | BP008 - Step 115 | MHHS-BR-RS-107 | Registration Service | DIP | IF-008 (for import) IF-008 (for export) | Registration Service must, on passing all validation rules, update Registration Service systems and publish acceptance of the energisation update on the Data Integration Platform via the appropriate interface (IF-008) 1 instance for import MPAN 1 instance for export MPAN | Y | Registration Service must update their systems and publish acceptance of energisation update via IF-008 1 instance for import MPAN 1 instance for export MPAN
5 | BP008 - Step 125, Step 135 & Step 165 | MHHS-BR-LD-024 | DIP | LDSO | PUB-008 (for import) PUB-008 (for export) | The DIP will receive IF-008 with the outcome of the request to change the energisation status and publish the updated energisation status to LDSO. LDSO will receive notification of the energisation change via PUB-008 1 instance for import MPAN 1 instance for export MPAN | Y | LDSO receiving notification of the energisation change via PUB-008 and updating records accordingly 1 instance for import MPAN 1 instance for export MPAN
6 | BP008 - Step 135, Step 140, Step 155, Step 156 & Step 175 | NA | DIP | Metering Service (Test Harness) Data Service (Test Harness) EES (Test Harness) Supplier (Test Harness) | PUB-008 (for import) (MS) PUB-008 (for export) (MS) PUB-008 (for import) (DS) PUB-008 (for export) (DS) PUB-008 (for import) (EES) PUB-008 (for export) (EES) PUB-008 (for import) (SUP) PUB-008 (for export) (SUP) | The DIP will receive IF-008 with the outcome of the request to change the energisation status and publish the updated energisation status to Metering Service (Test Harness), Data Services (Test Harness), EES (Test Harness) and Supplier (Test Harness). Metering Service, Data Service, EES and Supplier will receive notification of the energisation change via PUB-008 1 instance for import MPAN for each party 1 instance for export MPAN for each party | N | A message to validate the notification of the energisation change via PUB-008 by Metering Service (Test Harness), Data Services (Test Harness), EES (Test Harness) and Supplier (Test Harness) 1 instance for import MPAN for each party 1 instance for export MPAN for each party
7 | BP008 - Step 135 & Step 160 | NA | DIP | Central Settlements (Test Harness) | PUB-008 (for import) PUB-008 (for export) | The DIP will receive IF-008 with the outcome of the request to change the energisation status and publish the updated energisation status to Central Settlements (Test Harness). Central Settlements will receive notification of the energisation change via PUB-008 1 instance for import MPAN 1 instance for export MPAN | Y | A message to validate the notification of the energisation change via PUB-008 by Central Settlements (Test Harness) 1 instance for import MPAN 1 instance for export MPAN

## TC_BP008_05_05
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP008_05_05 | LDSO and Metering Service (Test Harness for Metered Supply) will Receive Change of Energisation Via Subscription Service - Accepted - for Segment S, Single MPAN (Disconnected) | TS_BP008_05 | Test Data • Segment S • Single MPAN (Disconnected) • Change in Energisation Status from E (Energised) to D (De-Energised). Data should have MPAN in Energised state. Data from test harness should generate message that Energisation Status has changed to De-Energized. • Change of Energisation Request received from Supplier • Accepted Response Actual Testing: IF-007 accepted response with the following characteristics: • (DI-999) Event Code = [EnergisationStatusChange] • (DI-033) Energisation Status = D (De-Energised) IF-008 accepted response with the following characteristics: • (DI-999) Event Code = [EnergisationStatusChange] • (DI-979) Response Code = A (Accept) • (DI-033) Energisation Status = D (De-Energised) | IF-008 will publish the updated energisation status to LDSO, Metering Service (Test Harness), Data Service (Test Harness), EES (Test Harness), Central Settlements (Test Harness) and Supplier (Test Harness) to confirm the change has been updated.
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP008 - Step 80 | MHHS-BR-MS-049 | Metering Service (Test Harness) | DIP | IF-007 | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface (IF-007). | N | Metering Service to provide updated energisation status details to DIP via IF-007
2 | BP008 - Step 90 & Step 105 | MHHS-BR-RS-104 | DIP | Registration Service | PUB-007 | Registration Service must obtain details of a successful change of energisation request from the Metering Service via the appropriate interface (PUB-007) on the Data Integration Platform. | Y | Registration Service must obtain details of a successful change of energisation request via PUB-007
3 | BP008 - Step 110 | MHHS-BR-RS-105 | Registration Service (internal processing) | Registration Service (internal processing) | NA | Registration Service must carry out validation in line with the validation rules set out in the appropriate interface specification. | N | Registration Service must carry out the validations
4 | BP008 - Step 115 | MHHS-BR-RS-107 | Registration Service | DIP | IF-008 | Registration Service must, on passing all validation rules, update Registration Service systems and publish acceptance of the energisation update on the Data Integration Platform via the appropriate interface (IF-008). | Y | Registration Service must update their systems and publish acceptance of energisation update via IF-008
5 | BP008 - Step 125, Step 135 & Step 165 | MHHS-BR-LD-024 | DIP | LDSO | PUB-008 | The DIP will receive IF-008 with the outcome of the request to change the energisation status and publish the updated energisation status to LDSO. LDSO will receive notification of the energisation change via PUB-008. | Y | LDSO receiving notification of the energisation change via PUB-008 and update their records accordingly
6 | BP008 - Step 135, Step 140, Step 155, Step 156 & Step 175 | NA | DIP | Metering Service (Test Harness) Data Service (Test Harness) EES (Test Harness) Supplier (Test Harness) | PUB-008 | The DIP will receive IF-008 with the outcome of the request to change the energisation status and publish the updated energisation status to Metering Service (Test Harness), Data Services (Test Harness), EES (Test Harness) and Supplier (Test Harness). Metering Service, Data Service, EES and Supplier will receive notification of the energisation change via PUB-008. | N | A message to validate the notification of the energisation change via PUB-008 by Metering Service (Test Harness), Data Services (Test Harness), EES (Test Harness) and Supplier (Test Harness).
7 | BP008 - Step 135 & Step 160 | NA | DIP | Central Settlements (Test Harness) | PUB-008 | The DIP will receive IF-008 with the outcome of the request to change the energisation status and publish the updated energisation status to Central Settlements (Test Harness). Central Settlements will receive notification of the energisation change via PUB-008. | Y | A message to validate the notification of the energisation change via PUB-008 by Central Settlements (Test Harness)

## Test Scenario Requirements
| denotes - req part of BSC Assessment Criteria | denotes - req OOS of BSC Assessment Criteria | denotes - req still in question
Test Scenario ID | Test Scenario Title | Link to Requirement ID | Role | Business Process Steps | Requirements Detail | Interface ID | Supporting Information | Optionality
TS_BP008_02 | Unmetered Supply: Validate that the Registration Service will Receive Change of Energisation Via Subscription from UMSO for an accepted request and rejected request will be received by UMSO and Supplier (Test Harness) |  | UMSO | 64 | When UMS require an energisation change they will follow this process. Any pre activity required to identify that an energisation change is required will be BAU processes
|  | MHHS-BR-MS-047 | UMSO | 65 | UMSO must be able to receive and process details for a UMS change of energisation request received from the supplier, customer or LDSO via agreed communication method
|  | MHHS-BR-MS-048 | UMSO | 70 | UMSO must update the Unmetered Supplies Inventory in line with the energisation change, as set out in the UMSO Method Statement.
|  |  |  | 75 | Once the change has been made by the UMSO they progress to BP004 in order to send the updates to the UMSDS
|  | MHHS-BR-MS-049 | Metering Service | 80 | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface
|  |  | DIP | 90 | The DIP will receive all the updates for the change of energisation from the Metering Services via MHHS-IF-007 and publish this to the Registration Service
|  | MHHS-BR-RS-104 | Registration Service | 105 | Registration Service must obtain details of a successful change of energisation request from the Metering Service via the appropriate interface on the Data Integration Platform | PUB-007
TS_BP008_03 | Unmetered Supply: Validate that the LDSO, UMSO will Receive Change of Energisation Via Subscription Service | MHHS-BR-MS-049 | Metering Service | 80 | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface | MHHS-IF-007 | MHHS-IF-007 to Registration Service | None
|  |  | DIP | 90 | The DIP will receive all the updates for the change of energisation from the Metering Services via MHHS-IF-007 and publish this to the Registration Service | PUB-007 (From DIP to Registration Service)
|  | MHHS-BR-RS-104 | Registration Service | 105 | Registration Service must obtain details of a successful change of energisation request from the Metering Service via the appropriate interface on the Data Integration Platform | PUB-007
|  | MHHS-BR-RS-105 | Registration Service | 110 | Registration Service must carry out validation in line with the validation rules set out in the appropriate interface specification (MHHS-IF-007).
|  | MHHS-BR-RS-107 | Registration Service | 115 | Registration Service must, on passing all validation rules, update Registration Service systems and publish acceptance of the energisation update on the Data Integration Platform via the appropriate interface | MHHS-IF-008 | MHHS-IF-008 to Central Settlements, Supplier, LDSO, Metering Service and Data Service
|  |  | DIP | 125 | The DIP will receive MHHS-IF-008 with the outcome of the request to change the energisation status
|  |  | DIP | 135 | The DIP will publish the updated energisation status to Metering Services to confirm the change has been updated. This will also be published to central settlements, LDSO, Supplier and Data Services.
|  | MHHS-BR-LD-024 | LDSO | 165 | LDSO will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to LDSO)
|  | MHHS-BR-MS-050 | UMSO | 140 | Metering services will take the appropriate action on receipt of PUB-008. Where the energisation update has been rejected Metering Service will need to review the reason why and ensure this is corrected and resend MHHS-IF-007 with the correct information | PUB-008 (From DIP to UMSO)
|  |  | ADS/SDS | 155 | Data Service will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to Data Service)
|  |  | EES | 156 | EES will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to EES)
|  |  | Central Settlements | 160 | Central settlements will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to Central Settlements)
|  |  | Supplier | 175 | Supplier will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to Supplier)
TS_BP008_05 | Metered Supply: Validate that the LDSO and Metering Service (Test Harness) will Receive Change of Energisation Via Subscription Service | MHHS-BR-MS-049 | Metering Service | 80 | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface | MHHS-IF-007 | MHHS-IF-007 to Registration Service | None
|  |  | DIP | 90 | The DIP will receive all the updates for the change of energisation from the Metering Services via MHHS-IF-007 and publish this to the Registration Service | PUB-007 (From DIP to Registration Service)
|  | MHHS-BR-RS-104 | Registration Service | 105 | Registration Service must obtain details of a successful change of energisation request from the Metering Service via the appropriate interface on the Data Integration Platform | PUB-007
|  | MHHS-BR-RS-105 | Registration Service | 110 | Registration Service must carry out validation in line with the validation rules set out in the appropriate interface specification (MHHS-IF-007).
|  | MHHS-BR-RS-107 | Registration Service | 115 | Registration Service must, on passing all validation rules, update Registration Service systems and publish acceptance of the energisation update on the Data Integration Platform via the appropriate interface | MHHS-IF-008 | MHHS-IF-008 to Central Settlements, Supplier, LDSO, Metering Service and Data Service
|  |  | DIP | 125 | The DIP will receive MHHS-IF-008 with the outcome of the request to change the energisation status
|  |  | DIP | 135 | The DIP will publish the updated energisation status to Metering Services to confirm the change has been updated. This will also be published to central settlements, LDSO, Supplier and Data Services.
|  | MHHS-BR-LD-024 | LDSO | 165 | LDSO will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to LDSO)
|  | MHHS-BR-MS-050 | UMSO | 140 | Metering services will take the appropriate action on receipt of PUB-008. Where the energisation update has been rejected Metering Service will need to review the reason why and ensure this is corrected and resend MHHS-IF-007 with the correct information | PUB-008 (From DIP to UMSO)
|  |  | ADS/SDS | 155 | Data Service will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to Data Service)
|  |  | EES | 156 | EES will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to EES)
|  |  | Central Settlements | 160 | Central settlements will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to Central Settlements)
|  |  | Supplier | 175 | Supplier will receive notification of the energisation change via PUB-008 | PUB-008 (From DIP to Supplier)
TS_BP008_06 | Validate that the LDSO will Receive Cumulative Read(s) | MHHS-BR-MS-043 | MSA/MSS | 35 | MSA/MSS must be able to capture Advanced and Smart cumulative reads and publish the reads to the Data Integration Platform via the appropriate interface | MHHS-IF-041 | MHHS-IF-041 to LDSO, Supplier & Data Service | MSS - Service Smart Meters
|  | MHHS-BR-MS-044 | MSA/MSS | 35 | MSA/MSS should attempt to recover UTC Period Level Consumption Data, for Advanced and Smart meters ( not UMS or Traditional), in line with contractual agreements and share via an agreed mechanism |  |  | MSS - Service Smart Meters
|  |  | DIP | 36 | On receipt of MHHS-IF-041 the DIP will publish the cumulative reads | PUB-041 (From DIP to Supplier & Data Service)
|  | MHHS-BR-LD-025 | LDSO | 171 | LDSO must receive Change of Energisation cumulative reads sent by the Metering Service via the appropriate interface and maintain records accordingly | PUB-041 (From DIP to LDSO)
|  |  | Supplier | 170 | Supplier will receive the cumulative register reads relating to the change of energisation via MHHS-IF-041. | PUB-041 (From DIP to Supplier)
|  |  | Data Service | 150 | Data Service will receive the cumulative register reads relating to the change of energisation via MHHS-IF-041. | PUB-041 (From DIP to Data Service)
TS_BP008_07 | Validate that the Registration Service will manage rejected Energisation Updates and Message Failures | MHHS-BR-MS-049 | Metering Service | 80 | Metering Service must be able to provide updated energisation status details to the Data Integration Platform via the appropriate interface | MHHS-IF-007 | MHHS-IF-007 to Registration Service | None
|  |  | DIP | 90 | The DIP will receive all the updates for the change of energisation from the Metering Services via MHHS-IF-007 and publish this to the Registration Service | PUB-007 (From DIP to Registration Service)
|  | MHHS-BR-RS-104 | Registration Service | 105 | Registration Service must publish a Registration Service Request for Service Appointment for the proposed Metering Service using the appropriate interface on the Data Integration Platform where initial validation rules are met. | MHHS-IF-033 | MHHS-IF-033 - Appointment scenario = "CSP", "COS" or "SEG"
|  | MHHS-BR-RS-105 | Registration Service | 110 | Registration Service must carry out validation in line with the validation rules set out in the appropriate interface specification (MHHS-IF-007).
|  | MHHS-BR-RS-106 | Registration Service | 120 | Registration Service must, on failure of any validation rules, publish a rejection of the energisation update to the Metering Service, with associated failure reason, on the Data Integration Platform via the appropriate interface | MHHS-IF-008
|  |  | DIP | 125 | The DIP will receive MHHS-IF-008 with the outcome of the request to change the energisation status
|  |  | DIP | 130 | The DIP will publish the rejection of the energisation update to Metering Services. Suppliers may choose to subscribe to this in order to manage their contractual agreements with Metering Services | PUB-008 (From DIP to Metering Service)
|  | MHHS-BR-MS-050 | UMSO | 140 | Metering Service must be able to obtain and process Registration Service Notification of Change of Energisation Status updates via the appropriate interface on the Data Integration Platform. Any rejections should be investigated and re-submitted as appropriate. | PUB-008 | PUB-008 | None