## CoverSheet
QT - Test Scenarios
Version | Description | Author | Date
v0.1 | Initial Draft | Expleo Test Team | 2023-12-19
v0.2 | Updated after feedback from Code Bodies | Expleo Test Team | 2024-01-31
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## Test Scenario BP009
Test Scenario ID | Role (s) | Theme | Business Process | Functional Category | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scnarios Size) | Priority | Expleo Comments
TS_BP009_001 | LDSO/Registration Services | Change of Metering | BP009 Change of Metering |  | Metering changes accepted and LDSO recevies changes | The Registration Service have accepted validation changes and metering update using the validation rules. Metering updates from the Registration Service will be sent via the DIP on PUB-006. LDSO will update their systems accordingly | Start point The start point for this scenario would be the Registration Services accepting the metering change validation End point The end point for this scenario would be LDSO as well as the out of scope roles (Test Harness) Supplier & Data Service receiving the Metering updates from the Registration Service sent via the DIP on PUB-006 | • Segment S • Segment A |  | 3 | M | L
TS_BP009_002 | Registration Services | Change of Metering | BP009 Change of Metering |  | Metering changes have been rejected | Registration Service have rejected the metering update due to validation failure, the Registration Service will send a rejection back to Metering Services with the reason as why this has been rejected. This will be sent via the DIP using MHHS-IF-006 | Start point The start point for this scenario would be the Registration Services rejecting the metering change validation End point The end point for this scenario would be the out of scope role (Test Harness) Metering Service receiving a rejection where the metering update has been unsuccessful. This will contain the reason the update has failed | • Segment S • Segment A |  | 3 | M | L
TS_BP009_003 | LDSO | Change of Metering | BP009 Change of Metering |  | Receiving cumulative readings | DIP will receive a MHHS-IF-041 message with the cumulative register reads from metering service and publish this to LDSO, Supplier & Data Services. LDSO, Supplier & Data Services will receive the cumulative register readings (PUB-014) relating to the metering update | Start point The start point for this scenario would be the Supplier sending a D0142/agreed method to UMSO to request for metering works to be taken out End point The end point for this scenario would be LDSO as well as the out of scope roles (Test Harness) Supplier & Data Service receiving the cumulative register readings via MHHS-IF-041 relating to the metering update | • Segment S • Segment A |  | 3 | M | L
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be a unique ID and created when each scenario is added
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be the participants role in delivery Multiple roles could be covered in 1 scenario
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each scenario will be linked to Business Processes
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The test scenario description field will outline the objective of the test
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The field will show any other variance related to the test scenario which needs to be considered
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The number of test cases created/related to the test scenario
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This field will outline the size and difficulty of the test scenario Will be flagged as S, M & L
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will outline the priority of the test scenario Flagged as VH, H, M & L

## BP009_01_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP009_01_01 | Metering changes Accepted and LDSO recevies changes - Segment S Smart Metering - Meter Exchange | TS_BP009_01 | Test Data • Segment S - Smart Metering • Linked MPAN Data Items for IF-005 • DI-999 Event Code = [MeterExchange] • DI-085 = Electricity Smart Meter Equipment (ESME ID) Data Items for Response IF-006 • DI-979 Response Code - A = Accept | LDSO receiving the Metering updates from the Registration Service sent via the DIP on PUB-006
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 55 to 65 | N/A | Metering Service (Test Harness) | DIP | MHHS-IF-005 | Metering service (Test Harness) has sent the notification to DIP for the metering change information | N | Not required
2 | 90 to 95 95 to 100 100 to 125 | MHHS-BR-RS-108 MHHS-BR-RS-108.1 MHHS-BR-RS-109 MHHS-BR-RS-110 MHHS-BR-RS-111 | DIP | Registration Services | PUB-005 | Registration service will receive a PUB-005 with the new metering technical details from DIP. Registration services will validate the metering update using the validation rules. | Y | The correct/all the technical metering details have been received by Registration Services and validated
3 | 125 to 140 | MHHS-BR-RS-111 | Registration Services | DIP | MHHS-IF-006 | Registration services have passed validation rules and accepted the data updates . Registration Service have sent a MHHS-IF-006 message via the DIP and DIP receiving the success update message | Y | To ensure that the success update message has been sent to DIP and DIP have received the message
4 | 150 to 195 | MHHS-BR-LD-030 (OPT OUT) | DIP | LDSO | PUB-006 | LDSO have received the confrimation of acceptance from Registartion Services via DIP and will update their systems accordingly . | Y | This will ensure that the confirmation of acceptance has been received from registration services (Optional)
5 | 150 to 200, 185 & 186 | N/A | DIP | Metering Service (Test Harness) Supplier (Test Harness) Data Service (Test Harness) EES (Test Harness) | PUB-006 | DIP have published the confirmation of acceptance to the following parties: - Metering Services (Test Harness) - Supplier (Test Harness) - Data Services (Test Harness) - EES (Test Harness) | N | Not required

## BP009_01_02
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP009_01_02 | Metering changes Accepted and LDSO recevies changes - Segment A Advanced Metering - Meter Install | TS_BP009_01 | Test Data • Segment A - Advanced • Related MPAN Data Items for IF-005 • DI-999 Event Code = [MeterInstall] • DI-056 = Meter ID - Serial number of the physical meter. Data Items for Response IF-006 • DI-979 Response Code - A = Accept | LDSO receiving the Metering updates from the Registration Service sent via the DIP on PUB-006
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 55 to 65 | N/A | Metering Service (Test Harness) | DIP | MHHS-IF-005 | Metering service (Test Harness) has sent the notification to DIP for the metering change information | N | Not required
2 | 90 to 95 95 to 100 100 to 125 | MHHS-BR-RS-108 MHHS-BR-RS-108.1 MHHS-BR-RS-109 MHHS-BR-RS-110 MHHS-BR-RS-111 | DIP | Registration Services | PUB-005 | Registration service will receive a PUB-005 with the new metering technical details from DIP. Registration services will validate the metering update using the validation rules. | Y | The correct/all the technical metering details have been received by Registration Services and validated
3 | 125 to 140 | MHHS-BR-RS-111 | Registration Services | DIP | MHHS-IF-006 | Registration services have passed validation rules and accepted the data updates . Registration Service have sent a MHHS-IF-006 message via the DIP and DIP receiving the success update message | Y | To ensure that the success update message has been sent to DIP and DIP have received the message
4 | 150 to 195 | MHHS-BR-LD-030 (OPT OUT) | DIP | LDSO | PUB-006 | LDSO have received the confrimation of acceptance from Registartion Services via DIP and will update their systems accordingly . | Y | This will ensure that the confirmation of acceptance has been received from registration services
5 | 150 to 200, 185 & 186 | N/A | DIP | Metering Service (Test Harness) Supplier (Test Harness) Data Service (Test Harness) EES (Test Harness) | PUB-006 | DIP have published the confirmation of acceptance to the following parties: - Metering Services (Test Harness) - Supplier (Test Harness) - Data Services (Test Harness) - EES (Test Harness) | N | Not required

## BP009_01_03
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP009_01_03 | Metering changes Accepted and LDSO recevies changes - Segment A Advanced Metering - Meter Install | TS_BP009_01 | Test Data • Segment S - Traditional • Single MPAN Data Items for IF-005 • DI-999 Event Code = [MeterRemoval] • DI-053 = Meter ID (Removed) - Serial number of the removed physical meter. Data Items for Response IF-006 • DI-979 Response Code - A = Accept | LDSO receiving the Metering updates from the Registration Service sent via the DIP on PUB-006
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 55 to 65 | N/A | Metering Service (Test Harness) | DIP | MHHS-IF-005 | Metering service (Test Harness) has sent the notification to DIP for the metering change information | N | Not required
2 | 90 to 95 95 to 100 100 to 125 | MHHS-BR-RS-108 MHHS-BR-RS-108.1 MHHS-BR-RS-109 MHHS-BR-RS-110 MHHS-BR-RS-111 | DIP | Registration Services | PUB-005 | Registration service will receive a PUB-005 with the new metering technical details from DIP. Registration services will validate the metering update using the validation rules. | Y | The correct/all the technical metering details have been received by Registration Services and validated
3 | 125 to 140 | MHHS-BR-RS-111 | Registration Services | DIP | MHHS-IF-006 | Registration services have passed validation rules and accepted the data updates . Registration Service have sent a MHHS-IF-006 message via the DIP and DIP receiving the success update message | Y | To ensure that the success update message has been sent to DIP and DIP have received the message
4 | 150 to 195 | MHHS-BR-LD-030 (OPT OUT) | DIP | LDSO | PUB-006 | LDSO have received the confrimation of acceptance from Registartion Services via DIP and will update their systems accordingly . | Y | This will ensure that the confirmation of acceptance has been received from registration services
5 | 150 to 200, 185 & 186 | N/A | DIP | Metering Service (Test Harness) Supplier (Test Harness) Data Service (Test Harness) EES (Test Harness) | PUB-006 | DIP have published the confirmation of acceptance to the following parties: - Metering Services (Test Harness) - Supplier (Test Harness) - Data Services (Test Harness) - EES (Test Harness) | N | Not required