## CoverSheet
QT - Test Scenarios
Version | Description | Author | Date
v0.1 | Initial Draft | Expleo Test Team | 2023-12-19
v0.2 | Updated after feedback from Code Bodies | Expleo Test Team | 2024-01-31
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## Test Scenario BP009
Test Scenario ID | Role (s) | Theme | Business Process | Functional Category | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scnarios Size) | Priority | Expleo Comments
TS_BP009_001 | LDSO/Registration Services | Change of Metering | BP009 Change of Metering |  | Metering changes accepted and LDSO recevies changes | The Registration Service have accepted validation changes and metering update using the validation rules. Metering updates from the Registration Service will be sent via the DIP on PUB-006. LDSO will update their systems accordingly | Start point The start point for this scenario would be the Registration Services accepting the metering change validation End point The end point for this scenario would be LDSO as well as the out of scope roles (Test Harness) Supplier & Data Service receiving the Metering updates from the Registration Service sent via the DIP on PUB-006 | • Segment S • Segment A |  | 3 | M | L
TS_BP009_002 | Registration Services | Change of Metering | BP009 Change of Metering |  | Metering changes have been rejected | Registration Service have rejected the metering update due to validation failure, the Registration Service will send a rejection back to Metering Services with the reason as why this has been rejected. This will be sent via the DIP using MHHS-IF-006 | Start point The start point for this scenario would be the Registration Services rejecting the metering change validation End point The end point for this scenario would be the out of scope role (Test Harness) Metering Service receiving a rejection where the metering update has been unsuccessful. This will contain the reason the update has failed | • Segment S • Segment A |  | 3 | M | L
TS_BP009_003 | LDSO | Change of Metering | BP009 Change of Metering |  | Receiving cumulative readings | DIP will receive a MHHS-IF-041 message with the cumulative register reads from metering service and publish this to LDSO, Supplier & Data Services. LDSO, Supplier & Data Services will receive the cumulative register readings (PUB-014) relating to the metering update | Start point The start point for this scenario would be the Supplier sending a D0142/agreed method to UMSO to request for metering works to be taken out End point The end point for this scenario would be LDSO as well as the out of scope roles (Test Harness) Supplier & Data Service receiving the cumulative register readings via MHHS-IF-041 relating to the metering update | • Segment S • Segment A |  | 3 | M | L
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be a unique ID and created when each scenario is added
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be the participants role in delivery Multiple roles could be covered in 1 scenario
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each scenario will be linked to Business Processes
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The test scenario description field will outline the objective of the test
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The field will show any other variance related to the test scenario which needs to be considered
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The number of test cases created/related to the test scenario
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This field will outline the size and difficulty of the test scenario Will be flagged as S, M & L
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will outline the priority of the test scenario Flagged as VH, H, M & L

## BP009_02_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP009_02_01 | Metering changes Rejected - Segment S Smart Metering - Metering History Update | TS_BP009_02 | Test Data • Segment S - Smart Metering • Linked MPAN Data Items for IF-005 • DI-999 Event Code = [MeterHistoryUpdate] • DI-054 Meter Asset Provider Effective From Date Data Items for Response IF-006 • DI-979 Response Code - R = Reject • DI-980 Response Message - R = Reject - Message describing the status/outcome of the previous originating transaction - Ref IF-005 Validation Rules & Outcomes | Registration services validation have been rejected and Metering Service (Test Harness) have been informed of the rejection stating that the metering update have been unsuccessful.
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 55 to 65 65 to 90 | N/A | Metering Service (Test Harness) | DIP | MHHS-IF-005 | Metering service (Test Harness) has sent the notification to DIP for the metering change information. DIP will publish the new metering details to the Registration Service | N | Not required
2 | 90 to 95 95 to 100 100 to 125 | MHHS-BR-RS-108 MHHS-BR-RS-108.1 MHHS-BR-RS-109 MHHS-BR-RS-110 MHHS-BR-RS-111 | DIP | Registration Services | PUB-005 | Registration service will receive a PUB-005 with the new metering technical details from DIP. Registration services will validate the metering update using the validation rules. | Y | To ensure that Registration Services have received the PUB message with all the correct/all the technical metering details
3 | 100 to 135 & 145 | MHHS-BR-RS-109 MHHS-BR-RS-110 | Registration Services | DIP | MHHS-IF-006 | Registration Service has rejected the metering update due to validation failure. Registration Service will send a rejection message to DIP using MHHS-IF-006 | Y | To ensure that the correct response outcome is given and this has been sent to DIP
4 | 145 to 155 | N/A | DIP | Metering Service (Test Harness) | PUB-006 | Metering Service (Test Harness) have received a rejection via DIP PUB-006 where the metering update has been unsuccessful. This will contain the reason the update has failed | N | Not required

## BP009_02_02
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP009_02_02 | Metering changes Rejected - Advanced Metering - Meter Update | TS_BP009_02 | Test Data • Segment A - Advanced • Related MPAN Data Items for IF-005 • DI-999 Event Code = [MeterUpdate] • DI-060 = Modified Meter ID Data Items for Response IF-006 • DI-979 Response Code - R = Reject • DI-980 Response Message - R = Reject - Message describing the status/outcome of the previous originating transaction - Ref IF-005 Validation Rules & Outcomes | Registration services validation have been rejected and Metering Service (Test Harness) have been informed of the rejection stating that the metering update have been unsuccessful.
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 55 to 65 65 to 90 | N/A | Metering Service (Test Harness) | DIP | MHHS-IF-005 | Metering service (Test Harness) has sent the notification to DIP for the metering change information. DIP will publish the new metering details to the Registration Service | N | Not required
2 | 90 to 95 95 to 100 100 to 125 | MHHS-BR-RS-108 MHHS-BR-RS-108.1 MHHS-BR-RS-109 MHHS-BR-RS-110 MHHS-BR-RS-111 | DIP | Registration Services | PUB-005 | Registration service will receive a PUB-005 with the new metering technical details from DIP. Registration services will validate the metering update using the validation rules. | Y | To ensure that Registration Services have received the PUB message with all the correct/all the technical metering details
3 | 100 to 135 & 145 | MHHS-BR-RS-109 MHHS-BR-RS-110 | Registration Services | DIP | MHHS-IF-006 | Registration Service has rejected the metering update due to validation failure. Registration Service will send a rejection message to DIP using MHHS-IF-006 | Y | To ensure that the correct response outcome is given and this has been sent to DIP
4 | 145 to 155 | N/A | DIP | Metering Service (Test Harness) | PUB-006 | Metering Service (Test Harness) have received a rejection via DIP PUB-006 where the metering update has been unsuccessful. This will contain the reason the update has failed | N | Not required

## BP009_02_03
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP009_02_02 | Metering changes Rejected - Traditional Metering - Meter Update | TS_BP009_02 | Test Data • Segment S - Traditional • Related MPAN Data Items for IF-005 • DI-999 Event Code = [MeterUpdate] • DI-060 = Modified Meter ID Data Items for Response IF-006 • DI-979 Response Code - R = Reject • DI-980 Response Message - R = Reject - Message describing the status/outcome of the previous originating transaction - Ref IF-005 Validation Rules & Outcomes | Registration services validation have been rejected and Metering Service (Test Harness) have been informed of the rejection stating that the metering update have been unsuccessful.
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 55 to 65 65 to 90 | N/A | Metering Service (Test Harness) | DIP | MHHS-IF-005 | Metering service (Test Harness) has sent the notification to DIP for the metering change information. DIP will publish the new metering details to the Registration Service | N | Not required
2 | 90 to 95 95 to 100 100 to 125 | MHHS-BR-RS-108 MHHS-BR-RS-108.1 MHHS-BR-RS-109 MHHS-BR-RS-110 MHHS-BR-RS-111 | DIP | Registration Services | PUB-005 | Registration service will receive a PUB-005 with the new metering technical details from DIP. Registration services will validate the metering update using the validation rules. | Y | To ensure that Registration Services have received the PUB message with all the correct/all the technical metering details
3 | 100 to 135 & 145 | MHHS-BR-RS-109 MHHS-BR-RS-110 | Registration Services | DIP | MHHS-IF-006 | Registration Service has rejected the metering update due to validation failure. Registration Service will send a rejection message to DIP using MHHS-IF-006 | Y | To ensure that the correct response outcome is given and this has been sent to DIP
4 | 145 to 155 | N/A | DIP | Metering Service (Test Harness) | PUB-006 | Metering Service (Test Harness) have received a rejection via DIP PUB-006 where the metering update has been unsuccessful. This will contain the reason the update has failed | N | Not required