## Sheet3 (hidden)
Proposed LDSO QT Scenario | SIT Scenario
Scenario ID | Scenario ID | SITFTS-0050
Role | Scenario Title | Create MPAN
Theme | Theme | New Connection
Business Process | Description | Create an MPAN through new connection process, appoint services and install meter. & Energise the MPAN
Functional Category | Functional Category | Create MPAN
Scenario Title | Functional Area 1 | New Connection |  |  | Business Process Steps
Description | Functional Area 2 | New MPAN, New Connection successful
Boundaries | Creator | Shaun Magee, Dan Gee |  |  | Interface Description
Test Case Variables | Priority | High |  |  | Regression flag
Optionality | Scenario size | Large
Number of test cases | Business Process | BP001, BP002, BP003, BP010B(Related), BP010C (Linked), BP009, BP008, (+BP003A for Smart meters) |  |  | Precondition Test Harness
Scenario size | Boundaries | Processing ends once the Meter is Installed (if not Unmetered) and Energisation has occurred |  |  | Precondition Other
Priority | Test Case Variables | (1) Smart, import+export, forward-dated (MPAN Creation current date)
Systems under test |  | (2) Traditional, single MPAN, forward-dated (MPAN Creation current date)
|  | (3) Advanced Single MPAN, forward-dated (MPAN Creation current date) |  |  | Test evidence
(4) Unmetered, single MPAN, forward-dated (MPAN Creation current date)
| Exception Codes | NA |  |  | Role (simulated)
LDSO Test Case | SIT Test Case
No.
Test Case Id | Test Case Id
Test Case Title | Test Case Title
Test Case Link | Test Case Link
Test Data Requirements | Test Data Requirements
Traceability Requirement |  |  | Test outcome
Test Harness |  |  | Test Harness
Key Validation & Test Evidence |  |  | Interface
BP Step |  |  | requirement
Service initiating process | SIT Test Steps |  | test evidence
Service Recepint Processor
Interface | Test Case Title |  | SITFTS-0050 - Smart Metered
Evidecne Reuiqred | Key Journey | Events | New MPAN Initial Registration - Start
| Step No. |  | 10
| Business Process |  | BP001
| BP Step |  | 5
| Traceability Requirement |  | MHHS-BR-LD-010.1 | MHHS-BR-LD-010.2
| Service Producing Trigger |  | LDSO
| Input/Trigger |  | DB01
| Message Input Event Code |  | N/A
| Service Recipient Processor of Input/Trigger |  | REGS
| Test Step |  | LDSO creates 2 MPAN'S for Import/Export linked MPAN and issues DB01 REGS
| Key Validation & Test Evidence |  | Import/Export Mpan creation and linkage required
| Evidence | Required | Y

## Cover Sheet
LDSO QT - Test Scenarios
Version | Description | Author | Status | Date
V 0.1 | Initial Draft of BP003 Test Scenarios | Non SIT LDSO QT Test Team |  | 2024-01-19
| Review by SIT |  |  | 2024-01-23
V0.2 | Amendments - incorporating SIT comments | Non SIT LDSO QT Test Team |  | 2024-01-24
V0.3 | Amendments - incorporating changes after clarifications from Design Team | Non SIT LDSO QT Test Team | In Progress | 2024-01-29
v0.4 | Amendments after Code Bodies Review & Final check |  |  | 2024-01-31
| Amendments made after data team input |  |  | 2024-02-07
| Start Test Cases |  |  | 12/02.2024
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## TC_BP010B_03_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010B_03_01 | "One Time" Change of Energy Direction is Valid | TS_BP010B_03 | • Segment U • Single MPAN • Change of Energy Direction request is Valid Test data IF-018 "Notification of Registration Data Item Changes" • (DI-999)Event Code = [EnergyDirection] | Suppler will send the "One Time" Change of Energy Direction update to the LDSO via the agreed communication mechanism(Email/SDEP). The LDSO will receive validate and update their records accordingly. The LDSO will send these updates to the Registration Service via the agreed communication mechanism (DB02). The Registration Service will receive validate and update their records accordingly. The Registration Service will the updates to the UMSO who will receive validate and update their records accordingly. The Registration Service will send the updates to the LDSO who will receive validate and update their records accordingly. The Registration Service will send the updates to the Central Settlements System (Helix) who will receive validate and update their records accordingly. The Registration Service will send the updates to the CSS via an agreed mechanism (CSS UPDATE). Finally the Registration Service will also send the updates to several systems that will be simulated by a Test Harness, they are as follows, Supplier, Data Service and EES.
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP010B -Step 430 to 435 | MHHS-BR-LD-038 MHHS-BR-LD-039 | Suppler (Agreed interface that sends EMAIL/SDEP updates) | LDSO (Agreed interface that receives EMAIL/SDEP updates) | (Email/SDEP) | This test case is for a valid request (38) LDSO must receive requests from the Supplier to update the Energy direction and set it for a New Connection via an agreed mechanism (e.g. SDEP or email ) and reject if it is not a valid one time request or if the MPAN is part of a linked Import/ Export group. (39) LDSO must update records accordingly if it is a valid one time request and send notification to the Registration Service of the updated Energy Direction via Internal Interface | N | Suppler sending update records to the LDSO via agreed communication method (Email/SDEP). LDSO Receives updates the Energy direction from via agreed communication mechanism and sets it for a New Connection (Evidence if possible)
2 | BP010B -Step 435 to 440 | MHHS-BR-RS-071.2 | LDSO (Agreed interface that sends DB02 updates) | Registration Service (Agreed interface that receives DB02 updates) | DB02 | This test case is for a Single MPAN (71.2) Registration Service must continue to allow the one time change of Energy Direction by the LDSO using the appropriate interface. Registration Service should prevent any proposed updates where there is a Linked Import/ Export MPAN. | N | LDSO sending updates to the Registration Service via agreed communication method (DB02). Registration Service must continue to allow the one time change of Energy Direction by the LDSO using the appropriate interface.
3 | BP010B -Step 450 to 502 | MHHS-BR-RS-071.31 | Registration Service (Agreed interface that sends CSS updates) | CSS (Agreed interface that receives CSS updates) (End) | CSS UPDATE | (71.31) Registration Service must notify CSS of any successful Energy Direction updates via the appropriate CSS interface | N | CSS flow to update CSS (Evidence if possible)
4 | BP010B -Step 450 to 470 | MHHS-BR-RS-071.3 | Registration Service | DIP | IF-018 | (71.3) Registration Service must publish successful Energy Direction updates (IF-018) on the Data Integration Platform via the appropriate interface | y | (71.3)Registration Service must publish successful Energy Direction updates (IF-018) on the Data Integration Platform via the appropriate interface
5 | BP010B -Step 470 to 480 | MHHS-BR-MS-066.2 | DIP | UMSO | PUB-018 | (66.2) Metering Service must be able to obtain Energy Direction updates (PUB-018) via the appropriate interface on the Data Integration Platform and maintain records accordingly | y | UMSO receiving (PUB-018), validating and updating their records accordingly.
6 | BP010B -Step 470 to 510 | MHHS-BR-LD-040 | DIP | LDSO | PUB-018 | (40) LDSO must be able to obtain Energy Direction updates (PUB-018) via the appropriate interface on the Data Integration Platform and maintain records accordingly | y | (40) LDSO must be able to obtain Energy Direction updates (PUB-018) via the appropriate interface on the Data Integration Platform and maintain records accordingly
7 | BP010B -Step 470 to 500 | NA | DIP | Central Settlements System (Helix) | PUB-018 | DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Central Settlements System (Helix) Who will receive, validate and update their records accordingly | Y | DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Central Settlements System (Helix) Who will receive, validate and update their records accordingly
8 | BP010B -Step 470 to 490 BP010B -Step 470 to 520 BP010B -Step 470 to 501 | NA | DIP | Data Service (Test Harness) Suppler (Test Harness) EES (Test Harness) | PUB-018 | DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Data Service (Test Harness) DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Suppler (Test Harness) DIP sends the PUB-018 "Notification of Registration Data Item Changes" to EES (Test Harness) | n | DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Data Service (Test Harness) DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Suppler (Test Harness) DIP sends the PUB-018 "Notification of Registration Data Item Changes" to EES (Test Harness)

## TC_BP010B_03_02
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010B_03_04 | "One Time" Change of Energy Direction fails DIP validation (DIP failure) | TS_BP010B_03 | • Segment S • Single MPAN • Change of Energy Direction request fails DIP validation (DIP failure) Test data IF-018 "Notification of Registration Data Item Changes" • (DI-999)Event Code = [EnergyDirection] | Suppler will send the "One Time" Change of Energy Direction update to the LDSO via the agreed communication mechanism(Email/SDEP). The LDSO will receive validate and update their records accordingly. The LDSO will send these updates to the Registration Service via the agreed communication mechanism (DB02). The Registration Service will receive validate and update their records accordingly. The Registration Service will send IF-018 "Notification of Registration Data Item Changes" to the DIP that will fail DIP validations. The DIP will send the notification of the failure back to the Registration Service who will review and re-issue a corrected message back into the DIP.
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP010B -Step 430 to 435 | MHHS-BR-LD-038 MHHS-BR-LD-039 | Suppler (Agreed interface that sends EMAIL/SDEP updates) | LDSO (Agreed interface that receives EMAIL/SDEP updates) | (Email/SDEP) | This test case is for a valid request (38) LDSO must receive requests from the Supplier to update the Energy direction and set it for a New Connection via an agreed mechanism (e.g. SDEP or email ) and reject if it is not a valid one time request or if the MPAN is part of a linked Import/ Export group. (39) LDSO must update records accordingly if it is a valid one time request and send notification to the Registration Service of the updated Energy Direction via Internal Interface | N | Suppler sending update records to the LDSO via agreed communication method (Email/SDEP). LDSO Receives updates the Energy direction from via agreed communication mechanism and sets it for a New Connection (Evidence if possible)
2 | BP010B -Step 435 to 440 | MHHS-BR-RS-071.2 | LDSO (Agreed interface that sends DB02 updates) | Registration Service (Agreed interface that receives DB02 updates) | DB02 | This test case is for a Single MPAN (71.2) Registration Service must continue to allow the one time change of Energy Direction by the LDSO using the appropriate interface. Registration Service should prevent any proposed updates where there is a Linked Import/ Export MPAN. | N | LDSO sending updates to the Registration Service via agreed communication method (DB02). Registration Service must continue to allow the one time change of Energy Direction by the LDSO using the appropriate interface.
3 | BP010B -Step 450 to 470 | MHHS-BR-RS-071.3 | Registration Service | DIP | IF-018 | (71.3) Registration Service must publish successful Energy Direction updates (IF-018) on the Data Integration Platform via the appropriate interface | y | (71.3)Registration Service must publish successful Energy Direction updates (IF-018) on the Data Integration Platform via the appropriate interface
4 | BP010B -Step 470 to 460 | MHHS-BR-RS-137 | DIP | Registration Service | DIP Failure | (137) All Services must obtain Data Integration Platform error messages in line with the End to End Solution Architecture Document, review the impacted data and re-issue corrected messages/transactions as required | y | Registration Service receiving the DIP failure message, reviewing the impacted data and re-issue corrected messages/transactions as required

## TC_BP010B_03_03
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010B_03_05 | "One Time" Change of Energy Direction is Valid | TS_BP010B_03 | • Segment A • Single MPAN • Change of Energy Direction request is Valid Test data IF-018 "Notification of Registration Data Item Changes" • (DI-999)Event Code = [EnergyDirection] | Suppler will send the "One Time" Change of Energy Direction update to the LDSO via the agreed communication mechanism(Email/SDEP). The LDSO will receive validate and update their records accordingly. The LDSO will send these updates to the Registration Service via the agreed communication mechanism (DB02). The Registration Service will receive validate and update their records accordingly. The Registration Service will send the updates to the LDSO who will receive validate and update their records accordingly. The Registration Service will send the updates to the Central Settlements System (Helix) who will receive validate and update their records accordingly. The Registration Service will send the updates to the CSS via an agreed mechanism (CSS UPDATE). Finally the Registration Service will also send the updates to several systems that will be simulated by a Test Harness, they are as follows, MSA Metering Service, Supplier, Data Service and EES.
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP010B -Step 430 to 435 | MHHS-BR-LD-038 MHHS-BR-LD-039 | Suppler (Agreed interface that sends EMAIL/SDEP updates) | LDSO (Agreed interface that receives EMAIL/SDEP updates) | (Email/SDEP) | This test case is for a valid request (38) LDSO must receive requests from the Supplier to update the Energy direction and set it for a New Connection via an agreed mechanism (e.g. SDEP or email ) and reject if it is not a valid one time request or if the MPAN is part of a linked Import/ Export group. (39) LDSO must update records accordingly if it is a valid one time request and send notification to the Registration Service of the updated Energy Direction via Internal Interface | N | Suppler sending update records to the LDSO via agreed communication method (Email/SDEP). LDSO Receives updates the Energy direction from via agreed communication mechanism and sets it for a New Connection (Evidence if possible)
2 | BP010B -Step 435 to 440 | MHHS-BR-RS-071.2 | LDSO (Agreed interface that sends DB02 updates) | Registration Service (Agreed interface that receives DB02 updates) | DB02 | This test case is for a Single MPAN (71.2) Registration Service must continue to allow the one time change of Energy Direction by the LDSO using the appropriate interface. Registration Service should prevent any proposed updates where there is a Linked Import/ Export MPAN. | N | LDSO sending updates to the Registration Service via agreed communication method (DB02). Registration Service must continue to allow the one time change of Energy Direction by the LDSO using the appropriate interface.
3 | BP010B -Step 450 to 502 | MHHS-BR-RS-071.31 | Registration Service (Agreed interface that sends CSS updates) | CSS (Agreed interface that receives CSS updates) (End) | CSS UPDATE | (71.31) Registration Service must notify CSS of any successful Energy Direction updates via the appropriate CSS interface | N | CSS flow to update CSS (Evidence if possible)
4 | BP010B -Step 450 to 470 | MHHS-BR-RS-071.3 | Registration Service | DIP | IF-018 | (71.3) Registration Service must publish successful Energy Direction updates (IF-018) on the Data Integration Platform via the appropriate interface | y | (71.3)Registration Service must publish successful Energy Direction updates (IF-018) on the Data Integration Platform via the appropriate interface
6 | BP010B -Step 470 to 510 | MHHS-BR-LD-040 | DIP | LDSO | PUB-018 | (40) LDSO must be able to obtain Energy Direction updates (PUB-018) via the appropriate interface on the Data Integration Platform and maintain records accordingly | y | (40) LDSO must be able to obtain Energy Direction updates( PUB-018) via the appropriate interface on the Data Integration Platform and maintain records accordingly
5 | BP010B -Step 470 to 480 | MHHS-BR-MS-066.2 | DIP | MSA (Test Harness) | PUB-018 | (66.2) Metering Service must be able to obtain Energy Direction updates (PUB-018) via the appropriate interface on the Data Integration Platform and maintain records accordingly | N | MSA (Test Harness) receiving, (PUB-018) validating and updating their records accordingly.
6 | BP010B -Step 470 to 500 | NA | DIP | Central Settlements System (Helix) | PUB-018 | DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Central Settlements System (Helix) Who will receive, validate and update their records accordingly | Y | DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Central Settlements System (Helix) Who will receive, validate and update their records accordingly
7 | BP010B -Step 470 to 490 BP010B -Step 470 to 520 BP010B -Step 470 to 501 | NA | DIP | Data Service (Test Harness) Suppler (Test Harness) EES (Test Harness) | PUB-018 | DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Data Service (Test Harness) DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Suppler (Test Harness) DIP sends the PUB-018 "Notification of Registration Data Item Changes" to EES (Test Harness) | n | DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Data Service (Test Harness) DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Suppler (Test Harness) DIP sends the PUB-018 "Notification of Registration Data Item Changes" to EES (Test Harness)