## Sheet3 (hidden)
Proposed LDSO QT Scenario | SIT Scenario
Scenario ID | Scenario ID | SITFTS-0050
Role | Scenario Title | Create MPAN
Theme | Theme | New Connection
Business Process | Description | Create an MPAN through new connection process, appoint services and install meter. & Energise the MPAN
Functional Category | Functional Category | Create MPAN
Scenario Title | Functional Area 1 | New Connection |  |  | Business Process Steps
Description | Functional Area 2 | New MPAN, New Connection successful
Boundaries | Creator | Shaun Magee, Dan Gee |  |  | Interface Description
Test Case Variables | Priority | High |  |  | Regression flag
Optionality | Scenario size | Large
Number of test cases | Business Process | BP001, BP002, BP003, BP010B(Related), BP010C (Linked), BP009, BP008, (+BP003A for Smart meters) |  |  | Precondition Test Harness
Scenario size | Boundaries | Processing ends once the Meter is Installed (if not Unmetered) and Energisation has occurred |  |  | Precondition Other
Priority | Test Case Variables | (1) Smart, import+export, forward-dated (MPAN Creation current date)
Systems under test |  | (2) Traditional, single MPAN, forward-dated (MPAN Creation current date)
|  | (3) Advanced Single MPAN, forward-dated (MPAN Creation current date) |  |  | Test evidence
(4) Unmetered, single MPAN, forward-dated (MPAN Creation current date)
| Exception Codes | NA |  |  | Role (simulated)
LDSO Test Case | SIT Test Case
No.
Test Case Id | Test Case Id
Test Case Title | Test Case Title
Test Case Link | Test Case Link
Test Data Requirements | Test Data Requirements
Traceability Requirement |  |  | Test outcome
Test Harness |  |  | Test Harness
Key Validation & Test Evidence |  |  | Interface
BP Step |  |  | requirement
Service initiating process | SIT Test Steps |  | test evidence
Service Recepint Processor
Interface | Test Case Title |  | SITFTS-0050 - Smart Metered
Evidecne Reuiqred | Key Journey | Events | New MPAN Initial Registration - Start
| Step No. |  | 10
| Business Process |  | BP001
| BP Step |  | 5
| Traceability Requirement |  | MHHS-BR-LD-010.1 | MHHS-BR-LD-010.2
| Service Producing Trigger |  | LDSO
| Input/Trigger |  | DB01
| Message Input Event Code |  | N/A
| Service Recipient Processor of Input/Trigger |  | REGS
| Test Step |  | LDSO creates 2 MPAN'S for Import/Export linked MPAN and issues DB01 REGS
| Key Validation & Test Evidence |  | Import/Export Mpan creation and linkage required
| Evidence | Required | Y

## Cover Sheet
LDSO QT - Test Scenarios
Version | Description | Author | Status | Date
V 0.1 | Initial Draft of BP003 Test Scenarios | Non SIT LDSO QT Test Team |  | 2024-01-19
| Review by SIT |  |  | 2024-01-23
V0.2 | Amendments - incorporating SIT comments | Non SIT LDSO QT Test Team |  | 2024-01-24
V0.3 | Amendments - incorporating changes after clarifications from Design Team | Non SIT LDSO QT Test Team | completed | 2024-01-29
v0.4 | Amendments after Code Bodies Review & Final check |  |  | 2024-01-31
| Amendments made after data team input |  |  | 2024-02-07
| Start Test Cases |  |  | 12/02.2024
v0.5 | added detial in the Test data requirment section to make it easier for the tester to understand | kamlesh | completed | 2024-07-05
v0.6 | There are 2 tests here TC_BP010B_04_01 TC_BP010B_04_02 | kamlesh | completed | 2024-08-16
v0.7 | There was a typing error that mentioned connection type change is received by LDSO, this should say metered indicator correction made to both tests Changed form The SDEP/email is mechanism is not in scope for QT so the tester will act as if a request to change the connection type is received by the LDSO as a starting point. Changed to The SDEP/email is mechanism is not in scope for QT so the tester will act as if a request to change the metered indicator is received by the LDSO as a starting point. | kamlesh | completed | 2024-11-01
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## TC_BP010B_04_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010B_04_01 | "One Time" Change of Unmetered indicator. Where the request from the suppler for a One Time" Change of Unmetered Indicator is Valid | TS_BP010B_04 | Tester will pick data of the following type • Segment U • Single MPAN • Unmetered to Metered (F TO T) Data item values in IF-018 DI-127 help False = U - Unmetered, True = M - Metered Variant Where the request from the suppler for a One Time" Change of metered Indicator is Valid Important: The SDEP/email is mechanism is not in scope for QT so the tester will act as if a request to change the metered indicator is received by the LDSO as a starting point. What we are testing • When the LDSO receives the SDEP/email from the Supplier (or an alternative method to mimic the receipt of the SDEP/email), The LDSO will trigger the DB02 update to the Registration Services. •When the Registration Service receives the DB02 update, the Registration Services will automatically trigger the IF-018 to all the expected participants. Where the recipient is the UMSO and LDSO we will validate that the message is received by both systems, validated and their records updated accordingly. The IF-018 will have the following attributes:- - (DI-999)Event Code = [MUMIndicator] • When the Registration Service receives the DB02 update, the Registration Services will automatically trigger the CSS update to the CSS (In QT testing, we will only validate the triggering of the CSS message from the Registration Services, and not validate how that mesdsage is handled in CSS). | In this scenario the Suppler will send the "One Time" Change of Unmetered Indicator "update to the LDSO via the agreed communication mechanism. The LDSO will receive validate and update their records accordingly. The LDSO will send these updates to the Registration Service via the agreed communication mechanism. The Registration Service will receive validate and update their records accordingly. The Registration Service will send updates to the UMSO who will receive validate and update their records accordingly. The Registration Service will send updates to the LDSO who will receive validate and update their records accordingly. The Registration Service will send the updates to the Central Settlements System (Helix) who will receive validate and update their records accordingly. The Registration Service will send the updates to the CSS via an agreed mechanism. Finally the Registration Service will also send the updates to several systems that will be simulated by a Test Harness, they are as follows, Supplier, Data Service and EES.
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP010B -Step 540 to 550 | MHHS-BR-LD-041 MHHS-BR-LD-042 | Suppler (Agreed interface that sends Email/SDEP updates) | LDSO (Agreed interface that receives Email/SDEP updates) | (Email/SDEP) | The SDEP/email is mechanism is not in scope for QT so the tester will act as if a request to update the metered indicator is received This test case is for a valid request (41) LDSO must receive requests from the Supplier to update the Metered Indicator via an agreed mechanism (e.g. SDEP or email ) and reject if it is not a valid one time request (42) LDSO must update records accordingly if it is a valid one time request and send notification to the Registration Service of the updated Metered Indicator via Internal Interface | N | This test case is for a valid request (41) LDSO must receive requests from the Supplier to update the Metered Indicator via an agreed mechanism (e.g. SDEP or email ) and reject if it is not a valid one time request (42) LDSO must update records accordingly if it is a valid one time request and send notification to the Registration Service of the updated Metered Indicator via Internal Interface (Evidence if possible)
2 | BP010B -Step 550 to 560 | MHHS-BR-RS-071.4 | LDSO (Agreed interface that sends DB02 updates) | Registration Service (Agreed interface that receives DB02 updates) | DB02 | This test case where only the metered indicator is being updated (71.4) Registration Service must continue to allow the one time change of Unmetered status by the LDSO using the appropriate interface and update the Metered Indicator and Connection Type accordingly | N | This test case where only the metered indicator is being updated (71.4) Registration Service must continue to allow the one time change of Unmetered status by the LDSO using the appropriate interface and update the Metered Indicator and Connection Type accordingly (Evidence if possible)
3 | BP010B -Step 560 to 662 | MHHS-BR-RS-071.51 | Registration Service (Agreed interface that sends CSS updates) | CSS (Agreed interface that receives CSS updates) (End) | CSS UPDATE | (71.51) Registration Service must notify CSS of any successful Metered Indicator updates via the appropriate CSS interface | N | (IF possible take evidence) (71.51) Registration Service must notify CSS of any successful Metered Indicator updates via the appropriate CSS interface (Evidence if possible)
4 | BP010B -Step 560 to 590 | MHHS-BR-RS-071.5 | Registration Service | DIP | IF-018 | (71.5) Registration Service must publish Metered Indicator updates (IF-018) on the Data Integration Platform via the appropriate interface | y | (71.5) Registration Service must publish Metered Indicator updates (IF-018) on the Data Integration Platform via the appropriate interface
5 | BP010B -Step 590 to 600 | MHHS-BR-MS-066.3 | DIP | UMSO | PUB-018 | (66.3) Metering Service (UMSO) must be able to obtain Metered Status updates (PUB-018) via the appropriate interface on the Data Integration Platform and maintain records accordingly | y | (66.3) Metering Service (UMSO) must be able to obtain Metered Status updates (PUB-018) via the appropriate interface on the Data Integration Platform and maintain records accordingly
6 | BP010B -Step 590 to 630 | MHHS-BR-LD-043 | DIP | LDSO | PUB-018 | (43) LDSO must be able to obtain Metered Status updates (PUB-018) via the appropriate interface on the Data Integration Platform and maintain records accordingly |  | (43) LDSO must be able to obtain Metered Status updates (PUB-018) via the appropriate interface on the Data Integration Platform and maintain records accordingly
7 | BP010B -Step 590 to 620 | NA | DIP | Central Settlements System (Helix) | PUB-018 | DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Central Settlements System (Helix) Who will receive, validate and update their records accordingly | Y | DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Central Settlements System (Helix) Who will receive, validate and update their records accordingly
8 | BP010B -Step 590 to 640 BP010B -Step 590 to 610 BP010B -Step 590 to 621 | NA | DIP | Suppler (Test Harness) Data Service (Test Harness) EES (Test Harness) | PUB-018 | DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Suppler (Test Harness) DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Data Service (Test Harness) DIP sends the PUB-018 "Notification of Registration Data Item Changes" to EES (Test Harness) | n | DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Suppler (Test Harness) DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Data Service (Test Harness) DIP sends the PUB-018 "Notification of Registration Data Item Changes" to EES (Test Harness)

## TC_BP010B_04_02
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010B_04_02 | "One Time" Change of Unmetered indicator. Where the request from the suppler for a One Time" Change of Unmetered Indicator is Valid Segment A | TS_BP010B_04 | Tester will pick data of the following type • Segment A • Single MPAN • Metered to Unmetered ( T TO F) Data item values in IF-018 DI-127 help False = U - Unmetered, True = M - Metered Variant • Where the request from the suppler for a One Time" Change of metered Indicator is Valid Important: The SDEP/email is mechanism is not in scope for QT so the tester will act as if a request to change the metered indicator is received by the LDSO as a starting point. What we are testing • When the LDSO receives the SDEP/email from the Supplier (or an alternative method to mimic the receipt of the SDEP/email), The LDSO will trigger the DB02 update to the Registration Services. • When the Registration Service receives the DB02 update, the Registration Services will automatically trigger the IF-018 to all the expected participants. Where the recipient is the LDSO we will validate that the message is received by the LDSO systems, validated and their records updated accordingly. The IF-018 will have the following attributes:- - (DI-999)Event Code = [MUMIndicator] • When the Registration Service receives the DB02 update from the LDSO, the Registration Services will automatically trigger the CSS update to the CSS (In QT testing, we will only validate the triggering of the CSS message from the Registration Services, and not validate how that message is handled in CSS). | In this scenario the Suppler will send the "One Time" Change of Unmetered Indicator "update to the LDSO via the agreed communication mechanism. The LDSO will receive validate and update their records accordingly. The LDSO will send these updates to the Registration Service via the agreed communication mechanism. The Registration Service will receive validate and update their records accordingly. The Registration Service will send updates to the LDSO who will receive validate and update their records accordingly. The Registration Service will send the updates to the Central Settlements System (Helix) who will receive validate and update their records accordingly. The Registration Service will send the updates to the CSS via an agreed mechanism. Finally the Registration Service will also send the updates to several systems that will be simulated by a Test Harness, they are as follows, Metering Service (MSA) Supplier, Data Service and EES.
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP010B -Step 540 to 550 | MHHS-BR-LD-041 MHHS-BR-LD-042 | Suppler (Agreed interface that sends Email/SDEP updates) | LDSO (Agreed interface that receives Email/SDEP updates) | (Email/SDEP) | The SDEP/email is mechanism is not in scope for QT so the tester will act as if a request to update the metered indicator is received This test case is for a valid request (41) LDSO must receive requests from the Supplier to update the Metered Indicator via an agreed mechanism (e.g. SDEP or email ) and reject if it is not a valid one time request (42) LDSO must update records accordingly if it is a valid one time request and send notification to the Registration Service of the updated Metered Indicator via Internal Interface | N | This test case is for a valid request (41) LDSO must receive requests from the Supplier to update the Metered Indicator via an agreed mechanism (e.g. SDEP or email ) and reject if it is not a valid one time request (42) LDSO must update records accordingly if it is a valid one time request and send notification to the Registration Service of the updated Metered Indicator via Internal Interface (Evidence if possible)
2 | BP010B -Step 550 to 560 | MHHS-BR-RS-071.4 | LDSO (Agreed interface that sends DB02 updates) | Registration Service (Agreed interface that receives DB02 updates) | DB02 | This test case where only the metered indicator is being updated (71.4) Registration Service must continue to allow the one time change of Unmetered status by the LDSO using the appropriate interface and update the Metered Indicator and Connection Type accordingly | N | This test case where only the metered indicator is being updated (71.4) Registration Service must continue to allow the one time change of Unmetered status by the LDSO using the appropriate interface and update the Metered Indicator and Connection Type accordingly (Evidence if possible)
3 | BP010B -Step 560 to 662 | MHHS-BR-RS-071.51 | Registration Service (Agreed interface that sends CSS updates) | CSS (Agreed interface that receives CSS updates) (End) | CSS UPDATE | (71.51) Registration Service must notify CSS of any successful Metered Indicator updates via the appropriate CSS interface | N | (If possible take evidence) (71.51) Registration Service must notify CSS of any successful Metered Indicator updates via the appropriate CSS interface (Evidence if possible)
4 | BP010B -Step 560 to 590 | MHHS-BR-RS-071.5 | Registration Service | DIP | IF-018 | (71.5) Registration Service must publish Metered Indicator updates (IF-018) on the Data Integration Platform via the appropriate interface | y | (71.5) Registration Service must publish Metered Indicator updates (IF-018) on the Data Integration Platform via the appropriate interface
5 | BP010B -Step 590 to 600 | MHHS-BR-MS-066.3 | DIP | Metering Service MSA (Test Harness) | PUB-018 | (66.3) Metering Service MSA (Test Harnes) must be able to obtain Metered Status updates (PUB-018) via the appropriate interface on the Data Integration Platform and maintain records accordingly | y | (66.3) Metering Service MSA (Test Harness) must be able to obtain Metered Status updates (PUB-018) via the appropriate interface on the Data Integration Platform and maintain records accordingly
6 | BP010B -Step 590 to 630 | MHHS-BR-LD-043 | DIP | LDSO | PUB-018 | (43) LDSO must be able to obtain Metered Status updates (PUB-018) via the appropriate interface on the Data Integration Platform and maintain records accordingly |  | (43) LDSO must be able to obtain Metered Status updates (PUB-018) via the appropriate interface on the Data Integration Platform and maintain records accordingly
7 | BP010B -Step 590 to 620 | NA | DIP | Central Settlements System (Helix) | PUB-018 | DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Central Settlements System (Helix) Who will receive, validate and update their records accordingly | Y | DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Central Settlements System (Helix) Who will receive, validate and update their records accordingly
8 | BP010B -Step 590 to 640 BP010B -Step 590 to 610 BP010B -Step 590 to 621 | NA | DIP | Suppler (Test Harness) Data Service (Test Harness) EES (Test Harness) | PUB-018 | DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Suppler (Test Harness) DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Data Service (Test Harness) DIP sends the PUB-018 "Notification of Registration Data Item Changes" to EES (Test Harness) | n | DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Suppler (Test Harness) DIP sends the PUB-018 "Notification of Registration Data Item Changes" to Data Service (Test Harness) DIP sends the PUB-018 "Notification of Registration Data Item Changes" to EES (Test Harness)