## CoverSheet
QT - Test Scenarios
Version | Description | Author | Date
v0.1 | Initial Draft | Expleo Test Team | 2023-12-19
v0.2 | Updated after feedback from Code Bodies | Expleo Test Team | 2024-01-31
v0.3 | IR8 updates | Expleo Test Team | 2024-05-20
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## Test Scenario BP0010C
Test Scenario ID | Role (s) | Theme | Business Process | Functional Category | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scnarios Size) | Priority | Expleo Comments
TS_BP010C_001 | LDSO/Registration Services | Change of Registration Data | BP010C Change of Registration Data |  | Linking Decision - Accepted | DIP will receive MHHS-IF-019 to update the import/export linkage from Supplier and send PUB-019 to the LDSO. LDSO will receive PUB-019 from the DIP to update the import/export linkage information. LDSO accepts the request to update, the LDSO will need to update the linkage in their systems, publish the response and notify the Registration Service of the update. LDSO will issue a DB05 to Registration Service with accepted import/export linkage updates. LDSO will receive PUB-020 via the DIP confirming the updated import/export information | Start point The start point for this scenario would be the Supplier (Test Harness) will submit the request for the change to the LDSO via the DIP End point The end point for this scenario would be the LDSO as well as the (Test Harnesses) Supplier, EES, Metering Service and Data Service will receive PUB-020 via the DIP to confirm the updated import/export information | • Where LDSO will update their systems to reflect the updated import/export linkage, LDSO publishing the response to registration services, registration services managing the response. This variance would cover LDSO/registration services - Segment S - Segment A |  | 3 | M | L
TS_BP010C_002 | LDSO | Change of Registration Data | BP010C Change of Registration Data |  | Linking Decision - Rejected | The LDSO will receive PUB-019 from the DIP to update the import/export linkage information. LDSO rejects the request and publishes the response. This will generate the IF-020 to the Supplier informing them of the import/export Linkage Rejection. | Start point The start point for this scenario would be the Supplier (Test Harness) will submit the request for the change to the LDSO via the DIP End point The end point for this scenario would be the (Test Harness) Supplier receiving PUB-020 via the DIP for rejected import/export information updates | • Where LDSO rejects the import/export linkage, LDSO publishing the response into DIP and supplier will receive PUB-020 via the DIP for the rejected information updates. This variance would cover LDSO - Segment S - Segment A |  | 3 | M | L
TS_BP010C_003 | Registration Services | Change of Registration Data | BP010C Change of Registration Data |  | Success and failure - update IHD information | DIP will receive MHHS-IF-025 from Supplier and send PUB-025 to the Registrations Service. The Registration Service will receive PUB-025 with the updated IHD information and will update their systems to reflect the updated IHD information. A MHHS-IF-026 message will be sent to DIP. DIP will receive MHHS-IF-026 and send PUB-026 to the Supplier and EES. If DIP validation fails, then DIP will send Registration Service a failed message where the Notification of Registration Data Item Changes has failed DIP validation | Start point The start point for this scenario would be the Supplier (Test Harness) will issue MHHS-IF-025 to the Registration service to update the information via DIP. Success End point The end point for this scenario would be the (Test Harness) Supplier and EES receiving PUB-026 via the DIP to confirm the updated IHD information Failed End point The end point for this scenario would be DIP sending Registration Service a failed message where the Notification of Registration Data Item Changes failed DIP validation | • Where registration services updates IHD information and sends it through to DIP. DIP will then publish this to Supplier and EES. This variance would cover Registartion Services. - Segment S - Segment A • Where registration services have received a failed message back from DIP due to validation. This variance would cover Registartion Services. - Segment S - Segment A |  | 2 | M | L
TS_BP010C_004 | Registration Services | Change of Registration Data | BP010C Change of Registration Data |  | Success and failure - update SMSO information | DIP will receive MHHS-IF-025 from Supplier and send PUB-025 to the Registrations Service. The Registration Service will receive PUB-025 with the updated SMSO information and will update their systems to reflect the updated SMSO information. A MHHS-IF-026 message will be sent to DIP. DIP will receive MHHS-IF-026 and send PUB-026 to Metering Service, Data Service, Supplier and EES. If DIP validation fails, then DIP will send Registration Service a failed message where the Notification of Registration Data Item Changes has failed DIP validation | Start point The start point for this scenario would be the Supplier (Test Harness) will issue MHHS-IF-025 to the Registration service to update the information via DIP. Success End point The end point for this scenario would be the LDSO as well as the (Test Harnesses) Supplier, EES, Metering Service and Data Service will receive receiving PUB-026 via the DIP to confirm the updated SMSO information Failed End point The end point for this scenario would be DIP sending Registration Service a failed message where the Notification of Registration Data Item Changes failed DIP validation | • Where registration services updates SMSO information and sends it through to DIP. DIP will then publish this to Metering Service, Data Service, Supplier and EES. This variance would cover Registartion Services. - Segment S - Segment A • Where registration services have received a failed message back from DIP due to validation. This variance would cover Registartion Services. - Segment S - Segment A |  | 2 | M | L
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be a unique ID and created when each scenario is added
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be the participants role in delivery Multiple roles could be covered in 1 scenario
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each scenario will be linked to Business Processes
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The test scenario description field will outline the objective of the test
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The field will show any other variance related to the test scenario which needs to be considered
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The number of test cases created/related to the test scenario
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This field will outline the size and difficulty of the test scenario Will be flagged as S, M & L
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will outline the priority of the test scenario Flagged as VH, H, M & L

## BP010C_01_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010C_01_01 | Linking Decision (Import/Export) - Accepted - Segment S Traditional | TS_BP010C_01 | Test Data • Segment S - Traditional • Linked MPAN - Import/Export Linkage Data Items for IF-019 • DI-999 Event Code - [LinkedImportExportAdd] • DI-074 Subsidiary MPAN - The subsidiary MPAN in a Related/Linked MPAN Relationship Data Items for IF-020 • DI-999 Event Code - [LinkedImportExportAdd] • DI-979 Response Code - A= Accept LDSO will apply the response reason in the IF-020 after validating the IF-019. it will be one of the following codes depending on the test IE000 - Proposed Linkage Change Accepted IE001 - Proposed Linkage Change Rejected | LDSO will receive PUB-019/PUB-020 via the DIP to confirm the updated import/export information
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 850 to 870 | N/A | Supplier (Test Harness) | DIP | IF-019 | DIP should receive MHHS-IF-019 update the import/export linkage and send PUB-019 to the LDSO | N | Not required
2 | 870 to 880 | MHHS-BR-LD-043.1 | DIP | LDSO | PUB-019 | The LDSO will receive PUB-019 from the DIP to update the import/export linkage information. | Y | To ensure that receive PUB-019 from the DIP to update the import/export linkage information.
3 | 880 to 890 890 to 900 | MHHS-BR-LD-043.1 MHHS-BR-LD-043.2 MHHS-BR-LD-043.3 | LDSO | LDSO | N/A | LDSO have accpeted the update and will update their systems to reflect the updated import/export linkage | N | To ensure that LDSO have accpeted the information received and their systems reflect the information given by the Supplier
4 | 900 to 905 | MHHS-BR-RS-071.8 MHHS-BR-RS-071.6 | LDSO | Registration Services | DB05 | The LDSO will send a internal DB05 to Registration Service. Registration services have received the information with accepted import/export linkage updates. | N | Not required
5 | 905 to 910 | N/A | Registration Services | DIP | IF-020 | The Registration Service will issue MHHS-IF-20 with the updated import/export linkage information to DIP. DIP will receive the MHHS-IF-020 and will send PUB-020 to the relevant participants | Y | Need to ensure that the MHSS-IF-20 has been received by DIP and PUB-020 has been sent out
6 | 910 to 940 | MHHS-BR-LD-046 | DIP | LDSO | PUB-020 | DIP has published the information to LDSO and LDSO have received PUB-020 confirming the updates to the import/export information | Y | Need to ensure that the PUB-020 has been received and the system updated accordingly
7 | 910 to 920, 930, 931 & 950 | N/A | DIP | Supplier (Test Harness) Metering Service (Test Harness) Data Service (Test Harness) EES (Test Harness) | PUB-020 | DIP has published the information to all the other relevant parties and they have all received PUB-020 confirming the updates to the import/export information | N | Not required

## BP010C_01_02
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010C_01_02 | Linking Decision (Import/Export)- Accepted - Segment S Smart Metering | TS_BP010C_01 | Test Data • Segment S - Smart Metering • Linked MPAN - Import/Export Linkage Data Items for IF-019 • DI-999 Event Code - [LinkedImportExportRemove] • DI-018 Distributor DIP ID Data Items for IF-020 • DI-999 Event Code -[LinkedImportExportRemove] • DI-979 Response Code - A= Accept LDSO will apply the response reason in the IF-020 after validating the IF-019. it will be one of the following codes depending on the test IE000 - Proposed Linkage Change Accepted IE001 - Proposed Linkage Change Rejected | LDSO will receive PUB-020/PUB-019 via the DIP to confirm the updated import/export information
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 850 to 870 | N/A | Supplier (Test Harness) | DIP | IF-019 | DIP should receive MHHS-IF-019 update the import/export linkage and send PUB-019 to the LDSO | N | Not required
2 | 870 to 880 | MHHS-BR-LD-043.1 | DIP | LDSO | PUB-019 | The LDSO will receive PUB-019 from the DIP to update the import/export linkage information. | Y | To ensure that receive PUB-019 from the DIP to update the import/export linkage information.
3 | 880 to 890 890 to 900 | MHHS-BR-LD-043.1 MHHS-BR-LD-043.2 MHHS-BR-LD-043.3 | LDSO | LDSO | N/A | LDSO have accpeted the update and will update their systems to reflect the updated import/export linkage | N | To ensure that LDSO have accpeted the information received and their systems reflect the information given by the Supplier
4 | 900 to 905 | MHHS-BR-RS-071.8 MHHS-BR-RS-071.6 | LDSO | Registration Services | DB05 | The LDSO will send a internal DB05 to Registration Service. Registration services have received the information with accepted import/export linkage updates. | N | Not required
5 | 905 to 910 | N/A | Registration Services | DIP | IF-020 | The Registration Service will issue MHHS-IF-20 with the updated import/export linkage information to DIP. DIP will receive the MHHS-IF-020 and will send PUB-020 to the relevant participants | Y | Need to ensure that the MHSS-IF-20 has been received by DIP and PUB-020 has been sent out
6 | 910 to 940 | MHHS-BR-LD-046 | DIP | LDSO | PUB-020 | DIP has published the information to LDSO and LDSO have received PUB-020 confirming the updates to the import/export information | Y | Need to ensure that the PUB-020 has been received and the system updated accordingly
7 | 910 to 920, 930, 931 & 950 | N/A | DIP | Supplier (Test Harness) Metering Service (Test Harness) Data Service (Test Harness) EES (Test Harness) | PUB-020 | DIP has published the information to all the other relevant parties and they have all received PUB-020 confirming the updates to the import/export information | N | Not required

## BP010C_01_03
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010C_01_03 | Linking Decision (Import/Export)- Accepted - Segment A Advanced | TS_BP010C_01 | Test Data • Segment A - Advanced • Linked MPAN - Import/Export Linkage Data Items for IF-019 • DI-999 Event Code - [LinkedImportExportCreate] • DI-073 Principal MPAN - The Principal MPAN in a Related/Linked MPAN Relationship Data Items for IF-020 • DI-999 Event Code - [LinkedImportExportCreate] • DI-979 Response Code - A= Accept LDSO will apply the response reason in the IF-020 after validating the IF-019. it will be one of the following codes depending on the test IE000 - Proposed Linkage Change Accepted IE001 - Proposed Linkage Change Rejected | LDSO will receive PUB-020/PUB-019 via the DIP to confirm the updated import/export information
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 850 to 870 | N/A | Supplier (Test Harness) | DIP | IF-019 | DIP should receive MHHS-IF-019 update the import/export linkage and send PUB-019 to the LDSO | N | Not required
2 | 870 to 880 | MHHS-BR-LD-043.1 | DIP | LDSO | PUB-019 | The LDSO will receive PUB-019 from the DIP to update the import/export linkage information. | Y | To ensure that receive PUB-019 from the DIP to update the import/export linkage information.
3 | 880 to 890 890 to 900 | MHHS-BR-LD-043.1 MHHS-BR-LD-043.2 MHHS-BR-LD-043.3 | LDSO | LDSO | N/A | LDSO have accpeted the update and will update their systems to reflect the updated import/export linkage | N | To ensure that LDSO have accpeted the information received and their systems reflect the information given by the Supplier
4 | 900 to 905 | MHHS-BR-RS-071.8 MHHS-BR-RS-071.6 | LDSO | Registration Services | DB05 | The LDSO will send a internal DB05 to Registration Service. Registration services have received the information with accepted import/export linkage updates. | N | Not required
5 | 905 to 910 | N/A | Registration Services | DIP | IF-020 | The Registration Service will issue MHHS-IF-20 with the updated import/export linkage information to DIP. DIP will receive the MHHS-IF-020 and will send PUB-020 to the relevant participants | Y | Need to ensure that the MHSS-IF-20 has been received by DIP and PUB-020 has been sent out
6 | 910 to 940 | MHHS-BR-LD-046 | DIP | LDSO | PUB-020 | DIP has published the information to LDSO and LDSO have received PUB-020 confirming the updates to the import/export information | Y | Need to ensure that the PUB-020 has been received and the system updated accordingly
7 | 910 to 920, 930, 931 & 950 | N/A | DIP | Supplier (Test Harness) Metering Service (Test Harness) Data Service (Test Harness) EES (Test Harness) | PUB-020 | DIP has published the information to all the other relevant parties and they have all received PUB-020 confirming the updates to the import/export information | N | Not required