## CoverSheet
QT - Test Scenarios
Version | Description | Author | Date
v0.1 | Initial Draft | Expleo Test Team | 2023-12-19
v0.2 | Updated after feedback from Code Bodies | Expleo Test Team | 2024-01-31
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## Test Scenario BP0010C
Test Scenario ID | Role (s) | Theme | Business Process | Functional Category | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scnarios Size) | Priority | Expleo Comments
TS_BP010C_001 | LDSO/Registration Services | Change of Registration Data | BP010C Change of Registration Data |  | Linking Decision - Accepted | DIP will receive MHHS-IF-019 to update the import/export linkage from Supplier and send PUB-019 to the LDSO. LDSO will receive PUB-019 from the DIP to update the import/export linkage information. LDSO accepts the request to update, the LDSO will need to update the linkage in their systems, publish the response and notify the Registration Service of the update. LDSO will issue a DB05 to Registration Service with accepted import/export linkage updates. LDSO will receive PUB-020 via the DIP confirming the updated import/export information | Start point The start point for this scenario would be the Supplier (Test Harness) will submit the request for the change to the LDSO via the DIP End point The end point for this scenario would be the LDSO as well as the (Test Harnesses) Supplier, EES, Metering Service and Data Service will receive PUB-020 via the DIP to confirm the updated import/export information | • Where LDSO will update their systems to reflect the updated import/export linkage, LDSO publishing the response to registration services, registration services managing the response. This variance would cover LDSO/registration services - Segment S - Segment A |  | 3 | M | L
TS_BP010C_002 | LDSO | Change of Registration Data | BP010C Change of Registration Data |  | Linking Decision - Rejected | The LDSO will receive PUB-019 from the DIP to update the import/export linkage information. LDSO rejects the request and publishes the response. This will generate the IF-020 to the Supplier informing them of the import/export Linkage Rejection. | Start point The start point for this scenario would be the Supplier (Test Harness) will submit the request for the change to the LDSO via the DIP End point The end point for this scenario would be the (Test Harness) Supplier receiving PUB-020 via the DIP for rejected import/export information updates | • Where LDSO rejects the import/export linkage, LDSO publishing the response into DIP and supplier will receive PUB-020 via the DIP for the rejected information updates. This variance would cover LDSO - Segment S - Segment A |  | 3 | M | L
TS_BP010C_003 | Registration Services | Change of Registration Data | BP010C Change of Registration Data |  | Success and failure - update IHD information | DIP will receive MHHS-IF-025 from Supplier and send PUB-025 to the Registrations Service. The Registration Service will receive PUB-025 with the updated IHD information and will update their systems to reflect the updated IHD information. A MHHS-IF-026 message will be sent to DIP. DIP will receive MHHS-IF-026 and send PUB-026 to the Supplier and EES. If DIP validation fails, then DIP will send Registration Service a failed message where the Notification of Registration Data Item Changes has failed DIP validation | Start point The start point for this scenario would be the Supplier (Test Harness) will issue MHHS-IF-025 to the Registration service to update the information via DIP. Success End point The end point for this scenario would be the (Test Harness) Supplier and EES receiving PUB-026 via the DIP to confirm the updated IHD information Failed End point The end point for this scenario would be DIP sending Registration Service a failed message where the Notification of Registration Data Item Changes failed DIP validation | • Where registration services updates IHD information and sends it through to DIP. DIP will then publish this to Supplier and EES. This variance would cover Registartion Services. - Segment S • Where registration services have received a failed message back from DIP due to validation. This variance would cover Registartion Services. - Segment S |  | 2 | M | L
TS_BP010C_004 | Registration Services | Change of Registration Data | BP010C Change of Registration Data |  | Success and failure - update SMSO information | DIP will receive MHHS-IF-025 from Supplier and send PUB-025 to the Registrations Service. The Registration Service will receive PUB-025 with the updated SMSO information and will update their systems to reflect the updated SMSO information. A MHHS-IF-026 message will be sent to DIP. DIP will receive MHHS-IF-026 and send PUB-026 to Metering Service, Data Service, Supplier and EES. If DIP validation fails, then DIP will send Registration Service a failed message where the Notification of Registration Data Item Changes has failed DIP validation | Start point The start point for this scenario would be the Supplier (Test Harness) will issue MHHS-IF-025 to the Registration service to update the information via DIP. Success End point The end point for this scenario would be the LDSO as well as the (Test Harnesses) Supplier, EES, Metering Service and Data Service will receive receiving PUB-026 via the DIP to confirm the updated SMSO information Failed End point The end point for this scenario would be DIP sending Registration Service a failed message where the Notification of Registration Data Item Changes failed DIP validation | • Where registration services updates SMSO information and sends it through to DIP. DIP will then publish this to Metering Service, Data Service, Supplier and EES. This variance would cover Registartion Services. - Segment S • Where registration services have received a failed message back from DIP due to validation. This variance would cover Registartion Services. - Segment S |  | 2 | M | L
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be a unique ID and created when each scenario is added
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be the participants role in delivery Multiple roles could be covered in 1 scenario
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each scenario will be linked to Business Processes
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The test scenario description field will outline the objective of the test
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The field will show any other variance related to the test scenario which needs to be considered
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The number of test cases created/related to the test scenario
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This field will outline the size and difficulty of the test scenario Will be flagged as S, M & L
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will outline the priority of the test scenario Flagged as VH, H, M & L

## BP010C_04_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010C_04_01 | Success update SMSO information - Segment S Smart Metering | TS_BP010C_04 | For this test, the tester will manually create the IF-25 using the Test Harness and trigger this message into REG services. When the REGS recieves the IF-25 it will carry out validations and successfully trigger IF-26 to expected participants Test Data • Segment S - Smart Metering • Linked MPAN Data Items for IF-025 (created manually by the tester in Test Harness) • DI-999 Event Code - [SMSO] • DI-134 - SMSO (Smart Metering System Operator) - [REG.MkSegment] = 'Smart' Data Items for IF-026 (automatically triggered by REGS after receiving IF-25) • DI-999 Event Code - [SMSO] • DI-134 - SMSO (Smart Metering System Operator) - [REG.MkSegment] = 'Smart' | Registration Services confimring that the SMSO information has been successfully updated on their systems and sent to DIP to be published to the relevant parties
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 750 to 770 | N/A | Supplier (Test Harness) | DIP | MHHS-IF-025 | DIP has received a MHHS-IF-025 from the Supplier to update the SMSO information | N | Not required
2 | 770 to 780 780 to 790 | MHHS-BR-RS-071.11 MHHS-BR-RS-071.12 | DIP | Registration Services | PUB-025 | Registration Service has received a PUB-025 with the updated SMSO information from DIP. Registration Service have successfully update their systems to reflect the updated SMSO information | Y | To ensure that RS has received the MHHS-IF-025 SMSO update from DIP and that the information has been updated successfully on the RS systems
3 | 790 to 810 | MHHS-BR-RS-071.12 | Registration Services | DIP | MHHS-IF-026 | Registration Sevices has sent MHHS-IF-026 (based on the value entered as per the Test Data for IF-026) to DIP and DIP has successfully received it | Y | To confirm that Registration Sevices has sent MHHS-IF-026 to DIP and DIP has successfully received it
4 | 810 to 820, 830, 831 & 840 | N/A | DIP | Supplier (Test Harness EES (Test Harness) Metering Service (Test Harness) Data Service (Test Harness) | PUB-026 | DIP has sent a PUB-026 to all the relevant parties and all of them have received PUB-026 confirming the updated SMSO information | N | Not required

## BP010C_04_02
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010C_04_02 | Failed update SMSO information - Segment S Smart Metering | TS_BP010C_04 | For this test, the tester will manually create the IF-25 using the Test Harness and trigger this message into REG services. When the REGS recieves the IF-25 it will carry out validations and successfully trigger IF-26 to expected participants Test Data • Segment S - Smart Metering • Linked MPAN Data Items for IF-025 (created manually by the tester in Test Harness) • DI-999 Event Code - [SMSO] • DI-134 - SMSO (Smart Metering System Operator) - [REG.MkSegment] = 'Smart' Data Items for IF-026 (automatically triggered by REGS after receiving IF-25) • DI-999 Event Code - [SMSO] • DI-134 - SMSO (Smart Metering System Operator) - [REG.MkSegment] = 'null' | Registration Service sending PUB-026 via the DIP to confirm the updated SMSO information
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 750 to 770 | N/A | Supplier (Test Harness) | DIP | MHHS-IF-025 | DIP has received a MHHS-IF-025 from the Supplier to update the SMSO information | N | Not required
2 | 770 to 780 780 to 790 | MHHS-BR-RS-071.11 MHHS-BR-RS-071.12 | DIP | Registration Services | PUB-025 | Registration Service has received a PUB-025 with the updated SMSO information from DIP. Registration Service have successfully update their systems to reflect the updated SMSO information | Y | To ensure that RS has received the MHHS-IF-025 SMSO update from DIP and that the information has been updated successfully on the RS systems
3 | 790 to 810 | MHHS-BR-RS-071.12 | Registration Services | DIP | MHHS-IF-026 | Registration Sevices has sent MHHS-IF-026 to DIP based on the value entered as per test data for IF-026 | Y | To confirm that Registration Sevices has sent MHHS-IF-026 to DIP and DIP has successfully received it
4 | 810 to 800 | MHHS-BR-RS-137 | DIP | Registration Services | PUB-026 | DIP has sent Registration Service a PUB-026 failed message where the Notification of Registration Data Item Changes has failed DIP validation. The following message is displayed: 'REG1022 - SMSO ID Cannot be set where Market Segment is [Reg.Segement]' | Y | Need to ensure that Registration Services has received the failed message from DIP