## Sheet3 (hidden)
Proposed LDSO QT Scenario | SIT Scenario
Scenario ID | Scenario ID | SITFTS-0050
Role | Scenario Title | Create MPAN
Theme | Theme | New Connection
Business Process | Description | Create an MPAN through new connection process, appoint services and install meter. & Energise the MPAN
Functional Category | Functional Category | Create MPAN
Scenario Title | Functional Area 1 | New Connection |  |  | Business Process Steps
Description | Functional Area 2 | New MPAN, New Connection successful
Boundaries | Creator | Shaun Magee, Dan Gee |  |  | Interface Description
Test Case Variables | Priority | High |  |  | Regression flag
Optionality | Scenario size | Large
Number of test cases | Business Process | BP001, BP002, BP003, BP010B(Related), BP010C (Linked), BP009, BP008, (+BP003A for Smart meters) |  |  | Precondition Test Harness
Scenario size | Boundaries | Processing ends once the Meter is Installed (if not Unmetered) and Energisation has occurred |  |  | Precondition Other
Priority | Test Case Variables | (1) Smart, import+export, forward-dated (MPAN Creation current date)
Systems under test |  | (2) Traditional, single MPAN, forward-dated (MPAN Creation current date)
|  | (3) Advanced Single MPAN, forward-dated (MPAN Creation current date) |  |  | Test evidence
(4) Unmetered, single MPAN, forward-dated (MPAN Creation current date)
| Exception Codes | NA |  |  | Role (simulated)
LDSO Test Case | SIT Test Case
No.
Test Case Id | Test Case Id
Test Case Title | Test Case Title
Test Case Link | Test Case Link
Test Data Requirements | Test Data Requirements
Traceability Requirement |  |  | Test outcome
Test Harness |  |  | Test Harness
Key Validation & Test Evidence |  |  | Interface
BP Step |  |  | requirement
Service initiating process | SIT Test Steps |  | test evidence
Service Recepint Processor
Interface | Test Case Title |  | SITFTS-0050 - Smart Metered
Evidecne Reuiqred | Key Journey | Events | New MPAN Initial Registration - Start
| Step No. |  | 10
| Business Process |  | BP001
| BP Step |  | 5
| Traceability Requirement |  | MHHS-BR-LD-010.1 | MHHS-BR-LD-010.2
| Service Producing Trigger |  | LDSO
| Input/Trigger |  | DB01
| Message Input Event Code |  | N/A
| Service Recipient Processor of Input/Trigger |  | REGS
| Test Step |  | LDSO creates 2 MPAN'S for Import/Export linked MPAN and issues DB01 REGS
| Key Validation & Test Evidence |  | Import/Export Mpan creation and linkage required
| Evidence | Required | Y

## BP010 D_TestScenarios
Test Scenario ID | Role (s) | Theme | Business Process | BP Steps | Interface | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scnarios Size) | Priority | Requirements Covered | Notes
TS_BP010 D_01 | Registration Service/LDSO | MPAN Ownership | BP010 D - Change of Registration Data |  |  | Legacy data item update and Notify parties of updated Legacy data items | In this scenario, Supplier (test harness) uses BAU process to identify Legacy data items update and issues to DIP via MHHS-IF-025, . Registration service will update thier systems to reflect Legacy Data items. Registration service issues MHHS-IF-026 via DIP to Supplier (test harness) , LDSO, Metering Service, Data Service (test harness), Central settlement and ECS (test harness) with the updated Legacy data items information | The boundaries for this scenario are as follows Starting point: The starting point for this scenario will be the Supplier (test harness) to identify Legacy data items and issues to Registration service End point: Legacy data items information to be updated onto LDSO, Metering service, Central settlements and test harness (Supplier, Data service, EES). | single MPAN for Segment A (Advanced) linked related MPAN for Segment S (Smart/Non smart) |  | 2 | VH | H | MHHS-BR-RS-071.13 MHHS-BR-RS-071.14 MHHS-BR-MS-066.6 MHHS-BR-LD-046.1
TS_BP010 D_02 | Registration Service/LDSO | MPAN Ownership | BP010 D - Change of Registration Data |  |  | Update legacy information - Failure message | Registration service issues MHHS-IF-026 to DIP. Registration Service receives failed message via DIP if Registration Service Successful Notification of Supplier Data Changes has failed DIP validation. | The boundaries for this scenario are as follows Starting point: The starting point for this scenario will be the Registration service to issue Notification of Registration Supplier Data Item Changes to DIP. End point: Registration service to receive failure message upon Registration Service Successful Notification of Supplier Data Changes has failed DIP validation | Failure message |  | 1 | H | H | MHHS-BR-RS-137
| Registration Service | MPAN Ownership | BP010 D - Change of Registration Data |  |  | DCC Enrolment updates - Out of scope | In this scenario, DCC notifies the Registration Service with DCC enrolment information via the existing interface. Registration service issues DCC enrolement updates via DIP using MHHS-IF-018 interface to the following participants: Supplier (test harness), Data service (test harness), EES (test harness) Registration Service receives failed message via DIP if Registration Service Successful Notification of Supplier Data Changes has failed DIP validation. | The boundaries for this scenario are as follows Starting point: The starting point for this scenario will be DCC (test harenss) to notify the Registration service with DCC enrolment information End point: The ending point will be Registration service issuing DCC enrolement updates via DIP using MHHS-IF-018 interface to the following participants: Supplier (test harness), Data service (test harness), EES (test harness) | single MPAN for Segment A (Advanced) linked related MPAN for Segment S (Smart/Non smart) |  | 2 | VH | H | MHHS-BR-RS-071.15 MHHS-BR-RS-071.16 MHHS-BR-RS-137 | MHHS-BR-RS-137 - As per assessment criteria document, this requirement is NOT included for QT evidence

## TC_BP010 D_02_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010 D_02_01 | Update legacy information - Failure message | TS_BP010 D_02 | • Segment A • Single MPAN | Registration service to receive failure message upon Registration Service Successful Notification of Supplier Data Changes has failed DIP validation
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP010 D - Step 1010 | MHHS-BR-RS-071.14 | Registration service | DIP | MHHS-IF-026 | The Registration Service will update their systems to reflect the updated Legacy information. Registration Service issues MHHS-IF-026 "Notification of Registration Supplier Data Item Changes" to DIP. | Y | Evidence of Supplier (test harness) issuing MHHS-IF-025 "Supplier Updates to Registration" to DIP
2 | BP010 D - Step 1020 | MHHS-BR-RS-137 | DIP | Registration service | NA | Registration service to receive failure message upon Registration Service Successful Notification of Supplier Data Changes has failed DIP validation | Y | Registration service receiving failure message from DIP

## Requirement coverage
Req. ID | Role(s) | Requirement description
MHHS-BR-RS-137 | Registration Service | All Services must obtain Data Integration Platform error messages in line with the End to End Solution Architecture Document, review the impacted data and re-issue corrected messages/transactions as required