## CoverSheet
QT - Test Scenarios
Version | Description | Author | Date
v0.1 | Initial Draft | Expleo Test Team | 2023-12-29
v0.2 | Feedback given from Code Bodies | Expleo Test Team | 2024-01-31
v0.3 | Updates made by Expleo Team | Expleo Test Team | 2024-02-27
v0.4 | Changes made to incorporate both import/export instances And Changes made to incorporate both primary/secondary instances | Expleo Test Team | 2024-10-15
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## Test Scenario BP0010E
Test Scenario ID | Role (s) | Theme | Business Process | Functional Category | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scenarios Size) | Priority | Expleo Comments
TS_BP010E_01 | Registration Services | Customer Direct Flag | BP010E Customer Direct Flag |  | Receive CDC Request - Accepted | DIP will receive a MHHS-IF-038 request to update Customer Direct Contract (CDC) from the CDC Service Provider. DIP will send a PUB-038 to Registration Services to validate the request. Once the validation checks have been accepted, Registration Services will update their systems and issue a CDC Acceptance Request to DIP via MHHS-IF-039. DIP will receive the request and send a PUB-039 to the Data Service, Metering Service, Supplier and EES to manage the Acceptance Request. | Start point The start point for this scenario would be the CDC Service Provider (Test Harness) will issue a CDC Request to Registration Services via the DIP End point The end point for this scenario would be the (Test Harnesses) Data Service, Metering Service, Supplier and EES will receive PUB-039 via the DIP to manage the accepted request | • Segment S • Segment A |  | 6 | M | L
TS_BP010E_02 | Registration Services | Customer Direct Flag | BP010E Customer Direct Flag |  | Process CDC Removal Request | DIP will receive a MHHS-IF-039 Manage CDC Contract (Site Removal) from the CDC Service Provider. DIP will send a PUB-039 publication request to Registration Services to start the process CDC removal request. Once complete, Registration Services will send a MHHS-IF-039 Removal Request to DIP. DIP will receive the request and send a PUB-039 to the Data Service, Metering Service, Supplier and EES to manage the CDC Removal Notification. | Start point The start point for this scenario would be the CDC Service Provider (Test Harness) will issue a CDC Removal Request to Registration Services via the DIP End point The end point for this scenario would be the (Test Harnesses) the Data Service, Metering Service, Supplier and EES will receive PUB-039 via the DIP to manage the CDC Removal Notification | • Segment S • Segment A |  | 6 | M | L
TS_BP010E_03 | Registration Services | Customer Direct Flag | BP010E Customer Direct Flag |  | Receive CDC Request - Rejected | DIP will receive a MHHS-IF-038 request to update Customer Direct Contract (CDC) from the CDC Service Provider. DIP will send a PUB-038 to Registration Services to validate the request. Once the validation checks have been rejected, Registration Services will issue a CDC Rejection Request to DIP via MHHS-IF-039. DIP will receive the request and send a PUB-039 to the to manage the Rejection Request. | Start point The start point for this scenario would be the CDC Service Provider (Test Harness) will issue a CDC Request to Registration Services via the DIP End point The end point for this scenario would be the (Test Harness) Supplier will receive PUB-039 via the DIP to manage the rejected request | • Segment S • Segment A |  | 6 | M | L
TS_BP010C_04 | Registration Services | Change of Registration Data | BP010C Change of Registration Data |  | Identify & Remove CDC Flags reaching their Contract End Date | Registration Services will Identify & Remove CDC Flags reaching their Contract End Date. | Start point The start point for this scenario would be Registration services being alerted those contracts which have reached Contract End Date End point The end point for this scenario would be that the CDC flag being set and the contracts which have reached their Contract End Date being removed | • Segment S • Segment A |  | 2 | M | L
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be a unique ID and created when each scenario is added
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be the participants role in delivery Multiple roles could be covered in 1 scenario
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each scenario will be linked to Business Processes
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The test scenario description field will outline the objective of the test
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The field will show any other variance related to the test scenario which needs to be considered
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The number of test cases created/related to the test scenario
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This field will outline the size and difficulty of the test scenario Will be flagged as S, M & L
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will outline the priority of the test scenario Flagged as VH, H, M & L

## BP0101E_03_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010E_03_01 | Receive CDC Request - Rejected - Segment S - Smart Metering - Data Service - Related MPAN | TS_BP010E_03 | For this test, the tester will manually create the IF-38 using the Test Harness and trigger this message into REG services. When the REGS receives the IF-38 it will carry out validations and successfully trigger IF-39 to expected participants Test Data • Segment S - Smart Metering • Related MPAN (1 instance for primary MPAN and 1 instance for secondary MPAN) • Data Service Data Items for IF-038 (created manually by the tester in Test Harness) • DI-999 Event Code - [DirectContractDSAdd] • DI-146 - Customer Direct Contract Data Service EffectiveTo Date - Contract End Date [DI-146] > [SysDate+1130] Data Items for IF-039 (automatically triggered by REGS after receiving IF-38) • DI-999 Event Code - [DirectContractDSAdd] • DI-146 - Customer Direct Contract Data Service EffectiveTo Date - Contract End Date [DI-146] > [SysDate+1130] | Registration Services have issued the CDC Rejection Request to back to Data Services via DIP
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 20 to 25 25 to 30 | N/A | Data Service (Test Harness) | DIP | MHHS-IF-038 (primary) MHHS-IF-038 (secondary) | Data service has issued a CDC request to DIP via IF-038 so that DIP can publish the request to registration services (1 instance for primary MPAN and 1 instance for secondary MPAN) | N | Not required
2 | 30 to 35 | MHHS-BR-RS-075 MHHS-BR-RS-076 MHHS-BR-RS-077 | DIP | Registration Services | PUB-038 (primary) PUB-038 (secondary) | Registration Services have received the CDC Request via PUB-038 from DIP and have processed to do the validation checks (1 instance for primary MPAN and 1 instance for secondary MPAN) Registration Service must hold a history of Data Service customer direct contract flags against each MPAN. This must consist of the following new data items: • Customer Direct Contract Data Service DIP ID • Customer Direct Contract Data Service Effective To Date | Y | To ensure that the CDC request has been received successfully
3 | 35 to 40 40 to 45 | MHHS-BR-RS-075 MHHS-BR-RS-076 MHHS-BR-RS-077 | Registration Services | DIP | MHHS-IF-039 (primary) MHHS-IF-039 (secondary) | Registration Services have rejected the validation checks (based on the Test Data given from IF-38) and will issue the CDC request of rejection to DIP via IF-039 to be published. The following message was displayed: 'REG1072 - Customer Direct Contract End Date [DI-146] cannot extend beyond 3 years' (1 instance for primary MPAN and 1 instance for secondary MPAN) | Y | To ensure that the registration services have sent the request successfully over to DIP
4 | 45 to 50 | N/A | DIP | Data Services (Test Harness) | PUB-039 (primary) PUB-039 (secondary) | Data Services will receive PUB-039 from DIP to manage the CDC Rejection Request (1 instance for primary MPAN and 1 instance for secondary MPAN) | N | Not required

## BP0101E_03_02
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010E_03_02 | Receive CDC Request - Rejected - Segment S - Smart Metering - Metering Service - Related MPAN | TS_BP010E_03 | For this test, the tester will manually create the IF-38 using the Test Harness and trigger this message into REG services. When the REGS receives the IF-38 it will carry out validations and successfully trigger IF-39 to expected participants Test Data • Segment S - Smart Metering • Related MPAN (1 instance for primary MPAN and 1 instance for secondary MPAN) • Metering Service Data Items for IF-038 (created manually by the tester in Test Harness) • DI-999 Event Code - [DirectContractMSAdd] • DI-145 - Customer Direct Contract Data Service EffectiveTo Date -- Contract End Date [DI-145] <= [SYSDate] Data Items for IF-039 (automatically triggered by REGS after receiving IF-38) • DI-999 Event Code - [DirectContractMSAdd] • DI-145 - Customer Direct Contract Data Service EffectiveTo Date - Contract End Date [DI-145] <= [SYSDate] | Registration Services have issued the CDC Rejection Request to back to Metering Services via DIP
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 20 to 25 25 to 30 | N/A | Metering Service (Test Harness) | DIP | MHHS-IF-038 (primary) MHHS-IF-038 (secondary) | Metering service has issued a CDC request to DIP via IF-038 so that DIP can publish the request to registration services (1 instance for primary MPAN and 1 instance for secondary MPAN) | N | Not required
2 | 30 to 35 | MHHS-BR-RS-040 MHHS-BR-RS-041 MHHS-BR-RS-042 | DIP | Registration Services | PUB-038 (primary) PUB-038 (secondary) | Registration Services have received the CDC Request via PUB-038 from DIP and have processed to do the validation checks (1 instance for primary MPAN and 1 instance for secondary MPAN) Registration Service must hold a history of Metering Service customer direct contract flags against each MPAN. This must consist of the following new data items: Customer Direct Contract Metering Service DIP ID Customer Direct Contract Metering Service Effective To Date | Y | To ensure that the CDC request has been received successfully
3 | 35 to 40 40 to 45 | MHHS-BR-RS-040 MHHS-BR-RS-041 MHHS-BR-RS-042 | Registration Services | DIP | MHHS-IF-039 (primary) MHHS-IF-039 (secondary) | Registration Services have rejected the validation checks (based on the Test Data given from IF-38) and will issue the CDC request of rejection to DIP via IF-039 to be published. The following message was displayed: 'REG1071 - Contract End Date [DI-145] cannot be in the past' (1 instance for primary MPAN and 1 instance for secondary MPAN) | Y | To ensure that the registration services have sent the request successfully over to DIP
4 | 45 to 50 | N/A | DIP | Metering Service (Test Harness) | PUB-039 (primary) PUB-039 (secondary) | Metering Services will receive PUB-039 from DIP to manage the CDC Rejection Request (1 instance for primary MPAN and 1 instance for secondary MPAN) | N | Not required

## BP0101E_03_03
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010E_03_03 | Receive CDC Request - Rejected - Segment S - Traditional - Data Service - Linked MPAN | TS_BP010E_03 | For this test, the tester will manually create the IF-38 using the Test Harness and trigger this message into REG services. When the REGS receives the IF-38 it will carry out validations and successfully trigger IF-39 to expected participants Test Data • Segment S - Traditional • Linked MPAN (1 instance for import MPAN and 1 instance for export MPAN) • Data Service Data Items for IF-038 (created manually by the tester in Test Harness) • DI-999 Event Code - [DirectContractDSAdd] • DI-146 - Customer Direct Contract Data Service EffectiveTo Date - Contract End Date [DI-146] > [SysDate+1130] Data Items for IF-039 (automatically triggered by REGS after receiving IF-38) • DI-999 Event Code - [DirectContractDSAdd] • DI-146 - Customer Direct Contract Data Service EffectiveTo Date - Contract End Date [DI-146] > [SysDate+1130] | Registration Services have issued the CDC Rejection Request to back to Data Services via DIP
TesStep Id | Business Process Steps | Traceability Requirements |  | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 20 to 25 25 to 30 | N/A | Data Service (Test Harness) | DIP | MHHS-IF-038 (import) MHHS-IF-038 (export) | Data service has issued a CDC request to DIP via IF-038 so that DIP can publish the request to registration services (1 instance for import MPAN and 1 instance for export MPAN) | N | Not required
2 | 30 to 35 | MHHS-BR-RS-075 MHHS-BR-RS-076 MHHS-BR-RS-077 | DIP | Registration Services | PUB-038 (import) PUB-038 (export) | Registration Services have received the CDC Request via PUB-038 from DIP and have processed to do the validation checks (1 instance for import MPAN and 1 instance for export MPAN) Registration Service must hold a history of Data Service customer direct contract flags against each MPAN. This must consist of the following new data items: • Customer Direct Contract Data Service DIP ID • Customer Direct Contract Data Service Effective To Date | Y | To ensure that the CDC request has been received successfully
3 | 35 to 40 40 to 45 | MHHS-BR-RS-075 MHHS-BR-RS-076 MHHS-BR-RS-077 | Registration Services | DIP | MHHS-IF-039 (import) MHHS-IF-039 (export) | Registration Services have rejected the validation checks (based on the Test Data given from IF-38) and will issue the CDC request of rejection to DIP via IF-039 to be published. The following message was displayed: 'REG1072 - Customer Direct Contract End Date [DI-146] cannot extend beyond 3 years' (1 instance for import MPAN and 1 instance for export MPAN) | Y | To ensure that the registration services have sent the request successfully over to DIP
4 | 45 to 50 | N/A | DIP | Data Services (Test Harness) | PUB-039 (import) PUB-039 (export) | Data Services will receive PUB-039 from DIP to manage the CDC Rejection Request (1 instance for import MPAN and 1 instance for export MPAN) | N | Not required

## BP0101E_03_04
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010E_03_04 | Receive CDC Request - Rejected - Segment S - Traditional - Metering Service - Linked MPAN | TS_BP010E_03 | For this test, the tester will manually create the IF-38 using the Test Harness and trigger this message into REG services. When the REGS receives the IF-38 it will carry out validations and successfully trigger IF-39 to expected participants Test Data • Segment S - Traditional Metering • Linked MPAN (1 instance for import MPAN and 1 instance for export MPAN) • Metering Service Data Items for IF-038 (created manually by the tester in Test Harness) • DI-999 Event Code - [DirectContractMSAdd] • DI-145 - Customer Direct Contract Data Service EffectiveTo Date - Contract End Date [DI-145] <= [SYSDate] Data Items for IF-039 (automatically triggered by REGS after receiving IF-38) • DI-999 Event Code - [DirectContractMSAdd] • DI-145 - Customer Direct Contract Data Service EffectiveTo Date - Contract End Date [DI-145] <= [SYSDate] | Registration Services have issued the CDC Rejection Request to back to Metering Services via DIP
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 20 to 25 25 to 30 | N/A | Metering Service (Test Harness) | DIP | MHHS-IF-038 (import) MHHS-IF-038 (export) | Metering service has issued a CDC request to DIP via IF-038 so that DIP can publish the request to registration services (1 instance for import MPAN and 1 instance for export MPAN) | N | Not required
2 | 30 to 35 | MHHS-BR-RS-040 MHHS-BR-RS-041 MHHS-BR-RS-042 | DIP | Registration Services | PUB-038 (import) PUB-038 (export) | Registration Services have received the CDC Request via PUB-038 from DIP and have processed to do the validation checks (1 instance for import MPAN and 1 instance for export MPAN) Registration Service must hold a history of Metering Service customer direct contract flags against each MPAN. This must consist of the following new data items: Customer Direct Contract Metering Service DIP ID Customer Direct Contract Metering Service Effective To Date | Y | To ensure that the CDC request has been received successfully
3 | 35 to 40 40 to 45 | MHHS-BR-RS-040 MHHS-BR-RS-041 MHHS-BR-RS-042 | Registration Services | DIP | MHHS-IF-039 (import) MHHS-IF-039 (export) | Registration Services have rejected the validation checks (based on the Test Data given from IF-38) and will issue the CDC request of rejection to DIP via IF-039 to be published. The following message was displayed: 'REG1071 - Contract End Date [DI-145] cannot be in the past' (1 instance for import MPAN and 1 instance for export MPAN) | Y | To ensure that the registration services have sent the request successfully over to DIP
4 | 45 to 50 | N/A | DIP | Metering Service (Test Harness) | PUB-039 (import) PUB-039 (export) | Metering Services will receive PUB-039 from DIP to manage the CDC Rejection Request (1 instance for import MPAN and 1 instance for export MPAN) | N | Not required

## BP0101E_03_05
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010E_03_05 | Receive CDC Request - Rejected - Segment A - Advanced - Data Service - Single MPAN | TS_BP010E_03 | For this test, the tester will manually create the IF-38 using the Test Harness and trigger this message into REG services. When the REGS receives the IF-38 it will carry out validations and successfully trigger IF-39 to expected participants Test Data • Segment A - Advanced • Single MPAN • Data Service Data Items for IF-038 (created manually by the tester in Test Harness) • DI-999 Event Code - [DirectContractDSAdd] • DI-146 - Customer Direct Contract Data Service EffectiveTo Date - Contract End Date [DI-146] > [SysDate+1130] Data Items for IF-039 (automatically triggered by REGS after receiving IF-38) • DI-999 Event Code - [DirectContractDSAdd] • DI-146 - Customer Direct Contract Data Service EffectiveTo Date - Contract End Date [DI-146] > [SysDate+1130] | Registration Services have issued the CDC Rejection Request to back to Data Services via DIP
TesStep Id | Business Process Steps | Traceability Requirements |  | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 20 to 25 25 to 30 | N/A | Data Service (Test Harness) | DIP | MHHS-IF-038 | Data service has issued a CDC request to DIP via IF-038 so that DIP can publish the request to registration services | N | Not required
2 | 30 to 35 | MHHS-BR-RS-075 MHHS-BR-RS-076 MHHS-BR-RS-077 | DIP | Registration Services | PUB-038 | Registration Services have received the CDC Request via PUB-038 from DIP and have processed to do the validation checks Registration Service must hold a history of Data Service customer direct contract flags against each MPAN. This must consist of the following new data items: Customer Direct Contract Data Service DIP ID Customer Direct Contract Data Service Effective To Date | Y | To ensure that the CDC request has been received successfully
3 | 35 to 40 40 to 45 | MHHS-BR-RS-075 MHHS-BR-RS-076 MHHS-BR-RS-077 | Registration Services | DIP | MHHS-IF-039 | Registration Services have rejected the validation checks (based on the Test Data given from IF-38) and will issue the CDC request of rejection to DIP via IF-039 to be published. The following message was displayed: 'REG1072 - Customer Direct Contract End Date [DI-146] cannot extend beyond 3 years' | Y | To ensure that the registration services have sent the request successfully over to DIP
4 | 45 to 50 | N/A | DIP | Data Services (Test Harness) | PUB-039 | Data Services will receive PUB-039 from DIP to manage the CDC Rejection Request | N | Not required

## BP0101E_03_06
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP010E_03_06 | Receive CDC Request - Rejected - Segment A - Advanced - Metering Service - Related MPAN | TS_BP010E_03 | For this test, the tester will manually create the IF-38 using the Test Harness and trigger this message into REG services. When the REGS receives the IF-38 it will carry out validations and successfully trigger IF-39 to expected participants Test Data • Segment A - Advanced • Single MPAN • Metering Service Data Items for IF-038 (created manually by the tester in Test Harness) • DI-999 Event Code - [DirectContractMSAdd] • DI-145 - Customer Direct Contract Data Service EffectiveTo Date - Contract End Date [DI-145] <= [SYSDate] Data Items for IF-039 (automatically triggered by REGS after receiving IF-38) • DI-999 Event Code - [DirectContractMSAdd] • DI-145 - Customer Direct Contract Data Service EffectiveTo Date - Contract End Date [DI-145] <= [SYSDate] | Registration Services have issued the CDC Rejection Request to back to Metering Services via DIP
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | 20 to 25 25 to 30 | N/A | Metering Service (Test Harness) | DIP | MHHS-IF-038 | Metering service has issued a CDC request to DIP via IF-038 so that DIP can publish the request to registration services | N | Not required
2 | 30 to 35 | MHHS-BR-RS-040 MHHS-BR-RS-041 MHHS-BR-RS-042 | DIP | Registration Services | PUB-038 | Registration Services have received the CDC Request via PUB-038 from DIP and have processed to do the validation checks Registration Service must hold a history of Metering Service customer direct contract flags against each MPAN. This must consist of the following new data items: Customer Direct Contract Metering Service DIP ID Customer Direct Contract Metering Service Effective To Date | Y | To ensure that the CDC request has been received successfully
3 | 35 to 40 40 to 45 | MHHS-BR-RS-040 MHHS-BR-RS-041 MHHS-BR-RS-042 | Registration Services | DIP | MHHS-IF-039 | Registration Services have rejected the validation checks (based on the Test Data given from IF-38) and will issue the CDC request of rejection to DIP via IF-039 to be published. The following message was displayed: 'REG1071 - Contract End Date [DI-145] cannot be in the past' | Y | To ensure that the registration services have sent the request successfully over to DIP
4 | 45 to 50 | N/A | DIP | Metering Service (Test Harness) | PUB-039 | Metering Services will receive PUB-039 from DIP to manage the CDC Rejection Request | N | Not required