## Cover Sheet
LDSO QT - Test Cases
Version | Description | Author | Status | Date
1 | Start Test Cases | Non SIT QT Team |  | 2024-02-21
2 | Test Lead Review | Non SIT QT Team |  | 2024-02-22
3 | Review Comments Incorporated | Non SIT QT Team |  | 2024-02-23
4 | Changes made to incorporate both primary/secondary instances And Changes made to incorporate both import/export instances | Non SIT QT Team |  | 2024-10-23
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## BP011A Test Scenarios
Test Scenario ID | LDSO Role (s) | Theme | Business Process | Steps | Requirements | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scenarios Size) | Priority | Expleo Comments
TS_BP011A_01 | LDSO/Registration Service | Metering Changes | BP011A – Change of Connection Type and/or Market Segment | START • Step 25 (Agree Add / Remove / Upgrade CT) • Step 205 (ACTION Physical Connection Type Change) • Step 220 (Update Registration) • Step 225 (Issue Connection Type Change) • Step 226 (Change of Connection Type) • Step 230 (DIP) (Publish Connection Type Change Notification) • Step 290 (Central Settlements) (Manage Connection Type Change) • Step 215 (Supplier) (Manage Connection Type Change) END | • MHHS-BR-LD-047 • MHHS-BR-LD-048 • MHHS-BR-LD-049 • MHHS-BR-LD-051 • MHHS-BR-LD-052 • MHHS-BR-RS-125.1 | Validate that the LDSO receives request to change the Connection Type, process it & notify the updates to Registration Service | In this scenario, a Supplier (Test Harness) is generating a request to the LDSO for changing the Connection Type. LDSO will process the agreed change of Connection Type, and issue the updates to Registration Service. LDSO must receive requests from the Supplier (Test Harness) to change the Connection Type via a bilaterally agreed communication method (Email, Web Portal, Etc.). LDSO must carry out the agreed change of Connection Type site work in line with the Supplier request and on the agreed date. LDSO must notify the Registration Service, when the Connection Type has been successfully updated. Registration Service must notify participants of any MPAN where the Connection Type has changed using the appropriate interface on the Data Integration Platform. | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the LDSO receiving request for changing the Connection Type from the Supplier (test harness) via a bilaterally agreed communication method (Email, Web Portal, Etc.). End Point The end point will be the LDSO sending the update to the Registration Service within 2 working days after completion of change in Connection Type. The notification will also be sent to Central settlements (Test Harness) and Supplier (Test Harness) from Registration Service via DIP (IF-043 & PUB-043) | • Where the Supplier request has initiated for Segment A (Advanced) and Related MPANs with Connection Type = "W" (Whole Current) • Where the Supplier has initiated the request for Segment S (Smart) and linked Import/Export MPANs with Connection Type = "W" (Whole Current) Negative Variations: • Where the Supplier request has initiated for Segment A (Advanced) and Related MPANs & Connection Type is not accurate • Where the Supplier has initiated the request for Segment S (Smart) and linked Import/Export MPANs with Connection Type = "W" (Whole Current) with Effective Date as backdate Other Possible Variations: W - Whole Current L - LV with CT H - HV with CT E - EHV with CT U - Unmetered |  | 4 | M | VH | IF-043 document states that this is valid only for MSA & MSS.
TS_BP011A_02 | Registration Service/UMSO | Metering Changes | BP011A – Change of Connection Type and/or Market Segment | START • Step 35 (Supplier) (Trigger SP Appointment(s) for Target Wk. Date) • Step 70 (DIP) (Publish Initial Appointment Request(s)) • Step 75 (Validate Initial SP Appointment Request(s)) • Step 80 (Issue Initial SP Appointment Request Response(s)) • Step 85 (DIP) (Publish Initial SP Appointment Request(s)) • Step 90 (Supplier) (Manage SP Appointment Response(s)) • Step 95 (Issue Request SP Proposed Appointment Validation) • Step 100 (DIP) (Publish Proposed SP Appointment Validation Request(s)) • Step 105 (Metering Service) (Manage MS Proposed Appointment Validation Request) • Step 115 (Data Service) (Manage DS Proposed Appointment Validation Request) END | • MHHS-BR-RS-130 • MHHS-BR-RS-011 • MHHS-BR-RS-012 • MHHS-BR-RS-045 • MHHS-BR-RS-046 • MHHS-BR-RS-015 • MHHS-BR-RS-049 • MHHS-BR-MS-001 | Validate that the Registration Service will receive Initial SP Appointment request for validation and generate response | In this scenario, the Registration Service will receive Initial SP Appointment request for validation and publish response to Supplier (Test Harness). Registration Service will also issue request for SP Proposed Appointment Validation to Metering Service (Test Harness) and Data Service (Test Harness) The Registration Service will receive the publication 'Supplier Service Appointment Request' from the DIP and validate the content of the message as per the registration validation rules for Service providers. The Registration Service will respond to the 'Supplier Service Appointment Request' with the appropriate response or Valid or Failed to the DIP . The Registration Service will send 'Registration Service Request for Service Appointment' to the correct service provider via the DIP. The DIP will publish the 'Registration Service Request for Service Appointment' to the Service providers. Metering Service will receive an appointment from the Supplier via The Registration Service. Data Service will receive an appointment from the Supplier via The Registration Service. | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Registration Service receiving Initial SP Appointment request generated by Supplier (Test Harness) for validation via DIP (Test Harness). (IF-031 & PUB-031) End Point There will be two end points generated from Registration Service simultaneously: 1. Registration Service will publish "Initial SP Appointment Response" to Supplier (Test Harness). (IF-032 & PUB-032) 2. Registration Service will issue request for SP Proposed Appointment Validation to Metering Service (Test Harness) and Data Service (Test Harness). (IF-033 & PUB-033) | For Metered Supply: • Where the metering service is for Segment S (Smart Meter) and Related MPAN with an Accepted outcome for W to L • Where the metering service is for Segment A (Advanced Meter) and Import/Export MPAN with an Accepted outcome for L to H • Where the metering service is for Segment S (Traditional) and Import/Export MPAN without an accepted response for W to L • Where the metering service is for Segment A (Advanced Meter) and Related MPAN without an accepted response for H to E For Unmetered Supply: • Where the Request Change of Meter with Proposed MS is raised for Segment U (UMSO) with an Accepted response • Where the Request Change of Meter with Proposed MS is raised for Segment U (UMSO) without an accepted response Other Possible Variations: SEG CSP |  | 6 | H
TS_BP011A_03 | Registration Service | Metering Changes | BP011A – Change of Connection Type and/or Market Segment | START • Step 110 (Metering Service) (Respond to MS Proposed Appointment Request) • Step 130 (DIP) (Publish Proposed SP Appointment Validation Responses) • Step 140 (Manage SP Prospective Appointment Response) • Step 200 (Issue SP Prospective Appointment Outcomes) • Step 195 (DIP) (Publish Prospective Appointment Outcome Responses) • Step 211 (Manage Appointment Response) • Step 210 (Supplier) (Manage Appointment Response) END | • MHHS-BR-MS-002 • MHHS-BR-MS-003 • MHHS-BR-RS-016 • MHHS-BR-RS-050 • MHHS-BR-RS-019 • MHHS-BR-RS-018 | Validate that the Registration Service will manage the appointment responses from the Metering services and publish the responses back to Metering Service (Test Harness) & Supplier (Test Harness) | In this scenario, the Registration Service will manage the appointment responses from the Metering services and publish the responses back to Metering Service (Test Harness) & Supplier (Test Harness) The Registration Service will manage the appointment responses from the Metering services and will send out all responses it has received from the Service providers back to Supplier via the DIP. | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Registration Service receiving responses from the Metering service (Test Harness). (IF-034 & PUB-034) End Point The end point will be the Registration Service publishing the responses back to Metering Service (Test Harness) & Supplier (Test Harness). (IF-035 & PUB-035) | For Metered Supply: • Where the metering service is for Segment S (Smart Meter) and Import/Export MPAN with Connection Type = "W" (Whole Current) and an Accepted outcome for COS (Change of Supply) • Where the metering service is for Segment A (Advanced Meter) and Related MPAN with Connection Type = "L" (LV with CT) and an Accepted outcome for SEG (Change of Segment) • Where the metering service is for Segment S (Traditional Prepayment) and Related MPAN with Connection Type = "W" (Whole Current) and without an accepted response for COS (Change of Supply) • Where the metering service is for Segment A (Advanced Meter) and Single MPAN with Connection Type = "H" (HV with CT) and without an accepted response for COS (Change of Supply) |  | 4 | M
TS_BP011A_04 | Registration Service | Metering Changes | BP011A – Change of Connection Type and/or Market Segment | START • Step 150 (Determine Processing Treatment) • Step 300 (Hold in Appointment Queue) • Step 305 (Review & Re-Validate Prospective Appointment(s)) For Confirmed Appointments: • Step 360 (DIP) (Notify Prospective Appointment as Effective) • Step 355 (Data Service) (Receive Appointment Notification & MTDs) • Step 320 (Metering Service) (Receive Appointment Notification & MTDs) For Lapsed/Void Appointments: • Step 365 (DIP) (Issue MS De-Appointment Notification) END | • MHHS-BR-RS-022 • MHHS-BR-RS-131 • MHHS-BR-RS-033 • MHHS-BR-RS-067 • MHHS-BR-MS-007 • MHHS-BR-MS-030 | Validate that the Registration Service will process Prospective SP Appointments and notify Metering Service (Test Harness), Data Service (Test Harness) & Supplier (Test Harness) | In this scenario, the Registration Service is generating an appointment notification & MTDs (Meter Technical Details) to Data Service (Test Harness) The Registration Service will process and validate Prospective Change of service appointments held in a queue. For valid Metering Service appointments, the Prospective Appointment confirmed as Effective and MTD (Meter Technical Details) will be sent to Data Service (Test Harness). The Registration Service will issue a lapsed notification where no CSS notification has been received for the appointment date or The Registration Service has a new Metering Service appointment that supersedes the open prospective appointment. | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Registration Service determining the Processing Treatment for Prospective SP Appointment Responses. End Point There will be two end points generated from Registration Service: 1. For confirmed appointments, the Registration Service will send Appointment notification & MTDs to Metering Service (Test Harness), Data Service (Test Harness) & Supplier (Test Harness). (IF-036 & PUB-036) 2. For Lapsed/Void Appointment, the Registration Service will issue a lapsed notification to Metering Service (Test Harness), Data Service (Test Harness) & Supplier (Test Harness). (IF-035 & PUB-035) | For Metered Supply: • Where the "Prospective" appointment date (any future date) occurs for: Segment A (Advanced) for COS (Change of Supply) with Related MPAN and Connection Type = "L" (LV with CT) • Where the "Prospective" appointment date (any future date) occurs for: Segment S (Smart) for Change of Service Provider (CSP) for Import/Export MPAN and Connection Type = "W" (Whole Current) • Where the "Prospective" appointment date has lapsed for Segment S (Smart) with Linked MPAN and Connection Type = "W" (Whole Current) that results in Lapsed outcome (MSAppLapsed) for SEG (Change of Segment) • Where the "Prospective" appointment date for Segment A (Advanced) with Single MPAN and Connection Type = "H" (HV with CT) that results in Rejected outcome (MSAppRejected) for SEG (Change of Segment) |  | 4 | M
TS_BP011A_05 | Registration Service | Metering Changes | BP011A – Change of Connection Type and/or Market Segment | START • Step 305 (Review & Re-Validate Prospective Appointment(s)) • Step 315 (DIP) (Issue MS De-Appointment Notification) • Step 340 (De-Appointment Notification) • Step 350 (Data Service) (De-Appointment Notification) END | • MHHS-BR-RS-131 • MHHS-BR-RS-033 • MHHS-BR-RS-067 • MHHS-BR-MS-005 • MHHS-BR-MS-009 • MHHS-BR-MS-009.1 | Validate that the Registration Service will issue de-appointment notification to Metering Service (Test Harness) & Data Service (Test Harness) | In this scenario, the Registration Service will issue a de-appointment notification to Metering Service (Test Harness) and Data Service (Test Harness) The Registration Service will process and validate Prospective Change of service appointments held in a queue. For valid Metering Service appointments, Registration Service will issue a de-appointment notification to Old Metering Service (Test Harness) and Old Data Service (Test Harness). | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Registration Service managing accepted Prospective SP Appointment Responses. End Point The end point will be the Registration Service issuing a de-appointment notification to Old Metering Service (Test Harness) and Old Data Service (Test Harness). (IF-036 & PUB-036) | For Metered Supply: • Where the "Prospective" appointment date (any future date) request is for: Segment A (Advanced) for Change of Service Provider (CSP) with Related MPAN and Connection Type = "L" (LV with CT) • Where the "Prospective" appointment date (any future date) request is for: Segment S (Smart) for Change of Service Provider (CSP) for Import/Export MPAN and Connection Type = "W" (Whole Current) |  | 2 | M
TS_BP011A_06 | Registration Service | Metering Changes | BP011A – Change of Connection Type and/or Market Segment | START • Step 185 (Issue Meter Exchange Details) • Step 245 (Publish Metering Change Request from MS) • Step 240 (Meter Change Validation) For Accepted: • Step 250 (Update Metering Information ) • Step 251 (Re-evaluate Market Segment) • Step 265 (DIP) (Publish Metering Change Request from MS) • Step 275 (Receive Confirmation of Metering Update) • Step 295 (Supplier) (Manage Metering Information Update) • Step 280 (Receive Meter Exchange MTDs & Readings) • Step 281 (Receive Meter Exchange MTDs & Readings) • Step 285 (Receive Meter Exchange MTDs & Readings) For rejected: • Step 260 (DIP) (Publish Metering Change Request from MS) • Step 270 (Metering Service) (Manage Rejection of Metering Update Rejection) END | • MHHS-BR-MS-094 • MHHS-BR-RS-132 • MHHS-BR-RS-108 • MHHS-BR-RS-109 • MHHS-BR-RS-110 • MHHS-BR-RS-111 • MHHS-BR-MS-095 | Validate that the registration Service will validate the metering update using the validation rules and update their systems with the new metering details, if accepted, and update Metering Service (Test Harness), if rejected. | In this scenario, the Registration Service will validate the metering update using the validation rules and update their systems with the new metering details. The Registration Service will validate the metering update using the validation rules and update their systems with the new metering details and update all relevant systems including EES. Where The Registration Service has accepted the metering update the DIP will publish the confirmation to Metering Service, Supplier and Data Service. Where The Registration Service has rejected the metering update the DIP will publish the rejection to Metering Service (Test Harness) and Supplier (if Supplier has subscribed for this option). | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Registration Service receiving Meter Exchange Details and perform validations. (IF-005 & PUB-005) End Point There will be two end points generated from Registration Service: 1. For an accepted Metering Update, Registration Service will update their systems. (IF-006 & PUB-006) 2. For rejected Metering Update, Registration Service will publish to Metering Service (Test Harness). (IF-006 & PUB-006) (Note: The outcome of accepted response will go to BP011B) | For Metered Supply: • Where the metering service is for Segment S (Smart Meter) with Related MPAN and Connection Type = "W" (Whole Current) and an Accepted outcome • Where the metering service is for Segment A (Advanced Meter) with Related MPAN and Connection Type = "L" (LV with CT) and an Accepted outcome • Where the metering service is for Segment S (Traditional Prepayment) with Import/Export MPAN and Connection Type = "W" (Whole Current) and without an accepted response • Where the metering service is for Segment A (Advanced Meter) and Single MPAN with Connection Type = "E" (EHV with CT) without an accepted response |  | 4 | M

## TC_BP011A_06_01
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP011A_06_01 | Process Meter Exchange: Registration Service will validate the metering update using the validation rules and update their systems with the new metering details, if accepted. | TS_BP011A_06 | Test Data • Segment S (Smart) • Related MPAN (for primary and secondary) • Connection Type = "W" (Whole Current) The IF-005 with the following characteristics: • (DI-999) Event Code = [MeterExchange] The IF-006 with the following characteristics: • (DI-999) Event Code = [MeterExchange] • (DI-979) Response Code = A (Accept) | Registration Service will update their systems with the new metering details and send MTDs to Old Metering Service (Test Harness), Old Data Service (Test Harness) and New Data Service (Test Harness)
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP011A - Step 185 | MHHS-BR-MS-094 | New Metering Service (Test Harness) | DIP | IF-005 (primary) IF-005 (secondary) | The new Metering Service, once work has been completed will issue the new metering details to the Registration Service. | N
2 | BP011A - Step 245 & Step 240 | MHHS-BR-RS-132 | DIP | Registration Service | PUB-005 (primary) PUB-005 (secondary) | The DIP will publish the new metering details to the Registration Service via PUB-005. The Registration Service will validate the metering update using the validation rules. | Y | A message to validate that the Registration Service has received new metering details via PUB-005
3 | BP011A - Step 250 | MHHS-BR-RS-108 MHHS-BR-RS-109 (Validate) MHHS-BR-RS-111 (Accept) | Registration Service | DIP | IF-006 (primary) IF-006 (secondary) | The Registration Service will update their systems with the new metering details and update all relevant systems via IF-006 | Y | An evidence to validate that the Registration Service will update their systems with the new metering details
4 | BP011A - Step 265, Step 275, Step 280, Step 281 & Step 285 | MHHS-BR-MS-095 | DIP | New Metering Service (Test Harness) Old Metering Service (Test Harness) Old Data Service (Test Harness) New Data Service (Test Harness) | PUB-006 (primary) New MS PUB-006 (secondary) New MS PUB-006 (primary) Old MS PUB-006 (secondary) Old MS PUB-006 (primary) New DS PUB-006 (secondary) New MS PUB-006 (primary) Old DS PUB-006 (secondary) Old MS | Metering Service will receive confirmation that the metering update has been successful and is now updated in the Registration Service. Where The Registration Service has accepted the metering update the DIP will publish the confirmation to Metering Service (Test Harness), Data Service (Test Harness) and Supplier (Test Harness) | N | A message to validate that the Metering Service (Test Harness) has received confirmation that the metering update has been successful A message to validate that the DIP has published Registration Service Change of Segment Meter Exchange confirmation with MTDs and readings to the old Metering Service (Test Harness), old Data Service (Test Harness) and Supplier (Test Harness) via PUB-006

## TC_BP011A_06_02
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP011A_06_02 | Process Meter Exchange: Registration Service will validate the metering update using the validation rules and update their systems with the new metering details, if accepted. | TS_BP011A_06 | Test Data • Segment A • Related MPAN (for primary and secondary) • Connection Type = "L" (LV with CT) The IF-005 with the following characteristics: • (DI-999) Event Code = [MeterExchange] The IF-006 with the following characteristics: • (DI-999) Event Code = [MeterExchange] • (DI-979) Response Code = A (Accept) | Registration Service will update their systems with the new metering details and send MTDs to Old Metering Service (Test Harness), Old Data Service (Test Harness) and New Data Service (Test Harness).
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP011A - Step 185 | MHHS-BR-MS-094 | New Metering Service (Test Harness) | DIP | IF-005 (import) IF-005 (export) | The new Metering Service, once work has been completed will issue the new metering details to the Registration Service. | N
2 | BP011A - Step 245 & Step 240 | MHHS-BR-RS-132 | DIP | Registration Service | PUB-005 (import) PUB-005 (export) | The DIP will publish the new metering details to the Registration Service via PUB-005. The Registration Service will validate the metering update using the validation rules. | Y | A message to validate that the Registration Service has received new metering details via PUB-005
3 | BP011A - Step 250 | MHHS-BR-RS-108 MHHS-BR-RS-109 (Validate) MHHS-BR-RS-111 (Accept) | Registration Service | DIP | IF-006 (import) IF-006 (export) | The Registration Service will update their systems with the new metering details and update all relevant systems via IF-006 | Y | An evidence to validate that the Registration Service will update their systems with the new metering details
4 | BP011A - Step 265, Step 275, Step 280, Step 281 & Step 285 | MHHS-BR-MS-095 | DIP | New Metering Service (Test Harness) Old Metering Service (Test Harness) Old Data Service (Test Harness) New Data Service (Test Harness) | PUB-006 (import) New MS PUB-006 (export) New MS PUB-006 (import) Old MS PUB-006 (export) Old MS PUB-006 (import) New DS PUB-006 (export) New MS PUB-006 (import) Old DS PUB-006 (export) Old MS | Metering Service will receive confirmation that the metering update has been successful and is now updated in the Registration Service. Where The Registration Service has accepted the metering update the DIP will publish the confirmation to Metering Service (Test Harness), Data Service (Test Harness) and Supplier (Test Harness) | N | A message to validate that the Metering Service (Test Harness) has received confirmation that the metering update has been successful A message to validate that the DIP has published Registration Service Change of Segment Meter Exchange confirmation with MTDs and readings to the old Metering Service (Test Harness), old Data Service (Test Harness) and Supplier (Test Harness) via PUB-006

## TC_BP011A_06_03
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP011A_06_03 | Process Meter Exchange: Registration Service will validate the metering update using the validation rules and update Metering Service (Test Harness), if rejected. | TS_BP011A_06 | Test Data • Segment S (Traditional Prepayment) • Linked MPAN (for import and export) • Connection Type = "W" (Whole Current) The IF-005 with the following characteristics: • (DI-999) Event Code = [MeterExchange] The IF-006 with the following characteristics: • (DI-999) Event Code = [MeterExchange] • (DI-979) Response Code = R (Reject) | Registration Service will update New Metering Service (Test Harness)
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP011A - Step 185 | MHHS-BR-MS-094 | New Metering Service (Test Harness) | DIP | IF-005 (import) IF-005 (export) | The new Metering Service, once work has been completed will issue the new metering details to the Registration Service. | N
2 | BP011A - Step 245 & Step 240 | MHHS-BR-RS-132 | DIP | Registration Service | PUB-005 (import) PUB-005 (export) | The DIP will publish the new metering details to the Registration Service via PUB-005. The Registration Service will validate the metering update using the validation rules. | Y | A message to validate that the Registration Service has received new metering details via PUB-005
3 | BP011A - Step 260 | MHHS-BR-RS-110 (Reject) | Registration Service | DIP | IF-006 (import) IF-006 (export) | Registration Service must, on failure of any validation rules, publish a rejection of the metering update, with associated failure reason, to the Metering Service via the appropriate interface (IF-006) on the Data Integration Platform | Y | An evidence to validate that the Registration Service has published a rejection of the metering update, with associated failure reason
4 | BP011A - Step 270 | MHHS-BR-MS-095 | DIP | New Metering Service (Test Harness) | PUB-006 (import) New MS PUB-006 (export) New MS PUB-006 (import) Old MS PUB-006 (export) Old MS PUB-006 (import) New DS PUB-006 (export) New MS PUB-006 (import) Old DS PUB-006 (export) Old MS | Where The Registration Service has rejected the metering update the DIP will publish the rejection to Metering Service (Test Harness) via IF-006 Metering Service will receive a rejection where the metering update has been unsuccessful. This will contain the reason the update has failed and Metering Service must review this, correct the information and send a new MHHS-IF-005. | N | A message to validate that the Metering Service (Test Harness) has received a rejection where the metering update has been unsuccessful

## TC_BP011A_06_04
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP011A_06_04 | Process Meter Exchange: Registration Service will validate the metering update using the validation rules and update Metering Service (Test Harness), if rejected. | TS_BP011A_06 | Test Data • Segment A • Single MPAN • Connection Type = "E" (EHV with CT) The IF-005 with the following characteristics: • (DI-999) Event Code = [MeterExchange] The IF-006 with the following characteristics: • (DI-999) Event Code = [MeterExchange] • (DI-979) Response Code = R (Reject) | Registration Service will update New Metering Service (Test Harness)
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP011A - Step 185 | MHHS-BR-MS-094 | New Metering Service (Test Harness) | DIP | IF-005 | The new Metering Service, once work has been completed will issue the new metering details to the Registration Service. | N
2 | BP011A - Step 245 & Step 240 | MHHS-BR-RS-132 | DIP | Registration Service | PUB-005 | The DIP will publish the new metering details to the Registration Service via PUB-005. The Registration Service will validate the metering update using the validation rules. | Y | A message to validate that the Registration Service has received new metering details via PUB-005
3 | BP011A - Step 250 | MHHS-BR-RS-110 (Reject) | Registration Service | DIP | IF-006 | The Registration Service will update their systems with the new metering details and update all relevant systems via IF-006 | Y | An evidence to validate that the Registration Service will update their systems with the new metering details
4 | BP011A - Step 270 | MHHS-BR-MS-095 | DIP | New Metering Service (Test Harness) | PUB-006 | Where The Registration Service has rejected the metering update the DIP will publish the rejection to Metering Service (Test Harness) via IF-006 Metering Service will receive a rejection where the metering update has been unsuccessful. This will contain the reason the update has failed and Metering Service must review this, correct the information and send a new MHHS-IF-005. | N | A message to validate that the Metering Service (Test Harness) has received a rejection where the metering update has been unsuccessful

## Requirements
| denotes - req part of BSC Assessment Criteria | denotes - req OOS of BSC Assessment Criteria | denotes - req still in question | Highlighted to mention that the requirements are mentioned under different BP in BRS documents & not for BP011A
Test Scenario ID | Reference | Area | Requirement | Requirement Description | Supporting information/ questions | Process | Step | Interface | Optionality | Reason for change
TS_BP011_01 | MHHS-BR-LD-047 | LDSO | Receive Change of Connection Type request | LDSO must receive requests from the Supplier to change the Connection Type via a bilaterally agreed communication method. |  | BP011B Change of Connection Type/Market Segment | 30 (BP011A-25)
| MHHS-BR-LD-048 | LDSO | Agree Connection Type change date | LDSO must liaise with the Supplier to agree and confirm a target work date |  | BP011B Change of Connection Type/Market Segment | 30 (BP011A-25)
| MHHS-BR-LD-049 | LDSO | Carry out physical Change of Connection work | LDSO must carry out the agreed change of Connection Type site work in line with the Supplier request and on the agreed date |  | BP011B Change of Connection Type/Market Segment | 60 (BP011A-205)
| MHHS-BR-LD-051 | LDSO | Notify Registration Service of Change of Connection Type | LDSO must notify the Registration Service via internal interface, when the Connection Type has been successfully updated. LDSO should provide the update as quickly as possible, but no later than 3 working days after completion of the work. In the case of Related MPANs the LDSO must update and notify changes for all Secondary MPANs in line with the Connection Type for the Primary MPAN. In the case of linked Import/Export MPANs, the LDSO must update and notify changes for all Export MPANs in line with the Connection Type for the linked Import MPAN. |  | BP011B Change of Connection Type/Market Segment | 85 (BP011A-220) |  |  | DIN-383
| MHHS-BR-LD-052 | LDSO | Resolve Change of Connection Type queries | LDSO must liaise with Suppliers and Metering Services to resolve queries where it is identified that an existing Connection Type is not accurate. A Change of Connection Type Change should be agreed (Supplier/Metering Service/LDSO); and actioned by the LDSO with an Effective Date equal to that at which the discrepancy was identified i.e it should not be backdated. |  | BP011B Change of Connection Type/Market Segment | 85 (BP011A-220)
| MHHS-BR-RS-125.1 | Registration Service | Inform participants of Change of Connection Type | Registration Service must notify participants of any MPAN where the Connection Type has changed using the appropriate interface on the Data Integration Platform. | MHHS-IF-043 to Central Settlements, Supplier, Data Service and Metering Service | BP011B Change of Connection Type/ Segment | 541 (BP011A - 225) | MHHS-IF-043
TS_BP011_02 | MHHS-BR-RS-130 | Registration Service | Change of Market Segment proposed appointment validation | Registration Service must not apply any segment based validation rules on receipt of a Supplier Service Appointment Request, where the Appointment reason is "SEG". All other validation rules, as set out in the appropriate interface specification should be applied. | Appointment scenario = "SEG" | BP011A Change of Connection Type/ Segment | 75
| MHHS-BR-RS-011 | Registration Service | Send Initial Metering Service Appointment acceptance | Registration Service must publish a Registration Service Response to Supplier Service Appointment Request, using the appropriate interface on the Data Integration Platform, with initial acceptance of the proposed Metering Service where validation rules are met. | MHHS-IF-032 - Appointment scenario = "CSP", "COS" or "SEG" | BP002 Change of Metering Service | 45 | MHHS-IF-032
| MHHS-BR-RS-012 | Registration Service | Send Metering Service Appointment rejection | Registration Service must publish a Registration Service Response to Supplier Service Appointment Request, using the appropriate interface on the Data Integration Platform, with a rejection of the proposed Metering Service and associated rejection reason, where validation rules are not met. | MHHS-IF-032 - Appointment scenario = "CSP", "COS" or "SEG" | BP002 Change of Metering Service | 45 | MHHS-IF-032
| MHHS-BR-RS-045 | Registration Service | Send Initial Data Service Appointment acceptance | Registration Service must publish a Registration Service Response to Supplier Service Appointment Request, using the appropriate interface on the Data Integration Platform, with initial acceptance of the proposed Data Service where validation rules are met. | MHHS-IF-032 - Appointment scenario = "CSP", "COS" or "SEG" | BP003 Change of Data Service | 45 | MHHS-IF-032
| MHHS-BR-RS-046 | Registration Service | Send Data Service Appointment rejection | Registration Service must publish a Registration Service Response to Supplier Service Appointment Request, using the appropriate interface on the Data Integration Platform, with a rejection of the proposed Data Service and associated rejection reason, where validation rules are not met. | MHHS-IF-032 - Appointment scenario = "CSP", "COS" or "SEG" | BP003 Change of Data Service | 45 | MHHS-IF-032
| MHHS-BR-RS-015 | Registration Service | Send proposed Metering Service a Request for Service Appointment | Registration Service must publish a Registration Service Request for Service Appointment for the proposed Metering Service using the appropriate interface on the Data Integration Platform where initial validation rules are met. | MHHS-IF-033 - Appointment scenario = "CSP", "COS" or "SEG" | BP002 Change of Metering Service | 60 | MHHS-IF-033
| MHHS-BR-RS-049 | Registration Service | Send proposed Data Service a Request for Service Appointment | Registration Service must publish a Registration Service Request for Service Appointment for the proposed Data Service using the appropriate interface on the Data Integration Platform where initial validation rules are met. | MHHS-IF-033 - Appointment scenario = "CSP", "COS" or "SEG" | BP003 Change of Data Service | 60 | MHHS-IF-033
| MHHS-BR-MS-001 | Metering Service | Receive proposed appointment service request | Metering Service must obtain Registration Service Request for Service Appointment with Metering Service proposed appointment requests, via the appropriate interface on the Data Integration Platform | PUB-033 | BP002 Change of Metering Service | 70 | PUB-033 | None
TS_BP011_03 | MHHS-BR-MS-002 | Metering Service | Validate and respond to proposed appointment service request | Metering Service must confirm that they are certified to service the connection type and able to contractually deliver the Metering Service based on the information contained in the proposed appointment request and publish a response (acceptance or rejection) on the Data Integration Platform via the appropriate interface. Where a request is rejected the Metering Service must provide an appropriate rejection reason in the response. When the appointment request is accepted the Metering Service should be aware that at this point the appointment remains "prospective" and there is a possibility that it may need to be lapsed at a later stage. | MHHS-IF-034 to Registration Service | BP002 Change of Metering Service | 75 | MHHS-IF-034 | None
| MHHS-BR-MS-003 | Metering Service | Delete data for rejected appointments | Metering Service must, for any proposed appointments it rejects, delete any metering details received, within 30 days of notifying the rejection. |  | BP002 Change of Metering Service | 75 |  | None
| MHHS-BR-RS-016 | Registration Service | Receive proposed Metering Service Response to Appointment request | Registration Service must obtain Service Provider Response to Appointment Requests from the proposed Metering Service via the appropriate interface on the Data Integration Platform and maintain records accordingly | PUB-034 - Appointment scenario = "CSP", "COS" or "SEG" | BP002 Change of Metering Service | 85 | PUB-034
| MHHS-BR-RS-050 | Registration Service | Receive proposed Data Service Response to Appointment request | Registration Service must obtain Service Provider Response to Appointment Requests from the proposed Data Service via the appropriate interface on the Data Integration Platform and maintain records accordingly | PUB-034 - Appointment scenario = "CSP", "COS" or "SEG" | BP003 Change of Data Service | 85 | PUB-034
| MHHS-BR-RS-019 | Registration Service | Notify incumbent Metering Service | Registration Service must, where a Traditional or Advanced Meter is installed, publish a Registration Service Appointment Status Notification to the incumbent Metering Service, where the proposed Metering Service has accepted. | MHHS-IF-035 - Appointment scenario = "CSP", "COS" or "SEG" Note, Meter Type would need to be looked up in ISD in order to identify whether a meter is Smart or Traditional | BP002 Change of Metering Service | 86 | MHHS-IF-035
| MHHS-BR-RS-018 | Registration Service | Send proposed Metering Service Appointment response | Registration Service must publish a Registration Service Appointment Status Notification to the Supplier and Metering Service confirming the Metering Service response using the appropriate interface on the Data Integration Platform | MHHS-IF-035 - Appointment scenario = "CSP", "COS" or "SEG" | BP002 Change of Metering Service | 87 | MHHS-IF-035
TS_BP011_04 | MHHS-BR-RS-022 | Registration Service | Store details of Prospective Metering Service appointments in Prospective Appointments Queue | Registration Service must be able to hold Prospective Metering Service appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received. | Appointment scenario = "CSP", "COS" or "SEG" . | BP002 Change of Metering Service | 101
| MHHS-BR-RS-131 | Registration Service | Change of Market Segment lapsed/rejected appointments | Registration Service must, where the Appointment reason is SEG, send a lapsed/rejected appointment notification to the Service Provider if it is 3 working days (configurable) beyond the appointment date, | MHHS-IF-035 - Appointment scenario = "SEG" | BP011A Change of Connection Type/ Segment | 305 | MHHS-IF-035 |  | DIN-383
| MHHS-BR-RS-033 | Registration Service | Send Metering Service Appointment notification | Registration Service must publish a Registration Service Notification of Service Appointment & Supporting Info with registration and metering details via the appropriate interface on the Data Integration Platform when a Metering Service appointment has been confirmed and will become effective. | MHHS-IF-036 to Metering Service, Data Service, Supplier, Market-wide Data Service and LDSO Appointment scenario = "CSP", "COS" or "SEG" Domestic Premise Indicator notified should be as held in the Registration System as provided by CSS. | BP002 Change of Metering Service | 240 | MHHS-IF-036
| MHHS-BR-RS-067 | Registration Service | Send Data Service Appointment notification | Registration Service must publish a Registration Service Notification of Service Appointment & Supporting Info with registration and metering details via the appropriate interface on the Data Integration Platform when a Data Service appointment has been confirmed and will become effective. | MHHS-IF-036 to Metering Service, Data Service, Supplier, Market-wide Data Service and LDSO Appointment scenario = "CSP", "COS" or "SEG" Domestic Premise Indicator notified should be as held in the Registration System as provided by CSS. | BP003 Change of Data Service | 250 | MHHS-IF-036
| MHHS-BR-MS-007 | Metering Service | Receive Metering Service appointment notification | Metering Service must obtain Registration Service Notification of Service Appointment & Supporting Info updates, with confirmed Metering Service appointments, via the appropriate interface on the Data Integration Platform and update records with MPAN and Meter Technical Details (ADS and SDS only). For the avoidance of doubt this is the message that indicates that an appointment will/has taken effect. | PUB-036. Note: for Smart meters PUB-036 contains all the Meter Technical Detail required ( No additional D-flow as is the case with Trad and Advanced ) | BP002 Change of Metering Service | 195 | PUB-036 | None
| MHHS-BR-MS-030 | Metering Service | Receive Data Service appointment notification | Metering Service must obtain Registration Service Notification of Service Appointment & Supporting Info updates, with confirmed Data Service appointments, via the appropriate interface on the Data Integration Platform and maintain records accordingly | PUB-036. Note for Smart meters PUB-036 contains all the Meter Technical Detail required ( No additional D-flow as is the case with Trad and Advanced ) | BP003 Change of Data Service | 281 | PUB-036 | None
TS_BP011_05 | MHHS-BR-RS-131 | Registration Service | Change of Market Segment lapsed/rejected appointments | Registration Service must, where the Appointment reason is SEG, send a lapsed/rejected appointment notification to the Service Provider if it is 3 working days (configurable) beyond the appointment date, | MHHS-IF-035 - Appointment scenario = "SEG" | BP011A Change of Connection Type/ Segment | 305 | MHHS-IF-035 |  | DIN-383
| MHHS-BR-RS-033 | Registration Service | Send Metering Service Appointment notification | Registration Service must publish a Registration Service Notification of Service Appointment & Supporting Info with registration and metering details via the appropriate interface on the Data Integration Platform when a Metering Service appointment has been confirmed and will become effective. | MHHS-IF-036 to Metering Service, Data Service, Supplier, Market-wide Data Service and LDSO Appointment scenario = "CSP", "COS" or "SEG" Domestic Premise Indicator notified should be as held in the Registration System as provided by CSS. | BP002 Change of Metering Service | 240 | MHHS-IF-036
| MHHS-BR-RS-067 | Registration Service | Send Data Service Appointment notification | Registration Service must publish a Registration Service Notification of Service Appointment & Supporting Info with registration and metering details via the appropriate interface on the Data Integration Platform when a Data Service appointment has been confirmed and will become effective. | MHHS-IF-036 to Metering Service, Data Service, Supplier, Market-wide Data Service and LDSO Appointment scenario = "CSP", "COS" or "SEG" Domestic Premise Indicator notified should be as held in the Registration System as provided by CSS. | BP003 Change of Data Service | 250 | MHHS-IF-036
| MHHS-BR-MS-005 | Metering Service | Receive de-appointment notification | Metering Service must obtain Registration Service Notification of Service De-Appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly | PUB-037 A second notification will be received, if the first notification does not identify the new Metering Service. | BP002 Change of Metering Service | 230 | PUB-037 | None
| MHHS-BR-MS-009 | MSA/MSS | Receive Metering Service de-appointment for linked Export MPAN | MSA/MSS must obtain Export MPAN de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. MSA/MSS should note this message will be automatically triggered when a change of Metering Service has successfully completed for the linked import MPAN. | PUB-037 | BP002 Change of Metering Service | 760 | PUB-037 | None
| MHHS-BR-MS-009.1 | MSA/MSS | Receive Metering Service de-appointment for linked Related MPAN | MSA/MSS must obtain Related MPAN de-appointments via the appropriate interface on the Data Integration Platform and maintain records accordingly. MSA/MSS should note this message will be automatically triggered when a change of Metering Service has successfully completed for the Primary Related MPAN. | PUB-037 | BP002 Change of Metering Service | 760 | PUB-037 | None
TS_BP011_06 | MHHS-BR-MS-094 | MSA/MSS | Issue Change of Segment Meter exchange details and reads | MSA/MSS must be able to publish Change of Segment Meter Exchange details and reads via the appropriate interfaces, where it is not formally appointed as the Metering Service but does have an accepted prospective appointment (Appointment Scenario = "SEG"). The MSA/MSS must issue the work update to Registration at the earliest opportunity but within [3] days of completion at the latest. | MHHS-IF-005 to Registration Service and other DTC flows as outlined in BP009 Change of Metering process. This requirement is added to cater for non-appointed Metering Services issuing the work and to highlight the critical nature of the timeliness to ensure all elements of the Change of Segment happen promptly. | BP011A Change of Connection Type/ Change of Segment | 180-185 | MHHS-IF-005 | None
| MHHS-BR-RS-132 | Registration Service | Change of Market Segment metering validation | Registration Service must allow a prospective Metering Service to provide updated metering details for an MPAN, via the appropriate interface, where there is a prospective Metering Service Appointment for that MPAN, the Appointment reason is "SEG" and the metering activity date is >= the prospective appointment date | MHHS-IF-005 | BP011A Change of Connection Type/ Segment | 240 | MHHS-IF-005
| MHHS-BR-RS-108 | Registration Service | Receive updated metering details | Registration Service must obtain updated metering details from the Metering Service via the appropriate interface on the Data Integration Platform | PUB-005 | BP009 Change of Metering | 95 | PUB-005
| MHHS-BR-RS-109 | Registration Service | Validate metering details | Registration Service must carry out validation of the metering update in line with the validation rules set out in the appropriate interface specification (MHHS-IF-005). |  | BP009 Change of Metering | 100
| MHHS-BR-RS-110 | Registration Service | Reject Metering Update | Registration Service must, on failure of any validation rules, publish a rejection of the metering update, with associated failure reason, to the Metering Service via the appropriate interface on the Data Integration Platform | MHHS-IF-006 | BP009 Change of Metering | 135 | MHHS-IF-006
| MHHS-BR-RS-111 | Registration Service | Accept Metering Update | Registration Service must, on passing all validation rules, update Registration Service systems and publish acceptance of the metering update via the appropriate interface on the Data Integration Platform | MHHS-IF-006 to Supplier, LDSO, Metering Service and Data Service | BP009 Change of Metering | 125 | MHHS-IF-006
| MHHS-BR-MS-095 | MSA/MSS | Receive Change of Segment Meter exchange confirmation | MSA/MSS must be able to obtain a Registration Service Change of Segment Meter Exchange confirmation with MTDs and readings via the appropriate interface on the Data Integration Platform, even when it is from a 3rd party Metering Service. | PUB-006 | BP011A Change of Connection Type/ Change of Segment | 280 | PUB-006 | None
Note on F25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DIN-705