## Sheet3 (hidden)
Proposed LDSO QT Scenario | SIT Scenario
Scenario ID | Scenario ID | SITFTS-0050
Role | Scenario Title | Create MPAN
Theme | Theme | New Connection
Business Process | Description | Create an MPAN through new connection process, appoint services and install meter. & Energise the MPAN
Functional Category | Functional Category | Create MPAN
Scenario Title | Functional Area 1 | New Connection |  |  | Business Process Steps
Description | Functional Area 2 | New MPAN, New Connection successful
Boundaries | Creator | Shaun Magee, Dan Gee |  |  | Interface Description
Test Case Variables | Priority | High |  |  | Regression flag
Optionality | Scenario size | Large
Number of test cases | Business Process | BP001, BP002, BP003, BP010B(Related), BP010C (Linked), BP009, BP008, (+BP003A for Smart meters) |  |  | Precondition Test Harness
Scenario size | Boundaries | Processing ends once the Meter is Installed (if not Unmetered) and Energisation has occurred |  |  | Precondition Other
Priority | Test Case Variables | (1) Smart, import+export, forward-dated (MPAN Creation current date)
Systems under test |  | (2) Traditional, single MPAN, forward-dated (MPAN Creation current date)
|  | (3) Advanced Single MPAN, forward-dated (MPAN Creation current date) |  |  | Test evidence
(4) Unmetered, single MPAN, forward-dated (MPAN Creation current date)
| Exception Codes | NA |  |  | Role (simulated)
LDSO Test Case | SIT Test Case
No.
Test Case Id | Test Case Id
Test Case Title | Test Case Title
Test Case Link | Test Case Link
Test Data Requirements | Test Data Requirements
Traceability Requirement |  |  | Test outcome
Test Harness |  |  | Test Harness
Key Validation & Test Evidence |  |  | Interface
BP Step |  |  | requirement
Service initiating process | SIT Test Steps |  | test evidence
Service Recepint Processor
Interface | Test Case Title |  | SITFTS-0050 - Smart Metered
Evidecne Reuiqred | Key Journey | Events | New MPAN Initial Registration - Start
| Step No. |  | 10
| Business Process |  | BP001
| BP Step |  | 5
| Traceability Requirement |  | MHHS-BR-LD-010.1 | MHHS-BR-LD-010.2
| Service Producing Trigger |  | LDSO
| Input/Trigger |  | DB01
| Message Input Event Code |  | N/A
| Service Recipient Processor of Input/Trigger |  | REGS
| Test Step |  | LDSO creates 2 MPAN'S for Import/Export linked MPAN and issues DB01 REGS
| Key Validation & Test Evidence |  | Import/Export Mpan creation and linkage required
| Evidence | Required | Y

## Cover Sheet
LDSO QT - Test Scenarios
Version | Description | Author | Status | Date
V 1.0 | BP011 C Test cases final draft for Test scenario TS_BP0011C_01 | Syed Naveedh | Complete | 2024-02-27
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## BP011C Test Scenarios
Test Scenario ID | LDSO Role (s) | Theme | Business Process | Steps | Requirements | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scenarios Size) | Priority | Expleo Comments
TS_BP0011C_01 | Reg Service | Metering Changes | BP011C - Registration Service Monitoring and Notification Processes | START Step 10 Step 20 Step 30 Step 40 Step 90 END | MHHS-BR-RS-128.3 MHHS-BR-RS-128.4 MHHS-BR-RS-128.5 | Linked MPAN alignment - issuing de-appointment for existing Metering service and confirmed appointment to align metering service | The Registration Service will identify the linked MPAN set to assess if the service providers are aligned, if the MPAN is the primary and/or a linked import MPAN and if the appointed Metering Service for the secondary and primary MPAN is not aligned the Registration Service will issue a de-appointment of existing metering service notification via MHHS-IF-037 . It will issue out a confirmed appointment via MHHS-IF-036 to align the Metering Service | The boundaries for this scenario are as follows: Start Point Registration Service identify the linked MPAN set End Point Registration service to issue de-appointment of existing metering service via DIP in case the appointed Metering service for the primary and secondary MPAN mis-matches. Registrations Service will issue out a confirmed appointment of matching metering service to align the Metering Service | 1. Linked MPAN where Metering Service for the secondary and primary MPAN is not aligned. Segments Smart and advanced |  | 1 | H | H
TS_BP0011C_02 | Reg Service | Metering Changes | BP011C - Registration Service Monitoring and Notification Processes | START Step 10 Step 20 Step 30 Step 130 Step 140 Step 150 Step 190 END | MHHS-BR-RS-128.3 MHHS-BR-RS-128.4 MHHS-BR-RS-128.6 MHHS-BR-RS-128.7 MHHS-BR-RS-128.8 | Related smart or advanced MPAN alignment - issuing de-appointment for existing Data service and confirmed appointment to align data service | If the Registration Service identifies that the MPAN is a Related smart MPAN or an advanced MPAN, the Registration service will validate if the appointed Data Service for the secondary MPAN is aligned to the primary MPAN If the appointed Data Service for the secondary and primary MPAN is not aligned the Registration Service will issue a de-appointment of existing Data Service. Registrations Service will issue out a confirmed appointment to the matching Data Service | The boundaries for this scenario are as follows: Start Point Registration Service identify the linked MPAN set End Point Registration service to issue de-appointment of existing data service via DIP in case the appointed data service for the primary and secondary MPAN mis-matches. Registrations Service will issue out a confirmed appointment of matching data service to align the data Service | 1. Linked MPAN - with 1 MPAN for export and 2 MPAN's for import. 2 import MPAN's with difference data services, segments being Smart 2. Linked MPAN - with 1 MPAN for export and 2 MPAN's for import. 2 import MPAN's with difference data services, segments being Traditional |  | 2 | VH | H
TS_BP0011C_03 | Reg Service | Metering Changes | BP011C - Registration Service Monitoring and Notification Processes | START Step 500 Step 510 Step 520 Step 530 Step 550 END | MHHS-BR-RS-128.1 | Registration Service issues advisory notification for missing service provider | The Registration Service will identify MPANs where no service provider is appointed and for MPANs with a missing service provider and SSD is today or there has not been a notification sent within 7 days the Registration Service will issue a missing service provider notification via MHHS-IF-045 to Supplier (Test Harness) | The boundaries for this scenario are as follows: Start Point Registration Service identify MPANs with no service provider is appointed End Point The Registration Service will identify MPANs where no service provider is appointed and for MPANs with a missing service provider and SSD is current date or there has not been a notification sent within 7 days the Registration Service will issue a missing service provider notification via MHHS-IF-045 to Supplier (Test Harness) | 1. Linked MPANs with missing service providers. Segment Smart and Advanced 2. Related MPANs with missing service providers. Segment Smart and Advanced |  | 2 | VH | H
TS_BP0011C_04 | Reg Service | Metering Changes | BP011C - Registration Service Monitoring and Notification Processes | START Step 500 Step 510 Step 560 Step 570 Step 575 Step 580 END | MHHS-BR-RS-128 | Registration Service issues advisory notification for Market Segment Invalid | The Registration Service will identify MPANs whether the Market segment flag is invalid and will check to confirm if the Segment change was within the last 2 days. Where the Market Segment flag is invalid and the Segment change was more than 2 days ago and there has not been a notification sent within 7 days the Registration Service will issue an Invalid Market Segment notification via MHHS-IF-045. | The boundaries for this scenario are as follows: Start Point Registration Service identify MPANs where market segment flag is invalid End Point The Registration Service will identify MPANs whether the Market segment flag is invalid and will check to confirm if the Segment change was within the last 3 working days. Where the Market Segment flag is invalid and the Segment change was more than 3 working days ago and there has not been a notification sent within 7 days from the current date the Registration Service will issue an Invalid Market Segment notification via MHHS-IF-045. | 1. 1 single MPANs where service provider is already appointed. Segment is A. Market segment invalid flag 'N' |  | 1 | VH | H
TS_BP0011C_05 | Reg Service | Metering Changes | BP011C - Registration Service Monitoring and Notification Processes | START Step 500 Step 510 Step 560 Step 600 Step 610 Step 620 Step 630 END | MHHS-BR-RS-128.2 | Registration Service issues advisory notification for mis aligned consent granularity | The Registration Service will identify MPANs where the consent granularity is mis-aligned and there has not been a notification sent within 7 days. Registration Service will issue an Inconsistent Consent Advisory notification via MHHS-IF-045. | The boundaries for this scenario are as follows: Start Point Registration Service identify MPANs where consent granularity is misaligned End Point Supplier (Test Harness) receivingMHHS-IF-045 | 1. Linked MPANs where service providers are already appointed and Segment is S. Market segment invalid flag Y |  | 1 | VH | H

## TC_BP0011C_01_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP0011C_01_01 | Linked MPAN alignment - issuing de-appointment for existing Metering service and confirmed appointment to align metering service | TS_BP0011C_01 | Linked MPAN where Metering Service for the secondary and primary MPAN is not aligned Segments Smart and advanced | Registration service to issue de-appointment of existing metering service via DIP in case the appointed Metering service for the primary and secondary MPAN mis-matches. Registrations Service will issue out a confirmed appointment of matching metering service to align the Metering Service
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP011C-Step 10 | NA | Registration service | Registration service | NA | Registration Service will identify the linked MPAN set to assess if the service providers are aligned | Y | Registration service identifies linked MPAN set
2 | BP011C-Step 20/Step 30 | MHHS-BR-RS-128.3 | Registration service | Registration service | NA | Registration Service with assess if the MPAN is the primary and/or a linked import MPAN. Registration service validates if appointed Metering Service for the secondary MPAN is aligned to the primary MPAN | Y | Evidence of Registration service assess MPAN to be secondary and/or a linked import MPAN. Evidence of Registration service validating the appointed Metering Service to be mis-matched for the secondary MPAN and primary MPAN.
3 | BP011C-Step 40 | MHHS-BR-RS-128.4 | Registration service | DIP | MHHS-IF-037 | Registration Service will issue a de-appointment of existing metering service notification via MHHS-IF-037 "Notification of Service De-Appointment" | Y | Evidence of Registration service issuing MHHS-IF-037
4 | BP011C-Step 50/Step 60/ Step 70 | NA | DIP | Test harness (Supplier, Existing Metering service) | PUB-037 | DIP publishes PUB-037 to Test harness (Supplier, Existing Metering service) | N | NA
5 | BP011C-Step 90 | MHHS-BR-RS-128.5 | Registration service | DIP | MHHS-IF-036 | Registrations Service will issue out a confirmed appointment to the DIP via MHHS-IF-036 "Service Provider Notification of Appointment" to align the Metering Service | Y | Evidence of Registration service issuing MHHS-IF-036
6 | BP011C-Step 100/Step 110/ Step 120 | NA | DIP | Test harness (Supplier, Prospective Metering service) | PUB-036 | DIP publishes PUB-037 to Test harness (Supplier, Prospective Metering service) | N | NA

## Requirement coverage
Req. ID | Role(s) | Requirement description
MHHS-BR-RS-128.3 | Registration service | Registration Service must, after processing the prospective appointment queue each day, in the case where there are Related MPANs or linked Import/Export MPANs, review for any Secondary MPANs/ Export MPANs that do not have the same Metering Service as the Primary MPAN/ linked Import MPAN.
MHHS-BR-RS-128.4 | Registration service | Registration Service must automatically publish a de-appointment notification via the appropriate interface on the Data Integration Platform, for any Secondary MPAN/ linked Export MPAN which has a mis-aligned Metering Service. The Metering Service should be de-appointed with an effective date of D.
MHHS-BR-RS-128.5 | Registration service | Registration Service must automatically publish an appointment confirmation via the appropriate interface on the Data Integration Platform, for any Secondary MPAN/ linked Export MPAN needing to be aligned with the Primary/ Import MPAN Metering Service. The same Metering Service as the Primary/ Import should be appointed with an effective date of D+1.
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DIN393