## Sheet3 (hidden)
Proposed LDSO QT Scenario | SIT Scenario
Scenario ID | Scenario ID | SITFTS-0050
Role | Scenario Title | Create MPAN
Theme | Theme | New Connection
Business Process | Description | Create an MPAN through new connection process, appoint services and install meter. & Energise the MPAN
Functional Category | Functional Category | Create MPAN
Scenario Title | Functional Area 1 | New Connection |  |  | Business Process Steps
Description | Functional Area 2 | New MPAN, New Connection successful
Boundaries | Creator | Shaun Magee, Dan Gee |  |  | Interface Description
Test Case Variables | Priority | High |  |  | Regression flag
Optionality | Scenario size | Large
Number of test cases | Business Process | BP001, BP002, BP003, BP010B(Related), BP010C (Linked), BP009, BP008, (+BP003A for Smart meters) |  |  | Precondition Test Harness
Scenario size | Boundaries | Processing ends once the Meter is Installed (if not Unmetered) and Energisation has occurred |  |  | Precondition Other
Priority | Test Case Variables | (1) Smart, import+export, forward-dated (MPAN Creation current date)
Systems under test |  | (2) Traditional, single MPAN, forward-dated (MPAN Creation current date)
|  | (3) Advanced Single MPAN, forward-dated (MPAN Creation current date) |  |  | Test evidence
(4) Unmetered, single MPAN, forward-dated (MPAN Creation current date)
| Exception Codes | NA |  |  | Role (simulated)
LDSO Test Case | SIT Test Case
No.
Test Case Id | Test Case Id
Test Case Title | Test Case Title
Test Case Link | Test Case Link
Test Data Requirements | Test Data Requirements
Traceability Requirement |  |  | Test outcome
Test Harness |  |  | Test Harness
Key Validation & Test Evidence |  |  | Interface
BP Step |  |  | requirement
Service initiating process | SIT Test Steps |  | test evidence
Service Recepint Processor
Interface | Test Case Title |  | SITFTS-0050 - Smart Metered
Evidecne Reuiqred | Key Journey | Events | New MPAN Initial Registration - Start
| Step No. |  | 10
| Business Process |  | BP001
| BP Step |  | 5
| Traceability Requirement |  | MHHS-BR-LD-010.1 | MHHS-BR-LD-010.2
| Service Producing Trigger |  | LDSO
| Input/Trigger |  | DB01
| Message Input Event Code |  | N/A
| Service Recipient Processor of Input/Trigger |  | REGS
| Test Step |  | LDSO creates 2 MPAN'S for Import/Export linked MPAN and issues DB01 REGS
| Key Validation & Test Evidence |  | Import/Export Mpan creation and linkage required
| Evidence | Required | Y

## Cover Sheet
LDSO QT - Test Scenarios
Version | Description | Author | Status | Date
V 1.0 | BP011 C Test cases final draft for Test scenario TS_BP0011C_02 | Syed Naveedh | Complete | 2024-02-27
V 1.1 | File name changed to reflect 3 test cases in this file | Kamlesh | Complete | 2024-09-06
V 1.2 | Changes made to incorporate both primary/secondary instances And Changes made to incorporate both import/export instances | QT team | Complete | 2024-10-24
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## BP011C Test Scenarios
Test Scenario ID | LDSO Role (s) | Theme | Business Process | Steps | Requirements | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scenarios Size) | Priority | Expleo Comments
TS_BP0011C_01 | Reg Service | Metering Changes | BP011C - Registration Service Monitoring and Notification Processes | START Step 10 Step 20 Step 30 Step 40 Step 90 END | MHHS-BR-RS-128.3 MHHS-BR-RS-128.4 MHHS-BR-RS-128.5 | Linked/Related MPAN alignment - issuing de-appointment for existing Metering service and confirmed appointment to align metering service | The Registration Service will identify the linked MPAN sets to assess if the service providers are aligned, if the MPAN is the primary and/or a linked import MPAN and if the appointed Metering Service for the Secondary/Linked Export and Primary/Linked Import MPAN is not aligned the Registration Service will issue a de-appointment of existing metering service notification via MHHS-IF-037 . It will issue out a confirmed appointment via MHHS-IF-036 to align the Metering Service. | The boundaries for this scenario are as follows: Start Point Registration Service identify the linked MPAN sets End Point Registration service to issue de-appointment of existing metering service via DIP in case the appointed Metering service for the Primary/Linked Import and Secondary/Linked Export MPAN mis-matches. Registrations Service will issue out a confirmed appointment of matching metering service to align the Metering Service | 1. Related MPAN where Metering Service for the secondary and primary MPAN is not aligned. Segment Advanced 2. Linked MPAN where Metering Service for the import and export MPAN is not aligned. Segment Smart |  | 2 | H | H
TS_BP0011C_02 | Reg Service | Metering Changes | BP011C - Registration Service Monitoring and Notification Processes | START Step 10 Step 20 Step 30 Step 130 Step 140 Step 150 Step 190 END | MHHS-BR-RS-128.3 MHHS-BR-RS-128.4 MHHS-BR-RS-128.6 MHHS-BR-RS-128.7 MHHS-BR-RS-128.8 | Linked/Related smart or advanced MPAN alignment - issuing de-appointment for existing Data service and confirmed appointment to align data service | If the Registration Service identifies that the MPAN is a Linked/Related smart/advanced MPAN, the Registration service will validate if the appointed Data Service for the Linked export/secondary MPAN is aligned to the linked import/primary MPAN. If the appointed Data Service for the Linked export/secondary and Linked import/primary MPAN is not aligned the Registration Service will issue a de-appointment of existing Data Service. Registrations Service will issue out a confirmed appointment to the matching Data Service. | The boundaries for this scenario are as follows: Start Point Registration Service identify the linked MPAN sets End Point Registration service to issue de-appointment of existing data service via DIP in case the appointed data service for the Primary/Linked Import and Secondary/Linked Export MPAN mis-matches. Registrations Service will issue out a confirmed appointment of matching data service to align the data Service | 1. Related MPAN where Metering Service for the secondary and primary MPAN is not aligned. Segment Smart (Traditional) 2. Linked MPAN where Metering Service for the import and export MPAN is not aligned. Segment Advanced 3. Non Related smart or UMS MPAN alignment (is quite possible that this scenario cannot be achieved for QT) |  | 3 | VH | H
TS_BP0011C_03 | Reg Service | Metering Changes | BP011C - Registration Service Monitoring and Notification Processes | START Step 500 Step 510 Step 520 Step 530 Step 550 END | MHHS-BR-RS-128.1 | Registration Service issues advisory notification for missing service provider | The Registration Service will identify MPANs where no service provider is appointed and for MPANs with a missing service provider and SSD is today or there has not been a notification sent within 7 days the Registration Service will issue a missing service provider notification via MHHS-IF-045 to Supplier (Test Harness) | The boundaries for this scenario are as follows: Start Point Registration Service identify MPANs with no service provider is appointed End Point The Registration Service will identify MPANs where no service provider is appointed and for MPANs with a missing service provider and SSD is current date or there has not been a notification sent within 7 days the Registration Service will issue a missing service provider notification via MHHS-IF-045 to Supplier (Test Harness) | 1. Linked MPANs with missing service providers. Segment Smart and Advanced 2. Related MPANs with missing service providers. Segment Smart and Advanced |  | 2 | VH | H
TS_BP0011C_04 | Reg Service | Metering Changes | BP011C - Registration Service Monitoring and Notification Processes | START Step 500 Step 510 Step 560 Step 570 Step 575 Step 580 END | MHHS-BR-RS-128 | Registration Service issues advisory notification for Market Segment Invalid | The Registration Service will identify MPANs whether the Market segment flag is invalid and will check to confirm if the Segment change was within the last 2 days. Where the Market Segment flag is invalid and the Segment change was more than 2 days ago and there has not been a notification sent within 7 days the Registration Service will issue an Invalid Market Segment notification via MHHS-IF-045. | The boundaries for this scenario are as follows: Start Point Registration Service identify MPANs where market segment flag is invalid End Point The Registration Service will identify MPANs whether the Market segment flag is invalid and will check to confirm if the Segment change was within the last 3 working days. Where the Market Segment flag is invalid and the Segment change was more than 3 working days ago and there has not been a notification sent within 7 days from the current date the Registration Service will issue an Invalid Market Segment notification via MHHS-IF-045. | 1. 1 single MPANs where service provider is already appointed. Segment is A. Market segment invalid flag 'N' |  | 1 | VH | H
TS_BP0011C_05 | Reg Service | Metering Changes | BP011C - Registration Service Monitoring and Notification Processes | START Step 500 Step 510 Step 560 Step 600 Step 610 Step 620 Step 630 END | MHHS-BR-RS-128.2 | Registration Service issues advisory notification for mis aligned consent granularity | The Registration Service will identify MPANs where the consent granularity is mis-aligned and there has not been a notification sent within 7 days. Registration Service will issue an Inconsistent Consent Advisory notification via MHHS-IF-045. | The boundaries for this scenario are as follows: Start Point Registration Service identify MPANs where consent granularity is misaligned End Point Supplier (Test Harness) receivingMHHS-IF-045 | 1. Linked MPANs where service providers are already appointed and Segment is S. Market segment invalid flag Y |  | 1 | VH | H

## TC_BP0011C_02_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP0011C_02_01 | Related smart or advanced MPAN alignment - issuing de-appointment for existing Data service and confirmed appointment to align data service | TS_BP0011C_02 | • Related MPAN (for primary and secondary) • Smart (Traditional) Segment • Secondary MPAN with different data services | Registration service to issue de-appointment of existing data service via DIP in case the appointed data service for the primary and secondary MPAN mis-matches. Registrations Service will issue out a confirmed appointment of matching data service to align the data Service
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP011C-Step 10 | NA | Registration service | Registration service | NA | Registration Service will identify the linked MPAN set to assess if the service providers are aligned | N | Registration service identifies linked MPAN set
2 | BP011C-Step 20/Step 30 | MHHS-BR-RS-128.3 | Registration service | Registration service | NA | Registration Service with assess if the MPAN is the primary MPAN. Registration service validates if appointed Metering Service for the secondary MPAN is aligned to the primary MPAN | Y | Evidence of Registration service assess MPAN to be secondary MPAN. Evidence of Registration service validating the appointed Metering Service to be mis-matched for the secondary MPAN and primary MPAN.
3 | BP011C-Step 130 | MHHS-BR-RS-128.6 | Registration service | Registration service | NA | The Registration Service will need to separate MPANs that are related and non-related | N | Evidence of Registration service separating MPAN's that are Related smart MPAN or an advanced MPAN
4 | BP011C-Step 140 | MHHS-BR-RS-128.6 | Registration service | Registration service | NA | Registration service will validate if the appointed Data Service for the secondary MPAN is aligned to the primary MPAN | N | Evidence of Registration service validating the appointed Data Service to be mis-matched for the secondary MPAN and primary MPAN.
5 | BP011C-Step 150 | MHHS-BR-RS-128.7 | Registration service | DIP | MHHS-IF-037 (primary) MHHS-IF-037 (secondary) | Registration Service will issue a de-appointment of existing Data service notification via MHHS-IF-037 "Notification of Service De-Appointment". | Y | Evidence of Registration service issuing MHHS-IF-037
6 | BP011C-Step 160/Step 170/ Step 180 | NA | DIP | Test harness (Supplier, Existing Data service) | PUB-037 (primary) Supplier PUB-037 (secondary) Supplier PUB-037 (primary) Existing DS PUB-037 (secondary) Existing DS | DIP publishes PUB-037 to Test harness (Supplier, Existing Data service) | N | NA
7 | BP011C-Step 190 | MHHS-BR-RS-128.8 | Registration service | DIP | MHHS-IF-036 (primary) MHHS-IF-036 (secondary) | Registrations Service will issue out a confirmed appointment to the DIP via MHHS-IF-036 "Service Provider Notification of Appointment" to align the Data Service | Y | Evidence of Registration service issuing MHHS-IF-036
8 | BP011C-Step 200/Step 210/ Step 220 | NA | DIP | Test harness (Supplier, Prospective Data service) | PUB-036 (primary) Supplier PUB-036 (secondary) Supplier PUB-036 (primary) Prospective DS PUB-036 (secondary) Prospective DS | DIP publishes PUB-037 to Test harness (Supplier, Prospective Data service) | N | NA

## TC_BP0011C_02_02
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP0011C_02_02 | Linked Import/Export smart or advanced MPAN alignment - issuing de-appointment for existing Data service and confirmed appointment to align data service | TS_BP0011C_02 | • Linked Import/Export MPAN (for import and export - 2 instances) • Advanced Segment • Import MPAN's with different data services than export MPAN | Registration service to issue de-appointment of existing data service via DIP in case the appointed data service for the primary and secondary MPAN mis-matches. Registrations Service will issue out a confirmed appointment of matching data service to align the data Service
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP011C-Step 10 | NA | Registration service | Registration service | NA | Registration Service will identify the linked MPAN set to assess if the service providers are aligned | N | Registration service identifies linked MPAN set
2 | BP011C-Step 20/Step 30 | MHHS-BR-RS-128.3 | Registration service | Registration service | NA | Registration Service with assess if the MPAN is a linked import MPAN. Registration service validates if appointed Metering Service for the linked export MPAN is aligned to the linked import MPAN | Y | Evidence of Registration service assess MPAN to be a linked export MPAN. Evidence of Registration service validating the appointed Metering Service to be mis-matched for the linked import MPAN and linked export MPAN.
3 | BP011C-Step 130 | MHHS-BR-RS-128.6 | Registration service | Registration service | NA | The Registration Service will need to separate MPANs that are related and non-related | N | Evidence of Registration service separating MPAN's that are Related smart MPAN or an advanced MPAN
4 | BP011C-Step 140 | MHHS-BR-RS-128.6 | Registration service | Registration service | NA | Registration service will validate if the appointed Data Service for the secondary MPAN is aligned to the primary MPAN | N | Evidence of Registration service validating the appointed Data Service to be mis-matched for the secondary MPAN and primary MPAN.
5 | BP011C-Step 150 | MHHS-BR-RS-128.7 | Registration service | DIP | MHHS-IF-037 (import) MHHS-IF-037 (export) | Registration Service will issue a de-appointment of existing Data service notification via MHHS-IF-037 "Notification of Service De-Appointment". | Y | Evidence of Registration service issuing MHHS-IF-037
6 | BP011C-Step 160/Step 170/ Step 180 | NA | DIP | Test harness (Supplier, Existing Data service) | PUB-037 (import) Supplier PUB-037 (export) Supplier PUB-037 (import) Existing DS PUB-037 (export) Existing DS | DIP publishes PUB-037 to Test harness (Supplier, Existing Data service) | N | NA
7 | BP011C-Step 190 | MHHS-BR-RS-128.8 | Registration service | DIP | MHHS-IF-036 (import) MHHS-IF-036 (export) | Registrations Service will issue out a confirmed appointment to the DIP via MHHS-IF-036 "Service Provider Notification of Appointment" to align the Data Service | Y | Evidence of Registration service issuing MHHS-IF-036
8 | BP011C-Step 200/Step 210/ Step 220 | NA | DIP | Test harness (Supplier, Prospective Data service) | PUB-036 (import) Supplier PUB-036 (export) Supplier PUB-036 (import) Prospective DS PUB-036 (export) Prospective DS | DIP publishes PUB-037 to Test harness (Supplier, Prospective Data service) | N | NA

## TC_BP0011C_02_03
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP0011C_02_03 | Non Related smart or UMS MPAN alignment | TS_BP0011C_02 | This test case has been written for coverage. It is quite possible that this scenario cannot be achieved for QT • Linked/Related MPAN - with 1 import MPAN and 2 export MPANs • Smart Segment • Out of the 2 export MPAN - one should be non-related smart MPAN or UMS MPAN | Registration Service identifies that the MPAN is UMS or an unrelated MPAN and will end the process for the Data Service alignment validation
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP011C-Step 10 | NA | Registration service | Registration service | NA | Registration Service will identify the linked MPAN set to assess if the service providers are aligned | Y | Registration service identifies linked MPAN set
2 | BP011C-Step 20/Step 30 | MHHS-BR-RS-128.3 | Registration service | Registration service | NA | Registration Service with assess if the MPAN is the primary and/or a linked import MPAN. Registration service validates if appointed Metering Service for the secondary MPAN is aligned to the primary MPAN | Y | Evidence of Registration service assess MPAN to be secondary and/or a linked import MPAN. Evidence of Registration service validating the appointed Metering Service to be matched for the secondary MPAN and primary MPAN.
3 | BP011C-Step 130 | MHHS-BR-RS-128.6 | Registration service | Registration service | NA | The Registration Service will need to separate MPANs that are related and non-related | Y | Evidence of Registration service separating MPAN's that are Related smart MPAN or an advanced MPAN
4 | BP011C-Step 131 | NA | Registration service | Registration service | NA | Registration Service identifies that the MPAN is UMS or an unrelated MPAN and will end the process for the Data Service alignment validation | Y | Evidence of end or process for data service alignment validation

## Requirement coverage
Req. ID | Role(s) | Requirement description
MHHS-BR-RS-128.3 | Registration service | Registration Service must, after processing the prospective appointment queue each day, in the case where there are Related MPANs or linked Import/Export MPANs, review for any Secondary MPANs/ Export MPANs that do not have the same Metering Service as the Primary MPAN/ linked Import MPAN.
MHHS-BR-RS-128.6 | Registration service | Registration Service must, after processing the prospective appointment queue each day, in the case where there are Related MPANs or linked Import/Export MPANs (Advanced and Unmetered only), review for any Secondary MPANs/ Export MPANs that do not have the same Data Service as the Primary MPAN/ linked Import MPAN.
MHHS-BR-RS-128.7 | Registration service | Registration Service must automatically publish a de-appointment notification via the appropriate interface on the Data Integration Platform, for any Secondary MPAN/ linked Export MPAN which has a mis-aligned Data Service. The Data Service should be de-appointed with an effective date of D.