## Cover Sheet
LDSO QT - Test Cases
Version | Description | Author | Status | Date
1 | Start Test Cases | Non SIT QT Team |  | 2024-03-08
2 | Test Lead Review | Non SIT QT Team |  | 2024-03-11
3 | Review Comments Incorporated | Non SIT QT Team |  | 2024-03-12
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## BP016 Test Scenarios
Test Scenario ID | LDSO Role (s) | Theme | Business Process | Steps | Requirements | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scenarios Size) | Priority | Expleo Comments
TS_BP016_01 | LDSO | Meter to Bank | BP016 - Consumption Amendment | START • Step 500 (Supplier Identifies that ‘Override Reading’ is Required) • Step 505 (Publish ‘Override Reading’) • Step 510 (Manage Receipt of ‘Override Reading’) • Step 520 (Data Service) (Manage Receipt of ‘Override Reading’) END | • MHHS-BR-LD-055 | Metered Supply: Validate that the LDSO will receive PUB-041 from the DIP with the override reading | In this scenario, a Supplier (Test Harness) is issuing an override read to LDSO and Data Service (Test Harness) via DIP in exceptional events eg. missed meter exchange, tampering, theft, stolen meters etc which will effectively set a new reference point with the SDS/ADS for future validation and estimating. | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Supplier (Test Harness) issuing an override read to the LDSO via DIP. (IF-041) End Point The end point will be the LDSO and Data Service (Test Harness) receiving the 'Override Reading' . (PUB-041) | • Where the Supplier is issuing an override read for Segment S (Smart) • Where the Supplier is issuing an override read for Segment S (Traditional) • Where the Supplier is issuing an override read for Segment A (Advanced) |  | 3 | M | VH
TS_BP016_02 | LDSO | Meter to Bank | BP016 - Consumption Amendment | START • Step 120 (Data Service) (Submit Validated Consumption(s) Amendment to Settlements) • Step 130 (DIP) (Publish Revised Consumption for Amendment Period) • Step 320 (LDSO) (Manage Receipt of Revised Consumption Data) END | • MHHS-BR-LD-056 | Metered Supply: Validate that the LDSO will receive PUB-021 from the DIP with the accepted Consumption Amendment Data | In this scenario, Data Service (Test Harness) will submit the validated consumption to Central settlements via the DIP. The DIP will receive the validated consumption from Data Services and issue PUB-021 to Central Settlements, Supplier and LDSO. LDSO will receive PUB-021 from the DIP confirming the submission of the consumption amendment. | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Data Service (Test Harness) issuing the revised consumption. (IF-021) End Point The end point will be the LDSO receiving Consumption Data. (PUB-021) | • Where the Supplier is issuing consumption data for Segment S (Smart) • Where the Supplier is issuing consumption data for Segment S (Traditional) • Where the Supplier is issuing consumption data for Segment A (Advanced) |  | 3 | M | VH
TS_BP016_03 | LDSO | Meter to Bank | BP016 - Consumption Amendment | START • Step 130 (DIP) (Publish Revised Consumption for Amendment Period) • Step 200 (Central Settlements) (Process Validated Consumption Amendment Request) • Step 210 (Central Settlements) (Reject Consumption Amendment) • Step 250 (DIP) (Publish Consumption Rejection) • Step 280 (LDSO) (Manage Receipt of Consumption Rejection) END | • MHHS-BR-LD-008.2 | Metered Supply: Validate that the LDSO will receive PUB-014 with the consumption data rejection from DIP | In this scenario, Central Settlements will receive PUB-021 from the DIP confirming the submission of the consumption amendment and will need to assess whether this can be accepted or not. If central settlements rejects the amendment submission MDS will issue MHHS-IF-014 to the DIP. LDSO will receive PUB-014 with the consumption data rejection from DIP. | The boundaries for this scenario are as follows: Start Point The starting point for this scenario will be the Central Settlements will receive PUB-021 from the DIP confirming the submission of the consumption amendment and will need to assess whether this can be accepted or not (IF-014) End Point The end point will be the LDSO receiving Consumption Data Rejection. (PUB-014) | • Where the Supplier is issuing Consumption Data Rejection for Segment S (Smart) • Where the Supplier is issuing Consumption Data Rejection for Segment S (Traditional) • Where the Supplier is issuing Consumption Data Rejection for Segment A (Advanced) |  | 3 | M | VH

## TC_BP016_02_01
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP016_02_01 | Metered Supply: Validate that the LDSO will receive PUB-021 from the DIP with the accepted Consumption Amendment Data | TS_BP016_02 | • Segment S (Smart) Test Data: IF-021 with the following characteristics: • (DI-076) Estimation Reason Code = 9 (Consumption Amendment) | LDSO receiving Consumption Data. (PUB-021)
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP016 -Step 120 | NA | Data Service (Test Harness) | DIP | IF-021 | Data Service will submit the validated consumption to LDSO via the DIP | N
2 | BP016 -Step 130 & Step 320 | MHHS-BR-LD-056 | DIP | LDSO | PUB-021 | LDSO will receive PUB-021 from the DIP confirming the submission of the consumption amendment. LDSO must obtain accepted Consumption Amendments with Consumption and Reactive data (where appropriate), sent by the Data Service on the Data Integration Platform, via the appropriate interface and maintain records accordingly. | Y | Evidence of LDSO receiving Consumption Data via PUB-021. LDSO system/records have been updated as a result of message being received.

## TC_BP016_02_02
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP016_02_02 | Metered Supply: Validate that the LDSO will receive PUB-021 from the DIP with the accepted Consumption Amendment Data | TS_BP016_02 | • Segment S (Traditional) Test Data: IF-021 with the following characteristics: • (DI-076) Estimation Reason Code = 9 (Consumption Amendment) | LDSO receiving Consumption Data. (PUB-021)
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP016 -Step 120 | NA | Data Service (Test Harness) | DIP | IF-021 | Data Service will submit the validated consumption to LDSO via the DIP | N
2 | BP016 -Step 130 & Step 320 | MHHS-BR-LD-056 | DIP | LDSO | PUB-021 | LDSO will receive PUB-021 from the DIP confirming the submission of the consumption amendment. LDSO must obtain accepted Consumption Amendments with Consumption and Reactive data (where appropriate), sent by the Data Service on the Data Integration Platform, via the appropriate interface and maintain records accordingly. | Y | Evidence of LDSO receiving Consumption Data via PUB-021. LDSO system/records have been updated as a result of message being received.

## TC_BP016_02_03
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BP016_02_03 | Metered Supply: Validate that the LDSO will receive PUB-021 from the DIP with the accepted Consumption Amendment Data | TS_BP016_02 | • Segment A Test Data: IF-021 with the following characteristics: • (DI-076) Estimation Reason Code = 9 (Consumption Amendment) | LDSO receiving Consumption Data. (PUB-021)
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP016 -Step 120 | NA | Data Service (Test Harness) | DIP | IF-021 | Data Service will submit the validated consumption to LDSO via the DIP | N
2 | BP016 -Step 130 & Step 320 | MHHS-BR-LD-056 | DIP | LDSO | PUB-021 | LDSO will receive PUB-021 from the DIP confirming the submission of the consumption amendment. LDSO must obtain accepted Consumption Amendments with Consumption and Reactive data (where appropriate), sent by the Data Service on the Data Integration Platform, via the appropriate interface and maintain records accordingly. | Y | Evidence of LDSO receiving Consumption Data via PUB-021. LDSO system/records have been updated as a result of message being received.

## Test Scenario Requirements
| denotes - req part of BSC Assessment Criteria | denotes - req OOS of BSC Assessment Criteria | denotes - req still in question
Test Scenario ID | Test Scenario Title | Link to Requirement ID | Role | Business Process Steps | Requirements Detail | Interface ID | Supporting Information | Optionality
TS_BP016_01 | Metered Supply: Validate that the LDSO will receive PUB-041 from the DIP with the override reading |  | Supplier | 500 | In exceptional events eg. missed meter exchange, tampering, theft, stolen meters etc it is possible for Supplier to issue an override read which will effectively set a new reference point with the SDS/ADS for future validation and estimating. Supplier should consider the impact of setting this read
|  |  | DIP | 505 | Supplier will issue the override reading to the LDSO and Data Services via the DIP | MHHS-IF-041
|  | MHHS-BR-LD-055 | LDSO | 510 | LDSO will receive PUB-041 from the DIP with the override reading. LDSO must obtain Override Reads, sent by the Supplier on the Data Integration Platform, via the appropriate interface and maintain records accordingly. | PUB-041
|  |  | Data Service (Appointed Period) | 520 | Data Service will receive PUB-041 from the DIP with the override reading | PUB-041
TS_BP016_02 | Metered Supply: Validate that the LDSO will receive PUB-021 from the DIP with the accepted Consumption Amendment Data |  | Data Service (Appointed Period) | 120 | Once Data Service have confirmed all criteria is valid for the consumption amendment and period they will submit the validated consumption to Central settlements via the DIP | MHHS-IF-021
|  |  | DIP | 130 | The DIP will receive the validated consumption from Data Services and issue PUB-021 to Central Settlements, Supplier and LDSO | PUB-021 (From DIP to Central Settlements, Supplier & LDSO)
|  | MHHS-BR-LD-056 | LDSO | 320 | LDSO will receive PUB-021 from the DIP confirming the submission of the consumption amendment. LDSO must obtain accepted Consumption Amendments with Consumption and Reactive data (where appropriate), sent by the Data Service on the Data Integration Platform, via the appropriate interface and maintain records accordingly. | PUB-021
TS_BP016_03 | Metered Supply: Validate that the LDSO will receive PUB-014 with the consumption data rejection from DIP |  | DIP | 130 | The DIP will receive the validated consumption from Data Services and issue PUB-021 to Central Settlements, Supplier and LDSO | PUB-021 (From DIP to Central Settlements, Supplier & LDSO)
|  |  | Central Settlements | 200 | Central Settlements will receive PUB-021 from the DIP confirming the submission of the consumption amendment and will need to assess whether this can be accepted or not | PUB-021
|  |  | Central Settlements | 210 | If central settlements rejects the amendment submission MDS will issue MHHS-IF-014 to the DIP | MHHS-IF-014
|  |  | DIP | 250 | The DIP will issue PUB-014 for the consumption rejection | PUB-014
|  | MHHS-BR-LD-008.2 | LDSO | 280 | LDSO will receive PUB-014 with the consumption rejection. LDSO must obtain UTC Settlement Period Consumption Data Rejections, sent by Central Settlements on the Data Integration Platform, via the appropriate interface and maintain records accordingly. | PUB-014