## CoverSheet
LDSO QT - Test Scenarios
S.No. | Description | Author | Status | Date
1 | Initial Draft of BPM002 Test Scenarios | Non SIT LDSO QT Test Team |  | 2024-03-22
2 | Review by Test Lead | Non SIT LDSO QT Test Team |  | 2024-04-11
3 | Amendments - incorporating review comments | Non SIT LDSO QT Test Team |  | 2024-04-11
4 | Added more detail to the steps, to make it more clear what this test is trying to achieve | Non SIT LDSO QT Test Team | completed | 2024-10-15
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## TC_BPM002_FM_04_01
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BPM002_FM_04_01 | For Segment S (Smart) Related Secondary MPAN - IF-031 triggered for Secondary MPAN where the Primary MPAN of the same Related group is not yet migrated using migration appointment codes | TS_BPM002_FM_04 | Pre requisites: The tester must make sure that the Primary MPAN of the same Related group is not yet migrated. Actual testing: The Tester will pick a Related Secondary MPAN and trigger an if-031 from the Supplier (Test Harness) to the Registration Services. The Registration Service will reject the request and respond to the Supplier (Test Harness) using an IF-032 with rejection code and reason. The data for this test should be as follows: - Where IF-031 is sent with (DI-999) Event Code = [MSApp] - Where IF-031 is sent with (DI-800) Service Provider Appointment Scenario = MCA (Migration Change of Agent) - Where IF-031 contains Related Secondary MPAN (not using the unmigrated Related Primary MPAN associated with that secondary MPAN) - Where IF-031 is being sent to appoint a Segment S (Smart) - (outcome) Where IF-031 is rejected with (DI-979) Response Code = R (Reject) and IF-032 is sent back using (DI-980) Response Message = REG1039 - Appointments barred on Related Secondary MPAN | In this scenario, a Supplier (Test Harness) is generating an IF-031 for a secondary MPAN using a "migration" appointment scenario code, then the Registration Service will reject it and send the IF-032 back to the Supplier (Test Harness) to inform them of the rejection.
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BPM002_FM - Step 20 to Step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 9 (for the secondary mpan) | Supplier (Test Harness) issues IF-031 "Supplier Service Provider Appointment Request" to DIP For the secondary mpan | N | Evidence of the message that is created by the Test Harness (if possible) and being triggered to DIP.
2 | BPM002_FM - Step 30 to Step 40 | NA | DIP | Registration Service | PUB-031 (for the secondary mpan) | DIP publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services For the secondary mpan | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems.
3 | BPM002_FM - Step 40 to Step 45 to Step 50 | MHHS-Migration-CoA(MS)-RS-011 MHHS-Migration-CoA(MS)-RS-012 | Registration Service | DIP | MHHS-IF-032 (for the secondary mpan) | Registration Service send IF-032 to the DIP with rejection code and reason. For the secondary mpan Response Code = R (Reject) Response Message = REG1039 - Appointments barred on Related Secondary MPAN | Y | Registration Services sending the message to the DIP.
4 | BPM002_FM - Step 50 to Step 55 | NA | DIP | Supplier (Test Harness) | PUB-032 (for the secondary mpan) | DIP publishes PUB-032 to Supplier (Test Harness) with rejection code and reason. For the secondary mpan Response Code = R (Reject) Response Message = REG1039 - Appointments barred on Related Secondary MPAN | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.