## CoverSheet
LDSO QT - Test Scenarios
S.No. | Description | Author | Status | Date
1 | Initial Draft of BPM002 Test Scenarios | Non SIT LDSO QT Test Team |  | 2024-03-22
2 | Review by Test Lead | Non SIT LDSO QT Test Team |  | 2024-04-11
3 | Amendments - incorporating review comments | Non SIT LDSO QT Test Team |  | 2024-04-11
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## TC_BPM002_FM_07_01
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BPM002_FM_07_01 | Metering Service: IF-031 sent for the terminated MPAN will be rejected and the response is sent back to the Supplier (Test Harness) | TS_BPM002_FM_07 | Pre requisites: The tester will pick MPAN that is terminated. This means that the MPAN RMP (Registered Meter Point) Status that is held in the Registration Service = "Terminated" Manual actions required by tester: - creation of the IF-031 in the Supplier (Test Harness) for the terminated MPAN The data for this test should be as follows: - Where IF-031 is sent with (DI-999) Event Code = [MSApp] - Where IF-031 is sent with (DI-800) Service Provider Appointment Scenario = MCA (Migration Change of Agent) - Appointment is for Single MPAN - Appointment is for a Segment S (Smart Meter) - (outcome) Where IF-032 sends rejection using REG1001 - MPAN not status Created/Operational | In this scenario, a Supplier (Test Harness) will initiate the migration of a Metering Service (by triggering the IF-031) for MPAN that is terminated. This will be rejected by Registration Service who will respond sent back to the Supplier (Test Harness) with a rejection code and reason
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BPM002_FM - Step 20 to Step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created by the Test Harness (if possible) and being triggered to DIP.
2 | BPM002_FM - Step 30 to Step 40 | MHHS-Migration-Can-RS-006 | DIP | Registration Service | PUB-031 | DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will reject the request because the MPAN is terminated. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will reject the request because the mpan is terminated.
3 | BPM002_FM - Step 40 to Step 45 to Step 50 | NA | Registration Service | DIP | MHHS-IF-032 | Registration Service automatically sends IF-032 to the DIP with a rejected response code | Y | Registration Service automatically sends IF-032 to the DIP with an rejected response code
4 | BPM002_FM - Step 50 to Step 55 | NA | DIP | Supplier (Test Harness) | PUB-032 | DIP automatically publishes PUB-032 to Suppler (Test Harness) with a rejected response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.