## CoverSheet
LDSO QT - Test Scenarios
S.No. | Description | Author | Status | Date
1 | Initial Draft of BPM002 Test Scenarios | Non SIT LDSO QT Test Team |  | 2024-03-22
2 | Review by Test Lead | Non SIT LDSO QT Test Team |  | 2024-04-11
3 | Amendments - incorporating review comments | Non SIT LDSO QT Test Team |  | 2024-04-11
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## TC_BPM002_FM_09_01
Test Case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BPM002_FM_09_01 | Legacy EES extract testing for Metering Service : Validate that MPANs do not appear on the Legacy EES Extract upon successful completion of Forward Migration of MS | TS_BPM002_FM_09 | Pre requisites: Tester will run the Legacy EES extract manually (or wait for the extract to naturally run) and validate that legacy MPANs do exist on the extract. Actual testing: The Tester will then wait for the legacy EES extract to be ran again (or manually run the extract) after the MPAN have been successfully migrated (definition of successful migration is the sending of the IF-036). Once the MPANs have been successfully migrated, they will no longer show on the legacy EES extract. The tester will validate that MPANs do not appear on the Legacy EES Extract upon successful completion of Forward Migration The data to validate will be of the following types: - Segment U MPAN - Segment S MPAN (Traditional Meter) - Segment S MPAN (Smart Meter) - Segment A MPAN (HH Advanced Meter) - Segment A MPAN (NHH Advanced Meter) | In this scenario, the tester will wait for the EES extract to be run (or run the extract manually) and validate that MPANs do not appear on the Legacy EES Extract upon successful completion of Forward Migration
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BPM002_FM - NA | MHHS-Migration-CoA(MS)-RS-008 | EES | NA | NA | Run the Legacy EES extract (or wait for the Extract to be ran naturally) Validate that the MPANs that are now successfully migrated are not showing on the extract. This test is passed when the tester can prove that MPANs of the following types have dropped off the extract: - Segment U MPAN - Segment S MPAN (Traditional Meter) - Segment S MPAN (Smart Meter) - Segment A MPAN (HH Advanced Meter) - Segment A MPAN (NHH Advanced Meter) | Y | Run the Legacy EES extract (or wait for the Extract to be ran naturally). This test is passed when the tester can prove that MPANs have dropped off the extract.