## Cover Sheet
LDSO QT - Test Scenarios
S.No. | Description | Author | Status | Date
1 | Initial Draft of BP002 Test case | Non SIT LDSO QT Test Team |  | 2024-04-26
2 | Removed step going to Helix | Non SIT LDSO QT Test Team |  | 2024-12-06
3 | Added 2 steps for IF-035 (Accepted) | Non SIT LDSO QT Test Team |  | 2024-12-13
4 | Added 3 steps at the start of the test to show that CSS pending notification and IF/PUB-002 are needed for this test. Also added some more detail in the data requirement section. | Non SIT LDSO QT Test Team |  | 2025-01-02
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## TC_BPM002_FM_10_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BPM002_FM_10_01 | Successful migration of MS and failed migration of DS, for Segment A (Advanced) with Single MPAN | TS_BPM002_FM_10 | Pre requisites The Tester will pick a legacy Mpan for which they want to initiate the COS process and forward migration for. Whereby the initiating Suppler of the COS process (The supplier making the COS request) is not the supplier held in the Registration Services that is supplying the meter point currently This test The Tester will start at step 1 of this script where the Registration Service has received a Change of Supplier (COS) pending notification from the Central Switching Service (CSS) via the CSS flow (CSS2800), after the incoming supplier (initiating suppler of the COS) has submitted the COS request to CSS (this will be achieved either by a CSS simulator or tester manual action in RS). The Registration Service, on the receipt of the COS pending notification will publish initial Registration details of the MPAN to the incoming supplier using an IF-002. The Supplier will then trigger the IF-031 for both DS and MS appointments using scenario code MCS. Note Use the same MPAN and same appointment effective dates on both DS and MS appointments (IF-031's), choose an appointment effective dates in the future (2-3 days). We want the MS appointment to go through the prospective processing route in RS. The MS appointment will enter the prospective processing route in RS after receiving the IF-034 (Accepted) from the Service providers and will await a CSS secured notification (achieved either by CSS simulator or tester manual action in RS) for the appointment to be processed out of the Queue. When the appointment is processed out of the Queue an IF-036 will be sent to the expected participants (The sending of the IF-036 will denote that migration of the MS has been successful). For the DS, the appointment will be rejected by the Data Service (the tester will manually create the IF-034 with response code "Rejected"), and an IF-035 will be sent to the Metering Service (Test Harness) and Supplier (Test Harness) notifying them of the rejection of the DS appointment. When the SSD (Supply Start Date) is reached and only the MS is appointed and no DS is appointed then the Registration Services will trigger the IF-045 to the Supplier (Test Harness) with event code [NoDSAppointed]. Manual actions required by tester - Creation of the IF-031 in the Supplier (Test Harness) for the Data Service appointment - Creation of the IF-031 in the Supplier (Test Harness) for the Metering Service appointment - Creation of the IF-034 in the New Metering Service (Test Harness) Accepted - Creation of the IF-034 in the New Data Service (Test Harness) Rejected The data for this test should be as follows: for the Metering Service appointment - IF-031 Event Code = [MSApp] - IF-031 Appointment Scenario = MCS (Migration Change of Supply) - IF-034 Response Code = A (Accept) - Appointment is for a Single MPAN - Appointment is for a Segment A (Advanced) Metering Service - Effective date of the appointment is such that prospective processing route is taken in RS The data for this test should be as follows: for the Data Service appointment - IF-031 Event Code = [DSApp] - IF-031 Appointment Scenario = MCS (Migration Change of Supply) - IF-034 Response Code = R (Reject) - Appointment is for a Single MPAN - Appointment is for a Segment A (Advanced) Data Service - Effective date of the appointment is such that prospective processing route is taken in RS | In this scenario a Supplier (Test Harness) will initiate the migration of a Data Service and Metering Service (by triggering the IF-031 for each). The migration will be successful for the MS (defined by the sending of the IF-036 notification). And the Migration of the DS will be unsuccessful (IF-034 will have the response code "rejected"). For the MS migration (successful migration), the LDSO, Supplier, Data Service, Metering Service and EES will receive the notification of the successful migration in either a real system or a test harness as follows. The LDSO will receive the notification, validate and update their records accordingly. For the Supplier, ECS (Helix), Data Service, Metering Service and EES a test harness will be in place to receive the notification. For the DS (failed migration) an IF-035 will be sent to the Data Service (Test Harness) and Supplier (Test Harness) When the SSD (Supply start date) is reached and only the MS is appointed and no DS is appointed then the Registration Services will trigger the IF-045 to the Supplier (test harness) with event code [NoDSAppointed].
Test Step Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BP001 70 | MHHS-BR-RS-005 | CSS | Registration Services | CSS flow (CSS2800) | Registration Service has received notification from CSS (Simulator) via the CSS flow (CSS2800) after the new supplier submitting the request to CSS (Simulator). The notification will be a pending request. | N | To ensure that the Registration Services has received the pending supplier request.
2 | BP001 70 to 75 75 to 80 | MHHS-BR-RS-005 MHHS-BR-RS-006 MHHS-Migration-CoS-RS-001 MHHS-Migration-CoS-RS-002 MHHS-Migration-CoS-RS-003 | Registration Services | DIP | IF-002 | Once it has been confirmed that the switch from the Legacy MPAN to a MHSS Qualified Supplier has been achieved, Registration Services will send the IF-002 to the incoming Supplier via DIP | Y | To ensure that the information required has been sent to DIP and also the acceptance criteria/requirement has been met
3 | BP001 80 to 85 85 to 190 | N/A | DIP | Incoming Supplier (Test Harness) | PUB-002 | DIP has received IF-002 from Registration Services and will send PUB-002 to the incoming Supplier. | N | Not required
4 | BPM003FM -Step 20 to step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | DS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
5 | BPM003FM -Step 30 to step 40 | NA | DIP | Registration Service | PUB-031 | DS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
6 | BPM002_FM - Step 20 to Step 30 | NA | Supplier (Test Harness) | DIP | MHHS-IF-031 | MS: Tester will manually create the IF-031 in the Supplier (Test Harness) and trigger it to the DIP | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
7 | BPM002_FM -Step 30 to Step 40 | NA | DIP | Registration Service | PUB-031 | MS: DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will accept the request. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will accept the request.
8 | BPM003FM - Step 40 to 45 to 50 | NA | Registration Service | DIP | MHHS-IF-032 | DS: Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
9 | BPM003FM -Step 50 to 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | DS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
10 | BPM002_FM - Step 40 to Step 45 to Step 50 | NA | Registration Service | DIP | MHHS-IF-032 | MS: Registration Service automatically sends IF-032 to the DIP with an accepted response code | Y | Registration Service send IF-032 to the DIP with an accepted response code
11 | BPM002_FM -Step 50 to Step 55 | NA | DIP | Supplier (Test Harness) End | PUB-032 | MS: DIP automatically publishes PUB-032 to Supplier (Test Harness) with an accepted response code | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
12 | BPM003FM - Step 60 to 65 | NA | Registration Service | DIP | MHHS-IF-033 | DS: Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
13 | BPM003FM - Step 65 to 220 and 221 | NA | DIP | New Data Service (Test Harness) End | PUB-033 | DS: DIP automatically publishes PUB-033 to the New Data Service (Test Harness) | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
14 | BPM002_FM - Step 40 to Step 60 to Step 65 | NA | Registration Service | DIP | MHHS-IF-033 | MS: Registration Service automatically sends IF-033 to the DIP | Y | Registration Service send IF-033 to the DIP
15 | BPM002_FM - Step 65 to Step 70 and Step 75 | NA | DIP | New Metering Service (Test Harness) End | PUB-033 | MS: DIP automatically publishes PUB-033 to the New Metering Service (Test Harness) | N | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
16 | BPM003FM - Step 221 to 80 | NA | New Data Service (Test Harness) End | DIP | MHHS-IF-034 (Rejected) | DS: Tester will manually create the IF-034 in the New Data Service (Test Harness) and trigger it to the DIP with a Rejected response code | N | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP with an accepted response code
17 | BPM003FM - Step 80 to 85 | NA | DIP | Registration Service | PUB-034 | DS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the CSS simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
18 | BPM003FM - Step 85 to 90 | NA | Registration Service | DIP | MHHS-IF-035 (Rejected) | DS: Registration Service automatically sends IF-035 to the DIP | Y | Registration Service automatically sends IF-035 to the DIP
19 | BPM003FM - Step 85 to 90 to 91 (DS) BPM003FM - Step 85 to 90 to 95 (Supplier) | NA | DIP | New Data Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | DS: DIP automatically sends an PUB-035 to the New Data Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) | N | DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
20 | BPM002_FM - Step 75 to Step 80 | NA | New Metering Service (Test Harness) | DIP | MHHS-IF-034 (Accepted) | MS: Tester will manually create the IF-034 in the New Metering Service (Test Harness) and trigger it to the DIP with an Accepted response code | N | Tester will manually create the IF-034 in the New Metering Service (Test Harness) and trigger it to the DIP with an rejected response code
21 | BPM002_FM - Step 80 to 85 to Step 100 to Step 101 to Step 120 to Step 125 | NA | DIP | Registration Service | PUB-034 | MS: DIP automatically publishes PUB-034 to the Registration Services with accepted response code When the IF-034 is received by the Registration Service it will do the following : - •"Registration Service must, in cases where the proposed appointment is accepted, determine the processing path to be followed: •"Prospective" Processing •"Registration Service must be able to hold Prospective appointments in a Prospective Appointments Queue for future validation and re-processing as the daily CSS COS secured notifications are received (this will be achieved by the CSS simulator). •"Registration Service must, following receipt of the CSS COS secured notifications, select Prospective Appointments from the Prospective Appointment Queue to process. | Y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.
22 | BPM002_FM - Step 80 to 87 to 91 | NA | Registration Service | DIP | MHHS-IF-035 (Accepted) | This Step relates to the Meter Service appointment process: Registration Service automatically sends IF-035 to the DIP [MSAppAccepted] | Y | Registration Service automatically sends IF-035 to the DIP
23 | BPM002_FM - Step 91 to 92 (MS) BPM002_FM - Step 91 to 95 (SUP) | NA | DIP | Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-035 | This Step relates to the Meter Service appointment process: DIP automatically sends an PUB-035 to the Metering Service (Test Harness) [MSAppAccepted] DIP automatically sends an PUB-035 to the Supplier (Test Harness) End [MSAppAccepted] | N | DIP automatically sends an PUB-035 to the Metering Service (Test Harness) DIP automatically sends an PUB-035 to the Supplier (Test Harness) End
24 | BPM002_FM - Step 240 to Step 245 | MHHS-Migration-CoA(MS)-RS-018 | Registration Service | DIP | MHHS-IF-036 | MS: Registration Service automatically sends IF-036 to the DIP. This will act as the definitive indicator that a Forward Migration has completed. | Y | Registration Service automatically send IF-036 to the DIP
25 | BPM002_FM - Step 245 to Step 280 | MHHS-Migration-CoA(MS)-LDSO-001 | DIP | LDSO | PUB-036 | MS: Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing MS appointment notification. And update their record accordingly | Y | Registration Service automatically sends an PUB-036 to the LDSO. LDSO to receive PUB-036 from the DIP, containing DS appointment notification. And update their record accordingly
26 | BPM002_FM - Step 245 to Step 283 (EES) BPM002_FM - Step 245 to Step 270 (DS) BPM002_FM - Step 245 to Step 195 (MS) BPM002_FM - Step 245 to Step 260 (SUP) | NA | DIP | EES (Test Harness) End New Data Service (Test Harness) End Metering Service (Test Harness) End Supplier (Test Harness) End | PUB-036 | MS: DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to New Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness) | N | DIP sends PUB-036 to EES (Test Harness) DIP sends PUB-036 to new Data Service (Test Harness) DIP sends PUB-036 to Metering Service (Test Harness) DIP sends PUB-036 to Supplier (Test Harness)
27 | NA no step mentioned | MHHS-Migration-Mis-RS-002 | Registration Service | DIP | MHHS-IF-045 | Registrations will perform a daily scan for sites where the SSD (Supply start date ) is reached and where only 1 of the Service providers is appointed . IF the DS appointed, and MS is not then the registration Service will trigger an IF-045 to the Supplier (Test Harness) with event code [NoMSAppointed] IF the MS appointed, and DS is not then the registration Service will trigger an IF-045 to the Supplier (Test Harness) with event code [NoDSAppointed] | Y | Registrations will perform a daily scan for sites where the SSD (Supply start date ) is reached and where only 1 of the Service providers is appointed . IF the DS appointed, and MS is not then the registration Service will trigger a IF-045 to the Supplier (Test Harness) with event code [NoMSAppointed] IF the MS appointed, and DS is not then the registration Service will trigger a IF-045 to the Supplier (Test Harness) with event code [NoDSAppointed]
28 | NA no step mentioned | NA | DIP | Supplier (Test Harness) End | PUB-045 | DIP will automatically will trigger a IF-045 to the Suppler (test harness) | N | DIP will automatically will trigger a IF-045 to the Suppler (test harness)
Steps related to DS
Steps related to MS