## Sheet3 (hidden)
Proposed LDSO QT Scenario | SIT Scenario
Scenario ID | Scenario ID | SITFTS-0050
Role | Scenario Title | Create MPAN
Theme | Theme | New Connection
Business Process | Description | Create an MPAN through new connection process, appoint services and install meter. & Energise the MPAN
Functional Category | Functional Category | Create MPAN
Scenario Title | Functional Area 1 | New Connection |  |  | Business Process Steps
Description | Functional Area 2 | New MPAN, New Connection successful
Boundaries | Creator | Shaun Magee, Dan Gee |  |  | Interface Description
Test Case Variables | Priority | High |  |  | Regression flag
Optionality | Scenario size | Large
Number of test cases | Business Process | BP001, BP002, BP003, BP010B(Related), BP010C (Linked), BP009, BP008, (+BP003A for Smart meters) |  |  | Precondition Test Harness
Scenario size | Boundaries | Processing ends once the Meter is Installed (if not Unmetered) and Energisation has occurred |  |  | Precondition Other
Priority | Test Case Variables | (1) Smart, import+export, forward-dated (MPAN Creation current date)
Systems under test |  | (2) Traditional, single MPAN, forward-dated (MPAN Creation current date)
|  | (3) Advanced Single MPAN, forward-dated (MPAN Creation current date) |  |  | Test evidence
(4) Unmetered, single MPAN, forward-dated (MPAN Creation current date)
| Exception Codes | NA |  |  | Role (simulated)
LDSO Test Case | SIT Test Case
No.
Test Case Id | Test Case Id
Test Case Title | Test Case Title
Test Case Link | Test Case Link
Test Data Requirements | Test Data Requirements
Traceability Requirement |  |  | Test outcome
Test Harness |  |  | Test Harness
Key Validation & Test Evidence |  |  | Interface
BP Step |  |  | requirement
Service initiating process | SIT Test Steps |  | test evidence
Service Recepint Processor
Interface | Test Case Title |  | SITFTS-0050 - Smart Metered
Evidecne Reuiqred | Key Journey | Events | New MPAN Initial Registration - Start
| Step No. |  | 10
| Business Process |  | BP001
| BP Step |  | 5
| Traceability Requirement |  | MHHS-BR-LD-010.1 | MHHS-BR-LD-010.2
| Service Producing Trigger |  | LDSO
| Input/Trigger |  | DB01
| Message Input Event Code |  | N/A
| Service Recipient Processor of Input/Trigger |  | REGS
| Test Step |  | LDSO creates 2 MPAN'S for Import/Export linked MPAN and issues DB01 REGS
| Key Validation & Test Evidence |  | Import/Export Mpan creation and linkage required
| Evidence | Required | Y

## Cover Sheet
LDSO QT - Test Scenarios
Version | Description | Author | Status | Date
V 0.1 | Initial Draft of BP003 Test Scenarios | Non SIT LDSO QT Test Team |  | 2024-01-19
| Review by SIT |  |  | 2024-01-23
V0.2 | Amendments - incorporating SIT comments | Non SIT LDSO QT Test Team |  | 2024-01-24
V0.3 | Amendments - incorporating changes after clarifications from Design Team | Non SIT LDSO QT Test Team | completed | 2024-01-29
v0.4 | Amendments after Code Bodies Review & Final check |  |  | 2024-01-31
| Amendments made after data team input |  |  | 2024-02-07
| Start Test Cases |  |  | 12/02.2024
v0.5 | Added more details to the data reqs and the test steps to clarify what we are testing | Non SIT LDSO QT Test Team | ready for review | 2024-10-15
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## TC_BPM003FM_02_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BPM003FM_02_01 | IF-019 to remove a related mpan is rejected whist migration for DS of the primary mpan is in progress. For segment A mpan | TS_BPM003FM_02 | Pre requisites. The tester will pick a legacy mpan that they are currently supplyig that they wish to carry out forward migration for. The tester will start @ step 1 of this test and trigger the IF-031 from the Supplier test harness with scneario code MCA and the Event Code is [DSApp] for the primary mpan. Actual testing Whilst migration is "in progress" for the primary mpan (the definition of migration in progress is anywhere in-between the point when the IF-031 is triggered and the PUB-036 is published). When the data is within this window, the tester will submit a IF-019 (to remove the Subsidiary MPAN from the principal MPAN) from the suppler (Test Harness) to the Registration Service. The Registration Service will reject the IF-019 and respond back to the Suppler with the rejection code and reason using a IF-020. The data for this test should be as follows: - Where IF-031 is sent with (DI-999) Event Code = [DSApp] - Where IF-031 is sent with (DI-800) Service Provider Appointment Scenario = MCA (Migration Change of Agent) - Where IF-031 primary MPan is in a relationship group (the primary MPan has a relationship with a secondary mpan). - Where IF-031 is being sent to appoint a Segment A (NHH meter) Data Service - Where IF-019 event code is [RelatedRemove] - (outcome) Where IF-019 is rejected and IF-020 is sent back using REG9010 - Cannot Manage MPAN Relationships while Migration is in Progress | In this scenario a Supplier (a test harness) is generating an IF-031 to the Registration Service to initiate a migration. whilst the migration is in progress an IF-019 is received by the Registration Service who will reject it and respond back to the Supplier (Test Harness) with an IF-020 to inform them of the rejection.
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BPM003FM -Step 20 to step 30 | NA | Suppler (Test Harness) | DIP | MHHS-IF-031 (for the primary) | Suppler (Test Harness) issues IF-031 "Supplier Service Provider Appointment Request" to DIP For the primary mpan | n | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
2 | BPM003FM -Step 30 to step 40 | NA | DIP | Registration Service | PUB-031 (for the primary) | DIP publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services For the primary mpan | y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems.
3 | No Step mentioned | NA | Suppler (Test Harness) | DIP | MHHS-IF-019 | Suppler (Test Harness) sends IF-019 to the DIP This will contain the principal mpan in the relationship (DI-073) and also the mpan in the relationship you want to un-marry from the principal mpan (DI-074) | n | Evidence of the message that is created the Test Harness (if possible) and being triggered to the DIP.
4 | No Step mentioned | MHHS-Migration-Mis-RS-017 | DIP | Registration Service | PUB-019 | DIP publishes PUB-019 to RS This will contain the principal mpan in the relationship (DI-073) and also the mpan in the relationship you want to un-marry from the principal mpan (DI-074) | y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems.
5 | BPM003FM - Step 40 to 45 to 50 | MHHS-Migration-CoA(DS)-RS-004 | Registration Service | DIP | MHHS-IF-020 | Registration Service send IF-020 to the DIP with rejection code and reason. This will contain the principal mpan in the relationship (DI-073) and also the mpan in the relationship you want to un-marry from the principal mpan (DI-074) Response code (DI-979) = R Response message (DI-980) = REG9010 - Cannot Manage MPAN Relationships while Migration is in Progress | y | Registration Services sending the IF-020 to the DIP.
6 | BPM003FM -Step 50 to 55 | MHHS-Migration-Mis-RS-018 | DIP | Suppler (Test Harness) | PUB-020 | DIP publishes PUB-020 to Suppler(Test Harness) with rejection code and reason. This will contain the principal mpan in the relationship (DI-073) and also the mpan in the relationship you want to un-marry from the principal mpan (DI-074) Response code (DI-979) = R Response message (DI-980) = REG9010 - Cannot Manage MPAN Relationships while Migration is in Progress | n | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.

## TC_BPM003FM_02_02
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BPM003FM_02_02 | IF-019 to add a related mpan is rejected whist migration of DS the mpan is in progress. For segment A mpan | TS_BPM003FM_02 | Pre requisites. The tester will pick a legacy mpan that they are currently supplying that they wish to carry out forward migration for. The tester will start @ step 1 of this test and trigger the IF-031 from the Supplier test harness with scenario code MCA and the Event Code is [DSApp] for the primary mpan. Actual testing Whilst migration is "in progress" for the primary mpan (the definition of migration in progress is anywhere in-between the point when the IF-031 is triggered and the PUB-036 is published). When the data is within this window, the tester will submit an IF-019 (to add a Subsidiary MPAN to the existing group) from the suppler (Test Harness) to the Registration Service. The Registration Service will reject the IF-019 and respond back to the Suppler with the rejection code and reason using an IF-020. The data for this test should be as follows: - Where IF-031 is sent with (DI-999) Event Code = [DSApp] - Where IF-031 is sent with (DI-800) Service Provider Appointment Scenario = MCA (Migration Change of Agent) - Where IF-031 contains single Mpan - Where IF-031 is being sent to appoint a Segment A (HH advanced meter) Data Service - Where IF-019 event code is [RelatedAdd] - (outcome) Where IF-019 is rejected and IF-020 is sent back using REG9010 - Cannot Manage MPAN Relationships while Migration is in Progress | In this scenario a Supplier (a test harness) is generating an IF-031 to the Registration Service to initiate a migration. whilst the migration is in progress an IF-019 is received by the Registration Service who will reject it and respond back to the Supplier (Test Harness) with an IF-020 to inform them of the rejection.
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BPM003FM -Step 20 to step 30 | NA | Suppler (Test Harness) | DIP | MHHS-IF-031 (for the primary) | Suppler (Test Harness) issues IF-031 "Supplier Service Provider Appointment Request" to DIP For the primary mpan | n | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
2 | BPM003FM -Step 30 to step 40 | NA | DIP | Registration Service | PUB-031 (for the primary) | DIP publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services For the primary mpan | y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems.
3 | No Step mentioned |  | Suppler (Test Harness) | DIP | MHHS-IF-019 | Suppler (Test Harness) sends IF-019 to the DIP This will contain the principal mpan in the relationship (DI-073) and also the mpan in the relationship you want to marry to the existing group | n | Evidence of the message that is created the Test Harness (if possible) and being triggered to the DIP.
4 | No Step mentioned | MHHS-Migration-Mis-RS-017 | DIP | Registration Service | PUB-019 | DIP publishes PUB-019 to RS This will contain the principal mpan in the relationship (DI-073) and also the mpan in the relationship you want to marry to the existing group | y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems.
5 | BPM003FM - Step 40 to 45 to 50 | MHHS-Migration-CoA(DS)-RS-004 | Registration Service | DIP | MHHS-IF-020 | Registration Service send IF-020 to the DIP with rejection code and reason. This will contain the principal mpan in the relationship (DI-073) and also the mpan in the relationship you want to marry to the existing group Response code (DI-979) = R Response message (DI-980) = REG9010 - Cannot Manage MPAN Relationships while Migration is in Progress | y | Registration Services sending the IF-020 to the DIP.
6 | BPM003FM -Step 50 to 55 | MHHS-Migration-Mis-RS-018 | DIP | Suppler (Test Harness) | PUB-020 | DIP publishes PUB-020 to Suppler(Test Harness) with rejection code and reason. This will contain the principal mpan in the relationship (DI-073) and also the mpan in the relationship you want to marry to the existing group Response code (DI-979) = R Response message (DI-980) = REG9010 - Cannot Manage MPAN Relationships while Migration is in Progress | n | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.