## Sheet3 (hidden)
Proposed LDSO QT Scenario | SIT Scenario
Scenario ID | Scenario ID | SITFTS-0050
Role | Scenario Title | Create MPAN
Theme | Theme | New Connection
Business Process | Description | Create an MPAN through new connection process, appoint services and install meter. & Energise the MPAN
Functional Category | Functional Category | Create MPAN
Scenario Title | Functional Area 1 | New Connection |  |  | Business Process Steps
Description | Functional Area 2 | New MPAN, New Connection successful
Boundaries | Creator | Shaun Magee, Dan Gee |  |  | Interface Description
Test Case Variables | Priority | High |  |  | Regression flag
Optionality | Scenario size | Large
Number of test cases | Business Process | BP001, BP002, BP003, BP010B(Related), BP010C (Linked), BP009, BP008, (+BP003A for Smart meters) |  |  | Precondition Test Harness
Scenario size | Boundaries | Processing ends once the Meter is Installed (if not Unmetered) and Energisation has occurred |  |  | Precondition Other
Priority | Test Case Variables | (1) Smart, import+export, forward-dated (MPAN Creation current date)
Systems under test |  | (2) Traditional, single MPAN, forward-dated (MPAN Creation current date)
|  | (3) Advanced Single MPAN, forward-dated (MPAN Creation current date) |  |  | Test evidence
(4) Unmetered, single MPAN, forward-dated (MPAN Creation current date)
| Exception Codes | NA |  |  | Role (simulated)
LDSO Test Case | SIT Test Case
No.
Test Case Id | Test Case Id
Test Case Title | Test Case Title
Test Case Link | Test Case Link
Test Data Requirements | Test Data Requirements
Traceability Requirement |  |  | Test outcome
Test Harness |  |  | Test Harness
Key Validation & Test Evidence |  |  | Interface
BP Step |  |  | requirement
Service initiating process | SIT Test Steps |  | test evidence
Service Recepint Processor
Interface | Test Case Title |  | SITFTS-0050 - Smart Metered
Evidecne Reuiqred | Key Journey | Events | New MPAN Initial Registration - Start
| Step No. |  | 10
| Business Process |  | BP001
| BP Step |  | 5
| Traceability Requirement |  | MHHS-BR-LD-010.1 | MHHS-BR-LD-010.2
| Service Producing Trigger |  | LDSO
| Input/Trigger |  | DB01
| Message Input Event Code |  | N/A
| Service Recipient Processor of Input/Trigger |  | REGS
| Test Step |  | LDSO creates 2 MPAN'S for Import/Export linked MPAN and issues DB01 REGS
| Key Validation & Test Evidence |  | Import/Export Mpan creation and linkage required
| Evidence | Required | Y

## Cover Sheet
LDSO QT - Test Scenarios
Version | Description | Author | Status | Date
V 0.1 | Initial Draft of BP003 Test Scenarios | Non SIT LDSO QT Test Team |  | 2024-01-19
| Review by SIT |  |  | 2024-01-23
V0.2 | Amendments - incorporating SIT comments | Non SIT LDSO QT Test Team |  | 2024-01-24
V0.3 | Amendments - incorporating changes after clarifications from Design Team | Non SIT LDSO QT Test Team | In Progress | 2024-01-29
v0.4 | Amendments after Code Bodies Review & Final check |  |  | 2024-01-31
| Amendments made after data team input |  |  | 2024-02-07
| Start Test Cases |  |  | 12/02.2024
v0.5 | IR8 updates | Test team |  | 20/05.2024
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## TC_BPM003FM_06_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BPM003FM_06_01 | Data Service test. Multiple IF-031 for DS received whilst migration for the same mpan is in progress. This results in the oldest requests being lapsed. | TS_BPM003FM_06 | Notes If a subsequent IF-031 is received for the same mpan before the initial Migration (original IF-031 with oldest timestamp) is completed (Migration completion is indicated through the sending of an IF-036), the original IF-031 should be lapsed and the IF-031 with the most recent timestamp should be used instead. In this case, an IF-035 would be sent cancel the Migration for the IF-031 with the oldest timestamp. Please use the MCA event code in the IF-031, and pick an appointment date 2-3 days in the future, we want the Registration Service to hold off the sending of the IF-036 (wait for the appointment date to become effective, whist we carry out our test). Then we will trigger an new IF-031 for the same mpan with a more recent timestamp. The result will be that Registration Services will trigger the IF-035 (lased) for the original migration attempt rather than the IF-036. Pre requisite The pre requisite for this test, is for the tester to have already initiated the migration for an mpan using the IF-031 created in the Suppler test harness. This IF-031 will be received by the Registration Services. The Registration Services will automatically respond with an accepted IF-032. The Registration Services will automatically send an IF-033 to the Data Service (Test Harness), the user will manually create an accepted IF-034 response from the Data Service (test harness) back to the Registration Service. At this stage the IF-036 is not yet triggered (being held in RS until effective date is reached) Actual testing The tester will trigger another IF-031 for the same mpan that contains a newer timestamp. This condition will trigger an IF-035 lapsed notification from the Registration Services to the suppler (Test Harness) and Data Service (Test Harness) for the IF-031 with the older timestamp. The IF-035 will contain a lapsed reason and code. The data for this test should be as follows: The user will start by generating the IF-031 "Supplier Service Provider Appointment Request" created in the Suppler Test Harness and triggered to the Registration Services with the following characteristics. - IF-031 event code = [DSApp] - Where IF-031 Appointment Scenario is MCA (Migration Change of Agent). When then the Registration Services receives the IF-031 it will do the following automatically Upon receiving the IF-031, the Registration Service will automatically trigger the IF-032 "Supplier Service Provider Appointment Request Response" back to the Suppler (Test Harness) with the following characteristics. • (DI-999)Event Code = [DSAppInitialResp] • (DI-979) Response Code = Accepted Upon receiving the IF-031, the Registration Service will automatically trigger the IF-033 "Registration Service Request for Service Appointment" from the Registration Services to new Data Service (Test Harness) with the following characteristics. • (DI-999)Event Code = [DSAppSPRequest] • (DI-979) Response Code = Accepted After the above is done, the tester will manually create the IF-034 "Service Provider Appointment Request Response" message from the new Data Service test harness back to the Registration Service with the following characteristics. • (DI-999)Event Code = [DSAppSPResponse] • (DI-979) Response Code = Accepted Actual testing The "IF-035 will be automatically triggered from the Registration Service to the expected participants • (DI-999) Event Code = [DSAppLapsed] • (DI-800) Service Provider Appointment Scenario = MCA (Migration Change of Agent) • Code = LP002 - Subsequent Appointment Received | In this scenario a Supplier (a test harness) is generating an IF-031 to the Registration Service to initiate a migration. During this time another IF-031 is triggered for the same Mpan. In this case the old IF-031 should be lapsed using an IF-035 that is sent to the Supplier (Test Harness) and Data Service (Test Harness).
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BPM003FM -Step 20 to step 30 | NA | Suppler (Test Harness) | DIP | MHHS-IF-031 | User manually creates from the Suppler (Test Harness) a IF-031 "Supplier Service Provider Appointment Request" to DIP | n | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
2 | BPM003FM -Step 30 to step 40 | NA | DIP | Registration Service | PUB-031 | DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services | y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems.
3 | BPM003FM -Step 45 to step 50 | NA | Registration Service | DIP | MHHS-IF-032 | Registration Service automatically sends IF-032 (accepted) to the DIP | y | Registration Service automatically sends IF-032 (accepted) to the DIP
4 | BPM003FM -Step 50 to step 55 | NA | DIP | Suppler (Test Harness) | PUB-032 | DIP automatically sends PUB-032 to the Suppler (Test Harness) | n | DIP automatically sends PUB-032 to the Suppler (Test Harness)
5 | BPM003FM -Step 60 to step 65 | NA | Registration Service | DIP | MHHS-IF-033 | Registration Service automatically sends IF-033 to the DIP | y | Registration Service automatically sends IF-033 to the DIP
6 | BPM003FM -Step 65 to step 220 | NA | DIP | Data Service (Test Harness) | PUB-033 | DIP automatically sends PUB-033 to the Data Service (Test Harness) | n | DIP automatically sends PUB-033 to the Data Service (Test Harness)
7 | BPM003FM -Step 221 to step 80 | NA | Data Service (Test Harness) | DIP | MHHS-IF-034 | User manually creates from the Data Service (Test Harness) a IF-034 to the DIP | n | User manually creates from the Data Service (Test Harness) a IF-034 to the DIP
8 | BPM003FM -Step 80 to step 210 | NA | DIP | Registration Service | PUB-034 | DIP automatically sends PUB-034 to the Registration Service | y | DIP automatically sends PUB-034 to the Registration Service
9 | BPM003FM - Step 210 to step 215 | MHHS-Migration-Can-RS-005 | Registration Service | DIP | MHHS-IF-035 | This will happen for the request with the older timestamp Registration Service send IF-035 to the DIP with lapsed code and reason. | y | Registration Services sending the message to the DIP.
10 | BPM003FM - Step 215 to step 95 (Suppler test harness) BPM003FM - Step 215 to step 231 (DS test harness) | NA | DIP | Suppler (Test Harness) Data Service (Test Harness) | PUB-035 | DIP publishes PUB-035 to Suppler (Test Harness) with lapsed code and reason. DIP publishes PUB-035 to Data Service (Test Harness) with lapsed code and reason. | n | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.