## Sheet3 (hidden)
Proposed LDSO QT Scenario | SIT Scenario
Scenario ID | Scenario ID | SITFTS-0050
Role | Scenario Title | Create MPAN
Theme | Theme | New Connection
Business Process | Description | Create an MPAN through new connection process, appoint services and install meter. & Energise the MPAN
Functional Category | Functional Category | Create MPAN
Scenario Title | Functional Area 1 | New Connection |  |  | Business Process Steps
Description | Functional Area 2 | New MPAN, New Connection successful
Boundaries | Creator | Shaun Magee, Dan Gee |  |  | Interface Description
Test Case Variables | Priority | High |  |  | Regression flag
Optionality | Scenario size | Large
Number of test cases | Business Process | BP001, BP002, BP003, BP010B(Related), BP010C (Linked), BP009, BP008, (+BP003A for Smart meters) |  |  | Precondition Test Harness
Scenario size | Boundaries | Processing ends once the Meter is Installed (if not Unmetered) and Energisation has occurred |  |  | Precondition Other
Priority | Test Case Variables | (1) Smart, import+export, forward-dated (MPAN Creation current date)
Systems under test |  | (2) Traditional, single MPAN, forward-dated (MPAN Creation current date)
|  | (3) Advanced Single MPAN, forward-dated (MPAN Creation current date) |  |  | Test evidence
(4) Unmetered, single MPAN, forward-dated (MPAN Creation current date)
| Exception Codes | NA |  |  | Role (simulated)
LDSO Test Case | SIT Test Case
No.
Test Case Id | Test Case Id
Test Case Title | Test Case Title
Test Case Link | Test Case Link
Test Data Requirements | Test Data Requirements
Traceability Requirement |  |  | Test outcome
Test Harness |  |  | Test Harness
Key Validation & Test Evidence |  |  | Interface
BP Step |  |  | requirement
Service initiating process | SIT Test Steps |  | test evidence
Service Recepint Processor
Interface | Test Case Title |  | SITFTS-0050 - Smart Metered
Evidecne Reuiqred | Key Journey | Events | New MPAN Initial Registration - Start
| Step No. |  | 10
| Business Process |  | BP001
| BP Step |  | 5
| Traceability Requirement |  | MHHS-BR-LD-010.1 | MHHS-BR-LD-010.2
| Service Producing Trigger |  | LDSO
| Input/Trigger |  | DB01
| Message Input Event Code |  | N/A
| Service Recipient Processor of Input/Trigger |  | REGS
| Test Step |  | LDSO creates 2 MPAN'S for Import/Export linked MPAN and issues DB01 REGS
| Key Validation & Test Evidence |  | Import/Export Mpan creation and linkage required
| Evidence | Required | Y

## Cover Sheet
LDSO QT - Test Scenarios
Version | Description | Author | Status | Date
V 0.1 | Initial Draft of BP003 Test Scenarios | Non SIT LDSO QT Test Team |  | 2024-01-19
| Review by SIT |  |  | 2024-01-23
V0.2 | Amendments - incorporating SIT comments | Non SIT LDSO QT Test Team |  | 2024-01-24
V0.3 | Amendments - incorporating changes after clarifications from Design Team | Non SIT LDSO QT Test Team | In Progress | 2024-01-29
v0.4 | Amendments after Code Bodies Review & Final check |  |  | 2024-01-31
| Amendments made after data team input |  |  | 2024-02-07
| Start Test Cases |  |  | 12/02.2024
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## TC_BPM003FM_07_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
TC_BPM003FM_07_01 | IF-031 for DS sent for the terminated Mpan will be rejected and the response sent back to the Suppler (Test Harness) | TS_BPM003FM_07 | Pre requisites. The tester will pick an Mpan that is terminated. This means that the MPAN RMP (Registered Meter Point) Status as held in the Registration Service = "Terminated" Manul actions required by tester - creation of the IF-031 in the Suppler test harness for the terminated mpan The data for this test should be as follows: - IF-031 event code = [DSApp] - Where IF-031 Appointment Scenario is MCA (Migration Change of Agent). - Appointment is for a single mpan - Appointment is for a Segment S (smart meter) - (outcome) Where IF-032 is rejected using REG1001 - MPAN not status Created/Operational | In this scenario a Supplier (a test harness) will initiate the migration of a data service (by triggering the IF-031) for an mpan that is terminated. This will be rejected by Registration Services who will respond sent back to the Suppler (Test Harness) with a rejection code an reason
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BPM003FM -Step 20 to step 30 | NA | Suppler (Test Harness) | DIP | MHHS-IF-031 | Tester will manually create the IF-031 in the Suppler (Test Harness) and trigger it to the DIP | n | Evidence of the message that is created the Test Harness (if possible) and being triggered to DIP.
2 | BPM003FM -Step 30 to step 40 | MHHS-Migration-Can-RS-006 | DIP | Registration Service | PUB-031 | DIP automatically publishes PUB-031 "Supplier Service Provider Appointment Request" to Registration Services. The Registration Service will reject the request because the mpan is terminated. | y | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message and updating their systems. The Registration Service will reject the request because the mpan is terminated.
3 | BPM003FM - Step 40 to 45 to 50 | NA | Registration Service | DIP | MHHS-IF-032 | Registration Service automatically sends IF-032 to the DIP with a rejected response code | y | Registration Service automatically sends IF-032 to the DIP with an rejected response code
4 | BPM003FM -Step 50 to 55 | NA | DIP | Suppler (Test Harness) End | PUB-032 | DIP automatically publishes PUB-032 to Suppler (Test Harness) with a rejected response code | n | Evidence of the message published from DIP (if possible) and being triggered to Recipient Service. And the Recipient Service receiving the message.