## Sheet3 (hidden)
Proposed LDSO QT Scenario | SIT Scenario
Scenario ID | Scenario ID | SITFTS-0050
Role | Scenario Title | Create MPAN
Theme | Theme | New Connection
Business Process | Description | Create an MPAN through new connection process, appoint services and install meter. & Energise the MPAN
Functional Category | Functional Category | Create MPAN
Scenario Title | Functional Area 1 | New Connection |  |  | Business Process Steps
Description | Functional Area 2 | New MPAN, New Connection successful
Boundaries | Creator | Shaun Magee, Dan Gee |  |  | Interface Description
Test Case Variables | Priority | High |  |  | Regression flag
Optionality | Scenario size | Large
Number of test cases | Business Process | BP001, BP002, BP003, BP010B(Related), BP010C (Linked), BP009, BP008, (+BP003A for Smart meters) |  |  | Precondition Test Harness
Scenario size | Boundaries | Processing ends once the Meter is Installed (if not Unmetered) and Energisation has occurred |  |  | Precondition Other
Priority | Test Case Variables | (1) Smart, import+export, forward-dated (MPAN Creation current date)
Systems under test |  | (2) Traditional, single MPAN, forward-dated (MPAN Creation current date)
|  | (3) Advanced Single MPAN, forward-dated (MPAN Creation current date) |  |  | Test evidence
(4) Unmetered, single MPAN, forward-dated (MPAN Creation current date)
| Exception Codes | NA |  |  | Role (simulated)
LDSO Test Case | SIT Test Case
No.
Test Case Id | Test Case Id
Test Case Title | Test Case Title
Test Case Link | Test Case Link
Test Data Requirements | Test Data Requirements
Traceability Requirement |  |  | Test outcome
Test Harness |  |  | Test Harness
Key Validation & Test Evidence |  |  | Interface
BP Step |  |  | requirement
Service initiating process | SIT Test Steps |  | test evidence
Service Recepint Processor
Interface | Test Case Title |  | SITFTS-0050 - Smart Metered
Evidecne Reuiqred | Key Journey | Events | New MPAN Initial Registration - Start
| Step No. |  | 10
| Business Process |  | BP001
| BP Step |  | 5
| Traceability Requirement |  | MHHS-BR-LD-010.1 | MHHS-BR-LD-010.2
| Service Producing Trigger |  | LDSO
| Input/Trigger |  | DB01
| Message Input Event Code |  | N/A
| Service Recipient Processor of Input/Trigger |  | REGS
| Test Step |  | LDSO creates 2 MPAN'S for Import/Export linked MPAN and issues DB01 REGS
| Key Validation & Test Evidence |  | Import/Export Mpan creation and linkage required
| Evidence | Required | Y

## Cover Sheet
LDSO QT - Test Scenarios
Version | Description | Author | Status | Date
V 0.1 | Initial Draft of BP003 Test Scenarios | Non SIT LDSO QT Test Team |  | 2024-01-19
| Review by SIT |  |  | 2024-01-23
V0.2 | Amendments - incorporating SIT comments | Non SIT LDSO QT Test Team |  | 2024-01-24
V0.3 | Amendments - incorporating changes after clarifications from Design Team | Non SIT LDSO QT Test Team | In Progress | 2024-01-29
v0.4 | Amendments after Code Bodies Review & Final check |  |  | 2024-01-31
| Amendments made after data team input |  |  | 2024-02-07
| Start Test Cases |  |  | 12/02.2024
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## TC_BPM003FM_08_01
Test case Id | Test Case Title | Test Case Link (to Scenario) | Test Data Requirements | Test Case Outcome
Tc_BPM003FM_08_01 | Migration in progress for DS and pending switch is received for the same mpan resulting in a cancelled migration | TS_BPM003FM_08 | Pre requisites. The tester will then initiate a migration by triggering a IF-031 using scenario code MCA (Migration Change of Agent)created in the Suppler test harness. The effective date of the appointment will be a date 2-3 days in the future. The tester will allow Registration Services to automatically trigger the IF-032 and IF-033 to the expected participants. The Tester will then create and trigger the IF-034 from the Data Service test harness. When the IF-034 reaches the registration service it will hold the appointment until D-1 effective from date of the appointment is reached. When the data is in this state the IF-036 is not yet triggered (basically means migration is not complete) . Keep the data in this state This Test Using the same mpan create a pending switch request in the Registration Services, normally a pending registrations is received into RS via the CSS2880 file, however if the participant has opted out of using the CSS mechanism then they can use the CSS simulator to create the data. As a result of this condition where a pending switch has arrived in RS, where there is a migration already in progress for the same mpan the following will happen:- When the appointment (appointment created as per the pre reqs ) D-1 effective from date is reached, a IF-035 with migration cancellation reason will be sent to the to inform incoming Data Service (Test Harness) and incumbent Supplier (Test Harness) that the Migration has been cancelled. The mpan will be reverted back to legacy. Manul actions required by tester for re req data setup - creation of the IF-031 in the Suppler test harness (for pre req data setup) - creation of the IF-034 in the New Data Service test harness (for pre req data setup) The data for the pre req data setup - IF-031 event code = DSapp - Appointment Scenario in IF-031 is MCA (Migration Change of Agent). - Appointment is for a single mpan - Appointment is for a Segment S (traditional meter) Data Service - Appointment effective date 2-3 days in the future - (outcome) Where IF-035 is cancelled using LP006 - Migration Aborted, Pending Registration Received Data for this test - CSS simulator to create pending switch | In the scenario that a Migration is already underway and a Pending switch is received, when the D-1 effective from status of the Agent appointment is reached, Registration Service sends IF-035 in place of an IF-036 with specific Migration cancellation event code to inform incoming Data Service (Test Harness) and incumbent Supplier (Test Harness) that the Migration has been cancelled. The IF-035 will be received at the same time as the Agents would normally receive an IF-036.
TesStep Id | Business Process Steps | Traceability Requirements | Service Initiating Process | Service Recipient Process | Interface (Input Data) | Test Step Outcome | Evidence Required | Key Validation and Test Evidence
1 | BPM001FM -Step 70 | NA | CSS (Simulator) | Registration Services | CSS flow (CSS2800) | Important This is a pending switch created in the CSS simulator Registration Service has receives the pending switch from CSS (Simulator) | y | To ensure that the Registration Services has received the pending supplier request from the CSS simulator.
2 | BPM003FM -Step 85 to 90 | MHHS-Migration-CoA(DS)-RS-002 | Registration Services | DIP | IF-035 | Because migration is already underway for the same mpan and a Pending switch is received from a new suppler, when the D-1 effective from date of the Agent appointment (the appointment created as part of the re req that is awaiting D-1 effective date) is reached then RS will trigger the IF-035 to the DIP with cancellation reason and code. This mentions Step 85 to 90 on the diagram, however it happens at step 210 to 215 | y | IF-035 sent to the DIP with cancellation reason and code
3 | BPM003FM -Step 90 to 91 (DS) BPM003FM -Step 90 to 95 (SUP) | NA | DIP | Incoming Data Service (Test Harness) Incumbent Supplier (Test Harness) | PUB-035 | PUB-035 sent form DIP to the Incoming Data Service (Test Harness) and Incumbent Supplier (Test Harness) This mentions the following steps on the diagram, Step 90 to 91 (DS) Step 90 to 95 (SUP) But actually happens at the following steps Step 215 to 231 (DS) Step 215 to 95 (SUP) | n | PUB-035 sent form DIP to the Incoming Data Service (Test Harness) and Incumbent Supplier (Test Harness)