## Comments
DEL2207 - Qualification Approach & Plan Comments Log
*Organisation: |  |  | Please add your comments to the template below, ensuring that you fill all of the mandatory columns marked with an *. If you have no comments and want to confirm you have reviewed the document, please input 'Confirmed Reviewed' in the Comment box and 'n/a' for the remaining boxes. Where mandatory columns have not been filled, these comments may be rejected or the sender may be asked to provide more detail.
*Constituency:
*Date:
Comment ID | *Ref # | *Comment | *Suggested Change | *Impact of not making the Change | *Comment Owner | *Comment Owner to be anonymised | Constituency | Theme | Decision | Action | Owner | Action Status | Final Comments
A4 - 1 | Annex 4 - Section2 Impact for Participant Roles | 1) Appears inconsistent with the Migration Strategy & Approach which requires 100% of NHH sites to complete migration to HH 2) Does not appear to consider the impact upon LDSO's if Suppliers do not qualify by M14. Any extended requirement for migration will have unbudgeted cost implications upon LDSO's. | 1) Align the Qualification approach with the Migration Strategy & Approach. 2) Complete a review of the impact on LDSOs regarding this risk and recommend mitigation measures against that risk with timescales. | 1) Customers and MPANs are not migrated over. 2) Contingency plans and timescales not available. | Electricity North West |  |  |  | Accept | Respond | George P | Closed | Programme to confirm any inconsitiency with Migration Strat & Approach and Impact oon M14 for LDSOs
A4 - 2 | Annex 4 | Lots of decisions to be agreed within the working groups so is difficult to comment on a document that is yet to be completed. | Updates & clarifications from MHHS programme. | If change/clarification not provided then as a participant we would struggle to plan the most appropriate approach. | SSE Energy Solutions |  |  |  | Update Document | Update Document | George P | Closed | Updated Section 3 to include footnote which states "Please be advised that these are the current arrangements agreed by the Programme and Code Bodies’ Performance Assurance Boards (PAB) and the view may be revised."
A4 - 3 | 1.Requirement to Complete Qualification | Section 1.2 refers to, 'Failure to complete such MHHS Qualification by the date set out in the MHHS Qualification Plan shall result in the Party not being able to become a Registrant for Metering Systems for which it is not already a Registrant until it has completed MHHS Qualification'. The role of Registrants can apply to more than one BSC Party role and in different contexts i.e. DNOs can be registrants (for CVA sites) but our assumption is that this is not what is meant. | Expand the section detailing who is impacted, in what context and what the specific impact is (so for all parties) OR Make clear this is referencing Suppliers only. | No clarity as to what failure to complete MHHS Qualification means for parties (other than Suppliers). | UK Power Networks |  |  |  | Update Document | Update Document | George P | Closed | Clairification made to Section 1.3 to advise "Suppliers, in their role as Registrants"
A4 - 4 | 2 - Impact for Participant Roles (LDSOs) | This currently states, 'As the LDSO, SMRA and UMSO roles are integral for the operation of the rest of the market our assumption is that the MHHSP will ensure that all existing LDSOs have completed MHHS Qualification prior to M11/M12 (the start of migration)'. However, we understood the LDSO milestone is M10 (Central Systems Ready for Migrating MPANs) and thus allowing a contingency between M10 and M11/M12. | Amend to 'As the LDSO, SMRA and UMSO roles are integral for the operation of the rest of the market our assumption is that the MHHSP will ensure that all existing LDSOs have completed MHHS Qualification prior to M10 (Central Systems Ready for Migrating MPANs).' | Unclear if M10 (Central Systems Ready for Migrating MPANs) or M11/M12 (Start of Migration) are the key milestones for LDSOs to meet. | UK Power Networks |  |  |  | Update Document | Update Document | George P | Closed | Updated to read "MHHS Qualification prior to M10 (Central Systems Ready for Migrating MPANs)"
A4 - 5 | 2 - Impact for Participant Roles (IDNOs) | This section only references new entrant iDNOs. What is the expectancy of existing iDNOs? | Add row for existing iDNOs. Presumably will be the same requirement as for LDSOs? (i.e. complete Qualification before M10 or M11/M12)? OR Combine LDSO and IDNO sections together as the impact should be same for both and make it clear that LDSOs is referring to DNOs and IDNOs. | No clarity as to what failure to complete MHHS Qualification means for iDNOs. | UK Power Networks |  |  |  | Update Document | Update Document | George P | Closed | Updated Role titles to specify "New Entrant IDNOs"
A4 - 6 | 2 - Impact for Participant Roles (IDNOs) | The final column states that, 'This restriction does not apply to LDSOs'. This should be IDNOs. | Amend to, 'This restriction does not apply to IDNOs'. OR Combine LDSO and IDNO sections together as the impact should be same for both. | Unclear if this is referring to LDSOs or IDNOs. | UK Power Networks |  |  |  | Update Document | Update Document | George P | Closed | Updated Column to read "New entrant IDNOs …"
A4 - 7 | 3 - Detailed Process | The section refers to 'all participants' but M14 is when all suppliers must be able to accept MPANs under the new TOM. This is not relevant to LDSOs and iDNOs where the assumption is they will be ready by M10 (or M11/M12) so over 12 months in advance of M14. | Make it clear that Section 3 is not 'All Participants' but excludes LDSOs and iDNOs. | Confusion and inconsistencies on the impacted parties in this section. | UK Power Networks |  |  |  | Update Document | Update Document | George P | Closed | Updated to Read "Remind all Suppliers and Supplier Agents"
A4 - 8 | General | Need to be clear is the reference of LDSOs is including IDNOs and DNOs. | Add a note to state LDSOs includes DNOs and IDNOs. Update tables to then remove references to DNOs and IDNOs and treat all as LDSOs (and only make the distinction between existing or new entrants). | Unclear if this is referring to LDSOs or IDNOs. | UK Power Networks |  |  |  | Update Document | Update Document | George P | Closed | Updated to ensure all refferecnes specifcy "LDSO" or "New Entrant IDNO".
A4 - 9 | 1.2 | It is made clear that Suppliers will not be able to register Metering Systems if they have failed to migrate by M14. However, if the Supplier continues to fail to qualify, there is nothing about what will happen to the Metering Systems already registered to them. Surely we cannot have any MPANs trading in the old NHH system post M16 as we shouldn't be running 2 settlement systems past this date? | We are aware this has already been raised at QWG and we would support the view that more detail is required about what will happen if Suppliers don't qualify (eg potential forced exit from the market, leading to SOLR). This document assumes all Suppliers will be intending to qualify. | Parties will not have a clear understanding of the outcome should this scenario occur. | SSE Energy Supply Ltd |  |  |  | Accept | Respond | George P | Closed | This incentive is being progressed by the Programme and OFGEM and further details will be made avaiable once finalised. This incentive sits outside of this process document.
A4 - 10 | 3 | The detailed process has less of a collaborative approach than would be desireable. It does not set out the monitioring activities and steps the Programme and/or Code Bodies would take to identify and work with Parties who may be at risk of failing to qualify by M14, in order to avoid the later steps in the detailed process. | Provide more detail of ways in which Programme and/or Code Bodies would identify and work with Parties who may be at risk of failing to qualify. | The areas identified are material to the holistic process, and should therefore be included in the scope of this document to ensure completeness and transparency. | Eon Next |  |  |  | Reject | Respond | George P | Closed | Please see QA&P section 11.1 & 11.2 which sets out the MHHS Qualification Progress Reporting and Escalation Process
A4 - 11 | 2 | The scope of the document is limited in that it provides a repercussion for suppliers who fail to qualify, but not IDNOs or LDSOs. | Provide detail on the incentive regime, or any other alternative assurances, for other Roles who's failure to qualify by M14 would have a material impact on the Programme. | Provides transparency of governnce for other Roles. | Eon Next |  |  |  | Accept | Respond | George P | Closed | This incentive is being progressed by the Programme and OFGEM and further details will be made avaiable once finalised. This incentive sits outside of this process document.
A4 - 12 | 3 | The document makes clear that suppliers will be subject to restrictions if they fail to qualify, and cannot be excused due to failures of third parties. Detailed steps are provided to set out what will happen in such a circumstance. The exception to this is if the failure is caused by issues with the central systems, Code Body, or MHHSP, however the document does not provide any detail as to what steps are taken in such a curcumstance. | Provide detail as to 'what next' if failure to qualify by M14 is caused by central systems, Code Body, or MHHSP. | Non-inclusion of this deatil means a lack of common understanding between Programme and Participants as to how such a failure would be managed. | Eon Next |  |  |  | Accept | Respond | George P | Closed | Programme to confirm any Guideance around the M14 go/no go decision. Section 3.2 Outlines that Code bodies will "Notify Ofgem whether there are any material issues with Central System, Code Body or MHHSP issues during the MHHS Qualification phase that could be considered to impact Programme Parties’ ability to hit M14"
A4 - 13 |  | Customer contract implications where a supplier is prevented from gaining new meters | if a supplier is stopped from gaining new business due to not qualifying by M14 then customers contracts may not be honored, causing possible customer detriment, particularly product & pricing if a contract is agreed for XX date - has there been any consideration into customer protections?? | further clarification & strengthening of consequence is required from Ofgem - the codes do not stretch to consumer impacts in the instance a prevented switch causes customer harm. | Npower Business Solutions |  |  |  | Accept | Respond | George P | Closed | This sits outside of this Process Document. OFGEM to provide detail on Customer Impacts of this Process Document. Meeting the requirements for M14 is a Supplier requirement and Suppliers will be made aware significantly in advance of M14 of the consequence of not meeting this date.
A4 - 14 |  | End state: if a supplier does not qualify at any point prior to M16 | if a supplier is stopped from gaining new business due to not qualifying by M14 & continues to not qualify at all then what's the consequence/remedial action? | Risks full transition to MHHS | Npower Business Solutions |  |  |  | Accept | Respond | George P | Closed | This incentive is being progressed by the Programme and OFGEM and further details will be made avaiable once finalised. This incentive sits outside of this process document.
A4 - 15 | 1.3 | Typo | "..by do.." should say "..by milestone M14 do.." | Typo needs correction. | Siemens |  |  |  | Update Document | Update Document | George P | Closed | Updated to read "by Milestone 14 do not…"
A4 - 16 | 1.3 | Annex 4 needs to acknowledge that a participant with multiple roles could qualify in some but not all of those roles. | To ensure that participants that do not complete MHHS Qualification for all their roles by M14 do not participate in MHHS for the roles that are not qualified. | A participant that only qualifies in some of their roles needs to be in scope of annex 4 for the unqualified roles. | Siemens |  |  |  | Reject | Respond | George P | Closed | Annex 4 sets out Process for each role, as participants will qualify per Role. If an organisation has multiple roles, each role has an applicable process set out within Annex 4
A4 - 17 | 2 | Typo | Section title "Impact of for Participant Roles" should say "Impact of missing M14 for Participant Roles". | Typo needs correction. | Siemens |  |  |  | Update Document | Update Document | George P | Closed | Updated to read "2. Impact of missing M14 for Participant Roles"
A4 - 18 | 2 | Under LDSO "our assumption is that the MHHSP will ensure that all existing LDSOs have completed MHHS Qualification prior to M11/M12". I don’t think something this serious can be an assumption. | It should be stated as fact that LDSOs must be qualified by M11/M12. If an LDSO is not qualified, the M11/M12 date will be pushed back. | While the probability of an LDSO not being qualified is low, the knock-on consequences of an M11/M12 delay could be severe. | Siemens |  |  |  | Update Document | Update Document | George P | Closed | Updated to highlight "MHHS Qualification prior to M10 (Central Systems Ready for Migrating MPANs)"
A4 - 19 | 3.3 | This section needs to acknowledge that a participant could qualify in some roles but not all roles. | "Contact all participants that have not completed MHHS Qualification to.." should say "Contact all participants that have not completed MHHS Qualification for all their roles to.." | A participant that only qualifies in some of their roles needs to be in scope. | Siemens |  |  |  | Update Document | Update Document | George P | Closed | Updated to read "Contact all participants that have not completed MHHS Qualification for all their Roles "
A4 - 20
A4 - 21
A4 - 22
A4 - 23
A4 - 24
A4 - 25
A4 - 26
A4 - 27
A4 - 28
A4 - 29
A4 - 30
A4 - 31
A4 - 32
A4 - 33
A4 - 34
A4 - 35
A4 - 36
A4 - 37
A4 - 38
A4 - 39
A4 - 40
A4 - 41
A4 - 42
A4 - 43
A4 - 44
A4 - 45
A4 - 46
A4 - 47
A4 - 48
A4 - 49
A4 - 50
A4 - 51
A4 - 52
A4 - 53
A4 - 54
A4 - 55
A4 - 56
A4 - 57
A4 - 58
A4 - 59
A4 - 60
A4 - 61
A4 - 62
A4 - 63
A4 - 64
A4 - 65
A4 - 66
A4 - 67
A4 - 68
A4 - 69
A4 - 70
A4 - 71
A4 - 72
A4 - 73
A4 - 74
A4 - 75
A4 - 76
A4 - 77
A4 - 78
A4 - 79
A4 - 80
A4 - 81
A4 - 82
A4 - 83
A4 - 84
A4 - 85
A4 - 86
A4 - 87
A4 - 88
A4 - 89
A4 - 90
A4 - 91
A4 - 92
A4 - 93
A4 - 94
A4 - 95
A4 - 96
A4 - 97
A4 - 98
A4 - 99
A4 - 100
A4 - 101
A4 - 102
A4 - 103
A4 - 104
A4 - 105
A4 - 106
A4 - 107
A4 - 108
A4 - 109
A4 - 110
A4 - 111
A4 - 112
A4 - 113
A4 - 114
A4 - 115
A4 - 116
A4 - 117
A4 - 118
A4 - 119
A4 - 120
A4 - 121
A4 - 122
A4 - 123
A4 - 124
A4 - 125
A4 - 126
A4 - 127
A4 - 128
A4 - 129
A4 - 130
A4 - 131
A4 - 132
A4 - 133
A4 - 134
A4 - 135
A4 - 136
A4 - 137
A4 - 138
A4 - 139

## Control (hidden)
Constituency | Artefacts
Central Party | MHHSP-TRANS-BRS001-Transition Approach and Parallel Running Requirments
Large Supplier | MHHS-DES242-Transitional BMU Aggreated Data
Medium Supplier | MHHS-DES241 - Transitional Scaling Weights
Small Supplier
I&C Supplier
Supplier Agent
Independent Supplier Agent
DNO
IDNO
Software Provider
Other- MHHS Participant

## Design Artefacts (hidden)
Published Documents |  | Lists
Design Artefact | Version Number | Version Number | Status
METH001 - ADV Validation and Estimation | 1 | v1.1 | Accepted
Rejected
Requires Further Clarification
Action
Submitted