## Summary (hidden)
Theme | Scope Theme | Scenario Details | Equivalent SIT Scenario | Test Case Name | Test cases | Comments | Questions
1 | New Connection | End to end covering: New connection (LDSO only so could start later for non LDSO) Initial Registration (Supplier only so could start later for MOA / DS) Agent appointment (relevant for all roles) Energisation and Meter Install (relevant for all roles) | SITFTS 0050 | SITFTS0050- Advanced SITFTS0050- Traditional | Traditional needed for SDS and Smart MOA Smart to be created for SDS and Smart MOA Advanced needed for ADS and Advanced MOA Supplier could do both | Didn’t suggest Smart Test Case as this covers impact and export. | Are we ok with just a single end to end scenario for this theme? Yes Should supplier test against both? Both to be created Do we need import / export and related or can we just do these for the appointment and CoS scenarios? covered in other scenarios as the link is added after the connection
2 | Change of Registration Data | Change of Customer Appointment MS | SITFTS 0100 |  | Traditional / Smart needed for SDS and Smart MOA Advanced needed for ADS and Advanced MOA Supplier could do both |  | Should supplier test against both? We should create both and then ask if they have separate processes / systems for smart and advanced before determining whether to test both
2 | Change of Registration Data | Change of Customer Appointment DS | SITFTS 0180 |  | Smart needed for SDS and Smart MOA Advanced needed for ADS and Advanced MOA Supplier could do both
2 | Change of Registration Data | DCC Enrolment Update | SITFTS 1020 |  | TC01 - applicable to Supplier and SDS. Not applicable to MOA | There are two test cases and the difference is not clear
2 | Change of Registration Data | Domestic Premises Update | SITFTS 0940 |  | TC01 is Smart - applicable to SDS and Smart MOA TC02 is Advanced - applicable to ADS and Advanced MOA Supplier could do both
2 | Change of Registration Data | Legacy Info Update | SITFTS 1010 |  | TC01 Trad for smart agents and suppliers TC02 Smart for smart agents and suppliers | There are 4 different test cases covering Profile Class and SSC update individually and separately. Just doing the joint scenario
2 | Change of Registration Data | Consent Granularity Update | SITFTS 0930 |  | BSC to confirm which test case
2 | Change of Registration Data | IHD Update | SITFTS 0995 |  | TC01 - smart covers Smart MOA, SDS and Supplier TC02 rejection - Supplier only | No Advanced needed
2 | Change of Registration Data | GSP Group Update | SITFTS 0920 |  | BSC to confirm which test case. TC02 is Traditional, TC03 is Advanced
2 | Change of Registration Data | Address Update | SITFTS 0920 |  | TC01 - smart covers Smart MOA, SDS and Supplier TC01A create new advanced test case for Smart MOA, ADS and Supplier
2 | Change of Registration Data | SMSO Update | SITFTS 0990 |  | TCO1 - covers Smart MOA, SDS and Supplier. | No Advanced needed
2 | Change of Registration Data | SMSO Update | SITFTS 0990 |  | TCO2 - Supplier only covers rejection
2 | Change of Registration Data | Metered Indicator Update | SITFTS 0980 |  | TC01 Smart / TC02 Trad covers Smart MOA and SDS TC03 Advanced covers Advanced MOA and ADS Supplier could do both
2 | Change of Registration Data | Energy Direction Update | SITFTS 0970 |  | TC01 Smart import to export TC02 Advanced export to import Suppliers could do both
2 | Change of Registration Data | Related Metering Point Update | SITFTS 0960 |  | TC01 Smart Related Removal Smart MOA and SDS and Supplier TC01A create new Advanced Related Removal for Advanced MOA, ADS and Supplier TC02 Advanced Related Addition Advanced MOA and ADS and Supplier TC02A create new Smart Related Addition for Smart MOA, SDS and Supplier
2 | Change of Registration Data | Related Metering Point Update Rejection (supplier only) | SITFTS 0965 |  | Supplier only
2 | Change of Registration Data | Import / Export Association Update | SITFTS 1000 |  | TC01 smart addition single supplier - Smart MOA, SDS and Supplier TC01A create new advanced addition for Advanced MOA, ADS, Supplier TC02 advanced removal single supplier Advanced MOA, ADS and Supplier TC02A create new Smart removal for Smart MOA, SDS and Supplier TC03 covers smart separate supplier linkage creation - should test export only TC03A create new test case for Advanced export only linkage creation
2 | Change of Registration Data | Import / Export Association Update Rejection (supplier only) | SITFTS 1005 |  | Supplier only
3 | Change of Supplier | Single MPAN end to end covering: Switch Request to CSS (Supplier only so could start later for MOA / DS) Agent Appointment (including MTD transfer) Transfer Read Settlement Calender | SITFTS 0035 |  | There is only a single test case covering Smart with estimated read TC02 create new advanced single MPAN test case | BSC question - do we need to check for smart with actual data as this scenario only covers estimated read There are scenarios with change of DS but no change of MS (SITFTS 0020) or scenarios with change of MS but no change of DS (SITFTS0030) - not required for QT
3 | Change of Supplier | Appointment rejection (Supplier only) |  |  |  | There is an appointment update rejection but no appointment rejection that I can see. To be created if no one can find one
3 | Change of Supplier | Appointment lapsed due to secured active not being received | SITFTS 0045 |  | Smart for SDS and Smart MOA Advanced for ADS and Advanced MOA Suppliers could do both
3 | Change of Supplier | Related CoS covering agent appointments | SITFTS 0040 |  | Traditional for SDS, Smart MOA and Supplier Create new test cases for smart and advanced
3 | Change of Supplier | Import / Export CoS covering agent appointments | SITFTS 0040 |  | Advanced for ADS, Advanced MOA and Supplier Create new test cases for smart and trad
3 | Change of Supplier | Import / Export CoS covering agent appointments with different supplier | SITFTS 0025 |  | TC02 smart linked export for Smart MOA, SDS and Supplier. TC02A create advanced linked export for Advanced MOA, ADS and Supplier
4 | Change of Data Service | Single MPAN end to end covering: Agent Appointment (including MTD transfer) Transfer Read - consumption transfer Can we also cover the COS MS DS Change - Settlement
4 | Change of Data Service | Appointment rejection (Supplier only)
4 | Change of Data Service | Related CoS covering agent appointments | N/A |  | Use shared steps for smart, trad advanced related | No related for Advanced
4 | Change of Data Service | Import / Export CoS covering agent appointments | N/A |  | Use shared steps for smart, trad advanced linked | No import export for Smart
5 | Change of Metering Service | Single MPAN single covering agent appointment | N/A |  | Use shared steps for smart, trad advanced linked
5 | Change of Metering Service | Appointment rejection (Supplier only) |  |  |  | There is an appointment update rejection but no appointment rejection that I can see
5 | Change of Metering Service | Related CoS covering agent appointments | N/A |  | Use shared steps for smart, trad advanced related
5 | Change of Metering Service | Import / Export CoS covering agent appointments | N/A |  | Use shared steps for smart, trad advanced linked
6 | Metering Changes | Meter Update - Install, Remove, Exchange | SITFTS 0900 |  | TC01 covers trad to smart exchange for Smart MOA, Smart DS and Supplier TC03 covers advanced to advanced exchange for Advanced MOA, Smart DS and Supplier | TC02 smart install and TC04 advanced removal not included | We cover install with new connection, remove with de-energisation and exchange with change of market segment. Suggest we just use an exchange scenario as a basic test
6 | Metering Changes | Meter Update Rejection | SITFTS 0905 |  | There are 6 test cases - keep them all and decide which apply later: (1) traditional--> smart SMETS2 exchange (2) smart SMETS1 --> smart SMETS2 exchange (3) Smart SMETS2 installation (4) Advanced installation (5) traditional, removal (6) Advanced, removal
6 | Metering Changes | End to end covering: Disconnection leading to IF009 Registration de-activation Auto de-appointment of agents | SITFTS 0840 |  | TC01 for smart MOA and Smart DS TC03 for Advanced MOA and Advanced DS Supplier could do both | I dont think we need TC02 which covers trad. TC04 covers unmetered I would like to have had this starting with a de-energisation and meter removal as the equivalent to new connection but this is only available for related (SITFTS 0850) of import / export (SITFTS 0855) to decide if we need this as well
6 | Metering Changes | Related Disconnection | SITFTS 0850 |  | Smart for Smart MOA, SDS and Supplier Advanced for Advanced MOA, ADS and Supplier Traditional for Smart MOA, SDS and Supplier
6 | Metering Changes | Linked Disconnection | SITFTS 0855 |  | Smart for Smart MOA, SDS and Supplier Advanced for Advanced MOA, ADS and Supplier Create new test case for Traditional for Smart MOA, SDS and Supplier
6 | Metering Changes | Change of Energisation Status | SITFTS 280 |  | TC01 Smart credit for Smart MOA, Smart DS and Supplier TC01A create smart Ldso energisation for Smart MOA, SDS and Supplier TC04 Advanced for Advanced MOA, Advanced DS TC04A create Advanced MOA energisation for Advanced MOA and Supplier | No De-energisation scenarios but this is covered for related and linked in SITFTS 0850 and 0855 and also rejections in SITFTS0360 I dont think we need : TC02 smart prepay - I think the proceses are the same with just a different event code TC03 Trad - process the same as smart Unmetered is covered in TC05 These scenarios differ as the TC01 has MOA energisation and TC04 has LDSO energisation. Additional test cases to be created | MAC - SITFTS-ST0015 - Can we also cover the settlement section of the requirements at the end?
6 | Metering Changes | Change of Energisation Status Rejection by Registration Service | SITFTS 0360 |  | TC01 Smart MOA de-energisation for Smart MOA, SDS and Supplier TC01A create smart Ldso de-energisation for Smart MOA, SDS and Supplier TC03 Advanced LDSO de-energisation for Advanced MOA and Supplier TC03A create Advanced MOA de-energisation for Advanced MOA and Supplier | TC02 not needed as just covering a different rejection reason. These scenarios differ as the TC01 have MOA de-energisation and TC03 has LDSO de-energisation. Additional test cases to be created
6 | Metering Changes | Change of Energisation Status Rejection by MOA | SITFTS 0360 |  | TC04 covers this for trad for smart MOA and Supplier TC04A create test case for advanced MOA and Supplier
6 | Metering Changes | Historic Meter Update | SITFTS 0890 |  | TC01 Amend Meter Id for smart MOA, Smart DS TC02 Amend meter Id rejected for smart MOA TC03 Meter Removal for Advanced MOA, Advanced DS TC04 Meter Removal rejected (trad) for smart MOA TC05 Meter Addition for smart MOA and Smart DS TC06 meter addition rejection for smart MOA Supplier could test all | We dont have meter rejection for Advanced but the scenarios is the same for trad and advanced so could just apply to advanced? | Do we need all these scenarios - maybe for MOA but not for DS and Supplier
6 | Metering Changes | MAP Id Update | SITFTS 0910 |  | TC01 Smart for Smart MOA and Supplier TC03 Advanced for Advanced MOA and Supplier | TC02 not needed as just covering a different rejection reason. These scenarios differ as the TC01 have MOA de-energisation and TC02 has LDSO de-energisation. | Do we need to test MOA de-energisation and LDSO de-energisation for both?
6 | Metering Changes | MAP Id Update Failure | SITFTS 0915 |  | Smart MOA and Supplier Create test case for Advance MOA and Supplier
6 | Metering Changes | Change of Market Segment | SITFTS 0860 |  | TC01 Advanced to Smart - Advanced and Smart MOA and Advance and Smart DS TC02 Smart to Advanced - Advanced and Smart MOA and Advanced and Smart DS Supplier could test both | I havent included TC03 which include import / export association or TC04 which is Trad to Advanced I havent seen a straightforward change of connection type to test the IF043 / 44 - will need to check this is covered.
6 | Metering Changes | Change of Market Segment with CoS | SITFTS 0862 |  | Single test case - smart to advanced for all agents |  | This is a very complicated scenario. Most of the complexity comes from the choreography and registraton service processing but it would be a good one to test in QT unless people feel like its an edge case
6 | Metering Changes | Receipt of invalid Market Segment |  |  |  |  | There is a full change of segment scenario covering this (SITFTS0880) but I dont think we need it all so need to understand if theis element is tested as a small send and receive scenario
7 | Consumption | Amend Override Readings | SITFTS 1070
7 | Consumption | Amendment Accepted | SITFTS 10110
7 | Consumption | Amendment Criteria No Met | SITFTS-1080
7 | Consumption | Amendment Rejected | SITFTS-1100 TC01
7 | Consumption | Amendment Invalid Data | SITFTS-1090 TC01
7 | Consumption | Amendment Trading Dispute | SITFTS-1095 TC01
7 | Consumption | COS Transfer Reads | SITFTS0012
7 | Consumption | Invalid | SITFTS-0270
7 | Consumption | LSS IF-021 | SITFTS0530
7 | Consumption | Smart | SITFTS-0260 TC03
7 | Consumption | Unmetered Invalid
7 | Consumption | DS Change of Transfer of Reads | SITFTS0132-
7 | Consumption | Estimated Tra Multi Rates
7 | Consumption | SDS Estimation
7 | Consumption | ADS Meter Adance Reconcillation
7 | Consumption | ADS Import Estimation | SITFTS-0305 TC07
7 | Consumption | ADS Export Estimation
7 | Consumption | ADS Opt-Out Estimation | SITFTS0315- 01 Method 0 O-R
7 | Consumption | UMSDS Estimation
7 | Consumption | Load Shapes in Estimation | Shared Steps
8 | Settlement | BSC

## Overview
Purpose | List of Test Scenarios and Cases for Non-SIT Supplier and Agent Qualification Testing.
Overview | To maintain equivalence between the testing carried out by SIT participants and Non-SIT S&A QT Participants, the Non-SIT S&A QT Test Scenarios and Test Cases will aim to re-use the SIT Test Scenarios and Test Cases as far as possible. Selection of the specific SIT Test Scenarios and Test Cases for inclusion in Non-SIT S&A QT will focus on tests covering the MHHS Business Requirements identified by the Code Bodies as part of the BSC & REC Assessment Criteria. The selection of SIT Test Cases will be informed by the MHHS Business Requirement traceability tagging contained in the SIT Test Steps, with a view to providing maximum coverage of Code Body-identified MHHS Business Requirements whilst minimising the number of Qualification Test Cases each Non-SIT S&A QT Participant is required to perform. Responsibility for the final selection of Qualification Test Cases resides with the Code Bodies. For further information please refer to Qualification Approach & Plan - Annex 2 Non-SIT Supplier and Agent MHHS QT Approach and Plan.
Assumptions | - Prioritise more common scenarios as our approach is risk-based. - For Suppliers, if Smart and Advanced Test Cases are identical, we should only test one, ensuring sufficient coverage across Smart and Advanced segments. - For Metering Services and Data Services, in SIT there are some test cases where only one market segment is covered e.g. Advanced or Smart as participants are qualifying in both, for Qualification these may need to be split into two separate test cases to ensure coverage where participants may not be qualifying in both roles. - QT Test Cases should cover all possible event codes for a particular DIP message, however, the Participant will not be required to test each variant. From the full set of Test Cases, Code Bodies may identify one or more event code variant for a Participant to test. - In QT, we won't test retrospective Test Case variants and just test prospective. - Batch 1 of Test Scenarios is the initial core set of Scenarios that will form a part of QT. These have been developed to ensure coverage of the key MHHS Business Processes. - Code Bodies are doing further work on these to determine coverage of MHHS Business Requirements. Any gaps identified will be covered in Batch 2 of the QT Test Scenarios.
Authors | Non-SIT S&A QT Team and Code Bodies

## QT Scenarios Batch 1
Theme | Scope Theme | QT Scenario Details | Equivalent SIT Scenario | Document ID | SIT Scenario Title | SIT Test Case Title | SMOA | AMOA | SDS | ADS | Supplier | UMSDS
1 | New Connection | End to end covering: New connection Initial Registration Agent appointment Energisation and Meter Install | SITFTS 0050 | MHHS-DEL1757 | SITFTS-0050 New Connection | SITFTS0050- Traditional | Y |  | Y |  | Y
1 | New Connection | End to end covering: New connection Initial Registration Agent appointment Energisation and Meter Install | SITFTS 0050 | MHHS-DEL1757 | SITFTS-0050 New Connection | SITFTS0050- Advanced |  | Y |  | Y | Y
2 | Change of Registration Data | Change of Customer Appointment MS | SITFTS 0100 | MHHS-DEL1806 | SITFTS-0100 REG Change Cust Appt MS | SITFTS0100- Smart | Y |  |  |  | Y
2 | Change of Registration Data | Change of Customer Appointment MS | SITFTS 0100 | MHHS-DEL1806 | SITFTS-0100 REG Change Cust Appt MS | SITFTS0100- Advanced |  | Y |  |  | Y
2 | Change of Registration Data | Change of Customer Appointment DS | SITFTS 0180 | MHHS-DEL1805 | SITFTS0180 | SITFTS0180- Smart |  |  | Y |  | Y
2 | Change of Registration Data | Change of Customer Appointment DS | SITFTS 0180 | MHHS-DEL1805 | SITFTS0180 | SITFTS0180- Advanced |  |  |  | Y | Y
2 | Change of Registration Data | DCC Enrolment Update | SITFTS 1020 | MHHS-DEL1775 | SITFTS-1020 REG DCC Enrolment | SITFTS-1020 TC01 |  |  | Y |  | Y
2 | Change of Registration Data | Domestic Premises Update | SITFTS 0940 | MHHS-DEL1764 | REG UPD Domestic Premise Indicator | SITFTS-0940 TC01 | Y |  | Y |  | Y
2 | Change of Registration Data | Domestic Premises Update | SITFTS 0940 | MHHS-DEL1764 | REG UPD Domestic Premise Indicator | SITFTS-0940 TC02 |  | Y |  | Y | Y
2 | Change of Registration Data | Legacy Info Update | SITFTS 1010 | MHHS-DEL1774 | REG UPD Legacy Info | SITFTS-1010 TC01 | Y |  | Y |  | Y
2 | Change of Registration Data | Legacy Info Update | SITFTS 1010 | MHHS-DEL1774 | REG UPD Legacy Info | SITFTS-1010 TC02 | Y |  | Y |  | Y
2 | Change of Registration Data | Consent Granularity Update | SITFTS 0930 | MHHS-DEL1763 | REG UPD Consent Granularity | SITFTS-0930 TC01 |  |  | Y |  | Y
2 | Change of Registration Data | Consent Granularity Update | SITFTS 0930 | MHHS-DEL1763 | REG UPD Consent Granularity | SITFTS-0930 TC02 |  |  |  | Y | Y
2 | Change of Registration Data | IHD Update | SITFTS 0995 | MHHS-DEL1771 | REG UPD IHD | SITFTS-0995 TC01 |  |  |  |  | Y
2 | Change of Registration Data | IHD Update | SITFTS 0995 | MHHS-DEL1771 | REG UPD IHD | SITFTS-0995 TC02 |  |  |  |  | Y
2 | Change of Registration Data | GSP Group Update | SITFTS 0920 | MHHS-DEL1762 | REG UPD MPL Address GSP Group ID | SITFTS-0920 TC02 | Y |  | Y |  | Y
2 | Change of Registration Data | Address Update | SITFTS 0920 | MHHS-DEL1762 | REG UPD MPL Address GSP Group ID | SITFTS-0920 TC01 | Y |  | Y |  | Y
2 | Change of Registration Data | SMSO Update | SITFTS 0990 | MHHS-DEL1770 | SITFTS-0990 | SITFTS-0990 TC01 | Y |  | Y |  | Y
2 | Change of Registration Data | SMSO Update | SITFTS 0990 | MHHS-DEL1770 | SITFTS-0990 | SITFTS-0990 TC02 |  |  |  |  | Y
2 | Change of Registration Data | Metered Indicator Update | SITFTS 0980 | MHHS-DEL1769 | REG UPD Metered Indicator | SITFTS-0980 TC01 | Y |  | Y |  | Y
2 | Change of Registration Data | Metered Indicator Update | SITFTS 0980 | MHHS-DEL1769 | REG UPD Metered Indicator | SITFTS-0980 TC03 |  | Y |  | Y | Y
2 | Change of Registration Data | Energy Direction Update | SITFTS 0970 | MHHS-DEL1768 | REG UPD Energy Direction | SITFTS-0970 TC01 | Y |  | Y |  | Y
2 | Change of Registration Data | Energy Direction Update | SITFTS 0970 | MHHS-DEL1768 | REG UPD Energy Direction | SITFTS-0970 TC02 |  | Y |  | Y | Y
2 | Change of Registration Data | Related Metering Point Update | SITFTS 0960 | MHHS-DEL1766 | SITFTS-0960 REG UPD Related | SITFTS-0960 TC01 | Y |  | Y |  | Y
2 | Change of Registration Data | Related Metering Point Update | SITFTS 0960 | MHHS-DEL1766 | SITFTS-0960 REG UPD Related | SITFTS-0960 TC02 |  | Y |  | Y | Y
2 | Change of Registration Data | Related Metering Point Update Rejection | SITFTS 0965 | MHHS-DEL1767 | REG UPD Related Rejection | SITFTS-0965 TC01 |  |  |  |  | Y
2 | Change of Registration Data | Import / Export Association Update | SITFTS 1000 | MHHS-DEL1772 | REG UPD Linked | SITFTS-1000 TC01 | Y |  | Y |  | Y
2 | Change of Registration Data | Import / Export Association Update | SITFTS 1000 | MHHS-DEL1772 | REG UPD Linked | SITFTS-1000 TC02 |  | Y |  | Y | Y
2 | Change of Registration Data | Import / Export Association Update | SITFTS 1000 | MHHS-DEL1772 | REG UPD Linked | SITFTS-1000 TC03 | Y |  | Y |  | Y
2 | Change of Registration Data | Import / Export Association Update Rejection | SITFTS 1005 | MHHS-DEL1773 | SITFTS-1005 REG UPD Linked Rejection | SITFTS-1005 TC01 |  |  |  |  | Y
3 | Change of Registration Data | GSP Group Update | SITFTS 0920 | MHHS-DEL1762 | REG UPD MPL Address GSP Group ID | SITFTS-0920 TC03 |  | Y |  | Y | Y
3 | Change of Supplier | Single MPAN end to end covering: Switch Request to CSS Agent Appointment (including MTD transfer) Transfer Read Settlement Calender | SITFTS 0035 | MHHS-DEL1817 | COS DS Change Est Read | SITFTS0035-Smart | Y |  | Y |  | Y
3 | Change of Supplier | Appointment lapsed due to secured active not being received | SITFTS 0045 | MHHS-DEL1819 | COS MS DS Change Lapsed Appointments | SITFTS0045-Smart | Y |  | Y |  | Y
3 | Change of Supplier | Appointment lapsed due to secured active not being received | SITFTS 0045 | MHHS-DEL1819 | COS MS DS Change Lapsed Appointments | SITFTS0045-Advanced |  | Y |  | Y | Y
3 | Change of Supplier | Related CoS covering agent appointments | SITFTS 0040 | MHHS-DEL1818 | COS MS DS Change | SITFTS0040- Traditional | Y |  | Y |  | Y
3 | Change of Supplier | Import / Export CoS covering agent appointments | SITFTS 0040 | MHHS-DEL1818 | COS MS DS Change | SITFTS0040- Advanced |  | Y |  | Y | Y
3 | Change of Supplier | Import / Export CoS covering agent appointments with different supplier | SITFTS 0025 | MHHS-DEL1815 | COS DS Change Linked Diff Suppliers | SITFTS0025- Smart Export | Y |  | Y |  | Y
4 | Change of Data Service | Single MPAN single covering agent appointment | Shared Steps | MHHS-DEL1827 | SITFTC-Change of DS Smart Single | Chg of DS-SM Single Steps | Y |  | Y |  | Y
4 | Change of Data Service | Single MPAN single covering agent appointment | Shared Steps | MHHS-DEL1830 | Change of DS Traditional Single | Chg of DS-SM Traditional Steps | Y |  | Y |  | Y
4 | Change of Data Service | Single MPAN single covering agent appointment | Shared Steps | MHHS-DEL1831 | Change of DS Unmeterered Single | Chg of DS-Un Single Steps |  |  |  |  | Y | Y
4 | Change of Data Service | Single MPAN single covering agent appointment | Shared Steps | MHHS-DEL1824 | Change of DS Advanced Single | Chg of DS-AD Single Steps |  | Y |  | Y | Y
4 | Change of Data Service | Related CoS covering agent appointments | Shared Steps | MHHS-DEL1826 | Change of DS Smart Related | Chg of DS-SM Related Steps | Y |  | Y |  | Y
4 | Change of Data Service | Related CoS covering agent appointments | Shared Steps | MHHS-DEL1829 | Change of DS Traditional Related | Chg of DS-TRAD Related Steps | Y |  | Y |  | Y
4 | Change of Data Service | Related CoS covering agent appointments | Shared Steps | MHHS-DEL2017 | Change of DS Advanced Related Multiple | Chg of DS-AD Related Steps |  | Y |  | Y | Y
4 | Change of Data Service | Import / Export CoS covering agent appointments | Shared Steps | MHHS-DEL1825 | Change of DS Smart Linked | Chg of DS-SM Linked Steps | Y |  | Y |  | Y
4 | Change of Data Service | Import / Export CoS covering agent appointments | Shared Steps | MHHS-DEL1828 | Change of DS Traditional Linked | Chg of DS-TRAD Linked Steps | Y |  | Y |  | Y
4 | Change of Data Service | Import / Export CoS covering agent appointments | Shared Steps | MHHS-DEL1822 | Change of DS Advanced Linked | Chg of DS-AD Linked Steps |  | Y |  | Y | Y
5 | Change of Metering Service | Single MPAN single covering agent appointment | Shared Steps | MHHS-DEL1837 | Change of MS Smart Single | Chg of MS-SMART Single Steps | Y |  | Y |  | Y
5 | Change of Metering Service | Single MPAN single covering agent appointment | Shared Steps | MHHS-DEL1840 | Change of MS Trad Single | Chg of MS-TRAD Single Steps | Y |  | Y |  | Y
5 | Change of Metering Service | Single MPAN single covering agent appointment | Shared Steps | MHHS-DEL1834 | Change of MS Advanced Single | Chg of MS-AD Single Steps |  | Y |  | Y | Y
5 | Change of Metering Service | Related CoS covering agent appointments | Shared Steps | MHHS-DEL1836 | Change of MS Smart Related | Chg of MS-SMART Related Steps | Y |  | Y |  | Y
5 | Change of Metering Service | Related CoS covering agent appointments | Shared Steps | MHHS-DEL2022 | Change of MS Traditionial Related Mult | Chg of MS-TRAD Related Steps | Y |  | Y |  | Y
5 | Change of Metering Service | Related CoS covering agent appointments | Shared Steps | MHHS-DEL1833 | Change of MS Advanced Related | Chg of MS-AD Related Steps |  | Y |  | Y | Y
5 | Change of Metering Service | Import / Export CoS covering agent appointments | Shared Steps | MHHS-DEL1835 | Change of MS Smart Linked | Chg of MS-SMART Linked Steps | Y |  | Y |  | Y
5 | Change of Metering Service | Import / Export CoS covering agent appointments | Shared Steps | MHHS-DEL1838 | Change of MS Trad Linked | Chg of MS-TRAD Linked Steps | Y |  | Y |  | Y
5 | Change of Metering Service | Import / Export CoS covering agent appointments | Shared Steps | MHHS-DEL1832 | SITFTC-Change of MS Advanced Linked | Chg of MS-AD Linked Steps |  | Y |  | Y | Y
6 | Metering Changes | Meter Update - Install, Remove, Exchange | SITFTS 0900 | MHHS-DEL1894 | MET Change of Meter successful | SITFTS-0900 TC01 | Y |  | Y |  | Y
6 | Metering Changes | Meter Update - Install, Remove, Exchange | SITFTS 0900 | MHHS-DEL1894 | MET Change of Meter successful | SITFTS-0900 TC03 |  | Y |  | Y | Y
6 | Metering Changes | Meter Update Rejection | SITFTS 0905 | MHHS-DEL1913 | MET Change REGS Rejection | SITFTS-0905 TC01 | Y |  |  |  | Y
6 | Metering Changes | Meter Update Rejection | SITFTS 0905 | MHHS-DEL1913 | MET Change REGS Rejection | SITFTS-0905 TC02 | Y |  |  |  | Y
6 | Metering Changes | Meter Update Rejection | SITFTS 0905 | MHHS-DEL1913 | MET Change REGS Rejection | SITFTS-0905 TC03 | Y |  |  |  | Y
6 | Metering Changes | Meter Update Rejection | SITFTS 0905 | MHHS-DEL1913 | MET Change REGS Rejection | SITFTS-0905 TC04 |  | Y |  |  | Y
6 | Metering Changes | Meter Update Rejection | SITFTS 0905 | MHHS-DEL1913 | MET Change REGS Rejection | SITFTS-0905 TC05 | Y |  |  |  | Y
6 | Metering Changes | Meter Update Rejection | SITFTS 0905 | MHHS-DEL1913 | MET Change REGS Rejection | SITFTS-0905 TC06 |  | Y |  |  | Y
6 | Metering Changes | End to end covering: Disconnection leading to IF009 Registration de-activation Auto de-appointment of agents | SITFTS 0840 | MHHS-DEL1889 | MET DISCONNECT | SITFTS0840-Smart Customer | Y |  | Y |  | Y
6 | Metering Changes | End to end covering: Disconnection leading to IF009 Registration de-activation Auto de-appointment of agents | SITFTS 0840 | MHHS-DEL1889 | MET DISCONNECT | SITFTS0840-Adv LDSO No Meter |  | Y |  | Y | Y
6 | Metering Changes | Related Disconnection | SITFTS 0850 | MHHS-DEL1891 | MET Disconnect Related | SITFTS0850-Smart | Y |  | Y |  | Y
6 | Metering Changes | Related Disconnection | SITFTS 0850 | MHHS-DEL1891 | MET Disconnect Related | SITFTS0850-Advanced |  | Y |  | Y | Y
6 | Metering Changes | Related Disconnection | SITFTS 0850 | MHHS-DEL1891 | MET Disconnect Related | SITFTS0850-Traditional | Y |  | Y |  | Y
6 | Metering Changes | Linked Disconnection | SITFTS 0855 | MHHS-DEL1892 | MET Disconnect Linked | SITFTS0855-Smart | Y |  | Y |  | Y
6 | Metering Changes | Linked Disconnection | SITFTS 0855 | MHHS-DEL1892 | MET Disconnect Linked | SITFTS0855-Advanced |  | Y |  | Y | Y
6 | Metering Changes | Change of Energisation Status | SITFTS 280 | MHHS-DEL1887 | MET Energisation Change | SITFTS-0280 TC01 | Y |  | Y |  | Y
6 | Metering Changes | Change of Energisation Status | SITFTS 280 | MHHS-DEL1887 | MET Energisation Change | SITFTS-0280 TC04 |  | Y |  | Y | Y
6 | Metering Changes | Change of Energisation Status Rejection by Registration Service | SITFTS 0360 | MHHS-DEL1888 | MET Energisation Change Fails | SITFTS-0360 TC01 | Y |  | Y |  | Y
6 | Metering Changes | Change of Energisation Status Rejection by Registration Service | SITFTS 0360 | MHHS-DEL1888 | MET Energisation Change Fails | SITFTS-0360 TC03 |  | Y |  | Y | Y
6 | Metering Changes | Change of Energisation Status Rejection by MOA | SITFTS 0360 | MHHS-DEL1888 | MET Energisation Change Fails | SITFTS-0360 TC04 | Y |  |  |  | Y
6 | Metering Changes | Historic Meter Update | SITFTS 0890 | MHHS-DEL1893 | MET Historic Updates Incl Rejections | SITFTS0890 Trad Hist UPD Rej | Y |  | Y |  | Y
6 | Metering Changes | Historic Meter Update | SITFTS 0890 | MHHS-DEL1893 | MET Historic Updates Incl Rejections | SITFTS0890 Smart Hist UPD Rej | Y
6 | Metering Changes | Historic Meter Update | SITFTS 0890 | MHHS-DEL1893 | MET Historic Updates Incl Rejections | SITFTS0890 Adv Hist REM Acc |  | Y |  |  | Y
6 | Metering Changes | Historic Meter Update | SITFTS 0890 | MHHS-DEL1893 | MET Historic Updates Incl Rejections | SITFTS0890 Trad Hist REM Rej | Y
6 | Metering Changes | Historic Meter Update | SITFTS 0890 | MHHS-DEL1893 | MET Historic Updates Incl Rejections | SITFTS0890 Smart Hist ADD Acc | Y |  |  |  | Y
6 | Metering Changes | MAP Id Update | SITFTS 0910 | MHHS-DEL1914 | MET Change of MAP | SITFTS-0910 TC01 | Y |  | Y |  | Y
6 | Metering Changes | MAP Id Update | SITFTS 0910 | MHHS-DEL1914 | MET Change of MAP | SITFTS-0910 TC02 |  | Y |  | Y | Y
6 | Metering Changes | MAP Id Update Failure | SITFTS 0915 | MHHS-DEL1915 | MET Change of MAP update unsuccessful | SITFTS-0915 TC01 | Y |  |  |  | Y
6 | Metering Changes | Change of Market Segment | SITFTS 0860 | MHHS-DEL1916 | MET Change of Market Segment v0.3 (redlined) | SITFTS-0860 TC01 | Y | Y | Y | Y | Y
6 | Metering Changes | Change of Market Segment | SITFTS 0860 | MHHS-DEL1916 | MET Change of Market Segment v0.3 (redlined) | SITFTS-0860 TC02 | Y | Y | Y | Y | Y
6 | Metering Changes | Change of Market Segment with CoS | SITFTS 0862 | MHHS-DEL1917 | MET Change of Market Segement with COS | SITFTS-0862 TC01 | Y | Y | Y | Y | Y
6 | Metering Changes | Historic Meter Update | SITFTS 0890 | MHHS-DEL1893 | MET Historic Updates Incl Rejections | SITFTS-0890 - Trad Hist ADD Rej | Y
6 | Metering Changes | Receipt of invalid Market Segment |  | MHHS-DEL1919 | MET Connect Type Change with missing Services (MS) | SITFTS-0880 TC01 | Y | Y | Y | Y | Y
7 | Consumption | Amend Override Readings | SITFTS-1070 | MHHS-DEL1977 | CONS Amend Override Readings | SITFTS-1070 TC01 |  |  | Y |  | Y
7 | Consumption | Amend Override Readings | SITFTS-1070 | MHHS-DEL1977 | CONS Amend Override Readings | SITFTS-1070 TC02 |  |  |  | Y | Y
7 | Consumption | Amendment Accepted | SITFTS-1110 | MHHS-DEL1981 | CONS Amendment Accepted | SITFTS-1110 TC01 |  |  | Y |  | Y
7 | Consumption | Amendment Accepted | SITFTS-1110 | MHHS-DEL1981 | CONS Amendment Accepted | SITFTS-1110 TC02 |  |  |  | Y | Y
7 | Consumption | Amendment Criteria No Met | SITFTS-1080 | MHHS-DEL1978 | CONS Amendment Criteria Not Met | SITFTS-1080 TC01 |  |  |  |  | Y
7 | Consumption | Amendment Rejected | SITFTS-1100 | MHHS-DEL1980 | CONS Amendment Rejected | SITFTS-1100 TC01 |  |  | Y |  | Y
7 | Consumption | Amendment Rejected | SITFTS-1100 | MHHS-DEL1980 | CONS Amendment Rejected | SITFTS-1100 TC02 |  |  |  | Y | Y
7 | Consumption | Amendment Invalid Data | SITFTS-1090 | MHHS-DEL1979 | CONS Amendment Invalid Data | SITFTS-1090 TC01 |  |  | Y |  | Y
7 | Consumption | Amendment Invalid Data | SITFTS-1090 | MHHS-DEL1979 | CONS Amendment Invalid Data | SITFTS-1090 TC02 |  |  |  | Y | Y
7 | Consumption | Amendment Trading Dispute | SITFTS-1095 | MHHS-DEL1943 | CONS Amendment Trading Dispute | SITFTS-1095 TC01 |  |  |  |  | Y
7 | Consumption | Amendment Trading Dispute | SITFTS-1095 | MHHS-DEL1943 | CONS Amendment Trading Dispute | SITFTS-1095 TC02 |  |  |  | Y | Y
7 | Consumption | COS Transfer Reads | SITFTS-0012 | MHHS-DEL1937 | CONS CoS Transfer of Reads | SITFTS0012- Trad COR |  |  | Y |  | Y
7 | Consumption | COS Transfer Reads | SITFTS-0012 | MHHS-DEL1937 | CONS CoS Transfer of Reads | SITFTS0012- Smart |  |  | Y |  | Y
7 | Consumption | COS Transfer Reads | SITFTS-0012 | MHHS-DEL1937 | CONS CoS Transfer of Reads | SITFTS0012- Advanced |  |  |  |  | Y
7 | Consumption | COS Transfer Reads | SITFTS-0012 | MHHS-DEL1937 | CONS CoS Transfer of Reads | SITFTS0012- Unmetered |  |  |  |  | Y
7 | Consumption | Invalid | SITFTS-0270 | MHHS-DEL1940 | CONS Invalid | SITFTS-0270 TC01 |  |  | Y |  | Y
7 | Consumption | Invalid | SITFTS-0270 | MHHS-DEL1940 | CONS Invalid | SITFTS-0270 TC02 |  |  |  | Y | Y
7 | Consumption | LSS IF-021 Rejected | SITFTS-0530 | MHHS-DEL1942 | CONS LSS IF-021 Rejected | SITFTS0530 Smart |  |  | Y |  | Y
7 | Consumption | LSS IF-021 Rejected | SITFTS-0530 | MHHS-DEL1942 | CONS LSS IF-021 Rejected | SITFTS0530 Advanced |  |  |  | Y | Y
7 | Consumption | Smart with Gaps | SITFTS-0260 | MHHS-DEL1939 | CONS Smart with gaps | SITFTS-0260 TC01 |  |  | Y
7 | Consumption | Smart with Gaps | SITFTS-0260 | MHHS-DEL1939 | CONS Smart with gaps | SITFTS-0260 TC02 |  |  | Y
7 | Consumption | Smart with Gaps | SITFTS-0260 | MHHS-DEL1939 | CONS Smart with gaps | SITFTS-0260 TC03 |  |  | Y |  | Y
7 | Consumption | Unmetered Invalid | SITFTS-0330 | MHHS-DEL1941 | CONS Unmetered Invalid | SITFTS-0330 TC01 | [5 empty] | Y
7 | Consumption | Unmetered Invalid | SITFTS-0330 | MHHS-DEL1941 | CONS Unmetered Invalid | SITFTS-0330 TC02 | [5 empty] | Y
7 | Consumption | Unmetered Invalid | SITFTS-0330 | MHHS-DEL1941 | CONS Unmetered Invalid | SITFTS-0330 TC03 | [5 empty] | Y
7 | Consumption | Unmetered Invalid | SITFTS-0330 | MHHS-DEL1941 | CONS Unmetered Invalid | SITFTS-0330 TC04 | [5 empty] | Y
7 | Consumption | Unmetered Invalid | SITFTS-0330 | MHHS-DEL1941 | CONS Unmetered Invalid | SITFTS-0330 TC05 | [5 empty] | Y
7 | Consumption | Unmetered Invalid | SITFTS-0330 | MHHS-DEL1941 | CONS Unmetered Invalid | SITFTS-0330 TC06 | [5 empty] | Y
7 | Consumption | Unmetered Invalid | SITFTS-0330 | MHHS-DEL1941 | CONS Unmetered Invalid | SITFTS-0330 TC07 | [5 empty] | Y
7 | Consumption | Unmetered Invalid | SITFTS-0330 | MHHS-DEL1941 | CONS Unmetered Invalid | SITFTS-0330 TC08 | [5 empty] | Y
7 | Consumption | Unmetered Invalid | SITFTS-0330 | MHHS-DEL1941 | CONS Unmetered Invalid | SITFTS-0330 TC09 | [5 empty] | Y
7 | Consumption | DS Change of Transfer of Reads | SITFTS-0132 | MHHS-DEL1938 | CONS DS Change Transfer of Reads | SITFTS0132- Trad |  |  | Y |  | Y
7 | Consumption | DS Change of Transfer of Reads | SITFTS-0132 | MHHS-DEL1938 | CONS DS Change Transfer of Reads | SITFTS0132- Smart |  |  | Y |  | Y
7 | Consumption | DS Change of Transfer of Reads | SITFTS-0132 | MHHS-DEL1938 | CONS DS Change Transfer of Reads | SITFTS0132- Advanced |  |  |  | Y | Y
7 | Consumption | DS Change of Transfer of Reads | SITFTS-0132 | MHHS-DEL1938 | CONS DS Change Transfer of Reads | SITFTS0132- Unmetered |  |  | Y |  |  | Y
7 | Consumption | Estimated Tra Multi Rates | SITFTS-0290 | MHHS-DEL1970 | SITFTS-0290 CONS Trad Meters Different Meter Types | SITFTS0290- E7 Switched Load |  |  | Y |  | Y
7 | Consumption | SDS Estimation | SITFTS-0295 | MHHS-DEL1971 | CONS SDS Estimation | SITFTS0295- 01 Opt-Out |  |  | Y
7 | Consumption | ADS Meter Adance Reconcillation | SITFTS-0300 | MHHS-DEL1972 | SITFTS-0300 CONS SETTLE Advanced Meters Estimation Import | SITFTS-0300 TC01 |  |  |  | Y
7 | Consumption | ADS Meter Adance Reconcillation | SITFTS-0300 | MHHS-DEL1972 | SITFTS-0300 CONS SETTLE Advanced Meters Estimation Import | SITFTS-0300 TC02 |  |  |  | Y
7 | Consumption | ADS Import Estimation | SITFTS-0305 | MHHS-DEL1973 | CONS ADS Import Estimation | SITFTS-0305 TC01 |  |  |  | Y
7 | Consumption | ADS Export Estimation | SITFTS-0310 | MHHS-DEL1974 | SITFTS-0310 CONS SETTLE Advanced Meters Estimation Scenarios | SITFTS-0310 TC02 |  |  |  | Y
7 | Consumption | ADS Opt-Out Estimation | SITFTS-0315 | MHHS-DEL1975 | CONS ADS Opt-Out Estimation | SITFTS0315- 02 Method 0 C-A |  |  |  | Y | Y
7 | Consumption | UMSDS Estimation | SITFTS-0320 | MHHS-DEL1976 | SITFTS-0320 CONS SETTLE Unmetered Estimation | SITFTS0320 TC01 | [5 empty] | Y
7 | Consumption | Load Shapes in Estimation | Shared Steps | MHHS-DEL1983 | SITFTC-MPAN Load Shapes in Estimation | Load Shapes SDS |  |  | Y
7 | Consumption | Load Shapes in Estimation | Shared Steps | MHHS-DEL1983 | SITFTC-MPAN Load Shapes in Estimation | Load Shapes ADS |  |  |  | Y | Y
7 | Consumption | Load Shapes in Estimation | Shared Steps | MHHS-DEL1983 | SITFTC-MPAN Load Shapes in Estimation | Load Shapes UMDS | [5 empty] | Y
8 | Settlement | Settlement Shared Steps ADS | Shared Steps | MHHS-DEL1982 | SITFTC-MPAN Settlement Advanced Data Service | Settle Advanced DS |  |  |  | Y | Y
8 | Settlement | Settlement Shared Steps SDS | Shared Steps | MHHS-DEL1984 | SITFTC-MPAN Settlement Smart Data Service | Settle Smart DS |  |  | Y |  | Y
8 | Settlement | Settlement Shared Steps UMSDS | Shared Steps | MHHS-DEL1985 | SITFTC MPAN Settlement Unmetered Data Service | Settle UMDS |  |  |  |  | Y | Y

## Change Log
Date | Author | Release | Reason for change
2024-03-18 | Non-SIT S&A QT Team / Code Bodies | v0.2 | Initial batch of QT Scenarios
2024-03-20 | Non-SIT S&A QT Team / Code Bodies | v0.3 | Corrections to role mapping errors in version 0.2