## Data List
LDSO
UMSO
Registration Services
LDSO/UMSO/Registration Services
LDSO/UMSO
LDSO/Registration Services
UMSO/Registration Services
Y
N
PIT
QT
PIT/QT
S
M
L
VH
H
M
L

## CoverSheet
QT - Test Scenarios
Version | Description | Author | Date
v0.1 | Initial Draft | Non SIT LDSO QT Test Team | 2022-11-29
v2.0 | Updated following the review with Code Bodies |  | 2024-01-31
Please note that a Glossary of Terms and Acronyms used by the MHHS Programme is available on the MHHS Website
www.mhhsprogramme.co.uk

## Test Scenarios Template
Test Scenario ID | Role | Link to Requirement ID | Link to Business Process | Business Process Steps | Interface ID | Interface Description | Regression flag | Test Scenario Title | Test Scenario Description | Precondition – Data | Precondition Test Harness | Precondition Other | Test variances | Test outcome | Optionality | Test evidence | Number of test cases | Complexity | Priority | Systems under test | Role (simulated)
1 | LDSO/Registration Services | LDSO004, MHHS-BR-RS-064 MHHS-BR-RS-065 | BP003 Change of Data | 120, 130, 145 | MHHS-IF-037, PUB-037 | Notification of Service De-Appointment |  | Data Service De-appointment | Registration Service publishing a Data Service Notification of Service De-appointment via DIP and LDSO recieving and processing the corresponding message and successfully update records in their system | MPAN (Import or export) MPAN for UMS segment MPAN for Advanced segment CSS Secured Active | Outgoing Supplier and old data service set to persudo role for MPAN under test |  | Message received for single MPAN Message received for multiple MPANs Import Export Advanced UMS Negative scenarios, MPANs don't match or receive one type but not receive the other | Registration Service successful generates MHHSP-IF-037 and recives acceptance from DIP. DIP generates PUB-037 which is successfully recivied and processed by LDSO and record is updated accordingly. | If LDSO has opted out of receiving PUB-037, they do not need to run this test via DIP but should provide evidence of receiving this information via alternative mechanism | QT |  | L | VH | Registration Services, LDSO | Outgoing Supplier and Old Data Service
2 | LDSO/UMSO/Registration Services | MHHS-BR-RS-067, MHHS-BR-LD-005, MHHS-BR-MS-030, MHHS-BR-MS-030.1 | BP003 Change of Data | 250 280 281 282 | MHHS-IF-036, PUB-036 | Service Provider Notification of Appointment |  | Data Service Appointment | Registration Service notifying of effective prospective appointment via DIP, LDSO receiving and processing coressponding notification and MTD and UMSO reciving and processing coressponding notification and MTD and sending D0388, if applicable. | UMS Non UMS | Incoming Supplier and ESS set to pseudo role for MPAN under test |  | Variances where we capture both the positive and negative test cases (including any expected error messages) |  | If LDSO has opted out of receiving PUB-036, they do not need to run this test via DIP but should provide evidence of receiving this information via alternative mechanism | QT |  | M |  | Registration Services, LDSO, UMSO | Incoming Supplier and EES
| UMSO/Registration Services |  | BP003 Change of Data | 86, 160, 161, 165, 267 | MHHS-IF-035 | Registraion Service Appointment Status Notification |  | MTD Issued to new data Service |  |  |  |  | Smart, Tradtional, Advanced |  |  | QT |  | M
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be a unique ID and created when each scenario is added
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be the participants role in delivery Multiple roles could be covered in 1 scenario
Note on D11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is a unique number of the requirement link to the requirement spreadsheet Each requirement should be linked to the Design and Assessment criteria
Note on E11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each scenario will be linked to Business Processes
Note on G11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: An ID will be displayed if there is an interface linked to a scenario
Note on H11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This field will show the description of the Interface linked
Note on I11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is will indicate if the scenario is required to be Regression Tested (Y/N)
Note on K11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The test scenario description field will outline the objective of the test
Note on L11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What specific data is required for each test scenario
Note on M11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What specific test harness is required for each test scenario
Note on N11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Any other pre-req data which is required to satisfy the test scenario
Note on O11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The field will show any other variance related to the test scenario which needs to be considered
Note on O12: Nicola Farley: no varience in BP so need to check with design
Note on P11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This field will outline what is expected to happen from the test scenario
Note on R11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This field will outline if the evidence has been captured or not Will be a flag of PIT or QT or both
Note on S11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The number of test cases created/related to the test scenario
Note on T11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This field will outline the size and difficulty of the test scenario Will be flagged as S, M & L
Note on U11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will outline the priority of the test scenario Flagged as VH, H, M & L
Note on V11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be the participant system under test What releases we are using
Note on W11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will indicate which system is being simulated

## Test Scenarios OLD (hidden)
Test Scenario ID | Role | Link to Requirement ID | Link to Business Process | Business Process Steps | Interface ID | Interface Description | Regression flag | Test Scenerio Title | Test Scenario Description | Precondition – Data | Precondition Test Harness | Precondition Other | Test variances | Test outcome | Optionality | Test evidence | Number of test cases | Complexity | Priority | Systems under test | Role (simulated)
BP007_001 | LDSO/Registration Services | MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 31 - LDSO - Start Point 35 - LDSO 40 - LDSO 70 - RS 126 - DIP 127 - EES | Internal DB03 MHHS-IF-050 PUB-050 | The purpose of this interface is to provide updates to EES from the Registration Service which are not required to be serviced by any other interface. |  | LDSO disconnects meter point - No meter onsite - Change of status | None Metered - LDSO initiated disconnections of the meter point and then registration services generates an IF message for onward processing. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish the change EES to receive the change |  | 1. No Meter/Supplier Onsite (what data is needed??) | None Metered - LDSO initiated disconnections of the meter point and then registration services generates an IF message for onward processing. |  | QT |  | L | VH | LDSO/Registration Services
BP007_002 | LDSO/Registration Services | MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-137 | BP007 Disconnection | 31 - LDSO - Start Point 35 - LDSO 40 - LDSO 70 - RS 85 - DIP 90 - RS | Internal DB03 MHHS-IF-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | LDSO disconnects meter point - No meter onsite - Message failure | None Metered - LDSO initiated disconnections of the meter point and then registration services generates an IF message for onward processing. Failure message is sent back to registration services to be managed. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection |  | 1. No Meter/Supplier Onsite (what data is needed??) | None Metered - LDSO initiated disconnections of the meter point and then registration services generates an IF message for onward processing. Failure message is sent back to registration services to be managed. |  | QT |  | L | VH | LDSO/Registration Services
BP007_003 | LDSO/Registration Services | MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-020 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 31 - LDSO - Start Point 35 - LDSO 40 - LDSO 70 - RS 85 - DIP 86 - LDSO | Internal DB03 MHHS-IF-009 PUB-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | LDSO disconnects meter point - No meter onsite - LDSO receive disconnection | None Metered - LDSO initiated disconnections of the meter point and then registration services generates an IF message for onward processing. LDSO will receive a disconnection publication via subscription services | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection |  | 1. No Meter/Supplier Onsite (what data is needed??) | None Metered - LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message back to LDSO to disconnect publication via subscription services. |  | QT |  | L | VH | LDSO/Registration Services
BP007_004 | LDSO/Registration Services | MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-020 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-SU-056 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-SU-057 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 31 - LDSO - Start Point 35 - LDSO 40 - LDSO 70 - RS 85 - DIP 95 - Supplier | Internal DB03 MHHS-IF-009 PUB-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | LDSO disconnects meter point - No meter onsite - Supplier receives disconnection | None Metered - LDSO initiated disconnections of the meter point and then registration services generates an IF message for onward processing. (Supplier will receive a disconnection publication via subscription services) | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection Supplier to receive disconnection publication |  | 1. No Meter/Supplier Onsite (what data is needed??) | None Metered - LDSO initiated disconnections of the meter point and then registration services generates an IF message for onward processing. Supplier will receive a disconnection publication via subscription services |  | QT |  | L | VH | LDSO/Registration Services
BP007_005 | LDSO/Registration Services | MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-020 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-EES-016.3 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 31 - LDSO - Start Point 35 - LDSO 40 - LDSO 70 - RS 85 - DIP 87 - ESS | Internal DB03 MHHS-IF-009 PUB-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | LDSO disconnects meter point- No meter onsite - ESS receives disconnection | None Metered - LDSO initiated disconnections of the meter point and then registration services generates an IF message for onward processing. (EES will receive a disconnection publication via subscription services) | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection EES to receive the change |  | 1. No Meter/Supplier Onsite (what data is needed??) | None Metered - LDSO initiated disconnections of the meter point and then registration services generates an IF message for onward processing. (EES will receive a disconnection publication via subscription services) |  | QT |  | L | VH | LDSO/Registration Services
BP007_006 | LDSO/Registration Services | MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 31 - LDSO - Start Point 32 - LDSO 40 - LDSO 70 - RS 126 - DIP 127 - EES | Internal DB03 MHHS-IF-050 PUB-050 | The purpose of this interface is to provide updates to EES from the Registration Service which are not required to be serviced by any other interface. |  | LDSO disconnects meter point - Metered - Change of status | Metered - LDSO initiated disconnections of the meter point and then registration services generates an IF message for onward processing. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish the change EES to receive the change |  | 1. Metered (what data is needed??) | Metered - LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent to DIP to publish change to MPAN/RMP status and for ESS to receive the change |  | QT |  | L | VH | LDSO/Registration Services
BP007_007 | LDSO/Registration Services | MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-137 | BP007 Disconnection | 31 - LDSO - Start Point 32 - LDSO 40 - LDSO 70 - RS 85 - DIP 90 - RS | Internal DB03 MHHS-IF-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | LDSO disconnects meter point - Metered - Message failure | Metered - LDSO initiated disconnections of the meter point and then registration services generates an IF message for onward processing. Failure message is sent back to registration services to be managed. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection |  | 1. Metered (what data is needed??) | Metered - LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. If the publication failed to disconnect in DIP then a failure message is sent back to registartion service. |  | QT |  | L | VH | LDSO/Registration Services
BP007_008 | LDSO/Registration Services | MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-020 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 31 - LDSO - Start Point 32 - LDSO 40 - LDSO 70 - RS 85 - DIP 86 - LDSO | Internal DB03 MHHS-IF-009 PUB-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | LDSO disconnects meter point - Metered - LDSO receive disconnection | Metered - LDSO initiated disconnections of the meter point and then registration services generates an IF message for onward processing. LDSO will receive a disconnection publication via subscription services | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection |  | 1. Metered (what data is needed??) | Metered - LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message back to LDSO to disconnect publication via subscription services. |  | QT |  | L | VH | LDSO/Registration Services
BP007_009 | LDSO/Registration Services | MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-020 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-SU-056 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-SU-057 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 31 - LDSO - Start Point 32 - LDSO 40 - LDSO 70 - RS 85 - DIP 95 - Supplier | Internal DB03 MHHS-IF-009 PUB-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | LDSO disconnects meter point - Metered - Supplier receives disconnection | Metered - LDSO initiated disconnections of the meter point and then registration services generates an IF message for onward processing. (Supplier will receive a disconnection publication via subscription services) | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection Supplier to receive disconnection publication |  | 1. Metered (what data is needed??) | Metered - LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message to the supplier to disconnect publication via subscription services. |  | QT |  | L | VH | LDSO/Registration Services
BP007_010 | LDSO/Registration Services | MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-020 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-EES-016.3 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 31 - LDSO - Start Point 32 - LDSO 40 - LDSO 70 - RS 85 - DIP 87 - ESS | Internal DB03 MHHS-IF-009 PUB-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | LDSO disconnects meter point- Metered - ESS receives disconnection | Metered - LDSO initiated disconnections of the meter point and then registration services generates an IF message for onward processing. (EES will receive a disconnection publication via subscription services) | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection EES to receive the change |  | 1. Metered (what data is needed??) | Metered - LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message to ESS to disconnect publication via subscription services. |  | QT |  | L | VH | LDSO/Registration Services
BP007_011 | LDSO/Registration Services | MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 31 - LDSO - Start Point 30 - LDSO 40 - LDSO 70 - RS 126 - DIP 127 - EES | Internal DB03 MHHS-IF-050 PUB-050 | The purpose of this interface is to provide updates to EES from the Registration Service which are not required to be serviced by any other interface. |  | LDSO disconnects meter point - UMS Only - Change of status | UMS Only - LDSO initiated disconnections of the meter point and then registration services generates an IF message for onward processing. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish the change EES to receive the change |  | 1. UMS Only (what data is needed??) | UMS Only - LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent to DIP to publish change to MPAN/RMP status and for ESS to receive the change |  | QT |  | L | VH | LDSO/Registration Services
BP007_012 | LDSO/Registration Services | MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-137 | BP007 Disconnection | 31 - LDSO - Start Point 30 - LDSO 40 - LDSO 70 - RS 85 - DIP 90 - RS | Internal DB03 MHHS-IF-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | LDSO disconnects meter point - UMS Only - Message failure | UMS Only - LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. If the publication failed to disconnect in DIP then a failure message is sent back to registartion service. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection |  | 1. UMS Only (what data is needed??) | UMS Only - LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. If the publication failed to disconnect in DIP then a failure message is sent back to registartion service. |  | QT |  | L | VH | LDSO/Registration Services
BP007_013 | LDSO/Registration Services | MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-020 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 31 - LDSO - Start Point 30 - LDSO 40 - LDSO 70 - RS 85 - DIP 86 - LDSO | Internal DB03 MHHS-IF-009 PUB-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | LDSO disconnects meter point - UMS Only - LDSO receive disconnection | UMS Only - LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message back to LDSO to disconnect publication via subscription services. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection |  | 1. UMS Only (what data is needed??) | UMS Only - LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message back to LDSO to disconnect publication via subscription services. |  | QT |  | L | VH | LDSO/Registration Services
BP007_014 | LDSO/Registration Services | MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-020 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-SU-056 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-SU-057 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 31 - LDSO - Start Point 30 - LDSO 40 - LDSO 70 - RS 85 - DIP 95 - Supplier | Internal DB03 MHHS-IF-009 PUB-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | LDSO disconnects meter point - UMS Only - Supplier receives disconnection | UMS Only - LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message to the supplier to disconnect publication via subscription services. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection Supplier to receive disconnection publication |  | 1. UMS Only (what data is needed??) | UMS Only - LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message to the supplier to disconnect publication via subscription services. |  | QT |  | L | VH | LDSO/Registration Services
BP007_015 | LDSO/Registration Services | MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-020 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-EES-016.3 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 31 - LDSO - Start Point 30 - LDSO 40 - LDSO 70 - RS 85 - DIP 87 - ESS | Internal DB03 MHHS-IF-009 PUB-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | LDSO disconnects meter point- UMS Only - ESS receives disconnection | UMS Only - LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message to ESS to disconnect publication via subscription services. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection EES to receive the change |  | 1.UMS Only (what data is needed??) | UMS Only - LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message to ESS to disconnect publication via subscription services. |  | QT |  | L | VH | LDSO/Registration Services
BP007_016 | LDSO/UMSO | MHHS-BR-LD-013 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-014 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-MS-038 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 31 - LDSO - Start Point 30 - LDSO 50 - UMSO 51 - UMSO | UMS Only (Email or other Agreed Mechanism) | UMS Only (Email or other Agreed Mechanism) |  | LDSO initiated disconnections - UMS Only - Notify customer of disconnection | UMS Only - LDSO initiated disconnections via UMS only where an email or other agreed mechanism is triggered. UMSO then receive a notification from the customer/supplier or UMSO service to initiate the disconnection. Customer is then notified of the disconnection | Need to confirm | Need to confirm |  | 1. LDSO email notification sent to meter service, received and notified the customer | UMS Only - LDSO initiated disconnections via UMS only where an email or other agreed mechanism is triggered. UMSO then receive a notification from the customer/supplier or UMSO service to initiate the disconnection. Customer is then notified of the disconnection |  | QT |  | L | H | LDSO/UMSO
BP007_017 | LDSO/UMSO/Registration Services | MHHS-BR-LD-013 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-014 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-016 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-MS-038 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 54 - LDSO - Start Point 55 - LDSO 50 - UMSO 30 - LDSO 40 - LDSO 70 - RS 126 - DIP 127 - EES | Internal DB03 MHHS-IF-050 PUB-050 UMS Only | The purpose of this interface is to provide updates to EES from the Registration Service which are not required to be serviced by any other interface. |  | Customer initiated disconnection - Change of status | Customer initiate disconnection via email which is sent to UMSO to start the process. UMSO triggers LDSO to initiate disconnection of the meter point and then interacts with registration services. Message has been sent to DIP to publish change to MPAN/RMP status and for ESS to receive the change | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish the change EES to receive the change |  | 1. Customer initiated disconnection - Change of status | Customer initiate disconnection via email which is sent to UMSO to start the process. UMSO triggers LDSO to initiate disconnection of the meter point and then interacts with registration services. Message has been sent to DIP to publish change to MPAN/RMP status and for ESS to receive the change |  | QT |  | L | VH | LDSO/UMSO/Registration Services
BP007_018 | LDSO/UMSO/Registration Services | MHHS-BR-LD-013 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-014 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-016 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-MS-038 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-137 | BP007 Disconnection | 54 - LDSO - Start Point 55 - LDSO 50 - UMSO 30 - LDSO 40 - LDSO 70 - RS 85 - DIP 90 - RS | Internal DB03 MHHS-IF-009 UMS Only | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | Customer initiated disconnection - UMS Only - Message failure | Customer initiate disconnection via email which is sent to UMSO to start the process. UMSO triggers LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. If the publication failed to disconnect in DIP then a failure message is sent back to registartion service. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection |  | 1. Customer initiated disconnection - UMS Only - Message failure | Customer initiate disconnection via email which is sent to UMSO to start the process. UMSO triggers LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. If the publication failed to disconnect in DIP then a failure message is sent back to registartion service. |  | QT |  | L | VH | LDSO/UMSO/Registration Services
BP007_019 | LDSO/UMSO/Registration Services | MHHS-BR-LD-013 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-014 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-016 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-020 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 54 - LDSO - Start Point 55 - LDSO 50 - UMSO 30 - LDSO 40 - LDSO 70 - RS 85 - DIP 86 - LDSO | Internal DB03 MHHS-IF-009 PUB-009 UMS Only | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | Customer initiated disconnection - UMS Only - LDSO receive disconnection | Customer initiate disconnection via email which is sent to UMSO to start the process. UMSO triggers LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message back to LDSO to disconnect publication via subscription services. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection |  | 1. Customer initiated disconnection - UMS Only - LDSO receive disconnection | Customer initiate disconnection via email which is sent to UMSO to start the process. UMSO triggers LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message back to LDSO to disconnect publication via subscription services. |  | QT |  | L | VH | LDSO/UMSO/Registration Services
BP007_020 | LDSO/UMSO/Registration Services | MHHS-BR-LD-013 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-014 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-016 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-020 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-SU-056 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-SU-057 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 54 - LDSO - Start Point 55 - LDSO 50 - UMSO 30 - LDSO 40 - LDSO 70 - RS 85 - DIP 95 - Supplier | Internal DB03 MHHS-IF-009 PUB-009 UMS Only | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | Customer initiated disconnection - Supplier to receive disconnection | Customer initiate disconnection via email which is sent to UMSO to start the process. UMSO triggers LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message to the supplier to disconnect publication via subscription services. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection Supplier to receive disconnection publication |  | 1. Customer initiated disconnection - Supplier to receive disconnection | Customer initiate disconnection via email which is sent to UMSO to start the process. UMSO triggers LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message to the supplier to disconnect publication via subscription services. |  | QT |  | L | VH | LDSO/UMSO/Registration Services
BP007_021 | LDSO/UMSO/Registration Services | MHHS-BR-LD-013 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-014 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-015 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-016 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-020 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-EES-016.3 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 54 - LDSO - Start Point 55 - LDSO 50 - UMSO 30 - LDSO 40 - LDSO 70 - RS 85 - DIP 87 - ESS | Internal DB03 MHHS-IF-009 PUB-009 UMS Only | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | Customer initiated disconnection - ESS receives disconnection | Customer initiate disconnection via email which is sent to UMSO to start the process. UMSO triggers LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message to ESS to disconnect publication via subscription services. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection EES to receive the change |  | 1. Customer initiated disconnection - ESS receives disconnection | Customer initiate disconnection via email which is sent to UMSO to start the process. UMSO triggers LDSO initiated disconnections of the meter point and then interacts with registration services. Message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message to ESS to disconnect publication via subscription services. |  | QT |  | L | VH | LDSO/UMSO/Registration Services
BP007_022 | LDSO/Registration Services | MHHS-BR-LD-013 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-014 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-016 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-017 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 54 - LDSO - Start Point 55 - LDSO 60 - LDSO 65 - LDSO 70 - RS 126 - DIP 127 - EES | Internal DB03 MHHS-IF-050 PUB-050 | The purpose of this interface is to provide updates to EES from the Registration Service which are not required to be serviced by any other interface. |  | Customer initiated disconnection - Accepted - Change MPAN/RMP Status | Customer initiated disconnections where an email is sent for the disconnection to be requested and once accepted, the meter point will interact with registration services. A message will be sent to DIP to publish change to MPAN/RMP status and for ESS to receive the change | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish the change EES to receive the change |  | 1. Customer initiated disconnection - Accepted - Change MPAN/RMP Status | Customer initiated disconnections where an email is sent for the disconnection to be requested and once accepted, the meter point will interact with registration services. A message will be sent to DIP to publish change to MPAN/RMP status and for ESS to receive the change |  | QT |  | L | VH | LDSO/Registration Services
BP007_023 | LDSO/Registration Services | MHHS-BR-LD-013 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-014 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-016 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-017 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-137 | BP007 Disconnection | 54 - LDSO - Start Point 55 - LDSO 60 - LDSO 65 - LDSO 70 - RS 85 - DIP 90 - RS | Internal DB03 MHHS-IF-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | Customer initiated disconnection - Accepted - Message failure | Customer initiated disconnections where an email is sent for the disconnection to be requested and once accepted, the meter point will interact with registration services. Registration services will interact with DIP to publish the disconnection and if the publication fails to disconnect in DIP then a failure message is sent back to registartion service. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection |  | 1. Customer initiated disconnection - Accepted - Message failure | Customer initiated disconnections where an email is sent for the disconnection to be requested and once accepted, the meter point will interact with registration services. Registration services will interact with DIP to publish the disconnection and if the publication fails to disconnect in DIP then a failure message is sent back to registartion service. |  | QT |  | L | VH | LDSO/Registration Services
BP007_024 | LDSO/Registration Services | MHHS-BR-LD-013 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-014 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-016 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-017 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-020 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 54 - LDSO - Start Point 55 - LDSO 60 - LDSO 65 - LDSO 70 - RS 85 - DIP 86 - LDSO | Internal DB03 MHHS-IF-009 PUB-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | Customer initiated disconnection - Accepted - LDSO receive disconnection | Customer initiated disconnections where an email is sent for the disconnection to be requested and once accepted, the meter point will interact with registration services. A message will been sent from registration services to DIP to publish the disconnection. DIP will then send a message back to LDSO to disconnect publication via subscription services. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection |  | 1. Customer initiated disconnection - Accepted - LDSO receive disconnection | Customer initiated disconnections where an email is sent for the disconnection to be requested and once accepted, the meter point will interact with registration services. A message will been sent from registration services to DIP to publish the disconnection. DIP will then send a message back to LDSO to disconnect publication via subscription services. |  | QT |  | L | VH | LDSO/Registration Services
BP007_025 | LDSO/Registration Services | MHHS-BR-LD-013 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-014 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-016 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-017 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-020 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-SU-056 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-SU-057 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 54 - LDSO - Start Point 55 - LDSO 60 - LDSO 65 - LDSO 70 - RS 85 - DIP 95 - Supplier | Internal DB03 MHHS-IF-009 PUB-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | Customer initiated disconnection - Accepted - Supplier receives disconnection | Customer initiated disconnections where an email is sent for the disconnection to be requested and once accepted, the meter point will interact with registration services. A message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message to the supplier to disconnect publication via subscription services. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection Supplier to receive disconnection publication |  | 1. Customer initiated disconnection - Accepted - Supplier receives disconnection | Customer initiated disconnections where an email is sent for the disconnection to be requested and once accepted, the meter point will interact with registration services. A message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message to the supplier to disconnect publication via subscription services. |  | QT |  | L | VH | LDSO/Registration Services
BP007_026 | LDSO/Registration Services | MHHS-BR-LD-013 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-014 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-016 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-017 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-018 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-020 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-097 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-098 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-099 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-EES-016.3 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 54 - LDSO - Start Point 55 - LDSO 60 - LDSO 65 - LDSO 70 - RS 85 - DIP 87 - ESS | Internal DB03 MHHS-IF-009 PUB-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | Customer initiated disconnection - Accepted - ESS receives disconnection | Customer initiated disconnections where an email is sent for the disconnection to be requested and once accepted, the meter point will interact with registration services. A message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message to ESS to disconnect publication via subscription services. | 1 MPANs required LDSO able to create Internal DB03 | DIP to publish disconnection EES to receive the change |  | 1. Customer initiated disconnection - Accepted - ESS receives disconnection | Customer initiated disconnections where an email is sent for the disconnection to be requested and once accepted, the meter point will interact with registration services. A message has been sent from registration services to DIP to publish the disconnection. DIP will then send a message to ESS to disconnect publication via subscription services. |  | QT |  | L | VH | LDSO/Registration Services
BP007_027 | LDSO | MHHS-BR-LD-013 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-014 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-016 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-017 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 54 - Start Point 55 - LDSO 60 - LDSO 76 - LDSO | N/A | N/A |  | Customer initiated disconnection - rejected - Customer notified of rejection | Customer initiated disconnections where an email is sent for the disconnection to be requested. If rejected, a trigger will be sent to the customer notifying them of the rejection | Need to confirm | Need to confirm |  | 1. Customer initiated disconnection - rejected - Customer notified of rejection | Customer initiated disconnections where an email is sent for the disconnection to be requested. If rejected, a trigger will be sent to the customer notifying them of the rejection |  | QT |  | L | H | LDSO
BP007_028 | LDSO | MHHS-BR-LD-013 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-014 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-016 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-017 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-019 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-SU-055 | BP007 Disconnection | 54 - Start Point 55 - LDSO 60 - LDSO 75 - LDSO 80 - Supplier | D0262 | Need to confirm |  | Customer initiated disconnection - rejected - Supplier manage rejection | Customer initiated disconnections where an email is sent for the disconnection to be requested. If rejected, a trigger will be sent to the supplier to manage the rejection. | 1 MPANs required | Supplier |  | 1. Customer initiated disconnection - rejected - Supplier manage rejection | Customer initiated disconnections where an email is sent for the disconnection to be requested. If rejected, a trigger will be sent to the supplier to manage the rejection. |  | QT |  | L | H | LDSO
BP007_029 | Registration Services | MHHS-BR-RS-100 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-101 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-EES-016.3 | BP007 Disconnection | 125 - RS 130 - DIP 131 - ESS | MHHS-IF-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | Update Registration - Deactivate - ESS | Update to registration is required to deactivate. Registration services will interact with DIP to publish the De-activation notification. A message will then be sent to ESS to De-activate the publication via subsscription service | 1 MPANs required | CSS required to trigger the deactivation request ESS to receive deactivation publication |  | 1. Update Registration - Deactivate - ESS | Update to registration is required to deactivate. LDSO will interact with DIP to publish the De-activation notification. A message will then be sent to ESS to De-activate the publication via subsscription service |  | QT |  | L | H | Registration Services
BP007_030 | Registration Services | MHHS-BR-RS-100 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-101 - Not in scope for LDSO QT BSC Aseessment Criteria Central Settlement | BP007 Disconnection | 125 - RS 130 - DIP 135 - Central Settlement (LSS/MDS) | MHHS-IF-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | Update Registration - Deactivate - Central Settlement | Update to registration is required to deactivate. Registration services will interact with DIP to publish the De-activation notification. A message will then be sent to Central Settlement to De-activate the publication via subsscription service | 1 MPANs required | CSS required to trigger the deactivation request Central Settlement to receive deactivation publication |  | 1. Update Registration - Deactivate - Central Settlement | Update to registration is required to deactivate. LDSO will interact with DIP to publish the De-activation notification. A message will then be sent to Central Settlement to De-activate the publication via subsscription service |  | QT |  | L | H | Registration Services
BP007_031 | LDSO/Registration Services | MHHS-BR-RS-100 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-101 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-020.1 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 125 - RS 130 - DIP 136 - LDSO | MHHS-IF-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | Update Registration - Deactivate - LDSO | Update to registration is required to deactivate. Registration services will interact with DIP to publish the De-activation notification. A message will then be sent to LDSO to De-activate the publication via subsscription service | 1 MPANs required LDSO to receive deactivation publication | CSS required to trigger the deactivation request |  | 1. Update Registration - Deactivate - LDSO | Update to registration is required to deactivate. Registration services will interact with DIP to publish the De-activation notification. A message will then be sent to LDSO to De-activate the publication via subsscription service |  | QT |  | L | H | LDSO/Registration Services
BP007_032 | Registration Services | MHHS-BR-RS-100 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-101 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 125 - RS 130 - DIP 137 - Supplier | MHHS-IF-009 | This interface is used by Registration Service to notify participants that an MPAN has been Disconnected by LDSO and/or terminated by CSS. It is no longer possible to register an MPAN following this point. |  | Update Registration - Deactivate - Supplier | Update to registration is required to deactivate. Registration services will interact with DIP to publish the De-activation notification. A message will then be sent to the Supplier to De-activate the publication via subsscription service | 1 MPANs required | CSS required to trigger the deactivation request Supplier to receive deactivation publication |  | 1. Update Registration - Deactivate - LDSO | Update to registration is required to deactivate. Registration services will interact with DIP to publish the De-activation notification. A message will then be sent to LDSO to De-activate the publication via subsscription service |  | QT |  | L | H | Registration Services
BP007_033 | Registration Services | MHHS-BR-RS-100 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-101 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-102 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-103 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-102.1 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-DS-104 MHHS-BR-DS-105 | BP007 Disconnection | 125 - RS 155 - RS 145 - DIP 140 - DS | MHHS-IF-037 PUB-037 | Notification to a Service Provider that they have been De-Appointed, and no longer have responsibility for the MPAN |  | Update Registration - Deappointment - Data Service | Update to registration is required for deappointment. Registration services will interact with DIP to send notification of deappointment. A message will then be sent from DIP to notify Data service of deappointment | 1 MPANs required | Data Service to receive deappointment |  | 1. Update Registration - Deappointment - Data Service | Update to registration is required for deappointment. Registration services will interact with DIP to send notification of deappointment. A message will then be sent from DIP to notify Data service of deappointment |  | QT |  | L | H | Registration Services
BP007_034 | UMSO/Registration Services | MHHS-BR-RS-100 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-101 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-102 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-103 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-102.1 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-MS-040 | BP007 Disconnection | 125 - RS 155 - RS 145 - DIP 150 - UMSO | MHHS-IF-037 PUB-037 | Notification to a Service Provider that they have been De-Appointed, and no longer have responsibility for the MPAN |  | Update Registration - Deappointment - UMSO | Update to registration is required for deappointment. Registration services will interact with DIP to send notification of deappointment. A message will then be sent from DIP to notify UMSO of deappointment | 1 MPANs required UMSO to receive deappointment |  |  | 1. Update Registration - Deappointment - UMSO | Update to registration is required for deappointment. Registration services will interact with DIP to send notification of deappointment. A message will then be sent from DIP to notify UMSO of deappointment |  | QT |  | L | H | UMSO/Registration Services
BP007_035 | LDSO/Registration Services | MHHS-BR-RS-100 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-101 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-102 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-103 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-102.1 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-LD-021 - Not in scope for LDSO QT BSC Aseessment Criteria | BP007 Disconnection | 125 - RS 155 - RS 145 - DIP 156 - LDSO | MHHS-IF-037 PUB-037 | Notification to a Service Provider that they have been De-Appointed, and no longer have responsibility for the MPAN |  | Update Registration - Deappointment - LDSO | Update to registration is required for deappointment. Registration services will interact with DIP to send notification of deappointment. A message will then be sent from DIP to notify LDSO of deappointment | 1 MPANs required LDSO to receive deappointment |  |  | 1. Update Registration - Deappointment - LDSO | Update to registration is required for deappointment. Registration services will interact with DIP to send notification of deappointment. A message will then be sent from DIP to notify LDSO of deappointment |  | QT |  | L | H | LDSO/Registration Services
BP007_036 | Registration Services | MHHS-BR-RS-100 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-101 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-102 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-103 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-RS-102.1 - Not in scope for LDSO QT BSC Aseessment Criteria MHHS-BR-SU-059 | BP007 Disconnection | 125 - RS 155 - RS 145 - DIP 157 - Supplier | MHHS-IF-037 PUB-037 | Notification to a Service Provider that they have been De-Appointed, and no longer have responsibility for the MPAN |  | Update Registration - Deappointment - Supplier | Update to registration is required for deappointment. Registration services will interact with DIP to send notification of deappointment. A message will then be sent from DIP to notify Supplier of deappointment | 1 MPANs required | Supplier to receive deappointment |  | 1. Update Registration - Deappointment - Supplier | Update to registration is required for deappointment. Registration services will interact with DIP to send notification of deappointment. A message will then be sent from DIP to notify Supplier of deappointment |  | QT |  | L | H | Registration Services
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be a unique ID and created when each scenario is added
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be the participants role in delivery Multiple roles could be covered in 1 scenario
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is a unique number of the requirement link to the requirement spreadsheet Each requirement should be linked to the Design and Assessment criteria
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each scenario will be linked to Business Processes
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: An ID will be displayed if there is an interface linked to a scenario
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This field will show the description of the Interface linked
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is will indicate if the scenario is required to be Regression Tested (Y/N)
Note on J1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The test scenario description field will outline the objective of the test
Note on K1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What specific data is required for each test scenario
Note on L1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What specific test harness is required for each test scenario
Note on M1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Any other pre-req data which is required to satisfy the test scenario
Note on N1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The field will show any other variance related to the test scenario which needs to be considered
Note on N2: Nicola Farley: no varience in BP so need to check with design
Note on N3: Nicola Farley: no varience in BP so need to check with design
Note on N7: Nicola Farley: no varience in BP so need to check with design
Note on N8: Nicola Farley: no varience in BP so need to check with design
Note on N9: Nicola Farley: no varience in BP so need to check with design
Note on N10: Nicola Farley: no varience in BP so need to check with design
Note on N11: Nicola Farley: no varience in BP so need to check with design
Note on N12: Nicola Farley: no varience in BP so need to check with design
Note on N13: Nicola Farley: no varience in BP so need to check with design
Note on N14: Nicola Farley: no varience in BP so need to check with design
Note on N15: Nicola Farley: no varience in BP so need to check with design
Note on N16: Nicola Farley: no varience in BP so need to check with design
Note on N17: Nicola Farley: no varience in BP so need to check with design
Note on O1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This field will outline what is expected to happen from the test scenario
Note on Q1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This field will outline if the evidence has been captured or not Will be a flag of PIT or QT or both
Note on R1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The number of test cases created/related to the test scenario
Note on S1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This field will outline the size and difficulty of the test scenario Will be flagged as S, M & L
Note on T1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will outline the priority of the test scenario Flagged as VH, H, M & L
Note on U1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be the participant system under test What releases we are using
Note on V1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will indicate which system is being simulated

## BP007 Test Scenarios
Test Scenario ID | Role (s) | Theme | Business Process | Functional Category | Test Scenario Title | Test Scenario Description | Boundaries | Test variances (Test Case Variables) | Optionality | Number of test cases | Complexity (Scenarios Size) | Priority | Expleo Comments
TS_BP007_001 | LDSO/Registration Services | Metering Changes | BP007 Disconnection |  | LDSO intitated discconection | LDSO initiates meter disconnection process. Registration services request for a change of MPAN/RMP status in EES (Test Harness). LDSO, EES (Test Harness) and Supplier (Test Harness) will receive notification that disconnection has been updated with the Registration Service | Harness as end point for EES | - MPAN created in error - No active Supplier • Metered • UMS-Only is Unmetered • Customer initiated disconnection - (passing through UMSO double check that this is UMSO and back to LDSO) - Customer requests disconnection - Disconnection Accepted Emergency disconnections |  | 7 | M | L | Should testing start from Step 31 or from Step 70? How do we test Step 32? LDSO may need to disconnect sites in emergency scenarios. Where an LDSO has initiated a disconnection in cases of emergency they must where possible update the Metering Service of the meter removal Systems not in scope • Suppler • EES Disconnect meter point (Step 40) will run through to registration services via Internal DB03 start the Disconnection (Step 70) • Step 126 (DIP) Publish Change MPAN/RMP Status (MHHS-IF-050) TO • Step 127 (EES) Receive Change to MPAN/RMP Status (PUB-050) (END) All Business process are not in scope for LDSO QT BSC Aseessment Criteria
TS_BP007_002 | LDSO/Registration Services | Metering Changes | BP007 Disconnection |  | LDSO disconnects meter point - Receive Disconnection Publication via subscription service | LDSO initiates meter disconnection process to update the registrations system. LDSO receives notification that the disconnection has been updated with Registration Service | Harness as end point for a Supplier and end point for EES | • Non-Metered - Manage Failure message (validation) - Notification received in LDSO - MPAN created in error - No active Supplier • Metered - Manage Failure message (validation) - Notification received in LDSO • UMS-Only - Manage Failure message (validation) - Notification received in LDSO • Customer initiated disconnection - (passing through UMSO and back to LDSO) - Customer requests disconnection - Disconnection Accepted Failure scenarios |  | 5 | M | L | Should testing start from Step 31 or from Step 70? How do we test Step 32? LDSO may need to disconnect sites in emergency scenarios. Where an LDSO has initiated a disconnection in cases of emergency they must where possible update the Metering Service of the meter removal Disconnect meter point (Step 40) will run through to registration services via Internal DB03 start the Disconnection (Step 70) • Step 85 - (DIP) DIP will publish the disconnection notification (MHHS-IF-009) but will fail validation TO • Step 90 - Registration Service will receive a failed message from DIP where the Registration Notification of Disconnection has failed validation (END) All Business process are not in scope for LDSO QT BSC Aseessment Criteria apart from MHHS-BR-RS-137
TS_BP007_003 | LDSO/UMSO | Metering Changes | BP007 Disconnection |  | UMSO notify customer of disconnection | UMSO have received a request from LDSO to initiate disconnection via an agreed communication method (email). UMSO will then notify the customer of the disconnection ( to be reviewed and possibly inlcuded in the scenarios 2) | N/A | • UMS-Only |  | 1 | M | L | How is step 30 tested? What has triggered step 30 to initiate disconnection? All Business process are not in scope for LDSO QT BSC Aseessment Criteria
TS_BP007_004 | LDSO | Metering Changes | BP007 Disconnection |  | Customer requests disconnection - Disconnection Rejected - Notify customer | Customer requests for the MPAN to be disconnected via an agreed communication method (email). LDSO will receive the request to disconnect the meter point from customers. If the disconnection process has been rejected from LDSO, LDSO will inform the customer via the agreed communication method that the ( how to do that) disconnection will not be actioned. | Harness as end point for a Supplier | • Customer initiated - Customer notified of rejection - Manage customers disconnection request |  | 2 | M | L | All Business process are not in scope for LDSO QT BSC Aseessment Criteria
TS_BP007_005 | LDSO/Registration Services | Metering Changes | BP007 Disconnection |  | Update Registration - Deactivate | Registration services will receive a CSS2860 to inform them of an MPAN deactivation. LDSO will then receive notification that the Registration has been De-activated | Harness as start point for CSS Harness as end point for Central Settlement, ESS & Supplier | • Update registration - publish deactivation notification |  | 1 | M | L | All Business process are not in scope for LDSO QT BSC Aseessment Criteria
TS_BP007_006 | LDSO/UMSO/Registration Services | Metering Changes | BP007 Disconnection |  | Update Registration - De-appoint services - Deactivate | Registration services will receive a CSS2860 to inform them of an MPAN deactivation. Registration Service will send out the de-appointment notification to the service providers. UMSO and LDSO will receive notification that all appointed services have been de-appointed | Harness as start point for CSS Harness as end point for Central Settlement, ESS & Supplier | • Update registration - LDSO receives notification to de-appoint - UMSO receives notification to de-appoint |  | 2 | M | L | All Business process are not in scope for LDSO QT BSC Aseessment Criteria
[9 empty] | Total TC | 23
TS_BP07_01 | LDSO/UMSO/Registration Services | Metering Changes | BP007 Disconnection |  | LDSO Initiated Disconnection | In this scenario a LDSO is initiating, either for a UMS, metered or non-metered site, a disconnection of a metering point and issuing DB03 messages to registration services. Registration services generating Notification of LDSO Disconnection / CSS De-Registration and ESS Updates messages and this being published and received by LDSO, ESS & Supplier. For UMS site, this scenario would also include UMSO initiating disconnection and informing customer. | Start point The starting point for this scenario would be LDSO initiating disconnection. End point The end point this for scenario would be (PUB-09) LDSO Disconnection / CSS De-Registration received by LDSO End point for out of scope roles (PUB-050) ESS update being received by ESS (Test Harness) (PUB-09) LDSO Disconnection / CSS De-Registration received by ESS & Supplier (Test Harness) | Where this disconnection is initiated by LDSO for UMS site. This variance would cover LDSO/UMSO/Registration Services Where this disconnection is initiated by LDSO for metered site. This variance would cover LDSO/ Registration Services Where this disconnection is initiated by LDSO and there is no meter on site. This variance would cover LDSO/Registration Services Where this disconnection is initiated by LDSO and registration Service has received a failed message where the Registration Notification of Disconnection has failed DIP validation. | If LDSO has opted out of receiving PUB-009, they do not need to run this test via DIP but should provide evidence of receiving this information via alternative mechanism | 4 | M
TS_BP07_02 | LDSO/UMSO/Registration Services | Metering Changes | BP007 Disconnection |  | Supplier and Customer Initiated Disconnection | In this scenario a Supplier or a Customer is initiating, either for a UMS or metered, a disconnection of a metering point to LDSO. LDSO either accepting issuing DB03 messages to registration services or confirming rejection back to the supplier or customer. If accepted, Registration services generating Notification of LDSO Disconnection / CSS De-Registration and ESS Updates messages and this being published and received by LDSO, ESS & Supplier. For UMS site, this scenario would also include UMSO initiating disconnection and informing customer. | Start point The starting point for this scenario would be LDSO receiving initiating disconnection request from either a supplier or a customer. End point The end point this for scenario would be (PUB-09) LDSO Disconnection / CSS De-Registration received by LDSO End point for out of scope roles (PUB-050) ESS update being received by ESS (Test Harness) (PUB-09) LDSO Disconnection / CSS De-Registration received by ESS & Supplier (Test Harness) | Where this disconnection is initiated by customer for UMS site and is accepted by LDSO. This variance would cover LDSO/UMSO/Registration Services Where this disconnection is initiated by customer for UMS site and is rejected by LDSO. This variance would cover LDSO/UMSO/Registration Services Where this disconnection is initiated by customer for metered site and is accepted by LDSO. This variance would cover LDSO/ Registration Services. Where this disconnection is initiated by customer for metered site and is rejected by LDSO. This variance would cover LDSO/ Registration Services. Where this disconnection is initiated by as supplier for UMS site and is accepted by LDSO. This variance would cover LDSO/UMSO/Registration Services. Where this disconnection is initiated by supplier for UMS site and is rejected by LDSO. This variance would cover LDSO/UMSO/Registration Services Where this disconnection is initiated by supplier for metered site and is accepted by LDSO. This variance would cover LDSO/ Registration Services. Where this disconnection is initiated by supplier for metered site and is rejected by LDSO. This variance would cover LDSO/ Registration Services. Where this disconnection is initiated by either customer or a supplier and registration Service has received a failed message where the Registration Notification of Disconnection has failed DIP validation. | If LDSO has opted out of receiving PUB-009, they do not need to run this test via DIP but should provide evidence of receiving this information via alternative mechanism | 9 | M
TS_BP07_03 | LDSO/UMSO/Registration Services | Metering Changes | BP007 Disconnection |  | Registration Services sending Notification of LDSO Disconnection / CSS De-Registration and Notification of De-Appointment. | In this scenario a registration services is updating the MPAN is deactivated and sending a Notification of LDSO Disconnection / CSS De-Registration and Notification of De-Appointment. LDSO and UMSO is receiving a Notification of De-Appointment. | Start point The start point of this scenario is registration Services updating that an MPAN is deactivated. The CSS message CSS2860 will not be stubbed by programme provided test harnesses. LDSO may need to simulate this themselves. The end point this for scenario would be (PUB-37) Notification of De-Appointment received by LDSO End point for out of scope PUB-37) Notification of De-Appointment received by Data Service, Supplier and metering services (test Harness) (PUB-09) LDSO Disconnection / CSS De-Registration received by ESS (Test Harness)& Central Settlement Systems. |  | If LDSO has opted out of receiving PUB-037, they do not need to run this test via DIP but should provide evidence of receiving this information via alternative mechanism | 2 | L
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be a unique ID and created when each scenario is added
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will be the participants role in delivery Multiple roles could be covered in 1 scenario
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Each scenario will be linked to Business Processes
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The test scenario description field will outline the objective of the test
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The field will show any other variance related to the test scenario which needs to be considered
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The number of test cases created/related to the test scenario
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This field will outline the size and difficulty of the test scenario Will be flagged as S, M & L
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will outline the priority of the test scenario Flagged as VH, H, M & L