## Outline Plan
Outline Level | WBS | Tier | Milestone ID | Approving Governance Forum | Artefact ID | Task Name | % Complete | Start | Finish | Duration | Baseline Start | Baseline Finish | Start Variance | Finish Variance | Duration Variance | Responsible | M/S Change Status | Update Version | Active | Resource Names | Notes | Resource Names2 | Notes3
1 | 1 |  |  |  |  | PROGRAMME PLAN. | 56% | 31/10/22 | 23/12/27 | 1344 days? | 31/10/22 | 23/12/27 | 0 days | 0 days | 149 days? | N/A |  | 5 | Yes
2 | 1.1 |  |  |  |  | MHHS Programme Start | 100% | 31/10/22 | 31/10/22 | 0 days | 31/10/22 | 31/10/22 | 0 days | -1 day | 0 days | N/A |  | 5.7 | Yes
2 | 1.2 |  |  |  |  | PROGRAMME MANAGEMENT | 44% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
3 | 1.2.1 |  |  |  |  | Programme Management | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.2.1.1 |  |  |  |  | Sprint-based prioritisation planning and execution | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.1.2 |  |  |  |  | Programme governance secretariat | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.1.3 |  |  |  |  | RAID management and reporting | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.1.4 |  |  |  |  | Tracking against Programme outcomes and KPIs | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.1.5 |  |  |  |  | Change control and reporting | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.1.6 |  |  |  |  | Ongoing identification of lessons learned relating to the PMO and implementation of improvements | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
3 | 1.2.2 |  |  |  |  | Programme Internal Assurance Reviews | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.2.2.1 |  |  |  |  | Programme Internal Assurance Reviews | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
3 | 1.2.3 |  |  |  |  | Engagement with PPs | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.2.3.1 |  |  |  |  | Ongoing PP liaison activities | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.2.3.2 |  |  |  |  | Milestone and Control Point objective setting | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.2.3.3 |  |  |  |  | Reporting | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.2.3.4 |  |  |  |  | PP Engagement Events | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.2.3.4.1 |  |  |  |  | Bilateral meetings | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
5 | 1.2.3.4.2 |  |  |  |  | Monthly webinars | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
5 | 1.2.3.4.3 |  |  |  |  | Open days | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.2.3.5 |  |  |  |  | PP Communications | 43% | 31/10/22 | 30/12/26 | 1088 days | 31/10/22 | 30/12/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.2.3.5.1 |  |  |  |  | The Clock updates (weekly) | 43% | 31/10/22 | 30/12/26 | 1088 days | 31/10/22 | 30/12/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
5 | 1.2.3.5.2 |  |  |  |  | Maintain and update content on public-facing Portal (and ongoing feedback reviews to identify and implement Portal improvements) | 43% | 31/10/22 | 30/12/26 | 1088 days | 31/10/22 | 30/12/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
3 | 1.2.4 |  |  |  |  | Code Change Support / Other Programme Alignment | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.2.4.1 |  |  |  |  | Support DCC/BEIS on SEC change | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.4.2 |  |  |  |  | Support on Smart Meters Act changes | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.4.3 |  |  |  |  | Support DCC/RECCo on CSS change | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.4.4 |  |  |  |  | Support Elexon on BSC change | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.4.5 |  |  |  |  | Support code change inside & outside CCIAG | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.4.6 |  |  |  |  | Support code change inside & outside CCAG | 43% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
3 | 1.2.5 |  |  |  |  | Programme Replan Baseline | 100% | 31/10/22 | 14/06/23 | 163 days | 31/10/22 | 14/06/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.2.5.1 |  |  |  |  | Round 3 consultation preparation | 100% | 31/10/22 | 13/12/22 | 32 days | 31/10/22 | 13/12/22 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.2 |  |  |  |  | PSG decision to launch Round 3 consultation | 100% | 07/12/22 | 07/12/22 | 0 days | 07/12/22 | 07/12/22 | 0 days | -1 day | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.3 |  |  |  |  | Round 3 consultation (incl. walkthroughs and Q&A) | 100% | 14/12/22 | 31/01/23 | 35 days | 14/12/22 | 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.2.5.4 |  |  |  |  | Review and uplift of foundational testing documents to align with replan approach | 100% | 14/12/22 | 20/04/23 | 92 days | 14/12/22 | 20/04/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
4 | 1.2.5.5 |  |  |  |  | Round 3 consultation responses analysis (incl. identification of SIT volunteers) | 100% | 01/02/23 | 14/02/23 | 10 days | 01/02/23 | 14/02/23 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.6 |  |  |  |  | Replan re-drafting and supporting artefact updates (incl. engagement with Ofgem) | 100% | 15/02/23 | 22/03/23 | 26 days | 15/02/23 | 22/03/23 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.7 |  |  |  |  | Draft Replan Change Request | 100% | 15/02/23 | 29/03/23 | 31 days | 15/02/23 | 29/03/23 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.8 |  |  |  |  | PSG decision to issue CR for industry impact assessment | 100% | 05/04/23 | 05/04/23 | 0 days | 05/04/23 | 05/04/23 | 1 day | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.9 |  |  |  |  | Industry impact assessment | 100% | 06/04/23 | 19/04/23 | 10 days | 06/04/23 | 19/04/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.2.5.10 |  |  |  |  | Replan playbacks (to assist PPs in impact assessment) | 100% | 11/04/23 | 17/04/23 | 5 days | 11/04/23 | 17/04/23 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.5.11 |  |  |  |  | Industry impact assessment responses analysis | 100% | 20/04/23 | 26/04/23 | 5 days | 20/04/23 | 26/04/23 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
4 | 1.2.5.12 |  |  |  |  | Extraordinary PSG decision to agree baseline recommendation | 100% | 03/05/23 | 03/05/23 | 0 days | 03/05/23 | 03/05/23 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.2.5.13 |  |  |  |  | Programme Replan playbacks and drop-in sessions | 100% | 08/06/23 | 14/06/23 | 5 days | 08/06/23 | 14/06/23 | 0 days | 0 days | 0 days | PMO |  | 5 | Yes
2 | 1.3 |  |  | DAG |  | DESIGN, BUILD & TEST (PIT) | 79% | 31/10/22 | 05/07/27 | 1221 days? | 31/10/22 | 05/07/27 | 0 days | 0 days | 120 days? | N/A |  |  | Yes
3 | 1.3.1 |  |  |  |  | Design Baseline & Enduring PP Support | 71% | 31/10/22 | 18/01/27 | 1101 days | 31/10/22 | 18/01/27 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.3.1.1 | T1 | T1-DB-1000 | PSG | MHHS-ART001 | Physical design baselined (M5) | 100% | 31/10/22 | 31/10/22 | 0 days | 31/10/22 | 31/10/22 | 0 days | -1 day | 0 days | SRO Design |  | 5 | Yes
4 | 1.3.1.2 |  |  |  |  | M5 Design Work-Off Plan Implementation & Approval | 100% | 31/10/22 | 16/02/23 | 79 days | 31/10/22 | 16/02/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.1.2.1 |  |  |  |  | Implementation of M5 design Work-Off Plan | 100% | 31/10/22 | 09/02/23 | 74 days | 31/10/22 | 09/02/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.2.2 | T3 | T3-DB-0014 | DAG |  | M5 design Work-Off Plan completion approved | 100% | 16/02/23 | 16/02/23 | 0 days | 16/02/23 | 16/02/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.1.3 |  |  |  |  | Enduring PP Design Support | 100% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.1.3.1 |  |  |  |  | Design playbacks and drop-in sessions | 100% | 31/10/22 | 30/12/22 | 45 days | 31/10/22 | 30/12/22 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.3.2 |  |  |  |  | Support participants on E2E MHHS Design | 100% | 31/10/22 | 31/12/26 | 1089 days | 31/10/22 | 31/12/26 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.3.3 |  |  |  |  | DIP Onboarding Support | 100% | 14/11/22 | 17/02/23 | 70 days | 14/11/22 | 17/02/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.3.4 |  |  |  |  | iServer Launch | 100% | 16/02/23 | 16/02/23 | 0 days | 16/02/23 | 16/02/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.1.4 |  |  |  |  | Establish Design Change Management Processes | 36% | 31/10/22 | 18/01/27 | 1101 days | 31/10/22 | 18/01/27 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.1.4.1 |  |  |  |  | Internal review of internal change management processes | 100% | 31/10/22 | 16/12/22 | 35 days | 31/10/22 | 16/12/22 | 0 days | 0 days | 0 days | SRO |  | 5 | Yes
5 | 1.3.1.4.2 |  |  |  |  | SRO approval of internal change management processes | 100% | 16/12/22 | 16/12/22 | 0 days | 16/12/22 | 16/12/22 | 1 day | 0 days | 0 days | SRO |  | 5 | Yes
5 | 1.3.1.4.3 |  |  |  |  | Change Process Webinar | 100% | 16/01/23 | 16/01/23 | 0 days | 16/01/23 | 16/01/23 | 0 days | -1 day | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.4.4 | T3 | T3-DB-0016 | DAG |  | Enduring change management process approved | 100% | 16/02/23 | 16/02/23 | 0 days | 16/02/23 | 16/02/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.4.5 |  |  |  |  | Maintain E2E MHHS Design (post-M5 design change management processes operational) | 34% | 17/02/23 | 18/01/27 | 1022 days | 17/02/23 | 18/01/27 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.1.5 |  |  |  |  | Design Authority Mobilisation | 100% | 14/12/22 | 23/01/23 | 29 days | 14/12/22 | 23/01/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.1.5.1 | T3 | T3-DB-0010 | DAG |  | Design Authority ToR approved | 100% | 14/12/22 | 14/12/22 | 0 days | 14/12/22 | 14/12/22 | 0 days | -1 day | 0 days | SI Design |  | 5 | Yes
5 | 1.3.1.5.2 |  |  |  |  | Inaugural Design Authority | 100% | 23/01/23 | 23/01/23 | 0 days | 23/01/23 | 23/01/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.1.6 |  |  |  |  | Network Operation Services Adaptor Procurement | 100% | 23/05/23 | 23/05/23 | 0 days | 23/05/23 | 23/05/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.1.6.1 | T3 | T3-DB-0020 | DAG |  | All SIT LDSOs have procured their adapter providers | 100% | 23/05/23 | 23/05/23 | 0 days | 23/05/23 | 23/05/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
3 | 1.3.2 |  |  |  |  | PP Mobilisation | 100% | 31/10/22 | 31/01/23 | 67 days | 31/10/22 | 31/01/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.3.2.1 |  |  |  |  | Set up governance | 100% | 31/10/22 | 31/01/23 | 67 days | 31/10/22 | 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.3.2.2 |  |  |  |  | Set up reporting | 100% | 31/10/22 | 31/01/23 | 67 days | 31/10/22 | 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.3.2.3 |  |  |  |  | Obtain funding | 100% | 31/10/22 | 31/01/23 | 67 days | 31/10/22 | 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.3.2.4 |  |  |  |  | Earmark resources | 100% | 31/10/22 | 31/01/23 | 67 days | 31/10/22 | 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.3.2.5 |  |  |  |  | Mobilise initial team | 100% | 31/10/22 | 31/01/23 | 67 days | 31/10/22 | 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
3 | 1.3.3 |  |  |  |  | PIT Stub Specification and Delivery | 100% | 31/10/22 | 28/06/24 | 435 days | 31/10/22 | 28/06/24 | 0 days | 0 days | 5 days | N/A |  | 5 | Yes
4 | 1.3.3.1 |  |  |  |  | DIP Simulator | 100% | 31/10/22 | 29/03/23 | 108 days | 31/10/22 | 29/03/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.3.1.1 |  |  |  |  | Build & Test | 100% | 31/10/22 | 10/03/23 | 95 days | 31/10/22 | 10/03/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
5 | 1.3.3.1.2 |  |  |  |  | UAT | 100% | 14/11/22 | 10/03/23 | 85 days | 14/11/22 | 10/03/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.3.3.1.3 |  |  |  |  | Beta test | 100% | 31/10/22 | 10/03/23 | 95 days | 31/10/22 | 10/03/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.3.3.1.4 |  |  |  |  | Prepare for release | 100% | 06/03/23 | 29/03/23 | 18 days | 06/03/23 | 29/03/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
5 | 1.3.3.1.5 | T3 | T3-DB-0018 | SITAG |  | DIP Simulator released | 100% | 29/03/23 | 29/03/23 | 0 days | 29/03/23 | 29/03/23 | 1 day | 0 days | 0 days | SI DevOps |  | 5 | Yes
4 | 1.3.3.2 |  |  |  |  | DIP Simulator Uplifts | 100% | 06/07/23 | 28/06/24 | 257 days | 06/07/23 | 28/06/24 | 0 days | 0 days | 5 days | N/A |  | 5.1 | Yes
5 | 1.3.3.2.1 |  |  |  |  | DIP Simulator uplifted to align with design releases - design/build/test | 100% | 06/07/23 | 11/08/23 | 27 days | 06/07/23 | 11/08/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5.1 | Yes
5 | 1.3.3.2.2 | T3 | T3-DB-0035 | SITAG |  | DIP Simulator uplifted to align with Interim Release 2 | 100% | 11/08/23 | 11/08/23 | 0 days | 11/08/23 | 11/08/23 | 1 day | 0 days | 0 days | SI DevOps |  | 5.1 | Yes
5 | 1.3.3.2.3 |  |  |  |  | DIP Simulator uplifted to align with design releases - design/build/test | 100% | 09/10/23 | 03/11/23 | 20 days | 09/10/23 | 03/11/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5.3 | Yes
5 | 1.3.3.2.4 | T3 | T3-DB-0039 | SITAG |  | DIP Simulator uplifted to align with Interim Release 5 | 100% | 03/11/23 | 03/11/23 | 0 days | 03/11/23 | 03/11/23 | 1 day | 0 days | 0 days | SI DevOps |  | 5.11 | Yes
5 | 1.3.3.2.5 |  |  |  |  | DIP Simulator uplifted to align with design releases - design/build/test | 100% | 01/02/24 | 22/03/24 | 37 days | 01/02/24 | 22/03/24 | 0 days | 0 days | 0 days | SI DevOps |  | 5.14 | Yes
5 | 1.3.3.2.6 | T3 | T3-DB-0182 | SITAG |  | DIP Simulator uplifted to align with Interim Release 7 | 100% | 22/03/24 | 22/03/24 | 0 days | 22/03/24 | 22/03/24 | 1 day | 0 days | 0 days | SI DevOps |  | 5.14 | Yes
5 | 1.3.3.2.7 |  |  |  |  | DIP Simulator uplifted to align with design releases - design/build/test | 100% | 04/04/24 | 21/06/24 | 57 days | 04/04/24 | 21/06/24 | 0 days | 0 days | 0 days | SI DevOps |  | 5.14 | Yes
5 | 1.3.3.2.8 | T3 | T3-DB-0183 | SITAG |  | DIP Simulator uplifted to align with Interim Release 8 | 100% | 28/06/24 | 28/06/24 | 0 days | 28/06/24 | 28/06/24 | 1 day | 0 days | 0 days | SI DevOps |  | 5.28 | Yes
4 | 1.3.3.3 |  |  |  |  | Data Generator | 100% | 01/12/22 | 31/05/23 | 130 days | 01/12/22 | 31/05/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.3.3.1 |  |  |  |  | Design | 100% | 01/12/22 | 21/12/22 | 15 days | 01/12/22 | 21/12/22 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
5 | 1.3.3.3.2 |  |  |  |  | Build & Test | 100% | 16/02/23 | 26/04/23 | 50 days | 16/02/23 | 26/04/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
5 | 1.3.3.3.3 |  |  |  |  | UAT | 100% | 27/04/23 | 10/05/23 | 10 days | 27/04/23 | 10/05/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.3.3.3.4 |  |  |  |  | Beta test | 100% | 30/03/23 | 31/05/23 | 45 days | 30/03/23 | 31/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.3.3.3.5 |  |  |  |  | Prepare for release | 100% | 27/04/23 | 30/05/23 | 24 days | 27/04/23 | 30/05/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
5 | 1.3.3.3.6 | T3 | T3-DB-0022 | SITAG |  | Data Generator released | 100% | 31/05/23 | 31/05/23 | 0 days | 31/05/23 | 31/05/23 | 1 day | 0 days | 0 days | SI DevOps |  | 5 | Yes
3 | 1.3.4 |  |  | DAG |  | Design Artefact Releases | 97% | 22/02/23 | 24/01/25 | 503 days? | 22/02/23 | 13/11/24 | 0 days | 52 days | 105 days? | N/A |  | 5 | Yes
4 | 1.3.4.1 |  |  |  |  | Interim release 1 | 100% | 22/02/23 | 12/06/23 | 79 days | 22/02/23 | 12/06/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.4.1.1 |  |  |  |  | Prioritise DINs and CR | 100% | 22/02/23 | 22/02/23 | 1 day | 22/02/23 | 22/02/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.4.1.2 |  |  |  |  | Industry input session | 100% | 23/02/23 | 03/03/23 | 7 days | 23/02/23 | 03/03/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.4.1.2.1 |  |  |  |  | Raise a CR covering prioritized assessment cluster | 100% | 23/02/23 | 23/02/23 | 1 day | 23/02/23 | 23/02/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.2.2 |  |  |  |  | Organize Industry Input session to go through significant items to reach consensus | 100% | 23/02/23 | 23/02/23 | 1 day | 23/02/23 | 23/02/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.2.3 |  |  |  |  | Conduct Meeting | 100% | 03/03/23 | 03/03/23 | 1 day | 03/03/23 | 03/03/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.4.1.3 |  |  |  |  | Update baselined artefacts | 100% | 24/03/23 | 06/04/23 | 10 days | 24/03/23 | 06/04/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.4.1.4 |  |  |  |  | Participant review and impact assess changes | 100% | 14/04/23 | 09/05/23 | 18 days | 14/04/23 | 09/05/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.4.1.4.1 |  |  |  |  | Issue Redline Version of documents | 100% | 14/04/23 | 14/04/23 | 1 day | 14/04/23 | 14/04/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.4.2 |  |  |  |  | Participants provide review comments to common log | 100% | 17/04/23 | 09/05/23 | 17 days | 17/04/23 | 09/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.3.4.1.5 |  |  |  |  | Assurance review | 100% | 10/05/23 | 05/06/23 | 19 days | 10/05/23 | 05/06/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.4.1.5.1 |  |  |  |  | SI Design Review and Respond to Comments | 100% | 10/05/23 | 16/05/23 | 5 days | 10/05/23 | 16/05/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.5.2 |  |  |  |  | Prep for Assurance Review Meeting | 100% | 17/05/23 | 25/05/23 | 7 days | 17/05/23 | 25/05/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.5.3 |  |  |  |  | Conduct Assurance Review Meeting | 100% | 26/05/23 | 26/05/23 | 1 day | 26/05/23 | 26/05/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.4.1.5.4 |  |  |  |  | Update Artefacts following Assurance Review | 100% | 29/05/23 | 05/06/23 | 6 days | 29/05/23 | 05/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.4.1.6 |  |  |  |  | PSG Approval of interim release plan | 100% | 08/06/23 | 08/06/23 | 1 day | 08/06/23 | 08/06/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
5 | 1.3.4.1.7 |  |  |  |  | Publish updated baselined artefacts | 100% | 06/06/23 | 12/06/23 | 0 days | 06/06/23 | 12/06/23 | 0 days | 0 days | -5 days | SI Design |  | 5 | Yes
5 | 1.3.4.1.8 | T3 | T3-DB-0095 | DAG |  | Interim release 1 Go live | 100% | 12/06/23 | 12/06/23 | 0 days | 12/06/23 | 12/06/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.4.2 |  |  |  |  | Interim release 2 | 100% | 30/05/23 | 05/07/23 | 27 days | 30/05/23 | 05/07/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.4.2.1 |  |  |  |  | Update baselined artefacts | 100% | 30/05/23 | 05/07/23 | 27 days | 30/05/23 | 05/07/23 | 0 days | 0 days | 0 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.2.2 | T3 | T3-DB-0096 | DAG |  | Interim release 2 Go live | 100% | 05/07/23 | 05/07/23 | 0 days | 05/07/23 | 05/07/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.4.3 |  |  |  |  | Interim release 3 | 100% | 15/06/23 | 02/08/23 | 35 days | 15/06/23 | 02/08/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.4.3.1 |  |  |  |  | Update baselined artefacts | 100% | 15/06/23 | 02/08/23 | 35 days | 15/06/23 | 02/08/23 | 0 days | 0 days | 0 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.3.2 | T3 | T3-DB-0097 | DAG |  | Interim release 3 Go live | 100% | 02/08/23 | 02/08/23 | 0 days | 02/08/23 | 02/08/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.4.4 |  |  |  |  | Interim release 4 | 100% | 12/07/23 | 30/08/23 | 36 days | 12/07/23 | 30/08/23 | 0 days | 0 days | 0 days | N/A |  | 5.1 | Yes
5 | 1.3.4.4.1 |  |  |  |  | Update baselined artefacts | 100% | 12/07/23 | 30/08/23 | 36 days | 12/07/23 | 30/08/23 | 0 days | 0 days | 0 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.4.2 | T3 | T3-DB-0081 | DAG |  | Interim release 4 Go live | 100% | 30/08/23 | 30/08/23 | 0 days | 30/08/23 | 30/08/23 | 1 day | 0 days | 0 days | SI Design |  | 5.1 | Yes
4 | 1.3.4.5 |  |  |  |  | Interim release 5 | 100% | 17/08/23 | 08/03/24 | 147 days | 17/08/23 | 08/03/24 | 0 days | 0 days | 0 days | N/A |  | 5.1 | Yes
5 | 1.3.4.5.1 |  |  |  |  | Update baselined artefacts | 100% | 17/08/23 | 04/10/23 | 35 days | 17/08/23 | 04/10/23 | 0 days | 0 days | 0 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.5.2 | T3 | T3-DB-0083 | DAG |  | Interim release 5 Go live | 100% | 04/10/23 | 04/10/23 | 0 days | 04/10/23 | 04/10/23 | 1 day | 0 days | 0 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.5.3 |  |  |  |  | Interim Release 5 Deployed to SIT | 100% | 26/02/24 | 08/03/24 | 10 days | 26/02/24 | 08/03/24 | 0 days | 0 days | 0 days | SI Testing |  | 5.16 | Yes
4 | 1.3.4.6 |  |  |  |  | Interim release 6 | 100% | 14/09/23 | 07/06/24 | 192 days | 14/09/23 | 07/06/24 | 0 days | 0 days | 0 days | N/A |  | 5.1 | Yes
5 | 1.3.4.6.1 |  |  |  |  | Update baselined artefacts | 100% | 14/09/23 | 01/11/23 | 35 days | 14/09/23 | 01/11/23 | 0 days | 0 days | 3 days | SI Design |  | 5.1 | Yes
5 | 1.3.4.6.2 | T3 | T3-DB-0085 | DAG |  | Interim release 6 Go live | 100% | 01/11/23 | 01/11/23 | 0 days | 01/11/23 | 01/11/23 | 1 day | 0 days | 0 days | SI Design |  | 5.11 | Yes
5 | 1.3.4.6.3 |  |  |  |  | Interim Release 6 Deployed to SIT | 100% | 27/05/24 | 07/06/24 | 10 days | 27/05/24 | 07/06/24 | 0 days | 0 days | 0 days | SI Testing |  | 5.16 | Yes
4 | 1.3.4.7 |  |  |  |  | Interim release 7 | 100% | 18/10/23 | 07/06/24 | 168 days | 18/10/23 | 07/06/24 | 0 days | 0 days | 0 days | N/A |  | 5.5 | Yes
5 | 1.3.4.7.1 |  |  |  |  | Update baselined artefacts | 100% | 18/10/23 | 31/01/24 | 76 days | 18/10/23 | 31/01/24 | 0 days | 0 days | 0 days | SI Design |  | 5.5 | Yes
5 | 1.3.4.7.2 | T3 | T3-DB-0098 | DAG |  | Interim release 7 Go live | 100% | 31/01/24 | 31/01/24 | 0 days | 31/01/24 | 31/01/24 | 1 day | 0 days | 0 days | SI Design |  | 5.14 | Yes
5 | 1.3.4.7.3 |  |  |  |  | Interim Release 7 Deployed to SIT | 100% | 27/05/24 | 07/06/24 | 10 days | 27/05/24 | 07/06/24 | 0 days | 0 days | 0 days | SI Testing |  | 5.16 | Yes
4 | 1.3.4.8 |  |  | DAG |  | Interim release 8 | 84% | 14/02/24 | 24/01/25 | 248 days? | 14/02/24 | 13/11/24 | 0 days | 52 days | 105 days? | N/A |  | 5.5 | Yes
5 | 1.3.4.8.1 |  |  |  |  | Update baselined artefacts | 100% | 14/02/24 | 03/04/24 | 36 days | 14/02/24 | 03/04/24 | 0 days | 0 days | 0 days | SI Design |  | 5.5 | Yes
5 | 1.3.4.8.2 | T3 | T3-DB-0099 | DAG |  | Interim release 8 Go live | 100% | 03/04/24 | 03/04/24 | 0 days | 03/04/24 | 03/04/24 | 1 day | 0 days | 0 days | SI Design |  | 5.14 | Yes
5 | 1.3.4.8.3 |  |  |  |  | Interim Release 8.3 - Maintenance Window | 100% | 07/10/24 | 21/10/24 | 11 days | 07/10/24 | 21/10/24 | 0 days | 0 days | 11 days | Design |  | 6 | Yes
6 | 1.3.4.8.3.1 |  |  |  |  | Interim Release 8.3 'effective from date' to SIT A | 100% | 21/10/24 | 21/10/24 | 0 days | 21/10/24 | 21/10/24 | 1 day | 0 days | -10 days | SI Testing |  | 5.16 | Yes
6 | 1.3.4.8.3.2 |  |  |  |  | Interim Release 8.3 'effective from date' to SIT B | 100% | 07/10/24 | 07/10/24 | 0 days | 07/10/24 | 07/10/24 | 0 days | -1 day | 0 days | Design |  | 5.16 | Yes
5 | 1.3.4.8.4 |  |  | DAG |  | Interim Release 8.4 | 100% | 25/09/24 | 02/12/24 | 49 days | 25/09/24 | 13/11/24 | 0 days | 13 days | 49 days | Design |  | 6.1 | Yes
6 | 1.3.4.8.4.1 |  |  |  |  | Update baselined artefacts | 100% | 25/09/24 | 04/10/24 | 8 days | 25/09/24 | 04/10/24 | 0 days | 0 days | 8 days | Design |  | 6.1 | Yes
6 | 1.3.4.8.4.2 | T3 | T3-DB-0184 | DAG |  | Interim Release 8.4 Published | 100% | 16/10/24 | 16/10/24 | 0 days | 16/10/24 | 16/10/24 | 1 day | 0 days | 0 days | Design |  | 6.1 | Yes
6 | 1.3.4.8.4.3 |  |  |  |  | Interim Release 8.4 Deployed to SIT by Participants | 100% | 25/11/24 | 02/12/24 | 6 days | 13/11/24 | 13/11/24 | 8 days | 13 days | 6 days | Design |  | 6.12 | Yes
5 | 1.3.4.8.5 |  |  | DAG |  | Interim Release 8.5 | 73% | 16/10/24 | 22/01/25 | 71 days | 16/10/24 | 04/12/24 | 0 days | 35 days | 71 days | Design |  | 6.11 | Yes
6 | 1.3.4.8.5.1 |  |  |  |  | Update baselined artefacts | 100% | 16/10/24 | 25/10/24 | 8 days | 16/10/24 | 25/10/24 | 0 days | 0 days | 8 days | Design |  | 6.11 | Yes
6 | 1.3.4.8.5.2 | T3 | T3-DB-0185 | DAG |  | Interim Release 8.5 Published | 100% | 06/11/24 | 06/11/24 | 0 days | 06/11/24 | 06/11/24 | 1 day | 0 days | 0 days | Design |  | 6.11 | Yes
6 | 1.3.4.8.5.3 |  |  |  |  | Interim Release 8.5 Deployed to SIT by Participants | 0% | 20/01/25 | 22/01/25 | 3 days | 04/12/24 | 04/12/24 | 33 days | 35 days | 3 days | Design |  | 6.12 | Yes
5 | 1.3.4.8.6 |  |  | DAG |  | Interim Release 8.6 | 50% | 21/11/24 | 22/01/25 | 45 days? | 21/11/24 | 22/01/25 | 0 days | 0 days | 45 days? | Design |  | 6.14 | Yes
6 | 1.3.4.8.6.1 |  |  |  |  | Update baselined artefacts | 100% | 21/11/24 | 22/11/24 | 2 days? | 21/11/24 | 22/11/24 | 0 days | 0 days | 2 days? |  |  | 6.14 | Yes
6 | 1.3.4.8.6.2 |  |  |  |  | Interim Release 8.6 Published | 100% | 25/11/24 | 25/11/24 | 1 day? | 25/11/24 | 25/11/24 | 0 days | 0 days | 1 day? |  |  | 6.14 | Yes
6 | 1.3.4.8.6.3 | T3 | T3-TE-0187 | DAG |  | Interim Release 8.6 Deployed to SIT by Participants | 0% | 20/01/25 | 22/01/25 | 3 days | 20/01/25 | 22/01/25 | 0 days | 0 days | 3 days | Design |  | 6.14 | Yes
5 | 1.3.4.8.7 |  |  | DAG |  | Interim Release 8.7 | 0% | 20/01/25 | 24/01/25 | 5 days | 20/01/25 | 27/01/25 | 0 days | -1 day | 5 days | Design |  | 6.16 | Yes |  | 14/01/25 - IR 8.7 dates have now been confirmed, plan updated to relfect this.
6 | 1.3.4.8.7.1 |  |  |  |  | Update baselined artefacts | 0% | 20/01/25 | 21/01/25 | 2 days | 20/01/25 | 21/01/25 | 0 days | 0 days | 2 days |  |  | 6.16 | Yes |  | 14/01/25 - IR 8.7 dates have now been confirmed, plan updated to relfect this.
6 | 1.3.4.8.7.2 |  |  |  |  | Interim Release 8.7 Published | 0% | 22/01/25 | 22/01/25 | 1 day | 22/01/25 | 22/01/25 | 0 days | 0 days | 1 day |  |  | 6.16 | Yes |  | 14/01/25 - IR 8.7 dates have now been confirmed, plan updated to relfect this.
6 | 1.3.4.8.7.3 | T3 | T3-TE-0188 | DAG |  | Interim Release 8.7 Deployed to SIT by Participants | 0% | 22/01/25 | 24/01/25 | 3 days | 23/01/25 | 27/01/25 | -1 day | -1 day | 3 days | Design |  | 6.16 | Yes |  | 14/01/25 - IR 8.7 dates have now been confirmed, plan updated to relfect this.
3 | 1.3.5 |  |  |  |  | Queries Support / Knowledgebase & Tool Roll-Out (Systems) | 100% | 03/01/23 | 01/04/24 | 325 days | 03/01/23 | 01/04/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.3.5.1 |  |  |  |  | Query Management | 100% | 03/01/23 | 01/04/24 | 325 days | 03/01/23 | 01/04/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.5.1.1 |  |  |  |  | Respond to Participant Queries | 100% | 03/01/23 | 01/04/24 | 325 days | 03/01/23 | 01/04/24 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.1.2 |  |  |  |  | Respond to Programme Queries | 100% | 03/01/23 | 01/04/24 | 325 days | 03/01/23 | 01/04/24 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.5.2 |  |  |  |  | Query Support tooling (FreshDesk) | 100% | 01/06/23 | 03/07/23 | 23 days | 01/06/23 | 03/07/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.5.2.1 |  |  |  |  | Migrate to Standalone Freshdesk | 100% | 01/06/23 | 14/06/23 | 10 days | 01/06/23 | 14/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.2.2 |  |  |  |  | Develop reporting dashboard | 100% | 15/06/23 | 21/06/23 | 5 days | 15/06/23 | 21/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.2.3 |  |  |  |  | Issue to SRO for Review | 100% | 22/06/23 | 28/06/23 | 5 days | 22/06/23 | 28/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.2.4 |  |  |  |  | Update following review | 100% | 29/06/23 | 30/06/23 | 2 days | 29/06/23 | 30/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.2.5 |  |  |  |  | Sign off | 100% | 03/07/23 | 03/07/23 | 1 day | 03/07/23 | 03/07/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.5.3 |  |  |  |  | KnowledgeBase Development | 100% | 01/06/23 | 08/09/23 | 72 days | 01/06/23 | 08/09/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.5.3.1 |  |  |  |  | Define Scope of KB | 100% | 01/06/23 | 01/06/23 | 1 day | 01/06/23 | 01/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.3.2 |  |  |  |  | Capture Existing KB artefacts | 100% | 02/06/23 | 29/06/23 | 20 days | 02/06/23 | 29/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.3.3 |  |  |  |  | Tag artefacts | 100% | 30/06/23 | 06/07/23 | 5 days | 30/06/23 | 06/07/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.3.4 |  |  |  |  | Develop Participant Interfaces | 100% | 07/07/23 | 03/08/23 | 20 days | 07/07/23 | 03/08/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.3.5 |  |  |  |  | Promote to Collaboration Portal | 100% | 04/08/23 | 01/09/23 | 21 days | 04/08/23 | 01/09/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.5.3.6 |  |  |  |  | Link into FreshDesk | 100% | 04/09/23 | 08/09/23 | 5 days | 04/09/23 | 08/09/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
3 | 1.3.6 |  |  |  |  | PP Design, Build & Test (DBT) | 83% | 31/10/22 | 05/07/27 | 1221 days? | 31/10/22 | 05/07/27 | 0 days | 0 days | 726 days? | N/A |  | 5 | Yes
4 | 1.3.6.1 |  |  |  |  | PP Impact Assessment, Planning & Procurement | 100% | 31/10/22 | 31/03/23 | 110 days | 31/10/22 | 31/03/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.6.1.1 |  |  |  |  | PP Impact Assessment | 100% | 31/10/22 | 31/01/23 | 67 days | 31/10/22 | 31/01/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.6.1.1.1 |  |  |  |  | Develop heatmap for impact of MHHS | 100% | 31/10/22 | 31/01/23 | 67 days | 31/10/22 | 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.1.1.2 |  |  |  |  | Develop detailed impact assessment | 100% | 31/10/22 | 31/01/23 | 67 days | 31/10/22 | 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.3.6.1.2 |  |  |  |  | PP Planning | 100% | 31/10/22 | 31/01/23 | 67 days | 31/10/22 | 31/01/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.6.1.2.1 |  |  |  |  | Develop detailed short-term plan | 100% | 31/10/22 | 30/11/22 | 23 days | 31/10/22 | 30/11/22 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.1.2.2 |  |  |  |  | Develop overall project plan for implementation | 100% | 31/10/22 | 31/01/23 | 67 days | 31/10/22 | 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.1.2.3 |  |  |  |  | Develop procurement plan | 100% | 31/10/22 | 31/01/23 | 67 days | 31/10/22 | 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.3.6.1.3 |  |  |  |  | PP Software/Service Procurement | 100% | 31/10/22 | 31/03/23 | 110 days | 31/10/22 | 31/03/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.6.1.3.1 |  |  |  |  | Run tender process | 100% | 31/10/22 | 31/01/23 | 67 days | 31/10/22 | 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.1.3.2 |  |  |  |  | Select provider & sign commercials | 100% | 01/02/23 | 31/03/23 | 43 days | 01/02/23 | 31/03/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.3.6.2 |  |  |  |  | Design Handover | 6% | 02/09/24 | 05/07/27 | 741 days? | 02/09/24 | 05/07/27 | 0 days | 0 days | 741 days? | Design |  | 6.1 | Yes
5 | 1.3.6.2.1 |  |  |  |  | Creation of the Configuration Management Database | 100% | 02/09/24 | 19/09/24 | 14 days | 02/09/24 | 19/09/24 | 0 days | 0 days | 14 days | Design |  | 6.1 | Yes
6 | 1.3.6.2.1.1 |  |  |  |  | Identify all baselined design artefacts | 100% | 02/09/24 | 12/09/24 | 9 days | 02/09/24 | 12/09/24 | 0 days | 0 days | 9 days | Design |  | 6.1 | Yes
6 | 1.3.6.2.1.2 |  |  |  |  | Create CMBD | 100% | 13/09/24 | 19/09/24 | 5 days | 13/09/24 | 19/09/24 | 0 days | 0 days | 5 days | Design |  | 6.1 | Yes
5 | 1.3.6.2.2 |  |  |  |  | Knowledge Transfer | 0% | 02/09/24 | 28/10/24 | 41 days? | 02/09/24 | 28/10/24 | 0 days | 0 days | 41 days? | Design |  | 6.1 | Yes
6 | 1.3.6.2.2.1 |  |  |  |  | Elexon to document knowledge transfer requirements | 0% | 02/09/24 | 12/09/24 | 9 days? | 02/09/24 | 12/09/24 | 0 days | 0 days | 9 days? | Design |  | 6.1 | Yes |  | 14/01/25 - Design Handover activities dependent on Helix completing an action before they can be progressed.
6 | 1.3.6.2.2.2 |  |  |  |  | Review Requirements | 0% | 13/09/24 | 19/09/24 | 5 days | 13/09/24 | 19/09/24 | 0 days | 0 days | 5 days | Design |  | 6.1 | Yes |  | 14/01/25 - Design Handover activities dependent on Helix completing an action before they can be progressed.
6 | 1.3.6.2.2.3 |  |  |  |  | Agree Success Criteria | 0% | 20/09/24 | 03/10/24 | 10 days | 20/09/24 | 03/10/24 | 0 days | 0 days | 10 days | Design |  | 6.1 | Yes |  | 14/01/25 - Design Handover activities dependent on Helix completing an action before they can be progressed.
6 | 1.3.6.2.2.4 |  |  |  |  | Identify Key personel with Elexon | 0% | 04/10/24 | 08/10/24 | 3 days | 04/10/24 | 08/10/24 | 0 days | 0 days | 3 days | Design |  | 6.1 | Yes |  | 14/01/25 - Design Handover activities dependent on Helix completing an action before they can be progressed.
6 | 1.3.6.2.2.5 |  |  |  |  | Draft Agenda for initial meeting | 0% | 09/10/24 | 09/10/24 | 1 day? | 09/10/24 | 09/10/24 | 0 days | 0 days | 1 day? | Design |  | 6.1 | Yes |  | 14/01/25 - Design Handover activities dependent on Helix completing an action before they can be progressed.
6 | 1.3.6.2.2.6 |  |  |  |  | Define cadence for handover sessions | 0% | 10/10/24 | 11/10/24 | 2 days | 10/10/24 | 11/10/24 | 0 days | 0 days | 2 days | Design |  | 6.1 | Yes |  | 14/01/25 - Design Handover activities dependent on Helix completing an action before they can be progressed.
6 | 1.3.6.2.2.7 |  |  |  |  | Share Design Information | 0% | 02/09/24 | 27/09/24 | 20 days | 02/09/24 | 27/09/24 | 0 days | 0 days | 20 days | Design |  | 6.1 | Yes |  | 14/01/25 - Design Handover activities dependent on Helix completing an action before they can be progressed.
6 | 1.3.6.2.2.8 |  |  |  |  | Conduct Initial Handover Session | 0% | 01/10/24 | 28/10/24 | 20 days? | 01/10/24 | 28/10/24 | 0 days | 0 days | 20 days? | Design |  | 6.1 | Yes |  | 14/01/25 - Design Handover activities dependent on Helix completing an action before they can be progressed.
5 | 1.3.6.2.3 |  |  |  |  | Triage Sessions | 0% | 01/10/24 | 01/04/25 | 131 days? | 01/10/24 | 01/04/25 | 0 days | 0 days | 131 days? | Design |  | 6.1 | Yes
6 | 1.3.6.2.3.1 |  |  |  |  | Design Triage Sessions | 0% | 01/10/24 | 01/04/25 | 131 days? | 01/10/24 | 01/04/25 | 0 days | 0 days | 131 days? | Design |  | 6.1 | Yes
6 | 1.3.6.2.3.2 |  |  |  |  | Test Triage Sessions | 0% | 01/10/24 | 01/04/25 | 131 days? | 01/10/24 | 01/04/25 | 0 days | 0 days | 131 days? | Design |  | 6.1 | Yes
5 | 1.3.6.2.4 |  |  |  |  | Knowledge Base | 100% | 02/09/24 | 12/09/24 | 9 days | 02/09/24 | 12/09/24 | 0 days | 0 days | 9 days | Design |  | 6.1 | Yes
6 | 1.3.6.2.4.1 |  |  |  |  | Document Knowledge base update process | 100% | 02/09/24 | 05/09/24 | 4 days | 02/09/24 | 05/09/24 | 0 days | 0 days | 4 days | Design |  | 6.1 | Yes
6 | 1.3.6.2.4.2 |  |  |  |  | Document Design updates to Collaboration Base | 100% | 06/09/24 | 12/09/24 | 5 days | 06/09/24 | 12/09/24 | 0 days | 0 days | 5 days | Design |  | 6.1 | Yes
5 | 1.3.6.2.5 |  |  |  |  | FreshDesk | 0% | 03/02/25 | 14/03/25 | 30 days? | 03/02/25 | 14/03/25 | 0 days | 0 days | 30 days? | Design |  | 6.1 | Yes
6 | 1.3.6.2.5.1 |  |  |  |  | Agree Indicative Handover of FreshDesk Calls to Service Now | 0% | 03/02/25 | 06/02/25 | 4 days | 03/02/25 | 06/02/25 | 0 days | 0 days | 4 days | Design |  | 6.1 | Yes
6 | 1.3.6.2.5.2 |  |  |  |  | Prepare Comms to Industry | 0% | 07/02/25 | 20/02/25 | 10 days | 07/02/25 | 20/02/25 | 0 days | 0 days | 10 days | Design |  | 6.1 | Yes
6 | 1.3.6.2.5.3 |  |  |  |  | Issue Comms to Industry | 0% | 21/02/25 | 21/02/25 | 1 day? | 21/02/25 | 21/02/25 | 0 days | 0 days | 1 day? | Design |  | 6.1 | Yes
6 | 1.3.6.2.5.4 |  |  |  |  | Redirect Design Mailbox to Service Now | 0% | 03/03/25 | 03/03/25 | 1 day? | 03/03/25 | 03/03/25 | 0 days | 0 days | 1 day? | Design |  | 6.1 | Yes
6 | 1.3.6.2.5.5 |  |  |  |  | Archive Freshdesk calls | 0% | 03/03/25 | 07/03/25 | 5 days | 03/03/25 | 07/03/25 | 0 days | 0 days | 5 days | Design |  | 6.1 | Yes
6 | 1.3.6.2.5.6 |  |  |  |  | Decommission FreshDesk | 0% | 10/03/25 | 14/03/25 | 5 days | 10/03/25 | 14/03/25 | 0 days | 0 days | 5 days | Design |  | 6.1 | Yes
5 | 1.3.6.2.6 |  |  |  |  | iServer | 5% | 03/03/25 | 05/07/27 | 611 days? | 03/03/25 | 05/07/27 | 0 days | 0 days | 611 days? | Design |  | 6.1 | Yes
6 | 1.3.6.2.6.1 |  |  |  |  | Gather Licensing information | 100% | 03/03/25 | 03/03/25 | 1 day? | 03/03/25 | 03/03/25 | 0 days | 0 days | 1 day? | Design |  | 6.1 | Yes
6 | 1.3.6.2.6.2 |  |  |  |  | Clear down old information | 0% | 03/03/25 | 07/03/25 | 5 days | 03/03/25 | 07/03/25 | 0 days | 0 days | 5 days | Design |  | 6.1 | Yes
6 | 1.3.6.2.6.3 |  |  |  |  | Clear down accounts | 0% | 10/03/25 | 11/03/25 | 2 days | 10/03/25 | 11/03/25 | 0 days | 0 days | 2 days | Design |  | 6.1 | Yes
6 | 1.3.6.2.6.4 |  |  |  |  | Identify Collaboration Base Design Dependencies on iServer | 0% | 01/04/25 | 02/04/25 | 2 days | 01/04/25 | 02/04/25 | 0 days | 0 days | 2 days | Design |  | 6.1 | Yes
6 | 1.3.6.2.6.5 |  |  |  |  | Remove Design dependencies | 0% | 03/04/25 | 09/04/25 | 5 days | 03/04/25 | 09/04/25 | 0 days | 0 days | 5 days | Design |  | 6.1 | Yes
6 | 1.3.6.2.6.6 |  |  |  |  | Close down iServer | 0% | 10/04/25 | 16/04/25 | 5 days | 10/04/25 | 16/04/25 | 0 days | 0 days | 5 days | Design |  | 6.1 | Yes
4 | 1.3.6.3 |  |  |  |  | Central Systems DBT | 100% | 31/10/22 | 26/01/24 | 325 days | 31/10/22 | 26/01/24 | 0 days | 0 days | -20 days | N/A |  | 5 | Yes
5 | 1.3.6.3.1 |  |  |  |  | Elexon Central Systems DBT CIT (Entering at Interval 1) | 100% | 31/10/22 | 11/10/23 | 248 days | 31/10/22 | 11/10/23 | 0 days | 0 days | -1 day | N/A |  | 5 | Yes
6 | 1.3.6.3.1.1 |  |  |  |  | Design and Build | 100% | 31/10/22 | 22/09/23 | 235 days | 31/10/22 | 22/09/23 | 0 days | 0 days | -5 days | N/A |  | 5 | Yes
7 | 1.3.6.3.1.1.1 |  |  |  |  | Helix Design and Build | 100% | 31/10/22 | 22/09/23 | 235 days | 31/10/22 | 22/09/23 | 0 days | 0 days | -5 days | PP |  | 5 | Yes
6 | 1.3.6.3.1.2 |  |  |  |  | Test Approach & Plan | 100% | 31/10/22 | 22/09/23 | 235 days | 31/10/22 | 22/09/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.1.2.1 |  |  |  |  | Develop Test Approach & Plan | 100% | 31/10/22 | 07/07/23 | 180 days | 31/10/22 | 07/07/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.1.2.2 | T3 | T3-DB-0029 | SITAG |  | Elexon Central Systems Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | 13/07/23 | 13/07/23 | 0 days | 13/07/23 | 13/07/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.1.2.3 |  |  |  |  | Elexon Central Systems Test Approach & Plan (PIT) V2 resubmitted to Programme for assurance | 100% | 27/07/23 | 27/07/23 | 0 days | 27/07/23 | 27/07/23 | 0 days | -1 day | 0 days | PP |  | 5.4 | Yes
7 | 1.3.6.3.1.2.4 |  |  |  |  | Elexon Central Systems Test Approach & Plan (PIT) V3 resubmitted to Programme for assurance | 100% | 18/08/23 | 18/08/23 | 0 days | 18/08/23 | 18/08/23 | 1 day | 0 days | 0 days | PP |  | 5.4 | Yes
7 | 1.3.6.3.1.2.5 | T3 | T3-DB-0106 | SITAG |  | Elexon Central Systems Test approach and plan MHHS Review Completed | 100% | 22/09/23 | 22/09/23 | 0 days | 22/09/23 | 22/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.3.1.3 |  |  |  |  | Test Readiness Report | 100% | 28/07/23 | 18/08/23 | 16 days | 28/07/23 | 18/08/23 | 0 days | 0 days | -35 days | N/A |  | 5 | Yes
7 | 1.3.6.3.1.3.1 |  |  |  |  | Test readiness reporting | 100% | 28/07/23 | 18/08/23 | 16 days | 28/07/23 | 18/08/23 | 0 days | 0 days | -35 days | PP |  | 5 | Yes
6 | 1.3.6.3.1.4 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | 04/08/23 | 22/09/23 | 35 days | 04/08/23 | 22/09/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.1.4.1 | T3 | T3-DB-0030 | SITAG | MHHS-ART009 | Elexon Central Systems RTTM submitted to Programme for assurance | 100% | 04/08/23 | 04/08/23 | 0 days | 04/08/23 | 04/08/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.1.4.2 | T3 | T3-DB-0107 | SITAG |  | Elexon Central Systems RTTM MHHS Review Completed | 100% | 22/09/23 | 22/09/23 | 0 days | 22/09/23 | 22/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.3.1.5 |  |  |  |  | Test Scenarios | 100% | 04/08/23 | 22/09/23 | 35 days | 04/08/23 | 22/09/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.1.5.1 | T3 | T3-DB-0032 | SITAG |  | Elexon Central Systems test scenarios submitted to Programme for assurance | 100% | 04/08/23 | 04/08/23 | 0 days | 04/08/23 | 04/08/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.1.5.2 | T3 | T3-DB-0108 | SITAG |  | Elexon Central Systems Test scenarios MHHS Review Completed | 100% | 22/09/23 | 22/09/23 | 0 days | 22/09/23 | 22/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.3.1.6 |  |  |  |  | PIT Execution | 100% | 21/08/23 | 11/10/23 | 38 days | 21/08/23 | 11/10/23 | 0 days | 0 days | -210 days | N/A |  | 5 | Yes
7 | 1.3.6.3.1.6.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | 04/09/23 | 27/09/23 | 18 days | 04/09/23 | 27/09/23 | 0 days | 0 days | -217 days | PP |  | 5.1 | Yes
7 | 1.3.6.3.1.6.2 |  |  |  |  | Elexon Central Systems PIT Execution | 100% | 21/08/23 | 27/09/23 | 28 days | 21/08/23 | 27/09/23 | 0 days | 0 days | -212 days | PP |  | 5.1 | Yes
7 | 1.3.6.3.1.6.3 | T3 | T3-DB-0109 | SITAG |  | Elexon Central Systems PIT Completion Report submitted to Programme for assurance | 100% | 27/09/23 | 27/09/23 | 0 days | 27/09/23 | 27/09/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
7 | 1.3.6.3.1.6.4 | T3 | T3-DB-0110 | SITAG |  | Elexon Central Systems PIT Completion Report MHHS Review Completed | 100% | 11/10/23 | 11/10/23 | 0 days | 11/10/23 | 11/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
5 | 1.3.6.3.2 |  |  |  |  | DIP DBT CIT (Entering at Interval 1) | 100% | 02/01/23 | 06/11/23 | 221 days | 02/01/23 | 06/11/23 | 0 days | 0 days | -45 days | N/A |  | 5 | Yes
6 | 1.3.6.3.2.1 |  |  |  |  | Design | 100% | 02/01/23 | 21/04/23 | 80 days | 02/01/23 | 21/04/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.3.2.2 |  |  |  |  | Build | 100% | 09/01/23 | 11/08/23 | 155 days | 09/01/23 | 11/08/23 | 0 days | 0 days | 0 days | PP |  | 5.5 | Yes
6 | 1.3.6.3.2.3 |  |  |  |  | Test Approach & Plan | 100% | 07/07/23 | 20/07/23 | 9 days | 07/07/23 | 20/07/23 | 1 day | 0 days | -181 days | N/A |  | 5 | Yes
7 | 1.3.6.3.2.3.1 | T3 | T3-DB-0026 | SITAG | MHHS-ART073 | DIP Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | 07/07/23 | 07/07/23 | 0 days | 07/07/23 | 07/07/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.2.3.2 |  |  |  |  | DIP Test Approach & Plan (PIT) MHHS Review Completed | 100% | 20/07/23 | 20/07/23 | 0 days | 20/07/23 | 20/07/23 | 1 day | 0 days | -10 days | SI Test |  | 5 | Yes
6 | 1.3.6.3.2.4 |  |  |  |  | PIT Test Readiness Report | 100% | 21/07/23 | 01/09/23 | 31 days | 21/07/23 | 01/09/23 | 0 days | 0 days | -20 days | N/A |  | 5 | Yes
7 | 1.3.6.3.2.4.1 |  |  |  |  | Test readiness reporting | 100% | 21/07/23 | 01/09/23 | 31 days | 21/07/23 | 01/09/23 | 0 days | 0 days | -20 days | SI Test |  | 5 | Yes
6 | 1.3.6.3.2.5 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | 04/08/23 | 30/08/23 | 18 days | 04/08/23 | 30/08/23 | 1 day | 0 days | -192 days | N/A |  | 5 | Yes
7 | 1.3.6.3.2.5.1 | T3 | T3-DB-0034 | SITAG | MHHS-ART009 | DIP RTTM submitted to Programme for assurance | 100% | 04/08/23 | 04/08/23 | 0 days | 04/08/23 | 04/08/23 | 1 day | 0 days | 0 days | PP |  | 5.6 | Yes
7 | 1.3.6.3.2.5.2 |  |  |  |  | DIP RTTM MHHS Review Completed | 100% | 30/08/23 | 30/08/23 | 0 days | 30/08/23 | 30/08/23 | 1 day | 0 days | -10 days | SI Test |  | 5 | Yes
6 | 1.3.6.3.2.6 |  |  |  |  | Test Scenarios | 100% | 31/07/23 | 30/08/23 | 22 days | 31/07/23 | 30/08/23 | 1 day | 0 days | -184 days | N/A |  | 5 | Yes
7 | 1.3.6.3.2.6.1 | T3 | T3-DB-0036 | SITAG |  | DIP PIT test scenarios submitted to Programme for assurance | 100% | 31/07/23 | 31/07/23 | 0 days | 31/07/23 | 31/07/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.2.6.2 |  |  |  |  | DIP Test scenarios MHHS Review Completed | 100% | 30/08/23 | 30/08/23 | 0 days | 30/08/23 | 30/08/23 | 1 day | 0 days | -10 days | SI Test |  | 5 | Yes
6 | 1.3.6.3.2.7 |  |  |  |  | PIT execution | 100% | 29/08/23 | 06/11/23 | 50 days | 29/08/23 | 06/11/23 | 0 days | 0 days | 3 days | N/A |  | 5 | Yes
7 | 1.3.6.3.2.7.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | 01/09/23 | 23/10/23 | 37 days | 01/09/23 | 23/10/23 | 0 days | 0 days | 0 days | PP |  | 5.6 | Yes
7 | 1.3.6.3.2.7.2 |  |  |  |  | PIT Execution (Interim Release 1) | 100% | 29/08/23 | 09/10/23 | 30 days | 29/08/23 | 09/10/23 | 0 days | 0 days | 6 days | PP |  | 5.6 | Yes
7 | 1.3.6.3.2.7.3 |  |  |  |  | PIT Execution (Interim Release 2) | 100% | 10/10/23 | 23/10/23 | 10 days | 10/10/23 | 23/10/23 | 0 days | 0 days | 0 days | PP |  | 5.6 | Yes
7 | 1.3.6.3.2.7.4 | T3 | T3-DB-0111 | SITAG |  | DIP PIT Completion Report (Interim Release 1) submitted to Programme for assurance | 100% | 09/10/23 | 09/10/23 | 0 days | 09/10/23 | 09/10/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
7 | 1.3.6.3.2.7.5 | T3 | T3-DB-0112 | SITAG |  | DIP PIT Completion Report (Interim Release 1) MHHS Review Completed | 100% | 23/10/23 | 23/10/23 | 0 days | 23/10/23 | 23/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.1 | Yes
7 | 1.3.6.3.2.7.6 | T3 | T3-DB-0113 | SITAG |  | DIP PIT Completion Report (Interim Release 2) submitted to Programme for assurance | 100% | 23/10/23 | 23/10/23 | 0 days | 23/10/23 | 23/10/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.3.6.3.2.7.7 | T3 | T3-DB-0114 | SITAG |  | DIP PIT Completion Report (Interim Release 2) MHHS Review Completed | 100% | 06/11/23 | 06/11/23 | 0 days | 06/11/23 | 06/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
5 | 1.3.6.3.3 |  |  |  |  | DCC (DSP) DBT SIT Functional (Entering at SIT Functional) | 100% | 31/10/22 | 26/01/24 | 325 days | 31/10/22 | 26/01/24 | 0 days | 0 days | -20 days | N/A |  | 5.18 | Yes
6 | 1.3.6.3.3.1 |  |  |  |  | Design | 100% | 31/10/22 | 31/01/23 | 67 days | 31/10/22 | 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5.18 | Yes
6 | 1.3.6.3.3.2 |  |  |  |  | Test Approach & Plan | 100% | 17/11/23 | 15/12/23 | 20 days | 17/11/23 | 15/12/23 | 1 day | 0 days | 0 days | N/A |  | 5.18 | Yes
7 | 1.3.6.3.3.2.1 | T3 | T3-DB-0068 | SITAG |  | DCC Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | 17/11/23 | 17/11/23 | 0 days | 17/11/23 | 17/11/23 | 1 day | 0 days | 0 days | PP |  | 5.18 | Yes
7 | 1.3.6.3.3.2.2 | T3 | T3-DB-0115 | SITAG |  | DCC Test Approach & Plan (PIT) MHHS Review Completed | 100% | 15/12/23 | 15/12/23 | 0 days | 15/12/23 | 15/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.18 | Yes
6 | 1.3.6.3.3.3 |  |  |  |  | Test Readiness Report | 100% | 04/12/23 | 02/01/24 | 22 days | 04/12/23 | 02/01/24 | 0 days | 0 days | -29 days | N/A |  | 5.18 | Yes
7 | 1.3.6.3.3.3.1 |  |  |  |  | Test readiness reporting | 100% | 04/12/23 | 02/01/24 | 22 days | 04/12/23 | 02/01/24 | 0 days | 0 days | -29 days | PP |  | 5.18 | Yes
6 | 1.3.6.3.3.4 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | 15/12/23 | 26/01/24 | 30 days | 15/12/23 | 26/01/24 | 1 day | 0 days | 0 days | N/A |  | 5.18 | Yes
7 | 1.3.6.3.3.4.1 | T3 | T3-DB-0074 | SITAG |  | DCC RTTM submitted to Programme for assurance | 100% | 15/12/23 | 15/12/23 | 0 days | 15/12/23 | 15/12/23 | 1 day | 0 days | 0 days | PP |  | 5.18 | Yes
7 | 1.3.6.3.3.4.2 | T3 | T3-DB-0116 | SITAG |  | DCC RTTM MHHS Review Completed | 100% | 26/01/24 | 26/01/24 | 0 days | 26/01/24 | 26/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.18 | Yes
6 | 1.3.6.3.3.5 |  |  |  |  | Test Scenarios | 100% | 15/12/23 | 26/01/24 | 30 days | 15/12/23 | 26/01/24 | 1 day | 0 days | 0 days | N/A |  | 5.18 | Yes
7 | 1.3.6.3.3.5.1 | T3 | T3-DB-0078 | SITAG |  | DCC test scenarios submitted to Programme for assurance | 100% | 15/12/23 | 15/12/23 | 0 days | 15/12/23 | 15/12/23 | 1 day | 0 days | 0 days | PP |  | 5.18 | Yes
7 | 1.3.6.3.3.5.2 | T3 | T3-DB-0117 | SITAG |  | DCC Test Scenarios MHHS Review Completed | 100% | 26/01/24 | 26/01/24 | 0 days | 26/01/24 | 26/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.18 | Yes
5 | 1.3.6.3.4 |  |  |  |  | RECCo (EES) DBT CIT (Entering at Interval 6) | 100% | 13/10/23 | 19/01/24 | 71 days | 13/10/23 | 19/01/24 | 0 days | 0 days | -249 days | N/A |  | 5 | Yes
6 | 1.3.6.3.4.1 |  |  |  |  | Test Approach & Plan | 100% | 13/10/23 | 09/11/23 | 20 days | 13/10/23 | 09/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.4.1.1 | T3 | T3-DB-0066 | SITAG |  | EES Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | 13/10/23 | 13/10/23 | 0 days | 13/10/23 | 13/10/23 | 0 days | -1 day | 0 days | PP |  | 5.8 | Yes
7 | 1.3.6.3.4.1.2 | T3 | T3-DB-0119 | SITAG |  | EES Test approach and plan (PIT) MHHS Review Completed | 100% | 09/11/23 | 09/11/23 | 0 days | 09/11/23 | 09/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.3.4.2 |  |  |  |  | Test Readiness Report | 100% | 27/10/23 | 09/11/23 | 10 days | 27/10/23 | 09/11/23 | 0 days | 0 days | -41 days | N/A |  | 5 | Yes
7 | 1.3.6.3.4.2.1 |  |  |  |  | Test readiness reporting | 100% | 27/10/23 | 09/11/23 | 10 days | 27/10/23 | 09/11/23 | 0 days | 0 days | -41 days | PP |  | 5 | Yes
6 | 1.3.6.3.4.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | 02/11/23 | 30/11/23 | 20 days | 02/11/23 | 30/11/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.4.3.1 | T3 | T3-DB-0072 | SITAG | MHHS-ART009 | EES RTTM submitted to Programme for assurance | 100% | 02/11/23 | 02/11/23 | 0 days | 02/11/23 | 02/11/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
7 | 1.3.6.3.4.3.2 | T3 | T3-DB-0120 | SITAG |  | EES RTTM MHHS Review Completed | 100% | 30/11/23 | 30/11/23 | 0 days | 30/11/23 | 30/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
6 | 1.3.6.3.4.4 |  |  |  |  | Test Scenarios | 100% | 02/11/23 | 30/11/23 | 20 days | 02/11/23 | 30/11/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.4.4.1 | T3 | T3-DB-0031 | SITAG |  | EES test scenarios submitted to Programme for assurance | 100% | 02/11/23 | 02/11/23 | 0 days | 02/11/23 | 02/11/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
7 | 1.3.6.3.4.4.2 | T3 | T3-DB-0121 | SITAG |  | EES Test scenarios MHHS Review Completed | 100% | 30/11/23 | 30/11/23 | 0 days | 30/11/23 | 30/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
6 | 1.3.6.3.4.5 |  |  |  |  | PIT execution | 100% | 10/11/23 | 19/01/24 | 51 days | 10/11/23 | 19/01/24 | 0 days | 0 days | -269 days | N/A |  | 5 | Yes
7 | 1.3.6.3.4.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | 10/11/23 | 05/01/24 | 41 days | 10/11/23 | 05/01/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.4.5.2 |  |  |  |  | PIT Execution | 100% | 10/11/23 | 05/01/24 | 41 days | 10/11/23 | 05/01/24 | 0 days | 0 days | -269 days | PP |  | 5 | Yes
7 | 1.3.6.3.4.5.3 | T3 | T3-DB-0122 | SITAG |  | EES PIT Completion Report submitted to Programme for assurance | 100% | 05/01/24 | 05/01/24 | 0 days | 05/01/24 | 05/01/24 | 1 day | 0 days | 0 days | PP |  | 5.14 | Yes
7 | 1.3.6.3.4.5.4 | T3 | T3-DB-0123 | SITAG |  | EES PIT Completion Report MHHS Review Completed | 100% | 19/01/24 | 19/01/24 | 0 days | 19/01/24 | 19/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
5 | 1.3.6.3.5 |  |  |  |  | Registration Services DBT CIT (Entering at Interval 2) | 100% | 28/07/23 | 03/11/23 | 70 days | 28/07/23 | 03/11/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.6.3.5.1 |  |  |  |  | Test Approach & Plan | 100% | 28/07/23 | 22/09/23 | 40 days | 28/07/23 | 22/09/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.5.1.1 | T3 | T3-DB-0028 | SITAG | MHHS-ART073 | Registration Services Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | 28/07/23 | 28/07/23 | 0 days | 28/07/23 | 28/07/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.5.1.2 | T3 | T3-DB-0124 | SITAG |  | Registration Services Test approach and plan MHHS Review Completed | 100% | 22/09/23 | 22/09/23 | 0 days | 22/09/23 | 22/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.3.5.2 |  |  |  |  | Test Readiness Report | 100% | 14/08/23 | 08/09/23 | 20 days | 14/08/23 | 08/09/23 | 0 days | 0 days | -31 days | N/A |  | 5 | Yes
7 | 1.3.6.3.5.2.1 |  |  |  |  | Test readiness reporting | 100% | 14/08/23 | 08/09/23 | 20 days | 14/08/23 | 08/09/23 | 0 days | 0 days | -31 days | PP |  | 5 | Yes
6 | 1.3.6.3.5.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | 01/09/23 | 29/09/23 | 20 days | 01/09/23 | 29/09/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.5.3.1 | T3 | T3-DB-0042 | SITAG | MHHS-ART009 | Registration Services RTTM submitted to Programme for assurance | 100% | 01/09/23 | 01/09/23 | 0 days | 01/09/23 | 01/09/23 | 1 day | 0 days | 0 days | PP |  | 5.6 | Yes
7 | 1.3.6.3.5.3.2 | T3 | T3-DB-0125 | SITAG |  | Registration Services RTTM MHHS Review Completed | 100% | 29/09/23 | 29/09/23 | 0 days | 29/09/23 | 29/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.3.5.4 |  |  |  |  | Test Scenarios | 100% | 01/09/23 | 29/09/23 | 20 days | 01/09/23 | 29/09/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.5.4.1 | T3 | T3-DB-0044 | SITAG |  | Registration Services test scenarios submitted to Programme for assurance | 100% | 01/09/23 | 01/09/23 | 0 days | 01/09/23 | 01/09/23 | 1 day | 0 days | 0 days | PP |  | 5.6 | Yes
7 | 1.3.6.3.5.4.2 | T3 | T3-DB-0126 | SITAG |  | Registration Services Test scenarios MHHS Review Completed | 100% | 29/09/23 | 29/09/23 | 0 days | 29/09/23 | 29/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.3.5.5 |  |  |  |  | PIT execution | 100% | 11/09/23 | 03/11/23 | 40 days | 11/09/23 | 03/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.3.5.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | 11/09/23 | 25/10/23 | 33 days | 11/09/23 | 25/10/23 | 0 days | 0 days | 3 days | PP |  | 5 | Yes
7 | 1.3.6.3.5.5.2 |  |  |  |  | PIT Execution | 100% | 11/09/23 | 20/10/23 | 30 days | 11/09/23 | 20/10/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.3.5.5.3 | T3 | T3-DB-0127 | SITAG |  | Registration Services PIT (CIT interval 2) Completion Report submitted to Programme for assurance | 100% | 25/10/23 | 25/10/23 | 0 days | 25/10/23 | 25/10/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.3.6.3.5.5.4 | T3 | T3-DB-0128 | SITAG |  | Registration Services PIT (CIT interval 2) Completion Report MHHS Review Completed | 100% | 03/11/23 | 03/11/23 | 0 days | 03/11/23 | 03/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.11 | Yes
4 | 1.3.6.4 |  |  |  |  | SIT Participants DBT | 89% | 11/08/23 | 21/02/25 | 401 days | 11/08/23 | 20/12/24 | 0 days | 45 days | -94 days | N/A |  | 5 | Yes
5 | 1.3.6.4.1 |  |  |  |  | All Data Services DBT CIT (Entering at Interval 3) | 100% | 11/08/23 | 17/11/23 | 71 days | 11/08/23 | 17/11/23 | 0 days | 0 days | -204 days | N/A |  | 5 | Yes
6 | 1.3.6.4.1.1 |  |  |  |  | Test Approach & Plan | 100% | 11/08/23 | 21/09/23 | 30 days | 11/08/23 | 21/09/23 | 0 days | 0 days | 1 day | N/A |  | 5 | Yes
7 | 1.3.6.4.1.1.1 | T3 | T3-DB-0038 | SITAG |  | All Data Services Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | 11/08/23 | 11/08/23 | 0 days | 11/08/23 | 11/08/23 | 0 days | -1 day | 0 days | PP |  | 5 | Yes
7 | 1.3.6.4.1.1.2 | T3 | T3-DB-0129 | SITAG |  | All Data Services Test approach and plans MHHS Review Completed | 100% | 21/09/23 | 21/09/23 | 0 days | 21/09/23 | 21/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.11 | Yes
6 | 1.3.6.4.1.2 |  |  |  |  | Test Readiness Report | 100% | 25/08/23 | 08/09/23 | 11 days | 25/08/23 | 08/09/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.4.1.2.1 |  |  |  |  | Test readiness reporting | 100% | 25/08/23 | 08/09/23 | 11 days | 25/08/23 | 08/09/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.4.1.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | 20/09/23 | 29/09/23 | 7 days | 20/09/23 | 29/09/23 | 1 day | 0 days | 2 days | N/A |  | 5 | Yes
7 | 1.3.6.4.1.3.1 | T3 | T3-DB-0058 | SITAG |  | All Data Services RTTMs submitted to Programme for assurance | 100% | 20/09/23 | 20/09/23 | 0 days | 20/09/23 | 20/09/23 | 1 day | 0 days | 0 days | PP |  | 5.7 | Yes
7 | 1.3.6.4.1.3.2 | T3 | T3-DB-0130 | SITAG |  | All Data Services RTTMs MHHS Review Completed | 100% | 29/09/23 | 29/09/23 | 0 days | 29/09/23 | 29/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.4.1.4 |  |  |  |  | Test Scenarios | 100% | 20/09/23 | 28/09/23 | 6 days | 20/09/23 | 28/09/23 | 1 day | 0 days | 2 days | N/A |  | 5 | Yes
7 | 1.3.6.4.1.4.1 | T3 | T3-DB-0056 | SITAG |  | All Data Services test scenarios' submitted to Programme for assurance | 100% | 20/09/23 | 20/09/23 | 0 days | 20/09/23 | 20/09/23 | 1 day | 0 days | 0 days | PP |  | 5.7 | Yes
7 | 1.3.6.4.1.4.2 | T3 | T3-DB-0131 | SITAG |  | All Data Services Test scenarios' MHHS Review Completed | 100% | 28/09/23 | 28/09/23 | 0 days | 28/09/23 | 28/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.11 | Yes
6 | 1.3.6.4.1.5 |  |  |  |  | PIT execution | 100% | 11/09/23 | 17/11/23 | 50 days | 11/09/23 | 17/11/23 | 0 days | 0 days | -225 days | N/A |  | 5 | Yes
7 | 1.3.6.4.1.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | 11/09/23 | 03/11/23 | 40 days | 11/09/23 | 03/11/23 | 0 days | 0 days | -220 days | PP |  | 5 | Yes
7 | 1.3.6.4.1.5.2 |  |  |  |  | PIT Execution | 100% | 28/09/23 | 03/11/23 | 27 days | 28/09/23 | 03/11/23 | 0 days | 0 days | -238 days | PP |  | 5 | Yes
7 | 1.3.6.4.1.5.3 | T3 | T3-DB-0132 | SITAG |  | All Data Services PIT Completion Reports submitted to Programme for assurance | 100% | 03/11/23 | 03/11/23 | 0 days | 03/11/23 | 03/11/23 | 1 day | 0 days | 0 days | PP |  | 5.11 | Yes
7 | 1.3.6.4.1.5.4 | T3 | T3-DB-0133 | SITAG |  | All Data Services PIT Completion Reports MHHS Review Completed | 100% | 17/11/23 | 17/11/23 | 0 days | 17/11/23 | 17/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.13 | Yes
5 | 1.3.6.4.2 |  |  |  |  | All Metering Services DBT CIT (Entering at Interval 4) | 100% | 25/08/23 | 01/12/23 | 70 days | 25/08/23 | 01/12/23 | 1 day | 0 days | -215 days | N/A |  | 5 | Yes
6 | 1.3.6.4.2.1 |  |  |  |  | Test Approach & Plan | 100% | 25/08/23 | 20/10/23 | 40 days | 25/08/23 | 20/10/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.4.2.1.1 | T3 | T3-DB-0040 | SITAG |  | All Metering Services Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | 25/08/23 | 25/08/23 | 0 days | 25/08/23 | 25/08/23 | 1 day | 0 days | 0 days | PP |  | 5.6 | Yes
7 | 1.3.6.4.2.1.2 | T3 | T3-DB-0134 | SITAG |  | All Metering Services Test approach and plans MHHS Review Completed | 100% | 20/10/23 | 20/10/23 | 0 days | 20/10/23 | 20/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.4.2.2 |  |  |  |  | Test Readiness Report | 100% | 11/09/23 | 25/09/23 | 11 days | 11/09/23 | 25/09/23 | 0 days | 0 days | -40 days | N/A |  | 5 | Yes
7 | 1.3.6.4.2.2.1 |  |  |  |  | Test readiness reporting | 100% | 11/09/23 | 25/09/23 | 11 days | 11/09/23 | 25/09/23 | 0 days | 0 days | -40 days | PP |  | 5 | Yes
6 | 1.3.6.4.2.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | 15/09/23 | 27/10/23 | 30 days | 15/09/23 | 27/10/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.4.2.3.1 | T3 | T3-DB-0048 | SITAG | MHHS-ART009 | All Metering Services RTTMs submitted to Programme for assurance | 100% | 15/09/23 | 15/09/23 | 0 days | 15/09/23 | 15/09/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
7 | 1.3.6.4.2.3.2 | T3 | T3-DB-0135 | SITAG |  | All Metering Services MHHS Reviews Completed | 100% | 27/10/23 | 27/10/23 | 0 days | 27/10/23 | 27/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.13 | Yes
6 | 1.3.6.4.2.4 |  |  |  |  | Test Scenarios | 100% | 15/09/23 | 27/10/23 | 30 days | 15/09/23 | 27/10/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.4.2.4.1 | T3 | T3-DB-0050 | SITAG |  | All Metering Services test scenarios' submitted to Programme for assurance | 100% | 15/09/23 | 15/09/23 | 0 days | 15/09/23 | 15/09/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
7 | 1.3.6.4.2.4.2 | T3 | T3-DB-0136 | SITAG |  | All Metering Services Test scenarios' MHHS Review Completed | 100% | 27/10/23 | 27/10/23 | 0 days | 27/10/23 | 27/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.13 | Yes
6 | 1.3.6.4.2.5 |  |  |  |  | PIT execution | 100% | 25/09/23 | 01/12/23 | 50 days | 25/09/23 | 01/12/23 | 0 days | 0 days | -235 days | N/A |  | 5 | Yes
7 | 1.3.6.4.2.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | 26/09/23 | 17/11/23 | 39 days | 26/09/23 | 17/11/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.4.2.5.2 |  |  |  |  | PIT Execution | 100% | 25/09/23 | 17/11/23 | 40 days | 25/09/23 | 17/11/23 | 0 days | 0 days | -235 days | PP |  | 5 | Yes
7 | 1.3.6.4.2.5.3 | T3 | T3-DB-0137 | SITAG |  | All Metering Services PIT Completion Reports submitted to Programme for assurance | 100% | 17/11/23 | 17/11/23 | 0 days | 17/11/23 | 17/11/23 | 1 day | 0 days | 0 days | PP |  | 5.13 | Yes
7 | 1.3.6.4.2.5.4 | T3 | T3-DB-0138 | SITAG |  | All Metering Services PIT Completion Reports MHHS Review Completed | 100% | 01/12/23 | 01/12/23 | 0 days | 01/12/23 | 01/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.13 | Yes
5 | 1.3.6.4.3 |  |  |  |  | All SIT Programme Participants PIT (SIT Functional) | 77% | 17/11/23 | 21/02/25 | 331 days | 17/11/23 | 20/12/24 | 0 days | 45 days | -120 days | N/A |  | 5 | Yes
6 | 1.3.6.4.3.1 |  |  |  |  | Test Approach & Plans | 100% | 17/11/23 | 11/01/24 | 40 days | 17/11/23 | 11/01/24 | 0 days | 0 days | 0 days | N/A |  | 5.2 | Yes
7 | 1.3.6.4.3.1.1 | T3 | T3-DB-0093 | SITAG |  | SIT Functional PIT Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | 17/11/23 | 17/11/23 | 0 days | 17/11/23 | 17/11/23 | 0 days | -1 day | 0 days | PP |  | 5.16 | Yes
7 | 1.3.6.4.3.1.2 | T3 | T3-DB-0139 | SITAG |  | All SIT Functional Test approach and plans MHHS Reviews Completed | 100% | 11/01/24 | 11/01/24 | 0 days | 11/01/24 | 11/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.4.3.2 |  |  |  |  | Test Readiness Reports | 100% | 01/12/23 | 15/12/23 | 11 days | 01/12/23 | 15/12/23 | 0 days | 0 days | -40 days | N/A |  | 5.2 | Yes
7 | 1.3.6.4.3.2.1 |  |  |  |  | Test readiness reporting | 100% | 01/12/23 | 15/12/23 | 11 days | 01/12/23 | 15/12/23 | 0 days | 0 days | -40 days | PP |  | 5.2 | Yes
6 | 1.3.6.4.3.3 |  |  |  |  | Requirements to test Traceability Matrices (RTTM) | 100% | 07/12/23 | 18/01/24 | 30 days | 07/12/23 | 18/01/24 | 1 day | 0 days | 0 days | N/A |  | 5.2 | Yes
7 | 1.3.6.4.3.3.1 | T3 | T3-DB-0091 | SITAG |  | SIT Functional PIT RTTM submitted to Programme for assurance | 100% | 07/12/23 | 07/12/23 | 0 days | 07/12/23 | 07/12/23 | 1 day | 0 days | 0 days | PP |  | 5.14 | Yes
7 | 1.3.6.4.3.3.2 | T3 | T3-DB-0140 | SITAG |  | All SIT Functional RTTMs MHHS Reviews Completed | 100% | 18/01/24 | 18/01/24 | 0 days | 18/01/24 | 18/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
6 | 1.3.6.4.3.4 |  |  |  |  | Test Scenarios | 100% | 07/12/23 | 18/01/24 | 30 days | 07/12/23 | 18/01/24 | 1 day | 0 days | 0 days | N/A |  | 5.2 | Yes
7 | 1.3.6.4.3.4.1 | T3 | T3-DB-0089 | SITAG |  | SIT Functional PIT test scenarios submitted to Programme for assurance | 100% | 07/12/23 | 07/12/23 | 0 days | 07/12/23 | 07/12/23 | 1 day | 0 days | 0 days | PP |  | 5.14 | Yes
7 | 1.3.6.4.3.4.2 | T3 | T3-DB-0141 | SITAG |  | All SIT Functional Test scenarios' MHHS Reviews Completed | 100% | 18/01/24 | 18/01/24 | 0 days | 18/01/24 | 18/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
6 | 1.3.6.4.3.5 |  |  |  |  | PIT execution | 100% | 15/12/23 | 23/02/24 | 51 days | 15/12/23 | 23/02/24 | 0 days | 0 days | -250 days | N/A |  | 5 | Yes
7 | 1.3.6.4.3.5.1 |  |  |  |  | PIT Test Execution Progress Reports | 100% | 18/12/23 | 09/02/24 | 40 days | 18/12/23 | 09/02/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.4.3.5.2 |  |  |  |  | PIT Execution | 100% | 15/12/23 | 09/02/24 | 41 days | 15/12/23 | 09/02/24 | 0 days | 0 days | -249 days | PP |  | 5 | Yes
7 | 1.3.6.4.3.5.3 | T3 | T3-DB-0087 | SITAG |  | All SIT Functional PIT Completion Reports submitted to Programme for Assurance | 100% | 09/02/24 | 09/02/24 | 0 days | 09/02/24 | 09/02/24 | 1 day | 0 days | 0 days | PP |  | 5.19 | Yes
7 | 1.3.6.4.3.5.4 | T3 | T3-DB-0142 | SITAG |  | All SIT Functional PIT Completion Reports MHHS Review Completed | 100% | 23/02/24 | 23/02/24 | 0 days | 23/02/24 | 23/02/24 | 1 day | 0 days | 0 days | SI Test |  | 5.19 | Yes
6 | 1.3.6.4.3.6 |  |  |  |  | All SIT Programme Participants PIT (SIT Migration) | 100% | 16/02/24 | 24/05/24 | 71 days | 16/02/24 | 24/05/24 | 0 days | 0 days | -230 days | N/A |  | 5.1 | Yes
7 | 1.3.6.4.3.6.1 |  |  |  |  | Test Approach & Plans | 100% | 16/02/24 | 11/04/24 | 40 days | 16/02/24 | 11/04/24 | 0 days | 0 days | 0 days | N/A |  | 5.2 | Yes
8 | 1.3.6.4.3.6.1.1 | T3 | T3-DB-0143 | SITAG |  | All SIT Migration PIT Test Approach & Plans submitted to Programme for assurance | 100% | 16/02/24 | 16/02/24 | 0 days | 16/02/24 | 16/02/24 | 0 days | -1 day | 0 days | PP |  | 5.8 | Yes
8 | 1.3.6.4.3.6.1.2 | T3 | T3-DB-0144 | SITAG |  | All SIT Migration PIT Test approach and plans MHHS Reviews Completed | 100% | 11/04/24 | 11/04/24 | 0 days | 11/04/24 | 11/04/24 | 1 day | 0 days | 0 days | SI Test |  | 5.23 | Yes
7 | 1.3.6.4.3.6.2 |  |  |  |  | Test Readiness Reports | 100% | 01/03/24 | 15/03/24 | 11 days | 01/03/24 | 15/03/24 | 0 days | 0 days | -40 days | N/A |  | 5.2 | Yes
8 | 1.3.6.4.3.6.2.1 |  |  |  |  | Test readiness reporting | 100% | 01/03/24 | 15/03/24 | 11 days | 01/03/24 | 15/03/24 | 0 days | 0 days | -40 days | PP |  | 5.2 | Yes
7 | 1.3.6.4.3.6.3 |  |  |  |  | Requirements to test Traceability Matrices (RTTM) | 100% | 07/03/24 | 18/04/24 | 30 days | 07/03/24 | 18/04/24 | 1 day | 0 days | 0 days | N/A |  | 5.2 | Yes
8 | 1.3.6.4.3.6.3.1 | T3 | T3-DB-0145 | SITAG |  | All SIT Migration PIT RTTMs submitted to Programme for assurance | 100% | 07/03/24 | 07/03/24 | 0 days | 07/03/24 | 07/03/24 | 1 day | 0 days | 0 days | PP |  | 5.23 | Yes
8 | 1.3.6.4.3.6.3.2 | T3 | T3-DB-0146 | SITAG |  | All SIT Migration RTTMs MHHS Reviews Completed | 100% | 18/04/24 | 18/04/24 | 0 days | 18/04/24 | 18/04/24 | 1 day | 0 days | 0 days | SI Test |  | 5.25 | Yes
7 | 1.3.6.4.3.6.4 |  |  |  |  | Test Scenarios | 100% | 07/03/24 | 18/04/24 | 30 days | 07/03/24 | 18/04/24 | 1 day | 0 days | 0 days | N/A |  | 5.2 | Yes
8 | 1.3.6.4.3.6.4.1 | T3 | T3-DB-0147 | SITAG |  | All SIT Migration PIT test scenarios submitted to Programme for assurance | 100% | 07/03/24 | 07/03/24 | 0 days | 07/03/24 | 07/03/24 | 1 day | 0 days | 0 days | PP |  | 5.23 | Yes
8 | 1.3.6.4.3.6.4.2 | T3 | T3-DB-0148 | SITAG |  | All SIT Migration Test scenarios MHHS Reviews Completed | 100% | 18/04/24 | 18/04/24 | 0 days | 18/04/24 | 18/04/24 | 1 day | 0 days | 0 days | SI Test |  | 5.25 | Yes
7 | 1.3.6.4.3.6.5 |  |  |  |  | PIT execution | 100% | 15/03/24 | 24/05/24 | 51 days | 15/03/24 | 24/05/24 | 0 days | 0 days | -250 days | N/A |  | 5.1 | Yes
8 | 1.3.6.4.3.6.5.1 |  |  |  |  | PIT Test Execution Progress Reports | 100% | 18/03/24 | 10/05/24 | 40 days | 18/03/24 | 10/05/24 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.3.6.4.3.6.5.2 |  |  |  |  | PIT Execution | 100% | 15/03/24 | 10/05/24 | 41 days | 15/03/24 | 10/05/24 | 0 days | 0 days | -249 days | PP |  | 5.1 | Yes
8 | 1.3.6.4.3.6.5.3 | T3 | T3-DB-0149 | SITAG |  | All SIT Migration PIT Completion Reports submitted to Programme for assurance | 100% | 10/05/24 | 10/05/24 | 0 days | 10/05/24 | 10/05/24 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
8 | 1.3.6.4.3.6.5.4 | T3 | T3-DB-0150 | SITAG |  | All SIT Migration PIT Completion Reports MHHS Review Completed | 100% | 24/05/24 | 24/05/24 | 0 days | 24/05/24 | 24/05/24 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
6 | 1.3.6.4.3.7 |  |  |  |  | All SIT Programme Participants PIT (SIT Non Functional) | 63% | 12/07/24 | 21/02/25 | 161 days | 12/07/24 | 20/12/24 | 0 days | 45 days | -140 days | N/A |  | 6 | Yes
7 | 1.3.6.4.3.7.1 |  |  |  |  | Test Approach & Plan | 0% | 27/09/24 | 22/11/24 | 41 days | 27/09/24 | 22/11/24 | 0 days | 0 days | 1 day | N/A |  | 6 | Yes
8 | 1.3.6.4.3.7.1.1 | T3 | T3-DB-0151 | SITAG |  | SIT Non-Functional PIT Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | 27/09/24 | 27/09/24 | 0 days | 27/09/24 | 27/09/24 | 0 days | -1 day | 0 days | PP |  | 6 | Yes
8 | 1.3.6.4.3.7.1.2 | T3 | T3-DB-0152 | SITAG |  | SIT Non-Functional Test approach and plan MHHS Review Completed | 0% | 21/11/24 | 22/11/24 | 1 day | 21/11/24 | 22/11/24 | 0 days | 0 days | 1 day | SI Test |  | 6 | Yes |  | 15/01/25 - 19/34 test approach reviews completed. RAG'd red because there are some outstanding comments by the programme on test approaches which have not been addressed by PPs, hence why this activity hasn't been completed yet.
7 | 1.3.6.4.3.7.2 |  |  |  |  | Test Readiness Report | 85% | 04/10/24 | 22/10/24 | 13 days | 04/10/24 | 22/10/24 | 0 days | 0 days | -38 days | N/A |  | 6 | Yes
8 | 1.3.6.4.3.7.2.1 |  |  |  |  | Test readiness reporting | 85% | 04/10/24 | 22/10/24 | 13 days | 04/10/24 | 22/10/24 | 0 days | 0 days | -38 days | PP |  | 6 | Yes
7 | 1.3.6.4.3.7.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 0% | 01/11/24 | 29/11/24 | 20 days | 01/11/24 | 29/11/24 | 1 day | 0 days | -10 days | N/A |  | 6 | Yes
8 | 1.3.6.4.3.7.3.1 | T3 | T3-DB-0153 | SITAG |  | SIT Non-Functional PIT RTTM submitted to Programme for assurance | 100% | 01/11/24 | 01/11/24 | 0 days | 01/11/24 | 01/11/24 | 1 day | 0 days | 0 days | PP |  | 6 | Yes
8 | 1.3.6.4.3.7.3.2 | T3 | T3-DB-0154 | SITAG |  | SIT Non-Functional RTTM MHHS Review Completed | 0% | 29/11/24 | 29/11/24 | 0 days | 29/11/24 | 29/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes |  | 15/01/25 -18/34 RTTMs reviews complete. Status red because Programme is still expecting responses to feedback from some PPs on PIT RTTMs and understands some of these will not be recieved by the 29/11/24 deadline.
7 | 1.3.6.4.3.7.4 |  |  |  |  | Test Scenarios | 0% | 01/11/24 | 29/11/24 | 20 days | 01/11/24 | 29/11/24 | 1 day | 0 days | -10 days | N/A |  | 6 | Yes
8 | 1.3.6.4.3.7.4.1 | T3 | T3-DB-0155 | SITAG |  | SIT Non-Functional PIT test scenarios submitted to Programme for assurance | 100% | 01/11/24 | 01/11/24 | 0 days | 01/11/24 | 01/11/24 | 1 day | 0 days | 0 days | PP |  | 6 | Yes
8 | 1.3.6.4.3.7.4.2 | T3 | T3-DB-0156 | SITAG |  | SIT Non-Functional Test scenarios MHHS Review Completed | 0% | 29/11/24 | 29/11/24 | 0 days | 29/11/24 | 29/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes |  | 15/01/25 - 21/34 scenarios have been completed.
7 | 1.3.6.4.3.7.5 |  |  |  |  | PIT execution | 61% | 12/07/24 | 21/02/25 | 161 days | 12/07/24 | 20/12/24 | 0 days | 45 days | -140 days | N/A |  | 6 | Yes
8 | 1.3.6.4.3.7.5.1 |  |  |  |  | PIT Test Execution Progress Report | 56% | 15/07/24 | 21/11/24 | 50 days | 15/07/24 | 21/11/24 | 0 days | 0 days | 11 days | PP |  | 6 | Yes
8 | 1.3.6.4.3.7.5.2 |  |  |  |  | PIT Execution | 66% | 12/07/24 | 29/11/24 | 44 days | 12/07/24 | 29/11/24 | 0 days | 0 days | -246 days | PP |  | 6 | Yes
8 | 1.3.6.4.3.7.5.3 | T3 | T3-DB-0157 | SITAG |  | SIT Non-Functional PIT Completion Report submitted to Programme for assurance | 0% | 29/11/24 | 29/11/24 | 0 days | 29/11/24 | 29/11/24 | 1 day | 0 days | 0 days | PP |  | 6 | Yes |  | 15/01/25 - 31/34 SIT Non-Functional PIT Completion Reports have been submitted to the Programme. Status red because not all PIT Completion Reports will be recieved by the baseline finish.
8 | 1.3.6.4.3.7.5.4 | T3 | T3-DB-0158 | SITAG |  | SIT Non-Functional PIT Completion Report Theme 1 MHHS Review Completed | 50% | 20/12/24 | 20/12/24 | 0 days | 20/12/24 | 20/12/24 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes |  | 15/01/25 - 1/2 Theme 1 Completion Reports assured by the Programme. Status red as report not available by 20/12, however the requirement for PIT completion report is not due until 21/01.
8 | 1.3.6.4.3.7.5.5 | T3 | T3-DB-0186 | SITAG |  | SIT Non-Functional PIT Completion Report Theme 2 & 3 MHHS Review Completed | 0% | 21/02/25 | 21/02/25 | 0 days | N/A | N/A | 0 days | 0 days | 0 days | SI Test |  | 6.13 | Yes |  | 15/01/25 - 10/34 Theme 2 & 3 Completion Reports assured by the Programme. Status green because the deadline for assurance 5s 21/02/24, as agreed at NFTWG.
6 | 1.3.6.4.3.8 |  |  |  |  | All SIT Programme Participants PIT (SIT Operational) | 46% | 12/07/24 | 31/01/25 | 146 days | 12/07/24 | 20/12/24 | 0 days | 30 days | 75 days | N/A |  | 6 | Yes
7 | 1.3.6.4.3.8.1 |  |  |  |  | Test Approach & Plan | 0% | 27/09/24 | 21/11/24 | 40 days | 27/09/24 | 21/11/24 | 0 days | 0 days | 0 days | N/A |  | 6 | Yes
8 | 1.3.6.4.3.8.1.1 | T3 | T3-DB-0159 | SITAG |  | SIT Operational PIT Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | 27/09/24 | 27/09/24 | 0 days | 27/09/24 | 27/09/24 | 0 days | -1 day | 0 days | PP |  | 6 | Yes |  | 15/01/25 - 33/34 test approach and plans have been submitted to the Programme, this however is complete because the final PP who have not submitted have a seperate approach and plan arragement agreed.
8 | 1.3.6.4.3.8.1.2 | T3 | T3-DB-0160 | SITAG |  | SIT Operational Test approach and plan MHHS Review Completed | 0% | 21/11/24 | 21/11/24 | 0 days | 21/11/24 | 21/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes |  | 15/01/25 - 26/34 reviewed. Status red because not all PIT test approach and plans will be recieved by the baseline finish. Revised version received requiring updates.
7 | 1.3.6.4.3.8.2 |  |  |  |  | Test Readiness Report | 42% | 04/10/24 | 22/10/24 | 13 days | 04/10/24 | 22/10/24 | 0 days | 0 days | -38 days | N/A |  | 6 | Yes
8 | 1.3.6.4.3.8.2.1 |  |  |  |  | Test readiness reporting | 42% | 04/10/24 | 22/10/24 | 13 days | 04/10/24 | 22/10/24 | 0 days | 0 days | -38 days | PP |  | 6 | Yes
7 | 1.3.6.4.3.8.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 0% | 01/11/24 | 29/11/24 | 20 days | 01/11/24 | 29/11/24 | 1 day | 0 days | -10 days | N/A |  | 6 | Yes
8 | 1.3.6.4.3.8.3.1 | T3 | T3-DB-0161 | SITAG |  | SIT Operational PIT RTTM submitted to Programme for assurance | 100% | 01/11/24 | 01/11/24 | 0 days | 01/11/24 | 01/11/24 | 1 day | 0 days | 0 days | PP |  | 6 | Yes |  | 15/01/25 - 33/34 SIT Operational PIT RTTMs have been submitted to the Programme, this however is complete because the final PP who have not submitted have a seperate appraoch and plan arragement agreed.
8 | 1.3.6.4.3.8.3.2 | T3 | T3-DB-0162 | SITAG |  | SIT Operational RTTM MHHS Review Completed | 0% | 29/11/24 | 29/11/24 | 0 days | 29/11/24 | 29/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes |  | 15/01/25 - 19/34 reviewed. RAG is red because velocity of RTTM returns by PPs means all reviews won't be completed in time for the baseline finish.
7 | 1.3.6.4.3.8.4 |  |  |  |  | Test Scenarios | 0% | 01/11/24 | 29/11/24 | 20 days | 01/11/24 | 29/11/24 | 1 day | 0 days | -10 days | N/A |  | 6 | Yes
8 | 1.3.6.4.3.8.4.1 | T3 | T3-DB-0163 | SITAG |  | SIT Operational PIT test scenarios submitted to Programme for assurance | 100% | 01/11/24 | 01/11/24 | 0 days | 01/11/24 | 01/11/24 | 1 day | 0 days | 0 days | PP |  | 6 | Yes |  | 15/01/25 - 33/34 SIT Operational PIT test scenarios have been submitted to the Programme, this however is complete because the final PP who have not submitted have a seperate approach and plan arragement agreed.
8 | 1.3.6.4.3.8.4.2 | T3 | T3-DB-0164 | SITAG |  | SIT Operational Test scenarios MHHS Review Completed | 0% | 29/11/24 | 29/11/24 | 0 days | 29/11/24 | 29/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes |  | 15/01/25 - 28/34 reviewed. RAG is red because velocity of test scenario returns by PPs means all reviews won't be completed in time for the baseline finish.
7 | 1.3.6.4.3.8.5 |  |  |  |  | PIT execution | 47% | 12/07/24 | 31/01/25 | 146 days | 12/07/24 | 20/12/24 | 0 days | 30 days | 95 days | N/A |  | 6 | Yes
8 | 1.3.6.4.3.8.5.1 |  |  |  |  | PIT Test Execution Progress Report | 45% | 15/07/24 | 21/11/24 | 40 days | 15/07/24 | 21/11/24 | 0 days | 0 days | 0 days | PP |  | 6 | Yes
8 | 1.3.6.4.3.8.5.2 |  |  |  |  | PIT Execution | 49% | 12/07/24 | 29/11/24 | 39 days | 12/07/24 | 29/11/24 | 0 days | 0 days | -2 days | PP |  | 6 | Yes
8 | 1.3.6.4.3.8.5.3 | T3 | T3-DB-0165 | SITAG |  | SIT Operational PIT Completion Report submitted to Programme for assurance | 0% | 10/01/25 | 10/01/25 | 0 days | 29/11/24 | 29/11/24 | 31 days | 30 days | 0 days | PP |  | 6 | Yes |  | 15/01/25 - 29/34 submitted. RAG is red because velocity of PIT Completion Report submissions by PPs means all reviews won't be completed in time for the baseline finish.
8 | 1.3.6.4.3.8.5.4 | T3 | T3-DB-0166 | SITAG |  | SIT Operational PIT Completion Report MHHS Review Completed | 0% | 31/01/25 | 31/01/25 | 0 days | 20/12/24 | 20/12/24 | 31 days | 30 days | 0 days | SI Test |  | 6 | Yes |  | 15/01/25 - 2/34 submitted. RAG is red because velocity of PIT Completion Report submissions by PPs means all reviews won't be completed in time for the baseline finish.
5 | 1.3.6.4.4 |  |  |  |  | All Suppliers DBT CIT (Entering at Interval 5) | 100% | 15/09/23 | 22/12/23 | 71 days | 15/09/23 | 22/12/23 | 0 days | 0 days | -229 days | N/A |  | 6 | Yes
6 | 1.3.6.4.4.1 |  |  |  |  | Test Approach & Plan | 100% | 15/09/23 | 12/10/23 | 20 days | 15/09/23 | 12/10/23 | 0 days | 0 days | 1 day | N/A |  | 6 | Yes
7 | 1.3.6.4.4.1.1 | T3 | T3-DB-0046 | SITAG |  | All SIT Suppliers Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | 15/09/23 | 15/09/23 | 0 days | 15/09/23 | 15/09/23 | 0 days | -1 day | 0 days | PP |  | 6 | Yes
7 | 1.3.6.4.4.1.2 | T3 | T3-DB-0167 | SITAG |  | All SIT Suppliers Test Approach & Plans MHHS Review Completed | 100% | 12/10/23 | 12/10/23 | 0 days | 12/10/23 | 12/10/23 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.3.6.4.4.2 |  |  |  |  | Test Readiness Report | 100% | 29/09/23 | 13/10/23 | 11 days | 29/09/23 | 13/10/23 | 0 days | 0 days | -40 days | N/A |  | 6 | Yes
7 | 1.3.6.4.4.2.1 |  |  |  |  | Test readiness reporting | 100% | 29/09/23 | 13/10/23 | 11 days | 29/09/23 | 13/10/23 | 0 days | 0 days | -40 days | PP |  | 6 | Yes
6 | 1.3.6.4.4.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | 06/10/23 | 03/11/23 | 20 days | 06/10/23 | 03/11/23 | 1 day | 0 days | -1 day | N/A |  | 6 | Yes
7 | 1.3.6.4.4.3.1 | T3 | T3-DB-0064 | SITAG | MHHS-ART009 | All SIT Suppliers RTTMs submitted to Programme for assurance | 100% | 06/10/23 | 06/10/23 | 0 days | 06/10/23 | 06/10/23 | 1 day | 0 days | -1 day | PP |  | 6 | Yes
7 | 1.3.6.4.4.3.2 | T3 | T3-DB-0168 | SITAG |  | All SIT Suppliers RTTMs MHHS Review Completed | 100% | 03/11/23 | 03/11/23 | 0 days | 03/11/23 | 03/11/23 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.3.6.4.4.4 |  |  |  |  | Test Scenarios | 100% | 05/10/23 | 02/11/23 | 20 days | 05/10/23 | 02/11/23 | 1 day | 0 days | 0 days | N/A |  | 6 | Yes
7 | 1.3.6.4.4.4.1 | T3 | T3-DB-0037 | SITAG |  | All SIT Suppliers test scenarios' submitted to Programme for assurance | 100% | 05/10/23 | 05/10/23 | 0 days | 05/10/23 | 05/10/23 | 1 day | 0 days | 0 days | PP |  | 6 | Yes
7 | 1.3.6.4.4.4.2 | T3 | T3-DB-0169 | SITAG |  | All SIT Suppliers Test scenarios' MHHS Review Completed | 100% | 02/11/23 | 02/11/23 | 0 days | 02/11/23 | 02/11/23 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.3.6.4.4.5 |  |  |  |  | PIT execution | 100% | 13/10/23 | 22/12/23 | 51 days | 13/10/23 | 22/12/23 | 0 days | 0 days | -249 days | N/A |  | 6 | Yes
7 | 1.3.6.4.4.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | 16/10/23 | 08/12/23 | 40 days | 16/10/23 | 08/12/23 | 0 days | 0 days | 0 days | PP |  | 6 | Yes
7 | 1.3.6.4.4.5.2 |  |  |  |  | PIT Execution | 100% | 13/10/23 | 08/12/23 | 41 days | 13/10/23 | 08/12/23 | 0 days | 0 days | -249 days | PP |  | 6 | Yes
7 | 1.3.6.4.4.5.3 | T3 | T3-DB-0170 | SITAG |  | All SIT Suppliers PIT Completion Reports submitted to Programme for assurance | 100% | 08/12/23 | 08/12/23 | 0 days | 08/12/23 | 08/12/23 | 1 day | 0 days | 0 days | PP |  | 6 | Yes
7 | 1.3.6.4.4.5.4 | T3 | T3-DB-0171 | SITAG |  | All SIT Suppliers PIT Completion Reports MHHS Review Completed | 100% | 22/12/23 | 22/12/23 | 0 days | 22/12/23 | 22/12/23 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
5 | 1.3.6.4.5 |  |  |  |  | All LDSO Network Operations DBT CIT (Entering at Interval 5) | 100% | 15/09/23 | 22/12/23 | 71 days | 15/09/23 | 22/12/23 | 0 days | 0 days | -239 days | N/A |  | 5 | Yes
6 | 1.3.6.4.5.1 |  |  |  |  | Test Approach & Plan | 100% | 15/09/23 | 22/12/23 | 71 days | 15/09/23 | 22/12/23 | 0 days | 0 days | -239 days | N/A |  | 5 | Yes
7 | 1.3.6.4.5.1.1 | T3 | T3-DB-0054 | SITAG |  | All Network Operation Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | 15/09/23 | 15/09/23 | 0 days | 15/09/23 | 15/09/23 | 0 days | -1 day | 0 days | PP |  | 5.8 | Yes
7 | 1.3.6.4.5.1.2 | T3 | T3-DB-0172 | SITAG |  | All Network Operation Test Approach & Plans MHHS Review Completed | 100% | 12/10/23 | 12/10/23 | 0 days | 12/10/23 | 12/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.8 | Yes
7 | 1.3.6.4.5.1.3 |  |  |  |  | Test Readiness Report | 100% | 29/09/23 | 13/10/23 | 11 days | 29/09/23 | 13/10/23 | 0 days | 0 days | -40 days | N/A |  | 5 | Yes
8 | 1.3.6.4.5.1.3.1 |  |  |  |  | Test readiness reporting | 100% | 29/09/23 | 13/10/23 | 11 days | 29/09/23 | 13/10/23 | 0 days | 0 days | -40 days | PP |  | 5 | Yes
7 | 1.3.6.4.5.1.4 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | 05/10/23 | 02/11/23 | 20 days | 05/10/23 | 02/11/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.3.6.4.5.1.4.1 | T3 | T3-DB-0062 | SITAG | MHHS-ART009 | All Network Operation RTTMs submitted to Programme for assurance | 100% | 05/10/23 | 05/10/23 | 0 days | 05/10/23 | 05/10/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
8 | 1.3.6.4.5.1.4.2 | T3 | T3-DB-0173 | SITAG |  | All Network Operation RTTMs MHHS Review Completed | 100% | 02/11/23 | 02/11/23 | 0 days | 02/11/23 | 02/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
7 | 1.3.6.4.5.1.5 |  |  |  |  | Test Scenarios | 100% | 05/10/23 | 02/11/23 | 20 days | 05/10/23 | 02/11/23 | 1 day | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.3.6.4.5.1.5.1 | T3 | T3-DB-0011 | SITAG |  | All Network Operation test scenarios' submitted to Programme for assurance | 100% | 05/10/23 | 05/10/23 | 0 days | 05/10/23 | 05/10/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
8 | 1.3.6.4.5.1.5.2 | T3 | T3-DB-0174 | SITAG |  | All Network Operation test scenarios' MHHS Review Completed | 100% | 02/11/23 | 02/11/23 | 0 days | 02/11/23 | 02/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
7 | 1.3.6.4.5.1.6 |  |  |  |  | PIT execution | 100% | 13/10/23 | 22/12/23 | 51 days | 13/10/23 | 22/12/23 | 0 days | 0 days | -259 days | N/A |  | 5 | Yes
8 | 1.3.6.4.5.1.6.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | 16/10/23 | 08/12/23 | 40 days | 16/10/23 | 08/12/23 | 0 days | 0 days | -265 days | PP |  | 5 | Yes
8 | 1.3.6.4.5.1.6.2 |  |  |  |  | PIT Execution | 100% | 13/10/23 | 08/12/23 | 41 days | 13/10/23 | 08/12/23 | 0 days | 0 days | -269 days | PP |  | 5 | Yes
8 | 1.3.6.4.5.1.6.3 | T3 | T3-DB-0175 | SITAG |  | All Network Operation PIT (CIT interval 5) Completion Reports submitted to Programme for assurance | 100% | 08/12/23 | 08/12/23 | 0 days | 08/12/23 | 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.3.6.4.5.1.6.4 | T3 | T3-DB-0176 | SITAG |  | All Network Operation PIT (CIT interval 5) Completion Reports MHHS Review Completed | 100% | 22/12/23 | 22/12/23 | 0 days | 22/12/23 | 22/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.15 | Yes
5 | 1.3.6.4.6 |  |  |  |  | All UMSO DBT CIT (Entering at Interval 6) | 100% | 29/09/23 | 19/01/24 | 81 days | 29/09/23 | 19/01/24 | 0 days | 0 days | -239 days | N/A |  | 5 | Yes
6 | 1.3.6.4.6.1 |  |  |  |  | Test Approach & Plan | 100% | 13/10/23 | 09/11/23 | 20 days | 13/10/23 | 09/11/23 | 0 days | 0 days | -20 days | N/A |  | 5 | Yes
7 | 1.3.6.4.6.1.1 | T3 | T3-DB-0052 | SITAG |  | All UMSO Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | 13/10/23 | 13/10/23 | 0 days | 13/10/23 | 13/10/23 | 0 days | -1 day | 0 days | PP |  | 5.11 | Yes
7 | 1.3.6.4.6.1.2 | T3 | T3-DB-0177 | SITAG |  | All UMSO Test Approach & Plans MHHS Review Completed | 100% | 09/11/23 | 09/11/23 | 0 days | 09/11/23 | 09/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.1 | Yes
6 | 1.3.6.4.6.2 |  |  |  |  | Test Readiness Report | 100% | 29/09/23 | 13/10/23 | 11 days | 29/09/23 | 13/10/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.4.6.2.1 |  |  |  |  | Test readiness reporting | 100% | 27/10/23 | 10/11/23 | 11 days | 27/10/23 | 10/11/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.6.4.6.3 |  |  |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | 05/10/23 | 01/11/23 | 20 days | 05/10/23 | 01/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.4.6.3.1 | T3 | T3-DB-0060 | SITAG | MHHS-ART009 | All UMSO RTTMs submitted to Programme for assurance | 100% | 02/11/23 | 02/11/23 | 0 days | 02/11/23 | 02/11/23 | 1 day | 0 days | 0 days | PP |  | 5.12 | Yes
7 | 1.3.6.4.6.3.2 | T3 | T3-DB-0178 | SITAG |  | All UMSO RTTMs MHHS Review Completed | 100% | 30/11/23 | 30/11/23 | 0 days | 30/11/23 | 30/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.12 | Yes
6 | 1.3.6.4.6.4 |  |  |  |  | Test Scenarios | 100% | 05/10/23 | 01/11/23 | 20 days | 05/10/23 | 01/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.3.6.4.6.4.1 | T3 | T3-DB-0025 | SITAG |  | All UMSO test scenarios' submitted to Programme for assurance | 100% | 02/11/23 | 02/11/23 | 0 days | 02/11/23 | 02/11/23 | 1 day | 0 days | 0 days | PP |  | 5.12 | Yes
7 | 1.3.6.4.6.4.2 | T3 | T3-DB-0179 | SITAG |  | All UMSO Test scenarios' MHHS Review Completed | 100% | 30/11/23 | 30/11/23 | 0 days | 30/11/23 | 30/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.1 | Yes
6 | 1.3.6.4.6.5 |  |  |  |  | PIT execution | 100% | 10/11/23 | 19/01/24 | 51 days | 10/11/23 | 19/01/24 | 0 days | 0 days | -269 days | N/A |  | 5 | Yes
7 | 1.3.6.4.6.5.1 |  |  |  |  | PIT Test Execution Progress Report | 100% | 13/11/23 | 05/01/24 | 40 days | 13/11/23 | 05/01/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.3.6.4.6.5.2 |  |  |  |  | PIT Execution | 100% | 10/11/23 | 04/01/24 | 40 days | 10/11/23 | 04/01/24 | 0 days | 0 days | -250 days | PP |  | 5 | Yes
7 | 1.3.6.4.6.5.3 | T3 | T3-DB-0180 | SITAG |  | All UMSO PIT (CIT interval 6) Completion Reports submitted to Programme for assurance | 100% | 05/01/24 | 05/01/24 | 0 days | 05/01/24 | 05/01/24 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.3.6.4.6.5.4 | T3 | T3-DB-0181 | SITAG |  | All UMSO PIT (CIT interval 6) Completion Reports MHHS Review Completed | 100% | 19/01/24 | 19/01/24 | 0 days | 19/01/24 | 19/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.1 | Yes
3 | 1.3.7 |  |  |  |  | DBT Monitoring and Assurance | 69% | 31/10/22 | 20/01/26 | 842 days | 31/10/22 | 20/01/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.3.7.1 |  |  |  |  | Planning and DBT Progress Monitoring of PPs | 67% | 31/10/22 | 30/06/25 | 696 days | 31/10/22 | 30/06/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.7.1.1 |  |  |  |  | Monitor Non-SIT PPs Planning and DBT1 progress (to inform confirmation of Qualification Testing Tranche participants milestones) | 67% | 31/10/22 | 30/06/25 | 696 days | 31/10/22 | 30/06/25 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
4 | 1.3.7.2 |  |  |  |  | DBT Progress Monitoring of Consequential Change | 51% | 02/02/23 | 20/01/26 | 774 days | 02/02/23 | 20/01/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.7.2.1 |  |  |  |  | Monitor & report data cleanse progress | 51% | 02/02/23 | 20/01/26 | 774 days | 02/02/23 | 20/01/26 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
4 | 1.3.7.3 |  |  |  |  | Design Assurance | 80% | 14/11/22 | 06/08/25 | 713 days | 14/11/22 | 06/08/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.7.3.1 |  |  |  |  | Design Assurance Readiness Assessment Preparation | 100% | 28/02/23 | 21/04/23 | 39 days | 28/02/23 | 21/04/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.3.1.1 |  |  |  |  | Set up FTIG | 100% | 03/04/23 | 21/04/23 | 15 days | 03/04/23 | 21/04/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.2 |  |  |  |  | Produce Draft Questions | 100% | 28/02/23 | 13/03/23 | 10 days | 28/02/23 | 13/03/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.3 |  |  |  |  | Pilot with SRO | 100% | 14/03/23 | 14/03/23 | 1 day | 14/03/23 | 14/03/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.4 |  |  |  |  | Finalise questions | 100% | 15/03/23 | 28/03/23 | 10 days | 15/03/23 | 28/03/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.5 |  |  |  |  | Prepare on-line RA tooling | 100% | 29/03/23 | 11/04/23 | 10 days | 29/03/23 | 11/04/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.6 |  |  |  |  | Prepare webinar content | 100% | 20/03/23 | 24/03/23 | 5 days | 20/03/23 | 24/03/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.1.7 |  |  |  |  | Conduct webinar | 100% | 30/03/23 | 30/03/23 | 1 day | 30/03/23 | 30/03/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.7.3.2 |  |  |  |  | Participant Design Assurance Approach | 100% | 14/11/22 | 11/01/23 | 43 days | 14/11/22 | 11/01/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.3.2.1 |  |  |  |  | Develop document | 100% | 14/11/22 | 09/12/22 | 20 days | 14/11/22 | 09/12/22 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.2.2 |  |  |  |  | Review document | 100% | 12/12/22 | 04/01/23 | 18 days | 12/12/22 | 04/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.7.3.2.3 | T3 | T3-DB-0012 | DAG |  | Participant Design Assurance Approach approved | 100% | 11/01/23 | 11/01/23 | 0 days | 11/01/23 | 11/01/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.3.7.3.3 |  |  |  |  | Phase 1 - SIT Volunteers (Core Providers) | 100% | 10/04/23 | 27/10/23 | 145 days | 10/04/23 | 27/10/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.3.3.1 |  |  |  |  | Send on-line questionnaire to core capability providers and current SIT volunteers (from Round 3 consultation) | 100% | 10/04/23 | 10/04/23 | 1 day | 10/04/23 | 10/04/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.3.2 |  |  |  |  | Participants Provide Responses to questionnaires | 100% | 11/04/23 | 01/05/23 | 15 days | 11/04/23 | 01/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.7.3.3.3 |  |  |  |  | Assess on-line responses and provided evidence | 100% | 02/05/23 | 08/05/23 | 5 days | 02/05/23 | 08/05/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.3.4 |  |  |  |  | Bi-lateral meeting with each responder, to walk and navigate through provided materials | 100% | 09/05/23 | 20/06/23 | 31 days | 09/05/23 | 20/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.3.5 |  |  |  |  | Plan for, create and execute deep dive assurance interviews based on agreed priorities (participants, design areas) | 100% | 07/06/23 | 31/08/23 | 62 days | 07/06/23 | 31/08/23 | 0 days | 0 days | 0 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.3.6 |  |  |  |  | SI endorsement of participants’ design – assurance reports | 100% | 02/08/23 | 29/09/23 | 43 days | 02/08/23 | 29/09/23 | 0 days | 0 days | 0 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.3.7 |  |  |  |  | Post-assurance review of recommendations take-up by assured participants | 100% | 29/08/23 | 27/10/23 | 44 days | 29/08/23 | 27/10/23 | 0 days | 0 days | 24 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.3.8 | T2 | T2-DB-0100 | DAG | MHHS-ART002 | Phase 1 - SIT Volunteers (Core Providers) complete | 100% | 27/10/23 | 27/10/23 | 0 days | 27/10/23 | 27/10/23 | 1 day | 0 days | 0 days | SI Design |  | 5.11 | Yes
5 | 1.3.7.3.4 |  |  |  |  | Phase 2 - SIT all other participants | 100% | 08/05/23 | 22/11/23 | 143 days | 08/05/23 | 22/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.3.4.1 |  |  |  |  | Send on-line questionnaire to core capability providers and current SIT volunteers (from Round 3 consultation) | 100% | 08/05/23 | 08/05/23 | 1 day | 08/05/23 | 08/05/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.4.2 |  |  |  |  | Participants Provide Responses to questionnaires | 100% | 09/05/23 | 29/05/23 | 15 days | 09/05/23 | 29/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.3.7.3.4.3 |  |  |  |  | Assess on-line responses and provided evidence | 100% | 30/05/23 | 05/06/23 | 5 days | 30/05/23 | 05/06/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.3.7.3.4.4 |  |  |  |  | Bi-lateral meeting with each responder, to walk and navigate through provided materials | 100% | 06/06/23 | 29/09/23 | 84 days | 06/06/23 | 29/09/23 | 0 days | 0 days | 0 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.4.5 |  |  |  |  | Plan for, create and execute deep dive assurance interviews based on agreed priorities (participants, design areas) | 100% | 27/06/23 | 29/09/23 | 69 days | 27/06/23 | 29/09/23 | 0 days | 0 days | 0 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.4.6 |  |  |  |  | SI endorsement of participants’ design – assurance reports | 100% | 18/07/23 | 29/09/23 | 54 days | 18/07/23 | 29/09/23 | 0 days | 0 days | 0 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.4.7 |  |  |  |  | Post-assurance review of recommendations take-up by assured participants | 100% | 14/08/23 | 22/11/23 | 73 days | 14/08/23 | 22/11/23 | 0 days | 0 days | 35 days | SI Design |  | 5.2 | Yes
6 | 1.3.7.3.4.8 | T2 | T2-DB-0200 | DAG | MHHS-ART002 | SIT PPs design assurance (excl Migration/Reverse Migration) complete | 100% | 22/11/23 | 22/11/23 | 0 days | 22/11/23 | 22/11/23 | 1 day | 0 days | 0 days | SI Design |  | 5.11 | Yes
5 | 1.3.7.3.5 |  |  |  |  | Non-SIT PPs design assurance | 53% | 23/11/23 | 06/08/25 | 445 days | 23/11/23 | 06/08/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.3.5.1 |  |  |  |  | Non-SIT PPs design assurance (risk-based sample) | 53% | 23/11/23 | 06/08/25 | 445 days | 23/11/23 | 06/08/25 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.3.7.4 |  |  |  |  | Test Assurance | 71% | 01/02/23 | 30/06/25 | 629 days | 01/02/23 | 30/06/25 | 0 days | 0 days | -67 days | N/A |  | 5 | Yes
5 | 1.3.7.4.1 |  |  |  |  | Non-SIT PPs test assurance | 71% | 01/02/23 | 30/06/25 | 629 days | 01/02/23 | 30/06/25 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
4 | 1.3.7.5 |  |  |  |  | Pre-Qualification Guidance (PIT Guidance) | 100% | 31/10/22 | 31/01/23 | 67 days | 31/10/22 | 31/01/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.3.7.5.1 |  |  |  |  | Develop document (incl. collaboration with code bodies, as required) | 100% | 31/10/22 | 16/01/23 | 56 days | 31/10/22 | 16/01/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.3.7.5.2 |  |  |  |  | Review, update and agree Pre-Qualification Guidance internally | 100% | 17/01/23 | 31/01/23 | 11 days | 17/01/23 | 31/01/23 | 0 days | 0 days | 0 days | SRO Function |  | 5 | Yes
4 | 1.3.7.6 |  |  |  |  | External Programme Dependency Management | 100% | 03/11/22 | 03/11/22 | 0 days | 03/11/22 | 03/11/22 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
5 | 1.3.7.6.1 |  |  |  |  | SLC47 | 100% | 03/11/22 | 03/11/22 | 0 days | 03/11/22 | 03/11/22 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
6 | 1.3.7.6.1.1 |  |  |  |  | SLC47 implementation date | 100% | 03/11/22 | 03/11/22 | 0 days | 03/11/22 | 03/11/22 | 0 days | -1 day | 0 days | Ofgem |  | 5 | Yes
2 | 1.4 |  |  | SITAG |  | SYSTEMS INTEGRATION TESTING (SIT) | 72% | 31/10/22 | 24/04/26 | 910 days? | 31/10/22 | 24/04/26 | 0 days | 0 days | 69 days? | N/A |  |  | Yes
3 | 1.4.1 |  |  | SITAG |  | SIT Preparation | 93% | 31/10/22 | 16/05/25 | 665 days? | 31/10/22 | 16/05/25 | 0 days | 0 days | 54 days? | N/A |  | 5 | Yes
4 | 1.4.1.1 |  |  |  |  | Test Artefact Development | 99% | 31/10/22 | 21/08/24 | 472 days | 31/10/22 | 21/08/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
5 | 1.4.1.1.1 |  |  |  |  | Environment Approach & Plan | 100% | 16/11/22 | 21/08/24 | 460 days | 16/11/22 | 21/08/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
6 | 1.4.1.1.1.1 | T3 | T3-TE-0010 | SITAG | MHHS-ART139 | Environment Approach & Plan approved | 100% | 16/11/22 | 16/11/22 | 0 days | 16/11/22 | 16/11/22 | 0 days | -1 day | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.1.2 |  |  |  |  | Environment Approach & Plan - Work Off | 100% | 17/11/22 | 23/06/23 | 157 days | 17/11/22 | 23/06/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.1.3 | T3 | T3-TE-0068 | SITAG | MHHS-ART139 | Environment Approach & Plan - Work Off Approved | 100% | 16/08/23 | 16/08/23 | 0 days | 16/08/23 | 16/08/23 | 0 days | -1 day | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.1.4 | T3 | T3-TE-0090 | SITAG | MHHS-DEL 618 | Environment Approach and Plan - SIT Functional | 100% | 20/11/23 | 20/11/23 | 0 days | 20/11/23 | 20/11/23 | 0 days | -1 day | 0 days | SI Test |  | 5.12 | Yes
6 | 1.4.1.1.1.5 |  |  |  |  | Define Approach to Simulator for Non-SIT LDSO | 100% | 15/11/23 | 15/11/23 | 0 days | 15/11/23 | 15/11/23 | 0 days | -1 day | 0 days | SI Test |  | 5.12 | Yes
6 | 1.4.1.1.1.6 | T3 | T3-TE-0091 | SITAG/QAG | MHHS-DEL 619 | Environment Approach and Plan - Non SIT LDSO Testing | 100% | 17/04/24 | 17/04/24 | 0 days | 17/04/24 | 17/04/24 | 0 days | -1 day | 0 days | SI Test |  | 5.22 | Yes
6 | 1.4.1.1.1.7 | T3 | T3-TE-0120 | SITAG/QAG | MHHS-DEL 619 | Environment Approach and Plan - S and A Testing | 100% | 17/07/24 | 17/07/24 | 0 days | 17/07/24 | 17/07/24 | 0 days | -1 day | 0 days | SI Test |  | 5.27 | Yes
6 | 1.4.1.1.1.8 | T3 | T3-TE-0092 | SITAG | MHHS-DEL 620 | Environment Approach and Plan - SIT Non Functional | 100% | 19/06/24 | 19/06/24 | 0 days | 19/06/24 | 19/06/24 | 0 days | -1 day | 0 days | SI Test |  | 5.27 | Yes
6 | 1.4.1.1.1.9 | T3 | T3-TE-0093 | SITAG/QAG | MHHS-DEL 621 | Environment Approach and Plan - Sandbox | 100% | 21/08/24 | 21/08/24 | 0 days | 21/08/24 | 21/08/24 | 0 days | -1 day | 0 days | SI Test |  | 5.27 | Yes
5 | 1.4.1.1.2 |  |  |  |  | Overarching Test Scope (for all stages) | 100% | 31/10/22 | 27/01/23 | 65 days | 31/10/22 | 27/01/23 | 0 days | 0 days | -110 days | N/A |  | 5 | Yes
6 | 1.4.1.1.2.1 |  |  |  |  | Overarching Test Scope (excl. Migration/Reverse Migration, NFT and Ops components) | 100% | 31/10/22 | 27/01/23 | 65 days | 31/10/22 | 27/01/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.1.2.1.1 |  |  |  |  | Develop document (excl Migration/Reverse Migration, NFT and Ops components) | 100% | 31/10/22 | 13/01/23 | 55 days | 31/10/22 | 13/01/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.1.2.1.2 |  |  |  |  | Review, update & agree document (excl Migration/Reverse Migration, NFT and Ops components) | 100% | 16/01/23 | 27/01/23 | 10 days | 16/01/23 | 27/01/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.1.3 |  |  |  |  | Configuration and Release Management Approach & Plan | 100% | 01/11/22 | 16/06/23 | 164 days | 01/11/22 | 16/06/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.1.1.3.1 |  |  |  |  | Develop document | 100% | 01/11/22 | 16/06/23 | 69 days | 01/11/22 | 16/06/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.3.2 |  |  |  |  | Review, update and agree Configuration and Release Management Approach & Plan internally | 100% | 01/02/23 | 28/04/23 | 63 days | 01/02/23 | 28/04/23 | 0 days | 0 days | 0 days | SRO Function |  | 5 | Yes
5 | 1.4.1.1.4 |  |  |  |  | Test Data Overarching Approach & Plan | 100% | 14/11/22 | 20/07/23 | 179 days | 14/11/22 | 20/07/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.1.1.4.1 |  |  |  |  | Develop document | 100% | 14/11/22 | 09/12/22 | 20 days | 14/11/22 | 09/12/22 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.4.2 |  |  |  |  | Document review and update | 100% | 12/12/22 | 14/07/23 | 155 days | 12/12/22 | 14/07/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.4.1.1.4.3 | T3 | T3-TE-0072 | SITAG |  | Test Data Overarching Approach & Plan approved by TMAG | 100% | 19/07/23 | 19/07/23 | 0 days | 19/07/23 | 19/07/23 | 1 day | 0 days | 0 days | SRO Test |  | 5 | Yes
6 | 1.4.1.1.4.4 |  |  |  |  | Document publication final version | 100% | 20/07/23 | 20/07/23 | 1 day | 20/07/23 | 20/07/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.1.5 |  |  |  |  | Interface Code of Connection (dates subject to DIP Service Provider's plan) | 100% | 01/03/23 | 05/05/23 | 48 days | 01/03/23 | 05/05/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.1.1.5.1 |  |  |  |  | Develop Interface Code of Connection with DIP Service Provider | 100% | 01/03/23 | 28/04/23 | 43 days | 01/03/23 | 28/04/23 | 0 days | 0 days | 0 days | DIP Provider |  | 5 | Yes
6 | 1.4.1.1.5.2 |  |  |  |  | Interface Code of Connection approved at SDWG | 100% | 05/05/23 | 05/05/23 | 0 days | 05/05/23 | 05/05/23 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.1.6 |  |  |  |  | Test Traceability | 98% | 01/06/23 | 17/01/24 | 165 days | 01/06/23 | 17/01/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.1.1.6.1 |  |  |  |  | RTM containing Method Statement Implied Requirements into Azure DevOps | 100% | 01/06/23 | 30/06/23 | 22 days | 01/06/23 | 30/06/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.6.2 |  |  |  |  | RTM Containing Interface Catalogue Implied Requirements | 100% | 01/06/23 | 07/07/23 | 27 days | 01/06/23 | 07/07/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.6.3 |  |  |  |  | SIT CIT Full Traceability & Coverage complete | 100% | 10/07/23 | 20/12/23 | 118 days | 10/07/23 | 20/12/23 | 0 days | 0 days | 8 days | SI Test |  | 5 | Yes
6 | 1.4.1.1.6.4 |  |  |  |  | SIT Functional Full Traceability & Coverage complete | 96% | 10/07/23 | 17/01/24 | 138 days | 10/07/23 | 17/01/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
4 | 1.4.1.2 |  |  |  |  | Test Tool Development | 100% | 31/10/22 | 23/10/23 | 256 days? | 31/10/22 | 23/10/23 | 0 days | 0 days | 81 days? | N/A |  | 5 | Yes
5 | 1.4.1.2.1 |  |  |  |  | Test Management Tool | 100% | 31/10/22 | 23/10/23 | 256 days | 31/10/22 | 23/10/23 | 0 days | 0 days | 81 days | N/A |  | 5 | Yes
6 | 1.4.1.2.1.1 |  |  |  |  | Test Management Tool Implementation | 100% | 31/10/22 | 23/10/23 | 256 days | 31/10/22 | 23/10/23 | 0 days | 0 days | 81 days | N/A |  | 5 | Yes
7 | 1.4.1.2.1.1.1 |  |  |  |  | Requirements identification | 100% | 31/10/22 | 23/12/22 | 40 days | 31/10/22 | 23/12/22 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.1.2 |  |  |  |  | Development | 100% | 02/01/23 | 23/06/23 | 125 days | 02/01/23 | 23/06/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.1.3 |  |  |  |  | Testing | 100% | 02/01/23 | 23/06/23 | 125 days | 02/01/23 | 23/06/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.1.4 |  |  |  |  | Accept tool | 100% | 23/06/23 | 23/06/23 | 0 days | 23/06/23 | 23/06/23 | 1 day | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.1.5 |  |  |  |  | Implementation | 100% | 23/10/23 | 23/10/23 | 1 day | 23/10/23 | 23/10/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
6 | 1.4.1.2.1.2 |  |  |  |  | Test Management Tool User Guide | 100% | 02/01/23 | 09/06/23 | 115 days | 02/01/23 | 09/06/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.2.1.2.1 |  |  |  |  | Develop document | 100% | 02/01/23 | 19/05/23 | 100 days | 02/01/23 | 19/05/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.2.2 |  |  |  |  | Review, update and agree Test Management Tool User Guide internally | 100% | 22/05/23 | 09/06/23 | 15 days | 22/05/23 | 09/06/23 | 0 days | 0 days | 0 days | SRO Function |  | 5 | Yes
6 | 1.4.1.2.1.3 |  |  |  |  | Test Management Tool Configuration Guide | 100% | 02/01/23 | 24/03/23 | 60 days | 02/01/23 | 24/03/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.2.1.3.1 |  |  |  |  | Develop document | 100% | 02/01/23 | 03/03/23 | 45 days | 02/01/23 | 03/03/23 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
7 | 1.4.1.2.1.3.2 |  |  |  |  | Review, update and agree Test Management Tool Configuration Guide internally | 100% | 06/03/23 | 24/03/23 | 15 days | 06/03/23 | 24/03/23 | 0 days | 0 days | 0 days | SRO Function |  | 5 | Yes
5 | 1.4.1.2.2 |  |  |  |  | Secure Volunteer SIT Participants | 100% | 31/01/23 | 14/09/23 | 163 days? | 31/01/23 | 14/09/23 | 0 days | 0 days | 163 days? |  |  | 6 | Yes
6 | 1.4.1.2.2.1 |  |  |  |  | PPs decide whether to volunteer to participate in SIT and inform Programme of decision via Round 3 Replan consultation | 100% | 31/01/23 | 31/01/23 | 1 day? | 31/01/23 | 31/01/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
6 | 1.4.1.2.2.2 |  |  |  |  | Assurance of SIT volunteers' plans (submitted via Round 3 Replan Consultation) | 100% | 14/02/23 | 14/02/23 | 1 day? | 14/02/23 | 14/02/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
6 | 1.4.1.2.2.3 |  |  |  |  | SIT Participant Volunteers Identified | 100% | 14/02/23 | 14/02/23 | 1 day? | 14/02/23 | 14/02/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
6 | 1.4.1.2.2.4 |  |  |  |  | Engagement with SIT volunteers | 100% | 23/05/23 | 23/05/23 | 1 day? | 23/05/23 | 23/05/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
6 | 1.4.1.2.2.5 |  |  |  |  | SIT Participants Agreed | 100% | 23/05/23 | 23/05/23 | 1 day? | 23/05/23 | 23/05/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
6 | 1.4.1.2.2.6 |  |  |  |  | Data Protection Impact Assessment (DPIA) | 100% | 30/06/23 | 14/07/23 | 11 days? | 30/06/23 | 14/07/23 | 0 days | 0 days | 11 days? | SI Test |  | 6 | Yes
7 | 1.4.1.2.2.6.1 |  |  |  |  | Conduct DPIA on Overall Test Data Approach | 100% | 30/06/23 | 30/06/23 | 1 day? | 30/06/23 | 30/06/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
7 | 1.4.1.2.2.6.2 |  |  |  |  | Revise Overarching Test Data Approach& plan for DPIA (if required), including engagement with DWG | 100% | 13/07/23 | 13/07/23 | 1 day? | 13/07/23 | 13/07/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
7 | 1.4.1.2.2.6.3 |  |  |  |  | Review (internal), update and approve revised Overarching Test Data Approach& Plan (if required) | 100% | 14/07/23 | 14/07/23 | 1 day? | 14/07/23 | 14/07/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
6 | 1.4.1.2.2.7 |  |  |  |  | Data Sharing Agreements | 100% | 04/08/23 | 14/09/23 | 30 days? | 04/08/23 | 14/09/23 | 0 days | 0 days | 30 days? | SI Test |  | 6 | Yes
7 | 1.4.1.2.2.7.1 |  |  |  |  | Produce Data Sharing Agreement for Industry Review | 100% | 04/08/23 | 04/08/23 | 1 day? | 04/08/23 | 04/08/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
7 | 1.4.1.2.2.7.2 |  |  |  |  | Manage Participant Queries and Contract Agreement Execution | 100% | 14/09/23 | 14/09/23 | 1 day? | 14/09/23 | 14/09/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
7 | 1.4.1.2.2.7.3 |  |  |  |  | Data Sharing Agreements Complete | 100% | 14/09/23 | 14/09/23 | 1 day? | 14/09/23 | 14/09/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
6 | 1.4.1.2.2.8 |  |  |  |  | Production Data Cut & Data Obfuscation | 100% | 19/06/23 | 01/09/23 | 55 days? | 19/06/23 | 01/09/23 | 0 days | 0 days | 55 days? |  |  | 6 | Yes
7 | 1.4.1.2.2.8.1 |  |  |  |  | SI Data Cut Preparation& Infrastructure | 100% | 19/06/23 | 18/08/23 | 45 days? | 19/06/23 | 18/08/23 | 0 days | 0 days | 45 days? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.1.1 |  |  |  |  | SI Data Cut Planning activities (incl. pre-cut and post-cut cleansing and population approach) | 100% | 19/06/23 | 19/06/23 | 1 day? | 19/06/23 | 19/06/23 | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.1.2 |  |  |  |  | Set up SI database and transmission structure | 100% | 17/08/23 | 17/08/23 | 1 day? | 17/08/23 | 17/08/23 | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.1.3 |  |  |  |  | Mechanism for transfer of data in place | 100% | 18/08/23 | 18/08/23 | 1 day? | 18/08/23 | 18/08/23 | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.1.4 |  |  |  |  | SI Data Cut Preparation& Infrastructure Complete | 100% | 18/08/23 | 18/08/23 | 1 day? | 18/08/23 | 18/08/23 | 0 days | 0 days | 1 day? |  |  | 6 | Yes
7 | 1.4.1.2.2.8.2 |  |  |  |  | Production Data Cut | 100% | 19/06/23 | 01/09/23 | 55 days? | 19/06/23 | 01/09/23 | 0 days | 0 days | 55 days? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.2.1 |  |  |  |  | Notification of Production Data Cut issued to relevant participants | 100% | 19/06/23 | 19/06/23 | 1 day? | 19/06/23 | 19/06/23 | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.2.2 |  |  |  |  | Coordinate relevant participants taking data cut from production systems | 100% | 11/08/23 | 11/08/23 | 1 day? | 11/08/23 | 11/08/23 | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.2.3 |  |  |  |  | Production data cut GONG decision | 100% | 16/08/23 | 16/08/23 | 1 day? | 16/08/23 | 16/08/23 | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.2.4 |  |  |  |  | Relevant participants take data cut from production systems (Saturday 19 August) | 100% | 21/08/23 | 21/08/23 | 1 day? | 21/08/23 | 21/08/23 | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.2.5 |  |  |  |  | EES transmit request data to SI | 100% | 25/08/23 | 25/08/23 | 1 day? | 25/08/23 | 25/08/23 | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.2.6 |  |  |  |  | Check data alignment and integrity of data cut | 100% | 01/09/23 | 01/09/23 | 1 day? | 01/09/23 | 01/09/23 | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.2.7 |  |  |  |  | Data cut from relevant participants' production systems completed (Saturday 19 August) | 100% | 21/08/23 | 21/08/23 | 1 day? | 21/08/23 | 21/08/23 | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.2.2.8.2.8 |  |  |  |  | Production Data Cut Complete | 100% | 21/08/23 | 21/08/23 | 1 day? | 21/08/23 | 21/08/23 | 0 days | 0 days | 1 day? |  |  | 6 | Yes
4 | 1.4.1.3 |  |  |  |  | SIT Participation | 100% | 31/10/22 | 23/05/23 | 147 days | 31/10/22 | 23/05/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.4.1.3.1 |  |  |  |  | PPs decide whether to volunteer to participate in SIT and inform Programme of decision via Round 3 Replan consultation | 100% | 31/10/22 | 31/01/23 | 67 days | 31/10/22 | 31/01/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.4.1.3.2 |  |  |  |  | Assurance of SIT volunteers' plans (submitted via Round 3 Replan Consultation) | 100% | 01/02/23 | 14/02/23 | 10 days | 01/02/23 | 14/02/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.3.3 | T2 | T2-TE-0100 | SITAG |  | SIT Participant Volunteers Identified | 100% | 14/02/23 | 14/02/23 | 0 days | 14/02/23 | 14/02/23 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.3.4 |  |  |  |  | Engagement with SIT volunteers | 100% | 31/10/22 | 23/05/23 | 147 days | 31/10/22 | 23/05/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.3.5 | T2 | T2-TE-0150 | SITAG |  | SIT Participants Agreed | 100% | 23/05/23 | 23/05/23 | 0 days | 23/05/23 | 23/05/23 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
4 | 1.4.1.4 |  |  | SITAG |  | SIT Stage-Specific Preparation | 91% | 31/10/22 | 16/05/25 | 665 days? | 31/10/22 | 16/05/25 | 0 days | 0 days | 54 days? | N/A |  | 5 | Yes
5 | 1.4.1.4.1 |  |  |  |  | SIT Component Integration Preparation | 100% | 31/10/22 | 19/01/24 | 320 days | 31/10/22 | 19/01/24 | 0 days | 0 days | -1 day | N/A |  | 5 | Yes
6 | 1.4.1.4.1.1 |  |  |  |  | Test Approach & Plan | 100% | 31/10/22 | 19/07/23 | 188 days | 31/10/22 | 19/07/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.1.1 |  |  |  |  | Develop document with SITWG | 100% | 31/10/22 | 08/06/23 | 159 days | 31/10/22 | 08/06/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.1.2 |  |  |  |  | Industry consultation | 100% | 09/06/23 | 22/06/23 | 10 days | 09/06/23 | 22/06/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.1.3 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | 23/06/23 | 19/07/23 | 19 days | 23/06/23 | 19/07/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.1.4 | T3 | T3-TE-0012 | SITAG | MHHS-ART073 | SIT Component Integration Testing Test Approach & Plan approved | 100% | 19/07/23 | 19/07/23 | 0 days | 19/07/23 | 19/07/23 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.1.2 |  |  |  |  | Test Data Approach & Plan | 100% | 09/06/23 | 19/07/23 | 29 days | 09/06/23 | 19/07/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.2.1 |  |  |  |  | Industry consultation | 100% | 09/06/23 | 22/06/23 | 10 days | 09/06/23 | 22/06/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.2.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | 23/06/23 | 19/07/23 | 19 days | 23/06/23 | 19/07/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.2.3 |  |  |  |  | SIT Component Integration Testing Test Data Approach & Plan approved | 100% | 19/07/23 | 19/07/23 | 0 days | 19/07/23 | 19/07/23 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.1.3 |  |  |  |  | Test scenarios | 100% | 02/01/23 | 30/08/23 | 173 days | 02/01/23 | 30/08/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.3.1 |  |  |  |  | Development of test scenarios | 100% | 02/01/23 | 28/04/23 | 0 days | 02/01/23 | 28/04/23 | 0 days | 0 days | -85 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.3.2 |  |  |  |  | Review test scenarios with SIT Working Group | 100% | 01/02/23 | 09/08/23 | 11 days | 01/02/23 | 09/08/23 | 0 days | 0 days | -125 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.3.3 | T3 | T3-TE-0014 | SITAG | MHHS-ART148 | SIT Component Integration Testing Test scenarios approved | 100% | 30/08/23 | 30/08/23 | 0 days | 30/08/23 | 30/08/23 | 1 day | 0 days | 0 days | SI Test |  | 5.6 | Yes
6 | 1.4.1.4.1.4 |  |  |  |  | Test cases | 100% | 01/05/23 | 08/12/23 | 160 days | 01/05/23 | 08/12/23 | 0 days | 0 days | 0 days | N/A |  | 5.6 | Yes
7 | 1.4.1.4.1.4.1 |  |  |  |  | SI Test cases | 100% | 01/05/23 | 08/12/23 | 160 days | 01/05/23 | 08/12/23 | 0 days | 0 days | 0 days | N/A |  | 5.6 | Yes
8 | 1.4.1.4.1.4.1.1 |  |  |  |  | Batch 1 (CIT Intervals 1 and 2) | 100% | 01/05/23 | 29/09/23 | 110 days | 01/05/23 | 29/09/23 | 0 days | 0 days | 0 days | N/A |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.1.1 |  |  |  |  | Develop Test cases | 100% | 01/05/23 | 15/09/23 | 100 days | 01/05/23 | 15/09/23 | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.1.2 |  |  |  |  | Review Test cases with SIT Working Group | 100% | 18/09/23 | 28/09/23 | 9 days | 18/09/23 | 28/09/23 | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.1.3 | T3 | T3-TE-0069 | SITAG | MHHS-ART073 | SIT Component Integration Testing Test cases Batch 1 (CIT Intervals 1 and 2) approved at ETMAG | 100% | 29/09/23 | 29/09/23 | 0 days | 29/09/23 | 29/09/23 | 1 day | 0 days | 0 days | SI Test |  | 5.6 | Yes
8 | 1.4.1.4.1.4.1.2 |  |  |  |  | Batch 2 (CIT Intervals 3 and 4) | 100% | 02/10/23 | 03/11/23 | 25 days | 02/10/23 | 03/11/23 | 0 days | 0 days | 0 days | N/A |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.2.1 |  |  |  |  | Develop Test cases | 100% | 02/10/23 | 20/10/23 | 15 days | 02/10/23 | 20/10/23 | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.2.2 |  |  |  |  | Review Test cases with SIT Working Group | 100% | 23/10/23 | 02/11/23 | 9 days | 23/10/23 | 02/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.2.3 | T3 | T3-TE-0104 | SITAG |  | SIT Component Integration Testing Test cases Batch 2 (CIT Intervals 3 and 4) approved at ETMAG | 100% | 03/11/23 | 03/11/23 | 0 days | 03/11/23 | 03/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.11 | Yes
8 | 1.4.1.4.1.4.1.3 |  |  |  |  | Batch 3 (CIT Intervals 5 and 6) | 100% | 03/11/23 | 08/12/23 | 25 days | 03/11/23 | 08/12/23 | 1 day | 0 days | 0 days | N/A |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.3.1 |  |  |  |  | Develop Test cases | 100% | 03/11/23 | 24/11/23 | 15 days | 03/11/23 | 24/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.3.2 |  |  |  |  | Review Test cases with SIT Working Group | 100% | 27/11/23 | 07/12/23 | 9 days | 27/11/23 | 07/12/23 | 0 days | 0 days | 0 days | SI Test |  | 5.6 | Yes
9 | 1.4.1.4.1.4.1.3.3 | T3 | T3-TE-0105 | SITAG |  | SIT Component Integration Testing Test cases Batch 3 (CIT Intervals 5 and 6) approved at ETMAG | 100% | 08/12/23 | 08/12/23 | 0 days | 08/12/23 | 08/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
6 | 1.4.1.4.1.5 |  |  |  |  | CIT Interval 1 Preparation | 100% | 16/11/22 | 15/12/23 | 283 days | 16/11/22 | 15/12/23 | 0 days | 0 days | 5 days | N/A |  | 5.6 | Yes
7 | 1.4.1.4.1.5.1 |  |  |  |  | Environments (SIT A) | 100% | 16/11/22 | 25/10/23 | 246 days | 16/11/22 | 25/10/23 | 0 days | 0 days | 7 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.5.1.1 |  |  |  |  | PPs register PKI Officers and request PKI certificates | 100% | 09/10/23 | 13/10/23 | 5 days | 09/10/23 | 13/10/23 | 0 days | 0 days | 0 days | PP |  | 5.5 | Yes
8 | 1.4.1.4.1.5.1.2 | T3 | T3-TE-0094 | SITAG |  | PPs register PKI Officers and request PKI certificates Complete - Interval 1 | 100% | 25/10/23 | 25/10/23 | 0 days | 25/10/23 | 25/10/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.5.1.3 |  |  |  |  | PP SIT A environment preparation (incl. security certificates and security compliance) | 100% | 16/11/22 | 13/10/23 | 238 days | 16/11/22 | 13/10/23 | 0 days | 0 days | 30 days | PP |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.4 |  |  |  |  | SI coordinate SIT Participants' SIT A environment preparation | 100% | 16/11/22 | 13/10/23 | 238 days | 16/11/22 | 13/10/23 | 0 days | 0 days | 30 days | SI Test |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.5 |  |  |  |  | PP submit self-declaration of environment preparation complete (incl. security certificates and security compliance) to Programme for assurance | 100% | 13/10/23 | 13/10/23 | 0 days | 13/10/23 | 13/10/23 | 1 day | 0 days | 0 days | PP |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.6 |  |  |  |  | SI assure PPs' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 100% | 16/10/23 | 20/10/23 | 5 days | 16/10/23 | 20/10/23 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.7 | T3 | T3-TE-0019 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 1 | 100% | 01/09/23 | 01/09/23 | 0 days | 01/09/23 | 01/09/23 | 1 day | 0 days | 0 days | PP |  | 5.6 | Yes
8 | 1.4.1.4.1.5.1.8 |  |  |  |  | PP SIT A environment connectivity proving | 100% | 04/09/23 | 15/09/23 | 10 days | 04/09/23 | 15/09/23 | 0 days | 0 days | -10 days | PP |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.9 |  |  |  |  | SI coordinate SIT Participants' SIT A environment connectivity proving | 100% | 04/09/23 | 15/09/23 | 10 days | 04/09/23 | 15/09/23 | 0 days | 0 days | -10 days | SI Test |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.10 |  |  |  |  | PP deployment of MHHS solution code to SIT A environments | 100% | 25/09/23 | 06/10/23 | 10 days | 25/09/23 | 06/10/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.5.1.11 |  |  |  |  | SI coordinate deployment of MHHS solution code to SIT Participants' SIT A environments | 100% | 25/09/23 | 06/10/23 | 10 days | 25/09/23 | 06/10/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.5.1.12 |  |  |  |  | PP submit evidence of SIT A environment connectivity proving and code deployment completion to Programme for assurance | 100% | 04/09/23 | 13/10/23 | 30 days | 04/09/23 | 13/10/23 | 0 days | 0 days | 10 days | PP |  | 5.8 | Yes
8 | 1.4.1.4.1.5.1.13 |  |  |  |  | SI assurance of SIT Participants' SIT A environment connectivity proving and code deployment completion | 100% | 18/09/23 | 20/10/23 | 25 days | 18/09/23 | 20/10/23 | 0 days | 0 days | 0 days | SI Test |  | 5.8 | Yes
7 | 1.4.1.4.1.5.2 |  |  |  |  | Test Data - ISD Creation | 100% | 22/08/23 | 01/09/23 | 9 days | 22/08/23 | 01/09/23 | 0 days | 0 days | 0 days | N/A |  | 5.5 | Yes
8 | 1.4.1.4.1.5.2.1 |  |  |  |  | Set-up Market Participants and DIP ID Data | 100% | 22/08/23 | 31/08/23 | 8 days | 22/08/23 | 31/08/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.2.2 |  |  |  |  | Distribute ISD Data to Participants | 100% | 01/09/23 | 01/09/23 | 1 day | 01/09/23 | 01/09/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.2.3 | T3 | T3-TE-0083 | SITAG |  | Test Data - ISD Creation Complete | 100% | 01/09/23 | 01/09/23 | 0 days | 01/09/23 | 01/09/23 | 1 day | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
7 | 1.4.1.4.1.5.3 |  |  |  |  | Test Data - SFTP Onboarding | 100% | 21/08/23 | 24/11/23 | 70 days | 21/08/23 | 24/11/23 | 0 days | 0 days | 0 days | N/A |  | 5.5 | Yes
8 | 1.4.1.4.1.5.3.1 |  |  |  |  | Create Containers and Keys for Participants | 100% | 21/08/23 | 23/08/23 | 3 days | 21/08/23 | 23/08/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.3.2 |  |  |  |  | Share SFTP Access with Participants | 100% | 24/08/23 | 30/08/23 | 5 days | 24/08/23 | 30/08/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.3.3 |  |  |  |  | Test SFTP Connectivity | 100% | 31/08/23 | 06/09/23 | 5 days | 31/08/23 | 06/09/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.3.4 | T3 | T3-TE-0084 | SITAG |  | Test Data - SFTP Onboarding Complete | 100% | 24/11/23 | 24/11/23 | 0 days | 24/11/23 | 24/11/23 | 1 day | 0 days | 0 days | SI Test Data |  | 5.13 | Yes
7 | 1.4.1.4.1.5.4 |  |  |  |  | Test Data - Provide Sample Files | 100% | 21/08/23 | 01/09/23 | 10 days | 21/08/23 | 01/09/23 | 0 days | 0 days | 0 days | N/A |  | 5.5 | Yes
8 | 1.4.1.4.1.5.4.1 |  |  |  |  | Generate Sample Files off IF Messages | 100% | 21/08/23 | 30/08/23 | 8 days | 21/08/23 | 30/08/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.4.2 |  |  |  |  | Transmit Sample Files off IF Messages to Participants (More detail needs to be planned for a POC) | 100% | 31/08/23 | 01/09/23 | 2 days | 31/08/23 | 01/09/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.4.3 | T3 | T3-TE-0085 | SITAG |  | Test Data - Provide Sample Files Complete | 100% | 01/09/23 | 01/09/23 | 0 days | 01/09/23 | 01/09/23 | 1 day | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
7 | 1.4.1.4.1.5.5 |  |  |  |  | Test Data - Detailed SIT Data Load Guidance | 100% | 07/09/23 | 06/12/23 | 65 days | 07/09/23 | 06/12/23 | 0 days | 0 days | 3 days | N/A |  | 5.5 | Yes
8 | 1.4.1.4.1.5.5.1 |  |  |  |  | Document Guidance | 100% | 07/09/23 | 05/10/23 | 21 days | 07/09/23 | 05/10/23 | 0 days | 0 days | 5 days | SI Test Data |  | 5.9 | Yes
8 | 1.4.1.4.1.5.5.2 |  |  |  |  | Provide Guidance to PPs | 100% | 06/10/23 | 06/10/23 | 1 day | 06/10/23 | 06/10/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.9 | Yes
8 | 1.4.1.4.1.5.5.3 | T3 | T3-TE-0095 | SITAG | MHHS-DEL 1545 | Test Data - Detailed SIT Functional Data Load Guidance Complete | 100% | 06/12/23 | 06/12/23 | 0 days | 06/12/23 | 06/12/23 | 1 day | 0 days | 0 days | SI Test Data |  | 5.13 | Yes
7 | 1.4.1.4.1.5.6 |  |  |  |  | Test Data - Population of Data Items for Testing Guidance - Draft | 100% | 17/08/23 | 06/12/23 | 80 days | 17/08/23 | 06/12/23 | 0 days | 0 days | 3 days | N/A |  | 5.5 | Yes
8 | 1.4.1.4.1.5.6.1 |  |  |  |  | Document Guidance - Draft | 100% | 17/08/23 | 31/08/23 | 11 days | 17/08/23 | 31/08/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.6 | Yes
8 | 1.4.1.4.1.5.6.2 |  |  |  |  | Provide Guidance to PPs - Draft | 100% | 01/09/23 | 01/09/23 | 1 day | 01/09/23 | 01/09/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.6 | Yes
8 | 1.4.1.4.1.5.6.3 | T3 | T3-TE-0096 | SITAG | MHHS-DEL 816 | Test Data - Population of Data Items for Testing Guidance - Draft Complete | 100% | 06/12/23 | 06/12/23 | 0 days | 06/12/23 | 06/12/23 | 1 day | 0 days | 0 days | SI Test Data |  | 5.13 | Yes
7 | 1.4.1.4.1.5.7 |  |  |  |  | Test Data - Population of Data Items for Testing Guidance - Final | 100% | 17/08/23 | 15/12/23 | 87 days | 17/08/23 | 15/12/23 | 0 days | 0 days | 42 days | N/A |  | 5.5 | Yes
8 | 1.4.1.4.1.5.7.1 |  |  |  |  | Update Document Guidance With PPS Feedback | 100% | 17/08/23 | 07/12/23 | 81 days | 17/08/23 | 07/12/23 | 0 days | 0 days | 37 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.7.2 |  |  |  |  | Provide Final Guidance to PPs | 100% | 08/12/23 | 08/12/23 | 1 day | 08/12/23 | 08/12/23 | 0 days | 0 days | 0 days | SI Test Data |  | 5.5 | Yes
8 | 1.4.1.4.1.5.7.3 | T3 | T3-TE-0097 | SITAG | MHHS-DEL 816 | Test Data - Population of Data Items for Testing Guidance - Final Complete | 100% | 15/12/23 | 15/12/23 | 0 days | 15/12/23 | 15/12/23 | 1 day | 0 days | 0 days | SI Test Data |  | 5.14 | Yes
7 | 1.4.1.4.1.5.8 |  |  |  |  | Test Data (SIT A) Interval 1 | 100% | 04/09/23 | 27/10/23 | 40 days | 04/09/23 | 27/10/23 | 0 days | 0 days | 20 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.5.8.1 |  |  |  |  | Run data allocation | 100% | 04/09/23 | 07/09/23 | 4 days | 04/09/23 | 07/09/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.5.8.2 |  |  |  |  | Cleanse, anonymise and populate data post cut | 100% | 08/09/23 | 13/09/23 | 4 days | 08/09/23 | 13/09/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.5.8.3 |  |  |  |  | Transmit data sets to PPs | 100% | 15/09/23 | 19/09/23 | 3 days | 15/09/23 | 19/09/23 | 0 days | 0 days | 2 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.5.8.4 |  |  |  |  | PP - Load test data to test environments | 100% | 20/09/23 | 28/09/23 | 7 days | 20/09/23 | 28/09/23 | 0 days | 0 days | 2 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.5.8.5 |  |  |  |  | PP Check data integrity on test environment | 100% | 29/09/23 | 29/09/23 | 1 day | 29/09/23 | 29/09/23 | 0 days | 0 days | -4 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.5.8.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | 29/09/23 | 29/09/23 | 0 days | 29/09/23 | 29/09/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.5.8.7 | T3 | T3-TE-0073 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 1 Complete | 100% | 27/10/23 | 27/10/23 | 0 days | 27/10/23 | 27/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.1 | Yes
7 | 1.4.1.4.1.5.9 |  |  |  |  | Other Preparation | 100% | 03/07/23 | 01/09/23 | 45 days | 03/07/23 | 01/09/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.5.9.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | 03/07/23 | 01/09/23 | 45 days | 03/07/23 | 01/09/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.5.9.2 |  |  |  |  | Test Management Tool onboarding | 100% | 03/07/23 | 01/09/23 | 45 days | 03/07/23 | 01/09/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.5.10 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | 14/09/23 | 23/10/23 | 28 days | 14/09/23 | 23/10/23 | 0 days | 0 days | 19 days | N/A |  | 5.6 | Yes
8 | 1.4.1.4.1.5.10.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | 20/10/23 | 20/10/23 | 0 days | 20/10/23 | 20/10/23 | 1 day | 0 days | 0 days | PP |  | 5.6 | Yes
8 | 1.4.1.4.1.5.10.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | 23/10/23 | 23/10/23 | 1 day | 23/10/23 | 23/10/23 | 0 days | 0 days | -4 days | SI Test |  | 5.6 | Yes
8 | 1.4.1.4.1.5.10.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | 14/09/23 | 16/10/23 | 23 days | 14/09/23 | 16/10/23 | 0 days | 0 days | 19 days | SI Test |  | 5.6 | Yes
8 | 1.4.1.4.1.5.10.4 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | 17/10/23 | 20/10/23 | 4 days | 17/10/23 | 20/10/23 | 0 days | 0 days | -1 day | SI Test |  | 5.6 | Yes
7 | 1.4.1.4.1.5.11 | T2 | T2-TE-0250 | SITAG | MHHS-ART071 | SIT Component Integration Testing 1 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | 27/10/23 | 27/10/23 | 0 days | 27/10/23 | 27/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.11 | Yes
6 | 1.4.1.4.1.6 |  |  |  |  | CIT Interval 2 Preparation | 100% | 03/07/23 | 22/11/23 | 103 days | 03/07/23 | 22/11/23 | 0 days | 0 days | 8 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.6.1 |  |  |  |  | Environments (SIT A) | 100% | 22/09/23 | 22/11/23 | 43 days | 22/09/23 | 22/11/23 | 1 day | 0 days | 8 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.6.1.1 | T3 | T3-TE-0020 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 2 | 100% | 22/09/23 | 22/09/23 | 0 days | 22/09/23 | 22/09/23 | 1 day | 0 days | 0 days | PP |  | 5.6 | Yes
8 | 1.4.1.4.1.6.1.2 |  |  |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | 22/09/23 | 22/09/23 | 0 days | 22/09/23 | 22/09/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.6.1.3 |  |  |  |  | Internal Connectivity Proving Phase | 100% | 25/09/23 | 06/10/23 | 10 days | 25/09/23 | 06/10/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.6.1.4 |  |  |  |  | Internal Connectivity Proving Phase Complete | 100% | 06/10/23 | 06/10/23 | 0 days | 06/10/23 | 06/10/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.6.1.5 |  |  |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | 16/10/23 | 22/11/23 | 28 days | 16/10/23 | 22/11/23 | 0 days | 0 days | 8 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.6.1.6 |  |  |  |  | DIP Onboarding Complete | 100% | 22/11/23 | 22/11/23 | 0 days | 22/11/23 | 22/11/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.6.1.7 | T3 | T3-TE-0098 | SITAG |  | PPs Register PKI Officers and request PKI certificates Complete - Interval 2 | 100% | 22/11/23 | 22/11/23 | 0 days | 22/11/23 | 22/11/23 | 1 day | 0 days | 0 days | PP |  | 5.15 | Yes
8 | 1.4.1.4.1.6.1.8 |  |  |  |  | PP Code Deployment | 100% | 20/10/23 | 20/10/23 | 0 days | 20/10/23 | 20/10/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.6.2 |  |  |  |  | Test Data (SIT A) Interval 2 | 100% | 20/09/23 | 17/11/23 | 43 days | 20/09/23 | 17/11/23 | 0 days | 0 days | 18 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.6.2.1 |  |  |  |  | Run data allocation | 100% | 20/09/23 | 28/09/23 | 7 days | 20/09/23 | 28/09/23 | 0 days | 0 days | 2 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.2.2 |  |  |  |  | Cleanse and populate data post cut | 100% | 29/09/23 | 02/10/23 | 2 days | 29/09/23 | 02/10/23 | 0 days | 0 days | -3 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.2.3 |  |  |  |  | Transmit data sets to PPs | 100% | 03/10/23 | 03/10/23 | 1 day | 03/10/23 | 03/10/23 | 0 days | 0 days | -1 day | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.2.4 |  |  |  |  | PP - Load test data to test environments | 100% | 04/10/23 | 17/11/23 | 33 days | 04/10/23 | 17/11/23 | 0 days | 0 days | 25 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.6.2.5 |  |  |  |  | PP Check data integrity on test environment | 100% | 23/10/23 | 17/11/23 | 15 days | 23/10/23 | 17/11/23 | 0 days | 0 days | 10 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.6.2.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | 17/11/23 | 17/11/23 | 0 days | 17/11/23 | 17/11/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.6.2.7 | T3 | T3-TE-0074 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 2 Complete | 100% | 17/11/23 | 17/11/23 | 0 days | 17/11/23 | 17/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.12 | Yes
7 | 1.4.1.4.1.6.3 |  |  |  |  | Other Preparation | 100% | 03/07/23 | 31/10/23 | 87 days | 03/07/23 | 31/10/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.6.3.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | 03/07/23 | 22/09/23 | 60 days | 03/07/23 | 22/09/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.3.2 |  |  |  |  | Test Management Tool onboarding | 100% | 25/09/23 | 31/10/23 | 27 days | 25/09/23 | 31/10/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.6.4 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | 02/10/23 | 03/11/23 | 25 days | 02/10/23 | 03/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.6.4.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | 25/10/23 | 25/10/23 | 0 days | 25/10/23 | 25/10/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.6.4.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | 26/10/23 | 27/10/23 | 2 days | 26/10/23 | 27/10/23 | 0 days | 0 days | -3 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.4.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | 02/10/23 | 27/10/23 | 20 days | 02/10/23 | 27/10/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.6.4.4 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | 30/10/23 | 03/11/23 | 5 days | 30/10/23 | 03/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.6.5 | T2 | T2-TE-0300 | SITAG | MHHS-ART071 | SIT Component Integration Testing 2 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | 06/11/23 | 06/11/23 | 0 days | 06/11/23 | 06/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.11 | Yes
6 | 1.4.1.4.1.7 |  |  |  |  | CIT Interval 3 Preparation | 100% | 03/10/23 | 15/12/23 | 54 days | 03/10/23 | 15/12/23 | 0 days | 0 days | -37 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.7.1 |  |  |  |  | PIT Test Completion Report (incl. evidence) | 100% | 13/10/23 | 17/11/23 | 26 days | 13/10/23 | 17/11/23 | 0 days | 0 days | 5 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.7.1.1 |  |  |  |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 100% | 13/10/23 | 27/10/23 | 11 days | 13/10/23 | 27/10/23 | 0 days | 0 days | 10 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.1.2 |  |  |  |  | Finalise PIT Test Completion Report (incl. evidence) | 100% | 30/10/23 | 03/11/23 | 5 days | 30/10/23 | 03/11/23 | 0 days | 0 days | -10 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.1.3 | T3 | T3-DB-0017 | SITAG |  | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 3 | 100% | 03/11/23 | 03/11/23 | 0 days | 03/11/23 | 03/11/23 | 1 day | 0 days | 0 days | PP |  | 5.11 | Yes
8 | 1.4.1.4.1.7.1.4 |  |  |  |  | PP Final PIT Completion Reports assured by SI | 100% | 06/11/23 | 17/11/23 | 10 days | 06/11/23 | 17/11/23 | 0 days | 0 days | 5 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.7.2 |  |  |  |  | Environments (SIT A) | 100% | 06/10/23 | 15/12/23 | 51 days | 06/10/23 | 15/12/23 | 0 days | 0 days | 25 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.7.2.1 |  |  |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | 06/10/23 | 06/10/23 | 0 days | 06/10/23 | 06/10/23 | 0 days | -1 day | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.2 | T3 | T3-TE-0021 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 3 | 100% | 06/10/23 | 06/10/23 | 0 days | 06/10/23 | 06/10/23 | 0 days | -1 day | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.3 |  |  |  |  | Internal Connectivity Proving Phase | 100% | 09/10/23 | 20/10/23 | 10 days | 09/10/23 | 20/10/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.4 |  |  |  |  | Internal Connectivity Proving Phase Complete | 100% | 20/10/23 | 20/10/23 | 0 days | 20/10/23 | 20/10/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.5 |  |  |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | 30/10/23 | 15/12/23 | 35 days | 30/10/23 | 15/12/23 | 0 days | 0 days | 25 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.6 |  |  |  |  | DIP Onboarding Complete | 100% | 15/12/23 | 15/12/23 | 0 days | 15/12/23 | 15/12/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.7.2.7 | T3 | T3-TE-0099 | SITAG |  | PPs Register PKI Officers and Request PKI certificates Complete - Interval 3 | 100% | 15/12/23 | 15/12/23 | 0 days | 15/12/23 | 15/12/23 | 1 day | 0 days | 0 days | PP |  | 5.13 | Yes
8 | 1.4.1.4.1.7.2.8 |  |  |  |  | PP Code Deployment | 100% | 10/11/23 | 10/11/23 | 0 days | 10/11/23 | 10/11/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.7.3 |  |  |  |  | Test Data (SIT A) Interval 3 | 100% | 03/10/23 | 17/11/23 | 34 days | 03/10/23 | 17/11/23 | 0 days | 0 days | 9 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.7.3.1 |  |  |  |  | Run data allocation | 100% | 03/10/23 | 06/10/23 | 4 days | 03/10/23 | 06/10/23 | 0 days | 0 days | -1 day | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.3.2 |  |  |  |  | Cleanse and populate data post cut | 100% | 09/10/23 | 13/10/23 | 5 days | 09/10/23 | 13/10/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.3.3 |  |  |  |  | Transmit data sets to PPs | 100% | 16/10/23 | 17/10/23 | 2 days | 16/10/23 | 17/10/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.3.4 |  |  |  |  | PP - Load test data to test environments | 100% | 18/10/23 | 27/10/23 | 8 days | 18/10/23 | 27/10/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.3.5 |  |  |  |  | PP Check data integrity on test environment | 100% | 30/10/23 | 17/11/23 | 15 days | 30/10/23 | 17/11/23 | 0 days | 0 days | 10 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.3.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | 17/11/23 | 17/11/23 | 0 days | 17/11/23 | 17/11/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.3.7 | T3 | T3-TE-0075 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 3 Complete | 100% | 17/11/23 | 17/11/23 | 0 days | 17/11/23 | 17/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.13 | Yes
7 | 1.4.1.4.1.7.4 |  |  |  |  | Other Preparation | 100% | 16/10/23 | 17/11/23 | 25 days | 16/10/23 | 17/11/23 | 0 days | 0 days | -35 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.7.4.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | 16/10/23 | 17/11/23 | 25 days | 16/10/23 | 17/11/23 | 0 days | 0 days | -35 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.4.2 |  |  |  |  | Test Management Tool onboarding | 100% | 16/10/23 | 17/11/23 | 25 days | 16/10/23 | 17/11/23 | 0 days | 0 days | -35 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.7.5 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | 16/10/23 | 17/11/23 | 25 days | 16/10/23 | 17/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.7.5.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | 03/11/23 | 03/11/23 | 0 days | 03/11/23 | 03/11/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.7.5.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | 06/11/23 | 10/11/23 | 5 days | 06/11/23 | 10/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.5.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | 16/10/23 | 10/11/23 | 20 days | 16/10/23 | 10/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.7.5.4 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | 13/11/23 | 17/11/23 | 5 days | 13/11/23 | 17/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.7.6 | T2 | T2-TE-0350 | SITAG | MHHS-ART071 | SIT Component Integration Testing 3 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | 20/11/23 | 20/11/23 | 0 days | 20/11/23 | 20/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.12 | Yes
6 | 1.4.1.4.1.8 |  |  |  |  | CIT Interval 4 Preparation | 100% | 16/10/23 | 04/12/23 | 36 days | 16/10/23 | 04/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.8.1 |  |  |  |  | PIT Test Completion Report (incl. evidence) | 100% | 27/10/23 | 24/11/23 | 21 days | 27/10/23 | 24/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.8.1.1 |  |  |  |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 100% | 27/10/23 | 27/10/23 | 1 day | 27/10/23 | 27/10/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.1.2 |  |  |  |  | Finalise PIT Test Completion Report (incl. evidence) | 100% | 30/10/23 | 17/11/23 | 15 days | 30/10/23 | 17/11/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.1.3 | T3 | T3-DB-0019 | SITAG |  | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 4 | 100% | 17/11/23 | 17/11/23 | 0 days | 17/11/23 | 17/11/23 | 1 day | 0 days | 0 days | PP |  | 5.13 | Yes
8 | 1.4.1.4.1.8.1.4 |  |  |  |  | PP Final PIT Completion Reports assured by SI | 100% | 20/11/23 | 24/11/23 | 5 days | 20/11/23 | 24/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.8.2 |  |  |  |  | Environments (SIT A) | 100% | 23/10/23 | 24/11/23 | 25 days | 23/10/23 | 24/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.8.2.1 |  |  |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | 23/10/23 | 23/10/23 | 0 days | 23/10/23 | 23/10/23 | 0 days | -1 day | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.2 | T3 | T3-TE-0022 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 4 | 100% | 23/10/23 | 23/10/23 | 0 days | 23/10/23 | 23/10/23 | 0 days | -1 day | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.3 |  |  |  |  | Internal Connectivity Proving Phase | 100% | 23/10/23 | 03/11/23 | 10 days | 23/10/23 | 03/11/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.4 |  |  |  |  | Internal Connectivity Proving Phase Complete | 100% | 03/11/23 | 03/11/23 | 0 days | 03/11/23 | 03/11/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.5 |  |  |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | 13/11/23 | 24/11/23 | 10 days | 13/11/23 | 24/11/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.6 |  |  |  |  | DIP Onboarding Complete | 100% | 24/11/23 | 24/11/23 | 0 days | 24/11/23 | 24/11/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.8.2.7 | T3 | T3-TE-0100 | SITAG |  | PPs register PKI Officers and Request PKI Certificates Complete - Interval 4 | 100% | 24/11/23 | 24/11/23 | 0 days | 24/11/23 | 24/11/23 | 1 day | 0 days | 0 days | PP |  | 5.16 | Yes
8 | 1.4.1.4.1.8.2.8 |  |  |  |  | PP Code Deployment | 100% | 17/11/23 | 17/11/23 | 0 days | 17/11/23 | 17/11/23 | 0 days | -1 day | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.8.3 |  |  |  |  | Test Data (SIT A) Interval 4 | 100% | 23/10/23 | 01/12/23 | 30 days | 23/10/23 | 01/12/23 | 0 days | 0 days | 5 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.8.3.1 |  |  |  |  | Run data allocation | 100% | 23/10/23 | 27/10/23 | 5 days | 23/10/23 | 27/10/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.3.2 |  |  |  |  | Cleanse and populate data post cut | 100% | 30/10/23 | 31/10/23 | 2 days | 30/10/23 | 31/10/23 | 0 days | 0 days | -3 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.3.3 |  |  |  |  | Transmit data sets to PPs | 100% | 01/11/23 | 07/11/23 | 5 days | 01/11/23 | 07/11/23 | 0 days | 0 days | 3 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.3.4 |  |  |  |  | PP - Load test data to test environments | 100% | 08/11/23 | 14/11/23 | 5 days | 08/11/23 | 14/11/23 | 0 days | 0 days | -3 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.3.5 |  |  |  |  | PP Check data integrity on test environment | 100% | 15/11/23 | 01/12/23 | 13 days | 15/11/23 | 01/12/23 | 0 days | 0 days | 8 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.3.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | 01/12/23 | 01/12/23 | 0 days | 01/12/23 | 01/12/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.3.7 | T3 | T3-TE-0076 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 4 Complete | 100% | 01/12/23 | 01/12/23 | 0 days | 01/12/23 | 01/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.13 | Yes
7 | 1.4.1.4.1.8.4 |  |  |  |  | Other Preparation | 100% | 30/10/23 | 01/12/23 | 25 days | 30/10/23 | 01/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.8.4.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | 30/10/23 | 01/12/23 | 25 days | 30/10/23 | 01/12/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.4.2 |  |  |  |  | Test Management Tool onboarding | 100% | 30/10/23 | 01/12/23 | 25 days | 30/10/23 | 01/12/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.8.5 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | 16/10/23 | 21/11/23 | 27 days | 16/10/23 | 21/11/23 | 0 days | 0 days | 2 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.8.5.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | 03/11/23 | 03/11/23 | 0 days | 03/11/23 | 03/11/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.8.5.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | 06/11/23 | 10/11/23 | 5 days | 06/11/23 | 10/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.5.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | 16/10/23 | 10/11/23 | 20 days | 16/10/23 | 10/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.8.5.4 |  |  |  |  | Artefact review (via SITAG) and updates | 100% | 13/11/23 | 21/11/23 | 7 days | 13/11/23 | 21/11/23 | 0 days | 0 days | 2 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.8.6 | T2 | T2-TE-0400 | SITAG | MHHS-ART071 | SIT Component Integration Testing 4 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | 04/12/23 | 04/12/23 | 0 days | 04/12/23 | 04/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.13 | Yes
6 | 1.4.1.4.1.9 |  |  |  |  | CIT Interval 5 Preparation | 100% | 01/11/23 | 12/01/24 | 53 days | 01/11/23 | 12/01/24 | 0 days | 0 days | -2 days | N/A |  | 5 | Yes
7 | 1.4.1.4.1.9.1 |  |  |  |  | PIT Test Completion Report (incl. evidence) | 100% | 17/11/23 | 15/12/23 | 21 days | 17/11/23 | 15/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.9.1.1 |  |  |  |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 100% | 17/11/23 | 17/11/23 | 1 day | 17/11/23 | 17/11/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.1.2 |  |  |  |  | Finalise PIT Test Completion Report (incl. evidence) | 100% | 20/11/23 | 08/12/23 | 15 days | 20/11/23 | 08/12/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.1.3 | T3 | T3-DB-0021 | SITAG |  | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 5 | 100% | 08/12/23 | 08/12/23 | 0 days | 08/12/23 | 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5.14 | Yes
8 | 1.4.1.4.1.9.1.4 |  |  |  |  | PP Final PIT Completion Reports assured by SI | 100% | 11/12/23 | 15/12/23 | 5 days | 11/12/23 | 15/12/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.9.2 |  |  |  |  | Environments (SIT A) | 100% | 10/11/23 | 08/12/23 | 21 days | 10/11/23 | 08/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.9.2.1 |  |  |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | 10/11/23 | 10/11/23 | 0 days | 10/11/23 | 10/11/23 | 0 days | -1 day | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.9.2.2 | T3 | T3-TE-0023 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 5 | 100% | 10/11/23 | 10/11/23 | 0 days | 10/11/23 | 10/11/23 | 0 days | -1 day | 0 days | PP |  | 5.6 | Yes
8 | 1.4.1.4.1.9.2.3 |  |  |  |  | Internal Connectivity Proving Phase | 100% | 13/11/23 | 24/11/23 | 10 days | 13/11/23 | 24/11/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.9.2.4 |  |  |  |  | Internal Connectivity Proving Phase Complete | 100% | 24/11/23 | 24/11/23 | 0 days | 24/11/23 | 24/11/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.9.2.5 |  |  |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | 27/11/23 | 08/12/23 | 10 days | 27/11/23 | 08/12/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.9.2.6 |  |  |  |  | DIP Onboarding Complete | 100% | 08/12/23 | 08/12/23 | 0 days | 08/12/23 | 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.9.2.7 | T3 | T3-TE-0101 | SITAG |  | PPs register PKI Officers and Request PKI Certificates Complete - Interval 5 | 100% | 08/12/23 | 08/12/23 | 0 days | 08/12/23 | 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5.17 | Yes
8 | 1.4.1.4.1.9.2.8 |  |  |  |  | PP Code Deployment | 100% | 08/12/23 | 08/12/23 | 0 days | 08/12/23 | 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.9.3 |  |  |  |  | Test Data (SIT A) Interval 5 | 100% | 01/11/23 | 15/12/23 | 33 days | 01/11/23 | 15/12/23 | 0 days | 0 days | 3 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.9.3.1 |  |  |  |  | Run data allocation | 100% | 01/11/23 | 07/11/23 | 5 days | 01/11/23 | 07/11/23 | 0 days | 0 days | -5 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.3.2 |  |  |  |  | Cleanse and populate data post cut | 100% | 08/11/23 | 17/11/23 | 8 days | 08/11/23 | 17/11/23 | 0 days | 0 days | 3 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.3.3 |  |  |  |  | Transmit data sets to PPs | 100% | 20/11/23 | 21/11/23 | 2 days | 20/11/23 | 21/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.3.4 |  |  |  |  | PP - Load test data to test environments | 100% | 22/11/23 | 01/12/23 | 8 days | 22/11/23 | 01/12/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.3.5 |  |  |  |  | PP Check data integrity on test environment | 100% | 04/12/23 | 15/12/23 | 10 days | 04/12/23 | 15/12/23 | 0 days | 0 days | 5 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.3.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | 15/12/23 | 15/12/23 | 0 days | 15/12/23 | 15/12/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.3.7 | T3 | T3-TE-0077 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 5 Complete | 100% | 15/12/23 | 15/12/23 | 0 days | 15/12/23 | 15/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
7 | 1.4.1.4.1.9.4 |  |  |  |  | Other Preparation | 100% | 20/11/23 | 12/01/24 | 40 days | 20/11/23 | 12/01/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.9.4.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | 20/11/23 | 12/01/24 | 40 days | 20/11/23 | 12/01/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.4.2 |  |  |  |  | Test Management Tool onboarding | 100% | 20/11/23 | 08/01/24 | 36 days | 20/11/23 | 08/01/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.9.5 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | 20/11/23 | 05/01/24 | 35 days | 20/11/23 | 05/01/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.9.5.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | 08/12/23 | 08/12/23 | 0 days | 08/12/23 | 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.9.5.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | 11/12/23 | 15/12/23 | 5 days | 11/12/23 | 15/12/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.5.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | 20/11/23 | 15/12/23 | 20 days | 20/11/23 | 15/12/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.9.5.4 |  |  |  |  | Artefact review (via SITAG) and updates | 100% | 18/12/23 | 05/01/24 | 15 days | 18/12/23 | 05/01/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.9.6 | T2 | T2-TE-0450 | SITAG | MHHS-ART071 | SIT Component Integration Testing 5 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | 08/01/24 | 08/01/24 | 0 days | 08/01/24 | 08/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.15 | Yes
6 | 1.4.1.4.1.10 |  |  |  |  | CIT Interval 6 Preparation | 100% | 20/11/23 | 19/01/24 | 45 days | 20/11/23 | 19/01/24 | 0 days | 0 days | -1 day | N/A |  | 5 | Yes
7 | 1.4.1.4.1.10.1 |  |  |  |  | PIT Test Completion Report (incl. evidence) | 100% | 01/12/23 | 12/01/24 | 31 days | 01/12/23 | 12/01/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.10.1.1 |  |  |  |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 100% | 01/12/23 | 01/12/23 | 1 day | 01/12/23 | 01/12/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.1.2 |  |  |  |  | Finalise PIT Test Completion Report (incl. evidence) | 100% | 04/12/23 | 05/01/24 | 25 days | 04/12/23 | 05/01/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.1.3 | T3 | T3-DB-0023 | SITAG |  | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 6 | 100% | 05/01/24 | 05/01/24 | 0 days | 05/01/24 | 05/01/24 | 1 day | 0 days | 0 days | PP |  | 5.19 | Yes
8 | 1.4.1.4.1.10.1.4 |  |  |  |  | PP Final PIT Completion Reports assured by SI | 100% | 08/01/24 | 12/01/24 | 5 days | 08/01/24 | 12/01/24 | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes
7 | 1.4.1.4.1.10.2 |  |  |  |  | Environments (SIT A) | 100% | 24/11/23 | 05/01/24 | 30 days | 24/11/23 | 05/01/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.10.2.1 |  |  |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | 24/11/23 | 24/11/23 | 0 days | 24/11/23 | 24/11/23 | 0 days | -1 day | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.10.2.2 | T3 | T3-TE-0024 | SITAG | MHHS-ART139 | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 6 | 100% | 24/11/23 | 24/11/23 | 0 days | 24/11/23 | 24/11/23 | 0 days | -1 day | 0 days | PP |  | 5.6 | Yes
8 | 1.4.1.4.1.10.2.3 |  |  |  |  | Internal Connectivity Proving Phase | 100% | 27/11/23 | 08/12/23 | 10 days | 27/11/23 | 08/12/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.10.2.4 |  |  |  |  | Internal Connectivity Proving Phase Complete | 100% | 08/12/23 | 08/12/23 | 0 days | 08/12/23 | 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.10.2.5 |  |  |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | 04/12/23 | 08/12/23 | 5 days | 04/12/23 | 08/12/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.10.2.6 |  |  |  |  | DIP Onboarding Complete | 100% | 08/12/23 | 08/12/23 | 0 days | 08/12/23 | 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5.1 | Yes
8 | 1.4.1.4.1.10.2.7 | T3 | T3-TE-0102 | SITAG |  | PPs register PKI Officers and Request PKI Certificates Complete - Interval 6 | 100% | 08/12/23 | 08/12/23 | 0 days | 08/12/23 | 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5.17 | Yes
8 | 1.4.1.4.1.10.2.8 |  |  |  |  | PP Code Deployment | 100% | 05/01/24 | 05/01/24 | 0 days | 05/01/24 | 05/01/24 | 0 days | -1 day | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.1.10.3 |  |  |  |  | Test Data (SIT A) Interval 6 | 100% | 20/11/23 | 22/12/23 | 25 days | 20/11/23 | 22/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.10.3.1 |  |  |  |  | Run data allocation | 100% | 20/11/23 | 01/12/23 | 10 days | 20/11/23 | 01/12/23 | 0 days | 0 days | 5 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.3.2 |  |  |  |  | Cleanse and populate data post cut | 100% | 04/12/23 | 04/12/23 | 1 day | 04/12/23 | 04/12/23 | 0 days | 0 days | -4 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.3.3 |  |  |  |  | Transmit data sets to PPs | 100% | 05/12/23 | 05/12/23 | 1 day | 05/12/23 | 05/12/23 | 0 days | 0 days | -1 day | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.3.4 |  |  |  |  | PP - Load test data to test environments | 100% | 06/12/23 | 15/12/23 | 8 days | 06/12/23 | 15/12/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.3.5 |  |  |  |  | PP Check data integrity on test environment | 100% | 18/12/23 | 22/12/23 | 5 days | 18/12/23 | 22/12/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.3.6 |  |  |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | 22/12/23 | 22/12/23 | 0 days | 22/12/23 | 22/12/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.3.7 | T3 | T3-TE-0078 | SITAG | MHHS-ART148/169 | Test Data (SIT A) Interval 6 Complete | 100% | 22/12/23 | 22/12/23 | 0 days | 22/12/23 | 22/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.5 | Yes
7 | 1.4.1.4.1.10.4 |  |  |  |  | Other Preparation | 100% | 04/12/23 | 15/01/24 | 31 days | 04/12/23 | 15/01/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.10.4.1 |  |  |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | 04/12/23 | 15/01/24 | 31 days | 04/12/23 | 15/01/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.4.2 |  |  |  |  | Test Management Tool onboarding | 100% | 04/12/23 | 15/01/24 | 31 days | 04/12/23 | 15/01/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.1.10.5 |  |  |  |  | SIT Component Integration Test Readiness Report | 100% | 20/11/23 | 22/12/23 | 25 days | 20/11/23 | 22/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.1.10.5.1 |  |  |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | 08/12/23 | 08/12/23 | 0 days | 08/12/23 | 08/12/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.1.10.5.2 |  |  |  |  | SI assure Test Participants' Test Readiness Reports | 100% | 11/12/23 | 15/12/23 | 5 days | 11/12/23 | 15/12/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.5.3 |  |  |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | 20/11/23 | 15/12/23 | 20 days | 20/11/23 | 15/12/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.1.10.5.4 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | 18/12/23 | 22/12/23 | 5 days | 18/12/23 | 22/12/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.1.10.6 | T2 | T2-TE-0500 | SITAG | MHHS-ART071 | SIT Component Integration Testing 6 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | 19/01/24 | 19/01/24 | 0 days | 19/01/24 | 19/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.15 | Yes
5 | 1.4.1.4.2 |  |  | SITAG |  | SIT Functional Preparation | 100% | 31/10/22 | 07/02/25 | 595 days? | 31/10/22 | 07/04/25 | 0 days | -41 days | 75 days? | N/A |  | 5 | Yes
6 | 1.4.1.4.2.1 |  |  |  |  | Environment Approach and Plan - SIT Functional | 100% | 20/11/23 | 20/11/23 | 1 day? | 20/11/23 | 20/11/23 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
6 | 1.4.1.4.2.2 |  |  |  |  | Test Approach & Plan | 100% | 31/10/22 | 16/08/23 | 208 days | 31/10/22 | 16/08/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.2.2.1 |  |  |  |  | Develop document with SITWG | 100% | 31/10/22 | 06/07/23 | 179 days | 31/10/22 | 06/07/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.2.2.2 |  |  |  |  | Industry Consultation | 100% | 07/07/23 | 20/07/23 | 10 days | 07/07/23 | 20/07/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.2.2.3 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | 21/07/23 | 16/08/23 | 19 days | 21/07/23 | 16/08/23 | 0 days | 0 days | 0 days | SI Test |  | 5.5 | Yes
7 | 1.4.1.4.2.2.4 | T3 | T3-TE-0013 | SITAG | MHHS-ART073 | SIT Functional Test Approach & Plan approved | 100% | 16/08/23 | 16/08/23 | 0 days | 16/08/23 | 16/08/23 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.2.3 |  |  |  |  | Test Data Approach & Plan | 100% | 07/07/23 | 16/08/23 | 29 days | 07/07/23 | 16/08/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.2.3.1 |  |  |  |  | Industry Consultation | 100% | 07/07/23 | 20/07/23 | 10 days | 07/07/23 | 20/07/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.2.3.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | 21/07/23 | 16/08/23 | 19 days | 21/07/23 | 16/08/23 | 0 days | 0 days | 0 days | SI Test |  | 5.5 | Yes
7 | 1.4.1.4.2.3.3 |  |  |  |  | SIT Functional Testing Test Data Approach & Plan approved | 100% | 16/08/23 | 16/08/23 | 0 days | 16/08/23 | 16/08/23 | 1 day | 0 days | 0 days | SI Test |  | 5.5 | Yes
6 | 1.4.1.4.2.4 |  |  |  |  | Test scenarios | 100% | 02/01/23 | 21/02/24 | 298 days | 02/01/23 | 21/02/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.2.4.1 |  |  |  |  | Development of test scenarios | 100% | 02/01/23 | 28/04/23 | 85 days | 02/01/23 | 28/04/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.2.4.2 |  |  |  |  | Review test scenarios with SIT Working Group | 100% | 17/08/23 | 15/11/23 | 65 days | 17/08/23 | 15/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.2.4.3 | T3 | T3-TE-0015 | SITAG | MMHS-ART073 | SIT Functional Testing Test scenarios (themes 1-5) approved | 100% | 08/12/23 | 08/12/23 | 0 days | 08/12/23 | 08/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
7 | 1.4.1.4.2.4.4 | T3 | T3-TE-0106 | SITAG | MMHS-ART073 | SIT Functional Testing Test scenarios (themes 6,7,9) approved | 100% | 17/01/24 | 17/01/24 | 0 days | 17/01/24 | 17/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.16 | Yes
7 | 1.4.1.4.2.4.5 | T3 | T3-TE-0107 | SITAG | MMHS-ART073 | SIT Functional Testing Test scenarios (theme 8) approved | 100% | 21/02/24 | 21/02/24 | 0 days | 21/02/24 | 21/02/24 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
6 | 1.4.1.4.2.5 |  |  |  |  | Test cases | 100% | 01/05/23 | 07/02/25 | 465 days? | 01/05/23 | 07/02/25 | 0 days | 0 days | 252 days? | N/A |  | 5 | Yes
7 | 1.4.1.4.2.5.1 |  |  |  |  | SI Test cases | 100% | 01/05/23 | 21/02/24 | 213 days | 01/05/23 | 21/02/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.2.5.1.1 |  |  |  |  | Development of Test cases | 100% | 01/05/23 | 24/11/23 | 150 days | 01/05/23 | 24/11/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.2.5.1.2 |  |  |  |  | Review Test cases with SIT Working Group | 100% | 25/09/23 | 10/01/24 | 78 days | 25/09/23 | 10/01/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.2.5.1.3 | T3 | T3-TE-0070 | SITAG | MHHS-ART140 | SIT Functional Testing Test Cases (themes 1-5) approved | 100% | 17/01/24 | 17/01/24 | 0 days | 17/01/24 | 17/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
8 | 1.4.1.4.2.5.1.4 | T3 | T3-TE-0108 | SITAG | MHHS-ART140 | SIT Functional Testing Test cases (themes 6,7,9) approved | 100% | 17/01/24 | 17/01/24 | 0 days | 17/01/24 | 17/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
8 | 1.4.1.4.2.5.1.5 | T3 | T3-TE-0109 | SITAG | MHHS-ART140 | SIT Functional Testing Test cases (theme 8) approved | 100% | 21/02/24 | 21/02/24 | 0 days | 21/02/24 | 21/02/24 | 1 day | 0 days | 0 days | SI Test |  | 5.14 | Yes
7 | 1.4.1.4.2.5.2 |  |  | SITAG |  | SIT Functional Programme RTTM | 100% | 29/07/24 | 07/11/24 | 74 days? | 29/07/24 | 11/10/24 | 0 days | 19 days | 74 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.2.1 |  |  | SITAG |  | RTTM Development | 100% | 29/07/24 | 06/09/24 | 30 days? | 29/07/24 | 20/09/24 | 0 days | -10 days | 30 days? | SI Test |  | 6 | Yes
9 | 1.4.1.4.2.5.2.1.1 |  |  | SITAG |  | Development of Manual SIT Functional RTTM | 100% | 29/07/24 | 06/09/24 | 30 days? | 29/07/24 | 06/09/24 | 0 days | 0 days | 30 days? | SI Test |  | 6 | Yes
9 | 1.4.1.4.2.5.2.1.2 |  |  | SITAG |  | Manual SIT Functional RTTM Complete | 100% | 06/09/24 | 06/09/24 | 0 days? | 06/09/24 | 06/09/24 | 1 day | 0 days | 0 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.2.2 |  |  | SITAG |  | Gap analysis | 100% | 26/08/24 | 07/11/24 | 54 days? | 26/08/24 | 11/10/24 | 0 days | 19 days | 54 days? | SI Test |  | 6 | Yes
9 | 1.4.1.4.2.5.2.2.1 |  |  | SITAG |  | Identify gaps in test case coverage following RTTM review | 100% | 26/08/24 | 20/09/24 | 20 days? | 26/08/24 | 20/09/24 | 0 days | 0 days | 20 days? | SI Test |  | 6 | Yes
9 | 1.4.1.4.2.5.2.2.2 |  |  | SITAG |  | Address gaps in test case coverage following RTTM review | 100% | 09/09/24 | 11/10/24 | 25 days | 09/09/24 | 04/10/24 | 0 days | 5 days | 25 days | SI Test |  | 6 | Yes
9 | 1.4.1.4.2.5.2.2.3 |  |  | SITAG |  | Gap analysis complete | 100% | 11/10/24 | 11/10/24 | 0 days | 11/10/24 | 11/10/24 | 1 day | 0 days | 0 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.4 |  |  | SITAG |  | Test Script updates identified | 100% | 14/10/24 | 14/10/24 | 1 day? | 14/10/24 | 14/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.5 |  |  | SITAG |  | Test Scripts updates | 100% | 15/10/24 | 15/10/24 | 1 day | 15/10/24 | 15/10/24 | 0 days | 0 days | 1 day | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.6 |  |  | SITAG |  | RTTM Updated Additional Static RTTM WBS items | 100% | 14/10/24 | 25/10/24 | 10 days | 14/10/24 | 25/10/24 | 0 days | 0 days | 10 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.7 |  |  | SITAG |  | Removal of de-scoped TCs from the RTTMs | 100% | 21/10/24 | 25/10/24 | 5 days | 21/10/24 | 25/10/24 | 0 days | 0 days | 5 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.8 |  |  | SITAG |  | Update and stabilisation of all TC ADO IDs | 100% | 21/10/24 | 07/11/24 | 14 days | 21/10/24 | 25/10/24 | 0 days | 9 days | 14 days | SI Test |  | 6.12 | Yes
9 | 1.4.1.4.2.5.2.2.9 |  |  | SITAG |  | Addition and integration of Role tags to reqs in the Role RTTMs | 100% | 21/10/24 | 25/10/24 | 5 days | 21/10/24 | 25/10/24 | 0 days | 0 days | 5 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.10 |  |  | SITAG |  | Update of the RTTM All sheet (porting of the individual RTTMs) | 100% | 24/10/24 | 01/11/24 | 7 days | 24/10/24 | 25/10/24 | 0 days | 5 days | 7 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.11 |  |  | SITAG |  | Define Additional ADO Tags | 100% | 23/10/24 | 23/10/24 | 1 day | 23/10/24 | 23/10/24 | 0 days | 0 days | 1 day | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.12 |  |  | SITAG |  | Functional RTTM ready for import into ADO | 100% | 01/11/24 | 01/11/24 | 0 days | 25/10/24 | 25/10/24 | 6 days | 5 days | 0 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.13 |  |  | SITAG |  | Further Interative Deepdive on the requirements to testcase mapping | 100% | 21/10/24 | 31/10/24 | 9 days | 21/10/24 | 31/10/24 | 0 days | 0 days | 9 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.14 |  |  | SITAG |  | Internal review | 100% | 21/10/24 | 25/10/24 | 5 days | 01/11/24 | 05/11/24 | -9 days | -7 days | 5 days | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.15 |  |  | SITAG |  | Issue Static RTTM to Code Bodies | 100% | 29/10/24 | 29/10/24 | 1 day? | 06/11/24 | 06/11/24 | -6 days | -6 days | 1 day? | SI Test |  | 6.11 | Yes
9 | 1.4.1.4.2.5.2.2.16 |  |  | SITAG |  | Code Body Acceptance of RTTM | 100% | 30/10/24 | 05/11/24 | 5 days | 07/11/24 | 13/11/24 | -6 days | -6 days | 5 days | Code Bodies |  | 6.11 | Yes
7 | 1.4.1.4.2.5.3 |  |  | SITAG |  | Cycle 3 Test Evidence Capturing Approach | 100% | 16/09/24 | 18/10/24 | 25 days? | 16/09/24 | 18/10/24 | 0 days | 0 days | 25 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.3.1 |  |  | SITAG |  | Define guiding principles and proof of concept | 100% | 16/09/24 | 27/09/24 | 10 days | 16/09/24 | 27/09/24 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.3.2 |  |  | SITAG |  | Draft proposed test evidence capturing approach | 100% | 30/09/24 | 02/10/24 | 3 days | 30/09/24 | 02/10/24 | 0 days | 0 days | 3 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.3.3 |  |  | SITAG |  | SRO review | 100% | 03/10/24 | 09/10/24 | 5 days | 03/10/24 | 09/10/24 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.3.4 |  |  | SITAG |  | Present proposed approach | 100% | 11/10/24 | 11/10/24 | 1 day? | 11/10/24 | 11/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.3.5 |  |  | SITAG |  | Incorporate feedback | 100% | 14/10/24 | 17/10/24 | 4 days | 14/10/24 | 17/10/24 | 0 days | 0 days | 4 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.3.6 |  |  | SITAG |  | Publish proposed approach ahead of Cycle 3 start | 100% | 18/10/24 | 18/10/24 | 1 day? | 18/10/24 | 18/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
7 | 1.4.1.4.2.5.4 |  |  | SITAG |  | DITL Cycle 3 Pack Development | 100% | 08/10/24 | 17/10/24 | 8 days? | 08/10/24 | 17/10/24 | 0 days | 0 days | 8 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.4.1 |  |  | SITAG |  | Programme Cycle 2 Retro | 100% | 08/10/24 | 08/10/24 | 1 day? | 08/10/24 | 08/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.4.2 |  |  | SITAG |  | Post-retro DITL Changes | 100% | 09/10/24 | 11/10/24 | 3 days | 09/10/24 | 11/10/24 | 0 days | 0 days | 3 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.4.3 |  |  | SITAG |  | SRO Review | 100% | 14/10/24 | 15/10/24 | 2 days | 14/10/24 | 15/10/24 | 0 days | 0 days | 2 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.4.4 |  |  | SITAG |  | Post-SRO Review Changes | 100% | 16/10/24 | 16/10/24 | 1 day? | 16/10/24 | 16/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.4.5 |  |  | SITAG |  | Publish Cycle 3 DITL / Cycle 3 DITL Online Sessions for SIT PPs | 100% | 17/10/24 | 17/10/24 | 1 day? | 17/10/24 | 17/10/24 | 0 days | 0 days | 1 day? | SI Test, PPs |  | 6 | Yes
7 | 1.4.1.4.2.5.5 |  |  | SITAG |  | Test Script Exit Points | 100% | 14/10/24 | 07/02/25 | 85 days | 14/10/24 | 07/02/25 | 0 days | 0 days | 85 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.1 |  |  | SITAG |  | Implement exit points for Sprint 5 | 100% | 14/10/24 | 18/10/24 | 5 days | 14/10/24 | 18/10/24 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.2 |  |  | SITAG |  | Identify exit points for Sprint 6 | 100% | 07/11/24 | 13/11/24 | 5 days | 21/10/24 | 25/10/24 | 13 days | 13 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.3 |  |  | SITAG |  | Identify exit points for Sprint 7 | 100% | 08/11/24 | 14/11/24 | 5 days | 04/11/24 | 08/11/24 | 4 days | 4 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.4 |  |  | SITAG |  | Identify exit points for Sprint 8 | 100% | 18/11/24 | 22/11/24 | 5 days | 18/11/24 | 22/11/24 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.5 |  |  | SITAG |  | Identify exit points for Sprint 9 | 100% | 02/12/24 | 06/12/24 | 5 days | 02/12/24 | 06/12/24 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.6 |  |  | SITAG |  | Identify exit points for Sprint 10 | 100% | 23/12/24 | 27/12/24 | 5 days | 23/12/24 | 27/12/24 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.7 |  |  | SITAG |  | Identify exit points for Sprint 11 | 100% | 06/01/25 | 10/01/25 | 5 days | 06/01/25 | 10/01/25 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.8 |  |  | SITAG |  | Identify exit points for Sprint 12 | 100% | 20/01/25 | 24/01/25 | 5 days | 20/01/25 | 24/01/25 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.9 |  |  | SITAG |  | Identify exit points for Sprint 13 | 100% | 03/02/25 | 07/02/25 | 5 days | 03/02/25 | 07/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.2.5.5.10 | T3 | T3-TE-0125 | SITAG |  | Exit point identified and evidence capture flags updated | 100% | 07/02/25 | 07/02/25 | 0 days | 07/02/25 | 07/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.13 | Yes
6 | 1.4.1.4.2.6 |  |  | SITAG |  | Environments (SIT-Staging) | 100% | 04/12/23 | 15/12/23 | 10 days | 04/12/23 | 15/12/23 | 0 days | 0 days | -313 days | N/A |  | 5 | Yes
7 | 1.4.1.4.2.6.1 |  |  | SITAG |  | SIT Functional pre-requisites | 100% | 04/12/23 | 15/12/23 | 10 days | 04/12/23 | 15/12/23 | 0 days | 0 days | 0 days | N/A |  | 5.3 | Yes
8 | 1.4.1.4.2.6.1.1 |  |  | SITAG |  | DCC | 100% | 04/12/23 | 15/12/23 | 10 days | 04/12/23 | 15/12/23 | 0 days | 0 days | 0 days | N/A |  | 5.3 | Yes
9 | 1.4.1.4.2.6.1.1.1 |  |  | SITAG |  | CSS | 100% | 04/12/23 | 15/12/23 | 10 days | 04/12/23 | 15/12/23 | 0 days | 0 days | 0 days | N/A |  | 5.3 | Yes
10 | 1.4.1.4.2.6.1.1.1.1 |  |  | SITAG |  | SIT participants have requested DCC CSS PKI certificates for access to UIT-B environment | 100% | 04/12/23 | 15/12/23 | 10 days | 04/12/23 | 15/12/23 | 0 days | 0 days | 0 days | SIT Participants (Suppliers & Third Parties) |  | 5.3 | Yes
10 | 1.4.1.4.2.6.1.1.1.2 | T3 | T3-TE-0088 | SITAG |  | SIT participants have received DCC CSS PKI certificates for UIT-B environment | 100% | 15/12/23 | 15/12/23 | 0 days | 15/12/23 | 15/12/23 | 1 day | 0 days | 0 days | SIT Participants (Suppliers & Third Parties) |  | 5.5 | Yes
9 | 1.4.1.4.2.6.1.1.2 |  |  | SITAG |  | DSP | 100% | 04/12/23 | 15/12/23 | 10 days | 04/12/23 | 15/12/23 | 0 days | 0 days | 0 days | N/A |  | 5.3 | Yes
10 | 1.4.1.4.2.6.1.1.2.1 |  |  | SITAG |  | SIT participants have requested DCC DSP PKI certificates for access to UIT-B environment | 100% | 04/12/23 | 15/12/23 | 10 days | 04/12/23 | 15/12/23 | 0 days | 0 days | 0 days | PPs in SDS Market Role |  | 5.3 | Yes
10 | 1.4.1.4.2.6.1.1.2.2 | T3 | T3-TE-0089 | SITAG |  | SIT participants have received DCC DSP PKI certificates for UIT-B environment | 100% | 15/12/23 | 15/12/23 | 0 days | 15/12/23 | 15/12/23 | 1 day | 0 days | 0 days | PPs in SDS Market Role |  | 5.5 | Yes
6 | 1.4.1.4.2.7 |  |  | SITAG |  | Stand up SIT A Environment | 100% | 05/02/24 | 08/03/24 | 25 days | 05/02/24 | 08/03/24 | 0 days | 0 days | 0 days | N/A |  | 6 | Yes
7 | 1.4.1.4.2.7.1 |  |  | SITAG |  | SIT Functional Connectivity Proving | 100% | 12/02/24 | 01/03/24 | 15 days | 12/02/24 | 01/03/24 | 0 days | 0 days | -5 days | N/A |  | 5.5 | Yes
8 | 1.4.1.4.2.7.1.1 |  |  | SITAG |  | SIT Functional Connectivity Proving Period | 100% | 12/02/24 | 01/03/24 | 15 days | 12/02/24 | 01/03/24 | 0 days | 0 days | -5 days | SI Test |  | 5.19 | Yes
8 | 1.4.1.4.2.7.1.2 | T3 | T3-TE-0103 | SITAG |  | SIT Functional Connectivity Proving Complete | 100% | 01/03/24 | 01/03/24 | 0 days | 01/03/24 | 01/03/24 | 1 day | 0 days | 0 days | SI Test |  | 5.19 | Yes
7 | 1.4.1.4.2.7.2 |  |  | SITAG |  | PP Environments (SIT A) | 100% | 05/02/24 | 08/03/24 | 25 days | 05/02/24 | 08/03/24 | 0 days | 0 days | 20 days | N/A |  | 5 | Yes
8 | 1.4.1.4.2.7.2.1 |  |  | SITAG |  | Deployment of MHHS solution code to SIT A environments | 100% | 05/02/24 | 08/03/24 | 25 days | 05/02/24 | 08/03/24 | 0 days | 0 days | 20 days | PP |  | 5 | Yes
7 | 1.4.1.4.2.7.3 |  |  | SITAG |  | SI Environments (SIT A) | 100% | 05/02/24 | 08/03/24 | 25 days | 05/02/24 | 08/03/24 | 0 days | 0 days | 20 days | N/A |  | 5 | Yes
8 | 1.4.1.4.2.7.3.1 |  |  | SITAG |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT A environments | 100% | 05/02/24 | 08/03/24 | 25 days | 05/02/24 | 08/03/24 | 0 days | 0 days | 20 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.2.8 |  |  | SITAG |  | Test data (SIT A) | 100% | 18/12/23 | 21/10/24 | 221 days? | 18/12/23 | 07/04/25 | 0 days | -120 days | -4 days? | N/A |  | 5.4 | Yes
7 | 1.4.1.4.2.8.1 |  |  | SITAG |  | Cycle 1 Test data (SIT A) | 100% | 18/12/23 | 01/03/24 | 55 days | 18/12/23 | 01/03/24 | 0 days | 0 days | 0 days | N/A |  | 5.4 | Yes
8 | 1.4.1.4.2.8.1.1 |  |  | SITAG |  | Prepare, Generate and Allocate Test Data | 100% | 18/12/23 | 24/01/24 | 28 days | 18/12/23 | 24/01/24 | 0 days | 0 days | 0 days | SI Test Data |  | 5.14 | Yes
8 | 1.4.1.4.2.8.1.2 |  |  | SITAG |  | Transmit Data Sets to PPs | 100% | 26/01/24 | 31/01/24 | 4 days | 26/01/24 | 31/01/24 | 0 days | 0 days | 2 days | SI Test Data |  | 5.14 | Yes
8 | 1.4.1.4.2.8.1.3 |  |  | SITAG |  | PP's Iterative load and data integrity check | 100% | 01/02/24 | 01/03/24 | 22 days | 01/02/24 | 01/03/24 | 0 days | 0 days | 12 days | PP |  | 5.14 | Yes
8 | 1.4.1.4.2.8.1.4 | T3 | T3-TE-0079 | SITAG | MHHS-ART140 MHHS-ART169 | Cycle 1 - PP's confirmation that test data is ready for SIT Functional | 100% | 01/03/24 | 01/03/24 | 0 days | 01/03/24 | 01/03/24 | 1 day | 0 days | 0 days | SI Test Data |  | 5.18 | Yes
7 | 1.4.1.4.2.8.2 |  |  | SITAG |  | Cycle 2 Test data (inc. Settlement Data) (SIT A) | 100% | 28/03/24 | 14/06/24 | 57 days | 28/03/24 | 14/06/24 | 0 days | 0 days | 10 days | N/A |  | 6 | Yes
8 | 1.4.1.4.2.8.2.1 |  |  | SITAG |  | Prepare, Generate and Allocate Test Data | 100% | 28/03/24 | 09/05/24 | 31 days | 28/03/24 | 09/05/24 | 0 days | 0 days | 0 days | SI Test Data |  | 5.14 | Yes
8 | 1.4.1.4.2.8.2.2 |  |  | SITAG |  | Transmit Data Sets to PPs | 100% | 10/05/24 | 14/05/24 | 3 days | 10/05/24 | 14/05/24 | 0 days | 0 days | 0 days | SI Test Data |  | 5.14 | Yes
8 | 1.4.1.4.2.8.2.3 |  |  | SITAG |  | PP's Iterative load and data integrity check | 100% | 15/05/24 | 31/05/24 | 13 days | 15/05/24 | 31/05/24 | 0 days | 0 days | 0 days | PP |  | 5.14 | Yes
8 | 1.4.1.4.2.8.2.4 | T3 | T3-TE-0080 | SITAG | MHHS-ART140 MHHS-ART169 | Cycle 2 - PP's confirmation that test data is ready for SIT Functional | 100% | 14/06/24 | 14/06/24 | 0 days | 14/06/24 | 14/06/24 | 1 day | 0 days | 0 days | SI Test Data |  | 5.27 | Yes
7 | 1.4.1.4.2.8.3 |  |  | SITAG |  | Cycle 3 Test data (SIT A) (2) | 100% | 15/07/24 | 21/10/24 | 71 days? | 15/07/24 | 21/10/24 | 0 days | 0 days | 30 days? | N/A |  | 5.4 | Yes
8 | 1.4.1.4.2.8.3.1 |  |  | SITAG |  | Cycle 3 data requirments analysis - check Cycle 2 data for gaps Check blocked test cases | 100% | 15/07/24 | 26/07/24 | 10 days? | 15/07/24 | 26/07/24 | 0 days | 0 days | 10 days? |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.2 |  |  | SITAG |  | Provide DCC with MPANS for deletion secure file with password | 100% | 12/08/24 | 12/08/24 | 1 day? | 12/08/24 | 12/08/24 | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.3 |  |  | SITAG |  | Receive MPANS from DCC to exclude | 100% | 09/08/24 | 09/08/24 | 1 day? | 09/08/24 | 09/08/24 | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.4 |  |  | SITAG |  | Exclude MPANS from allocation | 100% | 16/08/24 | 16/08/24 | 1 day | 16/08/24 | 16/08/24 | 0 days | 0 days | 1 day |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.5 |  |  | SITAG |  | Allocate Cycle 3 MPANS | 100% | 06/08/24 | 27/08/24 | 16 days? | 06/08/24 | 27/08/24 | 0 days | 0 days | 16 days? |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.6 |  |  | SITAG |  | Generate Cycle 3 Data | 100% | 27/08/24 | 28/08/24 | 2 days? | 27/08/24 | 28/08/24 | 0 days | 0 days | 2 days? |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.7 |  |  | SITAG |  | Check data prior to sending to DCC | 100% | 22/08/24 | 28/08/24 | 5 days? | 22/08/24 | 28/08/24 | 0 days | 0 days | 5 days? |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.8 |  |  | SITAG |  | Share Cycle 3 MPAN data with DCC | 100% | 29/08/24 | 29/08/24 | 1 day? | 29/08/24 | 29/08/24 | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.9 |  |  | SITAG |  | DCC - load data and create registration Id's for Cycle 3 data | 100% | 27/08/24 | 12/09/24 | 13 days? | 27/08/24 | 12/09/24 | 0 days | 0 days | 13 days? |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.10 |  |  | SITAG |  | Add registration ID's to Cycle 3 Data | 100% | 12/09/24 | 13/09/24 | 2 days? | 12/09/24 | 13/09/24 | 0 days | 0 days | 2 days? |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.11 |  |  | SITAG |  | Share subset of data with St Cls for data load | 100% | 12/09/24 | 13/09/24 | 2 days? | 12/09/24 | 13/09/24 | 0 days | 0 days | 2 days? |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.12 |  |  | SITAG |  | St Clements to run test with Subset of data - MPRS business process checks including Import/Export MPANS | 100% | 16/09/24 | 20/09/24 | 5 days? | 16/09/24 | 20/09/24 | 0 days | 0 days | 5 days? |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.13 |  |  | SITAG |  | Send Cycle 3 data to partcipants for early sight of data | 100% | 25/09/24 | 27/09/24 | 3 days? | 25/09/24 | 27/09/24 | 0 days | 0 days | 3 days? |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.14 |  |  | SITAG |  | St Clements MPRS data load bulk files for Cycle 3 | 100% | 23/09/24 | 11/10/24 | 15 days? | 23/09/24 | 11/10/24 | 0 days | 0 days | 15 days? |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.15 |  |  | SITAG |  | New MPAN creation and load through DCC and St Clements | 100% | 11/10/24 | 11/10/24 | 1 day? | 11/10/24 | 11/10/24 | 0 days | 0 days | 1 day? |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.16 |  |  | SITAG |  | Share files with PP's and central parties | 100% | 11/10/24 | 11/10/24 | 1 day | 11/10/24 | 11/10/24 | 0 days | 0 days | 1 day |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.17 |  |  | SITAG |  | Avanade to load data | 100% | 14/10/24 | 21/10/24 | 6 days | 14/10/24 | 21/10/24 | 0 days | 0 days | 6 days |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.18 |  |  | SITAG |  | Helix to load data | 100% | 14/10/24 | 21/10/24 | 6 days | 14/10/24 | 21/10/24 | 0 days | 0 days | 6 days |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.19 |  |  | SITAG |  | PP's and central parties to load all Cycle 3 data | 100% | 14/10/24 | 21/10/24 | 6 days | 14/10/24 | 21/10/24 | 0 days | 0 days | 6 days |  |  | 6 | Yes
8 | 1.4.1.4.2.8.3.20 |  | T3-TE-0081 | SITAG |  | All parties to finalise data load | 100% | 21/10/24 | 21/10/24 | 1 day? | 21/10/24 | 21/10/24 | 0 days | 0 days | 1 day? | SI Data |  | 6 | Yes
6 | 1.4.1.4.2.9 |  |  | SITAG |  | SIT Functional Test Readiness Report | 100% | 01/01/24 | 01/03/24 | 45 days | 01/01/24 | 01/03/24 | 0 days | 0 days | 1 day | N/A |  | 5 | Yes
7 | 1.4.1.4.2.9.1 |  |  | SITAG |  | PP SIT Functional Test Readiness Report | 100% | 01/01/24 | 29/02/24 | 44 days | 01/01/24 | 29/02/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.2.9.1.1 |  |  | SITAG |  | Develop draft Test Readiness Report and submit to Programme for assurance | 100% | 01/01/24 | 29/01/24 | 21 days | 01/01/24 | 29/01/24 | 0 days | 0 days | 1 day | PP |  | 5 | Yes
8 | 1.4.1.4.2.9.1.2 |  |  | SITAG |  | Placing Reliance Stage 2 Review | 100% | 15/01/24 | 29/02/24 | 34 days | 15/01/24 | 29/02/24 | 0 days | 0 days | 0 days | SI Test |  | 5.12 | Yes
8 | 1.4.1.4.2.9.1.3 |  |  | SITAG |  | Finalise Test Readiness Report and submit to Programme for assurance | 100% | 30/01/24 | 09/02/24 | 9 days | 30/01/24 | 09/02/24 | 0 days | 0 days | -1 day | PP |  | 5 | Yes
7 | 1.4.1.4.2.9.2 |  |  | SITAG |  | SI SIT Functional Test Readiness Report | 100% | 01/01/24 | 23/02/24 | 40 days | 01/01/24 | 23/02/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.2.9.2.1 |  |  | SITAG |  | Assure Test Participants' Test Readiness Reports | 100% | 01/01/24 | 16/02/24 | 35 days | 01/01/24 | 16/02/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.2.9.2.2 |  |  | SITAG |  | Develop Overarching SIT Functional Test Readiness Report | 100% | 22/01/24 | 16/02/24 | 20 days | 22/01/24 | 16/02/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.2.9.2.3 |  |  | SITAG |  | Artefact review (via TMAG) and updates | 100% | 19/02/24 | 23/02/24 | 5 days | 19/02/24 | 23/02/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.2.9.3 | T2 | T2-TE-0550 | SITAG |  | SIT Functional Testing Preparation Complete | 100% | 01/03/24 | 01/03/24 | 0 days | 01/03/24 | 01/03/24 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.4.3 |  |  | SITAG |  | SIT Migration Testing Preparation | 96% | 31/10/22 | 07/02/25 | 595 days? | 31/10/22 | 04/10/24 | 0 days | 90 days | 175 days? | N/A |  | 5.21 | Yes
6 | 1.4.1.4.3.1 |  |  | SITAG |  | Test Approach & Plan | 100% | 07/09/23 | 20/12/23 | 75 days | 07/09/23 | 20/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.3.1.1 |  |  | SITAG |  | Develop document with SITWG | 100% | 07/09/23 | 20/10/23 | 32 days | 07/09/23 | 20/10/23 | 0 days | 0 days | 7 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.3.1.2 |  |  | SITAG |  | Draft document review with Code Bodies | 100% | 23/10/23 | 01/11/23 | 8 days | 23/10/23 | 01/11/23 | 0 days | 0 days | -2 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.3.1.3 |  |  | SITAG |  | Industry Consultation | 100% | 02/11/23 | 15/11/23 | 10 days | 02/11/23 | 15/11/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.3.1.4 |  |  | SITAG |  | Artefact review (via TMAG) and updates | 100% | 16/11/23 | 20/12/23 | 25 days | 16/11/23 | 20/12/23 | 0 days | 0 days | -5 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.3.1.5 | T3 | T3-TE-0018 | SITAG | MHHS-ART073 | SIT Migration Testing Test Approach & Plan approved | 100% | 20/12/23 | 20/12/23 | 0 days | 20/12/23 | 20/12/23 | 1 day | 0 days | -1 day | SI Test |  | 5.14 | Yes
6 | 1.4.1.4.3.2 |  |  | SITAG |  | Test Data Approach & Plan | 100% | 02/11/23 | 20/12/23 | 35 days | 02/11/23 | 20/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.3.2.1 |  |  | SITAG |  | Industry Consultation | 100% | 02/11/23 | 15/11/23 | 10 days | 02/11/23 | 15/11/23 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.3.2.2 |  |  | SITAG |  | Artefact review (via TMAG) and updates | 100% | 16/11/23 | 20/12/23 | 25 days | 16/11/23 | 20/12/23 | 0 days | 0 days | -5 days | SI Test Data |  | 5 | Yes
7 | 1.4.1.4.3.2.3 |  |  | SITAG |  | SIT Migration Test Data Test Approach & Plan approved | 100% | 20/12/23 | 20/12/23 | 0 days | 20/12/23 | 20/12/23 | 1 day | 0 days | 0 days | SI Test Data |  | 5.14 | Yes
6 | 1.4.1.4.3.3 |  |  | SITAG |  | Test scenarios & Test Cases | 88% | 21/12/23 | 07/02/25 | 297 days? | 21/12/23 | 04/10/24 | 0 days | 90 days | 232 days? | N/A |  | 5.16 | Yes
7 | 1.4.1.4.3.3.1 |  |  | SITAG |  | Theme 1 | 100% | 21/12/23 | 20/03/24 | 65 days | 21/12/23 | 20/03/24 | 0 days | 0 days | 0 days | N/A |  | 5.16 | Yes
8 | 1.4.1.4.3.3.1.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases | 100% | 21/12/23 | 24/01/24 | 25 days | 21/12/23 | 24/01/24 | 0 days | 0 days | 0 days | SI Test |  | 5.16 | Yes
8 | 1.4.1.4.3.3.1.2 |  |  | SITAG |  | Industry Review Workshop | 100% | 25/01/24 | 25/01/24 | 1 day | 25/01/24 | 25/01/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.1.3 |  |  | SITAG |  | Industry Consultation Review | 100% | 05/02/24 | 12/02/24 | 6 days | 05/02/24 | 12/02/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.1.4 |  |  | SITAG |  | Review with SIT Working Group | 100% | 29/02/24 | 06/03/24 | 5 days | 29/02/24 | 06/03/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.19 | Yes
8 | 1.4.1.4.3.3.1.5 | T3 | T3-TE-0110 | SITAG |  | SIT Migration Test scenarios & Test Cases Approved - Theme 1 | 100% | 20/03/24 | 20/03/24 | 0 days | 20/03/24 | 20/03/24 | 1 day | 0 days | 0 days | SI Test |  | 5.21 | Yes
7 | 1.4.1.4.3.3.2 |  |  | SITAG |  | Theme 2 | 100% | 21/12/23 | 17/04/24 | 85 days | 21/12/23 | 17/04/24 | 0 days | 0 days | 0 days | N/A |  | 5.16 | Yes
8 | 1.4.1.4.3.3.2.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases | 100% | 21/12/23 | 14/02/24 | 40 days | 21/12/23 | 14/02/24 | 0 days | 0 days | 0 days | SI Test |  | 5.16 | Yes
8 | 1.4.1.4.3.3.2.2 |  |  | SITAG |  | Industry Review Workshop | 100% | 15/02/24 | 15/02/24 | 1 day | 15/02/24 | 15/02/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.2.3 |  |  | SITAG |  | Industry Consultation Review | 100% | 26/02/24 | 04/03/24 | 6 days | 26/02/24 | 04/03/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.19 | Yes
8 | 1.4.1.4.3.3.2.4 |  |  | SITAG |  | Review with SIT Working Group | 100% | 28/03/24 | 03/04/24 | 5 days | 28/03/24 | 03/04/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.2.5 | T3 | T3-TE-0111 | SITAG |  | SIT Migration Test scenarios & Test Cases Approved - Theme 2 | 100% | 17/04/24 | 17/04/24 | 0 days | 17/04/24 | 17/04/24 | 1 day | 0 days | 0 days | SI Test |  | 5.22 | Yes
7 | 1.4.1.4.3.3.3 |  |  | SITAG |  | Theme 3 | 100% | 21/12/23 | 17/04/24 | 85 days | 21/12/23 | 17/04/24 | 0 days | 0 days | 0 days | N/A |  | 5.16 | Yes
8 | 1.4.1.4.3.3.3.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases | 100% | 21/12/23 | 06/03/24 | 55 days | 21/12/23 | 06/03/24 | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes
8 | 1.4.1.4.3.3.3.2 |  |  | SITAG |  | Industry Review Workshop | 100% | 07/03/24 | 07/03/24 | 1 day | 07/03/24 | 07/03/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.3.3 |  |  | SITAG |  | Industry Consultation Review | 100% | 13/03/24 | 20/03/24 | 6 days | 13/03/24 | 20/03/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.3.4 |  |  | SITAG |  | Review with SIT Working Group | 100% | 28/03/24 | 03/04/24 | 5 days | 28/03/24 | 03/04/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.16 | Yes
8 | 1.4.1.4.3.3.3.5 | T3 | T3-TE-0112 | SITAG |  | SIT Migration Test scenarios & Test Cases Approved - Theme 3 | 100% | 17/04/24 | 17/04/24 | 0 days | 17/04/24 | 17/04/24 | 1 day | 0 days | 0 days | SI Test |  | 5.22 | Yes
7 | 1.4.1.4.3.3.4 |  |  | SITAG |  | RTTM Development | 100% | 29/08/24 | 20/09/24 | 17 days | 29/08/24 | 04/10/24 | 0 days | -10 days | 17 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.3.3.4.1 |  |  | SITAG |  | Develop Manual SIT Migration RTTM | 100% | 29/08/24 | 20/09/24 | 17 days | 29/08/24 | 20/09/24 | 0 days | 0 days | 17 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.3.3.4.2 |  |  | SITAG |  | Manual SIT Migration RTTM Complete | 100% | 20/09/24 | 20/09/24 | 0 days | 20/09/24 | 20/09/24 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
7 | 1.4.1.4.3.3.5 |  |  | SITAG |  | Gap analysis | 75% | 12/09/24 | 07/02/25 | 107 days? | 12/09/24 | 04/10/24 | 0 days | 90 days | 107 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.3.3.5.1 |  |  | SITAG |  | Identify gaps in test case coverage following RTTM review. | 100% | 12/09/24 | 27/09/24 | 12 days | 12/09/24 | 27/09/24 | 0 days | 0 days | 12 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.3.3.5.2 |  |  | SITAG |  | Address gaps in test case coverage following RTTM review. | 100% | 19/09/24 | 11/10/24 | 17 days | 19/09/24 | 04/10/24 | 0 days | 5 days | 17 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.3.3.5.3 |  |  | SITAG |  | Gap analysis complete | 100% | 11/10/24 | 11/10/24 | 0 days? | 04/10/24 | 04/10/24 | 6 days | 5 days | 0 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.3.3.5.4 |  |  | SITAG |  | Test Script updates identified | 100% | 14/10/24 | 14/10/24 | 1 day? | 14/10/24 | 14/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.5 |  |  | SITAG |  | Test Scripts updates | 100% | 14/10/24 | 04/11/24 | 16 days? | 14/10/24 | 04/11/24 | 0 days | 0 days | 16 days? | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.6 |  |  | SITAG |  | RTTM Updated | 100% | 29/10/24 | 29/10/24 | 1 day? | 29/10/24 | 29/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.7 |  |  | SITAG |  | Removal of de-scoped TCs from the RTTMs | 100% | 31/10/24 | 01/11/24 | 2 days | 31/10/24 | 01/11/24 | 0 days | 0 days | 2 days | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.8 |  |  | SITAG |  | Update and stabilisation of all TC ADO IDs | 100% | 31/10/24 | 01/11/24 | 2 days | 31/10/24 | 01/11/24 | 0 days | 0 days | 2 days | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.9 |  |  | SITAG |  | Addition and integration of Role tags to reqs in the Role RTTMs | 100% | 30/10/24 | 01/11/24 | 3 days | 30/10/24 | 01/11/24 | 0 days | 0 days | 3 days | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.10 |  |  | SITAG |  | Update of the RTTM All sheet (porting of the individual RTTMs) | 100% | 31/10/24 | 01/11/24 | 2 days | 31/10/24 | 01/11/24 | 0 days | 0 days | 2 days | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.11 |  |  | SITAG |  | ADO IDs corrected | 100% | 04/11/24 | 04/11/24 | 1 day? | 04/11/24 | 04/11/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.12 |  |  | SITAG |  | Migration RTTM ready for import into ADO | 100% | 04/11/24 | 04/11/24 | 0 days | 04/11/24 | 04/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.13 |  |  | SITAG |  | Issue Static RTTM to Code Bodies | 100% | 05/11/24 | 05/11/24 | 1 day? | 05/11/24 | 05/11/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.14 |  |  | SITAG |  | Implement Code Bodies feedback on RTTM | 100% | 06/11/24 | 13/11/24 | 6 days | 06/11/24 | 13/11/24 | 0 days | 0 days | 6 days | SI Test |  | 6.12 | Yes
8 | 1.4.1.4.3.3.5.15 |  |  | SITAG |  | Code Body Acceptance of RTTM | 100% | 13/11/24 | 13/11/24 | 0 days | 06/11/24 | 13/11/24 | 6 days | 0 days | 0 days | SI Test |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.16 |  |  | SITAG |  | ADO Clean-up | 100% | 24/10/24 | 15/11/24 | 17 days? | 24/10/24 | 15/11/24 | 0 days | 0 days | 17 days? |  |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.16.1 |  |  | SITAG |  | Theme alignment | 100% | 28/10/24 | 28/10/24 | 1 day? | 28/10/24 | 28/10/24 | 0 days | 0 days | 1 day? |  |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.16.2 |  |  | SITAG |  | Understand Additional suffix Fields in ADO as defined by Kevin | 100% | 25/10/24 | 25/10/24 | 1 day? | 25/10/24 | 25/10/24 | 0 days | 0 days | 1 day? |  |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.16.3 |  |  | SITAG |  | Correct Missing Test Case References | 100% | 28/10/24 | 28/10/24 | 1 day? | 28/10/24 | 28/10/24 | 0 days | 0 days | 1 day? |  |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.16.4 |  |  | SITAG |  | Load Functional RTTMs into ADO | 100% | 28/10/24 | 28/10/24 | 1 day? | 28/10/24 | 28/10/24 | 0 days | 0 days | 1 day? |  |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.16.5 |  |  | SITAG |  | Load Migration RTTMs into ADO | 100% | 06/11/24 | 06/11/24 | 1 day? | 06/11/24 | 06/11/24 | 0 days | 0 days | 1 day? |  |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.16.6 |  |  | SITAG |  | Confirm Missing fields in ADO are resolved | 100% | 07/11/24 | 07/11/24 | 1 day? | 07/11/24 | 07/11/24 | 0 days | 0 days | 1 day? |  |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.16.7 |  |  | SITAG |  | Reload Functional RTTM into ADO | 100% | 07/11/24 | 07/11/24 | 1 day? | 07/11/24 | 07/11/24 | 0 days | 0 days | 1 day? |  |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.16.8 |  |  | SITAG |  | ADO Design Documentation | 100% | 04/11/24 | 15/11/24 | 10 days? | 04/11/24 | 15/11/24 | 0 days | 0 days | 10 days? |  |  | 6.11 | Yes
10 | 1.4.1.4.3.3.5.16.8.1 |  |  | SITAG |  | Produce ADO high Level Design and Data Model | 100% | 15/11/24 | 15/11/24 | 1 day? | 15/11/24 | 15/11/24 | 0 days | 0 days | 1 day? |  |  | 6.11 | Yes
10 | 1.4.1.4.3.3.5.16.8.2 |  |  | SITAG |  | Produce Report derivation document | 100% | 15/11/24 | 15/11/24 | 1 day? | 15/11/24 | 15/11/24 | 0 days | 0 days | 1 day? |  |  | 6.11 | Yes
8 | 1.4.1.4.3.3.5.17 |  |  | SITAG |  | Test Case Rationalisation (Functional + Migration) | 54% | 07/11/24 | 07/02/25 | 67 days | 07/11/24 | 20/12/24 | 0 days | 35 days | 67 days |  |  | 6.11 | Yes
9 | 1.4.1.4.3.3.5.17.1 |  |  | SITAG |  | Internal preliminary rationalisation workshop 1 | 100% | 07/11/24 | 07/11/24 | 1 day | 07/11/24 | 07/11/24 | 0 days | 0 days | 1 day |  | Proposed | 6.11 | Yes
9 | 1.4.1.4.3.3.5.17.2 |  |  | SITAG |  | Baseline RTTMs | 90% | 13/11/24 | 13/11/24 | 0 days | 13/11/24 | 13/11/24 | 1 day | 0 days | 0 days |  | Proposed | 6.11 | Yes
9 | 1.4.1.4.3.3.5.17.3 |  |  | SITAG |  | Baseline test cases | 100% | 13/11/24 | 13/11/24 | 0 days | 13/11/24 | 13/11/24 | 1 day | 0 days | 0 days |  | Proposed | 6.11 | Yes
9 | 1.4.1.4.3.3.5.17.4 |  |  | SITAG |  | Produce requirements / test case analysis doc | 100% | 14/11/24 | 14/11/24 | 1 day | 14/11/24 | 14/11/24 | 0 days | 0 days | 1 day |  | Proposed | 6.11 | Yes
9 | 1.4.1.4.3.3.5.17.5 |  |  | SITAG |  | Internal finalisation rationalisation workshop 2 | 100% | 15/11/24 | 03/12/24 | 13 days | 15/11/24 | 15/11/24 | 0 days | 12 days | 13 days |  | Proposed | 6.14 | Yes
9 | 1.4.1.4.3.3.5.17.6 |  |  | SITAG |  | SRO walkthrough | 100% | 04/12/24 | 04/12/24 | 1 day | 21/11/24 | 21/11/24 | 9 days | 9 days | 1 day |  | Proposed | 6.14 | Yes
9 | 1.4.1.4.3.3.5.17.7 |  |  | SITAG |  | Code Bodies walkthrough | 100% | 04/12/24 | 04/12/24 | 1 day | 26/11/24 | 26/11/24 | 6 days | 6 days | 1 day |  | Proposed | 6.14 | Yes
9 | 1.4.1.4.3.3.5.17.8 |  |  | SITAG |  | Send invites to PPs for walkthrough | 100% | 04/12/24 | 04/12/24 | 1 day | 26/11/24 | 26/11/24 | 6 days | 6 days | 1 day |  | Proposed | 6.14 | Yes
9 | 1.4.1.4.3.3.5.17.9 |  |  | SITAG |  | PP walkthrough | 100% | 17/12/24 | 17/12/24 | 1 day | 03/12/24 | 03/12/24 | 10 days | 10 days | 1 day |  | Proposed | 6.14 | Yes
9 | 1.4.1.4.3.3.5.17.10 |  |  |  |  | Update requirements / test case analysis doc | 100% | 05/12/24 | 14/01/25 | 29 days | 05/12/24 | 14/01/25 | 0 days | 0 days | 29 days |  | Proposed | 6.16 | Yes |  | 15/01/25 - Rationalisation completion now forecasted to be 07/02/25, this is to allow time after SITAG to update ADO, test cases, RTTM and the master test case spreadsheet. Programme still aims to get sign off of rationalisation at January SITAG. Activity
9 | 1.4.1.4.3.3.5.17.11 |  |  | SITAG |  | SITWG Paper Day | 100% | 14/01/25 | 14/01/25 | 0 days | 20/12/24 | 20/12/24 | 18 days | 17 days | 0 days |  | Proposed | 6.14 | Yes
9 | 1.4.1.4.3.3.5.17.12 |  |  | SITAG |  | SITWG recommendation on requirements / test case analysis doc | 0% | 21/01/25 | 21/01/25 | 0 days | 08/01/25 | 08/01/25 | 10 days | 9 days | 0 days |  | Proposed | 6.14 | Yes
9 | 1.4.1.4.3.3.5.17.13 |  |  | SITAG |  | Issue to SITAG / SITAG paper day | 0% | 22/01/25 | 22/01/25 | 0 days | 11/12/24 | 11/12/24 | 31 days | 30 days | 0 days |  | Proposed | 6.14 | Yes
9 | 1.4.1.4.3.3.5.17.14 |  |  | SITAG |  | Prepare ADO update | 0% | 22/01/25 | 29/01/25 | 6 days | 11/12/24 | 18/12/24 | 30 days | 30 days | 6 days |  | Proposed | 6.14 | Yes
9 | 1.4.1.4.3.3.5.17.15 |  |  | SITAG |  | Sign off by SITAG | 0% | 29/01/25 | 29/01/25 | 0 days | 18/12/24 | 18/12/24 | 31 days | 30 days | 0 days |  | Proposed | 6.14 | Yes
9 | 1.4.1.4.3.3.5.17.16 |  |  | SITAG |  | Update ADO | 0% | 30/01/25 | 07/02/25 | 7 days | 19/12/24 | 20/12/24 | 30 days | 35 days | 7 days |  | Proposed | 6.14 | Yes
9 | 1.4.1.4.3.3.5.17.17 |  |  | SITAG |  | Update all ADO reporting | 0% | 30/01/25 | 07/02/25 | 7 days | 19/12/24 | 20/12/24 | 30 days | 35 days | 7 days |  | Proposed | 6.14 | Yes
9 | 1.4.1.4.3.3.5.17.18 |  |  |  |  | Update test cases | 0% | 30/01/25 | 07/02/25 | 7 days | N/A | N/A | 0 days | 0 days | 7 days |  | Proposed | 6.16 | Yes |  | 15/01/25 - Rationalisation completion now forecasted to be 07/02/25, this is to allow time after SITAG to update ADO, test cases, RTTM and the master test case spreadsheet. Programme still aims to get sign off of rationalisation at January SITAG. Activity
9 | 1.4.1.4.3.3.5.17.19 |  |  |  |  | Update RTTM | 0% | 30/01/25 | 07/02/25 | 7 days | N/A | N/A | 0 days | 0 days | 7 days |  | Proposed | 6.16 | Yes |  | 15/01/25 - Rationalisation completion now forecasted to be 07/02/25, this is to allow time after SITAG to update ADO, test cases, RTTM and the master test case spreadsheet. Programme still aims to get sign off of rationalisation at January SITAG. Activity
9 | 1.4.1.4.3.3.5.17.20 |  |  |  |  | Update master test case spreadsheet | 0% | 30/01/25 | 07/02/25 | 7 days | N/A | N/A | 0 days | 0 days | 7 days |  | Proposed | 6.16 | Yes |  | 15/01/25 - Rationalisation completion now forecasted to be 07/02/25, this is to allow time after SITAG to update ADO, test cases, RTTM and the master test case spreadsheet. Programme still aims to get sign off of rationalisation at January SITAG. Activity
9 | 1.4.1.4.3.3.5.17.21 | T3 | T3-TE-0141 | SITAG |  | Test Case Rationalisation complete | 0% | 07/02/25 | 07/02/25 | 0 days | 20/12/24 | 20/12/24 | 36 days | 35 days | 0 days | SI Test | Proposed | 6.16 | Yes |  | 15/01/25 - Rationalisation completion now forecasted to be 07/02/25, this is to allow time after SITAG to update ADO, test cases, RTTM and the master test case spreadsheet. Programme still aims to get sign off of rationalisation at January SITAG. Activity
6 | 1.4.1.4.3.4 |  |  | SITAG |  | Environments (SIT B) | 100% | 31/10/22 | 28/06/24 | 435 days | 31/10/22 | 28/06/24 | 0 days | 0 days | 15 days | N/A |  | 5 | Yes
7 | 1.4.1.4.3.4.1 |  |  | SITAG |  | PP Environments (SIT B) | 100% | 03/05/24 | 28/06/24 | 41 days | 03/05/24 | 28/06/24 | 0 days | 0 days | 15 days | N/A |  | 5 | Yes
8 | 1.4.1.4.3.4.1.1 |  |  | SITAG |  | PP Environments available | 100% | 03/05/24 | 03/05/24 | 0 days | 03/05/24 | 03/05/24 | 0 days | -1 day | 0 days | PP |  | 5.21 | Yes
8 | 1.4.1.4.3.4.1.2 |  |  | SITAG |  | PP Onboarding / Smoke test | 100% | 13/05/24 | 28/06/24 | 35 days | 13/05/24 | 28/06/24 | 0 days | 0 days | 15 days | PP |  | 5.21 | Yes
8 | 1.4.1.4.3.4.1.3 |  |  | SITAG |  | DTN Connectivity Proving Complete | 100% | 10/06/24 | 14/06/24 | 5 days | 10/06/24 | 14/06/24 | 0 days | 0 days | 5 days | PP |  | 5.21 | Yes
8 | 1.4.1.4.3.4.1.4 |  |  | SITAG |  | PP Code Deployment | 100% | 14/06/24 | 14/06/24 | 0 days | 14/06/24 | 14/06/24 | 1 day | 0 days | 0 days | PP |  | 5.21 | Yes
7 | 1.4.1.4.3.4.2 |  |  | SITAG |  | SI Environments (SIT B) | 100% | 31/10/22 | 14/06/24 | 425 days | 31/10/22 | 14/06/24 | 0 days | 0 days | 5 days | N/A |  | 5 | Yes
8 | 1.4.1.4.3.4.2.1 |  |  | SITAG |  | Coordinate SIT Participants' SIT B environment preparation | 100% | 31/10/22 | 07/06/24 | 420 days | 31/10/22 | 07/06/24 | 0 days | 0 days | 0 days | SI Test |  | 5.21 | Yes
8 | 1.4.1.4.3.4.2.2 |  |  | SITAG |  | Assure PPs' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 100% | 07/06/24 | 07/06/24 | 0 days | 07/06/24 | 07/06/24 | 1 day | 0 days | 0 days | SI Test |  | 5.21 | Yes
8 | 1.4.1.4.3.4.2.3 | T3 | T3-TE-0033 | SITAG |  | SIT Participants' SIT B environments ready to start connectivity proving (incl. certificates and security compliance) | 100% | 05/06/24 | 05/06/24 | 0 days | 05/06/24 | 05/06/24 | 1 day | 0 days | 0 days | SI Test |  | 5.26 | Yes
8 | 1.4.1.4.3.4.2.4 |  |  | SITAG |  | Coordinate SIT Participants' SIT B environment connectivity proving | 100% | 06/06/24 | 07/06/24 | 2 days | 06/06/24 | 07/06/24 | 0 days | 0 days | -17 days | SI Test |  | 5.21 | Yes
8 | 1.4.1.4.3.4.2.5 |  |  | SITAG |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT B environments | 100% | 14/06/24 | 14/06/24 | 0 days | 14/06/24 | 14/06/24 | 1 day | 0 days | -4 days | SI Test |  | 5.21 | Yes
6 | 1.4.1.4.3.5 |  |  | SITAG |  | SIT Migration Test Readiness Report | 100% | 02/04/24 | 31/05/24 | 44 days | 02/04/24 | 31/05/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.3.5.1 |  |  | SITAG |  | PP SIT Migration Test Readiness Report | 100% | 02/04/24 | 31/05/24 | 44 days | 02/04/24 | 31/05/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.3.5.1.1 |  |  | SITAG |  | Develop draft Test Readiness Report and submit to Programme for assurance | 100% | 02/04/24 | 29/04/24 | 20 days | 02/04/24 | 29/04/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
8 | 1.4.1.4.3.5.1.2 |  |  | SITAG |  | Placing Reliance Stage 2 Review | 100% | 15/04/24 | 31/05/24 | 35 days | 15/04/24 | 31/05/24 | 0 days | 0 days | 0 days | SI Test |  | 5.12 | Yes
8 | 1.4.1.4.3.5.1.3 |  |  | SITAG |  | Finalise Test Readiness Report and submit to Programme for assurance | 100% | 30/04/24 | 13/05/24 | 10 days | 30/04/24 | 13/05/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
7 | 1.4.1.4.3.5.2 |  |  | SITAG |  | SI SIT Migration Test Readiness Report | 100% | 02/04/24 | 27/05/24 | 40 days | 02/04/24 | 27/05/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.3.5.2.1 |  |  | SITAG |  | Assure Test Participants' Test Readiness Reports | 100% | 02/04/24 | 20/05/24 | 35 days | 02/04/24 | 20/05/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.3.5.2.2 |  |  | SITAG |  | Develop Overarching SIT Migration Test Readiness Report | 100% | 23/04/24 | 20/05/24 | 20 days | 23/04/24 | 20/05/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
8 | 1.4.1.4.3.5.2.3 |  |  | SITAG |  | Artefact review (via SITAG) and updates | 100% | 21/05/24 | 27/05/24 | 5 days | 21/05/24 | 27/05/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.3.6 | T2 | T2-TE-0650 | SITAG |  | SIT Migration Testing Preparation Complete | 100% | 03/06/24 | 03/06/24 | 0 days | 03/06/24 | 03/06/24 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.1.4.4 |  |  | SITAG |  | SIT Non-Functional Preparation | 72% | 30/11/23 | 28/03/25 | 347 days? | 30/11/23 | 14/03/25 | 0 days | 10 days | 154 days? | N/A |  | 5 | Yes
6 | 1.4.1.4.4.1 |  |  | SITAG |  | Test Approach & Plan | 100% | 30/11/23 | 15/05/24 | 120 days | 30/11/23 | 15/05/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.4.1.1 |  |  | SITAG |  | Develop document with SITWG | 100% | 30/11/23 | 01/03/24 | 67 days | 30/11/23 | 01/03/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.4.1.2 |  |  | SITAG |  | Draft document review with Code Bodies | 100% | 04/03/24 | 15/03/24 | 10 days | 04/03/24 | 15/03/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.4.1.3 |  |  | SITAG |  | Industry Consultation | 100% | 18/03/24 | 29/03/24 | 10 days | 18/03/24 | 29/03/24 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.4.1.4 |  |  | SITAG |  | Industry Assurance Review | 100% | 11/04/24 | 17/04/24 | 5 days | 11/04/24 | 17/04/24 | 0 days | 0 days | 0 days |  |  | 5.16 | Yes
7 | 1.4.1.4.4.1.5 | T3 | T3-TE-0026 | SITAG | MHHS-ART073 | SIT Non-Functional Testing Test Approach & Plan approved | 100% | 15/05/24 | 15/05/24 | 0 days | 15/05/24 | 15/05/24 | 1 day | 0 days | 0 days | SI Test |  | 5.3 | Yes
6 | 1.4.1.4.4.2 |  |  | SITAG |  | Test Data Approach & Plan | 100% | 20/03/24 | 15/05/24 | 41 days | 20/03/24 | 15/05/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.4.2.1 |  |  | SITAG |  | Industry Consultation | 100% | 20/03/24 | 08/04/24 | 14 days | 20/03/24 | 08/04/24 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.4.2.2 |  |  | SITAG |  | Artefact review (via SITAG) and updates | 100% | 09/04/24 | 15/05/24 | 27 days | 09/04/24 | 15/05/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.4.2.3 | T3 | T3-TE-0113 | SITAG |  | SIT Non-Functional Testing Test Data Approach & Plan approved | 100% | 15/05/24 | 15/05/24 | 0 days | 15/05/24 | 15/05/24 | 1 day | 0 days | 0 days | SI Test |  | 5.24 | Yes
6 | 1.4.1.4.4.3 |  |  | SITAG |  | Test scenarios & Test Cases | 84% | 04/03/24 | 17/07/24 | 98 days? | 04/03/24 | 17/07/24 | 0 days | 0 days | -25 days? | N/A |  | 5.21 | Yes
7 | 1.4.1.4.4.3.1 |  |  | SITAG |  | Theme 1 | 100% | 04/03/24 | 19/06/24 | 78 days | 04/03/24 | 19/06/24 | 0 days | 0 days | 0 days | N/A |  | 5.21 | Yes
8 | 1.4.1.4.4.3.1.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases | 100% | 04/03/24 | 17/04/24 | 33 days | 04/03/24 | 17/04/24 | 0 days | 0 days | 0 days | SI Test |  | 5.21 | Yes
8 | 1.4.1.4.4.3.1.2 |  |  | SITAG |  | Industry Review Workshop | 100% | 18/04/24 | 18/04/24 | 1 day | 18/04/24 | 18/04/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.1.3 |  |  | SITAG |  | Industry Consultation Review | 100% | 02/05/24 | 10/05/24 | 7 days | 02/05/24 | 10/05/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.1.4 |  |  | SITAG |  | Review with NFT Working Group | 100% | 31/05/24 | 06/06/24 | 5 days | 31/05/24 | 06/06/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.1.5 | T3 | T3-TE-0114 | SITAG |  | SIT NFT Scenarios & Test Cases Approved - Theme 1 | 100% | 19/06/24 | 19/06/24 | 0 days | 19/06/24 | 19/06/24 | 1 day | 0 days | 0 days | SI Test |  | 5.3 | Yes
7 | 1.4.1.4.4.3.2 |  |  | SITAG |  | Theme 2 | 100% | 04/03/24 | 17/07/24 | 98 days | 04/03/24 | 17/07/24 | 0 days | 0 days | 0 days | N/A |  | 5.21 | Yes
8 | 1.4.1.4.4.3.2.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases | 100% | 04/03/24 | 15/05/24 | 53 days | 04/03/24 | 15/05/24 | 0 days | 0 days | 0 days | SI Test |  | 5.21 | Yes
8 | 1.4.1.4.4.3.2.2 |  |  | SITAG |  | Industry Review Workshop | 100% | 16/05/24 | 16/05/24 | 1 day | 16/05/24 | 16/05/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.2.3 |  |  | SITAG |  | Industry Consultation Review | 100% | 20/05/24 | 28/05/24 | 7 days | 20/05/24 | 28/05/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.2.4 |  |  | SITAG |  | Review with NFT Working Group | 100% | 28/06/24 | 04/07/24 | 5 days | 28/06/24 | 04/07/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 5.21 | Yes
8 | 1.4.1.4.4.3.2.5 | T3 | T3-TE-0115 | SITAG |  | SIT NFT Scenarios & Test Cases Approved - Theme 2 | 100% | 17/07/24 | 17/07/24 | 0 days | 17/07/24 | 17/07/24 | 1 day | 0 days | 0 days | SI Test |  | 5.22 | Yes
7 | 1.4.1.4.4.3.3 |  |  | SITAG |  | Theme 3 | 100% | 04/03/24 | 17/07/24 | 98 days? | 04/03/24 | 17/07/24 | 0 days | 0 days | -25 days? | N/A |  | 6 | Yes
8 | 1.4.1.4.4.3.3.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases | 100% | 04/03/24 | 29/05/24 | 63 days | 04/03/24 | 29/05/24 | 0 days | 0 days | 0 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.4.3.3.2 |  |  | SITAG |  | Industry Review Workshop | 100% | 30/05/24 | 30/05/24 | 1 day | 30/05/24 | 30/05/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.4.3.3.3 |  |  | SITAG |  | Industry Consultation Review | 100% | 10/06/24 | 17/06/24 | 6 days | 10/06/24 | 17/06/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.4.3.3.4 |  |  | SITAG |  | Review with NFT Working Group | 100% | 28/06/24 | 04/07/24 | 5 days | 28/06/24 | 04/07/24 | 0 days | 0 days | -25 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.4.3.3.5 | T3 | T3-TE-0116 | SITAG |  | SIT NFT Scenarios & Test Cases Approved - Theme 3 | 100% | 18/09/24 | 18/09/24 | 0 days | 18/09/24 | 18/09/24 | 0 days | -1 day | 0 days | SI Test |  | 5.3 | Yes
7 | 1.4.1.4.4.3.4 |  |  | SITAG |  | SIT NFT Programme RTTM | 95% | 18/09/24 | 19/11/24 | 45 days | 18/09/24 | 16/10/24 | 0 days | 24 days | 45 days |  |  | 6.11 | Yes
8 | 1.4.1.4.4.3.4.1 |  |  | SITAG |  | Develop Manual SIT NFT RTTM | 100% | 18/09/24 | 29/10/24 | 30 days | 18/09/24 | 29/10/24 | 0 days | 0 days | 30 days |  |  | 6.11 | Yes
8 | 1.4.1.4.4.3.4.2 |  |  | SITAG |  | LDP peer review | 100% | 30/10/24 | 12/11/24 | 10 days | 30/10/24 | 12/11/24 | 0 days | 0 days | 10 days |  |  | 6.11 | Yes
8 | 1.4.1.4.4.3.4.3 |  |  | SITAG |  | Review with SRO | 100% | 13/11/24 | 19/11/24 | 5 days | 13/11/24 | 19/11/24 | 0 days | 0 days | 5 days |  |  | 6.11 | Yes
8 | 1.4.1.4.4.3.4.4 |  |  | SITAG |  | DIP Manager / Code Bodies / Full SRO to review | 100% | 13/11/24 | 19/11/24 | 5 days | 13/11/24 | 19/11/24 | 0 days | 0 days | 5 days |  |  | 6.12 | Yes |  | 13/01/25 - Code Bodies and SRO have provided feedback on NFT RTTM, but programme awaiting feedback from DIP Managers. Once feedback has been recieved from DIP Managers, this can be concluded.
8 | 1.4.1.4.4.3.4.5 |  |  | SITAG |  | DIP Manager / Code Bodies / Full SRO acceptance of RTTM | 100% | 19/11/24 | 19/11/24 | 0 days | 19/11/24 | 19/11/24 | 1 day | 0 days | 0 days |  |  | 6.16 | Yes |  | 13/01/25 - Code Bodies and SRO have provided feedback on NFT RTTM, but programme awaiting feedback from DIP Managers. Once feedback has been recieved from DIP Managers, this can be concluded.
8 | 1.4.1.4.4.3.4.6 |  |  | SITAG |  | Manual SIT NFT RTTM Complete | 100% | 19/11/24 | 19/11/24 | 0 days | 19/11/24 | 19/11/24 | 1 day | 0 days | 0 days |  |  | 6.11 | Yes
7 | 1.4.1.4.4.3.5 |  |  | SITAG |  | Production of NFT RTTM | 0% | 23/01/25 | 18/02/25 | 19 days? | 26/08/24 | 11/10/24 | 108 days | 92 days | 19 days? | SI Test |  | 6.15 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
8 | 1.4.1.4.4.3.5.1 |  |  | SITAG |  | Test Script updates identified | 0% | 23/01/25 | 23/01/25 | 1 day? | 23/01/25 | 23/01/25 | 0 days | 0 days | 1 day? | SI Test |  | 6.15 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
8 | 1.4.1.4.4.3.5.2 |  |  | SITAG |  | Test Scripts updates | 0% | 24/01/25 | 24/01/25 | 1 day | 24/01/25 | 24/01/25 | 0 days | 0 days | 1 day | SI Test |  | 6.15 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
8 | 1.4.1.4.4.3.5.3 |  |  | SITAG |  | RTTM Updated Additional RTTM WBS items | 0% | 23/01/25 | 05/02/25 | 10 days | 23/01/25 | 05/02/25 | 0 days | 0 days | 10 days | SI Test |  | 6.15 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
8 | 1.4.1.4.4.3.5.4 |  |  | SITAG |  | Removal of de-scoped TCs from the RTTMs | 0% | 30/01/25 | 05/02/25 | 5 days | 30/01/25 | 05/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6.15 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
8 | 1.4.1.4.4.3.5.5 |  |  | SITAG |  | Update and stabilisation of all TC ADO IDs | 0% | 30/01/25 | 18/02/25 | 14 days | 30/01/25 | 18/02/25 | 0 days | 0 days | 14 days | SI Test |  | 6.15 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
8 | 1.4.1.4.4.3.5.6 |  |  | SITAG |  | Addition and integration of Role tags to reqs in the Role RTTMs | 0% | 30/01/25 | 05/02/25 | 5 days | 30/01/25 | 05/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6.15 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
8 | 1.4.1.4.4.3.5.7 |  |  | SITAG |  | Update of the RTTM All sheet (porting of the individual RTTMs) | 0% | 04/02/25 | 12/02/25 | 7 days | 04/02/25 | 12/02/25 | 0 days | 0 days | 7 days | SI Test |  | 6.15 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
8 | 1.4.1.4.4.3.5.8 |  |  | SITAG |  | Define Additional ADO Tags | 0% | 03/02/25 | 03/02/25 | 1 day | 03/02/25 | 03/02/25 | 0 days | 0 days | 1 day | SI Test |  | 6.15 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
8 | 1.4.1.4.4.3.5.9 |  |  | SITAG |  | Non-Functional RTTM ready for import into ADO | 0% | 12/02/25 | 12/02/25 | 0 days | 12/02/25 | 12/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
8 | 1.4.1.4.4.3.5.10 |  |  | SITAG |  | Further Interative Deepdive on the requirements to testcase mapping | 0% | 30/01/25 | 11/02/25 | 9 days | 30/01/25 | 11/02/25 | 0 days | 0 days | 9 days | SI Test |  | 6.15 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
8 | 1.4.1.4.4.3.5.11 |  |  | SITAG |  | Internal review | 0% | 30/01/25 | 05/02/25 | 5 days | 30/01/25 | 05/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6.15 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
8 | 1.4.1.4.4.3.5.12 |  |  | SITAG |  | Issue Static RTTM to Code Bodies | 0% | 07/02/25 | 07/02/25 | 1 day? | 07/02/25 | 07/02/25 | 0 days | 0 days | 1 day? | SI Test |  | 6.15 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
8 | 1.4.1.4.4.3.5.13 |  |  | SITAG |  | Code Body Acceptance of RTTM | 100% | 07/02/25 | 07/02/25 | 0 days | 30/10/24 | 10/02/25 | 73 days | -1 day | 0 days | Code Bodies |  | 6.15 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
7 | 1.4.1.4.4.3.6 |  |  | SITAG |  | NFT (Theme 1, 2 and 3) DITL | 44% | 03/02/25 | 26/02/25 | 18 days | 08/10/24 | 17/10/24 | 84 days | 94 days | 18 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.3.6.1 |  |  | SITAG |  | DITL Development | 80% | 03/02/25 | 14/02/25 | 10 days | 03/02/25 | 14/02/25 | 0 days | 0 days | 10 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.3.6.2 |  |  | SITAG |  | SRO Review | 0% | 17/02/25 | 21/02/25 | 5 days | 17/02/25 | 21/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.3.6.3 |  |  | SITAG |  | Post-SRO Review Changes | 0% | 24/02/25 | 26/02/25 | 3 days | 24/02/25 | 26/02/25 | 0 days | 0 days | 3 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.3.6.4 |  |  | SITAG |  | Programme walkthrough with Theme 1 PPs on DITL | 0% | 26/02/25 | 26/02/25 | 0 days | 26/02/25 | 26/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.4.3.7 |  |  | SITAG |  | NFT Performance Tool Theme 1 Setup | 98% | 04/03/24 | 12/03/25 | 268 days? | 04/03/24 | 10/01/25 | 0 days | 43 days | 268 days? |  |  | 6.1 | Yes
8 | 1.4.1.4.4.3.7.1 |  |  | SITAG |  | Theme 1 injection tool initial POC | 100% | 04/03/24 | 28/06/24 | 85 days? | 04/03/24 | 28/06/24 | 0 days | 0 days | 85 days? |  |  | 6.1 | Yes
8 | 1.4.1.4.4.3.7.2 |  |  | SITAG |  | Theme 1 injection tool configuration and validation against DIP SIM (IR7.1) | 100% | 01/07/24 | 21/08/24 | 38 days | 01/07/24 | 21/08/24 | 0 days | 0 days | 38 days |  |  | 6.1 | Yes
8 | 1.4.1.4.4.3.7.3 |  |  | SITAG |  | Theme 1 injection tool configuration and validation against DIP SIM (IR8.1) | 100% | 22/08/24 | 01/10/24 | 29 days | 22/08/24 | 01/10/24 | 0 days | 0 days | 29 days |  |  | 6.1 | Yes
8 | 1.4.1.4.4.3.7.4 |  |  | SITAG |  | Theme 1 injection tool configuration and validation againast UIT DIP (IR8.1) | 100% | 02/10/24 | 16/10/24 | 11 days | 02/10/24 | 16/10/24 | 0 days | 0 days | 11 days |  |  | 6.1 | Yes
8 | 1.4.1.4.4.3.7.5 |  |  | SITAG |  | Theme 1 injection tool configuration and validation against SIT-B DIP (IR8.X) | 0% | 10/03/25 | 12/03/25 | 3 days? | 06/01/25 | 08/01/25 | 45 days | 45 days | 3 days? |  |  | 6.1 | Yes
6 | 1.4.1.4.4.4 |  |  | SITAG |  | Environments (SIT B) | 0% | 27/08/24 | 28/02/25 | 134 days | 27/08/24 | 03/01/25 | 0 days | 40 days | 134 days | N/A |  | 5 | Yes
7 | 1.4.1.4.4.4.1 |  |  | SITAG |  | PP Environments (SIT B) | 100% | 27/08/24 | 27/08/24 | 0 days | 27/08/24 | 27/08/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.4.4.1.1 |  |  | SITAG |  | Deployment of MHHS solution code to SIT B environments | 100% | 27/08/24 | 27/08/24 | 0 days | 27/08/24 | 27/08/24 | 0 days | -1 day | 0 days | PP |  | 5.21 | Yes
7 | 1.4.1.4.4.4.2 |  |  | SITAG |  | SI Environments (SIT B) | 100% | 27/08/24 | 27/08/24 | 0 days | 27/08/24 | 27/08/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.4.4.2.1 |  |  | SITAG |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT B environments | 100% | 27/08/24 | 27/08/24 | 0 days | 27/08/24 | 27/08/24 | 0 days | -1 day | 0 days | SI Test |  | 5.21 | Yes
7 | 1.4.1.4.4.4.3 |  |  | SITAG |  | Helix and Avanade Environments Upscale | 0% | 24/02/25 | 28/02/25 | 5 days | 23/12/24 | 03/01/25 | 45 days | 40 days | 5 days |  |  | 6 | Yes
8 | 1.4.1.4.4.4.3.1 |  |  | SITAG |  | Environment Uplift Window | 0% | 24/02/25 | 28/02/25 | 5 days | 23/12/24 | 03/01/25 | 45 days | 40 days | 5 days |  |  | 6 | Yes
6 | 1.4.1.4.4.5 |  |  | SITAG |  | Test Data - Non-Functional and Operational (SIT B) | 0% | 24/02/25 | 28/03/25 | 25 days? | 06/01/25 | 14/03/25 | 35 days | 10 days | 25 days? |  |  | 6 | Yes
7 | 1.4.1.4.4.5.1 |  |  | SITAG |  | Data Load | 0% | 24/02/25 | 28/03/25 | 25 days? | 06/01/25 | 14/03/25 | 35 days | 10 days | 25 days? |  |  | 6 | Yes
8 | 1.4.1.4.4.5.1.1 | T3 | T3-TE-0126 | SITAG |  | Non-Functional Theme 1 (Avenade) Data Load | 0% | 24/02/25 | 28/02/25 | 5 days? | 24/02/25 | 28/02/25 | 0 days | 0 days | 5 days? | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.5.1.2 | T3 | T3-TE-0127 | SITAG |  | Non-Functional Theme 2 & 3 (Helix, Avenade & PPs) Data Load | 0% | 24/03/25 | 28/03/25 | 5 days | 24/03/25 | 28/03/25 | 0 days | 0 days | 5 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.5.1.3 | T3 | T3-TE-0128 | SITAG |  | Non-Functional Themes 2 & 3 (LDSO's and DCC) Data Load | 0% | 03/03/25 | 21/03/25 | 15 days | 03/03/25 | 21/03/25 | 0 days | 0 days | 15 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.5.1.4 | T3 | T3-TE-0129 | SITAG |  | Operational Themes 1, 2 & 3 (Batch 2) (LDSO's and DCC) Data Load | 0% | 03/03/25 | 28/03/25 | 20 days? | 03/03/25 | 28/03/25 | 0 days | 0 days | 20 days? | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.5.1.5 | T3 | T3-TE-0130 | SITAG |  | Operational Themes 1, 2 & 3 (Batch 2) (Helix, Avenade & PPs) Data Load | 0% | 24/03/25 | 28/03/25 | 5 days | 24/03/25 | 28/03/25 | 0 days | 0 days | 5 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.4.5.1.6 | T3 | T3-TE-0131 | SITAG |  | Non-Functional and Operational Test Data Preparation Complete | 0% | 28/03/25 | 28/03/25 | 0 days | 28/03/25 | 28/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
6 | 1.4.1.4.4.6 |  |  | SITAG |  | SIT Non-Functional Test Readiness Report | 7% | 20/01/25 | 27/03/25 | 48 days | 25/06/24 | 07/03/25 | 149 days | 13 days | 4 days | N/A |  | 5 | Yes
7 | 1.4.1.4.4.6.1 |  |  | SITAG |  | SIT Non-Functional Theme 1 Overarching Test Readiness Report | 0% | 21/01/25 | 28/02/25 | 29 days | 25/06/24 | 10/01/25 | 150 days | 35 days | -11 days | N/A |  | 6.15 | Yes
8 | 1.4.1.4.4.6.1.1 |  |  | SITAG |  | Develop Overarching SIT Non-Functional Theme 1 Overarching Test Readiness Report | 0% | 21/01/25 | 04/02/25 | 11 days | 02/12/24 | 20/12/24 | 36 days | 32 days | -9 days | SI Test |  | 6.16 | Yes |  | 15/01/25 - There are still outstanding PIT documentation that need to be submitted by participants, which puts delivery at risk. Programme will be presenting the governance route overarching reports will go through at January SITAG, if endorsed, overarchi
8 | 1.4.1.4.4.6.1.2 |  |  | SITAG |  | SRO review | 0% | 05/02/25 | 11/02/25 | 5 days | 10/01/25 | 16/01/25 | 18 days | 18 days | 5 days |  |  | 6.16 | Yes |  | 15/01/25 - Programme will be presenting the governance route overarching reports will go through at January SITAG, if endorsed, overarching report will be rebaselined and RAGs will return to green.
8 | 1.4.1.4.4.6.1.3 |  |  | SITAG |  | NFTWG paper day | 0% | 11/02/25 | 11/02/25 | 0 days | 16/01/25 | 16/01/25 | 19 days | 18 days | 0 days |  |  | 6.15 | Yes |  | 15/01/25 - Programme will be presenting the governance route overarching reports will go through at January SITAG, if endorsed, overarching report will be rebaselined and RAGs will return to green.
8 | 1.4.1.4.4.6.1.4 |  |  | SITAG |  | NFTWG review the Non-Functional Theme 1 Overarching Test Readiness Report | 0% | 18/02/25 | 18/02/25 | 0 days | 23/01/25 | 23/01/25 | 19 days | 18 days | 0 days |  |  | 6.15 | Yes |  | 15/01/25 - Programme will be presenting the governance route overarching reports will go through at January SITAG, if endorsed, overarching report will be rebaselined and RAGs will return to green.
8 | 1.4.1.4.4.6.1.5 |  |  | SITAG |  | Update Non-Functional Theme 1 Overarching Test Readiness Report following SRO / NFTWG feedback | 0% | 19/02/25 | 26/02/25 | 6 days | 17/01/25 | 12/02/25 | 23 days | 10 days | 6 days |  |  | 6.15 | Yes
8 | 1.4.1.4.4.6.1.6 |  |  | SITAG |  | eSITAG paper day | 0% | 26/02/25 | 26/02/25 | 0 days | 12/02/25 | 12/02/25 | 11 days | 10 days | 0 days |  |  | 6.16 | Yes
8 | 1.4.1.4.4.6.1.7 |  | T3-TE-XXXX | SITAG |  | eSITAG approve Non-Functional Theme 1 Overarching Test Readiness Report | 0% | 28/02/25 | 28/02/25 | 0 days | 28/02/25 | 28/02/25 | 1 day | 0 days | 0 days |  |  | 6.16 | Yes |  | 15/01/25 - Programme will ask Jan SITAG to approve creation of milestone ID for this activity.
7 | 1.4.1.4.4.6.2 |  |  | SITAG |  | SIT Non-Functional Overarching Test Readiness Report Theme 2 & 3 | 0% | 18/02/25 | 27/03/25 | 27 days | 13/01/25 | 28/03/25 | 26 days | -2 days | 27 days |  |  | 6.15 | Yes
8 | 1.4.1.4.4.6.2.1 |  |  | SITAG |  | Develop Overarching SIT Non-Functional Overarching Test Readiness Report Theme 2 & 3 | 0% | 18/02/25 | 04/03/25 | 11 days | 13/01/25 | 04/02/25 | 26 days | 20 days | 11 days |  |  | 6.16 | Yes |  | 15/01/25 - There are still outstanding PIT documentation that need to be submitted by participants, which puts delivery at risk. Programme will be presenting the governance route overarching reports will go through at January SITAG, if endorsed, overarchi
8 | 1.4.1.4.4.6.2.2 |  |  | SITAG |  | SRO review | 0% | 05/03/25 | 11/03/25 | 5 days | 05/02/25 | 11/02/25 | 20 days | 20 days | 5 days |  |  | 6.16 | Yes |  | 15/01/25 - Programme will be presenting the governance route overarching reports will go through at January SITAG, if endorsed, overarching report approach will be rebaselined.
8 | 1.4.1.4.4.6.2.3 |  |  | SITAG |  | NFTWG paper day | 0% | 11/03/25 | 11/03/25 | 0 days | 11/02/25 | 11/02/25 | 21 days | 20 days | 0 days |  |  | 6.15 | Yes
8 | 1.4.1.4.4.6.2.4 |  |  | SITAG |  | NFTWG review the Non-Functional Overarching Test Readiness Report Theme 2 & 3 | 0% | 18/03/25 | 18/03/25 | 0 days | 18/02/25 | 18/02/25 | 21 days | 20 days | 0 days |  |  | 6.15 | Yes
8 | 1.4.1.4.4.6.2.5 |  |  | SITAG |  | Update Non-Functional Overarching Test Readiness Report Theme 2 & 3 following SRO / NFTWG feedback | 0% | 19/03/25 | 25/03/25 | 5 days | 19/02/25 | 12/03/25 | 20 days | 9 days | 5 days |  |  | 6.15 | Yes |  | 15/01/25 - Programme will be presenting the governance route overarching reports will go through at January SITAG, if endorsed, overarching report approach will be rebaselined.
8 | 1.4.1.4.4.6.2.6 |  |  | SITAG |  | eSITAG paper day | 0% | 25/03/25 | 25/03/25 | 0 days | 12/03/25 | 12/03/25 | 10 days | 9 days | 0 days |  |  | 6.16 | Yes |  | 15/01/25 - Programme will be presenting the governance route overarching reports will go through at January SITAG, if endorsed, overarching report approach will be rebaselined.
8 | 1.4.1.4.4.6.2.7 |  | T3-TE-XXXX | SITAG |  | eSITAG approve Non-Functional Overarching Test Readiness Report Theme 2 & 3 | 0% | 27/03/25 | 27/03/25 | 0 days | 28/03/25 | 28/03/25 | -1 day | -2 days | 0 days |  |  | 6.16 | Yes |  | 15/01/25 - Programme will ask Jan SITAG to approve creation of milestone ID for this activity.
7 | 1.4.1.4.4.6.3 |  |  | SITAG |  | SIT Non-Functional Execution Model | 14% | 20/01/25 | 14/02/25 | 20 days | 20/01/25 | 12/02/25 | 0 days | 2 days | 20 days |  |  | 6.15 | Yes
8 | 1.4.1.4.4.6.3.1 |  |  | SITAG |  | Theme 1 | 23% | 20/01/25 | 12/02/25 | 18 days | 20/01/25 | 12/02/25 | 0 days | 0 days | 18 days |  |  | 6.15 | Yes
9 | 1.4.1.4.4.6.3.1.1 |  |  | SITAG |  | Develop execution model Theme 1 | 100% | 20/01/25 | 22/01/25 | 3 days | 20/01/25 | 22/01/25 | 0 days | 0 days | 3 days |  |  | 6.15 | Yes
9 | 1.4.1.4.4.6.3.1.2 |  |  | SITAG |  | SRO provide feedback | 0% | 23/01/25 | 29/01/25 | 5 days | 23/01/25 | 29/01/25 | 0 days | 0 days | 5 days |  |  | 6.15 | Yes
9 | 1.4.1.4.4.6.3.1.3 |  |  | SITAG |  | Address SRO feedback on execution model | 0% | 30/01/25 | 31/01/25 | 2 days | 30/01/25 | 31/01/25 | 0 days | 0 days | 2 days |  |  | 6.15 | Yes
9 | 1.4.1.4.4.6.3.1.4 |  |  | SITAG |  | Finalise execution model | 0% | 03/02/25 | 05/02/25 | 3 days | 03/02/25 | 05/02/25 | 0 days | 0 days | 3 days |  |  | 6.15 | Yes
9 | 1.4.1.4.4.6.3.1.5 |  |  | SITAG |  | SITWG paper day | 0% | 05/02/25 | 05/02/25 | 0 days | 05/02/25 | 05/02/25 | 1 day | 0 days | 0 days |  |  | 6.15 | Yes
9 | 1.4.1.4.4.6.3.1.6 |  |  | SITAG |  | SITWG update on execution model | 0% | 12/02/25 | 12/02/25 | 0 days | 12/02/25 | 12/02/25 | 1 day | 0 days | 0 days |  |  | 6.15 | Yes
8 | 1.4.1.4.4.6.3.2 |  |  | SITAG |  | Theme 2 & 3 | 23% | 20/01/25 | 12/02/25 | 18 days | 20/01/25 | 12/02/25 | 0 days | 0 days | 18 days |  |  | 6.15 | Yes
9 | 1.4.1.4.4.6.3.2.1 |  |  | SITAG |  | Develop execution model Theme 2 & 3 | 100% | 20/01/25 | 22/01/25 | 3 days | 20/01/25 | 22/01/25 | 0 days | 0 days | 3 days |  |  | 6.15 | Yes
9 | 1.4.1.4.4.6.3.2.2 |  |  | SITAG |  | SRO provide feedback | 0% | 23/01/25 | 29/01/25 | 5 days | 23/01/25 | 29/01/25 | 0 days | 0 days | 5 days |  |  | 6.15 | Yes
9 | 1.4.1.4.4.6.3.2.3 |  |  | SITAG |  | Address SRO feedback on execution model | 0% | 30/01/25 | 31/01/25 | 2 days | 30/01/25 | 31/01/25 | 0 days | 0 days | 2 days |  |  | 6.15 | Yes
9 | 1.4.1.4.4.6.3.2.4 |  |  | SITAG |  | Finalise execution model | 0% | 03/02/25 | 05/02/25 | 3 days | 03/02/25 | 05/02/25 | 0 days | 0 days | 3 days |  |  | 6.15 | Yes
9 | 1.4.1.4.4.6.3.2.5 |  |  | SITAG |  | SITWG paper day | 0% | 05/02/25 | 05/02/25 | 0 days | 05/02/25 | 05/02/25 | 1 day | 0 days | 0 days |  |  | 6.15 | Yes
9 | 1.4.1.4.4.6.3.2.6 |  |  | SITAG |  | SITWG update on execution model | 0% | 12/02/25 | 12/02/25 | 0 days | 12/02/25 | 12/02/25 | 1 day | 0 days | 0 days |  |  | 6.15 | Yes
8 | 1.4.1.4.4.6.3.3 |  |  | SITAG |  | SIT Non-Functional Progress reporting | 0% | 23/01/25 | 14/02/25 | 17 days | 30/12/24 | 24/01/25 | 18 days | 15 days | 17 days |  |  | 6.14 | Yes
9 | 1.4.1.4.4.6.3.3.1 |  |  | SITAG |  | Determine reporting methodology | 0% | 23/01/25 | 24/01/25 | 2 days | 23/01/25 | 24/01/25 | 0 days | 0 days | 2 days |  |  | 6.14 | Yes
9 | 1.4.1.4.4.6.3.3.2 | T2 |  | SITAG |  | Implement reporting | 0% | 27/01/25 | 14/02/25 | 15 days | 27/01/25 | 14/02/25 | 0 days | 0 days | 15 days | SI Test |  | 6.14 | Yes
6 | 1.4.1.4.4.7 |  | T2-TE-0700 | SITAG |  | SIT Non-Functional Testing Preparation Complete Theme 1 | 0% | 28/02/25 | 28/02/25 | 0 days | 28/02/25 | 28/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
6 | 1.4.1.4.4.8 | T2 | T2-TE-1100 | SITAG |  | SIT Non-Functional Testing Preparation Complete Theme 2 & 3 | 0% | 28/03/25 | 28/03/25 | 0 days | 28/03/25 | 28/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
5 | 1.4.1.4.5 |  |  | SITAG |  | SIT Operational Preparation | 89% | 31/10/22 | 05/05/25 | 656 days? | 01/02/24 | 31/01/25 | -328 days | 66 days | 373 days? | N/A |  | 5 | Yes
6 | 1.4.1.4.5.1 |  |  | SITAG |  | Test Approach & Plan | 100% | 01/02/24 | 15/05/24 | 75 days | 01/02/24 | 15/05/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.5.1.1 |  |  | SITAG |  | Develop document with SITWG | 100% | 01/02/24 | 06/03/24 | 25 days | 01/02/24 | 06/03/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.5.1.2 |  |  | SITAG |  | Draft document review with Code Bodies | 100% | 21/03/24 | 26/03/24 | 4 days | 21/03/24 | 26/03/24 | 0 days | 0 days | -6 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.5.1.3 |  |  | SITAG |  | Industry Consultation | 100% | 27/03/24 | 09/04/24 | 10 days | 27/03/24 | 09/04/24 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.5.1.4 |  |  | SITAG |  | Artefact review (via SITAG) and updates | 100% | 10/04/24 | 15/05/24 | 26 days | 10/04/24 | 15/05/24 | 0 days | 0 days | -4 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.5.1.5 | T3 | T3-TE-0029 | SITAG | MHHS-ART073 | SIT Operational Testing Test Approach & Plan approved | 100% | 15/05/24 | 15/05/24 | 0 days | 15/05/24 | 15/05/24 | 1 day | 0 days | 0 days | SI Test |  | 5.24 | Yes
6 | 1.4.1.4.5.2 |  |  | SITAG |  | Test Data Approach & Plan | 100% | 27/03/24 | 15/05/24 | 36 days | 27/03/24 | 15/05/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.5.2.1 |  |  | SITAG |  | Industry Consultation | 100% | 27/03/24 | 09/04/24 | 10 days | 27/03/24 | 09/04/24 | 0 days | 0 days | 0 days | PP |  | 5.1 | Yes
7 | 1.4.1.4.5.2.2 |  |  | SITAG |  | Artefact review (via SITAG) and updates | 100% | 10/04/24 | 15/05/24 | 26 days | 10/04/24 | 15/05/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.1.4.5.2.3 |  |  | SITAG |  | SIT Operational Testing Test Data Approach & Plan approved | 100% | 15/05/24 | 15/05/24 | 0 days | 15/05/24 | 15/05/24 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.1.4.5.3 |  |  | SITAG |  | Test scenarios & Test Cases | 100% | 10/04/24 | 06/09/24 | 108 days | 10/04/24 | 31/01/25 | 0 days | -105 days | -8 days | N/A |  | 5.21 | Yes
7 | 1.4.1.4.5.3.1 |  |  | SITAG |  | Theme 1 | 100% | 10/04/24 | 06/09/24 | 108 days | 10/04/24 | 06/09/24 | 0 days | 0 days | 12 days | N/A |  | 6 | Yes
8 | 1.4.1.4.5.3.1.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases | 100% | 10/04/24 | 21/06/24 | 53 days | 10/04/24 | 21/06/24 | 0 days | 0 days | 37 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.3.1.2 |  |  | SITAG |  | Industry Review Workshop | 100% | 24/06/24 | 24/06/24 | 1 day | 24/06/24 | 24/06/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.5.3.1.3 |  |  | SITAG |  | Industry Consultation Review | 100% | 02/07/24 | 09/07/24 | 6 days | 02/07/24 | 09/07/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.5.3.1.4 |  |  | SITAG |  | Review with SIT Working Group | 100% | 19/08/24 | 23/08/24 | 5 days | 19/08/24 | 23/08/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.5.3.1.5 | T3 | T3-TE-0117 | SITAG |  | SIT Operational Scenarios & Test Cases Approved - Theme 1 | 100% | 06/09/24 | 06/09/24 | 0 days | 06/09/24 | 06/09/24 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
7 | 1.4.1.4.5.3.2 |  |  | SITAG |  | Theme 2 | 100% | 10/04/24 | 06/09/24 | 107 days | 10/04/24 | 06/09/24 | 0 days | -1 day | 36 days | N/A |  | 6 | Yes
8 | 1.4.1.4.5.3.2.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases | 100% | 10/04/24 | 21/06/24 | 53 days | 10/04/24 | 21/06/24 | 0 days | 0 days | 22 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.3.2.2 |  |  | SITAG |  | Industry Review Workshop | 100% | 24/06/24 | 24/06/24 | 1 day | 24/06/24 | 24/06/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.5.3.2.3 |  |  | SITAG |  | Industry Consultation Review | 100% | 02/07/24 | 09/07/24 | 6 days | 02/07/24 | 09/07/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.5.3.2.4 |  |  | SITAG |  | Review with SIT Working Group | 100% | 19/08/24 | 23/08/24 | 5 days | 19/08/24 | 23/08/24 | 0 days | 0 days | 0 days | SI Test, PP |  | 6 | Yes
8 | 1.4.1.4.5.3.2.5 | T3 | T3-TE-0118 | SITAG |  | SIT Operational Scenarios & Test Cases Approved - Theme 2 | 100% | 06/09/24 | 06/09/24 | 0 days | 06/09/24 | 06/09/24 | 0 days | -1 day | 0 days | SI Test |  | 6 | Yes
6 | 1.4.1.4.5.4 |  |  |  |  | SIT Operations Manual | 97% | 31/10/22 | 31/01/25 | 589 days? | 31/10/22 | 31/01/25 | 0 days | -1 day | 589 days? |  |  | 6.13 | Yes
7 | 1.4.1.4.5.4.1 |  |  |  |  | Version 1 SIT Operations Manual | 100% | 07/10/24 | 22/11/24 | 35 days | 07/10/24 | 22/11/24 | 0 days | 0 days | 35 days |  |  | 6.13 | Yes
8 | 1.4.1.4.5.4.1.1 |  |  |  |  | Creation of SIT Operations Manual Template | 100% | 07/10/24 | 16/10/24 | 8 days | 07/10/24 | 16/10/24 | 0 days | 0 days | 8 days |  |  | 6.13 | Yes
8 | 1.4.1.4.5.4.1.2 |  |  |  |  | November TORWG Paper Day | 100% | 07/11/24 | 07/11/24 | 0 days | 07/11/24 | 07/11/24 | 1 day | 0 days | 0 days |  |  | 6.13 | Yes
8 | 1.4.1.4.5.4.1.3 |  |  |  |  | November TORWG (Timeline and Next Steps for SIT Operations Manual) | 100% | 14/11/24 | 14/11/24 | 0 days | 14/11/24 | 14/11/24 | 1 day | 0 days | 0 days |  |  | 6.13 | Yes
8 | 1.4.1.4.5.4.1.4 |  |  |  |  | SIT Operations Manual Version 1 Shared with MHHSP | 100% | 11/11/24 | 11/11/24 | 0 days | 11/11/24 | 11/11/24 | 1 day | 0 days | 0 days |  |  | 6.13 | Yes
8 | 1.4.1.4.5.4.1.5 |  |  |  |  | MHHSP provide feedback on SIT Operations Manual Version 1 | 100% | 12/11/24 | 22/11/24 | 9 days | 12/11/24 | 22/11/24 | 0 days | 0 days | 9 days |  |  | 6.13 | Yes
8 | 1.4.1.4.5.4.1.6 |  |  |  |  | SIT Operations Manual Version 1 Shared with Programme Participants | 100% | 13/11/24 | 13/11/24 | 0 days | 13/11/24 | 13/11/24 | 1 day | 0 days | 0 days |  |  | 6.13 | Yes
8 | 1.4.1.4.5.4.1.7 |  |  |  |  | PPs provide feedback on SIT Operations Manual Version 1 | 100% | 14/11/24 | 22/11/24 | 7 days | 14/11/24 | 22/11/24 | 0 days | 0 days | 7 days |  |  | 6.13 | Yes
8 | 1.4.1.4.5.4.1.8 |  |  |  |  | Programme Participants and MHHSP Feedback and Actions Received (SIT Ops Manual Version 1) | 100% | 22/11/24 | 22/11/24 | 0 days | 22/11/24 | 22/11/24 | 1 day | 0 days | 0 days |  |  | 6.13 | Yes
7 | 1.4.1.4.5.4.2 |  |  |  |  | Version 2 SIT Operations Manual | 100% | 12/11/24 | 18/12/24 | 27 days | 12/11/24 | 18/12/24 | 0 days | 0 days | 27 days |  |  | 6.13 | Yes
8 | 1.4.1.4.5.4.2.1 |  |  |  |  | Version 2 SIT Operations Manual (Composition) | 100% | 12/11/24 | 27/11/24 | 12 days | 12/11/24 | 27/11/24 | 0 days | 0 days | 12 days |  |  | 6.13 | Yes
8 | 1.4.1.4.5.4.2.2 | T3 | T3-TE-0132 | MCAG |  | Version 2 SIT Operations Manual Completed | 100% | 27/11/24 | 27/11/24 | 0 days | 27/11/24 | 27/11/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes |  | 27/11/24 - New milestone added by Programme, awaiting formal SITAG approval.
8 | 1.4.1.4.5.4.2.3 |  |  |  |  | Version 2 SIT Operations Manual Shared with MHHSP & PPs for TORWG (Consultation Starts) | 100% | 27/11/24 | 27/11/24 | 0 days | 27/11/24 | 27/11/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.2.4 |  |  |  |  | Version 2 SIT Ops Manual - PP Consultation (Iterative Feedback Process) | 100% | 28/11/24 | 11/12/24 | 10 days | 28/11/24 | 11/12/24 | 0 days | 0 days | 10 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.2.5 |  |  |  |  | Version 2 SIT Ops Manual - PP Consultation Completed | 100% | 11/12/24 | 11/12/24 | 0 days | 11/12/24 | 11/12/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.2.6 |  |  |  |  | December TORWG Paper Day | 100% | 04/12/24 | 04/12/24 | 0 days | 04/12/24 | 04/12/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.2.7 |  |  |  |  | December TORWG (Initial Feedback, Common Themes and Comments) | 100% | 11/12/24 | 11/12/24 | 0 days | 11/12/24 | 11/12/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.2.8 |  |  |  |  | December Extraordinary TORWG Paper Day | 100% | 11/12/24 | 11/12/24 | 0 days | 11/12/24 | 11/12/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.2.9 |  |  |  |  | Publication of key themes from consultation to eTORWG | 100% | 12/12/24 | 13/12/24 | 2 days | 12/12/24 | 13/12/24 | 0 days | 0 days | 2 days | Helix |  | 6.14 | Yes
8 | 1.4.1.4.5.4.2.10 |  |  |  |  | December Extraordinary TORWG (Summary of Version 2 Feedback and Response Approach Shared with PPs) | 100% | 18/12/24 | 18/12/24 | 0 days | 18/12/24 | 18/12/24 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
7 | 1.4.1.4.5.4.3 |  |  |  |  | Version 3 (Final) SIT Operations Manual | 99% | 28/11/24 | 28/01/25 | 44 days | 28/11/24 | 28/01/25 | 0 days | 0 days | 44 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.3.1 |  |  |  |  | Update SIT Operations Manual (Final) Version 3 (with Comments Received From Version 2) [Pre-Christmas Furlough] | 100% | 28/11/24 | 20/12/24 | 17 days | 28/11/24 | 20/12/24 | 0 days | 0 days | 17 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.3.2 |  |  |  |  | Update SIT Operations Manual (Final) Version 3 (with Comments Received From Version 2) [Post-Christmas Furlough] | 100% | 02/01/25 | 08/01/25 | 5 days | 02/01/25 | 08/01/25 | 0 days | 0 days | 5 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.3.3 | T3 | T3-TE-0133 | MCAG |  | SIT Operations Manual (Final) Version 3 Completed | 100% | 08/01/25 | 08/01/25 | 0 days | 08/01/25 | 08/01/25 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.3.4 |  |  |  |  | January TORWG Paper Day | 100% | 08/01/25 | 08/01/25 | 0 days | 08/01/25 | 08/01/25 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.3.5 |  |  |  |  | January TORWG (SIT Operations Manual Agreement) [Assurance Meeting] | 0% | 15/01/25 | 15/01/25 | 0 days | 15/01/25 | 15/01/25 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.3.6 |  |  |  |  | January MCAG Paper Day (Final SIT Operations Manual Submitted) | 0% | 21/01/25 | 21/01/25 | 0 days | 21/01/25 | 21/01/25 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.3.7 | T3 | T3-TE-0135 | MCAG |  | January MCAG (Final SIT Operations Manual Endorsement) [Advisory Group Sign-off] | 0% | 28/01/25 | 28/01/25 | 0 days | 28/01/25 | 28/01/25 | 1 day | 0 days | 0 days | Helix |  | 6.13 | Yes
7 | 1.4.1.4.5.4.4 |  |  |  |  | Elexon / Helix Service Now Test Prep | 100% | 01/08/24 | 14/01/25 | 119 days? | 15/07/24 | 31/01/25 | 13 days | -13 days | 119 days? | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.4.1 |  |  |  |  | Incident Management Build | 100% | 05/08/24 | 15/11/24 | 75 days? | 05/08/24 | 15/11/24 | 0 days | 0 days | 75 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.1.1 |  |  |  |  | Build | 100% | 05/08/24 | 27/09/24 | 40 days | 27/09/24 | 27/09/24 | -39 days | 0 days | 40 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.1.2 |  |  |  |  | Test | 100% | 30/09/24 | 18/10/24 | 15 days | 18/10/24 | 18/10/24 | -14 days | 0 days | 15 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.1.3 |  |  |  |  | Deploy | 100% | 21/10/24 | 15/11/24 | 20 days | 15/11/24 | 15/11/24 | -19 days | 0 days | 20 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.1.4 |  |  |  |  | Incident Management Build & Configuration Complete | 100% | 15/11/24 | 15/11/24 | 0 days | N/A | N/A | 0 days | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.4.2 |  |  |  |  | Major Incident Management Build & Configuration | 100% | 15/11/24 | 15/11/24 | 0 days? | 02/10/24 | 14/01/25 | 32 days | -43 days | 0 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.2.1 |  |  |  |  | Build | 100% | 02/10/24 | 26/11/24 | 40 days | 26/11/24 | 26/11/24 | -39 days | 0 days | 40 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.2.2 |  |  |  |  | Test | 100% | 27/11/24 | 17/12/24 | 15 days | 17/12/24 | 17/12/24 | -14 days | 0 days | 15 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.2.3 |  |  |  |  | Deploy | 100% | 18/12/24 | 14/01/25 | 20 days | 14/01/25 | 14/01/25 | -19 days | 0 days | 20 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.2.4 |  |  |  |  | Major Incident Management Build & Configuration Complete | 100% | 14/01/25 | 14/01/25 | 0 days | N/A | N/A | 0 days | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.4.3 |  |  |  |  | Knowledge Management Build & Configuration | 100% | 02/10/24 | 14/01/25 | 75 days? | 02/10/24 | 14/01/25 | 0 days | 0 days | 75 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.3.1 |  |  |  |  | Build | 100% | 02/10/24 | 26/11/24 | 40 days | 26/11/24 | 26/11/24 | -39 days | 0 days | 40 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.3.2 |  |  |  |  | Test | 100% | 27/11/24 | 17/12/24 | 15 days | 17/12/24 | 17/12/24 | -14 days | 0 days | 15 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.3.3 |  |  |  |  | Deploy | 100% | 18/12/24 | 14/01/25 | 20 days | 14/01/25 | 14/01/25 | -19 days | 0 days | 20 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.3.4 |  |  |  |  | Knowledge Management Build & Configuration Complete | 100% | 14/01/25 | 14/01/25 | 0 days | N/A | N/A | 0 days | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.4.4 |  |  |  |  | Problem Management Build & Configuration | 100% | 01/08/24 | 01/08/24 | 1 day? | 02/10/24 | 14/01/25 | -44 days | -118 days | 1 day? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.4.1 |  |  |  |  | Build | 100% | 02/10/24 | 26/11/24 | 40 days | 26/11/24 | 26/11/24 | -39 days | 0 days | 40 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.4.2 |  |  |  |  | Test | 100% | 27/11/24 | 17/12/24 | 15 days | 17/12/24 | 17/12/24 | -14 days | 0 days | 15 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.4.3 |  |  |  |  | Deploy | 100% | 18/12/24 | 14/01/25 | 20 days | 14/01/25 | 14/01/25 | -19 days | 0 days | 20 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.4.4 |  |  |  |  | Problem Management Build & Configuration Complete | 100% | 14/01/25 | 14/01/25 | 0 days | N/A | N/A | 0 days | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.4.5 |  |  |  |  | Change Management Build & Configuration | 100% | 02/10/24 | 14/01/25 | 75 days? | 02/10/24 | 14/01/25 | 0 days | 0 days | 75 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.5.1 |  |  |  |  | Build | 100% | 02/10/24 | 26/11/24 | 40 days | 26/11/24 | 26/11/24 | -39 days | 0 days | 40 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.5.2 |  |  |  |  | Test | 100% | 27/11/24 | 17/12/24 | 15 days | 17/12/24 | 17/12/24 | -14 days | 0 days | 15 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.5.3 |  |  |  |  | Deploy | 100% | 18/12/24 | 14/01/25 | 20 days | 14/01/25 | 14/01/25 | -19 days | 0 days | 20 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.5.4 |  |  |  |  | Change Management Build & Configuration Complete | 100% | 14/01/25 | 14/01/25 | 0 days | N/A | N/A | 0 days | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.4.6 |  |  |  |  | Service Catalogue Management Build & Configuration | 100% | 02/10/24 | 14/01/25 | 75 days? | 02/10/24 | 14/01/25 | 0 days | 0 days | 75 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.6.1 |  |  |  |  | Build | 100% | 02/10/24 | 26/11/24 | 40 days | 26/11/24 | 26/11/24 | -39 days | 0 days | 40 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.6.2 |  |  |  |  | Test | 100% | 27/11/24 | 17/12/24 | 15 days | 17/12/24 | 17/12/24 | -14 days | 0 days | 15 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.6.3 |  |  |  |  | Deploy | 100% | 18/12/24 | 14/01/25 | 20 days | 14/01/25 | 14/01/25 | -19 days | 0 days | 20 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.4.6.4 |  |  |  |  | Service Catalogue Management Build & Configuration Complete | 100% | 14/01/25 | 14/01/25 | 0 days | N/A | N/A | 0 days | 0 days | 0 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.4.7 | T3 | T3-TE-0136 | SITAG |  | ServiceNow SIT Ops Available | 100% | 14/01/25 | 14/01/25 | 0 days? | 14/01/25 | 14/01/25 | 1 day | 0 days | 0 days? | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.4.8 |  |  |  |  | Helix Service Management Documentation (Service Design Pack) | 100% | 01/08/24 | 08/01/25 | 115 days | 09/09/24 | 31/01/25 | -27 days | -17 days | 115 days | Helix |  | 6 | Yes
9 | 1.4.1.4.5.4.4.8.1 |  |  |  |  | Document Drafting | 100% | 01/08/24 | 11/12/24 | 95 days | 01/08/24 | 11/12/24 | 0 days | 0 days | 95 days | Helix |  | 6.11 | Yes
9 | 1.4.1.4.5.4.4.8.2 |  |  |  |  | Internal Elexon Review | 100% | 06/01/25 | 08/01/25 | 3 days | 12/12/24 | 16/12/24 | 17 days | 17 days | 3 days | Helix |  | 6.11 | Yes
9 | 1.4.1.4.5.4.4.8.3 |  |  |  |  | Elexon Service Panel Sign off | 100% | 08/01/25 | 08/01/25 | 0 days | 20/12/24 | 20/12/24 | 13 days | 12 days | 0 days | Helix |  | 6.11 | Yes
7 | 1.4.1.4.5.4.5 |  |  |  |  | Incident Management Support | 64% | 31/10/22 | 31/10/22 |  | N/A | N/A | 0 days | 0 days | 1 day? | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.5.1 |  |  |  |  | Identify Relevant Stakeholders to Support Incident Management Process | 100% | 02/12/24 | 13/12/24 | 10 days | 18/11/24 | 29/11/24 | 10 days | 10 days | 10 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.5.2 |  |  |  |  | Schedule Time to Upskill Stakeholders | 100% | 16/12/24 | 20/12/24 | 5 days | 02/12/24 | 06/12/24 | 10 days | 10 days | 5 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.5.3 |  |  |  |  | Helix Stakeholders Attendance at MHHS Defect Triage Meetings [Meeting Dates to be Confirmed] | 10% | 06/01/25 | 17/01/25 | 10 days | 09/12/24 | 20/12/24 | 20 days | 20 days | 10 days | Helix |  | 6.13 | Yes
7 | 1.4.1.4.5.4.6 |  |  |  |  | SIT Service Readiness (Elexon & Helix) Completed | 0% | 17/01/25 | 17/01/25 | 0 days | 20/12/24 | 20/12/24 | 21 days | 20 days | 0 days | Helix |  | 6.13 | Yes
7 | 1.4.1.4.5.4.7 |  |  |  |  | SIT Service Readiness (External Parties) | 99% | 07/10/24 | 24/01/25 | 80 days | 30/09/24 | 06/01/25 | 5 days | 14 days | 80 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.7.1 |  |  |  |  | Helix Engagement & Comms | 100% | 07/10/24 | 13/01/25 | 71 days | 30/09/24 | 06/01/25 | 5 days | 5 days | 71 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.7.1.1 |  |  |  |  | Engagement Execution | 100% | 07/10/24 | 13/01/25 | 71 days | 07/10/24 | 06/01/25 | 0 days | 5 days | 71 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.7.1.2 |  |  |  |  | Information Gathering | 100% | 29/11/24 | 13/01/25 | 32 days | 31/10/24 | 27/11/24 | 21 days | 33 days | 32 days | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.7.1.3 |  |  |  |  | SIT Participants Preparation | 100% | 28/11/24 | 10/12/24 | 9 days | 22/11/24 | 06/01/25 | 4 days | -19 days | 9 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.7.2 |  |  |  |  | SIT Service Readiness (External Parties) Completed | 0% | 24/01/25 | 24/01/25 | 0 days | 06/01/25 | 06/01/25 | 15 days | 14 days | 0 days | Helix |  | 6.13 | Yes |  | 13/01/25 - Additional activity may be required, hence why the baseline for this activity has been pushed back to 24/01/25.
7 | 1.4.1.4.5.4.8 |  |  |  |  | ServiceNow Support Portal Onboarding (Helix Suppliers & SIT Participants) | 85% | 02/10/24 | 17/01/25 | 78 days? | 02/10/24 | 17/01/25 | 0 days | 0 days | 78 days? | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.8.1 |  |  |  |  | ServiceNow Portal Preparation and Planning | 100% | 02/10/24 | 26/11/24 | 40 days? | 02/10/24 | 26/11/24 | 0 days | 0 days | 40 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.8.1.1 |  |  |  |  | Define Supplier Requirements | 100% | 02/10/24 | 12/11/24 | 30 days? | 02/10/24 | 12/11/24 | 0 days | 0 days | 30 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.8.1.2 |  |  |  |  | Determine Supplier ServiceNow modules | 100% | 13/11/24 | 26/11/24 | 10 days? | 13/11/24 | 26/11/24 | 0 days | 0 days | 10 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.8.1.3 |  |  |  |  | Review compliance requirements, including data privacy and access limitations. | 100% | 13/11/24 | 26/11/24 | 10 days? | 13/11/24 | 26/11/24 | 0 days | 0 days | 10 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.8.1.4 |  |  |  |  | Conduct a security assessment to ensure the supplier complies with organisational policies. | 100% | 13/11/24 | 26/11/24 | 10 days? | 13/11/24 | 26/11/24 | 0 days | 0 days | 10 days? | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.8.2 |  |  |  |  | ServiceNow Portal System Configuration | 76% | 27/11/24 | 07/01/25 | 30 days? | 27/11/24 | 07/01/25 | 0 days | 0 days | 30 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.8.2.1 |  |  |  |  | Create Supplier User Accounts | 86% | 27/11/24 | 10/01/25 | 33 days | 27/11/24 | 10/12/24 | 0 days | 23 days | 33 days | Helix |  | 6.13 | Yes |  | 13/01/25 - Delay in collating user info has delayed completion of this activity, but Helix now have this and aim to complete by 17/01/25, in time for execution.
9 | 1.4.1.4.5.4.8.2.2 |  |  |  |  | Assign appropriate access based on the supplier’s needs and security requirements (e.g., read-only access, submit requests, etc.). | 60% | 30/12/24 | 10/01/25 | 10 days? | 11/12/24 | 24/12/24 | 13 days | 13 days | 10 days? | Helix |  | 6.13 | Yes |  | 13/01/25 - Delay in collating user info has delayed completion of this activity, but Helix now have this and aim to complete by 17/01/25, in time for execution.
9 | 1.4.1.4.5.4.8.2.3 |  |  |  |  | Configure Access Controls | 60% | 30/12/24 | 10/01/25 | 10 days? | 25/12/24 | 07/01/25 | 3 days | 3 days | 10 days? | Helix |  | 6.13 | Yes |  | 13/01/25 - Delay in collating user info has delayed completion of this activity, but Helix now have this and aim to complete by 17/01/25, in time for execution.
8 | 1.4.1.4.5.4.8.3 |  |  |  |  | ServiceNow Portal Training and Documentation | 83% | 06/01/25 | 10/01/25 | 5 days? | 06/01/25 | 10/01/25 | 0 days | 0 days | 5 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.8.3.1 |  |  |  |  | Provide Training to the Supplier | 0% | 24/01/25 | 24/01/25 | 1 day | 06/01/25 | 10/01/25 | 14 days | 10 days | 1 day | Helix |  | 6.13 | Yes |  | 13/01/25 - 24/01/25 has now been set for supplier training, this was later than the origional expected date, hence why this is red, but this date will not impact execution so not a concern.
9 | 1.4.1.4.5.4.8.3.2 |  |  |  |  | Create Supplier Training Documentation | 100% | 06/01/25 | 10/01/25 | 5 days | 06/01/25 | 10/01/25 | 0 days | 0 days | 5 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.8.4 |  |  |  |  | ServiceNow Portal Testing and Validation | 0% | 08/01/25 | 17/01/25 | 8 days? | 08/01/25 | 17/01/25 | 0 days | 0 days | 8 days? | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.8.4.1 |  |  |  |  | Conduct User Acceptance Testing (UAT) | 0% | 24/01/25 | 24/01/25 | 1 day | 13/01/25 | 17/01/25 | 9 days | 5 days | 1 day | Helix |  | 6.13 | Yes
9 | 1.4.1.4.5.4.8.4.2 |  |  |  |  | Validate Access and Security Controls | 0% | 20/01/25 | 23/01/25 | 4 days | 13/01/25 | 17/01/25 | 5 days | 4 days | 4 days | Helix |  | 6.13 | Yes
8 | 1.4.1.4.5.4.8.5 |  |  |  |  | ServiceNow Support Portal Onboarding (Helix Suppliers& SIT Participants) Completed | 0% | 24/01/25 | 24/01/25 | 0 days | 17/01/25 | 17/01/25 | 6 days | 5 days | 0 days | Helix |  | 6.13 | Yes |  | 13/01/25 - Onboarding deadline updated to align with the newly set supplier training date, which is on 24/01/25.
7 | 1.4.1.4.5.4.9 | T3 | T3-TE-0137 | SITAG |  | Stage 1 - Helix SIT Operational Readiness Completed | 0% | 31/01/25 | 31/01/25 | 0 days | 31/01/25 | 31/01/25 | 0 days | -1 day | 0 days | Helix |  | 6.13 | Yes |  | 27/11/24 - New milestone added by Programme, awaiting formal SITAG approval.
7 | 1.4.1.4.5.4.10 |  |  | SITAG |  | Theme 3 (Batch 2) | 100% | 19/09/24 | 18/12/24 | 65 days | 19/09/24 | 11/12/24 | 0 days | 5 days | -51 days | N/A |  | 6 | Yes
8 | 1.4.1.4.5.4.10.1 |  |  | SITAG |  | Conclude BCDR Scope with SRO, Code Bodies and DIP Manager | 100% | 19/09/24 | 18/10/24 | 22 days | 19/09/24 | 18/10/24 | 0 days | 0 days | 22 days |  |  | 6 | Yes
8 | 1.4.1.4.5.4.10.2 |  |  | SITAG |  | Develop BDCR Test Scenarios & Test Cases (Batch 2) | 100% | 14/10/24 | 25/10/24 | 10 days | 14/10/24 | 25/10/24 | 0 days | 0 days | 10 days |  |  | 6 | Yes |  | 12/09/24 - Added new milestone for Batch 2
8 | 1.4.1.4.5.4.10.3 |  |  | SITAG |  | Develop DIP Test Scenarios and Test Cases (Batch 2) | 100% | 19/09/24 | 25/10/24 | 27 days | 19/09/24 | 25/10/24 | 0 days | 0 days | 27 days |  |  | 6 | Yes
8 | 1.4.1.4.5.4.10.4 |  |  | SITAG |  | SRO Review | 100% | 28/10/24 | 01/11/24 | 5 days | 28/10/24 | 01/11/24 | 0 days | 0 days | 5 days |  |  | 6 | Yes |  | 06/11/24 - SRO Review and Industry Workshop have both been moved to alleviate concurrent review with Batch 1.
8 | 1.4.1.4.5.4.10.5 |  |  | SITAG |  | Industry Consultation (Batch 2) | 100% | 11/11/24 | 22/11/24 | 10 days | 11/11/24 | 22/11/24 | 0 days | 0 days | 9 days | SI Test, PP |  | 6 | Yes |  | 12/09/24 - Forecast date changed in line with SI Plan.
8 | 1.4.1.4.5.4.10.6 |  |  | SITAG |  | Review Feedback and Update | 100% | 25/11/24 | 28/11/24 | 4 days | 25/11/24 | 29/11/24 | 0 days | -1 day | 4 days | SI Test |  | 6.13 | Yes
8 | 1.4.1.4.5.4.10.7 |  |  | SITAG |  | SITWG paper day | 100% | 28/11/24 | 28/11/24 | 0 days | 28/11/24 | 28/11/24 | 1 day | 0 days | 0 days |  |  | 6.13 | Yes
8 | 1.4.1.4.5.4.10.8 |  |  | SITAG |  | Review with SIT WG (Batch 2) | 100% | 29/11/24 | 05/12/24 | 5 days | 29/11/24 | 05/12/24 | 0 days | 0 days | 5 days | SI Test |  | 6.13 | Yes
8 | 1.4.1.4.5.4.10.9 |  |  | SITAG |  | SITWG endorse Theme 3 (Batch 2) | 100% | 05/12/24 | 05/12/24 | 0 days | 05/12/24 | 05/12/24 | 1 day | 0 days | 0 days |  |  | 6.13 | Yes |  | 09/12/24 - Endorsed with caveat that two test cases should be descoped, but this does not impact successor activity and still meant Batch was endorsed.
8 | 1.4.1.4.5.4.10.10 |  |  | SITAG |  | SITAG paper day | 100% | 11/12/24 | 11/12/24 | 0 days | 11/12/24 | 11/12/24 | 1 day | 0 days | 0 days |  |  | 6.13 | Yes
8 | 1.4.1.4.5.4.10.11 | T3 | T3-TE-0138 | SITAG |  | SITAG approve Theme 3 (Batch 2) | 100% | 18/12/24 | 18/12/24 | 1 day | 18/12/24 | 18/12/24 | 0 days | 0 days | 1 day | SI Test |  | 6.13 | Yes
7 | 1.4.1.4.5.4.11 |  |  | SITAG |  | Theme 3 (Batch 1) | 100% | 10/04/24 | 18/12/24 | 181 days? | 10/04/24 | 11/12/24 | 0 days | 5 days | 181 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.4.11.1 |  |  | SITAG |  | Develop Test Scenarios & Test Cases (Batch 1) | 100% | 10/04/24 | 26/07/24 | 78 days | 10/04/24 | 26/07/24 | 0 days | 0 days | 32 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.4.11.2 |  |  | SITAG |  | Conclude Industry Consultation (Batch 1) | 100% | 05/09/24 | 19/09/24 | 11 days | 05/09/24 | 19/09/24 | 0 days | 0 days | 11 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.4.11.3 |  |  | SITAG |  | Review Feedback and Update | 100% | 20/09/24 | 26/09/24 | 5 days | 20/09/24 | 26/09/24 | 0 days | 0 days | 5 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.4.11.4 |  |  | SITAG |  | Draft Test Cases from Feedback and LLSD | 100% | 30/09/24 | 18/10/24 | 15 days? | 30/09/24 | 18/10/24 | 0 days | 0 days | 15 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.4.11.5 |  |  | SITAG |  | SRO Review | 100% | 21/10/24 | 25/10/24 | 5 days? | 21/10/24 | 25/10/24 | 0 days | 0 days | 5 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.4.11.6 |  |  | SITAG |  | Industry Consultation | 100% | 28/10/24 | 08/11/24 | 10 days? | 28/10/24 | 08/11/24 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.4.11.7 |  |  | SITAG |  | Review Feedback and Update | 100% | 11/11/24 | 22/11/24 | 10 days | 11/11/24 | 15/11/24 | 0 days | 5 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.4.11.8 |  |  | SITAG |  | SITWG paper day | 100% | 28/11/24 | 28/11/24 | 0 days | 28/11/24 | 28/11/24 | 1 day | 0 days | 0 days |  |  | 6.13 | Yes
8 | 1.4.1.4.5.4.11.9 |  |  | SITAG |  | Review with SITWG (Batch 1) | 100% | 29/11/24 | 05/12/24 | 5 days | 29/11/24 | 05/12/24 | 0 days | 0 days | 5 days | SI Test |  | 6.13 | Yes
8 | 1.4.1.4.5.4.11.10 |  |  | SITAG |  | SITWG endorse Theme 3 (Batch 1) | 100% | 05/12/24 | 05/12/24 | 0 days | 05/12/24 | 05/12/24 | 1 day | 0 days | 0 days |  |  | 6.13 | Yes
8 | 1.4.1.4.5.4.11.11 |  |  | SITAG |  | SITAG paper day | 100% | 11/12/24 | 11/12/24 | 0 days | 11/12/24 | 11/12/24 | 1 day | 0 days | 0 days |  |  | 6.13 | Yes
8 | 1.4.1.4.5.4.11.12 | T3 | T3-TE-0139 | SITAG |  | SITAG approve Theme 3 (Batch 1) | 100% | 18/12/24 | 18/12/24 | 0 days | 18/12/24 | 18/12/24 | 1 day | 0 days | 0 days | SI Test |  | 6.13 | Yes
8 | 1.4.1.4.5.4.11.13 | T3 | T3-TE-0119 | SITAG |  | SIT Operational Scenarios & Test Cases Approved - Theme 3 (Batch 1 + 2) | 100% | 18/12/24 | 18/12/24 | 0 days | 18/12/24 | 18/12/24 | 1 day | 0 days | 0 days | SI Test |  | 6.13 | Yes
7 | 1.4.1.4.5.4.12 |  |  | SITAG |  | Helix SDD and LLSD Development and Approval | 100% | 27/09/24 | 30/09/24 | 1 day | 27/09/24 | 30/09/24 | 0 days | -1 day | 1 day | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.4.12.1 |  |  | SITAG |  | Development | 100% | 27/09/24 | 27/09/24 | 0 days | 27/09/24 | 27/09/24 | 0 days | -1 day | 0 days | SI Test |  | 6 | Yes
8 | 1.4.1.4.5.4.12.2 |  |  | SITAG |  | Approval | 100% | 30/09/24 | 30/09/24 | 0 days | 30/09/24 | 30/09/24 | 0 days | -1 day | 0 days | SI Test |  | 6 | Yes
6 | 1.4.1.4.5.5 |  |  | SITAG |  | SIT Operational Programme RTTM | 71% | 09/12/24 | 24/01/25 | 35 days | 12/12/24 | 17/01/25 | -3 days | 5 days | 35 days | SI Test |  | 6.12 | Yes
7 | 1.4.1.4.5.5.1 |  |  | SITAG |  | Develop Manual SIT Operational RTTM | 100% | 09/12/24 | 10/01/25 | 25 days | 12/12/24 | 10/01/25 | -3 days | 0 days | 25 days | SI Test |  | 6.16 | Yes |  | 13/01/25 - Programme manual Operational RTTM is with SRO for review, this means completion is behind schedule, but this won't delay start of Operational testing.
7 | 1.4.1.4.5.5.2 |  |  | SITAG |  | SRO review of Manual SIT Operational RTTM | 0% | 13/01/25 | 17/01/25 | 5 days | 13/01/25 | 17/01/25 | 0 days | 0 days | 5 days |  |  | 6.16 | Yes |  | 15/01/25 - Operational RTTM plan updated to reflect activity that will be required to complete Operational RTTM.
7 | 1.4.1.4.5.5.3 |  |  | SITAG |  | DIP Manager / Code Bodies / Full SRO to review | 0% | 20/01/25 | 24/01/25 | 5 days | 20/01/25 | 24/01/25 | 0 days | 0 days | 5 days |  |  | 6.16 | Yes |  | 15/01/25 - Operational RTTM plan updated to reflect activity that will be required to complete Operational RTTM.
7 | 1.4.1.4.5.5.4 |  |  | SITAG |  | DIP Manager / Code Bodies / Full SRO acceptance of Operational RTTM | 0% | 24/01/25 | 24/01/25 | 0 days | 24/01/25 | 24/01/25 | 1 day | 0 days | 0 days |  |  | 6.16 | Yes |  | 15/01/25 - Operational RTTM plan updated to reflect activity that will be required to complete Operational RTTM.
7 | 1.4.1.4.5.5.5 |  |  | SITAG |  | Manual SIT Operational RTTM Complete | 0% | 24/01/25 | 24/01/25 | 0 days | 10/01/25 | 10/01/25 | 11 days | 10 days | 0 days | SI Test |  | 6.12 | Yes |  | 13/01/25 - Programme manual Operational RTTM is with SRO for review, this means completion is behind schedule, but this won't delay start of Operational testing.
6 | 1.4.1.4.5.6 |  |  | SITAG |  | Theme 3 Work-off plan | 4% | 06/01/25 | 05/05/25 | 86 days? | 17/02/25 | 01/05/25 | -30 days | 2 days | 86 days? | SI Test |  | 6.13 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
7 | 1.4.1.4.5.6.1 |  |  | SITAG |  | Test Scripts updates | 0% | 27/01/25 | 08/04/25 | 52 days | 08/04/25 | 08/04/25 | -51 days | 0 days | 52 days | SI Test |  | 6.13 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
7 | 1.4.1.4.5.6.2 |  |  | SITAG |  | RTTM Updated Additional RTTM WBS items | 0% | 09/04/25 | 22/04/25 | 10 days | 07/04/25 | 18/04/25 | 2 days | 2 days | 10 days | SI Test |  | 6.13 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
7 | 1.4.1.4.5.6.3 |  |  | SITAG |  | Removal of de-scoped TCs from the RTTMs | 0% | 16/04/25 | 22/04/25 | 5 days | 14/04/25 | 18/04/25 | 2 days | 2 days | 5 days | SI Test |  | 6.13 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
7 | 1.4.1.4.5.6.4 |  |  | SITAG |  | Update and stabilisation of all TC ADO IDs | 0% | 16/04/25 | 05/05/25 | 14 days | 14/04/25 | 01/05/25 | 2 days | 2 days | 14 days | SI Test |  | 6.13 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
7 | 1.4.1.4.5.6.5 |  |  | SITAG |  | Addition and integration of Role tags to reqs in the Role RTTMs | 0% | 16/04/25 | 22/04/25 | 5 days | 14/04/25 | 18/04/25 | 2 days | 2 days | 5 days | SI Test |  | 6.13 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
7 | 1.4.1.4.5.6.6 |  |  | SITAG |  | Update of the RTTM All sheet (porting of the individual RTTMs) | 0% | 21/04/25 | 29/04/25 | 7 days | 17/04/25 | 25/04/25 | 2 days | 2 days | 7 days | SI Test |  | 6.13 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
7 | 1.4.1.4.5.6.7 |  |  | SITAG |  | Define Additional ADO Tags | 0% | 18/04/25 | 18/04/25 | 1 day | 16/04/25 | 16/04/25 | 2 days | 2 days | 1 day | SI Test |  | 6.13 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
7 | 1.4.1.4.5.6.8 |  |  | SITAG |  | Upload Operational RTTM to ADO | 0% | 29/04/25 | 29/04/25 | 0 days | 25/04/25 | 25/04/25 | 3 days | 2 days | 0 days | SI Test |  | 6.13 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
7 | 1.4.1.4.5.6.9 |  |  | SITAG |  | Further Interative Deepdive on the requirements to testcase mapping | 0% | 16/04/25 | 28/04/25 | 9 days | 14/04/25 | 24/04/25 | 2 days | 2 days | 9 days | SI Test |  | 6.13 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
7 | 1.4.1.4.5.6.10 |  |  | SITAG |  | Internal review | 0% | 16/04/25 | 22/04/25 | 5 days | 14/04/25 | 18/04/25 | 2 days | 2 days | 5 days | SI Test |  | 6.13 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
7 | 1.4.1.4.5.6.11 |  |  | SITAG |  | Issue Static RTTM to Code Bodies | 0% | 24/04/25 | 24/04/25 | 1 day? | 22/04/25 | 22/04/25 | 2 days | 2 days | 1 day? | SI Test |  | 6.13 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
7 | 1.4.1.4.5.6.12 |  |  | SITAG |  | Code Body Acceptance of RTTM | 0% | 25/04/25 | 01/05/25 | 5 days | 23/04/25 | 29/04/25 | 2 days | 2 days | 5 days | Code Bodies |  | 6.13 | Yes |  | 15/01/25 - These activities will be removed as not relevant to the NF RTTM.
7 | 1.4.1.4.5.6.13 |  |  | SITAG |  | SIT Operational DITL | 33% | 06/01/25 | 28/01/25 | 17 days | 08/10/24 | 17/10/24 | 64 days | 73 days | 17 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.6.13.1 |  |  | SITAG |  | DITL + Familiarisation session development | 63% | 06/01/25 | 15/01/25 | 8 days | 06/01/25 | 17/01/25 | 0 days | -2 days | 8 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.6.13.2 |  |  | SITAG |  | SRO Review | 0% | 16/01/25 | 22/01/25 | 5 days | 20/01/25 | 24/01/25 | -2 days | -2 days | 5 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.5.6.13.3 |  |  |  |  | Post-SRO Review Changes | 0% | 23/01/25 | 24/01/25 | 2 days | 23/01/25 | 24/01/25 | 0 days | 0 days | 2 days |  |  | 6.16 | Yes
8 | 1.4.1.4.5.6.13.4 |  |  |  |  | Familiarisation session Service Management test case schedule + mapping | 0% | 24/01/25 | 24/01/25 | 0 days | 24/01/25 | 24/01/25 | 1 day | 0 days | 0 days |  |  | 6.16 | Yes
8 | 1.4.1.4.5.6.13.5 |  |  | SITAG |  | Publish Cycle 3 DITL / Cycle 3 DITL Online Sessions for SIT PPs | 0% | 28/01/25 | 28/01/25 | 0 days | 29/01/25 | 29/01/25 | 0 days | -1 day | 0 days | SI Test |  | 6.15 | Yes |  | 13/01/25 - Date to come forward to avoid clash with SITAG.
6 | 1.4.1.4.5.7 |  |  | SITAG |  | Environments (SIT B) | 100% | 07/10/24 | 07/10/24 | 0 days | 07/10/24 | 07/10/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
7 | 1.4.1.4.5.7.1 |  |  | SITAG |  | PP Environments (SIT B) | 100% | 07/10/24 | 07/10/24 | 0 days | 07/10/24 | 07/10/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.5.7.1.1 |  |  | SITAG |  | Deployment of MHHS solution code to SIT B environments | 100% | 07/10/24 | 07/10/24 | 0 days | 07/10/24 | 07/10/24 | 0 days | -1 day | 0 days | PP |  | 5.21 | Yes
7 | 1.4.1.4.5.7.2 |  |  | SITAG |  | SI Environments (SIT B) | 100% | 07/10/24 | 07/10/24 | 0 days | 07/10/24 | 07/10/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
8 | 1.4.1.4.5.7.2.1 |  |  | SITAG |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT B environments | 100% | 07/10/24 | 07/10/24 | 0 days | 07/10/24 | 07/10/24 | 0 days | -1 day | 0 days | SI Test |  | 5.21 | Yes
5 | 1.4.1.4.6 |  |  | SITAG |  | SIT Operational Overarching Test Readiness Reports | 22% | 05/08/24 | 18/09/24 | 33 days? | 05/08/24 | 18/09/24 | 0 days | 0 days | -118 days? | N/A |  | 6 | Yes
6 | 1.4.1.4.6.1 |  |  | SITAG |  | SI SIT Operational Theme 3 (Batch 1) Overarching Test Readiness Report | 0% | 18/12/24 | 29/01/25 | 31 days | 23/12/24 | 29/01/25 | -3 days | 0 days | 31 days |  |  | 6.15 | Yes
7 | 1.4.1.4.6.1.1 |  |  | SITAG |  | Develop Overarching SIT Operational Theme 3 (Batch 1) Overarching Test Readiness Report | 0% | 18/12/24 | 14/01/25 | 20 days | 23/12/24 | 15/01/25 | -3 days | -1 day | 20 days |  |  | 6.15 | Yes |  | 15/01/25 - There is still outstanding PIT documentation that need to be submitted by participants, delyaing this activity.
7 | 1.4.1.4.6.1.2 |  |  | SITAG |  | SRO review | 0% | 08/01/25 | 14/01/25 | 5 days | 16/01/25 | 22/01/25 | -6 days | -6 days | 5 days |  |  | 6.15 | Yes |  | 15/01/25 - Programme will be presenting the governance route overarching reports will go through at January SITAG, if endorsed, overarching report will be rebaselined and RAGs will return to green.
7 | 1.4.1.4.6.1.3 |  |  | SITAG |  | SITWG Paper day | 0% | 14/01/25 | 14/01/25 | 0 days | N/A | N/A | 0 days | 0 days | 0 days |  |  | 6.16 | Yes |  | 07/01/25 - Added SITWG activity to the plan. Programme will be presenting the governance route overarching reports will go through at January SITAG, if endorsed, overarching report will be rebaselined and RAGs will return to green.
7 | 1.4.1.4.6.1.4 |  |  | SITAG |  | SITWG review the Operational Theme 3 (Batch 1) Overarching Test Readiness Report | 0% | 21/01/25 | 21/01/25 | 0 days | N/A | N/A | 0 days | 0 days | 0 days |  |  | 6.16 | Yes |  | 07/01/25 - Added SITWG activity to the plan. Programme will be presenting the governance route overarching reports will go through at January SITAG, if endorsed, overarching report will be rebaselined and RAGs will return to green.
7 | 1.4.1.4.6.1.5 |  |  | SITAG |  | Update Operational Theme 3 (Batch 1) Overarching Test Readiness Report following SRO / SITWG feedback | 0% | 22/01/25 | 22/01/25 | 1 day | 16/01/25 | 22/01/25 | 4 days | 0 days | 1 day |  |  | 6.15 | Yes
7 | 1.4.1.4.6.1.6 |  |  | SITAG |  | SITAG paper day | 0% | 22/01/25 | 22/01/25 | 0 days | 22/01/25 | 22/01/25 | 1 day | 0 days | 0 days |  |  | 6.15 | Yes
7 | 1.4.1.4.6.1.7 |  | T3-TE-XXXX | SITAG |  | SITAG approve Theme 3 (Batch 1) Test Readiness Report | 0% | 29/01/25 | 29/01/25 | 0 days | 29/01/25 | 29/01/25 | 1 day | 0 days | 0 days |  |  | 6.15 | Yes |  | 15/01/25 - Programme will ask Jan SITAG to approve creation of milestone ID for this activity.
6 | 1.4.1.4.6.2 |  |  | SITAG |  | SI SIT Operational Theme 1, 2 and 3 (Batch 2) Overarching Test Readiness Report | 0% | 27/01/25 | 28/03/25 | 45 days | 27/01/25 | 28/03/25 | 0 days | 0 days | 45 days |  |  | 6.15 | Yes
7 | 1.4.1.4.6.2.1 |  |  | SITAG |  | Develop Overarching SIT Operational Theme 1, 2 and 3 (Batch 2) Overarching Test Readiness Report | 0% | 27/01/25 | 21/02/25 | 20 days | 27/01/25 | 21/02/25 | 0 days | 0 days | 20 days |  |  | 6.15 | Yes
7 | 1.4.1.4.6.2.2 |  |  | SITAG |  | SRO review | 0% | 24/02/25 | 28/02/25 | 5 days | 24/02/25 | 28/02/25 | 0 days | 0 days | 5 days |  |  | 6.15 | Yes
7 | 1.4.1.4.6.2.3 |  |  | SITAG |  | SITWG Paper day | 0% | 27/02/25 | 27/02/25 | 0 days | N/A | N/A | 0 days | 0 days | 0 days |  |  | 6.16 | Yes |  | 07/01/25 - Added SITWG activity to the plan. Programme will be presenting the governance route overarching reports will go through at January SITAG, if endorsed, overarching report will be rebaselined and RAGs will return to green.
7 | 1.4.1.4.6.2.4 |  |  | SITAG |  | SITWG review the Operational Theme 1, 2 and 3 (Batch 2) Overarching Test Readiness Report | 0% | 06/03/25 | 06/03/25 | 0 days | N/A | N/A | 0 days | 0 days | 0 days |  |  | 6.16 | Yes |  | 07/01/25 - Added SITWG activity to the plan. Programme will be presenting the governance route overarching reports will go through at January SITAG, if endorsed, overarching report will be rebaselined and RAGs will return to green.
7 | 1.4.1.4.6.2.5 |  |  | SITAG |  | Update Operational Theme 1, 2 and 3 (Batch 2) Overarching Test Readiness Report following SRO feedback | 0% | 07/03/25 | 25/03/25 | 13 days | 03/03/25 | 12/03/25 | 4 days | 9 days | 13 days |  |  | 6.15 | Yes |  | 15/01/25 - Programme will be presenting the governance route overarching reports will go through at January SITAG, if endorsed, overarching report will be rebaselined and RAGs will return to green.
7 | 1.4.1.4.6.2.6 |  |  | SITAG |  | eSITAG paper day | 0% | 26/03/25 | 26/03/25 | 0 days | 12/03/25 | 12/03/25 | 11 days | 10 days | 0 days |  |  | 6.15 | Yes |  | 15/01/25 - Programme will be presenting the governance route overarching reports will go through at January SITAG, if endorsed, overarching report will be rebaselined and RAGs will return to green.
7 | 1.4.1.4.6.2.7 |  | T3-TE-XXXX | SITAG |  | eSITAG approve Operational Theme 1, 2 and 3 (Batch 2) Overarching Test Readiness Report | 0% | 28/03/25 | 28/03/25 | 0 days | 28/03/25 | 28/03/25 | 1 day | 0 days | 0 days |  |  | 6.15 | Yes |  | 15/01/25 - Programme will ask Jan SITAG to approve creation of milestone ID for this activity.
6 | 1.4.1.4.6.3 |  |  | SITAG |  | SIT Operational Execution Model | 63% | 05/08/24 | 02/10/24 | 43 days | 05/08/24 | 02/10/24 | 0 days | 0 days | 43 days | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.6.3.1 |  |  | SITAG |  | Theme 3 (Batch 1) | 99% | 05/08/24 | 10/09/24 | 27 days | 05/08/24 | 10/09/24 | 0 days | 0 days | 27 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.6.3.1.1 |  |  | SITAG |  | Develop execution model Theme 3 (Batch 1) | 100% | 16/12/24 | 18/12/24 | 3 days | 16/12/24 | 18/12/24 | 0 days | 0 days | 3 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.6.3.1.2 |  |  | SITAG |  | SRO provide feedback | 100% | 19/12/24 | 07/01/25 | 14 days | 19/12/24 | 07/01/25 | 0 days | 0 days | 14 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.6.3.1.3 |  |  | SITAG |  | Address SRO feedback on execution model | 100% | 08/01/25 | 09/01/25 | 2 days | 08/01/25 | 09/01/25 | 0 days | 0 days | 2 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.6.3.1.4 |  |  | SITAG |  | Finalise execution model | 100% | 10/01/25 | 14/01/25 | 3 days | 10/01/25 | 14/01/25 | 0 days | 0 days | 3 days | SI Test |  | 6.15 | Yes |  | 08/01/15 - Volunteers were confirmed on 07/01, therefore execution model finalised.
8 | 1.4.1.4.6.3.1.5 |  |  | SITAG |  | SITWG paper day | 0% | 14/01/25 | 14/01/25 | 0 days | 14/01/25 | 14/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.6.3.1.6 |  |  | SITAG |  | SITWG update on execution model | 0% | 21/01/25 | 21/01/25 | 0 days | 21/01/25 | 21/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.6.3.2 |  |  | SITAG |  | Theme 1, 2 and 3 (Batch 2) | 0% | 05/08/24 | 04/09/24 | 23 days | 05/08/24 | 04/09/24 | 0 days | 0 days | 23 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.6.3.2.1 |  |  | SITAG |  | Develop execution model Theme 1, 2 and 3 (Batch 2) | 0% | 13/01/25 | 15/01/25 | 3 days | 13/01/25 | 15/01/25 | 0 days | 0 days | 3 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.6.3.2.2 |  |  | SITAG |  | SRO provide feedback | 0% | 16/01/25 | 22/01/25 | 5 days | 16/01/25 | 22/01/25 | 0 days | 0 days | 5 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.6.3.2.3 |  |  | SITAG |  | Address SRO feedback on execution model | 0% | 23/01/25 | 24/01/25 | 2 days | 23/01/25 | 24/01/25 | 0 days | 0 days | 2 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.6.3.2.4 |  |  | SITAG |  | Finalise execution model | 0% | 27/01/25 | 29/01/25 | 3 days | 27/01/25 | 29/01/25 | 0 days | 0 days | 3 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.6.3.2.5 |  |  | SITAG |  | SITWG paper day | 0% | 05/02/25 | 05/02/25 | 0 days | 05/02/25 | 05/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
8 | 1.4.1.4.6.3.2.6 |  |  | SITAG |  | SITWG update on execution model | 0% | 12/02/25 | 12/02/25 | 0 days | 12/02/25 | 12/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
6 | 1.4.1.4.6.4 |  |  | SITAG |  | SIT Operational Theme 3 (Batch 1) progress reporting | 17% | 19/12/24 | 28/01/25 | 29 days? | 19/12/24 | 31/01/25 | 0 days | -3 days | 29 days? | SI Test |  | 6.14 | Yes
7 | 1.4.1.4.6.4.1 |  |  | SITAG |  | Determine reporting methodology | 100% | 19/12/24 | 20/12/24 | 2 days? | 19/12/24 | 17/01/25 | 0 days | -20 days | 2 days? | SI Test |  | 6.14 | Yes
7 | 1.4.1.4.6.4.2 |  |  | SITAG |  | Implement reporting | 0% | 23/12/24 | 03/01/25 | 10 days | 20/01/25 | 31/01/25 | -20 days | -20 days | 10 days | SI Test |  | 6.14 | Yes |  | 06/01/25 - Awaiting confirmation of ADO format
6 | 1.4.1.4.6.5 |  | T2-TE-0750 | SITAG |  | SIT Operational Theme 3 (Batch 1) Testing Preparation Complete | 0% | 30/01/25 | 30/01/25 | 0 days | 17/01/25 | 17/01/25 | 10 days | 9 days | 0 days | SI Test |  | 6.15 | Yes
6 | 1.4.1.4.6.6 | T2 | T2-TE-1300 | SITAG |  | SIT Operational Theme 1, 2, 3 (Batch 2) Testing Preparation Complete | 0% | 28/03/25 | 28/03/25 | 0 days | 31/03/25 | 25/04/25 | 0 days | -20 days | 0 days | SI Test |  | 6.15 | Yes
5 | 1.4.1.4.7 |  |  | SITAG |  | Regression Test Preparation | 10% | 18/11/24 | 19/11/24 | 2 days? | 16/09/24 | 16/05/25 | 45 days | -128 days | 2 days? | SI Test | Proposed | 6.15 | Yes
6 | 1.4.1.4.7.1 |  |  | SITAG |  | Regression Test Approach | 22% | 18/11/24 | 29/11/24 | 10 days | 16/09/24 | 20/11/24 | 45 days | 7 days | 10 days | SI Test | Proposed | 6.16 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.1.1 |  |  | SITAG |  | Develop approach doc | 35% | 18/11/24 | 15/01/25 | 43 days | 18/11/24 | 13/12/24 | 0 days | 23 days | 43 days | SI Test | Proposed | 6.16 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.1.2 |  |  | SITAG |  | SRO / LDP review of approach doc | 0% | 16/01/25 | 22/01/25 | 5 days | 16/12/24 | 18/12/24 | 23 days | 25 days | 5 days | SI Test | Proposed | 6.16 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.1.3 |  |  | SITAG |  | Incorporate SRO feedback into approach doc | 0% | 16/01/25 | 22/01/25 | 5 days | 19/12/24 | 20/12/24 | 20 days | 23 days | 5 days | SI Test | Proposed | 6.16 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.1.4 |  |  | SITAG |  | Industry review of approach | 0% | 23/01/25 | 05/02/25 | 10 days | 20/01/25 | 31/01/25 | 3 days | 3 days | 10 days | SI Test | Proposed | 6.16 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.1.5 |  |  | SITAG |  | Updates to approach doc on back of industry feedback | 0% | 06/02/25 | 11/02/25 | 4 days | 03/02/25 | 11/02/25 | 3 days | 0 days | 4 days | SI Test | Proposed | 6.16 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.1.6 |  |  | SITAG |  | eSITWG paper day | 0% | 11/02/25 | 11/02/25 | 0 days | 20/12/24 | 20/12/24 | 38 days | 37 days | 0 days | SI Test | Proposed | 6.16 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.1.7 |  |  | SITAG |  | eSITWG Recommendation | 0% | 18/02/25 | 18/02/25 | 0 days | 08/01/25 | 08/01/25 | 30 days | 29 days | 0 days | SI Test | Proposed | 6.16 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.1.8 |  |  | SITAG |  | Incorporate eSITWG feedback into approach doc | 0% | 19/02/25 | 20/02/25 | 2 days | 09/01/25 | 09/01/25 | 29 days | 30 days | 2 days | SI Test | Proposed | 6.16 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.1.9 |  |  | SITAG |  | eSITAG paper day | 0% | 20/02/25 | 20/02/25 | 0 days | 09/01/25 | 09/01/25 | 31 days | 30 days | 0 days | SI Test | Proposed | 6.16 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.1.10 |  |  | SITAG |  | eSITAG (inc SRO) Approval | 0% | 28/02/25 | 28/02/25 | 0 days | 16/01/25 | 16/01/25 | 32 days | 31 days | 0 days | SI Test | Proposed | 6.16 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.1.11 | T3 | T3-TE-0123 | SITAG |  | SIT Regression Testing Approach and Plan Approval | 0% | 28/02/25 | 28/02/25 | 0 days | 16/01/25 | 16/01/25 | 32 days | 31 days | 0 days | SI Test | Proposed | 6.16 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
6 | 1.4.1.4.7.2 |  |  | SITAG |  | Regression Test Suite | 0% | 12/02/25 | 16/04/25 | 46 days | 17/01/25 | 18/03/25 | 18 days | 21 days | 46 days | SI Test | Proposed | 6.15 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.2.1 |  |  | SITAG |  | Build Regression Test Suite | 0% | 12/02/25 | 28/02/25 | 13 days | 17/01/25 | 06/02/25 | 18 days | 16 days | 13 days | SI Test | Proposed | 6.15 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.2.2 |  |  |  |  | SITWG paper day | 0% | 27/02/25 | 27/02/25 | 1 day | N/A | N/A | 0 days | 0 days | 1 day |  | Proposed | 6.16 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.2.3 |  |  |  |  | SITWG provides feedback on regression suite approach | 0% | 06/03/25 | 06/03/25 | 0 days | N/A | N/A | 0 days | 0 days | 0 days |  | Proposed | 6.16 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.2.4 |  |  | SITAG |  | LDP walkthrough of Regression Test Suite | 0% | 28/02/25 | 28/02/25 | 1 day | 17/03/25 | 18/03/25 | -11 days | -12 days | 1 day | SI Test | Proposed | 6.15 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.2.5 |  |  | SITAG |  | SRO Review of regression suite doc | 0% | 03/03/25 | 07/03/25 | 5 days | 07/02/25 | 20/02/25 | 16 days | 11 days | 5 days | SI Test | Proposed | 6.15 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.2.6 |  |  | SITAG |  | Incorporate SRO feedback into regression suite doc | 0% | 03/03/25 | 07/03/25 | 5 days | 21/02/25 | 27/02/25 | 6 days | 6 days | 5 days | SI Test | Proposed | 6.15 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.2.7 |  |  | SITAG |  | Industry review of Regression Test Suite | 0% | 10/03/25 | 21/03/25 | 10 days | 31/03/25 | 11/04/25 | -15 days | -15 days | 10 days | SI Test | Proposed | 6.15 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.2.8 |  |  | SITAG |  | Incorporate Industry feedback into regression suite doc | 0% | 24/03/25 | 27/03/25 | 4 days | 14/04/25 | 16/04/25 | -15 days | -14 days | 4 days | SI Test | Proposed | 6.15 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.2.9 |  |  | SITAG |  | SITWG paper day | 0% | 27/03/25 | 27/03/25 | 0 days | 27/02/25 | 27/02/25 | 21 days | 20 days | 0 days | SI Test | Proposed | 6.15 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.2.10 |  |  | SITAG |  | SITWG endorses regression suite doc | 0% | 03/04/25 | 03/04/25 | 0 days | 06/03/25 | 06/03/25 | 21 days | 20 days | 0 days | SI Test | Proposed | 6.15 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.2.11 |  |  | SITAG |  | Incorporate SITWG feedback into regression suite doc | 0% | 04/04/25 | 04/04/25 | 1 day | 07/03/25 | 11/03/25 | 20 days | 18 days | 1 day | SI Test | Proposed | 6.15 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.2.12 |  |  | SITAG |  | eSITAG paper day | 0% | 09/04/25 | 09/04/25 | 0 days | 11/03/25 | 11/03/25 | 22 days | 21 days | 0 days | SI Test | Proposed | 6.15 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.2.13 |  |  | SITAG |  | eSITAG (inc SRO) Approval of regression suite doc | 0% | 16/04/25 | 16/04/25 | 0 days | 18/03/25 | 18/03/25 | 22 days | 21 days | 0 days | SI Test | Proposed | 6.15 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
7 | 1.4.1.4.7.2.14 | T3 | T3-TE-0122 | SITAG |  | SIT Regression Approval | 0% | 16/04/25 | 16/04/25 | 0 days | 18/03/25 | 18/03/25 | 22 days | 21 days | 0 days | SI Test | Proposed | 6.15 | Yes |  | 15/01/25 - Programme walked through the proposed updates to Regression plan at Dec SITAG. Due to return to Jan SITAG to formally approve and rebaseline this date.
6 | 1.4.1.4.7.3 |  |  |  |  | Regression Test Data Load Window (SIT Functional and Migration) - SIT A | 0% | 28/04/25 | 29/04/25 | 1 day? | 14/03/25 | 17/03/25 | 32 days | 31 days | 1 day? | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.7.3.1 |  |  |  |  | Data Load preparation activities | 0% | 31/03/25 | 25/04/25 | 20 days | 31/03/25 | 25/04/25 | 0 days | 0 days | 20 days | SI Test |  | 6.15 | Yes |  | 14/01/25 - Dependency added to non-functional theme 1 data load. Duration reduced so the activity still completes on 25/04/25.
7 | 1.4.1.4.7.3.2 | T2 | T2-TE-1000 | SITAG |  | Regression Test Data Load Start | 0% | 28/04/25 | 28/04/25 | 0 days? | 28/04/25 | 28/04/25 | 1 day | 0 days | 0 days? | SI Test |  | 6.15 | Yes
7 | 1.4.1.4.7.3.3 |  |  |  |  | Regression Test Data Load Window | 0% | 29/04/25 | 16/05/25 | 14 days | 28/04/25 | 16/05/25 | 1 day | 0 days | 14 days | SI Test |  | 6.15 | Yes
5 | 1.4.1.4.8 |  |  |  |  | Single Instance ADO | 98% | 21/08/24 | 03/10/24 | 32 days? | 21/08/24 | 03/10/24 | 0 days | 0 days | 32 days? | SI Test |  | 6.1 | Yes
6 | 1.4.1.4.8.1 |  |  |  |  | Single ADO Project for all Cohorts - Implementation and Test Phase | 100% | 21/08/24 | 01/10/24 | 30 days? | 21/08/24 | 01/10/24 | 0 days | 0 days | 30 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.1.1 |  |  |  |  | Create test plans and suites in master project | 100% | 21/08/24 | 22/08/24 | 2 days? | 21/08/24 | 22/08/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.1.2 |  |  |  |  | Create area paths / iterations | 100% | 21/08/24 | 22/08/24 | 2 days? | 21/08/24 | 22/08/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.1.3 |  |  |  |  | Create IAM roles | 100% | 21/08/24 | 22/08/24 | 2 days? | 21/08/24 | 22/08/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.1.4 |  |  |  |  | Add users to roles | 100% | 23/08/24 | 23/08/24 | 1 day? | 23/08/24 | 23/08/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.1.5 |  |  |  |  | Testing permissions | 100% | 27/08/24 | 28/08/24 | 2 days? | 27/08/24 | 28/08/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.1 | Yes
8 | 1.4.1.4.8.1.5.1 |  |  |  |  | Adding tests | 100% | 27/08/24 | 28/08/24 | 2 days? | 27/08/24 | 28/08/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.1 | Yes
8 | 1.4.1.4.8.1.5.2 |  |  |  |  | Deleting tests | 100% | 27/08/24 | 28/08/24 | 2 days? | 27/08/24 | 28/08/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.1 | Yes
8 | 1.4.1.4.8.1.5.3 |  |  |  |  | Adding tests to incorrect Cohort | 100% | 27/08/24 | 28/08/24 | 2 days? | 27/08/24 | 28/08/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.1 | Yes
8 | 1.4.1.4.8.1.5.4 |  |  |  |  | Add / delete defects | 100% | 27/08/24 | 28/08/24 | 2 days? | 27/08/24 | 28/08/24 | 0 days | 0 days | 2 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.1.6 |  |  |  |  | Migrate defects from cohort project to master - Option 2 | 100% | 23/09/24 | 25/09/24 | 3 days | 23/09/24 | 25/09/24 | 0 days | 0 days | 3 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.1.7 |  |  |  |  | Testing Permissions - Evidence attachment security | 100% | 18/09/24 | 01/10/24 | 10 days? | 18/09/24 | 01/10/24 | 0 days | 0 days | 10 days? | SI Test |  | 6.1 | Yes
6 | 1.4.1.4.8.2 |  |  |  |  | ADO Dashboard Updates | 100% | 03/09/24 | 30/09/24 | 20 days? | 03/09/24 | 30/09/24 | 0 days | 0 days | 20 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.2.1 |  |  |  |  | Update reporting dashboards in ADO | 100% | 03/09/24 | 05/09/24 | 3 days | 03/09/24 | 05/09/24 | 0 days | 0 days | 3 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.2.2 |  |  |  |  | Review dashboards with SI LDP leads | 100% | 06/09/24 | 27/09/24 | 16 days | 06/09/24 | 27/09/24 | 0 days | 0 days | 16 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.2.3 |  |  |  |  | Review dashboards with SRO | 100% | 09/09/24 | 30/09/24 | 16 days | 09/09/24 | 30/09/24 | 0 days | 0 days | 16 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.2.4 |  |  |  |  | Update dashboards following review | 100% | 12/09/24 | 13/09/24 | 2 days | 12/09/24 | 13/09/24 | 0 days | 0 days | 2 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.2.5 |  |  |  |  | Document changes to dashboard creation process | 100% | 16/09/24 | 19/09/24 | 4 days | 16/09/24 | 19/09/24 | 0 days | 0 days | 4 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.2.6 |  |  |  |  | Update SIT Dashboards for Sprints 4.1 & 4.2 across all Cohorts | 100% | 03/09/24 | 03/09/24 | 1 day? | 03/09/24 | 03/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
6 | 1.4.1.4.8.3 |  |  |  |  | Reporting Changes - PowerBI & QIP | 70% | 23/08/24 | 24/09/24 | 23 days? | 23/08/24 | 24/09/24 | 0 days | 0 days | 23 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.3.1 |  |  |  |  | Design, Create and ETL ADO Entities into PowerBI Data Model | 100% | 23/08/24 | 23/08/24 | 1 day? | 23/08/24 | 23/08/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.3.2 |  |  |  |  | Determine Relationships between ADO Entities & Attributes | 100% | 27/08/24 | 27/08/24 | 1 day? | 27/08/24 | 27/08/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.3.3 |  |  |  |  | Create Relevant Dax Measures | 100% | 28/08/24 | 28/08/24 | 1 day? | 28/08/24 | 28/08/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.3.4 |  |  |  |  | Design & Build Visualisations (Graphs) | 100% | 29/08/24 | 29/08/24 | 1 day? | 29/08/24 | 29/08/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.3.5 |  |  |  |  | Implement Filters | 100% | 23/09/24 | 23/09/24 | 1 day? | 23/09/24 | 23/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.3.6 |  |  |  |  | Check Data Quality & Integrity | 100% | 24/09/24 | 24/09/24 | 1 day? | 24/09/24 | 24/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.3.7 |  |  |  |  | Performance Optimisation | 100% | 24/09/24 | 24/09/24 | 1 day? | 24/09/24 | 24/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.3.8 |  |  |  |  | Publish (QIP) | 0% | 04/09/24 | 04/09/24 | 1 day? | 04/09/24 | 04/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes |  | 13/11/24 - This is on hold, assessed whether this is needed and if deemed so, will be resumed.
7 | 1.4.1.4.8.3.9 |  |  |  |  | Review & UAT | 0% | 05/09/24 | 05/09/24 | 1 day? | 05/09/24 | 05/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes |  | 13/11/24 - This is on hold, assessed whether this is needed and if deemed so, will be resumed.
7 | 1.4.1.4.8.3.10 |  |  |  |  | QIP Training Material & User Guides | 0% | 10/09/24 | 10/09/24 | 1 day? | 10/09/24 | 10/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes |  | 13/11/24 - This is on hold, assessed whether this is needed and if deemed so, will be resumed.
6 | 1.4.1.4.8.4 |  |  |  |  | Reporting Changes - Daily Excel Extract & PDF | 100% | 05/09/24 | 06/09/24 | 2 days | 05/09/24 | 06/09/24 | 0 days | 0 days | 2 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.4.1 |  |  |  |  | Excel Daily Report changes (Refer to above) | 100% | 05/09/24 | 06/09/24 | 2 days | 05/09/24 | 06/09/24 | 0 days | 0 days | 2 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.4.2 |  |  |  |  | PDF Daily Report changes (Refer to Above) | 100% | 05/09/24 | 06/09/24 | 2 days | 05/09/24 | 06/09/24 | 0 days | 0 days | 2 days | SI Test |  | 6.1 | Yes
6 | 1.4.1.4.8.5 |  |  |  |  | Documentation Updates | 100% | 02/09/24 | 02/10/24 | 23 days? | 02/09/24 | 02/10/24 | 0 days | 0 days | 23 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.5.1 |  |  |  |  | Changes to onboarding process (security) | 100% | 02/09/24 | 13/09/24 | 10 days | 02/09/24 | 13/09/24 | 0 days | 0 days | 10 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.5.2 |  |  |  |  | Update the documents on loading tests into ADO? | 100% | 02/09/24 | 13/09/24 | 10 days | 02/09/24 | 13/09/24 | 0 days | 0 days | 10 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.5.3 |  |  |  |  | Update ADO Training material | 100% | 02/09/24 | 13/09/24 | 10 days | 02/09/24 | 13/09/24 | 0 days | 0 days | 10 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.5.4 |  |  |  |  | Update ADO User Guide | 100% | 02/09/24 | 13/09/24 | 10 days | 02/09/24 | 13/09/24 | 0 days | 0 days | 10 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.5.5 |  |  |  |  | Update ADO Configuration document | 100% | 02/09/24 | 13/09/24 | 10 days | 02/09/24 | 13/09/24 | 0 days | 0 days | 10 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.5.6 |  |  |  |  | Update ADO Training Material and User Guide following SRO review | 100% | 02/10/24 | 02/10/24 | 1 day? | 02/10/24 | 02/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
6 | 1.4.1.4.8.6 |  |  |  |  | ADO Changes - Review Stage | 100% | 09/09/24 | 03/10/24 | 19 days? | 09/09/24 | 03/10/24 | 0 days | 0 days | 19 days? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.6.1 |  |  |  |  | Review implementation with SI LDP leads | 100% | 27/09/24 | 27/09/24 | 1 day? | 27/09/24 | 27/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.6.2 |  |  |  |  | Review implementation with SRO | 100% | 30/09/24 | 30/09/24 | 1 day? | 30/09/24 | 30/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.6.3 |  |  |  |  | LDP Review - ADO User Guide, Training Materials | 100% | 09/09/24 | 13/09/24 | 5 days | 09/09/24 | 13/09/24 | 0 days | 0 days | 5 days | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.6.4 |  |  |  |  | SRO Review - ADO User Guide, Training Materials | 100% | 30/09/24 | 30/09/24 | 1 day? | 30/09/24 | 30/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.6.5 |  |  |  |  | LDP Review - Config doc | 100% | 30/09/24 | 30/09/24 | 1 day? | 30/09/24 | 30/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.6.6 |  |  |  |  | SRO Review - Config doc | 100% | 30/09/24 | 30/09/24 | 1 day? | 30/09/24 | 30/09/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.6.7 |  |  |  |  | SRO Sign-off of all changes | 100% | 03/10/24 | 03/10/24 | 1 day? | 03/10/24 | 03/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
6 | 1.4.1.4.8.7 |  |  |  |  | Azure DevOps Changes - Final Implementation | 100% | 03/10/24 | 03/10/24 | 1 day? | 03/10/24 | 03/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.7.1 |  |  |  |  | Final task rollout | 100% | 03/10/24 | 03/10/24 | 1 day? | 03/10/24 | 03/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
7 | 1.4.1.4.8.7.2 |  |  |  |  | ADO Training Drop-in Session ahead of Cycle 3 | 100% | 03/10/24 | 03/10/24 | 1 day? | 03/10/24 | 03/10/24 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
3 | 1.4.2 |  |  | SITAG |  | SIT Execution | 36% | 31/10/22 | 27/11/25 | 804 days? | 31/10/22 | 27/11/25 | 0 days | 0 days | 414 days? | N/A |  | 5 | Yes
4 | 1.4.2.1 | T1 | T1-TE-1000 | PSG | MHHS-ART071 | System Integration Testing Start (M9) | 100% | 30/10/23 | 30/10/23 | 0 days | 30/10/23 | 30/10/23 | 0 days | -1 day | 0 days | CPT |  | 5.11 | Yes
4 | 1.4.2.2 |  |  | SITAG |  | SIT Component Integration Testing | 100% | 30/10/23 | 11/03/24 | 96 days | 30/10/23 | 11/03/24 | 0 days | 0 days | 1 day | N/A |  | 5 | Yes
5 | 1.4.2.2.1 |  |  |  |  | SIT Component Integration Testing Start | 100% | 30/10/23 | 30/10/23 | 0 days | 30/10/23 | 30/10/23 | 0 days | -1 day | 0 days | SI Test |  | 5.11 | Yes
5 | 1.4.2.2.2 | T3 | T3-TE-0060 | SITAG | MHHS-ART071 | Component Integration Testing Interval 1 Start | 100% | 30/10/23 | 30/10/23 | 0 days | 30/10/23 | 30/10/23 | 1 day | 0 days | 0 days | SI Test |  | 5.11 | Yes
5 | 1.4.2.2.3 | T3 | T3-TE-0061 | SITAG |  | Component Integration Testing Interval 2 Start | 100% | 13/11/23 | 13/11/23 | 0 days | 13/11/23 | 13/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5.12 | Yes
5 | 1.4.2.2.4 | T3 | T3-TE-0062 | SITAG |  | Component Integration Testing Interval 3 Start | 100% | 27/11/23 | 27/11/23 | 0 days | 27/11/23 | 27/11/23 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.2.2.5 | T3 | T3-TE-0063 | SITAG |  | Component Integration Testing Interval 4 Start | 100% | 11/12/23 | 11/12/23 | 0 days | 11/12/23 | 11/12/23 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.2.2.6 | T3 | T3-TE-0064 | SITAG |  | Component Integration Testing Interval 5 Start | 100% | 15/01/24 | 15/01/24 | 0 days | 15/01/24 | 15/01/24 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.2.2.7 | T3 | T3-TE-0065 | SITAG |  | Component Integration Testing Interval 6 Start | 100% | 29/01/24 | 29/01/24 | 0 days | 29/01/24 | 29/01/24 | 0 days | -1 day | 0 days | SI Test |  | 5 | Yes
5 | 1.4.2.2.8 |  |  |  |  | SIT Component Integration Testing Execution | 100% | 30/10/23 | 23/02/24 | 85 days | 30/10/23 | 23/02/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.2.2.9 | T3 | T3-TE-0032 | SITAG | MHHS-ART074 | SIT Component Integration Testing End (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 100% | 23/02/24 | 23/02/24 | 0 days | 23/02/24 | 23/02/24 | 1 day | 0 days | 0 days | SI Test |  | 5.19 | Yes
5 | 1.4.2.2.10 |  |  |  |  | Assurance of PPs Test Completion Reports | 100% | 22/01/24 | 01/03/24 | 30 days | 22/01/24 | 01/03/24 | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes
5 | 1.4.2.2.11 |  |  |  |  | SIT CI Test Completion Report | 100% | 07/02/24 | 01/03/24 | 18 days | 07/02/24 | 01/03/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.2.2.11.1 |  |  |  |  | Develop document | 100% | 07/02/24 | 23/02/24 | 13 days | 07/02/24 | 23/02/24 | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes
6 | 1.4.2.2.11.2 |  |  |  |  | Review & agree document | 100% | 26/02/24 | 01/03/24 | 5 days | 26/02/24 | 01/03/24 | 0 days | 0 days | 0 days | SI Test |  | 5.19 | Yes
5 | 1.4.2.2.12 | T2 | T2-TE-0600 | SITAG | MHHS-ART074 | SIT Component Integration Testing Test Completion Report Approved | 100% | 11/03/24 | 11/03/24 | 0 days | 11/03/24 | 11/03/24 | 1 day | 0 days | 0 days | SI Test |  | 5.18 | Yes
4 | 1.4.2.3 |  |  | SITAG |  | SIT - Minimum Viable Cohort (MVC) | 35% | 31/10/22 | 22/08/25 | 735 days? | 31/10/22 | 22/08/25 | 0 days | 0 days | 495 days? | N/A |  | 5 | Yes
5 | 1.4.2.3.1 |  |  |  |  | SIT Functional Testing (MVC) | 49% | 31/10/22 | 15/08/25 | 730 days? | 31/10/22 | 15/08/25 | 0 days | 0 days | 505 days? | N/A |  | 5 | Yes
6 | 1.4.2.3.1.1 | T3 | T3-TE-0034 | SITAG | MHHS-ART073 | SIT Functional Testing Start | 100% | 11/03/24 | 11/03/24 | 0 days | 11/03/24 | 11/03/24 | 1 day | 0 days | 0 days | SI Test |  | 6.1 | Yes
6 | 1.4.2.3.1.2 |  |  |  |  | SIT Functional Testing Execution (Minimum Viable Cohort) | 49% | 31/10/22 | 15/08/25 | 730 days? | 31/10/22 | 15/08/25 | 0 days | 0 days | 505 days? | N/A |  | 5 | Yes
7 | 1.4.2.3.1.2.1 |  |  |  |  | Cycle 1 (Full Cycle) | 100% | 11/03/24 | 14/06/24 | 70 days | 11/03/24 | 14/06/24 | 0 days | 0 days | -20 days | N/A |  | 5 | Yes
8 | 1.4.2.3.1.2.1.1 |  |  |  |  | Test Execution | 100% | 11/03/24 | 24/05/24 | 55 days | 11/03/24 | 24/05/24 | 0 days | 0 days | -25 days | PP |  | 5 | Yes
8 | 1.4.2.3.1.2.1.2 |  |  |  |  | Defect resolution, assurance, review, data & environments maintenance | 100% | 27/05/24 | 14/06/24 | 15 days | 27/05/24 | 14/06/24 | 0 days | 0 days | 5 days | SI Test |  | 5 | Yes
7 | 1.4.2.3.1.2.2 |  |  |  |  | Cycle 2 (Defect retests and targeted regression testing) | 100% | 17/06/24 | 04/10/24 | 80 days | 17/06/24 | 04/10/24 | 0 days | 0 days | 30 days | N/A |  | 5 | Yes
8 | 1.4.2.3.1.2.2.1 |  |  |  |  | Test Execution | 100% | 17/06/24 | 20/09/24 | 70 days | 17/06/24 | 20/09/24 | 0 days | 0 days | 30 days | PP |  | 5 | Yes
8 | 1.4.2.3.1.2.2.2 |  |  |  |  | Defect resolution, assurance, review, data & environments maintenance | 100% | 23/09/24 | 04/10/24 | 10 days | 23/09/24 | 04/10/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
7 | 1.4.2.3.1.2.3 |  |  |  |  | SIT Functional Testing back-up progress risk-assessment | 0% | 31/10/22 | 31/10/22 | 0 days | 31/10/22 | 31/10/22 | 0 days | -1 day | -20 days | N/A |  | 5.31 | Yes
8 | 1.4.2.3.1.2.3.1 |  |  |  |  | Back-up risk-assessment of SIT Functional progress to assess whether Qualification Execution can start early | 0% | 07/10/24 | 25/10/24 | 15 days | 07/10/24 | 25/10/24 | 0 days | 0 days | 0 days | SI Test |  | 5.31 | No
8 | 1.4.2.3.1.2.3.2 | T3 |  | QAG |  | Back-up SITAG decision on early Qualification Testing Execution start | 0% | 01/11/24 | 01/11/24 | 0 days | 01/11/24 | 01/11/24 | 1 day | 0 days | 0 days | SI Test |  | 5.31 | No
7 | 1.4.2.3.1.2.4 |  |  |  |  | Cycle 3 (Defect retests and targeted regression testing) | 41% | 21/10/24 | 14/03/25 | 105 days? | 21/10/24 | 14/03/25 | 0 days | 0 days | 75 days? | SI Test |  | 5 | Yes
8 | 1.4.2.3.1.2.4.1 |  |  |  |  | Sprint 5 | 100% | 21/10/24 | 01/11/24 | 10 days? | 21/10/24 | 01/11/24 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.2 |  |  |  |  | Sprint 6 | 100% | 04/11/24 | 15/11/24 | 10 days? | 04/11/24 | 15/11/24 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.3 |  |  |  |  | Sprint 7 | 100% | 18/11/24 | 29/11/24 | 10 days? | 18/11/24 | 29/11/24 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.4 |  |  |  |  | Sprint 8 | 100% | 02/12/24 | 20/12/24 | 15 days? | 02/12/24 | 20/12/24 | 0 days | 0 days | 15 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.5 |  |  |  |  | Christmas downtime | 100% | 23/12/24 | 03/01/25 | 10 days? | 23/12/24 | 03/01/25 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.6 |  |  |  |  | Sprint 9 | 10% | 06/01/25 | 17/01/25 | 10 days? | 06/01/25 | 17/01/25 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.7 |  |  |  |  | Sprint 10 | 0% | 20/01/25 | 31/01/25 | 10 days? | 20/01/25 | 31/01/25 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.8 |  |  |  |  | Sprint 11 | 0% | 03/02/25 | 14/02/25 | 10 days? | 03/02/25 | 14/02/25 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.9 |  |  |  |  | Sprint 12 | 0% | 17/02/25 | 28/02/25 | 10 days? | 17/02/25 | 28/02/25 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.10 |  |  |  |  | Sprint 13 (RTTM Gap Analysis + CR056) | 0% | 03/03/25 | 14/03/25 | 10 days? | 03/03/25 | 14/03/25 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.1.2.4.11 |  |  |  |  | Sprint 14 (RTTM Gap Analysis + CR056) | 0% | 17/03/25 | 28/03/25 | 10 days? | 17/03/25 | 28/03/25 | 0 days | 0 days | 10 days? | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.1.2.4.12 |  |  |  |  | Sprint 15 (Contingency 1) | 0% | 31/03/25 | 11/04/25 | 10 days? | 31/03/25 | 11/04/25 | 0 days | 0 days | 10 days? | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.1.2.4.13 |  |  |  |  | Sprint 16 (Contingency 2) | 0% | 14/04/25 | 25/04/25 | 10 days? | 14/04/25 | 25/04/25 | 0 days | 0 days | 10 days? | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.1.2.4.14 | T2 | T2-TE-1150 |  |  | SIT Functional Cycle 3 Complete | 0% | 28/04/25 | 28/04/25 | 1 day? | N/A | N/A | 0 days | 0 days | 1 day? | SI Test |  | 6.13 | Yes
7 | 1.4.2.3.1.2.5 |  |  |  |  | SIT Functional Settlement Testing | 35% | 17/06/24 | 02/05/25 | 230 days? | 17/06/24 | 02/05/25 | 0 days | 0 days | 230 days? | SI Test |  | 6.12 | Yes
8 | 1.4.2.3.1.2.5.1 |  |  |  |  | SIT-B Settlement Testing Cycle 2 | 0% | 10/03/25 | 13/06/25 | 70 days | 17/06/24 | 20/09/24 | 190 days | 190 days | 70 days | SI Test |  | 6.12 | Yes
8 | 1.4.2.3.1.2.5.2 |  |  |  |  | SIT-B Settlement Testing Cycle 3 | 68% | 07/10/24 | 21/02/25 | 100 days? | 07/10/24 | 20/12/24 | 0 days | 45 days | 100 days? | SI Test |  | 6.12 | Yes
9 | 1.4.2.3.1.2.5.2.1 |  |  |  |  | Sprint 5 | 100% | 07/10/24 | 01/11/24 | 20 days? | 07/10/24 | 01/11/24 | 0 days | 0 days | 20 days? | SI Test |  | 6.12 | Yes
9 | 1.4.2.3.1.2.5.2.2 |  |  |  |  | Sprint 5 Review (Flexibility Window Checkpoint) | 100% | 04/11/24 | 04/11/24 | 0 days | 04/11/24 | 04/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6.12 | Yes
9 | 1.4.2.3.1.2.5.2.3 |  |  |  |  | Sprint 6 | 100% | 04/11/24 | 15/11/24 | 10 days? | 04/11/24 | 15/11/24 | 0 days | 0 days | 10 days? | SI Test |  | 6.12 | Yes
9 | 1.4.2.3.1.2.5.2.4 |  |  |  |  | Sprint 6 Review (Pre Christmas Contingency Decision Point) | 100% | 18/11/24 | 18/11/24 | 0 days | 18/11/24 | 18/11/24 | 1 day | 0 days | 0 days | SI Test |  | 6.12 | Yes
9 | 1.4.2.3.1.2.5.2.5 |  |  |  |  | Sprint 7 | 100% | 18/11/24 | 29/11/24 | 10 days? | 18/11/24 | 29/11/24 | 0 days | 0 days | 10 days? | SI Test |  | 6.12 | Yes
9 | 1.4.2.3.1.2.5.2.6 |  |  |  |  | Sprint 7 Review (Post Christmas Contingency Decision Point) | 100% | 02/12/24 | 02/12/24 | 0 days | 02/12/24 | 02/12/24 | 1 day | 0 days | 0 days | SI Test |  | 6.12 | Yes
9 | 1.4.2.3.1.2.5.2.7 |  |  |  |  | Sprint 8 | 100% | 02/12/24 | 20/12/24 | 15 days | 02/12/24 | 20/12/24 | 0 days | 0 days | 15 days | SI Test |  | 6.15 | Yes
9 | 1.4.2.3.1.2.5.2.8 |  |  |  |  | Post-Christmas Stabilisation | 100% | 06/01/25 | 10/01/25 | 5 days | 06/01/25 | 10/01/25 | 0 days | 0 days | 5 days | SI Test |  | 6.15 | Yes
9 | 1.4.2.3.1.2.5.2.9 |  |  |  |  | Sprint 9 | 50% | 06/01/25 | 17/01/25 | 10 days | 13/01/25 | 17/01/25 | -5 days | 0 days | 10 days | SI Test |  | 6.15 | Yes
9 | 1.4.2.3.1.2.5.2.10 |  |  |  |  | Sprint 9 Review | 0% | 20/01/25 | 20/01/25 | 0 days | 20/01/25 | 20/01/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
9 | 1.4.2.3.1.2.5.2.11 |  |  |  |  | Sprint 10 | 0% | 20/01/25 | 31/01/25 | 10 days | 20/01/25 | 31/01/25 | 0 days | 0 days | 10 days | SI Test |  | 6.15 | Yes
9 | 1.4.2.3.1.2.5.2.12 |  |  |  |  | Sprint 10 Review | 0% | 03/02/25 | 03/02/25 | 0 days | 03/02/25 | 03/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
9 | 1.4.2.3.1.2.5.2.13 |  |  |  |  | Sprint 11 | 0% | 03/02/25 | 14/02/25 | 10 days | 03/02/25 | 14/02/25 | 0 days | 0 days | 10 days | SI Test |  | 6.15 | Yes
9 | 1.4.2.3.1.2.5.2.14 |  |  |  |  | Sprint 11 Review | 0% | 14/02/25 | 14/02/25 | 0 days | 14/02/25 | 14/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
9 | 1.4.2.3.1.2.5.2.15 |  |  |  |  | Sprint 12 | 0% | 17/02/25 | 21/02/25 | 5 days | 17/02/25 | 21/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6.15 | Yes
9 | 1.4.2.3.1.2.5.2.16 | T3 | T3-TE-0140 | SITAG |  | End of Settlement Testing Cycle 3 | 0% | 21/02/25 | 21/02/25 | 0 days | 21/02/25 | 21/02/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
8 | 1.4.2.3.1.2.5.3 |  |  |  |  | SIT-A CoS Settlement Testing | 0% | 19/05/25 | 13/06/25 | 20 days? | 19/05/25 | 13/06/25 | 0 days | 0 days | 20 days? | SI Test |  | 6.15 | Yes
7 | 1.4.2.3.1.2.6 |  |  |  |  | SIT Functional MVC Regression Testing (code freeze) | 0% | 16/06/25 | 08/08/25 | 40 days? | 16/06/25 | 08/08/25 | 0 days | 0 days | -5 days? | PP |  | 6.15 | Yes
8 | 1.4.2.3.1.2.6.1 | T2 | T2-TE-1250 | SITAG |  | Regression Test Execution Start | 0% | 16/06/25 | 16/06/25 | 1 day | 16/06/25 | 16/06/25 | 0 days | 0 days | 1 day | SI Test |  | 6.15 | Yes
8 | 1.4.2.3.1.2.6.2 |  |  |  |  | Regression Sprint 1 | 0% | 16/06/25 | 27/06/25 | 10 days? | 16/06/25 | 27/06/25 | 0 days | 0 days | 10 days? | SI Test |  | 6.14 | Yes
8 | 1.4.2.3.1.2.6.3 |  |  |  |  | Regression Sprint 2 | 0% | 30/06/25 | 18/07/25 | 15 days | 30/06/25 | 18/07/25 | 0 days | 0 days | 15 days | SI Test |  | 6.15 | Yes
8 | 1.4.2.3.1.2.6.4 |  |  |  |  | Regression Sprint 3 | 0% | 21/07/25 | 08/08/25 | 15 days | 21/07/25 | 08/08/25 | 0 days | 0 days | 15 days | SI Test |  | 6.15 | Yes
7 | 1.4.2.3.1.2.7 | T3 | T3-TE-0046 | SITAG | MHHS-ART072 | SIT Functional Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | 08/08/25 | 08/08/25 | 0 days | 08/08/25 | 08/08/25 | 1 day | 0 days | 0 days | SI Test |  | 6.1 | Yes
7 | 1.4.2.3.1.2.8 |  |  |  |  | Assurance of PPs Test Completion Reports | 0% | 14/07/25 | 15/08/25 | 25 days | 14/07/25 | 15/08/25 | 0 days | 0 days | -5 days | SI Test |  | 6.1 | Yes
7 | 1.4.2.3.1.2.9 |  |  |  |  | SIT Functional Test Completion Report (Minimum Viable Cohort) | 0% | 21/07/25 | 15/08/25 | 20 days | 21/07/25 | 15/08/25 | 0 days | 0 days | 0 days | N/A |  | 6.1 | Yes
8 | 1.4.2.3.1.2.9.1 |  |  |  |  | Develop document | 0% | 21/07/25 | 08/08/25 | 15 days | 21/07/25 | 08/08/25 | 0 days | 0 days | 0 days | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.1.2.9.2 |  |  |  |  | Review & agree document | 0% | 11/08/25 | 15/08/25 | 5 days | 11/08/25 | 15/08/25 | 0 days | 0 days | 0 days | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.1.2.9.3 | T2 | T2-TE-0850 | SITAG | MHHS-ART072 | SIT Functional Testing Test Completion Report (Minimum Viable Cohort) Approved | 0% | 15/08/25 | 15/08/25 | 0 days | 15/08/25 | 15/08/25 | 1 day | 0 days | 0 days | SI Test |  | 6.1 | Yes
5 | 1.4.2.3.2 |  |  |  |  | Helix E2E Settlement Testing | 0% | 07/02/25 | 06/06/25 | 86 days? | 06/01/25 | 04/04/25 | 24 days | 45 days | 86 days? | SI Test |  | 6 | Yes
6 | 1.4.2.3.2.1 |  |  |  |  | Programme agreement into Settlement Testing | 0% | 07/02/25 | 07/02/25 | 1 day? | 07/02/25 | 07/02/25 | 0 days | 0 days | 1 day? | SI Test |  | 6.15 | Yes
6 | 1.4.2.3.2.2 |  |  |  |  | Helix E2E Settlement Testing Execution | 0% | 10/03/25 | 06/06/25 | 65 days | 06/01/25 | 04/04/25 | 45 days | 45 days | 65 days | SI Test |  | 6 | Yes
6 | 1.4.2.3.2.3 |  |  |  |  | Helix E2E Settlement Testing Execution Complete | 0% | 06/06/25 | 06/06/25 | 0 days | 04/04/25 | 04/04/25 | 46 days | 45 days | 0 days | SI Test |  | 6 | Yes
6 | 1.4.2.3.2.4 |  |  |  |  | MHHSP Helix E2E Testing Assurance | 0% | 10/03/25 | 06/06/25 | 65 days | 06/01/25 | 04/04/25 | 45 days | 45 days | 65 days | SI Test |  | 6 | Yes
6 | 1.4.2.3.2.5 |  |  |  |  | MHHSP Helix E2E Testing Assurance Complete | 0% | 06/06/25 | 06/06/25 | 0 days | 04/04/25 | 04/04/25 | 46 days | 45 days | 0 days | SI Test |  | 6 | Yes
5 | 1.4.2.3.3 |  |  | SITAG |  | SIT Migration Testing (MVC) | 54% | 11/03/24 | 22/08/25 | 380 days? | 11/03/24 | 22/08/25 | 0 days | 0 days | 225 days? | SI Test |  | 6 | Yes
6 | 1.4.2.3.3.1 |  |  |  |  | SIT Migration Testing Start | 0% | 11/03/24 | 11/03/24 | 0 days? | 11/03/24 | 11/03/24 | 0 days | -1 day | 0 days? | SI Test |  | 6 | Yes
6 | 1.4.2.3.3.2 |  |  | SITAG |  | SIT Migration Testing Execution (Minimum Viable Cohort) | 54% | 11/03/24 | 22/08/25 | 380 days? | 11/03/24 | 22/08/25 | 0 days | 0 days | 380 days? | SI Test |  | 6 | Yes
7 | 1.4.2.3.3.2.1 |  |  |  |  | Cycle 1 (Full Cycle) | 100% | 11/03/24 | 14/06/24 | 70 days? | 11/03/24 | 14/06/24 | 0 days | 0 days | 70 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.1.1 |  |  |  |  | Test Execution | 100% | 11/03/24 | 24/05/24 | 55 days? | 11/03/24 | 24/05/24 | 0 days | 0 days | 55 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.1.2 |  |  |  |  | Defect resolution, assurance, review, data& environments maintenance | 100% | 27/05/24 | 14/06/24 | 15 days? | 27/05/24 | 14/06/24 | 0 days | 0 days | 15 days? | SI Test |  | 6 | Yes
7 | 1.4.2.3.3.2.2 |  |  |  |  | Cycle 2 (Defect retests and targeted regression testing) | 100% | 11/03/24 | 28/06/24 | 80 days? | 11/03/24 | 28/06/24 | 0 days | 0 days | 80 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.2.1 |  |  |  |  | Test Execution | 100% | 17/06/24 | 20/09/24 | 70 days? | 17/06/24 | 20/09/24 | 0 days | 0 days | 70 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.2.2 |  |  |  |  | Defect resolution, assurance, review, data & environments maintenance | 100% | 23/09/24 | 04/10/24 | 10 days? | 23/09/24 | 04/10/24 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
7 | 1.4.2.3.3.2.3 |  |  |  |  | SIT Functional Testing back-up progress risk-assessment | 0% | 17/06/24 | 20/09/24 | 70 days? | 17/06/24 | 20/09/24 | 0 days | 0 days | 70 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.3.1 |  |  |  |  | Back-up risk-assessment of SIT Migration progress to assess whether Qualification Execution can start early | 0% | 07/10/24 | 25/10/24 | 15 days? | 07/10/24 | 25/10/24 | 0 days | 0 days | 15 days? | SI Test |  | 6 | Yes |  | 13/11/24 - 8/9 prerequisite test complete, final test relies on deployment of IR8.4.
8 | 1.4.2.3.3.2.3.2 |  |  |  |  | Back-up SITAG decision on early Qualification Testing Execution start | 0% | 01/11/24 | 01/11/24 | 0 days? | 01/11/24 | 01/11/24 | 1 day | 0 days | 0 days? | SI Test |  | 6 | Yes
7 | 1.4.2.3.3.2.4 |  |  |  |  | Cycle 3 (Defect retests and targeted regression testing) | 41% | 21/10/24 | 25/04/25 | 135 days? | 21/10/24 | 25/04/25 | 0 days | 0 days | 135 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.4.1 |  |  |  |  | Sprint 5 | 100% | 21/10/24 | 01/11/24 | 10 days | 21/10/24 | 01/11/24 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.4.2 |  |  |  |  | Sprint 6 | 100% | 04/11/24 | 15/11/24 | 10 days | 04/11/24 | 15/11/24 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.4.3 |  |  |  |  | Sprint 7 | 100% | 18/11/24 | 29/11/24 | 10 days | 18/11/24 | 29/11/24 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.4.4 |  |  |  |  | Sprint 8 | 100% | 02/12/24 | 20/12/24 | 15 days | 02/12/24 | 20/12/24 | 0 days | 0 days | 15 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.4.5 |  |  |  |  | Christmas downtime | 100% | 23/12/24 | 03/01/25 | 10 days | 23/12/24 | 03/01/25 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.4.6 |  |  |  |  | Sprint 9 | 10% | 06/01/25 | 17/01/25 | 10 days | 06/01/25 | 17/01/25 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.4.7 |  |  |  |  | Sprint 10 | 0% | 20/01/25 | 31/01/25 | 10 days | 20/01/25 | 31/01/25 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.4.8 |  |  |  |  | Sprint 11 | 0% | 03/02/25 | 14/02/25 | 10 days | 03/02/25 | 14/02/25 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.4.9 |  |  |  |  | Sprint 12 | 0% | 17/02/25 | 28/02/25 | 10 days | 17/02/25 | 28/02/25 | 0 days | 0 days | 10 days | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.4.10 |  |  |  |  | Sprint 13 | 0% | 03/03/25 | 14/03/25 | 10 days | 03/03/25 | 14/03/25 | 0 days | 0 days | 10 days | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.3.2.4.11 |  |  |  |  | Sprint 14 (RTTM Gap Analysis + CR056) | 0% | 17/03/25 | 28/03/25 | 10 days? | 17/03/25 | 28/03/25 | 0 days | 0 days | 10 days? | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.3.2.4.12 |  |  |  |  | Sprint 15 (Contingency 1) | 0% | 31/03/25 | 11/04/25 | 10 days? | 31/03/25 | 11/04/25 | 0 days | 0 days | 10 days? | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.3.2.4.13 |  |  |  |  | Sprint 16 (Contingency 2) | 0% | 14/04/25 | 25/04/25 | 10 days? | 14/04/25 | 25/04/25 | 0 days | 0 days | 10 days? | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.3.2.4.14 | T2 | T2-TE-1200 |  |  | SIT Migration Cycle 3 Complete | 0% | 25/04/25 | 25/04/25 | 0 days | 25/04/25 | 25/04/25 | 1 day | 0 days | 0 days | SI Test |  | 6.1 | Yes
7 | 1.4.2.3.3.2.5 |  |  |  |  | SIT Migration MVC Regression Testing (code freeze) | 0% | 16/06/25 | 01/08/25 | 35 days? | 16/06/25 | 01/08/25 | 0 days | 0 days | 35 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.5.1 |  |  |  |  | Regression Sprint 1 | 0% | 16/06/25 | 27/06/25 | 10 days? | 16/06/25 | 27/06/25 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.5.2 |  |  |  |  | Regression Sprint 2 | 0% | 30/06/25 | 11/07/25 | 10 days? | 30/06/25 | 11/07/25 | 0 days | 0 days | 10 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.5.3 |  |  |  |  | Regression Sprint 3 | 0% | 14/07/25 | 01/08/25 | 15 days? | 14/07/25 | 01/08/25 | 0 days | 0 days | 15 days? | SI Test |  | 6 | Yes
8 | 1.4.2.3.3.2.5.4 |  |  |  |  | SIT Migration Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | 01/08/25 | 01/08/25 | 0 days | 01/08/25 | 01/08/25 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
7 | 1.4.2.3.3.2.6 | T3 |  | SITAG | MHHS-ART076 | SIT Migration Test Completion Report (Minimum Viable Cohort) | 0% | 14/07/25 | 15/08/25 | 25 days | 14/07/25 | 15/08/25 | 0 days | 0 days | 25 days | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.3.2.6.1 |  |  |  |  | Develop document | 0% | 14/07/25 | 01/08/25 | 15 days | 14/07/25 | 01/08/25 | 0 days | 0 days | -70 days | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.3.2.6.2 |  |  |  |  | Review & agree document | 0% | 04/08/25 | 08/08/25 | 5 days | 04/08/25 | 08/08/25 | 0 days | 0 days | -5 days | SI Test |  | 6.1 | Yes
8 | 1.4.2.3.3.2.6.3 | T2 | T2-TE-0800 | SITAG |  | SIT Migration Testing Test Completion Report (Minimum Viable Cohort) Approved | 0% | 15/08/25 | 15/08/25 | 0 days | 15/08/25 | 15/08/25 | 1 day | 0 days | -45 days | SI Test |  | 6.1 | Yes
7 | 1.4.2.3.3.2.7 | T3 | T3-TE-0043 | SITAG | MHHS-ART076 | SIT Migration Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | 15/08/25 | 15/08/25 | 0 days | 15/08/25 | 15/08/25 | 1 day | 0 days | 0 days | SI Test |  | 6.1 | Yes
7 | 1.4.2.3.3.2.8 |  |  |  |  | Assurance of PPs Test Completion Reports | 0% | 14/07/25 | 22/08/25 | 30 days | 14/07/25 | 22/08/25 | 0 days | 0 days | 0 days | SI Test |  | 6.1 | Yes
5 | 1.4.2.3.4 |  |  | SITAG |  | SIT Non-Functional Testing (all SIT PPs) | 0% | 03/03/25 | 05/06/25 | 69 days? | 28/02/25 | 10/07/25 | 1 day | -25 days | -31 days? | N/A |  | 6.1 | Yes
6 | 1.4.2.3.4.1 | T3 | T3-TE-0124 | SITAG |  | Theme 1 (Helix and DIP Volume Testing) Start | 0% | 03/03/25 | 03/03/25 | 0 days? | 03/03/25 | 03/03/25 | 1 day | 0 days | 0 days? | SIT Participant |  | 6.15 | Yes
6 | 1.4.2.3.4.2 |  |  |  |  | Theme 1 (Helix and DIP Volume Testing) Execution | 0% | 03/03/25 | 21/03/25 | 15 days? | 03/03/25 | 21/03/25 | 0 days | 0 days | 15 days? |  |  | 6.15 | Yes
6 | 1.4.2.3.4.3 | T3 | T3-TE-0040 | SITAG | MHHS-ART079 | Theme 2 SIT Non-Functional Testing Start | 0% | 27/03/25 | 27/03/25 | 0 days | 31/03/25 | 31/03/25 | -1 day | -2 days | 0 days | SI Test |  | 6.15 | Yes
6 | 1.4.2.3.4.4 |  |  |  |  | Theme 2 SIT Non-Functional Testing Execution | 0% | 27/03/25 | 21/05/25 | 40 days | 01/05/25 | 25/06/25 | -25 days | -25 days | -50 days | SI Test |  | 6.15 | Yes
6 | 1.4.2.3.4.5 |  |  |  |  | Theme 3 SIT Non-Functional Testing Start | 0% | 27/03/25 | 27/03/25 | 1 day? | 02/05/25 | 02/05/25 | -26 days | -26 days | 1 day? |  |  | 6.15 | Yes
6 | 1.4.2.3.4.6 |  |  |  |  | Theme 3 SIT Non-Functional Testing Execution | 0% | 27/03/25 | 21/05/25 | 40 days? | 02/05/25 | 26/06/25 | -26 days | -26 days | 40 days? |  |  | 6.15 | Yes
6 | 1.4.2.3.4.7 | T3 | T3-TE-0047 | SITAG | MHHS-ART079 | SIT Non-Functional Testing End (all SIT PPs) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | 23/05/25 | 23/05/25 | 0 days | 23/05/25 | 23/05/25 | 0 days | -1 day | 0 days | SI Test |  | 6.15 | Yes
6 | 1.4.2.3.4.8 |  |  |  |  | Assurance of PPs Test Completion Reports | 0% | 02/05/25 | 29/05/25 | 20 days | 05/05/25 | 30/05/25 | -1 day | -1 day | -10 days | SI Test |  | 6.15 | Yes
6 | 1.4.2.3.4.9 |  |  |  |  | SIT Non-Functional Testing Test Completion Report (all SIT PPs) | 0% | 02/05/25 | 29/05/25 | 20 days | 02/05/25 | 29/05/25 | 0 days | 0 days | 0 days | N/A |  | 6.15 | Yes
7 | 1.4.2.3.4.9.1 |  |  |  |  | Develop document | 0% | 02/05/25 | 23/05/25 | 15 days | 05/05/25 | 23/05/25 | -1 day | -1 day | 0 days | SI Test |  | 6.15 | Yes
7 | 1.4.2.3.4.9.2 |  |  |  |  | Review & agree document | 0% | 23/05/25 | 29/05/25 | 5 days | 26/05/25 | 30/05/25 | -1 day | -1 day | 0 days | SI Test |  | 6.15 | Yes
6 | 1.4.2.3.4.10 | T2 | T2-TE-0900 | SITAG | MHHS-ART079 | SIT Non-Functional Testing Test Completion Report (all SIT PPs) Approved | 0% | 05/06/25 | 05/06/25 | 0 days | 06/06/25 | 06/06/25 | 0 days | -1 day | 0 days | SI Test |  | 6.15 | Yes
5 | 1.4.2.3.5 |  |  | SITAG |  | SIT Operational Testing (all SIT PPs) | 0% | 03/02/25 | 25/07/25 | 125 days? | 03/02/25 | 06/06/25 | 0 days | 35 days | 35 days? | N/A |  | 5 | Yes
6 | 1.4.2.3.5.1 |  |  | SITAG |  | Non-SIT B Testing | 0% | 03/02/25 | 07/03/25 | 25 days? | 03/02/25 | 07/03/25 | 0 days | 0 days | 25 days? |  |  |  | Yes
7 | 1.4.2.3.5.1.1 | T3 | T3-TE-0121 | SITAG |  | SIT Operational Testing Start (Theme 3 - Batch 1 (Service Management)) | 0% | 03/02/25 | 03/02/25 | 0 days? | 03/02/25 | 03/02/25 | 0 days | -1 day | 0 days? | SI Test |  | 6 | Yes
7 | 1.4.2.3.5.1.2 |  |  |  |  | SIT Operational Testing Execution Window (Theme 3 - Batch 1 (Service Management)) | 0% | 03/02/25 | 07/03/25 | 25 days? | 03/02/25 | 07/03/25 | 0 days | 0 days | 25 days? |  |  | 6 | Yes
6 | 1.4.2.3.5.2 |  |  |  |  | SIT B Testing | 0% | 31/03/25 | 04/07/25 | 70 days? | 07/02/25 | 16/05/25 | 36 days | 35 days | 70 days? |  |  | 6.15 | Yes
7 | 1.4.2.3.5.2.1 | T3 | T3-TE-0042 | SITAG | MHHS-ART073 MHHS-ART143 | SIT Operational Testing Start (SIT B) | 0% | 31/03/25 | 31/03/25 | 0 days | 31/03/25 | 31/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
7 | 1.4.2.3.5.2.2 |  |  |  |  | SIT Operational Testing Execution Theme 3 Batch 2 | 0% | 31/03/25 | 02/05/25 | 25 days? | 31/03/25 | 02/05/25 | 0 days | 0 days | 25 days? | SI Test |  | 6.15 | Yes
7 | 1.4.2.3.5.2.3 |  |  |  |  | SIT Operational Testing Execution Theme 1 | 0% | 05/05/25 | 06/06/25 | 25 days? | 05/05/25 | 06/06/25 | 0 days | 0 days | 25 days? | SI Test |  | 6.15 | Yes
7 | 1.4.2.3.5.2.4 |  |  |  |  | SIT Operational Testing Execution Theme 2 | 0% | 09/06/25 | 04/07/25 | 20 days? | 09/06/25 | 04/07/25 | 0 days | 0 days | 20 days? | SI Test |  | 6.15 | Yes
6 | 1.4.2.3.5.3 | T3 | T3-TE-0050 | SITAG | MHHS-ART081 | SIT Operational Testing End (all SIT PPs) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | 11/07/25 | 11/07/25 | 0 days | 11/07/25 | 11/07/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
6 | 1.4.2.3.5.4 |  |  |  |  | Assurance of PPs Test Completion Reports | 0% | 09/06/25 | 18/07/25 | 30 days | 09/06/25 | 18/07/25 | 0 days | 0 days | 0 days | SI Test |  | 6.15 | Yes
6 | 1.4.2.3.5.5 |  |  |  |  | SIT Operational Testing Test Completion Report (all SIT PPs) | 0% | 23/06/25 | 18/07/25 | 20 days | 23/06/25 | 18/07/25 | 0 days | 0 days | 0 days | N/A |  | 6.15 | Yes
7 | 1.4.2.3.5.5.1 |  |  |  |  | Develop document | 0% | 23/06/25 | 11/07/25 | 15 days | 23/06/25 | 11/07/25 | 0 days | 0 days | 0 days | SI Test |  | 6.15 | Yes
7 | 1.4.2.3.5.5.2 |  |  |  |  | Review & agree document | 0% | 14/07/25 | 18/07/25 | 5 days | 14/07/25 | 18/07/25 | 0 days | 0 days | 0 days | SI Test |  | 6.15 | Yes
6 | 1.4.2.3.5.6 | T2 | T2-TE-0950 | SITAG | MHHS-ART081 | SIT Operational Testing Test Completion Report (all SIT PPs) Approved | 0% | 25/07/25 | 25/07/25 | 0 days | 25/07/25 | 25/07/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes
5 | 1.4.2.3.6 |  |  |  |  | SIT MVC Test Exit Report | 0% | 21/07/25 | 15/08/25 | 20 days | 14/07/25 | 08/08/25 | 5 days | 5 days | 0 days | N/A |  | 6 | Yes
5 | 1.4.2.3.7 | T1 | T1-TE-2000 | PSG | MHHS-ART081 | SIT Minimum Viable Cohort Complete (SIT Minimum Viable Cohort Test Exit Report Approved) | 0% | 22/08/25 | 22/08/25 | 0 days | 22/08/25 | 22/08/25 | 1 day | 0 days | 0 days | CPT |  | 6 | Yes
4 | 1.4.2.4 |  |  |  |  | SIT (non-MVC) | 10% | 16/06/25 | 27/11/25 | 119 days? | 05/05/25 | 27/11/25 | 30 days | 0 days | -176 days? | N/A |  | 6 | Yes
5 | 1.4.2.4.1 |  |  |  |  | SIT Functional Testing (non-MVC) | 0% | 16/06/25 | 14/11/25 | 110 days? | 16/06/25 | 14/11/25 | 0 days | 0 days | -185 days? | N/A |  | 6 | Yes
6 | 1.4.2.4.1.1 |  |  |  |  | SIT Functional Testing Execution (non-MVC) | 0% | 16/06/25 | 24/10/25 | 95 days? | 16/06/25 | 24/10/25 | 0 days | 0 days | -185 days? | N/A |  | 6 | Yes
7 | 1.4.2.4.1.1.1 |  |  |  |  | Test Execution (Cycle 3 Completion and Regression Testing) | 0% | 16/06/25 | 24/10/25 | 95 days? | 16/06/25 | 24/10/25 | 0 days | 0 days | 95 days? |  |  | 6 | Yes
7 | 1.4.2.4.1.1.2 | T3 | T3-TE-0052 | SITAG | MHHS-ART072 | SIT Functional Testing End (non-MVC) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | 24/10/25 | 24/10/25 | 0 days | 24/10/25 | 24/10/25 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.4.2.4.1.2 |  |  |  |  | Assurance of PPs Test Completion Reports | 0% | 03/11/25 | 07/11/25 | 5 days | 03/11/25 | 07/11/25 | 0 days | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.4.2.4.1.3 |  |  |  |  | SIT Functional Testing Test Completion Report (non-MVC) | 0% | 06/10/25 | 07/11/25 | 25 days | 06/10/25 | 07/11/25 | 0 days | 0 days | 0 days | N/A |  | 6 | Yes
7 | 1.4.2.4.1.3.1 |  |  |  |  | Develop document | 0% | 06/10/25 | 24/10/25 | 15 days | 06/10/25 | 24/10/25 | 0 days | 0 days | 0 days | SI Test |  | 6 | Yes
7 | 1.4.2.4.1.3.2 |  |  |  |  | Review & agree document | 0% | 03/11/25 | 07/11/25 | 5 days | 03/11/25 | 07/11/25 | 0 days | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.4.2.4.1.4 | T3 | T3-TE-0055 | SITAG | MHHS-ART072 | SIT Functional Testing Test Completion Report (non-MVC) Approved | 0% | 14/11/25 | 14/11/25 | 0 days | 14/11/25 | 14/11/25 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
5 | 1.4.2.4.2 |  |  |  |  | SIT Migration Testing (non-MVC) | 23% | 16/06/25 | 14/11/25 | 110 days | 05/05/25 | 08/10/25 | 30 days | 27 days | -120 days | N/A |  | 6 | Yes
6 | 1.4.2.4.2.1 |  |  |  |  | Test Execution (Cycle 3 Completion and Regression Testing) | 28% | 16/06/25 | 24/10/25 | 95 days | 16/06/25 | 24/10/25 | 0 days | 0 days | -120 days | SI Test |  | 6 | Yes
6 | 1.4.2.4.2.2 | T3 | T3-TE-0051 | SITAG | MHHS-ART076 | SIT Migration Testing End (non-MVC) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | 24/10/25 | 24/10/25 | 0 days | 24/10/25 | 24/10/25 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.4.2.4.2.3 |  |  |  |  | Assurance of PPs Test Completion Reports | 0% | 03/11/25 | 07/11/25 | 5 days | 03/11/25 | 07/11/25 | 0 days | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.4.2.4.2.4 |  |  |  |  | SIT Migration Testing Test Completion Report (non-MVC) | 0% | 06/10/25 | 07/11/25 | 25 days | 06/10/25 | 07/11/25 | 0 days | 0 days | 0 days | N/A |  | 6 | Yes
7 | 1.4.2.4.2.4.1 |  |  |  |  | Develop document | 0% | 06/10/25 | 24/10/25 | 15 days | 06/10/25 | 24/10/25 | 0 days | 0 days | 0 days | SI Test |  | 6 | Yes
7 | 1.4.2.4.2.4.2 |  |  |  |  | Review & agree document | 0% | 03/11/25 | 07/11/25 | 5 days | 03/11/25 | 07/11/25 | 0 days | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.4.2.4.2.5 | T3 | T3-TE-0056 | SITAG | MHHS-ART076 | SIT Migration Testing Test Completion Report (non-MVC Approved) | 0% | 14/11/25 | 14/11/25 | 0 days | 14/11/25 | 14/11/25 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
5 | 1.4.2.4.3 |  |  |  |  | SIT non-MVC Test Exit Report | 0% | 27/10/25 | 21/11/25 | 20 days | 27/10/25 | 21/11/25 | 0 days | 0 days | 0 days | N/A |  | 6 | Yes
6 | 1.4.2.4.3.1 |  |  |  |  | Develop document | 0% | 27/10/25 | 14/11/25 | 15 days | 27/10/25 | 14/11/25 | 0 days | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.4.2.4.3.2 |  |  |  |  | Review & agree document | 0% | 17/11/25 | 21/11/25 | 5 days | 17/11/25 | 21/11/25 | 0 days | 0 days | 0 days | SI Test |  | 6 | Yes
5 | 1.4.2.4.4 | T3 | T3-TE-0059 | SITAG | MHHS-ART081 | SIT non-MVC Complete | 0% | 27/11/25 | 27/11/25 | 0 days | 27/11/25 | 27/11/25 | 1 day | 0 days | 0 days | SI Test |  | 6 | Yes
3 | 1.4.3 |  |  | SITAG |  | UIT Environment Preparation | 51% | 31/10/22 | 06/06/25 | 680 days? | 31/10/22 | 04/07/25 | 0 days | -20 days | 0 days? | N/A |  | 6 | Yes
4 | 1.4.3.1 |  |  | SITAG |  | Test Artefact Development | 51% | 01/03/23 | 16/04/25 | 556 days? | 01/03/23 | 18/07/24 | 0 days | 194 days | 195 days? | N/A |  | 6 | Yes
5 | 1.4.3.1.1 |  |  |  |  | E2E Sandbox Guidance | 71% | 01/03/23 | 24/03/25 | 539 days? | 01/03/23 | 18/07/24 | 0 days | 177 days | 178 days? | N/A |  | 6 | Yes
6 | 1.4.3.1.1.1 |  |  |  |  | Develop document | 100% | 01/03/23 | 23/06/23 | 83 days | 01/03/23 | 23/06/23 | 0 days | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.4.3.1.1.2 |  |  |  |  | Artefact review (via SITAG) and updates | 100% | 26/06/23 | 28/07/23 | 25 days | 26/06/23 | 28/07/23 | 0 days | 0 days | 0 days | SI Test |  | 6 | Yes
6 | 1.4.3.1.1.3 | T3 | T3-TE-0067 | QAG | MHHS-ART154 | E2E Sandbox Guidance approved | 100% | 18/07/24 | 18/07/24 | 0 days | 18/07/24 | 18/07/24 | 0 days | -1 day | 0 days | SI Test |  | 6 | Yes
6 | 1.4.3.1.1.4 |  |  |  |  | Update E2E Sandbox guidance to reflect CR55 | 0% | 13/01/25 | 20/02/25 | 29 days | 13/01/25 | 20/02/25 | 0 days | 0 days | 29 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.1.5 |  |  |  |  | Internal SI review | 0% | 21/02/25 | 27/02/25 | 5 days | 21/02/25 | 27/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.1.6 |  |  |  |  | SRO / Code Bodies review | 0% | 28/02/25 | 06/03/25 | 5 days | 28/02/25 | 06/03/25 | 0 days | 0 days | 5 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.1.7 |  |  |  |  | Submit version to QWG | 0% | 07/03/25 | 11/03/25 | 3 days | 07/03/25 | 11/03/25 | 0 days | 0 days | 3 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.1.8 |  |  |  |  | Artefact Approval (via QWG) | 0% | 11/03/25 | 11/03/25 | 0 days | 11/03/25 | 11/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.1.9 |  |  |  |  | Final Document updates post QWG review | 0% | 13/03/25 | 13/03/25 | 1 day | 13/03/25 | 13/03/25 | 0 days | 0 days | 1 day | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.1.10 |  |  |  |  | Submit final version to QAG | 0% | 17/03/25 | 17/03/25 | 1 day? | 17/03/25 | 17/03/25 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.1.11 |  |  |  |  | E2E Sandbox guidance update approved | 0% | 24/03/25 | 24/03/25 | 1 day? | 24/03/25 | 24/03/25 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
5 | 1.4.3.1.2 |  |  | SITAG |  | E2E Sandbox Test Data Approach & Plan | 0% | 13/01/25 | 16/04/25 | 68 days | 05/12/23 | 09/05/24 | 289 days | 244 days | -25 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.2.1 |  |  |  |  | Develop document | 0% | 13/01/25 | 18/02/25 | 27 days | 13/01/25 | 18/02/25 | 0 days | 0 days | -41 days | SI Test |  | 5 | Yes
6 | 1.4.3.1.2.2 |  |  |  |  | Internal SI review and updates | 0% | 19/02/25 | 25/02/25 | 5 days | 19/02/25 | 25/02/25 | 0 days | 0 days | 5 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.2.3 |  |  |  |  | SRO / Code Bodies review | 0% | 26/02/25 | 04/03/25 | 5 days | 26/02/25 | 04/03/25 | 0 days | 0 days | 5 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.2.4 |  |  |  |  | Submit proposed version to QWG | 0% | 04/03/25 | 04/03/25 | 0 days | 04/03/25 | 04/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.2.5 |  |  |  |  | Discuss document at QWG | 0% | 11/03/25 | 11/03/25 | 0 days | 11/03/25 | 11/03/25 | 1 day | 0 days | 0 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.2.6 |  |  |  |  | Final updates prior to consultation | 0% | 12/03/25 | 17/03/25 | 4 days | 12/03/25 | 17/03/25 | 0 days | 0 days | 4 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.2.7 |  |  |  |  | Industry Consultation for E2E Sandbox Test Data Approach and Plan document | 0% | 18/03/25 | 31/03/25 | 10 days | 18/03/25 | 31/03/25 | 0 days | 0 days | 10 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.2.8 |  |  |  |  | Document updates post Industry Consultation | 0% | 01/04/25 | 03/04/25 | 3 days | 01/04/25 | 03/04/25 | 0 days | 0 days | 3 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.2.9 |  |  |  |  | Submit Proposed Version to QWG | 0% | 04/04/25 | 08/04/25 | 3 days | 04/04/25 | 08/04/25 | 0 days | 0 days | 3 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.2.10 |  |  |  |  | Artefact Approval (via QWG) | 0% | 08/04/25 | 08/04/25 | 0 days | 08/04/25 | 08/04/25 | 1 day | 0 days | 0 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.2.11 |  |  |  |  | Final Document updates post QWG review | 0% | 09/04/25 | 09/04/25 | 0 days | 09/04/25 | 09/04/25 | 1 day | 0 days | 0 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.2.12 |  |  |  |  | Submit final version to QAG | 0% | 10/04/25 | 10/04/25 | 0 days | 10/04/25 | 10/04/25 | 1 day | 0 days | 0 days | SI Test |  | 6.1 | Yes
6 | 1.4.3.1.2.13 | T3 | T3-QU-0124 | SITAG |  | E2E Sandbox Test Data Approach and Plan | 0% | 16/04/25 | 16/04/25 | 0 days | 16/04/25 | 16/04/25 | 1 day | 0 days | 0 days | SI Test |  | 6.1 | Yes
4 | 1.4.3.2 |  |  |  |  | UIT Stub Specification and Delivery | 100% | 04/12/23 | 29/11/24 | 260 days | 04/12/23 | 18/10/24 | 0 days | 30 days | 70 days | N/A |  | 5 | Yes
5 | 1.4.3.2.1 |  |  |  |  | Qualification Test Stubs | 100% | 04/12/23 | 29/11/24 | 260 days | 04/12/23 | 18/10/24 | 0 days | 30 days | 70 days | N/A |  | 5.16 | Yes
6 | 1.4.3.2.1.1 |  |  |  |  | Specify | 100% | 04/12/23 | 01/02/24 | 44 days | 04/12/23 | 01/02/24 | 0 days | 0 days | 0 days | SI DevOps |  | 5 | Yes
6 | 1.4.3.2.1.2 |  |  |  |  | Build & Test | 100% | 02/02/24 | 16/08/24 | 141 days | 02/02/24 | 16/08/24 | 0 days | 0 days | 0 days | SI DevOps |  | 5.23 | Yes
6 | 1.4.3.2.1.3 |  |  |  |  | Prepare for release | 100% | 19/08/24 | 29/11/24 | 75 days | 19/08/24 | 29/11/24 | 0 days | 0 days | 70 days | SI DevOps |  | 5 | Yes
6 | 1.4.3.2.1.4 | T3 | T3-TE-0035 | QAG | MHHS-ART080 | Non-SIT LDSO Test Harness Released | 100% | 29/11/24 | 29/11/24 | 0 days | 29/11/24 | 29/11/24 | 1 day | 0 days | 0 days | SI DevOps |  | 5.27 | Yes
4 | 1.4.3.3 |  |  |  |  | Environments (UIT) | 50% | 31/10/22 | 06/06/25 | 680 days | 31/10/22 | 04/07/25 | 0 days | -20 days | 0 days | N/A |  | 5 | Yes
5 | 1.4.3.3.1 |  |  |  |  | Central Party (Avanade) Environments (UIT) | 100% | 16/11/22 | 27/09/24 | 488 days | 16/11/22 | 27/09/24 | 0 days | 0 days | -5 days | N/A |  | 5.28 | Yes
6 | 1.4.3.3.1.1 |  |  |  |  | Central Party (Avandae) environment preparation (incl. security certificates and security compliance) | 100% | 16/11/22 | 01/08/24 | 447 days | 16/11/22 | 01/08/24 | 0 days | 0 days | -16 days | PP |  | 5.28 | Yes
6 | 1.4.3.3.1.2 |  |  |  |  | Submit self-declaration of environment preparation complete (incl. security certificates and security compliance) to Programme for assurance | 100% | 16/11/22 | 01/08/24 | 447 days | 16/11/22 | 01/08/24 | 0 days | 0 days | -16 days | PP |  | 5.28 | Yes
6 | 1.4.3.3.1.3 |  |  |  |  | Central Party (Avanade) UIT environment connectivity proving | 100% | 26/08/24 | 27/09/24 | 25 days | 26/08/24 | 27/09/24 | 0 days | 0 days | 0 days | PP |  | 5.28 | Yes
6 | 1.4.3.3.1.4 |  |  |  |  | Deployment of MHHS solution code to UIT environments | 100% | 29/07/24 | 30/07/24 | 2 days | 29/07/24 | 30/07/24 | 0 days | 0 days | -8 days | PP |  | 5.28 | Yes
6 | 1.4.3.3.1.5 |  |  |  |  | Central Party (Avanade) UIT environment Regression Testing | 100% | 31/07/24 | 31/07/24 | 1 day | 31/07/24 | 31/07/24 | 0 days | 0 days | -9 days | PP |  | 5.28 | Yes
5 | 1.4.3.3.2 |  |  |  |  | E2E Sandbox Participants (UIT) | 0% | 31/10/22 | 06/06/25 | 680 days | 31/10/22 | 06/06/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.4.3.3.2.1 |  |  |  |  | E2E Sandbox Participants environment preparation (incl. security certificates and security compliance) | 0% | 31/10/22 | 09/05/25 | 660 days | 31/10/22 | 09/05/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.4.3.3.2.2 |  |  |  |  | Submit self-declaration of environment preparation complete (incl. security certificates and security compliance) to Programme for assurance | 0% | 31/10/22 | 09/05/25 | 660 days | 31/10/22 | 09/05/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.4.3.3.2.3 |  |  |  |  | E2E Sandbox Participants UIT environment connectivity proving | 0% | 12/05/25 | 06/06/25 | 20 days | 12/05/25 | 06/06/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.4.3.3.2.4 |  |  |  |  | Deployment of MHHS solution code to UIT environments | 0% | 26/05/25 | 06/06/25 | 10 days | 26/05/25 | 06/06/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.4.3.3.2.5 |  |  |  |  | Coordinate E2E Sandbox Participants' UIT environment preparation (for E2E Sandbox Testing Start) | 0% | 31/10/22 | 07/08/24 | 463 days | 31/10/22 | 07/08/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
5 | 1.4.3.3.3 |  |  |  |  | SI Environments (UIT) | 99% | 16/11/22 | 30/09/24 | 489 days | 16/11/22 | 04/07/25 | 0 days | -199 days | -191 days | N/A |  | 5 | Yes
6 | 1.4.3.3.3.1 |  |  |  |  | Coordinate Central Parties' UIT environment preparation | 100% | 16/11/22 | 01/08/24 | 447 days | 16/11/22 | 01/08/24 | 0 days | 0 days | -16 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.3.2 |  |  |  |  | Assure Central Parties' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 97% | 16/11/22 | 23/08/24 | 463 days | 16/11/22 | 23/08/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.3.3 | T3 | T3-TE-0044 | QAG |  | Central Parties' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 100% | 23/08/24 | 23/08/24 | 0 days | 23/08/24 | 23/08/24 | 1 day | 0 days | 0 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.3.4 |  |  |  |  | Coordinate Central Parties' UIT environment connectivity proving | 100% | 26/08/24 | 30/09/24 | 26 days | 26/08/24 | 30/09/24 | 0 days | 0 days | 7 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.3.5 |  |  |  |  | Coordinate deployment of MHHS solution code to Central Parties' UIT environments | 100% | 29/07/24 | 30/07/24 | 2 days | 29/07/24 | 30/07/24 | 0 days | 0 days | -8 days | SI Test |  | 5 | Yes
6 | 1.4.3.3.3.6 |  |  |  |  | Coordinate Central Parties' UIT environment Regression Testing | 0% | 31/07/24 | 31/07/24 | 1 day | 31/07/24 | 31/07/24 | 0 days | 0 days | -9 days | SI Test |  | 5 | Yes
4 | 1.4.3.4 |  |  |  |  | Test Data | 0% | 26/08/24 | 04/10/24 | 30 days | 26/08/24 | 04/10/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
5 | 1.4.3.4.1 |  |  |  |  | Central Parties (for E2E Sandbox & Qualification) | 0% | 26/08/24 | 04/10/24 | 30 days | 26/08/24 | 04/10/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
6 | 1.4.3.4.1.1 |  |  |  |  | Central Parties' UIT environment test data loading & verification (& data cleansing, if required) | 0% | 26/08/24 | 04/10/24 | 30 days | 26/08/24 | 04/10/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
6 | 1.4.3.4.1.2 |  |  |  |  | Submit self-declaration to Programme to confirm loading & verification of test data | 0% | 26/08/24 | 04/10/24 | 30 days | 26/08/24 | 04/10/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
5 | 1.4.3.4.2 |  |  |  |  | E2E Sandbox Participants | 0% | 26/08/24 | 04/10/24 | 30 days | 26/08/24 | 04/10/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
6 | 1.4.3.4.2.1 |  |  |  |  | UIT environment test data loading and verification (and data cleansing, if required) (for E2E Sandbox Testing Start) | 0% | 26/08/24 | 04/10/24 | 30 days | 26/08/24 | 04/10/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
5 | 1.4.3.4.3 |  |  |  |  | SI Test Data | 0% | 26/08/24 | 04/10/24 | 30 days | 26/08/24 | 04/10/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
6 | 1.4.3.4.3.1 |  |  |  |  | Coordinate Central Parties' UIT environment test data loading and verification (and data cleansing, if required) | 0% | 26/08/24 | 04/10/24 | 30 days | 26/08/24 | 04/10/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
6 | 1.4.3.4.3.2 |  |  |  |  | Assure evidence of Central Parties' UIT environment test data load and verification | 0% | 26/08/24 | 04/10/24 | 30 days | 26/08/24 | 04/10/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
6 | 1.4.3.4.3.3 |  |  |  |  | Coordinate E2E Sandbox Participants' UIT environment test data loading and verification (and data cleansing, if required) (for E2E Sandbox Testing Start) | 0% | 26/08/24 | 04/10/24 | 30 days | 26/08/24 | 04/10/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
4 | 1.4.3.5 |  |  |  |  | Other Preparation | 59% | 31/10/22 | 23/09/24 | 496 days | 31/10/22 | 23/09/24 | 0 days | 0 days | 12 days | N/A |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
5 | 1.4.3.5.1 |  |  |  |  | SI Other Preparation | 0% | 31/10/22 | 30/01/23 | 66 days | 31/10/22 | 30/01/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
6 | 1.4.3.5.1.1 |  |  |  |  | Onboarding of UIT E2E Sandbox Participants to Test Management Tool for E2E Sandbox Testing Start (onboarding of participants will be ongoing hereafter) | 0% | 31/10/22 | 30/01/23 | 66 days | 31/10/22 | 30/01/23 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
5 | 1.4.3.5.2 |  |  |  |  | Other Preparation (for Central Parties & E2E Sandbox Participants) | 67% | 16/11/22 | 23/09/24 | 484 days | 16/11/22 | 23/09/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
6 | 1.4.3.5.2.1 |  |  |  |  | Test Management Tool onboarding for E2E Sandbox Testing Start (onboarding will be ongoing hereafter) | 0% | 02/05/24 | 01/08/24 | 66 days | 02/05/24 | 01/08/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
6 | 1.4.3.5.2.2 |  |  |  |  | Other Preparation (incl. test execution planning) | 76% | 16/11/22 | 23/09/24 | 484 days | 16/11/22 | 23/09/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
4 | 1.4.3.6 |  |  |  |  | UIT E2E Sandbox Test Readiness Report | 0% | 26/08/24 | 31/01/25 | 114 days | 26/08/24 | 31/01/25 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
5 | 1.4.3.6.1 |  |  |  |  | Central Parties E2E Sandbox Test Readiness Report | 0% | 26/08/24 | 04/10/24 | 30 days | 26/08/24 | 04/10/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
6 | 1.4.3.6.1.1 |  |  |  |  | Develop draft Test Readiness Report and submit to Programme for assurance | 0% | 26/08/24 | 20/09/24 | 20 days | 26/08/24 | 20/09/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
6 | 1.4.3.6.1.2 |  |  |  |  | Finalise Test Readiness Report and submit to Programme for assurance | 0% | 23/09/24 | 04/10/24 | 10 days | 23/09/24 | 04/10/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
5 | 1.4.3.6.2 |  |  |  |  | SI E2E Sandbox Test Readiness Report | 0% | 26/08/24 | 18/10/24 | 40 days | 26/08/24 | 18/10/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
6 | 1.4.3.6.2.1 |  |  |  |  | Assure Central Parties' E2E Sandbox Test Readiness Reports | 0% | 26/08/24 | 11/10/24 | 35 days | 26/08/24 | 11/10/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
6 | 1.4.3.6.2.2 |  |  |  |  | Develop Overarching E2E Sandbox Test Readiness Report | 0% | 16/09/24 | 11/10/24 | 20 days | 16/09/24 | 11/10/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
6 | 1.4.3.6.2.3 |  |  |  |  | Artefact review (via SITAG) and updates | 0% | 14/10/24 | 18/10/24 | 5 days | 14/10/24 | 18/10/24 | 0 days | 0 days | 0 days | SI Test |  | 5 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
5 | 1.4.3.6.3 | T3 | T3-TE-0048 | QAG | MHHS-ART154 MHHS-ART147 | UIT E2E Sandbox Preparation Complete | 0% | 31/01/25 | 31/01/25 | 0 days | 31/01/25 | 31/01/25 | 0 days | -1 day | 0 days | SI Test |  | 5.28 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
3 | 1.4.4 |  |  |  |  | Sandbox Testing Execution (UIT) | 0% | 01/09/25 | 28/08/26 | 260 days | 07/02/25 | 24/04/26 | 146 days | 90 days | -56 days | N/A |  | 6.15 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
4 | 1.4.4.1 | T3 | T3-TE-0049 | QAG | MHHS-ART018 MHHS-ART154 MHHS-ART147 | Sandbox Testing Start (UIT) | 0% | 01/09/25 | 01/09/25 | 0 days | 01/09/25 | 01/09/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
4 | 1.4.4.2 |  |  |  |  | Sandbox Testing Execution (UIT) | 0% | 01/09/25 | 28/08/26 | 260 days | 01/09/25 | 28/08/26 | 0 days | 0 days | -56 days | PP |  | 6.15 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
4 | 1.4.4.3 |  | T3-TE-XXXX |  |  | Sandbox Testing End (UIT) | 0% | 28/08/26 | 28/08/26 | 0 days | 28/08/26 | 28/08/26 | 1 day | 0 days | 0 days |  |  | 6.15 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
3 | 1.4.5 |  |  |  |  | SIT PPs Early Sandbox Testing Execution (SIT-A) | 0% | 08/08/25 | 24/10/25 | 56 days | 07/02/25 | 24/04/26 | 130 days | -130 days | -260 days | N/A |  | 6.15 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
4 | 1.4.5.1 | T3 | T3-TE-0049 | QAG | MHHS-ART018 MHHS-ART154 MHHS-ART147 | SIT PPs E2E Sandbox Testing Start | 0% | 08/08/25 | 08/08/25 | 0 days | 08/08/25 | 08/08/25 | 1 day | 0 days | 0 days | SI Test |  | 6.15 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
4 | 1.4.5.2 |  |  |  |  | SIT PPs E2E Sandbox Testing Execution | 0% | 08/08/25 | 24/10/25 | 56 days | 07/02/25 | 24/04/26 | 130 days | -130 days | -260 days | PP |  | 6.15 | Yes |  | 14/01/25 - Programme is working on updating these dates over the coming weeks.
3 | 1.4.6 |  |  | SITAG |  | System Integration Testing - Tier 1 Milestones | 0% | 28/02/25 | 24/12/25 | 214 days? | 28/02/25 | 24/12/25 | 0 days | 0 days | 214 days? |  |  | 6.15 | Yes
4 | 1.4.6.1 | T3 | T3-MI-0040 | SITAG |  | M10 Checkpoint | 0% | 28/02/25 | 28/02/25 | 1 day? | 28/02/25 | 28/02/25 | 0 days | 0 days | 1 day? | SI Test |  | 6.1 | Yes
4 | 1.4.6.2 | T1 | T1-MI-1000 | PSG |  | Central systems ready for migrating MPANs (M10) | 0% | 24/09/25 | 24/09/25 | 0 days | 24/09/25 | 24/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.1 | Yes
4 | 1.4.6.3 | T1 | T2-MI-1500 | PSG |  | Central systems ready for migrating MPANs (M10*) - Late Exit | 0% | 24/12/25 | 24/12/25 | 0 days | 24/12/25 | 24/12/25 | 1 day | 0 days | 0 days | CPT |  | 6.1 | Yes
3 | 1.4.7 |  |  |  |  | External Programme Dependency Management | 100% | 31/10/22 | 30/06/23 | 174 days | 31/10/22 | 30/06/23 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
4 | 1.4.7.1 |  |  |  |  | BSC CP1558 | 100% | 31/10/22 | 29/06/23 | 173 days | 31/10/22 | 29/06/23 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
5 | 1.4.7.1.1 |  |  |  |  | Monitor progress to implementation date | 100% | 31/10/22 | 28/06/23 | 173 days | 31/10/22 | 28/06/23 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
5 | 1.4.7.1.2 |  |  |  |  | BSC CP1558 Implementation Date | 100% | 29/06/23 | 29/06/23 | 0 days | 29/06/23 | 29/06/23 | 0 days | -1 day | 0 days | Code Bodies |  | 5 | Yes
4 | 1.4.7.2 |  |  |  |  | REC CP R0032 | 100% | 31/10/22 | 30/06/23 | 174 days | 31/10/22 | 30/06/23 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
5 | 1.4.7.2.1 |  |  |  |  | Monitor progress to implementation date | 100% | 31/10/22 | 29/06/23 | 174 days | 31/10/22 | 29/06/23 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
5 | 1.4.7.2.2 |  |  |  |  | REC CP R0032 Implementation Date | 100% | 30/06/23 | 30/06/23 | 0 days | 30/06/23 | 30/06/23 | 0 days | -1 day | 0 days | Code Bodies |  | 5 | Yes
4 | 1.4.7.3 |  |  |  |  | REC CP R0044 | 100% | 31/10/22 | 29/06/23 | 173 days | 31/10/22 | 29/06/23 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
5 | 1.4.7.3.1 |  |  |  |  | Monitor progress to implementation date | 100% | 31/10/22 | 28/06/23 | 173 days | 31/10/22 | 28/06/23 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
5 | 1.4.7.3.2 |  |  |  |  | REC CP R0044 Implementation Date | 100% | 29/06/23 | 29/06/23 | 0 days | 29/06/23 | 29/06/23 | 0 days | -1 day | 0 days | Code Bodies |  | 5 | Yes
2 | 1.5 |  |  | QAG |  | NON SIT LDSO QUALIFICATION | 65% | 07/11/23 | 19/09/25 | 489 days? | 07/11/23 | 22/08/25 | 0 days | 20 days | 146 days? | N/A |  |  | Yes
3 | 1.5.1 |  |  |  |  | Approach Planning | 100% | 07/11/23 | 22/08/24 | 208 days | 07/11/23 | 22/08/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
4 | 1.5.1.1 |  |  |  |  | Develop Draft Testing Approach & Plan | 100% | 07/11/23 | 30/01/24 | 61 days | 07/11/23 | 30/01/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.1.2 |  |  |  |  | Draft Testing Approach & Plan Issued to LDSO for Review | 100% | 31/01/24 | 31/01/24 | 1 day | 31/01/24 | 31/01/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.1.3 |  |  |  |  | LDSO Review Complete | 100% | 01/02/24 | 14/02/24 | 10 days | 01/02/24 | 14/02/24 | 0 days | 0 days | 0 days | LDSOs |  | 5.24 | Yes
4 | 1.5.1.4 |  |  |  |  | Update Following LDSO Review | 100% | 15/02/24 | 05/03/24 | 14 days | 15/02/24 | 05/03/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.1.5 |  |  |  |  | QWG Review of Approach & Plan | 100% | 12/03/24 | 12/03/24 | 1 day | 12/03/24 | 12/03/24 | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.24 | Yes
4 | 1.5.1.6 |  |  |  |  | QAG Approval for Approach & Plan | 100% | 21/03/24 | 21/03/24 | 0 days | 21/03/24 | 21/03/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
4 | 1.5.1.7 | T3 | T3-QU-0011 | QAG (Non-SIT LDSO) |  | Confirmation of Participants for Non-SIT LDSO Qualification Testing | 100% | 21/03/24 | 21/03/24 | 0 days | 21/03/24 | 21/03/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.1.8 |  |  |  |  | Update to Annex 1 for internal review (NF, Not Operational) | 100% | 18/03/24 | 05/04/24 | 15 days | 18/03/24 | 05/04/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.1.9 |  |  |  |  | Non-Functional, Operational & Migration Approaches Socialised with Code Bodies & LDSO & Feedback Actioned | 100% | 08/04/24 | 05/08/24 | 86 days | 08/04/24 | 05/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.27 | Yes
4 | 1.5.1.10 |  |  |  |  | QWG Review Operational, Non-Functional & Migration Annexes of Approach & Plan | 100% | 13/08/24 | 13/08/24 | 1 day | 13/08/24 | 13/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.27 | Yes
4 | 1.5.1.11 |  |  |  |  | Update Following QWG Review | 100% | 14/08/24 | 21/08/24 | 6 days | 14/08/24 | 21/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.27 | Yes
4 | 1.5.1.12 | T3 | T3-QU-0110 | QAG (Non-SIT LDSO) |  | QAG Approval for Operational, Non-Functional & Migration Annexes of Approach & Plan | 100% | 22/08/24 | 22/08/24 | 0 days | 22/08/24 | 22/08/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.29 | Yes
3 | 1.5.2 |  |  |  |  | Functional Test Cases & Scenarios | 100% | 30/01/24 | 18/04/24 | 58 days | 30/01/24 | 18/04/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
4 | 1.5.2.1 |  |  |  |  | Functional Test Cases & Scenarios Batch 1 | 100% | 30/01/24 | 08/02/24 | 8 days | 30/01/24 | 08/02/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.5.2.1.1 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 1 with Code Bodies | 100% | 30/01/24 | 30/01/24 | 1 day | 30/01/24 | 30/01/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.1.2 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 1 with LDSO | 100% | 01/02/24 | 01/02/24 | 1 day | 01/02/24 | 01/02/24 | 0 days | 0 days | 0 days | LDSO, Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.1.3 |  |  |  |  | Action Feedback on Test Cases & Scenarios Batch 1 | 100% | 02/02/24 | 08/02/24 | 5 days | 02/02/24 | 08/02/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.2.2 |  |  |  |  | Functional Test Cases & Scenarios Batch 2 | 100% | 20/02/24 | 08/03/24 | 14 days | 20/02/24 | 08/03/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.5.2.2.1 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 2 with Code Bodies | 100% | 20/02/24 | 20/02/24 | 1 day | 20/02/24 | 20/02/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.2.2 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 2 with LDSO | 100% | 01/03/24 | 01/03/24 | 1 day | 01/03/24 | 01/03/24 | 0 days | 0 days | 0 days | LDSO, Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.2.3 |  |  |  |  | Action Feedback on Test Cases & Scenarios Batch 2 | 100% | 04/03/24 | 08/03/24 | 5 days | 04/03/24 | 08/03/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.2.3 |  |  |  |  | Functional Test Cases & Scenarios Batch 3 | 100% | 20/03/24 | 05/04/24 | 13 days | 20/03/24 | 05/04/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.5.2.3.1 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 3 with Code Bodies | 100% | 20/03/24 | 20/03/24 | 1 day | 20/03/24 | 20/03/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.3.2 |  |  |  |  | Walkthrough Test Cases & Scenarios Batch 3 with LDSO | 100% | 28/03/24 | 28/03/24 | 1 day | 28/03/24 | 28/03/24 | 0 days | 0 days | 0 days | LDSO, Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.2.3.3 |  |  |  |  | Action Feedback on Test Cases & Scenarios Batch 3 | 100% | 29/03/24 | 05/04/24 | 6 days | 29/03/24 | 05/04/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.2.4 |  |  |  |  | Test Cases & Scenarios Batch 1-3 Discussion at QWG | 100% | 09/04/24 | 09/04/24 | 1 day | 09/04/24 | 09/04/24 | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.24 | Yes
4 | 1.5.2.5 |  |  |  |  | Action QWG Feedback on Test Cases & Scenarios Batch 1-3 | 100% | 10/04/24 | 11/04/24 | 2 days | 10/04/24 | 11/04/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.2.6 | T3 | T3-QU-0069 | QAG (Non-SIT LDSO) |  | Batch 1-3 Non-SIT LDSO QT Functional Test Scenarios and Test Cases approved | 100% | 18/04/24 | 18/04/24 | 0 days | 18/04/24 | 18/04/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
3 | 1.5.3 |  |  |  |  | Test Execution Schedule | 100% | 19/04/24 | 29/11/24 | 161 days | 19/04/24 | 29/11/24 | 0 days | 0 days | 71 days | N/A |  | 5.24 | Yes
4 | 1.5.3.1 |  |  |  |  | Draft Test Delivery Schedule for Functional and Operational Testing | 100% | 19/04/24 | 16/05/24 | 20 days | 19/04/24 | 16/05/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.3.2 |  |  |  |  | Socialise Test Delivery Schedule with Code Bodies & LDSO for Review & Action Feedback | 100% | 17/05/24 | 08/07/24 | 37 days | 17/05/24 | 08/07/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.3.3 |  |  |  |  | Agree Test Execution Timetable Format at QWG, Including Anonymisation Requirements | 100% | 09/07/24 | 09/07/24 | 1 day | 09/07/24 | 09/07/24 | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.24 | Yes
4 | 1.5.3.4 |  |  |  |  | Action QWG Feedback | 100% | 10/07/24 | 12/07/24 | 3 days | 10/07/24 | 12/07/24 | 0 days | 0 days | 0 days | Non-SIT LDSO, PP |  | 5.24 | Yes
4 | 1.5.3.5 | T3 | T3-QU-0111 | QAG (Non-SIT LDSO) |  | Agree Test Execution Timetable Format at QAG, Including Anonymisation Requirements | 100% | 18/07/24 | 18/07/24 | 0 days | 18/07/24 | 18/07/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.29 | Yes
4 | 1.5.3.6 | T3 | T3-QU-0008 | QAG (Non-SIT LDSO) |  | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test Execution Schedule Complete | 100% | 29/11/24 | 29/11/24 | 0 days | 29/11/24 | 29/11/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.29 | Yes
3 | 1.5.4 |  |  |  |  | Functional, Non-Functional, Operational & Migration Test Scenarios & Cases | 100% | 22/03/24 | 22/08/24 | 110 days | 22/03/24 | 22/08/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
4 | 1.5.4.1 |  |  |  |  | Test Scenarios & Cases - Functional - Drafted, Reviewed | 100% | 01/04/24 | 18/04/24 | 14 days | 01/04/24 | 18/04/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.2 | T3 | T3-QU-0070 | QAG (Non-SIT LDSO) |  | Test Scenarios & Cases- Functional - Approved at QAG | 100% | 18/04/24 | 18/04/24 | 0 days | 18/04/24 | 18/04/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.3 |  |  |  |  | Test Scenarios & Cases - Non-Functional - Drafted, Reviewed | 100% | 22/03/24 | 22/08/24 | 110 days | 22/03/24 | 22/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.4 | T3 | T3-QU-0071 | QAG (Non-SIT LDSO) |  | Test Scenarios & Cases - Non-Functional - Approved at QAG | 100% | 22/08/24 | 22/08/24 | 0 days | 22/08/24 | 22/08/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.29 | Yes
4 | 1.5.4.5 |  |  |  |  | Test Scenarios & Cases - Migration - Drafted, Reviewed | 100% | 22/03/24 | 23/05/24 | 45 days | 22/03/24 | 23/05/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.6 | T3 | T3-QU-0072 | QAG (Non-SIT LDSO) |  | Test Scenarios & Cases - Migration - Approved at QAG | 100% | 23/05/24 | 23/05/24 | 0 days | 23/05/24 | 23/05/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.7 |  |  |  |  | Test Scenarios & Cases - Operational - Drafted, Reviewed | 100% | 03/06/24 | 22/08/24 | 59 days | 03/06/24 | 22/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.4.8 | T3 | T3-QU-0073 | QAG (Non-SIT LDSO) |  | Test Scenarios & Cases - Operational - Approved at QAG | 100% | 22/08/24 | 22/08/24 | 0 days | 22/08/24 | 22/08/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.29 | Yes
3 | 1.5.5 |  |  |  |  | Test Data | 65% | 22/01/24 | 16/05/25 | 345 days | 22/01/24 | 16/05/25 | 0 days | 0 days | 104 days | N/A |  | 5.24 | Yes
4 | 1.5.5.1 |  |  |  |  | Test Data Plan Drafted & Reviewed | 100% | 22/01/24 | 23/05/24 | 89 days | 22/01/24 | 23/05/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
4 | 1.5.5.2 | T3 | T3-QU-0074 | QAG (Non-SIT LDSO) |  | Non-SIT LDSO QT Test Data Plan Approved by QAG | 100% | 23/05/24 | 23/05/24 | 0 days | 23/05/24 | 23/05/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
4 | 1.5.5.3 |  |  |  |  | Develop Test Data Matrices | 100% | 24/05/24 | 06/06/24 | 10 days | 24/05/24 | 06/06/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.5.4 |  |  |  |  | Test Data Cut | 100% | 24/05/24 | 17/06/24 | 17 days | 24/05/24 | 17/06/24 | 0 days | 0 days | 0 days | PP, Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.5.5 | T3 | T3-QU-0112 | QAG (Non-SIT LDSO) |  | Test Data Cut Complete | 100% | 17/06/24 | 17/06/24 | 0 days | 17/06/24 | 17/06/24 | 1 day | 0 days | 0 days | PP, Non-SIT LDSO |  | 5.27 | Yes
4 | 1.5.5.6 |  |  |  |  | Test Data Reviewed by the Programme | 100% | 18/06/24 | 09/08/24 | 39 days | 18/06/24 | 09/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.5.7 |  |  |  |  | Test Data Loaded | 90% | 12/08/24 | 06/12/24 | 85 days | 12/08/24 | 06/12/24 | 0 days | 0 days | 68 days | Non-SIT LDSO |  | 5.24 | Yes |  | 03/12/24 - Data load is continuing in support of test readiness assessments but additional support has been required by some LDSOs to load some data elements. LDSOs are clear that approved data is a condition of test readiness approval.
4 | 1.5.5.8 | T3 | T3-QU-0113 | QAG (Non-SIT LDSO) |  | Test Data Signed Off | 0% | 06/12/24 | 06/12/24 | 0 days | 06/12/24 | 06/12/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.25 | Yes |  | 08/01/25 - This activity will be signed off by Nic Farley, after assurance is given by Paul Morgan that the test data recieve meets our requirements. Data load is continuing in support of test readiness assessments but additional support has been required
4 | 1.5.5.9 |  |  |  |  | Test Execution Data Support | 0% | 09/12/24 | 16/05/25 | 115 days | 09/12/24 | 16/05/25 | 0 days | 0 days | 36 days | Non-SIT LDSO |  | 5.24 | Yes
3 | 1.5.6 |  |  |  |  | Tooling | 100% | 31/01/24 | 23/08/24 | 148 days | 31/01/24 | 23/08/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
4 | 1.5.6.1 |  |  |  |  | Design Approach & Set-Up ADO Tool for Test & Defect Management Tool | 100% | 31/01/24 | 12/04/24 | 53 days | 31/01/24 | 12/04/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.6.2 |  |  |  |  | Develop Training Requirements & Materials Inc. Day in the Life | 100% | 15/04/24 | 13/08/24 | 87 days | 15/04/24 | 13/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.6.3 |  |  |  |  | ADO Launch complete | 100% | 23/08/24 | 23/08/24 | 1 day | 23/08/24 | 23/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
3 | 1.5.7 |  |  |  |  | Pre-Integration Testing | 84% | 31/01/24 | 24/01/25 | 258 days | 31/01/24 | 29/11/24 | 0 days | 40 days | 84 days | N/A |  | 5.24 | Yes
4 | 1.5.7.1 |  |  |  |  | PIT Guidance & Templates & Approach & Plans Developed | 100% | 05/02/24 | 01/07/24 | 106 days | 05/02/24 | 01/07/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.27 | Yes
4 | 1.5.7.2 | T3 | T3-QU-0075 | QAG (Non-SIT LDSO) |  | PIT Test Approach & Plan Deadline for Submission for Non-SIT LDSO​ QT | 100% | 01/07/24 | 01/07/24 | 0 days | 01/07/24 | 01/07/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.28 | Yes
4 | 1.5.7.3 |  |  |  |  | Develop and agree PIT Test Scenarios | 100% | 02/07/24 | 29/07/24 | 20 days | 02/07/24 | 29/07/24 | 0 days | 0 days | -11 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.7.4 |  |  |  |  | PIT Execution (Functional and Migration) | 90% | 30/09/24 | 29/11/24 | 45 days | 30/09/24 | 29/11/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes |  | 09/12/24 - At least one participant has not completed PIT Execution, hence why this is Red. This is not expected to delay testing start.
4 | 1.5.7.5 |  |  |  |  | PIT Execution (Non-Functional and Operational) | 23% | 23/09/24 | 24/01/25 | 90 days | 23/09/24 | 24/01/25 | 0 days | 0 days | 90 days |  | Approved | 5.24 | Yes |  | 21/10/24 - Proposed to add this as a new activity, to go to QAG for approval.
4 | 1.5.7.6 | T3 | T3-QU-0076 | QAG (Non-SIT LDSO) |  | Non-SIT LDSO Participants have submitted functional PIT Test Completion Report & evidence for QT Entry​ | 0% | 29/11/24 | 29/11/24 | 0 days | 29/11/24 | 29/11/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes |  | 09/12/24 - At least one participant has not completed PIT Execution, hence why this is Red. This is not expected to delay testing start.
4 | 1.5.7.7 |  |  |  |  | Non-SIT LDSO Participants have submitted non-functional PIT Test Completion Report | 0% | 24/01/25 | 24/01/25 | 0 days | 27/01/25 | 27/01/25 | 0 days | -1 day | 0 days |  | Approved | 5.24 | Yes |  | 21/10/24 - Proposed to add this as a new activity, to go to QAG for approval.
4 | 1.5.7.8 |  |  |  |  | Placing Reliance - Code Body & LDSO Functional and Migration | 100% | 31/01/24 | 22/08/24 | 147 days | 31/01/24 | 22/08/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.5.7.8.1 |  |  |  |  | Placing Reliance Submitted & Reviewed | 100% | 31/01/24 | 28/02/24 | 21 days | 31/01/24 | 28/02/24 | 0 days | 0 days | 0 days | LDSO, Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.7.8.2 |  |  |  |  | Define & Agree QT Testing for Each LDSO | 100% | 29/02/24 | 29/03/24 | 22 days | 29/02/24 | 29/03/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.7.8.3 |  |  |  |  | Develop Test Scope & Reliance Submissions | 100% | 01/04/24 | 26/04/24 | 20 days | 01/04/24 | 26/04/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
5 | 1.5.7.8.4 |  |  |  |  | Review and Consultation | 100% | 29/04/24 | 22/08/24 | 84 days | 29/04/24 | 22/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.27 | Yes
4 | 1.5.7.9 |  |  |  |  | Placing Reliance - Code Body & LDSO Non Functional and Operational | 100% | 17/06/24 | 22/08/24 | 49 days | 17/06/24 | 22/08/24 | 0 days | 0 days | 0 days | N/A |  | 5.25 | Yes
5 | 1.5.7.9.1 |  |  |  |  | Placing Reliance Submitted & Reviewed | 100% | 17/06/24 | 30/07/24 | 32 days | 17/06/24 | 30/07/24 | 0 days | 0 days | 0 days | LDSO, Non-SIT LDSO |  | 5.27 | Yes
5 | 1.5.7.9.2 |  |  |  |  | Review and Consultation | 100% | 31/07/24 | 22/08/24 | 17 days | 31/07/24 | 22/08/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.27 | Yes
5 | 1.5.7.9.3 | T3 | T3-QU-0077 | QAG (Non-SIT LDSO) |  | PP Test Scope Presented at QAG | 100% | 22/08/24 | 22/08/24 | 0 days | 22/08/24 | 22/08/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.29 | Yes
3 | 1.5.8 |  |  |  |  | LDSO Test Readiness Reporting | 100% | 19/04/24 | 26/07/24 | 71 days | 19/04/24 | 26/07/24 | 0 days | 0 days | -47 days | N/A |  | 5.24 | Yes
4 | 1.5.8.1 |  |  |  |  | Interim Test Readiness Report & Plan Developed & Reviewed | 100% | 19/04/24 | 26/07/24 | 71 days | 19/04/24 | 26/07/24 | 0 days | 0 days | 0 days | Non-SIT LDSO, LDSO |  | 5.24 | Yes
4 | 1.5.8.2 | T3 | T3-QU-0114 | QAG (Non-SIT LDSO) |  | Test Plan Submission to MHHS Programme For Review | 100% | 26/07/24 | 26/07/24 | 0 days | 26/07/24 | 26/07/24 | 1 day | 0 days | 0 days | LDSO |  | 5.3 | Yes
3 | 1.5.9 |  |  |  |  | Test Environment | 100% | 17/04/24 | 29/11/24 | 163 days | 17/04/24 | 29/11/24 | 0 days | 0 days | 52 days | N/A |  | 5.24 | Yes
4 | 1.5.9.1 |  |  |  |  | Define Test Harness Requirements and Sign-Off with SRO | 100% | 17/04/24 | 03/05/24 | 13 days | 17/04/24 | 03/05/24 | 0 days | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.9.2 |  |  |  |  | Central System (DIP Env & Helix Test Harness) Test Environment DBT | 100% | 17/04/24 | 29/11/24 | 163 days | 17/04/24 | 29/11/24 | 0 days | 0 days | 71 days | LDSO |  | 5.24 | Yes
4 | 1.5.9.3 |  |  |  |  | Coordinate LDSO Environment Preparation | 100% | 12/07/24 | 29/11/24 | 101 days | 12/07/24 | 29/11/24 | 0 days | 0 days | 71 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.9.4 |  |  |  |  | DIP available for Onboarding | 100% | 01/08/24 | 01/08/24 | 1 day | 01/08/24 | 01/08/24 | 0 days | 0 days | 0 days | Test Env |  | 5.24 | Yes
4 | 1.5.9.5 | T3 | T3-QU-0009 | QAG (Non-SIT LDSO) |  | Qualification Testing for Non-SIT LDSOs Participants' environments) Ready to start DIP onboarding (incl. certificates and security compliance) | 100% | 05/08/24 | 05/08/24 | 0 days | 05/08/24 | 05/08/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.3 | Yes
4 | 1.5.9.6 | T3 | T3-QU-0078 | QAG (Non-SIT LDSO) |  | LDSO Test Environments Connection Confirmed to UIT Environment | 100% | 29/11/24 | 29/11/24 | 0 days | 29/11/24 | 29/11/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes
3 | 1.5.10 |  |  |  |  | Test Readiness | 90% | 02/07/24 | 20/12/24 | 124 days | 02/07/24 | 20/12/24 | 0 days | 0 days | 48 days | N/A |  | 5.24 | Yes
4 | 1.5.10.1 |  |  |  |  | Preparation for Interim Test Readiness Report | 100% | 02/07/24 | 26/07/24 | 19 days | 02/07/24 | 26/07/24 | 0 days | 0 days | -11 days | LDSO |  | 5.24 | Yes
4 | 1.5.10.2 | T3 | T3-QU-0116 | QAG (Non-SIT LDSO) |  | Interim Test Readiness Report Submission to MHHS Programme for Review | 100% | 26/07/24 | 26/07/24 | 0 days | 26/07/24 | 26/07/24 | 1 day | 0 days | 0 days | LDSO |  | 5.25 | Yes
4 | 1.5.10.3 |  |  |  |  | LDSO Update Readiness Report & Final Assurance by Programme | 95% | 29/07/24 | 12/12/24 | 99 days | 29/07/24 | 12/12/24 | 0 days | 0 days | 74 days | Non-SIT LDSO, LDSO |  | 5.24 | Yes
4 | 1.5.10.4 |  |  |  |  | Final Test Readiness Report Submitted to MHHS Programme | 0% | 13/12/24 | 13/12/24 | 1 day | 13/12/24 | 13/12/24 | 0 days | 0 days | 0 days | LDSO |  | 5.24 | Yes
4 | 1.5.10.5 |  |  |  |  | Final Programme Assurance of LDSO Test Readiness | 0% | 13/12/24 | 20/12/24 | 6 days | 13/12/24 | 20/12/24 | 0 days | 0 days | -15 days | Non-SIT LDSO |  | 5.24 | Yes
4 | 1.5.10.6 | T3 | T3-QU-0007 | QAG (Non-SIT LDSO) |  | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Programme Test Readiness confirmed | 0% | 20/12/24 | 20/12/24 | 0 days | 20/12/24 | 20/12/24 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 5.24 | Yes |  | 13/01/25 - Milestone RAG'd red because a predecssor activity (T3-QU-0076) is delayed because at least one participant is being delayed, but the factors behind this are internal to them, so not affecting all PPs.
4 | 1.5.10.7 | T2 | T2-QU-0550 | QAG (Non-SIT LDSO) |  | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test Readiness Confirmed (Final Test Readiness Review for LDSO) | 0% | 20/12/24 | 20/12/24 | 0 days | 20/12/24 | 20/12/24 | 1 day | 0 days | 0 days | LDSO |  | 5.24 | Yes |  | 13/01/25 - Milestone RAG'd red because a predecssor activity (T3-QU-0076) is delayed because at least one participant is being delayed, but the factors behind this are internal to them, so not affecting all PPs.
3 | 1.5.11 |  |  | QAG (Non-SIT LDSO) |  | Test Window | 0% | 06/01/25 | 22/08/25 | 165 days? | 06/01/25 | 16/05/25 | 0 days | 70 days | 106 days? | N/A |  | 6 | Yes
4 | 1.5.11.1 |  |  | QAG (Non-SIT LDSO) |  | All Non-SIT LDSOs Qualification Testing | 0% | 06/01/25 | 16/05/25 | 94 days | 06/01/25 | 16/05/25 | 0 days | -1 day | 35 days | LDSO |  | 6 | Yes
5 | 1.5.11.1.1 | T3 | T3-QU-0115 | QAG (Non-SIT LDSO) |  | Non-SIT LDSO QT Test Execution Starts | 100% | 06/01/25 | 06/01/25 | 0 days | 06/01/25 | 06/01/25 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 6 | Yes
5 | 1.5.11.1.2 |  |  | QAG (Non-SIT LDSO) |  | LDSO Alpha | 1% | 06/01/25 | 05/05/25 | 86 days | 06/01/25 | 05/05/25 | 0 days | 0 days | 86 days | LDSO |  | 6.15 | Yes
5 | 1.5.11.1.3 |  |  | QAG (Non-SIT LDSO) |  | LDSO Bravo | 0% | 06/01/25 | 27/03/25 | 59 days | 06/01/25 | 27/03/25 | 0 days | 0 days | 59 days | LDSO |  | 6.15 | Yes
5 | 1.5.11.1.4 |  |  | QAG (Non-SIT LDSO) |  | LDSO Charlie | 0% | 06/01/25 | 07/05/25 | 88 days | 06/01/25 | 07/05/25 | 0 days | 0 days | 88 days | LDSO |  | 6.15 | Yes
5 | 1.5.11.1.5 |  |  | QAG (Non-SIT LDSO) |  | LDSO Delta | 1% | 06/01/25 | 30/04/25 | 83 days | 06/01/25 | 30/04/25 | 0 days | 0 days | 83 days | LDSO |  | 6.15 | Yes
5 | 1.5.11.1.6 |  |  | QAG (Non-SIT LDSO) |  | LDSO Echo | 0% | 06/01/25 | 10/04/25 | 69 days | 06/01/25 | 10/04/25 | 0 days | 0 days | 69 days | LDSO |  | 6.15 | Yes
5 | 1.5.11.1.7 |  |  | QAG (Non-SIT LDSO) |  | LDSO Foxtrot | 0% | 20/01/25 | 20/03/25 | 44 days | 20/01/25 | 20/03/25 | 0 days | 0 days | 44 days | LDSO |  | 6.15 | Yes
5 | 1.5.11.1.8 |  |  | QAG (Non-SIT LDSO) |  | LDSO Golf | 0% | 06/01/25 | 07/04/25 | 66 days | 06/01/25 | 07/04/25 | 0 days | 0 days | 66 days | LDSO |  | 6.15 | Yes
5 | 1.5.11.1.9 |  |  | QAG (Non-SIT LDSO) |  | LDSO Hotel | 1% | 06/01/25 | 07/03/25 | 45 days | 06/01/25 | 07/03/25 | 0 days | 0 days | 45 days | LDSO |  | 6.15 | Yes
5 | 1.5.11.1.10 |  |  | QAG (Non-SIT LDSO) |  | LDSO India | 1% | 06/01/25 | 05/05/25 | 86 days | 06/01/25 | 05/05/25 | 0 days | 0 days | 86 days | LDSO |  | 6.15 | Yes
5 | 1.5.11.1.11 | T3 | T3-QU-0010 | QAG (Non-SIT LDSO) |  | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) 1 End | 0% | 16/05/25 | 16/05/25 | 0 days | 16/05/25 | 16/05/25 | 0 days | -1 day | 0 days | LDSO |  | 6 | Yes
4 | 1.5.11.2 |  |  | QAG (Non-SIT LDSO) |  | Potential for non-SIT LDSO QT Regression for Qualification | 0% | 19/05/25 | 22/08/25 | 70 days? | 19/05/25 | 22/08/25 | 0 days | 0 days | 70 days? | Non-SIT LDSO |  | 6.12 | Yes
3 | 1.5.12 |  |  | QAG (Non-SIT LDSO) |  | Test Result Assurance | 0% | 21/04/25 | 29/05/25 | 29 days | 21/04/25 | 29/05/25 | 0 days | 0 days | -31 days | N/A |  | 6 | Yes
4 | 1.5.12.1 |  |  | QAG (Non-SIT LDSO) |  | LDSOs Develop & Submit Test Report (QT Test Completion Report) | 0% | 21/04/25 | 16/05/25 | 19 days | 21/04/25 | 16/05/25 | 0 days | -1 day | 0 days | LDSO |  | 6 | Yes
4 | 1.5.12.2 |  |  | QAG (Non-SIT LDSO) |  | Test Reports Reviewed By MHHS & Code Bodies & Finalised | 0% | 16/05/25 | 29/05/25 | 10 days | 16/05/25 | 29/05/25 | 0 days | 0 days | -6 days | Non-SIT LDSO |  | 6 | Yes
4 | 1.5.12.3 | T3 | T3-QU-0079 | QAG (Non-SIT LDSO) |  | Non-SIT LDSOs submission deadline for their QT Test Completion Report to MHHS Programme | 0% | 29/05/25 | 29/05/25 | 0 days | 29/05/25 | 29/05/25 | 1 day | 0 days | 0 days | Non-SIT LDSO |  | 6 | Yes
3 | 1.5.13 |  |  | QAG (Non-SIT LDSO) |  | Non-SIT LDSO Qualification Closure | 0% | 25/08/25 | 19/09/25 | 20 days | 30/05/25 | 22/08/25 | 61 days | 20 days | -29 days | N/A |  | 6 | Yes
4 | 1.5.13.1 |  |  | QAG (Non-SIT LDSO) |  | Non-SIT LDSO Qualification Learned Captured | 0% | 25/08/25 | 12/09/25 | 15 days | 30/05/25 | 19/06/25 | 61 days | 61 days | 0 days | Non-SIT LDSO |  | 6 | Yes |  | 08/01/25 - Milestones moved to accommodate potential regression testing
4 | 1.5.13.2 |  |  | QAG (Non-SIT LDSO) |  | Non-SIT LDSO Qualification Closure Down | 0% | 15/09/25 | 19/09/25 | 5 days | 20/06/25 | 26/06/25 | 61 days | 61 days | 0 days | Non-SIT LDSO |  | 6 | Yes |  | 08/01/25 - Milestones moved to accommodate potential regression testing
2 | 1.6 |  |  |  |  | S & A QUALIFICATION | 56% | 07/11/23 | 28/01/27 | 843 days? | 07/11/23 | 28/01/27 | 0 days | 0 days | 240 days? | N/A |  |  | Yes
3 | 1.6.1 |  |  |  |  | MHHS Qualification - Qualification Deliverables | 95% | 07/11/23 | 17/10/25 | 509 days | 07/11/23 | 14/08/25 | 0 days | 46 days | 160 days | N/A |  | 5.24 | Yes
4 | 1.6.1.1 |  |  |  |  | BSC & REC Assessment Criteria | 100% | 07/11/23 | 14/08/25 | 463 days | 07/11/23 | 14/08/25 | 0 days | 0 days | 251 days | N/A |  | 5.24 | Yes
5 | 1.6.1.1.1 |  |  |  |  | Draft BSC Assessment Criteria (Functional) | 100% | 07/11/23 | 05/12/23 | 21 days | 07/11/23 | 05/12/23 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.1.1.2 |  |  |  |  | BSC PAB Review | 100% | 14/12/23 | 14/12/23 | 1 day | 14/12/23 | 14/12/23 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.1.1.3 |  |  |  |  | Update BSC Assessment Criteria (Functional, Non-Functional, Migration) | 100% | 07/02/24 | 19/03/24 | 30 days | 07/02/24 | 19/03/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.1.1.4 |  |  |  |  | REC & BSC PAB Approval | 100% | 26/03/24 | 28/03/24 | 3 days | 26/03/24 | 28/03/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.1.1.5 |  |  |  |  | Update BSC Assessment Criteria (Functional, Non-Functional, Migration, Operational) | 100% | 24/07/24 | 20/08/24 | 20 days | 24/07/24 | 20/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.1.1.6 | T3 | T3-QU-0080 | QAG |  | Assessment Criteria (Functional, Non-Functional, Migration, Operational) Approved by REC PAB and BSC PAB | 100% | 29/08/24 | 14/08/25 | 250 days | 29/08/24 | 14/08/25 | 1 day | 0 days | 250 days | Code Bodies |  | 5.25 | Yes
4 | 1.6.1.2 |  |  |  |  | Qualification Approach and Plan | 100% | 04/12/23 | 29/08/24 | 194 days | 04/12/23 | 29/08/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
5 | 1.6.1.2.1 |  |  |  |  | Qualification Approach and Plan v2 | 100% | 04/12/23 | 28/03/24 | 84 days | 04/12/23 | 28/03/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.1.2.1.1 |  |  |  |  | Draft Qualification Approach and Plan v2 | 100% | 04/12/23 | 12/01/24 | 30 days | 04/12/23 | 12/01/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.2.1.2 |  |  |  |  | Internal Review (Code Bodies and MHHSP) for Qualification Approach and Plan V2 | 100% | 15/01/24 | 26/01/24 | 10 days | 15/01/24 | 26/01/24 | 0 days | 0 days | 0 days | Code Bodies, SI Team, SRO |  | 5.24 | Yes
6 | 1.6.1.2.1.3 |  |  |  |  | Industry consultation for Qualification Approach and Plan v2 | 100% | 31/01/24 | 14/02/24 | 11 days | 31/01/24 | 14/02/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.1.2.1.4 |  |  |  |  | Update Qualification Approach and Plan v2 post industry consultation | 100% | 15/02/24 | 28/02/24 | 10 days | 15/02/24 | 28/02/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.2.1.5 |  |  |  |  | QWG Endorsement of Qualification Approach and Plan v2 | 100% | 12/03/24 | 12/03/24 | 1 day | 12/03/24 | 12/03/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.2.1.6 |  |  |  |  | QAG Approval of Qualification Approach and Plan v2 | 100% | 21/03/24 | 21/03/24 | 1 day | 21/03/24 | 21/03/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.2.1.7 |  |  |  |  | BSC and REC PAB Approval of Qualification Approach and Plan v2 | 100% | 26/03/24 | 28/03/24 | 3 days | 26/03/24 | 28/03/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.2.1.8 | T3 | T3-QU-0063 | QAG |  | Functional Testing elements of Qualification Approach & Plan v2 approvement by REC PAB and BSC PAB | 100% | 28/03/24 | 28/03/24 | 0 days | 28/03/24 | 28/03/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.2.1.9 | T3 | T3-QU-0064 | QAG |  | Migration Testing elements of Qualification Approach & Plan v2 appoved by REC PAB and BSC PAB | 100% | 28/03/24 | 28/03/24 | 0 days | 28/03/24 | 28/03/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.1.2.2 |  |  |  |  | Qualification Approach and Plan v3 | 100% | 06/05/24 | 29/08/24 | 84 days | 06/05/24 | 29/08/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.1.2.2.1 |  |  |  |  | Draft Qualification Approach and Plan v3 | 100% | 06/05/24 | 21/06/24 | 35 days | 06/05/24 | 21/06/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.6.1.2.2.2 |  |  |  |  | Internal Review (Code Bodies and MHHSP) of Qualification Approach and Plan v3 | 100% | 24/06/24 | 05/07/24 | 10 days | 24/06/24 | 05/07/24 | 0 days | 0 days | 0 days | Code Bodies, SI Team, SRO |  | 5.27 | Yes
6 | 1.6.1.2.2.3 |  |  |  |  | Industry consultation for Qualification Approach and Plan v3 | 100% | 08/07/24 | 19/07/24 | 10 days | 08/07/24 | 19/07/24 | 0 days | 0 days | 0 days | Participants |  | 5.27 | Yes
6 | 1.6.1.2.2.4 |  |  |  |  | Update Qualification Approach and Plan v3 Post-Consultation | 100% | 22/07/24 | 02/08/24 | 10 days | 22/07/24 | 02/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.6.1.2.2.5 |  |  |  |  | QWG Endorsement of Qualification Approach and Plan v3 | 100% | 13/08/24 | 13/08/24 | 1 day | 13/08/24 | 13/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.6.1.2.2.6 |  | T3-QU-0081 | QAG |  | QAG Approval of Qualification Approach and Plan v3 | 100% | 22/08/24 | 22/08/24 | 0 days | 22/08/24 | 22/08/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.6.1.2.2.7 |  |  |  |  | BSC and REC PAB Approval of Qualification Approach and Plan v3 | 100% | 27/08/24 | 29/08/24 | 3 days | 27/08/24 | 29/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
6 | 1.6.1.2.2.8 | T3 | T3-QU-0065 | QAG |  | Non-Functional Testing elements of Qualification Approach and Plan v3 approved by REC PAB and BSC PAB | 100% | 29/08/24 | 29/08/24 | 0 days | 29/08/24 | 29/08/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.27 | Yes
4 | 1.6.1.3 |  |  |  |  | Qualification Assessment Document | 87% | 22/12/23 | 17/10/25 | 476 days | 22/12/23 | 07/03/25 | 0 days | 160 days | 160 days | N/A |  | 5.24 | Yes
5 | 1.6.1.3.1 |  |  |  |  | Qualification Assessment Document v1 | 100% | 22/12/23 | 28/03/24 | 70 days | 22/12/23 | 28/03/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.1.3.1.1 |  |  |  |  | Draft Qualification Assessment Document v1 | 100% | 22/12/23 | 01/02/24 | 30 days | 22/12/23 | 01/02/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.1.2 |  |  |  |  | Internal Review (Code Bodies and MHHSP) of Qualification Assessment Document v1 | 100% | 01/02/24 | 14/02/24 | 10 days | 01/02/24 | 14/02/24 | 0 days | 0 days | 0 days | Code Bodies, SI Team, SRO |  | 5.24 | Yes
6 | 1.6.1.3.1.3 |  |  |  |  | Industry consultation for Qualification Assessment Document v1 | 100% | 16/02/24 | 01/03/24 | 11 days | 16/02/24 | 01/03/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.1.3.1.4 |  |  |  |  | Update Post-Consultation for Qualification Assessment Document v1 | 100% | 04/03/24 | 15/03/24 | 10 days | 04/03/24 | 15/03/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.1.5 |  |  |  |  | BSC and REC PAB Approval of Qualification Assessment Document v1 | 100% | 26/03/24 | 28/03/24 | 3 days | 26/03/24 | 28/03/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.1.6 | T3 | T3-QU-0066 | QAG |  | Qualification Assessment Document v1 approved by REC PAB and BSC PAB | 100% | 28/03/24 | 28/03/24 | 0 days | 28/03/24 | 28/03/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.1.3.2 |  |  |  |  | Qualification Assessment Document v3 | 100% | 29/03/24 | 29/08/24 | 110 days | 29/03/24 | 29/08/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.1.3.2.1 |  |  |  |  | Draft Qualification Assessment Document V1.1 | 100% | 29/03/24 | 03/05/24 | 26 days | 29/03/24 | 03/05/24 | 0 days | 0 days | 0 days |  |  | 5.24 | Yes
6 | 1.6.1.3.2.2 |  |  |  |  | Industry Consultation for Qualification Assessment Document V1.1 | 100% | 06/05/24 | 21/05/24 | 12 days | 06/05/24 | 21/05/24 | 0 days | 0 days | 0 days |  |  | 5.24 | Yes
6 | 1.6.1.3.2.3 |  |  |  |  | Draft Qualification Assessment Document v3 | 100% | 14/06/24 | 21/06/24 | 6 days | 14/06/24 | 21/06/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.2.4 |  |  |  |  | Internal Review (Code Bodies and MHHSP) of Qualification Assessment Document v3 | 100% | 24/06/24 | 05/07/24 | 10 days | 24/06/24 | 05/07/24 | 0 days | 0 days | 0 days | Code Bodies, SI Team, SRO |  | 5.24 | Yes
6 | 1.6.1.3.2.5 |  |  |  |  | Industry consultation for Qualification Assessment Document v3 | 100% | 08/07/24 | 19/07/24 | 10 days | 08/07/24 | 19/07/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.1.3.2.6 |  |  |  |  | Update Post-Consultation for Qualification Assessment Document v3 | 100% | 22/07/24 | 02/08/24 | 10 days | 22/07/24 | 02/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.2.7 |  |  |  |  | QWG Endorsement of Qualification Assessment Document v3 | 100% | 13/08/24 | 13/08/24 | 1 day | 13/08/24 | 13/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.2.8 | T3 | T3-QU-0083 | QAG |  | QAG Endorsement of Qualification Assessment Document v3 | 100% | 22/08/24 | 22/08/24 | 1 day | 22/08/24 | 22/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.25 | Yes
6 | 1.6.1.3.2.9 |  |  |  |  | BSC and REC PAB Approval of Qualification Assessment Document v3 | 100% | 27/08/24 | 29/08/24 | 3 days | 27/08/24 | 29/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.2.10 | T3 | T3-QU-0067 | QAG |  | Qualification Assessment Document v3 approved by REC PAB and BSC PAB | 100% | 29/08/24 | 29/08/24 | 0 days | 29/08/24 | 29/08/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
5 | 1.6.1.3.3 |  |  |  |  | Qualification Assessment Document Portal | 77% | 05/02/24 | 17/10/25 | 445 days | 05/02/24 | 07/03/25 | 0 days | 160 days | 160 days | N/A |  | 5.24 | Yes
6 | 1.6.1.3.3.1 |  |  |  |  | Design Completion | 100% | 05/02/24 | 15/03/24 | 30 days | 05/02/24 | 15/03/24 | 0 days | 0 days | 0 days | QAD Portal Dev Team |  | 5.24 | Yes
6 | 1.6.1.3.3.2 |  |  |  |  | Qualification Assessment Document Portal Build | 100% | 18/03/24 | 26/04/24 | 30 days | 18/03/24 | 26/04/24 | 0 days | 0 days | 0 days | QAD Portal Dev Team |  | 5.24 | Yes
6 | 1.6.1.3.3.3 |  |  |  |  | Qualification Assessment Document Internal Testing | 100% | 29/04/24 | 24/05/24 | 20 days | 29/04/24 | 24/05/24 | 0 days | 0 days | 0 days | QAD Portal Dev Team. Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.3.4 |  |  |  |  | Qualification Assessment Document Portal Training and Onboarding Material Creation | 100% | 27/05/24 | 21/06/24 | 20 days | 27/05/24 | 21/06/24 | 0 days | 0 days | 0 days | QAD Portal Dev Team |  | 5.24 | Yes
6 | 1.6.1.3.3.5 |  |  |  |  | Qualification Assessment Document Portal Webinar (Date TBC) | 100% | 18/06/24 | 18/06/24 | 1 day | 18/06/24 | 18/06/24 | 0 days | 0 days | 0 days | QAD Portal Dev Team |  | 5.24 | Yes
6 | 1.6.1.3.3.6 |  |  |  |  | SIT Participant QAD Application Creation in Portal | 100% | 09/12/24 | 20/12/24 | 10 days | 09/12/24 | 20/12/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.3.7 |  |  |  |  | Non-SIT LDSO Participant QAD Application Creation in Portal | 100% | 09/12/24 | 20/12/24 | 10 days | 09/12/24 | 20/12/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.1.3.3.8 |  |  |  |  | QT Wave 1 Participant QAD Application Creation in Portal | 0% | 21/04/25 | 02/05/25 | 10 days | 21/04/25 | 02/05/25 | 0 days | 0 days | 0 days | Code Bodies |  | 6.1 | Yes
6 | 1.6.1.3.3.9 |  |  |  |  | QT Wave 2 Participant QAD Application Creation in Portal | 0% | 26/05/25 | 06/06/25 | 10 days | 26/05/25 | 06/06/25 | 0 days | 0 days | 0 days | Code Bodies |  | 6.1 | Yes
6 | 1.6.1.3.3.10 |  |  |  |  | QT Wave 3 Participant QAD Application Creation in Portal | 0% | 28/07/25 | 08/08/25 | 10 days | 28/07/25 | 08/08/25 | 0 days | 0 days | 0 days | Code Bodies |  | 6.1 | Yes
6 | 1.6.1.3.3.11 |  |  |  |  | QT Wave 4 Participant QAD Application Creation in Portal | 0% | 06/10/25 | 17/10/25 | 10 days | 06/10/25 | 17/10/25 | 0 days | 0 days | 0 days | Code Bodies |  | 6.1 | Yes
6 | 1.6.1.3.3.12 |  |  |  |  | Update to Qualification Assessment Document Portal post QAD V3 | 100% | 30/08/24 | 12/09/24 | 10 days | 30/08/24 | 12/09/24 | 0 days | 0 days | 0 days | QAD Portal Dev Team |  | 6.1 | Yes
6 | 1.6.1.3.3.13 | T3 | T3-QU-0084 | QAG |  | Update to Qualification Assessment Document Portal post QAD V3 Complete | 100% | 12/09/24 | 12/09/24 | 0 days | 12/09/24 | 12/09/24 | 1 day | 0 days | 0 days | QAD Portal Dev Team |  | 6.1 | Yes
3 | 1.6.2 |  |  |  |  | MHHS Qualification - SIT Participants | 0% | 06/01/25 | 18/12/25 | 249 days | 06/01/25 | 22/12/25 | 0 days | -2 days | 55 days | N/A |  | 6.11 | Yes
4 | 1.6.2.1 |  |  |  |  | Initial QAD Submission Window opens | 100% | 06/01/25 | 06/01/25 | 0 days | 06/01/25 | 06/01/25 | 0 days | -1 day | 0 days | Participants |  | 6.11 | Yes
4 | 1.6.2.2 |  |  |  |  | SIT Participants submit Initial QAD | 0% | 06/01/25 | 14/02/25 | 30 days | 06/01/25 | 14/02/25 | 0 days | 0 days | 1 day | Participants |  | 6.11 | Yes
4 | 1.6.2.3 |  |  |  |  | Code Bodies review Initial QAD | 0% | 14/02/25 | 04/04/25 | 36 days | 14/02/25 | 04/04/25 | 0 days | 0 days | 0 days | Code Bodies |  | 6.11 | Yes
4 | 1.6.2.4 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 0% | 04/04/25 | 04/04/25 | 0 days | 04/04/25 | 04/04/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.11 | Yes
4 | 1.6.2.5 |  |  |  |  | MHHS Qualification - SIT MVC Participants | 0% | 07/04/25 | 11/09/25 | 114 days | 07/04/25 | 11/09/25 | 0 days | 0 days | 50 days | N/A |  | 6.11 | Yes
5 | 1.6.2.5.1 |  |  |  |  | Final QAD Submission Window (MVC) opens | 0% | 07/04/25 | 07/04/25 | 0 days | 07/04/25 | 07/04/25 | 1 day | 0 days | 0 days | Participants |  | 6.11 | Yes
5 | 1.6.2.5.2 |  |  |  |  | SIT MVC Participants submit Final QAD (exc Test Reports) | 0% | 07/04/25 | 09/05/25 | 25 days | 07/04/25 | 09/05/25 | 0 days | 0 days | -1 day | Participants |  | 6.11 | Yes
5 | 1.6.2.5.3 |  |  |  |  | Completion of Code Bodies review of Final QAD (MVC) | 0% | 12/05/25 | 06/06/25 | 20 days | 12/05/25 | 06/06/25 | 0 days | 0 days | 1 day | Code Bodies |  | 6.11 | Yes
5 | 1.6.2.5.4 |  |  |  |  | QAD Sign Off Deadline (MVC) + Test Reports | 0% | 22/08/25 | 22/08/25 | 0 days | 22/08/25 | 22/08/25 | 1 day | 0 days | -1 day | Participants |  | 6.11 | Yes
5 | 1.6.2.5.5 | T3 | T3-QU-0085 | QAG |  | REC Code Manager / BSC PAB Approval of Qualification (MVC) | 0% | 11/09/25 | 11/09/25 | 0 days | 11/09/25 | 11/09/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.11 | Yes
4 | 1.6.2.6 |  |  |  |  | MHHS Qualification - SIT Non-MVC Participants | 0% | 19/05/25 | 18/12/25 | 154 days | 19/05/25 | 22/12/25 | 0 days | -2 days | 25 days | N/A |  | 6.11 | Yes
5 | 1.6.2.6.1 |  |  |  |  | Final QAD Submission Window (Non-MVC) opens | 0% | 19/05/25 | 19/05/25 | 0 days | 19/05/25 | 19/05/25 | 1 day | 0 days | 0 days | Participants |  | 6.11 | Yes
5 | 1.6.2.6.2 |  |  |  |  | SIT Non-MVC Participants submit Final QAD | 0% | 19/05/25 | 19/09/25 | 90 days | 19/05/25 | 19/09/25 | 0 days | 0 days | 4 days | Participants |  | 6.11 | Yes
5 | 1.6.2.6.3 |  |  |  |  | Completion of Code Bodies review of Final QAD (Non-MVC) | 0% | 22/09/25 | 24/10/25 | 25 days | 22/09/25 | 24/10/25 | 0 days | 0 days | 6 days | Code Bodies |  | 6.11 | Yes
5 | 1.6.2.6.4 |  |  |  |  | QAD Sign Off Deadline (Non-MVC) | 0% | 28/11/25 | 28/11/25 | 1 day | 28/11/25 | 28/11/25 | 0 days | 0 days | 0 days | Participants |  | 6.11 | Yes
5 | 1.6.2.6.5 | T3 | T3-QU-0086 | QAG |  | REC Code Manager / BSC PAB Approval of Qualification (Non-MVC) | 0% | 18/12/25 | 18/12/25 | 0 days | 22/12/25 | 22/12/25 | -1 day | -2 days | 0 days | Code Bodies |  | 6.11 | Yes
3 | 1.6.3 |  |  |  |  | MHHS Qualification - Non-SIT LDSO | 0% | 06/01/25 | 10/09/25 | 178 days | 06/01/25 | 11/09/25 | 0 days | -1 day | 63 days | N/A |  | 6.11 | Yes
4 | 1.6.3.1 |  |  |  |  | Initial QAD Submission window opens | 100% | 06/01/25 | 06/01/25 | 0 days | 06/01/25 | 06/01/25 | 1 day | 0 days | 0 days | Participants |  | 6.11 | Yes
4 | 1.6.3.2 |  |  |  |  | Non-SIT LDSO Participants submit initial QAD | 0% | 06/01/25 | 14/02/25 | 30 days | 06/01/25 | 14/02/25 | 0 days | 0 days | 1 day | Participants |  | 6.11 | Yes
4 | 1.6.3.3 | T3 | T3-QU-0087 | QAG |  | Non-SIT LDSO QT Participants have submitted their initial QAD | 0% | 14/02/25 | 14/02/25 | 0 days | 14/02/25 | 14/02/25 | 1 day | 0 days | 0 days | Participants |  | 6.11 | Yes
4 | 1.6.3.4 |  |  |  |  | Code Bodies review of Non-SIT LDSO participants Initial QAD | 0% | 17/02/25 | 04/04/25 | 35 days | 17/02/25 | 04/04/25 | 0 days | 0 days | -1 day | Code Bodies |  | 6.11 | Yes
4 | 1.6.3.5 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 0% | 04/04/25 | 04/04/25 | 0 days | 04/04/25 | 04/04/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.11 | Yes
4 | 1.6.3.6 |  |  |  |  | Final QAD Submission window opens | 0% | 07/04/25 | 07/04/25 | 0 days | 07/04/25 | 07/04/25 | 1 day | 0 days | 0 days | Participants |  | 6.11 | Yes
4 | 1.6.3.7 |  |  |  |  | Non-SIT LDSO Participants submit Final QAD | 0% | 21/04/25 | 23/05/25 | 25 days | 21/04/25 | 23/05/25 | 0 days | 0 days | -1 day | Participants |  | 6.11 | Yes
4 | 1.6.3.8 | T3 | T3-QU-0088 | QAG |  | Non-SIT LDSO QT Participants have submitted their final QAD | 0% | 23/05/25 | 23/05/25 | 0 days | 23/05/25 | 23/05/25 | 1 day | 0 days | 0 days | Participants |  | 6.11 | Yes
4 | 1.6.3.9 |  |  |  |  | Completion of Code Bodies review of the Final QAD | 0% | 26/05/25 | 20/06/25 | 20 days | 26/05/25 | 20/06/25 | 0 days | 0 days | 1 day | Code Bodies |  | 6.11 | Yes
4 | 1.6.3.10 |  |  |  |  | QAD Sign Off Deadline (Non-SIT LDSOs) | 0% | 22/08/25 | 22/08/25 | 0 days | 22/08/25 | 22/08/25 | 1 day | 0 days | -1 day | Participants |  | 6.11 | Yes
4 | 1.6.3.11 | T2 | T2-QU-0500 | QAG (Non-SIT LDSO) |  | BSC PAB & REC Manager approval of Qualification for Non-SIT LDSOs | 0% | 10/09/25 | 10/09/25 | 0 days | 11/09/25 | 11/09/25 | 0 days | -1 day | 0 days | Non-SIT LDSO |  | 6.12 | Yes
3 | 1.6.4 |  |  |  |  | MHHS Qualification - Qualification Waves | 53% | 18/12/23 | 28/01/27 | 814 days? | 18/12/23 | 28/01/27 | 0 days | 0 days | 240 days? | N/A |  | 5.24 | Yes
4 | 1.6.4.1 |  |  |  |  | Qualification Wave Prep | 86% | 18/12/23 | 08/01/26 | 539 days? | 18/12/23 | 26/12/25 | 0 days | 9 days | 115 days? | N/A |  | 5.24 | Yes
5 | 1.6.4.1.1 |  |  |  |  | Non-SIT Supplier and Agent Test Approach and Plan | 100% | 18/12/23 | 30/05/24 | 119 days | 18/12/23 | 30/05/24 | 0 days | 0 days | 1 day | N/A |  | 5.24 | Yes
6 | 1.6.4.1.1.1 |  |  |  |  | Draft Non-SIT S&A Test Approach and Plan | 100% | 18/12/23 | 23/02/24 | 50 days | 18/12/23 | 23/02/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.1.1.2 |  |  |  |  | Internal Review of Non-SIT S&A Test Approach and Plan (Code Bodies and MHHSP) | 100% | 26/02/24 | 08/03/24 | 10 days | 26/02/24 | 08/03/24 | 0 days | 0 days | 0 days | Code Bodies, SI Team, SRO |  | 5.24 | Yes
6 | 1.6.4.1.1.3 |  |  |  |  | Issue Non-SIT S&A Test Approach and Plan for Consultation | 100% | 18/03/24 | 05/04/24 | 15 days | 18/03/24 | 05/04/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.1.1.4 |  |  |  |  | Update Non-SIT S&A Test Approach and Plan Post-Consultation | 100% | 08/04/24 | 19/04/24 | 10 days | 08/04/24 | 19/04/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.1.1.5 |  |  |  |  | QWG Endorsement of Non-SIT S&A Test Approach and Plan | 100% | 14/05/24 | 14/05/24 | 1 day | 14/05/24 | 14/05/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.1.1.6 | T3 | T3-QU-0089 | QAG |  | QAG Approval of Non-SIT S&A Test Approach and Plan | 100% | 23/05/24 | 23/05/24 | 0 days | 23/05/24 | 23/05/24 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
6 | 1.6.4.1.1.7 | T3 | T3-QU-0090 | QAG |  | BSC & REC PAB Approval of Non-SIT S&A Test Approach and Plan | 100% | 30/05/24 | 30/05/24 | 0 days | 30/05/24 | 30/05/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.25 | Yes
5 | 1.6.4.1.2 |  |  |  |  | QT Test Data Approach and Plan | 100% | 19/04/24 | 18/07/24 | 64 days | 19/04/24 | 18/07/24 | 1 day | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.4.1.2.1 |  |  |  |  | QT Test Data Approach agreed as part of the Non-SIT Supplier and Agent Test Approach and Plan | 100% | 19/04/24 | 19/04/24 | 0 days | 19/04/24 | 19/04/24 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team, Participants |  | 5.24 | Yes
6 | 1.6.4.1.2.2 |  |  |  |  | Draft Test Data Approach and Plan for QT | 100% | 06/05/24 | 17/05/24 | 10 days | 06/05/24 | 17/05/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.1.2.3 |  |  |  |  | Internal Review (Code Bodies and MHHSP) of QT Test Data Approach and Plan | 100% | 20/05/24 | 07/06/24 | 15 days | 20/05/24 | 07/06/24 | 0 days | 0 days | 5 days | Code Bodies, SI Team, SRO |  | 5.24 | Yes
6 | 1.6.4.1.2.4 |  |  |  |  | Issue QT Test Data Approach and Plan for Industry Consultation | 100% | 10/06/24 | 21/06/24 | 10 days | 10/06/24 | 21/06/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.1.2.5 |  |  |  |  | Update QT Test Approach and Plan Post Industry Consultation | 100% | 24/06/24 | 28/06/24 | 5 days | 24/06/24 | 28/06/24 | 0 days | 0 days | -5 days | Non-SIT S&A QT Team |  | 5.24 | Yes
6 | 1.6.4.1.2.6 |  |  |  |  | QWG Endorsement of Test Data Approach and Plan | 100% | 09/07/24 | 09/07/24 | 1 day | 09/07/24 | 09/07/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.1.2.7 | T3 | T3-QU-0091 | QAG |  | QAG Approval of QT Test Data Approach and Plan | 100% | 18/07/24 | 18/07/24 | 0 days | 18/07/24 | 18/07/24 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.29 | Yes
5 | 1.6.4.1.3 |  |  |  |  | QT Functional Test Scenarios and Test Cases | 100% | 04/03/24 | 23/05/24 | 59 days | 04/03/24 | 23/05/24 | 0 days | 0 days | 0 days | N/A |  | 5.24 | Yes
6 | 1.6.4.1.3.1 |  |  |  |  | Draft Test Scenarios and Test Case list - Batch 1 | 100% | 04/03/24 | 15/03/24 | 10 days | 04/03/24 | 15/03/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team, Code Bodies |  | 5.24 | Yes
6 | 1.6.4.1.3.2 |  |  |  |  | Issue Batch 1 for Consultation | 100% | 18/03/24 | 05/04/24 | 15 days | 18/03/24 | 05/04/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.1.3.3 |  |  |  |  | Gap analysis against QT Requirements | 100% | 18/03/24 | 27/03/24 | 8 days | 18/03/24 | 27/03/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.1.3.4 |  |  |  |  | Update Test Scenarios and Test Case list - Batch 2 | 100% | 28/03/24 | 04/04/24 | 6 days | 28/03/24 | 04/04/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team, Code Bodies |  | 5.24 | Yes
6 | 1.6.4.1.3.5 |  |  |  |  | Issue Batch 2 for consultation | 100% | 05/04/24 | 18/04/24 | 10 days | 05/04/24 | 18/04/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.1.3.6 |  |  |  |  | Update Batch 2 post consultation | 100% | 19/04/24 | 02/05/24 | 10 days | 19/04/24 | 02/05/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team, Code Bodies |  | 5.24 | Yes
6 | 1.6.4.1.3.7 |  |  |  |  | QWG Endorsement of Batch 1 and 2 | 100% | 14/05/24 | 14/05/24 | 1 day | 14/05/24 | 14/05/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.24 | Yes
6 | 1.6.4.1.3.8 | T3 | T3-QU-0092 | QAG |  | QAG Approval of QT Functional Test Scenarios and Test Cases Batches 1 and 2 | 100% | 23/05/24 | 23/05/24 | 0 days | 23/05/24 | 23/05/24 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
5 | 1.6.4.1.4 |  |  |  |  | QT Migration Test Scenarios and Test Cases | 100% | 06/05/24 | 18/07/24 | 54 days | 06/05/24 | 18/07/24 | 0 days | 0 days | 0 days | N/A |  | 5.25 | Yes
6 | 1.6.4.1.4.1 |  |  |  |  | Draft Test Scenarios and Test Case list - Batch 1 | 100% | 06/05/24 | 31/05/24 | 20 days | 06/05/24 | 31/05/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team, Code Bodies |  | 5.25 | Yes
6 | 1.6.4.1.4.2 |  |  |  |  | Issue Batch 1 for Consultation | 100% | 03/06/24 | 14/06/24 | 10 days | 03/06/24 | 14/06/24 | 0 days | 0 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.1.4.3 |  |  |  |  | Update Batch 1 Post Consultation | 100% | 17/06/24 | 28/06/24 | 10 days | 17/06/24 | 28/06/24 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
6 | 1.6.4.1.4.4 |  |  |  |  | QWG Endorsement of Batch 1 | 100% | 09/07/24 | 09/07/24 | 0 days | 09/07/24 | 09/07/24 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.25 | Yes
6 | 1.6.4.1.4.5 | T3 | T3-QU-0119 | QAG |  | QAG Approval of QT Migration Test Scenarios and Test Cases Batches 1 | 100% | 18/07/24 | 18/07/24 | 0 days | 18/07/24 | 18/07/24 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 5.29 | Yes
5 | 1.6.4.1.5 |  |  |  |  | QT Functional (inc NF and Operational) Test Scenarios and Test Cases | 54% | 05/11/24 | 30/01/25 | 63 days | 04/11/24 | 27/12/24 | 1 day | 24 days | 63 days | Non-SIT S&A QT Test Team | Approved |  | Yes
6 | 1.6.4.1.5.1 |  |  |  |  | Draft Test Scenarios and Test Case list - Batch 3 | 100% | 05/11/24 | 02/12/24 | 20 days | 05/11/24 | 02/12/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team | Approved | 6.11 | Yes
6 | 1.6.4.1.5.2 |  |  |  |  | Issue Batch 3 for Consultation | 70% | 03/12/24 | 16/12/24 | 10 days | 03/12/24 | 16/12/24 | 0 days | 0 days | 10 days | Non-SIT S&A QT Test Team | Approved | 6.11 | Yes |  | 17/12/24 - This will be published on 18/12/24 and close on 15/01/24, delay caused by test cases being added to the RTTM, postponing the previous activity.
6 | 1.6.4.1.5.3 |  |  |  |  | Update Batch 3 Post Consultation | 0% | 17/12/24 | 13/01/25 | 20 days | 17/12/24 | 13/01/25 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team | Approved | 6.11 | Yes |  | 17/12/24 - This will now take place in Feb due to consultation going out late.
6 | 1.6.4.1.5.4 |  |  |  |  | QWG Endorsement of Batch 3 | 0% | 22/01/25 | 22/01/25 | 0 days | 22/01/25 | 22/01/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team | Approved | 6.11 | Yes |  | 17/12/24 - This will now take place in Feb due to consultation going out late.
6 | 1.6.4.1.5.5 | T3 | T3-QU-0123 | QAG |  | QAG Approval of QT Functional Test Scenarios and Test Cases Batches 3 | 0% | 30/01/25 | 30/01/25 | 0 days | 30/01/25 | 30/01/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team | Approved | 6.11 | Yes |  | 14/01/25 - Expected that QAG approval will place in February. This is because drafting of test cases is behind schedule due to dependency on SIT RTTM which is still adding additional test cases.
5 | 1.6.4.1.6 |  |  |  |  | Qualification Testing Framework (Test Stubs and Supporting UI) | 84% | 29/01/24 | 08/01/26 | 509 days? | 29/01/24 | 08/01/26 | 0 days | 0 days | 509 days? | Non-SIT S&A QT Test Team |  | 6.12 | Yes
6 | 1.6.4.1.6.1 |  |  |  |  | Proof of Concept for QTF Completion | 100% | 29/01/24 | 29/03/24 | 45 days | 29/01/24 | 29/03/24 | 0 days | 0 days | 45 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
6 | 1.6.4.1.6.2 |  |  |  |  | Discovery and Mobilisation | 100% | 01/04/24 | 03/05/24 | 25 days | 01/04/24 | 03/05/24 | 0 days | 0 days | 25 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
6 | 1.6.4.1.6.3 |  |  |  |  | Agile DBT of Qualification Testing Framework | 100% | 24/04/24 | 16/08/24 | 83 days | 24/04/24 | 16/08/24 | 0 days | 0 days | 83 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.3.1 |  |  |  |  | User Interface (UI) | 100% | 24/04/24 | 28/06/24 | 48 days | 24/04/24 | 28/06/24 | 0 days | 0 days | 48 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.3.1.1 |  |  |  |  | UI Wireframe | 100% | 24/04/24 | 28/06/24 | 48 days | 24/04/24 | 28/06/24 | 0 days | 0 days | 48 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.3.1.2 |  |  |  |  | UI Standards | 100% | 13/05/24 | 28/06/24 | 35 days | 13/05/24 | 28/06/24 | 0 days | 0 days | 35 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.3.1.3 |  |  |  |  | Elexon Branding Sylesheet | 100% | 17/05/24 | 20/05/24 | 2 days | 17/05/24 | 20/05/24 | 0 days | 0 days | 2 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.3.1.4 |  |  |  |  | Elexon Branding QTF Logo | 100% | 31/05/24 | 03/06/24 | 2 days | 31/05/24 | 03/06/24 | 0 days | 0 days | 2 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.3.2 |  |  |  |  | Design, Build, Test | 100% | 13/05/24 | 16/08/24 | 70 days | 13/05/24 | 16/08/24 | 0 days | 0 days | 70 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.3.2.1 |  |  |  |  | Core UI Screens | 100% | 13/05/24 | 02/08/24 | 60 days | 13/05/24 | 02/08/24 | 0 days | 0 days | 60 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.3.2.2 |  |  |  |  | Tooling (Trigger Files / Template Generators) | 100% | 13/05/24 | 16/08/24 | 70 days | 13/05/24 | 16/08/24 | 0 days | 0 days | 70 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.3.2.3 |  |  |  |  | Database Schema | 100% | 13/05/24 | 19/07/24 | 50 days | 13/05/24 | 19/07/24 | 0 days | 0 days | 50 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.3.2.4 |  |  |  |  | Core API's | 100% | 13/05/24 | 02/08/24 | 60 days | 13/05/24 | 02/08/24 | 0 days | 0 days | 60 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
6 | 1.6.4.1.6.4 |  |  |  |  | QTF Test Cases DBT Refinement, Execution and Results Validation, Defect Management, Error Handling | 75% | 05/11/24 | 31/01/25 | 64 days | 05/11/24 | 31/01/25 | 0 days | 0 days | 64 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
6 | 1.6.4.1.6.5 |  |  |  |  | Environments | 98% | 15/04/24 | 31/07/25 | 339 days | 15/04/24 | 31/07/25 | 0 days | 0 days | 339 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.5.1 |  |  |  |  | Azure Devops | 100% | 15/04/24 | 11/12/24 | 173 days | 15/04/24 | 11/12/24 | 0 days | 0 days | 173 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.5.1.1 |  |  |  |  | QFT ADO Development Instance | 100% | 15/04/24 | 03/05/24 | 15 days | 15/04/24 | 03/05/24 | 0 days | 0 days | 15 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
9 | 1.6.4.1.6.5.1.1.1 |  |  |  |  | Elexon Instance Setup for QTF Build | 100% | 15/04/24 | 19/04/24 | 5 days | 15/04/24 | 19/04/24 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
9 | 1.6.4.1.6.5.1.1.2 |  |  |  |  | Configuration and User Access | 100% | 22/04/24 | 03/05/24 | 10 days | 22/04/24 | 03/05/24 | 0 days | 0 days | 10 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.5.1.2 |  |  |  |  | MHHSP ADO Instance | 100% | 23/07/24 | 11/12/24 | 102 days | 23/07/24 | 11/12/24 | 0 days | 0 days | 102 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
9 | 1.6.4.1.6.5.1.2.1 |  |  |  |  | MHHSP Instance Setup for QTF Production | 100% | 23/07/24 | 30/08/24 | 29 days | 23/07/24 | 30/08/24 | 0 days | 0 days | 29 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
9 | 1.6.4.1.6.5.1.2.2 |  |  |  |  | Configuration and User Access | 100% | 02/09/24 | 11/12/24 | 73 days | 02/09/24 | 11/12/24 | 0 days | 0 days | 73 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.5.2 |  |  |  |  | Temporary Development Environment | 100% | 15/04/24 | 31/05/24 | 35 days | 15/04/24 | 31/05/24 | 0 days | 0 days | 35 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.5.2.1 |  |  |  |  | Design | 100% | 15/04/24 | 03/05/24 | 15 days | 15/04/24 | 03/05/24 | 0 days | 0 days | 15 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.5.2.2 |  |  |  |  | Build and Deployment | 100% | 06/05/24 | 31/05/24 | 20 days | 06/05/24 | 31/05/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.5.3 |  |  |  |  | Dev, Test & Prod Environment Requirements + Design | 100% | 27/05/24 | 29/11/24 | 135 days | 27/05/24 | 29/11/24 | 0 days | 0 days | 135 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.5.3.1 |  |  |  |  | Design (including Security Review) | 100% | 27/05/24 | 29/11/24 | 135 days | 27/05/24 | 29/11/24 | 0 days | 0 days | 135 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.5.3.2 |  |  |  |  | Hub Development Dev/Test | 100% | 10/06/24 | 05/07/24 | 20 days | 10/06/24 | 05/07/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.5.3.3 |  |  |  |  | Hub Deployment | 100% | 10/06/24 | 05/07/24 | 20 days | 10/06/24 | 05/07/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.5.3.4 |  |  |  |  | Development Envn. Deployment | 100% | 08/07/24 | 19/09/24 | 53.8 days | 08/07/24 | 19/09/24 | 0 days | -0.2 days | 53.8 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.5.3.5 |  |  |  |  | Test Envn. Deployment | 100% | 19/09/24 | 03/10/24 | 10 days | 19/09/24 | 03/10/24 | 0.8 days | -0.2 days | 10 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.5.3.6 |  |  |  |  | Production Envn. Deployment | 100% | 03/10/24 | 07/11/24 | 25 days | 03/10/24 | 07/11/24 | 0.8 days | -0.2 days | 25 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.5.4 |  |  |  |  | QTF Deployment into Production | 0% | 03/02/25 | 27/02/25 | 19 days | 03/02/25 | 25/04/25 | 0 days | -41 days | 19 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.4.1 |  |  |  |  | App Deployment | 0% | 03/02/25 | 07/02/25 | 5 days | 03/02/25 | 07/02/25 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.4.2 |  |  |  |  | Smoke Test | 0% | 10/02/25 | 11/02/25 | 2 days | 10/02/25 | 11/02/25 | 0 days | 0 days | 2 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.4.3 |  |  |  |  | PEN Test | 0% | 12/02/25 | 13/02/25 | 2 days | 12/02/25 | 13/02/25 | 0 days | 0 days | 2 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.4.4 |  |  |  |  | Regression Test | 0% | 14/02/25 | 27/02/25 | 10 days | 14/02/25 | 27/02/25 | 0 days | 0 days | 10 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
7 | 1.6.4.1.6.5.5 |  |  |  |  | DIP Onboarding (UIT) | 100% | 26/07/24 | 13/12/24 | 101 days | 26/07/24 | 29/11/24 | 0 days | 10 days | 101 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.5.1 |  |  |  |  | DIP Simulator | 100% | 26/07/24 | 15/08/24 | 15 days | 26/07/24 | 15/08/24 | 0 days | 0 days | 15 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.5.2 |  |  |  |  | DIP (UIT) Instance available for Onboarding | 100% | 05/08/24 | 05/08/24 | 1 day | 05/08/24 | 05/08/24 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.5.3 |  |  |  |  | DIP (UIT) Portal | 100% | 03/09/24 | 03/09/24 | 1 day | 03/09/24 | 03/09/24 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.5.4 |  |  |  |  | DIP (UIT) Onboarding for Development (incl. certificates and security compliance) | 100% | 06/08/24 | 27/09/24 | 39 days | 06/08/24 | 27/09/24 | 0 days | 0 days | 39 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.5.5 |  |  |  |  | DIP (UIT) Onboarding for Development Connection Confirmed | 100% | 30/09/24 | 30/09/24 | 1 day | 30/09/24 | 30/09/24 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.5.6 |  |  |  |  | DIP (UIT) Onboarding for Test (incl. certificates and security compliance) | 100% | 01/10/24 | 07/10/24 | 5 days | 01/10/24 | 07/10/24 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.5.7 |  |  |  |  | DIP (UIT) Onboarding for Test Connection Confirmed | 100% | 08/10/24 | 08/10/24 | 1 day | 08/10/24 | 08/10/24 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.5.8 |  |  |  |  | DIP (UIT) Onboarding for Prod (incl. certificates and security compliance) | 100% | 09/10/24 | 15/10/24 | 5 days | 09/10/24 | 15/10/24 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.5.9 |  |  |  |  | DIP (UIT) Onboarding for Prod Connection Confirmed | 100% | 16/10/24 | 16/10/24 | 1 day | 16/10/24 | 16/10/24 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.5.10 |  |  |  |  | DIP UIT Test Stubs | 100% | 31/10/24 | 13/12/24 | 32 days | 17/10/24 | 29/11/24 | 10 days | 10 days | 32 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes |  | 12/11/24 - Additional time required to configure test stubs, forecast pushed out to reflect this.
7 | 1.6.4.1.6.5.6 |  |  |  |  | DTN Onboarding | 100% | 20/05/24 | 25/10/24 | 115 days | 20/05/24 | 25/10/24 | 0 days | 0 days | 115 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.6.1 |  |  |  |  | DTN Request Raised for Onboarding | 100% | 20/05/24 | 21/06/24 | 25 days | 20/05/24 | 21/06/24 | 0 days | 0 days | 25 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.6.2 |  |  |  |  | Setup, configuration of New Host and Test Flags | 100% | 24/06/24 | 28/06/24 | 5 days | 24/06/24 | 28/06/24 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.6.3 |  |  |  |  | New VPN Connection (Test) | 100% | 05/08/24 | 13/09/24 | 30 days | 05/08/24 | 13/09/24 | 0 days | 0 days | 30 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.6.4 |  |  |  |  | New VPN Connection (Prod) | 100% | 16/09/24 | 25/10/24 | 30 days | 16/09/24 | 25/10/24 | 0 days | 0 days | 30 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.6.5 |  |  |  |  | DTN Test Stubs | 100% | 16/09/24 | 27/09/24 | 10 days | 16/09/24 | 27/09/24 | 0 days | 0 days | 10 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
7 | 1.6.4.1.6.5.7 |  |  |  |  | Generate Tooling | 100% | 22/04/24 | 31/07/25 | 334 days | 22/04/24 | 31/07/25 | 0 days | 0 days | 334 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.7.1 |  |  |  |  | MPAN Core Generator | 100% | 22/04/24 | 24/05/24 | 25 days | 22/04/24 | 24/05/24 | 0 days | 0 days | 25 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.7.2 |  |  |  |  | MPAN File Generator | 100% | 27/05/24 | 09/08/24 | 55 days | 27/05/24 | 09/08/24 | 0 days | 0 days | 55 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.7.3 |  |  |  |  | MPAN Template Loader | 100% | 12/08/24 | 24/09/24 | 32 days | 12/08/24 | 24/09/24 | 0 days | 0 days | 32 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.7.4 |  |  |  |  | ADO Extract (QTC) From SIT | 100% | 06/05/24 | 14/06/24 | 30 days | 06/05/24 | 14/06/24 | 0 days | 0 days | 30 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.7.5 |  |  |  |  | Populate QT ADO | 100% | 17/06/24 | 09/08/24 | 40 days | 17/06/24 | 09/08/24 | 0 days | 0 days | 40 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.7.6 |  |  |  |  | Create QTC Spreadsheets | 100% | 03/06/24 | 28/06/24 | 20 days | 03/06/24 | 28/06/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.7.7 |  |  |  |  | Upload QTC Spreadsheets to QTF | 100% | 01/07/24 | 26/07/24 | 20 days | 01/07/24 | 26/07/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
8 | 1.6.4.1.6.5.7.8 |  |  |  |  | Create QTC Set / Master QTC Loader | 100% | 22/07/24 | 13/09/24 | 40 days | 22/07/24 | 13/09/24 | 0 days | 0 days | 40 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes
7 | 1.6.4.1.6.5.8 |  |  |  |  | Test Data | 100% | 10/06/24 | 28/06/24 | 15 days | 10/06/24 | 28/06/24 | 0 days | 0 days | 15 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.5.8.1 |  |  |  |  | Sample MPAN Data + Attributes from Suppliers | 100% | 10/06/24 | 28/06/24 | 15 days | 10/06/24 | 28/06/24 | 0 days | 0 days | 15 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
6 | 1.6.4.1.6.6 |  |  |  |  | MPANs, DIP Messages, Settlement, Consumption, Reference | 65% | 27/05/24 | 07/01/26 | 423 days? | 27/05/24 | 07/01/26 | 0 days | 0 days | 423 days? | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.6.1 |  |  |  |  | Create MPAN Data | 100% | 27/05/24 | 09/08/24 | 55 days | 27/05/24 | 09/08/24 | 0 days | 0 days | 55 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.6.2 |  |  |  |  | Create message templates (DIP, CSS, DTN) | 100% | 03/06/24 | 26/07/24 | 40 days | 03/06/24 | 26/07/24 | 0 days | 0 days | 40 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.6.3 |  |  |  |  | Create Consumption Data Templates | 100% | 16/09/24 | 11/10/24 | 20 days | 16/09/24 | 11/10/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.6.4 |  |  |  |  | Load Consumption Data | 100% | 11/11/24 | 13/12/24 | 25 days | 11/11/24 | 06/12/24 | 0 days | 5 days | 25 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.6.5 |  |  |  |  | Create Load Shape and Load Shape Total Templates | 100% | 16/09/24 | 11/10/24 | 20 days | 16/09/24 | 11/10/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.6.6 |  |  |  |  | Load Shape and Load Shape Total Data | 100% | 11/11/24 | 13/12/24 | 25 days | 11/11/24 | 06/12/24 | 0 days | 5 days | 25 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.6.7 |  |  |  |  | Create Settlement Report Templates | 100% | 16/09/24 | 11/10/24 | 20 days | 16/09/24 | 11/10/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.6.8 |  |  |  |  | Load Settlement Report Data | 100% | 11/11/24 | 13/12/24 | 25 days | 11/11/24 | 06/12/24 | 0 days | 5 days | 25 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.6.9 |  |  |  |  | Market Domain Data (MDD) For Legacy Systems | 100% | 29/07/24 | 30/08/24 | 25 days | 29/07/24 | 30/08/24 | 0 days | 0 days | 25 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.6.10 |  |  |  |  | Industry Standing Data (ISD) | 100% | 26/07/24 | 01/11/24 | 71 days? | 26/07/24 | 01/11/24 | 0 days | 0 days | 71 days? | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.10.1 |  |  |  |  | Dependant on Receiving ISD Agreed Source Data from Helix | 100% | 26/07/24 | 26/07/24 | 1 day | 26/07/24 | 26/07/24 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.10.2 |  |  |  |  | Helix Dev Environment migration | 100% | 29/07/24 | 05/08/24 | 6 days | 29/07/24 | 05/08/24 | 0 days | 0 days | 6 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.10.3 |  |  |  |  | STGi (UK) migration | 100% | 09/09/24 | 13/09/24 | 5 days | 09/09/24 | 13/09/24 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.10.4 |  |  |  |  | Maintenance window between cycle 2 and 3 | 100% | 20/09/24 | 20/09/24 | 1 day | 20/09/24 | 20/09/24 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.10.5 |  |  |  |  | First View of Migrated ISD Data | 100% | 23/09/24 | 27/09/24 | 5 days | 23/09/24 | 27/09/24 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.10.6 |  |  |  |  | Second View of Migrated ISD Data (HXT1 (SIT B) migration) | 100% | 23/09/24 | 27/09/24 | 5 days | 23/09/24 | 27/09/24 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.10.7 |  |  |  |  | Final Cycle 3 Migrated ISD Data | 100% | 07/10/24 | 11/10/24 | 5 days | 07/10/24 | 11/10/24 | 0 days | 0 days | 5 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.10.8 |  |  |  |  | Create ISD Template inc. DIP ID | 100% | 16/09/24 | 01/11/24 | 35 days? | 16/09/24 | 01/11/24 | 0 days | 0 days | 35 days? | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.10.9 |  |  |  |  | Publish Qualification ISD | 100% | 14/10/24 | 25/10/24 | 10 days? | 14/10/24 | 25/10/24 | 0 days | 0 days | 10 days? | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.6.11 |  |  |  |  | BETA Testing 1 - Test Data | 58% | 01/11/24 | 09/12/24 | 27 days | 01/11/24 | 15/11/24 | 0 days | 16 days | 27 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.11.1 |  |  |  |  | Provide Example MPAN File | 100% | 01/11/24 | 05/11/24 | 3 days | 01/11/24 | 05/11/24 | 0 days | 0 days | 3 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.11.2 |  |  |  |  | Load Example MPAN File | 100% | 06/11/24 | 13/11/24 | 6 days | 06/11/24 | 13/11/24 | 0 days | 0 days | 6 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.11.3 |  |  |  |  | Industry Standing Data (ISD) | 100% | 06/11/24 | 13/11/24 | 6 days | 06/11/24 | 13/11/24 | 0 days | 0 days | 6 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.11.4 |  |  |  |  | Market Domain Data (MDD) | 100% | 06/11/24 | 13/11/24 | 6 days | 06/11/24 | 13/11/24 | 0 days | 0 days | 6 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.11.5 |  |  |  |  | Load ISD / MDD Data | 100% | 06/12/24 | 06/12/24 | 1 day | 14/11/24 | 14/11/24 | 16 days | 16 days | 1 day | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.11.6 |  |  |  |  | Create QTC sets and Test MPANs via QTF | 100% | 06/12/24 | 06/12/24 | 1 day | 14/11/24 | 14/11/24 | 16 days | 16 days | 1 day | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.11.7 |  |  |  |  | Create QTC sets in ADO via QTF | 100% | 06/12/24 | 06/12/24 | 1 day | 14/11/24 | 14/11/24 | 16 days | 16 days | 1 day | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.11.8 |  |  |  |  | Provide Test MPANs (Suppliers only) allocated to specfic QTC's | 100% | 06/12/24 | 06/12/24 | 1 day | 14/11/24 | 14/11/24 | 16 days | 16 days | 1 day | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.11.9 |  |  |  |  | Load Test MPANs | 100% | 09/12/24 | 09/12/24 | 1 day | 15/11/24 | 15/11/24 | 16 days | 16 days | 1 day | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.11.10 |  |  |  |  | BETA Testing 2 - Test Data | 16% | 08/01/25 | 22/01/25 | 11 days | 08/01/25 | 22/01/25 | 0 days | 0 days | 11 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes |  | 17/12/24 - Expanded QTF section has been included.
9 | 1.6.4.1.6.6.11.10.1 |  |  |  |  | Provide Example MPAN File | 100% | 08/01/25 | 10/01/25 | 3 days | 08/01/25 | 10/01/25 | 0 days | 0 days | 3 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes |  | 17/12/24 - Expanded QTF section has been included.
9 | 1.6.4.1.6.6.11.10.2 |  |  |  |  | Load Example MPAN File | 20% | 13/01/25 | 20/01/25 | 6 days | 13/01/25 | 20/01/25 | 0 days | 0 days | 6 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes |  | 17/12/24 - Expanded QTF section has been included.
9 | 1.6.4.1.6.6.11.10.3 |  |  |  |  | Industry Standing Data (ISD) | 0% | 08/01/25 | 15/01/25 | 6 days | 08/01/25 | 15/01/25 | 0 days | 0 days | 6 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes |  | 17/12/24 - Expanded QTF section has been included.
9 | 1.6.4.1.6.6.11.10.4 |  |  |  |  | Market Domain Data (MDD) | 0% | 08/01/25 | 15/01/25 | 6 days | 08/01/25 | 15/01/25 | 0 days | 0 days | 6 days | Non-SIT S&A QT Test Team |  | 6.15 | Yes |  | 17/12/24 - Expanded QTF section has been included.
9 | 1.6.4.1.6.6.11.10.5 |  |  |  |  | Load ISD / MDD Data | 0% | 16/01/25 | 16/01/25 | 1 day | 16/01/25 | 16/01/25 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes |  | 17/12/24 - Expanded QTF section has been included.
9 | 1.6.4.1.6.6.11.10.6 |  |  |  |  | Create QTC sets and Test MPANs via QTF | 0% | 21/01/25 | 21/01/25 | 1 day | 21/01/25 | 21/01/25 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes |  | 17/12/24 - Expanded QTF section has been included.
9 | 1.6.4.1.6.6.11.10.7 |  |  |  |  | Create QTC sets in ADO via QTF | 0% | 21/01/25 | 21/01/25 | 1 day | 21/01/25 | 21/01/25 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes |  | 17/12/24 - Expanded QTF section has been included.
9 | 1.6.4.1.6.6.11.10.8 |  |  |  |  | Provide Test MPANs (Suppliers only) allocated to specfic QTC's | 0% | 21/01/25 | 21/01/25 | 1 day | 21/01/25 | 21/01/25 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes |  | 17/12/24 - Expanded QTF section has been included.
9 | 1.6.4.1.6.6.11.10.9 |  |  |  |  | Load Test MPANs | 0% | 22/01/25 | 22/01/25 | 1 day | 22/01/25 | 22/01/25 | 0 days | 0 days | 1 day | Non-SIT S&A QT Test Team |  | 6.15 | Yes |  | 17/12/24 - Expanded QTF section has been included.
7 | 1.6.4.1.6.6.12 |  |  |  |  | Wave 1 Test Data | 0% | 12/05/25 | 15/07/25 | 46 days | 12/05/25 | 15/07/25 | 1 day | 0 days | 46 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.12.1 |  |  |  |  | Test Data Request + Templates Completed | 0% | 21/04/25 | 12/05/25 | 16 days | 21/04/25 | 12/05/25 | 0 days | 0 days | 16 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.12.2 |  |  |  |  | Test Data Generated | 0% | 21/05/25 | 03/06/25 | 10 days | 21/05/25 | 03/06/25 | 0 days | 0 days | 10 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.12.3 |  |  |  |  | Test Data Loaded into QP Systems | 0% | 04/06/25 | 01/07/25 | 20 days | 04/06/25 | 01/07/25 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.12.4 |  |  |  |  | Test Data Loaded into QTF + ADO | 0% | 04/06/25 | 30/06/25 | 19 days | 04/06/25 | 30/06/25 | 0 days | 0 days | 19 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.6.13 |  |  |  |  | Wave 2 Test Data | 0% | 07/07/25 | 03/09/25 | 42 days | 07/07/25 | 03/09/25 | 1 day | 0 days | 42 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.13.1 |  |  |  |  | Test Data Request + Templates Completed | 0% | 16/06/25 | 07/07/25 | 16 days | 16/06/25 | 07/07/25 | 0 days | 0 days | 16 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.13.2 |  |  |  |  | Test Data Generated | 0% | 16/07/25 | 29/07/25 | 10 days | 16/07/25 | 29/07/25 | 0 days | 0 days | 10 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.13.3 |  |  |  |  | Test Data Loaded into QP Systems | 0% | 30/07/25 | 20/08/25 | 16 days | 30/07/25 | 20/08/25 | 0 days | 0 days | 16 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.13.4 |  |  |  |  | Test Data Loaded into QTF + ADO | 0% | 30/07/25 | 20/08/25 | 16 days | 30/07/25 | 20/08/25 | 0 days | 0 days | 16 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.6.14 |  |  |  |  | Wave 3 Test Data | 0% | 08/09/25 | 10/11/25 | 45 days | 08/09/25 | 10/11/25 | 1 day | 0 days | 45 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.14.1 |  |  |  |  | Test Data Request + Templates Completed | 0% | 19/08/25 | 08/09/25 | 15 days | 19/08/25 | 08/09/25 | 0 days | 0 days | 15 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.14.2 |  |  |  |  | Test Data Generated | 0% | 16/09/25 | 29/09/25 | 10 days | 16/09/25 | 29/09/25 | 0 days | 0 days | 10 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.14.3 |  |  |  |  | Test Data Loaded into QP Systems | 0% | 30/09/25 | 27/10/25 | 20 days | 30/09/25 | 27/10/25 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.14.4 |  |  |  |  | Test Data Loaded into QTF + ADO | 0% | 30/09/25 | 27/10/25 | 20 days | 30/09/25 | 27/10/25 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.6.15 |  |  |  |  | Wave 4 Test Data | 0% | 06/11/25 | 08/01/26 | 45 days | 06/11/25 | 08/01/26 | 1 day | 0 days | 45 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.15.1 |  |  |  |  | Test Data Request + Templates Completed | 0% | 17/10/25 | 06/11/25 | 15 days | 17/10/25 | 06/11/25 | 0 days | 0 days | 15 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.15.2 |  |  |  |  | Test Data Generated | 0% | 14/11/25 | 27/11/25 | 10 days | 14/11/25 | 27/11/25 | 0 days | 0 days | 10 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.15.3 |  |  |  |  | Test Data Loaded into QP Systems | 0% | 28/11/25 | 25/12/25 | 20 days | 28/11/25 | 25/12/25 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.15.4 |  |  |  |  | Test Data Loaded into QTF + ADO | 0% | 28/11/25 | 25/12/25 | 20 days | 28/11/25 | 25/12/25 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.6.16 |  |  |  |  | Governance | 81% | 01/07/24 | 28/03/25 | 195 days | 01/07/24 | 20/12/24 | 0 days | 70 days | 195 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.16.1 |  |  |  |  | Onboarding Strategy and Develop Training Requirements & Materials Inc. Day in the Life | 100% | 01/07/24 | 13/12/24 | 120 days | 01/07/24 | 29/11/24 | 0 days | 10 days | 120 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.16.2 |  |  |  |  | Design Approach & Set-Up ADO Tool for Test & Defect Management Tool | 100% | 01/07/24 | 26/07/24 | 20 days | 01/07/24 | 26/07/24 | 0 days | 0 days | 20 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.16.3 |  |  |  |  | Knowledge Transfer, Training, Demonstrations, Documentation, Governance | 100% | 30/08/24 | 17/12/24 | 78 days | 30/08/24 | 17/12/24 | 0 days | 0 days | 78 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.16.4 |  |  |  |  | BETA Testing | 100% | 01/11/24 | 17/12/24 | 33 days | 01/11/24 | 20/12/24 | 0 days | -3 days | 33 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
8 | 1.6.4.1.6.6.16.5 |  |  |  |  | BETA Testing 2 | 0% | 08/01/25 | 28/03/25 | 58 days | N/A | N/A | 0 days | 0 days | 58 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
7 | 1.6.4.1.6.6.17 |  |  |  |  | Qualification Testing Framework Readiness Confirmed | 0% | 28/03/25 | 28/03/25 | 0 days | 28/03/25 | 28/03/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.12 | Yes
7 | 1.6.4.1.6.6.18 | T2 | T2-QU-1100 |  |  | Qualification Testing Wave Readiness Confirmed | 0% | 21/08/25 | 21/08/25 | 0 days | 21/08/25 | 21/08/25 | 0 days | -1 day | 0 days |  | Approved | 6.13 | Yes |  | 19/12/24 - QAG approved the creation of this milestone. Programme will continue to develop the dependencies feeding into it in due course.
5 | 1.6.4.1.7 |  |  |  |  | Wave Allocation | 100% | 02/01/24 | 28/06/24 | 129 days | 02/01/24 | 28/06/24 | 0 days | 0 days | 1 day | N/A |  | 5.24 | Yes
6 | 1.6.4.1.7.1 |  |  |  |  | Draft Pre-Qualification Submission (PQS) document | 100% | 02/01/24 | 29/01/24 | 20 days | 02/01/24 | 29/01/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.4.1.7.2 |  |  |  |  | Publish PQS document | 100% | 31/01/24 | 31/01/24 | 1 day | 31/01/24 | 31/01/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.4.1.7.3 |  |  |  |  | PQS Submission window | 100% | 05/02/24 | 26/04/24 | 60 days | 05/02/24 | 26/04/24 | 0 days | 0 days | 0 days | Participants |  | 5.24 | Yes
6 | 1.6.4.1.7.4 | T3 | T3-QU-0118 | QAG |  | Pre-Qualification Submission and PIT Test Plan Deadline for Submission​ | 100% | 26/04/24 | 26/04/24 | 0 days | 26/04/24 | 26/04/24 | 1 day | 0 days | 0 days | Participants |  | 5.25 | Yes
6 | 1.6.4.1.7.5 |  |  |  |  | PQS Review by Code Bodies | 100% | 29/04/24 | 31/05/24 | 25 days | 29/04/24 | 31/05/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.4.1.7.6 |  |  |  |  | Draft Wave Allocations | 100% | 03/06/24 | 21/06/24 | 15 days | 03/06/24 | 21/06/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5.24 | Yes
6 | 1.6.4.1.7.7 | T3 | T3-QU-0012 | QAG |  | Confirmation of participant Qualification Wave allocation | 100% | 28/06/24 | 28/06/24 | 0 days | 28/06/24 | 28/06/24 | 1 day | 0 days | 0 days | Code Bodies |  | 5.28 | Yes
4 | 1.6.4.2 |  |  |  |  | Qualification Wave 1 | 0% | 05/05/25 | 15/04/26 | 248 days | 24/03/25 | 10/04/26 | 30 days | 3 days | 19 days | N/A |  | 6.13 | Yes
5 | 1.6.4.2.1 |  |  |  |  | Qualification Wave 1 QAD Prep | 0% | 05/05/25 | 22/08/25 | 80 days | 24/03/25 | 11/07/25 | 30 days | 30 days | 0 days | N/A |  | 6.13 | Yes
6 | 1.6.4.2.1.1 |  |  |  |  | Initial QAD Submission window opens | 0% | 05/05/25 | 05/05/25 | 0 days | 05/05/25 | 05/05/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.2.1.2 |  |  |  |  | Qualification Wave 1 Participants Submit Initial QAD | 0% | 05/05/25 | 11/07/25 | 50 days | 05/05/25 | 11/07/25 | 0 days | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.2.1.3 | T3 | T3-QU-0094 | QAG |  | Qualification Wave 1 Participants have submitted their initial QAD | 0% | 14/07/25 | 14/07/25 | 0 days | 14/07/25 | 14/07/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.2.1.4 |  |  |  |  | Code Bodies review of Wave 1 Participants Initial QAD | 0% | 14/07/25 | 22/08/25 | 30 days | 14/07/25 | 22/08/25 | 0 days | 0 days | 0 days | Code Bodies |  | 6.13 | Yes
6 | 1.6.4.2.1.5 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 0% | 22/08/25 | 22/08/25 | 0 days | 22/08/25 | 22/08/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.13 | Yes
5 | 1.6.4.2.2 |  |  |  |  | Qualification Wave 1 Test Prep | 0% | 26/05/25 | 15/08/25 | 60 days | 14/04/25 | 04/07/25 | 30 days | 30 days | 0 days | N/A |  | 6.13 | Yes
6 | 1.6.4.2.2.1 | T3 | T3-QU-0017 | QAG |  | Confirmation from Qualification Wave 1 Participants that DIP onboarding has commenced | 0% | 26/05/25 | 26/05/25 | 0 days | 26/05/25 | 26/05/25 | 0 days | -1 day | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.2.2.2 |  |  |  |  | Qualification Wave 1 Participants DIP Onboarding Window | 0% | 26/05/25 | 11/07/25 | 35 days | 26/05/25 | 11/07/25 | 0 days | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.2.2.3 | T3 | T3-TE-0017 | QAG |  | Confirmation from Qualification Wave 1 Participants that DIP onboarding has completed | 0% | 11/07/25 | 11/07/25 | 0 days | 11/07/25 | 11/07/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes |  | 26/11/24 - There was duplicative activity in the SIT plan, which we propose to remove. We also propose to move the milestone ID associated with that activity to this task, this is going to QAG for approval.
6 | 1.6.4.2.2.4 | T3 | T3-QU-0095 | QAG |  | Qualification Wave 1 Participants' to provide status of PIT completion and submit QT Test Plan | 0% | 13/06/25 | 13/06/25 | 0 days | 16/06/25 | 16/06/25 | -1 day | -2 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.2.2.5 |  |  |  |  | Review of Participants' PIT Status and QT Test Plan | 0% | 13/06/25 | 03/07/25 | 15 days | 16/06/25 | 04/07/25 | -1 day | -1 day | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.2.2.6 | T3 | T3-QU-0016 | QAG |  | Qualification Test Plans for Wave 1 Participants approved | 0% | 03/07/25 | 03/07/25 | 0 days | 04/07/25 | 04/07/25 | 0 days | -1 day | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.2.2.7 | T3 | T3-QU-0096 | QAG |  | Qualification Wave 1 Participants have submitted PIT Test Completion Report and evidence for QT Entry | 0% | 14/07/25 | 14/07/25 | 0 days | 14/07/25 | 14/07/25 | 0 days | -1 day | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.2.2.8 |  |  |  |  | Review of Participants PIT Test Completion Report | 0% | 14/07/25 | 15/08/25 | 25 days | 14/07/25 | 15/08/25 | 0 days | 0 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.2.2.9 |  |  |  |  | Onboarding to QTF & ADO | 0% | 14/07/25 | 15/08/25 | 25 days | 14/07/25 | 15/08/25 | 0 days | 0 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
5 | 1.6.4.2.3 |  |  |  |  | Qualification Wave 1 QT Execution | 0% | 18/08/25 | 09/01/26 | 105 days | 18/08/25 | 09/01/26 | 0 days | 0 days | 5 days | N/A |  | 6.13 | Yes
6 | 1.6.4.2.3.1 |  |  |  |  | Review Entry Criteria Evidence for each Wave 1 Participant | 0% | 18/08/25 | 22/08/25 | 5 days | 18/08/25 | 22/08/25 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.2.3.2 | T3 | T3-QU-0027 | QAG |  | Qualification Wave 1 Participant Test Readiness Confirmed | 0% | 22/08/25 | 22/08/25 | 0 days | 22/08/25 | 22/08/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.2.3.3 | T3 | T3-QU-0028 | QAG |  | Qualification Wave 1 QT Execution Start | 0% | 25/08/25 | 25/08/25 | 0 days | 25/08/25 | 25/08/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.2.3.4 |  |  |  |  | Qualification Wave 1 QT Execution Window | 0% | 25/08/25 | 09/01/26 | 100 days | 25/08/25 | 09/01/26 | 0 days | 0 days | 5 days | Participants |  | 6.13 | Yes
6 | 1.6.4.2.3.5 | T3 | T3-QU-0054 | QAG |  | Qualification Wave 1 QT Projected Execution End | 0% | 09/01/26 | 09/01/26 | 0 days | 09/01/26 | 09/01/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
5 | 1.6.4.2.4 |  |  |  |  | Qualification Wave 1 Exit | 0% | 25/08/25 | 15/04/26 | 168 days | 25/08/25 | 15/04/26 | 0 days | 0 days | 19 days | N/A |  | 6.13 | Yes
6 | 1.6.4.2.4.1 |  |  |  |  | Final QAD Submission window opens | 0% | 25/08/25 | 25/08/25 | 0 days | 25/08/25 | 25/08/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.2.4.2 |  |  |  |  | Qualification Wave 1 Participants submit their Final QAD | 0% | 25/08/25 | 16/01/26 | 105 days | 25/08/25 | 16/01/26 | 0 days | 0 days | 5 days | Participants |  | 6.13 | Yes
6 | 1.6.4.2.4.3 | T3 | T3-QU-0097 | QAG |  | Qualification Wave 1 Participants have submitted their final QAD | 0% | 16/01/26 | 16/01/26 | 0 days | 16/01/26 | 16/01/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.2.4.4 |  |  |  |  | Completion of Code Bodies review of Final QAD | 0% | 19/01/26 | 06/03/26 | 35 days | 19/01/26 | 06/03/26 | 0 days | 0 days | 15 days | Code Bodies |  | 6.13 | Yes
6 | 1.6.4.2.4.5 |  |  |  |  | QAD Sign Off deadline | 0% | 20/03/26 | 20/03/26 | 1 day | 20/03/26 | 20/03/26 | 0 days | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.2.4.6 | T2 | T2-QU-0150 | QAG |  | Qualification Wave 1 Participants Qualification approved by BSC PAB and REC Manager | 0% | 15/04/26 | 15/04/26 | 0 days | 15/04/26 | 15/04/26 | 1 day | 0 days | 0 days | Code Bodies |  | 6.13 | Yes
4 | 1.6.4.3 |  |  |  |  | Qualification Wave 2 | 0% | 09/06/25 | 28/05/26 | 254 days | 09/06/25 | 28/05/26 | 0 days | 0 days | 5 days | N/A |  | 6.13 | Yes
5 | 1.6.4.3.1 |  |  |  |  | Qualification Wave 2 QAD Prep | 0% | 09/06/25 | 17/10/25 | 95 days | 09/06/25 | 17/10/25 | 0 days | 0 days | -1 day | N/A |  | 6.13 | Yes
6 | 1.6.4.3.1.1 |  |  |  |  | Initial QAD Submission window opens | 0% | 09/06/25 | 09/06/25 | 0 days | 09/06/25 | 09/06/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.3.1.2 |  |  |  |  | Qualification Wave 2 Participants Submit Initial QAD | 0% | 09/06/25 | 12/09/25 | 70 days | 09/06/25 | 12/09/25 | 0 days | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.3.1.3 | T3 | T3-QU-0098 | QAG |  | Qualification Wave 2 Participants have submitted their initial QAD | 0% | 12/09/25 | 12/09/25 | 0 days | 12/09/25 | 12/09/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.3.1.4 |  |  |  |  | Code Bodies review of Wave 2 Participants' Initial QAD | 0% | 15/09/25 | 17/10/25 | 25 days | 15/09/25 | 17/10/25 | 0 days | 0 days | -1 day | Code Bodies |  | 6.13 | Yes
6 | 1.6.4.3.1.5 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 0% | 17/10/25 | 17/10/25 | 0 days | 17/10/25 | 17/10/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.13 | Yes
5 | 1.6.4.3.2 |  |  |  |  | Qualification Wave 2 Test Prep | 0% | 21/07/25 | 10/10/25 | 60 days | 21/07/25 | 10/10/25 | 0 days | 0 days | 0 days | N/A |  | 6.13 | Yes
6 | 1.6.4.3.2.1 | T3 | T3-QU-0021 | QAG |  | Confirmation from Qualification Wave 2 Participants that DIP Onboarding has commenced | 0% | 21/07/25 | 21/07/25 | 0 days | 21/07/25 | 21/07/25 | 0 days | -1 day | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.3.2.2 |  |  |  |  | Qualification Wave 2 Participants DIP Onboarding Window | 0% | 21/07/25 | 05/09/25 | 35 days | 21/07/25 | 05/09/25 | 0 days | 0 days | -5 days | Participants |  | 6.13 | Yes
6 | 1.6.4.3.2.3 |  |  |  |  | Confirmation from Qualificiation Wave 2 Participants that DIP onboarding has completed | 0% | 05/09/25 | 05/09/25 | 0 days | 05/09/25 | 05/09/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.3.2.4 | T3 | T3-QU-0099 | QAG |  | Qualification Wave 2 Participants' to provide status of PIT completion and submit QT Test Plan | 0% | 18/08/25 | 18/08/25 | 0 days | 18/08/25 | 18/08/25 | 0 days | -1 day | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.3.2.5 |  |  |  |  | Review of Participants' PIT Status and QT Test Plan | 0% | 18/08/25 | 05/09/25 | 15 days | 18/08/25 | 05/09/25 | 0 days | 0 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.3.2.6 | T3 | T3-QU-0020 | QAG |  | Qualification Test Plans for Wave 2 Participants approved | 0% | 05/09/25 | 05/09/25 | 0 days | 05/09/25 | 05/09/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.3.2.7 | T3 | T3-QU-0100 | QAG |  | Qualification Wave 2 Participants have submitted PIT Test Completion Report and evidence for QT entry | 0% | 08/09/25 | 08/09/25 | 0 days | 08/09/25 | 08/09/25 | 0 days | -1 day | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.3.2.8 |  |  |  |  | Review of Participants' PIT Test Completion Report | 0% | 08/09/25 | 10/10/25 | 25 days | 08/09/25 | 10/10/25 | 0 days | 0 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.3.2.9 |  |  |  |  | Onboarding to QTF & ADO | 0% | 08/09/25 | 10/10/25 | 25 days | 08/09/25 | 10/10/25 | 0 days | 0 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
5 | 1.6.4.3.3 |  |  |  |  | Qualification Wave 2 QT Execution | 0% | 13/10/25 | 27/02/26 | 100 days | 13/10/25 | 27/02/26 | 0 days | 0 days | 1 day | N/A |  | 6.13 | Yes
6 | 1.6.4.3.3.1 |  |  |  |  | Review Entry Criteria Evidence for each Wave 2 Participant | 0% | 13/10/25 | 17/10/25 | 5 days | 13/10/25 | 17/10/25 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.3.3.2 | T3 | T3-QU-0033 | QAG |  | Qualification Wave 2 Participant Test Readiness Confirmed | 0% | 17/10/25 | 17/10/25 | 0 days | 17/10/25 | 17/10/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.3.3.3 | T3 | T3-QU-0034 | QAG |  | Qualification Wave 2 Execution Start | 0% | 20/10/25 | 20/10/25 | 0 days | 20/10/25 | 20/10/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.3.3.4 |  |  |  |  | Qualification Wave 2 QT Execution Window | 0% | 20/10/25 | 27/02/26 | 95 days | 20/10/25 | 27/02/26 | 0 days | 0 days | 1 day | Participants |  | 6.13 | Yes
6 | 1.6.4.3.3.5 | T3 | T3-QU-0055 | QAG |  | Qualfication Wave 2 QT Execution End | 0% | 27/02/26 | 27/02/26 | 0 days | 27/02/26 | 27/02/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
5 | 1.6.4.3.4 |  |  |  |  | Qualification Wave 2 Exit | 0% | 20/10/25 | 28/05/26 | 159 days | 20/10/25 | 28/05/26 | 0 days | 0 days | 6 days | N/A |  | 6.13 | Yes
6 | 1.6.4.3.4.1 |  |  |  |  | Final QAD Submission window opens | 0% | 20/10/25 | 20/10/25 | 0 days | 20/10/25 | 20/10/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.3.4.2 |  |  |  |  | Qualification Wave 2 Participants submit their Final QAD | 0% | 20/10/25 | 06/03/26 | 100 days | 20/10/25 | 06/03/26 | 0 days | 0 days | 1 day | Participants |  | 6.13 | Yes
6 | 1.6.4.3.4.3 | T3 | T3-QU-0101 | QAG |  | Qualification Wave 2 Participants have submitted their final QAD | 0% | 06/03/26 | 06/03/26 | 0 days | 06/03/26 | 06/03/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.3.4.4 |  |  |  |  | Completion of Code Bodies review of Final QAD | 0% | 09/03/26 | 13/04/26 | 26 days | 09/03/26 | 13/04/26 | 0 days | 0 days | -1 day | Code Bodies |  | 6.13 | Yes
6 | 1.6.4.3.4.5 |  |  |  |  | QAD Sign Off deadline | 0% | 20/04/26 | 20/04/26 | 1 day | 20/04/26 | 20/04/26 | 0 days | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.3.4.6 | T2 | T2-QU-0200 | QAG |  | Qualification Wave 2 Participants Qualification approved by BSC PAB and REC Manager | 0% | 28/05/26 | 28/05/26 | 0 days | 28/05/26 | 28/05/26 | 1 day | 0 days | 0 days | Code Bodies |  | 6.13 | Yes |  | 14/11/24 - Updated to align with the actual PAB date.
4 | 1.6.4.4 |  |  |  |  | Qualification Wave 3 | 0% | 11/08/25 | 30/07/26 | 254 days | 11/08/25 | 30/07/26 | 0 days | 0 days | 15 days | N/A |  | 6.13 | Yes
5 | 1.6.4.4.1 |  |  |  |  | Qualification Wave 3 QAD Prep | 0% | 11/08/25 | 19/12/25 | 95 days | 11/08/25 | 19/12/25 | 0 days | 0 days | 0 days | N/A |  | 6.13 | Yes
6 | 1.6.4.4.1.1 |  |  |  |  | Initial QAD Submission window opens | 0% | 11/08/25 | 11/08/25 | 0 days | 11/08/25 | 11/08/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.4.1.2 |  |  |  |  | Qualification Wave 3 Participants Submit Initial QAD | 0% | 11/08/25 | 07/11/25 | 65 days | 11/08/25 | 07/11/25 | 0 days | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.4.1.3 | T3 | T3-QU-0102 | QAG |  | Qualification Wave 3 Participants have submitted their initial QAD | 0% | 07/11/25 | 07/11/25 | 0 days | 07/11/25 | 07/11/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.4.1.4 |  |  |  |  | Code Bodies review of Wave 3 Participants' Initial QAD | 0% | 10/11/25 | 19/12/25 | 30 days | 10/11/25 | 19/12/25 | 0 days | 0 days | 0 days | Code Bodies |  | 6.13 | Yes
6 | 1.6.4.4.1.5 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 0% | 19/12/25 | 19/12/25 | 0 days | 19/12/25 | 19/12/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.13 | Yes
5 | 1.6.4.4.2 |  |  |  |  | Qualification Wave 3 Test Prep | 0% | 15/09/25 | 12/12/25 | 65 days | 15/09/25 | 12/12/25 | 0 days | 0 days | 0 days | N/A |  | 6.13 | Yes
6 | 1.6.4.4.2.1 | T3 | T3-QU-0025 | QAG |  | Confirmation from Qualification Wave 3 Participants that DIP Onboarding has commenced | 0% | 15/09/25 | 15/09/25 | 0 days | 15/09/25 | 15/09/25 | 0 days | -1 day | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.4.2.2 |  |  |  |  | Qualification Wave 3 Participants DIP Onboarding window | 0% | 15/09/25 | 31/10/25 | 35 days | 15/09/25 | 31/10/25 | 0 days | 0 days | -5 days | Participants |  | 6.13 | Yes
6 | 1.6.4.4.2.3 |  |  |  |  | Confirmation from Qualification Wave 3 Participants that DIP onboarding has completed | 0% | 31/10/25 | 31/10/25 | 0 days | 31/10/25 | 31/10/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.4.2.4 | T3 | T3-QU-0103 | QAG |  | Qualification Wave 3 Participants' to provide status of PIT completion and submit QT Test Plan | 0% | 20/10/25 | 20/10/25 | 0 days | 20/10/25 | 20/10/25 | 0 days | -1 day | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.4.2.5 |  |  |  |  | Review of Participants' PIT Status and QT Test Plan | 0% | 20/10/25 | 07/11/25 | 15 days | 20/10/25 | 07/11/25 | 0 days | 0 days | 0 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.4.2.6 | T3 | T3-QU-0024 | QAG |  | Qualification Test Plans for Wave 3 Participants approved | 0% | 07/11/25 | 07/11/25 | 0 days | 07/11/25 | 07/11/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.4.2.7 | T3 | T3-QU-0104 | QAG |  | Qualification Wave 3 Participants have submitted PIT Test Completion Report and evidence for QT Entry | 0% | 10/11/25 | 10/11/25 | 0 days | 10/11/25 | 10/11/25 | 0 days | -1 day | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.4.2.8 |  |  |  |  | Review of Participants' PIT Test Completion Report | 0% | 10/11/25 | 12/12/25 | 25 days | 10/11/25 | 12/12/25 | 0 days | 0 days | -5 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.4.2.9 |  |  |  |  | Onboarding to QTF & ADO | 0% | 10/11/25 | 12/12/25 | 25 days | 10/11/25 | 12/12/25 | 0 days | 0 days | -5 days |  |  | 6.13 | Yes
5 | 1.6.4.4.3 |  |  |  |  | Qualification Wave 3 QT Execution | 0% | 03/11/25 | 24/03/26 | 102 days | 03/11/25 | 24/03/26 | 0 days | 0 days | 2 days | N/A |  | 6.13 | Yes
6 | 1.6.4.4.3.1 |  |  |  |  | Review Entry Criteria Evidence for each Wave 3 Participant | 0% | 15/12/25 | 19/12/25 | 5 days | 15/12/25 | 19/12/25 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.4.3.2 | T3 | T3-QU-0038 | QAG |  | Qualification Wave 3 Participant Test Readiness confirmed | 0% | 19/12/25 | 19/12/25 | 0 days | 19/12/25 | 19/12/25 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.4.3.3 | T3 | T3-QU-0039 | QAG |  | Qualification Wave 3 Execution Start | 0% | 12/01/26 | 12/01/26 | 0 days | 12/01/26 | 12/01/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.4.3.4 |  |  |  |  | Qualification Wave 3 QT Execution Window | 0% | 12/01/26 | 15/05/26 | 90 days | 12/01/26 | 15/05/26 | 0 days | 0 days | -5 days | Participants |  | 6.13 | Yes
6 | 1.6.4.4.3.5 | T3 | T3-QU-0056 | QAG |  | Qualification Wave 3 Projected Execution End | 0% | 15/05/26 | 15/05/26 | 0 days | 15/05/26 | 15/05/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
5 | 1.6.4.4.4 |  |  |  |  | Qualification Wave 3 Exit | 0% | 12/01/26 | 30/07/26 | 144 days | 12/01/26 | 30/07/26 | 0 days | 0 days | 0 days | N/A |  | 6.13 | Yes
6 | 1.6.4.4.4.1 |  |  |  |  | Final QAD Submission window opens | 0% | 12/01/26 | 12/01/26 | 0 days | 12/01/26 | 12/01/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.4.4.2 |  |  |  |  | Qualification Wave 3 Participants submit their Final QAD | 0% | 12/01/26 | 22/05/26 | 95 days | 12/01/26 | 22/05/26 | 0 days | 0 days | -5 days | Participants |  | 6.13 | Yes
6 | 1.6.4.4.4.3 | T3 | T3-QU-0105 | QAG |  | Qualification Wave 3 Participants have submitted their Final QAD | 0% | 22/05/26 | 22/05/26 | 0 days | 22/05/26 | 22/05/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.4.4.4 |  |  |  |  | Completion of Code Bodies review of Final QAD | 0% | 25/05/26 | 19/06/26 | 20 days | 25/05/26 | 19/06/26 | 0 days | 0 days | 0 days | Code Bodies |  | 6.13 | Yes
6 | 1.6.4.4.4.5 |  |  |  |  | QAD Sign Off deadline | 0% | 26/06/26 | 26/06/26 | 1 day | 26/06/26 | 26/06/26 | 0 days | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.4.4.6 | T2 | T2-QU-0250 | QAG |  | Qualification Wave 3 Participants Qualification approved by BSC PAB and REC Manager | 0% | 30/07/26 | 30/07/26 | 0 days | 30/07/26 | 30/07/26 | 1 day | 0 days | 0 days | Code Bodies |  | 6.13 | Yes
4 | 1.6.4.5 |  |  |  |  | Qualification Wave 4 | 0% | 20/10/25 | 28/01/27 | 334 days | 20/10/25 | 28/01/27 | 0 days | 0 days | 85 days | N/A |  | 6.13 | Yes
5 | 1.6.4.5.1 |  |  |  |  | Qualification Wave 4 QAD Prep | 0% | 20/10/25 | 27/02/26 | 95 days | 20/10/25 | 27/02/26 | 0 days | 0 days | -4 days | N/A |  | 6.13 | Yes
6 | 1.6.4.5.1.1 |  |  |  |  | Initial QAD Submission window opens | 0% | 20/10/25 | 20/10/25 | 0 days | 20/10/25 | 20/10/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.5.1.2 |  |  |  |  | Qualification Wave 4 Participants Submit Initial QAD | 0% | 20/10/25 | 16/01/26 | 65 days | 20/10/25 | 16/01/26 | 0 days | 0 days | -5 days | Participants |  | 6.13 | Yes
6 | 1.6.4.5.1.3 | T3 | T3-QU-0106 | QAG |  | Qualification Wave 4 Participants have submitted their Initial QAD | 0% | 16/01/26 | 16/01/26 | 0 days | 16/01/26 | 16/01/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.5.1.4 |  |  |  |  | Code Bodies review of Wave 4 Participants' Initial QAD | 0% | 19/01/26 | 27/02/26 | 30 days | 19/01/26 | 27/02/26 | 0 days | 0 days | 1 day | Code Bodies |  | 6.13 | Yes
6 | 1.6.4.5.1.5 |  |  |  |  | Completion of Code Bodies review of Initial QAD | 0% | 27/02/26 | 27/02/26 | 0 days | 27/02/26 | 27/02/26 | 1 day | 0 days | 0 days | Code Bodies |  | 6.13 | Yes
5 | 1.6.4.5.2 |  |  |  |  | Qualification Wave 4 Test Prep | 0% | 03/11/25 | 13/02/26 | 75 days | 03/11/25 | 13/02/26 | 0 days | 0 days | 8 days | N/A |  | 6.13 | Yes
6 | 1.6.4.5.2.1 | T3 | T3-QU-0031 | QAG |  | Confirmation from Qualification 4 Participants that DIP Onboarding has commenced | 0% | 03/11/25 | 03/11/25 | 0 days | 03/11/25 | 03/11/25 | 0 days | -1 day | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.5.2.2 |  |  |  |  | Qualification Wave 4 Participants DIP Onboarding Window | 0% | 03/11/25 | 19/12/25 | 35 days | 03/11/25 | 19/12/25 | 0 days | 0 days | -7 days | Participants |  | 6.13 | Yes
6 | 1.6.4.5.2.3 |  |  |  |  | Confirmation from Qualification Wave 4 Participants that DIP onboarding has completed | 0% | 19/12/25 | 19/12/25 | 0 days | 19/12/25 | 19/12/25 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.5.2.4 | T3 | T3-QU-0107 | QAG |  | Qualification Wave 4 Participants' to provide status of PIT completion and submit QT Test Plan | 0% | 08/12/25 | 08/12/25 | 0 days | 08/12/25 | 08/12/25 | 0 days | -1 day | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.5.2.5 |  |  |  |  | Review of Participants' PIT Status and QT Test Plan | 0% | 08/12/25 | 09/01/26 | 25 days | 08/12/25 | 09/01/26 | 0 days | 0 days | 9 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.5.2.6 | T3 | T3-QU-0030 | QAG |  | Qualification Test Plans for Qualification Wave 4 Participants approved | 0% | 09/01/26 | 09/01/26 | 0 days | 09/01/26 | 09/01/26 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.5.2.7 | T3 | T3-QU-0108 | QAG |  | Qualification Wave 4 Participants have submitted PIT Test Completion Report and evidence for QT entry | 0% | 09/01/26 | 09/01/26 | 0 days | 09/01/26 | 09/01/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.5.2.8 |  |  |  |  | Review of Participants' PIT Test Completion Report | 0% | 12/01/26 | 13/02/26 | 25 days | 12/01/26 | 13/02/26 | 0 days | 0 days | -5 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.5.2.9 |  |  |  |  | Onboarding to QTF & ADO | 0% | 12/01/26 | 13/02/26 | 25 days | 12/01/26 | 13/02/26 | 0 days | 0 days | -5 days | Code Bodies, Non-SIT S&A QT Test Team |  | 6.13 | Yes
5 | 1.6.4.5.3 |  |  |  |  | Qualification Wave 4 QT Execution | 0% | 02/03/26 | 17/07/26 | 100 days | 02/03/26 | 17/07/26 | 0 days | 0 days | -1 day | N/A |  | 6.13 | Yes
6 | 1.6.4.5.3.1 |  |  |  |  | Review Entry Criteria Evidence for each Wave 4 Participant | 0% | 02/03/26 | 06/03/26 | 5 days | 02/03/26 | 06/03/26 | 0 days | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.5.3.2 | T3 | T3-QU-0043 | QAG |  | Qualification Wave 4 Participant Test Readiness Confirmed | 0% | 06/03/26 | 06/03/26 | 0 days | 06/03/26 | 06/03/26 | 1 day | 0 days | 0 days | Non-SIT S&A QT Test Team |  | 6.13 | Yes
6 | 1.6.4.5.3.3 | T3 | T3-QU-0044 | QAG |  | Qualification Wave 4 QT Execution Start | 0% | 09/03/26 | 09/03/26 | 0 days | 09/03/26 | 09/03/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.5.3.4 |  |  |  |  | Qualification Wave 4 QT Execution Window | 0% | 09/03/26 | 17/07/26 | 95 days | 09/03/26 | 17/07/26 | 0 days | 0 days | -1 day | Participants |  | 6.13 | Yes
6 | 1.6.4.5.3.5 | T3 | T3-QU-0057 | QAG |  | Qualification Wave 4 Projected Execution End | 0% | 17/07/26 | 17/07/26 | 0 days | 17/07/26 | 17/07/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
5 | 1.6.4.5.4 |  |  |  |  | Qualification Wave 4 Exit | 0% | 09/03/26 | 24/09/26 | 144 days | 09/03/26 | 24/09/26 | 0 days | 0 days | -6 days | N/A |  | 6.13 | Yes
6 | 1.6.4.5.4.1 |  |  |  |  | Final QAD Submission window opens | 0% | 09/03/26 | 09/03/26 | 0 days | 09/03/26 | 09/03/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.5.4.2 |  |  |  |  | Qualification Wave 4 Participants submit their Final QAD | 0% | 09/03/26 | 24/07/26 | 100 days | 09/03/26 | 24/07/26 | 0 days | 0 days | -1 day | Participants |  | 6.13 | Yes
6 | 1.6.4.5.4.3 | T3 | T3-QU-0109 | QAG |  | Qualification Wave 4 Participants have submitted their Final QAD | 0% | 24/07/26 | 24/07/26 | 0 days | 24/07/26 | 24/07/26 | 1 day | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.5.4.4 |  |  |  |  | Completion of Code Bodies review of Final QAD | 0% | 27/07/26 | 21/08/26 | 20 days | 27/07/26 | 21/08/26 | 0 days | 0 days | -5 days | Code Bodies |  | 6.13 | Yes
6 | 1.6.4.5.4.5 |  |  |  |  | QAD Sign Off deadline | 0% | 28/08/26 | 28/08/26 | 1 day | 28/08/26 | 28/08/26 | 0 days | 0 days | 0 days | Participants |  | 6.13 | Yes
6 | 1.6.4.5.4.6 | T3 | T2-QU-0300 | QAG |  | Qualification Wave 4 Participants Qualification approved by BSC PAB and REC Manager | 0% | 24/09/26 | 24/09/26 | 0 days | 24/09/26 | 24/09/26 | 1 day | 0 days | 0 days | Code Bodies |  | 6.13 | Yes
5 | 1.6.4.5.5 |  |  |  |  | Qualification Tier 1 Milestone | 0% | 28/10/26 | 28/01/27 | 66 days | 28/10/26 | 28/01/27 | 1 day | 0 days | 66 days |  |  | 6.13 | Yes
6 | 1.6.4.5.5.1 | T1 | T1-MI-5000 | PSG |  | All suppliers must be able to access MPANs under the new TOM (M14) | 0% | 28/10/26 | 28/10/26 | 0 days | 28/10/26 | 28/10/26 | 1 day | 0 days | 0 days | CPT |  | 6.13 | Yes
6 | 1.6.4.5.5.2 | T1 | T1-MI-5500 | PSG |  | All suppliers must be able to access MPANs under the new TOM (M14*) - Late Exit | 0% | 28/01/27 | 28/01/27 | 0 days | 28/01/27 | 28/01/27 | 1 day | 0 days | 0 days | CPT |  | 6.13 | Yes
2 | 1.7 |  |  |  |  | REGULATORY | 99% | 31/10/22 | 24/12/25 | 823 days | 31/10/22 | 24/12/25 | 0 days | 0 days | 143 days | N/A |  |  | Yes
3 | 1.7.1 |  |  |  |  | Baseline MHHS Code Changes | 100% | 31/10/22 | 23/08/24 | 475 days | 31/10/22 | 23/08/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.7.1.1 |  |  |  |  | Preparation and planning | 100% | 31/10/22 | 16/12/22 | 35 days | 31/10/22 | 16/12/22 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.7.1.1.1 |  |  |  |  | Impact assessment of Programme design on codes to determine required changes | 100% | 31/10/22 | 25/11/22 | 20 days | 31/10/22 | 25/11/22 | 0 days | 0 days | 0 days | Code Bodies,SRO Code Drafters |  | 5 | Yes
5 | 1.7.1.1.2 |  |  |  |  | Become 'code draft ready' | 100% | 31/10/22 | 16/12/22 | 35 days | 31/10/22 | 16/12/22 | 0 days | 0 days | 0 days | Code Bodies,SRO Code Drafters |  | 5 | Yes
5 | 1.7.1.1.3 |  |  |  |  | Soft start drafting where possible | 100% | 31/10/22 | 16/12/22 | 35 days | 31/10/22 | 16/12/22 | 0 days | 0 days | 0 days | Code Bodies,SRO Code Drafters |  | 5 | Yes
4 | 1.7.1.2 |  |  |  |  | Code drafting | 100% | 12/12/22 | 21/08/24 | 443 days | 12/12/22 | 21/08/24 | 0 days | 0 days | -2 days | N/A |  | 5 | Yes
5 | 1.7.1.2.1 |  |  |  |  | Data Services (BSC driven) | 100% | 12/12/22 | 24/05/23 | 118 days | 12/12/22 | 24/05/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.7.1.2.1.1 |  |  |  |  | Pre Code Drafting activities | 100% | 12/12/22 | 16/12/22 | 5 days | 12/12/22 | 16/12/22 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.1.2 |  |  |  |  | Code and subsidiary document drafting takes place offline | 100% | 03/01/23 | 27/01/23 | 19 days | 03/01/23 | 27/01/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.1.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | 30/01/23 | 13/02/23 | 11 days | 30/01/23 | 13/02/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.1.4 |  |  |  |  | External industry review via consultation | 100% | 14/02/23 | 13/03/23 | 20 days | 14/02/23 | 13/03/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.1.5 |  |  |  |  | Triage and action comments | 100% | 10/03/23 | 05/04/23 | 19 days | 10/03/23 | 05/04/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.1.6 |  |  |  |  | CDWG review | 100% | 06/04/23 | 17/05/23 | 30 days | 06/04/23 | 17/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.1.7 |  |  |  |  | CCAG review | 100% | 18/05/23 | 24/05/23 | 5 days | 18/05/23 | 24/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.1.8 | T2 | T2-RE-0100 | CCAG | MHHS-ART060 | Code drafting for Data Services topic area approved | 100% | 24/05/23 | 24/05/23 | 0 days | 24/05/23 | 24/05/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.7.1.2.2 |  |  |  |  | Metering (REC driven) | 100% | 12/12/22 | 24/05/23 | 118 days | 12/12/22 | 24/05/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.7.1.2.2.1 |  |  |  |  | Pre Code Drafting activities | 100% | 12/12/22 | 16/12/22 | 5 days | 12/12/22 | 16/12/22 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.2.2 |  |  |  |  | Code and subsidiary document drafting takes place offline | 100% | 03/01/23 | 27/01/23 | 19 days | 03/01/23 | 27/01/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.2.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | 30/01/23 | 13/02/23 | 11 days | 30/01/23 | 13/02/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.2.4 |  |  |  |  | External industry review via consultation | 100% | 14/02/23 | 13/03/23 | 20 days | 14/02/23 | 13/03/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.2.5 |  |  |  |  | Triage and action comments | 100% | 10/03/23 | 05/04/23 | 19 days | 10/03/23 | 05/04/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.2.6 |  |  |  |  | CDWG review | 100% | 06/04/23 | 17/05/23 | 30 days | 06/04/23 | 17/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.2.7 |  |  |  |  | CCAG review | 100% | 18/05/23 | 24/05/23 | 5 days | 18/05/23 | 24/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.2.8 | T2 | T2-RE-0150 | CCAG | MHHS-ART060 | Code drafting for Metering topic area approved | 100% | 24/05/23 | 24/05/23 | 0 days | 24/05/23 | 24/05/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.7.1.2.3 |  |  |  |  | BSC Central Services (BSC driven) | 100% | 22/02/23 | 27/09/23 | 156 days | 22/02/23 | 27/09/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.7.1.2.3.1 |  |  |  |  | Pre Code Drafting activities | 100% | 22/02/23 | 28/02/23 | 5 days | 22/02/23 | 28/02/23 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.3.2 |  |  |  |  | Code Drafting (offline) | 100% | 01/03/23 | 20/06/23 | 80 days | 01/03/23 | 20/06/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.3.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | 15/03/23 | 20/06/23 | 70 days | 15/03/23 | 20/06/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.3.4 |  |  |  |  | External industry review via consultation | 100% | 21/06/23 | 11/07/23 | 15 days | 21/06/23 | 11/07/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.3.5 |  |  |  |  | Triage and action comments | 100% | 10/07/23 | 03/08/23 | 19 days | 10/07/23 | 03/08/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.3.6 |  |  |  |  | CDWG review | 100% | 04/08/23 | 12/09/23 | 28 days | 04/08/23 | 12/09/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.3.7 |  |  |  |  | CCAG review | 100% | 13/09/23 | 27/09/23 | 11 days | 13/09/23 | 27/09/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.3.8 | T2 | T2-RE-0200 | CCAG | MHHS-ART060 | Code drafting for BSC Central Services topic area approved | 100% | 27/09/23 | 27/09/23 | 0 days | 27/09/23 | 27/09/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.7.1.2.4 |  |  |  |  | Registration (BSC & REC driven) | 100% | 22/02/23 | 23/08/23 | 131 days | 22/02/23 | 23/08/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.7.1.2.4.1 |  |  |  |  | Pre Code Drafting activities | 100% | 22/02/23 | 28/02/23 | 5 days | 22/02/23 | 28/02/23 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.4.2 |  |  |  |  | Code Drafting (offline) | 100% | 01/03/23 | 30/05/23 | 65 days | 01/03/23 | 30/05/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.4.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | 15/03/23 | 30/05/23 | 55 days | 15/03/23 | 30/05/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.4.4 |  |  |  |  | External industry review via consultation | 100% | 31/05/23 | 20/06/23 | 15 days | 31/05/23 | 20/06/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.4.5 |  |  |  |  | Triage and action comments | 100% | 19/06/23 | 13/07/23 | 19 days | 19/06/23 | 13/07/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.4.6 |  |  |  |  | CDWG review | 100% | 14/07/23 | 08/08/23 | 18 days | 14/07/23 | 08/08/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.4.7 |  |  |  |  | CCAG review | 100% | 09/08/23 | 23/08/23 | 11 days | 09/08/23 | 23/08/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.4.8 | T2 | T2-RE-0250 | CCAG | MHHS-ART060 | Code drafting for Registration topic area approved | 100% | 23/08/23 | 23/08/23 | 0 days | 23/08/23 | 23/08/23 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.7.1.2.5 |  |  |  |  | Governance and Qualification (BSC & REC driven) | 100% | 25/05/23 | 22/11/23 | 130 days | 25/05/23 | 22/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.7.1.2.5.1 |  |  |  |  | Pre Code Drafting activities | 100% | 25/05/23 | 31/05/23 | 5 days | 25/05/23 | 31/05/23 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.5.2 |  |  |  |  | Code Drafting (offline) | 100% | 01/06/23 | 16/08/23 | 55 days | 01/06/23 | 16/08/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.5.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | 15/06/23 | 16/08/23 | 45 days | 15/06/23 | 16/08/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.5.4 |  |  |  |  | External industry review via consultation | 100% | 18/08/23 | 07/09/23 | 15 days | 18/08/23 | 07/09/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.5.5 |  |  |  |  | Triage and action comments | 100% | 06/09/23 | 02/10/23 | 19 days | 06/09/23 | 02/10/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.5.6 |  |  |  |  | CDWG review | 100% | 03/10/23 | 14/11/23 | 31 days | 03/10/23 | 14/11/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.5.7 |  |  |  |  | CCAG review | 100% | 15/11/23 | 22/11/23 | 6 days | 15/11/23 | 22/11/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.5.8 | T2 | T3-RE-0300 | CCAG | MHHS-ART060 | Code drafting for Governance and Qualification topic areas approved | 100% | 22/11/23 | 22/11/23 | 0 days | 22/11/23 | 22/11/23 | 1 day | 0 days | 0 days | PP |  | 5.12 | Yes
5 | 1.7.1.2.6 |  |  |  |  | Interfaces / Data Specification (REC driven) | 100% | 25/05/23 | 23/01/24 | 174 days | 25/05/23 | 23/01/24 | 0 days | 0 days | -1 day | N/A |  | 5.2 | Yes
6 | 1.7.1.2.6.1 |  |  |  |  | Pre Code Drafting activities | 100% | 25/05/23 | 31/05/23 | 5 days | 25/05/23 | 31/05/23 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.6.2 |  |  |  |  | Code Drafting (offline) | 100% | 01/06/23 | 10/10/23 | 94 days | 01/06/23 | 10/10/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.7.1.2.6.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | 15/06/23 | 10/10/23 | 84 days | 15/06/23 | 10/10/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.7.1.2.6.4 |  |  |  |  | External industry review via consultation | 100% | 11/10/23 | 31/10/23 | 15 days | 11/10/23 | 31/10/23 | 0 days | 0 days | 0 days | PP |  | 5.2 | Yes
6 | 1.7.1.2.6.5 |  |  |  |  | Triage and action comments | 100% | 30/10/23 | 24/11/23 | 20 days | 30/10/23 | 24/11/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.7.1.2.6.6 |  |  |  |  | CDWG review | 100% | 27/11/23 | 16/01/24 | 37 days | 27/11/23 | 16/01/24 | 0 days | 0 days | 5 days | PP |  | 5.2 | Yes
6 | 1.7.1.2.6.7 |  |  |  |  | CCAG review | 100% | 17/01/24 | 23/01/24 | 5 days | 17/01/24 | 23/01/24 | 0 days | 0 days | -6 days | PP |  | 5.2 | Yes
6 | 1.7.1.2.6.8 | T2 | T3-RE-0350 | CCAG | MHHS-ART060 | Code drafting for Interfaces / Data Specification topic areas approved | 100% | 23/01/24 | 23/01/24 | 0 days | 23/01/24 | 23/01/24 | 1 day | 0 days | 0 days | PP |  | 5.16 | Yes
5 | 1.7.1.2.7 |  |  |  |  | Migration (BSC & REC driven) | 100% | 25/05/23 | 22/11/23 | 130 days | 25/05/23 | 22/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.7.1.2.7.1 |  |  |  |  | Pre Code Drafting activities | 100% | 25/05/23 | 31/05/23 | 5 days | 25/05/23 | 31/05/23 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.7.2 |  |  |  |  | Code Drafting (offline) | 100% | 01/06/23 | 16/08/23 | 55 days | 01/06/23 | 16/08/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.7.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | 15/06/23 | 16/08/23 | 45 days | 15/06/23 | 16/08/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.7.4 |  |  |  |  | External industry review via consultation | 100% | 18/08/23 | 07/09/23 | 15 days | 18/08/23 | 07/09/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.7.5 |  |  |  |  | Triage and action comments | 100% | 06/09/23 | 02/10/23 | 19 days | 06/09/23 | 02/10/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.7.6 |  |  |  |  | CDWG review | 100% | 03/10/23 | 14/11/23 | 31 days | 03/10/23 | 14/11/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.7.7 |  |  |  |  | CCAG review | 100% | 15/11/23 | 22/11/23 | 6 days | 15/11/23 | 22/11/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.7.8 | T2 | T3-RE-0400 | CCAG | MHHS-ART060 | Code drafting for Migration topic area approved | 100% | 22/11/23 | 22/11/23 | 0 days | 22/11/23 | 22/11/23 | 1 day | 0 days | 0 days | PP |  | 5.12 | Yes
5 | 1.7.1.2.8 |  |  |  |  | Consequential Code Change | 100% | 11/10/23 | 11/03/24 | 109 days | 11/10/23 | 11/03/24 | 0 days | 0 days | 1 day | N/A |  | 5 | Yes
6 | 1.7.1.2.8.1 |  |  |  |  | External industry review via consultation - drop 1 (DCUSA) | 100% | 11/10/23 | 31/10/23 | 15 days | 11/10/23 | 31/10/23 | 0 days | 0 days | 0 days | Code Bodies |  | 5.2 | Yes
6 | 1.7.1.2.8.2 |  |  |  |  | External industry review via consultation - drop 2 (Elexon) | 100% | 19/02/24 | 11/03/24 | 16 days | 19/02/24 | 11/03/24 | 0 days | 0 days | 1 day | Code Bodies |  | 5.2 | Yes
5 | 1.7.1.2.9 |  |  |  |  | Transition Text (all codes) | 100% | 11/08/23 | 23/01/24 | 118 days | 11/08/23 | 23/01/24 | 0 days | 0 days | -1 day | N/A |  | 5.2 | Yes
6 | 1.7.1.2.9.1 |  |  |  |  | Pre Code Drafting activities | 100% | 11/08/23 | 22/08/23 | 8 days | 11/08/23 | 22/08/23 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.9.2 |  |  |  |  | Code Drafting (offline) | 100% | 18/08/23 | 10/10/23 | 38 days | 18/08/23 | 10/10/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.7.1.2.9.3 |  |  |  |  | Internal review and cross-checking of drafting across code drafters | 100% | 01/09/23 | 10/10/23 | 28 days | 01/09/23 | 10/10/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.7.1.2.9.4 |  |  |  |  | External industry review via consultation | 100% | 11/10/23 | 31/10/23 | 15 days | 11/10/23 | 31/10/23 | 0 days | 0 days | 0 days | PP |  | 5.2 | Yes
6 | 1.7.1.2.9.5 |  |  |  |  | Triage and action comments | 100% | 30/10/23 | 24/11/23 | 20 days | 30/10/23 | 24/11/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5.2 | Yes
6 | 1.7.1.2.9.6 |  |  |  |  | CDWG review | 100% | 27/11/23 | 16/01/24 | 37 days | 27/11/23 | 16/01/24 | 0 days | 0 days | 0 days | PP |  | 5.2 | Yes
6 | 1.7.1.2.9.7 |  |  |  |  | CCAG review | 100% | 17/01/24 | 23/01/24 | 5 days | 17/01/24 | 23/01/24 | 0 days | 0 days | -1 day | PP |  | 5.2 | Yes
6 | 1.7.1.2.9.8 | T2 | T3-RE-0450 | CCAG | MHHS-ART060 | Code drafting for Transition Text topic area approved | 100% | 23/01/24 | 23/01/24 | 0 days | 23/01/24 | 23/01/24 | 1 day | 0 days | 0 days | PP |  | 5.16 | Yes
5 | 1.7.1.2.10 |  |  |  |  | Final Code Drafting (mop-up) (all codes) | 100% | 18/08/23 | 22/05/24 | 199 days | 18/08/23 | 22/05/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.7.1.2.10.1 |  |  |  |  | Forward look and confirm remaining plan | 100% | 18/08/23 | 07/09/23 | 15 days | 18/08/23 | 07/09/23 | 0 days | 0 days | 0 days | Code Drafting PM |  | 5 | Yes
6 | 1.7.1.2.10.2 |  |  |  |  | Identify remaining or additional areas of code (e.g. consequential change requirements) to be completed | 100% | 18/08/23 | 07/09/23 | 15 days | 18/08/23 | 07/09/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.10.3 |  |  |  |  | Code Drafting (offline) Interim Consultation (1) | 100% | 08/09/23 | 30/11/23 | 60 days | 08/09/23 | 30/11/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.10.4 |  |  |  |  | Internal review and cross-checking of drafting across code drafters Interim Consultation (1) | 100% | 22/09/23 | 30/11/23 | 50 days | 22/09/23 | 30/11/23 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.10.5 |  |  |  |  | External industry review via consultation Interim Consultation (1) | 100% | 01/12/23 | 02/01/24 | 23 days | 01/12/23 | 02/01/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.10.6 |  |  |  |  | Code Drafting (offline) Final Consultation (2) | 100% | 01/12/23 | 15/02/24 | 55 days | 01/12/23 | 15/02/24 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.10.7 |  |  |  |  | Internal review and cross-checking of drafting across code drafters Final Consultation (2) | 100% | 15/12/23 | 15/02/24 | 45 days | 15/12/23 | 15/02/24 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.10.8 |  |  |  |  | External industry review via consultation Final Consultation (2) | 100% | 19/02/24 | 11/03/24 | 16 days | 19/02/24 | 11/03/24 | 0 days | 0 days | 1 day | PP |  | 5 | Yes
6 | 1.7.1.2.10.9 |  |  |  |  | Triage and action comments | 100% | 11/03/24 | 03/04/24 | 18 days | 11/03/24 | 03/04/24 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.10.10 |  |  |  |  | CDWG review | 100% | 04/04/24 | 14/05/24 | 29 days | 04/04/24 | 14/05/24 | 0 days | 0 days | -2 days | PP |  | 5 | Yes
6 | 1.7.1.2.10.11 |  |  |  |  | CCAG review | 100% | 15/05/24 | 22/05/24 | 6 days | 15/05/24 | 22/05/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.7.1.2.10.12 | T2 | T3-RE-0500 | CCAG | MHHS-ART060 | Final code drafting (mop-up) approved | 100% | 22/05/24 | 22/05/24 | 0 days | 22/05/24 | 22/05/24 | 1 day | 0 days | 0 days | PP |  | 5.25 | Yes
5 | 1.7.1.2.11 |  |  |  |  | Final code review, consistency check and approval | 100% | 04/04/24 | 21/08/24 | 100 days | 04/04/24 | 21/08/24 | 0 days | 0 days | -2 days | N/A |  | 5 | Yes
6 | 1.7.1.2.11.1 |  |  |  |  | Gap analysis of final code against design artefacts (reverse process to code drafting) | 100% | 04/04/24 | 27/05/24 | 38 days | 04/04/24 | 27/05/24 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.11.2 |  |  |  |  | Outputs of gap analysis actioned offline | 100% | 28/05/24 | 11/06/24 | 11 days | 28/05/24 | 11/06/24 | 0 days | 0 days | 0 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.11.3 |  |  |  |  | Final documentation collated for final consultation | 100% | 12/06/24 | 21/06/24 | 8 days | 12/06/24 | 21/06/24 | 0 days | 0 days | -1 day | Code Drafting PM |  | 5.23 | Yes
6 | 1.7.1.2.11.4 |  |  |  |  | External industry review via consultation | 100% | 24/06/24 | 12/07/24 | 15 days | 24/06/24 | 12/07/24 | 0 days | 0 days | -5 days | PP |  | 5 | Yes
6 | 1.7.1.2.11.5 |  |  |  |  | Triage and action comments | 100% | 15/07/24 | 26/07/24 | 10 days | 15/07/24 | 26/07/24 | 0 days | 0 days | -3 days | Code Bodies,SRO Design |  | 5 | Yes
6 | 1.7.1.2.11.6 |  |  |  |  | Final CDWG review | 100% | 02/08/24 | 13/08/24 | 8 days | 02/08/24 | 13/08/24 | 0 days | 0 days | 2 days | PP |  | 5 | Yes
6 | 1.7.1.2.11.7 |  |  |  |  | Final CCAG review | 100% | 14/08/24 | 21/08/24 | 6 days | 14/08/24 | 21/08/24 | 0 days | 0 days | -2 days | PP |  | 5 | Yes
6 | 1.7.1.2.11.8 | T2 | T3-RE-0550 | CCAG | MHHS-ART060 | CCAG recommend final code to PSG for baselining | 100% | 21/08/24 | 21/08/24 | 0 days | 21/08/24 | 21/08/24 | 1 day | 0 days | 0 days | PP |  | 5.9 | Yes
4 | 1.7.1.3 | T1 | T1-RE-1000 | PSG | MHHS-ART012 | Code changes baselined (M6) | 100% | 23/08/24 | 23/08/24 | 0 days | 23/08/24 | 23/08/24 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
3 | 1.7.2 |  |  |  |  | Ofgem preparation and enactment of SCR powers | 100% | 05/02/24 | 13/12/24 | 225 days | 05/02/24 | 13/12/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.7.2.1 |  |  |  |  | Preparation and enactment of SCR Powers | 100% | 05/02/24 | 11/12/24 | 223 days | 05/02/24 | 11/12/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.7.2.1.1 |  |  |  |  | Ofgem to keep Ofgem legal informed of process followed and nature of Code drafting to ensure that prepared for SCR go/no go decision | 100% | 05/02/24 | 24/06/24 | 101 days | 05/02/24 | 24/06/24 | 0 days | 0 days | 0 days | Ofgem |  | 5 | Yes
5 | 1.7.2.1.2 |  |  |  |  | OFGEM Legal to review Code Artefacts deliver policy intent and process followed and confirm that SCR powers are appropriate to use rather than SMAP - SCR go/no go | 100% | 24/06/24 | 11/07/24 | 14 days | 24/06/24 | 11/07/24 | 0 days | 0 days | -1 day | Ofgem |  | 5 | Yes
5 | 1.7.2.1.3 |  |  |  |  | Code Bodies to draft MOD proposal forms | 100% | 12/07/24 | 08/08/24 | 20 days | 12/07/24 | 08/08/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.7.2.1.4 |  |  |  |  | Ofgem discuss and agree code mod timetable with code bodies (and MHHSP in relation to the dates for expected decisions) | 100% | 12/07/24 | 08/08/24 | 20 days | 12/07/24 | 08/08/24 | 0 days | 0 days | 0 days | Ofgem |  | 5 | Yes
5 | 1.7.2.1.5 |  |  |  |  | Ofgem to publish each Direction to each code body specifying the timetable for each modification | 100% | 28/08/24 | 28/08/24 | 1 day | 28/08/24 | 28/08/24 | 0 days | 0 days | 0 days | Ofgem |  | 5 | Yes
5 | 1.7.2.1.6 |  |  |  |  | Formally submit (by separate email) Modification Proposal Forms and legal texts to each code body | 100% | 28/08/24 | 28/08/24 | 1 day | 28/08/24 | 28/08/24 | 0 days | 0 days | 0 days | Ofgem |  | 5 | Yes
5 | 1.7.2.1.7 |  |  |  |  | Each Code Body publishes and issues Modification Proposal Forms | 100% | 29/08/24 | 02/09/24 | 3 days | 29/08/24 | 02/09/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.7.2.1.8 |  |  |  |  | Each Code Body sends Modification Proposal Forms to Panel to approve Mod to go to consultation | 100% | 03/09/24 | 16/09/24 | 10 days | 03/09/24 | 16/09/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.7.2.1.9 |  |  |  |  | Modification Proposal approved by Panel for Consultation | 100% | 17/09/24 | 17/09/24 | 1 day | 17/09/24 | 17/09/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.7.2.1.10 |  |  |  |  | Draft Modification Report issued for consultation | 100% | 18/09/24 | 18/09/24 | 1 day | 18/09/24 | 18/09/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.7.2.1.11 |  |  |  |  | Consultation Close-out for representations | 100% | 19/09/24 | 09/10/24 | 15 days | 19/09/24 | 09/10/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.7.2.1.12 |  |  |  |  | Each Code Body reviews consultation response and drafts Modification Report | 100% | 10/10/24 | 23/10/24 | 10 days | 10/10/24 | 23/10/24 | 0 days | 0 days | 0 days | Code Bodies |  | 5 | Yes
5 | 1.7.2.1.13 |  |  |  |  | Final Modification Report sent to Panel for decision with recommendation to approve | 100% | 24/10/24 | 24/10/24 | 1 day | 24/10/24 | 24/10/24 | 0 days | 0 days | 0 days | Code Bodies |  | 6.11 | Yes
5 | 1.7.2.1.14 |  |  |  |  | Modification Panel decision | 100% | 07/11/24 | 07/11/24 | 1 day | 07/11/24 | 07/11/24 | 0 days | 0 days | 0 days | Code Bodies |  | 6.11 | Yes
5 | 1.7.2.1.15 |  |  |  |  | Code Bodies Submit Final Modification/Change Reports | 100% | 08/11/24 | 08/11/24 | 1 day | 08/11/24 | 08/11/24 | 0 days | 0 days | 0 days | Code Bodies |  | 6.11 | Yes
5 | 1.7.2.1.16 |  |  |  |  | Ofgem Reviews Final Modification/Change Reports | 100% | 11/11/24 | 22/11/24 | 10 days | 11/11/24 | 22/11/24 | 0 days | 0 days | 0 days | Ofgem |  | 6.11 | Yes
5 | 1.7.2.1.17 |  |  |  |  | Ofgem Drafts Decision/Direction Letters | 100% | 18/11/24 | 10/12/24 | 17 days | 18/11/24 | 10/12/24 | 0 days | 0 days | 0 days | Ofgem |  | 6.11 | Yes
5 | 1.7.2.1.18 |  |  |  |  | Ofgem Internally Signs Off the Decision/Direction Letters and Sends Them to the Code Bodies | 100% | 11/12/24 | 11/12/24 | 1 day | 11/12/24 | 11/12/24 | 0 days | 0 days | 0 days | Ofgem |  | 6.11 | Yes
4 | 1.7.2.2 | T2 | T2-RE-0600 | CCAG | MHHS-ART012 | Ofgem decisions on M6 baselined code modification proposals (M7) | 100% | 11/12/24 | 11/12/24 | 0 days | 11/12/24 | 11/12/24 | 1 day | 0 days | 0 days | CPT | Approved | 6.11 | Yes
4 | 1.7.2.3 |  |  |  |  | Ofgem Publishes the Decisions/Directions | 100% | 12/12/24 | 13/12/24 | 2 days | 12/12/24 | 13/12/24 | 0 days | 0 days | 0 days | Ofgem |  | 6.11 | Yes
3 | 1.7.3 |  |  |  |  | Deliver MHHS Code Changes | 84% | 12/11/24 | 24/12/25 | 292 days | 12/11/24 | 24/12/25 | 0 days | 0 days | 143 days | N/A |  | 6.11 | Yes
4 | 1.7.3.1 |  |  |  |  | Releases | 84% | 12/11/24 | 24/12/25 | 292 days | 12/11/24 | 24/12/25 | 0 days | 0 days | 143 days | N/A |  | 6.11 | Yes
5 | 1.7.3.1.1 |  |  |  |  | Impacted codes make resourcing provisions and prepare to implement new Code via internal code body change processes | 90% | 12/11/24 | 27/02/25 | 78 days | 12/11/24 | 27/02/25 | 0 days | 0 days | 0 days | Code Bodies |  | 6.11 | Yes
5 | 1.7.3.1.2 |  |  |  |  | Main Code Release | 0% | 17/09/25 | 24/12/25 | 71 days | 17/09/25 | 24/12/25 | 0 days | 0 days | 0 days | N/A |  | 6.11 | Yes
6 | 1.7.3.1.2.1 |  |  |  |  | Release preparation (e.g. preparing release documentation) | 0% | 17/09/25 | 24/09/25 | 6 days | 17/09/25 | 24/09/25 | 0 days | 0 days | 1 day | Code Bodies |  | 6.11 | Yes
6 | 1.7.3.1.2.2 |  |  |  |  | Implement new code on day of code release | 0% | 24/09/25 | 24/09/25 | 0 days | 24/09/25 | 24/09/25 | 1 day | 0 days | -1 day | Code Bodies |  | 6.11 | Yes
6 | 1.7.3.1.2.3 | T2 | T2-RE-0650 | CCAG | MHHS-ART060 | Code changes delivered (M8) | 0% | 24/09/25 | 24/09/25 | 0 days | 24/09/25 | 24/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.11 | Yes
6 | 1.7.3.1.2.4 | T2 | T2-RE-0700 | CCAG | MHHS-ART060 | Code changes delivered (M8*) late exit | 0% | 24/12/25 | 24/12/25 | 0 days | 24/12/25 | 24/12/25 | 1 day | 0 days | 0 days | CPT |  | 6.11 | Yes
3 | 1.7.4 |  |  |  |  | External Programme Dependency Management | 100% | 01/12/23 | 24/01/24 | 38 days | 01/12/23 | 24/01/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
4 | 1.7.4.1 |  |  |  |  | DCP397 | 100% | 01/12/23 | 24/01/24 | 38 days | 01/12/23 | 24/01/24 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
5 | 1.7.4.1.1 |  |  |  |  | Ensure DCP397 drafting included in mop-up code drafting activity (link to mop-up) | 100% | 01/12/23 | 28/12/23 | 20 days | 01/12/23 | 28/12/23 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
5 | 1.7.4.1.2 |  |  |  |  | Implementation of DCP397 | 100% | 24/01/24 | 24/01/24 | 0 days | 24/01/24 | 24/01/24 | 0 days | -1 day | 0 days | Code Bodies |  | 5 | Yes
2 | 1.8 |  |  |  |  | MIGRATION | 37% | 31/10/22 | 03/08/27 | 1242 days? | 31/10/22 | 09/08/27 | 0 days | -4 days | 150 days? | N/A |  |  | Yes
3 | 1.8.1 | T3 | T3-MI-0016 | MCAG (Migration) |  | Migration Period Plan Review 1 Completed | 0% | 31/01/25 | 31/01/25 | 0 days | 31/01/25 | 31/01/25 | 1 day | 0 days | 0 days | SRO |  | 5.28 | Yes |  | 27/11/24 - To go to MCAG for removal because milestone no longer reflects the delivery of the migration approach.
3 | 1.8.2 |  |  |  |  | Regulatory Governance | 47% | 01/04/24 | 01/01/25 | 198 days | 01/04/24 | 01/01/25 | 0 days | 0 days | 25 days | N/A |  | 5.28 | Yes
4 | 1.8.2.1 |  |  |  |  | Incentive Mods Created | 85% | 01/04/24 | 30/08/24 | 110 days | 01/04/24 | 30/08/24 | 0 days | 0 days | 25 days | SRO Migration |  | 5.28 | Yes |  | Potential to extend this to end of the year
4 | 1.8.2.2 |  |  |  |  | Incentives Implemented | 0% | 02/09/24 | 01/01/25 | 88 days | 02/09/24 | 01/01/25 | 0 days | 0 days | 0 days | Code Bodies |  | 5.28 | Yes
3 | 1.8.3 |  |  |  |  | Migration Framework Agreed and Implemented | 58% | 01/02/24 | 07/05/25 | 330 days? | 01/02/24 | 23/01/25 | 0 days | 74 days | 116 days? | N/A |  | 5.28 | Yes
4 | 1.8.3.1 |  |  |  |  | Consultation 1 - Schedule | 100% | 01/02/24 | 08/05/24 | 70 days | 01/02/24 | 08/05/24 | 0 days | 0 days | 0 days | N/A |  | 5.28 | Yes
5 | 1.8.3.1.1 |  |  |  |  | Prepare Artefacts for Consultation | 100% | 01/02/24 | 18/03/24 | 33 days | 01/02/24 | 18/03/24 | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
5 | 1.8.3.1.2 |  |  |  |  | Industry Consultation | 100% | 18/03/24 | 08/04/24 | 16 days | 18/03/24 | 08/04/24 | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
5 | 1.8.3.1.3 |  |  |  |  | Triage and Action Comments | 100% | 08/04/24 | 19/04/24 | 10 days | 08/04/24 | 19/04/24 | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
5 | 1.8.3.1.4 |  |  |  |  | Industry Assurance Review | 100% | 19/04/24 | 26/04/24 | 6 days | 19/04/24 | 26/04/24 | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
5 | 1.8.3.1.5 |  |  |  |  | MWG Recommendation | 100% | 26/04/24 | 26/04/24 | 1 day | 26/04/24 | 26/04/24 | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
5 | 1.8.3.1.6 |  |  |  |  | MCAG Interim Approval Artefacts | 100% | 08/05/24 | 08/05/24 | 1 day | 08/05/24 | 08/05/24 | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
4 | 1.8.3.2 |  |  |  |  | Consultation 2 - Control | 100% | 08/04/24 | 25/07/24 | 79 days | 08/04/24 | 25/07/24 | 0 days | 0 days | 0 days | N/A |  | 5.28 | Yes
5 | 1.8.3.2.1 |  |  |  |  | Prepare Artefacts for Consultation | 100% | 08/04/24 | 13/06/24 | 49 days | 08/04/24 | 13/06/24 | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
5 | 1.8.3.2.2 |  |  |  |  | Industry Consultation | 100% | 14/06/24 | 28/06/24 | 11 days | 14/06/24 | 28/06/24 | 0 days | 0 days | 0 days |  |  | 5.28 | Yes
5 | 1.8.3.2.3 |  |  |  |  | Triage and Action Comments | 100% | 01/07/24 | 11/07/24 | 9 days | 01/07/24 | 11/07/24 | 0 days | 0 days | 0 days | SRO Migration |  | 5.28 | Yes
5 | 1.8.3.2.4 |  |  |  |  | Industry Assurance Review | 100% | 12/07/24 | 18/07/24 | 5 days | 12/07/24 | 18/07/24 | 0 days | 0 days | 0 days | PP |  | 5.28 | Yes
5 | 1.8.3.2.5 |  |  |  |  | MWG Recommendation | 100% | 18/07/24 | 18/07/24 | 0 days | 18/07/24 | 18/07/24 | 1 day | 0 days | 0 days | PP |  | 5.28 | Yes
5 | 1.8.3.2.6 | T3 | T3-MI-0037 | MCAG (Migration) |  | Consultation 2 - Control - MCAG Approval of Interim Artefacts | 100% | 25/07/24 | 25/07/24 | 0 days | 25/07/24 | 25/07/24 | 1 day | 0 days | 0 days | PP |  | 5.3 | Yes
4 | 1.8.3.3 |  |  |  |  | Consultation 3 - Parameters | 71% | 18/11/24 | 25/02/25 | 72 days | 18/11/24 | 25/02/25 | 0 days | 0 days | -4 days | N/A |  | 6.14 | Yes
5 | 1.8.3.3.1 |  |  |  |  | Prepare Artefacts for Consultation | 100% | 18/11/24 | 19/12/24 | 24 days | 18/11/24 | 19/12/24 | 0 days | 0 days | -12 days | SRO Migration |  | 6.14 | Yes
5 | 1.8.3.3.2 |  |  |  |  | Industry Consultation | 95% | 20/12/24 | 17/01/25 | 21 days | 20/12/24 | 17/01/25 | 0 days | 0 days | 11 days | PP |  | 6.14 | Yes
5 | 1.8.3.3.3 |  |  |  |  | Triage Response | 0% | 20/01/25 | 31/01/25 | 10 days | 20/01/25 | 31/01/25 | 0 days | 0 days | 0 days | SRO Migration |  | 6.14 | Yes
5 | 1.8.3.3.4 |  |  |  |  | Industry Assurance Review | 0% | 03/02/25 | 11/02/25 | 7 days | 03/02/25 | 11/02/25 | 0 days | 0 days | 0 days | PP |  | 6.14 | Yes
5 | 1.8.3.3.5 |  |  |  |  | MWG Recommendation | 0% | 21/02/25 | 21/02/25 | 0 days | 21/02/25 | 21/02/25 | 1 day | 0 days | 0 days | PP |  | 6.14 | Yes
5 | 1.8.3.3.6 |  |  |  |  | MCAG Paper Day | 0% | 25/02/25 | 25/02/25 | 0 days | 25/02/25 | 25/02/25 | 1 day | 0 days | 0 days |  |  | 6.14 | Yes
5 | 1.8.3.3.7 | T3 | T3-MI-0017 | MCAG (Migration) |  | MCAG Approval of Migration Framework Artefacts (Baselined) | 0% | 25/02/25 | 25/02/25 | 0 days | 25/02/25 | 25/02/25 | 1 day | 0 days | 0 days | PP |  | 6.14 | Yes
4 | 1.8.3.4 |  |  |  |  | Consultation 4 | 1% | 07/01/25 | 07/05/25 | 87 days? | 07/01/25 | 07/05/25 | 0 days | 0 days | 87 days? | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - Dates for Consultation 4 included in the plan, these are due to be discussed and agreed at January MCAG.
5 | 1.8.3.4.1 |  |  |  |  | Prepare Artefacts | 1% | 07/01/25 | 07/05/25 | 87 days? | 07/01/25 | 07/05/25 | 0 days | 0 days | 87 days? | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - Dates for Consultation 4 included in the plan, these are due to be discussed and agreed at January MCAG.
6 | 1.8.3.4.1.1 |  |  |  |  | Test Approach | 5% | 07/01/25 | 03/02/25 | 20 days? | 07/01/25 | 03/02/25 | 0 days | 0 days | 20 days? | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - Dates for Consultation 4 included in the plan, these are due to be discussed and agreed at January MCAG.
6 | 1.8.3.4.1.2 |  |  |  |  | Test Plan | 0% | 04/02/25 | 03/03/25 | 20 days? | 04/02/25 | 03/03/25 | 0 days | 0 days | 20 days? | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - Dates for Consultation 4 included in the plan, these are due to be discussed and agreed at January MCAG.
6 | 1.8.3.4.1.3 |  |  |  |  | Other Framework items | 0% | 04/03/25 | 07/05/25 | 47 days? | 04/03/25 | 07/05/25 | 0 days | 0 days | 47 days? | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - Dates for Consultation 4 included in the plan, these are due to be discussed and agreed at January MCAG.
5 | 1.8.3.4.2 |  |  |  |  | Industry Consultation | 0% | 12/03/25 | 25/03/25 | 10 days? | 12/03/25 | 25/03/25 | 0 days | 0 days | 10 days? | PP | Proposed | 6.14 | Yes |  | 15/01/25 - Dates for Consultation 4 included in the plan, these are due to be discussed and agreed at January MCAG.
5 | 1.8.3.4.3 |  |  |  |  | Triage Response | 0% | 26/03/25 | 08/04/25 | 10 days? | 26/03/25 | 08/04/25 | 0 days | 0 days | 10 days? | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - Dates for Consultation 4 included in the plan, these are due to be discussed and agreed at January MCAG.
5 | 1.8.3.4.4 |  |  |  |  | Assurance and MCAG Approval | 0% | 09/04/25 | 22/04/25 | 10 days? | 09/04/25 | 22/04/25 | 0 days | 0 days | 10 days? | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - Dates for Consultation 4 included in the plan, these are due to be discussed and agreed at January MCAG.
5 | 1.8.3.4.5 |  |  |  |  | Consultation 4 Approved | 0% | 22/04/25 | 22/04/25 | 0 days | 22/04/25 | 22/04/25 | 1 day | 0 days | 0 days | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - Dates for Consultation 4 included in the plan, these are due to be discussed and agreed at January MCAG.
5 | 1.8.3.4.6 | T3 | T3-MI-XXXX | MCAG (Migration) |  | Framework Baselined at MCAG | 0% | 22/04/25 | 22/04/25 | 0 days | 22/04/25 | 22/04/25 | 1 day | 0 days | 0 days | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - Dates for Consultation 4 included in the plan, these are due to be discussed and agreed at January MCAG. Also propose that milestone ID is set.
3 | 1.8.4 |  |  |  |  | Migration Schedule Agreed and Maintained | 57% | 01/07/24 | 18/07/25 | 275 days? | 01/07/24 | 30/01/26 | 0 days | -140 days | 68 days? | SI Migration |  | 5.28 | Yes
4 | 1.8.4.1 |  |  |  |  | Indicative Envelopes Issued | 100% | 01/07/24 | 31/07/24 | 23 days | 01/07/24 | 31/07/24 | 0 days | 0 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.4.2 |  |  |  |  | Supplier Submissions | 100% | 01/08/24 | 02/10/24 | 45 days | 01/08/24 | 02/10/24 | 0 days | 0 days | 0 days | PP |  | 5.28 | Yes
4 | 1.8.4.3 |  |  |  |  | Team Assess Responses | 100% | 03/10/24 | 16/10/24 | 10 days | 03/10/24 | 16/10/24 | 0 days | 0 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.4.4 |  |  |  |  | Discuss and Agree Approach with Participants where necessary | 100% | 17/10/24 | 22/10/24 | 4 days | 17/10/24 | 22/10/24 | 0 days | 0 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.4.5 | T3 | T3-MI-XXXX | MCAG (Migration) |  | Schedule Production v1 | 100% | 18/11/24 | 20/12/24 | 25 days? | 18/11/24 | 20/12/24 | 0 days | 0 days | 25 days? | SI Migration |  | 6.14 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this milestone date is updated and ID assigned, but not baselined yet.
4 | 1.8.4.6 | T3 | T3-MI-XXXX | MCAG (Migration) |  | Schedule Production v2 | 0% | 31/03/25 | 18/07/25 | 80 days? | 31/03/25 | 18/07/25 | 0 days | 0 days | 80 days? | SI Migration |  | 6.14 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this milestone date is updated and ID assigned, but not baselined yet.
4 | 1.8.4.7 | T3 | T3-MI-0039 | MCAG (Migration) |  | V1.0 of Migration Schedule Baseline Approved at MCAG | 0% | 18/07/25 | 18/07/25 | 0 days | 18/07/25 | 18/07/25 | 1 day | 0 days | 0 days | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this milestone date is updated, but not baselined yet.
3 | 1.8.5 |  |  |  |  | MCC Stood up | 0% | 18/11/24 | 21/11/25 | 265 days? | 18/11/24 | 21/11/25 | 0 days | 0 days | 265 days? | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this milestone date is updated, but not baselined yet.
4 | 1.8.5.1 |  |  |  |  | MPMT Delivered | 0% | 18/11/24 | 21/11/25 | 265 days? | 18/11/24 | 21/11/25 | 0 days | 0 days | 265 days? | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this milestone date is updated, but not baselined yet.
5 | 1.8.5.1.1 |  |  |  |  | Migration Planning Tool - Delivery | 0% | 18/11/24 | 21/11/25 | 265 days? | 18/11/24 | 21/11/25 | 0 days | 0 days | 265 days? | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this milestone date is updated, but not baselined yet.
6 | 1.8.5.1.1.1 |  |  |  |  | MPMT Build Sprints - MVP | 0% | 06/01/25 | 20/06/25 | 120 days? | 06/01/25 | 20/06/25 | 0 days | 0 days | 120 days? | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this milestone date is updated, but not baselined yet.
6 | 1.8.5.1.1.2 |  |  |  |  | Delivery Activity | 0% | 18/11/24 | 21/11/25 | 265 days? | 18/11/24 | 21/11/25 | 0 days | 0 days | 265 days? | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this milestone date is updated, but not baselined yet.
4 | 1.8.5.2 |  |  |  |  | MCC - Pilot | 0% | 20/11/24 | 20/11/24 | 0 days | 20/11/24 | 20/11/24 | 0 days | -1 day | 0 days | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this milestone date is updated, but not baselined yet.
4 | 1.8.5.3 | T2 | T2-MI-XXXX | MCAG (Migration) |  | MCC Stood up complete | 0% | 18/11/24 | 18/11/24 | 1 day? | 18/11/24 | 18/11/24 | 0 days | 0 days | 1 day? | SI Migration | Proposed | 6.14 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this milestone date is updated and ID assigned, but not baselined yet.
4 | 1.8.5.4 |  |  |  |  | Sprint Planning (Cycle 1) | 0% | 22/12/25 | 13/02/26 | 40 days | 16/06/25 | 08/08/25 | 135 days | 135 days | 20 days | SRO Migration | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
4 | 1.8.5.5 |  |  |  |  | Sprint Planning (Cycle 2) | 0% | 23/03/26 | 15/05/26 | 40 days | 15/09/25 | 07/11/25 | 135 days | 135 days | 20 days | SRO Migration | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
4 | 1.8.5.6 |  |  |  |  | Sprint Planning (Cycle 3) | 0% | 15/06/26 | 07/08/26 | 40 days | 08/12/25 | 30/01/26 | 135 days | 135 days | 21 days | SRO Migration | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
3 | 1.8.6 |  |  |  |  | Migration Control Centre Tooling | 66% | 09/05/24 | 11/04/25 | 242 days | 09/05/24 | 11/04/25 | 0 days | 0 days | 60 days | N/A | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
4 | 1.8.6.1 |  |  |  |  | Data Source Definition | 100% | 09/05/24 | 23/10/24 | 120 days | 09/05/24 | 23/10/24 | 0 days | 0 days | 60 days | SRO Migration | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
4 | 1.8.6.2 |  |  |  |  | Scheduling and Data Requirements | 100% | 09/05/24 | 23/10/24 | 120 days | 09/05/24 | 23/10/24 | 0 days | 0 days | 60 days | SRO Migration | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
4 | 1.8.6.3 |  |  |  |  | Tool Phase 1 | 0% | 24/10/24 | 07/11/24 | 11 days | 24/10/24 | 07/11/24 | 0 days | 0 days | 0 days | SRO Migration | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
4 | 1.8.6.4 |  |  |  |  | Data Requirements | 0% | 08/11/24 | 06/12/24 | 21 days | 08/11/24 | 06/12/24 | 0 days | 0 days | 0 days | SRO Migration | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
4 | 1.8.6.5 |  |  |  |  | Tool Phase 2 | 0% | 09/12/24 | 10/01/25 | 25 days | 09/12/24 | 10/01/25 | 0 days | 0 days | 0 days | SRO Migration | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
4 | 1.8.6.6 |  |  |  |  | Data Source Provision | 0% | 13/01/25 | 21/01/25 | 7 days | 13/01/25 | 21/01/25 | 0 days | 0 days | 0 days | SRO Migration | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
4 | 1.8.6.7 |  |  |  |  | Tool - Internal and External Testing | 0% | 22/01/25 | 11/04/25 | 58 days | 22/01/25 | 11/04/25 | 0 days | 0 days | 0 days | SRO Migration | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
3 | 1.8.7 |  |  |  |  | Migration Control Centre Mobilised and Ready | 1% | 30/07/24 | 02/05/25 | 199 days | 30/07/24 | 14/04/25 | 0 days | 14 days | 65 days | N/A | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
4 | 1.8.7.1 |  |  |  |  | Migration Control Centre TOM Definition | 3% | 30/07/24 | 28/10/24 | 65 days | 30/07/24 | 28/10/24 | 0 days | 0 days | 36 days | SRO Migration | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
4 | 1.8.7.2 |  |  |  |  | Access to Data | 0% | 04/11/24 | 06/12/24 | 25 days | 04/11/24 | 06/12/24 | 0 days | 0 days | 0 days | SRO Migration | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
4 | 1.8.7.3 |  |  |  |  | Migration Control Centre Delegation of Authority | 0% | 24/12/24 | 08/01/25 | 12 days | 24/12/24 | 08/01/25 | 0 days | 0 days | 0 days | SRO Migration | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
4 | 1.8.7.4 |  |  |  |  | Recruit and Train | 0% | 24/12/24 | 24/03/25 | 65 days | 24/12/24 | 24/03/25 | 0 days | 0 days | 0 days | SRO Migration | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
4 | 1.8.7.5 |  |  |  |  | Dress Rehearsal | 0% | 02/05/25 | 02/05/25 | 1 day | 14/04/25 | 14/04/25 | 14 days | 14 days | 0 days | SRO Migration | Proposed | 5.28 | Yes |  | 15/01/25 - The Programme is updating the Migration Schedule, with a discussion due at MCAG in January to agree this. Proposed that this activity is removed.
3 | 1.8.8 |  |  |  |  | PP's Prepared for Migration | 23% | 01/07/24 | 01/05/25 | 219 days | 01/07/24 | 31/03/25 | 0 days | 23 days | 65 days | N/A |  | 5.28 | Yes
4 | 1.8.8.1 |  |  |  |  | Prep for Envelope Webinar | 100% | 01/07/24 | 05/08/24 | 26 days | 01/07/24 | 05/08/24 | 0 days | 0 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.8.2 |  |  |  |  | Envelope/Submission Webinar | 100% | 05/08/24 | 05/08/24 | 1 day | 05/08/24 | 05/08/24 | 0 days | 0 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.8.3 |  |  |  |  | Guides Creation | 0% | 28/02/25 | 01/05/25 | 45 days | 28/01/25 | 31/03/25 | 23 days | 23 days | 0 days | SRO Migration |  | 5.28 | Yes
4 | 1.8.8.4 |  |  |  |  | Support Channels | 0% | 28/02/25 | 01/05/25 | 45 days | 28/01/25 | 31/03/25 | 23 days | 23 days | 0 days | SRO Migration |  | 5.28 | Yes
3 | 1.8.9 |  |  |  |  | Migration Artefact Development and Publication | 91% | 31/10/22 | 15/10/25 | 773 days | 31/10/22 | 03/09/25 | 0 days | 30 days | 138 days | N/A |  | 5 | Yes
4 | 1.8.9.1 |  |  |  |  | Migration Approach | 100% | 31/10/22 | 07/12/22 | 28 days | 31/10/22 | 07/12/22 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.8.9.1.1 |  |  |  |  | Option analysis (via MWG and PPIR) and recommendation | 100% | 31/10/22 | 30/11/22 | 23 days | 31/10/22 | 30/11/22 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.8.9.1.2 | T3 | T3-MI-0010 | PSG | MHHS-DEL770 | Migration Approach approved | 100% | 07/12/22 | 07/12/22 | 0 days | 07/12/22 | 07/12/22 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
4 | 1.8.9.2 |  |  |  |  | Migration Design | 100% | 14/11/22 | 31/03/23 | 100 days | 14/11/22 | 31/03/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.8.9.2.1 |  |  |  |  | Review and update existing design artefacts and socialise with participants ahead of MDSG | 100% | 14/11/22 | 25/11/22 | 10 days | 14/11/22 | 25/11/22 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.9.2.2 |  |  |  |  | Develop design artefacts and supporting technical documents in line with MDSG | 100% | 30/11/22 | 10/02/23 | 53 days | 30/11/22 | 10/02/23 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.9.2.3 | T3 | T3-MI-0011 | DAG |  | Migration design artefacts issued for consultation | 100% | 13/02/23 | 13/02/23 | 0 days | 13/02/23 | 13/02/23 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.9.2.4 |  |  |  |  | Industry consultation | 100% | 14/02/23 | 20/02/23 | 5 days | 14/02/23 | 20/02/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.8.9.2.5 |  |  |  |  | Review consultation feedback, address comments and update artefacts | 100% | 21/02/23 | 27/02/23 | 5 days | 21/02/23 | 27/02/23 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.9.2.6 |  |  |  |  | Internal artefact review and comms preparation | 100% | 28/02/23 | 02/03/23 | 3 days | 28/02/23 | 02/03/23 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.9.2.7 | T3 | T3-MI-0013 | DAG |  | Updated Migration Design artefacts issued to PPs for assurance review | 100% | 03/03/23 | 03/03/23 | 0 days | 03/03/23 | 03/03/23 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.9.2.8 |  |  |  |  | Final Migration Design artefacts walkthrough with PPs | 100% | 22/03/23 | 22/03/23 | 0 days | 22/03/23 | 22/03/23 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.9.2.9 | T2 | T2-MI-0050 | DAG |  | Migration Design approved | 100% | 31/03/23 | 31/03/23 | 0 days | 31/03/23 | 31/03/23 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
4 | 1.8.9.3 |  |  |  |  | Transition Design | 100% | 01/03/23 | 15/11/23 | 186 days | 01/03/23 | 15/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.8.9.3.1 |  |  |  |  | Tranche 1 | 100% | 01/03/23 | 17/05/23 | 56 days | 01/03/23 | 17/05/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.8.9.3.1.1 |  |  |  |  | Develop design artefacts and supporting technical details with participants | 100% | 01/03/23 | 09/05/23 | 50 days | 01/03/23 | 09/05/23 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
6 | 1.8.9.3.1.2 |  |  |  |  | Issue Material for DAG approval | 100% | 10/05/23 | 10/05/23 | 1 day | 10/05/23 | 10/05/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.8.9.3.1.3 | T2 | T2-DB-0150 | DAG |  | Tranche 1 Transition Design approved | 100% | 17/05/23 | 17/05/23 | 0 days | 17/05/23 | 17/05/23 | 1 day | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.8.9.3.2 |  |  |  |  | Tranche 2 | 100% | 18/05/23 | 15/11/23 | 130 days | 18/05/23 | 15/11/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.8.9.3.2.1 |  |  |  |  | Develop Initial design artefacts and supporting technical details | 100% | 18/05/23 | 31/08/23 | 76 days | 18/05/23 | 31/08/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.9.3.2.2 |  |  |  |  | Communicate Initial Design Artefacts with Industry (MTDSG) | 100% | 01/09/23 | 01/09/23 | 1 day | 01/09/23 | 01/09/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.9.3.2.3 |  |  |  |  | Host MTDSG | 100% | 11/09/23 | 11/09/23 | 1 day | 11/09/23 | 11/09/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.9.3.2.4 |  |  |  |  | Process MTDSG Feedback and Amend Design Artefacts | 100% | 12/09/23 | 15/09/23 | 4 days | 12/09/23 | 15/09/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.9.3.2.5 |  |  |  |  | Communicate Amended Design Artefacts with Industry | 100% | 15/09/23 | 15/09/23 | 1 day | 15/09/23 | 15/09/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.9.3.2.6 |  |  |  |  | Host MTDSG | 100% | 26/09/23 | 26/09/23 | 1 day | 26/09/23 | 26/09/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.9.3.2.7 |  |  |  |  | Make Final Amendments to Design Artefact | 100% | 27/09/23 | 03/10/23 | 5 days | 27/09/23 | 03/10/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.9.3.2.8 |  |  |  |  | Request DAG Consultation | 100% | 04/10/23 | 04/10/23 | 1 day | 04/10/23 | 04/10/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.9.3.2.9 |  |  |  |  | Consultation Period | 100% | 04/10/23 | 18/10/23 | 11 days | 04/10/23 | 18/10/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.9.3.2.10 |  |  |  |  | Action Consultation Comments | 100% | 19/10/23 | 25/10/23 | 5 days | 19/10/23 | 25/10/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.9.3.2.11 |  |  |  |  | Post Consultation Industry Assurance | 100% | 26/10/23 | 01/11/23 | 5 days | 26/10/23 | 01/11/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.9.3.2.12 |  |  |  |  | Request DAG Approval | 100% | 01/11/23 | 01/11/23 | 1 day | 01/11/23 | 01/11/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.9.3.2.13 |  |  |  |  | DAG Transition Design Approved | 100% | 08/11/23 | 08/11/23 | 1 day | 08/11/23 | 08/11/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.9.3.2.14 |  |  |  |  | Update Transition Design Admin | 100% | 09/11/23 | 15/11/23 | 5 days | 09/11/23 | 15/11/23 | 0 days | 0 days | 0 days | SRO |  | 5.5 | Yes
6 | 1.8.9.3.2.15 | T2 | T2-DB-0250 | DAG |  | Tranche 2 Transition Design Baselined | 100% | 15/11/23 | 15/11/23 | 0 days | 15/11/23 | 15/11/23 | 1 day | 0 days | 0 days | SRO |  | 5.12 | Yes
4 | 1.8.9.4 |  |  |  |  | Data Assessment Report | 100% | 06/12/22 | 28/02/23 | 61 days | 06/12/22 | 28/02/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.8.9.4.1 |  |  |  |  | Develop document with MWG | 100% | 06/12/22 | 10/02/23 | 49 days | 06/12/22 | 10/02/23 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.9.4.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | 18/01/23 | 21/02/23 | 25 days | 18/01/23 | 21/02/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.8.9.4.3 | T3 | T3-MI-0012 | MCAG |  | Data Assessment Report approved | 100% | 28/02/23 | 28/02/23 | 0 days | 28/02/23 | 28/02/23 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
4 | 1.8.9.5 |  |  |  |  | Migration, Cutover & Data Strategy (incl. Migration Entry Criteria) | 100% | 08/12/22 | 28/04/23 | 102 days | 08/12/22 | 28/04/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.8.9.5.1 |  |  |  |  | Develop document with MWG | 100% | 08/12/22 | 10/03/23 | 67 days | 08/12/22 | 10/03/23 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.9.5.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | 15/03/23 | 21/04/23 | 28 days | 15/03/23 | 21/04/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.8.9.5.3 | T3 | T3-MI-0014 | MCAG |  | Migration, Cutover & Data Strategy approved | 100% | 28/04/23 | 28/04/23 | 0 days | 28/04/23 | 28/04/23 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
4 | 1.8.9.6 |  |  |  |  | Data Cleanse Plan | 84% | 02/03/23 | 15/10/25 | 685 days | 02/03/23 | 03/09/25 | 0 days | 30 days | 138 days | N/A |  | 5 | Yes
5 | 1.8.9.6.1 |  |  |  |  | Develop document with MWG | 100% | 02/03/23 | 10/05/23 | 50 days | 02/03/23 | 10/05/23 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.9.6.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | 11/05/23 | 07/06/23 | 20 days | 11/05/23 | 07/06/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.8.9.6.3 | T3 | T3-MI-0020 | MCAG |  | Data Cleanse Plan approved | 100% | 19/07/23 | 19/07/23 | 0 days | 19/07/23 | 19/07/23 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.9.6.4 |  |  |  |  | Monitor Programme Participant adherence to Data Cleanse Plan | 80% | 15/06/23 | 28/03/25 | 467 days | 15/06/23 | 28/03/25 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.9.6.5 |  |  |  |  | MTDs | 98% | 16/08/24 | 24/01/25 | 115 days | 16/08/24 | 31/01/25 | 1 day | -5 days | 24 days | N/A |  | 5.4 | Yes
6 | 1.8.9.6.5.1 |  |  |  |  | ESME ID | 100% | 16/08/24 | 20/12/24 | 90 days | 16/08/24 | 20/12/24 | 1 day | 0 days | 0 days | N/A |  | 5.4 | Yes
7 | 1.8.9.6.5.1.1 | T3 | T3-MI-0024 | MCAG (Transition) |  | DCC to extract ESME ID and share with LDSO | 100% | 16/08/24 | 16/08/24 | 0 days | 16/08/24 | 16/08/24 | 1 day | 0 days | 0 days | DCC/SI |  | 5.5 | Yes
7 | 1.8.9.6.5.1.2 | T3 | T3-MI-0025 | MCAG (Transition) |  | LDSO ‘full refresh’ between their Registration Service and the EES (ESME ID) | 100% | 21/10/24 | 11/11/24 | 16 days | 21/10/24 | 11/11/24 | 0 days | 0 days | 16 days | LDSO/EES | Proposed | 5.5 | Yes
7 | 1.8.9.6.5.1.3 |  |  |  |  | Suppliers complete investigation of exceptions and resolution of exceptions | 100% | 20/12/24 | 20/12/24 | 1 day | 20/12/24 | 20/12/24 | 0 days | 0 days | 0 days | Supplier |  | 5.4 | Yes
7 | 1.8.9.6.5.1.4 |  |  |  |  | ESME ID Complete | 100% | 20/12/24 | 20/12/24 | 0 days | 20/12/24 | 20/12/24 | 1 day | 0 days | 0 days |  |  | 5.4 | Yes
6 | 1.8.9.6.5.2 |  |  |  |  | Meter Location and Number of Displayed Register Digits | 96% | 13/09/24 | 24/01/25 | 96 days | 13/09/24 | 31/01/25 | 0 days | -5 days | 5 days | N/A |  | 5.4 | Yes
7 | 1.8.9.6.5.2.1 |  |  |  |  | MEM to extract data and share with LDSO | 100% | 13/09/24 | 20/09/24 | 6 days | 13/09/24 | 20/09/24 | 0 days | 0 days | 5 days | MEM/SI |  | 5.4 | Yes
7 | 1.8.9.6.5.2.2 | T3 | T3-MI-0026 | MCAG (Transition) |  | LDSO ‘full refresh’ between their Registration Service and the EES (Meter Location and Number of Displayed Register Digits) | 100% | 21/10/24 | 15/11/24 | 16 days | 28/10/24 | 18/11/24 | -5 days | -1 day | 16 days | LDSO /EES | Approved | 5.5 | Yes
7 | 1.8.9.6.5.2.3 |  |  |  |  | Suppliers complete investigation of exceptions and resolution of exceptions | 0% | 24/01/25 | 24/01/25 | 1 day | 31/01/25 | 31/01/25 | -5 days | -5 days | 0 days | Supplier |  | 5.4 | Yes
7 | 1.8.9.6.5.2.4 |  |  |  |  | Meter Location and Number of Displayed Register Digits Complete | 0% | 24/01/25 | 24/01/25 | 0 days | 31/01/25 | 31/01/25 | -4 days | -5 days | 0 days |  |  | 5.4 | Yes
5 | 1.8.9.6.6 |  |  |  |  | Registration Data | 81% | 06/09/24 | 15/10/25 | 289 days | 06/09/24 | 03/09/25 | 0 days | 30 days | 142 days | N/A |  | 5.4 | Yes
6 | 1.8.9.6.6.1 |  |  |  |  | Connection Type | 100% | 06/09/24 | 11/11/24 | 47 days | 06/09/24 | 11/11/24 | 0 days | 0 days | 31 days | N/A |  | 5.4 | Yes
7 | 1.8.9.6.6.1.1 | T3 | T3-MI-0027 | MCAG (Transition) |  | Automated Population of Connection Type for Measurement Classes ‘B’, ‘D’, ‘F’ & ‘G’ | 100% | 04/10/24 | 04/10/24 | 0 days | 04/10/24 | 04/10/24 | 1 day | 0 days | 0 days | LDSO | Approved | 5.5 | Yes
7 | 1.8.9.6.6.1.2 | T3 | T3-MI-0028 | MCAG (Transition) |  | BAU Population of Connection Type for Site Specific LLFCs within Measurement Classes ‘C’ & ‘E’ | 100% | 04/10/24 | 04/10/24 | 0 days | 04/10/24 | 04/10/24 | 1 day | 0 days | 0 days | LDSO | Approved | 5.5 | Yes
7 | 1.8.9.6.6.1.3 | T3 | T3-MI-0029 | MCAG (Transition) |  | Automated Population of Connection Type for Smart Meters within Measurement Class ‘A’ | 100% | 04/10/24 | 04/10/24 | 0 days | 04/10/24 | 04/10/24 | 1 day | 0 days | 0 days | LDSO | Approved | 5.5 | Yes
7 | 1.8.9.6.6.1.4 |  |  |  |  | Population of Connection Type for Traditional and Advanced Meters within Measurement Class ‘A’ | 100% | 06/09/24 | 06/09/24 | 1 day | 06/09/24 | 06/09/24 | 0 days | 0 days | 0 days | Suppliers |  | 5.4 | Yes
7 | 1.8.9.6.6.1.5 | T3 | T3-MI-0030 | MCAG (Transition) |  | Automated Population of Null Connection Type | 100% | 04/10/24 | 04/10/24 | 0 days | 04/10/24 | 04/10/24 | 1 day | 0 days | 0 days | LDSO | Approved | 5.5 | Yes
7 | 1.8.9.6.6.1.6 |  |  |  |  | Full MPAN refresh to ESS | 100% | 21/10/24 | 11/11/24 | 16 days | 21/10/24 | 11/11/24 | 0 days | 0 days | 15 days | LDSO/EES |  | 5.4 | Yes
7 | 1.8.9.6.6.1.7 |  |  |  |  | Connection Type Complete | 100% | 11/11/24 | 11/11/24 | 0 days | 11/11/24 | 11/11/24 | 1 day | 0 days | 0 days |  |  | 5.4 | Yes
6 | 1.8.9.6.6.2 |  |  |  |  | Domestic Premises Indicator | 0% | 19/09/25 | 15/10/25 | 19 days | 08/08/25 | 03/09/25 | 30 days | 30 days | 2 days | N/A |  | 5.4 | Yes
7 | 1.8.9.6.6.2.1 |  |  |  |  | The DCC to extract Domestic Premises Indicator from the CSS and provide a file to each LDSO and EES. | 0% | 19/09/25 | 22/09/25 | 2 days | 19/09/25 | 22/09/25 | 0 days | 0 days | 1 day | DCC |  | 5.4 | Yes
7 | 1.8.9.6.6.2.2 |  |  |  |  | Each LDSO notifies the DCC of any exceptions | 0% | 23/09/25 | 23/09/25 | 1 day | 23/09/25 | 23/09/25 | 0 days | 0 days | 0 days | LDSO |  | 5.4 | Yes
7 | 1.8.9.6.6.2.3 |  |  |  |  | Each LDSO and DCC completes investigation and resolution of exceptions | 0% | 15/10/25 | 15/10/25 | 1 day | 15/10/25 | 15/10/25 | 0 days | 0 days | 0 days | LDSO / DCC |  | 5.4 | Yes
7 | 1.8.9.6.6.2.4 |  |  |  |  | Domestic Premises Indicator Complete | 0% | 15/10/25 | 15/10/25 | 0 days | 15/10/25 | 15/10/25 | 1 day | 0 days | 0 days |  |  | 5.4 | Yes
5 | 1.8.9.6.7 |  |  |  |  | Export / Import MPANs | 100% | 22/03/24 | 18/10/24 | 151 days | 22/03/24 | 18/10/24 | 0 days | 0 days | 0 days | N/A |  | 5.4 | Yes
6 | 1.8.9.6.7.1 |  |  |  |  | Linking of Export / Import MPANS | 100% | 22/03/24 | 18/10/24 | 151 days | 22/03/24 | 18/10/24 | 0 days | 0 days | 0 days | N/A |  | 5.4 | Yes
7 | 1.8.9.6.7.1.1 |  |  |  |  | LDSO utilises BAU processing (DB05s) to populate each import/export association | 100% | 22/03/24 | 22/03/24 | 1 day | 22/03/24 | 22/03/24 | 0 days | 0 days | 0 days | LDSO |  | 5.4 | Yes
7 | 1.8.9.6.7.1.2 |  |  |  |  | Each LDSO notifies the Registered Supplier of any exceptions | 100% | 19/04/24 | 19/04/24 | 1 day | 19/04/24 | 19/04/24 | 0 days | 0 days | 0 days | LDSO |  | 5.4 | Yes
7 | 1.8.9.6.7.1.3 |  |  |  |  | Each Supplier completes investigation and resolution of exceptions | 100% | 23/08/24 | 23/08/24 | 1 day | 23/08/24 | 23/08/24 | 0 days | 0 days | 0 days | Supplier |  | 5.4 | Yes
7 | 1.8.9.6.7.1.4 | T3 | T3-MI-0031 | MCAG (Transition) |  | Each LDSO has linked al relevant import/export MPANS | 100% | 18/10/24 | 18/10/24 | 0 days | 18/10/24 | 18/10/24 | 1 day | 0 days | 0 days | LDSO |  | 5.5 | Yes
7 | 1.8.9.6.7.1.5 |  |  |  |  | Linking of Export / Import MPANS Complete | 100% | 18/10/24 | 18/10/24 | 0 days | 18/10/24 | 18/10/24 | 1 day | 0 days | 0 days |  |  | 5.4 | Yes
5 | 1.8.9.6.8 | T2 | T2-MI-0450 | MCAG (Transition) |  | Pre-migration data cleanse complete | 0% | 13/08/25 | 13/08/25 | 0 days | 13/08/25 | 13/08/25 | 0 days | -1 day | 0 days | SI Migration |  | 5 | Yes
3 | 1.8.10 |  |  |  |  | Migration Period Planning | 83% | 03/07/23 | 26/11/24 | 367 days | 03/07/23 | 26/11/24 | 0 days | 0 days | -484 days | N/A |  | 5 | Yes
4 | 1.8.10.1 |  |  |  |  | Migration Implementation Plan (incl. Migration Exit Criteria) | 83% | 03/07/23 | 26/11/24 | 367 days | 03/07/23 | 26/11/24 | 0 days | 0 days | -484 days | N/A |  | 5 | Yes
5 | 1.8.10.1.1 |  |  |  |  | Migration Threshold Volumes | 100% | 03/07/23 | 20/11/23 | 101 days | 03/07/23 | 20/11/23 | 0 days | 0 days | 3 days | N/A |  | 5 | Yes
6 | 1.8.10.1.1.1 |  |  |  |  | Threshold volumes reviewed by MWG | 100% | 03/07/23 | 14/09/23 | 54 days | 03/07/23 | 14/09/23 | 0 days | 0 days | 0 days | SI Migration |  | 5.6 | Yes
6 | 1.8.10.1.1.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | 15/09/23 | 20/11/23 | 47 days | 15/09/23 | 20/11/23 | 0 days | 0 days | 3 days | PP |  | 5.9 | Yes
6 | 1.8.10.1.1.3 | T3 | T3-MI-0021 | SITAG |  | Threshold volumes approved at TMAG | 100% | 20/11/23 | 20/11/23 | 0 days | 20/11/23 | 20/11/23 | 1 day | 0 days | 0 days | SI Migration |  | 5.12 | Yes
5 | 1.8.10.1.2 |  |  |  |  | Define acceptance criteria for M15 | 100% | 04/09/23 | 20/12/23 | 78 days | 04/09/23 | 20/12/23 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.8.10.1.2.1 |  |  |  |  | Review acceptance criteria and reporting requirements with MWG | 100% | 04/09/23 | 09/11/23 | 49 days | 04/09/23 | 09/11/23 | 0 days | 0 days | 9 days | SI Migration |  | 5 | Yes
6 | 1.8.10.1.2.2 |  |  |  |  | Artefact review (via TMAG) and updates | 100% | 10/11/23 | 20/12/23 | 29 days | 10/11/23 | 20/12/23 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
6 | 1.8.10.1.2.3 | T3 | T3-MI-0022 | SITAG |  | Acceptance criteria for M15 agreed at TMAG | 100% | 20/12/23 | 20/12/23 | 0 days | 20/12/23 | 20/12/23 | 1 day | 0 days | 0 days | SI Migration |  | 5.14 | Yes
5 | 1.8.10.1.3 |  |  |  |  | M10/M11 cut-over plan | 100% | 21/12/23 | 04/06/24 | 119 days | 21/12/23 | 04/06/24 | 0 days | 0 days | 0 days | N/A |  | 5.16 | Yes
6 | 1.8.10.1.3.1 |  |  |  |  | Draft Document | 100% | 21/12/23 | 16/04/24 | 84 days | 21/12/23 | 16/04/24 | 0 days | 0 days | 0 days | SI Transition |  | 5.16 | Yes
6 | 1.8.10.1.3.2 |  |  |  |  | Share Document with SRO | 100% | 17/04/24 | 17/04/24 | 1 day | 17/04/24 | 17/04/24 | 0 days | 0 days | 0 days | SI Transition |  | 5.16 | Yes
6 | 1.8.10.1.3.3 |  |  |  |  | Industry Consultation | 100% | 23/04/24 | 07/05/24 | 11 days | 23/04/24 | 07/05/24 | 0 days | 0 days | 0 days | SI Transition |  | 5.16 | Yes
6 | 1.8.10.1.3.4 |  |  |  |  | Assurance Meeting | 100% | 21/05/24 | 21/05/24 | 1 day | 21/05/24 | 21/05/24 | 0 days | 0 days | 0 days | SI Transition |  | 5.16 | Yes
6 | 1.8.10.1.3.5 | T3 | T3-MI-0023 | MCAG |  | MCAG Approval of M10/M11 Cut-over Plan | 100% | 04/06/24 | 04/06/24 | 0 days | 04/06/24 | 04/06/24 | 1 day | 0 days | 0 days | SI Transition |  | 5.26 | Yes
5 | 1.8.10.1.4 |  |  |  |  | M16 Methodology | 10% | 31/07/24 | 26/11/24 | 85 days | 31/07/24 | 26/11/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
6 | 1.8.10.1.4.1 |  |  |  |  | Draft Document | 12% | 31/07/24 | 08/10/24 | 50 days | 31/07/24 | 08/10/24 | 0 days | 0 days | 0 days | SI Transition |  | 5.26 | Yes |  | 17/12/24 - Production of this artefact has been delayed. M16 decision making process to be reviewed in Jan 2025 following CR055.
6 | 1.8.10.1.4.2 |  |  |  |  | Share Document with SRO | 0% | 09/10/24 | 09/10/24 | 1 day | 09/10/24 | 09/10/24 | 0 days | 0 days | 0 days | SI Transition |  | 5.26 | Yes |  | 17/12/24 - Production of this artefact has been delayed. M16 decision making process to be reviewed in Jan 2025 following CR055.
6 | 1.8.10.1.4.3 |  |  |  |  | Industry Consultation | 0% | 15/10/24 | 29/10/24 | 11 days | 15/10/24 | 29/10/24 | 0 days | 0 days | 0 days | SI Transition |  | 5.26 | Yes |  | 17/12/24 - Production of this artefact has been delayed. M16 decision making process to be reviewed in Jan 2025 following CR055.
6 | 1.8.10.1.4.4 |  |  |  |  | Assurance Meeting | 0% | 12/11/24 | 12/11/24 | 1 day | 12/11/24 | 12/11/24 | 0 days | 0 days | 0 days | SI Transition |  | 5.26 | Yes |  | 17/12/24 - Production of this artefact has been delayed. M16 decision making process to be reviewed in Jan 2025 following CR055.
6 | 1.8.10.1.4.5 | T2 | T3-MI-0500 | MCAG (Transition) |  | M16 methodology approved | 0% | 26/11/24 | 26/11/24 | 0 days | 26/11/24 | 26/11/24 | 1 day | 0 days | 0 days | SI Transition | Approved | 5.26 | Yes |  | 17/12/24 - Production of this artefact has been delayed. M16 decision making process to be reviewed in Jan 2025 following CR055.
3 | 1.8.11 |  |  |  |  | Preparation for Cutover to Live | 0% | 28/06/24 | 17/10/25 | 341 days | 28/06/24 | 22/10/25 | 0 days | -3 days | 140 days | N/A |  | 6.11 | Yes
4 | 1.8.11.1 |  |  |  |  | Central Systems Prepare for Cutover to Live | 0% | 28/06/24 | 26/09/25 | 326 days | 28/06/24 | 26/09/25 | 0 days | 0 days | 140 days | N/A |  | 6.11 | Yes
5 | 1.8.11.1.1 |  |  |  |  | DCC (Functionality available June 2024) | 100% | 28/06/24 | 28/06/24 | 0 days | 28/06/24 | 28/06/24 | 0 days | -1 day | 0 days | DCC |  | 6.11 | Yes
5 | 1.8.11.1.2 |  |  |  |  | Development of Comms Approach and Declaration Guidance | 0% | 28/04/25 | 14/08/25 | 79 days | 03/03/25 | 19/06/25 | 40 days | 40 days | 0 days | N/A |  | 6.11 | Yes
6 | 1.8.11.1.2.1 |  |  |  |  | Draft Cutover Comms Approach | 0% | 28/04/25 | 17/07/25 | 59 days | 28/04/25 | 17/07/25 | 0 days | 0 days | 0 days | SI Transition |  | 6.11 | Yes
6 | 1.8.11.1.2.2 |  |  |  |  | Draft Cutover Comms Approach shared | 0% | 17/07/25 | 17/07/25 | 0 days | 17/07/25 | 17/07/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.11 | Yes
6 | 1.8.11.1.2.3 |  |  |  |  | Development of Implementation Group | 0% | 28/04/25 | 17/07/25 | 59 days | 28/04/25 | 17/07/25 | 0 days | 0 days | 0 days | SI Transition |  | 6.11 | Yes
6 | 1.8.11.1.2.4 |  |  |  |  | Implementation Group Established | 0% | 17/07/25 | 17/07/25 | 0 days | 17/07/25 | 17/07/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.11 | Yes
6 | 1.8.11.1.2.5 |  |  |  |  | Finalised Cutover Comms Approach shared | 0% | 14/08/25 | 14/08/25 | 0 days | 14/08/25 | 14/08/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.11 | Yes
5 | 1.8.11.1.3 |  |  |  |  | Development of Cutover Plan requirements with Participants | 0% | 28/04/25 | 04/09/25 | 94 days | 03/03/25 | 06/08/25 | 40 days | 21 days | 35 days | N/A |  | 6.11 | Yes
6 | 1.8.11.1.3.1 |  |  |  |  | Development of SIT Participant Cutover Plans | 0% | 28/04/25 | 17/07/25 | 59 days | 28/04/25 | 17/07/25 | 0 days | 0 days | 0 days | SI Transition |  | 6.11 | Yes
6 | 1.8.11.1.3.2 |  |  |  |  | SIT Participant Cutover Plans Ready | 0% | 17/07/25 | 17/07/25 | 0 days | 17/07/25 | 17/07/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.11 | Yes
6 | 1.8.11.1.3.3 |  |  |  |  | Programme SIT Participant Cutover Plan Assurance | 0% | 18/07/25 | 04/09/25 | 35 days | 18/07/25 | 17/09/25 | 0 days | -9 days | -9 days | SI Transition |  | 6.11 | Yes
5 | 1.8.11.1.4 |  |  |  |  | M10/M11 Cutover Activities | 0% | 05/09/25 | 26/09/25 | 15 days | 14/04/25 | 26/09/25 | 105 days | 0 days | 0 days |  |  | 6.11 | Yes
6 | 1.8.11.1.4.1 |  |  |  |  | Production DIP Portal (DIP Deployment) | 0% | 05/09/25 | 05/09/25 | 0 days | 05/09/25 | 05/09/25 | 1 day | 0 days | 0 days | Elexon,DIP Manager |  | 6.11 | Yes
6 | 1.8.11.1.4.2 |  |  |  |  | Production Certificates (DIP Deployment) | 0% | 05/09/25 | 05/09/25 | 0 days | 05/09/25 | 05/09/25 | 1 day | 0 days | 0 days | Elexon,DIP Manager |  | 6.11 | Yes
6 | 1.8.11.1.4.3 |  |  |  |  | Completion of the pre-M10 MHHS Data Cleanse | 0% | 24/09/25 | 24/09/25 | 0 days | 24/09/25 | 24/09/25 | 1 day | 0 days | 0 days | PP,DCC,SI Transition |  | 6.11 | Yes
6 | 1.8.11.1.4.4 |  |  |  |  | Market-wide Participant MHHS Supporting Functionality Ready - Confirmation from Code Bodies | 0% | 15/09/25 | 15/09/25 | 0 days | 15/09/25 | 15/09/25 | 0 days | -1 day | 0 days | Code Bodies |  | 6.11 | Yes |  | 09/10/24 - WR and Fola O extended duration by 110d so the activity completes at 04/08/25.
6 | 1.8.11.1.4.5 |  |  |  |  | Market-wide Participant MHHS Supporting Functionality Ready | 0% | 22/09/25 | 22/09/25 | 0 days | 22/09/25 | 22/09/25 | 0 days | -1 day | 0 days | PP |  | 6.11 | Yes |  | 09/10/24 - WR and Fola O reduced the lag so the activity completes at 11/08/25.
6 | 1.8.11.1.4.6 |  |  |  |  | Elexon Central Services Deployment | 0% | 19/09/25 | 19/09/25 | 0 days | 19/09/25 | 19/09/25 | 1 day | 0 days | 0 days | DIP Manager,Elexon |  | 6.11 | Yes
6 | 1.8.11.1.4.7 |  |  |  |  | Service Management Go-Live | 0% | 19/09/25 | 19/09/25 | 0 days | 19/09/25 | 19/09/25 | 1 day | 0 days | 0 days | Elexon |  | 6.11 | Yes
6 | 1.8.11.1.4.8 |  |  |  |  | Data Transfer Service (DTS) New Functionality Deployment | 0% | 19/09/25 | 19/09/25 | 0 days | 19/09/25 | 19/09/25 | 1 day | 0 days | 0 days | Code Bodies,Electralink |  | 6.11 | Yes
6 | 1.8.11.1.4.9 |  |  |  |  | Electricity Enquiry Service (EES) Deployment | 0% | 19/09/25 | 19/09/25 | 0 days | 19/09/25 | 19/09/25 | 1 day | 0 days | 0 days | Code Bodies |  | 6.11 | Yes
6 | 1.8.11.1.4.10 |  |  |  |  | MPRS, UMSO Role, LDSO Role Operational | 0% | 19/09/25 | 19/09/25 | 0 days | 19/09/25 | 19/09/25 | 1 day | 0 days | 0 days | PP |  | 6.11 | Yes
6 | 1.8.11.1.4.11 |  |  |  |  | Population of Domestic Premises Indicator | 0% | 19/09/25 | 19/09/25 | 0 days | 19/09/25 | 19/09/25 | 1 day | 0 days | 0 days | PP,DCC,SI Transition |  | 6.11 | Yes
6 | 1.8.11.1.4.12 |  |  |  |  | Population of Market Segment | 0% | 19/09/25 | 19/09/25 | 0 days | 19/09/25 | 19/09/25 | 1 day | 0 days | 0 days | PP,SI Transition |  | 6.11 | Yes
6 | 1.8.11.1.4.13 |  |  |  |  | Early Life Support Implemented | 0% | 19/09/25 | 19/09/25 | 0 days | 19/09/25 | 19/09/25 | 1 day | 0 days | 0 days | SI Transition,Elexon,Central Services |  | 6.11 | Yes
6 | 1.8.11.1.4.14 |  |  |  |  | MCC Tested and Ready to Operate | 0% | 19/09/25 | 19/09/25 | 0 days | 19/09/25 | 19/09/25 | 0 days | -1 day | 0 days | SI Migration |  | 6.11 | Yes
6 | 1.8.11.1.4.15 |  |  |  |  | MCC Operational | 0% | 19/09/25 | 19/09/25 | 0 days | 19/09/25 | 19/09/25 | 0 days | -1 day | 0 days | SI Migration |  | 6.11 | Yes
6 | 1.8.4.1.4 | T3 | T3-MI-0034 | MCAG (Transition) |  | Central Systems live and Codes designated at 00:00 | 0% | 22/09/25 | 22/09/25 | 0 days | 22/09/25 | 22/09/25 | 1 day | 0 days | 0 days | SI Transition | Proposed | 6.11 | Yes
6 | 1.8.11.1.4.17 |  |  |  |  | SIT Participant Qualification - The final date by which participant qualification status can be confirmed for participants to be ready for the start of Migration at M11. | 0% | 26/09/25 | 26/09/25 | 0 days | 26/09/25 | 26/09/25 | 1 day | 0 days | 0 days | PP,Code Bodies,BSC PAB |  | 6.11 | Yes
4 | 1.8.11.2 |  |  |  |  | Cutover Governance M10 | 0% | 10/09/25 | 24/09/25 | 11 days | 30/07/25 | 24/09/25 | 30 days | 0 days | -16 days | N/A |  | 6.11 | Yes
5 | 1.8.11.2.1 |  |  |  |  | Confirmation that Pre-migration Data Cleanse Activities have successfully taken place | 0% | 10/09/25 | 10/09/25 | 0 days | 10/09/25 | 10/09/25 | 0 days | -1 day | 0 days | PP |  | 6.11 | Yes
5 | 1.8.11.2.2 |  |  |  |  | Confirmation of Helix E2E Settlement Testing Complete | 0% | 15/09/25 | 15/09/25 | 0 days | 15/09/25 | 15/09/25 | 0 days | -1 day | 0 days |  |  | 6.11 | Yes
5 | 1.8.11.2.3 |  |  |  |  | Confirmation of assurance of Helix E2E Settlement Testing | 0% | 15/09/25 | 15/09/25 | 0 days | 15/09/25 | 15/09/25 | 0 days | -1 day | 0 days |  |  | 6.11 | Yes
5 | 1.8.11.2.4 |  |  |  |  | Confirmation of Qualification Status for SIT MVC | 0% | 15/09/25 | 15/09/25 | 0 days | 15/09/25 | 15/09/25 | 0 days | -1 day | 0 days | SIT MVC,Code Bodies |  | 6.11 | Yes
5 | 1.8.11.2.5 |  |  |  |  | Confirmation of Qualification Status for Non-SIT LDSOs | 0% | 15/09/25 | 15/09/25 | 0 days | 15/09/25 | 15/09/25 | 0 days | -1 day | 0 days | PP,Code Bodies |  | 6.11 | Yes
5 | 1.8.11.2.6 |  |  |  |  | Confirmation of Qualification Status of at least one Supplier and their contracted Agents | 0% | 15/09/25 | 15/09/25 | 0 days | 15/09/25 | 15/09/25 | 0 days | -1 day | 0 days | S&A Qualification |  | 6.11 | Yes
5 | 1.8.11.2.7 |  |  |  |  | Declaration from all Central Services and LDSOs that they are in a position to move forwards | 0% | 15/09/25 | 15/09/25 | 0 days | 15/09/25 | 15/09/25 | 0 days | -1 day | 0 days | DIP Manager,Elexon,PP,Code Bodies |  | 6.11 | Yes
5 | 1.8.11.2.8 |  |  |  |  | Market-wide Participant MHHS Migration Supporting Functionality is Live | 0% | 15/09/25 | 15/09/25 | 0 days | 15/09/25 | 15/09/25 | 0 days | -1 day | 0 days |  |  | 6.11 | Yes
5 | 1.8.11.2.9 |  |  |  |  | TORWG (Recommendation from TORWG that the Programme should enter M10) | 0% | 17/09/25 | 17/09/25 | 0 days | 17/09/25 | 17/09/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.11 | Yes
5 | 1.8.4.1.4 | T3 | T3-MI-0035 | MCAG (Transition) |  | MCAG (Confirm that the Programme can Enter M10) | 0% | 19/09/25 | 19/09/25 | 0 days | 19/09/25 | 19/09/25 | 1 day | 0 days | 0 days | SI Migration | Approved | 6.11 | Yes
5 | 1.8.11.2.11 |  |  |  |  | Self-Declaration from all Central Services and LDSOs that Cutover activities have been successfully carried out | 0% | 22/09/25 | 22/09/25 | 0 days | 22/09/25 | 22/09/25 | 1 day | 0 days | 0 days | PP,DCC,Code Bodies |  | 6.11 | Yes
5 | 1.8.11.2.12 |  |  |  |  | Confirmation that DIP and ECS have been deployed, Service management is active, ISD has been populated | 0% | 22/09/25 | 22/09/25 | 0 days | 22/09/25 | 22/09/25 | 1 day | 0 days | 0 days | Elexon,DIP Manager |  | 6.11 | Yes
5 | 1.8.11.2.13 |  |  |  |  | Self-Declarations against all M10 Data Cleanse Activities | 0% | 22/09/25 | 22/09/25 | 0 days | 22/09/25 | 22/09/25 | 1 day | 0 days | 0 days | PP |  | 6.11 | Yes
5 | 1.8.11.2.14 |  |  |  |  | IF-047 has been sent | 0% | 22/09/25 | 22/09/25 | 0 days | 22/09/25 | 22/09/25 | 1 day | 0 days | 0 days | ECS |  | 6.11 | Yes
5 | 1.8.11.2.15 |  |  |  |  | Recommendation from TORWG that PSG should approve M10 | 0% | 23/09/25 | 23/09/25 | 0 days | 23/09/25 | 23/09/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.11 | Yes
5 | 1.8.11.2.16 |  |  |  |  | PSG (OFGEM and PSG to Approve That Conditions of M10 and M13 Have Been Met) | 0% | 24/09/25 | 24/09/25 | 0 days | 24/09/25 | 24/09/25 | 1 day | 0 days | 0 days | SI Transition,Ofgem |  | 6.11 | Yes
4 | 1.8.11.3 |  |  |  |  | Cutover Governance M11 | 0% | 26/09/25 | 17/10/25 | 16 days | 26/09/25 | 22/10/25 | 0 days | -3 days | 16 days |  |  | 6.11 | Yes
5 | 1.8.11.3.1 |  |  |  |  | Confirmation of Qualified Parties from Code Bodies | 0% | 26/09/25 | 10/10/25 | 11 days | 26/09/25 | 10/10/25 | 0 days | 0 days | 0 days | Code Bodies,SIT Participants |  | 6.11 | Yes
5 | 1.8.11.3.2 |  |  |  |  | Self-Declaration that MHHS Functionality will be deployed to Production by Qualified parties | 0% | 10/10/25 | 10/10/25 | 0 days | 10/10/25 | 10/10/25 | 1 day | 0 days | 0 days | PP |  | 6.11 | Yes
5 | 1.8.11.3.3 |  |  |  |  | Production Service Activation Activities have taken place | 0% | 10/10/25 | 10/10/25 | 0 days | 10/10/25 | 10/10/25 | 1 day | 0 days | 0 days | PP |  | 6.11 | Yes
5 | 1.8.11.3.4 |  |  |  |  | TORWG (Confirmation of Qualified Parties from TORWG) | 0% | 13/10/25 | 13/10/25 | 0 days | 13/10/25 | 13/10/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.11 | Yes
5 | 1.8.11.3.5 | T3 | T3-MI-0036 | MCAG (Transition) |  | MCAG (Provide recommendation to PSG on M11 decision) | 0% | 15/10/25 | 15/10/25 | 0 days | 15/10/25 | 15/10/25 | 1 day | 0 days | 0 days | SI Migration | Approved | 6.11 | Yes
5 | 1.8.11.3.6 |  |  |  |  | PSG (OFGEM and PSG Decision to Confirm M11 and M12) | 0% | 17/10/25 | 17/10/25 | 0 days | 17/10/25 | 17/10/25 | 1 day | 0 days | 0 days | SI Transition |  | 6.11 | Yes
3 | 1.8.12 |  |  |  |  | UMS / Advanced Migration | 0% | 23/10/25 | 30/04/27 | 397 days | 23/10/25 | 07/05/27 | 0 days | -5 days | 6 days | N/A |  | 6 | Yes
4 | 1.8.12.1 |  |  |  |  | SIT MVC UMS / Advanced Migration | 0% | 23/10/25 | 22/04/27 | 391 days | 23/10/25 | 22/04/27 | 0 days | 0 days | 0 days |  |  | 6 | Yes
4 | 1.8.12.2 |  |  |  |  | SIT Non-MVC UMS / Advanced Migration | 0% | 29/12/25 | 29/03/27 | 326 days | 02/01/26 | 02/04/27 | -4 days | -4 days | 0 days |  |  | 6 | Yes
4 | 1.8.12.3 |  |  |  |  | Wave 1 UMS / Advanced Migration | 0% | 15/05/26 | 30/04/27 | 251 days | 15/05/26 | 30/04/27 | 0 days | 0 days | -10 days |  |  | 6.0 | Yes
4 | 1.8.12.4 |  |  |  |  | Wave 2 UMS / Advanced Migration | 0% | 01/07/26 | 29/04/27 | 217 days | 01/07/26 | 29/04/27 | 0 days | 0 days | 1 day |  |  | 6 | Yes
4 | 1.8.12.5 |  |  |  |  | Wave 3 UMS / Advanced Migration | 0% | 14/08/26 | 26/04/27 | 182 days | 27/08/26 | 07/05/27 | -9 days | -9 days | 1 day |  |  | 6 | Yes
4 | 1.8.12.6 |  |  |  |  | Wave 4 UMS / Advanced Migration | 0% | 23/10/26 | 30/04/27 | 136 days | 23/10/26 | 30/04/27 | 0 days | 0 days | 5 days |  |  | 6 | Yes
3 | 1.8.13 |  |  |  |  | Smart / Non-Smart Migration | 0% | 23/10/25 | 30/04/27 | 397 days | 23/10/25 | 07/05/27 | 0 days | -5 days | 6 days | N/A |  | 6 | Yes
4 | 1.8.13.1 |  |  |  |  | SIT MVC Smart / Non-Smart Migration | 0% | 23/10/25 | 22/04/27 | 391 days | 23/10/25 | 22/04/27 | 0 days | 0 days | 0 days |  |  | 6 | Yes
4 | 1.8.13.2 |  |  |  |  | SIT Non-MVC Smart / Non-Smart Migration | 0% | 29/12/25 | 29/03/27 | 326 days | 02/01/26 | 02/04/27 | -4 days | -4 days | 0 days |  |  | 6 | Yes
4 | 1.8.13.3 |  |  |  |  | Wave 1 Smart / Non-Smart Migration | 0% | 15/05/26 | 30/04/27 | 251 days | 15/05/26 | 30/04/27 | 0 days | 0 days | -10 days |  |  | 6.0 | Yes
4 | 1.8.13.4 |  |  |  |  | Wave 2 Smart / Non-Smart Migration | 0% | 01/07/26 | 29/04/27 | 217 days | 01/07/26 | 29/04/27 | 0 days | 0 days | 1 day |  |  | 6 | Yes
4 | 1.8.13.5 |  |  |  |  | Wave 3 Smart / Non-Smart Migration | 0% | 14/08/26 | 26/04/27 | 182 days | 27/08/26 | 07/05/27 | -9 days | -9 days | 1 day |  |  | 6 | Yes
4 | 1.8.13.6 |  |  |  |  | Wave 4 Smart / Non-Smart Migration | 0% | 23/10/26 | 30/04/27 | 136 days | 23/10/26 | 30/04/27 | 0 days | 0 days | 5 days |  |  | 6 | Yes
3 | 1.8.14 |  |  |  |  | External Programme Dependency Management | 66% | 31/10/22 | 29/08/25 | 740 days | 31/10/22 | 29/08/25 | 0 days | 0 days | -87 days | N/A |  | 5 | Yes
4 | 1.8.14.1 |  |  |  |  | BSC Mod P432 & REC CP R0015 | 100% | 31/10/22 | 30/04/24 | 392 days | 31/10/22 | 30/04/24 | 0 days | 0 days | -435 days | N/A |  | 5 | Yes
5 | 1.8.14.1.1 |  |  |  |  | MHHSP engagement with BSCCo until Ofgem decision | 100% | 31/10/22 | 15/01/24 | 316 days | 31/10/22 | 15/01/24 | 0 days | 0 days | -84 days | CPT,SRO Function |  | 5 | Yes
5 | 1.8.14.1.2 |  |  |  |  | Monitor progress and await implementation date | 100% | 16/01/24 | 30/04/24 | 76 days | 16/01/24 | 30/04/24 | 0 days | 0 days | -576 days | CPT,SRO Function |  | 5 | Yes
4 | 1.8.14.2 |  |  |  |  | BSC Mod P434 | 57% | 31/10/22 | 23/07/25 | 713 days | 31/10/22 | 23/07/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.8.14.2.1 |  |  |  |  | MHHSP engagement with BSCCo until Ofgem decision | 100% | 31/10/22 | 23/01/23 | 61 days | 31/10/22 | 23/01/23 | 0 days | 0 days | 0 days | CPT,SRO Function |  | 5 | Yes
5 | 1.8.14.2.2 |  |  |  |  | Monitor progress and await implementation date | 52% | 24/01/23 | 23/07/25 | 652 days | 24/01/23 | 23/07/25 | 0 days | 0 days | 0 days | CPT,SRO Function |  | 5 | Yes
4 | 1.8.14.3 |  |  |  |  | Elexon System Capacity Upgrade | 58% | 31/10/22 | 01/07/25 | 697 days | 31/10/22 | 01/07/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.8.14.3.1 |  |  |  |  | Monitor progress to implementation | 58% | 31/10/22 | 01/07/25 | 697 days | 31/10/22 | 01/07/25 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.14.3.2 |  |  |  |  | Implementation date | 0% | 01/07/25 | 01/07/25 | 0 days | 01/07/25 | 01/07/25 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.8.14.4 |  |  |  |  | DCC System Capacity Upgrade | 0% | 28/07/25 | 29/08/25 | 25 days | 28/07/25 | 29/08/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.8.14.4.1 |  |  |  |  | Assurance of DCC capacity upgrade to ensure suitability to support migration | 0% | 28/07/25 | 22/08/25 | 20 days | 28/07/25 | 22/08/25 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
5 | 1.8.14.4.2 | T2 | T2-MI-0350 | MCAG |  | DCC Capacity Upgrade Operational | 0% | 29/08/25 | 29/08/25 | 0 days | 29/08/25 | 29/08/25 | 1 day | 0 days | 0 days | PP |  | 5 | Yes
3 | 1.8.15 |  |  |  |  | Migration - Tier 1 Milestones | 0% | 24/09/25 | 03/08/27 | 484 days | 24/09/25 | 09/08/27 | 1 day | -4 days | 7 days | N/A |  | 5 | Yes
4 | 1.8.15.1 | T1 | T1-MI-2000 | PSG |  | Load Shaping Service switched on (M13) | 0% | 24/09/25 | 24/09/25 | 0 days | 24/09/25 | 24/09/25 | 1 day | 0 days | 0 days | CPT |  | 6.1 | Yes
4 | 1.8.15.2 | T1 | T2-MI-2500 | PSG |  | Load Shaping Service switched on (M13*) - Late Exit | 0% | 24/12/25 | 24/12/25 | 0 days | 24/12/25 | 24/12/25 | 1 day | 0 days | 0 days | CPT |  | 6.1 | Yes
4 | 1.8.15.3 | T1 | T1-MI-3000 | PSG |  | Start of 18-month migration for UMS / Advanced (M11) | 0% | 22/10/25 | 22/10/25 | 0 days | 22/10/25 | 22/10/25 | 1 day | 0 days | 0 days | CPT |  | 6.1 | Yes
4 | 1.8.15.4 | T1 | T2-MI-3500 | PSG |  | Start of 18-month migration for UMS / Advanced (M11*) - Late Exit | 0% | 21/01/26 | 21/01/26 | 0 days | 21/01/26 | 21/01/26 | 1 day | 0 days | 0 days | CPT |  | 6.1 | Yes
4 | 1.8.15.5 | T1 | T1-MI-4000 | PSG |  | Start of 18-month migration for Smart / Non-smart (M12) | 0% | 22/10/25 | 22/10/25 | 0 days | 22/10/25 | 22/10/25 | 1 day | 0 days | 0 days | CPT |  | 6.1 | Yes
4 | 1.8.15.6 | T1 | T2-MI-4500 | PSG |  | Start of 18-month migration for Smart / Non-smart (M12*) - Late Exit | 0% | 21/01/26 | 21/01/26 | 0 days | 21/01/26 | 21/01/26 | 1 day | 0 days | 0 days | CPT |  | 6.1 | Yes
4 | 1.8.15.7 | T1 | T1-MI-6000 | PSG |  | Full transition complete (M15) | 0% | 03/05/27 | 03/05/27 | 0 days | 07/05/27 | 07/05/27 | -3 days | -4 days | 0 days | CPT |  | 6.1 | Yes
4 | 1.8.15.8 | T1 | T2-MI-6500 | PSG |  | Full transition complete (M15*) - Late Exit | 0% | 03/08/27 | 03/08/27 | 0 days | 09/08/27 | 09/08/27 | -3 days | -4 days | 0 days | CPT |  | 6.1 | Yes
2 | 1.9 |  |  |  |  | BUSINESS & OPERATIONAL READINESS | 6% | 31/10/22 | 17/12/27 | 1340 days? | 31/10/22 | 23/12/27 | 0 days | -4 days | 376 days? | N/A |  |  | Yes
3 | 1.9.1 |  |  |  |  | Service Management | 26% | 19/09/23 | 24/06/27 | 983 days | 19/09/23 | 24/06/27 | 0 days | 0 days | 143 days | N/A |  | 5 | Yes
4 | 1.9.1.1 |  |  |  |  | Service Management Strategy | 100% | 19/09/23 | 27/02/24 | 116 days | 19/09/23 | 27/02/24 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
5 | 1.9.1.1.1 |  |  |  |  | Develop document with relevant participants (incl. review of the design baseline to ensure service management arrangements are in place across the solution architecture) | 100% | 19/09/23 | 12/01/24 | 84 days | 19/09/23 | 12/01/24 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.9.1.1.2 |  |  |  |  | Artefact review (via relevant Advisory Group) and updates | 100% | 15/01/24 | 26/02/24 | 31 days | 15/01/24 | 26/02/24 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
5 | 1.9.1.1.3 | T3 | T3-BC-0010 | MCAG |  | Service Management Strategy approved | 100% | 27/02/24 | 27/02/24 | 0 days | 27/02/24 | 27/02/24 | 1 day | 0 days | 0 days | SI Design |  | 5.16 | Yes
4 | 1.9.1.2 |  |  |  |  | Early Life Support Model | 82% | 28/02/24 | 30/07/24 | 110 days | 28/02/24 | 30/07/24 | 0 days | 0 days | 0 days | N/A |  | 5.16 | Yes
5 | 1.9.1.2.1 |  |  |  |  | Draft Document | 96% | 28/02/24 | 10/06/24 | 74 days | 28/02/24 | 10/06/24 | 0 days | 0 days | 0 days | SI Transition |  | 5.24 | Yes
5 | 1.9.1.2.2 |  |  |  |  | Share document with SRO | 0% | 11/06/24 | 11/06/24 | 1 day | 11/06/24 | 11/06/24 | 0 days | 0 days | 0 days | SI Transition |  | 5.24 | Yes
5 | 1.9.1.2.3 |  |  |  |  | Industry Consultation | 0% | 18/06/24 | 02/07/24 | 11 days | 18/06/24 | 02/07/24 | 0 days | 0 days | 0 days | SI Transition |  | 5.24 | Yes
5 | 1.9.1.2.4 |  |  |  |  | Assurance Meeting | 0% | 16/07/24 | 16/07/24 | 1 day | 16/07/24 | 16/07/24 | 0 days | 0 days | 0 days | SI Transition |  | 5.24 | Yes
5 | 1.9.1.2.5 | T3 | T3-MI-0033 | MCAG (Transition) |  | MCAG Approval of Early Life Support Model | 0% | 30/07/24 | 30/07/24 | 0 days | 30/07/24 | 30/07/24 | 1 day | 0 days | 0 days | SI Transition |  | 5.24 | Yes |  | 14/01/25 - High level update was shared at December TORWG. Further update on the Transition governance framework will be given at the January TORWG. Early Life Support Model is a part of this framework.
4 | 1.9.1.3 |  |  |  |  | Service Management Arrangements Implementation | 0% | 25/09/25 | 24/06/27 | 456 days | 25/09/25 | 24/06/27 | 0 days | 0 days | 3 days | N/A |  | 5 | Yes
5 | 1.9.1.3.1 |  |  |  |  | Hypercare post M10 | 0% | 25/09/25 | 14/01/26 | 80 days | 25/09/25 | 14/01/26 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
5 | 1.9.1.3.2 |  |  |  |  | Monitor Elexon implementation of Service Management arrangements | 0% | 23/10/25 | 24/06/27 | 436 days | 23/10/25 | 24/06/27 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
3 | 1.9.2 |  |  |  |  | Service Activation | 0% | 31/10/22 | 28/10/26 | 1043 days? | 31/10/22 | 22/10/26 | 0 days | 4 days | 754 days? | N/A |  | 5.24 | Yes
4 | 1.9.2.1 |  |  |  |  | SIT MVC | 0% | 31/10/22 | 10/10/25 | 770 days? | 03/02/25 | 22/09/25 | -590 days | 14 days | 770 days? |  |  | 5.31 | Yes
5 | 1.9.2.1.1 |  |  |  |  | SIT MVC Service Activation Preparation Tasks | 0% | 03/02/25 | 28/02/25 | 20 days | 03/02/25 | 28/02/25 | 0 days | 0 days | 20 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.1 |  |  |  |  | Identify operational resources | 0% | 03/02/25 | 07/02/25 | 5 days | 03/02/25 | 07/02/25 | 0 days | 0 days | 5 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.2 |  |  |  |  | Define and approve operational support model | 0% | 10/02/25 | 14/02/25 | 5 days | 10/02/25 | 14/02/25 | 0 days | 0 days | 5 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.3 |  |  |  |  | Confirm SA Training completed | 0% | 10/02/25 | 21/02/25 | 10 days | 10/02/25 | 21/02/25 | 0 days | 0 days | 10 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.4 |  |  |  |  | Participant Engagement / Communications | 0% | 10/02/25 | 28/02/25 | 15 days | 10/02/25 | 28/02/25 | 0 days | 0 days | 15 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.5 |  |  |  |  | Internal Communications | 0% | 10/02/25 | 28/02/25 | 15 days | 10/02/25 | 28/02/25 | 0 days | 0 days | 15 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.6 |  |  |  |  | Validate User Access | 0% | 17/02/25 | 21/02/25 | 5 days | 17/02/25 | 21/02/25 | 0 days | 0 days | 5 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.7 |  |  |  |  | Target Systems and Environments Ready | 0% | 20/02/25 | 24/02/25 | 3 days | 20/02/25 | 24/02/25 | 0 days | 0 days | 3 days | HELIX |  | 5.31 | Yes
6 | 1.9.2.1.1.8 |  |  |  |  | Provide opeartional resources with LWIs | 0% | 17/02/25 | 21/02/25 | 5 days | 17/02/25 | 21/02/25 | 0 days | 0 days | 5 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.9 |  |  |  |  | Business Readiness Governance Approval | 0% | 17/02/25 | 19/02/25 | 3 days | 17/02/25 | 19/02/25 | 0 days | 0 days | 3 days |  |  | 5.31 | Yes
6 | 1.9.2.1.1.10 |  |  |  |  | SIT MVC Service Activation Preparation Tasks Complete | 0% | 28/02/25 | 28/02/25 | 0 days | 28/02/25 | 28/02/25 | 1 day | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.1.2 |  |  |  |  | MHHSP Confirms SIT MVC PPs MHHS Enabled | 0% | 31/10/22 | 31/10/22 | 1 day | 15/04/25 | 15/04/25 | -641 days | -641 days | 1 day |  |  | 5.28 | Yes |  | 22/11/24 - For M11 need MCC enabled - need confirmation suppliers agree to being mhhs enabled
5 | 1.9.2.1.3 |  |  |  |  | SIT MVC Service Activation Implementation | 0% | 12/09/25 | 22/09/25 | 7 days? | 12/09/25 | 22/09/25 | 0 days | 0 days | 7 days? |  |  | 6.13 | Yes
6 | 1.9.2.1.3.1 |  |  |  |  | Add EFD to DIP | 0% | 12/09/25 | 12/09/25 | 1 day | 12/09/25 | 12/09/25 | 0 days | 0 days | 1 day |  |  | 6.13 | Yes
6 | 1.9.2.1.3.2 |  |  |  |  | DIP Promoted to Production | 0% | 15/09/25 | 15/09/25 | 1 day? | 15/09/25 | 15/09/25 | 0 days | 0 days | 1 day? |  |  | 6.13 | Yes
6 | 1.9.2.1.3.3 |  |  |  |  | SIT LDSOs Create Certificates and Test Connectivity | 0% | 16/09/25 | 16/09/25 | 1 day? | 16/09/25 | 16/09/25 | 0 days | 0 days | 1 day? |  |  | 6.13 | Yes
6 | 1.9.2.1.3.4 |  |  |  |  | SIT MVC S&As Create Certificates and Test Connectivity | 0% | 16/09/25 | 16/09/25 | 1 day? | 16/09/25 | 16/09/25 | 0 days | 0 days | 1 day? |  |  | 6.13 | Yes
6 | 1.9.2.1.3.5 |  |  |  |  | Create M16 in Customer Solution | 0% | 16/09/25 | 17/09/25 | 2 days | 16/09/25 | 17/09/25 | 0 days | 0 days | 2 days |  |  | 6.13 | Yes |  | 18/09/24 - This milestone is consistent with the Service Activation Verison 2.0 Process Map.
6 | 1.9.2.1.3.6 |  |  |  |  | Publish ISD | 0% | 18/09/25 | 19/09/25 | 2 days | 18/09/25 | 19/09/25 | 0 days | 0 days | 2 days |  |  | 6.13 | Yes
6 | 1.9.2.1.3.7 |  |  |  |  | SIT LDSOs to update systems with ISD | 0% | 22/09/25 | 22/09/25 | 1 day? | 22/09/25 | 22/09/25 | 0 days | 0 days | 1 day? |  |  | 6.13 | Yes
6 | 1.9.2.1.3.8 |  |  |  |  | SIT MVC S&As to update systems with ISD | 0% | 22/09/25 | 22/09/25 | 1 day? | 22/09/25 | 22/09/25 | 0 days | 0 days | 1 day? |  |  | 6.13 | Yes
6 | 1.9.2.1.3.9 |  |  |  |  | SIT MVC Service Activation Implementation Complete | 0% | 19/09/25 | 19/09/25 | 0 days | 19/09/25 | 19/09/25 | 1 day | 0 days | 0 days |  |  | 6.13 | Yes
5 | 1.9.2.1.4 |  |  |  |  | SIT MVC Service Activation Implementation MDD | 0% | 22/09/25 | 10/10/25 | 15 days | 06/03/25 | 25/03/25 | 142 days | 143 days | 15 days |  |  | 6.13 | Yes
6 | 1.9.2.1.4.1 |  |  |  |  | MDD Manual Load | 0% | 22/09/25 | 30/09/25 | 7 days | 06/03/25 | 14/03/25 | 142 days | 142 days | 7 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.1.4.2 |  |  |  |  | MDD Update | 0% | 01/10/25 | 10/10/25 | 8 days | 14/03/25 | 25/03/25 | 143 days | 143 days | 8 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.1.4.3 |  |  |  |  | SIT MVC Service Activation Implementation MDD Complete | 0% | 10/10/25 | 10/10/25 | 0 days | 25/03/25 | 25/03/25 | 144 days | 143 days | 0 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
5 | 1.9.2.1.5 |  |  |  |  | SIT MVC Service Activation Hypercare | 0% | 12/09/25 | 10/10/25 | 21 days | 03/03/25 | 26/03/25 | 139 days | 142 days | 21 days |  |  | 6.13 | Yes
6 | 1.9.2.1.5.1 |  |  |  |  | Service & Process Monitoring | 0% | 12/09/25 | 07/10/25 | 18 days | 03/03/25 | 26/03/25 | 139 days | 139 days | 18 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.1.5.2 |  |  |  |  | Daily Reporting | 0% | 12/09/25 | 07/10/25 | 18 days | 03/03/25 | 26/03/25 | 139 days | 139 days | 18 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.1.5.3 |  |  |  |  | Issue Management | 0% | 12/09/25 | 07/10/25 | 18 days | 03/03/25 | 26/03/25 | 139 days | 139 days | 18 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.1.5.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | 12/09/25 | 07/10/25 | 18 days | 03/03/25 | 26/03/25 | 139 days | 139 days | 18 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.1.5.5 |  |  |  |  | Handover to MHHSP | 0% | 08/10/25 | 10/10/25 | 3 days | 21/03/25 | 25/03/25 | 143 days | 143 days | 3 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.1.5.6 |  |  |  |  | SIT MVC Service Activation Hypercare Complete | 0% | 10/10/25 | 10/10/25 | 0 days | 25/03/25 | 25/03/25 | 144 days | 143 days | 0 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
4 | 1.9.2.2 |  |  |  |  | SIT Non-MVC | 0% | 31/10/22 | 19/01/26 | 841 days? | 31/10/22 | 01/01/26 | 0 days | 12 days | 841 days? |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
5 | 1.9.2.2.1 |  |  |  |  | SIT Non-MVC Service Activation Preparation Tasks | 0% | 31/10/22 | 28/02/25 | 610 days | 31/10/22 | 31/10/22 | 0 days | 609 days | 610 days |  |  | 6.13 | Yes
6 | 1.9.2.2.1.1 |  |  |  |  | Helix Preparatory Activities Complete | 0% | 28/02/25 | 28/02/25 | 0 days | 31/10/22 | 31/10/22 | 610 days | 609 days | 0 days |  |  | 6.13 | Yes
6 | 1.9.2.2.1.2 |  |  |  |  | MHHSP Confirms SIT Non-MVC PPs MHHS Enabled | 0% | 31/10/22 | 31/10/22 | 1 day | 31/10/22 | 31/10/22 | 0 days | 0 days | 1 day |  |  | 6.13 | Yes |  | 22/11/24 - Confirm Predecessors
5 | 1.9.2.2.2 |  |  |  |  | SIT Non-MVC Service Activation Implementation | 0% | 19/12/25 | 29/12/25 | 7 days? | 23/12/25 | 01/01/26 | -2 days | -3 days | 7 days? |  |  | 5.31 | Yes
6 | 1.9.2.2.2.1 |  |  |  |  | Add EDF to DIP | 0% | 19/12/25 | 19/12/25 | 1 day | 23/12/25 | 24/12/25 | -2 days | -3 days | 1 day |  |  | 5.31 | Yes
6 | 1.9.2.2.2.2 |  |  |  |  | DIP Promoted to Production | 0% | 22/12/25 | 22/12/25 | 1 day | 25/12/25 | 26/12/25 | -3 days | -4 days | 1 day |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.2.2.3 |  |  |  |  | SIT non-MVC S&As Create Certificates and Test Connectivity | 0% | 23/12/25 | 23/12/25 | 1 day? | N/A | N/A | 0 days | 0 days | 1 day? |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.2.2.4 |  |  |  |  | Create M16 in Customer Solution | 0% | 23/12/25 | 24/12/25 | 2 days | 29/12/25 | 30/12/25 | -4 days | -4 days | 2 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.2.2.5 |  |  |  |  | Publish ISD | 0% | 25/12/25 | 26/12/25 | 2 days | 31/12/25 | 01/01/26 | -4 days | -4 days | 2 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.2.2.6 |  |  |  |  | SIT non-MVC S&As to update systems with ISD | 0% | 29/12/25 | 29/12/25 | 1 day? | N/A | N/A | 0 days | 0 days | 1 day? |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.2.2.7 |  |  |  |  | SIT Non-MVC Service Activation Implementation Complete | 0% | 26/12/25 | 26/12/25 | 0 days | 01/01/26 | 01/01/26 | -3 days | -4 days | 0 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
5 | 1.9.2.2.3 |  |  |  |  | SIT Non-MVC Service Activation Implementation MDD | 0% | 29/12/25 | 16/01/26 | 15 days | 05/06/25 | 24/06/25 | 147 days | 148 days | 15 days |  |  | 6.13 | Yes
6 | 1.9.2.2.3.1 |  |  |  |  | MDD Manual Load | 0% | 29/12/25 | 06/01/26 | 7 days | 05/06/25 | 13/06/25 | 147 days | 147 days | 7 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.2.3.2 |  |  |  |  | MDD Update | 0% | 07/01/26 | 16/01/26 | 8 days | 13/06/25 | 24/06/25 | 148 days | 148 days | 8 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.2.3.3 |  |  |  |  | SIT Non-MVC Service Activation Implementation MDD Complete | 0% | 16/01/26 | 16/01/26 | 0 days | 24/06/25 | 24/06/25 | 149 days | 148 days | 0 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
5 | 1.9.2.2.4 |  |  |  |  | Non-SIT MVC Service Activation Hypercare | 0% | 19/12/25 | 19/01/26 | 22 days | 02/06/25 | 26/06/25 | 144 days | 147 days | 22 days |  |  | 6.13 | Yes
6 | 1.9.2.2.4.1 |  |  |  |  | Service& Process Monitoring | 0% | 19/12/25 | 13/01/26 | 18 days | 02/06/25 | 25/06/25 | 144 days | 144 days | 18 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.2.4.2 |  |  |  |  | Daily Reporting | 0% | 19/12/25 | 13/01/26 | 18 days | 02/06/25 | 25/06/25 | 144 days | 144 days | 18 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.2.4.3 |  |  |  |  | Issue Management | 0% | 19/12/25 | 13/01/26 | 18 days | 02/06/25 | 25/06/25 | 144 days | 144 days | 18 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.2.4.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | 19/12/25 | 13/01/26 | 18 days | 02/06/25 | 25/06/25 | 144 days | 144 days | 18 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.2.4.5 |  |  |  |  | Handover to MHHSP | 0% | 14/01/26 | 19/01/26 | 4 days | 23/06/25 | 26/06/25 | 147 days | 147 days | 4 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
6 | 1.9.2.2.4.6 |  |  |  |  | Non-SIT MVC Service Activation Hypercare Complete (M) | 0% | 19/01/26 | 19/01/26 | 0 days | 25/06/25 | 25/06/25 | 149 days | 148 days | 0 days |  |  | 6.13 | Yes |  | 22/11/24 - Dependency added and date shifted.
4 | 1.9.2.3 |  |  |  |  | Wave 1 | 0% | 31/10/22 | 14/05/26 | 924 days | 31/10/22 | 14/05/26 | 0 days | 0 days | 924 days |  |  | 5.31 | Yes |  | 08/07/24 - Confirm Predecessors
5 | 1.9.2.3.1 |  |  |  |  | SIT Non-MVC Service Activation Preparation Tasks | 0% | 31/10/22 | 14/05/26 | 924 days | 31/10/22 | 14/05/26 | 0 days | 0 days | 924 days |  |  | 5.31 | Yes
6 | 1.9.2.3.1.1 |  |  |  |  | Helix Preparatory Activities Complete | 0% | 31/10/22 | 31/10/22 | 0 days | 31/10/22 | 31/10/22 | 0 days | -1 day | 0 days |  |  | 5.29 | Yes
6 | 1.9.2.3.1.2 |  |  |  |  | MHHSP Confirms Wave 1 PPs MHHS Enabled | 0% | 31/10/22 | 31/10/22 | 1 day | 31/10/22 | 31/10/22 | 0 days | 0 days | 1 day |  |  | 5.28 | Yes
6 | 1.9.2.3.1.3 |  |  |  |  | Wave 1 Service Activation | 0% | 16/04/26 | 14/05/26 | 21 days | 13/04/26 | 14/05/26 | 3 days | 0 days | -4 days |  |  | 6.13 | Yes |  | 14/11/24 - Duration reduced to ensure the date remains the same despite a minor change in 2040. Expecting this duration to be further reduced.
5 | 1.9.2.3.2 |  |  |  |  | Wave 1 - Service Activation Implementation | 0% | 01/09/25 | 27/04/26 | 171 days | 01/09/25 | 05/09/25 | 0 days | 166 days | 171 days |  |  | 5.31 | Yes
6 | 1.9.2.3.2.1 |  |  |  |  | MHHSP Enabled Confirmation | 0% | 01/09/25 | 02/09/25 | 2 days | 01/09/25 | 02/09/25 | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.3.2.2 |  |  |  |  | PAB Approval | 0% | 16/04/26 | 17/04/26 | 2 days | 01/09/25 | 02/09/25 | 163 days | 163 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.3.2.3 |  |  |  |  | Add EFD to DIP | 0% | 16/04/26 | 17/04/26 | 2 days | 02/09/25 | 03/09/25 | 162 days | 162 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.3.2.4 |  |  |  |  | DIP Promoted to Production | 0% | 20/04/26 | 21/04/26 | 2 days | 03/09/25 | 04/09/25 | 163 days | 163 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.3.2.5 |  |  |  |  | Create M16 in Customer Solution | 0% | 22/04/26 | 23/04/26 | 2 days | 04/09/25 | 05/09/25 | 164 days | 164 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.3.2.6 |  |  |  |  | Publish ISD | 0% | 24/04/26 | 27/04/26 | 2 days | 04/09/25 | 05/09/25 | 166 days | 166 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.3.2.7 |  |  |  |  | Wave 1 - Service Activation Implementation Complete (M) | 0% | 27/04/26 | 27/04/26 | 0 days | 05/09/25 | 05/09/25 | 167 days | 166 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.3.3 |  |  |  |  | Wave 1 - Service Activation Implementation MDD | 0% | 28/04/26 | 12/05/26 | 11 days | 04/09/25 | 17/09/25 | 168 days | 169 days | 11 days |  |  | 5.31 | Yes
6 | 1.9.2.3.3.1 |  |  |  |  | MDD Manual Load | 0% | 28/04/26 | 04/05/26 | 5 days | 04/09/25 | 10/09/25 | 168 days | 168 days | 5 days |  |  | 5.31 | Yes
6 | 1.9.2.3.3.2 |  |  |  |  | MDD Update | 0% | 05/05/26 | 12/05/26 | 6 days | 10/09/25 | 17/09/25 | 169 days | 169 days | 6 days |  |  | 5.31 | Yes
6 | 1.9.2.3.3.3 |  |  |  |  | Wave 1 - Service Activation Implementation MDD Complete (M) | 0% | 12/05/26 | 12/05/26 | 0 days | 17/09/25 | 17/09/25 | 170 days | 169 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.3.4 |  |  |  |  | Wave 1 - Service Activation Hypercare | 0% | 01/09/25 | 05/05/26 | 177 days | 31/10/22 | 18/09/25 | 740 days | 163 days | 177 days |  |  | 5.31 | Yes
6 | 1.9.2.3.4.1 |  |  |  |  | Service& Process Monitoring | 0% | 16/04/26 | 05/05/26 | 14 days | 01/09/25 | 18/09/25 | 163 days | 163 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.3.4.2 |  |  |  |  | Daily Reporting | 0% | 16/04/26 | 05/05/26 | 14 days | 01/09/25 | 18/09/25 | 163 days | 163 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.3.4.3 |  |  |  |  | Issue Management | 0% | 16/04/26 | 05/05/26 | 14 days | 01/09/25 | 18/09/25 | 163 days | 163 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.3.4.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | 01/09/25 | 18/09/25 | 14 days | 01/09/25 | 18/09/25 | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.3.4.5 |  |  |  |  | Handover to MHHSP | 0% | 19/09/25 | 24/09/25 | 4 days | 15/09/25 | 18/09/25 | 4 days | 4 days | 4 days |  |  | 5.31 | Yes
6 | 1.9.2.3.4.6 |  |  |  |  | Non-SIT LDSO Service Activation Hypercare Complete (M) | 0% | 24/09/25 | 24/09/25 | 0 days | 31/10/22 | 31/10/22 | 758 days | 757 days | 0 days |  |  | 5.31 | Yes
4 | 1.9.2.4 |  |  |  |  | Wave 2 | 0% | 31/10/22 | 01/07/26 | 958 days | 31/10/22 | 30/06/26 | 0 days | 1 day | 958 days |  |  | 5.31 | Yes |  | 08/07/24 - Confirm Predecessors
5 | 1.9.2.4.1 |  |  |  |  | SIT Non-MVC Service Activation Preparation Tasks | 0% | 31/10/22 | 01/07/26 | 958 days | 31/10/22 | 30/06/26 | 0 days | 1 day | 958 days |  |  | 5.31 | Yes
6 | 1.9.2.4.1.1 |  |  |  |  | Helix Preparatory Activities Complete | 0% | 31/10/22 | 31/10/22 | 0 days | 31/10/22 | 31/10/22 | 0 days | -1 day | 0 days |  |  | 5.29 | Yes
6 | 1.9.2.4.1.2 |  |  |  |  | MHHSP Confirms Wave 2 PPs MHHS Enabled | 0% | 31/10/22 | 31/10/22 | 1 day | 31/10/22 | 31/10/22 | 0 days | 0 days | 1 day |  |  | 5.28 | Yes
6 | 1.9.2.4.1.3 |  |  |  |  | Wave 2 Service Activation | 0% | 29/05/26 | 01/07/26 | 24 days | 28/05/26 | 30/06/26 | 1 day | 1 day | -1 day |  |  | 5.24 | Yes
5 | 1.9.2.4.2 |  |  |  |  | Wave 2 - Service Activation Implementation | 0% | 03/11/25 | 09/06/26 | 157 days | 03/11/25 | 07/11/25 | 0 days | 152 days | 157 days |  |  | 5.31 | Yes
6 | 1.9.2.4.2.1 |  |  |  |  | MHHSP Enabled Confirmation | 0% | 03/11/25 | 04/11/25 | 2 days | 03/11/25 | 04/11/25 | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.4.2.2 |  |  |  |  | PAB Approval | 0% | 29/05/26 | 01/06/26 | 2 days | 03/11/25 | 04/11/25 | 149 days | 149 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.4.2.3 |  |  |  |  | Add EFD to DIP | 0% | 29/05/26 | 01/06/26 | 2 days | 04/11/25 | 05/11/25 | 148 days | 148 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.4.2.4 |  |  |  |  | DIP Promoted to Production | 0% | 02/06/26 | 03/06/26 | 2 days | 05/11/25 | 06/11/25 | 149 days | 149 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.4.2.5 |  |  |  |  | Create M16 in Customer Solution | 0% | 04/06/26 | 05/06/26 | 2 days | 06/11/25 | 07/11/25 | 150 days | 150 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.4.2.6 |  |  |  |  | Publish ISD | 0% | 08/06/26 | 09/06/26 | 2 days | 06/11/25 | 07/11/25 | 152 days | 152 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.4.2.7 |  |  |  |  | Wave 2 - Service Activation Implementation Complete (M) | 0% | 09/06/26 | 09/06/26 | 0 days | 07/11/25 | 07/11/25 | 153 days | 152 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.4.3 |  |  |  |  | Wave 2 - Service Activation Implementation MDD | 0% | 06/11/25 | 19/11/25 | 10 days | 06/11/25 | 19/11/25 | 0 days | 0 days | 10 days |  |  | 5.31 | Yes
6 | 1.9.2.4.3.1 |  |  |  |  | MDD Manual Load | 0% | 06/11/25 | 12/11/25 | 5 days | 06/11/25 | 12/11/25 | 0 days | 0 days | 5 days |  |  | 5.31 | Yes
6 | 1.9.2.4.3.2 |  |  |  |  | MDD Update | 0% | 12/11/25 | 19/11/25 | 6 days | 12/11/25 | 19/11/25 | 0 days | 0 days | 6 days |  |  | 5.31 | Yes
6 | 1.9.2.4.3.3 |  |  |  |  | Wave 2 - Service Activation Implementation MDD Complete (M) | 0% | 19/11/25 | 19/11/25 | 0 days | 19/11/25 | 19/11/25 | 1 day | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.4.4 |  |  |  |  | Wave 2 - Service Activation Hypercare | 0% | 03/11/25 | 20/11/25 | 14 days | 03/11/25 | 20/11/25 | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.4.4.1 |  |  |  |  | Service& Process Monitoring | 0% | 03/11/25 | 20/11/25 | 14 days | 03/11/25 | 20/11/25 | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.4.4.2 |  |  |  |  | Daily Reporting | 0% | 03/11/25 | 20/11/25 | 14 days | 03/11/25 | 20/11/25 | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.4.4.3 |  |  |  |  | Issue Management | 0% | 03/11/25 | 20/11/25 | 14 days | 03/11/25 | 20/11/25 | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.4.4.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | 03/11/25 | 20/11/25 | 14 days | 03/11/25 | 20/11/25 | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.4.4.5 |  |  |  |  | Handover to MHHSP | 0% | 17/11/25 | 20/11/25 | 4 days | 17/11/25 | 20/11/25 | 0 days | 0 days | 4 days |  |  | 5.31 | Yes
6 | 1.9.2.4.4.6 |  |  |  |  | Wave 2 - Service Activation Hypercare Complete (M) | 0% | 19/11/25 | 19/11/25 | 0 days | 19/11/25 | 19/11/25 | 1 day | 0 days | 0 days |  |  | 5.31 | Yes
4 | 1.9.2.5 |  |  |  |  | Wave 3 | 0% | 31/10/22 | 13/08/26 | 989 days | 31/10/22 | 26/08/26 | 0 days | -9 days | 989 days |  |  | 5.31 | Yes
5 | 1.9.2.5.1 |  |  |  |  | SIT Non-MVC Service Activation Preparation Tasks | 0% | 31/10/22 | 13/08/26 | 989 days | 31/10/22 | 26/08/26 | 0 days | -9 days | 989 days |  |  | 5.31 | Yes |  | 08/07/24 - Confirm Predecessors
6 | 1.9.2.5.1.1 |  |  |  |  | Helix Preparatory Activities Complete | 0% | 31/10/22 | 31/10/22 | 0 days | 31/10/22 | 31/10/22 | 0 days | -1 day | 0 days |  |  | 5.29 | Yes
6 | 1.9.2.5.1.2 |  |  |  |  | MHHSP Confirms Wave 3 PPs MHHS Enabled | 0% | 31/10/22 | 31/10/22 | 1 day | 31/10/22 | 31/10/22 | 0 days | 0 days | 1 day |  |  | 5.28 | Yes
6 | 1.9.2.5.1.3 |  |  |  |  | Wave 3 Service Activation | 0% | 31/07/26 | 13/08/26 | 10 days | 24/07/26 | 26/08/26 | 5 days | -9 days | -15 days |  |  | 5.24 | Yes
5 | 1.9.2.5.2 |  |  |  |  | Wave 3 - Service Activation Implementation | 0% | 22/12/25 | 13/08/26 | 169 days | 22/12/25 | 30/12/25 | 0 days | 162 days | 169 days |  |  | 5.31 | Yes
6 | 1.9.2.5.2.1 |  |  |  |  | MHHSP Enabled Confirmation | 0% | 22/12/25 | 23/12/25 | 2 days | 22/12/25 | 23/12/25 | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.5.2.2 |  |  |  |  | PAB Approval | 0% | 31/07/26 | 03/08/26 | 2 days | 22/12/25 | 23/12/25 | 159 days | 159 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.5.2.3 |  |  |  |  | Add EFD to DIP | 0% | 04/08/26 | 05/08/26 | 2 days | 23/12/25 | 24/12/25 | 160 days | 160 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.5.2.4 |  |  |  |  | DIP Promoted to Production | 0% | 06/08/26 | 07/08/26 | 2 days | 29/12/25 | 30/12/25 | 158 days | 158 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.5.2.5 |  |  |  |  | Create M16 in Customer Solution | 0% | 10/08/26 | 11/08/26 | 2 days | 29/12/25 | 30/12/25 | 160 days | 160 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.5.2.6 |  |  |  |  | Publish ISD | 0% | 12/08/26 | 13/08/26 | 2 days | 29/12/25 | 30/12/25 | 162 days | 162 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.5.2.7 |  |  |  |  | Wave 3 - Service Activation Implementation Complete (M) | 0% | 13/08/26 | 13/08/26 | 0 days | 30/12/25 | 30/12/25 | 163 days | 162 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.5.3 |  |  |  |  | Wave 3 - Service Activation Implementation MDD | 0% | 31/10/22 | 15/01/26 | 839 days | 31/10/22 | 15/01/26 | 0 days | 0 days | 839 days |  |  | 5.31 | Yes
6 | 1.9.2.5.3.1 |  |  |  |  | MDD Manual Load | 0% | 29/12/25 | 06/01/26 | 7 days | 29/12/25 | 06/01/26 | 0 days | 0 days | 7 days |  |  | 5.31 | Yes
6 | 1.9.2.5.3.2 |  |  |  |  | MDD Update | 0% | 06/01/25 | 15/01/26 | 269 days | 06/01/25 | 15/01/26 | 0 days | 0 days | 269 days |  |  | 5.31 | Yes
6 | 1.9.2.5.3.3 |  |  |  |  | Wave 3 - Service Activation Implementation MDD Complete (M) | 0% | 31/10/22 | 31/10/22 | 0 days | 31/10/22 | 31/10/22 | 0 days | -1 day | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.5.4 |  |  |  |  | Wave 3 - Service Activation Hypercare | 0% | 31/10/22 | 16/01/26 | 840 days | 31/10/22 | 16/01/26 | 0 days | 0 days | 840 days |  |  | 5.31 | Yes
6 | 1.9.2.5.4.1 |  |  |  |  | Service& Process Monitoring | 0% | 22/12/25 | 16/01/26 | 20 days | 22/12/25 | 16/01/26 | 0 days | 0 days | 20 days |  |  | 5.31 | Yes
6 | 1.9.2.5.4.2 |  |  |  |  | Daily Reporting | 0% | 22/12/25 | 16/01/26 | 20 days | 22/12/25 | 16/01/26 | 0 days | 0 days | 20 days |  |  | 5.31 | Yes
6 | 1.9.2.5.4.3 |  |  |  |  | Issue Management | 0% | 22/12/25 | 16/01/26 | 20 days | 22/12/25 | 16/01/26 | 0 days | 0 days | 20 days |  |  | 5.31 | Yes
6 | 1.9.2.5.4.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | 22/12/25 | 16/01/26 | 20 days | 22/12/25 | 16/01/26 | 0 days | 0 days | 20 days |  |  | 5.31 | Yes
6 | 1.9.2.5.4.5 |  |  |  |  | Handover to MHHSP | 0% | 12/01/26 | 15/01/26 | 4 days | 12/01/26 | 15/01/26 | 0 days | 0 days | 4 days |  |  | 5.31 | Yes
6 | 1.9.2.5.4.6 |  |  |  |  | Wave 3 Service Activation Hypercare Complete (M) | 0% | 31/10/22 | 31/10/22 | 0 days | 31/10/22 | 31/10/22 | 0 days | -1 day | 0 days |  |  | 5.31 | Yes
4 | 1.9.2.6 |  |  |  |  | Wave 4 | 0% | 31/10/22 | 28/10/26 | 1043 days | 31/10/22 | 22/10/26 | 0 days | 4 days | 1043 days |  |  | 5.31 | Yes |  | 08/07/24 - Confirm Predecessors
5 | 1.9.2.6.1 |  |  |  |  | SIT Non-MVC Service Activation Preparation Tasks | 0% | 31/10/22 | 28/10/26 | 1043 days | 31/10/22 | 22/10/26 | 0 days | 4 days | 1043 days |  |  | 5.31 | Yes
6 | 1.9.2.6.1.1 |  |  |  |  | Helix Preparatory Activities Complete | 0% | 31/10/22 | 31/10/22 | 0 days | 31/10/22 | 31/10/22 | 0 days | -1 day | 0 days |  |  | 5.29 | Yes
6 | 1.9.2.6.1.2 |  |  |  |  | MHHSP Confirms Wave 4 PPs MHHS Enabled | 0% | 31/10/22 | 31/10/22 | 1 day | 31/10/22 | 31/10/22 | 0 days | 0 days | 1 day |  |  | 5.28 | Yes |  | 8/7/24 - Confirm Predecessors
6 | 1.9.2.6.1.3 |  |  |  |  | Wave 4 Service Activation | 0% | 25/09/26 | 28/10/26 | 24 days | 21/09/26 | 22/10/26 | 4 days | 4 days | -1 day |  |  | 5.24 | Yes
5 | 1.9.2.6.2 |  |  |  |  | Wave 4 - Service Activation Implementation | 0% | 02/03/26 | 07/10/26 | 158 days | 03/03/25 | 06/03/26 | 260 days | 153 days | 158 days |  |  | 5.31 | Yes
6 | 1.9.2.6.2.1 |  |  |  |  | MHHSP Enabled Confirmation | 0% | 02/03/26 | 03/03/26 | 2 days | 02/03/26 | 03/03/26 | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.6.2.2 |  |  |  |  | PAB Approval | 0% | 25/09/26 | 25/09/26 | 1 day | 03/03/25 | 03/03/25 | 409 days | 409 days | 1 day |  |  | 5.31 | Yes
6 | 1.9.2.6.2.3 |  |  |  |  | Add EFD to DIP | 0% | 28/09/26 | 29/09/26 | 2 days | 03/03/26 | 04/03/26 | 149 days | 149 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.6.2.4 |  |  |  |  | DIP Promoted to Production | 0% | 30/09/26 | 01/10/26 | 2 days | 04/03/26 | 05/03/26 | 150 days | 150 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.6.2.5 |  |  |  |  | Create M16 in Customer Solution | 0% | 02/10/26 | 05/10/26 | 2 days | 05/03/26 | 06/03/26 | 151 days | 151 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.6.2.6 |  |  |  |  | Publish ISD | 0% | 06/10/26 | 07/10/26 | 2 days | 05/03/26 | 06/03/26 | 153 days | 153 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.6.2.7 |  |  |  |  | Wave 4 - Service Activation Implementation Complete (M) | 0% | 07/10/26 | 07/10/26 | 0 days | 06/03/26 | 06/03/26 | 154 days | 153 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.6.3 |  |  |  |  | Wave 4 - Service Activation Implementation MDD | 0% | 06/03/26 | 26/03/26 | 15 days | 06/03/26 | 26/03/26 | 0 days | 0 days | 15 days |  |  | 5.31 | Yes
6 | 1.9.2.6.3.1 |  |  |  |  | MDD Manual Load | 0% | 06/03/26 | 16/03/26 | 7 days | 06/03/26 | 16/03/26 | 0 days | 0 days | 7 days |  |  | 5.31 | Yes
6 | 1.9.2.6.3.2 |  |  |  |  | MDD Update | 0% | 16/03/26 | 26/03/26 | 9 days | 16/03/26 | 26/03/26 | 0 days | 0 days | 9 days |  |  | 5.31 | Yes
6 | 1.9.2.6.3.3 |  |  |  |  | Wave 4 - Service Activation Implementation MDD Complete | 0% | 25/03/26 | 25/03/26 | 0 days | 25/03/26 | 25/03/26 | 1 day | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.6.4 |  |  |  |  | Wave 4 - Service Activation Hypercare | 0% | 02/03/26 | 26/03/26 | 19 days | 02/03/26 | 26/03/26 | 0 days | 0 days | 19 days |  |  | 5.31 | Yes
6 | 1.9.2.6.4.1 |  |  |  |  | Service& Process Monitoring | 0% | 02/03/26 | 26/03/26 | 19 days | 02/03/26 | 26/03/26 | 0 days | 0 days | 19 days |  |  | 5.31 | Yes
6 | 1.9.2.6.4.2 |  |  |  |  | Daily Reporting | 0% | 02/03/26 | 26/03/26 | 19 days | 02/03/26 | 26/03/26 | 0 days | 0 days | 19 days |  |  | 5.31 | Yes
6 | 1.9.2.6.4.3 |  |  |  |  | Issue Management | 0% | 02/03/26 | 26/03/26 | 19 days | 02/03/26 | 26/03/26 | 0 days | 0 days | 19 days |  |  | 5.31 | Yes
6 | 1.9.2.6.4.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | 02/03/26 | 26/03/26 | 19 days | 02/03/26 | 26/03/26 | 0 days | 0 days | 19 days |  |  | 5.31 | Yes
6 | 1.9.2.6.4.5 |  |  |  |  | Handover to MHHSP | 0% | 02/03/26 | 05/03/26 | 4 days | 02/03/26 | 05/03/26 | 0 days | 0 days | 4 days |  |  | 5.31 | Yes
6 | 1.9.2.6.4.6 |  |  |  |  | Wave 4 - Service Activation Hypercare Complete (M) | 0% | 25/03/26 | 25/03/26 | 0 days | 25/03/26 | 25/03/26 | 1 day | 0 days | 0 days |  |  | 5.31 | Yes
4 | 1.9.2.7 |  |  |  |  | Non-SIT LDSO | 0% | 31/10/22 | 18/09/25 | 754 days | 31/10/22 | 01/09/25 | 0 days | 13 days | 754 days |  |  | 5.31 | Yes
5 | 1.9.2.7.1 |  |  |  |  | Non-SIT LDSO Service Activation Data Loading | 0% | 07/06/24 | 07/02/25 | 176 days | 07/06/24 | 07/02/25 | 0 days | 0 days | 176 days |  |  | 5.31 | Yes
6 | 1.9.2.7.1.1 |  |  |  |  | Define pre Non-SIT LDSO upfront activities | 0% | 07/06/24 | 17/06/24 | 7 days | 07/06/24 | 17/06/24 | 0 days | 0 days | 7 days |  |  | 5.31 | Yes
6 | 1.9.2.7.1.2 |  |  |  |  | Execute Non-SIT LDSO Activities | 0% | 03/02/25 | 07/02/25 | 5 days | 03/02/25 | 07/02/25 | 0 days | 0 days | 5 days |  |  | 5.31 | Yes
7 | 1.9.2.7.1.2.1 |  |  |  |  | Create Entity Forms in Customer Solution | 0% | 03/02/25 | 05/02/25 | 3 days | 03/02/25 | 05/02/25 | 0 days | 0 days | 3 days | PMP |  | 5.31 | Yes
7 | 1.9.2.7.1.2.2 |  |  |  |  | DIP - Promote to Production Environment | 0% | 03/02/25 | 05/02/25 | 3 days | 03/02/25 | 05/02/25 | 0 days | 0 days | 3 days | DIP |  | 5.31 | Yes
7 | 1.9.2.7.1.2.3 |  |  |  |  | DIP - Enable Technology capabilities for participants | 0% | 03/02/25 | 05/02/25 | 3 days | 03/02/25 | 05/02/25 | 0 days | 0 days | 3 days | DIP |  | 5.31 | Yes
7 | 1.9.2.7.1.2.4 |  |  |  |  | DIP - Add EFD to DIP | 0% | 03/02/25 | 05/02/25 | 3 days | 03/02/25 | 05/02/25 | 0 days | 0 days | 3 days | DIP |  | 5.31 | Yes
7 | 1.9.2.7.1.2.5 |  |  |  |  | ISD - Replicate Entity Forms from CS | 0% | 06/02/25 | 07/02/25 | 2 days | 06/02/25 | 07/02/25 | 0 days | 0 days | 2 days | HELIX |  | 5.31 | Yes
7 | 1.9.2.7.1.2.6 |  |  |  |  | MDD - Load MHHS roles | 0% | 03/02/25 | 05/02/25 | 3 days | 03/02/25 | 05/02/25 | 0 days | 0 days | 3 days | PMP |  | 5.31 | Yes
6 | 1.9.2.7.1.3 |  |  |  |  | Non-SIT LDSO Service Activation Data Loading Completed (M) | 0% | 07/02/25 | 07/02/25 | 0 days | 07/02/25 | 07/02/25 | 1 day | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.7.2 |  |  |  |  | SIT Non-MVC Service Activation Preparation Tasks | 0% | 31/10/22 | 18/09/25 | 754 days | 31/10/22 | 01/09/25 | 0 days | 13 days | 754 days |  |  | 5.31 | Yes
6 | 1.9.2.7.2.1 |  |  |  |  | Helix Preparatory Activities Complete | 0% | 31/10/22 | 31/10/22 | 0 days | 31/10/22 | 31/10/22 | 0 days | -1 day | 0 days |  |  | 5.29 | Yes
6 | 1.9.2.7.2.2 |  |  |  |  | MHHSP Confirms Non-SIT LDSO PPs MHHS Enabled | 0% | 31/10/22 | 31/10/22 | 1 day | 31/10/22 | 31/10/22 | 0 days | 0 days | 1 day |  |  | 5.28 | Yes |  | 08/07/24 - Confirm Predecessors
6 | 1.9.2.7.2.3 |  |  |  |  | Non-SIT LDSO Service Activation | 0% | 11/09/25 | 18/09/25 | 6 days | 25/08/25 | 01/09/25 | 13 days | 13 days | -3 days |  |  | 6.12 | Yes |  | 13/11/24 - Dependency updated so that this activity is now connected to the right activity. This has resulted in the forecast slipping, but this is now the correct date, this will be baselined at Approval Group.
5 | 1.9.2.7.3 |  |  |  |  | Non-SIT LDSO Service Activation Implementation | 0% | 24/02/25 | 27/02/25 | 4 days | 24/02/25 | 27/02/25 | 0 days | 0 days | 4 days |  |  | 5.31 | Yes
6 | 1.9.2.7.3.1 |  |  |  |  | MHHSP Enabled Confirmation | 0% | 24/02/25 | 25/02/25 | 2 days | 24/02/25 | 25/02/25 | 0 days | 0 days | 2 days | MHHSP |  | 5.31 | Yes
6 | 1.9.2.7.3.2 |  |  |  |  | PAB Approval | 0% | 24/02/25 | 25/02/25 | 2 days | 24/02/25 | 25/02/25 | 0 days | 0 days | 2 days | QUALF |  | 5.31 | Yes
6 | 1.9.2.7.3.3 |  |  |  |  | Add EFD to DIP | 0% | 25/02/25 | 26/02/25 | 2 days | 25/02/25 | 26/02/25 | 0 days | 0 days | 2 days | DIP |  | 5.31 | Yes
6 | 1.9.2.7.3.4 |  |  |  |  | DIP Promoted to Production | 0% | 26/02/25 | 27/02/25 | 2 days | 26/02/25 | 27/02/25 | 0 days | 0 days | 2 days | DIP |  | 5.31 | Yes
6 | 1.9.2.7.3.5 |  |  |  |  | Create M16 in Customer Solution | 0% | 26/02/25 | 27/02/25 | 2 days | 26/02/25 | 27/02/25 | 0 days | 0 days | 2 days | PMP |  | 5.31 | Yes
6 | 1.9.2.7.3.6 |  |  |  |  | Publish ISD | 0% | 26/02/25 | 27/02/25 | 2 days | 26/02/25 | 27/02/25 | 0 days | 0 days | 2 days |  |  | 5.31 | Yes
6 | 1.9.2.7.3.7 |  |  |  |  | Non-SIT LDSO Service Activation Implementation Completed (M) | 0% | 27/02/25 | 27/02/25 | 0 days | 27/02/25 | 27/02/25 | 1 day | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.7.4 |  |  |  |  | Non-SIT LDSO Service Activation Implementation MDD | 0% | 27/02/25 | 18/03/25 | 14 days | 27/02/25 | 18/03/25 | 0 days | 0 days | 14 days |  |  | 5.31 | Yes
6 | 1.9.2.7.4.1 |  |  |  |  | MDD Manual Load | 0% | 27/02/25 | 07/03/25 | 7 days | 27/02/25 | 07/03/25 | 0 days | 0 days | 7 days | PMP |  | 5.31 | Yes
6 | 1.9.2.7.4.2 |  |  |  |  | MDD Update | 0% | 07/03/25 | 18/03/25 | 8 days | 07/03/25 | 18/03/25 | 0 days | 0 days | 8 days | PMP |  | 5.31 | Yes
6 | 1.9.2.7.4.3 |  |  |  |  | Non-SIT LDSO Service Activation Implementation MDD Complete (M) | 0% | 18/03/25 | 18/03/25 | 0 days | 18/03/25 | 18/03/25 | 1 day | 0 days | 0 days |  |  | 5.31 | Yes
5 | 1.9.2.7.5 |  |  |  |  | Non-SIT LDSO Service Activation Hypercare | 0% | 24/02/25 | 19/03/25 | 18 days | 24/02/25 | 19/03/25 | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
6 | 1.9.2.7.5.1 |  |  |  |  | Non-SIT LDSO Service Activation Hypercare Support | 0% | 24/02/25 | 19/03/25 | 18 days | 24/02/25 | 19/03/25 | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
7 | 1.9.2.7.5.1.1 |  |  |  |  | Service& Process Monitoring | 0% | 24/02/25 | 19/03/25 | 18 days | 24/02/25 | 19/03/25 | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
7 | 1.9.2.7.5.1.2 |  |  |  |  | Daily Reporting | 0% | 24/02/25 | 19/03/25 | 18 days | 24/02/25 | 19/03/25 | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
7 | 1.9.2.7.5.1.3 |  |  |  |  | Issue Management | 0% | 24/02/25 | 19/03/25 | 18 days | 24/02/25 | 19/03/25 | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
7 | 1.9.2.7.5.1.4 |  |  |  |  | SA Hypercare Close Down Activities | 0% | 24/02/25 | 19/03/25 | 18 days | 24/02/25 | 19/03/25 | 0 days | 0 days | 18 days |  |  | 5.31 | Yes
7 | 1.9.2.7.5.1.5 |  |  |  |  | Handover to MHHSP | 0% | 14/03/25 | 18/03/25 | 3 days | 14/03/25 | 18/03/25 | 0 days | 0 days | 3 days |  |  | 5.31 | Yes
7 | 1.9.2.7.5.1.6 |  |  |  |  | Non-SIT LDSO Service Activation Hypercare Complete (M) | 0% | 18/03/25 | 18/03/25 | 0 days | 18/03/25 | 18/03/25 | 1 day | 0 days | 0 days |  |  | 5.31 | Yes
3 | 1.9.3 |  |  |  |  | Implement Early Life Support Plan | 0% | 07/07/25 | 19/09/25 | 55 days | 07/07/25 | 19/09/25 | 0 days | 0 days | 10 days | N/A |  | 5 | Yes
4 | 1.9.3.1 |  |  |  | MHHS-ART095 | Implement Early Life Support Plan | 0% | 07/07/25 | 19/09/25 | 55 days | 07/07/25 | 19/09/25 | 0 days | 0 days | 10 days | SI Transition |  | 5.23 | Yes |  | 12/11/24 - Once MCAG approval of Early Life Support Plan is secured, dependency will be added back in.
3 | 1.9.4 |  |  |  |  | Business Continuity and Disaster Recovery Plan | 0% | 31/07/25 | 24/09/25 | 40 days | 31/07/25 | 24/09/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.9.4.1 |  |  |  |  | Central Parties BCDRs in Place | 0% | 31/07/25 | 27/08/25 | 20 days | 31/07/25 | 27/08/25 | 0 days | 0 days | 0 days | SI Design |  | 5 | Yes
4 | 1.9.4.2 |  |  |  |  | Risk Based Assurance of Cental Party BCDRs | 0% | 28/08/25 | 24/09/25 | 20 days | 28/08/25 | 24/09/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
3 | 1.9.5 |  |  |  |  | Training and Support Materials | 0% | 21/08/25 | 14/10/25 | 39 days | 21/08/25 | 14/10/25 | 0 days | 0 days | -1 day | N/A |  | 5 | Yes
4 | 1.9.5.1 |  |  |  |  | Develop document | 0% | 21/08/25 | 17/09/25 | 20 days | 21/08/25 | 17/09/25 | 0 days | 0 days | 0 days | SI Migration |  | 5 | Yes
4 | 1.9.5.2 |  |  |  |  | Document review and update | 0% | 18/09/25 | 14/10/25 | 19 days | 18/09/25 | 14/10/25 | 0 days | 0 days | -1 day | SI Migration |  | 5 | Yes
4 | 1.9.5.3 |  |  |  | MHHS-ART118 | Training and Support Materials approved | 0% | 14/10/25 | 14/10/25 | 0 days | 14/10/25 | 14/10/25 | 1 day | 0 days | 0 days | SI Migration |  | 5 | Yes
3 | 1.9.6 |  |  |  |  | PP Business Change | 0% | 03/02/25 | 31/07/25 | 129 days | 03/02/25 | 31/07/25 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.9.6.1 |  |  |  |  | Plan stakeholder management | 0% | 03/02/25 | 31/07/25 | 129 days | 03/02/25 | 31/07/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.9.6.2 |  |  |  |  | Manage stakeholders | 0% | 03/02/25 | 31/07/25 | 129 days | 03/02/25 | 31/07/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.9.6.3 |  |  |  |  | Develop & implement changes to KPIs, organisation & people management | 0% | 03/02/25 | 31/07/25 | 129 days | 03/02/25 | 31/07/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.9.6.4 |  |  |  |  | Develop & test changes to business processes | 0% | 03/02/25 | 31/07/25 | 129 days | 03/02/25 | 31/07/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.9.6.5 |  |  |  |  | Develop and deliver training | 0% | 03/02/25 | 31/07/25 | 129 days | 03/02/25 | 31/07/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.9.6.6 |  |  |  |  | Programme support for PP Business Change activities | 0% | 03/02/25 | 31/07/25 | 129 days | 03/02/25 | 31/07/25 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
3 | 1.9.7 |  |  |  |  | Transition to New Settlement Timetable (M16) | 0% | 22/10/25 | 17/12/27 | 562 days | 22/10/25 | 23/12/27 | 1 day | -4 days | 2 days | N/A |  | 5.15 | Yes
4 | 1.9.7.1 |  |  |  |  | Elexon to produce Settlement Calendar for Settlement Year 2025/2026 | 0% | 22/10/25 | 22/10/25 | 0 days | 22/10/25 | 22/10/25 | 1 day | 0 days | 0 days | PP |  | 5.15 | Yes
4 | 1.9.7.2 |  |  |  |  | Elexon monitor settlement data of migrated MPANs | 0% | 23/10/25 | 24/06/27 | 436 days | 23/10/25 | 24/06/27 | 0 days | 0 days | 0 days | PP |  | 5.15 | Yes
4 | 1.9.7.3 |  |  |  |  | M16 Checkpoint 1 | 0% | 25/06/26 | 25/06/26 | 0 days | 25/06/26 | 25/06/26 | 1 day | 0 days | 0 days | PP |  | 5.15 | Yes
4 | 1.9.7.4 |  |  |  |  | Confirm if M16 date retained as 07/12/2026 | 0% | 23/07/26 | 23/07/26 | 0 days | 23/07/26 | 23/07/26 | 1 day | 0 days | 0 days | CPT |  | 5.15 | Yes
4 | 1.9.7.5 |  |  |  |  | Readiness assessment of participants' readiness to transition to new Settlement Timetable | 0% | 20/08/26 | 20/08/26 | 0 days | 20/08/26 | 20/08/26 | 1 day | 0 days | 0 days | CPT |  | 5.15 | Yes
4 | 1.9.7.6 |  |  |  |  | Elexon to produce Settlement Calendar for Settlement Year 2026 up until day before M16 cutover | 0% | 19/10/26 | 19/10/26 | 0 days | 19/10/26 | 19/10/26 | 1 day | 0 days | 0 days | PP |  | 5.15 | Yes
4 | 1.9.7.7 |  |  |  |  | M16 Checkpoint 2 | 0% | 02/04/27 | 02/04/27 | 0 days | 02/04/27 | 02/04/27 | 1 day | 0 days | 0 days | PP |  | 5.15 | Yes
4 | 1.9.7.8 |  |  |  |  | Readiness assessment of participants' readiness to transition to new Settlement Timetable | 0% | 19/04/27 | 19/04/27 | 0 days | 19/04/27 | 19/04/27 | 1 day | 0 days | 0 days | CPT |  | 5.15 | Yes
4 | 1.9.7.9 | T2 | T2-EL-0100 | PSG/BSC PAB |  | Confirm M16 Date | 0% | 30/04/27 | 30/04/27 | 0 days | 30/04/27 | 30/04/27 | 1 day | 0 days | -1 day | CPT |  | 5.3 | Yes
4 | 1.9.7.10 |  |  |  |  | Raise fast track change to ISD (November publish) | 0% | 30/04/27 | 30/04/27 | 0 days | 30/04/27 | 30/04/27 | 1 day | 0 days | 0 days | PP |  | 5.15 | Yes
4 | 1.9.7.11 |  |  |  |  | M16 Approval Window | 0% | 25/06/27 | 17/12/27 | 125 days | 25/06/27 | 23/12/27 | 1 day | -4 days | 1 day | N/A |  | 5 | Yes
5 | 1.9.7.11.1 |  |  |  |  | Panel approval that M16 criteria met | 0% | 25/06/27 | 25/06/27 | 0 days | 25/06/27 | 25/06/27 | 1 day | 0 days | 0 days | Panel |  | 5 | Yes
5 | 1.9.7.11.2 | T1 | T1-EL-1000 | PSG |  | Cut over to new settlement timetable (M16) | 0% | 28/06/27 | 28/06/27 | 0 days | 02/07/27 | 02/07/27 | -3 days | -4 days | 0 days | CPT |  | 5 | Yes
5 | 1.9.7.11.3 |  |  |  |  | Maximum 6-month window for approval of M16 | 0% | 29/06/27 | 17/12/27 | 124 days | 05/07/27 | 23/12/27 | -4 days | -4 days | 0 days | CPT |  | 5 | Yes
5 | 1.9.7.11.4 | T1 | T1-EL-2000 | PSG |  | Cut over to new settlement timetable (M16*) - Late Exit | 0% | 17/12/27 | 17/12/27 | 0 days | 23/12/27 | 23/12/27 | -3 days | -4 days | 0 days | CPT |  | 5 | Yes
2 | 1.1 |  |  |  |  | EARLY LIVE RUNNING | 0% | 04/05/27 | 05/07/27 | 45 days | 10/05/27 | 09/07/27 | -4 days | -4 days | -844 days | N/A |  |  | Yes
3 | 1.10.1 |  |  |  |  | Early Live Running Stabilisation Period | 0% | 04/05/27 | 05/07/27 | 45 days | 10/05/27 | 09/07/27 | -4 days | -4 days | 0 days | N/A |  | 5 | Yes
4 | 1.10.1.1 |  |  |  |  | Manage Early Live Running stabilisation period | 0% | 04/05/27 | 05/07/27 | 45 days | 10/05/27 | 09/07/27 | -4 days | -4 days | 0 days | Code Bodies |  | 5 | Yes
4 | 1.10.1.2 |  |  |  |  | Monitor Early Live Running stabilisation period | 0% | 04/05/27 | 05/07/27 | 45 days | 10/05/27 | 09/07/27 | -4 days | -4 days | 0 days | SI Migration |  | 5 | Yes
2 | 1.11 |  |  |  |  | PROGRAMME CLOSURE | 0% | 02/03/27 | 21/06/27 | 80 days | 08/03/27 | 25/06/27 | -4 days | -4 days | -5 days | N/A |  |  | Yes
3 | 1.11.1 |  |  |  |  | Handover Pack | 0% | 02/03/27 | 21/06/27 | 80 days | 08/03/27 | 25/06/27 | -4 days | -4 days | -5 days | N/A |  | 5 | Yes
4 | 1.11.1.1 |  |  |  |  | Draft Handover Pack (for M15) | 0% | 02/03/27 | 26/04/27 | 40 days | 08/03/27 | 30/04/27 | -4 days | -4 days | 0 days | N/A |  | 5 | Yes
5 | 1.11.1.1.1 |  |  |  |  | Develop document | 0% | 02/03/27 | 29/03/27 | 20 days | 08/03/27 | 02/04/27 | -4 days | -4 days | 0 days | PMO |  | 5 | Yes
5 | 1.11.1.1.2 |  |  |  |  | Document review and update | 0% | 30/03/27 | 26/04/27 | 20 days | 05/04/27 | 30/04/27 | -4 days | -4 days | 0 days | SRO |  | 5 | Yes
5 | 1.11.1.1.3 |  |  |  | MHHS-ART126 | Draft Handover Pack approved | 0% | 26/04/27 | 26/04/27 | 0 days | 30/04/27 | 30/04/27 | -3 days | -4 days | 0 days | SRO |  | 5 | Yes
4 | 1.11.1.2 |  |  |  |  | Master Handover Pack (for M16) | 0% | 27/04/27 | 21/06/27 | 40 days | 03/05/27 | 25/06/27 | -4 days | -4 days | 0 days | N/A |  | 5 | Yes
5 | 1.11.1.2.1 |  |  |  |  | Update document | 0% | 27/04/27 | 24/05/27 | 20 days | 03/05/27 | 28/05/27 | -4 days | -4 days | 0 days | PMO |  | 5 | Yes
5 | 1.11.1.2.2 |  |  |  |  | Document review and update | 0% | 25/05/27 | 21/06/27 | 20 days | 31/05/27 | 25/06/27 | -4 days | -4 days | 0 days | SRO |  | 5 | Yes
5 | 1.11.1.2.3 |  |  |  | MHHS-ART126 | Master Handover Pack approved | 0% | 21/06/27 | 21/06/27 | 0 days | 25/06/27 | 25/06/27 | -3 days | -4 days | 0 days | SRO |  | 5 | Yes
3 | 1.11.2 |  |  |  |  | Programme Lessons Learned | 0% | 02/03/27 | 26/04/27 | 40 days | 08/03/27 | 30/04/27 | -4 days | -4 days | 0 days | N/A |  | 5 | Yes
4 | 1.11.2.1 |  |  |  |  | Develop document | 0% | 02/03/27 | 29/03/27 | 20 days | 08/03/27 | 02/04/27 | -4 days | -4 days | 0 days | PMO |  | 5 | Yes
4 | 1.11.2.2 |  |  |  |  | Document review and update | 0% | 30/03/27 | 26/04/27 | 20 days | 05/04/27 | 30/04/27 | -4 days | -4 days | 0 days | SRO |  | 5 | Yes
4 | 1.11.2.3 |  |  |  | MHHS-ART131 | Programme Lessons Learned document approved | 0% | 26/04/27 | 26/04/27 | 0 days | 30/04/27 | 30/04/27 | -3 days | -4 days | 0 days | SRO |  | 5 | Yes
3 | 1.11.3 |  |  |  |  | Programme Closure Report | 0% | 02/03/27 | 26/04/27 | 40 days | 08/03/27 | 30/04/27 | -4 days | -4 days | 0 days | N/A |  | 5 | Yes
4 | 1.11.3.1 |  |  |  |  | Develop document | 0% | 02/03/27 | 29/03/27 | 20 days | 08/03/27 | 02/04/27 | -4 days | -4 days | 0 days | PMO |  | 5 | Yes
4 | 1.11.3.2 |  |  |  |  | Document review and update | 0% | 30/03/27 | 26/04/27 | 20 days | 05/04/27 | 30/04/27 | -4 days | -4 days | 0 days | Ofgem |  | 5 | Yes
4 | 1.11.3.3 |  |  |  | MHHS-ART130 | Programme Closure Report approved | 0% | 26/04/27 | 26/04/27 | 0 days | 30/04/27 | 30/04/27 | -3 days | -4 days | 0 days | Ofgem |  | 5 | Yes
3 | 1.11.4 |  |  |  |  | Benefit Realisation Report | 0% | 02/03/27 | 03/05/27 | 45 days | 08/03/27 | 07/05/27 | -4 days | -4 days | 0 days | N/A |  | 5 | Yes
4 | 1.11.4.1 |  |  |  |  | Develop document | 0% | 02/03/27 | 29/03/27 | 20 days | 08/03/27 | 02/04/27 | -4 days | -4 days | 0 days | PMO |  | 5 | Yes
4 | 1.11.4.2 |  |  |  |  | Document review and update | 0% | 30/03/27 | 26/04/27 | 20 days | 05/04/27 | 30/04/27 | -4 days | -4 days | 0 days | PP |  | 5 | Yes
4 | 1.11.4.3 | T3 | T3-PC-0010 | PSG | MHHS-ART124 | Benefit Realisation Report approved | 0% | 03/05/27 | 03/05/27 | 0 days | 07/05/27 | 07/05/27 | -3 days | -4 days | 0 days | PMO |  | 5 | Yes
3 | 1.11.5 |  |  |  |  | Operating Model Gap Review with recommendations | 0% | 02/03/27 | 03/05/27 | 45 days | 08/03/27 | 07/05/27 | -4 days | -4 days | 0 days | N/A |  | 5 | Yes
4 | 1.11.5.1 |  |  |  |  | Develop document | 0% | 02/03/27 | 29/03/27 | 20 days | 08/03/27 | 02/04/27 | -4 days | -4 days | 0 days | PMO |  | 5 | Yes
4 | 1.11.5.2 |  |  |  |  | Document review and update | 0% | 30/03/27 | 26/04/27 | 20 days | 05/04/27 | 30/04/27 | -4 days | -4 days | 0 days | PP |  | 5 | Yes
4 | 1.11.5.3 | T3 | T3-PC-0020 | DAG | MHHS-ART128 | Operating Model Gap Review with recommendations approved | 0% | 03/05/27 | 03/05/27 | 0 days | 07/05/27 | 07/05/27 | -3 days | -4 days | 0 days | Paul Pettitt |  | 5 | Yes
3 | 1.11.6 |  |  |  |  | Post-Implementation Review | 0% | 02/03/27 | 03/05/27 | 45 days | 08/03/27 | 07/05/27 | -4 days | -4 days | 0 days | N/A |  | 5 | Yes
4 | 1.11.6.1 |  |  |  |  | Develop document | 0% | 02/03/27 | 29/03/27 | 20 days | 08/03/27 | 02/04/27 | -4 days | -4 days | 0 days | PMO |  | 5 | Yes
4 | 1.11.6.2 |  |  |  |  | Document review and update | 0% | 30/03/27 | 26/04/27 | 20 days | 05/04/27 | 30/04/27 | -4 days | -4 days | 0 days | PP |  | 5 | Yes
4 | 1.11.6.3 | T3 | T3-PC-0030 | PSG | MHHS-ART129 | Post-Implementation Review approved | 0% | 03/05/27 | 03/05/27 | 0 days | 07/05/27 | 07/05/27 | -3 days | -4 days | 0 days | PMO |  | 5 | Yes
3 | 1.11.7 |  |  |  |  | Reinforcement Guide | 0% | 02/03/27 | 03/05/27 | 45 days | 08/03/27 | 07/05/27 | -4 days | -4 days | 0 days | N/A |  | 5 | Yes
4 | 1.11.7.1 |  |  |  |  | Develop document | 0% | 02/03/27 | 29/03/27 | 20 days | 08/03/27 | 02/04/27 | -4 days | -4 days | 0 days | PMO |  | 5 | Yes
4 | 1.11.7.2 |  |  |  |  | Document review and update | 0% | 30/03/27 | 26/04/27 | 20 days | 05/04/27 | 30/04/27 | -4 days | -4 days | 0 days | PP |  | 5 | Yes
4 | 1.11.7.3 | T3 | T3-PC-0040 | PSG | MHHS-ART133 | Reinforcement Guide approved | 0% | 03/05/27 | 03/05/27 | 0 days | 07/05/27 | 07/05/27 | -3 days | -4 days | 0 days | PMO |  | 5 | Yes
3 | 1.11.8 |  |  |  |  | Material and Licenses Transfer | 0% | 30/03/27 | 21/06/27 | 60 days | 05/04/27 | 25/06/27 | -4 days | -4 days | 0 days | N/A |  | 5 | Yes
4 | 1.11.8.1 |  |  |  | MHHS-ART139 | Transfer of Programme material to Elexon and perpetual licenses as appropriate | 0% | 30/03/27 | 21/06/27 | 60 days | 05/04/27 | 25/06/27 | -4 days | -4 days | 0 days | PMO |  | 5 | Yes
2 | 1.12 |  |  |  |  | READINESS ASSESSMENTS | 23% | 05/09/23 | 11/06/27 | 984 days | 05/09/23 | 17/06/27 | 0 days | -4 days | 135 days | N/A |  |  | Yes
3 | 1.12.1 |  |  |  |  | Readiness Assessment 3 - Design and Build Progress Check and CP2 Check | 100% | 05/09/23 | 27/11/23 | 60 days | 05/09/23 | 27/11/23 | 0 days | 0 days | 10 days | N/A |  | 5.5 | Yes
4 | 1.12.1.1 |  |  |  |  | Launch Readiness Assessment survey | 100% | 05/09/23 | 05/09/23 | 0 days | 05/09/23 | 05/09/23 | 0 days | -1 day | 0 days | PPC |  | 5.5 | Yes
4 | 1.12.1.2 |  |  |  |  | PPs submit survey responses | 100% | 05/09/23 | 25/09/23 | 15 days | 05/09/23 | 25/09/23 | 0 days | 0 days | 0 days | PP |  | 5.5 | Yes
4 | 1.12.1.3 |  |  |  |  | Analyse survey responses | 100% | 26/09/23 | 16/10/23 | 15 days | 26/09/23 | 16/10/23 | 0 days | 0 days | 0 days | PPC |  | 5.5 | Yes
4 | 1.12.1.4 |  |  |  |  | Conduct deep-dive interviews (sample of PPs) | 100% | 26/09/23 | 16/10/23 | 15 days | 26/09/23 | 16/10/23 | 0 days | 0 days | 0 days | PPC |  | 5.5 | Yes |  | 16/11- FD confirmed activity didn't take place for RA3 because responses did not warrant follow-up
4 | 1.12.1.5 |  |  |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 100% | 17/10/23 | 20/11/23 | 25 days | 17/10/23 | 20/11/23 | 0 days | 0 days | 10 days | PPC |  | 5.5 | Yes
4 | 1.12.1.6 | T2 | T2-RA-0200 | PSG |  | Readiness Assessment 3 - Design & Build Checkpoint 1 - Completed (incl. Readiness Assessment Report approval) | 100% | 27/11/23 | 27/11/23 | 0 days | 27/11/23 | 27/11/23 | 1 day | 0 days | 0 days | CPT |  | 5.13 | Yes |  | 16/11-RA3 outputs and initial findings shared with PSG to support M9 decision making. Individual reports and final closure report being finalised. No impact to Programme timelines or activities
3 | 1.12.2 |  |  |  |  | Readiness Assessment 5 / 6 - Start of Qualification and Participant Readiness for M10 and M11 and CP3/CP4 check | 0% | 21/04/25 | 24/06/25 | 47 days | 21/04/25 | 24/06/25 | 0 days | 0 days | -2 days | N/A |  | 5 | Yes
4 | 1.12.2.1 |  |  |  |  | Launch Readiness Assessment survey | 0% | 21/04/25 | 21/04/25 | 0 days | 21/04/25 | 21/04/25 | 0 days | -1 day | 0 days | PPC |  | 5 | Yes
4 | 1.12.2.2 |  |  |  |  | PPs submit survey responses | 0% | 21/04/25 | 09/05/25 | 15 days | 21/04/25 | 09/05/25 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.12.2.3 |  |  |  |  | Analyse survey responses | 0% | 12/05/25 | 30/05/25 | 15 days | 12/05/25 | 30/05/25 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.2.4 |  |  |  |  | Conduct deep-dive interviews (sample of PPs) | 0% | 12/05/25 | 30/05/25 | 15 days | 12/05/25 | 30/05/25 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.2.5 |  |  |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 0% | 02/06/25 | 20/06/25 | 15 days | 02/06/25 | 20/06/25 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.2.6 | T2 | T2-RA-0400 | PSG |  | Readiness Assessment 5 / 6 - Start of Qualification and Participant Readiness for M10 and M11 and CP3/CP4 check (incl. Readiness Assessment Report approval) Completed | 0% | 24/06/25 | 24/06/25 | 0 days | 24/06/25 | 24/06/25 | 1 day | 0 days | 0 days | CPT |  | 5.18 | Yes |  | 08/02/2024 Name change approval at PSG on 07/02/24 from Readiness Assessment 5 - Start of Qualification - Completed (incl. Readiness Assessment Report approval)
3 | 1.12.3 |  |  |  |  | Readiness Assessment 7 - Migration Checkpoint | 0% | 12/01/26 | 19/03/26 | 49 days | 12/01/26 | 19/03/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.12.3.1 |  |  |  |  | Launch Readiness Assessment survey | 0% | 12/01/26 | 12/01/26 | 0 days | 12/01/26 | 12/01/26 | 0 days | -1 day | 0 days | PPC |  | 5 | Yes
4 | 1.12.3.2 |  |  |  |  | PPs submit survey responses | 0% | 12/01/26 | 30/01/26 | 15 days | 12/01/26 | 30/01/26 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.12.3.3 |  |  |  |  | Analyse survey responses | 0% | 02/02/26 | 20/02/26 | 15 days | 02/02/26 | 20/02/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.3.4 |  |  |  |  | Conduct deep-dive interviews (sample of PPs) | 0% | 02/02/26 | 20/02/26 | 15 days | 02/02/26 | 20/02/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.3.5 |  |  |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 0% | 23/02/26 | 13/03/26 | 15 days | 23/02/26 | 13/03/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.3.6 | T2 | T2-RA-0600 | PSG |  | Readiness Assessment 7 - Migration Checkpoint - Completed (incl. Readiness Assessment Report approval) | 0% | 19/03/26 | 19/03/26 | 0 days | 19/03/26 | 19/03/26 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
3 | 1.12.4 |  |  |  |  | Readiness Assessment 8 - Ready to Accept New MPANs | 0% | 06/08/26 | 13/10/26 | 49 days | 06/08/26 | 13/10/26 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.12.4.1 |  |  |  |  | Launch Readiness Assessment survey | 0% | 06/08/26 | 06/08/26 | 0 days | 06/08/26 | 06/08/26 | 0 days | -1 day | 0 days | PPC |  | 5 | Yes
4 | 1.12.4.2 |  |  |  |  | PPs submit survey responses | 0% | 06/08/26 | 26/08/26 | 15 days | 06/08/26 | 26/08/26 | 0 days | 0 days | 0 days | PP |  | 5 | Yes
4 | 1.12.4.3 |  |  |  |  | Analyse survey responses | 0% | 27/08/26 | 16/09/26 | 15 days | 27/08/26 | 16/09/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.4.4 |  |  |  |  | Conduct deep-dive interviews (sample of PPs) | 0% | 27/08/26 | 16/09/26 | 15 days | 27/08/26 | 16/09/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.4.5 |  |  |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 0% | 17/09/26 | 07/10/26 | 15 days | 17/09/26 | 07/10/26 | 0 days | 0 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.4.6 | T2 | T2-RA-0700 | PSG |  | Readiness Assessment 8 - Ready to Accept New MPANs - Completed (incl. Readiness Assessment Report approval) | 0% | 13/10/26 | 13/10/26 | 0 days | 13/10/26 | 13/10/26 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
3 | 1.12.5 |  |  |  |  | Readiness Assessment 9 - Ready for New Settlement Timetable and CP5 Check | 0% | 06/04/27 | 11/06/27 | 49 days | 12/04/27 | 17/06/27 | -4 days | -4 days | 0 days | N/A |  | 5 | Yes
4 | 1.12.5.1 |  |  |  |  | Launch Readiness Assessment survey | 0% | 06/04/27 | 06/04/27 | 0 days | 12/04/27 | 12/04/27 | -4 days | -5 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.5.2 |  |  |  |  | PPs submit survey responses | 0% | 06/04/27 | 26/04/27 | 15 days | 12/04/27 | 30/04/27 | -4 days | -4 days | 0 days | PP |  | 5 | Yes
4 | 1.12.5.3 |  |  |  |  | Analyse survey responses | 0% | 27/04/27 | 17/05/27 | 15 days | 03/05/27 | 21/05/27 | -4 days | -4 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.5.4 |  |  |  |  | Conduct deep-dive interviews (sample of PPs) | 0% | 27/04/27 | 17/05/27 | 15 days | 03/05/27 | 21/05/27 | -4 days | -4 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.5.5 |  |  |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 0% | 18/05/27 | 07/06/27 | 15 days | 24/05/27 | 11/06/27 | -4 days | -4 days | 0 days | PPC |  | 5 | Yes
4 | 1.12.5.6 | T2 | T2-RA-0800 | PSG |  | Readiness Assessment 9 - Readiness for New Settlement Timetable - Completed (incl. Readiness Assessment Report approval) | 0% | 11/06/27 | 11/06/27 | 0 days | 17/06/27 | 17/06/27 | -3 days | -4 days | 0 days | CPT |  | 5 | Yes
3 | 1.12.6 |  |  |  |  | Readiness Assessments - Tier 1 Milestones | 0% | 24/06/25 | 11/06/27 | 513 days | 24/06/25 | 17/06/27 | 1 day | -4 days | -286 days | N/A |  | 5 | Yes
4 | 1.12.6.1 | T2 | T2-RA-0500 | PSG |  | Readiness Assessment 6 - Start of Migration - Completed (incl. Readiness Assessment Report approval) | 0% | 24/06/25 | 24/06/25 | 0 days | 24/06/25 | 24/06/25 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.12.6.2 | T2 | T2-RA-0600 | PSG |  | Readiness Assessment 7 - Migration Checkpoint - Completed (incl. Readiness Assessment Report approval) | 0% | 19/03/26 | 19/03/26 | 0 days | 19/03/26 | 19/03/26 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.12.6.3 | T2 | T2-RA-0700 | PSG |  | Readiness Assessment 8 - Ready to Accept New MPANs - Completed (incl. Readiness Assessment Report approval) | 0% | 13/10/26 | 13/10/26 | 0 days | 13/10/26 | 13/10/26 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.12.6.4 | T2 | T2-RA-0800 | PSG |  | Readiness Assessment 9 - Readiness for New Settlement Timetable - Completed (incl. Readiness Assessment Report approval) | 0% | 11/06/27 | 11/06/27 | 0 days | 17/06/27 | 17/06/27 | -3 days | -4 days | 0 days | CPT |  | 5 | Yes
2 | 1.13 |  |  |  |  | CONTROL POINTS | 51% | 10/11/22 | 17/06/27 | 1200 days | 10/11/22 | 23/06/27 | 0 days | -5 days | 137 days | N/A |  |  | Yes
3 | 1.13.1 |  |  |  |  | Control Point 1 - Start of System Design, Build & Test | 100% | 10/11/22 | 07/12/22 | 20 days | 10/11/22 | 07/12/22 | 0 days | 0 days | 0 days | N/A |  | 5 | Yes
4 | 1.13.1.1 |  |  |  |  | Control Point 1 Preparation (incl. Control Point Report development and review) | 100% | 10/11/22 | 30/11/22 | 15 days | 10/11/22 | 30/11/22 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.13.1.2 | T1 | T1-CP-1000 | PSG |  | Control Point 1 - Start of System Design, Build & Test (incl. Control Point Report approval) | 100% | 07/12/22 | 07/12/22 | 0 days | 07/12/22 | 07/12/22 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
3 | 1.13.2 |  |  |  |  | Control Point 2 - Start of Integration & Test | 100% | 02/10/23 | 30/10/23 | 20 days | 02/10/23 | 30/10/23 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
4 | 1.13.2.1 |  |  |  |  | Control Point 2 Preparation (incl. Control Point Report development and review) | 100% | 02/10/23 | 20/10/23 | 15 days | 02/10/23 | 20/10/23 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.13.2.2 | T1 | T1-CP-2000 | PSG |  | Control Point 2 - Start of Integration & Test (incl. Control Point Report approval) | 100% | 30/10/23 | 30/10/23 | 0 days | 30/10/23 | 30/10/23 | 0 days | -1 day | 0 days | CPT |  | 5.11 | Yes
3 | 1.13.3 |  |  |  |  | Control Point 3/4 - Readiness for Migration | 0% | 21/08/25 | 18/09/25 | 20 days | 21/08/25 | 18/09/25 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
4 | 1.13.3.1 |  |  |  |  | Control Point 3/4 Preparation (incl. Control Point Report development and review) | 0% | 21/08/25 | 09/09/25 | 14 days | 21/08/25 | 09/09/25 | 0 days | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.13.3.2 | T1 | T1-CP-3000 | PSG |  | Control Point 3/4 - Readiness for Migration (incl. Control Point Report approval) | 0% | 18/09/25 | 18/09/25 | 0 days | 18/09/25 | 18/09/25 | 0 days | -1 day | 0 days | CPT |  | 5 | Yes
3 | 1.13.4 |  |  |  |  | Control Point 5 - Cut Over to New Settlement Timetable | 0% | 20/05/27 | 17/06/27 | 20 days | 26/05/27 | 23/06/27 | -4 days | -5 days | 0 days | N/A |  | 5 | Yes
4 | 1.13.4.1 |  |  |  |  | Control Point 5 Preparation (incl. Control Point Report development and review) | 0% | 20/05/27 | 09/06/27 | 15 days | 26/05/27 | 15/06/27 | -4 days | -4 days | 0 days | CPT |  | 5 | Yes
4 | 1.13.4.2 | T1 | T1-CP-4000 | PSG |  | Control Point 5 - Cut Over to New Settlement Timetable (incl. Control Point Report approval) | 0% | 17/06/27 | 17/06/27 | 0 days | 23/06/27 | 23/06/27 | -4 days | -5 days | 0 days | CPT |  | 5 | Yes
3 | 1.13.5 |  |  |  |  | Control Points - Tier 1 Milestones | 0% | 07/12/22 | 17/06/27 | 1180 days | 07/12/22 | 23/06/27 | 1 day | -5 days | 137 days | N/A |  | 5 | Yes
4 | 1.13.5.1 | T1 | T1-CP-1000 | PSG |  | Control Point 1 - Start of System Design, Build & Test (incl. Control Point Report approval) | 100% | 07/12/22 | 07/12/22 | 0 days | 07/12/22 | 07/12/22 | 1 day | 0 days | 0 days | CPT |  | 5 | Yes
4 | 1.13.5.2 | T1 | T1-CP-2000 | PSG |  | Control Point 2 - Start of Integration & Test (incl. Control Point Report approval) | 100% | 30/10/23 | 30/10/23 | 0 days | 30/10/23 | 30/10/23 | 0 days | -1 day | 0 days | CPT |  | 5.11 | Yes
4 | 1.13.5.3 | T1 | T1-CP-3000 | PSG |  | Control Point 3/4 - Readiness for Migration (incl. Control Point Report approval) | 0% | 18/09/25 | 18/09/25 | 0 days | 18/09/25 | 18/09/25 | 0 days | -1 day | 0 days | CPT |  | 5 | Yes
4 | 1.13.5.4 | T1 | T1-CP-4000 | PSG |  | Control Point 5 - Cut Over to New Settlement Timetable (incl. Control Point Report approval) | 0% | 17/06/27 | 17/06/27 | 0 days | 23/06/27 | 23/06/27 | -4 days | -5 days | 0 days | CPT |  | 5 | Yes
2 | 1.14 |  |  |  |  | MILESTONE RANGE CHECKPOINTS | 0% | 31/10/22 | 06/04/27 | 1156 days? | 31/10/22 | 12/04/27 | 0 days | -5 days | 720 days? | N/A |  |  | Yes
3 | 1.14.1 |  |  |  |  | M10, M11, M12 and M13 milestone checkpoint | 0% | 31/07/25 | 31/07/25 | 0 days | 31/07/25 | 31/07/25 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
4 | 1.14.1.1 | T2 | T2-MR-0100 | PSG |  | M10, M11, M12, and M13 milestone checkpoint - date approval | 0% | 31/07/25 | 31/07/25 | 0 days | 31/07/25 | 31/07/25 | 0 days | -1 day | 0 days | CPT |  | 5 | Yes
3 | 1.14.2 |  |  |  |  | M14 milestone checkpoint | 0% | 06/08/26 | 06/08/26 | 0 days | 06/08/26 | 06/08/26 | 0 days | -1 day | 0 days | N/A |  | 5 | Yes
4 | 1.14.2.1 | T2 | T2-MR-0200 | PSG |  | M14 milestone checkpoint - date approval | 0% | 06/08/26 | 06/08/26 | 0 days | 06/08/26 | 06/08/26 | 0 days | -1 day | 0 days | CPT |  | 5 | Yes
3 | 1.14.3 |  |  |  |  | M15 milestone checkpoint | 0% | 09/02/27 | 09/02/27 | 0 days | 15/02/27 | 15/02/27 | -4 days | -5 days | 0 days | N/A |  | 5 | Yes
4 | 1.14.3.1 | T2 | T2-MR-0300 | PSG |  | M15 milestone checkpoint - date approval | 0% | 09/02/27 | 09/02/27 | 0 days | 15/02/27 | 15/02/27 | -4 days | -5 days | 0 days | CPT |  | 5 | Yes
3 | 1.14.4 |  |  |  |  | M16 milestone checkpoint | 0% | 31/10/22 | 06/04/27 | 1156 days? | 31/10/22 | 12/04/27 | 0 days | -5 days | 1156 days? | N/A |  | 5 | Yes
4 | 1.14.4.1 | T2 | T2-MR-0400 | PSG |  | M16 milestone checkpoint - date approval | 0% | 06/04/27 | 06/04/27 | 0 days | 12/04/27 | 12/04/27 | -4 days | -5 days | 0 days | CPT |  | 5 | Yes
4 | 1.14.4.2 | [5 empty] | 0% | 31/10/22 | 31/10/22 | 1 day? | 31/10/22 | 31/10/22 | 0 days | 0 days | 1 day? |  |  |  | Yes