## Task_Table1
Outline Level | WBS | Milestone ID | Approving Governance Forum | Name | % Complete | Start Date | Finish Date | Duration | Baseline Start | Baseline Finish | Predecessors | Successors | Start Variance | Finish Variance | Duration Variance | Responsible | Involved | Milestone Change Status | Milestone Change | Update Version | Active | Resource Name | Notes
1 | 1 |  |  | Programme Plan | 39% | Mon 31/10/22 | Fri 28/05/27 | 1195 days | Mon 31/10/22 | Fri 28/05/27 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
2 | 1.1 |  |  | MHHS Programme Start | 100% | Mon 31/10/22 | Mon 31/10/22 | 0 days | Mon 31/10/22 | Mon 31/10/22 |  | 173 | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.7 | Yes | N/A
2 | 1.2 |  |  | PROGRAMME MANAGEMENT | 35% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
3 | 1.2.1 |  |  | Programme Management | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.2.1.1 |  |  | Sprint-based prioritisation planning and execution | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes | N/A
4 | 1.2.1.2 |  |  | Programme governance secretariat | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes | N/A
4 | 1.2.1.3 |  |  | RAID management and reporting | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes | N/A
4 | 1.2.1.4 |  |  | Tracking against Programme outcomes and KPIs | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes | N/A
4 | 1.2.1.5 |  |  | Change control and reporting | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes | N/A
4 | 1.2.1.6 |  |  | Ongoing identification of lessons learned relating to the PMO and implementation of improvements | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes | N/A
3 | 1.2.2 |  |  | Programme Internal Assurance Reviews | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.2.2.1 |  |  | Programme Internal Assurance Reviews | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | CPT | PMO |  |  | 5 | Yes | N/A
3 | 1.2.3 |  |  | Engagement with PPs | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.2.3.1 |  |  | Ongoing PP liaison activities | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PPC | CPT |  |  | 5 | Yes | N/A
4 | 1.2.3.2 |  |  | Milestone and Control Point objective setting | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PPC | CPT |  |  | 5 | Yes | N/A
4 | 1.2.3.3 |  |  | Reporting | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PPC |  |  |  | 5 | Yes | N/A
4 | 1.2.3.4 |  |  | PP Engagement Events | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.2.3.4.1 |  |  | Bilateral meetings | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PPC | CPT |  |  | 5 | Yes | N/A
5 | 1.2.3.4.2 |  |  | Monthly webinars | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PPC | CPT |  |  | 5 | Yes | N/A
5 | 1.2.3.4.3 |  |  | Open days | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | PPC | CPT |  |  | 5 | Yes | N/A
4 | 1.2.3.5 |  |  | PP Communications | 34% | Mon 31/10/22 | Wed 30/12/26 | 1088 days | Mon 31/10/22 | Wed 30/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.2.3.5.1 |  |  | The Clock updates (weekly) | 34% | Mon 31/10/22 | Wed 30/12/26 | 1088 days | Mon 31/10/22 | Wed 30/12/26 |  |  | 0 days | 0 days | 0 days | PPC |  |  |  | 5 | Yes | N/A
5 | 1.2.3.5.2 |  |  | Maintain and update content on public-facing Portal (and ongoing feedback reviews to identify and implement Portal improvements) | 34% | Mon 31/10/22 | Wed 30/12/26 | 1088 days | Mon 31/10/22 | Wed 30/12/26 |  |  | 0 days | 0 days | 0 days | PPC |  |  |  | 5 | Yes | N/A
3 | 1.2.4 |  |  | Code Change Support / Other Programme Alignment | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.2.4.1 |  |  | Support DCC/BEIS on SEC change | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | CPT |  |  |  | 5 | Yes | N/A
4 | 1.2.4.2 |  |  | Support on Smart Meters Act changes | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | CPT |  |  |  | 5 | Yes | N/A
4 | 1.2.4.3 |  |  | Support DCC/RECCo on CSS change | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | CPT |  |  |  | 5 | Yes | N/A
4 | 1.2.4.4 |  |  | Support Elexon on BSC change | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | CPT |  |  |  | 5 | Yes | N/A
4 | 1.2.4.5 |  |  | Support code change inside & outside CCIAG | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | CPT |  |  |  | 5 | Yes | N/A
4 | 1.2.4.6 |  |  | Support code change inside & outside CCAG | 34% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | CPT |  |  |  | 5 | Yes | N/A
3 | 1.2.5 |  |  | Programme Replan Baseline | 100% | Mon 31/10/22 | Wed 14/06/23 | 163 days | Mon 31/10/22 | Wed 14/06/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.2.5.1 |  |  | Round 3 consultation preparation | 100% | Mon 31/10/22 | Tue 13/12/22 | 32 days | Mon 31/10/22 | Tue 13/12/22 |  | 33FS-5 days | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes | N/A
4 | 1.2.5.2 |  |  | PSG decision to launch Round 3 consultation | 100% | Wed 07/12/22 | Wed 07/12/22 | 0 days | Wed 07/12/22 | Wed 07/12/22 | 32FS-5 days | 34FS+5 days | 0 days | 0 days | 0 days | PMO | PPC |  |  | 5 | Yes | N/A
4 | 1.2.5.3 |  |  | Round 3 consultation (incl. walkthroughs and Q&A) | 100% | Wed 14/12/22 | Tue 31/01/23 | 35 days | Wed 14/12/22 | Tue 31/01/23 | 33FS+5 days | 36,523FF,524,35SS | 0 days | 0 days | 0 days | PP | PMO, PPC,IPA |  |  | 5 | Yes | N/A
4 | 1.2.5.4 |  |  | Review and uplift of foundational testing documents to align with replan approach | 100% | Wed 14/12/22 | Thu 20/04/23 | 92 days | Wed 14/12/22 | Thu 20/04/23 | 34SS |  | 0 days | 0 days | 0 days | SI Test | CPT |  |  | 5 | Yes | N/A
4 | 1.2.5.5 |  |  | Round 3 consultation responses analysis (incl. identification of SIT volunteers) | 100% | Wed 01/02/23 | Tue 14/02/23 | 10 days | Wed 01/02/23 | Tue 14/02/23 | 34 | 37,38 | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes | N/A
4 | 1.2.5.6 |  |  | Replan re-drafting and supporting artefact updates (incl. engagement with Ofgem) | 100% | Wed 15/02/23 | Wed 22/03/23 | 26 days | Wed 15/02/23 | Wed 22/03/23 | 36 |  | 0 days | 0 days | 0 days | PMO | CPT,IPA,Ofgem |  |  | 5 | Yes | N/A
4 | 1.2.5.7 |  |  | Draft Replan Change Request | 100% | Wed 15/02/23 | Wed 29/03/23 | 31 days | Wed 15/02/23 | Wed 29/03/23 | 36 | 39FS+5 days | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes | N/A
4 | 1.2.5.8 |  |  | PSG decision to issue CR for industry impact assessment | 100% | Wed 05/04/23 | Wed 05/04/23 | 0 days | Wed 05/04/23 | Wed 05/04/23 | 38FS+5 days | 40 | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes | N/A
4 | 1.2.5.9 |  |  | Industry impact assessment | 100% | Thu 06/04/23 | Wed 19/04/23 | 10 days | Thu 06/04/23 | Wed 19/04/23 | 39 | 42,41SS+3 days | 0 days | 0 days | 0 days | PP | PMO,PPC |  |  | 5 | Yes | N/A
4 | 1.2.5.10 |  |  | Replan playbacks (to assist PPs in impact assessment) | 100% | Tue 11/04/23 | Mon 17/04/23 | 5 days | Tue 11/04/23 | Mon 17/04/23 | 40SS+3 days |  | 0 days | 0 days | 0 days | CPT | PPC,PP |  |  | 5 | Yes | N/A
4 | 1.2.5.11 |  |  | Industry impact assessment responses analysis | 100% | Thu 20/04/23 | Wed 26/04/23 | 5 days | Thu 20/04/23 | Wed 26/04/23 | 40 | 43FS+5 days | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes | N/A
4 | 1.2.5.12 |  |  | Extraordinary PSG decision to agree baseline recommendation | 100% | Wed 03/05/23 | Wed 03/05/23 | 0 days | Wed 03/05/23 | Wed 03/05/23 | 42FS+5 days | 44FS+25 days | 0 days | 0 days | 0 days | CPT | PMO,PP |  |  | 5 | Yes | N/A
4 | 1.2.5.13 | T1-PM-1000 | PSG | Plan Rebaselined (subject to Ofgem decision) | 100% | Thu 08/06/23 | Thu 08/06/23 | 0 days | Thu 08/06/23 | Thu 08/06/23 | 43FS+25 days | 45 | 0 days | -1 day | 0 days | CPT | PMO,PP |  |  | 5 | Yes | N/A
4 | 1.2.5.14 |  |  | Programme Replan playbacks and drop-in sessions | 100% | Thu 08/06/23 | Wed 14/06/23 | 5 days | Thu 08/06/23 | Wed 14/06/23 | 44 |  | 0 days | 0 days | 0 days | PMO | PPC, PP |  |  | 5 | Yes | N/A
2 | 1.3 |  |  | DESIGN, BUILD & TEST (PIT) | 75% | Mon 31/10/22 | Mon 18/01/27 | 1101 days | Mon 31/10/22 | Mon 18/01/27 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  |  | Yes | N/A
3 | 1.3.1 |  |  | Design Baseline & Enduring PP Support | 68% | Mon 31/10/22 | Mon 18/01/27 | 1101 days | Mon 31/10/22 | Mon 18/01/27 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.3.1.1 | T1-DB-1000 | PSG | Physical design baselined (M5) | 100% | Mon 31/10/22 | Mon 31/10/22 | 0 days | Mon 31/10/22 | Mon 31/10/22 |  | 53,161,162,168,431FS+10 days,477,76,164,165,166,1617,54,50 | 0 days | 0 days | 0 days | SRO Design | SI Design,PP,IPA |  |  | 5 | Yes | Paul Pettitt
4 | 1.3.1.2 |  |  | M5 Design Work-Off Plan Implementation & Approval | 100% | Mon 31/10/22 | Thu 16/02/23 | 79 days | Mon 31/10/22 | Thu 16/02/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.1.2.1 |  |  | Implementation of M5 design Work-Off Plan | 100% | Mon 31/10/22 | Thu 09/02/23 | 74 days | Mon 31/10/22 | Thu 09/02/23 | 48 | 51FS+5 days | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.1.2.2 | T3-DB-0014 | DAG | M5 design Work-Off Plan completion approved | 100% | Thu 16/02/23 | Thu 16/02/23 | 0 days | Thu 16/02/23 | Thu 16/02/23 | 50FS+5 days | 56,61FF | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
4 | 1.3.1.3 |  |  | Enduring PP Design Support | 100% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.1.3.1 |  |  | Design playbacks and drop-in sessions | 100% | Mon 31/10/22 | Fri 30/12/22 | 45 days | Mon 31/10/22 | Fri 30/12/22 | 48 |  | 0 days | 0 days | 0 days | SI Design | PMO,PPC, SRO Design |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.1.3.2 |  |  | Support participants on E2E MHHS Design | 100% | Mon 31/10/22 | Thu 31/12/26 | 1089 days | Mon 31/10/22 | Thu 31/12/26 | 48 |  | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.1.3.3 |  |  | DIP Onboarding Support | 100% | Mon 14/11/22 | Fri 17/02/23 | 70 days | Mon 14/11/22 | Fri 17/02/23 |  |  | 0 days | 0 days | 0 days | SI Design | SRO Design |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.1.3.4 |  |  | iServer Launch | 100% | Thu 16/02/23 | Thu 16/02/23 | 0 days | Thu 16/02/23 | Thu 16/02/23 | 51 |  | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
4 | 1.3.1.4 |  |  | Establish Design Change Management Processes | 30% | Mon 31/10/22 | Mon 18/01/27 | 1101 days | Mon 31/10/22 | Mon 18/01/27 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.1.4.1 |  |  | Internal review of internal change management processes | 100% | Mon 31/10/22 | Fri 16/12/22 | 35 days | Mon 31/10/22 | Fri 16/12/22 |  | 59FF | 0 days | 0 days | 0 days | SRO | SI Design |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.1.4.2 |  |  | SRO approval of internal change management processes | 100% | Fri 16/12/22 | Fri 16/12/22 | 0 days | Fri 16/12/22 | Fri 16/12/22 | 58FF |  | 0 days | 0 days | 0 days | SRO | SI Design |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.1.4.3 |  |  | Change Process Webinar | 100% | Mon 16/01/23 | Mon 16/01/23 | 0 days | Mon 16/01/23 | Mon 16/01/23 |  |  | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.1.4.4 | T3-DB-0016 | DAG | Enduring change management process approved | 100% | Thu 16/02/23 | Thu 16/02/23 | 0 days | Thu 16/02/23 | Thu 16/02/23 | 51FF | 62 | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.1.4.5 |  |  | Maintain E2E MHHS Design (post-M5 design change management processes operational) | 28% | Fri 17/02/23 | Mon 18/01/27 | 1022 days | Fri 17/02/23 | Mon 18/01/27 | 61 |  | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
4 | 1.3.1.5 |  |  | Design Authority Mobilisation | 100% | Wed 14/12/22 | Mon 23/01/23 | 29 days | Wed 14/12/22 | Mon 23/01/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.1.5.1 | T3-DB-0010 | DAG | Design Authority ToR approved | 100% | Wed 14/12/22 | Wed 14/12/22 | 0 days | Wed 14/12/22 | Wed 14/12/22 |  | 65FS+29 days | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.1.5.2 |  |  | Inaugural Design Authority | 100% | Mon 23/01/23 | Mon 23/01/23 | 0 days | Mon 23/01/23 | Mon 23/01/23 | 64FS+29 days |  | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
4 | 1.3.1.6 |  |  | Network Operation Services Adaptor Procurement | 100% | Tue 23/05/23 | Tue 23/05/23 | 0 days | Thu 02/02/23 | Mon 17/03/25 |  |  | 79 days | -474 days | -553 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.1.6.1 | T3-DB-0020 | DAG | All SIT LDSOs have procured their adapter providers | 100% | Tue 23/05/23 | Tue 23/05/23 | 0 days | Tue 23/05/23 | Tue 23/05/23 | 527SS |  | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
3 | 1.3.2 |  |  | PP Mobilisation | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.3.2.1 |  |  | Set up governance | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | PP
4 | 1.3.2.2 |  |  | Set up reporting | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | PP
4 | 1.3.2.3 |  |  | Obtain funding | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | PP
4 | 1.3.2.4 |  |  | Earmark resources | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | PP
4 | 1.3.2.5 |  |  | Mobilise initial team | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | PP
3 | 1.3.3 |  |  | PIT Stub Specification and Delivery | 90% | Mon 31/10/22 | Fri 21/06/24 | 430 days | Mon 31/10/22 | Fri 21/06/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.3.3.1 |  |  | DIP Simulator | 100% | Mon 31/10/22 | Wed 29/03/23 | 108 days | Mon 31/10/22 | Wed 29/03/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.3.1.1 |  |  | Build & Test | 100% | Mon 31/10/22 | Fri 10/03/23 | 95 days | Mon 31/10/22 | Fri 10/03/23 | 48 | 77SS+10 days,78SS | 0 days | 0 days | 0 days | SI DevOps |  |  |  | 5 | Yes | Rebecca Farooq
5 | 1.3.3.1.2 |  |  | UAT | 100% | Mon 14/11/22 | Fri 10/03/23 | 85 days | Mon 14/11/22 | Fri 10/03/23 | 76SS+10 days |  | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Rebecca Farooq
5 | 1.3.3.1.3 |  |  | Beta test | 100% | Mon 31/10/22 | Fri 10/03/23 | 95 days | Mon 31/10/22 | Fri 10/03/23 | 76SS | 79FS-5 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Rebecca Farooq
5 | 1.3.3.1.4 |  |  | Prepare for release | 100% | Mon 06/03/23 | Wed 29/03/23 | 18 days | Mon 06/03/23 | Wed 29/03/23 | 78FS-5 days | 80FF | 0 days | 0 days | 0 days | SI DevOps |  |  |  | 5 | Yes | Rebecca Farooq
5 | 1.3.3.1.5 | T3-DB-0018 | SITAG | DIP Simulator released | 100% | Wed 29/03/23 | Wed 29/03/23 | 0 days | Wed 29/03/23 | Wed 29/03/23 | 79FF | 668700732764 | 0 days | 0 days | 0 days | SI DevOps |  |  |  | 5 | Yes | Rebecca Farooq
4 | 1.3.3.2 |  |  | DIP Simulator Uplifts | 60% | Thu 06/07/23 | Fri 21/06/24 | 252 days | Thu 06/07/23 | Fri 21/06/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.1 | Yes | N/A
5 | 1.3.3.2.1 |  |  | DIP Simulator uplifted to align with design releases - design/build/test | 100% | Thu 06/07/23 | Fri 11/08/23 | 27 days | Thu 06/07/23 | Fri 11/08/23 | 118 | 83 | 0 days | 0 days | 0 days | SI DevOps |  |  |  | 5.1 | Yes | Rebecca Farooq
5 | 1.3.3.2.2 | T3-DB-0035 | SITAG | DIP Simulator uplifted to align with Interim Release 2 | 100% | Fri 11/08/23 | Fri 11/08/23 | 0 days | Fri 11/08/23 | Fri 11/08/23 | 82 |  | 0 days | 0 days | 0 days | SI DevOps |  |  |  | 5.1 | Yes | Rebecca Farooq
5 | 1.3.3.2.3 |  |  | DIP Simulator uplifted to align with design releases - design/build/test | 100% | Mon 09/10/23 | Fri 03/11/23 | 20 days | Mon 09/10/23 | Fri 03/11/23 | 127FS+2 days | 85 | 0 days | 0 days | 0 days | SI DevOps |  |  |  | 5.3 | Yes | Rebecca Farooq
5 | 1.3.3.2.4 | T3-DB-0039 | SITAG | DIP Simulator uplifted to align with Interim Release 5 | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 84 |  | 0 days | 0 days | 0 days | SI DevOps |  |  |  | 5.11 | Yes | Rebecca Farooq
5 | 1.3.3.2.5 |  |  | DIP Simulator uplifted to align with design releases - design/build/test | 100% | Thu 01/02/24 | Fri 22/03/24 | 37 days | Thu 01/02/24 | Fri 22/03/24 | 135 | 87 | 0 days | 0 days | 0 days | SI DevOps | PP,SRO,Testing |  |  | 5.14 | Yes | Matthew Bray
5 | 1.3.3.2.6 | T3-DB-0182 | SITAG | DIP Simulator uplifted to align with Interim Release 7 | 100% | Fri 22/03/24 | Fri 22/03/24 | 0 days | Fri 22/03/24 | Fri 22/03/24 | 86 |  | 0 days | 0 days | 0 days | SI DevOps | PP,SRO,Testing |  |  | 5.14 | Yes | Matthew Bray
5 | 1.3.3.2.7 |  |  | DIP Simulator uplifted to align with design releases - design/build/test | 0% | Thu 04/04/24 | Fri 21/06/24 | 57 days | Thu 04/04/24 | Fri 21/06/24 | 139 | 89 | 0 days | 0 days | 0 days | SI DevOps | PP,SRO,Testing |  |  | 5.14 | Yes | Matthew Bray
5 | 1.3.3.2.8 | T3-DB-0183 | SITAG | DIP Simulator uplifted to align with Interim Release 8 | 0% | Fri 21/06/24 | Fri 21/06/24 | 0 days | Fri 21/06/24 | Fri 21/06/24 | 88 |  | 0 days | 0 days | 0 days | SI DevOps | PP,SRO,Testing |  |  | 5.14 | Yes | Matthew Bray
4 | 1.3.3.3 |  |  | Data Generator | 100% | Thu 01/12/22 | Wed 31/05/23 | 130 days | Thu 01/12/22 | Wed 31/05/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.3.3.1 |  |  | Design | 100% | Thu 01/12/22 | Wed 21/12/22 | 15 days | Thu 01/12/22 | Wed 21/12/22 |  | 92FS+40 days | 0 days | 0 days | 0 days | SI DevOps |  |  |  | 5 | Yes | Rebecca Farooq
5 | 1.3.3.3.2 |  |  | Build & Test | 100% | Thu 16/02/23 | Wed 26/04/23 | 50 days | Thu 16/02/23 | Wed 26/04/23 | 91FS+40 days | 93,94FS-20 days | 0 days | 0 days | 0 days | SI DevOps |  |  |  | 5 | Yes | Rebecca Farooq
5 | 1.3.3.3.3 |  |  | UAT | 100% | Thu 27/04/23 | Wed 10/05/23 | 10 days | Thu 27/04/23 | Wed 10/05/23 | 92 | 95SS | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Rebecca Farooq
5 | 1.3.3.3.4 |  |  | Beta test | 100% | Thu 30/03/23 | Wed 31/05/23 | 45 days | Thu 30/03/23 | Wed 31/05/23 | 92FS-20 days,96FF |  | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Rebecca Farooq
5 | 1.3.3.3.5 |  |  | Prepare for release | 100% | Thu 27/04/23 | Tue 30/05/23 | 24 days | Thu 27/04/23 | Tue 30/05/23 | 93SS | 96FS+1 day | 0 days | 0 days | 0 days | SI DevOps |  |  |  | 5 | Yes | Rebecca Farooq
5 | 1.3.3.3.6 | T3-DB-0022 | SITAG | Data Generator released | 100% | Wed 31/05/23 | Wed 31/05/23 | 0 days | Wed 31/05/23 | Wed 31/05/23 | 95FS+1 day | 94FF,668,700,732,764 | 0 days | 0 days | 0 days | SI DevOps |  |  |  | 5 | Yes | Rebecca Farooq
3 | 1.3.4 |  |  | Design Artefact Releases | 92% | Wed 22/02/23 | Fri 30/08/24 | 398 days | Wed 22/02/23 | Fri 30/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.3.4.1 |  |  | Interim release 1 | 100% | Wed 22/02/23 | Mon 12/06/23 | 79 days | Wed 22/02/23 | Mon 12/06/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.4.1.1 |  |  | Prioritise DINs and CR | 100% | Wed 22/02/23 | Wed 22/02/23 | 1 day | Wed 22/02/23 | Wed 22/02/23 |  | 101 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.4.1.2 |  |  | Industry input session | 100% | Thu 23/02/23 | Fri 03/03/23 | 7 days | Thu 23/02/23 | Fri 03/03/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.4.1.2.1 |  |  | Raise a CR covering prioritized assessment cluster | 100% | Thu 23/02/23 | Thu 23/02/23 | 1 day | Thu 23/02/23 | Thu 23/02/23 | 99 | 102SS | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.4.1.2.2 |  |  | Organize Industry Input session to go through significant items to reach consensus | 100% | Thu 23/02/23 | Thu 23/02/23 | 1 day | Thu 23/02/23 | Thu 23/02/23 | 101SS | 103FS+5 days | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt,Berlinda Kugara
6 | 1.3.4.1.2.3 |  |  | Conduct Meeting | 100% | Fri 03/03/23 | Fri 03/03/23 | 1 day | Fri 03/03/23 | Fri 03/03/23 | 102FS+5 days |  | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt,Berlinda Kugara
5 | 1.3.4.1.3 |  |  | Update baselined artefacts | 100% | Fri 24/03/23 | Thu 06/04/23 | 10 days | Fri 24/03/23 | Thu 06/04/23 |  | 106FS+5 days | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.4.1.4 |  |  | Participant review and impact assess changes | 100% | Fri 14/04/23 | Tue 09/05/23 | 18 days | Fri 14/04/23 | Tue 09/05/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.4.1.4.1 |  |  | Issue Redline Version of documents | 100% | Fri 14/04/23 | Fri 14/04/23 | 1 day | Fri 14/04/23 | Fri 14/04/23 | 104FS+5 days | 107 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.4.1.4.2 |  |  | Participants provide review comments to common log | 100% | Mon 17/04/23 | Tue 09/05/23 | 17 days | Mon 17/04/23 | Tue 09/05/23 | 106 | 109 | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.4.1.5 |  |  | Assurance review | 100% | Wed 10/05/23 | Mon 05/06/23 | 19 days | Wed 10/05/23 | Mon 05/06/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.4.1.5.1 |  |  | SI Design Review and Respond to Comments | 100% | Wed 10/05/23 | Tue 16/05/23 | 5 days | Wed 10/05/23 | Tue 16/05/23 | 107 | 110 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.4.1.5.2 |  |  | Prep for Assurance Review Meeting | 100% | Wed 17/05/23 | Thu 25/05/23 | 7 days | Wed 17/05/23 | Thu 25/05/23 | 109 | 111 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.4.1.5.3 |  |  | Conduct Assurance Review Meeting | 100% | Fri 26/05/23 | Fri 26/05/23 | 1 day | Fri 26/05/23 | Fri 26/05/23 | 110 | 112 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.4.1.5.4 |  |  | Update Artefacts following Assurance Review | 100% | Mon 29/05/23 | Mon 05/06/23 | 6 days | Mon 29/05/23 | Mon 05/06/23 | 111 | 114 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.4.1.6 |  |  | PSG Approval of interim release plan | 100% | Thu 08/06/23 | Thu 08/06/23 | 1 day | Thu 08/06/23 | Thu 08/06/23 |  |  | 0 days | 0 days | 0 days | PP | SI Design |  |  | 5.1 | Yes | Paul Pettitt
5 | 1.3.4.1.7 |  |  | Publish updated baselined artefacts | 100% | Tue 06/06/23 | Mon 12/06/23 | 0 days | Tue 06/06/23 | Mon 12/06/23 | 112 | 115 | 0 days | 0 days | -5 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.4.1.8 | T3-DB-0095 | DAG | Interim release 1 Go live | 100% | Mon 12/06/23 | Mon 12/06/23 | 0 days | Mon 12/06/23 | Mon 12/06/23 | 114 | 1.0071e+23 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
4 | 1.3.4.2 |  |  | Interim release 2 | 100% | Tue 30/05/23 | Wed 05/07/23 | 27 days | Tue 30/05/23 | Wed 05/07/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.4.2.1 |  |  | Update baselined artefacts | 100% | Tue 30/05/23 | Wed 05/07/23 | 27 days | Tue 30/05/23 | Wed 05/07/23 |  | 118 | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5.1 | Yes | Paul Pettitt
5 | 1.3.4.2.2 | T3-DB-0096 | DAG | Interim release 2 Go live | 100% | Wed 05/07/23 | Wed 05/07/23 | 0 days | Wed 05/07/23 | Wed 05/07/23 | 117 | 82 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
4 | 1.3.4.3 |  |  | Interim release 3 | 100% | Thu 15/06/23 | Wed 02/08/23 | 35 days | Thu 15/06/23 | Wed 02/08/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.4.3.1 |  |  | Update baselined artefacts | 100% | Thu 15/06/23 | Wed 02/08/23 | 35 days | Thu 15/06/23 | Wed 02/08/23 |  | 121 | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5.1 | Yes | Paul Pettitt
5 | 1.3.4.3.2 | T3-DB-0097 | DAG | Interim release 3 Go live | 100% | Wed 02/08/23 | Wed 02/08/23 | 0 days | Wed 02/08/23 | Wed 02/08/23 | 120 |  | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
4 | 1.3.4.4 |  |  | Interim release 4 | 100% | Wed 12/07/23 | Wed 30/08/23 | 36 days | Wed 12/07/23 | Wed 30/08/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.1 | Yes | N/A
5 | 1.3.4.4.1 |  |  | Update baselined artefacts | 100% | Wed 12/07/23 | Wed 30/08/23 | 36 days | Wed 12/07/23 | Wed 30/08/23 |  | 124 | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5.1 | Yes | Paul Pettitt
5 | 1.3.4.4.2 | T3-DB-0081 | DAG | Interim release 4 Go live | 100% | Wed 30/08/23 | Wed 30/08/23 | 0 days | Wed 30/08/23 | Wed 30/08/23 | 123 |  | 0 days | 0 days | 0 days | SI Design |  |  |  | 5.1 | Yes | Paul Pettitt
4 | 1.3.4.5 |  |  | Interim release 5 | 99% | Thu 17/08/23 | Fri 08/03/24 | 147 days | Thu 17/08/23 | Fri 08/03/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.1 | Yes | N/A
5 | 1.3.4.5.1 |  |  | Update baselined artefacts | 100% | Thu 17/08/23 | Wed 04/10/23 | 35 days | Thu 17/08/23 | Wed 04/10/23 |  | 127 | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5.1 | Yes | Paul Pettitt
5 | 1.3.4.5.2 | T3-DB-0083 | DAG | Interim release 5 Go live | 100% | Wed 04/10/23 | Wed 04/10/23 | 0 days | Wed 04/10/23 | Wed 04/10/23 | 126 | 84FS+2 days,128FS+102 days | 0 days | 0 days | 0 days | SI Design |  |  |  | 5.1 | Yes | Paul Pettitt
5 | 1.3.4.5.3 |  |  | Interim Release 5 Deployed to SIT | 100% | Mon 26/02/24 | Fri 08/03/24 | 10 days | Mon 26/02/24 | Fri 08/03/24 | 127FS+102 days | 1082 | 0 days | 0 days | 0 days | SI Testing | PP |  |  | 5.16 | Yes | Lee Cox
4 | 1.3.4.6 |  |  | Interim release 6 | 78% | Thu 14/09/23 | Fri 07/06/24 | 192 days | Thu 14/09/23 | Fri 07/06/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.1 | Yes | N/A
5 | 1.3.4.6.1 |  |  | Update baselined artefacts | 100% | Thu 14/09/23 | Wed 01/11/23 | 35 days | Thu 14/09/23 | Fri 27/10/23 |  | 131 | 0 days | 3 days | 3 days | SI Design | PP |  |  | 5.1 | Yes | Paul Pettitt
5 | 1.3.4.6.2 | T3-DB-0085 | DAG | Interim release 6 Go live | 100% | Wed 01/11/23 | Wed 01/11/23 | 0 days | Fri 27/10/23 | Fri 27/10/23 | 130 | 132FS+147 days | 3 days | 3 days | 0 days | SI Design |  |  |  | 5.11 | Yes | Paul Pettitt
5 | 1.3.4.6.3 |  |  | Interim Release 6 Deployed to SIT | 0% | Mon 27/05/24 | Fri 07/06/24 | 10 days | Mon 27/05/24 | Fri 07/06/24 | 131FS+147 days | 1085 | 0 days | 0 days | 0 days | SI Testing | PP |  |  | 5.16 | Yes | Lee Cox
4 | 1.3.4.7 |  |  | Interim release 7 | 88% | Wed 18/10/23 | Fri 07/06/24 | 168 days | Wed 18/10/23 | Fri 07/06/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.5 | Yes | N/A
5 | 1.3.4.7.1 |  |  | Update baselined artefacts | 100% | Wed 18/10/23 | Wed 31/01/24 | 76 days | Wed 18/10/23 | Wed 31/01/24 |  | 135 | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5.5 | Yes | Paul Pettitt
5 | 1.3.4.7.2 | T3-DB-0098 | DAG | Interim release 7 Go live | 100% | Wed 31/01/24 | Wed 31/01/24 | 0 days | Wed 31/01/24 | Wed 31/01/24 | 134 | 86,136FS+82 days | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5.14 | Yes | Paul Pettitt
5 | 1.3.4.7.3 |  |  | Interim Release 7 Deployed to SIT | 0% | Mon 27/05/24 | Fri 07/06/24 | 10 days | Mon 27/05/24 | Fri 07/06/24 | 135FS+82 days | 1085 | 0 days | 0 days | 0 days | SI Testing | PP |  |  | 5.16 | Yes | Lee Cox
4 | 1.3.4.8 |  |  | Interim release 8 | 78% | Wed 14/02/24 | Fri 30/08/24 | 143 days | Wed 14/02/24 | Fri 30/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.5 | Yes | N/A
5 | 1.3.4.8.1 |  |  | Update baselined artefacts | 100% | Wed 14/02/24 | Wed 03/04/24 | 36 days | Wed 14/02/24 | Wed 03/04/24 |  | 139 | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5.5 | Yes | Paul Pettitt
5 | 1.3.4.8.2 | T3-DB-0099 | DAG | Interim release 8 Go live | 100% | Wed 03/04/24 | Wed 03/04/24 | 0 days | Wed 03/04/24 | Wed 03/04/24 | 138 | 88,140FS+97 days | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5.14 | Yes | Paul Pettitt
5 | 1.3.4.8.3 |  |  | Interim Release 8 Deployed to SIT | 0% | Mon 19/08/24 | Fri 30/08/24 | 10 days | Mon 19/08/24 | Fri 30/08/24 | 139FS+97 days | 1088 | 0 days | 0 days | 0 days | SI Testing | PP |  |  | 5.16 | Yes | Lee Cox
3 | 1.3.5 |  |  | Queries Support / Knowledgebase & Tool Roll-Out (Systems) | 99% | Tue 03/01/23 | Mon 01/04/24 | 325 days | Tue 03/01/23 | Mon 01/04/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.3.5.1 |  |  | Query Management | 100% | Tue 03/01/23 | Mon 01/04/24 | 325 days | Tue 03/01/23 | Mon 01/04/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.5.1.1 |  |  | Respond to Participant Queries | 100% | Tue 03/01/23 | Mon 01/04/24 | 325 days | Tue 03/01/23 | Mon 01/04/24 |  | 144SS | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.5.1.2 |  |  | Respond to Programme Queries | 100% | Tue 03/01/23 | Mon 01/04/24 | 325 days | Tue 03/01/23 | Mon 01/04/24 | 143SS |  | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
4 | 1.3.5.2 |  |  | Query Support tooling (FreshDesk) | 100% | Thu 01/06/23 | Mon 03/07/23 | 23 days | Thu 01/06/23 | Mon 03/07/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.5.2.1 |  |  | Migrate to Standalone Freshdesk | 100% | Thu 01/06/23 | Wed 14/06/23 | 10 days | Thu 01/06/23 | Wed 14/06/23 |  | 152SS,147 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.5.2.2 |  |  | Develop reporting dashboard | 100% | Thu 15/06/23 | Wed 21/06/23 | 5 days | Thu 15/06/23 | Wed 21/06/23 | 146 | 148 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.5.2.3 |  |  | Issue to SRO for Review | 100% | Thu 22/06/23 | Wed 28/06/23 | 5 days | Thu 22/06/23 | Wed 28/06/23 | 147 | 149 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.5.2.4 |  |  | Update following review | 100% | Thu 29/06/23 | Fri 30/06/23 | 2 days | Thu 29/06/23 | Fri 30/06/23 | 148 | 150 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.5.2.5 |  |  | Sign off | 100% | Mon 03/07/23 | Mon 03/07/23 | 1 day | Mon 03/07/23 | Mon 03/07/23 | 149 |  | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
4 | 1.3.5.3 |  |  | KnowledgeBase Development | 100% | Thu 01/06/23 | Fri 08/09/23 | 72 days | Thu 01/06/23 | Fri 08/09/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.5.3.1 |  |  | Define Scope of KB | 100% | Thu 01/06/23 | Thu 01/06/23 | 1 day | Thu 01/06/23 | Thu 01/06/23 | 146SS | 153 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.5.3.2 |  |  | Capture Existing KB artefacts | 100% | Fri 02/06/23 | Thu 29/06/23 | 20 days | Fri 02/06/23 | Thu 29/06/23 | 152 | 154 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.5.3.3 |  |  | Tag artefacts | 100% | Fri 30/06/23 | Thu 06/07/23 | 5 days | Fri 30/06/23 | Thu 06/07/23 | 153 | 155 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.5.3.4 |  |  | Develop Participant Interfaces | 100% | Fri 07/07/23 | Thu 03/08/23 | 20 days | Fri 07/07/23 | Thu 03/08/23 | 154 | 156 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.5.3.5 |  |  | Promote to Collaboration Portal | 100% | Fri 04/08/23 | Fri 01/09/23 | 21 days | Fri 04/08/23 | Fri 01/09/23 | 155 | 157 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.5.3.6 |  |  | Link into FreshDesk | 100% | Mon 04/09/23 | Fri 08/09/23 | 5 days | Mon 04/09/23 | Fri 08/09/23 | 156 |  | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
3 | 1.3.6 |  |  | PP Design, Build & Test (DBT) | 91% | Mon 31/10/22 | Fri 20/09/24 | 495 days | Mon 31/10/22 | Mon 16/02/26 |  |  | 0 days | -366 days | -366 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.3.6.1 |  |  | PP Impact Assessment, Planning & Procurement | 100% | Mon 31/10/22 | Fri 31/03/23 | 110 days | Mon 31/10/22 | Fri 31/03/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.6.1.1 |  |  | PP Impact Assessment | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.6.1.1.1 |  |  | Develop heatmap for impact of MHHS | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 48 |  | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | PP
6 | 1.3.6.1.1.2 |  |  | Develop detailed impact assessment | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 48 |  | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | PP
5 | 1.3.6.1.2 |  |  | PP Planning | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.6.1.2.1 |  |  | Develop detailed short-term plan | 100% | Mon 31/10/22 | Wed 30/11/22 | 23 days | Mon 31/10/22 | Wed 30/11/22 | 48 | 418SS | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | PP
6 | 1.3.6.1.2.2 |  |  | Develop overall project plan for implementation | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 48 |  | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | PP
6 | 1.3.6.1.2.3 |  |  | Develop procurement plan | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 48 |  | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | PP
5 | 1.3.6.1.3 |  |  | PP Software/Service Procurement | 100% | Mon 31/10/22 | Fri 31/03/23 | 110 days | Mon 31/10/22 | Fri 31/03/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.6.1.3.1 |  |  | Run tender process | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 48 | 169 | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | PP
6 | 1.3.6.1.3.2 |  |  | Select provider & sign commercials | 100% | Wed 01/02/23 | Fri 31/03/23 | 43 days | Wed 01/02/23 | Fri 31/03/23 | 168 |  | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | PP
4 | 1.3.6.2 |  |  | Central Systems DBT | 100% | Mon 31/10/22 | Fri 26/01/24 | 325 days | Mon 31/10/22 | Fri 23/02/24 |  |  | 0 days | -20 days | -20 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.6.2.1 |  |  | Elexon Central Systems DBT CIT (Entering at Interval 1) | 100% | Mon 31/10/22 | Wed 11/10/23 | 248 days | Mon 31/10/22 | Thu 12/10/23 |  |  | 0 days | -1 day | -1 day | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.6.2.1.1 |  |  | Design and Build | 100% | Mon 31/10/22 | Fri 22/09/23 | 235 days | Mon 31/10/22 | Fri 29/09/23 |  |  | 0 days | -5 days | -5 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.1.1.1 |  |  | Helix Design and Build | 100% | Mon 31/10/22 | Fri 22/09/23 | 235 days | Mon 31/10/22 | Fri 29/09/23 | 2 |  | 0 days | -5 days | -5 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
6 | 1.3.6.2.1.2 |  |  | Test Approach & Plan | 100% | Mon 31/10/22 | Fri 22/09/23 | 235 days | Mon 31/10/22 | Fri 22/09/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.1.2.1 |  |  | Develop Test Approach & Plan | 100% | Mon 31/10/22 | Fri 07/07/23 | 180 days | Mon 31/10/22 | Fri 07/07/23 |  | 176FF+4 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.2.1.2.2 | T3-DB-0029 | SITAG | Elexon Central Systems Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Thu 13/07/23 | Thu 13/07/23 | 0 days | Thu 13/07/23 | Thu 13/07/23 | 175FF+4 days | 177FS+9 days,183,186,181FS+10 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.2.1.2.3 |  |  | Elexon Central Systems Test Approach & Plan (PIT) V2 resubmitted to Programme for assurance | 100% | Thu 27/07/23 | Thu 27/07/23 | 0 days | Thu 27/07/23 | Thu 27/07/23 | 176FS+9 days | 178FS+17 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.4 | Yes | Lee Cox
7 | 1.3.6.2.1.2.4 |  |  | Elexon Central Systems Test Approach & Plan (PIT) V3 resubmitted to Programme for assurance | 100% | Fri 18/08/23 | Fri 18/08/23 | 0 days | Fri 18/08/23 | Fri 18/08/23 | 177FS+17 days | 179FS+25 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.4 | Yes | Lee Cox
7 | 1.3.6.2.1.2.5 | T3-DB-0106 | SITAG | Elexon Central Systems Test approach and plan MHHS Review Completed | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 178FS+25 days | 192 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
6 | 1.3.6.2.1.3 |  |  | Test Readiness Report | 100% | Fri 28/07/23 | Fri 18/08/23 | 16 days | Thu 03/08/23 | Thu 12/10/23 |  |  | -4 days | -39 days | -35 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.1.3.1 |  |  | Test readiness reporting | 100% | Fri 28/07/23 | Fri 18/08/23 | 16 days | Thu 03/08/23 | Thu 12/10/23 | 176FS+10 days | 189FS+10 days,190 | -4 days | -39 days | -35 days | PP | 109 |  |  | 5 | Yes | Lee Cox
6 | 1.3.6.2.1.4 |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 04/08/23 | Fri 22/09/23 | 35 days | Fri 04/08/23 | Fri 22/09/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.1.4.1 | T3-DB-0030 | SITAG | Elexon Central Systems RTTM submitted to Programme for assurance | 100% | Fri 04/08/23 | Fri 04/08/23 | 0 days | Fri 04/08/23 | Fri 04/08/23 | 176 | 184FS+35 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.2.1.4.2 | T3-DB-0107 | SITAG | Elexon Central Systems RTTM MHHS Review Completed | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 183FS+35 days | 192 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
6 | 1.3.6.2.1.5 |  |  | Test Scenarios | 100% | Fri 04/08/23 | Fri 22/09/23 | 35 days | Fri 04/08/23 | Fri 22/09/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.1.5.1 | T3-DB-0032 | SITAG | Elexon Central Systems test scenarios submitted to Programme for assurance | 100% | Fri 04/08/23 | Fri 04/08/23 | 0 days | Fri 04/08/23 | Fri 04/08/23 | 176 | 187FS+35 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.2.1.5.2 | T3-DB-0108 | SITAG | Elexon Central Systems Test scenarios MHHS Review Completed | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 186FS+35 days | 192 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
6 | 1.3.6.2.1.6 |  |  | PIT Execution | 100% | Mon 21/08/23 | Wed 11/10/23 | 38 days | Mon 31/10/22 | Wed 11/10/23 |  |  | 210 days | 0 days | -210 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.1.6.1 |  |  | PIT Test Execution Progress Report | 100% | Mon 04/09/23 | Wed 27/09/23 | 18 days | Mon 31/10/22 | Fri 22/09/23 | 181FS+10 days | 192 | 220 days | 3 days | -217 days | PP | SI Test |  |  | 5.1 | Yes | Lee Cox
7 | 1.3.6.2.1.6.2 |  |  | Elexon Central Systems PIT Execution | 100% | Mon 21/08/23 | Wed 27/09/23 | 28 days | Tue 08/11/22 | Mon 09/10/23 | 181 | 191 | 204 days | -8 days | -212 days | PP | SI Test |  |  | 5.1 | Yes | Lee Cox
7 | 1.3.6.2.1.6.3 | T3-DB-0109 | SITAG | Elexon Central Systems PIT Completion Report submitted to Programme for assurance | 100% | Wed 27/09/23 | Wed 27/09/23 | 0 days | Wed 27/09/23 | Wed 27/09/23 | 190 | 192FS+10 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.2.1.6.4 | T3-DB-0110 | SITAG | Elexon Central Systems PIT Completion Report MHHS Review Completed | 100% | Wed 11/10/23 | Wed 11/10/23 | 0 days | Wed 11/10/23 | Wed 11/10/23 | 184,187,189,191FS+10 days,179 | 636 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
5 | 1.3.6.2.2 |  |  | DIP DBT CIT (Entering at Interval 1) | 100% | Mon 02/01/23 | Mon 06/11/23 | 221 days | Mon 31/10/22 | Mon 06/11/23 |  |  | 45 days | 0 days | -45 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.6.2.2.1 |  |  | Design | 100% | Mon 02/01/23 | Fri 21/04/23 | 80 days | Mon 02/01/23 | Fri 21/04/23 |  | 195SS+5 days | 0 days | 0 days | 0 days | PP | SI Design |  |  | 5 | Yes | Lee Cox
6 | 1.3.6.2.2.2 |  |  | Build | 100% | Mon 09/01/23 | Fri 11/08/23 | 155 days | Mon 09/01/23 | Fri 11/08/23 | 194SS+5 days |  | 0 days | 0 days | 0 days | PP |  |  |  | 5.5 | Yes | Lee Cox
6 | 1.3.6.2.2.3 |  |  | Test Approach & Plan | 100% | Fri 07/07/23 | Thu 20/07/23 | 9 days | Mon 31/10/22 | Fri 21/07/23 |  |  | 180 days | -1 day | -181 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.2.3.1 | T3-DB-0026 | SITAG | DIP Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 07/07/23 | Fri 07/07/23 | 0 days | Fri 07/07/23 | Fri 07/07/23 |  | 198FS+9 days,200FS+9 days,202FS+15 days,205FS+15 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.2.2.3.2 |  |  | DIP Test Approach & Plan (PIT) MHHS Review Completed | 100% | Thu 20/07/23 | Thu 20/07/23 | 0 days | Mon 10/07/23 | Fri 21/07/23 | 197FS+9 days | 636 | 9 days | -1 day | -10 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.3.6.2.2.4 |  |  | PIT Test Readiness Report | 100% | Fri 21/07/23 | Fri 01/09/23 | 31 days | Fri 21/07/23 | Fri 29/09/23 |  |  | 0 days | -20 days | -20 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.2.4.1 |  |  | Test readiness reporting | 100% | Fri 21/07/23 | Fri 01/09/23 | 31 days | Fri 21/07/23 | Fri 29/09/23 | 197FS+9 days | 208 | 0 days | -20 days | -20 days | SI Test | 109 |  |  | 5 | Yes | Lee Cox
6 | 1.3.6.2.2.5 |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 04/08/23 | Wed 30/08/23 | 18 days | Mon 31/10/22 | Fri 18/08/23 |  |  | 200 days | 8 days | -192 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.2.5.1 | T3-DB-0034 | SITAG | DIP RTTM submitted to Programme for assurance | 100% | Fri 04/08/23 | Fri 04/08/23 | 0 days | Fri 04/08/23 | Fri 04/08/23 | 197FS+15 days | 203FS+18 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.6 | Yes | Lee Cox
7 | 1.3.6.2.2.5.2 |  |  | DIP RTTM MHHS Review Completed | 100% | Wed 30/08/23 | Wed 30/08/23 | 0 days | Mon 07/08/23 | Fri 18/08/23 | 202FS+18 days | 636 | 18 days | 8 days | -10 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.3.6.2.2.6 |  |  | Test Scenarios | 100% | Mon 31/07/23 | Wed 30/08/23 | 22 days | Mon 31/10/22 | Mon 14/08/23 |  |  | 196 days | 12 days | -184 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.2.6.1 | T3-DB-0036 | SITAG | DIP PIT test scenarios submitted to Programme for assurance | 100% | Mon 31/07/23 | Mon 31/07/23 | 0 days | Mon 31/07/23 | Mon 31/07/23 | 197FS+15 days | 206FS+22 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.2.2.6.2 |  |  | DIP Test scenarios MHHS Review Completed | 100% | Wed 30/08/23 | Wed 30/08/23 | 0 days | Tue 01/08/23 | Mon 14/08/23 | 205FS+22 days |  | 22 days | 12 days | -10 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.3.6.2.2.7 |  |  | PIT execution | 100% | Tue 29/08/23 | Mon 06/11/23 | 50 days | Fri 01/09/23 | Mon 06/11/23 |  |  | -3 days | 0 days | 3 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.2.7.1 |  |  | PIT Test Execution Progress Report | 100% | Fri 01/09/23 | Mon 23/10/23 | 37 days | Fri 01/09/23 | Mon 23/10/23 | 209FF,200 | 213 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.6 | Yes | Lee Cox
7 | 1.3.6.2.2.7.2 |  |  | PIT Execution (Interim Release 1) | 100% | Tue 29/08/23 | Mon 09/10/23 | 30 days | Wed 06/09/23 | Mon 09/10/23 |  | 208FF,210,211 | -6 days | 0 days | 6 days | PP | SI Test |  |  | 5.6 | Yes | Lee Cox
7 | 1.3.6.2.2.7.3 |  |  | PIT Execution (Interim Release 2) | 100% | Tue 10/10/23 | Mon 23/10/23 | 10 days | Tue 10/10/23 | Mon 23/10/23 | 209 | 213 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.6 | Yes | Lee Cox
7 | 1.3.6.2.2.7.4 | T3-DB-0111 | SITAG | DIP PIT Completion Report (Interim Release 1) submitted to Programme for assurance | 100% | Mon 09/10/23 | Mon 09/10/23 | 0 days | Mon 09/10/23 | Mon 09/10/23 | 209 | 212FS+10 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.2.2.7.5 | T3-DB-0112 | SITAG | DIP PIT Completion Report (Interim Release 1) MHHS Review Completed | 100% | Mon 23/10/23 | Mon 23/10/23 | 0 days | Mon 23/10/23 | Mon 23/10/23 | 211FS+10 days | 636 | 0 days | 0 days | 0 days | SI Test | SI Test |  |  | 5.1 | Yes | Lee Cox
7 | 1.3.6.2.2.7.6 | T3-DB-0113 | SITAG | DIP PIT Completion Report (Interim Release 2) submitted to Programme for assurance | 100% | Mon 23/10/23 | Mon 23/10/23 | 0 days | Mon 23/10/23 | Mon 23/10/23 | 210208 | 214FS+10 days,636 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.1 | Yes | Lee Cox
7 | 1.3.6.2.2.7.7 | T3-DB-0114 | SITAG | DIP PIT Completion Report (Interim Release 2) MHHS Review Completed | 100% | Mon 06/11/23 | Mon 06/11/23 | 0 days | Mon 06/11/23 | Mon 06/11/23 | 213FS+10 days |  | 0 days | 0 days | 0 days | SI Test | SI Test |  |  | 5.14 | Yes | Lee Cox
5 | 1.3.6.2.3 |  |  | DCC (DSP) DBT SIT Functional (Entering at SIT Functional) | 100% | Mon 31/10/22 | Fri 26/01/24 | 325 days | Mon 31/10/22 | Fri 23/02/24 |  |  | 0 days | -20 days | -20 days | N/A | N/A |  |  | 5.18 | Yes | N/A
6 | 1.3.6.2.3.1 |  |  | Design | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  | 218FS+208 days | 0 days | 0 days | 0 days | PP | SI Design |  |  | 5.18 | Yes | Lee Cox
6 | 1.3.6.2.3.2 |  |  | Test Approach & Plan | 100% | Fri 17/11/23 | Fri 15/12/23 | 20 days | Fri 17/11/23 | Fri 15/12/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.18 | Yes | N/A
7 | 1.3.6.2.3.2.1 | T3-DB-0068 | SITAG | DCC Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 216FS+208 days | 219FS+20 days,221FS+10 days,764,223FS+20 days,226FS+20 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.18 | Yes | Lee Cox
7 | 1.3.6.2.3.2.2 | T3-DB-0115 | SITAG | DCC Test Approach & Plan (PIT) MHHS Review Completed | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 218FS+20 days |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.18 | Yes | Lee Cox
6 | 1.3.6.2.3.3 |  |  | Test Readiness Report | 100% | Mon 04/12/23 | Tue 02/01/24 | 22 days | Fri 27/10/23 | Fri 05/01/24 |  |  | 26 days | -3 days | -29 days | N/A | N/A |  |  | 5.18 | Yes | N/A
7 | 1.3.6.2.3.3.1 |  |  | Test readiness reporting | 100% | Mon 04/12/23 | Tue 02/01/24 | 22 days | Fri 27/10/23 | Fri 05/01/24 | 218FS+10 days |  | 26 days | -3 days | -29 days | PP | 109 |  |  | 5.18 | Yes | Lee Cox
6 | 1.3.6.2.3.4 |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 15/12/23 | Fri 26/01/24 | 30 days | Fri 15/12/23 | Fri 26/01/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.18 | Yes | N/A
7 | 1.3.6.2.3.4.1 | T3-DB-0074 | SITAG | DCC RTTM submitted to Programme for assurance | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 218FS+20 days | 224FS+30 days,764 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.18 | Yes | Lee Cox
7 | 1.3.6.2.3.4.2 | T3-DB-0116 | SITAG | DCC RTTM MHHS Review Completed | 100% | Fri 26/01/24 | Fri 26/01/24 | 0 days | Fri 26/01/24 | Fri 26/01/24 | 223FS+30 days |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.18 | Yes | Lee Cox
6 | 1.3.6.2.3.5 |  |  | Test Scenarios | 100% | Fri 15/12/23 | Fri 26/01/24 | 30 days | Fri 15/12/23 | Fri 26/01/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.18 | Yes | N/A
7 | 1.3.6.2.3.5.1 | T3-DB-0078 | SITAG | DCC test scenarios submitted to Programme for assurance | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 218FS+20 days | 227FS+30 days,764 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.18 | Yes | Lee Cox
7 | 1.3.6.2.3.5.2 | T3-DB-0117 | SITAG | DCC Test Scenarios MHHS Review Completed | 100% | Fri 26/01/24 | Fri 26/01/24 | 0 days | Fri 26/01/24 | Fri 26/01/24 | 226FS+30 days |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.18 | Yes | Lee Cox
5 | 1.3.6.2.4 |  |  | RECCo (EES) DBT CIT (Entering at Interval 6) | 100% | Fri 13/10/23 | Fri 19/01/24 | 71 days | Mon 31/10/22 | Fri 19/01/24 |  |  | 249 days | 0 days | -249 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.6.2.4.1 |  |  | Test Approach & Plan | 100% | Fri 13/10/23 | Thu 09/11/23 | 20 days | Fri 13/10/23 | Thu 09/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.4.1.1 | T3-DB-0066 | SITAG | EES Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 13/10/23 | Fri 13/10/23 | 0 days | Fri 13/10/23 | Fri 13/10/23 |  | 231FS+20 days,233FS+10 days,235FS+15 days,238FS+15 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.2.4.1.2 | T3-DB-0119 | SITAG | EES Test approach and plan (PIT) MHHS Review Completed | 100% | Thu 09/11/23 | Thu 09/11/23 | 0 days | Thu 09/11/23 | Thu 09/11/23 | 230FS+20 days | 244 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
6 | 1.3.6.2.4.2 |  |  | Test Readiness Report | 100% | Fri 27/10/23 | Thu 09/11/23 | 10 days | Fri 27/10/23 | Fri 05/01/24 |  |  | 0 days | -41 days | -41 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.4.2.1 |  |  | Test readiness reporting | 100% | Fri 27/10/23 | Thu 09/11/23 | 10 days | Fri 27/10/23 | Fri 05/01/24 | 230FS+10 days | 241 | 0 days | -41 days | -41 days | PP | 109 |  |  | 5 | Yes | Lee Cox
6 | 1.3.6.2.4.3 |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Thu 02/11/23 | Thu 30/11/23 | 20 days | Thu 02/11/23 | Thu 30/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.4.3.1 | T3-DB-0072 | SITAG | EES RTTM submitted to Programme for assurance | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 230FS+15 days | 236FS+20 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.2.4.3.2 | T3-DB-0120 | SITAG | EES RTTM MHHS Review Completed | 100% | Thu 30/11/23 | Thu 30/11/23 | 0 days | Thu 30/11/23 | Thu 30/11/23 | 235FS+20 days | 244 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
6 | 1.3.6.2.4.4 |  |  | Test Scenarios | 100% | Thu 02/11/23 | Thu 30/11/23 | 20 days | Thu 02/11/23 | Thu 30/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.4.4.1 | T3-DB-0031 | SITAG | EES test scenarios submitted to Programme for assurance | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 230FS+15 days | 239FS+20 days,242FS+5 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.2.4.4.2 | T3-DB-0121 | SITAG | EES Test scenarios MHHS Review Completed | 100% | Thu 30/11/23 | Thu 30/11/23 | 0 days | Thu 30/11/23 | Thu 30/11/23 | 238FS+20 days | 244 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
6 | 1.3.6.2.4.5 |  |  | PIT execution | 100% | Fri 10/11/23 | Fri 19/01/24 | 51 days | Mon 31/10/22 | Fri 19/01/24 |  |  | 269 days | 0 days | -269 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.4.5.1 |  |  | PIT Test Execution Progress Report | 100% | Fri 10/11/23 | Fri 05/01/24 | 41 days | Fri 10/11/23 | Fri 05/01/24 | 233 | 243 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.2.4.5.2 |  |  | PIT Execution | 100% | Fri 10/11/23 | Fri 05/01/24 | 41 days | Mon 31/10/22 | Fri 05/01/24 | 238FS+5 days | 243 | 269 days | 0 days | -269 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.2.4.5.3 | T3-DB-0122 | SITAG | EES PIT Completion Report submitted to Programme for assurance | 100% | Fri 05/01/24 | Fri 05/01/24 | 0 days | Fri 05/01/24 | Fri 05/01/24 | 241242 | 244FS+10 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.14 | Yes | Lee Cox
7 | 1.3.6.2.4.5.4 | T3-DB-0123 | SITAG | EES PIT Completion Report MHHS Review Completed | 100% | Fri 19/01/24 | Fri 19/01/24 | 0 days | Fri 19/01/24 | Fri 19/01/24 | 231,236,239,243FS+10 days | 791 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
5 | 1.3.6.2.5 |  |  | Registration Services DBT CIT (Entering at Interval 2) | 100% | Fri 28/07/23 | Fri 03/11/23 | 70 days | Fri 28/07/23 | Fri 03/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.6.2.5.1 |  |  | Test Approach & Plan | 100% | Fri 28/07/23 | Fri 22/09/23 | 40 days | Fri 28/07/23 | Fri 22/09/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.5.1.1 | T3-DB-0028 | SITAG | Registration Services Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 28/07/23 | Fri 28/07/23 | 0 days | Fri 28/07/23 | Fri 28/07/23 |  | 248FS+40 days,250FS+10 days,252FS+15 days,255FS+15 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.2.5.1.2 | T3-DB-0124 | SITAG | Registration Services Test approach and plan MHHS Review Completed | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 247FS+40 days | 261 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
6 | 1.3.6.2.5.2 |  |  | Test Readiness Report | 100% | Mon 14/08/23 | Fri 08/09/23 | 20 days | Fri 11/08/23 | Fri 20/10/23 |  |  | 1 day | -30 days | -31 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.5.2.1 |  |  | Test readiness reporting | 100% | Mon 14/08/23 | Fri 08/09/23 | 20 days | Fri 11/08/23 | Fri 20/10/23 | 247FS+10 days | 258 | 1 day | -30 days | -31 days | PP | 109 |  |  | 5 | Yes | Lee Cox
6 | 1.3.6.2.5.3 |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 01/09/23 | Fri 29/09/23 | 20 days | Fri 01/09/23 | Fri 29/09/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.5.3.1 | T3-DB-0042 | SITAG | Registration Services RTTM submitted to Programme for assurance | 100% | Fri 01/09/23 | Fri 01/09/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 247FS+15 days | 253FS+20 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.6 | Yes | Lee Cox
7 | 1.3.6.2.5.3.2 | T3-DB-0125 | SITAG | Registration Services RTTM MHHS Review Completed | 100% | Fri 29/09/23 | Fri 29/09/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 252FS+20 days | 261 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
6 | 1.3.6.2.5.4 |  |  | Test Scenarios | 100% | Fri 01/09/23 | Fri 29/09/23 | 20 days | Fri 01/09/23 | Fri 29/09/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.5.4.1 | T3-DB-0044 | SITAG | Registration Services test scenarios submitted to Programme for assurance | 100% | Fri 01/09/23 | Fri 01/09/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 247FS+15 days | 256FS+20 days,259FS+5 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.6 | Yes | Lee Cox
7 | 1.3.6.2.5.4.2 | T3-DB-0126 | SITAG | Registration Services Test scenarios MHHS Review Completed | 100% | Fri 29/09/23 | Fri 29/09/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 255FS+20 days | 261 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
6 | 1.3.6.2.5.5 |  |  | PIT execution | 100% | Mon 11/09/23 | Fri 03/11/23 | 40 days | Mon 11/09/23 | Fri 03/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.2.5.5.1 |  |  | PIT Test Execution Progress Report | 100% | Mon 11/09/23 | Wed 25/10/23 | 33 days | Mon 11/09/23 | Fri 20/10/23 | 250 | 260 | 0 days | 3 days | 3 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.2.5.5.2 |  |  | PIT Execution | 100% | Mon 11/09/23 | Fri 20/10/23 | 30 days | Mon 11/09/23 | Fri 20/10/23 | 255FS+5 days | 260 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.2.5.5.3 | T3-DB-0127 | SITAG | Registration Services PIT (CIT interval 2) Completion Report submitted to Programme for assurance | 100% | Wed 25/10/23 | Wed 25/10/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 258259 | 261FS+7 days | 3 days | 3 days | 0 days | PP | SI Test |  |  | 5.1 | Yes | Lee Cox
7 | 1.3.6.2.5.5.4 | T3-DB-0128 | SITAG | Registration Services PIT (CIT interval 2) Completion Report MHHS Review Completed | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 248,253,256,260FS+7 days | 663 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.11 | Yes | Lee Cox
4 | 1.3.6.3 |  |  | SIT Participants DBT | 73% | Fri 11/08/23 | Fri 20/09/24 | 291 days | Mon 31/10/22 | Fri 20/09/24 |  |  | 204 days | 0 days | -204 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.6.3.1 |  |  | All Data Services DBT CIT (Entering at Interval 3) | 100% | Fri 11/08/23 | Fri 17/11/23 | 71 days | Mon 31/10/22 | Fri 17/11/23 |  |  | 204 days | 0 days | -204 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.6.3.1.1 |  |  | Test Approach & Plan | 100% | Fri 11/08/23 | Thu 21/09/23 | 30 days | Fri 11/08/23 | Thu 21/09/23 |  |  | -1 day | 0 days | 1 day | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.1.1.1 | T3-DB-0038 | SITAG | All Data Services Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | Fri 11/08/23 | Fri 11/08/23 | 0 days | Fri 11/08/23 | Fri 11/08/23 |  | 266FS+30 days,268FS+10 days,270FS+29 days,273FS+29 days | -1 day | -1 day | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.3.1.1.2 | T3-DB-0129 | SITAG | All Data Services Test approach and plans MHHS Review Completed | 100% | Thu 21/09/23 | Thu 21/09/23 | 0 days | Thu 21/09/23 | Thu 21/09/23 | 265FS+30 days | 279 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.11 | Yes | Lee Cox
6 | 1.3.6.3.1.2 |  |  | Test Readiness Report | 100% | Fri 25/08/23 | Fri 08/09/23 | 11 days | Fri 25/08/23 | Fri 08/09/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.1.2.1 |  |  | Test readiness reporting | 100% | Fri 25/08/23 | Fri 08/09/23 | 11 days | Fri 25/08/23 | Fri 08/09/23 | 265FS+10 days | 276 | 0 days | 0 days | 0 days | PP | 109 |  |  | 5 | Yes | Lee Cox
6 | 1.3.6.3.1.3 |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Wed 20/09/23 | Fri 29/09/23 | 7 days | Fri 22/09/23 | Fri 29/09/23 |  |  | -2 days | 0 days | 2 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.1.3.1 | T3-DB-0058 | SITAG | All Data Services RTTMs submitted to Programme for assurance | 100% | Wed 20/09/23 | Wed 20/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 265FS+29 days | 271FS+7 days | -2 days | -2 days | 0 days | PP | SI Test |  |  | 5.7 | Yes | Lee Cox
7 | 1.3.6.3.1.3.2 | T3-DB-0130 | SITAG | All Data Services RTTMs MHHS Review Completed | 100% | Fri 29/09/23 | Fri 29/09/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 270FS+7 days | 279 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
6 | 1.3.6.3.1.4 |  |  | Test Scenarios | 100% | Wed 20/09/23 | Thu 28/09/23 | 6 days | Fri 22/09/23 | Thu 28/09/23 |  |  | -2 days | 0 days | 2 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.1.4.1 | T3-DB-0056 | SITAG | All Data Services test scenarios' submitted to Programme for assurance | 100% | Wed 20/09/23 | Wed 20/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 | 265FS+29 days | 274FS+6 days,277FS+5 days | -2 days | -2 days | 0 days | PP | SI Test |  |  | 5.7 | Yes | Lee Cox
7 | 1.3.6.3.1.4.2 | T3-DB-0131 | SITAG | All Data Services Test scenarios' MHHS Review Completed | 100% | Thu 28/09/23 | Thu 28/09/23 | 0 days | Thu 28/09/23 | Thu 28/09/23 | 273FS+6 days | 279 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.11 | Yes | Lee Cox
6 | 1.3.6.3.1.5 |  |  | PIT execution | 100% | Mon 11/09/23 | Fri 17/11/23 | 50 days | Mon 31/10/22 | Fri 17/11/23 |  |  | 225 days | 0 days | -225 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.1.5.1 |  |  | PIT Test Execution Progress Report | 100% | Mon 11/09/23 | Fri 03/11/23 | 40 days | Mon 31/10/22 | Fri 27/10/23 | 268 | 278 | 225 days | 5 days | -220 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.3.1.5.2 |  |  | PIT Execution | 100% | Thu 28/09/23 | Fri 03/11/23 | 27 days | Mon 31/10/22 | Fri 03/11/23 | 273FS+5 days | 278 | 238 days | 0 days | -238 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.3.1.5.3 | T3-DB-0132 | SITAG | All Data Services PIT Completion Reports submitted to Programme for assurance | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 276277 | 279FS+10 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.11 | Yes | Lee Cox
7 | 1.3.6.3.1.5.4 | T3-DB-0133 | SITAG | All Data Services PIT Completion Reports MHHS Review Completed | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 266,271,274,278FS+10 days | 695 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.13 | Yes | Lee Cox
5 | 1.3.6.3.2 |  |  | All Metering Services DBT CIT (Entering at Interval 4) | 100% | Fri 25/08/23 | Fri 01/12/23 | 70 days | Mon 31/10/22 | Fri 01/12/23 |  |  | 215 days | 0 days | -215 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.6.3.2.1 |  |  | Test Approach & Plan | 100% | Fri 25/08/23 | Fri 20/10/23 | 40 days | Fri 25/08/23 | Fri 20/10/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.2.1.1 | T3-DB-0040 | SITAG | All Metering Services Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | Fri 25/08/23 | Fri 25/08/23 | 0 days | Fri 25/08/23 | Fri 25/08/23 |  | 283FS+40 days,285FS+10 days,287FS+15 days,290FS+15 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.6 | Yes | Lee Cox
7 | 1.3.6.3.2.1.2 | T3-DB-0134 | SITAG | All Metering Services Test approach and plans MHHS Review Completed | 100% | Fri 20/10/23 | Fri 20/10/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 282FS+40 days | 296 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
6 | 1.3.6.3.2.2 |  |  | Test Readiness Report | 100% | Mon 11/09/23 | Mon 25/09/23 | 11 days | Fri 08/09/23 | Fri 17/11/23 |  |  | 1 day | -39 days | -40 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.2.2.1 |  |  | Test readiness reporting | 100% | Mon 11/09/23 | Mon 25/09/23 | 11 days | Fri 08/09/23 | Fri 17/11/23 | 282FS+10 days | 293 | 1 day | -39 days | -40 days | PP | 109 |  |  | 5 | Yes | Lee Cox
6 | 1.3.6.3.2.3 |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 15/09/23 | Fri 27/10/23 | 30 days | Fri 15/09/23 | Fri 27/10/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.2.3.1 | T3-DB-0048 | SITAG | All Metering Services RTTMs submitted to Programme for assurance | 100% | Fri 15/09/23 | Fri 15/09/23 | 0 days | Fri 15/09/23 | Fri 15/09/23 | 282FS+15 days | 288FS+30 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.3.2.3.2 | T3-DB-0135 | SITAG | All Metering Services MHHS Reviews Completed | 100% | Fri 27/10/23 | Fri 27/10/23 | 0 days | Fri 27/10/23 | Fri 27/10/23 | 287FS+30 days | 296 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.13 | Yes | Lee Cox
6 | 1.3.6.3.2.4 |  |  | Test Scenarios | 100% | Fri 15/09/23 | Fri 27/10/23 | 30 days | Fri 15/09/23 | Fri 27/10/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.2.4.1 | T3-DB-0050 | SITAG | All Metering Services test scenarios' submitted to Programme for assurance | 100% | Fri 15/09/23 | Fri 15/09/23 | 0 days | Fri 15/09/23 | Fri 15/09/23 | 282FS+15 days | 291FS+30 days,294FS+5 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.3.2.4.2 | T3-DB-0136 | SITAG | All Metering Services Test scenarios' MHHS Review Completed | 100% | Fri 27/10/23 | Fri 27/10/23 | 0 days | Fri 27/10/23 | Fri 27/10/23 | 290FS+30 days | 296 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.13 | Yes | Lee Cox
6 | 1.3.6.3.2.5 |  |  | PIT execution | 100% | Mon 25/09/23 | Fri 01/12/23 | 50 days | Mon 31/10/22 | Fri 01/12/23 |  |  | 235 days | 0 days | -235 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.2.5.1 |  |  | PIT Test Execution Progress Report | 100% | Tue 26/09/23 | Fri 17/11/23 | 39 days | Tue 26/09/23 | Fri 17/11/23 | 285 | 295 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.3.2.5.2 |  |  | PIT Execution | 100% | Mon 25/09/23 | Fri 17/11/23 | 40 days | Mon 31/10/22 | Fri 17/11/23 | 290FS+5 days | 295 | 235 days | 0 days | -235 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.3.2.5.3 | T3-DB-0137 | SITAG | All Metering Services PIT Completion Reports submitted to Programme for assurance | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 293294 | 296FS+10 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.13 | Yes | Lee Cox
7 | 1.3.6.3.2.5.4 | T3-DB-0138 | SITAG | All Metering Services PIT Completion Reports MHHS Review Completed | 100% | Fri 01/12/23 | Fri 01/12/23 | 0 days | Fri 01/12/23 | Fri 01/12/23 | 283,288,291,295FS+10 days | 727FS+1 day | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.13 | Yes | Lee Cox
5 | 1.3.6.3.3 |  |  | All SIT Programme Participants PIT (SIT Functional) | 41% | Fri 17/11/23 | Fri 20/09/24 | 221 days | Fri 30/12/22 | Fri 20/09/24 |  |  | 230 days | 0 days | -230 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.6.3.3.1 |  |  | Test Approach & Plans | 100% | Fri 17/11/23 | Thu 11/01/24 | 40 days | Fri 17/11/23 | Thu 11/01/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.2 | Yes | N/A
7 | 1.3.6.3.3.1.1 | T3-DB-0093 | SITAG | SIT Functional PIT Test Approach & Plan (PIT) submitted to Programme for assurance | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 |  | 300FS+40 days,302FS+10 days,304FS+15 days,307FS+15 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.16 | Yes | Lee Cox
7 | 1.3.6.3.3.1.2 | T3-DB-0139 | SITAG | All SIT Functional Test approach and plans MHHS Reviews Completed | 100% | Thu 11/01/24 | Thu 11/01/24 | 0 days | Thu 11/01/24 | Thu 11/01/24 | 299FS+40 days | 313 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
6 | 1.3.6.3.3.2 |  |  | Test Readiness Reports | 100% | Fri 01/12/23 | Fri 15/12/23 | 11 days | Fri 01/12/23 | Fri 09/02/24 |  |  | 0 days | -40 days | -40 days | N/A | N/A |  |  | 5.2 | Yes | N/A
7 | 1.3.6.3.3.2.1 |  |  | Test readiness reporting | 100% | Fri 01/12/23 | Fri 15/12/23 | 11 days | Fri 01/12/23 | Fri 15/12/23 | 299FS+10 days | 310 | 0 days | 0 days | -40 days | PP | 109 |  |  | 5.2 | Yes | Lee Cox
6 | 1.3.6.3.3.3 |  |  | Requirements to test Traceability Matrices (RTTM) | 100% | Thu 07/12/23 | Thu 18/01/24 | 30 days | Thu 07/12/23 | Thu 18/01/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.2 | Yes | N/A
7 | 1.3.6.3.3.3.1 | T3-DB-0091 | SITAG | SIT Functional PIT RTTM submitted to Programme for assurance | 100% | Thu 07/12/23 | Thu 07/12/23 | 0 days | Thu 07/12/23 | Thu 07/12/23 | 299FS+15 days | 305FS+30 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.14 | Yes | Lee Cox
7 | 1.3.6.3.3.3.2 | T3-DB-0140 | SITAG | All SIT Functional RTTMs MHHS Reviews Completed | 100% | Thu 18/01/24 | Thu 18/01/24 | 0 days | Thu 18/01/24 | Thu 18/01/24 | 304FS+30 days | 313 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
6 | 1.3.6.3.3.4 |  |  | Test Scenarios | 100% | Thu 07/12/23 | Thu 18/01/24 | 30 days | Thu 07/12/23 | Thu 18/01/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.2 | Yes | N/A
7 | 1.3.6.3.3.4.1 | T3-DB-0089 | SITAG | SIT Functional PIT test scenarios submitted to Programme for assurance | 100% | Thu 07/12/23 | Thu 07/12/23 | 0 days | Thu 07/12/23 | Thu 07/12/23 | 299FS+15 days | 308FS+30 days,311FS+5 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.14 | Yes | Lee Cox
7 | 1.3.6.3.3.4.2 | T3-DB-0141 | SITAG | All SIT Functional Test scenarios' MHHS Reviews Completed | 100% | Thu 18/01/24 | Thu 18/01/24 | 0 days | Thu 18/01/24 | Thu 18/01/24 | 307FS+30 days | 313 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
6 | 1.3.6.3.3.5 |  |  | PIT execution | 100% | Fri 15/12/23 | Fri 23/02/24 | 51 days | Fri 30/12/22 | Fri 23/02/24 |  |  | 250 days | 0 days | -250 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.3.5.1 |  |  | PIT Test Execution Progress Reports | 100% | Mon 18/12/23 | Fri 09/02/24 | 40 days | Mon 18/12/23 | Fri 09/02/24 | 302 | 312 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.3.3.5.2 |  |  | PIT Execution | 100% | Fri 15/12/23 | Fri 09/02/24 | 41 days | Fri 30/12/22 | Fri 09/02/24 | 307FS+5 days | 312 | 250 days | 1 day | -249 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.3.3.5.3 | T3-DB-0087 | SITAG | All SIT Functional PIT Completion Reports submitted to Programme for Assurance | 100% | Fri 09/02/24 | Fri 09/02/24 | 0 days | Fri 09/02/24 | Fri 09/02/24 | 310311 | 313FS+10 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.19 | Yes | Lee Cox
7 | 1.3.6.3.3.5.4 | T3-DB-0142 | SITAG | All SIT Functional PIT Completion Reports MHHS Review Completed | 100% | Fri 23/02/24 | Fri 23/02/24 | 0 days | Fri 23/02/24 | Fri 23/02/24 | 300,305,308,312FS+10 days | 862 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.19 | Yes | Lee Cox
6 | 1.3.6.3.3.6 |  |  | All SIT Programme Participants PIT (SIT Migration) | 63% | Fri 16/02/24 | Fri 24/05/24 | 71 days | Fri 31/03/23 | Fri 24/05/24 |  |  | 230 days | 0 days | -230 days | N/A | N/A |  |  | 5.1 | Yes | N/A
7 | 1.3.6.3.3.6.1 |  |  | Test Approach & Plans | 0% | Fri 16/02/24 | Thu 11/04/24 | 40 days | Fri 16/02/24 | Thu 11/04/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.2 | Yes | N/A
8 | 1.3.6.3.3.6.1.1 | T3-DB-0143 | SITAG | All SIT Migration PIT Test Approach & Plans submitted to Programme for assurance | 100% | Fri 16/02/24 | Fri 16/02/24 | 0 days | Fri 16/02/24 | Fri 16/02/24 |  | 317FS+40 days,319FS+10 days,321FS+15 days,324FS+15 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
8 | 1.3.6.3.3.6.1.2 | T3-DB-0144 | SITAG | All SIT Migration PIT Test approach and plans MHHS Reviews Completed | 0% | Thu 11/04/24 | Thu 11/04/24 | 0 days | Thu 11/04/24 | Thu 11/04/24 | 316FS+40 days | 330 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.3.3.6.2 |  |  | Test Readiness Reports | 100% | Fri 01/03/24 | Fri 15/03/24 | 11 days | Fri 01/03/24 | Fri 10/05/24 |  |  | 0 days | -40 days | -40 days | N/A | N/A |  |  | 5.2 | Yes | N/A
8 | 1.3.6.3.3.6.2.1 |  |  | Test readiness reporting | 100% | Fri 01/03/24 | Fri 15/03/24 | 11 days | Fri 01/03/24 | Fri 10/05/24 | 316FS+10 days | 327 | 0 days | -40 days | -40 days | PP | 109 |  |  | 5.2 | Yes | Lee Cox
7 | 1.3.6.3.3.6.3 |  |  | Requirements to test Traceability Matrices (RTTM) | 0% | Thu 07/03/24 | Thu 18/04/24 | 30 days | Thu 07/03/24 | Thu 18/04/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.2 | Yes | N/A
8 | 1.3.6.3.3.6.3.1 | T3-DB-0145 | SITAG | All SIT Migration PIT RTTMs submitted to Programme for assurance | 0% | Thu 07/03/24 | Thu 07/03/24 | 0 days | Thu 07/03/24 | Thu 07/03/24 | 316FS+15 days | 322FS+30 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
8 | 1.3.6.3.3.6.3.2 | T3-DB-0146 | SITAG | All SIT Migration RTTMs MHHS Reviews Completed | 0% | Thu 18/04/24 | Thu 18/04/24 | 0 days | Thu 18/04/24 | Thu 18/04/24 | 321FS+30 days | 330 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.3.3.6.4 |  |  | Test Scenarios | 0% | Thu 07/03/24 | Thu 18/04/24 | 30 days | Thu 07/03/24 | Thu 18/04/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.2 | Yes | N/A
8 | 1.3.6.3.3.6.4.1 | T3-DB-0147 | SITAG | All SIT Migration PIT test scenarios submitted to Programme for assurance | 0% | Thu 07/03/24 | Thu 07/03/24 | 0 days | Thu 07/03/24 | Thu 07/03/24 | 316FS+15 days | 325FS+30 days,328FS+5 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
8 | 1.3.6.3.3.6.4.2 | T3-DB-0148 | SITAG | All SIT Migration Test scenarios MHHS Reviews Completed | 0% | Thu 18/04/24 | Thu 18/04/24 | 0 days | Thu 18/04/24 | Thu 18/04/24 | 324FS+30 days | 330 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.3.3.6.5 |  |  | PIT execution | 58% | Fri 15/03/24 | Fri 24/05/24 | 51 days | Fri 31/03/23 | Fri 24/05/24 |  |  | 250 days | 0 days | -250 days | N/A | N/A |  |  | 5.1 | Yes | N/A
8 | 1.3.6.3.3.6.5.1 |  |  | PIT Test Execution Progress Reports | 58% | Mon 18/03/24 | Fri 10/05/24 | 40 days | Mon 18/03/24 | Fri 10/05/24 | 319 | 329 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.1 | Yes | Lee Cox
8 | 1.3.6.3.3.6.5.2 |  |  | PIT Execution | 59% | Fri 15/03/24 | Fri 10/05/24 | 41 days | Fri 31/03/23 | Fri 10/05/24 | 324FS+5 days | 329 | 250 days | 1 day | -249 days | PP | SI Test |  |  | 5.1 | Yes | Lee Cox
8 | 1.3.6.3.3.6.5.3 | T3-DB-0149 | SITAG | All SIT Migration PIT Completion Reports submitted to Programme for assurance | 0% | Fri 10/05/24 | Fri 10/05/24 | 0 days | Fri 10/05/24 | Fri 10/05/24 | 327328 | 330FS+10 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
8 | 1.3.6.3.3.6.5.4 | T3-DB-0150 | SITAG | All SIT Migration PIT Completion Reports MHHS Review Completed | 0% | Fri 24/05/24 | Fri 24/05/24 | 0 days | Fri 24/05/24 | Fri 24/05/24 | 317,322,325,329FS+10 days | 914 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
6 | 1.3.6.3.3.7 |  |  | All SIT Programme Participants PIT (SIT Non Functional) | 0% | Fri 10/05/24 | Fri 16/08/24 | 71 days | Fri 23/06/23 | Fri 16/08/24 |  |  | 230 days | 0 days | -230 days | N/A | N/A |  |  | 5.1 | Yes | N/A
7 | 1.3.6.3.3.7.1 |  |  | Test Approach & Plan | 0% | Fri 10/05/24 | Thu 04/07/24 | 40 days | Fri 10/05/24 | Thu 04/07/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.2 | Yes | N/A
8 | 1.3.6.3.3.7.1.1 | T3-DB-0151 | SITAG | SIT Non-Functional PIT Test Approach & Plan (PIT) submitted to Programme for assurance | 0% | Fri 10/05/24 | Fri 10/05/24 | 0 days | Fri 10/05/24 | Fri 10/05/24 |  | 334FS+40 days,336FS+10 days,338FS+15 days,341FS+15 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
8 | 1.3.6.3.3.7.1.2 | T3-DB-0152 | SITAG | SIT Non-Functional Test approach and plan MHHS Review Completed | 0% | Thu 04/07/24 | Thu 04/07/24 | 0 days | Thu 04/07/24 | Thu 04/07/24 | 333FS+40 days | 347 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.3.3.7.2 |  |  | Test Readiness Report | 0% | Fri 24/05/24 | Fri 07/06/24 | 11 days | Fri 24/05/24 | Fri 02/08/24 |  |  | 0 days | -40 days | -40 days | N/A | N/A |  |  | 5.2 | Yes | N/A
8 | 1.3.6.3.3.7.2.1 |  |  | Test readiness reporting | 0% | Fri 24/05/24 | Fri 07/06/24 | 11 days | Fri 24/05/24 | Fri 02/08/24 | 333FS+10 days | 344 | 0 days | -40 days | -40 days | PP | 109 |  |  | 5.2 | Yes | Lee Cox
7 | 1.3.6.3.3.7.3 |  |  | Requirements to test Traceability Matrix (RTTM) | 0% | Thu 30/05/24 | Thu 11/07/24 | 30 days | Thu 30/05/24 | Thu 11/07/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.2 | Yes | N/A
8 | 1.3.6.3.3.7.3.1 | T3-DB-0153 | SITAG | SIT Non-Functional PIT RTTM submitted to Programme for assurance | 0% | Thu 30/05/24 | Thu 30/05/24 | 0 days | Thu 30/05/24 | Thu 30/05/24 | 333FS+15 days | 339FS+30 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
8 | 1.3.6.3.3.7.3.2 | T3-DB-0154 | SITAG | SIT Non-Functional RTTM MHHS Review Completed | 0% | Thu 11/07/24 | Thu 11/07/24 | 0 days | Thu 11/07/24 | Thu 11/07/24 | 338FS+30 days | 347 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.3.3.7.4 |  |  | Test Scenarios | 0% | Thu 30/05/24 | Thu 11/07/24 | 30 days | Thu 30/05/24 | Thu 11/07/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.2 | Yes | N/A
8 | 1.3.6.3.3.7.4.1 | T3-DB-0155 | SITAG | SIT Non-Functional PIT test scenarios submitted to Programme for assurance | 0% | Thu 30/05/24 | Thu 30/05/24 | 0 days | Thu 30/05/24 | Thu 30/05/24 | 333FS+15 days | 342FS+30 days,345FS+5 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
8 | 1.3.6.3.3.7.4.2 | T3-DB-0156 | SITAG | SIT Non-Functional Test scenarios MHHS Review Completed | 0% | Thu 11/07/24 | Thu 11/07/24 | 0 days | Thu 11/07/24 | Thu 11/07/24 | 341FS+30 days | 347 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.3.3.7.5 |  |  | PIT execution | 0% | Fri 07/06/24 | Fri 16/08/24 | 51 days | Fri 23/06/23 | Fri 16/08/24 |  |  | 250 days | 0 days | -250 days | N/A | N/A |  |  | 5.1 | Yes | N/A
8 | 1.3.6.3.3.7.5.1 |  |  | PIT Test Execution Progress Report | 0% | Mon 10/06/24 | Thu 01/08/24 | 39 days | Mon 10/06/24 | Thu 01/08/24 | 336 | 346 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.1 | Yes | Lee Cox
8 | 1.3.6.3.3.7.5.2 |  |  | PIT Execution | 0% | Fri 07/06/24 | Fri 02/08/24 | 41 days | Fri 23/06/23 | Fri 02/08/24 | 341FS+5 days | 346 | 250 days | 1 day | -249 days | PP | SI Test |  |  | 5.1 | Yes | Lee Cox
8 | 1.3.6.3.3.7.5.3 | T3-DB-0157 | SITAG | SIT Non-Functional PIT Completion Report submitted to Programme for assurance | 0% | Fri 02/08/24 | Fri 02/08/24 | 0 days | Fri 02/08/24 | Fri 02/08/24 | 344345 | 347FS+10 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.1 | Yes | Lee Cox
8 | 1.3.6.3.3.7.5.4 | T3-DB-0158 | SITAG | SIT Non-Functional PIT Completion Report MHHS Review Completed | 0% | Fri 16/08/24 | Fri 16/08/24 | 0 days | Fri 16/08/24 | Fri 16/08/24 | 334,339,342,346FS+10 days | 959 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
6 | 1.3.6.3.3.8 |  |  | All SIT Programme Participants PIT (SIT Operational) | 0% | Fri 14/06/24 | Fri 20/09/24 | 71 days | Fri 28/07/23 | Fri 20/09/24 |  |  | 230 days | 0 days | -230 days | N/A | N/A |  |  | 5.1 | Yes | N/A
7 | 1.3.6.3.3.8.1 |  |  | Test Approach & Plan | 0% | Fri 14/06/24 | Thu 08/08/24 | 40 days | Fri 14/06/24 | Thu 08/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.2 | Yes | N/A
8 | 1.3.6.3.3.8.1.1 | T3-DB-0159 | SITAG | SIT Operational PIT Test Approach & Plan (PIT) submitted to Programme for assurance | 0% | Fri 14/06/24 | Fri 14/06/24 | 0 days | Fri 14/06/24 | Fri 14/06/24 |  | 351FS+40 days,353FS+10 days,355FS+15 days,358FS+15 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
8 | 1.3.6.3.3.8.1.2 | T3-DB-0160 | SITAG | SIT Operational Test approach and plan MHHS Review Completed | 0% | Thu 08/08/24 | Thu 08/08/24 | 0 days | Thu 08/08/24 | Thu 08/08/24 | 350FS+40 days | 364 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.3.3.8.2 |  |  | Test Readiness Report | 0% | Fri 28/06/24 | Fri 12/07/24 | 11 days | Fri 28/06/24 | Fri 06/09/24 |  |  | 0 days | -40 days | -40 days | N/A | N/A |  |  | 5.2 | Yes | N/A
8 | 1.3.6.3.3.8.2.1 |  |  | Test readiness reporting | 0% | Fri 28/06/24 | Fri 12/07/24 | 11 days | Fri 28/06/24 | Fri 06/09/24 | 350FS+10 days | 361 | 0 days | -40 days | -40 days | PP | 109 |  |  | 5.2 | Yes | Lee Cox
7 | 1.3.6.3.3.8.3 |  |  | Requirements to test Traceability Matrix (RTTM) | 0% | Thu 04/07/24 | Thu 15/08/24 | 30 days | Thu 04/07/24 | Thu 15/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.2 | Yes | N/A
8 | 1.3.6.3.3.8.3.1 | T3-DB-0161 | SITAG | SIT Operational PIT RTTM submitted to Programme for assurance | 0% | Thu 04/07/24 | Thu 04/07/24 | 0 days | Thu 04/07/24 | Thu 04/07/24 | 350FS+15 days | 356FS+30 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
8 | 1.3.6.3.3.8.3.2 | T3-DB-0162 | SITAG | SIT Operational RTTM MHHS Review Completed | 0% | Thu 15/08/24 | Thu 15/08/24 | 0 days | Thu 15/08/24 | Thu 15/08/24 | 355FS+30 days | 364 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.3.3.8.4 |  |  | Test Scenarios | 0% | Thu 04/07/24 | Thu 15/08/24 | 30 days | Thu 04/07/24 | Thu 15/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.2 | Yes | N/A
8 | 1.3.6.3.3.8.4.1 | T3-DB-0163 | SITAG | SIT Operational PIT test scenarios submitted to Programme for assurance | 0% | Thu 04/07/24 | Thu 04/07/24 | 0 days | Thu 04/07/24 | Thu 04/07/24 | 350FS+15 days | 359FS+30 days,362FS+5 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
8 | 1.3.6.3.3.8.4.2 | T3-DB-0164 | SITAG | SIT Operational Test scenarios MHHS Review Completed | 0% | Thu 15/08/24 | Thu 15/08/24 | 0 days | Thu 15/08/24 | Thu 15/08/24 | 358FS+30 days | 364 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.3.3.8.5 |  |  | PIT execution | 0% | Fri 12/07/24 | Fri 20/09/24 | 51 days | Fri 28/07/23 | Fri 20/09/24 |  |  | 250 days | 0 days | -250 days | N/A | N/A |  |  | 5.1 | Yes | N/A
8 | 1.3.6.3.3.8.5.1 |  |  | PIT Test Execution Progress Report | 0% | Mon 15/07/24 | Fri 06/09/24 | 40 days | Mon 15/07/24 | Fri 06/09/24 | 353 | 363 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.1 | Yes | Lee Cox
8 | 1.3.6.3.3.8.5.2 |  |  | PIT Execution | 0% | Fri 12/07/24 | Fri 06/09/24 | 41 days | Fri 28/07/23 | Fri 06/09/24 | 358FS+5 days | 363 | 250 days | 1 day | -249 days | PP | SI Test |  |  | 5.1 | Yes | Lee Cox
8 | 1.3.6.3.3.8.5.3 | T3-DB-0165 | SITAG | SIT Operational PIT Completion Report submitted to Programme for assurance | 0% | Fri 06/09/24 | Fri 06/09/24 | 0 days | Fri 06/09/24 | Fri 06/09/24 | 361362 | 364FS+10 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.1 | Yes | Lee Cox
8 | 1.3.6.3.3.8.5.4 | T3-DB-0166 | SITAG | SIT Operational PIT Completion Report MHHS Review Completed | 0% | Fri 20/09/24 | Fri 20/09/24 | 0 days | Fri 20/09/24 | Fri 20/09/24 | 351,356,359,363FS+10 days | 1002 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
5 | 1.3.6.3.4 |  |  | All Suppliers DBT CIT (Entering at Interval 5) | 100% | Fri 15/09/23 | Fri 22/12/23 | 71 days | Mon 31/10/22 | Fri 22/12/23 |  |  | 229 days | 0 days | -229 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.6.3.4.1 |  |  | Test Approach & Plan | 100% | Fri 15/09/23 | Thu 12/10/23 | 20 days | Fri 15/09/23 | Thu 12/10/23 |  |  | -1 day | 0 days | 1 day | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.4.1.1 | T3-DB-0046 | SITAG | All SIT Suppliers Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | Fri 15/09/23 | Fri 15/09/23 | 0 days | Fri 15/09/23 | Fri 15/09/23 |  | 368FS+20 days,370FS+10 days,372FS+16 days,375FS+15 days | -1 day | -1 day | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.3.4.1.2 | T3-DB-0167 | SITAG | All SIT Suppliers Test Approach & Plans MHHS Review Completed | 100% | Thu 12/10/23 | Thu 12/10/23 | 0 days | Thu 12/10/23 | Thu 12/10/23 | 367FS+20 days | 381 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
6 | 1.3.6.3.4.2 |  |  | Test Readiness Report | 100% | Fri 29/09/23 | Fri 13/10/23 | 11 days | Fri 29/09/23 | Fri 08/12/23 |  |  | 0 days | -40 days | -40 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.4.2.1 |  |  | Test readiness reporting | 100% | Fri 29/09/23 | Fri 13/10/23 | 11 days | Fri 29/09/23 | Fri 08/12/23 | 367FS+10 days | 378 | 0 days | -40 days | -40 days | PP | 109 |  |  | 5 | Yes | Lee Cox
6 | 1.3.6.3.4.3 |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Fri 06/10/23 | Fri 03/11/23 | 20 days | Fri 06/10/23 | Fri 03/11/23 |  |  | 1 day | 0 days | -1 day | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.4.3.1 | T3-DB-0064 | SITAG | All SIT Suppliers RTTMs submitted to Programme for assurance | 100% | Fri 06/10/23 | Fri 06/10/23 | 0 days | Fri 06/10/23 | Fri 06/10/23 | 367FS+16 days | 373FS+20 days | 1 day | 0 days | -1 day | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.3.4.3.2 | T3-DB-0168 | SITAG | All SIT Suppliers RTTMs MHHS Review Completed | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 372FS+20 days | 381 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
6 | 1.3.6.3.4.4 |  |  | Test Scenarios | 100% | Thu 05/10/23 | Thu 02/11/23 | 20 days | Thu 05/10/23 | Thu 02/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.4.4.1 | T3-DB-0037 | SITAG | All SIT Suppliers test scenarios' submitted to Programme for assurance | 100% | Thu 05/10/23 | Thu 05/10/23 | 0 days | Thu 05/10/23 | Thu 05/10/23 | 367FS+15 days | 376FS+20 days,378FS+5 days,379FS+5 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.3.4.4.2 | T3-DB-0169 | SITAG | All SIT Suppliers Test scenarios' MHHS Review Completed | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 375FS+20 days | 381 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
6 | 1.3.6.3.4.5 |  |  | PIT execution | 100% | Fri 13/10/23 | Fri 22/12/23 | 51 days | Mon 31/10/22 | Fri 22/12/23 |  |  | 249 days | 0 days | -249 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.4.5.1 |  |  | PIT Test Execution Progress Report | 100% | Mon 16/10/23 | Fri 08/12/23 | 40 days | Mon 16/10/23 | Fri 08/12/23 | 375FS+5 days,370 | 380 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.3.4.5.2 |  |  | PIT Execution | 100% | Fri 13/10/23 | Fri 08/12/23 | 41 days | Mon 31/10/22 | Fri 08/12/23 | 375FS+5 days | 380 | 249 days | 0 days | -249 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.3.4.5.3 | T3-DB-0170 | SITAG | All SIT Suppliers PIT Completion Reports submitted to Programme for assurance | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 379378 | 381FS+10 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.14 | Yes | Lee Cox
7 | 1.3.6.3.4.5.4 | T3-DB-0171 | SITAG | All SIT Suppliers PIT Completion Reports MHHS Review Completed | 100% | Fri 22/12/23 | Fri 22/12/23 | 0 days | Fri 22/12/23 | Fri 22/12/23 | 380FS+10 days,368,373,376 | 759 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
5 | 1.3.6.3.5 |  |  | All LDSO Network Operations DBT CIT (Entering at Interval 5) | 100% | Fri 15/09/23 | Fri 22/12/23 | 71 days | Mon 31/10/22 | Fri 05/01/24 |  |  | 229 days | -10 days | -239 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.6.3.5.1 |  |  | Test Approach & Plan | 100% | Fri 15/09/23 | Fri 22/12/23 | 71 days | Mon 31/10/22 | Fri 05/01/24 |  |  | 229 days | -10 days | -239 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.5.1.1 | T3-DB-0054 | SITAG | All Network Operation Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | Fri 15/09/23 | Fri 15/09/23 | 0 days | Fri 15/09/23 | Fri 15/09/23 |  | 385FS+20 days,387FS+10 days,389FS+15 days,392FS+15 days | 0 days | -1 day | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.3.5.1.2 | T3-DB-0172 | SITAG | All Network Operation Test Approach & Plans MHHS Review Completed | 100% | Thu 12/10/23 | Thu 12/10/23 | 0 days | Thu 12/10/23 | Thu 12/10/23 | 384FS+20 days | 398 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Lee Cox
7 | 1.3.6.3.5.1.3 |  |  | Test Readiness Report | 100% | Fri 29/09/23 | Fri 13/10/23 | 11 days | Fri 11/08/23 | Fri 20/10/23 |  |  | 35 days | -5 days | -40 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.3.6.3.5.1.3.1 |  |  | Test readiness reporting | 100% | Fri 29/09/23 | Fri 13/10/23 | 11 days | Fri 11/08/23 | Fri 20/10/23 | 384FS+10 days | 395 | 35 days | -5 days | -40 days | PP | 109 |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.3.5.1.4 |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Thu 05/10/23 | Thu 02/11/23 | 20 days | Thu 05/10/23 | Thu 02/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.3.6.3.5.1.4.1 | T3-DB-0062 | SITAG | All Network Operation RTTMs submitted to Programme for assurance | 100% | Thu 05/10/23 | Thu 05/10/23 | 0 days | Thu 05/10/23 | Thu 05/10/23 | 384FS+15 days | 390FS+20 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
8 | 1.3.6.3.5.1.4.2 | T3-DB-0173 | SITAG | All Network Operation RTTMs MHHS Review Completed | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 389FS+20 days | 398 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
7 | 1.3.6.3.5.1.5 |  |  | Test Scenarios | 100% | Thu 05/10/23 | Thu 02/11/23 | 20 days | Thu 05/10/23 | Thu 02/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.3.6.3.5.1.5.1 | T3-DB-0011 | SITAG | All Network Operation test scenarios' submitted to Programme for assurance | 100% | Thu 05/10/23 | Thu 05/10/23 | 0 days | Thu 05/10/23 | Thu 05/10/23 | 384FS+15 days | 393FS+20 days,395FS+5 days,396FS+5 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Lee Cox
8 | 1.3.6.3.5.1.5.2 | T3-DB-0174 | SITAG | All Network Operation test scenarios' MHHS Review Completed | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 392FS+20 days | 398 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
7 | 1.3.6.3.5.1.6 |  |  | PIT execution | 100% | Fri 13/10/23 | Fri 22/12/23 | 51 days | Mon 31/10/22 | Fri 05/01/24 |  |  | 249 days | -10 days | -259 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.3.6.3.5.1.6.1 |  |  | PIT Test Execution Progress Report | 100% | Mon 16/10/23 | Fri 08/12/23 | 40 days | Mon 31/10/22 | Fri 29/12/23 | 392FS+5 days,387 | 397 | 250 days | -15 days | -265 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.3.6.3.5.1.6.2 |  |  | PIT Execution | 100% | Fri 13/10/23 | Fri 08/12/23 | 41 days | Mon 31/10/22 | Fri 05/01/24 | 392FS+5 days | 397 | 249 days | -20 days | -269 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.3.6.3.5.1.6.3 | T3-DB-0175 | SITAG | All Network Operation PIT (CIT interval 5) Completion Reports submitted to Programme for assurance | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 396395 | 398FS+10 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.3.6.3.5.1.6.4 | T3-DB-0176 | SITAG | All Network Operation PIT (CIT interval 5) Completion Reports MHHS Review Completed | 100% | Fri 22/12/23 | Fri 22/12/23 | 0 days | Fri 22/12/23 | Fri 22/12/23 | 397FS+10 days,385,390,393 | 759 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.15 | Yes | Lee Cox
5 | 1.3.6.3.6 |  |  | All UMSO DBT CIT (Entering at Interval 6) | 100% | Fri 29/09/23 | Fri 19/01/24 | 81 days | Mon 31/10/22 | Fri 19/01/24 |  |  | 239 days | 0 days | -239 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.6.3.6.1 |  |  | Test Approach & Plan | 100% | Fri 13/10/23 | Thu 09/11/23 | 20 days | Fri 15/09/23 | Thu 09/11/23 |  |  | 20 days | 0 days | -20 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.6.1.1 | T3-DB-0052 | SITAG | All UMSO Test Approach & Plans (PIT) submitted to Programme for assurance | 100% | Fri 13/10/23 | Fri 13/10/23 | 0 days | Fri 15/09/23 | Fri 15/09/23 |  | 402FS+20 days,404FS+10 days,406FS+15 days,409FS+15 days | 20 days | 19 days | 0 days | PP | SI Test |  |  | 5.11 | Yes | Lee Cox
7 | 1.3.6.3.6.1.2 | T3-DB-0177 | SITAG | All UMSO Test Approach & Plans MHHS Review Completed | 100% | Thu 09/11/23 | Thu 09/11/23 | 0 days | Thu 09/11/23 | Thu 09/11/23 | 401FS+20 days | 415 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.1 | Yes | Lee Cox
6 | 1.3.6.3.6.2 |  |  | Test Readiness Report | 100% | Fri 29/09/23 | Fri 13/10/23 | 11 days | Fri 27/10/23 | Fri 10/11/23 |  |  | -20 days | -20 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.6.2.1 |  |  | Test readiness reporting | 100% | Fri 27/10/23 | Fri 10/11/23 | 11 days | Fri 27/10/23 | Fri 10/11/23 | 401FS+10 days | 412 | 0 days | 0 days | 0 days | PP | 109 |  |  | 5 | Yes | Lee Cox
6 | 1.3.6.3.6.3 |  |  | Requirements to test Traceability Matrix (RTTM) | 100% | Thu 05/10/23 | Wed 01/11/23 | 20 days | Thu 02/11/23 | Thu 30/11/23 |  |  | -21 days | -21 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.6.3.1 | T3-DB-0060 | SITAG | All UMSO RTTMs submitted to Programme for assurance | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 401FS+15 days | 407FS+20 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.12 | Yes | Lee Cox
7 | 1.3.6.3.6.3.2 | T3-DB-0178 | SITAG | All UMSO RTTMs MHHS Review Completed | 100% | Thu 30/11/23 | Thu 30/11/23 | 0 days | Thu 30/11/23 | Thu 30/11/23 | 406FS+20 days | 415 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.12 | Yes | Lee Cox
6 | 1.3.6.3.6.4 |  |  | Test Scenarios | 100% | Thu 05/10/23 | Wed 01/11/23 | 20 days | Thu 02/11/23 | Thu 30/11/23 |  |  | -21 days | -21 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.6.4.1 | T3-DB-0025 | SITAG | All UMSO test scenarios' submitted to Programme for assurance | 100% | Thu 02/11/23 | Thu 02/11/23 | 0 days | Thu 02/11/23 | Thu 02/11/23 | 401FS+15 days | 410FS+20 days,412FS+5 days,413FS+5 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.12 | Yes | Lee Cox
7 | 1.3.6.3.6.4.2 | T3-DB-0179 | SITAG | All UMSO Test scenarios' MHHS Review Completed | 100% | Thu 30/11/23 | Thu 30/11/23 | 0 days | Thu 30/11/23 | Thu 30/11/23 | 409FS+20 days | 415 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.1 | Yes | Lee Cox
6 | 1.3.6.3.6.5 |  |  | PIT execution | 100% | Fri 10/11/23 | Fri 19/01/24 | 51 days | Mon 31/10/22 | Fri 19/01/24 |  |  | 269 days | 0 days | -269 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.3.6.3.6.5.1 |  |  | PIT Test Execution Progress Report | 100% | Mon 13/11/23 | Fri 05/01/24 | 40 days | Mon 13/11/23 | Fri 05/01/24 | 409FS+5 days,404 | 414 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.3.6.5.2 |  |  | PIT Execution | 100% | Fri 10/11/23 | Thu 04/01/24 | 40 days | Mon 31/10/22 | Fri 05/01/24 | 409FS+5 days | 414 | 269 days | -1 day | -250 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.3.6.3.6.5.3 | T3-DB-0180 | SITAG | All UMSO PIT (CIT interval 6) Completion Reports submitted to Programme for assurance | 100% | Fri 05/01/24 | Fri 05/01/24 | 0 days | Fri 05/01/24 | Fri 05/01/24 | 413412 | 415FS+10 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.1 | Yes | Lee Cox
7 | 1.3.6.3.6.5.4 | T3-DB-0181 | SITAG | All UMSO PIT (CIT interval 6) Completion Reports MHHS Review Completed | 100% | Fri 19/01/24 | Fri 19/01/24 | 0 days | Fri 19/01/24 | Fri 19/01/24 | 402,407,410,414FS+10 days | 791 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.1 | Yes | Lee Cox
3 | 1.3.7 |  |  | DBT Monitoring and Assurance | 55% | Mon 31/10/22 | Tue 20/01/26 | 842 days | Mon 31/10/22 | Tue 20/01/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.3.7.1 |  |  | Planning and DBT Progress Monitoring of PPs | 55% | Mon 31/10/22 | Mon 30/06/25 | 696 days | Mon 31/10/22 | Mon 30/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.7.1.1 |  |  | Monitor Non-SIT PPs Planning and DBT1 progress (to inform confirmation of Qualification Testing Tranche participants milestones) | 55% | Mon 31/10/22 | Mon 30/06/25 | 696 days | Mon 31/10/22 | Mon 30/06/25 | 164SS |  | 0 days | 0 days | 0 days | Code Bodies | SI Test,PPC |  |  | 5 | Yes | Lee Cox
4 | 1.3.7.2 |  |  | DBT Progress Monitoring of Consequential Change | 41% | Thu 02/02/23 | Tue 20/01/26 | 774 days | Thu 02/02/23 | Tue 20/01/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.7.2.1 |  |  | Monitor & report data cleanse progress | 41% | Thu 02/02/23 | Tue 20/01/26 | 774 days | Thu 02/02/23 | Tue 20/01/26 |  |  | 0 days | 0 days | 0 days | SI Test | PPC |  |  | 5 | Yes | Matthew Breen
4 | 1.3.7.3 |  |  | Design Assurance | 64% | Mon 14/11/22 | Wed 06/08/25 | 713 days | Mon 14/11/22 | Wed 06/08/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.7.3.1 |  |  | Design Assurance Readiness Assessment Preparation | 100% | Tue 28/02/23 | Fri 21/04/23 | 39 days | Tue 28/02/23 | Fri 21/04/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.7.3.1.1 |  |  | Set up FTIG | 100% | Mon 03/04/23 | Fri 21/04/23 | 15 days | Mon 03/04/23 | Fri 21/04/23 |  |  | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.7.3.1.2 |  |  | Produce Draft Questions | 100% | Tue 28/02/23 | Mon 13/03/23 | 10 days | Tue 28/02/23 | Mon 13/03/23 |  | 425,428FS+4 days | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.7.3.1.3 |  |  | Pilot with SRO | 100% | Tue 14/03/23 | Tue 14/03/23 | 1 day | Tue 14/03/23 | Tue 14/03/23 | 424 | 426 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.7.3.1.4 |  |  | Finalise questions | 100% | Wed 15/03/23 | Tue 28/03/23 | 10 days | Wed 15/03/23 | Tue 28/03/23 | 425 | 427 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.7.3.1.5 |  |  | Prepare on-line RA tooling | 100% | Wed 29/03/23 | Tue 11/04/23 | 10 days | Wed 29/03/23 | Tue 11/04/23 | 426 |  | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.7.3.1.6 |  |  | Prepare webinar content | 100% | Mon 20/03/23 | Fri 24/03/23 | 5 days | Mon 20/03/23 | Fri 24/03/23 | 424FS+4 days | 429FS+3 days | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.7.3.1.7 |  |  | Conduct webinar | 100% | Thu 30/03/23 | Thu 30/03/23 | 1 day | Thu 30/03/23 | Thu 30/03/23 | 428FS+3 days |  | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.7.3.2 |  |  | Participant Design Assurance Approach | 100% | Mon 14/11/22 | Wed 11/01/23 | 43 days | Mon 14/11/22 | Wed 11/01/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.7.3.2.1 |  |  | Develop document | 100% | Mon 14/11/22 | Fri 09/12/22 | 20 days | Mon 14/11/22 | Fri 09/12/22 | 48FS+10 days | 432 | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.7.3.2.2 |  |  | Review document | 100% | Mon 12/12/22 | Wed 04/01/23 | 18 days | Mon 12/12/22 | Wed 04/01/23 | 431 | 433FF+5 days | 0 days | 0 days | 0 days | PP | SI Design,IPA |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.7.3.2.3 | T3-DB-0012 | DAG | Participant Design Assurance Approach approved | 100% | Wed 11/01/23 | Wed 11/01/23 | 0 days | Wed 11/01/23 | Wed 11/01/23 | 432FF+5 days |  | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
5 | 1.3.7.3.3 |  |  | Phase 1 - SIT Volunteers (Core Providers) | 100% | Mon 10/04/23 | Fri 27/10/23 | 145 days | Mon 10/04/23 | Fri 27/10/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.7.3.3.1 |  |  | Send on-line questionnaire to core capability providers and current SIT volunteers (from Round 3 consultation) | 100% | Mon 10/04/23 | Mon 10/04/23 | 1 day | Mon 10/04/23 | Mon 10/04/23 |  | 436 | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.7.3.3.2 |  |  | Participants Provide Responses to questionnaires | 100% | Tue 11/04/23 | Mon 01/05/23 | 15 days | Tue 11/04/23 | Mon 01/05/23 | 435 | 437 | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.7.3.3.3 |  |  | Assess on-line responses and provided evidence | 100% | Tue 02/05/23 | Mon 08/05/23 | 5 days | Tue 02/05/23 | Mon 08/05/23 | 436 | 438 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.7.3.3.4 |  |  | Bi-lateral meeting with each responder, to walk and navigate through provided materials | 100% | Tue 09/05/23 | Tue 20/06/23 | 31 days | Tue 09/05/23 | Tue 20/06/23 | 437 | 439FS-10 days | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.7.3.3.5 |  |  | Plan for, create and execute deep dive assurance interviews based on agreed priorities (participants, design areas) | 100% | Wed 07/06/23 | Thu 31/08/23 | 62 days | Wed 07/06/23 | Thu 31/08/23 | 438FS-10 days | 440FS-22 days | 0 days | 0 days | 0 days | SI Design |  |  |  | 5.2 | Yes | Paul Pettitt
6 | 1.3.7.3.3.6 |  |  | SI endorsement of participants’ design – assurance reports | 100% | Wed 02/08/23 | Fri 29/09/23 | 43 days | Wed 02/08/23 | Fri 29/09/23 | 439FS-22 days | 441SS+19 days | 0 days | 0 days | 0 days | SI Design |  |  |  | 5.2 | Yes | Paul Pettitt
6 | 1.3.7.3.3.7 |  |  | Post-assurance review of recommendations take-up by assured participants | 100% | Tue 29/08/23 | Fri 27/10/23 | 44 days | Mon 02/10/23 | Fri 27/10/23 | 440SS+19 days | 442 | -24 days | 0 days | 24 days | SI Design |  |  |  | 5.2 | Yes | Paul Pettitt
6 | 1.3.7.3.3.8 | T2-DB-0100 | DAG | Phase 1 - SIT Volunteers (Core Providers) complete | 100% | Fri 27/10/23 | Fri 27/10/23 | 0 days | Fri 27/10/23 | Fri 27/10/23 | 441 |  | 0 days | 0 days | 0 days | SI Design |  |  |  | 5.11 | Yes | Paul Pettitt
5 | 1.3.7.3.4 |  |  | Phase 2 - SIT all other participants | 100% | Mon 08/05/23 | Wed 22/11/23 | 143 days | Mon 08/05/23 | Wed 22/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.7.3.4.1 |  |  | Send on-line questionnaire to core capability providers and current SIT volunteers (from Round 3 consultation) | 100% | Mon 08/05/23 | Mon 08/05/23 | 1 day | Mon 08/05/23 | Mon 08/05/23 |  | 445 | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.7.3.4.2 |  |  | Participants Provide Responses to questionnaires | 100% | Tue 09/05/23 | Mon 29/05/23 | 15 days | Tue 09/05/23 | Mon 29/05/23 | 444 | 446 | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.7.3.4.3 |  |  | Assess on-line responses and provided evidence | 100% | Tue 30/05/23 | Mon 05/06/23 | 5 days | Tue 30/05/23 | Mon 05/06/23 | 445 | 447 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Paul Pettitt
6 | 1.3.7.3.4.4 |  |  | Bi-lateral meeting with each responder, to walk and navigate through provided materials | 100% | Tue 06/06/23 | Fri 29/09/23 | 84 days | Tue 06/06/23 | Fri 29/09/23 | 446 | 448SS+15 days | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5.2 | Yes | Paul Pettitt
6 | 1.3.7.3.4.5 |  |  | Plan for, create and execute deep dive assurance interviews based on agreed priorities (participants, design areas) | 100% | Tue 27/06/23 | Fri 29/09/23 | 69 days | Tue 27/06/23 | Fri 29/09/23 | 447SS+15 days | 449SS+15 days | 0 days | 0 days | 0 days | SI Design |  |  |  | 5.2 | Yes | Paul Pettitt
6 | 1.3.7.3.4.6 |  |  | SI endorsement of participants’ design – assurance reports | 100% | Tue 18/07/23 | Fri 29/09/23 | 54 days | Tue 18/07/23 | Fri 29/09/23 | 448SS+15 days | 450SS+19 days | 0 days | 0 days | 0 days | SI Design |  |  |  | 5.2 | Yes | Paul Pettitt
6 | 1.3.7.3.4.7 |  |  | Post-assurance review of recommendations take-up by assured participants | 100% | Mon 14/08/23 | Wed 22/11/23 | 73 days | Mon 02/10/23 | Wed 22/11/23 | 449SS+19 days | 451 | -35 days | 0 days | 35 days | SI Design |  |  |  | 5.2 | Yes | Paul Pettitt
6 | 1.3.7.3.4.8 | T2-DB-0200 | DAG | SIT PPs design assurance (excl Migration/Reverse Migration) complete | 100% | Wed 22/11/23 | Wed 22/11/23 | 0 days | Wed 22/11/23 | Wed 22/11/23 | 450 | 453 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5.11 | Yes | Paul Pettitt
5 | 1.3.7.3.5 |  |  | Non-SIT PPs design assurance | 17% | Thu 23/11/23 | Wed 06/08/25 | 445 days | Thu 23/11/23 | Wed 06/08/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.7.3.5.1 |  |  | Non-SIT PPs design assurance (risk-based sample) | 17% | Thu 23/11/23 | Wed 06/08/25 | 445 days | Thu 23/11/23 | Wed 06/08/25 | 451 |  | 0 days | 0 days | 0 days | SI Design | PPC |  |  | 5 | Yes | Paul Pettitt
4 | 1.3.7.4 |  |  | Test Assurance | 50% | Wed 01/02/23 | Mon 30/06/25 | 629 days | Mon 31/10/22 | Mon 30/06/25 |  |  | 67 days | 0 days | -67 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.7.4.1 |  |  | Non-SIT PPs test assurance | 50% | Wed 01/02/23 | Mon 30/06/25 | 629 days | Wed 01/02/23 | Mon 30/06/25 |  |  | 0 days | 0 days | 0 days | Code Bodies | PP,PPC,SI Test |  |  | 5 | Yes | Lee Cox
4 | 1.3.7.5 |  |  | Pre-Qualification Guidance (PIT Guidance) | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.7.5.1 |  |  | Develop document (incl. collaboration with code bodies, as required) | 100% | Mon 31/10/22 | Mon 16/01/23 | 56 days | Mon 31/10/22 | Mon 16/01/23 |  | 458 | 0 days | 0 days | 0 days | SI Test | Code Bodies |  |  | 5 | Yes | Lee Cox
5 | 1.3.7.5.2 |  |  | Review, update and agree Pre-Qualification Guidance internally | 100% | Tue 17/01/23 | Tue 31/01/23 | 11 days | Tue 17/01/23 | Tue 31/01/23 | 457 |  | 0 days | 0 days | 0 days | SRO Function | IPA,SI Test |  |  | 5 | Yes | Lee Cox
4 | 1.3.7.6 |  |  | External Programme Dependency Management | 100% | Thu 03/11/22 | Thu 03/11/22 | 0 days | Thu 03/11/22 | Thu 03/11/22 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.3.7.6.1 |  |  | SLC47 | 100% | Thu 03/11/22 | Thu 03/11/22 | 0 days | Thu 03/11/22 | Thu 03/11/22 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.3.7.6.1.1 |  |  | SLC47 implementation date | 100% | Thu 03/11/22 | Thu 03/11/22 | 0 days | Thu 03/11/22 | Thu 03/11/22 |  |  | 0 days | 0 days | 0 days | Ofgem |  |  |  | 5 | Yes | Lee Cox
2 | 1.4 |  |  | SYSTEMS INTEGRATION TESTING (SIT) | 49% | Mon 31/10/22 | Mon 19/01/26 | 841 days | Mon 31/10/22 | Mon 19/01/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  |  | Yes | N/A
3 | 1.4.1 |  |  | SIT Preparation | 88% | Mon 31/10/22 | Fri 25/10/24 | 520 days | Mon 31/10/22 | Mon 03/03/25 |  |  | 0 days | -91 days | -91 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.4.1.1 |  |  | Test Artefact Development | 99% | Mon 31/10/22 | Wed 21/08/24 | 472 days | Mon 31/10/22 | Wed 21/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.1.1.1 |  |  | Environment Approach & Plan | 99% | Wed 16/11/22 | Wed 21/08/24 | 460 days | Wed 16/11/22 | Wed 21/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.1.1.1.1 | T3-TE-0010 | SITAG | Environment Approach & Plan approved | 100% | Wed 16/11/22 | Wed 16/11/22 | 0 days | Wed 16/11/22 | Wed 16/11/22 |  | 895,1145,467FS+1 day,584 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Simon Berry
6 | 1.4.1.1.1.2 |  |  | Environment Approach & Plan - Work Off | 100% | Thu 17/11/22 | Fri 23/06/23 | 157 days | Thu 17/11/22 | Fri 23/06/23 | 466FS+1 day | 468FS+5 days | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Simon Berry
6 | 1.4.1.1.1.3 | T3-TE-0068 | SITAG | Environment Approach & Plan - Work Off Approved | 100% | Wed 16/08/23 | Wed 16/08/23 | 0 days | Wed 16/08/23 | Wed 16/08/23 | 467FS+5 days |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Simon Berry
6 | 1.4.1.1.1.4 | T3-TE-0090 | SITAG | Environment Approach and Plan - SIT Functional | 100% | Mon 20/11/23 | Mon 20/11/23 | 0 days | Wed 15/11/23 | Wed 15/11/23 |  |  | 3 days | 3 days | 0 days | SI Test | PP |  |  | 5.12 | Yes | Simon Berry
6 | 1.4.1.1.1.5 |  |  | Define Approach to Simulator for Non-SIT LDSO | 100% | Wed 15/11/23 | Wed 15/11/23 | 0 days | Wed 15/11/23 | Wed 15/11/23 |  | 1137FS+13 days | 0 days | -1 day | 0 days | SI Test | PP |  |  | 5.12 | Yes | Simon Berry
6 | 1.4.1.1.1.6 | T3-TE-0091 | SITAG/QAG | Environment Approach and Plan - Non SIT LDSO Testing | 100% | Wed 17/04/24 | Wed 17/04/24 | 0 days | Wed 17/04/24 | Wed 17/04/24 |  | 1282 | 0 days | 0 days | 0 days | SI Test | PP | Approved | Name Change | 5.22 | Yes | Simon Berry
6 | 1.4.1.1.1.7 | T3-TE-0120 | SITAG/QAG | Environment Approach and Plan - S and A Testing | 0% | Wed 17/07/24 | Wed 17/07/24 | 0 days | Wed 17/07/24 | Wed 17/07/24 |  |  | 0 days | 0 days | 0 days | SI Test | PP | Approved | New | 5.22 | Yes | Simon Berry
6 | 1.4.1.1.1.8 | T3-TE-0092 | SITAG | Environment Approach and Plan - SIT Non Functional | 0% | Wed 19/06/24 | Wed 19/06/24 | 0 days | Wed 19/06/24 | Wed 19/06/24 |  |  | 0 days | 0 days | 0 days | SI Test | PP | Approved | Date Change | 5.22 | Yes | Simon Berry
6 | 1.4.1.1.1.9 | T3-TE-0093 | SITAG/QAG | Environment Approach and Plan - Sandbox | 0% | Wed 21/08/24 | Wed 21/08/24 | 0 days | Wed 21/08/24 | Wed 21/08/24 |  |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.21 | Yes | Simon Berry
5 | 1.4.1.1.2 |  |  | Overarching Test Scope (for all stages) | 100% | Mon 31/10/22 | Fri 27/01/23 | 65 days | Mon 31/10/22 | Fri 30/06/23 |  |  | 0 days | -110 days | -110 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.1.1.2.1 |  |  | Overarching Test Scope (excl. Migration/Reverse Migration, NFT and Ops components) | 100% | Mon 31/10/22 | Fri 27/01/23 | 65 days | Mon 31/10/22 | Fri 27/01/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.1.2.1.1 |  |  | Develop document (excl Migration/Reverse Migration, NFT and Ops components) | 100% | Mon 31/10/22 | Fri 13/01/23 | 55 days | Mon 31/10/22 | Fri 13/01/23 | 48 | 478 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.1.2.1.2 |  |  | Review, update & agree document (excl Migration/Reverse Migration, NFT and Ops components) | 100% | Mon 16/01/23 | Fri 27/01/23 | 10 days | Mon 16/01/23 | Fri 27/01/23 | 477 |  | 0 days | 0 days | 0 days | SI Test | IPA,Code Bodies,PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.1.1.2.2 |  |  | Updated Overarching Test Scope (incl. Migration/Reverse Migration, NFT and Ops components) | 0% | Mon 01/05/23 | Fri 30/06/23 | 45 days | Mon 01/05/23 | Fri 30/06/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.21 | No | N/A
7 | 1.4.1.1.2.2.1 |  |  | Develop Migration/Reverse Migration, NFT and Ops components of document | 0% | Mon 01/05/23 | Fri 23/06/23 | 40 days | Mon 01/05/23 | Fri 23/06/23 | 1806 | 481 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5.21 | No | Lee Cox
7 | 1.4.1.1.2.2.2 |  |  | Review, update & agree Migration/Reverse Migration, NFT and Ops components of document | 0% | Mon 26/06/23 | Fri 30/06/23 | 5 days | Mon 26/06/23 | Fri 30/06/23 | 480 |  | 0 days | 0 days | 0 days | SI Test | IPA,Code Bodies,PP |  |  | 5.21 | No | Lee Cox
5 | 1.4.1.1.3 |  |  | Configuration and Release Management Approach & Plan | 100% | Tue 01/11/22 | Fri 16/06/23 | 164 days | Tue 01/11/22 | Fri 16/06/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.1.1.3.1 |  |  | Develop document | 100% | Tue 01/11/22 | Fri 16/06/23 | 69 days | Tue 01/11/22 | Fri 16/06/23 |  | 484 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Simon Berry
6 | 1.4.1.1.3.2 |  |  | Review, update and agree Configuration and Release Management Approach & Plan internally | 100% | Wed 01/02/23 | Fri 28/04/23 | 63 days | Wed 01/02/23 | Fri 28/04/23 | 483 |  | 0 days | 0 days | 0 days | SRO Function | IPA,SI Test |  |  | 5 | Yes | Simon Berry
5 | 1.4.1.1.4 |  |  | Test Data Overarching Approach & Plan | 100% | Mon 14/11/22 | Thu 20/07/23 | 179 days | Mon 14/11/22 | Thu 20/07/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.1.1.4.1 |  |  | Develop document | 100% | Mon 14/11/22 | Fri 09/12/22 | 20 days | Mon 14/11/22 | Fri 09/12/22 |  | 487 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Cesar Lopes
6 | 1.4.1.1.4.2 |  |  | Document review and update | 100% | Mon 12/12/22 | Fri 14/07/23 | 155 days | Mon 12/12/22 | Fri 14/07/23 | 486 | 488FS+3 days | 0 days | 0 days | 0 days | PP | SI Test,IPA |  |  | 5 | Yes | Cesar Lopes
6 | 1.4.1.1.4.3 | T3-TE-0072 | SITAG | Test Data Overarching Approach & Plan approved by TMAG | 100% | Wed 19/07/23 | Wed 19/07/23 | 0 days | Wed 19/07/23 | Wed 19/07/23 | 487FS+3 days | 489543529 | 0 days | 0 days | 0 days | SRO Test | PP,IPA,Code Bodies |  |  | 5 | Yes | Cesar Lopes
6 | 1.4.1.1.4.4 |  |  | Document publication final version | 100% | Thu 20/07/23 | Thu 20/07/23 | 1 day | Thu 20/07/23 | Thu 20/07/23 | 488 |  | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Cesar Lopes
5 | 1.4.1.1.5 |  |  | Interface Code of Connection (dates subject to DIP Service Provider's plan) | 100% | Wed 01/03/23 | Fri 05/05/23 | 48 days | Wed 01/03/23 | Fri 05/05/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.1.1.5.1 |  |  | Develop Interface Code of Connection with DIP Service Provider | 100% | Wed 01/03/23 | Fri 28/04/23 | 43 days | Wed 01/03/23 | Fri 28/04/23 |  | 492FS+5 days | 0 days | 0 days | 0 days | DIP Provider | SI Test |  |  | 5 | Yes | Lee Cox
6 | 1.4.1.1.5.2 |  |  | Interface Code of Connection approved at SDWG | 100% | Fri 05/05/23 | Fri 05/05/23 | 0 days | Fri 05/05/23 | Fri 05/05/23 | 491FS+5 days |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.1.1.6 |  |  | Test Traceability | 98% | Thu 01/06/23 | Wed 17/01/24 | 165 days | Thu 01/06/23 | Wed 17/01/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.1.1.6.1 |  |  | RTM containing Method Statement Implied Requirements into Azure DevOps | 100% | Thu 01/06/23 | Fri 30/06/23 | 22 days | Thu 01/06/23 | Fri 30/06/23 |  | 496497 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
6 | 1.4.1.1.6.2 |  |  | RTM Containing Interface Catalogue Implied Requirements | 100% | Thu 01/06/23 | Fri 07/07/23 | 27 days | Thu 01/06/23 | Fri 07/07/23 |  | 496497 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
6 | 1.4.1.1.6.3 |  |  | SIT CIT Full Traceability & Coverage complete | 100% | Mon 10/07/23 | Wed 20/12/23 | 118 days | Mon 10/07/23 | Fri 08/12/23 | 495494 |  | 0 days | 8 days | 8 days | SI Test |  |  |  | 5 | Yes | Lee Cox
6 | 1.4.1.1.6.4 |  |  | SIT Functional Full Traceability & Coverage complete | 96% | Mon 10/07/23 | Wed 17/01/24 | 138 days | Mon 10/07/23 | Wed 17/01/24 | 495494 | 1555 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
4 | 1.4.1.2 |  |  | Test Tool Development | 100% | Mon 31/10/22 | Mon 23/10/23 | 256 days | Mon 31/10/22 | Fri 30/06/23 |  |  | 0 days | 81 days | 81 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.1.2.1 |  |  | Test Management Tool | 100% | Mon 31/10/22 | Mon 23/10/23 | 256 days | Mon 31/10/22 | Fri 30/06/23 |  |  | 0 days | 81 days | 81 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.1.2.1.1 |  |  | Test Management Tool Implementation | 100% | Mon 31/10/22 | Mon 23/10/23 | 256 days | Mon 31/10/22 | Fri 30/06/23 |  |  | 0 days | 81 days | 81 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.2.1.1.1 |  |  | Requirements identification | 100% | Mon 31/10/22 | Fri 23/12/22 | 40 days | Mon 31/10/22 | Fri 23/12/22 |  | 502FS+5 days,510 | 0 days | 0 days | 0 days | SI DevOps | SI Test |  |  | 5 | Yes | Simon Berry
7 | 1.4.1.2.1.1.2 |  |  | Development | 100% | Mon 02/01/23 | Fri 23/06/23 | 125 days | Mon 02/01/23 | Fri 23/06/23 | 501FS+5 days | 503FF,507SS | 0 days | 0 days | 0 days | SI DevOps | SI Test |  |  | 5 | Yes | Simon Berry
7 | 1.4.1.2.1.1.3 |  |  | Testing | 100% | Mon 02/01/23 | Fri 23/06/23 | 125 days | Mon 02/01/23 | Fri 23/06/23 | 502FF | 504FF,507SS | 0 days | 0 days | 0 days | SI DevOps | SI Test |  |  | 5 | Yes | Simon Berry
7 | 1.4.1.2.1.1.4 |  |  | Accept tool | 100% | Fri 23/06/23 | Fri 23/06/23 | 0 days | Fri 23/06/23 | Fri 23/06/23 | 503FF | 505FS+85 days | 0 days | 0 days | 0 days | SI DevOps | SI Test |  |  | 5 | Yes | Simon Berry
7 | 1.4.1.2.1.1.5 |  |  | Implementation | 100% | Mon 23/10/23 | Mon 23/10/23 | 1 day | Fri 30/06/23 | Fri 30/06/23 | 504FS+85 days |  | 81 days | 81 days | 0 days | SI DevOps | PPC |  |  | 5 | Yes | Simon Berry
6 | 1.4.1.2.1.2 |  |  | Test Management Tool User Guide | 100% | Mon 02/01/23 | Fri 09/06/23 | 115 days | Mon 02/01/23 | Fri 09/06/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.2.1.2.1 |  |  | Develop document | 100% | Mon 02/01/23 | Fri 19/05/23 | 100 days | Mon 02/01/23 | Fri 19/05/23 | 502SS,503SS | 508 | 0 days | 0 days | 0 days | SI DevOps |  |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.2.1.2.2 |  |  | Review, update and agree Test Management Tool User Guide internally | 100% | Mon 22/05/23 | Fri 09/06/23 | 15 days | Mon 22/05/23 | Fri 09/06/23 | 507 |  | 0 days | 0 days | 0 days | SRO Function | SI DevOps,SI Test,IPA,PPC |  |  | 5 | Yes | Lee Cox
6 | 1.4.1.2.1.3 |  |  | Test Management Tool Configuration Guide | 100% | Mon 02/01/23 | Fri 24/03/23 | 60 days | Mon 02/01/23 | Fri 24/03/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.2.1.3.1 |  |  | Develop document | 100% | Mon 02/01/23 | Fri 03/03/23 | 45 days | Mon 02/01/23 | Fri 03/03/23 | 501 | 511 | 0 days | 0 days | 0 days | SI DevOps | SI Test,IPA |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.2.1.3.2 |  |  | Review, update and agree Test Management Tool Configuration Guide internally | 100% | Mon 06/03/23 | Fri 24/03/23 | 15 days | Mon 06/03/23 | Fri 24/03/23 | 510 |  | 0 days | 0 days | 0 days | SRO Function | SI DevOps,SI Test,IPA |  |  | 5 | Yes | Lee Cox
5 | 1.4.1.2.2 |  |  | Test Query Tool | 0% | Mon 31/10/22 | Fri 28/04/23 | 130 days | Mon 31/10/22 | Fri 28/04/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | No | N/A
6 | 1.4.1.2.2.1 |  |  | Test Query Tool Implementation | 0% | Mon 31/10/22 | Fri 28/04/23 | 130 days | Mon 31/10/22 | Fri 28/04/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | No | N/A
7 | 1.4.1.2.2.1.1 |  |  | Requirements identification | 0% | Mon 31/10/22 | Fri 25/11/22 | 20 days | Mon 31/10/22 | Fri 25/11/22 |  | 515 | 0 days | 0 days | 0 days | SI DevOps | SI Test |  |  | 5 | No | Lee Cox
7 | 1.4.1.2.2.1.2 |  |  | Development | 0% | Tue 11/04/23 | Mon 24/04/23 | 10 days | Tue 11/04/23 | Mon 24/04/23 | 514 | 516FF,520SS | 0 days | 0 days | 0 days | SI DevOps | SI Test |  |  | 5 | No | Lee Cox
7 | 1.4.1.2.2.1.3 |  |  | Testing | 0% | Tue 18/04/23 | Mon 24/04/23 | 5 days | Tue 18/04/23 | Mon 24/04/23 | 515FF | 517FF | 0 days | 0 days | 0 days | SI DevOps | SI Test |  |  | 5 | No | Lee Cox
7 | 1.4.1.2.2.1.4 |  |  | Accept tool | 0% | Mon 24/04/23 | Mon 24/04/23 | 0 days | Mon 24/04/23 | Mon 24/04/23 | 516FF | 518FS+3 days | 0 days | 0 days | 0 days | SI DevOps | SI Test |  |  | 5 | No | Lee Cox
7 | 1.4.1.2.2.1.5 |  |  | Implementation | 0% | Fri 28/04/23 | Fri 28/04/23 | 1 day | Fri 28/04/23 | Fri 28/04/23 | 517FS+3 days |  | 0 days | 0 days | 0 days | SI DevOps | PPC |  |  | 5 | No | Lee Cox
6 | 1.4.1.2.2.2 |  |  | Test Query Tool User Guide | 0% | Tue 11/04/23 | Fri 28/04/23 | 14 days | Tue 11/04/23 | Fri 28/04/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | No | N/A
7 | 1.4.1.2.2.2.1 |  |  | Develop document | 0% | Tue 11/04/23 | Mon 24/04/23 | 10 days | Tue 11/04/23 | Mon 24/04/23 | 515SS | 521 | 0 days | 0 days | 0 days | SI DevOps |  |  |  | 5 | No | Lee Cox
7 | 1.4.1.2.2.2.2 |  |  | Review, update and agree Test Query Tool User Guide internally | 0% | Tue 25/04/23 | Fri 28/04/23 | 4 days | Tue 25/04/23 | Fri 28/04/23 | 520 |  | 0 days | 0 days | 0 days | SRO Function | IPA,SI Test |  |  | 5 | No | Lee Cox
4 | 1.4.1.3 |  |  | SIT Participation | 100% | Mon 31/10/22 | Tue 23/05/23 | 147 days | Mon 31/10/22 | Tue 23/05/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.1.3.1 |  |  | PPs decide whether to volunteer to participate in SIT and inform Programme of decision via Round 3 Replan consultation | 100% | Mon 31/10/22 | Tue 31/01/23 | 67 days | Mon 31/10/22 | Tue 31/01/23 | 34FF | 524 | 0 days | 0 days | 0 days | PP | SI Test,PMO |  |  | 5 | Yes | Lee Cox
5 | 1.4.1.3.2 |  |  | Assurance of SIT volunteers' plans (submitted via Round 3 Replan Consultation) | 100% | Wed 01/02/23 | Tue 14/02/23 | 10 days | Wed 01/02/23 | Tue 14/02/23 | 523,34 | 525FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.1.3.3 | T2-TE-0100 | SITAG | SIT Participant Volunteers Identified | 100% | Tue 14/02/23 | Tue 14/02/23 | 0 days | Tue 14/02/23 | Tue 14/02/23 | 524FF |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.1.3.4 |  |  | Engagement with SIT volunteers | 100% | Mon 31/10/22 | Tue 23/05/23 | 147 days | Mon 31/10/22 | Tue 23/05/23 |  | 527 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.1.3.5 | T2-TE-0150 | SITAG | SIT Participants Agreed | 100% | Tue 23/05/23 | Tue 23/05/23 | 0 days | Tue 23/05/23 | Tue 23/05/23 | 526,584FS-74 days | 67SS,1004 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
4 | 1.4.1.4 |  |  | Data Protection Impact Assessment (DPIA) | 100% | Thu 01/06/23 | Fri 14/07/23 | 32 days | Thu 01/06/23 | Fri 14/07/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.1.4.1 |  |  | Conduct DPIA on Overall Test Data Approach | 100% | Thu 01/06/23 | Fri 30/06/23 | 22 days | Thu 01/06/23 | Fri 30/06/23 | 488 | 530549 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Cesar Lopes
5 | 1.4.1.4.2 |  |  | Revise Overarching Test Data Approach & plan for DPIA (if required), including engagement with DWG | 100% | Mon 03/07/23 | Thu 13/07/23 | 9 days | Mon 03/07/23 | Thu 13/07/23 | 529 | 531 | 0 days | 0 days | 0 days | SI Test Data |  |  |  | 5 | Yes | Cesar Lopes
5 | 1.4.1.4.3 |  |  | Review (internal), update and approve revised Overarching Test Data Approach & Plan (if required) | 100% | Fri 14/07/23 | Fri 14/07/23 | 1 day | Fri 14/07/23 | Fri 14/07/23 | 530 | 533 | 0 days | 0 days | 0 days | SI Test Data | PP,IPA |  |  | 5 | Yes | Cesar Lopes
4 | 1.4.1.5 |  |  | Data Sharing Agreements | 100% | Mon 17/07/23 | Thu 14/09/23 | 44 days | Mon 17/07/23 | Thu 14/09/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.5 | Yes | N/A
5 | 1.4.1.5.1 |  |  | Produce Data Sharing Agreement for Industry Review | 100% | Mon 17/07/23 | Fri 04/08/23 | 15 days | Mon 17/07/23 | Fri 04/08/23 | 531 | 534 | 0 days | 0 days | 0 days | SI Test Data | PPC, Elexon |  |  | 5.5 | Yes | Cesar Lopes
5 | 1.4.1.5.2 |  |  | Manage Participant Queries and Contract Agreement Execution | 100% | Mon 07/08/23 | Thu 14/09/23 | 29 days | Mon 07/08/23 | Thu 14/09/23 | 533 | 535 | 0 days | 0 days | 0 days | SI Test Data | PPC, Elexon |  |  | 5.5 | Yes | Cesar Lopes
5 | 1.4.1.5.3 | T3-TE-0086 | SITAG | Data Sharing Agreements Complete | 100% | Thu 14/09/23 | Thu 14/09/23 | 0 days | Thu 14/09/23 | Thu 14/09/23 | 534 | 623 | 0 days | 0 days | 0 days | SI Test Data | PPC, Elexon |  |  | 5.5 | Yes | Cesar Lopes
4 | 1.4.1.6 |  |  | Production Data Cut & Data Obfuscation | 100% | Tue 04/04/23 | Fri 01/09/23 | 109 days | Tue 04/04/23 | Fri 01/09/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.1.6.1 |  |  | SI Data Cut Preparation & Infrastructure | 100% | Tue 04/04/23 | Fri 18/08/23 | 99 days | Tue 04/04/23 | Fri 18/08/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.1.6.1.1 |  |  | SI Data Cut Planning activities (incl. pre-cut and post-cut cleansing and population approach) | 100% | Tue 04/04/23 | Mon 19/06/23 | 55 days | Tue 04/04/23 | Mon 19/06/23 |  | 539 | 0 days | 0 days | 0 days | SI Test Data | SI Test |  |  | 5 | Yes | Cesar Lopes
6 | 1.4.1.6.1.2 |  |  | Set up SI database and transmission structure | 100% | Mon 19/06/23 | Thu 17/08/23 | 44 days | Mon 19/06/23 | Thu 17/08/23 | 538 | 540 | 0 days | 0 days | 0 days | SI Test Data | SI Test |  |  | 5 | Yes | Cesar Lopes
6 | 1.4.1.6.1.3 |  |  | Mechanism for transfer of data in place | 100% | Fri 18/08/23 | Fri 18/08/23 | 1 day | Fri 18/08/23 | Fri 18/08/23 | 539 | 541 | 0 days | 0 days | 0 days | SI Test Data | SI Test |  |  | 5 | Yes | Cesar Lopes
6 | 1.4.1.6.1.4 | T3-TE-0087 | SITAG | SI Data Cut Preparation & Infrastructure Complete | 100% | Fri 18/08/23 | Fri 18/08/23 | 0 days | Fri 18/08/23 | Fri 18/08/23 | 540 | 600605 | 0 days | 0 days | 0 days | SI Test Data | SI Test |  |  | 5.5 | Yes | Cesar Lopes
5 | 1.4.1.6.2 |  |  | Production Data Cut | 100% | Mon 19/06/23 | Fri 01/09/23 | 55 days | Mon 19/06/23 | Fri 01/09/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.1.6.2.1 | T3-TE-0011 | SITAG | Notification of Production Data Cut issued to relevant participants | 100% | Mon 19/06/23 | Mon 19/06/23 | 0 days | Mon 19/06/23 | Mon 19/06/23 | 488 | 544 | 0 days | 0 days | 0 days | SI Test Data | PP |  |  | 5 | Yes | Cesar Lopes
6 | 1.4.1.6.2.2 |  |  | Coordinate relevant participants taking data cut from production systems | 100% | Mon 19/06/23 | Fri 11/08/23 | 40 days | Mon 19/06/23 | Fri 11/08/23 | 543 | 545FS+3 days | 0 days | 0 days | 0 days | SI Test Data | PP |  |  | 5 | Yes | Cesar Lopes
6 | 1.4.1.6.2.3 | T3-TE-0017 | SITAG | Production data cut GONG decision | 100% | Wed 16/08/23 | Wed 16/08/23 | 0 days | Wed 16/08/23 | Wed 16/08/23 | 544FS+3 days | 546FS+2 days | 0 days | 0 days | 0 days | SI Test Data | PP |  |  | 5 | Yes | Cesar Lopes
6 | 1.4.1.6.2.4 |  |  | Relevant participants take data cut from production systems (Saturday 19 August) | 100% | Mon 21/08/23 | Mon 21/08/23 | 1 day | Mon 21/08/23 | Mon 21/08/23 | 545FS+2 days | 547SS,549 | 0 days | 0 days | 0 days | SI Test Data | SI Test |  |  | 5 | Yes | Cesar Lopes
6 | 1.4.1.6.2.5 |  |  | EES transmit request data to SI | 100% | Mon 21/08/23 | Fri 25/08/23 | 5 days | Mon 21/08/23 | Fri 25/08/23 | 546SS | 548 | 0 days | 0 days | 0 days | SI Test Data | SI Test |  |  | 5 | Yes | Cesar Lopes
6 | 1.4.1.6.2.6 |  |  | Check data alignment and integrity of data cut | 100% | Mon 28/08/23 | Fri 01/09/23 | 5 days | Mon 28/08/23 | Fri 01/09/23 | 547 | 621 | 0 days | 0 days | 0 days | SI Test Data | PP |  |  | 5 | Yes | Cesar Lopes
6 | 1.4.1.6.2.7 | T2-TE-0200 | SITAG | Data cut from relevant participants' production systems completed (Saturday 19 August) | 100% | Mon 21/08/23 | Mon 21/08/23 | 0 days | Mon 21/08/23 | Mon 21/08/23 | 546529 | 550 | 0 days | 0 days | 0 days | SI Test Data | PP |  |  | 5 | Yes | Cesar Lopes
6 | 1.4.1.6.2.8 |  |  | Production Data Cut Complete | 100% | Mon 21/08/23 | Mon 21/08/23 | 0 days | Mon 21/08/23 | Mon 21/08/23 | 549 | 1004621596 | 0 days | 0 days | 0 days | SI Test Data | PP |  |  | 5.4 | Yes | Cesar Lopes
4 | 1.4.1.7 |  |  | SIT Stage-Specific Preparation | 83% | Mon 31/10/22 | Fri 25/10/24 | 520 days | Mon 31/10/22 | Mon 03/03/25 |  |  | 0 days | -91 days | -91 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.1.7.1 |  |  | SIT Component Integration Preparation | 98% | Mon 31/10/22 | Fri 19/01/24 | 320 days | Mon 31/10/22 | Mon 22/01/24 |  |  | 0 days | -1 day | -1 day | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.1.7.1.1 |  |  | Test Approach & Plan | 100% | Mon 31/10/22 | Wed 19/07/23 | 188 days | Mon 31/10/22 | Wed 19/07/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.1.1.1 |  |  | Develop document with SITWG | 100% | Mon 31/10/22 | Thu 08/06/23 | 159 days | Mon 31/10/22 | Thu 08/06/23 |  | 563SS+45 days,555 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.1.1.2 |  |  | Industry consultation | 100% | Fri 09/06/23 | Thu 22/06/23 | 10 days | Fri 09/06/23 | Thu 22/06/23 | 554 | 556,559SS | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Lee Cox
7 | 1.4.1.7.1.1.3 |  |  | Artefact review (via TMAG) and updates | 100% | Fri 23/06/23 | Wed 19/07/23 | 19 days | Fri 23/06/23 | Wed 19/07/23 | 555 | 557 | 0 days | 0 days | 0 days | SI Test | PP,IPA,Code Bodies |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.1.1.4 | T3-TE-0012 | SITAG | SIT Component Integration Testing Test Approach & Plan approved | 100% | Wed 19/07/23 | Wed 19/07/23 | 0 days | Wed 19/07/23 | Wed 19/07/23 | 556 | 1007,1008,1009,1010,1011,1012,634FS+40 days | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.1.7.1.2 |  |  | Test Data Approach & Plan | 100% | Fri 09/06/23 | Wed 19/07/23 | 29 days | Fri 09/06/23 | Wed 19/07/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.1.2.1 |  |  | Industry consultation | 100% | Fri 09/06/23 | Thu 22/06/23 | 10 days | Fri 09/06/23 | Thu 22/06/23 | 555SS | 560 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Cesar Lopes
7 | 1.4.1.7.1.2.2 |  |  | Artefact review (via TMAG) and updates | 100% | Fri 23/06/23 | Wed 19/07/23 | 19 days | Fri 23/06/23 | Wed 19/07/23 | 559 | 561 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Cesar Lopes
7 | 1.4.1.7.1.2.3 |  |  | SIT Component Integration Testing Test Data Approach & Plan approved | 100% | Wed 19/07/23 | Wed 19/07/23 | 0 days | Wed 19/07/23 | Wed 19/07/23 | 560 | 6.211e+26 | 0 days | 0 days | 0 days | SI Test | IPA |  |  | 5 | Yes | Cesar Lopes
6 | 1.4.1.7.1.3 |  |  | Test scenarios | 100% | Mon 02/01/23 | Wed 30/08/23 | 173 days | Mon 02/01/23 | Wed 30/08/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.1.3.1 |  |  | Development of test scenarios | 100% | Mon 02/01/23 | Fri 28/04/23 | 0 days | Mon 02/01/23 | Fri 28/04/23 | 554SS+45 days | 564SS+22 days,569 | 0 days | 0 days | -85 days | SI Test | PP, Code Bodies |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.1.3.2 |  |  | Review test scenarios with SIT Working Group | 100% | Wed 01/02/23 | Wed 09/08/23 | 11 days | Wed 01/02/23 | Wed 09/08/23 | 563SS+22 days | 565FS+15 days | 0 days | 0 days | -125 days | SI Test | PP, Code Bodies, IPA |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.1.3.3 | T3-TE-0014 | SITAG | SIT Component Integration Testing Test scenarios approved | 100% | Wed 30/08/23 | Wed 30/08/23 | 0 days | Wed 30/08/23 | Wed 30/08/23 | 564FS+15 days | 1.0071e+23 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.6 | Yes | Lee Cox
6 | 1.4.1.7.1.4 |  |  | Test cases | 100% | Mon 01/05/23 | Fri 08/12/23 | 160 days | Mon 01/05/23 | Fri 08/12/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.6 | Yes | N/A
7 | 1.4.1.7.1.4.1 |  |  | SI Test cases | 100% | Mon 01/05/23 | Fri 08/12/23 | 160 days | Mon 01/05/23 | Fri 08/12/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.6 | Yes | N/A
8 | 1.4.1.7.1.4.1.1 |  |  | Batch 1 (CIT Intervals 1 and 2) | 100% | Mon 01/05/23 | Fri 29/09/23 | 110 days | Mon 01/05/23 | Fri 29/09/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.6 | Yes | N/A
9 | 1.4.1.7.1.4.1.1.1 |  |  | Develop Test cases | 100% | Mon 01/05/23 | Fri 15/09/23 | 100 days | Mon 01/05/23 | Fri 15/09/23 | 563 | 570 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5.6 | Yes | Lee Cox
9 | 1.4.1.7.1.4.1.1.2 |  |  | Review Test cases with SIT Working Group | 100% | Mon 18/09/23 | Thu 28/09/23 | 9 days | Mon 18/09/23 | Thu 28/09/23 | 569 | 571FS+1 day | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5.6 | Yes | Lee Cox
9 | 1.4.1.7.1.4.1.1.3 | T3-TE-0069 | SITAG | SIT Component Integration Testing Test cases Batch 1 (CIT Intervals 1 and 2) approved at ETMAG | 100% | Fri 29/09/23 | Fri 29/09/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 570FS+1 day | 573,632,659FS+18 days | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.6 | Yes | Lee Cox
8 | 1.4.1.7.1.4.1.2 |  |  | Batch 2 (CIT Intervals 3 and 4) | 100% | Mon 02/10/23 | Fri 03/11/23 | 25 days | Mon 02/10/23 | Fri 03/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.6 | Yes | N/A
9 | 1.4.1.7.1.4.1.2.1 |  |  | Develop Test cases | 100% | Mon 02/10/23 | Fri 20/10/23 | 15 days | Mon 02/10/23 | Fri 20/10/23 | 571 | 574 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5.6 | Yes | Lee Cox
9 | 1.4.1.7.1.4.1.2.2 |  |  | Review Test cases with SIT Working Group | 100% | Mon 23/10/23 | Thu 02/11/23 | 9 days | Mon 23/10/23 | Thu 02/11/23 | 573 | 575FS+1 day | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5.6 | Yes | Lee Cox
9 | 1.4.1.7.1.4.1.2.3 | T3-TE-0104 | SITAG | SIT Component Integration Testing Test cases Batch 2 (CIT Intervals 3 and 4) approved at ETMAG | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 574FS+1 day | 577691723 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.11 | Yes | Lee Cox
8 | 1.4.1.7.1.4.1.3 |  |  | Batch 3 (CIT Intervals 5 and 6) | 100% | Fri 03/11/23 | Fri 08/12/23 | 25 days | Fri 03/11/23 | Fri 08/12/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.6 | Yes | N/A
9 | 1.4.1.7.1.4.1.3.1 |  |  | Develop Test cases | 100% | Fri 03/11/23 | Fri 24/11/23 | 15 days | Fri 03/11/23 | Fri 24/11/23 | 575 | 578 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5.6 | Yes | Lee Cox
9 | 1.4.1.7.1.4.1.3.2 |  |  | Review Test cases with SIT Working Group | 100% | Mon 27/11/23 | Thu 07/12/23 | 9 days | Mon 27/11/23 | Thu 07/12/23 | 577 | 579FS+1 day | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5.6 | Yes | Lee Cox
9 | 1.4.1.7.1.4.1.3.3 | T3-TE-0105 | SITAG | SIT Component Integration Testing Test cases Batch 3 (CIT Intervals 5 and 6) approved at ETMAG | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 578FS+1 day | 755787 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
6 | 1.4.1.7.1.5 |  |  | CIT Interval 1 Preparation | 100% | Wed 16/11/22 | Fri 15/12/23 | 283 days | Wed 16/11/22 | Fri 08/12/23 |  |  | 0 days | 5 days | 5 days | N/A | N/A |  |  | 5.6 | Yes | N/A
7 | 1.4.1.7.1.5.1 |  |  | Environments (SIT A) | 100% | Wed 16/11/22 | Wed 25/10/23 | 246 days | Wed 16/11/22 | Mon 16/10/23 |  |  | 0 days | 7 days | 7 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.5.1.1 |  |  | PPs register PKI Officers and request PKI certificates | 100% | Mon 09/10/23 | Fri 13/10/23 | 5 days | Mon 09/10/23 | Fri 13/10/23 |  | 583FS+8 days | 0 days | 0 days | 0 days | PP | DIP Provider |  |  | 5.5 | Yes | Simon Berry
8 | 1.4.1.7.1.5.1.2 | T3-TE-0094 | SITAG | PPs register PKI Officers and request PKI certificates Complete - Interval 1 | 100% | Wed 25/10/23 | Wed 25/10/23 | 0 days | Fri 13/10/23 | Fri 13/10/23 | 582FS+8 days |  | 8 days | 8 days | 0 days | PP | DIP Provider |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.5.1.3 |  |  | PP SIT A environment preparation (incl. security certificates and security compliance) | 100% | Wed 16/11/22 | Fri 13/10/23 | 238 days | Wed 16/11/22 | Fri 01/09/23 | 466 | 586FF,527FS-74 days,585SS | 0 days | 30 days | 30 days | PP | SI Test |  |  | 5.8 | Yes | Simon Berry
8 | 1.4.1.7.1.5.1.4 |  |  | SI coordinate SIT Participants' SIT A environment preparation | 100% | Wed 16/11/22 | Fri 13/10/23 | 238 days | Wed 16/11/22 | Fri 01/09/23 | 584SS |  | 0 days | 30 days | 30 days | SI Test | PP |  |  | 5.8 | Yes | Simon Berry
8 | 1.4.1.7.1.5.1.5 |  |  | PP submit self-declaration of environment preparation complete (incl. security certificates and security compliance) to Programme for assurance | 100% | Fri 13/10/23 | Fri 13/10/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 584FF | 587FF+5 days,588SS | 30 days | 30 days | 0 days | PP | SI Test |  |  | 5.8 | Yes | Simon Berry
8 | 1.4.1.7.1.5.1.6 |  |  | SI assure PPs' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 100% | Mon 16/10/23 | Fri 20/10/23 | 5 days | Mon 04/09/23 | Fri 08/09/23 | 586FF+5 days |  | 30 days | 30 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Simon Berry
8 | 1.4.1.7.1.5.1.7 | T3-TE-0019 | SITAG | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 1 | 100% | Fri 01/09/23 | Fri 01/09/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 586SS | 589,629SF,630SF,636 | 0 days | 0 days | 0 days | PP | PP,IPA |  |  | 5.6 | Yes | Simon Berry
8 | 1.4.1.7.1.5.1.8 |  |  | PP SIT A environment connectivity proving | 100% | Mon 04/09/23 | Fri 15/09/23 | 10 days | Tue 12/09/23 | Mon 09/10/23 | 588 | 590SS,593SS | -6 days | -16 days | -10 days | PP | SI Test |  |  | 5.8 | Yes | Simon Berry
8 | 1.4.1.7.1.5.1.9 |  |  | SI coordinate SIT Participants' SIT A environment connectivity proving | 100% | Mon 04/09/23 | Fri 15/09/23 | 10 days | Tue 12/09/23 | Mon 09/10/23 | 589SS |  | -6 days | -16 days | -10 days | SI Test | PP |  |  | 5.8 | Yes | Simon Berry
8 | 1.4.1.7.1.5.1.10 |  |  | PP deployment of MHHS solution code to SIT A environments | 100% | Mon 25/09/23 | Fri 06/10/23 | 10 days | Tue 26/09/23 | Mon 09/10/23 | 632FF |  | -1 day | -1 day | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
8 | 1.4.1.7.1.5.1.11 |  |  | SI coordinate deployment of MHHS solution code to SIT Participants' SIT A environments | 100% | Mon 25/09/23 | Fri 06/10/23 | 10 days | Tue 26/09/23 | Mon 09/10/23 | 632FF |  | -1 day | -1 day | 0 days | SI Test | PP |  |  | 5 | Yes | Simon Berry
8 | 1.4.1.7.1.5.1.12 |  |  | PP submit evidence of SIT A environment connectivity proving and code deployment completion to Programme for assurance | 100% | Mon 04/09/23 | Fri 13/10/23 | 30 days | Tue 12/09/23 | Mon 09/10/23 | 589SS | 594FF+5 days | -6 days | 4 days | 10 days | PP | SI Test |  |  | 5.8 | Yes | Simon Berry
8 | 1.4.1.7.1.5.1.13 |  |  | SI assurance of SIT Participants' SIT A environment connectivity proving and code deployment completion | 100% | Mon 18/09/23 | Fri 20/10/23 | 25 days | Tue 12/09/23 | Mon 16/10/23 | 593FF+5 days |  | 4 days | 4 days | 0 days | SI Test | PP |  |  | 5.8 | Yes | Simon Berry
7 | 1.4.1.7.1.5.2 |  |  | Test Data - ISD Creation | 100% | Tue 22/08/23 | Fri 01/09/23 | 9 days | Tue 22/08/23 | Fri 01/09/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.5 | Yes | N/A
8 | 1.4.1.7.1.5.2.1 |  |  | Set-up Market Participants and DIP ID Data | 100% | Tue 22/08/23 | Thu 31/08/23 | 8 days | Tue 22/08/23 | Thu 31/08/23 | 550 | 597 | 0 days | 0 days | 0 days | SI Test Data | SI Test, DIP, Helix |  |  | 5.5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.2.2 |  |  | Distribute ISD Data to Participants | 100% | Fri 01/09/23 | Fri 01/09/23 | 1 day | Fri 01/09/23 | Fri 01/09/23 | 596 | 598 | 0 days | 0 days | 0 days | SI Test Data | SI Test, DIP, Helix |  |  | 5.5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.2.3 | T3-TE-0083 | SITAG | Test Data - ISD Creation Complete | 100% | Fri 01/09/23 | Fri 01/09/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 597 | 621 | 0 days | 0 days | 0 days | SI Test Data | SI Test, DIP, Helix |  |  | 5.5 | Yes | Cesar Lopes
7 | 1.4.1.7.1.5.3 |  |  | Test Data - SFTP Onboarding | 100% | Mon 21/08/23 | Fri 24/11/23 | 70 days | Mon 21/08/23 | Fri 24/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.5 | Yes | N/A
8 | 1.4.1.7.1.5.3.1 |  |  | Create Containers and Keys for Participants | 100% | Mon 21/08/23 | Wed 23/08/23 | 3 days | Mon 21/08/23 | Wed 23/08/23 | 541 | 601 | 0 days | 0 days | 0 days | SI Test Data | SI Test |  |  | 5.5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.3.2 |  |  | Share SFTP Access with Participants | 100% | Thu 24/08/23 | Wed 30/08/23 | 5 days | Thu 24/08/23 | Wed 30/08/23 | 600 | 602 | 0 days | 0 days | 0 days | SI Test Data | SI Test, PP |  |  | 5.5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.3.3 |  |  | Test SFTP Connectivity | 100% | Thu 31/08/23 | Wed 06/09/23 | 5 days | Thu 31/08/23 | Wed 06/09/23 | 601 | 603FS+57 days | 0 days | 0 days | 0 days | SI Test Data | SI Test, PP |  |  | 5.5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.3.4 | T3-TE-0084 | SITAG | Test Data - SFTP Onboarding Complete | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 | 602FS+57 days | 1012 | 0 days | 0 days | 0 days | SI Test Data | SI Test, PP |  |  | 5.13 | Yes | Cesar Lopes
7 | 1.4.1.7.1.5.4 |  |  | Test Data - Provide Sample Files | 100% | Mon 21/08/23 | Fri 01/09/23 | 10 days | Mon 21/08/23 | Fri 01/09/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.5 | Yes | N/A
8 | 1.4.1.7.1.5.4.1 |  |  | Generate Sample Files off IF Messages | 100% | Mon 21/08/23 | Wed 30/08/23 | 8 days | Mon 21/08/23 | Wed 30/08/23 | 541 | 606 | 0 days | 0 days | 0 days | SI Test Data | SI Test |  |  | 5.5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.4.2 |  |  | Transmit Sample Files off IF Messages to Participants (More detail needs to be planned for a POC) | 100% | Thu 31/08/23 | Fri 01/09/23 | 2 days | Thu 31/08/23 | Fri 01/09/23 | 605 | 607 | 0 days | 0 days | 0 days | SI Test Data | SI Test |  |  | 5.5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.4.3 | T3-TE-0085 | SITAG | Test Data - Provide Sample Files Complete | 100% | Fri 01/09/23 | Fri 01/09/23 | 0 days | Fri 01/09/23 | Fri 01/09/23 | 606 | 624,609FS+3 days | 0 days | 0 days | 0 days | SI Test Data | SI Test |  |  | 5.5 | Yes | Cesar Lopes
7 | 1.4.1.7.1.5.5 |  |  | Test Data - Detailed SIT Data Load Guidance | 100% | Thu 07/09/23 | Wed 06/12/23 | 65 days | Thu 07/09/23 | Fri 01/12/23 |  |  | 0 days | 3 days | 3 days | N/A | N/A |  |  | 5.5 | Yes | N/A
8 | 1.4.1.7.1.5.5.1 |  |  | Document Guidance | 100% | Thu 07/09/23 | Thu 05/10/23 | 21 days | Thu 07/09/23 | Thu 28/09/23 | 607FS+3 days | 610 | 0 days | 5 days | 5 days | SI Test Data | SI Test |  |  | 5.9 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.5.2 |  |  | Provide Guidance to PPs | 100% | Fri 06/10/23 | Fri 06/10/23 | 1 day | Fri 29/09/23 | Fri 29/09/23 | 609 | 611FS+43 days | 5 days | 5 days | 0 days | SI Test Data | SI Test |  |  | 5.9 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.5.3 | T3-TE-0095 | SITAG | Test Data - Detailed SIT Functional Data Load Guidance Complete | 100% | Wed 06/12/23 | Wed 06/12/23 | 0 days | Fri 01/12/23 | Fri 01/12/23 | 610FS+43 days | 834 | 3 days | 3 days | 0 days | SI Test Data | SI Test |  |  | 5.13 | Yes | Richard Puddephatt
7 | 1.4.1.7.1.5.6 |  |  | Test Data - Population of Data Items for Testing Guidance - Draft | 100% | Thu 17/08/23 | Wed 06/12/23 | 80 days | Thu 17/08/23 | Fri 01/12/23 |  |  | 0 days | 3 days | 3 days | N/A | N/A |  |  | 5.5 | Yes | N/A
8 | 1.4.1.7.1.5.6.1 |  |  | Document Guidance - Draft | 100% | Thu 17/08/23 | Thu 31/08/23 | 11 days | Thu 17/08/23 | Thu 31/08/23 | 801 | 614,617SS | 0 days | 0 days | 0 days | SI Test Data | SI Test |  |  | 5.6 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.6.2 |  |  | Provide Guidance to PPs - Draft | 100% | Fri 01/09/23 | Fri 01/09/23 | 1 day | Fri 01/09/23 | Fri 01/09/23 | 613 | 615FS+68 days | 0 days | 0 days | 0 days | SI Test Data | SI Test |  |  | 5.6 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.6.3 | T3-TE-0096 | SITAG | Test Data - Population of Data Items for Testing Guidance - Draft Complete | 100% | Wed 06/12/23 | Wed 06/12/23 | 0 days | Fri 01/12/23 | Fri 01/12/23 | 614FS+68 days |  | 3 days | 3 days | 0 days | SI Test Data | SI Test |  |  | 5.13 | Yes | Richard Puddephatt
7 | 1.4.1.7.1.5.7 |  |  | Test Data - Population of Data Items for Testing Guidance - Final | 100% | Thu 17/08/23 | Fri 15/12/23 | 87 days | Mon 09/10/23 | Fri 08/12/23 |  |  | -37 days | 5 days | 42 days | N/A | N/A |  |  | 5.5 | Yes | N/A
8 | 1.4.1.7.1.5.7.1 |  |  | Update Document Guidance With PPS Feedback | 100% | Thu 17/08/23 | Thu 07/12/23 | 81 days | Mon 09/10/23 | Thu 07/12/23 | 613SS | 618 | -37 days | 0 days | 37 days | SI Test Data | SI Test |  |  | 5.5 | Yes | Richard Puddephatt
8 | 1.4.1.7.1.5.7.2 |  |  | Provide Final Guidance to PPs | 100% | Fri 08/12/23 | Fri 08/12/23 | 1 day | Fri 08/12/23 | Fri 08/12/23 | 617 | 619FS+5 days | 0 days | 0 days | 0 days | SI Test Data | SI Test |  |  | 5.5 | Yes | Richard Puddephatt
8 | 1.4.1.7.1.5.7.3 | T3-TE-0097 | SITAG | Test Data - Population of Data Items for Testing Guidance - Final Complete | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 618FS+5 days | 834 | 5 days | 5 days | 0 days | SI Test Data | SI Test |  |  | 5.14 | Yes | Richard Puddephatt
7 | 1.4.1.7.1.5.8 |  |  | Test Data (SIT A) Interval 1 | 100% | Mon 04/09/23 | Fri 27/10/23 | 40 days | Mon 04/09/23 | Fri 29/09/23 |  |  | 0 days | 20 days | 20 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.5.8.1 |  |  | Run data allocation | 100% | Mon 04/09/23 | Thu 07/09/23 | 4 days | Mon 04/09/23 | Thu 07/09/23 | 548561550598 | 622 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.8.2 |  |  | Cleanse, anonymise and populate data post cut | 100% | Fri 08/09/23 | Wed 13/09/23 | 4 days | Fri 08/09/23 | Wed 13/09/23 | 621 | 623 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.8.3 |  |  | Transmit data sets to PPs | 100% | Fri 15/09/23 | Tue 19/09/23 | 3 days | Fri 15/09/23 | Fri 15/09/23 | 622535 | 624 | 0 days | 2 days | 2 days | SI Test |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.8.4 |  |  | PP - Load test data to test environments | 100% | Wed 20/09/23 | Thu 28/09/23 | 7 days | Mon 18/09/23 | Fri 22/09/23 | 623607 | 625,648SS | 2 days | 4 days | 2 days | PP |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.8.5 |  |  | PP Check data integrity on test environment | 100% | Fri 29/09/23 | Fri 29/09/23 | 1 day | Mon 25/09/23 | Fri 29/09/23 | 624 | 626FF | 4 days | 0 days | -4 days | PP |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.8.6 |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 29/09/23 | Fri 29/09/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 625FF | 627FS+20 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.5.8.7 | T3-TE-0073 | SITAG | Test Data (SIT A) Interval 1 Complete | 100% | Fri 27/10/23 | Fri 27/10/23 | 0 days | Fri 29/09/23 | Fri 29/09/23 | 626FS+20 days | 636632 | 20 days | 20 days | 0 days | SI Test | PP |  |  | 5.1 | Yes | Cesar Lopes
7 | 1.4.1.7.1.5.9 |  |  | Other Preparation | 100% | Mon 03/07/23 | Fri 01/09/23 | 45 days | Mon 03/07/23 | Fri 01/09/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.5.9.1 |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 03/07/23 | Fri 01/09/23 | 45 days | Mon 03/07/23 | Fri 01/09/23 | 588SF |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.5.9.2 |  |  | Test Management Tool onboarding | 100% | Mon 03/07/23 | Fri 01/09/23 | 45 days | Mon 03/07/23 | Fri 01/09/23 | 588SF | 632636 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.1.5.10 |  |  | SIT Component Integration Test Readiness Report | 100% | Thu 14/09/23 | Mon 23/10/23 | 28 days | Mon 09/10/23 | Fri 20/10/23 |  |  | -18 days | 1 day | 19 days | N/A | N/A |  |  | 5.6 | Yes | N/A
8 | 1.4.1.7.1.5.10.1 |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Fri 20/10/23 | Fri 20/10/23 | 0 days | Mon 09/10/23 | Mon 09/10/23 | 630571627 | 591FF,592FF,636,633SS | 9 days | 9 days | 0 days | PP | SI Test |  |  | 5.6 | Yes | Lee Cox
8 | 1.4.1.7.1.5.10.2 |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Mon 23/10/23 | Mon 23/10/23 | 1 day | Tue 10/10/23 | Mon 16/10/23 | 632SS | 636 | 9 days | 5 days | -4 days | SI Test | PP,IPA |  |  | 5.6 | Yes | Lee Cox
8 | 1.4.1.7.1.5.10.3 |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Thu 14/09/23 | Mon 16/10/23 | 23 days | Tue 10/10/23 | Fri 13/10/23 | 557FS+40 days | 635 | -18 days | 1 day | 19 days | SI Test |  |  |  | 5.6 | Yes | Lee Cox
8 | 1.4.1.7.1.5.10.4 |  |  | Artefact review (via TMAG) and updates | 100% | Tue 17/10/23 | Fri 20/10/23 | 4 days | Mon 16/10/23 | Fri 20/10/23 | 634 | 636FS+1 day | 1 day | 0 days | -1 day | SI Test | PP,IPA |  |  | 5.6 | Yes | Lee Cox
7 | 1.4.1.7.1.5.11 | T2-TE-0250 | SITAG | SIT Component Integration Testing 1 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Fri 27/10/23 | Fri 27/10/23 | 0 days | Mon 23/10/23 | Mon 23/10/23 | 635FS+1 day,632,588,630,627,198,203,192,212,213,633 | 1004FS+5 days,1007SS+1 day | 4 days | 4 days | 0 days | SI Test | PP,IPA |  |  | 5.11 | Yes | Lee Cox
6 | 1.4.1.7.1.6 |  |  | CIT Interval 2 Preparation | 100% | Mon 03/07/23 | Wed 22/11/23 | 103 days | Mon 03/07/23 | Fri 10/11/23 |  |  | 0 days | 8 days | 8 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.1.6.1 |  |  | Environments (SIT A) | 100% | Fri 22/09/23 | Wed 22/11/23 | 43 days | Fri 22/09/23 | Fri 10/11/23 |  |  | 0 days | 8 days | 8 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.6.1.1 | T3-TE-0020 | SITAG | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 2 | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 |  | 656SF,663 | 0 days | 0 days | 0 days | PP | PP,IPA |  |  | 5.6 | Yes | Simon Berry
8 | 1.4.1.7.1.6.1.2 |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | Fri 22/09/23 | Fri 22/09/23 | 0 days | Fri 22/09/23 | Fri 22/09/23 |  | 641 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.6.1.3 |  |  | Internal Connectivity Proving Phase | 100% | Mon 25/09/23 | Fri 06/10/23 | 10 days | Mon 25/09/23 | Fri 06/10/23 | 640 | 642 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.6.1.4 |  |  | Internal Connectivity Proving Phase Complete | 100% | Fri 06/10/23 | Fri 06/10/23 | 0 days | Fri 06/10/23 | Fri 06/10/23 | 641 | 643FS+5 days | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.6.1.5 |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | Mon 16/10/23 | Wed 22/11/23 | 28 days | Mon 16/10/23 | Fri 10/11/23 | 642FS+5 days | 644 | 0 days | 8 days | 8 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.6.1.6 |  |  | DIP Onboarding Complete | 100% | Wed 22/11/23 | Wed 22/11/23 | 0 days | Fri 10/11/23 | Fri 10/11/23 | 643 | 645 | 8 days | 8 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.6.1.7 | T3-TE-0098 | SITAG | PPs Register PKI Officers and request PKI certificates Complete - Interval 2 | 100% | Wed 22/11/23 | Wed 22/11/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 644 |  | 23 days | 23 days | 0 days | PP | DIP Provider |  |  | 5.15 | Yes | Simon Berry
8 | 1.4.1.7.1.6.1.8 |  |  | PP Code Deployment | 100% | Fri 20/10/23 | Fri 20/10/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 |  |  | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
7 | 1.4.1.7.1.6.2 |  |  | Test Data (SIT A) Interval 2 | 100% | Wed 20/09/23 | Fri 17/11/23 | 43 days | Mon 18/09/23 | Fri 20/10/23 |  |  | 2 days | 20 days | 18 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.6.2.1 |  |  | Run data allocation | 100% | Wed 20/09/23 | Thu 28/09/23 | 7 days | Mon 18/09/23 | Fri 22/09/23 | 624SS | 649 | 2 days | 4 days | 2 days | SI Test |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.6.2.2 |  |  | Cleanse and populate data post cut | 100% | Fri 29/09/23 | Mon 02/10/23 | 2 days | Mon 25/09/23 | Fri 29/09/23 | 648 | 650 | 4 days | 1 day | -3 days | SI Test |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.6.2.3 |  |  | Transmit data sets to PPs | 100% | Tue 03/10/23 | Tue 03/10/23 | 1 day | Mon 02/10/23 | Tue 03/10/23 | 649 | 651,680SS | 1 day | 0 days | -1 day | SI Test |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.6.2.4 |  |  | PP - Load test data to test environments | 100% | Wed 04/10/23 | Fri 17/11/23 | 33 days | Wed 04/10/23 | Fri 13/10/23 | 650 | 652FF | 0 days | 25 days | 25 days | PP |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.6.2.5 |  |  | PP Check data integrity on test environment | 100% | Mon 23/10/23 | Fri 17/11/23 | 15 days | Mon 16/10/23 | Fri 20/10/23 | 651FF | 653FF | 5 days | 20 days | 10 days | PP |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.6.2.6 |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 652FF | 654 | 20 days | 20 days | 0 days | PP | SI Test |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.6.2.7 | T3-TE-0074 | SITAG | Test Data (SIT A) Interval 2 Complete | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 653 |  | 20 days | 20 days | 0 days | SI Test | PP |  |  | 5.12 | Yes | Cesar Lopes
7 | 1.4.1.7.1.6.3 |  |  | Other Preparation | 100% | Mon 03/07/23 | Tue 31/10/23 | 87 days | Mon 03/07/23 | Tue 31/10/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.6.3.1 |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 03/07/23 | Fri 22/09/23 | 60 days | Mon 03/07/23 | Fri 22/09/23 | 639SF | 657 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.6.3.2 |  |  | Test Management Tool onboarding | 100% | Mon 25/09/23 | Tue 31/10/23 | 27 days | Mon 25/09/23 | Tue 31/10/23 | 656 | 663 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
7 | 1.4.1.7.1.6.4 |  |  | SIT Component Integration Test Readiness Report | 100% | Mon 02/10/23 | Fri 03/11/23 | 25 days | Mon 02/10/23 | Fri 03/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.6.4.1 |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Wed 25/10/23 | Wed 25/10/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 571FS+18 days | 660 | 3 days | 3 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.6.4.2 |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Thu 26/10/23 | Fri 27/10/23 | 2 days | Mon 23/10/23 | Fri 27/10/23 | 659 | 661FF | 3 days | 0 days | -3 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.6.4.3 |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Mon 02/10/23 | Fri 27/10/23 | 20 days | Mon 02/10/23 | Fri 27/10/23 | 660FF | 662 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.6.4.4 |  |  | Artefact review (via TMAG) and updates | 100% | Mon 30/10/23 | Fri 03/11/23 | 5 days | Mon 30/10/23 | Fri 03/11/23 | 661 | 663FS+1 day | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.1.6.5 | T2-TE-0300 | SITAG | SIT Component Integration Testing 2 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Mon 06/11/23 | Mon 06/11/23 | 0 days | Mon 06/11/23 | Mon 06/11/23 | 657,662FS+1 day,639,261 | 1008SS+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5.11 | Yes | Lee Cox
6 | 1.4.1.7.1.7 |  |  | CIT Interval 3 Preparation | 100% | Tue 03/10/23 | Fri 15/12/23 | 54 days | Mon 17/07/23 | Mon 20/11/23 |  |  | 56 days | 19 days | -37 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.1.7.1 |  |  | PIT Test Completion Report (incl. evidence) | 100% | Fri 13/10/23 | Fri 17/11/23 | 26 days | Fri 13/10/23 | Fri 10/11/23 |  |  | 0 days | 5 days | 5 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.7.1.1 |  |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 100% | Fri 13/10/23 | Fri 27/10/23 | 11 days | Fri 13/10/23 | Fri 13/10/23 |  | 667 | 0 days | 10 days | 10 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.7.1.2 |  |  | Finalise PIT Test Completion Report (incl. evidence) | 100% | Mon 30/10/23 | Fri 03/11/23 | 5 days | Mon 16/10/23 | Fri 03/11/23 | 666 | 668 | 10 days | 0 days | -10 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.7.1.3 | T3-DB-0017 | SITAG | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 3 | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 667,80,96 | 669695 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.11 | Yes | Lee Cox
8 | 1.4.1.7.1.7.1.4 |  |  | PP Final PIT Completion Reports assured by SI | 100% | Mon 06/11/23 | Fri 17/11/23 | 10 days | Mon 06/11/23 | Fri 10/11/23 | 668 |  | 0 days | 5 days | 5 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.1.7.2 |  |  | Environments (SIT A) | 100% | Fri 06/10/23 | Fri 15/12/23 | 51 days | Fri 06/10/23 | Fri 10/11/23 |  |  | 0 days | 25 days | 25 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.7.2.1 |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | Fri 06/10/23 | Fri 06/10/23 | 0 days | Fri 06/10/23 | Fri 06/10/23 |  | 673FS+1 day,672 | 0 days | 0 days | 0 days | PP | PP.SI Test |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.7.2.2 | T3-TE-0021 | SITAG | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 3 | 100% | Fri 06/10/23 | Fri 06/10/23 | 0 days | Fri 06/10/23 | Fri 06/10/23 | 671 | 695 | -1 day | -1 day | 0 days | PP | PP,SI Test |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.7.2.3 |  |  | Internal Connectivity Proving Phase | 100% | Mon 09/10/23 | Fri 20/10/23 | 10 days | Mon 09/10/23 | Fri 20/10/23 | 671FS+1 day | 674 | 0 days | 0 days | 0 days | PP | PP,SI Test |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.7.2.4 |  |  | Internal Connectivity Proving Phase Complete | 100% | Fri 20/10/23 | Fri 20/10/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 673 | 675FS+5 days,678FS+15 days | 0 days | 0 days | 0 days | PP | PP,SI Test |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.7.2.5 |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | Mon 30/10/23 | Fri 15/12/23 | 35 days | Mon 30/10/23 | Fri 10/11/23 | 674FS+5 days | 676 | 0 days | 25 days | 25 days | PP | PP,DIP Provider |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.7.2.6 |  |  | DIP Onboarding Complete | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 10/11/23 | Fri 10/11/23 | 675 | 677FF | 25 days | 25 days | 0 days | PP | PP,DIP Provider |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.7.2.7 | T3-TE-0099 | SITAG | PPs Register PKI Officers and Request PKI certificates Complete - Interval 3 | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 10/11/23 | Fri 10/11/23 | 676FF |  | 25 days | 25 days | 0 days | PP | PP,DIP Provider |  |  | 5.13 | Yes | Simon Berry
8 | 1.4.1.7.1.7.2.8 |  |  | PP Code Deployment | 100% | Fri 10/11/23 | Fri 10/11/23 | 0 days | Fri 10/11/23 | Fri 10/11/23 | 674FS+15 days |  | 0 days | 0 days | 0 days | PP | PP |  |  | 5.1 | Yes | Simon Berry
7 | 1.4.1.7.1.7.3 |  |  | Test Data (SIT A) Interval 3 | 100% | Tue 03/10/23 | Fri 17/11/23 | 34 days | Mon 02/10/23 | Fri 03/11/23 |  |  | 1 day | 10 days | 9 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.7.3.1 |  |  | Run data allocation | 100% | Tue 03/10/23 | Fri 06/10/23 | 4 days | Mon 02/10/23 | Fri 06/10/23 | 650SS | 681 | 1 day | 0 days | -1 day | SI Test |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.7.3.2 |  |  | Cleanse and populate data post cut | 100% | Mon 09/10/23 | Fri 13/10/23 | 5 days | Mon 09/10/23 | Fri 13/10/23 | 680 | 682,712FS+5 days | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.7.3.3 |  |  | Transmit data sets to PPs | 100% | Mon 16/10/23 | Tue 17/10/23 | 2 days | Mon 16/10/23 | Tue 17/10/23 | 681 | 683 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.7.3.4 |  |  | PP - Load test data to test environments | 100% | Wed 18/10/23 | Fri 27/10/23 | 8 days | Wed 18/10/23 | Fri 27/10/23 | 682 | 684 | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.7.3.5 |  |  | PP Check data integrity on test environment | 100% | Mon 30/10/23 | Fri 17/11/23 | 15 days | Mon 30/10/23 | Fri 03/11/23 | 683 | 685FF | 0 days | 10 days | 10 days | PP |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.7.3.6 |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 684FF | 686 | 10 days | 10 days | 0 days | PP | SI Test |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.7.3.7 | T3-TE-0075 | SITAG | Test Data (SIT A) Interval 3 Complete | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 685 | 695 | 10 days | 10 days | 0 days | SI Test | PP |  |  | 5.13 | Yes | Cesar Lopes
7 | 1.4.1.7.1.7.4 |  |  | Other Preparation | 100% | Mon 16/10/23 | Fri 17/11/23 | 25 days | Mon 17/07/23 | Fri 06/10/23 |  |  | 65 days | 30 days | -35 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.7.4.1 |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 16/10/23 | Fri 17/11/23 | 25 days | Mon 17/07/23 | Fri 06/10/23 |  |  | 65 days | 30 days | -35 days | SI Test | PP |  |  | 5 | Yes | Simon Berry
8 | 1.4.1.7.1.7.4.2 |  |  | Test Management Tool onboarding | 100% | Mon 16/10/23 | Fri 17/11/23 | 25 days | Mon 17/07/23 | Fri 06/10/23 |  | 695 | 65 days | 30 days | -35 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
7 | 1.4.1.7.1.7.5 |  |  | SIT Component Integration Test Readiness Report | 100% | Mon 16/10/23 | Fri 17/11/23 | 25 days | Mon 16/10/23 | Fri 17/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.7.5.1 |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 575 | 692FF+5 days,695 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.7.5.2 |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Mon 06/11/23 | Fri 10/11/23 | 5 days | Mon 06/11/23 | Fri 10/11/23 | 691FF+5 days | 693FF | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.7.5.3 |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Mon 16/10/23 | Fri 10/11/23 | 20 days | Mon 16/10/23 | Fri 10/11/23 | 692FF | 694 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.7.5.4 |  |  | Artefact review (via TMAG) and updates | 100% | Mon 13/11/23 | Fri 17/11/23 | 5 days | Mon 13/11/23 | Fri 17/11/23 | 693 | 695FS+1 day | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.1.7.6 | T2-TE-0350 | SITAG | SIT Component Integration Testing 3 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Mon 20/11/23 | Mon 20/11/23 | 0 days | Mon 20/11/23 | Mon 20/11/23 | 694FS+1 day,668,672,691,689,686,279 | 1009SS+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5.12 | Yes | Lee Cox
6 | 1.4.1.7.1.8 |  |  | CIT Interval 4 Preparation | 95% | Mon 16/10/23 | Mon 04/12/23 | 36 days | Mon 16/10/23 | Mon 04/12/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.1.8.1 |  |  | PIT Test Completion Report (incl. evidence) | 100% | Fri 27/10/23 | Fri 24/11/23 | 21 days | Fri 27/10/23 | Fri 24/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.8.1.1 |  |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 100% | Fri 27/10/23 | Fri 27/10/23 | 1 day | Fri 27/10/23 | Fri 27/10/23 |  | 699 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.8.1.2 |  |  | Finalise PIT Test Completion Report (incl. evidence) | 100% | Mon 30/10/23 | Fri 17/11/23 | 15 days | Mon 30/10/23 | Fri 17/11/23 | 698 | 700 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.8.1.3 | T3-DB-0019 | SITAG | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 4 | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 699,80,96 | 701727 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.13 | Yes | Lee Cox
8 | 1.4.1.7.1.8.1.4 |  |  | PP Final PIT Completion Reports assured by SI | 100% | Mon 20/11/23 | Fri 24/11/23 | 5 days | Mon 20/11/23 | Fri 24/11/23 | 700 |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.1.8.2 |  |  | Environments (SIT A) | 100% | Mon 23/10/23 | Fri 24/11/23 | 25 days | Fri 20/10/23 | Fri 24/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.8.2.1 |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | Mon 23/10/23 | Mon 23/10/23 | 0 days | Mon 23/10/23 | Mon 23/10/23 |  | 704 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.8.2.2 | T3-TE-0022 | SITAG | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 4 | 100% | Mon 23/10/23 | Mon 23/10/23 | 0 days | Fri 20/10/23 | Fri 20/10/23 | 703 | 727705 | 0 days | 0 days | 0 days | PP | PP,IPA |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.8.2.3 |  |  | Internal Connectivity Proving Phase | 100% | Mon 23/10/23 | Fri 03/11/23 | 10 days | Mon 23/10/23 | Fri 03/11/23 | 704 | 706 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.8.2.4 |  |  | Internal Connectivity Proving Phase Complete | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 03/11/23 | Fri 03/11/23 | 705 | 707FS+5 days | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.8.2.5 |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | Mon 13/11/23 | Fri 24/11/23 | 10 days | Mon 13/11/23 | Fri 24/11/23 | 706FS+5 days | 708 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.8.2.6 |  |  | DIP Onboarding Complete | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 | 707 | 709 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.8.2.7 | T3-TE-0100 | SITAG | PPs register PKI Officers and Request PKI Certificates Complete - Interval 4 | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 | 708 |  | 0 days | 0 days | 0 days | PP | DIP Provider |  |  | 5.16 | Yes | Simon Berry
8 | 1.4.1.7.1.8.2.8 |  |  | PP Code Deployment | 100% | Fri 17/11/23 | Fri 17/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 |  |  | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
7 | 1.4.1.7.1.8.3 |  |  | Test Data (SIT A) Interval 4 | 100% | Mon 23/10/23 | Fri 01/12/23 | 30 days | Mon 16/10/23 | Fri 17/11/23 |  |  | 5 days | 10 days | 5 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.8.3.1 |  |  | Run data allocation | 100% | Mon 23/10/23 | Fri 27/10/23 | 5 days | Mon 16/10/23 | Fri 20/10/23 | 681FS+5 days | 713 | 5 days | 5 days | 0 days | SI Test |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.8.3.2 |  |  | Cleanse and populate data post cut | 100% | Mon 30/10/23 | Tue 31/10/23 | 2 days | Mon 23/10/23 | Fri 27/10/23 | 712 | 714 | 5 days | 2 days | -3 days | SI Test |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.8.3.3 |  |  | Transmit data sets to PPs | 100% | Wed 01/11/23 | Tue 07/11/23 | 5 days | Mon 30/10/23 | Tue 31/10/23 | 713 | 715,744SS | 2 days | 5 days | 3 days | SI Test |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.8.3.4 |  |  | PP - Load test data to test environments | 100% | Wed 08/11/23 | Tue 14/11/23 | 5 days | Wed 01/11/23 | Fri 10/11/23 | 714 | 716 | 5 days | 2 days | -3 days | PP |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.8.3.5 |  |  | PP Check data integrity on test environment | 100% | Wed 15/11/23 | Fri 01/12/23 | 13 days | Mon 13/11/23 | Fri 17/11/23 | 715 | 717FF | 2 days | 10 days | 8 days | PP |  |  |  | 5 | Yes | Richard Puddephatt
8 | 1.4.1.7.1.8.3.6 |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 01/12/23 | Fri 01/12/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 716FF | 718 | 10 days | 10 days | 0 days | PP | SI Test |  |  | 5 | Yes | Richard Puddephatt
8 | 1.4.1.7.1.8.3.7 | T3-TE-0076 | SITAG | Test Data (SIT A) Interval 4 Complete | 100% | Fri 01/12/23 | Fri 01/12/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 717 | 727 | 10 days | 10 days | 0 days | SI Test | PP |  |  | 5.13 | Yes | Richard Puddephatt
7 | 1.4.1.7.1.8.4 |  |  | Other Preparation | 100% | Mon 30/10/23 | Fri 01/12/23 | 25 days | Mon 30/10/23 | Fri 01/12/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.8.4.1 |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 30/10/23 | Fri 01/12/23 | 25 days | Mon 30/10/23 | Fri 01/12/23 |  |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Simon Berry
8 | 1.4.1.7.1.8.4.2 |  |  | Test Management Tool onboarding | 100% | Mon 30/10/23 | Fri 01/12/23 | 25 days | Mon 30/10/23 | Fri 01/12/23 |  |  | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
7 | 1.4.1.7.1.8.5 |  |  | SIT Component Integration Test Readiness Report | 78% | Mon 16/10/23 | Tue 21/11/23 | 27 days | Mon 30/10/23 | Fri 01/12/23 |  |  | -10 days | -8 days | 2 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.8.5.1 |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Fri 03/11/23 | Fri 03/11/23 | 0 days | Fri 17/11/23 | Fri 17/11/23 | 575 | 724FF+5 days,727 | -10 days | -10 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.8.5.2 |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Mon 06/11/23 | Fri 10/11/23 | 5 days | Mon 20/11/23 | Fri 24/11/23 | 723FF+5 days | 725FF | -10 days | -10 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.8.5.3 |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Mon 16/10/23 | Fri 10/11/23 | 20 days | Mon 30/10/23 | Fri 24/11/23 | 724FF | 726 | -10 days | -10 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.8.5.4 |  |  | Artefact review (via SITAG) and updates | 0% | Mon 13/11/23 | Tue 21/11/23 | 7 days | Mon 27/11/23 | Fri 01/12/23 | 725 | 727FS+2 days | -10 days | -8 days | 2 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.1.8.6 | T2-TE-0400 | SITAG | SIT Component Integration Testing 4 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Mon 04/12/23 | Mon 04/12/23 | 0 days | Mon 04/12/23 | Mon 04/12/23 | 726FS+2 days,700,704,723,718,296FS+1 day | 1010SS+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5.13 | Yes | Lee Cox
6 | 1.4.1.7.1.9 |  |  | CIT Interval 5 Preparation | 82% | Wed 01/11/23 | Fri 12/01/24 | 53 days | Mon 30/10/23 | Fri 12/01/24 |  |  | 2 days | 0 days | -2 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.1.9.1 |  |  | PIT Test Completion Report (incl. evidence) | 100% | Fri 17/11/23 | Fri 15/12/23 | 21 days | Fri 17/11/23 | Fri 15/12/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.9.1.1 |  |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 100% | Fri 17/11/23 | Fri 17/11/23 | 1 day | Fri 17/11/23 | Fri 17/11/23 |  | 731 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.9.1.2 |  |  | Finalise PIT Test Completion Report (incl. evidence) | 100% | Mon 20/11/23 | Fri 08/12/23 | 15 days | Mon 20/11/23 | Fri 08/12/23 | 730 | 732 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.9.1.3 | T3-DB-0021 | SITAG | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 5 | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 731,80,96 | 733759 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.14 | Yes | Lee Cox
8 | 1.4.1.7.1.9.1.4 |  |  | PP Final PIT Completion Reports assured by SI | 100% | Mon 11/12/23 | Fri 15/12/23 | 5 days | Mon 11/12/23 | Fri 15/12/23 | 732 |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.1.9.2 |  |  | Environments (SIT A) | 100% | Fri 10/11/23 | Fri 08/12/23 | 21 days | Fri 10/11/23 | Fri 08/12/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.9.2.1 |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | Fri 10/11/23 | Fri 10/11/23 | 0 days | Fri 10/11/23 | Fri 10/11/23 |  | 737FS+1 day,736 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.9.2.2 | T3-TE-0023 | SITAG | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 5 | 100% | Fri 10/11/23 | Fri 10/11/23 | 0 days | Fri 10/11/23 | Fri 10/11/23 | 735 | 759 | -1 day | -1 day | 0 days | PP | PP,IPA |  |  | 5.6 | Yes | Simon Berry
8 | 1.4.1.7.1.9.2.3 |  |  | Internal Connectivity Proving Phase | 100% | Mon 13/11/23 | Fri 24/11/23 | 10 days | Mon 13/11/23 | Fri 24/11/23 | 735FS+1 day | 738 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.9.2.4 |  |  | Internal Connectivity Proving Phase Complete | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 | 737 | 739 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.9.2.5 |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | Mon 27/11/23 | Fri 08/12/23 | 10 days | Mon 27/11/23 | Fri 08/12/23 | 738 | 740 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.9.2.6 |  |  | DIP Onboarding Complete | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 739 | 741 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.9.2.7 | T3-TE-0101 | SITAG | PPs register PKI Officers and Request PKI Certificates Complete - Interval 5 | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 740 | 742 | 0 days | 0 days | 0 days | PP | DIP Provider |  |  | 5.17 | Yes | Simon Berry
8 | 1.4.1.7.1.9.2.8 |  |  | PP Code Deployment | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 741 |  | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
7 | 1.4.1.7.1.9.3 |  |  | Test Data (SIT A) Interval 5 | 100% | Wed 01/11/23 | Fri 15/12/23 | 33 days | Mon 30/10/23 | Fri 08/12/23 |  |  | 2 days | 5 days | 3 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.9.3.1 |  |  | Run data allocation | 100% | Wed 01/11/23 | Tue 07/11/23 | 5 days | Mon 30/10/23 | Fri 10/11/23 | 714SS | 745 | 2 days | -3 days | -5 days | SI Test |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.9.3.2 |  |  | Cleanse and populate data post cut | 100% | Wed 08/11/23 | Fri 17/11/23 | 8 days | Mon 13/11/23 | Fri 17/11/23 | 744 | 746 | -3 days | 0 days | 3 days | SI Test |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.9.3.3 |  |  | Transmit data sets to PPs | 100% | Mon 20/11/23 | Tue 21/11/23 | 2 days | Mon 20/11/23 | Tue 21/11/23 | 745 | 747,776SS | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Cesar Lopes
8 | 1.4.1.7.1.9.3.4 |  |  | PP - Load test data to test environments | 100% | Wed 22/11/23 | Fri 01/12/23 | 8 days | Wed 22/11/23 | Fri 01/12/23 | 746 | 748 | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | Richard Puddephatt
8 | 1.4.1.7.1.9.3.5 |  |  | PP Check data integrity on test environment | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 08/12/23 | 747 | 749FF | 0 days | 5 days | 5 days | PP |  |  |  | 5 | Yes | Richard Puddephatt
8 | 1.4.1.7.1.9.3.6 |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 748FF | 750 | 5 days | 5 days | 0 days | PP | SI Test |  |  | 5 | Yes | Richard Puddephatt
8 | 1.4.1.7.1.9.3.7 | T3-TE-0077 | SITAG | Test Data (SIT A) Interval 5 Complete | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 749 | 759 | 5 days | 5 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Richard Puddephatt
7 | 1.4.1.7.1.9.4 |  |  | Other Preparation | 100% | Mon 20/11/23 | Fri 12/01/24 | 40 days | Mon 20/11/23 | Fri 12/01/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.9.4.1 |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 20/11/23 | Fri 12/01/24 | 40 days | Mon 20/11/23 | Fri 12/01/24 |  |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Simon Berry
8 | 1.4.1.7.1.9.4.2 |  |  | Test Management Tool onboarding | 100% | Mon 20/11/23 | Mon 08/01/24 | 36 days | Mon 20/11/23 | Mon 08/01/24 |  | 759 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
7 | 1.4.1.7.1.9.5 |  |  | SIT Component Integration Test Readiness Report | 13% | Mon 20/11/23 | Fri 05/01/24 | 35 days | Mon 20/11/23 | Fri 05/01/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.9.5.1 |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 579 | 756FF+5 days,759 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.9.5.2 |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Mon 11/12/23 | Fri 15/12/23 | 5 days | Mon 11/12/23 | Fri 15/12/23 | 755FF+5 days | 757FF | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.9.5.3 |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 0% | Mon 20/11/23 | Fri 15/12/23 | 20 days | Mon 20/11/23 | Fri 15/12/23 | 756FF | 758 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.9.5.4 |  |  | Artefact review (via SITAG) and updates | 0% | Mon 18/12/23 | Fri 05/01/24 | 15 days | Mon 18/12/23 | Fri 05/01/24 | 757 | 759FS+1 day | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.1.9.6 | T2-TE-0450 | SITAG | SIT Component Integration Testing 5 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Mon 08/01/24 | Mon 08/01/24 | 0 days | Mon 08/01/24 | Mon 08/01/24 | 758FS+1 day,732,736,753,755,750,398,381 | 1011SS+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5.15 | Yes | Lee Cox
6 | 1.4.1.7.1.10 |  |  | CIT Interval 6 Preparation | 100% | Mon 20/11/23 | Fri 19/01/24 | 45 days | Mon 20/11/23 | Mon 22/01/24 |  |  | 0 days | -1 day | -1 day | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.1.10.1 |  |  | PIT Test Completion Report (incl. evidence) | 100% | Fri 01/12/23 | Fri 12/01/24 | 31 days | Fri 01/12/23 | Fri 12/01/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.10.1.1 |  |  | Submit draft PIT Test Completion Report (incl. evidence) and submit to Programme for assurance | 100% | Fri 01/12/23 | Fri 01/12/23 | 1 day | Fri 01/12/23 | Fri 01/12/23 |  | 763 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.10.1.2 |  |  | Finalise PIT Test Completion Report (incl. evidence) | 100% | Mon 04/12/23 | Fri 05/01/24 | 25 days | Mon 04/12/23 | Fri 05/01/24 | 762 | 764 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.10.1.3 | T3-DB-0023 | SITAG | PP PIT Completion Report (excl. Migration/Reverse Migration) submitted to Programme for assurance CIT Interval 6 | 100% | Fri 05/01/24 | Fri 05/01/24 | 0 days | Fri 05/01/24 | Fri 05/01/24 | 763,80,96,218,223,226 | 765791 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.19 | Yes | Lee Cox
8 | 1.4.1.7.1.10.1.4 |  |  | PP Final PIT Completion Reports assured by SI | 100% | Mon 08/01/24 | Fri 12/01/24 | 5 days | Mon 08/01/24 | Fri 12/01/24 | 764 |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.19 | Yes | Lee Cox
7 | 1.4.1.7.1.10.2 |  |  | Environments (SIT A) | 100% | Fri 24/11/23 | Fri 05/01/24 | 30 days | Fri 24/11/23 | Fri 05/01/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.10.2.1 |  |  | Programme Participants Ready to Start Connectivity Proving | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 |  | 768 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.10.2.2 | T3-TE-0024 | SITAG | SIT Participants' SIT A environments ready to start connectivity proving CIT Interval 6 | 100% | Fri 24/11/23 | Fri 24/11/23 | 0 days | Fri 24/11/23 | Fri 24/11/23 | 767 | 791,769FS+1 day,771FS+6 days | -1 day | -1 day | 0 days | PP | PP,IPA |  |  | 5.6 | Yes | Simon Berry
8 | 1.4.1.7.1.10.2.3 |  |  | Internal Connectivity Proving Phase | 100% | Mon 27/11/23 | Fri 08/12/23 | 10 days | Mon 27/11/23 | Fri 08/12/23 | 768FS+1 day | 770 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.10.2.4 |  |  | Internal Connectivity Proving Phase Complete | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 769 |  | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.10.2.5 |  |  | DIP Onboarding Activity (1. PKI Officers and Certificates, 2. Set-up Validation, 3. End Point Creation, 4. Controlled Smoke Test ) | 100% | Mon 04/12/23 | Fri 08/12/23 | 5 days | Mon 04/12/23 | Fri 08/12/23 | 768FS+6 days | 772 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.10.2.6 |  |  | DIP Onboarding Complete | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 771 | 773 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
8 | 1.4.1.7.1.10.2.7 | T3-TE-0102 | SITAG | PPs register PKI Officers and Request PKI Certificates Complete - Interval 6 | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 772 |  | 1 day | 0 days | 0 days | PP | DIP Provider |  |  | 5.17 | Yes | Simon Berry
8 | 1.4.1.7.1.10.2.8 |  |  | PP Code Deployment | 100% | Fri 05/01/24 | Fri 05/01/24 | 0 days | Fri 05/01/24 | Fri 05/01/24 |  |  | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Simon Berry
7 | 1.4.1.7.1.10.3 |  |  | Test Data (SIT A) Interval 6 | 100% | Mon 20/11/23 | Fri 22/12/23 | 25 days | Mon 20/11/23 | Fri 22/12/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.10.3.1 |  |  | Run data allocation | 100% | Mon 20/11/23 | Fri 01/12/23 | 10 days | Mon 20/11/23 | Fri 24/11/23 | 746SS | 777 | 0 days | 5 days | 5 days | SI Test |  |  |  | 5 | Yes | Richard Puddephatt
8 | 1.4.1.7.1.10.3.2 |  |  | Cleanse and populate data post cut | 100% | Mon 04/12/23 | Mon 04/12/23 | 1 day | Mon 27/11/23 | Fri 01/12/23 | 776 | 778 | 5 days | 1 day | -4 days | SI Test |  |  |  | 5 | Yes | Richard Puddephatt
8 | 1.4.1.7.1.10.3.3 |  |  | Transmit data sets to PPs | 100% | Tue 05/12/23 | Tue 05/12/23 | 1 day | Mon 04/12/23 | Tue 05/12/23 | 777 | 779 | 1 day | 0 days | -1 day | SI Test |  |  |  | 5 | Yes | Richard Puddephatt
8 | 1.4.1.7.1.10.3.4 |  |  | PP - Load test data to test environments | 100% | Wed 06/12/23 | Fri 15/12/23 | 8 days | Wed 06/12/23 | Fri 15/12/23 | 778 | 780 | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | Richard Puddephatt
8 | 1.4.1.7.1.10.3.5 |  |  | PP Check data integrity on test environment | 100% | Mon 18/12/23 | Fri 22/12/23 | 5 days | Mon 18/12/23 | Fri 22/12/23 | 779 | 781FF | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | Richard Puddephatt
8 | 1.4.1.7.1.10.3.6 |  |  | PP submit self-declaration to Programme to confirm loading & verification of test data | 100% | Fri 22/12/23 | Fri 22/12/23 | 0 days | Fri 22/12/23 | Fri 22/12/23 | 780FF | 782 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Richard Puddephatt
8 | 1.4.1.7.1.10.3.7 | T3-TE-0078 | SITAG | Test Data (SIT A) Interval 6 Complete | 100% | Fri 22/12/23 | Fri 22/12/23 | 0 days | Fri 22/12/23 | Fri 22/12/23 | 781 | 791 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.5 | Yes | Richard Puddephatt
7 | 1.4.1.7.1.10.4 |  |  | Other Preparation | 100% | Mon 04/12/23 | Mon 15/01/24 | 31 days | Mon 04/12/23 | Mon 15/01/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.10.4.1 |  |  | Onboarding of Test Participants to Test Management Tool (Azure DevOps) | 100% | Mon 04/12/23 | Mon 15/01/24 | 31 days | Mon 04/12/23 | Mon 15/01/24 |  |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Simon Berry
8 | 1.4.1.7.1.10.4.2 |  |  | Test Management Tool onboarding | 100% | Mon 04/12/23 | Mon 15/01/24 | 31 days | Mon 04/12/23 | Mon 15/01/24 |  | 791 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
7 | 1.4.1.7.1.10.5 |  |  | SIT Component Integration Test Readiness Report | 100% | Mon 20/11/23 | Fri 22/12/23 | 25 days | Mon 18/12/23 | Fri 19/01/24 |  |  | -20 days | -20 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.1.10.5.1 |  |  | PP submit Test Readiness Report to Programme for assurance | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 05/01/24 | Fri 05/01/24 | 579 | 788FF+5 days,791 | -20 days | -20 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.10.5.2 |  |  | SI assure Test Participants' Test Readiness Reports | 100% | Mon 11/12/23 | Fri 15/12/23 | 5 days | Mon 08/01/24 | Fri 12/01/24 | 787FF+5 days | 789FF | -20 days | -20 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.10.5.3 |  |  | SI develop Overarching SIT Component Integration Test Readiness Report | 100% | Mon 20/11/23 | Fri 15/12/23 | 20 days | Mon 18/12/23 | Fri 12/01/24 | 788FF | 790 | -20 days | -20 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.1.10.5.4 |  |  | Artefact review (via TMAG) and updates | 100% | Mon 18/12/23 | Fri 22/12/23 | 5 days | Mon 15/01/24 | Fri 19/01/24 | 789 | 791FS+1 day | -20 days | -20 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.1.10.6 | T2-TE-0500 | SITAG | SIT Component Integration Testing 6 Preparation Complete (incl. approval of SI SIT Component Integration Test Readiness Report) | 100% | Fri 19/01/24 | Fri 19/01/24 | 0 days | Mon 22/01/24 | Mon 22/01/24 | 790FS+1 day,764,768,785,787,782,244,415 | 1012 | -1 day | -1 day | 0 days | SI Test | PP,IPA |  |  | 5.15 | Yes | Lee Cox
5 | 1.4.1.7.2 |  |  | SIT Functional Preparation | 88% | Mon 31/10/22 | Fri 25/10/24 | 520 days | Mon 31/10/22 | Fri 25/10/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.1.7.2.1 |  |  | Test Approach & Plan | 100% | Mon 31/10/22 | Wed 16/08/23 | 208 days | Mon 31/10/22 | Wed 16/08/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.2.1.1 |  |  | Develop document with SITWG | 100% | Mon 31/10/22 | Thu 06/07/23 | 179 days | Mon 31/10/22 | Thu 06/07/23 |  | 803SS+45 days,795 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.2.1.2 |  |  | Industry Consultation | 100% | Fri 07/07/23 | Thu 20/07/23 | 10 days | Fri 07/07/23 | Thu 20/07/23 | 794 | 796,799SS | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes
7 | 1.4.1.7.2.1.3 |  |  | Artefact review (via TMAG) and updates | 100% | Fri 21/07/23 | Wed 16/08/23 | 19 days | Fri 21/07/23 | Wed 16/08/23 | 795 |  | 0 days | 0 days | 0 days | SI Test | PP,IPA,Code Bodies |  |  | 5.5 | Yes | Lee Cox
7 | 1.4.1.7.2.1.4 | T3-TE-0013 | SITAG | SIT Functional Testing Test Approach & Plan approved | 100% | Wed 16/08/23 | Wed 16/08/23 | 0 days | Wed 16/08/23 | Wed 16/08/23 |  | 862,959,1022,1316FS-1 day | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.1.7.2.2 |  |  | Test Data Approach & Plan | 100% | Fri 07/07/23 | Wed 16/08/23 | 29 days | Fri 07/07/23 | Wed 16/08/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.2.2.1 |  |  | Industry Consultation | 100% | Fri 07/07/23 | Thu 20/07/23 | 10 days | Fri 07/07/23 | Thu 20/07/23 | 795SS | 800 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Cesar Lopes
7 | 1.4.1.7.2.2.2 |  |  | Artefact review (via TMAG) and updates | 100% | Fri 21/07/23 | Wed 16/08/23 | 19 days | Fri 21/07/23 | Wed 16/08/23 | 799 | 801 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5.5 | Yes | Cesar Lopes
7 | 1.4.1.7.2.2.3 |  |  | SIT Functional Testing Test Data Approach & Plan approved | 100% | Wed 16/08/23 | Wed 16/08/23 | 0 days | Wed 16/08/23 | Wed 16/08/23 | 800 | 613 | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5.5 | Yes | Cesar Lopes
6 | 1.4.1.7.2.3 |  |  | Test scenarios | 100% | Mon 02/01/23 | Wed 21/02/24 | 298 days | Mon 02/01/23 | Wed 21/02/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.2.3.1 |  |  | Development of test scenarios | 100% | Mon 02/01/23 | Fri 28/04/23 | 85 days | Mon 02/01/23 | Fri 28/04/23 | 794SS+45 days | 804FS+78 days,810,1555 | 0 days | 0 days | 0 days | SI Test | PP, Code Bodies |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.2.3.2 |  |  | Review test scenarios with SIT Working Group | 100% | Thu 17/08/23 | Wed 15/11/23 | 65 days | Thu 17/08/23 | Wed 15/11/23 | 803FS+78 days | 805FS+17 days | 0 days | 0 days | 0 days | SI Test | PP, Code Bodies, IPA |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.2.3.3 | T3-TE-0015 | SITAG | SIT Functional Testing Test scenarios (themes 1-5) approved | 100% | Fri 08/12/23 | Fri 08/12/23 | 0 days | Fri 08/12/23 | Fri 08/12/23 | 804FS+17 days | 862,1022,806FS+28 days | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
7 | 1.4.1.7.2.3.4 | T3-TE-0106 | SITAG | SIT Functional Testing Test scenarios (themes 6,7,9) approved | 100% | Wed 17/01/24 | Wed 17/01/24 | 0 days | Wed 17/01/24 | Wed 17/01/24 | 805FS+28 days | 807FS+25 days,1022 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.16 | Yes | Lee Cox
7 | 1.4.1.7.2.3.5 | T3-TE-0107 | SITAG | SIT Functional Testing Test scenarios (theme 8) approved | 100% | Wed 21/02/24 | Wed 21/02/24 | 0 days | Wed 21/02/24 | Wed 21/02/24 | 806FS+25 days | 1022 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
6 | 1.4.1.7.2.4 |  |  | Test cases | 100% | Mon 01/05/23 | Wed 21/02/24 | 213 days | Mon 01/05/23 | Wed 21/02/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.2.4.1 |  |  | SI Test cases | 100% | Mon 01/05/23 | Wed 21/02/24 | 213 days | Mon 01/05/23 | Wed 21/02/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.2.4.1.1 |  |  | Development of Test cases | 100% | Mon 01/05/23 | Fri 24/11/23 | 150 days | Mon 01/05/23 | Fri 24/11/23 | 803 | 811SS+105 days,1555 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.2.4.1.2 |  |  | Review Test cases with SIT Working Group | 100% | Mon 25/09/23 | Wed 10/01/24 | 78 days | Mon 25/09/23 | Wed 10/01/24 | 810SS+105 days | 812FS+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.2.4.1.3 | T3-TE-0070 | SITAG | SIT Functional Testing Test Cases (themes 1-5) approved | 100% | Wed 17/01/24 | Wed 17/01/24 | 0 days | Wed 17/01/24 | Wed 17/01/24 | 811FS+5 days | 862813 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
8 | 1.4.1.7.2.4.1.4 | T3-TE-0108 | SITAG | SIT Functional Testing Test cases (themes 6,7,9) approved | 100% | Wed 17/01/24 | Wed 17/01/24 | 0 days | Wed 17/01/24 | Wed 17/01/24 | 812 | 814FS+25 days | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
8 | 1.4.1.7.2.4.1.5 | T3-TE-0109 | SITAG | SIT Functional Testing Test cases (theme 8) approved | 100% | Wed 21/02/24 | Wed 21/02/24 | 0 days | Wed 21/02/24 | Wed 21/02/24 | 813FS+25 days | 1022 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
6 | 1.4.1.7.2.5 |  |  | Environments (SIT-Staging) | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Wed 16/11/22 | Fri 09/02/24 |  |  | 273 days | -40 days | -313 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.2.5.1 |  |  | SIT Functional pre-requisites | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.3 | Yes | N/A
8 | 1.4.1.7.2.5.1.1 |  |  | DCC | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.3 | Yes | N/A
9 | 1.4.1.7.2.5.1.1.1 |  |  | CSS | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.3 | Yes | N/A
10 | 1.4.1.7.2.5.1.1.1.1 |  |  | SIT participants have requested DCC CSS PKI certificates for access to UIT-B environment | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 |  | 820 | 0 days | 0 days | 0 days | SIT Participants (Suppliers & Third Parties) | PP |  |  | 5.3 | Yes | Simon Berry
10 | 1.4.1.7.2.5.1.1.1.2 | T3-TE-0088 | SITAG | SIT participants have received DCC CSS PKI certificates for UIT-B environment | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 819 |  | 0 days | 0 days | 0 days | SIT Participants (Suppliers & Third Parties) | PP |  |  | 5.5 | Yes | Simon Berry
9 | 1.4.1.7.2.5.1.1.2 |  |  | DSP | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.3 | Yes | N/A
10 | 1.4.1.7.2.5.1.1.2.1 |  |  | SIT participants have requested DCC DSP PKI certificates for access to UIT-B environment | 100% | Mon 04/12/23 | Fri 15/12/23 | 10 days | Mon 04/12/23 | Fri 15/12/23 |  | 823 | 0 days | 0 days | 0 days | PPs in SDS Market Role | PP |  |  | 5.3 | Yes | Simon Berry
10 | 1.4.1.7.2.5.1.1.2.2 | T3-TE-0089 | SITAG | SIT participants have received DCC DSP PKI certificates for UIT-B environment | 100% | Fri 15/12/23 | Fri 15/12/23 | 0 days | Fri 15/12/23 | Fri 15/12/23 | 822 |  | 0 days | 0 days | 0 days | PPs in SDS Market Role | PP |  |  | 5.5 | Yes | Simon Berry
6 | 1.4.1.7.2.6 |  |  | Environments (SIT A) | 99% | Mon 05/02/24 | Fri 08/03/24 | 25 days | Mon 08/01/24 | Fri 09/02/24 |  |  | 20 days | 20 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.2.6.1 |  |  | SIT Functional Connectivity Proving | 100% | Mon 12/02/24 | Fri 01/03/24 | 15 days | Mon 08/01/24 | Fri 02/02/24 |  |  | 25 days | 20 days | -5 days | N/A | N/A |  |  | 5.5 | Yes | N/A
8 | 1.4.1.7.2.6.1.1 |  |  | SIT Functional Connectivity Proving Period | 100% | Mon 12/02/24 | Fri 01/03/24 | 15 days | Mon 12/02/24 | Fri 01/03/24 |  | 827 | 0 days | 0 days | -5 days | SI Test | PP |  |  | 5.19 | Yes | Simon Berry
8 | 1.4.1.7.2.6.1.2 | T3-TE-0103 | SITAG | SIT Functional Connectivity Proving Complete | 100% | Fri 01/03/24 | Fri 01/03/24 | 0 days | Fri 01/03/24 | Fri 01/03/24 | 826 |  | 1 day | 0 days | 0 days | SI Test | PP |  |  | 5.19 | Yes | Simon Berry
7 | 1.4.1.7.2.6.2 |  |  | PP Environments (SIT A) | 100% | Mon 05/02/24 | Fri 08/03/24 | 25 days | Mon 05/02/24 | Fri 09/02/24 |  |  | 0 days | 20 days | 20 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.2.6.2.1 |  |  | Deployment of MHHS solution code to SIT A environments | 100% | Mon 05/02/24 | Fri 08/03/24 | 25 days | Mon 05/02/24 | Fri 09/02/24 |  | 831SS | 0 days | 20 days | 20 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
7 | 1.4.1.7.2.6.3 |  |  | SI Environments (SIT A) | 100% | Mon 05/02/24 | Fri 08/03/24 | 25 days | Mon 05/02/24 | Fri 09/02/24 |  |  | 0 days | 20 days | 20 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.2.6.3.1 |  |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT A environments | 100% | Mon 05/02/24 | Fri 08/03/24 | 25 days | Mon 05/02/24 | Fri 09/02/24 | 829SS |  | 0 days | 20 days | 20 days | SI Test | PP |  |  | 5 | Yes | Simon Berry
6 | 1.4.1.7.2.7 |  |  | Test data (SIT A) | 37% | Mon 18/12/23 | Fri 25/10/24 | 225 days | Mon 18/12/23 | Fri 25/10/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.4 | Yes | N/A
7 | 1.4.1.7.2.7.1 |  |  | Cycle 1 Test data (SIT A) | 100% | Mon 18/12/23 | Fri 01/03/24 | 55 days | Mon 18/12/23 | Fri 01/03/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.4 | Yes | N/A
8 | 1.4.1.7.2.7.1.1 |  |  | Prepare, Generate and Allocate Test Data | 100% | Mon 18/12/23 | Wed 24/01/24 | 28 days | Mon 18/12/23 | Wed 24/01/24 | 611619 | 835FS+1 day | 0 days | 0 days | 0 days | SI Test Data |  |  |  | 5.14 | Yes | Richard Puddephatt
8 | 1.4.1.7.2.7.1.2 |  |  | Transmit Data Sets to PPs | 100% | Fri 26/01/24 | Wed 31/01/24 | 4 days | Thu 25/01/24 | Fri 26/01/24 | 834FS+1 day | 836 | 1 day | 3 days | 2 days | SI Test Data |  |  |  | 5.14 | Yes | Richard Puddephatt
8 | 1.4.1.7.2.7.1.3 |  |  | PP's Iterative load and data integrity check | 100% | Thu 01/02/24 | Fri 01/03/24 | 22 days | Mon 29/01/24 | Fri 09/02/24 | 835 | 837 | 3 days | 15 days | 12 days | PP |  |  |  | 5.14 | Yes | Richard Puddephatt
8 | 1.4.1.7.2.7.1.4 | T3-TE-0079 | SITAG | Cycle 1 - PP's confirmation that test data is ready for SIT Functional | 100% | Fri 01/03/24 | Fri 01/03/24 | 0 days | Fri 01/03/24 | Fri 01/03/24 | 836 | 839FS+18 days,862,1025 | 0 days | 0 days | 0 days | SI Test Data |  |  |  | 5.18 | Yes | Richard Puddephatt
7 | 1.4.1.7.2.7.2 |  |  | Cycle 2 Test data (SIT A) | 32% | Thu 28/03/24 | Fri 31/05/24 | 47 days | Thu 28/03/24 | Fri 31/05/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.4 | Yes | N/A
8 | 1.4.1.7.2.7.2.1 |  |  | Prepare, Generate and Allocate Test Data | 48% | Thu 28/03/24 | Thu 09/05/24 | 31 days | Thu 28/03/24 | Thu 09/05/24 | 837FS+18 days | 840 | 0 days | 0 days | 0 days | SI Test Data |  |  |  | 5.14 | Yes | Richard Puddephatt
8 | 1.4.1.7.2.7.2.2 |  |  | Transmit Data Sets to PPs | 0% | Fri 10/05/24 | Tue 14/05/24 | 3 days | Fri 10/05/24 | Tue 14/05/24 | 839 | 841 | 0 days | 0 days | 0 days | SI Test Data |  |  |  | 5.14 | Yes | Richard Puddephatt
8 | 1.4.1.7.2.7.2.3 |  |  | PP's Iterative load and data integrity check | 0% | Wed 15/05/24 | Fri 31/05/24 | 13 days | Wed 15/05/24 | Fri 31/05/24 | 840 | 842 | 0 days | 0 days | 0 days | PP |  |  |  | 5.14 | Yes | Richard Puddephatt
8 | 1.4.1.7.2.7.2.4 | T3-TE-0080 | SITAG | Cycle 2 - PP's confirmation that test data is ready for SIT Functional | 0% | Fri 31/05/24 | Fri 31/05/24 | 0 days | Fri 31/05/24 | Fri 31/05/24 | 841 | 844FS+15 days,1031 | 0 days | 0 days | 0 days | SI Test Data |  | Approved | Date Change | 5.22 | Yes | Richard Puddephatt
7 | 1.4.1.7.2.7.3 |  |  | Cycle 3 Test data (SIT A) | 0% | Mon 24/06/24 | Mon 19/08/24 | 41 days | Mon 24/06/24 | Mon 19/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.4 | Yes | N/A
8 | 1.4.1.7.2.7.3.1 |  |  | Prepare, Generate and Allocate Test Data | 0% | Mon 24/06/24 | Wed 17/07/24 | 18 days | Mon 24/06/24 | Wed 17/07/24 | 842FS+15 days | 845 | 0 days | 0 days | 0 days | SI Test Data |  |  |  | 5.14 | Yes | Richard Puddephatt
8 | 1.4.1.7.2.7.3.2 |  |  | Transmit Data Sets to PPs | 0% | Thu 18/07/24 | Fri 19/07/24 | 2 days | Thu 18/07/24 | Fri 19/07/24 | 844 | 846 | 0 days | 0 days | 0 days | SI Test Data |  |  |  | 5.14 | Yes | Richard Puddephatt
8 | 1.4.1.7.2.7.3.3 |  |  | PP's Iterative load and data integrity check | 0% | Mon 22/07/24 | Mon 19/08/24 | 21 days | Mon 22/07/24 | Mon 19/08/24 | 845 | 847 | 0 days | 0 days | 0 days | PP |  |  |  | 5.14 | Yes | Richard Puddephatt
8 | 1.4.1.7.2.7.3.4 | T3-TE-0081 | SITAG | Cycle 3 - PP's confirmation that test data is ready for SIT Functional | 0% | Mon 19/08/24 | Mon 19/08/24 | 0 days | Mon 19/08/24 | Mon 19/08/24 | 846 | 849FS+4 days,1037 | 1 day | 0 days | 0 days | SI Test Data |  |  |  | 5.14 | Yes | Richard Puddephatt
7 | 1.4.1.7.2.7.4 |  |  | Regression Test data (SIT A) | 0% | Mon 26/08/24 | Fri 25/10/24 | 45 days | Mon 26/08/24 | Fri 25/10/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.4 | Yes | N/A
8 | 1.4.1.7.2.7.4.1 |  |  | Prepare, Generate and Allocate Test Data | 0% | Mon 26/08/24 | Wed 25/09/24 | 23 days | Mon 26/08/24 | Wed 25/09/24 | 847FS+4 days | 850 | 0 days | 0 days | 0 days | SI Test Data |  |  |  | 5.14 | Yes | Richard Puddephatt
8 | 1.4.1.7.2.7.4.2 |  |  | Transmit Data Sets to PPs | 0% | Thu 26/09/24 | Fri 27/09/24 | 2 days | Mon 23/09/24 | Fri 04/10/24 | 849 | 851 | 3 days | -5 days | -8 days | SI Test Data |  |  |  | 5.14 | Yes | Richard Puddephatt
8 | 1.4.1.7.2.7.4.3 |  |  | PP's Iterative load and data integrity check | 0% | Mon 30/09/24 | Fri 25/10/24 | 20 days | Mon 21/10/24 | Fri 25/10/24 | 850 | 852 | -15 days | 0 days | 15 days | PP |  |  |  | 5.14 | Yes | Richard Puddephatt
8 | 1.4.1.7.2.7.4.4 | T3-TE-0082 | SITAG | Regression - PP's confirmation that test data is ready for SIT Functional | 0% | Fri 25/10/24 | Fri 25/10/24 | 0 days | Fri 25/10/24 | Fri 25/10/24 | 851 | 1040 | 0 days | 0 days | 0 days | SI Test Data |  |  |  | 5.14 | Yes | Richard Puddephatt
6 | 1.4.1.7.2.8 |  |  | SIT Functional Test Readiness Report | 100% | Mon 01/01/24 | Thu 29/02/24 | 44 days | Mon 01/01/24 | Thu 29/02/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.2.8.1 |  |  | PP SIT Functional Test Readiness Report | 100% | Mon 01/01/24 | Thu 29/02/24 | 44 days | Mon 01/01/24 | Thu 29/02/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.2.8.1.1 |  |  | Develop draft Test Readiness Report and submit to Programme for assurance | 100% | Mon 01/01/24 | Mon 29/01/24 | 21 days | Mon 01/01/24 | Mon 29/01/24 |  | 859SS,857,856SS+10 days | 0 days | 1 day | 1 day | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.2.8.1.2 |  |  | Placing Reliance Stage 2 Review | 100% | Mon 15/01/24 | Thu 29/02/24 | 34 days | Mon 15/01/24 | Thu 29/02/24 | 855SS+10 days | 862 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.12 | Yes | Lee Cox
8 | 1.4.1.7.2.8.1.3 |  |  | Finalise Test Readiness Report and submit to Programme for assurance | 100% | Tue 30/01/24 | Fri 09/02/24 | 9 days | Mon 29/01/24 | Fri 09/02/24 | 855 | 859FF+5 days | 1 day | 0 days | -1 day | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.2.8.2 |  |  | SI SIT Functional Test Readiness Report | 100% | Mon 01/01/24 | Fri 23/02/24 | 40 days | Mon 01/01/24 | Fri 23/02/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.2.8.2.1 |  |  | Assure Test Participants' Test Readiness Reports | 100% | Mon 01/01/24 | Fri 16/02/24 | 35 days | Mon 01/01/24 | Fri 16/02/24 | 855SS,857FF+5 days | 860FF | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.2.8.2.2 |  |  | Develop Overarching SIT Functional Test Readiness Report | 100% | Mon 22/01/24 | Fri 16/02/24 | 20 days | Mon 22/01/24 | Fri 16/02/24 | 859FF | 861 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.2.8.2.3 |  |  | Artefact review (via TMAG) and updates | 100% | Mon 19/02/24 | Fri 23/02/24 | 5 days | Mon 19/02/24 | Fri 23/02/24 | 860 | 862FF+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
6 | 1.4.1.7.2.9 | T2-TE-0550 | SITAG | SIT Functional Testing Preparation Complete | 100% | Fri 01/03/24 | Fri 01/03/24 | 0 days | Fri 01/03/24 | Fri 01/03/24 | 861FF+5 days,797,313,856,805,812,837 | 1022FS+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
5 | 1.4.1.7.3 |  |  | SIT Migration Testing Preparation | 78% | Mon 31/10/22 | Fri 07/06/24 | 420 days | Mon 31/10/22 | Fri 07/06/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.21 | Yes | N/A
6 | 1.4.1.7.3.1 |  |  | Test Approach & Plan | 100% | Thu 07/09/23 | Wed 20/12/23 | 75 days | Thu 07/09/23 | Wed 20/12/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.3.1.1 |  |  | Develop document with SITWG | 100% | Thu 07/09/23 | Fri 20/10/23 | 32 days | Thu 07/09/23 | Wed 11/10/23 | 1777 | 866 | 0 days | 7 days | 7 days | SI Test |  |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.3.1.2 |  |  | Draft document review with Code Bodies | 100% | Mon 23/10/23 | Wed 01/11/23 | 8 days | Thu 12/10/23 | Wed 25/10/23 | 865 | 867 | 7 days | 5 days | -2 days | SI Test | Code Bodies |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.3.1.3 |  |  | Industry Consultation | 100% | Thu 02/11/23 | Wed 15/11/23 | 10 days | Thu 02/11/23 | Wed 15/11/23 | 866 | 868,871SS | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Lee Cox
7 | 1.4.1.7.3.1.4 |  |  | Artefact review (via TMAG) and updates | 100% | Thu 16/11/23 | Wed 20/12/23 | 25 days | Thu 09/11/23 | Wed 20/12/23 | 867 | 869 | 5 days | 0 days | -5 days | SI Test | PP,IPA,Code Bodies |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.3.1.5 | T3-TE-0018 | SITAG | SIT Migration Testing Test Approach & Plan approved | 100% | Wed 20/12/23 | Wed 20/12/23 | 0 days | Wed 20/12/23 | Wed 20/12/23 | 868 | 9.141e+19 | 1 day | 0 days | -1 day | SI Test | PP |  |  | 5.14 | Yes | Lee Cox
6 | 1.4.1.7.3.2 |  |  | Test Data Approach & Plan | 100% | Thu 02/11/23 | Wed 20/12/23 | 35 days | Thu 02/11/23 | Wed 20/12/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.3.2.1 |  |  | Industry Consultation | 100% | Thu 02/11/23 | Wed 15/11/23 | 10 days | Thu 02/11/23 | Wed 15/11/23 | 867SS | 872 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | PP
7 | 1.4.1.7.3.2.2 |  |  | Artefact review (via TMAG) and updates | 100% | Thu 16/11/23 | Wed 20/12/23 | 25 days | Thu 09/11/23 | Wed 20/12/23 | 871 | 873 | 5 days | 0 days | -5 days | SI Test Data |  |  |  | 5 | Yes | Richard Puddephatt
7 | 1.4.1.7.3.2.3 |  |  | SIT Migration Test Data Test Approach & Plan approved | 100% | Wed 20/12/23 | Wed 20/12/23 | 0 days | Wed 20/12/23 | Wed 20/12/23 | 872 | 1048 | 0 days | 0 days | 0 days | SI Test Data | PP,IPA |  |  | 5.14 | Yes | Richard Puddephatt
6 | 1.4.1.7.3.3 |  |  | Test scenarios & Test Cases | 99% | Thu 21/12/23 | Wed 17/04/24 | 85 days | Thu 21/12/23 | Wed 20/03/24 |  |  | 0 days | 20 days | 20 days | N/A | N/A |  |  | 5.16 | Yes | N/A
7 | 1.4.1.7.3.3.1 |  |  | Theme 1 | 100% | Thu 21/12/23 | Wed 20/03/24 | 65 days | Thu 21/12/23 | Wed 20/03/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.16 | Yes | N/A
8 | 1.4.1.7.3.3.1.1 |  |  | Develop Test Scenarios & Test Cases | 100% | Thu 21/12/23 | Wed 24/01/24 | 25 days | Thu 21/12/23 | Wed 24/01/24 | 869 | 877 | 0 days | 0 days | 0 days | SI Test | SI Test, PP |  |  | 5.16 | Yes | Lee Cox
8 | 1.4.1.7.3.3.1.2 |  |  | Industry Review Workshop | 100% | Thu 25/01/24 | Thu 25/01/24 | 1 day | Thu 25/01/24 | Thu 25/01/24 | 876 | 878FS+6 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.16 | Yes | Lee Cox
8 | 1.4.1.7.3.3.1.3 |  |  | Industry Consultation Review | 100% | Mon 05/02/24 | Mon 12/02/24 | 6 days | Mon 05/02/24 | Mon 12/02/24 | 877FS+6 days | 879FS+12 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.16 | Yes | Lee Cox
8 | 1.4.1.7.3.3.1.4 |  |  | Review with SIT Working Group | 100% | Thu 29/02/24 | Wed 06/03/24 | 5 days | Thu 29/02/24 | Wed 06/03/24 | 878FS+12 days | 880FS+10 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.19 | Yes | Lee Cox
8 | 1.4.1.7.3.3.1.5 | T3-TE-0110 | SITAG | SIT Migration Test scenarios & Test Cases Approved - Theme 1 | 100% | Wed 20/03/24 | Wed 20/03/24 | 0 days | Wed 20/03/24 | Wed 20/03/24 | 879FS+10 days | 9141048 | 0 days | 0 days | 0 days | SI Test | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
7 | 1.4.1.7.3.3.2 |  |  | Theme 2 | 99% | Thu 21/12/23 | Wed 17/04/24 | 85 days | Thu 21/12/23 | Wed 17/04/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.16 | Yes | N/A
8 | 1.4.1.7.3.3.2.1 |  |  | Develop Test Scenarios & Test Cases | 100% | Thu 21/12/23 | Wed 14/02/24 | 40 days | Thu 21/12/23 | Wed 14/02/24 | 869 | 883 | 0 days | 0 days | 0 days | SI Test | SI Test, PP |  |  | 5.16 | Yes | Lee Cox
8 | 1.4.1.7.3.3.2.2 |  |  | Industry Review Workshop | 100% | Thu 15/02/24 | Thu 15/02/24 | 1 day | Thu 15/02/24 | Thu 15/02/24 | 882 | 884FS+6 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.16 | Yes | Lee Cox
8 | 1.4.1.7.3.3.2.3 |  |  | Industry Consultation Review | 100% | Mon 26/02/24 | Mon 04/03/24 | 6 days | Mon 26/02/24 | Mon 04/03/24 | 883FS+6 days | 885FS+17 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.19 | Yes | Lee Cox
8 | 1.4.1.7.3.3.2.4 |  |  | Review with SIT Working Group | 100% | Thu 28/03/24 | Wed 03/04/24 | 5 days | Thu 28/03/24 | Wed 03/04/24 | 884FS+17 days | 886FS+10 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.16 | Yes | Lee Cox
8 | 1.4.1.7.3.3.2.5 | T3-TE-0111 | SITAG | SIT Migration Test scenarios & Test Cases Approved - Theme 2 | 100% | Wed 17/04/24 | Wed 17/04/24 | 0 days | Wed 17/04/24 | Wed 17/04/24 | 885FS+10 days | 9141048 | 0 days | 0 days | 0 days | SI Test | SI Test, PP |  |  | 5.22 | Yes | Lee Cox
7 | 1.4.1.7.3.3.3 |  |  | Theme 3 | 99% | Thu 21/12/23 | Wed 17/04/24 | 85 days | Thu 21/12/23 | Wed 17/04/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.16 | Yes | N/A
8 | 1.4.1.7.3.3.3.1 |  |  | Develop Test Scenarios & Test Cases | 100% | Thu 21/12/23 | Wed 06/03/24 | 55 days | Thu 21/12/23 | Wed 06/03/24 | 869 | 889 | 0 days | 0 days | 0 days | SI Test | SI Test, PP |  |  | 5.19 | Yes | Lee Cox
8 | 1.4.1.7.3.3.3.2 |  |  | Industry Review Workshop | 100% | Thu 07/03/24 | Thu 07/03/24 | 1 day | Thu 07/03/24 | Thu 07/03/24 | 888 | 890FS+3 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.16 | Yes | Lee Cox
8 | 1.4.1.7.3.3.3.3 |  |  | Industry Consultation Review | 100% | Wed 13/03/24 | Wed 20/03/24 | 6 days | Wed 13/03/24 | Wed 20/03/24 | 889FS+3 days | 891FS+5 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.16 | Yes | Lee Cox
8 | 1.4.1.7.3.3.3.4 |  |  | Review with SIT Working Group | 100% | Thu 28/03/24 | Wed 03/04/24 | 5 days | Thu 28/03/24 | Wed 03/04/24 | 890FS+5 days | 892FS+10 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.16 | Yes | Lee Cox
8 | 1.4.1.7.3.3.3.5 | T3-TE-0112 | SITAG | SIT Migration Test scenarios & Test Cases Approved - Theme 3 | 100% | Wed 17/04/24 | Wed 17/04/24 | 0 days | Wed 17/04/24 | Wed 17/04/24 | 891FS+10 days | 9141048 | 0 days | 0 days | 0 days | SI Test | SI Test, PP |  |  | 5.22 | Yes | Lee Cox
6 | 1.4.1.7.3.4 |  |  | Environments (SIT B) | 80% | Mon 31/10/22 | Fri 07/06/24 | 420 days | Mon 31/10/22 | Fri 07/06/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.3.4.1 |  |  | PP Environments (SIT B) | 0% | Fri 03/05/24 | Fri 07/06/24 | 26 days | Fri 03/05/24 | Fri 07/06/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.3.4.1.1 |  |  | PP Environments available | 0% | Fri 03/05/24 | Fri 03/05/24 | 0 days | Fri 03/05/24 | Fri 03/05/24 | 466 | 896FS+6 days,897FS+21 days,902 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.21 | Yes | Simon Berry
8 | 1.4.1.7.3.4.1.2 |  |  | PP Onboarding / Smoke test | 0% | Mon 13/05/24 | Fri 07/06/24 | 20 days | Mon 13/05/24 | Fri 07/06/24 | 895FS+6 days |  | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.21 | Yes | Simon Berry
8 | 1.4.1.7.3.4.1.3 |  |  | DTN Connectivity Proving Complete | 0% | Fri 31/05/24 | Fri 31/05/24 | 0 days | Fri 31/05/24 | Fri 31/05/24 | 895FS+21 days | 898FS+1 day | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.21 | Yes | Simon Berry
8 | 1.4.1.7.3.4.1.4 |  |  | PP Code Deployment | 0% | Mon 03/06/24 | Mon 03/06/24 | 0 days | Mon 03/06/24 | Mon 03/06/24 | 897FS+1 day | 904 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.21 | Yes | Simon Berry
7 | 1.4.1.7.3.4.2 |  |  | SI Environments (SIT B) | 84% | Mon 31/10/22 | Fri 07/06/24 | 420 days | Mon 31/10/22 | Fri 07/06/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.3.4.2.1 |  |  | Coordinate SIT Participants' SIT B environment preparation | 90% | Mon 31/10/22 | Fri 07/06/24 | 420 days | Mon 31/10/22 | Fri 07/06/24 |  | 901 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.21 | Yes | Simon Berry
8 | 1.4.1.7.3.4.2.2 |  |  | Assure PPs' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 0% | Fri 07/06/24 | Fri 07/06/24 | 0 days | Fri 07/06/24 | Fri 07/06/24 | 900 |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.21 | Yes | Simon Berry
8 | 1.4.1.7.3.4.2.3 | T3-TE-0033 | SITAG | SIT Participants' SIT B environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Fri 03/05/24 | Fri 03/05/24 | 0 days | Fri 03/05/24 | Fri 03/05/24 | 895 | 903 | 0 days | 0 days | 0 days | SI Test | PP,IPA | Approved | Date Change | 5.22 | Yes | Simon Berry
8 | 1.4.1.7.3.4.2.4 |  |  | Coordinate SIT Participants' SIT B environment connectivity proving | 0% | Fri 03/05/24 | Fri 07/06/24 | 26 days | Tue 14/05/24 | Fri 07/06/24 | 902 |  | -7 days | 0 days | 7 days | SI Test | PP |  |  | 5.21 | Yes | Simon Berry
8 | 1.4.1.7.3.4.2.5 |  |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT B environments | 0% | Tue 04/06/24 | Fri 07/06/24 | 4 days | Tue 04/06/24 | Fri 07/06/24 | 898 |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.21 | Yes | Simon Berry
6 | 1.4.1.7.3.5 |  |  | SIT Migration Test Readiness Report | 22% | Tue 02/04/24 | Fri 31/05/24 | 44 days | Tue 02/04/24 | Fri 31/05/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.3.5.1 |  |  | PP SIT Migration Test Readiness Report | 23% | Tue 02/04/24 | Fri 31/05/24 | 44 days | Tue 02/04/24 | Fri 31/05/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.3.5.1.1 |  |  | Develop draft Test Readiness Report and submit to Programme for assurance | 60% | Tue 02/04/24 | Mon 29/04/24 | 20 days | Tue 02/04/24 | Tue 30/04/24 |  | 911SS,909,908SS+9 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.3.5.1.2 |  |  | Placing Reliance Stage 2 Review | 9% | Mon 15/04/24 | Fri 31/05/24 | 35 days | Mon 15/04/24 | Fri 31/05/24 | 907SS+9 days | 914 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.12 | Yes | Lee Cox
8 | 1.4.1.7.3.5.1.3 |  |  | Finalise Test Readiness Report and submit to Programme for assurance | 0% | Tue 30/04/24 | Mon 13/05/24 | 10 days | Tue 30/04/24 | Mon 13/05/24 | 907 | 911FF+5 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.3.5.2 |  |  | SI SIT Migration Test Readiness Report | 20% | Tue 02/04/24 | Mon 27/05/24 | 40 days | Tue 02/04/24 | Mon 27/05/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.3.5.2.1 |  |  | Assure Test Participants' Test Readiness Reports | 34% | Tue 02/04/24 | Mon 20/05/24 | 35 days | Tue 02/04/24 | Mon 20/05/24 | 907SS,909FF+5 days | 912FF | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.3.5.2.2 |  |  | Develop Overarching SIT Migration Test Readiness Report | 0% | Tue 23/04/24 | Mon 20/05/24 | 20 days | Tue 23/04/24 | Mon 20/05/24 | 911FF | 913 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.3.5.2.3 |  |  | Artefact review (via SITAG) and updates | 0% | Tue 21/05/24 | Mon 27/05/24 | 5 days | Tue 21/05/24 | Mon 27/05/24 | 912 | 914FF+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
6 | 1.4.1.7.3.6 | T2-TE-0650 | SITAG | SIT Migration Testing Preparation Complete | 0% | Mon 03/06/24 | Mon 03/06/24 | 0 days | Mon 03/06/24 | Mon 03/06/24 | 913FF+5 days,869,330,908,880,886,892 | 1048FS+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
5 | 1.4.1.7.4 |  |  | SIT Non-Functional Preparation | 46% | Thu 30/11/23 | Tue 27/08/24 | 193 days | Thu 30/11/23 | Tue 27/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.1.7.4.1 |  |  | Test Approach & Plan | 99% | Thu 30/11/23 | Wed 15/05/24 | 120 days | Thu 30/11/23 | Wed 15/05/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.4.1.1 |  |  | Develop document with SITWG | 100% | Thu 30/11/23 | Fri 01/03/24 | 67 days | Thu 30/11/23 | Fri 01/03/24 |  | 918940934928 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.4.1.2 |  |  | Draft document review with Code Bodies | 100% | Mon 04/03/24 | Fri 15/03/24 | 10 days | Mon 04/03/24 | Fri 15/03/24 | 917 | 9191210 | 0 days | 0 days | 0 days | SI Test | Code Bodies |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.4.1.3 |  |  | Industry Consultation | 100% | Mon 18/03/24 | Fri 29/03/24 | 10 days | Mon 18/03/24 | Fri 29/03/24 | 918 | 923SS+2 days,920FS+8 days | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Lee Cox
7 | 1.4.1.7.4.1.4 |  |  | Industry Assurance Review | 100% | Thu 11/04/24 | Wed 17/04/24 | 5 days | Thu 11/04/24 | Wed 17/04/24 | 919FS+8 days | 921FS+20 days | 0 days | 0 days | 0 days |  |  |  |  | 5.16 | Yes | Lee Cox
7 | 1.4.1.7.4.1.5 | T3-TE-0026 | SITAG | SIT Non-Functional Testing Test Approach & Plan approved | 0% | Wed 15/05/24 | Wed 15/05/24 | 0 days | Wed 15/05/24 | Wed 15/05/24 | 920FS+20 days | 925FF,1057,1326,1214 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.18 | Yes | Lee Cox
6 | 1.4.1.7.4.2 |  |  | Test Data Approach & Plan | 51% | Wed 20/03/24 | Wed 15/05/24 | 41 days | Wed 20/03/24 | Wed 15/05/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.4.2.1 |  |  | Industry Consultation | 100% | Wed 20/03/24 | Mon 08/04/24 | 14 days | Wed 20/03/24 | Mon 08/04/24 | 919SS+2 days | 924 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Richard Puddephatt
7 | 1.4.1.7.4.2.2 |  |  | Artefact review (via SITAG) and updates | 26% | Tue 09/04/24 | Wed 15/05/24 | 27 days | Tue 09/04/24 | Wed 15/05/24 | 923 | 925 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Richard Puddephatt
7 | 1.4.1.7.4.2.3 | T3-TE-0113 | SITAG | SIT Non-Functional Testing Test Data Approach & Plan approved | 0% | Wed 15/05/24 | Wed 15/05/24 | 0 days | Wed 15/05/24 | Wed 15/05/24 | 921FF,924 | 1057 | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5.18 | Yes | Richard Puddephatt
6 | 1.4.1.7.4.3 |  |  | Test scenarios & Test Cases | 50% | Mon 04/03/24 | Wed 17/07/24 | 98 days | Mon 04/03/24 | Wed 17/07/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.21 | Yes | N/A
7 | 1.4.1.7.4.3.1 |  |  | Theme 1 | 61% | Mon 04/03/24 | Wed 19/06/24 | 78 days | Mon 04/03/24 | Wed 19/06/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.21 | Yes | N/A
8 | 1.4.1.7.4.3.1.1 |  |  | Develop Test Scenarios & Test Cases | 85% | Mon 04/03/24 | Wed 17/04/24 | 33 days | Mon 04/03/24 | Wed 17/04/24 | 917 | 929 | 0 days | 0 days | 0 days | SI Test | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.4.3.1.2 |  |  | Industry Review Workshop | 0% | Thu 18/04/24 | Thu 18/04/24 | 1 day | Thu 18/04/24 | Thu 18/04/24 | 928 | 930FS+9 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.4.3.1.3 |  |  | Industry Consultation Review | 0% | Thu 02/05/24 | Fri 10/05/24 | 7 days | Thu 02/05/24 | Fri 10/05/24 | 929FS+9 days | 931FS+14 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.4.3.1.4 |  |  | Review with NFT Working Group | 0% | Fri 31/05/24 | Thu 06/06/24 | 5 days | Fri 31/05/24 | Thu 06/06/24 | 930FS+14 days | 932FS+9 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.4.3.1.5 | T3-TE-0114 | SITAG | SIT NFT Scenarios & Test Cases Approved - Theme 1 | 0% | Wed 19/06/24 | Wed 19/06/24 | 0 days | Wed 19/06/24 | Wed 19/06/24 | 931FS+9 days | 9591057 | 0 days | 0 days | 0 days | SI Test | SI Test, PP | Approved | New | 5.22 | Yes | Lee Cox
7 | 1.4.1.7.4.3.2 |  |  | Theme 2 | 50% | Mon 04/03/24 | Wed 17/07/24 | 98 days | Mon 04/03/24 | Wed 17/07/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.21 | Yes | N/A
8 | 1.4.1.7.4.3.2.1 |  |  | Develop Test Scenarios & Test Cases | 62% | Mon 04/03/24 | Wed 15/05/24 | 53 days | Mon 04/03/24 | Wed 15/05/24 | 917 | 935 | 0 days | 0 days | 0 days | SI Test | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.4.3.2.2 |  |  | Industry Review Workshop | 0% | Thu 16/05/24 | Thu 16/05/24 | 1 day | Thu 16/05/24 | Thu 16/05/24 | 934 | 936FS+1 day | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.4.3.2.3 |  |  | Industry Consultation Review | 0% | Mon 20/05/24 | Tue 28/05/24 | 7 days | Mon 20/05/24 | Tue 28/05/24 | 935FS+1 day | 937FS+22 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.4.3.2.4 |  |  | Review with NFT Working Group | 0% | Fri 28/06/24 | Thu 04/07/24 | 5 days | Fri 28/06/24 | Thu 04/07/24 | 936FS+22 days | 938FS+9 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.4.3.2.5 | T3-TE-0115 | SITAG | SIT NFT Scenarios & Test Cases Approved - Theme 2 | 0% | Wed 17/07/24 | Wed 17/07/24 | 0 days | Wed 17/07/24 | Wed 17/07/24 | 937FS+9 days | 9591057 | 0 days | 0 days | 0 days | SI Test | SI Test, PP | Approved | New | 5.22 | Yes | Lee Cox
7 | 1.4.1.7.4.3.3 |  |  | Theme 3 | 44% | Mon 04/03/24 | Wed 17/07/24 | 98 days | Mon 04/03/24 | Wed 17/07/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.21 | Yes | N/A
8 | 1.4.1.7.4.3.3.1 |  |  | Develop Test Scenarios & Test Cases | 52% | Mon 04/03/24 | Wed 29/05/24 | 63 days | Mon 04/03/24 | Wed 29/05/24 | 917 | 941 | 0 days | 0 days | 0 days | SI Test | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.4.3.3.2 |  |  | Industry Review Workshop | 0% | Thu 30/05/24 | Thu 30/05/24 | 1 day | Thu 30/05/24 | Thu 30/05/24 | 940 | 942FS+6 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.4.3.3.3 |  |  | Industry Consultation Review | 0% | Mon 10/06/24 | Mon 17/06/24 | 6 days | Mon 10/06/24 | Mon 17/06/24 | 941FS+6 days | 943FS+8 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.4.3.3.4 |  |  | Review with NFT Working Group | 0% | Fri 28/06/24 | Thu 04/07/24 | 5 days | Fri 28/06/24 | Thu 04/07/24 | 942FS+8 days | 944FS+9 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.4.3.3.5 | T3-TE-0114 | SITAG | SIT NFT Scenarios & Test Cases Approved - Theme 3 | 0% | Wed 17/07/24 | Wed 17/07/24 | 0 days | Wed 17/07/24 | Wed 17/07/24 | 943FS+9 days | 9591057 | 0 days | 0 days | 0 days | SI Test | SI Test, PP | Approved | New | 5.22 | Yes | Lee Cox
6 | 1.4.1.7.4.4 |  |  | Environments (SIT B) | 0% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.4.4.1 |  |  | PP Environments (SIT B) | 0% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.4.4.1.1 |  |  | Deployment of MHHS solution code to SIT B environments | 0% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 |  | 949SS | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.21 | Yes | Simon Berry
7 | 1.4.1.7.4.4.2 |  |  | SI Environments (SIT B) | 0% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.4.4.2.1 |  |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT B environments | 0% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 | 947SS |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.21 | Yes | Simon Berry
6 | 1.4.1.7.4.5 |  |  | SIT Non-Functional Test Readiness Report | 0% | Tue 25/06/24 | Fri 23/08/24 | 44 days | Tue 25/06/24 | Fri 23/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.4.5.1 |  |  | PP SIT Non-Functional Test Readiness Report | 0% | Tue 25/06/24 | Fri 23/08/24 | 44 days | Tue 25/06/24 | Fri 23/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.4.5.1.1 |  |  | Develop draft Test Readiness Report and submit to Programme for assurance | 0% | Tue 25/06/24 | Mon 22/07/24 | 20 days | Tue 25/06/24 | Mon 22/07/24 |  | 956SS,954,953SS+4 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.4.5.1.2 |  |  | Placing Reliance Stage 2 Review | 0% | Mon 01/07/24 | Fri 23/08/24 | 40 days | Mon 01/07/24 | Fri 23/08/24 | 952SS+4 days | 959 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.12 | Yes | Lee Cox
8 | 1.4.1.7.4.5.1.3 |  |  | Finalise Test Readiness Report and submit to Programme for assurance | 0% | Tue 23/07/24 | Mon 05/08/24 | 10 days | Tue 23/07/24 | Mon 05/08/24 | 952 | 956FF+5 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.4.5.2 |  |  | SI SIT Non-Functional Test Readiness Report | 0% | Tue 25/06/24 | Mon 19/08/24 | 40 days | Tue 25/06/24 | Mon 19/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.4.5.2.1 |  |  | Assure Test Participants' Test Readiness Reports | 0% | Tue 25/06/24 | Mon 12/08/24 | 35 days | Tue 25/06/24 | Mon 12/08/24 | 952SS,954FF+5 days | 957FF | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.4.5.2.2 |  |  | Develop Overarching SIT Non-Functional Test Readiness Report | 0% | Tue 16/07/24 | Mon 12/08/24 | 20 days | Tue 16/07/24 | Mon 12/08/24 | 956FF | 958 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.4.5.2.3 |  |  | Artefact review (via SITAG) and updates | 0% | Tue 13/08/24 | Mon 19/08/24 | 5 days | Tue 13/08/24 | Mon 19/08/24 | 957 | 959FF+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
6 | 1.4.1.7.4.6 | T2-TE-0700 | SITAG | SIT Non-Functional Testing Preparation Complete | 0% | Mon 26/08/24 | Mon 26/08/24 | 0 days | Mon 26/08/24 | Mon 26/08/24 | 958FF+5 days,797,347,953,932,938,944 | 1057FS+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
5 | 1.4.1.7.5 |  |  | SIT Operational Preparation | 28% | Thu 01/02/24 | Wed 25/09/24 | 170 days | Thu 01/02/24 | Mon 03/03/25 |  |  | 0 days | -113 days | -113 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.1.7.5.1 |  |  | Test Approach & Plan | 69% | Thu 01/02/24 | Wed 15/05/24 | 75 days | Thu 01/02/24 | Wed 15/05/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.5.1.1 |  |  | Develop document with SITWG | 100% | Thu 01/02/24 | Wed 06/03/24 | 25 days | Thu 01/02/24 | Wed 06/03/24 |  | 963FS+10 days | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.5.1.2 |  |  | Draft document review with Code Bodies | 100% | Thu 21/03/24 | Tue 26/03/24 | 4 days | Thu 07/03/24 | Wed 20/03/24 | 962FS+10 days | 964 | 10 days | 4 days | -6 days | SI Test | Code Bodies |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.5.1.3 |  |  | Industry Consultation | 100% | Wed 27/03/24 | Tue 09/04/24 | 10 days | Wed 27/03/24 | Tue 09/04/24 | 963 | 965,968SS,973,979,985 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Lee Cox
7 | 1.4.1.7.5.1.4 |  |  | Artefact review (via SITAG) and updates | 23% | Wed 10/04/24 | Wed 15/05/24 | 26 days | Thu 04/04/24 | Wed 15/05/24 | 964 | 966 | 4 days | 0 days | -4 days | SI Test | PP,IPA,Code Bodies |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.5.1.5 | T3-TE-0029 | SITAG | SIT Operational Testing Test Approach & Plan approved | 0% | Wed 15/05/24 | Wed 15/05/24 | 0 days | Wed 15/05/24 | Wed 15/05/24 | 965 | 10661331 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.1.7.5.2 |  |  | Test Data Approach & Plan | 44% | Wed 27/03/24 | Wed 15/05/24 | 36 days | Wed 27/03/24 | Wed 15/05/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.5.2.1 |  |  | Industry Consultation | 100% | Wed 27/03/24 | Tue 09/04/24 | 10 days | Wed 27/03/24 | Tue 09/04/24 | 964SS | 969 | 0 days | 0 days | 0 days | PP |  |  |  | 5.1 | Yes | Richard Puddephatt
7 | 1.4.1.7.5.2.2 |  |  | Artefact review (via SITAG) and updates | 23% | Wed 10/04/24 | Wed 15/05/24 | 26 days | Wed 10/04/24 | Wed 15/05/24 | 968 | 970 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Richard Puddephatt
7 | 1.4.1.7.5.2.3 |  |  | SIT Operational Testing Test Data Approach & Plan approved | 0% | Wed 15/05/24 | Wed 15/05/24 | 0 days | Wed 15/05/24 | Wed 15/05/24 | 969 | 1066 | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Richard Puddephatt
6 | 1.4.1.7.5.3 |  |  | Test scenarios & Test Cases | 14% | Wed 10/04/24 | Wed 21/08/24 | 96 days | Wed 10/04/24 | Wed 21/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.21 | Yes | N/A
7 | 1.4.1.7.5.3.1 |  |  | Theme 1 | 21% | Wed 10/04/24 | Wed 17/07/24 | 71 days | Wed 10/04/24 | Wed 17/07/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.21 | Yes | N/A
8 | 1.4.1.7.5.3.1.1 |  |  | Develop Test Scenarios & Test Cases | 38% | Wed 10/04/24 | Wed 01/05/24 | 16 days | Wed 10/04/24 | Wed 01/05/24 | 964 | 974 | 0 days | 0 days | 0 days | SI Test | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.5.3.1.2 |  |  | Industry Review Workshop | 0% | Thu 02/05/24 | Thu 02/05/24 | 1 day | Thu 02/05/24 | Thu 02/05/24 | 973 | 975FS+5 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.5.3.1.3 |  |  | Industry Consultation Review | 0% | Fri 10/05/24 | Fri 17/05/24 | 6 days | Fri 10/05/24 | Fri 17/05/24 | 974FS+5 days | 976FS+28 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.5.3.1.4 |  |  | Review with SIT Working Group | 0% | Thu 27/06/24 | Wed 03/07/24 | 5 days | Thu 27/06/24 | Wed 03/07/24 | 975FS+28 days | 977FS+10 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.5.3.1.5 | T3-TE-0117 | SITAG | SIT Operational Scenarios & Test Cases Approved - Theme 1 | 0% | Wed 17/07/24 | Wed 17/07/24 | 0 days | Wed 17/07/24 | Wed 17/07/24 | 976FS+10 days | 10021066 | 0 days | 0 days | 0 days | SI Test | SI Test, PP | Approved | New | 5.22 | Yes | Lee Cox
7 | 1.4.1.7.5.3.2 |  |  | Theme 2 | 14% | Wed 10/04/24 | Wed 17/07/24 | 71 days | Wed 10/04/24 | Wed 17/07/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.21 | Yes | N/A
8 | 1.4.1.7.5.3.2.1 |  |  | Develop Test Scenarios & Test Cases | 19% | Wed 10/04/24 | Wed 22/05/24 | 31 days | Wed 10/04/24 | Wed 22/05/24 | 964 | 980 | 0 days | 0 days | 0 days | SI Test | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.5.3.2.2 |  |  | Industry Review Workshop | 0% | Thu 23/05/24 | Thu 23/05/24 | 1 day | Thu 23/05/24 | Thu 23/05/24 | 979 | 981FS+7 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.5.3.2.3 |  |  | Industry Consultation Review | 0% | Tue 04/06/24 | Tue 11/06/24 | 6 days | Tue 04/06/24 | Tue 11/06/24 | 980FS+7 days | 982FS+11 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.5.3.2.4 |  |  | Review with SIT Working Group | 0% | Thu 27/06/24 | Wed 03/07/24 | 5 days | Thu 27/06/24 | Wed 03/07/24 | 981FS+11 days | 983FS+10 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.5.3.2.5 | T3-TE-0118 | SITAG | SIT Operational Scenarios & Test Cases Approved - Theme 2 | 0% | Wed 17/07/24 | Wed 17/07/24 | 0 days | Wed 17/07/24 | Wed 17/07/24 | 982FS+10 days | 10021066 | 0 days | 0 days | 0 days | SI Test | SI Test, PP | Approved | New | 5.22 | Yes | Lee Cox
7 | 1.4.1.7.5.3.3 |  |  | Theme 3 | 10% | Wed 10/04/24 | Wed 21/08/24 | 96 days | Wed 10/04/24 | Wed 21/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.21 | Yes | N/A
8 | 1.4.1.7.5.3.3.1 |  |  | Develop Test Scenarios & Test Cases | 13% | Wed 10/04/24 | Wed 12/06/24 | 46 days | Wed 10/04/24 | Wed 12/06/24 | 964 | 986 | 0 days | 0 days | 0 days | SI Test | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.5.3.3.2 |  |  | Industry Review Workshop | 0% | Thu 13/06/24 | Thu 13/06/24 | 1 day | Thu 13/06/24 | Thu 13/06/24 | 985 | 987FS+6 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.5.3.3.3 |  |  | Industry Consultation Review | 0% | Mon 24/06/24 | Mon 01/07/24 | 6 days | Mon 24/06/24 | Mon 01/07/24 | 986FS+6 days | 988FS+17 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.5.3.3.4 |  |  | Review with SIT Working Group | 0% | Thu 25/07/24 | Wed 31/07/24 | 5 days | Thu 25/07/24 | Wed 31/07/24 | 987FS+17 days | 989FS+15 days | 0 days | 0 days | 0 days | SI Test, PP | SI Test, PP |  |  | 5.21 | Yes | Lee Cox
8 | 1.4.1.7.5.3.3.5 | T3-TE-0114 | SITAG | SIT Operational Scenarios & Test Cases Approved - Theme 3 | 0% | Wed 21/08/24 | Wed 21/08/24 | 0 days | Wed 21/08/24 | Wed 21/08/24 | 988FS+15 days | 10021066 | 0 days | 0 days | 0 days | SI Test | SI Test, PP | Approved | New | 5.22 | Yes | Lee Cox
6 | 1.4.1.7.5.4 |  |  | Environments (SIT B) | 0% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.5.4.1 |  |  | PP Environments (SIT B) | 0% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.5.4.1.1 |  |  | Deployment of MHHS solution code to SIT B environments | 0% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 |  | 994SS | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5.21 | Yes | Simon Berry
7 | 1.4.1.7.5.4.2 |  |  | SI Environments (SIT B) | 0% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.5.4.2.1 |  |  | Coordinate deployment of MHHS solution code to SIT Participants' SIT B environments | 0% | Tue 27/08/24 | Tue 27/08/24 | 0 days | Tue 27/08/24 | Tue 27/08/24 | 992SS |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.21 | Yes | Simon Berry
6 | 1.4.1.7.5.5 |  |  | SIT Operational Test Readiness Report | 0% | Mon 05/08/24 | Wed 18/09/24 | 33 days | Mon 05/08/24 | Mon 03/03/25 |  |  | 0 days | -118 days | -118 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.1.7.5.5.1 |  |  | PP SIT Operational Test Readiness Report | 0% | Mon 05/08/24 | Mon 05/08/24 | 0 days | Mon 05/08/24 | Mon 03/02/25 |  |  | 0 days | -131 days | -131 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.5.5.1.1 |  |  | Test Readiness Report submitted to Programme for assurance | 0% | Mon 05/08/24 | Mon 05/08/24 | 0 days | Tue 07/01/25 | Mon 03/02/25 |  | 999 | -111 days | -131 days | -20 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.4.1.7.5.5.2 |  |  | SI SIT Operational Test Readiness Report | 0% | Mon 05/08/24 | Wed 18/09/24 | 33 days | Tue 07/01/25 | Mon 03/03/25 |  |  | -111 days | -118 days | -7 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.1.7.5.5.2.1 |  |  | Assure Test Participants' Test Readiness Reports | 0% | Mon 05/08/24 | Fri 06/09/24 | 25 days | Tue 07/01/25 | Mon 24/02/25 | 997 | 1000SS+10 days | -111 days | -121 days | -10 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.5.5.2.2 |  |  | Develop Overarching SIT Operational Test Readiness Report | 0% | Mon 19/08/24 | Wed 11/09/24 | 18 days | Tue 28/01/25 | Mon 24/02/25 | 999SS+10 days | 1001 | -116 days | -118 days | -2 days | SI Test |  |  |  | 5 | Yes | Lee Cox
8 | 1.4.1.7.5.5.2.3 |  |  | Artefact review (via SITAG) and updates | 0% | Thu 12/09/24 | Wed 18/09/24 | 5 days | Tue 25/02/25 | Mon 03/03/25 | 1000 | 1002FS+5 days | -118 days | -118 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
6 | 1.4.1.7.5.6 | T2-TE-0750 | SITAG | SIT Operational Testing Preparation Complete | 0% | Wed 25/09/24 | Wed 25/09/24 | 0 days | Wed 25/09/24 | Wed 25/09/24 | 1001FS+5 days,364,977,983,989 | 1066FS+8 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5.1 | Yes | Lee Cox
3 | 1.4.2 |  |  | SIT Execution | 10% | Mon 30/10/23 | Fri 25/04/25 | 390 days | Mon 30/10/23 | Fri 25/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.4.2.1 | T1-TE-1000 | PSG | System Integration Testing Start (M9) | 100% | Mon 30/10/23 | Mon 30/10/23 | 0 days | Mon 30/10/23 | Mon 30/10/23 | 636FS+5 days,527,550 | 1006,2079,2034FS-40 days | 0 days | 0 days | 0 days | CPT | PMO |  |  | 5.11 | Yes | Lee Cox
4 | 1.4.2.2 |  |  | SIT Component Integration Testing | 99% | Mon 30/10/23 | Mon 11/03/24 | 96 days | Mon 30/10/23 | Fri 08/03/24 |  |  | 0 days | 1 day | 1 day | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.2.2.1 |  |  | SIT Component Integration Testing Start | 100% | Mon 30/10/23 | Mon 30/10/23 | 0 days | Mon 30/10/23 | Mon 30/10/23 | 1004 |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.11 | Yes | Lee Cox
5 | 1.4.2.2.2 | T3-TE-0060 | SITAG | Component Integration Testing Interval 1 Start | 100% | Mon 30/10/23 | Mon 30/10/23 | 0 days | Mon 30/10/23 | Mon 30/10/23 | 636SS+1 day,557,561,565,115 | 1013SS | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.11 | Yes | Lee Cox
5 | 1.4.2.2.3 | T3-TE-0061 | SITAG | Component Integration Testing Interval 2 Start | 100% | Mon 13/11/23 | Mon 13/11/23 | 0 days | Mon 13/11/23 | Mon 13/11/23 | 663SS+5 days,557,565,561,115 |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.12 | Yes | Lee Cox
5 | 1.4.2.2.4 | T3-TE-0062 | SITAG | Component Integration Testing Interval 3 Start | 100% | Mon 27/11/23 | Mon 27/11/23 | 0 days | Mon 27/11/23 | Mon 27/11/23 | 695SS+5 days,557,561,565,115 |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.2.2.5 | T3-TE-0063 | SITAG | Component Integration Testing Interval 4 Start | 100% | Mon 11/12/23 | Mon 11/12/23 | 0 days | Mon 11/12/23 | Mon 11/12/23 | 727SS+5 days,557,561,565,115 |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.2.2.6 | T3-TE-0064 |  | Component Integration Testing Interval 5 Start | 100% | Mon 15/01/24 | Mon 15/01/24 | 0 days | Mon 15/01/24 | Mon 15/01/24 | 759SS+5 days,557,561,565,115 |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.2.2.7 | T3-TE-0065 | SITAG | Component Integration Testing Interval 6 Start | 100% | Mon 29/01/24 | Mon 29/01/24 | 0 days | Mon 29/01/24 | Mon 29/01/24 | 5.5756e+17 |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.2.2.8 |  |  | SIT Component Integration Testing Execution | 100% | Mon 30/10/23 | Fri 23/02/24 | 85 days | Mon 30/10/23 | Fri 23/02/24 | 1007SS | 1014FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.2.2.9 | T3-TE-0032 | SITAG | SIT Component Integration Testing End (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 100% | Fri 23/02/24 | Fri 23/02/24 | 0 days | Fri 23/02/24 | Fri 23/02/24 | 1013FF | 1017FF,1015FF+5 days | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.19 | Yes | Lee Cox
5 | 1.4.2.2.10 |  |  | Assurance of PPs Test Completion Reports | 100% | Mon 22/01/24 | Fri 01/03/24 | 30 days | Mon 22/01/24 | Fri 01/03/24 | 1014FF+5 days | 1018FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5.19 | Yes | Lee Cox
5 | 1.4.2.2.11 |  |  | SIT CI Test Completion Report | 100% | Wed 07/02/24 | Fri 01/03/24 | 18 days | Wed 07/02/24 | Fri 01/03/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.2.2.11.1 |  |  | Develop document | 100% | Wed 07/02/24 | Fri 23/02/24 | 13 days | Wed 07/02/24 | Fri 23/02/24 | 1014FF | 1018 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5.19 | Yes | Lee Cox
6 | 1.4.2.2.11.2 |  |  | Review & agree document | 100% | Mon 26/02/24 | Fri 01/03/24 | 5 days | Mon 26/02/24 | Fri 01/03/24 | 1017,1015FF | 1019FS+6 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5.19 | Yes | Lee Cox
5 | 1.4.2.2.12 | T2-TE-0600 | SITAG | SIT Component Integration Testing Test Completion Report Approved | 100% | Mon 11/03/24 | Mon 11/03/24 | 0 days | Fri 08/03/24 | Fri 08/03/24 | 1018FS+6 days | 10771022 | 1 day | 1 day | 0 days | SI Test | PP |  |  | 5.18 | Yes | Lee Cox
4 | 1.4.2.3 |  |  | SIT - Minimum Viable Cohort (MVC) | 4% | Mon 11/03/24 | Fri 07/02/25 | 240 days | Mon 11/03/24 | Fri 07/02/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.2.3.1 |  |  | SIT Functional Testing (MVC) | 9% | Mon 11/03/24 | Fri 17/01/25 | 225 days | Mon 11/03/24 | Fri 17/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.2.3.1.1 | T3-TE-0034 | SITAG | SIT Functional Testing Start | 100% | Mon 11/03/24 | Mon 11/03/24 | 0 days | Mon 11/03/24 | Mon 11/03/24 | 1019,862FS+5 days,797,805,806,807,814 | 1025SS-1 day | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.1.2 |  |  | SIT Functional Testing Execution (Minimum Viable Cohort) | 9% | Mon 11/03/24 | Fri 17/01/25 | 225 days | Mon 11/03/24 | Fri 17/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.2.3.1.2.1 |  |  | Cycle 1 (Full Cycle) | 43% | Mon 11/03/24 | Fri 07/06/24 | 65 days | Mon 11/03/24 | Fri 12/07/24 |  |  | 0 days | -25 days | -25 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.2.3.1.2.1.1 |  |  | Test Execution | 51% | Mon 11/03/24 | Fri 24/05/24 | 55 days | Mon 11/03/24 | Fri 28/06/24 | 1022SS-1 day,837 | 1026,1082SS | 0 days | -25 days | -25 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.2.3.1.2.1.2 |  |  | Defect resolution, assurance, review, data & environments maintenance | 0% | Mon 27/05/24 | Fri 07/06/24 | 10 days | Mon 01/07/24 | Fri 12/07/24 | 1025 | 10311028 | -25 days | -25 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.3.1.2.2 |  |  | SIT Functional Testing progress risk-assessment | 0% | Mon 10/06/24 | Fri 05/07/24 | 20 days | Mon 15/07/24 | Fri 09/08/24 |  |  | -25 days | -25 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.2.3.1.2.2.1 |  |  | Risk-assessment of SIT Functional progress to assess whether Qualification Testing Execution can start early | 0% | Mon 10/06/24 | Fri 28/06/24 | 15 days | Mon 15/07/24 | Fri 02/08/24 | 1026 | 1029FS+5 days | -25 days | -25 days | 0 days | SI Test | Code Bodies,PP,IPA |  |  | 5 | Yes | Nicola Farley,Lee Cox
8 | 1.4.2.3.1.2.2.2 | T3-TE-0039 | QAG | SITAG decision on early Qualification Testing Execution start | 0% | Fri 05/07/24 | Fri 05/07/24 | 0 days | Fri 09/08/24 | Fri 09/08/24 | 1028FS+5 days |  | -25 days | -25 days | 0 days | SI Test | Code Bodies,PP,IPA |  |  | 5 | Yes | Nicola Farley,Lee Cox
7 | 1.4.2.3.1.2.3 |  |  | Cycle 2 (Defect retests and targeted regression testing) | 0% | Mon 10/06/24 | Fri 30/08/24 | 60 days | Mon 15/07/24 | Fri 20/09/24 |  |  | -25 days | -15 days | 10 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.2.3.1.2.3.1 |  |  | Test Execution | 0% | Mon 10/06/24 | Fri 16/08/24 | 50 days | Mon 15/07/24 | Fri 06/09/24 | 1026842 | 1032,1057FS+5 days | -25 days | -15 days | 10 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.2.3.1.2.3.2 |  |  | Defect resolution, assurance, review, data & environments maintenance | 0% | Mon 19/08/24 | Fri 30/08/24 | 10 days | Mon 09/09/24 | Fri 20/09/24 | 1031 | 10371034 | -15 days | -15 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.3.1.2.4 |  |  | SIT Functional Testing back-up progress risk-assessment | 0% | Mon 02/09/24 | Fri 27/09/24 | 20 days | Mon 23/09/24 | Fri 18/10/24 |  |  | -15 days | -15 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.2.3.1.2.4.1 |  |  | Back-up risk-assessment of SIT Functional progress to assess whether Qualification Execution can start early | 0% | Mon 02/09/24 | Fri 20/09/24 | 15 days | Mon 23/09/24 | Fri 11/10/24 | 1032 | 1035FS+5 days | -15 days | -15 days | 0 days | SI Test | Code Bodies,PP,IPA |  |  | 5 | Yes | Nicola Farley,Lee Cox
8 | 1.4.2.3.1.2.4.2 | T3-TE-0041 | QAG | Back-up SITAG decision on early Qualification Testing Execution start | 0% | Fri 27/09/24 | Fri 27/09/24 | 0 days | Fri 18/10/24 | Fri 18/10/24 | 1034FS+5 days |  | -15 days | -15 days | 0 days | SI Test | Code Bodies,PP,IPA |  |  | 5 | Yes | Nicola Farley,Lee Cox
7 | 1.4.2.3.1.2.5 |  |  | Cycle 3 (Defect retests and targeted regression testing) | 0% | Mon 02/09/24 | Fri 01/11/24 | 45 days | Mon 23/09/24 | Fri 01/11/24 |  |  | -15 days | 0 days | 15 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.2.3.1.2.5.1 |  |  | Test Execution | 0% | Mon 02/09/24 | Fri 18/10/24 | 35 days | Mon 23/09/24 | Fri 18/10/24 | 1032847 | 1038 | -15 days | 0 days | 15 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.2.3.1.2.5.2 |  |  | Defect resolution, assurance, review, data & environments maintenance | 0% | Mon 21/10/24 | Fri 01/11/24 | 10 days | Mon 21/10/24 | Fri 01/11/24 | 1037 | 1040,1039FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.3.1.2.6 | T3-TE-0045 | SITAG | Core Systems Code Freeze | 0% | Fri 01/11/24 | Fri 01/11/24 | 0 days | Fri 01/11/24 | Fri 01/11/24 | 1038FF | 1189FS+1 day | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.3.1.2.7 |  |  | Regression Testing (code freeze) | 0% | Mon 04/11/24 | Fri 03/01/25 | 45 days | Mon 04/11/24 | Fri 03/01/25 | 1038852 | 1041FF | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.3.1.2.8 | T3-TE-0046 | SITAG | SIT Functional Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | Fri 03/01/25 | Fri 03/01/25 | 0 days | Fri 03/01/25 | Fri 03/01/25 | 1040FF | 1044FF,1042FF+5 days | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.3.1.2.9 |  |  | Assurance of PPs Test Completion Reports | 0% | Mon 02/12/24 | Fri 10/01/25 | 30 days | Mon 02/12/24 | Fri 10/01/25 | 1041FF+5 days | 1045FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.3.1.2.10 |  |  | SIT Functional Test Completion Report (Minimum Viable Cohort) | 0% | Mon 16/12/24 | Fri 10/01/25 | 20 days | Mon 16/12/24 | Fri 10/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.2.3.1.2.10.1 |  |  | Develop document | 0% | Mon 16/12/24 | Fri 03/01/25 | 15 days | Mon 16/12/24 | Fri 03/01/25 | 1041FF | 1045 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
8 | 1.4.2.3.1.2.10.2 |  |  | Review & agree document | 0% | Mon 06/01/25 | Fri 10/01/25 | 5 days | Mon 06/01/25 | Fri 10/01/25 | 1044,1042FF | 1046FF+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.3.1.2.11 | T2-TE-0850 | SITAG | SIT Functional Testing Test Completion Report (Minimum Viable Cohort) Approved | 0% | Fri 17/01/25 | Fri 17/01/25 | 0 days | Fri 17/01/25 | Fri 17/01/25 | 1045FF+5 days | 1077,1569FS+1 day | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.2.3.2 |  |  | SIT Migration Testing (MVC) | 0% | Mon 10/06/24 | Fri 18/10/24 | 95 days | Mon 10/06/24 | Fri 18/10/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.2.3.2.1 | T3-TE-0038 | SITAG | SIT Migration Testing Start | 0% | Mon 10/06/24 | Mon 10/06/24 | 0 days | Mon 10/06/24 | Mon 10/06/24 | 914FS+5 days,869,873,880,886,892 | 1049SS,1099SS | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.2.2 |  |  | SIT Migration Testing Execution (Minimum Viable Cohort) | 0% | Mon 10/06/24 | Fri 04/10/24 | 85 days | Mon 10/06/24 | Fri 04/10/24 | 1048SS | 1050FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.2.3 | T3-TE-0043 | SITAG | SIT Migration Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | Fri 04/10/24 | Fri 04/10/24 | 0 days | Fri 04/10/24 | Fri 04/10/24 | 1049FF | 1053FF,1051FF+5 days | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.2.4 |  |  | Assurance of PPs Test Completion Reports | 0% | Mon 02/09/24 | Fri 11/10/24 | 30 days | Mon 02/09/24 | Fri 11/10/24 | 1050FF+5 days | 1054FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.2.5 |  |  | SIT Migration Testing Test Completion Report (Minimum Viable Cohort) | 0% | Mon 16/09/24 | Fri 11/10/24 | 20 days | Mon 16/09/24 | Fri 11/10/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.2.3.2.5.1 |  |  | Develop document | 0% | Mon 16/09/24 | Fri 04/10/24 | 15 days | Mon 16/09/24 | Fri 04/10/24 | 1050FF | 1054 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.3.2.5.2 |  |  | Review & agree document | 0% | Mon 07/10/24 | Fri 11/10/24 | 5 days | Mon 07/10/24 | Fri 11/10/24 | 1053,1051FF | 1055FF+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.2.6 | T2-TE-0800 | SITAG | SIT Migration Testing Test Completion Report (Minimum Viable Cohort) Approved | 0% | Fri 18/10/24 | Fri 18/10/24 | 0 days | Fri 18/10/24 | Fri 18/10/24 | 1054FF+5 days | 1077 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.2.3.3 |  |  | SIT Non-Functional Testing (MVC) | 0% | Mon 02/09/24 | Fri 17/01/25 | 100 days | Mon 02/09/24 | Fri 17/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.2.3.3.1 | T3-TE-0040 | SITAG | SIT Non-Functional Testing Start | 0% | Mon 02/09/24 | Mon 02/09/24 | 0 days | Mon 02/09/24 | Mon 02/09/24 | 959FS+5 days,1031FS+5 days,921,925,932,938,944 | 1058SS,1107SS | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.3.2 |  |  | SIT Non-Functional Testing Execution (Minimum Viable Cohort) | 0% | Mon 02/09/24 | Fri 03/01/25 | 90 days | Mon 02/09/24 | Fri 03/01/25 | 1057SS | 1059FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.3.3 | T3-TE-0047 | SITAG | SIT Non-Functional Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | Fri 03/01/25 | Fri 03/01/25 | 0 days | Fri 03/01/25 | Fri 03/01/25 | 1058FF | 1062FF,1060FF+5 days | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.3.4 |  |  | Assurance of PPs Test Completion Reports | 0% | Mon 02/12/24 | Fri 10/01/25 | 30 days | Mon 02/12/24 | Fri 10/01/25 | 1059FF+5 days | 1063FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.3.5 |  |  | SIT Non-Functional Testing Test Completion Report (Minimum Viable Cohort) | 0% | Mon 16/12/24 | Fri 10/01/25 | 20 days | Mon 16/12/24 | Fri 10/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.2.3.3.5.1 |  |  | Develop document | 0% | Mon 16/12/24 | Fri 03/01/25 | 15 days | Mon 16/12/24 | Fri 03/01/25 | 1059FF | 1063 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.3.3.5.2 |  |  | Review & agree document | 0% | Mon 06/01/25 | Fri 10/01/25 | 5 days | Mon 06/01/25 | Fri 10/01/25 | 1062,1060FF | 1064FF+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.3.6 | T2-TE-0900 | SITAG | SIT Non-Functional Testing Test Completion Report (Minimum Viable Cohort) Approved | 0% | Fri 17/01/25 | Fri 17/01/25 | 0 days | Fri 17/01/25 | Fri 17/01/25 | 1063FF+5 days | 1077 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.2.3.4 |  |  | SIT Operational Testing (MVC) | 0% | Mon 07/10/24 | Fri 07/02/25 | 89 days | Mon 07/10/24 | Fri 07/02/25 |  |  | 1 day | 0 days | -1 day | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.2.3.4.1 | T3-TE-0042 | SITAG | SIT Operational Testing Start | 0% | Mon 07/10/24 | Mon 07/10/24 | 0 days | Mon 07/10/24 | Mon 07/10/24 | 1002FS+8 days,966,970,977,983,989 | 1067SS,1115SS | 1 day | 1 day | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.4.2 |  |  | SIT Operational Testing Execution (Minimum Viable Cohort) | 0% | Tue 08/10/24 | Fri 24/01/25 | 79 days | Mon 07/10/24 | Fri 24/01/25 | 1066SS | 1068FF | 1 day | 0 days | -1 day | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.4.3 | T3-TE-0050 | SITAG | SIT Operational Testing End (Minimum Viable Cohort) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | Fri 24/01/25 | Fri 24/01/25 | 0 days | Fri 24/01/25 | Fri 24/01/25 | 1067FF | 1071FF,1069FF+5 days | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.4.4 |  |  | Assurance of PPs Test Completion Reports | 0% | Mon 23/12/24 | Fri 31/01/25 | 30 days | Mon 23/12/24 | Fri 31/01/25 | 1068FF+5 days | 1072FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.4.5 |  |  | SIT Operational Testing Test Completion Report (Minimum Viable Cohort) | 0% | Mon 06/01/25 | Fri 31/01/25 | 20 days | Mon 06/01/25 | Fri 31/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.2.3.4.5.1 |  |  | Develop document | 0% | Mon 06/01/25 | Fri 24/01/25 | 15 days | Mon 06/01/25 | Fri 24/01/25 | 1068FF | 1072,1075FF | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.3.4.5.2 |  |  | Review & agree document | 0% | Mon 27/01/25 | Fri 31/01/25 | 5 days | Mon 27/01/25 | Fri 31/01/25 | 1071,1069FF | 1073FF+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.4.6 | T2-TE-0950 | SITAG | SIT Operational Testing Test Completion Report (Minimum Viable Cohort) Approved | 0% | Fri 07/02/25 | Fri 07/02/25 | 0 days | Fri 07/02/25 | Fri 07/02/25 | 1072FF+5 days | 1077 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.2.3.5 |  |  | SIT MVC Test Exit Report | 0% | Mon 06/01/25 | Fri 31/01/25 | 20 days | Mon 06/01/25 | Fri 31/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.2.3.5.1 |  |  | Develop document | 0% | Mon 06/01/25 | Fri 24/01/25 | 15 days | Mon 06/01/25 | Fri 24/01/25 | 1071FF | 1076 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.3.5.2 |  |  | Review & agree document | 0% | Mon 27/01/25 | Fri 31/01/25 | 5 days | Mon 27/01/25 | Fri 31/01/25 | 1075 | 1077FS+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
5 | 1.4.2.3.6 | T1-TE-2000 | PSG | SIT Minimum Viable Cohort Complete (SIT Minimum Viable Cohort Test Exit Report Approved) | 0% | Fri 07/02/25 | Fri 07/02/25 | 0 days | Fri 07/02/25 | Fri 07/02/25 | 1076FS+5 days,1019,1046,1055,1064,1073 | 1890,1926FS+21 days,1894,1896,1898,1607 | 0 days | 0 days | 0 days | CPT | PP,IPA |  |  | 5 | Yes | Lee Cox
4 | 1.4.2.4 |  |  | SIT - Other Participants | 2% | Mon 11/03/24 | Fri 25/04/25 | 295 days | Mon 11/03/24 | Fri 25/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.2.4.1 |  |  | SIT Functional Testing (Other Participants) | 6% | Mon 11/03/24 | Fri 25/04/25 | 295 days | Mon 11/03/24 | Fri 25/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.2.4.1.1 |  |  | SIT Functional Testing Execution (Other Participants) | 6% | Mon 11/03/24 | Fri 04/04/25 | 280 days | Mon 11/03/24 | Fri 04/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.2.4.1.1.1 |  |  | Cycle 1 (Full Cycle) | 28% | Mon 11/03/24 | Fri 07/06/24 | 65 days | Mon 11/03/24 | Fri 12/07/24 |  |  | 0 days | -25 days | -25 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.2.4.1.1.1.1 |  |  | Test Execution | 33% | Mon 11/03/24 | Fri 24/05/24 | 55 days | Mon 11/03/24 | Fri 28/06/24 | 1025SS,128 | 1083 | 0 days | -25 days | -25 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.2.4.1.1.1.2 |  |  | Defect resolution, assurance, review, data & environments maintenance | 0% | Mon 27/05/24 | Fri 07/06/24 | 10 days | Mon 01/07/24 | Fri 12/07/24 | 1082 | 1085 | -25 days | -25 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.4.1.1.2 |  |  | Cycle 2 (Defect retests and targeted regression testing) | 0% | Mon 10/06/24 | Fri 30/08/24 | 60 days | Mon 15/07/24 | Fri 20/09/24 |  |  | -25 days | -15 days | 10 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.2.4.1.1.2.1 |  |  | Test Execution | 0% | Mon 10/06/24 | Fri 16/08/24 | 50 days | Mon 15/07/24 | Fri 06/09/24 | 1083132136 | 1086 | -25 days | -15 days | 10 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.2.4.1.1.2.2 |  |  | Defect resolution, assurance, review, data & environments maintenance | 0% | Mon 19/08/24 | Fri 30/08/24 | 10 days | Mon 09/09/24 | Fri 20/09/24 | 1085 | 1088 | -15 days | -15 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.4.1.1.3 |  |  | Cycle 3 (Defect retests and targeted regression testing) | 0% | Mon 02/09/24 | Fri 01/11/24 | 45 days | Mon 23/09/24 | Fri 01/11/24 |  |  | -15 days | 0 days | 15 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.4.2.4.1.1.3.1 |  |  | Test Execution | 0% | Mon 02/09/24 | Fri 18/10/24 | 35 days | Mon 23/09/24 | Fri 18/10/24 | 1086140 | 1089 | -15 days | 0 days | 15 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
8 | 1.4.2.4.1.1.3.2 |  |  | Defect resolution, assurance, review, data & environments maintenance | 0% | Mon 21/10/24 | Fri 01/11/24 | 10 days | Mon 21/10/24 | Fri 01/11/24 | 1088 | 1090 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.4.1.1.4 |  |  | Regression Testing (code freeze) | 0% | Mon 04/11/24 | Fri 03/01/25 | 45 days | Mon 04/11/24 | Fri 03/01/25 | 1089 | 1091 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.4.1.1.5 |  |  | SIT Other PPs continued support | 0% | Mon 06/01/25 | Fri 04/04/25 | 65 days | Mon 06/01/25 | Fri 04/04/25 | 1090 | 1092FF | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.1.2 | T3-TE-0052 | SITAG | SIT Functional Testing End (Other Participants) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | Fri 04/04/25 | Fri 04/04/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 1091FF | 1095FF,1093FS+5 days | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.1.3 |  |  | Assurance of PPs Test Completion Reports | 0% | Mon 14/04/25 | Fri 18/04/25 | 5 days | Mon 14/04/25 | Fri 18/04/25 | 1092FS+5 days | 1096FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.1.4 |  |  | SIT Functional Testing Test Completion Report (Other Participants) | 0% | Mon 17/03/25 | Fri 18/04/25 | 25 days | Mon 17/03/25 | Fri 18/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.2.4.1.4.1 |  |  | Develop document | 0% | Mon 17/03/25 | Fri 04/04/25 | 15 days | Mon 17/03/25 | Fri 04/04/25 | 1092FF | 1096 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.4.1.4.2 |  |  | Review & agree document | 0% | Mon 14/04/25 | Fri 18/04/25 | 5 days | Mon 14/04/25 | Fri 18/04/25 | 1095,1093FF | 1097FF+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.1.5 | T3-TE-0055 | SITAG | SIT Functional Testing Test Completion Report (Other Participants) Approved | 0% | Fri 25/04/25 | Fri 25/04/25 | 0 days | Fri 25/04/25 | Fri 25/04/25 | 1096FF+5 days | 1125 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.2.4.2 |  |  | SIT Migration Testing (Other Participants) | 0% | Mon 10/06/24 | Fri 25/04/25 | 230 days | Mon 10/06/24 | Fri 25/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.2.4.2.1 |  |  | SIT Migration Testing Execution (Other Participants) | 0% | Mon 10/06/24 | Fri 04/04/25 | 215 days | Mon 10/06/24 | Fri 04/04/25 | 1048SS | 1100FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.2.2 | T3-TE-0051 | SITAG | SIT Migration Testing End (Other Participants) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | Fri 04/04/25 | Fri 04/04/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 1099FF | 1103FF,1101FS+5 days | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.2.3 |  |  | Assurance of PPs Test Completion Reports | 0% | Mon 14/04/25 | Fri 18/04/25 | 5 days | Mon 14/04/25 | Fri 18/04/25 | 1100FS+5 days | 1104FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.2.4 |  |  | SIT Migration Testing Test Completion Report (Other Participants) | 0% | Mon 17/03/25 | Fri 18/04/25 | 25 days | Mon 17/03/25 | Fri 18/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.2.4.2.4.1 |  |  | Develop document | 0% | Mon 17/03/25 | Fri 04/04/25 | 15 days | Mon 17/03/25 | Fri 04/04/25 | 1100FF | 1104 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.4.2.4.2 |  |  | Review & agree document | 0% | Mon 14/04/25 | Fri 18/04/25 | 5 days | Mon 14/04/25 | Fri 18/04/25 | 1103,1101FF | 1105FF+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.2.5 | T3-TE-0056 | SITAG | SIT Migration Testing Test Completion Report (Other Participants) Approved | 0% | Fri 25/04/25 | Fri 25/04/25 | 0 days | Fri 25/04/25 | Fri 25/04/25 | 1104FF+5 days | 1125 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.2.4.3 |  |  | SIT Non-Functional Testing (Other Participants) | 0% | Mon 02/09/24 | Fri 25/04/25 | 170 days | Mon 02/09/24 | Fri 25/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.2.4.3.1 |  |  | SIT Non-Functional Testing Execution (Other Participants) | 0% | Mon 02/09/24 | Fri 04/04/25 | 155 days | Mon 02/09/24 | Fri 04/04/25 | 1057SS | 1108FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.3.2 | T3-TE-0053 | SITAG | SIT Non-Functional Testing End (Other Participants) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | Fri 04/04/25 | Fri 04/04/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 1107FF | 1111FF,1109FS+5 days | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.3.3 |  |  | Assurance of PPs Test Completion Reports | 0% | Mon 14/04/25 | Fri 18/04/25 | 5 days | Mon 14/04/25 | Fri 18/04/25 | 1108FS+5 days | 1112FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.3.4 |  |  | SIT Non-Functional Testing Test Completion Report (Other Participants) | 0% | Mon 17/03/25 | Fri 18/04/25 | 25 days | Mon 17/03/25 | Fri 18/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.2.4.3.4.1 |  |  | Develop document | 0% | Mon 17/03/25 | Fri 04/04/25 | 15 days | Mon 17/03/25 | Fri 04/04/25 | 1108FF | 1112 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.4.3.4.2 |  |  | Review & agree document | 0% | Mon 14/04/25 | Fri 18/04/25 | 5 days | Mon 14/04/25 | Fri 18/04/25 | 1111,1109FF | 1113FF+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.3.5 | T3-TE-0057 | SITAG | SIT Non-Functional Testing Test Completion Report (Other Participants) Approved | 0% | Fri 25/04/25 | Fri 25/04/25 | 0 days | Fri 25/04/25 | Fri 25/04/25 | 1112FF+5 days | 1125 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.2.4.4 |  |  | SIT Operational Testing (Other Participants) | 0% | Tue 08/10/24 | Fri 25/04/25 | 144 days | Mon 07/10/24 | Fri 25/04/25 |  |  | 1 day | 0 days | -1 day | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.2.4.4.1 |  |  | SIT Operational Testing Execution (Other Participants) | 0% | Tue 08/10/24 | Fri 04/04/25 | 129 days | Mon 07/10/24 | Fri 04/04/25 | 1066SS | 1116FF | 1 day | 0 days | -1 day | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.4.2 | T3-TE-0054 | SITAG | SIT Operational Testing End (Other Participants) (incl. confirmation that PPs have submitted their Test Completion Reports to Programme for assurance) | 0% | Fri 04/04/25 | Fri 04/04/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 1115FF | 1119FF,1117FS+5 days | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.4.3 |  |  | Assurance of PPs Test Completion Reports | 0% | Mon 14/04/25 | Fri 18/04/25 | 5 days | Mon 14/04/25 | Fri 18/04/25 | 1116FS+5 days | 1120FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.4.4 |  |  | SIT Operational Testing Test Completion Report (Other Participants) | 0% | Mon 17/03/25 | Fri 18/04/25 | 25 days | Mon 17/03/25 | Fri 18/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.4.2.4.4.4.1 |  |  | Develop document | 0% | Mon 17/03/25 | Fri 04/04/25 | 15 days | Mon 17/03/25 | Fri 04/04/25 | 1116FF | 1120,1123FF | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
7 | 1.4.2.4.4.4.2 |  |  | Review & agree document | 0% | Mon 14/04/25 | Fri 18/04/25 | 5 days | Mon 14/04/25 | Fri 18/04/25 | 1119,1117FF | 1121FF+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.4.5 | T3-TE-0058 | SITAG | SIT Operational Testing Test Completion Report (Other Participants) Approved | 0% | Fri 25/04/25 | Fri 25/04/25 | 0 days | Fri 25/04/25 | Fri 25/04/25 | 1120FF+5 days | 1125 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
5 | 1.4.2.4.5 |  |  | SIT Other Participants Test Exit Report | 0% | Mon 17/03/25 | Fri 11/04/25 | 20 days | Mon 17/03/25 | Fri 11/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.2.4.5.1 |  |  | Develop document | 0% | Mon 17/03/25 | Fri 04/04/25 | 15 days | Mon 17/03/25 | Fri 04/04/25 | 1119FF | 1124 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Lee Cox
6 | 1.4.2.4.5.2 |  |  | Review & agree document | 0% | Mon 07/04/25 | Fri 11/04/25 | 5 days | Mon 07/04/25 | Fri 11/04/25 | 1123 | 1125FS+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Lee Cox
5 | 1.4.2.4.6 | T3-TE-0059 | SITAG | SIT - Other Participants Complete | 0% | Mon 21/04/25 | Mon 21/04/25 | 0 days | Mon 21/04/25 | Mon 21/04/25 | 1124FS+5 days,1097,1105,1113,1121 | 1609 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Lee Cox
3 | 1.4.3 |  |  | E2E Sandbox Testing Preparation | 9% | Mon 31/10/22 | Fri 06/06/25 | 680 days | Mon 31/10/22 | Fri 06/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.4.3.1 |  |  | Test Artefact Development | 0% | Wed 01/03/23 | Thu 18/07/24 | 361 days | Wed 01/03/23 | Fri 04/08/23 |  |  | 0 days | 248 days | 248 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.3.1.1 |  |  | E2E Sandbox Guidance | 0% | Wed 01/03/23 | Thu 18/07/24 | 361 days | Wed 01/03/23 | Fri 04/08/23 |  |  | 0 days | 248 days | 248 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.3.1.1.1 |  |  | Develop document | 0% | Wed 01/03/23 | Fri 23/06/23 | 83 days | Wed 01/03/23 | Fri 23/06/23 |  | 1130,1133SS+20 days | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Stuart Scott
6 | 1.4.3.1.1.2 |  |  | Artefact review (via SITAG) and updates | 0% | Mon 26/06/23 | Fri 28/07/23 | 25 days | Mon 26/06/23 | Fri 28/07/23 | 1129 | 1131FF+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Stuart Scott
6 | 1.4.3.1.1.3 | T3-TE-0067 | QAG | E2E Sandbox Guidance approved | 0% | Thu 18/07/24 | Thu 18/07/24 | 0 days | Fri 04/08/23 | Fri 04/08/23 | 1130FF+5 days |  | 248 days | 248 days | 0 days | SI Test | PP |  |  | 5.22 | Yes | Stuart Scott
5 | 1.4.3.1.2 |  |  | E2E Sandbox Test Data Approach & Plan | 0% | Wed 29/03/23 | Fri 04/08/23 | 93 days | Wed 29/03/23 | Fri 04/08/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.3.1.2.1 |  |  | Develop document | 0% | Wed 29/03/23 | Fri 30/06/23 | 68 days | Wed 29/03/23 | Fri 30/06/23 | 1129SS+20 days | 1134 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Stuart Scott
6 | 1.4.3.1.2.2 |  |  | Review, update & agree document internally | 0% | Mon 03/07/23 | Fri 04/08/23 | 25 days | Mon 03/07/23 | Fri 04/08/23 | 1133 |  | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Stuart Scott
4 | 1.4.3.2 |  |  | UIT Stub Specification and Delivery | 52% | Mon 04/12/23 | Fri 23/08/24 | 190 days | Mon 04/12/23 | Fri 23/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.3.2.1 |  |  | Qualification Test Stubs | 52% | Mon 04/12/23 | Fri 23/08/24 | 190 days | Mon 04/12/23 | Fri 23/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.16 | Yes | N/A
6 | 1.4.3.2.1.1 |  |  | Specify | 100% | Mon 04/12/23 | Thu 01/02/24 | 44 days | Mon 04/12/23 | Thu 01/02/24 | 470FS+13 days | 1138 | 0 days | 0 days | 0 days | SI DevOps | Qualification,SRO |  |  | 5 | Yes | Matthew Bray
6 | 1.4.3.2.1.2 |  |  | Build & Test | 54% | Fri 02/02/24 | Thu 20/06/24 | 100 days | Fri 02/02/24 | Thu 20/06/24 | 1137 | 1139 | 0 days | 0 days | 0 days | SI DevOps | Qualification,SRO |  |  | 5 | Yes | Matthew Bray
6 | 1.4.3.2.1.3 |  |  | UAT | 0% | Fri 21/06/24 | Wed 03/07/24 | 9 days | Fri 21/06/24 | Wed 03/07/24 | 1138 | 1140 | 0 days | 0 days | 0 days | SI Test | Qualification,SRO |  |  | 5 | Yes | Matthew Bray
6 | 1.4.3.2.1.4 |  |  | Beta test | 0% | Thu 04/07/24 | Fri 16/08/24 | 32 days | Thu 04/07/24 | Fri 16/08/24 | 1139 | 1141 | 0 days | 0 days | 0 days | PP | Qualification,SRO |  |  | 5 | Yes | Matthew Bray
6 | 1.4.3.2.1.5 |  |  | Prepare for release | 0% | Mon 19/08/24 | Fri 23/08/24 | 5 days | Mon 19/08/24 | Fri 23/08/24 | 1140 | 1142 | 0 days | 0 days | 0 days | SI DevOps | Qualification,SRO |  |  | 5 | Yes | Matthew Bray
6 | 1.4.3.2.1.6 | T3-TE-0035 | QAG | CSS & SMRS Simulators Released | 0% | Fri 23/08/24 | Fri 23/08/24 | 0 days | Fri 23/08/24 | Fri 23/08/24 | 1141 | 1159 | 0 days | 0 days | 0 days | SI DevOps | Qualification,SRO | Proposed | Name Change | 5 | Yes | Matthew Bray
4 | 1.4.3.3 |  |  | Environments (UIT) | 0% | Mon 31/10/22 | Fri 06/06/25 | 680 days | Mon 31/10/22 | Fri 06/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.3.3.1 |  |  | Central Party Environments (UIT) | 0% | Wed 16/11/22 | Fri 04/10/24 | 493 days | Wed 16/11/22 | Fri 04/10/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.3.3.1.1 |  |  | Central Parties' environment preparation (incl. security certificates and security compliance) | 0% | Wed 16/11/22 | Fri 23/08/24 | 463 days | Wed 16/11/22 | Fri 23/08/24 | 466 | 1146SS,1156SS,1178SS | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
6 | 1.4.3.3.1.2 |  |  | Submit self-declaration of environment preparation complete (incl. security certificates and security compliance) to Programme for assurance | 0% | Wed 16/11/22 | Fri 23/08/24 | 463 days | Wed 16/11/22 | Fri 23/08/24 | 1145SS | 1158SS | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
6 | 1.4.3.3.1.3 |  |  | Central Parties' UIT environment connectivity proving | 0% | Tue 27/08/24 | Fri 20/09/24 | 19 days | Tue 27/08/24 | Fri 20/09/24 | 1159FS+1 day | 1160SS,1148FF | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
6 | 1.4.3.3.1.4 |  |  | Deployment of MHHS solution code to UIT environments | 0% | Mon 09/09/24 | Fri 20/09/24 | 10 days | Mon 09/09/24 | Fri 20/09/24 | 1147FF | 1161SS,1149 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
6 | 1.4.3.3.1.5 |  |  | Central Parties' UIT environment Regression Testing | 0% | Mon 23/09/24 | Fri 04/10/24 | 10 days | Mon 23/09/24 | Fri 04/10/24 | 1148 | 1162SS,1165FF | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
5 | 1.4.3.3.2 |  |  | E2E Sandbox Participants (UIT) | 0% | Mon 31/10/22 | Fri 06/06/25 | 680 days | Mon 31/10/22 | Fri 06/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.3.3.2.1 |  |  | E2E Sandbox Participants environment preparation (incl. security certificates and security compliance) | 0% | Mon 31/10/22 | Fri 09/05/25 | 660 days | Mon 31/10/22 | Fri 09/05/25 | 1599FF-2 mons | 1178SS,1157SS | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
6 | 1.4.3.3.2.2 |  |  | Submit self-declaration of environment preparation complete (incl. security certificates and security compliance) to Programme for assurance | 0% | Mon 31/10/22 | Fri 09/05/25 | 660 days | Mon 31/10/22 | Fri 09/05/25 |  | 1158SS,1153 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
6 | 1.4.3.3.2.3 |  |  | E2E Sandbox Participants UIT environment connectivity proving | 0% | Mon 12/05/25 | Fri 06/06/25 | 20 days | Mon 12/05/25 | Fri 06/06/25 | 1152 | 1160SS,1154FF | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
6 | 1.4.3.3.2.4 |  |  | Deployment of MHHS solution code to UIT environments | 0% | Mon 26/05/25 | Fri 06/06/25 | 10 days | Mon 26/05/25 | Fri 06/06/25 | 1153FF | 1161SS | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
5 | 1.4.3.3.3 |  |  | SI Environments (UIT) | 0% | Mon 31/10/22 | Fri 06/06/25 | 680 days | Mon 31/10/22 | Fri 06/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.3.3.3.1 |  |  | Coordinate Central Parties' UIT environment preparation | 0% | Wed 16/11/22 | Fri 23/08/24 | 463 days | Wed 16/11/22 | Fri 23/08/24 | 1145SS |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Simon Berry
6 | 1.4.3.3.3.2 |  |  | Coordinate E2E Sandbox Participants' UIT environment preparation (for E2E Sandbox Testing Start) | 0% | Mon 31/10/22 | Wed 07/08/24 | 463 days | Mon 31/10/22 | Wed 07/08/24 | 1151SS |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Simon Berry
6 | 1.4.3.3.3.3 |  |  | Assure Central Parties' self-declaration of environment preparation complete (incl. security certificates and security compliance) | 0% | Wed 16/11/22 | Fri 23/08/24 | 463 days | Wed 16/11/22 | Fri 23/08/24 | 1146SS,1152SS | 1159 | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Simon Berry
6 | 1.4.3.3.3.4 | T3-TE-0044 | QAG | Central Parties' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Fri 23/08/24 | Fri 23/08/24 | 0 days | Fri 23/08/24 | Fri 23/08/24 | 11581142 | 1147FS+1 day | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Simon Berry
6 | 1.4.3.3.3.5 |  |  | Coordinate Central Parties' UIT environment connectivity proving | 0% | Mon 12/05/25 | Thu 05/06/25 | 19 days | Mon 12/05/25 | Thu 05/06/25 | 1147SS,1153SS |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Simon Berry
6 | 1.4.3.3.3.6 |  |  | Coordinate deployment of MHHS solution code to Central Parties' UIT environments | 0% | Mon 26/05/25 | Fri 06/06/25 | 10 days | Mon 26/05/25 | Fri 06/06/25 | 1148SS,1154SS |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Simon Berry
6 | 1.4.3.3.3.7 |  |  | Coordinate Central Parties' UIT environment Regression Testing | 0% | Mon 23/09/24 | Fri 04/10/24 | 10 days | Mon 23/09/24 | Fri 04/10/24 | 1149SS |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Simon Berry
4 | 1.4.3.4 |  |  | Test Data | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.3.4.1 |  |  | Central Parties (for E2E Sandbox & Qualification) | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.3.4.1.1 |  |  | Central Parties' UIT environment test data loading & verification (& data cleansing, if required) | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 | 1149FF | 1170SS,1166SS,1168FF | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
6 | 1.4.3.4.1.2 |  |  | Submit self-declaration to Programme to confirm loading & verification of test data | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 | 1165SS | 1171SS,1181FF-10 days,1182FF | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
5 | 1.4.3.4.2 |  |  | E2E Sandbox Participants | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.3.4.2.1 |  |  | UIT environment test data loading and verification (and data cleansing, if required) (for E2E Sandbox Testing Start) | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 | 1165FF | 1172SS | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Simon Berry
5 | 1.4.3.4.3 |  |  | SI Test Data | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.3.4.3.1 |  |  | Coordinate Central Parties' UIT environment test data loading and verification (and data cleansing, if required) | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 | 1165SS |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Richard Puddephatt
6 | 1.4.3.4.3.2 |  |  | Assure evidence of Central Parties' UIT environment test data load and verification | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 | 1166SS |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Richard Puddephatt
6 | 1.4.3.4.3.3 |  |  | Coordinate E2E Sandbox Participants' UIT environment test data loading and verification (and data cleansing, if required) (for E2E Sandbox Testing Start) | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 | 1168SS |  | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Richard Puddephatt
4 | 1.4.3.5 |  |  | Other Preparation | 59% | Wed 16/11/22 | Mon 23/09/24 | 484 days | Wed 16/11/22 | Mon 23/09/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.3.5.1 |  |  | SI Other Preparation | 0% | Thu 02/05/24 | Thu 01/08/24 | 66 days | Thu 02/05/24 | Thu 01/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.3.5.1.1 |  |  | Onboarding of UIT E2E Sandbox Participants to Test Management Tool for E2E Sandbox Testing Start (onboarding of participants will be ongoing hereafter) | 0% | Thu 02/05/24 | Thu 01/08/24 | 66 days | Thu 02/05/24 | Thu 01/08/24 | 1190SS-132 days | 1177SS | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Stuart Scott
5 | 1.4.3.5.2 |  |  | Other Preparation (for Central Parties & E2E Sandbox Participants) | 67% | Wed 16/11/22 | Mon 23/09/24 | 484 days | Wed 16/11/22 | Mon 23/09/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.3.5.2.1 |  |  | Test Management Tool onboarding for E2E Sandbox Testing Start (onboarding will be ongoing hereafter) | 0% | Thu 02/05/24 | Thu 01/08/24 | 66 days | Thu 02/05/24 | Thu 01/08/24 | 1175SS |  | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Stuart Scott
6 | 1.4.3.5.2.2 |  |  | Other Preparation (incl. test execution planning) | 76% | Wed 16/11/22 | Mon 23/09/24 | 484 days | Wed 16/11/22 | Mon 23/09/24 | 1145SS,1151SS |  | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Stuart Scott
4 | 1.4.3.6 |  |  | UIT E2E Sandbox Test Readiness Report | 0% | Mon 26/08/24 | Fri 25/10/24 | 45 days | Mon 26/08/24 | Fri 25/10/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.3.6.1 |  |  | Central Parties E2E Sandbox Test Readiness Report | 0% | Mon 26/08/24 | Fri 04/10/24 | 30 days | Mon 26/08/24 | Fri 04/10/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.3.6.1.1 |  |  | Develop draft Test Readiness Report and submit to Programme for assurance | 0% | Mon 26/08/24 | Fri 20/09/24 | 20 days | Mon 26/08/24 | Fri 20/09/24 | 1166FF-10 days | 1184SS | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Stuart Scott
6 | 1.4.3.6.1.2 |  |  | Finalise Test Readiness Report and submit to Programme for assurance | 0% | Mon 23/09/24 | Fri 04/10/24 | 10 days | Mon 23/09/24 | Fri 04/10/24 | 1166FF | 1184FF+5 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Stuart Scott
5 | 1.4.3.6.2 |  |  | SI E2E Sandbox Test Readiness Report | 0% | Mon 26/08/24 | Fri 18/10/24 | 40 days | Mon 26/08/24 | Fri 18/10/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.4.3.6.2.1 |  |  | Assure Central Parties' E2E Sandbox Test Readiness Reports | 0% | Mon 26/08/24 | Fri 11/10/24 | 35 days | Mon 26/08/24 | Fri 11/10/24 | 1181SS,1182FF+5 days | 1185FF | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Stuart Scott
6 | 1.4.3.6.2.2 |  |  | Develop Overarching E2E Sandbox Test Readiness Report | 0% | Mon 16/09/24 | Fri 11/10/24 | 20 days | Mon 16/09/24 | Fri 11/10/24 | 1184FF | 1186 | 0 days | 0 days | 0 days | SI Test |  |  |  | 5 | Yes | Stuart Scott
6 | 1.4.3.6.2.3 |  |  | Artefact review (via SITAG) and updates | 0% | Mon 14/10/24 | Fri 18/10/24 | 5 days | Mon 14/10/24 | Fri 18/10/24 | 1185 | 1187FS+5 days | 0 days | 0 days | 0 days | SI Test | PP,IPA |  |  | 5 | Yes | Stuart Scott
5 | 1.4.3.6.3 | T3-TE-0048 | QAG | UIT E2E Sandbox Preparation Complete | 0% | Fri 25/10/24 | Fri 25/10/24 | 0 days | Fri 25/10/24 | Fri 25/10/24 | 1186FS+5 days | 1189FS+5 days | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Stuart Scott
3 | 1.4.4 |  |  | SIT PPs E2E Sandbox Testing Execution | 0% | Mon 04/11/24 | Mon 19/01/26 | 316 days | Mon 04/11/24 | Mon 19/01/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.4.4.1 | T3-TE-0049 | QAG | SIT PPs E2E Sandbox Testing Start | 0% | Mon 04/11/24 | Mon 04/11/24 | 0 days | Mon 04/11/24 | Mon 04/11/24 | 1039FS+1 day,1187FS+5 days | 1190SS-1 day | 0 days | 0 days | 0 days | SI Test | PP |  |  | 5 | Yes | Stuart Scott
4 | 1.4.4.2 |  |  | SIT PPs E2E Sandbox Testing Execution | 0% | Mon 04/11/24 | Mon 19/01/26 | 316 days | Mon 04/11/24 | Mon 19/01/26 | 1189SS-1 day,1600FF | 1175SS-132 days | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes | Stuart Scott
3 | 1.4.5 |  |  | External Programme Dependency Management | 100% | Mon 31/10/22 | Fri 30/06/23 | 174 days | Mon 31/10/22 | Fri 30/06/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.4.5.1 |  |  | BSC CP1558 | 100% | Mon 31/10/22 | Thu 29/06/23 | 173 days | Mon 31/10/22 | Thu 29/06/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.5.1.1 |  |  | Monitor progress to implementation date | 100% | Mon 31/10/22 | Wed 28/06/23 | 173 days | Mon 31/10/22 | Wed 28/06/23 |  | 1194 | 0 days | 0 days | 0 days | CPT | Code Bodies |  |  | 5 | Yes | Andrew Margan
5 | 1.4.5.1.2 |  |  | BSC CP1558 Implementation Date | 100% | Thu 29/06/23 | Thu 29/06/23 | 0 days | Thu 29/06/23 | Thu 29/06/23 | 1193 |  | 0 days | 0 days | 0 days | Code Bodies |  |  |  | 5 | Yes | Andrew Margan
4 | 1.4.5.2 |  |  | REC CP R0032 | 100% | Mon 31/10/22 | Fri 30/06/23 | 174 days | Mon 31/10/22 | Fri 30/06/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.5.2.1 |  |  | Monitor progress to implementation date | 100% | Mon 31/10/22 | Thu 29/06/23 | 174 days | Mon 31/10/22 | Thu 29/06/23 |  | 1197 | 0 days | 0 days | 0 days | CPT | Code Bodies |  |  | 5 | Yes | Andrew Margan
5 | 1.4.5.2.2 |  |  | REC CP R0032 Implementation Date | 100% | Fri 30/06/23 | Fri 30/06/23 | 0 days | Fri 30/06/23 | Fri 30/06/23 | 1196 |  | 0 days | 0 days | 0 days | Code Bodies |  |  |  | 5 | Yes | Andrew Margan
4 | 1.4.5.3 |  |  | REC CP R0044 | 100% | Mon 31/10/22 | Thu 29/06/23 | 173 days | Mon 31/10/22 | Thu 29/06/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.4.5.3.1 |  |  | Monitor progress to implementation date | 100% | Mon 31/10/22 | Wed 28/06/23 | 173 days | Mon 31/10/22 | Wed 28/06/23 |  | 1200 | 0 days | 0 days | 0 days | CPT | Code Bodies |  |  | 5 | Yes | Andrew Margan
5 | 1.4.5.3.2 |  |  | REC CP R0044 Implementation Date | 100% | Thu 29/06/23 | Thu 29/06/23 | 0 days | Thu 29/06/23 | Thu 29/06/23 | 1199 |  | 0 days | 0 days | 0 days | Code Bodies |  |  |  | 5 | Yes | Andrew Margan
2 | 1.5 |  |  | NON SIT LDSO QUALIFICATION | 28% | Tue 07/11/23 | Fri 28/02/25 | 344 days | Mon 31/10/22 | Fri 24/01/25 |  |  | 266 days | 25 days | -241 days | N/A | N/A |  |  | 5.18 | Yes | N/A
3 | 1.5.1 |  |  | Approach Planning | 88% | Tue 07/11/23 | Thu 16/05/24 | 138 days | Mon 29/01/24 | Tue 28/05/24 |  |  | -59 days | -8 days | 51 days | N/A | N/A |  |  | 5.18 | Yes | N/A
4 | 1.5.1.1 |  |  | Develop Draft Testing Approach & Plan | 100% | Tue 07/11/23 | Tue 30/01/24 | 61 days | NA | NA |  | 1204,1217SS+60 days,1221SS+75 days,1225SS+96 days,1261,1265FS+3 days,1271,1251 | 0 days | 0 days | 61 days | Non-SIT LDSO | Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.1.2 |  |  | Draft Testing Approach & Plan Issued to LDSO for Review | 100% | Wed 31/01/24 | Wed 31/01/24 | 1 day | NA | NA | 1203 | 1205 | 0 days | 0 days | 1 day | Non-SIT LDSO | Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.1.3 |  |  | LDSO Review Complete | 100% | Thu 01/02/24 | Wed 14/02/24 | 10 days | NA | NA | 1204 | 1206 | 0 days | 0 days | 10 days | LDSOs | Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.1.4 |  |  | Update Following LDSO Review | 100% | Thu 15/02/24 | Tue 05/03/24 | 14 days | NA | NA | 1205 | 1207FS+4 days | 0 days | 0 days | 14 days | Non-SIT LDSO | Non-SIT LDSO, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.1.5 |  |  | QWG Review of Approach & Plan | 100% | Tue 12/03/24 | Tue 12/03/24 | 1 day | NA | NA | 1206FS+4 days | 1208FS+7 days | 0 days | 0 days | 1 day | Non-SIT LDSO, PP | Non-SIT LDSO, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.1.6 |  |  | QAG Approval for Approach & Plan | 100% | Thu 21/03/24 | Thu 21/03/24 | 0 days | NA | NA | 1207FS+7 days | 1209,1239,1241,1245FS+51 days,1243 | 0 days | 0 days | 0 days | Code Bodies | Non-SIT LDSO,Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.1.7 | T3-QU-0011 | QAG (Non-SIT LDSO) | Confirmation of Participants for Non-SIT LDSO Qualification Testing | 100% | Thu 21/03/24 | Thu 21/03/24 | 0 days | Mon 29/01/24 | Mon 29/01/24 | 1208 | 1214 | 39 days | 38 days | 0 days | Non-SIT LDSO | SI Test, PP, IPA |  |  | 5.21 | Yes | Ben Wickins
4 | 1.5.1.8 |  |  | Update to Annex 1 for internal review (NF, Not Operational) | 100% | Mon 18/03/24 | Fri 05/04/24 | 15 days | NA | NA | 918 | 1211 | 0 days | 0 days | 15 days | Non-SIT LDSO | PP, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.1.9 |  |  | Non-Functional, Operational & Migration Approaches Socialised with Code Bodies & LDSO & Feedback Actioned | 38% | Mon 08/04/24 | Mon 06/05/24 | 21 days | NA | NA | 1210 | 1212FS+5 days | 0 days | 0 days | 21 days | Non-SIT LDSO | PP, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.1.10 |  |  | QWG Review Operational, Non-Functional & Migration Annexes of Approach & Plan | 0% | Tue 14/05/24 | Tue 14/05/24 | 1 day | NA | NA | 1211FS+5 days | 1213 | 0 days | 0 days | 1 day | Non-SIT LDSO, PP | Non-SIT LDSO, PP, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.1.11 |  |  | Update Following QWG Review | 0% | Wed 15/05/24 | Wed 15/05/24 | 1 day | NA | NA | 1212 | 1214FS+1 day | 0 days | 0 days | 1 day | Non-SIT LDSO, PP | Non-SIT LDSO, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.1.12 | TBC | QAG (Non-SIT LDSO) | QAG Approval for Operational, Non-Functional & Migration Annexes of Approach & Plan | 0% | Thu 16/05/24 | Thu 16/05/24 | 0 days | Tue 28/05/24 | Tue 28/05/24 | 1213FS+1 day,1209,921 | 1288 | -7 days | -8 days | -1 day | Code Bodies | Non-SIT LDSO, Code Bodies | Proposed | New | 5.18 | Yes | Ben Wickins
3 | 1.5.2 |  |  | Functional Test Cases & Scenarios | 99% | Tue 30/01/24 | Thu 18/04/24 | 58 days | Thu 18/04/24 | Thu 18/04/24 |  |  | -58 days | 0 days | 58 days | N/A | N/A |  |  | 5.18 | Yes | N/A
4 | 1.5.2.1 |  |  | Functional Test Cases & Scenarios Batch 1 | 100% | Tue 30/01/24 | Thu 08/02/24 | 8 days | NA | NA |  |  | 0 days | 0 days | 8 days | N/A | N/A |  |  | 5.18 | Yes | N/A
5 | 1.5.2.1.1 |  |  | Walkthrough Test Cases & Scenarios Batch 1 with Code Bodies | 100% | Tue 30/01/24 | Tue 30/01/24 | 1 day | NA | NA | 1203SS+60 days | 1218 | 0 days | 0 days | 1 day | Non-SIT LDSO | Non-SIT LDSO, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
5 | 1.5.2.1.2 |  |  | Walkthrough Test Cases & Scenarios Batch 1 with LDSO | 100% | Thu 01/02/24 | Thu 01/02/24 | 1 day | NA | NA | 1217 | 1219 | 0 days | 0 days | 1 day | LDSO, Non-SIT LDSO | LDSO, Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
5 | 1.5.2.1.3 |  |  | Action Feedback on Test Cases & Scenarios Batch 1 | 100% | Fri 02/02/24 | Thu 08/02/24 | 5 days | NA | NA | 1218 | 1228 | 0 days | 0 days | 5 days | Non-SIT LDSO | Non-SIT LDSO, LDSO , Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.2.2 |  |  | Functional Test Cases & Scenarios Batch 2 | 100% | Tue 20/02/24 | Fri 08/03/24 | 14 days | NA | NA |  |  | 0 days | 0 days | 14 days | N/A | N/A |  |  | 5.18 | Yes | N/A
5 | 1.5.2.2.1 |  |  | Walkthrough Test Cases & Scenarios Batch 2 with Code Bodies | 100% | Tue 20/02/24 | Tue 20/02/24 | 1 day | NA | NA | 1203SS+75 days | 1222FS+7 days | 0 days | 0 days | 1 day | Non-SIT LDSO | Non-SIT LDSO, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
5 | 1.5.2.2.2 |  |  | Walkthrough Test Cases & Scenarios Batch 2 with LDSO | 100% | Fri 01/03/24 | Fri 01/03/24 | 1 day | NA | NA | 1221FS+7 days | 1223 | 0 days | 0 days | 1 day | LDSO, Non-SIT LDSO | LDSO, Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
5 | 1.5.2.2.3 |  |  | Action Feedback on Test Cases & Scenarios Batch 2 | 100% | Mon 04/03/24 | Fri 08/03/24 | 5 days | NA | NA | 1222 | 1228 | 0 days | 0 days | 5 days | Non-SIT LDSO | Non-SIT LDSO, LDSO , Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.2.3 |  |  | Functional Test Cases & Scenarios Batch 3 | 99% | Wed 20/03/24 | Fri 05/04/24 | 13 days | NA | NA |  |  | 0 days | 0 days | 13 days | N/A | N/A |  |  | 5.18 | Yes | N/A
5 | 1.5.2.3.1 |  |  | Walkthrough Test Cases & Scenarios Batch 3 with Code Bodies | 100% | Wed 20/03/24 | Wed 20/03/24 | 1 day | NA | NA | 1203SS+96 days | 1226FS+5 days | 0 days | 0 days | 1 day | Non-SIT LDSO | Non-SIT LDSO, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
5 | 1.5.2.3.2 |  |  | Walkthrough Test Cases & Scenarios Batch 3 with LDSO | 100% | Thu 28/03/24 | Thu 28/03/24 | 1 day | NA | NA | 1225FS+5 days | 1227 | 0 days | 0 days | 1 day | LDSO, Non-SIT LDSO | LDSO, Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
5 | 1.5.2.3.3 |  |  | Action Feedback on Test Cases & Scenarios Batch 3 | 100% | Fri 29/03/24 | Fri 05/04/24 | 6 days | NA | NA | 1226 | 1228FS+1 day | 0 days | 0 days | 6 days | Non-SIT LDSO | Non-SIT LDSO, LDSO , Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.2.4 |  |  | Test Cases & Scenarios Batch 1-3 Discussion at QWG | 100% | Tue 09/04/24 | Tue 09/04/24 | 1 day | NA | NA | 1219,1223,1227FS+1 day | 1229 | 0 days | 0 days | 1 day | Non-SIT LDSO, PP | Non-SIT LDSO, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.2.5 |  |  | Action QWG Feedback on Test Cases & Sceanrios Batch 1-3 | 100% | Wed 10/04/24 | Thu 11/04/24 | 2 days | NA | NA | 1228 | 1230FS+5 days | 0 days | 0 days | 2 days | Non-SIT LDSO | Non-SIT LDSO, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.2.6 | TBC | QAG (Non-SIT LDSO) | Approval of Batch 1-3 Test Cases & Scenarios at QAG | 0% | Thu 18/04/24 | Thu 18/04/24 | 0 days | Thu 18/04/24 | Thu 18/04/24 | 1229FS+5 days | 12321277 | 0 days | 0 days | 0 days | Code Bodies | Non-SIT LDSO, Code Bodies | Proposed | New | 5.19 | Yes | Ben Wickins
3 | 1.5.3 |  |  | Test Execution Schedule | 0% | Fri 19/04/24 | Thu 15/08/24 | 84 days | Fri 26/04/24 | Wed 24/07/24 |  |  | -5 days | 15 days | 20 days | N/A | N/A |  |  | 5.18 | Yes | N/A
4 | 1.5.3.1 |  |  | Draft Test Delivery Schedule | 0% | Fri 19/04/24 | Thu 16/05/24 | 20 days | NA | NA | 1230 | 1233 | 0 days | 0 days | -20 days | Non-SIT LDSO | SI Test, PP, Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.3.2 |  |  | Socialise Test Delivery Schedule with Code Bodies & LDSO for Review & Action Feedback | 0% | Fri 17/05/24 | Mon 08/07/24 | 37 days | NA | NA | 1232 | 1234 | 0 days | 0 days | 37 days | Non-SIT LDSO | LDSO, Code Bodies, Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.3.3 |  |  | Agree Test Execution Timetable Format at QWG, Including Anonymisation Requirements | 0% | Tue 09/07/24 | Tue 09/07/24 | 1 day | NA | NA | 1233 | 1235 | 0 days | 0 days | -19 days | Non-SIT LDSO, PP | Non-SIT LDSO, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.3.4 |  |  | Action QWG Feedback | 0% | Wed 10/07/24 | Fri 12/07/24 | 3 days | NA | NA | 1234 | 1236FS+4 days | 0 days | 0 days | 3 days | Non-SIT LDSO, PP | Non-SIT LDSO, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.3.5 | TBC | QAG (Non-SIT LDSO) | Agree Test Execution Timetable Format at QAG, Including Anonymisation Requirements | 0% | Thu 18/07/24 | Thu 18/07/24 | 0 days | Wed 24/07/24 | Wed 24/07/24 | 1235FS+4 days | 1237 | -3 days | -4 days | -1 day | Code Bodies | Non-SIT LDSO, Code Bodies | Proposed | New | 5.18 | Yes | Ben Wickins
4 | 1.5.3.6 | T3-QU-0008 | QAG (Non-SIT LDSO) | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test Execution Schedule Approved | 0% | Thu 15/08/24 | Thu 15/08/24 | 0 days | Fri 26/04/24 | Fri 26/04/24 | 1236 | 1280 | 79 days | 78 days | 0 days | Non-SIT LDSO | Non-SIT LDSO, Code Bodies, PP | Proposed | Date Change | 5.18 | Yes | Ben Wickins
3 | 1.5.4 |  |  | Functional, Non-Functional, Operational & Migration Test Scenarios & Cases | 41% | Fri 22/03/24 | Thu 27/06/24 | 70 days | Fri 22/03/24 | Thu 27/06/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.21 | Yes | N/A
4 | 1.5.4.1 |  |  | Test Scenarios & Cases - Functional - Drafted, Reviewed | 93% | Mon 01/04/24 | Thu 18/04/24 | 14 days | Mon 01/04/24 | Thu 18/04/24 | 1208 | 1240 | 0 days | 0 days | 0 days | Non-SIT LDSO | Non-SIT LDSO, LDSO, Code Bodies |  |  | 5.21 | Yes | Ben Wickins
4 | 1.5.4.2 | TBC | QAG (Non-SIT LDSO) | Test Scenarios & Cases- Functional - Approved at QAG | 0% | Thu 18/04/24 | Thu 18/04/24 | 0 days | Thu 18/04/24 | Thu 18/04/24 | 1239 | 1293 | 0 days | 0 days | 0 days | Non-SIT LDSO | Non-SIT LDSO, LDSO, Code Bodies | Proposed | New | 5.21 | Yes | Ben Wickins
4 | 1.5.4.3 |  |  | Test Scenarios & Cases - Non-Functional - Drafted, Reviewed | 35% | Fri 22/03/24 | Thu 16/05/24 | 40 days | Fri 22/03/24 | Thu 20/06/24 | 1208 | 1242FS+25 days | 0 days | -25 days | -25 days | Non-SIT LDSO | Non-SIT LDSO, LDSO, Code Bodies |  |  | 5.21 | Yes | Ben Wickins
4 | 1.5.4.4 | TBC | QAG (Non-SIT LDSO) | Test Scenarios & Cases - Non-Functional - Approved at QAG | 0% | Thu 20/06/24 | Thu 20/06/24 | 0 days | Thu 20/06/24 | Thu 20/06/24 | 1241FS+25 days | 1293 | 0 days | 0 days | 0 days | Non-SIT LDSO | Non-SIT LDSO, LDSO, Code Bodies | Proposed | New | 5.21 | Yes | Ben Wickins
4 | 1.5.4.5 |  |  | Test Scenarios & Cases - Migration - Drafted, Reviewed | 48% | Fri 22/03/24 | Thu 16/05/24 | 40 days | Fri 22/03/24 | Thu 16/05/24 | 1208 | 1244 | 0 days | 0 days | 0 days | Non-SIT LDSO | Non-SIT LDSO, LDSO, Code Bodies |  |  | 5.21 | Yes | Ben Wickins
4 | 1.5.4.6 | TBC | QAG (Non-SIT LDSO) | Test Scenarios & Cases - Migration - Approved at QAG | 0% | Thu 16/05/24 | Thu 16/05/24 | 0 days | Thu 16/05/24 | Thu 16/05/24 | 1243 | 1293 | 0 days | 0 days | 0 days | Non-SIT LDSO | Non-SIT LDSO, LDSO, Code Bodies | Proposed | New | 5.21 | Yes | Ben Wickins
4 | 1.5.4.7 |  |  | Test Scenarios & Cases - Operational - Drafted, Reviewed | 0% | Mon 03/06/24 | Thu 27/06/24 | 19 days | Mon 03/06/24 | Thu 27/06/24 | 1208FS+51 days | 1246 | 0 days | 0 days | 0 days | Non-SIT LDSO | Non-SIT LDSO, LDSO, Code Bodies |  |  | 5.21 | Yes | Ben Wickins
4 | 1.5.4.8 | TBC | QAG (Non-SIT LDSO) | Test Scenarios & Cases - Operational - Approved at QAG | 0% | Thu 27/06/24 | Thu 27/06/24 | 0 days | Thu 27/06/24 | Thu 27/06/24 | 1245 | 1248 | 0 days | 0 days | 0 days | Non-SIT LDSO | Non-SIT LDSO, LDSO, Code Bodies | Proposed | New | 5.21 | Yes | Ben Wickins
3 | 1.5.5 |  |  | Cross Check Against SIT | 0% | Fri 28/06/24 | Thu 11/07/24 | 10 days | Mon 31/10/22 | Wed 16/11/22 |  |  | 434 days | 431 days | -3 days | N/A | N/A |  |  | 5.18 | Yes | N/A
4 | 1.5.5.1 |  |  | Cross Check Scenarios Against Those Used In Waves | 0% | Fri 28/06/24 | Thu 04/07/24 | 5 days | NA | NA | 1246 | 1249 | 0 days | 0 days | 5 days | Non-SIT LDSO | Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.5.2 |  |  | Updates to Test Deliverables Post SIT Cross Check | 0% | Fri 05/07/24 | Thu 11/07/24 | 5 days | NA | NA | 1248 | 1293 | 0 days | 0 days | 5 days | Non-SIT LDSO | Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
3 | 1.5.6 |  |  | Test Data | 25% | Mon 22/01/24 | Fri 20/12/24 | 240 days | Thu 16/05/24 | Mon 02/09/24 |  |  | -84 days | 79 days | 163 days | N/A | N/A |  |  | 5.18 | Yes | N/A
4 | 1.5.6.1 |  |  | Test Data Plan Drafted & Reviewed | 75% | Mon 22/01/24 | Thu 16/05/24 | 84 days | NA | NA | 1203 | 1252 | 0 days | 0 days | 21 days | Code Bodies | Non-SIT LDSO, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.6.2 | TBC | QAG (Non-SIT LDSO) | Test Data Plan Approved at QAG | 0% | Thu 16/05/24 | Thu 16/05/24 | 0 days | Fri 26/04/24 | Fri 26/04/24 | 1251 | 12541253 | 15 days | 14 days | 0 days | Code Bodies | Non-SIT LDSO, Code Bodies | Proposed | New | 5.19 | Yes | Ben Wickins
4 | 1.5.6.3 |  |  | Develop Test Data Matrices | 0% | Fri 17/05/24 | Thu 30/05/24 | 10 days | NA | NA | 1252 | 1255 | 0 days | 0 days | 10 days | Non-SIT LDSO | Non-SIT LDSO |  |  | 5.22 | Yes | Ben Wickins
4 | 1.5.6.4 |  |  | Test Data Cut | 0% | Fri 17/05/24 | Mon 10/06/24 | 17 days | NA | NA | 1252 | 1255 | 0 days | 0 days | 17 days | PP, Non-SIT LDSO | PP, Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.6.5 | TBC | QAG (Non-SIT LDSO) | Test Data Cut Complete | 0% | Mon 10/06/24 | Mon 10/06/24 | 0 days | Mon 10/06/24 | Mon 10/06/24 | 12541253 | 1256 | 0 days | 0 days | 0 days | PP, Non-SIT LDSO | PP, Non-SIT LDSO | Proposed | New | 5.21 | Yes | Ben Wickins
4 | 1.5.6.6 |  |  | Test Data Reviewed by the Programme | 0% | Tue 11/06/24 | Thu 08/08/24 | 43 days | NA | NA | 1255 | 1257 | 0 days | 0 days | 43 days | Non-SIT LDSO | PP, Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.6.7 |  |  | Test Data Loaded | 0% | Fri 09/08/24 | Mon 02/09/24 | 17 days | NA | NA | 1256 | 1258 | 0 days | 0 days | 17 days | Non-SIT LDSO | PP, Non-SIT LDSO |  |  | 5.21 | Yes | Ben Wickins
4 | 1.5.6.8 | TBC | QAG (Non-SIT LDSO) | Test Data Signed Off | 0% | Mon 02/09/24 | Mon 02/09/24 | 0 days | Mon 02/09/24 | Mon 02/09/24 | 1257 | 1259 | 0 days | 0 days | 0 days | Non-SIT LDSO | PP, Non-SIT LDSO | Proposed | New | 5.21 | Yes | Ben Wickins
4 | 1.5.6.9 |  |  | Test Execution Data Support | 0% | Tue 03/09/24 | Fri 20/12/24 | 79 days | NA | NA | 1258 | 1301 | 0 days | 0 days | 79 days | Non-SIT LDSO | Non-SIT LDSO |  |  | 5.22 | Yes | Ben Wickins
3 | 1.5.7 |  |  | Tooling | 39% | Wed 31/01/24 | Tue 20/08/24 | 145 days | NA | NA |  |  | 0 days | 0 days | 145 days | N/A | N/A |  |  | 5.18 | Yes | N/A
4 | 1.5.7.1 |  |  | Design Approach & Set-Up ADO Tool for Test & Defect Management Tool | 100% | Wed 31/01/24 | Fri 12/04/24 | 53 days | NA | NA | 1203 | 1262 | 0 days | 0 days | 53 days | Non-SIT LDSO | Non-SIT LDSO, SI Test |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.7.2 |  |  | Develop Training Requirements & Materials Inc. Day in the Life | 3% | Mon 15/04/24 | Tue 13/08/24 | 87 days | NA | NA | 1261 | 1263 | 0 days | 0 days | 87 days | Non-SIT LDSO | Non-SIT LDSO, SI Test |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.7.3 |  |  | ADO Launch | 0% | Wed 14/08/24 | Tue 20/08/24 | 5 days | NA | NA | 1262 | 1280 | 0 days | 0 days | 5 days | Non-SIT LDSO | Non-SIT LDSO |  |  | 5.21 | Yes | Ben Wickins
3 | 1.5.8 |  |  | Pre-Integration Testing | 31% | Mon 05/02/24 | Mon 30/09/24 | 171 days | Fri 26/04/24 | Mon 30/09/24 |  |  | -59 days | 0 days | 59 days | N/A | N/A |  |  | 5.18 | Yes | N/A
4 | 1.5.8.1 |  |  | PIT Guidance & Templates & Approach & Plans Developed | 56% | Mon 05/02/24 | Fri 14/06/24 | 95 days | NA | NA | 1203FS+3 days | 1266 | 0 days | 0 days | 95 days | Non-SIT LDSO | Non-SIT LDSO, LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.8.2 | TBC | QAG (Non-SIT LDSO) | PIT Test Plan Deadline for Submission for Non-SIT LDSO​ QT | 0% | Fri 14/06/24 | Fri 14/06/24 | 0 days | Fri 26/04/24 | Fri 26/04/24 | 1265 | 1267 | 36 days | 35 days | 0 days | Non-SIT LDSO | Non-SIT LDSO, LDSO | Proposed | New | 5.18 | Yes | Ben Wickins
4 | 1.5.8.3 |  |  | Develop and agree PIT Test Senarios | 0% | Mon 17/06/24 | Mon 29/07/24 | 31 days | NA | NA | 1266 | 1268 | 0 days | 0 days | 31 days | Non-SIT LDSO | Non-SIT LDSO, Code Bodies, LDSO |  |  | 5.22 | Yes | Ben Wickins
4 | 1.5.8.4 |  |  | PIT Execution | 0% | Tue 30/07/24 | Mon 30/09/24 | 45 days | NA | NA | 1267 | 1269 | 0 days | 0 days | 45 days | Non-SIT LDSO | Non-SIT LDSO, LDSO |  |  | 5.22 | Yes | Ben Wickins
4 | 1.5.8.5 | TBC | QAG (Non-SIT LDSO) | Non-SIT LDSO Participants have submitted PIT Test Completion Report & evidence for QT Entry​ | 0% | Mon 30/09/24 | Mon 30/09/24 | 0 days | Mon 30/09/24 | Mon 30/09/24 | 1268 | 1293 | 0 days | 0 days | 0 days | Non-SIT LDSO | Non-SIT LDSO, LDSO | Proposed | New | 5.18 | Yes | Ben Wickins
3 | 1.5.9 |  |  | Placing Reliance - Code Body & LDSO | 55% | Wed 31/01/24 | Thu 20/06/24 | 102 days | Thu 20/06/24 | Thu 20/06/24 |  |  | -102 days | 0 days | 102 days | N/A | N/A |  |  | 5.18 | Yes | N/A
4 | 1.5.9.1 |  |  | Placing Reliance Submitted & Reviewed | 100% | Wed 31/01/24 | Wed 28/02/24 | 21 days | NA | NA | 1203 | 1272 | 0 days | 0 days | 21 days | LDSO, Non-SIT LDSO | LDSO, Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.9.2 |  |  | Define & Agree QT Testing for Each LDSO | 100% | Thu 29/02/24 | Fri 29/03/24 | 22 days | NA | NA | 1271 | 1273 | 0 days | 0 days | 22 days | Non-SIT LDSO | LDSO, Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.9.3 |  |  | Develop Test Scope & Reliance Submissions | 87% | Mon 01/04/24 | Fri 19/04/24 | 15 days | NA | NA | 1272 | 1274 | 0 days | 0 days | 15 days | Non-SIT LDSO | LDSO, Non-SIT LDSO, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.9.4 |  |  | Review and Consultation | 0% | Mon 22/04/24 | Thu 20/06/24 | 44 days | NA | NA | 1273 | 1275 | 0 days | 0 days | 44 days | Non-SIT LDSO | LDSO, Non-SIT LDSO |  |  | 5.22 | Yes | Ben Wickins
4 | 1.5.9.5 | TBC | QAG (Non-SIT LDSO) | PP Test Scope Approved at QAG | 0% | Thu 20/06/24 | Thu 20/06/24 | 0 days | Thu 20/06/24 | Thu 20/06/24 | 1274 | 1289 | 0 days | 0 days | 0 days | Non-SIT LDSO | LDSO, Non-SIT LDSO | Proposed | New | 5.19 | Yes | Ben Wickins
3 | 1.5.10 |  |  | LDSO Test Reporting | 0% | Fri 19/04/24 | Tue 01/10/24 | 118 days | Fri 26/07/24 | Thu 10/10/24 |  |  | -71 days | -7 days | 64 days | N/A | N/A |  |  | 5.18 | Yes | N/A
4 | 1.5.10.1 |  |  | Interim Test Report & Plan Developed & Reviewed | 0% | Fri 19/04/24 | Fri 26/07/24 | 71 days | NA | NA | 1230 | 1278 | 0 days | 0 days | 71 days | Non-SIT LDSO, LDSO | Non-SIT LDSO, LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.10.2 | TBC | QAG (Non-SIT LDSO) | Test Plan Submission to MHHS Programme For Review | 0% | Fri 26/07/24 | Fri 26/07/24 | 0 days | Fri 26/07/24 | Fri 26/07/24 | 1277 | 1279 | 0 days | 0 days | 0 days | LDSO | Non-SIT LDSO, LDSO | Proposed | New | 5.18 | Yes | Ben Wickins
4 | 1.5.10.3 |  |  | Final Test Report Developed & Submitted | 0% | Mon 29/07/24 | Thu 26/09/24 | 44 days | NA | NA | 1278 | 1280FS+3 days | 0 days | 0 days | 44 days | Non-SIT LDSO | Non-SIT LDSO, LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.10.4 | TBC | QAG (Non-SIT LDSO) | Non-SIT LDSO QT Test Execution Starts | 0% | Tue 01/10/24 | Tue 01/10/24 | 0 days | Thu 10/10/24 | Thu 10/10/24 | 1279FS+3 days,1263,1286,1293,1294,1237 | 1298FS+23 days | -7 days | -7 days | 0 days | Non-SIT LDSO | Non-SIT LDSO, LDSO, Code Bodies | Proposed | New | 5.18 | Yes | Ben Wickins
3 | 1.5.11 |  |  | Test Environment | 0% | Wed 17/04/24 | Thu 19/09/24 | 112 days | Fri 26/04/24 | Fri 24/01/25 |  |  | -7 days | -91 days | -84 days | N/A | N/A |  |  | 5.18 | Yes | N/A
4 | 1.5.11.1 |  |  | Central System (DIP Env & Helix Test Harness) Test Environment DBT | 0% | Wed 17/04/24 | Thu 22/08/24 | 92 days | NA | NA | 471 | 1283FF | 0 days | 0 days | 92 days | LDSO | Non SIT-LDSO, LDSO |  |  | 5.2 | Yes | Ben Wickins
4 | 1.5.11.2 |  |  | Coordinate LDSO Env Preparation | 0% | Fri 12/07/24 | Thu 22/08/24 | 30 days | NA | NA | 1282FF | 1286 | 0 days | 0 days | 30 days | Non-SIT LDSO | Non-SIT LDSO |  |  | 5.22 | Yes | Ben Wickins
4 | 1.5.11.3 |  |  | DIP available for Onboarding | 0% | Thu 01/08/24 | Thu 01/08/24 | 1 day | NA | NA |  | 1285FS+2 days | 0 days | 0 days | 1 day | Test Env | Test Env, Non-SIT LDSO |  |  | 5.22 | Yes | Ben Wickins
4 | 1.5.11.4 | T3-QU-0009 | QAG (Non-SIT LDSO) | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Participants' Environments (TBC) Ready To Start Connectivity Proving (Incl. Certificates & Security Compliance) | 0% | Mon 05/08/24 | Mon 05/08/24 | 0 days | Fri 26/04/24 | Fri 26/04/24 | 1284FS+2 days | 1286FS+33 days | 72 days | 71 days | 0 days | Non-SIT LDSO | Code Bodies, PP, IPA | Proposed | Date Change | 5.18 | Yes | Ben Wickins
4 | 1.5.11.5 | TBC | QAG (Non-SIT LDSO) | LDSO Test Environments Connection Confirmed to UIT Environment | 0% | Thu 19/09/24 | Thu 19/09/24 | 0 days | Thu 19/09/24 | Thu 19/09/24 | 1285FS+33 days,1283 | 1280 | 0 days | 0 days | 0 days | Non-SIT LDSO | Code Bodies, PP, IPA | Proposed | New | 5.18 | Yes | Ben Wickins
3 | 1.5.12 |  |  | Test Readiness | 0% | Fri 17/05/24 | Mon 30/09/24 | 97 days | Wed 12/06/24 | Thu 10/10/24 |  |  | -19 days | -8 days | 11 days | N/A | N/A |  |  | 5.18 | Yes | N/A
4 | 1.5.12.1 |  |  | Preparation for Interim Test Readiness Report | 0% | Fri 17/05/24 | Fri 26/07/24 | 51 days | NA | NA | 1214 | 1289 | 0 days | 0 days | 51 days | LDSO | LDSO, Non-SIT LDSO |  |  | 5.22 | Yes | Ben Wickins
4 | 1.5.12.2 | TBC | QAG (Non-SIT LDSO) | Interim Test Readiness Report Submission to MHHS Programme for Review | 0% | Fri 26/07/24 | Fri 26/07/24 | 0 days | Wed 12/06/24 | Wed 12/06/24 | 12881275 | 1290 | 32 days | 32 days | 0 days | LDSO | Non-SIT LDSO, LDSO | Proposed | New | 5.18 | Yes | Ben Wickins
4 | 1.5.12.3 |  |  | LDSO Update Readiness Report & Final Assurance by Programme | 0% | Mon 29/07/24 | Fri 30/08/24 | 25 days | NA | NA | 1289 | 129112941292 | 0 days | 0 days | 25 days | Non-SIT LDSO, LDSO | Non-SIT LDSO, LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.12.4 |  |  | Final Test Readiness Report Submitted to MHHS Programme | 0% | Mon 02/09/24 | Mon 02/09/24 | 1 day | NA | NA | 1290 | 1293FS+13 days | 0 days | 0 days | 1 day | LDSO | Non-SIT LDSO, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.12.5 |  |  | Final Programme Assurance of LDSO Test Readiness | 0% | Mon 02/09/24 | Mon 30/09/24 | 21 days | NA | NA | 1290 | 1294 | 0 days | 0 days | 21 days | Non-SIT LDSO | Non-SIT LDSO, LDSO |  |  | 5.22 | Yes | Ben Wickins
4 | 1.5.12.6 | T3-QU-0007 | QAG (Non-SIT LDSO) | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test Readiness Confirmed From The Programme | 0% | Mon 30/09/24 | Mon 30/09/24 | 0 days | Fri 05/07/24 | Fri 05/07/24 | 1291FS+13 days,1269,1240,1242,1244,1249 | 1280 | 62 days | 61 days | 0 days | Non-SIT LDSO | SI Test, PP, Non-SIT LDSO | Proposed | Date Change | 5.18 | Yes | Ben Wickins
4 | 1.5.12.7 | TBC | QAG (Non-SIT LDSO) | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Test Readiness Confirmed (Final Test Readiness Review for LDSO) | 0% | Mon 30/09/24 | Mon 30/09/24 | 0 days | Thu 10/10/24 | Thu 10/10/24 | 12901292 | 12801296 | -8 days | -8 days | 0 days | LDSO | SI Test, PP, LDSO | Proposed | New | 5.18 | Yes | Ben Wickins
3 | 1.5.13 |  |  | Test Window | 0% | Tue 01/10/24 | Fri 20/12/24 | 59 days | NA | NA |  |  | 0 days | 0 days | 59 days | N/A | N/A |  |  |  | Yes | N/A
4 | 1.5.13.1 |  |  | All Cohorts Qualification Testing | 0% | Tue 01/10/24 | Fri 20/12/24 | 59 days | NA | NA | 1294 | 1300 | 0 days | 0 days | 59 days | LDSO | Non-SIT LDSO,Code Bodies,LDSO |  |  |  | Yes | Ben Wickins
3 | 1.5.14 |  |  | Test Result Assurance | 0% | Mon 04/11/24 | Fri 24/01/25 | 60 days | Tue 31/12/24 | Fri 24/01/25 |  |  | -42 days | 0 days | 42 days | N/A | N/A |  |  | 5.18 | Yes | N/A
4 | 1.5.14.1 |  |  | LDSOs Develop & Submit Test Report (QT Test Completion Report) | 0% | Mon 04/11/24 | Thu 28/11/24 | 19 days | NA | NA | 1280FS+23 days | 1299 | 0 days | 0 days | 19 days | LDSO | Non-SIT LDSO, LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.14.2 |  |  | Test Reports Reviewed By MHHS & Code Bodies & Finalised | 0% | Fri 29/11/24 | Fri 20/12/24 | 16 days | NA | NA | 1298 | 1300 | 0 days | 0 days | 16 days | Non-SIT LDSO | Non-SIT LDSO, Code Bodies |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.14.3 | TBC | QAG (Non-SIT LDSO) | Non-SIT LDSOs submission deadline for their QT Test Completion Report to MHHS Programme | 0% | Fri 20/12/24 | Fri 20/12/24 | 0 days | Tue 31/12/24 | Tue 31/12/24 | 12991296 | 1301FS+25 days,1303 | -7 days | -7 days | 0 days | Non-SIT LDSO | Non-SIT LDSO | Proposed | New | 5.18 | Yes | Ben Wickins
4 | 1.5.14.4 | T3-QU-0010 | QAG (Non-SIT LDSO) | Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) 1 End | 0% | Fri 24/01/25 | Fri 24/01/25 | 0 days | Fri 24/01/25 | Fri 24/01/25 | 1300FS+25 days,1259 | 1305 | 1 day | 0 days | 0 days | Non-SIT LDSO | Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
3 | 1.5.15 |  |  | Non-SIT LDSO Qualification Closure | 0% | Mon 23/12/24 | Fri 28/02/25 | 50 days | NA | NA |  |  | 0 days | 0 days | 50 days | N/A | N/A |  |  | 5.18 | Yes | N/A
4 | 1.5.15.1 |  |  | Non-SIT LDSO Qualification Learned Captured | 0% | Mon 23/12/24 | Fri 10/01/25 | 15 days | NA | NA | 1300 | 1304 | 0 days | 0 days | 15 days | Non-SIT LDSO | Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.15.2 |  |  | Non-SIT LDSO Qualification Closure Down | 0% | Mon 13/01/25 | Fri 17/01/25 | 5 days | NA | NA | 1303 | 1305FS+30 days | 0 days | 0 days | 5 days | Non-SIT LDSO | Non-SIT LDSO |  |  | 5.18 | Yes | Ben Wickins
4 | 1.5.15.3 | T2-QU-500 | QAG (Non-SIT LDSO) | BSC PAB & REC Manager approval of Qualification Testing for Non-SIT LDSOs (Functional, Migration, NFT, Operational) Completion (Start of Migration for Qualification Participants) | 0% | Fri 28/02/25 | Fri 28/02/25 | 0 days | Fri 21/02/25 | Fri 21/02/25 | 1304FS+30 days,1301 |  | 6 days | 5 days | 0 days | Non-SIT LDSO | Non-SIT LDSO | Proposed | Date Change | 5.18 | Yes | Ben Wickins
2 | 1.6 |  |  | QUALIFICATION | 1% | Mon 27/02/23 | Thu 31/12/26 | 1004 days | Mon 27/02/23 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
3 | 1.6.1 | TBC | QAG | Pre-Qualification Submission and PIT Test Plan Deadline for Submission | 0% | Fri 26/04/24 | Fri 26/04/24 | 0 days | Fri 26/04/24 | Fri 26/04/24 |  |  | 0 days | -1 day | 0 days | PP | PP, Code Bodies |  |  | 5.18 | Yes | Nicola Farley
3 | 1.6.2 |  |  | Qualification Preparation | 1% | Mon 27/02/23 | Mon 30/06/25 | 611 days | Mon 27/02/23 | Mon 30/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.6.2.1 |  |  | Artefact Development | 27% | Mon 27/02/23 | Wed 14/08/24 | 383 days | Mon 27/02/23 | Wed 14/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.6.2.1.1 |  |  | Collaborative ways of working | 100% | Mon 27/02/23 | Fri 09/06/23 | 75 days | Mon 27/02/23 | Fri 09/06/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.6.2.1.1.1 |  |  | Develop collaboration ways of working with Code Bodies | 100% | Mon 27/02/23 | Fri 26/05/23 | 65 days | Mon 27/02/23 | Fri 26/05/23 |  | 1312 | 0 days | 0 days | 0 days | SI Test | Code Bodies |  |  | 5 | Yes | Lee Cox
6 | 1.6.2.1.1.2 |  |  | Internal review and updates | 100% | Mon 29/05/23 | Fri 09/06/23 | 10 days | Mon 29/05/23 | Fri 09/06/23 | 1311 | 1313 | 0 days | 0 days | 0 days | SI Test | Code Bodies |  |  | 5 | Yes | Lee Cox
6 | 1.6.2.1.1.3 |  |  | Collaborative ways of working agreed | 100% | Fri 09/06/23 | Fri 09/06/23 | 0 days | Fri 09/06/23 | Fri 09/06/23 | 1312 |  | 0 days | 0 days | 0 days | SI Test | Code Bodies |  |  | 5 | Yes | Lee Cox
5 | 1.6.2.1.2 |  |  | Qualification Approach & Plan (iterative development) | 0% | Wed 16/08/23 | Wed 14/08/24 | 261 days | Wed 16/08/23 | Wed 14/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.6.2.1.2.1 |  |  | Qualification Functional Testing | 0% | Wed 16/08/23 | Tue 31/10/23 | 55 days | Wed 16/08/23 | Tue 31/10/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.1.2.1.1 |  |  | Develop Functional Testing elements (incl. Test Data and Schedule for Test Scenario & Script development) of Qualification Approach & Plan with QWG | 0% | Wed 16/08/23 | Tue 12/09/23 | 20 days | Wed 16/08/23 | Tue 12/09/23 | 797FS-1 day | 1317 | 0 days | 0 days | 0 days | Code Bodies | SI Test,PP |  |  | 5 | Yes | Nicola Farley
7 | 1.6.2.1.2.1.2 |  |  | Review draft artefact with Programme to ensure alignment with SIT | 0% | Wed 13/09/23 | Tue 26/09/23 | 10 days | Wed 13/09/23 | Tue 26/09/23 | 1316 | 1318 | 0 days | 0 days | 0 days | Code Bodies | SI Test |  |  | 5 | Yes | Nicola Farley
7 | 1.6.2.1.2.1.3 |  |  | Artefact review (via QWG) and updates | 0% | Wed 27/09/23 | Tue 24/10/23 | 20 days | Wed 27/09/23 | Tue 24/10/23 | 1317 | 1319FS+5 days | 0 days | 0 days | 0 days | Code Bodies | SI Test,PP,IPA |  |  | 5 | Yes | Nicola Farley
7 | 1.6.2.1.2.1.4 | T3-QU-0063 | QAG | Functional Testing elements of Qualification Approach & Plan approved by REC Manager & BSC PAB | 100% | Tue 31/10/23 | Tue 31/10/23 | 0 days | Tue 31/10/23 | Tue 31/10/23 | 1318FS+5 days | 1335 | 0 days | 0 days | 0 days | Code Bodies |  |  |  | 5 | Yes | Nicola Farley
6 | 1.6.2.1.2.2 |  |  | Qualification Migration Testing | 0% | Thu 21/12/23 | Wed 06/03/24 | 55 days | Thu 21/12/23 | Wed 06/03/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.1.2.2.1 |  |  | Develop Migration Testing elements (incl. Test Data and Schedule for Test Scenario & Script development) of Qualification Approach & Plan with QWG | 0% | Thu 21/12/23 | Wed 31/01/24 | 30 days | Thu 21/12/23 | Wed 31/01/24 | 869 | 1322 | 0 days | 0 days | 0 days | Code Bodies | SI Test,PP |  |  | 5 | Yes | Nicola Farley
7 | 1.6.2.1.2.2.2 |  |  | Review draft artefact with Programme to ensure alignment with SIT | 0% | Thu 01/02/24 | Wed 14/02/24 | 10 days | Thu 01/02/24 | Wed 14/02/24 | 1321 | 1323 | 0 days | 0 days | 0 days | Code Bodies | SI Test |  |  | 5 | Yes | Nicola Farley
7 | 1.6.2.1.2.2.3 |  |  | Artefact review (via QWG) and updates | 0% | Thu 15/02/24 | Wed 28/02/24 | 10 days | Thu 15/02/24 | Wed 28/02/24 | 1322 | 1324FS+5 days | 0 days | 0 days | 0 days | Code Bodies | SI Test,PP,IPA |  |  | 5 | Yes | Nicola Farley
7 | 1.6.2.1.2.2.4 | T3-QU-0064 | QAG | Migration Testing elements of Qualification Approach & Plan approved by REC Manager & BSC PAB | 100% | Wed 06/03/24 | Wed 06/03/24 | 0 days | Wed 06/03/24 | Wed 06/03/24 | 1323FS+5 days | 1335 | 0 days | 0 days | 0 days | Code Bodies |  |  |  | 5 | Yes | Nicola Farley
6 | 1.6.2.1.2.3 |  |  | Qualification Non-Functional Testing | 0% | Thu 16/05/24 | Thu 25/07/24 | 51 days | Thu 21/03/24 | Thu 30/05/24 |  |  | 40 days | 40 days | 0 days | N/A | N/A |  |  | 5.2 | Yes | N/A
7 | 1.6.2.1.2.3.1 |  |  | Develop Non-Functional Testing elements (incl. Test Data and Schedule for Test Scenario & Script development) of Qualification Approach & Plan with QWG | 0% | Thu 16/05/24 | Wed 26/06/24 | 30 days | Thu 21/03/24 | Wed 01/05/24 | 921 | 1327 | 40 days | 40 days | 0 days | Code Bodies | SI Test,PP |  |  | 5.2 | Yes | Nicola Farley
7 | 1.6.2.1.2.3.2 |  |  | Review draft artefact with Programme to ensure alignment with SIT | 0% | Thu 27/06/24 | Wed 10/07/24 | 10 days | Thu 02/05/24 | Wed 15/05/24 | 1326 | 1328 | 40 days | 40 days | 0 days | Code Bodies | SI Test |  |  | 5.2 | Yes | Nicola Farley
7 | 1.6.2.1.2.3.3 |  |  | Artefact review (via QWG) and updates | 0% | Thu 11/07/24 | Thu 18/07/24 | 6 days | Thu 16/05/24 | Thu 23/05/24 | 1327 | 1329FS+5 days | 40 days | 40 days | 0 days | Code Bodies | SI Test,PP,IPA |  |  | 5.2 | Yes | Nicola Farley
7 | 1.6.2.1.2.3.4 | T3-QU-0065 | QAG | Non-Functional Testing elements of Qualification Approach & Plan approved by REC Manager & BSC PAB | 0% | Thu 25/07/24 | Thu 25/07/24 | 0 days | Thu 30/05/24 | Thu 30/05/24 | 1328FS+5 days | 1335 | 40 days | 40 days | 0 days | Code Bodies |  |  |  | 5.2 | Yes | Nicola Farley
6 | 1.6.2.1.2.4 |  |  | Qualification Operational Testing | 0% | Thu 16/05/24 | Wed 14/08/24 | 65 days | Thu 16/05/24 | Wed 14/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.1.2.4.1 |  |  | Develop Operational Testing elements (incl. Test Data and Schedule for Test Scenario & Script development) of Qualification Approach & Plan with QWG | 0% | Thu 16/05/24 | Wed 26/06/24 | 30 days | Thu 16/05/24 | Wed 26/06/24 | 966 | 1332 | 0 days | 0 days | 0 days | Code Bodies | SI Test,PP |  |  | 5 | Yes | Nicola Farley
7 | 1.6.2.1.2.4.2 |  |  | Review draft artefact with Programme to ensure alignment with SIT | 0% | Thu 27/06/24 | Wed 10/07/24 | 10 days | Thu 27/06/24 | Wed 10/07/24 | 1331 | 1333 | 0 days | 0 days | 0 days | Code Bodies | SI Test |  |  | 5 | Yes | Nicola Farley
7 | 1.6.2.1.2.4.3 |  |  | Artefact review (via QWG) and updates | 0% | Thu 11/07/24 | Wed 07/08/24 | 20 days | Thu 11/07/24 | Wed 07/08/24 | 1332 | 1334FS+5 days | 0 days | 0 days | 0 days | Code Bodies | SI Test,PP,IPA |  |  | 5 | Yes | Nicola Farley
7 | 1.6.2.1.2.4.4 | T3-QU-0068 | QAG | Operational Testing elements of Qualification Approach & Plan approved by REC Manager & BSC PAB | 0% | Wed 14/08/24 | Wed 14/08/24 | 0 days | Wed 14/08/24 | Wed 14/08/24 | 1333FS+5 days | 1335 | 0 days | 0 days | 0 days |  |  |  |  | 5 | Yes | Nicola Farley
7 | 1.6.2.1.2.4.5 | T3-QU-0062 | QAG | Final Qualification Approach & Plan approved by REC Manager & BSC PAB | 0% | Wed 14/08/24 | Wed 14/08/24 | 0 days | Wed 14/08/24 | Wed 14/08/24 | 1334132913241310 | 1559 | 0 days | 0 days | 0 days | Code Bodies |  |  |  | 5 | Yes | Nicola Farley
4 | 1.6.2.2 |  |  | Qualification Test Tranche-Specific Preparation | 0% | Tue 06/08/24 | Mon 30/06/25 | 235 days | Tue 06/08/24 | Mon 30/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.6.2.2.1 |  |  | Tranche 1 Preparation | 0% | Tue 06/08/24 | Mon 13/01/25 | 115 days | Tue 06/08/24 | Mon 13/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.6.2.2.1.1 |  |  | SI Tranche 1 Preparation | 0% | Tue 06/08/24 | Mon 13/01/25 | 115 days | Tue 06/08/24 | Mon 13/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.2.1.1.1 | T3-QU-0012 | QAG | Confirm Qualification Testing Tranche 1 Participants | 0% | Tue 06/08/24 | Tue 06/08/24 | 0 days | Tue 06/08/24 | Tue 06/08/24 | 1569FS-6 mons | 1.3531e+23 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP, IPA |  |  | 5 | Yes | Nicola Farley
7 | 1.6.2.2.1.1.2 |  |  | Test execution schedule | 0% | Tue 06/08/24 | Mon 04/11/24 | 65 days | Tue 06/08/24 | Mon 04/11/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.1.1.2.1 |  |  | Develop document | 0% | Tue 06/08/24 | Mon 30/09/24 | 40 days | Tue 06/08/24 | Mon 30/09/24 | 1339 | 1342 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes | Nicola Farley
8 | 1.6.2.2.1.1.2.2 |  |  | Review & agree document | 0% | Tue 01/10/24 | Mon 28/10/24 | 20 days | Tue 01/10/24 | Mon 28/10/24 | 1341 | 1343FS+5 days | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes | Nicola Farley
8 | 1.6.2.2.1.1.2.3 | T3-QU-0016 | QAG | Qualification Testing Tranche 1 Test execution schedule approved | 0% | Mon 04/11/24 | Mon 04/11/24 | 0 days | Mon 04/11/24 | Mon 04/11/24 | 1342FS+5 days | 1355 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes | Nicola Farley
7 | 1.6.2.2.1.1.3 |  |  | Environments | 0% | Tue 06/08/24 | Mon 13/01/25 | 115 days | Tue 06/08/24 | Mon 13/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.1.1.3.1 |  |  | Coordinate Qualification Participants' environment preparation | 0% | Tue 06/08/24 | Mon 28/10/24 | 60 days | Tue 06/08/24 | Mon 28/10/24 | 1339 | 1346FF | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes | Simon Berry
8 | 1.6.2.2.1.1.3.2 |  |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 0% | Tue 15/10/24 | Mon 28/10/24 | 10 days | Tue 15/10/24 | Mon 28/10/24 | 1345FF | 1347FS+5 days | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes | Simon Berry
8 | 1.6.2.2.1.1.3.3 | T3-QU-0017 | QAG | Qualification Testing Tranche 1 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Mon 04/11/24 | Mon 04/11/24 | 0 days | Mon 04/11/24 | Mon 04/11/24 | 1346FS+5 days | 135113551349 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP, IPA |  |  | 5 | Yes | Simon Berry
8 | 1.6.2.2.1.1.3.4 |  |  | Coordinate Qualification Participants' connectivity proving | 0% | Tue 05/11/24 | Mon 13/01/25 | 50 days | Tue 05/11/24 | Mon 13/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
9 | 1.6.2.2.1.1.3.4.1 |  |  | Assurance of Qualification Participants' connectivity proving | 0% | Tue 05/11/24 | Mon 13/01/25 | 50 days | Tue 05/11/24 | Mon 13/01/25 | 1347 | 1355 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
7 | 1.6.2.2.1.1.4 |  |  | Test Data | 0% | Mon 04/11/24 | Mon 04/11/24 | 0 days | Mon 04/11/24 | Mon 04/11/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.1.1.4.1 | T3-QU-0018 | QAG | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 1 Participants) | 0% | Mon 04/11/24 | Mon 04/11/24 | 0 days | Mon 04/11/24 | Mon 04/11/24 | 1347 | 1355 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes | Richard Puddephatt
7 | 1.6.2.2.1.1.5 |  |  | Other Preparation | 0% | Tue 06/08/24 | Mon 13/01/25 | 115 days | Tue 06/08/24 | Mon 13/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.1.1.5.1 |  |  | Onboarding of Test Participants to Test Management Tool | 0% | Tue 06/08/24 | Mon 13/01/25 | 115 days | Tue 06/08/24 | Mon 13/01/25 | 1339 | 1355 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.1.1.5.2 |  |  | Other Preparation (activities TBC) | 0% | Tue 06/08/24 | Mon 13/01/25 | 115 days | Tue 06/08/24 | Mon 13/01/25 | 1339 | 1355 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes | Nicola Farley
7 | 1.6.2.2.1.1.6 | T3-QU-0027 | QAG | Qualification Testing Tranche 1 Test Readiness confirmed | 0% | Mon 13/01/25 | Mon 13/01/25 | 0 days | Mon 13/01/25 | Mon 13/01/25 | 1.3531e+27 |  | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes | Nicola Farley
6 | 1.6.2.2.1.2 |  |  | PP Tranche 1 Preparation | 0% | Tue 06/08/24 | Mon 13/01/25 | 115 days | Tue 06/08/24 | Mon 13/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.2.1.2.1 | T3-QU-0012 | QAG | Confirm Qualification Testing Tranche 1 Participants | 0% | Tue 06/08/24 | Tue 06/08/24 | 0 days | Tue 06/08/24 | Tue 06/08/24 | 1569FS-6 mons | 13591365 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP, IPA |  |  | 5 | Yes
7 | 1.6.2.2.1.2.2 |  |  | Environments | 0% | Tue 06/08/24 | Mon 13/01/25 | 115 days | Tue 06/08/24 | Mon 13/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.1.2.2.1 |  |  | UIT environment preparation | 0% | Tue 06/08/24 | Mon 28/10/24 | 60 days | Tue 06/08/24 | Mon 28/10/24 | 1357 | 1360FF | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.1.2.2.2 |  |  | Deployment of MHHS solution code to UIT environments | 0% | Tue 15/10/24 | Mon 28/10/24 | 10 days | Tue 15/10/24 | Mon 28/10/24 | 1359FF | 1361FS+5 days | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.1.2.2.3 | T3-QU-0017 | QAG | Qualification Testing Tranche 1 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Mon 04/11/24 | Mon 04/11/24 | 0 days | Mon 04/11/24 | Mon 04/11/24 | 1360FS+5 days | 1362 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP, IPA |  |  | 5 | Yes
8 | 1.6.2.2.1.2.2.4 |  |  | UIT environment connectivity proving | 0% | Tue 05/11/24 | Mon 13/01/25 | 50 days | Tue 05/11/24 | Mon 13/01/25 | 1361 | 1363SS,1367FF | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.1.2.2.5 |  |  | Submit evidence of UIT environment connectivity proving to Programme for assurance | 0% | Tue 05/11/24 | Mon 13/01/25 | 50 days | Tue 05/11/24 | Mon 13/01/25 | 1362SS |  | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
7 | 1.6.2.2.1.2.3 |  |  | Other Preparation | 0% | Tue 06/08/24 | Mon 13/01/25 | 115 days | Tue 06/08/24 | Mon 13/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.1.2.3.1 |  |  | Other Preparation (incl. test execution planning) | 0% | Tue 06/08/24 | Mon 13/01/25 | 115 days | Tue 06/08/24 | Mon 13/01/25 | 1357 |  | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
7 | 1.6.2.2.1.2.4 |  |  | Monitoring of provisional Qualification Testing Tranche 1 Participants' PIT progress and test readiness | 0% | Tue 06/08/24 | Mon 13/01/25 | 115 days | Tue 06/08/24 | Mon 13/01/25 | 1339 |  | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
7 | 1.6.2.2.1.2.5 | T3-QU-0027 | QAG | Qualification Testing Tranche 1 Test Readiness confirmed | 0% | Mon 13/01/25 | Mon 13/01/25 | 0 days | Mon 13/01/25 | Mon 13/01/25 | 1362FF |  | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
5 | 1.6.2.2.2 |  |  | Tranche 2 Preparation | 0% | Tue 03/09/24 | Mon 10/02/25 | 115 days | Tue 03/09/24 | Mon 10/02/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.6.2.2.2.1 |  |  | SI Tranche 2 Preparation | 0% | Tue 03/09/24 | Mon 10/02/25 | 115 days | Tue 03/09/24 | Mon 10/02/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.2.2.1.1 | T3-QU-0013 | QAG | Confirm Qualification Testing Tranche 2 Participants | 0% | Tue 03/09/24 | Tue 03/09/24 | 0 days | Tue 03/09/24 | Tue 03/09/24 | 1574FS-6 mons | 1.3841e+23 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP, IPA |  |  | 5 | Yes
7 | 1.6.2.2.2.1.2 |  |  | Test execution schedule | 0% | Tue 03/09/24 | Mon 02/12/24 | 65 days | Tue 03/09/24 | Mon 02/12/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.2.1.2.1 |  |  | Develop document | 0% | Tue 03/09/24 | Mon 28/10/24 | 40 days | Tue 03/09/24 | Mon 28/10/24 | 1370 | 1373 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
8 | 1.6.2.2.2.1.2.2 |  |  | Review & agree document | 0% | Tue 29/10/24 | Mon 25/11/24 | 20 days | Tue 29/10/24 | Mon 25/11/24 | 1372 | 1374FS+5 days | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
8 | 1.6.2.2.2.1.2.3 | T3-QU-0020 | QAG | Qualification Testing Tranche 2 Test execution schedule approved | 0% | Mon 02/12/24 | Mon 02/12/24 | 0 days | Mon 02/12/24 | Mon 02/12/24 | 1373FS+5 days | 1387 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
7 | 1.6.2.2.2.1.3 |  |  | Environments | 0% | Tue 03/09/24 | Mon 10/02/25 | 115 days | Tue 03/09/24 | Mon 10/02/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.2.1.3.1 |  |  | Coordinate Qualification Participants' environment preparation | 0% | Tue 03/09/24 | Mon 25/11/24 | 60 days | Tue 03/09/24 | Mon 25/11/24 | 1370 | 1377FF | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.2.1.3.2 |  |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 0% | Tue 12/11/24 | Mon 25/11/24 | 10 days | Tue 12/11/24 | Mon 25/11/24 | 1376FF | 1378FS+5 days | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.2.1.3.3 | T3-QU-0021 | QAG | Qualification Testing Tranche 2 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Mon 02/12/24 | Mon 02/12/24 | 0 days | Mon 02/12/24 | Mon 02/12/24 | 1377FS+5 days | 137913821387 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP, IPA |  |  | 5 | Yes
8 | 1.6.2.2.2.1.3.4 |  |  | Coordinate Qualification Participants' connectivity proving | 0% | Tue 03/12/24 | Mon 10/02/25 | 50 days | Tue 03/12/24 | Mon 10/02/25 | 1378 | 1380SS,1387 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.2.1.3.5 |  |  | Assurance of Qualification Participants' connectivity proving | 0% | Tue 03/12/24 | Mon 10/02/25 | 50 days | Tue 03/12/24 | Mon 10/02/25 | 1379SS |  | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
7 | 1.6.2.2.2.1.4 |  |  | Test Data | 0% | Mon 02/12/24 | Mon 02/12/24 | 0 days | Mon 02/12/24 | Mon 02/12/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.2.1.4.1 | T3-QU-0022 | QAG | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 2 Participants) | 0% | Mon 02/12/24 | Mon 02/12/24 | 0 days | Mon 02/12/24 | Mon 02/12/24 | 1378 | 1387 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes | Richard Puddephatt
7 | 1.6.2.2.2.1.5 |  |  | Other Preparation | 0% | Tue 03/09/24 | Mon 10/02/25 | 115 days | Tue 03/09/24 | Mon 10/02/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.2.1.5.1 |  |  | Onboarding of Test Participants to Test Management Tool | 0% | Tue 03/09/24 | Mon 10/02/25 | 115 days | Tue 03/09/24 | Mon 10/02/25 | 1370 | 1387 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.2.1.5.2 |  |  | Other Preparation (activities TBC) | 0% | Tue 03/09/24 | Mon 10/02/25 | 115 days | Tue 03/09/24 | Mon 10/02/25 | 1370 | 1387 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
7 | 1.6.2.2.2.1.6 |  |  | Monitoring of provisional Qualification Testing Tranche 2 Participants' PIT progress and test readiness | 0% | Tue 03/09/24 | Mon 10/02/25 | 115 days | Tue 03/09/24 | Mon 10/02/25 | 1370 |  | 0 days | 0 days | 0 days |  |  |  |  | 5 | Yes
7 | 1.6.2.2.2.1.7 | T3-QU-0033 | QAG | Qualification Testing Tranche 2 Test Readiness confirmed | 0% | Mon 10/02/25 | Mon 10/02/25 | 0 days | Mon 10/02/25 | Mon 10/02/25 | 1.3791e+27 |  | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
6 | 1.6.2.2.2.2 |  |  | PP Tranche 2 Preparation | 0% | Tue 03/09/24 | Mon 10/02/25 | 115 days | Tue 03/09/24 | Mon 10/02/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.2.2.2.1 | T3-QU-0013 | QAG | Confirm Qualification Testing Tranche 2 Participants | 0% | Tue 03/09/24 | Tue 03/09/24 | 0 days | Tue 03/09/24 | Tue 03/09/24 | 1574FS-6 mons | 139113971417 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP, IPA |  |  | 5 | Yes
7 | 1.6.2.2.2.2.2 |  |  | Environments | 0% | Tue 03/09/24 | Mon 10/02/25 | 115 days | Tue 03/09/24 | Mon 10/02/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.2.2.2.1 |  |  | UIT environment preparation | 0% | Tue 03/09/24 | Mon 25/11/24 | 60 days | Tue 03/09/24 | Mon 25/11/24 | 1389 | 1392FF | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.2.2.2.2 |  |  | Deployment of MHHS solution code to UIT environments | 0% | Tue 12/11/24 | Mon 25/11/24 | 10 days | Tue 12/11/24 | Mon 25/11/24 | 1391FF | 1393FS+5 days | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.2.2.2.3 | T3-QU-0021 | QAG | Qualification Testing Tranche 2 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Mon 02/12/24 | Mon 02/12/24 | 0 days | Mon 02/12/24 | Mon 02/12/24 | 1392FS+5 days | 1394 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP, IPA |  |  | 5 | Yes
8 | 1.6.2.2.2.2.2.4 |  |  | UIT environment connectivity proving | 0% | Tue 03/12/24 | Mon 10/02/25 | 50 days | Tue 03/12/24 | Mon 10/02/25 | 1393 | 1395SS,1398FF | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.2.2.2.5 |  |  | Submit evidence of UIT environment connectivity proving to Programme for assurance | 0% | Tue 03/12/24 | Mon 10/02/25 | 50 days | Tue 03/12/24 | Mon 10/02/25 | 1394SS |  | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
7 | 1.6.2.2.2.2.3 |  |  | Other Preparation | 0% | Tue 03/09/24 | Mon 10/02/25 | 115 days | Tue 03/09/24 | Mon 10/02/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.2.2.3.1 |  |  | Other Preparation (incl. test execution planning) | 0% | Tue 03/09/24 | Mon 10/02/25 | 115 days | Tue 03/09/24 | Mon 10/02/25 | 1389 |  | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
7 | 1.6.2.2.2.2.4 | T3-QU-0033 | QAG | Qualification Testing Tranche 2 Test Readiness confirmed | 0% | Mon 10/02/25 | Mon 10/02/25 | 0 days | Mon 10/02/25 | Mon 10/02/25 | 1394FF |  | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
5 | 1.6.2.2.3 |  |  | Tranche 3 Preparation | 0% | Tue 03/09/24 | Mon 10/03/25 | 135 days | Tue 03/09/24 | Mon 10/03/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.6.2.2.3.1 |  |  | SI Tranche 3 Preparation | 0% | Tue 03/09/24 | Mon 10/03/25 | 135 days | Tue 03/09/24 | Mon 10/03/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.2.3.1.1 | T3-QU-0014 | QAG | Confirm Qualification Testing Tranche 3 Participants | 0% | Tue 01/10/24 | Tue 01/10/24 | 0 days | Tue 01/10/24 | Tue 01/10/24 | 1579FS-6 mons | 1415140314071410 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP, IPA |  |  | 5 | Yes
7 | 1.6.2.2.3.1.2 |  |  | Test execution schedule | 0% | Tue 01/10/24 | Mon 30/12/24 | 65 days | Tue 01/10/24 | Mon 30/12/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.3.1.2.1 |  |  | Develop document | 0% | Tue 01/10/24 | Mon 25/11/24 | 40 days | Tue 01/10/24 | Mon 25/11/24 | 1401 | 1404 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
8 | 1.6.2.2.3.1.2.2 |  |  | Review & agree document | 0% | Tue 26/11/24 | Mon 23/12/24 | 20 days | Tue 26/11/24 | Mon 23/12/24 | 1403 | 1405FS+5 days | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
8 | 1.6.2.2.3.1.2.3 | T3-QU-0024 | QAG | Qualification Testing Tranche 3 Test execution schedule approved | 0% | Mon 30/12/24 | Mon 30/12/24 | 0 days | Mon 30/12/24 | Mon 30/12/24 | 1404FS+5 days |  | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
7 | 1.6.2.2.3.1.3 |  |  | Environments | 0% | Tue 01/10/24 | Mon 10/03/25 | 115 days | Tue 01/10/24 | Mon 10/03/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.3.1.3.1 |  |  | Coordinate Qualification Participants' environment preparation | 0% | Tue 01/10/24 | Mon 23/12/24 | 60 days | Tue 01/10/24 | Mon 23/12/24 | 1401 | 1408FF | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.3.1.3.2 |  |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 0% | Tue 10/12/24 | Mon 23/12/24 | 10 days | Tue 10/12/24 | Mon 23/12/24 | 1407FF | 1409FS+5 days | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.3.1.3.3 | T3-QU-0025 | QAG | Qualification Testing Tranche 3 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Mon 30/12/24 | Mon 30/12/24 | 0 days | Mon 30/12/24 | Mon 30/12/24 | 1408FS+5 days | 14101413 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP, IPA |  |  | 5 | Yes
8 | 1.6.2.2.3.1.3.4 |  |  | Coordinate Qualification Participants' connectivity proving | 0% | Tue 31/12/24 | Mon 10/03/25 | 50 days | Tue 31/12/24 | Mon 10/03/25 | 1409 | 1411SS,1418 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.3.1.3.5 |  |  | Assurance of Qualification Participants' connectivity proving | 0% | Tue 31/12/24 | Mon 10/03/25 | 50 days | Tue 31/12/24 | Mon 10/03/25 | 1410SS |  | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
7 | 1.6.2.2.3.1.4 |  |  | Test Data | 0% | Mon 30/12/24 | Mon 30/12/24 | 0 days | Mon 30/12/24 | Mon 30/12/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.3.1.4.1 | T3-QU-0026 | QAG | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 3 Participants) | 0% | Mon 30/12/24 | Mon 30/12/24 | 0 days | Mon 30/12/24 | Mon 30/12/24 | 1409 |  | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes | Richard Puddephatt
7 | 1.6.2.2.3.1.5 |  |  | Other Preparation | 0% | Tue 01/10/24 | Mon 10/03/25 | 115 days | Tue 01/10/24 | Mon 10/03/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.3.1.5.1 |  |  | Onboarding of Test Participants to Test Management Tool | 0% | Tue 01/10/24 | Mon 10/03/25 | 115 days | Tue 01/10/24 | Mon 10/03/25 | 1401 | 1418 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.3.1.5.2 |  |  | Other Preparation (activities TBC) | 0% | Tue 01/10/24 | Mon 10/03/25 | 115 days | Tue 01/10/24 | Mon 10/03/25 | 1401 | 1418 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
7 | 1.6.2.2.3.1.6 |  |  | Monitoring of provisional Qualification Testing Tranche 3 Participants' PIT progress and test readiness | 0% | Tue 03/09/24 | Mon 10/02/25 | 115 days | Tue 03/09/24 | Mon 10/02/25 | 1389 |  | 0 days | 0 days | 0 days |  |  |  |  | 5 | Yes
7 | 1.6.2.2.3.1.7 | T3-QU-0038 | QAG | Qualification Testing Tranche 3 Test Readiness confirmed | 0% | Mon 10/03/25 | Mon 10/03/25 | 0 days | Mon 10/03/25 | Mon 10/03/25 | 141014151416 |  | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
6 | 1.6.2.2.3.2 |  |  | PP Tranche 3 Preparation | 0% | Tue 01/10/24 | Mon 10/03/25 | 115 days | Tue 01/10/24 | Mon 10/03/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.2.3.2.1 | T3-QU-0014 | QAG | Confirm Qualification Testing Tranche 3 Participants | 0% | Tue 01/10/24 | Tue 01/10/24 | 0 days | Tue 01/10/24 | Tue 01/10/24 | 1579FS-6 mons | 14221428 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP, IPA |  |  | 5 | Yes
7 | 1.6.2.2.3.2.2 |  |  | Environments | 0% | Tue 01/10/24 | Mon 10/03/25 | 115 days | Tue 01/10/24 | Mon 10/03/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.3.2.2.1 |  |  | UIT environment preparation | 0% | Tue 01/10/24 | Mon 23/12/24 | 60 days | Tue 01/10/24 | Mon 23/12/24 | 1420 | 1423FF | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.3.2.2.2 |  |  | Deployment of MHHS solution code to UIT environments | 0% | Tue 10/12/24 | Mon 23/12/24 | 10 days | Tue 10/12/24 | Mon 23/12/24 | 1422FF | 1424FS+5 days | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.3.2.2.3 | T3-QU-0025 | QAG | Qualification Testing Tranche 3 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Mon 30/12/24 | Mon 30/12/24 | 0 days | Mon 30/12/24 | Mon 30/12/24 | 1423FS+5 days | 1425 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP, IPA |  |  | 5 | Yes
8 | 1.6.2.2.3.2.2.4 |  |  | UIT environment connectivity proving | 0% | Tue 31/12/24 | Mon 10/03/25 | 50 days | Tue 31/12/24 | Mon 10/03/25 | 1424 | 1426SS,1429FF | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.3.2.2.5 |  |  | Submit evidence of UIT environment connectivity proving to Programme for assurance | 0% | Tue 31/12/24 | Mon 10/03/25 | 50 days | Tue 31/12/24 | Mon 10/03/25 | 1425SS |  | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
7 | 1.6.2.2.3.2.3 |  |  | Other Preparation | 0% | Tue 01/10/24 | Mon 10/03/25 | 115 days | Tue 01/10/24 | Mon 10/03/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.3.2.3.1 |  |  | Other Preparation (incl. test execution planning) | 0% | Tue 01/10/24 | Mon 10/03/25 | 115 days | Tue 01/10/24 | Mon 10/03/25 | 1420 |  | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
7 | 1.6.2.2.3.2.4 | T3-QU-0038 | QAG | Qualification Testing Tranche 3 Test Readiness confirmed | 0% | Mon 10/03/25 | Mon 10/03/25 | 0 days | Mon 10/03/25 | Mon 10/03/25 | 1425FF |  | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
5 | 1.6.2.2.4 |  |  | Tranche 4 Preparation | 0% | Tue 29/10/24 | Mon 07/04/25 | 115 days | Tue 29/10/24 | Mon 07/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.6.2.2.4.1 |  |  | SI Tranche 4 Preparation | 0% | Tue 29/10/24 | Mon 07/04/25 | 115 days | Tue 29/10/24 | Mon 07/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.2.4.1.1 | T3-QU-0015 | QAG | Confirm Qualification Testing Tranche 4 Participants | 0% | Tue 29/10/24 | Tue 29/10/24 | 0 days | Tue 29/10/24 | Tue 29/10/24 | 1584FS-6 mons | 1.4461e+23 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP, IPA |  |  | 5 | Yes
7 | 1.6.2.2.4.1.2 |  |  | Test execution schedule | 0% | Tue 29/10/24 | Mon 27/01/25 | 65 days | Tue 29/10/24 | Mon 27/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.4.1.2.1 |  |  | Develop document | 0% | Tue 29/10/24 | Mon 23/12/24 | 40 days | Tue 29/10/24 | Mon 23/12/24 | 1432 | 1435 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
8 | 1.6.2.2.4.1.2.2 |  |  | Review & agree document | 0% | Tue 24/12/24 | Mon 20/01/25 | 20 days | Tue 24/12/24 | Mon 20/01/25 | 1434 | 1436FS+5 days | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
8 | 1.6.2.2.4.1.2.3 | T3-QU-0030 | QAG | Qualification Testing Tranche 4 Test execution schedule approved | 0% | Mon 27/01/25 | Mon 27/01/25 | 0 days | Mon 27/01/25 | Mon 27/01/25 | 1435FS+5 days | 1449 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
7 | 1.6.2.2.4.1.3 |  |  | Environments | 0% | Tue 29/10/24 | Mon 07/04/25 | 115 days | Tue 29/10/24 | Mon 07/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.4.1.3.1 |  |  | Coordinate Qualification Participants' environment preparation | 0% | Tue 29/10/24 | Mon 20/01/25 | 60 days | Tue 29/10/24 | Mon 20/01/25 | 1432 | 1439FF | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.4.1.3.2 |  |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 0% | Tue 07/01/25 | Mon 20/01/25 | 10 days | Tue 07/01/25 | Mon 20/01/25 | 1438FF | 1440FS+5 days | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.4.1.3.3 | T3-QU-0031 | QAG | Qualification Testing Tranche 4 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Mon 27/01/25 | Mon 27/01/25 | 0 days | Mon 27/01/25 | Mon 27/01/25 | 1439FS+5 days | 144114441449 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP, IPA |  |  | 5 | Yes
8 | 1.6.2.2.4.1.3.4 |  |  | Coordinate Qualification Participants' connectivity proving | 0% | Tue 28/01/25 | Mon 07/04/25 | 50 days | Tue 28/01/25 | Mon 07/04/25 | 1440 | 1442SS,1449 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.4.1.3.5 |  |  | Assurance of Qualification Participants' connectivity proving | 0% | Tue 28/01/25 | Mon 07/04/25 | 50 days | Tue 28/01/25 | Mon 07/04/25 | 1441SS |  | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
7 | 1.6.2.2.4.1.4 |  |  | Test Data | 0% | Mon 27/01/25 | Mon 27/01/25 | 0 days | Mon 27/01/25 | Mon 27/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.4.1.4.1 | T3-QU-0032 | QAG | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 4 Participants) | 0% | Mon 27/01/25 | Mon 27/01/25 | 0 days | Mon 27/01/25 | Mon 27/01/25 | 1440 | 1449 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes | Richard Puddephatt
7 | 1.6.2.2.4.1.5 |  |  | Other Preparation | 0% | Tue 29/10/24 | Mon 07/04/25 | 115 days | Tue 29/10/24 | Mon 07/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.4.1.5.1 |  |  | Onboarding of Test Participants to Test Management Tool | 0% | Tue 29/10/24 | Mon 07/04/25 | 115 days | Tue 29/10/24 | Mon 07/04/25 | 1432 | 1449 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.4.1.5.2 |  |  | Other Preparation (activities TBC) | 0% | Tue 29/10/24 | Mon 07/04/25 | 115 days | Tue 29/10/24 | Mon 07/04/25 | 1432 | 1449 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
7 | 1.6.2.2.4.1.6 |  |  | Monitoring of provisional Qualification Testing Tranche 4 Participants' PIT progress and test readiness | 0% | Tue 29/10/24 | Mon 07/04/25 | 115 days | Tue 29/10/24 | Mon 07/04/25 | 1432 |  | 0 days | 0 days | 0 days |  |  |  |  | 5 | Yes
7 | 1.6.2.2.4.1.7 | T3-QU-0043 | QAG | Qualification Testing Tranche 4 Test Readiness confirmed | 0% | Mon 07/04/25 | Mon 07/04/25 | 0 days | Mon 07/04/25 | Mon 07/04/25 | 1.4411e+27 |  | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
6 | 1.6.2.2.4.2 |  |  | PP Tranche 4 Preparation | 0% | Tue 29/10/24 | Mon 07/04/25 | 115 days | Tue 29/10/24 | Mon 07/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.2.4.2.1 | T3-QU-0015 | QAG | Confirm Qualification Testing Tranche 4 Participants | 0% | Tue 29/10/24 | Tue 29/10/24 | 0 days | Tue 29/10/24 | Tue 29/10/24 | 1584FS-6 mons | 14531459 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP, IPA |  |  | 5 | Yes
7 | 1.6.2.2.4.2.2 |  |  | Environments | 0% | Tue 29/10/24 | Mon 07/04/25 | 115 days | Tue 29/10/24 | Mon 07/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.4.2.2.1 |  |  | UIT environment preparation | 0% | Tue 29/10/24 | Mon 20/01/25 | 60 days | Tue 29/10/24 | Mon 20/01/25 | 1451 | 1454FF | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.4.2.2.2 |  |  | Deployment of MHHS solution code to UIT environments | 0% | Tue 07/01/25 | Mon 20/01/25 | 10 days | Tue 07/01/25 | Mon 20/01/25 | 1453FF | 1455FS+5 days | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.4.2.2.3 | T3-QU-0031 | QAG | Qualification Testing Tranche 4 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Mon 27/01/25 | Mon 27/01/25 | 0 days | Mon 27/01/25 | Mon 27/01/25 | 1454FS+5 days | 1456 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP, IPA |  |  | 5 | Yes
8 | 1.6.2.2.4.2.2.4 |  |  | UIT environment connectivity proving | 0% | Tue 28/01/25 | Mon 07/04/25 | 50 days | Tue 28/01/25 | Mon 07/04/25 | 1455 | 1457SS,1460FF | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.4.2.2.5 |  |  | Submit evidence of UIT environment connectivity proving to Programme for assurance | 0% | Tue 28/01/25 | Mon 07/04/25 | 50 days | Tue 28/01/25 | Mon 07/04/25 | 1456SS |  | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
7 | 1.6.2.2.4.2.3 |  |  | Other Preparation | 0% | Tue 29/10/24 | Mon 07/04/25 | 115 days | Tue 29/10/24 | Mon 07/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.4.2.3.1 |  |  | Other Preparation (incl. test execution planning) | 0% | Tue 29/10/24 | Mon 07/04/25 | 115 days | Tue 29/10/24 | Mon 07/04/25 | 1451 |  | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
7 | 1.6.2.2.4.2.4 | T3-QU-0043 | QAG | Qualification Testing Tranche 4 Test Readiness confirmed | 0% | Mon 07/04/25 | Mon 07/04/25 | 0 days | Mon 07/04/25 | Mon 07/04/25 | 1456FF |  | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
5 | 1.6.2.2.5 |  |  | Tranche 5 Preparation | 0% | Tue 26/11/24 | Mon 05/05/25 | 115 days | Tue 26/11/24 | Mon 05/05/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.6.2.2.5.1 |  |  | SI Tranche 5 Preparation | 0% | Tue 26/11/24 | Mon 05/05/25 | 115 days | Tue 26/11/24 | Mon 05/05/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.2.5.1.1 | T3-QU-0019 | QAG | Confirm Qualification Testing Tranche 5 Participants | 0% | Tue 26/11/24 | Tue 26/11/24 | 0 days | Tue 26/11/24 | Tue 26/11/24 | 1589FS-6 mons | 1.4771e+23 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP, IPA |  |  | 5 | Yes
7 | 1.6.2.2.5.1.2 |  |  | Test execution schedule | 0% | Tue 26/11/24 | Mon 24/02/25 | 65 days | Tue 26/11/24 | Mon 24/02/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.5.1.2.1 |  |  | Develop document | 0% | Tue 26/11/24 | Mon 20/01/25 | 40 days | Tue 26/11/24 | Mon 20/01/25 | 1463 | 1466 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
8 | 1.6.2.2.5.1.2.2 |  |  | Review & agree document | 0% | Tue 21/01/25 | Mon 17/02/25 | 20 days | Tue 21/01/25 | Mon 17/02/25 | 1465 | 1467FS+5 days | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
8 | 1.6.2.2.5.1.2.3 | T3-QU-0035 | QAG | Qualification Testing Tranche 5 Test execution schedule approved | 0% | Mon 24/02/25 | Mon 24/02/25 | 0 days | Mon 24/02/25 | Mon 24/02/25 | 1466FS+5 days |  | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
7 | 1.6.2.2.5.1.3 |  |  | Environments | 0% | Tue 26/11/24 | Mon 05/05/25 | 115 days | Tue 26/11/24 | Mon 05/05/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.5.1.3.1 |  |  | Coordinate Qualification Participants' environment preparation | 0% | Tue 26/11/24 | Mon 17/02/25 | 60 days | Tue 26/11/24 | Mon 17/02/25 | 1463 | 1470FF | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.5.1.3.2 |  |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 0% | Tue 04/02/25 | Mon 17/02/25 | 10 days | Tue 04/02/25 | Mon 17/02/25 | 1469FF | 1471FS+5 days | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.5.1.3.3 | T3-QU-0036 | QAG | Qualification Testing Tranche 5 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Mon 24/02/25 | Mon 24/02/25 | 0 days | Mon 24/02/25 | Mon 24/02/25 | 1470FS+5 days | 147214751480 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP, IPA |  |  | 5 | Yes
8 | 1.6.2.2.5.1.3.4 |  |  | Coordinate Qualification Participants' connectivity proving | 0% | Tue 25/02/25 | Thu 01/05/25 | 48 days | Tue 25/02/25 | Mon 05/05/25 | 1471 | 1473SS,1480 | 0 days | -2 days | -2 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.5.1.3.5 |  |  | Assurance of Qualification Participants' connectivity proving | 0% | Tue 25/02/25 | Mon 05/05/25 | 50 days | Tue 25/02/25 | Mon 05/05/25 | 1472SS | 1480 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
7 | 1.6.2.2.5.1.4 |  |  | Test Data | 0% | Mon 24/02/25 | Mon 24/02/25 | 0 days | Mon 24/02/25 | Mon 24/02/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.5.1.4.1 | T3-QU-0037 | QAG | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 5 Participants) | 0% | Mon 24/02/25 | Mon 24/02/25 | 0 days | Mon 24/02/25 | Mon 24/02/25 | 1471 | 1480 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes | Richard Puddephatt
7 | 1.6.2.2.5.1.5 |  |  | Other Preparation | 0% | Tue 26/11/24 | Mon 05/05/25 | 115 days | Tue 26/11/24 | Mon 05/05/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.5.1.5.1 |  |  | Onboarding of Test Participants to Test Management Tool | 0% | Tue 26/11/24 | Mon 05/05/25 | 115 days | Tue 26/11/24 | Mon 05/05/25 | 1463 | 1480 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.5.1.5.2 |  |  | Other Preparation (activities TBC) | 0% | Tue 26/11/24 | Mon 05/05/25 | 115 days | Tue 26/11/24 | Mon 05/05/25 | 1463 | 1480 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
7 | 1.6.2.2.5.1.6 |  |  | Monitoring of provisional Qualification Testing Tranche 5 Participants' PIT progress and test readiness | 0% | Tue 26/11/24 | Mon 05/05/25 | 115 days | Tue 26/11/24 | Mon 05/05/25 | 1463 |  | 0 days | 0 days | 0 days |  |  |  |  | 5 | Yes
7 | 1.6.2.2.5.1.7 | T3-QU-0048 | QAG | Qualification Testing Tranche 5 Test Readiness confirmed | 0% | Mon 05/05/25 | Mon 05/05/25 | 0 days | Mon 05/05/25 | Mon 05/05/25 | 1.4721e+27 |  | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
6 | 1.6.2.2.5.2 |  |  | PP Tranche 5 Preparation | 0% | Tue 26/11/24 | Mon 05/05/25 | 115 days | Tue 26/11/24 | Mon 05/05/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.2.5.2.1 | T3-QU-0019 | QAG | Confirm Qualification Testing Tranche 5 Participants | 0% | Tue 26/11/24 | Tue 26/11/24 | 0 days | Tue 26/11/24 | Tue 26/11/24 | 1589FS-6 mons | 14841490 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP, IPA |  |  | 5 | Yes
7 | 1.6.2.2.5.2.2 |  |  | Environments | 0% | Tue 26/11/24 | Mon 05/05/25 | 115 days | Tue 26/11/24 | Mon 05/05/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.5.2.2.1 |  |  | UIT environment preparation | 0% | Tue 26/11/24 | Mon 17/02/25 | 60 days | Tue 26/11/24 | Mon 17/02/25 | 1482 | 1485FF | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.5.2.2.2 |  |  | Deployment of MHHS solution code to UIT environments | 0% | Tue 04/02/25 | Mon 17/02/25 | 10 days | Tue 04/02/25 | Mon 17/02/25 | 1484FF | 1486FS+5 days | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.5.2.2.3 | T3-QU-0036 | QAG | Qualification Testing Tranche 5 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Mon 24/02/25 | Mon 24/02/25 | 0 days | Mon 24/02/25 | Mon 24/02/25 | 1485FS+5 days | 1487 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP, IPA |  |  | 5 | Yes
8 | 1.6.2.2.5.2.2.4 |  |  | UIT environment connectivity proving | 0% | Tue 25/02/25 | Mon 05/05/25 | 50 days | Tue 25/02/25 | Mon 05/05/25 | 1486 | 1488SS,1491FF | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.5.2.2.5 |  |  | Submit evidence of UIT environment connectivity proving to Programme for assurance | 0% | Tue 25/02/25 | Mon 05/05/25 | 50 days | Tue 25/02/25 | Mon 05/05/25 | 1487SS |  | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
7 | 1.6.2.2.5.2.3 |  |  | Other Preparation | 0% | Tue 26/11/24 | Mon 05/05/25 | 115 days | Tue 26/11/24 | Mon 05/05/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.5.2.3.1 |  |  | Other Preparation (incl. test execution planning) | 0% | Tue 26/11/24 | Mon 05/05/25 | 115 days | Tue 26/11/24 | Mon 05/05/25 | 1482 |  | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
7 | 1.6.2.2.5.2.4 | T3-QU-0048 | QAG | Qualification Testing Tranche 5 Test Readiness confirmed | 0% | Mon 05/05/25 | Mon 05/05/25 | 0 days | Mon 05/05/25 | Mon 05/05/25 | 1487FF |  | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
5 | 1.6.2.2.6 |  |  | Tranche 6 Preparation | 0% | Tue 24/12/24 | Mon 02/06/25 | 115 days | Tue 24/12/24 | Mon 02/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.6.2.2.6.1 |  |  | SI Tranche 6 Preparation | 0% | Tue 24/12/24 | Mon 02/06/25 | 115 days | Tue 24/12/24 | Mon 02/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.2.6.1.1 | T3-QU-0023 | QAG | Confirm Qualification Testing Tranche 6 Participants | 0% | Tue 24/12/24 | Tue 24/12/24 | 0 days | Tue 24/12/24 | Tue 24/12/24 | 1594FS-6 mons | 1.5081e+23 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP, IPA |  |  | 5 | Yes
7 | 1.6.2.2.6.1.2 |  |  | Test execution schedule | 0% | Tue 24/12/24 | Mon 24/03/25 | 65 days | Tue 24/12/24 | Mon 24/03/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.6.1.2.1 |  |  | Develop document | 0% | Tue 24/12/24 | Mon 17/02/25 | 40 days | Tue 24/12/24 | Mon 17/02/25 | 1494 | 1497 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
8 | 1.6.2.2.6.1.2.2 |  |  | Review & agree document | 0% | Tue 18/02/25 | Mon 17/03/25 | 20 days | Tue 18/02/25 | Mon 17/03/25 | 1496 | 1498FS+5 days | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
8 | 1.6.2.2.6.1.2.3 | T3-QU-0040 | QAG | Qualification Testing Tranche 6 Test execution schedule approved | 0% | Mon 24/03/25 | Mon 24/03/25 | 0 days | Mon 24/03/25 | Mon 24/03/25 | 1497FS+5 days | 1511 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
7 | 1.6.2.2.6.1.3 |  |  | Environments | 0% | Tue 24/12/24 | Mon 02/06/25 | 115 days | Tue 24/12/24 | Mon 02/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.6.1.3.1 |  |  | Coordinate Qualification Participants' environment preparation | 0% | Tue 24/12/24 | Mon 17/03/25 | 60 days | Tue 24/12/24 | Mon 17/03/25 | 1494 | 1501FF | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.6.1.3.2 |  |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 0% | Tue 04/03/25 | Mon 17/03/25 | 10 days | Tue 04/03/25 | Mon 17/03/25 | 1500FF | 1502FS+5 days | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.6.1.3.3 | T3-QU-0041 | QAG | Qualification Testing Tranche 6 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Mon 24/03/25 | Mon 24/03/25 | 0 days | Mon 24/03/25 | Mon 24/03/25 | 1501FS+5 days | 150315061511 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP, IPA |  |  | 5 | Yes
8 | 1.6.2.2.6.1.3.4 |  |  | Coordinate Qualification Participants' connectivity proving | 0% | Tue 25/03/25 | Mon 02/06/25 | 50 days | Tue 25/03/25 | Mon 02/06/25 | 1502 | 1504SS,1511 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.6.1.3.5 |  |  | Assurance of Qualification Participants' connectivity proving | 0% | Tue 25/03/25 | Mon 02/06/25 | 50 days | Tue 25/03/25 | Mon 02/06/25 | 1503SS |  | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
7 | 1.6.2.2.6.1.4 |  |  | Test Data | 0% | Mon 24/03/25 | Mon 24/03/25 | 0 days | Mon 24/03/25 | Mon 24/03/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.6.1.4.1 | T3-QU-0042 | QAG | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 6 Participants) | 0% | Mon 24/03/25 | Mon 24/03/25 | 0 days | Mon 24/03/25 | Mon 24/03/25 | 1502 | 1511 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes | Richard Puddephatt
7 | 1.6.2.2.6.1.5 |  |  | Other Preparation | 0% | Tue 24/12/24 | Mon 02/06/25 | 115 days | Tue 24/12/24 | Mon 02/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.6.1.5.1 |  |  | Onboarding of Test Participants to Test Management Tool | 0% | Tue 24/12/24 | Mon 02/06/25 | 115 days | Tue 24/12/24 | Mon 02/06/25 | 1494 | 1511 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.6.1.5.2 |  |  | Other Preparation (activities TBC) | 0% | Tue 24/12/24 | Mon 02/06/25 | 115 days | Tue 24/12/24 | Mon 02/06/25 | 1494 | 1511 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
7 | 1.6.2.2.6.1.6 |  |  | Monitoring of provisional Qualification Testing Tranche 6 Participants' PIT progress and test readiness | 0% | Tue 24/12/24 | Mon 02/06/25 | 115 days | Tue 24/12/24 | Mon 02/06/25 | 1494 |  | 0 days | 0 days | 0 days |  |  |  |  | 5 | Yes
7 | 1.6.2.2.6.1.7 | T3-QU-0050 | QAG | Qualification Testing Tranche 6 Test Readiness confirmed | 0% | Mon 02/06/25 | Mon 02/06/25 | 0 days | Mon 02/06/25 | Mon 02/06/25 | 1.5032e+27 |  | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
6 | 1.6.2.2.6.2 |  |  | PP Tranche 6 Preparation | 0% | Tue 24/12/24 | Mon 02/06/25 | 115 days | Tue 24/12/24 | Mon 02/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.2.6.2.1 | T3-QU-0023 | QAG | Confirm Qualification Testing Tranche 6 Participants | 0% | Tue 24/12/24 | Tue 24/12/24 | 0 days | Tue 24/12/24 | Tue 24/12/24 | 1594FS-6 mons | 15151521 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP, IPA |  |  | 5 | Yes
7 | 1.6.2.2.6.2.2 |  |  | Environments | 0% | Tue 24/12/24 | Mon 02/06/25 | 115 days | Tue 24/12/24 | Mon 02/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.6.2.2.1 |  |  | UIT environment preparation | 0% | Tue 24/12/24 | Mon 17/03/25 | 60 days | Tue 24/12/24 | Mon 17/03/25 | 1513 | 1516FF | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.6.2.2.2 |  |  | Deployment of MHHS solution code to UIT environments | 0% | Tue 04/03/25 | Mon 17/03/25 | 10 days | Tue 04/03/25 | Mon 17/03/25 | 1515FF | 1517FS+5 days | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.6.2.2.3 | T3-QU-0041 | QAG | Qualification Testing Tranche 6 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Mon 24/03/25 | Mon 24/03/25 | 0 days | Mon 24/03/25 | Mon 24/03/25 | 1516FS+5 days | 1518 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP, IPA |  |  | 5 | Yes
8 | 1.6.2.2.6.2.2.4 |  |  | UIT environment connectivity proving | 0% | Tue 25/03/25 | Mon 02/06/25 | 50 days | Tue 25/03/25 | Mon 02/06/25 | 1517 | 1519SS,1522FF | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.6.2.2.5 |  |  | Submit evidence of UIT environment connectivity proving to Programme for assurance | 0% | Tue 25/03/25 | Mon 02/06/25 | 50 days | Tue 25/03/25 | Mon 02/06/25 | 1518SS |  | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
7 | 1.6.2.2.6.2.3 |  |  | Other Preparation | 0% | Tue 24/12/24 | Mon 02/06/25 | 115 days | Tue 24/12/24 | Mon 02/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.6.2.3.1 |  |  | Other Preparation (incl. test execution planning) | 0% | Tue 24/12/24 | Mon 02/06/25 | 115 days | Tue 24/12/24 | Mon 02/06/25 | 1513 |  | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
7 | 1.6.2.2.6.2.4 | T3-QU-0050 | QAG | Qualification Testing Tranche 6 Test Readiness confirmed | 0% | Mon 02/06/25 | Mon 02/06/25 | 0 days | Mon 02/06/25 | Mon 02/06/25 | 1518FF |  | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
5 | 1.6.2.2.7 |  |  | Tranche 7 Preparation | 0% | Tue 21/01/25 | Mon 30/06/25 | 115 days | Tue 21/01/25 | Mon 30/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.6.2.2.7.1 |  |  | SI Tranche 7 Preparation | 0% | Tue 21/01/25 | Mon 30/06/25 | 115 days | Tue 21/01/25 | Mon 30/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.2.7.1.1 | T3-QU-0029 | QAG | Confirm Qualification Testing Tranche 7 Participants | 0% | Tue 21/01/25 | Tue 21/01/25 | 0 days | Tue 21/01/25 | Tue 21/01/25 | 1599FS-6 mons | 1.5392e+23 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP, IPA |  |  | 5 | Yes
7 | 1.6.2.2.7.1.2 |  |  | Test execution schedule | 0% | Tue 21/01/25 | Mon 21/04/25 | 65 days | Tue 21/01/25 | Mon 21/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.7.1.2.1 |  |  | Develop document | 0% | Tue 21/01/25 | Mon 17/03/25 | 40 days | Tue 21/01/25 | Mon 17/03/25 | 1525 | 1528 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
8 | 1.6.2.2.7.1.2.2 |  |  | Review & agree document | 0% | Tue 18/03/25 | Mon 14/04/25 | 20 days | Tue 18/03/25 | Mon 14/04/25 | 1527 | 1529FS+5 days | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
8 | 1.6.2.2.7.1.2.3 | T3-QU-0045 | QAG | Qualification Testing Tranche 7 Test execution schedule approved | 0% | Mon 21/04/25 | Mon 21/04/25 | 0 days | Mon 21/04/25 | Mon 21/04/25 | 1528FS+5 days | 1542 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
7 | 1.6.2.2.7.1.3 |  |  | Environments | 0% | Tue 21/01/25 | Mon 30/06/25 | 115 days | Tue 21/01/25 | Mon 30/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.7.1.3.1 |  |  | Coordinate Qualification Participants' environment preparation | 0% | Tue 21/01/25 | Mon 14/04/25 | 60 days | Tue 21/01/25 | Mon 14/04/25 | 1525 | 1532FF | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.7.1.3.2 |  |  | Coordinate deployment of MHHS solution code to Qualification Participants' UIT environments | 0% | Tue 01/04/25 | Mon 14/04/25 | 10 days | Tue 01/04/25 | Mon 14/04/25 | 1531FF | 1533FS+5 days | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.7.1.3.3 | T3-QU-0046 | QAG | Qualification Testing Tranche 7 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Mon 21/04/25 | Mon 21/04/25 | 0 days | Mon 21/04/25 | Mon 21/04/25 | 1532FS+5 days | 153415371542 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP, IPA |  |  | 5 | Yes
8 | 1.6.2.2.7.1.3.4 |  |  | Coordinate Qualification Participants' connectivity proving | 0% | Tue 22/04/25 | Mon 30/06/25 | 50 days | Tue 22/04/25 | Mon 30/06/25 | 1533 | 1535SS,1542 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.7.1.3.5 |  |  | Assurance of Qualification Participants' connectivity proving | 0% | Tue 22/04/25 | Mon 30/06/25 | 50 days | Tue 22/04/25 | Mon 30/06/25 | 1534SS |  | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
7 | 1.6.2.2.7.1.4 |  |  | Test Data | 0% | Mon 21/04/25 | Mon 21/04/25 | 0 days | Mon 21/04/25 | Mon 21/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.7.1.4.1 | T3-QU-0047 | QAG | Confirm MPAN range to Code Bodies (for Code Bodies to allocate to Qualification Testing Tranche 7 Participants) | 0% | Mon 21/04/25 | Mon 21/04/25 | 0 days | Mon 21/04/25 | Mon 21/04/25 | 1533 | 1542 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes | Richard Puddephatt
7 | 1.6.2.2.7.1.5 |  |  | Other Preparation | 0% | Tue 21/01/25 | Mon 30/06/25 | 115 days | Tue 21/01/25 | Mon 30/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.7.1.5.1 |  |  | Onboarding of Test Participants to Test Management Tool | 0% | Tue 21/01/25 | Mon 30/06/25 | 115 days | Tue 21/01/25 | Mon 30/06/25 | 1525 | 1542 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP |  |  | 5 | Yes
8 | 1.6.2.2.7.1.5.2 |  |  | Other Preparation (activities TBC) | 0% | Tue 21/01/25 | Mon 30/06/25 | 115 days | Tue 21/01/25 | Mon 30/06/25 | 1525 | 1542 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
7 | 1.6.2.2.7.1.6 |  |  | Monitoring of provisional Qualification Testing Tranche 7 Participants' PIT progress and test readiness | 0% | Tue 21/01/25 | Mon 30/06/25 | 115 days | Tue 21/01/25 | Mon 30/06/25 | 1525 |  | 0 days | 0 days | 0 days |  |  |  |  | 5 | Yes
7 | 1.6.2.2.7.1.7 | T3-QU-0052 | QAG | Qualification Testing Tranche 7 Test Readiness confirmed | 0% | Mon 30/06/25 | Mon 30/06/25 | 0 days | Mon 30/06/25 | Mon 30/06/25 | 1.5342e+27 |  | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
6 | 1.6.2.2.7.2 |  |  | PP Tranche 7 Preparation | 0% | Tue 21/01/25 | Mon 30/06/25 | 115 days | Tue 21/01/25 | Mon 30/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.6.2.2.7.2.1 | T3-QU-0029 | QAG | Confirm Qualification Testing Tranche 7 Participants | 0% | Tue 21/01/25 | Tue 21/01/25 | 0 days | Tue 21/01/25 | Tue 21/01/25 | 1599FS-6 mons | 15461552 | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP, IPA |  |  | 5 | Yes
7 | 1.6.2.2.7.2.2 |  |  | Environments | 0% | Tue 21/01/25 | Mon 30/06/25 | 115 days | Tue 21/01/25 | Mon 30/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.7.2.2.1 |  |  | UIT environment preparation | 0% | Tue 21/01/25 | Mon 14/04/25 | 60 days | Tue 21/01/25 | Mon 14/04/25 | 1544 | 1547FF | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.7.2.2.2 |  |  | Deployment of MHHS solution code to UIT environments | 0% | Tue 01/04/25 | Mon 14/04/25 | 10 days | Tue 01/04/25 | Mon 14/04/25 | 1546FF | 1548FS+5 days | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.7.2.2.3 | T3-QU-0046 | QAG | Qualification Testing Tranche 7 Participants' UIT environments ready to start connectivity proving (incl. certificates and security compliance) | 0% | Mon 21/04/25 | Mon 21/04/25 | 0 days | Mon 21/04/25 | Mon 21/04/25 | 1547FS+5 days | 1549 | 0 days | 0 days | 0 days | SI Test | Code Bodies, PP, IPA |  |  | 5 | Yes
8 | 1.6.2.2.7.2.2.4 |  |  | UIT environment connectivity proving | 0% | Tue 22/04/25 | Mon 30/06/25 | 50 days | Tue 22/04/25 | Mon 30/06/25 | 1548 | 1550SS,1553FF | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
8 | 1.6.2.2.7.2.2.5 |  |  | Submit evidence of UIT environment connectivity proving to Programme for assurance | 0% | Tue 22/04/25 | Mon 30/06/25 | 50 days | Tue 22/04/25 | Mon 30/06/25 | 1549SS |  | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
7 | 1.6.2.2.7.2.3 |  |  | Other Preparation | 0% | Tue 21/01/25 | Mon 30/06/25 | 115 days | Tue 21/01/25 | Mon 30/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
8 | 1.6.2.2.7.2.3.1 |  |  | Other Preparation (incl. test execution planning) | 0% | Tue 21/01/25 | Mon 30/06/25 | 115 days | Tue 21/01/25 | Mon 30/06/25 | 1544 |  | 0 days | 0 days | 0 days | PP | Code Bodies,SI Test |  |  | 5 | Yes
7 | 1.6.2.2.7.2.4 | T3-QU-0052 | QAG | Qualification Testing Tranche 7 Test Readiness confirmed | 0% | Mon 30/06/25 | Mon 30/06/25 | 0 days | Mon 30/06/25 | Mon 30/06/25 | 1549FF |  | 0 days | 0 days | 0 days | Code Bodies | SI Test, PP |  |  | 5 | Yes
3 | 1.6.3 |  |  | Qualification Assessment Document (QAD) Process | 0% | Thu 18/01/24 | Mon 23/03/26 | 568 days | Thu 18/01/24 | Mon 23/03/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.2 | Yes | N/A
4 | 1.6.3.1 |  |  | Qualification Assessment Document Preparation Initial Draft (Functional) | 0% | Thu 18/01/24 | Wed 28/02/24 | 30 days | Thu 18/01/24 | Wed 28/02/24 | 497810803 | 1556 | 0 days | 0 days | 0 days | Code Bodies |  |  |  | 5.2 | Yes
4 | 1.6.3.2 |  |  | Artefact review (via QWG) and updates | 0% | Thu 29/02/24 | Wed 13/03/24 | 10 days | Thu 29/02/24 | Wed 13/03/24 | 1555 | 1557 | 0 days | 0 days | 0 days | PP |  |  |  | 5.2 | Yes
4 | 1.6.3.3 |  |  | Qualification Assessment Document Initial Draft final review and approval by BSC PAB and REC Manager | 0% | Thu 14/03/24 | Tue 16/04/24 | 24 days | Thu 14/03/24 | Tue 16/04/24 | 1556 | 1558 | 0 days | 0 days | 0 days | Code Bodies |  |  |  | 5.2 | Yes
4 | 1.6.3.4 | T3-QU-0066 | QAG | Qualification Assessment Document v1 approved by REC PAB and BSC PAB | 100% | Tue 16/04/24 | Tue 16/04/24 | 0 days | Tue 16/04/24 | Tue 16/04/24 | 1557 | 1562FS+3 days,1563 | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5.1 | Yes | Nicola Farley
4 | 1.6.3.5 |  |  | Qualification Assessment Document Preparation (Non-Functional, Migration, Operational) | 0% | Thu 15/08/24 | Wed 25/09/24 | 30 days | Thu 15/08/24 | Wed 25/09/24 | 1704SS,1335,1701SS | 1560 | 0 days | 0 days | 0 days | Code bodies |  |  |  | 5 | Yes
4 | 1.6.3.6 |  |  | Qualification Assessment Document final review and approval by BSC PAB and REC Manager | 0% | Thu 26/09/24 | Fri 25/10/24 | 22 days | Thu 26/09/24 | Fri 25/10/24 | 1559 | 1561 | 0 days | 0 days | 0 days | Code Bodies |  |  |  | 5 | Yes
4 | 1.6.3.7 | T3-QU-0067 | QAG | Qualification Assessment Document Baselined | 0% | Fri 25/10/24 | Fri 25/10/24 | 0 days | Fri 25/10/24 | Fri 25/10/24 | 1560 |  | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
4 | 1.6.3.8 |  |  | PPs complete Qualification Assessment Document process | 0% | Mon 22/04/24 | Mon 23/03/26 | 501 days | Mon 22/04/24 | Mon 23/03/26 | 1934FF-2 mons,1558FS+3 days,1704SS,1701SS | 1606SS | 0 days | 0 days | 0 days | PP | Code Bodies |  |  | 5 | Yes
4 | 1.6.3.9 |  |  | Qualification Assessment Document process monitoring | 0% | Wed 17/04/24 | Wed 18/03/26 | 501 days | Wed 17/04/24 | Wed 18/03/26 | 1934FF-2 mons,1558,1704SS,1701SS |  | 0 days | 0 days | 0 days | SI Test | PP,Code Bodies |  |  | 5 | Yes
3 | 1.6.4 |  |  | PAB Support | 0% | Tue 26/11/24 | Mon 16/03/26 | 340 days | Tue 26/11/24 | Mon 16/03/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.6.4.1 |  |  | Support PAB in Qualification setup, monitoring & reporting | 0% | Tue 26/11/24 | Mon 20/01/25 | 40 days | Tue 26/11/24 | Mon 20/01/25 | 1569FS-40 days |  | 0 days | 0 days | 0 days | SI Test | Code Bodies |  |  | 5 | Yes
4 | 1.6.4.2 |  |  | Support PAB throughout Qualification | 0% | Tue 21/01/25 | Mon 16/03/26 | 300 days | Tue 21/01/25 | Mon 16/03/26 | 1569SS |  | 0 days | 0 days | 0 days | SI Test | Code Bodies |  |  | 5 | Yes
3 | 1.6.5 |  |  | Qualification Testing Execution & PAB Approval (test execution schedule subject to Qualification Approach & Plan) | 0% | Mon 20/01/25 | Thu 12/03/26 | 298 days | Mon 20/01/25 | Mon 16/03/26 |  |  | 0 days | -2 days | -2 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.6.5.1 |  |  | Qualification Testing Tranche 1 | 0% | Mon 20/01/25 | Mon 29/09/25 | 180 days | Mon 20/01/25 | Mon 29/09/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.6.5.1.1 | T3-QU-0028 | QAG | Qualification Testing Tranche 1 Start | 0% | Mon 20/01/25 | Mon 20/01/25 | 0 days | Mon 20/01/25 | Mon 20/01/25 | 1046FS+1 day | 1339FS-6 mons,1357FS-6 mons,1574SS+20 days,2041FS-50 days,1565FS-40 days,1566SS,1570FS+140 days | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
5 | 1.6.5.1.2 | T3-QU-0054 | QAG | Qualification Testing Tranche 1 End | 0% | Mon 04/08/25 | Mon 04/08/25 | 0 days | Mon 04/08/25 | Mon 04/08/25 | 1569FS+140 days | 1613,1571FS+20 days,1572 | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
5 | 1.6.5.1.3 | T2-QU-0150 | QAG | BSC PAB & REC Manager approval of Qualification Testing Tranche 1 Completion (Start of Migration for Qualification Participants) | 0% | Mon 01/09/25 | Mon 01/09/25 | 0 days | Mon 01/09/25 | Mon 01/09/25 | 1570FS+20 days | 1934 | 0 days | 0 days | 0 days | Code Bodies | PP |  |  | 5 | Yes
5 | 1.6.5.1.4 |  |  | Qualification Testing Tranche 1 Participants mobilise production environments | 0% | Tue 05/08/25 | Mon 29/09/25 | 40 days | Tue 05/08/25 | Mon 29/09/25 | 1570 | 190119041907 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes
4 | 1.6.5.2 |  |  | Qualification Testing Tranche 2 | 0% | Mon 17/02/25 | Mon 27/10/25 | 180 days | Mon 17/02/25 | Mon 27/10/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.6.5.2.1 | T3-QU-0034 | QAG | Qualification Testing Tranche 2 Start | 0% | Mon 17/02/25 | Mon 17/02/25 | 0 days | Mon 17/02/25 | Mon 17/02/25 | 1569SS+20 days | 1370FS-6 mons,1389FS-6 mons,1579SS+20 days,1575FS+140 days | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
5 | 1.6.5.2.2 | T3-QU-0055 | QAG | Qualification Testing Tranche 2 End | 0% | Mon 01/09/25 | Mon 01/09/25 | 0 days | Mon 01/09/25 | Mon 01/09/25 | 1574FS+140 days | 1577,1576FS+20 days | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
5 | 1.6.5.2.3 | T2-QU-0200 | QAG | BSC PAB & REC Manager approval of Qualification Testing Tranche 2 Completion | 0% | Mon 29/09/25 | Mon 29/09/25 | 0 days | Mon 29/09/25 | Mon 29/09/25 | 1575FS+20 days | 1934 | 0 days | 0 days | 0 days | Code Bodies | PP |  |  | 5 | Yes
5 | 1.6.5.2.4 |  |  | Qualification Testing Tranche 2 Participants mobilise production environments | 0% | Tue 02/09/25 | Mon 27/10/25 | 40 days | Tue 02/09/25 | Mon 27/10/25 | 1575 |  | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes
4 | 1.6.5.3 |  |  | Qualification Testing Tranche 3 | 0% | Mon 17/03/25 | Mon 24/11/25 | 180 days | Mon 17/03/25 | Mon 24/11/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.6.5.3.1 | T3-QU-0039 | QAG | Qualification Testing Tranche 3 Start | 0% | Mon 17/03/25 | Mon 17/03/25 | 0 days | Mon 17/03/25 | Mon 17/03/25 | 1574SS+20 days | 1401FS-6 mons,1420FS-6 mons,1584SS+20 days,1580FS+140 days | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
5 | 1.6.5.3.2 | T3-QU-0056 | QAG | Qualification Testing Tranche 3 End | 0% | Mon 29/09/25 | Mon 29/09/25 | 0 days | Mon 29/09/25 | Mon 29/09/25 | 1579FS+140 days | 1582,1581FS+20 days | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
5 | 1.6.5.3.3 | T2-QU-0250 | QAG | BSC PAB & REC Manager approval of Qualification Testing Tranche 3 Completion | 0% | Mon 27/10/25 | Mon 27/10/25 | 0 days | Mon 27/10/25 | Mon 27/10/25 | 1580FS+20 days | 1934 | 0 days | 0 days | 0 days | Code Bodies | PP |  |  | 5 | Yes
5 | 1.6.5.3.4 |  |  | Qualification Testing Tranche 3 Participants mobilise production environments | 0% | Tue 30/09/25 | Mon 24/11/25 | 40 days | Tue 30/09/25 | Mon 24/11/25 | 1580 |  | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes
4 | 1.6.5.4 |  |  | Qualification Testing Tranche 4 | 0% | Mon 14/04/25 | Mon 22/12/25 | 180 days | Mon 14/04/25 | Mon 22/12/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.6.5.4.1 | T3-QU-0044 | QAG | Qualification Testing Tranche 4 Start | 0% | Mon 14/04/25 | Mon 14/04/25 | 0 days | Mon 14/04/25 | Mon 14/04/25 | 1579SS+20 days | 1432FS-6 mons,1451FS-6 mons,1589SS+20 days,1585FS+140 days | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
5 | 1.6.5.4.2 | T3-QU-0057 | QAG | Qualification Testing Tranche 4 End | 0% | Mon 27/10/25 | Mon 27/10/25 | 0 days | Mon 27/10/25 | Mon 27/10/25 | 1584FS+140 days | 1587,1586FS+20 days | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
5 | 1.6.5.4.3 | T2-QU-0300 | QAG | BSC PAB & REC Manager approval of Qualification Testing Tranche 4 Completion | 0% | Mon 24/11/25 | Mon 24/11/25 | 0 days | Mon 24/11/25 | Mon 24/11/25 | 1585FS+20 days | 1934 | 0 days | 0 days | 0 days | Code Bodies | PP |  |  | 5 | Yes
5 | 1.6.5.4.4 |  |  | Qualification Testing Tranche 4 Participants mobilise production environments | 0% | Tue 28/10/25 | Mon 22/12/25 | 40 days | Tue 28/10/25 | Mon 22/12/25 | 1585 |  | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes
4 | 1.6.5.5 |  |  | Qualification Testing Tranche 5 | 0% | Mon 12/05/25 | Mon 19/01/26 | 180 days | Mon 12/05/25 | Mon 19/01/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.6.5.5.1 | T3-QU-0049 | QAG | Qualification Testing Tranche 5 Start | 0% | Mon 12/05/25 | Mon 12/05/25 | 0 days | Mon 12/05/25 | Mon 12/05/25 | 1584SS+20 days | 1463FS-6 mons,1482FS-6 mons,1594SS+20 days,1590FS+140 days | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
5 | 1.6.5.5.2 | T3-QU-0058 | QAG | Qualification Testing Tranche 5 End | 0% | Mon 24/11/25 | Mon 24/11/25 | 0 days | Mon 24/11/25 | Mon 24/11/25 | 1589FS+140 days | 1592,1591FS+20 days | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
5 | 1.6.5.5.3 | T2-QU-0350 | QAG | BSC PAB & REC Manager approval of Qualification Testing Tranche 5 Completion | 0% | Mon 22/12/25 | Mon 22/12/25 | 0 days | Mon 22/12/25 | Mon 22/12/25 | 1590FS+20 days | 1934 | 0 days | 0 days | 0 days | Code Bodies | PP |  |  | 5 | Yes
5 | 1.6.5.5.4 |  |  | Qualification Testing Tranche 5 Participants mobilise production environments | 0% | Tue 25/11/25 | Mon 19/01/26 | 40 days | Tue 25/11/25 | Mon 19/01/26 | 1590 |  | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes
4 | 1.6.5.6 |  |  | Qualification Testing Tranche 6 | 0% | Mon 09/06/25 | Mon 16/02/26 | 180 days | Mon 09/06/25 | Mon 16/02/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.6.5.6.1 | T3-QU-0051 | QAG | Qualification Testing Tranche 6 Start | 0% | Mon 09/06/25 | Mon 09/06/25 | 0 days | Mon 09/06/25 | Mon 09/06/25 | 1589SS+20 days | 1494FS-6 mons,1513FS-6 mons,1599SS+20 days,1595FS+140 days | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
5 | 1.6.5.6.2 | T3-QU-0059 | QAG | Qualification Testing Tranche 6 End | 0% | Mon 22/12/25 | Mon 22/12/25 | 0 days | Mon 22/12/25 | Mon 22/12/25 | 1594FS+140 days | 1597,1596FS+20 days | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
5 | 1.6.5.6.3 | T2-QU-0400 | QAG | BSC PAB & REC Manager approval of Qualification Testing Tranche 6 Completion | 0% | Mon 19/01/26 | Mon 19/01/26 | 0 days | Mon 19/01/26 | Mon 19/01/26 | 1595FS+20 days | 1934 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes
5 | 1.6.5.6.4 |  |  | Qualification Testing Tranche 6 Participants mobilise production environments | 0% | Tue 23/12/25 | Mon 16/02/26 | 40 days | Tue 23/12/25 | Mon 16/02/26 | 1595 |  | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
4 | 1.6.5.7 |  |  | Qualification Testing Tranche 7 | 0% | Mon 07/07/25 | Thu 12/03/26 | 178 days | Mon 07/07/25 | Mon 16/03/26 |  |  | 0 days | -2 days | -2 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.6.5.7.1 | T3-QU-0053 | QAG | Qualification Testing Tranche 7 Start | 0% | Mon 07/07/25 | Mon 07/07/25 | 0 days | Mon 07/07/25 | Mon 07/07/25 | 1594SS+20 days | 1525FS-6 mons,1544FS-6 mons,1151FF-2 mons,1600FS+140 days | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
5 | 1.6.5.7.2 | T3-QU-0060 | QAG | Qualification Testing Tranche 7 End | 0% | Mon 19/01/26 | Mon 19/01/26 | 0 days | Mon 19/01/26 | Mon 19/01/26 | 1599FS+140 days | 1602,1601FS+20 days,1190FF | 0 days | 0 days | 0 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
5 | 1.6.5.7.3 | T2-QU-0450 | QAG | BSC PAB & REC Manager approval of Qualification Testing Tranche 7 Completion | 0% | Mon 16/02/26 | Mon 16/02/26 | 0 days | Mon 16/02/26 | Mon 16/02/26 | 1600FS+20 days | 1934 | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes
5 | 1.6.5.7.4 |  |  | Qualification Testing Tranche 7 Participants mobilise production environments | 0% | Tue 20/01/26 | Thu 12/03/26 | 38 days | Tue 20/01/26 | Mon 16/03/26 | 1600 | 1934 | 0 days | -2 days | -2 days | Code Bodies | PP,SI Test |  |  | 5 | Yes
4 | 1.6.5.8 |  |  | Qualification Testing Monitoring | 0% | Tue 21/01/25 | Mon 19/01/26 | 260 days | Tue 21/01/25 | Mon 19/01/26 |  |  | 0 days | 0 days | 0 days | SI Test | PP,Code Bodies |  |  | 5 | Yes
3 | 1.6.6 |  |  | BSC PAB & REC Manager sign-off of qualified SIT participants for Migration | 0% | Mon 22/04/24 | Fri 30/05/25 | 290 days | Mon 19/02/24 | Fri 30/05/25 |  |  | 45 days | 0 days | -45 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.6.6.1 |  |  | Qualification Testing Tranche 0 | 0% | Mon 22/04/24 | Fri 30/05/25 | 290 days | Mon 19/02/24 | Fri 30/05/25 |  |  | 45 days | 0 days | -45 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.6.6.1.1 |  |  | Tranche 0 QAD completion and assurance | 0% | Mon 22/04/24 | Tue 31/12/24 | 182 days | Mon 19/02/24 | Tue 29/10/24 | 1562SS |  | 45 days | 45 days | 0 days | Code Bodies |  |  |  | 5 | Yes
5 | 1.6.6.1.2 |  |  | Qualification Testing Tranche 0 SIT MVC completion report review | 0% | Fri 07/02/25 | Fri 14/03/25 | 26 days | Mon 10/02/25 | Mon 17/03/25 | 1077 | 16111608 | -1 day | -1 day | 0 days | Code Bodies |  |  |  | 5 | Yes
5 | 1.6.6.1.3 |  |  | Qualification Testing Tranche 0 End for SIT MVC | 0% | Fri 14/03/25 | Fri 14/03/25 | 0 days | Mon 17/03/25 | Mon 17/03/25 | 1757FS+5 days,1607 | 1611 | -1 day | -1 day | 0 days | Code Bodies |  |  |  | 5 | Yes
5 | 1.6.6.1.4 |  |  | Qualification Testing Tranche 0 SIT non-MVC completion report review | 0% | Mon 21/04/25 | Fri 30/05/25 | 30 days | Mon 21/04/25 | Fri 30/05/25 | 1125 | 1610 | 0 days | 0 days | 0 days | Code Bodies |  |  |  | 5 | Yes
5 | 1.6.6.1.5 |  |  | Qualification Testing Tranche 0 End for SIT non-MVC | 0% | Fri 30/05/25 | Fri 30/05/25 | 0 days | Fri 30/05/25 | Fri 30/05/25 | 1609 |  | 0 days | 0 days | 0 days | Code Bodies |  |  |  | 5 | Yes
5 | 1.6.6.1.6 | T2-QU-0100 | QAG | BSC PAB & REC Code Manager sign-off of qualified SIT participants for Migration (post-M8 & pre-M11) | 0% | Fri 14/03/25 | Fri 14/03/25 | 0 days | Fri 14/03/25 | Fri 14/03/25 | 16081607 | 2082FS+9 days | 0 days | 0 days | 0 days | Code Bodies | PP |  |  | 5 | Yes
3 | 1.6.7 |  |  | Qualification PPs E2E Sandbox Execution | 0% | Tue 05/08/25 | Thu 31/12/26 | 368 days | Tue 05/08/25 | Thu 31/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.6.7.1 |  |  | Qualification PPs E2E Sandbox Testing Execution | 0% | Tue 05/08/25 | Thu 31/12/26 | 368 days | Tue 05/08/25 | Thu 31/12/26 | 1570 |  | 0 days | 0 days | 0 days | PP | SI Test |  |  | 5 | Yes
2 | 1.7 |  |  | REGULATORY | 80% | Mon 31/10/22 | Fri 06/06/25 | 680 days | Mon 31/10/22 | Fri 06/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  |  | Yes | N/A
3 | 1.7.1 |  |  | Baseline MHHS Code Changes | 94% | Mon 31/10/22 | Fri 23/08/24 | 475 days | Mon 31/10/22 | Fri 23/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.7.1.1 |  |  | Preparation and planning | 100% | Mon 31/10/22 | Fri 16/12/22 | 35 days | Mon 31/10/22 | Fri 16/12/22 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.7.1.1.1 |  |  | Impact assessment of Programme design on codes to determine required changes | 100% | Mon 31/10/22 | Fri 25/11/22 | 20 days | Mon 31/10/22 | Fri 25/11/22 | 48 |  | 0 days | 0 days | 0 days | Code Bodies,SRO Code Drafters | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
5 | 1.7.1.1.2 |  |  | Become 'code draft ready' | 100% | Mon 31/10/22 | Fri 16/12/22 | 35 days | Mon 31/10/22 | Fri 16/12/22 |  |  | 0 days | 0 days | 0 days | Code Bodies,SRO Code Drafters | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
5 | 1.7.1.1.3 |  |  | Soft start drafting where possible | 100% | Mon 31/10/22 | Fri 16/12/22 | 35 days | Mon 31/10/22 | Fri 16/12/22 |  |  | 0 days | 0 days | 0 days | Code Bodies,SRO Code Drafters | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
4 | 1.7.1.2 |  |  | Code drafting | 94% | Mon 12/12/22 | Fri 23/08/24 | 445 days | Mon 12/12/22 | Fri 23/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.7.1.2.1 |  |  | Data Services (BSC driven) | 100% | Mon 12/12/22 | Wed 24/05/23 | 118 days | Mon 12/12/22 | Wed 24/05/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.7.1.2.1.1 |  |  | Pre Code Drafting activities | 100% | Mon 12/12/22 | Fri 16/12/22 | 5 days | Mon 12/12/22 | Fri 16/12/22 |  | 1623FS+11 days,1631SS | 0 days | 0 days | 0 days | Code Drafting PM |  |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.1.2 |  |  | Code and subsidiary document drafting takes place offline | 100% | Tue 03/01/23 | Fri 27/01/23 | 19 days | Tue 03/01/23 | Fri 27/01/23 | 1622FS+11 days | 1624 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.1.3 |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Mon 30/01/23 | Mon 13/02/23 | 11 days | Mon 30/01/23 | Mon 13/02/23 | 1623 | 16251650 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.1.4 |  |  | External industry review via consultation | 100% | Tue 14/02/23 | Mon 13/03/23 | 20 days | Tue 14/02/23 | Mon 13/03/23 | 1624 | 1626FS-2 days,1641SS | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.1.5 |  |  | Triage and action comments | 100% | Fri 10/03/23 | Wed 05/04/23 | 19 days | Fri 10/03/23 | Wed 05/04/23 | 1625FS-2 days | 1627 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.1.6 |  |  | CDWG review | 100% | Thu 06/04/23 | Wed 17/05/23 | 30 days | Thu 06/04/23 | Wed 17/05/23 | 1626 | 1628 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.1.7 |  |  | CCAG review | 100% | Thu 18/05/23 | Wed 24/05/23 | 5 days | Thu 18/05/23 | Wed 24/05/23 | 1627 | 1629 | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.1.8 | T2-RE-0100 | CCAG | Code drafting for Data Services topic area approved | 100% | Wed 24/05/23 | Wed 24/05/23 | 0 days | Wed 24/05/23 | Wed 24/05/23 | 1628 | 1718 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
5 | 1.7.1.2.2 |  |  | Metering (REC driven) | 100% | Mon 12/12/22 | Wed 24/05/23 | 118 days | Mon 12/12/22 | Wed 24/05/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.7.1.2.2.1 |  |  | Pre Code Drafting activities | 100% | Mon 12/12/22 | Fri 16/12/22 | 5 days | Mon 12/12/22 | Fri 16/12/22 | 1622SS | 1632FS+11 days | 0 days | 0 days | 0 days | Code Drafting PM |  |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.2.2 |  |  | Code and subsidiary document drafting takes place offline | 100% | Tue 03/01/23 | Fri 27/01/23 | 19 days | Tue 03/01/23 | Fri 27/01/23 | 1631FS+11 days | 1633 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.2.3 |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Mon 30/01/23 | Mon 13/02/23 | 11 days | Mon 30/01/23 | Mon 13/02/23 | 1632 | 16341650 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.2.4 |  |  | External industry review via consultation | 100% | Tue 14/02/23 | Mon 13/03/23 | 20 days | Tue 14/02/23 | Mon 13/03/23 | 1633 | 1635FS-2 days | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.2.5 |  |  | Triage and action comments | 100% | Fri 10/03/23 | Wed 05/04/23 | 19 days | Fri 10/03/23 | Wed 05/04/23 | 1634FS-2 days | 1636 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.2.6 |  |  | CDWG review | 100% | Thu 06/04/23 | Wed 17/05/23 | 30 days | Thu 06/04/23 | Wed 17/05/23 | 1635 | 1637 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.2.7 |  |  | CCAG review | 100% | Thu 18/05/23 | Wed 24/05/23 | 5 days | Thu 18/05/23 | Wed 24/05/23 | 1636 | 1638 | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.2.8 | T2-RE-0150 | CCAG | Code drafting for Metering topic area approved | 100% | Wed 24/05/23 | Wed 24/05/23 | 0 days | Wed 24/05/23 | Wed 24/05/23 | 1637 | 1718 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
5 | 1.7.1.2.3 |  |  | BSC Central Services (BSC driven) | 100% | Wed 22/02/23 | Wed 27/09/23 | 156 days | Wed 22/02/23 | Wed 27/09/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.7.1.2.3.1 |  |  | Pre Code Drafting activities | 100% | Wed 22/02/23 | Tue 28/02/23 | 5 days | Wed 22/02/23 | Tue 28/02/23 | 1641SS-5 days |  | 0 days | 0 days | 0 days | Code Drafting PM |  |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.3.2 |  |  | Code Drafting (offline) | 100% | Wed 01/03/23 | Tue 20/06/23 | 80 days | Wed 01/03/23 | Tue 20/06/23 | 1625SS | 1642SS+10 days,1640SS-5 days | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.3.3 |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Wed 15/03/23 | Tue 20/06/23 | 70 days | Wed 15/03/23 | Tue 20/06/23 | 1641SS+10 days | 1643 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.3.4 |  |  | External industry review via consultation | 100% | Wed 21/06/23 | Tue 11/07/23 | 15 days | Wed 21/06/23 | Tue 11/07/23 | 1642 | 1644FS-2 days | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.3.5 |  |  | Triage and action comments | 100% | Mon 10/07/23 | Thu 03/08/23 | 19 days | Mon 10/07/23 | Thu 03/08/23 | 1643FS-2 days | 1645 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.3.6 |  |  | CDWG review | 100% | Fri 04/08/23 | Tue 12/09/23 | 28 days | Fri 04/08/23 | Tue 12/09/23 | 1644 | 1646 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.3.7 |  |  | CCAG review | 100% | Wed 13/09/23 | Wed 27/09/23 | 11 days | Wed 13/09/23 | Wed 27/09/23 | 1645 | 1647 | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.3.8 | T2-RE-0200 | CCAG | Code drafting for BSC Central Services topic area approved | 100% | Wed 27/09/23 | Wed 27/09/23 | 0 days | Wed 27/09/23 | Wed 27/09/23 | 1646 | 1718 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
5 | 1.7.1.2.4 |  |  | Registration (BSC & REC driven) | 100% | Wed 22/02/23 | Wed 23/08/23 | 131 days | Wed 22/02/23 | Wed 23/08/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.7.1.2.4.1 |  |  | Pre Code Drafting activities | 100% | Wed 22/02/23 | Tue 28/02/23 | 5 days | Wed 22/02/23 | Tue 28/02/23 | 1650SS-5 days |  | 0 days | 0 days | 0 days | Code Drafting PM |  |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.4.2 |  |  | Code Drafting (offline) | 100% | Wed 01/03/23 | Tue 30/05/23 | 65 days | Wed 01/03/23 | Tue 30/05/23 | 16241633 | 1651SS+10 days,1649SS-5 days | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.4.3 |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Wed 15/03/23 | Tue 30/05/23 | 55 days | Wed 15/03/23 | Tue 30/05/23 | 1650SS+10 days | 1652 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.4.4 |  |  | External industry review via consultation | 100% | Wed 31/05/23 | Tue 20/06/23 | 15 days | Wed 31/05/23 | Tue 20/06/23 | 1651 | 1653FS-2 days,1659SS+1 day,1668SS+1 day,1677SS+1 day | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.4.5 |  |  | Triage and action comments | 100% | Mon 19/06/23 | Thu 13/07/23 | 19 days | Mon 19/06/23 | Thu 13/07/23 | 1652FS-2 days | 1654 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.4.6 |  |  | CDWG review | 100% | Fri 14/07/23 | Tue 08/08/23 | 18 days | Fri 14/07/23 | Tue 08/08/23 | 1653 | 1655 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.4.7 |  |  | CCAG review | 100% | Wed 09/08/23 | Wed 23/08/23 | 11 days | Wed 09/08/23 | Wed 23/08/23 | 1654 | 1656 | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.4.8 | T2-RE-0250 | CCAG | Code drafting for Registration topic area approved | 100% | Wed 23/08/23 | Wed 23/08/23 | 0 days | Wed 23/08/23 | Wed 23/08/23 | 1655 | 1718 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
5 | 1.7.1.2.5 |  |  | Governance and Qualification (BSC & REC driven) | 100% | Thu 25/05/23 | Wed 22/11/23 | 130 days | Thu 25/05/23 | Wed 22/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.7.1.2.5.1 |  |  | Pre Code Drafting activities | 100% | Thu 25/05/23 | Wed 31/05/23 | 5 days | Thu 25/05/23 | Wed 31/05/23 | 1659SS-5 days |  | 0 days | 0 days | 0 days | Code Drafting PM |  |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.5.2 |  |  | Code Drafting (offline) | 100% | Thu 01/06/23 | Wed 16/08/23 | 55 days | Thu 01/06/23 | Wed 16/08/23 | 1652SS+1 day | 1660SS+10 days,1658SS-5 days | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.5.3 |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Thu 15/06/23 | Wed 16/08/23 | 45 days | Thu 15/06/23 | Wed 16/08/23 | 1659SS+10 days | 1661FS+1 day | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.5.4 |  |  | External industry review via consultation | 100% | Fri 18/08/23 | Thu 07/09/23 | 15 days | Fri 18/08/23 | Thu 07/09/23 | 1660FS+1 day | 1662FS-2 days | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.5.5 |  |  | Triage and action comments | 100% | Wed 06/09/23 | Mon 02/10/23 | 19 days | Wed 06/09/23 | Mon 02/10/23 | 1661FS-2 days | 1663 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.5.6 |  |  | CDWG review | 100% | Tue 03/10/23 | Tue 14/11/23 | 31 days | Tue 03/10/23 | Tue 14/11/23 | 1662 | 1664 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.5.7 |  |  | CCAG review | 100% | Wed 15/11/23 | Wed 22/11/23 | 6 days | Wed 15/11/23 | Wed 22/11/23 | 1663 | 1665 | 0 days | 0 days | 0 days | PP |  |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.5.8 | T3-RE-0300 | CCAG | Code drafting for Governance and Qualification topic areas approved | 100% | Wed 22/11/23 | Wed 22/11/23 | 0 days | Wed 22/11/23 | Wed 22/11/23 | 1664 | 1718 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5.12 | Yes | Andrew Margan
5 | 1.7.1.2.6 |  |  | Interfaces / Data Specification (REC driven) | 100% | Thu 25/05/23 | Tue 23/01/24 | 174 days | Thu 25/05/23 | Wed 24/01/24 |  |  | 0 days | -1 day | -1 day | N/A | N/A |  |  | 5.2 | Yes | N/A
6 | 1.7.1.2.6.1 |  |  | Pre Code Drafting activities | 100% | Thu 25/05/23 | Wed 31/05/23 | 5 days | Thu 25/05/23 | Wed 31/05/23 | 1668SS-5 days |  | 0 days | 0 days | 0 days | Code Drafting PM |  |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.6.2 |  |  | Code Drafting (offline) | 100% | Thu 01/06/23 | Tue 10/10/23 | 94 days | Thu 01/06/23 | Tue 10/10/23 | 1652SS+1 day | 1667SS-5 days,1669SS+10 days | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5.2 | Yes | Andrew Margan
6 | 1.7.1.2.6.3 |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Thu 15/06/23 | Tue 10/10/23 | 84 days | Thu 15/06/23 | Tue 10/10/23 | 1668SS+10 days | 1670 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5.2 | Yes | Andrew Margan
6 | 1.7.1.2.6.4 |  |  | External industry review via consultation | 100% | Wed 11/10/23 | Tue 31/10/23 | 15 days | Wed 11/10/23 | Tue 31/10/23 | 1669 | 1671FS-2 days | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5.2 | Yes | Andrew Margan
6 | 1.7.1.2.6.5 |  |  | Triage and action comments | 100% | Mon 30/10/23 | Fri 24/11/23 | 20 days | Mon 30/10/23 | Fri 24/11/23 | 1670FS-2 days | 1672 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5.2 | Yes | Andrew Margan
6 | 1.7.1.2.6.6 |  |  | CDWG review | 100% | Mon 27/11/23 | Tue 16/01/24 | 37 days | Mon 27/11/23 | Tue 09/01/24 | 1671 | 1673 | 0 days | 5 days | 5 days | PP | Code Drafting PM |  |  | 5.2 | Yes | Andrew Margan
6 | 1.7.1.2.6.7 |  |  | CCAG review | 100% | Wed 17/01/24 | Tue 23/01/24 | 5 days | Wed 10/01/24 | Wed 24/01/24 | 1672 | 1674 | 5 days | -1 day | -6 days | PP | Code Drafting PM |  |  | 5.2 | Yes | Andrew Margan
6 | 1.7.1.2.6.8 | T3-RE-0350 | CCAG | Code drafting for Interfaces / Data Specification topic areas approved | 100% | Tue 23/01/24 | Tue 23/01/24 | 0 days | Wed 24/01/24 | Wed 24/01/24 | 1673 | 1718 | -1 day | -1 day | 0 days | PP | Code Drafting PM |  |  | 5.16 | Yes | Andrew Margan
5 | 1.7.1.2.7 |  |  | Migration (BSC & REC driven) | 100% | Thu 25/05/23 | Wed 22/11/23 | 130 days | Thu 25/05/23 | Wed 22/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.7.1.2.7.1 |  |  | Pre Code Drafting activities | 100% | Thu 25/05/23 | Wed 31/05/23 | 5 days | Thu 25/05/23 | Wed 31/05/23 | 1677SS-5 days |  | 0 days | 0 days | 0 days | Code Drafting PM |  |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.7.2 |  |  | Code Drafting (offline) | 100% | Thu 01/06/23 | Wed 16/08/23 | 55 days | Thu 01/06/23 | Wed 16/08/23 | 1652SS+1 day | 1676SS-5 days,1678SS+10 days | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.7.3 |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Thu 15/06/23 | Wed 16/08/23 | 45 days | Thu 15/06/23 | Wed 16/08/23 | 1677SS+10 days | 1679FS+1 day | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.7.4 |  |  | External industry review via consultation | 100% | Fri 18/08/23 | Thu 07/09/23 | 15 days | Fri 18/08/23 | Thu 07/09/23 | 1678FS+1 day | 1680FS-2 days,1689SS | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.7.5 |  |  | Triage and action comments | 100% | Wed 06/09/23 | Mon 02/10/23 | 19 days | Wed 06/09/23 | Mon 02/10/23 | 1679FS-2 days | 1681 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.7.6 |  |  | CDWG review | 100% | Tue 03/10/23 | Tue 14/11/23 | 31 days | Tue 03/10/23 | Tue 14/11/23 | 1680 | 1682 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.7.7 |  |  | CCAG review | 100% | Wed 15/11/23 | Wed 22/11/23 | 6 days | Wed 15/11/23 | Wed 22/11/23 | 1681 | 1683 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.7.8 | T3-RE-0400 | CCAG | Code drafting for Migration topic area approved | 100% | Wed 22/11/23 | Wed 22/11/23 | 0 days | Wed 22/11/23 | Wed 22/11/23 | 1682 | 1718 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5.12 | Yes | Andrew Margan
5 | 1.7.1.2.8 |  |  | Consequential Code Change | 99% | Wed 11/10/23 | Mon 11/03/24 | 109 days | Wed 11/10/23 | Fri 08/03/24 |  |  | 0 days | 1 day | 1 day | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.7.1.2.8.1 |  |  | External industry review via consultation - drop 1 (DCUSA) | 100% | Wed 11/10/23 | Tue 31/10/23 | 15 days | Wed 11/10/23 | Tue 31/10/23 | 1691SS |  | 0 days | 0 days | 0 days | Code Bodies | PP |  |  | 5.2 | Yes | Andrew Margan
6 | 1.7.1.2.8.2 |  |  | External industry review via consultation - drop 2 (Elexon) | 100% | Mon 19/02/24 | Mon 11/03/24 | 16 days | Mon 19/02/24 | Fri 08/03/24 | 1701SS |  | 0 days | 1 day | 1 day | Code Bodies | PP |  |  | 5.2 | Yes | Andrew Margan
5 | 1.7.1.2.9 |  |  | Transition Text (all codes) | 100% | Fri 11/08/23 | Tue 23/01/24 | 118 days | Fri 11/08/23 | Wed 24/01/24 |  |  | 0 days | -1 day | -1 day | N/A | N/A |  |  | 5.2 | Yes | N/A
6 | 1.7.1.2.9.1 |  |  | Pre Code Drafting activities | 100% | Fri 11/08/23 | Tue 22/08/23 | 8 days | Fri 11/08/23 | Tue 22/08/23 | 1689SS-5 days |  | 0 days | 0 days | 0 days | Code Drafting PM |  |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.9.2 |  |  | Code Drafting (offline) | 100% | Fri 18/08/23 | Tue 10/10/23 | 38 days | Fri 18/08/23 | Tue 10/10/23 | 1679SS | 1690SS+10 days,1688SS-5 days,1697SS | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5.2 | Yes | Andrew Margan
6 | 1.7.1.2.9.3 |  |  | Internal review and cross-checking of drafting across code drafters | 100% | Fri 01/09/23 | Tue 10/10/23 | 28 days | Fri 01/09/23 | Tue 10/10/23 | 1689SS+10 days | 1691 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5.2 | Yes | Andrew Margan
6 | 1.7.1.2.9.4 |  |  | External industry review via consultation | 100% | Wed 11/10/23 | Tue 31/10/23 | 15 days | Wed 11/10/23 | Tue 31/10/23 | 1690 | 1692FS-2 days,1685SS | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5.2 | Yes | Andrew Margan
6 | 1.7.1.2.9.5 |  |  | Triage and action comments | 100% | Mon 30/10/23 | Fri 24/11/23 | 20 days | Mon 30/10/23 | Fri 24/11/23 | 1691FS-2 days | 1693 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5.2 | Yes | Andrew Margan
6 | 1.7.1.2.9.6 |  |  | CDWG review | 100% | Mon 27/11/23 | Tue 16/01/24 | 37 days | Mon 27/11/23 | Tue 16/01/24 | 1692 | 1694 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5.2 | Yes | Andrew Margan
6 | 1.7.1.2.9.7 |  |  | CCAG review | 100% | Wed 17/01/24 | Tue 23/01/24 | 5 days | Wed 17/01/24 | Wed 24/01/24 | 1693 | 1695 | 0 days | -1 day | -1 day | PP | Code Drafting PM |  |  | 5.2 | Yes | Andrew Margan
6 | 1.7.1.2.9.8 | T3-RE-0450 | CCAG | Code drafting for Transition Text topic area approved | 100% | Tue 23/01/24 | Tue 23/01/24 | 0 days | Wed 24/01/24 | Wed 24/01/24 | 1694 | 1718 | -1 day | -1 day | 0 days | PP | Code Drafting PM |  |  | 5.16 | Yes | Andrew Margan
5 | 1.7.1.2.10 |  |  | Final Code Drafting (mop-up) (all codes) | 92% | Fri 18/08/23 | Wed 22/05/24 | 199 days | Fri 18/08/23 | Wed 22/05/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.7.1.2.10.1 |  |  | Forward look and confirm remaining plan | 100% | Fri 18/08/23 | Thu 07/09/23 | 15 days | Fri 18/08/23 | Thu 07/09/23 | 1689SS | 1698SS | 0 days | 0 days | 0 days | Code Drafting PM |  |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.10.2 |  |  | Identify remaining or additional areas of code (e.g. consequential change requirements) to be completed | 100% | Fri 18/08/23 | Thu 07/09/23 | 15 days | Fri 18/08/23 | Thu 07/09/23 | 1697SS | 1699 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.10.3 |  |  | Code Drafting (offline) Interim Consultation (1) | 100% | Fri 08/09/23 | Thu 30/11/23 | 60 days | Fri 08/09/23 | Thu 30/11/23 | 1698 | 1700SS+10 days,1761SS | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.10.4 |  |  | Internal review and cross-checking of drafting across code drafters Interim Consultation (1) | 100% | Fri 22/09/23 | Thu 30/11/23 | 50 days | Fri 22/09/23 | Thu 30/11/23 | 1699SS+10 days | 17011702 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.10.5 |  |  | External industry review via consultation Interim Consultation (1) | 100% | Fri 01/12/23 | Tue 02/01/24 | 23 days | Fri 01/12/23 | Tue 02/01/24 | 1700 | 1559SS,1562SS,1563SS,1686SS | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.10.6 |  |  | Code Drafting (offline) Final Consultation (2) | 100% | Fri 01/12/23 | Thu 15/02/24 | 55 days | Fri 01/12/23 | Thu 15/02/24 | 1700 | 1703SS+10 days,1761SS | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.10.7 |  |  | Internal review and cross-checking of drafting across code drafters Final Consultation (2) | 100% | Fri 15/12/23 | Thu 15/02/24 | 45 days | Fri 15/12/23 | Thu 15/02/24 | 1702SS+10 days | 1704FS+1 day | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.10.8 |  |  | External industry review via consultation Final Consultation (2) | 100% | Mon 19/02/24 | Mon 11/03/24 | 16 days | Mon 19/02/24 | Fri 08/03/24 | 1703FS+1 day | 1705FS-1 day,1559SS,1562SS,1563SS | 0 days | 1 day | 1 day | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.10.9 |  |  | Triage and action comments | 100% | Mon 11/03/24 | Wed 03/04/24 | 18 days | Thu 07/03/24 | Mon 01/04/24 | 1704FS-1 day | 1706 | 2 days | 2 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.10.10 |  |  | CDWG review | 34% | Thu 04/04/24 | Tue 14/05/24 | 29 days | Tue 02/04/24 | Tue 14/05/24 | 1705 | 1710SS,1707 | 2 days | 0 days | -2 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.10.11 |  |  | CCAG review | 0% | Wed 15/05/24 | Wed 22/05/24 | 6 days | Wed 15/05/24 | Wed 22/05/24 | 1706 | 1708 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.10.12 | T3-RE-0500 | CCAG | Final code drafting (mop-up) approved | 0% | Wed 22/05/24 | Wed 22/05/24 | 0 days | Wed 22/05/24 | Wed 22/05/24 | 1707 | 1718 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5.9 | Yes | Andrew Margan
5 | 1.7.1.2.11 |  |  | Final code review, consistency check and approval | 10% | Thu 04/04/24 | Fri 23/08/24 | 102 days | Thu 04/04/24 | Fri 23/08/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.7.1.2.11.1 |  |  | Gap analysis of final code against design artefacts (reverse process to code drafting) | 26% | Thu 04/04/24 | Mon 27/05/24 | 38 days | Thu 04/04/24 | Mon 27/05/24 | 1706SS | 1711 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.11.2 |  |  | Outputs of gap analysis actioned offline | 0% | Tue 28/05/24 | Tue 11/06/24 | 11 days | Tue 28/05/24 | Tue 11/06/24 | 1710 | 1712 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.11.3 |  |  | Final documentation collated for final consultation | 0% | Wed 12/06/24 | Fri 21/06/24 | 8 days | Mon 10/06/24 | Fri 21/06/24 | 1711 | 1713 | 2 days | 0 days | -2 days | Code Drafting PM | Code Bodies,SRO Design |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.11.4 |  |  | External industry review via consultation | 0% | Mon 24/06/24 | Fri 19/07/24 | 20 days | Mon 24/06/24 | Fri 19/07/24 | 1712 | 1714FS-2 days,1722SS | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.11.5 |  |  | Triage and action comments | 0% | Thu 18/07/24 | Mon 05/08/24 | 13 days | Thu 18/07/24 | Mon 05/08/24 | 1713FS-2 days | 1715 | 0 days | 0 days | 0 days | Code Bodies,SRO Design | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.11.6 |  |  | Final CDWG review | 0% | Tue 06/08/24 | Tue 13/08/24 | 6 days | Tue 06/08/24 | Tue 13/08/24 | 1714 | 1716 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.11.7 |  |  | Final CCAG review | 0% | Wed 14/08/24 | Fri 23/08/24 | 8 days | Wed 14/08/24 | Fri 23/08/24 | 1715 | 17181717 | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5 | Yes | Andrew Margan
6 | 1.7.1.2.11.8 | T3-RE-0550 | CCAG | CCAG recommend final code to PSG for baselining | 0% | Fri 23/08/24 | Fri 23/08/24 | 0 days | Fri 23/08/24 | Fri 23/08/24 | 1716 |  | 0 days | 0 days | 0 days | PP | Code Drafting PM |  |  | 5.9 | Yes | Andrew Margan
4 | 1.7.1.3 | T1-RE-1000 | PSG | Code changes baselined (M6) | 0% | Fri 23/08/24 | Fri 23/08/24 | 0 days | Fri 23/08/24 | Fri 23/08/24 | 1.7162e+39 | 172617391757 | 0 days | 0 days | 0 days | CPT | PP |  |  | 5 | Yes | Andrew Margan
3 | 1.7.2 |  |  | Ofgem preparation and enactment of SCR powers | 17% | Mon 05/02/24 | Tue 12/11/24 | 201 days | Mon 05/02/24 | Tue 12/11/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.7.2.1 |  |  | Preparation and enactment of SCR Powers | 25% | Mon 05/02/24 | Mon 11/11/24 | 201 days | Mon 05/02/24 | Mon 11/11/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.7.2.1.1 |  |  | Ofgem to keep Ofgem legal informed of process followed and nature of Code drafting to ensure that prepared for SCR go/no go decision | 53% | Mon 05/02/24 | Mon 24/06/24 | 100 days | Mon 05/02/24 | Mon 24/06/24 | 1722SF |  | 0 days | 0 days | 0 days | Ofgem | Code Bodies |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.2 |  |  | OFGEM Legal to review Code Artefacts deliver policy intent and process followed and confirm that SCR powers are appropriate to use rather than SMAP - SCR go/no go | 0% | Mon 24/06/24 | Fri 12/07/24 | 15 days | Mon 24/06/24 | Fri 12/07/24 | 1713SS | 1721SF,1723,1724,1741SS | 0 days | 0 days | 0 days | Ofgem | Code Bodies |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.3 |  |  | Code Bodies to draft MOD proposal forms | 0% | Mon 15/07/24 | Fri 09/08/24 | 20 days | Mon 15/07/24 | Fri 09/08/24 | 1722 |  | 0 days | 0 days | 0 days | Code Bodies | Ofgem |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.4 |  |  | Ofgem discuss and agree code mod timetable with code bodies (and MHHSP in relation to the dates for expected decisions) | 0% | Mon 15/07/24 | Fri 09/08/24 | 20 days | Mon 15/07/24 | Fri 09/08/24 | 1722 | 1725 | 0 days | 0 days | 0 days | Ofgem | Code Bodies |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.5 |  |  | Ofgem to draft open letter and direction to each code body specifying the timetable for each modification | 0% | Mon 12/08/24 | Fri 16/08/24 | 5 days | Mon 12/08/24 | Fri 16/08/24 | 1724 |  | 0 days | 0 days | 0 days | Ofgem | Code Bodies |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.6 |  |  | Ofgem to publish open letter | 0% | Mon 26/08/24 | Mon 26/08/24 | 1 day | Mon 26/08/24 | Mon 26/08/24 | 1718 | 1727FS+1 day,1728FS+1 day | 0 days | 0 days | 0 days | Ofgem | Code Bodies |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.7 |  |  | Ofgem to publish each Direction to each code body specifying the timetable for each modification | 0% | Wed 28/08/24 | Wed 28/08/24 | 1 day | Wed 28/08/24 | Wed 28/08/24 | 1726FS+1 day |  | 0 days | 0 days | 0 days | Ofgem | Code Bodies |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.8 |  |  | Formally submit (by separate email) Modification Proposal Forms and legal texts to each code body | 0% | Wed 28/08/24 | Wed 28/08/24 | 1 day | Wed 28/08/24 | Wed 28/08/24 | 1726FS+1 day | 1729 | 0 days | 0 days | 0 days | Ofgem | Code Bodies |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.9 |  |  | Each Code Body publishes and issues Modification Proposal Forms | 0% | Thu 29/08/24 | Mon 02/09/24 | 3 days | Thu 29/08/24 | Mon 02/09/24 | 1728 | 1730 | 0 days | 0 days | 0 days | Code Bodies | Ofgem |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.10 |  |  | Each Code Body sends Modification Proposal Forms to Panel to approve Mod to go to consultation | 0% | Tue 03/09/24 | Mon 16/09/24 | 10 days | Tue 03/09/24 | Mon 16/09/24 | 1729 | 1731 | 0 days | 0 days | 0 days | Code Bodies | Ofgem |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.11 |  |  | Modification Proposal approved by Panel for Consultation | 0% | Tue 17/09/24 | Tue 17/09/24 | 1 day | Tue 17/09/24 | Tue 17/09/24 | 1730 | 1732 | 0 days | 0 days | 0 days | Code Bodies | Ofgem |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.12 |  |  | Draft Modification Report issued for consultation | 0% | Wed 18/09/24 | Wed 18/09/24 | 1 day | Wed 18/09/24 | Wed 18/09/24 | 1731 | 1733 | 0 days | 0 days | 0 days | Code Bodies | Ofgem |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.13 |  |  | Consultation Close-out for representations | 0% | Thu 19/09/24 | Wed 09/10/24 | 15 days | Thu 19/09/24 | Wed 09/10/24 | 1732 | 1734 | 0 days | 0 days | 0 days | Code Bodies | Ofgem |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.14 |  |  | Each Code Body reviews consultation response and drafts Modification Report | 0% | Thu 10/10/24 | Wed 23/10/24 | 10 days | Thu 10/10/24 | Wed 23/10/24 | 1733 | 1735 | 0 days | 0 days | 0 days | Code Bodies | Ofgem |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.15 |  |  | Final Modification Report sent to Panel for decision with recommendation to approve | 0% | Thu 24/10/24 | Thu 24/10/24 | 1 day | Thu 24/10/24 | Thu 24/10/24 | 1734 | 1736FS+9 days | 0 days | 0 days | 0 days | Code Bodies | Ofgem |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.16 |  |  | Modification Panel decision | 0% | Thu 07/11/24 | Thu 07/11/24 | 1 day | Thu 07/11/24 | Thu 07/11/24 | 1735FS+9 days | 17371738 | 0 days | 0 days | 0 days | Code Bodies | Ofgem |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.17 |  |  | Panel make recommendation to OFGEM | 0% | Fri 08/11/24 | Mon 11/11/24 | 2 days | Fri 08/11/24 | Mon 11/11/24 | 1736 |  | 0 days | 0 days | 0 days | Code Bodies | Ofgem |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.1.18 |  |  | MTDSG | 0% | Fri 08/11/24 | Mon 11/11/24 | 2 days | Fri 08/11/24 | Mon 11/11/24 | 1736 | 1739FF | 0 days | 0 days | 0 days | Ofgem | Code Bodies |  |  | 5 | Yes | Andrew Margan
4 | 1.7.2.2 | T2-RE-0600 | CCAG | SCR powers enabled (M7) | 0% | Mon 11/11/24 | Mon 11/11/24 | 0 days | Mon 11/11/24 | Mon 11/11/24 | 1738FF,1718 | 17531757 | 0 days | 0 days | 0 days | CPT | PP |  |  | 5 | Yes | Andrew Margan
4 | 1.7.2.3 |  |  | Ofgem preparation to enact Smart Meter Act powers [CONTINGENCY ONLY] | 0% | Mon 24/06/24 | Tue 12/11/24 | 101 days | Mon 24/06/24 | Tue 12/11/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.7.2.3.1 |  |  | SRO recommends Ofgem begin preparation to enact Smart Meter Act powers [CONTINGENCY ONLY] | 0% | Mon 24/06/24 | Mon 24/06/24 | 1 day | Mon 24/06/24 | Mon 24/06/24 | 1722SS | 1742 | 0 days | 0 days | 0 days | Ofgem | Code bodies |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.3.2 |  |  | Ofgem drafts letter to DESNZ to request trigger of Smart Meter Act powers [CONTINGENCY ONLY] | 0% | Tue 25/06/24 | Mon 15/07/24 | 15 days | Tue 25/06/24 | Mon 15/07/24 | 1741 | 1743 | 0 days | 0 days | 0 days | Ofgem | Code bodies |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.3.3 |  |  | DESNZ SoS letter response to trigger SMAP Powers [CONTINGENCY ONLY] | 0% | Tue 16/07/24 | Mon 12/08/24 | 1 mon | Tue 16/07/24 | Mon 12/08/24 | 1742 |  | 0 days | 0 days | 0 mons | Ofgem | Code bodies |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.3.4 |  |  | Ofgem enables Smart Meters Act powers (support from the Programme, where required) [CONTINGENCY ONLY] | 0% | Mon 05/08/24 | Tue 06/08/24 | 1 day | Mon 05/08/24 | Tue 06/08/24 | 1748SF | 1745 | 0 days | 0 days | 0 days | Tier 2 - M7 |  |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.3.5 |  |  | Smart Meters Act powers enabled (M7) [CONTINGENCY ONLY] | 0% | Tue 06/08/24 | Tue 06/08/24 | 0 days | Tue 06/08/24 | Tue 06/08/24 | 1744 |  | 0 days | 0 days | 0 days | Ofgem | Code bodies |  |  | 5 | Yes | Andrew Margan
5 | 1.7.2.3.6 |  |  | Deliver MHHS Code Changes [CONTINGENCY UNDER SMAP] | 0% | Tue 06/08/24 | Tue 12/11/24 | 70 days | Tue 06/08/24 | Tue 12/11/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.7.2.3.6.1 |  |  | Ofgem consultation and decision [CONTINGENCY ONLY] | 0% | Tue 06/08/24 | Tue 12/11/24 | 70 days | Tue 06/08/24 | Tue 12/11/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
7 | 1.7.2.3.6.1.1 |  |  | Ofgem issue completed code to industry for consultation under SMAP (consultation confirms robustness of the process undertaken via CCAG and does not re-open the detail of drafted code) [CONTINGENCY ONLY] | 0% | Tue 06/08/24 | Tue 20/08/24 | 10 days | Tue 06/08/24 | Tue 20/08/24 | 1749SF | 1744SF | 0 days | 0 days | 0 days | Ofgem | Code bodies |  |  | 5 | Yes | Andrew Margan
7 | 1.7.2.3.6.1.2 |  |  | Industry respond to consultation on new Code (28-day consultation) [CONTINGENCY ONLY] | 0% | Tue 20/08/24 | Tue 17/09/24 | 20 days | Tue 20/08/24 | Tue 17/09/24 | 1750SF | 1748SF | 0 days | 0 days | 0 days | PP | Ofgem |  |  | 5 | Yes | Andrew Margan
7 | 1.7.2.3.6.1.3 |  |  | Ofgem considers consultation responses and publishes decision confirming Code Releases dates (release dates may be <56 days following publication of Ofgem decision) [CONTINGENCY ONLY] | 0% | Tue 17/09/24 | Tue 12/11/24 | 40 days | Tue 17/09/24 | Tue 12/11/24 | 1753SF | 1749SF | 0 days | 0 days | 0 days | Ofgem | Code bodies |  |  | 5 | Yes | Andrew Margan
3 | 1.7.3 |  |  | Deliver MHHS Code Changes | 0% | Tue 12/11/24 | Fri 06/06/25 | 149 days | Tue 12/11/24 | Fri 06/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.7.3.1 |  |  | Releases | 0% | Tue 12/11/24 | Fri 06/06/25 | 149 days | Tue 12/11/24 | Fri 06/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.7.3.1.1 |  |  | Impacted codes make resourcing provisions and prepare to implement new Code via internal code body change processes | 0% | Tue 12/11/24 | Thu 27/02/25 | 78 days | Tue 12/11/24 | Thu 27/02/25 | 1739 | 1750SF | 0 days | 0 days | 0 days | Code Bodies |  |  |  | 5 | Yes | Andrew Margan
5 | 1.7.3.1.2 |  |  | Main Code Release | 0% | Fri 28/02/25 | Fri 06/06/25 | 71 days | Fri 28/02/25 | Fri 06/06/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.7.3.1.2.1 |  |  | Release preparation (e.g. preparing release documentation) | 0% | Fri 28/02/25 | Fri 07/03/25 | 5 days | Fri 28/02/25 | Fri 07/03/25 | 1756SF |  | 0 days | 0 days | 0 days | Code Bodies |  |  |  | 5 | Yes | Andrew Margan
6 | 1.7.3.1.2.2 |  |  | Implement new code on day of code release | 0% | Fri 07/03/25 | Fri 07/03/25 | 1 day | Fri 07/03/25 | Fri 07/03/25 | 1757SF | 1755SF | 0 days | 0 days | 0 days | Code Bodies |  |  |  | 5 | Yes | Andrew Margan
6 | 1.7.3.1.2.3 | T2-RE-0650 | CCAG | Code changes delivered (M8) | 0% | Fri 07/03/25 | Fri 07/03/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 1926SS,1739,1718 | 1956FS-40 days,1756SF,1608FS+5 days,1758FS+65 days | 0 days | 0 days | 0 days | CPT | Code Bodies,PP |  |  | 5 | Yes | Andrew Margan
6 | 1.7.3.1.2.4 | T2-RE-0700 | CCAG | Code changes delivered (M8*) late exit | 0% | Fri 06/06/25 | Fri 06/06/25 | 0 days | Fri 06/06/25 | Fri 06/06/25 | 1757FS+65 days |  | 0 days | 0 days | 0 days | CPT | Code Bodies,PP |  |  | 5.1 | Yes | Andrew Margan
3 | 1.7.4 |  |  | External Programme Dependency Management | 100% | Fri 01/12/23 | Wed 24/01/24 | 38 days | Fri 01/12/23 | Wed 24/01/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.7.4.1 |  |  | DCP397 | 100% | Fri 01/12/23 | Wed 24/01/24 | 38 days | Fri 01/12/23 | Wed 24/01/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.7.4.1.1 |  |  | Ensure DCP397 drafting included in mop-up code drafting activity (link to mop-up) | 100% | Fri 01/12/23 | Thu 28/12/23 | 20 days | Fri 01/12/23 | Thu 28/12/23 | 1702SS,1699SS |  | 0 days | 0 days | 0 days | CPT | Code Bodies,SRO Design, Code Drafting PM |  |  | 5 | Yes | Andrew Margan
5 | 1.7.4.1.2 |  |  | Implementation of DCP397 | 100% | Wed 24/01/24 | Wed 24/01/24 | 0 days | Wed 24/01/24 | Wed 24/01/24 |  |  | 0 days | 0 days | 0 days | Code Bodies |  |  |  | 5 | Yes | Andrew Margan
2 | 1.8 |  |  | MIGRATION | 31% | Mon 31/10/22 | Tue 05/01/27 | 1092 days | Mon 31/10/22 | Tue 05/01/27 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  |  | Yes | N/A
3 | 1.8.1 |  |  | Migration Artefact Development and Publication | 74% | Mon 31/10/22 | Fri 04/04/25 | 635 days | Mon 31/10/22 | Fri 04/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.8.1.1 |  |  | Migration Approach | 100% | Mon 31/10/22 | Wed 07/12/22 | 28 days | Mon 31/10/22 | Wed 07/12/22 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.8.1.1.1 |  |  | Option analysis (via MWG and PPIR) and recommendation | 100% | Mon 31/10/22 | Wed 30/11/22 | 23 days | Mon 31/10/22 | Wed 30/11/22 |  | 1767FS+5 days | 0 days | 0 days | 0 days | PP | SI Migration |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.1.1.2 | T3-MI-0010 | PSG | Migration Approach approved | 100% | Wed 07/12/22 | Wed 07/12/22 | 0 days | Wed 07/12/22 | Wed 07/12/22 | 1766FS+5 days | 1804 | 0 days | 0 days | 0 days | SI Migration | PP,IPA |  |  | 5 | Yes | John Wiggins,Matthew Breen
4 | 1.8.1.2 |  |  | Migration Design | 100% | Mon 14/11/22 | Fri 31/03/23 | 100 days | Mon 14/11/22 | Fri 31/03/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.8.1.2.1 |  |  | Review and update existing design artefacts and socialise with participants ahead of MDSG | 100% | Mon 14/11/22 | Fri 25/11/22 | 10 days | Mon 14/11/22 | Fri 25/11/22 |  | 1770FS+2 days | 0 days | 0 days | 0 days | SI Migration | SRO Design,CPT |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.1.2.2 |  |  | Develop design artefacts and supporting technical documents in line with MDSG | 100% | Wed 30/11/22 | Fri 10/02/23 | 53 days | Wed 30/11/22 | Fri 10/02/23 | 1769FS+2 days | 1771FS+1 day | 0 days | 0 days | 0 days | SI Migration | PP,SRO Function,CPT |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.1.2.3 | T3-MI-0011 | DAG | Migration design artefacts issued for consultation | 100% | Mon 13/02/23 | Mon 13/02/23 | 0 days | Mon 13/02/23 | Mon 13/02/23 | 1770FS+1 day | 1772SS | 0 days | 0 days | 0 days | SI Migration | PP,SRO Function,CPT |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.1.2.4 |  |  | Industry consultation | 100% | Tue 14/02/23 | Mon 20/02/23 | 5 days | Tue 14/02/23 | Mon 20/02/23 | 1771SS | 1773 | 0 days | 0 days | 0 days | PP | SI Migration |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.1.2.5 |  |  | Review consultation feedback, address comments and update artefacts | 100% | Tue 21/02/23 | Mon 27/02/23 | 5 days | Tue 21/02/23 | Mon 27/02/23 | 1772 | 1774 | 0 days | 0 days | 0 days | SI Migration | PP |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.1.2.6 |  |  | Internal artefact review and comms preparation | 100% | Tue 28/02/23 | Thu 02/03/23 | 3 days | Tue 28/02/23 | Thu 02/03/23 | 1773 | 1775FS+1 day | 0 days | 0 days | 0 days | SI Migration | SRO Function |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.1.2.7 | T3-MI-0013 | DAG | Updated Migration Design artefacts issued to PPs for assurance review | 100% | Fri 03/03/23 | Fri 03/03/23 | 0 days | Fri 03/03/23 | Fri 03/03/23 | 1774FS+1 day | 1776FS+13 days | 0 days | 0 days | 0 days | SI Migration | PP |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.1.2.8 |  |  | Final Migration Design artefacts walkthrough with PPs | 100% | Wed 22/03/23 | Wed 22/03/23 | 0 days | Wed 22/03/23 | Wed 22/03/23 | 1775FS+13 days | 1777FS+7 days | 0 days | 0 days | 0 days | SI Migration | PP |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.1.2.9 | T2-MI-0050 | DAG | Migration Design approved | 100% | Fri 31/03/23 | Fri 31/03/23 | 0 days | Fri 31/03/23 | Fri 31/03/23 | 1776FS+7 days | 865 | 0 days | 0 days | 0 days | SI Migration | PP,SRO Function,CPT |  |  | 5 | Yes | John Wiggins,Matthew Breen
4 | 1.8.1.3 |  |  | Transition Design | 100% | Wed 01/03/23 | Wed 15/11/23 | 186 days | Wed 01/03/23 | Wed 15/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.8.1.3.1 |  |  | Tranche 1 | 100% | Wed 01/03/23 | Wed 17/05/23 | 56 days | Wed 01/03/23 | Wed 17/05/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.8.1.3.1.1 |  |  | Develop design artefacts and supporting technical details with participants | 100% | Wed 01/03/23 | Tue 09/05/23 | 50 days | Wed 01/03/23 | Tue 09/05/23 |  | 1781 | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Andrew Margan
6 | 1.8.1.3.1.2 |  |  | Issue Material for DAG approval | 100% | Wed 10/05/23 | Wed 10/05/23 | 1 day | Wed 10/05/23 | Wed 10/05/23 | 1780 | 1782FS+5 days | 0 days | 0 days | 0 days | PP | SI Design |  |  | 5 | Yes | Andrew Margan
6 | 1.8.1.3.1.3 | T2-DB-0150 | DAG | Tranche 1 Transition Design approved | 100% | Wed 17/05/23 | Wed 17/05/23 | 0 days | Wed 17/05/23 | Wed 17/05/23 | 1781FS+5 days | 1784 | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Andrew Margan
5 | 1.8.1.3.2 |  |  | Tranche 2 | 100% | Thu 18/05/23 | Wed 15/11/23 | 130 days | Thu 18/05/23 | Wed 15/11/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.8.1.3.2.1 |  |  | Develop Initial design artefacts and supporting technical details | 100% | Thu 18/05/23 | Thu 31/08/23 | 76 days | Thu 18/05/23 | Thu 31/08/23 | 1782 | 1785 | 0 days | 0 days | 0 days | SRO | PP, CPT, SRO Design |  |  | 5.5 | Yes | Andrew Margan
6 | 1.8.1.3.2.2 |  |  | Communicate Initial Design Artefacts with Industry (MTDSG) | 100% | Fri 01/09/23 | Fri 01/09/23 | 1 day | Fri 01/09/23 | Fri 01/09/23 | 1784 | 1786FS+5 days | 0 days | 0 days | 0 days | SRO | PP, CPT, SRO Design |  |  | 5.5 | Yes | Andrew Margan
6 | 1.8.1.3.2.3 |  |  | Host MTDSG | 100% | Mon 11/09/23 | Mon 11/09/23 | 1 day | Mon 11/09/23 | Mon 11/09/23 | 1785FS+5 days | 1787 | 0 days | 0 days | 0 days | SRO | PP, CPT, SRO Design |  |  | 5.5 | Yes | Andrew Margan
6 | 1.8.1.3.2.4 |  |  | Process MTDSG Feedback and Amend Design Artefacts | 100% | Tue 12/09/23 | Fri 15/09/23 | 4 days | Tue 12/09/23 | Fri 15/09/23 | 1786 | 1788FF | 0 days | 0 days | 0 days | SRO | PP, CPT, SRO Design |  |  | 5.5 | Yes | Andrew Margan
6 | 1.8.1.3.2.5 |  |  | Communicate Amended Design Artefacts with Industry | 100% | Fri 15/09/23 | Fri 15/09/23 | 1 day | Fri 15/09/23 | Fri 15/09/23 | 1787FF | 1789FS+6 days | 0 days | 0 days | 0 days | SRO | PP, CPT, SRO Design |  |  | 5.5 | Yes | Andrew Margan
6 | 1.8.1.3.2.6 |  |  | Host MTDSG | 100% | Tue 26/09/23 | Tue 26/09/23 | 1 day | Tue 26/09/23 | Tue 26/09/23 | 1788FS+6 days | 1790 | 0 days | 0 days | 0 days | SRO | PP, CPT, SRO Design |  |  | 5.5 | Yes | Andrew Margan
6 | 1.8.1.3.2.7 |  |  | Make Final Amendments to Design Artefact | 100% | Wed 27/09/23 | Tue 03/10/23 | 5 days | Wed 27/09/23 | Tue 03/10/23 | 1789 | 1791 | 0 days | 0 days | 0 days | SRO | PP, CPT, SRO Design |  |  | 5.5 | Yes | Andrew Margan
6 | 1.8.1.3.2.8 |  |  | Request DAG Consultation | 100% | Wed 04/10/23 | Wed 04/10/23 | 1 day | Wed 04/10/23 | Wed 04/10/23 | 1790 | 1792SS | 0 days | 0 days | 0 days | SRO | PP, CPT, SRO Design |  |  | 5.5 | Yes | Andrew Margan
6 | 1.8.1.3.2.9 |  |  | Consultation Period | 100% | Wed 04/10/23 | Wed 18/10/23 | 11 days | Wed 04/10/23 | Wed 18/10/23 | 1791SS | 1793 | 0 days | 0 days | 0 days | SRO | PP, CPT, SRO Design |  |  | 5.5 | Yes | Andrew Margan
6 | 1.8.1.3.2.10 |  |  | Action Consultation Comments | 100% | Thu 19/10/23 | Wed 25/10/23 | 5 days | Thu 19/10/23 | Wed 25/10/23 | 1792 | 1794 | 0 days | 0 days | 0 days | SRO | PP, CPT, SRO Design |  |  | 5.5 | Yes | Andrew Margan
6 | 1.8.1.3.2.11 |  |  | Post Consultation Industry Assurance | 100% | Thu 26/10/23 | Wed 01/11/23 | 5 days | Thu 26/10/23 | Wed 01/11/23 | 1793 | 1795FF | 0 days | 0 days | 0 days | SRO | PP, CPT, SRO Design |  |  | 5.5 | Yes | Andrew Margan
6 | 1.8.1.3.2.12 |  |  | Request DAG Approval | 100% | Wed 01/11/23 | Wed 01/11/23 | 1 day | Wed 01/11/23 | Wed 01/11/23 | 1794FF | 1796FS+4 days | 0 days | 0 days | 0 days | SRO | PP, CPT, SRO Design |  |  | 5.5 | Yes | Andrew Margan
6 | 1.8.1.3.2.13 |  |  | DAG Transition Design Approved | 100% | Wed 08/11/23 | Wed 08/11/23 | 1 day | Wed 08/11/23 | Wed 08/11/23 | 1795FS+4 days | 1797 | 0 days | 0 days | 0 days | SRO | PP, CPT, SRO Design |  |  | 5.5 | Yes | Andrew Margan
6 | 1.8.1.3.2.14 |  |  | Update Transition Design Admin | 100% | Thu 09/11/23 | Wed 15/11/23 | 5 days | Thu 09/11/23 | Wed 15/11/23 | 1796 | 1798 | 0 days | 0 days | 0 days | SRO | PP, CPT, SRO Design |  |  | 5.5 | Yes | Andrew Margan
6 | 1.8.1.3.2.15 | T2-DB-0250 | DAG | Tranche 2 Transition Design Baselined | 100% | Wed 15/11/23 | Wed 15/11/23 | 0 days | Wed 15/11/23 | Wed 15/11/23 | 1797 |  | 0 days | 0 days | 0 days | SRO | PP, CPT, SRO Design |  |  | 5.12 | Yes | Andrew Margan
4 | 1.8.1.4 |  |  | Data Assessment Report | 100% | Tue 06/12/22 | Tue 28/02/23 | 61 days | Tue 06/12/22 | Tue 28/02/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.8.1.4.1 |  |  | Develop document with MWG | 100% | Tue 06/12/22 | Fri 10/02/23 | 49 days | Tue 06/12/22 | Fri 10/02/23 |  | 1801FS-18 days | 0 days | 0 days | 0 days | SI Migration |  |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.1.4.2 |  |  | Artefact review (via TMAG) and updates | 100% | Wed 18/01/23 | Tue 21/02/23 | 25 days | Wed 18/01/23 | Tue 21/02/23 | 1800FS-18 days | 1802FS+5 days | 0 days | 0 days | 0 days | PP | IPA,SI Migration |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.1.4.3 | T3-MI-0012 | MCAG | Data Assessment Report approved | 100% | Tue 28/02/23 | Tue 28/02/23 | 0 days | Tue 28/02/23 | Tue 28/02/23 | 1801FS+5 days |  | 0 days | 0 days | 0 days | SI Migration | PP,IPA |  |  | 5 | Yes | John Wiggins,Matthew Breen
4 | 1.8.1.5 |  |  | Migration, Cutover & Data Strategy (incl. Migration Entry Criteria) | 100% | Thu 08/12/22 | Fri 28/04/23 | 102 days | Thu 08/12/22 | Fri 28/04/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.8.1.5.1 |  |  | Develop document with MWG | 100% | Thu 08/12/22 | Fri 10/03/23 | 67 days | Thu 08/12/22 | Fri 10/03/23 | 1767 | 1805FS+2 days | 0 days | 0 days | 0 days | SI Migration | PP |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.1.5.2 |  |  | Artefact review (via TMAG) and updates | 100% | Wed 15/03/23 | Fri 21/04/23 | 28 days | Wed 15/03/23 | Fri 21/04/23 | 1804FS+2 days | 1806FF+5 days | 0 days | 0 days | 0 days | PP | SI Migration |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.1.5.3 | T3-MI-0014 | MCAG | Migration, Cutover & Data Strategy approved | 100% | Fri 28/04/23 | Fri 28/04/23 | 0 days | Fri 28/04/23 | Fri 28/04/23 | 1805FF+5 days | 480 | 0 days | 0 days | 0 days | SI Migration | PP |  |  | 5 | Yes | John Wiggins,Matthew Breen
4 | 1.8.1.6 |  |  | Data Cleanse Plan | 53% | Thu 02/03/23 | Fri 04/04/25 | 547 days | Thu 02/03/23 | Fri 04/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.8.1.6.1 |  |  | Develop document with MWG | 100% | Thu 02/03/23 | Wed 10/05/23 | 50 days | Thu 02/03/23 | Wed 10/05/23 |  | 1809 | 0 days | 0 days | 0 days | SI Migration | PP |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.1.6.2 |  |  | Artefact review (via TMAG) and updates | 100% | Thu 11/05/23 | Wed 07/06/23 | 20 days | Thu 11/05/23 | Wed 07/06/23 | 1808 | 1810FS+30 days | 0 days | 0 days | 0 days | PP | SI Migration,IPA |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.1.6.3 | T3-MI-0020 | MCAG | Data Cleanse Plan approved | 100% | Wed 19/07/23 | Wed 19/07/23 | 0 days | Wed 19/07/23 | Wed 19/07/23 | 1809FS+30 days | 1811,1814FS+282 days,1819FS+281 days,1825FS+302 days,1826FS+302 days,1827FS+302 days,1828FS+296 days,1829FS+302 days,1830FS+311 days,1833FS+426 days,1834FS+426 days,1839FS+176 days | 0 days | 0 days | 0 days | SI Migration | PP |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.1.6.4 |  |  | Monitor Programme Participant adherence to Data Cleanse Plan | 47% | Thu 15/06/23 | Fri 28/03/25 | 467 days | Thu 15/06/23 | Fri 28/03/25 | 1810 | 1844FS+5 days | 0 days | 0 days | 0 days | SI Migration | PP |  |  | 5 | Yes | Matthew Breen
5 | 1.8.1.6.5 |  |  | MTDs | 0% | Fri 16/08/24 | Fri 20/12/24 | 91 days | Fri 16/08/24 | Mon 23/12/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.4 | Yes | N/A
6 | 1.8.1.6.5.1 |  |  | ESME ID | 0% | Fri 16/08/24 | Fri 20/12/24 | 90 days | Fri 16/08/24 | Mon 23/12/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.4 | Yes | N/A
7 | 1.8.1.6.5.1.1 | T3-MI-0024 | MCAG | DCC to extract ESME ID and share with LDSO | 0% | Fri 16/08/24 | Fri 16/08/24 | 0 days | Fri 16/08/24 | Fri 16/08/24 | 1810FS+282 days | 1815FS+30 days | 0 days | 0 days | 0 days | DCC/SI |  |  |  | 5.5 | Yes | Matthew Breen
7 | 1.8.1.6.5.1.2 | T3-MI-0025 | MCAG | LDSO ‘full refresh’ between their Registration Service and the EES (ESME ID) | 0% | Fri 27/09/24 | Fri 27/09/24 | 0 days | Fri 27/09/24 | Fri 27/09/24 | 1814FS+30 days | 1816FS+59 days | 0 days | 0 days | 0 days | LDSO/EES |  |  |  | 5.5 | Yes | Matthew Breen
7 | 1.8.1.6.5.1.3 |  |  | Suppliers complete investigation of exceptions and resolution of exceptions | 0% | Fri 20/12/24 | Fri 20/12/24 | 1 day | Fri 20/12/24 | Fri 20/12/24 | 1815FS+59 days | 1817 | 0 days | 0 days | 0 days | Supplier |  |  |  | 5.4 | Yes | Matthew Breen
7 | 1.8.1.6.5.1.4 |  |  | ESME ID Complete | 0% | Fri 20/12/24 | Fri 20/12/24 | 0 days | Mon 23/12/24 | Mon 23/12/24 | 1816 | 1844 | 0 days | 0 days | 0 days |  |  |  |  | 5.4 | Yes | Matthew Breen
6 | 1.8.1.6.5.2 |  |  | Meter Location and Number of Displayed Register Digits | 0% | Fri 16/08/24 | Fri 20/12/24 | 91 days | Fri 16/08/24 | Mon 23/12/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.4 | Yes | N/A
7 | 1.8.1.6.5.2.1 |  |  | MEM to extract data and share with LDSO | 0% | Fri 16/08/24 | Fri 16/08/24 | 1 day | Fri 16/08/24 | Fri 16/08/24 | 1810FS+281 days | 1820FS+30 days | 0 days | 0 days | 0 days | MEM/SI |  |  |  | 5.4 | Yes | Matthew Breen
7 | 1.8.1.6.5.2.2 | T3-MI-0026 | MCAG | LDSO ‘full refresh’ between their Registration Service and the EES (Meter Location and Number of Displayed Register Digits) | 0% | Fri 27/09/24 | Fri 27/09/24 | 0 days | Fri 27/09/24 | Fri 27/09/24 | 1819FS+30 days | 1821FS+59 days | 0 days | 0 days | 0 days | LDSO /EES |  |  |  | 5.5 | Yes | Matthew Breen
7 | 1.8.1.6.5.2.3 |  |  | Suppliers complete investigation of exceptions and resolution of exceptions | 0% | Fri 20/12/24 | Fri 20/12/24 | 1 day | Fri 20/12/24 | Fri 20/12/24 | 1820FS+59 days | 1822 | 0 days | 0 days | 0 days | Supplier |  |  |  | 5.4 | Yes | Matthew Breen
7 | 1.8.1.6.5.2.4 |  |  | Meter Location and Number of Displayed Register Digits Complete | 0% | Fri 20/12/24 | Fri 20/12/24 | 0 days | Mon 23/12/24 | Mon 23/12/24 | 1821 | 1844 | 0 days | 0 days | 0 days |  |  |  |  | 5.4 | Yes | Matthew Breen
5 | 1.8.1.6.6 |  |  | Registration Data | 0% | Fri 06/09/24 | Mon 31/03/25 | 147 days | Fri 06/09/24 | Mon 31/03/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.4 | Yes | N/A
6 | 1.8.1.6.6.1 |  |  | Connection Type | 0% | Fri 06/09/24 | Fri 27/09/24 | 16 days | Fri 06/09/24 | Fri 27/09/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.4 | Yes | N/A
7 | 1.8.1.6.6.1.1 | T3-MI-0027 | MCAG | Automated Population of Connection Type for Measurement Classes ‘B’, ‘D’, ‘F’ & ‘G’ | 0% | Fri 13/09/24 | Fri 13/09/24 | 0 days | Fri 13/09/24 | Fri 13/09/24 | 1810FS+302 days | 1831 | 0 days | 0 days | 0 days | LDSO |  |  |  | 5.5 | Yes | Matthew Breen
7 | 1.8.1.6.6.1.2 | T3-MI-0028 | MCAG | BAU Population of Connection Type for Site Specific LLFCs within Measurement Classes ‘C’ & ‘E’ | 0% | Fri 13/09/24 | Fri 13/09/24 | 0 days | Fri 13/09/24 | Fri 13/09/24 | 1810FS+302 days | 1831 | 0 days | 0 days | 0 days | LDSO |  |  |  | 5.5 | Yes | Matthew Breen
7 | 1.8.1.6.6.1.3 | T3-MI-0029 | MCAG | Automated Population of Connection Type for Smart Meters within Measurement Class ‘A’ | 0% | Fri 13/09/24 | Fri 13/09/24 | 0 days | Fri 13/09/24 | Fri 13/09/24 | 1810FS+302 days | 1831 | 0 days | 0 days | 0 days | LDSO |  |  |  | 5.5 | Yes | Matthew Breen
7 | 1.8.1.6.6.1.4 |  |  | Population of Connection Type for Traditional and Advanced Meters within Measurement Class ‘A’ | 0% | Fri 06/09/24 | Fri 06/09/24 | 1 day | Fri 06/09/24 | Fri 06/09/24 | 1810FS+296 days | 1831 | 0 days | 0 days | 0 days | Suppliers |  |  |  | 5.4 | Yes | Matthew Breen
7 | 1.8.1.6.6.1.5 | T3-MI-0030 | MCAG | Automated Population of Null Connection Type | 0% | Fri 13/09/24 | Fri 13/09/24 | 0 days | Fri 13/09/24 | Fri 13/09/24 | 1810FS+302 days | 1831 | 0 days | 0 days | 0 days | LDSO |  |  |  | 5.5 | Yes | Matthew Breen
7 | 1.8.1.6.6.1.6 |  |  | Full MPAN refresh to ESS | 0% | Fri 27/09/24 | Fri 27/09/24 | 1 day | Fri 27/09/24 | Fri 27/09/24 | 1810FS+311 days | 1831 | 0 days | 0 days | 0 days | LDSO/EES |  |  |  | 5.4 | Yes | Matthew Breen
7 | 1.8.1.6.6.1.7 |  |  | Connection Type Complete | 0% | Fri 27/09/24 | Fri 27/09/24 | 0 days | Fri 27/09/24 | Fri 27/09/24 | 1.8252e+23 | 1844 | 0 days | 0 days | 0 days |  |  |  |  | 5.4 | Yes | Matthew Breen
6 | 1.8.1.6.6.2 |  |  | Domestic Premises Indicator | 0% | Fri 07/03/25 | Mon 31/03/25 | 17 days | Fri 07/03/25 | Mon 31/03/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.4 | Yes | N/A
7 | 1.8.1.6.6.2.1 |  |  | The DCC to extract Domestic Premises Indicator from the CSS and provide a file to each LDSO and EES. | 0% | Fri 07/03/25 | Fri 07/03/25 | 1 day | Fri 07/03/25 | Fri 07/03/25 | 1810FS+426 days | 1835FS+15 days | 0 days | 0 days | 0 days | DCC |  |  |  | 5.4 | Yes | Matthew Breen
7 | 1.8.1.6.6.2.2 |  |  | Each LDSO notifies the DCC of any exceptions | 0% | Fri 07/03/25 | Fri 07/03/25 | 1 day | Fri 07/03/25 | Fri 07/03/25 | 1810FS+426 days | 1835FS+15 days | 0 days | 0 days | 0 days | LDSO |  |  |  | 5.4 | Yes | Matthew Breen
7 | 1.8.1.6.6.2.3 |  |  | Each LDSO and DCC completes investigation and resolution of exceptions | 0% | Mon 31/03/25 | Mon 31/03/25 | 1 day | Mon 31/03/25 | Mon 31/03/25 | 1833FS+15 days,1834FS+15 days | 1836 | 0 days | 0 days | 0 days | LDSO / DCC |  |  |  | 5.4 | Yes | Matthew Breen
7 | 1.8.1.6.6.2.4 |  |  | Domestic Premises Indicator Complete | 0% | Mon 31/03/25 | Mon 31/03/25 | 0 days | Mon 31/03/25 | Mon 31/03/25 | 1835 | 1844 | 0 days | 0 days | 0 days |  |  |  |  | 5.4 | Yes | Matthew Breen
5 | 1.8.1.6.7 |  |  | Export / Import MPANs | 33% | Fri 22/03/24 | Fri 18/10/24 | 151 days | Fri 22/03/24 | Fri 18/10/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.4 | Yes | N/A
6 | 1.8.1.6.7.1 |  |  | Linking of Export / Import MPANS | 33% | Fri 22/03/24 | Fri 18/10/24 | 151 days | Fri 22/03/24 | Fri 18/10/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.4 | Yes | N/A
7 | 1.8.1.6.7.1.1 |  |  | LDSO utilises BAU processing (DB05s) to populate each import/export association | 100% | Fri 22/03/24 | Fri 22/03/24 | 1 day | Fri 22/03/24 | Fri 22/03/24 | 1810FS+176 days | 1840FS+19 days | 0 days | 0 days | 0 days | LDSO |  |  |  | 5.4 | Yes | Matthew Breen
7 | 1.8.1.6.7.1.2 |  |  | Each LDSO notifies the Registered Supplier of any exceptions | 0% | Fri 19/04/24 | Fri 19/04/24 | 1 day | Fri 19/04/24 | Fri 19/04/24 | 1839FS+19 days | 1841FS+89 days | 0 days | 0 days | 0 days | LDSO |  |  |  | 5.4 | Yes | Matthew Breen
7 | 1.8.1.6.7.1.3 |  |  | Each Supplier completes investigation and resolution of exceptions | 0% | Fri 23/08/24 | Fri 23/08/24 | 1 day | Fri 23/08/24 | Fri 23/08/24 | 1840FS+89 days | 1842FS+40 days | 0 days | 0 days | 0 days | Supplier |  |  |  | 5.4 | Yes | Matthew Breen
7 | 1.8.1.6.7.1.4 | T3-MI-0031 | MCAG | Each LDSO has linked al relevant import/export MPANS | 0% | Fri 18/10/24 | Fri 18/10/24 | 0 days | Fri 18/10/24 | Fri 18/10/24 | 1841FS+40 days | 1843 | 0 days | 0 days | 0 days | LDSO |  |  |  | 5.5 | Yes | Matthew Breen
7 | 1.8.1.6.7.1.5 |  |  | Linking of Export / Import MPANS Complete | 0% | Fri 18/10/24 | Fri 18/10/24 | 0 days | Fri 18/10/24 | Fri 18/10/24 | 1842 | 1844 | 0 days | 0 days | 0 days |  |  |  |  | 5.4 | Yes | Matthew Breen
5 | 1.8.1.6.8 | T2-MI-0450 | MCAG | Pre-migration data cleanse complete | 0% | Fri 04/04/25 | Fri 04/04/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 1930FS-20 days,1932FS-20 days,1811FS+5 days,1817,1822,1831,1836,1843 |  | 0 days | 0 days | 0 days | SI Migration | PP |  |  | 5 | Yes | Matthew Breen
3 | 1.8.2 |  |  | Migration Period Planning | 17% | Mon 03/07/23 | Mon 05/10/26 | 851 days | Mon 03/07/23 | Mon 05/10/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.8.2.1 |  |  | Migration Implementation Plan (incl. Migration Exit Criteria) | 23% | Mon 03/07/23 | Mon 05/10/26 | 851 days | Mon 03/07/23 | Mon 05/10/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.8.2.1.1 |  |  | Migration Threshold Volumes | 100% | Mon 03/07/23 | Mon 20/11/23 | 101 days | Mon 03/07/23 | Wed 15/11/23 |  |  | 0 days | 3 days | 3 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.8.2.1.1.1 |  |  | Threshold volumes reviewed by MWG | 100% | Mon 03/07/23 | Thu 14/09/23 | 54 days | Mon 03/07/23 | Thu 14/09/23 |  | 1849 | 0 days | 0 days | 0 days | SI Migration | PP |  |  | 5.6 | Yes | John Wiggins,Matthew Breen
6 | 1.8.2.1.1.2 |  |  | Artefact review (via TMAG) and updates | 100% | Fri 15/09/23 | Mon 20/11/23 | 47 days | Fri 15/09/23 | Wed 15/11/23 | 1848 | 1850 | 0 days | 3 days | 3 days | PP | SI Migration |  |  | 5.9 | Yes | John Wiggins,Matthew Breen
6 | 1.8.2.1.1.3 | T3-MI-0021 | SITAG | Threshold volumes approved at TMAG | 100% | Mon 20/11/23 | Mon 20/11/23 | 0 days | Wed 15/11/23 | Wed 15/11/23 | 1849 | 18811882 | 3 days | 3 days | 0 days | SI Migration | PP |  |  | 5.12 | Yes | John Wiggins,Matthew Breen
5 | 1.8.2.1.2 |  |  | Operational Migration Planning | 0% | Mon 30/09/24 | Mon 05/10/26 | 526 days | Mon 30/09/24 | Mon 05/10/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.8.2.1.2.1 |  |  | Agree migration plans for each SIT MVC Supplier | 0% | Mon 30/09/24 | Mon 16/12/24 | 55 days | Mon 30/09/24 | Mon 16/12/24 | 1926SF-3 mons | 1853 | 0 days | 0 days | 0 days | SRO | PP |  |  | 5 | Yes | Warren Fulton
6 | 1.8.2.1.2.2 |  |  | Initial migration plan agreed at SITAG | 0% | Mon 16/12/24 | Fri 31/01/25 | 35 days | Mon 16/12/24 | Fri 31/01/25 | 1852 | 1854 | 0 days | 0 days | 0 days | SRO |  |  |  | 5 | Yes | Warren Fulton
6 | 1.8.2.1.2.3 | T3-MI-0016 | MCAG | Migration Period Plan Review 1 Completed | 0% | Fri 31/01/25 | Fri 31/01/25 | 0 days | Fri 31/01/25 | Fri 31/01/25 | 1853 |  | 0 days | 0 days | 0 days | SRO | PP,IPA |  |  | 5 | Yes | Warren Fulton
6 | 1.8.2.1.2.4 |  |  | Finalise initial live plan | 0% | Mon 07/04/25 | Mon 07/04/25 | 1 day | Mon 07/04/25 | Mon 07/04/25 | 1930 |  | 0 days | 0 days | 0 days | SRO |  |  |  | 5 | Yes | Warren Fulton
6 | 1.8.2.1.2.5 |  |  | Agree migration plans with suppliers aligned with qualification tranches | 0% | Mon 30/12/24 | Thu 12/03/26 | 314 days | Wed 01/01/25 | Mon 16/03/26 | 1934FF |  | -2 days | -2 days | 0 days | SRO | PP |  |  | 5 | Yes | Warren Fulton
6 | 1.8.2.1.2.6 |  |  | Migration control centre undertakes iterative planning and performance monitoring | 0% | Mon 07/04/25 | Mon 05/10/26 | 391 days | Mon 07/04/25 | Mon 05/10/26 | 1930 |  | 0 days | 0 days | 0 days | SRO |  |  |  | 5 | Yes | Warren Fulton
5 | 1.8.2.1.3 |  |  | Define acceptance criteria for M15 | 100% | Mon 04/09/23 | Wed 20/12/23 | 78 days | Mon 04/09/23 | Wed 20/12/23 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.8.2.1.3.1 |  |  | Review acceptance criteria and reporting requirements with MWG | 100% | Mon 04/09/23 | Thu 09/11/23 | 49 days | Mon 04/09/23 | Fri 27/10/23 |  | 1860 | 0 days | 9 days | 9 days | SI Migration |  |  |  | 5 | Yes | John Wiggins,Matthew Breen
6 | 1.8.2.1.3.2 |  |  | Artefact review (via TMAG) and updates | 100% | Fri 10/11/23 | Wed 20/12/23 | 29 days | Fri 10/11/23 | Wed 20/12/23 | 1859 | 1861 | 0 days | 0 days | 0 days | PP | SI Migration |  |  | 5 | Yes | John Wiggins,Matthew Breen
6 | 1.8.2.1.3.3 | T3-MI-0022 | SITAG | Acceptance criteria for M15 agreed at TMAG | 100% | Wed 20/12/23 | Wed 20/12/23 | 0 days | Wed 20/12/23 | Wed 20/12/23 | 1860 | 1863 | 0 days | 0 days | 0 days | SI Migration |  |  |  | 5.14 | Yes | John Wiggins,Matthew Breen
5 | 1.8.2.1.4 |  |  | M10/M11 cut-over plan | 88% | Thu 21/12/23 | Tue 28/05/24 | 114 days | Thu 21/12/23 | Tue 28/05/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.16 | Yes | N/A
6 | 1.8.2.1.4.1 |  |  | Draft Document | 100% | Thu 21/12/23 | Tue 16/04/24 | 84 days | Thu 21/12/23 | Tue 16/04/24 | 1861 | 1864 | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.16 | Yes | Matthew Breen
6 | 1.8.2.1.4.2 |  |  | Share Document with SRO | 100% | Wed 17/04/24 | Wed 17/04/24 | 1 day | Wed 17/04/24 | Wed 17/04/24 | 1863 | 1865FS+3 days | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.16 | Yes | Matthew Breen
6 | 1.8.2.1.4.3 |  |  | Industry Consultation | 0% | Tue 23/04/24 | Tue 07/05/24 | 11 days | Tue 23/04/24 | Tue 07/05/24 | 1864FS+3 days | 1866FS+4 days | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.16 | Yes | Matthew Breen
6 | 1.8.2.1.4.4 |  |  | Assurance Meeting | 0% | Tue 14/05/24 | Tue 14/05/24 | 1 day | Tue 14/05/24 | Tue 14/05/24 | 1865FS+4 days | 1867FS+10 days | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.16 | Yes | Matthew Breen
6 | 1.8.2.1.4.5 | T3-MI-0023 | MCAG | MCAG Approval of M10/M11 Cut-over Plan | 0% | Tue 28/05/24 | Tue 28/05/24 | 0 days | Tue 28/05/24 | Tue 28/05/24 | 1866FS+10 days | 1869 | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.19 | Yes | Matthew Breen
5 | 1.8.2.1.5 |  |  | M15/M16 cut-over plan | 0% | Wed 29/05/24 | Tue 24/09/24 | 85 days | Thu 21/03/24 | Tue 24/09/24 |  |  | 49 days | 0 days | -49 days | N/A | N/A |  |  | 5.16 | Yes | N/A
6 | 1.8.2.1.5.1 |  |  | Draft Document | 0% | Wed 29/05/24 | Tue 20/08/24 | 60 days | Thu 21/03/24 | Tue 20/08/24 | 1867 | 1870 | 49 days | 0 days | -49 days | SI Transition | SI Transition,PP,SRO |  |  | 5.16 | Yes | Matthew Breen
6 | 1.8.2.1.5.2 |  |  | Share Document with SRO | 0% | Wed 21/08/24 | Wed 21/08/24 | 1 day | Wed 21/08/24 | Wed 21/08/24 | 1869 | 1871FS+3 days | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.16 | Yes | Matthew Breen
6 | 1.8.2.1.5.3 |  |  | Industry Consultation | 0% | Tue 27/08/24 | Tue 10/09/24 | 11 days | Tue 27/08/24 | Tue 10/09/24 | 1870FS+3 days | 1872FS+4 days | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.16 | Yes | Matthew Breen
6 | 1.8.2.1.5.4 |  |  | Assurance Meeting | 0% | Tue 17/09/24 | Tue 17/09/24 | 1 day | Tue 17/09/24 | Tue 17/09/24 | 1871FS+4 days | 1873FS+5 days,1875 | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.16 | Yes | Matthew Breen
6 | 1.8.2.1.5.5 | T3-MI-0032 | MCAG | Approval of M15/M16 cut-over plan | 0% | Tue 24/09/24 | Tue 24/09/24 | 0 days | Tue 24/09/24 | Tue 24/09/24 | 1872FS+5 days |  | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.19 | Yes | Matthew Breen
5 | 1.8.2.1.6 |  |  | M16 Methodology | 0% | Tue 17/09/24 | Tue 15/10/24 | 20 days | Tue 17/09/24 | Tue 15/10/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
6 | 1.8.2.1.6.1 |  |  | Draft Document | 0% | Tue 17/09/24 | Tue 17/09/24 | 0 days | Tue 17/09/24 | Tue 17/09/24 | 1872 | 1876 | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.16 | Yes | Matthew Breen
6 | 1.8.2.1.6.2 |  |  | Share Document with SRO | 0% | Tue 17/09/24 | Tue 17/09/24 | 0 days | Tue 17/09/24 | Tue 17/09/24 | 1875 | 1877FS+4 days | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.16 | Yes | Matthew Breen
6 | 1.8.2.1.6.3 |  |  | Industry Consultation | 0% | Tue 24/09/24 | Tue 08/10/24 | 11 days | Tue 24/09/24 | Tue 08/10/24 | 1876FS+4 days | 1878FS+4 days | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.16 | Yes | Matthew Breen
6 | 1.8.2.1.6.4 |  |  | Assurance Meeting | 0% | Tue 15/10/24 | Tue 15/10/24 | 1 day | Tue 15/10/24 | Tue 15/10/24 | 1877FS+4 days | 1879 | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.16 | Yes | Matthew Breen
6 | 1.8.2.1.6.5 | T3-MI-0500 | MCAG | M16 methodology approved | 0% | Tue 15/10/24 | Tue 15/10/24 | 0 days | Tue 15/10/24 | Tue 15/10/24 | 1878 |  | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.17 | Yes | Matthew Breen
4 | 1.8.2.2 |  |  | Migration Processes, Procedures and Tools | 0% | Mon 01/01/24 | Fri 21/02/25 | 300 days | Mon 01/01/24 | Fri 21/02/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.8.2.2.1 |  |  | Design Migration control centre processes and procedures | 0% | Mon 01/01/24 | Fri 28/06/24 | 130 days | Mon 01/01/24 | Fri 28/06/24 | 1850 | 1883 | 0 days | 0 days | 0 days | SRO |  |  |  | 5 | Yes | Warren Fulton
5 | 1.8.2.2.2 |  |  | Develop migration planning and management tool requirements | 0% | Mon 01/01/24 | Fri 28/06/24 | 130 days | Mon 01/01/24 | Fri 28/06/24 | 1850 |  | 0 days | 0 days | 0 days | SRO |  |  |  | 5 | Yes | Warren Fulton
5 | 1.8.2.2.3 |  |  | SITAG approval of migration processes, procedures and tools | 0% | Mon 01/07/24 | Fri 26/07/24 | 20 days | Mon 01/07/24 | Fri 26/07/24 | 1881 | 1884FF+5 days | 0 days | 0 days | 0 days | SRO |  |  |  | 5 | Yes | Warren Fulton
5 | 1.8.2.2.4 | T3-MI-0017 | MCAG | Migration Processes & Procedures approved | 0% | Fri 02/08/24 | Fri 02/08/24 | 0 days | Fri 02/08/24 | Fri 02/08/24 | 1883FF+5 days | 1885 | 0 days | 0 days | 0 days | SRO | PP,IPA |  |  | 5 | Yes | Warren Fulton
5 | 1.8.2.2.5 |  |  | Build and test migration tool | 0% | Mon 05/08/24 | Fri 27/12/24 | 105 days | Mon 05/08/24 | Fri 27/12/24 | 1884 | 1886 | 0 days | 0 days | 0 days | SRO |  |  |  | 5 | Yes | Warren Fulton
5 | 1.8.2.2.6 |  |  | Deploy migration tool | 0% | Mon 30/12/24 | Fri 24/01/25 | 20 days | Mon 30/12/24 | Fri 24/01/25 | 1885 | 1887 | 0 days | 0 days | 0 days | SRO |  |  |  | 5 | Yes | Warren Fulton
5 | 1.8.2.2.7 |  |  | Operationalisation of migration control centre | 0% | Mon 27/01/25 | Fri 21/02/25 | 20 days | Mon 27/01/25 | Fri 21/02/25 | 1886 |  | 0 days | 0 days | 0 days | SRO |  |  |  | 5 | Yes | Warren Fulton
3 | 1.8.3 |  |  | Go-Live Dress Rehearsals | 0% | Fri 04/10/24 | Thu 06/03/25 | 110 days | Fri 04/10/24 | Thu 06/03/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.8.3.1 |  |  | Define dress rehearsal scenarios (incl. engagement with MWG) | 0% | Fri 04/10/24 | Thu 31/10/24 | 20 days | Fri 04/10/24 | Thu 31/10/24 | 1930FS-131 days,1932FS-131 days |  | 0 days | 0 days | 0 days | SI Migration | PP |  |  | 5 | Yes | Matthew Breen
4 | 1.8.3.2 |  |  | Set up, coordinate and conduct dress rehearsals | 0% | Fri 07/02/25 | Thu 20/02/25 | 10 days | Fri 07/02/25 | Thu 20/02/25 | 1077 | 1891 | 0 days | 0 days | 0 days | SI Migration | PP |  |  | 5 | Yes | Matthew Breen
4 | 1.8.3.3 |  |  | Evaluate dress rehearsals and identify lessons learned | 0% | Fri 21/02/25 | Thu 06/03/25 | 10 days | Fri 21/02/25 | Thu 06/03/25 | 1890 |  | 0 days | 0 days | 0 days | SI Migration | PP |  |  | 5 | Yes | Matthew Breen
3 | 1.8.4 |  |  | Preparation for Cutover to Live | 0% | Mon 10/02/25 | Fri 04/04/25 | 40 days | Mon 10/02/25 | Fri 04/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.8.4.1 |  |  | Central Systems Prepare for Cutover to Live | 0% | Mon 10/02/25 | Fri 07/03/25 | 20 days | Mon 10/02/25 | Fri 07/03/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.8.4.1.1 |  |  | Central Systems Prepare for Cutover to Live | 0% | Mon 10/02/25 | Fri 07/03/25 | 20 days | Mon 10/02/25 | Fri 07/03/25 | 1926FF,1077 |  | 0 days | 0 days | 0 days | PP | SI |  |  | 5 | Yes | Matthew Breen
4 | 1.8.4.2 |  |  | Advanced & UMS Prepare for Cutover to Live | 0% | Mon 10/02/25 | Fri 04/04/25 | 40 days | Mon 10/02/25 | Fri 04/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.8.4.2.1 |  |  | Advanced & UMS Prepare for Cutover to Live | 0% | Mon 10/02/25 | Fri 04/04/25 | 40 days | Mon 10/02/25 | Fri 04/04/25 | 1930FF,1077 |  | 0 days | 0 days | 0 days | PP | SI |  |  | 5 | Yes | Matthew Breen
4 | 1.8.4.3 |  |  | Smart/Non-Smart Prepare for Cutover to Live | 0% | Mon 10/02/25 | Fri 04/04/25 | 40 days | Mon 10/02/25 | Fri 04/04/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.8.4.3.1 |  |  | Smart/Non-Smart Prepare for Cutover to Live | 0% | Mon 10/02/25 | Fri 04/04/25 | 40 days | Mon 10/02/25 | Fri 04/04/25 | 1932FF,1077 |  | 0 days | 0 days | 0 days | PP | SI |  |  | 5 | Yes | Matthew Breen
3 | 1.8.5 |  |  | Migration of Advanced Segment | 0% | Mon 07/04/25 | Mon 05/10/26 | 391 days | Mon 07/04/25 | Mon 05/10/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.8.5.1 |  |  | Migration of Advanced Segment (SIT MVC) | 0% | Mon 07/04/25 | Mon 05/10/26 | 391 days | Mon 07/04/25 | Mon 05/10/26 | 1930 | 1909SS,1936FF,1952SS | 0 days | 0 days | 0 days | SRO | PP |  |  | 5 | Yes | Warren Fulton
4 | 1.8.5.2 |  |  | Migration of Advanced Segment (non-SIT PPs) | 0% | Tue 30/09/25 | Thu 01/10/26 | 263 days | Tue 30/09/25 | Mon 05/10/26 | 1572 | 1936FF | 0 days | -2 days | -2 days | SRO | PP |  |  | 5 | Yes | Warren Fulton
3 | 1.8.6 |  |  | Migration of Unmetered Segment | 0% | Mon 07/04/25 | Mon 05/10/26 | 391 days | Mon 07/04/25 | Mon 05/10/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.8.6.1 |  |  | Migration of Unmetered Segment (SIT MVC) | 0% | Mon 07/04/25 | Mon 05/10/26 | 391 days | Mon 07/04/25 | Mon 05/10/26 | 1930 | 1909SS,1936FF | 0 days | 0 days | 0 days | SRO | PPC |  |  | 5 | Yes | Warren Fulton
4 | 1.8.6.2 |  |  | Migration of Unmetered Segment (non-SIT PPs) | 0% | Tue 30/09/25 | Thu 01/10/26 | 263 days | Tue 30/09/25 | Mon 05/10/26 | 1572 | 1936FF | 0 days | -2 days | -2 days | SRO | PP |  |  | 5 | Yes | Warren Fulton
3 | 1.8.7 |  |  | Migration of Smart / Non-Smart Segments | 0% | Mon 07/04/25 | Mon 05/10/26 | 391 days | Mon 07/04/25 | Mon 05/10/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.8.7.1 |  |  | Migration of Smart / Non-Smart Segments (SIT MVC) | 0% | Mon 07/04/25 | Mon 05/10/26 | 391 days | Mon 07/04/25 | Mon 05/10/26 | 1930 | 1909SS,1936FF | 0 days | 0 days | 0 days | SRO | PP |  |  | 5 | Yes | Warren Fulton
4 | 1.8.7.2 |  |  | Migration of Smart / Non-Smart Segments (non-SIT PPs) | 0% | Tue 30/09/25 | Thu 01/10/26 | 263 days | Tue 30/09/25 | Mon 05/10/26 | 1572 | 1936FF | 0 days | -2 days | -2 days | SRO | PP |  |  | 5 | Yes | Warren Fulton
3 | 1.8.8 |  |  | Migration Management | 0% | Mon 07/04/25 | Mon 05/10/26 | 391 days | Mon 07/04/25 | Mon 05/10/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.8.8.1 |  |  | Migration Management | 0% | Mon 07/04/25 | Mon 05/10/26 | 391 days | Mon 07/04/25 | Mon 05/10/26 | 1900SS,1903SS,1906SS |  | 0 days | 0 days | 0 days | SRO | PPC |  |  | 5 | Yes | Warren Fulton
3 | 1.8.9 |  |  | External Programme Dependency Management | 63% | Mon 31/10/22 | Wed 23/07/25 | 713 days | Mon 31/10/22 | Tue 30/12/25 |  |  | 0 days | -114 days | -114 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.8.9.1 |  |  | BSC Mod P432 & REC CP R0015 | 98% | Mon 31/10/22 | Tue 30/04/24 | 392 days | Mon 31/10/22 | Tue 30/12/25 |  |  | 0 days | -435 days | -435 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.8.9.1.1 |  |  | MHHSP engagement with BSCCo until Ofgem decision | 100% | Mon 31/10/22 | Mon 15/01/24 | 316 days | Mon 31/10/22 | Fri 10/05/24 |  | 1913 | 0 days | -84 days | -84 days | CPT,SRO Function | Code Bodies |  |  | 5 | Yes | Matthew Breen
5 | 1.8.9.1.2 |  |  | Monitor progress and await implementation date | 88% | Tue 16/01/24 | Tue 30/04/24 | 76 days | Mon 03/07/23 | Tue 30/12/25 | 1912 |  | 141 days | -435 days | -576 days | CPT,SRO Function | Code Bodies |  |  | 5 | Yes | Matthew Breen
4 | 1.8.9.2 |  |  | BSC Mod P434 | 54% | Mon 31/10/22 | Wed 23/07/25 | 713 days | Mon 31/10/22 | Wed 23/07/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.8.9.2.1 |  |  | MHHSP engagement with BSCCo until Ofgem decision | 100% | Mon 31/10/22 | Mon 23/01/23 | 61 days | Mon 31/10/22 | Mon 23/01/23 |  | 1916 | 0 days | 0 days | 0 days | CPT,SRO Function | Code Bodies |  |  | 5 | Yes | John Wiggins,Matthew Breen
5 | 1.8.9.2.2 |  |  | Monitor progress and await implementation date | 49% | Tue 24/01/23 | Wed 23/07/25 | 652 days | Tue 24/01/23 | Wed 23/07/25 | 1915 |  | 0 days | 0 days | 0 days | CPT,SRO Function | Code Bodies |  |  | 5 | Yes | Matthew Breen
4 | 1.8.9.3 |  |  | Elexon System Capacity Upgrade | 54% | Mon 31/10/22 | Tue 01/07/25 | 697 days | Mon 31/10/22 | Tue 01/07/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.8.9.3.1 |  |  | Monitor progress to implementation | 54% | Mon 31/10/22 | Tue 01/07/25 | 697 days | Mon 31/10/22 | Tue 01/07/25 |  | 1919 | 0 days | 0 days | 0 days | SI Migration | PP |  |  | 5 | Yes | Matthew Breen
5 | 1.8.9.3.2 |  |  | Implementation date | 0% | Tue 01/07/25 | Tue 01/07/25 | 0 days | Tue 01/07/25 | Tue 01/07/25 | 1918 |  | 0 days | 0 days | 0 days | PP | SI Migration |  |  | 5 | Yes | Matthew Breen
4 | 1.8.9.4 |  |  | DCC System Capacity Upgrade | 0% | Mon 13/01/25 | Fri 14/02/25 | 25 days | Mon 13/01/25 | Fri 14/02/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.8.9.4.1 |  |  | Assurance of DCC capacity upgrade to ensure suitability to support migration | 0% | Mon 13/01/25 | Fri 07/02/25 | 20 days | Mon 13/01/25 | Fri 07/02/25 | 1926FF-20 days | 1922FS+5 days | 0 days | 0 days | 0 days | SI Migration | PP |  |  | 5 | Yes | Matthew Breen
5 | 1.8.9.4.2 | T2-MI-0350 | MCAG | DCC Capacity Upgrade Operational | 0% | Fri 14/02/25 | Fri 14/02/25 | 0 days | Fri 14/02/25 | Fri 14/02/25 | 1921FS+5 days |  | 0 days | 0 days | 0 days | PP | SI Migration,IPA |  |  | 5 | Yes | Matthew Breen
4 | 1.8.9.5 |  |  | Performance Assurance Arrangements | 0% | Tue 01/07/25 | Tue 01/07/25 | 0 days | Tue 01/07/25 | Tue 01/07/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.8.9.5.1 |  |  | Performance assurance regime for migration success delivered | 0% | Tue 01/07/25 | Tue 01/07/25 | 0 days | Tue 01/07/25 | Tue 01/07/25 |  |  | 0 days | 0 days | 0 days | Code Bodies | SI Migration |  |  | 5 | Yes | Simon chidwick
3 | 1.8.10 |  |  | Migration - Tier 1 Milestones | 0% | Fri 07/03/25 | Tue 05/01/27 | 477 days | Fri 07/03/25 | Tue 05/01/27 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.8.10.1 | T1-MI-1000 | PSG | Central systems ready for migrating MPANs (M10) | 0% | Fri 07/03/25 | Fri 07/03/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 1077FS+21 days | 1928,1930FS+20 days,1932FS+20 days,1894FF,1757SS,1921FF-20 days,1927FS+65 days,2093FS-3 mons,1951,1852SF-3 mons | 0 days | 0 days | 0 days | CPT | CPT |  |  | 5 | Yes | CPT
4 | 1.8.10.2 | T2-MI-1500 | PSG | Central systems ready for migrating MPANs (M10*) - Late Exit | 0% | Fri 06/06/25 | Fri 06/06/25 | 0 days | Fri 06/06/25 | Fri 06/06/25 | 1926FS+65 days |  | 0 days | 0 days | 0 days | CPT | CPT |  |  | 5 | Yes | CPT
4 | 1.8.10.3 | T1-MI-2000 | PSG | Load Shaping Service switched on (M13) | 0% | Fri 07/03/25 | Fri 07/03/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 1926 | 1929FS+65 days,1930,1932,2093FS-3 mons | 0 days | 0 days | 0 days | CPT | CPT |  |  | 5 | Yes | CPT
4 | 1.8.10.4 | T2-MI-2500 | PSG | Load Shaping Service switched on (M13*) - Late Exit | 0% | Fri 06/06/25 | Fri 06/06/25 | 0 days | Fri 06/06/25 | Fri 06/06/25 | 1928FS+65 days |  | 0 days | 0 days | 0 days | CPT | CPT |  |  | 5 | Yes | CPT
4 | 1.8.10.5 | T1-MI-3000 | PSG | Start of 18-month migration for UMS / Advanced (M11) | 0% | Fri 04/04/25 | Fri 04/04/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 1926FS+20 days,1928 | 1903,1900,1889FS-131 days,1896FF,1844FS-20 days,1906,1931FS+65 days,2093FS-3 mons,1855,1857,1977 | 0 days | 0 days | 0 days | CPT | CPT |  |  | 5 | Yes | CPT
4 | 1.8.10.6 | T2-MI-3500 | PSG | Start of 18-month migration for UMS / Advanced (M11*) - Late Exit | 0% | Fri 04/07/25 | Fri 04/07/25 | 0 days | Fri 04/07/25 | Fri 04/07/25 | 1930FS+65 days |  | 0 days | 0 days | 0 days | CPT | CPT |  |  | 5 | Yes | CPT
4 | 1.8.10.7 | T1-MI-4000 | PSG | Start of 18-month migration for Smart / Non-smart (M12) | 0% | Fri 04/04/25 | Fri 04/04/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 1926FS+20 days,1928 | 1889FS-131 days,1898FF,1960FS-45 days,1964FS-45 days,1844FS-20 days,1933FS+65 days,2093FS-3 mons | 0 days | 0 days | 0 days | CPT | CPT |  |  | 5 | Yes | CPT
4 | 1.8.10.8 | T2-MI-4500 | PSG | Start of 18-month migration for Smart / Non-smart (M12*) - Late Exit | 0% | Fri 04/07/25 | Fri 04/07/25 | 0 days | Fri 04/07/25 | Fri 04/07/25 | 1932FS+65 days |  | 0 days | 0 days | 0 days | CPT | CPT |  |  | 5 | Yes | CPT
4 | 1.8.10.9 | T1-MI-5000 | PSG | All suppliers must be able to access MPANs under the new TOM (M14) | 0% | Thu 12/03/26 | Thu 12/03/26 | 0 days | Mon 16/03/26 | Mon 16/03/26 | 1.6022e+31 | 2055FS-50 days,1562FF-2 mons,1563FF-2 mons,1935FS+66 days,2095FS-3 mons,1856FF | -2 days | -2 days | 0 days | CPT | CPT |  |  | 5 | Yes | CPT
4 | 1.8.10.10 | T1-MI-5500 | PSG | All suppliers must be able to access MPANs under the new TOM (M14*) - Late Exit | 0% | Fri 12/06/26 | Fri 12/06/26 | 0 days | Tue 16/06/26 | Tue 16/06/26 | 1934FS+66 days |  | -2 days | -2 days | 0 days | CPT | CPT |  |  | 5 | Yes | CPT
4 | 1.8.10.11 | T1-MI-6000 | PSG | Full transition complete (M15) | 0% | Mon 05/10/26 | Mon 05/10/26 | 0 days | Mon 05/10/26 | Mon 05/10/26 | 1900FF,1903FF,1906FF,1901FF,1904FF,1907FF | 1994,1999FS-45 days,2007FS-45 days,2011FS-45 days,2015FS-45 days,2019FS-45 days,2023FS-45 days,2027FS-45 days,1937FS+66 days,2097FS-3 mons,1989FS+45 days | 0 days | 0 days | 0 days | CPT | CPT |  |  | 5 | Yes | CPT
4 | 1.8.10.12 | T2-MI-6500 | PSG | Full transition complete (M15*) - Late Exit | 0% | Tue 05/01/27 | Tue 05/01/27 | 0 days | Tue 05/01/27 | Tue 05/01/27 | 1936FS+66 days |  | 0 days | 0 days | 0 days | CPT | CPT |  |  | 5 | Yes | CPT
2 | 1.9 |  |  | BUSINESS & OPERATIONAL READINESS | 6% | Tue 19/09/23 | Fri 28/05/27 | 964 days | Tue 19/09/23 | Fri 28/05/27 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  |  | Yes | N/A
3 | 1.9.1 |  |  | Service Management | 22% | Tue 19/09/23 | Mon 07/12/26 | 840 days | Tue 19/09/23 | Mon 07/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.9.1.1 |  |  | Service Management Strategy | 100% | Tue 19/09/23 | Tue 27/02/24 | 116 days | Tue 19/09/23 | Tue 27/02/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.9.1.1.1 |  |  | Develop document with relevant participants (incl. review of the design baseline to ensure service management arrangements are in place across the solution architecture) | 100% | Tue 19/09/23 | Fri 12/01/24 | 84 days | Tue 19/09/23 | Fri 12/01/24 |  | 1942 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Matthew Breen
5 | 1.9.1.1.2 |  |  | Artefact review (via relevant Advisory Group) and updates | 100% | Mon 15/01/24 | Mon 26/02/24 | 31 days | Mon 15/01/24 | Mon 26/02/24 | 1941 | 1943FS+1 day | 0 days | 0 days | 0 days | PP | SI Design,IPA |  |  | 5 | Yes | Matthew Breen
5 | 1.9.1.1.3 | T3-BC-0010 | MCAG | Service Management Strategy approved | 100% | Tue 27/02/24 | Tue 27/02/24 | 0 days | Tue 27/02/24 | Tue 27/02/24 | 1942FS+1 day | 1945 | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5.16 | Yes | Matthew Breen
4 | 1.9.1.2 |  |  | Early Life Support Model | 53% | Wed 28/02/24 | Tue 25/06/24 | 85 days | Wed 28/02/24 | Tue 25/06/24 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.16 | Yes | N/A
5 | 1.9.1.2.1 |  |  | Draft Document | 65% | Wed 28/02/24 | Tue 14/05/24 | 55 days | Wed 28/02/24 | Tue 14/05/24 | 1943 | 1946 | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.16 | Yes | Matthew Breen
5 | 1.9.1.2.2 |  |  | Share document with SRO | 0% | Wed 15/05/24 | Wed 15/05/24 | 1 day | Wed 15/05/24 | Wed 15/05/24 | 1945 | 1947FS+3 days | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.16 | Yes | Matthew Breen
5 | 1.9.1.2.3 |  |  | Industry Consultation | 0% | Tue 21/05/24 | Tue 04/06/24 | 11 days | Tue 21/05/24 | Tue 04/06/24 | 1946FS+3 days | 1948FS+4 days | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.16 | Yes | Matthew Breen
5 | 1.9.1.2.4 |  |  | Assurance Meeting | 0% | Tue 11/06/24 | Tue 11/06/24 | 1 day | Tue 11/06/24 | Tue 11/06/24 | 1947FS+4 days | 1949FS+10 days | 0 days | 0 days | 0 days | SI Transition | SI Transition,PP,SRO |  |  | 5.16 | Yes | Matthew Breen
5 | 1.9.1.2.5 | T3-MI-0033 | MCAG | MCAG Approval of Early Life Support Model | 0% | Tue 25/06/24 | Tue 25/06/24 | 0 days | Tue 25/06/24 | Tue 25/06/24 | 1948FS+10 days | 1954 | 0 days | 0 days | 0 days | SI Transition | PP,SRO,SI Transition |  |  | 5.19 | Yes | Matthew Breen
4 | 1.9.1.3 |  |  | Service Management Arrangements Implementation | 0% | Mon 10/03/25 | Mon 07/12/26 | 456 days | Mon 10/03/25 | Mon 07/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.9.1.3.1 |  |  | Hypercare post M10 | 0% | Mon 10/03/25 | Fri 27/06/25 | 80 days | Mon 10/03/25 | Fri 27/06/25 | 1926 |  | 0 days | 0 days | 0 days | SI Design | PP |  |  | 5 | Yes | Matthew Breen
5 | 1.9.1.3.2 |  |  | Monitor Elexon implementation of Service Management arrangements | 0% | Mon 07/04/25 | Mon 07/12/26 | 436 days | Mon 07/04/25 | Mon 07/12/26 | 1900SS |  | 0 days | 0 days | 0 days | PP | SI Design |  |  | 5 | Yes | Matthew Breen
3 | 1.9.2 |  |  | Implement Early Life Support Plan | 0% | Mon 06/01/25 | Fri 28/02/25 | 40 days | Mon 06/01/25 | Fri 28/02/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.9.2.1 |  |  | Implement Early Life Support Plan | 0% | Mon 06/01/25 | Fri 28/02/25 | 40 days | Mon 06/01/25 | Fri 28/02/25 | 1949 |  | 0 days | 0 days | 0 days | SI Transition | SI Transition,CPT |  |  | 5 | Yes | Matthew Breen
3 | 1.9.3 |  |  | Business Continuity and Disaster Recovery Plan | 0% | Mon 13/01/25 | Fri 07/03/25 | 40 days | Mon 13/01/25 | Fri 07/03/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.9.3.1 |  |  | Develop document | 0% | Mon 13/01/25 | Fri 07/02/25 | 20 days | Mon 13/01/25 | Fri 07/02/25 | 1757FS-40 days | 1957 | 0 days | 0 days | 0 days | SI Design |  |  |  | 5 | Yes | Matthew Breen
4 | 1.9.3.2 |  |  | Document review and update | 0% | Mon 10/02/25 | Fri 07/03/25 | 20 days | Mon 10/02/25 | Fri 07/03/25 | 1956 | 1958 | 0 days | 0 days | 0 days | PP | SI Design |  |  | 5 | Yes | Matthew Breen
4 | 1.9.3.3 |  |  | Business Continuity and Disaster Recovery Plan approved by SRO | 0% | Fri 07/03/25 | Fri 07/03/25 | 0 days | Fri 07/03/25 | Fri 07/03/25 | 1957 |  | 0 days | 0 days | 0 days | SRO Design | SI Design |  |  | 5 | Yes | Matthew Breen
3 | 1.9.4 |  |  | Operations Support Guide | 0% | Mon 03/02/25 | Fri 28/03/25 | 40 days | Mon 03/02/25 | Fri 28/03/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.9.4.1 |  |  | Develop document | 0% | Mon 03/02/25 | Fri 28/02/25 | 20 days | Mon 03/02/25 | Fri 28/02/25 | 1932FS-45 days | 1961 | 0 days | 0 days | 0 days | SRO | SRO |  |  | 5 | Yes | Warren Fulton
4 | 1.9.4.2 |  |  | Document review and update | 0% | Mon 03/03/25 | Fri 28/03/25 | 20 days | Mon 03/03/25 | Fri 28/03/25 | 1960 | 1962 | 0 days | 0 days | 0 days | SRO | SRO |  |  | 5 | Yes | Warren Fulton
4 | 1.9.4.3 |  |  | Operations Support Guide approved | 0% | Fri 28/03/25 | Fri 28/03/25 | 0 days | Fri 28/03/25 | Fri 28/03/25 | 1961 |  | 0 days | 0 days | 0 days | SRO | SRO |  |  | 5 | Yes | Warren Fulton
3 | 1.9.5 |  |  | Training and Support Materials | 0% | Mon 03/02/25 | Fri 28/03/25 | 40 days | Mon 03/02/25 | Fri 28/03/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.9.5.1 |  |  | Develop document | 0% | Mon 03/02/25 | Fri 28/02/25 | 20 days | Mon 03/02/25 | Fri 28/02/25 | 1932FS-45 days | 1965 | 0 days | 0 days | 0 days | SI Migration | CPT |  |  | 5 | Yes | Matthew Breen
4 | 1.9.5.2 |  |  | Document review and update | 0% | Mon 03/03/25 | Fri 28/03/25 | 20 days | Mon 03/03/25 | Fri 28/03/25 | 1964 | 1966 | 0 days | 0 days | 0 days | SI Migration | PMO,CPT,IPA,PP |  |  | 5 | Yes | Matthew Breen
4 | 1.9.5.3 |  |  | Training and Support Materials approved | 0% | Fri 28/03/25 | Fri 28/03/25 | 0 days | Fri 28/03/25 | Fri 28/03/25 | 1965 |  | 0 days | 0 days | 0 days | SI Migration | PMO,CPT |  |  | 5 | Yes | Matthew Breen
3 | 1.9.6 |  |  | PP Business Change | 0% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.9.6.1 |  |  | Plan stakeholder management | 0% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 |  |  | 0 days | 0 days | 0 days | PP | PPC |  |  | 5 | Yes | Matthew Breen
4 | 1.9.6.2 |  |  | Manage stakeholders | 0% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 |  |  | 0 days | 0 days | 0 days | PP | PPC |  |  | 5 | Yes | Matthew Breen
4 | 1.9.6.3 |  |  | Develop & implement changes to KPIs, organisation & people management | 0% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 |  |  | 0 days | 0 days | 0 days | PP | PPC |  |  | 5 | Yes | Matthew Breen
4 | 1.9.6.4 |  |  | Develop & test changes to business processes | 0% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 |  |  | 0 days | 0 days | 0 days | PP | PPC |  |  | 5 | Yes | Matthew Breen
4 | 1.9.6.5 |  |  | Develop and deliver training | 0% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 |  |  | 0 days | 0 days | 0 days | PP | PPC |  |  | 5 | Yes | Matthew Breen
4 | 1.9.6.6 |  |  | Programme support for PP Business Change activities | 0% | Mon 03/02/25 | Thu 31/07/25 | 129 days | Mon 03/02/25 | Thu 31/07/25 |  |  | 0 days | 0 days | 0 days | PPC | PP |  |  | 5 | Yes | Matthew Breen
3 | 1.9.7 |  |  | Supplier Business Readiness for Cutover | 0% | Wed 01/10/25 | Fri 30/10/26 | 283 days | Wed 01/10/25 | Fri 30/10/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.9.7.1 |  |  | Programme support for Supplier Business Readiness for Cutover activities (incl. setup, management and evaluation of dress rehearsals) | 0% | Wed 01/10/25 | Fri 30/10/26 | 283 days | Wed 01/10/25 | Fri 30/10/26 |  |  | 0 days | 0 days | 0 days | PPC | PP |  |  | 5 | Yes | Matthew Breen
3 | 1.9.8 |  |  | Transition to New Settlement Timetable (M16) | 0% | Fri 04/04/25 | Fri 28/05/27 | 560 days | Fri 04/04/25 | Fri 28/05/27 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5.15 | Yes | N/A
4 | 1.9.8.1 |  |  | Elexon to produce Settlement Calendar for Settlement Year 2025/2026 | 0% | Fri 04/04/25 | Fri 04/04/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 | 1930 | 1978,1979FS+176 days | 0 days | 0 days | 0 days | PP | PP, Code Bodies |  |  | 5.15 | Yes | Matthew Breen
4 | 1.9.8.2 |  |  | Elexon monitor settlement data of migrated MPANs | 0% | Mon 07/04/25 | Mon 07/12/26 | 436 days | Mon 07/04/25 | Mon 07/12/26 | 1977 | 1989 | 0 days | 0 days | 0 days | PP | PP, Code Bodies |  |  | 5.15 | Yes | Matthew Breen
4 | 1.9.8.3 |  |  | M16 Checkpoint 1 | 0% | Mon 08/12/25 | Mon 08/12/25 | 0 days | Mon 08/12/25 | Mon 08/12/25 | 1977FS+176 days | 1980FS+20 days | 0 days | 0 days | 0 days | PP | PP, Code Bodies |  |  | 5.15 | Yes | Matthew Breen
4 | 1.9.8.4 |  |  | Confirm if M16 date retained as 07/12/2026 | 0% | Mon 05/01/26 | Mon 05/01/26 | 0 days | Mon 05/01/26 | Mon 05/01/26 | 1979FS+20 days | 1981FS+20 days | 0 days | 0 days | 0 days | CPT | PP |  |  | 5.15 | Yes | Matthew Breen
4 | 1.9.8.5 |  |  | Readiness assessment of participants' readiness to transition to new Settlement Timetable | 0% | Mon 02/02/26 | Mon 02/02/26 | 0 days | Mon 02/02/26 | Mon 02/02/26 | 1980FS+20 days | 1982FS+42 days | 0 days | 0 days | 0 days | CPT | PP |  |  | 5.15 | Yes | Matthew Breen
4 | 1.9.8.6 |  |  | Elexon to produce Settlement Calendar for Settlement Year 2026 up until day before M16 cutover | 0% | Wed 01/04/26 | Wed 01/04/26 | 0 days | Wed 01/04/26 | Wed 01/04/26 | 1981FS+42 days | 1983FS+119 days | 0 days | 0 days | 0 days | PP | PP, Code Bodies |  |  | 5.15 | Yes | Matthew Breen
4 | 1.9.8.7 |  |  | M16 Checkpoint 2 | 0% | Tue 15/09/26 | Tue 15/09/26 | 0 days | Tue 15/09/26 | Tue 15/09/26 | 1982FS+119 days | 1984FS+11 days | 0 days | 0 days | 0 days | PP | PP, Code Bodies |  |  | 5.15 | Yes | Matthew Breen
4 | 1.9.8.8 |  |  | Readiness assessment of participants' readiness to transition to new Settlement Timetable | 0% | Wed 30/09/26 | Wed 30/09/26 | 0 days | Wed 30/09/26 | Wed 30/09/26 | 1983FS+11 days | 1985FS+9 days | 0 days | 0 days | 0 days | CPT | PP |  |  | 5.15 | Yes | Matthew Breen
4 | 1.9.8.9 | T2-EL-0100 | PSG/BSC PAB | Confirm M16 Date | 0% | Tue 13/10/26 | Tue 13/10/26 | 0 days | Tue 13/10/26 | Tue 13/10/26 | 1984FS+9 days | 1988FS+39 days,1986 | 1 day | 0 days | -1 day | CPT | Code Bodies,CPT,PP,SRO |  |  | 5.3 | Yes | Matthew Breen
4 | 1.9.8.10 |  |  | Raise fast track change to ISD (November publish) | 0% | Tue 13/10/26 | Tue 13/10/26 | 0 days | Tue 13/10/26 | Tue 13/10/26 | 1985 | 1989 | 0 days | 0 days | 0 days | PP | PP,CPT,Code Bodies |  |  | 5.15 | Yes | Matthew Breen
4 | 1.9.8.11 |  |  | M16 Approval Window | 0% | Mon 07/12/26 | Fri 28/05/27 | 124 days | Mon 07/12/26 | Fri 28/05/27 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.9.8.11.1 |  |  | Panel approval that M16 criteria met | 0% | Mon 07/12/26 | Mon 07/12/26 | 0 days | Mon 07/12/26 | Mon 07/12/26 | 1985FS+39 days | 1989 | 0 days | 0 days | 0 days | Panel | Code Bodies,CPT,PP,SRO |  |  | 5 | Yes | Matthew Breen
5 | 1.9.8.11.2 | T1-EL-1000 | PSG | Cut over to new settlement timetable (M16) | 0% | Mon 07/12/26 | Mon 07/12/26 | 0 days | Mon 07/12/26 | Mon 07/12/26 | 1988,1936FS+45 days,1978,1986 | 1990,2085,2062FS-50 days,2003FS-45 days,2099FS-3 mons,2031FF-5 days | 0 days | 0 days | 0 days | CPT | PP |  |  | 5 | Yes | Matthew Breen
5 | 1.9.8.11.3 |  |  | Maximum 6-month window for approval of M16 | 0% | Tue 08/12/26 | Fri 28/05/27 | 124 days | Tue 08/12/26 | Fri 28/05/27 | 1989 | 1991 | 0 days | 0 days | 0 days | CPT |  |  |  | 5 | Yes | Matthew Breen
5 | 1.9.8.11.4 | T1-EL-2000 | PSG | Cut over to new settlement timetable (M16*) - Late Exit | 0% | Fri 28/05/27 | Fri 28/05/27 | 0 days | Fri 28/05/27 | Fri 28/05/27 | 1990 |  | 0 days | 0 days | 0 days | CPT | PP |  |  | 5 | Yes | Matthew Breen
2 | 1.1 |  |  | EARLY LIVE RUNNING | 0% | Tue 06/10/26 | Mon 07/12/26 | 45 days | Tue 02/01/24 | Fri 28/05/27 |  |  | 720 days | -124 days | -844 days | N/A | N/A |  |  |  | Yes | N/A
3 | 1.10.1 |  |  | Early Live Running Stabilisation Period | 0% | Tue 06/10/26 | Mon 07/12/26 | 45 days | Tue 06/10/26 | Mon 07/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.10.1.1 |  |  | Manage Early Live Running stabilisation period | 0% | Tue 06/10/26 | Mon 07/12/26 | 45 days | Tue 06/10/26 | Mon 07/12/26 | 1936 | 1995SS | 0 days | 0 days | 0 days | Code Bodies | PP |  |  | 5 | Yes | Matthew Breen
4 | 1.10.1.2 |  |  | Monitor Early Live Running stabilisation period | 0% | Tue 06/10/26 | Mon 07/12/26 | 45 days | Tue 06/10/26 | Mon 07/12/26 | 1994SS |  | 0 days | 0 days | 0 days | SI Migration | Code Bodies,PP |  |  | 5 | Yes | Matthew Breen
2 | 1.11 |  |  | PROGRAMME CLOSURE | 0% | Tue 04/08/26 | Mon 30/11/26 | 85 days | Tue 04/08/26 | Mon 30/11/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  |  | Yes | N/A
3 | 1.11.1 |  |  | Handover Pack | 0% | Tue 04/08/26 | Mon 30/11/26 | 85 days | Tue 04/08/26 | Mon 30/11/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.11.1.1 |  |  | Draft Handover Pack (for M15) | 0% | Tue 04/08/26 | Mon 28/09/26 | 40 days | Tue 04/08/26 | Mon 28/09/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.11.1.1.1 |  |  | Develop document | 0% | Tue 04/08/26 | Mon 31/08/26 | 20 days | Tue 04/08/26 | Mon 31/08/26 | 1936FS-45 days | 2000 | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes
5 | 1.11.1.1.2 |  |  | Document review and update | 0% | Tue 01/09/26 | Mon 28/09/26 | 20 days | Tue 01/09/26 | Mon 28/09/26 | 1999 | 2001 | 0 days | 0 days | 0 days | SRO | PMO,CPT,IPA,PP |  |  | 5 | Yes
5 | 1.11.1.1.3 |  |  | Draft Handover Pack approved | 0% | Mon 28/09/26 | Mon 28/09/26 | 0 days | Mon 28/09/26 | Mon 28/09/26 | 2000 |  | 0 days | 0 days | 0 days | SRO | PMO,CPT |  |  | 5 | Yes
4 | 1.11.1.2 |  |  | Master Handover Pack (for M16) | 0% | Tue 06/10/26 | Mon 30/11/26 | 40 days | Tue 06/10/26 | Mon 30/11/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
5 | 1.11.1.2.1 |  |  | Update document | 0% | Tue 06/10/26 | Mon 02/11/26 | 20 days | Tue 06/10/26 | Mon 02/11/26 | 1989FS-45 days | 2004 | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes
5 | 1.11.1.2.2 |  |  | Document review and update | 0% | Tue 03/11/26 | Mon 30/11/26 | 20 days | Tue 03/11/26 | Mon 30/11/26 | 2003 | 2005 | 0 days | 0 days | 0 days | SRO | PMO,CPT,IPA,PP |  |  | 5 | Yes
5 | 1.11.1.2.3 |  |  | Master Handover Pack approved | 0% | Mon 30/11/26 | Mon 30/11/26 | 0 days | Mon 30/11/26 | Mon 30/11/26 | 2004 |  | 0 days | 0 days | 0 days | SRO | PMO,CPT |  |  | 5 | Yes
3 | 1.11.2 |  |  | Programme Lessons Learned | 0% | Tue 04/08/26 | Mon 28/09/26 | 40 days | Tue 04/08/26 | Mon 28/09/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.11.2.1 |  |  | Develop document | 0% | Tue 04/08/26 | Mon 31/08/26 | 20 days | Tue 04/08/26 | Mon 31/08/26 | 1936FS-45 days | 2008 | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes
4 | 1.11.2.2 |  |  | Document review and update | 0% | Tue 01/09/26 | Mon 28/09/26 | 20 days | Tue 01/09/26 | Mon 28/09/26 | 2007 | 2009 | 0 days | 0 days | 0 days | SRO | PMO,CPT,IPA |  |  | 5 | Yes
4 | 1.11.2.3 |  |  | Programme Lessons Learned document approved | 0% | Mon 28/09/26 | Mon 28/09/26 | 0 days | Mon 28/09/26 | Mon 28/09/26 | 2008 |  | 0 days | 0 days | 0 days | SRO | PMO,CPT |  |  | 5 | Yes
3 | 1.11.3 |  |  | Programme Closure Report | 0% | Tue 04/08/26 | Mon 28/09/26 | 40 days | Tue 04/08/26 | Mon 28/09/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.11.3.1 |  |  | Develop document | 0% | Tue 04/08/26 | Mon 31/08/26 | 20 days | Tue 04/08/26 | Mon 31/08/26 | 1936FS-45 days | 2012 | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes
4 | 1.11.3.2 |  |  | Document review and update | 0% | Tue 01/09/26 | Mon 28/09/26 | 20 days | Tue 01/09/26 | Mon 28/09/26 | 2011 | 2013 | 0 days | 0 days | 0 days | Ofgem | PMO,CPT,IPA,SRO |  |  | 5 | Yes
4 | 1.11.3.3 |  |  | Programme Closure Report approved | 0% | Mon 28/09/26 | Mon 28/09/26 | 0 days | Mon 28/09/26 | Mon 28/09/26 | 2012 |  | 0 days | 0 days | 0 days | Ofgem | PMO,CPT,IPA,SRO |  |  | 5 | Yes
3 | 1.11.4 |  |  | Benefit Realisation Report | 0% | Tue 04/08/26 | Mon 05/10/26 | 45 days | Tue 04/08/26 | Mon 05/10/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.11.4.1 |  |  | Develop document | 0% | Tue 04/08/26 | Mon 31/08/26 | 20 days | Tue 04/08/26 | Mon 31/08/26 | 1936FS-45 days | 2016 | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes
4 | 1.11.4.2 |  |  | Document review and update | 0% | Tue 01/09/26 | Mon 28/09/26 | 20 days | Tue 01/09/26 | Mon 28/09/26 | 2015 | 2017FS+5 days | 0 days | 0 days | 0 days | PP | PMO,CPT,IPA,SRO |  |  | 5 | Yes
4 | 1.11.4.3 | T3-PC-0010 | PSG | Benefit Realisation Report approved | 0% | Mon 05/10/26 | Mon 05/10/26 | 0 days | Mon 05/10/26 | Mon 05/10/26 | 2016FS+5 days |  | 0 days | 0 days | 0 days | PMO | CPT,PP,IPA,SRO |  |  | 5 | Yes
3 | 1.11.5 |  |  | Operating Model Gap Review with recommendations | 0% | Tue 04/08/26 | Mon 05/10/26 | 45 days | Tue 04/08/26 | Mon 05/10/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.11.5.1 |  |  | Develop document | 0% | Tue 04/08/26 | Mon 31/08/26 | 20 days | Tue 04/08/26 | Mon 31/08/26 | 1936FS-45 days | 2020 | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes
4 | 1.11.5.2 |  |  | Document review and update | 0% | Tue 01/09/26 | Mon 28/09/26 | 20 days | Tue 01/09/26 | Mon 28/09/26 | 2019 | 2021FS+5 days | 0 days | 0 days | 0 days | PP | PMO,CPT,IPA,SRO |  |  | 5 | Yes
4 | 1.11.5.3 | T3-PC-0020 | DAG | Operating Model Gap Review with recommendations approved | 0% | Mon 05/10/26 | Mon 05/10/26 | 0 days | Mon 05/10/26 | Mon 05/10/26 | 2020FS+5 days |  | 0 days | 0 days | 0 days | Paul Pettitt | CPT,PP,IPA,SRO |  |  | 5 | Yes | Paul Pettitt
3 | 1.11.6 |  |  | Post-Implementation Review | 0% | Tue 04/08/26 | Mon 05/10/26 | 45 days | Tue 04/08/26 | Mon 05/10/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.11.6.1 |  |  | Develop document | 0% | Tue 04/08/26 | Mon 31/08/26 | 20 days | Tue 04/08/26 | Mon 31/08/26 | 1936FS-45 days | 2024 | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes
4 | 1.11.6.2 |  |  | Document review and update | 0% | Tue 01/09/26 | Mon 28/09/26 | 20 days | Tue 01/09/26 | Mon 28/09/26 | 2023 | 2025FS+5 days | 0 days | 0 days | 0 days | PP | PMO,CPT,IPA,SRO |  |  | 5 | Yes
4 | 1.11.6.3 | T3-PC-0030 | PSG | Post-Implementation Review approved | 0% | Mon 05/10/26 | Mon 05/10/26 | 0 days | Mon 05/10/26 | Mon 05/10/26 | 2024FS+5 days |  | 0 days | 0 days | 0 days | PMO | CPT,PP,IPA,SRO |  |  | 5 | Yes
3 | 1.11.7 |  |  | Reinforcement Guide | 0% | Tue 04/08/26 | Mon 05/10/26 | 45 days | Tue 04/08/26 | Mon 05/10/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.11.7.1 |  |  | Develop document | 0% | Tue 04/08/26 | Mon 31/08/26 | 20 days | Tue 04/08/26 | Mon 31/08/26 | 1936FS-45 days | 2028 | 0 days | 0 days | 0 days | PMO | CPT |  |  | 5 | Yes
4 | 1.11.7.2 |  |  | Document review and update | 0% | Tue 01/09/26 | Mon 28/09/26 | 20 days | Tue 01/09/26 | Mon 28/09/26 | 2027 | 2029FS+5 days | 0 days | 0 days | 0 days | PP | PMO,CPT,IPA,SRO |  |  | 5 | Yes
4 | 1.11.7.3 | T3-PC-0040 | PSG | Reinforcement Guide approved | 0% | Mon 05/10/26 | Mon 05/10/26 | 0 days | Mon 05/10/26 | Mon 05/10/26 | 2028FS+5 days |  | 0 days | 0 days | 0 days | PMO | CPT,PP,IPA,SRO |  |  | 5 | Yes
3 | 1.11.8 |  |  | Material and Licenses Transfer | 0% | Tue 08/09/26 | Mon 30/11/26 | 60 days | Tue 08/09/26 | Mon 30/11/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.11.8.1 |  |  | Transfer of Programme material to Elexon and perpetual licenses as appropriate | 0% | Tue 08/09/26 | Mon 30/11/26 | 60 days | Tue 08/09/26 | Mon 30/11/26 | 1989FF-5 days |  | 0 days | 0 days | 0 days | PMO | CPT,PP |  |  | 5 | Yes
2 | 1.12 |  |  | READINESS ASSESSMENTS | 23% | Tue 05/09/23 | Fri 04/12/26 | 849 days | Tue 05/09/23 | Fri 04/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  |  | Yes | N/A
3 | 1.12.1 |  |  | Readiness Assessment 3 - Design and Build Progress Check and CP2 Check | 100% | Tue 05/09/23 | Mon 27/11/23 | 60 days | Tue 05/09/23 | Mon 13/11/23 |  |  | 0 days | 10 days | 10 days | N/A | N/A |  |  | 5.5 | Yes | N/A
4 | 1.12.1.1 |  |  | Launch Readiness Assessment survey | 100% | Tue 05/09/23 | Tue 05/09/23 | 0 days | Tue 05/09/23 | Tue 05/09/23 | 1004FS-40 days | 2035 | 0 days | 0 days | 0 days | PPC |  |  |  | 5.5 | Yes | PPC
4 | 1.12.1.2 |  |  | PPs submit survey responses | 100% | Tue 05/09/23 | Mon 25/09/23 | 15 days | Tue 05/09/23 | Mon 25/09/23 | 2034 | 20362037 | 0 days | 0 days | 0 days | PP | PPC |  |  | 5.5 | Yes | PPC
4 | 1.12.1.3 |  |  | Analyse survey responses | 100% | Tue 26/09/23 | Mon 16/10/23 | 15 days | Tue 26/09/23 | Mon 16/10/23 | 2035 | 2038 | 0 days | 0 days | 0 days | PPC | CPT |  |  | 5.5 | Yes | PPC
4 | 1.12.1.4 |  |  | Conduct deep-dive interviews (sample of PPs) | 100% | Tue 26/09/23 | Mon 16/10/23 | 15 days | Tue 26/09/23 | Mon 16/10/23 | 2035 | 2038 | 0 days | 0 days | 0 days | PPC | CPT |  |  | 5.5 | Yes | PPC
4 | 1.12.1.5 |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 100% | Tue 17/10/23 | Mon 20/11/23 | 25 days | Tue 17/10/23 | Mon 06/11/23 | 20362037 | 2039FS+5 days | 0 days | 10 days | 10 days | PPC |  |  |  | 5.5 | Yes | PPC
4 | 1.12.1.6 | T2-RA-0200 | PSG | Readiness Assessment 3 - Design & Build Checkpoint 1 - Completed (incl. Readiness Assessment Report approval) | 100% | Mon 27/11/23 | Mon 27/11/23 | 0 days | Mon 13/11/23 | Mon 13/11/23 | 2038FS+5 days |  | 10 days | 10 days | 0 days | CPT | PPC |  |  | 5.13 | Yes | PPC
3 | 1.12.2 |  |  | Readiness Assessment 5 / 6 - Start of Qualification and Participant Readiness for M10 and M11 and CP3/CP4 check | 0% | Tue 12/11/24 | Wed 15/01/25 | 47 days | Tue 12/11/24 | Fri 17/01/25 |  |  | 0 days | -2 days | -2 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.12.2.1 |  |  | Launch Readiness Assessment survey | 0% | Tue 12/11/24 | Tue 12/11/24 | 0 days | Tue 12/11/24 | Tue 12/11/24 | 1569FS-50 days | 2042 | 0 days | 0 days | 0 days | PPC |  |  |  | 5 | Yes | PPC
4 | 1.12.2.2 |  |  | PPs submit survey responses | 0% | Tue 12/11/24 | Mon 02/12/24 | 15 days | Tue 12/11/24 | Mon 02/12/24 | 2041 | 20432044 | 0 days | 0 days | 0 days | PP | PPC |  |  | 5 | Yes | PPC
4 | 1.12.2.3 |  |  | Analyse survey responses | 0% | Tue 03/12/24 | Mon 23/12/24 | 15 days | Tue 03/12/24 | Mon 23/12/24 | 2042 | 2045 | 0 days | 0 days | 0 days | PPC | CPT |  |  | 5 | Yes | PPC
4 | 1.12.2.4 |  |  | Conduct deep-dive interviews (sample of PPs) | 0% | Tue 03/12/24 | Mon 23/12/24 | 15 days | Tue 03/12/24 | Mon 23/12/24 | 2042 | 2045 | 0 days | 0 days | 0 days | PPC | CPT |  |  | 5 | Yes | PPC
4 | 1.12.2.5 |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 0% | Tue 24/12/24 | Mon 13/01/25 | 15 days | Tue 24/12/24 | Mon 13/01/25 | 20432044 | 2046FS+2 days | 0 days | 0 days | 0 days | PPC |  |  |  | 5 | Yes | PPC
4 | 1.12.2.6 | T2-RA-0400 | PSG | Readiness Assessment 5 / 6 - Start of Qualification and Participant Readiness for M10 and M11 and CP3/CP4 check (incl. Readiness Assessment Report approval) Completed | 0% | Wed 15/01/25 | Wed 15/01/25 | 0 days | Fri 17/01/25 | Fri 17/01/25 | 2045FS+2 days |  | -2 days | -2 days | 0 days | CPT | PPC |  |  | 5.18 | Yes | PPC
3 | 1.12.3 |  |  | Readiness Assessment 7 - Migration Checkpoint | 0% | Mon 04/08/25 | Thu 09/10/25 | 49 days | Mon 04/08/25 | Thu 09/10/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.12.3.1 |  |  | Launch Readiness Assessment survey | 0% | Mon 04/08/25 | Mon 04/08/25 | 0 days | Mon 04/08/25 | Mon 04/08/25 |  | 2049 | 0 days | 0 days | 0 days | PPC |  |  |  | 5 | Yes | PPC
4 | 1.12.3.2 |  |  | PPs submit survey responses | 0% | Mon 04/08/25 | Fri 22/08/25 | 15 days | Mon 04/08/25 | Fri 22/08/25 | 2048 | 20502051 | 0 days | 0 days | 0 days | PP | PPC |  |  | 5 | Yes | PPC
4 | 1.12.3.3 |  |  | Analyse survey responses | 0% | Mon 25/08/25 | Fri 12/09/25 | 15 days | Mon 25/08/25 | Fri 12/09/25 | 2049 | 2052 | 0 days | 0 days | 0 days | PPC | CPT |  |  | 5 | Yes | PPC
4 | 1.12.3.4 |  |  | Conduct deep-dive interviews (sample of PPs) | 0% | Mon 25/08/25 | Fri 12/09/25 | 15 days | Mon 25/08/25 | Fri 12/09/25 | 2049 | 2052 | 0 days | 0 days | 0 days | PPC | CPT |  |  | 5 | Yes | PPC
4 | 1.12.3.5 |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 0% | Mon 15/09/25 | Fri 03/10/25 | 15 days | Mon 15/09/25 | Fri 03/10/25 | 20502051 | 2053FS+4 days,2070FS+4 days | 0 days | 0 days | 0 days | PPC |  |  |  | 5 | Yes | PPC
4 | 1.12.3.6 | T2-RA-0600 | PSG | Readiness Assessment 7 - Migration Checkpoint - Completed (incl. Readiness Assessment Report approval) | 0% | Thu 09/10/25 | Thu 09/10/25 | 0 days | Thu 09/10/25 | Thu 09/10/25 | 2052FS+4 days |  | 0 days | 0 days | 0 days | CPT | PPC |  |  | 5 | Yes | PPC
3 | 1.12.4 |  |  | Readiness Assessment 8 - Ready to Accept New MPANs | 0% | Fri 02/01/26 | Wed 11/03/26 | 49 days | Tue 06/01/26 | Fri 13/03/26 |  |  | -2 days | -2 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.12.4.1 |  |  | Launch Readiness Assessment survey | 0% | Fri 02/01/26 | Fri 02/01/26 | 0 days | Tue 06/01/26 | Tue 06/01/26 | 1934FS-50 days | 2056 | -2 days | -2 days | 0 days | PPC |  |  |  | 5 | Yes | PPC
4 | 1.12.4.2 |  |  | PPs submit survey responses | 0% | Fri 02/01/26 | Thu 22/01/26 | 15 days | Tue 06/01/26 | Mon 26/01/26 | 2055 | 20572058 | -2 days | -2 days | 0 days | PP | PPC |  |  | 5 | Yes | PPC
4 | 1.12.4.3 |  |  | Analyse survey responses | 0% | Fri 23/01/26 | Thu 12/02/26 | 15 days | Tue 27/01/26 | Mon 16/02/26 | 2056 | 2059 | -2 days | -2 days | 0 days | PPC | CPT |  |  | 5 | Yes | PPC
4 | 1.12.4.4 |  |  | Conduct deep-dive interviews (sample of PPs) | 0% | Fri 23/01/26 | Thu 12/02/26 | 15 days | Tue 27/01/26 | Mon 16/02/26 | 2056 | 2059 | -2 days | -2 days | 0 days | PPC | CPT |  |  | 5 | Yes | PPC
4 | 1.12.4.5 |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 0% | Fri 13/02/26 | Thu 05/03/26 | 15 days | Tue 17/02/26 | Mon 09/03/26 | 20572058 | 2060FS+4 days,2071FS+4 days | -2 days | -2 days | 0 days | PPC |  |  |  | 5 | Yes | PPC
4 | 1.12.4.6 | T2-RA-0700 | PSG | Readiness Assessment 8 - Ready to Accept New MPANs - Completed (incl. Readiness Assessment Report approval) | 0% | Wed 11/03/26 | Wed 11/03/26 | 0 days | Fri 13/03/26 | Fri 13/03/26 | 2059FS+4 days |  | -2 days | -2 days | 0 days | CPT | PPC |  |  | 5 | Yes | PPC
3 | 1.12.5 |  |  | Readiness Assessment 9 - Ready for New Settlement Timetable and CP5 Check | 0% | Tue 29/09/26 | Fri 04/12/26 | 49 days | Tue 29/09/26 | Fri 04/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.12.5.1 |  |  | Launch Readiness Assessment survey | 0% | Tue 29/09/26 | Tue 29/09/26 | 0 days | Tue 29/09/26 | Tue 29/09/26 | 1989FS-50 days | 2063 | 0 days | 0 days | 0 days | PPC |  |  |  | 5 | Yes | PPC
4 | 1.12.5.2 |  |  | PPs submit survey responses | 0% | Tue 29/09/26 | Mon 19/10/26 | 15 days | Tue 29/09/26 | Mon 19/10/26 | 2062 | 20642065 | 0 days | 0 days | 0 days | PP | PPC |  |  | 5 | Yes | PPC
4 | 1.12.5.3 |  |  | Analyse survey responses | 0% | Tue 20/10/26 | Mon 09/11/26 | 15 days | Tue 20/10/26 | Mon 09/11/26 | 2063 | 2066 | 0 days | 0 days | 0 days | PPC | CPT |  |  | 5 | Yes | PPC
4 | 1.12.5.4 |  |  | Conduct deep-dive interviews (sample of PPs) | 0% | Tue 20/10/26 | Mon 09/11/26 | 15 days | Tue 20/10/26 | Mon 09/11/26 | 2063 | 2066 | 0 days | 0 days | 0 days | PPC | CPT |  |  | 5 | Yes | PPC
4 | 1.12.5.5 |  |  | Produce Readiness Assessment Reports (Overall Report & Individual Participant Reports) | 0% | Tue 10/11/26 | Mon 30/11/26 | 15 days | Tue 10/11/26 | Mon 30/11/26 | 20642065 | 2067FS+4 days,2072FS+4 days | 0 days | 0 days | 0 days | PPC |  |  |  | 5 | Yes | PPC
4 | 1.12.5.6 | T2-RA-0800 | PSG | Readiness Assessment 9 - Readiness for New Settlement Timetable - Completed (incl. Readiness Assessment Report approval) | 0% | Fri 04/12/26 | Fri 04/12/26 | 0 days | Fri 04/12/26 | Fri 04/12/26 | 2066FS+4 days |  | 0 days | 0 days | 0 days | CPT | PPC |  |  | 5 | Yes | PPC
3 | 1.12.6 |  |  | Readiness Assessments - Tier 1 Milestones | 0% | Fri 04/04/25 | Fri 04/12/26 | 435 days | Mon 13/11/23 | Fri 04/12/26 |  |  | 364 days | 0 days | -364 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.12.6.1 | T2-RA-0500 | PSG | Readiness Assessment 6 - Start of Migration - Completed (incl. Readiness Assessment Report approval) | 0% | Fri 04/04/25 | Fri 04/04/25 | 0 days | Fri 04/04/25 | Fri 04/04/25 |  |  | 0 days | 0 days | 0 days | CPT | PPC |  |  | 5 | Yes | PPC
4 | 1.12.6.2 | T2-RA-0600 | PSG | Readiness Assessment 7 - Migration Checkpoint - Completed (incl. Readiness Assessment Report approval) | 0% | Thu 09/10/25 | Thu 09/10/25 | 0 days | Thu 09/10/25 | Thu 09/10/25 | 2052FS+4 days |  | 0 days | 0 days | 0 days | CPT | PPC |  |  | 5 | Yes | PPC
4 | 1.12.6.3 | T2-RA-0700 | PSG | Readiness Assessment 8 - Ready to Accept New MPANs - Completed (incl. Readiness Assessment Report approval) | 0% | Wed 11/03/26 | Wed 11/03/26 | 0 days | Fri 13/03/26 | Fri 13/03/26 | 2059FS+4 days |  | -2 days | -2 days | 0 days | CPT | PPC |  |  | 5 | Yes | PPC
4 | 1.12.6.4 | T2-RA-0800 | PSG | Readiness Assessment 9 - Readiness for New Settlement Timetable - Completed (incl. Readiness Assessment Report approval) | 0% | Fri 04/12/26 | Fri 04/12/26 | 0 days | Fri 04/12/26 | Fri 04/12/26 | 2066FS+4 days |  | 0 days | 0 days | 0 days | CPT | PPC |  |  | 5 | Yes | PPC
2 | 1.13 |  |  | CONTROL POINTS | 51% | Thu 10/11/22 | Mon 07/12/26 | 1063 days | Thu 10/11/22 | Mon 07/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  |  | Yes | N/A
3 | 1.13.1 |  |  | Control Point 1 - Start of System Design, Build & Test | 100% | Thu 10/11/22 | Wed 07/12/22 | 20 days | Thu 10/11/22 | Wed 07/12/22 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.13.1.1 |  |  | Control Point 1 Preparation (incl. Control Point Report development and review) | 100% | Thu 10/11/22 | Wed 30/11/22 | 15 days | Thu 10/11/22 | Wed 30/11/22 | 2076SS-20 days |  | 0 days | 0 days | 0 days | CPT | PMO |  |  | 5 | Yes | PMO
4 | 1.13.1.2 | T1-CP-1000 | PSG | Control Point 1 - Start of System Design, Build & Test (incl. Control Point Report approval) | 100% | Wed 07/12/22 | Wed 07/12/22 | 0 days | Wed 07/12/22 | Wed 07/12/22 |  | 2075SS-20 days,2087SS | 0 days | 0 days | 0 days | CPT | PMO |  |  | 5 | Yes | PMO
3 | 1.13.2 |  |  | Control Point 2 - Start of Integration & Test | 100% | Mon 02/10/23 | Mon 30/10/23 | 20 days | Tue 03/10/23 | Mon 30/10/23 |  |  | -1 day | -1 day | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.13.2.1 |  |  | Control Point 2 Preparation (incl. Control Point Report development and review) | 100% | Mon 02/10/23 | Fri 20/10/23 | 15 days | Tue 03/10/23 | Mon 23/10/23 | 2079SS-20 days |  | -1 day | -1 day | 0 days | CPT | PMO |  |  | 5 | Yes | PMO
4 | 1.13.2.2 | T1-CP-2000 | PSG | Control Point 2 - Start of Integration & Test (incl. Control Point Report approval) | 100% | Mon 30/10/23 | Mon 30/10/23 | 0 days | Mon 30/10/23 | Mon 30/10/23 | 1004 | 2088SS,2078SS-20 days | -1 day | -1 day | 0 days | CPT | PMO |  |  | 5.11 | Yes | PMO
3 | 1.13.3 |  |  | Control Point 3/4 - Readiness for Migration | 0% | Fri 28/02/25 | Thu 27/03/25 | 20 days | Mon 03/03/25 | Fri 28/03/25 |  |  | -1 day | -1 day | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.13.3.1 |  |  | Control Point 3/4 Preparation (incl. Control Point Report development and review) | 0% | Fri 28/02/25 | Wed 19/03/25 | 14 days | Mon 03/03/25 | Thu 20/03/25 | 2082SS-20 days |  | -1 day | -1 day | 0 days | CPT | PMO |  |  | 5 | Yes | PMO
4 | 1.13.3.2 | T1-CP-3000 | PSG | Control Point 3/4 - Readiness for Migration (incl. Control Point Report approval) | 0% | Thu 27/03/25 | Thu 27/03/25 | 0 days | Fri 28/03/25 | Fri 28/03/25 | 1611FS+9 days | 2089SS,2081SS-20 days | -1 day | -1 day | 0 days | CPT | PMO |  |  | 5 | Yes | PMO
3 | 1.13.4 |  |  | Control Point 5 - Cut Over to New Settlement Timetable | 0% | Tue 10/11/26 | Mon 07/12/26 | 20 days | Tue 10/11/26 | Mon 07/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.13.4.1 |  |  | Control Point 5 Preparation (incl. Control Point Report development and review) | 0% | Tue 10/11/26 | Mon 30/11/26 | 15 days | Tue 10/11/26 | Mon 30/11/26 | 2085SS-20 days |  | 0 days | 0 days | 0 days | CPT | PP |  |  | 5 | Yes | PMO
4 | 1.13.4.2 | T1-CP-4000 | PSG | Control Point 5 - Cut Over to New Settlement Timetable (incl. Control Point Report approval) | 0% | Mon 07/12/26 | Mon 07/12/26 | 0 days | Mon 07/12/26 | Mon 07/12/26 | 1989 | 2090SS,2084SS-20 days | 0 days | 0 days | 0 days | CPT | CPT |  |  | 5 | Yes | PMO
3 | 1.13.5 |  |  | Control Points - Tier 1 Milestones | 0% | Wed 07/12/22 | Mon 07/12/26 | 1043 days | Wed 07/12/22 | Mon 07/12/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.13.5.1 | T1-CP-1000 | PSG | Control Point 1 - Start of System Design, Build & Test (incl. Control Point Report approval) | 100% | Wed 07/12/22 | Wed 07/12/22 | 0 days | Wed 07/12/22 | Wed 07/12/22 | 2076SS |  | 0 days | 0 days | 0 days | CPT | PMO |  |  | 5 | Yes | PMO
4 | 1.13.5.2 | T1-CP-2000 | PSG | Control Point 2 - Start of Integration & Test (incl. Control Point Report approval) | 100% | Mon 30/10/23 | Mon 30/10/23 | 0 days | Mon 30/10/23 | Mon 30/10/23 | 2079SS |  | -1 day | -1 day | 0 days | CPT | PMO |  |  | 5.11 | Yes | PMO
4 | 1.13.5.3 | T1-CP-3000 | PSG | Control Point 3/4 - Readiness for Migration (incl. Control Point Report approval) | 0% | Thu 27/03/25 | Thu 27/03/25 | 0 days | Fri 28/03/25 | Fri 28/03/25 | 2082SS |  | -1 day | -1 day | 0 days | CPT | PMO |  |  | 5 | Yes | PMO
4 | 1.13.5.4 | T1-CP-4000 | PSG | Control Point 5 - Cut Over to New Settlement Timetable (incl. Control Point Report approval) | 0% | Mon 07/12/26 | Mon 07/12/26 | 0 days | Mon 07/12/26 | Mon 07/12/26 | 2085SS |  | 0 days | 0 days | 0 days | CPT | CPT |  |  | 5 | Yes | PMO
2 | 1.14 |  |  | MILESTONE RANGE CHECKPOINTS | 0% | Mon 13/01/25 | Tue 15/09/26 | 436 days | Mon 13/01/25 | Tue 15/09/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  |  | Yes | N/A
3 | 1.14.1 |  |  | M10, M11, M12 and M13 milestone checkpoint | 0% | Mon 13/01/25 | Mon 13/01/25 | 0 days | Mon 13/01/25 | Mon 13/01/25 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.14.1.1 | T2-MR-0100 | PSG | M10, M11, M12, and M13 milestone checkpoint - date approval | 0% | Mon 13/01/25 | Mon 13/01/25 | 0 days | Mon 13/01/25 | Mon 13/01/25 | 1926FS-3 mons,1930FS-3 mons,1932FS-3 mons,1928FS-3 mons |  | 0 days | 0 days | 0 days | CPT | CPT |  |  | 5 | Yes | PMO
3 | 1.14.2 |  |  | M14 milestone checkpoint | 0% | Fri 19/12/25 | Fri 19/12/25 | 0 days | Tue 23/12/25 | Tue 23/12/25 |  |  | -2 days | -2 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.14.2.1 | T2-MR-0200 | PSG | M14 milestone checkpoint - date approval | 0% | Fri 19/12/25 | Fri 19/12/25 | 0 days | Tue 23/12/25 | Tue 23/12/25 | 1934FS-3 mons |  | -2 days | -2 days | 0 days | CPT | CPT |  |  | 5 | Yes | PMO
3 | 1.14.3 |  |  | M15 milestone checkpoint | 0% | Tue 14/07/26 | Tue 14/07/26 | 0 days | Tue 14/07/26 | Tue 14/07/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.14.3.1 | T2-MR-0300 | PSG | M15 milestone checkpoint - date approval | 0% | Tue 14/07/26 | Tue 14/07/26 | 0 days | Tue 14/07/26 | Tue 14/07/26 | 1936FS-3 mons |  | 0 days | 0 days | 0 days | CPT | CPT |  |  | 5 | Yes | PMO
3 | 1.14.4 |  |  | M16 milestone checkpoint | 0% | Tue 15/09/26 | Tue 15/09/26 | 0 days | Tue 15/09/26 | Tue 15/09/26 |  |  | 0 days | 0 days | 0 days | N/A | N/A |  |  | 5 | Yes | N/A
4 | 1.14.4.1 | T2-MR-0400 | PSG | M16 milestone checkpoint - date approval | 0% | Tue 15/09/26 | Tue 15/09/26 | 0 days | Tue 15/09/26 | Tue 15/09/26 | 1989FS-3 mons |  | 0 days | 0 days | 0 days | CPT | CPT |  |  | 5 | Yes | PMO