## Cover Page
<organisation> PIT <stage> Test Execution Progress Report
Document owner | Document number | Version
<name or role> |  | <version number>
Status: | Date | Classification
<status> | <date> | Internal

## Instructions
Instructions
The PIT Test Execution Progress Report will be generated by Programme participants based on their test execution results. Programme participants can use this template as a guideline and will be required to populate the fields in this report based on the execution status. Programme participants will need to either create manual tables or link their testing/defect management tool to provide the actual stats. Programme participants can also use their own testing tools to generate PIT Test Execution Progress Report. Programme participants can submit Test Execution Progress Report using a 'pdf' version.
Column Name | Description of the data in each of the columns of <stage> Execution report worksheet
Programme Participant Name | This is the Programme participant name.
Report Date | This is the report date.
Phase | This is the phase for the report being sent e.g. PIT.
Overall RAG Status | Programme participant to provide the RAG status and reasoning.
Planned Dates | This is the baseline start, base line end, actual start and projected end date for PIT stage under test.
Headlines | In this section, any key highlights for overall testing are covered.
Key Issues | In this section, any key issues within the test phases are raised. Programme participants can provide any further details in the comments section.
Testing Progress and Defects | In this section, Programme participants can provide the testing updates. Programme participants can demonstrate using pie charts the overall testing summary, overall defect summary, open defects by priority and open defects by test severity
Burndown | In this section, Programme participants can provide a burndown graph for target, executed (passed & failed), passed and revised target.
Detailed Progress View | In this section, Programme participants can provide the detailed progress view for each PIT test stage based on functional areas etc.
Risk, Assumptions, Issue and Dependency Status | In this section, Programme participants can provide details on any Risks, Assumptions, Issues and Dependencies.
Guidance notes: Use of this template is OPTIONAL when creating their own PIT Test Execution Progress Report. Programme participants can use their own templates for PIT Test Execution Progress Report, however the content covered in this document should be included as a minimum for PIT phase including Functional, Migration, Non-functional and Operational testing. Guidance will be provided in each section of this template and is intended to demonstrate how the information will be laid out. Programme participants are expected to complete these sections as a minimum. Programme participants could expand upon this document by inserting any additional information that supports their PIT activities. Programme participants can also add any additional sections as they feel appropriate. Red text indicates guidelines or examples.

## <stage> Execution Report
|  |  | PIT <stage> Test Execution Progress Report | [19 empty] | Programme Participant Logo
Programme Participant Name |  |  |  |  | Programme Participant X | [9 empty] | Planned Dates
| Report Date |  |  | Phase |  | Overall RAG Status | [8 empty] | Description |  |  | Baseline Start |  | Actual Start |  | Baseline End |  | Projected End
2023-04-06 |  |  |  | PIT |  | GREEN |  |  | Provide reason for Red/Amber/Green | [5 empty] | <stage> |  |  | 2023-02-06 |  | 2023-02-06 |  | 2023-10-12 |  | 2023-10-08
Headlines
In this section please provide any key highlights, e.g.: Highlight 1 Highlight 2
Key Issues
| Issue ID | Description |  |  | Status |  | Priority |  |  | Assignee |  | Date Raised |  | Comments
|  | Provide details of any test issues/defects | [11 empty] | Provide any further details of issue. Is it an internal issue or external issue? Mitigation.
Testing Progress and Defects
Testing Updates
In this section please provide test execution updates, including plans for upcoming weeks
| Testing Summary | [9 empty] | Defect Summary | [6 empty] | Open Defects by Priority
EMT
Burndown
Detailed Progress View
| Functional Area |  | Passed | In Progress | Failed | Blocked |  | N/A | To Do |  | Total Executed | Total Scripts | Requirements Coverage | Total Executed % | Total Passed % | Total Failed % | Comments
| Change of Supplier/Service |  | 5 | 1 | 5 | 2 |  | 1 | 1 |  | 10 | 15 | 0% | 67% | 34% | 34%
Consumption
ISD
Load Shapes
MDS
Metering Changes
Registration Data
| Totals |  | 5 | 1 | 5 | 2 |  | 1 | 1 |  | 10 | 15 | 0% | 67% | 34% | 34%
Risk, Assumption, Issue and Dependency Status
| RAID Category |  |  | Description | [5 empty] | Impact |  |  | Priority |  | Status |  |  |  | Action On |  | Progress
| Risk |  |  | Risk Description | [5 empty] | Low/Medium/High |  |  | Low/Medium/High |  | Open/Closed..etc |  |  |  | Name 1.. |  | Updates…