## How To Use NEW (hidden)
How To Use
1. How to navigate this document
This section aims to provide an overview on how to navigate through this workbook. It consists of a number of worksheets that are arranged in a heirarchy, working from left to right. The 'List of Test Scenarios' provides an overview view of the scenarios that are included within this phase of testing. Within this worksheet each scenario has a link 'Click to see Test', which when selected, will take the user to a detailed view of the test scenario. This worksheet provides an overview of the test description, mapped requirements and will provide a list of all associated unique test cases. The 'List of Test Cases' gives the user the ability to view a list of test cases in scope and their associated test scenarios. This also includes a view of each attribute that makes up the test case and consists of the following:
Attributes
Meter Type | Trad, Smart, Advanced, Unmetered
Supplier (Outgoing)
Supplier (Incoming)
CSS
Registration Service
DIP
Central Settlement
LDSO
Metering Service
EES
For easy navigation, within each of the main tabs the user will be presented with links to other areas of the workbook. These include 'Click to view Test' and 'Click to view Test Case'. These will direct the user to a detailed view of the test scenario, or will direct them back to the Link of Test Cases worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Detailed Scenarios

## Front Cover (hidden)
SWITCHING PROGRAMME
E2E Test Scenarios
Reference: NCT-0045
Version: v0.3

## Change Control (hidden)
Confidentiality Statement
The information contained herein is for the purpose of the MHHS Programme. This document may not be copied, or communicated to a third party, or used, for any purpose other than that for which it is supplied without the express written consent of the MHHS Programme
Distribution List
Name | Organisation
Document History
Issue No. | Issue Date | Issued by | Change Description
0.1 | 2023-02-10 | Dean Bailey | First Draft & QA Checked
Reviewed By
Version | Date | Name | Title / Responsibility
0.1
Approvals
Version | Date | Name | Title / Responsibility

## Sheet1 (hidden)
(empty)

## Sheet2 (hidden)
Data returned for Distinct Count of Profile, 1 - Dual (First 1000 rows).
ListTestCases[Test Case Category] | ListTestCases[E2E Scenario] | ListTestCases[Test Case Id] | ListTestCases[Test Case Title] | ListTestCases[Domestic] | ListTestCases[Non Domestic] | ListTestCases[Smart] | ListTestCases[Non Smart] | ListTestCases[Associated Test Scenario Id] | ListTestCases[Pre-Requisite Test Case] | ListTestCases[Regression Tests] | ListTestCases[Profile] | ListTestCases[Unique ID]
Switch Request Objection | E2E-D001 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-004-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Objected | X |  |  | X | E2E-004-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters with Primary MPAN) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-004-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Objected |  | X | X |  | E2E-004-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Traditional - Gas, Smart Meter - Electricity)) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X | X | E2E-007-G001 | NA |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  | X | X | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-004-03 | Gaining Supplier - Switch Request for Dual Fuel Domestic (Traditional - Gas, Smart Meter - Electricity) is Objected | X |  | X | X | E2E-004-G001 | E2E-010-03 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-007-04 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-010-04 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-04 |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-004-04 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Objected | X |  |  | X | E2E-004-L001 | E2E-010-04 |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters with Primary MPAN) |  | X | X |  | E2E-010-L001 | E2E-007-05 |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-004-05 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Objected |  | X | X |  | E2E-004-L001 | E2E-010-05 |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Traditional - Gas, Smart Meter - Electricity) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X | X | E2E-007-L001 | NA |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Objection | E2E-D001 | E2E-010-06 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Traditional - Gas, Smart Meter - Electricity) | X |  | X | X | E2E-010-L001 | E2E-007-06 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Objection | E2E-D001 | E2E-004-06 | Losing Supplier - Switch Request for Dual Fuel Domestic (Traditional - Gas, Smart Meter - Electricity) is Objected | X |  | X | X | E2E-004-L001 | E2E-010-06 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Successful | E2E-D002 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-013-01 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-013-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-016-01 | Gaining Supplier - Post Switch Execution for Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-016-G001 | E2E-013-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-013-02 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-013-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-016-02 | Gaining Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-016-G001 | E2E-013-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-G001 | NA |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-013-03 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-013-G001 | E2E-010-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-016-03 | Gaining Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-016-G001 | E2E-013-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-007-04 | Gaining Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-010-04 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-013-04 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-013-G001 | E2E-010-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-016-04 | Gaining Supplier - Post Switch Execution for Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-016-G001 | E2E-013-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-013-05 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-013-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-016-05 | Losing Supplier - Post Switch Execution for Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-016-L001 | E2E-013-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-010-06 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-013-06 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-013-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-016-06 | Losing Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-016-L001 | E2E-013-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-007-07 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-010-07 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-013-07 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-013-L001 | E2E-010-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-016-07 | Losing Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-016-L001 | E2E-013-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-007-08 | Losing Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-010-08 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-L001 | E2E-007-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-013-08 | Losing Supplier - Switch Request Secured Active - Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-013-L001 | E2E-010-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-016-08 | Losing Supplier - Post Switch Execution for Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-016-L001 | E2E-013-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Withdrawal | E2E-D003 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-019-01 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-019-G001 | E2E-10-01 |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-019-02 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-019-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-G001 | NA |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-03 |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-019-03 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Traditional) when status is "Confirmed" in CSS |  | X |  | X | E2E-019-G001 | E2E-010-03 |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-007-04 | Gaining Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-010-04 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-G001 | E2E-007-04 |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-019-04 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Smart Meters) when status is "Confirmed" in CSS | X |  | X |  | E2E-019-G001 | E2E-010-04 |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-019-05 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-019-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-010-06 | LosingSupplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-019-06 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-019-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-007-07 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-010-07 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-07 |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-019-07 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Traditional) when status is "Confirmed" in CSS |  | X |  | X | E2E-019-L001 | E2E-010-07 |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-007-08 | Losing Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Withdrawal | E2E-D003 | E2E-010-08 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-L001 | E2E-007-08 |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Withdrawal | E2E-D003 | E2E-019-08 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Smart Meters) when status is "Confirmed" in CSS | X |  | X |  | E2E-019-L001 | E2E-010-08 |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Annulment | E2E-D004 | E2E-007-01 | Gaining Supplier- Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-010-01 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-022-01 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-022-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-007-02 | Gaining Supplier- Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-010-02 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-022-02 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-022-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-007-03 | Gaining Supplier- Switch Request for Dual Fuel (Domestic, Smart meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-010-03 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meter with Primary MPAN) | X |  | X |  | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-022-03 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Domestic Smart Meters with Primary MPAN) when status is "Pending" in CSS | X |  | X |  | E2E-022-G001 | E2E-010-03 |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-007-04 | Gaining Supplier- Switch Request for Dual Fuel (Non-Domestic, Traditional Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X |  | X | E2E-007-G001 | NA |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-010-04 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic,Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-04 |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-022-04 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Traditional Meters) when status is "Confirmed" in CSS |  | X |  | X | E2E-022-G001 | E2E-010-04 |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-007-05 | Losing Supplier- Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-010-05 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-022-05 | Losing Supplier- Switch Request Annulment - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-022-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-007-06 | Losing Supplier- Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-010-06 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-022-06 | Losing Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-022-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-007-07 | Losing Supplier- Switch Request for Dual Fuel (Domestic, Smart meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-010-07 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic smart Meter with Primary MPAN) | X |  | X |  | E2E-010-L001 | E2E-007-07 |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-022-07 | Losing Supplier- Switch Request Annulment - Dual Fuel (Domestic Smart Meters with Primary MPAN) when status is "Pending" in CSS | X |  | X |  | E2E-022-L001 | E2E-010-07 |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-007-08 | Losing Supplier- Switch Request for Dual Fuel (Non-Domestic, Traditional Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4
Switch Request Annulment | E2E-D004 | E2E-010-08 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-08 |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4
Switch Request Annulment | E2E-D004 | E2E-022-08 | Losing Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Traditional Meters) when status is "Confirmed" in CSS |  | X |  | X | E2E-022-L001 | E2E-010-08 |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4

## Summary (hidden)
Test Scenario View |  |  |  |  | Summary
Priority | Fuel Type | E2E Scenario | Profile | Test Cases | Priority | Fuel Type | Profile | Distinct Count of Profile | Distinct Count of E2E Scenario | Test Cases
1 |  |  |  |  | 1
| All |  |  |  |  | All
|  | E2E-GED-001 |  |  |  |  | Domestic, Smart Meter | 1 | 1 | 6
|  |  | Domestic, Smart Meter | 6 |  |  | Domestic, Traditional Meter | 1 | 1 | 4
|  |  | Domestic, Traditional Meter | 4 |  |  | Non Domestic, Smart Meter | 1 | 1 | 3
|  |  | Non Domestic, Smart Meter | 3 |  |  | Non Domestic, Traditional Meter | 1 | 1 | 5
|  |  | Non Domestic, Traditional Meter | 5 |  | All Total |  | 4 | 1 | 18
|  | E2E-GED-001 Total |  | 18 |  | Dual
| All Total |  |  | 18 |  |  | Domestic, Smart Meter | 1 | 4 | 14
| Dual | [5 empty] | Domestic, Traditional Meter | 1 | 4 | 14
|  | E2E-D001 |  |  |  |  | Non Domestic, Smart Meter | 1 | 4 | 14
|  |  | Domestic, Smart Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 4 | 14
|  |  | Domestic, Traditional Meter | 2 |  | Dual Total |  | 4 | 4 | 56
|  |  | Non Domestic, Smart Meter | 2 |  | Electricity
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Domestic, Smart Meter | 1 | 6 | 18
|  | E2E-D001 Total |  | 8 |  |  | Domestic, Traditional Meter | 1 | 6 | 16
|  | E2E-D002 |  |  |  |  | Non Domestic, Smart Meter | 1 | 6 | 20
|  |  | Domestic, Smart Meter | 8 |  |  | Non Domestic, Traditional Meter | 1 | 6 | 16
|  |  | Domestic, Traditional Meter | 8 |  | Electricity Total |  | 4 | 6 | 70
|  |  | Non Domestic, Smart Meter | 8 |  | Gas
|  |  | Non Domestic, Traditional Meter | 8 |  |  | Domestic, Smart Meter | 1 | 7 | 17
|  | E2E-D002 Total |  | 32 |  |  | Domestic, Traditional Meter | 1 | 7 | 17
|  | E2E-D003 |  |  |  |  | Non Domestic, Smart Meter | 1 | 7 | 21
|  |  | Domestic, Smart Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 7 | 17
|  |  | Domestic, Traditional Meter | 2 |  | Gas Total |  | 4 | 7 | 72
|  |  | Non Domestic, Smart Meter | 2 |  | SMS
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Service management | 1 | 1 | 7
|  | E2E-D003 Total |  | 8 |  | SMS Total |  | 1 | 1 | 7
|  | E2E-D004 |  |  | 1 Total |  |  | 5 | 19 | 223
|  |  | Domestic, Smart Meter | 2 | 2
|  |  | Domestic, Traditional Meter | 2 |  | Dual
|  |  | Non Domestic, Smart Meter | 2 |  |  | Domestic, Smart Meter | 1 | 2 | 6
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Domestic, Traditional Meter | 1 | 1 | 4
|  | E2E-D004 Total |  | 8 |  |  | Non Domestic, Smart Meter | 1 | 1 | 4
| Dual Total |  |  | 56 |  |  | Non Domestic, Traditional Meter | 1 | 1 | 4
| Electricity |  |  |  |  | Dual Total |  | 4 | 2 | 18
|  | E2E-E001 |  |  |  | Electricity
|  |  | Domestic, Smart Meter | 2 |  |  | Domestic, Smart Meter | 1 | 10 | 15
|  |  | Domestic, Traditional Meter | 2 |  |  | Domestic, Traditional Meter | 1 | 10 | 14
|  |  | Non Domestic, Smart Meter | 4 |  |  | Non Domestic, Smart Meter | 1 | 9 | 14
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 9 | 13
|  | E2E-E001 Total |  | 10 |  | Electricity Total |  | 4 | 11 | 54
|  | E2E-E002 |  |  |  | Gas
|  |  | Domestic, Smart Meter | 10 |  |  | Domestic, Smart Meter | 1 | 11 | 16
|  |  | Domestic, Traditional Meter | 8 |  |  | Domestic, Traditional Meter | 1 | 10 | 14
|  |  | Non Domestic, Smart Meter | 10 |  |  | Non Domestic, Smart Meter | 1 | 8 | 13
|  |  | Non Domestic, Traditional Meter | 8 |  |  | Non Domestic, Traditional Meter | 1 | 8 | 11
|  | E2E-E002 Total |  | 36 |  | Gas Total |  | 4 | 11 | 54
|  | E2E-E003 |  |  | 2 Total |  |  | 4 | 24 | 126
|  |  | Domestic, Smart Meter | 2 | Grand Total |  |  | 5 | 43 | 349
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E003 Total |  | 8
E2E-E004
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E004 Total |  | 8
E2E-E005
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E005 Total |  | 4
E2E-E009
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E009 Total |  | 4
| Electricity Total |  |  | 70
Gas
E2E-G001
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G001 Total |  | 10
E2E-G002
|  |  | Domestic, Smart Meter | 8
|  |  | Domestic, Traditional Meter | 8
|  |  | Non Domestic, Smart Meter | 10
|  |  | Non Domestic, Traditional Meter | 8
|  | E2E-G002 Total |  | 34
E2E-G003
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G003 Total |  | 8
E2E-G004
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G004 Total |  | 8
E2E-G005
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G005 Total |  | 4
E2E-G006
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G006 Total |  | 4
E2E-G010
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G010 Total |  | 4
| Gas Total |  |  | 72
SMS
E2E-SMS-001
|  |  | Service management | 7
|  | E2E-SMS-001 Total |  | 7
| SMS Total |  |  | 7
1 Total |  |  |  | 223
2
Dual
E2E-D005
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-D005 Total |  | 16
E2E-D006
|  |  | Domestic, Smart Meter | 2
|  | E2E-D006 Total |  | 2
| Dual Total |  |  | 18
Electricity
E2E-E006
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E006 Total |  | 4
E2E-E007
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E007 Total |  | 4
E2E-E008
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E008 Total |  | 4
E2E-E010
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E010 Total |  | 4
E2E-E011
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E011 Total |  | 4
E2E-E012
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E012 Total |  | 6
E2E-E013
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E013 Total |  | 4
E2E-E014
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-E014 Total |  | 16
E2E-E015
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E015 Total |  | 2
E2E-E016
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  | E2E-E016 Total |  | 4
E2E-E017
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 2
|  | E2E-E017 Total |  | 2
| Electricity Total |  |  | 54
Gas
E2E-G007
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G007 Total |  | 4
E2E-G008
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G008 Total |  | 4
E2E-G009
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G009 Total |  | 4
E2E-G011
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G011 Total |  | 4
E2E-G012
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G012 Total |  | 4
E2E-G013
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 3
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G013 Total |  | 6
E2E-G014
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G014 Total |  | 4
E2E-G015
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-G015 Total |  | 16
E2E-G016
|  |  | Domestic, Smart Meter | 2
|  | E2E-G016 Total |  | 2
E2E-G017
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  | E2E-G017 Total |  | 4
E2E-G018
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  | E2E-G018 Total |  | 2
| Gas Total |  |  | 54
2 Total |  |  |  | 126
Grand Total |  |  |  | 349

## How To Use (hidden)
How To Use
Contents
1. How to Navigate this document
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Overview of the Test Case worksheets
1. How to Navigate this document
This section aims to provide an overview on how to navigate through this workbook.
The workbook consists of a number of worksheets arranged in a hieracrchy working from left to right.
The 'List of Test Scenarios' is broken down into a 'List of Test Cases', which consist of individual Test Cases.
Within the 'List of Test Scenarios' worksheet each of the Scenarios has a hyperlink ('Click to See Test Cases') which when selected takes the user to the Test Cases associated to the selected scenario on the 'List of Test Cases' worksheet.
. | From here, the user can then navigate to a more detailed view of the Test Scenario by clicking on the 'Click to view Test' link
To return to the 'List of Test Scenarios' worksheet the user would select 'Back to list of Test Scenarios', which will return the user to the top of the List of Test Scenarios worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
This section aims to provide an overview of the information contained in the List of Test Scenarios worksheet
The List of 'Test Scenarios' worksheet details each Test Scenario that will be part of the testing phase and provides links to the scenario and list of test cases that make up the basic scenario.
The following are the populated Fields on the List of Test Scenarios worksheet and a brief description of each:
| Field | Details
| Test Scenario Category | A short title of the Scenario being defined
| E2E Scenario | A Unique reference for each Scenario (e.g. E2E-G001 is the first Gas Scenario)
| E2E Scenario Title | A Unique Title for each Test Scenario consisting of the E2E Scenario & Test Scenario Category
| Link | A link to the List of Test Cases appropriate to the Test Scenario
| Test ID | A scenario will require one or more Test Cases to deliver the Test Scenario. The same Test might be used in multiple scenarios. Each Test Case that delivers a particular scenario will be listed in the order they would be executed.
| Link | A link to each Test and Steps that will be used within the scenario
| Test Title | The title of the Test ID. This is defined on the individual Test Case worksheets.
| Fuel Type | Details if the Test Scenario is specific to Gas, Electricity or Dual Fuel
| Priority | Test Priority for any Risk Based Testing
| Pre-Requisite Test Scenario | The ID of the Test that must be executed prior to this one to complete a Test Scenario
| Comments | Any additional information regarding the Test Scenario will be provided here
| CSS | Indicates the number of steps the Test Case has defined that interact with CSS
| UK Link | Indicates the number of steps the Test Case has defined that interact with UK Link
| DES | Indicates the number of steps the Test Case has defined that interact with DES
| MPAS | Indicates the number of steps the Test Case has defined that interact with MPAS
| ECOES | Indicates the number of steps the Test Case has defined that interact with ECOES
| Smart Metering | Indicates the number of steps the Test Case has defined that interact with Smart Metering
| Gaining Shipper | Indicates the number of steps the Test Case has defined that interact with a Single Shipper or Gaining Shipper where the Test Scenario involves a two parties
| Losing Shipper | Indicates the number of steps the Test Case has defined that interact with a Losing Shipper where the Test Scenario involves a two parties
| Gas Transporter | Indicates the number of steps the Test Case has defined that interact with a GT or iGT
| Data Collector | Indicates the number of steps the Test Case has defined that interact with a DC
| Data Aggregator | Indicates the number of steps the Test Case has defined that interact with a DA
| MEM | Indicates the number of steps the Test Case has defined that interact with a MEM
| MAP | Indicates the number of steps the Test Case has defined that interact with a MAP
| DNO | Indicator as to whether the Test Case defined has steps that interact with a DNO/iDNO
| Gaining Supplier | Indicates the number of steps the Test Case has defined that interact with a single Supplier or a Gaining Supplier where the Test Scenario involves a two parties
| Losing Supplier | Indicates the number of steps the Test Case has defined that interact with a Losing Supplier where the Test Scenario involves a two parties
Third-Party IT Provider
3. Overview of the 'List of Test Cases' worksheet
This section aims to provide an overview of the information contained in the 'List of Test Cases' worksheet
The List of Test Cases details each variation of the Test Scenarios as Test Cases that will form part of the testing phase, and provides links to the Tests & the steps that make up the each scenario. Which Test Cases an E2E participant needs to execute will depend on the Licensed Parties profile
(see '1. How to Navigate this document' for details on how to navigate to & from the List of Test Cases worksheet)
Where Switching functionality is being tested there will be a matching 'GAIN' and a 'LOSE' Test Case. When executing a Test Case with a paired Supplier, the gaining supplier will execute the GAIN test case, and the losing supplier will execute the matching LOSE test case.
A green line separates the GAIN and LOSE test cases for the same scenario.
A blue line separates each Test Scenario, and the Test Case ID will indicate the Tests that make up a single Test Case for a Scenario.
The following are the populated Fields on the List of Test Scenarios worksheet and a brief description of each:
| Field | Details
| Test Case Category | The short title of the Scenario that the Test Case variations cover
| E2E Scenario | The Test Scenario ID of the Scenario that the Test Case variations cover
| Test Case Id | The Test Case ID is a combination of the Test Scenario ID and a unique reference to link each of the Tests that make up the Test Case
| Associated Test Id | Details the actual Test ID
| Link | A hyperlink to each Test Case worksheet that forms part of the Test Case
| Test Case Title | Details the Title of the Test Case from the associated Test Case worksheet, plus the variants in place for this particular Test Case.
| Fuel Type | Details if the Test Scenario is specific to Gas, Electricity or Dual Fuel
| Day(s) | Details the number of Days each Switch Test will be assigned. This will be blank where the number of days is not relevant to the Test Case
| Domestic | This will be marked with an 'X' where the Test Case is intended for a Domestic Customer.
| Non Domestic | This will be marked with an 'X' where the Test Case is intended for a Non Domestic Customer.
| OFAF | This will be marked with an 'X' where the Test Case is intended for a Switch of more than one Fuel Type or more than one Meter of the same Fuel Type to ensure the 'One Fail, All Fail' switching rule. The Test Case may not test a Failure in all cases.
| Related MPAN | This will be marked with an 'X' where the Test Case is intended to include related MPANs (Electricity only).
| Pre-Requisite Test Case | Details the Test ID that must have been executed prior to this Test
| Profile | The profile describes the options selected for each Test Case (i.e. where X's have been placed in the previous fields)
| Requirements | The requirements listed are the unique Abacus references documented against the in the relevant Test Case Worksheet
4. Overview of the Test Case worksheets
This section aims to provide an overview of the information contained in each of the Test Case worksheets. For example worksheet E2E-002.
Each Test Case worksheet gives an overview of the Case and the agreed steps that need to be executed. These will be loaded to Jira to form each Test Case per LP and the LP will then be able to expand on the Test Steps within Jira to make them more pertinent to the specific LP's systems and processes.
(see '1. How to Navigate this document' for details on how to navigate to & from each Test Case worksheet)
| The following are the Test Case overview Fields on each of the Test Case worksheets and a brief deCaseion of each field: |  | Example:
| Field | Details
| Scenario ID | The Test ID (as per the worksheet Name) that is used in the 'List of Test Scenarios' and 'List of Test Cases' worksheets to link Tests to Scenarios and Test Cases
| Title | The Short Title of the Test
| Description | An overview of the objectives of the Test
| Pre-Requisites | Any Pre-Requisites that need to be in place prior to this Test Case being executed
| Test Case Variable | A list of the Test Case variables that this particular Test should cater for.
| Mapped Requirements | A summary of the Abacus requirements that the Test Case covers
| Exception Codes | Exception Codes will not be applicable during E2E Testing, these will have been covered previously in SIT and/or UEPT
| The following are the Test Step Fields on each of the Test Case worksheets and a brief deCaseion of each field: |  | Example:
| Field | Details
| Mapped Requirements | The Abacus requirement reference(s) that each step covers
| Step Title | A short title outlining the purpose of the step
| Evidence Required | A 'Y' or 'N' indicator to highlight whether the Test Participant would be expected to provide evidence for the step. An 'O' indicates evidence is optional based on whether the agents and registered and have agreed to provide support during testing.
| Step Description | A more detailed description of the purpose of the step
| Related System | The system where the step would be executed
| Pre-requisite | Any Pre-Requisites that this step is dependent upon
| Expected Result | A description of the outcome of this Step
| API (Inbound to CSS) | API details retained from the original SIT tests
| Route | Route details retained from the original SIT tests
| Webhook context (Outbound from CSS) | Webhook context details retained from the original SIT tests
| Event Type | Event Type details retained from the original SIT tests
| Acknowledgement Messages | Acknowledgement Message details retained from the original SIT tests
| Comments | Any additional information / comments regarding the step
At the bottom of each Test Case worksheet are the list of Test Cases where this Test Case is called.
| The following is a brief description of each field in this section: |  | Example:
| Field | Details
| No. | Incremental number for each linked Test Case
| Unique Test Id | The Unique Test ID from the 'List of Test Cases' worksheet for each Test Case where this Test Case is called
| Return to Test Case | A Hyperlink to return directly to the current Test within the Test Case in the 'List of Test Cases' worksheet
| Test Case Title | The Test Case Title from the 'List of Test Cases' worksheet of the Unique Test ID Test Case
| Test Case ID | The Test Case ID from the 'List of Test Cases' worksheet of the Test Case
| E2E Scenario | The E2E Scenario ID from the 'List of Test Cases' worksheet of the Test Case
| Test Case Category | The Test Case Category from the 'List of Test Cases' worksheet of the Test Case
List of Test Scenarios
List of Test Cases

## List MASTER (hidden)
High
Medium
Low
MPAN Ownership
Metering Changes
Meter to Bank
Trad
Smart
Advanced
Unmetered
In Progress
Blocked - Reqt Query
Drafted
Peer Reviewed
Rework
Design Reviewed
WG Reviewed (Working Group Drops)​
WG Approved
TMAG Approved

## Change Log
Date | Author | Release | Defect ID | Reason for change
2023-09-27 | Shaun Magee |  |  | MHHS-BR-RS-084 - New scenario to check for IF-031 Change of Existing Service Appointment rejections.
2023-10-23 | Dan Gee |  |  | Test data requirements updated and expected results checked against IR5
2023-11-27 | Shaun Magee | 5.2.1 v0.1 |  | Remove columns Message Output and Message Output Event Code and Publish
2024-02-14 | Dan Gee | 5.2.1 v0.2 |  | Updated MPAN type on TC02 to Single MPAN to match Overview
2024-02-22 | Dan Gee | 5.2.1 v0.2 |  | New test case created TC03 to cover lapsing of Appointment amendment to cover requirement MHHS-BR-SU-036
2024-03-20 | Shaun Magee | 5.2.1 v0.3 |  | Merge shared steps and add Key Journey Events column
2024-05-07 | Izhan Ahsan | IR7 v0.4 |  | IF-37 test steps have been added above IF-36 test steps
2024-05-09 | Dan Gee | IR7 v0.4 |  | Added REGS Sends end date for existing MDR appointment upon setting new MDR on TC01 & TC03 based on IR7 updates
2024-05-10 | Dan Gee | IR7 v0.4 |  | Updated IF-037/PUB-037 Recipiant as Supplier due to IR7 updates on TC01 To TC03 DIN-793
2024-05-10 | Komal Deshmane | IR7 v0.4 |  | Replaced DIP response from "http 202 response from DIP" to "http 201 response from DIP" wherever needed
2024-05-10 | Komal Deshmane | IR7 v0.4 |  | Added (If opted in) to IF-036/PUB-036 for LDSO based on IR7 updates DIN-743 on TC's 01 to 03
2024-05-17 | Suraj Kadam | IR7 v0.4 |  | Added column "Test Case Version" in SITFTS0200 Overview and TC01 to TC03
2024-05-31 | Dan Gee | IR7 v0.4.1 | 33250 | Amended DCC MS appointment steps removing refrence to MDR and CSS07000 on TC01
2024-08-13 | Dan Gee | IR7 v0.4.2 | 37287 | Amended title on overview to reflect 'Change of MS or DS' from Change of MS or DS when only one service is being updated
2024-11-07 | Ashwin | IR7 v0.4.3 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC01 for steps 1,4,7,10,13,17,18,24,31,32,33,36
2024-11-07 | Ashwin | IR7 v0.4.3 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC02 for steps 1,4,7,10,13,17,20,22,23,25,26,27,28,30,38,41
2024-11-07 | Ashwin | IR7 v0.4.3 | Test Case Exit Point Identification | Evidence flag changed from Y to N of TC03 for steps 1,4,7,10,13,17,18,21,25,33,34,35,37,40,43,46,49,52
2025-02-17 | Dan Gee | v0.4.4 | 48958 | Amended event code for lapsed DS appointment on TC03 from [DSAppAccepted] to [DSAppLapsed]
2025-02-18 | Dan Gee | v0.4.4 | 48958 | Amended event code for lapsed DS appointment on TC03 from [DSAppLapsed] to [DSAppRejected]
2025-04-28 | Dan Gee | v0.4.4 | Requirements Update | Removed invalid mappings - TC01 MHHS-BR-SU-008, MHHS-BR-SU-011, MHHS-BR-SU-034, MHHS-BR-RS-030, MHHS-BR-DS-002, MHHS-BR-MS-003 TC02 MHHS-BR-SU-022, MHHS-BR-SU-025, MHHS-BR-SU-034, MHHS-BR-RS-046, MHHS-BR-RS-064, MHHS-BR-DS-011, MHHS-BR-DS-016 TC03 MHHS-BR-SU-022, MHHS-BR-SU-025, MHHS-BR-RS-046, MHHS-BR-RS-064

## SITFTS0200 Overview
Scenario ID | SITFTS-0200
Scenario Title | Change of MS or DS followed by Change of Existing Appointment
Theme | Change of Metering Service
Description | Existing MPAN with Supplier, Change MS (TC01) or DS (TC02 & TC03) followed by change to the raised MS (TC01) or DS (TC02 & TC03) Appointments and verify that the IF-031 is rejected when data fails validation checks. One test for change of MS Appointment and one for change of DS Appointment and one test that DS Appointment lapses and IF-035 is issued to supplier
Functional Category | Change of MS or DS, no change of supplier followed by Change of Service Appointment which is rejected
Functional Area 1 | Change of Service Appointment
Functional Area 2 | Existing MPAN, Chg Service Appointment fails
Creator | Shaun Magee
Priority | High
Scenario size | Medium
Design Document Ref
Business Process | BP002 / BP003 / BP003A / BP003B
Pre-Requisites
Boundaries | Test Ends on rejection notification being received due to failure of validation rules when trying to amend existing appointment.
Test Case Variables | (1) smart, single MPAN, forward-dated, Change of MS Appointment Rejected (2) advanced, single MPAN, forward-dated, Change of DS Appointment Rejected (3) smart, single MPAN, forward-dated, Change of DS Appointment fails queue processing validation
Mapped Requirements
Exception Codes | NA
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Test Case Link | Test Case Version | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | SITFTS-0200 TC01 | SITFTS-0200-Smart Metered | SITFTS-0200 - Smart Metered | 0.4.4 | Existing Live Smart Single MPAN Forward date MS appointment to be booked successfully. Amended appointment to be rejected due to failure of validation rule REG1025 - Scenario USP can only be used with currently appointed Service Provider (as per DES138 data specification) | Smart Meter | Single MPAN | Forward-dated
2 | SITFTS-0200 TC02 | SITFTS-0200-Advanced | SITFTS-0200 - Advanced | 0.4.3 | Existing Live Advanced Single MPAN Forward date DS appointment to be booked successfully Amended appointment to be rejected due to failure of validation rule REG1025 - Scenario USP can only be used with currently appointed Service Provider (as per DES138 data specification) | Advanced | Single MPAN | Forward-dated
3 | SITFTS-0200 TC03 | SITFTS-0200-Smart Meter appointment amendment Lapse | SITFTS-0200 Smart Meter appointment amendment Lapse | 0.4.5 | Existing Live Smart Single MPAN Forward date DS appointment to be booked successfully. Amended appointment to be rejected due to Insufficient Notice / Lead Time for Appointment to take effect | Smart Meter | Single MPAN | Forward-dated
Back to List of
Test Scenarios

## SITFTS0200- Smart
No. | Test Case Id |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
1 | SITFTS-0200 TC01 |  |  | 0.4.4 |  | SITFTS-0200-Smart Metered | SITFTS-0200 - Smart Metered | Existing Live Smart Single MPAN Forward date MS appointment to be booked successfully. Amended appointment to be rejected due to failure of validation rule REG1025 - Scenario USP can only be used with currently appointed Service Provider (as per DES138 data specification) | Smart Meter | Single MPAN | Forward-dated
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0200-Smart Metered | Change of Metering Service | [10 empty] | N
| Supplier Appointment Request | 1 | BP002 | 10 20 | MHHS-BR-SU-005 MHHS-BR-SU-006 MHHS-BR-SU-007 | SUPC | IF-031 | [MSApp] | DIP | SUPC sends IF-031 to the DIP for a MS Appointment. | http 201 response from DIP | N
|  | 2 | BP002 | 30 | MHHS-BR-RS-009 | DIP | PUB-031 | [MSApp] | REGS | DIP sends PUB-031 to REGS for a MS Appointment. |  | N
|  | 3 | BP002 | 40 | MHHS-BR-RS-010 | DIP | PUB-031 | [MSApp] | REGS | REGS receives PUB-031 - Supplier Service Appointment Request from the DIP. | REGS receives PUB-031 and confirms the Supplier Service Appointment Request from the Supplier successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Supplier Appointment Request Accepted | 4 | BP002 | 45 | MHHS-BR-RS-011 | REGS | IF-032 | [MSAppInitialResp] | DIP | REGS sends IF-032 - Supplier Service Provider Appointment Request Response to the DIP. | http 201 response from DIP | N
|  | 5 | BP002 | 50 |  | DIP | PUB-032 | [MSAppInitialResp] | SUPC | DIP sends PUB-032 to the Supplier. |  | N
|  | 6 | BP002 | 55 | MHHS-BR-SU-009 | DIP | PUB-032 | [MSAppInitialResp] | SUPC | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance | Supplier receives PUB-032 and confirms the Supplier Service Provider Appointment Request Response and waits for Acceptance successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request | 7 | BP002 | 60 | MHHS-BR-RS-014.1 MHHS-BR-RS-015 | REGS | IF-033 | [MSAppSPRequest] | DIP | REGS sends IF-033 to the DIP. | http 201 response from DIP | N
|  | 8 | BP002 | 65 |  | DIP | PUB-033 | [MSAppSPRequest] | SMSI | DIP sends PUB-033 to the SMS (Incoming). |  | N
|  | 9 | BP002 | 70 | MHHS-BR-MS-001 | DIP | PUB-033 | [MSAppSPRequest] | SMSI | SMS (Incoming) receives PUB-033. | SMS incoming receives PUB-033 from the REGS which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request Accepted | 10 | BP002 | 75 | MHHS-BR-MS-002 | SMSI | IF-034 | [MSAppSPResponse] | DIP | SMS (Incoming) sends IF-034 to the DIP. | http 201 response from DIP | N
|  | 11 | BP002 | 80 |  | DIP | PUB-034 | [MSAppSPResponse] | REGS | DIP sends PUB-034 to the REGS. |  | N
|  | 12 | BP002 | 85 | MHHS-BR-RS-016 MHHS-BR-RS-017 | DIP | PUB-034 | [MSAppSPResponse] | REGS | REGS receives PUB-034. | REGS receives PUB-034 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Accepted | 13 | BP002 | 87 | MHHS-BR-RS-018 | REGS | IF-035 | [MSAppAccepted] | DIP | REGS sends IF-035 to the DIP. | http 201 response from DIP | N
|  | 14 | BP002 | 91 |  | DIP | PUB-035 | [MSAppAccepted] | SUPC, SMSI | DIP sends PUB-035 to the Supplier and MSS (Incoming) |  | N
|  | 15 | BP002 | 95 | MHHS-BR-SU-010 | DIP | PUB-035 | [MSAppAccepted] | SUPC | Supplier receives PUB-035. | Supplier receives PUB-035 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 16 | BP002 | 92 | MHHS-BR-MS-006.1 | DIP | PUB-035 | [MSAppAccepted] | SMSI | SMSI receives PUB-035. | SMSI receives PUB-035 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Queue (If required) | 17 | BP002 | 100 101 | MHHS-BR-RS-020 | REGS |  |  |  | REGS Holds in appointment queue until appointment date reached (Prospective Appointments only) |  | N
| RS De-Appointment Notification | 18 | BP002 | 120 +130 | MHHS-BR-RS-024 MHHS-BR-RS-031 | REGS | IF-037 | [MSDeApp] | DIP | Registration service sends out IF-037 to DIP | http 201 response from DIP | N
|  | 19 | BP002 | 140 |  | DIP | PUB-037 | [MSDeApp] | SMSO, Supplier, LDSO, EES | DIP sends PUB-037 to Old Metering Service, Supplier, LDSO & EES |  | N
|  | 20 | BP002 | 231 | MHHS-BR-MS-005 | DIP | PUB-037 | [MSDeApp] | SMSO | Old Metering Service receives PUB-037 confirming MS De-appointment | Old metering service receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 21 | BP002 | 150 | MHHS-BR-SU-012 | DIP | PUB-037 | [MSDeApp] | Supplier | Supplier receives PUB-037 confirming MS De-appointment | Supplier receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 22 | BP002 | 145 | MHHS-BR-LD-002 | DIP | PUB-037 | [MSDeApp] | LDSO | LDSO receives PUB-037 confirming MS De-appointment | LDSO receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 23 | BP002 | 146 | MHHS-BR-EES-016.3 | DIP | PUB-037 | [MSDeApp] | EES | EES receives PUB-037 confirming MS De-appointment | EES receives PUB-037 and confirms MS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Notification | 24 | BP002 | 240 | MHHS-BR-RS-033 | REGS | IF-036 | [MSAppActive] | DIP | REGS sends IF-036 to DIP. | http 201 response from DIP | N
|  | 25 | BP002 | 245 |  | DIP | PUB-036 | [MSAppActive] | SDSC | DIP sends PUB-036 to SUPC, LDSO(If opted in), EES, SMSI and SDSC. |  | N
|  | 26 | BP002 | 260 | MHHS-BR-SU-013 | DIP | PUB-036 | [MSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 27 | BP002 | 280 | MHHS-BR-LD-003 | DIP | PUB-036 | [MSAppActive] | LDSO(If opted in) | LDSO(If opted in) receives PUB-036 | LDSO(If opted in) receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 28 | BP002 | 283 | MHHS-BR-EES-016.3 | DIP | PUB-036 | [MSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 29 | BP002 | 195 | MHHS-BR-MS-007 | DIP | PUB-036 | [MSAppActive] | SMSI | SMSI receives PUB-036 | SMSI receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 30 | BP002 | 270 | MHHS-BR-DS-003 | DIP | PUB-036 | [MSAppActive] | SDSC | SDSC receives PUB-036 | SDSC receives PUB-036 which successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| CSS/DCC Updates - Start | 31 | N/A | N/A | Existing requirement- REC Schedule 28 | REGS | ERDA CSS00200 (Issue MS appointment notification ) | N/A | CSS | REGS Sends ERDA CSS00200 for MS Appointment notification |  | N
| CSS/DCC Updates - Completed | 32 | N/A | N/A | CSS | CSS | DSP of MS appointment (CSS03200) | N/A | DCC | CSS calls CSS-DSP Interface to inform DSP of MS appointment |  | N
| Amend MS Appointment Rejection - Start | 33 | BP003B | 10 20 | MHHS-BR-SU-031 MHHS-BR-SU-032 | SUPC | IF-031 | [MSApp] | DIP | SUPC sends IF-031 to DIP for a MS Appointment Update where the Proposed Metering Service DIP ID <> Current Metering Service DIP ID in Registrations | http 201 response from DIP | N
|  | 34 | BP003B | 30 |  | DIP | PUB-031 | [MSApp] | REGS | DIP sends PUB-031 to REGS for a MS Appointment Update where the Proposed Metering Service DIP ID <> Current Metering Service DIP ID in Registrations | Validation rule failure to be set as - REG1025 - Scenario USP can only be used with currently appointed Service Provider | N
|  | 35 | BP003B | 40 | MHHS-BR-RS-081 MHHS-BR-RS-082 | DIP | PUB-031 | [MSApp] | REGS | REGS receives PUB-031 | REGS receives PUB-031 MSApp, confirms appointment and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 36 | BP003B | 45 | MHHS-BR-RS-084 | REGS | IF-032 | [MSAppInitialResp] | DIP | REGS sends IF-032 Service Response to Suppliers request to amend an MS Appointment to the DIP where the Response Code is "R" with the appropriate value in the Response Message | http 201 response from DIP | N
|  | 37 | BP003B | 50 |  | DIP | PUB-032 | [MSAppInitialResp] | SUPC | DIP sends PUB-032 Service Response to Suppliers request to amend an MS Appointment to the Supplier where the Response Code is "R" with the appropriate value in the Response Message |  | N
| Amend MS Appointment Rejection - End | 38 | BP003B | 55 | MHHS-BR-SU-033 | DIP | PUB-032 | [MSAppInitialResp] | SUPC | SUPC receives PUB-032 | Supplier receives PUB-032 MSAppInitialResp, confirms initial response and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS0200- Advanced
No. | Test Case Id |  |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
2 | SITFTS-0200 TC02 |  |  |  | 0.4.3 |  | SITFTS-0200-Advanced | SITFTS-0200 - Advanced | Existing Live Advanced Single MPAN Forward date DS appointment to be booked successfully Amended appointment to be rejected due to failure of validation rule REG1025 - Scenario USP can only be used with currently appointed Service Provider (as per DES138 data specification) | Advanced | Single MPAN | Forward-dated
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0200-Advanced | Change of Data Service | [10 empty] | N
| Supplier Appointment Request | 1 | BP003 | 10 20 | MHHS-BR-SU-019 MHHS-BR-SU-020 MHHS-BR-SU-021 | SUPC | IF-031 | [DSApp] | DIP | SUPC sends IF-031 to DIP | http 201 response from DIP | N
|  | 2 | BP003 | 30 |  | DIP | PUB-031 | [DSApp] | REGS | DIP sends PUB-031 to REGS for a DS Appointment. |  | N
|  | 3 | BP003 | 40 | MHHS-BR-RS-043 MHHS-BR-RS-044 | DIP | PUB-031 | [DSApp] | REGS | REGS receives PUB-031 - Supplier Service Appointment Request from the DIP. | REGS receives PUB-031 DSApp with details of Data Services Appointment and confims the supplier service appointment request from the Supplier successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Supplier Appointment Request Accepted | 4 | BP003 | 45 | MHHS-BR-RS-045 | REGS | IF-032 | [DSAppInitialResp] | DIP | REGS sends IF-032 to DIP | http 201 response from DIP | N
|  | 5 | BP003 | 50 |  | DIP | PUB-032 | [DSAppInitialResp] | SUPC | DIP sends PUB-032 - Supplier Service Provider Appointment Request Response to the Supplier. |  | N
|  | 6 | BP003 | 55 | MHHS-BR-SU-023 | DIP | PUB-032 | [DSAppInitialResp] | SUPC | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance | Supplier receives PUB-032 DSAppInitialResp with details of Data Services Appointment Initial Response and confims Supplier Service Provider Appointment Request Response and waits for acceptance successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request | 7 | BP003 | 60 | MHHS-BR-RS-049 MHHS-BR-RS-048.1 | REGS | IF-033 | [DSAppSPRequest] | DIP | REGS sends IF-033 to DIP | http 201 response from DIP | N
|  | 8 | BP003 | 65 |  | DIP | PUB-033 | [DSAppSPRequest] | ADSI | DIP sends PUB-033 to the ADS (Incoming). |  | N
|  | 9 | BP003 | 220 | MHHS-BR-DS-007 | DIP | PUB-033 | [DSAppSPRequest] | ADSI | ADS (Incoming) receives PUB-033 from the DIP. | Incoming ADS receives PUB-033 DSAppSPResponse with details of Data Services Appointment PR Response and confirms the REGS successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request Accepted | 10 | BP003 | 221 | MHHS-BR-DS-008 | ADSI | IF-034 | [DSAppSPResponse] | DIP | ADSI sends IF-034 to DIP | http 201 response from DIP | N
|  | 11 | BP003 | 80 |  | DIP | PUB-034 | [DSAppSPResponse] | REGS | DIP sends PUB-034 to the REGS. |  | N
|  | 12 | BP003 | 85 100 | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-054 MHHS-BR-RS-056 MHHS-BR-RS-057 | DIP | PUB-034 | [DSAppSPResponse] | REGS | REGS receives PUB-034 and determines processing treatment | REGS receives PUB-034 DSAppSPResponse with details of Data Services Appointment PR Response and confirms/determines processing treatment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Accepted | 13 | BP003 | 85 87 | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-052 | REGS | IF-035 | [DSAppAccepted] | DIP | REGS sends IF-035 to DIP | http 201 response from DIP | N
|  | 14 | BP003 | 215 |  | DIP | PUB-035 | [DSAppAccepted] | SUPC,ADSI | DIP sends PUB-035 to the Supplier and Data Service (Incoming) |  | N
|  | 15 | BP003 | 95 | MHHS-BR-SU-024 | DIP | PUB-035 | [DSAppAccepted] | SUPC | Supplier receives PUB-035. | Supplier receives PUB-035 DSAppAccepted with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 16 | BP003 | 91 | MHHS-BR-DS-012.1 | DIP | PUB-035 | [DSAppAccepted] | ADSI | ADSI receives PUB-035. | ADSI receives PUB-035 successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Prospective Appointment Notification | 17 | BP003 | 86 | MHHS-BR-RS-019 | REGS | IF-035 | [IMS-SendMTD] | DIP | REGS sends IF-035 to DIP | http 201 response from DIP | N
|  | 18 | BP003 | 88 |  | DIP | PUB-035 | [IMS-SendMTD] | AMSO | DIP sends PUB-035 [Prospective Appt] to the AMS (Outgoing). |  | N
| Adv MTD Exchanged | 19 | BP003 | 160 | MHHS-BR-MS-006 | DIP | PUB-035 | [IMS-SendMTD] | AMSO | AMS (Outgoing) receives PUB-035 from the DIP. | AMS Outgoing receives PUB-035 with details of IMS-SendMTD and confirm REGS successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 20 | BP003 | 170 | MHHS-BR-MS-027 | AMSO | D268 HH Adv MTD | N/A | ADSI | AMS (Outgoing) sends D268 HH Adv MTD to ADSI |  | N
|  | 21 | BP003 | 345 | MHHS-BR-DS-015 | AMSO | D268 HH Adv MTD | N/A | ADSI | ADSI receives D268 HH Adv MTD from AMS (Outgoing) |  | Y
| RS Apppointment Queue (If required) | 22 | BP003 | 100 101 120 | MHHS-BR-RS-054 MHHS-BR-RS-059 | REGS |  |  |  | REGS holds in appointment queue until appointment date reached [Prospective Appts only] |  | N
| RS De-Appointment Notification | 23 | BP003 | 130 | MHHS-BR-RS-065 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 201 response from DIP | N
|  | 24 | BP003 | 140 |  | DIP | PUB-037 | [DSDeApp] | ADSO, Supplier, LDSO, EES, MDS | DIP sends out PUB-037 to ADSO, Supplier, LDSO, EES and MDS confirming DS De-appointment |  | N
|  | 25 | BP003 | 96 | MHHS-BR-DS-018 | DIP | PUB-037 | [DSDeApp] | ADSO | ADSO recieves PUB-037 confirming DS De-appointment | ADSO receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | N
|  | 26 | BP003 | 150 | MHHS-BR-SU-026 | DIP | PUB-037 | [DSDeApp] | Supplier | Supplier recieves PUB-037 confirming DS De-appointment | Supplier receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | N
|  | 27 | BP003 | 145 | MHHS-BR-LD-004 | DIP | PUB-037 |  | LDSO | LDSO recieves PUB-037 confirming DS De-appointment | LDSO receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | N
|  | 28 | BP003 | 146 | MHHS-BR-EES-016.3 | DIP | PUB-037 | [DSDeApp] | EES | EES recieves PUB-037 confirming DS De-appointment | EES receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | N
|  | 29 | BP003 | 147 (TBC) | TBC | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037. | MDS receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Notification | 30 | BP003 | 250 | MHHS-BR-RS-067 | REGS | IF-036 | [DSAppActive] | DIP | REGS sends IF-036 to DIP | http 201 response from DIP | N
|  | 31 | BP003 | 255 |  | DIP | PUB-036 | [DSAppActive] | SUPC, AMSI, LDSO(If opted in), EES, ADSI , MDS | DIP sends PUB-036 to SUPC, AMSI, LDSO(If opted in), EES, ADSI and MDS confirming DS Appointment |  | N
|  | 32 | BP003 | 260 | MHHS-BR-SU-027 | DIP | PUB-036 | [DSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 33 | BP003 | 281 | MHHS-BR-MS-030 | DIP | PUB-036 | [DSAppActive] | AMSI | AMSI receives PUB-036 | AMSI receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 34 | BP003 | 280 | MHHS-BR-LD-005 | DIP | PUB-036 | [DSAppActive] | LDSO(If opted in) | LDSO(If opted in) receives PUB-036 | LDSO(If opted in) receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 35 | BP003 | 279 | MHHS-BR-EES-016.3 | DIP | PUB-036 | [DSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 36 | BP003 | 284 (TBC) | TBC | DIP | PUB-036 | [DSAppActive] | MDS | MDS receives PUB-036 | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 37 | BP003 | 340 | MHHS-BR-DS-013 | DIP | PUB-036 | [DSAppActive] | ADSI | ADS (Incoming) receives PUB-036 | ADS incoming receives PUB-036 DSAppActive with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Amend DS Appointment Rejection - Start | 38 | BP003B | 10 20 | MHHS-BR-SU-031 MHHS-BR-SU-032 | SUPC | IF-031 | [DSApp] | DIP | SUPC sends IF-031 to DIP for a DS Appointment Update where the Proposed Date Service DIP ID <> Current Data Service DIP ID in Registrations | http 201 response from DIP | N
|  | 39 | BP003B | 30 |  | DIP | PUB-031 | [DSApp] | REGS | DIP sends PUB-031 to REGS for a DS Appointment Update where the Proposed Date Service DIP ID <> Current Data Service DIP ID in Registrations | Validation rule failure to be set as - REG1025 - Scenario USP can only be used with currently appointed Service Provider | N
|  | 40 | BP003B | 40 | MHHS-BR-RS-081 MHHS-BR-RS-082 | DIP | PUB-031 | [DSApp] | REGS | REGS receives PUB-031 | REGS receives PUB-031 DSApp, confirms appointment and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 41 | BP003B | 45 | MHHS-BR-RS-084 | REGS | IF-032 | [DSAppInitialResp] | SUPC | REGS sends IF-032 Service Response to Suppliers request to amend an DS Appointment to the DIP where the Response Code is "R" with the appropriate value in the Response Message | http 201 response from DIP | N
|  | 42 | BP003B | 50 |  | DIP | PUB-032 | [DSAppInitialResp] | SUPC | DIP sends PUB-032 Service Response to Suppliers request to amend an DS Appointment to the Supplier where the Response Code is "R" with the appropriate value in the Response Message |  | N
| Amend DS Appointment Rejection - End | 43 | BP003B | 55 | MHHS-BR-SU-033 | DIP | PUB-032 | [DSAppInitialResp] | SUPC | SUPC receives PUB-032 | Supplier receives PUB-032 DSAppInitialResp, confirms initial response and successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## SITFTS0200- Smart DS Lapse
No. | Test Case Id |  |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
3 | SITFTS-0200 TC03 |  |  |  | 0.4.5 |  | SITFTS-0200-Smart Meter appointment amendment Lapse | SITFTS-0200 Smart Meter appointment amendment Lapse | Existing Live Smart Single MPAN Forward date DS appointment to be booked successfully. Amended appointment to be rejected due to Insufficient Notice / Lead Time for Appointment to take effect | Smart | Single MPAN | Forward-dated
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SITFTS-0200-Smart Meter appointment amendment Lapse | Change of Data Service | [10 empty] | N
| Supplier Appointment Request | 1 | BP003 | 10 20 | MHHS-BR-SU-019 MHHS-BR-SU-020 MHHS-BR-SU-021 | SUPC | IF-031 | [DSApp] | DIP | SUPC sends IF-031 to DIP for a DS Appointment. | http 201 response from DIP | N
|  | 2 | BP003 | 30 |  | DIP | PUB-031 | [DSApp] | REGS | DIP sends PUB-031 to REGS for a DS Appointment |  | N
|  | 3 | BP003 | 40 | MHHS-BR-RS-043 MHHS-BR-RS-044 | DIP | PUB-031 | [DSApp] | REGS | REGS receives PUB-031 - Supplier Service Appointment Request from the Supplier. | REGS receives PUB-031 DSApp with details of Data Services Appointment and confims the supplier service appointment request from the Supplier successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Supplier Appointment Request Accepted | 4 | BP003 | 45 | MHHS-BR-RS-045 | REGS | IF-032 | [DSAppInitialResp] | DIP | REGS sends IF-032 - Supplier Service Provider Appointment Request Response to the DIP. | http 201 response from DIP | N
|  | 5 | BP003 | 50 |  | DIP | PUB-032 | [DSAppInitialResp] | SUPC | DIP sends PUB-032 - Supplier Service Provider Appointment Request Response to the DIP. |  | N
|  | 6 | BP003 | 55 | MHHS-BR-SU-023 | DIP | PUB-032 | [DSAppInitialResp] | SUPC | Supplier receives PUB -032 - Supplier Service Provider Appointment Request Response and waits for Acceptance | Supplier receives PUB-032 DSAppInitialResp with details of Data Services Appointment Initial Response and confims Supplier Service Provider Appointment Request Response and waits for acceptance successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request | 7 | BP003 | 60 | MHHS-BR-RS-049 MHHS-BR-RS-048.1 | REGS | IF-033 | [DSAppSPRequest] | DIP | REGS sends IF-033 to DIP | http 201 response from DIP | N
|  | 8 | BP003 | 65 |  | DIP | PUB-033 | [DSAppSPRequest] | SDSI | DIP sends PUB-033 to the SDS (Incoming). |  | N
|  | 9 | BP003 | 220 | MHHS-BR-DS-007 MHHS-BR-DS-011 | DIP | PUB-033 | [DSAppSPRequest] | SDSI | SDS (Incoming) receives PUB-033 from the DIP. | SDS receives PUB-033 DSAppSPResponse with details of Data Services Appointment PR Response and confirms the REGS successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Request Accepted | 10 | BP003 | 221 | MHHS-BR-DS-008 MHHS-BR-DS-011 | SDSI | IF-034 | [DSAppSPResponse] | DIP | SDS (Incoming) sends IF-034 to the DIP. | http 201 response from DIP | N
|  | 11 | BP003 | 80 |  | DIP | PUB-034 | [DSAppSPResponse] | REGS | DIP sends PUB-034 to the REGS. |  | N
|  | 12 | BP003 | 85 100 | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-054 MHHS-BR-RS-056 MHHS-BR-RS-057 | DIP | PUB-034 | [DSAppSPResponse] | REGS | REGS receives PUB-034 and determines processing treatment | REGS receives PUB-034 DSAppSPResponse with relevant information of service appointment to determine processing treatment Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| RS Appointment Accepted | 13 | BP003 | 85 87 | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-052 | REGS | IF-035 | [DSAppAccepted] | DIP | REGS sends IF-035 to the DIP | http 201 response from DIP | N
|  | 14 | BP003 | 215 |  | DIP | PUB-035 | [DSAppAccepted] | SUPC, SDSI | DIP sends PUB-035 to the Supplier and Data Service (Incoming) |  | N
|  | 15 | BP003 | 95 | MHHS-BR-SU-024 | DIP | PUB-035 | [DSAppAccepted] | SUPC | Supplier receives PUB-035. | Supplier receives PUB-035 with details of Data Services Appointment Accepted successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 16 | BP003 | 91 | MHHS-BR-DS-012.1 | DIP | PUB-035 | [DSAppAccepted] | SDSI | SDSI receives PUB-035. | SDSI receives PUB-035 successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Apppointment Queue (If required) | 17 | BP003 | 100 101 120 | MHHS-BR-RS-054 MHHS-BR-RS-059 | REGS |  |  |  | REGS Holds in appointment queue until appointment date reached [Prospective Appts only] |  | N
| RS De-Appointment Notification | 18 | BP003 | 130 | MHHS-BR-RS-065 | REGS | IF-037 | [DSDeApp] | DIP | REGS sends IF-037 to DIP | http 201 response from DIP | N
|  | 19 | BP003 | 140 |  | DIP | PUB-037 | [DSDeApp] | SDSO, Supplier, LDSO, EES, MDS | DIP sends PUB-037 De-appointment to SDSO, Supplier, LDSO, EES and MDS |  | N
|  | 20 | BP003 | 96 | MHHS-BR-DS-018 | DIP | PUB-037 | [DSDeApp] | SDSO | Smart Data Service (Outgoing) receives PUB-037 De-appointment and continues with their BAU processes. | Outgoing Smart Data Service receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 21 | BP003 | 150 | MHHS-BR-SU-026 | DIP | PUB-037 | [DSDeApp] | Supplier | Supplier recieves PUB-037 confirming DS De-appointment | Supplier receives PUB-037 DSDeApp with details of Data Services DE Appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | N
|  | 22 | BP003 | 145 | MHHS-BR-LD-004 | DIP | PUB-037 | [DSDeApp] | LDSO | LDSO receives de appointment notification PUB-037. | LDSO receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 23 | BP003 | 146 | MHHS-BR-EES-016.3 | DIP | PUB-037 | [DSDeApp] | EES | EES receives de appointment notification PUB-037. | EES receives PUB-037 DSDeApp with details of Data Services Appointment Active and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 24 | BP003 | 147 (TBC) | TBC | DIP | PUB-037 | [DSDeApp] | MDS | MDS receives PUB-037. | MDS receives PUB-037 DSDeApp with details of Data Services Appointment and confirms the DS De-appointment successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| RS Appointment Notification | 25 | BP003 | 250 | MHHS-BR-RS-067 MHHS-BR-RS-067.1 | REGS | IF-036 | [DSAppActive] | DIP | REGS sends IF-036 to DIP | http 201 response from DIP | N
|  | 26 | BP003 | 255 |  | DIP | PUB-036 | [DSAppActive] | SUPC, SMSI, LDSO(If opted in), EES, SDSI, MDS | DIP sends PUB-036 to SUPC, SMSI, LDSO(If opted in), EES, SDSI and MDS confirming DS Appointment |  | N
|  | 27 | BP003 | 260 | MHHS-BR-SU-027 | DIP | PUB-036 | [DSAppActive] | SUPC | Supplier receives PUB-036 | Supplier receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 28 | BP003 | 281 | MHHS-BR-MS-030 | DIP | PUB-036 | [DSAppActive] | SMSI | SMSI receives PUB-036 | SMSI receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 29 | BP003 | 280 | MHHS-BR-LD-005 | DIP | PUB-036 | [DSAppActive] | LDSO(If opted in) | LDSO(If opted in) receives PUB-036 | LDSO(If opted in) receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 30 | BP003 | 279 | MHHS-BR-EES-016.3 | DIP | PUB-036 | [DSAppActive] | EES | EES receives PUB-036 | EES receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 31 | BP003 | 284 (TBC) | TBC | DIP | PUB-036 | [DSAppActive] | MDS | MDS receives PUB-036 | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 32 | BP003 | 340 | MHHS-BR-DS-013 | DIP | PUB-036 | [DSAppActive] | SDSI | SDS (Incoming) receives PUB-036 | SDS Incoming receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| CSS/DCC Updates - Start | 33 | BP003A | 20 | MHHS-BR-RS-078 MHHS-BR-RS-078.1 MHHS-BR-RS-078.2 | REGS | ERDA CSS00200 (Issue MDR Request) | N/A | CSS | REGS Sends end date for existing MDR appointment & Sends details of new MDR to CSS. Issues ERDA CSS00200 (Issue MDR Request) to CSS which outputs CSS07000 (Response) |  | N
|  | 34 | BP003A | 30 40 | CSS | CSS | DSP of MDR appointment | N/A | DCC | CSS calls CSS-DSP Interface to inform DSP of MDR appointment |  | N
|  | 35 | BP003A | 50 60 | DCC | DCC | DSP updates MDR appointment | N/A | CSS | DSP updates MDR appointment, and confirms update to CSS over CSS-DSP Interface |  | N
|  | 36 | BP003A | 80 | MHHS-BR-RS-079 | CSS | CSS07000 (Response) | N/A | REGS | REGS receives CSS07000 (Response) from CSS |  | Y
|  | 37 | BP003A | 90 | MHHS-BR-RS-080 | REGS | IF-035 | [DCC-MDROutcome] | DIP | REGS sends IF-035 - (DCC MDR Outcome) to DIP | http 201 response from DIP | N
|  | 38 | BP003A | 100 110 |  | DIP | PUB-035 | [DCC-MDROutcome] | SDSI | DIP sends PUB-035 to SDSI |  | N
| CSS/DCC Updates - Completed | 39 | BP003A | 120 | MHHS-BR-DS-042.1 | DIP | PUB-035 | [DCC-MDROutcome] | SDSI | SDS (Incoming) receives PUB-035 - (DCC MDR Outcome) and manages Service Provider Update (BAU). | SDS incoming receives PUB-035 with details of DCC MDR outcome and confirms (DCC MDR Outcome) and manages Service Provider Update (BAU) successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Lapsed DS Appointment Amendment - Start | 40 | BP003B | 10 20 | MHHS-BR-SU-031 MHHS-BR-SU-032 | SUPC | IF-031 | [DSApp] | DIP | SUPC sends IF-031 to DIP | http 201 response from DIP | N
|  | 41 | BP003B | 30 |  | DIP | PUB-031 | [DSApp] | REGS | DIP sends PUB-031 to REGS for a MS Appointment Update where the Contract Reference Data Service provided is amended |  | N
|  | 42 | BP003B | 40 | MHHS-BR-RS-081 MHHS-BR-RS-082 | DIP | PUB-031 | [DSApp] | REGS | REGS receives PUB-031 | REGS receives PUB-031 with details of Data Service Appointment and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 43 | BP003B | 45 | MHHS-BR-RS-083 | REGS | IF-032 | [DSAppInitialResp] | DIP | REGS sends IF-032 to DIP | http 201 response from DIP | N
|  | 44 | BP003B | 50 |  | DIP | PUB-032 | [DSAppInitialResp] | SUPC | DIP sends PUB-032 Service Response to Suppliers request to amend a DS Appointment to the Supplier |  | N
|  | 45 | BP003B | 55 | MHHS-BR-SU-034 | DIP | PUB-032 | [DSAppInitialResp] | SUPC | SUPC receives PUB-032 | Supplier receives PUB-032 with details of Data Service Appointment initial response and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 46 | BP003B | 60 | MHHS-BR-RS-085 | REGS | IF-033 | [DSAppSPRequest] | DIP | REGS sends IF-033 to the DIP | http 201 response from DIP | N
|  | 47 | BP003B | 65 |  | DIP | PUB-033 | [DSAppSPRequest] | SDSI | DIP sends PUB-033 to the SDS (Incoming). |  | N
|  | 48 | BP003B | 220 | MHHS-BR-MS-004 MHHS-BR-DS-011 | DIP | PUB-033 | [DSAppSPRequest] | SDSI | SDS (Incoming) receives PUB-033 from the REGS. | Data Service receives PUB-033 with details of Data Service Appointment service provider response and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 49 | BP003B | 225 | MHHS-BR-MS-004 MHHS-BR-DS-011 | SDSI | IF-034 | [DSAppSPResponse] | DIP | SDS (Incoming) sends IF-034 to the DIP this needs to include rejection reason SP011 - Insufficient Notice / Lead Time for Appointment to take effect | http 201 response from DIP | N
|  | 50 | BP003B | 80 |  | DIP | PUB-034 | [DSAppSPResponse] | REGS | DIP sends PUB-034 to the REGS. |  | N
|  | 51 | BP003B | 85 | MHHS-BR-RS-086 MHHS-BR-RS-086.1 MHHS-BR-RS-087 | DIP | PUB-034 | [DSAppSPResponse] | REGS | REGS receives PUB-034. | REGS receives PUB-034 with details of Data Service Appointment service provider response and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 52 | BP003B | 85 | MHHS-BR-RS-088 | REGS | IF-035 | [DSAppRejected] | DIP | REGS sends IF-035 for Rejected Appointment - to DIP confirming update | http 201 response from DIP | N
|  | 53 | BP003B | 90 |  | DIP | PUB-035 | [DSAppRejected] | SUPC, SDSI | DIP sends PUB-035 to SUPC and SDSI |  | N
|  | 54 | BP003B | 95 | MHHS-BR-SU-036 | DIP | PUB-035 | [DSAppRejected] | SUPC | Supplier receives PUB-035 with detail of the service providers response to the appointment. | Supplier receives PUB-035 with Registration Service Appointment Status Notification and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| Lapsed DS Appointment Amendment - End | 55 | BP003B | 96 | MHHS-BR-DS-012.1 | DIP | PUB-035 | [DSAppRejected] | SDSI | SDS (Incoming) receives PUB-035 confirming Registrations received the response to the appointment | Data Service receives PUB-035 with Registration Service Appointment Status Notification and confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y

## DPCache_List of Test Scenarios (hidden)
Test Category | Test Scenario | Scenario Title | Test Cases Link | Test ID | Test Scenario Link | Status Date | Status | Test Title | Priority | Pre-Requisite Test Scenario
Advisory Notification | E2E-001 | SITFTS-001 - Advisory Notification | Click to See Test Cases | E2E-001 | Click to view Test | 2023-02-09 | WG Reviewed (Working Group Drops)​ | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Advisory Notification | E2E-E004 | E2E-E004 - Advisory Notification | Click to See Test Cases | E2E-004 |  |  |  | Switch Request Objection - Dual Fuel | Medium | NA
Switch Request Objection | E2E-G006 |  | Click to See Test Cases | E2E-006 |  |  |  | Switch Request Objection - Dual Fuel | Medium | NA
Switch Request Objection | E2E-E007 | E2E-E007 - Switch Request Objection | Click to See Test Cases | E2E-007 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Switch Request Objection | E2E-D008 |  | Click to See Test Cases | E2E-008 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Switch Request Successful | E2E-G012 | E2E-G012 - Switch Request Successful | Click to See Test Cases | E2E-012 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | High | NA
Switch Request Successful | E2E-E011 |  | Click to See Test Cases | E2E-011 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | High | NA