## Change Control
Change Record
Date | Author | Version | Change Detail
2023-11-08 | SI Test Team | v5.2.1 | Consultation issue.
Document Approval
Reviewer/Approver | Role
SI Test Team | Internal review
Adrian Ackroyd | Approval ahead of industry review (including review by SRO Design Team)
Code Bodies | Approval ahead of industry review
SITWG | Recommendation to TMAG (with reference to Interval participants sub-group consultation and assurance)
TMAG | Approval (with reference to Interval participants sub-group consultation and assurance)
References
Reference | Documents | Publisher | Version | Additional Information
CIT Scenarios 5.2.2 |  |  | 5.2.2 | CIT Test Scenarios v5.2.2
Design Interim Release 2 | MHHSP-DES138-Interface Catalogue |  | v5.2.1 | MHHSP DES138 Interface Catalogue v5.2.1
SIT Component Integration Test Approach & Plan | MHHS-DEL1258 SIT Component Integration Test Approach & Plan |  | v1.0 | SIT CIT Test Approach & Plan v1.0
Terminology
Term | Description
For terminology, see programme glossary on the MHHS portal

## Cover Page
CIT Test Cases: Batch 3, Interval 6, UMSDS
Document owner | Document number | Version
SI Test Team | MHHS-DEL1902 | 5.2.1
Status: | Date | Classification
Draft | 2023-11-08 | Public

## CIT Overview
SIT Component Integration SIT Component Integration Testing (SIT CIT) is described in the SIT CIT Test Approach & Plan. Please refer to this before reading the rest of this document. Component systems/services will be integrated one at a time or in small groups. SIT CIT will be conducted on a bi-lateral basis between the SI Test Team and the organisation responsible for each component being integrated, with messages being exchanged between special end-points set up by the SI Test Team and the service being integrated. Each role has a set of interfaces and CIT scenarios associated with it. The Test Cases specify for each role the unique messages that collectively establish the coverage that is required to exit CIT. For message sending the test involves the role generating an IF, with the parameters defined in the test case, triggered from the agreed point in their infrastructure. The first key test outcome will be validation that the message has been successfully received at the DIP, having passed DIP validation. The second key test outcome will be validation that the message is successfully routed onwards by the DIP, to the recipient(s) as determined by the routing rules and expected outcome defined in the test case. The routing will be validated by the SI Test Team using pseudo endpoints, emulating the designated recipients. For message receipt, the SI Test Team will initiate that test by sending in the relevant message from a specially created end-point. The key test outcome will be validation that the role has successfully logged/evidenced the message in the recipient system component. Notes on the sheets in this workbook: Test Cases – This sheet contains a list of all the test cases, covering both sending and receiving tests. Scope includes verifying that: - your role can correctly generate messages and send via the DIP; - the DIP correctly routes the messages sent; - your role can successfully receive messages routed to it via the DIP. ADDITIONAL GUIDANCE ON CIT TEST VARIANTS The DES138 specifies a range of variants for Supplier and Service roles (see table below). Each organisation represented in CIT will test on their own, alongside the SI Test team (in Pseudo Organisation roles). Where test cases specify "Sending" and "Current" variants for the organisation under test, these will be treated as the same entity. Maintained / Variable at MPAN Level: SUPC Supplier – Current SUPS Supplier - Sending SUPL Supplier - Linked (Import/Export) XDSC Data Service - Current XDSP Data Service – Proposed * XDSS Data Service - Sending XMSC Metering Service – Current XMSP Metering Service – Proposed * XMSS Metering Service - Sending
MHHS-DEL 1258 SIT Component Integration Test Approach & Plan

## Data Service (hidden)
Sender | Interface | Interface Name | From | Always | Primary | Secondary | Event Code/Conditions
Data Service | MHHSP-IF-028 | Supplier Consumption Amendment Request Response | Data Service |  | Supplier |  | Consumption Element
Data Service | MHHSP-IF-034 | Service Provider Appointment Request Response | Data Service/Metering Service |  |  | REGS | DS App SP Response
Data Service | MHHSP-IF-034 | Service Provider Appointment Request Response | Data Service/Metering Service |  |  | REGS | SDS MDR Update
Data Service | MHHSP-IF-038 | Customer Direct Contract Advisory | Data Service/Metering Service |  |  | REGS | Direct Contact MS Add
Data Service | MHHSP-IF-038 | Customer Direct Contract Advisory | Data Service/Metering Service |  |  | REGS | Direct Contact DS Add
Data Service | MHHSP-IF-038 | Customer Direct Contract Advisory | Data Service/Metering Service |  |  | REGS | Direct Contact MS Remove
Data Service | MHHSP-IF-038 | Customer Direct Contract Advisory | Data Service/Metering Service |  |  | REGS | Direct Contact DS Remove
Data Service | MHHSP-IF-041 | Smart/Advanced Readings | Supplier/Data Service/Metering Service | LDSO |  | SUPC, SDSC, ADSC | DS: ReadingRemv
Data Service | MHHSP-IF-041 | Smart/Advanced Readings | Supplier/Data Service/Metering Service | LDSO |  | SUPC, SDSC, ADSC | DS: ReadingInstl
Data Service | MHHSP-IF-041 | Smart/Advanced Readings | Supplier/Data Service/Metering Service | LDSO |  | SUPC, SDSC, ADSC | DS: ReadingRemote
Data Service | MHHSP-IF-041 | Smart/Advanced Readings | Supplier/Data Service/Metering Service | LDSO |  | SUPC, SDSC, ADSC | DS: ReadingEnergisationChg, DSEstimate
Data Service | MHHSP-IF-041 | Smart/Advanced Readings | Supplier/Data Service/Metering Service | LDSO |  | SUPC, SDSC, ADSC | DS: DSEstimate
Data Service | MHHSP-IF-041 | Smart/Advanced Readings | Supplier/Data Service/Metering Service | LDSO |  | SUPC, SUPO, SDSC, SDSO | SDS: ReadingCOS,
Data Service | MHHSP-IF-041 | Smart/Advanced Readings | Supplier/Data Service/Metering Service | LDSO |  | SUPC, SUPO, SDSC, SDSO | SDS: ReadingOnSite

## Helix orig. (hidden)
T/C/Ref | Participant | Interval | Pre-requisites | Segment | Interface | IF_PUB | Event Code | Data Conditions | Sender | PP Routing | Step | Test Steps | Expected Results | DATA
| Helix | 2 |  | S | IF-001 |  | ChangeOfSupplier | N/A | REGS | MDS |  | DIP sends PUB-001 ChangeOfSupplier to MDS | MDS receives PUB-001 ChangeOfSupplier from DIP
| Helix | 2 |  | S | IF-001 |  | InitialRegistration | N/A | REGS | MDS |  | DIP sends PUB-001 InitialRegistration to MDS | MDS receives PUB-001 InitialRegistration from DIP
| Helix | 2 |  | S | IF-008 |  | EnergisationStatusChange | DI-979 = A | REGS | MDS |  | DIP sends out PUB-008 EnergisationStatusChange to MDS | MDS receives PUB-008 EnergisationStatusChange from DIP
| Helix | 2 |  | A | IF-008 |  | EnergisationStatusChange | DI-979 = A | REGS | MDS |  | DIP sends out PUB-008 EnergisationStatusChange to MDS | MDS receives PUB-008 EnergisationStatusChange from DIP
| Helix | 2 |  | U | IF-008 |  | EnergisationStatusChange | DI-979 = A | REGS | MDS |  | DIP sends out PUB-008 EnergisationStatusChange to MDS | MDS receives PUB-008 EnergisationStatusChange from DIP
| Helix | 2 |  | S | IF-009 |  | CSSDeRegistration |  |  |  |  | DIP sends out PUB-009 CSSDeRegistration to MDS | MDS receives PUB-009 CSSDeRegistration from DIP
| Helix | 2 |  | A | IF-009 |  | CSSDeRegistration | N/A | REGS | MDS |  | DIP sends out PUB-009 CSSDeRegistration to MDS | MDS receives PUB-009 CSSDeRegistration from DIP
| Helix | 1 |  | A | IF-013 |  | ActivePowerDefaulted | DI-015 <> W | MDS |  |  | MDS sends out IF-013 ActivePowerDefaulted & DI-015 <> 'W' to DIP DIP receives IF-013 ActivePowerDefaulted & DI-015 <> 'W' and routes to SI Pseudo Org (SUPS) End-Point, SI Pseudo Org LDSO End-Point​ and SI Pseudo Org ADS End-Point | DIP sends PUB to Routing PP (SI as no LDSO until Int 5)
| Helix | 1 |  | U | IF-013 |  | ActivePowerDefaulted | DI-015 <> W | MDS |  |  | MDS sends out IF-013 ActivePowerDefaulted & DI-015 <> 'W' to DIP | DIP sends PUB to Routing PP (LDSO)
| Helix | 1 |  | S | IF-013 |  | ActivePowerDefaulted | DI-015 = W | MDS |  |  | MDS sends out IF-013 ActivePowerDefaulted & DI-015 = 'W' to DIP | DIP sends PUB to Routing PP
| Helix | 1 |  | A | IF-014 |  | ActivePowerRejected | DI-015 <> W | MDS |  |  | MDS sends out IF-014 ActivePowerRejected & DI-015 <> 'W' to DIP | DIP sends PUB to Routing PP (LDSO)
| Helix | 1 |  | U | IF-014 |  | ActivePowerRejected | DI-015 <> W | MDS |  |  | MDS sends out IF-014 ActivePowerRejected & DI-015 <> 'W' to DIP | DIP sends PUB to Routing PP (LDSO)
| Helix | 1 |  | S | IF-014 |  | ActivePowerRejected | DI-015 = W | MDS |  |  | MDS sends out IF-014 ActivePowerRejected & DI-015 = 'W' to DIP | DIP sends PUB to Routing PP
| Helix | 1 |  | S | IF-014 |  | ConsumptionOnDeEnergisedMPAN |  | MDS |  |  | MDS sends out IF-014 ConsumptionOnDeEnergisedMPAN to DIP | DIP sends PUB to Routing PP (LDSO)
| Helix | 1 |  | A | IF-014 |  | ConsumptionOnDeEnergisedMPAN |  | MDS |  |  | MDS sends out IF-014 ConsumptionOnDeEnergisedMPAN to DIP | DIP sends PUB to Routing PP (LDSO)
| Helix | 1 |  | U | IF-014 |  | ConsumptionOnDeEnergisedMPAN |  | MDS |  |  | MDS sends out IF-014 ConsumptionOnDeEnergisedMPAN to DIP | DIP sends PUB to Routing PP
| Helix | 2 |  | S | IF-018 |  | GSPChg |  | REGS | MDS |  | DIP sends PUB-018 GSPChg to MDS | MDS receives PUB-018 GSPChg from DIP
| Helix | 2 |  | A | IF-018 |  | GSPChg |  | REGS | MDS |  | DIP sends PUB-018 GSPChg to MDS | MDS receives PUB-018 GSPChg from DIP
| Helix | 2 |  | U | IF-018 |  | GSPChg |  | REGS | MDS |  | DIP sends PUB-018 GSPChg to MDS | MDS receives PUB-018 GSPChg from DIP
| Helix | 2 |  | S | IF-018 |  | DOMPremInd |  | REGS | MDS |  | DIP sends PUB-018 DOMPremInd to MDS | MDS receives PUB-018 DOMPremInd from DIP
| Helix | 2 |  | A | IF-018 |  | DOMPremInd |  | REGS | MDS |  | DIP sends PUB-018 DOMPremInd to MDS | MDS receives PUB-018 DOMPremInd from DIP
| Helix | 2 |  | U | IF-018 |  | DOMPremInd |  | REGS | MDS |  | DIP sends PUB-018 DOMPremInd to MDS | MDS receives PUB-018 DOMPremInd from DIP
| Helix | 2 |  | S | IF-018 |  | DUOSTariffIDChg |  | REGS | MDS |  | DIP sends PUB-018 DUOSTariffIDChg to MDS | MDS receives PUB-018 DUOSTariffIDChg from DIP
| Helix | 2 |  | A | IF-018 |  | DUOSTariffIDChg |  | REGS | MDS |  | DIP sends PUB-018 DUOSTariffIDChg to MDS | MDS receives PUB-018 DUOSTariffIDChg from DIP
| Helix | 2 |  | U | IF-018 |  | DUOSTariffIDChg |  | REGS | MDS |  | DIP sends PUB-018 DUOSTariffIDChg to MDS | MDS receives PUB-018 DUOSTariffIDChg from DIP
| Helix | 2 |  | S | IF-018 |  | EnergyDirection |  | REGS | MDS |  | DIP sends PUB-018 EnergyDirection to MDS | MDS receives PUB-018 EnergyDirection from DIP
| Helix | 2 |  | A | IF-018 |  | EnergyDirection |  | REGS | MDS |  | DIP sends PUB-018 EnergyDirection to MDS | MDS receives PUB-018 EnergyDirection from DIP
| Helix | 2 |  | U | IF-018 |  | EnergyDirection |  | REGS | MDS |  | DIP sends PUB-018 EnergyDirection to MDS | MDS receives PUB-018 EnergyDirection from DIP
| Helix | 3 |  | S | IF-021 |  | ActivePower | DI-015 = W | SDSS | MDS |  | DIP sends PUB-021 ActivePower DI-015 = W | MDS receives PUB-021 ActivePower from DIP
| Helix | 3 |  | A | IF-021 |  | ActivePower | DI-015 <> W | ADSS | MDS |  | DIP sends PUB-021 ActivePower DI-015 <> W | MDS receives PUB-021 ActivePower from DIP
| Helix | 3 |  | U | IF-021 |  | ActivePower | DI-015 <> W | UMSDS | MDS |  | DIP sends PUB-021 ActivePower DI-015 <> W | MDS receives PUB-021 ActivePower from DIP
| Helix | 1 |  | S | IF-022 |  | LSSPeriodData |  | LSS |  |  | LSS sends IF-022 LSSPeriodData to DIP | DIP sends PUB-022 LSSPeriodData to routing parties
| Helix | 1 |  | A | IF-022 |  | LSSPeriodData |  | LSS |  |  | LSS sends IF-022 LSSPeriodData to DIP | DIP sends PUB-022 LSSPeriodData to routing parties
| Helix | 1 |  | U | IF-022 |  | LSSPeriodData |  | LSS |  |  | LSS sends IF-022 LSSPeriodData to DIP | DIP sends PUB-022 LSSPeriodData to routing parties
| Helix | 1 |  | S | IF-023 |  | LSSTotalsData |  | LSS |  |  | LSS sends IF-023 LSSTotalsData to DIP | DIP sends PUB-023 LSSTotalsData to routing parties
| Helix | 1 |  | A | IF-023 |  | LSSTotalsData |  | LSS |  |  | LSS sends IF-023 LSSTotalsData to DIP | DIP sends PUB-023 LSSTotalsData to routing parties
| Helix | 2 |  | S | IF-026 |  | SSCandProfileClass | DI-979 <> 'R' | REGS | LSS |  | DIP sends PUB-026 SSCandProfileClass DI-979 <> 'R' to LSS | LSS receives PUB-026 SSCandProfileClass DI-979 <> 'R' from DIP
| Helix | 2 |  | A | IF-026 |  | SSCandProfileClass | DI-979 <> 'R' | REGS | LSS |  | DIP sends PUB-026 SSCandProfileClass DI-979 <> 'R' to LSS | LSS receives PUB-026 SSCandProfileClass DI-979 <> 'R' from DIP
| Helix | 2 |  | S | IF-036 |  | DSAppActive |  | REGS | MDS |  | DIP sends PUB-036 DSAppActive to MDS | MDS receives PUB-036 DSAppActive from DIP
| Helix | 2 |  | A | IF-036 |  | DSAppActive |  | REGS | MDS |  | DIP sends PUB-036 DSAppActive to MDS | MDS receives PUB-036 DSAppActive from DIP
| Helix | 2 |  | U | IF-036 |  | DSAppActive |  | REGS | MDS |  | DIP sends PUB-036 DSAppActive to MDS | MDS receives PUB-036 DSAppActive from DIP
| Helix | 2 |  | S | IF-037 |  | DSDeApp |  | REGS | MDS |  | DIP sends PUB-037 DSDeApp to MDS | MDS receives PUB-037 DSDeApp from DIP
| Helix | 2 |  | A | IF-038 |  | DSDeApp |  | REGS | MDS |  | DIP sends PUB-037 DSDeApp to MDS | MDS receives PUB-037 DSDeApp from DIP
| Helix | 2 |  | U | IF-039 |  | DSDeApp |  | REGS | MDS |  | DIP sends PUB-037 DSDeApp to MDS | MDS receives PUB-037 DSDeApp from DIP
| Helix | 1 |  | S | IF-040 |  | AnnualConsumption |  | MDS |  |  | MDS sends IF-040 AnnualConsumption to DIP | DIP sends PUB-040 AnnualConsumption to routing parties
| Helix | 1 |  | A | IF-040 |  | AnnualConsumption |  | MDS |  |  | MDS sends IF-040 AnnualConsumption to DIP | DIP sends PUB-040 AnnualConsumption to routing parties
| Helix | 2 |  | S | IF-043 |  | ConnectionTypeChange |  | REGS | MDS |  | DIP sends PUB-043 ConnectionTypeChange to MDS | MDS receives PUB-043 ConnectionTypeChange from DIP
| Helix | 2 |  | A | IF-043 |  | ConnectionTypeChange |  | REGS | MDS |  | DIP sends PUB-043 ConnectionTypeChange to MDS | MDS receives PUB-043 ConnectionTypeChange from DIP
| Helix | 2 |  | S | IF-044 |  | MarketSegmentChange |  | REGS | MDS |  | DIP sends PUB-044 MarketSegmentChange to MDS | MDS receives PUB-044 MarketSegmentChange from DIP
| Helix | 2 |  | A | IF-044 |  | MarketSegmentChange |  | REGS | MDS |  | DIP sends PUB-044 MarketSegmentChange to MDS | MDS receives PUB-044 MarketSegmentChange from DIP
| Helix | 1 |  | S | IF-047 |  | ISD |  | ISD | MDS, LSS, VAS |  | TBC | TBC
| Helix | 1 |  | A | IF-047 |  | ISD |  | ISD | MDS, LSS, VAS |  | TBC | TBC
| Helix | 1 |  | U | IF-047 |  | ISD |  | ISD | MDS, LSS, VAS |  | TBC | TBC

## Test Cases
T/C/Ref | Status | Reason | Out of Scope | Reason | Interval | Pre-requisites | Test Execution Constraints | Segment | Interface | IF/PUB | Event Code | Data Conditions | Sender | Routing Category | Step # | Actors | Test Steps | Expected Results | Data Condition Value
Ref#057b MHHSP-IF-008 TC#01 |  |  |  | PUB | 6 |  |  | Unmetered | IF-008 | IF | EnergisationStatusChange | DI-979 = 'A' | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-008 EnergisationStatusChange & DI-979='A' to DIP | DIP Queue successfully receives IF-008 EnergisationStatusChange & R0 - DI-979 = A, Accept from PEP REGS | R0 - DI-979 = A, Accept
Ref#061b MHHSP-IF-013 TC#01 |  |  |  | PUB | 6 |  |  | Unmetered | IF-013 | IF | ActivePowerDefaulted | DI-015 <> W | PEP MDS |  | 1 | SI Test Analyst(s) | PEP MDS sends IF-013 ActivePowerDefaulted & DI-015 <> 'W' to DIP | DIP Queue successfully receives IF-013 ActivePowerDefaulted & B067 - DI-015 = U from PEP MDS | B067 - DI-015 = U
Ref#063b MHHSP-IF-014 TC#01 |  |  |  | PUB | 6 |  |  | Unmetered | IF-014 | IF | ActivePowerRejected | DI-015 <> W | PEP MDS |  | 1 | SI Test Analyst(s) | PEP MDS sends IF-014 ActivePowerRejected & DI-015 <> 'W' to DIP | DIP Queue successfully receives IF-014 ActivePowerRejected & B067 DI-015 = U from PEP MDS | B067 - DI-015 = U
Ref#065b MHHSP-IF-014 TC#01 |  |  |  | Revised based on Secondary Routing | 6 |  |  | Unmetered | IF-014 | IF | ConsumptionOnDeEnergisedMPAN |  | PEP MDS |  | 1 | SI Test Analyst(s) | PEP MDS sends out IF-014 ConsumptionOnDeEnergisedMPAN to DIP | DIP Queue successfully receives IF-014 ConsumptionOnDeEnergisedMPAN from PEP MDS
Ref#068b MHHSP-IF-018 TC#01 |  |  |  | PUB | 6 |  |  | Unmetered | IF-018 | IF | AddressChg |  | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-018 AddressChg to DIP | DIP Queue successfully receives IF-018 AddressChg from PEP REGS
Ref#070b MHHSP-IF-018 TC#01 |  |  |  | Revised based on Secondary Routing | 6 |  |  | Unmetered | IF-018 | IF | GSPChg |  | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-018 GSPChg to DIP | DIP Queue successfully receives IF-018 GSPChg from PEP REGS
Ref#071b MHHSP-IF-018 TC#01 |  |  |  | Revised based on Secondary Routing | 6 |  |  | Unmetered | IF-018 | IF | DomPremInd |  | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-018 DomPremInd to DIP | DIP Queue successfully receives IF-018 DomPremInd from PEP REGS
Ref#072b MHHSP-IF-018 TC#01 |  |  |  | Revised based on Secondary Routing | 6 |  |  | Unmetered | IF-018 | IF | DUOSTariffIDChg |  | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-018 DUOSTariffIDChg to DIP | DIP Queue successfully receives IF-018 DUOSTariffIDChg from PEP REGS
Ref#073b MHHSP-IF-018 TC#01 |  |  |  | Revised based on Secondary Routing | 6 |  |  | Unmetered | IF-018 | IF | EnergyDirection |  | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-018 EnergyDirection to DIP | DIP Queue successfully receives IF-018 EnergyDirection from PEP REGS
Ref#074b MHHSP-IF-018 TC#01 |  |  |  | Revised based on Secondary Routing | 6 |  |  | Unmetered | IF-018 | IF | MUMIndicator |  | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-018 MUMIndicator to DIP | DIP Queue successfully receives IF-018 MUMIndicator from PEP REGS
Ref#0105 MHHSP-IF-021 TC#01 |  |  |  | IF | 6 | Includes information covering consumption on 2 settlement days |  | Unmetered | IF-021 | IF | ActivePower | DI-015 <> W | UMSDSS |  | 1 | UMSDS Test Analyst(s), SI Test Analyst(s) | UMSDSS sends IF-021 ActivePower & DI-015 <> W to DIP | DIP Queue successfully receives IF-021 ActivePower & B067, DI-015 = U from UMSDSS
Ref#0108b MHHSP-IF-022 TC#01 |  |  |  | PUB | 6 |  |  | Unmetered | IF-022 | IF | LSSPeriodData |  | PEP LSS |  | 1 | SI Test Analyst(s) | PEP LSS sends IF-022 LSSPeriodData to DIP | DIP Queue successfully receives IF-022 LSSPeriodData from PEP LSS
Ref#0110b MHHSP-IF-024 TC#01 |  |  |  | PUB | 6 |  |  | Unmetered | IF-024 | IF | SN-Vacant |  | PEP SUPS |  | 1 | SI Test Analyst(s) | PEP SUPS sends IF-024 SN-Vacant to DIP | DIP Queue successfully receives IF-024 SN-Vacant from PEP SUPS
Ref#0111b MHHSP-IF-024 TC#01 |  |  |  | Revised based on Secondary Routing | 6 |  |  | Unmetered | IF-024 | IF | SN-NoComms |  | PEP SUPS |  | 1 | SI Test Analyst(s) | PEP SUPS sends IF-024 SN-NoComms to DIP | DIP Queue successfully receives IF-024 SN-NoComms from PEP SUPS
Ref#0112b MHHSP-IF-024 TC#01 |  |  |  | Revised based on Secondary Routing | 6 |  |  | Unmetered | IF-024 | IF | SN-RemoteEnabled |  | PEP SUPS |  | 1 | SI Test Analyst(s) | PEP SUPS sends IF-024 SN-RemoteEnabled to DIP | DIP Queue successfully receives IF-024 SN-RemoteEnabled from PEP SUPS
Ref#0113b MHHSP-IF-024 TC#01 |  |  |  | Revised based on Secondary Routing | 6 |  |  | Unmetered | IF-024 | IF | SN-RemoteDisabled |  | PEP SUPS |  | 1 | SI Test Analyst(s) | PEP SUPS sends IF-024 SN-RemoteDisabled to DIP | DIP Queue successfully receives IF-024 SN-RemoteDisabled from PEP SUPS
Ref#0114b MHHSP-IF-024 TC#01 |  |  |  | Revised based on Secondary Routing | 6 |  |  | Unmetered | IF-024 | IF | SN-SupplierAC |  | PEP SUPS |  | 1 | SI Test Analyst(s) | PEP SUPS sends IF-024 SN-SupplierAC to DIP | DIP Queue successfully receives IF-024 SN-SupplierAC from PEP SUPS
Ref#127b MHHSP-IF-027 TC#01 |  |  |  | PUB | 6 |  |  | Unmetered | IF-027 | IF | ConsumptionAmendment |  | PEP SUPS |  | 1 | SI Test Analyst(s) | PEP SUPS sends IF-027 ConsumptionAmendment to DIP | DIP Queue successfully receives IF-027 ConsumptionAmendment from PEP SUPS
Ref#0128b MHHSP-IF-028 TC#01 |  |  |  | IF | 6 |  |  | Unmetered | IF-028 | IF | ConsumptionAmendment |  | UMSDSS |  | 1 | UMSDS Test Analyst(s), SI Test Analyst(s) | UMSDSS sends IF-028 ConsumptionAmendment to DIP | DIP Queue successfully receives IF-028 ConsumptionAmendmentfrom UMSDSS
Ref#0136b MHHSP-IF-033 TC#01 |  |  |  | PUB | 6 |  |  | Unmetered | IF-033 | IF | DSAppSPRequest |  | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-033 DSAppSPRequest to DIP | DIP Queue successfully receives IF-033 DSAppSPRequest from PEP REGS
Ref#0137d MHHSP-IF-034 TC#01 |  |  |  | IF | 6 |  |  | Unmetered | IF-034 | IF | DSAppSPResponse |  | UMSDSS |  | 1 | UMSDS Test Analyst(s), SI Test Analyst(s) | UMSDSS sends IF-034 DSAppSPResponse to DIP | DIP Queue successfully receives IF-034 DSAppSPResponse from UMSDSS
Ref#0146b MHHSP-IF-035 TC#01 |  |  |  | PUB | 6 |  |  | Unmetered | IF-035 | IF | DSAppAccepted |  | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-035 DSAppAccepted to DIP | DIP Queue successfully receives IF-035 DSAppAccepted from PEP REGS
Ref#0147b MHHSP-IF-035 TC#01 |  |  |  | Revised based on Secondary Routing | 6 |  |  | Unmetered | IF-035 | IF | DSAppRejected |  | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-035 DSAppRejected to DIP | DIP Queue successfully received IF-035 DSAppRejected from PEP REGS
Ref#0148b MHHSP-IF-035 TC#01 |  |  |  | Revised based on Secondary Routing | 6 |  |  | Unmetered | IF-035 | IF | DSAppLapsed |  | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-035 DSAppLapsed to DIP | DIP Queue successfully receives IF-035 DSAppLapsed from PEP REGS
Ref#0154b MHHSP-IF-036 TC#01 |  |  |  | PUB | 6 |  |  | Unmetered | IF-036 | IF | MSAppActive |  | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-036 MSAppActive to DIP | DIP Queue successfully receives IF-036 MSAppActive from PEP REGS
Ref#0155b MHHSP-IF-036 TC#01 |  |  |  | Revised based on Secondary Routing | 6 |  |  | Unmetered | IF-036 | IF | DSAppActive |  | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-036 DSAppActive to DIP | DIP Queue successfully receives IF-036 DSAppActive from PEP REGS
Ref#0157b MHHSP-IF-037 TC#01 |  |  |  | PUB | 6 |  |  | Unmetered | IF-037 | IF | DSDeApp |  | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-037 DSDeApp to DIP | DIP Queue successfully receives IF-037 DSDeApp from PEP REGS
Ref#0159b MHHSP-IF-037 TC#01 |  |  |  | Revised based on Secondary Routing | 6 |  |  | Unmetered | IF-037 | IF | DSDeAppUpdate |  | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-037 DSDeAppUpdate to DIP | DIP Queue successfully receives IF-037 DSDeAppUpdate from PEP REGS
Ref#0161a MHHSP-IF-038 TC#01 |  |  |  | IF | 6 |  |  | Unmetered | IF-038 | IF | DirectContractDSAdd |  | UMSDSS |  | 1 | UMSDS Test Analyst(s), SI Test Analyst(s) | UMSDSS sends IF-038 DirectContractDSAdd to DIP | DIP Queue successfully receives IF-038 DirectContractDSAdd from UMSDSS
Ref#0163a MHHSP-IF-038 TC#01 |  |  |  | Revised based on Secondary Routing | 6 |  |  | Unmetered | IF-038 | IF | DirectContractDSRemove |  | UMSDSS |  | 1 | UMSDS Test Analyst(s), SI Test Analyst(s) | UMSDSS sends IF-038 DirectContractDSRemove to DIP | DIP Queue successfully receives IF-038 DirectContractDSRemove from UMSDSS
Ref#0169b MHHSP-IF-039 TC#01 |  |  |  | PUB | 6 |  |  | Unmetered | IF-039 | IF | DirectContractDSAdd | DI-979='A' | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-039 DirectContractDSAdd DI-979='A' to DIP | DIP Queue successfully receives IF-039 DirectContractDSAdd & R0 - DI-979 = A, Accept from PEP REGS | R0 - DI-979 = A, Accept
Ref#0171b MHHSP-IF-039 TC#01 |  |  |  | Revised based on Secondary Routing | 6 |  |  | Unmetered | IF-039 | IF | DirectContractDSRemove |  | PEP REGS |  | 1 | SI Test Analyst(s) | PEP REGS sends IF-039 DirectContractDSRemove to DIP | DIP Queue successfully receives IF-039 DirectContractDSRemove from PEP REGS
Ref#0205 MHHSP-IF-047 TC#01 |  |  |  | PUB | 6 |  |  | Unmetered | IF-047 | IF | ISD |  | PEP Central Settlements |  | 1 | SI Test Analyst(s) | PEP Central Settlements sends IF-047 ISD to DIP | DIP Queue successfully receives IF-047 ISD from PEP Central Settlements