## How To Use NEW (hidden)
How To Use
1. How to navigate this document
This section aims to provide an overview on how to navigate through this workbook. It consists of a number of worksheets that are arranged in a heirarchy, working from left to right. The 'List of Test Scenarios' provides an overview view of the scenarios that are included within this phase of testing. Within this worksheet each scenario has a link 'Click to see Test', which when selected, will take the user to a detailed view of the test scenario. This worksheet provides an overview of the test description, mapped requirements and will provide a list of all associated unique test cases. The 'List of Test Cases' gives the user the ability to view a list of test cases in scope and their associated test scenarios. This also includes a view of each attribute that makes up the test case and consists of the following:
Attributes
Meter Type | Trad, Smart, Advanced, Unmetered
Supplier (Outgoing)
Supplier (Incoming)
CSS
Registration Service
DIP
Central Settlement
LDSO
Metering Service
EES
For easy navigation, within each of the main tabs the user will be presented with links to other areas of the workbook. These include 'Click to view Test' and 'Click to view Test Case'. These will direct the user to a detailed view of the test scenario, or will direct them back to the Link of Test Cases worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Detailed Scenarios

## Front Cover (hidden)
SWITCHING PROGRAMME
E2E Test Scenarios
Reference: NCT-0045
Version: v0.3

## Change Control (hidden)
Confidentiality Statement
The information contained herein is for the purpose of the MHHS Programme. This document may not be copied, or communicated to a third party, or used, for any purpose other than that for which it is supplied without the express written consent of the MHHS Programme
Distribution List
Name | Organisation
Document History
Issue No. | Issue Date | Issued by | Change Description
0.1 | 2023-02-10 | Dean Bailey | First Draft & QA Checked
Reviewed By
Version | Date | Name | Title / Responsibility
0.1
Approvals
Version | Date | Name | Title / Responsibility

## Sheet1 (hidden)
(empty)

## Sheet2 (hidden)
Data returned for Distinct Count of Profile, 1 - Dual (First 1000 rows).
ListTestCases[Test Case Category] | ListTestCases[E2E Scenario] | ListTestCases[Test Case Id] | ListTestCases[Test Case Title] | ListTestCases[Domestic] | ListTestCases[Non Domestic] | ListTestCases[Smart] | ListTestCases[Non Smart] | ListTestCases[Associated Test Scenario Id] | ListTestCases[Pre-Requisite Test Case] | ListTestCases[Regression Tests] | ListTestCases[Profile] | ListTestCases[Unique ID]
Switch Request Objection | E2E-D001 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-004-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Objected | X |  |  | X | E2E-004-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D001-SRO_G1
Switch Request Objection | E2E-D001 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters with Primary MPAN) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-004-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Objected |  | X | X |  | E2E-004-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D001-SRO_G2
Switch Request Objection | E2E-D001 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Traditional - Gas, Smart Meter - Electricity)) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X | X | E2E-007-G001 | NA |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  | X | X | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-004-03 | Gaining Supplier - Switch Request for Dual Fuel Domestic (Traditional - Gas, Smart Meter - Electricity) is Objected | X |  | X | X | E2E-004-G001 | E2E-010-03 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_G3
Switch Request Objection | E2E-D001 | E2E-007-04 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-010-04 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-04 |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-004-04 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional Meters) is Objected | X |  |  | X | E2E-004-L001 | E2E-010-04 |  | Domestic Traditional Meter | E2E-D001-SRO_L1
Switch Request Objection | E2E-D001 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters with Primary MPAN) |  | X | X |  | E2E-010-L001 | E2E-007-05 |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-004-05 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters with Primary MPAN) is Objected |  | X | X |  | E2E-004-L001 | E2E-010-05 |  | Non Domestic Smart Meter | E2E-D001-SRO_L2
Switch Request Objection | E2E-D001 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Traditional - Gas, Smart Meter - Electricity) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X | X | E2E-007-L001 | NA |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Objection | E2E-D001 | E2E-010-06 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Traditional - Gas, Smart Meter - Electricity) | X |  | X | X | E2E-010-L001 | E2E-007-06 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Objection | E2E-D001 | E2E-004-06 | Losing Supplier - Switch Request for Dual Fuel Domestic (Traditional - Gas, Smart Meter - Electricity) is Objected | X |  | X | X | E2E-004-L001 | E2E-010-06 |  | Domestic Smart Traditional Meter | E2E-D001-SRO_L3
Switch Request Successful | E2E-D002 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-013-01 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-013-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-016-01 | Gaining Supplier - Post Switch Execution for Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-016-G001 | E2E-013-01 |  | Domestic Traditional Meter | E2E-D002-SRS-G1
Switch Request Successful | E2E-D002 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-013-02 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-013-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-016-02 | Gaining Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-016-G001 | E2E-013-02 |  | Non Domestic Smart Meter | E2E-D002-SRS-G2
Switch Request Successful | E2E-D002 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-G001 | NA |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-013-03 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-013-G001 | E2E-010-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-016-03 | Gaining Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-016-G001 | E2E-013-03 |  | Non Domestic Traditional Meter | E2E-D002-SRS-G3
Switch Request Successful | E2E-D002 | E2E-007-04 | Gaining Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-010-04 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-013-04 | Gaining Supplier - Switch Request Secured Active - Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-013-G001 | E2E-010-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-016-04 | Gaining Supplier - Post Switch Execution for Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-016-G001 | E2E-013-03 |  | Domestic Smart Meter | E2E-D002-SRS-G4
Switch Request Successful | E2E-D002 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-013-05 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-013-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-016-05 | Losing Supplier - Post Switch Execution for Dual Fuel - Traditional Domestic Meters with Primary MPAN | X |  |  | X | E2E-016-L001 | E2E-013-05 |  | Domestic Traditional Meter | E2E-D002-SRS-L1
Switch Request Successful | E2E-D002 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-010-06 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-013-06 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-013-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-016-06 | Losing Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Smart Meters |  | X | X |  | E2E-016-L001 | E2E-013-06 |  | Non Domestic Smart Meter | E2E-D002-SRS-L2
Switch Request Successful | E2E-D002 | E2E-007-07 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-010-07 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-013-07 | Losing Supplier - Switch Request Secured Active - Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-013-L001 | E2E-010-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-016-07 | Losing Supplier - Post Switch Execution for Dual Fuel - Non-Domestic Traditional Meters |  | X |  | X | E2E-016-L001 | E2E-013-07 |  | Non Domestic Traditional Meter | E2E-D002-SRS-L3
Switch Request Successful | E2E-D002 | E2E-007-08 | Losing Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-010-08 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-L001 | E2E-007-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-013-08 | Losing Supplier - Switch Request Secured Active - Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-013-L001 | E2E-010-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Successful | E2E-D002 | E2E-016-08 | Losing Supplier - Post Switch Execution for Dual Fuel - (Domestic Smart Meters) | X |  | X |  | E2E-016-L001 | E2E-013-07 |  | Domestic Smart Meter | E2E-D002-SRS-L4
Switch Request Withdrawal | E2E-D003 | E2E-007-01 | Gaining Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-010-01 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-019-01 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-019-G001 | E2E-10-01 |  | Domestic Traditional Meter | E2E-D003-SRW-G1
Switch Request Withdrawal | E2E-D003 | E2E-007-02 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-010-02 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-019-02 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-019-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D003-SRW-G2
Switch Request Withdrawal | E2E-D003 | E2E-007-03 | Gaining Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-G001 | NA |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-010-03 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-03 |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-019-03 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Traditional) when status is "Confirmed" in CSS |  | X |  | X | E2E-019-G001 | E2E-010-03 |  | Non Domestic Traditional Meter | E2E-D003-SRW-G3
Switch Request Withdrawal | E2E-D003 | E2E-007-04 | Gaining Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-010-04 | Gaining Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-G001 | E2E-007-04 |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-019-04 | Gaining Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Smart Meters) when status is "Confirmed" in CSS | X |  | X |  | E2E-019-G001 | E2E-010-04 |  | Domestic Smart Meter | E2E-D003-SRW-G4
Switch Request Withdrawal | E2E-D003 | E2E-007-05 | Losing Supplier - Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-010-05 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-019-05 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-019-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D003-SRW-L1
Switch Request Withdrawal | E2E-D003 | E2E-007-06 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-010-06 | LosingSupplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-019-06 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-019-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D003-SRW-L2
Switch Request Withdrawal | E2E-D003 | E2E-007-07 | Losing Supplier - Switch Request for Dual Fuel (Non-Domestic Traditional meters) is Confirmed in CSS after no objection received from Losing Supplier |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-010-07 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-07 |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-019-07 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Non-Domestic Traditional) when status is "Confirmed" in CSS |  | X |  | X | E2E-019-L001 | E2E-010-07 |  | Non Domestic Traditional Meter | E2E-D003-SRW-L3
Switch Request Withdrawal | E2E-D003 | E2E-007-08 | Losing Supplier - Switch Request for Dual Fuel (Domestic Smart meters) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Withdrawal | E2E-D003 | E2E-010-08 | Losing Supplier - MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meters) | X |  | X |  | E2E-010-L001 | E2E-007-08 |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Withdrawal | E2E-D003 | E2E-019-08 | Losing Supplier - Switch Request Withdrawal - Dual Fuel (Domestic Smart Meters) when status is "Confirmed" in CSS | X |  | X |  | E2E-019-L001 | E2E-010-08 |  | Domestic Smart Meter | E2E-D003-SRW-L4
Switch Request Annulment | E2E-D004 | E2E-007-01 | Gaining Supplier- Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-G001 | NA |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-010-01 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-G001 | E2E-007-01 |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-022-01 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-022-G001 | E2E-010-01 |  | Domestic Traditional Meter | E2E-D004-SRA-G1
Switch Request Annulment | E2E-D004 | E2E-007-02 | Gaining Supplier- Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-G001 | NA |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-010-02 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-G001 | E2E-007-02 |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-022-02 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-022-G001 | E2E-010-02 |  | Non Domestic Smart Meter | E2E-D004-SRA-G2
Switch Request Annulment | E2E-D004 | E2E-007-03 | Gaining Supplier- Switch Request for Dual Fuel (Domestic, Smart meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-G001 | NA |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-010-03 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Smart Meter with Primary MPAN) | X |  | X |  | E2E-010-G001 | E2E-007-03 |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-022-03 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Domestic Smart Meters with Primary MPAN) when status is "Pending" in CSS | X |  | X |  | E2E-022-G001 | E2E-010-03 |  | Domestic Smart Meter | E2E-D004-SRA-G3
Switch Request Annulment | E2E-D004 | E2E-007-04 | Gaining Supplier- Switch Request for Dual Fuel (Non-Domestic, Traditional Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X |  | X | E2E-007-G001 | NA |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-010-04 | Gaining Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic,Traditional Meters) |  | X |  | X | E2E-010-G001 | E2E-007-04 |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-022-04 | Gaining Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Traditional Meters) when status is "Confirmed" in CSS |  | X |  | X | E2E-022-G001 | E2E-010-04 |  | Non DomesticTraditional Meter | E2E-D004-SRA-G4
Switch Request Annulment | E2E-D004 | E2E-007-05 | Losing Supplier- Switch Request for Dual Fuel (Domestic, Traditional meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  |  | X | E2E-007-L001 | NA |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-010-05 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic Traditional Meter with Primary MPAN) | X |  |  | X | E2E-010-L001 | E2E-007-05 |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-022-05 | Losing Supplier- Switch Request Annulment - Dual Fuel (Domestic Traditional Meters with Primary MPAN) when status is "Pending" in CSS | X |  |  | X | E2E-022-L001 | E2E-010-05 |  | Domestic Traditional Meter | E2E-D004-SRA-L1
Switch Request Annulment | E2E-D004 | E2E-007-06 | Losing Supplier- Switch Request for Dual Fuel (Non-Domestic, Smart Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X | X |  | E2E-007-L001 | NA |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-010-06 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Smart Meters) |  | X | X |  | E2E-010-L001 | E2E-007-06 |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-022-06 | Losing Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Smart Meters) when status is "Confirmed" in CSS |  | X | X |  | E2E-022-L001 | E2E-010-06 |  | Non Domestic Smart Meter | E2E-D004-SRA-L2
Switch Request Annulment | E2E-D004 | E2E-007-07 | Losing Supplier- Switch Request for Dual Fuel (Domestic, Smart meters, Primary MPAN) is Confirmed in CSS after no objection received from Losing Supplier | X |  | X |  | E2E-007-L001 | NA |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-010-07 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Domestic smart Meter with Primary MPAN) | X |  | X |  | E2E-010-L001 | E2E-007-07 |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-022-07 | Losing Supplier- Switch Request Annulment - Dual Fuel (Domestic Smart Meters with Primary MPAN) when status is "Pending" in CSS | X |  | X |  | E2E-022-L001 | E2E-010-07 |  | Domestic Smart Meter | E2E-D004-SRA-L3
Switch Request Annulment | E2E-D004 | E2E-007-08 | Losing Supplier- Switch Request for Dual Fuel (Non-Domestic, Traditional Meters) is Confirmed in CSS and objection received from Losing Supplier outside objection window |  | X |  | X | E2E-007-L001 | NA |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4
Switch Request Annulment | E2E-D004 | E2E-010-08 | Losing Supplier- MPAS and UK Link process on receipt of Pending Synchronisation for Dual Fuel switch (Non-Domestic, Traditional Meters) |  | X |  | X | E2E-010-L001 | E2E-007-08 |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4
Switch Request Annulment | E2E-D004 | E2E-022-08 | Losing Supplier- Switch Request Annulment - Dual Fuel (Non-Domestic Traditional Meters) when status is "Confirmed" in CSS |  | X |  | X | E2E-022-L001 | E2E-010-08 |  | Non Domestic Traditional Meter | E2E-D004-SRA-L4

## Summary (hidden)
Test Scenario View |  |  |  |  | Summary
Priority | Fuel Type | E2E Scenario | Profile | Test Cases | Priority | Fuel Type | Profile | Distinct Count of Profile | Distinct Count of E2E Scenario | Test Cases
1 |  |  |  |  | 1
| All |  |  |  |  | All
|  | E2E-GED-001 |  |  |  |  | Domestic, Smart Meter | 1 | 1 | 6
|  |  | Domestic, Smart Meter | 6 |  |  | Domestic, Traditional Meter | 1 | 1 | 4
|  |  | Domestic, Traditional Meter | 4 |  |  | Non Domestic, Smart Meter | 1 | 1 | 3
|  |  | Non Domestic, Smart Meter | 3 |  |  | Non Domestic, Traditional Meter | 1 | 1 | 5
|  |  | Non Domestic, Traditional Meter | 5 |  | All Total |  | 4 | 1 | 18
|  | E2E-GED-001 Total |  | 18 |  | Dual
| All Total |  |  | 18 |  |  | Domestic, Smart Meter | 1 | 4 | 14
| Dual | [5 empty] | Domestic, Traditional Meter | 1 | 4 | 14
|  | E2E-D001 |  |  |  |  | Non Domestic, Smart Meter | 1 | 4 | 14
|  |  | Domestic, Smart Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 4 | 14
|  |  | Domestic, Traditional Meter | 2 |  | Dual Total |  | 4 | 4 | 56
|  |  | Non Domestic, Smart Meter | 2 |  | Electricity
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Domestic, Smart Meter | 1 | 6 | 18
|  | E2E-D001 Total |  | 8 |  |  | Domestic, Traditional Meter | 1 | 6 | 16
|  | E2E-D002 |  |  |  |  | Non Domestic, Smart Meter | 1 | 6 | 20
|  |  | Domestic, Smart Meter | 8 |  |  | Non Domestic, Traditional Meter | 1 | 6 | 16
|  |  | Domestic, Traditional Meter | 8 |  | Electricity Total |  | 4 | 6 | 70
|  |  | Non Domestic, Smart Meter | 8 |  | Gas
|  |  | Non Domestic, Traditional Meter | 8 |  |  | Domestic, Smart Meter | 1 | 7 | 17
|  | E2E-D002 Total |  | 32 |  |  | Domestic, Traditional Meter | 1 | 7 | 17
|  | E2E-D003 |  |  |  |  | Non Domestic, Smart Meter | 1 | 7 | 21
|  |  | Domestic, Smart Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 7 | 17
|  |  | Domestic, Traditional Meter | 2 |  | Gas Total |  | 4 | 7 | 72
|  |  | Non Domestic, Smart Meter | 2 |  | SMS
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Service management | 1 | 1 | 7
|  | E2E-D003 Total |  | 8 |  | SMS Total |  | 1 | 1 | 7
|  | E2E-D004 |  |  | 1 Total |  |  | 5 | 19 | 223
|  |  | Domestic, Smart Meter | 2 | 2
|  |  | Domestic, Traditional Meter | 2 |  | Dual
|  |  | Non Domestic, Smart Meter | 2 |  |  | Domestic, Smart Meter | 1 | 2 | 6
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Domestic, Traditional Meter | 1 | 1 | 4
|  | E2E-D004 Total |  | 8 |  |  | Non Domestic, Smart Meter | 1 | 1 | 4
| Dual Total |  |  | 56 |  |  | Non Domestic, Traditional Meter | 1 | 1 | 4
| Electricity |  |  |  |  | Dual Total |  | 4 | 2 | 18
|  | E2E-E001 |  |  |  | Electricity
|  |  | Domestic, Smart Meter | 2 |  |  | Domestic, Smart Meter | 1 | 10 | 15
|  |  | Domestic, Traditional Meter | 2 |  |  | Domestic, Traditional Meter | 1 | 10 | 14
|  |  | Non Domestic, Smart Meter | 4 |  |  | Non Domestic, Smart Meter | 1 | 9 | 14
|  |  | Non Domestic, Traditional Meter | 2 |  |  | Non Domestic, Traditional Meter | 1 | 9 | 13
|  | E2E-E001 Total |  | 10 |  | Electricity Total |  | 4 | 11 | 54
|  | E2E-E002 |  |  |  | Gas
|  |  | Domestic, Smart Meter | 10 |  |  | Domestic, Smart Meter | 1 | 11 | 16
|  |  | Domestic, Traditional Meter | 8 |  |  | Domestic, Traditional Meter | 1 | 10 | 14
|  |  | Non Domestic, Smart Meter | 10 |  |  | Non Domestic, Smart Meter | 1 | 8 | 13
|  |  | Non Domestic, Traditional Meter | 8 |  |  | Non Domestic, Traditional Meter | 1 | 8 | 11
|  | E2E-E002 Total |  | 36 |  | Gas Total |  | 4 | 11 | 54
|  | E2E-E003 |  |  | 2 Total |  |  | 4 | 24 | 126
|  |  | Domestic, Smart Meter | 2 | Grand Total |  |  | 5 | 43 | 349
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E003 Total |  | 8
E2E-E004
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E004 Total |  | 8
E2E-E005
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E005 Total |  | 4
E2E-E009
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E009 Total |  | 4
| Electricity Total |  |  | 70
Gas
E2E-G001
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G001 Total |  | 10
E2E-G002
|  |  | Domestic, Smart Meter | 8
|  |  | Domestic, Traditional Meter | 8
|  |  | Non Domestic, Smart Meter | 10
|  |  | Non Domestic, Traditional Meter | 8
|  | E2E-G002 Total |  | 34
E2E-G003
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G003 Total |  | 8
E2E-G004
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-G004 Total |  | 8
E2E-G005
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G005 Total |  | 4
E2E-G006
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G006 Total |  | 4
E2E-G010
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G010 Total |  | 4
| Gas Total |  |  | 72
SMS
E2E-SMS-001
|  |  | Service management | 7
|  | E2E-SMS-001 Total |  | 7
| SMS Total |  |  | 7
1 Total |  |  |  | 223
2
Dual
E2E-D005
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-D005 Total |  | 16
E2E-D006
|  |  | Domestic, Smart Meter | 2
|  | E2E-D006 Total |  | 2
| Dual Total |  |  | 18
Electricity
E2E-E006
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E006 Total |  | 4
E2E-E007
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E007 Total |  | 4
E2E-E008
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E008 Total |  | 4
E2E-E010
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E010 Total |  | 4
E2E-E011
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E011 Total |  | 4
E2E-E012
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 2
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E012 Total |  | 6
E2E-E013
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-E013 Total |  | 4
E2E-E014
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-E014 Total |  | 16
E2E-E015
|  |  | Non Domestic, Traditional Meter | 2
|  | E2E-E015 Total |  | 2
E2E-E016
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  | E2E-E016 Total |  | 4
E2E-E017
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 2
|  | E2E-E017 Total |  | 2
| Electricity Total |  |  | 54
Gas
E2E-G007
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G007 Total |  | 4
E2E-G008
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G008 Total |  | 4
E2E-G009
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G009 Total |  | 4
E2E-G011
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G011 Total |  | 4
E2E-G012
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G012 Total |  | 4
E2E-G013
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 3
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G013 Total |  | 6
E2E-G014
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  |  | Non Domestic, Smart Meter | 1
|  |  | Non Domestic, Traditional Meter | 1
|  | E2E-G014 Total |  | 4
E2E-G015
|  |  | Domestic, Smart Meter | 4
|  |  | Domestic, Traditional Meter | 4
|  |  | Non Domestic, Smart Meter | 4
|  |  | Non Domestic, Traditional Meter | 4
|  | E2E-G015 Total |  | 16
E2E-G016
|  |  | Domestic, Smart Meter | 2
|  | E2E-G016 Total |  | 2
E2E-G017
|  |  | Domestic, Smart Meter | 2
|  |  | Domestic, Traditional Meter | 2
|  | E2E-G017 Total |  | 4
E2E-G018
|  |  | Domestic, Smart Meter | 1
|  |  | Domestic, Traditional Meter | 1
|  | E2E-G018 Total |  | 2
| Gas Total |  |  | 54
2 Total |  |  |  | 126
Grand Total |  |  |  | 349

## How To Use (hidden)
How To Use
Contents
1. How to Navigate this document
2. Overview of the 'List of Test Scenarios' worksheet
3. Overview of the 'List of Test Cases' worksheet
4. Overview of the Test Case worksheets
1. How to Navigate this document
This section aims to provide an overview on how to navigate through this workbook.
The workbook consists of a number of worksheets arranged in a hieracrchy working from left to right.
The 'List of Test Scenarios' is broken down into a 'List of Test Cases', which consist of individual Test Cases.
Within the 'List of Test Scenarios' worksheet each of the Scenarios has a hyperlink ('Click to See Test Cases') which when selected takes the user to the Test Cases associated to the selected scenario on the 'List of Test Cases' worksheet.
. | From here, the user can then navigate to a more detailed view of the Test Scenario by clicking on the 'Click to view Test' link
To return to the 'List of Test Scenarios' worksheet the user would select 'Back to list of Test Scenarios', which will return the user to the top of the List of Test Scenarios worksheet.
2. Overview of the 'List of Test Scenarios' worksheet
This section aims to provide an overview of the information contained in the List of Test Scenarios worksheet
The List of 'Test Scenarios' worksheet details each Test Scenario that will be part of the testing phase and provides links to the scenario and list of test cases that make up the basic scenario.
The following are the populated Fields on the List of Test Scenarios worksheet and a brief description of each:
| Field | Details
| Test Scenario Category | A short title of the Scenario being defined
| E2E Scenario | A Unique reference for each Scenario (e.g. E2E-G001 is the first Gas Scenario)
| E2E Scenario Title | A Unique Title for each Test Scenario consisting of the E2E Scenario & Test Scenario Category
| Link | A link to the List of Test Cases appropriate to the Test Scenario
| Test ID | A scenario will require one or more Test Cases to deliver the Test Scenario. The same Test might be used in multiple scenarios. Each Test Case that delivers a particular scenario will be listed in the order they would be executed.
| Link | A link to each Test and Steps that will be used within the scenario
| Test Title | The title of the Test ID. This is defined on the individual Test Case worksheets.
| Fuel Type | Details if the Test Scenario is specific to Gas, Electricity or Dual Fuel
| Priority | Test Priority for any Risk Based Testing
| Pre-Requisite Test Scenario | The ID of the Test that must be executed prior to this one to complete a Test Scenario
| Comments | Any additional information regarding the Test Scenario will be provided here
| CSS | Indicates the number of steps the Test Case has defined that interact with CSS
| UK Link | Indicates the number of steps the Test Case has defined that interact with UK Link
| DES | Indicates the number of steps the Test Case has defined that interact with DES
| MPAS | Indicates the number of steps the Test Case has defined that interact with MPAS
| ECOES | Indicates the number of steps the Test Case has defined that interact with ECOES
| Smart Metering | Indicates the number of steps the Test Case has defined that interact with Smart Metering
| Gaining Shipper | Indicates the number of steps the Test Case has defined that interact with a Single Shipper or Gaining Shipper where the Test Scenario involves a two parties
| Losing Shipper | Indicates the number of steps the Test Case has defined that interact with a Losing Shipper where the Test Scenario involves a two parties
| Gas Transporter | Indicates the number of steps the Test Case has defined that interact with a GT or iGT
| Data Collector | Indicates the number of steps the Test Case has defined that interact with a DC
| Data Aggregator | Indicates the number of steps the Test Case has defined that interact with a DA
| MEM | Indicates the number of steps the Test Case has defined that interact with a MEM
| MAP | Indicates the number of steps the Test Case has defined that interact with a MAP
| DNO | Indicator as to whether the Test Case defined has steps that interact with a DNO/iDNO
| Gaining Supplier | Indicates the number of steps the Test Case has defined that interact with a single Supplier or a Gaining Supplier where the Test Scenario involves a two parties
| Losing Supplier | Indicates the number of steps the Test Case has defined that interact with a Losing Supplier where the Test Scenario involves a two parties
Third-Party IT Provider
3. Overview of the 'List of Test Cases' worksheet
This section aims to provide an overview of the information contained in the 'List of Test Cases' worksheet
The List of Test Cases details each variation of the Test Scenarios as Test Cases that will form part of the testing phase, and provides links to the Tests & the steps that make up the each scenario. Which Test Cases an E2E participant needs to execute will depend on the Licensed Parties profile
(see '1. How to Navigate this document' for details on how to navigate to & from the List of Test Cases worksheet)
Where Switching functionality is being tested there will be a matching 'GAIN' and a 'LOSE' Test Case. When executing a Test Case with a paired Supplier, the gaining supplier will execute the GAIN test case, and the losing supplier will execute the matching LOSE test case.
A green line separates the GAIN and LOSE test cases for the same scenario.
A blue line separates each Test Scenario, and the Test Case ID will indicate the Tests that make up a single Test Case for a Scenario.
The following are the populated Fields on the List of Test Scenarios worksheet and a brief description of each:
| Field | Details
| Test Case Category | The short title of the Scenario that the Test Case variations cover
| E2E Scenario | The Test Scenario ID of the Scenario that the Test Case variations cover
| Test Case Id | The Test Case ID is a combination of the Test Scenario ID and a unique reference to link each of the Tests that make up the Test Case
| Associated Test Id | Details the actual Test ID
| Link | A hyperlink to each Test Case worksheet that forms part of the Test Case
| Test Case Title | Details the Title of the Test Case from the associated Test Case worksheet, plus the variants in place for this particular Test Case.
| Fuel Type | Details if the Test Scenario is specific to Gas, Electricity or Dual Fuel
| Day(s) | Details the number of Days each Switch Test will be assigned. This will be blank where the number of days is not relevant to the Test Case
| Domestic | This will be marked with an 'X' where the Test Case is intended for a Domestic Customer.
| Non Domestic | This will be marked with an 'X' where the Test Case is intended for a Non Domestic Customer.
| OFAF | This will be marked with an 'X' where the Test Case is intended for a Switch of more than one Fuel Type or more than one Meter of the same Fuel Type to ensure the 'One Fail, All Fail' switching rule. The Test Case may not test a Failure in all cases.
| Related MPAN | This will be marked with an 'X' where the Test Case is intended to include related MPANs (Electricity only).
| Pre-Requisite Test Case | Details the Test ID that must have been executed prior to this Test
| Profile | The profile describes the options selected for each Test Case (i.e. where X's have been placed in the previous fields)
| Requirements | The requirements listed are the unique Abacus references documented against the in the relevant Test Case Worksheet
4. Overview of the Test Case worksheets
This section aims to provide an overview of the information contained in each of the Test Case worksheets. For example worksheet E2E-002.
Each Test Case worksheet gives an overview of the Case and the agreed steps that need to be executed. These will be loaded to Jira to form each Test Case per LP and the LP will then be able to expand on the Test Steps within Jira to make them more pertinent to the specific LP's systems and processes.
(see '1. How to Navigate this document' for details on how to navigate to & from each Test Case worksheet)
| The following are the Test Case overview Fields on each of the Test Case worksheets and a brief deCaseion of each field: |  | Example:
| Field | Details
| Scenario ID | The Test ID (as per the worksheet Name) that is used in the 'List of Test Scenarios' and 'List of Test Cases' worksheets to link Tests to Scenarios and Test Cases
| Title | The Short Title of the Test
| Description | An overview of the objectives of the Test
| Pre-Requisites | Any Pre-Requisites that need to be in place prior to this Test Case being executed
| Test Case Variable | A list of the Test Case variables that this particular Test should cater for.
| Mapped Requirements | A summary of the Abacus requirements that the Test Case covers
| Exception Codes | Exception Codes will not be applicable during E2E Testing, these will have been covered previously in SIT and/or UEPT
| The following are the Test Step Fields on each of the Test Case worksheets and a brief deCaseion of each field: |  | Example:
| Field | Details
| Mapped Requirements | The Abacus requirement reference(s) that each step covers
| Step Title | A short title outlining the purpose of the step
| Evidence Required | A 'Y' or 'N' indicator to highlight whether the Test Participant would be expected to provide evidence for the step. An 'O' indicates evidence is optional based on whether the agents and registered and have agreed to provide support during testing.
| Step Description | A more detailed description of the purpose of the step
| Related System | The system where the step would be executed
| Pre-requisite | Any Pre-Requisites that this step is dependent upon
| Expected Result | A description of the outcome of this Step
| API (Inbound to CSS) | API details retained from the original SIT tests
| Route | Route details retained from the original SIT tests
| Webhook context (Outbound from CSS) | Webhook context details retained from the original SIT tests
| Event Type | Event Type details retained from the original SIT tests
| Acknowledgement Messages | Acknowledgement Message details retained from the original SIT tests
| Comments | Any additional information / comments regarding the step
At the bottom of each Test Case worksheet are the list of Test Cases where this Test Case is called.
| The following is a brief description of each field in this section: |  | Example:
| Field | Details
| No. | Incremental number for each linked Test Case
| Unique Test Id | The Unique Test ID from the 'List of Test Cases' worksheet for each Test Case where this Test Case is called
| Return to Test Case | A Hyperlink to return directly to the current Test within the Test Case in the 'List of Test Cases' worksheet
| Test Case Title | The Test Case Title from the 'List of Test Cases' worksheet of the Unique Test ID Test Case
| Test Case ID | The Test Case ID from the 'List of Test Cases' worksheet of the Test Case
| E2E Scenario | The E2E Scenario ID from the 'List of Test Cases' worksheet of the Test Case
| Test Case Category | The Test Case Category from the 'List of Test Cases' worksheet of the Test Case
List of Test Scenarios
List of Test Cases

## List MASTER (hidden)
High
Medium
Low
MPAN Ownership
Metering Changes
Meter to Bank
Trad
Smart
Advanced
Unmetered
In Progress
Blocked - Reqt Query
Drafted
Peer Reviewed
Rework
Design Reviewed
WG Reviewed (Working Group Drops)​
WG Approved
TMAG Approved

## Change Log
Date | Author | Version | Defect ID | Reason for change
2024-01-17 | Shaun Magee |  |  | Scenario created
2024-01-24 | Shaun Magee | 5.2.1 v0.1 |  | PP DCC 23/01 Wording change to Key Validation & Test Evidence column for IF-041 Description
2024-01-25 | Shaun Magee | 5.2.1 v0.1 |  | PP DCC 23/01 Ref: 34 New Test Case - ST0037 - Smart. PP DCC 23/01 Ref: 45 Removed SUPC as recipient of IF-014 to align with DES138.
2024-01-31 | Shaun Magee | 5.2.1 v0.1 |  | PP DCC 23/01 Ref 5/6 Add Data provisioning PP DCC 23/01 Ref 11 Remove On-Demand Reads PP C&C Ref: 1: Clarify the expected unchanged values in subsequent Settlement Runs
2024-02-19 | Shaun Magee | 5.2.1 v0.2 |  | Adding in Method Statement REQ IDs:- METH001, ID-10039 METH001, ID-9273 METH004, ID-9463 METH004, ID-9511 METH005, ID-9600 METH007, ID-9685 which requires amendments to existing test cases and 2 new test cases for Advanced to cover flags A2 and A3.
2024-03-26 | Shaun Magee | 5.2.1 v0.3 |  | Merge shared steps
2024-05-01 | Shaun Magee | 5.2.1 v0.4 |  | Correct Settlement Steps to only call Load Shaping in the II Run. Any Actual Data will be passed to Load Shaping to add to the Load Shaping data and Data Service will use the Load Shaping to assist with Estimating the consumption. Update Calendar to reflect latest expected duration between II/SF/RF.
2024-05-21 | Gayatri Pasalkar | v0.5 |  | Updated to Version 0.5
2024-05-21 | Poonam Majalgaonkar | v0.5 |  | Added column "Test Case Version" in ST0037 Overview and TC01 to TC06
2024-05-22 | Ashish jadhav | v0.5 |  | Replaced DIP response from "http 202 response from DIP" to "http 201 response from DIP" on TC's01 to 06
2024-05-31 | Izhan Ahsan | v0.5 IR7 |  | Removed REP-D0354 and REP-D0237, as per DIN-761
2024-05-31 | Izhan Ahsan | v0.5 IR7 |  | Updated VAS and MDR requirements in all TCs
2024-09-26 | Alan Younger | v7.1 |  | Test Case simplified and consolidated (TC02 v7.1, TC03 v7.1, TC04 v7.1)
2024-11-07 | Alan Younger | 7.2 |  | TC02 (v7.2), TC03 (v7.2) and TC04 (v7.2) update for correct format MDS requirements.
2024-11-12 | Alan Younger | 7.2 |  | TC02 (v7.2), TC03 (v7.2) and TC04 (v7.2) updated to map requirements MHHSP-BRS014-ECS-BR-RD-022 and MHHSP-BRS014-ECS-BR-RD-023
2024-11-14 | Alan Younger | 7.2 |  | TC02 (v7.2), TC03 (v7.2) and TC04 (v7.2) updated for correct format VAS requirements and to remove invalid mappings for MHHSP-BRS009-VAS-42, MHHSP-BRS009-VAS-43, MHHSP-BRS009-VAS-44, MHHSP-BRS009-VAS-45 plus descoped requirements MHHSP-BRS009-VAS-52, MHHSP-BRS009-VAS-57
2025-04-16 | Alan Younger | 7.3 | Requirements Mapping | TC02 (v7.3), TC03 (v7.3) and TC04 (v7.3) have been updated to remove invalid requirement mappings and bring the test case mappings into alignment with the RTTM.

## ST0037 Overview
Scenario ID | SITFTS-ST0037
Theme | Settlement
Scenario Title | Consumption settling against De-Energised MPANs
Description | TC02 Advanced Import MPAN De-Energised A1 Consumption flagged A1 is generated and settles normally in the II run where MDS Reports on De-energised MPANs and issues a Warning to participants via the IF-014 TC03 Unmetered Single MPAN De-Energised Consumption flagged A is generated and settles normally in the II run where MDS Reports on De-energised MPANs and issues a Warning to participants via the IF-014 TC04: i) Traditional Single MPAN De-Energised Consumption flagged E6 is generated and settles normally in the II run where MDS Reports on De-energised MPANs and issues a Warning to participants via the IF-014 ii) Smart Single MPAN De-Energised Consumption flagged A is generated and settles normally in the II run where MDS Reports on De-energised MPANs and issues a Warning to participants via the IF-014 Assumes the following Calendar Run is in operation with example dates:
Functional Category | Settlement
Functional Area 1 | Consumption
Functional Area 2 | Settling normally with Warnings
Creator | Shaun Magee
Priority | High
Scenario size | Medium
Design Document Ref
Business Process | BP004, BP005, BP018, BP019, BP020, METH001, METH002, METH004, METH005, METH006, METH007
Pre-Requisites TC02 | For the purposes of this test the following is assumed: II Run is UTC Settlement Day + 2WD SF Run is UTC Settlement Day + 5WD RF Run is UTC Settlement Day + 8WD MPAN Data Check: Advanced single MPAN where the advanced meter has a main meter and check meter and is de-energised. The MPAN from the data cut has had a bulk Service Provider change - Metering Service and Data Service - via Migration or via the normal business processes. (and marked as migrated). Precursor to II Run Advanced MPAN Data Collection for [D] Occurs on [D] + 1 Data Payload On the day after the selected Settlement Day [D], the Data Service generates a Data Payload that represents both the Reads and the Consumption (HH Data) from the Meter obtained via Data Collection (remote/local/Customer) for the Settlement Day [D] . Data is available from the Main Meter but not available from the Check Meter. The Data Payload Reads are generated as a PUB-041 where the Event Code = "[ReadingRemote]". The Data Payload Consumption (HH Data) is generated in the appropriate Data Service format. IF-021 Data Using Active processing defined in the Method Statement, the Data Service will use this Payload Data to prepare UTC Settlement Period Consumption Data which will be submitted to the II Settlement Run. Note: Method a is used to generate a complete Set of IF-021 UTC Settlement Period Consumption Data is expected for the MPAN with no gaps in data where Settlement Period Quality Indicator = "A1".
Pre-Requisites TC03 | Calendar Check: Test Settlement Calendar is fully operational for the UTC Settlement Day (s). For the purposes of this test the following is assumed: II Run is UTC Settlement Day + 2WD SF Run is UTC Settlement Day + 5WD RF Run is UTC Settlement Day + 8WD MPAN Data Check: The selected Unmetered Single MPAN from the data cut has had a bulk Service Provider change - Metering Service and Data Service - via Migration or via the normal business processes. (and marked as migrated). The MPAN is De-Energised. Precursor to II Run Unmetered Data Service Provisioning: Unmetered MPAN D + 1WD Data Payload: Unmetered MPAN D0389 flows / PUB-047 messages PECU Array Data CMS Logs IF-021 Data Using Active processing defined in the Method Statement, the Data Service will use the UMS Inventory Data to prepare UTC Settlement Period Consumption Data which will be submitted to the II Settlement Run. Note: A Complete Set of IF-021 UTC Settlement Period Consumption Data is expected for the MPAN with no gaps in data where Settlement Period Quality Indicator = "A" and indicates the IF-021 Data is Actual.
Pre-Requisites TC04 | Calendar Check: Test Settlement Calendar is fully operational for the UTC Settlement Day (s). For the purposes of this test the following is assumed: II Run is UTC Settlement Day + 2WD SF Run is UTC Settlement Day + 5WD RF Run is UTC Settlement Day + 8WD MPAN Data Check: The selected Unmetered Single MPAN from the data cut has had a bulk Service Provider change - Metering Service and Data Service - via Migration or via the normal business processes. (and marked as migrated). The MPAN is De-Energised. Precursor for II Run Traditional Single MPAN Day [D] [D] + 1WD Data Payload The Data Service generates a Data Payload that represents a Customer Own Reading received for the Traditional MPAN dated on the Settlement Day [D] . The Data Payload Reading is generated as a D0010 IF-021 Data As this is a Traditional MPAN, the Customer Own Read Reading provided for the MPAN is being used on a daily basis to calculate Consumption Data from the selected Settlement Day[D]. The Data Service will use active processing as defined in the Method Statement to prepare estimated UTC Settlement Period Consumption Data which will be submitted to the II Settlement Run. Note: Method 6 is used to generate a Complete Set of UTC Settlement Period Consumption Data is expected for the MPAN with no gaps in data where Settlement Period Quality Indicator = "E6" and indicates the IF-021 Data is Estimated. Precursor for II Run: Smart Single MPAN Data Collection for [D] Occurs on [D] + 1WD Data Payload On the day after the selected Settlement Day [D], the Data Service generates a Data Payload that represents both the Reads and the Consumption (HH Data) from the Meter obtained via the DSP Schedule for the Settlement Day [D] . The Data Payload Reads is generated as a PUB-041 where the Event Code = "[ReadingRemote]". The Data Payload Consumption (HH Data) is generated in a format agreed between the MDR and the Data Service. IF-021 Data Using Active processing defined in the Method Statement, the Data Service will use this Payload Data to prepare UTC Settlement Period Consumption Data which will be submitted to the II Settlement Run. Note: A Complete Set of IF-021 UTC Settlement Period Consumption Data is expected for the MPAN with no gaps in data where Settlement Period Quality Indicator = "A" and indicates the IF-021 Data is Actual.
Boundaries | Processing ends when Settlement has completed to the II Run
Test Case Variables | (TC04) traditional, single MPAN migrated/flagged as migrated and de-energised TC02) advanced, Import MPAN migrated/flagged as migrated and de-energised (TC03) unmetered, single MPAN migrated/flagged as migrated and de-energised (TC04) smart, single MPAN migrated/flagged as migrated and de-energised
Mapped Requirements
Exception Codes | NA
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Test Case Link | Test Case Version | Test Data Requirements | Meter Type | MPAN Type | Effective time
2 | ST0037 TC02 | ST0037 - Advanced | ST0037 - Advanced | 7.3 | Advanced single MPAN (as per DES138 data specification) where the advanced meter has a main meter and check meter and is de-energised. The MPAN from the data cut has had a bulk Service Provider change - Metering Service and Data Service - via Migration or via the normal business processes. (and marked as migrated). | Advanced Meter | Import | UTC Settlement Day [D]
3 | ST0037 TC03 | ST0037 - Unmetered | ST0037 - Unmetered | 7.3 | Unmetered Dynamic MPAN (as per DES138 data specification) where the MPAN is De-Energised and IF-014 Warning Issued | No Meter | Single | UTC Settlement Day [D]
4 | ST0037 TC04 | ST0037 - Trad - Smart | ST0037 - Trad - Smart | 7.3 | Traditional Single Migrated MPAN and Smart Single Migrated MPAN with HH Consents (as per DES138 data specification) where the Meters are De-Energised and IF-014 Warning Issued | Traditional Meter Smart Meter | Traditional Single Smart Single | UTC Settlement Day [D]
Back to List of
Test Scenarios

## ST0037 - Advanced
No. | Test Case Id |  |  | Test case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
2 | ST0037 TC02 |  |  | 7.3 |  | ST0037 - Advanced | ST0037 - Advanced | Advanced single MPAN (as per DES138 data specification) where the advanced meter has a main meter and check meter and is de-energised. The MPAN from the data cut has had a bulk Service Provider change - Metering Service and Data Service - via Migration or via the normal business processes. (and marked as migrated). | Advanced Meter with check meter | Single (Import) | UTC Settlement Day [D]
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
ST0037 - Advanced | Calendar Check | 1 Pre-Req | [7 empty] | Test Settlement Calendar is fully operational for the UTC Settlement Day (s). For the purposes of this test the following is assumed: II Run is UTC Settlement Day + 2WD SF Run is UTC Settlement Day + 5WD RF Run is UTC Settlement Day + 8WD |  | N
| MPAN Data Check | 2 Pre-Req | [7 empty] | Advanced single MPAN where the advanced meter has a main meter and check meter and is de-energised. The MPAN from the data cut has had a bulk Service Provider change - Metering Service and Data Service - via Migration or via the normal business processes. (and marked as migrated). |  | N
| Precursor to II Run Advanced MPAN Data Collection for [D] Occurs on [D] + 1 | 3 Pre-Req | BP004, BP005 | 15 | MHHS-BR-DS-038 METH007, ID-9685 | ADSC | Data Provisioning |  | ADSC | Data Payload On the day after the selected Settlement Day [D], the Data Service generates a Data Payload that represents both the Reads and the Consumption (HH Data) from the Meter obtained via Data Collection (remote/local/Customer) for the Settlement Day [D] . Data is available from the Main Meter but not available from the Check Meter. The Data Payload Reads are generated as a PUB-041 where the Event Code = "[ReadingRemote]". The Data Payload Consumption (HH Data) is generated in the appropriate Data Service format. IF-021 Data Using Active processing defined in the Method Statement, the Data Service will use this Payload Data to prepare UTC Settlement Period Consumption Data which will be submitted to the II Settlement Run. Note: Method a is used to generate a complete Set of IF-021 UTC Settlement Period Consumption Data is expected for the MPAN with no gaps in data where Settlement Period Quality Indicator = "A1". | Data Service generates actual Cumulative Reads & HH Consumption. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. Note. The Data Service to use whatever tools available to generate the Data Payload with values which are commensurate with the test under execution. | Y
| Precursor to II Run Load Shaping runs and PUB-022 and PUB-023 output as normal. | 4 | BP0018 |  | MHHSP-BRS014-ECS-BR-RD-022 MHHSP-BRS014-ECS-BR-RD-023 MHHSP-BRS004-Supplier-BR-SU-043 MHHSP-BRS001-ADS-BR-DS-076 | LSS | Load Shaping |  | LSS | Load Shaping: LSS run and outputs PUB-022 and PUB-023 messages to Supplier and Data Services as normal. | LSS completes successfully. | N
| II RUN Occurs on [D] + 2WD | [10 empty] | N
| IF-021 Data in queue | 5 | BP005 | 220 | MHHSP-BRS001-Data Service-BR-DS-093 | ADSC | PUB-021 | [ActivePower] & [DI-015] <> W | DIP | The IF-021 data is now queued awaiting the next Calendar Run for the UTC Settlement Day [D] which will be processed as per the published calendar and timetable. |  | N
|  | 6 | BP019 | 15 | MHHSP-BRS008-MDS-07 MHHSP-BRS014-ECS-BR-RD-019 | DIP | PUB-021 | [ACTIVE Power] & [DI-015] <> W | MDS | MDS receives PUB-021 | MDS Receives the IF-021 messages. Test evidence is captured (IF-021 screenshots, logs, etc) | Y
MDS Run Starts
| MDS Identifies Consumption received for de-energised Advanced MPAN. | 7 | BP019 | 16 |  | MDS |  |  | MDS | MDS validates Advanced MPAN data, identifies consumption received for a De-Energised MPAN and issues a Warning via the IF-014 | MDS validates UTC Period Level Consumption data following receipt. MDS performs a number of checks as set out in the MDS Method Statement, including where consumption has been received for a de-energised MPAN. | N
|  | 8 | BP019 | 17 | MHHSP-BRS014-ECS-BR-RD-020 | MDS | IF-014 | [ConsumptionOnDeEnergisedMPAN] | DIP | Warning Reporting to Market Participants by sending IF-014 to the DIP Response Code [DI-979] = "W" | http 201 response from DIP | N
|  | 9 | BP019 | 85 | MHHSP-BRS014-ECS-BR-RD-020 | DIP | PUB-014 | [ConsumptionOnDeEnergisedMPAN] | ADSC LDSO | DIP sends PUB-014 to ADSC, & LDSO Response Code [DI-979] = "W" |  | N
|  | 10 |  |  | MHHSP-BRS014-ECS-BR-RD-020 | DIP | PUB-014 | [ConsumptionOnDeEnergisedMPAN] | ADSC | Data Service receives PUB-014 Response Code [DI-979] = "W" | Data Service receives the UTC Settlement Period Consumption Data (Warning). Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 11 |  |  | MHHSP-BRS014-ECS-BR-RD-020 | DIP | PUB-014 | [ConsumptionOnDeEnergisedMPAN] | LDSO | LDSO receives PUB-014 Response Code [DI-979] = "W" | LDSO receives the UTC Settlement Period Consumption Data (Warning). Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| MDS Reports are produced | 12 | BP0019 | 105 | MHHSP-BRS008-MDS-14 MHHSP-BRS008-MDS-23 MHHSP-BRS008-MDS-24 MHHSP-BRS008-MDS-27 MHHSP-BRS008-MDS-30 METH007, ID-9700 METH007, ID-9836 | MDS | REP-002 REP-002A REP-002B REP-006 REP-009 |  | DIP | On completion, MDS submits Reports for Publication to DIP | http 201 response from DIP | N
|  | 13 | BP0019 | 85 | REP-002 REP-002A REP-002B REP-006 REP-009 | DIP | REP-002 REP-002A REP-002B REP-006 REP-009 |  | SUPC, LDSO | DIP submits Reports for Publication to the Supplier and LDSO |  | N
|  | 14 | BP0019 | N/A | REP-002 REP-006 REP-009 | DIP | REP-002 REP-006 REP-009 |  | SUPC | Supplier receives published MDS Reports | Supplier receives MDS Reports. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 15 | BP0019 | N/A | REP-002A REP-002B | DIP | REP-002A REP-002B |  | LDSO | LDSO receives published MDS Reports | LDSO receives MDS Reports . Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| MDS Run Ends Internal MDS Calculations are validated | 16 |  |  |  | Helix |  |  | Helix | MDS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots | Y
|  | 17 | BP019 | 115 | VAS Requirement | MDS | HELIX-IF-11.1-MDS2DAH-AggregatedLineLosses HELIX-IF-10.1-MDS2DAH-AggregatedConsumption |  | VAS | Data that has passed validation as part of the MDS run is passed to the VAS for the Volume Allocation Run (VAR) |  | N
| VAS Run Starts VAS Reports are produced | 18 | BP020 | 75 | MHHSP-BRS009-VAS-55 MHHSP-BRS009-VAS-56 | VAS |  |  | DIP | On completion, VAS submits Reports for Publication to the DIP | http 201 response from DIP | N
| VAS Reports are produced | 19 | BP020 | 80 | REP-003 REP-003A REP-004 REP-007 REP-D0081 REP-D0266 REP-D0276 REP-D0296 REP-D0369 REP-D0370 REP-D0373 REP-D0374 | DIP | REP-003 REP-003A REP-004 REP-007 REP-D0081 REP-D0266 REP-D0276 REP-D0296 REP-D0369 REP-D0370 REP-D0373 REP-D0374 |  | SUPC | DIP submits Reports for Publication to the Supplier |  | N
|  | 20 | BP0020 | N/A | REP-003 REP-003A REP-004 REP-007 REP-D0081 REP-D0266 REP-D0276 REP-D0296 REP-D0369 REP-D0370 REP-D0373 REP-D0374 | DIP | REP-003 REP-003A REP-004 REP-007 REP-D0081 REP-D0266 REP-D0276 REP-D0296 REP-D0369 REP-D0370 REP-D0373 REP-D0374 |  | SUPC | Supplier receives published VAS Reports and confirms output is as expected | Supplier receives VAS Reports and confirms reports reconcile with expected results using the Settlement Supplier Base Data Report. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| VAS Run Ends Internal VAS Calculations are validated | 21 |  |  |  | Helix |  |  | Helix | VAS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots | Y

## ST0037 - Unmetered
No. | Test Case Id |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
3 | ST0037 TC03 |  |  | 7.3 |  | ST0037 - Unmetered | ST0037 - Unmetered | Unmetered Dynamic MPAN (as per DES138 data specification) where the MPAN is De-Energised and IF-014 Warning Issued | No Meter | Single | UTC Settlement Day [D]
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
ST0037 - Unmetered | Calendar Check | 1 Pre-Req | [7 empty] | Test Settlement Calendar is fully operational for the UTC Settlement Day (s). For the purposes of this test the following is assumed: II Run is UTC Settlement Day + 2WD SF Run is UTC Settlement Day + 5WD RF Run is UTC Settlement Day + 8WD |  | N
| MPAN Data Check | 2 Pre-Req | [7 empty] | The selected Unmetered Single MPAN from the data cut has had a bulk Service Provider change - Metering Service and Data Service - via Migration or via the normal business processes. (and marked as migrated). The MPAN is De-Energised. |  | N
| Precursor to II Run Unmetered Data Service Provisioning: Unmetered MPAN D + 1WD | 3 Pre-Req | BP004, BP005 |  | MHHSP-BRS001-UMSDS-BR-DS-061 MHHSP-BRS001-UMSDS-BR-DS-062 MHHSP-BRS001-UMSDS-BR-DS-063 MHHSP-BRS001-UMSDS-BR-DS-064 MHHSP-BRS001-UMSDS-BR-DS-065 MHHSP-BRS001-UMSDS-BR-DS-066 MHHSP-BRS001-UMSDS-BR-DS-067 MHHSP-BRS001-UMSDS-BR-DS-068 MHHSP-BRS001-UMSDS-BR-DS-069 MHHSP-BRS001-UMSDS-BR-DS-070 MHHSP-BRS001-UMSDS-BR-DS-071 MHHSP-BRS001-UMSDS-BR-DS-085 MHHSP-BRS001-UMSDS-BR-DS-090 | UMSDS | Data Provisioning |  | UMSDS | Data Payload: Unmetered MPAN D0389 flows / PUB-047 messages PECU Array Data CMS Logs IF-021 Data Using Active processing defined in the Method Statement, the Data Service will use the UMS Inventory Data to prepare UTC Settlement Period Consumption Data which will be submitted to the II Settlement Run. Note: A Complete Set of IF-021 UTC Settlement Period Consumption Data is expected for the MPAN with no gaps in data where Settlement Period Quality Indicator = "A" and indicates the IF-021 Data is Actual. | The Data Service to use whatever tools available to generate the Data Payload with values which are commensurate with the test under execution. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| Precursor to II Run Load Shaping runs and PUB-022 and PUB-023 output as normal. | 4 | BP0018 |  | MHHSP-BRS014-ECS-BR-RD-022 MHHSP-BRS014-ECS-BR-RD-023 | LSS | Load Shaping |  | LSS | Load Shaping: LSS run and outputs PUB-022 and PUB-023 messages to Supplier and Data Services as normal. | LSS completes successfully. | N
| II RUN Occurs on [D] + 2WD | [10 empty] | N
| IF-021 Data in queue | 5 | BP005 | 220 | MHHSP-BRS001-Data Service-BR-DS-093 MHHSP-BRS001-Data Service-BR-DS-094 | UMSDS | IF-021 | [ActivePower] & [DI-015] = U | DIP | The IF-021 data is now queued awaiting the next Calendar Run for the UTC Settlement Day [D] which will be processed as per the published calendar and timetable. |  | N
|  | 6 | BP019 | 15 | MHHSP-BRS008-MDS-07 MHHSP-BRS014-ECS-BR-RD-019 | DIP | PUB-021 | [ACTIVE Power] & [DI-015] = U | MDS | MDS receives PUB-021 | MDS Receives the IF-021 messages. Test evidence is captured (IF-021 screenshots, logs, etc) | Y
MDS Run Starts
| MDS Identifies Consumption received for de-energised Unmetered MPAN. | 7 | BP019 | 16 |  | MDS |  |  | MDS | MDS validates Unmetered MPAN data, identifies consumption received for a De-Energised MPAN and issues a Warning via the IF-014 message. | MDS validates UTC Period Level Consumption data following receipt. MDS performs a number of checks as set out in the MDS Method Statement, including where consumption has been received for a de-energised MPAN. | N
|  | 8 | BP019 | 17 | MHHSP-BRS014-ECS-BR-RD-020 | MDS | IF-014 | [ConsumptionOnDeEnergisedMPAN] | DIP | Warning Reporting to Market Participants by sending IF-014 to the DIP Response Code [DI-979] = "W" | http 201 response from DIP | N
|  | 9 | BP019 | 85 | MHHSP-BRS014-ECS-BR-RD-020 | DIP | PUB-014 | [ConsumptionOnDeEnergisedMPAN] | UMSDS, LDSO | DIP sends PUB-014 to UMSDS, & LDSO Response Code [DI-979] = "W" |  | N
|  | 10 |  |  | MHHSP-BRS014-ECS-BR-RD-020 | DIP | PUB-014 | [ConsumptionOnDeEnergisedMPAN] | UMSDS | Data Service receives PUB-014 Response Code [DI-979] = "W" | Data Service receives the UTC Settlement Period Consumption Data (Warning). Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 11 |  |  | MHHSP-BRS014-ECS-BR-RD-020 | DIP | PUB-014 | [ConsumptionOnDeEnergisedMPAN] | LDSO | LDSO receives PUB-014 Response Code [DI-979] = "W" | LDSO receives the UTC Settlement Period Consumption Data (Warning). Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| MDS Reports are produced | 12 | BP0019 | 105 | MHHSP-BRS008-MDS-14 MHHSP-BRS008-MDS-23 MHHSP-BRS008-MDS-24 MHHSP-BRS008-MDS-27 MHHSP-BRS008-MDS-30 METH007, ID-9700 METH007, ID-9836 | MDS | REP-002 REP-002A REP-002B REP-006 REP-009 |  | DIP | On completion, MDS submits Reports for Publication to DIP | http 201 response from DIP | N
|  | 13 | BP0019 | 85 | REP-002 REP-002A REP-002B REP-006 REP-009 | DIP | REP-002 REP-002A REP-002B REP-006 REP-009 |  | SUPC, LDSO | DIP submits Reports for Publication to the Supplier and LDSO |  | `N
|  | 14 | BP0019 | N/A | REP-002 REP-006 REP-009 | DIP | REP-002 REP-006 REP-009 |  | SUPC | Supplier receives published MDS Reports | Supplier receives MDS Reports. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 15 | BP0019 | N/A | REP-002A REP-002B | DIP | REP-002A REP-002B |  | LDSO | LDSO receives published MDS Reports | LDSO receives MDS Reports . Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| MDS Run Ends Internal MDS Calculations are validated | 16 |  |  |  | Helix |  |  | Helix | MDS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots | Y
|  | 17 | BP019 | 115 | VAS Requirement | MDS | HELIX-IF-11.1-MDS2DAH-AggregatedLineLosses HELIX-IF-10.1-MDS2DAH-AggregatedConsumption |  | VAS | Data that has passed validation as part of the MDS run is passed to the VAS for the Volume Allocation Run (VAR) |  | N
| VAS Run Starts VAS Reports are produced | 18 | BP020 | 75 | MHHSP-BRS009-VAS-55 MHHSP-BRS009-VAS-56 | VAS |  |  | DIP | On completion, VAS submits Reports for Publication to the DIP | http 201 response from DIP | N
| VAS Reports are produced | 19 | BP020 | 80 | REP-003 REP-003A REP-004 REP-007 REP-D0081 REP-D0266 REP-D0276 REP-D0296 REP-D0369 REP-D0370 REP-D0373 REP-D0374 | DIP | REP-003 REP-003A REP-004 REP-007 REP-D0081 REP-D0266 REP-D0276 REP-D0296 REP-D0369 REP-D0370 REP-D0373 REP-D0374 |  | SUPC | DIP submits Reports for Publication to the Supplier |  | N
|  | 20 | BP0020 | N/A | REP-003 REP-003A REP-004 REP-007 REP-D0081 REP-D0266 REP-D0276 REP-D0296 REP-D0369 REP-D0370 REP-D0373 REP-D0374 | DIP | REP-003 REP-003A REP-004 REP-007 REP-D0081 REP-D0266 REP-D0276 REP-D0296 REP-D0369 REP-D0370 REP-D0373 REP-D0374 |  | SUPC | Supplier receives published VAS Reports | Supplier receives VAS Reports. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| VAS Run Ends Internal VAS Calculations are validated | 21 |  |  |  | Helix |  |  | Helix | VAS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots | Y

## ST0037 - Trad - Smart
No. | Test Case Id |  |  | Test Case Version |  | Test Case Title | Test Case Link | Test Data Requirements | Meter Type | MPAN Type | Effective time
4 | ST0037 TC04 |  |  | 7.3 |  | ST0037 - Trad - Smart | ST0037 - Trad - Smart | Traditional Single Migrated MPAN and Smart Single Migrated MPAN with HH Consents (as per DES138 data specification) where the Meters are De-Energised and IF-014 Warning Issued | Traditional Meter Smart Meter | Traditional Single Smart Single | UTC Settlement Day [D]
Test Case Title | Key Journey Events | Step No. | Business Process | BP Step | Traceability Requirement | Service Producing Trigger | Input/Trigger | Message Input Event Code | Service Recipient/Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
ST0037 - Trad - Smart | Calendar Check | 1 Pre-Req | [7 empty] | Test Settlement Calendar is fully operational for the UTC Settlement Day (s). For the purposes of this test the following is assumed: II Run is UTC Settlement Day + 2WD SF Run is UTC Settlement Day + 5WD RF Run is UTC Settlement Day + 8WD |  | N
| MPAN Data Check | 2 Pre-Req | [7 empty] | MPAN Data Requirements: 1. Traditional single MPAN 2. Smart Single MPAN The selected MPANs from the data cut have had a bulk Service Provider change - Metering Service and Data Service - via Migration or via the normal business processes. (and marked as migrated). The meters for both MPANs are De-Energised. |  | N
| Precursor for II Run Traditional Single MPAN Day [D] [D] + 1WD | 3 Pre-Req | BP004, BP005 | 60 | METH001, ID-9273 METH007, ID-9685 MHHSP-BRS001-SDS-BR-DS-084 | SDSC | Data Provisioning |  | SDSC | Data Payload The Data Service generates a Data Payload that represents a Customer Own Reading received for the Traditional MPAN dated on the Settlement Day [D] . The Data Payload Reading is generated as a D0010 IF-021 Data As this is a Traditional MPAN, the Customer Own Read Reading provided for the MPAN is being used on a daily basis to calculate Consumption Data from the selected Settlement Day[D]. The Data Service will use active processing as defined in the Method Statement to prepare estimated UTC Settlement Period Consumption Data which will be submitted to the II Settlement Run. Note: Method 6 is used to generate a Complete Set of UTC Settlement Period Consumption Data is expected for the MPAN with no gaps in data where Settlement Period Quality Indicator = "E6" and indicates the IF-021 Data is Estimated. | Data Service generates estimated IF-021 message. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. NOTE: The Data Service to use whatever tools available to generate the Data Payload with values which are commensurate with the test under execution. | Y
| Precursor for II Run: Smart Single MPAN Data Collection for [D] Occurs on [D] + 1WD | 4 Pre-Req | BP005 | 130 160 | MHHS-BR-DS-044 MHHS-BR-DS-047 MHHS-BR-DS-050 MHHS-BR-DS-052 MHHS-BR-DS-073 MHHSP-BRS001-SDS-BR-DS-092 METH007, ID-9685 | SDSC | Data Provisioning |  | SDSC | Data Payload On the day after the selected Settlement Day [D], the Data Service generates a Data Payload that represents both the Reads and the Consumption (HH Data) from the Meter obtained via the DSP Schedule for the Settlement Day [D] . The Data Payload Reads is generated as a PUB-041 where the Event Code = "[ReadingRemote]". The Data Payload Consumption (HH Data) is generated in a format agreed between the MDR and the Data Service. IF-021 Data Using Active processing defined in the Method Statement, the Data Service will use this Payload Data to prepare UTC Settlement Period Consumption Data which will be submitted to the II Settlement Run. Note: A Complete Set of IF-021 UTC Settlement Period Consumption Data is expected for the MPAN with no gaps in data where Settlement Period Quality Indicator = "A" and indicates the IF-021 Data is Actual. | Data Service generates actual Cumulative Reads & HH Consumption. Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. Note. The Data Service to use whatever tools available to generate the Data Payload with values which are commensurate with the test under execution. | Y
| Precursor to II Run Load Shaping runs and PUB-022 and PUB-023 output as normal. | 5 | BP0018 |  | MHHSP-BRS014-ECS-BR-RD-022 MHHSP-BRS014-ECS-BR-RD-023 MHHSP-BRS004-Supplier-BR-SU-043 MHHSP-BRS001-SDS-BR-DS-077 | LSS | Load Shaping |  | LSS | Load Shaping: LSS run and outputs PUB-022 and PUB-023 messages to Supplier and Data Services as normal. | LSS completes successfully. | N
| II RUN Occurs on [D] + 2WD | [10 empty] | N
| IF-021 Data in queue | 6 | BP005 | 220 | MHHS-BR-RD-019 | SDSC | PUB-021 | [ActivePower] & [DI-015] = W | DIP | The IF-021 data is now queued awaiting the next Calendar Run for the UTC Settlement Day [D] which will be processed as per the published calendar and timetable. |  | N
|  | 7 | BP019 | 15 | MHHSP-BRS008-MDS-07 | DIP | PUB-021 | [ACTIVE Power] & [DI-015] = W | MDS | MDS receives PUB-021 | MDS Receives the IF-021 messages. Test evidence is captured (IF-021 screenshots, logs, etc) | Y
MDS Run Starts
| MDS Identifies Consumption received for de-energised Traditional MPAN. | 8 | BP019 | 16 |  | MDS |  |  | MDS | MDS validates Traditional MPAN data, identifies consumption received for a De-Energised MPAN and issues a Warning via the IF-014 message. | MDS validates UTC Period Level Consumption data following receipt. MDS performs a number of checks as set out in the MDS Method Statement, including where consumption has been received for a de-energised MPAN. | N
|  | 9 | BP019 | 17 | MHHSP-BRS014-ECS-BR-RD-020 | MDS | IF-014 | [ConsumptionOnDeEnergisedMPAN] | DIP | Warning Reporting to Market Participants by sending IF-014 to the DIP Response Code [DI-979] = "W" | http 201 response from DIP | N
|  | 10 | BP019 | 85 | MHHSP-BRS014-ECS-BR-RD-020 | DIP | PUB-014 | [ConsumptionOnDeEnergisedMPAN] | SDSC, LDSO | DIP sends PUB-014 to SDSC & LDSO Response Code [DI-979] = "W" |  | N
|  | 11 |  |  | MHHSP-BRS014-ECS-BR-RD-020 | DIP | PUB-014 | [ConsumptionOnDeEnergisedMPAN] | SDSC | Data Service receives PUB-014 in respect of the Traditional MPAN Response Code [DI-979] = "W" | Data Service receives the UTC Settlement Period Consumption Data (Warning). Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 12 |  |  | MHHSP-BRS014-ECS-BR-RD-020 | DIP | PUB-014 | [ConsumptionOnDeEnergisedMPAN] | LDSO | LDSO receives PUB-014 in respect of the Traditional MPAN Response Code [DI-979] = "W" | LDSO receives the UTC Settlement Period Consumption Data (Warning). Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| MDS Identifies Consumption received for de-energised Smart MPAN. | 13 | BP019 | 16 |  | MDS |  |  | MDS | MDS validates Smart MPAN Data, identifies consumption received for a De-Energised MPAN and issues a Warning via the IF-014 message. | MDS validates UTC Period Level Consumption data following receipt. MDS performs a number of checks as set out in the MDS Method Statement, including where consumption has been received for a de-energised MPAN. | N
|  | 14 | BP019 | 17 | MHHSP-BRS014-ECS-BR-RD-020 | MDS | IF-014 | [ConsumptionOnDeEnergisedMPAN] | DIP | Warning Reporting to Market Participants by sending IF-014 to the DIP Response Code [DI-979] = "W" | http 201 response from DIP | N
|  | 15 | BP019 | 85 | MHHSP-BRS014-ECS-BR-RD-020 | DIP | PUB-014 | [ConsumptionOnDeEnergisedMPAN] | SDSC, LDSO | DIP sends PUB-014 to SDSC & LDSO Response Code [DI-979] = "W" |  | N
|  | 16 |  |  | MHHSP-BRS014-ECS-BR-RD-020 | DIP | PUB-014 | [ConsumptionOnDeEnergisedMPAN] | SDSC | Data Service receives PUB-014 in respect of the Smart MPAN Response Code [DI-979] = "W" | Data Service receives the UTC Settlement Period Consumption Data (Warning). Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
|  | 17 |  |  | MHHSP-BRS014-ECS-BR-RD-020 | DIP | PUB-014 | [ConsumptionOnDeEnergisedMPAN] | LDSO | LDSO receives PUB-014 in respect of the Smart MPAN Response Code [DI-979] = "W" | LDSO receives the UTC Settlement Period Consumption Data (Warning). Confirms successful updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps. | Y
| MDS Reports are produced | 18 | BP0019 | 105 | MHHSP-BRS008-MDS-14 MHHSP-BRS008-MDS-23 MHHSP-BRS008-MDS-24 MHHSP-BRS008-MDS-27 MHHSP-BRS008-MDS-30 METH007, ID-9700 METH007, ID-9836 | MDS | REP-002 REP-002A REP-002B REP-006 REP-009 |  | DIP | On completion, MDS submits Reports for Publication to DIP | http 201 response from DIP | N
|  | 19 | BP0019 | 85 | REP-002 REP-002A REP-002B REP-006 REP-009 | DIP | REP-002 REP-002A REP-002B REP-006 REP-009 |  | SUPC, LDSO | DIP submits Reports for Publication to the Supplier and LDSO |  | N
|  | 20 | BP0019 | N/A | REP-002 REP-006 REP-009 | DIP | REP-002 REP-006 REP-009 |  | SUPC | Supplier receives published MDS Reports | Supplier receives MDS Reports. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
|  | 21 | BP0019 | N/A | REP-002A REP-002B | DIP | REP-002A REP-002B |  | LDSO | LDSO receives published MDS Reports | LDSO receives MDS Reports . Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| MDS Run Ends Internal MDS Calculations are validated | 22 |  |  |  | Helix |  |  | Helix | MDS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots | Y
|  | 23 | BP019 | 115 | VAS Requirement | MDS | HELIX-IF-11.1-MDS2DAH-AggregatedLineLosses HELIX-IF-10.1-MDS2DAH-AggregatedConsumption |  | VAS | Data that has passed validation as part of the MDS run is passed to the VAS for the Volume Allocation Run (VAR) |  | N
| VAS Run Starts VAS Reports are produced | 24 | BP020 | 75 | MHHSP-BRS009-VAS-55 MHHSP-BRS009-VAS-56 | VAS |  |  | DIP | On completion, VAS submits Reports for Publication to the DIP | http 201 response from DIP | N
| VAS Reports are produced | 25 | BP020 | 80 | REP-003 REP-003A REP-004 REP-007 REP-D0081 REP-D0266 REP-D0276 REP-D0296 REP-D0369 REP-D0370 REP-D0373 REP-D0374 | DIP | REP-003 REP-003A REP-004 REP-007 REP-D0081 REP-D0266 REP-D0276 REP-D0296 REP-D0369 REP-D0370 REP-D0373 REP-D0374 |  | SUPC | DIP submits Reports for Publication to the Supplier |  | N
|  | 26 | BP0020 | N/A | REP-003 REP-003A REP-004 REP-007 REP-D0081 REP-D0266 REP-D0276 REP-D0296 REP-D0369 REP-D0370 REP-D0373 REP-D0374 | DIP | REP-003 REP-003A REP-004 REP-007 REP-D0081 REP-D0266 REP-D0276 REP-D0296 REP-D0369 REP-D0370 REP-D0373 REP-D0374 |  | SUPC | Supplier receives published VAS Reports | Supplier receives VAS Reports. Capture test evidence in the form of logs / screenshots from downstream systems/apps | Y
| VAS Run Ends Internal VAS Calculations are validated | 27 |  |  |  | Helix |  |  | Helix | VAS Run completes and Helix validates internal calculations | Helix confirm successful validation of internal calculations. Capture test evidence in the form of logs / screenshots | Y

## DPCache_List of Test Scenarios (hidden)
Test Category | Test Scenario | Scenario Title | Test Cases Link | Test ID | Test Scenario Link | Status Date | Status | Test Title | Priority | Pre-Requisite Test Scenario
Advisory Notification | E2E-001 | SITFTS-001 - Advisory Notification | Click to See Test Cases | E2E-001 | Click to view Test | 2023-02-09 | WG Reviewed (Working Group Drops)​ | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Advisory Notification | E2E-E004 | E2E-E004 - Advisory Notification | Click to See Test Cases | E2E-004 |  |  |  | Switch Request Objection - Dual Fuel | Medium | NA
Switch Request Objection | E2E-G006 |  | Click to See Test Cases | E2E-006 |  |  |  | Switch Request Objection - Dual Fuel | Medium | NA
Switch Request Objection | E2E-E007 | E2E-E007 - Switch Request Objection | Click to See Test Cases | E2E-007 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Switch Request Objection | E2E-D008 |  | Click to See Test Cases | E2E-008 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | Medium | NA
Switch Request Successful | E2E-G012 | E2E-G012 - Switch Request Successful | Click to See Test Cases | E2E-012 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | High | NA
Switch Request Successful | E2E-E011 |  | Click to See Test Cases | E2E-011 |  |  |  | Switch Request Rejected during CSS Validation - Invalid Registration start Date (e.g. greater than Max Switch period, historic, wrong date format or during Standstill period) | High | NA