## Change Log
Date | Author | Release | Reason for change
05.03.2024 | Ankur Pande | 0.1 | New Migration Test Scenario document
26.03.2024 | Ankur Pande | 0.2 | Uplifted comments by PPs. Please see Release Notes.
11.04.2024 | Ankur Pande | 0.3 | Uplifted further comments by PPs & internal checks. Please see Release Notes.
30.04.2024 | Ankur Pande | 0.4 | Changed sequence of BP003A CSS/DCC Update Steps for Smart Meters

## Terminology
Terminology Used | Description | Type of Meter | Data Service | Description
BAU Process | This refers to a process within the MHHS arrangements as set out within the MHHS Core Design | Smart | SDSC | Smart Meter Data Service - Curent
CoA | Change of Agent |  | SDSI | Smart Meter Data Service - Incoming
CoS | Change of Supplier |  | SDSO | Smart Meter Data Service - Outgoing
CSS | Central Switching Service | Traditional | SDSC | Traditional Meter Data Service - Current
Data Cleanse Plan | The approach and activities required to improve and populate data prior to Migration start |  | SDSI | Traditional Meter Data Service - Incoming
DC | Data Collector |  | SDSO | Traditional Meter Data Service - Outgoing
DIP | Data Integration Platform | Advanced | ADSC | Advanced Meter Data Service - Current
DS | Data Service |  | ADSI | Advanced Meter Data Service - Incoming
Forward Migration | The process through which MPANs will move from Legacy arrangements to MHHS arrangements. |  | ADSO | Advanced Meter Data Service - Outgoing
Incoming / New MS | Incoming / New Metering Service | Unmetered | UMSDS | Unmetered Data Service
Incoming DS / New DS | Incoming Data Services
ISD | Industry Standing Data | Type of Meter | Metering Service | Description
LDSO | Licensed Distribution System Operator | Smart | SMSC | Smart Meter Metering Service - Current
MHHS | Market-Wide Half-Hourly Settlement |  | SMSI | Smart Meter Metering Service - Incoming
MHHS Arrangements | The new MHHS arrangements as set out in the MHHS Core Design Artefacts. |  | SMSO | Smart Meter Metering Service - Outgoing
Migration Design | The technical articulation of how MPANs will move from Legacy to new MHHS arrangements. | Traditional | SMSC | Traditional Meter Metering Service - Current
Migration Period | The period denoted by the Programme as occurring between the M11 and M15 milestones. |  | SMSI | Traditional Meter Metering Service - Incoming
MOP | Meter Operator |  | SMSO | Traditional Meter Metering Service - Outgoing
MPAN | Metering Point Administration Number | Advanced | AMSC | Advanced Meter Metering Service - Current
MS | Metering Service |  | AMSI | Advanced Meter Metering Service - Incoming
Outgoing MOP | Outgoing Meter Operator |  | AMSO | Advanced Meter Metering Service - Outgoing
Qualified Supplier | A Supplier recognised in ISD as both having passed the relevant System Integration Testing (SIT) requirements or BSC qualification requirements; and declared that their service is operational within the MHHS arrangements. | Unmetered | UMSO | Unmetered Metering Service
Registration Service | The service operated by LDSOs
REGS | Registration Services | Format | Description
Reverse Migration | The process through which MPANs will move from MHHS arrangements to Legacy arrangements. | Text in GREEN | NEW steps introduced for MIGRATION
Secondary MPAN | The MPAN, within a Related MPAN arrangement, for which a Forward Migration occurs when an IF-031 is received for a Primary MPAN. | Participants in RED | Out of scope participants - substituted by stubs or out of scope for testing
SUPC | Current Supplier | MS | Step in the "Change of Service - Metering Service" process
SUPI | Incoming Supplier | DS | Step in the "Change of Service - Data Service" process
SUPL | Linked Supplier | MS & DS | Common step for "Metering Service" and "Data Service" processes
SUPS | Sending Supplier
Switch | The process by which a new Supplier Registration supersedes an existing Supplier Registration, managed by the CSS.
XDSC | Data Service - Current
XDSP | Data Service – Proposed (denotes that multiple entries for same MAPN (but different DIP ID/Additional Info combinations) may exist for sniffer value)
XDSS | Data Service - Sending
XMIG | Migration Status (IF-036/IF-003)
XMSC | Metering Service – Current
XMSP | Metering Service – Proposed (denotes that multiple entries for same MAPN (but different DIP ID/Additional Info combinations) may exist for sniffer value )
XMSS | Metering Service - Sending
XMSU | Incumbent Metering Service (IF-035)
XMTR | Meter Type (IF-006)
XSEG | Segment (IF-044)
UMSO | Unmetered Metering Service
UMSDS | Unmetered Data Service

## SIT-M-FM-COA-DeemRead Overview
Scenario ID | SIT-M-FM-COA-DeemRead
Theme | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service). Deemed Reads.
Scenario Title | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service). Deemed Reads.
Description | This is a Forward Migration CoA Scenario. Deemed Reads Supplier choses to migrate an existing Legacy System MPAN to new MHHS compliant systems. The Supplier remains the same - the Metering Service and Data Services will change. This document lists both DS and MS changes for each meter segment type. For CoA, the Incoming/Prospective Supplier = Outgoing/Incumbent Supplier.
Functional Category | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service). Deemed Reads.
Functional Area 1 | Forward Migration CoA - Legacy MPAN CoA to a MHHS Qualified Supplier - Change of Services (Metering Service + Data Service). Deemed Reads.
Functional Area 2 | Existing MPAN, Change Agent successful with changes to Data Service and Metering Service - Deemed Reads
Creator | Ankur Pande
Priority | High
Scenario size | Large
Design Document Ref
Business Process | BP002, BP003, (+BP003A for Smart meters)
Pre-Requisites
Note
Test Case Variables | These test are specific to Prospective Appointments only as the process covers all functionality. Also the tests are relevant to NHH Meters. (1) Traditional Meter (Non Half Hourly - NHH) (2) Advanced Metering (Non Half Hourly - NHH) (3) Smart Metering (Non Half Hourly - NHH)
Below is a list of all associated test cases to this scenario.
No. | Test Case Id | Test Case Title | Test Description | Meter Type | HH / NHH | Effective Date | Status
1 | SIT-M-FM-COA-DeemRead-TC01 | SIT-M-FM-COA-DeemRead-TC01 - Traditional Meter | Under this scenario a MHHS Qualified Supplier chooses to migrate a Traditional meter MPAN from Legacy NHH settlements to MHHS arrangements - Deemed Reads. This test is specific to Prospective Appointments only as it covers all functionality. | Traditional | NHH | Next Day | Ready for review
2 | SIT-M-FM-COA-DeemRead-TC02 | SIT-M-FM-COA-DeemRead-TC02 - Advanced Meter (HH) | Under this scenario a MHHS Qualified Supplier chooses to migrate a Advanced Meter (HH) MPAN from Legacy HH settlements to MHHS arrangements - Deemed Reads This test is specific to Prospective Appointments only as it covers all functionality. | Advanced Meter | NHH | Next Day | Ready for review
3 | SIT-M-FM-COA-DeemRead-TC03 | SIT-M-FM-COA-DeemRead-TC03 - Smart Meter (HH) | Under this scenario a MHHS Qualified Supplier chooses to migrate a Smart Meter (HH) MPAN from Legacy HH settlements to MHHS arrangements - Deemed Reads This test is specific to Prospective Appointments only as it covers all functionality. | Smart Meter | NHH | Next Day | Ready for review

## SIT-M-FM-COA-DeemRead-TC01 Trad
Test Case Title | Key Journey Events | Test Step | Business Process | BP Step | Service Type | Test Steps | Test Description | Trigger Sender | Interface ID | Trigger Receipient | Traceability Requirement | Message Input Event Code | Evidence Required | Key Validation & Test Evidence
SIT-M-FM-COA-MS-DS-TC01 | Determine Service Required | 5 | BP002 BP003 | 5 10 | MS & DS | Determine Metering Service Required | Supplier must identify the correct Market Segment. | N/A | N/A | N/A | MS - MHHS-BR-SU-005 DS - MHHS-BR-SU-019 | N/A | N | N/A
| Setting up Appointments | 10 | BP002 | 20 | MS | Send Initial MS Appointment Request | Supplier will send the correct appointment details for the appropriate Service provider | SUPC | IF-031 | DIP | MHHS-BR-SU-006 MHHS-BR-SU-007 MHHS-Migration-CoA(MS)-SUP-001 MHHS-Migration-CoA(MS)-SUP-004 | [MSApp] | Y | http 202 response from DIP
|  | 15 | BP002 | 30 | MS | Publish Initial MS Appointment Request | The DIP will receive the appointment details from Supplier and publish them to the Registration Service. | DIP | PUB-031 | REGS | MHHS-BR-RS-009 | [MSApp] | Y | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems.
|  | 20 | BP003 | 20 | DS | Send Initial DS Appointment Request | Supplier will send the correct appointment details for the appropriate Service provider | SUPC | IF-031 | DIP | MHHS-BR-SU-020 MHHS-BR-SU-021 MHHS-Migration-CoA(DS)-SUP-002 MHHS-Migration-CoA(DS)-SUP-003 | [DSApp] | Y | http 202 response from DIP
|  | 25 | BP003 | 30 | DS | Publish Initial DS Appointment Request | The DIP will receive the appointment details from Supplier and publish them to the Registration Service. | DIP | PUB-031 | REGS | DIP | [DSApp] | Y | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems.
| Validate Initial Appointment Request | 30 | BP002 | 40 | MS | Validate Initial MS Appointment Request Step 45 - All requests Step 60 - Valid Requests only | The REGS will receive the publication 'Supplier Service Appointment Request' from the DIP and validate the content of the message as per the Registration validation rules for Service providers | DIP | PUB-031 | REGS | MHHS-BR-RS-010 MHHS-Migration-CoA(MS)-RS-004 MHHS-Migration-CoA(MS)-RS-005 MHHS-Migration-Can-RS-005 MHHS-Migration-CoA(MS)-RS-007 MHHS-Migration-CoA(MS)-RS-009 MHHS-Migration-CoA(MS)-RS-011 MHHS-Migration-CoA(MS)-RS-013 MHHS-Migration-CoA(MS)-RS-019 | [MSApp] | Y | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems.
|  | 35 | BP003 | 40 | DS | Validate Initial DS Appointment Request Step 45 - All requests Step 60 - Valid Requests only | The REGS will receive the publication 'Supplier Service Appointment Request' from the DIP and validate the content of the message as per the registration validation rules for Service providers | DIP | PUB-031 | REGS | MHHS-BR-RS-043 MHHS-BR-RS-044 MHHS-Migration-CoA(DS)-RS-004 MHHS-Migration-CoA(DS)-RS-005 MHHS-Migration-Can-RS-005 MHHS-Migration-CoA(DS)-RS-007 MHHS-Migration-CoA(DS)-RS-009 MHHS-Migration-CoA(DS)-RS-011 MHHS-Migration-CoA(DS)-RS-013 MHHS-Migration-CoA(DS)-RS-020 | [DSApp] | Y | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems.
| All Appointment Requests | 40 | BP002 | 45 | MS | Issue Initial MS Appointment Request Response for ALL requests | The REGS will respond to the DIP for the 'Supplier Service Appointment Request' with the appropriate response to Accept appointment. | REGS | IF-032 | DIP | MHHS-BR-RS-011 MHHS-BR-RS-012 MHHS-Migration-CoA(MS)-RS-010 MHHS-Migration-CoA(MS)-RS-012 MHHS-Migration-CoA(MS)-RS-014 | [MSAppInitialResp] | Y | http 202 response from DIP
|  | 45 | BP002 | 50 | MS | Publish Initial MS Appointment Request Response | The DIP will publish the REGS response to the 'Supplier Service Appointment Request' | DIP | PUB-032 | SUPC | DIP | [MSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
|  | 50 | BP002 | 55 | MS | Manage Initial MS Appointment Request Response | Supplier will receive response to the appointment request from the Registration Service and take the appropriate action dependant on outcome | DIP | PUB-032 | SUPC | MHHS-BR-SU-008 MHHS-BR-SU-009 | [MSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
|  | 55 | BP003 | 45 | DS | Issue Initial DS Appointment Request for all requests | The REGS will respond to the DIP for the 'Supplier Service Appointment Request' with the appropriate response to Accept appointment. | REGS | IF-032 | DIP | MHHS-BR-RS-045 MHHS-BR-RS-046 MHHS-Migration-CoA(DS)-RS-010 MHHS-Migration-CoA(DS)-RS-012 MHHS-Migration-CoA(DS)-RS-014 | [DSAppInitialResp] | Y | http 202 response from DIP
|  | 60 | BP003 | 50 | DS | Publish Initial DS Appointment Request Response | The DIP will publish the REGS response to the 'Supplier Service Appointment Request' | DIP | PUB-032 | SUPC | DIP | [DSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
|  | 65 | BP003 | 55 | DS | Manage Initial DS Appointment Request Response | Suppler will receive response to the appointment request from the Registration Service and take the appropriate action dependant on outcome | DIP | PUB-032 | SUPC | MHHS-BR-SU-022 MHHS-BR-SU-023 | [DSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
| Valid Requests Only | 70 | BP002 | 60 | MS | Issue Request MS Proposed Appointment Validation | The REGS will send 'REGS Request for Service Appointment' to the correct service provider via the DIP | REGS | IF-033 | DIP | MHHS-BR-RS-014.1 MHHS-BR-RS-015 | [MSAppSPRequest] | Y | http 202 response from DIP
|  | 75 | BP002 | 65 | MS | Publish Proposed MS Appointment Validation Request | The DIP will publish the 'REGS Request for Service Appointment' to the Metering Service | DIP | PUB-033 | SMSI | DIP | [MSAppSPRequest] | Y | Evidence that Metering Service processes the PUB-033 generated by DIP; log screenshots in downstream systems.
|  | 80 | BP002 | 70 | MS | Manage MS Proposed Appointment Validation Request | Metering Service will receive an appointment from the Supplier via the REGS. Metering Service must process and validate the appointment request as per the validation rules. Metering Service should be aware that an acceptance will result in the transfer of MPAN(s) | DIP | PUB-033 | SMSI | MHHS-BR-MS-001 | [MSAppSPRequest] | Y | Evidence that Metering Service processes the PUB-033 generated by DIP; log screenshots in downstream systems.
|  | 85 | BP002 | 75 | MS | Respond to MS Proposed Appointment Request | The Metering Service will accept the appointment request. | SMSI | IF-034 | DIP | MHHS-BR-MS-002 MHHS-BR-MS-003 | [MSAppSPResponse] | Y | http 202 response from DIP
|  | 90 | BP002 | 80 | MS | Publish Proposed MS Appointment Validation Response | The DIP will publish the responses from service providers | DIP | PUB-034 | REGS | DIP MHHS-Migration-CoA(MS)-SUP-005 | [MSAppSPResponse] | Y | Evidence that REGS processes the PUB-034 generated by DIP; log screenshots in downstream systems.
|  | 95 | BP002 | 85 | MS | Manage SP Prospective Appointment Response | The REGS will manage the appointment responses from the Metering Service and retain accepted responses in the background until the Effective from date when it will reflect as a live appointment | N/A | N/A | N/A | MHHS-BR-RS-016 MHHS-BR-RS-017 MHHS-Migration-CoA(MS)-RS-002 | N/A
|  | 100 | BP003 | 60 | DS | Issue Request DS Proposed Appointment | The REGS will send 'REGS Request for Service Appointment' to the correct Service provider via the DIP | REGS | IF-033 | DIP | MHHS-BR-RS-049 MHHS-BR-RS-048.1 | [DSAppSPRequest] | Y | http 202 response from DIP
|  | 105 | BP003 | 65 | DS | Publish Proposed DS Appointment Validation Request | The DIP will publish the 'REGS Request for Service Appointment' to the Data Service | DIP | PUB-033 | SDSI | DIP | [DSAppSPRequest] | Y | Evidence that Data Service processes the PUB-033 generated by DIP; log screenshots in downstream systems.
|  | 110 | BP003 | 220 | DS | Manage DS Appointment Request | Data Services will receive an appointment from the supplier via the REGS. Data services must process and validate the appointment request as per the validation rules | N/A | N/A | N/A | MHHS-BR-DS-007 MHHS-BR-DS-008 MHHS-BR-DS-011 | N/A
|  | 115 | BP003 | 221 | DS | Respond to DS Appointment Request - All outcomes - Acceptances | The Data Service will accept the appointment request | SDSI | IF-034 | DIP | MHHS-BR-DS-008 MHHS-BR-DS-011 | [DSAppSPResponse] | Y | http 202 response from DIP
| Additional step for DS in case of Acceptances | 120 | BP003 | 230 | DS | 3rd Party Appointment | Once the Data Service has accepted the appointment they must appoint the nominated 3rd parties as per the agreed contract and the agreed method. | N/A | N/A | N/A | MHHS-BR-DS-009 MHHS-BR-DS-010 | N/A
| All Outcomes | 125 | BP003 | 80 | DS | Publish Proposed DS Appointment Validation Response | The DIP will publish the responses from Data services | DIP | PUB-034 | REGS | DIP MHHS-Migration-CoA(DS)-SUP-004 | [DSAppSPResponse] | Y | Evidence that REGS processes the PUB-034 generated by DIP; log screenshots in downstream systems.
|  | 130 | BP003 | 85 | DS | Manage SP Prospective Appointment Response | The REGS will manage the appointment responses from the Data services and retain accepted responses in the background until the Effective from date when it will reflect as a live appointment. The REGS must Publish all responses via the DIP and notify the metering service (when acceptence and where meter is Traditional). | REGS | IF-035 | DIP | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-053 | [DSAppAccepted] | Y | http 202 response from DIP. Capture evidence that Metering Service has processed the IF-035 message from REGS.
| For All Appointment Responses | 135 | BP002 | 87 | MS | Issue MS Prospective Appointment Outcome | The REGS will send out all responses it has received from the Metering Services back to Supplier via the DIP. | REGS | IF-035 | DIP | MHHS-BR-RS-018 | [MSAppAccepted] | Y | http 202 response from DIP
|  | 140 | BP002 | 91 | MS | Publish Prospective Appointment Outcome Responses | The DIP will publish the Metering Service response for the appointment to Supplier. | DIP | PUB-035 | SUPC SMSI | DIP | [MSAppAccepted] | Y | Evidence that Supplier & Metering Services processes the PUB-035 generated by DIP; log screenshots in downstream systems.
|  | 145 | BP002 | 92 | MS | Manage MS Prospective Appointment Request Response | Metering Services will receive PUB-035 confirming the REGS has received the Metering Services response to the appointment | DIP | PUB-035 | SMSI | MHHS-BR-MS-006.1 | [MSAppAccepted] | Y | Evidence that Metering Service processes the PUB-035 generated by DIP; log screenshots in downstream systems.
|  | 150 | BP003 | 90 | DS | Publish Proposed Appointment Outcome Responses Step 86 : Step 91 : Step 160 : | The DIP will send out all responses it has received from the Data Services back to Supplier. | DIP | PUB-035 | SDSI SUPC | DIP | [DSAppAccepted] | Y | Evidence that Data Service & Supplier processes the PUB-035 generated by DIP; log screenshots in downstream systems.
|  | 155 | BP003 | 86 | DS | Receive Prospective Appointment Response | The Meter Service will receive accepted appointment responses from the REGSs where meter is Traditional | REGS | IF-035 | SMSC | MHHS-BR-RS-053 | [DSAppAccepted] | Y | Evidence that Metering Service processes the IF-035 generated by REGS; log screenshots in downstream systems.
|  | 160 | BP003 | 91 | DS | Manage DS Proposed Appointment Request Response | Data Services will receive PUB-035 confirming Registrations received the Data Services response to the appointment | DIP | PUB-035 | SDSI | MHHS-BR-DS-012.1 | [DSAppAccepted] | Y | Evidence that New Data Service processes the PUB-035 generated by DIP; log screenshots in downstream systems.
| Manage Prospective Appointment | 165 | BP002 | 95 | MS | Manage MS Prospective Appointment Request Response | Supplier will receive the publication of the Metering Service response to the appointment. Successful appointments will remain in a pending status until the effective from date. | DIP | PUB-035 | SUPC | MHHS-BR-SU-010 MHHS-BR-SU-011 | [MSAppAccepted] | Y | Evidence that Supplier processes the PUB-035 generated by DIP; log screenshots in downstream systems.
|  | 170 | BP003 | 95 | DS | Manage DS Proposed Appointment Request Response | Supplier will receive the publication for the Data Service response to the appointment. Successful appointments will remain in a pending status until the effective from date. | DIP | PUB-035 | SUPC | MHHS-BR-SU-024 MHHS-BR-SU-025 | [DSAppAccepted] | Y | Evidence that Supplier processes the PUB-035 generated by DIP; log screenshots in downstream systems.
| Determine further processing for Accepted Appointment Responses | 175 | BP002 | 100 | MS | Determine Processing Treatment - Prospective Appointments | For prospective appointments Registrations will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-020 MHHS-BR-RS-021 MHHS-BR-RS-023 | Interface Specifications
|  | 180 | BP003 | 100 | DS | Determine Processing Treatment - Prospective Appointments | For prospective appointments Registrations will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-054 MHHS-BR-RS-055 MHHS-BR-RS-057 MHHS-Migration-CoA(DS)-RS-001 | Interface Specifications
| Prospective Appointment Queue | 185 | BP002 | 101 | MS | Hold in Appointment Queue | REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-022 | Interface Specifications
|  | 190 | BP002 | 120 | MS | Review & Re-Validate Prospective Appointment(s) | REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-024 MHHS-BR-RS-025 MHHS-BR-RS-027 MHHS-BR-RS-028 MHHS-BR-RS-029 | Interface Specifications
|  | 195 | BP002 | 125 | MS | CSS Secured Notification | REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | N/A | Interface Specifications
|  | 200 | BP003 | 101 | DS | Hold in Appointment Queue | REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-056 | Interface Specifications
|  | 205 | BP003 | 120 | DS | Review & Re-Validate Prospective Appointment(s) | REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-058 MHHS-BR-RS-059 MHHS-BR-RS-061 MHHS-BR-RS-062 MHHS-BR-RS-063 | Interface Specifications
|  | 210 | BP003 | 125 | DS | CSS Secured Notification | REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | N/A | Interface Specifications
| Confirmed Appointments Only | 215 | BP002 | 240 | MS | Notify Prospective Appointment as Effective | The REGS will issue confirmation to the Metering Service their appointment is now active and send the meter technical details held in registration. They will also share the Data Service ID with the Metering Service. | REGS | IF-036 | DIP | MHHS-BR-RS-033 MHHS-Migration-CoA(MS)-RS-006 MHHS-Migration-CoA(MS)-RS-018 | [MSAppActive] | Y | http 202 response from DIP
|  | 220 | BP002 | 245 | MS | Publish Notification of Appointment (Acceptances) Step 195 - SMSI Step 280 - LDSO Step 283 - EES Step 270 - SDSC Step 260 - SUPC | The DIP will publish the Reg. Serv. Notification of Service App. & Supporting Info message. | DIP | PUB-036 | SMSI SDSC SUPC LDSO EES | DIP MHHS-Migration-CoA(MS)-ECS-001 MHHS-Migration-CoA(MS)-RS-008 | [MSAppActive] | Y | Evidence that DIP generates a PUB-036; Evidence that Data Service, SUPC, Metering Service and EES process the PUB-036; log screenshots in downstream systems.
|  | 225 | BP003 | 250 | DS | Notify Prospective Appointment as Effective | The REGS will issue confirmation to the Data Service their appointment is now active and send the meter technical details held in registration. They will also share the Metering Service ID with the Metering Service. | REGS | IF-036 | DIP | MHHS-BR-RS-067 MHHS-Migration-CoA(DS)-RS-018 MHHS-Migration-CoA(DS)-RS-019 | [DSAppActive] | Y | http 202 response from DIP
|  | 230 | BP003 | 255 | DS | Publish Notification of Appointment (Acceptances) Step 340 - SDSI Step 280 - LDSO Step 279 - EES Step 281 - SMSC Step 260 - SUPC | The DIP will publish the Reg. Serv. Notification of Service App. & Supporting Info message. | DIP | PUB-036 | SDSI SUPC LDSO SMSC EES | DIP MHHS-Migration-CoA(DS)-RS-006 MHHS-Migration-CoA(DS)-ECS-001 | [DSAppActive] | Y | Evidence that DIP generates a PUB-036, Evidence that Data Service, SUPC, LDSO, Metering Service and EES process the PUB-036; log screenshots in downstream systems.
| MDS is notified of DS appointment activation | 235 | BP003 | 255 | DS | MDS receives PUB-036 | MDS receives PUB-036 with details of Data Services Appointment Active | DIP | PUB-036 | MDS |  | [DSAppActive] | Y | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
| Notify Legacy agent of migration | 240 | BP002 | 1000 | MS | Send D0170 | If appointment accepted, the REGS will send a D0170 to the outgoing MOP. This flow informs the MOP of the identity of the new MS to which it will need to transfer MTDs and it also informs the MOP of the intent to migrate the MPAN. | REGS | D0170 | Outgoing MOP | MHHS-Migration-CoA(MS)-RS-001 |  | Y | Evidence that REGS has generated D0170; log screenshots in downstream systems.
|  | 245 | BP002 | 1001 | MS | (1) Receive D0170 from REGS (2) Send MTDs | Outgoing MOP to receive the D0170 from the REGS and send MTDs to the new MS. The D0170 will inform the old MOP of the identity of the new MS. | REGS | D0170 | Outgoing MOP | MHHS-Migration-CoA(MS)-MOP-001 |  | Y | (1) Evidence that REGS generates a D0170; log screenshots in downstream systems.
|  | 250 | BP003 | 1002 | DS | Send D0170 to request Transfer of Read data | The REGS will send a D0170 to the outgoing DC. This flow informs the DC of the identity of the new DS. | REGS | D0170 | Outgoing DC |  |  | Y | Evidence that REGS has generated D0170; log screenshots in downstream systems.
|  | 255 | BP003 | 1003 | DS | Receive D0170 with instructions for migration | The outgoing DC will receive the D0170 with the instructions for migration and info about the new DS. | REGS | D0170 | Outgoing DC |  |  | Y | Evidence that REGS has generated D0170; log screenshots in downstream systems.
| Issue & Receive MTDs | 260 | BP002 | 165 | MS | Send D0149/D0150 | Traditional Metering flows that will need to be sent from the existing Metering Service to the prospective Metering Service | Outgoing MOP (stub) | D0150 D0149 | SMSI | MHHS-BR-MS-018 |  | Y | Evidence that SMSC generates the D0150 & D0149; log screenshots in downstream systems.
|  | 265 | BP002 | 175 | MS | Receive Traditional MTDs | The prospective Metering Service will receive Meter technical details from the existing Metering Service via data flows. | Outgoing MOP (stub) | D0150 D0149 | SMSI | MHHS-BR-MS-020 MHHS-BR-MS-019 |  | Y | Evidence that the SMSI processes the D0150 & D0149 generated by the Outgoing MOP stub; log screenshots in downstream systems.
|  | 270 | BP003 | 165 | DS | Send D0149/D0150 | Traditional Metering flows that will need to be sent from the existing/new Metering Service to the prospective Data Service | SMSC | D0150 D0149 | SDSI | MHHS-BR-MS-028 |  | Y | Evidence that Prospective Data Service processes the D0150 & D0149 generated by New Existing Metering Service; log screenshots in downstream systems.
|  | 275 | BP003 | 345 | DS | Receive MTDs from MS | The Data Service will receive Meter technical details from the existing Metering Service via data flows. | SMSC | D0150 D0149 | SDSI | MHHS-BR-DS-015 MHHS-BR-DS-016 |  | Y | Evidence that Data Service processes the D0150, D0149 generated by New Metering Services ; log screenshots in downstream systems.
| Receive Appointment Notification & Manage MTD descrepancies | 280 | BP002 | 195 | MS | Receive Appointment Notification & MTDs | The REGS will send the Meter technical details that it holds and confirmation of live appointment to the Metering Service via the DIP | DIP | PUB-036 | SMSI | MHHS-BR-MS-007 | [MSAppActive] | Y | Evidence that Metering Service processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 285 | BP002 | 196 | MS | Manage MTD Discrepancies Check EES/IF-003 if MTDs missing | Metering Services can reconcile the meter technical received from Registrations compared to the Data flows received for Non-Smart (Traditional) For missing MTDs, check EES or IF-003 to validate that meters are installed on the MPAN. | N/A | N/A | N/A | MHHS-BR-MS-022
|  | 286 | BP002 |  | MS | MS requests counterparty to request missing MTDs | If meters are recorded in EES or REGS, MS/MOP requests counterparty for correct MTD | N/A | N/A | N/A
|  | 288 | BP002 |  | MS | MS/MOP sends correct details to MS | MS/MOP sends correct details to MS | N/A | N/A | N/A
|  | 290 | BP003 | 340 | DS | Manage Appointment Notification & Info | The REGS will send the Meter technical details that it holds and confirmation of live appointment to the data service, this will also contain who the Metering Service is. | DIP | PUB-036 | SDSI | MHHS-BR-DS-013 | [DSAppActive] | Y | Evidence that Data Service processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 295 | BP003 | 346 | DS | Manage MTD Discrepancies Check EES if MTDs missing | Data Services can reconcile the meter technical received from the REGS compared to the Data flows received for Traditional Metering Service For missing MTDs, check EES or IF-003 to validate that meters are installed on the MPAN. | N/A | N/A | N/A | MHHS-BR-DS-015 MHHS-BR-DS-016
|  | 296 | BP003 |  | DS | Manage MTD Discrepancies Check EES if MTDs missing | If meters are recorded in EES or REGS, MS/MOP requests counterparty for correct MTD | N/A | N/A | N/A
|  | 298 | BP003 |  | DS | MS/MOP sends correct details to MS | MS/MOP sends correct details to MS | N/A | N/A | N/A
| Issue MTDs via DTN (Traditional) | 300 | BP002 | 180 | MS | Issue MTDs via DTN (Traditional) | The New Metering Service will issue the meter technical details to Supplier | SMSI | D0150 D0149 | SUPC | MHHS-BR-MS-024 MHHS-BR-MS-023 |  | Y | Evidence that Supplier & Data Service processes the D0150, D0149 generated by Prospective Metering Service; log screenshots in downstream systems.
|  | 305 | BP002 | 191 | MS | Receive Traditional MTDs | The LDSO will receive Meter technical details from the new Metering Service via data flows. | SMSI | D0150 D0149 | LDSO | MHHS-BR-MS-024 |  | Y | Evidence that LDSO processes the D0150, D0149 generated by Prospective Metering Service; log screenshots in downstream systems.
| Publish Notification of Appointment to Data and Metering Services | 310 | BP002 | 270 | MS | MS Appointment Notification & MTD | The New Data Service will receive notification from the DIP containing confirmation of the new Metering Service | DIP | PUB-036 | ADSI | MHHS-BR-DS-002 MHHS-BR-DS-003 | [MSAppActive] | Y | Evidence that DIP generates a PUB-036, Evidence that Data Service process the PUB-036; log screenshots in downstream systems.
|  | 315 | BP002 | 271 | MS | Manage MTD Discrepancies if required | The NEW Data service will need to manage and discrepancies between the MTD's received from Metering Services and the MTD's received from the REGS. | N/A | N/A | N/A | MHHS-BR-DS-005 MHHS-BR-DS-006 MHHS-BR-DS-006.1
|  | 320 | BP003 | 281 | DS | DS Appointment Notification & MTD | The New metering Service will receive notification from the DIP containing confirmation of the new Data Service | DIP | PUB-036 | SMSC | MHHS-BR-MS-030 | [DSAppActive] | Y | Evidence that Metering Service processes the PUB-036 generated by DIP; log screenshots in downstream systems.
| Publish Notification of Appointment to LDSO | 325 | BP002 | 280 | MS | MS Appointment Notification & MTD | The LDSO will receive notification from the DIP containing confirmation of the new Metering Service | DIP | PUB-036 | LDSO | MHHS-BR-LD-003 MHHS-Migration-CoA(MS)-LDSO-001 | [MSAppActive] | Y | Evidence that LDSO processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 330 | BP002 | 281 | MS | Manage MTD Discrepancies if required | The LDSO will need to manage and discrepancies between the MTD's received from Metering Services and the MTD's received from the REGS. | N/A | N/A | N/A | MHHS-BR-LD-003
|  | 335 | BP002 | 282 | MS | END POINT | LDSO will continue with any BAU activity that may be required | N/A | N/A | N/A | N/A
|  | 340 | BP003 | 280 | DS | DS Appointment Notification & MTD | The LDSO Service will receive notification from the DIP containing confirmation of the new Data Service | DIP | PUB-036 | LDSO | MHHS-BR-LD-005 MHHS-Migration-CoA(DS)-LDSO-001 | [DSAppActive] | Y | Evidence that LDSO processes the PUB-036 generated by DIP; log screenshots in downstream systems.
| Publish Notification of Appointment to EES | 345 | BP002 | 283a | MS | MS Appointment Notification & MTD | EES will receive notification from the DIP containing confirmation of the new Metering Service Note EES will not process the MTDs from the IF-036. Only the agent appointment information will be used. | DIP | PUB-036 | EES | MHHS-BR-RS-034 MHHS-BR-RS-037 MHHS-Migration-CoA(MS)-RS-016 | [MSAppActive] | Y | Evidence that EES processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 350 | BP002 | 283b | MS | MS Appointment Notification & MTD | The EES will set a status that the MPAN is under MHHS arrangements after at least one PUB-036 is received. | N/A | N/A | N/A |  |  | Y | Parties should be able to enquire via the portal and the API and see this status.
|  | 355 | BP003 | 279a | DS | DS Appointment Notification & MTD | EES will receive notification from the DIP containing confirmation of the new Data Service Note EES will not process the MTDs from the IF-036. Only the agent appointment information will be used. | DIP | PUB-036 | EES | MHHS-BR-EES-016.3 MHHS-Migration-CoA(DS)-EES-001 | [DSAppActive] | Y | Evidence that EES processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 360 | BP003 | 279b | DS | DS Appointment Notification & MTD | Note: The EES will need to set a status that the MPAN is under MHHS arrangements after at least one PUB-036 is received. Parties should be able to enquire via the portal and the API and see this status. | N/A | N/A | N/A |  |  | Y | Parties should be able to enquire via the portal and the API and see this status.
| Publish Notification of Appointment to SUPC | 365 | BP002 | 260 | MS | Manage SP Confirmation and MTDs | Supplier will manage the Metering Service appointment and meter technical details received via D-flows | DIP | PUB-036 | SUPC | MHHS-BR-SU-013 | [MSAppActive] | Y | Evidence that Supplier processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 370 | BP002 | 201 | MS | Receive Traditional MTDs | The Supplier receives the MTDs from the Incoming Metering Service | SMSI | D0150 D0149 | SUPC | MHHS-BR-SU-014 MHHS-BR-SU-015 |  | Y | Evidence that Supplier processes the D0150 D0149 generated by Metering Service; log screenshots in downstream systems.
|  | 375 | BP002 | 202 | MS | END POINT | Supplier will continue with their BAU processes where additional actions are required | N/A | N/A | N/A | N/A
|  | 380 | BP003 | 260 | DS | Manage DS Appointment | The REGS will publish confirmation of the live Data Service appointment to Supplier | DIP | PUB-036 | SUPC | MHHS-BR-SU-027 MHHS-Migration-CoA(DS)-SUP-006 | [DSAppActive] | Y | Evidence that Supplier processes the PUB-036 generated by DIP; log screenshots in downstream systems.
| SUPC sends D0151 to Outgoing MOP/DC | 385 | BP002 | 1005 | MS | Send D0151 | The Supplier will send a D0151 to the outgoing MOP. | SUPC | D0151 | Outgoing MOP | MHHS-Migration-CoA(MS)-SUP-002 MHHS-Migration-CoA(MS)-SUP-007 |  | Y | Evidence that Current Supplier has generated D0151; log screenshots in downstream systems.
|  | 390 | BP003 | 1016 | DS | Send D0151 | The outgoing Supplier will send a D0151 to the outgoing DC. | SUPC | D0151 | Outgoing DC | MHHS-Migration-CoA(DS)-SUP-005 MHHS-Migration-CoA(DS)-SUP-007 |  | Y | Evidence that Current Supplier has generated D0151; log screenshots in downstream systems.
| Provide Meter Read | 395 | BP003 | 1011 | DS | Provide meter read via D0010 if available | The Current Supplier will provide the outgoing DC with a meter read via a D0010 if dated within 8 days of the CoA. | SUPC | D0010 | Outgoing DC | MHHS-Migration-CoA(DS)-DC-005 |  | Y | Evidence that Current Supplier has generated D0010; log screenshots in downstream systems.
| Validate Read, Generate AA, Deem Reading | 400 | BP003 | 1006 | DS | The Outgoing DC Validates read | The Outgoing DC Validates read |  |  |  | MHHS-Migration-CoA(DS)-DC-003 MHHS-Migration-CoA(DS)-DC-006 MHHS-Migration-CoA(DS)-DC-007
|  | 401 | BP003 | 1006 | DS | The Outgoing DC Generates an AA | The Outgoing DC Generates an AA |  |  |  | MHHS-Migration-CoA(DS)-DC-003 MHHS-Migration-CoA(DS)-DC-006 MHHS-Migration-CoA(DS)-DC-007
|  | 402 | BP003 | 1006 | DS | The Outgoing DC sends for a D0100/D0019 to Current Supplier | The Outgoing DC sends for a D0100/D0019 to Current Supplier | Outgoing DC (Stub) | D0010/D0019 | SUPC | MHHS-Migration-CoA(DS)-DC-003 MHHS-Migration-CoA(DS)-DC-006 MHHS-Migration-CoA(DS)-DC-007 |  | Y | Evidence that Current Supplier processes D0010/D0019 from stub; log screenshots in downstream systems.
|  | 403 | BP003 | 1006 | DS | If a reading is not received in 5 calendar days, the NHHDC will deem a reading. | If a reading is not received in 5 calendar days, the NHHDC will deem a reading. |  |  |  | MHHS-Migration-CoA(DS)-DC-003 MHHS-Migration-CoA(DS)-DC-006 MHHS-Migration-CoA(DS)-DC-007
| Receive Reads | 405 | BP003 | 1015 | DS | Receive Read | A D0010 will be sent for CoA | Outgoing DC (Stub) | CoA - D0010 | LDSO |  |  | Y | Evidence that LDSO has processed D0010 (for CoA) sent by stub; log screenshots in downstream systems.
|  | 410 | BP003 | 1012 | DS | Receive D0010 / D0019 | The current Supplier will receive a read via a D0010 / D0019 from the outgoing DC | Outgoing DC (Stub) | D0010 / D0019 | SUPC | MHHS-Migration-CoA(DS)-SUP-009 |  | Y | Evidence that Current Supplier has processed D0010/D0019 sent by stub; log screenshots in downstream systems.
|  | 415 | BP003 | 1013 | DS | Use as a Start Read | The Incoming DS will use the read they receive via a D0010 as a Start Read. | SUPC | D0010 | SDSI | MHHS-Migration-CoA(DS)-DS-003 |  | Y | Evidence that Prospective Data Service processes the D0010 generated by Current Supplier; log screenshots in downstream systems.
|  | 420 | BP003 | 1014 | DS | END POINT

## SIT-M-FM-COA-DeemRead-TC02 ANHH
Test Case Title | Key Journey Events | Test Steps | Business Process | BP Step | Service Type | Test Step Process Map Wording | Test Description | Trigger Sender | Interface ID | Trigger Receipient | Traceability Requirement | Message Input Event Code | Evidence Required | Key Validation & Test Evidence
SIT-M-FM-COA-MS-DS-TC02 | Determine Service Required | 5 | BP002 BP003 | 5 10 | MS & DS | Determine Metering Service Required | Supplier must identify the correct Market Segment. | N/A | N/A | N/A | MS - MHHS-BR-SU-005 DS - MHHS-BR-SU-019 | N/A | N | N/A
| Setting up Appointments | 10 | BP002 | 20 | MS | Send Initial MS Appointment Request | Supplier will send the correct appointment details for the appropriate Service provider | SUPC | IF-031 | DIP | MHHS-BR-SU-006 MHHS-BR-SU-007 MHHS-Migration-CoA(MS)-SUP-001 MHHS-Migration-CoA(MS)-SUP-004 | [MSApp] | Y | http 202 response from DIP
|  | 15 | BP002 | 30 | MS | Publish Initial MS Appointment Request | The DIP will receive the appointment details from Supplier and publish them to the Registration Service. | DIP | PUB-031 | REGS | MHHS-BR-RS-009 | [MSApp] | Y | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems.
|  | 20 | BP003 | 20 | DS | Send Initial DS Appointment Request | Supplier will send the correct appointment details for the appropriate Service provider | SUPC | IF-031 | DIP | MHHS-BR-SU-020 MHHS-BR-SU-021 MHHS-Migration-CoA(DS)-SUP-002 MHHS-Migration-CoA(DS)-SUP-003 | [DSApp] | Y | http 202 response from DIP
|  | 25 | BP003 | 30 | DS | Publish Initial DS Appointment Request | The DIP will receive the appointment details from Supplier and publish them to the Registration Service. | DIP | PUB-031 | REGS | DIP | [DSApp] | Y | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems.
| All Appointment Requests | 30 | BP002 | 45 | MS | Issue Initial MS Appointment Request Response for ALL requests | The REGS will respond to the DIP for the 'Supplier Service Appointment Request' with the appropriate response to Accept appointment. | REGS | IF-032 | DIP | MHHS-BR-RS-011 MHHS-BR-RS-012 MHHS-Migration-CoA(MS)-RS-010 MHHS-Migration-CoA(MS)-RS-012 MHHS-Migration-CoA(MS)-RS-014 | [MSAppInitialResp] | Y | http 202 response from DIP
|  | 35 | BP002 | 50 | MS | Publish Initial MS Appointment Request Response | The DIP will publish the REGS response to the 'Supplier Service Appointment Request' | DIP | PUB-032 | SUPC | DIP | [MSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
|  | 40 | BP002 | 55 | MS | Manage Initial MS Appointment Request Response | Supplier will receive response to the appointment request from the Registration Service and take the appropriate action dependant on outcome | DIP | PUB-032 | SUPC | MHHS-BR-SU-008 MHHS-BR-SU-009 | [MSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
|  | 45 | BP003 | 45 | DS | Issue Initial DS Appointment Request for all requests | The REGS will respond to the DIP for the 'Supplier Service Appointment Request' with the appropriate response to Accept appointment. | REGS | IF-032 | DIP | MHHS-BR-RS-045 MHHS-BR-RS-046 MHHS-Migration-CoA(DS)-RS-010 MHHS-Migration-CoA(DS)-RS-012 MHHS-Migration-CoA(DS)-RS-014 | [DSAppInitialResp] | Y | http 202 response from DIP
|  | 50 | BP003 | 50 | DS | Publish Initial DS Appointment Request Response | The DIP will publish the REGS response to the 'Supplier Service Appointment Request' | DIP | PUB-032 | SUPC | DIP | [DSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
|  | 55 | BP003 | 55 | DS | Manage Initial DS Appointment Request Response | Suppler will receive response to the appointment request from the Registration Service and take the appropriate action dependant on outcome | DIP | PUB-032 | SUPC | MHHS-BR-SU-022 MHHS-BR-SU-023 | [DSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
| Valid Requests Only | 60 | BP002 | 60 | MS | Issue Request MS Proposed Appointment Validation | The REGS will send 'REGS Request for Service Appointment' to the correct service provider via the DIP | REGS | IF-033 | DIP | MHHS-BR-RS-014.1 MHHS-BR-RS-015 | [MSAppSPRequest] | Y | http 202 response from DIP
|  | 65 | BP002 | 65 | MS | Publish Proposed MS Appointment Validation Request | The DIP will publish the 'REGS Request for Service Appointment' to the Metering Service | DIP | PUB-033 | AMSI | DIP | [MSAppSPRequest] | Y | Evidence that Metering Service processes the PUB-033 generated by DIP; log screenshots in downstream systems.
|  | 70 | BP002 | 70 | MS | Manage MS Proposed Appointment Validation Request | Metering Service will receive an appointment from the Supplier via the REGS. Metering Service must process and validate the appointment request as per the validation rules. Metering Service should be aware that an acceptance will result in the transfer of MPAN(s) | DIP | PUB-033 | AMSI | MHHS-BR-MS-001 | [MSAppSPRequest] | Y | Evidence that Metering Service processes the PUB-033 generated by DIP; log screenshots in downstream systems.
|  | 75 | BP002 | 75 | MS | Respond to MS Proposed Appointment Request | The Metering Service will accept the appointment request. | AMSI | IF-034 | DIP | MHHS-BR-MS-002 MHHS-BR-MS-003 | [MSAppSPResponse] | Y | http 202 response from DIP
|  | 80 | BP002 | 80 | MS | Publish Proposed MS Appointment Validation Response | The DIP will publish the responses from service providers | DIP | PUB-034 | REGS | DIP MHHS-Migration-CoA(MS)-SUP-005 | [MSAppSPResponse] | Y | Evidence that REGS processes the PUB-034 generated by DIP; log screenshots in downstream systems.
|  | 85 | BP002 | 85 | MS | Manage SP Prospective Appointment Response | The REGS will manage the appointment responses from the Metering Service and retain accepted responses in the background until the Effective from date when it will reflect as a live appointment | N/A | N/A | N/A | MHHS-BR-RS-016 MHHS-BR-RS-017 MHHS-Migration-CoA(MS)-RS-002 | N/A
|  | 90 | BP003 | 60 | DS | Issue Request DS Proposed Appointment | The REGS will send 'REGS Request for Service Appointment' to the correct Service provider via the DIP | REGS | IF-033 | DIP | MHHS-BR-RS-049 MHHS-BR-RS-048.1 | [DSAppSPRequest] | Y | http 202 response from DIP
|  | 95 | BP003 | 65 | DS | Publish Proposed DS Appointment Validation Request | The DIP will publish the 'REGS Request for Service Appointment' to the Data Service | DIP | PUB-033 | ADSI | DIP | [DSAppSPRequest] | Y | Evidence that Data Service processes the PUB-033 generated by DIP; log screenshots in downstream systems.
|  | 100 | BP003 | 220 | DS | Manage DS Appointment Request | Data Services will receive an appointment from the supplier via the REGS. Data services must process and validate the appointment request as per the validation rules | N/A | N/A | N/A | MHHS-BR-DS-007 MHHS-BR-DS-008 MHHS-BR-DS-011 | N/A
|  | 105 | BP003 | 221 | DS | Respond to DS Appointment Request - All outcomes - Acceptances | The Data Service will accept the appointment request. | ADSI | IF-034 | DIP | MHHS-BR-DS-008 MHHS-BR-DS-011 | [DSAppSPResponse] | Y | http 202 response from DIP
| Additional step for DS in case of Acceptances | 110 | BP003 | 230 | DS | 3rd Party Appointment | Once the Data Service has accepted the appointment they must appoint the nominated 3rd parties as per the agreed contract and the agreed method. | N/A | N/A | N/A | MHHS-BR-DS-009 MHHS-BR-DS-010 | N/A
| All Outcomes | 105 | BP003 | 80 | DS | Publish Proposed DS Appointment Validation Response | The DIP will publish the responses from Data services | DIP | PUB-034 | REGS | DIP MHHS-Migration-CoA(DS)-SUP-004 | [DSAppSPResponse] | Y | Evidence that REGS processes the PUB-034 generated by DIP; log screenshots in downstream systems.
|  | 120 | BP003 | 85 | DS | Manage SP Prospective Appointment Response | The REGS will manage the appointment responses from the Data services and retain accepted responses in the background until the Effective from date when it will reflect as a live appointment. The REGS must Publish all responses via the DIP and notify the metering service (when acceptence and where meter is Advanced). | REGS | IF-035 | DIP | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-053 | [DSAppAccepted] | Y | http 202 response from DIP. Capture evidence that Metering Service has processed the IF-035 message from REGS.
| For All Appointment Responses | 125 | BP002 | 87 | MS | Issue MS Prospective Appointment Outcome | The REGS will send out all responses it has received from the Metering Services back to Supplier via the DIP. | REGS | IF-035 | DIP | MHHS-BR-RS-018 | [MSAppAccepted] | Y | http 202 response from DIP
|  | 130 | BP002 | 91 | MS | Publish Prospective Appointment Outcome Responses | The DIP will publish the Metering Service response for the appointment to Supplier. | DIP | PUB-035 | SUPC AMSI | DIP | [MSAppAccepted] | Y | Evidence that Supplier & Metering Services processes the PUB-035 generated by DIP; log screenshots in downstream systems.
|  | 135 | BP002 | 92 | MS | Manage MS Prospective Appointment Request Response | Metering Services will receive PUB-035 confirming the REGS has received the Metering Services response to the appointment | DIP | PUB-035 | AMSI | MHHS-BR-MS-006.1 | [MSAppAccepted] | Y | Evidence that Metering Service processes the PUB-035 generated by DIP; log screenshots in downstream systems.
|  | 140 | BP003 | 90 | DS | Publish Proposed Appointment Outcome Responses Step 86 : Step 91 : Step 160 : | The DIP will send out all responses it has received from the Data Services back to Supplier. | DIP | PUB-035 | ADSI SUPC | DIP | [DSAppAccepted] | Y | Evidence that Data Service & Supplier processes the PUB-035 generated by DIP; log screenshots in downstream systems.
|  | 145 | BP003 | 86 | DS | Receive Prospective Appointment Response | The Meter Service will receive accepted appointment responses from the REGSs where meter is Advanced | REGS | IF-035 | AMSC | MHHS-BR-RS-053 | [DSAppAccepted] | Y | Evidence that Metering Service processes the IF-035 generated by REGS; log screenshots in downstream systems.
|  | 150 | BP003 | 91 | DS | Manage DS Proposed Appointment Request Response | Data Services will receive PUB-035 confirming Registrations received the Data Services response to the appointment | DIP | PUB-035 | ADSI | MHHS-BR-DS-012.1 | [DSAppAccepted] | Y | Evidence that New Data Service processes the PUB-035 generated by DIP; log screenshots in downstream systems.
| Manage Prospective Appointment | 155 | BP002 | 95 | MS | Manage MS Prospective Appointment Request Response | Supplier will receive the publication of the Metering Service response to the appointment. Successful appointments will remain in a pending status until the effective from date. | DIP | PUB-035 | SUPC | MHHS-BR-SU-010 MHHS-BR-SU-011 | [MSAppAccepted] | Y | Evidence that Supplier processes the PUB-035 generated by DIP; log screenshots in downstream systems.
|  | 160 | BP003 | 95 | DS | Manage DS Proposed Appointment Request Response | Supplier will receive the publication for the Data Service response to the appointment. Successful appointments will remain in a pending status until the effective from date. | DIP | PUB-035 | SUPC | MHHS-BR-SU-024 MHHS-BR-SU-025 | [DSAppAccepted] | Y | Evidence that Supplier processes the PUB-035 generated by DIP; log screenshots in downstream systems.
| Determine further processing for Accepted Appointment Responses | 165 | BP002 | 100 | MS | Determine Processing Treatment - Prospective Appointments | For prospective appointments Registrations will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-020 MHHS-BR-RS-021 MHHS-BR-RS-023 | Interface Specifications
|  | 170 | BP003 | 100 | DS | Determine Processing Treatment - Prospective Appointments | For prospective appointments Registrations will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-054 MHHS-BR-RS-055 MHHS-BR-RS-057 MHHS-Migration-CoA(DS)-RS-001 | Interface Specifications
| Prospective Appointment Queue | 175 | BP002 | 101 | MS | Hold in Appointment Queue | REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-022 | Interface Specifications
|  | 180 | BP002 | 120 | MS | Review & Re-Validate Prospective Appointment(s) | REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-024 MHHS-BR-RS-025 MHHS-BR-RS-027 MHHS-BR-RS-028 MHHS-BR-RS-029 | Interface Specifications
|  | 185 | BP002 | 125 | MS | CSS Secured Notification | For prospective appointments the REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | N/A | Interface Specifications
|  | 190 | BP003 | 101 | DS | Hold in Appointment Queue | For prospective appointments the REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the Data Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-056 | Interface Specifications
|  | 195 | BP003 | 120 | DS | Review & Re-Validate Prospective Appointment(s) | For prospective appointments the REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the data Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-058 MHHS-BR-RS-059 MHHS-BR-RS-061 MHHS-BR-RS-062 MHHS-BR-RS-063 | Interface Specifications
|  | 200 | BP003 | 125 | DS | CSS Secured Notification | For prospective appointments the REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the Data Service 'eff from date' comes into effect. | N/A | N/A | N/A | N/A | Interface Specifications
| Confirmed Appointments Only | 210 | BP002 | 240 | MS | Notify Prospective Appointment as Effective | The REGS will issue confirmation to the Metering Service their appointment is now active and send the meter technical details held in registration. They will also share the Data Service ID with the Metering Service. | REGS | IF-036 | DIP | MHHS-BR-RS-033 MHHS-Migration-CoA(MS)-RS-006 MHHS-Migration-CoA(MS)-RS-018 | [MSAppActive] | Y | http 202 response from DIP
|  | 215 | BP002 | 245 | MS | Publish Notification of Appointment (Acceptances) Step 195 - AMSI Step 280 - LDSO Step 283 - EES Step 270 - SDSC Step 260 - SUPC | The DIP will publish the Reg. Serv. Notification of Service App. & Supporting Info message. | DIP | PUB-036 | AMSI ADSC SUPC LDSO EES | DIP MHHS-Migration-CoA(MS)-ECS-001 MHHS-Migration-CoA(MS)-RS-008 | [MSAppActive] | Y | Evidence that DIP generates a PUB-036; Evidence that Data Service, SUPC, Metering Service and EES process the PUB-036; log screenshots in downstream systems.
|  | 220 | BP003 | 250 | DS | Notify Prospective Appointment as Effective | The REGS will issue confirmation to the Data Service their appointment is now active and send the meter technical details held in registration. They will also share the Metering Service ID with the Metering Service. | REGS | IF-036 | DIP | MHHS-BR-RS-067 MHHS-Migration-CoA(DS)-RS-018 MHHS-Migration-CoA(DS)-RS-019 | [DSAppActive] | Y | http 202 response from DIP
|  | 225 | BP003 | 255 | DS | Publish Notification of Appointment (Acceptances) Step 340 - ADSI Step 280 - LDSO Step 279 - EES Step 281 - SMSC Step 260 - SUPC | The DIP will publish the Reg. Serv. Notification of Service App. & Supporting Info message. | DIP | PUB-036 | ADSI SUPC LDSO AMSC EES | DIP MHHS-Migration-CoA(DS)-RS-006 MHHS-Migration-CoA(DS)-ECS-001 | [DSAppActive] | Y | Evidence that DIP generates a PUB-036, Evidence that Data Service, SUPC, LDSO, Metering Service and EES process the PUB-036; log screenshots in downstream systems.
| MDS is notified of DS appointment activation | 230 | BP003 | 255 | DS | MDS receives PUB-036 | MDS receives PUB-036 with details of Data Services Appointment Active | DIP | PUB-036 | MDS |  | [DSAppActive] | Y | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
| Notify Legacy agent of migration | 235 | BP002 | 1000 | MS | Send D0170 | If appointment accepted, the REGS will send a D0170 to the outgoing MOP. This flow informs the MOP of the identity of the new MS to which it will need to transfer MTDs and it also informs the MOP of the intent to migrate the MPAN. | REGS | D0170 | Outgoing MOP | MHHS-Migration-CoA(MS)-RS-001 |  | Y | Evidence that REGS has generated D0170; log screenshots in downstream systems.
|  | 240 | BP002 | 1001 | MS | (1) Receive D0170 from REGS (2) Send MTDs | Outgoing MOP to receive the D0170 from the REGS and send MTDs to the new MS. The D0170 will inform the old MOP of the identity of the new MS. | REGS | D0170 | Outgoing MOP | MHHS-Migration-CoA(MS)-MOP-001 |  | Y | (1) Evidence that REGS generates a D0170; log screenshots in downstream systems.
|  | 245 | BP003 | 1002 | DS | Send D0170 to request Transfer of Read data | The REGS will send a D0170 to the outgoing DC. This flow informs the DC of the identity of the new DS. | REGS | D0170 | Outgoing DC |  |  | Y | Evidence that REGS has generated D0170; log screenshots in downstream systems.
|  | 250 | BP003 | 1003 | DS | Receive D0170 with instructions for migration | The outgoing DC will receive the D0170 with the instructions for migration and info about the new DS. | REGS | D0170 | Outgoing DC |  |  | Y | Evidence that REGS has generated D0170; log screenshots in downstream systems.
| Issue & Receive MTDs | 255 | BP002 | 170 | MS | Issue MTD to Incoming Metering Service - Send D268 & D0383 / D0384 (if available) | Advanced Metering flows will need to be sent from the existing Metering Service to the prospective Metering Service | Outgoing MOP (stub) | D0268 D0383 D0384 | AMSI | MHHS-BR-MS-017 MHHS-Migration-CoA(MS)-MOP-003 MHHS-Migration-CoA(MS)-MOP-004 MHHS-Migration-CoA(MS)-MOP-005 |  | Y | Evidence that AMSC generates the D0268, D0383 and D0384 and they are consumed by the AMSI; log screenshots in downstream systems.
|  | 260 | BP002 | 175 | MS | Receive Advanced MTDs | The prospective Metering Service will receive Meter technical details from the existing Metering Service via data flows. | Outgoing MOP (stub) | D0268 D0383 D0384 | AMSI | MHHS-BR-MS-020 MHHS-BR-MS-019 |  | Y | Evidence that the AMSI processes the D0268 generated by the Outgoing MOP stub; log screenshots in downstream systems.
|  | 265 | BP003 | 170 | DS | Send D268 | Advanced Metering flows that will need to be sent from the existing/new Metering Service to the prospective Data Service | AMSC | D0268 | ADSI | MHHS-BR-MS-028 |  | Y | Evidence that Prospective Data Service processes the D0268, D0383 and D0384 generated by Existing Metering Service; log screenshots in downstream systems.
|  | 270 | BP003 | 345 | DS | Receive MTDs from MS | The Data Service will receive Meter technical details from the existing Metering Service via data flows. | AMSC | D0268 | ADSI | MHHS-BR-DS-015 MHHS-BR-DS-016 |  | Y | Evidence that Data Service processes the D0268 generated by New Metering Services ; log screenshots in downstream systems.
| Receive Appointment Notification & Manage MTD descrepancies | 275 | BP002 | 195 | MS | Receive Appointment Notification & MTDs | The REGS will send the Meter technical details that it holds and confirmation of live appointment to the Metering Service via the DIP | DIP | PUB-036 | AMSI | MHHS-BR-MS-007 | [MSAppActive] | Y | Evidence that Metering Service processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 280 | BP002 | 196 | MS | Manage MTD Discrepancies Check EES/IF-003 if MTDs missing | Metering Services can reconcile the meter technical received from Registrations compared to the Data flows received for Advanced For missing MTDs, check EES or IF-003 to validate that meters are installed on the MPAN. | N/A | N/A | N/A | MHHS-BR-MS-022
|  | 281 | BP002 |  | MS | MS requests counterparty to request missing MTDs | If meters are recorded in EES or REGS, MS/MOP requests counterparty for correct MTD | N/A | N/A | N/A
|  | 283 | BP002 |  | MS | MS/MOP sends correct details to MS | MS/MOP sends correct details to MS | N/A | N/A | N/A
|  | 285 | BP003 | 340 | DS | Manage Appointment Notification & Info | The REGS will send the Meter technical details that it holds and confirmation of live appointment to the data service, this will also contain who the Metering Service is. | DIP | PUB-036 | ADSI | MHHS-BR-DS-013 | [DSAppActive] | Y | Evidence that Data Service processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 290 | BP003 | 346 | DS | Manage MTD Discrepancies Check EES if MTDs missing | Data Services can reconcile the meter technical received from the REGS compared to the Data flows received for Traditional Metering Service For missing MTDs, check EES or IF-003 to validate that meters are installed on the MPAN. | N/A | N/A | N/A | MHHS-BR-DS-015 MHHS-BR-DS-016
|  | 291 | BP003 |  | DS | Manage MTD Discrepancies Check EES if MTDs missing | If meters are recorded in EES or REGS, MS/MOP requests counterparty for correct MTD | N/A | N/A | N/A
|  | 293 | BP003 |  | DS | MS/MOP sends correct details to MS | MS/MOP sends correct details to MS | N/A | N/A | N/A
| Collect HH Data | 295 | BP003 | 1007 | DS | Start to collect HH data | The incoming DS will start to collect HH data from the meter. | ADSI
|  | 300 | BP003 | 1010 | DS | End Point
| Issue MTDs via DTN (Advanced) | 305 | BP002 | 180 | MS | Issue MTDs via DTN (Advanced) | The New Metering Service will issue the meter technical details to Supplier | AMSI | D0268 | SUPC | MHHS-BR-MS-024 MHHS-BR-MS-023 |  | Y | Evidence that Supplier & Data Service processes the D0268 generated by Prospective Metering Service; log screenshots in downstream systems.
|  | 310 | BP002 | 191 | MS | Receive Advanced MTDs | The LDSO will receive Meter technical details from the new Metering Service via data flows. | AMSI | D0268 | LDSO | MHHS-BR-MS-024 |  | Y | Evidence that LDSO processes the D0268 generated by Prospective Metering Service; log screenshots in downstream systems.
| Publish Notification of Appointment to Data and Metering Services | 315 | BP002 | 270 | MS | MS Appointment Notification & MTD | The New Data Service will receive notification from the DIP containing the MTD's and confirmation of the new Metering Service | DIP | PUB-036 | ADSI | MHHS-BR-DS-002 MHHS-BR-DS-003 | [MSAppActive] | Y | Evidence that DIP generates a PUB-036, Evidence that Data Service process the PUB-036; log screenshots in downstream systems.
|  | 320 | BP002 | 271 | MS | Manage MTD Discrepancies if required | The NEW Data service will need to manage and discrepancies between the MTD's received from Metering Services and the MTD's received from the REGS. | N/A | N/A | N/A | MHHS-BR-DS-005 MHHS-BR-DS-006 MHHS-BR-DS-006.1
|  | 325 | BP003 | 281 | DS | DS Appointment Notification & MTD | The New metering Service will receive notification from the DIP containing confirmation of the new Data Service | DIP | PUB-036 | AMSC | MHHS-BR-MS-030 | [DSAppActive] | Y | Evidence that Metering Service processes the PUB-036 generated by DIP; log screenshots in downstream systems.
| Publish Notification of Appointment to LDSO | 330 | BP002 | 280 | MS | MS Appointment Notification & MTD | The LDSO will receive notification from the DIP containing the MTD's and confirmation of the new Metering Service | DIP | PUB-036 | LDSO | MHHS-BR-LD-003 MHHS-Migration-CoA(MS)-LDSO-001 | [MSAppActive] | Y | Evidence that LDSO processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 335 | BP002 | 281 | MS | Manage MTD Discrepancies if required | The LDSO will need to manage and discrepancies between the MTD's received from Metering Services and the MTD's received from the REGS. | N/A | N/A | N/A | MHHS-BR-LD-003
|  | 340 | BP002 | 282 | MS | END POINT | LDSO will continue with any BAU activity that may be required | N/A | N/A | N/A | N/A
|  | 345 | BP003 | 280 | DS | DS Appointment Notification & MTD | The LDSO Service will receive notification from the DIP containing confirmation of the new Data Service | DIP | PUB-036 | LDSO | MHHS-BR-LD-005 MHHS-Migration-CoA(DS)-LDSO-001 | [DSAppActive] | Y | Evidence that LDSO processes the PUB-036 generated by DIP; log screenshots in downstream systems.
| Publish Notification of Appointment to EES | 350 | BP002 | 283a | MS | MS Appointment Notification & MTD | EES will receive notification from the DIP containing the confirmation of the new Metering Service EES will not process the MTDs from the IF-036. Only the agent appointment information will be used. | DIP | PUB-036 | EES | MHHS-BR-RS-034 MHHS-BR-RS-037 MHHS-Migration-CoA(MS)-RS-016 | [MSAppActive] | Y | Evidence that EES processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 355 | BP002 | 283b | MS | MS Appointment Notification & MTD | The EES will set a status that the MPAN is under MHHS arrangements after at least one PUB-036 is received. | N/A | N/A | N/A |  |  | Y | Parties should be able to enquire via the portal and the API and see this status.
|  | 360 | BP003 | 279a | DS | DS Appointment Notification & MTD | EES will receive notification from the DIP containing confirmation of the new Data Service Note EES will not process the MTDs from the IF-036. Only the agent appointment information will be used. | DIP | PUB-036 | EES | MHHS-BR-EES-016.3 MHHS-Migration-CoA(DS)-EES-001 | [DSAppActive] | Y | Evidence that EES processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 365 | BP003 | 279b | DS | DS Appointment Notification & MTD | The EES will need to set a status that the MPAN is under MHHS arrangements after at least one PUB-036 is received. Parties should be able to enquire via the portal and the API and see this status. | N/A | N/A | N/A |  |  | Y | Parties should be able to enquire via the portal and the API and see this status.
| Publish Notification of Appointment to SUPC | 370 | BP002 | 260 | MS | Manage SP Confirmation and MTDs | Supplier will manage the Metering Service appointment and meter technical details received via D-flows | DIP | PUB-036 | SUPC | MHHS-BR-SU-013 | [MSAppActive] | Y | Evidence that Supplier processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 375 | BP002 | 201 | MS | Receive Advanced MTDs | The prospective Metering Service will send the meter technical details to Supplier | AMSI | D0268 | SUPC | MHHS-BR-SU-014 MHHS-BR-SU-015 |  | Y | Evidence that Supplier processes the D0268 generated by Metering Service; log screenshots in downstream systems.
|  | 380 | BP002 | 202 | MS | END POINT | Supplier will continue with their BAU processes where additional actions are required | N/A | N/A | N/A | N/A
|  | 385 | BP003 | 260 | DS | Manage DS Appointment | The REGS will publish confirmation of the live Data Service appointment to Supplier | DIP | PUB-036 | SUPC | MHHS-BR-SU-027 MHHS-Migration-CoA(DS)-SUP-006 | [DSAppActive] | Y | Evidence that Supplier processes the PUB-036 generated by DIP; log screenshots in downstream systems.
| SUPC sends D0151 to Outgoing MOP/DC | 390 | BP002 | 1005 | MS | Send D0151 | The Supplier will send a D0151 to the outgoing MOP. | SUPC | D0151 | Outgoing MOP | MHHS-Migration-CoA(MS)-SUP-002 MHHS-Migration-CoA(MS)-SUP-007 |  | Y | Evidence that Current Supplier has generated D0151; log screenshots in downstream systems.
|  | 395 | BP003 | 1016 | DS | Send D0151 | The outgoing Supplier will send a D0151 to the outgoing DC. | SUPC | D0151 | Outgoing DC | MHHS-Migration-CoA(DS)-SUP-005 MHHS-Migration-CoA(DS)-SUP-007 |  | Y | Evidence that Current Supplier has generated D0151; log screenshots in downstream systems.
| Validate Read, Generate AA, Deem Reading | 400 | BP003 | 1004 | DS | The Outgoing DC Validates read | The Outgoing DC Validates read |  |  |  | MHHS-Migration-CoA(DS)-DC-003 MHHS-Migration-CoA(DS)-DC-006 MHHS-Migration-CoA(DS)-DC-007
|  | 401 | BP003 | 1004 | DS | The Outgoing DC Generates an AA | The Outgoing DC Generates an AA |  |  |  | MHHS-Migration-CoA(DS)-DC-003 MHHS-Migration-CoA(DS)-DC-006 MHHS-Migration-CoA(DS)-DC-007
|  | 402 | BP003 | 1004 | DS | The Outgoing DC sends for a D0100/D0019 to Current Supplier | The Outgoing DC sends for a D0100/D0019 to Current Supplier | Outgoing DC (Stub) | D0010/D0019 | SUPC | MHHS-Migration-CoA(DS)-DC-003 MHHS-Migration-CoA(DS)-DC-006 MHHS-Migration-CoA(DS)-DC-007 |  | Y | Evidence that Current Supplier processes D0010/D0019 from stub; log screenshots in downstream systems.
|  | 403 | BP003 | 1004 | DS | If a reading is not received in 5 calendar days, the NHHDC will deem a reading. | If a reading is not received in 5 calendar days, the NHHDC will deem a reading. |  |  |  | MHHS-Migration-CoA(DS)-DC-003 MHHS-Migration-CoA(DS)-DC-006 MHHS-Migration-CoA(DS)-DC-007
|  | 405 | BP003 | 1011 | DS | Receive Read | Receive the D0010 | Outgoing DC (Stub) | D0010 | LDSO |  |  | Y | Evidence that LDSO processes D0010 from stub; log screenshots in downstream systems.
|  | 410 | BP003 | 1006 | DS | Receive Read | The outgoing DC will then share a read with the incumbent Supplier via a D0019/D0010 | Outgoing DC (Stub) | D0019 D0010 | SUPC |  |  | Y | Evidence that Current Supplier processes D0019/D0010 from stub; log screenshots in downstream systems.
|  | 415 | BP003 | 1009 | DS | End Point

## SIT-M-FM-COA-DeemRead-TC03 SNHH
Test Case Title | Key Journey Events | Step No | Business Process | BP Step | Service Type | Test Step/ Process Map Wording | Test Description | Trigger Sender | Interface ID | Trigger Receipient | Traceability Requirement | Message Input Event Code | Evidence Required | Key Validation & Test Evidence
SIT-M-FM-COA-MS-DS-TC03 | Determine Service Required | 5 | BP002 BP003 | 5 10 | MS & DS | Determine Metering Service Required | Supplier must identify the correct Market Segment | N/A | N/A | N/A | MS - MHHS-BR-SU-005 DS - MHHS-BR-SU-019 | N/A | N | N/A
| Setting up Appointments | 10 | BP002 | 20 | MS | Send Initial MS Appointment Request | Supplier will send the correct appointment details for the appropriate Service provider | SUPC | IF-031 | DIP | MHHS-BR-SU-006 MHHS-BR-SU-007 MHHS-Migration-CoA(MS)-SUP-001 MHHS-Migration-CoA(MS)-SUP-004 | [MSApp] | Y | http 202 response from DIP
|  | 15 | BP002 | 30 | MS | Publish Initial MS Appointment Request | The DIP will receive the appointment details from Supplier and publish them to the Registration Service. | DIP | PUB-031 | REGS | MHHS-BR-RS-009 | [MSApp] | Y | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems.
|  | 20 | BP003 | 20 | DS | Send Initial DS Appointment Request | Supplier will send the correct appointment details for the appropriate Service provider | SUPC | IF-031 | DIP | MHHS-BR-SU-020 MHHS-BR-SU-021 MHHS-Migration-CoA(DS)-SUP-002 MHHS-Migration-CoA(DS)-SUP-003 | [DSApp] | Y | http 202 response from DIP
|  | 25 | BP003 | 30 | DS | Publish Initial DS Appointment Request | The DIP will receive the appointment details from Supplier and publish them to the Registration Service. | DIP | PUB-031 | REGS | DIP | [DSApp] | Y | Evidence that REGS processes the PUB-031 generated by DIP; log screenshots in downstream systems.
| All Appointment Requests | 30 | BP002 | 45 | MS | Issue Initial MS Appointment Request Response for ALL requests | The REGS will respond to the DIP for the 'Supplier Service Appointment Request' with the appropriate response to Accept appointment. | REGS | IF-032 | DIP | MHHS-BR-RS-011 MHHS-BR-RS-012 MHHS-Migration-CoA(MS)-RS-010 MHHS-Migration-CoA(MS)-RS-012 MHHS-Migration-CoA(MS)-RS-014 | [MSAppInitialResp] | Y | http 202 response from DIP
|  | 35 | BP002 | 50 | MS | Publish Initial MS Appointment Request Response | The DIP will publish the REGS response to the 'Supplier Service Appointment Request' | DIP | PUB-032 | SUPC | DIP | [MSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
|  | 40 | BP002 | 55 | MS | Manage Initial MS Appointment Request Response | Supplier will receive response to the appointment request from the Registration Service and take the appropriate action dependant on outcome | DIP | PUB-032 | SUPC | MHHS-BR-SU-008 MHHS-BR-SU-009 | [MSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
|  | 45 | BP003 | 45 | DS | Issue Initial DS Appointment Request for all requests | The REGS will respond to the DIP for the 'Supplier Service Appointment Request' with the appropriate response to Accept appointment. | REGS | IF-032 | DIP | MHHS-BR-RS-045 MHHS-BR-RS-046 MHHS-Migration-CoA(DS)-RS-010 MHHS-Migration-CoA(DS)-RS-012 MHHS-Migration-CoA(DS)-RS-014 | [DSAppInitialResp] | Y | http 202 response from DIP
|  | 50 | BP003 | 50 | DS | Publish Initial DS Appointment Request Response | The DIP will publish the REGS response to the 'Supplier Service Appointment Request' | DIP | PUB-032 | SUPC | DIP | [DSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
|  | 55 | BP003 | 55 | DS | Manage Initial DS Appointment Request Response | Suppler will receive response to the appointment request from the Registration Service and take the appropriate action dependant on outcome | DIP | PUB-032 | SUPC | MHHS-BR-SU-022 MHHS-BR-SU-023 | [DSAppInitialResp] | Y | Evidence that Supplier processes the PUB-032 generated by DIP; log screenshots in downstream systems.
| Valid Requests Only | 60 | BP002 | 60 | MS | Issue Request MS Proposed Appointment Validation | The REGS will send 'REGS Request for Service Appointment' to the correct service provider via the DIP | REGS | IF-033 | DIP | MHHS-BR-RS-014.1 MHHS-BR-RS-015 | [MSAppSPRequest] | Y | http 202 response from DIP
|  | 65 | BP002 | 65 | MS | Publish Proposed MS Appointment Validation Request | The DIP will publish the 'REGS Request for Service Appointment' to the Metering Service | DIP | PUB-033 | SMSI | DIP | [MSAppSPRequest] | Y | Evidence that Metering Service processes the PUB-033 generated by DIP; log screenshots in downstream systems.
|  | 70 | BP002 | 70 | MS | Manage MS Proposed Appointment Validation Request | Metering Service will receive an appointment from the Supplier via the REGS. Metering Service must process and validate the appointment request as per the validation rules. Metering Service should be aware that an acceptance will result in the transfer of MPAN(s) | DIP | PUB-033 | SMSI | MHHS-BR-MS-001 | [MSAppSPRequest] | Y | Evidence that Metering Service processes the PUB-033 generated by DIP; log screenshots in downstream systems.
|  | 75 | BP002 | 75 | MS | Respond to MS Proposed Appointment Request | The Metering Service will accept the appointment request. | SMSI | IF-034 | DIP | MHHS-BR-MS-002 MHHS-BR-MS-003 | [MSAppSPResponse] | Y | http 202 response from DIP
|  | 80 | BP002 | 80 | MS | Publish Proposed MS Appointment Validation Response | The DIP will publish the responses from service providers | DIP | PUB-034 | REGS | DIP MHHS-Migration-CoA(MS)-SUP-005 | [MSAppSPResponse] | Y | Evidence that REGS processes the PUB-034 generated by DIP; log screenshots in downstream systems.
|  | 85 | BP002 | 85 | MS | Manage SP Prospective Appointment Response | The REGS will manage the appointment responses from the Metering Service and retain accepted responses in the background until the Effective from date when it will reflect as a live appointment | N/A | N/A | N/A | MHHS-BR-RS-016 MHHS-BR-RS-017 MHHS-Migration-CoA(MS)-RS-002 | N/A
|  | 90 | BP003 | 60 | DS | Issue Request DS Proposed Appointment | The REGS will send 'REGS Request for Service Appointment' to the correct Service provider via the DIP | REGS | IF-033 | DIP | MHHS-BR-RS-049 MHHS-BR-RS-048.1 | [DSAppSPRequest] | Y | http 202 response from DIP
|  | 95 | BP003 | 65 | DS | Publish Proposed DS Appointment Validation Request | The DIP will publish the 'REGS Request for Service Appointment' to the Data Service | DIP | PUB-033 | SDSI | DIP | [DSAppSPRequest] | Y | Evidence that Data Service processes the PUB-033 generated by DIP; log screenshots in downstream systems.
|  | 100 | BP003 | 220 | DS | Manage DS Appointment Request | Data Services will receive an appointment from the supplier via the REGS. Data services must process and validate the appointment request as per the validation rules | N/A | N/A | N/A | MHHS-BR-DS-007 MHHS-BR-DS-008 MHHS-BR-DS-011 | N/A
|  | 105 | BP003 | 221 | DS | Respond to DS Appointment Request - All outcomes - Acceptances | The Data Service will accept the appointment request. | SDSI | IF-034 | DIP | MHHS-BR-DS-008 MHHS-BR-DS-011 | [DSAppSPResponse] | Y | http 202 response from DIP
| Additional step for DS in case of Acceptances | 110 | BP003 | 230 | DS | 3rd Party Appointment | Once the Data Service has accepted the appointment they must appoint the nominated 3rd parties as per the agreed contract and the agreed method. | N/A | N/A | N/A | MHHS-BR-DS-009 MHHS-BR-DS-010 | N/A
| All Outcomes | 115 | BP003 | 80 | DS | Publish Proposed DS Appointment Validation Response | The DIP will publish the responses from Data services | DIP | PUB-034 | REGS | DIP MHHS-Migration-CoA(DS)-SUP-004 | [DSAppSPResponse] | Y | Evidence that REGS processes the PUB-034 generated by DIP; log screenshots in downstream systems.
|  | 120 | BP003 | 85 | DS | Manage SP Prospective Appointment Response | The REGS will manage the appointment responses from the Data services and retain accepted responses in the background until the Effective from date when it will reflect as a live appointment. The REGS must Publish all responses via the DIP and notify the metering service | REGS | IF-035 | DIP | MHHS-BR-RS-050 MHHS-BR-RS-051 MHHS-BR-RS-053 | [DSAppAccepted] | Y | http 202 response from DIP. Capture evidence that Metering Service has processed the IF-035 message from REGS.
| For All Appointment Responses | 125 | BP002 | 87 | MS | Issue MS Prospective Appointment Outcome | The REGS will send out all responses it has received from the Metering Services back to Supplier via the DIP. | REGS | IF-035 | DIP | MHHS-BR-RS-018 | [MSAppAccepted] | Y | http 202 response from DIP
|  | 130 | BP002 | 91 | MS | Publish Prospective Appointment Outcome Responses | The DIP will publish the Metering Service response for the appointment to Supplier. | DIP | PUB-035 | SUPC SMSI | DIP | [MSAppAccepted] | Y | Evidence that Supplier & Metering Services processes the PUB-035 generated by DIP; log screenshots in downstream systems.
|  | 135 | BP002 | 92 | MS | Manage MS Prospective Appointment Request Response | Metering Services will receive PUB-035 confirming the REGS has received the Metering Services response to the appointment | DIP | PUB-035 | SMSI | MHHS-BR-MS-006.1 | [MSAppAccepted] | Y | Evidence that Metering Service processes the PUB-035 generated by DIP; log screenshots in downstream systems.
|  | 140 | BP003 | 90 | DS | Publish Proposed Appointment Outcome Responses Step 86 : Step 91 : | The DIP will send out all responses it has received from the Data Services back to Supplier. | DIP | PUB-035 | SDSI SUPC | DIP | [DSAppAccepted] | Y | Evidence that Data Service & Supplier processes the PUB-035 generated by DIP; log screenshots in downstream systems.
|  | 145 | BP003 | 86 | DS | Receive Prospective Appointment Response | The Meter Service will receive accepted appointment responses from the REGSs | REGS | IF-035 | SMSC | MHHS-BR-RS-053 | [DSAppAccepted] | Y | Evidence that Metering Service processes the IF-035 generated by REGS; log screenshots in downstream systems.
|  | 150 | BP003 | 91 | DS | Manage DS Proposed Appointment Request Response | Data Services will receive PUB-035 confirming Registrations received the Data Services response to the appointment | DIP | PUB-035 | SDSI | MHHS-BR-DS-012.1 | [DSAppAccepted] | Y | Evidence that New Data Service processes the PUB-035 generated by DIP; log screenshots in downstream systems.
| Manage Prospective Appointment | 155 | BP002 | 95 | MS | Manage MS Prospective Appointment Request Response | Supplier will receive the publication of the Metering Service response to the appointment. Successful appointments will remain in a pending status until the effective from date. | DIP | PUB-035 | SUPC | MHHS-BR-SU-010 MHHS-BR-SU-011 | [MSAppAccepted] | Y | Evidence that Supplier processes the PUB-035 generated by DIP; log screenshots in downstream systems.
|  | 160 | BP003 | 95 | DS | Manage DS Proposed Appointment Request Response | Supplier will receive the publication for the Data Service response to the appointment. Successful appointments will remain in a pending status until the effective from date. | DIP | PUB-035 | SUPC | MHHS-BR-SU-024 MHHS-BR-SU-025 | [DSAppAccepted] | Y | Evidence that Supplier processes the PUB-035 generated by DIP; log screenshots in downstream systems.
| Determine further processing for Accepted Appointment Responses | 165 | BP002 | 100 | MS | Determine Processing Treatment - Prospective Appointments | For prospective appointments Registrations will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-020 MHHS-BR-RS-021 MHHS-BR-RS-023 | Interface Specifications
|  | 170 | BP003 | 100 | DS | Determine Processing Treatment - Prospective Appointments | For prospective appointments Registrations will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-054 MHHS-BR-RS-055 MHHS-BR-RS-057 MHHS-Migration-CoA(DS)-RS-001 | Interface Specifications
| Prospective Appointment Queue | 175 | BP002 | 101 | MS | Hold in Appointment Queue | For prospective appointments the REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-022 | Interface Specifications
|  | 180 | BP002 | 120 | MS | Review & Re-Validate Prospective Appointment(s) | For prospective appointments the REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect | N/A | N/A | N/A | MHHS-BR-RS-024 MHHS-BR-RS-025 MHHS-BR-RS-027 MHHS-BR-RS-028 MHHS-BR-RS-029 | Interface Specifications
|  | 185 | BP002 | 125 | MS | CSS Secured Notification | For prospective appointments the REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the Metering Service 'eff from date' comes into effect. | N/A | N/A | N/A | N/A | Interface Specifications
|  | 190 | BP003 | 101 | DS | Hold in Appointment Queue | For prospective appointments the REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the Data Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-056 | Interface Specifications
|  | 195 | BP003 | 120 | DS | Review & Re-Validate Prospective Appointment(s) | For prospective appointments the REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the data Service 'eff from date' comes into effect. | N/A | N/A | N/A | MHHS-BR-RS-058 MHHS-BR-RS-059 MHHS-BR-RS-061 MHHS-BR-RS-062 MHHS-BR-RS-063 | Interface Specifications
|  | 200 | BP003 | 125 | DS | CSS Secured Notification | For prospective appointments the REGS will hold these in a queue and re-process daily after the CSS updates have been received or until the Data Service 'eff from date' comes into effect. | N/A | N/A | N/A | N/A | Interface Specifications
| BP003A CSS/DCC Update Steps | 205 | BP003A | 5 | MS & DS | BP003A - CSS/DCC Update Steps | The Registration Service may need to update CSS or DCC with the MDR details. |  |  |  | N/A
|  | 210 | BP003A | 20 | MS & DS | REGS sends CSS0200 to CSS REGS also updates CSS of newly appointed MS | REGS sends CSS0200 to CSS REGS also updates CSS of newly appointed MS | REGS | CSS0200 | CSS | MHHS-BR-RS-078 MHHS-BR-RS-078.1 MHHS-BR-RS-078.2
|  | 215 | BP003A | 30 | MS & DS | CSS Updates internal records | CSS will update their internal records |  |  |  | CSS
|  | 220 | BP003A | 40 | MS & DS | CSS Updates DCC | CSS will update the DCC with the new Service provider details | CSS |  | DCC | CSS
|  | 225 | BP003A | 50 | MS & DS | DCC Receives Update from CSS | DCC will receive the CSS with the new Service provider details |  |  |  | DCC | [DCC-MDROutcome]
|  | 230 | BP003A | 60 | MS & DS | DCC Updates MDR Access Control Register | DCC will update their systems to reflect the access control register | DCC |  | CSS | DCC
|  | 235 | BP003A | 70 | MS & DS | Forward DCC Response to Registrations | DCC sends CSS0200 to CSS to confirm update and CSS will update the Registration Service | CSS | CSS0200 | REGS | CSS
|  | 240 | BP003A | 80 | MS & DS | CSS Response | CSS will issue DCC response to the Registration Service |  |  |  | MHHS-BR-RS-079
|  | 245 | BP003A | 90 | MS & DS | Update SDS with MDR outcome | REGS sends IF-035 in order to to update the appropriate SDS with the MDR outcome | REGS | IF-035 | DIP | MHHS-BR-RS-080 | [SDS-MDROutcome]
|  | 250 | BP003A | 91 | MS & DS | END POINT | Once the Registration Service has the update this is the end of the process |  |  |  | N/A
|  | 255 | BP003A | 100 | MS & DS | Receive Service Provider Update | The DIP will receive the update from the Registration Service |  |  |  | DIP
|  | 260 | BP003A | 110 | MS & DS | Publish Service Provider Update | The DIP will publish the update from the Registration Service | DIP | PUB-035 | Data Service Metering Service | DIP
|  | 265 | BP003A | 120 | MS & DS | Manage Service Provider Update | Data Service will receive the update from the DIP | DIP | PUB-035 | Data Service | MHHS-BR-DS-042.1
|  | 270 | BP003A | 121 | MS & DS | END POINT | Once Data Services has received the update this is the end of the process. Any additional activity required will be BAU processes |  |  |  | N/A
| Confirmed Appointments Only | 275 | BP002 | 240 | MS | Notify Prospective Appointment as Effective | The REGS will issue confirmation to the Metering Service their appointment is now active and send the meter technical details held in registration. They will also share the Data Service ID with the Metering Service. | REGS | IF-036 | DIP | MHHS-BR-RS-033 MHHS-Migration-CoA(MS)-RS-006 MHHS-Migration-CoA(MS)-RS-018 | [MSAppActive] | Y | http 202 response from DIP
|  | 280 | BP002 | 245 | MS | Publish Notification of Appointment (Acceptances) Step 195 - SMSI Step 280 - LDSO Step 283 - EES Step 270 - SDSC Step 260 - SUPC | The DIP will publish the Reg. Serv. Notification of Service App. & Supporting Info message. This will go to the Metering Service and the Smart Data Service as it will contain the Smart Meter technical details. | DIP | PUB-036 | SMSI SDSC SUPC LDSO EES | DIP MHHS-Migration-CoA(MS)-ECS-001 MHHS-Migration-CoA(MS)-RS-008 | [MSAppActive] | Y | Evidence that DIP generates a PUB-036; Evidence that Data Service, SUPC, Metering Service and EES process the PUB-036; log screenshots in downstream systems.
|  | 285 | BP003 | 250 | DS | Notify Prospective Appointment as Effective | The REGS will issue confirmation to the Data Service their appointment is now active and send the meter technical details held in registration. They will also share the Metering Service ID with the Metering Service. | REGS | IF-036 | DIP | MHHS-BR-RS-067 MHHS-Migration-CoA(DS)-RS-018 MHHS-Migration-CoA(DS)-RS-019 | [DSAppActive] | Y | http 202 response from DIP
|  | 290 | BP003 | 255 | DS | Publish Notification of Appointment (Acceptances) Step 340 - SDSI Step 280 - LDSO Step 279 - EES Step 281 - SMSC Step 260 - SUPC | The DIP will publish the Reg. Serv. Notification of Service App. & Supporting Info message. This will go to the Data Service and the Metering Service as it will contain the Smart Meter technical details. | DIP | PUB-036 | SDSI SUPC LDSO SMSC EES | DIP MHHS-Migration-CoA(DS)-RS-006 MHHS-Migration-CoA(DS)-ECS-001 | [DSAppActive] | Y | Evidence that DIP generates a PUB-036, Evidence that Data Service, SUPC, LDSO, Metering Service and EES process the PUB-036; log screenshots in downstream systems.
| MDS is notified of DS appointment activation | 295 | BP003 | 255 | DS | MDS receives PUB-036 | MDS receives PUB-036 with details of Data Services Appointment Active | DIP | PUB-036 | MDS |  | [DSAppActive] | Y | MDS receives PUB-036 DSAppActive with details of Data Services Appointment Active successfully updates on downstream systems. Capture test evidence in the form of logs / screenshots from downstream systems/apps.
| Issue MTDs | 300 | BP002 | 160 | MS | Issue MTD to Metering Service | The existing Metering Service will receive notification of who the prospective Metering Service is from the Registrations service. Metering Service will send the meter technical details to the prospective Metering Service. No transfer of data is required for SMART. Note: if no meter is installed, no MTDs should be sent. | REGS | D0170 | Outgoing MOP | MHHS-BR-MS-006 MHHS-Migration-CoA(MS)-MOP-002 MHHS-Migration-CoA(MS)-MOP-006 | [MSAppAccepted] | Y | Evidence that REGS generates the D0170; log screenshots in downstream systems.
|  | 305 | BP002 | 1004 | MS | Process Ends | In the case of Smart Meters, the outgoing MOP does not send on MTDs and the process for this logic thread ends.
| Notify Legacy agent of migration | 310 | BP002 | 1000 | MS | Send D0170 | If appointment accepted, the REGS will send a D0170 to the outgoing MOP. This flow informs the MOP of the identity of the new MS to which it will need to transfer MTDs and it also informs the MOP of the intent to migrate the MPAN. | REGS | D0170 | Outgoing MOP | MHHS-Migration-CoA(MS)-RS-001 |  | Y | Evidence that REGS has generated D0170; log screenshots in downstream systems.
|  | 315 | BP002 | 1001 | MS | (1) Receive D0170 from REGS (2) Send MTDs | Outgoing MOP to receive the D0170 from the REGS and send MTDs to the new MS. The D0170 will inform the old MOP of the identity of the new MS. | REGS | D0170 | Outgoing MOP | MHHS-Migration-CoA(MS)-MOP-001 |  | Y | (1) Evidence that REGS generates a D0170; log screenshots in downstream systems.
|  | 320 | BP003 | 1002 | DS | Send D0170 to request Transfer of Read data | The REGS will send a D0170 to the outgoing DC. This flow informs the DC of the identity of the new DS. | REGS | D0170 | Outgoing DC |  |  | Y | Evidence that REGS has generated D0170; log screenshots in downstream systems.
|  | 325 | BP003 | 1003 | DS | Receive D0170 with instructions for migration | The outgoing DC will receive the D0170 with the instructions for migration and info about the new DS. | REGS | D0170 | Outgoing DC |  |  | Y | Evidence that REGS has generated D0170; log screenshots in downstream systems.
|  | 330 | BP003 | 1016 | DS | Start Point - Supply Start Date | The Supply Start Date will be the trigger for the incoming DS to start collecting reads | N/A | N/A | N/A
|  | 335 | BP003 | 1004 | DS | Retrieve Midnight Read from Smart Meter | The incoming DS will retrieve a read from the Smart Meter and send this onto the DIP via an IF-041. (As per BAU Process) | SDSI | IF-041 | DIP | MHHS-Migration-CoA(DS)-DS-001 |  | Y | http 202 response from DIP
|  | 340 | BP003 | 1005 | DS | Issue PUB-041 | The DIP will receive an IF-041 from the incoming DS and share this with the current Supplier (CoA) (As per BAU Process) | DIP | PUB-041 | SUPC | MHHS-Migration-CoA(DS)-DS-002 |  | Y | Evidence that SUPC processes PUC-041 from DIP; log screenshots in downstream systems.
|  | 345 | BP003 | 1006 | DS | Receive PUB-041 | The Current Supplier (CoA) will receive a meter read via a PUB-041 from the DIP. (As per BAU Process) | DIP | PUB-041 | SUPC
|  | 350 | BP003 | 1007 | DS | Obtain read from Smart Meter and validate | The current Supplier (CoA) will retrieve a read from the Smart meter and validate this read before sending a D010 to the outgoing DC (CoA) In this case, the D0010 will be built so that it enables the outgoing DC to finalise settlement (CoA) (As per legacy process) | SUPC | D0010 | Outgoing DC |  |  | Y | Evidence that SUPC generates a D0010; log screenshots in downstream systems.
| Receive Appointment Notification & Manage MTD descrepancies | 355 | BP002 | 195 | MS | Receive Appointment Notification & MTDs | The REGS will send the Meter technical details that it holds and confirmation of live appointment to the Metering Service via the DIP | DIP | PUB-036 | SMSI | MHHS-BR-MS-007 | [MSAppActive] | Y | Evidence that Metering Service processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 360 | BP002 |  | MS | MS requests counterparty to request missing MTDs | If meters are recorded in EES or REGS, MS/MOP requests counterparty for correct MTD | N/A | N/A | N/A
|  | 365 | BP002 |  | MS | MS/MOP sends correct details to MS | MS/MOP sends correct details to MS | N/A | N/A | N/A
|  | 370 | BP003 | 340 | DS | Manage Appointment Notification & Info | The REGS will send the Meter technical details that it holds and confirmation of live appointment to the data service, this will also contain who the Metering Service is. | DIP | PUB-036 | SDSI | MHHS-BR-DS-013 | [DSAppActive] | Y | Evidence that Data Service processes the PUB-036 generated by DIP; log screenshots in downstream systems.
| Publish Notification of Appointment to LDSO | 375 | BP002 | 280 | MS | MS Appointment Notification & MTD | The LDSO will receive notification from the DIP containing the Smart MTD's and confirmation of the new Metering Service | DIP | PUB-036 | LDSO | MHHS-BR-LD-003 MHHS-Migration-CoA(MS)-LDSO-001 | [MSAppActive] | Y | Evidence that LDSO processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 380 | BP002 | 281 | MS | Manage MTD Discrepancies if required | The LDSO will need to manage and discrepancies between the MTD's received from Metering Services and the MTD's received from the REGS. | DIP | PUB-037 | SMSC | MHHS-BR-LD-003 |  | Y | Evidence that SMSC processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 385 | BP002 | 282 | MS | END POINT | LDSO will continue with any BAU activity that may be required | N/A | N/A | N/A | N/A
|  | 390 | BP003 | 280 | DS | DS Appointment Notification & MTD | The LDSO Service will receive notification from the DIP containing confirmation of the new Data Service | DIP | PUB-036 | LDSO | MHHS-BR-LD-005 MHHS-Migration-CoA(DS)-LDSO-001 | [DSAppActive] | Y | Evidence that LDSO processes the PUB-036 generated by DIP; log screenshots in downstream systems.
| Publish Notification of Appointment to EES | 395 | BP002 | 283a | MS | MS Appointment Notification & MTD | EES will receive notification from the DIP containing the Smart MTD's and confirmation of the new Metering Service EES will not process the MTDs from the IF-036. Only the agent appointment information will be used. | DIP | PUB-036 | EES | MHHS-BR-RS-034 MHHS-BR-RS-037 MHHS-Migration-CoA(MS)-RS-016 | [MSAppActive] | Y | Evidence that EES processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 400 | BP002 | 283b | MS | MS Appointment Notification & MTD | The EES will set a status that the MPAN is under MHHS arrangements after at least one PUB-036 is received. | N/A | N/A | N/A |  |  | Y | Parties should be able to enquire via the portal and the API and see this status.
|  | 405 | BP003 | 279a | DS | DS Appointment Notification & MTD | EES will receive notification from the DIP containing confirmation of the new Data Service EES will not process the MTDs from the IF-036. Only the agent appointment information will be used. | DIP | PUB-036 | EES | MHHS-BR-EES-016.3 MHHS-Migration-CoA(DS)-EES-001 | [DSAppActive] | Y | Evidence that EES processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 410 | BP003 | 279b | DS | DS Appointment Notification & MTD | Note: The EES will need to set a status that the MPAN is under MHHS arrangements after at least one PUB-036 is received. Parties should be able to enquire via the portal and the API and see this status. | N/A | N/A | N/A |  |  | Y | Parties should be able to enquire via the portal and the API and see this status.
| Publish Notification of Appointment to Data and Metering Services | 415 | BP002 | 270 | MS | MS Appointment Notification & MTD | The New Data Service will receive notification from the DIP containing the Smart MTD's and confirmation of the new Metering Service | DIP | PUB-036 | SDSI | MHHS-BR-DS-002 MHHS-BR-DS-003 | [MSAppActive] | Y | Evidence that DIP generates a PUB-036, Evidence that Data Service process the PUB-036; log screenshots in downstream systems.
|  | 420 | BP002 | 271 | MS | Manage MTD Discrepancies if required | The NEW Data service will need to manage and discrepancies between the MTD's received from Metering Services and the MTD's received from the REGS. | N/A | N/A | N/A | MHHS-BR-DS-005 MHHS-BR-DS-006 MHHS-BR-DS-006.1
|  | 425 | BP003 | 281 | DS | DS Appointment Notification & MTD | The New metering Service will receive notification from the DIP containing confirmation of the new Data Service | DIP | PUB-036 | SMSC | MHHS-BR-MS-030 | [DSAppActive] | Y | Evidence that Metering Service processes the PUB-036 generated by DIP; log screenshots in downstream systems.
| Publish Notification of Appointment to SUPC | 430 | BP002 | 260 | MS | Manage SP Confirmation and MTDs | Supplier will manage the Metering Service appointment | DIP | PUB-036 | SUPC | MHHS-BR-SU-013 | [MSAppActive] | Y | Evidence that Supplier processes the PUB-036 generated by DIP; log screenshots in downstream systems.
|  | 435 | BP003 | 260 | DS | Manage DS Appointment | The REGS will publish confirmation of the live Data Service appointment to Supplier | DIP | PUB-036 | SUPC | MHHS-BR-SU-027 MHHS-Migration-CoA(DS)-SUP-006 | [DSAppActive] | Y | Evidence that Supplier processes the PUB-036 generated by DIP; log screenshots in downstream systems.
| SUPC sends D0151 to Outgoing MOP/DC | 440 | BP002 | 1005 | MS | Send D0151 | The Supplier will send a D0151 to the outgoing MOP. | SUPC | D0151 | Outgoing MOP | MHHS-Migration-CoA(MS)-SUP-002 MHHS-Migration-CoA(MS)-SUP-007 |  | Y | Evidence that Current Supplier has generated D0151; log screenshots in downstream systems.
|  | 445 | BP003 | 1016 | DS | Send D0151 | The outgoing Supplier will send a D0151 to the outgoing DC. | SUPC | D0151 | Outgoing DC | MHHS-Migration-CoA(DS)-SUP-005 MHHS-Migration-CoA(DS)-SUP-007 |  | Y | Evidence that Current Supplier has generated D0151; log screenshots in downstream systems.
| Validate Read, Generate AA, Deem Reading | 450 | BP003 | 1011 | DS | The Outgoing DC Validates read | The Outgoing DC Validates read |  |  |  | MHHS-Migration-CoA(DS)-DC-003 MHHS-Migration-CoA(DS)-DC-006 MHHS-Migration-CoA(DS)-DC-007
|  | 455 | BP003 | 1011 | DS | The Outgoing DC Generates an AA | The Outgoing DC Generates an AA |  |  |  | MHHS-Migration-CoA(DS)-DC-003 MHHS-Migration-CoA(DS)-DC-006 MHHS-Migration-CoA(DS)-DC-007
|  | 460 | BP003 | 1011 | DS | The Outgoing DC sends for a D0100/D0019 to Current Supplier | The Outgoing DC sends for a D0100/D0019 to Current Supplier | Outgoing DC (Stub) | D0010 | SUPC | MHHS-Migration-CoA(DS)-DC-003 MHHS-Migration-CoA(DS)-DC-006 MHHS-Migration-CoA(DS)-DC-007 |  | Y | Evidence that Current Supplier processes D0010/D0019 from stub; log screenshots in downstream systems.
|  | 465 | BP003 | 1011 | DS | If a reading is not received in 5 calendar days, the NHHDC will deem a reading. | If a reading is not received in 5 calendar days, the NHHDC will deem a reading. |  |  |  | MHHS-Migration-CoA(DS)-DC-003 MHHS-Migration-CoA(DS)-DC-006 MHHS-Migration-CoA(DS)-DC-007
|  | 470 | BP003 | 1017 | DS | Receive Read | The LDSO will receive the D0010 from the outgoing DC | Outgoing DC (Stub) | D0010 | LDSO |  |  | Y | Evidence that the LDSO processes a D0010 from stub; log screenshots in downstream systems.
|  | 475 | BP003 | 1014 | DS | Receive Read | The current Supplier will receive a D0010 / D0019 from the outgoing DC | Outgoing DC (Stub) | D0019 D0010 | SUPC | MHHS-Migration-CoA(DS)-SUP-011 |  | Y | Evidence that Current Supplier processes D0019/D0010 from stub; log screenshots in downstream systems.
|  | 480 | BP003 | 1015 | DS | End Point